## H2 2010 Spring Outage
Location | Type | Crew | Project | Work Order | Description | EstHrs
ST002ASHASPASHSLUICEPMPS | ELEC | RDE1 | ST210SPT | 5994189 | PM-H-2-DRAIN & REFILL OIL "C" ASH SLUICE PUMP MOTOR | 1.5
ST002ASHASPASHSLUICEPMPS | ELEC | RDE1 | ST210SPT | 5994191 | PM-H-2-DRAIN & REFILL OIL "D" ASH SLUICE PUMP MOTOR | 1.5
ST002ASHCTRCONTROLS | ELEC | RDE1 | ST210SPG | 5990285 | PM-H-2 OUTAGE FLYASH CONTROLS CLEAN & CHECK | 2
ST002ASHARSBOTASHREMOVAL | MECH | STOC | ST210SPG | 5989422 | PM-H-2 OUTAGE INSECTION OF WET BOTTOM LANCING DOORS | 10
ST002ASHARSBOTASHREMOVAL | OTH | STOC | ST210SPG | 5989460 | PM-H-2 OUTAGE PM OF WEST HYDROEJECTOR | 94
ST002ASHARSBOTASHREMOVAL | OTH | STOC | ST210SPG | 5989462 | PM-H-2 OUTAGE PM OF EAST HYDROEJECTOR | 94
ST002ASHARSHOPPERBOTASH | MECH | STOC | ST210SPG | 5989412 | H-2 Wet Bottom Refrac needs to be repaired during the pitstop outage on 1-16-10 found damage | 160
ST002ASHARSHOPPERBOTASH | MECH | STOC | ST210SPG | 5989474 | PM-H-2 OUTAGE INSPECTION "B" ASH GATE HOUSING | 20
ST002ASHARSHOPPERBOTASH | MECH | STOC | ST210SPG | 5989476 | PM-H-2 OUTAGE INSPECTION "A" ASH GATE HOUSING | 20
ST002ASHARSHOPPERBOTASH | MECH | STOC | ST210SPG | 5994297 | H-2 Metal behind the west and East equalizing valves needs to be replaced | 60
ST002ASHARSHOPPERBOTASH | MECH | STOC | ST210SPG | 5994298 | H-2 Weset and East Equalizing valves needs to be replaced | 40
ST002ASHARSSLAGGRINDERS | MECH | STOC | BP10S021B | 5985158 | H2 A Slag Grinder Replacement Capital | 130
ST002ASHARSSLAGGRINDERS | MECH | STOC | BP10S021B | 5985162 | H2 B Slag Grinder Replacement Capital | 130
ST002ASHARSWETBTMPIPING | MECH | STOC | ST210SPG | 5989415 | H-2 Refrac cooling water header South Side needs to be replaced | 90
ST002ASHARSWETBTMPIPING | MECH | STOC | ST210SPG | 5989578 | outter flushing jets leaking at fitting going into the east side of H2- | 8
ST002ASHARSWETBTMPIPING | OTH | STOC | ST210SPG | 5989455 | PM-H-2 OUTAGE INSPECTION OF REFRACTORY COOLING SYSTEM | 150.6
ST002ASHFARFLYASHSYSTEM | MECH | STOC | ST210SPG | 5988044 | Install economizer hopper drains to accommodate wasing of the ecoomizer tubes. | 60
ST002ASHFARFLYASHSYSTEM | MECH | STOC | ST210SPG | 5989441 | PM-H-2 OUTAGE REPLACEMENT ECONOMIZER HOPPER VALVES | 60
ST002ASHFARFLYASHSYSTEM | MECH | STOC | ST210SPG | 5989443 | PM-H-2 OUTAGE REPLACEMENT PRECIPITATOR HOPPER VALVES | 81
ST002BFWFWCATTEMPERATION | INST | RDI1 | ST210SPG | 5994170 | H2 SUPERHEAT SPRAY BLOCK VALVES EAST AND WEST NEED LIMIT SWITCHS INSTALLED | 12
ST002BFWFWCATTEMPERATION | INST | RDI1 | ST210SPG | 5993430 | PM-H-2 OUTAGE-E&W R.H. SPRAY CONTROL VALVE CHECKS. | 4
ST002BFWFWCATTEMPERATION | INST | RDI1 | ST210SPG | 5993431 | PM-H-2 OUTAGE-E&W S.H. SPRAY CONTROL VALVE CHECKS. | 4
ST002BFWFWCATTEMPERATION | INST | RDI1 | ST210SPG | 5994167 | H2 REHEAT SPRAY BLOCK VALVE EAST AND WEST NEED LIMIT SWITCHS INSTALLED | 12
ST002BFWFWCBOILERFEEDPUMPS | INST | RDI1 | ST210SPG | 5922533 | h-2 A boiler feed pump on a pitstop we need to set the | 4
ST002BFWFWCDASTORAGETANK | INST | RDI1 | ST210SPG | 5842261 | high level switch not working correct | 3
ST002BFWFWCDASTORAGETANK | INST | RDI1 | ST210SPG | 5993357 | PM-H-2 OUTAGE D.A. LEVEL SWITCHES CHECK OPERATION | 4
ST002BFWFWCF.W.HEATERS | INST | RDI1 | ST210SPG | 5993356 | PM-H-2 OUTAGE H.P. HEATER LEVEL ALARMS CHECK OPERATION | 8
ST002BFWFWCF.W.HEATERS | INST | RDI1 | ST210SPG | 5993427 | PM-H-2 OUTAGE-H.P. HTR LEVEL CONTROL & VALVE CHECK OPERATION. | 10
ST002BFWFWCPIPINGTOECONOMIZER | INST | RDI1 | ST210SPG | 5993591 | PM-H-2 OUTAGE - FEEDWATER CONTROL VALVE CHECK OPERATION. | 2
ST002BFWFWCBOILERFEEDPUMPS | MECH | RDM3 | ST210SPG | 5989544 | PM-H-2 OUTAGE INSPEC OF "A" BOILER FEED PUMP COUPLING | 20
ST002BFWFWCBOILERFEEDPUMPS | MECH | RDM3 | ST210SPG | 5989546 | PM-H-2 OUTAGE INSPEC OF "B" BOILER FEED PUMP COUPLING | 20
ST002BFWFWCBOILERFEEDPUMPS | MECH | RDM3 | ST210SPG | 5989552 | PM-H-2 OUTAGE "A" BOILER FEED PUMPS LUB. INSPECTION | 6
ST002BFWFWCBOILERFEEDPUMPS | MECH | RDM3 | ST210SPG | 5989554 | PM-H-2 OUTAGE "B" BOILER FEED PUMPS LUB. INSPECTION | 6
ST002BFWFWCPIPINGTOECONOMIZER | MECH | RDM3 | ST210SPG | 5940256 | Install supply line to redundant feedwater flow transmitter | 16
ST002BFWFWCDASTORAGETANK | MECH | STOC | ST210SPG | 5989531 | PM-H-2 OUTAGE INSPECTION OF DEAERATOR STORAGE TANK | 63
ST002BFWFWCF.W.HEATERS | MECH | STOC | ST210SPG | 5995573 | H2 #6 HP FW heater vent blocks are leaking at the unions. | 32
ST002BFWFWCFEEDWATERSYSTEM | MECH | STOC | ST210SPG | 5988383 | H-2 FEED WATER OUT OF #6 HEATER BY B-2 COAL FEEDER BOTH DRAIN VALVES LEAKING THROUGH | 12
ST002BFWFWCFEEDWATERSYSTEM | MECH | STOC | BP10S015B | 5990271 | H-2 Install MOV valves on #2 #3 #5 & #6 Feedwater Heaters | 300
ST002BFWFWCPIPINGTOECONOMIZER | MECH | STOC | ST210SPG | 5995556 | H-2 A BFP Discharge Valve Leaking thru | 60
ST002BFWFWCRECIRCSYSTEM | MECH | STOC | ST210SPG | 5975432 | Rebuild H2 A Boiler Feed Pump Discharge Check Valve | 100
ST002BFWFWCRECIRCSYSTEM | MECH | STOC | ST210SPG | 5975435 | Rebuild H2 B Boiler Feed Pump Discharge Check Valve | 100
ST002CDSCSCCONDENSATEPUMP | ELEC | RDE1 | ST210SPT | 5994193 | PM-H-2-DRAIN & REFILL OIL "A" CONDENSATE PUMP MOTOR | 1.5
ST002CDSCSCCONDENSATEPUMP | ELEC | RDE1 | ST210SPT | 5994195 | PM-H-2-DRAIN & REFILL OIL "B" CONDENSATE PUMP MOTOR | 1.5
ST002CDSCSCCONDENSATEPUMP | ELEC | RDE1 | ST210SPT | 5994197 | PM-H-2-DRAIN & REFILL OIL "A" HEATER DRIP PUMP MOTOR | 1.5
ST002CDSCSCCONDENSATEPUMP | ELEC | RDE1 | ST210SPT | 5994199 | PM-H-2-DRAIN & REFILL OIL "B" HEATER DRIP PUMP MOTOR | 1.5
ST002CDSCSCCONDDRAINTANK | INST | RDI1 | ST210SPG | 5993445 | PM-H-2 Outage L.P. Drain Tank Check Controls. | 2
ST002CDSCSCLOWPRESSUREHEATERS | INST | RDI1 | ST210SPG | 5994258 | #1 HEATER LOW LEVEL ALARM IN & OUT, CONTROLER | 2
ST002CDSCSCLOWPRESSUREHEATERS | INST | RDI1 | ST210SPG | 5993426 | PM-H-2 OUTAGE-L.P. HTR. LEVEL CONTROL & VALVE CHECK OPERATION | 20
ST002CDSCSCLOWPRESSUREHEATERS | INST | RDI1 | ST210SPG | 5993504 | PM-H-2 OUTAGE L.P. HEATER LEVEL ALARMS CHECK OPERATION | 8
ST002CDSCSCGLANDSTEAMSYSTEM | MECH | RDM3 | ST210SPG | 5989567 | PM-H-2 OUTAGE INSPECTION "A" & "B" GLAND EXHAUSTER FANS | 10
ST002CDSCSCLOWPRESSUREHEATERS | MECH | STOC | ST210SPG | 5989533 | PM-H-2 OUTAGE INSPECTION OF DEAERATOR HEATER | 210
ST002CDSCSCLOWPRESSUREHEATERS | MECH | STOC | ST210SPG | 5989531 | PM-H-2 OUTAGE INSPECTION OF DEAERATOR STORAGE TANK | 63
ST002CWSCCSCONDENSERSYSTEM | ELEC | RDE1 | ST210SPT | 5991400 | PM-H-2 OUTAGE SEND OUT "A" VACUUM PUMP MOTOR | 1
ST002CWSCCSCONDENSERSYSTEM | ELEC | RDE1 | ST210SPT | 5991448 | PM-H-2 OUTAGE SEND OUT "B" VACUUM PUMP MOTOR | 1
ST002CWSCCSCOOLINGTOWERSYSTEM | ELEC | RDE1 | ST210SPG | 5990800 | PM-H-2 OUTAGE C.T. TOWER LUBE SYSTEM CHECK | 2
ST002CWSCCSCONDENSERSYSTEM | INST | RDI1 | ST210SPT | 5952088 | vac. pump suction valve has to be overiden to work. | 2
ST002CWSCCSCONDENSERSYSTEM | INST | RDI1 | ST210SPT | 5977616 | both A and B suction valves have to be overode to work | 4
ST002CWSCCSCONDENSERSYSTEM | INST | RDI1 | ST210SPT | 5993358 | PM-H-2 OUTAGE HOTWELL LEVEL SWITCHES CHECK OPERATION | 2
ST002CWSCCSCONDENSERSYSTEM | INST | RDI1 | ST210SPT | 5993428 | PM-H-2 OUTAGE-CONDENSER LEVEL CONTROL & VALVE CHECKS. | 3
ST002CWSCCSCONDENSERSYSTEM | MECH | RDM3 | ST210SPG | 5989529 | PM-H-2 OUTAGE INSPECT CONDENSER DOORS | 2
ST002CWSCCSCONDENSERSYSTEM | MECH | RDM3 | ST210SPG | 5989576 | PM-H-2 OUTAGE - CHECK STEAM WASHING OF CONDENSER TUBES | 60
ST002CWSCCSCOOLINGTOWERSYSTEM | MECH | RDM3 | ST210SPG | 5989542 | PM-H-2 OUTAGE INSPECTION OF NORTH COOLING TOWER | 129
ST002CW-CWSCOOLINGWTRSYS | MECH | STOC | ST210SPG | 5989526 | PM-H-2 OUTAGE OPEN & CLOSE HEAT EXCHANGER | 120
ST002CWSCCSCOOLINGTOWERSYSTEM | MECH | STOC | ST210SPG | 5989483 | PM-H-2 OUTAGE OUTSIDE VENDOR INSPECT NORTH COOLING TOWER | 0.5
ST002CWSCCSCOOLINGTOWERSYSTEM | OTH | STOC | BP10S011B | 5993176 | Replace H2 Cooling Tower Fill on cells A,B, and C | 1
ST002EDTDCSDCDIST.SYSTEM | ELEC | RDE1 | ST210SPG | 5990292 | PM-H-2 OUTAGE BATTERY CHARGER CLEAN & CHECK | 8
ST002EDTDCSDCDIST.SYSTEM | ELEC | RDE1 | ST210SPT | 5990768 | PM-H-2 OUTAGE LOAD TEST BATTERIES | 8
ST002EDTMCCMTR.CONT.CENTER | ELEC | RDE1 | ST210SPG | 5990299 | PM-H-2 OUTAGE - 480V MCC CLEAN & CHECK | 18
ST002EDTMCCMTR.CONT.CENTER | ELEC | RDE1 | ST210SPG | 5990317 | PM-H-2 OUTAGE COOLING TOWER MCC | 2
ST002EDTMCCMTR.CONT.CENTER | ELEC | RDE1 | ST210SPG | 5990325 | PM-H-2 OUTAGE 480V SOLID STATE TRIP DEVICE TEST | 60
ST002EDTMCCMTR.CONT.CENTER | ELEC | RDE1 | ST210SPT | 5992166 | PM-H-2 OUTAGE - SCR 480V MCC CLEAN & CHECK | 20
ST002EDTTSG4160VSWITCHGEAR | ELEC | RDE1 | ST210SPG | 5990295 | PM-H-2 OUTAGE - 4160V SWITCHGEAR CLEAN & CHECK | 75
ST002EDTTSG4160VSWITCHGEAR | ELEC | RDE1 | ST210SPT | 5992045 | PM-H-2 OUTAGE - SCRUBBER 4160 SWITCHGEAR CLEAN & CHECK | 40
ST002EDTTSG4160VSWITCHGEAR | ELEC | RDE1 | ST210SPT | 5992420 | PM-H-2 OUTAGE CLEAN AND CHECK "A" AUX PT.S | 14
ST002EDTTSG4160VSWITCHGEAR | ELEC | RDE1 | ST210SPT | 5992486 | PM-H-2 OUTAGE CLEAN AND CHECK "B" AUX PT.S | 14
ST002EDTTSG4160VSWITCHGEAR | ELEC | RDE1 | ST210SPT | 5992553 | PM-H-2 OUTAGE CLEAN AND CHECK "A" STARTUP PT.S | 14
ST002EDTTSG4160VSWITCHGEAR | ELEC | RDE1 | ST210SPT | 5992621 | PM-H-2 OUTAGE CLEAN AND CHECK "B" STARTUP PT.S | 14
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPG | 5990304 | PM-H-2 OUTAGE 480V SUBSTATION BREAKERS CLEAN & CHECK | 20
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPG | 5990310 | PM-H-2 OUTAGE 480V TRANSFORMERS CLEAN & CHECK | 16
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPT | 5991497 | PM-H-2 OUTAGE CLEAN/INSPECT C.T. 2A PCC 480 VOLT BUS | 20
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPT | 5991547 | PM-H-2 OUTAGE CLEAN/INSPECT 2A PCC 480 MAIN & TIE BREAKER | 20
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPT | 5991598 | PM-H-2 OUTAGE CLEAN/INSPECT C.T. 2B PCC 480 VOLT BUS | 20
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPT | 5991650 | PM-H-2 OUTAGE CLEAN/INSPECT 2B PCC 480 MAIN & TIE BREAKER | 20
ST002EDTTSG480VBUS | ELEC | RDE1 | ST210SPT | 5992228 | PM-H-2 OUTAGE SCRUBBER 480V SUBSTATION CLEAN & CHECK | 5
ST002EDTTSGSCRUBBERTRANSFMR | ELEC | RDE1 | ST210SPT | 5992105 | PM-H-2 OUTAGE - SCRUBBER 'B' TRANSFORMER CLEAN AND INSPECT | 20
ST002EDTTSGSTEPUPTRANSFMR | ELEC | RDE1 | ST210SPT | 5992355 | PM-H-2 OUTAGE GROUND LEADS ON STEPUP TRANSFORMER | 10
ST002EDTMCCMTR.CONT.CENTER | OTH | STOC | ST210SPT | 5986463 | PM-H-2 OUTAGE SEND OUT THE FOLLOWING MOTORS (see W.O. Hierarchy) | 3
ST002EVSAE-AIREMISSIONS | INST | RDI1 | ST210SPG | 5993338 | PM-H-2 OUTAGE CEM EQUIPMENT CLEAN & CHECK. | 8
ST002FGDCTWCONTROLSYSTEM | ELEC | RDE1 | WK09S036B | 5994327 | H-2 OUTAGE-ELECTRICAL ASSIST IN SCRUBBER CONTROLS INSTALLATION | 102
ST002FGDSSCBOOSTERFANH-2 | ELEC | RDE1 | ST210SPT | 5994201 | PM-H-2 DRAIN & REFILL OIL ON "B" BOOSTER FAN MOTOR | 3
ST002FGDCTWCONTROLSYSTEM | INST | RDI1 | ST210SPS | 5993449 | PM-H-2 Outage Scrubber Inspect Instrumentation & Calibrate. | 20
ST002FGDCTWCONTROLSYSTEM | INST | RDI1 | ST210SPS | 5993853 | FUSE BLOWN IN DCS GOING TO MFT (SEE REGY) | 6
ST002FGDCTWCONTROLSYSTEM | INST | RDI1 | WK09S036B | 5994323 | H-2 OUTAGE-INSTRUMENT ASSIST IN SCRUBBER CONTROLS INSTALLATION | 146
ST002FGDSSCBOOSTERFANH-2 | INST | RDI1 | ST210SPS | 5987037 | H-2 BOOSTER FAN- CHECK VIBRATION PROBES | 4
ST002FGDSSCBOOSTERFANH-2 | INST | RDI1 | ST210SPS | 5989392 | PM-H-2 OUTAGE CAL. BOOSTER FAN L.O. SYS DEVICES | 8
ST002FGDSSCBOOSTERFANH-2 | INST | RDI1 | ST210SPS | 5989393 | PM-H-2 OUTAGE BOOSTER FAN LOW FURNACE PRESSURE | 1.6
ST002FGDSSCBOOSTERFANH-2 | INST | RDI1 | ST210SPS | 5994175 | H-2 BOOSTER FAN R.T.D.S-MOVE TO DCS | 8
ST002FGDSSCGASDUCTS | INST | RDI1 | ST210SPS | 5994357 | h2 booster inboard motor bearing leaking oil | 2
ST002FGDSSCREACTIONTKH2 | INST | RDI1 | ST210SPS | 5993447 | PM-H-2 Outage Scrubber PH Probe Clean & Calibrate. | 2
ST002FGDSSCREACTIONTKH2 | MECH | RDI1 | ST210SPS | 5994243 | H-2 A Bleed pump discharge valve needs to be replaced | 20
ST002FGDSSCABSORBERTWRH2 | MECH | RDM2 | ST210SPS | 5989603 | PM-H-2 OUTAGE INSPECT SCRUBBER SYTEM (linked doc) | 4
ST002FGDSSCABSORBERTWRH2 | MECH | RDM2 | ST210SPS | 5989628 | PM-H-2 OUTAGE LUBRICATION OF SCRUBBER ITEMS | 1.3
ST002FGDSSCABSORBERTWRH2 | MECH | RDM2 | ST210SPS | 5989953 | H-2 B Recycle Pump seal is leaking | 120
ST002FGDSSCGASDUCTS | MECH | RDM2 | ST210SPS | 5989405 | PM-H-2 OUTAGE INSPECT BYPASS DAMPER SEAL AIR FAN COUPLING | 2
ST002FGDSSCGASDUCTS | MECH | RDM2 | ST210SPS | 5986617 | h2 booster inboard motor bearing leaking oil | 12
ST002FGDSSCGASDUCTS | MECH | RDM2 | ST210SPS | 5989397 | PM-H-2 OUTAGE INSPECT FGD IN DAMPER SEAL AIR FAN COUPLING | 2
ST002FGDSSCREACTIONTKH2 | MECH | RDM2 | ST210SPS | 5989403 | PM-H-2 OUTAGE INSPECTION OF "C" SCRUBBER AGITATOR | 3
ST002FGDSSCREACTIONTKH2 | MECH | RDM2 | ST210SPS | 5989400 | PM-H-2 OUTAGE INSPECTION OF "B" SCRUBBER AGITATOR | 3
ST002FGDSSCREACTIONTKH2 | MECH | RDM2 | ST210SPS | 5989398 | PM-H-2 OUTAGE INSPECTION OF "A" SCRUBBER AGITATOR | 3
ST002FGDSSCABSORBERTWRH2 | MECH | STOC | ST210SPS | 5988039 | Replace suction valve seat. Valve seat was inspected during pit stop. Seat is in bad shape. | 32
ST002FGDSSCABSORBERTWRH2 | MECH | STOC | ST210SPS | 5988041 | Replace suction valve seat. Valve seat was inspected during pitstop. Seat is in bad shape. | 32
ST002FGDSSCABSORBERTWRH2 | MECH | STOC | ST210SPS | 5989395 | PM-H-2 OUTAGE INSPECTION OF RECYCLE HEADER & NOZZLES | 124
ST002FGDSSCABSORBERTWRH2 | MECH | STOC | BP10S027B | 5986622 | H2-Replace mist eliminator panels | 60
ST002FGDSSCBOOSTERFANH-2 | MECH | STOC | ST210SPS | 5847389 | Need to oder new inlet vanes for H2 Booster Fan | 100
ST002FGDSSCBOOSTERFANH-2 | OTH | STOC | ST210SPS | 5987772 | H-2 Booster Fan Remove and Reinstall lagging and Insulation on the East Side of fan Housing | 1
ST002FGDSSCBOOSTERFANH-2 | OTH | STOC | ST210SPS | 5987773 | H-2 Booster Fan Acess Door move lower like H-1 Door | 90
ST002FGDSSCBOOSTERFANH-2 | OTH | STOC | ST210SPS | 5989488 | PM-H-2 OUTAGE INSPECTION OF SCRUBBER BOOSTER FAN | 144
ST002FGDSSCBOOSTERFANH-2 | MECH | STOC | ST210SPS | 5988368 | gas leak @ door | 20
ST002FGDSSCGASDUCTS | OTH | STOC | BP10S018B | 5987770 | H-2 Booster fan outlet expansion joint needs to be replaced | 150
ST002FGDSSCREACTIONTKH2 | MECH | STOC | ST210SPS | 5989469 | PM-H-2 OUTAGE INSPECTION OF FLUE GAS QUENCHING SYSTEM | 38
ST002FGDSSCREACTIONTKH2 | MECH | STOC | ST210SPS | 5989472 | PM-H-2 OUTAGE CLEANING BOTTOM OF CEILING REACTION TANK | 22
ST002FGDSSCREACTIONTKH2 | MECH | STOC | ST210SPS | 5989952 | H-2 A Bleed pump discharge valve needs to be replaced | 60
ST002FGDSSCREACTIONTKH2 | MECH | STOC | ST210SPS | 5980691 | weld pipe coupling in standpipe for the level probe | 12
ST002FGDSSCSTACKSCRUBBER | OTH | STOC | ST210SPS | 5989464 | PM-H-2 OUTAGE SCRUBBER STACK MEASUREMENTS | 11
ST002FOSFO-FUELOILPUMPS | MECH | RDM3 | ST210SPG | 5989565 | PM-H-2 OUTAGE "A" & "B" FUEL OIL PUMPS INSPECTION | 2
ST002PLCBCACCS | INST | RDI1 | ST210SPG | 5989514 | PM-H-2 OUTAGE CLEAN AND INSPECT SECONDARY AIR FLOW ELEMENT AND FURNACE PRESS. TAPS | 5
ST002PLCBCACCS | MECH | STOC | ST210SPG | 5995557 | H-2- OUTAGE REPLACE FURNACE PRESSURE SENSING LINES | 0
ST002RIDBTGGAUGES | INST | RDI1 | ST210SPG | 5841348 | AH t/c problems - ask Brian | 3
ST002RIDBTGGAUGES | INST | RDI1 | ST210SPG | 5886218 | check all 4 mill outlet temps again to be correct compare to classifier out temps | 1
ST002RIDBTGGAUGES | INST | RDI1 | ST210SPT | 5994180 | Turbine case expansion reading zero | 2
ST002RIDBTGMETERS | INST | RDI1 | ST210SPN | 5994181 | reactor inlet temp transmitter not reading correctly | 2
ST002RIDBTGRECORDERS | INST | RDI1 | ST210SPG | 5994178 | point 105 A MILL OUT WEST END reading 22 F should be higher | 2
ST002RIDBTGRECORDERS | INST | RDI1 | ST210SPT | 5734384 | H-2 #1 TURBINE THRUST BEARING IN ALARM | 8
ST002SCRDDE-DAMPERS-A | INST | RDI1 | ST210SPN | 5814030 | H2 SCR DIVERTER DAMPERS OUTPUT IS SHOWING 100% OPEN WHEN DAMPERS ARE CLOSED | 2
ST002SCRDDE-DAMPERSSEALAR | MECH | RDM3 | ST210SPN | 5993916 | A and C SCR seal air fan disc. dampers are not closing off | 4
ST002SCRDDE-DUCTWORK | MECH | STOC | ST210SPN | 5989339 | H2 SCR CATALYST DUCT WORK LAGGING ON SOUTH SIDE NEEDS TO BE LOOKED AT | 24
ST002SCRDDE-DUCTWORK | MECH | STOC | ST210SPN | 5974099 | H2 SCR REACTOR SAMPLE GRID LINES NEED TO BE TAKING APART AND LINE CLEANED OUT | 120
ST002SCRDDE-DUCTWORK | MECH | STOC | ST210SPN | 5993654 | H-2SCR Duct where the spray support mount to the duct floor | 60
ST002SCRDDE-DUCTWORK | MECH | STOC | ST210SPN | 5995569 | H2 SCR CATALYST SAMPLES NEED TO REMOVE THREE SAMPLES ON EFROM EACH LAYER | 30
ST002SCRDDE-DUCTWORK | MECH | STOC | ST210SPN | 5979427 | H2 SCR CATALYST SECTION HAVE BAD LEAK IN DUCT WORK | 60
ST002SCRAMF-FLOCTRLINJGRD | MECH | STOP | ST210SPN | 5956220 | PM-H-2 SCR AMMONIA ROPING - CLEAN INJECTION GRID | 1
ST002SGUCLTFUELSAFETYSYSTEM | INST | RDI1 | ST210SPG | 5994185 | H2 Fuel Oil Postion Sw's need relocating | 8
ST002SGUCLTO-2SYSTEM | INST | RDI1 | ST210SPG | 5993339 | PM-H-2 OUTAGE REMOVE BOILER CM-50/02 PROBE CLEAN/CHECK. | 12
ST002SGUCLTO-2SYSTEM | INST | RDI1 | WK09S059U | 5984878 | INSTALL NEW OXYGEN ANALYZERS ON H-2 BOILER | 20
ST002SGUCTLMISC.INSTR. | INST | RDI1 | ST210SPG | 5993341 | PM-H-2 OUTAGE START UP INSTRUMENTATION. | 45
ST002SGUCTLMISC.INSTR. | INST | RDI1 | ST210SPG | 5995446 | PM-H-2 OUTAGE-INSTRUMENT CAL'S (LINKED DOC). | 175
ST002SGUFDEAIRPREHEATERS | ELEC | RDE1 | ST210SPG | 5990525 | PM-H-2 OUTAGE AIR HEATER A&B CONTROLS CHECK | 2
ST002SGUFDEAIRPREHEATERS | ELEC | RDE1 | ST210SPG | 5990548 | PM-H-2 OUTAGE AIR HEATER "A" & "B" DRIVE MOTORS CHECK | 2
ST002SGUFDEAIRPREHEATERS | ELEC | RDE1 | ST210SPG | 5990572 | PM-H-2 OUTAGE "A" & "B" RADIATOR FAN MOTORS CHECK | 2
ST002SGUFDEF.D.FANS | ELEC | RDE1 | ST210SPT | 5994203 | PM-H-2-DRAIN & REFILL OIL "A" FORCED DRAFT FAN MOTOR | 1.5
ST002SGUFDEF.D.FANS | ELEC | RDE1 | ST210SPT | 5994205 | PM-H-2-DRAIN & REFILL OIL "B" FORCED DRAFT FAN MOTOR | 1.5
ST002SGUFDEAIRPREHEATERS | INST | RDI1 | ST210SPG | 5993434 | PM-H-2 OUTAGE-AIR HEATER A&B DIFF TAPS CLEAN & CHECK. | 4
ST002SGUFDEAIRPREHEATERS | INST | RDI1 | ST210SPG | 5993436 | PM-H-2 OUTAGE-A.P. HTR PRESS. SWITCHES/GAUGES CALABRIATE. | 6
ST002SGUFDEF.D.FANS | INST | RDI1 | ST210SPG | 5994262 | H2 A FD FAN SHUT OFF DAMPER/ LOOSING INDICATIONI | 2
ST002SGUFDEF.D.FANS | INST | RDI1 | ST210SPG | 5977044 | Sroke 2A and 2B FD fans inlet vanes. Vane position needs to relative of the rexa drive position. | 8
ST002SGUFDEF.D.FANS | INST | RDI1 | ST210SPG | 5993748 | PM-H-2 OUTAGE -"A" FD FAN INLET CHECK DAMPERS. | 2
ST002SGUFDEF.D.FANS | INST | RDI1 | ST210SPG | 5993749 | PM-H-2 OUTAGE -"A" FD FAN OUTLET CHECK DAMPERS. | 2
ST002SGUFDEF.D.FANS | INST | RDI1 | ST210SPG | 5993755 | PM-H-2 OUTAGE -"B" FD FAN INLET CHECK DAMPERS. | 2
ST002SGUFDEF.D.FANS | INST | RDI1 | ST210SPG | 5993756 | PM-H-2 OUTAGE -"B" FD FAN OUTLET CHECK DAMPERS. | 2
ST002SGUFDEF.D.FANS | MECH | RDI1 | ST210SPG | 5994244 | PM-H-2 OUTAGE INSPECTION OF "B" FORCED DRAFT FAN | 2
ST002SGUFDEF.D.FANS | MECH | RDI1 | ST210SPG | 5994247 | PM-H-2 OUTAGE INSPECTION OF "A" FORCED DRAFT FAN | 2
ST002SGUFDEAIRPREHEATERS | MECH | RDM2 | ST210SPG | 5989606 | PM-H-2 OUTAGE "B" AIR PREHEATER LUB. INSPECTION | 16
ST002SGUFDEAIRPREHEATERS | MECH | RDM2 | ST210SPG | 5989605 | PM-H-2 OUTAGE "A" AIR PREHEATER LUB. INSPECTION | 16
ST002SGUFDEF.D.FANS | MECH | RDM2 | ST210SPG | 5989505 | PM-H-2 OUTAGE INSPECTION OF "A" FORCED DRAFT FAN | 75
ST002SGUFDEF.D.FANS | MECH | RDM2 | ST210SPG | 5989503 | PM-H-2 OUTAGE INSPECTION OF "B" FORCED DRAFT FAN | 75
ST002SGUFDEAIR-GASDUCTS | MECH | STOC | ST210SPG | 5988363 | H2 Gas probe broken offf at valve temp repair made | 12
ST002SGUFDEAIR-GASDUCTS | MECH | STOC | ST210SPG | 5994301 | H-2 Hot Air header piping to the FD Fans needs to be checked from where it connect | 90
ST002SGUFDEAIR-GASDUCTS | OTH | STOC | BP10S020B | 5988133 | Replace H2 Precip Breeching Duct Work to the exp. joint. | 90
ST002SGUFDEAIR-GASDUCTS | MECH | STOC | BP10S018B | 5848146 | The lower windbox expansion joint needs to be replaced | 36
ST002SGUFDEAIR-GASDUCTS | OTH | STOC | BP10S018B | 5848149 | East air heater hot air in expansion joint needs to be | 8
ST002SGUFDEAIRPREHEATERS | MECH | STOC | ST210SPG | 5989447 | PM-H-2 OUTAGE INSPECTION OF AIR PREHEATER | 300
ST002SGUFDEAIRPREHEATERS | MECH | STOC | ST210SPG | 5989643 | PM-H-2 OUTAGE "A" AIR HEATER LUBE OIL RADIATOR | 30
ST002SGUFDEAIRPREHEATERS | MECH | STOC | ST210SPG | 5989645 | PM-H-2 OUTAGE "B" AIR HEATER LUBE OIL RADIATOR | 30
ST002SGUFDEF.D.FANS | MECH | STOC | ST210SPG | 5989468 | PM-H-2 OUTAGE DYE CHECK "A" & "B" F.D. FAN BLADES | 40
ST002SGUFPEP.A.FANS | ELEC | RDE1 | ST210SPT | 5991218 | PM-H-2 OUTAGE SEND OUT "A" P.A. FAN MOTOR | 1
ST002SGUFPEP.A.FANS | ELEC | RDE1 | ST210SPT | 5991262 | PM-H-2 OUTAGE SEND OUT "B" P.A. FAN MOTOR | 1
ST002SGUFPEPULVERIZERS | ELEC | RDE1 | ST210SPT | 5990902 | PM-H-2 OUTAGE SEND OUT "A" PULVERIZER MOTOR | 1
ST002SGUFPEPULVERIZERS | ELEC | RDE1 | ST210SPT | 5990938 | PM-H-2 OUTAGE SEND OUT "B" PULVERIZER MOTOR | 1
ST002SGUFPECOALFEEDERS | INST | RDI1 | ST210SPG | 5993236 | PM-H-2 OUTAGE REPLACE COAL FEEDER AIR SEALS | 24
ST002SGUFPECOALFEEDERS | INST | RDI1 | ST210SPG | 5993762 | PM-H-2 OUTAGE A1 COAL FEEDER CHECK & CALIBRATE. | 4
ST002SGUFPECOALFEEDERS | INST | RDI1 | ST210SPG | 5993763 | PM-H-2 OUTAGE A2 COAL FEEDER CHECK & CALIBRATE. | 4
ST002SGUFPECOALFEEDERS | INST | RDI1 | ST210SPG | 5993764 | PM-H-2 OUTAGE B1 COAL FEEDER CHECK & CALIBRATE. | 4
ST002SGUFPECOALFEEDERS | INST | RDI1 | ST210SPG | 5993765 | PM-H-2 OUTAGE B2 COAL FEEDER CHECK & CALIBRATE. | 4
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5990253 | PM-H-2 OUTAGE -"B" COLD AIR CHECK DAMPERS. | 2
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5990254 | PM-H-2 OUTAGE -"A" COLD AIR CHECK DAMPERS. | 2
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5993750 | PM-H-2 OUTAGE -"A" HOT AIR CHECK DAMPERS. | 2
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5993753 | PM-H-2 OUTAGE -"A" PA FAN CHECK DAMPERS. | 4
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5993757 | PM-H-2 OUTAGE -"B" HOT AIR CHECK DAMPERS. | 2
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5993759 | PM-H-2 OUTAGE -"B" PA FAN CHECK DAMPERS. | 4
ST002SGUFPEP.A.FANS | MECH | RDI1 | ST210SPG | 5994250 | PM-H-2 OUTAGE INSPECTION OF "B" PRIMARY AIR FAN | 2
ST002SGUFPEP.A.FANS | MECH | RDI1 | ST210SPG | 5994253 | PM-H-2 OUTAGE INSPECTION OF "A" PRIMARY AIR FAN | 2
ST002SGUFPEP.A.FANS | INST | RDI1 | ST210SPG | 5928657 | H2 A&B P.A. FANS HOT/COLD AIR DAMPERS NEED INDIVIDUAL CONTROL STATIONS | 24
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5993450 | PM-H-2 OUTAGE -"B" Mill Bypass East check dampers. | 2
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5993590 | PM-H-2 OUTAGE - CLASSIFIER T/Cs CHECK. | 2
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5993751 | PM-H-2 OUTAGE -"A" MILL BYPASS EAST CHECK DAMPERS. | 2
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5993752 | PM-H-2 OUTAGE -"A" MILL BYPASS WEST CHECK DAMPERS. | 2
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5993758 | PM-H-2 OUTAGE -"B" MILL BYPASS WEST CHECK DAMPERS. | 2
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5994187 | A MILL HIGH TEMP ALARM NOT READING | 2
ST002SGUFPEPULVERIZERS | INST | RDI1 | ST210SPG | 5995448 | PM-H-2 OUTAGE MILL TAPS & T/C's CLEAN & CHECK. | 8
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989618 | PM-H-2 OUTAGE LUBRICATION OF B-1 COAL FEEDER | 2.6
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989611 | PM-H-2 OUTAGE LUBRICATION OF A-1 COAL FEEDER | 2.6
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989600 | PM-H-2 OUTAGE INSPECTION OF "B-2" COAL FEEDER | 40
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989598 | PM-H-2 OUTAGE INSPECTION OF "B-1" COAL FEEDER | 40
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989595 | PM-H-2 OUTAGE INSPECTION OF "A-2" COAL FEEDER | 40
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989593 | PM-H-2 OUTAGE INSPECTION OF "A-1" COAL FEEDER | 40
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989622 | PM-H-2 OUTAGE LUBRICATION OF B-2 COAL FEEDER | 2.6
ST002SGUFPECOALFEEDERS | MECH | RDM2 | ST210SPG | 5989615 | PM-H-2 OUTAGE LUBRICATION OF A-2 COAL FEEDER | 2.6
ST002SGUFPEP.A.FANS | MECH | RDM2 | ST210SPG | 5994026 | H-2 B PA FAN OUT BORAD FAN BEARING SEAL IS LEAKING | 16
ST002SGUFPEP.A.FANS | MECH | RDM2 | ST210SPG | 5994025 | Housing on A PA fan has a hole in it on north side | 16
ST002SGUFPEP.A.FANS | MECH | RDM2 | ST210SPG | 5989509 | PM-H-2 OUTAGE INSPECTION OF "B" PRIMARY AIR FAN | 60
ST002SGUFPEP.A.FANS | MECH | RDM2 | ST210SPG | 5989587 | PM-H-2 OUTAGE INSPECTION OF "A" PRIMARY AIR FAN | 60
ST002SGUFPEP.A.FANS | MECH | RDM2 | ST210SPG | 5994024 | P. A. Fan access door leaking ash | 8
ST002SGUFPEPULVERIZERS | MECH | RDM2 | ST210SPG | 5989607 | PM-H-2 OUTAGE "A" PULVERIZER LUB INSPECTION | 20
ST002SGUFPEPULVERIZERS | MECH | RDM2 | ST210SPG | 5989609 | PM-H-2 OUTAGE "B" PULVERIZER LUB INSPECTION | 20
ST002SGUFPEPULVERIZERS | MECH | RDM2 | ST210SPG | 5994023 | H2 B mill inboard pinion bearing leaking bad. | 10
ST002SGUFPEPULVERIZERS | MECH | RDM3 | ST210SPG | 5994661 | b4 coal pipe has hole in line right below cooling air line tie in.reference w.o.#5994647 | 16
ST002SGUFPEPULVERIZERS | MECH | RDM3 | ST210SPG | 5994256 | H2 B mill inboard pinion bearing leaking bad. | 2
ST002SGUFPEBUNKERCOALVALVE | MECH | STOC | ST210SPG | 5989507 | H-2 A-1 Coal Feeder Stand Pipe needs to be replaced from the bunker gate to the feeder | 120
ST002SGUFPECOALFEEDERS | MECH | STOC | ST210SPG | 5980938 | H-2 B1 COAL FEEDER BLAST GATE SLIDES HAS DROPPED DOWN NEEDS TO BE REPAIRED | 16
ST002SGUFPEP.A.FANS | MECH | STOC | BP10S018B | 5848003 | B PA Fan discharge duct expansion joint located west | 120
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989428 | PM-H-2 OUTAGE REMOVE "A" PULVERIZER COOLER FOR CLEANING | 4
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989431 | PM-H-2 OUTAGE REMOVE "B" PULVERIZER COOLER FOR CLEANING | 4
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989449 | PM-H-2 OUTAGE INSPECTION OF "A" PULVERIZER | 45
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989451 | PM-H-2 OUTAGE INSPECTION OF "B" PULVERIZER | 45
ST002SGUFPEPULVERIZERS | OTH | STOC | ST210SPG | 5989479 | PM- H-2 OUTAGE INSPECTION "B" COAL CLASSIFIER | 60.6
ST002SGUFPEPULVERIZERS | OTH | STOC | ST210SPG | 5989481 | PM- H-2 OUTAGE INSPECTION "A" COAL CLASSIFIER | 60.6
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989501 | H-2 A Mill reject chute needs to be replaced | 80
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989502 | H-2 B Mill reject chute needs to be replaced | 80
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989638 | PM-H-2 OUTAGE-A PULV. REPAIR INLET IMPACT AREAS FOUND ON INSP. | 55
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989639 | PM-H-2 OUTAGE-B PULV. REPAIR INLET IMPACT AREAS FOUND ON INSP. | 55
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5989960 | H-2 A&B Mill Outlet & Inlet Pipes need to fix coal leaks | 120
ST002SGUFPEPULVERIZERS | OTH | STOC | ST210SPG | 5989484 | PM-H-2 OUTAGE TAKE THICKNESS READING OF COAL PIPING | 61
ST002SGUFPEPULVERIZERS | OTH | STOC | ST210SPG | 5989486 | PM-H-2 OUTAGE INSPECT THE VARIABLE ORIFICES | 40
ST002SGUFPEPULVERIZERS | MECH | STOC | ST210SPG | 5994263 | Coal leak on chute between feeder and blast gate on side | 20
ST002SGUFPEPULVERIZERS | OTH | STOC | ST210SPG | 5994264 | H-2 "B" East and West MILL INNER SEAL IS BROKEN | 200
ST002SGUMBCBOILER | ELEC | RDE1 | ST210SPG | 5990290 | PM-H-2 OUTAGE Hook up Construction Equipment | 50
ST002SGUMBCEASTTEMPPROBE | ELEC | RDE1 | ST210SPG | 5990355 | PM-H-2 OUTAGE EAST FURNACE PROBE CONTROLS INSPECT | 4
ST002SGUMBCSEALAIRSYSTEM | ELEC | RDE1 | ST210SPT | 5991307 | PM-H-2 OUTAGE SEND OUT "A" SEAL AIR FAN MOTOR | 1
ST002SGUMBCSEALAIRSYSTEM | ELEC | RDE1 | ST210SPT | 5991353 | PM-H-2 OUTAGE SEND OUT "B" SEAL AIR FAN MOTOR | 1
ST002SGUMBCSOOTBLOWERSYSTEM | ELEC | RDE1 | ST210SPG | 5990334 | PM-H-2 OUTAGE SB CONTROL PANEL CLEAN & INSPECT | 2
ST002SGUMBCSOOTBLOWERSYSTEM | ELEC | RDE1 | ST210SPG | 5990344 | PM-H-2 OUTAGE SB CABINETS CLEAN & INSPECT | 20
ST002SGUMBCBOILER | INST | RDI1 | ST210SPG | 5994359 | PM-H-2 OUTAGE BOILER TAPS CLEAN & CHECK. | 100
ST002SGUMBCBURNERS | INST | RDI1 | ST210SPG | 5993360 | PM-H-2 OUTAGE SCANNERS CLEAN & CHECK. | 2
ST002SGUMBCBURNERS | INST | RDI1 | ST210SPG | 5993505 | PM-H-2 OUTAGE REMOVE IGNITOR RODS & CHECK | 4
ST002SGUMBCBURNERS | INST | RDI1 | ST210SPG | 5993507 | PM-H-2 OUTAGE BURNER CONTROLS CHECK. | 3
ST002SGUMBCBURNERS | INST | RDI1 | ST210SPG | 5993509 | PM-H-2 OUTAGE COOLING AIR VALVES CLEAN & CHECK. | 5
ST002SGUMBCL.P.HEADERSYSTEM | INST | RDI1 | ST210SPG | 5993432 | PM-H-2 OUTAGE-STEAM COIL CONTROL VALVE CHECKS. | 2
ST002SGUMBCL.P.HEADERSYSTEM | INST | RDI1 | ST210SPG | 5993433 | PM-H-2 OUTAGE-LOW PRESSURE HEADER REG CHECK OPERATIONS. | 2
ST002SGUMBCL.P.HEADERSYSTEM | INST | RDI1 | ST210SPG | 5993435 | PM-H-2 OUTAGE-STEAM COIL DE-SUPERHEATER CONTROLS CHECKS. | 2
ST002SGUMBCREHEATERS | INST | RDI1 | ST210SPG | 5842268 | reheat west block valve not working | 3
ST002SGUMBCSEALAIRSYSTEM | INST | RDI1 | ST210SPG | 5993754 | PM-H-2 OUTAGE -"A" SEAL AIR CHECK DAMPERS. | 1
ST002SGUMBCSEALAIRSYSTEM | INST | RDI1 | ST210SPG | 5993761 | PM-H-2 OUTAGE -"B" SEAL AIR CHECK DAMPERS. | 1
ST002SGUMBCSOOTBLOWERSYSTEM | INST | RDI1 | ST210SPG | 5993592 | PM-H-2 OUTAGE - SB PRESSURE REG & VALVE CHECK OPERATION. | 3
ST002SGUMBCSTEAMDRUM | INST | RDI1 | ST210SPG | 5993425 | PM-H-2 OUTAGE REM DRUM LEVEL CAMERA/MONITOR CLEAN/CHECK. | 12
ST002SGUMBCVALVES | INST | RDI1 | ST210SPG | 5993340 | PM-H-2 OUTAGE ELECTROMATIC RELIEF VALVE CHECK OPERATION. | 4
ST002SGUMBCSEALAIRSYSTEM | MECH | RDM2 | ST210SPG | 5989589 | PM-H-2 OUTAGE INSPECTION OF "A" SEAL AIR FAN | 4
ST002SGUMBCSEALAIRSYSTEM | MECH | RDM2 | ST210SPG | 5989591 | PM-H-2 OUTAGE INSPECTION OF "B" SEAL AIR FAN | 4
ST002SGUMBCBURNERS | MECH | RDM3 | ST210SPG | 5989535 | PM-H-2 OUTAGE INSPECTION OF BURNER COOLING AIR FAN | 16
ST002SGUMBCSEALAIRSYSTEM | MECH | RDM3 | ST210SPG | 5994029 | discharge valve operator is loose | 8
ST002SGUMBCSTEAMDRUM | MECH | RDM3 | ST210SPG | 5989530 | PM-H-2 OUTAGE 18 MO DRUM INSPECT FOR BLR PERMIT RENEWAL | 10
ST002SGUMBCBURNERS | MECH | RDM5 | ST210SPG | 5989846 | Remove spreaders from tubes and re-install after being | 8
ST002SGUMBCBLRTUBES/HEADERS | MECH | STOC | ST210SPG | 5902758 | The seal casing and refractory on the east and | 250
ST002SGUMBCBLRTUBES/HEADERS | MECH | STOC | ST210SPG | 5985164 | Intermediate wall refractory (replaces 5848016) | 250
ST002SGUMBCBLRTUBES/HEADERS | MECH | STOC | ST210SPG | 5989528 | PM-H-2 OUTAGE OBSERVATION PORTS INSPECTION | 154
ST002SGUMBCBLRTUBES/HEADERS | MECH | STOC | ST210SPG | 5989436 | PM-H-2 OUTAGE INSPECTION OF BOILER BUCK STAYS | 241
ST002SGUMBCBLRTUBES/HEADERS | OTH | STOC | ST210SPG | 5989458 | PM-H-2 OUTAGE OBTAIN TIGHT WIRE OF RWW DEFLECTION TUBES | 5
ST002SGUMBCBLRTUBES/HEADERS | OTH | STOC | ST210SPG | 5989494 | PM-H-2 OUTAGE INSPECT THE LOWER WATER WALL HEADER | 16
ST002SGUMBCBOILER | OTH | STOC | ST210SPG | 5987652 | H-2 BOILER WATERWALL TUBE SURVEY | 350
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5989432 | PM-H-2 OUTAGE COVER COST OF BOILERMAKER SUPERVISION | 2304
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5989433 | PM-H-2 OUTAGE COVER COST OF TOOL RM CLERK & LABORER | 2304
ST002SGUMBCBOILER | OTH | STOC | ST210SPG | 5989478 | PM-H-2 OUTAGE OUTSIDE VENDOR VACUUM PENTHOUSE/DEAD AIR SPACE | 75
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5989523 | PM-H-2 OUTAGE BOILER INSPECTION BY SUPERVISION | 336
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5989539 | PM-H-2 OUTAGE REPAIR ALL BOILER GAS LEAKS | 150
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5992747 | H-2 BOILER HEADER CONDITION ASSESSMENT | 200
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5994241 | H-2 boiler taps, clean and pressure test all taps | 110
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5994242 | H-2 Open and close boiler doors | 60
ST002SGUMBCBOILER | MECH | STOC | ST210SPG | 5989434 | PM-H-2 OUTAGE OBTAIN A TUBE SAMPLE from ??? | 81
ST002SGUMBCBOILER | OTH | STOC | ST210SPG | 5989490 | PM-H-2 OUTAGE BOILERMAKERS NON-ANTICIPATED WORK | 250
ST002SGUMBCBOILER | OTH | STOC | ST210SPG | 5989495 | PM-H-2 OUTAGE CONSTRUCTION MOBILIZATION & DEMOBILIZATION | 300
ST002SGUMBCBURNERS | MECH | STOC | ST210SPG | 5989418 | PM-H-2 OUTAGE INSPECTION OF BURNERS & OIL TORCHES | 240
ST002SGUMBCBURNERS | MECH | STOC | ST210SPG | 5848071 | A1 Burner oil ignitor tube needs to be replaced. A weld | 60
ST002SGUMBCBURNERS | MECH | STOC | ST210SPG | 5848076 | A2 Burner oil ignitor tube needs to be replaced. A | 60
ST002SGUMBCBURNERS | MECH | STOC | ST210SPG | 5848079 | The head of the B1 Burner casing was found to be | 80
ST002SGUMBCINSULATION | OTH | STOC | ST210SPG | 5987771 | Remove and Reinstall lagging and insulation on the H-2 Boilerl | 1
ST002SGUMBCL.P.HEADERSYSTEM | OTH | STOC | ST210SPG | 5847852 | 2010 outage from first 6 inch tee to the south from the | 150
ST002SGUMBCL.P.HEADERSYSTEM | MECH | STOC | ST210SPG | 5989540 | PM-H-2 OUTAGE INSPECTION OF STEAM COILS | 64
ST002SGUMBCL.P.HEADERSYSTEM | MECH | STOC | ST210SPG | 5989580 | H-2 steam coils alternate drain line leaking from under insulation | 90
ST002SGUMBCL.P.HEADERSYSTEM | MECH | STOC | ST210SPG | 5989959 | H-2 Low Pressure Header Supply line to the steam coils | 200
ST002SGUMBCREHEATERS | OTH | STOC | ST210SPG | 5989466 | PM-H-2 OUTAGE INSPECTION OF HIGH TEMP REHEATER | 195.9
ST002SGUMBCREHEATERS | OTH | STOC | ST210SPG | 5989491 | PM-H-2 OUTAGE HOT REHEAT PIPING INSPECT THE HOT REHEAT | 250
ST002SGUMBCREHEATERS | OTH | STOC | ST210SPG | 5989493 | PM-H-2 OUTAGE PRIMARY REHEATER INSPECTION | 200
ST002SGUMBCREHEATERS | MECH | STOC | BP10S014B | 5850557 | H-2 Hot Reheat Replace #4,#5,#6,#7 Hanger spring is broken. Purchase | 150
ST002SGUMBCSEALAIRSYSTEM | MECH | STOC | ST210SPG | 5835756 | H-2 "A" seal air fan, replace fan blades, 2010 outage | 20
ST002SGUMBCSEALAIRSYSTEM | MECH | STOC | ST210SPG | 5835761 | H-2 "B" seal air fan, replace fan blades 2010 outage | 20
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | ST210SPG | 5848064 | #47 & #48 sootblower penetrations need to be moved | 250
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | ST210SPG | 5990156 | H-2 Change out Retract soot blowers #30,#31,#32 and #34 | 160
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | ST210SPG | 5937189 | scrapers bad on #43,44,45,46 | 60
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | ST210SPG | 5989050 | H2 #21 Seal air box plugged | 20
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | ST210SPG | 5989424 | PM-H-2 OUTAGE INSPECTION OF SOOT BLOWERS | 87.2
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | BP10S022B | 5986620 | H2-Replace (4) retractable sootblowers during spring outage | 320
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | BP10S023B | 5986621 | H2-Replace (3) wallblowers during spring outage | 120
ST002SGUMBCSOOTBLOWERSYSTEM | MECH | STOC | WK09S053U | 5957385 | #16 Soot Blower Needs to be replaced. It was | 40
ST002SGUMBCSUPERHEATERS | OTH | STOC | ST210SPG | 5989456 | PM-H-2 OUTAGE INSPECTION OF RADIANT SUPERHEATER | 300.9
ST002SGUMBCSUPERHEATERS | MECH | STOC | BP10S014B | 5990174 | H-2 Replace Main Steam Pipe Hangers #1& #5 | 150
ST002SGUMBCVALVES | MECH | STOC | ST210SPG | 5980536 | H2 NE Drum Safety Thru | 6
ST002SGUMBCVALVES | OTH | STOC | ST210SPG | 5989492 | PM-H-2 OUTAGE MAIN STEAM PIPING INSPECT THE MAIN STEAM | 150
ST002SGUMBCVALVES | MECH | STOC | ST210SPG | 5994240 | H-2 Clean out all safety valve drip pan | 100
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5986449 | PM-H-2 OUTAGE PRECIPITATOR FIELD INSPECTION | 20
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990394 | PM-H-2 OUTAGE PRECIPITATOR CONTROLS CLEAN & INSPECT | 8
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990409 | PM-H-2 OUTAGE PRECIPITATOR RAPPERS INSPECT | 4
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990425 | PM-H-2 OUTAGE PRECIPITATOR BUSHINGS & SUPPORTS CLEAN | 12
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990443 | PM-H-2 OUTAGE PRECIPITATOR CLEAN UP | 6
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990462 | PM-H-2 OUTAGE PRECIPITATOR HEATERS CHECK | 2
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990482 | PM-H-2 OUTAGE PRECIPITATOR DOORS OPEN | 10
ST002SGUPRPPRECIPITATOR | ELEC | RDE1 | ST210SPG | 5990503 | PM-H-2 OUTAGE PRECIPITATOR T/R SETS CLEAN & INSPECT | 12
ST002SGUPRPPRECIPITATOR | OTH | STOC | ST210SPG | 5984373 | H-2 OUTAGE-TEST THICKNESS OF PRECIPITATOR HOT ROOF AND SIDES | 16
ST002SGUPRPPRECIPITATOR | OTH | STOC | ST210SPG | 5986457 | PM-H-2 OUTAGE PRECIPITATOR FIELD INSPECTION BY OUTSIDE CONTRACTOR | 20
ST002SGUPRPPRECIPITATOR | MECH | STOC | ST210SPG | 5990177 | H-2 Replace Precipitator Enclosure Floor | 400
ST002SGUPRPPRECIPITATOR | MECH | STOC | ST210SPG | 5993391 | PM-H-2 OUTAGE check precip support piping thickness | 2
ST002TGNMGCEXCITER | ELEC | RDE1 | ST210SPT | 5990707 | PM-H-2 OUTAGE GEN EXCITER DIODE CHECK | 30
ST002TGNMGCEXCITER | ELEC | RDE1 | ST210SPT | 5990650 | PM-H-2 OUTAGE GEN EXCITER CLEAN & CHECK | 22
ST002TGNMGCSEALOILSYSTEM | ELEC | RDE1 | ST210SPT | 5990367 | PM-H-2 OUTAGE D.C. SEAL OIL & CONTROLS CLEAN & INSPECT | 2
ST002TGNMTCLUBEOILSYSTEM | ELEC | RDE1 | ST210SPT | 5990380 | PM-H-2 OUTAGE D.C. LUBE OIL & CONTROLS CLEAN & INSPECT | 2
ST002TGNMTCLUBEOILSYSTEM | ELEC | RDE1 | ST210SPT | 5991868 | PM-H-2 OUTAGE - PERFORM EBOP TESTING | 10.2
ST002TGNMTCTURNINGGEAR | ELEC | RDE1 | ST210SPT | 5990597 | PM-H-2 OUTAGE T & G TURNING GEAR CHECKS | 1
ST002TGNPM-AREAPMS | ELEC | RDE1 | ST210SPT | 5991926 | PM-H-2 OUTAGE PERFORM ELEC WORK ON THE TURBINE/GENERATOR | 3
ST002TGNTGCMETER-RELAY | ELEC | RDE1 | ST210SPT | 5990737 | PM-H-2 OUTAGE GEN PT's CLEAN & CHECK | 10
ST002TGNTGCMETER-RELAY | ELEC | RDE1 | ST210SPT | 5992291 | PM-H-2 OUTAGE GEN CTs CLEAN & CHECK | 10
ST002TGNTGCVOTAGEREG. | ELEC | RDE1 | ST210SPT | 5990623 | PM-H-2 OUTAGE GEN VOLTAGE REG CLEAN & CHECK | 10
ST002TGNTGCVOTAGEREG. | ELEC | RDE1 | ST210SPT | 5990678 | PM-H-2 OUTAGE GEN FIELD BREAKER CLEAN & INSPECT | 4
ST002TGNMTCELECTROHYDSYSTEM | INST | RDI1 | ST210SPT | 5993443 | PM-H-2 Outage Turbine EH Cooling Water Cont.& Valve Ck Op. | 1.5
ST002TGNMTCELECTROHYDSYSTEM | INST | RDI1 | ST210SPT | 5993502 | PM-H-2 Outage Turbine Interface Valve. | 2
ST002TGNMTCGLANDSSTEAM | INST | RDI1 | ST210SPT | 5993444 | PM-H-2 Outage Turbine Steam Seal Valve & Controls Ck Op. | 5
ST002TGNMTCLUBEOILSYSTEM | INST | RDI1 | ST210SPT | 5993442 | PM-H-2 Outage Turbine L.O. Cooling Water Controls/Valve Ck. | 1.5
ST002TGNMTCREHT/INTERCPT/RCV | MECH | RDI1 | ST210SPT | 5822074 | not testing properly | 2
ST002TGNMTCTURBINEBRG/PED | INST | RDI1 | ST210SPT | 5994188 | BRG. #1 Y READING 101 MILS | 2
ST002TGNTGCEMER.TRIP.INST. | INST | RDI1 | ST210SPT | 5989409 | PM-H-2 Outage TURBINE PROTECTIVE TRIP DEVICES CK OPERATION | 7
ST002TGNTGCMISC.TRUB.INST. | INST | RDI1 | ST210SPT | 5989407 | PM-H-2 Outage TURBINE/GEN: CONTROLS, VIB, RTD's CK OP | 18
ST002TGNTGCMISC.TRUB.INST. | INST | RDI1 | ST210SPT | 5989408 | PM-H-2 Outage TURBINE/ GEN CAL, PRESS /TEMP GAUGES | 18
ST002TGNTGCTURB.SUPV.INST. | INST | RDI1 | ST210SPT | 5993438 | PM-H-2 Outage Turbine Eccentricity Detector-Check Operation. | 4
ST002TGNTGCTURB.SUPV.INST. | INST | RDI1 | ST210SPT | 5993439 | PM-H-2 Outage Turbine Diff. Expansion Detector Ck Operation. | 3
ST002TGNTGCTURB.SUPV.INST. | INST | RDI1 | ST210SPT | 5993440 | PM-H-2 Outage Turbine Rotor Position Check Operation. | 3
ST002TGNTGCTURBINECONTROLS | INST | RDI1 | ST210SPT | 5990143 | H-2 TURBINE #2 BEARING CHECK VIBRATION PROBES | 2
ST002TGNTRBHMP-L2TURBINE | INST | RDI1 | ST210SPT | 5993441 | PM-H-2 Outage Turbine Cooling Water Cont. & Valve Ck Op. | 2
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM2 | ST210SPT | 5989602 | PM-H-2 OUTAGE VIBRATION ANALYSIS "DC" LUBE OIL PUMP | 1
ST002TGNMGCHYDROGENSYSTEM | MECH | RDM3 | ST210SPT | 5989571 | PM-H-2 OUTAGE LUBRICATION OF HYDROGEN DRYER | 1
ST002TGNMGCSEALOILSYSTEM | MECH | RDM3 | ST210SPT | 5989573 | PM-H-2 OUTAGE LUBRICATION & INSPECTION SEAL OIL UNIT | 7
ST002TGNMTCGOVERNORVALVES | MECH | RDM3 | ST210SPT | 5994265 | H-2 LEFT GOV. VALVE CYLINDER - REPLACE THE CYLINDER | 16
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM3 | ST210SPT | 5994022 | h-2 lube oil tank vapor extractor fan shaft oil leak lube | 3
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM3 | ST210SPT | 5989958 | H-2 Remove Lube Oil Cooler Heads for cleaning | 60
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM3 | ST210SPT | 5989569 | PM-H-2 OUTAGE INSPECTION LUBE OIL TANK VAPOR EXTRACTOR | 1.6
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM3 | ST210SPT | 5989560 | PM-H-2 OUTAGE "AC" LO PUMP COUPLING INSPECTION | 4
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM3 | ST210SPT | 5989558 | PM-H-2 OUTAGE "DC" LO PUMP COUPLING INSPECTION | 3
ST002TGNMTCLUBEOILSYSTEM | MECH | RDM3 | ST210SPT | 5989556 | PM-H-2 OUTAGE BOWSER SYSTEM PUMP COUPLINGS | 2.2
ST002TGNMTCREHT/INTERCPT/RCV | MECH | RDM3 | ST210SPT | 5989537 | PM-H-2 OUTAGE PM OF REVERSE CURRENT VALVES | 97

## H1 2011 Spring Outage 10 Day
Location | Resource | Project | Work Order | Description | EstHrs
ST001ASHARSBOTASHREMOVAL | STOC | ST1PLO | 6028702 | H-1 OUTAGE PM OF WEST HYDROEJECTOR | 94
ST001ASHARSBOTASHREMOVAL | STOC | ST1PLO | 6028703 | H-1 OUTAGE PM OF EAST HYDROEJECTOR | 94
ST001ASHARSWETBTMPIPING | STOC | ST1PLO | 6028719 | OUTAGE INSPECTION OF REFRACTORY COOLING SYSTEM | 150.6
ST001ASHARSWETBTMPIPING | STOC | BP11H015B | 6029618 | Re-position the H1 Bottom Ash Hopper, replace the seal skirt and interior portion of the seal trough, replace all refractory cooling water headers, repair sections of the hopper | 1750
ST001ASHARSWETBTMPIPING | STOC | BP11H015B | 6030576 | REMOVAL: Re-position the H1 Bottom Ash Hopper, replace the seal skirt and interior portion of the seal trough, replace all refractory cooling water headers, repair sections of the hopper | 1750
ST001ASHARSBOTASHREMOVAL | STOC | ST1PLO | 6005656 | PM-OUTAGE H-1 INSECTION OF WET BOTTOM LANCING DOORS:Max | 16
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6022631 | H-1 East & West Equilizing Valves need to check metal behind valves bad gas leaks | 60
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6022632 | H-1 west wet bottom Ash gate and seal needs to be changed out during the spring outage 2011 | 60
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6022633 | H-1 East wet bottom ash gate and seal needs to be replaced during the spring outage 2011 | 60
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6005704 | PM-OUTAGE H-1 INSPECTION "A" ASH GATE HOUSING:Max | 20
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6005706 | PM-OUTAGE H-1 INSPECTION "B" ASH GATE HOUSING:Max | 20
ST001ASHARSSLAGGRINDERS | STOC | ST1PLO | 6022693 | H-1 B East wet bottom Ash grinder needs to be pulled and the direction of the grinder reversed during the spring outage 2011 | 120
ST001BFWFWCF.W.HEATERS | STOC | BP11H012B | 6025234 | Install limitorques on both H1 HP FW Heaters 5&6 Steam Extraction Isolation valves. | 60
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6028704 | PM-OUTAGE H-1 OUTSIDE VENDOR INSPECT COOLING TOWER | 10
ST001CWSCCSCOOLTOWERSYSTEM | RDM3 | ST1PLO | 6005695 | PM-OUTAGE H-1 INSPECTION OF SOUTH COOLING TOWER:Max | 129
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030434 | B cell, east side, south valve, leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030431 | D cell,east side, north valve, valve is leaking through and leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030419 | A cell west side ,,water leaking bad between header and distribution piece at both valves | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030430 | C cell, east side, north valve is leaking through | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030436 | D cell, east side, south valve, valve is leaking through and leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030435 | C cell, east side, south valve, leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030422 | F cell west side valves leaking through and leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030428 | A cell ,, East side,, north valve,, valve leaking through | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030425 | B cell, west side, south valve,, valve leaking through and leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030440 | F cell, east side, north valve, valve is leaking through | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | BP11H010B | 6026271 | Install Archbar fill and Tuflock grids along with replacement of longitudinal/transverse 2x4's on Cell D,E, and F during the H1 Spring 2011 outage. | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030432 | E cell, east side, north valve, leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030420 | D cell west side leaking bad between header and distribution piece on both valves | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030427 | D cell, west side,, south valve,, valve leaking through | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030424 | A cell, west side, south valve is leaking through | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030437 | E cell, east side, south valve, valve leaking through and leaking between distribution piece and header | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030438 | F cell, east side, south valve, leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030421 | E cell west side,, valves leaking through and leaking between header and distribution piece | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030429 | B cell, east side, north valve will not shut | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030426 | C cell,, west side,, south valve,, valve leaking through and leaking between header and distribution piece | 1
ST001SCRDDE-DUCTWORK | STOC | ST1PLO | 6007787 | H-1 SCR inlet duct expansion joint leaking:Max | 350
ST001SGUFDEAIRPREHEATERS | STOC | BP11H009B | 6022003 | Installation of new CE AH Baskets on H1 "A" and "B" APH's | 5200
ST001SGUFDEAIRPREHEATERS | STOC | ST1PLO | 6005689 | PM-OUTAGE H-1 INSPECTION OF AIR PREHEATER:Max | 81
ST001SGUMBCBOILER | RDM2 | ST1PLO | 6028959 | H-1SPRING OUTAGE 2011 REFRACTORY REMOVAL AND REPLACEMENT IN THE BOILER | 2
ST001SGUMBCBOILER | STOC | ST1PLO | 6031967 | H-1 Inspect boiler Drain and Vent | 60
ST001SGUMBCBOILER | STOC | ST1PLO | 6026245 | H-1 OUTAGE INSPECTION OF BOILER SAFETY VALVES | 1
ST001SGUMBCBOILER | STOC | ST1PLO | 6031497 | H-1 Repair Gas Leaks on the Boiler | 300
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6031966 | H-1 Inspect duct work for gas leaks during the spring outage | 100
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6031965 | H-1 Inspect windbox during the spring outage | 60
ST001SGUMBCL.P.HEADERSYSTEM | STOC | BP11H035F | 6031759 | Remove the H1 LP HDR Desuperheater during the Spring 2011 Outage. | 20
ST001SGUMBCL.P.HEADERSYSTEM | STOC | BP11H035F | 6031758 | The H1 LP HDR Desuperheater is worn out. Replace during the 2011 Spring Outage. | 60
ST001SGUMBCBURNERS | STOC | BP11H014B | 6025433 | Install Scanner Cooling Air Blowers on H1. This will include two new blowers installed on the 3rd floor level of H1. One blower will be redundant. They will tie into the existing supply header on the first level burner deck. | 100
ST001CWSCCSCOOLTOWERSYSTEM | STOC | BP11H010B | 6026271 | Install Archbar fill and Tuflock grids along with replacement of longitudinal/transverse 2x4's on Cell D,E, and F during the H1 Spring 2011 outage. | 200
ST001FGDSSCGASDUCTS | STOC | BP11H008B | 6025835 | Installation : Replace Booster Fan inlet expansion joint EJ-4 (north) | 46
ST001FGDSSCGASDUCTS | STOC | BP11H008B | 6030580 | REMOVAL : Replace Booster Fan inlet expansion joint EJ-4 (north) | 46
ST001FGDSSCGASDUCTS | STOC | BP11H008B | 6025838 | Installation: Replace Booster Fan Inlet Expansion Joint (EJ-5) South | 46
ST001FGDSSCGASDUCTS | STOC | BP11H008B | 6030581 | Removal: Replace Booster Fan Inlet Expansion Joint (EJ-5) South | 46
ST001FGDSSCGASDUCTS | STOC | BP11H008B | 5982308 | Installation : Replace H1 Booster Outlet fan Expansion Joint (EJ-6) has a hole in it:Max | 105
ST001FGDSSCGASDUCTS | STOC | BP11H008B | 6030583 | Removal : Replace H1 Booster Outlet fan Expansion Joint (EJ-6) has a hole in it:Max | 105
ST001SGUFDEAIR-GASDUCTS | STOC | BP11H008B | 6029106 | Install an internal joint on H1 West Economizer Expansion Joint | 200
ST001SGUFDEAIR-GASDUCTS | STOC | BP11H008B | 6029107 | Install an internal expansion joint on H1 East Economizer expansion joint | 200
ST001SGUFDEF.D.FANS | STOC | ST1PLO | 6032025 | H-1 Outage Inspection of A & B FD Fan Housing | 60
ST001CHSCONMASSFLOWA | STOC | STPLO | 6030510 | H-1 A Mass Flow Conveyor needs to be overhauled during the spring outage | 360
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6025665 | H-1-PM-OUTAGE TAKE THICKNESS READING OF COAL PIPING | 61
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6025954 | PM-OUTAGE INSPECT THE VARIABLE ORIFICES | 40
ST001SGUMBCVALVES | STOC | ST1PLO | 6026245 | H-1 OUTAGE INSPECTION OF BOILER SAFETY VALVES | 1
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6028745 | PM-OUTAGE H-1 DYE CHECK SOUTH WATER WALL HMP&L ONE | 11.5
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6027227 | PM-OUTAGE H-1 OBTAIN TIGHT WIRE OF RWW DTUBES | 5
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6025667 | H-1-PM- OUTAGE INSPECTION OF BOILER BUCK STAYS | 120.5
ST001SGUMBCBURNERS | STOC | ST1PLO | 6028721 | PM-OUTAGE H-1 INSPECTION OF BURNERS & OIL TORCHES | 240
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6028718 | PM-OUTAGE H-1 INSPECTION OF SOOT BLOWERS HMP&L ONE | 87.8
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 6028720 | H-1 OUTAGE INSPECTION OF RADIANT SUPERHEATER | 300.9
ST001SCRDDE-DAMPERSSEALAR | STOC | ST1PLO | 6033081 | H-1 SCR Need to Inspect seal air piping from seal air fans to the Dampers | 60
ST001ASHFARFLYASHSYSTEM | STOC | ST1PLO | 6005686 | PM-OUTAGE H-1 REPLACEMENT ECONOMIZER HOPPER VALVES:Max | 57
ST001BFWFWCBFPSUCTPIPING | RDM3 | ST1PLO | 6005700 | PM-OUTAGE H-1 CLEAN "A" BOILER FEED PUMP SUCTION STRAINERS:Max | 6
ST001BFWFWCBFPSUCTPIPING | RDM3 | ST1PLO | 6005702 | PM-OUTAGE H-1 CLEAN "B" BOILER FEED PUMP SUCTION STRAINERS:Max | 6
ST001SGUMBCVALVES | STOC | ST1PLO | 6029493 | H1 Electromatic leaking through. | 1
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6005697 | PM-OUTAGE H-1 INSPEC OF "B" BOILER FEED PUMP COUPLING:Max | 20
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6005745 | PM-OUTAGE H-1 INSPEC OF "A" BOILER FEED PUMP COUPLING:Max | 20
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6005751 | PM-OUTAGE H-1 "A" BOILER FEED PUMPS LUB. INSPECTION:Max | 6
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6005753 | PM-OUTAGE H-1 "B" BOILER FEED PUMPS LUB. INSPECTION:Max | 6
ST001BFWFWCDASTORAGETANK | RDM3 | ST1PLO | 5983316 | H1 West side DA floor drain valve leaking:Max | 20
ST001BFWFWCDASTORAGETANK | STOC | ST1PLO | 6005735 | PM-OUTAGE H-1 INSPECTION OF DEAERATOR STORAGE TANK:Max | 63
ST001CDSCSCCONDENSATEPUMPS | RDM3 | ST1PLO | 6014920 | H1 A & B Condensate Pumps discharge valves &:Max | 60
ST001CDSCSCLOWPRESSUREHEATERS | STOC | ST1PLO | 6005737 | PM-OUTAGE H-1 INSPECTION OF DEAERATOR HEATER:Max | 210
ST001CW-CWSCOOLINGWTRSYS | RDM3 | ST1PLO | 6005659 | PM-OUTAGE H-1 OPEN & CLOSE HEAT EXCHANGER:Max | 120
ST001CWSCCSCIRCULATORS | RDM3 | ST1PLO | 5983656 | Stub valve line leaking where it is welded onto discharge line:Max | 20
ST001CWSCCSCONDENSERSYSTEM | RDM3 | ST1PLO | 6005634 | PM-OUTAGE H-1 INSPECT CONDENSER DOORS:Max | 10
ST001CWSCCSCONDENSERSYSTEM | RDM3 | ST1PLO | 6005660 | PM-OUTAGE H-1 CHECK STEAM WASHING OF CONDENSER TUBES:Max | 60
ST001CWSCCSCOOLTOWERSYSTEM | RDM3 | ST1PLO | 6005747 | PM-OUTAGE H-1 PM C.T. DISTRIBUTION HEADER EAST AIR RELIEF:Max | 8.5
ST001CWSCCSCOOLTOWERSYSTEM | RDM3 | ST1PLO | 6005749 | PM-OUTAGE H-1 PM C.T. DISTRIBUTION HEADER WEST AIR RELIEF:Max | 8.5
ST001FOSFO-FUELOILPUMPS | RDM3 | ST1PLO | 6005766 | PM-OUTAGE H-1 "A" & "B" FUEL OIL PUMPS INSPECTION:Max | 4
ST001SCRDDE-DUCTWORK | STOC | ST1PLO | 6031869 | RCD to clean catalyst modules with vacuum and air | 1
ST001SCRDDE-DAMPERS-A | STOC | ST1PLO | 6029076 | Replace H1 diverter damper seals on "A" damper | 100
ST001SCRDDE-DUCTWORK | STOC | ST1PLO | 6031174 | SCR samples collect sample from each layer to be sent off for analysis | 60
ST001SCRDDE-DAMPERS-B | STOC | ST1PLO | 6029077 | replace H1 diverter damper seals on "B" damper | 100
ST001SCRSHSSONICHORNS | STOC | BP11H017B | 6020315 | H1 scr catalyst reactor east side has gas leaks around the sonic horn gaskets. Need lagging removed to check where leaks are coming from | 1
ST001SCRSHSSONICHORNS | STOC | BP11H017B | 6032250 | H1 scr catalyst reactor east side has gas leaks around the sonic horn gaskets. Need lagging removed to check where leaks are coming from | 1
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6028969 | H-1 NEED TO INSPECT AND MAKE REPAIRS TO THE BY-PASS STACK DAMPER | 100
ST001SGUFDEAIR-GASDUCTS | RDM2 | ST1PLO | 6028969 | H-1 NEED TO INSPECT AND MAKE REPAIRS TO THE BY-PASS STACK DAMPER | 2
ST001SGUFDEAIRPREHEATERS | STOC | ST1PLO | 6032353 | Make modifications to air leakage test taps on A & B hot and cold side of H-1 AH. Need the 12 flanges and probes on the hot side removed and a new flange with a valve installed. On the cold side need to verify current valves work or be re | 40
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6026803 | H-1 Need to make repairs to the lagging and insulation on the west and east side windbox expansion joints during the spring outage 2011 | 75
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6026103 | H-1 West and East Expansion joint need to replace Lagging and Insulation | 100
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6026107 | H-1 Hot air supply header to the FD Fans needs to be replaced during the spring outage 2011 | 150
ST001SGUFDEAIRPREHEATERS | RDM3 | ST1PLO | 6005713 | PM-OUTAGE H-1 "A" AIR PREHEATER LUB. INSPECTION:Max | 16
ST001SGUFDEAIRPREHEATERS | RDM3 | ST1PLO | 6005714 | PM-OUTAGE H-1 "B" AIR PREHEATER LUB. INSPECTION:Max | 16
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6033193 | H1 A2 clean out conveyor drive coupling slipping.SEE THE FOLLOWING THE SHAFT ON THE CLEAN OUT GEAR BOX NEEDS A NEW SHAFT INSTALLED ALONG WITH A NEW COUP[LING . OR REPLACE THE GEAR BOX ASSEMBLY ON SPRING 2011 OUTAGE | 30
ST001SGUFDEAIRPREHEATERS | RDM2 | ST1PLO | 6028825 | H-1 "A" AIR HEATER LUBE OIL RADIATOR NEEDS TO BE CLEANED | 30
ST001SGUFDEF.D.FANS | STOC | ST1PLO | 6028747 | PM-OUTAGE H-1 DYE CHECK "A" & "B" F.D. FANS | 40
ST001SGUFPEP.A.FANS | STOC | ST1PLO | 6025200 | H-1 "A" P.A. Hot air duct leaking bad on hard deck. West side | 100
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6028943 | H-1 Install and Remove boiler scaffolding for Water Wall Inspection | 100
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 5934613 | The refractory block wall between the economizer:Max | 100
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6005661 | PM-OUTAGE H-1 OBSERVATION PORTS INSPECTION:Max | 154
ST001SGUMBCREHEATERS | STOC | ST1PLO | 6027228 | PM-OUTAGE H-1 INSPECTION OF HIGH TEMP REheater | 195
ST001SGUMBCBOILER | STOC | ST1PLO | 6028796 | PM-OUTAGE H-1 18 MO DRUM INSPECT FOR BLR. PERMIT RENEWAL | 10
ST001SGUFPECOALFEEDERS | STOC | BP11H034F | 6034826 | H-1 A Blast Gate Install during Outage | 60
ST001SGUFPECOALFEEDERS | STOC | BP11H034F | 6034825 | H-1 A Blast Gate Remove during Outage | 30
ST001SGUMBCBOILER | STOC | ST1PLO | 6028828 | PM-OUTAGE H-1 BOILERMAKERS NON-ANTICIPATED WORK | 250
ST001SGUMBCBOILER | STOC | ST1PLO | 6028959 | H-1SPRING OUTAGE 2011 REFRACTORY REMOVAL AND REPLACEMENT IN THE BOILER | 1
ST001SGUMBCBOILER | RDM3 | ST1PLO | 6005654 | PM-OUTAGE H-1 BOILER INSPECTION BY SUPERVISION:Max | 3
ST001SGUMBCBOILER | STOC | ST1PLO | 6005658 | PM-OUTAGE H-1 NON-ANTICIPATED WORK:Max | 250
ST001SGUMBCBOILER | STOC | ST1PLO | 6005666 | PM-OUTAGE H-1 COVER COST OF BOILERMAKER SUPERVISION:Max | 900
ST001SGUMBCBOILER | STOC | ST1PLO | 6005667 | PM-OUTAGE H-1 COVER COST OF TOOL RM CLERK & LABORER:Max | 720
ST001SGUMBCBOILER | STOC | ST1PLO | 6031288 | PM-OUTAGE-H-1 CONSTRUCTION MOBILIZATION & DEMOBILIZATION | 300
ST001ASHFARFLYASHSYSTEM | STOC | ST1PLO | 6030925 | H-1 SPRING OUTAGE INSTALL ECONOMIZIER HOPPER DRAINS TO ACCOMODATE WASHING THE ECONOMIZER TUBES | 100
ST001SGUMBCBOILER | STOC | BP11H017B | 6005688 | PM-OUTAGE H-1 REPAIR ALL BOILER GAS LEAKS:Max | 1
ST001SGUMBCBOILER | STOC | BP11H017B | 6032247 | PM-OUTAGE H-1 REPAIR ALL BOILER GAS LEAKS:Max | 1
ST001SGUMBCBOILER | STOC | ST1PLO | 6022645 | H-1 Boiler Penthouse need to remove the isomembrane and inspect the metal under it | 500
ST001SGUMBCBOILER | STOC | ST1PLO | 6026542 | H-1 Air Test for Spring outage 2011 | 4
ST001SGUMBCBOILER | STOC | ST1PLO | 6030930 | H1 SPRING OUTAGE OBTAIN TUBE SAMPLE | 47
ST001CHSCONMASSFLOWA | STOC | ST111AMFS | 6030510 | H-1 A Mass Flow Conveyor needs to be overhauled during the spring outage | 180
ST001CHSCONMASSFLOWA | STOC | ST111AMFS | 6032026 | H-1 B Mass Flow Conveyor & Screw Feeder Outage Repairs | 180
ST001SGUMBCBOILER | STOC | ST1PLO | 6026017 | H-1 BOILER WATERWALL TUBE SURVEY TO BE PERFORM DURING THE SPRING OUTAGE 2011 | 350
ST001SGUMBCBOILER | STOC | ST1PLO | 6026018 | H-1 BOILER HEADER INSPECTION TO BE PERFORMED DURING THE SPRING OUTAGE 2011 | 350
ST001SGUMBCBOILER | STOC | ST1PLO | 6028835 | H-1 OUTAGE NEED TO CLEAN OUT ALL SAFETY VALVE DIP PANS | 100
ST001SGUMBCBURNERS | RDM3 | ST1PLO | 6005739 | PM-OUTAGE H-1 INSPECTION OF BURNER COOLING AIR FAN:Max | 20
ST001SGUMBCBURNERS | RDM3 | ST1PLO | 6015520 | Apply Conforma Clad protectant to burner parts to be:Max | 1
ST001SGUMBCECONOMIZER | STOC | ST1PLO | 6009896 | Gas leaks around the economizer inlet:Max | 60
ST001SGUMBCINSULATION | STOC | ST1PLO | 6010030 | H1 penthouse has bad gas leaks:Max | 800
ST001SGUMBCINSULATION | STOC | ST1PLO | 6026386 | H-1 West and East side windbox expansion joints needs lagging and insulation replaced Where PA fan Duct connects (hard deck) | 100
ST001SGUMBCL.P.HEADERSYSTEM | STOC | ST1PLO | 6005743 | PM-OUTAGE H-1 INSPECTION OF STEAM COILS:Max | 64
ST001SGUMBCL.P.HEADERSYSTEM | STOC | BP11H019B | 6026253 | H1 Steam coils - Replace six steam coils | 125
ST001SGUMBCL.P.HEADERSYSTEM | STOC | BP11H019B | 6026267 | H-1 Steam Coils - replace six | 125
ST001SGUMBCREHEATERS | STOC | ST1PLO | 5976690 | cold reheat pipe hanger #10 broken:Max | 30
ST001SGUMBCREHEATERS | STOC | ST1PLO | 6026714 | H-1-PM-OUTAGE HOT REHEAT PIPING INSPECTION | 100
ST001SGUMBCREHEATERS | STOC | BP11H016B | 6025909 | H-1 Remove (2) Hot Reheat Pipe Hangers #2 and #8 during the spring outage 2011 | 40
ST001SGUMBCREHEATERS | STOC | BP11H016B | 6025912 | H-1 Install (2) new Hot Reheat pipe Hangers #1 and #8 during the spring outage 2011 | 100
ST001SGUMBCREHEATERS | STOC | BP11H016B | 6025917 | H-1 Remove (1) Cold Reheat Pipe Hanger #13 during the spring outage 2011 | 30
ST001SGUMBCREHEATERS | STOC | BP11H016B | 6025918 | H-1 Install (1) Cold Reheat Pipe Hanger # 13 during the spring outage 2011 | 60
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 5984114 | H1 #28 sootblower scraper is bad.:Max | 20
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 5984115 | H1 Sootblower #27 scraper is bad:Max | 20
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6004135 | #27 sootblower has seal air box plugged or bad scrapers:Max | 20
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6005536 | #42 seal air box plugged and scraers worn:Max | 20
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6015391 | # 30 sootblower has scrapers bad replace outage:Max | 20
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6023247 | H-1 #34 Retract Soot Blower replace During the Spring outage of 2011 | 100
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6030495 | H-1 #34 Retract Soot Blower removed During the Spring outage of 2011 | 30
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6023250 | H-1 #23 WALL BLOWER NEEDS TO BE REPLACED DURING THE SPRING OUTAGE 2011 | 60
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6030494 | H-1 #23 WALL BLOWER NEEDS TO BE REMOVED DURING THE SPRING OUTAGE 2011 | 40
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6023251 | H-1 #24 WALL BLOWER NEEDS TO BE REPLACED DURING THE SPRING OUTAGE 2011 | 60
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6030496 | H-1 #24 WALL BLOWER NEEDS TO BE REMOVED DURING THE SPRING OUTAGE 2011 | 40
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6023249 | H-1 #18 WALL BLOWER NEED TO REPLACE DURING SPRING OUTAGE | 60
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H004B | 6030493 | H-1 #18 WALL BLOWER NEED TO REMOVED DURING SPRING OUTAGE | 40
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6025921 | H-1 Remove and Replace #19 wall blower with a new Diamond Power wall blower during the spring outage 2011 | 100
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6025922 | H-1 Remove #20 wall blower and replace it with a new diamond power wall blower during the spring outage 2011 | 100
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6025923 | H-1 Remove #21 wall blower and replace with a new diamond power wall blower during the spring outage 2011 | 100
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6025924 | H-1 Remove #22 wall blower and replace with a new diamond power wall blower during the spring outage 2011 | 100
ST001SGUMBCSTEAMDRUM | STOC | ST1PLO | 5934855 | Replace insulation on steam drum inside penthouse:Max | 100
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 5982306 | Replace T-11 Material swedge with correct T-22:Max | 30
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 6010470 | H-1 Super Heater inlet loops need to replace the 2 outer loops on each elements:Max | 250
ST001SGUMBCSUPERHEATERS | STOC | BP11H016B | 6025902 | H-1 Remove Main Steam Pipe Hangers #2 , #4 and #6 during the spring outage 2011 | 80
ST001SGUMBCSUPERHEATERS | STOC | BP11H016B | 6025903 | H-1 Install (3) new main steam pipe hangers #2 ,#4 and #6 during the spring outage 2011 | 100
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 6030173 | H-1Primary Super Heater Pin casing in the Pent house needs to be replace damaged due to a tube leak all the way across the boiler | 300
ST001SGUMBCVALVES | STOC | ST1PLO | 6026241 | H-1 PM-OUTAGE Inspection of the Main Steam Piping | 100
ST001SGUMBCWESTTEMPPROBE | RDM3 | ST1PLO | 6005662 | PM-OUTAGE H-1 WEST FURNACE TEMP. PROBE INSPECT:Max | 1
ST001TGN | RDM3 | ST1PLO | 6015374 | PM-OUTAGE-H-1 (TURBINE PM'S):Max | 1
ST001TGNMGCSEALOILSYSTEM | RDM3 | ST1PLO | 5857113 | pump seal is leaking:Max | 20
ST001TGNMTCELECTROHYDSYSTEM | RDM3 | ST1PLO | 6005763 | PM-OUTAGE H-1 ELECTROHYDRAULIC SYSTEM INSPECTION:Max | 5
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6005755 | PM-OUTAGE H-1 BOWSER SYSTEM PUMP COUPLINGS:Max | 2.5
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6005757 | PM-OUTAGE H-1 #1 LO PUMP COUPLING INSPECTION:Max | 3
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6005759 | PM-OUTAGE H-1 #2 LO PUMP COUPLING INSPECTION:Max | 3
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6005761 | PM-OUTAGE H-1 "DC" LO PUMP COUPLING INSPECTION:Max | 3
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6027107 | PM-Outage H-1 Turbine L.O. Cooling Water | 1
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6005768 | PM-OUTAGE H-1 INSPECTION LUBE OIL TANK VAPOR EXTRACTOR:Max | 3
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6009720 | Left hand reheat stop valve drain line leak through to atmosphere:Max | 30
ST001TGNMTCSTEAMTRAPS | RDM3 | ST1PLO | 6008987 | needs replacing:Max | 30
ST002SCRDDE-DUCTWORK | STOC | ST1PLO | 6029414 | H-1 SCR Reactor sample grid lines need to be replaced | 100
ST001SGUMBCBURNERS | RDM5 | ST1PLO | 6015886 | Remove spreaders from tubes and re-install after:Max | 20
ST001TGNMGCGENERATORROTOR | STOC | BP11H008B | 6030608 | H-1 Rewedge of the Generator During the Spring Outage 2011 | 400
ST001TGNMGCGENERATORROTOR | STOC | BP11H008B | 6025782 | H-1 Rewedge of the Generator During the Spring Outage 2011 | 400
ST001TGNMGCSTATORDETAILS | STOC | ST1PLO | 6030931 | H-1 SPRING OUTAGE TURBINE & GENERATOR | 1
ST001TGNMGCSTATORDETAILS | STOC | ST1PLO | 6030932 | H-1 SPRING OUTAGE GENERATOR TD & TESTING | 1
ST001TGNMTCTURNINGGEAR | STOC | ST1PLO | 6032747 | H-1 turbine turning gear inspect for excessive wear. Making grinding noise when yrying to mesh. | 40
ST001TGNMTCHP-IPCYLINDER | STOC | ST1PLO | 6023657 | H-1 Emergency Blow Down Valve Mid Term Inspections spring outage 2011 | 60
ST001TGNMTCMAINSTOPVALVE | STOC | ST1PLO | 6025767 | H-1 Turbine Valve Inspection - Remove and replace Insulation | 60
ST001TGNMTCMAINSTOPVALVE | STOC | ST1PLO | 6022651 | H-1 TURBINE STOP VALVES-MID TERM INSPECTION | 200
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6022652 | H-1TURBINE RIGHT HAND REHEAT/INTERCRPT VALVE- MID TERM INSPECTION | 210
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6005741 | PM-OUTAGE H-1 OF REVERSE CURRENT VALVES:Max | 60
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6022656 | H-1 TURBINE LEFT HAND REHEAT/INTERCEPT VALVE-MID TERM INSPECTION | 210
ST001TGNMTCSTEAMCHEST | STOC | ST1PLO | 6022703 | H-1 TURBINE GOVERNOR VALVES- MID TERM INSPECTION SPRING OUTAGE 2011 | 700
ST001BFWFWCATTEMPERATION | RDI1 | ST1PLO | 6008369 | PM-OUTAGE H-1 E&W R.H. Spray Control Valve checks:Max | 4
ST001BFWFWCATTEMPERATION | RDI1 | ST1PLO | 6008370 | PM-OUTAGE H-1 E&W S.H. Spray Control Valve checks:Max | 4
ST001BFWFWCATTEMPERATION | RDI1 | ST1PLO | 6016487 | H1 Superheat Spray Block Valves East and West Need:Max | 16
ST001BFWFWCATTEMPERATION | RDI1 | ST1PLO | 6016488 | H1 Reheat Spray Block Valve East & West Needs Limit:Max | 16
ST001BFWFWCBOILERFEEDPUMPS | RDI1-OT | ST1PLO | 6020134 | H-1 A boiler feed pump Balance drum leak off reading very High 90+ check on outage | 1
ST001BFWFWCDASTORAGETANK | RDI1 | ST1PLO | 6008343 | PM-OUTAGE H-1 D.A. Level Switches check operation.:Max | 4
ST001BFWFWCF.W.HEATERS | RDI1 | ST1PLO | 6008342 | PM-OUTAGE H-1 H.P. Heater Level Alarms check operation:Max | 10
ST001BFWFWCF.W.HEATERS | RDI1 | ST1PLO | 6008367 | PM-OUTAGE H-1 H.P. HTR Level Control & Valve check operat:Max | 10
ST001BFWFWCF.W.HEATERS | RDI1 | BP11H012B | 6025234 | Install limitorques on both H1 HP FW Heaters 5&6 Steam Extraction Isolation valves. | 4
ST001BFWFWCPIPINGTOECONOMIZER | RDI1 | ST1PLO | 6008364 | PM-OUTAGE H-1 Feedwater Control Valve check operation:Max | 2
ST001CDSCSCCONDDISCHSYSTEM | RDI1 | ST1PLO | 6008365 | PM-OUTAGE H-1 DA Level Control & Valve check operation:Max | 2
ST001CDSCSCCONDDRAINTANK | RDI1 | ST1PLO | 6008387 | PM-Outage H-1 L.P. Drain Tank Check Controls:Max | 2
ST001CDSCSCCONDMAKEUPSYSTEM | RDI1 | ST1PLO | 6008368 | PM-OUTAGE H-1 Condenser Level Control & Valve checks:Max | 3
ST001CDSCSCLOWPRESSUREHEATERS | RDI1 | ST1PLO | 6008341 | PM-OUTAGE H-1 L.P. Heater Level Alarms check operation:Max | 10
ST001CDSCSCLOWPRESSUREHEATERS | RDI1 | ST1PLO | 6008366 | PM-OUTAGE H-1 L.P. HTR. Level Control & Valve check operat:Max | 20
ST001CWSCCSCONDENSERSYSTEM | RDI1 | ST1PLO | 6008344 | PM-OUTAGE H-1 Hotwell Level Switches check operation.:Max | 2
ST001CWSCCSCOOLTOWERSYSTEM | RDI1 | ST1PLO | 6008388 | PM-Outage H-1 South Cooling Tower Vib Sw's Ck Cal:Max | 4
ST001EVSAE-AIREMISSIONS | RDI1 | BP10S003B | 5999279 | HMPL CEMs-UPGRADE SCRUBBER STACK AND UMBILICALS:Max | 20
ST001EVSAE-AIREMISSIONS | RDI1 | ST1PLO | 6005638 | PM-OUTAGE H-1 CEM Equiptment clean & check:Max | 8
ST001EVSAE-AIREMISSIONS | RDI1 | BP10S003B | 6026531 | H-1 STACK CEM-INSTALL NEW UMBILICAL FOR DILUTION PROBE | 8
ST001EVSAE-AIREMISSIONS | RDI1 | BP10S003B | 6026543 | H-1 STACK CEM-REMOVE OLD DILUTION PROBE UMBILICAL | 8
ST001FGDSSCABSORBERTWRH1 | RDI1 | ST1PLO | 6008390 | PM-Outage H-1 Scrubber Inspect Instrumentation & Calibrate:Max | 20
ST001FGDSSCABSORBERTWRH1 | RDI1 | ST1PLO | 6028742 | PM-Outage H-1 Scrubber Inspect Instrumen | 1
ST001FGDSSCBOOSTERFANH-1 | RDI1 | ST1PLO | 6027138 | PM-OUTAGE H-1 CAL. OF BOOSTER FAN L.O. S DEVICES | 4
ST001FGDSSCREACTIONTKH1 | RDI1 | ST1PLO | 6008389 | PM-Outage H-1 Scrubber PH Probe Clean & Calibrate:Max | 2
ST001FGDSSCREACTIONTKH1 | RDI1 | ST1PLO | 6028915 | H-1 A BLEED PUMP SUCTION VALVE NEEDS TO BE REPLACED | 20
ST001FGDSSCREACTIONTKH1 | RDI1 | ST1PLO | 6028917 | H-1 A BLEED PUMP DISCHARGE VALVE NEEDS TO BE REPLACE | 20
ST001PLCBCACCS | RDI1 | ST1PLO | 6029283 | PM-OUTAGE-H-1 REMOVE AND CLEAN P.A. FLOW TRANSMITTERS | 1
ST001RIDBTGANNUCIATORS | RDI1 | ST1PLO | 5985179 | point 264 RH OUT MID RA-17-1 NOT READING:Max | 3
ST001SGUCTLMISC.INSTR. | RDI1 | ST1PLO | 6008393 | PM-OUTAGE H-1 Instrument Calibration's:Max | 175
ST001SGUCTLO-2SYSTEM | RDI1 | ST1PLO | 6005637 | PM-OUTAGE H-1 Remove Boiler CM-50/02 Probe clean/check:Max | 12
ST001SGUCTLO-2SYSTEM | RDI1 | BP11H031F | 6026108 | H-1 Oxygen Analyzers-Install 4 new systems | 150
ST001SGUCTLO-2SYSTEM | RDI1 | BP11H031F | 6026110 | H-1 Oxygen Analyzers-Remove existing oxygen analyzers | 50
ST001SGUCTLO-2SYSTEM | STOC | BP11H031F | 6026110 | H-1 Oxygen Analyzers-Remove existing oxygen analyzers | 50
ST001SGUCTLO-2SYSTEM | STOC | BP11H031F | 6026108 | H-1 Oxygen Analyzers-Install 4 new systems | 250
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6008339 | PM-OUTAGE H-1 Air Heater A&B Controls check:Max | 2
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6008374 | PM-OUTAGE H-1 Air Heaters A&B Diff Taps clean & check:Max | 4
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6008375 | PM-OUTAGE H-1 A.P. Htr Press. Switches/Gauges calabriate:Max | 6
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6008376 | PM-OUTAGE H-1 Air Heater A& B Bearing T/C's checks:Max | 4
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6005642 | PM-OUTAGE H-1 "A" FD Fan Inlet check dampers:Max | 1
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6005643 | PM-OUTAGE H-1 "A" FD Fan Outlet check dampers:Max | 2
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6005644 | PM-OUTAGE H-1 "B" FD Fan Inlet check dampers:Max | 2
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6005645 | PM-OUTAGE H-1 "B" FD Fan Outlet check dampers:Max | 2
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6008350 | PM-OUTAGE H-1 A1 Coal Feeder check & calibrate.:Max | 4
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6008352 | PM-OUTAGE H-1 A2 Coal Feeder check & calibrate.:Max | 4
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6008354 | PM-OUTAGE H-1 B1 Coal Feeder check & calibrate.:Max | 4
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6008356 | PM-OUTAGE H-1 B2 Coal Feeder check & calibrate.:Max | 4
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6016120 | H-1COAL FEEDERS-UPGRADE COAL FEEDER CONTROLS:Max | 100
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6005646 | PM-OUTAGE H-1 "A" Hot Air check dampers:Max | 2
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6005647 | PM-OUTAGE H-1 "A" Cold Air check dampers:Max | 2
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6005648 | PM-OUTAGE H-1 "B" Hot Air check dampers:Max | 2
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6005649 | PM-OUTAGE H-1 "B" Cold Air check dampers:Max | 2
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6008360 | PM-OUTAGE H-1 "A" PA Fan check dampers.:Max | 4
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6008361 | PM-OUTAGE H-1 "B" PA Fan check dampers.:Max | 4
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6027112 | PM-OUTAGE H-1 "B" PA Fan check dampers | 2
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6027213 | PM-OUTAGE H-1 "A" PA FAN CHECK DAMPERS | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 5678645 | Purchase and install Thermo-wells and temp:Max | 16
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6004376 | H-1 B mill east end air out reading is bad input:Max | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005640 | PM-OUTAGE H-1 Mill Taps & T/C's clean & check:Max | 8
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005641 | PM-OUTAGE H-1 Classifier T/Cs check:Max | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005650 | PM-OUTAGE H-1 "A" Mill Bypass East check dampers:Max | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005651 | PM-OUTAGE H-1 "A" Mill Bypass West check dampers:Max | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005652 | PM-OUTAGE H-1 "B" Mill Bypass East check dampers:Max | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005653 | PM-OUTAGE H-1 "B" Mill Bypass West check dampers:Max | 2
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6008358 | PM-OUTAGE H-1 Coal Valve Solenoids & Limits check.:Max | 4
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6008359 | PM-OUTAGE H-1 Mill Lift Pump Gauage/T/Cs/Switches checks.:Max | 8
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6020809 | H-1 B Pulverizer has excessive vibration on the pinon bearings needs to be checked out during the srring outage 2011 | 1
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6025417 | H-1 A mill West and East end Head Extension needs to be replaced during the spring outage in 2011 | 4
ST001SGUMBCBOILER | RDI1 | ST1PLO | 6008349 | PM-OUTAGE H-1 Boiler Taps clean & check.:Max | 100
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6005639 | PM-OUTAGE H-1 Cooling Air Valves clean & check:Max | 5
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6008345 | PM-OUTAGE H-1 Scanners clean & check.:Max | 8
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6008346 | PM-OUTAGE H-1 Remove Ignitor Rods & Check.:Max | 8
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6008347 | PM-OUTAGE H-1 Burner Controls check.:Max | 3
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6008371 | PM-OUTAGE H-1 Steam Coil Control Valve checks:Max | 2
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6008372 | PM-OUTAGE H-1 Low Pressure Header Reg check operations:Max | 2
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6008373 | PM-OUTAGE H-1 Steam Coil De-Superheater Controls checks:Max | 2
ST001SGUMBCSEALAIRSYSTEM | RDI1 | ST1PLO | 6008362 | PM-OUTAGE H-1 "A" Seal Air check dampers.:Max | 1
ST001SGUMBCSEALAIRSYSTEM | RDI1 | ST1PLO | 6008363 | PM-OUTAGE H-1 "B" Seal Air check dampers.:Max | 1
ST001SGUMBCSOOTBLOWERSYSTEM | RDI1 | ST1PLO | 6008348 | PM-OUTAGE H-1 SB Pressure Reg & Valve check operation.:Max | 3
ST001SGUMBCSTEAMDRUM | RDI1 | ST1PLO | 6008340 | PM-OUTAGE H-1 Remove Drum Level Camera/Monitor clean/check.:Max | 8
ST001SGUMBCSTEAMDRUM | RDI1 | ST1PLO | 6026407 | PM-OUTAGE H-1 Remove Drum Level Camera/MIRROR | 12
ST001SGUMBCSUPERHEATERS | RDI1 | ST1PLO | 5928635 | SH W-H-7-1 BAD QUALITY READING:Max | 8
ST001SGUMBCVALVES | RDI1 | ST1PLO | 6005623 | PM-OUTAGE H-1 Electromatic Relief Valve check operation:Max | 4
ST001TGNMGCHYDROGENSYSTEM | RDM3 | ST1PLO | 6005770 | PM-OUTAGE H-1 HYDROGEN DRYER.:Max | 10.5
ST001TGNMTCELECTROHYDSYSTEM | RDI1 | ST1PLO | 6008385 | PM-Outage H-1 Turbine EH Cooling Water Cont.& Valve Ck Op.:Max | 1.5
ST001TGNMTCHP-IPCYLINDER | RDI1-DT | ST1PLO | 6023657 | H-1 Emergency Blow Down Valve Mid Term Inspections spring outage 2011 | 1
ST001TGNMTCL.P.CYLINDER | RDI1 | ST1PLO | 6008384 | PM-Outage H-1Turbine Exhaust Hood Spray Ctrl/Valve Ck Op:Max | 2
ST001TGNMTCLUBEOILSYSTEM | RDI1 | ST1PLO | 6008383 | PM-Outage H-1 Turbine L.O. Cooling Water Controls/Valve Ck:Max | 1.5
ST001TGNMTCMAINSTOPVALVE | RDI1 | ST1PLO | 6022651 | H-1 TURBINE STOP VALVES-MID TERM INSPECTION | 2
ST001TGNMTCREHT/INTERCPT/RCV | RDI1 | ST1PLO | 6022652 | H-1TURBINE RIGHT HAND REHEAT/INTERCRPT VALVE- MID TERM INSPECTION | 12
ST001TGNMTCREHT/INTERCPT/RCV | RDI1 | ST1PLO | 6022656 | H-1 TURBINE LEFT HAND REHEAT/INTERCEPT VALVE-MID TERM INSPECTION | 12
ST001TGNMTCSTEAMCHEST | RDI1 | ST1PLO | 6008386 | PM-Outage H-1 Turbine Steam Seal Valve & Controls Ck Op:Max | 1.5
ST001TGNMTCSTEAMCHEST | RDI1 | ST1PLO | 6022703 | H-1 TURBINE GOVERNOR VALVES- MID TERM INSPECTION SPRING OUTAGE 2011 | 12
ST001TGNTGCEMER.TRIP.INST. | RDI1 | ST1PLO | 6008378 | PM-Outage H-1 Turbine Protective Trip Devices Ck Operation:Max | 7
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6005635 | PM-OUTAGE H-1 Start Up Instrumentation:Max | 45
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6008377 | PM-Outage H-1 Turbine/Gen Calibrations,Press/Temp gauges:Max | 20
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6008382 | PM-Outage H-1 Turbine Cooling Water Cont. & Valve Ck Op:Max | 3
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6015378 | PM-Outage H-1 Turbine/ Gen Cal, Press /Temp Gauges:Max | 18
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6015381 | PM-Outage H-1 Turbine/Gen: Controls, Vib, RTD's Ck Op:Max | 18
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6008379 | PM-Outage H-1 Turbine Eccentricity Detector-Check Operation:Max | 4
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6008380 | PM-Outage H-1 Turbine Diff. Expansion Detector Ck Operation:Max | 1
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6008381 | PM-Outage H-1 Turbine Rotor Position Check Operation:Max | 3
ST001FGDSSCBOOSTERFANH-1 | RDI1 | ST1PLO | 6015991 | H-1 BOOSTER FAN R.T.D.S-MOVE TO DCS:Max | 30
ST001SGUPRPPRECIPITATOR | STOC | BP11H018B | 6026247 | H-1 PRECIPITATOR HOT ROOF-REMOVE OLD HOT ROOF | 1
ST001SGUPRPPRECIPITATOR | STOC | BP11H018B | 6026251 | H-1 PRECIPITATOR HOT ROOF-INSTALL NEW HOT ROOF | 1
ST001EVSAE-AIREMISSIONS | STOC | BP10S003B | 6026531 | H-1 STACK CEM-INSTALL NEW UMBILICAL FOR DILUTION PROBE | 100
ST001EVSAE-AIREMISSIONS | STOC | BP10S003B | 6026543 | H-1 STACK CEM-REMOVE OLD DILUTION PROBE UMBILICAL | 60
ST001SGUPRPPRECIPITATOR | STOC | ST1PLO | 6005627 | PM-OUTAGE H-1 Precipitator Field Inspection:Max | 1
ST001SGUPRPPRECIPITATOR | STOC | ST1PLO | 5975064 | H-1 PRECIPITATOR CHECK THICKNESS OF WALL AND:Max | 30
ST001ASHCTRCONTROLS | RDE1 | ST1PLO | 6015316 | PM-OUTAGE H-1 Flyash Controls clean & check:Max | 2
ST001BFWFWCBOILERFEEDPUMPS | RDE1 | ST1PLO | 6015329 | PM-OUTAGE H-1 SEND OUT "A" BOILER FEED PUMP MOTOR:Max | 1
ST001BFWFWCBOILERFEEDPUMPS | RDE1 | ST1PLO | 6015343 | PM-OUTAGE H-1 DRAIN & REFILL OIL ON "A" BOILER FEED PUMP MOTOR:Max | 3
ST001BFWFWCBOILERFEEDPUMPS | RDE1 | ST1PLO | 6015345 | PM-OUTAGE H-1 DRAIN & REFILL OIL ON "B" BOILER FEED PUMP MOTOR:Max | 3
ST001BFWFWCBOILERFEEDPUMPS | RDE1 | ST1PLO | 6014083 | H-1 "B" BFP motor-replace with new motor:Max | 5
ST001CDSCSCCONDENSATEPUMPS | RDE1 | ST1PLO | 6015333 | PM-OUTAGE H-1 SEND OUT "A" CONDENSATE PUMP MOTOR:Max | 1
ST001CDSCSCCONDENSATEPUMPS | RDE1 | ST1PLO | 6015334 | PM-OUTAGE H-1 SEND OUT "B" CONDENSATE PUMP MOTOR:Max | 1
ST001CDSCSCCONDENSATEPUMPS | RDE1 | ST1PLO | 6015347 | PM-OUTAGE H-1 DRAIN & REFILL OIL ON "A" CONDENSATE PUMP MOTOR:Max | 3
ST001CDSCSCCONDENSATEPUMPS | RDE1 | ST1PLO | 6015349 | PM-OUTAGE H-1 DRAIN & REFILL OIL ON "B" CONDENSATE PUMP MOTOR:Max | 3
ST001CWSCCSCIRCULATORS | RDE1 | ST1PLO | 6015330 | PM-OUTAGE H-1 SEND OUT "A" CIRCULATING WATER PUMP:Max | 1
ST001CWSCCSCIRCULATORS | RDE1 | ST1PLO | 6027093 | PM-OUTAGE H-1-DRAIN & REFILL OIL "C" CIR | 10
ST001CWSCCSCIRCULATORS | RDE1 | ST1PLO | 6027096 | PM-OUTAGE H-1-DRAIN & REFILL OIL "D" CIR OUTAGE | 10
ST001CWSCCSCONDENSERSYSTEM | RDE1 | ST1PLO | 6015339 | PM-OUTAGE H-1 SEND OUT "A" VACUUM PUMP MOTOR:Max | 1
ST001CWSCCSCONDENSERSYSTEM | RDE1 | ST1PLO | 6015340 | PM-OUTAGE H-1 SEND OUT "B" VACUUM PUMP MOTOR:Max | 1
ST001CWSCCSCOOLTOWERSYSTEM | RDE1 | BP10S076F | 6008891 | Replacement of the Power Control Center on H1- Switchgear, MCC, VFD's, and Building:Max | 30
ST001CWSCCSCOOLTOWERSYSTEM | RDE1 | ST1PLO | 6015327 | PM-OUTAGE H-1 C.T. Tower Lube System check:Max | 8
ST001EDTDCS480VMCC1B | RDE1 | ST1PLO | 6015478 | LOSS OF DC ALARM & 480 1B MAIN & TIE C:Max | 20
ST001EDTDCSDCDIST.SYSTEM | RDE1 | ST1PLO | 6005621 | PM-OUTAGE H-1 Battery Charger clean & check:Max | 4
ST001EDTDCSDCDIST.SYSTEM | RDE1 | ST1PLO | 6015326 | PM-OUTAGE H-1 Load Test Batteries:Max | 8
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6015318 | PM-OUTAGE H-1 - 480V MCC clean & check:Max | 20
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6015358 | PM-OUTAGE H-1 SCR 480V MCC CLEAN & CHECK:Max | 20
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6015359 | PM-OUTAGE H-1 SCRUBBER 480V MCC CLEAN AND CHECK:Max | 20
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6015317 | PM-OUTAGE H-1 4160V Switchgear clean & check:Max | 35
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6015356 | PM-OUTAGE H-1 SCRUBBER 4160 SWITCHGEAR CLEAN & CHECK:Max | 40
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6015363 | PM-OUTAGE H-1 CLEAN AND CHECK "A" AUX PT.s:Max | 14
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6015364 | PM-OUTAGE H-1 CLEAN AND CHECK "B" AUX. PT.S:Max | 14
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6015365 | PM-OUTAGE H-1 CLEAN AND CHECK "A" STARTUP PT.S:Max | 14
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6015366 | PM-OUTAGE H-1 "B" CLEAN AND CHECK STARTUP PT.S:Max | 14
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6005622 | PM-OUTAGE H-1 480V Transformers clean & check:Max | 20
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6015319 | PM-OUTAGE H-1 480V Substation Breakers clean & check:Max | 20
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6015320 | PM-OUTAGE H-1 480V Solid State Trip Device test:Max | 60
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6015360 | PM-OUTAGE H-1 SCRUBBER 480V SUBSTATION CLEAN & CHECK:Max | 5
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6028751 | PM-OUTAGE H-1 CLEAN/INSPECT 1B PCC 480 V | 20
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6028754 | PM-OUTAGE H-1 CLEAN/INSPECT 1A PCC 480 V | 20
ST001EDTTSGSCRUBBERTRANSFMR | RDE1 | ST1PLO | 6015357 | PM-OUTAGE H-1 SCRUBBER 'A' TRANSFORMER CLEAN AND INSPECT:Max | 20
ST001EDTTSGSTEPUPTRANSFMR | RDE1 | ST1PLO | 6015362 | PM-OUTAGE H-1 GROUND LEADS ON STEPUP TRANSFORMER:Max | 10
ST001EDTTSGSTEPUPTRANSFMR | RDE1 | ST1PLO | 6015367 | PM-OUTAGE H-1, REMOVE GEN. LEADS AND CLEAN BUSHINGS:Max | 60
ST001EDTTSGSTEPUPTRANSFMR | STOC | ST1PLO | 5702369 | Clean oil coolers on H1 Step-Up Transformer:Max | 10
ST001FGDSSCABSORBERTWRH1 | RDE1 | ST1PLO | 6015355 | PM-OUTAGE H-1 SEND OUT "A" RECYCLE PUMP MOTOR:Max | 1
ST001FGDSSCBOOSTERFANH-1 | RDE1 | ST1PLO | 6015328 | PM-OUTAGE H-1 Scrubber Booster Fan Filters clean & inspect:Max | 10
ST001FGDSSCREACTIONTKH1 | RDE1 | ST1PLO | 6015351 | PM-OUTAGE H-1 GREASE "A" BLEED SLURRY PUMP MOTOR BEARINGS:Max | 1
ST001FGDSSCREACTIONTKH1 | RDE1 | ST1PLO | 6015353 | PM-OUTAGE H-1 GREASE "B" BLEED SLURRY PUMP MOTOR BEARINGS:Max | 1
ST001PASCA-COMPRESS/DRYERS | RDE1 | ST1PLO | 6026084 | PM-OUTAGE H-1 SEND OUT "A" AIR COMPRESSOR MOTOR (ELLIOTT) | 1
ST001SGUFDEAIRPREHEATERS | RDE1 | ST1PLO | 6005632 | PM-OUTAGE H-1 Air Heater A&B Drive Motors check:Max | 2
ST001SGUFDEAIRPREHEATERS | RDE1 | ST1PLO | 6005633 | PM-OUTAGE H-1 A&B Radiator Fan Motors check:Max | 2
ST001SGUFPEP.A.FANS | RDE1 | ST1PLO | 6015335 | PM-OUTAGE H-1 SEND OUT "A" P.A. FAN MOTOR:Max | 1
ST001SGUFPEP.A.FANS | RDE1 | ST1PLO | 6015336 | PM-OUTAGE H-1 SEND OUT "B" P.A. FAN MOTOR:Max | 1
ST001SGUFPEPULVERIZERS | RDE1 | ST1PLO | 6015331 | PM-OUTAGE H-1 SEND OUT "A" PULVERIZER MOTOR:Max | 1
ST001SGUFPEPULVERIZERS | RDE1 | ST1PLO | 6015332 | PM-OUTAGE H-1 SEND OUT "B" PULVERIZER MOTOR:Max | 1
ST001SGUMBCBOILER | RDE1 | ST1PLO | 6005663 | PM-OUTAGE H-1 COVER COST OF CONST. SETTING UP H-1:Max | 50
ST001SGUMBCSEALAIRSYSTEM | RDE1 | ST1PLO | 6015337 | PM-OUTAGE H-1 SEND OUT "A" SEAL AIR FAN MOTOR:Max | 1
ST001SGUMBCSEALAIRSYSTEM | RDE1 | ST1PLO | 6015338 | PM-OUTAGE H-1 SEND OUT "B" SEAL AIR FAN MOTOR:Max | 1
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST1PLO | 6027799 | PM-OUTAGE H-1 SB Cabinets clean & inspect | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | BP11H004B | 6023247 | H-1 #34 Retract Soot Blower replace During the Spring outage of 2011 | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | BP11H004B | 6023249 | H-1 #18 WALL BLOWER NEED TO REPLACE DURING SPRING OUTAGE | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | BP11H004B | 6023250 | H-1 #23 WALL BLOWER NEEDS TO BE REPLACED DURING THE SPRING OUTAGE 2011 | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | BP11H004B | 6023251 | H-1 #24 WALL BLOWER NEEDS TO BE REPLACED DURING THE SPRING OUTAGE 2011 | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST1PLO | 6025921 | H-1 Remove and Replace #19 wall blower with a new Diamond Power wall blower during the spring outage 2011 | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST1PLO | 6025922 | H-1 Remove #20 wall blower and replace it with a new diamond power wall blower during the spring outage 2011 | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST1PLO | 6025923 | H-1 Remove #21 wall blower and replace with a new diamond power wall blower during the spring outage 2011 | 20
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST1PLO | 6025924 | H-1 Remove #22 wall blower and replace with a new diamond power wall blower during the spring outage 2011 | 20
ST001SGUMBCWESTTEMPPROBE | RDE1 | ST1PLO | 6015982 | PM-OUTAGE H-1 ACCUTEMP-PERFORM ROUTINE MAINTENANCE- REMOVE AND RE-INSTALL ALL MICROPHONES:Max | 5
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005624 | PM-OUTAGE H-1 Precipitator Controls clean & inspect:Max | 8
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005625 | PM-OUTAGE H-1 Precipitator Rappers inspect:Max | 8
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005626 | PM-OUTAGE H-1 Precipitator Bushings & Supports clean:Max | 24
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005628 | PM-OUTAGE H-1 Precipitator Clean Up:Max | 6
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005629 | PM-OUTAGE H-1 Precipitator Heaters check:Max | 4
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005630 | PM-OUTAGE H-1 Precipitatior Doors open:Max | 10
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6005631 | PM-OUTAGE H-1 Precipitator T/R Sets clean & inspect:Max | 12
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6028798 | PM-OUTAGE H-1 Assist in Precipitator Field Inspection | 40
ST001TGNMGCEXCITER | RDE1 | ST1PLO | 6015323 | PM-OUTAGE H-1 Gen Exciter clean & check:Max | 22
ST001TGNMGCGENERATORROTOR | RDE1-DT | ST1PLO | 6014728 | Need to turn commutator on H1 generator:Max | 1
ST001TGNMGCSEALOILSYSTEM | RDE1 | ST1PLO | 6015375 | PM-OUTAGE H-1 D.C. Seal Oil & Controls clean & inspect:Max | 2
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6015376 | PM-OUTAGE H-1 D.C. Lube Oil & Controls clean & inspect:Max | 2
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6015379 | PM-OUTAGE H-1 PERFORM EBOP TESTING:Max | 10.5
ST001TGNMTCTURNINGGEAR | RDE1 | ST1PLO | 6015321 | PM-OUTAGE H-1 T & G Turning Gear ck:Max | 1
ST001TGNTGCMETER-RELAY | RDE1 | ST1PLO | 6015325 | PM-OUTAGE H-1 Gen PT's clean & check:Max | 14
ST001TGNTGCMETER-RELAY | RDE1 | ST1PLO | 6015361 | PM-OUTAGE H-1 GEN CT's CLEAN & CHECK:Max | 10
ST001TGNTGCVOLTAGEREG. | RDE1 | ST1PLO | 6015322 | PM-OUTAGE H-1 Gen Voltage Reg clean & check:Max | 14
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6030391 | PM-OUTAGE H-1 SEND OUT #2 LUBE OIL PUMP MOTOR | 1
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6030389 | PM-OUTAGE H-1 SEND OUT #1 LUBE OIL PUMP MOTOR | 1
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6030400 | PM-OUTAGE H-1 SEND OUT EMERGENCY BEARING LUBE OIL PUMP MOTOR | 1
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6015385 | PM-OUTAGE H-1 SEND OUT THE FOLLOWING MOTORS (see W.O. Hierarchy):Max | 1
ST001BFWFWCBOILERFEEDPUMPS | STOC | ST1PLO | 6014083 | H-1 "B" BFP motor-replace with new motor:Max | 1
ST001ASHFARFLYASHSYSTEM | RDM3 | ST1PLO | 6028701 | PM-OUTAGE H-1 REPLACEMENT PRECIPITATOR H | 81
ST001FGDSSCABSORBERTWRH1 | RDM2 | ST1PLO | 6028743 | PM-OUTAGE H-1 LUBRICATION OF SCRUBBER ITEMS | 1.5
ST001FGDSSCABSORBERTWRH1 | RDM3 | ST1PLO | 6028756 | PM-OUTAGE H-1 CLEAN OUT RECYCLE HEADER &NOZZELS | 123
ST001FGDSSCBOOSTERFANH-1 | STOC | ST1PLO | 6028896 | H-1 BOOSTER FAN BLADE TIPS NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 200
ST001FGDSSCBOOSTERFANH-1 | STOC | ST1PLO | 6025955 | H-1-PM-OUTAGE INSPECTION OF SCRUBBER BOOSTER FAN | 142
ST001FGDSSCBOOSTERFANH-1 | STOC | ST1PLO | 6026171 | H-1 Booster Fan Replace lagging on front sections of Fan during the spring outage 2011 | 90
ST001FGDSSCREACTIONTKH1 | RDM2 | ST1PLO | 6027806 | PM-OUTAGE H-1 INSPECTION OF "A" SCRUBBER | 2
ST001FGDSSCREACTIONTKH1 | RDM2 | ST1PLO | 6028722 | PM-OUTAGE H-1 INSPECTION OF "C" SCRUBBER | 3
ST001FGDSSCREACTIONTKH1 | RDM2 | ST1PLO | 6028723 | PM-OUTAGE H-1 INSPECTION OF "B" SCRUBBER | 3
ST001FGDSSCREACTIONTKH1 | RDM2 | ST1PLO | 6028739 | PM-OUTAGE H-1 INSPECTION OF "A" SCRUBBER | 3
ST001FGDSSCREACTIONTKH1 | RDM2 | STMFGD | 6029304 | H-1 SPRING 2011 OUTAGE SEND OUT AGITATOR BLADES TO GE REFURBISHED BY A OUTSIDE VENDOR | 1
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 6028900 | H-1 NEED TO INSPECT INLET DUCT AREA TO THE REACTION TANK WHERE THE HASTALLOY METAL IS | 100
ST001FGDSSCREACTIONTKH2 | STOC | BP11H033F | 6028915 | H-1 A BLEED PUMP SUCTION VALVE NEEDS TO BE REPLACED | 60
ST001FGDSSCREACTIONTKH1 | STOC | BP11H033F | 6029591 | H-1 A BLEED PUMP SUCTION VALVE NEEDS TO BE REMOVED | 20
ST001FGDSSCREACTIONTKH1 | STOC | BP11H033F | 6028917 | H-1 A BLEED PUMP DISCHARGE VALVE NEEDS TO BE REPLACE | 60
ST001FGDSSCREACTIONTKH2 | STOC | BP11H033F | 6029592 | H-1 A BLEED PUMP DISCHARGE VALVE NEEDS TO BE REMOVED | 20
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 5982324 | H1 SCRUBBER SAMPLE SINK DRAIN NEED TO REMOVE FIBERGLASS AND REPALCE WITH STRAINLESS:Max | 60
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 6028749 | OUTAGE CLEANING BOTTOM OF CEILING IN REACTION TANK | 22
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 6025664 | H-1-PM-OUTAGE INSPECTION OF FLUE GAS QUENCHING SYSTEM | 38
ST001SGUFDEAIRPREHEATERS | RDM2 | ST1PLO | 6027225 | PM-OUTAGE H-1 "A" AIRHEATER LUB INSPECTION | 16
ST001SGUFDEAIRPREHEATERS | STOC | ST1PLO | 6027271 | PM-OUTAGE-H-1 "B" AIR HEATER LUBE OIL RADIATOR | 30
ST001SGUFDEF.D.FANS | RDM2 | ST1PLO | 6005668 | PM-OUTAGE H-1 INSPECTION OF "A" FORCED DRAFT FAN:Max | 75
ST001SGUFDEF.D.FANS | RDM2 | ST1PLO | 6027168 | PM-OUTAGE H-1 INSPECTION OF "B" FORCED DRAFT FAN | 75
ST001SGUFDEF.D.FANS | STOC | ST1PLO | 5920647 | H1 B FD Fan shaft on the Inboard end needs to be built up and turned down also thrust:Max | 100
ST001SGUFPEBUNKERCOALVALVE | STOC | BP11H032F | 5928257 | A1 Bunker gate housing is worn out. Repairs were:Max | 60
ST001SGUFPEBUNKERCOALVALVE | STOC | BP11H032F | 6030974 | H-1 A1 Coal Bunker valve needs to be removed | 30
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005678 | PM-OUTAGE H-1 INSPECTION OF "A-1" COAL FEEDER:Max | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005680 | PM-OUTAGE H-1 INSPECTION OF "A-2" COAL FEEDER:Max | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005682 | PM-OUTAGE H-1 INSPECTION OF "B-1" COAL FEEDER:Max | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005684 | PM-OUTAGE H-1 INSPECTION OF "B-2" COAL FEEDER:Max | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005719 | PM-OUTAGE H-1 LUBRICATION OF A-1 COAL FEEDER:Max | 2.6
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005722 | PM-OUTAGE H-1 LUBRICATION OF A-2 COAL FEEDER:Max | 2.6
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005725 | PM-OUTAGE H-1 LUBRICATION OF B-1 COAL FEEDER:Max | 2.6
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6005728 | PM-OUTAGE H-1 LUBRICATION OF B-2 COAL FEEDER:Max | 2.6
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6027807 | H-1 OUTAGE INSPECTION OF "A-2" COAL FEEDER | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6027808 | HMP&L OUTAGE LUBRICATION OF COAL FEEDERS | 2.6
ST001SGUFPECOALFEEDERS | STOC | BP11H034F | 6028867 | H-1 A2 BLAST GATE NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 60
ST001SGUFPECOALFEEDERS | STOC | BP11H034F | 6030948 | H-1 A2 MILL BLAST GATE REMOVAL | 40
ST001SGUFPECOALFEEDERS | STOC | BP11H034F | 6028869 | H-1 B2 BLAST GATE NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 60
ST001SGUFPECOALFEEDERS | STOC | BP11H034F | 6030949 | H-1 SPRING OUTAGE B-2 MILL BLAST GATE REMOVAL | 30
ST001SGUFPECOALFEEDERS | STOC | ST1PLO | 6028871 | H-1 A 2 COAL FEEDER EXPANSION JOINT NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 30
ST001SGUFPECOALFEEDERS | STOC | ST1PLO | 6028872 | H-1 B 2 COAL FEEDER EXPANSION JOINT NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 30
ST001SGUFPEP.A.FANS | RDM2 | ST1PLO | 6005670 | PM-OUTAGE H-1 INSPECTION OF "A" PRIMARY AIR FAN:Max | 60
ST001SGUFPEP.A.FANS | RDM2 | ST1PLO | 6005672 | PM-OUTAGE H-1 INSPECTION OF "B" PRIMARY AIR FAN:Max | 60
ST001SGUFPEPULVERIZERS | RDM2 | ST1PLO | 5678645 | Purchase and install Thermo-wells and temp:Max | 1
ST001SGUFPEPULVERIZERS | RDM2 | ST1PLO | 6005715 | PM-OUTAGE H-1 "A" PULVERIZER LUB INSPECTION:Max | 30
ST001SGUFPEPULVERIZERS | RDM2 | ST1PLO | 6005717 | PM-OUTAGE H-1 "B" PULVERIZER LUB INSPECTION:Max | 30
ST001SGUFPEPULVERIZERS | RDM2 | STMSGUFPE | 6029011 | H1 - Inspect both A & B pulverizer gearboxes | 1
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6028758 | PM-OUTAGE- H-1 B PULV. REPAIR INLET IMPACT AREAS FOUND ON INSPECTION | 55
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6027200 | PM-OUTAGE-H-1 A PULV. REPAIR INLET IMPAC | 55
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 5982296 | extend landings out and around all blast gate valves for safer access:Max | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005664 | PM-OUTAGE H-1 REMOVE "A" PULVERIZER COOLER FOR CLEANING:Max | 4
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005665 | PM-OUTAGE H-1 REMOVE "B" PULVERIZER COOLER FOR CLEANING:Max | 4
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005691 | PM-OUTAGE H-1 INSPECTION OF "A" PULVERIZER:Max | 45
ST001SGUMBCSEALAIRSYSTEM | STOC | ST1PLO | 6033066 | H-1 Seal Air Fan need to replace Air Supply Line to the Damper from the main header to the Damper on both A & B Fans | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6027285 | PM-OUTAGE H-1 "A" Mill Bypass East chec | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6032845 | PM-OUTAGE H-1 "A" Mill Bypass West check dampers:Max | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6027142 | PM-OUTAGE H-1 "B" Mill Bypass East chec | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6032848 | PM-OUTAGE H-1 "B" Mill Bypass West check dampers:Max | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005693 | PM-OUTAGE H-1 INSPECTION OF "B" PULVERIZER:Max | 45
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6020809 | H-1 B Pulverizer has excessive vibration on the pinon bearings needs to be checked out during the srring outage 2011 | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6030709 | H-1 A & B pulverizers classify mill balls | 90
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6022646 | H-1 A Mill need to inspect the outlet pipe and replace the transition chute during the spring outage 2011 | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6022647 | H-1 B mill need to inspect outlet pipe and replace the transition chute during the spring outage in 2011 | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6025417 | H-1 A mill West and East end Head Extension needs to be replaced during the spring outage in 2011 | 600
ST001SGUMBCL.P.HEADERSYSTEM | RDM3-OT | ST1PLO | 6025854 | H-1 low pressure header need to fabricate line on H-1 side 2nd floor to tie in into H-2 aux steam supply to gas turbine heater skid. Any questions call Richard. | 1
ST001SGUMBCL.P.HEADERSYSTEM | STOC | ST1PLO | 6026651 | H1 Low Press Hdr supply to Steam Coils. Need to replace piping from isolation valve on 2nd floor to A & B side Steam Coil isolation valves on FD Fan Pad | 250
ST001SGUMBCSEALAIRSYSTEM | RDM2 | ST1PLO | 6005674 | PM-OUTAGE H-1 INSPECTION OF "A" SEAL AIR FAN:Max | 4
ST001SGUMBCSEALAIRSYSTEM | RDM2 | ST1PLO | 6005676 | PM-OUTAGE H-1 INSPECTION OF "B" SEAL AIR FAN:Max | 4
ST001TGNMTCLUBEOILSYSTEM | RDM2 | ST1PLO | 6005699 | PM-OUTAGE H-1 VIBRATION ANALYSIS "DC" LUBE OIL PUMP:Max | 1
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6030349 | H-1 "A" BFP Rotating Element change out | 200
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005709 | PM-OUTAGE H-1 INSPECTION "A" COAL CLASSIFIER:Max | 60
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005711 | PM-OUTAGE H-1 INSPECTION "B" COAL CLASSIFIER:Max | 60

## H1 2012 Spring Outage
Location | Resource | Project | Work Order Number | W/O Description | Est. Hrs
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6027154 | PM-OUTAGE H-1 D.C. Lube Oil & Controls Clean and Inspect | 2
ST001EDTTSGSCRUBBERTRANSFMR | RDE1 | ST1PLO | 6027208 | PM-OUTAGE H-1 SCRUBBER 'A' TRANSFORMER CLEAN AND CHECK | 20
ST001TGNTGCMETER-RELAY | RDE1 | ST1PLO | 6027292 | PM-OUTAGE H-1 GEN CT's CLEAN & CHECK | 10
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6027245 | PM-OUTAGE H-1 SCRUBBER 480V SUBSTATION CLEAN AND CHECK | 20
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6053937 | PM-OUTAGE H-1 SEND OUT THE FOLLOWING MOTORS (see W.O. hierarchy) | 1
ST001SGUPRPPRECIPITATOR | STOC | BP11H018B | 6055129 | H-1 PRECIPITATOR - REMOVE EXISTING FALSE FLOOR BY OUTSIDE CONTRACTOR | 1
ST001SGUPRPPRECIPITATOR | STOC | BP11H018B | 6055128 | H-1 PRECIPITATOR - INSTALL NEW FALSE FLOOR BY OUTSIDE CONTRACTOR | 1
ST001SGUPRPPRECIPITATOR | STOC | ST1PLO | 6057933 | PM-OUTAGE H-1 PRECIPITATOR INSPECTION BY OUTSIDE CONTRACTOR | 1
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6027291 | PM-OUTAGE H-1 SCRUBBER 480V MCC CLEAN AND CHECK | 20
ST001CDSCSCCONDENSATEPUMPS | RDE1 | ST1PLO | 6056471 | PM-H-1 S/OUT "A" CONDENSATE PUMP MOTOR | 1
ST001CWSCCSCIRCULATORS | RDE1 | ST1PLO | 6056551 | PM-OUTAGE H-1 S/OUT "A" C.W.P. MOTOR | 1
ST001SGUMBCBOILER | STOC | ST1PLO | 6057215 | PM-OUTAGE H-1 COVER COST OF CONST. SETTING UP H-1 | 50
ST001SGUFPEP.A.FANS | RDE1 | ST1PLO | 6056109 | H-1-"A" P.A.FAN MOTOR WINDING TEMP. HIGH ALARM IN bad klixon has to be sent out | 1
ST001TGNTGCMETER-RELAY | RDE1 | ST1PLO | 6055887 | H-1 GENERATOR Mvar INDICATION TO PI IS NOT WORKING | 5
ST001SGUMBCSEALAIRSYSTEM | RDE1 | ST1PLO | 6056382 | PM-OUTAGE H-1 S/OUT "B" SEAL AIR FAN MTR | 1
ST001SGUMBCWESTTEMPPROBE | RDE1 | ST1PLO | 6057195 | PM-OUTAGE H-1 ACCUTEMP-PERFORM ROUTINE MAINTENANCE- REMOVE AND RE-INSTALL ALL MICROPHONES | 5
ST001SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST1PLO | 6027180 | PM-OUTAGE H-1 SB Cabinets clean & inspect | 20
ST001TGNMGCEXCITER | RDE1 | ST1PLO | 6056696 | PM-OUTAGE H-1 Gen Exciter clean/check | 22
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6027281 | PM-OUTAGE H-1 CLEAN AND CHECK "A" AUX PT | 14
ST001SGUFDEAIRPREHEATERS | RDE1 | ST1PLO | 6057176 | PM-OUTAGE H-1 A&B Radiator Fan Motors check | 2
ST001FGDSSCBOOSTERFANH-1 | RDE1 | ST1PLO | 6056428 | PM-OUTAGE H-1Scrubber Booster Fan Filter | 10
096132: HMP&L ONE PRECIPITATOR | RDE1 | ST1PLO | 6057775 | PM-OUTAGE H-1 Assist in precipitator field inspection | 50
ST001SGUFPEP.A.FANS | RDE1 | ST1PLO | 6056339 | PM-OUTAGE H-1 S/OUT "B" P.A. FAN MOTOR | 1
ST001SGUFDEAIRPREHEATERS | RDE1 | ST1PLO | 6027249 | PM-OUTAGE H-1 Air Heater A&B Controls | 2
ST001TGNMGCEXCITER | RDE1 | ST1PLO | 6056941 | H-1 OUTAGE GENERATOR EXCITER-UNWIRE AND REWIRE | 30
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6027143 | PM-OUTAGE H-1 "B" CLEAN AND CHECK STARTUP P.T.s | 14
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6056259 | PM-OUTAGE H-1 CLEAN/CHECK "B" AUX. PT | 14
ST001CDSCSCCONDENSATEPUMPS | RDE1 | ST1PLO | 6056448 | PM-H-1 SEND OUT "B" CONDENSATE PUMP MTR | 1
ST001CWSCCSCOOLTOWERSYSTEM | RDE1 | ST1PLO | 6056266 | PM-OUTAGE H-1C.T.Tower Lube System check | 8
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6027282 | PM-OUTAGE H-1 CLEAN AND CHECK "A" STARTUP P.T.S | 14
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057181 | PM-OUTAGE H-1 Precipitator Rappers inspect | 8
ST001SGUFPEPULVERIZERS | RDE1 | ST1PLO | 6056672 | PM-OUTAGE H-1 S/OUT "A" PULVERIZER MTR | 1
ST001SGUMBCSEALAIRSYSTEM | RDE1 | ST1PLO | 6056518 | PM-OUTAGE H-1 S/OUT "A" SEAL AIR FAN MTR | 1
ST001SGUFDEAIRPREHEATERS | RDE1 | ST1PLO | 6057174 | PM-OUTAGE H-1 Air Heater A&B Drive Motors check | 2
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6055845 | PM-OUTAGE H-1 SEND OUT #2 TURBINE LUBE OIL PUMP MOTOR | 1
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6057190 | PM-OUTAGE H-1 PERFORM EBOP TESTING | 11
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6055996 | H-1 PCC 1A 4KV transformer: Take oil sample for PCB testing. | 1
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6057191 | PM-OUTAGE H-1 480V Solid State Trip Device test | 30
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057183 | PM-OUTAGE H-1 Precipitator Clean Up | 6
ST001CWSCCSCONDENSERSYSTEM | RDE1 | ST1PLO | 6056682 | PM-OUTAGE H-1 SEND OUT "B" VAC PMP MTR | 1
ST001CWSCCSCONDENSERSYSTEM | RDE1 | ST1PLO | 6056349 | PM-OUTAGE H-1 SEND OUT "A" VAC PMP MTR | 1
ST001SGUFDEAIRPREHEATERS | RDE1 | ST1PLO | 6056591 | PM-OUTAGE H-1 A/H A&B Controls check | 4
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057185 | PM-OUTAGE H-1 Precipitatior Doors open | 10
ST001SGUFDEF.D.FANS | RDE1 | ST1PLO | 6056595 | PM-OUTAGE H-1 S/OUT "B" F.D. FAN MOTOR | 1
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6055843 | PM-OUTAGE H-1 SEND OUT TURBINE #1 LUBE OIL PUMP MOTOR | 1
ST001EDTTSGSTEPUPTRANSFMR | RDE1 | ST1PLO | 6056446 | PM-OUTAGE H-1 GROUND LEADS ON STEPUP T/F | 10
ST001FGDSSCABSORBERTWRH1 | RDE1 | ST1PLO | 6056528 | PM-OUTAGE H-1 SEND OUT "B" REC PMP MTR | 1
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6056558 | PM-OUTAGE H-1 SCR 480V MCC CLEAN/TEST | 20
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057180 | PM-OUTAGE H-1 Precipitator Controls clean & inspect | 8
ST001EDTDCSDCDIST.SYSTEM | RDE1 | ST1PLO | 6027244 | PM-OUTAGE H-1 Battery Charger clean & check | 4
ST001EDTTSGSTEPUPTRANSFMR | RDE1 | ST1PLO | 6057194 | PM-OUTAGE H-1, REMOVE GEN. LEADS AND CLEAN BUSHINGS | 60
ST001ASHCTRCONTROLS | RDE1 | ST1PLO | 6027206 | PM-OUTAGE H-1 Flyash Controls clean & check | 4
ST001FGDSSCREACTIONTKH1 | RDE1 | ST1PLO | 6057188 | PM-OUTAGE H-1 GREASE "B" BLEED SLURRY PUMP MOTOR BEARINGS | 1
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6055995 | H-1 PCC 1B 4KV transformer: Take oil sample for PCB testing. | 1
ST001TGNMTCLUBEOILSYSTEM | RDE1 | ST1PLO | 6055837 | PM-OUTAGE H-1 SEND OUT TURBINE EMERGENCY LUBE OIL PUMP MOTOR | 1
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057184 | PM-OUTAGE H-1 Precipitator Heaters check | 4
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6057192 | PM-OUTAGE H-1 480V Substation Breakers clean & check | 20
ST001EDTTSG480VBUS | RDE1 | ST1PLO | 6055407 | H-1 a cooling tower transformer hotspot indicator j box needs to be replaced | 5
ST001FGDSSCREACTIONTKH1 | RDE1 | ST1PLO | 6057187 | PM-OUTAGE H-1 GREASE "A" BLEED SLURRY PUMP MOTOR BEARINGS | 1
ST001TGNMTCTURNINGGEAR | RDE1 | ST1PLO | 6056320 | PM-OUTAGE H-1 T & G Turning Gear ck | 1
ST001TGNTGCMETER-RELAY | RDE1 | ST1PLO | 6057189 | PM-OUTAGE H-1 Gen PT's clean & check | 14
ST001SGUFPEP.A.FANS | RDE1 | ST1PLO | 6056584 | PM-OUTAGE H-1 S/OUT "A" P.A. FAN MOTOR | 1
ST001SGUFDEF.D.FANS | RDE1 | ST1PLO | 6056463 | PM-OUTAGE H-1 S/OUT "A" F.D. FAN MOTOR | 1
ST001SGUFPEPULVERIZERS | RDE1 | ST1PLO | 6056345 | PM-OUTAGE H-1 SEND OUT "B" PULV. MTR | 1
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057186 | PM-OUTAGE H-1 Precipitator T/R Sets clean & inspect | 12
ST001SGUPRPPRECIPITATOR | RDE1 | ST1PLO | 6057182 | PM-OUTAGE H-1 Precipitator Bushings & Supports clean | 24
ST001TGNMGCEXCITER | RDE1 | ST1PLO | 6036315 | H1 Generator: Upgrade Exciter Controls Firmware | 3
ST001EDTMCCMTR.CONT.CENTER | RDE1 | ST1PLO | 6027262 | PM-OUTAGE H-1 - 480V MCC clean & check | 20
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6053935 | PM-OUTAGE H-1 4160 Switchgear clean and test | 35
ST001TGNTGCVOLTAGEREG. | RDE1 | ST1PLO | 6055169 | PM-OUTAGE H-1 Gen Voltage Reg Inspection | 14
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6052758 | H-1 4KV switchgear: Open switchgear for detail information for replacement project. See T.Taylor for information. | 10
ST001CWSCCSCOOLTOWERSYSTEM | RDE1 | BP10S076F | 6056017 | H1 Cooling Tower: Provide temporary power for C and D Circ. Water Pump greasers durng outage of MCC. | 10
ST001EDTTSG4160VSWITCHGEAR | RDE1 | ST1PLO | 6052757 | H-1 4KV switchgear: Verify phasing diagrams and lable busses in switchgear. Dwgs in EE office. | 10
ST001EDTDCS480VMCC1B | RDE1 | ST1PLO | 6015478 | LOSS OF DC ALARM & 480 1B MAIN & TIE C:Max | 22
ST001CWSCCSCOOLTOWERSYSTEM | STOC | BP10S076F | 6008891 | Replacement of the Power Control Center on H1- Switchgear, MCC, VFD's, and Building:Max | 39
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6027235 | PM-OUTAGE H-1 Steam Coil Control Valve | 2
ST001TGNMTCLUBEOILSYSTEM | RDI1 | ST1PLO | 6027107 | PM-Outage H-1 Turbine L.O. Cooling Water | 1.5
ST001SGUMBCREHEATERS | RDI1 | ST1PLO | 6039022 | Bad Penhouse T/C,RA-34-1, R-17-5, P-13-1, Drum 45, Drum Top East | 60
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6008380 | PM-Outage H-1 Turbine Diff. Expansion Detector Ck Operation:Max | 1
ST001TGNMTCELECTROHYDSYSTEM | RDI1 | ST1PLO | 6008385 | PM-Outage H-1 Turbine EH Cooling Water Cont.& Valve Ck Op.:Max | 1.5
ST001CWSCCSCONDENSERSYSTEM | RDI1 | ST1PLO | 6008344 | PM-OUTAGE H-1 Hotwell Level Switches check operation.:Max | 2
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6008373 | PM-OUTAGE H-1 Steam Coil De-Superheater Controls checks:Max | 2
ST001TGNMTCSTEAMCHEST | RDI1 | ST1PLO | 6008386 | PM-Outage H-1 Turbine Steam Seal Valve & Controls Ck Op:Max | 2.5
ST001SCREME-NEMS | STOC | BP11H038F | 6049334 | H-1 SCR NEMS ANALYZER AND PROBE UPGRADE | 60
ST001EVSAE-AIREMISSIONS | RDI1 | ST1PLO | 6054986 | H1 flow monitor replace stack electronic box | 32
ST001SCREME-NEMS | STOC | BP11H038F | 6049335 | H-1 SCR NEMS ANALYZER AND PROBE UPGRADE | 40
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6057096 | PM-OUTAGE H-1 "B" MILL BYPASS DAMPER CHECK DAMPERS | 2
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6036113 | H1 DIFFERENTIAL EXPANSION COMING IN AND OUT AFTER UNIT HAS BEEN UP FOR A WHILE OF ALARM NEEDS TO BE CHECKED FOR ACCURACY SH TEMP 983 RH TEMP 995 | 8
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6057205 | PM-OUTAGE H-1 Classifier T/Cs check | 2
ST001TGNMTCL.P.CYLINDER | RDI1 | ST1PLO | 6008384 | PM-Outage H-1Turbine Exhaust Hood Spray Ctrl/Valve Ck Op:Max | 2
ST001PLCBCACCS | RDI1 | ST1PLO | 6056575 | PM-OUTAGE H-1CLEAN/INSPECT SECONDARY AIR FLOW AND FURNACE PRESS. TAPS | 4
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6056559 | PM-OUTAGE H-1 S/C Control Valve CHECK | 2
ST001BFWFWCF.W.HEATERS | RDI1 | ST1PLO | 6027163 | PM-OUTAGE H-1 H.P. Heater Level Alarms Check Operation | 10
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6056241 | PM-OUTAGE H-1 "B" FD Fan Outlet DAMPER CHECK DAMPER | 2
ST001EVSAE-AIREMISSIONS | RDI1 | ST1PLO | 6027283 | PM-OUTAGE H-1 CLEAN STACK DILUTION PROBE | 8
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6027084 | PM-OUTAGE H-1 Mill Taps & T/C's clean and check | 8
ST001SGUMBCBOILER | RDI1 | ST1PLO | 6056356 | PM-OUTAGE H-1 Boiler Taps CLEAN/CHECK | 100
ST001EVSAE-AIREMISSIONS | RDI1 | ST1PLO | 6027099 | PM-OUTAGE H-1 CEM Equiptment clean & check. | 8
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6057095 | PM-OUTAGE H-1 "A" MILL BYPASS WEST CHECK DAMPERS | 2
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6057201 | PM-OUTAGE H-1 A2 Coal Feeder check & calibrate | 16
ST001CDSCSCLOWPRESSUREHEATERS | RDI1 | ST1PLO | 6027150 | PM-OUTAGE H-1 L.P. Heater Level Alarms Check Operation | 10
ST001FGDSSCABSORBERTWRH1 | RDI1 | ST1PLO | 6027195 | PM-Outage H-1 Scrubber Inspect Instrumentation and Calibrate | 20
ST001SGUMBCSUPERHEATERS | RDI1 | ST1PLO | 6046714 | PRIMARY SUPER HEAT P-17-1 IN ALARM | 8
ST001CDSCSCCONDDISCHSYSTEM | RDI1 | ST1PLO | 6027090 | PM-OUTAGE H-1 DA Level Control & Valve Check Operation | 2
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6057204 | PM-OUTAGE H-1 B2 Coal Feeder check & calibrate. | 16
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6057206 | PM-OUTAGE H-1 Mill Lift Pump Gauges/T/Cs/Switches checks. | 8
ST001CDSCSCCONDMAKEUPSYSTEM | RDI1 | ST1PLO | 6027267 | PM-OUTAGE H-1 Condenser Level Control & Valve Checks | 3
ST001CDSCSCCONDDRAINTANK | RDI1 | ST1PLO | 6056274 | PM-Outage H-1 L.P. Drain Tank Controls | 2
ST001SGUMBCSEALAIRSYSTEM | RDI1 | ST1PLO | 6056646 | PM-OUTAGE H-1 "A" Seal Air test damper | 1
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6055737 | PM-OUTAGE H-1 "B" Hot Air check dampers | 2
ST001SGUMBCL.P.HEADERSYSTEM | RDI1 | ST1PLO | 6008372 | PM-OUTAGE H-1 Low Pressure Header Reg check operations:Max | 2
ST001SGUMBCSEALAIRSYSTEM | RDI1 | ST1PLO | 6027278 | PM-OUTAGE H-1 "A" Seal Air check damper drive | 1
ST001SGUMBCSTEAMDRUM | RDI1 | ST1PLO | 6055580 | H-1 east drum temp indicator alarm sounding Alarm: Area 55 H155TE-D6 Hi alarm and bad input Drum top east | 8
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6057200 | PM-OUTAGE H-1 A1 Coal Feeder check & calibrate | 16
ST001SGUMBCSUPERHEATERS | RDI1 | ST1PLO | 6055625 | H-1- superheat inlet before sprays high temp. alarming bad input | 8
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6057202 | PM-OUTAGE H-1 B1 Coal Feeder check & calibrate. | 3
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6027270 | PM-OUTAGE H-1 Coal Valve Solenoids & Limits Check | 8
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6056302 | PM-OUTAGE H-1 "B" PA Fan check dampers | 2
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6056321 | PM-OUTAGE H-1 Start Up Instrumentation | 100
ST001TGNTGCTURBINECONTROLS | RDI1 | ST1PLO | 6055677 | H-1 TURBINE-REMOVE AND RE-INSTALL LVDTs. | 60
ST001RIDBTGINDICATINGLIGHTS | RDI1 | ST1PLO | 6053755 | H-1-PRIMARY SUPERHEAT OUT TUBE WEST P-5-1 ON DAS ALARMS STAYING IN ALARM & READING ERRATIC | 8
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6057208 | PM-Outage H-1 Turbine/ Gen Cal, Press /Temp Gauges | 20
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6056409 | PM-OUTAGE H-1 "A" FD Fan Outlet DAMPER CHECK DAMPER | 2
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6027132 | PM-OUTAGE H-1 Remove Ignitor Rods & Check Operation | 8
ST001BFWFWCDASTORAGETANK | RDI1 | ST1PLO | 6027121 | PM-OUTAGE H-1 D.A. Level Switches check operation | 4
ST001TGNTGCTURBINECONTROLS | RDI1 | ST1PLO | 6055689 | H-1 TURBINE-REMOVE SERVOS AND INSTALL FLUSHING BLOCKS-REMOVE FLUSHING BLOCKS AND RE-INSTALL SERVOS AFTER EH FLUSH. | 40
ST001SGUMBCSEALAIRSYSTEM | RDI1 | ST1PLO | 6027219 | PM-OUTAGE H-1 "B" Seal Air check damper drive | 1
ST001SGUCTLMISC.INSTR. | RDI1 | ST1PLO | 6055593 | H-1-REHEAT TUBE READS ON DAS POINTS # (165-RH OUT WEST MID R-98), )(167-RH OUT MID R-17-5), (170-RH OUT EAST MID R-26-1) NOT READING | 8
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6055614 | PM-OUTAGE H-1 Air Heaters A&B Diff Taps clean & check | 4
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6056553 | PM-OUTAGE H-1 Scanners clean & check | 8
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6056670 | PM-OUTAGE H-1 "B" FD Fan Inlet DAMPER CHECK DAMPERS | 2
ST001BFWFWCBOILERFEEDPUMPS | RDI1 | ST1PLO | 6020134 | H-1 A boiler feed pump Balance drum leak off reading very High 90+ check on outage | 3
ST001BFWFWCPIPINGTOECONOMIZER | RDI1 | ST1PLO | 6027203 | PM-OUTAGE H-1 Feedwater Control Valve Check Operation | 2
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6057207 | PM-OUTAGE H-1 Burner Controls check. | 3
ST001FGDSSCREACTIONTKH1 | RDI1 | ST1PLO | 6027255 | PM-Outage H-1 Scrubber PH Probe Clean & Calibrate | 3
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6055738 | PM-OUTAGE H-1 "B" Cold Air check dampers | 2
ST001SGUMBCSUPERHEATERS | RDI1 | ST1PLO | 6055592 | PRIMARY SUPERHEAT TUBE P-1-1 TEMP NOT READING ACCURATELY | 8
ST001SGUCTLO-2SYSTEM | RDI1 | ST1PLO | 6027258 | PM-OUTAGE H-1 Remove Boiler 02 Probes and clean | 12
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6055736 | PM-OUTAGE H-1 "A" Cold Air check dampers | 2
ST001PLCBCACCS | RDI1 | ST1PLO | 6057198 | PM-OUTAGE-H-1 REMOVE AND CLEAN P.A. FLOW TRANSMITTERS | 2
ST001SGUMBCSOOTBLOWERSYSTEM | RDI1 | ST1PLO | 6027265 | PM-OUTAGE H-1 SB Pressure Reg & Valve check operation. | 3
ST001SGUCTLMISC.INSTR. | RDI1 | ST1PLO | 6056396 | H-1 Outage Inst. Cal. List (Linked Document) | 100
ST001SGUFPEP.A.FANS | RDI1 | ST1PLO | 6056513 | PM-OUTAGE H-1 "A" PA Fan check dampers | 2
ST001SGUMBCVALVES | RDI1 | ST1PLO | 6027186 | PM-OUTAGE H-1 Electromatic Relief Valve Check Operation | 4
ST001TGNTGCTURBINECONTROLS | RDI1 | ST1PLO | 6057209 | PM-OUTAGE H-1 STROKE TURBINE VALVES AND CALIBRATE | 8
ST001SGUMBCSEALAIRSYSTEM | RDI1 | ST1PLO | 6056527 | PM-OUTAGE H-1 "B" Seal Air test damper | 1
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6008381 | PM-Outage H-1 Turbine Rotor Position Check Operation:Max | 3
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6057199 | PM-OUTAGE H-1 Air Heater A& B Bearing T/C's checks | 2
ST001TGNMGCSEALOILSYSTEM | RDI1 | ST1PLO | 6027205 | PM-OUTAGE H-1 D.C. Seal Oil Controls Calibrate | 8
ST001SGUFDEF.D.FANS | RDI1 | ST1PLO | 6056328 | PM-OUTAGE H-1 "A" FD Fan Inlet DAMPER CHECK DAMPERS | 2
ST001SGUFPECOALFEEDERS | RDI1 | ST1PLO | 6053995 | H-1 COAL FEEDERS-UPGRADE COAL FEEDER CONTROLS | 32
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005650 | PM-OUTAGE H-1 "A" Mill Bypass East check dampers:Max | 2
ST001TGNTGCTURB.SUPV.INST. | RDI1 | ST1PLO | 6008379 | PM-Outage H-1 Turbine Eccentricity Detector-Check Operation:Max | 4
ST001BFWFWCATTEMPERATION | RDI1 | ST1PLO | 6008369 | PM-OUTAGE H-1 E&W R.H. Spray Control Valve check operation:Max | 4
ST001SGUFPEPULVERIZERS | RDI1 | ST1PLO | 6005652 | PM-OUTAGE H-1 "B" Mill Bypass East check dampers:Max | 2
ST001BFWFWCATTEMPERATION | RDI1 | ST1PLO | 6008370 | PM-OUTAGE H-1 E&W S.H. Spray Control Valve checks:Max | 4
ST001FGDSSCBOOSTERFANH-1 | RDI1 | ST1PLO | 6056354 | H-1 OUTAGE CALIBRATION OF BOOSTER FAN L.O. SYSTEM DEVICES | 8
ST001TGNTGCEMER.TRIP.INST. | RDI1 | ST1PLO | 6008378 | PM-Outage H-1 Turbine Protective Trip Devices Ck Operation:Max | 7
ST001SGUFDEAIRPREHEATERS | RDI1 | ST1PLO | 6008375 | PM-OUTAGE H-1 A.P. Htr Press. Switches/Gauges calabriate:Max | 6
ST001SGUMBCBURNERS | RDI1 | ST1PLO | 6005639 | PM-OUTAGE H-1 Cooling Air Valves clean & check:Max | 10
ST001SGUMBCSTEAMDRUM | RDI1 | ST1PLO | 6026407 | PM-OUTAGE H-1 Remove Drum Level Camera/MIRROR clean and check | 16
ST001TGNTGCMISC.TRUB.INST. | RDI1 | ST1PLO | 6015381 | PM-Outage H-1 Turbine/Gen: Controls, Vib, RTD's Ck Op:Max | 18
ST001SCRDDE-DAMPERS-B | RDI1 | ST1PLO | 6055856 | H1 pre heater t/c well replacement | 70
ST001TGNMGCHYDROGENSYSTEM | RDM3 | ST1PLO | 6005770 | PM-OUTAGE H-1 HYDROGEN DRYER.:Max | 10.5
ST001FGDSSCGASDUCTS | STOC | BP12H005B | 6055004 | Remove Existing H-1 Scrubber Stack Expansion joint | 0
ST001SGUFPEPULVERIZERS | STOC | BP12H022B | 6054897 | Install new Classiifer rejects Valves On H-1 | 0
ST001SGUMBCSEALAIRSYSTEM | STOC | BP12H004B | 6057123 | Removel H-1 seal air fan Foundations | 0
ST001FGDSSCGASDUCTS | STOC | BP12H022B | 6055014 | Install New H-1 Stack Expansion joint per Quote dated 12-2-11 | 0
ST001SGUMBCSEALAIRSYSTEM | STOC | BP12H004B | 6055876 | Install New H-1 Seal Air Fan Foundations | 0
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6053747 | H1 economizer out to scr diverter damper transition ductwork need to inspect for leaks | 160
ST001CDSCSCCONDENSATEPUMPS | STOC | ST1PLO | 6047678 | H-1 "A"&"B" heater drip pumps mounting bases are crumbling | 36
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6052218 | H1 cooling tower,wooden catwalk down inside of "A" eastside cell is busted. | 10
ST001TGNMTCELECTROHYDSYSTEM | RDM3 | ST1PLO | 6027118 | PM-Outage H-1 Turbine EH Cooling Water COOLER | 8
ST001SGUMBCINSULATION | STOC | ST1PLO | 6055551 | H1 Boiler screenwall access door at 7th floor has a crack in the top left corner of the door frame. Needs a new refract plug also | 16
ST001TGNMTCL.P.CYLINDER | STOC | ST1PLO | 6051022 | H1 right crossover leaking | 40
ST001SCRDDE-DUCTWORK | STOC | BP11H017B | 6042205 | H-1 scr multiple gas leaks one at inlet to scr one at inlet to catalyst | 1
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | BP11H017B | 6030658 | H-1 # 45 sootblower gas leaking aroung lance - INSULATION | 1
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6057405 | H-1 # 45 sootblower gas leaking aroung lance | 30
ST001SGUMBCINSULATION | STOC | ST1PLO | 6055590 | h1 - Replace the #8 soot blower wall penetration during Spring 2012 Outage / See Attachment | 60
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030422 | F cell west side valves leaking through and leaking between header and distribution piece | 16
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030438 | F cell, east side, south valve, leaking between header and distribution piece | 8
ST001TGNMGCSTATORDETAILS | STOC | ST1PLO | 6030932 | H-1 SPRING OUTAGE GENERATOR TD & TESTING | 80
ST001SCRDDE-DAMPERS-A | STOC | BP12H022B | 6054135 | REMOVAL - H1 "A" Damper to SCR Expansion Joint needs to be replaced | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030421 | E cell west side, North valve leaking at the shroud | 4
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030432 | E cell, east side, north valve leaking at shroud, and south valve needs to be rebuilt | 12
ST001TGNMGCSTATORDETAILS | STOC | ST1PLO | 6030931 | H-1 SPRING OUTAGE TURBINE & GENERATOR INSPECTON | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030435 | C cell, east side, south valve, leaking between header and distribution piece | 8
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030430 | C cell, east side, north valve is leaking through | 8
ST001SGUMBCINSULATION | STOC | BP11H042F | 6047070 | Install New EAST SIDE access (de-slag) door for the H1 unit AT ELEVATION 497'-8" | 50
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030425 | B cell, west side, south valve,, valve leaking through and leaking between header and distribution piece | 4
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030426 | C cell,, west side,, south valve,, valve leaking through and leaking between header and distribution piece | 8
ST001SCRDDE-DAMPERS-A | STOC | BP12H005B | 6037885 | INSTALLATION - H1 "A" Damper to SCR Expansion Joint needs to be replaced | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030434 | B cell, east side, south valve, leaking between header and distribution piece | 4
ST001CWSCCSCOOLTOWERSYSTEM | STOC | BP11H010B | 6048134 | Remove fill and structure during the H1 Spring outage 2012 | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030429 | B cell, east side, north valve will not shut | 8
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030420 | D cell west side leaking bad between header and distribution piece on both valves | 16
ST001SGUFPEPULVERIZERS | OPS | ST1PLO | 6056108 | H1 A&B MILL BALL REPLACEMENT | 32
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030419 | A cell west side ,,water leaking bad between header and distribution piece at both valves | 16
ST001SGUFDEAIR-GASDUCTS | STOC | BP12H005B | 6054134 | REMOVE - H1 Precip outlet expansion joint needs to be replaced | 1
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6030440 | F cell, east side, north valve, valve is leaking through | 8
ST001SCRDDE-DAMPERS-B | STOC | BP11H039F | 6037887 | H1 "B" Damper to SCR Expansion Joint needs to be replaced | 1
ST001SGUFDEAIR-GASDUCTS | STOC | BP12H005B | 6037882 | INSTALL - H1 Precip outlet expansion joint needs to be replaced | 1
ST001TGNMGCSTATORDETAILS | STOC | BP11H002B | 6030608 | Removal charges for rewedge on H1 generator | 1
ST001SGUMBCBURNERS | STOC | BP12H003B | 6051420 | Removal: Replace Low Nox Burners on H1 during the 2012 Spring Outage | 2000
ST001CWSCCSCOOLTOWERSYSTEM | STOC | BP10S006B | 6033435 | Removal Work order for H1 South Cooling tower controls | 1
ST001ASHARSHOPPERBOTASH | STOC | BP11H015B | 6055374 | INSTALLATION - RELOCATION OF THE H1 BOTTOM ASH REMOVAL HOPPER DURING THE 2012 SPRING OUTAGE | 1200
ST001SCRSHSSONICHORNS | STOC | BP11H017B | 6032250 | INSULATION -H1 scr catalyst reactor east side has gas leaks around the sonic horn gaskets. Need lagging removed to check where leaks are coming from | 1
ST001SGUMBCBOILER | STOC | ST1PLO | 6034785 | H-1 Cover the cost for a Elevator operator for the outage | 320
ST001SGUMBCBOILER | STOC | BP11H017B | 6032247 | PM-OUTAGE H-1 REPAIR ALL BOILER GAS LEAKS:(INSTALLATION) INSULATION | 1
ST001SGUMBCBOILER | STOC | BP11H017B | 6005688 | PM-OUTAGE H-1 REPAIR ALL BOILER GAS LEAKS (REMOVAL):Max INSULATION | 1
ST001FGDSSCABSORBERTWRH1 | RDM2 | ST1PLO | 6056477 | H-1 OUTAGE LUBRICATION OF SCRUBBER ITEMS | 1.5
ST001TGNMTCL.P.CYLINDER | RDM3 | ST1PLO | 6027301 | PM-Outage H-1Turbine Exhaust Hood Spray | 4
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6056637 | H-1 OUTAGE INSPECTION LUBE OIL TANK VAPOR EXTRACTOR | 6
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6050999 | # 30 S/B Seal air box needs to be replaced. | 30
ST001TGNMGCSEALOILSYSTEM | RDM3 | ST1PLO | 6050234 | H1 main seal oil pump, has several small oil leaks, at inboard and outboard pump bearings also at outlet side of pump seal is leaking | 30
ST001BFWFWCRECIRCSYSTEM | RDM3 | ST1PLO | 6052806 | Isolation valves on both sides of H-1 "A" Boiler Feed Pump Recirculation Valve need to be replaced. Leaking through. | 3
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6053439 | Install port cleaners on all of h1 coal feeders front and back ports. Like the one installe on h2 a1 coal feeder south port | 12
ST001SGUMBCINSULATION | STOC | ST1PLO | 6047956 | H1 PENTHOUSE ROOF NEEDS REPLACING | 1
ST001SGUMBCVALVES | RDM3 | ST1PLO | 6053442 | H1 Main Steam Isolation Valve needs to be re-packed (leaking) | 12
ST001CDSCSCLOWPRESSUREHEATERS | RDM2 | ST1PLO | 6055587 | H1 #2 heater northtrap extration, handle missing off of drain, 1st floor by alt drain / See attachment | 3
ST001SGUMBCREHEATERS | RDM2 | ST1PLO | 6035281 | h-1 re heat root valve on west side of boiler @5&1/2 floor will not operate | 8
ST001SGUFPEPULVERIZERS | RDM2 | ST1PLO | 6027174 | PM-OUTAGE H-1 REMOVE "A" PULVERIZER COOL FOR CLEANING | 4
ST001SGUFPEPULVERIZERS | RDM2 | ST1PLO | 6058734 | PM-OUTAGE H-1 REMOVE "B" PULVERIZER COOL FOR CLEANING | 4
ST001SGUMBCSEALAIRSYSTEM | RDM2 | ST1PLO | 6056521 | H-1 OUTAGE INSPECTION OF "B" SEAL AIR FAN | 4
ST001SGUMBCVALVES | STOC | ST1PLO | 6029493 | H1 Electromatic leaking through. | 16
ST001SGUMBCSEALAIRSYSTEM | RDM2 | ST1PLO | 6056640 | H-1 OUTAGE INSPECTION OF "A" SEAL AIR FAN | 4
ST001TGNMTCLUBEOILSYSTEM | RDM3 | ST1PLO | 6005755 | PM-OUTAGE H-1 BOWSER SYSTEM PUMP COUPLINGS:Max | 2.5
ST001SGUMBCBOILER | STOC | ST1PLO | 6056816 | H1 BOILER AIR TEST DOORS - 2012 SPRING OUTAGE | 5
ST001FGDSSCABSORBERTWRH1 | RDM2 | ST1PLO | 6056983 | H1 absorber outlet temp well repairs | 16
ST001TGNMTCSTEAMCHEST | RDM3 | ST1PLO | 6027257 | PM-Outage H-1 Turbine Steam Seal Valve & | 8
ST001SGUMBCBLRTUBES/HEADERS | STOC | STMSGU | 6053578 | H-1 waterwall drains seperate drains from the other boiler drains coming off the manofold | 100
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6027227 | PM-OUTAGE H-1 OBTAIN TIGHT WIRE OF RWW DTUBES | 10
ST001CWSCCSCONDENSERSYSTEM | RDM3 | ST1PLO | 6056348 | PM-OUTAGE H-1 INSPECT CONDENSER DOORS | 30
ST001CWSCCSCOOLTOWERSYSTEM | RDM3 | ST1PLO | 6005749 | PM-OUTAGE H-1 PM C.T. DISTRIBUTION HEADER WEST AIR RELIEF:Max | 10.5
ST001TGNMTCELECTROHYDSYSTEM | STOC | ST1PLO | 6033849 | H-1 Lube Oil is getting into the EH system | 11
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6028745 | PM-OUTAGE H-1 DYE CHECK SOUTH WATER WALL HMP&L ONE | 11.5
ST001FGDSSCREACTIONTKH1 | RDM2 | ST1PLO | 6029304 | H-1 SPRING 2012 OUTAGE SEND OUT AGITATOR BLADES TO BE REFURBISHED BY A OUTSIDE VENDOR | 12
ST001SGUMBCWESTTEMPPROBE | RDM3 | ST1PLO | 6005662 | PM-OUTAGE H-1 WEST FURNACE TEMP. PROBE INSPECT:Max | 40
ST001ASHARSBOTASHREMOVAL | STOC | ST1PLO | 6005656 | PM-OUTAGE H-1 INSECTION OF WET BOTTOM LANCING DOORS:Max | 16
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6031111 | Mill ball classification on A and B mills | 80
ST001FGDSSCGASDUCTS | STOC | ST1PLO | 6051247 | H-1 Inspection of the Scrubber Duct Work and expansion Joints - from the precip outlet to the booster fan duiring the 2012 Planned Outage on H1 | 16
ST001SGUMBCSTEAMDRUM | STOC | ST1PLO | 6056013 | H1 east steam drum bottom isolation valve and root valve need replacing and positioned to operate with out cutting off valve handle | 30
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6005536 | #42 seal air box plugged and scraers worn:Max | 30
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 5984115 | H1 Sootblower #27 scraper is bad:Max | 30
ST001SGUFPEBUNKERCOALVALVE | STOC | ST1PLO | 6035107 | H-1 B-2 coal feeder Downspout is thin needs to repaired patch is painted green on 2nd floor | 80
ST001SGUMBCBURNERS | RDM3 | ST1PLO | 6056598 | H-1 OUTAGE INSPECTION OF BURNERS COOLING AIR FAN | 20
ST001CWSCCSCIRCULATORS | RDM3 | ST1PLO | 5983656 | Stub valve line leaking where it is welded onto discharge line:Max | 20
ST001CWSCCSCOOLTOWERSYSTEM | RDM3 | ST1PLO | 6005747 | PM-OUTAGE H-1 PM C.T. DISTRIBUTION HEADER EAST AIR RELIEF:Max | 20.5
ST001SGUMBCVALVES | STOC | ST1PLO | 6056729 | REPLACE S.E. WATER WALL DRAIN VALVE DURING THE H1 2012 SPRING OUTAGE | 24
ST001SGUMBCVALVES | STOC | ST1PLO | 6056728 | REPLACE N.W. WATER WALL DRAIN VALVE DURING THE H1 2012 SPRING OUTAGE | 24
ST001SGUMBCVALVES | STOC | ST1PLO | 6056725 | Replace N.E. water wall drain valve during the H1 2012 Spring Outage | 24
ST001SGUMBCVALVES | STOC | ST1PLO | 6056730 | REPLACE S.W. WATER WALL DRAIN VALVE DURING THE H1 2012 SPRING OUTAGE | 24
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6049999 | H1 #9 SB air box packing is leaking | 30
ST001SGUFPECOALFEEDERS | STOC | BP12H010B | 6052756 | Replace H1 A1 blast gate during the H1 2012 Spring Outage - REMOVAL | 20
ST001SGUFDEAIRPREHEATERS | RDM3 | ST1PLO | 6056634 | PM-OUTAGE-H-1 "B" A/H LUBE OIL RADIATOR | 30
ST001SGUFPECOALFEEDERS | STOC | ST1PLO | 6028871 | H-1 A 2 COAL FEEDER EXPANSION JOINT NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 30
ST001SGUFPECOALFEEDERS | STOC | ST1PLO | 6028872 | H-1 B 2 COAL FEEDER EXPANSION JOINT NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 30
ST001SGUMBCREHEATERS | STOC | ST1PLO | 6057241 | H1 Boiler Back pass inspection during the 2012 Spring Outage | 30
ST001SGUFPECOALFEEDERS | STOC | BP12H010B | 6052764 | Replace H1 B1 Blast gate during the H1 2012 Spring outage - REMOVAL | 20
ST001SGUFDEAIRPREHEATERS | RDM3 | ST1PLO | 6056536 | PM-OUTAGE-H-1 "A" A/H LUBE OIL RADIATOR | 30
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 5982306 | Replace T-11 Material swedge with correct T-22:Max | 80
ST001SGUMBCBOILER | STOC | ST1PLO | 6056815 | H1 BOILER HYDRO DURING THE 2012 SPRING OUTAGE | 30
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6009720 | Left hand reheat stop valve drain line leak through to atmosphere:Max | 30
ST001SGUMBCINSULATION | STOC | BP11H042F | 6055577 | Removal - Installation of East side Boiler Access door at elevation 497'-8" on H1 | 32
ST001TGNMTCSTEAMTRAPS | RDM3 | ST1PLO | 6008987 | Steam Trap needs replacing:Max | 32
ST001SCRDDE-DUCTWORK | STOC | ST1PLO | 6031665 | Need sample grid lines cleaned or replaced. 5/8 size tubing. 30 lines total same as we did on H2 | 60
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 6025664 | H-1-PM-OUTAGE INSPECTION OF FLUE GAS QUENCHING SYSTEM | 38
ST001SGUMBCINSULATION | STOC | BP12H025B | 6055579 | Install new deslag door on the west side of H1 during the H1 Spring outage 2012 at elevation 497' -8" | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6025954 | PM-OUTAGE INSPECT THE VARIABLE ORIFICES | 80
ST001SGUMBCINSULATION | STOC | BP12H025B | 6055581 | REMOVAL - Install new deslag door on the west side of H1 during the H1 Spring outage 2012 at elevation 497' -8" | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6056571 | H-1 OUTAGE INSPECTION OF "A-1" COAL FEEDER | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6056514 | H-1 OUTAGE INSPECTION OF "A-2" COAL FEEDER | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6056305 | H-1 OUTAGE INSPECTION OF "B-1" COAL FEEDER | 40
ST001SGUFPECOALFEEDERS | RDM2 | ST1PLO | 6056454 | H-1 OUTAGE INSPECTION OF "B-2" COAL FEEDER | 40
ST001SGUFDEF.D.FANS | STOC | ST1PLO | 6028747 | PM-OUTAGE H-1 DYE CHECK "A" & "B" F.D. FANS | 40
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005691 | PM-OUTAGE H-1 INSPECTION OF "A" PULVERIZER:Max | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005693 | PM-OUTAGE H-1 INSPECTION OF "B" PULVERIZER:Max | 100
ST001TGNMTCTURNINGGEAR | STOC | ST1PLO | 6032747 | H-1 turbine turning gear inspect for excessive wear. Making grinding noise when yrying to mesh. | 45
ST001CWSCCSCOOLTOWERSYSTEM | RDM3 | BP10S006B | 6030418 | Provide assistance for H1 Cooling Towers Controls Installation, Check Out, and Start-up | 54
ST001ASHFARFLYASHSYSTEM | STOC | ST1PLO | 6005686 | PM-OUTAGE H-1 REPLACEMENT ECONOMIZER HOPPER VALVES:Max | 57
ST001SGUFPECOALFEEDERS | STOC | BP12H010B | 6052762 | Replace H1 B1 Blast gate during the H1 2012 Spring outage - INSTALLATION | 20
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6005741 | PM-OUTAGE H-1 OF REVERSE CURRENT VALVES:Max | 1
ST001SGUFPECOALFEEDERS | STOC | BP12H010B | 6052755 | Replace H1 A1 blast gate during the H1 2012 Spring Outage - INSTALLATION | 20
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005709 | PM-OUTAGE H-1 INSPECTION "A" COAL CLASSIFIER:Max | 120
ST001SGUMBCBOILER | STOC | ST1PLO | 6031967 | H-1 Inspect boiler Drain and Vent Lines | 60
ST001SCRSHSSONICHORNS | STOC | ST1PLO | 6056962 | H1 scr catalyst reactor east side has gas leaks around the sonic horn gaskets. Need lagging removed to check where leaks are coming from | 120
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6005711 | PM-OUTAGE H-1 INSPECTION "B" COAL CLASSIFIER:Max | 120
ST001TGNMTCMAINSTOPVALVE | STOC | ST1PLO | 6025767 | H-1 Turbine Valve Inspection - Remove and replace Insulation | 1
ST001SGUFDEF.D.FANS | STOC | ST1PLO | 6032025 | H-1 Outage Inspection of A & B FD Fan Housing | 60
ST001SGUFPEP.A.FANS | RDM2 | ST1PLO | 6056298 | H-1 OUTAGE INSPECTION OF "B" PRIMARY AIR FAN | 60
ST001FGDSSCBOOSTERFANH-1 | STOC | ST1PLO | 6055741 | OUTAGE INSPECTION OF H1 BOOSTER FAN DURING THE 2012 SPRING OUTAGE | 80
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6031965 | H-1 Inspect windbox during the spring outage | 60
ST001SGUFPEP.A.FANS | RDM2 | ST1PLO | 6056508 | H-1 OUTAGE INSPECTION OF "A" PRIMARY AIR FAN | 60
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6025665 | H-1-PM-OUTAGE TAKE THICKNESS READING OF COAL PIPING | 60
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 5982324 | H1 SCRUBBER SAMPLE SINK DRAIN NEED TO REMOVE FIBERGLASS AND REPALCE WITH STRAINLESS:Max | 80
ST001BFWFWCDASTORAGETANK | STOC | ST1PLO | 6005735 | PM-OUTAGE H-1 INSPECTION OF DEAERATOR STORAGE TANK:Max | 63
ST001SGUMBCBOILER | STOC | ST1PLO | 6056817 | Install PVC drain line from economizer hoppers for boiler back pass wash during the H1 spring outage | 64
ST001SGUMBCL.P.HEADERSYSTEM | STOC | ST1PLO | 6005743 | PM-OUTAGE H-1 INSPECTION OF STEAM COILS:Max | 64
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6022632 | H-1 west wet bottom Ash gate and seal needs to be changed out during the spring outage 2012 | 60
ST001ASHARSHOPPERBOTASH | STOC | ST1PLO | 6022633 | H-1 East wet bottom ash gate and seal needs to be replaced during the spring outage 2012 | 60
ST001TGNMTCHP-IPCYLINDER | STOC | ST1PLO | 6023657 | H-1 Emergency Blow Down Valve Mid Term Inspections spring outage 2012 | 1
ST001SCRDDE-DAMPERS-A | STOC | ST1PLO | 6029076 | Replace H1 diverter damper seals on "A" damper | 120
ST001SCRDDE-DAMPERS-B | STOC | ST1PLO | 6029077 | replace H1 diverter damper seals on "B" damper | 120
ST001SGUFDEF.D.FANS | RDM2 | ST1PLO | 6056425 | H-1 OUTAGE INSPECTION OF "B" FORCED DRAFT FAN | 75
ST001SGUFDEF.D.FANS | RDM2 | ST1PLO | 6056566 | H-1 OUTAGE INSPECTION OF "A" FORCED DRAFT FAN | 75
ST001FGDSSCABSORBERTWRH1 | STOC | ST1PLO | 6056378 | H-1 OUTAGE INSPECTION OF RECYCLE HEADER & NOZZLES | 80
ST001ASHFARFLYASHSYSTEM | RDM3 | ST1PLO | 6056531 | H-1 OUTAGE REPLACEMENT PRECIPITATOR HOPPER VALVES | 81
ST001SGUFDEAIRPREHEATERS | STOC | ST1PLO | 6056588 | H-1 OUTAGE INSPECTION OF AIR PREHEATER | 100
ST001SGUMBCSOOTBLOWERSYSTEM | STOC | ST1PLO | 6028718 | PM-OUTAGE H-1 INSPECTION OF SOOT BLOWERS HMP&L ONE | 87.8
ST001SGUMBCBOILER | STOC | ST1PLO | 6056361 | H-1 OUTAGE OBTAIN A TUBE SAMPLE from REHEAT, ECONOMIZER, TARGET WALL, WW, PRI. SH, RAD. SH INLET AND OUTLET | 92
ST001FGDSSCBOOSTERFANH-1 | STOC | ST1PLO | 6026171 | H-1 Booster Fan Replace lagging on front sections of Fan during the spring outage 2012 | 1
ST001ASHARSBOTASHREMOVAL | STOC | ST1PLO | 6056248 | H-1 OUTAGE PM OF EAST HYDROEJECTOR | 94
ST001ASHARSBOTASHREMOVAL | STOC | ST1PLO | 6056486 | H-1 OUTAGE PM OF WEST HYDROEJECTOR | 94
ST001SGUMBCVALVES | STOC | ST1PLO | 6028835 | H-1 OUTAGE NEED TO CLEAN OUT ALL SAFETY VALVE DIP PANS | 100
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 6028900 | H-1 NEED TO INSPECT INLET DUCT AREA TO THE REACTION TANK WHERE THE HASTALLOY METAL IS | 100
ST001SCRDDE-DUCTWORK | STOC | ST1PLO | 6030738 | replace h1 top layer of catalyst seals old ones warpped | 180
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 5982296 | extend landings out and around all blast gate valves for safer access:Max | 100
ST001SGUMBCBOILER | STOC | ST1PLO | 6031497 | H-1 Repair Gas Leaks on the Boiler | 100
ST001SGUFDEF.D.FANS | STOC | ST1PLO | 5920647 | H1 B FD Fan shaft on the Inboard end needs to be built up and turned down also thrust:Max | 100
ST001SGUMBCSTEAMDRUM | STOC | ST1PLO | 5934855 | Replace insulation on steam drum inside penthouse:Max | 100
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 5934613 | The refractory block wall between the economizer:Max | 100
ST001SGUMBCREHEATERS | STOC | ST1PLO | 6055925 | H-1-PM-OUTAGE HOT REHEAT PIPING INSPECTION | 1
ST001SGUMBCVALVES | STOC | ST1PLO | 6026241 | H-1 PM-OUTAGE Inspection of the Main Steam Piping | 1
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6028969 | H-1 NEED TO INSPECT AND MAKE REPAIRS TO THE BY-PASS STACK DAMPER | 100
ST001SGUFPEP.A.FANS | STOC | ST1PLO | 6025200 | H-1 "A" P.A. Hot air duct leaking bad on hard deck. West side | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6022646 | H-1 A Mill need to inspect the outlet pipe and replace the transition chute during the spring outage 2011 | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6022647 | H-1 B mill need to inspect outlet pipe and replace the transition chute during the spring outage in 2012 | 100
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6020809 | H-1 B Pulverizer has excessive vibration on the pinon bearings needs to be checked out during the spring outage 2012 | 100
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6028943 | H-1 Install and Remove boiler scaffolding for Water Wall Inspection | 1
ST001CW-CWSCOOLINGWTRSYS | RDM3 | ST1PLO | 6056308 | PM-OUTAGE H-1 OPEN/CLOSE ALL HEAT EXCHANGERS | 120
ST001SGUMBCL.P.HEADERSYSTEM | STOC | BP11H019B | 6026253 | H1 Steam coils - Replace six steam coils | 125
ST001SGUMBCL.P.HEADERSYSTEM | STOC | BP11H019B | 6026267 | H-1 Steam Coils - replace six | 125
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6005695 | PM-OUTAGE H-1 INSPECTION OF SOUTH COOLING TOWER:Max | 100
ST001SGUFDEAIR-GASDUCTS | STOC | ST1PLO | 6026107 | H-1 Hot air supply header to the FD Fans needs to be replaced during the spring outage 2012 | 120
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6027202 | OBSERVATION PORTS OUTAGE INSPECTION HMP&L ONE | 150
ST001SGUMBCREHEATERS | STOC | ST1PLO | 6027228 | PM-OUTAGE H-1 INSPECTION OF HIGH TEMP REheater | 195.9
ST001FGDSSCBOOSTERFANH-1 | STOC | ST1PLO | 6028896 | H-1 BOOSTER FAN BLADE TIPS NEEDS TO BE REPLACED DURING THE SPRING OUTAGE | 500
ST001SGUFDEAIR-GASDUCTS | STOC | BP11H017B | 6055723 | REMOVAL: H-1 West and East Expansion joint need to replace Lagging and Insulation | 1
ST001SGUFDEAIR-GASDUCTS | STOC | BP11H017B | 6026103 | H-1 West and East Expansion joint need to replace Lagging and Insulation | 1
ST001TGNMTCMAINSTOPVALVE | STOC | ST1PLO | 6022651 | H-1 TURBINE STOP VALVES-MID TERM INSPECTION | 1
ST001CDSCSCLOWPRESSUREHEATERS | STOC | ST1PLO | 6005737 | PM-OUTAGE H-1 INSPECTION OF DEAERATOR HEATER:Max | 210
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6022656 | H-1 TURBINE LEFT HAND REHEAT/INTERCEPT VALVE-MID TERM INSPECTION | 1
ST001TGNMTCREHT/INTERCPT/RCV | STOC | ST1PLO | 6022652 | H-1TURBINE RIGHT HAND REHEAT/INTERCRPT VALVE- MID TERM INSPECTION | 1
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6025667 | H-1-PM- OUTAGE INSPECTION OF BOILER BUCK STAYS | 120.5
ST001SGUMBCBOILER | STOC | ST1PLO | 6028828 | PM-OUTAGE H-1 BOILERMAKERS NON-ANTICIPATED WORK | 250
ST001SGUMBCL.P.HEADERSYSTEM | STOC | ST1PLO | 6026651 | H1 Low Press Hdr supply to Steam Coils. Need to replace piping from isolation valve on 2nd floor to A & B side Steam Coil isolation valves on FD Fan Pad | 250
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6025417 | H-1 A mill West and East end Head Extension needs to be replaced during the spring outage in 2012 | 400
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 6030173 | H-1Primary Super Heater Pin casing in the Pent house needs to be replace damaged due to a tube leak all the way across the boiler | 300
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 6056629 | H-1 OUTAGE INSPECTION OF RADIANT SUPERHEATER | 300.9
ST001SGUMBCSUPERHEATERS | STOC | ST1PLO | 6010470 | H-1 Super Heater inlet loops need to replace the 2 outer loops on each elements:Max | 350
ST001SGUMBCBOILER | STOC | ST1PLO | 6026018 | H-1 BOILER HEADER INSPECTION TO BE PERFORMED DURING THE SPRING OUTAGE 2012 | 350
ST001SGUMBCBOILER | STOC | ST1PLO | 6026017 | H-1 BOILER WATERWALL TUBE SURVEY TO BE PERFORM DURING THE SPRING OUTAGE 2012 | 350
ST001SGUFPEPULVERIZERS | STOC | ST1PLO | 6054563 | H1 - B Mill replace mill head extensions west and east during the 2012 Spring Outage | 400
ST001CWSCCSCOOLTOWERSYSTEM | STOC | BP11H010B | 6026271 | Install Gulwing fill and PVC coated grids along with replacement of longitudinal/transverse 2x4's on Cell D,E, and F during the H1 Spring 2012 outage. | 1
ST001TGNMGCGENERATORROTOR | STOC | BP11H002B | 6025782 | H-1 Rewedge of the Generator During the Spring Outage 2012 | 1
ST001TGNMTCSTEAMCHEST | STOC | ST1PLO | 6022703 | H-1 TURBINE GOVERNOR VALVES- MID TERM INSPECTION SPRING OUTAGE 2011 | 1
ST001SGUMBCBOILER | STOC | ST1PLO | 6005667 | PM-OUTAGE H-1 COVER COST OF TOOL RM CLERK & LABORER:Max | 720
ST001SGUMBCBOILER | STOC | ST1PLO | 6005666 | PM-OUTAGE H-1 COVER COST OF BOILERMAKER SUPERVISION:Max | 900
ST001SGUFDEAIRPREHEATERS | STOC | BP11H009B | 6030600 | Removal of CE AH Baskets on H1 "A" and "B" APH's | 2600
ST001SGUFDEAIRPREHEATERS | STOC | BP11H009B | 6022003 | Installation of new CE AH Baskets on H1 "A" and "B" APH's | 2600
ST001SGUMBCBURNERS | STOC | BP12H003B | 6051417 | Installation: Replace Burners on H1 during the Spring Outage of 2012 | 2300
ST001CWSCCSCOOLTOWERSYSTEM | STOC | ST1PLO | 6031052 | H-1 south cooling tower clean basin | 32
ST001FGDSSCREACTIONTKH1 | OPS | ST1PLO | 6028749 | OUTAGE CLEANING BOTTOM OF CEILING IN REACTION TANK | 22
ST001SGUMBCBOILER | OPS | ST1PLO | 6005708 | PM-OUTAGE H-1 OUTSIDE VENDOR VACUUM PENTHOUSE/DEAD AIR SPACE:Max | 75
ST001SGUMBCSTEAMDRUM | STOC | ST1PLO | 6058177 | Open/close H1 Boiler drum for inspection and permit renewal during the H1 2012 Spring Outage. | 24
ST001SGUMBCBOILER | STOC | ST1PLO | 6058181 | H1 open/close boiler doors during the H1 2012 Spring Outage | 40
ST001SGUMBCBOILER | RDM3 | ST1PLO | 6058567 | PM- H1 BOILER INSPECTION BY SUPERVISOR | 4
ST001SGUMBCVALVES | STOC | ST1PLO | 6058586 | Replace Standpipe on H1 Electromatic with Stainless Steel Pipe. | 60
ST001SGUMBCBOILER | STOC | ST1PLO | 6028959 | H-1 SPRING OUTAGE 2012 REFRACTORY REMOVAL AND REPLACEMENT IN THE BOILER | 1
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6058668 | Drain and refill oil sumps on H1 A and B BFP's during the 2012 Spring Outage | 6
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6056452 | H-1 OUTAGE INSPEC OF "A" BOILER FEED PUMP COUPLING | 20
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6056312 | H-1 OUTAGE INSPEC OF "B" BOILER FEED PUMP COUPLING | 20
ST001BFWFWCBFPSUCTPIPING | RDM3 | ST1PLO | 6027097 | CLEAN OUT "A" BOILER FEED PUMP SUCTION STRAINERS | 6
ST001BFWFWCBFPSUCTPIPING | RDM3 | ST1PLO | 6027222 | CLEAN OUT "B" BOILER FEED PUMP SUCTION STRAINERS | 6
ST001SGUMBCBURNERS | RDI1 | BP12H003B | 6051417 | Installation: Replace Burners on H1 during the Spring Outage of 2012 (INSTRUMENT) | 80
ST001SGUMBCBURNERS | RDI1 | BP12H003B | 6051420 | Removal: Replace Low Nox Burners on H1 during the 2012 Spring Outage (INSTRUMENT) | 20
ST001SCRDDE-DUCTWORK | STOC | ST1PLO | 6058740 | H1 SCR obtain catalyst samples from each layer | 60
ST001SCRAMF-FLOCTRLUNIT | STOC | ST1PLO | 6057925 | H-1 Ammonia grid inlet valve (HV-501) is possibly leaking through - new valve on order 2-2-12 | 20
ST001FGDSSCREACTIONTKH1 | STOC | ST1PLO | 6058829 | Plum up Absorber Tower Agitator connection flanges with agitator motors. | 100
ST001FGDSSCABSORBERTWRH1 | STOC | ST1PLO | 6058833 | PM - H1 OUTAGE INSPECTION/CLEANING OF ME NOZZLES ALSO INSTALL FLANGES ON THE ENDS ME WASH HEADERS | 100
ST001BFWFWCBOILERFEEDPUMPS | RDM3 | ST1PLO | 6058864 | H1 "B" BFP "pump" overhaul, remove existing pump and install rebuilt pump during the 2012 Spring Outage | 500
ST001SGUMBCBOILER | STOC | ST1PLO | 6058908 | H1 Outage Contractor Mobilization/Demob, Spring Outage 2012 | 300
ST001SGUMBCBLRTUBES/HEADERS | STOC | ST1PLO | 6058917 | H1 Penthouse inspection/repairs during the 2012 Spring outage | 400
ST001CWS | STOC | BP10S006B | 6030418 | H1 Cooling Tower Controls - Electrical | 80
ST001CWS | RDI1 | BP10S006B | 6030418 | H1 Cooling Tower Controls - Instrument | 60

## H2 2012 Spring Outage 10 day
Location | Resource | Project | Work Order Number | W/O Description | Est. Hrs
ST002ASHFARFLYASHSYSTEM | STOC | ST2PLO | 6047541 | H-2 OUTAGE REPLACEMENT OF ECONOMIZER HOPPER VALVES | 57
ST002SCRDDE-DUCTWORK | STOC | ST2PLO | 6052373 | H2 SCR - repair gas leaks during the H2 winter outage 2012. | 80
ST002SCRDDE-DUCTWORK | STOC | BP12H013B | 6048662 | H2 SCR - lagging and insulation during the H2 winter outage 2012. | 0
ST002SCRDDE-DUCTWORK | STOC | ST2PLO | 6048658 | Repair Gas Leak on south side of the SCR outlet duct. Looks like repair can be made from the inside. Can get a good look at it from the west side of H2. | 16
ST002SGUFDEAIR-GASDUCTS | STOC | BP12H013B | 6048652 | Repair lagging on H2 east breeching (horizontal) expansion joint and duct. NE corner of duct approx. 20 sq ft. | 1
ST002SGUFDEAIRPREHEATERS | STOC | ST2PLO | 6048674 | HMP&L AIR PREHEATER A and B OUTAGE INSPECTION PM | 81
ST002SGUFDEAIRPREHEATERS | STOC | ST2PLO | 6048696 | PM-H-2 OUTAGE "B" A/H LUBE OIL RADIATOR | 30
ST002SGUFDEAIRPREHEATERS | STOC | ST2PLO | 6048716 | PM-H-2 OUTAGE "A" A/H LUBE OIL RADIATOR | 30
ST002SGUMBCBLRTUBES/HEADERS | STOC | ST2PLO | 6048688 | OBSERVATION PORTS OUTAGE INSPECTION HMP&L TWO | 154
ST002SGUMBCBOILER | STOC | ST2PLO | 6048691 | H-2 OUTAGE OBTAIN A TUBE SAMPLE from ??? | 81
ST002SGUMBCL.P.HEADERSYSTEM | STOC | ST2PLO | 6048672 | H-2 OUTAGE INSPECTION OF STEAM COILS | 64
ST002SGUMBCREHEATERS | STOC | BP12H012B | 6047861 | Installation: Replace Hot Reheat Hanger (HRH) #8 During the H2 Winter Outage 2012 | 20
ST002SGUMBCREHEATERS | STOC | BP12H012B | 6047864 | Removal: Replace Hot Reheat Hanger (HRH) #8 During the H2 Winter Outage 2012 | 20
ST002SGUMBCREHEATERS | STOC | BP12H012B | 6047872 | Installation: Replace Cold Reheat Hangers (CRH) #8, #9, #10, #11, #19 During the H2 Winter Outage 2012 | 100
ST002SGUMBCREHEATERS | STOC | BP12H012B | 6047873 | Removal: Replace Cold Reheat Hangers (CRH) #8, #9, #10, #11, #19 During the H2 Winter Outage 2012 | 100
ST002SGUMBCREHEATERS | STOC | ST2PLO | 6048669 | PM-H-2 OUTAGE PRIMARY REHEATER INSPECT | 144
ST002SGUMBCREHEATERS | STOC | ST2PLO | 6048700 | OUTAGE INSPECTION OF H-2 HIGH TEMP REHEATER | 195.9
ST002SGUMBCSOOTBLOWERSYSTEM | STOC | BP12H015B | 6048604 | Installation: Replace H2 #14 Wall Blower during the H2 Winter outage 2012 | 50
ST002SGUMBCSOOTBLOWERSYSTEM | STOC | BP12H015B | 6048605 | Removal: Replace H2 #14 Wall Blower during the H2 Winter outage 2012 | 30
ST002SGUMBCSOOTBLOWERSYSTEM | STOC | BP12H015B | 6048606 | Installation: Replace H2 #27 Retract Sootblower during the H2 Winter outage 2012 | 138.75
ST002SGUMBCSOOTBLOWERSYSTEM | STOC | BP12H015B | 6048607 | Removal: Replace H2 #27 Retract Sootblower during the H2 Winter outage 2012 | 40
ST002SGUMBCSOOTBLOWERSYSTEM | STOC | ST2PLO | 6048708 | PERFORM OUTAGE SOOT BLOWER INSPECTION FOR HMP&L TWO | 87.2
ST002SGUFDEAIR-GASDUCTS | STOC | BP12H013B | 6052370 | Replace lagging and insulation on the H2 boiler penthouse - northside during the H2 Winter outage of 2012 | 0
ST002SCRDDE-DUCTWORK | STOC | BP12H013B | 6047503 | Gas leak on H2 5th floor above the precips | 0
ST002SGUMBCSUPERHEATERS | STOC | BP12H012B | 6047865 | Installation: Replace Main Steam Hangers (MSH) #3, #4, #6 During the H2 Winter Outage 2012 | 150
ST002SGUMBCSUPERHEATERS | STOC | BP12H012B | 6047871 | Removal: Replace Main Steam Hangers (MSH) #3, #4, #6 During the H2 Winter Outage 2012 | 40
ST002SGUMBCSUPERHEATERS | STOC | ST2PLO | 6048707 | OUTAGE INSPECTION OF H-2 RADIANT SUPERHEATER | 300.9
ST002SGUFDEAIRPREHEATERS | STOC | ST2PLO | 6052378 | Replace H2 "B" APH HE steam cleaning device seal air box during the H2 2012 winter outage. | 40
ST002SGUFDEAIRPREHEATERS | STOC | ST2PLO | 6052379 | Replace H2 "A" APH HE steam cleaning device seal air box during the H2 2012 winter outage. | 40
ST002ASHARSHOPPERBOTASH | STOC | ST2PLO | 6052398 | H-2 winter OUTAGE 2012 REFRACTORY REMOVAL AND REPLACEMENT IN THE BOILER | 0
ST002SGUMBCBOILER | STOC | ST2PLO | 6052400 | INSPECT AND REPAIR GAS LEAKS IN BOILER PENTHOUSE DURING THE H2 2012 WINTER OUTAGE | 90
ST002SGUMBCBOILER | STOC | ST2PLO | 6052402 | H2 2012 WINTER OUTAGE ELEVATOR OPERATOR | 1
ST002SGUMBCBOILER | STOC | ST2PLO | 6052404 | H2 Boiler Gas leak repairs during the 2012 winter outage | 1
ST002SGUMBCBOILER | STOC | ST2PLO | 6052405 | H2 2012 winter outage - CONTRACTOR MOBILIZATION/DEMOB | 160
ST002SGUMBCBOILER | STOC | ST2PLO | 6052406 | H2 2012 winter outage - CONTRACTOR SUPERVISION | 540
ST002SGUMBCBOILER | STOC | ST2PLO | 6052407 | H2 2012 winter outage - CONTRACTOR TOOL ROOM EXPENSES | 360
ST002SCRDDE-DAMPERSSEALAR | STOC | ST2PLO | 6052422 | Replace H2 diverter damper seals on "A" damper | 16
ST002SCRDDE-DAMPERSSEALAR | STOC | ST2PLO | 6052423 | Replace H2 diverter damper seals on "B" damper | 16
ST002SCRDDE-DUCTWORK | STOC | ST2PLO | 6052425 | SCR SAMPLES FROM EACH LAYER | 60
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6052427 | PM-OUTAGE H-2 REMOVE "A" PULVERIZER COOLER FOR | 4
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6052429 | PM-OUTAGE H-2 REMOVE "B" PULVERIZER COOLER FOR | 4
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051680 | H-2 North cooling tower east distribution header "B" cell. Neither of the 2 valves will seal off when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051681 | H-2 north cooling tower "C" cell east distribution valves. Neither of the 2 valves will seal off when closed | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051682 | H-2 north cooling tower "D" cell east distribution deck valves. Neither of the 2 valves will isolate when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051683 | H-2 north cooling tower east distribution header valves "E" cell. Neither of the 2 valves will seal off when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051684 | H-2 north cooling tower east distribution header valves "F" cell. Neither of the 2 valves will seal off when closed | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051687 | H-2 North Cooling tower "A" cell. Neither of the 2 east cell valves will seal off when closed | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051713 | H-2 north cooling tower west distribution header "A" cell. Neither of the 2 valves will seal off when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051715 | H-2 north cooling tower west distribution valve "B" cell. The southwest valve will not seal off when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051717 | H-2 north cooling tower distribution header valves "C" cell. Neither of the 2 valves will seal off when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051724 | H-2 north cooling tower west distribution header valves "D" cell. Neither of the 2 valves will seal off. Northwest valve is stripped and will not move. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051725 | H-2 north cooling tower west distribution header valves "E" cell. Neither of the 2 valves will seal off when closed. | 20
ST002CWSCCSCOOLINGTOWERSYSTEM | STOC | ST2PLO | 6051727 | H-2 north cooling tower distribution header valves "F" cell. neither of the 2 valves will seal off when closed. | 20
ST002SGUMBCVALVES | STOC | ST2PLO | 6049014 | H-2 OUTAGE INSPECTION OF BOILER SAFETY VALVES | 1
ST001SCRDDE-DUCTWORK | RDI1 | BP12H018B | 6051354 | H-2 SCR 24" PRESSURE REDUCING VALVE-REPLACE ACTUATOR | 14
ST001SCRDDE-DUCTWORK | RDI1 | BP12H018B | 6051355 | H-2 SCR 24" PRESSURE REDUCING VALVE-REMOVE ACTUATOR | 3
ST001SCRDDE-DUCTWORK | STOC | BP12H018B | 6051354 | H-2 SCR 24" PRESSURE REDUCING VALVE-REPLACE ACTUATOR | 4
ST001SCRDDE-DUCTWORK | STOC | BP12H018B | 6051355 | H-2 SCR 24" PRESSURE REDUCING VALVE-REMOVE ACTUATOR | 4
ST002BFWFWCATTEMPERATION | RDI1 | ST2PLO | 6051227 | PM-H2 OUTAGE-E&W R.H. SPRAY C/V CHECKS | 4
ST002BFWFWCDASTORAGETANK | RDI1 | ST2PLO | 6051225 | PM-H2 OUTAGE D.A LEVEL SWITCHE TEST OPER | 4
ST002BFWFWCF.W.HEATERS | RDI1 | BP11H023B | 6048797 | H2 Feed Water Heater Level controls provide asstiance for instalation and start-up | 16
ST002BFWFWCF.W.HEATERS | RDI1 | BP11H023B | 6048798 | h2 Feed Water Heater Level controls replacement REMOVAL | 1
ST002BFWFWCF.W.HEATERS | RDI1 | ST2PLO | 6051588 | PM-H-2 OUTAGE-H.P. HEATER LEVEL CONTROL & VALVES CHECK OPERATION | 10
ST002BFWFWCPIPINGTOECONOMIZER | RDI1 | ST2PLO | 6051236 | PM-H2 OUTAGE- F.W. CONTROL VALVE TEST | 1
ST002CDSCSCCONDDRAINTANK | RDI1 | ST2PLO | 6051209 | PM-H-2 Outage L.P. Drain Tank Controls | 2
ST002CDSCSCLOWPRESSUREHEATERS | RDI1 | ST2PLO | 6051234 | PM-H2 OUTAGE L.P.HEATER LEVEL ALARMS | 8
ST002CDSCSCLOWPRESSUREHEATERS | RDI1 | ST2PLO | 6051586 | PM-H-2 OUTAGE-L.P. HEATER LEVEL CONTROL AND VALVES CHECK OPERATION | 20
ST002CWSCCSCONDENSERSYSTEM | RDI1 | ST2PLO | 6051237 | PM-H2 OUTAGE HOTWELL LEVEL SWITCHES TEST | 2
ST002EVSAE-AIREMISSIONS | RDI1 | ST2PLO | 6051190 | PM-H-2 OUTAGE CEM EQUIPMENT CLEAN/CHECK | 8
ST002FGDSSCBOOSTERFANH-2 | RDI1 | ST2PLO | 6051187 | OUTAGE CALIBRATION OF H-2 BOOSTER FAN L.O. SYSTEM DEVICES | 8
ST002PLCBCACCS | RDI1 | ST2PLO | 6051589 | PM-H-2 OUTAGE CLEAN AND INSPECT SECONDARY AIR FLOW ELEMENT AND FURNACE PRESSURE | 3
ST002SGUCLTO-2SYSTEM | RDI1 | ST2PLO | 6051231 | PM-H2 OUTAGE BOILER-02 PROBES CLEAN | 12
ST002SGUCLTO-2SYSTEM | RDI1 | BP12H016B | 6051461 | H-2 OXYGEN PROBE UPGRADES-REMOVE OLD PROBES 2012 | 30
ST002SGUCLTO-2SYSTEM | STOC | BP12H016B | 6051458 | H-2 OXYGEN PROBE UPGRADES-INSTALL NEW PROBES 2012 | 130
ST002SGUCTLMISC.INSTR. | RDI1 | ST2PLO | 6051197 | PM-H-2 OUTAGE START UP INSTRUMENTATION | 20
ST002SGUCTLMISC.INSTR. | RDI1 | ST2PLO | 6051198 | H-2 Outage Inst. Cal. List (Linked Document) | 80
ST002SGUFPECOALFEEDERS | RDI1 | ST2PLO | 6051193 | PM-H-2 OUTAGE B2 COAL FEEDER CHECK & CAL | 4
ST002SGUFPECOALFEEDERS | RDI1 | ST2PLO | 6051200 | PM-H-2 OUTAGE A1 COAL FEEDER CHECK & CAL | 4
ST002SGUFPECOALFEEDERS | RDI1 | ST2PLO | 6051212 | PM-H-2 OUTAGE B1 COAL FEEDER CHECK & CAL | 4
ST002SGUFPEP.A.FANS | RDI1 | ST2PLO | 6051239 | PM-H-2 OUTAGE -"B" COLD AIR CHECK DAMPER | 2
ST002SGUFPEP.A.FANS | RDI1 | ST2PLO | 6051240 | PM-H-2 OUTAGE -"A" COLD AIR CHECK DAMPER | 2
ST002SGUFPEP.A.FANS | RDI1 | ST2PLO | 6051248 | PM-H-2 OUTAGE -"B" PA FAN CHECK DAMPERS | 4
ST002SGUFPEP.A.FANS | RDI1 | ST2PLO | 6051397 | PM-H-2 OUTAGE -"B" HOT AIR CHECK DAMPERS | 2
ST002SGUFPEP.A.FANS | RDI1 | ST2PLO | 6051399 | PM-H-2 OUTAGE -"A" PA FAN CHECK DAMPERS | 4
ST002SGUFPEP.A.FANS | RDI1 | ST2PLO | 6051400 | PM-H-2 OUTAGE -"A" HOT AIR CHECK DAMPERS | 2
ST002SGUFPEPULVERIZERS | RDI1 | ST2PLO | 6048668 | PM-H-2 OUTAGE "A"MILL BYPASS EAST AND WEST DAMPERS | 4
ST002SGUFPEPULVERIZERS | RDI1 | ST2PLO | 6048678 | PM-H-2 OUTAGE MILL TAPS & T/C's CLEAN | 8
ST002SGUFPEPULVERIZERS | RDI1 | ST2PLO | 6051226 | PM-H2 OUTAGE COAL VALVE SOLENOIDS/LIMITS AND COOLING AIR VALVE OPERATION | 5
ST002SGUFPEPULVERIZERS | RDI1 | ST2PLO | 6051251 | PM-H-2 OUTAGE "B"MILL BYPASS EAST AND WEST DAMPERS | 4
ST002SGUMBCBURNERS | RDI1 | ST2PLO | 6048717 | PM-H-2 OUTAGE REMOVE IGNITOR RODS/CLEAN | 2
ST002SGUMBCBURNERS | RDI1 | ST2PLO | 6051585 | PM-H-2 OUTAGE SCANNERS CLEAN AND CHECK | 2
ST002SGUMBCL.P.HEADERSYSTEM | RDI1 | ST2PLO | 6051213 | PM-H-2 OUTAGE-STEAM COIL CONTROL VALVE | 2
ST002SGUMBCL.P.HEADERSYSTEM | RDI1 | ST2PLO | 6051232 | PM-H2 OUTAGE-LOW PRESS HEADER REG CHECK | 2
ST002SGUMBCL.P.HEADERSYSTEM | RDI1 | ST2PLO | 6051235 | PM-H2 OUTAGE-DE-SUPERHEATER CONTROL TEST | 2
ST002SGUMBCSOOTBLOWERSYSTEM | RDI1 | ST2PLO | 6051219 | PM-H2 OUTAGE - SB PRESS REG & VALVE TEST | 3
ST002SGUMBCSTEAMDRUM | RDI1 | ST2PLO | 6051222 | PM-H2 OUTAGE DRUM LEVEL CAMERA/MONITOR CLEAN AND CHECK | 12
ST002SGUMBCVALVES | RDI1 | ST2PLO | 6051229 | PM-H2 OUTAGE ELECTROMATIC RELIEF TEST | 4
ST002SGUPRPPRECIPITATOR | RDI1 | BP11H024B | 6048793 | H2 Precipitator controls replacment provide asstiance for instalation and start-up | 16
ST002TGNMGCHYDROGENSYSTEM | RDI1 | STMTGN | 6043911 | H2 HYDROGEN ALARM PANEL IN BASEMENT, LOW VACUUM SEAL OIL TANK ALARM KEEPS COMING IN, ALL LEVELS ARE IN THEIR NORMAL RANGES | 4
ST002TGNMTCELECTROHYDSYSTEM | RDI1 | ST2PLO | 6051183 | PM-H-2 Outage Turbine Interface Valve | 2
ST002TGNMTCELECTROHYDSYSTEM | RDI1 | ST2PLO | 6051230 | PM-H2Outage Turb EH C/W Control/Valve | 2
ST002TGNMTCGLANDSSTEAM | RDI1 | ST2PLO | 6051233 | PM-H2 Outage Turb Steam/S Valve/Control | 5
ST002TGNMTCL.P.CYLINDER | RDI1 | ST2PLO | 6051224 | PM-H2 Outage Turb E/Hood Spray Valve | 2
ST002TGNMTCLUBEOILSYSTEM | RDI1 | ST2PLO | 6051228 | PM-H2 Outage Turb L.O.C/W Control/Valve | 2
ST002TGNTGCEMER.TRIP.INST. | RDI1 | BP11H025B | 6048122 | Replace Westinghouse OEM trip block with ABB Control Trip Block replacement | 16
ST002TGNTGCTURB.SUPV.INST. | RDI1 | ST2PLO | 6051221 | PM-H2 Outage Turb Rotor Position Check | 10
ST002BFWFWCBOILERFEEDPUMPS | RDM3 | ST2PLO | 6034045 | DRAIN & REFILL OIL SUMPS ON PLANT MOTORS FOR OUTAGE | 4
ST002BFWFWCBOILERFEEDPUMPS | RDM3 | ST2PLO | 6048667 | H-2 OUTAGE INSPEC OF "B" BOILER FEED PUMP COUPLING | 20
ST002BFWFWCBOILERFEEDPUMPS | RDM3 | ST2PLO | 6048704 | H-2 OUTAGE INSPEC OF "A" BOILER FEED PUMP COUPLING | 20
ST002BFWFWCBOILERFEEDPUMPS | RDM3 | ST2PLO | 6051852 | Drain and refill oil sumps on H2 A BFP during the 2012 winter outage | 4
ST002CW-CWSCOOLINGWTRSYS | RDM3 | ST2PLO | 6048720 | PM-H-2 OUTAGE OPEN/CLOSE HEAT EXCHANGER | 120
ST002SGUMBCEASTTEMPPROBE | RDM3 | ST2PLO | 6051220 | PM-H2 OUTAGE EAST FURNACE PROBE INSPECT | 12
ST002TGNMGCHYDROGENSYSTEM | RDM3 | ST2PLO | 6004041 | reg is leaking / See failure remarks:Max | 1
ST002TGNMTCELECTROHYDSYSTEM | RDM3 | ST2PLO | 6048670 | HMP&L TWO ELECTROHYDRAULIC SYSTEM OUTAGE INSPECTION | 8
ST002CWSCCSCONDENSERSYSTEM | RDM3 | ST2PLO | 6052416 | PM-OUTAGE H-2 INSPECT CONDENSER DOORS:Max | 10
ST002BFWFWCBFPSUCTPIPING | RDM3 | ST2PLO | 6052417 | PM-OUTAGE H-2 CLEAN "A" BOILER FEED PUMP SUCTION STRAINERS:Max | 6
ST002BFWFWCBFPSUCTPIPING | RDM3 | ST2PLO | 6052419 | PM-OUTAGE H-2 CLEAN "B" BOILER FEED PUMP SUCTION STRAINERS:Max | 6
ST002CWSCCSCONDENSERSYSTEM | RDM3 | ST2PLO | 6052421 | PM-OUTAGE H-2 CHECK STEAM WASHING OF CONDENSER TUBES:Max | 20
ST002ASHCTRCONTROLS | RDE1 | ST2PLO | 6051179 | PM-H-2 OUTAGE FLYASH CONTROL CLEAN/CHECK | 2
ST002BFWFWCBOILERFEEDPUMPS | RDE1 | ST2PLO | 6051395 | H-2 "A" BOILER FEED PUMP MOTOR-REPLACE WITH SPARE MOTOR | 1
ST002CWSCCSCOOLINGTOWERSYSTEM | RDE1 | ST2PLO | 6051583 | PM-H-2 OUTAGE C.T. TOWER LUBE SYSTEM CHECK | 2
ST002EDTDCSDCDIST.SYSTEM | RDE1 | ST2PLO | 6051188 | PM-H-2 OUTAGE BATT CHARGER CLEAN/CHECK | 8
ST002EDTMCCMTR.CONT.CENTER | RDE1 | STMEDT | 6023774 | On H-2 MCC 2A need to replace a section of the 480V bus. | 8
ST002EDTMCCMTR.CONT.CENTER | RDE1 | ST2PLO | 6051186 | PM-H-2 OUTAGE - SCR 480V MCC CLEAN/TEST | 20
ST002EDTMCCMTR.CONT.CENTER | RDE1 | ST2PLO | 6051192 | PM-H-2 OUTAGE - 480V MCC CLEAN & CHECK | 18
ST002EDTMCCMTR.CONT.CENTER | RDE1 | ST2PLO | 6051203 | PM-H-2 - OUTAGE SCRUBBER 480V MCC CLEAN | 5
ST002EDTMCCMTR.CONT.CENTER | RDE1 | ST2PLO | 6051584 | PM-H-2 OUTAGE COOLING TOWER MCC | 2
ST002EDTTSG4160VSWITCHGEAR | RDE1 | ST2PLO | 6051189 | PM-H-2 OUTAGE CLEAN/CHECK "A"STARTUP T/F PTs | 14
ST002EDTTSG4160VSWITCHGEAR | RDE1 | ST2PLO | 6051195 | PM-H-2 OUTAGE CLEAN/CHECK "B" AUX PT | 14
ST002EDTTSG4160VSWITCHGEAR | RDE1 | ST2PLO | 6051196 | PM-H-2 OUTAGE CLEAN/CHECK "A" AUX PT | 14
ST002EDTTSG4160VSWITCHGEAR | RDE1 | ST2PLO | 6051204 | PM-H-2 OUTAGE CLEAN/CHECK "B"STARTUP T/F PTs | 14
ST002EDTTSG480VBUS | RDE1 | ST2PLO | 6051191 | PM-H-2 OUTAGE SCRUBBER 480V SUB CLEAN | 5
ST002EDTTSG480VBUS | RDE1 | ST2PLO | 6051576 | PM-H-2 OUTAGE CLEAN/INSPECT C.T. 2A PCC 480 VOLT BUS | 20
ST002EDTTSG480VBUS | RDE1 | ST2PLO | 6051577 | PM-H-2 OUTAGE CLEAN/INSPECT 2A PCC 480 VOLT MAIN & TIE BREAKER | 20
ST002EDTTSG480VBUS | RDE1 | ST2PLO | 6051580 | PM-H-2 OUTAGE CLEAN/INSPECT C.T. 2B PCC 480 VOLT BUS | 20
ST002EDTTSG4160VSWITCHGEAR | RDE1 | ST2PLO | 6052754 | 4KV switchgear: Verify phasing diagrams and lable busses in switchgear. Dwgs in EE office. | 6
ST002EDTTSG4160VSWITCHGEAR | RDE1 | ST2PLO | 6052759 | 4KV switchgear: Open switchgear for detail information for replacement project. See T.Taylor for information | 6
ST002EDTTSG480VBUS | RDE1 | ST2PLO | 6051581 | PM-H-2 OUAGE CLEAN/INSPECT 2B PCC 480 VOLT MAIN & TIE BREAKER | 20
ST002EDTTSGSCRUBBERTRANSFMR | RDE1 | ST2PLO | 6051194 | PM-H-2 OUTAGE - SCRUBBER 'B' TRANS CLEAN | 20
ST002EDTTSGSTEPUPTRANSFMR | RDE1 | ST2PLO | 6051214 | PM-H-2 OUTAGE GROUND LEADS ON STEPUP T/F | 10
ST002PASCA-AIRCOMPRESSOR | RDE1 | ST2PLO | 6051185 | PM-H-2 OUTAGE S/OUT "B" AIR COMP MTR | 2
ST002SGUFDEAIRPREHEATERS | RDE1 | ST2PLO | 6051184 | PM-H-2 OUTAGE A/H A&B CONTROLS TEST | 2
ST002SGUFPEP.A.FANS | RDE1 | ST2PLO | 6051199 | PM-H-2 OUTAGE S/OUT "B" P.A. FAN MOTOR | 1
ST002SGUFPEP.A.FANS | RDE1 | ST2PLO | 6051202 | PM-H-2 OUTAGE S/OUT "A" P.A. FAN MOTOR | 1
ST002SGUFPEPULVERIZERS | RDE1 | ST2PLO | 6051180 | PM-H-2 OUTAGE S/OUT "B" PULVERIZER MOTOR | 1
ST002SGUFPEPULVERIZERS | RDE1 | ST2PLO | 6051208 | PM-H-2 OUTAGE S/OUT "A" PULVERIZER MOTOR | 1
ST002SGUMBCBOILER | RDE1 | ST2PLO | 6051437 | PM-H-2 OUTAGE-HOOK UP CONSTRUCTION EQUIPMENT | 60
ST002SGUMBCEASTTEMPPROBE | RDE1 | ST2PLO | 6051278 | PM-H2 OUTAGE EAST FURNACE PROBE INSPECT | 4
ST002SGUMBCSEALAIRSYSTEM | RDE1 | ST2PLO | 6051207 | PM-H-2 OUTAGE S/OUT "B" SEAL AIR FAN MTR | 1
ST002SGUMBCSEALAIRSYSTEM | RDE1 | ST2PLO | 6051210 | PM-H-2 OUTAGE S/OUT "A" SEAL AIR FAN MTR | 1
ST002SGUMBCSOOTBLOWERSYSTEM | RDE1 | ST2PLO | 6051206 | PM-H-2 OUTAGE SB CABINET CLEAN & INSPECT | 2
ST002SGUPRPPRECIPITATOR | RDE1 | BP11H024B | 6048794 | H2 Precipitator controls replacment REMOVAL | 1
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051181 | PM-H-2 OUTAGE PRECIPITATOR HEATERS CHECK | 2
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051308 | PM-H-2 OUTAGE PRECIPITATOR FIELD IINSPECTION | 20
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051312 | PM-H-2 PRECIPITATOR RAPPERS INSPECT | 8
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051313 | PM-H-2 OUTAGE PRECIPITATOR BUSHINGS & SUPPORTS CLEAN AND CHECK | 12
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051315 | PM-H-2 OUTAGE PRECIPITATOR CLEAN UP | 6
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051317 | PM-H-2 OUTAGE PRECIPITATOR DOORS OPEN | 10
ST002SGUPRPPRECIPITATOR | RDE1 | ST2PLO | 6051318 | PM-H-2 OUTAGE PRECIPITATOR T/R SETS CLEAN & INSPECT | 12
ST002TGNMGCEXCITER | RDE1 | ST2PLO | 6051178 | PM-H-2 OUTAGE GEN EXCITER CLEAN & CHECK | 22
ST002TGNMGCEXCITER | RDE1 | ST2PLO | 6051582 | PM-H-2 OUTAGE GEN EXCITER DIODE CHECK | 30
ST002TGNMTCLUBEOILSYSTEM | RDE1 | ST2PLO | 6051320 | PM-H-2 OUTAGE PERFORM EBOP TESTING | 10
ST002TGNMTCTURNINGGEAR | RDE1 | ST2PLO | 6051182 | PM-H-2 OUTAGE T & G TURNING GEAR CHECKS | 1
ST002TGNPM-AREAPMS | RDE1 | ST2PLO | 6051205 | H-2 TURBINE OUTAGE ELECTRICAL WORK | 3
ST002TGNTGCMETER-RELAY | RDE1 | ST2PLO | 6051201 | PM-H-2 OUTAGE GEN CTs and PTs CLEAN & CHECK | 20
ST000FGXMEWMISTELIMNTSYS | STOC | ST2PLO | 6051290 | OUTAGE INSPECTION MIST ELIMINATOR HEADER & NOZZLES | 20
ST002FGDSSCABSORBERTWRH2 | STOC | ST2PLO | 6051216 | PM-H2 OUTAGE INSPECT SCRUBBER SYTEM | 40
ST002FGDSSCABSORBERTWRH2 | STOC | ST2PLO | 6051289 | H-2 OUTAGE INSPECTION OF RECYCLE HEADER & NOZZLES | 16
ST002FGDSSCBOOSTERFANH-2 | RDM2 | ST2PLO | 6051587 | PM-H2 Booster Fan Change Oil on Forced Oil System during the 2012 Winter Outage | 3
ST002FGDSSCBOOSTERFANH-2 | RDM2 | ST2PLO | 6013326 | still has a oil leak and is still leaking:Max | 1
ST002FGDSSCBOOSTERFANH-2 | STOC | ST2PLO | 6048682 | OUTAGE INSPECTION OF SCRUBBER BOOSTER FAN | 142
ST002FGDSSCGASDUCTS | STOC | ST2PLO | 6051244 | H-2 Inspection of the Scrubber Duct Work and Expansion Joints - from the precip outlet to the booster fan during the 2012 Planned Outage on H2 | 8
ST002SGUFDEF.D.FANS | RDM2 | ST2PLO | 6048713 | H-2 OUTAGE INSPECTION OF "A" FORCED DRAFT FAN | 60
ST002SGUFDEF.D.FANS | RDM2 | ST2PLO | 6048714 | H-2 OUTAGE INSPECTION OF "B" FORCED DRAFT FAN | 60
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6048676 | H-2 OUTAGE INSPECTION OF "B-2" COAL FEEDER | 30
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6051923 | H-2 OUTAGE INSPECTION OF "B-1" COAL FEEDER | 30
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6048677 | HMP&L OUTAGE LUBRICATION OF COAL FEEDERS | 2.6
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6048694 | HMP&L OUTAGE LUBRICATION OF COAL FEEDERS | 10
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6048695 | H-2 OUTAGE INSPECTION OF "A-1" COAL FEEDER | 30
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6051922 | H-2 OUTAGE INSPECTION OF "A-2" COAL FEEDER | 30
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6048715 | HMP&L OUTAGE LUBRICATION OF COAL FEEDERS | 2.6
ST002SGUFPECOALFEEDERS | RDM2 | ST2PLO | 6048718 | HMP&L OUTAGE LUBRICATION OF COAL FEEDERS | 2.6
ST002SGUFPECOALFEEDERS | STOC | BP12H010B | 6048634 | Installation: Replace H2 A2 Mill Blast Gate during the H2 winter outage 2012 | 60
ST002SGUFPECOALFEEDERS | STOC | BP12H010B | 6048638 | Installation: Replace H2 B1 Mill Blast Gate during H2 winter outage 2012 | 60
ST002SGUFPECOALFEEDERS | STOC | BP12H010B | 6048637 | Removal: Replace H2 A2 Mill Blast Gate during the H2 winter outage 2012 | 30
ST002SGUFPECOALFEEDERS | STOC | BP12H010B | 6048640 | Removal: Replace H2 B1 Mill Blast Gate during H2 winter outage 2012 | 30
ST002SGUFPEP.A.FANS | RDM2 | ST2PLO | 6051920 | H-2 OUTAGE INSPECTION OF "A" PRIMARY AIR FAN | 40
ST002SGUFPEP.A.FANS | RDM2 | ST2PLO | 6048711 | H-2 OUTAGE INSPECTION OF "B" PRIMARY AIR FAN | 40
ST002SGUFPEPULVERIZERS | RDM2 | ST2PLO | 6048680 | HMP&L PULVERIZER OUTAGE LUB INSPECTION | 30
ST002SGUFPEPULVERIZERS | RDM2 | ST2PLO | 6048697 | HMP&L PULVERIZER OUTAGE LUB INSPECTION | 30
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6048673 | OUTAGE INSPECTION "B" COAL CLASSIFIER | 60
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6048679 | PM-OUTAGE-A PULV. REPAIR INLET AREAS | 55
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6048686 | OUTAGE INSPECT THE VARIABLE ORIFICES | 14.6
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6048687 | OUTAGE INSPECTION "A" COAL CLASSIFIER | 60
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6048698 | PM-OUTAGE-B PULV.REPAIR IMPACT AREAS | 55
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6051403 | PM-H-2 OUTAGE "A"MILL BYPASS EAST AND WEST DAMPERS | 83
ST002SGUFPEPULVERIZERS | STOC | ST2PLO | 6051404 | PM-H-2 OUTAGE "B"MILL BYPASS EAST AND WEST DAMPERS | 83
ST002SGUMBCSEALAIRSYSTEM | RDM2 | ST2PLO | 6048702 | H-2 OUTAGE INSPECTION OF "A" SEAL AIR FAN | 4
ST002SGUMBCSEALAIRSYSTEM | RDM2 | ST2PLO | 6051918 | H-2 OUTAGE INSPECTION OF "B" SEAL AIR FAN | 4
ST002ASHARSBOTASHREMOVAL | STOC | ST2PLO | 6051438 | Ops - clean out wetbottom pit during the H2 2012 Winter Outage | 12
ST002ASHARSHOPPERBOTASH | STOC | ST2PLO | 6051436 | Ops - clean seal trough once deslag is completed during the H2 2012 Winter Outage | 4
ST002ASHFARFLYASHSYSTEM | STOC | ST2PLO | 6051434 | Ops - Vacuum out economizer hoppers on H2 during the 2012 Winter Outage | 24
ST002CW-CWSBEARINGCOOLINGWATER | STOC | ST2PLO | 6051442 | Ops - clean bearing cooling water coolers during the H2 Winter outage of 2012 | 18
ST002CWSCCSCONDENSERSYSTEM | STOC | ST2PLO | 6051596 | Ops - high pressure wash condenser during the H2 Winter Outage 2012 | 60
ST002FGDSSCABSORBERTWRH2 | STOC | ST2PLO | 6051433 | Ops - clean ME panels in H2 FGD during the 2012 H2 Winter Outage | 24
ST002FGDSSCBOOSTERFANH-2 | STOC | ST2PLO | 6051430 | Ops - High Pressure Wash Booster Fan and outlet Duct on H2 During the 2012 Winter Outage | 10
ST002SCRDDE-DUCTWORK | STOC | ST2PLO | 6051440 | Ops - vacuum H2 SCR duct work and catalyst during the 2012 winter outage | 96
ST002SGUFDEAIRPREHEATERS | STOC | ST2PLO | 6051435 | Ops - high pressure wash both Air Heaters on H2 during the 2012 winter outage | 12
ST002SGUFPECOALFEEDERS | STOC | ST2PLO | 6051428 | Ops - Vacuum coal feeders for the H2 Winter Outage 2012 | 6
ST002SGUMBCBOILER | STOC | ST2PLO | 6051238 | PM-H2 OUTAGE VACUUM PENTHOUSE/DEAD AIR | 96
ST002SGUMBCBOILER | STOC | ST2PLO | 6051429 | Ops - Deslagging Boiler for the H2 Winter Outage of 2012 | 20
ST002SGUPRPPRECIPITATOR | STOC | ST2PLO | 6051439 | Ops - high pressure wash H2 precip during the 2012 Winter Outage | 36
ST002TGNMTCELECTROHYDSYSTEM | STOP | ST2PLO | 6051441 | Ops - replace filters on EH system during the H2 2012 winter outage | 2
ST002ASHARSBOTASHREMOVAL | STOC | BP12H009B | 6048216 | Installation of H2 seal Skirt during the H2 Winter Outage of 2012 | 600
ST002ASHARSBOTASHREMOVAL | STOC | ST2PLO | 6048675 | H-2 OUTAGE PM OF EAST HYDROEJECTOR | 94
ST002ASHARSBOTASHREMOVAL | STOC | ST2PLO | 6048719 | H-2 OUTAGE PM OF WEST HYDROEJECTOR | 94
ST002ASHARSBOTASHREMOVAL | STOC | BP12H009B | 6051464 | Removal of H2 seal Skirt during the H2 Winter Outage of 2012 | 600
ST002ASHARSWETBTMPIPING | STOC | ST2PLO | 6048681 | OUTAGE INSPECTION OF REFRACTORY COOLING SYSTEM | 150.6
ST002FGDSSCGASDUCTS | STOC | BP12H008B | 6037629 | Installation:Interior Fabric Seal at FGD Stack/breeching duct connection leaking | 1
ST002FGDSSCGASDUCTS | STOC | BP12H008B | 6050879 | Removal Of H-2 Scrubber Stack Duct Interior Liner | 1
ST002SGUFDEAIR-GASDUCTS | STOC | BP12H008B | 6050872 | Installation of H2 Airheater Gas Inlet Expansion Joints | 1
ST002SGUFPEP.A.FANS | STOC | ST2PLO | 6051305 | Installation: Replace H2 "B" PA Fan Duct work Expansion Joint PA-10 during the H2 Winter Outage 2012 | 32
ST002SGUFPEP.A.FANS | STOC | ST2PLO | 6051306 | Removal: Replace H2 "B" PA Fan Duct work Expansion Joint PA-10 during the H2 Winter Outage 2012 | 32
ST002ASHARSSLAGGRINDERS | STOC | BP12H011B | 6052183 | Replace H2 A Slag Grinder - Installation | 130
ST002ASHARSSLAGGRINDERS | STOC | BP12H011B | 6052190 | Replace H2 A Slag Grinder - Removal | 130
ST002ASHARSSLAGGRINDERS | STOC | BP12H011B | 6052184 | Replace H2 B Slag Grinder - Installation | 130
ST002ASHARSSLAGGRINDERS | STOC | BP12H011B | 6052191 | Replace H2 B Slag Grinder - Removal | 130
ST002SGUMBCL.P.HEADERSYSTEM | STOC | BP12H014B | 6052185 | Replace 2 Steam Coils on B side - Installation | 60
ST002SGUMBCL.P.HEADERSYSTEM | STOC | BP12H014B | 6052189 | Replace 2 Steam Coils on B side - Removal | 60
ST002EDTMCCMTR.CONT.CENTER | STOC | ST2PLO | 6051323 | PM-H-2 OUTAGE SEND OUT THE FOLLOWING MOTORS (see W.O. Hierachy) | 1
ST002EDTTSG480VBUS | STOC | ST2PLO | 6051326 | PM-H-2 OUTAGE - 480V SWITCHGEAR CLEAN & CHECK | 20
ST002EDTTSG480VBUS | STOC | ST2PLO | 6051326 | PM-H-2 OUTAGE - 480V SWITCHGEAR CLEAN & CHECK | 1
ST002EVSAE-AIREMISSIONS | STOC | BP10S003B | 6050995 | H-2 STACK CEM-INSTALL NEW UMBILICAL FOR DILUTION PROBE | 10
ST002EVSAE-AIREMISSIONS | STOC | BP10S003B | 6050996 | H-2 STACK CEM-REMOVE OLD UMBILICAL | 4
ST002EVSAE-AIREMISSIONS | STOC | BP10S003B | 6050995 | H-2 STACK CEM-INSTALL NEW UMBILICAL FOR DILUTION PROBE | 1
ST002EVSAE-AIREMISSIONS | STOC | BP10S003B | 6050996 | H-2 STACK CEM-REMOVE OLD UMBILICAL | 4
ST002SGUCLTO-2SYSTEM | STOC | BP12H016B | 6051458 | H-2 OXYGEN PROBE UPGRADES-INSTALL NEW PROBES 2012 | 40
ST002SGUPRPPRECIPITATOR | STOC | ST2PLO | 6051325 | PM-H-2 OUTAGE PRECIPITATOR FIELD INSPECTION BY OUTSIDE CONTRACTOR | 1