## Consultant Comparison
Page E-1
DEDI PROJECTED RECORD KEEPING AND REPORTING COSTS
PRIMARY FUNCTIONS PERFORMED BY SHELBY ENERGY COOPERATIVE
|  |  | Annual Work Hours | 2080
|  | Pay | Time | Hours | Regular
| ID | Rate | Allocated | Allocated | Salary
Coop Student | 308 | 13 | 50% | 1040 | 13520
Technical Engineer | 702 | 33.93 | 20% | 416 | 14114.88
IT Specialist | 802 | 20.04 | - | 70 | 1402.8
Loss Control Supr | 706 | 37.14 | 10% | 208 | 7725.12
Billing Supervisor | 1002 | 21.88 | - | 70 | 1531.6
Senior Accountant | 801 | 26.79 | 10% | 208 | 5572.32
|  |  |  | 2012 | 43866.72
|  | Overtime |  | Estimated | Overtime
|  | Rate |  | Hours | Salary
Coop Student | 308 | 19.5 |  | 128 | 2496 | 2 hrs wkly - 2 mthly for reports
Technical Engineer | 702 | 50.895 |  | 128 | 6514.56 | 2 hrs wkly - 2 mthly for reports
Loss Control Supr | 706 | 55.71 |  | 104 | 5793.84 | 2 hrs wkly
Senior Accountant | 801 | 40.185 |  | 52 | 2089.62 | 1 hrs wkly
|  |  |  | 412 | 16894.02
Project Consultants
Regular Fee |  |  |  |  | 60000
Sectionalizing & Voltage Plans |  |  |  |  | 30000
90000
TOTAL PROJECTED COOPERATIVE COSTS |  |  |  |  | 150760.74
Page E-2
DEDI PROJECTED RECORD KEEPING REPORTING COSTS
PRIMARY FUNCTIONS PERFORMED BY CONSULTANT
Annual Work Hours |  |  |  | 2080
|  | Pay | Time | Hours | Regular
| ID | Rate | Allocated | Allocated | Salary
Coop Student | 308 | 13 | 20% | 416 | 5408
Technical Engineer | 702 | 33.93 | 10% | 208 | 7057.44
IT Specialist | 802 | 20.04 | - | 70 | 1402.8
Loss Control Supr | 706 | 37.14 | 5% | 104 | 3862.56
Billing Supervisor | 1002 | 21.88 | - | 70 | 1531.6
Senior Accountant | 801 | 26.79 | 5% | 104 | 2786.16
|  |  |  | 972 | 22048.56
|  | Overtime |  | Estimated | Overtime
|  | Rate |  | Hours | Salary
Coop Studendt | 308 | 19.5 |  | 88 | 1716 | 1.25 hrs wkly - 2 mthly for reports
Technical Engineer | 702 | 50.895 |  | 88 | 4478.76 | 1.252 hrs wkly - 2 mthly for reports
Loss Control Supr | 706 | 55.71 |  | 40 | 2228.4 | .75 hrs wkly
Senior Accountant | 801 | 40.185 |  | 26 | 1044.81 | .5 hrs wkly
|  |  |  | 242 | 9467.97
Consultant Charges
Regular Fee |  |  |  |  | 60000
Sectionalizing & Voltage Plans |  |  |  |  | 30000
520 | hours | 82 | Engineering Tech |  | 42640
480 | hours | 105 | Project Consultant |  | 50400
210 | hours | 127 | Senior Engineer |  | 26670
209710
TOTAL PROJECTED CONSULTANT COSTS |  |  |  |  | 241226.53
COST DIFFERENCE FOR COOPERATIVE VS. CONSULTANTS |  |  |  |  | 90465.79
Page E-3
SUMMARY OF ADDITIONAL COSTS
TO PROCEED WITH USGI GRANT PROJECT
ACCELERATED INSTALLATION PHASE OF AMI SYSTEM
| Labor for routine business hours |  |  |  | 68433.22
| Labor for overtime hours |  |  |  | 63049.23
ACCELERATED INSTALLATION PHASE OF CONTROLS
| Contract labor |  |  |  | 43680
RECORD KEEPING AND REPORTING FUNCTIONS
| Consultant labor |  |  |  | 90465.79
265628.24

## AMI
Page D - 1
COMPARISON OF "ACCELERATED" AND "REGULAR" INSTALLATION OF AMI SYSTEM
BASED ON ROUTINE BUSINESS HOURS
(1) | (2) |  | (3) | (4) | (5) | (6) | (7) | (8) | (9)
[8 empty] | Accelerated | Regular
|  |  |  | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | Total Hours | Hours
|  |  | Time | (6): (Holidays excluded)
| ID |  | Allocated
Coop Student | 308 |  | 100% | 176 | 168 | 160 | 168 | 672 | 134.4
Technical Engineer | 702 |  | 75% | 132 | 126 | 120 | 126 | 504 | 126
IT Specialist | 802 |  | 35% | 61.6 | 58.8 | 56 | 58.8 | 235.2 | 58.8
Loss Control Supr | 706 |  | 30% | 52.8 | 50.4 | 48 | 50.4 | 201.6 | 50.4
Billing Supervisor | 1002 |  | 75% | 132 | 126 | 120 | 126 | 504 | 126
Senior Accountant | 801 |  | 30% | 52.8 | 50.4 | 48 | 50.4 | 201.6 | 50.4
Contract Staff |  |  |  | 176 | 168 | 160 | 160 | 664 | 0
|  | Pay Rate |  | (8): 2982.4; (9): 546
|  |  |  | (10) | (11) | (12) | (13) | (14) | (15)
Coop Student | 308 | 13 |  | 2288 | 2184 | 2080 | 2184 | 8736 | 2795.52
Technical Engineer | 702 | 54.288 |  | 7166.016 | 6840.288 | 6514.56 | 6840.288 | 27361.152 | 10944.4608
IT Specialist | 802 | 32.064 |  | 1975.1424 | 1885.3632 | 1795.584 | 1885.3632 | 7541.4528 | 3016.5811
Loss Constrol Supr | 706 | 59.424 |  | 3137.5872 | 2994.9696 | 2852.352 | 2994.9696 | 11979.8784 | 4791.9514
Billing Supervisor | 1002 | 35.008 |  | 4621.056 | 4411.008 | 4200.96 | 4411.008 | 17644.032 | 7057.6128
Senior Accountant | 801 | 42.864 |  | 2263.2192 | 2160.3456 | 2057.472 | 2160.3456 | 8641.3824 | 3456.553
Contract Staff |  | 14 |  | 4928 | 4704 | 4480 | 4480 | 18592 | 0
[8 empty] | (18) | (19)
[5 empty] | Total Regular Wages |  |  | 100495.8976 | 32062.679
(20)
Variance in Regular Labor for "Accelerated Schedule" versus "Regular Schedule" AMI Installation |  |  |  | 2982.4 (14): 68433.2186
Page D - 2
COMPARISON OF "ACCELERATED" AND "REGULAR" INSTALLATION OF AMI SYSTEM
BASED ON OVERTIME HOURS
(1) |  |  | (2) | (3) | (4) | (5) | (6) | (7)
Accelerated
Days to Work |  |  | Avg Days/Hours | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | OT Hours
(Holiday weekends excluded)
Regular Work Days |  |  | 11 days @ 4 hrs | 48 | 48 | 36 | 40 | 172
Saturday |  |  | 4 days @ 8 hrs | 32 | 40 | 24 | 24 | 120
Sunday |  |  | 4 days @ 4 hrs | 16 | 20 | 12 | 12 | 60
|  |  |  | 96 | 108 | 72 | 76 | 352
(9) | (10) |  |  | (11) | (12) | (13) | (14) | (15) | (16)
Regular
Employees |  |  |  | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | Total | Overtime
OT Rate
Coop Student | 308 | 19.5 |  | 1872 | 2106 | 1404 | 1482 | 6864
Technical Engineer | 702 | 50.895 |  | 4885.92 | 5496.66 | 3664.44 | 3868.02 | 17915.04 | 9038.56
IT Specialist | 802 | 30.06 |  | 2885.76 | 3246.48 | 2164.32 | 2284.56 | 10581.12 | 1742.07
Billing Superviosr | 1002 | 32.82 |  | 3150.72 | 3544.56 | 2363.04 | 2494.32 | 11552.64 | 5639.26
Cons Acct Rep | 1306 | 34.395 |  | 3301.92 | 3714.66 | 2476.44 | 2614.02 | 12107.04 | 1784.18
Cons Acct Rep | 1308 | 33.03 |  | 3170.88 | 3567.24 | 2378.16 | 2510.28 | 11626.56 | 1994.58
Senior Accountant | 801 | 40.185 |  | 3857.76 | 4339.98 | 2893.32 | 3054.06 | 14145.12 | 1543.64
[8 empty] | (17) | (18)
[5 empty] | Total Overtime Wages |  |  | 84791.52 | 21742.29
(19)
Variance in Overtime Labor for "Accelerated Schedule" versus "Regular Schedule" AMI Installation |  |  |  | (15): 63049.23
Page D - 3
INSTALL RECLOSER, REGULATOR & CAPACITOR CONTROLS
BASED ON "ACCELERATED" SCHEDULE OF TWO (2) MONTHS
Based on 4-man crew
130
[6 empty] | (1) | (2) | (3) | (4)
[6 empty] | Quantity | Hours | Crew Hrs | Cost
Replace capacitor banks converted from fixed to switched | [5 empty] | 10 | 8 | 320 | 41600
Replace down line voltage reglators bank controls | [5 empty] | 5 | 4 | 80 | 10400
Set Regulator controls tied-in to communications network | [5 empty] | 5 | 4 | 80 | 10400
Replace substation three-phase recloser controls |  |  |  | (13): 14; (14): 4; (16): 0
Replace down line three phase recloser controls | [5 empty] | 6 | 4 | 96 | 12480
Deploy communications for each three-phase recloser | [5 empty] | 6 | 4 | 96 | 12480
(5)
87360
(6)
50% would have been completed during routine business hours |  |  |  | (15): 43680
hours by cooperative labor on the "Regular" installation schedule