## 2011
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2011
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2011
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | IP-1202-5 | North Broadway Main Replacement | Project design and construction was delayed due to the Kentucky Transportation Cabinet. | 3049717.73 | 3136145 | 2007-12-01 | 2009-06-01 | 2008-03-01 | 2011-10-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | IP-1202-17 | South Limestone Replacement | Project design and construction was delayed due to the scheduel and funding of the LFUCG. | 549821.23 | 532854 | 2009-05-01 | 2009-07-01 | 2010-06-01 | 2011-01-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 1820567.53 | 2300000 | -479432.47 | 79.16% | 8.999% | [7 empty] | IP-1202-32 | Lexington Operations Center | Project was used and useful in 2010, a few change orders remained open until Nov. 2011. | 2808875.57 | 2756632 | 2010-03-01 | 2010-12-01 | 2010-05-01 | 2011-11-01
A | MAINS - NEW | 165527.32 | 489000 | -323472.68 | 33.85% | 1.913%
B | MAINS - REPLACED/RESTORED | 1884555.13 | 1005300 | 879255.13 | 187.5% | 3.933% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 6408414.53 | 6425631
C | MAINS - UNSCHEDULED | 272448.69 | 138500 | 133948.69 | 196.7% | 0.5419%
D | MAINS - RELOCATED | 375491.54 | 1050300 | -674808.46 | 35.75% | 4.109%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 148799.15 | 195000 | -46200.85 | 76.31% | 0.763%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 283383.12 | 131500 | 151883.12 | 215.5% | 0.5145%
G | SERVICES AND LATERALS - NEW | 592605.62 | 750000 | -157394.38 | 79.01% | 2.935%
H | SERVICES AND LATERALS - REPLACED | 633636.39 | 267000 | 366636.39 | 237.3% | 1.045%
I | METERS - NEW | 861939.01 | 600000 | 261939.01 | 143.7% | 2.348%
J | METERS - REPLACED | 5403894.63 | 3769751 | 1634143.63 | 143.3% | 14.75%
K | ITS EQUIPMENT AND SYSTEMS | 175355.71 | 155540 | 19815.71 | 112.7% | 0.6086%
L | SCADA EQUIPMENT AND SYSTEMS | 1088481.82 | 200000 | 888481.82 | 544.2% | 0.7825%
M | SECURITY EQUIPMENT AND SYSTEMS | 51694.09 | 20000 | 31694.09 | 258.5% | 0.07825%
N | OFFICES AND OPERATIONS CENTERS | 548021.33 | 80000 | 468021.33 | 685% | 0.313%
O | VEHICLES | 559415.48 | 500000 | 59415.48 | 111.9% | 1.956%
P | TOOLS AND EQUIPMENT | 160725.45 | 160000 | 725.45 | 100.5% | 0.626%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1891192.33 | 1085000 | 806192.33 | 174.3% | 4.245%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 197662.51 | 0 | 197662.51 |  | 0%
S | ENGINEERING STUDIES | 470794.21 | 400000 | 70794.21 | 117.7% | 1.565%
| TOTAL | 17586191.06 | 13296891 | 4289300.06 | 132.3%
| ENTER ITEM DV AND SUBTRACT | 1820567.53 | 2300000 | -479432.47
| TOTAL ITEM A - S | 15765623.53 | 10996891 | 4768732.53 | 143.4%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2011
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
12020204 | Source of Supply Project Dev | 0 |  | 0 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01 | 2010-11-01
12020607 | New WTP On Pool 3 of Kentucky | 713639.1 | 199999.9 | 513639.2 | 356.8% | 0.7825% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
IP-1202-5 | North Broadway Main Replacement | -79129.33 |  | -79129.33 |  | 0% | 3049717.73 | 3136145 | -86427.27 | 2007-12-01 | 2009-06-01 | 2008-03-01 | 2011-10-01
IP-1202-6 | Carrick Pike Main Extension | -129988.6 | 980513 | -1110501.6 | -13.26% | 3.836% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01 | n/a
IP-1202-17 | South Limestone Replacement | -107.77 |  | -107.77 |  | 0% | 549821.23 | 532854 | 16967.23 | 2009-05-01 | 2009-07-01 | 2010-06-01 | 2011-01-01
IP-1202-18 | US 25 Relocation | 415236.31 | 897983 | -482746.69 | 46.24% | 3.514% |  |  | 0 | 2010-02-01 | 2010-10-01 | 2010-09-01
IP-1202-19 | Leestown Road | 666047.27 | 1263746 | -597698.73 | 52.7% | 4.945% |  |  | 0 | 2011-04-01 | 2011-10-01 | 2010-10-01
IP-1202-21 | KRS High Service Pumping | 0 | 660000 | -660000 | 0% | 2.582% |  |  | 0 | 2011-10-01 | 2012-09-01 | n/a | n/a
IP-1202-31 | KRS Raw Water Access | 0 | 1000000 | -1000000 | 0% | 3.913% |  |  | 0 | 2011-08-01 | 2011-12-01 | n/a | n/a
IP-1202-32 | Lexington Operations Center | 138043.15 |  | 138043.15 |  | 0% | 2808875.57 | 2756632 | 52243.57 | 2010-03-01 | 2010-12-01 | 2010-05-01 | 2011-11-01
IP-1202-38 | Russell Cave Road Sys Impr | 447813.89 |  | 447813.89 |  | 0% |  |  | 0 | 2011-10-01 | 2012-07-01 | 2011-10-01
IP-1232-3 | Northern Division Connection | 344375.07 | 4700000 | -4355624.93 | 7.327% | 18.39% |  |  | 0 | 2011-02-01 | n/a | n/a | n/a
IP-1233-1 | Owenton WWTP Phosphorous | 0 | 140000 | -140000 | 0% | 0.5478% |  |  | 0 | 2011-04-01 | 2011-07-01 | n/a | n/a
CS-1201-3 | Business Transformation | 3511543.81 | 2304462 | 1207081.81 | 152.4% | 9.017% |  |  |  | 2010-01-01 | 2014-12-01 | 2010-02-01
CS-1201-4 | Business Transformation Other | 300972.07 |  | 300972.07 |  | 0% |  |  |  | 2011-09-01 | 2014-12-01 | 2011-10-01
| Acquisitions | 0 | 114262.32 | -114262.32 | 0% | 0.4471% |  |  |  | 2011-01-01 | 2011-12-01 | n/a | n/a
IP-1232-1 | Owenton Chemical Bulk Storage/Owenton Post Acquisition Phase 2 | -83705.15 |  | -83705.15 |  | 0% |  |  |  |  | n/a | n/a | n/a
IP-1201-9 | IP Project Unbudgeted Capital | -1090.75 |  | -1090.75 |  | 0% |  |  |  | 2009-01-01 | n/a | n/a | n/a
|  | 6243649.07 | 12260966.22 | -6017317.15 | 50.92%

## 2010
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2010
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2010
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 12020204 | Source of Supply Project Dev | Project was delayed due to the final approval and construction of KRS2. | 2133802 | 2200060 | 2002-04-01 | 2003-12-01 | 2001-06-01 | 2010-11-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 2112707.45 | 3560000 | -1447292.55 | 59.35% | 7.017%
A | MAINS - NEW | 82272.64 | 400000 | -317727.36 | 20.57% | 0.7884%
B | MAINS - REPLACED/RESTORED | 999913.76 | 565000 | 434913.76 | 177% | 1.114% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 2133802 | 2200060
C | MAINS - UNSCHEDULED | 269041.7 | 244400 | 24641.7 | 110.1% | 0.4817%
D | MAINS - RELOCATED | 727692.99 | 950000 | -222307.01 | 76.6% | 1.872%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 107570.94 | 200000 | -92429.06 | 53.79% | 0.3942%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 162530.41 | 175000 | -12469.59 | 92.87% | 0.3449%
G | SERVICES AND LATERALS - NEW | 611401.46 | 874660 | -263258.54 | 69.9% | 1.724%
H | SERVICES AND LATERALS - REPLACED | 294286.13 | 1240975 | -946688.87 | 23.71% | 2.446%
I | METERS - NEW | 436639.89 | 971340 | -534700.11 | 44.95% | 1.914%
J | METERS - REPLACED | 2666026.57 | 1584929 | 1081097.57 | 168.2% | 3.124%
K | ITS EQUIPMENT AND SYSTEMS | 139407.75 | 111090 | 28317.75 | 125.5% | 0.219%
L | SCADA EQUIPMENT AND SYSTEMS | 487125.09 | 103500 | 383625.09 | 470.7% | 0.204%
M | SECURITY EQUIPMENT AND SYSTEMS | 25404.8 | 10000 | 15404.8 | 254% | 0.01971%
N | OFFICES AND OPERATIONS CENTERS | 147296.29 | 80000 | 67296.29 | 184.1% | 0.1577%
O | VEHICLES | 814084.24 | 250000 | 564084.24 | 325.6% | 0.4927%
P | TOOLS AND EQUIPMENT | 129297.22 | 117000 | 12297.22 | 110.5% | 0.2306%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1882344.36 | 750000 | 1132344.36 | 251% | 1.478%
R | CAPITALIZED TANK REHABILIATION/PAINTING | -11627.94 | 0 | -11627.94 | #DIV/0! | 0%
S | ENGINEERING STUDIES | -46.07 | 100000 | -100046.07 | -0.04607% | 0.1971%
| TOTAL | 12083369.68 | 12287894 | -204524.32 | 98.34%
| ENTER ITEM DV AND SUBTRACT | 2112707.45 | 3560000 | -1447292.55
| TOTAL ITEM A - S | 9970662.23 | 8727894 | 1242768.23 | 114.2%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2010
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
12020204 | Source of Supply Project Dev | -2114107.58 | 128360 | -2242467.58 | -1647% | 0.253% | 2133802 | 2200060 | -66258 | 2002-04-01 | 2003-12-01 | 2001-06-01 | 2010-11-01
12020607 | New WTP On Pool 3 of Kentucky | 30789846.79 | 29181785.1 | 1608061.69 | 105.5% | 57.52% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
12020702 | KY Major Highway | -91967.18 | 0 | -91967.18 |  | 0% |  |  | 0 | 2007-01-01 | n/a | n/a | n/a
IP-1202-5 | North Broadway Main Replacement | 1565365.02 | 1151928.69 | 413436.33 | 135.9% | 2.27% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
IP-1202-6 | Carrick Pike Main Extension | 41892.66 | 0 | 41892.66 |  | 0% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01 | n/a
IP-1202-17 | South Limestone Replacement | 549929 | 532854 | 17075 | 103.2% | 1.05% |  |  | 0 | 2009-05-01 | 2009-07-01 | 2010-06-01
IP-1202-18 | US 25 Relocation | 1215244.17 | 3200000 | -1984755.83 | 37.98% | 6.307% |  |  | 0 | 2010-02-01 | 2010-10-01 | 2010-09-01
IP-1202-19 | Leestown Road | 243564.41 | 0 | 243564.41 |  | 0% |  |  | 0 | 2011-04-01 | 2011-10-01 | 2010-10-01
IP-1202-31 | KRS Raw Water Access | 0 | 50000 | -50000 | 0% | 0.09855% |  |  | 0 | 2010-11-01 | 2011-09-01 | n/a | n/a
IP-1202-32 | Lexington Operations Center | 2670832.42 |  | 2670832.42 |  | 0% |  |  | 0 | 2010-03-01 | 2010-12-01 | 2010-05-01
CS-1201-1 | Business Transformation CPS | 984.17 | 0 | 984.17 |  | 0% |  |  | 0 | 2009-01-01 | 2009-12-31 | 2009-01-01
CS-1201-3 | Business Transformation CPS | 1011336.08 | 4036079.01 | -3024742.93 | 25.06% | 7.955% |  |  | 0 | 2010-01-01 | 2014-12-01 | 2010-02-01
IP-1201-10 | Unallocated Eng Clearing | -943.29 |  | -943.29 |  | 0% |  |  | 0 | 2010-01-01 | 2010-12-01 | 2010-01-01 | n/a
12020201 | Leestown Rd Main Improvements | -150954.98 | 0 | -150954.98 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01 | n/a
12020402 | KY Major Highway Relocations | -36976.84 | 0 | -36976.84 |  | 0% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
IP-1201-9 | IP Project Unbudgeted Capital | -989.46 | 0 | -989.46 |  | 0% |  |  | 0 | 2009-01-01 | n/a | n/a | n/a
| Acquisitions | 0 | 168000 | -168000 | 0% | 0.3311% |  |  | 0 | 2010-01-01 | 2010-12-01 | n/a | n/a
|  | 0 | 0 | 0 |  | 0%
|  | 35693055.39 | 38449006.8 | -2755951.41 | 92.83%

## 2009
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2009
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2009
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 05-08 | KENTUCKY RELIABILITY IMPROVEMENT | Construction was shutdown during peak demand. Bids exceeded original estimate and scope was expanded during construction. | 7529869.92 | 6239562 | 2005-12-01 | 2007-07-01 | 2005-12-01 | 2009-07-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 06-02 | YARNALLTON ROAD MAIN EXTENSION | KAW was looking to increase the size of Yarnalltion as a possible secondary feed to the 42-inch tranmission main. After careful consideration it was determined not to be effective. Scope was expanded during construction from original budget. | 442102.82 | 200000 | 2006-03-01 | 2007-09-01 | 2006-08-01 | 2009-01-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 2547150.64 | 4700000 | -2152849.36 | 54.19% | 5.692%
A | MAINS - NEW | 641032.49 | 560000 | 81032.49 | 114.5% | 0.6782%
B | MAINS - REPLACED/RESTORED | 592722.95 | 1005300 | -412577.05 | 58.96% | 1.218% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 7971972.74 | 6439562
C | MAINS - UNSCHEDULED | 198333.89 | 239400 | -41066.11 | 82.85% | 0.2899%
D | MAINS - RELOCATED | 1540243.32 | 1005300 | 534943.32 | 153.2% | 1.218%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 65172.82 | 192000 | -126827.18 | 33.94% | 0.2325%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 182670.67 | 150000 | 32670.67 | 121.8% | 0.1817%
G | SERVICES AND LATERALS - NEW | 1297272.78 | 980000 | 317272.78 | 132.4% | 1.187%
H | SERVICES AND LATERALS - REPLACED | 735602.13 | 1400000 | -664397.87 | 52.54% | 1.696%
I | METERS - NEW | 615748.27 | 1215048 | -599299.73 | 50.68% | 1.472%
J | METERS - REPLACED | 1904051.61 | 2000000 | -95948.39 | 95.2% | 2.422%
K | ITS EQUIPMENT AND SYSTEMS | 117123.33 | 102000 | 15123.33 | 114.8% | 0.1235%
L | SCADA EQUIPMENT AND SYSTEMS | 64074.32 | 90000 | -25925.68 | 71.19% | 0.109%
M | SECURITY EQUIPMENT AND SYSTEMS | 14279.9 | 10000 | 4279.9 | 142.8% | 0.01211%
N | OFFICES AND OPERATIONS CENTERS | 1039331.44 | 560000 | 479331.44 | 185.6% | 0.6782%
O | VEHICLES | 141312.41 | 500000 | -358687.59 | 28.26% | 0.6056%
P | TOOLS AND EQUIPMENT | 51034.7 | 257200 | -206165.3 | 19.84% | 0.3115%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 720747.81 | 800000 | -79252.19 | 90.09% | 0.9689%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 58419.74 | 40000 | 18419.74 | 146% | 0.04844%
S | ENGINEERING STUDIES | 38832.03 | 150000 | -111167.97 | 25.89% | 0.1817%
| TOTAL | 12565157.25 | 15956248 | -3391090.75 | 78.75%
| ENTER ITEM DV AND SUBTRACT | 2547150.64 | 4700000 | -2152849.36
| TOTAL ITEM A - S | 10018006.61 | 11256248 | -1238241.39 | 89%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2009
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 19206.22 | 0 | 19206.22 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 106607.45 | 64200 | 42407.45 | 166.1% | 0.07775% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 267429 | 0 | 267429 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 25968.79 | 49930 | -23961.21 | 52.01% | 0.06047% |  |  | 0 | 2004-01-01 | N/A | n/a | n/a
05-01 | GROUND STORAGE TANK | 0 | 122869.69 | -122869.69 | 0% | 0.1488% |  |  | 0 | 2005-07-01 | 2007-12-01 | n/a | n/a
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 163785.98 | 80000 | 83785.98 | 204.7% | 0.09689% | 7529869.92 | 6239562 | 1290307.92 | 2005-12-01 | 2007-07-01 | 2005-12-01 | 2009-07-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | -1929.18 | 0 | -1929.18 |  | 0% | 442102.82 | 200000 | 242102.82 | 2006-03-01 | 2007-09-01 | 2006-08-01 | 2009-01-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 86106959.74 | 59986790 | 26120169.74 | 143.5% | 72.65% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
12020701 | INCLINE CAR REPLACEMENT AT KRS | 0 | 815288 | -815288 | 0% | 0.9874% |  |  | 0 | 2007-01-01 | 2009-10-01 | 2007-02-01 | 2008-12-01
12020702 | MAJOR HIGHWAY RELOCATIONS 2007 | -23290.19 | 0 | -23290.19 |  | 0% |  |  | 0 | 2007-01-01 | 2007-12-01 | 2007-03-01
1202-5 | NORTH BROADWAY MAIN REPLACEMENT | 1264105.24 | 2470076 | -1205970.76 | 51.18% | 2.992% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
1232-1 | OWENTON CHEMICAL BULK STORAGE | 2185.07 | 29123 | -26937.93 | 7.503% | 0.03527% |  |  | 0 | 2008-04-01 | 2009-01-01 | 2008-04-01
1202-6 | CARRICK ROAD MAIN EXTENSION | 25590.42 | 2637494 | -2611903.58 | 0.9703% | 3.194% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01
CS-1201-1 | BUSINESS TRANSFORMATION | 211055.62 | 356822 | -145766.38 | 59.15% | 0.4322% |  |  | 0 | 2009-01-01 | 2009-12-31 | 2009-01-01
|  | 0 | 0 | 0 |  | 0%
|  | 88167674.16 | 66612592.69 | 21555081.47 | 132.4%

## 2008
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2008
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2008
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | Weather delays and tough laying conditions delayed project. | 2285900.34 | 2150001 | 2004-10-01 | 2007-12-01 | 2004-10-01 | 2008-09-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | Construction was shutdown during peak demand which delayed schedule and increased contractor costs. | 1236263.92 | 994000 | 2005-04-01 | 2006-12-01 | 2005-04-01 | 2008-11-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 4188865.53 | 4000000 | 188865.53 | 104.7% | 7.236% | [7 empty] | 05-06 | SLUDGE HANDLING IMPROVEMENT | Construction was shutdown during peak demand which delayed schedule and increased contractor costs. | 2199181.21 | 1910000 | 2005-04-01 | 2008-12-01 | 2005-04-01 | 2008-10-01
A | MAINS - NEW | 49941.21 | 535000 | -485058.79 | 9.335% | 0.9678% | [7 empty] | 12020701 | INCLINE CAR REPLACEMENT AT KRS | Project was put on hold to conduct a study. Phase one was completed for safety. | 194940.26 | 1150000 | 2007-01-01 | 2009-10-01 | 2007-02-01 | 2008-12-01
B | MAINS - REPLACED/RESTORED | 992301.17 | 1886000 | -893698.83 | 52.61% | 3.412% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 5916285.73 | 6204001
C | MAINS - UNSCHEDULED | 271187.06 | 221937 | 49250.06 | 122.2% | 0.4015%
D | MAINS - RELOCATED | 145362.95 | 0 | 145362.95 |  | 0%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 110740.4 | 427992 | -317251.6 | 25.87% | 0.7742%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 129359.57 | 125000 | 4359.57 | 103.5% | 0.2261%
G | SERVICES AND LATERALS - NEW | 1157819.34 | 855915 | 301904.34 | 135.3% | 1.548%
H | SERVICES AND LATERALS - REPLACED | 1137151.36 | 641603 | 495548.36 | 177.2% | 1.161%
I | METERS - NEW | 656982.99 | 1149930 | -492947.01 | 57.13% | 2.08%
J | METERS - REPLACED | 1656512.75 | 1473399 | 183113.75 | 112.4% | 2.665%
K | ITS EQUIPMENT AND SYSTEMS | 259958.08 | 259750 | 208.08 | 100.1% | 0.4699%
L | SCADA EQUIPMENT AND SYSTEMS | 45277.97 | 51000 | -5722.03 | 88.78% | 0.09226%
M | SECURITY EQUIPMENT AND SYSTEMS | 36285.69 | 10000 | 26285.69 | 362.9% | 0.01809%
N | OFFICES AND OPERATIONS CENTERS | 1800000 | 146300 | 1653700 | 1230% | 0.2647%
O | VEHICLES | 455969.68 | 500000 | -44030.32 | 91.19% | 0.9045%
P | TOOLS AND EQUIPMENT | 224127.59 | 218014 | 6113.59 | 102.8% | 0.3944%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 858215.95 | 820600 | 37615.95 | 104.6% | 1.484%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 97252.28 | 0 | 97252.28 |  | 0%
S | ENGINEERING STUDIES | 105355.43 | 81000 | 24355.43 | 130.1% | 0.1465%
| TOTAL | 14378667 | 13403440 | 975227 | 107.3%
| ENTER ITEM DV AND SUBTRACT | 4188865.53 | 4000000 | 188865.53
| TOTAL ITEM A - S | 10189801.47 | 9403440 | 786361.47 | 108.4%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2008
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 40.4 | 0 | 40.4 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 348733.67 | 64200 | 284533.67 | 543.2% | 0.1161% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | -30.6 | 0 | -30.6 |  | 0% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 337 | 0 | 337 |  | 0% |  |  | 0 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 290942.05 | 2935000 | -2644057.95 | 9.913% | 5.309% |  |  | 0 | 2004-01-01 | N/A | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 316963.01 | 0 | 316963.01 |  | 0% | 2285900.34 | 2150001 | 135899.34 | 2004-10-01 | 2007-12-01 | 2004-10-01 | 2008-09-01
05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | -195.69 | 0 | -195.69 |  | 0% |  |  | 0 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | 96036.5 | 0 | 96036.5 |  | 0% | 1236263.92 | 994000 | 242263.92 | 2005-04-01 | 2006-12-01 | 2005-04-01 | 2008-11-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 172653.36 | 50000 | 122653.36 | 345.3% | 0.09045% | 2199181.21 | 1910000 | 289181.21 | 2005-04-01 | 2008-12-01 | 2005-04-01 | 2008-10-01
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 1359116.86 | 1210964 | 148152.86 | 112.2% | 2.191% |  |  | 0 | 2005-12-01 | 2007-07-01 | 2005-12-01
06-01 | VALVE HOUSE UPGRADES AT KRS | -38141.61 | 0 | -38141.61 |  | 0% |  |  | 0 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | 414412.41 | 0 | 414412.41 |  | 0% |  |  | 0 | 2006-03-01 | 2007-09-01 | 2006-08-01
06-04 | OWEN COUNTY SCADA SYSTEM | 3004.64 | 0 | 3004.64 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-04-01 | 2007-11-01
06-05 | MALLARD POINT PRESSURE | 269.52 | 0 | 269.52 |  | 0% |  |  | 0 | 2006-01-01 | 2006-11-01 | 2006-03-01 | 2007-08-01
06-06 | PARKER'S MILL PUMP & DIESEL | -394.42 | 0 | -394.42 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-03-01 | 2007-10-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 41822904.81 | 33310430 | 8512474.81 | 125.6% | 60.26% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
06-13 | HIGHWAY RELOCATION - CLAYS MILL | 0 | 850000 | -850000 | 0% | 1.538% |  |  | 0 | 2006-01-01 | 2007-04-01 | 2006-07-01 | n/a
12020701 | INCLINE CAR REPLACEMENT AT KRS | 138047.11 | 280709 | -142661.89 | 49.18% | 0.5078% | 194940.26 | 1150000 | -955059.74 | 2007-01-01 | 2009-10-01 | 2007-02-01 | 2008-12-01
12020702 | MAJOR HIGHWAY RELOCATIONS 2007 | -102688.45 | 0 | -102688.45 |  | 0% |  |  | 0 | 2007-01-01 | 2007-12-01 | 2007-03-01
1202-5 | NORTH BROADWAY MAIN REPLACEMENT | 299376.8 | 2350000 | -2050623.2 | 12.74% | 4.251% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
1232-1 | OWENTON CHEMICAL BULK STORAGE | 81520.08 | 824836 | -743315.92 | 9.883% | 1.492% |  |  | 0 | 2008-04-01 | 2009-01-01 | 2008-04-01
1202-6 | CARRICK ROAD MAIN EXTENSION | 62505.52 | 0 | 62505.52 |  | 0% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01
12320507 | CHEMICAL FEED IMPROVEMENTS | -37669.8 | 0 | -37669.8 |  | 0% |  |  | 0 | 2005-12-01 | 2006-11-01 | 2006-06-01 | 2007-09-01
|  | 0 | 0 | 0 |  | 0%
|  | 0 | 0 | 0 |  | 0%
|  | 45227743.17 | 41876139 | 3351604.17 | 108%

## 2007
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2007
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2007
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 05-07 | CHEMICAL FEED IMPROVEMENTS | Project design delayed to accommodate Division of Water requirements. | 488756 | 480000 | 2005-12-01 | 2006-11-01 | 2006-06-01 | 2007-09-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 06-04 | OWEN COUNTY SCADA SYSTEM | Construction bids higher than anticipated. Project delayed for programming. | 610985 | 500000 | 2006-02-01 | 2006-12-01 | 2006-04-01 | 2007-11-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 3137371 | 5999999.5 | -2862628.5 | 52.29% | 21.88% | [7 empty] | 06-05 | MALLARD POINT PRESSURE | Pump manufacturer delayed delivery of booster station. | 332155 | 325000 | 2006-01-01 | 2006-11-01 | 2006-03-01 | 2007-08-01
A | MAINS - NEW | 489878 | 750000 | -260122 | 65.32% | 2.736% | [7 empty] | 06-06 | PARKER'S MILL PUMP & DIESEL | Project scope expanded in preliminary stage, delayed project start. | 806166 | 350000 | 2006-02-01 | 2006-12-01 | 2006-03-01 | 2007-10-01
B | MAINS - REPLACED/RESTORED | 2473473 | 2249999.74 | 223473.26 | 109.9% | 8.207% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 2238062 | 1655000
C | MAINS - UNSCHEDULED | 101183 | 0 | 101183 |  | 0%
D | MAINS - RELOCATED | 16024 | 0 | 16024 |  | 0%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 244947 | 520000 | -275053 | 47.11% | 1.897%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 19096 | 100000 | -80904 | 19.1% | 0.3647%
G | SERVICES AND LATERALS - NEW | 1087103 | 1303700 | -216597 | 83.39% | 4.755%
H | SERVICES AND LATERALS - REPLACED | 1242660 | 1200000 | 42660 | 103.6% | 4.377%
I | METERS - NEW | 1701718 | 1150400 | 551318 | 147.9% | 4.196%
J | METERS - REPLACED | 1330358 | 1150000 | 180358 | 115.7% | 4.195%
K | ITS EQUIPMENT AND SYSTEMS | 253947 | 100000 | 153947 | 253.9% | 0.3647%
L | SCADA EQUIPMENT AND SYSTEMS | 59013 | 0 | 59013 |  | 0%
M | SECURITY EQUIPMENT AND SYSTEMS | 0 | 0 | 0 |  | 0%
N | OFFICES AND OPERATIONS CENTERS | 140932 | 80000 | 60932 | 176.2% | 0.2918%
O | VEHICLES | 576684 | 0 | 576684 |  | 0%
P | TOOLS AND EQUIPMENT | 339773 | 154999.5 | 184773.5 | 219.2% | 0.5653%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1127337 | 650000 | 477337 | 173.4% | 2.371%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 4601 | 0 | 4601 |  | 0%
S | ENGINEERING STUDIES | 61018 | 100000 | -38982 | 61.02% | 0.3647%
| TOTAL | 14407116 | 15509098.74 | -1101982.74 | 92.89%
| ENTER ITEM DV AND SUBTRACT | 3137371 | 5999999.5 | -2862628.5
| TOTAL ITEM A - S | 11269745 | 9509099.24 | 1760645.76 | 118.5%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2007
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 5976 | 0 | 5976 |  | 0% |  |  | 0 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-07 | MAJOR HIGHWAY RELOCATIONS | -215782 | 0 | -215782 |  | 0% |  |  | 0 | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 6402.54 | 0 | 6402.54 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | -97.16 | 0 | -97.16 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 694808 | 0 | 694808 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | -16010.01 | 0 | -16010.01 |  | 0% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 1004584 | 0 | 1004584 |  | 0% |  |  | 0 | 2004-01-01 | N/A | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 1232752 | 440000 | 792752 | 280.2% | 1.605% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | -278.43 | 0 | -278.43 |  | 0% |  |  | 0 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
05-01 | GROUND STORAGE TANK - 3.0 MG (342) | 0 | 0 | 0 |  | 0% |  |  | 0 | 2005-07-01 | 2007-12-01
05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | 68037 | 0 | 68037 |  | 0% |  |  | 0 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | 801015 | 553000 | 248015 | 144.8% | 2.017% |  |  | 0 | 2005-04-01 | 2006-12-01 | 2005-04-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 1544166 | 711000 | 833166 | 217.2% | 2.593% |  |  | 0 | 2005-04-01 | 2008-12-01 | 2005-04-01
05-07 | CHEMICAL FEED IMPROVEMENTS | 211772 | 150000 | 61772 | 141.2% | 0.5471% | 488756 | 480000 | 8756 | 2005-12-01 | 2006-11-01 | 2006-06-01 | 2007-09-01
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 5064222 | 3800000 | 1264222 | 133.3% | 13.86% |  |  | 0 | 2005-12-01 | 2007-07-01 | 2005-12-01
06-01 | VALVE HOUSE UPGRADES AT KRS | 89096 | 0 | 89096 |  | 0% |  |  | 0 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | 6319.59 | 0 | 6319.59 |  | 0% |  |  | 0 | 2006-03-01 | 2007-09-01 | 2006-08-01
06-04 | OWEN COUNTY SCADA SYSTEM | 163461 | 0 | 163461 |  | 0% | 610985 | 500000 | 110985 | 2006-02-01 | 2006-12-01 | 2006-04-01 | 2007-11-01
06-05 | MALLARD POINT PRESSURE | 82191 | 0 | 82191 |  | 0% | 332155 | 325000 | 7155 | 2006-01-01 | 2006-11-01 | 2006-03-01 | 2007-08-01
06-06 | PARKER'S MILL PUMP & DIESEL | 749453 | 659000 | 90453 | 113.7% | 2.404% | 806166 | 350000 | 456166 | 2006-02-01 | 2006-12-01 | 2006-03-01 | 2007-10-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 2992224 | 3917000 | -924776 | 76.39% | 14.29% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
06-13 | HIGHWAY RELOCATION - CLAYS MILL | -48 | 100000 | -100048 | -0.048% | 0.3647% |  |  | 0 | 2006-01-01 | 2007-04-01 | 2006-07-01
12020701 | INCLINE CAR REPLACEMENT AT KRS | 56893 | 250000 | -193107 | 22.76% | 0.9118% |  |  | 0 | 2007-01-01 | 2009-10-01 | 2007-02-01
12020702 | MAJOR HIGHWAY RELOCATIONS 2007 | 1811645 | 1000000 | 811645 | 181.2% | 3.647% |  |  | 0 | 2007-01-01 | 2007-12-01 | 2007-03-01
1202-5 | NORTH BROADWAY MAIN REPLACEMENT | 0 | 50000 |  | 0% | 0.1824% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
| KY NRW | 0 | 100000 |  | 0% | 0.3647% |  |  | 0 | 2007-05-01 | 2007-09-01
| SYSTEM-WIDE ENHANCEMENT | 0 | 177707 | -177707 | 0% | 0.6482% |  |  | 0 | 2007-12-01 | 2011-12-01
|  | 16352801.53 | 11907707 | 4595094.53 | 137.3%

## 2006
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2006
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2006
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 98-01 | INTEGRATED RESOURCE PLAN | Completion delayed on source of supply. | 657269 | 350000 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | Construction bids favorable. | 1309064 | 1800000 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
80 | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 6486689.89 | 4500000 | 1986689.89 | 144.1% | 30.09% | [7 empty] | 05-04 | KRS IMPROVEMENTS | Bids favorable. | 191379 | 350000 | 2005-02-01 | 2005-10-01 | 2005-08-01 | 2006-01-01
81 | NETWORK - REPLACEMENT/RENEWAL | 2126150.99 | 650000 | 1476150.99 | 327.1% | 4.347% | [7 empty] | 06-01 | VALVE HOUSE UPGRADES AT KRS | Bids higher than anticipated. | 462866 | 350000 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
82 | NETWORK - EXTENSION | 651508.55 | 460000 | 191508.55 | 141.6% | 3.076% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 2620578 | 2850000
83 | HYDRANTS - REPLACEMENTS | 176730.09 | 26000 | 150730.09 | 679.7% | 0.1739%
84 | HYDRANTS - NEW | 492568.16 | 506000 | -13431.84 | 97.35% | 3.384%
85 | SERVICES - REPLACEMENT | 868071.04 | 525000 | 343071.04 | 165.3% | 3.511%
86 | SERVICES - NEW | 1326577.69 | 1180100 | 146477.69 | 112.4% | 7.892%
87 | METERS - REPLACEMENT | 1297577.01 | 600000 | 697577.01 | 216.3% | 4.012%
88 | METERS - NEW | 1551511.35 | 1118900 | 432611.35 | 138.7% | 7.483%
89 | ITS EQUIPMENT & SYSTEMS | 146309.88 | 100000 | 46309.88 | 146.3% | 0.6687%
90 | OFFICES AND OPERATIONS CENTERS | 79427.87 | 54000 | 25427.87 | 147.1% | 0.3611%
91 | VEHICLES | 694764.72 | 0 | 694764.72 |  | 0%
92 | TOOLS AND EQUIPMENT | 590832.02 | 150000 | 440832.02 | 393.9% | 1.003%
93 | PROCESS PLANT - REPLACEMENTS | 845296.88 | 225000 | 620296.88 | 375.7% | 1.505%
94 | PROCESS PLANT - ADDITIONS | 196118.18 | 50000 | 146118.18 | 392.2% | 0.3344%
95 | TREATMENT MEDIA REPLACEMENT & PROCESS REHAB (if capitalized) | 7020 | 0 | 7020 |  | 0%
96 | TANK REHABILITATION/PAINTING (if capitalized) | 0 | 0 | 0 |  | 0%
97 | COMPREHENSIVE PLANNING STUDIES (if capitalized) | 65926 | 300000 | -234074 | 21.98% | 2.006%
| TOTAL | 17603080.32 | 10445000 | 7158080.32 | 168.5%
| ENTER ITEM 80 AND SUBTRACT | 6486689.89 | 4500000 | 1986689.89
| TOTAL ITEM 81 - 97 | 11116390.43 | 5945000 | 5171390.43 | 187%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2006
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-02 | GROUND STORAGE TANK - 3.0 MG | -731.77 | 0 | -731.77 |  | 0% |  |  | 0 | 2001-03-01 | 2003-12-01 | 2001-02-01 | 2004-08-01
01-03 | SCADA IMPROVEMENTS | 9468.33 | 0 | 9468.33 |  | 0% |  |  | 0 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 209887.82 | 0 | 209887.82 |  | 0% |  |  | 0 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-07 | MAJOR HIGHWAY RELOCATIONS | 215782 | 0 | 215782 |  | 0% |  |  | 0 | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 9770.67 | 0 | 9770.67 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 219992.39 | 0 | 219992.39 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 436623.84 | 180000 | 256623.84 | 242.6% | 1.204% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | 270296.5 | 0 | 270296.5 |  | 0% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 30.76 | 0 | 30.76 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 20805.37 | 0 | 20805.37 |  | 0% |  |  | 0 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 478850.85 | 530000 | -51149.15 | 90.35% | 3.544% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 543523.25 | 170000 | 373523.25 | 319.7% | 1.137% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | -208706.93 | 700000 | -908706.93 | -29.82% | 4.681% | 632906 | 1190593 | -557687 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
05-01 | GROUND STORAGE TANK - 3.0 MG (342) | 0 | 750000 | -750000 | 0% | 5.016% |  |  | 0 | 2005-07-01 | 2007-12-01
05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | 799571.91 | 800000 | -428.09 | 99.95% | 5.35% | 1309064 | 1800000 | -490936 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-04 | KRS IMPROVEMENTS | -8512.91 | 0 | -8512.91 |  | 0% | 191379 | 350000 | -158621 | 2005-02-01 | 2005-10-01 | 2005-08-01 | 2006-01-01
05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | 339611.53 | 725000 | -385388.47 | 46.84% | 4.848% |  |  | 0 | 2005-04-01 | 2006-12-01 | 2005-04-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 314092.75 | 0 | 314092.75 |  | 0% |  |  | 0 | 2005-04-01 | 2008-12-01 | 2005-04-01
05-07 | CHEMICAL FEED IMPROVEMENTS | 276984 | 228460 | 48524 | 121.2% | 1.528% |  |  | 0 | 2005-12-01 | 2006-11-01 | 2006-06-01
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 944837.33 | 25000 | 919837.33 | 3779% | 0.1672% |  |  | 0 | 2005-12-01 | 2007-07-01 | 2005-12-01
06-01 | VALVE HOUSE UPGRADES AT KRS | 380264.17 | 350000 | 30264.17 | 108.6% | 2.341% | 462866 | 350000 | 112866 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | 23300 | 50000 | -26700 | 46.6% | 0.3344% |  |  | 0 | 2006-03-01 | 2007-09-01 | 2006-08-01
06-04 | OWEN COUNTY SCADA SYSTEM | 447523.83 | 0 | 447523.83 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-04-01
06-05 | MALLARD POINT PRESSURE | 249694.67 | 0 | 249694.67 |  | 0% |  |  | 0 | 2006-01-01 | 2006-11-01 | 2006-03-01
06-06 | PARKER'S MILL PUMP & DIESEL | 57400 | 0 | 57400 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-03-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 1676933.11 | 0 | 1676933.11 |  | 0% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
06-13 | HIGHWAY RELOCATION - CLAYS MILL | 47.71 | 0 | 47.71 |  | 0% |  |  | 0 | 2006-01-01 | 2007-04-01 | 2006-07-01
92-12 | BLUEGRASS WATER PROJECT | 37268.77 | 0 | 37268.77 |  | 0% |  |  | 0 | 1992-07-01 | 1996-12-01 | 1992-09-01
98-01 | INTEGRATED RESOURCE PLAN | 15839.97 | 0 | 15839.97 |  | 0% | 657269 | 350000 | 307269 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
|  | 7760449.92 | 4508460 | 3251989.92 | 172.1%

## 2005
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2005
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2005
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | Property acquisition longer than anticipated. | 1755786 | 1300000 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 03-01 | ELEVATED STORAGE TANK - 2.0 MG | On schedule, construction costs higher than anticipated. | 3744744 | 3000000 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
80 | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 6000465.36 | 4080000 | 1920465.36 | 147.1% | 23.71% | [7 empty] | 03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | Equipment delivery delayed on switchgear. | 999181 | 1320000 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
81 | NETWORK - REPLACEMENT/RENEWAL | 489069.49 | 600000 | -110930.51 | 81.51% | 3.486% | [7 empty] | 01-03 | SCADA IMPROVEMENTS | Delay in completing programming. | 675097 | 650000 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
82 | NETWORK - EXTENSION | 676942.06 | 255000 | 421942.06 | 265.5% | 1.482% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 7174808 | 6270000
83 | HYDRANTS - REPLACEMENTS | 23369.65 | 25500 | -2130.35 | 91.65% | 0.1482%
84 | HYDRANTS - NEW | 547823.42 | 300000 | 247823.42 | 182.6% | 1.743%
85 | SERVICES - REPLACEMENT | 738960.46 | 500000 | 238960.46 | 147.8% | 2.905%
86 | SERVICES - NEW | 1281489.73 | 1157000 | 124489.73 | 110.8% | 6.723%
87 | METERS - REPLACEMENT | 485925.15 | 416800 | 69125.15 | 116.6% | 2.422%
88 | METERS - NEW | 1064680.58 | 1121500 | -56819.42 | 94.93% | 6.517%
89 | ITS EQUIPMENT & SYSTEMS | 81510.92 | 75500 | 6010.92 | 108% | 0.4387%
90 | OFFICES AND OPERATIONS CENTERS | 93531.1 | 55000 | 38531.1 | 170.1% | 0.3196%
91 | VEHICLES | 6532.95 | 0 | 6532.95 |  | 0%
92 | TOOLS AND EQUIPMENT | 202115.7 | 160000 | 42115.7 | 126.3% | 0.9297%
93 | PROCESS PLANT - REPLACEMENTS | 441262.88 | 350000 | 91262.88 | 126.1% | 2.034%
94 | PROCESS PLANT - ADDITIONS | 10170.33 | 50000 | -39829.67 | 20.34% | 0.2905%
95 | TREATMENT MEDIA REPLACEMENT & PROCESS REHAB (if capitalized) | 167211.77 | 0 | 167211.77 |  | 0%
96 | TANK REHABILITATION/PAINTING (if capitalized) | 0 | 0 | 0 |  | 0%
97 | COMPREHENSIVE PLANNING STUDIES (if capitalized) | 0 | 0 | 0 |  | 0%
| TOTAL | 12311061.55 | 9146300 | 3164761.55 | 134.6%
| ENTER ITEM 80 AND SUBTRACT | 6000465.36 | 4080000 | 1920465.36
| TOTAL ITEM 81 - 97 | 6310596.19 | 5066300 | 1244296.19 | 124.6%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2005
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-02 | GROUND STORAGE TANK - 3.0 MG | 11297.5 | 0 | 11297.5 |  | 0% |  |  | 0 | 2001-03-01 | 2003-12-01 | 2001-02-01 | 2004-08-01
01-03 | SCADA IMPROVEMENTS | 7866.43 | 0 | 7866.43 |  | 0% | 675097 | 650000 | 25097 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 928000.47 | 766600 | 161400.47 | 121.1% | 4.454% | 1755786 | 1300000 | 455786 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-11 | NEW COLUMBUS PROJECT | 22612.72 | 0 | 22612.72 |  | 0% |  |  | 0 | 2001-10-01 | 2003-05-01 | 2002-02-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 9467.02 | 0 | 9467.02 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 446.31 | 0 | 446.31 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-03 | REPLACE TRAVELLING SCREEN & HOUSING | 11979.81 | 0 | 11979.81 |  | 0% |  |  | 0 | 2002-08-01 | 2003-04-01 | 2003-12-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 136001.48 | 1500000 | -1363998.52 | 9.067% | 8.716% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | 3032909.37 | 2180000 | 852909.37 | 139.1% | 12.67% | 3744744 | 3000000 | 744744 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 17816.69 | 0 | 17816.69 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 257105.57 | 219800 | 37305.57 | 117% | 1.277% | 999181 | 1320000 | -320819 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS | 1271759.76 | 910000 | 361759.76 | 139.8% | 5.288% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 214796.9 | 240000 | -25203.1 | 89.5% | 1.395% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | 0 | 1322035 | -1322035 | 0% | 7.682% |  |  | 0 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
04-06 | REPLACE FILTER MEDIA 3 & 4 | 1294.28 | 0 | 1294.28 |  | 0% |  |  | 0 | 2005-03-01 | 2005-07-01 | 2004-09-01 | 2004-12-01
05-01 | GROUND STORAGE TANK - 3.0 MG (342) | 0 | 75000 | -75000 | 0% | 0.4358% |  |  | 0 | 2005-07-01 | 2007-12-01
05-02 | RUSSELL CAVE ROAD MAIN | 392914.33 | 500000 | -107085.67 | 78.58% | 2.905% |  |  | 0 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-04 | KRS VALVE MECHANICAL IMPROVEMENT | 199892.31 | 350000 | -150107.69 | 57.11% | 2.034% |  |  | 0 | 2005-02-01 | 2005-10-01 | 2005-08-01 | 2006-01-01
05-05 | REPLACE TRAC-VAC SYSTEM | 340.85 | 0 | 340.85 |  | 0% |  |  | 0 | 2005-04-01 | 2006-12-01 | 2005-04-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 12041.25 | 0 | 12041.25 |  | 0% |  |  | 0 | 2005-04-01 | 2008-12-01 | 2005-04-01
92-12 | BLUEGRASS WATER PROJECT | 6754.25 | 0 | 6754.25 |  | 0% |  |  | 0 | 1992-07-01 | 1996-12-01 | 1992-09-01
96-19 | CUSTOMER SERVICE SOFTWARE | 55.57 | 0 | 55.57 |  | 0% |  |  | 0 | 1996-12-01 | 1999-06-01 | 1996-11-01 | 2003-12-01
98-01 | INTEGRATED RESOURCE PLAN | 31183.95 | 0 | 31183.95 |  | 0% |  |  | 0 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
98-08 | SURGE PROTECTION KRS | 1754.19 | 0 | 1754.19 |  | 0% |  |  | 0 | 1998-04-01 | 1999-11-01 | 1998-08-01
|  | 6568291.01 | 8063435 | -1495143.99 | 81.46%

## 2004
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2004
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2004
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 01-02 | GROUND STORAGE TANK - 3.0 MG | Engineer's estimate was increased after design. Construction was delayed by change in project manager. | 1601091 | 1500000 | 2001-03-01 | 2003-12-01 | 2001-02-01 | 2004-08-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 01-11 | NEW COLUMBUS PROJECT | Project scope was expanded. | 2132257 | 1800000 | 2001-10-01 | 2003-05-01 | 2002-02-01 | 2004-12-01
80 | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 4003165.9 | 4000000 | 3165.9 | 100.1% | 25.64% | [7 empty] | 02-03 | REPLACE TRAVELLING SCREEN & HOUSING | Bid exceeded estimate cost by $220,000. Project scope was expanded by $100,000 to include replacing trash rake which was scheduled for following year. | 773246 | 450000 | 2002-08-01 | 2003-04-01 | 2003-12-01 | 2004-12-01
81 | NETWORK - REPLACEMENT/RENEWAL | 886357.05 | 525000 | 361357.05 | 168.8% | 3.366% | [7 empty] | 04-06 | REPLACE FILTER MEDIA 3 & 4 | Project was moved forward due to filter media deterioration. Project scope was expanded to include repair to filter bottom. | 275760 | 250000 | 2005-03-01 | 2005-07-01 | 2004-09-01 | 2004-12-01
82 | NETWORK - EXTENSION | 460200.21 | 250000 | 210200.21 | 184.1% | 1.603% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 4782354 | 4000000
83 | HYDRANTS - REPLACEMENTS | 25782.27 | 25000 | 782.27 | 103.1% | 0.1603%
84 | HYDRANTS - NEW | 394983.69 | 260000 | 134983.69 | 151.9% | 1.667%
85 | SERVICES - REPLACEMENT | 612491.95 | 465650 | 146841.95 | 131.5% | 2.985%
86 | SERVICES - NEW | 1154016.14 | 1134350 | 19666.14 | 101.7% | 7.272%
87 | METERS - REPLACEMENT | 175758.21 | 800800 | -625041.79 | 21.95% | 5.134%
88 | METERS - NEW | 1720106.87 | 707350 | 1012756.87 | 243.2% | 4.535%
89 | ITS EQUIPMENT & SYSTEMS | 107436.3 | 75000 | 32436.3 | 143.2% | 0.4808%
90 | OFFICES AND OPERATIONS CENTERS | 23159.28 | 50000 | -26840.72 | 46.32% | 0.3205%
91 | VEHICLES | 235327.34 | 125000 | 110327.34 | 188.3% | 0.8013%
92 | TOOLS AND EQUIPMENT | 19084.64 | 76400 | -57315.36 | 24.98% | 0.4898%
93 | PROCESS PLANT - REPLACEMENTS | 142457.47 | 179250 | -36792.53 | 79.47% | 1.149%
94 | PROCESS PLANT - ADDITIONS | 22714.8 | 20000 | 2714.8 | 113.6% | 0.1282%
95 | TREATMENT MEDIA REPLACEMENT & PROCESS REHAB (if capitalized) | 187528.25 | 0 | 187528.25 |  | 0%
96 | TANK REHABILITATION/PAINTING (if capitalized) | 0 | 0 | 0 |  | 0%
97 | COMPREHENSIVE PLANNING STUDIES (if capitalized) | 0 | 0 | 0 |  | 0%
| TOTAL | 10170570.37 | 8693800 | 1476770.37 | 117%
| ENTER ITEM 80 AND SUBTRACT | 4003165.9 | 4000000 | 3165.9
| TOTAL ITEM 81 - 97 | 6167404.47 | 4693800 | 1473604.47 | 131.4%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2004
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-01 | LEX - SECURITY SYSTEM IMPROVEMENT | 20997.88 | 0 | 20997.88 |  | 0% |  |  | 0 | 2001-01-01 | 2001-12-01 | 2001-04-01 | 2001-12-01
01-02 | GROUND STORAGE TANK - 3.0 MG | 756645.82 | 666850 | 89795.82 | 113.5% | 4.275% | 1601091 | 1500000 | 101091 | 2001-03-01 | 2003-12-01 | 2001-02-01 | 2004-08-01
01-03 | SCADA IMPROVEMENTS | 80165.8 | 70000 | 10165.8 | 114.5% | 0.4487% |  |  | 0 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
01-04 | SCOTT COUNTY MAINS | 1545.88 | 0 | 1545.88 |  | 0% |  |  | 0 | 2001-01-01 | 2002-12-01 | 2001-01-01 | 2003-10-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 514517.92 | 950000 | -435482.08 | 54.16% | 6.09% |  |  | 0 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-10 | RRS HYDRAULIC IMPROVEMENTS | 6214.53 | 0 | 6214.53 |  | 0% |  |  | 0 | 2001-03-01 | 2002-09-01 | 2001-08-01 | 2003-06-01
01-11 | NEW COLUMBUS PROJECT | 98864.58 | 150000 | -51135.42 | 65.91% | 0.9616% | 2132257 | 1800000 | 332257 | 2001-10-01 | 2003-05-01 | 2002-02-01 | 2004-12-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 9248.8 | 616000 | -606751.2 | 1.501% | 3.949% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 412.38 | 0 | 412.38 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-03 | REPLACE TRAVELLING SCREEN & HOUSING | 761059.67 | 450000 | 311059.67 | 169.1% | 2.885% | 773246 | 450000 | 323246 | 2002-08-01 | 2003-04-01 | 2003-12-01 | 2004-12-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 0 | 241730 | -241730 | 0% | 1.55% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | 480216.23 | 1100000 | -619783.77 | 43.66% | 7.052% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 130942.64 | 0 | 130942.64 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 725151.48 | 1010000 | -284848.52 | 71.8% | 6.475% |  |  | 0 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS | 567181.38 | 400000 | 167181.38 | 141.8% | 2.564% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS | 0 | 60000 | -60000 | 0% | 0.3846% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | 0 | 1190593 | -1190593 | 0% | 7.633% |  |  | 0 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
04-06 | REPLACE FILTER MEDIA 3 & 4 | 274466.03 | 0 | 274466.03 |  | 0% | 275760 | 250000 | 25760 | 2005-03-01 | 2005-07-01 | 2004-09-01 | 2004-12-01
92-12 | BLUEGRASS WATER PROJECT | 49109.11 | 0 | 49109.11 |  | 0% |  |  | 0 | 1992-07-01 | 1996-12-01 | 1992-09-01
96-19 | CUSTOMER SERVICE SOFTWARE | 45257.03 | 0 | 45257.03 |  | 0% |  |  | 0 | 1996-12-01 | 1999-06-01 | 1996-11-01 | 2003-12-01
98-01 | INTEGRATED RESOURCE PLAN | 30465 | 0 | 30465 |  | 0% |  |  | 0 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
98-08 | SURGE PROTECTION KRS | 1862.4 | 0 | 1862.4 |  | 0% |  |  | 0 | 1998-04-01 | 1999-11-01 | 1998-08-01
|  | 4554324.56 | 6905173 | -2350848.44 | 65.96%

## 2003
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2003
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2003
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 96-19 | CUSTOMER SERVICE SOFTWARD | Project scope expanded to include national Call Center | 3403518 | 352200 | 1996-12-01 | 1999-06-01 | 1996-11-01 | 2003-12-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 01-04 | SCOTT COUNTY MAINS | Project scope expanded to complete Scott County service | 2356593 | 1500000 | 2001-01-01 | 2002-12-01 | 2001-01-01 | 2003-10-01
A | MAINS & HYDRANTS, DEPOSIT AGREEMENTS | 3711271 | 4250000 | -538729 | 87.32% | 32.38% | [7 empty] | 01-10 | RRS HYDRAULIC IMPROVEMENTS | Project delayed by DOW approval, completed as proposed | 1651323 | 1600000 | 2001-03-01 | 2002-09-01 | 2001-08-01 | 2003-06-01
B | MAINS & HYDRANTS, NEW & REPLACEMENT | 1388765 | 975000 | 413765 | 142.4% | 7.429% | [7 empty] | 03-02 | 2003 MAJOR HIGHWAY RELOCATIONS | Project scope reduced by KYDOT | 503390 | 700000 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
C | SERVICES | 2040517 | 1425000 | 615517 | 143.2% | 10.86% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 7914824 | 4152200
D | METERS & INSTALLATIONS | 1739016 | 1500000 | 239016 | 115.9% | 11.43%
E | OFFICE FURNITURE & EQUIPMENT | 96018 | 25000 | 71018 | 384.1% | 0.1905%
F | TRANSPORTATION EQUIPMENT | 22425 | 0 | 22425 |  | 0%
G | GENERAL EQUIPMENT | 253694 | 357750 | -104056 | 70.91% | 2.726%
H | MISCELLANEOUS | 390393 | 163400 | 226993 | 238.9% | 1.245%
| TOTAL | 9642099 | 8696150 | 945949 | 110.9%
| ENTER ITEM A AND SUBTRACT | 3711271 | 4250000 | -538729
| TOTAL ITEM B - H | 5930828 | 4446150 | 1484678 | 133.4%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2003
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
92-12 | BLUEGRASS WATER PROJECT | 61504 | 0 | 61504 |  | 0% |  |  |  | 1992-07-01 | 1996-12-01 | 1992-09-01
96-19 | CUSTOMER SERVICE SOFTWARE | 720918 | 0 | 720918 |  | 0% | 3403518 | 352200 | 3051318 | 1996-12-01 | 1999-06-01 | 1996-11-01 | 2003-12-01
98-01 | INTEGRATED RESOURCE PLAN | 56613 | 0 | 56613 |  | 0% |  |  |  | 1998-02-01 | 1999-09-01 | 1999-02-01
98-08 | SURGE PROTECTION KRS | 1693 | 0 | 1693 |  | 0% |  |  |  | 1998-04-01 | 1999-11-01 | 1998-08-01
98-09 | UPGRADE CART WINCH KRS | 140 | 0 | 140 |  | 0% |  |  |  | 1998-02-01 | 1998-11-01 | 1998-08-01
01-02 | GROUND STORAGE TANK - 3.0 MG | 774799 | 500000 | 274799 | 155% | 3.81% |  |  |  | 2001-03-01 | 2003-12-01 | 2001-02-01
01-03 | SCADA IMPROVEMENTS | 352624 | 500000 | -147376 | 70.52% | 3.81% |  |  |  | 2001-01-01 | 2003-05-01 | 2002-09-01
01-04 | SCOTT COUNTY MAINS | 487100 | 600000 | -112900 | 81.18% | 4.572% | 2356593 | 1500000 | 856593 | 2001-01-01 | 2002-12-01 | 2001-01-01 | 2003-10-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 37380 | 150000 | -112620 | 24.92% | 1.143% |  |  |  | 2001-01-01 | 2004-12-01 | 2001-02-01
01-07 | MAJOR HIGHWAY RELOCATIONS | -5551 | 0 | -5551 |  | 0% |  |  |  | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
01-10 | RRS HYDRAULIC IMPROVEMENTS | 504665 | 450000 | 54665 | 112.1% | 3.429% | 1651323 | 1600000 | 51323 | 2001-03-01 | 2002-09-01 | 2001-08-01 | 2003-06-01
01-11 | NEW COLUMBUS PROJECT | 1387929 | 770000 | 617929 | 180.3% | 5.867% |  |  |  | 2001-10-01 | 2003-05-01 | 2002-02-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 31644 | 0 | 31644 |  | 0% |  |  |  | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 182535 | 0 | 182535 |  | 0% |  |  |  | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-03 | REPLACE TRAVELLING SCREEN & HOUSING | 207 | 0 | 207 |  | 0% |  |  |  | 2002-08-01 | 2003-04-01 | 2003-12-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 0 | 207300 | -207300 | 0% | 1.58% |  |  |  | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | 0 | 150000 | -150000 | 0% | 1.143% |  |  |  | 2003-05-01 | 2005-12-01 | 2003-07-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 503390 | 700000 | -196610 | 71.91% | 5.334% | 503390 | 700000 | -196610 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 7229 | 400000 | -392771 | 1.807% | 3.048% |  |  |  | 2003-01-01 | 2004-07-01 | 2003-06-01
|  |  | 0 | 0 |  | 0%
|  | 5104819 | 4427300 | 677519 | 115.3%

## 2002
Kentucky American Water
Case No. 2012-00520 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2002
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2002
Lance Williams
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 00-02 | PARIS PIKE RELOCATION - DESIGN | Project completed as proposed - easement work delayed completion | 65990 | 50000 | 2000-03-01 | 2000-12-01 | 2000-03-01 | 2002-10-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 00-03 | HARRODSBURG ROAD RELOCATION - DESIGN | Project delayed by KYDOT | 69803 | 100000 | 2000-02-01 | 2000-09-01 | 11/200 | 2002-12-01
A | MAINS & HYDRANTS, DEPOSIT AGREEMENTS | 2758068 | 4250000 | -1491932 | 64.9% | 25.55% | [7 empty] | 00-04 | RICHMOND ROAD RELOCATION - DESIGN | Project scope expanded by KYDOT | 121461 | 94000 | 2000-03-01 | 2000-11-01 | 3/200 | 2002-11-01
B | MAINS & HYDRANTS, NEW & REPLACEMENT | 793184 | 1152600 | -359416 | 68.82% | 6.929% | [7 empty] | 01-06 | KRS SLUICE GATES | Project completed as proposed | 248960 | 250000 | 2001-08-01 | 2002-05-01 | 2001-08-01 | 2002-05-01
C | SERVICES | 1634330 | 1123200 | 511130 | 145.5% | 6.753% | [7 empty] | 01-07 | 2001 MAJOR HIGHWAY RELOCATIONS | Project exceeded scope due to KYDOT | 1221929 | 1050000 | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
D | METERS & INSTALLATIONS | 1351800 | 1281700 | 70100 | 105.5% | 7.706% | [7 empty] | 01-08 | ACQUISITION OF TRI-VILLAGE/ELK LAKE WATER | Project completed as proposed | 1849283 | 1860000 | 2000-08-01 | 2000-08-01 | 2001-07-01 | 2002-12-01
E | OFFICE FURNITURE & EQUIPMENT | 114535 | 305900 | -191365 | 37.44% | 1.839% | [7 empty] | 02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | Project scope expanded by KYDOT | 3369864 | 2000000 | 2000-08-01 | 2000-08-01 | 2002-01-01 | 2002-11-01
F | TRANSPORTATION EQUIPMENT | 143962 | 145000 | -1038 | 99.28% | 0.8717% | [8 empty] | GRAND TOTAL COMPLETED IP'S |  | 6947290 | 5404000
G | GENERAL EQUIPMENT | 96772 | 256700 | -159928 | 37.7% | 1.543%
H | MISCELLANEOUS | 276445 | 370700 | -94255 | 74.57% | 2.229%
| TOTAL | 7169096 | 8885800 | -1716704 | 80.68%
| ENTER ITEM A AND SUBTRACT | 2758068 | 4250000 | -1491932
| TOTAL ITEM B - H | 4411028 | 4635800 | -224772 | 95.15%
Kentucky American Water
Case No. 2012-00520
Construction Projects
|  |  | As of | 2002
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Lance Williams
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
| Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
INVESTMENT PROJECTS
92-12 | BLUEGRASS WATER PROJECT | 85274 | 0 | 85274 |  | 0% |  |  |  | 1992-07-01 | 1996-12-01 | 1992-09-01
96-19 | CUSTOMER SERVICE SOFTWARE | 644452 | 902300 | -257848 | 71.42% | 5.425% |  |  |  | 1996-12-01 | 1999-06-01 | 1996-11-01 | 2003-12-01
98-01 | INTEGRATED RESOURCE PLAN | 67945 | 0 | 67945 |  | 0% |  |  |  | 1998-02-01 | 1999-09-01 | 1999-02-01
98-08 | SURGE PROTECTION KRS | 1221 | 0 | 1221 |  | 0% |  |  |  | 1998-04-01 | 1999-11-01 | 1998-08-01
98-09 | UPGRADE CART WINCH KRS | 90822 | 0 | 90822 |  | 0% |  |  |  | 1998-02-01 | 1998-11-01 | 1998-08-01
00-02 | PARIS PIKE RELOCATION | -385583 | 0 | -385583 |  | 0% | 65990 | 50000 | 15990 | 2000-03-01 | 2000-12-01 | 2000-03-01 | 2002-10-01
00-03 | HARRODSBURG ROAD RELOCATION DESIGN | -47505 | 0 | -47505 |  | 0% | 69803 | 100000 | -30197 | 2000-02-01 | 2000-09-01 | 2000-01-01 | 2002-12-01
00-04 | RICHMOND ROAD RELOCATION | -774 | 0 | -774 |  | 0% | 121461 | 94000 | 27461 | 2000-03-01 | 2000-11-01 | 2000-03-01 | 2002-11-01
01-01 | SECURITY SYSTEM IMPROVEMENTS | 59287 | 0 | 59287 |  | 0% |  |  |  | 2001-01-01 | 2001-12-01 | 2001-04-01 | 2001-12-01
01-02 | GROUND STORAGE TANK - 3.0 MG | 6464 | 100000 | -93536 | 6.464% | 0.6012% |  |  |  | 2001-03-01 | 2003-12-01 | 2001-02-01
01-03 | SCADA IMPROVEMENTS | 165614 | 100000 | 65614 | 165.6% | 0.6012% |  |  |  | 2001-01-01 | 2003-05-01 | 2002-09-01
01-04 | SCOTT COUNTY MAINS | 764887 | 750000 | 14887 | 102% | 4.509% |  |  |  | 2001-01-01 | 2002-12-01 | 2001-01-01 | 2003-10-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 10317 | 50000 | -39683 | 20.63% | 0.3006% |  |  |  | 2001-01-01 | 2004-12-01 | 2001-02-01
01-06 | KRS SLUICE GATE | 8686 | 100000 | -91314 | 8.686% | 0.6012% | 248960 | 250000 | -1040 | 2001-08-01 | 2002-05-01 | 2001-08-01 | 2002-05-01
01-07 | MAJOR HIGHWAY RELOCATIONS | 230799 | 0 | 230799 |  | 0% | 1221929 | 1050000 | 171929 | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
01-08 | ACQUISITION OF TRIVILLAGE/ELK LAKE | 970 | 0 | 970 |  | 0% | 1849283 | 1860000 | -10717 | 2000-08-01 | 2000-08-01 | 2001-07-01 | 2002-12-01
01-10 | RRS HYDRAULIC IMPROVEMENTS | 1033926 | 1490200 | -456274 | 69.38% | 8.959% |  |  |  | 2001-03-01 | 2002-09-01 | 2001-08-01 | 2003-06-01
01-11 | TRI VILLAGE NEW COLUMBUS PROJECT | 959924 | 1355000 | -395076 | 70.84% | 8.146% |  |  |  | 2001-10-01 | 2003-05-01 | 2002-02-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 74945 | 700000 | -625055 | 10.71% | 4.208% |  |  |  | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | MAJOR HIGHWAY RELOCATIONS | 3047715 | 2000000 | 1047715 | 152.4% | 12.02% | 3369864 | 2000000 | 1369864 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-03 | REPLACE TRAVELING SCREEN & HOUSING | 0 | 200000 | -200000 | 0% | 1.202% |  |  |  | 2002-08-01 | 2003-04-01 | 2003-12-01
02-04 | WATER SUPPLY DEVELOPMENT PROJECT | 0 | 0 | 0 |  | 0% |  |  |  | 2002-04-01 | 2003-12-01 | 2001-06-01
| GRAND TOTAL ITEM B-H TO IP'S | 6819386 | 7747500 | -928114 | 88.02%