## 3rd March
|  | C' ROW |  |  |  |  | D' ROW |  |  |  |  | B' ROW
3rd March 2014
| 8:00 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Quarl Panel Removed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Quarl Panel Prepped | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 5% | 0% | 5%
3 | Quarl Panel Cleaned | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Quarl Panel Clear bore | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
5 | Quarl Panel Inspected | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
6 | Quarl Positioned | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
7 | Quarl Panel Welded |  | 50% |  | 100% | 100% | 100% | 25%
8 | Quarl Butt Welds NDT
9 | Weld Membranes
10 | Throat Liner 'Locking Tab's' Removed
11 | Released for Burner Installation
12 | Burner Installed
13 | Check Burner Hanger Attached
14 | Transportation restraints removed
15 | Burner Set & Aligned
16 | Wind Box Front Plate Welded
17 | Seal Box 'Slip Joint' Welded
18 | Refractory Seal Box Welded
19 | Core Air Expansion Fitted
20 | PF Flange Made
21 | Windbox Front Plate Welded
22 | Ignitor Installed
23 | Ignitor Set & Stroked
24 | Beck Drive Tested
25 | Outer zone Swirler adjustment check
26 | Inner zone Swirler adjustment check
27 | Burner Hoses Fitted
28 | Burner Viewing Ports Fitted
29 | Burner Electrical Complete
30 | Burner Loop Checks
31 | PF Pipe Work Complete
32
|  | F' ROW |  |  |  |  | A' ROW |  |  |  |  | E' ROW
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Quarl Panel Removed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Quarl Panel Prepped | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 0% | 5% | 5% | 0% | 5%
3 | Quarl Panel Cleaned | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100%
4 | Quarl Panel Clear bore | YES | YES | YES | YES |  | YES | YES | YES | YES | YES
5 | Quarl Panel Inspected | YES | YES | YES | YES |  | YES | YES | YES | YES | YES
6 | Quarl Positioned | YES | YES | YES | YES |  | YES | YES | YES | YES | YES
7 | Quarl Panel Welded | 100% | 100% | 50% | 100% |  | 5%
8 | Quarl Butt Welds NDT |  |  |  | ACC
9 | Weld Membranes
10 | Throat Liner 'Locking Tab's' Removed
11 | Released for Burner Installation
12 | Burner Installed
13 | Check Burner Hanger Attached
14 | Transportation restraints removed
15 | Burner Set & Aligned
16 | Wind Box Front Plate Welded
17 | Seal Box 'Slip Joint' Welded
18 | Refractory Seal Box Welded
19 | Core Air Expansion Fitted
20 | PF Flange Made
21 | Windbox Front Plate Welded
22 | Ignitor Installed
23 | Ignitor Set & Stroked
24 | Beck Drive Tested
25 | Outer zone Swirler adjustment check
26 | Inner zone Swirler adjustment check
27 | Burner Hoses Fitted
28 | Burner Viewing Ports Fitted
29 | Burner Electrical Complete
30 | Burner Loop Checks
31 | PF Pipe Work Complete
32