## Sheet1
PROJECT # | Proponent | System ID | DESCRIPTION | Last Completion Date | Frequency/ Due Date | Start Date | Total 2014 | O&M Current Estimates/ Actuals | Remainder O&M Outage Funds | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
TC2S14OUT | Sedam | Draft Equipment | ID Fan - Install Spare Hub (1) | 2014-03-01 | 2014 | 2014-03-17 | 0 | 360000 | -360000
TC2S14OUT | Sedam | Pulverizers | Pulverizer Overhauls- 2A & 2D | 2014-04-01 | 2014 | 2014-03-10 | 0 | 300000 | -300000
TC2S14OUT | Waller | Air Quality Control Systems | WESP Repairs (Leaks/ Water Distribution) | 2013-03-01 | All Major Outages | 2014-03-17 | 50000 | 100000 | -50000
TC2S14OUT | Maldonado | Boiler | Boiler Repairs (tubes, welds, X-rays, etc.) | 2014-02-14 | All Major Outages | 2014-03-10 | 250000 | 100000 | 150000
TC2S14OUT | Mills | FGD | Recycle Pump Disch./ Inlet Valves | 2014-04-01 |  | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Misc. | Misc/ Common | TC2 Platform additions | 2014-04-01 | 2014 | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Sedam | Draft Equipment | FD Fan Rebuild Hub/fan (2) | 2014-03-01 | 2014 | 2014-03-03 | 0 | 96000 | -96000
TC2S14OUT | Dorwart | Material Handling | Reactant Prep "A" Ball mill gearbox changeout. | 2014-04-01 | 2014 | 2014-03-17 | 0 | 90000 | -90000
TC2S14OUT | Waller | Air Quality Control Systems | DESP Repairs- (leaks, internal repairs, rappers/ plates) | 2013-03-01 | All Major Outages | 2014-03-17 | 50000 | 75000 | -25000
TC2S14OUT | Phelps | FGD | FGD Reactant Tank Cleanout/Inspect, Nozzle repairs (incr. $75K) | 2014-03-01 | All Major Outages | 2014-03-10 | 75000 | 75000 | 0
TC2S14OUT | Phelps | FGD | FGD Inspections- Inlet, Module, agitator, mist eliminators, nozzle & trays | 2014-02-01 | All Major Outages | 2014-03-10 | 0 | 75000 | -75000
TC2S14OUT | Sedam | Pulverizers | Pulverizer- Floor weld overlay | 2014-04-01 | 2014 | 2014-03-17 | 0 | 75000 | -75000
TC2S14OUT | Noonan | Turbine/ Generator | Main Turbine LP Blade Inspect | 2014-04-01 | 2014 | 2014-03-24 | 60000 | 60000 | 0
TC2S14OUT | Waller | Air Quality Control Systems | WESP Wash | 2013-03-01 | All Major Outages | 2014-03-17 | 100000 | 50000 | 50000
| Waller | Air Quality Control Systems | DESP Wash | 2013-03-01 | All Major Outages | 2014-03-17 | 0 | 40000 | -40000
TC2S14OUT | Bullock | Draft Equipment | Chimney flue inspection | 2014-03-01 | All Major Outages | 2014-03-17 | 30000 | 40000 | -10000
TC2S14OUT | Feider | Air Quality Control Systems | CEM's equipment testing and repairs. (Particulate Monitor Work) | 2014-03-01 | All Major Outages | 2014-03-17 | 0 | 35000 | -35000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- drag chain/ idlers | 2014-03-01 | As Needed | 2014-03-03 | 0 | 35000 | -35000
TC2S14OUT | Mills | Turbine/ Generator | 2A Turbine oil cooler clean | 2014-02-01 | 2014 | 2014-03-10 | 0 | 35000 | -35000
TC2S14OUT | Henderson | Pulverizers | Pulverizer Inerting steam valves | 2014-04-01 | 2014 | 2014-03-17 | 0 | 30000 | -30000
TC2S14OUT | Bullock | Feedwater Systems | Move Spare BCP | 2014-03-01 | 2014 | 2014-03-24 | 0 | 25000 | -25000
TC2S14OUT | Mills | Pulverizers | Mill Expansion Joints | 2014-04-01 | 2014 | 2014-03-03 | 0 | 20000 | -20000
1916000