## 21st April
SMR | MONDAY
132 | 21st April 2014 | C' ROW |  |  |  |  | D' ROW |  |  |  |  | B' ROW
| 8:00 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Quarl Panel Removed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Quarl Panel Prepped | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Quarl Panel Cleaned | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Quarl Panel Clear bore | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
5 | Quarl Panel Inspected | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
6 | Quarl Positioned | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
7 | Quarl Panel Welded | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Quarl Butt Welds NDT | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC
9 | Membranes Fitted | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Weld Membranes | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Throat Liner 'Locking Tab's' Removed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
12 | Refractory Seal Box Welded | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
13 | Refractory Installed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
14 | Windbox Seal Plate Installed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Windbox Seal Plate Welded | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | Burner Staged | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
16 | Released for Burner Installation | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
17 | Burner Installed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Check Burner Hanger Attached | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
19 | Transportation restraints removed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
20 | Burner Set & Aligned | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
21 | Windbox Front Plate Welded | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Wind Box Front Plate Gasket Fitted | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | Internal Seal Box 'Slip Joint' Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded
23 | Core Air Expansion Fitted | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
24 | PF Flange Made | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Ignitor Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed
26 | Final Alignment Check
27 | Ignitor Set & Stroked
| Beck Drive Installed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
28 | Beck Drive Tested
29 | Outer zone Swirler adjustment check
30 | Inner zone Swirler adjustment check
31 | Burner Hoses Fitted
32 | Burner Viewing Ports Fitted
33 | Burner Electrical Complete
34 | Burner Loop Checks
35 | PF Pipe Work Complete
36 | PF Gags Removed
| Rear Wall | F' ROW |  |  |  |  | A' ROW |  |  |  |  | E' ROW
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Quarl Panel Removed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Quarl Panel Prepped | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Quarl Panel Cleaned | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Quarl Panel Clear bore | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
5 | Quarl Panel Inspected | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
6 | Quarl Positioned | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
7 | Quarl Panel Welded | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Quarl Butt Welds NDT | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC | ACC
9 | Membranes Fitted | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Weld Membranes | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Throat Liner 'Locking Tab's' Removed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
12 | Refractory Seal Box Welded | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
13 | Refractory Installed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
14 | Windbox Seal Front Plate Installed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Windbox Seal Front Plate Welded | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | Burner Staged | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
16 | Released for Burner Installation | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
17 | Burner Installed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Check Burner Hanger Attached | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
19 | Transportation restraints removed | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
20 | Burner Set & Aligned | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
21 | Windbox Front Plate Welded | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Wind Box Front Plate Gasket Fitted | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | Internal Seal Box 'Slip Joint' Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded | Welded
23 | Core Air Expansion Fitted | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES
24 | PF Flange Made | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Ignitor Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed | Installed
26 | Final Alignment Check
27 | Ignitor Set & Stroked
Beck Drive Installed
28 | Beck Drive Tested
29 | Outer zone Swirler adjustment check
30 | Inner zone Swirler adjustment check
31 | Burner Hoses Fitted
32 | Burner Viewing Ports Fitted
33 | Burner Electrical Complete
34 | Burner Loop Checks
35 | PF Pipe Work Complete
36 | PF Gags Removed