## Sheet1
PROJECT # | Proponent | System ID | DESCRIPTION | Last Completion Date | Frequency/ Due Date | Start Date | Budget Totals 2014 | O&M Current Estimates/ Actuals | Remainder O&M Outage Funds | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
TC2S14OUT | H. Turner | Air Quality Control Systems | Pulse Jet Fabric Filter Bags & Cages- Samples/ Repairs | 2014-02-14 | All Major Outages | Capital | 0 | 0 | 0
TC2S14OUT | Feider | Air Quality Control Systems | CEM's equipment testing and repairs. (Particulate Monitor Work) | 2014-03-01 | All Major Outages | 2014-03-17 | 0 | 35000 | -35000
TC2S14OUT | H. Turner | Air Quality Control Systems | PJFF pulse header J tube inspect for corrosion (2 sections each side) | 2013-03-01 | As Needed | Not Scheduled | 10000 | 0 | 10000
TC2S14OUT | H. Turner | Air Quality Control Systems | PJFF Inlet, Outlet & bypassdamper inspection. (some scaffold requ.) | 2013-03-01 | All Major Outages | Not Scheduled | 25000 | 25000 | 0
TC2S14OUT | Henderson | Air Quality Control Systems | PJFF Inspection/ Repairs (bag detectors, solenoids, door seals, etc…) | 2014-02-14 | All Major Outages | 2014-02-20 | 60000 | 52000 | 8000
TC2S14OUT | Waller | Air Quality Control Systems | DESP Repairs- (leaks, internal repairs, rappers/ plates) | 2013-03-01 | All Major Outages | 2014-03-17 | 50000 | 50000 | 0
TC2S14OUT | Waller | Air Quality Control Systems | DESP/ WESP Inspection by 3rd Party | 2014-02-14 | All Major Outages | 2014-02-10 | 20000 | 25500 | -5500
| Waller | Air Quality Control Systems | DESP Wash | 2013-03-01 | All Major Outages | 2014-03-17 | 0 | 0 | 0
TC2S14OUT | Waller | Air Quality Control Systems | WESP Wash | 2013-03-01 | All Major Outages | 2014-03-17 | 100000 | 0 | 100000
TC2S14OUT | Waller | Air Quality Control Systems | WESP Repairs (Leaks/ Water Distribution) | 2013-03-01 | All Major Outages | 2014-03-17 | 50000 | 59000 | -9000
TC2S14OUT | Waller | Air Quality Control Systems | WESP piping replacement. | 2014-04-14 | 2014 | 2014-03-27 | 0 | 350000 | -350000
| Waller | Air Quality Control Systems | Clean WESP Irrigation Headers | 2013-03-01 | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- inspection | 2014-02-14 | All Major Outages | 2014-02-18 | 150000 | 25000 | 125000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- refactory | 2014-03-01 | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- drag chain/ idlers | 2014-03-01 | As Needed | 2014-03-03 | 0 | 35000 | -35000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- Ceramic Tile | 2014-03-01 | As Needed | 2014-04-07 | 0 | 15000 | -15000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- Seal plate/ Dipper | 2014-03-01 | As Needed | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Mills | Ash Handling Systems | Ash Pit Maintenance- Cleanout doors | 2014-03-01 | 2014 | 2014-04-07 | 0 | 40000 | -40000
TC2S14OUT | Henderson | Boiler | Sootbloweer control vavles | 2014-02-14 | 2014 | 2014-03-10 | 30000 | 8000 | 22000
TC2S14OUT | Henderson | Boiler | SH Sparay Valve overhauls (4) |  | All Major Outages |  | 230000 | 0 | 230000
TC2S14OUT | Henderson | Boiler | Stage 1- "A" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | Stage 1- "B" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | Stage 2- "A" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | Stage 2- "B" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | RH Spray valve rebuild |  | All Major Outages |  | 100000 | 0 | 100000
TC2S14OUT | Henderson | Boiler | 2A | 2012-02-01 | 2 yrs | 2014-03-17 | 0 | 4000 | -4000
TC2S14OUT | Henderson | Boiler | 2B | 2012-02-01 | 2 yrs | 2014-03-17 | 0 | 4000 | -4000
TC2S14OUT | Henderson | Boiler | O2 Probes | 2013-03-01 | All Major Outages | 2014-04-14 | 0 | 2500 | -2500
TC2S14OUT | Maldonado | Boiler | Boiler Inspection Wall NDE & Wall Insp where hydrojets blow | 2013-03-01 | All Major Outages | 2014-02-24 | 75000 | 100000 | -25000
TC2S14OUT | Maldonado | Boiler | Boiler Tube Thickness Mapping/ Samples | 2013-03-01 | All Major Outages | 2014-03-03 | 50000 | 0 | 50000
TC2S14OUT | Maldonado | Boiler | Boiler Amstar coating repair/patching | 2013-03-01 | All Major Outages | 2014-05-05 | 0 | 260000 | -260000
TC2S14OUT | Maldonado | Boiler | Boiler Repairs (tubes, welds, X-rays, etc.) | 2014-02-14 | All Major Outages | 2014-03-10 | 250000 | 100000 | 150000
TC2S14OUT | Maldonado | Boiler | Boiler Leak- Existing transition header | 2014-02-14 | 2014 | 2014-02-26 | 0 | 40000 | -40000
TC2S14OUT | Maldonado | Boiler | Boiler Deslag | 2014-02-14 | As Needed | 2014-02-08 | 20000 | 12000 | 8000
TC2S14OUT | Maldonado | Boiler | Boiler Inspection Door installation | 2014-02-14 | 2014 | 2014-02-24 | 0 | 120000 | -120000
TC2S14OUT | Maldonado | Boiler | Burners- Inspection/ Repairs | 2014-02-14 | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Maldonado | Boiler | Boiler Safeties- Insp./Repairs | 2014-02-01 |  | 2014-03-24 | 0 | 15000 | -15000
TC2S14OUT | Mills | Boiler | Overhaul Hydrojet water cannons (4) | 2014-02-14 | As Needed | 2014-04-07 | 120000 | 20000 | 100000
TC2S14OUT | Mills | Boiler | Boiler Valves- Main steam line drain | 2014-02-01 | As Needed | 2014-05-05 | 0 | 30000 | -30000
| Mills | Boiler | PORV Electromatic Relief Valve repairs (increase $100K) | 2013-03-01 | As Needed | Not Scheduled | 150000 | 0 | 150000
| Mills | Boiler | 2A | 2013-03-01 | As Needed | Not Scheduled | 0 | 0 | 0
| Mills | Boiler | 2B | 2013-03-01 | As Needed | Not Scheduled | 0 | 0 | 0
| Raker | Boiler | Boiler Chemical Clean | 2012-09-01 | 2020 | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Dorwart | Circulating Water | Circulating Water Line Inspection/ Repairs | 2013-03-01 | 2014-03-01 | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Henderson | Circulating Water | Cooling Tower Pump Motors |  | 2 yrs |  | 0 | 0 | 0
TC2S14OUT | Henderson | Circulating Water | 2A | 2013-03-01 | 2014 | 2014-03-31 | 0 | 1500 | -1500
TC2S14OUT | Henderson | Circulating Water | 2B | 2013-03-01 | 2014 | 2014-03-31 | 0 | 1500 | -1500
TC2S14OUT | Henderson | Circulating Water | 2C |  | 2014 | 3-34-2014 | 0 | 1500 | -1500
| Mills | Circulating Water | Cooling Tower Pump Overhauls |  | 2 yrs | Not Scheduled | 0 | 0 | 0
| Mills | Circulating Water | 2A |  | 2 yrs | Not Scheduled | 0 | 0 | 0
| Mills | Circulating Water | 2B |  | 2 yrs | Not Scheduled | 0 | 0 | 0
| Mills | Circulating Water | 2C |  | 2 yrs | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Phelps/ Stewart | Circulating Water | NDCT header/seal/ fill/ Insp./ Repairs | 2013-03-01 | All Major Outages | 2014-03-24 | 10000 | 15000 | -5000
TC2S14OUT | Dorwart | Condenser | Condensor Inspection/ NDE/ Repairs | 2014-03-01 | All Major Outages | 2014-02-17 | 20000 | 15000 | 5000
TC2S14OUT | Mills | Condenser | Condenser Vacuum Pump Overhauls- casing leak |  |  |  | 0 | 0 | 0
| Mills | Condenser | 2A |  |  | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Mills | Condenser | 2B |  | 2 yrs | 2014-03-24 | 0 | 17000 | -17000
| Mills | Condenser | 2C |  |  | Not Scheduled | 0 | 0 | 0
| Mills | Condenser | 2D |  |  | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Bullock | Draft Equipment | Chimney flue inspection | 2014-03-01 | All Major Outages | 2014-03-17 | 30000 | 40000 | -10000
TC2S14OUT | Dorwart | Draft Equipment | Expansion Joint Repair and Shields | 2014-04-01 | All Major Outages | 2014-04-07 | 250000 | 75000 | 175000
TC2S14OUT | Dorwart | Draft Equipment | Duct work- Inspections & Repairs- PA, SA, AH--out. | 2014-02-01 | All Major Outages | 2014-04-07 | 300000 | 150000 | 150000
TC2S14OUT | Henderson | Draft Equipment | ID Fan Motor Inspection | 2013-03-01 | All Major Outages | 2014-03-24 | 35000 | 15000 | 20000
TC2S14OUT | Henderson | Draft Equipment | FD Fan Motor Inspections | 2014-03-01 | All Major Outages | 2014-03-24 | 50000 | 5000 | 45000
TC2S14OUT | Hudson | Draft Equipment | Air Heater Wash | 2014-04-01 | Annually | 2014-05-05 | 40000 | 30000 | 10000
TC2S14OUT | Maldonado | Draft Equipment | Air Heater Repairs/ Inspection | 2014-03-01 | All Major Outages | 2014-03-03 | 25000 | 15000 | 10000
TC2S14OUT | Mills | Draft Equipment | Fan Inspections/ Cleaning (Serviceman/Blades) ID,FD,PA | 2014-03-01 | All Major Outages | 2014-02-24 | 40000 | 25000 | 15000
TC2S14OUT | Sedam | Draft Equipment | ID Fan - Install Spare Hub (1) | 2014-03-01 | 2014 | 2014-03-17 | 0 | 361000 | -361000
TC2S14OUT | Sedam | Draft Equipment | FD Fan Rebuild Hub/fan (2) | 2014-03-01 | 2014 | 2014-03-03 | 0 | 97000 | -97000
TC2S14OUT | Sedam | Draft Equipment | FD Fan Hydraulic Cylinder Rebuild |  |  | 2014-03-03 | 0 | 18500 | -18500
TC2S14OUT | Henderson | Electrical | Temporary Power |  | All Major Outages |  | 0 | 5000 | -5000
| Moore | Electrical | Substation Maintenance (Relays & Transformers) |  | 4 yrs | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Payne | Electrical | Switchgear Maintenance | 2012-04-01 | 2 yrs | Not Scheduled | 50000 | 0 | 50000
| Bullock | Feedwater Systems | BFP Pump overhauls/ inspections |  | As Needed | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | 2A |  | As Needed | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | 2B |  | As Needed | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | Motor Driven |  | As Needed | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | BFP Booster Pump overhauls/ inspections |  | As Needed | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | 2A |  | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Bullock | Feedwater Systems | 2B- mechanical seal | 2014-03-01 | As Needed | 2014-02-24 | 0 | 6000 | -6000
| Bullock | Feedwater Systems | Motor Driven |  | As Needed | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | BFP Turbine overhauls/ inspections |  | 2020 | Not Scheduled | 0 | 0 | 0
| Bullock | Feedwater Systems | 2A |  | 0 | Not Scheduled | 0 | 0
| Bullock | Feedwater Systems | 2B |  | 0 | Not Scheduled | 0 | 0
| Bullock | Feedwater Systems | De-gaussing of pump shafts during pump overhauls | 2012-04-01 | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Bullock | Feedwater Systems | Move Spare BCP | 2014-03-01 | 2014 | 2014-03-24 | 0 | 25000 | -25000
| Dorwart | Feedwater Systems | BCP Overhauls/ Thrust Inspection | 2014-03-01 | As Needed | 2014-02-24 | 0 | 40000 | -40000
TC2S14OUT | Dorwart | Feedwater Systems | Deaerator NDE | 2014-02-01 | All Major Outages | 2014-02-24 | 23000 | 35000 | -12000
| Dorwart | Feedwater Systems | Feedwater Heater Eddy Current Testing | 2012-05-01 | 2 yrs. Or All Major Outages | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Henderson | Feedwater Systems | BFP Recirc Valve Overhauls- |  | As Needed | Completed | 150000 | 0 | 150000
TC2S14OUT | Henderson | Feedwater Systems | 2A | 2014-02-01 |  | 2014-02-24 | 0 | 32000 | -32000
TC2S14OUT | Henderson | Feedwater Systems | 2B | 2014-02-01 |  | 2014-02-24 | 0 | 0 | 0
| Henderson | Feedwater Systems | MDBFP |  |  | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Henderson | Feedwater Systems | MBBFP motor inspection | 2013-03-01 | 2 yrs | 2014-03-01 | 25000 | 0 | 25000
TC2S14OUT | Mills | Feedwater Systems | Valve Inspections |  | All Major Outages | 2014-02-10 | 60000 | 40000 | 20000
TC2S14OUT | Mills | Feedwater Systems | Safeties- Testing & Repairs | 2014-02-01 | All Major Outages | 2014-03-24 | 40000 | 15000 | 25000
TC2S14OUT | Mills | Feedwater Systems | BCP recirc & HP/LP bypass valve pull & Insp. |  | 2014 | 2014-04-14 | 25000 | 37000 | -12000
TC2S14OUT | Mills | Feedwater Systems | Feedwater Heater Diaphragms | 2014-03-01 | As Needed | 2014-02-17 | 0 | 15000 | -15000
TC2S14OUT | Mills | Feedwater Systems | 2B TDBFP Booster Pump Mechanical Seal Leaking | 2014-03-01 | 2014 | 2014-04-07 | 0 | 6000 | -6000
TC2S14OUT | Henderson | FGD | Recycle Pump motor oil change | 2014-04-01 | All Major Outages | 2014-03-01 | 0 | 1200 | -1200
TC2S14OUT | Mills | FGD | Reaction Tank Agitator Overhaul |  | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Mills | FGD | Recycle Pump seal water line. | 2014-03-01 | 2014 | 2014-04-07 | 0 | 1000 | -1000
TC2S14OUT | Mills | FGD | Recycle Pump Disch./ Inlet Valves | 2014-04-01 |  | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Phelps | FGD | FGD Reactant Tank Cleanout/Inspect, Nozzle repairs (incr. $75K) | 2014-03-01 | All Major Outages | 2014-03-10 | 75000 | 75000 | 0
TC2S14OUT | Phelps | FGD | FGD Inspections- Inlet, Module, agitator, mist eliminators, nozzle & trays | 2014-02-01 | All Major Outages | 2014-03-10 | 0 | 75000 | -75000
TC2S14OUT | Phelps | FGD | Repair Reaction Tank Agitater Blades |  | As Needed | 2014-03-17 | 100000 | 0 | 100000
TC2S14OUT | Phelps | FGD | TC2 Gypsum Line | 2014-03-01 | 2014 | 2014-02-24 | 0 | 8880 | -8880
TC2S14OUT | Dorwart | High Energy Piping | HEP piping and hanger repairs from inspections | 2014-03-01 | 2 yrs. Or All Major Outages | 2014-03-03 | 150000 | 15000 | 135000
TC2S14OUT | Dorwart | Material Handling | Reactant Prep "A" Ball mill gearbox changeout. | 2014-04-01 | 2014 | 2014-03-17 | 0 | 90000 | -90000
TC2S14OUT | Osgood | Material Handling | Overhaul & Clean A/ B Ball Mill Motor |  | As Needed | Completed | 25000 | 0 | 25000
| Osgood | Material Handling | "A" | 2013-03-01 | As Needed | Completed | 0 | 0 | 0
| Osgood | Material Handling | "B" | 2012-10-01 | As Needed | Completed | 0 | 0 | 0
TC2S14OUT | Ball | Misc/ Common | Scaffolding |  | All Major Outages | Spread | 100000 | 0 | 100000
TC2S14OUT | Bullock | Misc/ Common | Elevator Operators/ Maintenance |  | All Major Outages | Spread | 0 | 35000 | -35000
TC2S14OUT | Henderson | Misc/ Common | Instrument Air Compressor Motor Overhaul |  | 2014 | 2014-04-07 | 24000 | 0 | 24000
TC2S14OUT | Henderson | Misc/ Common | 2A & 2B Inst. Air Dryers | 2014-04-01 | As Needed | 2014-04-07 | 0 | 6000 | -6000
TC2S14OUT | Henderson | Misc/ Common | Motor Testing | 2014-03-01 | All Major Outages |  | 0 | 0 | 0
TC2S14OUT | Hudson | Misc/ Common | Industrial Cleaning |  | All Major Outages | Spread | 200000 | 55000 | 145000
TC2S14OUT | Misc. | Misc/ Common | T&M add on work. |  | All Major Outages | Spread | 0 | 50000 | -50000
TC2S14OUT | Misc. | Misc/ Common | Service Reps- Alstom, Howden, MD&A, Diamond Power) |  | All Major Outages |  | 150000 | 0 | 150000
TC2S14OUT | Misc. | Misc/ Common | TC2 Platform additions | 2014-04-01 | 2014 | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Slaughter | Misc/ Common | inspect for leakage. (Air-in)? | 2014-01-01 | All Major Outages | Completed | 25000 | 0 | 25000
| Slaughter | Misc/ Common | Cooler Cleaning Support |  | All Major Outages | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Henderson | Pulverizers | Pulverizer Inerting steam valves | 2014-04-01 | 2014 | 2014-03-17 | 0 | 30000 | -30000
TC2S14OUT | Henderson | Pulverizers | Pulverizer 2D Classifier Motor | 2014-04-01 | 2014 | 2014-02-24 | 0 | 1500 | -1500
TC2S14OUT | Henderson | Pulverizers | PA Fan Motor Inspections | 2014-03-01 | All Major Outages | 2014-03-24 | 0 | 5000 | -5000
TC2S14OUT | Mills | Pulverizers | Mill Expansion Joints | 2014-04-01 | 2014 | 2014-03-03 | 0 | 20000 | -20000
TC2S14OUT | Mills/ Henderson | Pulverizers | PA Fan - Inspect bearings and input damper linkage | 2014-04-01 | 2014 | 2014-04-07 | 25000 | 0 | 25000
TC2S14OUT | Sedam | Pulverizers | Pulverizer Inspections | 2014-03-01 | All Major Outages | 2014-03-03 | 0 | 13500 | -13500
TC2S14OUT | Sedam | Pulverizers | Pulverizer Overhauls- 2A & 2D | 2014-04-01 | 2014 | 2014-03-10 | 0 | 35000 | -35000
TC2S14OUT | Sedam | Pulverizers | Pulverizer- Floor weld overlay | 2014-04-01 | 2014 | 2014-03-17 | 0 | 75000 | -75000
TC2S14OUT | Dorwart | SCR | Vacuum & Inspect SCR catalyst (increased $135K) | 2014-02-01 | All Major Outages | 2014-02-10 | 75000 | 10000 | 65000
| Dorwart | SCR | Structure Repairs |  | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Dorwart | SCR | Catalyst Samples | 2014-02-01 | All Major Outages | Completed | 0 | 0 | 0
TC2S14OUT | Dorwart | SCR | Catalyst Replacement/ Refurbishment | 2014-03-01 | As Needed | 2014-02-24 | 0 | 0 | 0
TC2S14OUT | Henderson | SCR | NH3 detectors | 2014-04-01 | All Major Outages | 2014-04-14 | 0 | 3300 | -3300
| Mills | SCR | Ammonia Pump Overhauls- 2A/ 2B |  | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Mills | SCR | Safety Relief Valve Replacements |  | 4 yrs | 2014-04-21 | 0 | 40000 | -40000
| Bullock | Turbine/ Generator | TC2 Turbine Expansion Joints (Replace)- 2018 (10yr) |  | 2018 | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Mills | Turbine/ Generator | 2A Turbine oil cooler clean | 2014-02-01 | 2014 | 2014-03-10 | 0 | 35000 | -35000
TC2S14OUT | Noonan | Turbine/ Generator | Main Turbine LP Blade Inspect | 2014-04-01 | 4yrs | 2014-03-24 | 60000 | 10000 | 50000
| Noonan | Turbine/ Generator | Turbine Overhaul |  | 2018 | Not Scheduled | 0 | 0 | 0
| Noonan | Turbine/ Generator | Turbine Extraction Steam Check Valves Overhaul- 2016 |  | 2016 | Not Scheduled | 30000 | 0 | 30000
| Noonan | Turbine/ Generator | Turbine Main Steam Valve Inspection move to 2016 |  | 2016 | Not Scheduled | 0 | 0 | 0
| Noonan | Turbine/ Generator | Turbine Bypass Valves- 2016 |  | 2016 | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Dorwart | Turbine/ Generator | Hot Reheat Turbine bypass valve flange pipe replacement | 2014-04-14 |  | 2014-04-24 | 0 | 200000 | -200000
| Noonan | Turbine/ Generator | Turbine Intercept Valves- |  |  | Not Scheduled | 0 | 0 | 0
| Noonan | Turbine/ Generator | Turbine Control Valves- |  |  | Not Scheduled | 0 | 0 | 0
| Noonan | Turbine/ Generator | Turbine Combined Reheat Stop Valves- |  |  | Not Scheduled | 0 | 0 | 0
| Noonan | Turbine/ Generator | Hit Skid Testing |  | 2018 | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Noonan | Turbine/ Generator | TC2 Turbine/ Generator #11 Bearing leak | 2014-04-01 | 2014 | 2014-03-24 | 0 | 5000 | -5000
| Noonan | Turbine/ Generator | EHC System Flush & Pump Overhauls | 2012-03-01 | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Payne | Turbine/ Generator | Generator Maintenance |  | All Major Outages | 2014-02-24 | 0 | 2000 | -2000
TC2S14OUT | Payne | Turbine/ Generator | Generator Lead Box Inspection/ Repairs | 2014-03-01 | All Major Outages | 2014-03-10 | 0 | 0 | 0
| T. Turner | Turbine/ Generator | Turbine Oil 3-way Valve | 2014-03-01 | As Needed | 2014-03-17 | 0 | 15000 | -15000
|  |  | TOTALS |  |  |  | 3702000 | 3806380 | -104380