## Cover
Trimble County Station Outage Planning Document
Unit 2
2014 Spring Outage
February 10th - May 26th
TC2S14

## Index
Tab
1 | Executive Summary
2 | EFOR Drivers
3 | Shutdown Procedure
4 | Outage Personel
5 | Support, Env, Health and Safety
6 | Areas of Responsibility
7 | Safety Walk-Down
8 | Work Schedules
9 | Major Work Schedule
10 | O&M Budget
11 | B&V Work Orders
12 | CO Work Orders
13 | PM Work Orders
14 | Capital Detail
15 | Post Outage Review
16 | Project Work Scopes

## Executive Summary
OUTAGE PURPOSE:
TC2 Burner replacements, boiler roof tube repairs, Inspections, backlog outage work orders and p.m.'s.
The critical path of this outage is the burner replacements- by Doosan & SE Boiler.
OUTAGE GOAL:
Boiler reliability and efficiency improvements.
OUTAGE SCHEDULE:
The unit is scheduled to come off line on February 7th, 2014 after peak and to be synchronized on line on May 26th, 2014 @ 0600 hours. Outage duration is driven by burner replacements.
PRE-OUTAGE MEETING AND PLANNING SCHEDULE:
Outage Review Meeting………………….….. (Monthly)
Job list finalized…………………………………… 1-31-14
LOTO Clearance Requests due date……..2-4-14
Plant Review……………………….…….………....1-30-14
Review with VP Generation……….………....To be determined.
OUTAGE UPDATE MEETINGS
Daily Contractors Safety Meet 0900 Lunch Room
Daily Plant Update Meeting 0215 5th Floor Main Conference Room
Post Outage Meeting June , 2014 in 5th Floor Main Conference Room
OUTAGE MILESTONES:
Unit Off-Line………………………………………… 2/7/14@ After Peak
Unit off gear....…………………………………….. 2/17/14 @ 1200
Unit on gear…………………………………………. 5/19/14 @ 1600
Warm Turbine..…………………………………….. 5/24/14 @ 1600
Turn over to Operations…………………...……5/24/14 @ 18:00
Turn over to Dispatch…………………………….5/26/14 @ 06:00

## EFOR Drivers
2014 EFOR (YTD)
EFOR Contributors | Dates: | Projects to Address EFOR
(1)Submerged Scraper Conveyor | 2013-12-19 | Bringing in Alstom Rep., Inspection, Idler wheel replacement, changing basalt tile & grout, Installing cleanout doors. Inspect sprocket & chain.
(2) Air Heater Pluggage | 2013-12-07 | Will check Air Heater Differential instrumentation. Air Heater sootblower steam quality upgrade.
(3) Heater 7B Bypass Valve Packing | 2013-11-21 | Resolved during the outage. No additional work needed. Heater 6A/B & 8A/B diaphragm repairs.
(4) Electromatic and #3 safety valve repairs. | 2013-11-16 | Overhauling isolation valves only. Safety Valve Testing.
(5) FD Fan Stalls/ Air Heater Wash | 2013-09-12 | Checking ports & instrumentation on FD Fan Stall. Logic changes were made. Blade Inspections.
(6) RH Safety Valve Integrity Test | 2013-02-11 | Testing RH Safety valves.
(7) RH Pendant Tube Leak | 2013-02-08 | Inspecting Pendants.
(8) 345KV 4542 Clifty Creek "A" phase line failure/ ID Fan EHC Leak | 2013-02-05 | Issue Resolved during outage.

## Shutdown Procedure
TC-2 Maintenance Outage
Spring 2014
Thursday (February 6th 2014)
· Change coal on the mills in service from 70/30 Riverview / PRB to 100% Riverview.
· Change the Hydro-jets to aggressive mode starting the am shift and remain on aggressive until the outage.
· Empty the normal H/L silo if possible.
Friday (February 7th 2014)
· Run Hydro-jets in aggressive mode until the unit is off.
· Check set point on all safeties, scheduled @ 12:00 hrs.
· Start reducing solids in the reaction tank in prep for draining.
· Remove the condenser ball cleaning system from service and card.
· Test run the Trip Manifold Test circuit. (see attached)
· Do not run a casing wash on the WESP before we come off line due to inspection request.
· Start the ramp down to come off line @ 24:00 hrs.
· Unit is scheduled off line @ 03:00 hrs.
· Remove fires from the boiler and start cool down. (increase air flow ~ 4200 KPPH and continue to circulate water). Note: Do not exceed > 100 degs per hour on cool down.
· Isolate and drain the water coils, just after fires are out!
· Isolate and card the ammonia system, open the injection valves and purge the lines on boiler cool down.
· Open available boiler doors for cool down.
· Card equipment as it’s available, as per carding request.
Saturday (February 8th 2014)
· Continue boiler cool down until we have about 170 to 180 on spiral and vertical tube temperatures. (~15 hrs.).
· Set up for boiler de-slag.
· Flash drain boiler.
· Card the DESP before fans are out of service to allow for purge.
· Complete boiler cool down, remove the fans from service and card.
· Card burners for change out.
· Remove A/H’s from service after fans are out of service.
· Check all hoppers empty.
· Have S/M pin the feedwater line before draining the feedwater system.
· Isolate and drain the condensate and feedwater line.
· Isolate and drain the Deaerator Storage Tank.
Sunday (February 9th 2014)
· Check the SSC empty and card, drain and card to move.
· Isolate and drain the Hotwell.
· Card equipment as requested.
· Isolate and drain the Stator Cooling System.
· Pull cooling tower screens and clean.
· Isolate and drain the Hydrojet System.
Week of 2/10/14
· Drain the reaction tank down and refill with water until the density is 1.06.
· Remove the Turbine from turning gear.
· Card and isolate the Condenser water box and clean.
· Remove the Circulation Water System from service.
· Refill the SSC after its back in place and return to service for Amstar Coating removal.
· Thursday – We will need to run one I/D fan at min. for Doosan to remove the Amstar Coating (24hrs). Please run the “2A” Recycle Pump and WESP plate irrigation wash when the I/D Fan is in service.
· Friday after we finish running the I/D fan for Doosan to remove the Amstar Coating, Isolate and drain the Reaction Tank.
· Check the SSC empty and card, drain and card to move.
· Isolate and drain the “A” turbine Oil Cooler for removal.
Week of 2/17/14
· Remove the trays in the deaerator heater for inspection.
· Purge the Generator.
· Drain Turbine Oil back for inspection.
· Isolate and drain the Seal Oil System. (Shut down the Seal Oil Vacuum Pump as per the shutdown procedure for extended lay-up).
· Open the doors on the SCR and clean as needed.
Week of 2/24/14
· Set-up and shoot the A1 & A2 condenser.
· Open the lower doors on the PJFF for inspection.
Week of 3/3/14
· Set-up and shoot the B1 & B2 condenser.
Card; Drain and inspect the hotwell.
· Clean the hotwell pump suction strainers.
· Remove the heads from the “2A” Closed Cooling heat exchanger and clean.
Week of 3/10/14
· Remove the heads from the “2B” Closed Cooling heat exchanger and clean.
Week of 3/17/14
· Pull and inspect the hydrated lime and PAC injection lances.
Week of 3/24/14
· Empty and clean the Cooling Tower basin.
Week of 3/31/14
· Change out Stator Resin.
Week of 4/7/14
· Empty and clean the oil / water separator, repair or replace the screen as needed.
· Inspect the Hotwell flash box.
Week of 4/14/14
· Inspect the boiler drains vessel.
· Work on valve tags and housekeeping.
Week of 4/21/14
· Work on valve tags and housekeeping.
Week of 4/28/14
· Work on valve tags and housekeeping.
· Refill the Cooling Tower.
· Refill the Reaction Tank.
Week of 5/5/14
· Purge the Generator.
· Refill the Turbine Oil System.
Week of 5/12/14
· Refill the Turbine Oil System.
· Complete dye test on the condenser.
· Drain and refill the hotwell.
Week of 5/19/14
· Refill the condensate system.
· Start water clean-up.
· Fans in service on 5/23/14.
· Boiler Hydro?
· Fires in the boiler 5/24/14.
TC-2 on Line May 25th

## Outage Personel
Trimble County Phone List
Last Updated: 12/27/13
REDACTED FOR PRIVACY - PERSONAL INFORMATION
Name | Office | Pager | Mobile | Home

## Support, Env, Health and Safety
Support, Env, Health and Safety
Sanitary facilities | Dave Gilliland/ Missy Davis (Evans)
Office & break facilities | David Gilliland
Daily safety | Walk downs to be performed by job representatives.
Whenever possible all hoses, leads and cords are to be maintained overhead.
Air monitoring | Job Proponent
Confined space permits | Job Proponent
Hot work permits | Job Proponent
Digging Permits | Job Proponent/ Grant Phelps
Scaffolding | Job Proponent- To be tagged and inspected daily by Competent person
PPE | Storeroom Supervisor- Chris Hayes
Security | Carolyn Moore
Special Tagging Requirements | Dave Gilliland
Special Waste | Hannah Hannon

## Areas of Responsibility
Mechanical Maintenance……………………Tyler Turner
I/E Maintenance………………………………….Nick Payne
Engineering…………………………………………Laura Mohn
Air Heaters……………………………………...Cisco Maldonado Boilers……………………………………………..Cisco Maldonado/ Sam Bullock/ Eric Thurston High Energy Piping…………………………. Hamit Afiyet/ Matt Sanders/ Jordan Dorwart HP Heaters…………………………………….. Jordan Dorwart Condenser……………………………………… Jordan Dorwart Circulating Water Piping………………… Jordan Dorwart Cooling Tower....................................Grant Phelps/ Bob Stewart Ductwork............................................Adam Ball Turbine/ Generator……………………….. Kenny Noonan/ Nick Payne Rotating Equipment……………………….. Sam Bullock SCR………………………………………………….Jordan Dorwart DESP………………………………………………. Adam Ball PJFF (Baghouse)………………………………Haley Turner WESP……………………………………………… Logan Waller/ David Anderson FGD………………………………………………… Grant Phelps/ John Heinz Stack………………………………………………. Ryan Feider/ Sam Bullock DCS.................................................... Rick Boone/ Chris Dukes/ Matt Owens
SHUTDOWN ISSUES: Run bunkers empty………………………… (Operations- Mitch Slaughter) Run coal feeders empty…………………. (Operations- Mitch Slaughter) Turbine Cool Down…………………………. (Operations- Mitch Slaughter) APH Wash……………………………………….. (Operations- Mitch Slaughter)
SUPPORT ISSUES AND RESPONSIBILITIES:
Mobile Crane Scheduling………………………..Sam Bullock
Turbine Crane Scheduling………………………David Anderson
Electric power hookups…………………………Rick Powell/ Emmett Moore
Vac Truck & Washing……………………………Glen Hudson
HOUSEKEEPING:
Dumpster Requirements……………………. Jill Simmons
Special Waste Requirements……………… Hannah Hannon
Jobsite Cleanup……………………….……...ALL
Contractor Resources
Boiler Repairs…………………………………………..Southeast Boiler/ Alstom | Cisco Maldonado
Burner Modifications………………………………..Bechtel/ Doosan/ SE Boiler | Cisco Maldonado/ Jordan Dorwart
Turbine/ Generator Inspection………………….Kenny Noonan | Nick Payne
Scaffold & Insulation………………………………..Adam Ball/ Petrochem | Adam Ball
Pulverizers………………………………………………..PIC/ Alstom | Dale Sedam
SCR…………………………………………………………..Jordan Dorwart
PJFF…………………………………………………………..Haley Turner
DESP…………………………………………………………Adam Ball
WESP………………………………………………………..Logan Waller/ David Anderson
Vacuum & Cleaning Services……………………Glen Hudson/ Thompson

## Safety Walk-Down
Trimble 2 Spring 2014 Outage Maintenance Safety Walkdown Schedule
Expectation: meet with Dave Gilliland before and after each walkdown. Morning walkdown will be from start of business to lunch. Afternoon walkdown will be from lunch to quitting time. All walkdowns must be documented. Dave will explain documentation to each inspector. Be sure that nobody is scheduled twice to allow for maximum participation. Supervisors may swap shedules as necessary. Supervisors and are exempt from this schedule because walking down multiple jobs and ensuring safe work practices and conditions is integral to their job.
|  | Su | Mo | Tu | We | Th | Fr | Sa |  |  | Su | Mo | Tu | We | Th | Fr | Sa
February | [7 empty] | 1 | March | [7 empty] | 1
| AM | [8 empty] | AM
| PM | [8 empty] | PM
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 2 | 3 I/E Shop | 4 I/E Shop | 5 I/E Shop | 6 I/E Shop | 7 I/E Shop | 8
| AM | [8 empty] | AM
| PM | [8 empty] | PM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15
| AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech Maint. Shop | Mech. Maint. Shop |  |  | AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop
| PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop |  |  | PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop
|  | 16 | 17 I/E Shop | 18 I/E Shop | 19 I/E Shop | 20 I/E Shop | 21 I/E Shop | 22 |  |  | 16 | 17 | 18 | 19 | 20 | 21 | 22
| AM | [8 empty] | AM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop
| PM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop |  |  | PM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop
|  | 23 | 24 | 25 | 26 | 27 | 28 |  |  |  | 23 | 24 | 25 | 26 | 27 | 28 | 29
| AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech Maint. Shop | Mech. Maint. Shop |  |  | AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop
| PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop |  |  | PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop
[11 empty] | 30 | 31
[10 empty] | AM |  | I/E Shop
[10 empty] | PM |  | Mech. Maint. Shop
|  | Su | Mo | Tu | We | Th | Fr | Sa | May |  | Su | Mo | Tu | We | Th | Fr | Sa
April |  |  |  | 1 | 2 | 3 | 4 | 5 | [6 empty] | 1 | 2 | 3
| AM |  |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop |  |  | AM |  |  |  |  | I/E Shop | I/E Shop
| PM |  |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop |  |  | PM |  |  |  |  | Mech. Maint. Shop | Mech. Maint. Shop
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10
| AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop |  |  | AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop
| PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop |  |  | PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17
| AM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop |  |  | AM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop
| PM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop |  |  | PM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 |  |  | 18 | 19 | 20 | 21 | 22 | 23 | 24
| AM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop |  |  | AM
| PM |  | I/E Shop | I/E Shop | I/E Shop | I/E Shop | I/E Shop |  |  | PM
|  | 27 | 28 | 29 | 30 | [5 empty] | 25 | 26 | 27 | 28 | 29 | 30 | 31
| AM |  | I/E Shop | I/E Shop | I/E Shop |  |  |  |  | AM
| PM |  | Mech. Maint. Shop | Mech. Maint. Shop | Mech. Maint. Shop |  |  |  |  | PM
| AM | [8 empty] | AM
| PM | [8 empty] | PM

## Work Schedules
LGE-KU work groups; | Hours of Work
Mechanical Maintenance (MM) | 5x8 (Weekends as needed)
Instrument & Electrical | 5x8 (Weekends as needed)
DCS (DCS) | 5x10
PIC | 5x16 (2 shifts)
PETROCHEM | As Needed
Melvin & Sons | 7x10 elevator coverage
Guards | 7x24
Warehouse | 5x8 (Weekends as needed/ Requested)
Contractors:
Thompson | As needed
SE Boiler (Burners/ Boiler) | 7x24
(PJFF, DESP, WESP)
Traffic routes……………………………………………… | Through Guard gate 1
Foot traffic routes……………………………………….. | Through Guard gate 1
NDE requirements………………………………………

## O&M Budget
PROJECT # | Proponent | System ID | DESCRIPTION | Last Completion Date | Frequency/ Due Date | Start Date | Budget Totals 2014 | O&M Current Estimates/ Actuals | Remainder O&M Outage Funds
TC2S14OUT | Feider | Air Quality Control Systems | CEM's equipment testing and repairs. (Particulate Monitor Work) | 2014-03-01 | All Major Outages | 2014-03-17 | 0 | 35000 | -35000
TC2S14OUT | H. Turner | Air Quality Control Systems | PJFF pulse header J tube inspect for corrosion (2 sections each side) | 2013-03-01 | As Needed | Not Scheduled | 10000 | 0 | 10000
TC2S14OUT | H. Turner | Air Quality Control Systems | PJFF Inlet, Outlet & bypassdamper inspection. (some scaffold requ.) | 2013-03-01 | All Major Outages | Not Scheduled | 25000 | 25000 | 0
TC2S14OUT | Henderson | Air Quality Control Systems | PJFF Inspection/ Repairs (bag detectors, solenoids, door seals, etc…) | 2014-02-14 | All Major Outages | 2014-02-20 | 60000 | 52000 | 8000
TC2S14OUT | Waller | Air Quality Control Systems | DESP Repairs- (leaks, internal repairs, rappers/ plates) | 2013-03-01 | All Major Outages | 2014-03-17 | 50000 | 50000 | 0
TC2S14OUT | Waller | Air Quality Control Systems | DESP/ WESP Inspection by 3rd Party | 2014-02-14 | All Major Outages | 2014-02-10 | 20000 | 25500 | -5500
TC2S14OUT | Waller | Air Quality Control Systems | WESP Wash | 2013-03-01 | All Major Outages | 2014-03-17 | 100000 | 0 | 100000
TC2S14OUT | Waller | Air Quality Control Systems | WESP Repairs (Leaks/ Water Distribution) | 2013-03-01 | All Major Outages | 2014-03-17 | 50000 | 59000 | -9000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- inspection | 2014-02-14 | All Major Outages | 2014-02-18 | 150000 | 25000 | 125000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- refactory | 2014-03-01 | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- drag chain/ idlers | 2014-03-01 | As Needed | 2014-03-03 | 0 | 35000 | -35000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- Ceramic Tile | 2014-03-01 | As Needed | 2014-04-07 | 0 | 15000 | -15000
TC2S14OUT | Maldonado | Ash Handling Systems | Ash Pit Maintenance- Seal plate/ Dipper | 2014-03-01 | As Needed | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Mills | Ash Handling Systems | Ash Pit Maintenance- Cleanout doors | 2014-03-01 | 2014 | 2014-04-07 | 0 | 40000 | -40000
TC2S14OUT | Henderson | Boiler | Sootbloweer control vavles | 2014-02-14 | 2014 | 2014-03-10 | 30000 | 8000 | 22000
TC2S14OUT | Henderson | Boiler | SH Sparay Valve overhauls (4) |  | All Major Outages |  | 230000 | 0 | 230000
TC2S14OUT | Henderson | Boiler | Stage 1- "A" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | Stage 1- "B" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | Stage 2- "A" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | Stage 2- "B" | 2012-04-01 | 2 yrs | 2014-03-10 | 0 | 7000 | -7000
TC2S14OUT | Henderson | Boiler | RH Spray valve rebuild |  | All Major Outages |  | 100000 | 0 | 100000
TC2S14OUT | Henderson | Boiler | 2A | 2012-02-01 | 2 yrs | 2014-03-17 | 0 | 4000 | -4000
TC2S14OUT | Henderson | Boiler | 2B | 2012-02-01 | 2 yrs | 2014-03-17 | 0 | 4000 | -4000
TC2S14OUT | Henderson | Boiler | O2 Probes | 2013-03-01 | All Major Outages | 2014-04-14 | 0 | 2500 | -2500
TC2S14OUT | Maldonado | Boiler | Boiler Inspection Wall NDE & Wall Insp where hydrojets blow | 2013-03-01 | All Major Outages | 2014-02-24 | 75000 | 100000 | -25000
TC2S14OUT | Maldonado | Boiler | Boiler Tube Thickness Mapping/ Samples | 2013-03-01 | All Major Outages | 2014-03-03 | 50000 | 0 | 50000
TC2S14OUT | Maldonado | Boiler | Boiler Amstar coating repair/patching | 2013-03-01 | All Major Outages | 2014-05-05 | 0 | 260000 | -260000
TC2S14OUT | Maldonado | Boiler | Boiler Repairs (tubes, welds, X-rays, etc.) | 2014-02-14 | All Major Outages | 2014-03-10 | 250000 | 100000 | 150000
TC2S14OUT | Maldonado | Boiler | Boiler Leak- Existing transition header | 2014-02-14 | 2014 | 2014-02-26 | 0 | 40000 | -40000
TC2S14OUT | Maldonado | Boiler | Boiler Deslag | 2014-02-14 | As Needed | 2014-02-08 | 20000 | 12000 | 8000
TC2S14OUT | Maldonado | Boiler | Boiler Inspection Door installation | 2014-02-14 | 2014 | 2014-02-24 | 0 | 120000 | -120000
TC2S14OUT | Maldonado | Boiler | Boiler Safeties- Insp./Repairs | 2014-02-01 |  | 2014-03-24 | 0 | 15000 | -15000
TC2S14OUT | Mills | Boiler | Overhaul Hydrojet water cannons (4) | 2014-02-14 | As Needed | 2014-04-07 | 120000 | 20000 | 100000
TC2S14OUT | Mills | Boiler | Boiler Valves- Main steam line drain | 2014-02-01 | As Needed | 2014-05-05 | 0 | 30000 | -30000
| Mills | Boiler | PORV Electromatic Relief Valve repairs 2A/ 2B | 2013-03-01 | As Needed | Not Scheduled | 150000 | 0 | 150000
TC2S14OUT | Dorwart | Circulating Water | Circulating Water Line Inspection/ Repairs | 2013-03-01 | 2014-03-01 | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Henderson | Circulating Water | Cooling Tower Pump Motors |  | 2 yrs |  | 0 | 0 | 0
TC2S14OUT | Henderson | Circulating Water | 2A | 2013-03-01 | 2014 | 2014-03-31 | 0 | 1500 | -1500
TC2S14OUT | Henderson | Circulating Water | 2B | 2013-03-01 | 2014 | 2014-03-31 | 0 | 1500 | -1500
TC2S14OUT | Henderson | Circulating Water | 2C |  | 2014 | 3-34-2014 | 0 | 1500 | -1500
TC2S14OUT | Phelps/ Stewart | Circulating Water | NDCT header/seal/ fill/ Insp./ Repairs | 2013-03-01 | All Major Outages | 2014-03-24 | 10000 | 15000 | -5000
TC2S14OUT | Dorwart | Condenser | Condensor Inspection/ NDE/ Repairs | 2014-03-01 | All Major Outages | 2014-02-17 | 20000 | 15000 | 5000
TC2S14OUT | Mills | Condenser | Condenser Vacuum Pump Overhauls- casing leak |  |  |  | 0 | 0 | 0
TC2S14OUT | Mills | Condenser | 2B |  | 2 yrs | 2014-03-24 | 0 | 17000 | -17000
TC2S14OUT | Bullock | Draft Equipment | Chimney flue inspection | 2014-03-01 | All Major Outages | 2014-03-17 | 30000 | 59000 | -29000
TC2S14OUT | Dorwart | Draft Equipment | Expansion Joint Repair and Shields | 2014-04-01 | All Major Outages | 2014-04-07 | 250000 | 75000 | 175000
TC2S14OUT | Dorwart | Draft Equipment | Duct work- Inspections & Repairs- PA, SA, AH--out. | 2014-02-01 | All Major Outages | 2014-04-07 | 300000 | 150000 | 150000
TC2S14OUT | Henderson | Draft Equipment | ID Fan Motor Inspection | 2013-03-01 | All Major Outages | 2014-03-24 | 35000 | 15000 | 20000
TC2S14OUT | Henderson | Draft Equipment | FD Fan Motor Inspections | 2014-03-01 | All Major Outages | 2014-03-24 | 50000 | 5000 | 45000
TC2S14OUT | Hudson | Draft Equipment | Air Heater Wash | 2014-04-01 | Annually | 2014-05-05 | 40000 | 30000 | 10000
TC2S14OUT | Maldonado | Draft Equipment | Air Heater Repairs/ Inspection | 2014-03-01 | All Major Outages | 2014-03-03 | 25000 | 15000 | 10000
TC2S14OUT | Mills | Draft Equipment | Fan Inspections/ Cleaning (Serviceman/Blades) ID,FD,PA | 2014-03-01 | All Major Outages | 2014-02-24 | 40000 | 102000 | -62000
TC2S14OUT | Sedam | Draft Equipment | ID Fan - Install Spare Hub (1) | 2014-03-01 | 2014 | 2014-03-17 | 0 | 361000 | -361000
TC2S14OUT | Sedam | Draft Equipment | FD Fan Rebuild Hub/fan (2) | 2014-03-01 | 2014 | 2014-03-03 | 0 | 97000 | -97000
TC2S14OUT | Sedam | Draft Equipment | FD Fan Hydraulic Cylinder Rebuild |  |  | 2014-03-03 | 0 | 18500 | -18500
TC2S14OUT | Henderson | Electrical | Temporary Power |  | All Major Outages |  | 0 | 5000 | -5000
TC2S14OUT | Payne | Electrical | Switchgear Maintenance | 2012-04-01 | 2 yrs | Not Scheduled | 50000 | 0 | 50000
| Bullock | Feedwater Systems | BFP Booster Pump overhauls/ inspections |  | As Needed | Not Scheduled | 0 | 0 | 0
TC2S14OUT | Mills | Feedwater Systems | 2B- mechanical seal | 2014-03-01 | As Needed | 2014-02-24 | 0 | 6000 | -6000
TC2S14OUT | Bullock | Feedwater Systems | Move Spare BCP | 2014-03-01 | 2014 | 2014-03-24 | 0 | 25000 | -25000
| Dorwart | Feedwater Systems | BCP Overhauls/ Thrust Inspection | 2014-03-01 | As Needed | 2014-02-24 | 0 | 40000 | -40000
TC2S14OUT | Dorwart | Feedwater Systems | Deaerator NDE | 2014-02-01 | All Major Outages | 2014-02-24 | 23000 | 50000 | -27000
TC2S14OUT | Henderson | Feedwater Systems | BFP Recirc Valve Overhauls- |  | As Needed | Completed | 150000 | 0 | 150000
TC2S14OUT | Henderson | Feedwater Systems | 2A | 2014-02-01 |  | 2014-02-24 | 0 | 32000 | -32000
TC2S14OUT | Henderson | Feedwater Systems | MBBFP motor inspection | 2013-03-01 | 2 yrs | 2014-03-01 | 25000 | 0 | 25000
TC2S14OUT | Mills | Feedwater Systems | Valve Inspections |  | All Major Outages | 2014-02-10 | 60000 | 40000 | 20000
TC2S14OUT | Mills | Feedwater Systems | Safeties- Testing & Repairs | 2014-02-01 | All Major Outages | 2014-03-24 | 40000 | 15000 | 25000
TC2S14OUT | Mills | Feedwater Systems | BCP recirc & HP/LP bypass valve pull & Insp. |  | 2014 | 2014-04-14 | 25000 | 37000 | -12000
TC2S14OUT | Mills | Feedwater Systems | Feedwater Heater Diaphragms | 2014-03-01 | As Needed | 2014-02-17 | 0 | 15000 | -15000
TC2S14OUT | Mills | Feedwater Systems | 2B TDBFP Booster Pump Mechanical Seal Leaking | 2014-03-01 | 2014 | 2014-04-07 | 0 | 6000 | -6000
TC2S14OUT | Henderson | FGD | Recycle Pump motor oil change | 2014-04-01 | All Major Outages | 2014-03-01 | 0 | 1200 | -1200
TC2S14OUT | Mills | FGD | Recycle Pump seal water line. | 2014-03-01 | 2014 | 2014-04-07 | 0 | 1000 | -1000
TC2S14OUT | Mills | FGD | Recycle Pump Disch./ Inlet Valves | 2014-04-01 |  | 2014-03-17 | 0 | 100000 | -100000
| Phelps/ Moore | FGD | Reaction Tank full range level indication. |  | 2014 |  | 0 | 11000 | -11000
TC2S14OUT | Phelps | FGD | FGD Reactant Tank Cleanout/Inspect, Nozzle repairs (incr. $75K) | 2014-03-01 | All Major Outages | 2014-03-10 | 75000 | 6000 | 69000
TC2S14OUT | Phelps | FGD | FGD Inspections- Inlet, Module, agitator, mist eliminators, nozzle & trays | 2014-02-01 | All Major Outages | 2014-03-10 | 0 | 15000 | -15000
TC2S14OUT | Phelps | FGD | Repair Reaction Tank Agitater Blades |  | As Needed | 2014-03-17 | 100000 | 25000 | 75000
TC2S14OUT | Phelps | FGD | TC2 Gypsum Line | 2014-03-01 | 2014 | 2014-02-24 | 0 | 6000 | -6000
TC2S14OUT | Dorwart | High Energy Piping | HEP piping and hanger repairs from inspections | 2014-03-01 | 2 yrs. Or All Major Outages | 2014-03-03 | 150000 | 15000 | 135000
TC2S14OUT | Dorwart | Material Handling | Reactant Prep "A" Ball mill gearbox changeout. | 2014-04-01 | 2014 | 2014-03-17 | 0 | 90000 | -90000
TC2S14OUT | Osgood | Material Handling | Overhaul & Clean A/ B Ball Mill Motor |  | As Needed | Completed | 25000 | 0 | 25000
TC2S14OUT | Ball | Misc/ Common | Scaffolding |  | All Major Outages | Spread | 100000 | 0 | 100000
TC2S14OUT | Bullock | Misc/ Common | Elevator Operators/ Maintenance |  | All Major Outages | Spread | 0 | 35000 | -35000
TC2S14OUT | Henderson | Misc/ Common | Instrument Air Compressor Motor Overhaul |  | 2014 | 2014-04-07 | 24000 | 0 | 24000
TC2S14OUT | Henderson | Misc/ Common | 2A & 2B Inst. Air Dryers | 2014-04-01 | As Needed | 2014-04-07 | 0 | 6000 | -6000
TC2S14OUT | Hudson | Misc/ Common | Industrial Cleaning |  | All Major Outages | Spread | 200000 | 210000 | -10000
TC2S14OUT | Misc. | Misc/ Common | T&M add on work. |  | All Major Outages | Spread | 0 | 50000 | -50000
TC2S14OUT | Misc. | Misc/ Common | Service Reps- Alstom, Howden, MD&A, Diamond Power) |  | All Major Outages |  | 150000 | 0 | 150000
TC2S14OUT | Misc. | Misc/ Common | TC2 Platform additions | 2014-04-01 | 2014 | 2014-03-17 | 0 | 100000 | -100000
TC2S14OUT | Slaughter | Misc/ Common | inspect for leakage. (Air-in)? | 2014-01-01 | All Major Outages | Completed | 25000 | 0 | 25000
TC2S14OUT | Henderson | Pulverizers | Pulverizer Inerting steam valves | 2014-04-01 | 2014 | 2014-03-17 | 0 | 30000 | -30000
TC2S14OUT | Henderson | Pulverizers | Pulverizer 2D Classifier Motor | 2014-04-01 | 2014 | 2014-02-24 | 0 | 1500 | -1500
TC2S14OUT | Henderson | Pulverizers | PA Fan Motor Inspections | 2014-03-01 | All Major Outages | 2014-03-24 | 0 | 5000 | -5000
TC2S14OUT | Mills | Pulverizers | Mill Expansion Joints | 2014-04-01 | 2014 | 2014-03-03 | 0 | 20000 | -20000
TC2S14OUT | Mills/ Henderson | Pulverizers | PA Fan - Inspect bearings and input damper linkage | 2014-04-01 | 2014 | 2014-04-07 | 25000 | 0 | 25000
TC2S14OUT | Sedam | Pulverizers | Pulverizer Inspections | 2014-03-01 | All Major Outages | 2014-03-03 | 0 | 13500 | -13500
TC2S14OUT | Sedam | Pulverizers | Pulverizer Overhauls- 2A & 2D | 2014-04-01 | 2014 | 2014-03-10 | 0 | 35000 | -35000
TC2S14OUT | Sedam | Pulverizers | Pulverizer- Floor weld overlay | 2014-04-01 | 2014 | 2014-03-17 | 0 | 122000 | -122000
TC2S14OUT | Dorwart | SCR | Vacuum & Inspect SCR catalyst (increased $135K) | 2014-02-01 | All Major Outages | 2014-02-10 | 75000 | 10000 | 65000
TC2S14OUT | Henderson | SCR | NH3 detectors | 2014-04-01 | All Major Outages | 2014-04-14 | 0 | 3300 | -3300
TC2S14OUT | Mills | SCR | Safety Relief Valve Replacements |  | 4 yrs | 2014-04-21 | 0 | 40000 | -40000
TC2S14OUT | Mills | Turbine/ Generator | 2A Turbine oil cooler clean | 2014-02-01 | 2014 | 2014-03-10 | 0 | 35000 | -35000
TC2S14OUT | Noonan | Turbine/ Generator | Main Turbine LP Blade Inspect | 2014-04-01 | 4yrs | 2014-03-24 | 60000 | 10000 | 50000
| Noonan | Turbine/ Generator | Turbine Extraction Steam Check Valves Overhaul- 2016 |  | 2016 | Not Scheduled | 30000 | 0 | 30000
TC2S14OUT | Dorwart | Turbine/ Generator | Hot Reheat Turbine bypass valve flange pipe replacement | 2014-04-14 |  | 2014-04-24 | 0 | 350000 | -350000
TC2S14OUT | Noonan | Turbine/ Generator | TC2 Turbine/ Generator #11 Bearing leak | 2014-04-01 | 2014 | 2014-03-24 | 0 | 5000 | -5000
TC2S14OUT | Payne | Turbine/ Generator | Generator Maintenance |  | All Major Outages | 2014-02-24 | 0 | 2000 | -2000
TC2S14OUT | Payne | Turbine/ Generator | Generator Lead Box Inspection/ Repairs | 2014-03-01 | All Major Outages | 2014-03-10 | 0 | 0 | 0
| T. Turner | Turbine/ Generator | Turbine Oil 3-way Valve | 2014-03-01 | As Needed | 2014-03-17 | 0 | 15000 | -15000
|  |  | TOTALS |  |  |  | 3702000 | 3823500 | -121500

## B&V Work Orders
Work Order | Description | Status | Reported Date | Location | Outage ID | Priority | Project | Crew
6466288 | TC2 Turbine Cap vibration 11Y is reading erratically | RMAT | 6/11/13 5:55 AM | TC002TA-TSIXIC | TC2S14 | OUTAGE | TC2S14OUT | TCMSL2
6535543 | Instrument ID 2ESPT307 Calibrate extraction steam pressure transmitter | WOUT | 1/20/14 11:17 AM | TC002CNDCNHMOV315 | TC2S14 | OUTAGE | TC2S14OUT | TCMSL2
6535545 | LP Condenser Shell Pressure Measurement Instrument ID 2CDPT010A ¿ Bad Output and higher than exp | WOUT | 1/20/14 11:20 AM | TC002TA-CONXIC | TC2S14 | OUTAGE | TC2S14OUT | TCMSL2
6542950 | Inspect TC2 1A LP Heater normal drain valve for pluggage | INPRG | 2/13/14 6:21 AM | TC002CNDCNHCV101AA | TC2S14 | OUTAGE | TC2S14OUT | TCMSL2
6542953 | 2F Mill RTD-C1 motor stator temp reading low tag-ID D-2FC001F-STMPCA | WOUT | 2/13/14 6:27 AM | TC002PFCPULF-MTR | TC2S14 | OUTAGE | TC2S14OUT | TCMSL2
6542954 | TC2 Heater 3 extraction steam pressure (2ESPT307) reading high | INPRG | 2/13/14 6:32 AM | TC002CNDCNHXIC | TC2S14 | OUTAGE | TC2S14OUT | TCMSL2

## CO Work Orders
Resource/ Crew | Plant Proponent | Work Order | Location | Activity / Task Name | Percent Complete | (C)- Capital (O)- O&M | Invoice Month | O&M Budget | O&M Current Estimates | O&M Unplanned Additional Expenses | O&M Actual Cost | Capital Budget | Capital Current Estimates | Capital Unplanned Additional Expenses | Days | Start Date | Finish Date | 2014-02-01 | [6 empty] | 2014-02-08 | [6 empty] | 2014-02-15 | [6 empty] | 2014-02-22 | [6 empty] | 2014-03-01 | [6 empty] | 2014-03-08 | [6 empty] | 2014-03-15 | [6 empty] | 2014-03-22 | [6 empty] | 2014-03-29 | [6 empty] | 2014-04-05 | [6 empty] | 2014-04-12 | [6 empty] | 2014-04-19 | [6 empty] | 2014-04-26 | [6 empty] | 2014-05-03 | [6 empty] | 2014-05-10 | [6 empty] | 2014-05-17 | [6 empty] | 2014-05-24
|  |  | TC000AC-- AUX COOLING | [10 empty] | #REF! | time axis 2014-02-01 to 2014-05-30
|  |  | TC000AH- ASH HANDLING |  | 100% | time axis 2014-02-01 to 2014-05-30
Budget |  |  |  | Ash Pit Maintenance- refactory, drag chain, Ceramic Tile (incr $70K) |  | O |  | 150000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6535461 | TC002AH-BACSCRAXXX | Install basalt tile on TC2 SSC. | 100% | O | Apr. |  | 10000 |  | 9604 |  |  |  |  | 2014-02-24 | 2014-02-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6522371 | TC002AH-BACSCRAXXX | Submerged Scraper Conveyer inspection and Mat'l Analysis | 100% | O | Apr. |  | 15000 |  | 1647 |  |  |  |  | 2014-02-18 | 2014-02-20
TCMSL2 | Powell/ Henderson | 6536046 | TC002AH-BACSCRAXIC | TC-2 Bottom Ash Submerged Scraper Conveyer Chain Tensioner west Press regulator needs adjusted. | 100% | O | [9 empty] | 2014-03-24 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6541411 | TC002AH-BACSCRAPCNV | Remove S.S.C | 100% | O |  |  |  |  | 1351
TCMSL6 | Jensen/ Mills | 6534349 | TC002AH-BACHYDPPG | Replace the hoses on the S.S.C. planetary gear reducer. | 100% | O | [9 empty] | 2014-02-18 | 2014-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6545135 | TC002AH-BACSCRAPCNV | Replace 3 idler wheels on the S.S.C. | 100% | O
TCMSL6 | Jensen/ Mills | 6534352 | TC002AH-BACSCRAXXX | Add safety guide to the top of the bunker rail to prevent rollers from rolling off rail. |  | O |  |  |  |  | 755 |  |  |  |  | 2014-02-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6554752 | TC002AH-BACVLVXXX | Add 2 four inch drain valves to the east side of the S.S.C. |  | O
TCMSL6 | Jensen/ Mills | 6508200 | TC000AH-CASCOMP-A | 0A Flyash convey air compressor overheated and needs to be inspected. | 100% | O |  |  |  |  | 117204
TCMSL6 | Jensen/ Mills | 6540983 | TC002AH-PYR2A-HPR | Replace TC2 pyrite hopper observation windows. All hoppers. | 100% | O |  |  |  |  | 1048 |  |  |  |  | 2014-03-21 | 2014-03-21
TCMSL6 | Jensen/ Mills | 6475590 | TC000AH-SILVLV | Install Flyash Silo Inst Air Supply bypass vlv around the dryers.Per M. Slaughter | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6497479 | TC000AH-SILVLV | unit1 flyash transfer hopper lower equalizing valve cv-568B needs mechanical troubleshoot and repair | 100% | O |  |  |  |  | 5222 |  |  |  |  | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6473892 | TC000AH-UNLWETVLVXXX | air operated fly ash valve will not open on the "C" fly ash rotary feeder | 100% | O |  |  | 20000 |  | 24812 |  |  |  |  | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6546799 | TC002AH-BACSCRAXXX | Replace chain on TC2 SSC. | 100% | O |  |  |  |  | 63612 |  |  |  |  | 2014-03-04 | 2014-03-21
TCMSL2 | Powell/ Henderson | 6483891 | TC002AH-HOPECONXIC | Move Econ. hopper actuator solenoid buttons to east side of hopper piping for safety reasons. Also n | 100% | O |  |  |  |  | 856 |  |  |  |  | 2014-03-15 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC000CH- Coal Handling |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENG | Moore |  |  | TC Replace Coal Stacker/ Reclaimer Cables | 100% | C | [5 empty] | 206838 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL1 | Stivers | 6444193 | TC000CHGSRCXXX | Change cables and tray on Coal Stacker Reclaimer | 100% | C | May | [5 empty] | 23106
|  |  | TC000RS- Reactant Supply |  | 100% | [10 empty] | 1900-01-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Overhaul & Clean A Ball Mill Motor | 100% | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Phelps |  |  | TC2 LST Pumps- Backup- Outage portion completed. | 100% | C | [5 empty] | 101911 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6532525 | TC000RS-MILA--GEARBOX | Reactant Prep - A Ball Mill Gearbox Changeout- (bids due 3/11) | 50% | O | Apr. |  | 90000 |  | 396 |  |  |  |  | 2014-04-21 | 2014-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002AS- AUX STEAM |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6508185 | TC002AS-HTRXIC | 2 AS-PT-018 has a fitting leaking steam at the electric superehater for auxilary steam | 100% | O |  |  |  |  | 112 |  |  |  |  | 2014-03-15 | 2014-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002BL- BOILER |  | 96.59% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Boiler Inspection Wall NDE & Wall Insp where hydrojets blow |  | O |  | 75000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Reset safeties |  | O |  | 40000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Deslag |  | O |  | 20000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Valve Inspections |  | O |  | 60000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | SH Sparay Valve overhauls (4) (increased $230K) |  | O |  | 230000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | RH Spray valve rebuild |  | O |  | 100000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | PORV Electromatic Relief Valve (2) |  | O |  | 150000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Sootblower control vavles |  | O |  | 30000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Overhaul Hydrojet water cannons (4) |  | O |  | 120000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Expansion Joint Repair and Shields |  | O |  | 250000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Duct work |  | O |  | 300000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Deaerator NDE |  | O |  | 23000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Boiler Tube Thickness Mapping |  | O |  | 50000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Boiler Repairs (tubes, welds, etc.) |  | O |  | 250000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | HEP piping and hanger repairs from inspections |  | O |  | 150000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6532040 | TC002BL-BCWPMP | TC2 BCP - Thrust Inspection | 100% | O | Apr. |  | 30000 |  | 9377 |  |  |  |  | 2014-04-08 | 2014-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | TC2 Boiler Roof Tube Issues |  | C | [5 empty] | 1189332 |  |  |  | 2014-02-24 | 2014-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6532526 | TC002BL-FRNXXX | TC2 CO Monitor System | 50% | C | [5 empty] | 715869 | 150000 |  |  | 2014-02-17 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado |  |  | TC2 Pegging Steam Supply |  | C | [5 empty] | 76433 |  | 124000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6535458 | TC002BL-FRNXXX | TC2 boiler inspections and punchlist repairs resulting from inspections. | 100% | C | Apr./ May |  | 100000 |  | 29137 |  |  |  |  | 2014-02-24 | 2014-02-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6535695 | TC002BL-FRNXXX | External boiler leak Unit 2 10th landing southwest corner at spiral to vertical transtion zone. | 100% | O | Mar. |  | 5000 | [6 empty] | 2014-02-03 | 2014-02-03 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6550776 | TC002BL-HRH2A-CV116A | TC2 HRH CV-116A/B Desuperheater, Expander Replacement | 100% | O | Apr. |  | 350000 |  | 134339 |  |  |  |  | 2014-03-24
TCBW | Dearman/ Craft | 6496138 | TC002BL-MS-2B-CV020B | 2-TDR-CV-020B is leaking at the body gasket. This valve's body gasket has been replaced in the past. |  | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6544965 | TC002BL-MS-PPG | TC2 High Energy Piping Repairs Post Inspection | 100% | O |  |  | 10000 |  | 4070
TCMSL2 | Powell/ Henderson | 6557815 | TC002BL-MS-2A-CV020A | Unwire and remove air line from 2-TDR-CV-020A | 100% | O
TCMSL2 | Powell/ Henderson | 6557819 | TC002BL-MS-2B-CV020B | Unwire and remove air line from 2-TDR-CV-020B | 100% | O
TCMSL2 | Powell/ Henderson | 6530119 | TC002BL-MS-XIC | PM-ANNUAL-OUTAGE- Boiler instrumentation loop checks. | 100% | O | [9 empty] | 2014-02-17 | 2014-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | " | " | Doosan Instrument Checks- 5 pt checks (See List- Green) | 100%
TCMSL2 | Powell/ Henderson | " | " | Doosan Instrument Checks- 3 pt checks (See List- Yellow) | 100%
TCMSL2 | Powell/ Henderson | " | " | Re-range OFA transmitters and 3 pt. check. (See List- Yellow) | 100%
TCMC | Bullock | 6540329 | TC002BL-FRNXXX | TC2 Boiler Deslag Spring 2014. | 100% | O | Feb. |  | 50000 |  | 11853
TCMC | Bullock | 6478797 | TC002BL-FRNXXX | During the Spring 2013 TC2 Outage, repairs were made to the membrane along the line where the undern (Insp./ Repairs) | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMC | Bullock | 6532422 | TC002BL-BCWPMP | While SEB is on site for the Unit 2 outage, move spare BCWP (Unit 2) to landing below Pump (See S. | 0% | O
TCMSL2 | Powell/ Henderson | 6467252 | TC002BL-FRNXXX | 2-BLS-PT-136 Spiral Tube Outlet Header pressure transmitter is leaking at the compression fitting | 100% | O | [9 empty] | 2014-02-10 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530117 | TC002BL-RH-2A-CV130A | PM-ANNUAL-OUTAGE- "A" Reheat Spray Water Control Valve 2-AT CV-130A. Check calibration, stroke | 100% | O | Mar. |  | 4000 |  | 28306 |  |  |  |  | 2014-03-10 | 2014-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530118 | TC002BL-RH-2B-CV130B | PM-ANNUAL-OUTAGE- "B" Reheat Spray Water Control Valve 2-AT CV-130B. Check calibration, stroke | 100% | O | Mar. |  | 4000 | [6 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6541707 | TC002BL-SBLHJ4-SAFAN | Please inspect the 2C hydrojet seal air motor during outage. Makes High pitched winding sound. | 100% | O | [9 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6544558 | TC002BL-SBLHJ1-XIC | Zone 24 and Zone 18 Heat Flux TC's reading low Inspect and repair if needed | 100% | O | [9 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6536553 | TC002BL-SBLHJCV521 | Pull and inspect the Hydrojet control valve. 2-SB-CV-521 | 100% | O |  |  |  |  | 896 |  |  |  |  | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6531312 | TC002BL-MS-VLVXXX | 2-TDR-CV-019A & B main steam line drain valve is leaking, needs repaired | 100% | O | Apr. |  | 30000 | [6 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6551180 | TC002BL-MS-2A-CV020A | 2-TDR-CV-020A Leaking at Body Gasket--This valve was temporarily repaired by LGE-VT during a weekend | 100% | O
TCMSL6 | Jensen/ Mills | 6554746 | TC002BL-SBLHJ1 | Inspect and repair all 4 TC2 water cannon | 100% | O |  |  | 31000 |  | 18639
TCMSL6 | Jensen/ Mills | 6494158 | TC002BL-SBLMOV500 | Inspect the gearbox on the sootblower main steam supply valve MOV 500 | 100% | O |  |  |  |  | 1316 |  |  |  |  | 2014-02-14 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535846 | TC002BL-SBL2A-MOV516A | 2-SB-516A AH sootblower air supply MOV has steam leaking around vlv | 100% | O
TCMSL6 | Jensen/ Mills | 6541045 | TC002BL-SBLPLATSH018 | unit 2 IK18 sootblower packing is leaking | 100% | O
TCMSL6 | Jensen/ Mills | 6554756 | TC002BL-SH-PSV907 | Repair TC2 Superheat Safety 907 drain valve | 100% | O
TCMSLENGMECH | Maldonado | 6533702 | TC002BL-SH-XXX | Pretest safety valves and repair valves as needed during outage. | 100% | O | Feb./ Mar. |  | 15000 |  | 27361 |  |  |  |  | 2014-01-30 | 2014-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6539280 | TC002BL-SH-XXX | check accuracy of transmiters2 BLSPT136,It reads 309 PSI then | 100% | O | [9 empty] | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530114 | TC002BL-SH-VLVXXX | PM-ANNUAL-OUTAGE- STAGE 1 "B" SH Spray Water Control Valve 2-AT CV-110B. Check calibration, stroke | 100% | O | Mar. |  | 7000 | [6 empty] | 2014-03-10 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530113 | TC002BL-SH-VLVXXX | PM-ANNUAL-OUTAGE- STAGE 1 "A" SH Spray Water Control Valve 2-AT CV-110A. Check calibration, stroke | 100% | O | Mar. |  | 7000 |  | 30 |  |  |  |  | 2014-03-10 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530115 | TC002BL-SH-VLVXXX | PM-ANNUAL-OUTAGE- STAGE 2 "A" SH Spray Water Control Valve 2-AT CV-120A. Check calibration, stroke | 100% | O | Mar. |  | 7000 |  | 8730 |  |  |  |  | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530116 | TC002BL-SH-VLVXXX | PM-ANNUAL-OUTAGE- STAGE 2 "B" SH Spray Water Control Valve 2-AT CV-120B. Check calibration, stroke | 100% | O | Mar. |  | 7000 |  | 8727 |  |  |  |  | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6520711 | TC002BL-SH-2A-CV902A | Replace the 2A Electromatic manual isolation valve gearbox. | 100% | O |  |  |  |  | 2401 |  |  |  |  | 2014-02-14 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535744 | TC002BL-SH-PSV904 | TC2 main steam safety PSV 904 is leaking through | 100% | O | [9 empty] | 2014-02-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6491865 | TC002BL-DRNVLVXXX | The Boiler drains recovery vessel manual level control valve has a packing leak. Please I/R. | 100% | O |  |  | 5200 |  | 9743 |  |  |  |  | 2014-02-18 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6542978 | TC002BL-DORXXX | Install refractory on new inspection doors and repair refractory on existing platform doors. | 100% | O |  |  |  |  | 38017 |  |  |  |  | 2014-03-17 | 2014-03-20
TCMSLENGMECH | Maldonado | 6501870 | TC002BL-FRNXXX | TC2 Ashpit Refractory--Inspect refractory and make any needed repairs. | 100% | O |  |  |  |  | 43218 |  |  |  |  | 2014-02-17 | 2014-02-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6542995 | TC002BL-FRNXXX | NDE on balancing/mising header welds on TC2. Repair as needed. | 100% | O | [9 empty] | 2014-02-19 | 2014-02-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6414714 | TC002BL-FRNXXX | Following four (4) events in which a total of nine (9) boiler roof tubes failed, LG&E arranged for m | 100% | C | May/ Jun. |  |  |  | 0 |  | 1190000 |  |  | 2014-02-24 | 2014-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530364 | TC002BL-SBLCV050 | Inspect the TC2 Sootblower control valve. 2-SB-CV-050 | 100% | O | Mar. |  | 8000 |  | 1556 |  |  |  |  | 2014-03-10 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6521228 | TC002BL-FRNXXX | Boiler inspection doors installation | 100% | O | Apr./ May |  | 60000 |  | 140117 |  |  |  |  | 2014-02-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart/ Hamit |  |  | HEP Inspections | 100% | O | Apr. | [8 empty] | 2014-01-20 | 2014-03-13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CA- COMPRESSED AIR |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Instrument Air Compressor Motor Overaul |  | O |  | 24000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6531289 | TC002CA-IAE2A-AIRDRYER | 2A Instr. Air Dryer- Rebuild acutators and check desicant level. | 100% | O | Mar. |  | 3000 | [6 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6531290 | TC002CA-IAE2B-AIRDRYER | 2B Instr. Air Dryer- Rebuild acutators and check desicant level. | 100% | O | Mar. |  | 3000 | [6 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6538904 | TC002CA-IAEPPG | Instrument air line on the mez south of essential switchgear room is broken | 100% | O |  |  |  |  | 1074
TCMSL6 | Jensen/ Mills | 6535519 | TC002CA-HAE | PM-ANNUAL - & - 2B HOUSE AIR COMPRESSOR - | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535518 | TC002CA-HAE | PM-ANNUAL - & - 2A HOUSE AIR COMPRESSOR - | 100% | O |  |  | 30000 | [6 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6563827 | TC002CA-HAE2A-COMPRESS | The 2A & 2B house air compressor HP element needs replaced | 100% | O
TCMSL6 | Jensen/ Mills | 6535520 | TC002CA-IAE2A-COMPRESS | PM-OUTAGE-ANNUAL - & - 2A INSTRUMENT AIR COMPRESSOR PM - | 100% | O |  |  | 32000 | [6 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535521 | TC002CA-IAE2B-COMPRESS | PM-OUTAGE-ANNUAL - & - 2B INSTRUMENT AIR COMPRESSOR PM - | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CAE- CONTROL AND EMERGENCY DC | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CBA- COMBUSTION AIR |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | AH Wash |  | O |  | 40000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | inspect for leakage. |  | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Air Heater Repairs |  | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | FD & PA Fan Motor Inspections |  | O |  | 50000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Maldonado | 6535456 | TC002CBAAHTXXX | TC2 Air Heater inspections and repairs. | 100% | O | Mar. |  | 4000 |  | 15625 |  |  |  |  | 2014-02-17 | 2014-02-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCBW | Dearman/ Craft | 6412361 | TC002CBAWAHXXX | The present state of the Water Coil Air Heaters (WCAH) system on TC2 needs to be corrected. While L | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCBW | Dearman/ Craft | 6430848 | TC002CBASLA2A-MILSABFAN | Either the 2A or 2B Mill Seal Air Fan is turning backwards when the alternating fan is in service. L | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530120 | TC002CBAFD-2A-FANMTR | PM-ANNUAL-OUTAGE- TC2 "A" FD Fan motor bearings- change oil, clean and inspect motor | 100% | O | Mar. |  | 6000 | [6 empty] | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530122 | TC002CBAFD-2B-FANMTR | PM-ANNUAL-OUTAGE- TC2 "B" FD Fan motor bearings- change oil, clean and inspect motor | 100% | O | [9 empty] | 2014-03-03 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6479417 | TC002CBAFD-2A-DMPCD020A | Check the calibration of the 2A FD Fan blade actuator and its associated linkages. | 100% | O | [9 empty] | 2014-03-03 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6500675 | TC002CBAFD-2A-FANMTR | Check out and repair the RTD on 2A FD fan Stator B1 showing -51 | 100% | O | [9 empty] | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6479419 | TC002CBAFD-2B-DMPCD020B | Check the calibration of the 2B FD Fan blade actuator and its associated linkages. | 100% | O | [9 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535967 | TC002CBADMPXXX | Replace all linkage arm nuts with lock nuts or apply loctite on all TC2 burner windbox dampers | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6539207 | TC002CBAAHT2AA-RDRVCLUTCH | PM-OUTAGE - & - 2A1 AIR HEATER CLUTCH OIL CHANGE | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539208 | TC002CBAAHT2AB-RDRVCLUTCH | PM-OUTAGE - & - 2A2 AIR HEATER CLUTCH OIL CHANGE | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539205 | TC002CBAAHT2A-RDRVGB | PM-OUTAGE-6 MONTH PM- 2A AIR HEATER GEARBOX OIL CHANGE | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539209 | TC002CBAAHT2BA-RDRVCLUTCH | PM-OUTAGE - & - 2B1 AIR HEATER CLUTCH OIL CHANGE | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539210 | TC002CBAAHT2BB-RDRVCLUTCH | PM-OUTAGE - & - 2B2 AIR HEATER CLUTCH OIL CHANGE | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539206 | TC002CBAAHT2B-RDRVGB | PM-OUTAGE-6 MONTH PM- 2B AIR HEATER GEARBOX OIL CHANGE | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539220 | TC002CBAFD-2A-FAN | PM-OUTAGE - & - 2A F.D. FAN BRAKE INSPECT | 100% | O | [9 empty] | 2014-03-08 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539203 | TC002CBAFD-2A-FAN | PM-OUTAGE-ANNUAL - & - 2A F.D. FAN VISUAL INSPECTION | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539229 | TC002CBAFD-2A-FAN | PM-OUTAGE - & - SCAN I.D. & F.D. FAN BLADES | 100% | O | [9 empty] | 2014-02-24 | 2014-03-21
TCMSL6 | Jensen/ Mills | 6539221 | TC002CBAFD-2B-FAN | PM-OUTAGE - & - 2B F.D. FAN BRAKE INSPECT | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6547567 | TC002CBAFD-2B-FAN | Change out 2B FD Fan blade hub. | 100% | O |  |  | 53000 |  | 5457 |  |  |  |  | 2014-02-24 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539204 | TC002CBAFD-2B-FAN | PM-OUTAGE-ANNUAL - & - 2B F.D. FAN VISUAL INSPECTION | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSLENGMECH | Dorwart | 6552384 | TC002CBADCTXXX | TC2 Ductwork and Expansion Joint Repair/Replacement work | 100% | O |  |  | 75000 |  | 19337 |  |  |  |  | 2014-03-24
|  |  |  | Fan Inspections | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Ductwork inspections | 100% | O |  |  |  |  | 1558 |  |  |  |  | 2014-02-24 | 2014-03-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CCW- CLOSED COOLING WATER |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530238 | TC002CCWPMP2A-PMPMTR | Change oil in the 2A & 2B Closed Cooling pump motors. GST 68 | 100% | O |  |  | 400 | [6 empty] | 2014-04-17 | 2014-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6554464 | TC002CCWCLR2A-HEATEXCH | Remove the closed cooling heat exchanger heads for cleaning | 100% | O
|  |  | TC002CI- ACTIVATED CARBON INJECTION | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CND- CONDENSATE |  | 95.24% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Condensor NDE Repair |  | O |  | 20000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530123 | TC002CNDCNP2A-PMPMTR | PM-ANNUAL - & - TC2 "A" Condensate Hotwell Pump motor clean, inspect & bearings oil change. | 100% | O |  |  | 800 | [6 empty] | 2014-04-07 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530124 | TC002CNDCNP2B-PMPMTR | PM-ANNUAL - & - TC2 "B" Condensate Hotwell Pump motor clean, inspect & bearings oil change. | 100% | O |  |  | 800 | [6 empty] | 2014-04-07 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530125 | TC002CNDCNP2C-PMPMTR | PM-ANNUAL - & - TC2 "C" Condensate Hotwell Pump motor clean, inspect & bearings oil change. | 100% | O |  |  | 800 | [6 empty] | 2014-04-07 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6535543 | TC002CNDCNHMOV315 | Instrument ID 2ESPT307 Calibrate extraction steam pressure transmitter | 100% | O | [9 empty] | 2014-02-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6534397 | TC002CNDCNHXXX | Inspect yellow cables on all of the K-Tecs on heaters | 100% | O | Mar. |  | 1000 | [6 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6542950 | TC002CNDCNHCV101AA | Inspect TC2 1A LP Heater normal drain valve for pluggage | 100% | O | [9 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6542954 | TC002CNDCNHXIC | TC2 Heater 3 extraction steam pressure (2ESPT307) reading high | 100% | O | [9 empty] | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6452229 | TC002CNDCNHM0V548A | Replace upper flange on 2A codensate heater MOV 2-CD-MOV 546 A | 100% | O |  |  |  |  | 662 |  |  |  |  | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6495803 | TC002CNDCNHMOV415 | Condensate heater #4 extraction steam isolation valve 2-ES-MOV-415 is leaking through aftre closing. | 100% | O |  |  |  |  | 39 |  |  |  |  | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6495897 | TC002CNDCNHVLVXXX | TC2 condensate heater 4 channel side relief valve was blowing hot water from under the insulation. | 100% | O |  |  |  |  | 1091 |  |  |  |  | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6544705 | TC002CNDCNPVLVXXX | Repack "A" hotwell pump By-Pass discharge valve | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6535704 | TC002CNDCNPXXX | 2A HWP dischagre vlv bypass vlv packing is leaking 2-CD-V072 | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6544285 | TC002CNDCNPXXX | remove grating and place a ladder for access to the 2A hotwell pump suction strainer drain vlv. | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6536625 | TC002CNDDEAXXX | TC2 Deaerator - Open Doors on heater and storage tank, both ends | 100% | O | [9 empty] | 2014-02-15 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6535743 | TC002CNDDEAXXX | TC2 DA startup vent vlv V089 leaking through | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6535739 | TC002CNDDEAXXX | TC2 DA operating vent MOV 544 leaking through | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSLENGMECH | Dorwart | 6538152 | TC002CNDPPGXXX | extend piping for easy access on TC2 condenste low point drains below grating on mezz under (Engineering) | 0% | O
TCMSL6 | Jensen/ Mills | 6535706 | TC002CNDPPGXXX | 2-CD-V009 Condensate recirc control vlv bypass vlv leaking on bottom of flange. | 100% | O | [9 empty] | 2014-04-07 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535707 | TC002CNDVLVXXX | Vent on bypass line around condensate control vlv is leaking | 100% | O | [9 empty] | 2014-04-07 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6532527 | TC002CNDDEAHTR | TC2 DA NDE Inspection and Needed Repairs | 100% | O | Feb. |  | 40000 |  | 4540 |  |  |  |  | 2014-02-24 | 2014-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6532528 | TC002CW-CONXIC | TC2 Condenser EC Inspection | 100% | O | Mar. |  | 15000 |  | 14990 |  |  |  |  | 2014-02-17 | 2014-02-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CTH- HYPERBOLIC COOLING TOWER |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | NDCT header/seal Insp. |  | O |  | 10000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6462893 | TC002CTHSTRXIC | 2CWFT160B 2B CTWR Blowdown flowrate is reading bad quality. | 100% | O |  |  |  |  | 20933 |  |  |  |  | 2014-04-21 | 2014-04-25
TCMSL2 | Powell/ Henderson | 6531327 | TC002CTHCW-2A-CTPMPMTR | Change oil in the 2A Cooling Tower pump motor GST 68. Also inspect the exciter compartment. | 100% | O | Mar. |  | 1500 | [6 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6531332 | TC002CTHCW-2B-CTPMPMTR | Change oil in the 2B Cooling Tower pump motor GST 68. Also inspect the exciter compartment. | 100% | O | Mar. |  | 1500 | [6 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6531333 | TC002CTHCW-2C-CTPMPMTR | Change oil in the 2C Cooling Tower pump motor GST 68. Also inspect the exciter compartment. | 100% | O | Mar. |  | 1500 | [6 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6539227 | TC002CTHVLV2A-MOV170A | PM-OUTAGE - & - INSPECT 2A & 2B COOLING TOWER BY PASS VALVES | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6524398 | TC002CTHCW-2C-CTPMPMTR | The 2A, 2B, and 2C CT pump motors need to have an Isol valve installed on the discharge side of the | 100% | O |  |  | 500 | [6 empty] | 2014-04-21 | 2014-04-25
TCMSLENGMECH | Dorwart | 6540759 | TC002CTHCW-2A-CTPMP | TC2 NDCT Pump Impeller and Screen Inspections | 100% | O
TCMSLENGCIVL | Phelps | 6504096 | TC002CTHSTRXXX | WO for TC2 hyperbolic cooling tower inpsection | 100% | O | [9 empty] | 2014-03-24 | 2014-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CU-DCS- COMPUTER/ DCS | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002CW- CIRCULATING WATER |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | BCP recirc & HP/LP bypass valve pull & Insp. |  | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6535765 | TC002CW-CONXIC | TC2 Condenser Hotwell Inspection | 100% | O
TCMSLENGMECH | Dorwart | 6539385 | TC002CW-CONXIC | TC2 Circulating Water Line Inspection | 100% | O
TCMSLENGMECH | Dorwart | 6540440 | TC002CW-CONXIC | Inspect TC2 waterboxes for cracks. Some vibration heard in B2 HP cond inlet. | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25
|  |  | TC002EHC- ELECTRO-HYDRAULIC CONTROL | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002ESPDRY- ELECTROSTATIC PRECIPITATOR |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | ESP Wash |  | O |  | 100000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | DESP,WESP plated Electrode Inspection by 3rd Party |  | O |  | 20000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | DESP Repairs- (leaks, internal repairs, rappers/ plates) |  | O |  | 50000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6510632 | TC002ESPHVDDRY2B11T/RCNT | DESP TR set 2A23 keeps tripping on UV TRIP. Bushing "A" | 100% | O |  |  | 0 | [6 empty] | 2014-03-17 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530141 | TC002ESPDRY | PM-ANNUAL-OUTAGE- DESP OUTAGE MAINTENANCE. | 100% | O |  |  |  |  | 34299 |  |  |  |  | 2014-03-17 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002ESPWET- ELECTROSTATIC PRECIPITATOR |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | WESP Repairs (Leaks/ Water Distribution) |  | O |  | 50000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCBW/ TCMSLCC | Dearman/ Craft/ Walcott | 6410930 | TC002ESPWETXXX | An inspection performed by LG&E, SESS and Bechtel of the WESP water irrigation balancing during the | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6300388 | TC002ESPWET2A2-23T/RSET | 2A2-23 WESP T/R trips on undervoltage, TS&R. | 100% | O | Mar. |  | 1500 | [6 empty] | 2014-03-17 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530140 | TC002ESPWET | PM-ANNUAL-OUTAGE PM - WESP OUTAGE MAINTENANCE INSPECTIONS. | 100% | O |  |  |  |  | 48286 |  |  |  |  | 2014-03-17 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6565879 | TC002ESPWETWASHXIC | Re-range 2-QWP-PT-061 to 0-60psi, See Logan. | 100% | O
TCMSL6 | Jensen/ Mills | 6549729 | TC002ESPWETXXX | WESP Observation Window--Repalce the broken glass on the western most window. | 100% | O
TCMSL6 | Jensen/ Mills | 6568232 | TC002ESPZONWETVLVXXX | Add pipe plugs to air vent valves. See Logan Waller for plugs. | 100% | O
|  |  |  | Inspections | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCENGCHEM | Waller | 6555042 | TC002ESPWETPPG | Capital -Replace TC2 WESP carbon steel piping with stainless steel piping from the strainers to WESP | 100% | C | [7 empty] | 286082
|  |  | TC002EXC- EXCITER |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530148 | TC002EXCEGRXXX | PM-ANNUAL- OUTAGE- Generator maintenace for outages. | 100% | O | Mar. |  | 2000 | [6 empty] | 2014-02-10 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002FG- FLUE GAS |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Fan Inspections (Serviceman/Blades) ID,FD,PA |  | O |  | 40000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | ID Fan Motor Inspection |  | O |  | 35000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCBW | Dearman/ Craft | 6470242 | TC002FG-DCTEXPJNT | There are several holes in the expansion on the 2A I.D. Fan discharge at about the 12 o'clock positi | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530145 | TC002FG-ID- | PM-ANNUAL-OUTAGE - & - TC2 "A" & "B" ID Fans- Inspection of Impeller heating elements- | 100% | O | [9 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6479416 | TC002FG-ID-2A-IDFAN | Calibrate the 2A ID Fan blade actuator and associated linkages. | 100% | O | [9 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530142 | TC002FG-ID-2A-IDFANMTR | PM-ANNUAL-OUTAGE- TC2 "A" ID Fan motor bearings- change oil, clean and inspect motor | 100% | O | Mar. |  | 10000 | [6 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530143 | TC002FG-ID-2B-IDFANMTR | PM-ANNUAL-OUTAGE- TC2 "B" ID Fan motor bearings- change oil, clean and inspect motor | 100% | O | [9 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6441278 | TC002FG-ID-2A-IDFANMTR | Modify motor heater circuits on TC2 medium voltage motors. | 100% | O |  |  | 600 | [6 empty] | 2014-02-10 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6479413 | TC002FG-ID-2B-IDFAN | Calibrate the 2B ID Fan blade actuator and associated linkages. | 100% | O | [9 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6529472 | TC002FG-ID-O2XXX | Pull and nspect TC2 O2 probes. | 100% | O | Feb. |  | 2500 |  | 13387 |  |  |  |  | 2014-02-10 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6547040 | TC002FG-ID-2A-XXX | Investigate issues with TC2 ID fan hub heaters. | 100% | O | [9 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6563013 | TC002FG-ID-2A-IDFANMTR | Replace shaft grounding brush | 100% | O
TCMSL6 | Jensen/ Mills | 6543175 | TC002FG-ID-2A-IDFAN | Check oil and Hydraulic levels on TC2 I.D. & F.D fans. | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6539213 | TC002FG-ID-2A-IDFAN | PM-OUTAGE-ANNUAL - & - 2A I.D. FAN VISUAL INSPECTION | 100% | O | Mar. |  | 16000 | [6 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539218 | TC002FG-ID-2A-XXX | PM-OUTAGE - & - 2A I.D. FAN BRAKE - INSPECT BRAKE ASSEMBLY | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSLENGMECH | Dorwart | 6550575 | TC002FG-DCTEXPJNT | Repair on replace the expansion joint on common duct work from the Air Heater duct to the Precip | 100% | O
TCMSLENGMECH | Dorwart | 6550581 | TC002FG-DCTEXPJNT | Replace to expansion joint on Duct work west of the 2A Air Heater | 100% | O
TCMSLENGMECH | Dorwart | 6550579 | TC002FG-DCTXXX | Repair, cover and make water tight inspection ports on sides of duct work down stream of the Air | 100% | O
TCMSL6 | Jensen/ Mills | 6543040 | TC002FG-DMP2A-OUTDMP | 2A ID Fan Outlet Damper binding especially at less than 10% open | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6547562 | TC002FG-ID-2B-IDFAN | Change out 2B ID Fan blade hubs | 100% | O |  |  |  |  | 33 |  |  |  |  | 2014-03-03 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539214 | TC002FG-ID-2B-IDFAN | PM-OUTAGE-ANNUAL - & - 2B I.D. FAN VISUAL INSPECTION | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539219 | TC002FG-ID-2B-XXX | PM-OUTAGE - & - 2B I.D. FAN BRAKE - INSPECT BRAKE ASSEMBLY | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSLENGMECH | Dorwart | 6550574 | TC002FG-DCTEXPJNT | Add cover over expansion joint inside Duct from Air Heater to precip. | 100% | O
TCMSLENGMECH | Maldonado | 6542829 | TC002FG-DMPXXX | Provide mechanic to assist with biasing damper inspection. | 100% | O | [9 empty] | 2014-04-07 | 2014-04-11
|  |  | TC002FP- FIRE PROTETCION | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002FW- FEEDWATER |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | MBBFP motor inspection |  | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | TDBFP Recirc Valve Overhauls |  | O |  | 150000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | BFP Study | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6487154 | TC002FW-TFP2A-RECCV054A | Inspect the 2A TDBFP recirc valve 2-BFD-CV-054A valve appears to be leaking through. | 100% | O | Mar. |  | 32000 | [6 empty] | 2014-03-03 | 2014-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530235 | TC002FW-MFP2C1MTR | Open and inspect both North and South MDBFP motors. | 100% | O | [9 empty] | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6529471 | TC002FW-TFP2B-RECCV054B | Pull and inspect the 2B TDBFP recirc valve. 2-BFD-CV-054B | 100% | O | [9 empty] | 2014-03-03 | 2014-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530146 | TC002FW-TFPXIC | PM-OUTAGE- & - 2A & 2B TDBFP Emergency Oil pump cabinets. - Clean out and check connections. | 100% | O | [9 empty] | 2014-03-15 | 2014-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6555039 | TC002FW-FWH8A-CV801AA | Pull and inspect 8A Heater normal drain. 2-HD-CV-801AA. | 100% | O
TCMSL6 | Jensen/ Mills | 6539228 | TC002FW-FWHPPG | PM-OUTAGE - & - PIN FEEDWATER PIPING HANGERS | 100% | O | [9 empty] | 2014-02-08 | 2014-04-30
TCMSL6 | Jensen/ Mills | 6534338 | TC002FW-FWH6A-HP-HTR | Install HP 6A Feedwater HTR Diaphragm per 2014 procedure. | 100% | O | Feb. |  | 1000 | [6 empty] | 2014-03-03 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6534392 | TC002FW-FWH6B-HP-HTR | Install HP 6B Feedwater HTR Diaphragm per 2014 procedure. | 100% | O | Feb. |  | 1000 |  | 5777 |  |  |  |  | 2014-03-03 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6534395 | TC002FW-FWH8A-HP-HTR | Install HP 8A Feedwater HTR Diaphragm per 2014 procedure. | 100% | O | Feb. |  | 1000 | [6 empty] | 2014-03-03 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6534396 | TC002FW-FWH8B-HP-HTR | Install HP 8B Feedwater HTR Diaphragm per 2014 procedure. | 100% | O | Feb. |  | 32000 |  | 30041 |  |  |  |  | 2014-03-03 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL7 | Thomas | 6520696 | TC002FW-TFP2A-BSTRPMPGR | Perform inspection of the 2A Booster Pump gear reducer | 100% | O | [9 empty] | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL7 | Thomas | 6520697 | TC002FW-TFP2B-BSTRPMPGR | Perform inspection of the 2B Booster Pump gear reducer | 100% | O | [9 empty] | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6548746 | TC002FW-TFPXXX | 2B BFP exhaust trunk rupture disc is leaking identified with condenser air leakage inspection | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6524450 | TC002FW-TFP2A-BSTRPMP | Clean all Suction strainers on the TC2 BFP's . | 100% | O |  |  |  |  | 3429
TCMSL6 | Jensen/ Mills | 6540595 | TC002FW-TFP2B-BSTRPMP | 2B TDBFP Booster pump north mechanical seal is leaking | 100% | O | Mar. |  | 6000 | [6 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535709 | TC002FW-FWH8A-CV801AA | TC2 HTR 8A normal drain to HTR 7A CV has packing leak | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6548547 | TC002FW-FWHHP-VLVXXX | TC2 8A HP Feedwater heater bypass valve will not open. TS&R | 100% | O |  |  | 6000 |  | 4852 |  |  |  |  | 2014-02-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6535712 | TC002FW-FWHHP-XXX | TC2 HTR 7A, 7B, 8A, 8B Shellside safety leaking trough | 100% | O |  |  |  |  | 1458 |  |  |  |  | 2014-02-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6544359 | TC002FW-FWHHP-VLVXXX | The heater 7B bypass valve has a broken gear box. Please replace and inspect valve | 100% | O | [9 empty] | 2014-02-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6535700 | TC002FW-FWHHP-XXX | Replace packing on TC2 HTR 6A, 6B, 7A, 7B, 8A, 8B inlet, outlet and bypass vlvs | 100% | O |  |  | 5000 |  | 1789 |  |  |  |  | 2014-02-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002GA- GENERATOR AND AUXILIARIES |  | 91.67% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6428543 | TC002GA-STASO-ESOPMTR | Make repairs to the TC2 ESOP panel. | 100% | O |  |  |  |  | 251 |  |  |  |  | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530150 | TC002GA-STASO-ESOPMTR | PM-ANNUAL-OUTAGE- Emergency Seal oil pump motor-Check brushes and wipe clean. Test run and grease | 100% | O | [9 empty] | 2014-03-15 | 2014-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6542399 | TC002GA-FLDXXX | Clean and inspect brush rigging on TC2 generator | 100% | O | [9 empty] | 2014-03-03 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530149 | TC002GA-STASO-XXX | PM-OUTAGE - & - Emergency Seal oil pump Cabinet 2-TSO-EP-002- Clean out and check connections. | 100% | O | [9 empty] | 2014-03-15 | 2014-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530147 | TC002GA-STAXIC | PM-ANNUAL OUTAGE - & - TC2- STATOR CONDUTCIVITY perform checks per OEM. | 100% | O | Feb. |  | 1500 | [6 empty] | 2014-03-15 | 2014-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6552404 | TC002GA-STASO-ESOPMTR | Install the spare TC2 Emergency Seal oil Pump | 100% | O
TCMSL6 | Jensen/ Mills | 6539216 | TC002GA-STA-2A-CLGPMP | PM-OUTAGE-ANNUAL- STATOR COOLING SYSTEM FILTER CHANGE | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6543239 | TC002GA-HYDVLV | Replace the Hydrogen supply vlv#003, the vlv is leaking through and will not isolate | 100% | O | [9 empty] | 2014-03-24 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6544280 | TC002GA-STASO-XXX | Flush TC2 Seal oil Vacuum pumps and piping with oil then refill pumps with clean oil | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
TCMSLENG | Moore | 6469864 | TC002GA-STAXXX | Install Gross MW transducer for AGC indication | 0% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002HL- HYDRATED LIME |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6550578 | TC002HL-INJPPG | Clean all Lime injection ports on duct work behind Air Heater. | 100% | O
TCENGCHEM | Turner |  |  | Installation of new HL system. |  | O | [9 empty] | 2014-03-05 | 2014-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | TC002HVC- HEATING VENT AND A/C | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002PFC- PRIMARY FUEL COMBUSTION |  | 99.71% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | PA Fan - Inspect bearings and input damper linkage |  | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Mohn |  |  | TC2 PA Fan Ext Bearing Coolers |  | C | [5 empty] | 102699 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH |  | 6354888 | TC002PFCBURXXX | Bechtel and Doosan burner inspection observation work order. | 85% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMC | Bullock | 6534214 | TC002PFCPULA | Weld overlay TC2 A, B, C, D, and E coal mill grind floors and rolls. | 100% | O |  |  |  |  | 122000
TCPIC | Sedam | 6444001 | TC002PFCPULA | Make repairs to TC2 Pulverizers per Alstom TA's report. | 100% | O |  |  |  |  | 16144 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCPIC | Sedam | 6538209 | TC002PFCPULA | Inspect TC2 pulverizers during spring 2014 outage. | 100% | O
TCPIC | Sedam | 6499823 | TC002PFCPULA | PM-SEMI-ANNUAL - & - 2A PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | 100% | O |  |  |  |  | 4158
TCPIC | Sedam/ Maldonado | 6538230 | TC002PFCPULA-CLAS-XXX | PM-OUTAGE-SEMI-ANNUAL - & - 2A PULVERIZER CLASSIFIER INSPECTION | 100% | O | Apr. |  | 13500
TCPIC | Sedam | 6538231 | TC002PFCPULB-CLAS-XXX | PM-OUTAGE-SEMI-ANNUAL - & - 2B PULVERIZER CLASSIFIER INSPECTION | 100% | O
TCPIC | Sedam | 6538232 | TC002PFCPULC-CLAS-XXX | PM-OUTAGE-SEMI-ANNUAL - & - 2C PULVERIZER CLASSIFIER INSPECTION | 100% | O
TCPIC | Sedam | 6538233 | TC002PFCPULD-CLAS-XXX | PM-OUTAGE-SEMI-ANNUAL - & - 2D PULVERIZER CLASSIFIER INSPECTION | 100% | O
TCPIC | Sedam | 6538234 | TC002PFCPULE-CLAS-XXX | PM-OUTAGE-SEMI-ANNUAL-PM- 2E PULVERIZER CLASSIFIER INSPECTION | 100% | O
TCPIC | Sedam | 6538224 | TC002PFCPULF-CLAS-XXX | PM-OUTAGE-SEMI-ANNUAL - & - 2F PULVERIZER CLASSIFIER INSPECTION | 100% | O
TCMSL6 | Jensen/ Mills | 6535828 | TC002PFCPULF-XXX | Inspect and replace as needed the first expansion joint from the TC2 coal mills on the pulverized fu | 100% | O |  |  | 20000 | [6 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539230 | TC002PFCFOEXXX | PM-OUTAGE - & - CLEAN AND INSPECT FUEL STRAINERS | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539222 | TC002PFCPAF2A-FAN | PM-OUTAGE - & - 2A P.A. FAN BRAKE INSPECT | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539211 | TC002PFCPAF2A-FAN | PM-OUTAGE-SEMI-ANNUAL - & - 2A P.A. FAN INSPECTION | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539201 | TC002PFCPAF2A-FAN | PM-OUTAGE-ANNUAL - & - 2A P.A. FAN VISUALLY INSPECTION | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539199 | TC002PFCPAF2A-FAN | PM-OUTAGE-ANNUAL - & - 2A P.A. FAN BEARINGS (DODGE) OIL CHANGE | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6542417 | TC002PFCPAF2A-FAN | PDM - Check shaft runout on the Outboard Fan Bearing | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539200 | TC002PFCPAF2B-FAN | PM-OUTAGE-ANNUAL - & - 2B P.A. FAN BEARINGS (DODGE) OIL CHANGE | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6539202 | TC002PFCPAF2B-FAN | PM-OUTAGE-ANNUAL - & - 2B P.A. FAN VISUAL INSPECTION | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539212 | TC002PFCPAF2B-FAN | PM-OUTAGE-SEMI-ANNUAL - & - 2B P.A. FAN INSPECTION | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539223 | TC002PFCPAF2B-FAN | PM-OUTAGE - & - 2B P.A. FAN BRAKE | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539225 | TC002PFCPAF2B-FAN | PM-OUTAGE - & - 2A P.A. FAN ALIGNMENT AND COUPLING PM | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6539226 | TC002PFCPAF2B-FAN | PM-OUTAGE - & - 2B P.A. FAN ALIGNMENT AND COUPLING PM | 100% | O | [9 empty] | 2014-03-17 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6554748 | TC002PFCPULA | Alignments need to be done on all the TC2 mill motors | 100% | O
TCMSL6 | Jensen/ Mills | 6534745 | TC002PFCSILMOV501F | THE 2F COAL MILL BUNKER VALVE GEAR BOX IS BROKE | 100% | O |  |  | 7000 |  | 3912
TCMSL6 | Jensen/ Mills | 6558542 | TC002PFCFDR2A- | Maintenance checks need to be performed on the TC2 coal feeders | 100% | O |  |  | 17000
TCMSL2 | Powell/ Henderson | 6379666 | TC002PFCFOE2A2-OFM | Flame Scanners on TC2 do not work correctly. TC2 has two scanners per burner (oil and Coal). When p | 100% | O | [9 empty] | 2014-04-28 | 2014-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530111 | TC002PFCBURXXX | I/E support for burner replacement project. | 100% | [5 empty] | 10480 |  |  |  |  | 2014-02-01 | 2014-05-02 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530168 | TC002PFCFDR2A- | PM-SEMI-ANNUAL - & - TC2-"2A" FEEDER, CALIBRATE FEEDER AND | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530163 | TC002PFCFDR2B- | PM-SEMI-ANNUAL - & - TC2-"2B" FEEDER, CALIBRATE FEEDER AND | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530164 | TC002PFCFDR2C- | PM-SEMI-ANNUAL - & -TC2- "2C" FEEDER, CALIBRATE FEEDER AND | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530165 | TC002PFCFDR2D- | PM-SEMI-ANNUAL - & -TC2- "2D" FEEDER, CALIBRATE FEEDER AND | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530166 | TC002PFCFDR2E- | PM-SEMI-ANNUAL - & - TC2- "2E" FEEDER, CALIBRATE FEEDER AND | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530167 | TC002PFCFDR2F- | PM-SEMI-ANNUAL - & - TC2-"2F" FEEDER, CALIBRATE FEEDER AND | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6554451 | TC002PFCFOE2D5-OFM | Replace trial oil flame scanner with original scanner. | 100% | O |  |  |  |  | 7128
TCMSL2 | Powell/ Henderson | 6539152 | TC002PFCPAF2A-FANMTR | Alarm Management, 2A PA Fan Motor Current Alarm is in reading bad 121.3B. TS&R Emerson Point | 100% | O | [9 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530152 | TC002PFCPAF2A-FANMTR | PM-ANNUAL-OUTAGE- TC2 "A" Primary Air Fan motor bearings- change oil, clean and inspect motor | 100% | O | Feb. |  | 5000 | [6 empty] | 2014-03-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530153 | TC002PFCPAF2B-FANMTR | PM-ANNUAL-OUTAGE- TC2 "B" Primary Air Fan motor bearings- change oil, clean and inspect motor | 100% | O | Feb. |  | 5000 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530154 | TC002PFCPULA-MTR | PM-ANNUAL - & - TC2 "A" Coal mill motor clean, inspect & bearings oil change- | 100% | O |  |  | 200 |  | 34 |  |  |  |  | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530151 | TC002PFCPULA-XIC | PM-ANNUAL-OUTAGE - & - Pulverizer instrumentation loop checks. | 100% | O | [9 empty] | 2014-04-18 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530156 | TC002PFCPULB-MTR | PM-ANNUAL - & - TC2 "B" Coal mill motor clean, inspect & bearings oil change- | 100% | O |  |  | 200 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6535532 | TC002PFCPULB-INERTCV030B | 2B mill inerting steam is leaking through. | 100% | O | Mar. |  | 10000 |  | 55 |  |  |  |  | 2014-03-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6529923 | TC002PFCPULC-INERTCV030C | Inspect 2-FC-CV-030C | 100% | O | Mar. |  | 10000 | [6 empty] | 2014-03-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6529925 | TC002PFCPULC-INERTCV030C | Inspect 2-FC-CV-030D | 100% | O | Mar. |  | 10000 |  | 5 |  |  |  |  | 2014-03-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530158 | TC002PFCPULC-MTR | PM-ANNUAL - & - TC2 "C" Coal mill motor clean, inspect & bearings oil change- | 100% | O |  |  | 200 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6561971 | TC002PFCPULD-CLAS-MTR | Test run 2D Coal Mill Classifier Motor | 100% | O
TCMSL2 | Powell/ Henderson | 6536572 | TC002PFCPULD-CLAS-MTR | Pull and inspect motor bearings on the 2D Coal Mill Classifier motor. Also order new motor for spare | 100% | O |  |  | 1500 | [6 empty] | 2014-03-03 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530160 | TC002PFCPULD-MTR | PM-ANNUAL - & - TC2 "D" Coal mill motor clean, inspect & bearings oil change- | 100% | O |  |  | 200 | [6 empty] | 2014-03-03 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530161 | TC002PFCPULE-MTR | PM-ANNUAL - & - TC2 "E" Coal mill motor clean, inspect & bearings oil change- | 100% | O |  |  | 200 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530162 | TC002PFCPULF-MTR | PM-ANNUAL - & - TC2 "F" Coal mill motor clean, inspect & bearings oil change- | 100% | O |  |  | 200 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6542953 | TC002PFCPULF-MTR | 2F Mill RTD-C1 motor stator temp reading low tag-ID D-2FC001F-STMPCA | 100% | O | [9 empty] | 2014-03-13 | 2014-03-13
|  |  | TC002PJF- PULSE JET FABRIC FILTER |  | 83.33% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | PJFF Inlet, Outlet & bypassdamper inspection. (some scaffold requ.) |  | O |  | 25000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | PJFF pulse header J tube inspect for corrosion (2 sections each side) |  | O |  | 10000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | PJFF Repairs (bag detectors, solenoids, door seals, etc…) |  | O |  | 60000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCENGCHEM | Turner |  |  | TC2 PJFF B&C | 0% | C | [5 empty] | 1760914 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Add SO3 monitors for baghouse. |  | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6552727 | TC002PJFCMPXXX | Calibrate transmitters and clean sensing lines in baghouse. See attached email. | 100% | O
TCENGCHEM | Turner/ Waller | 6535720 | TC002PJFCMPXXX | Bag replacements (leak test & pre-coat of new bags)(Seals) | 100% | O | Feb. |  | 52000 |  | 54766 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6539215 | TC002PJFCMPXXX | Remove 12 Sample bags from four different compartments and palce the compartment doors back in place | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6535522 | TC002PJFCA-2A-COMP | PM-ANNUAL - & - 2A PULSE JET FABRIC FILTER AIR COMPRESSOR | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6535523 | TC002PJFCA-2B-COMP | PM-ANNUAL - & - 2B PULSE JET FABRIC FILTER AIR COMPRESSOR | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002PLT- PLANT MISC. |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Industrial Cleaning |  | O |  | 200000 |  |  | 96000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Scaffolding |  | O |  | 100000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Service Reps- Alstom, Howden, MD&A, Diamond Power) |  | O |  | 150000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6512217 | TC002PLTXXX | Gather information on various TC2 transmitters during outage. | 100% | O | [9 empty] | 2014-02-10 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6534151 | TC002PLTXXX | Surge test medium voltage motors on TC2. | 100% | O |  |  |  |  | 268 |  |  |  |  | 2014-03-03 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6539282 | TC002PLTXXX | Winterize TC2 instrumentation For spring outage | 100% | O | [9 empty] | 2014-02-08 | 2014-04-25
TCMSL2 | Powell/ Henderson | 6531897 | TC002PLTXXX | Work order to cover temporary power. | 100% | O | Feb. |  | 5000 | [6 empty] | 2014-02-01 | 2014-04-25 | bar: 2014-02-01 to 2014-03-07
TCMSL6 | Jensen/ Mills | 6539224 | TC002PLTXXX | PM-OUTAGE - & - INSPECT TC2 DAMPERS | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 2014-02-01: 0; 2014-02-02: 0; 2014-02-03: 0; 2014-02-04: 0; 2014-02-05: 0; 2014-02-06: 0; 2014-02-07: 0; 2014-02-08: 0; 2014-02-09: 0; 2014-02-10: 0; 2014-02-11: 0; 2014-02-12: 0; 2014-02-13: 0; 2014-02-14: 0; 2014-02-15: 0; 2014-02-16: 0; 2014-02-17: 0; 2014-02-18: 0; 2014-02-19: 0; 2014-02-20: 0; 2014-02-21: 0; 2014-02-22: 0; 2014-02-23: 0; 2014-02-24: 0; 2014-02-25: 0; 2014-02-26: 0; 2014-02-27: 0; 2014-02-28: 0; 2014-03-01: 0; 2014-03-02: 0; 2014-03-03: 0; 2014-03-04: 0; 2014-03-05: 0; 2014-03-06: 0; 2014-03-07: 0
TCMSL6 | Jensen/ Mills | 6554888 | TC002PLTXXX | Misc. work that is being done by Sceptre | 100% | O
|  |  | TC002PRD- POWER ISTRIBUTION |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Switchgear Maintenance |  | O |  | 50000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6439451 | TC002PRD7KVXXX | TC2 7KV and 14KV breakers need to have the manual close | 100% | O |  |  |  |  | 15531 |  |  |  |  | 2014-02-10 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002SCR- SELECTIVE CATALYST REDUCTION |  | 93.25% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Vacuum & Inspect catalyst |  | O |  | 75000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart |  |  | TC2 SCR Layer 1 Replacement | 100% | C | Mar. |  |  |  |  | 3005166 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart |  |  | TC2 UPG Ammonia System | 90% | C | [5 empty] | 77026 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530230 | TC002SCRAMMDET | PM- SEMI-ANNUAL - & - 2 SCR AMMONIA DETECTOR CALIBRATION | 100% | O | Feb. |  | 3300 |  | 2743 |  |  |  |  | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530232 | TC002SCRAMMDET | PM- ANNUAL - & - 2 SCR SYSTEM E-STOP CHECK | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6547582 | TC002SCRAMMDET | Need to install sliding terminal blocks (slide links) on unit 2 ammonia detectors. | 100% | O | [9 empty] | 2014-04-21 | 2014-04-25
TCMSL2 | Powell/ Henderson | 6533729 | TC002SCRNOXXIC | TC2 SCR B CO analyzer has high flow alarm in. TS&R | 100% | O | [9 empty] | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6533733 | TC002SCRNOXXIC | TC2 SCR B SO2 analyzer has high flow alarm in. TS&R | 100% | O | [9 empty] | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6533734 | TC002SCRNOXXIC | TC2 SCR A NOX inlet analyzer has high pressure alarm in. TS&R | 100% | O | [9 empty] | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6535768 | TC002SCRMODCATALYST | TC2 SCR - Layer 1 Off-site Clean and store - Capital | 50% | C | Dec. | [5 empty] | 75000 |  |  | 2014-04-14 | 2014-04-25
TCMSLENGMECH | Dorwart | 6489828 | TC002SCRMODCATALYST | TC2 - Layer 1 Catalyst Changeout - Capital | 100% | C | Feb. | [5 empty] | 220000 |  |  | 2014-02-24 | 2014-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6494218 | TC002SCRMODCATALYST | TC2 SCR Catalyst Cleaning In Situ - Capital | 100% | C | Feb. | [5 empty] | 75000 |  |  | 2014-02-10 | 2014-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6494221 | TC002SCRMODCATALYST | TC2 SCR Catalyst Seals - Capital- (ETA end of Mar.) | 100% | C | Mar. | [5 empty] | 40000 |  |  | 2014-02-28 | 2014-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Dorwart | 6552390 | TC002SCRMODCATALYST | TC2 SCR Ash Piling Correction - Ash Sweeper Installations | 50% | C | Apr./ May |  |  |  |  | 300000 | 250000
TCBW | Dearman/ Craft | 6511593 | TC002SCRAMMTRANPPG | Bechtel to modify existing Ammonia piping at the storage tank pump skid to elimnate damage to the tr | 75% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6552593 | TC002SCRAMMTRANVLVXXX | Replace the ammonia relief valves that are the 5 year throw away valves | 100% | O |  |  | 7000 |  | 5566
TCMSL6 | Jensen/ Mills | 6551222 | TC002SCRDILHTRPPG | Repair the flange that has been filled by fermanite on the supply line to the SCR Water Coils. | 100% | O
TCMSL6 | Jensen/ Mills | 6539015 | TC002SCRMODCATALYST | TC2 SCR Catalyst Samples | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6536666 | TC002SCRAMMTRANA-PMP | The inlet strainer on the 2B ammonia pump has a high DP please T/R. | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6536621 | TC002SCRMODXXX | TC2 Open SCR Doors - 14 total | 100% | O | [9 empty] | 2014-02-08 | 2014-04-25
TCMSL6 | Jensen/ Mills | 6547030 | TC002SCRMODSRUCTURE | The TC2 A SCR dP pressure tap location needs to be changed. | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25
|  |  | TC002SD- SUMPS AND DRAINS |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6483873 | TC002SD-SMP-OILWTSPTNK | Work with Thompson on cleaning out the oil water separator on unit 2 | 100% | O |  |  |  |  | 7122 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002SDR- SDRS SCRUBBER |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | FGD Reactant Tank Cleanout/Inspect, Nozzle repairs (incr. $75K) |  | O |  | 75000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Chimney flue gutters inspection |  | O |  | 30000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Repair Reaction Tank Agitater Blades |  | O |  | 100000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530241 | TC002SDRFXE2A-BLWRMTR | Change oil in the 2A & 2B Oxidation Air Compressor motors. GST 32 | 100% | O |  |  | 200 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6530237 | TC002SDRREC2A-PMPMTR | Change oil in all 6 TC2 Recycle pump motors. GST 46 | 100% | O |  |  | 1200 | [6 empty] | 2014-03-13 | 2014-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6544289 | TC002SDRTNKXXX | Pull and store pH probes on TC2 SDRS and on NDCT | 100% | O | [9 empty] | 2014-02-10 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6475504 | TC002SDRTNKXXX | Install and setup ORP probes and transmitters on TC2 scrubber. | 100% | O |  |  | 4100 |  | 3772
TCMSL2 | Powell/ Henderson | 6545159 | TC002SDRTNKCV459 | unit 2 absorber service water make-up valve 2CV-459 is leaking through when 0% closed, TS/R | 100% | O | [9 empty] | 2014-03-24 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6497684 | TC002SDRDEMNOZZLES | Please check Operation and change nozzles as needed on the following Mist Eliminator bottom zones. | 100% | O |  |  |  |  | 2211 |  |  |  |  | 2014-03-17 | 2014-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6550731 | TC002SDRRECVLVXXX | Replace all the TC2 recycle pump inlet valve retaining flanges and pull one discharge valve to | 100% | O
TCMSL6 | Jensen/ Mills | 6494025 | TC002SDRREC2D-PMPGB | 2D Recycle Pump is leaking oil, from the north side of the gear box around the pump shaft. | 100% | O |  |  | 40000 |  | 39313 |  |  |  |  | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6555047 | TC002SDRREC2A-PMP | Change oil in all the TC2 recycle pump | 100% | O
TCMSL6 | Jensen/ Mills | 6533908 | TC002SDRRECXXX | Add back-up line for the Recycle pump mechanical seal water line. | 100% | O |  |  | 1000 | [6 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6536019 | TC002SDRTNKXXX | Open doors during 2014 TC2 spring outage | 100% | O | [9 empty] | 2014-02-08 | 2014-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TCMSL6 | Jensen/ Mills | 6544987 | TC002SDRTNKXXX | Need to add low point drains to the unit 2 reactant feed supply line | 100% | O | [9 empty] | 2014-02-24 | 2014-03-10
TCMSL6 | Jensen/ Mills | 6549593 | TC002SDRSTKXXX | Fabricate test ports for WESP inlet. | 100% | O
TCMSLENGCIVL | Phelps | 6504192 | TC002SDRBLDPPG | extend TC2 gypsum line to the west ~500'-700' in gypsum storage pond | 100% | O | Mar. |  | 8880 |  | 509 |  |  |  |  | 2014-02-24 | 2014-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGCIVL | Phelps | 6538933 | TC002SDRTNKXXX | Clean out TC2 reaction tank at beginning of outage | 100% | O |  |  |  |  | 15294
TCMSLENGCIVL | Phelps | 6535583 | TC002STBSDRXXX | WO for Inspection and repairs of TC2 FGD | 100% | O |  |  |  |  | 34000
TCMC | Bullock | 6540330 | TC002SDRSTKXXX | TC2 Stack Inspection Spring 2014. | 100% | O | Apr. |  | 40000
TCMSLENG | Moore | 6327090 | TC002SDRTNKXIC | Install full range level indication on unit 2 reaction tank. Provide tank connection/reference point | 100% | O |  |  |  |  | 1386 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002STB- STRUCTURES & BUILDINGS |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6532295 | TC002STBHT-XXX | TC2 cooling tower pump heat trace panel 2CTEHB1 ckt #6 fault alarm is in. located on pump platform. | 100% | O |  |  | 200 | [6 empty] | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002SW- SERVICE WATER | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002TA- TURBINE & AUXILIARIES |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Main Turbine LP Blade Inspect |  | O |  | 60000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget |  |  |  | Turbine Extraction Steam Check Valves Overhaul |  | O |  | 30000 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSLENGMECH | Ball | 6535788 | TC002TA-CTL-MARKVI | TC2 HMI update- Turbine Controls | 100% | C | [5 empty] | 58571 | 84000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMMRS1 | Noonan/ Jones | 6475510 | TC002TA-TURXXX | TC2 Turbine/ Generator- #11 bearing. It appears that the right side horizontal joint is slightly | 100% | O | Apr. |  | 5000 | [6 empty] | 2014-04-30 | 2014-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMMRS1 | Noonan/ Jones | 6540323 | TC002TA-TURXXX | TC2 last stage turbine bucket (L-0) Inspection. | 100% | O | Mar. |  | 60000
TCMSL6 | Jensen/ Mills | 6473483 | TC002TA-HP-VLVXXX | 2-TDR-V019 Isolation valve is leaking at the body gasket. Replace the valve. | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMC | Bullock | 6501962 | TC002TA-LO-2A-CLR | 2A (East) Turbine Oil Cooler should be pulled and sent off site to be cleaned. 3/4" Square Stock Gas | 100% | O | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6550543 | TC002TA-MSTXIC | TC2 MASTER TRIP SOLENOID VALVE TEST - On the TEST B2 the B2 OPERATED was showing illuminated when | 100% | O | [9 empty] | 2014-04-14 | 2014-04-18
TCMSL2 | Powell/ Henderson | 6473465 | TC002TA-MST2A-CV002A | Install servo manifolds for TC2 turbine valves after modications to them are made. | 100% | O |  |  |  |  | 11392 |  |  |  |  | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6414676 | TC002TA-TSIXXX | When TC2 came offline the turning gear did not engage. When we investigated we found that the rotor | 100% | O |  |  |  |  | 29109 |  |  |  |  | 2014-04-14 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6466288 | TC002TA-TSIXIC | TC2 Turbine Cap vibration 11Y is reading erratically | 100% | O | Mar. |  | 1377 | [6 empty] | 2014-03-17 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6535545 | TC002TA-CONXIC | LP Condenser Shell Pressure Measurement Instrument ID 2CDPT010A ¿ Bad Output and higher than exp | 100% | O | [9 empty] | 2014-03-13 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6544541 | TC002TA-CTL-MARKVI | Investigate TC 2 GPR Lockout | 100% | O |  |  |  |  | 1097 |  |  |  |  | 2014-03-03 | 2014-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL2 | Powell/ Henderson | 6554897 | TC002TA-TURXIX | The Level Switch on the Gen Casing Liquid detector 2-HV-LS 125 | 100% | O
TCMSL2 | Powell/ Henderson | 6561535 | TC002TA-HP-XIC | Rebuild REXROTH Turbine Control Servos | 100% | O
TCMSL2 | Powell/ Henderson | 6561934 | TC002TA-TSIXIC | Calibrate the TC2 turbine casing expansion LVDTs. See Nick Payne. | 100% | O
TCMSL6 | Jensen/ Mills | 6484252 | TC002TA-CRHXXX | there is water leaking out around insulation of 2A reheat/inter vlv. T/R | 100% | O | [9 empty] | 2014-02-24 | 2014-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6538179 | TC002TA-LO-2A-CLR | Remove and clean 2A turbine lube oil cooler. | 100% | O | Mar. |  | 35000 |  | 2708 |  |  |  |  | 2014-02-17 | 2014-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6481708 | TC002TA-AUVPPG | Heater #6 Extraction line from the turbine to the heater has a leak under the insulation that is dri | 100% | O | [9 empty] | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6548761 | TC002TA-CON2A-VACPMP | 2A CVP east & west shaft seals are leaking. Identified with condenser air leakage test | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6428808 | TC002TA-CON2B- | Check out 2"B" condenser vacuum pump out board pump casing on northside towards bottom for a leak | 100% | O | Mar. |  | 17000 |  | 15995 |  |  |  |  | 2014-02-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6539217 | TC002TA-JOPSTNR | PM-OUTAGE - & - ANNUALLY- TC2 JACKING OIL PUMP FILTER | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6548754 | TC002TA-IP-XXX | TC2 IP turbine north shaft seal leaking. Identified with condenser air leakage test | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6548753 | TC002TA-LP-XXX | TC2 #1 LP turbine northeast and southeast gland seal housing leaking, horizintal joint. Identified | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6542194 | TC002TA-LO-2A-DUPSTNR | PM-ANNUAL - & - TURBINE LUBE OIL DUPLEX FILTER CHANGE | 100% | O |  |  | 7000 |  | 12966
TCMSL6 | Jensen/ Mills | 6548752 | TC002TA-LP-XXX | TC2 #2 LP turbine southwest gland seal housing horizontal joint leaking. Identified with condenser | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6548750 | TC002TA-LP-XXX | TC2 #2 LP turbine northeast gland seal housing leaking, horizontal joint. Identified with condenser | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28
TCMSL6 | Jensen/ Mills | 6548755 | TC002TA-TURXXX | TC2 leak at southwest corner away from condenser, steam dump bypass vlv under insulation. Identified | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28
|  |  | TC002TRF- TRANSFORMERS | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TC002WTR- WATER TREATMENT |  | 100% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6533751 | TC002WTRCP-VLVXXX | Install Condensate Polisher outlet valve to allow for routing of TC1 pegging condensate back to TC1 | 100% | O | [9 empty] | 2014-03-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6447938 | TC002WTRCHI-XXX | Please Inspect Check Valves on TC2 O2 Injection Skids | 100% | O |  |  |  |  | 1378 |  |  |  |  | 2014-03-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6532492 | TC002WTRCP-XXX | Repairs to TC2 Polisher Chemical Skids | 100% | O |  |  | 3500 |  | 1619 |  |  |  |  | 2014-04-07 | 2014-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TCMSL6 | Jensen/ Mills | 6411189 | TC002WTRCP-XXX | 'A' Condensate Polisher Vessel Will NOT Pressurize After Transfer | 100% | O |  |  |  |  | 7742 |  |  |  |  | 2014-03-10 | 2014-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O&M Budget Dollars |  |  |  | 3702000 | 1645057 | 0 | 712260 | 7594759 | 2107106
| Outage Progress- |  |  | O&M Current Estimates |  |  |  | 1645057
|  |  |  | O&M Unplanned Additional Expenses |  |  |  | 0
|  |  |  | O&M Variance |  |  |  | 2056943
| 98.56% |  |  | Capital Budget |  |  |  | 7594759
|  |  |  | Capital Current Estimates |  |  |  | 2107106
|  |  |  | Capital Variance |  |  |  | 5487653

## PM Work Orders
Work Order | Description | Location | Crew
6530113 | PM-ANNUAL-OUTAGE- STAGE 1 "A" SH Spray Water Control Valve 2-AT CV-110A. Check calibration, stroke | TC002BL-SH-VLVXXX | TCMSL2
6530114 | PM-ANNUAL-OUTAGE- STAGE 1 "B" SH Spray Water Control Valve 2-AT CV-110B. Check calibration, stroke | TC002BL-SH-VLVXXX | TCMSL2
6530115 | PM-ANNUAL-OUTAGE- STAGE 2 "A" SH Spray Water Control Valve 2-AT CV-120A. Check calibration, stroke | TC002BL-SH-VLVXXX | TCMSL2
6530116 | PM-ANNUAL-OUTAGE- STAGE 2 "B" SH Spray Water Control Valve 2-AT CV-120B. Check calibration, stroke | TC002BL-SH-VLVXXX | TCMSL2
6530117 | PM-ANNUAL-OUTAGE- "A" Reheat Spray Water Control Valve 2-AT CV-130A. Check calibration, stroke | TC002BL-RH-2A-CV130A | TCMSL2
6530118 | PM-ANNUAL-OUTAGE- "B" Reheat Spray Water Control Valve 2-AT CV-130B. Check calibration, stroke | TC002BL-RH-2B-CV130B | TCMSL2
6530119 | PM-ANNUAL-OUTAGE- Boiler instrumentation loop checks. | TC002BL-MS-XIC | TCMSL2
6530120 | PM-ANNUAL-OUTAGE- TC2 "A" FD Fan motor bearings- change oil, clean and inspect motor | TC002CBAFD-2A-FANMTR | TCMSL2
6530122 | PM-ANNUAL-OUTAGE- TC2 "B" FD Fan motor bearings- change oil, clean and inspect motor | TC002CBAFD-2B-FANMTR | TCMSL2
6530123 | PM-ANNUAL - & - TC2 "A" Condensate Hotwell Pump motor clean, inspect & bearings oil change. | TC002CNDCNP2A-PMPMTR | TCMSL2
6530124 | PM-ANNUAL - & - TC2 "B" Condensate Hotwell Pump motor clean, inspect & bearings oil change. | TC002CNDCNP2B-PMPMTR | TCMSL2
6530125 | PM-ANNUAL - & - TC2 "C" Condensate Hotwell Pump motor clean, inspect & bearings oil change. | TC002CNDCNP2C-PMPMTR | TCMSL2
6530140 | PM-ANNUAL-OUTAGE PM - WESP OUTAGE MAINTENANCE INSPECTIONS. | TC002ESPWET | TCMSL2
6530141 | PM-ANNUAL-OUTAGE- DESP OUTAGE MAINTENANCE. | TC002ESPDRY | TCMSL2
6530142 | PM-ANNUAL-OUTAGE- TC2 "A" ID Fan motor bearings- change oil, clean and inspect motor | TC002FG-ID-2A-IDFANMTR | TCMSL2
6530143 | PM-ANNUAL-OUTAGE- TC2 "B" ID Fan motor bearings- change oil, clean and inspect motor | TC002FG-ID-2B-IDFANMTR | TCMSL2
6530145 | PM-ANNUAL-OUTAGE - & - TC2 "A" & "B" ID Fans- Inspection of Impeller heating elements- | TC002FG-ID- | TCMSL2
6530146 | PM-OUTAGE- & - 2A & 2B TDBFP Emergency Oil pump cabinets. - Clean out and check connections. | TC002FW-TFPXIC | TCMSL2
6530147 | PM-ANNUAL OUTAGE - & - TC2- STATOR CONDUTCIVITY perform checks per OEM. | TC002GA-STAXIC | TCMSL2
6530148 | PM-ANNUAL- OUTAGE- Generator maintenace for outages. | TC002EXCEGRXXX | TCMSL2
6530149 | PM-OUTAGE - & - Emergency Seal oil pump Cabinet 2-TSO-EP-002- Clean out and check connections. | TC002GA-STASO-XXX | TCMSL2
6530150 | PM-ANNUAL-OUTAGE- Emergency Seal oil pump motor-Check brushes and wipe clean. Test run and grease | TC002GA-STASO-ESOPMTR | TCMSL2
6530151 | PM-ANNUAL-OUTAGE - & - Pulverizer instrumentation loop checks. | TC002PFCPULA-XIC | TCMSL2
6530152 | PM-ANNUAL-OUTAGE- TC2 "A" Primary Air Fan motor bearings- change oil, clean and inspect motor | TC002PFCPAF2A-FANMTR | TCMSL2
6530153 | PM-ANNUAL-OUTAGE- TC2 "B" Primary Air Fan motor bearings- change oil, clean and inspect motor | TC002PFCPAF2B-FANMTR | TCMSL2
6530154 | PM-ANNUAL - & - TC2 "A" Coal mill motor clean, inspect & bearings oil change- | TC002PFCPULA-MTR | TCMSL2
6530156 | PM-ANNUAL - & - TC2 "B" Coal mill motor clean, inspect & bearings oil change- | TC002PFCPULB-MTR | TCMSL2
6530158 | PM-ANNUAL - & - TC2 "C" Coal mill motor clean, inspect & bearings oil change- | TC002PFCPULC-MTR | TCMSL2
6530160 | PM-ANNUAL - & - TC2 "D" Coal mill motor clean, inspect & bearings oil change- | TC002PFCPULD-MTR | TCMSL2
6530161 | PM-ANNUAL - & - TC2 "E" Coal mill motor clean, inspect & bearings oil change- | TC002PFCPULE-MTR | TCMSL2
6530162 | PM-ANNUAL - & - TC2 "F" Coal mill motor clean, inspect & bearings oil change- | TC002PFCPULF-MTR | TCMSL2
6530163 | PM-SEMI-ANNUAL - & - TC2-"2B" FEEDER, CALIBRATE FEEDER AND | TC002PFCFDR2B- | TCMSL2
6530164 | PM-SEMI-ANNUAL - & -TC2- "2C" FEEDER, CALIBRATE FEEDER AND | TC002PFCFDR2C- | TCMSL2
6530165 | PM-SEMI-ANNUAL - & -TC2- "2D" FEEDER, CALIBRATE FEEDER AND | TC002PFCFDR2D- | TCMSL2
6530166 | PM-SEMI-ANNUAL - & - TC2- "2E" FEEDER, CALIBRATE FEEDER AND | TC002PFCFDR2E- | TCMSL2
6530167 | PM-SEMI-ANNUAL - & - TC2-"2F" FEEDER, CALIBRATE FEEDER AND | TC002PFCFDR2F- | TCMSL2
6530168 | PM-SEMI-ANNUAL - & - TC2-"2A" FEEDER, CALIBRATE FEEDER AND | TC002PFCFDR2A- | TCMSL2
6530230 | PM- SEMI-ANNUAL - & - 2 SCR AMMONIA DETECTOR CALIBRATION | TC002SCRAMMDET | TCMSL2
6530232 | PM- ANNUAL - & - 2 SCR SYSTEM E-STOP CHECK | TC002SCRAMMDET | TCMSL2
6530233 | PM- SEMI-ANNUAL - & - 2 SCR AMMONIA TANK LEVEL CHECK | TC002SCRAMMSTOTNKXIC | TCMSL2
6535518 | PM-ANNUAL - & - 2A HOUSE AIR COMPRESSOR - | TC002CA-HAE | TCMSL6
6535519 | PM-ANNUAL - & - 2B HOUSE AIR COMPRESSOR - | TC002CA-HAE | TCMSL6
6535520 | PM-OUTAGE-ANNUAL - & - 2A INSTRUMENT AIR COMPRESSOR PM - | TC002CA-IAE2A-COMPRESS | TCMSL6
6535521 | PM-OUTAGE-ANNUAL - & - 2B INSTRUMENT AIR COMPRESSOR PM - | TC002CA-IAE2B-COMPRESS | TCMSL6
6535522 | PM-ANNUAL - & - 2A PULSE JET FABRIC FILTER AIR COMPRESSOR | TC002PJFCA-2A-COMP | TCMSL6
6535523 | PM-ANNUAL - & - 2B PULSE JET FABRIC FILTER AIR COMPRESSOR | TC002PJFCA-2B-COMP | TCMSL6
6539199 | PM-OUTAGE-ANNUAL - & - 2A P.A. FAN BEARINGS (DODGE) OIL CHANGE | TC002PFCPAF2A-FAN | TCMSL6
6539200 | PM-OUTAGE-ANNUAL - & - 2B P.A. FAN BEARINGS (DODGE) OIL CHANGE | TC002PFCPAF2B-FAN | TCMSL6
6539201 | PM-OUTAGE-ANNUAL - & - 2A P.A. FAN VISUALLY INSPECTION | TC002PFCPAF2A-FAN | TCMSL6
6539202 | PM-OUTAGE-ANNUAL - & - 2B P.A. FAN VISUAL INSPECTION | TC002PFCPAF2B-FAN | TCMSL6
6539203 | PM-OUTAGE-ANNUAL - & - 2A F.D. FAN VISUAL INSPECTION | TC002CBAFD-2A-FAN | TCMSL6
6539204 | PM-OUTAGE-ANNUAL - & - 2B F.D. FAN VISUAL INSPECTION | TC002CBAFD-2B-FAN | TCMSL6
6539205 | PM-OUTAGE-6 MONTH PM- 2A AIR HEATER GEARBOX OIL CHANGE | TC002CBAAHT2A-RDRVGB | TCMSL6
6539206 | PM-OUTAGE-6 MONTH PM- 2B AIR HEATER GEARBOX OIL CHANGE | TC002CBAAHT2B-RDRVGB | TCMSL6
6539207 | PM-OUTAGE - & - 2A1 AIR HEATER CLUTCH OIL CHANGE | TC002CBAAHT2AA-RDRVCLUTCH | TCMSL6
6539208 | PM-OUTAGE - & - 2A2 AIR HEATER CLUTCH OIL CHANGE | TC002CBAAHT2AB-RDRVCLUTCH | TCMSL6
6539209 | PM-OUTAGE - & - 2B1 AIR HEATER CLUTCH OIL CHANGE | TC002CBAAHT2BA-RDRVCLUTCH | TCMSL6
6539210 | PM-OUTAGE - & - 2B2 AIR HEATER CLUTCH OIL CHANGE | TC002CBAAHT2BB-RDRVCLUTCH | TCMSL6
6539211 | PM-OUTAGE-SEMI-ANNUAL - & - 2A P.A. FAN INSPECTION | TC002PFCPAF2A-FAN | TCMSL6
6539212 | PM-OUTAGE-SEMI-ANNUAL - & - 2B P.A. FAN INSPECTION | TC002PFCPAF2B-FAN | TCMSL6
6539213 | PM-OUTAGE-ANNUAL - & - 2A I.D. FAN VISUAL INSPECTION | TC002FG-ID-2A-IDFAN | TCMSL6
6539214 | PM-OUTAGE-ANNUAL - & - 2B I.D. FAN VISUAL INSPECTION | TC002FG-ID-2B-IDFAN | TCMSL6
6539216 | PM-OUTAGE-ANNUAL- STATOR COOLING SYSTEM FILTER CHANGE | TC002GA-STA-2A-CLGPMP | TCMSL6
6539217 | PM-OUTAGE - & - ANNUALLY- TC2 JACKING OIL PUMP FILTER | TC002TA-JOPSTNR | TCMSL6
6539218 | PM-OUTAGE - & - 2A I.D. FAN BRAKE - INSPECT BRAKE ASSEMBLY | TC002FG-ID-2A-XXX | TCMSL6
6539219 | PM-OUTAGE - & - 2B I.D. FAN BRAKE - INSPECT BRAKE ASSEMBLY | TC002FG-ID-2B-XXX | TCMSL6
6539220 | PM-OUTAGE - & - 2A F.D. FAN BRAKE INSPECT | TC002CBAFD-2A-FAN | TCMSL6
6539221 | PM-OUTAGE - & - 2B F.D. FAN BRAKE INSPECT | TC002CBAFD-2B-FAN | TCMSL6
6539222 | PM-OUTAGE - & - 2A P.A. FAN BRAKE INSPECT | TC002PFCPAF2A-FAN | TCMSL6
6539223 | PM-OUTAGE - & - 2B P.A. FAN BRAKE | TC002PFCPAF2B-FAN | TCMSL6
6539224 | PM-OUTAGE - & - INSPECT TC2 DAMPERS | TC002PLTXXX | TCMSL6
6539225 | PM-OUTAGE - & - 2A P.A. FAN ALIGNMENT AND COUPLING PM | TC002PFCPAF2B-FAN | TCMSL6
6539226 | PM-OUTAGE - & - 2B P.A. FAN ALIGNMENT AND COUPLING PM | TC002PFCPAF2B-FAN | TCMSL6
6539227 | PM-OUTAGE - & - INSPECT 2A & 2B COOLING TOWER BY PASS VALVES | TC002CTHVLV2A-MOV170A | TCMSL6
6539228 | PM-OUTAGE - & - PIN FEEDWATER PIPING HANGERS | TC002FW-FWHPPG | TCMSL6
6539229 | PM-OUTAGE - & - SCAN I.D. & F.D. FAN BLADES | TC002CBAFD-2A-FAN | TCMSL6
6539230 | PM-OUTAGE - & - CLEAN AND INSPECT FUEL STRAINERS | TC002PFCFOEXXX | TCMSL6
6540209 | PM-ANNUAL - & - BOTTOM ASH CHAIN CONVEYOR PLANETARY GEAR REDUCER. DRAIN, FLUSH, REFILL | TC002AH-BAC | TCMSL6
6542192 | PM-ANNUAL - & - TURBINE VAPOR EXTRACTOR CHANGE FILTER | TC002TA-LO-2A-VAPEXT | TCMSL6
6542193 | PM-ANNUAL - & - TURBINE LUBE OIL PURIFIER FILTER CHANGE | TC002TA-LO-OPUCOALFILT | TCMSL6
6542194 | PM-ANNUAL - & - TURBINE LUBE OIL DUPLEX FILTER CHANGE | TC002TA-LO-2A-DUPSTNR | TCMSL6
6497001 | PM-SEMI-ANNUAL - & - 2B PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | TC002PFCPULB | TCPIC
6497002 | PM-SEMI-ANNUAL - & - 2C PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | TC002PFCPULC | TCPIC
6497003 | PM-SEMI-ANNUAL - & - 2D PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | TC002PFCPULD | TCPIC
6499823 | PM-SEMI-ANNUAL - & - 2A PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | TC002PFCPULA | TCPIC
6508203 | PM-SEMI-ANNUAL - & - 2E PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | TC002PFCPULE | TCPIC
6538222 | PM-SEMI-ANNUAL - & - 2F PULVERIZER INSPECTION AND JOURNAL OIL LEVEL CHECK | TC002PFCPULF | TCPIC
6538223 | PM-ANNUAL - & - 2F DYNAMIC CLASSIFIER GEARBOX OIL CHANGE | TC002PFCPULF-CLAS-GB | TCPIC
6538224 | PM-OUTAGE-SEMI-ANNUAL - & - 2F PULVERIZER CLASSIFIER INSPECTION | TC002PFCPULF-CLAS-XXX | TCPIC
6538225 | PM-ANNUAL - & - 2A DYNAMIC CLASSIFIER GEARBOX OIL CHANGE | TC002PFCPULA-CLAS-GB | TCPIC
6538226 | PM-ANNUAL - & - 2B DYNAMIC CLASSIFIER GEARBOX OIL CHANGE | TC002PFCPULB-CLAS-GB | TCPIC
6538227 | PM-ANNUAL - & - 2C DYNAMIC CLASSIFIER GEARBOX OIL CHANGE | TC002PFCPULC-CLAS-GB | TCPIC
6538228 | PM-ANNUAL - & - 2D DYNAMIC CLASSIFIER GEARBOX OIL CHANGE | TC002PFCPULD-CLAS-GB | TCPIC
6538229 | PM-ANNUAL - & - 2E DYNAMIC CLASSIFIER GEARBOX OIL CHANGE | TC002PFCPULE-CLAS-GB | TCPIC
6538230 | PM-OUTAGE-SEMI-ANNUAL - & - 2A PULVERIZER CLASSIFIER INSPECTION | TC002PFCPULA-CLAS-XXX | TCPIC
6538231 | PM-OUTAGE-SEMI-ANNUAL - & - 2B PULVERIZER CLASSIFIER INSPECTION | TC002PFCPULB-CLAS-XXX | TCPIC
6538232 | PM-OUTAGE-SEMI-ANNUAL - & - 2C PULVERIZER CLASSIFIER INSPECTION | TC002PFCPULC-CLAS-XXX | TCPIC
6538233 | PM-OUTAGE-SEMI-ANNUAL - & - 2D PULVERIZER CLASSIFIER INSPECTION | TC002PFCPULD-CLAS-XXX | TCPIC
6538234 | PM-OUTAGE-SEMI-ANNUAL-PM- 2E PULVERIZER CLASSIFIER INSPECTION | TC002PFCPULE-CLAS-XXX | TCPIC

## Capital Detail
TRIMBLE COUNTY STATION
CAPITAL PLAN 2014 @ 100% |  | AS OF 12-6-13
budget_item | budget_description | 2014 | Proponent
133705LGE | TC CBU BKT & CHN REPL | 366247.5333 | Jeff Gray
140616LGE | TC CONVEYOR BELT REPL 2014 | 286648.1333 | Jeff Gray
131615LGE | TC REPLACE STACKER RECL CABL | 206837.76 | Emmett Moore
134072LGE | TC2 AUX BLR WET CHEM LAYUP | 141185.2533 | Adam Raker
140919LGE | TC2 BOILER ROOF TUBE ISSUES | 1189332 | Cisco Maldonado
139771LGE | TC2 CO MONITOR SYSTEM | 715869.04 | Jordan Dorwart
140023LGE | TC2 EHC TEMP CONTROL UPG | 77025.72 | Adam Ball
140378LGE | TC2 HMI UPDATE TURBINE CONTROLS | 58571.16 | Adam Ball
140160LGE | TC2 LST PUMPS-BACKUP | 101911 | Adam Ball
137667LGE | TC2 PA FAN EXT BEARING COOLERS | 102699.1333 | Tyler Turner/ Mark Thomas
140599LGE | TC2 PEGGING STEAM SUPPLY | 76433.2533 | Cisco Maldonado
137671LGE | TC2 PJFF B&C | 1760913.96 | Haley Turner
134110LGE | TC2 SCR Layer 1 Replacement | 3005165.6933 | Jordan Dorwart
139772LGE | TC2 UPG AMMONIA SYSTEM | 77025.72 | Jordan Dorwart
140609LGE | TC2 WESP IMPROVEMENTS | 513507.6533 | Logan Waller
0
| Steam Total 100% | 8679373.0133

## Post Outage Review
Provide a brief overview of the outage start-end dates and times. List lessons learned experiences.
Safety
Outage Safety Incidents
LG&E Medical- 9 Reports:
EMPLOYEE | DATE | INCIDENT DESCRIPTION | LT. TIME | TMD | TMD Days | MEDICAL | First Report | OSHA REP.
Sandra Townsend - Operations | 2014-02-07 | Ankle gave way causing fall to grating - striking right knee |  |  |  |  | Yes
Rick Peak - Mechanical Maint. A | 2014-02-11 | Cut on finger from wrench slipping on wallblower |  |  |  |  | Yes
Charles Baribeau - I/E Shop | 2014-03-16 | Knee sprain |  |  |  | Yes | Yes | Yes
Mark Pardon - Operations | 2014-03-19 | Twisted ankle while walking down stairs |  |  |  |  | Yes
Ben Creech - Operations | 2014-03-20 | Burns on both legs from Arch Flash heat | Yes |  |  | Yes | Yes | Yes
Roy E. Callis (Trey) - Mech Maint. | 2014-04-05 | Walked into valve stem - struck face and cheek |  |  |  |  | Yes
Mark Pardon - Operations | 2014-04-10 | Metal particle in eye |  |  |  | Yes | Yes
Maintenance & Material Handling Ops. | 2014-04-17 | Near Miss - Stacker Reclaimer moved while motors were tested |  |  |  |  | Yes
Bryan Boyer - I/E Shop | 2014-05-01 | Tripped on step in stacker/reclaimer - Near Miss |  |  |  |  | Yes
Totals |  | 9 | 1 | 0 | 0 | 3 | 9 | 2
LG&E Recordables- 2 Reports:
EMPLOYEE | DATE | INCIDENT DESCRIPTION | LT. TIME | TMD | TMD Days | MEDICAL | First Report | OSHA REP.
Charles Baribeau - I/E Shop | 2014-03-16 | Knee sprain |  |  |  | Yes | Yes | Yes
Ben Creech - Operations | 2014-03-20 | Burns on both legs from Arch Flash heat | Yes |  |  | Yes | Yes | Yes
Totals |  | 2 | 1 | 0 | 0 | 2 | 2 | 2
LG&E Contractor Medical- 6 Reports:
CONTRACTOR | DATE | INCIDENT DESCRIPTION | LT. TIME | TMD | TMD Days | MEDICAL | First Report | OSHA REP.
Thompson Industrial Services | 2014-02-18 | Outside control panel on truck caught on fire - extinguised |  |  |  |  | Yes
PIC Group | 2014-03-19 | Struck left hand with hammer - Required Stitches |  |  |  | Yes | Yes | Yes
Thompson Industrial Services | 2014-03-27 | Using washdown hose - Laceration to nose requiring stitches |  |  |  | Yes | Yes | Yes
Tandy Trucking | 2014-04-03 | Truck driver raised dump truck bed - drove into beltway |  |  |  |  | Yes
Early Construction | 2014-04-08 | Fork lift operator dropped a catalyst on the floor. |  |  |  |  | Yes
Youngblood Construction | 2014-04-30 | TC2 ammonia skid- small amount of liquid sprayed on employee |  |  |  | Yes | Yes
Totals |  | 6 | 0 | 0 | 0 | 3 | 6 | 2
LG&E Contractor Recordables- 2 Reports:
CONTRACTOR | DATE | INCIDENT DESCRIPTION | LT. TIME | TMD | TMD Days | MEDICAL | First Report | OSHA REP.
PIC Group | 2014-03-19 | Struck left hand with hammer - Required Stitches |  |  |  | Yes | Yes | Yes
Thompson Industrial Services | 2014-03-27 | Using washdown hose - Laceration to nose requiring stitches |  |  |  | Yes | Yes | Yes
Totals |  | 2 | 0 | 0 | 0 | 2 | 2 | 2
Project Engineering/ Bechtel/ Doosan Safety Report:
CONTRACTOR | DATE | INCIDENT DESCRIPTION | LT. TIME | TMD | TMD Days | MEDICAL | First Report | OSHA REP.
Early Construction (SE Boiler) | 2014-02-10 | Contusion to the right shoulder after slipping on ice (Nightshift ) |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-02-13 | Welder slight burn from a torch (Nightshift) First Aid, gloves were in use. |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-02-20 | Slag burn to the hand (Dayshift) First Aid Gloves were in use. |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-02-24 | Slip on top of a wind box causing a scrape to the hand (Dayshift) Gloves ? |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-02-27 | Changing out a flapper wheel on a grinder and Scratched his hand (Nightshift) No gloves |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-03-15 | Boilermaker using an angle grinder felt a vibration then the blade shattered sending part of the disk through the face shield causing a minor scratch to the cheek and lip. First aid only. (Dayshift) |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-03-30 | Boilermaker stepping off of a scaffold onto grating stumbled and twisted his knee. SEB employee came into work the next day and said he was in pain, went off site to the doctor and was given pain meds. (Recordable injury) |  |  |  | Yes | Yes | Yes
Petrochem | 2014-03-29 | A Petrochem employee was installing a ladder for a scaffold when he stepped backwards on a piece of softner used for rigging. He turned his ankle and was sent offsite to be looked at by a doctor, they took an X-ray which came up negative for injury then returned to work. (Dayshift) |  |  |  | Yes | Yes
Petrochem | 2014-04-04 | A Petrochem employee was working on insulating ductwork when he turned around striking his right shin on the mid-rail of a scaffold he was working off of causing a minor abrasion to his leg, band-aid was applied the returned to work. First aid. (Dayshift) |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-04-15 | Boilermaker taking rigging off a spring can and got his right finger pinched between the can and nut on the hanger, received an abrasion treated with cream and band aid returned to work minor first aid. (Nightshift) |  |  |  | Yes | Yes
Petrochem | 2014-04-22 | Insulator fell through insulation app.25-30’ received scrapes and bruises.(Was not tied off) Recordable injury. (Dayshift) |  |  |  | Yes | Yes | Yes
Petrochem | 2014-04-30 | Petrochem scaffold builder was removing scaffold from inside the furnace when a 4’ piece of clinker fell from above striking him in the leg causing a minor contusion to his R leg. Treated with ice then returned to work.(First aid) (Dayshift) |  |  |  | Yes | Yes
Early Construction (SE Boiler) | 2014-05-02 | Boilermaker walking up the stairs tripped for unknown reasons (no obstacles on the stairs) fell and busted his lip requiring him to received 3 stitches. (Recordable injury) (Dayshift) |  |  |  | Yes | Yes | Yes
Totals |  | 13 | 0 | 0 | 0 | 13 | 13 | 3
Unit shutdown / Clearing and holding equipment.
Unit Offline- Friday, February 7th, 2014.
Unit testing and start-up
Schedule Online- Sunday, May 25th, 2014
Delays:
Burner Commissioning
MFT Logic- Air Heater Sootblower Logic
Actual-Unit Online- May 28th, 2014 @ 04:59 hrs.
Unit Offline- June 1st, 2014 @ 13:49 hrs.- Inst. Air Dryer trip
Unit Online- June 2nd, 2014 @ 20:00 hrs.
Elevators
24 hour coverage during boiler maintenance
Support Team
Improvements suggested: None Reported
Production Team
Improvements suggested: None Reported
X-Ray
Issues: None Reported
Boiler Inspection
None Reported
Laydown
None Reported
Meetings
Improvements suggested: None Reported
Planning Scheduling
None Reported
Misc:
Is GFCI's required to use on TC2? TC2 receptacles should all be protected by GFCI breakers. Will continue to require GFCI pigtails and address as problems are reported.

## Coal Stacker Scope
Coal Stacker Reclaimer Cable Replacement
· Schedule
o 1/24/14 - I/E will be identifying cables and tray that needs to be replaced and verify what is on site and needing to be ordered
o 2/1/14 – Start of TC 2 outage
o 2/10/14 – Start staging materials and prefab any tray or items that can be preassembled
o 3/3/14 – Start demo of cables (Stacker unavailable, unload from the river)
o 3/17/14 – Stacker and E-Belt down for 7 days. Remove cables, tray, and chute. Reinstall cables, tray, and chute. Repair structure as needed.
o 3/31/14 – Stacker returned for service (minimum of travel, hydraulics, and stacking out available)
· Pre-outage checklist
o Verify logic and prints for running E conveyor while stacker is carded
o Clean up stacker a day or two before starting work
o Run R conveyor and perform any PM’s and have Mark Thomas take vibration readings
o Verify all materials are on site before demo starts
· I/E Work
o Cable and Tray
o Terminations
o Checkout
· Mechanical
o Replace chute
o Structure repair/fabrication
Discuss getting a crane and crane operator for the 7 day window
Order materials (beckets, special cables, sealtite and conduit fittings…)
During 7 day shutdown starting 3/17 silos will be filled at 500 ton level to allow ~10 hrs for E belt to be put in service in an emergency
Another meeting will be scheduled in mid-February with more detailed work scopes and refined schedules

## Cooling Tower Insp Scope
o Cooling Tower Inspection- Phelps – Bob Stewart
§ Structural inspection of cooling tower flumes, risers, basin, and supporting structures
§ Will be looking for any fatigue/cracking/exposed rebar.
§ Basin cleanout may be required if there is significant silt accumulation.
§ Maintenance will be responsible for inspecting the cooling tower fill, headers, nozzles, and any needed repairs.

## Reaction Tank Insp Scope
o Reaction Tank Clean-out/Inspection – Heinz/Phelps
§ Melvin & Sons will cleanout out reaction tank once it is drained
§ Inspection will include:
· Wet/dry interface
· Agitators and agitator blade coatings/wear
· Oxidation air piping
· Mist eliminators/chevrons
· Recycle pump piping headers and nozzles
· Tank level indication issues
§ FGD inspection to be completed during first month of outage to allow for WESP work.
§ Any outstanding items found during inspection will be addressed during the outage.

## SCR Scope
o SCR Work - Dorwart
§ Vibratory cleaning and vacuuming of the SCR catalyst layers and inlet
§ Catalyst samples from all layers
§ Change-out Layer 1 with brand new and in-kind replacement layer

## CO Monitor Scope
o CO Monitor Project- Dorwart
§ Installation of a 14 point grid to acquire CO, O2 and Temperature readings in the back pass of TC2
§ Located on landing 13: 8 probes will extend from the south wall and 6 from the north wall
§ Mechanical install by SEBLR for the probe and thermocouple sleeves
§ Electrical and instrumentation installation by Meiners & I/E of data panels, power panels, calibration gas lines, and necessary power wiring and DCS connections

## NH3 Piping Changes
o NH3 Piping changes- Dorwart
§ Bechtel to submit ammonia pump skid modifications and procedural changes to improve performance of ammonia pumps (documentation not yet received)
§ MOC meeting to be held to review all proposed changes
§ Modifications made during the outage

## TC2 HMI Turbine Control Scope
TC2 HMI UPDATE TURBINE CONTROLS
· Scope – The Mark VI HMI computers will be replaced with new computers running up to date Microsoft and GE control software.
· Timeline – Currently scheduled to complete replacement in early April, but subject to change.
· Will need I&E support to test controls once the update has been completed. The exact scope of testing TBD, but will most likely include valve calibrations.

## TC2 EHC Temp Control UPG
TC2 EHC TEMP CONTROL UPG
· Scope – Improve the temperature control for TC2’s EHC tank.
· Timeline – Set point adjustment prior to unit outage if possible and heating system installation TBD.
· First step will be to adjust set point on current temperature control system when allowed by Operations.
· Second step will be the installation of a heating source on the tank to maintain tank temperature when pumps are offline. The exact heating source TBD, but most likely can be accomplished online.

## TC2 LST Pumps Backup
TC2 LST PUMPS-BACKUP
· Scope – Install a redundant limestone slurry recirculation loop from Prep to TC2’s Absorber.
· Timeline – Initial tie-ins TBD, but definitely during the outage. Completion of all other piping and final connections most likely outside of the outage.
· Will install three tees and blank them during the outage and complete remaining piping when possible. Final connections will be made at the next available outage date.

## SSC Scope
Submerged Scrape Conveyer
Scope: The SSC will be inspected and repairs made as needed resulting from the inspection. Additional items will be repaired per previous punchlists and inspections.
· Inspections to include:
1. Wear plate
2. Chain thickness
3. Idlers
4. Basalt tile
5. Take up assembly
6. Overall operation
· Repairs to include:
1. Install basalt tile (Integrity Refractory)
2. Remove chain links
3. Install AR plate on drain box
4. Install new idler pulleys
5. Install side doors and drain lines and valves
6. Repair items as identified per the inspection
Schedule: The inspections will take place after the SSC is rolled out the second time. Target start date is the week of the 2/24/14.
NOTES: Mechanical maintenance will be performing most of the repair work with the exception of installing the basalt tile.

## Roof Tube Scope
TC2 Roof Tube Installation
Scope: 204 transition roof tubes will be replaced on weld line “D” (back pass area). These transition tubes tie in the boiler roof to the cage inlet header. Work is to be performed by early construction.
Schedule: Material is to arrive 2/24/14 and work will begin the same week.

## Boiler Insp Scope
TC2 Boiler Inspections
Scope: Boiler components will be inspected. Inspection items are as follows.
· Wall thickness readings including Amstar thicknesses.
· Backpass/economizer inspection
· Pendant inspection to include superheat and reheat
Schedule: The inspection is scheduled to start 2/24/14 in the backpass. The wall inspections will be done throughout as the burner work allows. Coordination will be made also complete the pendant inspection.
NOTES: The inspections will be performed by Alstom and any repairs will be completed by early construction.

## Boiler Insp Doors
Inspection Doors
Scope: Install inspection doors throughout boiler. Locations have been pre-determined by operations. The doors have 4 tubes (8 welds) and are 11” x 6”. Some refractory will also have to be installed at these locations.
Schedule: Door installation will be performed by Early Construction and is scheduled to start on 2/24/14.

## Pegging Steam Supply Scope
Pegging Steam Supply
Scope: This project is to install a pressure regulating valve and bypass line on the pegging steam supply line from TC1 to TC2.
Schedule: The tentative schedule to start this work is the first week of April.