## Final Acceptance Schedule
2014-01-11 | [8 empty] | 2014-02-11 | [27 empty] | 2014-03-11 | [30 empty] | 2014-04-11 | [29 empty] | 2014-05-11 | [30 empty] | 2014-06-11 | [29 empty] | 2014-07-11 | [30 empty] | 2014-08-11 | [30 empty] | 2014-09-11 | [29 empty] | 2014-10-11 | [29 empty] | 2014-11-11 | [30 empty] | 2014-12-11
[385 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | time axis 2014-01-26 to 2015-02-07
[385 empty] | S | M | T | W | Th | F | S | time axis 2014-01-26 to 2015-02-07
2014-01-11 | 2014-01-18 | 2014-01-25 | 2014-01-26: 2014-02-01; 2014-02-02: 2014-02-08; 2014-02-09: 2014-02-15; 2014-02-16: 2014-02-22; 2014-02-23: 2014-03-01; 2014-03-02: 2014-03-08; 2014-03-09: 2014-03-15; 2014-03-16: 2014-03-22; 2014-03-23: 2014-03-29; 2014-03-30: 2014-04-05; 2014-04-06: 2014-04-12; 2014-04-13: 2014-04-19; 2014-04-20: 2014-04-26; 2014-04-27: 2014-05-03; 2014-05-04: 2014-05-10; 2014-05-11: 2014-05-17; 2014-05-18: 2014-05-24; 2014-05-25: 2014-05-31; 2014-06-01: 2014-06-07; 2014-06-08: 2014-06-14; 2014-06-15: 2014-06-21; 2014-06-22: 2014-06-28; 2014-06-29: 2014-07-05; 2014-07-06: 2014-07-12; 2014-07-13: 2014-07-19; 2014-07-20: 2014-07-26; 2014-07-27: 2014-08-02; 2014-08-03: 2014-08-09; 2014-08-10: 2014-08-16; 2014-08-17: 2014-08-23; 2014-08-24: 2014-08-30; 2014-08-31: 2014-09-06; 2014-09-07: 2014-09-13; 2014-09-14: 2014-09-20; 2014-09-21: 2014-09-27; 2014-09-28: 2014-10-04; 2014-10-05: 2014-10-11; 2014-10-12: 2014-10-18; 2014-10-19: 2014-10-25; 2014-10-26: 2014-11-01; 2014-11-02: 2014-11-08; 2014-11-09: 2014-11-15; 2014-11-16: 2014-11-22; 2014-11-23: 2014-11-29; 2014-11-30: 2014-12-06; 2014-12-07: 2014-12-13; 2014-12-14: 2014-12-20; 2014-12-21: 2014-12-27; 2014-12-28: 2015-01-03; 2015-01-04: Dec 2014; 2015-01-11: Jan 2015; 2015-01-18: 2015-01-24; 2015-01-25: 2015-01-31; 2015-02-01: Feb 2015 | Mar 2015 | Apr 2015 | May 2015 | Jun 2015
TC2 Guarantee Combustion System Completion 12/15/14
(Unless Correction Plan Approved)
2/8
2.3.1 Turbine Generator Capability
2.3.3 Ramp Rates (80-100)% TMCR)
TC2 Guarantee Final Completion 2/13/15 (Unless Correction Plan Approved)
2/10
5/26
6/10
7/17
8/03
30 Day Reliability Run
Burner Modifications Outage
TC2 Shutdown/Cool Down
TC2 RTS / Hot Commissioning/Tuning (Group 1 Fuel)
Target Combustion System Completion 8/27/14
8/25
9/02
Surrogate Thermal Performance and Ammonia Consumption Test
7/23
7/23
Target Final Completion 10/07/14
5 Day Run Group 1 Fuel
7/17
7/22
2.3.3 Ramp Rates (50-80)% TMCR)
7/23
8/27
Unburned Carbon Tests
6/07
6/10
LGE Restart Activities
DRAFT
Combustion Test Group 1 Fuel
7/23
7/27
Group 2 Fuel Set-Up
7/27
7/28
5 Day Run Group 2 Fuel
7/28
8/02
Combustion Test Group 2 Fuel
8/03
8/07
Group 1 Fuel Operation
8/09
8/07
Group 3 Fuel Set-Up
8/09
8/10
5 Day Run Group 3 Fuel
8/10
8/15
Combustion Test Group 3 Fuel
8/16
8/20
Fuel Change Group 2 Fuel
7/27
Fuel Change Group 3 Fuel
8/09
2/13
8/27
7/23
2/13
2/13
10/07
2/13
Group 1 Fuel Stabilization Period
7/23
7/22
8/02
8/03
Group 2 Fuel Stabilization Period
Group 3 Fuel Stabilization Period
8/16
8/15
Note 1: Outage duration based on 50% boiler tube weld X-ray
Note 2: Commissioning period durations subject to change pending commissioning results
Fuel Change Performance Fuel
Performance Fuel Set-Up
8/20
8/20
8/25
Correction Plan to be given
No Later Than 10/15/14
2/13
6/07
5/26
Cold Commissioning
2/10
10/07
10/07
10/07
10/07
7/25