## Sheet1
PROJECT # |  | DESCRIPTION | Total 2014 | O&M Current Estimates/ Actuals | Remainder O&M Outage Funds
TC2S14OUT | Air Quality Control Systems | Chimney flue gutters inspection | 30000 | 40000 | -10000
TC2S14OUT | Air Quality Control Systems | PJFF Repairs (bag detectors, solenoids, door seals, etc…) | 60000 | 52000 | 8000
TC2S14OUT | Air Quality Control Systems | PJFF pulse header J tube inspect for corrosion (2 sections each side) | 10000 | 0 | 10000
TC2S14OUT | Air Quality Control Systems | PJFF Inlet, Outlet & bypassdamper inspection. (some scaffold requ.) | 25000 | 2500 | 22500
TC2S14OUT | Air Quality Control Systems | Pulse Jet Fabric Filter Bags & Cages - CAPITAL Project #137671LGE/KU | 0 | 0 | 0
TC2S14OUT | Air Quality Control Systems | DESP Repairs- (leaks, internal repairs, rappers/ plates) | 50000 | 0 | 50000
TC2S14OUT | Air Quality Control Systems | DESP,WESP plated Electrode Inspection by 3rd Party | 20000 | 25500 | -5500
TC2S14OUT | Air Quality Control Systems | ESP Wash | 100000 | 0 | 100000
TC2S14OUT | Air Quality Control Systems | WESP Repairs (Leaks/ Water Distribution) | 50000 | 0 | 50000
TC2S14OUT | Air Quality Control Systems | Clean WESP Irrigation Headers | 0 | 0 | 0
TC2S14OUT | Ash Handling Systems | Ash Pit Maintenance- refactory, drag chain, Ceramic Tile (incr $70K) | 150000 | 25000 | 125000
TC2S14OUT | Boiler | Boiler Inspection Wall NDE & Wall Insp where hydrojets blow | 75000 | 100000 | -25000
TC2S14OUT | Boiler | Boiler Tube Thickness Mapping | 50000 | 0 | 50000
TC2S14OUT | Boiler | Boiler Amstar coating repair/patching | 0 | 0 | 0
TC2S14OUT | Boiler | Boiler Repairs (tubes, welds, etc.) | 250000 | 0 | 250000
TC2S14OUT | Boiler | Boiler Deslag | 20000 | 11853 | 8147
TC2S14OUT | Boiler | Boiler Inspection Door installation | 0 | 60000 | -60000
TC2S14OUT | Boiler | Sootbloweer control vavles | 30000 | 8000 | 22000
TC2S14OUT | Boiler | Overhaul Hydrojet water cannons (4) | 120000 | 0 | 120000
TC2S14OUT | Boiler | PORV Electromatic Relief Valve repairs (2) (increase $100K) | 150000 | 0 | 150000
TC2S14OUT | Boiler | SH Sparay Valve overhauls (4) (increased $230K) | 230000 | 28000 | 202000
TC2S14OUT | Boiler | RH Spray valve rebuild | 100000 | 8000 | 92000
TC2S14OUT | Boiler | soot blower pressure regulating valve rebuild | 0 | 0 | 0
TC2S14OUT | Boiler | O2 Probes | 0 | 2500 | -2500
TC2S14OUT | Circulating Water | NDCT header/seal Insp. | 10000 | 0 | 10000
TC2S14OUT | Circulating Water | Cooling Tower Pump Motors | 0 | 4500 | -4500
TC2S14OUT | Condenser | Condensor NDE Repair | 20000 | 15000 | 5000
TC2S14OUT | Condenser | Condenser Vacuum Pump casing leak | 0 | 5000 | -5000
TC2S14OUT | Draft Equipment | Air Heater Wash | 40000 | 30000 | 10000
TC2S14OUT | Draft Equipment | Air Heater Repairs | 25000 | 4000 | 21000
TC2S14OUT | Draft Equipment | Fan Inspections (Serviceman/Blades) ID,FD,PA | 40000 | 16000 | 24000
TC2S14OUT | Draft Equipment | ID Fan Motor Inspection | 35000 | 10000 | 25000
TC2S14OUT | Draft Equipment | ID Fan - Install Spare Hub (1) | 0 | 0 | 0
TC2S14OUT | Draft Equipment | FD & PA Fan Motor Inspections | 50000 | 16000 | 34000
TC2S14OUT | Draft Equipment | FD Fan Rebuild Hub/fan (2) | 0 | 0 | 0
TC2S14OUT | Draft Equipment | Expansion Joint Repair and Shields | 250000 | 20000 | 230000
TC2S14OUT | Draft Equipment | Duct work | 300000 | 2500 | 297500
TC2S14OUT | Electrical | Switchgear Maintenance | 50000 | 0 | 50000
TC2S14OUT | Electrical | Temporary Power | 0 | 5000 | -5000
TC2S14OUT | Feedwater Systems | Valve Inspections | 60000 | 30000 | 30000
TC2S14OUT | Feedwater Systems | Reset safeties | 40000 | 15000 | 25000
TC2S14OUT | Feedwater Systems | MBBFP motor inspection | 25000 | 0 | 25000
TC2S14OUT | Feedwater Systems | BCP recirc & HP/LP bypass valve pull & Insp. | 25000 | 37000 | -12000
TC2S14OUT | Feedwater Systems | TDBFP Recirc Valve Overhauls | 150000 | 40000 | 110000
TC2S14OUT | Feedwater Systems | Deaerator NDE | 23000 | 30000 | -7000
TC2S14OUT | Feedwater Systems | Feedwater Heater Diaphragms | 0 | 4000 | -4000
TC2S14OUT | Feedwater Systems | 2B TDBFP Booster Pump Mechanical Seal Leaking | 0 | 6000 | -6000
TC2S14OUT | FGD | FGD Reactant Tank Cleanout/Inspect, Nozzle repairs (incr. $75K) | 75000 | 0 | 75000
TC2S14OUT | FGD | Reaction Tank Agitater Overhaul | 0 | 0 | 0
TC2S14OUT | FGD | Repair Reaction Tank Agitater Blades | 100000 | 0 | 100000
TC2S14OUT | FGD | Recycle Pump motor oil change | 0 | 1200 | -1200
TC2S14OUT | FGD | Recycle Pump seal water line. | 0 | 1000 | -1000
TC2S14OUT | FGD | TC2 Gypsum Line | 0 | 8880 | -8880
TC2S14OUT | High Energy Piping | HEP piping and hanger repairs from inspections | 150000 | 0 | 150000
TC2S14OUT | Material Handling | Overhaul & Clean A Ball Mill Motor- Completed | 25000 | 0 | 25000
TC2S14OUT | Material Handling | Reactant Prep "A" Ball mill gearbox changeout. | 0 | 90000 | -90000
TC2S14OUT | Misc/ Common | Industrial Cleaning | 200000 | 32000 | 168000
TC2S14OUT | Misc/ Common | Scaffolding | 100000 | 0 | 100000
TC2S14OUT | Misc/ Common | inspect for leakage. (Air-in)? | 25000 | 0 | 25000
TC2S14OUT | Misc/ Common | Service Reps- Alstom, Howden, MD&A, Diamond Power) | 150000 | 0 | 150000
TC2S14OUT | Misc/ Common | Instrument Air Compressor Motor Overaul | 24000 | 0 | 24000
TC2S14OUT | Misc/ Common | 2A & 2B Inst. Air Dryers | 0 | 6000 | -6000
TC2S14OUT | Pulverizers | PA Fan - Inspect bearings and input damper linkage | 25000 | 0 | 25000
TC2S14OUT | Pulverizers | Pulverizer Inspections | 0 | 13500 | -13500
TC2S14OUT | Pulverizers | Pulverizer Inerting steam valves | 0 | 30000 | -30000
TC2S14OUT | Pulverizers | Pulverizer 2D Classifier Motor | 0 | 1500 | -1500
TC2S14OUT | SCR | Vacuum & Inspect SCR catalyst (increased $135K) | 75000 | 10000 | 65000
TC2S14OUT | SCR | NH3 detectors | 0 | 3300 | -3300
TC2S14OUT | Turbine/ Generator | Main Turbine LP Blade Inspect | 60000 | 60000 | 0
TC2S14OUT | Turbine/ Generator | Turbine Extraction Steam Check Valves Overhaul | 30000 | 0 | 30000
TC2S14OUT | Turbine/ Generator | Turbine Main Steam Valve Inspection move to 2016 | 0 | 0 | 0
TC2S14OUT | Turbine/ Generator | Generator Maintenance | 0 | 2000 | -2000
TC2S14OUT | Turbine/ Generator | TC2 Turbine/ Generator #11 Bearing leak | 0 | 5000 | -5000
TC2S14OUT | Turbine/ Generator | 2A Turbine oil cooler clean | 0 | 35000 | -35000
TC2S14OUT | Turbine/ Generator | TC2 Turbine Expansion Joints- 2018 | 0 | 0 | 0
|  | TOTALS | 3702000 | 952733 | 2749267