## CAPITAL 100%
1 for Current & Prev Months
Capital Expenditures @ 100% (GROSS)
Trimble County Station
December, 2014
Actual
|  | Project |  | Yr to Date-14
|  | Total | Act / Frcst | 11873005.5
|  |  | App Frcst | 14121343.4567
|  |  | Prior Frcst | 12081509.4867
|  |  | Var to App | 2248337.9567
|  |  | Var to Prior | 208503.9867
|  | 131607LGE | Act / Frcst | 104316.87
|  | TC SDRS REACTANT TANK ROOF | App Frcst | 305733
|  | AIP APPROVED: YES | Prior Frcst | 113754.67
|  | GEN CAP: RELIABILITY | Var to App | 201416.13
|  |  | Var to Prior | 9437.8
|  | 131615LGE | Act / Frcst | 346510.61
|  | TC REPLACE STACKER RECL CABL | App Frcst | 205894.1867
|  | AIP APPROVED: YES | Prior Frcst | 346701.42
|  | GEN CAP: RELIABILITY | Var to App | -140616.4233
|  |  | Var to Prior | 190.81
|  | 133614LGE | Act / Frcst | 0
|  | TC ENG/MTR RWNDS 2014 | App Frcst | 277672.4533
|  | AIP APPROVED: N/A | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 277672.4533
|  |  | Var to Prior | 0
|  | 133621LGE | Act / Frcst | 112725.53
|  | TC LAB MONITORS 2014 | App Frcst | 97508.9467
|  | AIP APPROVED: YES | Prior Frcst | 95905.6467
| 7 | GEN CAP: RELIABILITY | Var to App | -15216.5833
|  |  | Var to Prior | -16819.8833
|  | 133652LGE | Act / Frcst | 43197.16
|  | TC SAFETY/ERT EQUIP 2014 | App Frcst | 61733.96
|  | AIP APPROVED: YES | Prior Frcst | 43228.93
|  | GEN CAP: RELIABILITY | Var to App | 18536.8
|  |  | Var to Prior | 31.77
|  | 133669LGE | Act / Frcst | 73596.56
|  | TC LSTN BALL MILL FIRE PROT | App Frcst | 36284.0667
|  | AIP APPROVED: YES | Prior Frcst | 86525.4067
|  | GEN CAP: RELIABILITY | Var to App | -37312.4933
|  |  | Var to Prior | 12928.8467
|  | 133675LGE | Act / Frcst | 13068.13
|  | TC CATHODIC PROTECTION LGE | App Frcst | 51735.3067
|  | AIP APPROVED: YES | Prior Frcst | 13577.8233
|  | GEN CAP: RELIABILITY | Var to App | 38667.1767
|  |  | Var to Prior | 509.6933
|  | 133681LGE | Act / Frcst | 45182.26
|  | TC PREDICTIVE MTCE | App Frcst | 20382.2
|  | AIP APPROVED: YES | Prior Frcst | 45182.26
|  | GEN CAP: RELIABILITY | Var to App | -24800.06
|  |  | Var to Prior | 0
|  | 133701LGE | Act / Frcst | 193911.11
|  | TC REPL C SVC BLDG CHLR | App Frcst | 230150.9333
|  | AIP APPROVED: YES | Prior Frcst | 174714.74
|  | GEN CAP: RELIABILITY | Var to App | 36239.8233
|  |  | Var to Prior | -19196.37
|  | 133705LGE | Act / Frcst | 120385.72
|  | TC CBU BKT & CHN REPL | App Frcst | 366247.5333
|  | AIP APPROVED: YES | Prior Frcst | 161552.43
|  | GEN CAP: RELIABILITY | Var to App | 245861.8133
|  |  | Var to Prior | 41166.71
|  | 133712 | Act / Frcst | 0
|  | TC1 SCR CAT L3 RE-GEN | App Frcst | 305733
|  | CANCEL | Prior Frcst | 0
|  | GEN CAP: ENVIRONMENTAL | Var to App | 305733
|  |  | Var to Prior | 0
|  | 134072LGE | Act / Frcst | 34912.01
|  | TC2 AUX BLR WET CHEM LAYUP | App Frcst | 141185.2533
|  | AIP APPROVED: YES | Prior Frcst | 34379.3
|  | GEN CAP: RELIABILITY | Var to App | 106273.2433
|  |  | Var to Prior | -532.71
|  | 134110LGE | Act / Frcst | 1495724.14
|  | TC2 SCR Layer 1 Replacement | App Frcst | 3006666.6667
|  | AIP APPROVED: YES | Prior Frcst | 1495724.14
|  | GEN CAP: ENVIRONMENTAL | Var to App | 1510942.5267
|  |  | Var to Prior | 375
|  | 134362 | Act / Frcst | 0
|  | TC1 REPLACE AIR HEATER BASKETS | App Frcst | 203822
|  | CANCEL | Prior Frcst | 0
|  | GEN CAP: OTHER | Var to App | 203822
|  |  | Var to Prior | 0
|  | 137667LGE | Act / Frcst | 0
|  | TC2 PA FAN EXT BEARING COOLERS | App Frcst | 102699.1333
|  | CANCEL | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 102699.1333
|  |  | Var to Prior | 0
|  | 137671LGE | Act / Frcst | 1374112.92
|  | TC2- PJFF BAGS & CAGES | App Frcst | 2571831.3333
|  | AIP APPROVED: YES | Prior Frcst | 1374112.92
|  | GEN CAP: ENVIRONMENTAL | Var to App | 1197718.4133
|  |  | Var to Prior | 0
|  | 138393 | Act / Frcst | 202504.64
|  | TC1 UPPER ARCH | App Frcst | 203822
|  | AIP APPROVED: YES | Prior Frcst | 199938.96
|  | GEN CAP: BOILER TUBES | Var to App | 1317.36
|  |  | Var to Prior | -2565.68
|  | 139763LGE | Act / Frcst | 124045.71
|  | TC ACID INJECTION FLYASH | App Frcst | 122853.6533
|  | AIP APPROVED: YES | Prior Frcst | 123836.68
|  | GEN CAP: RELIABILITY | Var to App | -1192.0567
|  |  | Var to Prior | -209.03
|  | 139770LGE | Act / Frcst | 27076.14
|  | TC FIRE PROTECTION SERV BUILD | App Frcst | 153567.0667
|  | AIP APPROVED: YES | Prior Frcst | 39934.8
|  | GEN CAP: RELIABILITY | Var to App | 126490.9267
|  |  | Var to Prior | 12858.66
|  | 139771LGE | Act / Frcst | 709254.14
|  | TC2 CO MONITOR SYSTEM | App Frcst | 718893.9067
|  | AIP APPROVED: YES | Prior Frcst | 717127.7967
|  | GEN CAP: RELIABILITY | Var to App | 9639.7667
|  |  | Var to Prior | 7873.6567
|  | 139772LGE | Act / Frcst | 0
|  | TC2 UPG AMMONIA SYSTEM | App Frcst | 77025.72
|  | CANCEL | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 77025.72
|  |  | Var to Prior | 0
|  | 139778LGE | Act / Frcst | 64022.95
|  | TC UPG PIPING FLY ASH SILO | App Frcst | 127972.5467
|  | AIP APPROVED: YES | Prior Frcst | 64022.95
|  | GEN CAP: RELIABILITY | Var to App | 63949.5967
|  |  | Var to Prior | 0
|  | 140023LGE | Act / Frcst | 121763.14
|  | TC2 EHC TEMP CONTROL UPG | App Frcst | 77025.72
|  | AIP APPROVED: YES | Prior Frcst | 167231.5467
|  | GEN CAP: RELIABILITY | Var to App | -44737.42
|  |  | Var to Prior | 45468.4067
|  | 140160LGE | Act / Frcst | 48223.73
|  | TC2 LST PUMPS-BACKUP | App Frcst | 101911
|  | AIP APPROVED: YES | Prior Frcst | 72774.8367
|  | GEN CAP: RELIABILITY | Var to App | 53687.27
|  |  | Var to Prior | 24551.1067
|  | 140234LGE | Act / Frcst | 381499.89
|  | TC2 TURBINE COUPLING BOLTS | App Frcst | 410796.52
|  | AIP APPROVED: YES | Prior Frcst | 381339.4267
|  | GEN CAP: RELIABILITY | Var to App | 29296.63
|  |  | Var to Prior | -160.4633
|  | 140378LGE | Act / Frcst | 65164.71
|  | TC2 HMI UPDATE TURB CONTROL | App Frcst | 103038.84
|  | AIP APPROVED: YES | Prior Frcst | 65197.3367
|  | GEN CAP: RELIABILITY | Var to App | 37874.13
|  |  | Var to Prior | 32.6267
|  | 140597LGE | Act / Frcst | 0
|  | TC GAS IGNITION FUEL | App Frcst | 407644
|  | AIP APPROVED: YES | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 407644
|  |  | Var to Prior | 0
|  | 140599LGE | Act / Frcst | 202667.28
|  | TC2 PEGGING STEAM SUPPLY | App Frcst | 76433.2533
|  | AIP APPROVED: YES | Prior Frcst | 219285.7267
|  | GEN CAP: RELIABILITY | Var to App | -126234.0267
|  |  | Var to Prior | 16618.4467
|  | 140609LGE | Act / Frcst | 385620.48
|  | TC2 WESP IMPROVEMENTS | App Frcst | 513495.6533
|  | AIP APPROVED: YES | Prior Frcst | 390389.3733
|  | GEN CAP: RELIABILITY | Var to App | 127875.1733
|  |  | Var to Prior | 4768.8933
|  | 140612LGE | Act / Frcst | 311180.34
|  | TC2 STATIC EXCITER TRANSFORMER | App Frcst | 462146.0933
|  | AIP APPROVED: YES | Prior Frcst | 293360.9967
|  | GEN CAP: RELIABILITY | Var to App | 150965.7533
|  |  | Var to Prior | -17819.3433
|  | 140616LGE | Act / Frcst | 0
|  | TC CONVEYOR BELT REPL 2014 | App Frcst | 286648.1333
|  | CANCEL | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 286648.1333
|  |  | Var to Prior | 0
|  | 140919LGE | Act / Frcst | 1125159.01
|  | TC2 TRANSITION TUBE REPL | App Frcst | 821593.04
|  | AIP APPROVED: YES | Prior Frcst | 1125159.01
|  | GEN CAP: RELIABILITY | Var to App | -303565.97
|  |  | Var to Prior | 0
|  | 142496 | Act / Frcst | 283548.82
|  | TC1 BENTLY NEVADA PHASE II | App Frcst | 270064.1467
|  | AIP APPROVED: YES | Prior Frcst | 267009.4
|  | GEN CAP: OTHER | Var to App | -13484.6733
|  |  | Var to Prior | -16539.42
|  | 137646 | Act / Frcst | -331204.39
|  | TC1 BOILER Reheat FPOL Assem | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -331204.39
|  | GEN CAP: RELIABILITY | Var to App | 331204.39
|  |  | Var to Prior | 0
|  | 137647 | Act / Frcst | -55908.86
|  | TC1 BOILER Final SH Assemb | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -55908.86
|  | GEN CAP: RELIABILITY | Var to App | 55908.86
|  |  | Var to Prior | 0
|  | 137650 | Act / Frcst | -53214.82
|  | TC1 BOILER UP REAR ARCH PNLS | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -53214.82
|  | GEN CAP: RELIABILITY | Var to App | 53214.82
|  |  | Var to Prior | 0
|  | 142961 | Act / Frcst | -3756.89
|  | TC1 CAP SALVAGE EQUIPMENT | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -1024.59
|  | GEN CAP: OTHER | Var to App | 3756.89
|  |  | Var to Prior | 2732.3
|  | 142966LGE | Act / Frcst | -746.72
|  | TC CRUSHER MOTOR RWD | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -746.72
|  | GEN CAP: RELIABILITY | Var to App | 746.72
|  |  | Var to Prior | 0
|  | 142987LGE | Act / Frcst | 0
|  | TC LGE LIC VEHICLES 2013 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 0
|  |  | Var to Prior | 0
|  | 142989LGE | Act / Frcst | 12119.86
|  | TC OFFICE REBUILD 2013 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 12119.86
|  | GEN CAP: RELIABILITY | Var to App | -12119.86
|  |  | Var to Prior | 0
|  | 143320LGE | Act / Frcst | 28795.54
|  | TC MACHINE SHOP EQUIPMENT | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 28795.54
|  | GEN CAP: OTHER | Var to App | -28795.54
|  |  | Var to Prior | 0
|  | 137631LGE | Act / Frcst | 8266.92
|  | TC2 RECIRC LOOP | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 8266.92
|  | GEN CAP: RELIABILITY | Var to App | -8266.92
|  |  | Var to Prior | 0
|  | 131627LGE | Act / Frcst | 1458.69
|  | TC1 BENTLY NEVADA UPG | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 1458.69
|  | GEN CAP: RELIABILITY | Var to App | -1458.69
|  |  | Var to Prior | 0
|  | 131619 | Act / Frcst | -307.4
|  | TC1 DUCTWORK EXPANSION JOINT | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -307.4
|  | GEN CAP: RELIABILITY | Var to App | 307.4
|  |  | Var to Prior | 0
|  | 132091 | Act / Frcst | 2079.73
|  | TC1 SCR Catalyst Re-gen | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 2079.73
|  | GEN CAP: RELIABILITY | Var to App | -2079.73
|  |  | Var to Prior | 0
|  | 133561LGE | Act / Frcst | -1663.74
|  | TC LAB EQUIP PURCH 2013 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -1663.7533
|  | GEN CAP: RELIABILITY | Var to App | 1663.74
|  |  | Var to Prior | -0.013333
|  | 142705LGE | Act / Frcst | -57812.9
|  | TC DOZER 2013 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -57618.2
|  | GEN CAP: OTHER | Var to App | 57812.9
|  |  | Var to Prior | 194.7
|  | 134231 | Act / Frcst | 23853.48
|  | TC1 DCS UPGRADE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 23853.48
|  | GEN CAP: OTHER | Var to App | -23853.48
|  |  | Var to Prior | 0
|  | 143585LGE | Act / Frcst | 252611.45
|  | TC2 SCR ASH SWEEPER | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 252611.45
|  | GEN CAP: RELIABILITY | Var to App | -252611.45
|  |  | Var to Prior | 0
|  | 143792LGE | Act / Frcst | 27011.1
|  | TC RWD B COAL CONVEYOR MTR | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 27011.1
|  | GEN CAP: RELIABILITY | Var to App | -27011.1
|  |  | Var to Prior | 0
|  | 144460LGE | Act / Frcst | 151409.53
|  | TC OFFICE REBUILD 2014 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 151198.32
|  | GEN CAP: RELIABILITY | Var to App | -151409.53
|  |  | Var to Prior | -211.21
|  | 144462 | Act / Frcst | 26558.23
|  | TC1 COAL FLOW ANALYZER TRIAL SYST | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 26572.85
|  | GEN CAP: RELIABILITY | Var to App | -26558.23
|  |  | Var to Prior | 14.62
|  | 134111LGE | Act / Frcst | 398620.14
|  | TC2 SCR L2 REPL 2016 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 433958.16
|  | GEN CAP: RELIABILITY | Var to App | -398620.14
|  |  | Var to Prior | 35338.02
|  | 144655LGE | Act / Frcst | 15645.39
|  | TC WATER TREATMENT RO SYSTEM UPGRADE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 15645.39
|  | GEN CAP: RELIABILITY | Var to App | -15645.39
|  |  | Var to Prior | 0
|  | 144649LGE | Act / Frcst | 418592.08
|  | TC BAP N DIKE INTERIOR SLOPE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 413100.83
|  | GEN CAP: RELIABILITY | Var to App | -418592.08
|  |  | Var to Prior | -5491.25
|  | 144651LGE | Act / Frcst | 171139.75
|  | TC BAP N DIKE EXTERIOR SLOPE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 185462.48
|  | GEN CAP: RELIABILITY | Var to App | -171139.75
|  |  | Var to Prior | 14322.73
|  | 144653LGE | Act / Frcst | 195597.89
|  | TC BAP W DIKE EXTERIOR SLOPE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 169045.96
|  | GEN CAP: RELIABILITY | Var to App | -195597.89
|  |  | Var to Prior | -26551.93
|  | 144699LGE | Act / Frcst | 246186.44
|  | TC2 FD FAN BLADE REPLACEMENT | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 246186.44
|  | GEN CAP: RELIABILITY | Var to App | -246186.44
|  |  | Var to Prior | 0
|  | 144684LGE | Act / Frcst | 21338.88
|  | TC2 SVC ELEVATOR UPGRADE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 21338.88
|  | GEN CAP: RELIABILITY | Var to App | -21338.88
|  |  | Var to Prior | 0
|  | 145036LGE | Act / Frcst | 16760.55
|  | TC CEM COAL UNIT SERVER | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 6770
|  | GEN CAP: RELIABILITY | Var to App | -16760.55
|  |  | Var to Prior | -9990.55
|  | 145848LGE | Act / Frcst | 34444.26
|  | TC LAPPING MACHINE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 34453.07
|  | GEN CAP: RELIABILITY | Var to App | -34444.26
|  |  | Var to Prior | 8.81
|  | 145878LGE | Act / Frcst | 89465.41
|  | TC RO MEMBRANE SYSTEM UPGRADE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 88262.17
|  | GEN CAP: RELIABILITY | Var to App | -89465.41
|  |  | Var to Prior | -1203.24
|  | 146010LGE | Act / Frcst | 173722.23
|  | TC2 TURBINE TRIP BLOCK | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 157242.34
|  | GEN CAP: RELIABILITY | Var to App | -173722.23
|  |  | Var to Prior | -16479.89
|  | 146200LGE | Act / Frcst | 39692.03
|  | TC BOILER SWING STAGE EQUIPMENT | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 39702.38
|  | GEN CAP: RELIABILITY | Var to App | -39692.03
|  |  | Var to Prior | 10.35
|  | 146202 | Act / Frcst | 48708.37
|  | TC1 COAL MILL MOTOR REWIND | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 48708.37
|  | GEN CAP: RELIABILITY | Var to App | -48708.37
|  |  | Var to Prior | 0
|  | 146294LGE | Act / Frcst | 119994.03
|  | TC2 R-PUMP EXP JOINT UPG | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 132356.39
|  | GEN CAP: RELIABILITY | Var to App | -119994.03
|  |  | Var to Prior | 12362.36
|  | 131591 | Act / Frcst | 0
|  | TC1 TURBINE CRANE CONTROLS | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 0
|  |  | Var to Prior | 0
|  | 133607LGE | Act / Frcst | -17205.99
|  | TC AC MOTOR FILTER UPG | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -17205.99
|  | GEN CAP: RELIABILITY | Var to App | 17205.99
|  |  | Var to Prior | 0
|  | 137645 | Act / Frcst | 0
|  | TC1 BOILER FLSPPR | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 0
|  |  | Var to Prior | 0
|  | 133561LGE | Act / Frcst | -1663.74
|  | TC LAB EQUIP PURCH 2013 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -1663.7533
|  | GEN CAP: RELIABILITY | Var to App | 1663.74
|  |  | Var to Prior | -0.013333
|  | 146262LGE | Act / Frcst | -40000
|  | TC SCRAP BELT PROCEEDS | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | -40000
|  | GEN CAP: RELIABILITY | Var to App | 40000
|  |  | Var to Prior | 0
|  | 146321LGE | Act / Frcst | 20195.8
|  | TC2 TURBINE & FP CONTROLS REPLACEMENT | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 26726.8933
|  | GEN CAP: RELIABILITY | Var to App | -20195.8
|  |  | Var to Prior | 6531.0933
|  | 146343LGE | Act / Frcst | 13342.2
|  | TC2 AIR DRAFT ACCESS PLATFORM | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 35703.8733
|  | GEN CAP: RELIABILITY | Var to App | -13342.2
|  |  | Var to Prior | 22361.6733
|  | 146345LGE | Act / Frcst | 47275.03
|  | TC FLY ASH ACCESS PLATFORM | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 22213.4667
|  | GEN CAP: RELIABILITY | Var to App | -47275.03
|  |  | Var to Prior | -25061.5633
|  | 146419LGE | Act / Frcst | 76122.94
|  | TC AIR HEATER SERVICE WATER LINE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 91256.1833
|  | GEN CAP: RELIABILITY | Var to App | -76122.94
|  |  | Var to Prior | 15133.2433
|  | 146487LGE | Act / Frcst | 29681.71
|  | TC BAP RAFT FLOAT UPG | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 72252.4967
|  | GEN CAP: RELIABILITY | Var to App | -29681.71
|  |  | Var to Prior | 42570.7867
|  | 146489LGE | Act / Frcst | 75776.85
|  | TC LST AGITATOR GEARBOX & BLADES | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 86354.1333
|  | GEN CAP: RELIABILITY | Var to App | -75776.85
|  |  | Var to Prior | 10577.2833
|  | 146491LGE | Act / Frcst | 26662.95
|  | TC WORK OUT ROOM REBUILD | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 25116.3467
|  | GEN CAP: RELIABILITY | Var to App | -26662.95
|  |  | Var to Prior | -1546.6033
|  | 146496 | Act / Frcst | 39387.88
|  | TC VEHICLES 2014 | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 39934.8
|  | GEN CAP: RELIABILITY | Var to App | -39387.88
|  |  | Var to Prior | 546.92
|  | 146536LGE | Act / Frcst | 6215.32
|  | TC LP GAS WELDER | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 6988.5867
|  | GEN CAP: RELIABILITY | Var to App | -6215.32
|  |  | Var to Prior | 773.2667
|  | 146538LGE | Act / Frcst | 25867.71
|  | TC COUPLING F1 & F2 CONVEYORS | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 28359.3067
|  | GEN CAP: RELIABILITY | Var to App | -25867.71
|  | 131612 | Act / Frcst | -34.06
|  | TC1 SCR STRUCT STEEL | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 34.06
|  | 134112LGE | Act / Frcst | 687798.07
|  | TC CT INSTALL AUX TRANS | App Frcst | 615143.94
|  | AIP APPROVED: YES | Prior Frcst | 654184.7
|  | GEN CAP: RELIABILITY | Var to App | -72654.13
|  |  | Var to Prior | -33613.37
|  | 139799LGE | Act / Frcst | 0
|  | TC CT UPGD NITRO PURGE SYS | App Frcst | 76433.25
|  | CANCEL | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 76433.25
|  |  | Var to Prior | 0
|  | 140012LGE | Act / Frcst | 201596.14
|  | TC CT HMI UPGRADE | App Frcst | 509555
|  | AIP APPROVED: YES | Prior Frcst | 201596.14
|  | GEN CAP: RELIABILITY | Var to App | 307958.86
|  |  | Var to Prior | 0
|  | 142880LGE | Act / Frcst | 1952.25
|  | TC CT8 BLADING ISSUE | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 1952.25
|  | GEN CAP: RELIABILITY | Var to App | -1952.25
|  |  | Var to Prior | 0
|  | 143726LGE | Act / Frcst | 314069.43
|  | TC CT REFURB SPARE BLADES | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 325504.81
|  | GEN CAP: RELIABILITY | Var to App | -314069.43
|  |  | Var to Prior | 11435.38
|  | 143867LGE | Act / Frcst | 0
|  | TC CT 7-10 89SS SWITCH REPL | App Frcst | 0
4 |  | CANCEL | Prior Frcst | 0
|  | GEN CAP: RELIABILITY | Var to App | 0
|  |  | Var to Prior | 0
|  | 146014LGE | Act / Frcst | 263119.22
|  | TC CT CEM ANALYZERS | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 302276.36
|  | GEN CAP: RELIABILITY | Var to App | -263119.22
|  |  | Var to Prior | 39157.14
|  | 146300LGE | Act / Frcst | 66233.22
|  | TC CT FIRE PROTECTION UPGD | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 70252.72
|  | GEN CAP: RELIABILITY | Var to App | -66233.22
|  |  | Var to Prior | 4019.5
|  | 146543LGE | Act / Frcst | 7782.31
|  | TC CT COMPRESSOR ROOM MODIFICATION | App Frcst | 0
|  | AIP APPROVED: YES | Prior Frcst | 13225.57
|  | GEN CAP: RELIABILITY | Var to App | -7782.31
|  |  | Var to Prior | 5443.26
|  | 5 | Act / Frcst | 0
|  | #N/A | App Frcst | 0
|  | #N/A | Prior Frcst | 0
|  | #N/A | Var to App | 0
|  |  | Var to Prior | 0

## Sheet1
Project | Yr to Date-14
TC2 SCR Layer 1 Replacement | 3006666.6667
TC2 UPG AMMONIA SYSTEM | 77025.72
TC2 EHC TEMP CONTROL UPG | 77025.72
TC2 TURBINE COUPLING BOLTS | 410796.52
TC2 WESP IMPROVEMENTS | 513495.6533
TC2 TRANSITION TUBE REPL | 821593.04
Subtotal: | 4906603.32
TC2 AUX BLR WET CHEM LAYUP | 141185.2533
TC2 PA FAN EXT BEARING COOLERS | 102699.1333
TC2- PJFF BAGS & CAGES | 2571831.3333
TC2 CO MONITOR SYSTEM | 718893.9067
TC2 LST PUMPS-BACKUP | 101911
TC2 HMI UPDATE TURB CONTROL | 103038.84
TC2 PEGGING STEAM SUPPLY | 76433.2533
TC2 STATIC EXCITER TRANSFORMER | 462146.0933
TC2 RECIRC LOOP | 0
TC2 SCR ASH SWEEPER | 0
TC2 SCR L2 REPL 2016 | 0
TC2 FD FAN BLADE REPLACEMENT | 0
TC2 SVC ELEVATOR UPGRADE | 0
TC2 TURBINE TRIP BLOCK | 0
TC2 R-PUMP EXP JOINT UPG | 0
TC2 TURBINE & FP CONTROLS REPLACEMENT | 0
TC2 AIR DRAFT ACCESS PLATFORM | 0