## Case Timeline
Complete |  | Kentucky Power Company
On Time |  | Filing Timeline for
At risk of delay |  | 2014 Base Case
Behind schedule
Responsible Party
2014-04-01 |  | Start Depreciation Study | Dave Davis
2014-04-01 |  | Review new filing requirements | Kentucky Office/Counsel
May/June/July 2014 |  | Meetings with customer field personnel discussing tariff issues to be addressed | Kentucky Office
2014-06-17 |  | Strategy Meeting- Columbus | Core Team
Early August 2014 |  | Contract ROE witness | Shelli Sloan
2014-08-28 |  | All Hands/Kick off Meeting | Shelli Sloan
Early September 2014 |  | COS spreadsheet template finalized | Shannon Listebarger/Alex Vaughan
2014-09-30 |  | Get ROE from Outside Witness | Shelli Sloan
2014-10-01 |  | Weekly financial touch point meetings begin | Shelli Sloan
2014-10-08 |  | Depreciation study complete | Dave Davis
October 8-10, 2014 |  | Twelve months ending September 30, 2014 financial reports available | Brad Funk
2014-10-08 |  | Begin work on Sections I-V (This includes adjustments) | Kentucky Office/Accounting/Tax/Witnesses
2014-10-16 |  | Cap Structure Complete <<Had to do Proforma>> | Marc Reitter
2014-10-23 |  | Complete FIT calculation, excluding adjustments | Jeff Bartsch
2014-10-30 |  | All Adjustments Complete (Schedule IV) | Multiple
2014-10-30 |  | First draft of testimony (financials not complete) | Witnesses
2014-10-30 |  | Complete base case jurisdictional cost of service study | Shannon Listebarger
Original due date | Updated due to slip | What | Who
2014-11-05 | 2014-11-11 | Complete jurisdictional cost of service study with adjustments. Send to Tax. | Shannon Listebarger
2014-11-11 | 2014-11-14 | Tax work complete on cost of service | Jeff Bartsch
2014-11-14 | 2014-11-19 | Complete Class cost of service study | Jason Stegall
2014-11-14 |  | Second draft of testimony | Witnesses
2014-11-14 |  | Notice of Intent to file | Kentucky Office/Legal
2014-11-14 | 2014-11-14 | Preliminary copy of Section IV complete and ready for review | Kentucky Office Distribute: Shelli Sloan
2014-11-19 | 2014-11-24 | Management approval of revenue increase | Kentucky Office
2014-11-21 | 2014-11-26 | Proposed rates ready for annualization test | Alex Vaughan
2014-11-25 |  | Third draft of testimony | Witnesses
2014-11-25 | 2014-12-03 | Computer verification of rates | Kentucky Office/Dave Roush/Alex Vaughan
2014-12-05 |  | Final Testimony due | Witnesses
Week of December 8, 2014 |  | Review sessions of final drafts of testimony with numbers | All
2014-12-08 |  | Legal Newspaper Advertisement | Kentucky Office/Legal
2014-12-12 |  | Testimony/Filing Package locked down | Kentucky Office/Shelli Sloan
2014-12-19 |  | Reproduction work | Kentucky Office
2014-12-29 |  | Filing made | Kentucky Office/Legal