## Big Sandy Unit No. 1
Company Name: Kentucky Power Company
Station Name - Unit Number: Big Sandy Unit No. 1
For the Months of: | November 1, 2014 to April 30, 2015
| MAINTENANCE |  |  |  | HOURS OF DURATION
| Scheduled |  | Actual1/
MONTH | From | To | From | To | Scheduled | Forced | Actual | REASON FOR DEVIATIONS FROM SCHEDULED MAINTENANCE OR REASON FOR FORCED OUTAGE, AS APPROPRIATE
November | 2015-11-01 | 2015-11-15 | 2015-11-01 | 2015-11-15 | 338.9 |  | 338.9 | Boiler Casing and Precipitator Repairs
January | 2015-01-01 | 2015-01-10 | 2015-01-01 | 2015-01-10 | 220.5 |  | 220.5 | Generator - North H2 Cooler Leak
January | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 13.1 |  | 13.1 | Reserve Shutdown
March | 2015-03-16 | 2015-03-25 | 2015-03-16 | 2015-03-25 | 210.9 |  | 210.9 | Boiler Drum Gage Glass Piping Leak
March | 2015-03-25 | 2015-03-26 | 2015-03-25 | 2015-03-26 | 22.9 |  | 22.9 | Reserve Shutdown

## Big Sandy Unit No. 2
Company Name: Kentucky Power
Station Name - Unit Number: Big Sandy Unit No. 2
For the Months of | November 1, 2014 to April 30, 2015
| MAINTENANCE |  |  |  | HOURS OF DURATION
| Scheduled |  | Actual1/
MONTH | From | To | From | To | Scheduled | Forced | Actual | REASON FOR DEVIATIONS FROM SCHEDULED MAINTANANCE OR REASON FOR FORCED OUTAGE, AS APPROPRIATE
November | 2015-11-01 | 2015-12-06 | 2015-11-01 | 2015-12-06 | 854.3 |  | 854.3 | Boiler Casing Repairs
December | 2015-12-06 | 2015-12-08 | 2015-12-06 | 2015-12-08 | 37.6 |  | 37.6 | Reserve Shutdown
January |  |  | 2015-01-01 | 2015-01-02 |  | 6.4 | 6.4 | Turbine Control Fluid Leak Repair
January | 2015-01-02 | 2015-01-02 | 2015-01-02 | 2015-01-02 | 11.5 |  | 11.5 | Reserve Shutdown
February |  |  | 2015-02-25 | 2015-03-04 |  | 163.4 | 163.4 | Boiler Tube Leak Repair
March | 2015-03-04 | 2015-03-04 | 2015-03-04 | 2015-03-04 | 15.7 |  | 15.7 | Reserve Shutdown

## Mitchell Unit No. 1
Company Name: Kentucky Power Company
Station Name - Unit Number: Mitchell Unit No. 1
For the Months of: | November 1, 2014 to April 30, 2015
| MAINTENANCE |  |  |  | HOURS OF DURATION
| Scheduled |  | Actual1/
MONTH | From | To | From | To | Scheduled | Forced | Actual | REASON FOR DEVIATIONS FROM SCHEDULED MAINTENANCE OR REASON FOR FORCED OUTAGE, AS APPROPRIATE
November |  |  | 2015-11-04 | 2015-11-11 |  | 169.2667 | 169.2667 | Boiler Tube Leak
November |  |  | 2014-11-27 | 2014-12-03 |  | 131.8 | 131.8 | Boiler Tube leak lower right rear furnace wall
December | 2014-12-03 | 2014-12-22 | 2014-12-03 | 2014-12-22 | 478.4167 |  | 478.4167 | Additional tube replacement preventive
January | 2015-01-02 | 2015-01-06 | 2015-01-02 | 2015-01-06 | 115.6333 |  | 115.6333 | ESP inspection/repair
January |  |  | 2015-01-09 | 2015-01-10 |  | 16.3833 | 16.3833 | Bad absorber temp probe indication (communication failure) trip
February |  |  | 2015-02-05 | 2015-02-10 |  | 109.7667 | 109.7667 | Duct work leak (EJ failure) causing opacity to be out of control
February |  |  | 2015-02-11 | 2015-02-13 |  | 31.7333 | 31.7333 | Hydraulic oil leak internal of #11 ID fan
March |  |  | 2015-03-10 | 2015-03-10 |  | 8.25 | 8.25 | Loss of 4kV buss due to DC ground
March | 2015-03-10 | 2015-03-17 | 2015-03-10 | 2015-03-17 | 151.1667 |  | 151.1667 | Slag/Clinker removal fireside cleaning
March | 2015-03-17 | 2015-03-20 | 2015-03-17 | 2015-03-20 | 71.5 |  | 71.5 | #11 ID fan vibration
April |  |  | 2015-03-31 | 2015-04-01 |  | 26.05 | 26.05 | Repair 12 ID fan hydraulic leak
April |  |  | 2015-04-01 | 2015-04-02 |  | 23.1667 | 23.1667 | Economizer Leak
April | 2015-04-02 | 2015-04-11 | 2015-04-02 | 2015-04-11 | 199.8333 |  | 199.8333 | ID Fan Repairs
April | 2015-04-11 | 2015-04-30 | 2015-04-11 | 2015-04-30 | 479.9833 |  | 479.9833 | General Maintenance

## Mitchell Unit No. 2
Company Name: Kentucky Power
Station Name - Unit Number: Mitchell Unit No. 2
For the Months of | November 1, 2014 to April 30, 2015
| MAINTENANCE |  |  |  | HOURS OF DURATION
| Scheduled |  | Actual1/
MONTH | From | To | From | To | Scheduled | Forced | Actual | REASON FOR DEVIATIONS FROM SCHEDULED MAINTANANCE OR REASON FOR FORCED OUTAGE, AS APPROPRIATE
December | 2014-12-04 | 2014-12-08 | 2014-12-04 | 2014-12-08 | 97.7167 |  | 97.7167 | 1st Reheater tube leak
January | 2015-01-28 | 2015-02-01 | 2015-01-28 | 2015-02-01 | 94.3 |  | 94.3 | Precipitator inspection and repair due to fouling
February | 2015-02-28 | 2015-03-07 | 2015-02-28 | 2015-03-07 | 154.6167 |  | 154.6167 | 2nd RH tube leak
March | 2015-03-07 | 2015-04-30 | 2015-03-07 | 2015-04-30 | 1319.9833 |  | 1319.9833 | General Maintenance