## Filed
Atmos Energy Corporation
Case No. 2015-003473
Calculation of Capital Construction Project Slippage Factor
Fiscal Yrs Ending Sep
(000's)
Kentucky
GKW-2
Source: Capital Expenditures and Budget |  |  |  |  | Schedule 13b
Years | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2015 | 55475 | 55854 | -379 | -0.6786% | 99.32%
2014 | 49197 | 43656 | 5541 | 12.69% | 112.7%
2013 | 35551 | 29805 | 5746 | 19.28% | 119.3%
2012 | 37799 | 31254 | 6545 | 20.94% | 120.9%
2011 | 22266 | 21659 | 607 | 2.803% | 102.8%
2010 | 21493 | 22717 | -1224 | -5.388% | 94.61%
2009 | 19736 | 17396 | 2340 | 13.45% | 113.5%
2008 | 17667 | 18816 | -1149 | -6.107% | 93.89%
2007 | 16407 | 16798 | -391 | -2.328% | 97.67%
2006 | 16626 | 14185 | 2441 | 17.21% | 117.2%
Totals | 292217 | 272140 | 20077 | 7.377% | 107.4%
10 Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 10 years) |  |  |  |  | 107.2%
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule 13a.
Total all projects for a given year.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor for
each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.

## PRP
Atmos Energy Corporation
Case No. 2015-003473
Calculation of Capital Construction Project Slippage Factor
Fiscal Yrs Ending Sep
(000's)
Kentucky
Source: Capital Expenditures and Budget - Approved PRP Program
Years | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor | Notes
2015 | 36926.4406 | 36259.795 | 666.6456 | 1.839% | 101.8%
2014 | 22691.1825 | 20031.072 | 2660.1105 | 13.28% | 113.3%
2013 | 17171.7936 | 17317.351 | -145.5574 | -0.8405% | 99.16%
2012 | 17300.3436 | 17926.77 | -626.4264 | -3.494% | 96.51%
2011 | 3741.1248 | 3407.068 | 334.0568 | 9.805% | 109.8%
2010 | 0 | 0 | 0 |  |  | Approved PRP Program did not exist
2009 | 0 | 0 | 0 |  |  | Approved PRP Program did not exist
2008 | 0 | 0 | 0 |  |  | Approved PRP Program did not exist
2007 | 0 | 0 | 0 |  |  | Approved PRP Program did not exist
2006 | 0 | 0 | 0 |  |  | Approved PRP Program did not exist
Totals | 97830.885 | 94942.056 | 2888.8291 | 3.043% | 103%
10 Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 10 years) |  |  |  |  | 52.06%

## Non-PRP
Atmos Energy Corporation
Case No. 2015-003473
Calculation of Capital Construction Project Slippage Factor
Fiscal Yrs Ending Sep
(000's)
Kentucky
Source: Capital Expenditures and Budget - Non PRP Spend
Years | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor | Notes
2015 | 18548.5594 | 19594.205 | -1045.6456 | -5.337% | 94.66%
2014 | 26505.8175 | 23624.928 | 2880.8895 | 12.19% | 112.2%
2013 | 18379.2064 | 12487.649 | 5891.5574 | 47.18% | 147.2%
2012 | 20498.6564 | 13327.23 | 7171.4264 | 53.81% | 153.8%
2011 | 18524.8752 | 18251.932 | 272.9432 | 1.495% | 101.5%
2010 | 21493 | 22717 | -1224 | -5.388% | 94.61% | Approved PRP Program did not exist
2009 | 19736 | 17396 | 2340 | 13.45% | 113.5% | Approved PRP Program did not exist
2008 | 17667 | 18816 | -1149 | -6.107% | 93.89% | Approved PRP Program did not exist
2007 | 16407 | 16798 | -391 | -2.328% | 97.67% | Approved PRP Program did not exist
2006 | 16626 | 14185 | 2441 | 17.21% | 117.2% | Approved PRP Program did not exist
Totals | 194386.115 | 177197.944 | 17188.1709 | 9.7% | 109.7%
10 Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 10 years) |  |  |  |  | 112.6%