## 2015a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2015
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2015 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.19593 | Hopkinsville 08 Non Growth | Hopkinsville 08 Non Growth | 594.82 | 0 |  |  | 0.6855% | 382898.5 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.19599 | Shelbyville 08 Non Growth | Shelbyville 08 Non Growth | 361 | 0 |  |  | 0.3765% | 210292.67 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.21065 | Bowling Green 09 Non Growth | Bowling Green 09 Non Growth | 282.68 | 0 |  |  | 2.924% | 1633219.04 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21071 | Danville 09 Non Growth | Danville 09 Non Growth | 766.99 | 0 |  |  | 1.179% | 658259.26 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21083 | Paducah 09 Non Growth | Paducah 09 Non Growth | 4442.83 | 0 |  |  | 1.722% | 961601.24 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21983 | 050.2637.Lady Karen Ext | Install 580 feet of 2 inch poly for two existing customers | 2584 | 2845.37 | 784.37 | 27.57% | 0.006499% | 3629.74 | 2845.37 | 784.37 | 2014-10-01 | 2015-09-30 | 2009-04-13 | 4 | 2011-01-21 | 1
| 050.22391 | 050.KY.BowlGrnIntegFunct2010 | 050.KY.BowlGrnIntegFunct2010 | 256.71 | 0 |  |  | 2.28% | 1273314.83 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22393 | 050.KY.HopkinsIntegFunct2010 | 050.KY.HopkinsIntegFunct2010 | 500 | 0 |  |  | 0.9702% | 541875.17 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22394 | 050.KY.DanvilleIntegFunct2010 | 050.KY.DanvilleIntegFunct2010 | 503.33 | 0 |  |  | 0.8852% | 494408.46 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22429 | 050.KY.BowlGrnLeakFunct2010 | 050.KY.BowlGrnLeakFunct2010 | 2769.9 | 0 |  |  | 1.888% | 1054241.95 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22432 | 050.KY.DanvilleLeakFunct2010 | 050.KY.DanvilleLeakFunct2010 | 435.52 | 0 |  |  | 0.3315% | 185153.31 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22433 | 050.KY.CampbellLeakFunct2010 | 050.KY.CampbellLeakFunct2010 | 1176.47 | 0 |  |  | 0.4638% | 259048.85 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22434 | 050.KY.ShelbyvLeakFunct2010 | 050.KY.ShelbyvLeakFunct2010 | 1628.25 | 0 |  |  | 0.1649% | 92079.33 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22438 | 050.KY.PaducahLeakFunct2010 | 050.KY.PaducahLeakFunct2010 | 10875.46 | 0 |  |  | 0.8376% | 467821.19 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 119755.9 | 0 |  |  | 1.688% | 943018.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 17770.3 | 0 |  |  | 0.1839% | 102704.39 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 27892.7 | 0 |  |  | 0.2883% | 161014.73 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 8868.94 | 0 |  |  | 0.2658% | 148448.92 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 15584.06 | 0 |  |  | 0.2671% | 149211.09 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 68726.65 | 0 |  |  | 0.7647% | 427109.25 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 14716.55 | 0 |  |  | 0.1512% | 84423.62 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 16958.89 | 0 |  |  | 0.153% | 85432.68 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 152824.96 | 0 |  |  | 1.07% | 597796.41 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 69892.44 | 0 |  |  | 0.6651% | 371508.63 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 26934.21 | 0 |  |  | 0.1452% | 81125.42 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 177428.84 | 0 |  |  | 1.361% | 759913.52 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 1072.62 | 0 |  |  | 0.03912% | 21852.12 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 23281.01 | 0 |  |  | 0.1049% | 58603.45 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 33493.37 | 0 |  |  | 0.4133% | 230834.11 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 58489.77 | 0 |  |  | 0.2108% | 117760.49 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 36075.65 | 0 |  |  | 0.3418% | 190885.65 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 4525.86 | 0 |  |  | 0.1021% | 57051.27 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5920.31 | 0 |  |  | 0.1526% | 85208.89 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 55172.5 | 0 |  |  | 0.6134% | 342615.42 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 30988.94 | 0 |  |  | 0.4159% | 232291.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 2870.85 | 0 |  |  | 0.1082% | 60450.89 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 573450.2 | 0 |  |  | 5.373% | 3001238.92 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 68661.91 | 0 |  |  | 0.6772% | 378235.39 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 103075.8 | 0 |  |  | 0.5709% | 318868.98 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 51613.98 | 0 |  |  | 0.4755% | 265597.55 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 56293.98 | 0 |  |  | 0.3924% | 219162.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 199453.99 | 0 |  |  | 1.643% | 917507.19 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 80803.99 | 0 |  |  | 0.6591% | 368148.22 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 35560.54 | 0 |  |  | 0.3578% | 199868.54 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 439748.54 | 0 |  |  | 3.547% | 1980963.13 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 324620.05 | 0 |  |  | 2.082% | 1162833.39 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 42308.69 | 0 |  |  | 0.5311% | 296653.1 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | -91277.18 | 0 |  |  | 1.281% | 715663.46 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 16560.02 | 0 |  |  | 0.2604% | 145463.13 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 45652.55 | 0 |  |  | 0.3359% | 187593.38 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 33497.45 | 0 |  |  | 0.3108% | 173599.03 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 26294.54 | 0 |  |  | 0.2035% | 113645.85 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 39555.17 | 0 |  |  | 0.2663% | 148745.5 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 25543.47 | 0 |  |  | 0.2967% | 165734 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 21501.26 | 0 |  |  | 0.1945% | 108615.88 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 83864.41 | 0 |  |  | 1.114% | 621959.44 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 111191.75 | 0 |  |  | 0.9785% | 546544.12 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 17806.78 | 0 |  |  | 0.1433% | 80036.21 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 417430.98 | 0 |  |  | 3.344% | 1867949.14 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 67821.63 | 0 |  |  | 0.6985% | 390165.85 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 207340.69 | 0 |  |  | 2.092% | 1168727.02 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 198962.23 | 0 |  |  | 1.869% | 1043896.02 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 105454.38 | 0 |  |  | 0.9237% | 515905.19 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 105350.1 | 0 |  |  | 0.8543% | 477184.17 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 154262.21 | 0 |  |  | 1.504% | 839906.75 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 73620.72 | 0 |  |  | 0.8075% | 450992.77 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 336420.1 | 0 |  |  | 2.705% | 1510612.71 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 326544.51 | 0 |  |  | 2.909% | 1624999.38 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 81481.35 | 0 |  |  | 0.8343% | 466001.18 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 559077.71 | 0 |  |  | 4.655% | 2599713.81 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 145870.4 | 0 |  |  | 1.446% | 807873.84 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 270318.61 | 0 |  |  | 1.824% | 1018580.56 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 174208.82 | 0 |  |  | 1.886% | 1053193.68 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 271414.37 | 0 |  |  | 1.786% | 997722.9 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 222179.5 | 0 |  |  | 1.442% | 805277.1 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 209808.57 | 0 |  |  | 2.201% | 1229474.09 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 103658.17 | 0 |  |  | 1.003% | 560026.73 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 882299.64 | 0 |  |  | 7.771% | 4340428.06 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 336103.69 | 0 |  |  | 2.678% | 1495981.48 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 177336.34 | 0 |  |  | 1.793% | 1001400.98 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23834 | DanvilleIntegRegs | Danville Non Growth Regs Functional | 6662.47 | 0 |  |  | 0.1217% | 67948.1 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23838 | MadisonvilleIntegRegs | Madisonville Non Growth Regs | 140.41 | 0 |  |  | 0.1353% | 75578.16 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23839 | PrincetonIntegRegs | Princeton Non Growth Regs Functional | 1114.71 | 0 |  |  | 0.1033% | 57709.44 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 137746.91 | 0 |  |  | 0.8944% | 499554.71 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 2080.22 | 0 |  |  | 0.0753% | 42060.13 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 65432.35 | 0 |  |  | 0.6441% | 359764.72 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 122207.82 | 0 |  |  | 0.7682% | 429094.58 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 5002.02 | 0 |  |  | 0.1932% | 107885.34 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 7870.19 | 0 |  |  | 0.1268% | 70805.95 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 26719.93 | 0 |  |  | 0.2237% | 124939.92 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 57510.94 | 0 |  |  | 0.4084% | 228113.72 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 13951.68 | 0 |  |  | 0.3228% | 180313.81 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 31764.34 | 0 |  |  | 0.5183% | 289489.72 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 3801.42 | 0 |  |  | 0.06849% | 38256.61 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 94109.05 | 0 |  |  | 2.279% | 1273172.76 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 121241.46 | 0 |  |  | 0.7913% | 441958.17 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 80887.82 | 0 |  |  | 0.4741% | 264785.42 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 55978.78 | 0 |  |  | 0.5035% | 281235.47 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 37316.42 | 0 |  |  | 0.2728% | 152388.47 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 24494.64 | 0 |  |  | 0.1605% | 89621.82 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 74567.49 | 0 |  |  | 0.4806% | 268451.34 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 23660.29 | 0 |  |  | 0.2085% | 116460.13 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 142020.79 | 0 |  |  | 1.088% | 607573.15 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 69616.04 | 0 |  |  | 0.8213% | 458702.11 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 11551.4 | 0 |  |  | 0.1212% | 67716.2 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 158953.54 | 0 |  |  | 2.108% | 1177391.76 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 130285.5 | 0 |  |  | 0.7574% | 423036.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 23928.59 | 0 |  |  | 0.6477% | 361758.71 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 119071.71 | 0 |  |  | 0.8821% | 492679.45 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 35028.02 | 0 |  |  | 0.3147% | 175752.86 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 52334.29 | 0 |  |  | 0.2921% | 163173.51 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 97624.67 | 0 |  |  | 0.4811% | 268700.35 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 22597.93 | 0 |  |  | 0.1916% | 107011.22 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 130686.73 | 0 |  |  | 1.263% | 705225.52 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 231959.64 | 0 |  |  | 1.67% | 932894.1 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 12152.31 | 0 |  |  | 0.1897% | 105980.7 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 253752.91 | 0 |  |  | 1.673% | 934408.68 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 37474.12 | 0 |  |  | 0.566% | 316124.75 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 22575.78 | 0 |  |  | 0.1682% | 93935.83 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 96245.68 | 0 |  |  | 0.8251% | 460861.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 97477.37 | 0 |  |  | 0.6677% | 372923.65 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 82724.56 | 0 |  |  | 0.389% | 217292.65 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 33308.71 | 0 |  |  | 0.2231% | 124586.29 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 29264.93 | 0 |  |  | 0.2408% | 134491.99 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 277343.8 | 0 |  |  | 1.846% | 1031100.65 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 99037.57 | 0 |  |  | 0.5759% | 321639.59 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 12516.26 | 0 |  |  | 0.1279% | 71458.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24031 | DanvilleLeakRegs | Danville Leak Regs Functional | 65.93 | 0 |  |  | 0.1095% | 61161.06 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2016-09-30 | 9
| 050.24035 | PrincetonLeakRegs | Princeton Leak Regs Functional | -45.36 | 0 |  |  | 0.01426% | 7962.7 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24070 | DanvilleLeakCP/LeakClamps | Danville Leak Functional - CP/Leak Clamps | 35380.24 | 0 |  |  | 0.3023% | 168863.72 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24073 | MadisonLeakCP/LeakClamps | Madisonville Leak Functional - CP/Leak Clamps | 133.18 | 0 |  |  | 0.1513% | 84498.93 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24074 | PrincetonLeakCP/LeakClamps | Princeton Leak Functional - CP/Leak Clamps | 5440.39 | 0 |  |  | 0.1155% | 64513.33 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 21.46 | 0 |  |  | 0.09728% | 54333.3 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 8 | 0 |  |  | 0.02125% | 11870.18 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 1649543.74 | 0 |  |  | 6.978% | 3897490.23 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 859276.84 | 0 |  |  | 4.372% | 2441847.57 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 1657808.36 | 0 |  |  | 7.687% | 4293596.92 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 411921.55 | 0 |  |  | 0.9024% | 504010.07 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24089 | DanvillePRPMeters | Danville KY PRP Functional - Meters | 795.09 | 0 |  |  | 0.007289% | 4071.16 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24109 | KY.Storage Integ RESI MEAS | KY Storage & Transmission Non Growth Functional - RESI MEAS. Meters, regulators, and meterset items typically used for residential applications. | 1820.51 | 0 |  |  | 0.01833% | 10239.45 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 758 | 0 |  |  | 0.01535% | 8571.07 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 58.32 | 0 |  |  | 0.01184% | 6613.28 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 40998.98 | 0 |  |  | 0.5413% | 302319.7 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 909197.3 | 0 |  |  | 2.456% | 1371761.49 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 524304.48 | 0 |  |  | 1.654% | 923682.94 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 478311.75 | 0 |  |  | 2.362% | 1319465.22 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 185972.04 | 0 |  |  | 4.231% | 2362977.66 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 152273.01 | 0 |  |  | 1.195% | 667489.72 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26310 | CampbellsvillePRPMeters | Campbellsville KY PRP Functional - Meters | 769.48 | 0 |  |  | 0.004219% | 2356.52 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2016-09-30 | 9
| 050.26312 | ShelbyvillePRPServices | Shelbyville KY PRP Functional - Services | 16105.17 | 0 |  |  | 0.0445% | 24854.29 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2010-09-16 | 9 | 2016-09-30 | 9
| 050.28160 | 050.2734.Hwy31W Reloc. B.G. | Hwy 31W HPD & IP Relocation | -454520.3 | 221016.86 | 164839.78 | 74.58% | 0.6908% | 385856.64 | 221016.86 | 164839.78 | 2014-10-01 | 2015-09-30 | 2011-09-15 | 9 | 2011-12-31 | 12
| 050.28803 | PRP.2634. Hanson St. Replacem | Replacing LP Bare Stl. main with 2,789 Ft 2 Inch PE IP | 15960.38 | 138003.74 | 7834.5 | 5.677% | 0.2611% | 145838.24 | 138003.74 | 7834.5 | 2014-10-01 | 2015-09-30 | 2011-12-27 | 12 | 2012-09-28 | 9
| 050.30252 | PRP.2736.4TH ST REPL | PRP.2736.4TH 2ND & MAIN ST REPL | 2000.95 | 546533.86 | -28770.81 | -5.264% | 0.927% | 517763.05 | 546533.86 | -28770.81 | 2014-10-01 | 2015-09-30 | 2012-04-25 | 4 | 2012-09-28 | 9
| 050.32038 | PRP.2635.Marion.W Belleville | PRP.2635.Marion.W Belleville St | 5957.04 | 0 |  |  | 0.4341% | 242453.1 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2013-09-28 | 9 | 2013-09-28 | 9
| 050.32775 | PRP.2609.Fruithill to Hoptown | Replace approximately 25000 Ft 10 Inch 6 Inch Bare Stl. with 12 Inch Stl. | 91002.38 | 5708987.47 | -295305.41 | -5.173% | 9.693% | 5413682.06 | 5708987.47 | -295305.41 | 2014-10-01 | 2015-09-30 | 2012-10-28 | 10 | 2015-09-30 | 9
| 050.32960 | 050.2734.Hwy31W Reloc - Frk | Hwy 31W- 1008 to Memorial Reloc. | 542.42 | 225067.56 | -66926.49 | -29.74% | 0.2831% | 158141.07 | 225067.56 | -66926.49 | 2014-10-01 | 2015-09-30 | 2012-11-26 | 11 | 2015-09-30 | 9
| 050.32990 | 050.2612 TN ECAT Replacement | ECAT replacement units for TN | -8.78 | 9569.6 | 9678.18 | 101.1% | 0.03446% | 19247.78 | 9569.6 | 9678.18 | 2014-10-01 | 2015-09-30 | 2012-12-06 | 12 | 2013-09-29 | 9
| 050.33087 | PRP.2734.EAST 2ND ST | Replace bare main on 2nd St | 542.42 | 0 |  |  | 0.08277% | 46232.83 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2013-05-11 | 5 | 2013-05-11 | 5
| 050.33425 | PRP.2636.Glendale Dr. | Replace 3 Inch bare main crossing that is leaking with 2 Inch PE. | -250.81 | 7245.23 | 2485.53 | 34.31% | 0.01742% | 9730.76 | 7245.23 | 2485.53 | 2014-10-01 | 2015-09-30 | 2013-02-05 | 2 | 2013-09-28 | 9
| 050.34098 | PRP.2636.W PARRISH AVE_1 | Bare pipe repl on Parrish and south | 77833.55 | 685518.46 | 33210.07 | 4.845% | 1.287% | 718728.53 | 685518.46 | 33210.07 | 2014-10-01 | 2015-09-30 | 2013-06-01 | 6 | 2013-12-01 | 12
| 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | REPLACE RECTIFIER AND GROUND BED IN JUNCTION CITY ON MILL ST | -343.17 | 19511.4 | -2463.67 | -12.63% | 0.03052% | 17047.73 | 19511.4 | -2463.67 | 2014-10-01 | 2015-09-30 | 2013-05-01 | 5 | 2015-05-01 | 5
| 050.34324 | 2737.HAR.PURCH ODOR REPLACE | REPLACE ORDORIZOR AT THE HARRODSBURG PURCHASE STATION - INSTALL YZ ODORIZOR | 2949.54 | 66681.61 | -5500.31 | -8.249% | 0.1095% | 61181.3 | 66681.61 | -5500.31 | 2014-10-01 | 2015-09-30 | 2012-10-01 | 10 | 2014-09-30 | 9
| 050.34783 | Install 3 inch Mooneys | Woodmill Regulator Station in Hopkinsville. We are replacing the (2) 3 inch 461 - 57S Roll out regulators with (2) new 3 inch Mooney regulators. | -522.35 | 11373.94 | -1683.8 | -14.8% | 0.01735% | 9690.14 | 11373.94 | -1683.8 | 2014-10-01 | 2015-09-30 | 2013-08-12 | 8 | 2013-09-28 | 9
| 050.34823 | PRP.2636.CLOVERDALE | Replace 3" bare steel | 2547.02 | 53836.15 | -5269.07 | -9.787% | 0.08695% | 48567.08 | 53836.15 | -5269.07 | 2014-10-01 | 2015-09-30 | 2013-07-03 | 7 | 2013-09-28 | 9
| 050.34850 | PRP.2nd at Bethel - Russ | Replace 3" Bare w 2nd at Bethel - Russellville | 512.68 | 24440.03 | -13684.94 | -55.99% | 0.01926% | 10755.09 | 24440.03 | -13684.94 | 2014-10-01 | 2015-09-30 | 2013-08-05 | 8 | 2013-12-31 | 12
| 050.35002 | 050.2637.13th St Replace | Abandon 318 ft of 2 inch M.W main. We currently have one grade 2 leak, gas getting near building. We have a history of leakage in this alley. we propose to retire some main in alley and install app. 100 ft on Jefferson and switch two services . | -1018.08 | 3844.33 | 1300.38 | 33.83% | 0.009211% | 5144.71 | 3844.33 | 1300.38 | 2014-10-01 | 2015-09-30 | 2013-08-28 | 8 | 2013-09-28 | 9
| 050.35012 | PRP.2609.Greenriver Steel | Replace 9010 ft Bare Stl | 263772.32 | 1230804.04 | 148126.32 | 12.03% | 2.469% | 1378930.36 | 1230804.04 | 148126.32 | 2014-10-01 | 2015-09-30 | 2013-08-25 | 8 | 2014-12-31 | 12
| 050.35013 | PRP.2609.Fruithill Hoptown 2 | Replace 26000 ft 6 Inch Bare Steel with 12 Inch Steel | 1699818.82 | 7419912.38 | -968318.59 | -13.05% | 11.55% | 6451593.79 | 7419912.38 | -968318.59 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-12-31 | 12
| 050.35055 | PRP.Woodburn-Franklin HPD | Replace Bare HPD from Woodburn Purchase to Akin Rd. | 923183.89 | 4133795.54 | 1347881.83 | 32.61% | 9.814% | 5481677.37 | 4133795.54 | 1347881.83 | 2014-10-01 | 2015-09-30 | 2013-08-30 | 8 | 2015-09-28 | 9
| 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | BRUEST HOT CAT STATION HEATER AND A KING TOOL 2B BY-PASS ODORIZER FOR THE TRI-CITIES AIRPORT STATION | -1520.04 | 53963.3 | -42067.07 | -77.95% | 0.0213% | 11896.23 | 53963.3 | -42067.07 | 2014-10-01 | 2015-09-30 | 2013-09-05 | 9 | 2014-08-15 | 8
| 050.35149 | PRP.2609.Fruithill 4 InchRt. | Retire 4 Inch HPD | 6871.79 | 19273.73 | -4735.41 | -24.57% | 0.02603% | 14538.32 | 19273.73 | -4735.41 | 2014-10-01 | 2015-09-30 | 2013-08-09 | 8 | 2014-11-30 | 11
| 050.35675 | PRP.2738.Grn.Henry St | PRP.2738.Grn.Henry St | 4172.02 | 376921.09 | -221728.17 | -58.83% | 0.2779% | 155192.92 | 376921.09 | -221728.17 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.35688 | 050.2609.Southwire | Replace existing 2 Inch Tap with 6 Inch tap to increase flow to Southwire | 3191.49 | 18470.31 | -303.16 | -1.641% | 0.03253% | 18167.15 | 18470.31 | -303.16 | 2014-10-01 | 2015-09-30 | 2013-10-18 | 10 | 2015-11-15 | 11
| 050.35692 | PRP.2636.E 6TH TRIP REPL | PRP.2636.E 6TH ST REPL | 25498.52 | 417982.34 | 51615.62 | 12.35% | 0.8408% | 469597.96 | 417982.34 | 51615.62 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.35739 | 050.2609.Wells St. Charles | Rework St. Charles Wells | -3069.6 | 1317457.69 | -97952.56 | -7.435% | 2.183% | 1219505.13 | 1317457.69 | -97952.56 | 2014-10-01 | 2015-09-30 | 2013-11-01 | 11 | 2014-09-30 | 9
| 050.35780 | 050.2636.TRIP ST SYS IMP REPL | Install 2600 Ft of 6 Inch PE , 259 Ft 4 Inch PE and 220 Ft 2 Inch PE to replace aging pipe. | 25842.27 | 451231.73 | -35205.39 | -7.802% | 0.7449% | 416026.34 | 451231.73 | -35205.39 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | PRP.2735.Horse Cav.Cherry-Maple-Bedford 2014 | 27032.64 | 420919.56 | -208865.79 | -49.62% | 0.3797% | 212053.77 | 420919.56 | -208865.79 | 2014-10-01 | 2015-09-30 | 2013-09-30 | 9 | 2014-10-01 | 10
| 050.35859 | PRP.2734.OLD LVILLE RD TO RED | PRP.2734.OLD LVILLE RD TO RED | 13308.97 | 114299.19 | 225536.74 | 197.3% | 0.6084% | 339835.93 | 114299.19 | 225536.74 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35899 | PRP.2634.S. Seminary St. | Replace 4 Inch Steel low pressure bare main with 2056 Ft of 2 Inch PE IP Main. Approximately 50 customers involved. | 10757.52 | 137126.81 | 19970.14 | 14.56% | 0.2813% | 157096.95 | 137126.81 | 19970.14 | 2014-10-01 | 2015-09-30 | 2013-11-01 | 11 | 2014-09-28 | 9
| 050.35970 | PRP.2736.Hville-W Side South | PRP.2736.Hville W Side South | 163009.3 | 727947.71 | 41259.01 | 5.668% | 1.377% | 769206.72 | 727947.71 | 41259.01 | 2014-10-01 | 2015-09-30 | 2013-10-10 | 10 | 2015-01-30 | 1
| 050.36107 | KY Kinder Morgan ROC Cont | Kinder Morgan Purchase Station ROC Controllers for Kentucky | -33.73 | 56126.59 | 14325.2 | 25.52% | 0.1261% | 70451.79 | 56126.59 | 14325.2 | 2014-10-01 | 2015-09-30 | 2013-12-09 | 12 | 2014-05-01 | 5
| 050.36109 | ECAT Replacement KY | ECAT Replacement for KY Div 009 | 13135.61 | 53041.48 | -1330.4 | -2.508% | 0.09258% | 51711.08 | 53041.48 | -1330.4 | 2014-10-01 | 2015-09-30 | 2013-12-09 | 12 | 2014-04-01 | 4
| 050.36113 | Electronic Correctors KY | Electronic Correctors for Kentucky | 3281.57 | 34518.05 | -16533.73 | -47.9% | 0.0322% | 17984.32 | 34518.05 | -16533.73 | 2014-10-01 | 2015-09-30 | 2013-12-09 | 12 | 2014-10-01 | 10
| 050.36119 | Habit Purchase Heater KY | Habit Purchase Indirect Heater KY | 14376.05 | 141587.83 | 34992.32 | 24.71% | 0.3161% | 176580.15 | 141587.83 | 34992.32 | 2014-10-01 | 2015-09-30 | 2013-12-09 | 12 | 2014-10-01 | 10
| 050.36121 | ROC Upgrades KY | ROC Upgrades for Kentucky | -19 | 23747.27 | 15724.71 | 66.22% | 0.07067% | 39471.98 | 23747.27 | 15724.71 | 2014-10-01 | 2015-09-30 | 2013-12-09 | 12 | 2014-07-01 | 7
| 050.36132 | PRP.2734.B.G.-Auburn 2014 | PRP.2734.B.G.-Auburn 2014 | 6940.63 | 450096.88 | -122950.08 | -27.32% | 0.5857% | 327146.8 | 450096.88 | -122950.08 | 2014-10-01 | 2015-09-30 | 2013-10-14 | 10 | 2014-09-30 | 9
| 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | INSTALL 5270ft OF 2in PE ON GREEN AND MAIN STREETS | 32173.57 | 357169.26 | 94494.82 | 26.46% | 0.8087% | 451664.08 | 357169.26 | 94494.82 | 2014-10-01 | 2015-09-30 | 2013-10-02 | 10 | 2014-09-30 | 9
| 050.36287 | PRP.2609.Fruithill 4 Inch PE | replace approximately 7900 Ft of 4 Inch Bare Steel with 4 Inch High Density PE. | 1451.23 | 480743.64 | -48059.66 | -9.997% | 0.7747% | 432683.98 | 480743.64 | -48059.66 | 2014-10-01 | 2015-09-30 | 2014-01-15 | 1 | 2014-11-15 | 11
| 050.36288 | New Paducah Office | This project is for the building of a structure, the new Paducah, KY office located at 3510 Coleman Road | 78051.14 | 1362000 | 280077.26 | 20.56% | 2.94% | 1642077.26 | 1362000 | 280077.26 | 2014-10-01 | 2015-09-30 | 2014-03-01 | 3 | 2014-11-30 | 11
| 050.36301 | 050.2634.Tyson Boiler | Install Boiler at Tyson Foods to eliminate icing due to pressure change. | -2552.7 | 116757.23 | -20281.06 | -17.37% | 0.1727% | 96476.17 | 116757.23 | -20281.06 | 2014-10-01 | 2015-09-30 | 2014-01-20 | 1 | 2014-09-28 | 9
| 050.36302 | PRP.2737.HAR.GREENBR SUB 2014 | INSTALL 7700ft OF 2iN PE IN GREEBRIAR SUBDIVISION | 58366.17 | 770435.2 | -395922.62 | -51.39% | 0.6705% | 374512.58 | 770435.2 | -395922.62 | 2014-10-01 | 2015-09-30 | 2013-09-26 | 9 | 2014-10-01 | 10
| 050.36303 | PRP.2738.GRN.W COL AVE 2014 | INSTALL 3110ft OF 2in PE ON WEST COLUMBIA AVE | 7195.66 | 311198.5 | -56641.64 | -18.2% | 0.4558% | 254556.86 | 311198.5 | -56641.64 | 2014-10-01 | 2015-09-30 | 2013-10-02 | 10 | 2014-09-30 | 9
| 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | INSTALL 3375ft OF 2in PE ON DEPOT STREET | 186362.81 | 343251.89 | -71965.33 | -20.97% | 0.4857% | 271286.56 | 343251.89 | -71965.33 | 2014-10-01 | 2015-09-30 | 2013-10-04 | 10 | 2014-11-30 | 11
| 050.36324 | 2014 Equipment - Mayfield | This project is to capture the costs for equipment purchases for Mayfield, KY. These items include pipe locators, Wmson equip, Mueller equip, E.F equip, & Sensit G2 purchases. | 1051.7 | 77017.2 | 2181.26 | 2.832% | 0.1418% | 79198.46 | 77017.2 | 2181.26 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.36371 | 050.2609.Mueller Truck | Project created for the purchase of New Mueller Truck. | 1063.15 | 166487.4 | -8177.56 | -4.912% | 0.2834% | 158309.84 | 166487.4 | -8177.56 | 2014-10-01 | 2015-09-30 | 2014-01-20 | 1 | 2014-11-30 | 11
| 050.36378 | PRP.2737.E FACTORY-BARE JT | REPLACE 4" ST BARE JOINT AND 2" STEEL BARE JOINT ON EAST FACTORY STREET AND NORTH GREENVILLE STREET | 772.36 | 131431.43 | 164111.23 | 124.9% | 0.5291% | 295542.66 | 131431.43 | 164111.23 | 2014-10-01 | 2015-09-30 | 2014-01-08 | 1 | 2015-01-08 | 1
| 050.36387 | PRP.2734.BG-Coll-10th to 13th | PRP.2734.BG-Coll-10th to 13th | 212319.85 | 247075.12 | 434716.6 | 175.9% | 1.221% | 681791.72 | 247075.12 | 434716.6 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2015-03-31 | 3
| 050.36522 | PRP.2636.PARRISH AVE NORTH | Replace approximately 19801 Ft of Bare LP Steel main with approximately 14071 ft IP 2 InchPE , 3924 Ft IP 6 Inch PE and 1806 Ft IP 4 Inch PE.. There are approximately 365 residential services involved and 43 commercial services. | 576290.53 | 1178822.63 | 2281.78 | 0.1936% | 2.115% | 1181104.41 | 1178822.63 | 2281.78 | 2014-10-01 | 2015-09-30 | 2013-10-09 | 10 | 2015-03-30 | 3
| 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | RELOCATE 280' OF 4" HP STEEL FOR STATE RAOD PROJECT - NO REIMBURSABLE | 1005.34 | 102136.48 | -49080.09 | -48.05% | 0.09499% | 53056.39 | 102136.48 | -49080.09 | 2014-10-01 | 2015-09-30 | 2014-02-01 | 2 | 2015-03-13 | 3
| 050.36611 | PRP.2735.MUN.E UNION ST 2014 | INSTALL 1875fT OF 2in PE ON EAST UNION STREET | 72606.07 | 141792.06 | 13546.3 | 9.554% | 0.2781% | 155338.36 | 141792.06 | 13546.3 | 2014-10-01 | 2015-09-30 | 2013-10-04 | 10 | 2014-09-30 | 9
| 050.36618 | 2738.OFFICE BUILDING 2014 | PURCHASE OFFICE BUILDING FOR CAMPBELLSVILL. Physical address is 336 Commonwealth Drive. | 11120.61 | 690000 | 183664.21 | 26.62% | 1.564% | 873664.21 | 690000 | 183664.21 | 2014-10-01 | 2015-09-30 | 2014-04-01 | 4 | 2014-10-31 | 10
| 050.36619 | 2738.FURNITURE 2014 | PURCHASE NEW FURNITURE FOR OFFICE 2014. Physical address is 336 Commonwealth Drive. | 40212.35 | 15000 | 36900.35 | 246% | 0.09292% | 51900.35 | 15000 | 36900.35 | 2014-10-01 | 2015-09-30 | 2014-07-01 | 7 | 2015-03-30 | 3
| 050.36649 | PRP.2734.Gayle at Normalview | Replace 55 ft. of 2 inch Bare stell Main | 219.39 | 7662.19 | -5781.52 | -75.46% | 0.003367% | 1880.67 | 7662.19 | -5781.52 | 2014-10-01 | 2015-09-30 | 2014-02-06 | 2 | 2014-09-28 | 9
| 050.36655 | PRP.2735.MUN.MILL ST 2014 | INSTALL 3330' OF 2" PE PIPE TO REPLCAE BARE PIPE ON MILL STREET IN MUNFORDVILLE - 15 SERVICES | 8081.95 | 180214.35 | -43494.01 | -24.13% | 0.2448% | 136720.34 | 180214.35 | -43494.01 | 2014-10-01 | 2015-09-30 | 2014-01-01 | 1 | 2015-01-01 | 1
| 050.36688 | 2738.SUM.PURCH ST REG REPLACE | REPLACE REGULATORS AT SUMMERSVILLE PURCHASE STATION | -98.28 | 30884.59 | -21787.09 | -70.54% | 0.01629% | 9097.5 | 30884.59 | -21787.09 | 2014-10-01 | 2015-09-30 | 2014-05-01 | 5 | 2015-05-01 | 5
| 050.36696 | 050.2634.Robards TB Station | Replace Robards Town Border Station ageing Station with leakage and dated regs. and valves that are not serviceable. | 28196.58 | 146685.57 | 12435.7 | 8.478% | 0.2849% | 159121.27 | 146685.57 | 12435.7 | 2014-10-01 | 2015-09-30 | 2014-02-01 | 2 | 2014-10-28 | 10
| 050.36708 | PRP.2737.N MAIN.PRICE 2014 | INSTALL 1700' OF 6" PE AND 1050' OF 2" PE TO REPLACE 4150' OF BARE STEEL PIPE | 9200.61 | 374542.02 | 121619.16 | 32.47% | 0.8883% | 496161.18 | 374542.02 | 121619.16 | 2014-10-01 | 2015-09-30 | 2014-03-01 | 3 | 2015-03-01 | 3
| 050.36776 | PRP.2736.Hville-W_Side_North | PRP.2736.Hopkinsville-West Side North | 88237.83 | 441006.96 | 18739.81 | 4.249% | 0.8231% | 459746.77 | 441006.96 | 18739.81 | 2014-10-01 | 2015-09-30 | 2013-10-09 | 10 | 2015-01-30 | 1
| 050.36799 | 2737.DAN.ERX INSTALLATION | PURCHASE 3 ERX's FOR REPLACING CHARTS IN TEH DANVILLE OPERATIONS | 4323.17 | 29827.38 | -13067.47 | -43.81% | 0.03001% | 16759.91 | 29827.38 | -13067.47 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36801 | 2738.GRNBURG.CAMP-RECTIFIER | INSTALL NEW RECTIFIER IN GREENSBURG | 630.48 | 47902.59 | -32661.87 | -68.18% | 0.02729% | 15240.72 | 47902.59 | -32661.87 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36850 | 050.2736.8 Inch Improvement | Install approximaately 30000 Ft of 8 Inch Steel pipe for reinforcement to the Industrial Park. | 1017217.52 | 6639868.23 | -186605.77 | -2.81% | 11.55% | 6453262.46 | 6639868.23 | -186605.77 | 2014-10-01 | 2015-09-30 | 2014-02-20 | 2 | 2014-11-30 | 11
| 050.36878 | PRP.2734.BG-Normal to Regents | PRP.2734.BG-Normal to Regents & Offset | 46427.89 | 280654.79 | -78430.48 | -27.95% | 0.3621% | 202224.31 | 280654.79 | -78430.48 | 2014-10-01 | 2015-09-30 | 2013-10-23 | 10 | 2014-09-30 | 9
| 050.36898 | PRP.2734.South Way Replc. | Replace 2 inch bare steel - South Way | 3187.42 | 8039.75 | -3860.76 | -48.02% | 0.007482% | 4178.99 | 8039.75 | -3860.76 | 2014-10-01 | 2015-09-30 | 2014-03-12 | 3 | 2014-09-28 | 9
| 050.36902 | 050.2734.Hwy31W Public Imprv | University Blvd. and Hwy 31W Roundabout - State Hwy Reloc. | -790.62 | -0.02 | 136.14 | -680700% | 0.0002437% | 136.12 | -0.02 | 136.14 | 2014-10-01 | 2015-09-30 | 2014-02-17 | 2 | 2014-09-28 | 9
| 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | PRP.2734.BG-Oaklawn-Loving | -39294.75 | 330281.61 | -330281.61 | -100% | 0% | 0 | 330281.61 | -330281.61 | 2014-10-01 | 2015-09-30 | 2013-10-10 | 10 | 2014-09-30 | 9
| 050.37054 | 050.2734.2 inchExt.Cableas | 400 ft. 2 inch Ext. - Cabelsa off KenBale Blvd | -73.87 | 8137.88 | -3095.93 | -38.04% | 0.009027% | 5041.95 | 8137.88 | -3095.93 | 2014-10-01 | 2015-09-30 | 2014-04-01 | 4 | 2014-09-28 | 9
| 050.37077 | 050.2734.ThreeSprings II.Hwy | Three Springs II Public Improvement | -45.14 | 182740.37 | -78705.56 | -43.07% | 0.1863% | 104034.81 | 182740.37 | -78705.56 | 2014-10-01 | 2015-09-30 | 2014-03-31 | 3 | 2014-09-28 | 9
| 050.37154 | Install Infrared red heater | Replace boiler (leaking) at Pryorsburg Station with Hot Cat brand infrared heater | 2362.62 | 51622.76 | -13890.8 | -26.91% | 0.06755% | 37731.96 | 51622.76 | -13890.8 | 2014-10-01 | 2015-09-30 | 2014-06-01 | 6 | 2014-08-01 | 8
| 050.37250 | 050.2636.Bridgewood | Install 1686 ft 2 Inch PE to serve 14 residential lots | -8.82 | 9815.13 | 1501.24 | 15.3% | 0.02026% | 11316.37 | 9815.13 | 1501.24 | 2014-10-01 | 2015-09-30 | 2014-06-01 | 6 | 2014-08-01 | 8
| 050.37255 | 2738.COMMONWEALTH -NEW OFFICE | INSTALL 1650' OF 4" PE IN INDUSTRIAL PARK FOR NEW OFFICE | -122.34 | 14822.55 | -11075.52 | -74.72% | 0.006709% | 3747.03 | 14822.55 | -11075.52 | 2014-10-01 | 2015-09-30 | 2014-04-21 | 4 | 2015-04-21 | 4
| 050.37261 | 050.2635.Fox Road Rev Ext | Install 2,350 feet of 2 inch poly main forr one customer (Doug Brown) requesting natural gas service. | 2394.63 | 4895.26 | -9440.94 | -192.9% | -0.008139% | -4545.68 | 4895.26 | -9440.94 | 2014-10-01 | 2015-09-30 | 2014-05-15 | 5 | 2014-07-15 | 7
| 050.37301 | 2739.SVILLE.8th - COLLEGE LP | INSTALL IP MAIN TO REPLACE LP SYSTEM ON COLLEGE, 8th, 9th AND WASHINGTON | 5373.58 | 38918.57 | 16019.76 | 41.16% | 0.09836% | 54938.33 | 38918.57 | 16019.76 | 2014-10-01 | 2015-09-30 | 2012-02-01 | 2 | 2014-09-30 | 9
| 050.37351 | 050.2634.Slaughters upgrade | Install 2214 ft 4 Inch HD PE, 56 ft 2 Inch PE and 1 2 Inch Reg Station to increase capacity due to new Grain Dryer | -1161.64 | 62262.85 | 2077.7 | 3.337% | 0.1152% | 64340.55 | 62262.85 | 2077.7 | 2014-10-01 | 2015-09-30 | 2014-07-20 | 7 | 2014-09-28 | 9
| 050.37370 | 050.2636.Reg.Station Imp. | Project is for Reg. Station Improvements at various locations | 17189.52 | 24779.23 | -7589.71 | -30.63% | 0.03078% | 17189.52 | 24779.23 | -7589.71 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-11-30 | 11
| 050.37391 | 2739.BRUNERSTOWN RECT 2014 | REPLACE RECTICFIER ON BRUNERSTOWN RD IN SHELBYVILLE | -834.99 | 18678.9 | -13999.34 | -74.95% | 0.008378% | 4679.56 | 18678.9 | -13999.34 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37407 | 050.2734.CalBastel 2 inch Ext | 200 ft. of 2 ich PE - Cal Bastel | 923.08 | 2130.18 | -495.35 | -23.25% | 0.002927% | 1634.83 | 2130.18 | -495.35 | 2014-10-01 | 2015-09-30 | 2014-05-08 | 5 | 2014-09-28 | 9
| 050.37420 | 050.2637.Hansen Rd Rev-Ext | Install 490 feet of 2 inch PE main for one existing commercial customer (Faith Center of Paducah) | -220.97 | 3127.09 | -1358.38 | -43.44% | 0.003167% | 1768.71 | 3127.09 | -1358.38 | 2014-10-01 | 2015-09-30 | 2014-06-01 | 6 | 2014-09-28 | 9
| 050.37425 | Ground Bed 45 S | This project is to replace our depleted ground bed on U.S Highway 45 South in Mayfield, KY | -1125.07 | 11584.56 | -2778.75 | -23.99% | 0.01577% | 8805.81 | 11584.56 | -2778.75 | 2014-10-01 | 2015-09-30 | 2014-06-03 | 6 | 2015-09-30 | 9
| 050.37442 | 050.2634.Reg & ERX Rplmnt | Project to Install & Replace Regs, ERX Recorders | 67601.63 | 77135.3 | -9533.67 | -12.36% | 0.121% | 67601.63 | 77135.3 | -9533.67 | 2014-10-01 | 2015-09-30 | 2014-05-20 | 5 | 2014-10-28 | 10
| 050.37446 | PRP.2734.W.5th-S.Main Replc | 60 ft.-2 inch bare steel replc. - W5th-S.Main - Russ | 355.39 | 3559.5 | 2020.81 | 56.77% | 0.009991% | 5580.31 | 3559.5 | 2020.81 | 2014-10-01 | 2015-09-30 | 2014-05-02 | 5 | 2014-09-28 | 9
| 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | INSTALL 1310ft OF 2in PE IN LANCASTER ON ELLIOT STREET - THIS WAS CALLED LEXINGTON ALLEY - ACTUALLY ELLIOT STREET | 166634.94 | 135880.55 | 130956.72 | 96.38% | 0.4777% | 266837.27 | 135880.55 | 130956.72 | 2014-10-01 | 2015-09-30 | 2013-10-03 | 10 | 2014-11-30 | 11
| 050.37560 | 2735.Glasgow Office Land | Purchase of raw land for Glasgow, KY office | 173849.3 | 60000 | 117152.05 | 195.3% | 0.3172% | 177152.05 | 60000 | 117152.05 | 2014-10-01 | 2015-09-30 | 2014-06-01 | 6 | 2015-09-30 | 9
| 050.37575 | 2738.Lebanon Waterbath Heater | Purchase indirect waterbath heater from Total Energy Resources for Calvary station in Lebanon, KY. | 6352.35 | 64276.66 | 4890.39 | 7.608% | 0.1238% | 69167.05 | 64276.66 | 4890.39 | 2014-10-01 | 2015-09-30 | 2014-05-29 | 5 | 2014-11-30 | 11
| 050.37614 | PRP.2636.Hwy 181 | Install 811 ft 2 Inch PE to replace 435 ft 4 Inch Bare Stl. and 497 ft 2 Inch Hot tar coated pipe. 6 Customers will be involved | -220.87 | 33963.34 | -6730.06 | -19.82% | 0.04876% | 27233.28 | 33963.34 | -6730.06 | 2014-10-01 | 2015-09-30 | 2014-05-20 | 5 | 2014-07-01 | 7
| 050.37668 | PRP.2635.Brook St Replace | Retire 375 feet of 2 inch bare (100 ft of 2 inch bare running east to west is NOT MAPPED) Installing 375 ft. of 2 inch poly. 7 customers affected | 1112.75 | 5257.15 | 5843.42 | 111.2% | 0.01987% | 11100.57 | 5257.15 | 5843.42 | 2014-10-01 | 2015-09-30 | 2014-06-02 | 6 | 2014-07-30 | 7
| 050.37682 | 050.2636.Elwood Ct. | Install 300 Ft 2 Inch PE to serve 4 residential customers | -2537.76 | 6527.3 | 1551.02 | 23.76% | 0.01446% | 8078.32 | 6527.3 | 1551.02 | 2014-10-01 | 2015-09-30 | 2014-06-20 | 6 | 2014-07-01 | 7
| 050.37683 | 050.2636.Meridian Ct | Install 300 ft 2 Inch PE to serve 3 residential customers | -3164.79 | 6527.3 | 2886.12 | 44.22% | 0.01685% | 9413.42 | 6527.3 | 2886.12 | 2014-10-01 | 2015-09-30 | 2014-06-20 | 6 | 2014-07-01 | 7
| 050.37684 | 050.2636.Thorn Ridge Crossing | Install 515 ft 2 Inch PE to serve 13 residential customers | 185.98 | 4427.52 | -1980.12 | -44.72% | 0.004382% | 2447.4 | 4427.52 | -1980.12 | 2014-10-01 | 2015-09-30 | 2014-07-15 | 7 | 2014-08-25 | 8
| 050.37698 | 2739.LAW.EVERGREEN TBS 2014 | REBUILD THE LAWRENECEBURG EVERGREEN TBS STATION. THIS IS A BUDGETED ITEM FOR 2014 | 15938.49 | 38690.79 | -6741.43 | -17.42% | 0.0572% | 31949.36 | 38690.79 | -6741.43 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37699 | 2737.LAN.OLD DVILLE RD RECT | REPLACE THE RECTIFIER AND ANODE BED ON OLD DANVILLE ROAD IN LANCASTER. THIS IS A BUDGETED ITEM FOR 2014 | -834.99 | 27647.07 | -20882.39 | -75.53% | 0.01211% | 6764.68 | 27647.07 | -20882.39 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37701 | 2737.ODORANT TANK REMOVAL 14 | REMOVE AND RECYCLE THE ODORANT TANKS AT THE HARRODSBURG AND DANVILLE PURCHASE STATIONS. THIS WILL HAVE 4 ODORANT TANKS REMOVED FROM OUR SYSTEM THAT HAVE BEEN REPLACED WITH YZ SYSTEMS. THIS IS A BUDGETED ITEM FOR 2014 | -1023.4 | 18952.99 | -15643.21 | -82.54% | 0.005926% | 3309.78 | 18952.99 | -15643.21 | 2014-10-01 | 2015-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37743 | 050.2734.Henderson Ind.Park | 1600 ft.. of 4 inch steel HPD - Henderson Industrial Park - Franklin | 14851.13 | 35342.85 | -18762.59 | -53.09% | 0.02969% | 16580.26 | 35342.85 | -18762.59 | 2014-10-01 | 2015-09-30 | 2014-07-31 | 7 | 2014-09-28 | 9
| 050.37745 | 2636.WMR.Sensus Endpoints | Purchase 15,000 Sensus endpoints for installation in Owensboro, KY | 328663.8 | 1586909.8 | 130043.46 | 8.195% | 3.074% | 1716953.26 | 1586909.8 | 130043.46 | 2014-10-01 | 2015-09-30 | 2014-07-01 | 7 | 2015-06-30 | 6
| 050.37808 | 2738.SPR.HWY 150.CORNERSTONE | INSTALL 3500' OF 4" PE TO SERVE A NEW CUSTOMER ON 150 BYPASS ON WEST SIDE OF SPRINGFIELD - CORNERSTONE CHRISTIAN CHURCH | 619.67 | 14903.49 | 3060.75 | 20.54% | 0.03216% | 17964.24 | 14903.49 | 3060.75 | 2014-10-01 | 2015-09-30 | 2014-01-01 | 1 | 2014-09-30 | 9
| 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | INSTALL PIPE FOR NALLEY & HAYDON IN GREENSBURG | 24602.34 | 167242.45 | 26963.73 | 16.12% | 0.3477% | 194206.18 | 167242.45 | 26963.73 | 2014-10-01 | 2015-09-30 | 2014-06-01 | 6 | 2015-07-31 | 7
| 050.37863 | x | Replace station | 11924.37 | 40990.13 | 23861.01 | 58.21% | 0.1161% | 64851.14 | 40990.13 | 23861.01 | 2014-10-01 | 2015-09-30 | 2014-06-30 | 6 | 2014-09-28 | 9
| 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | REBUILD THE STATION AT TUNNEL LANE IN GREENSBURG FOR THE NEW 6" PE GAS LINE SERVING NALLEY AND HAYDON | 14905.74 | 41927.53 | -27021.79 | -64.45% | 0.02669% | 14905.74 | 41927.53 | -27021.79 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2015-08-31 | 8
| 050.37892 | PRP.2638.Mayfield 2014 | PRP.2638.Mayfield 2014 | 800035.53 | 666602.24 | 195099.96 | 29.27% | 1.543% | 861702.2 | 666602.24 | 195099.96 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2015-07-29 | 7
| 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | Replace approximately 1227 ft of 2 Inch Bare LP Stl with 2 Inch IP PE also retire 2 Low Pressure Reg Stations 13 customers involved. | 22060.25 | 47164.67 | -5029.65 | -10.66% | 0.07544% | 42135.02 | 47164.67 | -5029.65 | 2014-10-01 | 2015-09-30 | 2014-07-22 | 7 | 2014-12-31 | 12
| 050.37948 | 050.2736.W 8th St Relocate | The City of Hopkinsville has built parts of the new Municipal Building on top of our 4 inch steel gas main. | -590.81 | 8280.47 | 4186.21 | 50.56% | 0.02232% | 12466.68 | 8280.47 | 4186.21 | 2014-10-01 | 2015-09-30 | 2014-07-28 | 7 | 2014-08-30 | 8
| 050.37965 | 050.2636.Greenville 6 Inch Re | Relocate approximately 700 Ft of HPD Steel exposed in Creek Bank. | 114104 | 123381.36 | -1778.27 | -1.441% | 0.2177% | 121603.09 | 123381.36 | -1778.27 | 2014-10-01 | 2015-09-30 | 2014-07-10 | 7 | 2014-11-28 | 11
| 050.37992 | PRP.2635.Marion Westside | PRP.2635.Marion Westside | 460540.68 | 404045.26 | 85580.01 | 21.18% | 0.8766% | 489625.27 | 404045.26 | 85580.01 | 2014-10-01 | 2015-09-30 | 2013-10-17 | 10 | 2015-07-15 | 7
| 050.37999 | 050.2734.BelleHaven III | 2 inch PE Extension - Belle Haven III - Bowling Green | -587.59 | 7925.37 | -3757.27 | -47.41% | 0.007463% | 4168.1 | 7925.37 | -3757.27 | 2014-10-01 | 2015-09-30 | 2014-07-14 | 7 | 2014-09-28 | 9
| 050.38009 | 050.2637.Noble Road Relocatio | Relocate 700 feet of 8 inch HPD due to new Southern Coal Handling railroad tracks. We are letting customer pay contractor directly to lower gas main, customer is also providing the materials. | 20306.89 | 5932.5 | 17156.38 | 289.2% | 0.04134% | 23088.88 | 5932.5 | 17156.38 | 2014-10-01 | 2015-09-30 | 2014-08-04 | 8 | 2014-08-22 | 8
| 050.38015 | 2737.STN.LINCOLN PLAZA 2014 | INSTALL 425' OF 2" PE FOR NEW COMMERICAL BUILDING IN LINCOLN PLAZA STANFORD | -58.02 | 704.63 | 218.48 | 31.01% | 0.001653% | 923.11 | 704.63 | 218.48 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2015-08-01 | 8
| 050.38028 | 2738.SPR.W VIRGINIA AVE 2014 | INSTALL 150' OF 2" PE TO SERVE A NEW CUSTOMER | -30.78 | 1414.49 | -772.95 | -54.65% | 0.001149% | 641.54 | 1414.49 | -772.95 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2015-08-01 | 8
| 050.38038 | 050.2638.Douthitt St Ext | Install 485 ft of 2 inch PE for one new commercial customer | -2646.61 | 5350.57 | 5810.72 | 108.6% | 0.01998% | 11161.29 | 5350.57 | 5810.72 | 2014-10-01 | 2015-09-30 | 2014-07-28 | 7 | 2014-08-30 | 8
| 050.38046 | 050.2636.Vincent Station Rd. | Install 100 ft 2Inch PE to serve 1 Commercial Customer | 1248.36 | 2243.9 | -680.97 | -30.35% | 0.002798% | 1562.93 | 2243.9 | -680.97 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2014-08-30 | 8
| 050.38055 | PRP.2609.Fruithill Hoptown 2RT | Project created to retire approximately 26,000' of 6" Bare Transmission plant pipe, new 12" pipe is being installed on Distribution plant project 050.35013. | 48093.5 | 86142 | -38048.5 | -44.17% | 0.08611% | 48093.5 | 86142 | -38048.5 | 2014-10-01 | 2015-09-30 | 2014-09-10 | 9 | 2014-11-30 | 11
| 050.38086 | 050.2734.Northridge VII | 2 inch PE Extension Northridge VII - Bowling Green | -975.56 | 12478.77 | -5791.89 | -46.41% | 0.01197% | 6686.88 | 12478.77 | -5791.89 | 2014-10-01 | 2015-09-30 | 2014-06-16 | 6 | 2014-09-28 | 9
| 050.38155 | 050.2638.Commonwealth Dr Ext | Install 775 feet of 4 inch PE for one new commercial customer (Better Built Bldg office). | -421.89 | 5918.05 | -3079.41 | -52.03% | 0.005082% | 2838.64 | 5918.05 | -3079.41 | 2014-10-01 | 2015-09-30 | 2014-08-04 | 8 | 2014-09-30 | 9
| 050.38178 | 2739.LOCUST CREEK VILLA HOMES | INSTALL GAS MAIN TO SERVE 25 LOTS WITH VILLA HOMES BEING BUILT | 7357.09 | 15060.51 | -2320.43 | -15.41% | 0.02281% | 12740.08 | 15060.51 | -2320.43 | 2014-10-01 | 2015-09-30 | 2014-07-01 | 7 | 2014-09-30 | 9
| 050.38179 | 2735.WALL ST 2014 | INSTALL 100' OF 2" PE TO SERVE A NEW HOLIDAY INN HOTEL ON WALL ST | -45.06 | 1340.89 | -439.39 | -32.77% | 0.001614% | 901.5 | 1340.89 | -439.39 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2014-09-30 | 9
| 050.38187 | 050.2636.Aldi Hwy 54 | Install 400 ft 4Inch PE to serve the new Gateway Commons Commercial Developement | -165.55 | 3009 | -5921.02 | -196.8% | -0.005214% | -2912.02 | 3009 | -5921.02 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2014-08-30 | 8
| 050.38210 | 050.2636.Medley Rd. | Install 945 ft 2 Inch PE to serve 5 residential customers | -1573.41 | 7837.58 | -3518.13 | -44.89% | 0.007734% | 4319.45 | 7837.58 | -3518.13 | 2014-10-01 | 2015-09-30 | 2014-08-10 | 8 | 2014-09-28 | 9
| 050.38212 | 2737.JC.MARGUS DR 2014 | INSTALL A 2" PE GAS MAIN FROM JONES LN ALONG EASEMENT TO SERVE COMMERICAL BUSSINESS ON MARGUS DR | -868.11 | 1878.75 | 3773.04 | 200.8% | 0.01012% | 5651.79 | 1878.75 | 3773.04 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2015-08-01 | 8
| 050.38233 | PRP.2735.HISE.CORAL HILL 14 | INSTALL 300' OF 2" PE TO REPLACE BARE STEEL ON CORAL HILL ST IN HISEVILLE | -532.68 | 21569.11 | -4429.08 | -20.53% | 0.03069% | 17140.03 | 21569.11 | -4429.08 | 2014-10-01 | 2015-09-30 | 2014-08-08 | 8 | 2014-09-30 | 9
| 050.38244 | 2737.JC.HWY 2141 2014 | INSTALL 925' OF 2" PE FOR NEW CUSTOMER SOUTH OF HWY 300 ON HWY 2141 IN JUNCTION CITY | -758.99 | 4333.33 | -3136.2 | -72.37% | 0.002143% | 1197.13 | 4333.33 | -3136.2 | 2014-10-01 | 2015-09-30 | 2014-06-01 | 6 | 2014-09-30 | 9
| 050.38277 | 050.2637.Olivet Relocation | Relocate 3,160' - 2" PE due to road improvements | 79940.34 | 28349.48 | 51590.86 | 182% | 0.1431% | 79940.34 | 28349.48 | 51590.86 | 2014-10-01 | 2015-09-30 | 2014-09-02 | 9 | 2015-06-30 | 6
| 050.38278 | 050.2635.Eddyville Mall Ext | Install 250' - 2" PE for a new seafood restaurant | 1010.9 | 1508.21 | -1269.27 | -84.16% | 0.0004278% | 238.94 | 1508.21 | -1269.27 | 2014-10-01 | 2015-09-30 | 2014-08-30 | 8 | 2014-09-28 | 9
| 050.38279 | 050.2638.Pryorsburg TB Repl | Replace TB (regulator station) Install upstream and downstream valves | 42552.39 | 15584.5 | 35532.99 | 228% | 0.09152% | 51117.49 | 15584.5 | 35532.99 | 2014-10-01 | 2015-09-30 | 2014-09-02 | 9 | 2015-07-30 | 7
| 050.38374 | 050.2637.Lovelaceville Rd Ext | Install 650 ft of 4 inch PE for two customers | 7282.13 | 3770.99 | 3825.75 | 101.5% | 0.0136% | 7596.74 | 3770.99 | 3825.75 | 2014-10-01 | 2015-09-30 | 2014-09-08 | 9 | 2014-10-30 | 10
| 050.38385 | MEC Forfeiture 040.009 FY14 | MEC Forfeiture 040.009 FY14 | -83175.07 | -208885.04 | -689454.5 | 330.1% | -1.608% | -898339.54 | -208885.04 | -689454.5 | 2014-10-01 | 2015-09-30 | 2014-08-29 | 8 | 2015-10-31 | 10
| 050.38415 | PRP.2734.Riverview & College | Replace bare main along Riverview, College and side streets | 448465.34 | 1001570.07 | -550044.64 | -54.92% | 0.8084% | 451525.43 | 1001570.07 | -550044.64 | 2014-10-01 | 2015-09-30 | 2014-07-28 | 7 | 2015-02-28 | 2
| 050.38532 | 050.2734.Aspen Place Ext. | 2 inch PE Extension - Aspen Place B.G. | 7169.35 | 9851.93 | -2682.58 | -27.23% | 0.01284% | 7169.35 | 9851.93 | -2682.58 | 2014-10-01 | 2015-09-30 | 2014-09-15 | 9 | 2014-12-30 | 12
| 050.38536 | 2735.CORAL HILL 2014 | INSTALL 1100' OF 4" PE FOR ONE CUSTOMER AND POSSIBLE 8 CONVERSTIONS | 40379 | 17294.84 | 23084.16 | 133.5% | 0.07229% | 40379 | 17294.84 | 23084.16 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2014-11-01 | 11
| 050.38537 | 050.2636.Boston Laffon Rd. | 1000 ft. of 2 inch pe to serve 10 residenttialo customers | 7209.6 | 8972.87 | -9117.9 | -101.6% | -0.0002597% | -145.03 | 8972.87 | -9117.9 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2014-10-31 | 10
| 050.38863 | 050.2636.Milton Rd. Ext | 2180 ft. of 2 inch PE - Milton Rd. - Oboro | 24481.54 | 11946.92 | 12534.62 | 104.9% | 0.04383% | 24481.54 | 11946.92 | 12534.62 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2014-12-30 | 12
| 050.38881 | 050.2734.CumberlandRdg.VI | 2 inch PE Extension - Cumberland Ridge VI - B.G. | 5636.22 | 9525.65 | -3889.43 | -40.83% | 0.01009% | 5636.22 | 9525.65 | -3889.43 | 2014-10-01 | 2015-09-30 | 2014-10-06 | 10 | 2014-12-15 | 12
| 050.38897 | PRP.2738.W HODGENVILL-McCULLE | REPLACE 600' OF 4" BARE PIPE ON WEST HODGENVILLE FROM 2ND TO 1ST AND ON 1590' OF 2" ON McCULLEN FROM LEGION PARK NORTH - 31 SERVICES | 223615.46 | 190161.96 | 33453.5 | 17.59% | 0.4004% | 223615.46 | 190161.96 | 33453.5 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-02-28 | 2
| 050.38903 | PRP.2735.Glasgow.E. Main St | Replace 1885 Ft 4 Inch Bare stl. with 2 Inch and 4 Inch Pe. 29 Services involved | 373615.77 | 346825.84 | 26789.93 | 7.724% | 0.6689% | 373615.77 | 346825.84 | 26789.93 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-05-30 | 5
| 050.38912 | 2637.New Office Furniture | Purchase furniture for new service center in Paducah, KY, | 124405.32 | 118659.55 | 5745.77 | 4.842% | 0.2227% | 124405.32 | 118659.55 | 5745.77 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2014-12-30 | 12
| 050.38923 | PRP.2636.E 17 th St Repl | Replace approximately 2984 ft of Bare Stl main with 1930 ft 2 Inch IP PE and 1054 ft 4 Inch IP PE. approximately 60 Services involved. | 166561.93 | 213543.57 | -46981.64 | -22% | 0.2982% | 166561.93 | 213543.57 | -46981.64 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-07-15 | 7
| 050.38935 | PRP.2735.HC Dale Heights_ | Replace 2587 ft Bare Stl with 2 Inch and 4 Inch PE. | 187829.43 | 218909.64 | -31080.21 | -14.2% | 0.3363% | 187829.43 | 218909.64 | -31080.21 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-04-30 | 4
| 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | REPLACE BARE PIPE ON MARIMON, EAST OFFICE, ROBARDS, BALLARD, MONITROSE, MAPLE AND HIGH | 1172076.3 | 1212179.37 | -40103.07 | -3.308% | 2.098% | 1172076.3 | 1212179.37 | -40103.07 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-09-28 | 9
| 050.38963 | 2739.OFFICE ASPHALT.REAR PARK | ASPHALT THE BACK LOT TO GET TO THE WAREHOUSE FOPR PARKING AND TURN AROUND SPCE FRO CREW TRUCKS. REMOVE CONCRETE WALLS | 57787 | 57787 | 0 | 0% | 0.1035% | 57787 | 57787 | 0 | 2014-10-01 | 2015-09-30 | 2014-10-20 | 10 | 2014-12-30 | 12
| 050.38964 | 2739.ERX FOR SHELBYVILLE | PURCHASE 4 MI WIRELESS INSTRUMENTS WITH ERX FOR INSTALLATION IN THE SHELBYVILLE OPERATIONS. ERXS INSTALLED AT: FOUR ROSES DISTILLERY, FLORIDA TILE STATION, MARTINREA STATION, MT. EDEN STATION | 19456.41 | 16271.24 | 3185.17 | 19.58% | 0.03483% | 19456.41 | 16271.24 | 3185.17 | 2014-10-01 | 2015-09-30 | 2014-10-20 | 10 | 2015-06-28 | 6
| 050.38968 | PRP.2734.Bristow Rd. Replc | Replace Bares Steel Main on Bristow Rd. - B.G. | 82229.9 | 135278.75 | -53048.85 | -39.21% | 0.1472% | 82229.9 | 135278.75 | -53048.85 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-05-30 | 5
| 050.38969 | 050.2734.BristowMoorman PI | Bristow Rd. - Moorman Realignment - KY State Public Imprv. B.G. | 156490.56 | 106105.47 | 50385.09 | 47.49% | 0.2802% | 156490.56 | 106105.47 | 50385.09 | 2014-10-01 | 2015-09-30 | 2014-10-01 | 10 | 2015-08-01 | 8
| 050.38970 | 050.2636WhisperingMeadows II | 2 inch PE Extension - Meadow Grove II - Owensboro | 4930.96 | 5468.51 | -537.55 | -9.83% | 0.008828% | 4930.96 | 5468.51 | -537.55 | 2014-10-01 | 2015-09-30 | 2014-10-20 | 10 | 2015-01-28 | 1
| 050.38971 | 050.2636.DeerValleyExt. | 2 inch PE Extension - Deer Valley Sub. - Owensboro | 10787.4 | 11847.32 | -1059.92 | -8.946% | 0.01931% | 10787.4 | 11847.32 | -1059.92 | 2014-10-01 | 2015-09-30 | 2014-10-15 | 10 | 2014-11-30 | 11
| 050.38972 | PRP.2734.Nashville Rd. Replc. | 440 ft of 4 inch PE to replace bare steel for Leak - Brentmore at Nashville Rd - B.G. | 15203.72 | 24151.33 | -8947.61 | -37.05% | 0.02722% | 15203.72 | 24151.33 | -8947.61 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2014-10-31 | 10
| 050.39019 | 050.2736.E Pton Rd Ext | Coming off 8" HP (395 MAOP) run 100' - 2" steel, install 2" upstream valve, 100' - 2" steel, then small reg sta, 100' - 2" poly, 2" downstream valve, then 1,790' more 2: poly for commercial customer | 15672.66 | 15534.97 | 137.69 | 0.8863% | 0.02806% | 15672.66 | 15534.97 | 137.69 | 2014-10-01 | 2015-09-30 | 2014-10-20 | 10 | 2015-02-27 | 2
| 050.39034 | 2602.KY.Desktop.Repl.FY15 | This Project is for the standard yearly KY desktop one quarter replacement. We will replace 36 Desktops in this project. 36 Dell OptiPlex 7020 SFF | 43167.84 | 33714.8 | 9453.04 | 28.04% | 0.07729% | 43167.84 | 33714.8 | 9453.04 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-06-30 | 6
| 050.39035 | 2602.KY.Laptop.Replc.FY15 | This Project is for the standard yearly KY Laptop one quarter replacement. We will replace 18 Laptops in this project. 12 Dell Latitude 14 5000 Series, 5 Dell Latitude E 7250, 1 Dell Tablet Venue Pro | 29769.7 | 42143.5 | -12373.8 | -29.36% | 0.0533% | 29769.7 | 42143.5 | -12373.8 | 2014-10-01 | 2015-09-30 | 2014-10-21 | 10 | 2015-07-31 | 7
| 050.39036 | 2602.KY.MDT.Replac.FY15 | This Project is for the standard yearly KY MDT one quarter replacement. We will replace 26 MDT's in this project. 26 Panasonic CF-31 Toughbook | 120230.51 | 120410 | -179.49 | -0.1491% | 0.2153% | 120230.51 | 120410 | -179.49 | 2014-10-01 | 2015-09-30 | 2014-10-21 | 10 | 2015-06-30 | 6
| 050.39044 | 2737.JC.W EADES AVE 15 | INSTALL 250' OF 2" PE FOR NEW CHURCH ON US HIGHWAY 127 IN JUNCTION CITY | 331.01 | 1043.32 | -712.31 | -68.27% | 0.0005926% | 331.01 | 1043.32 | -712.31 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-08-01 | 8
| 050.39079 | 050.2637.Coleman Rd Ext | Install app. 7780 feet of 2 inch PE main for new Paducah office | 3884.85 | 4298.95 | -414.1 | -9.633% | 0.006955% | 3884.85 | 4298.95 | -414.1 | 2014-10-01 | 2015-09-30 | 2014-10-20 | 10 | 2014-11-30 | 11
| 050.39087 | PRP.2635.Marion Eastside | Replaces approximately 4173 ft of 2 Inch Bare main with 2 Inch PE approximately 40 customers will be involved with this replacement. | 227905.52 | 292646.32 | -64740.8 | -22.12% | 0.408% | 227905.52 | 292646.32 | -64740.8 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-11-30 | 11
| 050.39094 | 050.2637.Valerie Ln Main Ext | install 100 ft for one customer | 3573.25 | 1119.8 | 2453.45 | 219.1% | 0.006398% | 3573.25 | 1119.8 | 2453.45 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2014-11-30 | 11
| 050.39095 | 050.2637.Pepper Ln Ext | install 100 ft for one customer | 1958.33 | 1089.72 | 868.61 | 79.71% | 0.003506% | 1958.33 | 1089.72 | 868.61 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2014-11-30 | 11
| 050.39096 | 050.2637.Highland Ch Rd Ext | 400 ft extension for one residential customer (Brian Heine) requesting gas at 930 Highland Church Rd | 4774.2 | 933.68 | 3840.52 | 411.3% | 0.008548% | 4774.2 | 933.68 | 3840.52 | 2014-10-01 | 2015-09-30 | 2014-11-03 | 11 | 2014-12-30 | 12
| 050.39097 | 050.2637.Strathmoore Ext | Installm 225 feet of 2 inch PE for one existing residential customer (William Hatcher requesting natural gas service at 214 Strathmoore Blvd. | 1856.5 | 568.74 | 1287.76 | 226.4% | 0.003324% | 1856.5 | 568.74 | 1287.76 | 2014-10-01 | 2015-09-30 | 2014-10-27 | 10 | 2014-12-30 | 12
| 050.39098 | 050.2637.Park Ave Relocate | Relocate 2" pe. It is currently in the middle of a lot | 8726.84 | 2856.57 | 5870.27 | 205.5% | 0.01562% | 8726.84 | 2856.57 | 5870.27 | 2014-10-01 | 2015-09-30 | 2014-10-30 | 10 | 2015-02-28 | 2
| 050.39099 | 050.2637.Key Dr Rev Ext | Install 80' - 2 inch PE main for one exisitng residential customer (Chris Colson Auction & Realty) | 4259.16 | 1069 | 3190.16 | 298.4% | 0.007626% | 4259.16 | 1069 | 3190.16 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-02-27 | 2
| 050.39101 | 050.2637.Lakes of Paducah | Install 2,200 ft of 2 inch pe for The Lakes of Paducah senior living community, there will be future extensions in this area. | -1950.16 | 6696.85 | -8647.01 | -129.1% | -0.003492% | -1950.16 | 6696.85 | -8647.01 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-02-27 | 2
| 050.39106 | 050.2637.Krebs Sta Rd Ext | Install 385' for two existing residential customers. One customer requesting service. | 3370.99 | 2084.16 | 1286.83 | 61.74% | 0.006035% | 3370.99 | 2084.16 | 1286.83 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-02-27 | 2
| 050.39115 | 050.2635.Cerulean Rd Replace | Relocate 250 feet of 2 inch PE pipe, property owner cutting down bank along Ky 124 (Cerulean Rd) in Cadiz, KY | 1203.13 | 0 |  |  | 0.002154% | 1203.13 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2014-11-03 | 11 | 2014-12-31 | 12
| 050.39117 | 2738.ROLAND ST-MOBILE HOME 15 | INSTALL 1271' OF 2" PE FOR MOBILE HOME DEVELOPMENT | 4632.36 | 4200.32 | 432.04 | 10.29% | 0.008294% | 4632.36 | 4200.32 | 432.04 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-06-01 | 6
| 050.39143 | BowlingGreen Cisco Switch Repl | Replace Bowling Green, KY Cisco network switch. Lightning storm hit building and destroyed existing switch. | 12462.23 | 11772.72 | 689.51 | 5.857% | 0.02231% | 12462.23 | 11772.72 | 689.51 | 2014-10-01 | 2015-09-30 | 2014-11-04 | 11 | 2014-12-30 | 12
| 050.39151 | 2634.Woodlawn.Dr.Lot.Pur.FY15 | Purchase lot from Mt. Zion Church. Lot is located at Woodlawn Drive in Earlington, KY 42410. Existing station sits on lot. | 2723.21 | 2000 | 723.21 | 36.16% | 0.004876% | 2723.21 | 2000 | 723.21 | 2014-10-01 | 2015-09-30 | 2014-11-04 | 11 | 2014-12-30 | 12
| 050.39170 | 2738.RIGHT OF WAY EQUIPMENT | PURCHASE BOBCAT WITH BRUSH CUTTER FOR RIGHT OF WAY CLEARING | 104062.05 | 99855 | 4207.05 | 4.213% | 0.1863% | 104062.05 | 99855 | 4207.05 | 2014-10-01 | 2015-09-30 | 2014-09-24 | 9 | 2015-10-31 | 10
| 050.39171 | 2738.2015 EQUIPMENT | PURCHASE THE FOLLOWING EQUIPMENT - 1 GAUGE, 4-BRUEST HEATERS, 4 ERX RECORDERS | 26991.08 | 26628.03 | 363.05 | 1.363% | 0.04832% | 26991.08 | 26628.03 | 363.05 | 2014-10-01 | 2015-09-30 | 2014-09-24 | 9 | 2015-10-31 | 10
| 050.39174 | 050.2635.Old Grinell Retire | Abandon app. 400 feet of 4 inch HP Steel gas main no longer being utilized. | 10211.82 | 12739.32 | -2527.5 | -19.84% | 0.01828% | 10211.82 | 12739.32 | -2527.5 | 2014-10-01 | 2015-09-30 | 2014-11-03 | 11 | 2014-12-31 | 12
| 050.39179 | 2735.CHEVY LN 2015 | INSTALL 250' FOR A NEW CUSTOMER ON CHEVY LN IN GLASGOW - THIS COULD BE USED FOR FURTHER RELIEF OF TRANSMISSION TAPS AND FARM TAPS ON CHEVY LANE | 4157.38 | 1495.48 | 2661.9 | 178% | 0.007443% | 4157.38 | 1495.48 | 2661.9 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-02-01 | 2
| 050.39190 | 2737.2015 EQUIPMENT | PURCHASE THE FOLLOWING EQUIPMENT - 2" VALVE CHANGER, CONCRETE SAW, 2 - PIPE LOCATORS, DITCH WITCH PIERCE ARROW | 44380.4 | 56185.08 | -11804.68 | -21.01% | 0.07946% | 44380.4 | 56185.08 | -11804.68 | 2014-10-01 | 2015-09-30 | 2014-09-24 | 9 | 2015-10-31 | 10
| 050.39194 | 2737.INTERIOR RENOVATION 2015 | RENOVATE RESTROOMS - BRING UP TO ADA REQUIREMENTS, REPLACE CONFERENCE ROOM CARPET WITH TILE | 40489.38 | 30000 | 10489.38 | 34.96% | 0.07249% | 40489.38 | 30000 | 10489.38 | 2014-10-01 | 2015-09-30 | 2014-09-24 | 9 | 2015-10-31 | 10
| 050.39195 | 2737.BUILD ADD-TRUCK BAY 2015 | BUILDING ADDITION - TRUCK BAY AT REAR OF BUILDING TO ACCOMIDATE LARGER TRUCKS - ADDS ROOM FOR COMPLIANCE PERSONEL | 108429.09 | 62000 | 46429.09 | 74.89% | 0.1941% | 108429.09 | 62000 | 46429.09 | 2014-10-01 | 2015-09-30 | 2014-09-24 | 9 | 2015-10-31 | 10
| 050.39201 | Bon Harbor/ANR RTU.15 | Bon Harbor/ANR RTU and Station Upgrade | 18825.5 | 32766.87 | -13941.37 | -42.55% | 0.03371% | 18825.5 | 32766.87 | -13941.37 | 2014-10-01 | 2015-09-30 | 2014-11-10 | 11 | 2015-09-15 | 9
| 050.39210 | Replace ECAT Correctors.KY.15 | Replacement of obsolete ECAT Correctors in Kentucky for FY15 | 23544.61 | 18049.55 | 5495.06 | 30.44% | 0.04215% | 23544.61 | 18049.55 | 5495.06 | 2014-10-01 | 2015-09-30 | 2014-12-02 | 12 | 2015-09-30 | 9
| 050.39211 | Electronic Corr. Trans. KY.15 | Electronic Correctors for Transportation Customers | 35874.04 | 24230.25 | 11643.79 | 48.05% | 0.06423% | 35874.04 | 24230.25 | 11643.79 | 2014-10-01 | 2015-09-30 | 2014-12-02 | 12 | 2015-09-30 | 9
| 050.39218 | 050.2636.Equipment FY 2015 | Mueller No Blo Valve Changer for 3/4" - 1" and 11/4" Meter Valves $ 2885.52 Mueller No Blo Valve Changer for 11/2" and 2" Mater Valves $3598.95 Hand Held Plasma Cutter $1650.00 2- VM 810 Metrotech Locators - $ 3500.00 each - total $7000.00 Boss III El | 24098.99 | 24143.61 | -44.62 | -0.1848% | 0.04315% | 24098.99 | 24143.61 | -44.62 | 2014-10-01 | 2015-09-30 | 2014-11-12 | 11 | 2015-09-28 | 9
| 050.39258 | 2739.CLOVERBROOK SEC 9-PH 2 | INSTALL 550' OF 2" PE TO SERVE 20 CUSTOMERS AND COMPLETE THE LINE ON EDGEMONT WAY | 14157.41 | 6317.51 | 7839.9 | 124.1% | 0.02535% | 14157.41 | 6317.51 | 7839.9 | 2014-10-01 | 2015-09-30 | 2014-11-15 | 11 | 2015-03-01 | 3
| 050.39270 | 050.2634.McCoy Ave Ext | Install 100 ft of 2 inch poly for one customer (City of Madisonville) | 1523.84 | 1219.65 | 304.19 | 24.94% | 0.002728% | 1523.84 | 1219.65 | 304.19 | 2014-10-01 | 2015-09-30 | 2014-11-05 | 11 | 2014-12-31 | 12
| 050.39271 | 050.2736.Russellville Rd Ext | Install 1,000 feet for commerciall and residential customers | 16586.55 | 21100.66 | -4514.11 | -21.39% | 0.0297% | 16586.55 | 21100.66 | -4514.11 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-02-27 | 2
| 050.39272 | PRP.2636.Coast Guard Ln. | Replace 1500 Ft 2" Bare Stl with 2 Inch PE 23 residential customers involved. Work being done with Company Crew. | 26656.07 | 37779.19 | -11123.12 | -29.44% | 0.04772% | 26656.07 | 37779.19 | -11123.12 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-08-01 | 8
| 050.39281 | 050.2635.Mechanic St Ext | Install 100 feet of 2 inch poly for one existing residential mcustomer requesting gas service | 2760.53 | 1312.53 | 1448 | 110.3% | 0.004942% | 2760.53 | 1312.53 | 1448 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2014-12-31 | 12
| 050.39282 | SCBA - Glasgow | 2 SCBA respirators, 2 masks, 2 extra respirator tanks, 2 hard carry cases for use in Glasgow, KY | 7227.78 | 6803.16 | 424.62 | 6.242% | 0.01294% | 7227.78 | 6803.16 | 424.62 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-01-30 | 1
| 050.39294 | PRP.2734.Church & Nugent St. | Install 2350 Ft 2 Inch Pe on Church and Nugent St in Bowling Green Ky replacing bare Steel Main , approximately 28 Services involved. | 134083.67 | 187511.1 | -53427.43 | -28.49% | 0.2401% | 134083.67 | 187511.1 | -53427.43 | 2014-10-01 | 2015-09-30 | 2014-11-30 | 11 | 2015-06-30 | 6
| 050.39297 | 2739.HERITAGE PARK 2014 | INSTALL GAS MAIN TO SERVE 7 COMMERICAL LOTS OFF OF FREEDOM'S WAY IN SHELBYVILLE | 12990.21 | 21360.7 | -8370.49 | -39.19% | 0.02326% | 12990.21 | 21360.7 | -8370.49 | 2014-10-01 | 2015-09-30 | 2014-11-15 | 11 | 2015-03-01 | 3
| 050.39308 | 2602.Paducah.KY.Mapping.TV | Purchase Samsung 60" LED television and mount for Paducah office. The purpose of this TV is the use of Field Smart View for mapping. | 1169.94 | 1174.22 | -4.28 | -0.3645% | 0.002095% | 1169.94 | 1174.22 | -4.28 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2014-12-31 | 12
| 050.39309 | 2602.Campbellsville.TV.Mapping | Purchase Samsung tv for using with Field Smartview in association with Mapping. TV is a Samsung LC-70LE650U. | 4011.92 | 1204.1 | 2807.82 | 233.2% | 0.007183% | 4011.92 | 1204.1 | 2807.82 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2014-12-31 | 12
| 050.39314 | 050.2637.Ridge Rd Ext | Install 500' - 2" pe for one exising residential customer (David Greeman requesting service | 25052.93 | 25100.09 | -47.16 | -0.1879% | 0.04485% | 25052.93 | 25100.09 | -47.16 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-02-28 | 2
| 050.39366 | PRP.2734.Russell W.9th St. | Install 3500 ft 4 Inch PE and 400 ft 2 Inch PE to replace Bare steel main in Russellville Ky , 42 Services will be involved. | 324909.44 | 345134.63 | -20225.19 | -5.86% | 0.5817% | 324909.44 | 345134.63 | -20225.19 | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-08-30 | 8
| 050.39371 | Madisonville Equipment | Equipment includes 4 heath locators, grease gun, pipe cutters, trencher attachment, back fill blade, Vemmeer mole, hydro pump for trailer, and a Mueller valve tapping tool. | 50311.92 | 49528.08 | 783.84 | 1.583% | 0.09008% | 50311.92 | 49528.08 | 783.84 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-03-31 | 3
| 050.39372 | Princeton Equipment | Equipment for use in the Princeton area including 3 ERX's, saw, fusion spacers, smart cal, utility trailer, | 29628.29 | 31114.87 | -1486.58 | -4.778% | 0.05305% | 29628.29 | 31114.87 | -1486.58 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-07-31 | 7
| 050.39373 | 2612.RTU Upgrades.KY.15 | Purchase of 3 RTUs for Kentucky operations in FY15 | 9566.14 | 43420.04 | -33853.9 | -77.97% | 0.01713% | 9566.14 | 43420.04 | -33853.9 | 2014-10-01 | 2015-09-30 | 2014-12-04 | 12 | 2015-03-31 | 3
| 050.39376 | 2612.Comm&Indus Meters.KY.15 | Purchase of large commercial and industrial meters for KY operations | 14253.58 | 14453.63 | -200.05 | -1.384% | 0.02552% | 14253.58 | 14453.63 | -200.05 | 2014-10-01 | 2015-09-30 | 2015-02-01 | 2 | 2015-07-28 | 7
| 050.39378 | 2612.CorrectorModemUpg.KY.15 | Purchase of corrector modems to secure network modem | 20722.08 | 19306.16 | 1415.92 | 7.334% | 0.0371% | 20722.08 | 19306.16 | 1415.92 | 2014-10-01 | 2015-09-30 | 2015-03-01 | 3 | 2015-07-31 | 7
| 050.39380 | 2612.Emergency Regs.KY.15 | Purchase of Emergency Regulators for KY operations in FY15 | 2610.23 | 30125.55 | -27515.32 | -91.34% | 0.004673% | 2610.23 | 30125.55 | -27515.32 | 2014-10-01 | 2015-09-30 | 2015-04-01 | 4 | 2015-09-30 | 9
| 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | RELOCATE 60' OF HPD STEEL PIPE ON OLD BRUNERSTOWN ROAD FOR THE BUILDING OF A LOT FOR TRACTOR SUPPLY STORE | -131.72 | 172.6 | -304.32 | -176.3% | -0.0002358% | -131.72 | 172.6 | -304.32 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-04-01 | 4
| 050.39386 | 050.2635.Phoenix Dr Ext | Install 220 feet of 2 inch poly for one new commercial customer (Phoenix Storage Solutions, LLC) | 156.79 | 1400.8 | -1244.01 | -88.81% | 0.0002807% | 156.79 | 1400.8 | -1244.01 | 2014-10-01 | 2015-09-30 | 2014-12-08 | 12 | 2015-01-30 | 1
| 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | TD WILLIAMSON 4"&2" MACHINES 2 OF EACH, DW PIPE LOCATORS, SEWERIN ETHANE DETECTOR, SQUEEZE OFF TOOLS (2), SENSIT GOLD, ERX w/MODEM, BOSS III EF UNIT | 43130.48 | 43337.08 | -206.6 | -0.4767% | 0.07722% | 43130.48 | 43337.08 | -206.6 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-06-01 | 6
| 050.39399 | 050.2637.H C Mathis Ext | Install 115 feet of 2 inch pe for one new commercial business | 8301.39 | 1865.07 | 6436.32 | 345.1% | 0.01486% | 8301.39 | 1865.07 | 6436.32 | 2014-10-01 | 2015-09-30 | 2014-12-08 | 12 | 2015-02-28 | 2
| 050.39403 | Hopkinsville Equipment | Misc equipment for use in the Hopkinsville area. includes ERX's, air ratchet, concrete saw, locators, stop changers, calibration test station, etc. | 39086.9 | 43050.8 | -3963.9 | -9.207% | 0.06998% | 39086.9 | 43050.8 | -3963.9 | 2014-10-01 | 2015-09-30 | 2014-12-09 | 12 | 2015-09-28 | 9
| 050.39405 | PRP.2739.Shelbyville 12 Inch | Replace 9 miles of 8 Inch steel with 12 Inch Steel, see addtional comments. | 13780612.23 | 16281504.53 | -2500892.3 | -15.36% | 24.67% | 13780612.23 | 16281504.53 | -2500892.3 | 2014-10-01 | 2015-09-30 | 2014-12-10 | 12 | 2016-01-30 | 1
| 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2" MUELLER VALVE CHANGER, 4 SURELOK LOCATORS, 4 ERX, 150psi COMPRESSOR | 33073.82 | 31287.91 | 1785.91 | 5.708% | 0.05922% | 33073.82 | 31287.91 | 1785.91 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-09-01 | 9
| 050.39436 | 050.2638.Ken Tex Rd Ext | Install 1,500 feet of 2 inch poly pipe for ACE Compressor. They are converting from propane. | 1734.66 | 6937.24 | -5202.58 | -74.99% | 0.003106% | 1734.66 | 6937.24 | -5202.58 | 2014-10-01 | 2015-09-30 | 2014-11-17 | 11 | 2015-02-27 | 2
| 050.39453 | 050.2636.GoshenRd. Ext | 330 ft. of 4 inch PE Extension - Goshen Rd. - Beaver Dam | 4686.67 | 5053.65 | -366.98 | -7.262% | 0.008391% | 4686.67 | 5053.65 | -366.98 | 2014-10-01 | 2015-09-30 | 2014-12-15 | 12 | 2015-02-15 | 2
| 050.39474 | PRP.2636.Walnut St.Rpl | Replace approximately 500 Ft 3 Inch bare steel and 237 Ft 2 Inch bare steel with 2 Inch PE, 22 services involved. | 37259.31 | 38007.74 | -748.43 | -1.969% | 0.06671% | 37259.31 | 38007.74 | -748.43 | 2014-10-01 | 2015-09-30 | 2014-12-10 | 12 | 2015-04-30 | 4
| 050.39477 | 050.2636.Brownwood Oaks II | 700 ft. of 2 inch PE to serve 14 new lots - Brownwood Oaks II unit one - owensboro | 5814.05 | 4259.96 | 1554.09 | 36.48% | 0.01041% | 5814.05 | 4259.96 | 1554.09 | 2014-10-01 | 2015-09-30 | 2014-11-10 | 11 | 2015-12-10 | 12
| 050.39478 | 050.2734.EaglestoneReloc.B.G. | Relocate 2 inch PE - New Development - Eaglestone B.G | 6457.47 | 7088.5 | -631.03 | -8.902% | 0.01156% | 6457.47 | 7088.5 | -631.03 | 2014-10-01 | 2015-09-30 | 2014-12-16 | 12 | 2015-02-18 | 2
| 050.39482 | Mayfield Equipment | Misc equipment for use in the Mayfield area including ERX's, Electro Fuse machine, and a Metrotech pipe locator. | 42012.55 | 40075.12 | 1937.43 | 4.834% | 0.07522% | 42012.55 | 40075.12 | 1937.43 | 2014-10-01 | 2015-09-30 | 2014-12-17 | 12 | 2015-05-30 | 5
| 050.39492 | Paducah Equipment | This project is for equipment to be used in the Paducah area including a yet to be determined number of ERX's, 3 water pumps, 2 Metrotech pipe locators, and one Jameson plastic line locator. | 49395.93 | 39942 | 9453.93 | 23.67% | 0.08844% | 49395.93 | 39942 | 9453.93 | 2014-10-01 | 2015-09-30 | 2014-12-19 | 12 | 2015-07-31 | 7
| 050.39531 | PRP.2735.HC Woodlawn | Replace 6300 ft of 4 Inch and 6 Inch Bare LP and IP steel with 5969 ft 2 Inch and 331 ft 4 Inch PE IP. Approximately 86 services involved Commercial/Residential. See additional commets above | 461058.92 | 490994.76 | -29935.84 | -6.097% | 0.8255% | 461058.92 | 490994.76 | -29935.84 | 2014-10-01 | 2015-09-30 | 2015-02-01 | 2 | 2015-09-30 | 9
| 050.39533 | PRP.2635.Sturgis Rd. | Replace 6792 ft of 4 Inch Bare Stl.IP with 6306 ft 4 Inch PE and 612 ft 2 inch PE IP in Marion ky. approximately 83 services involved. | 494821.08 | 486298.95 | 8522.13 | 1.752% | 0.8859% | 494821.08 | 486298.95 | 8522.13 | 2014-10-01 | 2015-09-30 | 2014-12-30 | 12 | 2015-11-20 | 11
| 050.39546 | 050.2637.Fisher Blvd Ext | Install 300' - 2 inch PE for two existing residential customers | 19532.2 | 20715.76 | -1183.56 | -5.713% | 0.03497% | 19532.2 | 20715.76 | -1183.56 | 2014-10-01 | 2015-09-30 | 2015-01-26 | 1 | 2015-02-27 | 2
| 050.39549 | 050.2637.Royal Park Dr 3 | Install 530 feet - 2 inch PE for one new and four vacant lots | 14857.87 | 14857.87 | 0 | 0% | 0.0266% | 14857.87 | 14857.87 | 0 | 2014-10-01 | 2015-09-30 | 2015-02-09 | 2 | 2015-03-31 | 3
| 050.39552 | 050.2637.Lakewood Villas - 1 | Install 470 feet of 2 inch PE for 2 fourplex condominiums | 13014.89 | 2897.73 | 10117.16 | 349.1% | 0.0233% | 13014.89 | 2897.73 | 10117.16 | 2014-10-01 | 2015-09-30 | 2015-02-16 | 2 | 2015-03-31 | 3
| 050.39578 | 050.2734.MackenzieMeadows | 2 inch PE Extension - Mackenzie Meadows - Bowling Green | 12195.94 | 12797.59 | -601.65 | -4.701% | 0.02184% | 12195.94 | 12797.59 | -601.65 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-09-28 | 9
| 050.39584 | PRP.2734.Vine St | Replace 1100 ft 2 Inch Stl. IP with 1100 ft 2 Inch PE IP. In Bowling Green Ky approximately 23 services involved. | 43128.75 | 48442.09 | -5313.34 | -10.97% | 0.07722% | 43128.75 | 48442.09 | -5313.34 | 2014-10-01 | 2015-09-30 | 2015-01-15 | 1 | 2015-08-30 | 8
| 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | INSTALL 1750' OF 2" PE FOR 4 CHICKEN HOUSES ON D HALL LN IN SUMMERSVILLE | 1632 | 681.42 | 950.58 | 139.5% | 0.002922% | 1632 | 681.42 | 950.58 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-06-01 | 6
| 050.39589 | 050.2734.North-South Replc | Replace 2" coated steel with 2" PE - Land Development-North South Corridoe - B.G. | 4073.35 | 0 |  |  | 0.007293% | 4073.35 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2015-01-19 | 1 | 3015-03-31 | 3
| 050.39606 | 2735.GLS.HARBISON WYATT 15 | INSTALL 300' OF 2" PE FOR ONE CUSTOMER | 765.43 | 0 |  |  | 0.00137% | 765.43 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2014-12-01 | 12 | 2015-02-01 | 2
| 050.39614 | PRP.2637.Monroe St | Replace approximately 300 ft of 4 Inch bare Stl. IP with 300 ft of 4 Inch IP PE, 11 services involved | 34424.21 | 22703.7 | 11720.51 | 51.62% | 0.06163% | 34424.21 | 22703.7 | 11720.51 | 2014-10-01 | 2015-09-30 | 2015-01-25 | 1 | 2015-03-30 | 3
| 050.39623 | PRP.2738.Legion Park Penick | Replace approximately 3510 ft of bare IP Stl main with 2104 ft of 4 Inch IP PE and 1411 ft of 2 Inch IP PE in Greensburg Ky. 33 Services are involved. | 186334.1 | 306532.41 | -120198.31 | -39.21% | 0.3336% | 186334.1 | 306532.41 | -120198.31 | 2014-10-01 | 2015-09-30 | 2015-02-15 | 2 | 2015-07-30 | 7
| 050.39647 | 2602.ITRON.Replacement.FY15 | This is a 4 year replacement of already failing Itron FC300 handhelds. Four to Five units will be purchased. | 17004.97 | 16857.4 | 147.57 | 0.8754% | 0.03045% | 17004.97 | 16857.4 | 147.57 | 2014-10-01 | 2015-09-30 | 2015-02-01 | 2 | 2015-06-30 | 6
| 050.39659 | 050.2636.Essex Dr. Ext | 1072 ft. of 2 inch PE - Essex Dr. Extension - Owensboro | 7807.14 | 12439.8 | -4632.66 | -37.24% | 0.01398% | 7807.14 | 12439.8 | -4632.66 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-03-16 | 3
| 050.39660 | 050.2636.Celebration Circle | 2 inch PE Extension - Celebration Circle - Owensboro | 9846.65 | 16810.46 | -6963.81 | -41.43% | 0.01763% | 9846.65 | 16810.46 | -6963.81 | 2014-10-01 | 2015-09-30 | 2015-01-12 | 1 | 2015-07-01 | 7
| 050.39661 | 050.2636.Worthington Rd. Ext. | 170 ft. of 2 inch PE - Worthington Rd. | 2805.46 | 2955.4 | -149.94 | -5.073% | 0.005023% | 2805.46 | 2955.4 | -149.94 | 2014-10-01 | 2015-09-30 | 2015-01-19 | 1 | 2015-03-30 | 3
| 050.39664 | 050.2609.6 Well Head Replc.15 | Replace 6 Well Heads - Storage | 798146.86 | 931672.82 | -133525.96 | -14.33% | 1.429% | 798146.86 | 931672.82 | -133525.96 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-09-28 | 9
| 050.39677 | 050.2734.Mics Equipment - B.G. | 2- Odorators - $4994.00 5 - ERX'S - $17,500.00 2 - Squeeze Off Tools - $6954.00 1 - Sensit Locator - $1391.00 1- Gator with Trailer and DPI- $24,321 | 66820.63 | 73440.02 | -6619.39 | -9.013% | 0.1196% | 66820.63 | 73440.02 | -6619.39 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-09-28 | 9
| 050.39686 | PRP.2634.Main St Sebree | Replace approximately 2406 ft of 4 Inch and 2 Inch Bare LP Stl. with 2232 ft IP PE. Bare pipe has leakage and customer outages are occuring due to water and extreme temperature changes. Work to be done with Company Crews 40 services involved. | 53722.68 | 57620.33 | -3897.65 | -6.764% | 0.09618% | 53722.68 | 57620.33 | -3897.65 | 2014-10-01 | 2015-09-30 | 2015-01-27 | 1 | 2015-07-30 | 7
| 050.39688 | 050.2734.HPDRiverRelocAdvl | 3 inch Steel Relocation - Adairville River Crossing | 18255.61 | 64381.86 | -46126.25 | -71.64% | 0.03268% | 18255.61 | 64381.86 | -46126.25 | 2014-10-01 | 2015-09-30 | 2014-11-01 | 11 | 2015-11-30 | 11
| 050.39699 | Retire Tractor | Retire 1987 Case Tractor, includes front end loader and bushog attachment. The unit still runs pretty good. The salvage value is $4,000 | -4000 | 0 |  |  | -0.007162% | -4000 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2015-01-26 | 1 | 2015-03-31 | 3
| 050.39729 | 2738.NEWCOMB.MEADOW CRK 2015 | INSTALL 4650' OF MAIN AND 1850' OF SERVICE TO SERVE A NEW CHICKEN HOUSE ON MEADOW CREEK ROAD PAST EXISTING CHICKEN HOUSES - MAIN INSTALLED 2013 | 19792.14 | 24610.37 | -4818.23 | -19.58% | 0.03544% | 19792.14 | 24610.37 | -4818.23 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-09-01 | 9
| 050.39743 | 050.2636.Leitchfield Rd. Ext. | 175 ft. of 2 inch PE - Leitchfield Rd. - Owensboro | 4899.25 | 5460.61 | -561.36 | -10.28% | 0.008772% | 4899.25 | 5460.61 | -561.36 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-03-16 | 3
| 050.39744 | 050.2636.Retire4inchSPTrans. | Retire 4094 ft. of 4 inch MW Trans. Line - TB4 to 5th st. Rd. | 3789.2 | 9459.53 | -5670.33 | -59.94% | 0.006784% | 3789.2 | 9459.53 | -5670.33 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-04-27 | 4
| 050.39756 | PRP.2737.Lexington-Greenville | Replace 5479 ft of Bare 2 and 6 Inch Stl. with 3191 ft of 2 Inch PE IP, 1522 ft of 6 Inch IP PE. and 1018 ft of 4 Inch IP PE. approximately 87 Services involved | 857203.81 | 928693.34 | -71489.53 | -7.698% | 1.535% | 857203.81 | 928693.34 | -71489.53 | 2014-10-01 | 2015-09-30 | 2015-02-09 | 2 | 2015-11-30 | 11
| 050.39776 | 050.2634.Grapevine Rd Ext | Install 500 ft of 2 inch PE for County Sports Complex. | 962.22 | 3119.38 | -2157.16 | -69.15% | 0.001723% | 962.22 | 3119.38 | -2157.16 | 2014-10-01 | 2015-09-30 | 2015-02-09 | 2 | 2015-05-08 | 5
| 050.39784 | PRP.2734.High St. Cabell-14th | Replace approximately1951 ft of 6 Inch 4 Inch and 2 Inch LP and IP Stl. with approximately 1286 Ft of 6 Inch IP PE and 665 ft of 2 Inch IP PE. 52 services will be involved in this replacement. | 183675.89 | 273210.75 | -89534.86 | -32.77% | 0.3289% | 183675.89 | 273210.75 | -89534.86 | 2014-10-01 | 2015-09-30 | 2015-02-01 | 2 | 2015-10-30 | 10
| 050.39797 | 2637.Lourdes Hosp. Easement | Permanent above ground easement on Lourdes Hospital Property for Regulator Station. We had previously been leasing the 40'x40' lot in 20 year increments | 14124.06 | 13329.08 | 794.98 | 5.964% | 0.02529% | 14124.06 | 13329.08 | 794.98 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-02-28 | 2
| 050.39801 | 2609.Storage.Equipment.FY15 | Purchase equipment for Storage including: 1 ignitition engine, 4 Package consisting of personal gas monitors and calibration station for well workover and maintenance. | 28210.5 | 21302.4 | 6908.1 | 32.43% | 0.05051% | 28210.5 | 21302.4 | 6908.1 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-07-31 | 7
| 050.39809 | 2735.RETIRE TRUCK.TRAILER | RETIRE FOR SALVAGE TRUCK AND TRAILER UNIT 6553 AND UNIT 6816 | -8793.59 | 0 |  |  | -0.01574% | -8793.59 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-10-22 | 10
| 050.39824 | 2738.REYNOLDS RD 2015 | INSTALL 360' OF 2" PE FOR NEW CUSTOMERS ON REYNOLDS ROAD OFF SMITH RIDGE ROAD | 1342.32 | 2095.82 | -753.5 | -35.95% | 0.002403% | 1342.32 | 2095.82 | -753.5 | 2014-10-01 | 2015-09-30 | 2015-02-15 | 2 | 2015-04-15 | 4
| 050.39827 | JimSmithContractingEasement.15 | Purchase 20 ft. wide easement for approximately 3,000 feet from Jim Smith Contracting LLC. | 14153.84 | 12044.41 | 2109.43 | 17.51% | 0.02534% | 14153.84 | 12044.41 | 2109.43 | 2014-10-01 | 2015-09-30 | 2015-04-01 | 4 | 2015-04-30 | 4
| 050.39858 | 050.2734.BrennerSt.StationRep | Replace Reg. Station - Third Party Damage - Brenner St. Bowling Green | 12542.24 | 39193.59 | -26651.35 | -68% | 0.02246% | 12542.24 | 39193.59 | -26651.35 | 2014-10-01 | 2015-09-30 | 2015-02-13 | 2 | 2015-09-28 | 9
| 050.39898 | 050.2634.Mahr Park Main Ext | Install 850 feet of 2 inch PE for the city park in Madisonville named Mahr Park | 4062.4 | 3560.19 | 502.21 | 14.11% | 0.007273% | 4062.4 | 3560.19 | 502.21 | 2014-10-01 | 2015-09-30 | 2015-04-01 | 4 | 2015-04-30 | 4
| 050.39906 | 050.2634.Hwy 351 Relocation | Relocate app. 700' feet of 2 inch steel main along Ky Hwy 351 in Henderson County | -7560.23 | 9549.9 | -17110.13 | -179.2% | -0.01354% | -7560.23 | 9549.9 | -17110.13 | 2014-10-01 | 2015-09-30 | 2015-02-23 | 2 | 2015-05-08 | 5
| 050.39907 | PRP.2635.Maple St. | Replace approximately 5618 ft 2 Inch Bare Main with 2 Inch PE IP . 67 services involved | 221366.11 | 357374.02 | -136007.91 | -38.06% | 0.3963% | 221366.11 | 357374.02 | -136007.91 | 2014-10-01 | 2015-09-30 | 2015-03-20 | 3 | 2015-11-30 | 11
| 050.39911 | 2015 WMR | We are requesting $18,300 (budgeted amount) worth of AMR equipment and $1,875 (budgeted amount) worth of direct capital labor to continue our wireless meter reading program in Paducah for 2015 FY. | 28218.07 | 32239.71 | -4021.64 | -12.47% | 0.05052% | 28218.07 | 32239.71 | -4021.64 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-10-22 | 10
| 050.39912 | 2738.COX ST RETIREMENT 2015 | RETIREMENT OF THE COX ST MAIN IN CAMPBELLSVILLE | 456.51 | 1328.22 | -871.71 | -65.63% | 0.0008173% | 456.51 | 1328.22 | -871.71 | 2014-10-01 | 2015-09-30 | 2015-03-02 | 3 | 2015-04-02 | 4
| 050.39913 | 050.2636.Palomino Pl. Ext. | 460 ft.-2 inch PE - Palomino Pl. Owensboro | 6306.91 | 7366.41 | -1059.5 | -14.38% | 0.01129% | 6306.91 | 7366.41 | -1059.5 | 2014-10-01 | 2015-09-30 | 2015-02-09 | 2 | 2015-06-30 | 6
| 050.39930 | 050.2734.McCoy Place II-A | 2 and 4 inch PE Extension McCoy Pl II-A - B.G. | 28704.87 | 31427.89 | -2723.02 | -8.664% | 0.05139% | 28704.87 | 31427.89 | -2723.02 | 2014-10-01 | 2015-09-30 | 2015-02-05 | 2 | 2015-09-28 | 9
| 050.39931 | Mayfield Purch Upgrade | Mayfield Purchase station upgrade includes replacing 2 - 4 inch Axial flo regulators with 2 new 4 inch Mooney regulators. | 16318.77 | 16806.82 | -488.05 | -2.904% | 0.02922% | 16318.77 | 16806.82 | -488.05 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-05-08 | 5
| 050.39954 | Reg Replace - Barham Rd | Barham Road Regulator Station - We propose to retire one 2 inch Fisher 399 regulator and replace it with one 2 inch Mooney regulator. We will purchase from Tri-State Meter out of Memphis, TN | 3374.34 | 5088.57 | -1714.23 | -33.69% | 0.006041% | 3374.34 | 5088.57 | -1714.23 | 2014-10-01 | 2015-09-30 | 2014-09-24 | 9 | 2015-05-08 | 5
| 050.39996 | 2739.DIAGEO PHASE 1 2015 | INSTALL 10,500' OF 6" PE FOR PHASE 1 OF DIAGEO | -70464.23 | -720129.99 | 649665.76 | -90.22% | -0.1262% | -70464.23 | -720129.99 | 649665.76 | 2014-10-01 | 2015-09-30 | 2015-03-01 | 3 | 2015-09-30 | 9
| 050.40009 | 050.2636.EByersRegSta | East Byers Reg. Stat and Tie-In - Heartland Reg Sta. | 44802.12 | 30507.85 | 14294.27 | 46.85% | 0.08021% | 44802.12 | 30507.85 | 14294.27 | 2014-10-01 | 2015-09-30 | 2015-03-02 | 3 | 2015-07-30 | 7
| 050.40010 | 050.2636.UnionStRelocHartford | Relocate 1000 ft. of 2 inch Stl with 2 inch PE - Union St. - Hartford | 14196.81 | 28075.76 | -13878.95 | -49.43% | 0.02542% | 14196.81 | 28075.76 | -13878.95 | 2014-10-01 | 2015-09-30 | 2015-03-02 | 3 | 2015-06-30 | 6
| 050.40014 | 2653.Oboro.GEO.7X.GPS.FY15 | Purchase one GEO.7X with Rangefinder GPS for the Owensboro, KY PRP crew. | 11889.65 | 10855.41 | 1034.24 | 9.527% | 0.02129% | 11889.65 | 10855.41 | 1034.24 | 2014-10-01 | 2015-09-30 | 2015-03-16 | 3 | 2015-03-31 | 3
| 050.40015 | 2653.GEO.7X.GPS.Bowling.Green | Purchase 1 GEO 7X with Rangefinder GPS for Bowling Green PRP crew. | 12770.75 | 10855.41 | 1915.34 | 17.64% | 0.02286% | 12770.75 | 10855.41 | 1915.34 | 2014-10-01 | 2015-09-30 | 2015-03-16 | 3 | 2015-03-31 | 3
| 050.40023 | PRP.2734.Hwy 31W | Replace 590 ft of 4 Inch Bare Steel IP with 4 Inch PE IP due to leakage on Bare Steel. Approximately 8 services involved. | 50810.91 | 34516.3 | 16294.61 | 47.21% | 0.09097% | 50810.91 | 34516.3 | 16294.61 | 2014-10-01 | 2015-09-30 | 2015-03-09 | 3 | 2015-06-30 | 6
| 050.40035 | 050.2734.Technology6inchPE | 1300 ft. of 6 inch PE - Technology Way - BowlingGreen | -7711 | -0.02 | -7710.98 | 38554900% | -0.01381% | -7711 | -0.02 | -7710.98 | 2014-10-01 | 2015-09-30 | 2015-02-06 | 2 | 2015-09-28 | 9
| 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | INSTALL 2" PE IN CLOVERBROOKJ SEC 8 PHASE 1 ON ST REGIS DR FROM TEALWOOD PAST RUTHERFORD | 2365.26 | 13697.21 | -11331.95 | -82.73% | 0.004235% | 2365.26 | 13697.21 | -11331.95 | 2014-10-01 | 2015-09-30 | 2015-02-01 | 2 | 2015-06-01 | 6
| 050.40044 | 2738.GRE.WILLIAM DIAL RD 15 | INSTALL 2800' OF 4" PE 3408 AND 1300ft OF 2" PE 3408 TO SERVICE NEW CHICKEN HOUSES ON WILLIAM DIAL RD FROM NEW 6" PE | 21104.43 | 14363.9 | 6740.53 | 46.93% | 0.03779% | 21104.43 | 14363.9 | 6740.53 | 2014-10-01 | 2015-09-30 | 2015-04-01 | 4 | 2015-07-01 | 7
| 050.40092 | 050.2636.ERX, regs, guages | Purchase 6 ERX's, 6 guages and 2 4" Moonies for Greenville/Central City area | 25270.74 | 31239.42 | -5968.68 | -19.11% | 0.04524% | 25270.74 | 31239.42 | -5968.68 | 2014-10-01 | 2015-09-30 | 2015-04-01 | 4 | 2015-09-30 | 9
| 050.40112 | 050.2636.Fiddlesticks Phase 3 | 595 ft. of 2 inch PE will serve 12 new lots in Fiddlesticks Sub. Phase 3 - Owensboro | 5334.78 | 7508.77 | -2173.99 | -28.95% | 0.009551% | 5334.78 | 7508.77 | -2173.99 | 2014-10-01 | 2015-09-30 | 2015-04-02 | 4 | 2015-06-30 | 6
| 050.40132 | 050.2637.USEC.MeterSet.FY15 | Retire 2,749' - 6" steel, 2,763' - 3" steel. Move gas meter outside of the fenced off nuclear facility | 12663.71 | 0 |  |  | 0.02267% | 12663.71 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-08-31 | 8
| 050.40153 | 050.2736.Commerce Ct Ext | Install 780 feet of 4 inch poly for one new commercial customer (Mid-South Equipment) requesting nartural gas | 6617.82 | 6183.38 | 434.44 | 7.026% | 0.01185% | 6617.82 | 6183.38 | 434.44 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-08-30 | 8
| 050.40171 | BowlingGreen.Office.Carpet.15 | Replace carpet at Bowling Green office. | 30815.92 | 26628 | 4187.92 | 15.73% | 0.05517% | 30815.92 | 26628 | 4187.92 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-07-31 | 7
| 050.40172 | Bowling Green Office Furniture | Purchase desk/cubicles for new employees - 3 Construction Employees and 2 Field Construction Coordinators. | 26634.81 | 46599 | -19964.19 | -42.84% | 0.04769% | 26634.81 | 46599 | -19964.19 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-09-28 | 9
| 050.40218 | PRP.2735.East Back MUN. | Replace approximately 2142 ft of 2 Inch IP Bare steel with 2 Inch IP PE. approximately 30 services involved. | 115029.55 | 208562.05 | -93532.5 | -44.85% | 0.2059% | 115029.55 | 208562.05 | -93532.5 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-09-30 | 9
| 050.40232 | PRP.2735.Washington St.MUN | Replace approximately 3217 ft of 2 Inch Bare IP steel with 2 Inch IP PE. Approximately 26 services involed. | 285180.77 | 347110.72 | -61929.95 | -17.84% | 0.5106% | 285180.77 | 347110.72 | -61929.95 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-09-30 | 9
| 050.40255 | 050.2736.W 18th St Retire | Abandon 2 inch and 4 inch pipe on W 18th Street | 1662.43 | 430.95 | 1231.48 | 285.8% | 0.002976% | 1662.43 | 430.95 | 1231.48 | 2014-10-01 | 2015-09-30 | 2015-04-22 | 4 | 2015-05-30 | 5
| 050.40270 | 050.2734.Champion Pet Foods | 5900 ft. of 6 inch PE to serve new Champion Pet Foods in South Union | 67.06 | 504.36 | -437.3 | -86.7% | 0.0001201% | 67.06 | 504.36 | -437.3 | 2014-10-01 | 2015-09-30 | 2015-04-20 | 4 | 2015-11-30 | 11
| 050.40271 | 050.2637.Ohio Ct Main Ext | Install 140 ft of 2 inch pe for one existing customer wanting to convert from LP | 954.97 | 1283.43 | -328.46 | -25.59% | 0.00171% | 954.97 | 1283.43 | -328.46 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-09-28 | 9
| 050.40277 | 050.2637.Ky Ave Replacements | State of Kentucky is making road improvements to Kentucky Ave in Paducah. They are improving the road from 10th Street (Jetton blvd) to N 24th. We have 5 sections of gas mains affected. All 5 are road crossings | 57842.55 | 56401.89 | 1440.66 | 2.554% | 0.1036% | 57842.55 | 56401.89 | 1440.66 | 2014-10-01 | 2015-09-30 | 2015-03-01 | 3 | 2015-09-28 | 9
| 050.40278 | Calvert Purchase Upgrade | This project consists of replacing the relief valve at what we call Calvert City Purchase Station, located on Ky Hwy 282, just east of Calvert City | 9881.35 | 23946.76 | -14065.41 | -58.74% | 0.01769% | 9881.35 | 23946.76 | -14065.41 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-10-22 | 10
| 050.40284 | 050.2635.Charleston TB Reloc | Move Charleston Town border some 150 feet north to get it out of customers front yard | 17499.7 | 11889.51 | 5610.19 | 47.19% | 0.03133% | 17499.7 | 11889.51 | 5610.19 | 2014-10-01 | 2015-09-30 | 2015-04-06 | 4 | 2015-09-28 | 9
| 050.40290 | 050.2637.Fantasy Ln Ext | Install 160 feet of 2 inch pe for one customer (Mo Morad) requesting natural gas | -123.2 | 1293.7 | -1416.9 | -109.5% | -0.0002206% | -123.2 | 1293.7 | -1416.9 | 2014-10-01 | 2015-09-30 | 2015-04-01 | 4 | 2015-11-30 | 11
| 050.40291 | 050.2637.Pecan Dr Rev Ext | Install 600 feet of 2 inch pe for two existing customers requesting gas service | 16907.02 | 2507.97 | 14399.05 | 574.1% | 0.03027% | 16907.02 | 2507.97 | 14399.05 | 2014-10-01 | 2015-09-30 | 2015-04-06 | 4 | 2015-09-28 | 9
| 050.40292 | 050.2637.Bruce Ave Rev Ext | Install 330 feet of 2 inch poly main for six existing customers wanting to convert from all-electric to natural gas heat. | 449.32 | 2598.6 | -2149.28 | -82.71% | 0.0008045% | 449.32 | 2598.6 | -2149.28 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-30 | 7
| 050.40296 | Retire Welder #9471 | We propose to retire welder #9471, a 2001 Miller Trailblazer 300D. The V.I.N is LB116288. Can be picked p at 3510 Coleman Rd Paducah, KY. Salvage value has been placed at -$500.00 | -1762 | 0 |  |  | -0.003155% | -1762 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-05-31 | 5
| 050.40375 | 2602.Oboro.Server.Replc.15 | Server/Switch replacement for Owensboro OWN00N04 | 14389.76 | 27092.25 | -12702.49 | -46.89% | 0.02576% | 14389.76 | 27092.25 | -12702.49 | 2014-10-01 | 2015-09-30 | 2015-05-12 | 5 | 2015-11-28 | 11
| 050.40377 | 2602.KY.Laptop.Purch.FY15.2 | Purchase 1 Dell Latitude 12 E7250 laptop and 4 Dell 24 Dual Monitors E2414H with MDS 14. | 4170.5 | 4061.92 | 108.58 | 2.673% | 0.007467% | 4170.5 | 4061.92 | 108.58 | 2014-10-01 | 2015-09-30 | 2015-05-12 | 5 | 2015-07-15 | 7
| 050.40386 | Replace Fences | We have budgeted the replacement of fences at five town border stations including T.B 3 ( Cairo Rd ), T.B 4 ( WKCTC Campus ), Calvert City T.B, and Schaeffer Rd station. | 21787.2 | 18000 | 3787.2 | 21.04% | 0.03901% | 21787.2 | 18000 | 3787.2 | 2014-10-01 | 2015-09-30 | 2015-06-01 | 6 | 2015-07-31 | 7
| 050.40425 | PRP.2636.River Rd. | Install approximately 5499 ft of 2 Inch IP PE to replace 2 Inch and 6 Inch Bare LP Steel. approximately 66 Services involved. | 192369 | 441675.05 | -249306.05 | -56.45% | 0.3444% | 192369 | 441675.05 | -249306.05 | 2014-10-01 | 2015-09-30 | 2015-05-15 | 5 | 2015-10-30 | 10
| 050.40434 | 050.2636.Newbolt Rd. Ext | 350 ft. of inch PE | 4949.03 | 4827.24 | 121.79 | 2.523% | 0.008861% | 4949.03 | 4827.24 | 121.79 | 2014-10-01 | 2015-09-30 | 2015-02-02 | 2 | 2015-07-30 | 7
| 050.40453 | 050.2637.Krebs Sta Rd Ext 3 | Install 300 feet of 2 inch pe gas main for three exisitng residential customers requesting natural gas. All three converting from propane. | 1723.35 | 1820.17 | -96.82 | -5.319% | 0.003085% | 1723.35 | 1820.17 | -96.82 | 2014-10-01 | 2015-09-30 | 2015-06-01 | 6 | 2015-09-28 | 9
| 050.40471 | PRP.2734.Crewdson Ln. | See Canned Stories | 456731.07 | 1065458.52 | -608727.45 | -57.13% | 0.8177% | 456731.07 | 1065458.52 | -608727.45 | 2014-10-01 | 2015-09-30 | 2015-05-30 | 5 | 2015-11-30 | 11
| 050.40481 | 2734.PRP.Coil.Pipe.Trailer.15 | Purchase Lazy Susan Coil Pipe Trailer (Model CT1143TT) with hydraulic tilt and turntable brake for internal Bowling Green PRP crew. Serial #1RCFECJ13F1001494 | 9808.41 | 9962.87 | -154.46 | -1.55% | 0.01756% | 9808.41 | 9962.87 | -154.46 | 2014-10-01 | 2015-09-30 | 2015-06-01 | 6 | 2015-07-30 | 7
| 050.40483 | 2734.PRP.Line.Locator.FY15 | Purchase All-PRO S-Lock locator from Heath Consultants for internal Bowling Green PRP crew. Serial # 6001523002 | 4824.23 | 4547.4 | 276.83 | 6.088% | 0.008637% | 4824.23 | 4547.4 | 276.83 | 2014-10-01 | 2015-09-30 | 2015-06-01 | 6 | 2015-07-30 | 7
| 050.40488 | 050.2637.Creek Replacements | We have 4 inch pe exposed in creeks at two locations in the Lone Oak area. We propose to have Revell Construction of Union City, TN replace both of these creek exposures. | 23888.97 | 25540.33 | -1651.36 | -6.466% | 0.04277% | 23888.97 | 25540.33 | -1651.36 | 2014-10-01 | 2015-09-30 | 2015-06-15 | 6 | 2015-07-30 | 7
| 050.40489 | 050.2736.Katie Peden Dr Ext | Install 100 ft of 2 inch steel, set a 3/4 inch MTDeason reg station, 100 ft od 2 inch poly, then 830 ft of 2 inch poly for one commercial customer (Garnett By-Pass Warehouse) requesting gas | 11228.29 | 12468.95 | -1240.66 | -9.95% | 0.0201% | 11228.29 | 12468.95 | -1240.66 | 2014-10-01 | 2015-09-30 | 2015-06-01 | 6 | 2015-07-30 | 7
| 050.40491 | 050.2739.WalkerLnStaRebuild | Replace Walker Ln Regulator Station - Lawrencburg | 104382.21 | 186193.05 | -81810.84 | -43.94% | 0.1869% | 104382.21 | 186193.05 | -81810.84 | 2014-10-01 | 2015-09-30 | 2015-06-01 | 6 | 2015-09-28 | 9
| 050.40506 | PRP.2635. H ville St Replace | Abbandon 115 feet of 2 inch bare pipe. Install 118 feet of 2 inch poly pipe due to leakage | 4371.31 | 3483.23 | 888.08 | 25.5% | 0.007826% | 4371.31 | 3483.23 | 888.08 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-07-31 | 7
| 050.40532 | 050.2637.Ham Rd Rev Ext | Install 1,200 feet of 2 inch poly main for one new residential customer (Kevin Stahr) requesting gas service. | -4071.92 | 7785.07 | -11856.99 | -152.3% | -0.00729% | -4071.92 | 7785.07 | -11856.99 | 2014-10-01 | 2015-09-30 | 2015-06-15 | 6 | 2015-10-30 | 10
| 050.40534 | PRP.2637.Madison | Replace approximately 4584 ft of 4 and 6 Inch Bare IP Steel with 4 and 6 Inch IP PE. Approximately103 services involved | 424750.22 | 493772.76 | -69022.54 | -13.98% | 0.7605% | 424750.22 | 493772.76 | -69022.54 | 2014-10-01 | 2015-09-30 | 2015-06-10 | 6 | 2015-12-22 | 12
| 050.40556 | 050.2638.Dale Dr Rev Ext | Install 400 feet of 2 inch pe pipe for two existing customers requesting natural gas | 4039.96 | 2477.78 | 1562.18 | 63.05% | 0.007233% | 4039.96 | 2477.78 | 1562.18 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40557 | 050.2634.Versnick Dr Rev Ext | Install 300 feet of 2 inch pe main for one existing commercial customer requesting service. | 3419.06 | 2744.34 | 674.72 | 24.59% | 0.006121% | 3419.06 | 2744.34 | 674.72 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40566 | 2609.HickoryStorageBuilding.15 | Construction of new building at Hickory Storage in Philpot, KY. Builder is Hayden Construction Company. Estimate cost is $153,469.00 | 164076.16 | 153468 | 10608.16 | 6.912% | 0.2938% | 164076.16 | 153468 | 10608.16 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-11-30 | 11
| 050.40577 | 050.2638.S 17th St Ext | Install 80 feet of 2 inch poly pipe for one residential customer (Larry Jackson) requesting natural gas service at 201 South 17th Street in Mayfield. | 2992.48 | 1274.88 | 1717.6 | 134.7% | 0.005358% | 2992.48 | 1274.88 | 1717.6 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40578 | New roof on TB 1 | We have budgeted monies to put a new roof on Mayfield Town Border #1 | 12146.37 | 10000 | 2146.37 | 21.46% | 0.02175% | 12146.37 | 10000 | 2146.37 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-10-22 | 10
| 050.40587 | PRP.2636.Dublin LN | Replace 6056 ft of bare LP Stl with 5591 ft 2 Inch and 465 ft of 6 Inch IP PE . 106 services involved. | 195493.66 | 497699.56 | -302205.9 | -60.72% | 0.35% | 195493.66 | 497699.56 | -302205.9 | 2014-10-01 | 2015-09-30 | 2015-06-25 | 6 | 2015-11-30 | 11
| 050.40589 | 050.2739.MooneyRegsShelbyville | Mooney Regulators for : RS1514 Zaring Mill RS1550 Pearce Industrial RS1555 Mt. Eden Rd RS1548 Brunnerstown Rd R | 23378.49 | 20452.37 | 2926.12 | 14.31% | 0.04186% | 23378.49 | 20452.37 | 2926.12 | 2014-10-01 | 2015-09-30 | 2015-06-17 | 6 | 2015-10-31 | 10
| 050.40590 | 050.2739.Grade3LeakRepaieSlbyv | Approved FY2015 Grade Three Leak Repairs - Shelbyville Area | 18218.4 | 20334.38 | -2115.98 | -10.41% | 0.03262% | 18218.4 | 20334.38 | -2115.98 | 2014-10-01 | 2015-09-30 | 2015-06-17 | 6 | 2015-09-28 | 9
| 050.40596 | 050.2739.McCormack Ext. | 1420 ft. of 2 inch PE Extension to serve three new customers - McCormack -Waddy | -11844.69 | 3174 | -15018.69 | -473.2% | -0.02121% | -11844.69 | 3174 | -15018.69 | 2014-10-01 | 2015-09-30 | 2015-05-08 | 5 | 2015-11-30 | 11
| 050.40609 | 2636.Retire backhoe trailer | o retire tandem axle dual wheel backhoe trailer | -3525 | -4000 | 475 | -11.88% | -0.006311% | -3525 | -4000 | 475 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40615 | 050.2637.CANDLELIGHT EXT 2 | Install app. 2400 feet of 2 inch FOR DEPOSIT PURPOSES ONLY | -893.54 | 25111.82 | -26005.36 | -103.6% | -0.0016% | -893.54 | 25111.82 | -26005.36 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-09-28 | 9
| 050.40632 | Coleman.Rd.Security.System | Install camera security system at 3510 Coleman Rd office location. 12 cameras IP plus High Definition 2 Terrabyte Storage NVR. | 6739.5 | 7203.6 | -464.1 | -6.443% | 0.01207% | 6739.5 | 7203.6 | -464.1 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40639 | PRP.2734.Clay-Stubbins | Replace 1823 Ft 2 Inch Bare IP Stl. and 1160 ft 2 Inch Bare LP Stl with 2440ft 2Inch IP PE. Also retire 1 LP Reg Sta. 44 Services involved. | 119386.6 | 345210.5 | -225823.9 | -65.42% | 0.2137% | 119386.6 | 345210.5 | -225823.9 | 2014-10-01 | 2015-09-30 | 2015-06-30 | 6 | 2015-09-28 | 9
| 050.40662 | PRP.2734.BG-Oaklawn-Loving | PRP.2734.BG-Oaklawn-Loving | 296270.53 | 296707.86 | -437.33 | -0.1474% | 0.5304% | 296270.53 | 296707.86 | -437.33 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40672 | PRP.2734.Henry-McElroy | Replace approximately 700ft of 2 Inch Bare IP Stl with 2 Inch PE IP. 14 Services involved. | 57317.96 | 83674.41 | -26356.45 | -31.5% | 0.1026% | 57317.96 | 83674.41 | -26356.45 | 2014-10-01 | 2015-09-30 | 2015-06-25 | 6 | 2015-09-30 | 9
| 050.40678 | 050.2637.Mallard Cr Ext II | Install app. 900 feet of 2 inch poly for 3 fourplexes and 2 threeplexes for a total of 18 new residential meter sets. This is in the Ky Oaks Mall area of Paducah | 5278.84 | 4065.05 | 1213.79 | 29.86% | 0.009451% | 5278.84 | 4065.05 | 1213.79 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-07-31 | 7
| 050.40679 | 050.2637.Schneidman Relocate | Move existing Sccneidman Rd T.B station west app. 100 feet. Currently station is on city right-of-way and very close to road. Property owner is not happy with location. We propose to move from east side of road to west side of road. | 24737.29 | 94340.72 | -69603.43 | -73.78% | 0.04429% | 24737.29 | 94340.72 | -69603.43 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-08-30 | 8
| 050.40685 | 050.2636 DameWay Dr.Ext | 350 ft. of 2 iNCH pe Dame Way Rd. - Powderly | 758.39 | 1101.85 | -343.46 | -31.17% | 0.001358% | 758.39 | 1101.85 | -343.46 | 2014-10-01 | 2015-09-30 | 2015-03-10 | 3 | 2015-09-28 | 9
| 050.40687 | PRP.2636.Kennedy Dr. | Replace 1326 ft of 4 Inch Bare IP Steel with 1589 Ft of 2 Inch IP PE 7 services involved. | 25441.37 | 20054.03 | 5387.34 | 26.86% | 0.04555% | 25441.37 | 20054.03 | 5387.34 | 2014-10-01 | 2015-09-30 | 2015-06-29 | 6 | 2015-08-28 | 8
| 050.40693 | 050.2735.TB1Reloc.HorseCave | Replace Horse Cave TB 2 | -117910.97 | 0 |  |  | -0.2111% | -117910.97 | Non Budgeted |  | 2014-10-01 | 2015-09-30 | 2015-06-15 | 6 | 2015-11-30 | 11
| 050.40699 | 050.2634.St Charles TB Repl | Retire existing regulator station, install new station east and south adjacent to Main Street | 20418.45 | 23657.48 | -3239.03 | -13.69% | 0.03656% | 20418.45 | 23657.48 | -3239.03 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-10-30 | 10
| 050.40703 | 050.2634.Liberty Sta Rebuild | Replace Liberty Station due to bad valves, PSC suggested. | 92026.43 | 114318.3 | -22291.87 | -19.5% | 0.1648% | 92026.43 | 114318.3 | -22291.87 | 2014-10-01 | 2015-09-30 | 2015-08-01 | 8 | 2015-08-31 | 8
| 050.40709 | 050.2637.Lourdes HCA Removal | Install app. 700 feet of 8 inch H.P.D. Abandon/Retire app. 700 feet of 8 inch Transmission Main. We do this to get rid of "High Consequence Area" label. | 422778.45 | 402594.45 | 20184 | 5.013% | 0.7569% | 422778.45 | 402594.45 | 20184 | 2014-10-01 | 2015-09-30 | 2015-07-25 | 7 | 2015-08-31 | 8
| 050.40723 | 050.2638.Sedalia Rd Sys Imp | Tap on to 2" HPD (175# MAOP) run 180 ft 2 in steel, 2 inch regulator station, then app. 2,300 feet of 4 in poly. Tie-ing two systems together. The 36 PSI MAOP to the north needs to be bolstered, there is a lg subdivision at the end of north system. | 135240.83 | 52567.13 | 82673.7 | 157.3% | 0.2421% | 135240.83 | 52567.13 | 82673.7 | 2014-10-01 | 2015-09-30 | 2015-07-15 | 7 | 2015-09-30 | 9
| 050.40733 | 050.2636.Avondale Reg. Repl. | Replace Pole Mount Regulator Station - Avondale at Castlewood - Owensboro | 29679.4 | 30420.87 | -741.47 | -2.437% | 0.05314% | 29679.4 | 30420.87 | -741.47 | 2014-10-01 | 2015-09-30 | 2015-06-18 | 6 | 2015-11-30 | 11
| 050.40736 | PRP.2735.Buckner-Main St.MUN | Replace approximately 3600 ft of Bare 2 inch IP Stl. with 3650 ft 2 inch IP PE. 50 Services involved. | 148084.1 | 345285.8 | -197201.7 | -57.11% | 0.2651% | 148084.1 | 345285.8 | -197201.7 | 2014-10-01 | 2015-09-30 | 2015-07-15 | 7 | 2015-10-28 | 10
| 050.40737 | PRP.2637.Madison-Harrison | Replace approximately 6200 ft of Bare IP Stl Main with 4400 ft 4 Inch IP PE and 2199 ft of 2 Inch Ip PE. 159 Services involved. | 244936.82 | 519852.6 | -274915.78 | -52.88% | 0.4385% | 244936.82 | 519852.6 | -274915.78 | 2014-10-01 | 2015-09-30 | 2015-08-01 | 8 | 2015-10-28 | 10
| 050.40757 | 050.2736.Davenport Ln Ext | Install 2,920 feet of 4 inch PE as well as 280 feet of 2 inch PE for 6 customers requesting natural gas. A partial deposit is required. | 9832.89 | 5610.97 | 4221.92 | 75.24% | 0.0176% | 9832.89 | 5610.97 | 4221.92 | 2014-10-01 | 2015-09-30 | 2015-07-15 | 7 | 2015-08-30 | 8
| 050.40767 | Lourdes HCA - Retirement | This is a seperate project to retire TRANSMISSION main. There is a seperate project 050.40709 to install H.P.D, needs to be two seperate projects, one for H.P.D, one for Transmission. We propose to retire app. 700 ft of 8" pipe | 1573.9 | 2031.51 | -457.61 | -22.53% | 0.002818% | 1573.9 | 2031.51 | -457.61 | 2014-10-01 | 2015-09-30 | 2014-09-22 | 9 | 2015-10-22 | 10
| 050.40779 | PRP.2734.Centerline Phase 2 | Replace approximately 1 mile of 8 Inch bare steel from PS1 towards Rhoades Ln with 9300 of 8 Inch Stl HPD and 1300 of 6 Inch PE IP. Replace 6 services. | 764422.7 | 4308210.9 | -3543788.2 | -82.26% | 1.369% | 764422.7 | 4308210.9 | -3543788.2 | 2014-10-01 | 2015-09-30 | 2015-07-20 | 7 | 2016-02-29 | 2
| 050.40793 | 2737.HAR.NORTH REG STATION | INSTALL 4 inch STEEL, REGUALTOR STATION AND 4inch PE TO TIE THE HP LINE TO THE IP LINE ON THE NORTH SIDE OF HARRODSBURG AT WAUSAU AND BOHON ROAD | 206587.23 | 386221.96 | -179634.73 | -46.51% | 0.3699% | 206587.23 | 386221.96 | -179634.73 | 2014-10-01 | 2015-09-30 | 2015-05-29 | 5 | 2016-01-01 | 1
| 050.40801 | Coleman.Rd.Office Projector | Install (1) 16:10 Projector, Mount, and Ceiling Plant at new Paducah, KY office located at 3510 Coleman Road. Vivitek Model D968U-WT Projector; Serial#: WD968U-WT5020021 | 7279.81 | 7439.95 | -160.14 | -2.152% | 0.01303% | 7279.81 | 7439.95 | -160.14 | 2014-10-01 | 2015-09-30 | 2015-07-16 | 7 | 2015-08-31 | 8
| 050.40807 | 2739.LOCUST CRK 10b 2015 | INSATALL 2" PE FOR 13 LOTS IN LOCUST CREEK SECTION 10b | 4400.05 | 7510.03 | -3109.98 | -41.41% | 0.007878% | 4400.05 | 7510.03 | -3109.98 | 2014-10-01 | 2015-09-30 | 2015-05-01 | 5 | 2015-11-30 | 11
| 050.40810 | Rebuild Madville Purch Sta | We propose to rebuild the Madisonville Purchase Station due to outdated regulators and leaking valves. This is approved in the FY 2015 Capital Budget. | 51432.06 | 112366.22 | -60934.16 | -54.23% | 0.09208% | 51432.06 | 112366.22 | -60934.16 | 2014-10-01 | 2015-09-30 | 2015-08-01 | 8 | 2015-09-28 | 9
| 050.40849 | 050.2739.Ninevah Road | 675' of 2" PE | -3128.7 | 447.14 | -3575.84 | -799.7% | -0.005602% | -3128.7 | 447.14 | -3575.84 | 2014-10-01 | 2015-09-30 | 2015-07-16 | 7 | 2015-08-31 | 8
| 050.40855 | 2602.Desktop.Laptop Purch.15 | Purchase 20 Dell OptiPlex 7020 SFF desktop computers, 2 Dell Latitude E5450 Laptops, and 2 Dell Latitude E7250. This purhcase will allow Kentucky operations to rid ourselves of XP machines putting us in compliance with the Enerprise. | 26703.48 | 24997.6 | 1705.88 | 6.824% | 0.04781% | 26703.48 | 24997.6 | 1705.88 | 2014-10-01 | 2015-09-30 | 2015-07-23 | 7 | 2015-08-31 | 8
| 050.40866 | PRP.2736.Robin Rd. | Replace 800 ft of 2 and 4 Inch LP Bare Stl with 2 Inch Ip PE. also remove LP Reg. Station, 16 services. Co Crew to do work | 26027.25 | 32894.21 | -6866.96 | -20.88% | 0.0466% | 26027.25 | 32894.21 | -6866.96 | 2014-10-01 | 2015-09-30 | 2015-07-29 | 7 | 2015-09-29 | 9
| 050.40894 | PRP.2734.E. 13th Ave Rt | Retire 310 ft of 2 Inch Bare Stl. Main | 520.24 | 2708.16 | -2187.92 | -80.79% | 0.0009314% | 520.24 | 2708.16 | -2187.92 | 2014-10-01 | 2015-09-30 | 2015-07-24 | 7 | 2015-09-30 | 9
| 050.40909 | 050.2636.DeerValley3 | 3440 ft of 4 inch and 300 ft. of 2 inch PE - Deer Valley 3-Owensboro | 44792.53 | 54933.77 | -10141.24 | -18.46% | 0.0802% | 44792.53 | 54933.77 | -10141.24 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-09-28 | 9
| 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 100 ft. of 2 inch HPD, Regulator Station and 6inch PE to serve Deweese Asphalt Plant - Brown Rd. Franklin | -77674.01 | 21.77 | -77695.78 | -356894% | -0.1391% | -77674.01 | 21.77 | -77695.78 | 2014-10-01 | 2015-09-30 | 2015-08-03 | 8 | 2015-11-30 | 11
| 050.40936 | 050.2637.Maxon Rd Relocation | McCracken County making improvements to Maxon Road, we propose to relocate app. 5,000 feet of 4 inch poly pipe along with a small amount of 2 inch poly and app. 32 residential customers | 205926.37 | 362329.41 | -156403.04 | -43.17% | 0.3687% | 205926.37 | 362329.41 | -156403.04 | 2014-10-01 | 2015-09-30 | 2015-08-24 | 8 | 2015-10-30 | 10
| 050.40959 | PRP.2636.Ewing Rd. | Replace 3,4 and 6 Inch Bare LP Stl with approximately 6000 Ft of 2 Inch IP PE , also remove 1 low pressure Reg Station . Approximately 67 Services. | 133342.37 | 449169.48 | -315827.11 | -70.31% | 0.2387% | 133342.37 | 449169.48 | -315827.11 | 2014-10-01 | 2015-09-30 | 2015-07-20 | 7 | 2015-12-15 | 12
| 050.40963 | PRP.2736.Liberty St RT | Retire approximately 239 ft of bare 6 Inch LP Stl. and 6 Ft 4 Inch Bare Stl. | 8884.78 | 9887.91 | -1003.13 | -10.15% | 0.01591% | 8884.78 | 9887.91 | -1003.13 | 2014-10-01 | 2015-09-30 | 2015-07-20 | 7 | 2015-09-30 | 9
| 050.40982 | 050.2734.Hunts Ln. Ext | 1000 ft. of 4 inch PE Ext. - Hunts Ln. B.G. | 9334.29 | 7056.4 | 2277.89 | 32.28% | 0.01671% | 9334.29 | 7056.4 | 2277.89 | 2014-10-01 | 2015-09-30 | 2014-08-01 | 8 | 2015-09-28 | 9
| 050.40986 | PRP.2609.Dawson Springs | Replace approximately 1 mile of 4 Inch bare Stl. with 6 Inch Stl Project being created to capture cost of Material and R/W clearing. Revision will be routed after contract is awarded job to start Oct. 1st No Services | 486466 | 505547.54 | -19081.54 | -3.774% | 0.871% | 486466 | 505547.54 | -19081.54 | 2014-10-01 | 2015-09-30 | 2015-08-13 | 8 | 2016-07-28 | 7
| 050.41011 | 050.2637.Walton Rd Rev Ext | Install 625 feet of 2 inch poly for 6 new commercial lots located near intersection of Coleman Rd & Old Cairo Rd | -980.58 | 3168.84 | -4149.42 | -130.9% | -0.001756% | -980.58 | 3168.84 | -4149.42 | 2014-10-01 | 2015-09-30 | 2015-08-15 | 8 | 2015-09-28 | 9
| 050.41020 | 050.2609.MoslyvlVlvRepl | 050.2609 Mosleyville Habit Junction Valve Replacement. Fiscal Year 2015, Approved Capital Project | 10226.84 | 26049 | -15822.16 | -60.74% | 0.01831% | 10226.84 | 26049 | -15822.16 | 2014-10-01 | 2015-09-30 | 2015-08-20 | 8 | 2015-11-30 | 11
| 050.41029 | 2738.ELKHORN RD 2015 | INSTALL 5108' OF PE GAS LINE TO SERVE ELKHORN BAPTIST CHURCH | 7828.55 | 24498.75 | -16670.2 | -68.05% | 0.01402% | 7828.55 | 24498.75 | -16670.2 | 2014-10-01 | 2015-09-30 | 2015-01-01 | 1 | 2015-11-30 | 11
| 050.41037 | 050.2637.Central Rd Rev Ext | Install 200 ft. of 2 inch poly main for one new residential customer (Stacey Wright) requesting gas service at 158 Central Rd | -11.36 | 1309.6 | -1320.96 | -100.9% | -2.034e-05% | -11.36 | 1309.6 | -1320.96 | 2014-10-01 | 2015-09-30 | 2015-09-01 | 9 | 2015-09-28 | 9
| 050.41042 | 060.2636.BuffaloTrace Ext | 1450 ft. of 2 inch PE will serve Buffalo Trace located in Honeysuckle Estates - Owensboro | 5631.83 | 18158.76 | -12526.93 | -68.99% | 0.01008% | 5631.83 | 18158.76 | -12526.93 | 2014-10-01 | 2015-09-30 | 2015-08-05 | 8 | 2015-09-29 | 9
| 050.41043 | 050.2636.Wright Ave Est | 350 ft. of 2 inch PE - Wright Ave. - Owensboro | 6451.61 | 2650.94 | 3800.67 | 143.4% | 0.01155% | 6451.61 | 2650.94 | 3800.67 | 2014-10-01 | 2015-09-30 | 2015-02-16 | 2 | 2015-09-28 | 9
| 050.41052 | 050.2634.N McEuen Ave Retire | Abandon 272 feet - 2 inch PE and 42 feet - 2 inch steel for a total of 314 feet | 2.16 | 263.79 | -261.63 | -99.18% | 3.867e-06% | 2.16 | 263.79 | -261.63 | 2014-10-01 | 2015-09-30 | 2015-08-24 | 8 | 2015-09-05 | 9
| 050.41056 | 050.2637.Riley Cr Ext | Install 540 feet of 2 inch poly for one new residential customer (Joe Frank Riley) requesting gas service to 200 Riley Circle in Calvert City, KY | -1904.57 | 477.34 | -2381.91 | -499% | -0.00341% | -1904.57 | 477.34 | -2381.91 | 2014-10-01 | 2015-09-30 | 2015-08-18 | 8 | 2015-09-29 | 9
| 050.41082 | 050.2737.4thStReplacement | Retire 4th St. Reg. Station and Station Piping and install tie ins to existing IP main | 140237.54 | 180554 | -40316.46 | -22.33% | 0.2511% | 140237.54 | 180554 | -40316.46 | 2014-10-01 | 2015-09-30 | 2015-08-24 | 8 | 2015-11-15 | 11
| 050.41091 | 050.2738.PoplarSt.Retire | Retire 275 ft. of 2 inch steel - Poplar St.-Campbellsville | 762.21 | 1772.55 | -1010.34 | -57% | 0.001365% | 762.21 | 1772.55 | -1010.34 | 2014-10-01 | 2015-09-30 | 2015-06-25 | 6 | 2015-09-28 | 9
| 050.41093 | 2738.LEB.MERCER AVE 2015 | INSTALL 100' OF 2" PE TO SERVE NEW INDUSTRIAL BUILDING IN LEBANON | 848.98 | 2011.15 | -1162.17 | -57.79% | 0.00152% | 848.98 | 2011.15 | -1162.17 | 2014-10-01 | 2015-09-30 | 2015-05-18 | 5 | 2015-09-28 | 9
| 050.41095 | 050.2738.Trade Ln. | Estimate | -522.01 | 3799.41 | -4321.42 | -113.7% | -0.0009346% | -522.01 | 3799.41 | -4321.42 | 2014-10-01 | 2015-09-30 | 2015-07-01 | 7 | 2015-11-30 | 11
| 050.41108 | 2636.Vehicle.Methane.Detector | Purchase Vehicle Methane Detector (VMD) system. Includes 5' Survey Bar Assembly with IR Transmiter and Receiver, Tablet, Bluetooth and GPS Interface, Vehicle Mounting Kit, and Brush Guard from Sensit Technologies | 37390.25 | 31869.6 | 5520.65 | 17.32% | 0.06694% | 37390.25 | 31869.6 | 5520.65 | 2014-10-01 | 2015-09-30 | 2015-09-02 | 9 | 2015-09-30 | 9
| 050.41113 | 31W.Mizpah Rd.Interconnect | Establish new Texas Gas interconnect at Hwy 31W and Mizpah Rd. This is for in-line Tee and side valve to be installed while Texas Gas line is out of service. | 196015.26 | 240507.99 | -44492.73 | -18.5% | 0.3509% | 196015.26 | 240507.99 | -44492.73 | 2014-10-01 | 2015-09-30 | 2015-09-02 | 9 | 2015-11-30 | 11
| 050.41124 | 050.2734.KY 181 PI elkton | State Hwy Relocation - KY 181 - Elkton | 51124.85 | 403522.8 | -352397.95 | -87.33% | 0.09153% | 51124.85 | 403522.8 | -352397.95 | 2014-10-01 | 2015-09-30 | 2015-09-01 | 9 | 2015-11-30 | 11
| 050.41125 | 050.2735.Grade 3 Leaks | Approved FY 2015 Project Revision. Original project was ste up under general plant resulting in project failure. ( 050.40990 ). Original project was cancelled and replaced with this project. Grade three leak repairs for Glasgow | 46053.86 | 49820.82 | -3766.96 | -7.561% | 0.08245% | 46053.86 | 49820.82 | -3766.96 | 2014-10-01 | 2015-09-30 | 2014-09-03 | 9 | 2015-10-31 | 10
| 050.41147 | 050.2734.Federal St. Franklin | 625 ft. of 2 inch PE - Federal St. Franklin | 561.03 | 3917.56 | -3356.53 | -85.68% | 0.001004% | 561.03 | 3917.56 | -3356.53 | 2014-10-01 | 2015-09-30 | 2015-07-16 | 7 | 2015-09-28 | 9
| 050.41149 | 050.2739.DgwdVilaMnExt | 200 ft 2 in MDPE Main Extension | 1502.09 | 1810.71 | -308.62 | -17.04% | 0.002689% | 1502.09 | 1810.71 | -308.62 | 2014-10-01 | 2015-09-30 | 2015-07-07 | 7 | 2015-09-30 | 9
| 050.41158 | 050.2636.Barnett Rd. Ext | 550 ft. of 2 inch to serve one new customer | -899.94 | 6396.75 | -7296.69 | -114.1% | -0.001611% | -899.94 | 6396.75 | -7296.69 | 2014-10-01 | 2015-09-30 | 2015-09-04 | 9 | 2015-09-28 | 9
| 050.41198 | PRP.2736.Metcalfe Dr. | Replace approximately 700 ' of bare stl IP. with 2" PE IP. 11 services Company Crew | 7925.25 | 20848.21 | -12922.96 | -61.99% | 0.01419% | 7925.25 | 20848.21 | -12922.96 | 2014-10-01 | 2015-09-30 | 2015-09-16 | 9 | 2015-11-30 | 11
| 050.41246 | 050.2638.S 7th St Retire | Abandon 59' - 2" steel and 241' - 2" PE for a total retirement of 300 feet. Buildings being razed | 97.47 | 1161.56 | -1064.09 | -91.61% | 0.0001745% | 97.47 | 1161.56 | -1064.09 | 2014-10-01 | 2015-09-30 | 2015-09-21 | 9 | 2015-09-30 | 9
| 050.41254 | 050.2736.Ft.Campbell Blvd Ext | Install app. 200 feet of 2 inch pe for a five meter commercial building requesting natural gas service. | 530.02 | 1447.02 | -917 | -63.37% | 0.0009489% | 530.02 | 1447.02 | -917 | 2014-10-01 | 2015-09-30 | 2015-09-21 | 9 | 2015-09-28 | 9
| 050.41274 | 050.2635.E.Locust Retirement | Abandon 180 feet of 2 inch bare main. We had a grade II leak on this main, we propose retiring the main and inserting 3/4 inch service. | 97.47 | 1270.33 | -1172.86 | -92.33% | 0.0001745% | 97.47 | 1270.33 | -1172.86 | 2014-10-01 | 2015-09-30 | 2015-09-22 | 9 | 2015-09-28 | 9
| 050.41275 | 050.2636. Free Silver Rd. Ext | 2020 ft. of 2 inch PE Extension - Free Silver Rd. - Philpot | 1506.11 | 7969.63 | -6463.52 | -81.1% | 0.002697% | 1506.11 | 7969.63 | -6463.52 | 2014-10-01 | 2015-09-30 | 2015-10-01 | 10 | 2015-12-30 | 12

## 2014a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2014
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2014 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.23173 | 050.2637.Drawbridge Trace Ext | Install 215' PE for one existing residential customer requesting natural gas | 795.2 | 1532.49 | 438.7 | 28.63% | 0.004515% | 1971.19 | 1532.49 | 438.7 | 2013-10-01 | 2014-09-30 | 2010-02-11 | 2 | 2010-06-01 | 6
| 050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth Meters Functional | 149127.47 | 0 |  |  | 1.886% | 823263.03 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth Meters Functional | 12589.51 | 0 |  |  | 0.1946% | 84934.09 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth Meter Functional | 25537.04 | 0 |  |  | 0.3049% | 133122.03 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth Meters Functional | 21528.26 | 0 |  |  | 0.3197% | 139579.98 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth Meter Functional | 18488.99 | 0 |  |  | 0.3061% | 133627.03 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth Meters Functional | 88623.34 | 0 |  |  | 0.8209% | 358382.6 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth Meters Functional | 11819.71 | 0 |  |  | 0.1597% | 69707.07 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth Meters Functional | 9548.68 | 0 |  |  | 0.1568% | 68473.79 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth Meters Functional | 80506.61 | 0 |  |  | 1.019% | 444971.45 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth Meters Functional | 49494.54 | 0 |  |  | 0.6909% | 301616.19 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth Meters Functional | 14254.05 | 0 |  |  | 0.1241% | 54191.21 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth Regs Functional | 67631.73 | 0 |  |  | 1.334% | 582484.68 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth Regs Functional | 892.56 | 0 |  |  | 0.0476% | 20779.5 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth Regs Functional | 8152.03 | 0 |  |  | 0.08091% | 35322.44 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23641 | KY.Danville Growth COMM MEAS | Danville Growth Regs Functional | 14803.61 | 0 |  |  | 0.452% | 197340.74 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth Regs Functional | 30273.29 | 0 |  |  | 0.1358% | 59270.72 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth Regs Functional | 38299.45 | 0 |  |  | 0.3546% | 154810 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth Regs Functional | 24412.32 | 0 |  |  | 0.1203% | 52525.41 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth Regs Functional | 2383.12 | 0 |  |  | 0.1816% | 79288.58 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth Regs Functional | 63338.22 | 0 |  |  | 0.6584% | 287442.92 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth Regs Functional | 24520.29 | 0 |  |  | 0.4611% | 201302.99 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth Regs Functional | 11339.82 | 0 |  |  | 0.1319% | 57580.04 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 562436.93 | 0 |  |  | 5.561% | 2427788.72 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 62244.39 | 0 |  |  | 0.7091% | 309573.48 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functiona | 75127.98 | 0 |  |  | 0.4943% | 215793.18 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 68549.11 | 0 |  |  | 0.4902% | 213983.57 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 60439.5 | 0 |  |  | 0.3731% | 162868.95 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 230439.33 | 0 |  |  | 1.645% | 718053.2 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 63686.73 | 0 |  |  | 0.6582% | 287344.23 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 44961.33 | 0 |  |  | 0.3764% | 164308 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 465324.47 | 0 |  |  | 3.53% | 1541214.59 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 85905.09 | 0 |  |  | 1.92% | 838213.34 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 46696.16 | 0 |  |  | 0.5826% | 254344.41 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional | 210445.94 | 0 |  |  | 1.848% | 806940.64 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 11819.68 | 0 |  |  | 0.2953% | 128903.11 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 35438.93 | 0 |  |  | 0.3251% | 141940.83 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional | 26999.4 | 0 |  |  | 0.3209% | 140101.58 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 17269.71 | 0 |  |  | 0.2001% | 87351.31 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 50728.79 | 0 |  |  | 0.2501% | 109190.33 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional | 20295.93 | 0 |  |  | 0.3211% | 140190.53 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional | 25515.17 | 0 |  |  | 0.1995% | 87114.62 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional | 76887.52 | 0 |  |  | 1.233% | 538095.03 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional | 61641.37 | 0 |  |  | 0.9972% | 435352.37 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional | 11020.92 | 0 |  |  | 0.1425% | 62229.43 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 426121.13 | 0 |  |  | 3.323% | 1450518.16 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 68704.45 | 0 |  |  | 0.7384% | 322344.22 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 328704.27 | 0 |  |  | 2.202% | 961386.33 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 179830.04 | 0 |  |  | 1.935% | 844933.79 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 104990.51 | 0 |  |  | 0.9402% | 410450.81 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 143378.61 | 0 |  |  | 0.8517% | 371834.07 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 227659.22 | 0 |  |  | 1.571% | 685644.54 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 86542.46 | 0 |  |  | 0.8644% | 377372.05 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 220884.41 | 0 |  |  | 2.69% | 1174192.61 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 326940.77 | 0 |  |  | 2.974% | 1298454.87 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 100797.03 | 0 |  |  | 0.8808% | 384519.83 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth Meters Functional | 552682.93 | 0 |  |  | 4.674% | 2040636.1 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth Meters Functional | 196242.56 | 0 |  |  | 1.516% | 662003.44 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth Meters Functional | 240277.23 | 0 |  |  | 1.714% | 748261.95 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth Meters Functional | 210032.2 | 0 |  |  | 2.013% | 878984.86 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth Meters Functional | 270486.56 | 0 |  |  | 1.664% | 726308.53 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth Meters Functional | 206437.96 | 0 |  |  | 1.336% | 583097.6 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth Meters Functional | 195365.22 | 0 |  |  | 2.336% | 1019665.52 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth Meters Functional | 116107.49 | 0 |  |  | 1.045% | 456368.56 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth Meters Functional | 901617.51 | 0 |  |  | 7.921% | 3458128.42 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth Meters Functional | 301501.56 | 0 |  |  | 2.657% | 1159877.79 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth Meters Functional | 205528.62 | 0 |  |  | 1.888% | 824064.64 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23834 | DanvilleIntegRegs | Danville Non Growth Regs Functional | 27.28 | 0 |  |  | 0.1404% | 61285.63 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23835 | CampbellsvilleIntegRegs | Campbellsville Non Growth Regs Functional | 171.92 | 0 |  |  | 0.1154% | 50369.47 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23836 | KY.ShelbyvilleIntegRegs | Shelbyville KY Non Growth Regs Functional | 483.84 | 0 |  |  | 0.2239% | 97753.86 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23838 | MadisonvilleIntegRegs | Madisonville Non Growth Regs | 1992.65 | 0 |  |  | 0.1728% | 75437.75 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23839 | PrincetonIntegRegs | Princeton Non Growth Regs Functional | 3375.15 | 0 |  |  | 0.1296% | 56594.73 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non Growth CP/Leak Clamps Functional | 101903.58 | 0 |  |  | 0.8288% | 361807.8 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23872 | Glasgow Integ CP / ANODES | Glasgow Non Growth CP/Leak Clamps Functional | 5869.33 | 0 |  |  | 0.09158% | 39979.91 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non Growth CP/Leak Clamps Functional | 69249.59 | 0 |  |  | 0.6742% | 294332.37 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23874 | Danville Integ CP / ANODES | Danville Non Growth CP/Leak Clamps Functional | 95046.1 | 0 |  |  | 0.703% | 306886.76 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non Growth CP/Leak Clamps Functional | 7192.84 | 0 |  |  | 0.2357% | 102883.32 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non Growth CP/Leak Clamps Functional | 7264.38 | 0 |  |  | 0.1442% | 62935.76 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non Growth CP/Leak Clamps Functional | 12171.42 | 0 |  |  | 0.225% | 98219.99 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23878 | Princeton Integ CP/ ANODE | Princeton Non Growth CP/Leak Clamps Functional | 42627.58 | 0 |  |  | 0.3908% | 170602.78 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23879 | Owensboro Integ CP / ANODE | Owensboro Non Growth CP/Leak Clamps Functional | 10674.55 | 0 |  |  | 0.3811% | 166362.13 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23880 | Paducah Integ CP / ANODE | Paducah Non Growth CP/Leak Clamps Functional | 44509.95 | 0 |  |  | 0.5904% | 257725.38 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non Growth CP/Leak Clamps Functional | 6322.55 | 0 |  |  | 0.07892% | 34455.19 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 387598.42 | 0 |  |  | 2.701% | 1179063.71 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 138105.34 | 0 |  |  | 0.7346% | 320716.71 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 46002.56 | 0 |  |  | 0.4212% | 183897.6 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 31817.64 | 0 |  |  | 0.516% | 225256.69 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 18359.97 | 0 |  |  | 0.2636% | 115072.05 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 11378.64 | 0 |  |  | 0.1492% | 65127.18 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 50396.41 | 0 |  |  | 0.4441% | 193883.85 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 27523.4 | 0 |  |  | 0.2126% | 92799.84 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 92402.54 | 0 |  |  | 1.066% | 465552.36 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 89377.47 | 0 |  |  | 0.8912% | 389086.07 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 26773.9 | 0 |  |  | 0.1287% | 56164.8 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 255689.48 | 0 |  |  | 2.333% | 1018438.22 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 95778.1 | 0 |  |  | 0.6706% | 292751.43 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 40855.58 | 0 |  |  | 0.7738% | 337830.12 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23952 | DanvilleLeakServices | Dannville Leak Functional Services | 56294.21 | 0 |  |  | 0.8558% | 373607.74 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 21512.55 | 0 |  |  | 0.3223% | 140724.84 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 24058.59 | 0 |  |  | 0.2539% | 110839.22 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 28213.76 | 0 |  |  | 0.3919% | 171075.68 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 12929.4 | 0 |  |  | 0.1934% | 84413.29 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 118189.73 | 0 |  |  | 1.316% | 574538.79 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 193383.6 | 0 |  |  | 1.606% | 700934.46 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 22305.73 | 0 |  |  | 0.2149% | 93828.39 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Leak Functional Meters | 171409.9 | 0 |  |  | 1.559% | 680655.77 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Leak Functional Meters | 66347.65 | 0 |  |  | 0.6383% | 278650.63 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Leak Functional Meters | 29823.39 | 0 |  |  | 0.1635% | 71360.05 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23992 | KY.Danville Integ COMM MEAS | Danville Leak Meters Functional | 125061.95 | 0 |  |  | 0.8352% | 364616.25 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Leak Functional Meters | 89346.76 | 0 |  |  | 0.6309% | 275446.28 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Leak Functional Meters | 56905.43 | 0 |  |  | 0.3082% | 134568.09 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Leak Functional Meters | 28674.32 | 0 |  |  | 0.2091% | 91277.58 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23996 | KY.Princeton Integ COMM MEAS | Princeton Leak Functional Meters | 28157.3 | 0 |  |  | 0.241% | 105227.06 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Leak Functional Meters | 258057.38 | 0 |  |  | 1.727% | 753756.85 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23998 | KY.Paducah Integ COMM MEAS | Paducah Leak Functional Meters | 45811.47 | 0 |  |  | 0.5099% | 222602.02 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Leak Meters Functional | 10900.41 | 0 |  |  | 0.135% | 58942.67 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24034 | MadisonvilleLeakRegs | Madisonville Leak Regs Functional | 115.83 | 0 |  |  | 0.02202% | 9612.53 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24035 | PrincetonLeakRegs | Princeton Leak Regs Functional | 923.26 | 0 |  |  | 0.01834% | 8008.06 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24067 | BowlingLeakCP/LeakClamps | Bowling Green KY Leak Functional - CP/Leak Clamps | 32795.36 | 0 |  |  | 1.079% | 471020.15 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24070 | DanvilleLeakCP/LeakClamps | Danville Leak Functional - CP/Leak Clamps | 7552.34 | 0 |  |  | 0.3058% | 133483.48 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24073 | MadisonLeakCP/LeakClamps | Madisonville Leak Functional - CP/Leak Clamps | 440.43 | 0 |  |  | 0.1932% | 84365.75 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24074 | PrincetonLeakCP/LeakClamps | Princeton Leak Functional - CP/Leak Clamps | 3004.03 | 0 |  |  | 0.1353% | 59072.94 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 29819.91 | 0 |  |  | 0.1244% | 54311.84 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 10.2 | 0 |  |  | 0.02717% | 11862.18 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 853304.8 | 0 |  |  | 5.149% | 2247946.49 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 473841.61 | 0 |  |  | 3.625% | 1582570.73 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 755549.8 | 0 |  |  | 6.038% | 2635788.56 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 8725.34 | 0 |  |  | 0.2109% | 92088.52 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24088 | BowlingGreenPRPMeters | Bowling Greek KY PRP Functional - Meters | 8035.06 | 0 |  |  | 0.01849% | 8070.64 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24089 | DanvillePRPMeters | Danville KY PRP Functional - Meters | 96.21 | 0 |  |  | 0.007504% | 3276.07 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24109 | KY.Storage Integ RESI MEAS | KY Storage & Transmission Non Growth Functional - Meters | 2097.72 | 0 |  |  | 0.01928% | 8418.94 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non Growth Functional - Regs | 842.69 | 0 |  |  | 0.0179% | 7813.07 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non Growth Functional - CP & Leak Clamps | 1968.86 | 0 |  |  | 0.01501% | 6554.96 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.26158 | 050.2636.Allen St. Rplmnt. | Replace 3120 Ft Bare 4 Inch Main with 4 Inch PE. | 21223.89 | 133927.1 | 14023.96 | 10.47% | 0.3389% | 147951.06 | 133927.1 | 14023.96 | 2013-10-01 | 2014-09-30 | 2011-06-01 | 6 | 2011-09-28 | 9
| 050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 118190.98 | 0 |  |  | 0.5986% | 261320.72 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 74722.06 | 0 |  |  | 1.06% | 462564.19 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26298 | MayfieldPRPMains | Mayfiled KY Pipe Replacement Program Functional - Mains | 151.92 | 0 |  |  | 0.000348% | 151.92 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2011-08-01 | 8
| 050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 26119.84 | 0 |  |  | 0.9148% | 399378.46 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 262417.62 | 0 |  |  | 1.927% | 841153.47 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 1615515.64 | 0 |  |  | 4.987% | 2177005.62 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 300253.8 | 0 |  |  | 1.18% | 515216.71 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.28095 | 050.2734. Hwy 100 Pub. Impv. | 6 inch HPD Reloc. - Hwy. 100 Franklin | -179370.55 | 5962.11 | -422.33 | -7.084% | 0.01269% | 5539.78 | 5962.11 | -422.33 | 2013-10-01 | 2014-09-30 | 2011-11-15 | 11 | 2012-09-28 | 9
| 050.28560 | PRP.2735 MORRIS LINE | PRP.2735.MORRIS LINE | 443.87 | 0 |  |  | 0.628% | 274170.28 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2012-05-01 | 5 | 2012-05-01 | 5
| 050.29150 | 050.2637.Windmere Cv Ext | Install 400 feet of 2 inch PE along Windmere Drive and Windmere Cove. | 3745.54 | 4997.76 | -798.67 | -15.98% | 0.009619% | 4199.09 | 4997.76 | -798.67 | 2013-10-01 | 2014-09-30 | 2012-03-01 | 3 | 2013-09-28 | 9
| 050.29205 | PRP.2635.WASH & ALLEY | WASH & ALLEY TO HARRISON | 8451.73 | 52710.31 | 10913.66 | 20.7% | 0.1457% | 63623.97 | 52710.31 | 10913.66 | 2013-10-01 | 2014-09-30 | 2012-03-12 | 3 | 2013-12-31 | 12
| 050.30242 | 050.2637.Ladera Ln Ext | Install 1,960' of 4" PE and 1,130' of 2" PE | 8466 | 24537.23 | 2809.36 | 11.45% | 0.06264% | 27346.59 | 24537.23 | 2809.36 | 2013-10-01 | 2014-09-30 | 2012-05-07 | 5 | 2012-05-31 | 5
| 050.30863 | 050.2734.northridge VI | 2 inch PE Extension - Northridge VI | -2.2 | 10147.78 | -5200.98 | -51.25% | 0.01133% | 4946.8 | 10147.78 | -5200.98 | 2013-10-01 | 2014-09-30 | 2012-06-04 | 6 | 2012-09-28 | 9
| 050.31066 | PRP.2638. Mayfield 2012 | PRP.2638. Mayfield 2012 | 3698.37 | 267423.93 | 38458.6 | 14.38% | 0.7007% | 305882.53 | 267423.93 | 38458.6 | 2013-10-01 | 2014-09-30 | 2012-06-30 | 6 | 2012-09-29 | 9
| 050.31726 | PRP.2636.FORD & GRIFFITH PL W | PRP.2636.FORD & GRIFFITH PL W | 11525.35 | 161001.17 | 46187.8 | 28.69% | 0.4746% | 207188.97 | 161001.17 | 46187.8 | 2013-10-01 | 2014-09-30 | 2012-08-21 | 8 | 2012-09-28 | 9
| 050.31914 | 050.2734.WestStBare Replc. | 3 inch Bare Steel Replc. - Franklin | 604.62 | 12579.19 | -2756.67 | -21.91% | 0.0225% | 9822.52 | 12579.19 | -2756.67 | 2013-10-01 | 2014-09-30 | 2012-08-06 | 8 | 2012-12-31 | 12
| 050.32020 | PRP.2737.HAR.BROADWAY-MAGNOLI | PRP.2737.HAR.BROADWAY-MAGNOLIA | 2574.63 | 176977.21 | 324016.02 | 183.1% | 1.148% | 500993.23 | 176977.21 | 324016.02 | 2013-10-01 | 2014-09-30 | 2012-09-14 | 9 | 2013-10-01 | 10
| 050.32038 | PRP.2635.Marion.W Belleville | PRP.2635.Marion.W Belleville St | 15265.26 | 0 |  |  | 0.5417% | 236496.06 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-09-28 | 9 | 2013-09-28 | 9
| 050.32412 | PRP.2635.Marion.South Main St | PRP.2635.Marion.South Main St | 42103.21 | 0 |  |  | 0.7057% | 308074.11 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-09-28 | 9 | 2013-09-28 | 9
| 050.32676 | 050.2735.AUTUMN RIDGE | 6136 ft, of 2 inch PE - Autumn Ridge Sub. | -7203.24 | 79855 | 75617.48 | 94.69% | 0.3561% | 155472.48 | 79855 | 75617.48 | 2013-10-01 | 2014-09-30 | 2012-10-29 | 10 | 2013-09-28 | 9
| 050.32688 | 050.2609.St.Charles Wells | Workover wells at St Charles Storage Field. | 27970.3 | 977316.46 | 36631.89 | 3.748% | 2.323% | 1013948.35 | 977316.46 | 36631.89 | 2013-10-01 | 2014-09-30 | 2012-10-30 | 10 | 2013-09-28 | 9
| 050.32704 | PRP.2734.State St Repl | Replace and Convert LP to IP | 16877.72 | 0 |  |  | 1.164% | 508203.35 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-07-31 | 7 | 2015-09-30 | 9
| 050.32775 | PRP.2609.Fruithill to Hoptown | Replace approximately 25000 Ft 10 Inch 6 Inch Bare Stl. with 12 Inch Stl. | 373853.92 | 5708987.47 | -386307.79 | -6.767% | 12.19% | 5322679.68 | 5708987.47 | -386307.79 | 2013-10-01 | 2014-09-30 | 2012-10-28 | 10 | 2015-09-30 | 9
| 050.32930 | PRP.2737.HAR.COLLEGE-CORNISH | PRP.2737.HAR.NORTH COLLEGE AND CORNISHVILLE RD | 364657.26 | 665397.26 | 603706.67 | 90.73% | 2.907% | 1269103.93 | 665397.26 | 603706.67 | 2013-10-01 | 2014-09-30 | 2012-09-14 | 9 | 2015-09-30 | 9
| 050.32960 | 050.2734.Hwy31W Reloc - Frk | Hwy 31W- 1008 to Memorial Reloc. | 2292.95 | 225067.56 | -67468.91 | -29.98% | 0.361% | 157598.65 | 225067.56 | -67468.91 | 2013-10-01 | 2014-09-30 | 2012-11-26 | 11 | 2015-09-30 | 9
| 050.32986 | RTU upgrades KY | RTU upgrades for KY stations | 668.14 | 7177.44 | 6251.27 | 87.1% | 0.03076% | 13428.71 | 7177.44 | 6251.27 | 2013-10-01 | 2014-09-30 | 2012-10-12 | 10 | 2014-09-30 | 9
| 050.33000 | 050.2612 KY YZ Covers | Covers for KY YZ odorizers | 3955.74 | 14354.4 | -3618.12 | -25.21% | 0.02459% | 10736.28 | 14354.4 | -3618.12 | 2013-10-01 | 2014-09-30 | 2012-12-06 | 12 | 2015-09-30 | 9
| 050.33143 | 050.2734.Cumberland Ridge V | 1670 ft. of 2 inch PE - Cumberland Ridge V | -751.21 | 9651.17 | -4579.92 | -47.45% | 0.01162% | 5071.25 | 9651.17 | -4579.92 | 2013-10-01 | 2014-09-30 | 2012-11-15 | 11 | 2015-09-30 | 9
| 050.33144 | PRP Horse Cave SE 2013 | PRP Horse Cave SE 2013 | 216257.72 | 519599.52 | 105154.21 | 20.24% | 1.431% | 624753.73 | 519599.52 | 105154.21 | 2013-10-01 | 2014-09-30 | 2013-01-19 | 1 | 2015-09-30 | 9
| 050.33154 | 050.2734.Vet.Mem and Gordon | Relocate 6 inch Coated Steel - Family Dollar B.G. | -14287.27 | 45208.21 | -16893.06 | -37.37% | 0.06486% | 28315.15 | 45208.21 | -16893.06 | 2013-10-01 | 2014-09-30 | 2012-12-31 | 12 | 2015-09-30 | 9
| 050.33220 | PRP.2734.Fairview and High | Replace 4 ich LP Bare - Fairview at High | -132.04 | 60061.39 | -50732.2 | -84.47% | 0.02137% | 9329.19 | 60061.39 | -50732.2 | 2013-10-01 | 2014-09-30 | 2012-12-19 | 12 | 2015-09-30 | 9
| 050.33294 | PRP.2734.Auburn Repl 2013 | Main, Park, S Lincoln, Mill, Spring & E. Main | 94719.21 | 714121.99 | -128993.98 | -18.06% | 1.34% | 585128.01 | 714121.99 | -128993.98 | 2013-10-01 | 2014-09-30 | 0013-01-25 | #VALUE! | 2015-09-30 | 9
| 050.33349 | 050.2637.N 6th Relocate | City of Paducah making road improvements, we propose to install 364' of 2 inch PR, abandon 270' of 2 inch MW and 90' of 2 inch PE for a total retirement of 360 feet. No reimbursement | 2611.14 | 4659.21 | -906.78 | -19.46% | 0.008595% | 3752.43 | 4659.21 | -906.78 | 2013-10-01 | 2014-09-30 | 2013-04-08 | 4 | 2015-09-30 | 9
| 050.33379 | 050.2609.De-Hy Replacements | Replace De-Hy plants at St. Charles and Bon Horbor | -1502.97 | 218700.88 | 33134.39 | 15.15% | 0.5769% | 251835.27 | 218700.88 | 33134.39 | 2013-10-01 | 2014-09-30 | 2013-02-05 | 2 | 2015-09-30 | 9
| 050.33410 | 2737.JC.HENRY ST 2013 | INSTALL 178ft OF 2in PE TO SERVE ONE COMMERICAL CUSTOMER | -744.14 | 668.84 | 982.31 | 146.9% | 0.003782% | 1651.15 | 668.84 | 982.31 | 2013-10-01 | 2014-09-30 | 2013-03-01 | 3 | 2015-09-30 | 9
| 050.33413 | 050.2634.Northern Star Way | Install approximately 5200 ft 4" High Density PE in the 4 Star industrial park in Henderson County. Industrial Board contacting through approved Contractor WHF INC . Atmos will be Inspecting and tying new pipe in to existing Reg Set. | 1710.42 | 7687.81 | 5322.52 | 69.23% | 0.0298% | 13010.33 | 7687.81 | 5322.52 | 2013-10-01 | 2014-09-30 | 2013-02-11 | 2 | 2014-11-30 | 11
| 050.33425 | PRP.2636.Glendale Dr. | Replace 3 Inch bare main crossing that is leaking with 2 Inch PE. | 9073.03 | 7245.23 | 2736.34 | 37.77% | 0.02286% | 9981.57 | 7245.23 | 2736.34 | 2013-10-01 | 2014-09-30 | 2013-02-05 | 2 | 2013-09-28 | 9
| 050.33502 | 050.2734.SglenGables Apprch | 10,032 ft of 4 inch HPD Approach Main - S Glen Gables - B.G. | -4705.38 | 393862.41 | 435240.71 | 110.5% | 1.899% | 829103.12 | 393862.41 | 435240.71 | 2013-10-01 | 2014-09-30 | 2013-01-22 | 1 | 2015-09-30 | 9
| 050.33534 | PRP.2734.WOODFORD STA REPL | Woodford,Vine, Wilson, W 11th & W 12th | 76444.22 | 0 |  |  | 0.7886% | 344263.11 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-12-31 | 12 | 2015-09-30 | 9
| 050.33542 | 050.2636.Bourbon Ct. | Install 1611 ft 2 Inch PE to serve 1 commercial customer | -3081.51 | 9773.76 | 1232.51 | 12.61% | 0.02521% | 11006.27 | 9773.76 | 1232.51 | 2013-10-01 | 2014-09-30 | 2013-02-22 | 2 | 2015-09-30 | 9
| 050.33641 | 050.2736.Lovers Ln. Relo. | Relocate 150 ft 4 Inch PE for road widening | 3225.28 | 39274.35 | 363.05 | 0.9244% | 0.09079% | 39637.4 | 39274.35 | 363.05 | 2013-10-01 | 2014-09-30 | 2013-03-05 | 3 | 2013-12-28 | 12
| 050.33723 | 2737.STANFORD TBS REBUILD | REBUILD THE STANFORD TOWN BORDER STATION INSTALLING UPSTREAM AND DOWNSTREAM VALVES | 132.04 | 82385.21 | 0 |  | 0.1887% | 82385.21 | 82385.21 | 0 | 2013-10-01 | 2014-09-30 | 2013-03-01 | 3 | 2014-03-01 | 3
| 050.33729 | 050.2638.The Meadows 5 Ext | Install 1,300 feet of 2 inch poly for 17 new residential lots in this fifth phase of The Meadows Subdivision. | 6641.75 | 6343.44 | 3796.05 | 59.84% | 0.02323% | 10139.49 | 6343.44 | 3796.05 | 2013-10-01 | 2014-09-30 | 2013-05-02 | 5 | 2013-07-28 | 7
| 050.33870 | 050.2637.Estes Lane Ext | Install 230 feet of two inch poly pipe for one customer converting heat from electric. | -0.66 | 1449.75 | 2201.85 | 151.9% | 0.008364% | 3651.6 | 1449.75 | 2201.85 | 2013-10-01 | 2014-09-30 | 2013-04-22 | 4 | 2013-09-28 | 9
| 050.33969 | 050.2637.Stiles Lndg Ext | Install 370 feet of 2 inch poly main for one new residential customer requesting gas service. | -691.46 | 4252.8 | -2755.29 | -64.79% | 0.00343% | 1497.51 | 4252.8 | -2755.29 | 2013-10-01 | 2014-09-30 | 2013-05-05 | 5 | 2013-09-28 | 9
| 050.33971 | 050.2636.Beaver Dam Purchase | Replace and repair equipment at Hartford & Beaver Dam purchase due to lighting Strike at Station. | -2047.39 | 34477.68 | -10362.01 | -30.05% | 0.05524% | 24115.67 | 34477.68 | -10362.01 | 2013-10-01 | 2014-09-30 | 2013-04-17 | 4 | 2013-09-28 | 9
| 050.33985 | 050.2609.Ground Beds | Replace depleted ground beds at Kirkwood Springs & Line #176 Highway 85. | -4626.23 | 53738.52 | -12491.09 | -23.24% | 0.09448% | 41247.43 | 53738.52 | -12491.09 | 2013-10-01 | 2014-09-30 | 2013-04-25 | 4 | 2013-09-28 | 9
| 050.33986 | 050.2636.Ground Bed | Replace depleted ground bed Oak St. in Greeenville | -1294.62 | 27525.84 | -8212.97 | -29.84% | 0.04424% | 19312.87 | 27525.84 | -8212.97 | 2013-10-01 | 2014-09-30 | 2013-04-25 | 4 | 2013-09-28 | 9
| 050.34005 | 2737.WALTON AVE-HWY 127 | INSTALL 2in PE TO SERVE LOT 4 ON WALTON AVE - WALMART OUTPARCEL | -2792.5 | 1625.32 | -2275.7 | -140% | -0.00149% | -650.38 | 1625.32 | -2275.7 | 2013-10-01 | 2014-09-30 | 2012-07-01 | 7 | 2013-07-01 | 7
| 050.34066 | PRP.2738.N COLUMBIA-3rd | INSTALL 450ft OF 2in PE TO REPLACE BARE PIPE ON NORTH COLUMBIA AND 3rd STREETS IN CAMPBELLSVILLE | 800.16 | 14361.2 | -12582.03 | -87.61% | 0.004075% | 1779.17 | 14361.2 | -12582.03 | 2013-10-01 | 2014-09-30 | 2013-05-01 | 5 | 2014-05-01 | 5
| 050.34098 | PRP.2636.W PARRISH AVE_1 | Bare pipe repl on Parrish and south | 91299.52 | 685518.46 | -44623.48 | -6.509% | 1.468% | 640894.98 | 685518.46 | -44623.48 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2013-12-01 | 12
| 050.34127 | PRP.2734.AVE OF CHAMPIONS | Replace main along Ave of Champions | 720.36 | 0 |  |  | 0.4956% | 216346.61 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-09-27 | 9 | 2013-09-27 | 9
| 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | REPLACE RECTIFIER AND GROUND BED IN JUNCTION CITY ON MILL ST | 13188.44 | 19511.4 | -2120.5 | -10.87% | 0.03984% | 17390.9 | 19511.4 | -2120.5 | 2013-10-01 | 2014-09-30 | 2013-05-01 | 5 | 2015-05-01 | 5
| 050.34129 | PRP.2734.W 15TH & STUBBINS | Repl bare main on W 15th & Stubbins | 33877.96 | 0 |  |  | 0.1583% | 69104.25 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-09-27 | 9 | 2013-09-27 | 9
| 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | HUBBLE ROAD STATION REPLACEMENT. INSTALL 1500ft OF 4in PE AND RETIRE MORGANS SUBD STATION 1962 | 24607.38 | 37316.65 | 19812.12 | 53.09% | 0.1309% | 57128.77 | 37316.65 | 19812.12 | 2013-10-01 | 2014-09-30 | 2013-03-01 | 3 | 2015-03-01 | 3
| 050.34184 | 050.2634.Basket Boiler | Install Boiler at Basket Purchase Station | 27521.85 | 58782.52 | 2895.64 | 4.926% | 0.1413% | 61678.16 | 58782.52 | 2895.64 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2013-09-28 | 9
| 050.34186 | 050.2634.Hanson TBS Regs | Replace Rockwell Regs. with Mooney Regs at Hanson TBS. | 398.77 | 42202.09 | -29267.97 | -69.35% | 0.02963% | 12934.12 | 42202.09 | -29267.97 | 2013-10-01 | 2014-09-30 | 2013-05-28 | 5 | 2013-09-28 | 9
| 050.34206 | 2737.DOWNTOWN LP RETIRE | REITRE THE LP SYSTEM IN DOWNTOWN DANVILLE. IP IS INSTALLED AND ALL METERS HAVE BEEN TRANSFERED OVER TO THE IP LINES | -384.22 | 9138.25 | -3422.57 | -37.45% | 0.01309% | 5715.68 | 9138.25 | -3422.57 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2014-06-01 | 6
| 050.34264 | 2738.CAM.MEADOW CREEK RD | INSTALL 18,500ft OF pe PIPE TO SERVE CHICKEN HOUSES | 19353.61 | 73569.82 | -15824.65 | -21.51% | 0.1323% | 57745.17 | 73569.82 | -15824.65 | 2013-10-01 | 2014-09-30 | 2012-07-01 | 7 | 2013-07-01 | 7
| 050.34293 | 050.2636.Masonville TBS | Replace and upgrade Masonville TBS for Deer Valley Subdivision | 13163.42 | 38023.07 | 7869.38 | 20.7% | 0.1051% | 45892.45 | 38023.07 | 7869.38 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2013-09-28 | 9
| 050.34295 | 050.2634.Basket TBS Relo. | Relocate Basket TBS Station due to Soil erosion at present location | 487.26 | 28790.67 | -15296.94 | -53.13% | 0.03091% | 13493.73 | 28790.67 | -15296.94 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2013-09-28 | 9
| 050.34324 | 2737.HAR.PURCH ODOR REPLACE | REPLACE ORDORIZOR AT THE HARRODSBURG PURCHASE STATION - INSTALL YZ ODORIZOR | 20831.61 | 66681.61 | -8449.85 | -12.67% | 0.1334% | 58231.76 | 66681.61 | -8449.85 | 2013-10-01 | 2014-09-30 | 2012-10-01 | 10 | 2014-09-30 | 9
| 050.34327 | 2739.CLOVERBROOK 3b-2 2013 | INSTALL 1150 ft OF 2in PE FOR 19 LOTS IN CLOVERBROOK - JOINT TRENCH PROJECT | 9004.9 | 11800.11 | -1896.17 | -16.07% | 0.02269% | 9903.94 | 11800.11 | -1896.17 | 2013-10-01 | 2014-09-30 | 2013-05-01 | 5 | 2014-05-01 | 5
| 050.34448 | PRP.2637.31st Street | City of Paducah making road improvements that include widening. We are abandoning app. 1000 feet of 6 inch bare steel main. Replacing with 6 inch poly pipe. No services affected.. | -2799.35 | 35879.82 | 17074.08 | 47.59% | 0.1213% | 52953.9 | 35879.82 | 17074.08 | 2013-10-01 | 2014-09-30 | 2013-06-17 | 6 | 2013-09-28 | 9
| 050.34460 | 050.2636.Lafayette St. | Install 1573 ft 2 Inch PE to serve 38 residential apartments. | 13399.35 | 12046.61 | 4897.27 | 40.65% | 0.03881% | 16943.88 | 12046.61 | 4897.27 | 2013-10-01 | 2014-09-30 | 2013-03-15 | 3 | 2013-09-28 | 9
| 050.34504 | PRP.2609.Fruithill Hoptown Rt | This project is to retire the Trans Pipe that is being repplaced on project 050.32775 new pipe is HPD can't retire Trans assets on Distibution plant projects. | 77124.52 | 73156.12 | 6249.18 | 8.542% | 0.1819% | 79405.3 | 73156.12 | 6249.18 | 2013-10-01 | 2014-09-30 | 2013-06-19 | 6 | 2013-09-28 | 9
| 050.34507 | PRP.2736.VIRGINIA ST | Repl bare main along Virginia & side streets to | 359368.93 | 345660.25 | 238421.91 | 68.98% | 1.338% | 584082.16 | 345660.25 | 238421.91 | 2013-10-01 | 2014-09-30 | 2013-06-24 | 6 | 2013-09-28 | 9
| 050.34539 | 050.2736.Clinic Dr.Relocation | Relocate approximately 974 ft 4 Inch Stl. and 2 Inch Pe for Clinic Dr. and Hwy 41 widening. | -2711.16 | 26784.97 | -16194.65 | -60.46% | 0.02426% | 10590.32 | 26784.97 | -16194.65 | 2013-10-01 | 2014-09-30 | 2013-04-20 | 4 | 2013-09-28 | 9
| 050.34585 | Reg Replace T.B 2 - Paducah | We propose to install 4" Mooney Regulators, Retire existing 4" Axial flow Regulators at Paducah Town border 2 - Lourdes Hospital. | -1288.65 | 27715.76 | 991.08 | 3.576% | 0.06576% | 28706.84 | 27715.76 | 991.08 | 2013-10-01 | 2014-09-30 | 2014-07-15 | 7 | 2014-09-30 | 9
| 050.34598 | PRP.2738.SOUTH C-VILLE 2013 | REPLACE 5445ft OF 2in BARE AND 800ft OF 4in BARE STEEL AROUND SOUTH CENTRAL AVE AREA IN CAMPBELLSVILLE | 135188.57 | 606799.55 | -346184.56 | -57.05% | 0.597% | 260614.99 | 606799.55 | -346184.56 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2014-06-01 | 6
| 050.34623 | Replace regulators - Cadiz TB | Replace (2) 2" Fisher 299's with (4) 2" Mooney regulators | 3002.19 | 20082.84 | -3240.18 | -16.13% | 0.03858% | 16842.66 | 20082.84 | -3240.18 | 2013-10-01 | 2014-09-30 | 2013-08-01 | 8 | 2013-09-30 | 9
| 050.34635 | 050.2638.Youngblood Dr Ext | Install 225 feet of 2 inch PE for one commercial customerr (Joey Hobbs) | -390.07 | 2123.99 | 713.96 | 33.61% | 0.006501% | 2837.95 | 2123.99 | 713.96 | 2013-10-01 | 2014-09-30 | 2013-07-29 | 7 | 2013-09-28 | 9
| 050.34638 | 050.2736.Millbrooke Relocate | Replace app. 700 feet of 6 inch MW with 6 inch P.E. Existing main is strapped to a bridge, the pipe and it's support structure are in a deteriorated condition. | 29983.62 | 163854.88 | -44841.53 | -27.37% | 0.2726% | 119013.35 | 163854.88 | -44841.53 | 2013-10-01 | 2014-09-30 | 2013-07-15 | 7 | 2013-09-28 | 9
| 050.34639 | 050.2638.Coplen Reg Replace | Replace existing regulator station with 3/4 inch MTDeason station that has 627R regulator | 10721.39 | 9232.67 | 6140.77 | 66.51% | 0.03521% | 15373.44 | 9232.67 | 6140.77 | 2013-10-01 | 2014-09-30 | 2013-07-29 | 7 | 2013-09-28 | 9
| 050.34691 | 050.2636.Hwy 138 | Install 2200 ft 2 Inch PE to serve 1 residential customer | -1468.28 | 1664 | 2605.82 | 156.6% | 0.009781% | 4269.82 | 1664 | 2605.82 | 2013-10-01 | 2014-09-30 | 2013-07-25 | 7 | 2013-09-28 | 9
| 050.34708 | 2735.ASHKIRK LN 2013 | INSTALL 280' OF 2" PE FOR THREE LOTS ON ASHKIRK LN IN GLASGOW | 1049.39 | 2797.89 | -1096.33 | -39.18% | 0.003898% | 1701.56 | 2797.89 | -1096.33 | 2013-10-01 | 2014-09-30 | 2013-07-15 | 7 | 2014-07-15 | 7
| 050.34710 | DTEX Odorant Detection System | YZ Systems Inc DTEX Odorant Detection System. Model DX01000G. | 280.41 | 3883.98 | 159.41 | 4.104% | 0.009262% | 4043.39 | 3883.98 | 159.41 | 2013-10-01 | 2014-09-30 | 2012-10-12 | 10 | 2014-09-30 | 9
| 050.34737 | 2739.McCORMICK LN 2013 | INSTALL 230' OF 2" PE ON McCORMICK LN TOWARDS HWY 127 | 1484.2 | 1006.34 | 5467.38 | 543.3% | 0.01483% | 6473.72 | 1006.34 | 5467.38 | 2013-10-01 | 2014-09-30 | 2013-07-01 | 7 | 2013-09-01 | 9
| 050.34783 | Install 3 inch Mooneys | Woodmill Regulator Station in Hopkinsville. We are replacing the (2) 3 inch 461 - 57S Roll out regulators with (2) new 3 inch Mooney regulators. | -6160.29 | 11373.94 | -1161.45 | -10.21% | 0.02339% | 10212.49 | 11373.94 | -1161.45 | 2013-10-01 | 2014-09-30 | 2013-08-12 | 8 | 2013-09-28 | 9
| 050.34793 | 050.2637.Walnut Ext | Install 100 feet of 2 inch poly for one new residential customer requesting natural gas | -1.13 | 1593.53 | 2599.85 | 163.2% | 0.009605% | 4193.38 | 1593.53 | 2599.85 | 2013-10-01 | 2014-09-30 | 2013-08-15 | 8 | 2013-09-28 | 9
| 050.34794 | 050.2637.Hovekamp Valve | Replace broken valve | 3760.76 | 5866.24 | -1194.44 | -20.36% | 0.0107% | 4671.8 | 5866.24 | -1194.44 | 2013-10-01 | 2014-09-30 | 2013-07-29 | 7 | 2013-09-28 | 9
| 050.34806 | 050.2634.Dixon Purchase | Change out Dixon Purchase Station | 25861.93 | 24951.38 | 2593.49 | 10.39% | 0.06309% | 27544.87 | 24951.38 | 2593.49 | 2013-10-01 | 2014-09-30 | 2013-08-10 | 8 | 2013-09-28 | 9
| 050.34823 | PRP.2636.CLOVERDALE | Replace 3" bare steel | 43670.52 | 53836.15 | -7816.09 | -14.52% | 0.1054% | 46020.06 | 53836.15 | -7816.09 | 2013-10-01 | 2014-09-30 | 2013-07-03 | 7 | 2013-09-28 | 9
| 050.34824 | 2737.STAN.HUBBLE RD HP RELO | RELOCATE 550ft OF 4in STEEL HP LINE AT HUBBLE AND RIDGEWAY RD-THIS IS AT THE REQUEST OF TOMMY OWNES -PROPERTY OWNER | 117.67 | 19706.05 | -17394.45 | -88.27% | 0.005295% | 2311.6 | 19706.05 | -17394.45 | 2013-10-01 | 2014-09-30 | 2013-07-29 | 7 | 2014-09-02 | 9
| 050.34836 | 050.2637.Hwy 1523 Retire | Retire 636 feet of 4 inch steel service | -22.16 | 324.26 | 252.61 | 77.9% | 0.001321% | 576.87 | 324.26 | 252.61 | 2013-10-01 | 2014-09-30 | 2013-08-12 | 8 | 2013-09-28 | 9
| 050.34838 | 2738.SPR.LINCOLN WAY 2013 | INSTALL 300ft OF 2in PE TO SERVE FOUR COMMERICAL LOTS | -975.46 | 1519.96 | 1391.8 | 91.57% | 0.00667% | 2911.76 | 1519.96 | 1391.8 | 2013-10-01 | 2014-09-30 | 2013-06-01 | 6 | 2014-06-01 | 6
| 050.34843 | 050.2634.Midtown Commons_ | Relocate approximately 600 ft 4 Inch Stl. for new entrance into Midtown Commons Commercial developement in Madisonville Ky. | -1177.93 | 0 |  |  | -0.01746% | -7621.26 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-08-01 | 8 | 2013-09-28 | 9
| 050.34844 | PRP.Nashville Rd. Bare Replc | Replace Bare Steel on Nashville Rd - Russellville | 6494.04 | 12252.7 | -5358.91 | -43.74% | 0.01579% | 6893.79 | 12252.7 | -5358.91 | 2013-10-01 | 2014-09-30 | 2013-08-01 | 8 | 2013-12-31 | 12
| 050.34845 | PRP.2734.Barren River & Wdfrd | Repl 6 in stl with 6 in PE along Old Barren River Rd and Woodford Ave | 75852.46 | 123893.13 | 15441.09 | 12.46% | 0.3192% | 139334.22 | 123893.13 | 15441.09 | 2013-10-01 | 2014-09-30 | 2013-08-01 | 8 | 2013-12-31 | 12
| 050.34847 | PRP.2734.MaxHamptonAlley | Replace 4 inch between 5th and 6th and College and State | 20380.51 | 98751.38 | -42286.85 | -42.82% | 0.1293% | 56464.53 | 98751.38 | -42286.85 | 2013-10-01 | 2014-09-30 | 2013-08-05 | 8 | 2013-12-31 | 12
| 050.34849 | PRP.Old Louisville Rd. I | replace 575 ft, of 4 inch Bare - Old Louisville Rd. | 217.32 | 83228.57 | -56061.43 | -67.36% | 0.06223% | 27167.14 | 83228.57 | -56061.43 | 2013-10-01 | 2014-09-30 | 2013-08-15 | 8 | 2013-12-31 | 12
| 050.34850 | PRP.2nd at Bethel - Russ | Replace 3" Bare w 2nd at Bethel - Russellville | 9690.13 | 24440.03 | -14197.62 | -58.09% | 0.02346% | 10242.41 | 24440.03 | -14197.62 | 2013-10-01 | 2014-09-30 | 2013-08-05 | 8 | 2013-12-31 | 12
| 050.34881 | 2739.SIMP.TRANS RELOC 2013 | RELOCATE 3925' OF 8" STEEL TRANSMISSION LINE IN SIMPSONVILLE FOR A DEVELOPER BUILDING THE OUTLET SHOPPES SOUTH OF I-64 ON VEECHDALE-CLARK STATION ROAD | 4174.54 | 0 |  |  | 0.0734% | 32043.88 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2013-08-14 | 8 | 2013-10-01 | 10
| 050.34965 | 050.2637.Union Sta Replace | Replace existing Union Station with a new pre-fab regulator station due to the existing by-pass valve being broken | 17028.75 | 23156.82 | 17463.4 | 75.41% | 0.09305% | 40620.22 | 23156.82 | 17463.4 | 2013-10-01 | 2014-09-30 | 2013-08-27 | 8 | 2013-09-28 | 9
| 050.35002 | 050.2637.13th St Replace | Abandon 318 ft of 2 inch M.W main. We currently have one grade 2 leak, gas getting near building. We have a history of leakage in this alley. we propose to retire some main in alley and install app. 100 ft on Jefferson and switch two services . | 3681.39 | 3844.33 | 2318.46 | 60.31% | 0.01412% | 6162.79 | 3844.33 | 2318.46 | 2013-10-01 | 2014-09-30 | 2013-08-28 | 8 | 2013-09-28 | 9
| 050.35012 | PRP.2609.Greenriver Steel | Replace 9010 ft Bare Stl | 825853.67 | 1230804.04 | -115646 | -9.396% | 2.554% | 1115158.04 | 1230804.04 | -115646 | 2013-10-01 | 2014-09-30 | 2013-08-25 | 8 | 2014-12-31 | 12
| 050.35013 | PRP.2609.Fruithill Hoptown 2 | Replace 26000 ft 6 Inch Bare Steel with 12 Inch Steel | 3709851.45 | 7419912.38 | -2668137.41 | -35.96% | 10.88% | 4751774.97 | 7419912.38 | -2668137.41 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-12-31 | 12
| 050.35018 | PRP.2736.W 1st St Replace | replace 108 ft of 2 inch bare with 2 inch poly | -1154.07 | 4141.13 | -713.08 | -17.22% | 0.007852% | 3428.05 | 4141.13 | -713.08 | 2013-10-01 | 2014-09-30 | 2013-08-29 | 8 | 2013-09-27 | 9
| 050.35055 | PRP.Woodburn-Franklin HPD | Replace Bare HPD from Woodburn Purchase to Akin Rd. | 3836560.65 | 4133795.54 | 424697.94 | 10.27% | 10.44% | 4558493.48 | 4133795.54 | 424697.94 | 2013-10-01 | 2014-09-30 | 2013-08-30 | 8 | 2015-09-28 | 9
| 050.35062 | 050.2638.Haven Rd Ext | Install 180 feet of 2 inch poly pipe for Mako Nesler | 499.87 | 3517.85 | -2259.6 | -64.23% | 0.002882% | 1258.25 | 3517.85 | -2259.6 | 2013-10-01 | 2014-09-30 | 2013-09-10 | 9 | 2013-09-27 | 9
| 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | BRUEST HOT CAT STATION HEATER AND A KING TOOL 2B BY-PASS ODORIZER FOR THE TRI-CITIES AIRPORT STATION | 13416.27 | 53963.3 | -40547.03 | -75.14% | 0.03073% | 13416.27 | 53963.3 | -40547.03 | 2013-10-01 | 2014-09-30 | 2013-09-05 | 9 | 2014-08-15 | 8
| 050.35066 | PRP.2738.N COLUMBIA RETIRE | RETIRE 363' OF 2" BARE STEEL PIPE ON NORTH COLUMBIA AVE BETWEEN MATTHEW AND UNIVERISTY DR | -54.88 | 1205.23 | -1071.17 | -88.88% | 0.0003071% | 134.06 | 1205.23 | -1071.17 | 2013-10-01 | 2014-09-30 | 2013-08-01 | 8 | 2013-10-01 | 10
| 050.35072 | 050.3436.OFFICE IMPROVEMENTS | PURCHASE A DEHUMIDIFICATION UNIT AND AN AIR CONDITIONER FOR THE OFFICE AT 2833 W. MARKET ST. JOHNSON CITY | 21979.42 | 25855.2 | 1988.68 | 7.692% | 0.06378% | 27843.88 | 25855.2 | 1988.68 | 2013-10-01 | 2014-09-30 | 2013-09-06 | 9 | 2013-10-30 | 10
| 050.35076 | 050.2734.Adairville Outage | Adairville Outage - 09-02-13 | -12497.74 | 63803.42 | -25334.04 | -39.71% | 0.08812% | 38469.38 | 63803.42 | -25334.04 | 2013-10-01 | 2014-09-30 | 2013-09-03 | 9 | 2013-12-31 | 12
| 050.35106 | 2739.LAW.W WOODFORD 2013 | INSTALL 270' OF 2" PE OFF OF WEST WOODFORD ACROSS FROM HUMSTON DR | -291.48 | 1644.68 | -921.73 | -56.04% | 0.001656% | 722.95 | 1644.68 | -921.73 | 2013-10-01 | 2014-09-30 | 2013-08-25 | 8 | 2013-10-01 | 10
| 050.35145 | 050.2637.Hwy 453 Relocate | Relocate 4 inch transmission main due to proximity to new building | 90097.75 | 88441.93 | 20521.65 | 23.2% | 0.2496% | 108963.58 | 88441.93 | 20521.65 | 2013-10-01 | 2014-09-30 | 2013-09-18 | 9 | 2014-09-28 | 9
| 050.35153 | 050.2637.Ky Hwy 453 Retirement | This is a seperate project to retire 1,265' - 4" steel (Transmission main). 050.35145 calls for the installation of 1,060' - 4" (H.P.D main). Two seperate projects are required. | 1483.78 | 325.06 | 1158.72 | 356.5% | 0.003399% | 1483.78 | 325.06 | 1158.72 | 2013-10-01 | 2014-09-30 | 2013-09-25 | 9 | 2014-09-30 | 9
| 050.35332 | 050.2636.Springhill Dr. | Install 1379 ft 2 Inch PE to serve residential and commercial developement. | 8031.08 | 8864.21 | -833.13 | -9.399% | 0.0184% | 8031.08 | 8864.21 | -833.13 | 2013-10-01 | 2014-09-30 | 2013-10-04 | 10 | 2014-09-28 | 9
| 050.35450 | 050.2634.Factory Outlet Dr. | Install approximately 783 ft 4 Inch PE main to serve 1 Commercial customer. | 5041.01 | 9560.79 | -4519.78 | -47.27% | 0.01155% | 5041.01 | 9560.79 | -4519.78 | 2013-10-01 | 2014-09-30 | 2013-10-11 | 10 | 2014-09-28 | 9
| 050.35570 | 050.2636.E. 8th. St. | Install 200 Ft 2 Inch PE to serve 2 residential customers | 1770.22 | 2277.1 | -506.88 | -22.26% | 0.004055% | 1770.22 | 2277.1 | -506.88 | 2013-10-01 | 2014-09-30 | 2013-10-09 | 10 | 2014-09-28 | 9
| 050.35624 | 050.2636.Circle Dr. | Install 100 Ft 2 Inch PE to serve 1 residential customer. | 3724.32 | 2286.7 | 1437.62 | 62.87% | 0.008531% | 3724.32 | 2286.7 | 1437.62 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.35628 | 050.2636.Hucks Southtown | Install approximately 2500 ft 4 Inch PE and 970 ft 2 Inch PE to serve 1 Commercial customer. | 38053.99 | 29638.26 | 8415.73 | 28.39% | 0.08717% | 38053.99 | 29638.26 | 8415.73 | 2013-10-01 | 2014-09-30 | 2013-10-14 | 10 | 2014-09-28 | 9
| 050.35635 | 2739.OLD MILL SEC 3 2014 | INSTALL 2" PE FOR 19 LOTS | 18477.12 | 24525.39 | -6048.27 | -24.66% | 0.04232% | 18477.12 | 24525.39 | -6048.27 | 2013-10-01 | 2014-09-30 | 2013-07-01 | 7 | 2014-09-30 | 9
| 050.35636 | 050.2636.Williams Dr. | Install 100 ft 2 Inch PE to serve 2 New residential customers | 2281.51 | 2056.71 | 224.8 | 10.93% | 0.005226% | 2281.51 | 2056.71 | 224.8 | 2013-10-01 | 2014-09-30 | 2013-10-10 | 10 | 2014-09-28 | 9
| 050.35638 | 2739.HAVEN HILL RD 2014 | INSTALL 810' OF 2" PE FOR ONE NEW CUSTOMER | -853.14 | 739.97 | -1593.11 | -215.3% | -0.001954% | -853.14 | 739.97 | -1593.11 | 2013-10-01 | 2014-09-30 | 2013-08-01 | 8 | 2014-08-01 | 8
| 050.35644 | 050.2637.Hwy 95 Main Ext | Install 100 ft of 2 inch pe main for one new commercial customer (95 Motorsports) requesting natural gas service. | 4484.46 | 2821.01 | 1663.45 | 58.97% | 0.01027% | 4484.46 | 2821.01 | 1663.45 | 2013-10-01 | 2014-09-30 | 2013-11-11 | 11 | 2014-09-28 | 9
| 050.35647 | 2738.FOXWOOD-ASHWOOD 2014 | INSTALL 700' OF 2" PE ON FOXWOOD AND ASHWOOD | 2907.37 | 5925.14 | -3017.77 | -50.93% | 0.00666% | 2907.37 | 5925.14 | -3017.77 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.35649 | 2737.DANVILLE EQUIPMENT 2014 | EQUIPMENT FOR THE DANVILLE OPERATIONS FOR THE YEAR 2014 | 33843.42 | 42294 | -8450.58 | -19.98% | 0.07752% | 33843.42 | 42294 | -8450.58 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35650 | 2735.GLASGOW EQUIPMENT 2014 | EQUIPMENT FOR THE GLASGOW OPERATIONS FOR THE YEAR 2014 | 34454.32 | 39615.31 | -5160.99 | -13.03% | 0.07892% | 34454.32 | 39615.31 | -5160.99 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35651 | 2738.C-VILLE EQUIPMENT 2014 | EQUIPMENT PURCHASES FOR CAMPBELLSVILLE OPERATIONS FOR THE YEAR 2014 | 20096.75 | 19384.74 | 712.01 | 3.673% | 0.04603% | 20096.75 | 19384.74 | 712.01 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35652 | 2739.S-VILLE EQUIPMENT 2014 | EQUIPMENT PURCHASES FOR THE SHELBYVILLE OPERATIONS FOR THE YEAR 2014 | 39330.85 | 35103.92 | 4226.93 | 12.04% | 0.09009% | 39330.85 | 35103.92 | 4226.93 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-11-30 | 11
| 050.35653 | 2739.SIMPSONVILLE HP 2013 | THIS IS TO ADD THE HP LINE IN SIMPSONVILLE - THIS WAS A TRANSMISSION LINE AT THE OUTLET SHPPES THAT HAS BEEN REPLACED AND RELOCATED WITH HP DISTRIBUTION 8" STEEL IN SIMPSONVILLE | 152168.6 | 106960.71 | 45207.89 | 42.27% | 0.3486% | 152168.6 | 106960.71 | 45207.89 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-11-30 | 11
| 050.35664 | 050.2634.Sercice Center Roof | Project created to have new roof installed on the Madisonvilee Service Center. | 56690.41 | 56565.21 | 125.2 | 0.2213% | 0.1299% | 56690.41 | 56565.21 | 125.2 | 2013-10-01 | 2014-09-30 | 2013-10-21 | 10 | 2014-09-28 | 9
| 050.35669 | 050.2602.KMD North PCs | Replace PC's and laptops KMD North. | 130764.19 | 130505.38 | 258.81 | 0.1983% | 0.2995% | 130764.19 | 130505.38 | 258.81 | 2013-10-01 | 2014-09-30 | 2013-10-21 | 10 | 2014-09-28 | 9
| 050.35675 | PRP.2738.Grn.Henry St | PRP.2738.Grn.Henry St | 151020.9 | 376921.09 | -225900.19 | -59.93% | 0.3459% | 151020.9 | 376921.09 | -225900.19 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.35679 | 050.2636.Palomino Pl. 2 | Install 200 Ft 2 Inch PE to serve 8 residential lots. | 1966.2 | 3943.73 | -1977.53 | -50.14% | 0.004504% | 1966.2 | 3943.73 | -1977.53 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.35688 | 050.2609.Southwire | Replace existing 2 Inch Tap with 6 Inch tap to increase flow to Southwire | 14975.66 | 18470.31 | -3494.65 | -18.92% | 0.0343% | 14975.66 | 18470.31 | -3494.65 | 2013-10-01 | 2014-09-30 | 2013-10-18 | 10 | 2015-11-15 | 11
| 050.35692 | PRP.2636.E 6TH TRIP REPL | PRP.2636.E 6TH ST REPL | 444099.44 | 417982.34 | 26117.1 | 6.248% | 1.017% | 444099.44 | 417982.34 | 26117.1 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.35695 | PRP.2737.Har.Cane Run 2014 | PRP.2737.Har.Cane Run 2014 | 701626.65 | 477460.6 | 224166.05 | 46.95% | 1.607% | 701626.65 | 477460.6 | 224166.05 | 2013-10-01 | 2014-09-30 | 2013-10-02 | 10 | 2014-09-30 | 9
| 050.35700 | 050.2736.Dawson Spr Rd Ext | Install 550 fet of 2 inch pe main for two customers requesting natural gas | 2097.32 | 4860.75 | -2763.43 | -56.85% | 0.004804% | 2097.32 | 4860.75 | -2763.43 | 2013-10-01 | 2014-09-30 | 2013-10-28 | 10 | 2014-09-28 | 9
| 050.35714 | 050.2637.Commerce Dr Rev Ext | Install 925 ft. 4 inch poly for one new industrial customer (Whitehall Industries) requesting natural gas. | 17807.82 | 11335.25 | 6472.57 | 57.1% | 0.04079% | 17807.82 | 11335.25 | 6472.57 | 2013-10-01 | 2014-09-30 | 2013-10-28 | 10 | 2014-09-28 | 9
| 050.35724 | 050.2636.Winning Colors Way 2 | Install 443 Ft 4 Inch PE to serve 20 residential lots, 4 Inch is being installed down the center of the development for future growth and demand. | 7904.03 | 9089.68 | -1185.65 | -13.04% | 0.01811% | 7904.03 | 9089.68 | -1185.65 | 2013-10-01 | 2014-09-30 | 2013-10-21 | 10 | 2014-09-28 | 9
| 050.35734 | 050.2636.PRP Crew Equipment | Purchase Squeeze off tools, Metrotech line locator, and ERX chart recorder for new PRP Crew. | 16803.3 | 14602.51 | 2200.79 | 15.07% | 0.03849% | 16803.3 | 14602.51 | 2200.79 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-09-30 | 9
| 050.35739 | 050.2609.Wells St. Charles | Rework St. Charles Wells | 1222574.73 | 1317457.69 | -94882.96 | -7.202% | 2.8% | 1222574.73 | 1317457.69 | -94882.96 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-09-30 | 9
| 050.35760 | 050.2634.Misc Eq. | Purchase Rotary Air Drill, 12" Line up tool, Boss3 Fusion Machine and replace 8 Ultra Leak Detectors. | 24882.77 | 22089.34 | 2793.43 | 12.65% | 0.057% | 24882.77 | 22089.34 | 2793.43 | 2013-10-01 | 2014-09-30 | 2013-10-28 | 10 | 2014-09-30 | 9
| 050.35762 | WMR for downtown and mall area | We are requesting 200 endpoints to set up up our Wireless Meter Reading in the Paducah downtown and Ky Oaks Mall areas. | 21434.67 | 32030.6 | -10595.93 | -33.08% | 0.0491% | 21434.67 | 32030.6 | -10595.93 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35763 | 2738.WAREHOUSE FENCE 2014 | REPLACE FENCE AROUND THE WAREHOUSE IN CAMPBELLSVILLE | 24121.22 | 24183.1 | -61.88 | -0.2559% | 0.05525% | 24121.22 | 24183.1 | -61.88 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35764 | 050.2637.Noble Rd Ext | Install 100 feet of two inch poly for one residential customer requesting service. | 2988.38 | 1665.93 | 1322.45 | 79.38% | 0.006845% | 2988.38 | 1665.93 | 1322.45 | 2013-10-01 | 2014-09-30 | 2013-11-18 | 11 | 2014-09-28 | 9
| 050.35780 | 050.2636.TRIP ST SYS IMP REPL | Install 2600 Ft of 6 Inch PE , 259 Ft 4 Inch PE and 220 Ft 2 Inch PE to replace aging pipe. | 390184.07 | 451231.73 | -61047.66 | -13.53% | 0.8938% | 390184.07 | 451231.73 | -61047.66 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.35790 | 2738.OLD COLUMBIA RD 2013 | INSTALL 900' OF 4" PE FOR 3 CUSTOMERS FROM A NEW LINE INSTALLED FOR MEADOW CRK RD | 7039.75 | 7366.34 | -326.59 | -4.434% | 0.01613% | 7039.75 | 7366.34 | -326.59 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | PRP.2735.Horse Cav.Cherry-Maple-Bedford 2014 | 185021.13 | 420919.56 | -235898.43 | -56.04% | 0.4238% | 185021.13 | 420919.56 | -235898.43 | 2013-10-01 | 2014-09-30 | 2013-09-30 | 9 | 2014-10-01 | 10
| 050.35800 | 050.2634.Gainsway Dr. | Install 1320 ft 2 Inch PE to serve 26 residential lots. | 10096.59 | 7332.63 | 2763.96 | 37.69% | 0.02313% | 10096.59 | 7332.63 | 2763.96 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-09-28 | 9
| 050.35827 | 050.2634.University Circle 2 | Install 443 ft 2 Inch PE to serve 7 residential customers | 3800.22 | 3817.03 | -16.81 | -0.4404% | 0.008705% | 3800.22 | 3817.03 | -16.81 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-09-28 | 9
| 050.35840 | 050.2636.Challenger Center 3 | Install 200 ft 2 Inch PE to serve 2 commercial customers | 3654.5 | 3359.12 | 295.38 | 8.793% | 0.008371% | 3654.5 | 3359.12 | 295.38 | 2013-10-01 | 2014-09-30 | 2013-11-04 | 11 | 2014-09-28 | 9
| 050.35843 | 050.2638.Torian Cr Relocate | Relocate app. 1,160 feet of 2 inch poly main due to Ky Transportation Cabinet improvements to the bridge | 2738.15 | 22080.05 | -19341.9 | -87.6% | 0.006272% | 2738.15 | 22080.05 | -19341.9 | 2013-10-01 | 2014-09-30 | 2013-11-18 | 11 | 2014-09-28 | 9
| 050.35853 | 050.2636.Hwy 951 | Install 360 ft 2 Inch PE to serve 1 residential customer | 2232.3 | 2286.67 | -54.37 | -2.378% | 0.005113% | 2232.3 | 2286.67 | -54.37 | 2013-10-01 | 2014-09-30 | 2013-11-15 | 11 | 2014-09-28 | 9
| 050.35856 | ERX's for use in Graves County | 4 ERX's to be installed as follows; Wingo TBS, Sedalia Rd TBS, Symsonia TBS, & Pryorsburg TBS | 18364.45 | 18293.88 | 70.57 | 0.3858% | 0.04207% | 18364.45 | 18293.88 | 70.57 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35858 | PRP.2734.BG-11TH & ELM ST | PRP.2734.BG-11TH & ELM ST | 457911.44 | 85039.34 | 372872.1 | 438.5% | 1.049% | 457911.44 | 85039.34 | 372872.1 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35859 | PRP.2734.OLD LVILLE RD TO RED | PRP.2734.OLD LVILLE RD TO RED | 326526.96 | 114299.19 | 212227.77 | 185.7% | 0.7479% | 326526.96 | 114299.19 | 212227.77 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35860 | 050.2734.SpringfieldSub VII-D | 2 inch PE Ext. - Springfield Sub. VII-D to serve 34 new lots | 7731.36 | 13797.87 | -6066.51 | -43.97% | 0.01771% | 7731.36 | 13797.87 | -6066.51 | 2013-10-01 | 2014-09-30 | 2013-09-12 | 9 | 2013-12-30 | 12
| 050.35862 | 050.2636.Summer Valley 2 | Install 555 ft 2 Inch PE to serve 6 residential lots | 3222.74 | 4466.32 | -1243.58 | -27.84% | 0.007382% | 3222.74 | 4466.32 | -1243.58 | 2013-10-01 | 2014-09-30 | 2013-11-11 | 11 | 2014-09-28 | 9
| 050.35882 | 050.2637.Royal Park Estates | Install 2,040 ft for new residential subdivision. Extension makes gas available to 8 existing homes, 3 vacant lots, two homes under construction, & one existing church | 27396.2 | 10321.68 | 17074.52 | 165.4% | 0.06275% | 27396.2 | 10321.68 | 17074.52 | 2013-10-01 | 2014-09-30 | 2013-11-11 | 11 | 2014-09-28 | 9
| 050.35899 | PRP.2634.S. Seminary St. | Replace 4 Inch Steel low pressure bare main with 2056 Ft of 2 Inch PE IP Main. Approximately 50 customers involved. | 146339.43 | 137126.81 | 9212.62 | 6.718% | 0.3352% | 146339.43 | 137126.81 | 9212.62 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-09-28 | 9
| 050.35934 | 2739.LOCUST CREEK 10a 2014 | INSTALL XXXX OF 4" PE THIS WILL CONNECT LOCUST CREEK WITH NOTTING HILLS AND CREATE A TWO WAY FEED FOR THIS POPULATED AREA | 4522.17 | 7036.14 | -2513.97 | -35.73% | 0.01036% | 4522.17 | 7036.14 | -2513.97 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.35935 | 2739.HP.HCA.CARDINAL CLUB | INSTALL 1012' OF 8" 0.250 WALL PIPE TO HAVE THIS SECTION UNDER TRANSMISSION LINE AND BE HP DISTRIBUTION IN THE HCA AREA OF THE CLUB HOUSE AT CARDINAL CLUB | 385518.24 | 593395.7 | -207877.46 | -35.03% | 0.8831% | 385518.24 | 593395.7 | -207877.46 | 2013-10-01 | 2014-09-30 | 2013-12-01 | 12 | 2014-12-01 | 12
| 050.35961 | 2735.MUN.HWY 31W RELOCATE | RELOCATE 4" PE ON 31W AT THE I-65 INTERCHANGE. HWY DEPT REBUILDING INTERCHANGE ON AND OFF RAMPS | 132933.22 | 154620.15 | -21686.93 | -14.03% | 0.3045% | 132933.22 | 154620.15 | -21686.93 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-11-01 | 11
| 050.35962 | 2739.TRANS RETIRE.CARD CLUB | RETIRE 1000' OF EXISTING TRANSMISSION LINE IN CARDINAL CLUB AT THE CLUB HOUSE AND REPLACE WITH HP 8" THICK WALL PIPE. THIS IS FOR RETIREMENT ONLY | 36725.41 | 42110.13 | -5384.72 | -12.79% | 0.08412% | 36725.41 | 42110.13 | -5384.72 | 2013-10-01 | 2014-09-30 | 2013-12-01 | 12 | 2014-12-01 | 12
| 050.35967 | 050.2602.Replace Itrons 1 | Replace aging Itron Meter reading devices. | 93706.38 | 89219.99 | 4486.39 | 5.028% | 0.2146% | 93706.38 | 89219.99 | 4486.39 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.35970 | PRP.2736.Hville-W Side South | PRP.2736.Hville W Side South | 606197.42 | 727947.71 | -121750.29 | -16.73% | 1.389% | 606197.42 | 727947.71 | -121750.29 | 2013-10-01 | 2014-09-30 | 2013-10-10 | 10 | 2015-01-30 | 1
| 050.36031 | 2737.OFFICE REMODELING 2014 | REMODEL THE OFFICE TO ADD OFFICE FOR VISITORS AND FOR THE CP, MIC TECHS AND FCC. ALSO REMODEL OF THE KITCHEN AREA. | 67847.76 | 38805.28 | 29042.48 | 74.84% | 0.1554% | 67847.76 | 38805.28 | 29042.48 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36032 | 2737.FURN-APPLIANCE 2014 | INSTALL NEW APPLIANCES AND FURNITURE FOR REMODEL OF OFFICES AND KITCHEN | 45297.56 | 55987.46 | -10689.9 | -19.09% | 0.1038% | 45297.56 | 55987.46 | -10689.9 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36058 | 050.2636.Millers Mill Rd. | Install 300 Ft 3/4 Inch Steell 1 MT Deason Farm Tap and 2080 ft 2 Inch PE to serve 10 residential customers | 23630.41 | 18634.5 | 4995.91 | 26.81% | 0.05413% | 23630.41 | 18634.5 | 4995.91 | 2013-10-01 | 2014-09-30 | 2013-11-20 | 11 | 2014-09-28 | 9
| 050.36059 | 050.2609.Misc EQ. | Purchase DP4-Leak Machine and Hickory Bush Hog , Retire Bush Hog | 20924.01 | 20095.67 | 828.34 | 4.122% | 0.04793% | 20924.01 | 20095.67 | 828.34 | 2013-10-01 | 2014-09-30 | 2013-12-10 | 12 | 2014-11-28 | 11
| 050.36061 | 050.2609.Rectifier & Pumps | Change out Rectifier at Grand view Storage and install Methanol pumps at Hickory. | 10237.72 | 20854.8 | -10617.08 | -50.91% | 0.02345% | 10237.72 | 20854.8 | -10617.08 | 2013-10-01 | 2014-09-30 | 2013-12-10 | 12 | 2014-09-28 | 9
| 050.36071 | 2738.W WALNUT ST RELO 2014 | REPLACE 1-1/4" STEEL MAIN TO BE ABLE TO LOWER DUE TO McDONALDS ADDING DRIVE THROUGH LANE | 4406.09 | 1883.35 | 2522.74 | 133.9% | 0.01009% | 4406.09 | 1883.35 | 2522.74 | 2013-10-01 | 2014-09-30 | 2013-12-04 | 12 | 2014-12-04 | 12
| 050.36074 | 2737.MINOR DRIVE.2014 | INSTALL 350' OF 4" HP STEEL LINE TO SERVE TWO LOTS ON MINOR DRIVE | 7874.12 | 5496.39 | 2377.73 | 43.26% | 0.01804% | 7874.12 | 5496.39 | 2377.73 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.36107 | KY Kinder Morgan ROC Cont | Kinder Morgan Purchase Station ROC Controllers for Kentucky | 70485.52 | 56126.59 | 14358.93 | 25.58% | 0.1615% | 70485.52 | 56126.59 | 14358.93 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-05-01 | 5
| 050.36109 | ECAT Replacement KY | ECAT Replacement for KY Div 009 | 38575.47 | 53041.48 | -14466.01 | -27.27% | 0.08836% | 38575.47 | 53041.48 | -14466.01 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-04-01 | 4
| 050.36113 | Electronic Correctors KY | Electronic Correctors for Kentucky | 14702.75 | 34518.05 | -19815.3 | -57.41% | 0.03368% | 14702.75 | 34518.05 | -19815.3 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-10-01 | 10
| 050.36117 | Emergency Regulators KY | Emergency Regulators for Kentucky | 1778.7 | 31904.24 | -30125.54 | -94.42% | 0.004074% | 1778.7 | 31904.24 | -30125.54 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-09-01 | 9
| 050.36119 | Habit Purchase Heater KY | Habit Purchase Indirect Heater KY | 162204.1 | 141587.83 | 20616.27 | 14.56% | 0.3715% | 162204.1 | 141587.83 | 20616.27 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-10-01 | 10
| 050.36120 | Large Com/Indus Meter KY | Large commercial and industrial meter | 1909.16 | 22930.23 | -21021.07 | -91.67% | 0.004373% | 1909.16 | 22930.23 | -21021.07 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-02-01 | 2
| 050.36121 | ROC Upgrades KY | ROC Upgrades for Kentucky | 39490.98 | 23747.27 | 15743.71 | 66.3% | 0.09046% | 39490.98 | 23747.27 | 15743.71 | 2013-10-01 | 2014-09-30 | 2013-12-09 | 12 | 2014-07-01 | 7
| 050.36132 | PRP.2734.B.G.-Auburn 2014 | PRP.2734.B.G.-Auburn 2014 | 320206.17 | 450096.88 | -129890.71 | -28.86% | 0.7335% | 320206.17 | 450096.88 | -129890.71 | 2013-10-01 | 2014-09-30 | 2013-10-14 | 10 | 2014-09-30 | 9
| 050.36154 | 050.2636.Retire Air Compressor | Retire unit # 5646 Gimmer Schmidt Air Compressor | 66.32 | -3.6 | 69.92 | -1942% | 0.0001519% | 66.32 | -3.6 | 69.92 | 2013-10-01 | 2014-09-30 | 2013-12-13 | 12 | 2014-09-28 | 9
| 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | INSTALL 5270ft OF 2in PE ON GREEN AND MAIN STREETS | 419490.51 | 357169.26 | 62321.25 | 17.45% | 0.9609% | 419490.51 | 357169.26 | 62321.25 | 2013-10-01 | 2014-09-30 | 2013-10-02 | 10 | 2014-09-30 | 9
| 050.36196 | Tractor retirement | This project is for capturing the proceeds (-$500) for the retirement/ sale of unit number 5133, a John Deere model 401-D tractor including bushog attachment. | -2057.75 | -500 | -1557.75 | 311.6% | -0.004714% | -2057.75 | -500 | -1557.75 | 2013-10-01 | 2014-09-30 | 2013-12-17 | 12 | 2014-03-01 | 3
| 050.36198 | Sensit purchase | This project is for the purchase of (7) Sensit Gold units and (3) Track-It III units. This equipment is for use in the Paducah area. | 16672.32 | 15677.61 | 994.71 | 6.345% | 0.03819% | 16672.32 | 15677.61 | 994.71 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2013-11-30 | 11
| 050.36207 | 050.2602.GPS Modems | Purchase GPS Modems fo Trucks | 82165.27 | 95952 | -13786.73 | -14.37% | 0.1882% | 82165.27 | 95952 | -13786.73 | 2013-10-01 | 2014-09-30 | 2013-12-22 | 12 | 2014-09-28 | 9
| 050.36212 | 050.2734.Equipment FY2014 | Equipment Purchase - Bowling Green -- FY 2014 Approved Capital Budget Item 1 - 6 inch BT Machine, 1 - Electrufusion Machine, 7 - Sensit Units, 1- Odorometer, 1- Line locator for Russellville, 1- RMLD unit for Russellville | 66336.82 | 72368.94 | -6032.12 | -8.335% | 0.152% | 66336.82 | 72368.94 | -6032.12 | 2013-10-01 | 2014-09-30 | 2013-12-26 | 12 | 2014-09-30 | 9
| 050.36237 | 050.2736.Linneth Dr Ext | Install 130 ft of 2 inch poly for one residential customer requesting natural gas service. | 1980.96 | 1085.62 | 895.34 | 82.47% | 0.004538% | 1980.96 | 1085.62 | 895.34 | 2013-10-01 | 2014-09-30 | 2014-01-16 | 1 | 2014-09-28 | 9
| 050.36253 | 050.2636.Sensit Gold G-2 | Purchase 17-Sensit Gold G-2's and retire 17- Sensit Golds | 31316.47 | 25901.31 | 5415.16 | 20.91% | 0.07173% | 31316.47 | 25901.31 | 5415.16 | 2013-10-01 | 2014-09-30 | 2014-01-05 | 1 | 2014-09-28 | 9
| 050.36254 | 050.2609.Track-It-3 | Purchase 8-Track-it 3 leak detectors, retire 8 Sensit Golds | 12897.33 | 10678.98 | 2218.35 | 20.77% | 0.02954% | 12897.33 | 10678.98 | 2218.35 | 2013-10-01 | 2014-09-30 | 2014-01-05 | 1 | 2014-09-28 | 9
| 050.36263 | 050.2636.Retire Truck 5947 | Retire Ford Truck unit # 5947 Vin #1995 FORD Flatbed Truck; Diesel; 5/2SPD Rear End; 11' Flatbed vin#:1FDNF70J9SVA04815 odo reads:56274 | -7092.86 | -7194.18 | 101.32 | -1.408% | -0.01625% | -7092.86 | -7194.18 | 101.32 | 2013-10-01 | 2014-09-30 | 2014-01-03 | 1 | 2014-09-28 | 9
| 050.36266 | Retire trailer - Mayfield | Retire trailer, unit #7029 a 1979 model dump trailer. Unit was sold at auction for $892.00 | -967.5 | 0 |  |  | -0.002216% | -967.5 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2014-01-03 | 1 | 2014-04-03 | 4
| 050.36268 | Sensit purchase - Princeton | This project is for the replacement of 4 Sensit Gold units with the new Sensit G-2 units in Princeton, KY | 7323.24 | 6052.22 | 1271.02 | 21% | 0.01677% | 7323.24 | 6052.22 | 1271.02 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2013-11-30 | 11
| 050.36277 | Land for Paducah office | This project is to capture the costs associated with the purchase of a 3.68 acre site at 3510 Coleman Road. this tract is the home of the proposed new Paducah, KY office. | 138339.3 | 191254.2 | -52914.9 | -27.67% | 0.3169% | 138339.3 | 191254.2 | -52914.9 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.36279 | 050.2638.S 6th St Retire | Retire app. 80 feet of 2 inch steel main. The only home being served is being torn down, parking lot going up. | 534.43 | 852 | -317.57 | -37.27% | 0.001224% | 534.43 | 852 | -317.57 | 2013-10-01 | 2014-09-30 | 2014-01-07 | 1 | 2014-09-28 | 9
| 050.36287 | PRP.2609.Fruithill 4 Inch PE | replace approximately 7900 Ft of 4 Inch Bare Steel with 4 Inch High Density PE. | 431232.75 | 480743.64 | -49510.89 | -10.3% | 0.9878% | 431232.75 | 480743.64 | -49510.89 | 2013-10-01 | 2014-09-30 | 2014-01-15 | 1 | 2014-11-15 | 11
| 050.36288 | New Paducah Office | This project is for the building of a structure, the new Paducah, KY office located at 3510 Coleman Road | 1564026.12 | 1362000 | 202026.12 | 14.83% | 3.583% | 1564026.12 | 1362000 | 202026.12 | 2013-10-01 | 2014-09-30 | 2014-03-01 | 3 | 2014-11-30 | 11
| 050.36301 | 050.2634.Tyson Boiler | Install Boiler at Tyson Foods | 99028.87 | 116757.23 | -17728.36 | -15.18% | 0.2268% | 99028.87 | 116757.23 | -17728.36 | 2013-10-01 | 2014-09-30 | 2014-01-20 | 1 | 2014-09-28 | 9
| 050.36302 | PRP.2737.HAR.GREENBR SUB 2014 | INSTALL 7700ft OF 2iN PE IN GREEBRIAR SUBDIVISION | 316146.41 | 770435.2 | -454288.79 | -58.97% | 0.7242% | 316146.41 | 770435.2 | -454288.79 | 2013-10-01 | 2014-09-30 | 2013-09-26 | 9 | 2014-10-01 | 10
| 050.36303 | PRP.2738.GRN.W COL AVE 2014 | INSTALL 3110ft OF 2in PE ON WEST COLUMBIA AVE | 247361.2 | 311198.5 | -63837.3 | -20.51% | 0.5666% | 247361.2 | 311198.5 | -63837.3 | 2013-10-01 | 2014-09-30 | 2013-10-02 | 10 | 2014-09-30 | 9
| 050.36304 | 2737.SCBA - FOR EMERGENCY | PURCHASE 3 SCOTT SCBA AIR UNITS FOR DANVILLE OPERATIONS | 5335.72 | 5088.8 | 246.92 | 4.852% | 0.01222% | 5335.72 | 5088.8 | 246.92 | 2013-10-01 | 2014-09-30 | 2013-10-02 | 10 | 2013-11-30 | 11
| 050.36306 | ERX project - Hopkinsville | This project is for the purchase of two ERX's for use in the Hopkinsville area. One will be located in Commerce Park, the other unit will be placed at a yet determined site to on the Hopkinsville low pressure system. | 9034.64 | 7544.83 | 1489.81 | 19.75% | 0.02069% | 9034.64 | 7544.83 | 1489.81 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36307 | Sensits - Hopkinsville | This project is for the purchse of 5 new Sensit G2 models and 1 Track-It III detector for use in the Hopkinsville area, we are trading in 6 old Sensit units. | 11115.22 | 9016.26 | 2098.96 | 23.28% | 0.02546% | 11115.22 | 9016.26 | 2098.96 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | INSTALL 3375ft OF 2in PE ON DEPOT STREET | 84923.75 | 343251.89 | -258328.14 | -75.26% | 0.1945% | 84923.75 | 343251.89 | -258328.14 | 2013-10-01 | 2014-09-30 | 2013-10-04 | 10 | 2014-11-30 | 11
| 050.36324 | 2014 Equipment - Mayfield | This project is to capture the costs for equipment purchases for Mayfield, KY. These items include pipe locators, Wmson equip, Mueller equip, E.F equip, & Sensit G2 purchases. | 78146.76 | 77017.2 | 1129.56 | 1.467% | 0.179% | 78146.76 | 77017.2 | 1129.56 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.36349 | 2739.RONNIE LN REG ST SUPPLY | REPLACE THE INLET 3/4" LINE WITH 2" STEEL FOR RONNIE LANE REG STATION | 9374.32 | 9413.03 | -38.71 | -0.4112% | 0.02147% | 9374.32 | 9413.03 | -38.71 | 2013-10-01 | 2014-09-30 | 2014-01-13 | 1 | 2015-01-13 | 1
| 050.36367 | Equipment Purchase - Princeton | This project is to capture the costs associated with equipment purchases in Princeton, KY. Items to be purchased include a hammer drill, a generator, and a pressure washer. | 2904.87 | 2609.59 | 295.28 | 11.32% | 0.006654% | 2904.87 | 2609.59 | 295.28 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.36371 | 050.2609.Mueller Truck | Project created for the purchase of New Mueller Truck. | 157246.69 | 166487.4 | -9240.71 | -5.55% | 0.3602% | 157246.69 | 166487.4 | -9240.71 | 2013-10-01 | 2014-09-30 | 2014-01-20 | 1 | 2014-11-30 | 11
| 050.36378 | PRP.2737.E FACTORY-BARE JT | REPLACE 4" ST BARE JOINT AND 2" STEEL BARE JOINT ON EAST FACTORY STREET AND NORTH GREENVILLE STREET | 294770.3 | 131431.43 | 163338.87 | 124.3% | 0.6752% | 294770.3 | 131431.43 | 163338.87 | 2013-10-01 | 2014-09-30 | 2014-01-08 | 1 | 2015-01-08 | 1
| 050.36380 | 2739.CLOVERBROOK 9a 2014 | INSTALL XXX OF 2" PE TO SERVE 21 LOTS IN CLOVERBROOK | 11169.68 | 9738.87 | 1430.81 | 14.69% | 0.02559% | 11169.68 | 9738.87 | 1430.81 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
| 050.36386 | 050.2734.Swanee Trail 2 inch | 300 ft. of 2 inch PE to serve three customers | 1971.61 | 4043.35 | -2071.74 | -51.24% | 0.004516% | 1971.61 | 4043.35 | -2071.74 | 2013-10-01 | 2014-09-30 | 2014-01-14 | 1 | 2015-05-15 | 5
| 050.36387 | PRP.2734.BG-Coll-10th to 13th | PRP.2734.BG-Coll-10th to 13th | 469471.87 | 247075.12 | 222396.75 | 90.01% | 1.075% | 469471.87 | 247075.12 | 222396.75 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2015-03-31 | 3
| 050.36416 | 2737.BONTA LN 2014 | INSTALL 185' OF 2" PE TO SERVE ONE CUSTOMER | -15.27 | 1458.1 | -1473.37 | -101% | -3.498e-05% | -15.27 | 1458.1 | -1473.37 | 2013-10-01 | 2014-09-30 | 2014-02-01 | 2 | 2015-02-01 | 2
| 050.36417 | 2737.FURN ST 2014 | INSTALL 150' OF 2" PE ON FERN STREET FROM DILLEHAY STREET FOR ONE COMMERICAL CUSTOMER | 2243.25 | 821.82 | 1421.43 | 173% | 0.005138% | 2243.25 | 821.82 | 1421.43 | 2013-10-01 | 2014-09-30 | 2013-12-01 | 12 | 2014-12-01 | 12
| 050.36427 | Paducah Equip Purchases | This project is for equipment purchases for the Paducah area including Ditch Witch Locator, 6 inch fusing equipment, Mueller tapping equipment, Jackhammer, DC Electro-fuse, & 2 inch squeeze-offs. | 86397.13 | 75146.28 | 11250.85 | 14.97% | 0.1979% | 86397.13 | 75146.28 | 11250.85 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2013-11-30 | 11
| 050.36428 | 050.2634.Genevieve Dr. | Install 100 Ft 2 Inch PE to serve 1 residential customer | 2145.09 | 3424.93 | -1279.84 | -37.37% | 0.004914% | 2145.09 | 3424.93 | -1279.84 | 2013-10-01 | 2014-09-30 | 2014-01-20 | 1 | 2014-09-28 | 9
| 050.36475 | 2734.TRENCHER-WALK W/TRAILER | DITCH WITCH TRENCHER - WALK BEHIND WITH TRAILER | 22648.19 | 21481.5 | 1166.69 | 5.431% | 0.05188% | 22648.19 | 21481.5 | 1166.69 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36478 | 2734.BG.FRAN.MADISON REG REP | REPLACE THE REGULATORS ON THE REGUALTOR STATION IN FRANKLIN ON MADISON AVE. | 10279.06 | 14298.69 | -4019.63 | -28.11% | 0.02355% | 10279.06 | 14298.69 | -4019.63 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36511 | 050.2609.St Charles Building | Project for construction of new building at St. Charles | 85727.13 | 90000 | -4272.87 | -4.748% | 0.1964% | 85727.13 | 90000 | -4272.87 | 2013-10-01 | 2014-09-30 | 2014-02-01 | 2 | 2014-09-28 | 9
| 050.36519 | 050.2734.North-South2inchRep | Replace 2 inch stl. main- North-South Corridor -OldLouisville Rd. | 1544.27 | 13.31 | 1530.96 | 11502% | 0.003537% | 1544.27 | 13.31 | 1530.96 | 2013-10-01 | 2014-09-30 | 2013-12-03 | 12 | 2014-09-28 | 9
| 050.36522 | PRP.2636.PARRISH AVE NORTH | Replace approximately 19801 Ft of Bare LP Steel main with approximately 14071 ft IP 2 InchPE , 3924 Ft IP 6 Inch PE and 1806 Ft IP 4 Inch PE.. There are approximately 365 residential services involved and 43 commercial services. | 604813.88 | 1178822.63 | -574008.75 | -48.69% | 1.385% | 604813.88 | 1178822.63 | -574008.75 | 2013-10-01 | 2014-09-30 | 2013-10-09 | 10 | 2015-03-30 | 3
| 050.36528 | 050.2609.St. Charles Furniture | Project is to purchase furniture for the new St. Charles Building. | 11079.86 | 7109.04 | 3970.82 | 55.86% | 0.02538% | 11079.86 | 7109.04 | 3970.82 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2014-09-28 | 9
| 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | RELOCATE 280' OF 4" HP STEEL FOR STATE RAOD PROJECT - NO REIMBURSABLE | 52051.05 | 102136.48 | -50085.43 | -49.04% | 0.1192% | 52051.05 | 102136.48 | -50085.43 | 2013-10-01 | 2014-09-30 | 2014-02-01 | 2 | 2015-03-13 | 3
| 050.36577 | Replace ground bed - G.R | This project is to capture costs associated with the replacement of our Grand Rivers, KY ground bed. This ground bed and rectifier are located on the south side of Commerce Drive near Patti's restaurant. | 18276.12 | 8460.22 | 9815.9 | 116% | 0.04186% | 18276.12 | 8460.22 | 9815.9 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-28 | 9
| 050.36598 | 2738.CHERYL LN RETIRE 1-1/4" | RETIRE 312' OF 1-1/4" PE THAT WAS DAMAGED AND SERVICES NO CUSTOMERS - INSTALLED 1983 | 764.16 | 1193.77 | -429.61 | -35.99% | 0.00175% | 764.16 | 1193.77 | -429.61 | 2013-10-01 | 2014-09-30 | 2014-02-05 | 2 | 2014-09-30 | 9
| 050.36611 | PRP.2735.MUN.E UNION ST 2014 | INSTALL 1875fT OF 2in PE ON EAST UNION STREET | 82732.29 | 141792.06 | -59059.77 | -41.65% | 0.1895% | 82732.29 | 141792.06 | -59059.77 | 2013-10-01 | 2014-09-30 | 2013-10-04 | 10 | 2014-09-30 | 9
| 050.36614 | 2738.LAND. NEW OFFICE 2014 | PURCHASE OF LAND FOR THE NEW CAMPBELLSVILLE OFFICE | 100071.29 | 110000 | -9928.71 | -9.026% | 0.2292% | 100071.29 | 110000 | -9928.71 | 2013-10-01 | 2014-09-30 | 2014-03-01 | 3 | 2014-03-31 | 3
| 050.36618 | 2738.OFFICE BUILDING 2014 | PURCHASE OFFICE BUILDING FOR CAMPBELLSVILLE | 862543.6 | 690000 | 172543.6 | 25.01% | 1.976% | 862543.6 | 690000 | 172543.6 | 2013-10-01 | 2014-09-30 | 2014-04-01 | 4 | 2014-10-31 | 10
| 050.36619 | 2738.FURNITURE 2014 | PURCHASE NEW FURNITURE FOR OFFICE 2014 | 11688 | 15000 | -3312 | -22.08% | 0.02677% | 11688 | 15000 | -3312 | 2013-10-01 | 2014-09-30 | 2014-07-01 | 7 | 2015-03-30 | 3
| 050.36649 | PRP.2734.Gayle at Normalview | Replace 55 ft. of 2 inch Bare stell Main | 1661.28 | 7662.19 | -6000.91 | -78.32% | 0.003805% | 1661.28 | 7662.19 | -6000.91 | 2013-10-01 | 2014-09-30 | 2014-02-06 | 2 | 2014-09-28 | 9
| 050.36655 | PRP.2735.MUN.MILL ST 2014 | INSTALL 3330' OF 2" PE PIPE TO REPLCAE BARE PIPE ON MILL STREET IN MUNFORDVILLE - 15 SERVICES | 128638.39 | 180214.35 | -51575.96 | -28.62% | 0.2947% | 128638.39 | 180214.35 | -51575.96 | 2013-10-01 | 2014-09-30 | 2014-01-01 | 1 | 2015-01-01 | 1
| 050.36677 | Retire Gator | This project is for the retiring of our 2008 John Deere Model 620i Gator Unit #50048. A new gator has been purchased for use in Paducah. | -3544.35 | 0 |  |  | -0.008119% | -3544.35 | Non Budgeted |  | 2013-10-01 | 2014-09-30 | 2014-02-14 | 2 | 2014-09-28 | 9
| 050.36688 | 2738.SUM.PURCH ST REG REPLACE | REPLACE REGULATORS AT SUMMERSVILLE PURCHASE STATION | 9195.78 | 30884.59 | -21688.81 | -70.23% | 0.02106% | 9195.78 | 30884.59 | -21688.81 | 2013-10-01 | 2014-09-30 | 2014-05-01 | 5 | 2015-05-01 | 5
| 050.36696 | 050.2634.Robards TB Station | Replace Robarbs Town Border Station ageing Station with leakage and dated regs. and valves that are not serviceable. | 130924.69 | 146685.57 | -15760.88 | -10.74% | 0.2999% | 130924.69 | 146685.57 | -15760.88 | 2013-10-01 | 2014-09-30 | 2014-02-01 | 2 | 2014-10-28 | 10
| 050.36708 | PRP.2737.N MAIN.PRICE 2014 | INSTALL 1700' OF 6" PE AND 1050' OF 2" PE TO REPLACE 4150' OF BARE STEEL PIPE | 486960.57 | 374542.02 | 112418.55 | 30.01% | 1.115% | 486960.57 | 374542.02 | 112418.55 | 2013-10-01 | 2014-09-30 | 2014-03-01 | 3 | 2015-03-01 | 3
| 050.36740 | 050.2637.Chappell Rd Rev Ext | Install 265 feet of 2 inch poly pipe for one new customer requesting natural gas | 4028.36 | 2006.5 | 2021.86 | 100.8% | 0.009227% | 4028.36 | 2006.5 | 2021.86 | 2013-10-01 | 2014-09-30 | 2014-03-24 | 3 | 2014-09-28 | 9
| 050.36742 | 050.2636.Middleground Dr. | Install 197' 2" PE to serve 2 residential customers | 2591.86 | 4224.03 | -1632.17 | -38.64% | 0.005937% | 2591.86 | 4224.03 | -1632.17 | 2013-10-01 | 2014-09-30 | 2014-04-01 | 4 | 2014-09-28 | 9
| 050.36765 | 2738.NOE_RD_CHICKEN_HOUSES | INSTALL 8000' OF 4 in PE TO SERVE 5 EXISTING CHICKEN HOUSES | 43654.45 | 49507.65 | -5853.2 | -11.82% | 0.1% | 43654.45 | 49507.65 | -5853.2 | 2013-10-01 | 2014-09-30 | 2014-02-01 | 2 | 2015-02-01 | 2
| 050.36776 | PRP.2736.Hville-W_Side_North | PRP.2736.Hopkinsville-West Side North | 371508.94 | 441006.96 | -69498.02 | -15.76% | 0.851% | 371508.94 | 441006.96 | -69498.02 | 2013-10-01 | 2014-09-30 | 2013-10-09 | 10 | 2015-01-30 | 1
| 050.36790 | 050.2636.Hwy 951 Phase 2 | Install 829 ft 2Inch PE to serve 1 residential customer | 6933.08 | 10923.28 | -3990.2 | -36.53% | 0.01588% | 6933.08 | 10923.28 | -3990.2 | 2013-10-01 | 2014-09-30 | 2014-04-25 | 4 | 2014-09-28 | 9
| 050.36799 | 2737.DAN.ERX INSTALLATION | PURCHASE 3 ERX's FOR REPLACING CHARTS IN TEH DANVILLE OPERATIONS | 12436.74 | 29827.38 | -17390.64 | -58.3% | 0.02849% | 12436.74 | 29827.38 | -17390.64 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36801 | 2738.GRNBURG.CAMP-RECTIFIER | INSTALL NEW RECTIFIER IN GREENSBURG | 14610.24 | 47902.59 | -33292.35 | -69.5% | 0.03347% | 14610.24 | 47902.59 | -33292.35 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.36850 | 050.2736.8 Inch Improvement | Install approximaately 30000 Ft of 8 Inch Steel pipe for reinforcement to the Industrial Park. | 5436044.94 | 6639868.23 | -1203823.29 | -18.13% | 12.45% | 5436044.94 | 6639868.23 | -1203823.29 | 2013-10-01 | 2014-09-30 | 2014-02-20 | 2 | 2014-11-30 | 11
| 050.36878 | PRP.2734.BG-Normal to Regents | PRP.2734.BG-Normal to Regents & Offset | 155796.42 | 280654.79 | -124858.37 | -44.49% | 0.3569% | 155796.42 | 280654.79 | -124858.37 | 2013-10-01 | 2014-09-30 | 2013-10-23 | 10 | 2014-09-30 | 9
| 050.36898 | PRP.2734.South Way Replc. | Replace 2 inch bare steel - South Way | 991.57 | 8039.75 | -7048.18 | -87.67% | 0.002271% | 991.57 | 8039.75 | -7048.18 | 2013-10-01 | 2014-09-30 | 2014-03-12 | 3 | 2014-09-28 | 9
| 050.36902 | 050.2734.Hwy31W Public Imprv | University Blvd. and Hwy 31W Roundabout - State Hwy Reloc. | 926.74 | -0.02 | 926.76 | -4633800% | 0.002123% | 926.74 | -0.02 | 926.76 | 2013-10-01 | 2014-09-30 | 2014-02-17 | 2 | 2014-09-28 | 9
| 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | PRP.2734.BG-Oaklawn-Loving | 39294.75 | 330281.61 | -290986.86 | -88.1% | 0.09001% | 39294.75 | 330281.61 | -290986.86 | 2013-10-01 | 2014-09-30 | 2013-10-10 | 10 | 2014-09-30 | 9
| 050.37007 | 050.2634.College Dr. Reloc. | Relocate 128 ft 4 Inch Stl. for Roadway widening. | -2335.73 | 0.01 | -2335.74 | -23357400% | -0.00535% | -2335.73 | 0.01 | -2335.74 | 2013-10-01 | 2014-09-30 | 2014-05-01 | 5 | 2014-09-28 | 9
| 050.37008 | 050.2637.Royal Park 2 | Install 300 feet of 2 inch poly for two residential customers requesting service. | 2054.07 | 2325.49 | -271.42 | -11.67% | 0.004705% | 2054.07 | 2325.49 | -271.42 | 2013-10-01 | 2014-09-30 | 2014-04-14 | 4 | 2014-05-01 | 5
| 050.37016 | 050.2637.Ky Dam Rd Ext | Install 150' - 2" PE for one customer | 2568.99 | 1508.22 | 1060.77 | 70.33% | 0.005885% | 2568.99 | 1508.22 | 1060.77 | 2013-10-01 | 2014-09-30 | 2014-04-15 | 4 | 2014-05-15 | 5
| 050.37025 | 050.2636.Hill Bridge | Install 1100 ft 2 Inch PE to serve 4 residential customers | 7092.91 | 4987.26 | 2105.65 | 42.22% | 0.01625% | 7092.91 | 4987.26 | 2105.65 | 2013-10-01 | 2014-09-30 | 2014-05-01 | 5 | 2014-09-28 | 9
| 050.37031 | 050.2636.Sterling Park 2 | Install approximately 2091 Ft 2 Inch PE to serve 40 residential lots | 11629.92 | 12497.42 | -867.5 | -6.941% | 0.02664% | 11629.92 | 12497.42 | -867.5 | 2013-10-01 | 2014-09-30 | 2014-04-01 | 4 | 2014-09-28 | 9
| 050.37040 | 050.2734.Massey Springs III | 320 ft. - 2 inch Extension - Massey Springs III | 3957.59 | 5269.9 | -1312.31 | -24.9% | 0.009065% | 3957.59 | 5269.9 | -1312.31 | 2013-10-01 | 2014-09-30 | 2014-03-31 | 3 | 2014-09-28 | 9
| 050.37054 | 050.2734.2 inchExt.Cableas | 400 ft. 2 inch Ext. - Cabelsa off KenBale Blvd | 5115.82 | 8137.88 | -3022.06 | -37.14% | 0.01172% | 5115.82 | 8137.88 | -3022.06 | 2013-10-01 | 2014-09-30 | 2014-04-01 | 4 | 2014-09-28 | 9
| 050.37067 | 050.2636.Thompson Dr. | Install 560 ft. 2 Inch Pe to serve 1 residential lot | 5999.26 | 5171.35 | 827.91 | 16.01% | 0.01374% | 5999.26 | 5171.35 | 827.91 | 2013-10-01 | 2014-09-30 | 2014-06-20 | 6 | 2014-09-28 | 9
| 050.37077 | 050.2734.ThreeSprings II.Hwy | Three Springs II Public Improvement | 104079.95 | 182740.37 | -78660.42 | -43.04% | 0.2384% | 104079.95 | 182740.37 | -78660.42 | 2013-10-01 | 2014-09-30 | 2014-03-31 | 3 | 2014-09-28 | 9
| 050.37079 | 050.2636.Jones Rd. Relo. | Relocate 304 ft 2 Inch PE exposed in Ditch line. | 4556.13 | 5133.96 | -577.83 | -11.26% | 0.01044% | 4556.13 | 5133.96 | -577.83 | 2013-10-01 | 2014-09-30 | 2014-04-02 | 4 | 2014-05-01 | 5
| 050.37105 | 2738. WEST MARTIN 2014 | INSTALL 950' OF 2" PE ON WEST MARTIN ROAD SOUTHWEST FROM HWY 372 | 2833.03 | 2453.9 | 379.13 | 15.45% | 0.006489% | 2833.03 | 2453.9 | 379.13 | 2013-10-01 | 2014-09-30 | 2014-03-01 | 3 | 2015-03-01 | 3
| 050.37108 | 050.2637.Londonderry Ln Ext | Install 85 feet of 2 inch poly for one new residential customer | 4821.5 | 1172.63 | 3648.87 | 311.2% | 0.01104% | 4821.5 | 1172.63 | 3648.87 | 2013-10-01 | 2014-09-30 | 2014-04-14 | 4 | 2014-05-14 | 5
| 050.37118 | 050.2636.Sir Wren | Install 295 ft 2 Inch PE to serve 1 residential customer | 3765.79 | 5242.61 | -1476.82 | -28.17% | 0.008626% | 3765.79 | 5242.61 | -1476.82 | 2013-10-01 | 2014-09-30 | 2014-06-10 | 6 | 2014-09-28 | 9
| 050.37119 | 2739.THOROUGHBRED 2014 | INSTALL 350' OF 2" PE TO SERVE THOROUGHBRED | 2963.36 | 2901.52 | 61.84 | 2.131% | 0.006788% | 2963.36 | 2901.52 | 61.84 | 2013-10-01 | 2014-09-30 | 2013-11-01 | 11 | 2014-11-01 | 11
| 050.37132 | 050.2636.Middleground Dr.2 | Install 200 ft 2 Inch PE to serve 2 residential customers | 3809.35 | 4234.18 | -424.83 | -10.03% | 0.008726% | 3809.35 | 4234.18 | -424.83 | 2013-10-01 | 2014-09-30 | 2014-07-01 | 7 | 2014-09-28 | 9
| 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | REPLACE APPROXIMATLY 2000' OF 2" ALDYLA WITH 2" PE PIPE ON RUSSELL STREET - JUNCTION CITY | 16193.54 | 20649.3 | -4455.76 | -21.58% | 0.03709% | 16193.54 | 20649.3 | -4455.76 | 2013-10-01 | 2014-09-30 | 2014-04-10 | 4 | 2015-04-10 | 4
| 050.37154 | Install Infrared red heater | Replace boiler (leaking) at Pryorsburg Station with Hot Cat brand infrared heater | 35369.34 | 51622.76 | -16253.42 | -31.48% | 0.08102% | 35369.34 | 51622.76 | -16253.42 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2014-08-01 | 8
| 050.37169 | 2739.BOONE STAT 6 PE-SYS IMPR | INSTALL 6" PE ALONG BOONE STATION ROAD FROM SUMMIT DR TO MT VERNON DR - TO INCREASE FLOW TO SONOCO | 54715.65 | 53220.11 | 1495.54 | 2.81% | 0.1253% | 54715.65 | 53220.11 | 1495.54 | 2013-10-01 | 2014-09-30 | 2014-05-01 | 5 | 2015-05-01 | 5
| 050.37175 | Retire Trencher and Trailer | Retire 1994 Ditch Witch model 4010 trencher - Unit #05498 Retire 1991 Big Tex trailer - Unit #06468 | -7500 | -7500 | 0 | 0% | -0.01718% | -7500 | -7500 | 0 | 2013-10-01 | 2014-09-30 | 2014-04-15 | 4 | 2014-09-30 | 9
| 050.37185 | PRP.2635.Dawson Road Repl | Abandon 128 feet of two inch bare main in order to repair one grade II leak. Note, this project is actually completed. | 3601.72 | 3095.75 | 505.97 | 16.34% | 0.00825% | 3601.72 | 3095.75 | 505.97 | 2013-10-01 | 2014-09-30 | 2014-04-15 | 4 | 2014-06-01 | 6
| 050.37232 | 2738.NOE RD. SYS IMP 2014 | INSTALL 1100' OF 2" PE FOR SYSTEM IMPROVEMENT ON NOE ROAD | 4088.41 | 6665.6 | -2577.19 | -38.66% | 0.009365% | 4088.41 | 6665.6 | -2577.19 | 2013-10-01 | 2014-09-30 | 2014-04-15 | 4 | 2015-04-15 | 4
| 050.37233 | 2738.SALOMA RD 2014 | INSTALL 1040' OF 2" PE ON SALOMA ROAD | 1497.18 | 3670.68 | -2173.5 | -59.21% | 0.003429% | 1497.18 | 3670.68 | -2173.5 | 2013-10-01 | 2014-09-30 | 2014-04-15 | 4 | 2015-04-15 | 4
| 050.37250 | 050.2636.Bridgewood | Install 1686 ft 2 Inch PE to serve 14 residential lots | 11325.19 | 9815.13 | 1510.06 | 15.39% | 0.02594% | 11325.19 | 9815.13 | 1510.06 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2014-08-01 | 8
| 050.37255 | 2738.COMMONWEALTH -NEW OFFICE | INSTALL 1650' OF 4" PE IN INDUSTRIAL PARK FOR NEW OFFICE | 3869.37 | 14822.55 | -10953.18 | -73.9% | 0.008863% | 3869.37 | 14822.55 | -10953.18 | 2013-10-01 | 2014-09-30 | 2014-04-21 | 4 | 2015-04-21 | 4
| 050.37261 | 050.2635.Fox Road Rev Ext | Install 2,350 feet of 2 inch poly main forr one customer (Doug Brown) requesting natural gas service. | -6940.31 | 4895.26 | -11835.57 | -241.8% | -0.0159% | -6940.31 | 4895.26 | -11835.57 | 2013-10-01 | 2014-09-30 | 2014-05-15 | 5 | 2014-07-15 | 7
| 050.37296 | 050.2734.Sunnitt Phase IV | 4 inch and 2 inch PE Ext. - The Summitt Phase IV - B.B. | 17510.41 | 23165.19 | -5654.78 | -24.41% | 0.04011% | 17510.41 | 23165.19 | -5654.78 | 2013-10-01 | 2014-09-30 | 2014-03-24 | 3 | 2014-09-28 | 9
| 050.37301 | 2739.SVILLE.8th - COLLEGE LP | INSTALL IP MAIN TO REPLACE LP SYSTEM ON COLLEGE, 8th, 9th AND WASHINGTON | 49564.75 | 38918.57 | 10646.18 | 27.36% | 0.1135% | 49564.75 | 38918.57 | 10646.18 | 2013-10-01 | 2014-09-30 | 2012-02-01 | 2 | 2014-09-30 | 9
| 050.37312 | TDW Equipment | This project is to capture costs associated with the purchase of T.D Williamson tapping equipment to be purchased for use in the Paducah area. | 61380.46 | 49484.06 | 11896.4 | 24.04% | 0.1406% | 61380.46 | 49484.06 | 11896.4 | 2013-10-01 | 2014-09-30 | 2014-04-28 | 4 | 2014-06-30 | 6
| 050.37346 | 2739.FRIESIAN CT 2014 | INSTALL 350' OF 2" PE ON FRIESIAN CT TO SERVE 10 LOTS | 7404.78 | 6568.17 | 836.61 | 12.74% | 0.01696% | 7404.78 | 6568.17 | 836.61 | 2013-10-01 | 2014-09-30 | 2014-04-10 | 4 | 2015-04-10 | 4
| 050.37351 | 050.2634.Slaughters upgrade | Install 2214 ft 4 Inch HD PE, 56 ft 2 Inch PE and 1 2 Inch Reg Station to increase capacity due to new Grain Dryer | 65502.19 | 62262.85 | 3239.34 | 5.203% | 0.15% | 65502.19 | 62262.85 | 3239.34 | 2013-10-01 | 2014-09-30 | 2014-07-20 | 7 | 2014-09-28 | 9
| 050.37391 | 2739.BRUNERSTOWN RECT 2014 | REPLACE RECTICFIER ON BRUNERSTOWN RD IN SHELBYVILLE | 5514.55 | 18678.9 | -13164.35 | -70.48% | 0.01263% | 5514.55 | 18678.9 | -13164.35 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37407 | 050.2734.CalBastel 2 inch Ext | 200 ft. of 2 ich PE - Cal Bastel | 711.75 | 2130.18 | -1418.43 | -66.59% | 0.00163% | 711.75 | 2130.18 | -1418.43 | 2013-10-01 | 2014-09-30 | 2014-05-08 | 5 | 2014-09-28 | 9
| 050.37420 | 050.2637.Hansen Rd Rev-Ext | Install 490 feet of 2 inch PE main for one existing commercial customer (Faith Center of Paducah) | 1989.68 | 3127.09 | -1137.41 | -36.37% | 0.004558% | 1989.68 | 3127.09 | -1137.41 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2014-09-28 | 9
| 050.37425 | Ground Bed 45 S | This project is to replace our depleted ground bed on U.S Highway 45 South in Mayfield, KY | 9930.88 | 11584.56 | -1653.68 | -14.27% | 0.02275% | 9930.88 | 11584.56 | -1653.68 | 2013-10-01 | 2014-09-30 | 2014-06-03 | 6 | 2015-09-30 | 9
| 050.37445 | PRP.2635.Franklin Alley | Retire 465 feet of bare pipe in alley | 5514.06 | 1081.18 | 4432.88 | 410% | 0.01263% | 5514.06 | 1081.18 | 4432.88 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2014-07-01 | 7
| 050.37446 | PRP.2734.W.5th-S.Main Replc | 60 ft.-2 inch bare steel replc. - W5th-S.Main - Russ | 5224.92 | 3559.5 | 1665.42 | 46.79% | 0.01197% | 5224.92 | 3559.5 | 1665.42 | 2013-10-01 | 2014-09-30 | 2014-05-02 | 5 | 2014-09-28 | 9
| 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | INSTALL 1310ft OF 2in PE IN LANCASTER ON ELLIOT STREET - THIS WAS CALLED LEXINGTON ALLEY - ACTUALLY ELLIOT STREET | 100202.33 | 135880.55 | -35678.22 | -26.26% | 0.2295% | 100202.33 | 135880.55 | -35678.22 | 2013-10-01 | 2014-09-30 | 2013-10-03 | 10 | 2014-11-30 | 11
| 050.37534 | 050.2602.MDT XP Non Support | Replace 30 MDT's that no longer have Windows XP support | 111677.76 | 142725.32 | -31047.56 | -21.75% | 0.2558% | 111677.76 | 142725.32 | -31047.56 | 2013-10-01 | 2014-09-30 | 2014-05-25 | 5 | 2014-08-20 | 8
| 050.37538 | PRP.2635.1st Street Replace | Retire 96 ft of 1 1/4 inch BARE main, Install 106 ft 2 inch POLY | 1186.66 | 2666.95 | -1480.29 | -55.5% | 0.002718% | 1186.66 | 2666.95 | -1480.29 | 2013-10-01 | 2014-09-30 | 2014-05-20 | 5 | 2014-06-30 | 6
| 050.37558 | 2738.LEB.CAMPBELLSVILLE RD 14 | INSTALL 250' OF 2" PE FOR NEW CUSTOMERS OFF CAMPBELLSVILLE RD NORTHEAST OF WAREHOUSE DR | 861.19 | 2923.21 | -2062.02 | -70.54% | 0.001973% | 861.19 | 2923.21 | -2062.02 | 2013-10-01 | 2014-09-30 | 2014-05-23 | 5 | 2015-05-23 | 5
| 050.37560 | 2735.Glasgow Office Land | Purchase of raw land for Glasgow, KY office | 3302.75 | 60000 | -56697.25 | -94.5% | 0.007565% | 3302.75 | 60000 | -56697.25 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2015-09-30 | 9
| 050.37575 | 2738.Lebanon Waterbath Heater | Purchase indirect waterbath heater from Total Energy Resources for Calvary station in Lebanon, KY. | 62814.7 | 64276.66 | -1461.96 | -2.274% | 0.1439% | 62814.7 | 64276.66 | -1461.96 | 2013-10-01 | 2014-09-30 | 2014-05-29 | 5 | 2014-11-30 | 11
| 050.37614 | PRP.2636.Hwy 181 | Install 811 ft 2 Inch PE to replace 435 ft 4 Inch Bare Stl. and 497 ft 2 Inch Hot tar coated pipe. 6 Customers will be involved | 27454.15 | 33963.34 | -6509.19 | -19.17% | 0.06289% | 27454.15 | 33963.34 | -6509.19 | 2013-10-01 | 2014-09-30 | 2014-05-20 | 5 | 2014-07-01 | 7
| 050.37668 | PRP.2635.Brook St Replace | Retire 375 feet of 2 inch bare (100 ft of 2 inch bare running east to west is NOT MAPPED) Installing 375 ft. of 2 inch poly. 7 customers affected | 9987.82 | 5257.15 | 4730.67 | 89.99% | 0.02288% | 9987.82 | 5257.15 | 4730.67 | 2013-10-01 | 2014-09-30 | 2014-06-02 | 6 | 2014-07-30 | 7
| 050.37675 | Retire units 5274 & 10702 | Retirement of trencher #5274, a 1990 Ditch Witch model 4010, salvage value is -$4,500. Retirement of trailer #10702, a Belshe model WB-12, salvage value is -$2,500 for a total salvage value of $7,000 for both. | -7033.76 | -7000 | -33.76 | 0.4823% | -0.01611% | -7033.76 | -7000 | -33.76 | 2013-10-01 | 2014-09-30 | 2014-05-30 | 5 | 2014-09-30 | 9
| 050.37682 | 050.2636.Elwood Ct. | Install 300 Ft 2 Inch PE to serve 4 residential customers | 10616.08 | 6527.3 | 4088.78 | 62.64% | 0.02432% | 10616.08 | 6527.3 | 4088.78 | 2013-10-01 | 2014-09-30 | 2014-06-20 | 6 | 2014-07-01 | 7
| 050.37683 | 050.2636.Meridian Ct | Install 300 ft 2 Inch PE to serve 3 residential customers | 12578.21 | 6527.3 | 6050.91 | 92.7% | 0.02881% | 12578.21 | 6527.3 | 6050.91 | 2013-10-01 | 2014-09-30 | 2014-06-20 | 6 | 2014-07-01 | 7
| 050.37684 | 050.2636.Thorn Ridge Crossing | Install 515 ft 2 Inch PE to serve 13 residential customers | 2261.42 | 4427.52 | -2166.1 | -48.92% | 0.00518% | 2261.42 | 4427.52 | -2166.1 | 2013-10-01 | 2014-09-30 | 2014-07-15 | 7 | 2014-08-25 | 8
| 050.37698 | 2739.LAW.EVERGREEN TBS 2014 | REBUILD THE LAWRENECEBURG EVERGREEN TBS STATION. | 16010.87 | 38690.79 | -22679.92 | -58.62% | 0.03667% | 16010.87 | 38690.79 | -22679.92 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37699 | 2737.LAN.OLD DVILLE RD RECT | REPLACE THE RECTIFIER AND ANODE BED ON OLD DANVILLE ROAD IN LANCASTER. THIS IS A BUDGETED ITEM FOR 2014 | 7599.67 | 27647.07 | -20047.4 | -72.51% | 0.01741% | 7599.67 | 27647.07 | -20047.4 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37701 | 2737.ODORANT TANK REMOVAL 14 | REMOVE AND RECYCLE THE ODORANT TANKS AT THE HARRODSBURG AND DANVILLE PURCHASE STATIONS. THIS WILL HAVE 4 ODORANT TANKS REMOVED FROM OUR SYSTEM THAT HAVE BEEN REPLACED WITH YZ SYSTEMS. THIS IS A BUDGETED ITEM FOR 2014 | 4333.18 | 18952.99 | -14619.81 | -77.14% | 0.009926% | 4333.18 | 18952.99 | -14619.81 | 2013-10-01 | 2014-09-30 | 2013-10-01 | 10 | 2014-09-30 | 9
| 050.37704 | 050.2636.Whispering Meadows 4 | Install 2463 Ft 2 Inch PE to serve 53 lots | 14413.77 | 16390.67 | -1976.9 | -12.06% | 0.03302% | 14413.77 | 16390.67 | -1976.9 | 2013-10-01 | 2014-09-30 | 2014-07-01 | 7 | 2014-09-28 | 9
| 050.37719 | 050.2636.Spring Haven Trace | Install 100 ft 2 Inch PE to serve 1 residential lot | 1112.89 | 1671.96 | -559.07 | -33.44% | 0.002549% | 1112.89 | 1671.96 | -559.07 | 2013-10-01 | 2014-09-30 | 2014-07-01 | 7 | 2014-08-20 | 8
| 050.37732 | 050.2635.Green Meadow Ext | Install 93 ft of 2 inch PE for one new residential customer requesting gas service. | 873.45 | 1048.32 | -174.87 | -16.68% | 0.002001% | 873.45 | 1048.32 | -174.87 | 2013-10-01 | 2014-09-30 | 2014-06-18 | 6 | 2014-07-03 | 7
| 050.37743 | 050.2734.Henderson Ind.Park | 1600 ft.. of 4 inch steel HPD - Henderson Industrial Park - Franklin | 1729.13 | 35342.85 | -33613.72 | -95.11% | 0.003961% | 1729.13 | 35342.85 | -33613.72 | 2013-10-01 | 2014-09-30 | 2014-07-31 | 7 | 2014-09-28 | 9
| 050.37745 | 2636.WMR.Sensus Endpoints | Purchase 15,000 Sensus endpoints for installation in Owensboro, KY | 1388289.46 | 1586909.8 | -198620.34 | -12.52% | 3.18% | 1388289.46 | 1586909.8 | -198620.34 | 2013-10-01 | 2014-09-30 | 2014-07-01 | 7 | 2015-06-30 | 6
| 050.37808 | 2738.SPR.HWY 150.CORNERSTONE | INSTALL 3500' OF 4" PE TO SERVE A NEW CUSTOMER ON 150 BYPASS ON WEST SIDE OF SPRINGFIELD - CORNERSTONE CHRISTIAN CHURCH | 17344.57 | 14903.49 | 2441.08 | 16.38% | 0.03973% | 17344.57 | 14903.49 | 2441.08 | 2013-10-01 | 2014-09-30 | 2014-01-01 | 1 | 2014-09-30 | 9
| 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | INSTALL PIPE FOR NALLEY & HAYDON IN GREENSBURG | 169603.84 | 167242.45 | 2361.39 | 1.412% | 0.3885% | 169603.84 | 167242.45 | 2361.39 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2015-07-31 | 7
| 050.37863 | Replace station | Replace station | 52926.77 | 40990.13 | 11936.64 | 29.12% | 0.1212% | 52926.77 | 40990.13 | 11936.64 | 2013-10-01 | 2014-09-30 | 2014-06-30 | 6 | 2014-09-28 | 9
| 050.37890 | 050.2637.Eva Dr Main Ext | Install 30 ft of 2 inch PE for one existing residential customer requesting gas service. | 1208.87 | 733.55 | 475.32 | 64.8% | 0.002769% | 1208.87 | 733.55 | 475.32 | 2013-10-01 | 2014-09-30 | 2014-07-07 | 7 | 2014-07-31 | 7
| 050.37892 | PRP.2638.Mayfield 2014 | PRP.2638.Mayfield 2014 | 61666.67 | 666602.24 | -604935.57 | -90.75% | 0.1413% | 61666.67 | 666602.24 | -604935.57 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2015-07-29 | 7
| 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | Replace approximately 1227 ft of 2 Inch Bare LP Stl with 2 Inch IP PE also retire 2 Low Pressure Reg Stations 13 customers involved. | 20074.77 | 47164.67 | -27089.9 | -57.44% | 0.04598% | 20074.77 | 47164.67 | -27089.9 | 2013-10-01 | 2014-09-30 | 2014-07-22 | 7 | 2014-12-31 | 12
| 050.37948 | 050.2736.W 8th St Relocate | The City of Hopkinsville has built parts of the new Municipal Building on top of our 4 inch steel gas main. | 13057.49 | 8280.47 | 4777.02 | 57.69% | 0.02991% | 13057.49 | 8280.47 | 4777.02 | 2013-10-01 | 2014-09-30 | 2014-07-28 | 7 | 2014-08-30 | 8
| 050.37959 | 050.2637.Hwy 95 Relocate | Property owner (Mark Devine) requesting Atmos relocate existing 2 inch steel main, he is cutting down the bank. We are going to install 190 feet of 2 inch PE and retire 180 feet of 2 inch steel. Customer will be billed "post-job". | 785.66 | 3042.73 | -2257.07 | -74.18% | 0.0018% | 785.66 | 3042.73 | -2257.07 | 2013-10-01 | 2014-09-30 | 2014-07-17 | 7 | 2014-08-30 | 8
| 050.37965 | 050.2636.Greenville 6 Inch Re | Relocate approximately 700 Ft of HPD Steel exposed in Creek Bank. | 7499.09 | 123381.36 | -115882.27 | -93.92% | 0.01718% | 7499.09 | 123381.36 | -115882.27 | 2013-10-01 | 2014-09-30 | 2014-07-10 | 7 | 2014-11-28 | 11
| 050.37992 | PRP.2635.Marion Westside | PRP.2635.Marion Westside | 29084.59 | 404045.26 | -374960.67 | -92.8% | 0.06662% | 29084.59 | 404045.26 | -374960.67 | 2013-10-01 | 2014-09-30 | 2013-10-17 | 10 | 2015-07-15 | 7
| 050.37999 | 050.2734.BelleHaven III | 2 inch PE Extension - Belle Haven III - Bowling Green | 4755.69 | 7925.37 | -3169.68 | -39.99% | 0.01089% | 4755.69 | 7925.37 | -3169.68 | 2013-10-01 | 2014-09-30 | 2014-07-14 | 7 | 2014-09-28 | 9
| 050.38009 | 050.2637.Noble Road Relocatio | Relocate 700 feet of 8 inch HPD due to new Southern Coal Handling railroad tracks. We are letting customer pay contractor directly to lower gas main, customer is also providing the materials. | 2781.99 | 5932.5 | -3150.51 | -53.11% | 0.006372% | 2781.99 | 5932.5 | -3150.51 | 2013-10-01 | 2014-09-30 | 2014-08-04 | 8 | 2014-08-22 | 8
| 050.38015 | 2737.STN.LINCOLN PLAZA 2014 | INSTALL 425' OF 2" PE FOR NEW COMMERICAL BUILDING IN LINCOLN PLAZA STANFORD | 981.13 | 704.63 | 276.5 | 39.24% | 0.002247% | 981.13 | 704.63 | 276.5 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2015-08-01 | 8
| 050.38028 | 2738.SPR.W VIRGINIA AVE 2014 | INSTALL 150' OF 2" PE TO SERVE A NEW CUSTOMER | 672.32 | 1414.49 | -742.17 | -52.47% | 0.00154% | 672.32 | 1414.49 | -742.17 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2015-08-01 | 8
| 050.38038 | 050.2638.Douthitt St Ext | Install 485 ft of 2 inch PE for one new commercial customer | 13807.9 | 5350.57 | 8457.33 | 158.1% | 0.03163% | 13807.9 | 5350.57 | 8457.33 | 2013-10-01 | 2014-09-30 | 2014-07-28 | 7 | 2014-08-30 | 8
| 050.38046 | 050.2636.Vincent Station Rd. | Install 100 ft 2Inch PE to serve 1 Commercial Customer | 314.57 | 2243.9 | -1929.33 | -85.98% | 0.0007206% | 314.57 | 2243.9 | -1929.33 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2014-08-30 | 8
| 050.38067 | 050.2637.N 13th Street Ext | Install 135 feet of 2 inch PE main for one existing residential customer (Pamela Dodd) requesting natural gas. | 496.17 | 1590.93 | -1094.76 | -68.81% | 0.001137% | 496.17 | 1590.93 | -1094.76 | 2013-10-01 | 2014-09-30 | 2014-08-04 | 8 | 2014-09-28 | 9
| 050.38086 | 050.2734.Northridge VII | 2 inch PE Extension Northridge VII - Bowling Green | 7662.44 | 12478.77 | -4816.33 | -38.6% | 0.01755% | 7662.44 | 12478.77 | -4816.33 | 2013-10-01 | 2014-09-30 | 2014-06-16 | 6 | 2014-09-28 | 9
| 050.38089 | 050.2734.Boston Pk.Traditions | 2 inch PE Extension -Boston Pk and Alley 10 - Traditions -B.G. | 1513.49 | 6173.13 | -4659.64 | -75.48% | 0.003467% | 1513.49 | 6173.13 | -4659.64 | 2013-10-01 | 2014-09-30 | 2014-06-16 | 6 | 2015-06-30 | 6
| 050.38155 | 050.2638.Commonwealth Dr Ext | Install 775 feet of 4 inch PE for one new commercial customer (Better Built Bldg office). | 3260.53 | 5918.05 | -2657.52 | -44.91% | 0.007469% | 3260.53 | 5918.05 | -2657.52 | 2013-10-01 | 2014-09-30 | 2014-08-04 | 8 | 2014-09-30 | 9
| 050.38178 | 2739.LOCUST CREEK VILLA HOMES | INSTALL GAS MAIN TO SERVE 25 LOTS WITH VILLA HOMES BEING BUILT | 5382.99 | 15060.51 | -9677.52 | -64.26% | 0.01233% | 5382.99 | 15060.51 | -9677.52 | 2013-10-01 | 2014-09-30 | 2014-07-01 | 7 | 2014-09-30 | 9
| 050.38179 | 2735.WALL ST 2014 | INSTALL 100' OF 2" PE TO SERVE A NEW HOLIDAY INN HOTEL ON WALL ST | 946.56 | 1340.89 | -394.33 | -29.41% | 0.002168% | 946.56 | 1340.89 | -394.33 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2014-09-30 | 9
| 050.38187 | 050.2636.Aldi Hwy 54 | Install 400 ft 4Inch PE to serve the new Gateway Commons Commercial Developement | -2746.47 | 3009 | -5755.47 | -191.3% | -0.006291% | -2746.47 | 3009 | -5755.47 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2014-08-30 | 8
| 050.38210 | 050.2636.Medley Rd. | Install 945 ft 2 Inch PE to serve 5 residential customers | 5892.86 | 7837.58 | -1944.72 | -24.81% | 0.0135% | 5892.86 | 7837.58 | -1944.72 | 2013-10-01 | 2014-09-30 | 2014-08-10 | 8 | 2014-09-28 | 9
| 050.38212 | 2737.JC.MARGUS DR 2014 | INSTALL A 2" PE GAS MAIN FROM JONES LN ALONG EASEMENT TO SERVE COMMERICAL BUSSINESS ON MARGUS DR | 6519.9 | 1878.75 | 4641.15 | 247% | 0.01493% | 6519.9 | 1878.75 | 4641.15 | 2013-10-01 | 2014-09-30 | 2014-08-01 | 8 | 2015-08-01 | 8
| 050.38233 | PRP.2735.HISE.CORAL HILL 14 | INSTALL 300' OF 2" PE TO REPLACE BARE STEEL ON CORAL HILL ST IN HISEVILLE | 17672.71 | 21569.11 | -3896.4 | -18.06% | 0.04048% | 17672.71 | 21569.11 | -3896.4 | 2013-10-01 | 2014-09-30 | 2014-08-08 | 8 | 2014-09-30 | 9
| 050.38244 | 2737.JC.HWY 2141 2014 | INSTALL 925' OF 2" PE FOR NEW CUSTOMER SOUTH OF HWY 300 ON HWY 2141 IN JUNCTION CITY | 1956.12 | 4333.33 | -2377.21 | -54.86% | 0.004481% | 1956.12 | 4333.33 | -2377.21 | 2013-10-01 | 2014-09-30 | 2014-06-01 | 6 | 2014-09-30 | 9
| 050.38278 | 050.2635.Eddyville Mall Ext | Install 250' - 2" PE for a new seafood restaurant | -771.96 | 1508.21 | -2280.17 | -151.2% | -0.001768% | -771.96 | 1508.21 | -2280.17 | 2013-10-01 | 2014-09-30 | 2014-08-30 | 8 | 2014-09-28 | 9
| 050.38279 | 050.2638.Pryorsburg TB Repl | Replace TB (regulator station) Install upstream and downstream valves | 8565.1 | 15584.5 | -7019.4 | -45.04% | 0.01962% | 8565.1 | 15584.5 | -7019.4 | 2013-10-01 | 2014-09-30 | 2014-09-02 | 9 | 2015-07-30 | 7
| 050.38364 | 050.2635.Marion Ind Park | Install 2,000 feet of 4 inch PE into the City of Marion KY industrial park. | -1545.03 | 2603.11 | -4148.14 | -159.4% | -0.003539% | -1545.03 | 2603.11 | -4148.14 | 2013-10-01 | 2014-09-30 | 2014-09-02 | 9 | 2014-09-28 | 9
| 050.38374 | 050.2637.Lovelaceville Rd Ext | Install 650 ft of 4 inch PE for two customers | 314.61 | 3770.99 | -3456.38 | -91.66% | 0.0007207% | 314.61 | 3770.99 | -3456.38 | 2013-10-01 | 2014-09-30 | 2014-09-08 | 9 | 2014-10-30 | 10
| 050.38385 | MEC Forfeiture 040.009 FY14 | MEC Forfeiture 040.009 FY14 | -815164.47 | -208885.04 | -606279.43 | 290.2% | -1.867% | -815164.47 | -208885.04 | -606279.43 | 2013-10-01 | 2014-09-30 | 2014-08-29 | 8 | 2015-10-31 | 10
| 050.38415 | PRP.2734.Riverview & College | Replace bare main along Riverview, College and side streets | 3060.09 | 1001570.07 | -998509.98 | -99.69% | 0.00701% | 3060.09 | 1001570.07 | -998509.98 | 2013-10-01 | 2014-09-30 | 2014-07-28 | 7 | 2015-02-28 | 2
| 050.38537 | 050.2636.Boston Laffon Rd. | 1000 ft. of 2 inch pe to serve 10 residenttialo customers | -7354.63 | 8972.87 | -16327.5 | -182% | -0.01685% | -7354.63 | 8972.87 | -16327.5 | 2013-10-01 | 2014-09-30 | 2014-09-22 | 9 | 2014-10-31 | 10

## 2013a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2013
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2013 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | 2013 Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.19593 | Hopkinsville 08 Non Growth | Hopkinsville 08 Non Growth | -594.82 | 0 |  |  | 1.283% | 382303.68 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.19596 | Campbellsville 08 Growth | Campbellsville 08 Growth | -55.87 | 0 |  |  | 0.2688% | 80114.8 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.19599 | Shelbyville 08 Non Growth | Shelbyville 08 Non Growth | -361 | 0 |  |  | 0.7043% | 209931.67 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.19601 | Madisonville 08 Non Growth | Madisonville 08 Non Growth | -143.35 | 0 |  |  | 1.639% | 488616.64 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.19607 | Paducah 08 Non Growth | Paducah 08 Non Growth | -4760.56 | 0 |  |  | 3.167% | 944015.23 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2007-09-18 | 9 | 2008-10-31 | 10
| 050.20823 | 050.BGR.8"CENTER LINE HPD | 8" CENTER LINE HPD RELOC PHASE I - B.G. | 10999.77 | 1398465 | 455330.7 | 32.56% | 6.22% | 1853795.7 | 1398465 | 455330.7 | 2012-10-01 | 2013-09-30 | 2008-07-25 | 7 | 2009-07-25 | 7
| 050.21065 | Bowling Green 09 Non Growth | Bowling Green 09 Non Growth | -533.96 | 0 |  |  | 5.479% | 1632936.36 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21071 | Danville 09 Non Growth | Danville 09 Non Growth | -766.99 | 0 |  |  | 2.206% | 657492.27 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21077 | Madisonville 09 Non Growth | Madisonville 09 Non Growth | -3497.19 | 0 |  |  | 2.128% | 634160.45 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21079 | Princeton 09 Non Growth | Princeton 09 Non Growth | -2647.25 | 0 |  |  | 0.6371% | 189898.7 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21083 | Paducah 09 Non Growth | Paducah 09 Non Growth | -10778.74 | 0 |  |  | 3.211% | 957158.41 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2008-09-29 | 9 | 2009-10-31 | 10
| 050.21917 | 050.2609.Nort'ville Hwy 62 12" | 050.2609 Replace 10" 90-159-10 at Hwy 62 w/ 12" | -97184.95 | 638316.21 | -260441.67 | -40.8% | 1.268% | 377874.54 | 638316.21 | -260441.67 | 2012-10-01 | 2013-09-30 | 2009-03-09 | 3 | 2012-02-25 | 2
| 050.22391 | 050.KY.BowlGrnIntegFunct2010 | 050.KY.BowlGrnIntegFunct2010 | -1648.56 | 0 |  |  | 4.271% | 1273058.12 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22394 | 050.KY.DanvilleIntegFunct2010 | 050.KY.DanvilleIntegFunct2010 | -503.33 | 0 |  |  | 1.657% | 493905.13 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22397 | 050.KY.MadisonIntegFunct2010 | 050.KY.MadisonIntegFunct2010 | -1667.28 | 0 |  |  | 2.483% | 740095.79 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2011-01-12 | 1
| 050.22429 | 050.KY.BowlGrnLeakFunct2010 | 050.KY.BowlGrnLeakFunct2010 | -2769.9 | 0 |  |  | 3.528% | 1051472.05 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22432 | 050.KY.DanvilleLeakFunct2010 | 050.KY.DanvilleLeakFunct2010 | -435.52 | 0 |  |  | 0.6197% | 184717.79 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22433 | 050.KY.CampbellLeakFunct2010 | 050.KY.CampbellLeakFunct2010 | -1176.47 | 0 |  |  | 0.8652% | 257872.38 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22434 | 050.KY.ShelbyvLeakFunct2010 | 050.KY.ShelbyvLeakFunct2010 | -1628.25 | 0 |  |  | 0.3035% | 90451.08 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22436 | 050.KY.PrincetonLeakFunct2010 | 050.KY.PrincetonLeakFunct2010 | -551.98 | 0 |  |  | 0.451% | 134417.18 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22437 | 050.KY.OboroLeakFunct2010 | 050.KY.OboroLeakFunct2010 | -3390.38 | 0 |  |  | 2.068% | 616412.98 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22438 | 050.KY.PaducahLeakFunct2010 | 050.KY.PaducahLeakFunct2010 | -19744.49 | 0 |  |  | 1.533% | 456945.73 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.22439 | 050.KY.MayfieldLeakFunct2010 | 050.KY.MayfieldLeakFunct2010 | -458.8 | 0 |  |  | 0.2899% | 86419.86 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2009-09-10 | 9 | 2010-09-30 | 9
| 050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 220164.49 | 0 |  |  | 2.262% | 674135.56 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 32298.02 | 0 |  |  | 0.2427% | 72344.58 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 21570.19 | 0 |  |  | 0.361% | 107584.99 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 27797.4 | 0 |  |  | 0.3961% | 118051.72 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 23512.23 | 0 |  |  | 0.3863% | 115138.04 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 78644.05 | 0 |  |  | 0.9051% | 269759.26 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 16259.36 | 0 |  |  | 0.1942% | 57887.36 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 17412.22 | 0 |  |  | 0.1977% | 58925.11 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 95160.41 | 0 |  |  | 1.223% | 364464.84 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 59221.84 | 0 |  |  | 0.8459% | 252121.65 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 13021.2 | 0 |  |  | 0.134% | 39937.16 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-10 | 9 | 2015-09-30 | 9
| 050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 167232.13 | 0 |  |  | 1.727% | 514852.95 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 1731.82 | 0 |  |  | 0.06672% | 19886.94 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 2976.21 | 0 |  |  | 0.09116% | 27170.41 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 52321.05 | 0 |  |  | 0.6124% | 182537.13 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 6029.22 | 0 |  |  | 0.09729% | 28997.43 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 11587.9 | 0 |  |  | 0.3909% | 116510.55 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5061.23 | 0 |  |  | 0.09432% | 28113.09 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5470.82 | 0 |  |  | 0.258% | 76905.46 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 51314.19 | 0 |  |  | 0.7519% | 224104.7 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 131313 | 0 |  |  | 0.5931% | 176782.7 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 24564.28 | 0 |  |  | 0.1551% | 46240.22 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-11 | 9 | 2015-09-30 | 9
| 050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 666169.68 | 0 |  |  | 6.258% | 1865351.79 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 138424.52 | 0 |  |  | 0.8298% | 247329.09 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 39321.61 | 0 |  |  | 0.4719% | 140665.2 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 32044.64 | 0 |  |  | 0.4879% | 145434.46 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 34081.3 | 0 |  |  | 0.3437% | 102429.45 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 200176.07 | 0 |  |  | 1.636% | 487613.87 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 75963.02 | 0 |  |  | 0.7504% | 223657.5 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 37141.76 | 0 |  |  | 0.4004% | 119346.67 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 413784.03 | 0 |  |  | 3.61% | 1075890.12 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 264428.27 | 0 |  |  | 2.524% | 752308.25 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 70324.91 | 0 |  |  | 0.6967% | 207648.25 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-12 | 9 | 2015-09-30 | 9
| 050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 149596.34 | 0 |  |  | 2.001% | 596494.7 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 24546.38 | 0 |  |  | 0.3928% | 117083.43 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 50641.28 | 0 |  |  | 0.3573% | 106501.9 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 42827.87 | 0 |  |  | 0.3795% | 113102.18 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 26182.18 | 0 |  |  | 0.2351% | 70081.6 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 26704.19 | 0 |  |  | 0.1961% | 58461.54 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 40218.4 | 0 |  |  | 0.4023% | 119894.6 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 25093.91 | 0 |  |  | 0.2067% | 61599.45 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 118105.58 | 0 |  |  | 1.547% | 461207.51 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 163261.05 | 0 |  |  | 1.254% | 373711 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 6748.95 | 0 |  |  | 0.1718% | 51208.51 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 324991.79 | 0 |  |  | 3.437% | 1024397.03 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 123156.38 | 0 |  |  | 0.851% | 253639.77 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 243185.56 | 0 |  |  | 2.123% | 632682.06 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 317846.79 | 0 |  |  | 2.231% | 665103.75 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 82753.28 | 0 |  |  | 1.025% | 305460.3 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 73110.97 | 0 |  |  | 0.7665% | 228455.46 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 100810.95 | 0 |  |  | 1.537% | 457985.32 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 64801.98 | 0 |  |  | 0.9758% | 290829.59 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 381124.19 | 0 |  |  | 3.198% | 953308.2 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 278769.22 | 0 |  |  | 3.26% | 971514.1 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 102074.19 | 0 |  |  | 0.9519% | 283722.8 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-13 | 9 | 2015-09-30 | 9
| 050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 599351.37 | 0 |  |  | 4.992% | 1487953.17 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 240069.66 | 0 |  |  | 1.563% | 465760.88 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 235909.87 | 0 |  |  | 1.704% | 507984.72 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 300930.89 | 0 |  |  | 2.244% | 668952.66 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 219096.65 | 0 |  |  | 1.529% | 455821.97 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 181366.87 | 0 |  |  | 1.264% | 376659.64 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 267215.54 | 0 |  |  | 2.766% | 824300.3 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 145522.88 | 0 |  |  | 1.142% | 340261.07 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 970301.72 | 0 |  |  | 8.577% | 2556510.91 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 382626.23 | 0 |  |  | 2.88% | 858376.23 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 243136.57 | 0 |  |  | 2.075% | 618536.02 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23831 | BowlingGreenIntegRegs | Bowling Green Non Growth Regs Functional | 503.38 | 0 |  |  | 0.1983% | 59115.1 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23834 | DanvilleIntegRegs | Danville Non Growth Regs Functional | 628.39 | 0 |  |  | 0.2055% | 61258.35 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23836 | KY.ShelbyvilleIntegRegs | Shelbyville KY Non Growth Regs Functional | 438.91 | 0 |  |  | 0.3264% | 97270.02 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23838 | MadisonvilleIntegRegs | Madisonville Non Growth Regs | 315.46 | 0 |  |  | 0.2464% | 73445.1 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23839 | PrincetonIntegRegs | Princeton Non Growth Regs Functional | -1353.02 | 0 |  |  | 0.1786% | 53219.58 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23840 | OboroIntegRegs | Owensboro Non Growth Regs Functional | 10083.26 | 0 |  |  | 0.6903% | 205756.51 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2016-09-30 | 9
| 050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 96156.46 | 0 |  |  | 0.872% | 259904.22 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 6592.52 | 0 |  |  | 0.1144% | 34110.58 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 64879.92 | 0 |  |  | 0.7552% | 225082.78 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 48845.4 | 0 |  |  | 0.7107% | 211840.66 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 33556 | 0 |  |  | 0.3211% | 95690.48 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 13787.49 | 0 |  |  | 0.1868% | 55671.38 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 21428.11 | 0 |  |  | 0.2887% | 86048.57 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 42101.11 | 0 |  |  | 0.4294% | 127975.2 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 15785.37 | 0 |  |  | 0.5223% | 155687.58 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 56589.76 | 0 |  |  | 0.7154% | 213215.43 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 2854.06 | 0 |  |  | 0.09439% | 28132.64 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-14 | 9 | 2015-09-30 | 9
| 050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 269210.54 | 0 |  |  | 2.655% | 791465.29 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 81029 | 0 |  |  | 0.6127% | 182611.37 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 58405.31 | 0 |  |  | 0.4627% | 137895.04 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 114706.23 | 0 |  |  | 0.649% | 193439.05 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 35524.9 | 0 |  |  | 0.3245% | 96712.08 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 27623.91 | 0 |  |  | 0.1803% | 53748.54 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 68777.76 | 0 |  |  | 0.4814% | 143487.44 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 30480.6 | 0 |  |  | 0.219% | 65276.44 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 177881.75 | 0 |  |  | 1.252% | 373149.82 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 127494.97 | 0 |  |  | 1.006% | 299708.6 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 12444.8 | 0 |  |  | 0.09861% | 29390.9 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 184916.31 | 0 |  |  | 2.559% | 762748.74 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 50432.52 | 0 |  |  | 0.6609% | 196973.33 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 111589.2 | 0 |  |  | 0.9964% | 296974.54 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 132833.32 | 0 |  |  | 1.065% | 317313.53 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 22960.36 | 0 |  |  | 0.4% | 119212.29 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 52247.65 | 0 |  |  | 0.2912% | 86780.63 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 50554.56 | 0 |  |  | 0.4793% | 142861.92 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 12468.62 | 0 |  |  | 0.2398% | 71483.89 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 160112.49 | 0 |  |  | 1.531% | 456349.06 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 161104.96 | 0 |  |  | 1.703% | 507550.86 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 34648.26 | 0 |  |  | 0.24% | 71522.66 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 279344.42 | 0 |  |  | 1.709% | 509245.87 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 39986.1 | 0 |  |  | 0.7123% | 212302.98 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 20220.13 | 0 |  |  | 0.1394% | 41536.66 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 112864.96 | 0 |  |  | 0.8037% | 239554.3 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 108703.39 | 0 |  |  | 0.6244% | 186099.52 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 38369.31 | 0 |  |  | 0.2606% | 77662.66 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 25832.27 | 0 |  |  | 0.21% | 62603.26 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 30800.05 | 0 |  |  | 0.2586% | 77069.76 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 247035.03 | 0 |  |  | 1.663% | 495699.47 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 132032.46 | 0 |  |  | 0.5931% | 176790.55 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 28587.4 | 0 |  |  | 0.1612% | 48042.26 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24031 | DanvilleLeakRegs | Danville Leak Regs Functional | 1223.57 | 0 |  |  | 0.205% | 61095.13 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2016-09-30 | 9
| 050.24035 | PrincetonLeakRegs | Princeton Leak Regs Functional | 1496.37 | 0 |  |  | 0.02377% | 7084.8 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24067 | BowlingLeakCP/LeakClamps | Bowling Green KY Leak Functional - CP/Leak Clamps | -5057.62 | 0 |  |  | 1.47% | 438224.79 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24068 | GlasgowLeakCP/LeakClamps | Glasgow Leak Functional - CP/Leak Clamps | 323.38 | 0 |  |  | 0.5823% | 173571.25 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2016-09-30 | 9
| 050.24073 | MadisonLeakCP/LeakClamps | Madisonville Leak Functional - CP/Leak Clamps | 2445.18 | 0 |  |  | 0.2816% | 83925.32 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24074 | PrincetonLeakCP/LeakClamps | Princeton Leak Functional - CP/Leak Clamps | 16020.77 | 0 |  |  | 0.1881% | 56068.91 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-15 | 9 | 2015-09-30 | 9
| 050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 3184.85 | 0 |  |  | 0.08217% | 24491.93 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 7.35 | 0 |  |  | 0.03976% | 11851.98 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 665045.01 | 0 |  |  | 4.679% | 1394641.69 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 371811.07 | 0 |  |  | 3.72% | 1108729.12 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 1221676.48 | 0 |  |  | 6.308% | 1880238.76 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 21603.55 | 0 |  |  | 0.2797% | 83363.18 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24088 | BowlingGreenPRPMeters | Bowling Greek KY PRP Functional - Meters | 35.58 | 0 |  |  | 0.0001194% | 35.58 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24089 | DanvillePRPMeters | Danville KY PRP Functional - Meters | 813.28 | 0 |  |  | 0.01067% | 3179.86 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.24090 | OwensboroPRPMeters | Owensboro KY PRP Functional - Meters | 16915.13 | 0 |  |  | 0.2778% | 82792.43 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2016-09-30 | 9
| 050.24109 | KY.Storage Integ RESI MEAS | KY Storage & Transmission Non Growth Functional - RESI MEAS. Meters, regulators, and meterset items typically used for residential applications. | 1334.42 | 0 |  |  | 0.02121% | 6321.22 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 2026.39 | 0 |  |  | 0.02339% | 6970.38 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 39.29 | 0 |  |  | 0.01539% | 4586.1 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-20 | 9 | 2015-09-30 | 9
| 050.24813 | 050.2634. Bruest Heaters | Purchase and retire Bruest Heaters | -11.31 | 9073.76 | -279.72 | -3.083% | 0.0295% | 8794.04 | 9073.76 | -279.72 | 2012-10-01 | 2013-09-30 | 2010-12-09 | 12 | 2011-09-28 | 9
| 050.25348 | 050.2638.Water Valley Replace | Replace 2" steel pipe that is exposed in creek. Will move chart box to puchase station. will retire above ground valve, not critical | 129.07 | 9505.9 | 5595.82 | 58.87% | 0.05067% | 15101.72 | 9505.9 | 5595.82 | 2012-10-01 | 2013-09-30 | 2011-04-01 | 4 | 2011-08-30 | 8
| 050.25359 | 050.2636.Reg. & Relief upgrades | Make Relief and reg upgrades at Old State Rd, Calhoun purchase, Hartford and Town Border # 4. Also upgrade 4 charts with ERX recorders | 4438.76 | 51375.09 | 3904.62 | 7.6% | 0.1855% | 55279.71 | 51375.09 | 3904.62 | 2012-10-01 | 2013-09-30 | 2011-03-22 | 3 | 2011-09-30 | 9
| 050.25441 | 050.2637.Prestwick Place Ext | Install 1145 feet of two inch poly for 26 new residential lots adjacent to the country club of Paducah | -31.75 | 6914.14 | 1388.36 | 20.08% | 0.02786% | 8302.5 | 6914.14 | 1388.36 | 2012-10-01 | 2013-09-30 | 2011-04-25 | 4 | 2011-09-30 | 9
| 050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 6236.29 | 0 |  |  | 0.4802% | 143129.74 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 357193.09 | 0 |  |  | 1.301% | 387842.13 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 219883.18 | 0 |  |  | 1.252% | 373258.62 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 261808.19 | 0 |  |  | 1.942% | 578735.85 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26305 | HopkinsvillePRPMains | Hopkinsville KY Pipe Replacement Program Functional - Mains | 2462.52 | 0 |  |  | 0.009766% | 2910.8 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2011-08-01 | 8
| 050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 286314.05 | 0 |  |  | 1.884% | 561489.98 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26307 | HopkinsvillePRPMeters | Hopkinsville KY PRP Functional - Meters | 2082.05 | 0 |  |  | 0.006985% | 2082.05 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2016-09-30 | 9
| 050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 44090.68 | 0 |  |  | 0.7212% | 214962.91 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2015-09-30 | 9
| 050.26312 | ShelbyvillePRPServices | Shelbyville KY PRP Functional - Services | 35.57 | 0 |  |  | 0.02935% | 8749.12 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2010-09-16 | 9 | 2016-09-30 | 9
| 050.27096 | 050.PRP.2609.DanielsLn 8 Inch | Relocate approximately 518 Ft 8 Inch HPD for storm sewer and rd. widening due to the new Hospital | -37009.6 | 116214.9 | 0 | 0% | 0.3899% | 116214.9 | 116214.9 | 0 | 2012-10-01 | 2013-09-30 | 2011-09-01 | 9 | 2011-09-28 | 9
| 050.28119 | 050.2602.MDT's 2012 | Purchase and retire MDT's | -11.31 | 121087.46 | 11108.7 | 9.174% | 0.4435% | 132196.16 | 121087.46 | 11108.7 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2012-09-28 | 9
| 050.28120 | 050.2602.Laptops and Desktops | Purchase and retire laptops and Desktops | -11.31 | 121087.48 | -654.17 | -0.5402% | 0.4041% | 120433.31 | 121087.48 | -654.17 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2012-09-28 | 9
| 050.28127 | 2738.CAM.EQUIPMENT 2012 | BOSS III ELECTROFUSION, CONCRETE SAW, DITCH WITCH LOCATOR, SENSIT GOLD CGI, GAUGES | 233.52 | 19736.15 | 6280.47 | 31.82% | 0.08729% | 26016.62 | 19736.15 | 6280.47 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.28143 | 050.2734.Misc.Equipment | 1 - Trailer for Mule - used for survey 1 - DP-IR 1 - RMLD 1 - 1" - 4" Squeeze off Tool - Russellville 1 - Trac-It II - C&M 2 - Sensit Golds - Russellville 1 - 3D ( 0-100 ) and 1- 3D ( 0-1000) - Franklin 1 - 12 volt Sub Pump - Russellville | -372.76 | 62867.79 | -25153.71 | -40.01% | 0.1265% | 37714.08 | 62867.79 | -25153.71 | 2012-10-01 | 2013-09-30 | 2011-11-26 | 11 | 2012-09-28 | 9
| 050.28150 | 2737.DAN.EQUIPMENT 2012 | 2-DITCH WITCH LOCATORS, GENERATOR, SOUTHERN CROSS FLAME PAK, BOSS III ELCTROFUSION PROCESSOR, TRAILER FOR TD WILLIAMSON TOOLS | -105.01 | 33133.89 | -1269.45 | -3.831% | 0.1069% | 31864.44 | 33133.89 | -1269.45 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.28160 | 050.2734.Hwy31W Reloc. B.G. | Hwy 31W HPD & IP Relocation | 31360.69 | 221016.86 | 619360.08 | 280.2% | 2.82% | 840376.94 | 221016.86 | 619360.08 | 2012-10-01 | 2013-09-30 | 2011-09-15 | 9 | 2011-12-31 | 12
| 050.28247 | PRP.2734.Boatlanding Replc | 150 ft. Bare Steel Replc. - Boatlanding at Beech St. - B.G. | 393.28 | 7222.21 | -3133.92 | -43.39% | 0.01372% | 4088.29 | 7222.21 | -3133.92 | 2012-10-01 | 2013-09-30 | 2011-10-27 | 10 | 2012-09-28 | 9
| 050.28434 | 2737.DAN.ODORIZOR REPLACE | REP[LACE ODORIZOR AND TANKS AT THE DANVILLE PURCHASE STATION ON HUSTONVILLE ROAD | -429.04 | 49616.6 | 2357.81 | 4.752% | 0.1744% | 51974.41 | 49616.6 | 2357.81 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.28445 | PRP.2734.MAIN Replc | PRP.2734.MAIN CENTER & FAIR | 127703.43 | 918603.32 | 0 | 0% | 3.082% | 918603.32 | 918603.32 | 0 | 2012-10-01 | 2013-09-30 | 2011-11-11 | 11 | 2012-09-28 | 9
| 050.28465 | 050.2736.Hwy 41 Nortonville | Install 300 Ft 2 Inch PE to serve 1 residential customers | -11.31 | 2881.48 | 1355.1 | 47.03% | 0.01421% | 4236.58 | 2881.48 | 1355.1 | 2012-10-01 | 2013-09-30 | 2011-11-14 | 11 | 2012-09-28 | 9
| 050.28593 | PRP.2737.HAR.MAGNOLIA-OFFICE | PRP.2737.HAR.MAGNOLIA-OFFICE | -1570.2 | 407840.5 | 249644.91 | 61.21% | 2.206% | 657485.41 | 407840.5 | 249644.91 | 2012-10-01 | 2013-09-30 | 2011-11-01 | 11 | 2012-11-01 | 11
| 050.28682 | 050.2634.Bruest Heaters | Purchase and retire 3 Bruest Heaters | 310.13 | 11641.5 | -3293.27 | -28.29% | 0.02801% | 8348.23 | 11641.5 | -3293.27 | 2012-10-01 | 2013-09-30 | 2011-12-05 | 12 | 2012-09-30 | 9
| 050.28782 | PRP.2609.Empire Fruithill | Replacement of 10 Inch Bare Steel pipe between Possum Pocket Rd. and Crofton and with 12 Inch | -82636.79 | 8967835.86 | -451858.88 | -5.039% | 28.57% | 8515976.98 | 8967835.86 | -451858.88 | 2012-10-01 | 2013-09-30 | 2012-03-01 | 3 | 2012-09-28 | 9
| 050.29091 | 050.2609.Well Workovers | Rework 5 Wells and retire 1 at Hickory Storage, Rework 1 well at St. Charles. | 16455.81 | 941994.33 | 5479.05 | 0.5816% | 3.179% | 947473.38 | 941994.33 | 5479.05 | 2012-10-01 | 2013-09-30 | 2012-01-20 | 1 | 2012-09-28 | 9
| 050.29108 | PRP.2737.HAR.PARKVIEW.CANE | PRP.2737.HAR.PARKVIEW CANE | -699.98 | 128607.66 | 227803.33 | 177.1% | 1.196% | 356410.99 | 128607.66 | 227803.33 | 2012-10-01 | 2013-09-30 | 2011-11-01 | 11 | 2012-11-01 | 11
| 050.29109 | PRP.2737.HAR.E OFFICE.GREENVI | PRP.2737.HAR.E OFFICE.GREENVI | 1672.16 | 218722.95 | 155982 | 71.31% | 1.257% | 374704.95 | 218722.95 | 155982 | 2012-10-01 | 2013-09-30 | 2011-11-01 | 11 | 2012-11-01 | 11
| 050.29199 | 2737.HARRODSBURG INDUST LINE | INSTALL 21,550ft OF 6in STEEL TO SERVE THE INDUSTRIAL PARK NORTH OF TOWN | -401.05 | 2047280.77 | 48185.67 | 2.354% | 7.03% | 2095466.44 | 2047280.77 | 48185.67 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2013-10-01 | 10
| 050.29493 | 050.2635.Hwy139 | Install 14000 Ft 4 Inch PE | 3997.78 | 33814.97 | -13187.32 | -39% | 0.06921% | 20627.65 | 33814.97 | -13187.32 | 2012-10-01 | 2013-09-30 | 2012-02-16 | 2 | 2012-09-28 | 9
| 050.29564 | 2737.DANVILLE BASEMENT METERS | INSTALL IP AND REMOVE LP AND BASEMENT METERS DOWNTOWN | -11006.39 | 221461.47 | 0 | 0% | 0.743% | 221461.47 | 221461.47 | 0 | 2012-10-01 | 2013-09-30 | 2011-06-01 | 6 | 2012-06-01 | 6
| 050.29806 | PRP.2734.GREENLAWN AREA | PRP.2734.GREENLAWN AREA | -57.39 | 356768.28 | -37759.03 | -10.58% | 1.07% | 319009.25 | 356768.28 | -37759.03 | 2012-10-01 | 2013-09-30 | 2011-10-15 | 10 | 2012-09-28 | 9
| 050.29845 | 050.2736.Rogers Group | Install 1800 ft 6 Inch PE to serve the Rogers Group Asphalt Plant | 11661.37 | 31169.63 | -513.52 | -1.648% | 0.1029% | 30656.11 | 31169.63 | -513.52 | 2012-10-01 | 2013-09-30 | 2012-03-15 | 3 | 2012-09-28 | 9
| 050.29906 | 050.2638.Hwy 45 Four Lane | The state of Kentucky is widening U.S Hwy 45 just south of Purchase Parkway. We have app. 3,500' of 4" and 2" pipe affected as well as 20 services. 25% reimbursable | -65561.39 | 246789.35 | -109249.95 | -44.27% | 0.4615% | 137539.4 | 246789.35 | -109249.95 | 2012-10-01 | 2013-09-30 | 2012-04-01 | 4 | 2012-07-22 | 7
| 050.29945 | PRP.2734 Morgantown Rd | Replace Bare Main due to leakage - Morgantown Rd. between Brevard & Parkway | 393.28 | 6917.11 | -1797.63 | -25.99% | 0.01718% | 5119.48 | 6917.11 | -1797.63 | 2012-10-01 | 2013-09-30 | 2012-03-15 | 3 | 2012-09-28 | 9
| 050.29948 | KY RTU Upgrades | Upgradeing Fisher RTU's | 1161.93 | 26611.1 | -2835.62 | -10.66% | 0.07977% | 23775.48 | 26611.1 | -2835.62 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.29959 | 050.2734.Elrod Rd. Reloc | Relocate 625 ft. of 4 inch PE - Elrod Rd. | 393.28 | 37027.57 | -1492.18 | -4.03% | 0.1192% | 35535.39 | 37027.57 | -1492.18 | 2012-10-01 | 2013-09-30 | 2012-03-12 | 3 | 2012-09-28 | 9
| 050.30003 | PRP.2736.EMPIRE DIST EXT | PRP.2736.EMPIRE DIST EXT | -847.33 | 181533.29 | -5696.77 | -3.138% | 0.5899% | 175836.52 | 181533.29 | -5696.77 | 2012-10-01 | 2013-09-30 | 2012-03-28 | 3 | 2012-09-28 | 9
| 050.30005 | 050.2636.Daniels Ln. Relo 2 | Relocate 2 Inch Stl. for road. widening and to get 2 Inch Stll airplaning creek removed pipe will be replaced with 3145 ft 4 Inch PE and 94 ft 2 Inch PE to help support future growth in the area near the new hospital | -254.81 | 69198.61 | 5441.92 | 7.864% | 0.2504% | 74640.53 | 69198.61 | 5441.92 | 2012-10-01 | 2013-09-30 | 2012-03-15 | 3 | 2012-09-28 | 9
| 050.30045 | PRP.2735 ROCKY HILL | PRP.2735 ROCKY HILL | 30723.92 | 219865.36 | 25847.06 | 11.76% | 0.8244% | 245712.42 | 219865.36 | 25847.06 | 2012-10-01 | 2013-09-30 | 2012-02-13 | 2 | 2012-09-28 | 9
| 050.30061 | 2738.WOODHILL RD 2012 | INSTALL 600ft OF 2in PE FROM THE END OF PROJECT 2738.WOODHILL RD 2011 | -199.97 | 0.26 | 2995.81 | 1152235% | 0.01005% | 2996.07 | 0.26 | 2995.81 | 2012-10-01 | 2013-09-30 | 2012-03-01 | 3 | 2013-03-01 | 3
| 050.30199 | 2738.WOODHILL RD 2011 | INSTALL 2100ft 2in PE PIPE FOR CUSTOMER | -56.19 | 8582.91 | 577.89 | 6.733% | 0.03074% | 9160.8 | 8582.91 | 577.89 | 2012-10-01 | 2013-09-30 | 2011-05-01 | 5 | 2012-05-01 | 5
| 050.30241 | 050.Sir Charles Ct Ext II | Install 100 ft. 2 inch PE for one customer. | -3.78 | 1493.17 | -447.03 | -29.94% | 0.00351% | 1046.14 | 1493.17 | -447.03 | 2012-10-01 | 2013-09-30 | 2012-05-14 | 5 | 2012-06-30 | 6
| 050.30242 | 050.2637.Ladera Ln Ext | Install 1,960' of 4" PE and 1,130' of 2" PE | -222.97 | 24537.23 | -5656.64 | -23.05% | 0.06335% | 18880.59 | 24537.23 | -5656.64 | 2012-10-01 | 2013-09-30 | 2012-05-07 | 5 | 2012-05-31 | 5
| 050.30252 | PRP.2736.4TH ST REPL | PRP.2736.4TH 2ND & MAIN ST REPL | -2701.47 | 546533.86 | -30771.76 | -5.63% | 1.73% | 515762.1 | 546533.86 | -30771.76 | 2012-10-01 | 2013-09-30 | 2012-04-25 | 4 | 2012-09-28 | 9
| 050.30290 | 2738.GRN.HP RELO SUMMERSVILL | RELOCATE 4in STEEL HP LINE IN SUMMERSVILLE | 16342.17 | 23031.8 | -999.22 | -4.338% | 0.07392% | 22032.58 | 23031.8 | -999.22 | 2012-10-01 | 2013-09-30 | 2012-03-01 | 3 | 2013-03-01 | 3
| 050.30318 | 050.2636.Poly Tapping Machine | Purchase Poly tapping machine enabling us to side tap Poly pipe without by -passing and squeezing off main. | -7.54 | 20747.94 | -468.9 | -2.26% | 0.06804% | 20279.04 | 20747.94 | -468.9 | 2012-10-01 | 2013-09-30 | 2012-04-25 | 4 | 2012-09-28 | 9
| 050.30328 | 050.2636.Payton Place | Install approximately 2417 ft 2 Inch PE to serve 28 residential lots | -289.55 | 11859.42 | 2658.39 | 22.42% | 0.04871% | 14517.81 | 11859.42 | 2658.39 | 2012-10-01 | 2013-09-30 | 2012-05-01 | 5 | 2012-09-28 | 9
| 050.30345 | PRP.2735 PARK CITY | PRP.2735 PARK CITY | 296253.65 | 0 |  |  | 2.503% | 745917.17 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2012-04-23 | 4 | 2013-02-28 | 2
| 050.30400 | PRP.2734.N Main 2 Bare Replc | Replace 70 ft. of 2 inch Bare - N. Main - Franklin | 1179.61 | 4520.4 | -3340.79 | -73.9% | 0.003958% | 1179.61 | 4520.4 | -3340.79 | 2012-10-01 | 2013-09-30 | 2012-04-20 | 4 | 2012-09-28 | 9
| 050.30401 | PRP.2734.MillSt.atLincoln-AUB | Replace 35 ft. of 2 inch bare - Mill St. at Lincoln - Auburn | 393.28 | 2809.37 | -2028.5 | -72.2% | 0.00262% | 780.87 | 2809.37 | -2028.5 | 2012-10-01 | 2013-09-30 | 2012-04-19 | 4 | 2012-09-28 | 9
| 050.30565 | 050.2736.TB 2 Reg. Replacement | Replace dated 2" Axel Flow regulators with 4" Mooney Regs. | 12063.49 | 58944.31 | -178.76 | -0.3033% | 0.1972% | 58765.55 | 58944.31 | -178.76 | 2012-10-01 | 2013-09-30 | 2012-06-01 | 6 | 2012-09-28 | 9
| 050.30574 | PRP.2735.Duke-2nd-Cave City | 9 ft. 4 ich Bare Replc. Duke - 2nd - Cave City | 1182.37 | 3692.22 | -2509.85 | -67.98% | 0.003967% | 1182.37 | 3692.22 | -2509.85 | 2012-10-01 | 2013-09-30 | 2012-04-30 | 4 | 2012-09-28 | 9
| 050.30578 | 2739.MT EDEN REG REPLACEMENT | INSTALL 4in PE AND REGULATOR STATION TO REPLACE 4 OTHER STATIONS FEEDING EAST OF MT EDEN ROAD NORTH OF I-64 | -974.14 | 119707.15 | 2732.38 | 2.283% | 0.4108% | 122439.53 | 119707.15 | 2732.38 | 2012-10-01 | 2013-09-30 | 2012-05-01 | 5 | 2013-05-01 | 5
| 050.30630 | 2739.CLOVERBROOK SEC 3b | INSTALL 2in PE FOR 25 LOTS | 9402.28 | 10039.15 | 1392.48 | 13.87% | 0.03835% | 11431.63 | 10039.15 | 1392.48 | 2012-10-01 | 2013-09-30 | 2012-05-01 | 5 | 2013-05-01 | 5
| 050.30730 | 050.2637.Lightfoot Rd Ext | Install 340 feet of 2 inch PE for one new and one existing residential customer. | 2132.18 | 3001.27 | 5206.33 | 173.5% | 0.02754% | 8207.6 | 3001.27 | 5206.33 | 2012-10-01 | 2013-09-30 | 2012-06-15 | 6 | 2012-08-30 | 8
| 050.30751 | 050.2635.Eddyville TB Relocat | Relocate Eddyville TB to get HPD gas from behind Hotels | -220.27 | 56645.75 | -2963 | -5.231% | 0.1801% | 53682.75 | 56645.75 | -2963 | 2012-10-01 | 2013-09-30 | 2012-05-25 | 5 | 2012-09-28 | 9
| 050.30786 | PRP.2609.Empire Fruithill Rt. | Retire approximately 26,000 ft of 10" Bare Transmission Main | 113.46 | 96323.13 | -56055.18 | -58.19% | 0.1351% | 40267.95 | 96323.13 | -56055.18 | 2012-10-01 | 2013-09-30 | 2012-01-16 | 1 | 2012-09-30 | 9
| 050.30792 | 050.2635.Butt Fuse Machine | Purchase Butt Fuse Machine for Princeton | -7.54 | 4702 | 210.6 | 4.479% | 0.01648% | 4912.6 | 4702 | 210.6 | 2012-10-01 | 2013-09-30 | 2012-05-24 | 5 | 2012-09-24 | 9
| 050.30863 | 050.2734.northridge VI | 2 inch PE Extension - Northridge VI | 4949 | 10147.78 | -5198.78 | -51.23% | 0.0166% | 4949 | 10147.78 | -5198.78 | 2012-10-01 | 2013-09-30 | 2012-06-04 | 6 | 2012-09-28 | 9
| 050.30889 | 050.2636.Deer Valley 2 | Install 1174 ft 2 Inch PE and 451 ft 4 PE to serve 30 residential customers | -11.31 | 13136.54 | 2785.86 | 21.21% | 0.05342% | 15922.4 | 13136.54 | 2785.86 | 2012-10-01 | 2013-09-30 | 2012-06-10 | 6 | 2012-09-28 | 9
| 050.30956 | PRP.2734.CREASON-MARYLAN | PRP.2734.CREASON-MARYLAN | -72.01 | 0 |  |  | 0.4821% | 143702.72 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2012-09-28 | 9 | 2012-09-28 | 9
| 050.30962 | 050.2734.NSunrise 2 inch repl | Replace 2" Epoxy Main in conjunction with City storm drain install | -229.17 | 19139.11 | -9110.03 | -47.6% | 0.03365% | 10029.08 | 19139.11 | -9110.03 | 2012-10-01 | 2013-09-30 | 2012-07-02 | 7 | 2012-09-28 | 9
| 050.31037 | 050.2638.Dana Lane Ext | Install 100 feet of 2 inch PE for one new residential customer | -3.25 | 1213.75 | -238.81 | -19.68% | 0.003271% | 974.94 | 1213.75 | -238.81 | 2012-10-01 | 2013-09-30 | 2012-06-25 | 6 | 2012-07-29 | 7
| 050.31061 | 050.2638.McGuire Rd Relocate | Lower 550 feet of 2 inch PE main | 29.95 | 3531.38 | 2580.65 | 73.08% | 0.02051% | 6112.03 | 3531.38 | 2580.65 | 2012-10-01 | 2013-09-30 | 2012-07-02 | 7 | 2012-08-30 | 8
| 050.31066 | PRP.2638. Mayfield 2012 | PRP.2638. Mayfield 2012 | 115489.49 | 267423.93 | 34760.23 | 13% | 1.014% | 302184.16 | 267423.93 | 34760.23 | 2012-10-01 | 2013-09-30 | 2012-06-30 | 6 | 2012-09-29 | 9
| 050.31248 | PRP.2636.BOSLEY & GRIFFITH | PRP.2636.BOSLEY & GRIFFITH | 119374.38 | 271619.4 | 20711.42 | 7.625% | 0.9808% | 292330.82 | 271619.4 | 20711.42 | 2012-10-01 | 2013-09-30 | 2012-07-10 | 7 | 2012-09-28 | 9
| 050.31251 | 050.2638.Paris Rd Relocate | Install 160 feet of 2 inch PE, Retire 155 feet of 2 inch steel. | -1.48 | 2771.47 | -1636.41 | -59.04% | 0.003808% | 1135.06 | 2771.47 | -1636.41 | 2012-10-01 | 2013-09-30 | 2012-07-16 | 7 | 2012-09-26 | 9
| 050.31254 | 050.2635.Seven Springs | Install | 5546.34 | 99437.89 | -554.95 | -0.5581% | 0.3318% | 98882.94 | 99437.89 | -554.95 | 2012-10-01 | 2013-09-30 | 2012-06-20 | 6 | 2012-09-28 | 9
| 050.31259 | 050.2638.Charles Dr Ext | Install 400 feet of 2 inch PE for one new commercial customer. | -169.7 | 1956.34 | 552.88 | 28.26% | 0.008419% | 2509.22 | 1956.34 | 552.88 | 2012-10-01 | 2013-09-30 | 2012-07-30 | 7 | 2012-09-28 | 9
| 050.31261 | 050.2635.Industrial Dr. | Install 700 ft 2 Inch Pe to serve 1 commercial Customer. | 835.49 | 623.14 | -1268.1 | -203.5% | -0.002164% | -644.96 | 623.14 | -1268.1 | 2012-10-01 | 2013-09-30 | 2011-11-30 | 11 | 2012-09-28 | 9
| 050.31275 | 050.2636.Burton Rd. | Install 210 ft 2 Inch PE | -19.04 | 1584.39 | -1129.94 | -71.32% | 0.001525% | 454.45 | 1584.39 | -1129.94 | 2012-10-01 | 2013-09-30 | 2012-05-25 | 5 | 2012-09-28 | 9
| 050.31323 | 050.2634.Hwy 262 | Install 900 Ft. 2 Inch PE. to serve new County Garage | -645.44 | 6289.19 | -2611.21 | -41.52% | 0.01234% | 3677.98 | 6289.19 | -2611.21 | 2012-10-01 | 2013-09-30 | 2012-05-01 | 5 | 2012-09-28 | 9
| 050.31329 | 050.2636.Palomino Place 2 | Install | -107.11 | 3429.31 | -891.41 | -25.99% | 0.008515% | 2537.9 | 3429.31 | -891.41 | 2012-10-01 | 2013-09-30 | 2012-07-01 | 7 | 2012-09-28 | 9
| 050.31339 | 050.2734.Oak Hills Dr. Ext | 200 ft. of 2 ich PE - Oak Hills Dr. - Franklin | -207.36 | 17955.7 | -11175.58 | -62.24% | 0.02275% | 6780.12 | 17955.7 | -11175.58 | 2012-10-01 | 2013-09-30 | 2012-03-19 | 3 | 2012-09-28 | 9
| 050.31389 | 050.2734.Warehouse-Lot-Russ. | Purchase lot and building for New Atmos Warehouse in Russellville KY. Lot is located in the Thurston Commercial Development on the corner of Thurston and Fisher in Russellville | 89155.12 | 181315.2 | 40306.35 | 22.23% | 0.7436% | 221621.55 | 181315.2 | 40306.35 | 2012-10-01 | 2013-09-30 | 2012-05-24 | 5 | 2012-09-28 | 9
| 050.31419 | 050.2638.Casablanca Ext | Install 115 feet of 2 inch PE for two new residenetial lots | -39.52 | 1476.59 | -562.85 | -38.12% | 0.003066% | 913.74 | 1476.59 | -562.85 | 2012-10-01 | 2013-09-30 | 2012-08-28 | 8 | 2012-09-28 | 9
| 050.31446 | 2736.Fence @ 19th&Woodmill | Replace security fence around regulator station at 19th & Woodmill in Hopkinsville, KY | -36.52 | 8760.89 | -473.89 | -5.409% | 0.0278% | 8287 | 8760.89 | -473.89 | 2012-10-01 | 2013-09-30 | 2012-08-01 | 8 | 2012-08-31 | 8
| 050.31466 | 050.2636.Industial Dr. | Relocate Reg station that is falling into ditch City of Owensboro is reworking the ditch also install new reg station and make tie back into HPD in front of Swedish Match installing approximately 1700 ft 4 Inch Stl and 200 ft 4 Inch PE | 35413.48 | 159559.9 | -7642.91 | -4.79% | 0.5097% | 151916.99 | 159559.9 | -7642.91 | 2012-10-01 | 2013-09-30 | 2012-08-01 | 8 | 2013-07-08 | 7
| 050.31509 | 2739.LOCUST CRK 9a 2012 | INSTALL 2in PE IN LOCUST CREEK SECTION 9a | 14720.46 | 9562.4 | 5315.04 | 55.58% | 0.04992% | 14877.44 | 9562.4 | 5315.04 | 2012-10-01 | 2013-09-30 | 2012-08-01 | 8 | 2013-08-01 | 8
| 050.31529 | PRP.2636.Allen St. Alley | Replace 51 ft Bare 2 Inch Stl due to River Front Renovation | 9190.12 | 4582.81 | 4993.7 | 109% | 0.03213% | 9576.51 | 4582.81 | 4993.7 | 2012-10-01 | 2013-09-30 | 2012-08-10 | 8 | 2012-09-28 | 9
| 050.31536 | 050.2634.Hwy 425 | Install 1100 Ft. 2 Inch PE to serve two Commercial customers | -698.6 | 5245.76 | 562.17 | 10.72% | 0.01949% | 5807.93 | 5245.76 | 562.17 | 2012-10-01 | 2013-09-30 | 2012-07-15 | 7 | 2012-09-28 | 9
| 050.31556 | 050.2637.Ogilvie Ave Ext | Install 350 feet of 2 inch PE for seven new residential duplexes. | 758.4 | 2472.64 | -1714.24 | -69.33% | 0.002545% | 758.4 | 2472.64 | -1714.24 | 2012-10-01 | 2013-09-30 | 2012-08-14 | 8 | 2012-09-28 | 9
| 050.31561 | 2738.CAM.WOODLAND HEIGHT 2012 | INSTALL 3400ft OF 2in PE FOR SUBDIVISION | -79.92 | 8794.12 | -2165.57 | -24.63% | 0.02224% | 6628.55 | 8794.12 | -2165.57 | 2012-10-01 | 2013-09-30 | 2011-12-01 | 12 | 2012-12-01 | 12
| 050.31601 | 050.2636.Winning Colors Way | Install 270 Ft 2 Inch PE to serve 11 residential lots | -153.21 | 3357.72 | -1467.34 | -43.7% | 0.006342% | 1890.38 | 3357.72 | -1467.34 | 2012-10-01 | 2013-09-30 | 2012-07-25 | 7 | 2012-09-28 | 9
| 050.31615 | 050.2602.Laptop and Desktop 2 | Purchase and retire Desktop and Laptop computers | 38205.08 | 60269.43 | -7910.62 | -13.13% | 0.1757% | 52358.81 | 60269.43 | -7910.62 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 10 | 2013-10-31 | 10
| 050.31634 | 050.2736.Control Valve Rplmt. | Replace Control Valve at Hopkinsville Purchase Regulator is no loner operational, and beyond repair. | 36283.38 | 36844.31 | -560.93 | -1.522% | 0.1217% | 36283.38 | 36844.31 | -560.93 | 2012-10-01 | 2013-09-30 | 2011-11-03 | 11 | 2012-09-30 | 9
| 050.31653 | 050.2734.Three Springs Reloc. | 1575 ft of 4 inch PE - 430 ft. 0f 2 inch PE - Three Springs Rd. | 358482.12 | 245143.23 | 136881.44 | 55.84% | 1.282% | 382024.67 | 245143.23 | 136881.44 | 2012-10-01 | 2013-09-30 | 2012-07-09 | 7 | 2012-12-31 | 12
| 050.31669 | 050.2734.Oak Ridge Replc. | 680 ft. of 2 inch PE on Broadway to replace existimg 2 inchac 3aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa | -522.28 | 10841.62 | -4499.9 | -41.51% | 0.02128% | 6341.72 | 10841.62 | -4499.9 | 2012-10-01 | 2013-09-30 | 2012-08-06 | 8 | 2012-12-31 | 12
| 050.31690 | 050.2734.S.Glen Ext. | Estimate SouthGlen - 7035 ft -4 inch - 9665 ft -2 inch | -12388.09 | 18685 | -14799.53 | -79.21% | 0.01304% | 3885.47 | 18685 | -14799.53 | 2012-10-01 | 2013-09-30 | 2012-06-25 | 6 | 2012-09-28 | 9
| 050.31691 | 050.2734.Springfield VII-A | 2 inch PE Extension - Springfield VII-A - B.G. | 1457.89 | 6360.17 | -28.5 | -0.4481% | 0.02124% | 6331.67 | 6360.17 | -28.5 | 2012-10-01 | 2013-09-30 | 2012-08-10 | 8 | 2012-12-31 | 12
| 050.31693 | PRP.2734.FAIR ST | FAIR ST FROM GLEN LILY TO 10TH | 182993.7 | 0 |  |  | 0.787% | 234556.24 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2012-12-31 | 12 | 2012-12-31 | 12
| 050.31726 | PRP.2636.FORD & GRIFFITH PL W | PRP.2636.FORD & GRIFFITH PL W | 95248.47 | 161001.17 | 34662.45 | 21.53% | 0.6565% | 195663.62 | 161001.17 | 34662.45 | 2012-10-01 | 2013-09-30 | 2012-08-21 | 8 | 2012-09-28 | 9
| 050.31735 | 050.009.OMU Uprate 040.11988 | Project to capture entries that need to be made related to the Owensboro Municipal Utilities Uprate Project 040.11988 unitized in Aug 2004. This project was to install Msmt and regulation equipment to uprate approximately 194,557 feet of 6 & 8 inch pipeli | -129026.5 | 10000 | -4498.5 | -44.98% | 0.01846% | 5501.5 | 10000 | -4498.5 | 2012-10-01 | 2013-09-30 | 2012-08-22 | 8 | 2013-03-31 | 3
| 050.31804 | PRP.2636.18th and Allen St. | Retire 78 ft 4 Inch Bare Stl. Due to leak in intersection | -418.19 | 4218.84 | -665.46 | -15.77% | 0.01192% | 3553.38 | 4218.84 | -665.46 | 2012-10-01 | 2013-09-30 | 2012-08-14 | 8 | 2012-09-28 | 9
| 050.31830 | PRP.2735 WEST HORSE CAVE | PRP.2735 WEST HORSE CAVE | 351781.95 | 538008.43 | -163841.58 | -30.45% | 1.255% | 374166.85 | 538008.43 | -163841.58 | 2012-10-01 | 2013-09-30 | 2012-08-27 | 8 | 2012-12-31 | 12
| 050.31833 | PRP.2738.AIPORT RD.LEB.SPR | RELOCATE BARE STEEL GAS MAIN FOR AIRPORT EXPANSION | 7976.66 | 19547.72 | 9662.44 | 49.43% | 0.098% | 29210.16 | 19547.72 | 9662.44 | 2012-10-01 | 2013-09-30 | 2012-05-01 | 5 | 2013-05-01 | 5
| 050.31855 | PRP.2736.E 4th. and Brown St. | Replace 377 ft 4 Inch LP Stl. Bare main with 2 Inch PE IP. approximately 5 residerntial customers involved | 15593.62 | 17286.31 | 0 | 0% | 0.058% | 17286.31 | 17286.31 | 0 | 2012-10-01 | 2013-09-30 | 2012-09-01 | 9 | 2012-09-28 | 9
| 050.31863 | 050.2638.Leah Way Ext II | Install 50 feet of 2 inch poly main for one new residential customer requesting gas sevice. ` | 593.45 | 1216.9 | -623.45 | -51.23% | 0.001991% | 593.45 | 1216.9 | -623.45 | 2012-10-01 | 2013-09-30 | 2012-09-10 | 9 | 2012-09-12 | 9
| 050.31914 | 050.2734.WestStBare Replc. | 3 inch Bare Steel Replc. - Franklin | 6260.71 | 12579.19 | -3361.29 | -26.72% | 0.03093% | 9217.9 | 12579.19 | -3361.29 | 2012-10-01 | 2013-09-30 | 2012-08-06 | 8 | 2012-12-31 | 12
| 050.31922 | 055.2734.Main - Wrenwood 2 in | 1200 ft. of 2 inch PE - Main to Wrenwood - Auburn | 2431.75 | 1947.87 | 2415.26 | 124% | 0.01464% | 4363.13 | 1947.87 | 2415.26 | 2012-10-01 | 2013-09-30 | 2012-04-30 | 4 | 2012-09-28 | 9
| 050.31956 | 050.2637.Clinton Rd Relocate | 4 inch PE gas main exposed in large creek. Not only exposed, app. 30 feet simply hanging in the air. | 259.63 | 23200.52 | -106.72 | -0.46% | 0.07748% | 23093.8 | 23200.52 | -106.72 | 2012-10-01 | 2013-09-30 | 2012-09-13 | 9 | 2012-09-28 | 9
| 050.32020 | PRP.2737.HAR.BROADWAY-MAGNOLI | PRP.2737.HAR.BROADWAY-MAGNOLIA | 498418.6 | 176977.21 | 321441.39 | 181.6% | 1.672% | 498418.6 | 176977.21 | 321441.39 | 2012-10-01 | 2013-09-30 | 2012-09-14 | 9 | 2013-10-01 | 10
| 050.32021 | 2739.MEADOWBROOK SEC 3 PH 3 | INSTALL 2in PE IN SECTION 3 PHASE 3 ON OAKVIEW DRIVE | 5611.83 | 9663.74 | -4051.91 | -41.93% | 0.01883% | 5611.83 | 9663.74 | -4051.91 | 2012-10-01 | 2013-09-30 | 2012-09-01 | 9 | 2013-09-01 | 9
| 050.32025 | 050.2636.River Rd. | Install 500 ft. 2 Inch PE to serve air handlers for water treatment plant | 3730.6 | 961.77 | 3559.61 | 370.1% | 0.01517% | 4521.38 | 961.77 | 3559.61 | 2012-10-01 | 2013-09-30 | 2012-09-24 | 9 | 2013-02-14 | 2
| 050.32027 | 050.2609.Hawesville Reg Sta. | Project to install a regulator station allowing the regulation of gas on the 6 Inch SP leg of PIM 9016200 leading to Century Aluminum and Southwire. | 82357.14 | 87052.73 | -4695.59 | -5.394% | 0.2763% | 82357.14 | 87052.73 | -4695.59 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2013-09-28 | 9
| 050.32038 | PRP.2635.Marion.W Belleville | PRP.2635.Marion.W Belleville St | 221230.8 | 0 |  |  | 0.7423% | 221230.8 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-09-28 | 9 | 2013-09-28 | 9
| 050.32054 | 050.2636.Hospital Loop Ext. | Install 1493 Ft 4 Inch PE to serve new Medical Office Building | 8121.13 | 1573.92 | 7312.12 | 464.6% | 0.02981% | 8886.04 | 1573.92 | 7312.12 | 2012-10-01 | 2013-09-30 | 2012-09-27 | 9 | 2013-09-28 | 9
| 050.32074 | 050.2736.PRP.Smith St | Replace 2 and 4 Inch Bare Stl. LP Main with 500 ft. of 2 Inch IP PE, approximately 6 customers invovled active leaks on this pipe. | 18414.93 | 18901.66 | -486.73 | -2.575% | 0.06178% | 18414.93 | 18901.66 | -486.73 | 2012-10-01 | 2013-09-30 | 2012-11-05 | 11 | 2013-09-28 | 9
| 050.32136 | 2739.LAW.EAGLE LAKE 2012 | INSTALL 2in PE FOR EAGLE LAKE EXPANSION | 91.6 | 867.92 | -776.32 | -89.45% | 0.0003073% | 91.6 | 867.92 | -776.32 | 2012-10-01 | 2013-09-30 | 2012-07-01 | 7 | 2013-11-01 | 11
| 050.32145 | PRP.2636. BIRKHEAD AVE | PRP.2636. BIRKHEAD AVE | 320674.33 | 345481.83 | -24807.5 | -7.181% | 1.076% | 320674.33 | 345481.83 | -24807.5 | 2012-10-01 | 2013-09-30 | 2012-09-24 | 9 | 2013-09-28 | 9
| 050.32147 | 050.2636.W 13th. St. | Install 200 ft 2 Inch PE to serve 1 residential customer | 2507.97 | 1270.8 | 1237.17 | 97.35% | 0.008414% | 2507.97 | 1270.8 | 1237.17 | 2012-10-01 | 2013-09-30 | 2012-09-28 | 9 | 2013-09-28 | 9
| 050.32412 | PRP.2635.Marion.South Main St | PRP.2635.Marion.South Main St | 265970.9 | 0 |  |  | 0.8924% | 265970.9 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-09-28 | 9 | 2013-09-28 | 9
| 050.32561 | 050.2636.Hwy 189 | Install 920 ft 2 Inch PE to serve new Pogue Car Dealership on the Ky 189 bypass | 10646.41 | 7385.31 | 3261.1 | 44.16% | 0.03572% | 10646.41 | 7385.31 | 3261.1 | 2012-10-01 | 2013-09-30 | 2012-09-25 | 9 | 2013-09-28 | 9
| 050.32595 | 050.2734.Lovers Ln. Ext. | 6 inch PE Ext. at Traditions | 10606.95 | 21994.63 | -11387.68 | -51.77% | 0.03559% | 10606.95 | 21994.63 | -11387.68 | 2012-10-01 | 2013-09-30 | 2012-09-01 | 9 | 2012-12-31 | 12
| 050.32601 | PRP.2734.E 4TH MAIN REPL | From S. Spring St. to the creek | 85899.76 | 0 |  |  | 0.2882% | 85899.76 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-09-28 | 9 | 2013-09-28 | 9
| 050.32626 | 050.2653.GIS Equipment | Purchase GIS equipment | 19379.69 | 19311.22 | 68.47 | 0.3546% | 0.06502% | 19379.69 | 19311.22 | 68.47 | 2012-10-01 | 2013-09-30 | 2012-10-22 | 10 | 2013-01-31 | 1
| 050.32653 | 050.2637.Princess Jennifer II | Install 250 feet of 2 inch PE for one existing customer converting from propane. | 4167.5 | 1776.37 | 2391.13 | 134.6% | 0.01398% | 4167.5 | 1776.37 | 2391.13 | 2012-10-01 | 2013-09-30 | 2012-11-01 | 11 | 2012-12-31 | 12
| 050.32671 | 050.2637.Triangle Ave Ext | Install 225 feet of 2 inch PE for one existing customer converting from propane | 1920.89 | 1346.63 | 574.26 | 42.64% | 0.006445% | 1920.89 | 1346.63 | 574.26 | 2012-10-01 | 2013-09-30 | 2012-10-29 | 10 | 2012-12-31 | 12
| 050.32672 | 2738.LEB.MLK Jr ST.RETIREMENT | RETIRE THIS SECTION OF MAIN DUE TO LEAKS AND NO SERVICES OFF OF THIS SECTION. PRP MAIN REPLACEMENT WILL TAKE CARE OF THIS SECTION AS MAIN ON OTHER SIDE OF STREET TO BE REPLACED WITH PRP PROJECT IN THE FUTURE | 1879.56 | 1097.14 | 782.42 | 71.31% | 0.006306% | 1879.56 | 1097.14 | 782.42 | 2012-10-01 | 2013-09-30 | 2012-10-25 | 10 | 2013-10-25 | 10
| 050.32676 | 050.2735.AUTUMN RIDGE | 6136 ft, of 2 inch PE - Autumn Ridge Sub. | 162675.72 | 79855 | 82820.72 | 103.7% | 0.5458% | 162675.72 | 79855 | 82820.72 | 2012-10-01 | 2013-09-30 | 2012-10-29 | 10 | 2013-09-28 | 9
| 050.32688 | 050.2609.St.Charles Wells | Workover 5 wells at St Charles Storage Field. | 985978.05 | 977316.46 | 8661.59 | 0.8863% | 3.308% | 985978.05 | 977316.46 | 8661.59 | 2012-10-01 | 2013-09-30 | 2012-10-30 | 10 | 2013-09-28 | 9
| 050.32690 | 050.2609.Pipe Locator | Purchase Metro -Tech pipe locator | 4831.64 | 4464.81 | 366.83 | 8.216% | 0.01621% | 4831.64 | 4464.81 | 366.83 | 2012-10-01 | 2013-09-30 | 2012-10-30 | 10 | 2013-09-28 | 9
| 050.32694 | 050.2638.Meadows Subd IV | Install 175 feet of 2 inch PE for one new residential customer (George McAlpin) requesting gas service. | 1355.57 | 967.27 | 388.3 | 40.14% | 0.004548% | 1355.57 | 967.27 | 388.3 | 2012-10-01 | 2013-09-30 | 2012-11-12 | 11 | 2013-09-28 | 9
| 050.32695 | 050.2602.CSS Computers | Purchase Tough book computers for CSS training/ replace older units with these once training is complete | 136865.13 | 130251.18 | 6613.95 | 5.078% | 0.4592% | 136865.13 | 130251.18 | 6613.95 | 2012-10-01 | 2013-09-30 | 2012-10-31 | 10 | 2013-09-28 | 9
| 050.32701 | 050.2612.RMLD | Purchase RMLD leak detector | 21715.74 | 21713.15 | 2.59 | 0.01193% | 0.07286% | 21715.74 | 21713.15 | 2.59 | 2012-10-01 | 2013-09-30 | 2012-11-01 | 11 | 2013-09-28 | 9
| 050.32704 | PRP.2734.State St Repl | Replace and Convert LP to IP | 491325.63 | 0 |  |  | 1.648% | 491325.63 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-07-31 | 7 | 2015-09-30 | 9
| 050.32716 | 050.2612.WMR Equipment | Purchase Wireless Meter reading equipment | 45171.06 | 42089.37 | 3081.69 | 7.322% | 0.1516% | 45171.06 | 42089.37 | 3081.69 | 2012-10-01 | 2013-09-30 | 2012-11-01 | 11 | 2013-09-28 | 9
| 050.32719 | MEC Forfeiture 040.10129 | MEC Forfeiture referring back to MEC Proj#040.10129- Craig Clark task 10768-01 and J. James Properties Inc. task 10758-01 | -2211.38 | -2211.38 | 0 | 0% | -0.007419% | -2211.38 | -2211.38 | 0 | 2012-10-01 | 2013-09-30 | 2012-10-31 | 10 | 2015-10-31 | 10
| 050.32747 | 050.2634.Bruest Heaters 2013 | Purchase and retire Bruest Heaters for Dixon and Earlington | 7363.36 | 10977.82 | -3614.46 | -32.93% | 0.0247% | 7363.36 | 10977.82 | -3614.46 | 2012-10-01 | 2013-09-30 | 2012-11-05 | 11 | 2013-09-28 | 9
| 050.32769 | PRP.2736.MECHANIC St. | PRP.2736.MECHANIC St. | 194099.48 | 193663.35 | 436.13 | 0.2252% | 0.6512% | 194099.48 | 193663.35 | 436.13 | 2012-10-01 | 2013-09-30 | 2012-10-30 | 10 | 2013-09-28 | 9
| 050.32775 | PRP.2609.Fruithill to Hoptown | Replace approximately 25000 Ft 10 Inch 6 Inch Bare Stl. with 12 Inch Stl. | 4948825.76 | 5708987.47 | -760161.71 | -13.32% | 16.6% | 4948825.76 | 5708987.47 | -760161.71 | 2012-10-01 | 2013-09-30 | 2012-10-28 | 10 | 2015-09-30 | 9
| 050.32779 | 050.2636.Fair Haven. | Install 688' 2 Inch PE | 6791.8 | 6270.23 | 521.57 | 8.318% | 0.02279% | 6791.8 | 6270.23 | 521.57 | 2012-10-01 | 2013-09-30 | 2012-11-15 | 11 | 2013-09-28 | 9
| 050.32800 | 2739.SHV.2013 EQUIPMENT | DPIR, LEAK EQUIPMENT RMLD, SENSIT SMART CAL STATION | 60321.06 | 57449.64 | 2871.42 | 4.998% | 0.2024% | 60321.06 | 57449.64 | 2871.42 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.32806 | 2737.DANVILLE.EQUIPMENT.2013 | LEAK EQUIPMENT DPIR, LEAK EQUIPMENT RMLD, SMALL TOOLS, LOCATORS, SENSITS, TRAILER | 87598.26 | 87161.53 | 436.73 | 0.5011% | 0.2939% | 87598.26 | 87161.53 | 436.73 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2014-09-30 | 9
| 050.32807 | 2738.CVILLE.EQUIPMENT.2013 | LEAK EQUIPMENT DPIR, LEAK EQUIPMENT RMLD, AIR MOLE, 12in BACKHOE BUCKET, GATOR TRAILER | 58840.19 | 53642.64 | 5197.55 | 9.689% | 0.1974% | 58840.19 | 53642.64 | 5197.55 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.32813 | PRP.2737.LAN.PURCHASE ST OUT | LEAK ON 4in ST CROSSING HWY 27 - PROPOSE TO REPLACE WITH 6in THICK WALL POWERCRETE PIPE | 47480.3 | 33821.63 | 13658.67 | 40.38% | 0.1593% | 47480.3 | 33821.63 | 13658.67 | 2012-10-01 | 2013-09-30 | 2012-11-01 | 11 | 2015-09-30 | 9
| 050.32818 | 050.2637.McKendree Ext | Install 140 feet of 2 inch PE pipe for one new residential customer (Eathen Flint) requesting natural gas service. | 478.7 | 781.2 | -302.5 | -38.72% | 0.001606% | 478.7 | 781.2 | -302.5 | 2012-10-01 | 2013-09-30 | 2012-12-10 | 12 | 2013-09-28 | 9
| 050.32848 | 050.2635.Commerce St Ext | Install 155 feet of 2 inch PE for a new church that is under construction in Cadiz, KY | 1069.85 | 845.06 | 224.79 | 26.6% | 0.003589% | 1069.85 | 845.06 | 224.79 | 2012-10-01 | 2013-09-30 | 2012-11-12 | 11 | 2012-12-31 | 12
| 050.32882 | 050.2634.Poole Rd. | Install 200Ft 2 Inch PE to serve 1 residential customer | 4251.33 | 1538.61 | 2712.72 | 176.3% | 0.01426% | 4251.33 | 1538.61 | 2712.72 | 2012-10-01 | 2013-09-30 | 2012-11-10 | 11 | 2013-09-28 | 9
| 050.32894 | Schaeffer Rd Reg Replace | Replace existing 2 inch Axial-flo regulators with 2 inch Mooney regulators. Axial-flo regulators continue to leak at the seals resulting in leak calls. | 8113.6 | 7579.23 | 534.37 | 7.05% | 0.02722% | 8113.6 | 7579.23 | 534.37 | 2012-10-01 | 2013-09-30 | 2012-10-12 | 10 | 2015-09-30 | 9
| 050.32897 | 050.2609.Mueller Machine | Purchase 2" Mueller DH-5 Machine and accessories | 13621.05 | 12873.41 | 747.64 | 5.808% | 0.0457% | 13621.05 | 12873.41 | 747.64 | 2012-10-01 | 2013-09-30 | 2012-11-28 | 11 | 2013-09-28 | 9
| 050.32929 | 2737.HUST.WATKINS-GRIFFIN | INSTALL 100ft OF 2in PE AT END OF GRIFFIN TOWARDS WATKINS ON SOUTH SIDE OF ROAD | 1436.46 | 1375.13 | 61.33 | 4.46% | 0.004819% | 1436.46 | 1375.13 | 61.33 | 2012-10-01 | 2013-09-30 | 2012-12-01 | 12 | 2015-09-30 | 9
| 050.32930 | PRP.2737.HAR.COLLEGE-CORNISH | PRP.2737.HAR.NORTH COLLEGE AND CORNISHVILLE RD | 904446.67 | 665397.26 | 239049.41 | 35.93% | 3.035% | 904446.67 | 665397.26 | 239049.41 | 2012-10-01 | 2013-09-30 | 2012-09-14 | 9 | 2015-09-30 | 9
| 050.32960 | 050.2734.Hwy31W Reloc - Frk | Hwy 31W- 1008 to Memorial Reloc. | 155305.7 | 225067.56 | -69761.86 | -31% | 0.5211% | 155305.7 | 225067.56 | -69761.86 | 2012-10-01 | 2013-09-30 | 2012-11-26 | 11 | 2015-09-30 | 9
| 050.32976 | 050.2734.MasseySprings II | 2 inch PE Extension - Massey Springs II - B.G. | 2587.55 | 8006.24 | -5418.69 | -67.68% | 0.008681% | 2587.55 | 8006.24 | -5418.69 | 2012-10-01 | 2013-09-30 | 2012-12-05 | 12 | 2013-09-28 | 9
| 050.32986 | RTU upgrades KY | RTU upgrades for KY stations | 12760.57 | 7177.44 | 5583.13 | 77.79% | 0.04281% | 12760.57 | 7177.44 | 5583.13 | 2012-10-01 | 2013-09-30 | 2012-10-12 | 10 | 2014-09-30 | 9
| 050.32989 | 050.2612 KY Correctors | Electronic correctors for KY | 810.51 | 11165.3 | -10354.79 | -92.74% | 0.002719% | 810.51 | 11165.3 | -10354.79 | 2012-10-01 | 2013-09-30 | 2012-12-06 | 12 | 2013-09-29 | 9
| 050.32990 | 050.2612 TN ECAT Replacement | ECAT replacement units for TN | 19256.56 | 9569.6 | 9686.96 | 101.2% | 0.06461% | 19256.56 | 9569.6 | 9686.96 | 2012-10-01 | 2013-09-30 | 2012-12-06 | 12 | 2013-09-29 | 9
| 050.32998 | 050.2612 ECAT Replacement KY | Replacement units for existing ECATS | 8290.56 | 5741.7 | 2548.86 | 44.39% | 0.02782% | 8290.56 | 5741.7 | 2548.86 | 2012-10-01 | 2013-09-30 | 2012-12-06 | 12 | 2013-09-29 | 9
| 050.33000 | 050.2612 KY YZ Covers | Covers for KY YZ odorizers | 6780.54 | 14354.4 | -7573.86 | -52.76% | 0.02275% | 6780.54 | 14354.4 | -7573.86 | 2012-10-01 | 2013-09-30 | 2012-12-06 | 12 | 2015-09-30 | 9
| 050.33025 | 050.2636.Hwy 2830 | Install 850ft 2 Inch PE to serve 1 residential customer | 1824.99 | 955.81 | 869.18 | 90.94% | 0.006123% | 1824.99 | 955.81 | 869.18 | 2012-10-01 | 2013-09-30 | 2012-12-15 | 12 | 2013-09-28 | 9
| 050.33084 | 2738.EASTPORT RD.2012 | INSTALL 1200ft OF 2in PE MAIN FROM BLUEGRASS DR ALONG EASTPORT ROAD | 1889.09 | 6457.78 | -4568.69 | -70.75% | 0.006338% | 1889.09 | 6457.78 | -4568.69 | 2012-10-01 | 2013-09-30 | 2012-12-15 | 12 | 2015-09-30 | 9
| 050.33087 | PRP.2734.EAST 2ND ST | Replace bare main on 2nd St | 45690.41 | 0 |  |  | 0.1533% | 45690.41 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-05-11 | 5 | 2013-05-11 | 5
| 050.33093 | MEC Forfeiture 040.10129-009 | MEC Forfeiture referring back to MEC 040.10129- 11338 Deer Haven Drive; 10341 Whispering Meadows; 917929 Phillip R. Young; 10620 Creekside Ct.; 917999 Mike Vollman; 10739 Highway 142; 918000 Alan Powers; 10742 Hideway Ct.; 918094 Jay Wise; 10820 Vincent | -35335.05 | -35335.05 | 0 | 0% | -0.1186% | -35335.05 | -35335.05 | 0 | 2012-10-01 | 2013-09-30 | 2012-12-17 | 12 | 2015-09-30 | 9
| 050.33111 | MEC Forfeiture SA 009 | MEC Forfeiture referring back to MEC Proj#040.10129- Phillip R. Young 0917929-01; Hummingbird Ln Hartford 11224-01; Cardinal Investors LLC 10973-01; Greg Smith 0918517-01; Finley's of Danville 10999-01; Jerry Fowler 10211-01 | -22992.81 | -22992.81 | 0 | 0% | -0.07714% | -22992.81 | -22992.81 | 0 | 2012-10-01 | 2013-09-30 | 2012-12-20 | 12 | 2012-12-31 | 12
| 050.33142 | 050.2609.Misc. Equipment | Purchase 1-684 Brown Cutter Bush hog Purchase Aerial Mile Markers | 17541.9 | 16976.28 | 565.62 | 3.332% | 0.05885% | 17541.9 | 16976.28 | 565.62 | 2012-10-01 | 2013-09-30 | 2013-01-04 | 1 | 2015-09-30 | 9
| 050.33143 | 050.2734.Cumberland Ridge V | 1670 ft. of 2 inch PE - Cumberland Ridge V | 5822.46 | 9651.17 | -3828.71 | -39.67% | 0.01953% | 5822.46 | 9651.17 | -3828.71 | 2012-10-01 | 2013-09-30 | 2012-11-15 | 11 | 2015-09-30 | 9
| 050.33144 | PRP Horse Cave SE 2013 | PRP Horse Cave SE 2013 | 408496.01 | 519599.52 | -111103.51 | -21.38% | 1.371% | 408496.01 | 519599.52 | -111103.51 | 2012-10-01 | 2013-09-30 | 2013-01-19 | 1 | 2015-09-30 | 9
| 050.33154 | 050.2734.Vet.Mem and Gordon | Relocate 6 inch Coated Steel - Family Dollar B.G. | 42602.42 | 45208.21 | -2605.79 | -5.764% | 0.1429% | 42602.42 | 45208.21 | -2605.79 | 2012-10-01 | 2013-09-30 | 2012-12-31 | 12 | 2015-09-30 | 9
| 050.33156 | 050.2636.Greenville Office | Construct new Greenville Ky office | 285233.94 | 269445.05 | 15788.89 | 5.86% | 0.957% | 285233.94 | 269445.05 | 15788.89 | 2012-10-01 | 2013-09-30 | 2013-01-04 | 1 | 2013-09-28 | 9
| 050.33220 | PRP.2734.Fairview and High | Replace 4 ich LP Bare - Fairview at High | 9461.23 | 60061.39 | -50600.16 | -84.25% | 0.03174% | 9461.23 | 60061.39 | -50600.16 | 2012-10-01 | 2013-09-30 | 2012-12-19 | 12 | 2015-09-30 | 9
| 050.33222 | 050.2634.Equipment | Purchase 1-fusion machine, 1-2" Mustang squeeze off tool, 2-2" Timberline Squeeze off tools, 1- Smart Cal Kit, 1- Rycom pipelocator. | 16777.03 | 16555.28 | 221.75 | 1.339% | 0.05629% | 16777.03 | 16555.28 | 221.75 | 2012-10-01 | 2013-09-30 | 2013-01-20 | 1 | 2013-09-28 | 9
| 050.33242 | 050.2634.University Circle | Install 550Ft 2 Inch PE to serve 1 residential customer | 3304.35 | 4157.71 | -853.36 | -20.52% | 0.01109% | 3304.35 | 4157.71 | -853.36 | 2012-10-01 | 2013-09-30 | 2012-12-03 | 12 | 2013-09-28 | 9
| 050.33243 | PRP.2634.Daves St. | Retire 375 ft bare 4 Inch stl. low pressure pipe insert with 2 Inch PE IP. | 7362.3 | 19778.86 | -12416.56 | -62.78% | 0.0247% | 7362.3 | 19778.86 | -12416.56 | 2012-10-01 | 2013-09-30 | 2013-02-25 | 2 | 2013-09-28 | 9
| 050.33245 | PRP.2734.9th-Nashville Replc | 400 ft. - bare steel replc. - 9th - Nashville Rd. - Russ | 112750.31 | 47399.99 | 65350.32 | 137.9% | 0.3783% | 112750.31 | 47399.99 | 65350.32 | 2012-10-01 | 2013-09-30 | 2013-01-14 | 1 | 2013-09-28 | 9
| 050.33248 | Valve Changer Kits - 4 each | We are requesting 4 - Valve Changer Kits that include 3/4 inch, 1 inch, & 1 1/4 inch. This tool allows us to safely replace leaking or damaged stopcocks on risers. For use on Service trucks in the Paducah area. | 12336.2 | 14765.34 | -2429.14 | -16.45% | 0.04139% | 12336.2 | 14765.34 | -2429.14 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.33252 | 050.2736.N. Elm St. | Install 485 ft. 2 Inch PE to serve 1 residential customer | 7637.44 | 7741.9 | -104.46 | -1.349% | 0.02562% | 7637.44 | 7741.9 | -104.46 | 2012-10-01 | 2013-09-30 | 2013-02-13 | 2 | 2013-09-28 | 9
| 050.33293 | 050.2736.Hwy 41A | Install 370 ft 4" PE to serve new Commercial customer | 14303.15 | 12689.69 | 1613.46 | 12.71% | 0.04799% | 14303.15 | 12689.69 | 1613.46 | 2012-10-01 | 2013-09-30 | 2013-01-25 | 1 | 2013-09-28 | 9
| 050.33294 | PRP.2734.Auburn Repl 2013 | Main, Park, S Lincoln, Mill, Spring & E. Main | 490408.8 | 714121.99 | -223713.19 | -31.33% | 1.645% | 490408.8 | 714121.99 | -223713.19 | 2012-10-01 | 2013-09-30 | 0013-01-25 | #VALUE! | 2015-09-30 | 9
| 050.33298 | 050.2636.W. 2nd. St. | Install 220 ft 4 Inch PE to serve new Texas Gas building at 610 W 2nd St. | 11431.19 | 10574.8 | 856.39 | 8.098% | 0.03835% | 11431.19 | 10574.8 | 856.39 | 2012-10-01 | 2013-09-30 | 2013-02-05 | 2 | 2013-09-28 | 9
| 050.33323 | Mueller equipment | This is new Mueller equipment for 3/4 inch, 1 inch, & 1 1/4 inch. | 4623.9 | 4229.28 | 394.62 | 9.331% | 0.01551% | 4623.9 | 4229.28 | 394.62 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.33349 | 050.2637.N 6th Relocate | City of Paducah making road improvements, we propose to install 364' of 2 inch PR, abandon 270' of 2 inch MW and 90' of 2 inch PE for a total retirement of 360 feet. No reimbursement | 1141.29 | 4659.21 | -3517.92 | -75.5% | 0.003829% | 1141.29 | 4659.21 | -3517.92 | 2012-10-01 | 2013-09-30 | 2013-04-08 | 4 | 2015-09-30 | 9
| 050.33372 | Purchase of a new R.M.L.D | We are requesting the purchase of a new Heath brand Remote Methane Laser Detector. This equipment will be used for leak surveys in our region including Paducah, Mayfield, and Union City, TN. Our quote from Heath Consultants is $19,000 + $1,140 tx + $250 S | 30141.38 | 28745.87 | 1395.51 | 4.855% | 0.1011% | 30141.38 | 28745.87 | 1395.51 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.33379 | 050.2609.De-Hy Replacements | Replace De-Hy plants at St. Charles and Bon Horbor | 253338.24 | 218700.88 | 34637.36 | 15.84% | 0.85% | 253338.24 | 218700.88 | 34637.36 | 2012-10-01 | 2013-09-30 | 2013-02-05 | 2 | 2015-09-30 | 9
| 050.33385 | 050.2637.Court Ave Ext | Install 90 feet of 2 inch PE for the new Murray State University - Paducah Campus | 1234.23 | 1544.49 | -310.26 | -20.09% | 0.004141% | 1234.23 | 1544.49 | -310.26 | 2012-10-01 | 2013-09-30 | 2013-03-15 | 3 | 2013-06-15 | 6
| 050.33402 | Segway battery and tires | New battery and tires for the Paducah Segway | 3289.17 | 2044.2 | 1244.97 | 60.9% | 0.01104% | 3289.17 | 2044.2 | 1244.97 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.33410 | 2737.JC.HENRY ST 2013 | INSTALL 178ft OF 2in PE TO SERVE ONE COMMERICAL CUSTOMER | 2395.29 | 668.84 | 1726.45 | 258.1% | 0.008036% | 2395.29 | 668.84 | 1726.45 | 2012-10-01 | 2013-09-30 | 2013-03-01 | 3 | 2015-09-30 | 9
| 050.33411 | Equipment for Mayfield | Equipment includes (2) Sensit gas detectors and (1) Valve Changer Kit for 1 1/4 inch and 2 inch. | 8496.34 | 8528.23 | -31.89 | -0.3739% | 0.02851% | 8496.34 | 8528.23 | -31.89 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.33412 | 050.2634.Storage Building | Purchase Storage Building for odorant storage. | 8143.54 | 14290.72 | -6147.18 | -43.02% | 0.02732% | 8143.54 | 14290.72 | -6147.18 | 2012-10-01 | 2013-09-30 | 2013-02-07 | 2 | 2013-02-07 | 2
| 050.33413 | 050.2634.Northern Star Way | Install approximately 5200 ft 4" High Density PE in the 4 Star industrial park in Henderson County. Industrial Board contacting through approved Contractor WHF INC . Atmos will be Inspecting and tying new pipe in to existing Reg Set. | 11299.91 | 7687.81 | 3612.1 | 46.98% | 0.03791% | 11299.91 | 7687.81 | 3612.1 | 2012-10-01 | 2013-09-30 | 2013-02-11 | 2 | 2014-11-30 | 11
| 050.33415 | New pipe locator | We propose to purchase one Subsite Model 910 Receiver/ 950 Transmitter Pipe Locator with (512hz, 1k, 8k, 29k, 80k, 33k, 60hz, 120hz) Cathodic Protection and Carry Bag. 3 Watt Transmitter. Price quote from EGW is $2,750.00 | 3881.79 | 3742.18 | 139.61 | 3.731% | 0.01302% | 3881.79 | 3742.18 | 139.61 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2015-09-30 | 9
| 050.33425 | PRP.2636.Glendale Dr. | Replace 3 Inch bare main crossing that is leaking with 2 Inch PE. | 908.54 | 7245.23 | -6336.69 | -87.46% | 0.003048% | 908.54 | 7245.23 | -6336.69 | 2012-10-01 | 2013-09-30 | 2013-02-05 | 2 | 2013-09-28 | 9
| 050.33480 | 050.2735.C Knicely-68-80 Ext | 800 ft. of 4 inch stl. HPD - Carroll Knicely -- John Deer | 56829.78 | 13905.09 | 42924.69 | 308.7% | 0.1907% | 56829.78 | 13905.09 | 42924.69 | 2012-10-01 | 2013-09-30 | 2012-04-16 | 4 | 2012-09-28 | 9
| 050.33497 | 050.2636.Mooney Pilots & ERX's | Purchase 3 ERX recorders to replace old chart recorders. Purchase 4 Mooney pilots. | 12139.65 | 14298.08 | -2158.43 | -15.1% | 0.04073% | 12139.65 | 14298.08 | -2158.43 | 2012-10-01 | 2013-09-30 | 2013-02-20 | 2 | 2013-09-28 | 9
| 050.33502 | 050.2734.SglenGables Apprch | 10,032 ft of 4 inch HPD Approach Main - S Glen Gables - B.G. | 833808.5 | 393862.41 | 439946.09 | 111.7% | 2.798% | 833808.5 | 393862.41 | 439946.09 | 2012-10-01 | 2013-09-30 | 2013-01-22 | 1 | 2015-09-30 | 9
| 050.33534 | PRP.2734.WOODFORD STA REPL | Woodford,Vine, Wilson, W 11th & W 12th | 267818.89 | 0 |  |  | 0.8986% | 267818.89 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-12-31 | 12 | 2015-09-30 | 9
| 050.33542 | 050.2636.Bourbon Ct. | Install 1611 ft 2 Inch PE to serve 1 commercial customer | 14087.78 | 9773.76 | 4314.02 | 44.14% | 0.04727% | 14087.78 | 9773.76 | 4314.02 | 2012-10-01 | 2013-09-30 | 2013-02-22 | 2 | 2015-09-30 | 9
| 050.33543 | 050.2636.Challenger Ctr. 2 | Install 220 ft 2 Inch PE to serve new Southern Star Central Gas Pipeline Building | 1854.66 | 2145.55 | -290.89 | -13.56% | 0.006223% | 1854.66 | 2145.55 | -290.89 | 2012-10-01 | 2013-09-30 | 2013-04-01 | 4 | 2013-09-28 | 9
| 050.33564 | 050.2636.Silent Doe | Install 100 ft 2 Inch PE to serve 1 residential cuatomer | 1885.03 | 2065.44 | -180.41 | -8.735% | 0.006324% | 1885.03 | 2065.44 | -180.41 | 2012-10-01 | 2013-09-30 | 2013-02-25 | 2 | 2013-09-28 | 9
| 050.33621 | 050.2636.Pleasant Heights Ln. | Retire 1020 ft 2 Inch PE no longer needed to serve Lake Forrest pipe in way of customers new waterline. | 1018.71 | 1585.38 | -566.67 | -35.74% | 0.003418% | 1018.71 | 1585.38 | -566.67 | 2012-10-01 | 2013-09-30 | 2013-03-05 | 3 | 2013-09-28 | 9
| 050.33641 | 050.2736.Lovers Ln. Relo. | Relocate 150 ft 4 Inch PE for road widening | 36412.12 | 39274.35 | -2862.23 | -7.288% | 0.1222% | 36412.12 | 39274.35 | -2862.23 | 2012-10-01 | 2013-09-30 | 2013-03-05 | 3 | 2013-12-28 | 12
| 050.33665 | 2739.LOCUST CRK 9b | INSTALL 2in PE MAIN ON WEYMUTH PLACE 800ft | 8552.65 | 5913.91 | 2638.74 | 44.62% | 0.02869% | 8552.65 | 5913.91 | 2638.74 | 2012-10-01 | 2013-09-30 | 2013-03-01 | 3 | 2014-03-01 | 3
| 050.33690 | 050.2637.Dana Drive Ext | Install 225 feet of 2 inch poly for one exisiting residential customer requesting gas service. | -388.65 | 1541.94 | -1930.59 | -125.2% | -0.001304% | -388.65 | 1541.94 | -1930.59 | 2012-10-01 | 2013-09-30 | 2013-04-01 | 4 | 2013-04-30 | 4
| 050.33723 | 2737.STANFORD TBS REBUILD | REBUILD THE STANFORD TOWN BORDER STATION INSTALLING UPSTREAM AND DOWNSTREAM VALVES | 82253.17 | 82385.21 | -132.04 | -0.1603% | 0.276% | 82253.17 | 82385.21 | -132.04 | 2012-10-01 | 2013-09-30 | 2013-03-01 | 3 | 2014-03-01 | 3
| 050.33729 | 050.2638.The Meadows 5 Ext | Install 1,300 feet of 2 inch poly for 17 new residential lots in this fifth phase of The Meadows Subdivision. | 3497.74 | 6343.44 | -2845.7 | -44.86% | 0.01174% | 3497.74 | 6343.44 | -2845.7 | 2012-10-01 | 2013-09-30 | 2013-05-02 | 5 | 2013-07-28 | 7
| 050.33736 | Squeeze off tool | We would like to purchase a Timberline top side squeeze off tool for use in the Princeton area. | 3122.65 | 2255.7 | 866.95 | 38.43% | 0.01048% | 3122.65 | 2255.7 | 866.95 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2013-09-30 | 9
| 050.33744 | 2738.FEDERAL PLACE 2012 | INSTALL 350ft OF 2in PE FOR NEW CUSTOMER - DOLLAR GENARAL STORE | 1454.54 | 3163 | -1708.46 | -54.01% | 0.00488% | 1454.54 | 3163 | -1708.46 | 2012-10-01 | 2013-09-30 | 2012-11-01 | 11 | 2013-11-01 | 11
| 050.33861 | PRP.2636.ALLEN 1ST - 3RD | PRP.2636.ALLEN 1ST - 3RD | 84725.46 | 72621.28 | 12104.18 | 16.67% | 0.2843% | 84725.46 | 72621.28 | 12104.18 | 2012-10-01 | 2013-09-30 | 2013-04-22 | 4 | 2013-09-28 | 9
| 050.33870 | 050.2637.Estes Lane Ext | Install 230 feet of two inch poly pipe for one customer converting heat from electric. | 3652.26 | 1449.75 | 2202.51 | 151.9% | 0.01225% | 3652.26 | 1449.75 | 2202.51 | 2012-10-01 | 2013-09-30 | 2013-04-22 | 4 | 2013-09-28 | 9
| 050.33969 | 050.2637.Stiles Lndg Ext | Install 370 feet of 2 inch poly main for one new residential customer requesting gas service. | 2188.97 | 4252.8 | -2063.83 | -48.53% | 0.007344% | 2188.97 | 4252.8 | -2063.83 | 2012-10-01 | 2013-09-30 | 2013-05-05 | 5 | 2013-09-28 | 9
| 050.33971 | 050.2636.Beaver Dam Purchase | Replace and repair equipment at Hartford & Beaver Dam purchase due to lighting Strike at Station. | 26163.06 | 34477.68 | -8314.62 | -24.12% | 0.08778% | 26163.06 | 34477.68 | -8314.62 | 2012-10-01 | 2013-09-30 | 2013-04-17 | 4 | 2013-09-28 | 9
| 050.33985 | 050.2609.Ground Beds | Replace depleted ground beds at Kirkwood Springs & Line #176 Highway 85. | 45873.66 | 53738.52 | -7864.86 | -14.64% | 0.1539% | 45873.66 | 53738.52 | -7864.86 | 2012-10-01 | 2013-09-30 | 2013-04-25 | 4 | 2013-09-28 | 9
| 050.33986 | 050.2636.Ground Bed | Replace depleted ground bed Oak St. in Greeenville | 20607.49 | 27525.84 | -6918.35 | -25.13% | 0.06914% | 20607.49 | 27525.84 | -6918.35 | 2012-10-01 | 2013-09-30 | 2013-04-25 | 4 | 2013-09-28 | 9
| 050.34005 | 2737.WALTON AVE-HWY 127 | INSTALL 2in PE TO SERVE LOT 4 ON WALTON AVE - WALMART OUTPARCEL | 2142.12 | 1625.32 | 516.8 | 31.8% | 0.007187% | 2142.12 | 1625.32 | 516.8 | 2012-10-01 | 2013-09-30 | 2012-07-01 | 7 | 2013-07-01 | 7
| 050.34042 | 050.2636.Locust Hill Rd. | Install 661 ft 2 Inch PE to serve 1 residential customer | 4230.44 | 4977.75 | -747.31 | -15.01% | 0.01419% | 4230.44 | 4977.75 | -747.31 | 2012-10-01 | 2013-09-30 | 2013-04-25 | 4 | 2013-09-28 | 9
| 050.34044 | 050.2636.Button Buck Ct. | Install 503 ft 2 Inch PE to serve 1 residential customer | 6258.99 | 5605.69 | 653.3 | 11.65% | 0.021% | 6258.99 | 5605.69 | 653.3 | 2012-10-01 | 2013-09-30 | 2013-05-01 | 5 | 2013-09-28 | 9
| 050.34063 | PRP.2738.KERR-McNARY 2013 | 1/1/2700 | 7918.45 | 0 |  |  | 0.02657% | 7918.45 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-05-01 | 5 | 2013-07-01 | 7
| 050.34066 | PRP.2738.N COLUMBIA-3rd | INSTALL 450ft OF 2in PE TO REPLACE BARE PIPE ON NORTH COLUMBIA AND 3rd STREETS IN CAMPBELLSVILLE | 979.01 | 14361.2 | -13382.19 | -93.18% | 0.003285% | 979.01 | 14361.2 | -13382.19 | 2012-10-01 | 2013-09-30 | 2013-05-01 | 5 | 2014-05-01 | 5
| 050.34077 | 050.2734.MarkTrail Ext. | 590 ft. of 2 inch PE - Mark Trail Bowling Green | 1471.16 | 2449.12 | -977.96 | -39.93% | 0.004936% | 1471.16 | 2449.12 | -977.96 | 2012-10-01 | 2013-09-30 | 2012-08-15 | 8 | 2012-12-31 | 12
| 050.34098 | PRP.2636.W PARRISH AVE_1 | Bare pipe repl on Parrish and south | 549595.46 | 685518.46 | -135923 | -19.83% | 1.844% | 549595.46 | 685518.46 | -135923 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2013-12-01 | 12
| 050.34099 | 050.2636.Silver St. | Install 520 ft 2 Inch PE to serve 1 Commercial customer | 7007.91 | 5016.43 | 1991.48 | 39.7% | 0.02351% | 7007.91 | 5016.43 | 1991.48 | 2012-10-01 | 2013-09-30 | 2013-05-15 | 5 | 2013-09-28 | 9
| 050.34100 | 050.2636.Zion Church Rd. | Relocate 350 ft 2 Inch Pe due to property grade work | 2455.66 | 2550.32 | -94.66 | -3.712% | 0.008239% | 2455.66 | 2550.32 | -94.66 | 2012-10-01 | 2013-09-30 | 2013-05-06 | 5 | 2013-09-28 | 9
| 050.34101 | 050.2636.Oakwood Dr. | Install 500 ft 2 Inch PE to serve | 10728.48 | 4414.47 | 6314.01 | 143% | 0.036% | 10728.48 | 4414.47 | 6314.01 | 2012-10-01 | 2013-09-30 | 2013-05-15 | 5 | 2013-09-28 | 9
| 050.34127 | PRP.2734.AVE OF CHAMPIONS | Replace main along Ave of Champions | 215626.25 | 0 |  |  | 0.7234% | 215626.25 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-09-27 | 9 | 2013-09-27 | 9
| 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | REPLACE RECTIFIER AND GROUND BED IN JUNCTION CITY ON MILL ST | 4202.46 | 19511.4 | -15308.94 | -78.46% | 0.0141% | 4202.46 | 19511.4 | -15308.94 | 2012-10-01 | 2013-09-30 | 2013-05-01 | 5 | 2015-05-01 | 5
| 050.34129 | PRP.2734.W 15TH & STUBBINS | Repl bare main on W 15th & Stubbins | 35226.29 | 0 |  |  | 0.1182% | 35226.29 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-09-27 | 9 | 2013-09-27 | 9
| 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | HUBBLE ROAD STATION REPLACEMENT. INSTALL 1500ft OF 4in PE AND RETIRE MORGANS SUBD STATION 1962 | 32521.39 | 37316.65 | -4795.26 | -12.85% | 0.1091% | 32521.39 | 37316.65 | -4795.26 | 2012-10-01 | 2013-09-30 | 2013-03-01 | 3 | 2015-03-01 | 3
| 050.34184 | 050.2634.Basket Boiler | Install Boiler at Basket Purchase Station | 34156.31 | 58782.52 | -24626.21 | -41.89% | 0.1146% | 34156.31 | 58782.52 | -24626.21 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2013-09-28 | 9
| 050.34186 | 050.2634.Hanson TBS Regs | Replace Rockwell Regs. with Mooney Regs at Hanson TBS. | 12535.35 | 42202.09 | -29666.74 | -70.3% | 0.04206% | 12535.35 | 42202.09 | -29666.74 | 2012-10-01 | 2013-09-30 | 2013-05-28 | 5 | 2013-09-28 | 9
| 050.34206 | 2737.DOWNTOWN LP RETIRE | REITRE THE LP SYSTEM IN DOWNTOWN DANVILLE. IP IS INSTALLED AND ALL METERS HAVE BEEN TRANSFERED OVER TO THE IP LINES | 6099.9 | 9138.25 | -3038.35 | -33.25% | 0.02047% | 6099.9 | 9138.25 | -3038.35 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2014-06-01 | 6
| 050.34224 | 050.2734.Summit Phase III | 2 and 4 inch PE extension - Summit Phase III - B.G. | 19070.7 | 40563.66 | -21492.96 | -52.99% | 0.06398% | 19070.7 | 40563.66 | -21492.96 | 2012-10-01 | 2013-09-30 | 2013-03-04 | 3 | 2013-09-28 | 9
| 050.34225 | 050.2734.Ewing Bend Dr | 185 ft. of 2 inch PE extension Ewing Bend Dr. | 485.11 | 2731.28 | -2246.17 | -82.24% | 0.001628% | 485.11 | 2731.28 | -2246.17 | 2012-10-01 | 2013-09-30 | 2013-05-15 | 5 | 2013-09-28 | 9
| 050.34264 | 2738.CAM.MEADOW CREEK RD | INSTALL 18,500ft OF pe PIPE TO SERVE CHICKEN HOUSES | 38391.56 | 73569.82 | -35178.26 | -47.82% | 0.1288% | 38391.56 | 73569.82 | -35178.26 | 2012-10-01 | 2013-09-30 | 2012-07-01 | 7 | 2013-07-01 | 7
| 050.34293 | 050.2636.Masonville TBS | Replace and upgrade Masonville TBS for Deer Valley Subdivision | 32729.03 | 38023.07 | -5294.04 | -13.92% | 0.1098% | 32729.03 | 38023.07 | -5294.04 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2013-09-28 | 9
| 050.34295 | 050.2634.Basket TBS Relo. | Relocate Basket TBS Station due to Soil erosion at present location | 13006.47 | 28790.67 | -15784.2 | -54.82% | 0.04364% | 13006.47 | 28790.67 | -15784.2 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2013-09-28 | 9
| 050.34322 | 050.2609.Retirement Hwy 62 | This project is for the retirement of 433' 10" Transmission pipe that was replaced on Distribution project 050.21917 in March of 2010. Transmission assets can't be retired on a Distribution project. Once this project is approved Retirement dollars will be | 97184.95 | 99436.5 | -2251.55 | -2.264% | 0.3261% | 97184.95 | 99436.5 | -2251.55 | 2012-10-01 | 2013-09-30 | 2013-05-30 | 5 | 2013-09-28 | 9
| 050.34324 | 2737.HAR.PURCH ODOR REPLACE | REPLACE ORDORIZOR AT THE HARRODSBURG PURCHASE STATION - INSTALL YZ ODORIZOR | 37400.15 | 66681.61 | -29281.46 | -43.91% | 0.1255% | 37400.15 | 66681.61 | -29281.46 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2014-09-30 | 9
| 050.34327 | 2739.CLOVERBROOK 3b-2 2013 | INSTALL 1150 ft OF 2in PE FOR 19 LOTS IN CLOVERBROOK - JOINT TRENCH PROJECT | 899.04 | 11800.11 | -10901.07 | -92.38% | 0.003016% | 899.04 | 11800.11 | -10901.07 | 2012-10-01 | 2013-09-30 | 2013-05-01 | 5 | 2014-05-01 | 5
| 050.34407 | 050.2638.Dana Drive Ext | Install 300 feet of 2 inch PE for seven new residential lots in Koby Court Subdivision. Developer is Steve Lamb. | 1317.65 | 1529.86 | -212.21 | -13.87% | 0.004421% | 1317.65 | 1529.86 | -212.21 | 2012-10-01 | 2013-09-30 | 2013-06-15 | 6 | 2013-09-28 | 9
| 050.34411 | 050.2636.Deer Valley 3 | Install | 36862.89 | 41739.59 | -4876.7 | -11.68% | 0.1237% | 36862.89 | 41739.59 | -4876.7 | 2012-10-01 | 2013-09-30 | 2013-05-17 | 5 | 2013-09-28 | 9
| 050.34448 | PRP.2637.31st Street | City of Paducah making road improvements that include widening. We are abandoning app. 1000 feet of 6 inch bare steel main. Replacing with 6 inch poly pipe. No services affected.. | 55753.25 | 35879.82 | 19873.43 | 55.39% | 0.1871% | 55753.25 | 35879.82 | 19873.43 | 2012-10-01 | 2013-09-30 | 2013-06-17 | 6 | 2013-09-28 | 9
| 050.34454 | 050.2734.Springfield Sub VII- | 2 inch PE Extension - Springfield VII-B | 3856.91 | 5865.71 | -2008.8 | -34.25% | 0.01294% | 3856.91 | 5865.71 | -2008.8 | 2012-10-01 | 2013-09-30 | 2013-06-18 | 6 | 2013-09-28 | 9
| 050.34460 | 050.2636.Lafayette St. | Install 1573 ft 2 Inch PE to serve 38 residential apartments. | 3544.53 | 12046.61 | -8502.08 | -70.58% | 0.01189% | 3544.53 | 12046.61 | -8502.08 | 2012-10-01 | 2013-09-30 | 2013-03-15 | 3 | 2013-09-28 | 9
| 050.34504 | PRP.2609.Fruithill Hoptown Rt | This project is to retire the Trans Pipe that is being repplaced on project 050.32775 new pipe is HPD can't retire Trans assets on Distibution plant projects. | 2280.78 | 73156.12 | -70875.34 | -96.88% | 0.007652% | 2280.78 | 73156.12 | -70875.34 | 2012-10-01 | 2013-09-30 | 2013-06-19 | 6 | 2013-09-28 | 9
| 050.34506 | 050.2609.Hwy 271 Retirement | Project to Retire Trans pipe while installing Reg Station, Station was installed on Distribution plant project, trans plant assets can't be retire on Distribution plant projects. | 359.87 | 1066.48 | -706.61 | -66.26% | 0.001207% | 359.87 | 1066.48 | -706.61 | 2012-10-01 | 2013-09-30 | 2013-06-19 | 6 | 2013-09-28 | 9
| 050.34507 | PRP.2736.VIRGINIA ST | Repl bare main along Virginia & side streets to | 224713.23 | 345660.25 | -120947.02 | -34.99% | 0.7539% | 224713.23 | 345660.25 | -120947.02 | 2012-10-01 | 2013-09-30 | 2013-06-24 | 6 | 2013-09-28 | 9
| 050.34509 | 050.2734.Belle Haven II Ext | 2 inch PE Extension Belle Haven Phase II - B.G. | 5128.2 | 16800.28 | -11672.08 | -69.48% | 0.01721% | 5128.2 | 16800.28 | -11672.08 | 2012-10-01 | 2013-09-30 | 2013-06-04 | 6 | 2013-09-28 | 9
| 050.34515 | 050.2734.Technology Way Ext | 450 ft. - 4 inch steel HPD Ext. - Technology Way - B.G. | 2938.15 | 15868.83 | -12930.68 | -81.48% | 0.009858% | 2938.15 | 15868.83 | -12930.68 | 2012-10-01 | 2013-09-30 | 2013-06-17 | 6 | 2013-09-28 | 9
| 050.34539 | 050.2736.Clinic Dr.Relocation | Relocate approximately 974 ft 4 Inch Stl. and 2 Inch Pe for Clinic Dr. and Hwy 41 widening. | 13301.48 | 26784.97 | -13483.49 | -50.34% | 0.04463% | 13301.48 | 26784.97 | -13483.49 | 2012-10-01 | 2013-09-30 | 2013-04-20 | 4 | 2013-09-28 | 9
| 050.34585 | Reg Replace T.B 2 - Paducah | We propose to install 4" Mooney Regulators, Retire existing 4" Axial flow Regulators at Paducah Town border 2 - Lourdes Hospital. | 29995.49 | 27715.76 | 2279.73 | 8.225% | 0.1006% | 29995.49 | 27715.76 | 2279.73 | 2012-10-01 | 2013-09-30 | 2014-07-15 | 7 | 2014-09-30 | 9
| 050.34596 | 2735.CAVE CITY.OLD LEXINGTON | INSTALL 200ft OF 2in PE ON OLD LEXINGTON RD IN CAVE CITY | 2834.33 | 1503.41 | 1330.92 | 88.53% | 0.009509% | 2834.33 | 1503.41 | 1330.92 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2013-10-01 | 10
| 050.34598 | PRP.2738.SOUTH C-VILLE 2013 | REPLACE 5445ft OF 2in BARE AND 800ft OF 4in BARE STEEL AROUND SOUTH CENTRAL AVE AREA IN CAMPBELLSVILLE | 125426.42 | 606799.55 | -481373.13 | -79.33% | 0.4208% | 125426.42 | 606799.55 | -481373.13 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2014-06-01 | 6
| 050.34600 | 2735.GLASGOW EQUIPMENT 2013 | PURCHASE 1-LINE LOCATOR AND 2-ERX | 12937.51 | 13077.36 | -139.85 | -1.069% | 0.04341% | 12937.51 | 13077.36 | -139.85 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 10 | 2014-09-30 | 9
| 050.34623 | Replace regulators - Cadiz TB | Replace (2) 2" Fisher 299's with (4) 2" Mooney regulators | 13840.47 | 20082.84 | -6242.37 | -31.08% | 0.04644% | 13840.47 | 20082.84 | -6242.37 | 2012-10-01 | 2013-09-30 | 2013-08-01 | 8 | 2013-09-30 | 9
| 050.34635 | 050.2638.Youngblood Dr Ext | Install 225 feet of 2 inch PE for one commercial customerr (Joey Hobbs) | 3228.02 | 2123.99 | 1104.03 | 51.98% | 0.01083% | 3228.02 | 2123.99 | 1104.03 | 2012-10-01 | 2013-09-30 | 2013-07-29 | 7 | 2013-09-28 | 9
| 050.34638 | 050.2736.Millbrooke Relocate | Replace app. 700 feet of 6 inch MW with 6 inch P.E. Existing main is strapped to a bridge, the pipe and it's support structure are in a deteriorated condition. | 89029.73 | 163854.88 | -74825.15 | -45.67% | 0.2987% | 89029.73 | 163854.88 | -74825.15 | 2012-10-01 | 2013-09-30 | 2013-07-15 | 7 | 2013-09-28 | 9
| 050.34639 | 050.2638.Coplen Reg Replace | Replace existing regulator station with 3/4 inch MTDeason station that has 627R regulator | 4652.05 | 9232.67 | -4580.62 | -49.61% | 0.01561% | 4652.05 | 9232.67 | -4580.62 | 2012-10-01 | 2013-09-30 | 2013-07-29 | 7 | 2013-09-28 | 9
| 050.34646 | 050.2634.Retire Dump Truck | Retire company owned Dump Truck Unit # 006565 Vin # 1FDKF37H65EA22719 | 170.62 | -3760.06 | 3930.68 | -104.5% | 0.0005724% | 170.62 | -3760.06 | 3930.68 | 2012-10-01 | 2013-09-30 | 2013-07-10 | 7 | 2013-09-28 | 9
| 050.34691 | 050.2636.Hwy 138 | Install 2200 ft 2 Inch PE to serve 1 residential customer | 5738.1 | 1664 | 4074.1 | 244.8% | 0.01925% | 5738.1 | 1664 | 4074.1 | 2012-10-01 | 2013-09-30 | 2013-07-25 | 7 | 2013-09-28 | 9
| 050.34708 | 2735.ASHKIRK LN 2013 | INSTALL 280' OF 2" PE FOR THREE LOTS ON ASHKIRK LN IN GLASGOW | 652.17 | 2797.89 | -2145.72 | -76.69% | 0.002188% | 652.17 | 2797.89 | -2145.72 | 2012-10-01 | 2013-09-30 | 2013-07-15 | 7 | 2014-07-15 | 7
| 050.34710 | DTEX Odorant Detection System | YZ Systems Inc DTEX Odorant Detection System. Model DX01000G. | 3762.98 | 3883.98 | -121 | -3.115% | 0.01263% | 3762.98 | 3883.98 | -121 | 2012-10-01 | 2013-09-30 | 2012-10-12 | 10 | 2014-09-30 | 9
| 050.34737 | 2739.McCORMICK LN 2013 | INSTALL 230' OF 2" PE ON McCORMICK LN TOWARDS HWY 127 | 4989.52 | 1006.34 | 3983.18 | 395.8% | 0.01674% | 4989.52 | 1006.34 | 3983.18 | 2012-10-01 | 2013-09-30 | 2013-07-01 | 7 | 2013-09-01 | 9
| 050.34756 | Bowling Green Equipment FY2013 | TD Williamson 4 on 6 Tapping Equipment | 29723.67 | 59916.5 | -30192.83 | -50.39% | 0.09973% | 29723.67 | 59916.5 | -30192.83 | 2012-10-01 | 2013-09-30 | 2013-07-25 | 7 | 2013-09-30 | 9
| 050.34783 | Install 3 inch Mooneys | Woodmill Regulator Station in Hopkinsville. We are replacing the (2) 3 inch 461 - 57S Roll out regulators with (2) new 3 inch Mooney regulators. | 16372.78 | 11373.94 | 4998.84 | 43.95% | 0.05493% | 16372.78 | 11373.94 | 4998.84 | 2012-10-01 | 2013-09-30 | 2013-08-12 | 8 | 2013-09-28 | 9
| 050.34793 | 050.2637.Walnut Ext | Install 100 feet of 2 inch poly for one new residential customer requesting natural gas | 4194.51 | 1593.53 | 2600.98 | 163.2% | 0.01407% | 4194.51 | 1593.53 | 2600.98 | 2012-10-01 | 2013-09-30 | 2013-08-15 | 8 | 2013-09-28 | 9
| 050.34794 | 050.2637.Hovekamp Valve | Replace broken valve | 911.04 | 5866.24 | -4955.2 | -84.47% | 0.003057% | 911.04 | 5866.24 | -4955.2 | 2012-10-01 | 2013-09-30 | 2013-07-29 | 7 | 2013-09-28 | 9
| 050.34806 | 050.2634.Dixon Purchase | Change out Dixon Purchase Station | 1682.94 | 24951.38 | -23268.44 | -93.26% | 0.005646% | 1682.94 | 24951.38 | -23268.44 | 2012-10-01 | 2013-09-30 | 2013-08-10 | 8 | 2013-09-28 | 9
| 050.34823 | PRP.2636.CLOVERDALE | Replace 3" bare steel | 2349.54 | 53836.15 | -51486.61 | -95.64% | 0.007883% | 2349.54 | 53836.15 | -51486.61 | 2012-10-01 | 2013-09-30 | 2013-07-03 | 7 | 2013-09-28 | 9
| 050.34824 | 2737.STAN.HUBBLE RD HP RELO | RELOCATE 550ft OF 4in STEEL HP LINE AT HUBBLE AND RIDGEWAY RD-THIS IS AT THE REQUEST OF TOMMY OWNES -PROPERTY OWNER | 2193.93 | 19706.05 | -17512.12 | -88.87% | 0.007361% | 2193.93 | 19706.05 | -17512.12 | 2012-10-01 | 2013-09-30 | 2013-07-29 | 7 | 2014-09-02 | 9
| 050.34836 | 050.2637.Hwy 1523 Retire | Retire 636 feet of 4 inch steel service | 599.03 | 324.26 | 274.77 | 84.74% | 0.00201% | 599.03 | 324.26 | 274.77 | 2012-10-01 | 2013-09-30 | 2013-08-12 | 8 | 2013-09-28 | 9
| 050.34838 | 2738.SPR.LINCOLN WAY 2013 | INSTALL 300ft OF 2in PE TO SERVE FOUR COMMERICAL LOTS | 3887.22 | 1519.96 | 2367.26 | 155.7% | 0.01304% | 3887.22 | 1519.96 | 2367.26 | 2012-10-01 | 2013-09-30 | 2013-06-01 | 6 | 2014-06-01 | 6
| 050.34843 | 050.2634.Midtown Commons_ | Relocate approximately 600 ft 4 Inch Stl. for new entrance into Midtown Commons Commercial developement in Madisonville Ky. | -6443.33 | 0 |  |  | -0.02162% | -6443.33 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-08-01 | 8 | 2013-09-28 | 9
| 050.34844 | PRP.Nashville Rd. Bare Replc | Replace Bare Steel on Nashville Rd - Russellville | 399.75 | 12252.7 | -11852.95 | -96.74% | 0.001341% | 399.75 | 12252.7 | -11852.95 | 2012-10-01 | 2013-09-30 | 2013-08-01 | 8 | 2013-12-31 | 12
| 050.34845 | PRP.2734.Barren River & Wdfrd | Repl 6 in stl with 6 in PE along Old Barren River Rd and Woodford Ave | 63481.76 | 123893.13 | -60411.37 | -48.76% | 0.213% | 63481.76 | 123893.13 | -60411.37 | 2012-10-01 | 2013-09-30 | 2013-08-01 | 8 | 2013-12-31 | 12
| 050.34847 | PRP.2734.MaxHamptonAlley | Replace 4 inch between 5th and 6th and College and State | 36084.02 | 98751.38 | -62667.36 | -63.46% | 0.1211% | 36084.02 | 98751.38 | -62667.36 | 2012-10-01 | 2013-09-30 | 2013-08-05 | 8 | 2013-12-31 | 12
| 050.34849 | PRP.Old Louisville Rd. I | replace 575 ft, of 4 inch Bare - Old Louisville Rd. | 26949.82 | 83228.57 | -56278.75 | -67.62% | 0.09042% | 26949.82 | 83228.57 | -56278.75 | 2012-10-01 | 2013-09-30 | 2013-08-15 | 8 | 2013-12-31 | 12
| 050.34850 | PRP.2nd at Bethel - Russ | Replace 3" Bare w 2nd at Bethel - Russellville | 552.28 | 24440.03 | -23887.75 | -97.74% | 0.001853% | 552.28 | 24440.03 | -23887.75 | 2012-10-01 | 2013-09-30 | 2013-08-05 | 8 | 2013-12-31 | 12
| 050.34874 | Portable building - Princeton | We would like to purchase a 10' X 16' portable building from Eagle Buildings in Princeton for use at the Princeton office. This will be a metal building, stone with brown trim. This is a 2013 FY budgeted item. | 2740.4 | 2981.3 | -240.9 | -8.08% | 0.009194% | 2740.4 | 2981.3 | -240.9 | 2012-10-01 | 2013-09-30 | 2013-08-06 | 8 | 2013-09-28 | 9
| 050.34881 | 2739.SIMP.TRANS RELOC 2013 | RELOCATE 3925' OF 8" STEEL TRANSMISSION LINE IN SIMPSONVILLE FOR A DEVELOPER BUILDING THE OUTLET SHOPPES SOUTH OF I-64 ON VEECHDALE-CLARK STATION ROAD | 27869.34 | 0 |  |  | 0.0935% | 27869.34 | Non Budgeted |  | 2012-10-01 | 2013-09-30 | 2013-08-14 | 8 | 2013-10-01 | 10
| 050.34965 | 050.2637.Union Sta Replace | Replace existing Union Station with a new pre-fab regulator station due to the existing by-pass valve being broken | 23591.47 | 23156.82 | 434.65 | 1.877% | 0.07915% | 23591.47 | 23156.82 | 434.65 | 2012-10-01 | 2013-09-30 | 2013-08-27 | 8 | 2013-09-28 | 9
| 050.35002 | 050.2637.13th St Replace | Abandon 318 ft of 2 inch M.W main. We currently have one grade 2 leak, gas getting near building. We have a history of leakage in this alley. we propose to retire some main in alley and install app. 100 ft on Jefferson and switch two services . | 2481.4 | 3844.33 | -1362.93 | -35.45% | 0.008325% | 2481.4 | 3844.33 | -1362.93 | 2012-10-01 | 2013-09-30 | 2013-08-28 | 8 | 2013-09-28 | 9
| 050.35012 | PRP.2609.Greenriver Steel | Replace 9010 ft Bare Stl | 289304.37 | 1230804.04 | -941499.67 | -76.49% | 0.9706% | 289304.37 | 1230804.04 | -941499.67 | 2012-10-01 | 2013-09-30 | 2013-08-25 | 8 | 2014-12-31 | 12
| 050.35013 | PRP.2609.Fruithill Hoptown 2 | Replace 26000 ft 6 Inch Bare Steel with 12 Inch Steel | 1041923.52 | 7419912.38 | -6377988.86 | -85.96% | 3.496% | 1041923.52 | 7419912.38 | -6377988.86 | 2012-10-01 | 2013-09-30 | 2013-10-01 | 10 | 2014-12-31 | 12
| 050.35018 | PRP.2736.W 1st St Replace | replace 108 ft of 2 inch bare with 2 inch poly | 4582.12 | 4141.13 | 440.99 | 10.65% | 0.01537% | 4582.12 | 4141.13 | 440.99 | 2012-10-01 | 2013-09-30 | 2013-08-29 | 8 | 2013-09-27 | 9
| 050.35025 | 050.2637.Woodcreek Dr Ext | Install 225 feet of 2 inch poly for one new residential customer requesting gas. | 3505.6 | 1642.23 | 1863.37 | 113.5% | 0.01176% | 3505.6 | 1642.23 | 1863.37 | 2012-10-01 | 2013-09-30 | 2013-09-09 | 9 | 2013-09-28 | 9
| 050.35055 | PRP.Woodburn-Franklin HPD | Replace Bare HPD from Woodburn Purchase to Akin Rd. | 721932.83 | 4133795.54 | -3411862.71 | -82.54% | 2.422% | 721932.83 | 4133795.54 | -3411862.71 | 2012-10-01 | 2013-09-30 | 2013-08-30 | 8 | 2015-09-28 | 9
| 050.35062 | 050.2638.Haven Rd Ext | Install 180 feet of 2 inch poly pipe for Mako Nesler | 758.38 | 3517.85 | -2759.47 | -78.44% | 0.002544% | 758.38 | 3517.85 | -2759.47 | 2012-10-01 | 2013-09-30 | 2013-09-10 | 9 | 2013-09-27 | 9
| 050.35066 | PRP.2738.N COLUMBIA RETIRE | RETIRE 363' OF 2" BARE STEEL PIPE ON NORTH COLUMBIA AVE BETWEEN MATTHEW AND UNIVERISTY DR | 188.94 | 1205.23 | -1016.29 | -84.32% | 0.0006339% | 188.94 | 1205.23 | -1016.29 | 2012-10-01 | 2013-09-30 | 2013-08-01 | 8 | 2013-10-01 | 10
| 050.35072 | 050.3436.OFFICE IMPROVEMENTS | PURCHASE A DEHUMIDIFICATION UNIT AND AN AIR CONDITIONER FOR THE OFFICE AT 2833 W. MARKET ST. JOHNSON CITY | 5864.46 | 25855.2 | -19990.74 | -77.32% | 0.01968% | 5864.46 | 25855.2 | -19990.74 | 2012-10-01 | 2013-09-30 | 2013-09-06 | 9 | 2013-10-30 | 10
| 050.35076 | 050.2734.Adairville Outage | Adairville Outage - 09-02-13 | 50967.12 | 63803.42 | -12836.3 | -20.12% | 0.171% | 50967.12 | 63803.42 | -12836.3 | 2012-10-01 | 2013-09-30 | 2013-09-03 | 9 | 2013-12-31 | 12
| 050.35106 | 2739.LAW.W WOODFORD 2013 | INSTALL 270' OF 2" PE OFF OF WEST WOODFORD ACROSS FROM HUMSTON DR | 1014.43 | 1644.68 | -630.25 | -38.32% | 0.003404% | 1014.43 | 1644.68 | -630.25 | 2012-10-01 | 2013-09-30 | 2013-08-25 | 8 | 2013-10-01 | 10
| 050.35145 | 050.2637.Hwy 453 Relocate | Relocate 4 inch transmission main due to proximity to new building | 18865.83 | 88441.93 | -69576.1 | -78.67% | 0.0633% | 18865.83 | 88441.93 | -69576.1 | 2012-10-01 | 2013-09-30 | 2013-09-18 | 9 | 2014-09-28 | 9
| 050.35149 | PRP.2609.Fruithill 4 InchRt. | Retire 4 Inch HPD | 7666.53 | 19273.73 | -11607.2 | -60.22% | 0.02572% | 7666.53 | 19273.73 | -11607.2 | 2012-10-01 | 2013-09-30 | 2013-08-09 | 8 | 2014-11-30 | 11

## 2012a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2012
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2012 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.19607 | Paducah 08 Non Growth | Paducah 08 Non Growth | 4760.56 | 0 |  |  | 3.036% | 948775.79 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.22147 | 050.2638.King Dr Rev Ext | Install 645' - 2" PE | 2678.51 | 2955.17 | 1867.9 | 63.21% | 0.01543% | 4823.07 | 2955.17 | 1867.9 | 2011-10-01 | 2012-09-30 | 2009-07-06 | 07 | 2012-05-23 | 05
| 050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 14744.16 | 0 |  |  | 0.1016% | 31757.35 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 28873.04 | 0 |  |  | 0.2549% | 79676.2 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 111108.79 | 0 |  |  | 1.098% | 343101.93 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 246990.35 | 0 |  |  | 1.849% | 577832.43 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 84025.21 | 0 |  |  | 0.4053% | 126689.34 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24030 | HopkinsvilleLeakRegs | Hopkinsville Leak Regs Functional | -1044.99 | 0 |  |  | 0.003612% | 1128.96 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24032 | CampbellsvilleLeakRegs | CampbellsvilleLeakRegs | 17011.55 | 0 |  |  | 0.1093% | 34147.49 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24070 | DanvilleLeakCP/LeakClamps | Danville Leak Functional - CP/Leak Clamps | 20642.69 | 0 |  |  | 0.4029% | 125931.14 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24071 | CampbellLeakCP/LeakClamps | Campbellsville KY Leak Functional - CP/Leak Clamps | 8145.65 | 0 |  |  | 0.1423% | 44489.94 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24076 | PaducahLeakCP/LeakClamps | Paducah Leak Functional - CP/Leak Clamps | 3998.69 | 0 |  |  | 0.06599% | 20624.24 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 70274.64 | 0 |  |  | 0.5126% | 160202.86 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 60519.5 | 0 |  |  | 0.4476% | 139902.21 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 328529.08 | 0 |  |  | 2.238% | 699405.24 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 271702.38 | 0 |  |  | 1.178% | 368021.77 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 267793.69 | 0 |  |  | 1.782% | 557084.76 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 56594.55 | 0 |  |  | 0.2888% | 90254.32 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 8652.98 | 0 |  |  | 0.07376% | 23051.86 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 611723.25 | 0 |  |  | 3.837% | 1199182.11 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 38574.41 | 0 |  |  | 0.2519% | 78732.82 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24773 | 2737.2011 EQUIPMENT | EQUIPMENT FOR 2011 | 216.05 | 21562.8 | 6289.91 | 29.17% | 0.08912% | 27852.71 | 21562.8 | 6289.91 | 2011-10-01 | 2012-09-30 | 2010-11-19 | 11 | 2011-10-03 | 10
| 050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 86840.32 | 0 |  |  | 0.6115% | 191115.21 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 719897 | 0 |  |  | 2.334% | 729596.68 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24109 | KY.Storage Integ RESI MEAS | KY Storage & Transmission Non Growth Functional - RESI MEAS. Meters, regulators, and meterset items typically used for residential applications. | 2054.79 | 0 |  |  | 0.01596% | 4986.8 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-20 | 09 | 2016-09-30 | 09
| 050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 227741.86 | 0 |  |  | 1.111% | 347256.96 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 282971.87 | 0 |  |  | 1.561% | 487879.98 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 112837.15 | 0 |  |  | 1.108% | 346445.9 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 153199.24 | 0 |  |  | 1.112% | 347620.82 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 6750.05 | 0 |  |  | 0.06935% | 21675.94 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 216796.34 | 0 |  |  | 1.014% | 316927.66 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26308 | CampbellsvillePRPMains | Campbellsville KY Pipe Replacement Program Functional - Mains | 116.69 | 0 |  |  | 0.0003734% | 116.69 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 124101.34 | 0 |  |  | 0.5467% | 170872.23 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.29086 | 2737.2739.NEW PHONE SYSTEM | NEW PHONE SYSTEM FOR DANVILLE AND SHELBYVILLE OFFICES 2012 | 30168.87 | 48383.98 | -18215.11 | -37.65% | 0.09653% | 30168.87 | 48383.98 | -18215.11 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.27389 | 050.2635.Welder Purchase | Purchase new Miller 302D Welder and Retire Miller Bobcat Welder that no longer works. | 14004.18 | 12498.12 | 1506.06 | 12.05% | 0.04481% | 14004.18 | 12498.12 | 1506.06 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2011-12-31 | 12
| 050.27355 | 050.2635.Chapel Hill | Install 540 Ft 2 Inch PE | 3809.75 | 6602.63 | -2792.88 | -42.3% | 0.01219% | 3809.75 | 6602.63 | -2792.88 | 2011-10-01 | 2012-09-30 | 2011-09-13 | 09 | 2011-11-20 | 11
| 050.29953 | Ky ECAT Replacement | replacing Mercury ECAT that or failing due to age. | 45760.78 | 45360.04 | 400.74 | 0.8835% | 0.1464% | 45760.78 | 45360.04 | 400.74 | 2011-10-01 | 2012-09-30 | 2012-03-21 | 03 | 2012-10-31 | 10
| 050.26897 | 055.2734.Nutwood-Neal-15th | Replace Bare Steel - Nutwood-Neal-15th - 14th - Bowling Green | 156020.56 | 205063.49 | 63284.05 | 30.86% | 0.8586% | 268347.54 | 205063.49 | 63284.05 | 2011-10-01 | 2012-09-30 | 2011-08-08 | 08 | 2011-09-28 | 09
| 050.29906 | 050.2638.Hwy 45 Four Lane | The state of Kentucky is widening U.S Hwy 45 just south of Purchase Parkway. We have app. 3,500' of 4" and 2" pipe affected as well as 20 services. 25% reimbursable | 203100.79 | 246789.35 | -43688.56 | -17.7% | 0.6498% | 203100.79 | 246789.35 | -43688.56 | 2011-10-01 | 2012-09-30 | 2012-04-01 | 04 | 2012-07-22 | 07
| 050.28119 | 050.2602.MDT's 2012 | Purchase and retire MDT's | 132207.47 | 121087.46 | 11120.01 | 9.183% | 0.423% | 132207.47 | 121087.46 | 11120.01 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-09-28 | 09
| 050.28832 | PRP.2734.Montague - Liberty | replace 3 inch bare - Montague - Franklin | 8308.56 | 6144.18 | 2164.38 | 35.23% | 0.02658% | 8308.56 | 6144.18 | 2164.38 | 2011-10-01 | 2012-09-30 | 2011-12-09 | 12 | 2012-09-28 | 09
| 050.28018 | 050.2635.Hwy 373 | Install 1000 Ft 2 Inch PE | 8137.89 | 10014.59 | -1876.7 | -18.74% | 0.02604% | 8137.89 | 10014.59 | -1876.7 | 2011-10-01 | 2012-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.27098 | Industrial Regulators | Back up Inventory | 23301.6 | 26046.3 | 1814.48 | 6.966% | 0.08914% | 27860.78 | 26046.3 | 1814.48 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27100 | Industrial Meters-2612 | Back up Meter | 1967.17 | 22325.4 | 8500.84 | 38.08% | 0.09863% | 30826.24 | 22325.4 | 8500.84 | 2011-10-01 | 2012-09-30 | 2011-08-30 | 08 | 2011-09-30 | 09
| 050.27096 | 050.PRP.2609.DanielsLn 8 Inch | Relocate approximately 518 Ft 8 Inch HPD for storm sewer and rd. widening due to the new Hospital | 112189.4 | 116214.9 | 37009.6 | 31.85% | 0.4902% | 153224.5 | 116214.9 | 37009.6 | 2011-10-01 | 2012-09-30 | 2011-09-01 | 09 | 2011-09-28 | 09
| 050.29493 | 050.2635.Hwy139 | Install 14000 Ft 4 Inch PE | 16629.87 | 33814.97 | -17185.1 | -50.82% | 0.05321% | 16629.87 | 33814.97 | -17185.1 | 2011-10-01 | 2012-09-30 | 2012-02-16 | 02 | 2012-09-28 | 09
| 050.27291 | 050.2734.Cemetery Rd. Ext. | 150 ft. of 4 inch PE - Cemetery Rd. - B.G. | 3258.78 | 3105.01 | 153.77 | 4.952% | 0.01043% | 3258.78 | 3105.01 | 153.77 | 2011-10-01 | 2012-09-30 | 2011-09-26 | 09 | 2011-10-31 | 10
| 050.28172 | Replace ground bed | The ground bed at the corner of Lakeview Drive and Tom Underwood Drive is depleted and in need of replacement. | 5893.59 | 6832.16 | -938.57 | -13.74% | 0.01886% | 5893.59 | 6832.16 | -938.57 | 2011-10-01 | 2012-09-30 | 2011-10-14 13:05 | 10 | 2012-10-31 | 10
| 050.28267 | 050.2636.Carlton Dr. | Install 1283 Ft 2 Inch PE to serve 1 commercial customer | 6765.25 | 5645.47 | 1119.78 | 19.84% | 0.02165% | 6765.25 | 5645.47 | 1119.78 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-09-28 | 09
| 050.29007 | 2738.ROLAND ST 2011 | INSTALL 250ft OF 2in PE ON ROLAND ST | -179.84 | 0.68 | -180.52 | -26547% | -0.0005754% | -179.84 | 0.68 | -180.52 | 2011-10-01 | 2012-09-30 | 2011-02-01 | 02 | 2012-02-01 | 02
| 050.29164 | 050.2609.Stanco Retirement | Retire 3868 Ft 4 Inch HPD Stl from Staco in Muhlenburg County | 13114.65 | 10944.89 | 2169.76 | 19.82% | 0.04196% | 13114.65 | 10944.89 | 2169.76 | 2011-10-01 | 2012-09-30 | 2012-01-13 | 01 | 2012-09-28 | 09
| 050.26196 | 050.2736.Canton Pike | Install 2500 ft 4 Inch PE | -1414.08 | 29240.14 | -1569.87 | -5.369% | 0.08853% | 27670.27 | 29240.14 | -1569.87 | 2011-10-01 | 2012-09-30 | 2011-05-01 | 05 | 2011-09-28 | 09
| 050.29205 | PRP.2635.WASH & ALLEY | WASH & ALLEY TO HARRISON | 55172.24 | 52710.31 | 2461.93 | 4.671% | 0.1765% | 55172.24 | 52710.31 | 2461.93 | 2011-10-01 | 2012-09-30 | 2012-03-12 | 03 | 2012-09-28 | 09
| 050.26540 | 050.2736.Electro Fuse Machine | Purchase portable electro fuse machine | 252.31 | 3905.01 | -233.6 | -5.982% | 0.01175% | 3671.41 | 3905.01 | -233.6 | 2011-10-01 | 2012-09-30 | 2011-07-15 | 07 | 2011-09-30 | 09
| 050.30440 | Fence for Clover St Reg Sta | We propose to buy and install a three foot tall fence around our regulator station at 823 N Clover Street. | 1383.17 | 1377.98 | 5.19 | 0.3766% | 0.004426% | 1383.17 | 1377.98 | 5.19 | 2011-10-01 | 2012-09-30 | 2012-04-30 | 04 | 2012-10-31 | 10
| 050.31248 | PRP.2636.BOSLEY & GRIFFITH | PRP.2636.BOSLEY & GRIFFITH | 172956.44 | 271619.4 | -98662.96 | -36.32% | 0.5534% | 172956.44 | 271619.4 | -98662.96 | 2011-10-01 | 2012-09-30 | 2012-07-10 | 07 | 2012-09-28 | 09
| 050.30290 | 2738.GRN.HP RELO SUMMERSVILL | RELOCATE 4in STEEL HP LINE IN SUMMERSVILLE | 5690.41 | 23031.8 | -17341.39 | -75.29% | 0.01821% | 5690.41 | 23031.8 | -17341.39 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2013-03-01 | 03
| 050.31833 | PRP.2738.AIPORT RD.LEB.SPR | RELOCATE BARE STEEL GAS MAIN FOR AIRPORT EXPANSION | 21233.5 | 18044.04 | 3189.46 | 17.68% | 0.06794% | 21233.5 | 18044.04 | 3189.46 | 2011-10-01 | 2012-09-30 | 2012-05-01 | 05 | 2013-05-01 | 05
| 050.31329 | 050.2636.Palomino Place 2 | Install | 2645.01 | 3429.31 | -784.3 | -22.87% | 0.008463% | 2645.01 | 3429.31 | -784.3 | 2011-10-01 | 2012-09-30 | 2012-07-01 | 07 | 2012-09-28 | 09
| 050.31061 | 050.2638.McGuire Rd Relocate | Lower 550 feet of 2 inch PE main | 6082.08 | 3531.38 | 2550.7 | 72.23% | 0.01946% | 6082.08 | 3531.38 | 2550.7 | 2011-10-01 | 2012-09-30 | 2012-07-02 | 07 | 2012-08-30 | 08
| 050.30889 | 050.2636.Deer Valley 2 | Install 1174 ft 2 Inch PE and 451 ft 4 PE to serve 30 residential customers | 15933.71 | 13136.54 | 2797.17 | 21.29% | 0.05098% | 15933.71 | 13136.54 | 2797.17 | 2011-10-01 | 2012-09-30 | 2012-06-10 | 06 | 2012-09-28 | 09
| 050.30730 | 050.2637.Lightfoot Rd Ext | Install 340 feet of 2 inch PE for one new and one existing residential customer. | 6075.42 | 3001.27 | 3074.15 | 102.4% | 0.01944% | 6075.42 | 3001.27 | 3074.15 | 2011-10-01 | 2012-09-30 | 2012-06-15 | 06 | 2012-08-30 | 08
| 050.21917 | 050.2609.Nort'ville Hwy 62 12" | 050.2609 Replace 10" 90-159-10 at Hwy 62 w/ 12" | -67746.7 | 638316.21 | -163256.72 | -25.58% | 1.52% | 475059.49 | 638316.21 | -163256.72 | 2011-10-01 | 2012-09-30 | 2009-03-09 | 03 | 2012-02-25 | 02
| 050.22437 | 050.KY.OboroLeakFunct2010 | 050.KY.OboroLeakFunct2010 | 3653.52 | 0 |  |  | 1.983% | 619803.36 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 20927.91 | 0 |  |  | 0.118% | 36874.4 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 14649.98 | 0 |  |  | 0.0682% | 21316.53 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24036 | OwensboroLeakRegs | Owensboro Leak Regs Functional | 11711.49 | 0 |  |  | 0.1128% | 35240.46 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24028 | BowlingGreenLeakRegs | Bowling Green Leak Regs Functional | 30480.48 | 0 |  |  | 0.2751% | 85975.3 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 24391.35 | 0 |  |  | 0.06817% | 21307.08 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-09-30 | 09
| 050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 26994.91 | 0 |  |  | 0.134% | 41883.89 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 127733.67 | 0 |  |  | 1.143% | 357174.37 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 320690.72 | 0 |  |  | 1.831% | 572184.01 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 510474.8 | 0 |  |  | 2.843% | 888601.8 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 66736.69 | 0 |  |  | 0.2752% | 86014.8 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23838 | MadisonvilleIntegRegs | Madisonville Non Growth Regs | 14852.82 | 0 |  |  | 0.234% | 73129.64 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 103729.26 | 0 |  |  | 0.6172% | 192899.81 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 111673.38 | 0 |  |  | 0.4166% | 130216.08 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 21054.73 | 0 |  |  | 0.1455% | 45469.7 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 64509 | 0 |  |  | 0.3243% | 101343.59 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23560 | 050.2636.Insulators & Anodes | Retire ground bed & rectifier at Legion Park. Install insulators at Legion Blvd.& Warwick Dr. with Anodes | 2582.25 | 45777.27 | -5762.74 | -12.59% | 0.128% | 40014.53 | 45777.27 | -5762.74 | 2011-10-01 | 2012-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 36953.27 | 0 |  |  | 0.239% | 74709.68 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24926 | 050.2634.Station Retirements | Retire old Station piping at Lone Star in Muhlenberg County and J L West Rd in Sacramento | -11.96 | 12144.3 | 5007.14 | 41.23% | 0.05488% | 17151.44 | 12144.3 | 5007.14 | 2011-10-01 | 2012-09-30 | 2011-02-03 | 02 | 2011-09-28 | 09
| 050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 145359.38 | 0 |  |  | 0.9478% | 296236.57 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24920 | 050.2637.Shawnee Reg Replace | Regulator at corner of Hwy 996 and Carneal ln damaged by car we plan to replace reg and relocate | 195 | 10528.68 | -3336.35 | -31.69% | 0.02301% | 7192.33 | 10528.68 | -3336.35 | 2011-10-01 | 2012-09-30 | 2011-02-01 | 02 | 2011-03-30 | 03
| 050.24082 | OwensboroPRPMains | Owensboro Sub-region KY PRP Functional - Mains | 4782.83 | 0 |  |  | 0.01874% | 5856.19 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 1859.18 | 0 |  |  | 0.01582% | 4943.99 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-20 | 09 | 2016-09-30 | 09
| 050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 53043.98 | 0 |  |  | 0.308% | 96251.93 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23535 | 050.2609.Storage Misc. | Replace Safety Shut Offs and Install Methanol Injectors | -842.94 | 113968.24 | -842.94 | -0.7396% | 0.362% | 113125.3 | 113968.24 | -842.94 | 2011-10-01 | 2012-09-30 | 2010-08-27 | 08 | 2010-09-28 | 09
| 050.24077 | MayfieldLeakCP/LeakClamps | Mayfield Leak Functional - CP/Leak Clamps | 12433.67 | 0 |  |  | 0.07991% | 24974.97 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 61652.78 | 0 |  |  | 0.1976% | 61759.63 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.25441 | 050.2637.Prestwick Place Ext | Install 1145 feet of two inch poly for 26 new residential lots adjacent to the country club of Paducah | 8334.25 | 6914.14 | 1420.11 | 20.54% | 0.02667% | 8334.25 | 6914.14 | 1420.11 | 2011-10-01 | 2012-09-30 | 2011-04-25 | 04 | 2011-09-30 | 09
| 050.29015 | 050.2636.Challenger Center 54 | Install 252 ft 2 Inch PE | 3343.58 | 2653.18 | 690.4 | 26.02% | 0.0107% | 3343.58 | 2653.18 | 690.4 | 2011-10-01 | 2012-09-30 | 2010-08-01 | 08 | 2010-09-28 | 09
| 050.26048 | 050.2609.Kirkwood Rplmt | Replace 18000 Ft 6 And 8 Inch Bare pipe | 129894.98 | 2405504.58 | -151023.3 | -6.278% | 7.213% | 2254481.28 | 2405504.58 | -151023.3 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2011-09-18 | 09
| 050.29055 | Odorizer Replacement - Joppa | The existing odorizer is a Williams model. It is old and obsolete, parts are no longer available. We plan to purchase a YZ model NJEX 7300. | 44837.04 | 49012.53 | -4175.49 | -8.519% | 0.1435% | 44837.04 | 49012.53 | -4175.49 | 2011-10-01 | 2012-09-30 | 2011-10-17 09:47 | 10 | 2012-10-31 | 10
| 050.26251 | 050.2637.Friendship Relocate | Our existing 2 inch poly gas main is in the way of construction. | -56.99 | 2030.92 | -209.4 | -10.31% | 0.005828% | 1821.52 | 2030.92 | -209.4 | 2011-10-01 | 2012-09-30 | 2011-06-15 | 06 | 2011-06-30 | 06
| 050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 136893.45 | 0 |  |  | 0.438% | 136893.45 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26305 | HopkinsvillePRPMains | Hopkinsville KY Pipe Replacement Program Functional - Mains | 448.28 | 0 |  |  | 0.001434% | 448.28 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.26311 | ShelbyvillePRPMains | Shelbyville KY Pipe Replacement Program Functional - Mains | 1708.49 | 0 |  |  | 0.005466% | 1708.49 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.29876 | 2737.BEATTY-ROY ARNOLD 2011 | INSTALL 4in PE TO RETIRE 4in STEEL ON CENTRE COLLEGE PROPERTY | 8226.72 | 819.74 | 7406.98 | 903.6% | 0.02632% | 8226.72 | 819.74 | 7406.98 | 2011-10-01 | 2012-09-30 | 2011-12-01 | 12 | 2012-12-01 | 12
| 050.29708 | 050.2609.Gator Trailer | Purchase Trailer for John Deere gator | 3125.69 | 3078.83 | 46.86 | 1.522% | 0.01% | 3125.69 | 3078.83 | 46.86 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2012-09-28 | 09
| 050.30199 | 2738.WOODHILL RD 2011 | INSTALL 2100ft 2in PE PIPE FOR CUSTOMER | 9216.99 | 8582.91 | 634.08 | 7.388% | 0.02949% | 9216.99 | 8582.91 | 634.08 | 2011-10-01 | 2012-09-30 | 2011-05-01 | 05 | 2012-05-01 | 05
| 050.31726 | PRP.2636.FORD & GRIFFITH PL W | PRP.2636.FORD & GRIFFITH PL W | 100415.15 | 161001.17 | -60586.02 | -37.63% | 0.3213% | 100415.15 | 161001.17 | -60586.02 | 2011-10-01 | 2012-09-30 | 2012-08-21 | 08 | 2012-09-28 | 09
| 050.30061 | 2738.WOODHILL RD 2012 | INSTALL 600ft OF 2in PE FROM THE END OF PROJECT 2738.WOODHILL RD 2011 | 3196.04 | 0.26 | 3195.78 | 1229146% | 0.01023% | 3196.04 | 0.26 | 3195.78 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2013-03-01 | 03
| 050.30163 | 050.2734.Penn Dr. II | 243 ft. of 2 inch PE - Penn Dr. II - B.G. | 1122.81 | 2230.59 | -1107.78 | -49.66% | 0.003592% | 1122.81 | 2230.59 | -1107.78 | 2011-10-01 | 2012-09-30 | 2012-02-20 | 02 | 2012-09-28 | 09
| 050.26270 | PRP.2638.Broadway Street | Abandon 7,525' of bare pipe. Install 6,625' of PE pipe. | 7959.15 | 212483.24 | -50935.51 | -23.97% | 0.5169% | 161547.73 | 212483.24 | -50935.51 | 2011-10-01 | 2012-09-30 | 2011-07-05 | 07 | 2011-09-16 | 09
| 050.28465 | 050.2736.Hwy 41 Nortonville | Install 300 Ft 2 Inch PE to serve 1 residential customers | 4247.89 | 2881.48 | 1366.41 | 47.42% | 0.01359% | 4247.89 | 2881.48 | 1366.41 | 2011-10-01 | 2012-09-30 | 2011-11-14 | 11 | 2012-09-28 | 09
| 050.25665 | 050.2636.Deer Valley 1 | Run gas for 78 residential lots | -399.21 | 73139.28 | -399.21 | -0.5458% | 0.2327% | 72740.07 | 73139.28 | -399.21 | 2011-10-01 | 2012-09-30 | 2010-12-01 | 12 | 2011-09-28 | 09
| 050.28143 | 050.2734.Misc.Equipment | 1 - Trailer for Mule - used for survey 1 - DP-IR 1 - RMLD 1 - 1" - 4" Squeeze off Tool - Russellville 1 - Trac-It II - C&M 2 - Sensit Golds - Russellville 1 - 3D ( 0-100 ) and 1- 3D ( 0-1000) - Franklin 1 - 12 volt Sub Pump - Russellville | 38086.84 | 62867.79 | -24780.95 | -39.42% | 0.1219% | 38086.84 | 62867.79 | -24780.95 | 2011-10-01 | 2012-09-30 | 2011-11-26 | 11 | 2012-09-28 | 09
| 050.28782 | PRP.2609.Empire Fruithill | Replacement of 10 Inch Bare Steel pipe between Possum Pocket Rd. and Crofton and with 12 Inch | 8598613.77 | 8967835.86 | -369222.09 | -4.117% | 27.51% | 8598613.77 | 8967835.86 | -369222.09 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2012-09-28 | 09
| 050.27061 | 050.2634.Oakwood Dr. | Install 2023 ft 2 Inch PE | 9285.79 | 9698.35 | -1508.46 | -15.55% | 0.0262% | 8189.89 | 9698.35 | -1508.46 | 2011-10-01 | 2012-09-30 | 2011-04-21 | 04 | 2011-09-28 | 09
| 050.27159 | Sensit Golds (2) | We are requesting to purchase (2) new Sensit gold C.G.I's for use in the Mayfield area. We are "trading in" two older units for $300 each. These should be the new highly anticipated G-2 models. | 216.05 | 3215.32 | -71.59 | -2.227% | 0.01006% | 3143.73 | 3215.32 | -71.59 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.28025 | 050.2634.Hwy 260 | Install 420 Ft 4 Inch PE to serve new addition at the Veterans center in Hanson Ky. | 3965.8 | 4047.41 | -81.61 | -2.016% | 0.01269% | 3965.8 | 4047.41 | -81.61 | 2011-10-01 | 2012-09-30 | 2010-12-15 | 12 | 2011-09-28 | 09
| 050.25289 | Pipe splitting tool for Shelbyville | Approval is needed to purchase a pipe splitting tool for the Shelbyville office | -2963.7 | 2406.65 | -2443.79 | -101.5% | -0.0001188% | -37.14 | 2406.65 | -2443.79 | 2011-10-01 | 2012-09-30 | 2011-03-14 | 03 | 2011-09-30 | 09
| 050.25675 | 050..2734.Cave.Mill.Sta.Ext. | 4 inch PE Ext. Cave Mill Sta. | 3576.68 | 9045.07 | -2691.4 | -29.76% | 0.02033% | 6353.67 | 9045.07 | -2691.4 | 2011-10-01 | 2012-09-30 | 2011-04-15 | 04 | 2011-09-28 | 09
| 050.26406 | 050.2636.Cross Creek Phase 5 | Install 545 Ft 2 Inch PE | -18.42 | 4034.51 | -2483.37 | -61.55% | 0.004963% | 1551.14 | 4034.51 | -2483.37 | 2011-10-01 | 2012-09-30 | 2011-06-25 | 06 | 2011-09-28 | 09
| 050.26716 | PRP.2737.STAN.MILL ST | INSTALL 400ft OF 2in PE TO REPLACE BARE STEEL SECTION - CITY REWORKING STREET - CONTRACTOR WITH AIC | -13089.33 | 8096.35 | -9930.56 | -122.7% | -0.005869% | -1834.21 | 8096.35 | -9930.56 | 2011-10-01 | 2012-09-30 | 2011-07-18 | 07 | 2012-07-18 | 07
| 050.29039 | 050.2636.Springhurst Ln. | Install | 10461.54 | 12900.28 | -2438.74 | -18.9% | 0.03347% | 10461.54 | 12900.28 | -2438.74 | 2011-10-01 | 2012-09-30 | 2011-12-01 | 12 | 2012-09-28 | 09
| 050.29109 | PRP.2737.HAR.E OFFICE.GREENVI | PRP.2737.HAR.E OFFICE.GREENVI | 373032.79 | 218722.95 | 154309.84 | 70.55% | 1.194% | 373032.79 | 218722.95 | 154309.84 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-11-01 | 11
| 050.25359 | 050.2636.Reg. & Relief upgrades | Make Relief and reg upgrades at Old State Rd, Calhoun purchase, Hartford and Town Border # 4. Also upgrade 4 charts with ERX recorders | 12375.52 | 51375.09 | -534.14 | -1.04% | 0.1627% | 50840.95 | 51375.09 | -534.14 | 2011-10-01 | 2012-09-30 | 2011-03-22 | 03 | 2011-09-30 | 09
| 050.26141 | 2738.SALOMA PURCH REBUILD | REPLACE PURCHASE STATION REGULATORS AT SALOMA FOR CAMPBELLSVILLE | 1344.53 | 20435.52 | -8157.97 | -39.92% | 0.03928% | 12277.55 | 20435.52 | -8157.97 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.31389 | 050.2734.Warehouse-Lot-Russ. | Purchase lot and building for New Atmos Warehouse in Russellville KY. Lot is located in the Thurston Commercial Development on the corner of Thurston and Fisher in Russellville | 132466.43 | 181315.2 | -48848.77 | -26.94% | 0.4238% | 132466.43 | 181315.2 | -48848.77 | 2011-10-01 | 2012-09-30 | 2012-05-24 08:33 | 05 | 2012-09-28 | 09
| 050.30630 | 2739.CLOVERBROOK SEC 3b | INSTALL 2in PE FOR 25 LOTS | 2029.35 | 9267 | -7237.65 | -78.1% | 0.006493% | 2029.35 | 9267 | -7237.65 | 2011-10-01 | 2012-09-30 | 2012-05-01 | 05 | 2013-05-01 | 05
| 050.31623 | 050.2734.OakRidge Tie-In | 100 ft of 2 inch tie-in - Oak Ridge - Franklin | 499.49 | 5351.06 | -4851.57 | -90.67% | 0.001598% | 499.49 | 5351.06 | -4851.57 | 2011-10-01 | 2012-09-30 | 2012-08-06 | 08 | 2012-12-31 | 12
| 050.31261 | 050.2635.Industrial Dr. | Install 700 ft 2 Inch Pe to serve 1 commercial Customer. | -1480.45 | 623.14 | -2103.59 | -337.6% | -0.004737% | -1480.45 | 623.14 | -2103.59 | 2011-10-01 | 2012-09-30 | 2011-11-30 | 11 | 2012-09-28 | 09
| 050.31914 | 050.2734.WestStBare Replc. | 3 inch Bare Steel Replc. - Franklin | 2957.19 | 12579.19 | -9622 | -76.49% | 0.009462% | 2957.19 | 12579.19 | -9622 | 2011-10-01 | 2012-09-30 | 2012-08-06 | 08 | 2012-12-31 | 12
| 050.31466 | 050.2636.Industial Dr. | Relocate Reg station that is falling into ditch City of Owensboro is reworking the ditch also install new reg station and make tie back into HPD in front of Swedish Match installing approximately 1700 ft 4 Inch Stl and 200 ft 4 Inch PE | 116503.51 | 132596.74 | -16093.23 | -12.14% | 0.3728% | 116503.51 | 132596.74 | -16093.23 | 2011-10-01 | 2012-09-30 | 2012-08-01 | 08 | 2012-09-28 | 09
| 050.30260 | 2738.RETIRE DITCH WITCH EQUIP | RETIRE DITCH WITCH EQUIPMENT, 3610 TRENCHER { UNIT # 7067}, 5110 TRENCHER { UNIT # 10582} AND DITCH WITCH TRAILER { UNIT # 10583} | -19373.91 | 137.89 | -19511.8 | -14150% | -0.06199% | -19373.91 | 137.89 | -19511.8 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.30481 | 2738.GRN.HP REINFORCEMENT | EXPOSED PIPE NEEDS TO BE COVERED AND REPAIRED | 4047.12 | 5559.51 | -1512.39 | -27.2% | 0.01295% | 4047.12 | 5559.51 | -1512.39 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.30345 | PRP.2735 PARK CITY | PRP.2735 PARK CITY | 449663.52 | 0 |  |  | 1.439% | 449663.52 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2012-04-23 | 04 | 2013-02-28 | 02
| 050.30402 | PRP.2735.Green St. - Horse CV | 5 ft. Bare Steel Replacement - Green St. Horse Cave | 569.34 | 1699.97 | -1130.63 | -66.51% | 0.001822% | 569.34 | 1699.97 | -1130.63 | 2011-10-01 | 2012-09-30 | 2012-04-18 | 04 | 2012-09-28 | 09
| 050.31446 | 2736.Fence @ 19th&Woodmill | Replace security fence around regulator station at 19th & Woodmill in Hopkinsville, KY | 8323.52 | 8760.89 | -437.37 | -4.992% | 0.02663% | 8323.52 | 8760.89 | -437.37 | 2011-10-01 | 2012-09-30 | 2012-08-01 | 08 | 2012-08-31 | 08
| 050.22436 | 050.KY.PrincetonLeakFunct2010 | 050.KY.PrincetonLeakFunct2010 | 551.98 | 0 |  |  | 0.4318% | 134969.16 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 38580.67 | 0 |  |  | 0.2961% | 92537.05 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 18031.81 | 0 |  |  | 0.1787% | 55860.62 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 92183.48 | 0 |  |  | 0.5903% | 184480.21 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 30419.97 | 0 |  |  | 0.148% | 46269.71 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 11450.01 | 0 |  |  | 0.06225% | 19454.86 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24069 | HopkinsLeakCP/LeakClamps | Hopkinsville KY Leak Functional - CP/Leak Clamps | 10831.09 | 0 |  |  | 0.08622% | 26947.16 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 37763.64 | 0 |  |  | 0.1988% | 62134.48 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 29340.9 | 0 |  |  | 0.2748% | 85874.09 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 127419.62 | 0 |  |  | 0.7574% | 236725.32 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 65143.25 | 0 |  |  | 0.3484% | 108904.57 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.19601 | Madisonville 08 Non Growth | Madisonville 08 Non Growth | 143.35 | 0 |  |  | 1.564% | 488759.99 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 112634.42 | 0 |  |  | 0.6248% | 195268.07 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 94987.81 | 0 |  |  | 0.551% | 172213.63 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24729 | 050.2636.New Hospital | Install 100 feet 2 Inch Steel &2077 feet 6 Inch PE | -8303.94 | 45581.69 | -264.42 | -0.5801% | 0.145% | 45317.27 | 45581.69 | -264.42 | 2011-10-01 | 2012-09-30 | 2010-11-01 | 11 | 2010-12-31 | 12
| 050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 29976.48 | 0 |  |  | 0.3357% | 104922.65 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.24808 | 050.2734.14th Replc. | Relocated 450 ft.of 4" PE | 719.21 | 4.66 | 1549.85 | 33259% | 0.004974% | 1554.51 | 4.66 | 1549.85 | 2011-10-01 | 2012-09-30 | 2010-12-06 | 12 | 2011-09-28 | 09
| 050.23842 | MayfieldIntegRegs | Mayfield Non Growth Regs Functional | 4529.82 | 0 |  |  | 0.05609% | 17529.15 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 117972.02 | 0 |  |  | 0.8617% | 269304.43 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.22429 | 050.KY.BowlGrnLeakFunct2010 | 050.KY.BowlGrnLeakFunct2010 | 2769.9 | 0 |  |  | 3.373% | 1054241.95 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 168305.61 | 0 |  |  | 0.8705% | 272074.85 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23836 | KY.ShelbyvilleIntegRegs | Shelbyville KY Non Growth Regs Functional | 35314.32 | 0 |  |  | 0.3098% | 96831.11 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.28972 | KY Refub Meters | KY Refub Meters and WMR | 38640.02 | 90720.12 | -52080.1 | -57.41% | 0.1236% | 38640.02 | 90720.12 | -52080.1 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.29009 | 2739.WAREHOUSE-NEW OFFICE | PURCHASE OF SHELVING, WASHER, DRYER AND ICE MACHINE FOR THE NEW SHELBYVILLE OFFICE | 35384.93 | 21704.3 | 13680.63 | 63.03% | 0.1132% | 35384.93 | 21704.3 | 13680.63 | 2011-10-01 | 2012-09-30 | 2011-08-15 11:05 | 08 | 2012-02-15 | 02
| 050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 32229.98 | 0 |  |  | 0.4907% | 153375.44 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.29163 | PRP.050.Bellville Relocate | Install 320' - 4" PE. Retire 220' - 4" PE. | 40576.31 | 19465.54 | 21110.77 | 108.5% | 0.1298% | 40576.31 | 19465.54 | 21110.77 | 2011-10-01 | 2012-09-30 | 2012-02-01 | 02 | 2012-04-30 | 04
| 050.25108 | 050.2609.Hickory Wells | Rework 5 wells at Hickory Storage. | 3636.53 | 884840.28 | 11186.7 | 1.264% | 2.867% | 896026.98 | 884840.28 | 11186.7 | 2011-10-01 | 2012-09-30 | 2011-03-01 | 03 | 2011-09-28 | 09
| 050.29954 | YZ Covers | Covers for YZ odorizors to stabilize temperature | 10772.33 | 9676.8 | 1095.53 | 11.32% | 0.03447% | 10772.33 | 9676.8 | 1095.53 | 2011-10-01 | 2012-09-30 | 2012-03-21 | 03 | 2012-10-31 | 10
| 050.30005 | 050.2636.Daniels Ln. Relo 2 | Relocate 2 Inch Stl. for road. widening and to get 2 Inch Stll airplaning creek removed pipe will be replaced with 3145 ft 4 Inch PE and 94 ft 2 Inch PE to help support future growth in the area near the new hospital | 74895.34 | 69198.61 | 5696.73 | 8.232% | 0.2396% | 74895.34 | 69198.61 | 5696.73 | 2011-10-01 | 2012-09-30 | 2012-03-15 | 03 | 2012-09-28 | 09
| 050.30252 | PRP.2736.4TH ST REPL | PRP.2736.4TH 2ND & MAIN ST REPL | 518463.57 | 546533.86 | -28070.29 | -5.136% | 1.659% | 518463.57 | 546533.86 | -28070.29 | 2011-10-01 | 2012-09-30 | 2012-04-25 | 04 | 2012-09-28 | 09
| 050.28778 | PRP.2734.6th and Breathitt | 100 ft. of 4 inch and 40 ft. of 2 inch relocation - 6th and Breathitt - Russellville | 15451.83 | 12682.15 | 2769.68 | 21.84% | 0.04944% | 15451.83 | 12682.15 | 2769.68 | 2011-10-01 | 2012-09-30 | 2011-12-05 | 12 | 2012-09-28 | 09
| 050.27050 | 050.2637.Mallard Cr Ext | Install 240 feet of 2 inch PE for 9 new residential customers. | 5337.83 | 2042.8 | 3295.03 | 161.3% | 0.01708% | 5337.83 | 2042.8 | 3295.03 | 2011-10-01 | 2012-09-30 | 2011-08-29 | 08 | 2011-09-28 | 09
| 050.26922 | 050.2636.River Front Crossing | Relocated 1 Inch and 2 Inch Stl. main replaced with 301 ft 2 Inch PE | -85.1 | 5059.17 | -2370.32 | -46.85% | 0.008603% | 2688.85 | 5059.17 | -2370.32 | 2011-10-01 | 2012-09-30 | 2011-04-01 | 04 | 2011-09-28 | 09
| 050.27233 | 050.2637.S Friendship Ext | Install 100 feet of two inch pe pipe for one new residential customer. | 1727.74 | 1491.21 | 236.53 | 15.86% | 0.005528% | 1727.74 | 1491.21 | 236.53 | 2011-10-01 | 2012-09-30 | 2011-09-19 | 09 | 2011-09-28 | 09
| 050.26717 | 2737.HAR.KINGS WAY RELOCATE | RELOCATE 1-1/4in PE AND REPLACE WITH 2in PE | 5810.64 | 1043.15 | 5636.98 | 540.4% | 0.02137% | 6680.13 | 1043.15 | 5636.98 | 2011-10-01 | 2012-09-30 | 2011-07-21 | 07 | 2012-07-21 | 07
| 050.28593 | PRP.2737.HAR.MAGNOLIA-OFFICE | PRP.2737.HAR.MAGNOLIA-OFFICE | 659055.61 | 407840.5 | 251215.11 | 61.6% | 2.109% | 659055.61 | 407840.5 | 251215.11 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-11-01 | 11
| 050.28510 | 050.2636.Diane Ave. | Install 100 Ft. 2 Inch PE to serve 1 residential customer | 3549.71 | 1604.02 | 1945.69 | 121.3% | 0.01136% | 3549.71 | 1604.02 | 1945.69 | 2011-10-01 | 2012-09-30 | 2011-11-27 | 11 | 2012-09-28 | 09
| 050.29208 | PRP.2738.BELL AVE.2012 | PRP.2738.BELL AVE 2012 | 213906.21 | 220194.34 | -6288.13 | -2.856% | 0.6844% | 213906.21 | 220194.34 | -6288.13 | 2011-10-01 | 2012-09-30 | 2012-01-01 | 01 | 2013-01-01 | 01
| 050.26158 | 050.2636.Allen St. Rplmnt. | Replace 3120 Ft Bare 4 Inch Main with 4 Inch PE. | 751.93 | 133927.1 | -7199.93 | -5.376% | 0.4055% | 126727.17 | 133927.1 | -7199.93 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.30318 | 050.2636.Poly Tapping Machine | Purchase Poly tapping machine enabling us to side tap Poly pipe without by -passing and squeezing off main. | 20286.58 | 20747.94 | -461.36 | -2.224% | 0.06491% | 20286.58 | 20747.94 | -461.36 | 2011-10-01 | 2012-09-30 | 2012-04-25 | 04 | 2012-09-28 | 09
| 050.31251 | 050.2638.Paris Rd Relocate | Install 160 feet of 2 inch PE, Retire 155 feet of 2 inch steel. | 1136.54 | 2771.47 | -1634.93 | -58.99% | 0.003636% | 1136.54 | 2771.47 | -1634.93 | 2011-10-01 | 2012-09-30 | 2012-07-16 | 07 | 2012-09-26 | 09
| 050.31419 | 050.2638.Casablanca Ext | Install 115 feet of 2 inch PE for two new residenetial lots | 953.26 | 1476.59 | -523.33 | -35.44% | 0.00305% | 953.26 | 1476.59 | -523.33 | 2011-10-01 | 2012-09-30 | 2012-08-28 | 08 | 2012-09-28 | 09
| 050.30958 | 050.2735SecuritySystemGlasgow | Sercurity system For Glasgow Area | 7729.15 | 8102.87 | -373.72 | -4.612% | 0.02473% | 7729.15 | 8102.87 | -373.72 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.31509 | 2739.LOCUST CRK 9a 2012 | INSTALL 2in PE IN LOCUST CREEK SECTION 9a | 156.98 | 6610.36 | -6453.38 | -97.63% | 0.0005023% | 156.98 | 6610.36 | -6453.38 | 2011-10-01 | 2012-09-30 | 2012-08-01 | 08 | 2013-08-01 | 08
| 050.31561 | 2738.CAM.WOODLAND HEIGHT 2012 | INSTALL 3400ft OF 2in PE FOR SUBDIVISION | 6708.47 | 8794.12 | -2085.65 | -23.72% | 0.02146% | 6708.47 | 8794.12 | -2085.65 | 2011-10-01 | 2012-09-30 | 2011-12-01 | 12 | 2012-12-01 | 12
| 050.30650 | 2737.ULTRA SHORE SHORING BOX | PURCHASE ULTRA SHORE SHORING BOX AND ASSOICATED EQUIPMENT | 8853.11 | 7830.4 | 1022.71 | 13.06% | 0.02833% | 8853.11 | 7830.4 | 1022.71 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.30962 | 050.2734.NSunrise 2 inch repl | Replace 2" Epoxy Main in conjunction with City storm drain install | 10258.25 | 19139.11 | -8880.86 | -46.4% | 0.03282% | 10258.25 | 19139.11 | -8880.86 | 2011-10-01 | 2012-09-30 | 2012-07-02 | 07 | 2012-09-28 | 09
| 050.31037 | 050.2638.Dana Lane Ext | Install 100 feet of 2 inch PE for one new residential customer | 978.19 | 1213.75 | -235.56 | -19.41% | 0.00313% | 978.19 | 1213.75 | -235.56 | 2011-10-01 | 2012-09-30 | 2012-06-25 | 06 | 2012-07-29 | 07
| 050.30956 | PRP.2734.CREASON-MARYLAN | PRP.2734.CREASON-MARYLAN | 143774.73 | 0 |  |  | 0.46% | 143774.73 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2012-09-28 | 09 | 2012-09-28 | 09
| 050.31053 | 050.2734.Security System B.G. | Seciurity system for the Bowling Green Office | 11800.73 | 9135.07 | 2665.66 | 29.18% | 0.03776% | 11800.73 | 9135.07 | 2665.66 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.21065 | Bowling Green 09 Non Growth | Bowling Green 09 Non Growth | 533.96 | 0 |  |  | 5.226% | 1633470.32 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.19596 | Campbellsville 08 Growth | Campbellsville 08 Growth | 55.87 | 0 |  |  | 0.2565% | 80170.67 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 16457.31 | 0 |  |  | 0.2248% | 70274.31 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 22652.62 | 0 |  |  | 0.1168% | 36505.54 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 104014.99 | 0 |  |  | 0.6733% | 210449.95 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 8176.52 | 0 |  |  | 0.05422% | 16946.1 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 157746.95 | 0 |  |  | 0.7356% | 229901.45 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24034 | MadisonvilleLeakRegs | Madisonville Leak Regs Functional | 2069.64 | 0 |  |  | 0.03039% | 9496.7 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 45698.85 | 0 |  |  | 0.497% | 155344.49 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 199250.37 | 0 |  |  | 1.453% | 453971.07 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 14556.81 | 0 |  |  | 0.1328% | 41512.89 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23833 | HopkinsvilleIntegRegs | Hopkinsville Non Growth Regs Functional | 10098.4 | 0 |  |  | 0.1704% | 53255.27 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 8487.67 | 0 |  |  | 0.07349% | 22968.21 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23045 | 050.2734.Beltline 8 | Bowling Green 8 inch System Improvement | -97682.12 | 5596208.03 | -3020499.16 | -53.97% | 8.241% | 2575708.87 | 5596208.03 | -3020499.16 | 2011-10-01 | 2012-09-30 | 2009-11-30 | 11 | 2010-09-28 | 09
| 050.22434 | 050.KY.ShelbyvLeakFunct2010 | 050.KY.ShelbyvLeakFunct2010 | 1628.25 | 0 |  |  | 0.2946% | 92079.33 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 17157.46 | 0 |  |  | 0.08359% | 26124.63 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 71785.77 | 0 |  |  | 0.4726% | 147694.48 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 51368.21 | 0 |  |  | 0.263% | 82204.91 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 87229.59 | 0 |  |  | 0.4394% | 137323.34 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24724 | 050.2734.CumberlandTrc.Relo | Cumberland Trace - State Hwy. Relocation | 719.12 | 250091.43 | -39907.03 | -15.96% | 0.6725% | 210184.4 | 250091.43 | -39907.03 | 2011-10-01 | 2012-09-30 | 2010-10-29 | 10 | 2011-09-28 | 09
| 050.24081 | DanvillePRPMains | Danville Sub-Region KY Pipe Replacement Program Functional - Mains | 1353.53 | 0 |  |  | 0.02771% | 8661.25 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.24029 | GlasgowLeakRegs | Glasgow Leak Regs Functional | 13724.13 | 0 |  |  | 0.09577% | 29930.91 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.19593 | Hopkinsville 08 Non Growth | Hopkinsville 08 Non Growth | 594.82 | 0 |  |  | 1.225% | 382898.5 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.25171 | 050.2734.BarberWay Replc. | Replace 950 ft. of 2 inch bare with 2 inch PE - Barber Way | 719.21 | 49025.88 | 17859.7 | 36.43% | 0.214% | 66885.58 | 49025.88 | 17859.7 | 2011-10-01 | 2012-09-30 | 2011-03-01 | 03 | 2011-09-28 | 09
| 050.26049 | 050.2634.Hwy 62 Relo. | Relocate 4 Inch Stl for Road Widening | -2704.44 | 18325.17 | 160039.74 | 873.3% | 0.5707% | 178364.91 | 18325.17 | 160039.74 | 2011-10-01 | 2012-09-30 | 2011-05-20 | 05 | 2011-09-28 | 09
| 050.29199 | 2737.HARRODSBURG INDUST LINE | INSTALL 21,550ft OF 6in STEEL TO SERVE THE INDUSTRIAL PARK NORTH OF TOWN | 2095867.49 | 1555933.37 | 539934.12 | 34.7% | 6.706% | 2095867.49 | 1555933.37 | 539934.12 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2013-10-01 | 10
| 050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 275175.93 | 0 |  |  | 0.8804% | 275175.93 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.29730 | PRP.2638.S 14th Retire | We have a grade II leak that is soon to be 15 months old. We propose to abandon a 290' section of 2" bare. We have one service on this main, we will switch this service to main across street. | 1492.07 | 100.47 | 1391.6 | 1385% | 0.004774% | 1492.07 | 100.47 | 1391.6 | 2011-10-01 | 2012-09-30 | 2012-02-29 | 02 | 2012-03-28 | 03
| 050.26490 | 050.2636.Veterans Relo 2 | Relocate 6 Inch Stl. and 6 Inch PE for Riverfront Developement | 15712.9 | 31569.56 | -7476.64 | -23.68% | 0.07709% | 24092.92 | 31569.56 | -7476.64 | 2011-10-01 | 2012-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
| 050.30177 | 050.2638.W Vaughn Rd Ext | Install 100 ft for one customer converting furnace from propane | 1224.52 | 1297.11 | -72.59 | -5.596% | 0.003918% | 1224.52 | 1297.11 | -72.59 | 2011-10-01 | 2012-09-30 | 2012-05-14 | 05 | 2012-05-30 | 05
| 050.27267 | 050.2634.Beulah Sta. replace | Replace Beulah Town Border | 9372.76 | 14350.08 | -3903.93 | -27.2% | 0.03342% | 10446.15 | 14350.08 | -3903.93 | 2011-10-01 | 2012-09-30 | 2011-09-07 | 09 | 2011-11-01 | 11
| 050.29564 | 2737.DANVILLE BASEMENT METERS | INSTALL IP AND REMOVE LP AND BASEMENT METERS DOWNTOWN | 232467.86 | 221461.47 | 11006.39 | 4.97% | 0.7438% | 232467.86 | 221461.47 | 11006.39 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.28148 | 0500.2735.Misc. Equipment | 1 - DPIR Mobile Kit 4 Cone 3 - Mueller No Blo Changer 1 inch 3 - Mueller No Blo Changer 3/4 inch 3 - Digital Pressure Gauges | 40304.41 | 24882.03 | 15422.38 | 61.98% | 0.129% | 40304.41 | 24882.03 | 15422.38 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-09-28 | 09
| 050.29804 | 050.2636.Old Brownie Rd. Relo | Relocate 426 ft 1 Inch Stl. with | 6302.56 | 4576.64 | 1725.92 | 37.71% | 0.02017% | 6302.56 | 4576.64 | 1725.92 | 2011-10-01 | 2012-09-30 | 2012-03-20 | 03 | 2012-09-28 | 09
| 050.28150 | 2737.DAN.EQUIPMENT 2012 | 2-DITCH WITCH LOCATORS, GENERATOR, SOUTHERN CROSS FLAME PAK, BOSS III ELCTROFUSION PROCESSOR, TRAILER FOR TD WILLIAMSON TOOLS | 31969.45 | 33133.89 | -1164.44 | -3.514% | 0.1023% | 31969.45 | 33133.89 | -1164.44 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.29043 | 050.2734.Forklift | Bowling Green Forklift. Lease ended on forklift - Bowling Green. Will purchase Invoice: Garrison Service Company. 5000 lb. Pnuematic Forklift, Model 7FGU25. $5883.00 | 8153.8 | 8145.52 | 8.28 | 0.1017% | 0.02609% | 8153.8 | 8145.52 | 8.28 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.27983 | 050.2636.Menards | Install 1741 ft 2 Inch Pe and 750 ft 4 Inch PE to serve new commercial Developement | 9312.99 | 11988.09 | -2675.1 | -22.31% | 0.0298% | 9312.99 | 11988.09 | -2675.1 | 2011-10-01 | 2012-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
| 050.26465 | 050.2734.Park St. Bare Replc. | 4 inch Bare Replc. Parks St. | -19.58 | 48992.29 | -4751.1 | -9.698% | 0.1416% | 44241.19 | 48992.29 | -4751.1 | 2011-10-01 | 2012-09-30 | 2011-06-27 | 06 | 2011-09-28 | 09
| 050.26766 | 050.2734.Magnolia Alley Replc | 4 inch Bare Steel Replc. - Install l 2 inch PE convert from LP to IP; | 45735.94 | 151333.57 | -21344.22 | -14.1% | 0.4159% | 129989.35 | 151333.57 | -21344.22 | 2011-10-01 | 2012-09-30 | 2011-07-21 | 07 | 2011-09-28 | 09
| 050.28445 | PRP.2734.MAIN Replc | PRP.2734.MAIN CENTER & FAIR | 790899.89 | 680006.21 | 110893.68 | 16.31% | 2.531% | 790899.89 | 680006.21 | 110893.68 | 2011-10-01 | 2012-09-30 | 2011-11-11 | 11 | 2012-09-28 | 09
| 050.25627 | 050.2636.Daniels Ln. Reloc. | Reloc. main due to road widening | -417.38 | 12784.99 | -5421.14 | -42.4% | 0.02356% | 7363.85 | 12784.99 | -5421.14 | 2011-10-01 | 2012-09-30 | 2010-09-01 | 09 | 2010-09-28 | 09
| 050.29559 | KY Correctors | Mercury Corrector for New Transportation | 43053.01 | 49593.56 | -6540.55 | -13.19% | 0.1378% | 43053.01 | 49593.56 | -6540.55 | 2011-10-01 | 2012-09-30 | 2012-02-16 | 02 | 2012-10-31 | 10
| 050.25119 | 050.2634.Grapevine | Install 2,000 Ft 2" PE | -156.5 | 25880.83 | 2105.81 | 8.137% | 0.08954% | 27986.64 | 25880.83 | 2105.81 | 2011-10-01 | 2012-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
| 050.28682 | 050.2634.Bruest Heaters | Purchase and retire 3 Bruest Heaters | 8038.1 | 11641.5 | -3603.4 | -30.95% | 0.02572% | 8038.1 | 11641.5 | -3603.4 | 2011-10-01 | 2012-09-30 | 2011-12-05 | 12 | 2012-09-30 | 09
| 050.23434 | Hopkinsville 10-inch Replacem | Replace 4 Mi of 10 L-90-159 w/ 12" from MP 1.25 to MP 5 | 1881.49 | 3009467.72 | 809610.42 | 26.9% | 12.22% | 3819078.14 | 3009467.72 | 809610.42 | 2011-10-01 | 2012-09-30 | 2010-07-01 | 07 | 2010-12-31 | 12
| 050.29196 | PRP.2738.SPR.W HIGH ST | INSTALL 500ft OF 2in PE TO REPLACE BARE STEEL WITH MANY LEAKS AND CLAMPS | 16056.81 | 6673.87 | 9382.94 | 140.6% | 0.05137% | 16056.81 | 6673.87 | 9382.94 | 2011-10-01 | 2012-09-30 | 2012-01-01 | 01 | 2013-01-01 | 01
| 050.28326 | 050.2634.Sensit G2 | Purchase 1- Sensit G2 and retire 1-Sensit Gold | 1709.34 | 2169.46 | -460.12 | -21.21% | 0.005469% | 1709.34 | 2169.46 | -460.12 | 2011-10-01 | 2012-09-30 | 2011-11-04 14:41 | 11 | 2012-09-30 | 09
| 050.25322 | 050.2602.Laptops_&_Desktops | Purchase new laptop & Desktop computers. | 17281.15 | 62145.63 | -12785.78 | -20.57% | 0.1579% | 49359.85 | 62145.63 | -12785.78 | 2011-10-01 | 2012-09-30 | 2011-03-18 | 03 | 2011-09-30 | 09
| 050.31259 | 050.2638.Charles Dr Ext | Install 400 feet of 2 inch PE for one new commercial customer. | 2678.92 | 1956.34 | 722.58 | 36.94% | 0.008571% | 2678.92 | 1956.34 | 722.58 | 2011-10-01 | 2012-09-30 | 2012-07-30 | 07 | 2012-09-28 | 09
| 050.31830 | PRP.2735 WEST HORSE CAVE | PRP.2735 WEST HORSE CAVE | 22384.9 | 538008.43 | -515623.53 | -95.84% | 0.07162% | 22384.9 | 538008.43 | -515623.53 | 2011-10-01 | 2012-09-30 | 2012-08-27 | 08 | 2012-12-31 | 12
| 050.30960 | 050.2734.Scottsville Rd.Reloc | 325 ft. of 6inch PE - 40 ft. of 4 inch steel reloc - Scootsville rRd. Interchange | 30239.24 | 37103.04 | -6863.8 | -18.5% | 0.09675% | 30239.24 | 37103.04 | -6863.8 | 2011-10-01 | 2012-09-30 | 2012-06-25 | 06 | 2012-09-28 | 09
| 050.31529 | PRP.2636.Allen St. Alley | Replace 51 ft Bare 2 Inch Stl due to River Front Renovation | 386.39 | 4582.81 | -4196.42 | -91.57% | 0.001236% | 386.39 | 4582.81 | -4196.42 | 2011-10-01 | 2012-09-30 | 2012-08-10 | 08 | 2012-09-28 | 09
| 050.31339 | 050.2734.Oak Hills Dr. Ext | 200 ft. of 2 ich PE - Oak Hills Dr. - Franklin | 6987.48 | 17955.7 | -10968.22 | -61.08% | 0.02236% | 6987.48 | 17955.7 | -10968.22 | 2011-10-01 | 2012-09-30 | 2012-03-19 | 03 | 2012-09-28 | 09
| 050.31691 | 050.2734.Springfield VII-A | 2 inch PE Extension - Springfield VII-A - B.G. | 4873.78 | 6360.17 | -1486.39 | -23.37% | 0.01559% | 4873.78 | 6360.17 | -1486.39 | 2011-10-01 | 2012-09-30 | 2012-08-10 | 08 | 2012-12-31 | 12
| 050.31693 | PRP.2734.FAIR ST | FAIR ST FROM GLEN LILY TO 10TH | 51562.54 | 0 |  |  | 0.165% | 51562.54 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2012-12-31 | 12 | 2012-12-31 | 12
| 050.31653 | 050.2734.Three Springs Reloc. | 1575 ft of 4 inch PE - 430 ft. 0f 2 inch PE - Three Springs Rd. | 23542.55 | 245143.23 | -221600.68 | -90.4% | 0.07533% | 23542.55 | 245143.23 | -221600.68 | 2011-10-01 | 2012-09-30 | 2012-07-09 | 07 | 2012-12-31 | 12
| 050.30578 | 2739.MT EDEN REG REPLACEMENT | INSTALL 4in PE AND REGULATOR STATION TO REPLACE 4 OTHER STATIONS FEEDING EAST OF MT EDEN ROAD NORTH OF I-64 | 123413.67 | 110498.88 | 12914.79 | 11.69% | 0.3949% | 123413.67 | 110498.88 | 12914.79 | 2011-10-01 | 2012-09-30 | 2012-05-01 | 05 | 2013-05-01 | 05
| 050.23420 | 050.2734.North South Retire | 050.2734.North South Retire | 1438.42 | 406.06 | 1032.36 | 254.2% | 0.004602% | 1438.42 | 406.06 | 1032.36 | 2011-10-01 | 2012-09-30 | 2010-06-24 | 06 | 2010-09-28 | 09
| 050.23235 | 050.2637.Calvert T.B 2 | Introduce a second feed into Calvert city distribution system from the south, exising feed is from north side of city. | 9783.96 | 18727.55 | 16420.24 | 87.68% | 0.1125% | 35147.79 | 18727.55 | 16420.24 | 2011-10-01 | 2012-09-30 | 2010-03-12 | 03 | 2010-07-16 | 07
| 040.12346 | 040.BGR.HOP.18TH & CAMPBELL | 18TH & CAMPBELL BRIDGE REPLC. - ST. HWY - HOPK. | -17392 | 22303 | -39198.61 | -175.8% | -0.05406% | -16895.61 | 22303 | -39198.61 | 2011-10-01 | 2012-09-30 | 2004-09-09 | 09 | 2005-05-04 | 05
| 050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 89007.41 | 0 |  |  | 0.5932% | 185385.34 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24073 | MadisonLeakCP/LeakClamps | Madisonville Leak Functional - CP/Leak Clamps | 32191.61 | 0 |  |  | 0.2607% | 81480.14 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24074 | PrincetonLeakCP/LeakClamps | Princeton Leak Functional - CP/Leak Clamps | 20699.68 | 0 |  |  | 0.1281% | 40048.14 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24075 | OboroLeakCP/LeakClamps | Owensboro Leak Functional - CP/Leak Clamps | 47369 | 0 |  |  | 0.4158% | 129947.76 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 7963.25 | 0 |  |  | 0.08088% | 25278.58 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 205565.67 | 0 |  |  | 1.246% | 389496.5 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 951658.06 | 0 |  |  | 5.075% | 1586209.19 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 220880.91 | 0 |  |  | 1.201% | 375399.45 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 39056.61 | 0 |  |  | 0.2932% | 91625.81 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23832 | GlasgowIntegRegs | Glasgow Non Growth Regs Functional | 29528.45 | 0 |  |  | 0.1448% | 45269.3 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23839 | PrincetonIntegRegs | Princeton Non Growth Regs Functional | 12692.14 | 0 |  |  | 0.1746% | 54572.6 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22274 | 050.2338.May Reinforcement | Install 12,000 feet 4" HD PE pipe from KT Clay (190 maop) to Dairyman Inc (36 maop) | 31624.78 | 67799.57 | 120568.59 | 177.8% | 0.6027% | 188368.16 | 67799.57 | 120568.59 | 2011-10-01 | 2012-09-30 | 2009-08-24 | 08 | 2009-09-28 | 09
| 050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 39535.85 | 0 |  |  | 0.3628% | 113389.82 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 648634.58 | 0 |  |  | 2.358% | 736918.05 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 461574.75 | 0 |  |  | 2.107% | 658562.28 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 89043.18 | 0 |  |  | 0.5812% | 181648.61 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24947 | 050.2636.Hwy 54 Whitesville | Install 1000 feet 2 Inch PE | -213.45 | 2127.02 | 1560.4 | 73.36% | 0.0118% | 3687.42 | 2127.02 | 1560.4 | 2011-10-01 | 2012-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
| 050.22433 | 050.KY.CampbellLeakFunct2010 | 050.KY.CampbellLeakFunct2010 | 1176.47 | 0 |  |  | 0.8288% | 259048.85 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 24976.64 | 0 |  |  | 0.1257% | 39293.35 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 91193.66 | 0 |  |  | 0.5239% | 163747.76 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.29150 | 050.2637.Windmere Cv Ext | Install 400 feet of 2 inch PE along Windmere Drive and Windmere Cove. | 453.55 | 4997.76 | -4544.21 | -90.92% | 0.001451% | 453.55 | 4997.76 | -4544.21 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2012-05-28 | 05
| 050.26301 | MayfieldPRPMeters | Mayfield KY PRP Functional - Meters | 5715.37 | 0 |  |  | 0.01829% | 5715.37 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26302 | GlasgowPRPMains | Glasgow KY Pipe Replacement Program Functional - Mains | 1983.21 | 0 |  |  | 0.01361% | 4254.39 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.25518 | 050.2734.S.MainBareReplc.FRK | South Main Bare TSeel Replacement - Franklin | -810.3 | 138643.36 | -19661.04 | -14.18% | 0.3807% | 118982.32 | 138643.36 | -19661.04 | 2011-10-01 | 2012-09-30 | 2011-04-01 | 04 | 2011-09-28 | 09
| 050.26050 | 050.2636.Frederica St. Rplmnt | Replace 1750 Ft. Bare Stl. Pipe | -81.56 | 164009.73 | -10966.93 | -6.687% | 0.4897% | 153042.8 | 164009.73 | -10966.93 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.29941 | 050.2636.Fiddlesticks Phase 2 | Install approximately 620 ft.2 Inch Pe to serve 12 residential customers | 4355.67 | 5852.24 | -1496.57 | -25.57% | 0.01394% | 4355.67 | 5852.24 | -1496.57 | 2011-10-01 | 2012-09-30 | 2012-03-15 | 03 | 2012-09-28 | 09
| 050.29845 | 050.2736.Rogers Group | Install 1800 ft 6 Inch PE to serve the Rogers Group Asphalt Plant | 18994.74 | 31169.63 | -12174.89 | -39.06% | 0.06077% | 18994.74 | 31169.63 | -12174.89 | 2011-10-01 | 2012-09-30 | 2012-03-15 | 03 | 2012-09-28 | 09
| 050.29948 | KY RTU Upgrades | Upgradeing Fisher RTU's | 22613.55 | 26611.1 | -3997.55 | -15.02% | 0.07235% | 22613.55 | 26611.1 | -3997.55 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.29950 | KY Monitor Stations | Installing Mercury ERX's to replace Fisher ROC at monitor Stations | 42260.03 | 42335.9 | -75.87 | -0.1792% | 0.1352% | 42260.03 | 42335.9 | -75.87 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.30045 | PRP.2735 ROCKY HILL | PRP.2735 ROCKY HILL | 214988.5 | 219865.36 | -4876.86 | -2.218% | 0.6879% | 214988.5 | 219865.36 | -4876.86 | 2011-10-01 | 2012-09-30 | 2012-02-13 | 02 | 2012-09-28 | 09
| 050.28259 | 050.2636.Highland Pointe Dr. | Install 100 Ft. 2 Inch PE to server 1 Commercial Customer | 1606.77 | 1534.04 | 72.73 | 4.741% | 0.005141% | 1606.77 | 1534.04 | 72.73 | 2011-10-01 | 2012-09-30 | 2011-11-15 | 11 | 2012-09-28 | 09
| 050.28329 | PRP.2734.OrangeLemonReplc. | Replace Bare 333ft.4 inch 75 ft. 2 inch OrangeLemon Franklin | 32070.24 | 31318.34 | 751.9 | 2.401% | 0.1026% | 32070.24 | 31318.34 | 751.9 | 2011-10-01 | 2012-09-30 | 2011-11-27 | 11 | 2012-09-28 | 09
| 050.29835 | 2739.BREIGHTON BUS LOT 17 | INSTALL 240ft OF 4in PE TO CROSS LOT 17 THAT IS BEING DEVELOPED - CUSTOMER IS INSTALLING GAS | 2056.3 | 3178.17 | -1121.87 | -35.3% | 0.006579% | 2056.3 | 3178.17 | -1121.87 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2013-03-12 | 03
| 050.30242 | 050.2637.Ladera Ln Ext | Install 1,960' of 4" PE and 1,130' of 2" PE | 19103.56 | 24537.23 | -5433.67 | -22.14% | 0.06112% | 19103.56 | 24537.23 | -5433.67 | 2011-10-01 | 2012-09-30 | 2012-05-07 | 05 | 2012-05-31 | 05
| 050.26053 | 2737.LAN.TBS REG REPLACE | REPLACE REGULATORS AT THE TOWN BORDER STATION IN LANCASTER | -696.93 | 2.6 | 5750.78 | 221184% | 0.01841% | 5753.38 | 2.6 | 5750.78 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.27218 | Easements | Phase 2 of I-69 was originally scheduled for FY 2011, it has been moved to FY 2012, however, we would like to proceed with securing easements for the project. We anticipate easements to cost Atmos $49,630. This is using $7 per ft. In 2010 we paid $85,000 | 42653.18 | 49974.88 | -7101.5 | -14.21% | 0.1372% | 42873.38 | 49974.88 | -7101.5 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.26139 | 2737.WAREHOUSE PARKING IMPROVEMENTS | IMPROVEMENTS FOR PARKING AT THE MAIN OFFICE | -346.29 | 5149.55 | -521.39 | -10.12% | 0.01481% | 4628.16 | 5149.55 | -521.39 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27157 | Aldyl A Repair Kit | We would like to purchase a model GFCP #10007584 Aldyl A refurbish tool. this allows us to repair leaking aldyl a service tees. | 50.99 | 819.3 | -84.16 | -10.27% | 0.002352% | 735.14 | 819.3 | -84.16 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.26044 | 050.2638 W Slaughter Rd Ext | Install 700 feet of 2 inch poly for one new residential customer and one customer converting from propane. | 6672.38 | 3333.56 | 3338.82 | 100.2% | 0.02135% | 6672.38 | 3333.56 | 3338.82 | 2011-10-01 | 2012-09-30 | 2011-06-13 | 06 | 2011-07-13 | 07
| 050.27003 | 050.2636.Southtown Relo. | Relocate 2 Inch PE for Southtown Widening | 52511.7 | 94530.6 | -35758.87 | -37.83% | 0.188% | 58771.73 | 94530.6 | -35758.87 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.26046 | 050.2637.Hwy 996 Rev Ext | Install 635 feet of 2 inch poly for one new residential customer plus two vacant lots that will build in the near future. | 1744.59 | 2783.6 | -3015.1 | -108.3% | -0.0007407% | -231.5 | 2783.6 | -3015.1 | 2011-10-01 | 2012-09-30 | 2011-06-06 | 06 | 2011-07-06 | 07
| 050.25348 | 050.2638.Water Valley Replace | Replace 2" steel pipe that is exposed in creek. Will move chart box to puchase station. will retire above ground valve, not critical | 13675.54 | 9505.9 | 5466.75 | 57.51% | 0.04791% | 14972.65 | 9505.9 | 5466.75 | 2011-10-01 | 2012-09-30 | 2011-04-01 | 04 | 2011-08-30 | 08
| 050.28383 | 050.2636.Breck Co. Airport | Relocate 3550 Ft 2 Inch HPD for Airport Construction | 10346.95 | 10410.21 | -63.26 | -0.6077% | 0.03311% | 10346.95 | 10410.21 | -63.26 | 2011-10-01 | 2012-09-30 | 2011-10-25 | 10 | 2012-09-28 | 09
| 050.26599 | 050.2637.Valerie Ln Ext | Install 435 feet of 2 inch PE | -669.28 | 2052.5 | 146.21 | 7.124% | 0.007035% | 2198.71 | 2052.5 | 146.21 | 2011-10-01 | 2012-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.29557 | Commercial Industrial Meter | Metering equipment for Emergency Stock | 27078.14 | 30240.05 | -3161.91 | -10.46% | 0.08664% | 27078.14 | 30240.05 | -3161.91 | 2011-10-01 | 2012-09-30 | 2012-02-16 | 02 | 2012-10-31 | 10
| 050.26477 | 050.2637.Tina Dr Main Ext | Install 75 feet of 2 inch poly for one conversion customer | -295.3 | 855.39 | 104.96 | 12.27% | 0.003073% | 960.35 | 855.39 | 104.96 | 2011-10-01 | 2012-09-30 | 2011-07-05 | 07 | 2011-09-28 | 09
| 050.26495 | 050.2609.Heartland xing Relo. | Relocate 2100 ft 8 Inch HPD for new shopping center | -422.44 | -25037.17 | 13422.1 | -53.61% | -0.03716% | -11615.07 | -25037.17 | 13422.1 | 2011-10-01 | 2012-09-30 | 2011-06-10 | 06 | 2011-09-28 | 09
| 050.26711 | RETIREMENT OF TRAILER 11121 | RETIREMENT OF TRAILER 11121 | -2084 | -3678.18 | 1594.18 | -43.34% | -0.006668% | -2084 | -3678.18 | 1594.18 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.26442 | PRP.2738.LEB.PROCTOR KNOTT | REPLACE 4in STEEL ON S PROCTOR KNOTT AVE WITH 4in PE | 32382.37 | 248257.09 | -86086.52 | -34.68% | 0.5189% | 162170.57 | 248257.09 | -86086.52 | 2011-10-01 | 2012-09-30 | 2010-05-01 | 05 | 2012-05-01 | 05
| 050.28131 | 050.2735.Old Munfrdville Ext | 100 ft of 2 inch PE - Old Munfordville Rd and Rose | 5098.43 | 2838.52 | 2259.91 | 79.62% | 0.01631% | 5098.43 | 2838.52 | 2259.91 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-09-28 | 09
| 050.29385 | 2737.OFFICE HVAC | REPLACE THE OFFICE HVAC THAT IS 20 YEARS OLD | 15055.07 | 15230.6 | -175.53 | -1.152% | 0.04817% | 15055.07 | 15230.6 | -175.53 | 2011-10-01 | 2012-09-30 | 2012-01-01 | 01 | 2012-03-31 | 03
| 050.28279 | PRP.2636 HILL AVE & FAIRWAY | PRP.2636.HILL AVE & FAIRWAY DR | 114650.54 | 114994.59 | -344.05 | -0.2992% | 0.3668% | 114650.54 | 114994.59 | -344.05 | 2011-10-01 | 2012-09-30 | 2011-10-04 | 10 | 2012-09-28 | 09
| 050.29568 | 050.2636.Hot Cat Boiler | Install Hot Cat Boiler to eliminate line freezing at Calhoun purchase station | 71071.73 | 59985.63 | 11086.1 | 18.48% | 0.2274% | 71071.73 | 59985.63 | 11086.1 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2012-09-28 | 09
| 050.28707 | PRP.2636.WINDSOR AVE | PRP.2636.WINDSOR AVE | 56771.32 | 46623.91 | 10147.41 | 21.76% | 0.1816% | 56771.32 | 46623.91 | 10147.41 | 2011-10-01 | 2012-09-30 | 2011-12-01 | 12 | 2012-09-28 | 09
| 050.26121 | PRP.050.2734.Pritchardsville | 2210 ft. of 2 inch PE - Bare Replc. - Protchardsville Rd | 674.77 | 140915.71 | 16046.6 | 11.39% | 0.5022% | 156962.31 | 140915.71 | 16046.6 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.29157 | Husband Rd Reg Sta Upgrade | Replace Mooney pilots, restrictors, & Mooney filters at our Husband Road regulator station, just south of Estes Lane in Paducah. | 2191.67 | 3655.27 | -1463.6 | -40.04% | 0.007012% | 2191.67 | 3655.27 | -1463.6 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.31956 | 050.2637.Clinton Rd Relocate | 4 inch PE gas main exposed in large creek. Not only exposed, app. 30 feet simply hanging in the air. | 22834.17 | 23200.52 | -366.35 | -1.579% | 0.07306% | 22834.17 | 23200.52 | -366.35 | 2011-10-01 | 2012-09-30 | 2012-09-13 | 09 | 2012-09-28 | 09
| 050.30786 | PRP.2609.Empire Fruithill Rt. | Retire approximately 26,000 ft of 10" Bare Transmission Main | 40154.49 | 96323.13 | -56168.64 | -58.31% | 0.1285% | 40154.49 | 96323.13 | -56168.64 | 2011-10-01 | 2012-09-30 | 2012-01-16 15:48 | 01 | 2012-09-30 | 09
| 050.30792 | 050.2635.Butt Fuse Machine | Purchase Butt Fuse Machine for Princeton | 4920.14 | 4702 | 218.14 | 4.639% | 0.01574% | 4920.14 | 4702 | 218.14 | 2011-10-01 | 2012-09-30 | 2012-05-24 | 05 | 2012-09-24 | 09
| 050.31323 | 050.2634.Hwy 262 | Install 900 Ft. 2 Inch PE. to serve new County Garage | 4323.42 | 6289.19 | -1965.77 | -31.26% | 0.01383% | 4323.42 | 6289.19 | -1965.77 | 2011-10-01 | 2012-09-30 | 2012-05-01 | 05 | 2012-09-28 | 09
| 050.31601 | 050.2636.Winning Colors Way | Install 270 Ft 2 Inch PE to serve 11 residential lots | 2043.59 | 3357.72 | -1314.13 | -39.14% | 0.006539% | 2043.59 | 3357.72 | -1314.13 | 2011-10-01 | 2012-09-30 | 2012-07-25 | 07 | 2012-09-28 | 09
| 050.31855 | PRP.2736.E 4th. and Brown St. | Replace 377 ft 4 Inch LP Stl. Bare main with 2 Inch PE IP. approximately 5 residerntial customers involved | 1692.69 | 17286.31 | -15593.62 | -90.21% | 0.005416% | 1692.69 | 17286.31 | -15593.62 | 2011-10-01 | 2012-09-30 | 2012-09-01 | 09 | 2012-09-28 | 09
| 050.31254 | 050.2635.Seven Springs | Install | 93336.6 | 99437.89 | -6101.29 | -6.136% | 0.2986% | 93336.6 | 99437.89 | -6101.29 | 2011-10-01 | 2012-09-30 | 2012-06-20 | 06 | 2012-09-28 | 09
| 050.31669 | 050.2734.Oak Ridge Replc. | 680 ft. of 2 inch PE on Broadway to replace existimg 2 inchac 3aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa | 6864 | 10841.62 | -3977.62 | -36.69% | 0.02196% | 6864 | 10841.62 | -3977.62 | 2011-10-01 | 2012-09-30 | 2012-08-06 | 08 | 2012-12-31 | 12
| 050.30401 | PRP.2734.MillSt.atLincoln-AUB | Replace 35 ft. of 2 inch bare - Mill St. at Lincoln - Auburn | 387.59 | 2809.37 | -2421.78 | -86.2% | 0.00124% | 387.59 | 2809.37 | -2421.78 | 2011-10-01 | 2012-09-30 | 2012-04-19 | 04 | 2012-09-28 | 09
| 050.21077 | Madisonville 09 Non Growth | Madisonville 09 Non Growth | 3497.19 | 0 |  |  | 2.04% | 637657.64 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.19599 | Shelbyville 08 Non Growth | Shelbyville 08 Non Growth | 361 | 0 |  |  | 0.6728% | 210292.67 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.22438 | 050.KY.PaducahLeakFunct2010 | 050.KY.PaducahLeakFunct2010 | 19744.49 | 0 |  |  | 1.525% | 476690.22 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22439 | 050.KY.MayfieldLeakFunct2010 | 050.KY.MayfieldLeakFunct2010 | 458.8 | 0 |  |  | 0.278% | 86878.66 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 28881.87 | 0 |  |  | 0.1423% | 44459.56 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24745 | 050.2635.Lafayette St. | Install 525 Ft 2 Inch PE | -1255.44 | 5045.01 | -5045.01 | -100% | 0% | 0 | 5045.01 | -5045.01 | 2011-10-01 | 2012-09-30 | 2010-11-07 | 11 | 2011-09-28 | 09
| 050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 90176.73 | 0 |  |  | 0.4689% | 146540.81 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 8270.3 | 0 |  |  | 0.1105% | 34532.98 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 31021.83 | 0 |  |  | 0.2953% | 92307.36 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 30049.71 | 0 |  |  | 0.1888% | 59015.27 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 21430.53 | 0 |  |  | 0.1177% | 36770.99 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24035 | PrincetonLeakRegs | Princeton Leak Regs Functional | -579.06 | 0 |  |  | 0.01788% | 5588.43 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24038 | MayfieldLeakRegs | Mayfield Leak Regs Functional | 2845.73 | 0 |  |  | 0.02748% | 8587.21 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24031 | DanvilleLeakRegs | Danville Leak Regs Functional | 17847.62 | 0 |  |  | 0.1916% | 59871.56 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24033 | KY.ShelbyvilleLeakRegs | Shelbyville KY Leak Regs Functional | 11683.53 | 0 |  |  | 0.04491% | 14035.93 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 27213.61 | 0 |  |  | 0.2068% | 64620.46 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 349776.04 | 0 |  |  | 2.216% | 692744.88 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 306562.71 | 0 |  |  | 1.522% | 475750 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 15062.64 | 0 |  |  | 0.1281% | 40046.56 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23835 | CampbellsvilleIntegRegs | Campbellsville Non Growth Regs Functional | 24466.03 | 0 |  |  | 0.1606% | 50197.55 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23840 | OboroIntegRegs | Owensboro Non Growth Regs Functional | 66252.06 | 0 |  |  | 0.6261% | 195673.25 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23841 | PaducahIntegRegs | Paducah Non Growth Regs Functional | 27262.78 | 0 |  |  | 0.2306% | 72061.12 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22394 | 050.KY.DanvilleIntegFunct2010 | 050.KY.DanvilleIntegFunct2010 | 503.33 | 0 |  |  | 1.582% | 494408.46 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 261532.61 | 0 |  |  | 1.671% | 522254.75 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 63528.13 | 0 |  |  | 0.325% | 101582.37 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24758 | 050.2734.Robbins Ext - Russ | 400 ft. of 2 inch PE - Robbins Way - Russellville | 3154.69 | 2236.25 | -147.6 | -6.6% | 0.006683% | 2088.65 | 2236.25 | -147.6 | 2011-10-01 | 2012-09-30 | 2010-11-12 | 11 | 2011-09-28 | 09
| 050.22397 | 050.KY.MadisonIntegFunct2010 | 050.KY.MadisonIntegFunct2010 | 2234.89 | 0 |  |  | 2.373% | 741763.07 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2011-01-12 | 01
| 050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 61958.56 | 0 |  |  | 0.5011% | 156625.67 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 80427.59 | 0 |  |  | 0.7232% | 226027.61 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 37383.84 | 0 |  |  | 0.1958% | 61187.18 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 20031.34 | 0 |  |  | 0.1405% | 43899.42 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23339 | 050.2635.Macedonia Sta. Rt. | Retire Macedonia East Station | 465.38 | 3928.89 | -3268.5 | -83.19% | 0.002113% | 660.39 | 3928.89 | -3268.5 | 2011-10-01 | 2012-09-30 | 2010-05-18 | 05 | 2010-09-28 | 09
| 050.21778 | 2737.BURGIN RECTIFIER REPLACE | REPLACE BURGIN RECTIFIER DAMAGED IN CAR ACCIDENT | 7876 | 7877 | -2475.54 | -31.43% | 0.01728% | 5401.46 | 7877 | -2475.54 | 2011-10-01 | 2012-09-30 | 2008-12-15 | 12 | 2009-12-15 | 12
| 050.29091 | 050.2609.Well Workovers | Rework 5 Wells and retire 1 at Hickory Storage, Rework 1 well at St. Charles. | 931017.57 | 941994.33 | -10976.76 | -1.165% | 2.979% | 931017.57 | 941994.33 | -10976.76 | 2011-10-01 | 2012-09-30 | 2012-01-20 | 01 | 2012-09-28 | 09
| 050.26304 | GlasgowPRPMeters | Glasgow KY PRP Functional - Meters | 1064.93 | 0 |  |  | 0.02668% | 8339.28 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26312 | ShelbyvillePRPServices | Shelbyville KY PRP Functional - Services | 8713.55 | 0 |  |  | 0.02788% | 8713.55 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.29764 | 2739.LAW.BLUEBIRD CT 2012 | INSTALL 300ft OF 2in PE FOR RESTURANT AND FUTURE EXPANSION | 1674.14 | 1193.5 | 480.64 | 40.27% | 0.005356% | 1674.14 | 1193.5 | 480.64 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2013-03-01 | 03
| 050.29959 | 050.2734.Elrod Rd. Reloc | Relocate 625 ft. of 4 inch PE - Elrod Rd. | 35142.11 | 37027.57 | -1885.46 | -5.092% | 0.1124% | 35142.11 | 37027.57 | -1885.46 | 2011-10-01 | 2012-09-30 | 2012-03-12 | 03 | 2012-09-28 | 09
| 050.30201 | 2739.LAW.E WOODFORD RETIRE | RETIRE 187ft OF 2in STEEL MAIN ON EAST WOODFORD ST | 353.04 | 1416.8 | -1063.76 | -75.08% | 0.00113% | 353.04 | 1416.8 | -1063.76 | 2011-10-01 | 2012-09-30 | 2012-04-01 | 04 | 2012-04-01 | 04
| 050.28247 | PRP.2734.Boatlanding Replc | 150 ft. Bare Steel Replc. - Boatlanding at Beech St. - B.G. | 3695.01 | 7222.21 | -3527.2 | -48.84% | 0.01182% | 3695.01 | 7222.21 | -3527.2 | 2011-10-01 | 2012-09-30 | 2011-10-27 | 10 | 2012-09-28 | 09
| 050.26286 | PRP.2737.HAR.PEARSON ST | INSTALL 300ft OF 2in PE TO REPLACE BARE STEEL | -152.2 | 8894.53 | -6864.49 | -77.18% | 0.006495% | 2030.04 | 8894.53 | -6864.49 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.28626 | 050.2634.Kitchen Equipment | Purchase and retire stove for Break room in the Madisonville Ky office. Purchase Microwave | 1381.64 | 1134.82 | 246.82 | 21.75% | 0.004421% | 1381.64 | 1134.82 | 246.82 | 2011-10-01 | 2012-09-30 | 2011-11-04 14:41 | 11 | 2012-09-30 | 09
| 050.28160 | 050.2734.Hwy31W Reloc. B.G. | Hwy 31W HPD & IP Relocation | 809016.25 | 221016.86 | 587999.39 | 266% | 2.588% | 809016.25 | 221016.86 | 587999.39 | 2011-10-01 | 2012-09-30 | 2011-09-15 | 09 | 2011-12-31 | 12
| 050.28152 | 2739.SHV.EQUIPMENT 2012 | BORING MOLES 2in AND 4in, GAUGES, CHAIN SAW, STAR DRILL-AIR OPERATED | 13103.39 | 14766.08 | -1662.69 | -11.26% | 0.04192% | 13103.39 | 14766.08 | -1662.69 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.25659 | Bon Harbor Storage YZ | Bon Harbor Storage YZ for no flow conditions | 2348.96 | 37209 | -210.22 | -0.565% | 0.1184% | 36998.78 | 37209 | -210.22 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.28052 | 050.2636.Tamarack Rd. | Install 1250 feet of 2 Inch Stl. to serve the new National Guard Armory | -6932.89 | 39272.22 | -46205.11 | -117.7% | -0.02218% | -6932.89 | 39272.22 | -46205.11 | 2011-10-01 | 2012-09-30 | 1899-12-31 | 01 | 2009-09-28 | 09
| 050.27103 | I/P EFM's | I/P EFM for new customers | -10.63 | 31007.5 | 285.02 | 0.9192% | 0.1001% | 31292.52 | 31007.5 | 285.02 | 2011-10-01 | 2012-09-30 | 2011-08-30 | 08 | 2011-09-30 | 09
| 050.25695 | 050.2734.Penn Station Ext. | 230 ft. of 2 inch PE Extension - Penn Station Bowling Green | 1905.74 | 2553.89 | -86.38 | -3.382% | 0.007895% | 2467.51 | 2553.89 | -86.38 | 2011-10-01 | 2012-09-30 | 2011-04-21 | 04 | 2011-09-28 | 09
| 050.26383 | 050.2734.Suwannee Trl. Ext. | 550 ft. of 2 inch PE - Suwannee Trail | -430.15 | 2092.82 | 626.42 | 29.93% | 0.0087% | 2719.24 | 2092.82 | 626.42 | 2011-10-01 | 2012-09-30 | 2011-06-21 | 06 | 2011-09-28 | 09
| 050.25128 | 050.2609.Hwy 60 bypass Relo. | Relocate 1100 ft 8 Inch Stl. and 1200 ft 4 Inch Stl. HPD | -328433.69 | 7754.15 | -3256.68 | -42% | 0.01439% | 4497.47 | 7754.15 | -3256.68 | 2011-10-01 | 2012-09-30 | 2011-02-01 | 02 | 2011-09-28 | 09
| 050.26602 | 050.2637.Hilldale Road Ext | Install 100 feet of 2 inch PE | 578.8 | 1310.24 | -731.44 | -55.82% | 0.001852% | 578.8 | 1310.24 | -731.44 | 2011-10-01 | 2012-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.29603 | 050.2637.NFriendship Project | Install 375' - 2" PE. Retire 365' - 2" PE for KYDOT project | 4199.44 | 3401.94 | 797.5 | 23.44% | 0.01344% | 4199.44 | 3401.94 | 797.5 | 2011-10-01 | 2012-09-30 | 2012-03-01 | 03 | 2012-05-28 | 05
| 050.28560 | PRP.2735 MORRIS LINE | PRP.2735.MORRIS LINE | 273726.41 | 0 |  |  | 0.8758% | 273726.41 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2012-05-01 | 05 | 2012-05-01 | 05
| 050.28095 | 050.2734. Hwy 100 Pub. Impv. | 6 inch HPD Reloc. - Hwy. 100 Franklin | 184910.33 | 5962.11 | 178948.22 | 3001% | 0.5916% | 184910.33 | 5962.11 | 178948.22 | 2011-10-01 | 2012-09-30 | 2011-11-15 | 11 | 2012-09-28 | 09
| 050.28198 | 050.2609.Misc Equipment | Purchase 2 bush hogs and 1-Sensit Gold G2 | 22520.17 | 18607.51 | 3912.66 | 21.03% | 0.07205% | 22520.17 | 18607.51 | 3912.66 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-09-28 | 09
| 050.28262 | 050.2636.King Rd. | Install 600 Ft. 2 Inch PE to serve 1 residential customer | 3974.22 | 2879.25 | 1094.97 | 38.03% | 0.01272% | 3974.22 | 2879.25 | 1094.97 | 2011-10-01 | 2012-09-30 | 2011-10-30 | 10 | 2012-09-28 | 09
| 050.28799 | 2738.MONTGOMERY MILL RD 2011 | INSTALL 5800ft OF 2in PE FOR 4 POULTRY HOUSES | -164.86 | -1274.24 | 1109.38 | -87.06% | -0.0005275% | -164.86 | -1274.24 | 1109.38 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-01 | 10
| 050.28066 | 050.2636.Sensit G2, 2 | Purchase 3 new Sensit G2's | 6087.08 | 4970.85 | 1116.23 | 22.46% | 0.01948% | 6087.08 | 4970.85 | 1116.23 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.29108 | PRP.2737.HAR.PARKVIEW.CANE | PRP.2737.HAR.PARKVIEW CANE | 357110.97 | 128607.66 | 228503.31 | 177.7% | 1.143% | 357110.97 | 128607.66 | 228503.31 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-11-01 | 11
| 050.30442 | SCBA for Union city | SCBA for Union City. I am setting up this project per Steve Bittel request. | 6568.46 | 6861.62 | -293.16 | -4.272% | 0.02102% | 6568.46 | 6861.62 | -293.16 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.31922 | 055.2734.Main - Wrenwood 2 in | 1200 ft. of 2 inch PE - Main to Wrenwood - Auburn | 1931.38 | 1947.87 | -16.49 | -0.8466% | 0.00618% | 1931.38 | 1947.87 | -16.49 | 2011-10-01 | 2012-09-30 | 2012-04-30 | 04 | 2012-09-28 | 09
| 050.30328 | 050.2636.Payton Place | Install approximately 2417 ft 2 Inch PE to serve 28 residential lots | 14807.36 | 11859.42 | 2947.94 | 24.86% | 0.04738% | 14807.36 | 11859.42 | 2947.94 | 2011-10-01 | 2012-09-30 | 2012-05-01 | 05 | 2012-09-28 | 09
| 050.30356 | 050.2734.WalnutExt Adairville | 100 ft. of 2 inch PE - Walnut St. Adairville | 1373.58 | 1467.4 | -93.82 | -6.394% | 0.004395% | 1373.58 | 1467.4 | -93.82 | 2011-10-01 | 2012-09-30 | 2012-04-20 | 04 | 2012-09-28 | 09
| 050.30955 | Ultra Shore Shoring Box | Ultra Shore Shoring Box to be used in the Mayfield, KY area. | 8334.12 | 7830.4 | 503.72 | 6.433% | 0.02667% | 8334.12 | 7830.4 | 503.72 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.23356 | 050.2734.Massey Springs Ext. | 420 ft. of 2 inch PE to serve assisted livining development | 3290.89 | 4654.13 | 367.68 | 7.9% | 0.01607% | 5021.81 | 4654.13 | 367.68 | 2011-10-01 | 2012-09-30 | 2010-05-27 | 05 | 2010-09-28 | 09
| 050.21071 | Danville 09 Non Growth | Danville 09 Non Growth | 766.99 | 0 |  |  | 2.106% | 658259.26 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21628 | 050.BGR.GLS.HWY 31W RELOC. | 1100 FT OF 2" PE - HYW 31W - MUNFORDVILLE | -2610.34 | 53495 | 15396.45 | 28.78% | 0.2204% | 68891.45 | 53495 | 15396.45 | 2011-10-01 | 2012-09-30 | 2008-11-11 | 11 | 2009-11-11 | 11
| 050.22391 | 050.KY.BowlGrnIntegFunct2010 | 050.KY.BowlGrnIntegFunct2010 | 1648.56 | 0 |  |  | 4.078% | 1274706.68 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 366118.28 | 0 |  |  | 1.43% | 446898.36 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 79886.98 | 0 |  |  | 0.5513% | 172316.88 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 162353.51 | 0 |  |  | 0.7956% | 248664.44 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 1594.86 | 0 |  |  | 0.0379% | 11844.63 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24067 | BowlingLeakCP/LeakClamps | Bowling Green KY Leak Functional - CP/Leak Clamps | 230285.07 | 0 |  |  | 1.418% | 443282.41 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24072 | KY.ShelbyvilleLeakCP/LeakClmps | Shelbyville KY Leak Functional - CP/Leak Clamps | 11685.43 | 0 |  |  | 0.06402% | 20008.1 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 86191.03 | 0 |  |  | 0.4175% | 130483.39 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 77761.58 | 0 |  |  | 0.7126% | 222707.02 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 190345.6 | 0 |  |  | 0.7221% | 225691.22 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 10809.31 | 0 |  |  | 0.08612% | 26915.96 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 9595.21 | 0 |  |  | 0.07741% | 24194.2 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 101960 | 0 |  |  | 0.5529% | 172790.51 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 33856.79 | 0 |  |  | 0.2543% | 79489.73 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 158690.22 | 0 |  |  | 0.9197% | 287437.8 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24946 | 050.2636.Pleasant Valley Rd. | Install 1244 ft 2 Inch PE | 9187.26 | 2730.05 | 6496.73 | 238% | 0.02952% | 9226.78 | 2730.05 | 6496.73 | 2011-10-01 | 2012-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
| 050.24089 | DanvillePRPMeters | Danville KY PRP Functional - Meters | 913.81 | 0 |  |  | 0.007572% | 2366.58 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 1614.8 | 0 |  |  | 0.01455% | 4546.81 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-20 | 09 | 2016-09-30 | 09
| 050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 106011.12 | 0 |  |  | 0.5215% | 162995.26 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23834 | DanvilleIntegRegs | Danville Non Growth Regs Functional | 40612.75 | 0 |  |  | 0.194% | 60629.96 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.21083 | Paducah 09 Non Growth | Paducah 09 Non Growth | 10778.74 | 0 |  |  | 3.097% | 967937.15 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.24068 | GlasgowLeakCP/LeakClamps | Glasgow Leak Functional - CP/Leak Clamps | 68182.18 | 0 |  |  | 0.5543% | 173247.87 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23381 | 050.2638.Mayfield Bypass | Relocate required due to KYDOT improvements | 164.89 | 49488.84 | 96649 | 195.3% | 0.4676% | 146137.84 | 49488.84 | 96649 | 2011-10-01 | 2012-09-30 | 2010-06-09 | 06 | 2010-09-28 | 09
| 050.29013 | PRP.2738.S COURT.RETIRE | RETIRE 2in STEEL MAIN ON SOUTH COURT - BARE PIPE | 1246.12 | 1867.68 | -621.56 | -33.28% | 0.003987% | 1246.12 | 1867.68 | -621.56 | 2011-10-01 | 2012-09-30 | 2012-01-01 | 01 | 2013-01-01 | 01
| 050.28973 | KY Emergency Regulators | Regulators for emergency replacements | 19154.79 | 30240.02 | -11085.23 | -36.66% | 0.06129% | 19154.79 | 30240.02 | -11085.23 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 30517.13 | 0 |  |  | 0.09806% | 30649.04 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.29127 | 050.2636.Misc Equipment | Purchase Heath RMLD and 6 " Fusion Machine | 34840.17 | 34772.07 | 68.1 | 0.1958% | 0.1115% | 34840.17 | 34772.07 | 68.1 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.25118 | 050.2734.Daisy Field Ct. Relo | Relocate 450 ft. of 2" PE Main | 719.21 | 4131.13 | -335.43 | -8.12% | 0.01214% | 3795.7 | 4131.13 | -335.43 | 2011-10-01 | 2012-09-30 | 2011-02-28 | 02 | 2011-09-28 | 09
| 050.30003 | PRP.2736.EMPIRE DIST EXT | PRP.2736.EMPIRE DIST EXT | 176683.85 | 181533.29 | -4849.44 | -2.671% | 0.5653% | 176683.85 | 181533.29 | -4849.44 | 2011-10-01 | 2012-09-30 | 2012-03-28 | 03 | 2012-09-28 | 09
| 050.26812 | 050.PRP.2634.Woodson St. Rt. | Retire 244 Ft 2 Inch Bare in Madisonville 3 services to be move to main across the street. | -12.94 | 777.48 | 929.65 | 119.6% | 0.005462% | 1707.13 | 777.48 | 929.65 | 2011-10-01 | 2012-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.27137 | 050.2636.Plantation Pointe 2 | Install 1000 ft 2 Inch PE | -778.95 | 5694.69 | -1889.7 | -33.18% | 0.01217% | 3804.99 | 5694.69 | -1889.7 | 2011-10-01 | 2012-09-30 | 2010-12-01 | 12 | 2011-04-01 | 04
| 050.29945 | PRP.2734 Morgantown Rd | Replace Bare Main due to leakage - Morgantown Rd. between Brevard & Parkway | 4726.2 | 6917.11 | -2190.91 | -31.67% | 0.01512% | 4726.2 | 6917.11 | -2190.91 | 2011-10-01 | 2012-09-30 | 2012-03-15 | 03 | 2012-09-28 | 09
| 050.28127 | 2738.CAM.EQUIPMENT 2012 | BOSS III ELECTROFUSION, CONCRETE SAW, DITCH WITCH LOCATOR, SENSIT GOLD CGI, GAUGES | 25783.1 | 19736.15 | 6046.95 | 30.64% | 0.08249% | 25783.1 | 19736.15 | 6046.95 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.30101 | 050.2637.Sivley Dr. | Install 210 ft of 2 Inch PE to serve 2 residential customers | 1705.92 | 3170.24 | -1464.32 | -46.19% | 0.005458% | 1705.92 | 3170.24 | -1464.32 | 2011-10-01 | 2012-09-30 | 2012-04-10 | 04 | 2012-09-28 | 09
| 050.30241 | 050.Sir Charles Ct Ext II | Install 100 ft. 2 inch PE for one customer. | 1049.92 | 1493.17 | -443.25 | -29.69% | 0.003359% | 1049.92 | 1493.17 | -443.25 | 2011-10-01 | 2012-09-30 | 2012-05-14 | 05 | 2012-06-30 | 06
| 050.28120 | 050.2602.Laptops and Desktops | Purchase and retire laptops and Desktops | 120444.62 | 121087.48 | -642.86 | -0.5309% | 0.3854% | 120444.62 | 121087.48 | -642.86 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-09-28 | 09
| 050.26418 | 050.2636.Autumn Creek | Install 1166 Ft 2 Inch PE to serve 22 residential lots | -44.06 | 12367.15 | -4890.85 | -39.55% | 0.02392% | 7476.3 | 12367.15 | -4890.85 | 2011-10-01 | 2012-09-30 | 2011-06-20 | 06 | 2011-09-28 | 09
| 050.28803 | PRP.2634. Hanson St. Replacem | Replacing LP Bare Stl. main with 2,789 Ft 2 Inch PE IP | 129877.86 | 138003.74 | -8125.88 | -5.888% | 0.4156% | 129877.86 | 138003.74 | -8125.88 | 2011-10-01 | 2012-09-30 | 2011-12-27 | 12 | 2012-09-28 | 09
| 050.26745 | 050.2734.Commerce and B White | 1875 ft. of 2 inch PE - Commerce and B. White - Elkton | 4010.11 | 8119.62 | -383.01 | -4.717% | 0.02475% | 7736.61 | 8119.62 | -383.01 | 2011-10-01 | 2012-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.26935 | 2739.SVILL.2011-12 OFFICE | TURN KEY-LOT9b HI POINT INDUST PARK,LAND&BUILDING,LANDSCAPE,BUILD,ASPHALT,CONCRETE BINS,FENCE,700ft SIDEWALK ON RD FRONTAGE,USING LOCAL CONTRACTORS AND MATERIAL SUPPLIERS,INCLUDE DETENTION BASIN. DEAN SANDERSON-DIR FACILITIES MANAGEMENT - HAS FACILITATED | 749924.89 | 745000 | 386975.62 | 51.94% | 3.622% | 1131975.62 | 745000 | 386975.62 | 2011-10-01 | 2012-09-30 | 2011-08-15 11:05 | 08 | 2012-02-15 | 02
| 050.27142 | Gas_line_tracer_kit | We are requesting to purchase a Jameson model 15-316-300-GL gas line tracer kit. The kit includes mini duct hunter with bullet nose tip, stuffing box w/ 3/4" NPT male threads, accessory kit, & instructions/manual. | 76.09 | 1131.31 | -24.14 | -2.134% | 0.003542% | 1107.17 | 1131.31 | -24.14 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27207 | 050.2635.Hwy 62 | Install 2,112 feet 4 Inch PE to serve natural gas fleet fueling station. | 33317.01 | 7683.47 | 26564.68 | 345.7% | 0.1096% | 34248.15 | 7683.47 | 26564.68 | 2011-10-01 | 2012-09-30 | 2009-08-19 | 08 | 2009-09-28 | 09
| 050.28838 | 2612.Misc.Equipment | Calibration and Measurement Equipment | 8751.23 | 14515.22 | -5763.99 | -39.71% | 0.028% | 8751.23 | 14515.22 | -5763.99 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.27156 | Battery powered EF machine | We would like to purchase a new battery powered EF machine. These machines are good for getting into tight spaces and places where we cannot get our large crew trucks. The unit we want to purchase is the Boss III. | 3534.28 | 3751.8 | -217.52 | -5.798% | 0.01131% | 3534.28 | 3751.8 | -217.52 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.26506 | 050.2637.Adams St Retirement | Abandon 1,257 feet of 2 inch steel | -15.2 | 3656.15 | -1323.19 | -36.19% | 0.007464% | 2332.96 | 3656.15 | -1323.19 | 2011-10-01 | 2012-09-30 | 2011-07-11 | 07 | 2011-09-28 | 09
| 050.29411 | PRP.2734.11th and Kenton | 11th and Kenton PRP Replacement | 63275.09 | 83426.33 | -20151.24 | -24.15% | 0.2025% | 63275.09 | 83426.33 | -20151.24 | 2011-10-01 | 2012-09-30 | 2012-02-14 | 02 | 2012-09-28 | 09
| 050.29298 | 2737.SHAWNEE RUN | INSTALL 312ft OF 2in PE WITH A FARM TAP SET UP FOR FUTURE DISTRIBUTION SYSTEM TO SERVE ONE CUSTOMER | 665.53 | 8042.33 | -7376.8 | -91.72% | 0.002129% | 665.53 | 8042.33 | -7376.8 | 2011-10-01 | 2012-09-30 | 2012-01-20 | 01 | 2013-01-20 | 01
| 050.31735 | 050.009.OMU Uprate 040.11988 | Project to capture entries that need to be made related to the Owensboro Municipal Utilities Uprate Project 040.11988 unitized in Aug 2004. This project was to install Msmt and regulation equipment to uprate approximately 194,557 feet of 6 & 8 inch pipeli | 134528 | 10000 | 124528 | 1245% | 0.4304% | 134528 | 10000 | 124528 | 2011-10-01 | 2012-09-30 | 2012-08-22 14:42 | 08 | 2013-03-31 | 03
| 050.30751 | 050.2635.Eddyville TB Relocat | Relocate Eddyville TB to get HPD gas from behind Hotels | 53903.02 | 56645.75 | -2742.73 | -4.842% | 0.1725% | 53903.02 | 56645.75 | -2742.73 | 2011-10-01 | 2012-09-30 | 2012-05-25 | 05 | 2012-09-28 | 09
| 050.30261 | PRP.2737.HAR.W BROADWAY REPL | INSTALL 225ft OF 2in PE TO REPLACE 2in STEEL BARE MAIN UNDER PRP SYSTEM INTEGRITY | 13577.29 | 7397.41 | 6179.88 | 83.54% | 0.04344% | 13577.29 | 7397.41 | 6179.88 | 2011-10-01 | 2012-09-30 | 2012-04-11 | 04 | 2013-04-11 | 04
| 050.30651 | 2739.ULTRA SHORE SHORING EQUIP | PURCHASE ULTRA SHORE SHORING EQUIPMENT | 8853.11 | 7830.4 | 1022.71 | 13.06% | 0.02833% | 8853.11 | 7830.4 | 1022.71 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.31275 | 050.2636.Burton Rd. | Install 210 ft 2 Inch PE | 473.49 | 1584.39 | -1110.9 | -70.12% | 0.001515% | 473.49 | 1584.39 | -1110.9 | 2011-10-01 | 2012-09-30 | 2012-05-25 | 05 | 2012-09-28 | 09
| 050.30565 | 050.2736.TB 2 Reg. Replacement | Replace dated 2" Axel Flow regulators with 4" Mooney Regs. | 46702.06 | 58944.31 | -12242.25 | -20.77% | 0.1494% | 46702.06 | 58944.31 | -12242.25 | 2011-10-01 | 2012-09-30 | 2012-06-01 | 06 | 2012-09-28 | 09
| 050.30731 | 050.2637.PrincessJennifer Ext | Install 110 ft. 2 inch PE for one existing residential customer requesting natural gas. | 1046.14 | 912.84 | 133.3 | 14.6% | 0.003347% | 1046.14 | 912.84 | 133.3 | 2011-10-01 | 2012-09-30 | 2012-06-04 | 06 | 2012-07-28 | 07
| 050.24144 | 050.2612.REFURB METERS FY11 | cc2612 KY Refurb Meters FY 2011 | 4130.89 | 248506 | -61209.42 | -24.63% | 0.5993% | 187296.58 | 248506 | -61209.42 | 2011-10-01 | 2012-09-30 | 2010-09-22 | 09 | 2011-09-30 | 09
| 050.21079 | Princeton 09 Non Growth | Princeton 09 Non Growth | 2647.25 | 0 |  |  | 0.6161% | 192545.95 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23431 | 050.2734.Springfield VII | 1200 ft. of 2 inch PE - Springfield VII | -365.06 | 6165.79 | -2246.49 | -36.43% | 0.01254% | 3919.3 | 6165.79 | -2246.49 | 2011-10-01 | 2012-09-30 | 2010-06-25 | 06 | 2010-09-28 | 09
| 050.22432 | 050.KY.DanvilleLeakFunct2010 | 050.KY.DanvilleLeakFunct2010 | 435.52 | 0 |  |  | 0.5924% | 185153.31 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.24813 | 050.2634. Bruest Heaters | Purchase and retire Bruest Heaters | 1753.45 | 9073.76 | -268.41 | -2.958% | 0.02817% | 8805.35 | 9073.76 | -268.41 | 2011-10-01 | 2012-09-30 | 2010-12-09 | 12 | 2011-09-28 | 09
| 050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 50202.46 | 0 |  |  | 0.2476% | 77396.13 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 34459.61 | 0 |  |  | 0.1432% | 44758.09 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24037 | PaducahLeakRegs | Paducah Leak Regs Functional | 4831.45 | 0 |  |  | 0.04013% | 12541.21 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 14411.22 | 0 |  |  | 0.08805% | 27518.06 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 138074.51 | 0 |  |  | 0.6248% | 195292.77 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 97884.49 | 0 |  |  | 0.6231% | 194738.19 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 15144.26 | 0 |  |  | 0.1332% | 41628 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23831 | BowlingGreenIntegRegs | Bowling Green Non Growth Regs Functional | 34032.38 | 0 |  |  | 0.1875% | 58611.72 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5505.61 | 0 |  |  | 0.05809% | 18155.12 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 64905.05 | 0 |  |  | 0.2286% | 71434.64 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 23873 | 0 |  |  | 0.1113% | 34795.84 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 36498.01 | 0 |  |  | 0.2187% | 68348.15 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 328161.74 | 0 |  |  | 2.118% | 662106.09 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24929 | 2738.W SALOMA 2011 | INSTALL4000ft OF 2in PE FOR GRAIN DRYER ON W SALOMA ROAD REG STATION INCLUDED | -54.62 | 3861.54 | 13773.34 | 356.7% | 0.05642% | 17634.88 | 3861.54 | 13773.34 | 2011-10-01 | 2012-09-30 | 2011-02-04 | 02 | 2012-02-01 | 02
| 050.24853 | 2737.PERRYVILLE PURCH REBUILD | REBUILD PERRYVILLE PURCHASE STATION ADDING 1st CUT REGULATION | -151.36 | 48209.34 | 9791.13 | 20.31% | 0.1856% | 58000.47 | 48209.34 | 9791.13 | 2011-10-01 | 2012-09-30 | 2011-01-06 | 01 | 2011-10-01 | 10
| 050.24090 | OwensboroPRPMeters | Owensboro KY PRP Functional - Meters | 65877.3 | 0 |  |  | 0.2108% | 65877.3 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.28966 | 050.2735.Reynolds Rd. Ext. | 300 ft. of 2 inch - Reynolds Rd. Ext. - Glasgow | 9508.19 | 8637.75 | 870.44 | 10.08% | 0.03042% | 9508.19 | 8637.75 | 870.44 | 2011-10-01 | 2012-09-30 | 2011-11-14 | 11 | 2012-09-28 | 09
| 050.29008 | 2739.FURNITURE - NEW OFFICE | PURCHASE DESKS, CHAIRS, SHELVING, TV, DISHWASHER, RANGE, REFRIDGERATOR AND OTHER ITEMS FOR THE NEW OFFICE IN SHELBYVILLE | 31729.86 | 27341.81 | 4388.05 | 16.05% | 0.1015% | 31729.86 | 27341.81 | 4388.05 | 2011-10-01 | 2012-09-30 | 2011-08-15 11:05 | 08 | 2012-02-15 | 02
| 050.26310 | CampbellsvillePRPMeters | Campbellsville KY PRP Functional - Meters | 1239.04 | 0 |  |  | 0.005078% | 1587.04 | Not Budgeted |  | 2011-10-01 | 2012-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26221 | 050.2734.Franklin Warehouse | Replace existing metal building on Franklin Warehouse site. Existing building is approx. 70 years old . Approved FY 2011 Budget = $63,500.00 | 1003.94 | 92613.92 | -3302.78 | -3.566% | 0.2858% | 89311.14 | 92613.92 | -3302.78 | 2011-10-01 | 2012-09-30 | 2011-06-20 | 06 | 2011-09-28 | 09
| 050.29806 | PRP.2734.GREENLAWN AREA | PRP.2734.GREENLAWN AREA | 319066.64 | 356768.28 | -37701.64 | -10.57% | 1.021% | 319066.64 | 356768.28 | -37701.64 | 2011-10-01 | 2012-09-30 | 2011-10-15 | 10 | 2012-09-28 | 09
| 050.29650 | 2738.CVILLE BYPASS.GOODYEAR12 | INSTALL 2in PE FOR NEW GOODYEAR TIRE STORE ON THE BYPASS | -1187.49 | 4079.23 | -5266.72 | -129.1% | -0.003799% | -1187.49 | 4079.23 | -5266.72 | 2011-10-01 | 2012-09-30 | 2011-12-01 | 12 | 2012-12-01 | 12
| 050.28356 | 050.2637.NFriendship Relocate | Relocate 1,350' - 2" PE due to sewer main construction. | 3425.12 | 6218.9 | -2793.78 | -44.92% | 0.01096% | 3425.12 | 6218.9 | -2793.78 | 2011-10-01 | 2012-09-30 | 2011-11-21 | 11 | 2011-12-30 | 12
| 050.26285 | PRP.2737.HAR.McCLELLAN DR | REPLACE 200ft OF BARE STEEL WITH 2in PE ON McCLELLAN DRIVE | 269.03 | 6818.61 | -2869.82 | -42.09% | 0.01263% | 3948.79 | 6818.61 | -2869.82 | 2011-10-01 | 2012-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.28572 | PRP.2734.Creekwood Ave Replc | Relocates 170 ft. of 6 inch hot tar - Creekwood Ave, | 3893.37 | 6109.64 | -2216.27 | -36.27% | 0.01246% | 3893.37 | 6109.64 | -2216.27 | 2011-10-01 | 2012-09-30 | 2011-11-16 | 11 | 2012-09-28 | 09
| 050.26810 | 050.2734.Traditions III | 2 inch PE Extension - Traditions III - B.G. | 6073.14 | 7458.67 | 625.52 | 8.386% | 0.02587% | 8084.19 | 7458.67 | 625.52 | 2011-10-01 | 2012-09-30 | 2011-08-15 | 08 | 2011-09-28 | 09
| 050.28613 | 050.2636.35D Excavator Trailer | Purchase trailer for 35D Excavator. | 10012.38 | 10842.35 | -829.97 | -7.655% | 0.03204% | 10012.38 | 10842.35 | -829.97 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.28197 | 050.2734.Baileys Farm Final | 2 inch PE Extension - Baileys Farms Final Phase | 8287.75 | 7990.4 | 297.35 | 3.721% | 0.02652% | 8287.75 | 7990.4 | 297.35 | 2011-10-01 | 2012-09-30 | 2011-11-07 | 11 | 2012-09-28 | 09
| 050.27102 | Cell EFM Units | New customer Cell /I/P EFM's | 49.49 | 30585.8 | -1519.85 | -4.969% | 0.093% | 29065.95 | 30585.8 | -1519.85 | 2011-10-01 | 2012-09-30 | 2011-08-30 | 08 | 2011-09-30 | 09
| 050.25440 | 050.2637.Marina Village Ext | Install 300 feet of 2 inch poly for two new residential customers. | 3043.48 | 2351.45 | -490.15 | -20.84% | 0.005955% | 1861.3 | 2351.45 | -490.15 | 2011-10-01 | 2012-09-30 | 2011-06-15 | 06 | 2011-09-28 | 09
| 050.28434 | 2737.DAN.ODORIZOR REPLACE | REP[LACE ODORIZOR AND TANKS AT THE DANVILLE PURCHASE STATION ON HUSTONVILLE ROAD | 52403.45 | 49616.6 | 2786.85 | 5.617% | 0.1677% | 52403.45 | 49616.6 | 2786.85 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.27383 | 050.2636.Sensit G2 | Purchase 3- Sensit G2 leak machines , retire 3 Sensit Golds | 514.11 | 4984.96 | -79.34 | -1.592% | 0.0157% | 4905.62 | 4984.96 | -79.34 | 2011-10-01 | 2012-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.28194 | 050.2637.Hwy 45 S Rev Ext | Install 375' - 4" PE, 1,470 - 2" PE for 5 rcommercial customers. | 23312.38 | 24722.53 | -1410.15 | -5.704% | 0.07459% | 23312.38 | 24722.53 | -1410.15 | 2011-10-01 | 2012-09-30 | 2011-11-01 | 11 | 2012-09-28 | 09
| 050.27236 | 050.2734.W Madison 2inch Ext | 445 ft. of 2 inch PE - West Madison Ext. | -2764.41 | 907.31 | -330.05 | -36.38% | 0.001847% | 577.26 | 907.31 | -330.05 | 2011-10-01 | 2012-09-30 | 2011-09-15 | 09 | 2011-12-30 | 12
| 050.23525 | 2737.PERRYVILLE TBS RELOCATE | RELOCATE THE TBS FROM PRESENT LOCATION TO REYNOLDS PROPERTY OFF OF HIGHWAY 68 | 35.31 | 137270.6 | 21022.29 | 15.31% | 0.5065% | 158292.89 | 137270.6 | 21022.29 | 2011-10-01 | 2012-09-30 | 2010-08-20 | 08 | 2011-03-25 | 03
| 050.31303 | Wmson Equipment | Misc Wmson equip incl. 4 hole saw, 4 inch cup, 2 inch and 3 inch wheel brushes, wire coupon retainer. All for use in the Mayfield area. | 2042.51 | 2085.66 | -43.15 | -2.069% | 0.006535% | 2042.51 | 2085.66 | -43.15 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.32025 | 050.2636.River Rd. | Install 500 ft. 2 Inch PE to serve air handlers for water treatment plant | 790.78 | 961.77 | -170.99 | -17.78% | 0.00253% | 790.78 | 961.77 | -170.99 | 2011-10-01 | 2012-09-30 | 2012-09-24 | 09 | 2013-02-14 | 02
| 050.31536 | 050.2634.Hwy 425 | Install 1100 Ft. 2 Inch PE to serve two Commercial customers | 6506.53 | 5245.76 | 1260.77 | 24.03% | 0.02082% | 6506.53 | 5245.76 | 1260.77 | 2011-10-01 | 2012-09-30 | 2012-07-15 | 07 | 2012-09-28 | 09
| 050.31923 | 050.2637.MCHS Ext | Install 650 feet of 2 inch poly for new McCracken County High School | 11221.73 | 14136.48 | -2914.75 | -20.62% | 0.0359% | 11221.73 | 14136.48 | -2914.75 | 2011-10-01 | 2012-09-30 | 2012-09-10 | 09 | 2012-09-28 | 09
| 050.31066 | PRP.2638. Mayfield 2012 | PRP.2638. Mayfield 2012 | 186694.67 | 267423.93 | -80729.26 | -30.19% | 0.5973% | 186694.67 | 267423.93 | -80729.26 | 2011-10-01 | 2012-09-30 | 2012-06-30 | 06 | 2012-09-29 | 09
| 050.31804 | PRP.2636.18th and Allen St. | Retire 78 ft 4 Inch Bare Stl. Due to leak in intersection | 3971.57 | 4218.84 | -247.27 | -5.861% | 0.01271% | 3971.57 | 4218.84 | -247.27 | 2011-10-01 | 2012-09-30 | 2012-08-14 | 08 | 2012-09-28 | 09
| 050.30789 | 050.2634.Seneit Gold Replace | Replace Damaged Senst Gold | 1431.22 | 1761.3 | -330.08 | -18.74% | 0.004579% | 1431.22 | 1761.3 | -330.08 | 2011-10-01 | 2012-09-30 | 2011-11-04 14:41 | 11 | 2012-09-30 | 09
| 050.31615 | 050.2602.Laptop and Desktop 2 | Purchase and retire Desktop and Laptop computers | 14153.73 | 60269.43 | -46115.7 | -76.52% | 0.04529% | 14153.73 | 60269.43 | -46115.7 | 2011-10-01 | 2012-09-30 | 2011-10-01 | 10 | 2012-10-31 | 10
| 050.31690 | 050.2734.S.Glen Ext. | Estimate SouthGlen - 7035 ft -4 inch - 9665 ft -2 inch | 16273.56 | 18685 | -2411.44 | -12.91% | 0.05207% | 16273.56 | 18685 | -2411.44 | 2011-10-01 | 2012-09-30 | 2012-06-25 | 06 | 2012-09-28 | 09
| 050.32054 | 050.2636.Hospital Loop Ext. | Install 1493 Ft 4 Inch PE to serve new Medical Office Building | 764.91 | 1573.92 | -809.01 | -51.4% | 0.002447% | 764.91 | 1573.92 | -809.01 | 2011-10-01 | 2012-09-30 | 2012-09-27 | 09 | 2013-09-28 | 09

## 2011a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2011
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2011 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.20823 | 050.BGR.8"CENTER LINE HPD | 8" CENTER LINE HPD RELOC PHASE I - B.G. | -49723.92 | 1398465 | 444330.93 | 31.77% | 8.508% | 1842795.93 | 1398465 | 444330.93 | 2010-10-01 | 2011-09-30 | 2008-07-25 | 07 | 2009-07-25 | 07
| 050.21069 | Hopkinsville 09 Non Growth | Hopkinsville 09 Non Growth | 379.55 | 0 |  |  | 2.202% | 476835.1 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23479 | 050.2638.Wtr Valley Imp | Improvements include the installation of a Balon check valve | -74.34 | 2554.89 | 1202.15 | 47.05% | 0.01735% | 3757.04 | 2554.89 | 1202.15 | 2010-10-01 | 2011-09-30 | 2010-08-02 | 08 | 2010-09-28 | 09
| 050.23217 | 050.2637.New Hope Rd Ext | 414 feet of 2 inch poly pipe for three exisrting residential customers | -85.77 | 2164.15 | 789.8 | 36.49% | 0.01364% | 2953.95 | 2164.15 | 789.8 | 2010-10-01 | 2011-09-30 | 2010-03-03 | 03 | 2010-04-25 | 04
| 050.24224 | 050.2637.Lake City Purch Imp | We have had problems with three of the four Nordstrom valves. One is leaking and cannot be repaired. | 44805.27 | 37209.7 | 7595.57 | 20.41% | 0.2069% | 44805.27 | 37209.7 | 7595.57 | 2010-10-01 | 2011-09-30 | 2010-10-18 | 10 | 2010-12-28 | 12
| 050.24792 | 050.2737.10402 | Mec Forfeiture | -740 | 0 |  |  | -0.003417% | -740 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.24795 | 050.2638.918907 | MEC FORFEITURE | -510 | 0 |  |  | -0.002355% | -510 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.24796 | 050.2636.Ditch Project | Blanket Project for Main replacements due to Ditch projects in Owensboro | 33771.84 | 83463.68 | -49691.84 | -59.54% | 0.1559% | 33771.84 | 83463.68 | -49691.84 | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2011-09-28 | 09
| 050.22352 | 050.KY.BowlgGrnGrowthFunct2010 | 050.KY.BowlgGrnGrowthFunct2010 | -11374.75 | 0 |  |  | 3.204% | 693869.56 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22354 | 050.KY.HopkinsGrowthFunct2010 | 050.KY.HopkinsGrowthFunct2010 | -2239.41 | 0 |  |  | 0.7437% | 161086.91 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 17013.19 | 0 |  |  | 0.07855% | 17013.19 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 50803.16 | 0 |  |  | 0.2346% | 50803.16 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 231608.12 | 0 |  |  | 1.071% | 231993.14 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24818 | 050.2734.0917317-01 | Mec Forfeiture | -568 | 0 |  |  | -0.002622% | -568 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 330842.08 | 0 |  |  | 1.527% | 330842.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 42664.13 | 0 |  |  | 0.197% | 42664.13 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24030 | HopkinsvilleLeakRegs | Hopkinsville Leak Regs Functional | 2173.95 | 0 |  |  | 0.01004% | 2173.95 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24032 | CampbellsvilleLeakRegs | CampbellsvilleLeakRegs | 17135.94 | 0 |  |  | 0.07912% | 17135.94 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24070 | DanvilleLeakCP/LeakClamps | Danville Leak Functional - CP/Leak Clamps | 105288.45 | 0 |  |  | 0.4861% | 105288.45 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24071 | CampbellLeakCP/LeakClamps | Campbellsville KY Leak Functional - CP/Leak Clamps | 36344.29 | 0 |  |  | 0.1678% | 36344.29 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24076 | PaducahLeakCP/LeakClamps | Paducah Leak Functional - CP/Leak Clamps | 16625.55 | 0 |  |  | 0.07676% | 16625.55 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 89928.22 | 0 |  |  | 0.4152% | 89928.22 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 79382.71 | 0 |  |  | 0.3665% | 79382.71 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24127 | 050.2636.Veterans Blvd. Relo | Relocate 900 Ft 6 Inch stl. with 6 Inch PE due to River Front project | 48635.56 | 56991.48 | 6711.02 | 11.78% | 0.2941% | 63702.5 | 56991.48 | 6711.02 | 2010-10-01 | 2011-09-30 | 2010-09-21 | 09 | 2010-12-25 | 12
| 050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 370876.16 | 0 |  |  | 1.712% | 370876.16 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 91606.75 | 0 |  |  | 0.4447% | 96319.39 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 288258.04 | 0 |  |  | 1.336% | 289291.07 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 33659.77 | 0 |  |  | 0.1554% | 33659.77 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23444 | 050.2636.Graystone Phase 5 | Install 1015 Ft 2 Inch PE | -59.8 | 8192.72 | -1587.63 | -19.38% | 0.0305% | 6605.09 | 8192.72 | -1587.63 | 2010-10-01 | 2011-09-30 | 2010-07-09 | 07 | 2010-09-28 | 09
| 050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 14398.88 | 0 |  |  | 0.06648% | 14398.88 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23003 | 050.2637.21st & Monroe | Main replacement project due to leakage | -1498.33 | 42170.28 | 17172.9 | 40.72% | 0.274% | 59343.18 | 42170.28 | 17172.9 | 2010-10-01 | 2011-09-30 | 2009-11-13 | 11 | 2009-11-30 | 11
| 050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 587458.86 | 0 |  |  | 2.712% | 587458.86 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23526 | 2738.BARE STEEL REPLACE 2010 | REPLACE 2500ft OF BARE STEEL ROSE, CENTER AND REDMAN | 25407.63 | 80790.58 | 8031.44 | 9.941% | 0.4101% | 88822.02 | 80790.58 | 8031.44 | 2010-10-01 | 2011-09-30 | 2010-08-20 | 08 | 2011-03-25 | 03
| 050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 40058.35 | 0 |  |  | 0.1854% | 40158.41 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24863 | 060.2737.10730-01 | Mec Forfeiture | -3291 | 0 |  |  | -0.01519% | -3291 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-12 | 01 | 2011-01-12 | 01
| 050.24732 | 050.2635.Meadow Dr. | Install 100 Ft 2 Inch PE | 819.18 | 1965.11 | -1145.93 | -58.31% | 0.003782% | 819.18 | 1965.11 | -1145.93 | 2010-10-01 | 2011-09-30 | 2010-11-01 | 11 | 2011-09-28 | 09
| 050.24719 | 050.2751.MIC EQUIPMENT | EQUIPMENT FOR JODY BRAMBLETT - MIC TECHNICIAN | 11186.26 | 13685.1 | -2498.84 | -18.26% | 0.05165% | 11186.26 | 13685.1 | -2498.84 | 2010-10-01 | 2011-09-30 | 2010-10-28 | 10 | 2011-10-03 | 10
| 050.24756 | 050.2602.MDTs 2011 | Purchase MDTs | 124259.99 | 141788.07 | -17528.08 | -12.36% | 0.5737% | 124259.99 | 141788.07 | -17528.08 | 2010-10-01 | 2011-09-30 | 2010-11-11 | 11 | 2011-09-28 | 09
| 050.24773 | 2737.2011 EQUIPMENT | EQUIPMENT FOR 2011 | 27636.66 | 21562.8 | 6073.86 | 28.17% | 0.1276% | 27636.66 | 21562.8 | 6073.86 | 2010-10-01 | 2011-09-30 | 2010-11-19 | 11 | 2011-10-03 | 10
| 050.24831 | 050.2637.McGuire Ave Ext | Install 250 feet of 2 inch poly for one new tire store. | 1122.2 | 3100.98 | -1978.78 | -63.81% | 0.005181% | 1122.2 | 3100.98 | -1978.78 | 2010-10-01 | 2011-09-30 | 2010-12-17 | 12 | 2011-09-28 | 09
| 050.24775 | 050.2636.0918718-01 | Mec Forfeiture | -7487 | 0 |  |  | -0.03457% | -7487 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24782 | 050.2636.0918801-01 | Mec Forfeiture | -4065 | 0 |  |  | -0.01877% | -4065 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24774 | 050.2636.0918453-01 | Mec Forfeiture | -1285 | 0 |  |  | -0.005933% | -1285 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.21528 | TchSvr.Mea.Outsourced Meters | Oursourced meter retirments and new meter purchases | -462.63 | 195288 | 108317.37 | 55.47% | 1.402% | 303605.37 | 195288 | 108317.37 | 2010-10-01 | 2011-09-30 | 2008-10-15 | 10 | 2009-09-30 | 09
| 050.24836 | 050.2735.Electrofuse Equip | 050.2735. Electrofuse Equip | 15439.53 | 8336.9 | 7102.63 | 85.2% | 0.07128% | 15439.53 | 8336.9 | 7102.63 | 2010-10-01 | 2011-09-30 | 2010-12-27 | 12 | 2011-09-28 | 09
| 050.22357 | 050.KY.ShelbyviGrowthFunct2010 | 050.KY.ShelbyviGrowthFunct2010 | 98610.88 | 0 |  |  | 0.8332% | 180475.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 104274.89 | 0 |  |  | 0.4814% | 104274.89 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.24862 | 2739.LAW.GREEN GARDEN | INSTALL 140ft OF 2in PE AT THE END OF GREEN GARDEN IN LAWRENCEBURG | 1493.46 | 2525.04 | -1031.58 | -40.85% | 0.006895% | 1493.46 | 2525.04 | -1031.58 | 2010-10-01 | 2011-09-30 | 2011-01-11 | 01 | 2011-02-01 | 02
| 050.24889 | 050.2734.Page Rd. Franklin | 4 inch PE Ext. - Page Rd. Franklin - TSC | 7372.94 | 20777.22 | -13404.28 | -64.51% | 0.03404% | 7372.94 | 20777.22 | -13404.28 | 2010-10-01 | 2011-09-30 | 2011-01-24 | 01 | 2011-09-28 | 09
| 050.24886 | 050.2609.Rectifier Replacement | Replace damaged Rectifier | 5761.62 | 9484.72 | -3723.1 | -39.25% | 0.0266% | 5761.62 | 9484.72 | -3723.1 | 2010-10-01 | 2011-09-30 | 2011-01-20 | 01 | 2011-09-28 | 09
| 050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 9699.68 | 0 |  |  | 0.04478% | 9699.68 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24109 | KY.Storage Integ RESI MEAS | KY Storage & Transmission Non Growth Functional - RESI MEAS. Meters, regulators, and meterset items typically used for residential applications. | 2932.01 | 0 |  |  | 0.01354% | 2932.01 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-20 | 09 | 2016-09-30 | 09
| 050.24187 | Railroad Consolidation - KY | Payment of Railroad Crossings for 20 - 25 years - 7 Crossings | 68.47 | 15529.5 | -6677.16 | -43% | 0.04087% | 8852.34 | 15529.5 | -6677.16 | 2010-10-01 | 2011-09-30 | 2010-09-30 | 09 | 2010-10-30 | 10
| 050.23558 | 050.2634.Las Vegas Ave.Ret. | Retire 251 ft. 2 Inch Stl. | 373.92 | 139.29 | 421.19 | 302.4% | 0.002588% | 560.48 | 139.29 | 421.19 | 2010-10-01 | 2011-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 119515.1 | 0 |  |  | 0.5518% | 119515.1 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 204908.11 | 0 |  |  | 0.9461% | 204908.11 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24817 | 050.2735.916321-01 | Mec Forfeiture | -1445 | 0 |  |  | -0.006672% | -1445 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.24869 | 050.2637.Tyree Rd Main Ext | Install 25 feet of 2 inch pe for one customer | 1327.77 | 602.74 | 725.03 | 120.3% | 0.00613% | 1327.77 | 602.74 | 725.03 | 2010-10-01 | 2011-09-30 | 2011-01-13 | 01 | 2011-02-24 | 02
| 050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 235605.1 | 0 |  |  | 1.079% | 233608.75 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 194421.58 | 0 |  |  | 0.8976% | 194421.58 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 14925.89 | 0 |  |  | 0.06891% | 14925.89 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23495 | 2937.TYRONE.MAGO CONSTRUCTION | INSTALL4200ft OF 6in PE FOR MAGO CONSTRUCTION ASPHALT PLANT ON TYRONE ROAD | -60373.53 | 88085.69 | 15382.54 | 17.46% | 0.4777% | 103468.23 | 88085.69 | 15382.54 | 2010-10-01 | 2011-09-30 | 2010-08-12 | 08 | 2011-02-01 | 02
| 050.24182 | 050.2634.N. Seminary Rplmt. | Replace approximately 1350 Ft 4 Inch LP Stl. with 2 Inch IP | 47765.32 | 38419.72 | 9345.6 | 24.33% | 0.2205% | 47765.32 | 38419.72 | 9345.6 | 2010-10-01 | 2011-09-30 | 2010-09-30 | 09 | 2011-06-30 | 06
| 050.24802 | 050.2602.Software Purchase | Purchase 2010 Office Software | 65605.8 | 74149.07 | -8543.27 | -11.52% | 0.3029% | 65605.8 | 74149.07 | -8543.27 | 2010-10-01 | 2011-09-30 | 2010-12-02 | 12 | 2011-09-28 | 09
| 050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 100131.32 | 0 |  |  | 0.4623% | 100131.32 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 46770.89 | 0 |  |  | 0.2159% | 46770.89 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.27029 | Ice Machine | Purchase a Manitowoc model 0502A ice machine to be installed at our 3034 Parker Street warehouse for use in the Paducah area. We currently purchase our ice by the bag from Home City Ice out of Calvert City. | 4346.81 | 4769.8 | -422.99 | -8.868% | 0.02007% | 4346.81 | 4769.8 | -422.99 | 2010-10-01 | 2011-09-30 | 2011-08-18 22:13 | 08 | 2011-09-30 | 09
| 050.25885 | 050.2634.S. Locust St. Retire | Retire 628 Ft 2 Inch Stl. Main | 1424.48 | 1613.57 | -189.09 | -11.72% | 0.006577% | 1424.48 | 1613.57 | -189.09 | 2010-10-01 | 2011-09-30 | 2011-04-28 | 04 | 2011-04-28 | 04
| 050.26897 | 055.2734.Nutwood-Neal-15th | Replace Bare Steel - Nutwood-Neal-15th - 14th - Bowling Green | 112326.98 | 205063.49 | -92736.51 | -45.22% | 0.5186% | 112326.98 | 205063.49 | -92736.51 | 2010-10-01 | 2011-09-30 | 2011-08-08 | 08 | 2011-09-28 | 09
| 050.25720 | 050.3341.WATER HEATER REPLACEMENT | APPROVAL IS NEEDED TO REPLACE LEAKING WATER HEATER IN THE COLUMBIA OFFICE, WITH A RINNAI TANKLESS WATER HEATER | 6035.12 | 6142.78 | -107.66 | -1.753% | 0.02786% | 6035.12 | 6142.78 | -107.66 | 2010-10-01 | 2011-09-30 | 2011-04-25 | 04 | 2011-09-30 | 09
| 050.26329 | 050.2609.Ret Hopkinsville 10" | Retire 21,635' 10" Transmission Line. Pipe was replaced on project 050.23434 | 71151.41 | 78126 | -6974.59 | -8.927% | 0.3285% | 71151.41 | 78126 | -6974.59 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-12-30 | 12
| 050.27098 | Industrial Regulators | Back up Inventory | 4559.18 | 26046.3 | -21487.12 | -82.5% | 0.02105% | 4559.18 | 26046.3 | -21487.12 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27100 | Industrial Meters-2612 | Back up Meter | 28859.07 | 22325.4 | 6533.67 | 29.27% | 0.1332% | 28859.07 | 22325.4 | 6533.67 | 2010-10-01 | 2011-09-30 | 2011-08-30 | 08 | 2011-09-30 | 09
| 050.25253 | 050.2636.Stopper Equipment | Purchase 1 safe T L stopper LS25, 1 h17010 mueller valve changer kit and 1 safe T stopper tool 3000bv | 20097.01 | 13391.42 | 6705.59 | 50.07% | 0.09279% | 20097.01 | 13391.42 | 6705.59 | 2010-10-01 | 2011-09-30 | 2011-03-10 | 03 | 2011-09-30 | 09
| 050.25963 | 050.2634. Beveling Machine | Purchase new Beveling Machine for Madisonville to replace old non functioning machine. | 2181.95 | 2579.8 | -397.85 | -15.42% | 0.01007% | 2181.95 | 2579.8 | -397.85 | 2010-10-01 | 2011-09-30 | 2011-05-20 | 05 | 2011-09-28 | 09
| 050.27096 | 050.PRP.2609.DanielsLn 8 Inch | Relocate approximately 518 Ft 8 Inch HPD for storm sewer and rd. widening due to the new Hospital | 41035.1 | 116214.9 | -75179.8 | -64.69% | 0.1895% | 41035.1 | 116214.9 | -75179.8 | 2010-10-01 | 2011-09-30 | 2011-09-01 | 09 | 2011-09-28 | 09
| 050.26928 | 050.2618.SCBA Respirators | 4- SCBA Respirators with extra tanks for Bowling Green Area onstruction Crews | 11673.75 | 12622.54 | -948.79 | -7.517% | 0.0539% | 11673.75 | 12622.54 | -948.79 | 2010-10-01 | 2011-09-30 | 2011-08-11 | 08 | 2011-09-30 | 09
| 050.25621 | 11m Cerified test Meter | 11M Test meter for verifing Model 5 prover proof | 4262.71 | 4961.2 | -698.49 | -14.08% | 0.01968% | 4262.71 | 4961.2 | -698.49 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.26196 | 050.2736.Canton Pike | Install 2500 ft 4 Inch PE | 29084.35 | 29240.14 | -155.79 | -0.5328% | 0.1343% | 29084.35 | 29240.14 | -155.79 | 2010-10-01 | 2011-09-30 | 2011-05-01 | 05 | 2011-09-28 | 09
| 050.26540 | 050.2736.Electro Fuse Machine | Purchase portable electro fuse machine | 3419.1 | 3905.01 | -485.91 | -12.44% | 0.01579% | 3419.1 | 3905.01 | -485.91 | 2010-10-01 | 2011-09-30 | 2011-07-15 | 07 | 2011-09-30 | 09
| 050.22437 | 050.KY.OboroLeakFunct2010 | 050.KY.OboroLeakFunct2010 | -1904.7 | 0 |  |  | 2.845% | 616149.84 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23189 | 2737.STAN.HILLTOPPER 10 | INSTALL 200ft OF 2in PE ON HILLTOPPER ACROSS HUBLE | 112.83 | 4391.05 | 944.31 | 21.51% | 0.02463% | 5335.36 | 4391.05 | 944.31 | 2010-10-01 | 2011-09-30 | 2010-02-17 | 02 | 2011-02-04 | 02
| 050.23150 | 050.2739.WALKER LANE FENCE | INSTALL FENCE AROUND THE REGULATOR STATION ON WALKER LANE IN LAWRENCEBURG, KENTUCKY | 111.39 | 20540 | 20655.09 | 100.6% | 0.1902% | 41195.09 | 20540 | 20655.09 | 2010-10-01 | 2011-09-30 | 2010-02-01 | 02 | 2010-12-01 | 12
| 050.22359 | 050.KY.PrincetnGrowthFunct2010 | 050.KY.PrincetnGrowthFunct2010 | -1547.9 | 0 |  |  | 0.5091% | 110269.79 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 15946.49 | 0 |  |  | 0.07362% | 15946.49 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 6666.55 | 0 |  |  | 0.03078% | 6666.55 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24036 | OwensboroLeakRegs | Owensboro Leak Regs Functional | 23528.97 | 0 |  |  | 0.1086% | 23528.97 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24028 | BowlingGreenLeakRegs | Bowling Green Leak Regs Functional | 55494.82 | 0 |  |  | 0.2562% | 55494.82 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | -3084.27 | 0 |  |  | -0.01424% | -3084.27 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2011-09-30 | 09
| 050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 14237.94 | 0 |  |  | 0.06874% | 14888.98 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24173 | 050.2636.Electro Fuse Eq. | Purchase Electro Fuse Equipment | 693.69 | 11441.38 | 17.45 | 0.1525% | 0.05291% | 11458.83 | 11441.38 | 17.45 | 2010-10-01 | 2011-09-30 | 2010-09-27 | 09 | 2010-09-30 | 09
| 050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 221932.62 | 0 |  |  | 1.059% | 229440.7 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 251308.26 | 0 |  |  | 1.161% | 251493.29 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 378127 | 0 |  |  | 1.746% | 378127 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 19278.11 | 0 |  |  | 0.08901% | 19278.11 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23838 | MadisonvilleIntegRegs | Madisonville Non Growth Regs | 57135.32 | 0 |  |  | 0.2691% | 58276.82 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 89170.55 | 0 |  |  | 0.4117% | 89170.55 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 18542.7 | 0 |  |  | 0.08561% | 18542.7 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 24414.97 | 0 |  |  | 0.1127% | 24414.97 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 36834.59 | 0 |  |  | 0.1701% | 36834.59 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23560 | 050.2636.Insulators & Anodes | Retire ground bed & rectifier at Legion Park. Install insulators at Legion Blvd.& Warwick Dr. with Anodes | 19613.47 | 45777.27 | -8344.99 | -18.23% | 0.1728% | 37432.28 | 45777.27 | -8344.99 | 2010-10-01 | 2011-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 37756.41 | 0 |  |  | 0.1743% | 37756.41 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24220 | 050.2734.Shelton Ln. Ext | 750 ft. of 4 inch PE - Shelton Ln | -1063.03 | 2097.51 | -3160.54 | -150.7% | -0.004908% | -1063.03 | 2097.51 | -3160.54 | 2010-10-01 | 2011-09-30 | 2010-10-14 | 10 | 2011-09-28 | 09
| 050.24219 | 050.2637.May-Met Rd Ext | Extend gas main 180 feet with 4 inch pe for two exisitng residential customers requesting natural gas. | 141.76 | 2255.02 | -2113.26 | -93.71% | 0.0006545% | 141.76 | 2255.02 | -2113.26 | 2010-10-01 | 2011-09-30 | 2010-10-14 | 10 | 2010-12-28 | 12
| 050.24221 | 050.2734.Ken Bale Ext. | 1500 ft. of 4 inch PE - Ken Bale | 15279.25 | 5994.02 | 9285.23 | 154.9% | 0.07054% | 15279.25 | 5994.02 | 9285.23 | 2010-10-01 | 2011-09-30 | 2010-10-14 | 10 | 2011-09-28 | 09
| 050.23266 | 050.2634.Hwy 62 Replacement | Replace exposed 2 Inch Steel with 2 Inch PE | -15.95 | 11895.61 | 789.91 | 6.64% | 0.05857% | 12685.52 | 11895.61 | 789.91 | 2010-10-01 | 2011-09-30 | 2010-04-06 | 04 | 2010-09-28 | 09
| 050.24926 | 050.2634.Station Retirements | Retire old Station piping at Lone Star in Muhlenberg County and J L West Rd in Sacramento | 17163.4 | 12144.3 | 5019.1 | 41.33% | 0.07924% | 17163.4 | 12144.3 | 5019.1 | 2010-10-01 | 2011-09-30 | 2011-02-03 | 02 | 2011-09-28 | 09
| 050.24937 | 050.2602.Itron Purchase | Purchase new Itrons to replace ageing equipment | 84537.99 | 85358.11 | -820.12 | -0.9608% | 0.3903% | 84537.99 | 85358.11 | -820.12 | 2010-10-01 | 2011-09-30 | 2011-02-07 | 02 | 2011-09-28 | 09
| 050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 144185.75 | 0 |  |  | 0.6966% | 150877.19 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24780 | 050.2636.0918795-01 | Mec Forfeiture | -8237 | 0 |  |  | -0.03803% | -8237 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24781 | 050.2636.0918458-01 | Mec Forfeiture | -1534 | 0 |  |  | -0.007082% | -1534 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24776 | 050.2636.091859-01 | Mec Forfeiture | -354 | 0 |  |  | -0.001634% | -354 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24847 | 050.2636.TDW Drilling Machine | Purchase TDW T101b Drilling Machine | 6913.71 | 5493.58 | 1420.13 | 25.85% | 0.03192% | 6913.71 | 5493.58 | 1420.13 | 2010-10-01 | 2011-09-30 | 2011-01-04 | 01 | 2011-09-28 | 09
| 050.24909 | 050.2635.918321-01 | Mec Forfeiture | -843 | 0 |  |  | -0.003892% | -843 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24904 | 050.2635.917667-01 | Mec Forfeiture | -912 | 0 |  |  | -0.004211% | -912 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24903 | 050.2635.917295-01 | Mec Forfeiture | -852 | 0 |  |  | -0.003934% | -852 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24920 | 050.2637.Shawnee Reg Replace | Regulator at corner of Hwy 996 and Carneal ln damaged by car we plan to replace reg and relocate | 6997.33 | 10528.68 | -3531.35 | -33.54% | 0.03231% | 6997.33 | 10528.68 | -3531.35 | 2010-10-01 | 2011-09-30 | 2011-02-01 | 02 | 2011-03-30 | 03
| 050.24884 | 050.2734.0916316-01 | Mec Forfeiture | -758.8 | 0 |  |  | -0.003503% | -758.8 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-19 | 01 | 2011-01-19 | 01
| 050.24713 | 050.2636.Hwy 60 Bypass 2 | Relocate 180 Ft 2 Inch Stl and 892 Ft 2 Inch PE | 8083.07 | 10549.99 | -2466.92 | -23.38% | 0.03732% | 8083.07 | 10549.99 | -2466.92 | 2010-10-01 | 2011-09-30 | 2010-10-25 | 10 | 2011-09-28 | 09
| 050.23443 | 050.2636.Verden St. Retire | Retire 1.25 leaking Stl. main not in use | -85.95 | 1782.72 | -1347.12 | -75.57% | 0.002011% | 435.6 | 1782.72 | -1347.12 | 2010-10-01 | 2011-09-30 | 2010-07-09 | 07 | 2010-09-28 | 09
| 050.24082 | OwensboroPRPMains | Owensboro Sub-region KY PRP Functional - Mains | 1073.36 | 0 |  |  | 0.004956% | 1073.36 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 3084.81 | 0 |  |  | 0.01424% | 3084.81 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-20 | 09 | 2016-09-30 | 09
| 050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 43207.95 | 0 |  |  | 0.1995% | 43207.95 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23535 | 050.2609.Storage Misc. | Replace Safety Shut Offs and Install Methanol Injectors | 62329.46 | 113968.24 | 0 | 0% | 0.5262% | 113968.24 | 113968.24 | 0 | 2010-10-01 | 2011-09-30 | 2010-08-27 | 08 | 2010-09-28 | 09
| 050.24218 | 050.2636.Winkler Rd. | Install 700 2 Inch PE | -916.82 | 840.01 | -1756.83 | -209.1% | -0.004233% | -916.82 | 840.01 | -1756.83 | 2010-10-01 | 2011-09-30 | 2010-10-14 | 10 | 2010-11-30 | 11
| 050.22353 | 050.KY.GlasgowGrowthFunct2010 | 050.KY.GlasgowGrowthFunct2010 | -939.27 | 0 |  |  | 0.3828% | 82921.21 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.24077 | MayfieldLeakCP/LeakClamps | Mayfield Leak Functional - CP/Leak Clamps | 12541.3 | 0 |  |  | 0.0579% | 12541.3 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 106.85 | 0 |  |  | 0.0004933% | 106.85 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26048 | 050.2609.Kirkwood Rplmt | Replace 18000 Ft 6 And 8 Inch Bare pipe | 2124586.3 | 2405504.58 | -280918.28 | -11.68% | 9.809% | 2124586.3 | 2405504.58 | -280918.28 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2011-09-18 | 09
| 050.26251 | 050.2637.Friendship Relocate | Our existing 2 inch poly gas main is in the way of construction. | 1878.51 | 2030.92 | -152.41 | -7.504% | 0.008673% | 1878.51 | 2030.92 | -152.41 | 2010-10-01 | 2011-09-30 | 2011-06-15 | 06 | 2011-06-30 | 06
| 050.26270 | PRP.2638.Broadway Street | Abandon 7,525' of bare pipe. Install 6,625' of PE pipe. | 153588.58 | 212483.24 | -58894.66 | -27.72% | 0.7091% | 153588.58 | 212483.24 | -58894.66 | 2010-10-01 | 2011-09-30 | 2011-07-05 | 07 | 2011-09-16 | 09
| 050.25665 | 050.2636.Deer Valley 1 | Run gas for 78 residential lots | 73139.28 | 73139.28 | 0 | 0% | 0.3377% | 73139.28 | 73139.28 | 0 | 2010-10-01 | 2011-09-30 | 2010-12-01 | 12 | 2011-09-28 | 09
| 050.27061 | 050.2634.Oakwood Dr. | Install 2023 ft 2 Inch PE | -1095.9 | 9698.35 | -10794.25 | -111.3% | -0.00506% | -1095.9 | 9698.35 | -10794.25 | 2010-10-01 | 2011-09-30 | 2011-04-21 | 04 | 2011-09-28 | 09
| 050.27159 | Sensit Golds (2) | We are requesting to purchase (2) new Sensit gold C.G.I's for use in the Mayfield area. We are "trading in" two older units for $300 each. These should be the new highly anticipated G-2 models. | 2927.68 | 3215.32 | -287.64 | -8.946% | 0.01352% | 2927.68 | 3215.32 | -287.64 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.25289 | Pipe splitting tool for Shelbyville | Approval is needed to purchase a pipe splitting tool for the Shelbyville office | 2926.56 | 2406.65 | 519.91 | 21.6% | 0.01351% | 2926.56 | 2406.65 | 519.91 | 2010-10-01 | 2011-09-30 | 2011-03-14 | 03 | 2011-09-30 | 09
| 050.25675 | 050..2734.Cave.Mill.Sta.Ext. | 4 inch PE Ext. Cave Mill Sta. | 2776.99 | 9045.07 | -6268.08 | -69.3% | 0.01282% | 2776.99 | 9045.07 | -6268.08 | 2010-10-01 | 2011-09-30 | 2011-04-15 | 04 | 2011-09-28 | 09
| 050.25325 | 2739.LOCUST CRK 8a | INSTALL 2in PE FOR LOCUST CREEK SEC 8a | 4239.06 | 8915.6 | -4676.54 | -52.45% | 0.01957% | 4239.06 | 8915.6 | -4676.54 | 2010-10-01 | 2011-09-30 | 2011-03-01 | 03 | 2012-03-01 | 03
| 050.26406 | 050.2636.Cross Creek Phase 5 | Install 545 Ft 2 Inch PE | 1569.56 | 4034.51 | -2464.95 | -61.1% | 0.007247% | 1569.56 | 4034.51 | -2464.95 | 2010-10-01 | 2011-09-30 | 2011-06-25 | 06 | 2011-09-28 | 09
| 050.26716 | PRP.2737.STAN.MILL ST | INSTALL 400ft OF 2in PE TO REPLACE BARE STEEL SECTION - CITY REWORKING STREET - CONTRACTOR WITH AIC | 11255.12 | 8096.35 | 3158.77 | 39.01% | 0.05196% | 11255.12 | 8096.35 | 3158.77 | 2010-10-01 | 2011-09-30 | 2011-07-18 | 07 | 2012-07-18 | 07
| 050.24800 | 050.2637.Paducah Bank Dr Ext | Install 450 feet of 2 inch poly for new Paducah Bank | 943.36 | 3462.97 | -2519.61 | -72.76% | 0.004355% | 943.36 | 3462.97 | -2519.61 | 2010-10-01 | 2011-09-30 | 2010-12-02 | 12 | 2010-12-28 | 12
| 050.25359 | 050.2636.Reg. & Relief upgrades | Make Relief and reg upgrades at Old State Rd, Calhoun purchase, Hartford and Town Border # 4. Also upgrade 4 charts with ERX recorders | 38465.43 | 51375.09 | -12909.66 | -25.13% | 0.1776% | 38465.43 | 51375.09 | -12909.66 | 2010-10-01 | 2011-09-30 | 2011-03-22 | 03 | 2011-09-30 | 09
| 050.26141 | 2738.SALOMA PURCH REBUILD | REPLACE PURCHASE STATION REGULATORS AT SALOMA FOR CAMPBELLSVILLE | 10933.02 | 20435.52 | -9502.5 | -46.5% | 0.05048% | 10933.02 | 20435.52 | -9502.5 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.23333 | 050.2637.Benton Rd Replacemen | Replace 2" steel damaged by third party | 85.57 | 4442.05 | -9257.77 | -208.4% | -0.02223% | -4815.72 | 4442.05 | -9257.77 | 2010-10-01 | 2011-09-30 | 2010-05-13 | 05 | 2010-06-29 | 06
| 050.20926 | 050.2609.Bon Harbor Well #2 | Workover Bon Harbor Well #2 | -6400.04 | 150302.01 | -9703.32 | -6.456% | 0.6491% | 140598.69 | 150302.01 | -9703.32 | 2010-10-01 | 2011-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.24790 | 050.2637.10372 | Mec Forfeiture | -469 | 0 |  |  | -0.002165% | -469 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.24793 | 050.2637.10147 | Mec Forfeiture | -573 | 0 |  |  | -0.002646% | -573 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.22360 | 050.KY.OboroGrowthFunct2010 | 050.KY.OboroGrowthFunct2010 | -8294.46 | 0 |  |  | 2.023% | 438257.79 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22436 | 050.KY.PrincetonLeakFunct2010 | 050.KY.PrincetonLeakFunct2010 | -1064.2 | 0 |  |  | 0.6206% | 134417.18 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 53956.38 | 0 |  |  | 0.2491% | 53956.38 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 37828.81 | 0 |  |  | 0.1747% | 37828.81 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 92296.73 | 0 |  |  | 0.4261% | 92296.73 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 15849.74 | 0 |  |  | 0.07318% | 15849.74 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 8004.85 | 0 |  |  | 0.03696% | 8004.85 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24069 | HopkinsLeakCP/LeakClamps | Hopkinsville KY Leak Functional - CP/Leak Clamps | 16116.07 | 0 |  |  | 0.07441% | 16116.07 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 24370.84 | 0 |  |  | 0.1125% | 24370.84 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 56362.03 | 0 |  |  | 0.261% | 56533.19 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24121 | 050.2637.E.F Equip II | Electro fuse equipment for use in the Paducah area. | 1546.4 | 9166.96 | 1760.97 | 19.21% | 0.05045% | 10927.93 | 9166.96 | 1760.97 | 2010-10-01 | 2011-09-30 | 2010-09-21 | 09 | 2010-09-30 | 09
| 050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 104987.69 | 0 |  |  | 0.5047% | 109305.7 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 43732.9 | 0 |  |  | 0.202% | 43761.32 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.20922 | 050.2609.Bon Harbor Well #1 | Workover Well # 1 Bon Harbor | -9491.44 | 316705.87 | -16528.6 | -5.219% | 1.386% | 300177.27 | 316705.87 | -16528.6 | 2010-10-01 | 2011-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.24132 | 050.2634.Evergreen Circle | Install 214 ft. 2 Inch PE | 1769.42 | 3327.35 | -1557.93 | -46.82% | 0.008169% | 1769.42 | 3327.35 | -1557.93 | 2010-10-01 | 2011-09-30 | 2010-09-22 | 09 | 2010-09-28 | 09
| 050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 81293.22 | 0 |  |  | 0.3815% | 82633.65 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 77225.82 | 0 |  |  | 0.3565% | 77225.82 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24729 | 050.2636.New Hospital | Install 100 feet 2 Inch Steel &2077 feet 6 Inch PE | 53621.21 | 45581.69 | 8039.52 | 17.64% | 0.2476% | 53621.21 | 45581.69 | 8039.52 | 2010-10-01 | 2011-09-30 | 2010-11-01 | 11 | 2010-12-31 | 12
| 050.24738 | 050.2634.Gas Tracker | Purchase Gas Tracker Pipe locator to locate unwired plastic. | 30313.74 | 27657.15 | 2656.59 | 9.605% | 0.14% | 30313.74 | 27657.15 | 2656.59 | 2010-10-01 | 2011-09-30 | 2010-11-04 | 11 | 2011-09-28 | 09
| 050.24767 | 050.2734.TDWMachine | 050.2734.TWDMachine | 10375.79 | 10805.93 | -430.14 | -3.981% | 0.0479% | 10375.79 | 10805.93 | -430.14 | 2010-10-01 | 2011-09-30 | 2010-11-17 | 11 | 2011-09-28 | 09
| 050.24857 | 050.2734.Ashley 4 inch tie in | 1150 ft. of 4 inch PE - Ashley St. tie in | 29790.15 | 58359.12 | -28568.97 | -48.95% | 0.1375% | 29790.15 | 58359.12 | -28568.97 | 2010-10-01 | 2011-09-30 | 2011-01-07 | 01 | 2011-09-28 | 09
| 050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 74946.17 | 0 |  |  | 0.346% | 74946.17 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23561 | 050.2636.Short Sta. Rd. Relo. | Relocate 655ft 2 Inch PE for roadway work | -629.49 | 7061.43 | -4815.82 | -68.2% | 0.01037% | 2245.61 | 7061.43 | -4815.82 | 2010-10-01 | 2011-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.24912 | 050.2634.918096-01 | Mec Forfeiture | -336 | 0 |  |  | -0.001551% | -336 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24808 | 050.2734.14th Replc. | Relocated 450 ft.of 4" PE | 835.3 | 4.66 | 830.64 | 17825% | 0.003857% | 835.3 | 4.66 | 830.64 | 2010-10-01 | 2011-09-30 | 2010-12-06 | 12 | 2011-09-28 | 09
| 050.24204 | 050.2637.Linden Street Ext | Install 195 feet of 2 inch plastic main for one existing residential customer | 3582.11 | 1813.09 | 1769.02 | 97.57% | 0.01654% | 3582.11 | 1813.09 | 1769.02 | 2010-10-01 | 2011-09-30 | 2010-10-06 | 10 | 2010-12-28 | 12
| 050.24852 | 2739.LAW.MAIN-WALKER LN | INSTALL 800ft OF 2in PE TO REPLACE 8 FARM TAPS ON MAIN STREET AT WALKER LANE | 23440.19 | 14207.72 | 9232.47 | 64.98% | 0.1082% | 23440.19 | 14207.72 | 9232.47 | 2010-10-01 | 2011-09-30 | 2011-01-06 | 01 | 2011-10-01 | 10
| 050.24854 | 050.2634.Electro Fuse Machine | Purchase Eletro Fuse machine | 2450.81 | 3873.39 | -1422.58 | -36.73% | 0.01132% | 2450.81 | 3873.39 | -1422.58 | 2010-10-01 | 2011-09-30 | 2011-01-06 | 01 | 2011-09-28 | 09
| 050.24950 | 050.2636.10159-01 | Mec Forfeiture | -381 | 0 |  |  | -0.001759% | -381 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-02-14 | 02 | 2011-02-14 | 02
| 050.23136 | 050.2634.Countryview Boiler | Install Boiler at Countryview | 10146.68 | 38196.56 | 3438.37 | 9.002% | 0.1922% | 41634.93 | 38196.56 | 3438.37 | 2010-10-01 | 2011-09-30 | 2010-01-26 | 01 | 2010-09-28 | 09
| 050.23842 | MayfieldIntegRegs | Mayfield Non Growth Regs Functional | 12999.33 | 0 |  |  | 0.06002% | 12999.33 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 151332.41 | 0 |  |  | 0.6987% | 151332.41 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.24918 | 050.2636.10559-01 | Mec Forfeiture | -392 | 0 |  |  | -0.00181% | -392 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-31 | 01 | 2011-01-31 | 01
| 050.22429 | 050.KY.BowlGrnLeakFunct2010 | 050.KY.BowlGrnLeakFunct2010 | -3437.07 | 0 |  |  | 4.855% | 1051472.05 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 103769.24 | 0 |  |  | 0.4791% | 103769.24 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23836 | KY.ShelbyvilleIntegRegs | Shelbyville KY Non Growth Regs Functional | 61516.79 | 0 |  |  | 0.284% | 61516.79 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24788 | 050.2638.10613 | MEc Forfeiture | -457 | 0 |  |  | -0.00211% | -457 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.24907 | 050.2634.917983-01 | Mec Forfeiture | -400 | 0 |  |  | -0.001847% | -400 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.22199 | 050.2634.Franklin St Reg | Relocate Franklin St. Reg. Sta. | -175.64 | 37.45 | -10554.7 | -28183% | -0.04856% | -10517.25 | 37.45 | -10554.7 | 2010-10-01 | 2011-09-30 | 2009-08-03 | 08 | 2009-09-28 | 09
| 050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 121145.46 | 0 |  |  | 0.5593% | 121145.46 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.25523 | 050.2734.Lain Ave Replc. | 1100 ft. of 4 inch PE Replacement | 54110.96 | 78044.1 | -23933.14 | -30.67% | 0.2498% | 54110.96 | 78044.1 | -23933.14 | 2010-10-01 | 2011-09-30 | 2011-01-01 | 01 | 2011-09-28 | 09
| 050.26289 | pnuematic boring tool | This project is for the purchase of a pnuematic boring tool to be used in Paducah | 5298.82 | 5375 | -76.18 | -1.417% | 0.02446% | 5298.82 | 5375 | -76.18 | 2010-10-01 | 2011-09-30 | 2011-06-13 11:09 | 06 | 2011-09-28 | 09
| 050.25108 | 050.2609.Hickory Wells | Rework 5 wells at Hickory Storage. | 892390.45 | 884840.28 | 7550.17 | 0.8533% | 4.12% | 892390.45 | 884840.28 | 7550.17 | 2010-10-01 | 2011-09-30 | 2011-03-01 | 03 | 2011-09-28 | 09
| 050.26764 | 050.PRP.2636.Monroe St. | Replace 160 ft 1.25 Inch Bare Stl. with 172 ft 2 Inch PE | 7000.79 | 7311.82 | -311.03 | -4.254% | 0.03232% | 7000.79 | 7311.82 | -311.03 | 2010-10-01 | 2011-09-30 | 2011-07-05 | 07 | 2011-09-28 | 09
| 050.26320 | 050.2609.Security Cameras | Purchase security cameras to deter theft of company property. | 6396.88 | 7361.48 | -964.6 | -13.1% | 0.02953% | 6396.88 | 7361.48 | -964.6 | 2010-10-01 | 2011-09-30 | 2011-06-16 10:22 | 06 | 2011-09-28 | 09
| 050.25339 | Gas line tracer kit | Fiberglass rod with tracer wire and grounding with integrated stuffing box that locates live plastic lateral gas lines from meter to main. | 1031.08 | 1094.63 | -63.55 | -5.806% | 0.00476% | 1031.08 | 1094.63 | -63.55 | 2010-10-01 | 2011-09-30 | 2011-03-17 | 03 | 2011-09-30 | 09
| 050.25575 | 050.2626.Staylit System | Purchase Staylit System | 9184.78 | 7560.14 | 1624.64 | 21.49% | 0.04241% | 9184.78 | 7560.14 | 1624.64 | 2010-10-01 | 2011-09-30 | 2011-04-14 | 04 | 2011-09-30 | 09
| 050.26922 | 050.2636.River Front Crossing | Relocated 1 Inch and 2 Inch Stl. main replaced with 301 ft 2 Inch PE | 2773.95 | 5059.17 | -2285.22 | -45.17% | 0.01281% | 2773.95 | 5059.17 | -2285.22 | 2010-10-01 | 2011-09-30 | 2011-04-01 | 04 | 2011-09-28 | 09
| 050.26717 | 2737.HAR.KINGS WAY RELOCATE | RELOCATE 1-1/4in PE AND REPLACE WITH 2in PE | 869.49 | 1043.15 | -173.66 | -16.65% | 0.004014% | 869.49 | 1043.15 | -173.66 | 2010-10-01 | 2011-09-30 | 2011-07-21 | 07 | 2012-07-21 | 07
| 050.23446 | 050.2637.Bleich Rd Relocation | Lone Oak High School constructing a new access road | -2544.05 | 2968.69 | -1956.01 | -65.89% | 0.004676% | 1012.68 | 2968.69 | -1956.01 | 2010-10-01 | 2011-09-30 | 2010-07-12 | 07 | 2010-09-28 | 09
| 050.23480 | 050.2637.R.D Locator | Radiodetection model RD8000 universal precision cable and pipe locator for use in the Paducah area. Will be assigned to Richard (Bates) Anderson. | 590.02 | 7413.24 | 807.19 | 10.89% | 0.03795% | 8220.43 | 7413.24 | 807.19 | 2010-10-01 | 2011-09-30 | 2010-08-02 | 08 | 2010-09-28 | 09
| 050.26158 | 050.2636.Allen St. Rplmnt. | Replace 3120 Ft Bare 4 Inch Main with 4 Inch PE. | 125975.24 | 133927.1 | -7951.86 | -5.937% | 0.5816% | 125975.24 | 133927.1 | -7951.86 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.25955 | Segway for Columbia Office | Approval is needed to purchase a Segway for the Columbia Office | 10187.67 | 9982.05 | 205.62 | 2.06% | 0.04704% | 10187.67 | 9982.05 | 205.62 | 2010-10-01 | 2011-09-30 | 2011-05-13 | 05 | 2011-09-30 | 09
| 050.21065 | Bowling Green 09 Non Growth | Bowling Green 09 Non Growth | 9380.35 | 0 |  |  | 7.539% | 1632936.36 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23275 | 050.2637.Hwy 282 Replacement | Replace 500 feet of 4 inch steel with 500 feet of 4 inch plastic | -0.04 | 11610.64 | 3672.24 | 31.63% | 0.07056% | 15282.88 | 11610.64 | 3672.24 | 2010-10-01 | 2011-09-30 | 2010-04-09 | 04 | 2010-05-28 | 05
| 050.23489 | 050.2636.London Pike Spur | Install 100 Ft 2 Inch PE | 2100.93 | 3107.03 | -742.95 | -23.91% | 0.01091% | 2364.08 | 3107.03 | -742.95 | 2010-10-01 | 2011-09-30 | 2010-08-05 | 08 | 2010-09-28 | 09
| 050.23490 | 050.2636.Pro Park Dr. Reloc. | Relocate 2 Inch PE for new Street | -77.61 | 1547.41 | -1253.58 | -81.01% | 0.001357% | 293.83 | 1547.41 | -1253.58 | 2010-10-01 | 2011-09-30 | 2010-08-05 | 08 | 2010-09-28 | 09
| 050.19366 | 050.2636.Hill Bridge Rd. | Install 910' 2" PE | 2559 | 3412.37 | 3884.83 | 113.8% | 0.03369% | 7297.2 | 3412.37 | 3884.83 | 2010-10-01 | 2011-09-30 | 2007-07-24 | 07 | 2010-10-27 | 10
| 050.23358 | 050.2618.Misc.Equipment | Purchase misc. equipment Respirator, Respirator test kit, Shoring Box End Panels. | 31.16 | 31975.51 | -2445.24 | -7.647% | 0.1363% | 29530.27 | 31975.51 | -2445.24 | 2010-10-01 | 2011-09-30 | 2010-06-01 | 06 | 2010-09-28 | 09
| 050.23563 | 050.2637.Locator - Young | This project is for new model 840 Pipehorn pipe locator to be assigned to Mike Young for use in the Paducah area. | 131.12 | 1896.24 | -69.48 | -3.664% | 0.008434% | 1826.76 | 1896.24 | -69.48 | 2010-10-01 | 2011-09-30 | 2010-09-08 | 09 | 2010-09-28 | 09
| 050.22355 | 050.KY.DanvilleGrowthFunct2010 | 050.KY.DanvilleGrowthFunct2010 | -1238.97 | 0 |  |  | 0.8324% | 180287.97 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22358 | 050.KY.MadisonGrowthFunct2010 | 050.KY.MadisonGrowthFunct2010 | -1215.85 | 0 |  |  | 0.9867% | 213721.58 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23413 | 050.2734.Misc Equip | 050.2734.Misc Equip | 487.56 | 11198.25 | -2403.03 | -21.46% | 0.04061% | 8795.22 | 11198.25 | -2403.03 | 2010-10-01 | 2011-09-30 | 2010-06-24 | 06 | 2010-09-28 | 09
| 050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 53817 | 0 |  |  | 0.2485% | 53817 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 13852.92 | 0 |  |  | 0.06396% | 13852.92 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 106434.96 | 0 |  |  | 0.4914% | 106434.96 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 8769.58 | 0 |  |  | 0.04049% | 8769.58 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 72154.5 | 0 |  |  | 0.3331% | 72154.5 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24034 | MadisonvilleLeakRegs | Madisonville Leak Regs Functional | 7427.06 | 0 |  |  | 0.03429% | 7427.06 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 109645.64 | 0 |  |  | 0.5062% | 109645.64 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 254720.7 | 0 |  |  | 1.176% | 254720.7 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 26956.08 | 0 |  |  | 0.1245% | 26956.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23833 | HopkinsvilleIntegRegs | Hopkinsville Non Growth Regs Functional | 43156.87 | 0 |  |  | 0.1993% | 43156.87 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 14331.25 | 0 |  |  | 0.06686% | 14480.54 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23045 | 050.2734.Beltline 8 | Bowling Green 8 inch System Improvement | 26106.31 | 5596208.03 | -2922817.04 | -52.23% | 12.34% | 2673390.99 | 5596208.03 | -2922817.04 | 2010-10-01 | 2011-09-30 | 2009-11-30 | 11 | 2010-09-28 | 09
| 050.23485 | 050.2637.E.F Equip | M.T Deason electro-fuse processor with data printermodel EF-T for use in the Paducah area. | 392.83 | 5449.81 | 23.15 | 0.4248% | 0.02527% | 5472.96 | 5449.81 | 23.15 | 2010-10-01 | 2011-09-30 | 2010-08-03 | 08 | 2010-09-28 | 09
| 050.24135 | 050.2734.ELECTROFUSE UNITS | 050.2734.ELECTROFUSE UNITS | 12347.78 | 46168.28 | 12962.68 | 28.08% | 0.273% | 59130.96 | 46168.28 | 12962.68 | 2010-10-01 | 2011-09-30 | 2010-09-22 | 09 | 2011-09-28 | 09
| 050.22434 | 050.KY.ShelbyvLeakFunct2010 | 050.KY.ShelbyvLeakFunct2010 | -1331.26 | 0 |  |  | 0.4176% | 90451.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23562 | 050.2635.East Dale Ave. | Install 100 ft 2 Inch PE to serve 1 residential customer and extra 134 ft to provide two way feed. | -467.29 | 3266.95 | -953.3 | -29.18% | 0.01068% | 2313.65 | 3266.95 | -953.3 | 2010-10-01 | 2011-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 8967.17 | 0 |  |  | 0.0414% | 8967.17 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 75286.78 | 0 |  |  | 0.3505% | 75908.71 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 30667.08 | 0 |  |  | 0.1424% | 30836.7 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 49986.82 | 0 |  |  | 0.2313% | 50093.75 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24217 | 050.2637.Sir Charles Ct Ext | Install 170 feet of 2 inch poly main | 6025.91 | -7395.07 | 13420.98 | -181.5% | 0.02782% | 6025.91 | -7395.07 | 13420.98 | 2010-10-01 | 2011-09-30 | 2010-10-14 | 10 | 2010-12-28 | 12
| 050.24214 | 050.2636.Paradise Landing | Install 430 Ft 2 Inch PE to serve Commercial Developement | 5307.84 | 5211.74 | 96.1 | 1.844% | 0.02451% | 5307.84 | 5211.74 | 96.1 | 2010-10-01 | 2011-09-30 | 2010-10-12 | 10 | 2010-09-28 | 09
| 050.24766 | 050.2734.ERX.BowlingGreen | 050.2734.ERX.BowlingGreen | 14371.57 | 13864.42 | 507.15 | 3.658% | 0.06635% | 14371.57 | 13864.42 | 507.15 | 2010-10-01 | 2011-09-30 | 2010-11-17 | 11 | 2011-09-28 | 09
| 050.24783 | 050.2636.0918631-01 | Mec Forfeiture | -2216 | 0 |  |  | -0.01023% | -2216 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.23276 | 050.2636.Replace Heaters,Regs. | Replace Bruest Heaters Big Rivers, Replace regulators Southwire & 5th St Station | -57.36 | 23750.77 | -2163.43 | -9.109% | 0.09967% | 21587.34 | 23750.77 | -2163.43 | 2010-10-01 | 2011-09-30 | 2010-04-12 | 04 | 2010-09-28 | 09
| 050.24861 | 050.2736.Rycom Locator | Purchase pipeline locator | 1458.81 | 1719.95 | -261.14 | -15.18% | 0.006735% | 1458.81 | 1719.95 | -261.14 | 2010-10-01 | 2011-09-30 | 2011-01-10 | 01 | 2011-09-28 | 09
| 050.24908 | 050.2634.917153-01 | Mec Forfeiture | -3500 | 0 |  |  | -0.01616% | -3500 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24910 | 050.2634.918017-01 | Mec Forfeiture | -1966 | 0 |  |  | -0.009077% | -1966 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24900 | 050.2634.918378-01 | Mec Forfeiture | -1206 | 0 |  |  | -0.005568% | -1206 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24898 | 050.2634.10672-01 | Mec Forfeiture | -5789 | 0 |  |  | -0.02673% | -5789 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24882 | 050.2734.915235-01 | Mec Forfeiture | -582 | 0 |  |  | -0.002687% | -582 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-19 | 01 | 2011-01-19 | 01
| 050.24724 | 050.2734.CumberlandTrc.Relo | Cumberland Trace - State Hwy. Relocation | 209465.28 | 250091.43 | -40626.15 | -16.24% | 0.9671% | 209465.28 | 250091.43 | -40626.15 | 2010-10-01 | 2011-09-30 | 2010-10-29 | 10 | 2011-09-28 | 09
| 050.24799 | 050.2637.Commerce Dr Ext | Install 1,350 feet of 4 inch PE pipe | 16561.92 | 13086.28 | 3475.64 | 26.56% | 0.07647% | 16561.92 | 13086.28 | 3475.64 | 2010-10-01 | 2011-09-30 | 2010-12-02 | 12 | 2011-01-21 | 01
| 050.24216 | 050.2636.Fields Rd. | Install 100 Ft 2 Inch PE | 1694.52 | 2313.15 | -618.63 | -26.74% | 0.007824% | 1694.52 | 2313.15 | -618.63 | 2010-10-01 | 2011-09-30 | 2010-10-13 | 10 | 2011-09-28 | 09
| 050.24830 | 050.2638.Leah Way Ext | Install 55 feet of 2 inch pe for one new residential customer | 561.99 | 1118.88 | -556.89 | -49.77% | 0.002595% | 561.99 | 1118.88 | -556.89 | 2010-10-01 | 2011-09-30 | 2010-12-16 | 12 | 2011-01-28 | 01
| 050.24081 | DanvillePRPMains | Danville Sub-Region KY Pipe Replacement Program Functional - Mains | 7307.72 | 0 |  |  | 0.03374% | 7307.72 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.24029 | GlasgowLeakRegs | Glasgow Leak Regs Functional | 16206.78 | 0 |  |  | 0.07483% | 16206.78 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24183 | 050.2734.Overholt Commercial | 900 ft. of 2" PE Ext. - Overholt Commercial | 2265.41 | 4728.45 | -2463.04 | -52.09% | 0.01046% | 2265.41 | 4728.45 | -2463.04 | 2010-10-01 | 2011-09-30 | 2010-09-30 | 09 | 2011-09-28 | 09
| 050.23348 | 050.2637.Monroe St II Replace | City widening road, if we do not relocate we will be under the ashphalt. Install 750 feet 4 inch pls, retire 750 feet 4 inch steel. 15 services affected. | -133.36 | 21121.59 | 8805.78 | 41.69% | 0.1382% | 29927.37 | 21121.59 | 8805.78 | 2010-10-01 | 2011-09-30 | 2010-05-24 | 05 | 2010-09-28 | 09
| 050.25171 | 050.2734.BarberWay Replc. | Replace 950 ft. of 2 inch bare with 2 inch PE - Barber Way | 66166.37 | 49025.88 | 17140.49 | 34.96% | 0.3055% | 66166.37 | 49025.88 | 17140.49 | 2010-10-01 | 2011-09-30 | 2011-03-01 | 03 | 2011-09-28 | 09
| 050.26049 | 050.2634.Hwy 62 Relo. | Relocate 4 Inch Stl for Road Widening | 181069.35 | 18325.17 | 162744.18 | 888.1% | 0.836% | 181069.35 | 18325.17 | 162744.18 | 2010-10-01 | 2011-09-30 | 2011-05-20 | 05 | 2011-09-28 | 09
| 050.26490 | 050.2636.Veterans Relo 2 | Relocate 6 Inch Stl. and 6 Inch PE for Riverfront Developement | 8380.02 | 31569.56 | -23189.54 | -73.46% | 0.03869% | 8380.02 | 31569.56 | -23189.54 | 2010-10-01 | 2011-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
| 050.27267 | 050.2634.Beulah Sta. replace | Replace Beulah Town Border | 1073.39 | 14350.08 | -13276.69 | -92.52% | 0.004956% | 1073.39 | 14350.08 | -13276.69 | 2010-10-01 | 2011-09-30 | 2011-09-07 | 09 | 2011-11-01 | 11
| 050.26465 | 050.2734.Park St. Bare Replc. | 4 inch Bare Replc. Parks St. | 44260.77 | 48992.29 | -4731.52 | -9.658% | 0.2044% | 44260.77 | 48992.29 | -4731.52 | 2010-10-01 | 2011-09-30 | 2011-06-27 | 06 | 2011-09-28 | 09
| 050.26766 | 050.2734.Magnolia Alley Replc | 4 inch Bare Steel Replc. - Install l 2 inch PE convert from LP to IP; | 84253.41 | 151333.57 | -67080.16 | -44.33% | 0.389% | 84253.41 | 151333.57 | -67080.16 | 2010-10-01 | 2011-09-30 | 2011-07-21 | 07 | 2011-09-28 | 09
| 050.25627 | 050.2636.Daniels Ln. Reloc. | Reloc. main due to road widening | 7781.23 | 12784.99 | -5003.76 | -39.14% | 0.03593% | 7781.23 | 12784.99 | -5003.76 | 2010-10-01 | 2011-09-30 | 2010-09-01 | 09 | 2010-09-28 | 09
| 050.25119 | 050.2634.Grapevine | Install 2,000 Ft 2" PE | 28143.14 | 25880.83 | 2262.31 | 8.741% | 0.1299% | 28143.14 | 25880.83 | 2262.31 | 2010-10-01 | 2011-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
| 050.23434 | Hopkinsville 10-inch Replacem | Replace 4 Mi of 10 L-90-159 w/ 12" from MP 1.25 to MP 5 | 1718043.71 | 3009467.72 | 807728.93 | 26.84% | 17.62% | 3817196.65 | 3009467.72 | 807728.93 | 2010-10-01 | 2011-09-30 | 2010-07-01 | 07 | 2010-12-31 | 12
| 050.25322 | 050.2602.Laptops_&_Desktops | Purchase new laptop & Desktop computers. | 32078.7 | 62145.63 | -30066.93 | -48.38% | 0.1481% | 32078.7 | 62145.63 | -30066.93 | 2010-10-01 | 2011-09-30 | 2011-03-18 | 03 | 2011-09-30 | 09
| 050.23370 | 2738.CALVARY PURCHASE REBUILD | REBUILD THE CALVARY PURCHASE STATION | 8334.07 | 57532.62 | -18484.11 | -32.13% | 0.1803% | 39048.51 | 57532.62 | -18484.11 | 2010-10-01 | 2011-09-30 | 2010-06-02 | 06 | 2011-05-12 | 05
| 050.24212 | 050.2636.Lucas Ln. | Install 240 Ft 2 Inch PE | 3178.53 | 2791.99 | 386.54 | 13.84% | 0.01468% | 3178.53 | 2791.99 | 386.54 | 2010-10-01 | 2011-09-30 | 2010-10-11 | 10 | 2010-10-24 | 10
| 050.23235 | 050.2637.Calvert T.B 2 | Introduce a second feed into Calvert city distribution system from the south, exising feed is from north side of city. | 223.32 | 18727.55 | 6636.28 | 35.44% | 0.1171% | 25363.83 | 18727.55 | 6636.28 | 2010-10-01 | 2011-09-30 | 2010-03-12 | 03 | 2010-07-16 | 07
| 050.23400 | 050.2636. Summer Walk 2 | Install 1062 ft 2 Inch PE | -87.86 | 6645.08 | -1451.77 | -21.85% | 0.02398% | 5193.31 | 6645.08 | -1451.77 | 2010-10-01 | 2011-09-30 | 2010-06-21 | 06 | 2010-09-28 | 09
| 050.24794 | 050.2638.10359 | Mec Forfeiture | -162 | 0 |  |  | -0.0007479% | -162 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.23686 | 2738.SPRNG.LEBANON HILL RD | INSTALL 200ft OF 2in PE FOR CUSTOMER | 1113.3 | 986.03 | 321.24 | 32.58% | 0.006036% | 1307.27 | 986.03 | 321.24 | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2011-02-01 | 02
| 050.22356 | 050.KY.CampbellGrowthFunct2010 | 050.KY.CampbellGrowthFunct2010 | -1961.88 | 0 |  |  | 0.5026% | 108850.58 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22392 | 050.KY.GlasgowIntegFunct2010 | 050.KY.GlasgowIntegFunct2010 | -3491.81 | 0 |  |  | 1.488% | 322225.9 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22396 | 050.KY.ShelbyviIntegFunct.2010 | 050.KY.ShelbyviIntegFunct.2010 | -3100.55 | 0 |  |  | 0.9321% | 201876.17 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22400 | 050.KY.PaducahIntegFunct2010 | 050.KY.PaducahIntegFunct2010 | -23688.11 | 0 |  |  | 3.956% | 856813.05 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22431 | 050.KY.HopkinsLeakFunct2010 | 050.KY.HopkinsLeakFunct2010 | -1908.05 | 0 |  |  | 0.3253% | 70458.22 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.24743 | 2738.EQUIPMENT FOR 2011 | SENSIT SMART CAL STATION, SENSIT RAK-ITIII AND MINIMC EQUIPMENT | 9302.44 | 9438 | -135.56 | -1.436% | 0.04295% | 9302.44 | 9438 | -135.56 | 2010-10-01 | 2011-09-30 | 2010-11-05 | 11 | 2011-10-03 | 10
| 050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 96377.93 | 0 |  |  | 0.445% | 96377.93 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23513 | 2739.MEADOW GLEN SEC III | INSTALL IN JOINT TRENCH 2in PE | 10151.1 | 8013.63 | 2219.34 | 27.69% | 0.04725% | 10232.97 | 8013.63 | 2219.34 | 2010-10-01 | 2011-09-30 | 2010-08-16 | 08 | 2010-12-01 | 12
| 050.24073 | MadisonLeakCP/LeakClamps | Madisonville Leak Functional - CP/Leak Clamps | 48778.6 | 0 |  |  | 0.2276% | 49288.53 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24074 | PrincetonLeakCP/LeakClamps | Princeton Leak Functional - CP/Leak Clamps | 19069.62 | 0 |  |  | 0.08933% | 19348.46 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24075 | OboroLeakCP/LeakClamps | Owensboro Leak Functional - CP/Leak Clamps | 79897.88 | 0 |  |  | 0.3813% | 82578.76 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 17315.33 | 0 |  |  | 0.07994% | 17315.33 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 183930.83 | 0 |  |  | 0.8492% | 183930.83 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 634363.49 | 0 |  |  | 2.93% | 634551.13 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 154518.54 | 0 |  |  | 0.7134% | 154518.54 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 52569.2 | 0 |  |  | 0.2427% | 52569.2 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23832 | GlasgowIntegRegs | Glasgow Non Growth Regs Functional | 15740.85 | 0 |  |  | 0.07267% | 15740.85 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23839 | PrincetonIntegRegs | Princeton Non Growth Regs Functional | 41880.46 | 0 |  |  | 0.1934% | 41880.46 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23285 | 050.2734.Old Morgantown Replc | 3" Bare Steel Replacement - Old Morgantown Rd.- B.G. | 1076.95 | 87761.8 | 34383.28 | 39.18% | 0.5639% | 122145.08 | 87761.8 | 34383.28 | 2010-10-01 | 2011-09-30 | 2010-04-15 | 04 | 2010-09-28 | 09
| 050.22274 | 050.2338.May Reinforcement | Install 12,000 feet 4" HD PE pipe from KT Clay (190 maop) to Dairyman Inc (36 maop) | 53420.39 | 67799.57 | 88943.81 | 131.2% | 0.7237% | 156743.38 | 67799.57 | 88943.81 | 2010-10-01 | 2011-09-30 | 2009-08-24 | 08 | 2009-09-28 | 09
| 050.23185 | 050.3634.Sensit Gold Purchase | Purchase 4 new Sensit Golds, 4 old ones to be traded in. | 452.65 | 18408.92 | -11910.89 | -64.7% | 0.03% | 6498.03 | 18408.92 | -11910.89 | 2010-10-01 | 2011-09-30 | 2010-02-16 | 02 | 2010-09-28 | 09
| 050.22502 | 050.2612.REFURB METERS FY10 | CC2612 FY10 Outsourced Meter Retirements & New Meter Purchases | -328.21 | 226684 | 9668.13 | 4.265% | 1.091% | 236352.13 | 226684 | 9668.13 | 2010-10-01 | 2011-09-30 | 2009-10-07 | 10 | 2010-09-30 | 09
| 050.19588 | Bowling Green 08 Growth | Bowling Green 08 Growth | 2047.03 | 0 |  |  | 5.144% | 1114252.01 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23064 | 050.2637.Mississippi St Ext | Install 255 ft of 2 in poly for one new customer Grand Rivers Fire Dept | -15.26 | 1095.34 | -152336.43 | -13908% | -0.6983% | -151241.09 | 1095.34 | -152336.43 | 2010-10-01 | 2011-09-30 | 2009-12-10 | 12 | 2009-12-21 | 12
| 050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 73853.97 | 0 |  |  | 0.341% | 73853.97 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.24917 | 050.2636.10453-01 | Mec Forfeiture | -2180 | 0 |  |  | -0.01006% | -2180 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-31 | 01 | 2011-01-31 | 01
| 050.24927 | 050.2637.Coleman Cr Ext | Install 92 feet of 2 inch pe for Fairfield Inn | 502.66 | 607.76 | -105.1 | -17.29% | 0.002321% | 502.66 | 607.76 | -105.1 | 2010-10-01 | 2011-09-30 | 2011-02-03 | 02 | 2011-03-21 | 03
| 050.24779 | 050.2636.0918001-01 | Mec Forfeiture | -1490 | 0 |  |  | -0.006879% | -1490 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24896 | 050.2735.Squeeze Off | 050.2735.Sqeeze Off | 10186.51 | 7393.1 | 2793.41 | 37.78% | 0.04703% | 10186.51 | 7393.1 | 2793.41 | 2010-10-01 | 2011-09-30 | 2011-01-26 | 01 | 2011-09-28 | 09
| 050.24870 | 050.2634.Lockers | Purchase lockers | 3739.29 | 4077.88 | -338.59 | -8.303% | 0.01726% | 3739.29 | 4077.88 | -338.59 | 2010-10-01 | 2011-09-30 | 2011-01-17 | 01 | 2011-09-28 | 09
| 050.24902 | 050.2634.10204-01 | Mec Forfeiture | -2031 | 0 |  |  | -0.009377% | -2031 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24911 | 050.2634.918093-01 | Mec Forfeiture | -1043 | 0 |  |  | -0.004815% | -1043 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24901 | 050.2634.918152-01 | Mec Forfeiture | -5707 | 0 |  |  | -0.02635% | -5707 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24928 | 2737.NORTH POINT REG STAT | REPLACE REGULATOR STATION DAMAGED BY MOTOR VEHICLE 1-29-2011 | 39510.73 | -15818.55 | 55329.28 | -349.8% | 0.1824% | 39510.73 | -15818.55 | 55329.28 | 2010-10-01 | 2011-09-30 | 2011-02-04 | 02 | 2012-01-29 | 01
| 050.24948 | 050.2636.Summer Valley Lane | Install 400 ft 2 Inch Pe to serve 3 residential lots | 3207.96 | 4938.91 | -1730.95 | -35.05% | 0.01481% | 3207.96 | 4938.91 | -1730.95 | 2010-10-01 | 2011-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
| 050.24107 | 2737.DANVILLE.ELECFUS 2010 | PURCHASE ELECTORFUSION EQUIPMENT FOR DANVILLE TO COMPLY WITH UOC DIRECTIVES | 639.82 | 6718.95 | 978.61 | 14.56% | 0.03554% | 7697.56 | 6718.95 | 978.61 | 2010-10-01 | 2011-09-30 | 2010-09-20 | 09 | 2010-10-29 | 10
| 050.24231 | 050.2739.2011 EQUIPMENT | MINI MAC EQUIPMENT FOR SHELBYVILLE, KY, ADDED ITEMS FROM BUDGET SENSIT GOLD AND TRACKIT III | 9611.04 | 8723.25 | 887.79 | 10.18% | 0.04437% | 9611.04 | 8723.25 | 887.79 | 2010-10-01 | 2011-09-30 | 2010-10-21 | 10 | 2011-03-15 | 03
| 050.24839 | 050.2637.Welder Freeman | Purchase new Miller Bobcat 250 EFI Welder for vehicle #9708 Ronnie Freeman Retire welder 6453 this unit is worn out | 7642.19 | 6200.53 | 1441.66 | 23.25% | 0.03528% | 7642.19 | 6200.53 | 1441.66 | 2010-10-01 | 2011-09-30 | 2010-12-30 | 12 | 2011-03-30 | 03
| 050.23537 | 050.2636.Sunrise Dr. Reloc | Relocate 430ft 2 Inch Stl.with 2 Inch PE | -771.7 | 4580.75 | -1705.7 | -37.24% | 0.01327% | 2875.05 | 4580.75 | -1705.7 | 2010-10-01 | 2011-09-30 | 2010-08-30 | 08 | 2010-09-28 | 09
| 050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 88283.47 | 0 |  |  | 0.4076% | 88283.47 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 196987.53 | 0 |  |  | 0.9095% | 196987.53 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 92605.43 | 0 |  |  | 0.4276% | 92605.43 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24881 | 050.2734.0914284-01 | Mec Forfeiture | -1600 | 0 |  |  | -0.007387% | -1600 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-19 | 01 | 2011-01-19 | 01
| 050.24711 | 050.2736.Squire Rd. | Install 786' 2" PE | 32199.31 | 32166.64 | 32.67 | 0.1016% | 0.1487% | 32199.31 | 32166.64 | 32.67 | 2010-10-01 | 2011-09-30 | 2010-10-25 | 10 | 2011-09-28 | 09
| 050.24947 | 050.2636.Hwy 54 Whitesville | Install 1000 feet 2 Inch PE | 3900.87 | 2127.02 | 1773.85 | 83.4% | 0.01801% | 3900.87 | 2127.02 | 1773.85 | 2010-10-01 | 2011-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
| 050.22433 | 050.KY.CampbellLeakFunct2010 | 050.KY.CampbellLeakFunct2010 | -1261.39 | 0 |  |  | 1.191% | 257872.38 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 11489.45 | 0 |  |  | 0.0661% | 14316.71 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 72554.1 | 0 |  |  | 0.335% | 72554.1 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24822 | 050.2737.918506-01 | Mec Forfeiture | -3900 | 0 |  |  | -0.01801% | -3900 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.24832 | 050.2735.0916411-01 | Mec Forfeiture | -2338 | 0 |  |  | -0.01079% | -2338 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-17 | 12 | 2010-12-17 | 12
| 050.26302 | GlasgowPRPMains | Glasgow KY Pipe Replacement Program Functional - Mains | 2271.18 | 0 |  |  | 0.01049% | 2271.18 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
| 050.25518 | 050.2734.S.MainBareReplc.FRK | South Main Bare TSeel Replacement - Franklin | 119792.62 | 138643.36 | -18850.74 | -13.6% | 0.5531% | 119792.62 | 138643.36 | -18850.74 | 2010-10-01 | 2011-09-30 | 2011-04-01 | 04 | 2011-09-28 | 09
| 050.26050 | 050.2636.Frederica St. Rplmnt | Replace 1750 Ft. Bare Stl. Pipe | 153124.36 | 164009.73 | -10885.37 | -6.637% | 0.707% | 153124.36 | 164009.73 | -10885.37 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.26053 | 2737.LAN.TBS REG REPLACE | REPLACE REGULATORS AT THE TOWN BORDER STATION IN LANCASTER | 6450.31 | 2.6 | 6447.71 | 247989% | 0.02978% | 6450.31 | 2.6 | 6447.71 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.27218 | Easements | Phase 2 of I-69 was originally scheduled for FY 2011, it has been moved to FY 2012, however, we would like to proceed with securing easements for the project. We anticipate easements to cost Atmos $49,630. This is using $7 per ft. In 2010 we paid $85,000 | 220.2 | 49974.88 | -49754.68 | -99.56% | 0.001017% | 220.2 | 49974.88 | -49754.68 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.26139 | 2737.WAREHOUSE PARKING IMPROVEMENTS | IMPROVEMENTS FOR PARKING AT THE MAIN OFFICE | 4974.45 | 5149.55 | -175.1 | -3.4% | 0.02297% | 4974.45 | 5149.55 | -175.1 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27157 | Aldyl A Repair Kit | We would like to purchase a model GFCP #10007584 Aldyl A refurbish tool. this allows us to repair leaking aldyl a service tees. | 684.15 | 819.3 | -135.15 | -16.5% | 0.003159% | 684.15 | 819.3 | -135.15 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.25698 | 2737.HARRODSBURG WTP RELOCATE | RELOCATE 4in STEEL FOR HARRODSBURG WATER TREATMENT PLANT EXPANSION | 18635.24 | 5118.1 | 13517.14 | 264.1% | 0.08604% | 18635.24 | 5118.1 | 13517.14 | 2010-10-01 | 2011-09-30 | 2011-05-01 | 05 | 2012-05-01 | 05
| 050.27003 | 050.2636.Southtown Relo. | Relocate 2 Inch PE for Southtown Widening | 6260.03 | 94530.6 | -88270.57 | -93.38% | 0.0289% | 6260.03 | 94530.6 | -88270.57 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.26046 | 050.2637.Hwy 996 Rev Ext | Install 635 feet of 2 inch poly for one new residential customer plus two vacant lots that will build in the near future. | -1976.09 | 2783.6 | -4759.69 | -171% | -0.009124% | -1976.09 | 2783.6 | -4759.69 | 2010-10-01 | 2011-09-30 | 2011-06-06 | 06 | 2011-07-06 | 07
| 050.25348 | 050.2638.Water Valley Replace | Replace 2" steel pipe that is exposed in creek. Will move chart box to puchase station. will retire above ground valve, not critical | 1297.11 | 9505.9 | -8208.79 | -86.35% | 0.005989% | 1297.11 | 9505.9 | -8208.79 | 2010-10-01 | 2011-09-30 | 2011-04-01 | 04 | 2011-08-30 | 08
| 050.25115 | 050.2634.High School Relo. | Relocate 1300ft 4 Inch Stl for Muhlenberg Co High School | 8382.5 | 2100.93 | 6281.57 | 299% | 0.0387% | 8382.5 | 2100.93 | 6281.57 | 2010-10-01 | 2011-09-30 | 2011-03-01 | 03 | 2011-09-28 | 09
| 050.26599 | 050.2637.Valerie Ln Ext | Install 435 feet of 2 inch PE | 2867.99 | 2052.5 | 815.49 | 39.73% | 0.01324% | 2867.99 | 2052.5 | 815.49 | 2010-10-01 | 2011-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.26477 | 050.2637.Tina Dr Main Ext | Install 75 feet of 2 inch poly for one conversion customer | 1255.65 | 855.39 | 400.26 | 46.79% | 0.005797% | 1255.65 | 855.39 | 400.26 | 2010-10-01 | 2011-09-30 | 2011-07-05 | 07 | 2011-09-28 | 09
| 050.26495 | 050.2609.Heartland xing Relo. | Relocate 2100 ft 8 Inch HPD for new shopping center | -11192.63 | -25037.17 | 13844.54 | -55.3% | -0.05168% | -11192.63 | -25037.17 | 13844.54 | 2010-10-01 | 2011-09-30 | 2011-06-10 | 06 | 2011-09-28 | 09
| 050.26442 | PRP.2738.LEB.PROCTOR KNOTT | REPLACE 4in STEEL ON S PROCTOR KNOTT AVE WITH 4in PE | 129788.2 | 248257.09 | -118468.89 | -47.72% | 0.5992% | 129788.2 | 248257.09 | -118468.89 | 2010-10-01 | 2011-09-30 | 2010-05-01 | 05 | 2012-05-01 | 05
| 050.26261 | Pipehorn locator | This project is for the purchase of a Pipehorn model MD840 pipe locator to be assigned to Steve Griffin and used in the Harrisburg, IL area. | 2050.36 | 1950.32 | 100.04 | 5.129% | 0.009466% | 2050.36 | 1950.32 | 100.04 | 2010-10-01 | 2011-09-30 | 2011-06-09 13:26 | 06 | 2011-09-28 | 09
| 050.25622 | 107 Flow Boss | 107 Flow Boss to replace 364 ROC | 10828.7 | 12092.93 | -1264.23 | -10.45% | 0.05% | 10828.7 | 12092.93 | -1264.23 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.25676 | Test Equipment | Miscelaneous Test equipment and fittings | 6748.41 | 9054.19 | -2305.78 | -25.47% | 0.03116% | 6748.41 | 9054.19 | -2305.78 | 2010-10-01 | 2011-09-30 | 2011-04-19 | 04 | 2011-09-30 | 09
| 050.26121 | PRP.050.2734.Pritchardsville | 2210 ft. of 2 inch PE - Bare Replc. - Protchardsville Rd | 156287.54 | 140915.71 | 15371.83 | 10.91% | 0.7216% | 156287.54 | 140915.71 | 15371.83 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.23520 | 050.2638.Randview Subd | Install 2,600 feet of 2" PE for 14 residential customers requesting natural gas service. | 12725.08 | 16453.98 | -1714.74 | -10.42% | 0.06805% | 14739.24 | 16453.98 | -1714.74 | 2010-10-01 | 2011-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
| 050.21802 | TchSvr.Mea.Westlake Methane | Rebuild Westlake Methane Meter Station in Calvert City | 261.86 | 114000 | -106216.17 | -93.17% | 0.03594% | 7783.83 | 114000 | -106216.17 | 2010-10-01 | 2011-09-30 | 2009-01-09 | 01 | 2009-09-30 | 09
| 050.24958 | 050.2637.16 duplexes | install 910 feet of 2 inch pe pipe for 16 duplexes | 440.83 | 5589.59 | -5148.76 | -92.11% | 0.002035% | 440.83 | 5589.59 | -5148.76 | 2010-10-01 | 2011-09-30 | 2011-02-18 | 02 | 2011-05-17 | 05
| 050.22438 | 050.KY.PaducahLeakFunct2010 | 050.KY.PaducahLeakFunct2010 | -11778.02 | 0 |  |  | 2.11% | 456945.73 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22439 | 050.KY.MayfieldLeakFunct2010 | 050.KY.MayfieldLeakFunct2010 | -622.38 | 0 |  |  | 0.399% | 86419.86 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23238 | 050.2638.Houseman St Reg Repl | We propose to replace the regulators at our Houseman Street regulator station. The existing regulators are Grove, they are outdated, we have trouble finding repair parts. We plan to install Mooney 300 series. | 3138.81 | 10479.94 | 1861.45 | 17.76% | 0.05698% | 12341.39 | 10479.94 | 1861.45 | 2010-10-01 | 2011-09-30 | 2010-03-17 | 03 | 2010-05-28 | 05
| 050.19591 | Glasgow 08 Non Growth | Glasgow 08 Non Growth | 221.88 | 0 |  |  | 2.265% | 490576.86 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2007-09-18 | 09 | 2009-05-13 | 05
| 050.23533 | 050.2636.RMLD | Purchase Remote Methane Leak Detector | -51.75 | 24769.54 | 1065.83 | 4.303% | 0.1193% | 25835.37 | 24769.54 | 1065.83 | 2010-10-01 | 2011-09-30 | 2010-08-24 | 08 | 2010-09-28 | 09
| 050.24789 | 050.2737.10168 | Mec Forfeiture | -1006 | 0 |  |  | -0.004645% | -1006 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.23409 | 050.2636.Village Run 3 | Install 680 ft 2 Inch PE | -38.6 | 4590.65 | -2234.52 | -48.68% | 0.01088% | 2356.13 | 4590.65 | -2234.52 | 2010-10-01 | 2011-09-30 | 2010-06-22 | 06 | 2010-09-28 | 09
| 050.22395 | 050.KY.CampbellIntegFunct2010 | 050.KY.CampbellIntegFunct2010 | -3281.95 | 0 |  |  | 1.209% | 261883.17 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22398 | 050.KY.PrincetonIntegFunct2010 | 050.KY.PrincetonIntegFunct2010 | -5040.61 | 0 |  |  | 1.045% | 226397.54 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22399 | 050.KY.OboroIntegFunct2010 | 050.KY.OboroIntegFunct2010 | -23325.21 | 0 |  |  | 6.894% | 1493085.18 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23462 | 2738.OLD PITMAN RD.MARK GRAY | INSTALL MAIN FOR DUPLEXES OFF OLD PITMAN RD FOR MARK GRAY | -33.57 | 3047.23 | -1773.52 | -58.2% | 0.005881% | 1273.71 | 3047.23 | -1773.52 | 2010-10-01 | 2011-09-30 | 2010-07-21 | 07 | 2010-10-01 | 10
| 050.23410 | Fairview Ave. Bare Steel Repl | Fairview Ave. Bare Steel Replacement | 119275.09 | 339934.28 | 4109.61 | 1.209% | 1.588% | 344043.89 | 339934.28 | 4109.61 | 2010-10-01 | 2011-09-30 | 2010-06-23 | 06 | 2010-09-28 | 09
| 050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 15577.69 | 0 |  |  | 0.07192% | 15577.69 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24742 | 050.2635.Carlisle St. Rplmnt. | Replace 430 Ft 2 Inch Stl. with 2 Inch PE | 17301.44 | 15249.03 | 2052.41 | 13.46% | 0.07988% | 17301.44 | 15249.03 | 2052.41 | 2010-10-01 | 2011-09-30 | 2010-11-05 | 11 | 2011-09-28 | 09
| 050.24745 | 050.2635.Lafayette St. | Install 525 Ft 2 Inch PE | 1255.44 | 5045.01 | -3789.57 | -75.12% | 0.005796% | 1255.44 | 5045.01 | -3789.57 | 2010-10-01 | 2011-09-30 | 2010-11-07 | 11 | 2011-09-28 | 09
| 050.24821 | 050.2737.918548-01 | Mec Forfeiture | -596 | 0 |  |  | -0.002752% | -596 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.24824 | 050.2737.918068-01 | Mec Forfeiture | -892 | 0 |  |  | -0.004118% | -892 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 56364.08 | 0 |  |  | 0.2602% | 56364.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 26262.68 | 0 |  |  | 0.1213% | 26262.68 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 61092.98 | 0 |  |  | 0.283% | 61285.53 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 28696.36 | 0 |  |  | 0.1337% | 28965.56 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 15340.46 | 0 |  |  | 0.07083% | 15340.46 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24035 | PrincetonLeakRegs | Princeton Leak Regs Functional | 6167.49 | 0 |  |  | 0.02848% | 6167.49 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24038 | MayfieldLeakRegs | Mayfield Leak Regs Functional | 5741.48 | 0 |  |  | 0.02651% | 5741.48 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23464 | 050.2638.Replace Ground Bed | The ground bed at our 18th Street rectifier is depleted. The output has been steadily falling off and is to the point where it is not protecting the pipleine. | -27.73 | 12181.95 | -2477.77 | -20.34% | 0.0448% | 9704.18 | 12181.95 | -2477.77 | 2010-10-01 | 2011-09-30 | 2010-07-22 | 07 | 2010-09-28 | 09
| 050.24031 | DanvilleLeakRegs | Danville Leak Regs Functional | 42023.94 | 0 |  |  | 0.194% | 42023.94 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24033 | KY.ShelbyvilleLeakRegs | Shelbyville KY Leak Regs Functional | 2352.4 | 0 |  |  | 0.01086% | 2352.4 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 37240.86 | 0 |  |  | 0.1727% | 37406.85 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22140 | 050.2637.Odorizer - Calvert | We plan to install an odorizer in the Calvert industrial park and abandon a dozen smaller individual drip pots.We will then dispose of these smaller units a few every year, as this is an expensive procedure. | 200.17 | 97154 | 7257.97 | 7.471% | 0.4821% | 104411.97 | 97154 | 7257.97 | 2010-10-01 | 2011-09-30 | 2009-07-02 | 07 | 2009-09-29 | 09
| 050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 342951.22 | 0 |  |  | 1.583% | 342968.84 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 169187.29 | 0 |  |  | 0.7811% | 169187.29 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 24983.92 | 0 |  |  | 0.1153% | 24983.92 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23835 | CampbellsvilleIntegRegs | Campbellsville Non Growth Regs Functional | 25731.52 | 0 |  |  | 0.1188% | 25731.52 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23840 | OboroIntegRegs | Owensboro Non Growth Regs Functional | 129421.19 | 0 |  |  | 0.5975% | 129421.19 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23841 | PaducahIntegRegs | Paducah Non Growth Regs Functional | 44798.34 | 0 |  |  | 0.2068% | 44798.34 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22394 | 050.KY.DanvilleIntegFunct2010 | 050.KY.DanvilleIntegFunct2010 | -13248.65 | 0 |  |  | 2.28% | 493905.13 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22301 | 050.2637.Allegheny Rd Ext | install 360 feet 2 inch pe for one existing residential | -77.28 | 2418.84 | 990.48 | 40.95% | 0.01574% | 3409.32 | 2418.84 | 990.48 | 2010-10-01 | 2011-09-30 | 2009-09-02 | 09 | 2009-09-17 | 09
| 050.20925 | 050.2609.Bon Harbor Well #6 | Workover Bon Harbor Well #6 | -6266.97 | 156248.88 | -9716.01 | -6.218% | 0.6765% | 146532.87 | 156248.88 | -9716.01 | 2010-10-01 | 2011-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.22435 | 050.KY.MadisonLeakFunct2010 | 050.KY.MadisonLeakFunct2010 | 1661.12 | 0 |  |  | 0.7277% | 157610.63 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 260722.14 | 0 |  |  | 1.204% | 260722.14 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 38054.24 | 0 |  |  | 0.1757% | 38054.24 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.21946 | 2738.GRN.E COLUMBIA RELOCATE | RELOCATE 2" STEEL ON EAST COLUMBIA WITH NEW WATERLINE | 53.26 | 8455 | -2407.74 | -28.48% | 0.02792% | 6047.26 | 8455 | -2407.74 | 2010-10-01 | 2011-09-30 | 2009-03-24 | 03 | 2012-03-25 | 03
| 050.24177 | 050.2637.Locator - Thomason | Pipehorn Model MD840 dual frequency pipe locator to be purchased for use in the Paducah area. Will be assigned to Mickie Thomason. | 165.9 | 1896.24 | -60.16 | -3.173% | 0.008477% | 1836.08 | 1896.24 | -60.16 | 2010-10-01 | 2011-09-30 | 2010-09-28 | 09 | 2010-09-30 | 09
| 050.24758 | 050.2734.Robbins Ext - Russ | 400 ft. of 2 inch PE - Robbins Way - Russellville | -1066.04 | 2236.25 | -3302.29 | -147.7% | -0.004922% | -1066.04 | 2236.25 | -3302.29 | 2010-10-01 | 2011-09-30 | 2010-11-12 | 11 | 2011-09-28 | 09
| 050.24915 | 050.2636.10424-01 | Mec Forfeitures | -2243 | 0 |  |  | -0.01036% | -2243 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-31 | 01 | 2011-01-31 | 01
| 050.24939 | 050.2612.Replace EFM KY 2011 | Purchase 13 Mercury Mini Max s To replace obsolete s | 24030.97 | 27401.66 | -3370.69 | -12.3% | 0.111% | 24030.97 | 27401.66 | -3370.69 | 2010-10-01 | 2011-09-30 | 2011-02-07 | 02 | 2011-09-29 | 09
| 050.22072 | TchSvr.Mea.EFM Repl - MO | EFM Replacement for Missoure | 109.31 | 19597 | -3100.76 | -15.82% | 0.07616% | 16496.24 | 19597 | -3100.76 | 2010-10-01 | 2011-09-30 | 2009-06-05 | 06 | 2009-09-30 | 09
| 050.20509 | 2738.LEB.HENDRICKSON STATION | INSTALL REGULATOR STATION ON HENDRICKSON DR IN LEBANON | -5552.6 | 9458 | -3384.37 | -35.78% | 0.02804% | 6073.63 | 9458 | -3384.37 | 2010-10-01 | 2011-09-30 | 2008-03-04 | 03 | 2010-10-28 | 10
| 050.24833 | 050.2734.091724-01 | Mec Forfeiture | -253 | 0 |  |  | -0.001168% | -253 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-17 | 12 | 2010-12-17 | 12
| 050.24768 | 0500.2735.RMLD.Glasgow | 050.2735.RMLD.Glasgow | 32280.99 | 26741 | 5539.99 | 20.72% | 0.149% | 32280.99 | 26741 | 5539.99 | 2010-10-01 | 2011-09-30 | 2010-11-18 | 11 | 2011-09-28 | 09
| 050.24835 | 050.2637.CGI - Tooley | This project is for the purpose of purchasing two CGIs One for Tim Tooley one for Alan Dillworth | 6151.97 | 4379.23 | 1772.74 | 40.48% | 0.0284% | 6151.97 | 4379.23 | 1772.74 | 2010-10-01 | 2011-09-30 | 2010-12-17 | 12 | 2011-02-25 | 02
| 050.24906 | 050.2653.918256-01 | Mec Forfeiture | -811 | 0 |  |  | -0.003744% | -811 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24913 | 050.2634.918018-01 | Mec Forfeiture | -1033 | 0 |  |  | -0.004769% | -1033 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24899 | 050.2634.10347-01 | Mec Forfeiture | -928 | 0 |  |  | -0.004285% | -928 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24232 | 050.2634.TB1 Boiler | Install Boiler at TB 1 | 54710.61 | 59359.95 | -4649.34 | -7.832% | 0.2526% | 54710.61 | 59359.95 | -4649.34 | 2010-10-01 | 2011-09-30 | 2010-10-21 | 10 | 2011-09-28 | 09
| 050.21983 | 050.2637.Lady Karen Ext | Install 580 feet of 2 inch poly for two existing customers | 1360 | 2845.37 | -1799.63 | -63.25% | 0.004828% | 1045.74 | 2845.37 | -1799.63 | 2010-10-01 | 2011-09-30 | 2009-04-13 | 04 | 2011-01-21 | 01
| 050.22397 | 050.KY.MadisonIntegFunct2010 | 050.KY.MadisonIntegFunct2010 | -15509.79 | 0 |  |  | 3.414% | 739528.18 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2011-01-12 | 01
| 050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 94667.11 | 0 |  |  | 0.4371% | 94667.11 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23522 | 050.2636.Hartford Purchase | Repair to Station | -4474.69 | 9980.66 | 7519.51 | 75.34% | 0.0808% | 17500.17 | 9980.66 | 7519.51 | 2010-10-01 | 2011-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
| 050.24757 | 0500.2734.Baileys Farm 2-B | 1500 ft. of 2 inch PE for 26 lots - Baileys Farms 2-B | 11586.23 | 4131.24 | 7454.99 | 180.5% | 0.05349% | 11586.23 | 4131.24 | 7454.99 | 2010-10-01 | 2011-09-30 | 2010-11-11 | 11 | 2011-09-28 | 09
| 050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 145600.02 | 0 |  |  | 0.6722% | 145600.02 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 23803.34 | 0 |  |  | 0.1099% | 23803.34 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 23868.08 | 0 |  |  | 0.1102% | 23868.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23188 | 050.2637.YZ Replace Trunkline | This project is for an upgrade to our YZ odorizer at our Trunkline Purchase Station in western Mccracken County This is a 2010 budgeted item. The existing model 7200 pump is obsolete, and we cannot get parts. We would like to purchase the model 7300. | 302.83 | 31656.86 | -10511.34 | -33.2% | 0.09763% | 21145.52 | 31656.86 | -10511.34 | 2010-10-01 | 2011-09-30 | 2010-02-17 | 02 | 2010-05-27 | 05
| 050.24874 | 050.2602.MDTs 2 2011 | Project to purchase additional MDTs | 81772.51 | 78868.07 | 2904.44 | 3.683% | 0.3775% | 81772.51 | 78868.07 | 2904.44 | 2010-10-01 | 2011-09-30 | 2011-01-19 | 01 | 2011-09-28 | 09
| 050.26304 | GlasgowPRPMeters | Glasgow KY PRP Functional - Meters | 7274.35 | 0 |  |  | 0.03359% | 7274.35 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.26286 | PRP.2737.HAR.PEARSON ST | INSTALL 300ft OF 2in PE TO REPLACE BARE STEEL | 2182.24 | 8894.53 | -6712.29 | -75.47% | 0.01008% | 2182.24 | 8894.53 | -6712.29 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.25659 | Bon Harbor Storage YZ | Bon Harbor Storage YZ for no flow conditions | 34649.82 | 37209 | -2559.18 | -6.878% | 0.16% | 34649.82 | 37209 | -2559.18 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27103 | I/P EFM's | I/P EFM for new customers | 31303.15 | 31007.5 | 295.65 | 0.9535% | 0.1445% | 31303.15 | 31007.5 | 295.65 | 2010-10-01 | 2011-09-30 | 2011-08-30 | 08 | 2011-09-30 | 09
| 050.25695 | 050.2734.Penn Station Ext. | 230 ft. of 2 inch PE Extension - Penn Station Bowling Green | 561.77 | 2553.89 | -1992.12 | -78% | 0.002594% | 561.77 | 2553.89 | -1992.12 | 2010-10-01 | 2011-09-30 | 2011-04-21 | 04 | 2011-09-28 | 09
| 050.26383 | 050.2734.Suwannee Trl. Ext. | 550 ft. of 2 inch PE - Suwannee Trail | 3149.39 | 2092.82 | 1056.57 | 50.49% | 0.01454% | 3149.39 | 2092.82 | 1056.57 | 2010-10-01 | 2011-09-30 | 2011-06-21 | 06 | 2011-09-28 | 09
| 050.25128 | 050.2609.Hwy 60 bypass Relo. | Relocate 1100 ft 8 Inch Stl. and 1200 ft 4 Inch Stl. HPD | 332931.16 | 7754.15 | 325177.01 | 4194% | 1.537% | 332931.16 | 7754.15 | 325177.01 | 2010-10-01 | 2011-09-30 | 2011-02-01 | 02 | 2011-09-28 | 09
| 050.25506 | 11m 175 Certified test meter | Certified test meter for verifing model 5 provers | 4262.71 | 4961.2 | -698.49 | -14.08% | 0.01968% | 4262.71 | 4961.2 | -698.49 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.25447 | 2738.LEB LORETTO RD 2011 | INSTALL 4in PE FOR EXISTING HOMES PER CUSTOMER REQUEST | 8978.02 | 14328.95 | -5350.93 | -37.34% | 0.04145% | 8978.02 | 14328.95 | -5350.93 | 2010-10-01 | 2011-09-30 | 2011-04-01 | 04 | 2012-04-01 | 04
| 050.23527 | 050.2612.Transportion EFM | New Transportion Customers,Amcor Caldwell Co. Hospital,S&Y Terminal And USNC | 112.19 | 13738.74 | -1038.58 | -7.559% | 0.05864% | 12700.16 | 13738.74 | -1038.58 | 2010-10-01 | 2011-09-30 | 2010-08-23 | 08 | 2010-09-30 | 09
| 050.23356 | 050.2734.Massey Springs Ext. | 420 ft. of 2 inch PE to serve assisted livining development | 855.54 | 4654.13 | -2923.21 | -62.81% | 0.007992% | 1730.92 | 4654.13 | -2923.21 | 2010-10-01 | 2011-09-30 | 2010-05-27 | 05 | 2010-09-28 | 09
| 050.23359 | 050.2736.TB 1 Replacement | Replace Dated Station | 245058.6 | 549090.34 | 11935.4 | 2.174% | 2.59% | 561025.74 | 549090.34 | 11935.4 | 2010-10-01 | 2011-09-30 | 2010-06-01 | 06 | 2010-09-28 | 09
| 050.23147 | 050.2636.Wescore Purchase | Purchase new 2" Mooney Regulator for the Wescore Purchase Station. | 27.73 | 4094.65 | -509.43 | -12.44% | 0.01655% | 3585.22 | 4094.65 | -509.43 | 2010-10-01 | 2011-09-30 | 2010-01-29 | 01 | 2010-09-28 | 09
| 050.21628 | 050.BGR.GLS.HWY 31W RELOC. | 1100 FT OF 2" PE - HYW 31W - MUNFORDVILLE | 14217.12 | 53495 | 18006.79 | 33.66% | 0.3301% | 71501.79 | 53495 | 18006.79 | 2010-10-01 | 2011-09-30 | 2008-11-11 | 11 | 2009-11-11 | 11
| 050.23534 | 050.2636.Hunters Chase Court | Install 500 Ft 2 Inch PE | -460.25 | 1596.86 | 231.32 | 14.49% | 0.008441% | 1828.18 | 1596.86 | 231.32 | 2010-10-01 | 2011-09-30 | 2010-08-26 | 08 | 2010-09-28 | 09
| 050.22391 | 050.KY.BowlGrnIntegFunct2010 | 050.KY.BowlGrnIntegFunct2010 | -23700.92 | 0 |  |  | 5.878% | 1273058.12 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22430 | 050.KY.GlasgowLeakFunct2010 | 050.KY.GlasgowLeakFunct2010 | -2070.01 | 0 |  |  | 1.118% | 242062.74 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2011-03-12 | 03
| 050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 80780.08 | 0 |  |  | 0.373% | 80780.08 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24819 | 050.2737.918231-02 | Mec Forfeiture | -768.12 | 0 |  |  | -0.003546% | -768.12 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.24823 | 050.2737.918535-01 | Mec Forfeiture | -973 | 0 |  |  | -0.004492% | -973 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 92429.9 | 0 |  |  | 0.4267% | 92429.9 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 86310.93 | 0 |  |  | 0.3985% | 86310.93 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 10249.77 | 0 |  |  | 0.04732% | 10249.77 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24067 | BowlingLeakCP/LeakClamps | Bowling Green KY Leak Functional - CP/Leak Clamps | 212997.34 | 0 |  |  | 0.9834% | 212997.34 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24072 | KY.ShelbyvilleLeakCP/LeakClmps | Shelbyville KY Leak Functional - CP/Leak Clamps | 7434.24 | 0 |  |  | 0.03843% | 8322.67 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23231 | 2737.DEAR MEADOW PH 2 | INSTALL 600ft OF 2in PE | -573.51 | 7710.64 | -5421.96 | -70.32% | 0.01057% | 2288.68 | 7710.64 | -5421.96 | 2010-10-01 | 2011-09-30 | 2010-03-10 | 03 | 2011-04-15 | 04
| 050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 44292.36 | 0 |  |  | 0.2045% | 44292.36 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 144108.65 | 0 |  |  | 0.6692% | 144945.44 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 35345.62 | 0 |  |  | 0.1632% | 35345.62 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 16106.65 | 0 |  |  | 0.07436% | 16106.65 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 14598.99 | 0 |  |  | 0.0674% | 14598.99 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 70830.51 | 0 |  |  | 0.327% | 70830.51 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 45632.94 | 0 |  |  | 0.2107% | 45632.94 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24916 | 050.2636.10382-01 | Mec Forfeiture | -453 | 0 |  |  | -0.002091% | -453 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-31 | 01 | 2011-01-31 | 01
| 050.24784 | 050.2636.0918633-01 | Mec Forfeiture | -4668 | 0 |  |  | -0.02155% | -4668 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24785 | 050.2734.0917319-01 | Mec Forfeiture | -48 | 0 |  |  | -0.0002216% | -48 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24771 | 050.2637.0917611-01 | Mec Forfeiture | -1566 | 0 |  |  | -0.00723% | -1566 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-18 | 11 | 2010-11-18 | 11
| 050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 128747.58 | 0 |  |  | 0.5944% | 128747.58 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23388 | 050.2634.TB1 Replacement | 050.2634.TB1 Replacement | 630.49 | 253593.8 | 2457.53 | 0.9691% | 1.182% | 256051.33 | 253593.8 | 2457.53 | 2010-10-01 | 2011-09-30 | 2010-06-14 | 06 | 2010-09-28 | 09
| 050.24914 | 050.2634.918154-01 | Mec Forfeiture | -6472 | 0 |  |  | -0.02988% | -6472 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-28 | 01 | 2011-01-28 | 01
| 050.24946 | 050.2636.Pleasant Valley Rd. | Install 1244 ft 2 Inch PE | 39.52 | 2730.05 | -2690.53 | -98.55% | 0.0001825% | 39.52 | 2730.05 | -2690.53 | 2010-10-01 | 2011-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
| 050.24807 | 2739.WELDER | TRAILBLAZER 302 WELDER WITH LEADS AND CONTROLS | 11025.89 | 17303 | -6277.11 | -36.28% | 0.05091% | 11025.89 | 17303 | -6277.11 | 2010-10-01 | 2011-09-30 | 2010-12-06 | 12 | 2011-04-01 | 04
| 050.24089 | DanvillePRPMeters | Danville KY PRP Functional - Meters | 1452.77 | 0 |  |  | 0.006707% | 1452.77 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 2932.01 | 0 |  |  | 0.01354% | 2932.01 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-20 | 09 | 2016-09-30 | 09
| 050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 56984.14 | 0 |  |  | 0.2631% | 56984.14 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23834 | DanvilleIntegRegs | Danville Non Growth Regs Functional | 20017.21 | 0 |  |  | 0.09242% | 20017.21 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24172 | 050.2736.E. 4th St. Rplmnt | Replace 400 ft 4 Inch LP with 2 Inch IP PE | 23295.39 | 20535.63 | 2759.76 | 13.44% | 0.1076% | 23295.39 | 20535.63 | 2759.76 | 2010-10-01 | 2011-09-30 | 2010-09-27 | 09 | 2010-09-28 | 09
| 050.20927 | 050.2609.Bon Harbor Well #4 | Workover Bonharbor Well #4 | -8926 | 215362.55 | -13723.92 | -6.372% | 0.931% | 201638.63 | 215362.55 | -13723.92 | 2010-10-01 | 2011-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.23531 | 050.2636.Hwy 56 | Install 4100 Feet 4 Inch PE | 47962.26 | 54644.06 | -6418.65 | -11.75% | 0.2227% | 48225.41 | 54644.06 | -6418.65 | 2010-10-01 | 2011-09-30 | 2010-08-23 | 08 | 2010-09-28 | 09
| 050.24068 | GlasgowLeakCP/LeakClamps | Glasgow Leak Functional - CP/Leak Clamps | 105065.69 | 0 |  |  | 0.4851% | 105065.69 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24769 | 050.2734.0917777-01 | Mec Forfeiture | -8087 | 0 |  |  | -0.03734% | -8087 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-18 | 11 | 2010-11-18 | 11
| 050.23519 | 050.2609.Line Locator | Purchase new line locator retire old one. | 227.6 | 8462.9 | -4447.59 | -52.55% | 0.01854% | 4015.31 | 8462.9 | -4447.59 | 2010-10-01 | 2011-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
| 050.22978 | 2737.STAN.HUBBLE RELOCATE | RELOCATE 440' OF 2in DUPONT WITH 2in PE | -297.9 | 3597.11 | 2574.12 | 71.56% | 0.02849% | 6171.23 | 3597.11 | 2574.12 | 2010-10-01 | 2011-09-30 | 2009-10-29 | 10 | 2010-10-01 | 10
| 050.23381 | 050.2638.Mayfield Bypass | Relocate required due to KYDOT improvements | 37683.96 | 49488.84 | 96484.11 | 195% | 0.674% | 145972.95 | 49488.84 | 96484.11 | 2010-10-01 | 2011-09-30 | 2010-06-09 | 06 | 2010-09-28 | 09
| 050.26187 | 050.2636.Palomino Place | Install 260 Ft 2 Inch PE | 791.35 | 3050.45 | -2259.1 | -74.06% | 0.003654% | 791.35 | 3050.45 | -2259.1 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2011-09-28 | 09
| 050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 131.91 | 0 |  |  | 0.000609% | 131.91 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.25029 | 050.2736.Station Retirement | Retire station piping no longer in use. | 2254.03 | 8610.1 | -6356.07 | -73.82% | 0.01041% | 2254.03 | 8610.1 | -6356.07 | 2010-10-01 | 2011-09-30 | 2011-02-17 | 02 | 2011-09-28 | 09
| 050.25118 | 050.2734.Daisy Field Ct. Relo | Relocate 450 ft. of 2" PE Main | 3076.49 | 4131.13 | -1054.64 | -25.53% | 0.0142% | 3076.49 | 4131.13 | -1054.64 | 2010-10-01 | 2011-09-30 | 2011-02-28 | 02 | 2011-09-28 | 09
| 050.26625 | PRP.2635.Nichols Ave. Ret. | Retire | 439.7 | 902.37 | -462.67 | -51.27% | 0.00203% | 439.7 | 902.37 | -462.67 | 2010-10-01 | 2011-09-30 | 2011-07-12 | 07 | 2011-09-28 | 09
| 050.26812 | 050.PRP.2634.Woodson St. Rt. | Retire 244 Ft 2 Inch Bare in Madisonville 3 services to be move to main across the street. | 1720.07 | 777.48 | 942.59 | 121.2% | 0.007942% | 1720.07 | 777.48 | 942.59 | 2010-10-01 | 2011-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.27137 | 050.2636.Plantation Pointe 2 | Install 1000 ft 2 Inch PE | 4583.94 | 5694.69 | -1110.75 | -19.51% | 0.02116% | 4583.94 | 5694.69 | -1110.75 | 2010-10-01 | 2011-09-30 | 2010-12-01 | 12 | 2011-04-01 | 04
| 050.26418 | 050.2636.Autumn Creek | Install 1166 Ft 2 Inch PE to serve 22 residential lots | 7520.36 | 12367.15 | -4846.79 | -39.19% | 0.03472% | 7520.36 | 12367.15 | -4846.79 | 2010-10-01 | 2011-09-30 | 2011-06-20 | 06 | 2011-09-28 | 09
| 050.26745 | 050.2734.Commerce and B White | 1875 ft. of 2 inch PE - Commerce and B. White - Elkton | 3726.5 | 8119.62 | -4393.12 | -54.1% | 0.01721% | 3726.5 | 8119.62 | -4393.12 | 2010-10-01 | 2011-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
| 050.26935 | 2739.SVILL.2011-12 OFFICE | TURN KEY-LOT9b HI POINT INDUST PARK,LAND&BUILDING,LANDSCAPE,BUILD,ASPHALT,CONCRETE BINS,FENCE,700ft SIDEWALK ON RD FRONTAGE,USING LOCAL CONTRACTORS AND MATERIAL SUPPLIERS,INCLUDE DETENTION BASIN. DEAN SANDERSON-DIR FACILITIES MANAGEMENT - HAS FACILITATED | 382050.73 | 745000 | -362949.27 | -48.72% | 1.764% | 382050.73 | 745000 | -362949.27 | 2010-10-01 | 2011-09-30 | 2011-08-15 11:05 | 08 | 2012-02-15 | 02
| 050.27142 | Gas_line_tracer_kit | We are requesting to purchase a Jameson model 15-316-300-GL gas line tracer kit. The kit includes mini duct hunter with bullet nose tip, stuffing box w/ 3/4" NPT male threads, accessory kit, & instructions/manual. | 1031.08 | 1131.31 | -100.23 | -8.86% | 0.00476% | 1031.08 | 1131.31 | -100.23 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27207 | 050.2635.Hwy 62 | Install 2,112 feet 4 Inch PE to serve natural gas fleet fueling station. | 931.14 | 7683.47 | -6752.33 | -87.88% | 0.004299% | 931.14 | 7683.47 | -6752.33 | 2010-10-01 | 2011-09-30 | 2009-08-19 | 08 | 2009-09-28 | 09
| 050.25223 | 050.2634.Purchase RMLD & DPIR | Purchase RMLD & DPIR to increase surveying productivity | 44778.52 | 35075.79 | 9702.73 | 27.66% | 0.2067% | 44778.52 | 35075.79 | 9702.73 | 2010-10-01 | 2011-09-30 | 2011-03-15 | 03 | 2011-09-28 | 09
| 050.26506 | 050.2637.Adams St Retirement | Abandon 1,257 feet of 2 inch steel | 2348.16 | 3656.15 | -1307.99 | -35.78% | 0.01084% | 2348.16 | 3656.15 | -1307.99 | 2010-10-01 | 2011-09-30 | 2011-07-11 | 07 | 2011-09-28 | 09
| 050.24120 | 050.2638.E.F Equip | Electro fuse equipment for use in the Mayfield area. | 792.11 | 10014.22 | -185.08 | -1.848% | 0.04538% | 9829.14 | 10014.22 | -185.08 | 2010-10-01 | 2011-09-30 | 2010-09-21 | 09 | 2010-09-30 | 09
| 050.26762 | 2734.Bowling Green KY Shed | Purchase single slope building (24'x45'x22'). Consult, design and build done by Hard Ten Group, LLC | 32160.98 | 35290.68 | -3129.7 | -8.868% | 0.1485% | 32160.98 | 35290.68 | -3129.7 | 2010-10-01 | 2011-09-30 | 2011-07-29 09:07 | 07 | 2011-08-01 | 08
| 050.26542 | 050.2635.Electro Fuse Machine | Purchase portable Electro Fuse Machine | 6744.03 | 6845.54 | -101.51 | -1.483% | 0.03114% | 6744.03 | 6845.54 | -101.51 | 2010-10-01 | 2011-09-30 | 2011-07-15 | 07 | 2011-09-30 | 09
| 050.23049 | 2739.WILD TURKEY EXPANSION | INSTALL 600ft OF 4iN STEEL FOR WILD TURKEY EXPANSION | 1438.97 | 11308.5 | 3809.73 | 33.69% | 0.0698% | 15118.23 | 11308.5 | 3809.73 | 2010-10-01 | 2011-09-30 | 2009-12-03 | 12 | 2010-10-01 | 10
| 050.24959 | 2738.GRE.CARLISLE AVE | INSTALL 140ft OF 2in PE ON CARLISLE AVE | 1086.18 | 1166.8 | -80.62 | -6.909% | 0.005015% | 1086.18 | 1166.8 | -80.62 | 2010-10-01 | 2011-09-30 | 2011-02-18 | 02 | 2012-02-01 | 02
| 050.24144 | 050.2612.REFURB METERS FY11 | cc2612 KY Refurb Meters FY 2011 | 175788.57 | 248506 | -65340.31 | -26.29% | 0.8457% | 183165.69 | 248506 | -65340.31 | 2010-10-01 | 2011-09-30 | 2010-09-22 | 09 | 2011-09-30 | 09
| 050.23465 | 050.2638.Ashcroft Guage | We propose to retire (7) Mercury pressure recorders from various small stations in the Mayfield area. We propose to replace them with Ashcroft model 1279 Duragauge pressure guages with "tell tale" dials. | 1348.46 | 6316.86 | -4968.4 | -78.65% | 0.006226% | 1348.46 | 6316.86 | -4968.4 | 2010-10-01 | 2011-09-30 | 2010-07-23 | 07 | 2010-09-28 | 09
| 050.22473 | 2739.HAVEN HILL-MIDLAND | REPLACE 4in STEEL WITH 4in PE FOR BYPASS CONSTRUCTION | 8.45 | 4004.35 | -3045.61 | -76.06% | 0.004426% | 958.74 | 4004.35 | -3045.61 | 2010-10-01 | 2011-09-30 | 2009-09-29 | 09 | 2010-10-01 | 10
| 050.23431 | 050.2734.Springfield VII | 1200 ft. of 2 inch PE - Springfield VII | 2031.25 | 6165.79 | -1881.43 | -30.51% | 0.01978% | 4284.36 | 6165.79 | -1881.43 | 2010-10-01 | 2011-09-30 | 2010-06-25 | 06 | 2010-09-28 | 09
| 050.22361 | 050.KY.PaducahGrowthFunct2010 | 050.KY.PaducahGrowthFunct2010 | -8270.37 | 0 |  |  | 2.65% | 574021.93 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22362 | 050.KY.MayfieldGrowthFunct2010 | 050.KY.MayfieldGrowthFunct2010 | -334.97 | 0 |  |  | 0.2346% | 50805.15 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22401 | 050.KY.MayfieldIntegFunct2010 | 050.KY.MayfieldIntegFunct2010 | -1520.09 | 0 |  |  | 1.295% | 280476.69 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22432 | 050.KY.DanvilleLeakFunct2010 | 050.KY.DanvilleLeakFunct2010 | -2408.49 | 0 |  |  | 0.8528% | 184717.79 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23415 | 050.2734.Reg Replc TB 4 | 050.2734.Reg Replc TB 4 | 617.62 | 14877.9 | -6273.15 | -42.16% | 0.03973% | 8604.75 | 14877.9 | -6273.15 | 2010-10-01 | 2011-09-30 | 2010-06-24 | 06 | 2010-09-28 | 09
| 050.24813 | 050.2634. Bruest Heaters | Purchase and retire Bruest Heaters | 7051.9 | 9073.76 | -2021.86 | -22.28% | 0.03256% | 7051.9 | 9073.76 | -2021.86 | 2010-10-01 | 2011-09-30 | 2010-12-09 | 12 | 2011-09-28 | 09
| 050.24820 | 050.2737.918392-01 | Mec Forfeiture | -1020 | 0 |  |  | -0.004709% | -1020 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.24825 | 050.2737.10475-01 | Mec Forfeiture | -801 | 0 |  |  | -0.003698% | -801 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2010-12-14 | 12
| 050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 27193.67 | 0 |  |  | 0.1256% | 27193.67 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 10298.48 | 0 |  |  | 0.04755% | 10298.48 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24037 | PaducahLeakRegs | Paducah Leak Regs Functional | 7709.76 | 0 |  |  | 0.0356% | 7709.76 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 13106.84 | 0 |  |  | 0.06051% | 13106.84 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 54391.04 | 0 |  |  | 0.2642% | 57218.26 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 96853.7 | 0 |  |  | 0.4472% | 96853.7 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 26483.74 | 0 |  |  | 0.1223% | 26483.74 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-10 | 09 | 2010-09-23 | 09
| 050.23831 | BowlingGreenIntegRegs | Bowling Green Non Growth Regs Functional | 24579.34 | 0 |  |  | 0.1135% | 24579.34 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 12649.51 | 0 |  |  | 0.0584% | 12649.51 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 6529.59 | 0 |  |  | 0.03015% | 6529.59 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.24123 | 050.2637.Valve 4 inch | This project is for the purchase of a 4 inch T.D Williamson Shortcutt Valve to tap 4" steel. | 8514.93 | 6172.1 | 2342.83 | 37.96% | 0.03931% | 8514.93 | 6172.1 | 2342.83 | 2010-10-01 | 2011-09-30 | 2010-09-21 | 09 | 2010-09-30 | 09
| 050.23559 | 2738.GREENSBURG RD.BLEVIN CON | INSTALL 2in PE FOR BLEVINS CONST OFFICE ON GREENSBURG RD | -442.16 | 3962.45 | -4387.13 | -110.7% | -0.001961% | -424.68 | 3962.45 | -4387.13 | 2010-10-01 | 2011-09-30 | 2010-09-07 | 09 | 2011-08-01 | 08
| 050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 10922.84 | 0 |  |  | 0.05043% | 10922.84 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 31850.14 | 0 |  |  | 0.1471% | 31850.14 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 334226.02 | 0 |  |  | 1.542% | 333944.35 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23406 | 2738.SALOMA RD.REPLACE | REPLACE 468ft OF 2in STEEL ON SALOMA RD NEAR HILL LN | -297.88 | 5735.48 | -4756.94 | -82.94% | 0.004518% | 978.54 | 5735.48 | -4756.94 | 2010-10-01 | 2011-09-30 | 2010-06-21 | 06 | 2010-10-01 | 10
| 050.24753 | 050.2636.Wood Valley Pointe | Install 1068 Ft 2 Inch PE | 8510.28 | 7475.73 | 1034.55 | 13.84% | 0.03929% | 8510.28 | 7475.73 | 1034.55 | 2010-10-01 | 2011-09-30 | 2010-11-11 | 11 | 2011-09-28 | 09
| 050.24764 | 050.2634.Safe T Stopper | Purchase Safe T Stopper | 12502.83 | 10999.08 | 1503.75 | 13.67% | 0.05773% | 12502.83 | 10999.08 | 1503.75 | 2010-10-01 | 2011-09-30 | 2010-11-17 | 11 | 2011-09-28 | 09
| 050.24827 | 2738.WATER TOWER RD | INSTALL 2in PE FOR NEW INDUSTRIAL CUSTOMER | 8285.39 | 1802.1 | 6483.29 | 359.8% | 0.03825% | 8285.39 | 1802.1 | 6483.29 | 2010-10-01 | 2011-09-30 | 2010-12-14 | 12 | 2011-12-01 | 12
| 050.24929 | 2738.W SALOMA 2011 | INSTALL4000ft OF 2in PE FOR GRAIN DRYER ON W SALOMA ROAD REG STATION INCLUDED | 17689.5 | 3861.54 | 13827.96 | 358.1% | 0.08167% | 17689.5 | 3861.54 | 13827.96 | 2010-10-01 | 2011-09-30 | 2011-02-04 | 02 | 2012-02-01 | 02
| 050.24215 | 050.2636.Pantle Point | Install 980 Ft 2 Inch PE | 7838.95 | 5436.96 | 2401.99 | 44.18% | 0.03619% | 7838.95 | 5436.96 | 2401.99 | 2010-10-01 | 2011-09-30 | 2010-10-13 | 10 | 2011-09-28 | 09
| 050.24853 | 2737.PERRYVILLE PURCH REBUILD | REBUILD PERRYVILLE PURCHASE STATION ADDING 1st CUT REGULATION | 58151.83 | 48209.34 | 9942.49 | 20.62% | 0.2685% | 58151.83 | 48209.34 | 9942.49 | 2010-10-01 | 2011-09-30 | 2011-01-06 | 01 | 2011-10-01 | 10
| 050.23267 | 050.2636.Install Relief valves | Replace Relief Valves Glenville Calhoun Beaver Dam TB and Stanley Wimsatt Rd Station | 127.26 | 24583.3 | 599.94 | 2.44% | 0.1163% | 25183.24 | 24583.3 | 599.94 | 2010-10-01 | 2011-09-30 | 2010-04-07 | 04 | 2010-09-28 | 09
| 050.22393 | 050.KY.HopkinsIntegFunct2010 | 050.KY.HopkinsIntegFunct2010 | -10745.07 | 0 |  |  | 2.5% | 541375.17 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.24791 | 050.2637.10300 | Mec Forfeiture | -329 | 0 |  |  | -0.001519% | -329 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-29 | 11 | 2010-11-29 | 11
| 050.24778 | 050.2636.0918802-01 | Mec Forfeiture | -7370 | 0 |  |  | -0.03403% | -7370 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24777 | 050.2636.0918622-01 | Mec Forfeiture | -11239 | 0 |  |  | -0.05189% | -11239 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-11-23 | 11 | 2010-11-23 | 11
| 050.24170 | 050.2634.Electro Fuse Eq. | Purchase Electro fuse equipment | 6134.28 | 18483.58 | 3756.07 | 20.32% | 0.1027% | 22239.65 | 18483.58 | 3756.07 | 2010-10-01 | 2011-09-30 | 2010-09-27 | 09 | 2010-09-30 | 09
| 050.26310 | CampbellsvillePRPMeters | Campbellsville KY PRP Functional - Meters | 348 | 0 |  |  | 0.001607% | 348 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
| 050.27028 | Purchase pipe trailer | Purchase single axial pipe trailer from Sweetwater Metal, model number CT1135 | 4809.53 | 6042.64 | -1233.11 | -20.41% | 0.02221% | 4809.53 | 6042.64 | -1233.11 | 2010-10-01 | 2011-09-30 | 2011-08-18 22:23 | 08 | 2011-09-28 | 09
| 050.26221 | 050.2734.Franklin Warehouse | Replace existing metal building on Franklin Warehouse site. Existing building is approx. 70 years old . Approved FY 2011 Budget = $63,500.00 | 88307.2 | 92613.92 | -4306.72 | -4.65% | 0.4077% | 88307.2 | 92613.92 | -4306.72 | 2010-10-01 | 2011-09-30 | 2011-06-20 | 06 | 2011-09-28 | 09
| 050.26294 | new fence and drive | This project is for the purchase of a chain link fence and driveway improvements at our new Calvert City Odorant Station. | 7286.47 | 8157.76 | -871.29 | -10.68% | 0.03364% | 7286.47 | 8157.76 | -871.29 | 2010-10-01 | 2011-09-30 | 2011-06-15 13:49 | 06 | 2011-09-28 | 09
| 050.25145 | 050.2637.Boss III EF Machine | This project is for the purchase of a battery pack portable electro fuse machine | 10293.95 | 7654.78 | 2639.17 | 34.48% | 0.04753% | 10293.95 | 7654.78 | 2639.17 | 2010-10-01 | 2011-09-30 | 2011-03-15 | 03 | 2011-09-28 | 09
| 050.27372 | F.I. Unit Purchase | Purchase Heath Mod 1002390-0 ASSY, DP-IR, IS Complete | 16779.15 | 16917.27 | -138.12 | -0.8164% | 0.07747% | 16779.15 | 16917.27 | -138.12 | 2010-10-01 | 2011-09-30 | 2011-09-29 | 09 | 2011-09-30 | 09
| 050.26285 | PRP.2737.HAR.McCLELLAN DR | REPLACE 200ft OF BARE STEEL WITH 2in PE ON McCLELLAN DRIVE | 3679.76 | 6818.61 | -3138.85 | -46.03% | 0.01699% | 3679.76 | 6818.61 | -3138.85 | 2010-10-01 | 2011-09-30 | 2011-06-01 | 06 | 2012-06-01 | 06
| 050.24883 | 050.2734.0915703-01 | Mec Forfeitures | -939 | 0 |  |  | -0.004335% | -939 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-01-19 | 01 | 2011-01-19 | 01
| 050.26810 | 050.2734.Traditions III | 2 inch PE Extension - Traditions III - B.G. | 2011.05 | 7458.67 | -5447.62 | -73.04% | 0.009285% | 2011.05 | 7458.67 | -5447.62 | 2010-10-01 | 2011-09-30 | 2011-08-15 | 08 | 2011-09-28 | 09
| 050.27102 | Cell EFM Units | New customer Cell /I/P EFM's | 29016.46 | 30585.8 | -1569.34 | -5.131% | 0.134% | 29016.46 | 30585.8 | -1569.34 | 2010-10-01 | 2011-09-30 | 2011-08-30 | 08 | 2011-09-30 | 09
| 050.25440 | 050.2637.Marina Village Ext | Install 300 feet of 2 inch poly for two new residential customers. | -1182.18 | 2351.45 | -3533.63 | -150.3% | -0.005458% | -1182.18 | 2351.45 | -3533.63 | 2010-10-01 | 2011-09-30 | 2011-06-15 | 06 | 2011-09-28 | 09
| 050.26441 | PRP.2737.STAN.LOGAN CLOVER | REPLACE 25ft OF 2in BARE STEEL WHERE CONTRACTOR NEEDED LINE LOWERED | 6636.19 | 0 |  |  | 0.03064% | 6636.19 | Not Budgeted |  | 2010-10-01 | 2011-09-30 | 2011-06-15 | 06 | 2011-10-01 | 10
| 050.27383 | 050.2636.Sensit G2 | Purchase 3- Sensit G2 leak machines , retire 3 Sensit Golds | 4391.51 | 4984.96 | -593.45 | -11.9% | 0.02028% | 4391.51 | 4984.96 | -593.45 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 10 | 2011-09-30 | 09
| 050.27236 | 050.2734.W Madison 2inch Ext | 445 ft. of 2 inch PE - West Madison Ext. | 3341.67 | 907.31 | 2434.36 | 268.3% | 0.01543% | 3341.67 | 907.31 | 2434.36 | 2010-10-01 | 2011-09-30 | 2011-09-15 | 09 | 2011-12-30 | 12
| 050.25996 | 050.2609.Carport | Have carport installed to protect mueller truck from the weather. | 6666 | 6822.31 | -156.31 | -2.291% | 0.03078% | 6666 | 6822.31 | -156.31 | 2010-10-01 | 2011-09-30 | 2011-05-17 21:48 | 05 | 2011-09-28 | 09
| 050.24748 | 050.2612 Winchester Gauge | Vac to 3000 psig Winchester Gauges | 3200.43 | 4721.42 | -1520.99 | -32.21% | 0.01478% | 3200.43 | 4721.42 | -1520.99 | 2010-10-01 | 2011-09-30 | 2010-11-08 | 11 | 2011-09-13 | 09
| 050.23525 | 2737.PERRYVILLE TBS RELOCATE | RELOCATE THE TBS FROM PRESENT LOCATION TO REYNOLDS PROPERTY OFF OF HIGHWAY 68 | 132919.41 | 137270.6 | 20986.98 | 15.29% | 0.7307% | 158257.58 | 137270.6 | 20986.98 | 2010-10-01 | 2011-09-30 | 2010-08-20 | 08 | 2011-03-25 | 03
| 050.23553 | 2738.SHELBY ST RETIREMENT | RETIRE 2in STEEL LINE ON SPRING AND SHELBY STREETS | -170.68 | 318.44 | 229.38 | 72.03% | 0.002529% | 547.82 | 318.44 | 229.38 | 2010-10-01 | 2011-09-30 | 2010-09-02 | 09 | 2011-01-06 | 01

## 2010a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2010
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2010 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.23340 | 050.2612.Crystal Cal XP | Crystal Cal XP Gauge Tester | 13082.29 | 14037.36 | -955.07 | -6.804% | 0.05759% | 13082.29 | 14037.36 | -955.07 | 2009-10-01 | 2010-09-30 | 2010-05-19 | 05 | 2010-09-30 | 09
| 050.20823 | 050.BGR.8"CENTER LINE HPD | 8" CENTER LINE HPD RELOC PHASE I - B.G. | -386837.01 | 1398465 | 494054.85 | 35.33% | 0.8333% | 1892519.85 | 1398465 | 494054.85 | 2009-10-01 | 2010-09-30 | 2008-07-25 | 07 | 2009-07-25 | 07
| 050.21069 | Hopkinsville 09 Non Growth | Hopkinsville 09 Non Growth | 4216.13 | Not Budgeted |  |  | 0.2098% | 476455.55 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21085 | Mayfield 09 Non Growth | Mayfield 09 Non Growth | 2781.21 | Not Budgeted |  |  | 0.1501% | 340824.22 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23065 | 050.2637.Calvert Reg Replace | We would like to retire the existing Axial flo regulator and install a 2" X 1" Mooney regulator. | 4530.72 | 3982.51 | 548.21 | 13.77% | 0.001995% | 4530.72 | 3982.51 | 548.21 | 2009-10-01 | 2010-09-30 | 2009-12-10 | 12 | 2010-01-26 | 01
| 050.19607 | Paducah 08 Non Growth | Paducah 08 Non Growth | -3447.86 | Not Budgeted |  |  | 0.4157% | 944015.23 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23479 | 050.2638.Wtr Valley Imp | Improvements include the installation of a Balon check valve | 3831.38 | 2554.89 | 1276.49 | 49.96% | 0.001687% | 3831.38 | 2554.89 | 1276.49 | 2009-10-01 | 2010-09-30 | 2010-08-02 | 08 | 2010-09-28 | 09
| 050.23217 | 050.2637.New Hope Rd Ext | 414 feet of 2 inch poly pipe for three exisrting residential customers | 3039.72 | 2164.15 | 875.57 | 40.46% | 0.001338% | 3039.72 | 2164.15 | 875.57 | 2009-10-01 | 2010-09-30 | 2010-03-03 | 03 | 2010-04-25 | 04
| 050.23094 | 040.009.2751Retirements | Old 040 retirement projects being transferred to 050 | -20504.81 | 1 | -20505.81 | -2050581% | -0.009028% | -20504.81 | 1 | -20505.81 | 2009-10-01 | 2010-09-30 | 2009-12-30 | 12 | 2010-12-30 | 12
| 050.23135 | 050.2634.ERX Recorders | Purchase 2 Dual pressure ERX Recorders | 4985.4 | 4040.77 | 944.63 | 23.38% | 0.002195% | 4985.4 | 4040.77 | 944.63 | 2009-10-01 | 2010-09-30 | 2010-01-26 | 01 | 2010-09-28 | 09
| 040.11699 | 040.DAN.CAM.VEH RETIRE #6793 | RETIRE VEHICLE #6793 | 2006.41 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-03-03 | 03 | 2005-05-04 | 05
| 050.22203 | TchSvr.EFM.Christian Fis. Crt | EFM for Christian County Fiscal Court | 200.48 | 4140 | -3168.22 | -76.53% | 0.0004279% | 971.78 | 4140 | -3168.22 | 2009-10-01 | 2010-09-30 | 2009-08-03 | 08 | 2009-09-30 | 09
| 050.23138 | 050.2612 I/P Modems | I/P modems | 7863.27 | 9019.31 | -1156.04 | -12.82% | 0.003462% | 7863.27 | 9019.31 | -1156.04 | 2009-10-01 | 2010-09-30 | 2010-01-27 | 01 | 2010-09-30 | 09
| 050.23324 | 050.2735 Glasgow Outer Loop | 4" PE Replacement - Glasgow Outer Loop | 42895.87 | 68162.83 | -25266.96 | -37.07% | 0.01889% | 42895.87 | 68162.83 | -25266.96 | 2009-10-01 | 2010-09-30 | 2010-05-10 | 05 | 2010-09-28 | 09
| 050.22352 | 050.KY.BowlgGrnGrowthFunct2010 | 050.KY.BowlgGrnGrowthFunct2010 | 655011.2 | Not Budgeted |  |  | 0.3105% | 705244.31 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22354 | 050.KY.HopkinsGrowthFunct2010 | 050.KY.HopkinsGrowthFunct2010 | 160868.5 | Not Budgeted |  |  | 0.07191% | 163326.32 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 385.02 | Not Budgeted |  |  | 0.0001695% | 385.02 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.24127 | 050.2636.Veterans Blvd. Relo | Relocate 900 Ft 6 Inch stl. with 6 Inch PE due to River Front project | 15066.94 | 56991.48 | -41924.54 | -73.56% | 0.006634% | 15066.94 | 56991.48 | -41924.54 | 2009-10-01 | 2010-09-30 | 2010-09-21 | 09 | 2010-12-25 | 12
| 050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 4712.64 | Not Budgeted |  |  | 0.002075% | 4712.64 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 1033.03 | Not Budgeted |  |  | 0.0004548% | 1033.03 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23444 | 050.2636.Graystone Phase 5 | Install 1015 Ft 2 Inch PE | 6664.89 | 8192.72 | -1527.83 | -18.65% | 0.002935% | 6664.89 | 8192.72 | -1527.83 | 2009-10-01 | 2010-09-30 | 2010-07-09 | 07 | 2010-09-28 | 09
| 050.23003 | 050.2637.21st & Monroe | Main replacement project due to leakage | 60841.51 | 42170.28 | 18671.23 | 44.28% | 0.02679% | 60841.51 | 42170.28 | 18671.23 | 2009-10-01 | 2010-09-30 | 2009-11-13 | 11 | 2009-11-30 | 11
| 050.22193 | 2737.W BUFORD RELOCATE | INSTALL 2in PE AND RETIRE ON BAUGHMAN BETWEEN GOVERNMENT ALLEY AND W BUFORD | 6254.76 | 7855.9 | -1027.66 | -13.08% | 0.003006% | 6828.24 | 7855.9 | -1027.66 | 2009-10-01 | 2010-09-30 | 2009-07-29 | 07 | 2010-10-01 | 10
| 050.21921 | TchSvr.Mea.EFM.Specialty Foods | EFM for Specialty Food Group in Owensboro | 28.32 | 4140 | -3165.17 | -76.45% | 0.0004292% | 974.83 | 4140 | -3165.17 | 2009-10-01 | 2010-09-30 | 2009-03-11 | 03 | 2009-09-30 | 09
| 050.22007 | 050.3351.CP Equip | various cp equipment for use by Mark Mars in the Sikeston, MO area | 2165.51 | 8960.11 | 1181.45 | 13.19% | 0.004465% | 10141.56 | 8960.11 | 1181.45 | 2009-10-01 | 2010-09-30 | 2009-05-01 | 05 | 2009-09-25 | 09
| 050.23312 | 050.2637.Irvin Cobb Relocate | Relocate 65 feet of gas main due to new sign being installed | 3157.24 | 4455.3 | -1298.06 | -29.14% | 0.00139% | 3157.24 | 4455.3 | -1298.06 | 2009-10-01 | 2010-09-30 | 2010-05-04 | 05 | 2010-09-30 | 09
| 050.23526 | 2738.BARE STEEL REPLACE 2010 | REPLACE 2500ft OF BARE STEEL ROSE, CENTER AND REDMAN | 63414.39 | 80790.58 | -17376.19 | -21.51% | 0.02792% | 63414.39 | 80790.58 | -17376.19 | 2009-10-01 | 2010-09-30 | 2010-08-20 | 08 | 2011-03-25 | 03
| 050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 100.06 | Not Budgeted |  |  | 4.406e-05% | 100.06 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.21528 | TchSvr.Mea.Outsourced Meters | Oursourced meter retirments and new meter purchases | 10806.16 | 195288 | 108780 | 55.7% | 0.1339% | 304068 | 195288 | 108780 | 2009-10-01 | 2010-09-30 | 2008-10-15 | 10 | 2009-09-30 | 09
| 050.22357 | 050.KY.ShelbyviGrowthFunct2010 | 050.KY.ShelbyviGrowthFunct2010 | 78676.29 | Not Budgeted |  |  | 0.03604% | 81864.2 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.24187 | Railroad Consolidation - KY | Payment of Railroad Crossings for 20 - 25 years - 7 Crossings | 8783.87 | 15529.5 | -6745.63 | -43.44% | 0.003868% | 8783.87 | 15529.5 | -6745.63 | 2009-10-01 | 2010-09-30 | 2010-09-30 | 09 | 2010-10-30 | 10
| 050.23558 | 050.2634.Las Vegas Ave.Ret. | Retire 251 ft. 2 Inch Stl. | 186.56 | 139.29 | 47.27 | 33.94% | 8.214e-05% | 186.56 | 139.29 | 47.27 | 2009-10-01 | 2010-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23958 | PaducahLeakServices | Paducah Leak Functional Services | -1996.35 | Not Budgeted |  |  | -0.000879% | -1996.35 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23117 | 050.2635.Poplar St. | Replace 2 Inch Bare Main with 712 feet of 2 Inc PE | 15856.25 | 11566.11 | 4290.14 | 37.09% | 0.006982% | 15856.25 | 11566.11 | 4290.14 | 2009-10-01 | 2010-09-30 | 2010-01-14 | 01 | 2010-09-28 | 09
| 050.23495 | 2937.TYRONE.MAGO CONSTRUCTION | INSTALL4200ft OF 6in PE FOR MAGO CONSTRUCTION ASPHALT PLANT ON TYRONE ROAD | 163841.76 | 88085.69 | 75756.07 | 86% | 0.07214% | 163841.76 | 88085.69 | 75756.07 | 2009-10-01 | 2010-09-30 | 2010-08-12 | 08 | 2011-02-01 | 02
| 040.10299 | WKG.DAN.SHV.WELD TRUCK | WKG.DAN.SHV.WELD TRUCK | 400 | 55625 | -55625 | -100% | 0% | 0 | 55625 | -55625 | 2009-10-01 | 2010-09-30 | 1999-09-27 | 09 | 2005-05-04 | 05
| 050.23173 | 050.2637.Drawbridge Trace Ext | Install 215' PE for one existing residential customer requesting natural gas | 1175.99 | 1532.49 | -356.5 | -23.26% | 0.0005178% | 1175.99 | 1532.49 | -356.5 | 2009-10-01 | 2010-09-30 | 2010-02-11 | 02 | 2010-03-08 | 03
| 050.23106 | 050.2612.New EFM Equipment | New EFM Equipment For Mahle Franklin,KY, TRAD Hopkinsville,KY,Springview Medical Lebanon,KY | 10649.72 | 11103.74 | -454.02 | -4.089% | 0.004689% | 10649.72 | 11103.74 | -454.02 | 2009-10-01 | 2010-09-30 | 2010-01-08 | 01 | 2010-09-28 | 09
| 050.23126 | 2739.LAW.PARKWOOD GARDEN 10 | INSTALL 200ft OF 2in PE FOR LOT 1 AND 14 IN SCENIC GARDEN - LAWRENCEBURG | 937 | 3079.16 | -2142.16 | -69.57% | 0.0004126% | 937 | 3079.16 | -2142.16 | 2009-10-01 | 2010-09-30 | 2010-01-22 | 01 | 2010-12-01 | 12
| 050.21902 | 2738.LEB.COMMERCE DR | 550' OF 4" PE FOR FUEL TOTAL SYS | -7619.67 | 9085 | -16601.95 | -182.7% | -0.00331% | -7516.95 | 9085 | -16601.95 | 2009-10-01 | 2010-09-30 | 2009-03-02 | 03 | 2010-03-02 | 03
| 050.21849 | 050.2636.Habit 12" | Rework Habit Station | 3708.05 | 22621.54 | 2782.2 | 12.3% | 0.01119% | 25403.74 | 22621.54 | 2782.2 | 2009-10-01 | 2010-09-30 | 2009-02-03 | 02 | 2009-07-01 | 07
| 040.11172 | wkg.dan.ret case trencher - DW | retire case trencher - DITCH WITCH 2310W 156958 | 2554.27 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2001-10-17 | 10 | 2005-05-04 | 05
| 050.21067 | Glasgow 09 Non Growth | Glasgow 09 Non Growth | 4623.03 | Not Budgeted |  |  | 0.1956% | 444307.23 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.20447 | 050.HOPK.HWY 41 RELOC. | HWY 41 8" & 6" RELOC. - HOPKINSVILLE | -51455 | 11486 | 232382.65 | 2023% | 0.1074% | 243868.65 | 11486 | 232382.65 | 2009-10-01 | 2010-09-30 | 2008-02-06 | 02 | 2009-02-06 | 02
| 050.22437 | 050.KY.OboroLeakFunct2010 | 050.KY.OboroLeakFunct2010 | 589947.93 | Not Budgeted |  |  | 0.2721% | 618054.54 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23144 | 050.2612.107 Flow Boss | 107 Flow Boss For Bench Testing | 9085.93 | 9587.98 | -502.05 | -5.236% | 0.004001% | 9085.93 | 9587.98 | -502.05 | 2009-10-01 | 2010-09-30 | 2010-01-28 | 01 | 2010-09-30 | 09
| 040.11704 | 040.DAN.SHV.VEH RETIRE #6920 | RETIRE VEHICLE #6920 | 2448.77 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-03-04 | 03 | 2005-05-04 | 05
| 040.11918 | 040.CAM.CENTRAL AVE - REPLACE | REPLACE 2000' OF 4" STEEL WITH 4" PE ON CENTRAL AVE FROM WALNUT TO LINCOLN | -505.53 | 101300 | -101300 | -100% | 0% | 0 | 101300 | -101300 | 2009-10-01 | 2010-09-30 | 2003-09-02 | 09 | 2005-05-04 | 05
| 050.23157 | 050.2737.TDWILLIAMSON EQUIP | PURCHASE TD WILLIAMSON 2" AND 4" PLUGGING MACHINES - EXISTING UNITS ARE NOT SAFE AND WE NEED TO UPDATE TO THE NEW EQUIPMENT FOR EMPLOYEE SAFTY. | 32995.13 | 9923.36 | 23071.77 | 232.5% | 0.01453% | 32995.13 | 9923.36 | 23071.77 | 2009-10-01 | 2010-09-30 | 2010-02-05 | 02 | 2010-07-30 | 07
| 050.23189 | 2737.STAN.HILLTOPPER 10 | INSTALL 200ft OF 2in PE ON HILLTOPPER ACROSS HUBLE | 5222.53 | 4391.05 | 831.48 | 18.94% | 0.002299% | 5222.53 | 4391.05 | 831.48 | 2009-10-01 | 2010-09-30 | 2010-02-17 | 02 | 2011-02-04 | 02
| 050.23186 | 050.2635.Fusion Equipment | Purchase Fusion Equipment | 9091.5 | 8899.46 | 192.04 | 2.158% | 0.004003% | 9091.5 | 8899.46 | 192.04 | 2009-10-01 | 2010-09-30 | 2010-02-17 | 02 | 2010-09-28 | 09
| 050.23150 | 050.2739.WALKER LANE FENCE | INSTALL FENCE AROUND THE REGULATOR STATION ON WALKER LANE IN LAWRENCEBURG, KENTUCKY | 41083.7 | 20540 | 20543.7 | 100% | 0.01809% | 41083.7 | 20540 | 20543.7 | 2009-10-01 | 2010-09-30 | 2010-02-01 | 02 | 2010-12-01 | 12
| 050.22194 | 050.2734.Covington Replc. | 050.2734.Covington Bare Steel Replc. | 3193.6 | 113411.92 | -24353.22 | -21.47% | 0.03921% | 89058.7 | 113411.92 | -24353.22 | 2009-10-01 | 2010-09-30 | 2009-07-30 | 07 | 2009-09-25 | 09
| 050.22195 | 050.009.2734.TB3Replacement | TB 3 relocation in cojunction with Highland Way Replacement | 11935.47 | 50336.17 | -420.41 | -0.8352% | 0.02198% | 49915.76 | 50336.17 | -420.41 | 2009-10-01 | 2010-09-30 | 2009-07-30 | 07 | 2009-09-28 | 09
| 050.23291 | 2739.HUDSON BLVD.HI POINT IN | INSTALL 297ft OF 4in PE AROUND CUL-DE-SAK ON HUDSON BLVD FOR HUMANE SOCIETY | 1380.68 | 4045.71 | -2665.03 | -65.87% | 0.0006079% | 1380.68 | 4045.71 | -2665.03 | 2009-10-01 | 2010-09-30 | 2010-04-20 | 04 | 2010-10-01 | 10
| 050.23249 | 050.2634.Locators and Mole | Purchase 2 locators and Mole | 8587.48 | 3505.18 | 5082.3 | 145% | 0.003781% | 8587.48 | 3505.18 | 5082.3 | 2009-10-01 | 2010-09-30 | 2010-03-26 | 03 | 2010-09-28 | 09
| 050.22359 | 050.KY.PrincetnGrowthFunct2010 | 050.KY.PrincetnGrowthFunct2010 | 111139.68 | Not Budgeted |  |  | 0.04923% | 111817.69 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22144 | TchSvr.Mea.EFM-BR Retread | EFM for BR Retreading in Glasgow, KY | 80.88 | 4140 | -1028.21 | -24.84% | 0.00137% | 3111.79 | 4140 | -1028.21 | 2009-10-01 | 2010-09-30 | 2009-07-06 | 07 | 2009-09-30 | 09
| 050.20231 | 050.HOP.NEW TOWN STATION | 1260 FT. OF 4" PE - NEW TOWN STATION - HOPK. | -11586.17 | 3626 | -3626 | -100% | 0% | 0 | 3626 | -3626 | 2009-10-01 | 2010-09-30 | 2007-10-19 | 10 | 2008-10-18 | 10
| 050.22508 | 2738.CVILLE WAREHOUSE ROOF | INSTALL NEW ROOF ON WAREHOUSE IN CAMPBELLSVILLE - STORM DAMAGE | 9662.1 | 19566.92 | -9904.82 | -50.62% | 0.004254% | 9662.1 | 19566.92 | -9904.82 | 2009-10-01 | 2010-09-30 | 2009-10-12 | 10 | 2010-02-01 | 02
| 050.23032 | 050.2636.Western Ave. | Relocate approximately 319 feet 2 Inch Stl. | 10299.12 | 7066.76 | 3232.36 | 45.74% | 0.004535% | 10299.12 | 7066.76 | 3232.36 | 2009-10-01 | 2010-09-30 | 2009-11-18 | 11 | 2010-01-29 | 01
| 050.23327 | 050.2636.Bruce School Rd. | Install 100 ft 2 Inch PE | 2302.06 | 2148.97 | 153.09 | 7.124% | 0.001014% | 2302.06 | 2148.97 | 153.09 | 2009-10-01 | 2010-09-30 | 2010-05-11 | 05 | 2010-09-28 | 09
| 050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 651.04 | Not Budgeted |  |  | 0.0002867% | 651.04 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24173 | 050.2636.Electro Fuse Eq. | Purchase Electro Fuse Equipment | 10765.14 | 11441.38 | -676.24 | -5.91% | 0.00474% | 10765.14 | 11441.38 | -676.24 | 2009-10-01 | 2010-09-30 | 2010-09-27 | 09 | 2010-09-30 | 09
| 050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 7508.08 | Not Budgeted |  |  | 0.003306% | 7508.08 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 185.03 | Not Budgeted |  |  | 8.147e-05% | 185.03 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.23838 | MadisonvilleIntegRegs | Madisonville Non Growth Regs | 1141.5 | Not Budgeted |  |  | 0.0005026% | 1141.5 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22991 | 050.2734.Louisville Rd. Ext. | Louisville Rd. 4 Inch Extension | 8296.7 | -3316 | 11612.7 | -350.2% | 0.003653% | 8296.7 | -3316 | 11612.7 | 2009-10-01 | 2010-09-30 | 2009-11-07 | 11 | 2010-09-28 | 09
| 050.22108 | 050.2737.HUSTONVILLE TBS | REBUILD HUSTONVILLE TBS - TENNESSEE GAS TO CHANGE REGULATION AND WE NEED TO ADD REGULATOR RUN WITH GAS HEATER AND FILTRATION | 23798.25 | 122382 | -41744.74 | -34.11% | 0.0355% | 80637.26 | 122382 | -41744.74 | 2009-10-01 | 2010-09-30 | 2009-06-18 | 06 | 2009-10-01 | 10
| 050.23055 | 050.2636.Vincent Station Dr. | Install 360 Feet 2 Inch PE | 1547.29 | 1262.01 | 285.28 | 22.61% | 0.0006813% | 1547.29 | 1262.01 | 285.28 | 2009-10-01 | 2010-09-30 | 2009-12-08 | 12 | 2010-01-29 | 01
| 050.23313 | 2737.BURGIN.LEAK.HWY 152-33 | REPLACE 500ft OF 2in STEEL WITH 2in PE FOR REPAIRING 3 LEAKS AND EASEMENT ENCROACHMENT | 67296.72 | 32791.75 | 34504.97 | 105.2% | 0.02963% | 67296.72 | 32791.75 | 34504.97 | 2009-10-01 | 2010-09-30 | 2010-05-04 | 05 | 2011-03-05 | 03
| 050.23560 | 050.2636.Insulators & Anodes | Retire ground bed & rectifier at Legion Park. Install insulators at Legion Blvd.& Warwick Dr. with Anodes | 17818.81 | 45777.27 | -27958.46 | -61.07% | 0.007846% | 17818.81 | 45777.27 | -27958.46 | 2009-10-01 | 2010-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23266 | 050.2634.Hwy 62 Replacement | Replace exposed 2 Inch Steel with 2 Inch PE | 12701.47 | 11895.61 | 805.86 | 6.774% | 0.005592% | 12701.47 | 11895.61 | 805.86 | 2009-10-01 | 2010-09-30 | 2010-04-06 | 04 | 2010-09-28 | 09
| 050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 6691.44 | Not Budgeted |  |  | 0.002946% | 6691.44 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23239 | 050.2602.MDTs 2 2010 | Purchase MTDs | 79079.48 | 149280.14 | -70200.66 | -47.03% | 0.03482% | 79079.48 | 149280.14 | -70200.66 | 2009-10-01 | 2010-09-30 | 2010-03-18 | 03 | 2010-09-28 | 09
| 050.23443 | 050.2636.Verden St. Retire | Retire 1.25 leaking Stl. main not in use | 521.55 | 1782.72 | -1261.17 | -70.74% | 0.0002296% | 521.55 | 1782.72 | -1261.17 | 2009-10-01 | 2010-09-30 | 2010-07-09 | 07 | 2010-09-28 | 09
| 050.22241 | TchSvr.Mea.EFM.Spec. Rock Prod | EFM for Specialty Rock Products, Inc. | 294.61 | 4140 | -766.74 | -18.52% | 0.001485% | 3373.26 | 4140 | -766.74 | 2009-10-01 | 2010-09-30 | 2009-08-18 | 08 | 2009-09-30 | 09
| 050.20899 | 050.2636.Fordsville TB Rplmnt. | Replace Fordsville TB Station | 13509.93 | 33631.34 | 635.79 | 1.89% | 0.01509% | 34267.13 | 33631.34 | 635.79 | 2009-10-01 | 2010-09-30 | 2008-08-25 | 08 | 2010-07-01 | 07
| 050.23535 | 050.2609.Storage Misc. | Replace Safety Shut Offs and Install Methanol Injectors | 51638.78 | 113968.24 | -62329.46 | -54.69% | 0.02274% | 51638.78 | 113968.24 | -62329.46 | 2009-10-01 | 2010-09-30 | 2010-08-27 | 08 | 2010-09-28 | 09
| 050.22353 | 050.KY.GlasgowGrowthFunct2010 | 050.KY.GlasgowGrowthFunct2010 | 83459.6 | Not Budgeted |  |  | 0.03692% | 83860.48 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23142 | 050.2612.Replacement EFM | Replacement EFM Equipment | 9456.17 | 5951.16 | 3505.01 | 58.9% | 0.004164% | 9456.17 | 5951.16 | 3505.01 | 2009-10-01 | 2010-09-30 | 2010-01-27 | 01 | 2010-09-30 | 09
| 050.21748 | 050.2637.New Holt Rd Rev Ext | Install 675' - 2" PE for new Montgomery Gardens greenhouse | 1386 | 1848 | -689.92 | -37.33% | 0.0005099% | 1158.08 | 1848 | -689.92 | 2009-10-01 | 2010-09-30 | 2008-12-05 | 12 | 2009-09-18 | 09
| 050.23394 | 050.2637.Cumberland Rd Ext | Install 140 feet of 2 inch pe pipe | 1115.89 | 1699.15 | -583.26 | -34.33% | 0.0004913% | 1115.89 | 1699.15 | -583.26 | 2009-10-01 | 2010-09-30 | 2010-06-17 | 06 | 2009-12-10 | 12
| 050.22226 | 2739.SUPERVISOR FURNITURE | OFFICE FURNITURE FOR OPERATIONS SUPERVISOR | 714.49 | 3917.5 | 1137.78 | 29.04% | 0.002226% | 5055.28 | 3917.5 | 1137.78 | 2009-10-01 | 2010-09-30 | 2009-08-12 | 08 | 2009-09-30 | 09
| 050.23225 | 050.2637.Gas Tracker | We would like to purchase this Gas Tracker non-Metallic pipe locator for use in the greater Paducah area. | 32542.96 | 23143.05 | 9399.91 | 40.62% | 0.01433% | 32542.96 | 23143.05 | 9399.91 | 2009-10-01 | 2010-09-30 | 2010-03-08 | 03 | 2010-05-21 | 05
| 050.21750 | 050.2637.Brookhaven III | 525' - 2" PE revenue extension for three new lots in Brookhaven subd | 988 | 1481.2 | 534.35 | 36.08% | 0.0008875% | 2015.55 | 1481.2 | 534.35 | 2009-10-01 | 2010-09-30 | 2008-12-08 | 12 | 2009-09-30 | 09
| 050.23111 | 050.2637.Light Pkg Pandolfi | This project is to capture the costs of a new light package for David Pandolfi new 2010 Ford vehicle. Package includes a remote control spotlight to be purchased from Emergency Equipment Specialist in Paducah, KY. | 1712.34 | 1047.62 | 664.72 | 63.45% | 0.0007539% | 1712.34 | 1047.62 | 664.72 | 2009-10-01 | 2010-09-30 | 2010-01-12 | 01 | 2010-01-29 | 01
| 050.23449 | 050.2637.Princess Jennifer | Install 200 feet of 2 inch poly pipe for two new residential customers requesting gas service | 1451.59 | 1897.36 | -445.77 | -23.49% | 0.0006391% | 1451.59 | 1897.36 | -445.77 | 2009-10-01 | 2010-09-30 | 2010-07-12 | 07 | 2010-09-28 | 09
| 050.21949 | 050.2602 Replace Phone Syst | Replace Dated Phone System | 863.24 | 84177.44 | -67436.23 | -80.11% | 0.007371% | 16741.21 | 84177.44 | -67436.23 | 2009-10-01 | 2010-09-30 | 2009-03-24 | 03 | 2009-09-01 | 09
| 040.10597 | RETIRE CASE BACKHOE # 5117 | 1981 CASE 480 BACKHOE | -44.19 | -1000 | 1000 | -100% | 0% | 0 | -1000 | 1000 | 2009-10-01 | 2010-09-30 | 2000-07-05 | 07 | 2005-05-04 | 05
| 050.21066 | Glasgow 09 Growth | Glasgow 09 Growth | 813.5 | Not Budgeted |  |  | 0.04804% | 109109.42 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23268 | 050.2636.Install Mooney Pilots | Install Mooney Pilots Commonwealth Purchase Wescore Purchase Dart Polymer TB 4 and Mosleyville Purchase | 6546.97 | 10670.88 | -4123.91 | -38.65% | 0.002883% | 6546.97 | 10670.88 | -4123.91 | 2009-10-01 | 2010-09-30 | 2010-04-07 | 04 | 2010-09-28 | 09
| 050.23333 | 050.2637.Benton Rd Replacemen | Replace 2" steel damaged by third party | -4901.29 | 4442.05 | -9343.34 | -210.3% | -0.002158% | -4901.29 | 4442.05 | -9343.34 | 2009-10-01 | 2010-09-30 | 2010-05-13 | 05 | 2010-06-29 | 06
| 050.20926 | 050.2609.Bon Harbor Well #2 | Workover Bon Harbor Well #2 | 84722.04 | 150302.01 | -3303.28 | -2.198% | 0.06472% | 146998.73 | 150302.01 | -3303.28 | 2009-10-01 | 2010-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.22023 | 050.2737.BARRACADE INSTALL | INSTALL BARRACADES AT THREE STATIONS. PERRYVILLE PURCHASE STATION, PERRYVILLE TBS AND STANFORD ROAD STATION | 798.03 | 8465.26 | 2167.69 | 25.61% | 0.004682% | 10632.95 | 8465.26 | 2167.69 | 2009-10-01 | 2010-09-30 | 2009-05-11 | 05 | 2009-10-01 | 10
| 050.23091 | 040.009.2737Retirements | Old 040 projects transferred to 050 | -1270.93 | 1 | -1271.93 | -127193% | -0.0005596% | -1270.93 | 1 | -1271.93 | 2009-10-01 | 2010-09-30 | 2009-12-30 | 12 | 2010-12-30 | 12
| 040.11850 | 040.DAN.SHV.151-127 2" ST RELO | RELOCATE 120' OF 2" STEEL WITH 2" PE AT 151&127 | -461.25 | 2905 | -2905 | -100% | 0% | 0 | 2905 | -2905 | 2009-10-01 | 2010-09-30 | 2003-07-03 | 07 | 2005-05-04 | 05
| 050.23160 | 050.2612.Portable ERX | Portable ERX dual Pressure | 4063.49 | 4959.3 | -895.81 | -18.06% | 0.001789% | 4063.49 | 4959.3 | -895.81 | 2009-10-01 | 2010-09-30 | 2010-02-05 | 02 | 2010-09-30 | 09
| 050.22282 | 2737.HAR.472 N MAIN REPLACE | REPLACE 15ft OF 4in STEEL AT 472 NORTH MAIN IN HARRODSBURG, KY | 10526.84 | 3601.87 | 10701.92 | 297.1% | 0.006298% | 14303.79 | 3601.87 | 10701.92 | 2009-10-01 | 2010-09-30 | 2009-08-25 | 08 | 2009-10-01 | 10
| 050.22202 | TchSvr.Mea.EFM Pinelake Med | EFM for Pinelake Medical Center | 200.48 | 4140 | -3168.22 | -76.53% | 0.0004279% | 971.78 | 4140 | -3168.22 | 2009-10-01 | 2010-09-30 | 2009-08-03 | 08 | 2009-09-30 | 09
| 050.23265 | 050.2638.Pipehorn Locator | We would like to purchase a new Pipehorn pipe locator model MD840 for use in the Mayfield area. | 2173.54 | 1896.24 | 277.3 | 14.62% | 0.000957% | 2173.54 | 1896.24 | 277.3 | 2009-10-01 | 2010-09-30 | 2010-04-05 | 04 | 2010-08-18 | 08
| 050.23343 | 050.2637.Safety Stopper | We would like to purchase Safety Stopper equipment. This equipment would allow us to safely work with "home made" service tees. | 12359.07 | 10739.77 | 1619.3 | 15.08% | 0.005442% | 12359.07 | 10739.77 | 1619.3 | 2009-10-01 | 2010-09-30 | 2010-05-20 | 05 | 2010-07-20 | 07
| 050.23176 | 050.2635.ERX Recorders | Purchase 4 ERX800 Electronic recorders | 8682.16 | 7296.78 | 1385.38 | 18.99% | 0.003823% | 8682.16 | 7296.78 | 1385.38 | 2009-10-01 | 2010-09-30 | 2010-02-11 | 02 | 2010-09-28 | 09
| 050.22360 | 050.KY.OboroGrowthFunct2010 | 050.KY.OboroGrowthFunct2010 | 442047.95 | Not Budgeted |  |  | 0.1966% | 446552.25 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23430 | 050.2734 Traditions Ext | 2 inch PE Extension - Traditions Alley 6 | 1797.07 | 3449.74 | -1652.67 | -47.91% | 0.0007913% | 1797.07 | 3449.74 | -1652.67 | 2009-10-01 | 2010-09-30 | 2010-06-25 | 06 | 2010-09-28 | 09
| 050.22436 | 050.KY.PrincetonLeakFunct2010 | 050.KY.PrincetonLeakFunct2010 | 134369.93 | Not Budgeted |  |  | 0.05965% | 135481.38 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23349 | 050.2637.Refrigerator | Purchase of a new refrigerator for use in our warehouse. | 1513.19 | 1493.1 | 20.09 | 1.346% | 0.0006663% | 1513.19 | 1493.1 | 20.09 | 2009-10-01 | 2010-09-30 | 2010-05-24 | 05 | 2010-09-21 | 09
| 050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 171.16 | Not Budgeted |  |  | 7.536e-05% | 171.16 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.24121 | 050.2637.E.F Equip II | Electro fuse equipment for use in the Paducah area. | 9381.53 | 9166.96 | 214.57 | 2.341% | 0.004131% | 9381.53 | 9166.96 | 214.57 | 2009-10-01 | 2010-09-30 | 2010-09-21 | 09 | 2010-09-30 | 09
| 050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 4318.01 | Not Budgeted |  |  | 0.001901% | 4318.01 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22242 | TchSvr.Mea.EFM.Daicel Safety | EFM for Daicel Safety Technologie | 205.69 | 4140 | -855.66 | -20.67% | 0.001446% | 3284.34 | 4140 | -855.66 | 2009-10-01 | 2010-09-30 | 2009-08-18 | 08 | 2009-09-30 | 09
| 050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 28.42 | Not Budgeted |  |  | 1.251e-05% | 28.42 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.19601 | Madisonville 08 Non Growth | Madisonville 08 Non Growth | -104.97 | Not Budgeted |  |  | 0.2151% | 488616.64 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.22180 | TchSvr.Mea.EFM for Dart #9 | EFM For Dart Container Building #9 | 95.44 | 4140 | -853.58 | -20.62% | 0.001447% | 3286.42 | 4140 | -853.58 | 2009-10-01 | 2010-09-30 | 2009-07-22 | 07 | 2009-09-30 | 09
| 050.20922 | 050.2609.Bon Harbor Well #1 | Workover Well # 1 Bon Harbor | 252133.97 | 316705.87 | -7037.16 | -2.222% | 0.1363% | 309668.71 | 316705.87 | -7037.16 | 2009-10-01 | 2010-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.20483 | 050.2609.Bon Harbor Well # 5 | Workover Bon Harbor Well # 5 | 2477.33 | 183203.93 | 31142.43 | 17% | 0.09438% | 214346.36 | 183203.93 | 31142.43 | 2009-10-01 | 2010-09-30 | 2008-02-20 | 02 | 2009-08-01 | 08
| 050.23380 | 050.2637.Shed Insulation | Insulation to be used for our recently remodeled shed on th lot at 3034 Parker St. | 2888.47 | 2660.62 | 227.85 | 8.564% | 0.001272% | 2888.47 | 2660.62 | 227.85 | 2009-10-01 | 2010-09-30 | 2010-06-09 | 06 | 2010-09-24 | 09
| 050.23311 | 050.2637.Kerth Rd Mian Ext | Install 95 feet of 2 inch poly for one existing residential customer requesting gas. | 130.9 | 1014.7 | -883.8 | -87.1% | 5.764e-05% | 130.9 | 1014.7 | -883.8 | 2009-10-01 | 2010-09-30 | 2010-05-03 | 05 | 2010-09-30 | 09
| 050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 1340.43 | Not Budgeted |  |  | 0.0005902% | 1340.43 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23561 | 050.2636.Short Sta. Rd. Relo. | Relocate 655ft 2 Inch PE for roadway work | 2875.1 | 7061.43 | -4186.33 | -59.28% | 0.001266% | 2875.1 | 7061.43 | -4186.33 | 2009-10-01 | 2010-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23136 | 050.2634.Countryview Boiler | Install Boiler at Countryview | 31488.25 | 38196.56 | -6708.31 | -17.56% | 0.01386% | 31488.25 | 38196.56 | -6708.31 | 2009-10-01 | 2010-09-30 | 2010-01-26 | 01 | 2010-09-28 | 09
| 050.23393 | 050.2636.Station Buildings | Purchase Buildings for Mosleyville station Beaver Dam Purchase and Hickory Storage Field. | 20394.53 | 22440.3 | -2045.77 | -9.117% | 0.00898% | 20394.53 | 22440.3 | -2045.77 | 2009-10-01 | 2010-09-30 | 2010-06-16 | 06 | 2010-09-28 | 09
| 050.22429 | 050.KY.BowlGrnLeakFunct2010 | 050.KY.BowlGrnLeakFunct2010 | 893685.5 | Not Budgeted |  |  | 0.4645% | 1054909.12 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23436 | 050.2736.Marietta Dr. Rplmnt. | Replace 4 Inch Stl. Due to Bridge Replacement | 88423.53 | 96531.05 | -8107.52 | -8.399% | 0.03893% | 88423.53 | 96531.05 | -8107.52 | 2009-10-01 | 2010-09-30 | 2010-07-06 | 07 | 2010-09-28 | 09
| 050.22199 | 050.2634.Franklin St Reg | Relocate Franklin St. Reg. Sta. | 19199.73 | 37.45 | -10379.06 | -27714% | -0.004553% | -10341.61 | 37.45 | -10379.06 | 2009-10-01 | 2010-09-30 | 2009-08-03 | 08 | 2009-09-28 | 09
| 050.22213 | 050.2637.Derby Cr Rev Ext | Install 180 feet of 2 inch PE for one new and one vacant residential | 209.39 | 1580.5 | -1083.5 | -68.55% | 0.0002188% | 497 | 1580.5 | -1083.5 | 2009-10-01 | 2010-09-30 | 2009-08-10 | 08 | 2009-09-28 | 09
| 050.23446 | 050.2637.Bleich Rd Relocation | Lone Oak High School constructing a new access road | 3556.73 | 2968.69 | 588.04 | 19.81% | 0.001566% | 3556.73 | 2968.69 | 588.04 | 2009-10-01 | 2010-09-30 | 2010-07-12 | 07 | 2010-09-28 | 09
| 050.23480 | 050.2637.R.D Locator | Radiodetection model RD8000 universal precision cable and pipe locator for use in the Paducah area. Will be assigned to Richard (Bates) Anderson. | 7630.41 | 7413.24 | 217.17 | 2.929% | 0.00336% | 7630.41 | 7413.24 | 217.17 | 2009-10-01 | 2010-09-30 | 2010-08-02 | 08 | 2010-09-28 | 09
| 040.11698 | 040.DAN.CAM.VEH RETIRE #6904 | RETIRE VEHICLE #6904 | 2781.97 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-03-03 | 03 | 2005-05-04 | 05
| 040.10193 | WKG.DAN.LEB.COURTSQUARE | RELOCATE 240' 2" PE PIPE | -1887.59 | 10569 | -10569 | -100% | 0% | 0 | 10569 | -10569 | 2009-10-01 | 2010-09-30 | 1999-07-21 | 07 | 2005-05-04 | 05
| 050.21530 | TchSvr.Mea.Meters-Large Volume | Large Volume Meters for Replacement of Damage Meters | 207.9 | 23435 | 18073.54 | 77.12% | 0.01828% | 41508.54 | 23435 | 18073.54 | 2009-10-01 | 2010-09-30 | 2008-10-15 | 10 | 2009-09-30 | 09
| 040.10972 | WKG.DAN.CAM.COLLEGE ST REP. | REPLACE 300' OF BARE 4" WITH 2" PE | -3.2 | 3561 | -3561 | -100% | 0% | 0 | 3561 | -3561 | 2009-10-01 | 2010-09-30 | 2001-06-18 | 06 | 2005-05-04 | 05
| 050.21064 | Bowling Green 09 Growth | Bowling Green 09 Growth | 6694.48 | Not Budgeted |  |  | 0.3103% | 704640.57 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21065 | Bowling Green 09 Non Growth | Bowling Green 09 Non Growth | 10379.04 | Not Budgeted |  |  | 0.7149% | 1623556.01 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21068 | Hopkinsville 09 Growth | Hopkinsville 09 Growth | 966.14 | Not Budgeted |  |  | 0.05483% | 124530.48 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23120 | 050.2737.EMERGENCY GENERATOR | EMERGENCY GENERATOR FOR TRAILER | 4506.58 | 8742.12 | -4235.54 | -48.45% | 0.001984% | 4506.58 | 8742.12 | -4235.54 | 2009-10-01 | 2010-09-30 | 2010-01-19 | 01 | 2010-12-01 | 12
| 050.23275 | 050.2637.Hwy 282 Replacement | Replace 500 feet of 4 inch steel with 500 feet of 4 inch plastic | 15282.92 | 11610.64 | 3672.28 | 31.63% | 0.006729% | 15282.92 | 11610.64 | 3672.28 | 2009-10-01 | 2010-09-30 | 2010-04-09 | 04 | 2010-05-28 | 05
| 050.19596 | Campbellsville 08 Growth | Campbellsville 08 Growth | -50.28 | Not Budgeted |  |  | 0.03527% | 80114.8 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23489 | 050.2636.London Pike Spur | Install 100 Ft 2 Inch PE | 263.15 | 3107.03 | -2843.88 | -91.53% | 0.0001159% | 263.15 | 3107.03 | -2843.88 | 2009-10-01 | 2010-09-30 | 2010-08-05 | 08 | 2010-09-28 | 09
| 050.23490 | 050.2636.Pro Park Dr. Reloc. | Relocate 2 Inch PE for new Street | 371.44 | 1547.41 | -1175.97 | -76% | 0.0001635% | 371.44 | 1547.41 | -1175.97 | 2009-10-01 | 2010-09-30 | 2010-08-05 | 08 | 2010-09-28 | 09
| 050.22971 | 050.2636.High Pass Pointe | Install 2" PE in Heartland Sub. | 9273.51 | 6882.26 | 2391.25 | 34.75% | 0.004083% | 9273.51 | 6882.26 | 2391.25 | 2009-10-01 | 2010-09-30 | 2009-10-26 | 10 | 2009-12-25 | 12
| 050.23000 | 050.2602.Desktop/Lap tops 2010 | Replace dated Desktops and lap tops | 69883.39 | 82655 | -12771.61 | -15.45% | 0.03077% | 69883.39 | 82655 | -12771.61 | 2009-10-01 | 2010-09-30 | 2009-11-12 | 11 | 2010-09-28 | 09
| 040.11980 | 040.CAM.LEB.VA CEM RELOC | RELOCATE 120' OF 4" STEEL WITH 4" PE AT VA CEMETERY - LEBANON | -916.02 | 3501 | -3501 | -100% | 0% | 0 | 3501 | -3501 | 2009-10-01 | 2010-09-30 | 2003-10-16 | 10 | 2005-05-04 | 05
| 040.12156 | 040.SHV.LAW.WALKER LN-4" ST HP | RELOCATE 300' OF 4" HIGH PRESURE STEEL ON WALKER LANE | -1189.98 | 16500 | -16500 | -100% | 0% | 0 | 16500 | -16500 | 2009-10-01 | 2010-09-30 | 2004-04-05 | 04 | 2005-05-04 | 05
| 050.23357 | 050.2736.Burley Ave. | Install 580 feet 2 Inch PE | 2696.9 | 4529.24 | -1832.34 | -40.46% | 0.001187% | 2696.9 | 4529.24 | -1832.34 | 2009-10-01 | 2010-09-30 | 2010-05-28 | 05 | 2009-12-31 | 12
| 050.23122 | 2 inch PE Ext. - Northridge V | 2 inch PE Extension - Northrigde V - Bowling Green | 5560.29 | 7861.9 | -2301.61 | -29.28% | 0.002448% | 5560.29 | 7861.9 | -2301.61 | 2009-10-01 | 2010-09-30 | 2010-01-20 | 01 | 2010-09-28 | 09
| 050.23358 | 050.2618.Misc.Equipment | Purchase misc. equipment Respirator, Respirator test kit, Shoring Box End Panels. | 29499.11 | 31975.51 | -2476.4 | -7.745% | 0.01299% | 29499.11 | 31975.51 | -2476.4 | 2009-10-01 | 2010-09-30 | 2010-06-01 | 06 | 2010-09-28 | 09
| 050.23563 | 050.2637.Locator - Young | This project is for new model 840 Pipehorn pipe locator to be assigned to Mike Young for use in the Paducah area. | 1695.64 | 1896.24 | -200.6 | -10.58% | 0.0007466% | 1695.64 | 1896.24 | -200.6 | 2009-10-01 | 2010-09-30 | 2010-09-08 | 09 | 2010-09-28 | 09
| 050.22355 | 050.KY.DanvilleGrowthFunct2010 | 050.KY.DanvilleGrowthFunct2010 | 174538.15 | Not Budgeted |  |  | 0.07993% | 181526.94 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22358 | 050.KY.MadisonGrowthFunct2010 | 050.KY.MadisonGrowthFunct2010 | 212029.7 | Not Budgeted |  |  | 0.09464% | 214937.43 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22207 | 050.2734.4 in Wn Gate Valves | Replace two 4 inch Williamson gate valves, Bowling Green | 1176.53 | 28832.8 | -937.88 | -3.253% | 0.01228% | 27894.92 | 28832.8 | -937.88 | 2009-10-01 | 2010-09-30 | 2009-08-06 | 08 | 2009-09-29 | 09
| 050.22146 | 050.2637.Star Hill Dr Rev Ext | Install 460 feet of 2 inch plastic main for one new residential customer | 228.43 | 749.92 | -19.11 | -2.548% | 0.0003218% | 730.81 | 749.92 | -19.11 | 2009-10-01 | 2010-09-30 | 2009-07-06 | 07 | 2009-09-28 | 09
| 050.22149 | 2738.N FOREST REPLACEMENT | REPLACE STEEL MAIN ON NORTH FOREST BETWEEN HOOD AND BOLDRICK | 9462.39 | 84801.69 | 29957.09 | 35.33% | 0.05053% | 114758.78 | 84801.69 | 29957.09 | 2009-10-01 | 2010-09-30 | 2009-07-07 | 07 | 2010-06-01 | 06
| 050.23413 | 050.2734.Misc Equip | 050.2734.Misc Equip | 8307.66 | 11198.25 | -2890.59 | -25.81% | 0.003658% | 8307.66 | 11198.25 | -2890.59 | 2009-10-01 | 2010-09-30 | 2010-06-24 | 06 | 2010-09-28 | 09
| 050.22507 | 2738.LEB.HENDRICKSON DR | INSTALL 4in PE ON HENDRICKSON DR FOR NEW WAREHOUSE | 5310.92 | -365.02 | 5675.94 | -1555% | 0.002338% | 5310.92 | -365.02 | 5675.94 | 2009-10-01 | 2010-09-30 | 2009-10-12 | 10 | 2010-08-26 | 08
| 050.22238 | 050.2635.Hwy 68 | Install 1600 feet 2" PE | 655.17 | 384.63 | -1127.88 | -293.2% | -0.0003273% | -743.25 | 384.63 | -1127.88 | 2009-10-01 | 2010-09-30 | 2009-08-14 | 08 | 2009-09-28 | 09
| 050.23206 | 050.2636.Holland Dr. Outage | Replace 12 feet 2 Inch PE and capture cost from outage. | 2197.13 | 9167.16 | -6970.03 | -76.03% | 0.0009674% | 2197.13 | 9167.16 | -6970.03 | 2009-10-01 | 2010-09-30 | 2010-02-24 | 02 | 2010-09-28 | 09
| 050.22319 | 050.2602 Replace PCs2 | Replace dated PCs | 27143.77 | 156668.66 | -78860.49 | -50.34% | 0.03426% | 77808.17 | 156668.66 | -78860.49 | 2009-10-01 | 2010-09-30 | 2009-09-08 | 09 | 2009-09-28 | 09
| 050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 149.29 | Not Budgeted |  |  | 6.573e-05% | 149.29 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-11 | 09 | 2010-09-23 | 09
| 050.22990 | 050.2734.10th Replacement | Replace 4 inch bare - E 10th. between Josephine and Bypass | 136205.05 | 60319.32 | 75885.73 | 125.8% | 0.05997% | 136205.05 | 60319.32 | 75885.73 | 2009-10-01 | 2010-09-30 | 2009-11-06 | 11 | 2010-09-28 | 09
| 050.23045 | 050.2734.Beltline 8 | Bowling Green 8 inch System Improvement | 2647284.68 | 5596208.03 | -2948923.35 | -52.7% | 1.166% | 2647284.68 | 5596208.03 | -2948923.35 | 2009-10-01 | 2010-09-30 | 2009-11-30 | 11 | 2010-09-28 | 09
| 050.23040 | Grinstead 4 inch Replc. | 4 inch Bare Steel Replacement, Grinstead Mill Rd. Cave City | 95374.73 | 65984.05 | 29390.68 | 44.54% | 0.04199% | 95374.73 | 65984.05 | 29390.68 | 2009-10-01 | 2010-09-30 | 2009-11-30 | 11 | 2010-09-29 | 09
| 050.23485 | 050.2637.E.F Equip | M.T Deason electro-fuse processor with data printermodel EF-T for use in the Paducah area. | 5080.13 | 5449.81 | -369.68 | -6.783% | 0.002237% | 5080.13 | 5449.81 | -369.68 | 2009-10-01 | 2010-09-30 | 2010-08-03 | 08 | 2010-09-28 | 09
| 050.22166 | TchSvrMeaEFM Circle H Farm | EFM for Circle H Farms in Madisonville | 28.23 | 4140 | -3167.48 | -76.51% | 0.0004282% | 972.52 | 4140 | -3167.48 | 2009-10-01 | 2010-09-30 | 2009-07-14 | 07 | 2009-09-30 | 09
| 050.22033 | EFM for Union City BPI | Replace BPI with EFM and wireless communication at Union City Purchase Stations | 4.62 | 11033 | -10874.14 | -98.56% | 6.995e-05% | 158.86 | 11033 | -10874.14 | 2009-10-01 | 2010-09-30 | 2009-05-18 | 05 | 2009-09-30 | 09
| 050.21967 | TchSvr.Mea.EFM.Estron Chem. | EFM for Estron Chemicals in Calvert City | 80.88 | 4140 | -1528.49 | -36.92% | 0.00115% | 2611.51 | 4140 | -1528.49 | 2009-10-01 | 2010-09-30 | 2009-04-03 | 04 | 2009-09-30 | 09
| 050.24135 | 050.2734.ELECTROFUSE UNITS | 050.2734.ELECTROFUSE UNITS | 46783.18 | 46168.28 | 614.9 | 1.332% | 0.0206% | 46783.18 | 46168.28 | 614.9 | 2009-10-01 | 2010-09-30 | 2010-09-22 | 09 | 2011-09-28 | 09
| 050.22434 | 050.KY.ShelbyvLeakFunct2010 | 050.KY.ShelbyvLeakFunct2010 | 91782.34 | Not Budgeted |  |  | 0.04041% | 91782.34 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23562 | 050.2635.East Dale Ave. | Install 100 ft 2 Inch PE to serve 1 residential customer and extra 134 ft to provide two way feed. | 2780.94 | 3266.95 | -486.01 | -14.88% | 0.001224% | 2780.94 | 3266.95 | -486.01 | 2009-10-01 | 2010-09-30 | 2010-09-07 | 09 | 2010-09-28 | 09
| 050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 621.93 | Not Budgeted |  |  | 0.0002738% | 621.93 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 169.62 | Not Budgeted |  |  | 7.468e-05% | 169.62 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 106.93 | Not Budgeted |  |  | 4.708e-05% | 106.93 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23276 | 050.2636.Replace Heaters,Regs. | Replace Bruest Heaters Big Rivers, Replace regulators Southwire & 5th St Station | 21644.7 | 23750.77 | -2106.07 | -8.867% | 0.00953% | 21644.7 | 23750.77 | -2106.07 | 2009-10-01 | 2010-09-30 | 2010-04-12 | 04 | 2010-09-28 | 09
| 050.23066 | 2738.ROLAND ST | INSTALL 250ft OF 2in PE FOR RELOCATION OF EXISTING METERS ON PRIVATE PROPERTY | 1688.12 | 5812.87 | -4124.75 | -70.96% | 0.0007433% | 1688.12 | 5812.87 | -4124.75 | 2009-10-01 | 2010-09-30 | 2009-12-11 | 12 | 2010-12-11 | 12
| 050.22183 | 2737.LAN.MAYERS CT REPLACE | REPLACED 10' OF 2in STEEL ON MAYERS CT IN LANCASTER | 149.22 | 5132.83 | -2604.94 | -50.75% | 0.001113% | 2527.89 | 5132.83 | -2604.94 | 2009-10-01 | 2010-09-30 | 2009-07-23 | 07 | 2009-10-01 | 10
| 050.19593 | Hopkinsville 08 Non Growth | Hopkinsville 08 Non Growth | -416.37 | Not Budgeted |  |  | 0.1683% | 382303.68 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23105 | 2737.BREATHITT AVE | INSTALL 800ft OF 2in PE FROM ILA AVE TO BREATHITT AVE | 12898.15 | -284.02 | 13182.17 | -4641% | 0.005679% | 12898.15 | -284.02 | 13182.17 | 2009-10-01 | 2010-09-30 | 2010-01-07 | 01 | 2011-01-05 | 01
| 050.23148 | 050.2737.CP TRAILER | PURCHASE TRAILER FOR CP TECHNICIAN. THIS WILL BE FOR EQUIPMENT NEEDED TO INSTALL ANODES. | 5924.2 | 4655.52 | 1268.68 | 27.25% | 0.002608% | 5924.2 | 4655.52 | 1268.68 | 2009-10-01 | 2010-09-30 | 2010-02-01 | 02 | 2010-07-01 | 07
| 050.23348 | 050.2637.Monroe St II Replace | City widening road, if we do not relocate we will be under the ashphalt. Install 750 feet 4 inch pls, retire 750 feet 4 inch steel. 15 services affected. | 30060.73 | 21121.59 | 8939.14 | 42.32% | 0.01324% | 30060.73 | 21121.59 | 8939.14 | 2009-10-01 | 2010-09-30 | 2010-05-24 | 05 | 2010-09-28 | 09
| 050.23140 | 050.2612 I/p Modems a | I/P Modems | 17478.65 | 23143.4 | -5664.75 | -24.48% | 0.007696% | 17478.65 | 23143.4 | -5664.75 | 2009-10-01 | 2010-09-30 | 2010-01-27 | 01 | 2010-09-30 | 09
| 050.23434 | Hopkinsville 10-inch Replacem | Replace 4 Mi of 10 L-90-159 w/ 12" from MP 1.25 to MP 5 | 2099152.94 | 3009467.72 | -910314.78 | -30.25% | 0.9243% | 2099152.94 | 3009467.72 | -910314.78 | 2009-10-01 | 2010-09-30 | 2010-07-01 | 07 | 2010-12-31 | 12
| 040.11692 | 040.CAM.VEHICLE RETIRE #5260 | RETIRE VEHICLE UNIT #5260 | 1390.99 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-02-27 | 02 | 2005-05-04 | 05
| 050.23370 | 2738.CALVARY PURCHASE REBUILD | REBUILD THE CALVARY PURCHASE STATION | 30714.44 | 57532.62 | -26818.18 | -46.61% | 0.01352% | 30714.44 | 57532.62 | -26818.18 | 2009-10-01 | 2010-09-30 | 2010-06-02 | 06 | 2011-05-12 | 05
| 050.21080 | Owensboro 09 Growth | Owensboro 09 Growth | 2064.71 | Not Budgeted |  |  | 0.1806% | 410112.42 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21081 | Owensboro 09 Non Growth | Owensboro 09 Non Growth | 7295.17 | Not Budgeted |  |  | 0.6437% | 1461867.14 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.20764 | 050.2636.Hwy 60 By Pass 1 | Hwy Relocation install 2,516' 4" PE, 246' 8" Stl., 187' 2" PE | -54830.53 | 57691.78 | -15248.26 | -26.43% | 0.01869% | 42443.52 | 57691.78 | -15248.26 | 2009-10-01 | 2010-09-30 | 2008-07-07 | 07 | 2008-09-28 | 09
| 050.23177 | 050.2637.Vulcan Relocation | Move regulator station upstream, relocate 2,200 feet of dist pressure 4" pe pipe that would have been intermediate presure if we hadn't moved station | 138381.22 | 99815.99 | 38565.23 | 38.64% | 0.06093% | 138381.22 | 99815.99 | 38565.23 | 2009-10-01 | 2010-09-30 | 2010-02-12 | 02 | 2010-04-21 | 04
| 050.23139 | 050.2612.I/P modems | I/P Modems | 19683.84 | 23143.4 | -3459.56 | -14.95% | 0.008667% | 19683.84 | 23143.4 | -3459.56 | 2009-10-01 | 2010-09-30 | 2010-01-27 | 01 | 2010-09-30 | 09
| 040.11290 | WKG.DAN.CAM.VEHIC 5918 RETIRE | RETIRE J. RICHARDSON VEHICLE | 1227.68 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2002-02-07 | 02 | 2005-05-04 | 05
| 040.11660 | WKG.DAN.SHV.VEHICL RETIRE 6903 | RETIRE D. THOMAS TRUCK #6903 | 3523.83 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-01-21 | 01 | 2005-05-04 | 05
| 040.11700 | 040.DAN.CAM.VEH RETIRE #6902 | RETIRE VEHICLE #6902 | 3917.94 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-03-03 | 03 | 2005-05-04 | 05
| 040.11756 | 040.DAN.VEHICLE RETIRE #6561 | RETIRE VEHICLE 6561 VIN 2G1WL52M6S9318219 | 1637.66 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-04-29 | 04 | 2005-05-04 | 05
| 050.23235 | 050.2637.Calvert T.B 2 | Introduce a second feed into Calvert city distribution system from the south, exising feed is from north side of city. | 25140.51 | 18727.55 | 6412.96 | 34.24% | 0.01107% | 25140.51 | 18727.55 | 6412.96 | 2009-10-01 | 2010-09-30 | 2010-03-12 | 03 | 2010-07-16 | 07
| 050.23400 | 050.2636. Summer Walk 2 | Install 1062 ft 2 Inch PE | 5281.17 | 6645.08 | -1363.91 | -20.53% | 0.002325% | 5281.17 | 6645.08 | -1363.91 | 2009-10-01 | 2010-09-30 | 2010-06-21 | 06 | 2010-09-28 | 09
| 050.23282 | 050.2634.Heath Mobile Kit | Purchase mobile kit & trailer for gator | 5876.02 | 7300.27 | -1424.25 | -19.51% | 0.002587% | 5876.02 | 7300.27 | -1424.25 | 2009-10-01 | 2010-09-30 | 2010-04-14 | 04 | 2010-09-28 | 09
| 050.23686 | 2738.SPRNG.LEBANON HILL RD | INSTALL 200ft OF 2in PE FOR CUSTOMER | 193.97 | 986.03 | -792.06 | -80.33% | 8.541e-05% | 193.97 | 986.03 | -792.06 | 2009-10-01 | 2010-09-30 | 2010-09-13 | 09 | 2011-02-01 | 02
| 050.22356 | 050.KY.CampbellGrowthFunct2010 | 050.KY.CampbellGrowthFunct2010 | 110099.51 | Not Budgeted |  |  | 0.04879% | 110812.46 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22392 | 050.KY.GlasgowIntegFunct2010 | 050.KY.GlasgowIntegFunct2010 | 321932.47 | Not Budgeted |  |  | 0.1434% | 325717.71 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22396 | 050.KY.ShelbyviIntegFunct.2010 | 050.KY.ShelbyviIntegFunct.2010 | 193433.57 | Not Budgeted |  |  | 0.09025% | 204976.72 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22400 | 050.KY.PaducahIntegFunct2010 | 050.KY.PaducahIntegFunct2010 | 862313.97 | Not Budgeted |  |  | 0.3877% | 880501.16 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22431 | 050.KY.HopkinsLeakFunct2010 | 050.KY.HopkinsLeakFunct2010 | 71605.46 | Not Budgeted |  |  | 0.03186% | 72366.27 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22145 | 050.2636.River Rd. Lazar | Install 390' 2" Steel Main | 10420.75 | 20398.29 | -4981.5 | -24.42% | 0.006788% | 15416.79 | 20398.29 | -4981.5 | 2009-10-01 | 2010-09-30 | 2009-07-06 | 07 | 2009-09-28 | 09
| 050.21866 | 2739.HWY 60.4 ST REPLACEMENT | REPLACE 360' OF 4" STEEL ON HWY 60 AND MIDLAND BLVD | 769.55 | 15599 | -7558.86 | -48.46% | 0.00354% | 8040.14 | 15599 | -7558.86 | 2009-10-01 | 2010-09-30 | 2009-02-10 | 02 | 2010-02-10 | 02
| 050.23513 | 2739.MEADOW GLEN SEC III | INSTALL IN JOINT TRENCH 2in PE | 81.87 | 8013.63 | -7931.76 | -98.98% | 3.605e-05% | 81.87 | 8013.63 | -7931.76 | 2009-10-01 | 2010-09-30 | 2010-08-16 | 08 | 2010-12-01 | 12
| 050.24073 | MadisonLeakCP/LeakClamps | Madisonville Leak Functional - CP/Leak Clamps | 509.93 | Not Budgeted |  |  | 0.0002245% | 509.93 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24074 | PrincetonLeakCP/LeakClamps | Princeton Leak Functional - CP/Leak Clamps | 278.84 | Not Budgeted |  |  | 0.0001228% | 278.84 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24075 | OboroLeakCP/LeakClamps | Owensboro Leak Functional - CP/Leak Clamps | 2680.88 | Not Budgeted |  |  | 0.00118% | 2680.88 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 187.64 | Not Budgeted |  |  | 8.262e-05% | 187.64 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.23285 | 050.2734.Old Morgantown Replc | 3" Bare Steel Replacement - Old Morgantown Rd.- B.G. | 121068.13 | 87761.8 | 33306.33 | 37.95% | 0.05331% | 121068.13 | 87761.8 | 33306.33 | 2009-10-01 | 2010-09-30 | 2010-04-15 | 04 | 2010-09-28 | 09
| 050.23036 | 050.2734.6 Tapping Equip | 6 Inch TD Williamson Equipment - Bowling Green Area. This is a approved FY2010 Budget Item | 53804.99 | 36193.51 | 17611.48 | 48.66% | 0.02369% | 53804.99 | 36193.51 | 17611.48 | 2009-10-01 | 2010-09-30 | 2009-11-19 | 11 | 2010-01-28 | 01
| 050.22274 | 050.2338.May Reinforcement | Install 12,000 feet 4" HD PE pipe from KT Clay (190 maop) to Dairyman Inc (36 maop) | 99527.4 | 67799.57 | 35523.42 | 52.39% | 0.04549% | 103322.99 | 67799.57 | 35523.42 | 2009-10-01 | 2010-09-30 | 2009-08-24 | 08 | 2009-09-28 | 09
| 050.23185 | 050.3634.Sensit Gold Purchase | Purchase 4 new Sensit Golds, 4 old ones to be traded in. | 6045.38 | 18408.92 | -12363.54 | -67.16% | 0.002662% | 6045.38 | 18408.92 | -12363.54 | 2009-10-01 | 2010-09-30 | 2010-02-16 | 02 | 2010-09-28 | 09
| 050.22992 | 050.2735.Redbird Ext - Adair | 450 ft. - 2 inch PE - Redbird- Adairville | 1461.13 | 3626.46 | -2165.33 | -59.71% | 0.0006433% | 1461.13 | 3626.46 | -2165.33 | 2009-10-01 | 2010-09-30 | 2009-11-07 | 11 | 2010-09-28 | 09
| 050.22502 | 050.2612.REFURB METERS FY10 | CC2612 FY10 Outsourced Meter Retirements & New Meter Purchases | 236680.34 | 226684 | 9996.34 | 4.41% | 0.1042% | 236680.34 | 226684 | 9996.34 | 2009-10-01 | 2010-09-30 | 2009-10-07 | 10 | 2010-09-30 | 09
| 050.19588 | Bowling Green 08 Growth | Bowling Green 08 Growth | -1842.33 | Not Budgeted |  |  | 0.4897% | 1112204.98 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.21777 | 2738.HEATER REPLACE.LEB-CVILLE | REPLACE HEATERS IN CVILLE AND LEBANON WAREHOUSES | 301.51 | 9149 | 1586.92 | 17.35% | 0.004727% | 10735.92 | 9149 | 1586.92 | 2009-10-01 | 2010-09-30 | 2008-12-15 | 12 | 2009-12-12 | 12
| 050.23064 | 050.2637.Mississippi St Ext | Install 255 ft of 2 in poly for one new customer Grand Rivers Fire Dept | -151225.83 | 1095.34 | -152321.17 | -13906% | -0.06659% | -151225.83 | 1095.34 | -152321.17 | 2009-10-01 | 2010-09-30 | 2009-12-10 | 12 | 2009-12-21 | 12
| 050.23193 | 2739.WADDY.BRADSTOWN TRL | INSTALL 600ft OF 2in PE FOR LOVES TRUCK STOP ON BRADSTOWN TRAIL | 27991.61 | 8513.41 | 19478.2 | 228.8% | 0.01232% | 27991.61 | 8513.41 | 19478.2 | 2009-10-01 | 2010-09-30 | 2010-02-19 | 02 | 2011-02-04 | 02
| 050.24107 | 2737.DANVILLE.ELECFUS 2010 | PURCHASE ELECTORFUSION EQUIPMENT FOR DANVILLE TO COMPLY WITH UOC DIRECTIVES | 7057.74 | 6718.95 | 338.79 | 5.042% | 0.003108% | 7057.74 | 6718.95 | 338.79 | 2009-10-01 | 2010-09-30 | 2010-09-20 | 09 | 2010-10-29 | 10
| 050.23537 | 050.2636.Sunrise Dr. Reloc | Relocate 430ft 2 Inch Stl.with 2 Inch PE | 3646.75 | 4580.75 | -934 | -20.39% | 0.001606% | 3646.75 | 4580.75 | -934 | 2009-10-01 | 2010-09-30 | 2010-08-30 | 08 | 2010-09-28 | 09
| 040.10459 | WKG.DAN.LAN.CAMPBELL ST. RET. | RETIRE 580' 2" STEEL PIPE | 3.13 | 406 | -406 | -100% | 0% | 0 | 406 | -406 | 2009-10-01 | 2010-09-30 | 2000-03-02 | 03 | 2005-05-04 | 05
| 050.21963 | 050.2636.Hale Ave.Reg.Sta. | Replace Regulator Station damaged in car accident | 10474.23 | 51834.59 | 7688.76 | 14.83% | 0.02621% | 59523.35 | 51834.59 | 7688.76 | 2009-10-01 | 2010-09-30 | 2009-03-31 | 03 | 2009-08-03 | 08
| 050.22970 | 050.2636.Forest Edge Cove | Install 2 Inch PE | 8963.71 | 7747.76 | 1215.95 | 15.69% | 0.003947% | 8963.71 | 7747.76 | 1215.95 | 2009-10-01 | 2010-09-30 | 2009-10-26 | 10 | 2009-11-27 | 11
| 050.22433 | 050.KY.CampbellLeakFunct2010 | 050.KY.CampbellLeakFunct2010 | 226181.79 | Not Budgeted |  |  | 0.1141% | 259133.77 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 2827.26 | Not Budgeted |  |  | 0.001245% | 2827.26 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.24192 | VehicleEquip009div | VehicleEquip009div | 190733.08 | 190733.08 | 0 | 0% | 0.08398% | 190733.08 | 190733.08 | 0 | 2009-10-01 | 2010-09-30 | 2010-10-05 | 10 | 2010-10-07 | 10
| 050.23092 | 040.009.2738Retirements | Old 040 retirement projects being tranferred to 050 | -12292.33 | 1 | -12293.33 | -1229333% | -0.005412% | -12292.33 | 1 | -12293.33 | 2009-10-01 | 2010-09-30 | 2009-12-30 | 12 | 2010-12-30 | 12
| 040.10828 | WKG.DAN.LEB.NORTHLAND DR. RET. | 99' OF 2" STEEL PIPE | -10.11 | 606.02 | -606.02 | -100% | 0% | 0 | 606.02 | -606.02 | 2009-10-01 | 2010-09-30 | 2001-01-26 | 01 | 2005-05-04 | 05
| 040.10882 | WKG.DAN.SHE.WOODFORD RETIRMENT | RETIRE 284' OF 2" STEEL ON WOODFORD ST. | -15.8 | 1086.16 | -1086.16 | -100% | 0% | 0 | 1086.16 | -1086.16 | 2009-10-01 | 2010-09-30 | 2001-03-16 | 03 | 2005-05-04 | 05
| 050.21074 | Shelbyville 09 Growth | Shelbyville 09 Growth | 870.32 | Not Budgeted |  |  | 0.06375% | 144786.11 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21075 | Shelbyville 09 Non Growth | Shelbyville 09 Non Growth | 2485.47 | Not Budgeted |  |  | 0.1396% | 317070.19 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21076 | Madisonville 09 Growth | Madisonville 09 Growth | 1402.08 | Not Budgeted |  |  | 0.09293% | 211055.1 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21077 | Madisonville 09 Non Growth | Madisonville 09 Non Growth | 5888.2 | Not Budgeted |  |  | 0.2792% | 634160.45 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21084 | Mayfield 09 Growth | Mayfield 09 Growth | 1167.94 | Not Budgeted |  |  | 0.03017% | 68529.3 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.19599 | Shelbyville 08 Non Growth | Shelbyville 08 Non Growth | -2616.41 | Not Budgeted |  |  | 0.09243% | 209931.67 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2008-10-31 | 10
| 050.23520 | 050.2638.Randview Subd | Install 2,600 feet of 2" PE for 14 residential customers requesting natural gas service. | 2014.16 | 16453.98 | -14439.82 | -87.76% | 0.0008868% | 2014.16 | 16453.98 | -14439.82 | 2009-10-01 | 2010-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
| 050.23175 | 050.2612 EFM Equipment | New EFM Equipment | 5892.52 | 11103.74 | -5211.22 | -46.93% | 0.002594% | 5892.52 | 11103.74 | -5211.22 | 2009-10-01 | 2010-09-30 | 2010-02-11 | 02 | 2010-09-30 | 09
| 050.21802 | TchSvr.Mea.Westlake Methane | Rebuild Westlake Methane Meter Station in Calvert City | -6188.33 | 114000 | -106478.03 | -93.4% | 0.003312% | 7521.97 | 114000 | -106478.03 | 2009-10-01 | 2010-09-30 | 2009-01-09 | 01 | 2009-09-30 | 09
| 050.21538 | 2739.WARRIORS WAY FIRE STATION | INSTALL 230' OF 2" PE TO SERVE NEW FIRE STATION ON WARRIORS WAY | 12.11 | 7206 | 1240.55 | 17.22% | 0.003719% | 8446.55 | 7206 | 1240.55 | 2009-10-01 | 2010-09-30 | 2008-10-17 | 10 | 2009-10-17 | 10
| 050.20482 | 050.2637.Sarakatsannis Ext | Sarakatsannis subd rev ext/ 1,370' - 2" PE for 16 new residential lots | -0.07 | 6184.81 | -6184.81 | -100% | 0% | 0 | 6184.81 | -6184.81 | 2009-10-01 | 2010-09-30 | 2008-02-20 | 02 | 2009-02-20 | 02
| 050.23058 | 050.2635.Heath Pipe Locator | Purchase new Heath Pipe Locator | 3767.2 | 6281.78 | -2514.58 | -40.03% | 0.001659% | 3767.2 | 6281.78 | -2514.58 | 2009-10-01 | 2010-09-30 | 2009-12-09 | 12 | 2010-09-28 | 09
| 050.22438 | 050.KY.PaducahLeakFunct2010 | 050.KY.PaducahLeakFunct2010 | 467251.48 | Not Budgeted |  |  | 0.2064% | 468723.75 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22439 | 050.KY.MayfieldLeakFunct2010 | 050.KY.MayfieldLeakFunct2010 | 86634.37 | Not Budgeted |  |  | 0.03832% | 87042.24 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 040.11312 | WKG.DAN.VEHICLE 6794 RETIRE | RETIRE VEHICLE 6794 CHEVY 1996 PU | 2533.84 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2002-02-25 | 02 | 2005-05-04 | 05
| 050.23156 | 050.2612.ABB GC | Replacing Daniel GC with ABB GC | 43430.78 | 43212.76 | 218.02 | 0.5045% | 0.01912% | 43430.78 | 43212.76 | 218.02 | 2009-10-01 | 2010-09-30 | 2010-02-05 | 02 | 2010-09-30 | 09
| 050.23158 | 050.2737.DW LOCATOR | PURCHASE DITCH WITCH LOCATOR FOR CONSTRUCTION DEPT. | 7024.04 | 6024.16 | 999.88 | 16.6% | 0.003093% | 7024.04 | 6024.16 | 999.88 | 2009-10-01 | 2010-09-30 | 2010-02-05 | 02 | 2010-08-03 | 08
| 050.22200 | 2738.GRN.WISON ST IP REPLACE | INSTALL 2in PE TO REPLACE 4in BARE STEEL LP | 298.44 | 7791.93 | -1899.05 | -24.37% | 0.002595% | 5892.88 | 7791.93 | -1899.05 | 2009-10-01 | 2010-09-30 | 2009-08-03 | 08 | 2009-10-01 | 10
| 050.23089 | 050.2637.Security System | We would like to purchase a security system. We have been burglarized several times in 2009. The system consists mainly of four cameras mounted on all four corners of our 3034 Parker Street office. | 6886 | 5771.55 | 1114.45 | 19.31% | 0.003032% | 6886 | 5771.55 | 1114.45 | 2009-10-01 | 2010-09-30 | 2009-12-29 | 12 | 2010-01-26 | 01
| 040.11645 | WKG.TECH SRV.RETIRE 6786 CAR | RETIRE KAY COOMES CHEV. LUMINA 6786 | 493.7 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-01-02 | 01 | 2005-05-04 | 05
| 050.23264 | Retire Bon Harbor Well 3 | Log plug Retire BH 3 well and Field Line | 30454.04 | 36767.94 | -6313.9 | -17.17% | 0.01341% | 30454.04 | 36767.94 | -6313.9 | 2009-10-01 | 2010-09-30 | 2010-04-05 | 04 | 2010-04-30 | 04
| 050.23141 | 050.2612.I/P Modems | I/P Modems | 20957.37 | 23143.4 | -2186.03 | -9.446% | 0.009228% | 20957.37 | 23143.4 | -2186.03 | 2009-10-01 | 2010-09-30 | 2010-01-27 | 01 | 2010-09-30 | 09
| 050.23232 | 050.2737.PLASTIC PIPE LOCATOR | PLASTIC PIPE LOCATOR FOR THE DANVILLE REGION - DANVILLE, CAMPBELLSVILLE AND SHELBYVILLE | 32542.96 | 25605.01 | 6937.95 | 27.1% | 0.01433% | 32542.96 | 25605.01 | 6937.95 | 2009-10-01 | 2010-09-30 | 2010-03-11 | 03 | 2010-09-30 | 09
| 050.23238 | 050.2638.Houseman St Reg Repl | We propose to replace the regulators at our Houseman Street regulator station. The existing regulators are Grove, they are outdated, we have trouble finding repair parts. We plan to install Mooney 300 series. | 9202.58 | 10479.94 | -1277.36 | -12.19% | 0.004052% | 9202.58 | 10479.94 | -1277.36 | 2009-10-01 | 2010-09-30 | 2010-03-17 | 03 | 2010-05-28 | 05
| 050.19591 | Glasgow 08 Non Growth | Glasgow 08 Non Growth | -199.69 | Not Budgeted |  |  | 0.2159% | 490354.98 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2007-09-18 | 09 | 2009-05-13 | 05
| 050.23533 | 050.2636.RMLD | Purchase Remote Methane Leak Detector | 25887.12 | 24769.54 | 1117.58 | 4.512% | 0.0114% | 25887.12 | 24769.54 | 1117.58 | 2009-10-01 | 2010-09-30 | 2010-08-24 | 08 | 2010-09-28 | 09
| 050.23409 | 050.2636.Village Run 3 | Install 680 ft 2 Inch PE | 2394.73 | 4590.65 | -2195.92 | -47.83% | 0.001054% | 2394.73 | 4590.65 | -2195.92 | 2009-10-01 | 2010-09-30 | 2010-06-22 | 06 | 2010-09-28 | 09
| 050.22395 | 050.KY.CampbellIntegFunct2010 | 050.KY.CampbellIntegFunct2010 | 252390.27 | Not Budgeted |  |  | 0.1168% | 265165.12 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22398 | 050.KY.PrincetonIntegFunct2010 | 050.KY.PrincetonIntegFunct2010 | 229076.07 | Not Budgeted |  |  | 0.1019% | 231438.15 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22399 | 050.KY.OboroIntegFunct2010 | 050.KY.OboroIntegFunct2010 | 1489497.77 | Not Budgeted |  |  | 0.6677% | 1516410.39 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23462 | 2738.OLD PITMAN RD.MARK GRAY | INSTALL MAIN FOR DUPLEXES OFF OLD PITMAN RD FOR MARK GRAY | 1307.28 | 3047.23 | -1739.95 | -57.1% | 0.0005756% | 1307.28 | 3047.23 | -1739.95 | 2009-10-01 | 2010-09-30 | 2010-07-21 | 07 | 2010-10-01 | 10
| 050.23410 | Fairview Ave. Bare Steel Repl | Fairview Ave. Bare Steel Replacement | 224768.8 | 339934.28 | -115165.48 | -33.88% | 0.09897% | 224768.8 | 339934.28 | -115165.48 | 2009-10-01 | 2010-09-30 | 2010-06-23 | 06 | 2010-09-28 | 09
| 050.23414 | 050.2734.Bobcat Welder | 050.2734.Bobcat Welder | 3900.26 | 4479.3 | -579.04 | -12.93% | 0.001717% | 3900.26 | 4479.3 | -579.04 | 2009-10-01 | 2010-09-30 | 2010-06-24 | 06 | 2010-09-28 | 09
| 050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 192.55 | Not Budgeted |  |  | 8.478e-05% | 192.55 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 269.2 | Not Budgeted |  |  | 0.0001185% | 269.2 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23464 | 050.2638.Replace Ground Bed | The ground bed at our 18th Street rectifier is depleted. The output has been steadily falling off and is to the point where it is not protecting the pipleine. | 9731.91 | 12181.95 | -2450.04 | -20.11% | 0.004285% | 9731.91 | 12181.95 | -2450.04 | 2009-10-01 | 2010-09-30 | 2010-07-22 | 07 | 2010-09-28 | 09
| 050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 165.99 | Not Budgeted |  |  | 7.309e-05% | 165.99 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22140 | 050.2637.Odorizer - Calvert | We plan to install an odorizer in the Calvert industrial park and abandon a dozen smaller individual drip pots.We will then dispose of these smaller units a few every year, as this is an expensive procedure. | 56257.11 | 97154 | 7057.8 | 7.265% | 0.04588% | 104211.8 | 97154 | 7057.8 | 2009-10-01 | 2010-09-30 | 2009-07-02 | 07 | 2009-09-29 | 09
| 050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 17.62 | Not Budgeted |  |  | 7.758e-06% | 17.62 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.22394 | 050.KY.DanvilleIntegFunct2010 | 050.KY.DanvilleIntegFunct2010 | 492994.58 | Not Budgeted |  |  | 0.2233% | 507153.78 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22985 | 0500.2734.Riverview Reloc. | Replace 2 inch steel with 2 inch PE - Riverview | 1923.78 | 4519.49 | -2595.71 |  | 0.000847% | 1923.78 | 4519.49 | -2595.71 | 2009-10-01 | 2010-09-30 | 2009-11-05 | 11 | 2009-12-15 | 12
| 050.23305 | 050.2734.New St. 2 ich Ext. | 255 ft. of 2 inch PE - New St. - Bowling Green | -972.23 | 1032.75 | -2004.98 | -194.1% | -0.0004281% | -972.23 | 1032.75 | -2004.98 | 2009-10-01 | 2010-09-30 | 2010-04-29 | 04 | 2010-09-28 | 09
| 050.23377 | 050.2636.Free Silver Rd. | Install 250 Ft 2 Inch PE | 2739.62 | 2601.02 | 138.6 | 5.329% | 0.001206% | 2739.62 | 2601.02 | 138.6 | 2009-10-01 | 2010-09-30 | 2010-06-07 | 06 | 2010-09-28 | 09
| 050.22302 | 050.2637.Eva Dr Rev Ext | 200 feet for four residential customers | 1826.69 | 1928.6 | 320.94 | 16.64% | 0.0009905% | 2249.54 | 1928.6 | 320.94 | 2009-10-01 | 2010-09-30 | 2009-09-02 | 09 | 2009-09-18 | 09
| 050.22303 | 050.2637.Smart-Cal | We are purchasing this Smart-Cal unit for the purpose of calibrating our Sensit Gold machines, in adition unit has the ability to store key information. | 281.8 | 3917.5 | -162.91 | -4.159% | 0.001653% | 3754.59 | 3917.5 | -162.91 | 2009-10-01 | 2010-09-30 | 2009-09-02 | 09 | 2009-09-25 | 09
| 050.22301 | 050.2637.Allegheny Rd Ext | install 360 feet 2 inch pe for one existing residential | 2623.99 | 2418.84 | 1067.76 | 44.14% | 0.001535% | 3486.6 | 2418.84 | 1067.76 | 2009-10-01 | 2010-09-30 | 2009-09-02 | 09 | 2009-09-17 | 09
| 050.22304 | 050.2637.Guages - M.Hunt | We would like to purchase one regulator guage assembly for testing with nitrogen 0 - 2000 psi. Unit sells for app. $700. Item number two is a digital guage 0 - 100 psi made by Ashcroft Manufacturing, sells for $500. | 1102.17 | 2115.45 | -1013.28 | -47.9% | 0.0004853% | 1102.17 | 2115.45 | -1013.28 | 2009-10-01 | 2010-09-30 | 2009-09-02 | 09 | 2009-09-25 | 09
| 050.22989 | 050.2734.E 10th. Replacement | 1295 ft. of 4 inch PE - E 10th between Bypass and Covington | 79165.17 | 80530.42 | -1365.25 | -1.695% | 0.03486% | 79165.17 | 80530.42 | -1365.25 | 2009-10-01 | 2010-09-30 | 2009-11-06 | 11 | 2010-09-28 | 09
| 050.23046 | 050.2636.Gas Tracker | Purchase Gas Tracker Pipe Locator | 36326.28 | 28912.72 | 7413.56 | 25.64% | 0.01599% | 36326.28 | 28912.72 | 7413.56 | 2009-10-01 | 2010-09-30 | 2009-11-30 | 11 | 2010-09-28 | 09
| 050.22201 | TchSvr.Mea.EFM.PAT, Inc | EFM for Premium Allied Tool, Inc | -2717.84 | 4140 | -3755.76 | -90.72% | 0.0001692% | 384.24 | 4140 | -3755.76 | 2009-10-01 | 2010-09-30 | 2009-08-03 | 08 | 2009-09-30 | 09
| 050.20925 | 050.2609.Bon Harbor Well #6 | Workover Bon Harbor Well #6 | 95265.1 | 156248.88 | -3449.04 | -2.207% | 0.06728% | 152799.84 | 156248.88 | -3449.04 | 2009-10-01 | 2010-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.22188 | 2738.GRB.DURHAM ST RETIREMENT | RETIRE 452ft OF 2in BARE STEEL ON DURHAM ST BETWEEN CAOKLY AND WILSON IN GREENSBURG KY | 149.22 | 5813.56 | -4800.14 | -82.57% | 0.0004462% | 1013.42 | 5813.56 | -4800.14 | 2009-10-01 | 2010-09-30 | 2009-07-27 | 07 | 2009-10-01 | 10
| 050.21958 | 050.2602 Replace PCs | Replace dated PCs | 147.66 | 168326.32 | -126825.46 | -75.34% | 0.01827% | 41500.86 | 168326.32 | -126825.46 | 2009-10-01 | 2010-09-30 | 2009-03-27 | 03 | 2009-09-25 | 09
| 050.22435 | 050.KY.MadisonLeakFunct2010 | 050.KY.MadisonLeakFunct2010 | 151836.75 | Not Budgeted |  |  | 0.06866% | 155949.51 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.21946 | 2738.GRN.E COLUMBIA RELOCATE | RELOCATE 2" STEEL ON EAST COLUMBIA WITH NEW WATERLINE | 391.28 | 8455 | -2461 | -29.11% | 0.002639% | 5994 | 8455 | -2461 | 2009-10-01 | 2010-09-30 | 2009-03-24 | 03 | 2012-03-25 | 03
| 040.10399 | wkg.dan.leb.Mackville Rd. GB | Replace ground to rectifier | -49.11 | 8291 | -8291 | -100% | 0% | 0 | 8291 | -8291 | 2009-10-01 | 2010-09-30 | 1999-12-22 | 12 | 2005-05-04 | 05
| 050.24177 | 050.2637.Locator - Thomason | Pipehorn Model MD840 dual frequency pipe locator to be purchased for use in the Paducah area. Will be assigned to Mickie Thomason. | 1670.18 | 1896.24 | -226.06 | -11.92% | 0.0007354% | 1670.18 | 1896.24 | -226.06 | 2009-10-01 | 2010-09-30 | 2010-09-28 | 09 | 2010-09-30 | 09
| 050.22072 | TchSvr.Mea.EFM Repl - MO | EFM Replacement for Missoure | 1875.61 | 19597 | -3210.07 | -16.38% | 0.007215% | 16386.93 | 19597 | -3210.07 | 2009-10-01 | 2010-09-30 | 2009-06-05 | 06 | 2009-09-30 | 09
| 050.20509 | 2738.LEB.HENDRICKSON STATION | INSTALL REGULATOR STATION ON HENDRICKSON DR IN LEBANON | 1845.49 | 9458 | 2168.23 | 22.92% | 0.005119% | 11626.23 | 9458 | 2168.23 | 2009-10-01 | 2010-09-30 | 2008-03-04 | 03 | 2010-10-28 | 10
| 050.22397 | 050.KY.MadisonIntegFunct2010 | 050.KY.MadisonIntegFunct2010 | 736902.62 | Not Budgeted |  |  | 0.3324% | 755037.97 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2011-01-12 | 01
| 050.23435 | 050.2634.Legion Dr. 1 | Replace 242 ft 2Inch Stl With 370 ft 2 Inch PE | 8516.02 | 11849.41 | -3333.39 | -28.13% | 0.00375% | 8516.02 | 11849.41 | -3333.39 | 2009-10-01 | 2010-09-30 | 2010-07-02 | 07 | 2010-09-28 | 09
| 050.23341 | 050.2636.Locust St.Retirement | Retire 3 Inch LP Main | 2891.11 | 91.99 | 2799.12 | 3043% | 0.001273% | 2891.11 | 91.99 | 2799.12 | 2009-10-01 | 2010-09-30 | 2010-05-19 | 05 | 2010-09-28 | 09
| 050.23522 | 050.2636.Hartford Purchase | Repair to Station | 21974.86 | 9980.66 | 11994.2 | 120.2% | 0.009676% | 21974.86 | 9980.66 | 11994.2 | 2009-10-01 | 2010-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
| 050.23188 | 050.2637.YZ Replace Trunkline | This project is for an upgrade to our YZ odorizer at our Trunkline Purchase Station in western Mccracken County This is a 2010 budgeted item. The existing model 7200 pump is obsolete, and we cannot get parts. We would like to purchase the model 7300. | 20842.69 | 31656.86 | -10814.17 | -34.16% | 0.009177% | 20842.69 | 31656.86 | -10814.17 | 2009-10-01 | 2010-09-30 | 2010-02-17 | 02 | 2010-05-27 | 05
| 050.23151 | 050.2609.OMHS Relocation | Relocate 4000 feet 8 Inch Stl. | 64350.03 | -4.32 | 64354.35 | -1489684% | 0.02833% | 64350.03 | -4.32 | 64354.35 | 2009-10-01 | 2010-09-30 | 2010-02-01 | 02 | 2010-09-28 | 09
| 050.21959 | 050.2602 Replace MDTs | Replace dated MDTs | 147.66 | 168292.66 | -109813.25 | -65.25% | 0.02575% | 58479.41 | 168292.66 | -109813.25 | 2009-10-01 | 2010-09-30 | 2009-03-27 | 03 | 2009-09-28 | 09
| 050.23339 | 050.2635.Macedonia Sta. Rt. | Retire Macedonia East Station | 195.01 | 3928.89 | -3733.88 | -95.04% | 8.586e-05% | 195.01 | 3928.89 | -3733.88 | 2009-10-01 | 2010-09-30 | 2010-05-18 | 05 | 2010-09-28 | 09
| 050.23399 | 050.2636.Settles Rd.2 | Install 176 Ft 2 Inch PE | 538.62 | 1327.2 | -788.58 | -59.42% | 0.0002372% | 538.62 | 1327.2 | -788.58 | 2009-10-01 | 2010-09-30 | 2010-06-21 | 06 | 2010-09-27 | 09
| 050.21778 | 2737.BURGIN RECTIFIER REPLACE | REPLACE BURGIN RECTIFIER DAMAGED IN CAR ACCIDENT | -5513.2 | 7877 | -10351.54 | -131.4% | -0.00109% | -2474.54 | 7877 | -10351.54 | 2009-10-01 | 2010-09-30 | 2008-12-15 | 12 | 2009-12-15 | 12
| 050.23093 | 040.009.2739Retirements | Old 040 retirement projects being transferred to 050 | -15730.81 | 1 | -15731.81 | -1573181% | -0.006926% | -15730.81 | 1 | -15731.81 | 2009-10-01 | 2010-09-30 | 2009-12-30 | 12 | 2010-12-30 | 12
| 050.23182 | 1100 - 1200 blk. Ky Replc BG | 1100 and 1200 blk. Ky St. Bare Replc. | 127018.71 | 95801.3 | 31217.41 | 32.59% | 0.05593% | 127018.71 | 95801.3 | 31217.41 | 2009-10-01 | 2010-09-30 | 2010-02-15 | 02 | 2010-09-28 | 09
| 050.23527 | 050.2612.Transportion EFM | New Transportion Customers,Amcor Caldwell Co. Hospital,S&Y Terminal And USNC | 12587.97 | 13738.74 | -1150.77 | -8.376% | 0.005543% | 12587.97 | 13738.74 | -1150.77 | 2009-10-01 | 2010-09-30 | 2010-08-23 | 08 | 2010-09-30 | 09
| 050.22999 | 050.2637.Bryant Ford Rd Ext | Install 140 feet of 2 inch pls main for one new residential customer | 1581.46 | 1173.82 | 407.64 | 34.73% | 0.0006963% | 1581.46 | 1173.82 | 407.64 | 2009-10-01 | 2010-09-30 | 2009-11-10 | 11 | 2009-11-30 | 11
| 050.21070 | Danville 09 Growth | Danville 09 Growth | 1939.81 | Not Budgeted |  |  | 0.09343% | 212201.65 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21082 | Paducah 09 Growth | Paducah 09 Growth | 2505.33 | Not Budgeted |  |  | 0.1607% | 365000.27 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23356 | 050.2734.Massey Springs Ext. | 420 ft. of 2 inch PE to serve assisted livining development | 875.38 | 4654.13 | -3778.75 | -81.19% | 0.0003854% | 875.38 | 4654.13 | -3778.75 | 2009-10-01 | 2010-09-30 | 2010-05-27 | 05 | 2010-09-28 | 09
| 050.22127 | 050.2636.Heartland phase 5 | Install 2 Inch Pe to serve 22 Residential lots | 347.62 | 6004.64 | -1810.47 | -30.15% | 0.001847% | 4194.17 | 6004.64 | -1810.47 | 2009-10-01 | 2010-09-30 | 2009-06-30 | 06 | 2009-09-28 | 09
| 040.11661 | WKG.DAN.SHV.VEH RETIRE 6790 | RETIRE VEHICLE # 6790 | 3616.57 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-01-24 | 01 | 2005-05-04 | 05
| 040.11701 | 040.DAN.CAM.VEH RETIRE #6791 | RETIRE VEHICLE #6791 | 3616.57 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-03-03 | 03 | 2005-05-04 | 05
| 040.11730 | 040.DAN.SHV.RETIRE VEH #6898 | RETIRE VEHICLE #6898 | 3712.65 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-04-03 | 04 | 2005-05-04 | 05
| 050.22254 | 2738.LEB.CVILLE RD-VILLAGE | REPLACE 200ft OF 2in STEEL - LEAKAGE | 1958.46 | 16340.6 | -13944.03 | -85.33% | 0.001055% | 2396.57 | 16340.6 | -13944.03 | 2009-10-01 | 2010-09-30 | 2009-08-19 | 08 | 2009-10-01 | 10
| 050.21071 | Danville 09 Non Growth | Danville 09 Non Growth | 4296.76 | Not Budgeted |  |  | 0.2895% | 657492.27 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23359 | 050.2736.TB 1 Replacement | Replace Dated Station | 315967.14 | 549090.34 | -233123.2 | -42.46% | 0.1391% | 315967.14 | 549090.34 | -233123.2 | 2009-10-01 | 2010-09-30 | 2010-06-01 | 06 | 2010-09-28 | 09
| 050.23147 | 050.2636.Wescore Purchase | Purchase new 2" Mooney Regulator for the Wescore Purchase Station. | 3557.49 | 4094.65 | -537.16 | -13.12% | 0.001566% | 3557.49 | 4094.65 | -537.16 | 2009-10-01 | 2010-09-30 | 2010-01-29 | 01 | 2010-09-28 | 09
| 050.21628 | 050.BGR.GLS.HWY 31W RELOC. | 1100 FT OF 2" PE - HYW 31W - MUNFORDVILLE | 14050.99 | 53495 | 3789.67 | 7.084% | 0.02522% | 57284.67 | 53495 | 3789.67 | 2009-10-01 | 2010-09-30 | 2008-11-11 | 11 | 2009-11-11 | 11
| 050.23534 | 050.2636.Hunters Chase Court | Install 500 Ft 2 Inch PE | 2288.43 | 1596.86 | 691.57 | 43.31% | 0.001008% | 2288.43 | 1596.86 | 691.57 | 2009-10-01 | 2010-09-30 | 2010-08-26 | 08 | 2010-09-28 | 09
| 050.22391 | 050.KY.BowlGrnIntegFunct2010 | 050.KY.BowlGrnIntegFunct2010 | 785904.77 | Not Budgeted |  |  | 0.571% | 1296759.04 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22430 | 050.KY.GlasgowLeakFunct2010 | 050.KY.GlasgowLeakFunct2010 | 241269.59 | Not Budgeted |  |  | 0.1075% | 244132.75 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2011-03-12 | 03
| 050.23337 | 2738.MAPLE ST-WICKLIFF | INSTALL 200ft OF 2in PE FOR RESTURANT ON BROADWAY | 1024.62 | 5595.91 | -4571.29 | -81.69% | 0.0004511% | 1024.62 | 5595.91 | -4571.29 | 2009-10-01 | 2010-09-30 | 2010-05-17 | 05 | 2011-05-12 | 05
| 050.22420 | 050.2634.Hwy 181 Retirement | Retire 2900 feet Bare 4 Inch Stl. | 1064.66 | 2125.51 | -337.13 | -15.86% | 0.0007874% | 1788.38 | 2125.51 | -337.13 | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2009-09-10 | 09
| 050.24072 | KY.ShelbyvilleLeakCP/LeakClmps | Shelbyville KY Leak Functional - CP/Leak Clamps | 888.43 | Not Budgeted |  |  | 0.0003912% | 888.43 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-15 | 09 | 2016-09-30 | 09
| 050.23231 | 2737.DEAR MEADOW PH 2 | INSTALL 600ft OF 2in PE | 2862.19 | 7710.64 | -4848.45 | -62.88% | 0.00126% | 2862.19 | 7710.64 | -4848.45 | 2009-10-01 | 2010-09-30 | 2010-03-10 | 03 | 2011-04-15 | 04
| 050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 836.79 | Not Budgeted |  |  | 0.0003684% | 836.79 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-13 | 09 | 2016-09-30 | 09
| 050.22318 | 050.2634.Center St. Rplmnt. | Replace 390' 6 " Bare pipe | 7509.51 | 11709.9 | 3440.49 | 29.38% | 0.006671% | 15150.39 | 11709.9 | 3440.49 | 2009-10-01 | 2010-09-30 | 2009-09-08 | 09 | 2009-09-28 | 09
| 050.23001 | 050.2602.MDTs2010 | Purchase new MDTs to replace dated equipment | 82246.23 | 97815 | -15568.77 | -15.92% | 0.03621% | 82246.23 | 97815 | -15568.77 | 2009-10-01 | 2010-09-30 | 2009-11-12 | 11 | 2010-09-28 | 09
| 050.20484 | 050.2609.Bon Harbor Well # 9 | Workover Well # 9 Bon Harbor | 4761.54 | 183203.93 | 7770.62 | 4.242% | 0.08409% | 190974.55 | 183203.93 | 7770.62 | 2009-10-01 | 2010-09-30 | 2008-02-21 | 02 | 2009-08-01 | 08
| 050.23388 | 050.2634.TB1 Replacement | 050.2634.TB1 Replacement | 255420.84 | 253593.8 | 1827.04 | 0.7205% | 0.1125% | 255420.84 | 253593.8 | 1827.04 | 2009-10-01 | 2010-09-30 | 2010-06-14 | 06 | 2010-09-28 | 09
| 050.23295 | 050.2736.S.Campbell St. Rplmt | Replace bare 4 Inch Steel | 134068 | 133134.61 | 933.39 | 0.7011% | 0.05903% | 134068 | 133134.61 | 933.39 | 2009-10-01 | 2010-09-30 | 2010-04-23 | 04 | 2010-05-22 | 05
| 050.20927 | 050.2609.Bon Harbor Well #4 | Workover Bonharbor Well #4 | 148287.94 | 215362.55 | -4797.92 | -2.228% | 0.09271% | 210564.63 | 215362.55 | -4797.92 | 2009-10-01 | 2010-09-30 | 2008-09-02 | 09 | 2009-08-01 | 08
| 050.21072 | Campbellsville 09 Growth | Campbellsville 09 Growth | 829.95 | Not Budgeted |  |  | 0.04021% | 91315.48 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21083 | Paducah 09 Non Growth | Paducah 09 Non Growth | 6019.86 | Not Budgeted |  |  | 0.4214% | 957158.41 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23531 | 050.2636.Hwy 56 | Install 4100 Feet 4 Inch PE | 263.15 | 54644.06 | -54380.91 | -99.52% | 0.0001159% | 263.15 | 54644.06 | -54380.91 | 2009-10-01 | 2010-09-30 | 2010-08-23 | 08 | 2010-09-28 | 09
| 050.23519 | 050.2609.Line Locator | Purchase new line locator retire old one. | 3787.71 | 8462.9 | -4675.19 | -55.24% | 0.001668% | 3787.71 | 8462.9 | -4675.19 | 2009-10-01 | 2010-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
| 050.22978 | 2737.STAN.HUBBLE RELOCATE | RELOCATE 440' OF 2in DUPONT WITH 2in PE | 6469.13 | 3597.11 | 2872.02 | 79.84% | 0.002848% | 6469.13 | 3597.11 | 2872.02 | 2009-10-01 | 2010-09-30 | 2009-10-29 | 10 | 2010-10-01 | 10
| 050.23381 | 050.2638.Mayfield Bypass | Relocate required due to KYDOT improvements | 108288.99 | 49488.84 | 58800.15 | 118.8% | 0.04768% | 108288.99 | 49488.84 | 58800.15 | 2009-10-01 | 2010-09-30 | 2010-06-09 | 06 | 2010-09-28 | 09
| 050.24120 | 050.2638.E.F Equip | Electro fuse equipment for use in the Mayfield area. | 9037.03 | 10014.22 | -977.19 | -9.758% | 0.003979% | 9037.03 | 10014.22 | -977.19 | 2009-10-01 | 2010-09-30 | 2010-09-21 | 09 | 2010-09-30 | 09
| 040.12085 | 040.DAN.RETIRE 5984 - TRAILER | RETIRE TRAILER FOR UNIT 5983 CASE TRENCHER | 777.23 | -100 | 100 | -100% | 0% | 0 | -100 | 100 | 2009-10-01 | 2010-09-30 | 2004-01-08 | 01 | 2005-05-04 | 05
| 040.11169 | wkg.dan.shv.retire case trench | retire case trencher #5982 | 4966.84 | -4000 | 4000 | -100% | 0% | 0 | -4000 | 4000 | 2009-10-01 | 2010-09-30 | 2001-10-17 | 10 | 2005-05-04 | 05
| 050.23049 | 2739.WILD TURKEY EXPANSION | INSTALL 600ft OF 4iN STEEL FOR WILD TURKEY EXPANSION | 13679.26 | 11308.5 | 2370.76 | 20.96% | 0.006023% | 13679.26 | 11308.5 | 2370.76 | 2009-10-01 | 2010-09-30 | 2009-12-03 | 12 | 2010-10-01 | 10
| 050.24144 | 050.2612.REFURB METERS FY11 | cc2612 KY Refurb Meters FY 2011 | 7377.12 | 248506 | -241128.88 | -97.03% | 0.003248% | 7377.12 | 248506 | -241128.88 | 2009-10-01 | 2010-09-30 | 2010-09-22 | 09 | 2011-09-30 | 09
| 040.10501 | RETIRE VEHICLE 5851 PHILLIPS | RETIRE 1993 CHEVROLET P.U. IN DANVILLE | -18.86 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2000-03-28 | 03 | 2005-05-04 | 05
| 040.10926 | wkg.dan.spri.rectifier repl. | replace 47 year old rectifier. | -58.81 | 5945 | -5945 | -100% | 0% | 0 | 5945 | -5945 | 2009-10-01 | 2010-09-30 | 2001-05-03 | 05 | 2005-05-04 | 05
| 050.21079 | Princeton 09 Non Growth | Princeton 09 Non Growth | 1059.82 | Not Budgeted |  |  | 0.08361% | 189898.7 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.21073 | Campbellsville 09 Non Growth | Campbellsville 09 Non Growth | 10601.08 | Not Budgeted |  |  | 0.261% | 592716.49 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23272 | 050.2734. 31W Reloc Woodburn | Reloc. 400 ft. of 2 inch PE - Hwy 31W - Woodburn | 2174.62 | 10.63 | 2163.99 | 20357% | 0.0009575% | 2174.62 | 10.63 | 2163.99 | 2009-10-01 | 2010-09-30 | 2010-04-08 | 04 | 2010-09-28 | 09
| 050.23125 | 2739.SCENIC GARDEN 2010 | INSTALL 200ft OF 2in PE FOR TWO LOTS ION SCENIC GARDEN - LOTS 26-27 | 3383.91 | 2889.15 | 494.76 | 17.12% | 0.00149% | 3383.91 | 2889.15 | 494.76 | 2009-10-01 | 2010-09-30 | 2010-01-22 | 01 | 2010-12-01 | 12
| 050.22473 | 2739.HAVEN HILL-MIDLAND | REPLACE 4in STEEL WITH 4in PE FOR BYPASS CONSTRUCTION | 950.29 | 4004.35 | -3054.06 | -76.27% | 0.0004184% | 950.29 | 4004.35 | -3054.06 | 2009-10-01 | 2010-09-30 | 2009-09-29 | 09 | 2010-10-01 | 10
| 050.22470 | 050.3305.Boiler Replacement | Replace Boiler leased property 2410 New Hartford Rd. | 26.53 | 28759.57 | -7215.97 | -25.09% | 0.009486% | 21543.6 | 28759.57 | -7215.97 | 2009-10-01 | 2010-09-30 | 2009-09-29 | 09 | 2009-09-30 | 09
| 050.23013 | 2739.CLOVERBROOK SEC 3 | INSTALL 2in PE ON BEAMTREE DRIVE CLOVERBROOK SEC 3 | 8368.03 | 9678.93 | -1310.9 | -13.54% | 0.003684% | 8368.03 | 9678.93 | -1310.9 | 2009-10-01 | 2010-09-30 | 2009-11-17 | 11 | 2010-10-28 | 10
| 050.23048 | 2737.COMMERECE DR.PAINT SHOP | INSTALL 2in PE FOR PAINT SHOP | 1606.77 | 2872.29 | -1265.52 | -44.06% | 0.0007075% | 1606.77 | 2872.29 | -1265.52 | 2009-10-01 | 2010-09-30 | 2009-12-02 | 12 | 2010-11-17 | 11
| 050.23002 | 050.2602.Phone system 2010 | Replace dated phone System | 47639.86 | 82655 | -35015.14 | -42.36% | 0.02098% | 47639.86 | 82655 | -35015.14 | 2009-10-01 | 2010-09-30 | 2009-11-12 | 11 | 2010-09-28 | 09
| 040.11210 | WKG.DAN.RETIRE BACKHOE 5441 | RETIRE 1990 CASE 480F #5441 | 9195.38 | -9000 | 9000 | -100% | 0% | 0 | -9000 | 9000 | 2009-10-01 | 2010-09-30 | 2001-11-12 | 11 | 2005-05-04 | 05
| 040.11731 | 040.DAN.SHV.RETIRE VEH #6919 | RETIRE VEHICLE #6919 | 4080.22 | -2500 | 2500 | -100% | 0% | 0 | -2500 | 2500 | 2009-10-01 | 2010-09-30 | 2003-04-03 | 04 | 2005-05-04 | 05
| 050.22281 | 2739.FAIRWAY XING 4 | INSTALL 2in PE FOR FAIRWAY CROSSING PHASE 4 | 11401.95 | 11094.24 | 307.71 | 2.774% | 0.00502% | 11401.95 | 11094.24 | 307.71 | 2009-10-01 | 2010-09-30 | 2009-08-25 | 08 | 2010-09-01 | 09
| 050.23431 | 050.2734.Springfield VII | 1200 ft. of 2 inch PE - Springfield VII | 2253.11 | 6165.79 | -3912.68 | -63.46% | 0.000992% | 2253.11 | 6165.79 | -3912.68 | 2009-10-01 | 2010-09-30 | 2010-06-25 | 06 | 2010-09-28 | 09
| 050.23290 | 050.2634.Spa Ln. Retirement | Retire 678 feet 2 Inch Stl. | 1247.44 | 199.51 | 1047.93 | 525.3% | 0.0005493% | 1247.44 | 199.51 | 1047.93 | 2009-10-01 | 2010-09-30 | 2010-04-20 | 04 | 2010-09-28 | 09
| 050.22361 | 050.KY.PaducahGrowthFunct2010 | 050.KY.PaducahGrowthFunct2010 | 566489.24 | Not Budgeted |  |  | 0.2564% | 582292.3 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22362 | 050.KY.MayfieldGrowthFunct2010 | 050.KY.MayfieldGrowthFunct2010 | 50234 | Not Budgeted |  |  | 0.02252% | 51140.12 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23429 | 050.2734.Frk.Macedonia Ext. | 2 inch PE Ext. - Macedonis Rd. - Franklin | 433.43 | 2835.42 | -2401.99 | -84.71% | 0.0001908% | 433.43 | 2835.42 | -2401.99 | 2009-10-01 | 2010-09-30 | 2010-06-25 | 06 | 2010-09-28 | 09
| 050.22994 | 050.2734.Ken Bale 2 Inch Ext. | 825 ft. of 2 inch PE - Ken Bale - Bowlingt Green | 741 | 1159.59 | -418.59 | -36.1% | 0.0003263% | 741 | 1159.59 | -418.59 | 2009-10-01 | 2010-09-30 | 2009-11-09 | 11 | 2010-09-28 | 09
| 050.22401 | 050.KY.MayfieldIntegFunct2010 | 050.KY.MayfieldIntegFunct2010 | 269934.2 | Not Budgeted |  |  | 0.1242% | 281996.78 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.22432 | 050.KY.DanvilleLeakFunct2010 | 050.KY.DanvilleLeakFunct2010 | 185377.44 | Not Budgeted |  |  | 0.08239% | 187126.28 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.23415 | 050.2734.Reg Replc TB 4 | 050.2734.Reg Replc TB 4 | 7987.13 | 14877.9 | -6890.77 | -46.32% | 0.003517% | 7987.13 | 14877.9 | -6890.77 | 2009-10-01 | 2010-09-30 | 2010-06-24 | 06 | 2010-09-28 | 09
| 050.23256 | 050.2635.Line St | Install 100 Feet 2 Inch PE | 1685.67 | 1338.06 | 347.61 | 25.98% | 0.0007422% | 1685.67 | 1338.06 | 347.61 | 2009-10-01 | 2010-09-30 | 2010-03-31 | 03 | 2010-09-28 | 09
| 050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 2827.22 | Not Budgeted |  |  | 0.001245% | 2827.22 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
| 050.22320 | 050.2602.Replace MDTs2 | Replace dated MDTs | 147.66 | 156386.6 | -112630.13 | -72.02% | 0.01927% | 43756.47 | 156386.6 | -112630.13 | 2009-10-01 | 2010-09-30 | 2009-09-08 | 09 | 2009-09-28 | 09
| 050.22988 | 050.2734.Mimosa Replc. | Replace 3 inch bare with 2 inch pe - Mimosa Alley | 1669.9 | 6258.11 | -4588.21 | -73.32% | 0.0007353% | 1669.9 | 6258.11 | -4588.21 | 2009-10-01 | 2010-09-30 | 2009-11-05 | 11 | 2010-01-05 | 01
| 050.22214 | 050.2638.N Sutton Ln Rev Ext | Install 160 feet of 2 inch ply pipe for one existing residential customer requesting gas service. | 414.45 | 1074.89 | 497.64 | 46.3% | 0.0006924% | 1572.53 | 1074.89 | 497.64 | 2009-10-01 | 2010-09-30 | 2009-08-10 | 08 | 2009-09-28 | 09
| 050.23053 | 050.2635.Good St. Alley | Replace 2 Inch Steel in Sewer | 5201.27 | 6441.22 | -1239.95 | -19.25% | 0.00229% | 5201.27 | 6441.22 | -1239.95 | 2009-10-01 | 2010-09-30 | 2009-12-07 | 12 | 2010-09-28 | 09
| 050.23559 | 2738.GREENSBURG RD.BLEVIN CON | INSTALL 2in PE FOR BLEVINS CONST OFFICE ON GREENSBURG RD | 17.48 | 3962.45 | -3944.97 | -99.56% | 7.696e-06% | 17.48 | 3962.45 | -3944.97 | 2009-10-01 | 2010-09-30 | 2010-09-07 | 09 | 2011-08-01 | 08
| 040.10398 | wkg.dan.leb. Calvary G.B. | Replace ground bed on rectifier | -15.35 | 10215 | -10215 | -100% | 0% | 0 | 10215 | -10215 | 2009-10-01 | 2010-09-30 | 1999-12-22 | 12 | 2005-05-04 | 05
| 050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | -281.67 | Not Budgeted |  |  | -0.000124% | -281.67 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2010-09-12 | 09 | 2010-09-23 | 09
| 050.23406 | 2738.SALOMA RD.REPLACE | REPLACE 468ft OF 2in STEEL ON SALOMA RD NEAR HILL LN | 1276.42 | 5735.48 | -4459.06 | -77.75% | 0.000562% | 1276.42 | 5735.48 | -4459.06 | 2009-10-01 | 2010-09-30 | 2010-06-21 | 06 | 2010-10-01 | 10
| 050.21078 | Princeton 09 Growth | Princeton 09 Growth | 1039.94 | Not Budgeted |  |  | 0.04998% | 113512.58 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2008-09-29 | 09 | 2009-10-31 | 10
| 050.23267 | 050.2636.Install Relief valves | Replace Relief Valves Glenville Calhoun Beaver Dam TB and Stanley Wimsatt Rd Station | 25055.98 | 24583.3 | 472.68 | 1.923% | 0.01103% | 25055.98 | 24583.3 | 472.68 | 2009-10-01 | 2010-09-30 | 2010-04-07 | 04 | 2010-09-28 | 09
| 050.22393 | 050.KY.HopkinsIntegFunct2010 | 050.KY.HopkinsIntegFunct2010 | 539496.4 | Not Budgeted |  |  | 0.2431% | 552120.24 | Not Budgeted |  | 2009-10-01 | 2010-09-30 | 2009-09-10 | 09 | 2010-09-30 | 09
| 050.24170 | 050.2634.Electro Fuse Eq. | Purchase Electro fuse equipment | 16105.37 | 18483.58 | -2378.21 | -12.87% | 0.007091% | 16105.37 | 18483.58 | -2378.21 | 2009-10-01 | 2010-09-30 | 2010-09-27 | 09 | 2010-09-30 | 09
| 050.23352 | 050.2734.No Blo Equipment | 050.2734 Mueller No Blo Equipment | 11738.97 | 8689.84 | 3049.13 | 35.09% | 0.005169% | 11738.97 | 8689.84 | 3049.13 | 2009-10-01 | 2010-09-30 | 2010-05-26 | 05 | 2010-09-28 | 09
| 050.21932 | 050.3351.M & R Test Equip | Test equipment for m & R personnel in the 3351 sub-region | -162.27 | 14795.44 | 2923.69 | 19.76% | 0.007802% | 17719.13 | 14795.44 | 2923.69 | 2009-10-01 | 2010-09-30 | 2009-03-17 | 03 | 2010-03-02 | 03
| 050.23525 | 2737.PERRYVILLE TBS RELOCATE | RELOCATE THE TBS FROM PRESENT LOCATION TO REYNOLDS PROPERTY OFF OF HIGHWAY 68 | 25338.17 | 137270.6 | -111932.43 | -81.54% | 0.01116% | 25338.17 | 137270.6 | -111932.43 | 2009-10-01 | 2010-09-30 | 2010-08-20 | 08 | 2011-03-25 | 03
| 050.23553 | 2738.SHELBY ST RETIREMENT | RETIRE 2in STEEL LINE ON SPRING AND SHELBY STREETS | 718.5 | 318.44 | 400.06 | 125.6% | 0.0003164% | 718.5 | 318.44 | 400.06 | 2009-10-01 | 2010-09-30 | 2010-09-02 | 09 | 2011-01-06 | 01

## 2009a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2009
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2009 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.20287 | 050.BGR.GLS.HART CO. IND. | HART CO. INDUSTRIAL PUR. STA. & 4" STL. EXT. | -272600.63 | 583548 | -196895.12 | -33.74% | 2.223% | 386652.88 | 583548 | -196895.12 | 2008-10-01 | 2009-09-30 | 2007-11-09 | 2007-11-09 | 2008-11-09 | 2008-11-09
| 050.20387 | 050.BGR.VIKING ENERGY | 6" PE & REG STA - VIKING ENERGY - B.G. | -29907.46 | 0 | 273.95 | - | 0.001575% | 273.95 | 0 | 273.95 | 2008-10-01 | 2009-09-30 | 2008-01-09 | 2008-01-09 | 2009-01-08 | 2009-01-08
| 050.22199 | 050.2634.Franklin St Reg | Relocate Franklin St. Reg. Sta. | -29541.34 | 37.45 | -29578.79 | -78982% | -0.1698% | -29541.34 | 37.45 | -29578.79 | 2008-10-01 | 2009-09-30 | 2009-08-03 | 2009-08-03 | 2009-09-28 | 2009-09-28
| 050.20888 | 2738.LEB.INDST RD RELOCATION | RELOCATE 4" PE AND 2" PE ON INDUSTRIAL DR LEBANON | -22586.77 | -8938.61 | 31942.97 | -357.4% | 0.1322% | 23004.36 | -8938.61 | 31942.97 | 2008-10-01 | 2009-09-30 | 2008-08-18 | 2008-08-18 | 2009-08-18 | 2009-08-18
| 050.20767 | 050.2636.Mosleyville Odor Tank | Replace Mosleyville Odorant Tank | -18251.52 | 14156.64 | -3650.8 | -25.79% | 0.06039% | 10505.84 | 14156.64 | -3650.8 | 2008-10-01 | 2009-09-30 | 2008-07-08 | 2008-07-08 | 2008-09-28 | 2008-09-28
| 050.21824 | 050.2637.Friendship Rd Pub Imp | KY DOT road relocation McCracken County, KY | -12965.2 | -12965.2 | 0 | 0% | -0.07453% | -12965.2 | -12965.2 | 0 | 2008-10-01 | 2009-09-30 | 2009-01-26 | 2009-01-26 | 2009-09-30 | 2009-09-30
| 050.21655 | 050.2367.0918054-01 | MEC Forfeiture | -8485 | Not Budgeted | - | - | -0.04878% | -8485 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21547 | 050.2736.918650 | MEC Forfeiture | -8146 | Not Budgeted | - | - | -0.04683% | -8146 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-20 | 2008-10-20 | 2008-10-20 | 2008-10-20
| 050.21671 | 050.2637.0918422-01 | MEC Forfeiture | -7889 | Not Budgeted | - | - | -0.04535% | -7889 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.20889 | 2738.LEB.CALVARY RD 4 ST | RELOCATE 4" STEEL ON CALVARY RD FOR INDUSTRIAL DR ROAD EXTENSION | -7075.02 | -13134.5 | 19749.15 | -150.4% | 0.03802% | 6614.65 | -13134.5 | 19749.15 | 2008-10-01 | 2009-09-30 | 2008-08-18 | 2008-08-18 | 2009-08-18 | 2009-08-18
| 050.20233 | Meters - Outsourced | Blanket Project for Outsourced Meters | -6297.36 | 247776 | -135915.58 | -54.85% | 0.643% | 111860.42 | 247776 | -135915.58 | 2008-10-01 | 2009-09-30 | 2007-10-22 | 2007-10-22 | 2008-10-01 | 2008-10-01
| 050.19662 | 2739.SHELBYVILLE.EQUIPMENT | 2 - DITCH WITCH LOCATORS, 1 - FLAME PAK | -5873.75 | 15759 | 1689.72 | 10.72% | 0.1003% | 17448.72 | 15759 | 1689.72 | 2008-10-01 | 2009-09-30 | 2007-09-28 | 2007-09-28 | 2008-12-23 | 2008-12-23
| 050.21672 | 050.2637.0918389-01 | MEC Forfeiture | -5814 | Not Budgeted | - | - | -0.03342% | -5814 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21636 | 050.2737.0918022-01 | MEC Forfeiture | -5499 | Not Budgeted | - | - | -0.03161% | -5499 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21604 | 050.2652.0917165-01 | Mec Forfeirture | -5195 | Not Budgeted | - | - | -0.02986% | -5195 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21651 | 050.2637.0917535-01 | MEC Forfeiture | -5082 | Not Budgeted | - | - | -0.02921% | -5082 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21574 | 050.2737.0917947-01 | MEC Forfeiture | -5010.97 | Not Budgeted | - | - | -0.02881% | -5010.97 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21602 | 050.2637.0916433-01 | MEC Forfeiture | -4624 | Not Budgeted | - | - | -0.02658% | -4624 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21562 | 050.2737.0917834-01 | MEC Forfeiture | -4594 | Not Budgeted | - | - | -0.02641% | -4594 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21635 | 050.2737.0918029-01 | MEC Forfeiture | -4554 | Not Budgeted | - | - | -0.02618% | -4554 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21647 | 050.2637.0918103-01 | MEC Forfeiture | -4262 | Not Budgeted | - | - | -0.0245% | -4262 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21637 | 050.2637.0918322-01 | MEC Forfeiture | -3682 | Not Budgeted | - | - | -0.02117% | -3682 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21685 | 050.2637.0918561-01 | MEC Forfeiture | -3676 | Not Budgeted | - | - | -0.02113% | -3676 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.22286 | 050.3351.13104-01 | MEC Forfeiture | -3438.18 | Not Budgeted | - | - | -0.01976% | -3438.18 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21559 | 050.2737.0918039-01 | MEC Forfeiture | -3253 | Not Budgeted | - | - | -0.0187% | -3253 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.20482 | 050.2637.Sarakatsannis Ext | Sarakatsannis subd rev ext/ 1,370' - 2" PE for 16 new residential lots | -3230.65 | 6184.81 | -6184.74 | -100% | 4.024e-07% | 0.07 | 6184.81 | -6184.74 | 2008-10-01 | 2009-09-30 | 2008-02-20 | 2008-02-20 | 2009-02-20 | 2009-02-20
| 050.21607 | 050.2734.0916933-01 | MEC Forfeiture | -3140 | Not Budgeted | - | - | -0.01805% | -3140 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21659 | 050.2637.0918105-01 | MEC Forfeiture | -3068 | Not Budgeted | - | - | -0.01764% | -3068 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.19031 | 050.PAD.Starlite Subd Rev Ext | Install 1,480' - 2" PE for nine new commercial lots | -2943.32 | 4572 | 1210.39 | 26.47% | 0.03324% | 5782.39 | 4572 | 1210.39 | 2008-10-01 | 2009-09-30 | 2007-03-27 | 2007-03-27 | 2008-03-21 | 2008-03-21
| 050.21642 | 050.2637.0917993-01 | MEC Forfeiture | -2723 | Not Budgeted | - | - | -0.01565% | -2723 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.22163 | 050.2637.Ridge Run Rev Ext | Install 1,620 feet 2 inch poly for 24 new residential lots | -2618.65 | 7843 | -10461.65 | -133.4% | -0.01505% | -2618.65 | 7843 | -10461.65 | 2008-10-01 | 2009-09-30 | 2009-07-09 | 2009-07-09 | 2009-09-28 | 2009-09-28
| 050.22290 | 050.2638.20237-01 | MEC Forfeiture | -2602.27 | Not Budgeted | - | - | -0.01496% | -2602.27 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21605 | 050.2734.0917332-01 | MEC Forfeiture | -2572 | Not Budgeted | - | - | -0.01479% | -2572 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.22288 | 050.2637.18907-01 | MEC Forfeiture | -2489.55 | Not Budgeted | - | - | -0.01431% | -2489.55 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21684 | 050.2637.0918545-01 | MEC Forfeiture | -2481 | Not Budgeted | - | - | -0.01426% | -2481 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21550 | 050.2737.918075-01 | MEC Forfeiture | -2438 | Not Budgeted | - | - | -0.01401% | -2438 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-21 | 2008-10-21 | 2008-10-21 | 2008-10-21
| 050.21563 | 050.2737.0917948-01 | MEC Forfeiture | -2436 | Not Budgeted | - | - | -0.014% | -2436 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21679 | 050.2637.0918390-01 | MEC Forfeiture | -2395 | Not Budgeted | - | - | -0.01377% | -2395 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.20916 | TCSVC.MEA.EFM.Sister Schubert | EFM for Sister Schubert in Glasgow | -2324.93 | 4161 | -6485.93 | -155.9% | -0.01336% | -2324.93 | 4161 | -6485.93 | 2008-10-01 | 2009-09-30 | 2008-08-29 | 2008-08-29 | 2008-09-30 | 2008-09-30
| 050.21564 | 050.2737.0917788-01 | MEC Forfeiture | -2209 | Not Budgeted | - | - | -0.0127% | -2209 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.22292 | 050.2637.20708-01 | MEC Forfeiture | -2131.63 | Not Budgeted | - | - | -0.01225% | -2131.63 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21678 | 050.2637.0918387-01 | MEC Forfeiture | -2096 | Not Budgeted | - | - | -0.01205% | -2096 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21554 | 050.2737.917186-01 | MEC Forfeiture | -1944 | Not Budgeted | - | - | -0.01118% | -1944 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-21 | 2008-10-21 | 2008-10-21 | 2008-10-21
| 050.21600 | 050.2637.0916836-01 | MEC Forfeiture | -1907 | Not Budgeted | - | - | -0.01096% | -1907 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21634 | 050.2737.0918224-01 | MEC Forfeiture | -1861 | Not Budgeted | - | - | -0.0107% | -1861 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21586 | 050.2636.917384 | MEC Forfeiture | -1829 | Not Budgeted | - | - | -0.01051% | -1829 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-03 | 2008-11-03 | 2008-11-03 | 2008-11-03
| 050.21594 | 050.2734.091776-01 | MEC Forfeiture | -1818 | Not Budgeted | - | - | -0.01045% | -1818 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21656 | 050.2652.0918270-01 | MEC Forfeiture | -1756 | Not Budgeted | - | - | -0.01009% | -1756 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21568 | 050.2737.0917624-01 | MEC Forfeiture | -1684 | Not Budgeted | - | - | -0.00968% | -1684 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21673 | 050.2637.0918714-01 | MEC Forfeiture | -1601 | Not Budgeted | - | - | -0.009203% | -1601 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21640 | 050.2367.0918246-01 | MEC Forfeiture | -1532 | Not Budgeted | - | - | -0.008807% | -1532 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21652 | 050.2637.0918058-01 | MEC Forfeiture | -1498 | Not Budgeted | - | - | -0.008611% | -1498 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21561 | 050.2737.0917943-01 | MEC Forfeiture | -1476 | Not Budgeted | - | - | -0.008485% | -1476 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21565 | 050.2737.0917722-01 | MEC Forfeiture | -1445 | Not Budgeted | - | - | -0.008307% | -1445 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21570 | 050.2737.0917941-01 | MEC Forfeiture | -1442 | Not Budgeted | - | - | -0.008289% | -1442 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.22238 | 050.2635.Hwy 68 | Install 1600 feet 2" PE | -1398.42 | 384.63 | -1783.05 | -463.6% | -0.008039% | -1398.42 | 384.63 | -1783.05 | 2008-10-01 | 2009-09-30 | 2009-08-14 | 2009-08-14 | 2009-09-28 | 2009-09-28
| 050.21675 | 050.2637.0918787-01 | MEC Forfeiture | -1269 | Not Budgeted | - | - | -0.007295% | -1269 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21612 | 050.2636.0918375-01 | Mec Forf eiture | -1260 | Not Budgeted | - | - | -0.007243% | -1260 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21613 | 050.2636.0918449-01 | MEC Forfeiture | -1257 | Not Budgeted | - | - | -0.007226% | -1257 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.22291 | 050.2637.20704-01 | MEC Forfeiture | -1226.76 | Not Budgeted | - | - | -0.007052% | -1226.76 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21553 | 050.2737.917268-01 | MEC Forfeiture | -1206 | Not Budgeted | - | - | -0.006933% | -1206 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-21 | 2008-10-21 | 2008-10-21 | 2008-10-21
| 050.21658 | 050.2637.0918013-01 | MEC Forfeiture | -1171 | Not Budgeted | - | - | -0.006731% | -1171 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21593 | 050.2734.0917404-01 | MEC Forfeiture | -1124 | Not Budgeted | - | - | -0.006461% | -1124 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21641 | 050.2637.0918230-01 | MEC Forfeiture | -1086 | Not Budgeted | - | - | -0.006243% | -1086 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21597 | 050.2637.0916844-01 | MEC Forfeiture | -1071 | Not Budgeted | - | - | -0.006157% | -1071 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21646 | 050.2637.0918107-01 | MEC Forfeiture | -1064 | Not Budgeted | - | - | -0.006116% | -1064 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21676 | 050.2637.0918812-01 | MEC Forfeiture | -1033 | Not Budgeted | - | - | -0.005938% | -1033 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21608 | 050.2636.0918159-01 | MEC Forfeiture | -1031 | Not Budgeted | - | - | -0.005927% | -1031 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21677 | 050.2637.0918368-01 | MEC Forfeiture | -978.1 | Not Budgeted | - | - | -0.005623% | -978.1 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21611 | 050.2734.0916246-01 | MEC Forfeiture | -940 | Not Budgeted | - | - | -0.005404% | -940 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.18349 | Madisonville 07 Non Growth | Madisonville 07 Non Growth Functional | -932.58 | Not Budgeted | - | - | 3.736% | 649943.24 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20890 | 050.2609.Retire Dehy Plant | Retire Grandview Dehy Plant | -905.5 | 5988.4 | -577.24 | -9.639% | 0.03111% | 5411.16 | 5988.4 | -577.24 | 2008-10-01 | 2009-09-30 | 2008-08-18 | 2008-08-18 | 2008-09-28 | 2008-09-28
| 050.20241 | 050.2637.Regina Drive Rev Ext | Install 575' - 2" PE for one new residential customer | -904.72 | 1859.99 | 524.56 | 28.2% | 0.01371% | 2384.55 | 1859.99 | 524.56 | 2008-10-01 | 2009-09-30 | 2007-10-23 | 2007-10-23 | 2008-10-23 | 2008-10-23
| 050.21680 | 050.2637.0918439-01 | MEC Forfeiture | -865 | Not Budgeted | - | - | -0.004972% | -865 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21681 | 050.2637.0918455-01 | MEC Forfeiture | -856 | Not Budgeted | - | - | -0.004921% | -856 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21643 | 050.2637.0918059-01 | MEC Forfeiture | -821 | Not Budgeted | - | - | -0.00472% | -821 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21686 | 050.2637.0918573-01 | MEC Forfeiture | -754 | Not Budgeted | - | - | -0.004334% | -754 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21674 | 050.2637.0918760-01 | MEC Forfeiture | -710 | Not Budgeted | - | - | -0.004081% | -710 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21609 | 050.2636.0918158-01 | MEC Forfeiture | -698 | Not Budgeted | - | - | -0.004012% | -698 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21601 | 050.2637.0916925-01 | MEC Forfeiture | -688 | Not Budgeted | - | - | -0.003955% | -688 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21660 | 050.2637.0918119-01 | MEC Forfeiture | -684 | Not Budgeted | - | - | -0.003932% | -684 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21592 | 050.2734.0917863-01 | MEC Forfeiture | -678 | Not Budgeted | - | - | -0.003897% | -678 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21599 | 050.2637.0916845-01 | MEC Forfeiture | -662 | Not Budgeted | - | - | -0.003806% | -662 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21560 | 050.2737.0918080-01 | MEC Forfeiture | -625 | Not Budgeted | - | - | -0.003593% | -625 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21610 | 050.2734.0916072-01 | MEC Forfeiture | -585 | Not Budgeted | - | - | -0.003363% | -585 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21596 | 050.2637.0916860-01 | MEC Forfeiture | -570 | Not Budgeted | - | - | -0.003277% | -570 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21598 | 050.2637.0916589-01 | MEC Forfeiture | -568 | Not Budgeted | - | - | -0.003265% | -568 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21644 | 050.2637.0917988-01 | MEC Forfeiture | -544 | Not Budgeted | - | - | -0.003127% | -544 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21603 | 050.2637.0916913-01 | MEC Forfeiture | -542 | Not Budgeted | - | - | -0.003116% | -542 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.20488 | 050.BGR.GLS.DART 9 METER SET | DART #9 TURBINE METER, SET & REGULATORS | -477.74 | 46551.02 | 16642.27 | 35.75% | 0.3633% | 63193.29 | 46551.02 | 16642.27 | 2008-10-01 | 2009-09-30 | 2008-02-22 | 2008-02-22 | 2009-02-22 | 2009-02-22
| 050.21546 | 050.2736.918778 | MEC Forfeiture | -457 | Not Budgeted | - | - | -0.002627% | -457 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-20 | 2008-10-20 | 2008-10-20 | 2008-10-20
| 050.21606 | 050.2734.0917140-01 | MEC Forfeiture | -442 | Not Budgeted | - | - | -0.002541% | -442 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21639 | 050.2637.0918221-01 | MEC Forfeiture | -426 | Not Budgeted | - | - | -0.002449% | -426 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21549 | 050.2737.918081-01 | MEC Forfeiture | -424 | Not Budgeted | - | - | -0.002437% | -424 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-21 | 2008-10-21 | 2008-10-21 | 2008-10-21
| 050.21567 | 050.2737.0917621-01 | MEC Forfeiture | -422 | Not Budgeted | - | - | -0.002426% | -422 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21595 | 050.2637.0916837-01 | MEC Forfeiture | -421 | Not Budgeted | - | - | -0.00242% | -421 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-04 | 2008-11-04 | 2008-11-04 | 2008-11-04
| 050.21551 | 050.2737.917111-01 | MEC Forfeiture | -358 | Not Budgeted | - | - | -0.002058% | -358 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-21 | 2008-10-21 | 2008-10-21 | 2008-10-21
| 050.18339 | Glasgow 07 Non Growth | Glasgow 07 Non Growth Functional | -349.02 | Not Budgeted | - | - | 3.33% | 579264.99 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.21983 | 050.2637.Lady Karen Ext | Install 580 feet of 2 inch poly for two existing customers | -314.26 | 2845.37 | -3159.63 | -111% | -0.001807% | -314.26 | 2845.37 | -3159.63 | 2008-10-01 | 2009-09-30 | 2009-04-13 | 2009-04-13 | 2009-06-19 | 2009-06-19
| 050.22067 | 050.2634.Tombs Lane | Install 315 feet 2 Inch PE | -287.49 | 1459.44 | -1746.93 | -119.7% | -0.001653% | -287.49 | 1459.44 | -1746.93 | 2008-10-01 | 2009-09-30 | 2009-06-03 | 2009-06-03 | 2009-09-28 | 2009-09-28
| 050.21654 | 050.2637.0918053-01 | MEC Forfeiture | -269 | Not Budgeted | - | - | -0.001546% | -269 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21687 | 050.2637.09183670-1 | MEC Forfeiture | -258 | Not Budgeted | - | - | -0.001483% | -258 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-18 | 2008-11-18 | 2008-11-18 | 2008-11-18
| 050.21569 | 050.2737.0917097-01 | MEC Forfeiture | -257 | Not Budgeted | - | - | -0.001477% | -257 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.21879 | 050.BGR.FIELDS DR. 2" EXT | 375 FT. OF 2" PE - FIELDS DR. - B.G. | -231.66 | 1102 | -1333.66 | -121% | -0.001332% | -231.66 | 1102 | -1333.66 | 2008-10-01 | 2009-09-30 | 2009-02-18 | 2009-02-18 | 2010-02-18 | 2010-02-18
| 050.21748 | 050.2637.New Holt Rd Rev Ext | Install 675' - 2" PE for new Montgomery Gardens greenhouse | -227.92 | 1848 | -2075.92 | -112.3% | -0.00131% | -227.92 | 1848 | -2075.92 | 2008-10-01 | 2009-09-30 | 2008-12-05 | 2008-12-05 | 2009-09-18 | 2009-09-18
| 050.21638 | 050.2637.0918267-01 | MEC Forfeiture | -227 | Not Budgeted | - | - | -0.001305% | -227 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21575 | 050.2737.0918069-01 | MEC Forfeiture | -193 | Not Budgeted | - | - | -0.001109% | -193 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-10-27 | 2008-10-27 | 2008-10-27 | 2008-10-27
| 050.22284 | 050.2636.12652-01 | MEC Forfeiture | -188 | Not Budgeted | - | - | -0.001081% | -188 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21661 | 050.2637.0917996-01 | MEC Forfeiture | -187 | Not Budgeted | - | - | -0.001075% | -187 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.22289 | 050.2637.19338-01 | MEC Forfeiture | -176.6 | Not Budgeted | - | - | -0.001015% | -176.6 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-08-27 | 2009-08-27 | 2009-08-27 | 2009-08-27
| 050.21653 | 050.2637.0918011-01 | MEC Forfeiture | -171 | Not Budgeted | - | - | -0.000983% | -171 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.21645 | 050.2637.0918108-01 | MEC Forfeiture | -137 | Not Budgeted | - | - | -0.0007875% | -137 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2008-11-13 | 2008-11-13
| 050.19207 | 050.BGR.RUSS.LOGAN PUR 6" | 60 FT. OF 6" STL. - LOGAN PURCHASE STATION | -68.13 | 24659 | 1612.42 | 6.539% | 0.151% | 26271.42 | 24659 | 1612.42 | 2008-10-01 | 2009-09-30 | 2007-05-17 | 2007-05-17 | 2008-05-17 | 2008-05-17
| 040.12765 | Glasgow 06 Non Growth | Glasgow 06 Non Growth | -37.42 | Not Budgeted | - | - | 3.815% | 663661.87 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-10-07 | 2005-10-07 | 2009-05-13 | 2009-05-13
| 050.20364 | 050.BGR.CHESTNUT ST REPLC | 1000,1100 & 1200 BLKS. - CHESTNUT ST REPLC. - B.G. | -10.79 | 242742 | 48099.08 | 19.81% | 1.672% | 290841.08 | 242742 | 48099.08 | 2008-10-01 | 2009-09-30 | 2007-12-21 | 2007-12-21 | 2008-12-21 | 2008-12-21
| OH.050.17884 | WKG State A&G Overhead | WKG State A&G Overhead Project | 0 | 0 | 0 | - | -1.071e-14% | -1.8626e-09 | 0 | -1.8626e-09 | 2008-10-01 | 2009-09-30 | Over | head | Over | head
| 050.19670 | 050.3351.F I Unit | Purchase F I unit DP-4 Heath | 0.33 | 7995.58 | -1447.28 | -18.1% | 0.03764% | 6548.3 | 7995.58 | -1447.28 | 2008-10-01 | 2009-09-30 | 2007-10-01 | 2007-10-01 | 2008-10-06 | 2008-10-06
| 050.20963 | Utility Trailer | Measurement Dept. Utility Trailer | 10.83 | 3675 | -770.22 | -20.96% | 0.0167% | 2904.78 | 3675 | -770.22 | 2008-10-01 | 2009-09-30 | 2008-09-09 | 2008-09-09 | 2008-09-30 | 2008-09-30
| 050.20452 | 050.GLS.METERS-REGS-RET. | METERS - REGULATOES - RETIREMENTS - GLASGOW | 22.11 | 28349 | -27322.82 | -96.38% | 0.005899% | 1026.18 | 28349 | -27322.82 | 2008-10-01 | 2009-09-30 | 2008-02-07 | 2008-02-07 | 2009-02-07 | 2009-02-07
| 050.20624 | 2739.MIDLAND TRAIL-LEAK | REPLACE 2" STEEL ACROSS HWY 60 WITH 2" PE BEHIND COMMWEALTH B&T | 44.07 | 11820 | -2498.39 | -21.14% | 0.05359% | 9321.61 | 11820 | -2498.39 | 2008-10-01 | 2009-09-30 | 2008-04-30 | 2008-04-30 | 2008-09-28 | 2008-09-28
| 050.18653 | 050.2612.METER REBUILD | REBUILD METERS FOR METER DEPARTMENT | 48.5 | 249936.11 | -138517.93 | -55.42% | 0.6405% | 111418.18 | 249936.11 | -138517.93 | 2008-10-01 | 2009-09-30 | 2006-11-08 | 2006-11-08 | 2007-11-07 | 2007-11-07
| 050.20382 | 050.BGR.HOP.METER-REG. | METERS & REGULATORS - HOPKINSVILLE | 52.75 | 44155 | -35678.61 | -80.8% | 0.04873% | 8476.39 | 44155 | -35678.61 | 2008-10-01 | 2009-09-30 | 2008-01-08 | 2008-01-08 | 2009-01-07 | 2009-01-07
| 050.20601 | 050.2637.Ascot Downs II | 530' revenue extension for Rodney Vaughn for 18 customers | 69.76 | 2989.4 | 731.45 | 24.47% | 0.02139% | 3720.85 | 2989.4 | 731.45 | 2008-10-01 | 2009-09-30 | 2008-04-21 | 2008-04-21 | 2009-04-02 | 2009-04-02
| 050.20485 | 050.2609.St. Charles Muffler | Install new Muffler St. Charles Compressor | 95.05 | 22022.75 | -1124 | -5.104% | 0.1201% | 20898.75 | 22022.75 | -1124 | 2008-10-01 | 2009-09-30 | 2008-02-21 | 2008-02-21 | 2008-09-28 | 2008-09-28
| 050.21902 | 2738.LEB.COMMERCE DR | 550' OF 4" PE FOR FUEL TOTAL SYS | 102.72 | 9085 | -8982.28 | -98.87% | 0.0005905% | 102.72 | 9085 | -8982.28 | 2008-10-01 | 2009-09-30 | 2009-03-02 | 2009-03-02 | 2010-03-02 | 2010-03-02
| 050.20777 | TechSvr.Mea.EFM.Modine | EFM for Modine in Harrodsburg | 106.9 | 4161 | -2438.69 | -58.61% | 0.009901% | 1722.31 | 4161 | -2438.69 | 2008-10-01 | 2009-09-30 | 2008-07-10 | 2008-07-10 | 2008-09-30 | 2008-09-30
| 050.20821 | 050.BGR 7TH & CENTER RELOC | 1700 FT. OF 2" PE 7TH & CENTER RELOC. - B.G. | 120.57 | 0 | 3413.64 | - | 0.01962% | 3413.64 | 0 | 3413.64 | 2008-10-01 | 2009-09-30 | 2008-07-24 | 2008-07-24 | 2009-07-24 | 2009-07-24
| 050.20513 | TchSvr.Mea.EFM Logan Uniform | EFM for Logan Uniform in Shelbyville | 132.4 | 4161 | -1378.19 | -33.12% | 0.016% | 2782.81 | 4161 | -1378.19 | 2008-10-01 | 2009-09-30 | 2008-03-06 | 2008-03-06 | 2008-09-30 | 2008-09-30
| 050.20423 | TechServ.Meas.EFM.Hitachi | EFM for Hitachi in Harrodsburg going transportation | 141.67 | 4161 | -1182.87 | -28.43% | 0.01712% | 2978.13 | 4161 | -1182.87 | 2008-10-01 | 2009-09-30 | 2008-01-25 | 2008-01-25 | 2008-09-30 | 2008-09-30
| 050.20945 | 2737.DP-4 HEATH CONSUL FI.CGI | PURCHASE DP-4 FI.CGI FOR SD SURVEY | 150.23 | 7198 | 2443.24 | 33.94% | 0.05542% | 9641.24 | 7198 | 2443.24 | 2008-10-01 | 2009-09-30 | 2008-09-05 | 2008-09-05 | 2008-12-12 | 2008-12-12
| 050.22033 | EFM for Union City BPI | Replace BPI with EFM and wireless communication at Union City Purchase Stations | 154.24 | 11033 | -10878.76 | -98.6% | 0.0008866% | 154.24 | 11033 | -10878.76 | 2008-10-01 | 2009-09-30 | 2009-05-18 | 2009-05-18 | 2009-09-30 | 2009-09-30
| 050.20324 | 2739.MEADOW GLEN SEC II | INSTALL 900' OF 2" PE AND 3 SERVICES | 177.8 | 7632 | 3022.21 | 39.6% | 0.06125% | 10654.21 | 7632 | 3022.21 | 2008-10-01 | 2009-09-30 | 2007-11-29 | 2007-11-29 | 2008-11-29 | 2008-11-29
| 040.12758 | Tim Montgomery MEC Forfeiture | Tim Montgomery MEC Forfeiture | 187 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-30 | 2005-09-30 | 2005-09-30 | 2005-09-30
| 050.20592 | Measurement Transmitters | Misc. Pres. & Temp. Transmitters | 218.23 | 7812 | 10614.65 | 135.9% | 0.1059% | 18426.65 | 7812 | 10614.65 | 2008-10-01 | 2009-09-30 | 2008-04-18 | 2008-04-18 | 2008-09-30 | 2008-09-30
| 050.20892 | 050.BGR.HOP.ELECTROFUSE EQUIP | ELECTROFUSION EQUIPMENT - HOPKINSVILLE | 271.27 | 5182 | 1244.93 | 24.02% | 0.03695% | 6426.93 | 5182 | 1244.93 | 2008-10-01 | 2009-09-30 | 2008-08-19 | 2008-08-19 | 2009-08-19 | 2009-08-19
| 050.22213 | 050.2637.Derby Cr Rev Ext | Install 180 feet of 2 inch PE for one new and one vacant residential | 287.61 | 1580.5 | -1292.89 | -81.8% | 0.001653% | 287.61 | 1580.5 | -1292.89 | 2008-10-01 | 2009-09-30 | 2009-08-10 | 2009-08-10 | 2009-09-28 | 2009-09-28
| 040.12681 | Patrica Higdon MEC Forfeiture | Patrica Higdon MEC Forfeiture | 308 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.20833 | 050.2634.TB Valve Rplmt | Replace valves on Slaughters TB | 311.6 | 11560.74 | -1059.83 | -9.167% | 0.06036% | 10500.91 | 11560.74 | -1059.83 | 2008-10-01 | 2009-09-30 | 2008-07-28 | 2008-07-28 | 2008-09-28 | 2008-09-28
| 040.12739 | AD Gaddis MEC Forfeiture | AD Gaddis MEC Forfeiture | 341 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-29 | 2005-09-29 | 2005-09-30 | 2005-09-30
| 050.20770 | 2737.HAR.SKYLARS LANDING PH I | INSTALL 1800' OF 2" PE FOR SKYLARS LANDINING | 382.1 | 10475 | 4793.92 | 45.77% | 0.08777% | 15268.92 | 10475 | 4793.92 | 2008-10-01 | 2009-09-30 | 2008-07-09 | 2008-07-09 | 2009-07-09 | 2009-07-09
| 050.22353 | 050.KY.GlasgowGrowthFunct2010 | 050.KY.GlasgowGrowthFunct2010 | 400.88 | Not Budgeted | - | - | 0.002304% | 400.88 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22439 | 050.KY.MayfieldLeakFunct2010 | 050.KY.MayfieldLeakFunct2010 | 407.87 | Not Budgeted | - | - | 0.002345% | 407.87 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20704 | 050.2637.Barkley Field I | 730' rev ext for new National Guard armory | 410.06 | 18550 | -16074.79 | -86.66% | 0.01423% | 2475.21 | 18550 | -16074.79 | 2008-10-01 | 2009-09-30 | 2008-06-12 | 2008-06-12 | 2009-06-12 | 2009-06-12
| 050.20243 | 050.2637.Westwood Rev Ext | Install 3,160' - 2" PE into Westwood Hills Subdivision for 65 new residential lots | 418.51 | 16447.63 | 3110.64 | 18.91% | 0.1124% | 19558.27 | 16447.63 | 3110.64 | 2008-10-01 | 2009-09-30 | 2007-10-24 | 2007-10-24 | 2008-10-24 | 2008-10-24
| 050.22302 | 050.2637.Eva Dr Rev Ext | 200 feet for four residential customers | 422.85 | 1928.6 | -1505.75 | -78.07% | 0.002431% | 422.85 | 1928.6 | -1505.75 | 2008-10-01 | 2009-09-30 | 2009-09-02 | 2009-09-02 | 2009-09-18 | 2009-09-18
| 050.22254 | 2738.LEB.CVILLE RD-VILLAGE | REPLACE 200ft OF 2in STEEL - LEAKAGE | 438.11 | 16340.6 | -15902.49 | -97.32% | 0.002518% | 438.11 | 16340.6 | -15902.49 | 2008-10-01 | 2009-09-30 | 2009-08-19 | 2009-08-19 | 2009-10-01 | 2009-10-01
| 050.20575 | 050.2609.Grandview Fence | Install security fence at Grandview | 441.53 | 24617.16 | 157.8 | 0.641% | 0.1424% | 24774.96 | 24617.16 | 157.8 | 2008-10-01 | 2009-09-30 | 2008-04-03 | 2008-04-03 | 2008-09-28 | 2008-09-28
| 050.20933 | 050.BGR.GLS.ELECTRO FUSE EQUIP | 4" ELECTROFUSION EQUIPMENT - GLASGOW | 459.34 | 6406 | 27.16 | 0.424% | 0.03698% | 6433.16 | 6406 | 27.16 | 2008-10-01 | 2009-09-30 | 2008-09-03 | 2008-09-03 | 2008-08-03 | 2008-08-03
| 050.20723 | 050.2636.Village Run Phase 3 | Install 995' 2" Pe | 463.3 | 6929.8 | -1948.74 | -28.12% | 0.02863% | 4981.06 | 6929.8 | -1948.74 | 2008-10-01 | 2009-09-30 | 2008-06-20 | 2008-06-20 | 2008-09-28 | 2008-09-28
| 050.20563 | 050.2609.Bon Harbor Fence | Install new security fence Bon Harbor | 464.57 | 24473.2 | -747.74 | -3.055% | 0.1364% | 23725.46 | 24473.2 | -747.74 | 2008-10-01 | 2009-09-30 | 2008-04-01 | 2008-04-01 | 2008-09-28 | 2008-09-28
| 050.22146 | 050.2637.Star Hill Dr Rev Ext | Install 460 feet of 2 inch plastic main for one new residential customer | 502.38 | 749.92 | -247.54 | -33.01% | 0.002888% | 502.38 | 749.92 | -247.54 | 2008-10-01 | 2009-09-30 | 2009-07-06 | 2009-07-06 | 2009-09-28 | 2009-09-28
| 050.20713 | 050.2637.Palma Bulding | The puchase of a building to cover the ROC and electronics | 504.11 | 18703.2 | -4485.74 | -23.98% | 0.08173% | 14217.46 | 18703.2 | -4485.74 | 2008-10-01 | 2009-09-30 | 2008-06-16 | 2008-06-16 | 2009-06-15 | 2009-06-15
| 050.22122 | TchSvr.Mea.EFM.Echo Lake Foods | EFM for Echo Lake Foods in Owensboro | 517.34 | 4140 | -3622.66 | -87.5% | 0.002974% | 517.34 | 4140 | -3622.66 | 2008-10-01 | 2009-09-30 | 2009-06-25 | 2009-06-25 | 2009-09-30 | 2009-09-30
| 040.12740 | Wallace Sapp MEC Forfeiture | Wallace Sapp MEC Forfeiture | 520 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-29 | 2005-09-29 | 2005-09-30 | 2005-09-30
| 050.22193 | 2737.W BUFORD RELOCATE | INSTALL 2in PE AND RETIRE ON BAUGHMAN BETWEEN GOVERNMENT ALLEY AND W BUFORD | 573.48 | 7855.9 | -7282.42 | -92.7% | 0.003297% | 573.48 | 7855.9 | -7282.42 | 2008-10-01 | 2009-09-30 | 2009-07-29 | 2009-07-29 | 2010-10-01 | 2010-10-01
| 050.20252 | 050.BGR.BRITE WAY 2" PE | 140 FT. OF 2" PE - BRITW WAY - BOWLING GREEN | 592.33 | 2443 | -1451.09 | -59.4% | 0.005702% | 991.91 | 2443 | -1451.09 | 2008-10-01 | 2009-09-30 | 2007-10-29 | 2007-10-29 | 2008-10-29 | 2008-10-29
| 040.12715 | Mike Duvall MEC Forfeiture | Mike Duvall MEC Forfeiture | 632 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-29 | 2005-09-29 | 2005-09-29 | 2005-09-29
| 050.20877 | 2738.WOODLAND HEIGHTS APPROACH | INSTALL 925' OF 2" PE FROM FROEST HILLS TO WOODLAND HEIGHTS PARKWAY | 640.92 | 3585 | -6126.08 | -170.9% | -0.01461% | -2541.08 | 3585 | -6126.08 | 2008-10-01 | 2009-09-30 | 2008-08-14 | 2008-08-14 | 2009-08-15 | 2009-08-15
| 050.21536 | 2738.MARK GRAY APTS II | INSTALL 270' OF 2" PE FOR 4 DUPLEXES | 641.65 | 3650 | -3008.35 | -82.42% | 0.003689% | 641.65 | 3650 | -3008.35 | 2008-10-01 | 2009-09-30 | 2008-10-17 | 2008-10-17 | 2009-10-17 | 2009-10-17
| 050.20625 | 050.2636.Summer Valley Ln. | Install 956' 2" PE | 655.94 | 5713.57 | 2592.46 | 45.37% | 0.04775% | 8306.03 | 5713.57 | 2592.46 | 2008-10-01 | 2009-09-30 | 2008-04-30 | 2008-04-30 | 2008-09-28 | 2008-09-28
| 050.22359 | 050.KY.PrincetnGrowthFunct2010 | 050.KY.PrincetnGrowthFunct2010 | 678.01 | Not Budgeted | - | - | 0.003898% | 678.01 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 040.12738 | Eddie Obanion MEC Forfeiture | Eddie Obanion MEC Forfeiture | 688 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-29 | 2005-09-29 | 2005-09-30 | 2005-09-30
| 050.22356 | 050.KY.CampbellGrowthFunct2010 | 050.KY.CampbellGrowthFunct2010 | 712.95 | Not Budgeted | - | - | 0.004098% | 712.95 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22420 | 050.2634.Hwy 181 Retirement | Retire 2900 feet Bare 4 Inch Stl. | 723.72 | 2125.51 | -1401.79 | -65.95% | 0.00416% | 723.72 | 2125.51 | -1401.79 | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2009-09-02 | 2009-09-02
| 050.22431 | 050.KY.HopkinsLeakFunct2010 | 050.KY.HopkinsLeakFunct2010 | 760.81 | Not Budgeted | - | - | 0.004374% | 760.81 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 040.12741 | Janice Stinnett MEC Forfeiture | Janice Stinnett MEC Forfeiture | 768 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-29 | 2005-09-29 | 2005-09-30 | 2005-09-30
| 050.22202 | TchSvr.Mea.EFM Pinelake Med | EFM for Pinelake Medical Center | 771.3 | 4140 | -3368.7 | -81.37% | 0.004434% | 771.3 | 4140 | -3368.7 | 2008-10-01 | 2009-09-30 | 2009-08-03 | 2009-08-03 | 2009-09-30 | 2009-09-30
| 050.22203 | TchSvr.EFM.Christian Fis. Crt | EFM for Christian County Fiscal Court | 771.3 | 4140 | -3368.7 | -81.37% | 0.004434% | 771.3 | 4140 | -3368.7 | 2008-10-01 | 2009-09-30 | 2009-08-03 | 2009-08-03 | 2009-09-30 | 2009-09-30
| 050.20426 | 050.2636.Keenland Phase 1 | Install 2,802' 2" PE | 819.96 | 16564.8 | 2814.47 | 16.99% | 0.1114% | 19379.27 | 16564.8 | 2814.47 | 2008-10-01 | 2009-09-30 | 2008-01-25 | 2008-01-25 | 2008-07-31 | 2008-07-31
| 050.20690 | 050.BGR.BARRY ST RET. | 410 FT. BARE STEEL RETIREMENT - BARRY ST. - B.G. | 821.5 | 874 | -52.5 | -6.007% | 0.004722% | 821.5 | 874 | -52.5 | 2008-10-01 | 2009-09-30 | 2008-06-03 | 2008-06-03 | 2009-06-03 | 2009-06-03
| 050.20860 | 050.BGR.RUSS.PUR 2 REG. REPLC. | rUSSELLVILLE PURCHASE #2 REGULATOR REPLACEMENT | 852.03 | 14563 | -2503.07 | -17.19% | 0.06933% | 12059.93 | 14563 | -2503.07 | 2008-10-01 | 2009-09-30 | 2008-08-08 | 2008-08-08 | 2009-08-08 | 2009-08-08
| 050.22301 | 050.2637.Allegheny Rd Ext | install 360 feet 2 inch pe for one existing residential | 862.61 | 2418.84 | -1556.23 | -64.34% | 0.004959% | 862.61 | 2418.84 | -1556.23 | 2008-10-01 | 2009-09-30 | 2009-09-02 | 2009-09-02 | 2009-09-17 | 2009-09-17
| 050.22188 | 2738.GRB.DURHAM ST RETIREMENT | RETIRE 452ft OF 2in BARE STEEL ON DURHAM ST BETWEEN CAOKLY AND WILSON IN GREENSBURG KY | 864.2 | 5813.56 | -4949.36 | -85.13% | 0.004968% | 864.2 | 5813.56 | -4949.36 | 2008-10-01 | 2009-09-30 | 2009-07-27 | 2009-07-27 | 2009-10-01 | 2009-10-01
| 050.20515 | 050.2636.Electronic Recorders | Install 21 Electronic Recorders | 895.18 | 36009.67 | 8706.83 | 24.18% | 0.2571% | 44716.5 | 36009.67 | 8706.83 | 2008-10-01 | 2009-09-30 | 2008-03-06 | 2008-03-06 | 2008-09-28 | 2008-09-28
| 050.22362 | 050.KY.MayfieldGrowthFunct2010 | 050.KY.MayfieldGrowthFunct2010 | 906.12 | Not Budgeted | - | - | 0.005209% | 906.12 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22166 | TchSvrMeaEFM Circle H Farm | EFM for Circle H Farms in Madisonville | 944.29 | 4140 | -3195.71 | -77.19% | 0.005428% | 944.29 | 4140 | -3195.71 | 2008-10-01 | 2009-09-30 | 2009-07-14 | 2009-07-14 | 2009-09-30 | 2009-09-30
| 050.22167 | TchSvrMeaEFM Hillside Farms | EFM for Hillside Farms in Madisonville | 944.29 | 4140 | -3195.71 | -77.19% | 0.005428% | 944.29 | 4140 | -3195.71 | 2008-10-01 | 2009-09-30 | 2009-07-14 | 2009-07-14 | 2009-09-30 | 2009-09-30
| 050.22168 | TchSvrMeaEFMEarlington Poultry | EFM for Earlington Poultry in Madisonville | 944.29 | 4140 | -3195.71 | -77.19% | 0.005428% | 944.29 | 4140 | -3195.71 | 2008-10-01 | 2009-09-30 | 2009-07-14 | 2009-07-14 | 2009-09-30 | 2009-09-30
| 050.20937 | 050.BGR.PIPE JEEP | PIPE JEEP - BOWLING GREEN | 945.32 | 5912 | 7452.17 | 126.1% | 0.07682% | 13364.17 | 5912 | 7452.17 | 2008-10-01 | 2009-09-30 | 2008-09-03 | 2008-09-03 | 2009-09-03 | 2009-09-03
| 050.21921 | TchSvr.Mea.EFM.Specialty Foods | EFM for Specialty Food Group in Owensboro | 946.51 | 4140 | -3193.49 | -77.14% | 0.005441% | 946.51 | 4140 | -3193.49 | 2008-10-01 | 2009-09-30 | 2009-03-11 | 2009-03-11 | 2009-09-30 | 2009-09-30
| 050.20743 | 050.BGR.E 8TH 3" BARE RET. | RETIRE 335 FT. OF 3' BARE STEEL - E 8TH - B.G. | 950.25 | 1807 | -237.28 | -13.13% | 0.009024% | 1569.72 | 1807 | -237.28 | 2008-10-01 | 2009-09-30 | 2008-06-26 | 2008-06-26 | 2009-06-26 | 2009-06-26
| 050.21617 | 050.BGR.HOP.COMMERCE CT. EXT. | 300 FT. OF 4" PE - COMMERCE CT. - WHAYNE SUPPLY - HOPK. | 1018.99 | 7302 | -6283.01 | -86.05% | 0.005858% | 1018.99 | 7302 | -6283.01 | 2008-10-01 | 2009-09-30 | 2008-11-06 | 2008-11-06 | 2009-11-06 | 2009-11-06
| 050.21750 | 050.2637.Brookhaven III | 525' - 2" PE revenue extension for three new lots in Brookhaven subd | 1027.55 | 1481.2 | -453.65 | -30.63% | 0.005907% | 1027.55 | 1481.2 | -453.65 | 2008-10-01 | 2009-09-30 | 2008-12-08 | 2008-12-08 | 2009-09-30 | 2009-09-30
| 050.21846 | 050.2638.Emergency Equip | Emergency equip purchased during ice storm | 1080.43 | 8406.5 | -7326.07 | -87.15% | 0.006211% | 1080.43 | 8406.5 | -7326.07 | 2008-10-01 | 2009-09-30 | 2009-02-03 | 2009-02-03 | 2009-09-30 | 2009-09-30
| 050.22436 | 050.KY.PrincetonLeakFunct2010 | 050.KY.PrincetonLeakFunct2010 | 1111.45 | Not Budgeted | - | - | 0.006389% | 1111.45 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20894 | 2739.CARDINAL OAKS PATIO PH II | INSTALL 1200' OF 2" PE CARDINAL OAKS PH II | 1113.32 | 11094 | -7057.01 | -63.61% | 0.02321% | 4036.99 | 11094 | -7057.01 | 2008-10-01 | 2009-09-30 | 2008-08-21 | 2008-08-21 | 2009-08-21 | 2009-08-21
| 050.21721 | 050.2635.Northfield Dr. | Install 100' 2" PE | 1154.76 | 1870.78 | -716.02 | -38.27% | 0.006638% | 1154.76 | 1870.78 | -716.02 | 2008-10-01 | 2009-09-30 | 2008-11-24 | 2008-11-24 | 2009-04-01 | 2009-04-01
| 050.22214 | 050.2638.N Sutton Ln Rev Ext | Install 160 feet of 2 inch ply pipe for one existing residential customer requesting gas service. | 1158.08 | 1074.89 | 83.19 | 7.739% | 0.006657% | 1158.08 | 1074.89 | 83.19 | 2008-10-01 | 2009-09-30 | 2009-08-10 | 2009-08-10 | 2009-09-28 | 2009-09-28
| 050.20714 | 050.2634.Slaughters 2" RPLMT | Replace exposed 2" Stl. with 2" PE | 1177.03 | 11334.87 | -3708.65 | -32.72% | 0.04384% | 7626.22 | 11334.87 | -3708.65 | 2008-10-01 | 2009-09-30 | 2008-06-16 | 2008-06-16 | 2008-09-28 | 2008-09-28
| 050.21998 | 050.2637.Thornberry Main Ext | install 100 feet of 2 inch plastic for one existing residential customer requesting gas service | 1238.11 | 1023.16 | 214.95 | 21.01% | 0.007117% | 1238.11 | 1023.16 | 214.95 | 2008-10-01 | 2009-09-30 | 2009-04-23 | 2009-04-23 | 2009-09-28 | 2009-09-28
| 050.20708 | 050.2637.Barkley Field II | 670' extension for new Paxton Media Group hanger | 1250.23 | 8625 | -1523.07 | -17.66% | 0.04083% | 7101.93 | 8625 | -1523.07 | 2008-10-01 | 2009-09-30 | 2008-06-13 | 2008-06-13 | 2009-06-12 | 2009-06-12
| 050.21974 | 050.2636 South Hampton Rd. | Install 100 feet 2 in PE | 1264.48 | 1771.8 | -507.32 | -28.63% | 0.007269% | 1264.48 | 1771.8 | -507.32 | 2008-10-01 | 2009-09-30 | 2009-04-06 | 2009-04-06 | 2009-08-04 | 2009-08-04
| 050.21968 | Tch.Svr.Mea.EFM.Carhart, Inc. | EFM for Carhart, Inc. in Hanson | 1269.2 | 4140 | -2870.8 | -69.34% | 0.007296% | 1269.2 | 4140 | -2870.8 | 2008-10-01 | 2009-09-30 | 2009-04-03 | 2009-04-03 | 2009-09-30 | 2009-09-30
| 050.20350 | 2739.LAW.ARBOR VIEW LANE | INSTALL 200' OF 2" PE OFF OF HWY 151 ARBOR VIEW LN | 1281.78 | 2760 | -1478.22 | -53.56% | 0.007368% | 1281.78 | 2760 | -1478.22 | 2008-10-01 | 2009-09-30 | 2007-12-12 | 2007-12-12 | 2008-09-09 | 2008-09-09
| 050.21969 | Tch.Svr.Mea.EFM.Daicel Tech. | EFM for Daicel Safety Technlogies in Beaver Dam | 1300.48 | 4140 | -2839.52 | -68.59% | 0.007476% | 1300.48 | 4140 | -2839.52 | 2008-10-01 | 2009-09-30 | 2009-04-03 | 2009-04-03 | 2009-09-30 | 2009-09-30
| 050.21722 | 050.2637.Tyree Rd Rev Ext | 340' revenue extension for four | 1304 | 1640.02 | -336.02 | -20.49% | 0.007496% | 1304 | 1640.02 | -336.02 | 2008-10-01 | 2009-09-30 | 2008-11-24 | 2008-11-24 | 2009-09-30 | 2009-09-30
| 050.21614 | 050.2635.Caldwell Co Hospital | run 800' - 4" PE for new hospital | 1346.29 | 4274.84 | -2928.55 | -68.51% | 0.007739% | 1346.29 | 4274.84 | -2928.55 | 2008-10-01 | 2009-09-30 | 2008-11-05 | 2008-11-05 | 2009-11-05 | 2009-11-05
| 050.20249 | 2737.DANVILLE OFFICE REMODEL | REMODEL DANVILLE OFFICE - SERVICE AND CONSTRUCTION | 1362.62 | 47506 | 23444.25 | 49.35% | 0.4079% | 70950.25 | 47506 | 23444.25 | 2008-10-01 | 2009-09-30 | 2007-10-29 | 2007-10-29 | 2008-02-02 | 2008-02-02
| 050.20250 | 2737.DANVILLE FURNITURE | PURCHASE NEW OFFICE FURNITURE | 1375.58 | 11516 | 15286.75 | 132.7% | 0.1541% | 26802.75 | 11516 | 15286.75 | 2008-10-01 | 2009-09-30 | 2007-10-29 | 2007-10-29 | 2008-02-02 | 2008-02-02
| 050.21997 | 050.2634.Mittie Render Ave. | Install 100 Feet 2 inch PE | 1377.28 | 2120.53 | -743.25 | -35.05% | 0.007917% | 1377.28 | 2120.53 | -743.25 | 2008-10-01 | 2009-09-30 | 2009-04-23 | 2009-04-23 | 2009-09-28 | 2009-09-28
| 050.21992 | 050.2636.WKU Campus Hwy 231 | Install 648' 4" PE | 1423.52 | 3450.43 | -2026.91 | -58.74% | 0.008183% | 1423.52 | 3450.43 | -2026.91 | 2008-10-01 | 2009-09-30 | 2009-04-22 | 2009-04-22 | 2009-09-28 | 2009-09-28
| 050.22003 | 050.2637.D-4 Calibration Kit | D-4 calibration kit for use by Mike Bridges in the Paducah, KY area | 1470.25 | 1324.11 | 146.14 | 11.04% | 0.008452% | 1470.25 | 1324.11 | 146.14 | 2008-10-01 | 2009-09-30 | 2009-04-28 | 2009-04-28 | 2009-09-25 | 2009-09-25
| 050.21980 | 050.2637.Ogilvie Ave Rev Ext | Install 300 feet for three new residential customers requesting natural gas service | 1470.94 | 1838.91 | -367.97 | -20.01% | 0.008456% | 1470.94 | 1838.91 | -367.97 | 2008-10-01 | 2009-09-30 | 2009-04-09 | 2009-04-09 | 2009-07-15 | 2009-07-15
| 050.22438 | 050.KY.PaducahLeakFunct2010 | 050.KY.PaducahLeakFunct2010 | 1472.27 | Not Budgeted | - | - | 0.008463% | 1472.27 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20851 | 050.BGR.HOPK.MARIE DR. EXT. | 230 FT. OF 2" PE -MARIEI DR. - HOPKINSVILLE | 1682.62 | 2726 | -585.34 | -21.47% | 0.01231% | 2140.66 | 2726 | -585.34 | 2008-10-01 | 2009-09-30 | 2008-08-06 | 2008-08-06 | 2009-08-06 | 2009-08-06
| 050.20395 | 050.2636.Harbor Hills Trace 2 | Install 2,596' 2" PE | 1685.35 | 11747.47 | 9050.87 | 77.05% | 0.1196% | 20798.34 | 11747.47 | 9050.87 | 2008-10-01 | 2009-09-30 | 2008-01-11 | 2008-01-11 | 2008-07-31 | 2008-07-31
| 050.20756 | 050.2634.S.Kentucky Ave.Rplmt. | Replace approximately 2,060' Bare LP pipe | 1694.9 | 55393.22 | -21464.4 | -38.75% | 0.195% | 33928.82 | 55393.22 | -21464.4 | 2008-10-01 | 2009-09-30 | 2008-07-01 | 2008-07-01 | 2008-09-28 | 2008-09-28
| 050.22432 | 050.KY.DanvilleLeakFunct2010 | 050.KY.DanvilleLeakFunct2010 | 1748.84 | Not Budgeted | - | - | 0.01005% | 1748.84 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20489 | 050.BGR.COLLEGEVIEW 2" REPLC. | 470 FT. - 2" BARE REPLACEMENT - COLLEGEVIEW - B.G. | 1771.75 | 9878 | -7796.1 | -78.92% | 0.01197% | 2081.9 | 9878 | -7796.1 | 2008-10-01 | 2009-09-30 | 2008-02-22 | 2008-02-22 | 2009-02-22 | 2009-02-22
| 050.21002 | 050.2602.NBUILD.SECURITY | Camera security recording system for the new Owensboro building and grounds in KY | 1843.48 | 37746.31 | -35902.83 | -95.12% | 0.0106% | 1843.48 | 37746.31 | -35902.83 | 2008-10-01 | 2009-09-30 | 2008-09-26 | 2008-09-26 | 2008-09-29 | 2008-09-29
| 050.19602 | Princeton 08 Growth | Princeton 08 Growth | 1858.09 | Not Budgeted | - | - | 0.2359% | 41037.72 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20422 | 2739.LP STATION RETIREMENT-3 | RETIRE ALTON RD, BROWN ST AND HENRY CLAY-8TH LP STATIONS | 1905.22 | 17793 | -11523.75 | -64.77% | 0.03604% | 6269.25 | 17793 | -11523.75 | 2008-10-01 | 2009-09-30 | 2008-01-24 | 2008-01-24 | 2008-01-24 | 2008-01-24
| 040.12711 | John Samsil MEC Forfeiture | John Samsil MEC Forfeiture | 1939.3 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.22028 | 2737.STN. HWY 27 RETIRE | RETIRE 60ft OF 2in STEEL ON HWY 27 | 1945.77 | 718.61 | 1227.16 | 170.8% | 0.01119% | 1945.77 | 718.61 | 1227.16 | 2008-10-01 | 2009-09-30 | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-10-01
| 050.21844 | 050.2637.Emergency Equip | Emergency equip purchased during ice storm | 1955.82 | 8406.5 | -6450.68 | -76.73% | 0.01124% | 1955.82 | 8406.5 | -6450.68 | 2008-10-01 | 2009-09-30 | 2009-02-03 | 2009-02-03 | 2009-09-30 | 2009-09-30
| 050.20930 | 050.2638.Marker Ball Locator | Purchase Rycom model 8890 marker ball locator for use in the Mayfield area | 2002.65 | 1620.66 | 381.99 | 23.57% | 0.01151% | 2002.65 | 1620.66 | 381.99 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-09-01 | 2009-09-01
| 050.20884 | 050.2634.S.Main&Broadway Rplmt | Install 803' 2" Pe IP Retire 6",4",3",2", Bare pipe | 2090.83 | 21805.2 | -5739.06 | -26.32% | 0.09236% | 16066.14 | 21805.2 | -5739.06 | 2008-10-01 | 2009-09-30 | 2008-08-15 | 2008-08-15 | 2008-09-28 | 2008-09-28
| 050.22147 | 050.2638.King Dr Rev Ext | Install 645' - 2" PE | 2144.56 | 2955.17 | -810.61 | -27.43% | 0.01233% | 2144.56 | 2955.17 | -810.61 | 2008-10-01 | 2009-09-30 | 2009-07-06 | 2009-07-06 | 2009-09-28 | 2009-09-28
| 050.20849 | MEA.TCHSVR.TRANSMITTERS | Pressure and Temperature Transmitters to replace damaged units | 2171.11 | 7812 | -830.08 | -10.63% | 0.04014% | 6981.92 | 7812 | -830.08 | 2008-10-01 | 2009-09-30 | 2008-08-05 | 2008-08-05 | 2008-09-30 | 2008-09-30
| 040.12686 | Brice Leech MEC Forfeiture | Brice Leech MEC Forfeiture | 2236 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 040.12685 | Norma Taylor MEC Forfeiture | Norma Taylor MEC Forfeiture | 2238.9 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.22398 | 050.KY.PrincetonIntegFunct2010 | 050.KY.PrincetonIntegFunct2010 | 2362.08 | Not Budgeted | - | - | 0.01358% | 2362.08 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22183 | 2737.LAN.MAYERS CT REPLACE | REPLACED 10' OF 2in STEEL ON MAYERS CT IN LANCASTER | 2378.67 | 5132.83 | -2754.16 | -53.66% | 0.01367% | 2378.67 | 5132.83 | -2754.16 | 2008-10-01 | 2009-09-30 | 2009-07-23 | 2009-07-23 | 2009-10-01 | 2009-10-01
| 050.22354 | 050.KY.HopkinsGrowthFunct2010 | 050.KY.HopkinsGrowthFunct2010 | 2457.82 | Not Budgeted | - | - | 0.01413% | 2457.82 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20691 | 2737.4TH STREET STATION | INSTALL NEW VALVES AND REGULATORS AT THE 4TH STREET STATION | 2466.33 | 15124 | 8598.89 | 56.86% | 0.1364% | 23722.89 | 15124 | 8598.89 | 2008-10-01 | 2009-09-30 | 2008-06-03 | 2008-06-03 | 2009-09-29 | 2009-09-29
| 050.21996 | 050.2634.Hillside Dr. | Install 100 Feet 2 Inch PE Main | 2467.01 | 2096.56 | 370.45 | 17.67% | 0.01418% | 2467.01 | 2096.56 | 370.45 | 2008-10-01 | 2009-09-30 | 2009-04-23 | 2009-04-23 | 2009-09-28 | 2009-09-28
| 050.21967 | TchSvr.Mea.EFM.Estron Chem. | EFM for Estron Chemicals in Calvert City | 2530.63 | 4140 | -1609.37 | -38.87% | 0.01455% | 2530.63 | 4140 | -1609.37 | 2008-10-01 | 2009-09-30 | 2009-04-03 | 2009-04-03 | 2009-09-30 | 2009-09-30
| 050.20859 | 050.2634.S. Franklin St.Rplmt. | Install 1,256' 2" PE to replace Bare LP Pipe | 2665.6 | 29876.08 | -12290.48 | -41.14% | 0.1011% | 17585.6 | 29876.08 | -12290.48 | 2008-10-01 | 2009-09-30 | 2008-08-07 | 2008-08-07 | 2008-09-28 | 2008-09-28
| 050.22013 | 050.2634. Chart Recorders | Purchase 2 Electronic Chart Recorders | 2683.95 | 3643.29 | -959.34 | -26.33% | 0.01543% | 2683.95 | 3643.29 | -959.34 | 2008-10-01 | 2009-09-30 | 2009-05-05 | 2009-05-05 | 2009-09-28 | 2009-09-28
| 050.20826 | 050.2637.Ky Dam Rd Rev Ext | 275' - 2" PE for two new homes | 2766.7 | 1538.01 | 1230.14 | 79.98% | 0.01591% | 2768.15 | 1538.01 | 1230.14 | 2008-10-01 | 2009-09-30 | 2008-07-28 | 2008-07-28 | 2009-07-10 | 2009-07-10
| 050.20846 | 050.2637.T.B# 3 Reg Replace | Replace jetstream wth Mooney | 2810.78 | 4047.25 | 5227.97 | 129.2% | 0.05332% | 9275.22 | 4047.25 | 5227.97 | 2008-10-01 | 2009-09-30 | 2008-08-04 | 2008-08-04 | 2009-08-03 | 2009-08-03
| 050.21585 | 2738.GRB.WILSON ST.RELOCATION | RELOCATE 150' OF 2" COATED STEEL FOR NEW SCHOOL | 2816.6 | 8054 | -5237.4 | -65.03% | 0.01619% | 2816.6 | 8054 | -5237.4 | 2008-10-01 | 2009-09-30 | 2008-10-31 | 2008-10-31 | 2009-11-11 | 2009-11-11
| 050.22430 | 050.KY.GlasgowLeakFunct2010 | 050.KY.GlasgowLeakFunct2010 | 2863.16 | Not Budgeted | - | - | 0.01646% | 2863.16 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22358 | 050.KY.MadisonGrowthFunct2010 | 050.KY.MadisonGrowthFunct2010 | 2907.73 | Not Budgeted | - | - | 0.01672% | 2907.73 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21752 | 050.2636.Earl Russell Court 2 | Install 220' 2" PE | 2963.75 | 2315.82 | 647.93 | 27.98% | 0.01704% | 2963.75 | 2315.82 | 647.93 | 2008-10-01 | 2009-09-30 | 2008-12-08 | 2008-12-08 | 2009-05-01 | 2009-05-01
| 050.22198 | 050.2637. Marker Capitalize | Project to capitalize labor associated with installation of pipeline marker posts on right-of-ways. | 2963.89 | 3720.06 | -756.17 | -20.33% | 0.01704% | 2963.89 | 3720.06 | -756.17 | 2008-10-01 | 2009-09-30 | 2009-08-03 | 2009-08-03 | 2009-09-28 | 2009-09-28
| 050.21896 | TchSvr.Mea.EFM.Ebonite Int. | EFM for Ebonite International in Hopkinsville | 3022.99 | 4140 | -1117.01 | -26.98% | 0.01738% | 3022.99 | 4140 | -1117.01 | 2008-10-01 | 2009-09-30 | 2009-02-26 | 2009-02-26 | 2009-09-30 | 2009-09-30
| 050.22144 | TchSvr.Mea.EFM-BR Retread | EFM for BR Retreading in Glasgow, KY | 3030.91 | 4140 | -1109.09 | -26.79% | 0.01742% | 3030.91 | 4140 | -1109.09 | 2008-10-01 | 2009-09-30 | 2009-07-06 | 2009-07-06 | 2009-09-30 | 2009-09-30
| 050.21778 | 2737.BURGIN RECTIFIER REPLACE | REPLACE BURGIN RECTIFIER DAMAGED IN CAR ACCIDENT | 3038.66 | 7877 | -4838.34 | -61.42% | 0.01747% | 3038.66 | 7877 | -4838.34 | 2008-10-01 | 2009-09-30 | 2008-12-15 | 2008-12-15 | 2009-12-15 | 2009-12-15
| 050.22241 | TchSvr.Mea.EFM.Spec. Rock Prod | EFM for Specialty Rock Products, Inc. | 3078.65 | 4140 | -1061.35 | -25.64% | 0.0177% | 3078.65 | 4140 | -1061.35 | 2008-10-01 | 2009-09-30 | 2009-08-18 | 2009-08-18 | 2009-09-30 | 2009-09-30
| 050.22242 | TchSvr.Mea.EFM.Daicel Safety | EFM for Daicel Safety Technologie | 3078.65 | 4140 | -1061.35 | -25.64% | 0.0177% | 3078.65 | 4140 | -1061.35 | 2008-10-01 | 2009-09-30 | 2009-08-18 | 2009-08-18 | 2009-09-30 | 2009-09-30
| 050.22201 | TchSvr.Mea.EFM.PAT, Inc | EFM for Premium Allied Tool, Inc | 3102.08 | 4140 | -1037.92 | -25.07% | 0.01783% | 3102.08 | 4140 | -1037.92 | 2008-10-01 | 2009-09-30 | 2009-08-03 | 2009-08-03 | 2009-09-30 | 2009-09-30
| 050.22357 | 050.KY.ShelbyviGrowthFunct2010 | 050.KY.ShelbyviGrowthFunct2010 | 3187.91 | Not Budgeted | - | - | 0.01833% | 3187.91 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22180 | TchSvr.Mea.EFM for Dart #9 | EFM For Dart Container Building #9 | 3190.98 | 4140 | -949.02 | -22.92% | 0.01834% | 3190.98 | 4140 | -949.02 | 2008-10-01 | 2009-09-30 | 2009-07-22 | 2009-07-22 | 2009-09-30 | 2009-09-30
| 050.22005 | 2738.DARE ST | INSTALL 150ft OF 2in PE ON DARE STREET | 3210.27 | 3122.62 | 87.65 | 2.807% | 0.01845% | 3210.27 | 3122.62 | 87.65 | 2008-10-01 | 2009-09-30 | 2009-04-29 | 2009-04-29 | 2009-10-01 | 2009-10-01
| 050.22123 | TchSvr.Mea.EFM.Logan Mem Hosp. | EFM for Logan Memorial Hospital in Bowling Green | 3287.47 | 4140 | -852.53 | -20.59% | 0.0189% | 3287.47 | 4140 | -852.53 | 2008-10-01 | 2009-09-30 | 2009-06-25 | 2009-06-25 | 2009-09-30 | 2009-09-30
| 050.22124 | Tch.MEA.EFM.TBMK | EFM for TBMK in Lebanon, KY | 3287.47 | 4140 | -852.53 | -20.59% | 0.0189% | 3287.47 | 4140 | -852.53 | 2008-10-01 | 2009-09-30 | 2009-06-25 | 2009-06-25 | 2009-09-30 | 2009-09-30
| 050.21807 | TchSvr.Mea.EFM.Nally & Hayden | EFM for Nally & Hayden upgrade to new wireless modem | 3403.33 | 6375 | -2971.67 | -46.61% | 0.01956% | 3403.33 | 6375 | -2971.67 | 2008-10-01 | 2009-09-30 | 2009-01-14 | 2009-01-14 | 2009-09-30 | 2009-09-30
| 050.20785 | 050.2637.Eich Rd Rev Ext | 2,300' - 2" PE for new Fed Ex building | 3404.55 | 2395.99 | -543.57 | -22.69% | 0.01065% | 1852.42 | 2395.99 | -543.57 | 2008-10-01 | 2009-09-30 | 2008-07-14 | 2008-07-14 | 2009-07-10 | 2009-07-10
| 050.22303 | 050.2637.Smart-Cal | We are purchasing this Smart-Cal unit for the purpose of calibrating our Sensit Gold machines, in adition unit has the ability to store key information. | 3472.79 | 3917.5 | -444.71 | -11.35% | 0.01996% | 3472.79 | 3917.5 | -444.71 | 2008-10-01 | 2009-09-30 | 2009-09-02 | 2009-09-02 | 2009-09-25 | 2009-09-25
| 050.21985 | 050.2736.Keeton Dr. | Install 200' 4" PE | 3486.2 | 3676.7 | -190.5 | -5.181% | 0.02004% | 3486.2 | 3676.7 | -190.5 | 2008-10-01 | 2009-09-30 | 2009-04-15 | 2009-04-15 | 2009-07-31 | 2009-07-31
| 050.22042 | 050.2634 No Blow Vlve Changer | Purchase no blow valve changer for Madisonville | 3551.81 | 3981.75 | -429.94 | -10.8% | 0.02042% | 3551.81 | 3981.75 | -429.94 | 2008-10-01 | 2009-09-30 | 2009-05-21 | 2009-05-21 | 2009-09-28 | 2009-09-28
| 050.19702 | 050.2635.Mtrs/Regs/Retire | purchase of meters, regs, & retirements for fy '08 | 3606.04 | 52629.51 | -38138.34 | -72.47% | 0.0833% | 14491.17 | 52629.51 | -38138.34 | 2008-10-01 | 2009-09-30 | 2007-10-04 | 2007-10-04 | 2008-10-03 | 2008-10-03
| 050.22063 | 050.3351.Locator - Pandolfi | Locator for use by D. Pandolfi in Paducah area | 3611.69 | 4118.08 | -506.39 | -12.3% | 0.02076% | 3611.69 | 4118.08 | -506.39 | 2008-10-01 | 2009-09-30 | 2009-06-03 | 2009-06-03 | 2009-09-30 | 2009-09-30
| 050.21934 | TchSvr.Mea.EFM Ceratech | EFM for Ceratech in Marion | 3625.16 | 4140 | -514.84 | -12.44% | 0.02084% | 3625.16 | 4140 | -514.84 | 2008-10-01 | 2009-09-30 | 2009-03-19 | 2009-03-19 | 2009-09-30 | 2009-09-30
| 050.21725 | TchSvrMeaEFM for Obo Med Ctr | EFM for Owensboro Medical Center | 3729.38 | 4140 | -410.62 | -9.918% | 0.02144% | 3729.38 | 4140 | -410.62 | 2008-10-01 | 2009-09-30 | 2008-12-01 | 2008-12-01 | 2009-03-02 | 2009-03-02
| 050.22282 | 2737.HAR.472 N MAIN REPLACE | REPLACE 15ft OF 4in STEEL AT 472 NORTH MAIN IN HARRODSBURG, KY | 3776.95 | 3601.87 | 175.08 | 4.861% | 0.02171% | 3776.95 | 3601.87 | 175.08 | 2008-10-01 | 2009-09-30 | 2009-08-25 | 2009-08-25 | 2009-10-01 | 2009-10-01
| 050.22392 | 050.KY.GlasgowIntegFunct2010 | 050.KY.GlasgowIntegFunct2010 | 3785.24 | Not Budgeted | - | - | 0.02176% | 3785.24 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21873 | TchSvrMea.EFM Am.Greetings | EFM for American Greetings in Danville, KY | 3787.92 | 4140 | -352.08 | -8.504% | 0.02177% | 3787.92 | 4140 | -352.08 | 2008-10-01 | 2009-09-30 | 2009-02-13 | 2009-02-13 | 2009-09-30 | 2009-09-30
| 050.22274 | 050.2338.May Reinforcement | Install 12,000 feet 4" HD PE pipe from KT Clay (190 maop) to Dairyman Inc (36 maop) | 3795.59 | 67799.57 | -64003.98 | -94.4% | 0.02182% | 3795.59 | 67799.57 | -64003.98 | 2008-10-01 | 2009-09-30 | 2009-08-24 | 2009-08-24 | 2009-09-28 | 2009-09-28
| 050.22127 | 050.2636.Heartland phase 5 | Install 2 Inch Pe to serve 22 Residential lots | 3846.55 | 6004.64 | -2158.09 | -35.94% | 0.02211% | 3846.55 | 6004.64 | -2158.09 | 2008-10-01 | 2009-09-30 | 2009-06-30 | 2009-06-30 | 2009-09-28 | 2009-09-28
| 050.21700 | EFM.Mea.TchSvr.Centre College | EFM for Centre College in Danville, KY | 3868.73 | 4140.1 | -271.37 | -6.555% | 0.02224% | 3868.73 | 4140.1 | -271.37 | 2008-10-01 | 2009-09-30 | 2008-11-21 | 2008-11-21 | 2009-01-30 | 2009-01-30
| 040.12694 | Daviess BD of EDU MEC Forf | Daviess BD of EDU MEC Forf | 3955 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.19708 | 050.2634.METER & REG PURCHASE | Purchase & retire meters &regulators | 4005.97 | 68688.95 | 9841.93 | 14.33% | 0.4514% | 78530.88 | 68688.95 | 9841.93 | 2008-10-01 | 2009-09-30 | 2007-10-08 | 2007-10-08 | 2008-09-26 | 2008-09-26
| 050.19600 | Madisonville 08 Growth | Madisonville 08 Growth | 4081.61 | Not Budgeted | - | - | 0.6111% | 106310.38 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22435 | 050.KY.MadisonLeakFunct2010 | 050.KY.MadisonLeakFunct2010 | 4112.76 | Not Budgeted | - | - | 0.02364% | 4112.76 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 040.12712 | Jerome Paul Haynes MEC Forf | Jerome Paul Haynes MEC Forf | 4113 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.19701 | 050.2638.Mtrs/Regs/Retire | purchase of meters, regs, & retirements for fy '08 | 4117.13 | 74254.59 | -44320.07 | -59.69% | 0.1721% | 29934.52 | 74254.59 | -44320.07 | 2008-10-01 | 2009-09-30 | 2007-10-04 | 2007-10-04 | 2008-10-03 | 2008-10-03
| 050.22226 | 2739.SUPERVISOR FURNITURE | OFFICE FURNITURE FOR OPERATIONS SUPERVISOR | 4340.79 | 3917.5 | 423.29 | 10.81% | 0.02495% | 4340.79 | 3917.5 | 423.29 | 2008-10-01 | 2009-09-30 | 2009-08-12 | 2009-08-12 | 2009-09-30 | 2009-09-30
| 050.20929 | 050.2637.Hansen Rd Rev Ext | 315' extension for one existing residential customer (JW Wallace) | 4393.8 | 2162.99 | 1409.05 | 65.14% | 0.02053% | 3572.04 | 2162.99 | 1409.05 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-09-01 | 2009-09-01
| 050.22360 | 050.KY.OboroGrowthFunct2010 | 050.KY.OboroGrowthFunct2010 | 4504.3 | Not Budgeted | - | - | 0.02589% | 4504.3 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.19700 | 050.2637.Mtrs/Regs/Retire | purchase meters, regs, & retirements | 4568.39 | 178972.79 | -97061.22 | -54.23% | 0.4709% | 81911.57 | 178972.79 | -97061.22 | 2008-10-01 | 2009-09-30 | 2007-10-04 | 2007-10-04 | 2008-10-03 | 2008-10-03
| 050.21557 | 050.2636.Highland Pointe 3 | Install 1,933' 2" PE | 4752.65 | 4873 | -120.35 | -2.47% | 0.02732% | 4752.65 | 4873 | -120.35 | 2008-10-01 | 2009-09-30 | 2008-10-23 | 2008-10-23 | 2008-12-01 | 2008-12-01
| 050.21548 | 2738.WALMART OUTPARCELS | INSTALL 400' OF 2" PE FOR WALMART OUTPARCELS | 4819.24 | 3786 | 1033.24 | 27.29% | 0.0277% | 4819.24 | 3786 | 1033.24 | 2008-10-01 | 2009-09-30 | 2008-10-21 | 2008-10-21 | 2009-10-20 | 2009-10-20
| 040.12680 | David Lashbrook MEC Forfeiture | David Lashbrook MEC Forfeiture | 4984 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.22145 | 050.2636.River Rd. Lazar | Install 390' 2" Steel Main | 4996.04 | 20398.29 | -15402.25 | -75.51% | 0.02872% | 4996.04 | 20398.29 | -15402.25 | 2008-10-01 | 2009-09-30 | 2009-07-06 | 2009-07-06 | 2009-09-28 | 2009-09-28
| 050.19706 | 050.2636.Owensboro meters | Purchase Meters & Regs. for Owensboro | 5054.81 | 91677.11 | -20305.25 | -22.15% | 0.4103% | 71371.86 | 91677.11 | -20305.25 | 2008-10-01 | 2009-09-30 | 2007-10-08 | 2007-10-08 | 2008-09-26 | 2008-09-26
| 050.20664 | 050.2636.S.Griffith Rplmt. | Replace 4" LP Stl. with 1600' 2" IP PE | 5485.02 | 35752.89 | -7445.83 | -20.83% | 0.1627% | 28307.06 | 35752.89 | -7445.83 | 2008-10-01 | 2009-09-30 | 2008-05-15 | 2008-05-15 | 2008-09-28 | 2008-09-28
| 040.12692 | Super America MEC Forfeiture | Super America MEC Forfeiture | 5500 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.22200 | 2738.GRN.WISON ST IP REPLACE | INSTALL 2in PE TO REPLACE 4in BARE STEEL LP | 5594.44 | 7791.93 | -2197.49 | -28.2% | 0.03216% | 5594.44 | 7791.93 | -2197.49 | 2008-10-01 | 2009-09-30 | 2009-08-03 | 2009-08-03 | 2009-10-01 | 2009-10-01
| 050.21946 | 2738.GRN.E COLUMBIA RELOCATE | RELOCATE 2" STEEL ON EAST COLUMBIA WITH NEW WATERLINE | 5602.72 | 8455 | -2852.28 | -33.73% | 0.03221% | 5602.72 | 8455 | -2852.28 | 2008-10-01 | 2009-09-30 | 2009-03-24 | 2009-03-24 | 2010-03-25 | 2010-03-25
| 050.20922 | 050.2609.Bon Harbor Well #1 | Workover Well # 1 Bon Harbor | 5877.41 | 58152.69 | -617.95 | -1.063% | 0.3307% | 57534.74 | 58152.69 | -617.95 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20925 | 050.2609.Bon Harbor Well #6 | Workover Bon Harbor Well #6 | 5877.41 | 58152.69 | -617.95 | -1.063% | 0.3307% | 57534.74 | 58152.69 | -617.95 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.19596 | Campbellsville 08 Growth | Campbellsville 08 Growth | 5954.7 | Not Budgeted | - | - | 0.4608% | 80165.08 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22177 | 050.2636.Graystone Phase 4 | Install 2" Pe to serve 25 Residential Lots | 6009.92 | 7917.83 | -1907.91 | -24.1% | 0.03455% | 6009.92 | 7917.83 | -1907.91 | 2008-10-01 | 2009-09-30 | 2009-07-21 | 2009-07-21 | 2009-09-28 | 2009-09-28
| 050.21811 | 050.2637.Pole Repair | Scneidman Rd Rectifier pole repair | 6019.25 | 3959.45 | 2059.8 | 52.02% | 0.0346% | 6019.25 | 3959.45 | 2059.8 | 2008-10-01 | 2009-09-30 | 2009-01-16 | 2009-01-16 | 2009-09-28 | 2009-09-28
| 050.20844 | 050.2637.Calvert City Reg Imp | Improvements to regulators at two sations in Calvert, one at Calvert City Purchase, one at Westlake Chem Sales sta | 6210.29 | 12451.49 | 4364.45 | 35.05% | 0.09667% | 16815.94 | 12451.49 | 4364.45 | 2008-10-01 | 2009-09-30 | 2008-08-04 | 2008-08-04 | 2009-08-03 | 2009-08-03
| 050.22014 | 2737.STAN.HWY 27.RITE AIDE | INSTALL 200ft OF 2in PE ON HWY 27 FROM SONIC NORTH ON THE WEST SIDE OF HWY 27 | 6361.84 | 6134.35 | 227.49 | 3.708% | 0.03657% | 6361.84 | 6134.35 | 227.49 | 2008-10-01 | 2009-09-30 | 2009-05-05 | 2009-05-05 | 2009-10-01 | 2009-10-01
| 050.20926 | 050.2609.Bon Harbor Well #2 | Workover Bon Harbor Well #2 | 6388.31 | 58152.69 | 4124 | 7.092% | 0.358% | 62276.69 | 58152.69 | 4124 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20927 | 050.2609.Bon Harbor Well #4 | Workover Bonharbor Well #4 | 6388.31 | 58152.69 | 4124 | 7.092% | 0.358% | 62276.69 | 58152.69 | 4124 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.21542 | 050.2636.Trails Way | Install 913' 2" PE | 6414.59 | 5478.76 | 935.83 | 17.08% | 0.03687% | 6414.59 | 5478.76 | 935.83 | 2008-10-01 | 2009-09-30 | 2008-10-20 | 2008-10-20 | 2009-02-27 | 2009-02-27
| 050.22276 | 050.2637.1515 Broadway Imp | This project is to capture costs associated with the repair to the air conditioning system at 1515 Broadway. estimate secured from CMI Heating & Air in Paducah. | 6455.63 | 6880.7 | -425.07 | -6.178% | 0.03711% | 6455.63 | 6880.7 | -425.07 | 2008-10-01 | 2009-09-30 | 2009-08-24 | 2009-08-24 | 2009-09-28 | 2009-09-28
| 050.20693 | 2738.C-VILLE OFFICE IMPROVE | INTERIOR REMODELING OF THE CAMPBELLSVILLE OFFICE | 6575.01 | 31420 | 11637.39 | 37.04% | 0.2475% | 43057.39 | 31420 | 11637.39 | 2008-10-01 | 2009-09-30 | 2008-06-03 | 2008-06-03 | 2009-09-29 | 2009-09-29
| 050.22355 | 050.KY.DanvilleGrowthFunct2010 | 050.KY.DanvilleGrowthFunct2010 | 6988.79 | Not Budgeted | - | - | 0.04018% | 6988.79 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21556 | 050.2636.Shade Wood Cove | Install 954' 2" PE | 7098.01 | 5825.08 | 1272.93 | 21.85% | 0.0408% | 7098.01 | 5825.08 | 1272.93 | 2008-10-01 | 2009-09-30 | 2008-10-22 | 2008-10-22 | 2009-03-02 | 2009-03-02
| 050.19608 | Mayfield 08 Growth | Mayfield 08 Growth | 7175.54 | Not Budgeted | - | - | 0.5789% | 100711.08 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22008 | 050.2736.Misc Equipment | Purchase leak detector & pipeline locator | 7203.21 | 6536.66 | 666.55 | 10.2% | 0.04141% | 7203.21 | 6536.66 | 666.55 | 2008-10-01 | 2009-09-30 | 2009-05-01 | 2009-05-01 | 2009-09-28 | 2009-09-28
| 050.22004 | 050.2637.2 Pipe Locators | Purchase 2 Rycom pipe locators for use in Paducah by Roger Baulckim and Terry Leavell | 7212.73 | 8305.1 | -1092.37 | -13.15% | 0.04146% | 7212.73 | 8305.1 | -1092.37 | 2008-10-01 | 2009-09-30 | 2009-04-28 | 2009-04-28 | 2009-09-25 | 2009-09-25
| 050.21911 | TCHSVR.MEA.EFM FOR REPLACEMENT | EFM replacement units for obsolete and damaged units | 7252.5 | 9499 | -2246.5 | -23.65% | 0.04169% | 7252.5 | 9499 | -2246.5 | 2008-10-01 | 2009-09-30 | 2009-03-05 | 2009-03-05 | 2009-09-30 | 2009-09-30
| 050.21866 | 2739.HWY 60.4 ST REPLACEMENT | REPLACE 360' OF 4" STEEL ON HWY 60 AND MIDLAND BLVD | 7270.59 | 15599 | -8328.41 | -53.39% | 0.0418% | 7270.59 | 15599 | -8328.41 | 2008-10-01 | 2009-09-30 | 2009-02-10 | 2009-02-10 | 2010-02-10 | 2010-02-10
| 050.22206 | 050.2635.Town Border Fences | Install fences Cadiz and Eddyville TB | 7348.42 | 8289.43 | -941.01 | -11.35% | 0.04224% | 7348.42 | 8289.43 | -941.01 | 2008-10-01 | 2009-09-30 | 2009-08-05 | 2009-08-05 | 2009-09-28 | 2009-09-28
| 050.22318 | 050.2634.Center St. Rplmnt. | Replace 390' 6 " Bare pipe | 7640.88 | 11709.9 | -4069.02 | -34.75% | 0.04392% | 7640.88 | 11709.9 | -4069.02 | 2008-10-01 | 2009-09-30 | 2009-09-08 | 2009-09-08 | 2009-09-28 | 2009-09-28
| 050.19590 | Glasgow 08 Growth | Glasgow 08 Growth | 7664.02 | Not Budgeted | - | - | 0.9823% | 170870.75 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.21865 | 2737.WATER PUMPS | PURCHASE 2 WATER PUMPS | 7834.47 | 6136.46 | 1698.01 | 27.67% | 0.04504% | 7834.47 | 6136.46 | 1698.01 | 2008-10-01 | 2009-09-30 | 2009-02-10 | 2009-02-10 | 2010-02-10 | 2010-02-10
| 050.22007 | 050.3351.CP Equip | various cp equipment for use by Mark Mars in the Sikeston, MO area | 7976.05 | 8960.11 | -984.06 | -10.98% | 0.04585% | 7976.05 | 8960.11 | -984.06 | 2008-10-01 | 2009-09-30 | 2009-05-01 | 2009-05-01 | 2009-09-25 | 2009-09-25
| 050.21648 | 050.2634.Hanson Odorizor | Install Odorizor | 8141.4 | 7959.6 | 181.8 | 2.284% | 0.0468% | 8141.4 | 7959.6 | 181.8 | 2008-10-01 | 2009-09-30 | 2008-11-13 | 2008-11-13 | 2009-03-31 | 2009-03-31
| 050.20935 | 050.BGR.PRESS RECORDERS | ELECTRONIC PRESSURE RECORDERS - BOWLING GREEN | 8168.43 | 6910 | 1258.43 | 18.21% | 0.04696% | 8168.43 | 6910 | 1258.43 | 2008-10-01 | 2009-09-30 | 2008-09-03 | 2008-09-03 | 2009-09-03 | 2009-09-03
| 050.20380 | 050.2636.Timber Ridge Phase 2 | Install , 2058' 2" PE | 8433.42 | 13645.17 | -146.37 | -1.073% | 0.0776% | 13498.8 | 13645.17 | -146.37 | 2008-10-01 | 2009-09-30 | 2008-01-07 | 2008-01-07 | 2008-07-30 | 2008-07-30
| 050.21538 | 2739.WARRIORS WAY FIRE STATION | INSTALL 230' OF 2" PE TO SERVE NEW FIRE STATION ON WARRIORS WAY | 8434.44 | 7206 | 1228.44 | 17.05% | 0.04849% | 8434.44 | 7206 | 1228.44 | 2008-10-01 | 2009-09-30 | 2008-10-17 | 2008-10-17 | 2009-10-17 | 2009-10-17
| 050.20231 | 050.HOP.NEW TOWN STATION | 1260 FT. OF 4" PE - NEW TOWN STATION - HOPK. | 8549.7 | 3626 | 7960.17 | 219.5% | 0.0666% | 11586.17 | 3626 | 7960.17 | 2008-10-01 | 2009-09-30 | 2007-10-19 | 2007-10-19 | 2008-10-18 | 2008-10-18
| 050.22074 | 050.2618 Shoring Boxes 2 | purchase shoring box equipment for Hopkinsville | 8561.9 | 10793.5 | -2231.6 | -20.68% | 0.04922% | 8561.9 | 10793.5 | -2231.6 | 2008-10-01 | 2009-09-30 | 2009-06-08 | 2009-06-08 | 2009-09-28 | 2009-09-28
| 050.19592 | Hopkinsville 08 Growth | Hopkinsville 08 Growth | 8653.84 | Not Budgeted | - | - | 0.7179% | 124882.53 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.21800 | 050.2736.S. Clay St. | Install 590' 2" PE IPto replace 2" LP Stl. | 9268.45 | 11955.45 | -2687 | -22.48% | 0.05328% | 9268.45 | 11955.45 | -2687 | 2008-10-01 | 2009-09-30 | 2009-01-08 | 2009-01-08 | 2009-07-01 | 2009-07-01
| 050.21868 | Wireless Modems for ROCs | Wireless Modems for replacement of telephone communications | 9284.5 | 15623 | -6338.5 | -40.57% | 0.05337% | 9284.5 | 15623 | -6338.5 | 2008-10-01 | 2009-09-30 | 2009-02-12 | 2009-02-12 | 2009-09-30 | 2009-09-30
| 040.13098 | 040.2739.LAW.LAWRENCEBURG XING | INSTALL 1500' OF 2" PE AND RETIRE 1300' OF 2" STEEL | 9305 | 9459 | -2727.21 | -28.83% | 0.0387% | 6731.79 | 9459 | -2727.21 | 2008-10-01 | 2009-09-30 | 2006-08-15 | 2006-08-15 | 2007-08-15 | 2007-08-15
| 050.22012 | 050.2634.Misc Equipment | Purchase 2 Sensit Golds | 9732.11 | 10104.95 | -372.84 | -3.69% | 0.05595% | 9732.11 | 10104.95 | -372.84 | 2008-10-01 | 2009-09-30 | 2009-05-04 | 2009-05-04 | 2009-09-28 | 2009-09-28
| 050.20509 | 2738.LEB.HENDRICKSON STATION | INSTALL REGULATOR STATION ON HENDRICKSON DR IN LEBANON | 9780.74 | 9458 | 322.74 | 3.412% | 0.05622% | 9780.74 | 9458 | 322.74 | 2008-10-01 | 2009-09-30 | 2008-03-04 | 2008-03-04 | 2009-03-04 | 2009-03-04
| 050.22023 | 050.2737.BARRACADE INSTALL | INSTALL BARRACADES AT THREE STATIONS. PERRYVILLE PURCHASE STATION, PERRYVILLE TBS AND STANFORD ROAD STATION | 9834.92 | 8465.26 | 1369.66 | 16.18% | 0.05654% | 9834.92 | 8465.26 | 1369.66 | 2008-10-01 | 2009-09-30 | 2009-05-11 | 2009-05-11 | 2009-10-01 | 2009-10-01
| 050.21931 | Tch.Svr.Mea.Office Furniture | Filing cabinets for Measurement Dept. | 9991.45 | 5849 | 4142.45 | 70.82% | 0.05744% | 9991.45 | 5849 | 4142.45 | 2008-10-01 | 2009-09-30 | 2009-03-16 | 2009-03-16 | 2009-09-30 | 2009-09-30
| 050.21893 | 2737.EMERGENCY TRAILER | TRAILER FOR TAPPING EQUIPMENT AND EMERGENCY RESPONSE | 10012.46 | 9704 | 308.46 | 3.179% | 0.05756% | 10012.46 | 9704 | 308.46 | 2008-10-01 | 2009-09-30 | 2009-02-25 | 2009-02-25 | 2010-02-25 | 2010-02-25
| 050.21777 | 2738.HEATER REPLACE.LEB-CVILLE | REPLACE HEATERS IN CVILLE AND LEBANON WAREHOUSES | 10434.41 | 9149 | 1285.41 | 14.05% | 0.05998% | 10434.41 | 9149 | 1285.41 | 2008-10-01 | 2009-09-30 | 2008-12-15 | 2008-12-15 | 2009-12-12 | 2009-12-12
| 040.12704 | Hunters Pointe Dev MEC Forfeit | Hunters Pointe Dev MEC Forfeit | 10646 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2005-09-28 | 2005-09-28 | 2005-09-30 | 2005-09-30
| 050.21869 | 2737.PLASTIC PIPE LOCATOR | PURCHASE PLASTIC PIPE LOCATOR TO BE USED AND TESTED IN THE DANVILLE REGION AND KMD DIVISION | 10814.58 | 7030 | 3784.58 | 53.83% | 0.06217% | 10814.58 | 7030 | 3784.58 | 2008-10-01 | 2009-09-30 | 2009-02-12 | 2009-02-12 | 2010-02-12 | 2010-02-12
| 050.21876 | 050.BGR.RUSS RD. - CREEKWOOD | REPLACE CROSSING - RUSSELLVILLE RD. & CREEKWOOD - B.G. | 10819.37 | 14288 | -3468.63 | -24.28% | 0.0622% | 10819.37 | 14288 | -3468.63 | 2008-10-01 | 2009-09-30 | 2009-02-17 | 2009-02-17 | 2010-02-16 | 2010-02-16
| 050.21086 | 050.BGR.11OO BLK. VINE REPLC. | 1100 BLK. VINE ST. 2" BARE STEEL REPLACEMENT - B.G. | 11468.78 | 9536 | 1932.78 | 20.27% | 0.06593% | 11468.78 | 9536 | 1932.78 | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-09-29 | 2009-09-29
| 050.22396 | 050.KY.ShelbyviIntegFunct.2010 | 050.KY.ShelbyviIntegFunct.2010 | 11543.15 | Not Budgeted | - | - | 0.06636% | 11543.15 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21555 | 050.BGR.GREENWOOD RELOC | 500 FT. - 2"PE - GREENWOOD LN. RELOCATION | 11901.83 | 9705 | 2196.83 | 22.64% | 0.06842% | 11901.83 | 9705 | 2196.83 | 2008-10-01 | 2009-09-30 | 2008-10-22 | 2008-10-22 | 2008-10-21 | 2008-10-21
| 050.22401 | 050.KY.MayfieldIntegFunct2010 | 050.KY.MayfieldIntegFunct2010 | 12062.58 | Not Budgeted | - | - | 0.06934% | 12062.58 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20936 | 2738.COLUMBIA AVE.REPLACEMENT | REPLACE 4" STEEL IP ON COLUMBIA AVE WITH 2" PE IP | 12616.06 | 14987 | 2181.71 | 14.56% | 0.09869% | 17168.71 | 14987 | 2181.71 | 2008-10-01 | 2009-09-30 | 2008-09-03 | 2008-09-03 | 2009-09-02 | 2009-09-02
| 050.22393 | 050.KY.HopkinsIntegFunct2010 | 050.KY.HopkinsIntegFunct2010 | 12623.84 | Not Budgeted | - | - | 0.07257% | 12623.84 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22395 | 050.KY.CampbellIntegFunct2010 | 050.KY.CampbellIntegFunct2010 | 12774.85 | Not Budgeted | - | - | 0.07344% | 12774.85 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21802 | TchSvr.Mea.Westlake Methane | Rebuild Westlake Methane Meter Station in Calvert City | 13710.3 | 114000 | -100289.7 | -87.97% | 0.07881% | 13710.3 | 114000 | -100289.7 | 2008-10-01 | 2009-09-30 | 2009-01-09 | 2009-01-09 | 2009-09-30 | 2009-09-30
| 050.21988 | CC2636 FY 09 Meter Pro | CC2636 FY 09 Meter Pro meter reading software | 13751.77 | 11717.25 | 2034.52 | 17.36% | 0.07905% | 13751.77 | 11717.25 | 2034.52 | 2008-10-01 | 2009-09-30 | 2009-04-17 | 2009-04-17 | 2009-05-29 | 2009-05-29
| 050.22394 | 050.KY.DanvilleIntegFunct2010 | 050.KY.DanvilleIntegFunct2010 | 14159.2 | Not Budgeted | - | - | 0.08139% | 14159.2 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21793 | 050.2637.Heater Parts | Heater parts for Bruest heaters | 14202.43 | 3713.99 | 10488.44 | 282.4% | 0.08164% | 14202.43 | 3713.99 | 10488.44 | 2008-10-01 | 2009-09-30 | 2009-01-05 | 2009-01-05 | 2009-09-28 | 2009-09-28
| 050.22072 | TchSvr.Mea.EFM Repl - MO | EFM Replacement for Missoure | 14511.32 | 19597 | -5085.68 | -25.95% | 0.08342% | 14511.32 | 19597 | -5085.68 | 2008-10-01 | 2009-09-30 | 2009-06-05 | 2009-06-05 | 2009-09-30 | 2009-09-30
| 050.20941 | 2738.SPR.BONNIE FARMS | INSTALL FARM TAP AND MAIN FOR BONNIE FARMS GREEN HOUSES ON HWY 55 | 14525.12 | 5854 | 9132.11 | 156% | 0.08615% | 14986.11 | 5854 | 9132.11 | 2008-10-01 | 2009-09-30 | 2008-09-04 | 2008-09-04 | 2009-09-04 | 2009-09-04
| 050.19599 | Shelbyville 08 Non Growth | Shelbyville 08 Non Growth | 14569.11 | Not Budgeted | - | - | 1.222% | 212548.08 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20873 | 050.2638.North St Bare Replace | Replace app 2,750' of bare main in downtown Mayfield | 15372.07 | 81350.92 | -16328.71 | -20.07% | 0.3738% | 65022.21 | 81350.92 | -16328.71 | 2008-10-01 | 2009-09-30 | 2008-08-13 | 2008-08-13 | 2009-08-13 | 2009-08-13
| 050.20659 | 050.2635.Marion TB Relocate | Project to relocate our Marion, KY town border station upstream nearly a mile | 15579.28 | 79761.14 | 4178.75 | 5.239% | 0.4825% | 83939.89 | 79761.14 | 4178.75 | 2008-10-01 | 2009-09-30 | 2008-05-13 | 2008-05-13 | 2009-05-01 | 2009-05-01
| 050.22361 | 050.KY.PaducahGrowthFunct2010 | 050.KY.PaducahGrowthFunct2010 | 15803.06 | Not Budgeted | - | - | 0.09084% | 15803.06 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21949 | 050.2602 Replace Phone Syst | Replace Dated Phone System | 15877.97 | 84177.44 | -68299.47 | -81.14% | 0.09127% | 15877.97 | 84177.44 | -68299.47 | 2008-10-01 | 2009-09-30 | 2009-03-24 | 2009-03-24 | 2009-09-01 | 2009-09-01
| 050.21537 | 2738.HALLS CEMETARY RD STATION | INSTALL NEW FARM TAP AND MAIN TO BRING INTO COMPLIANCE | 16173.39 | 18132 | -1958.61 | -10.8% | 0.09297% | 16173.39 | 18132 | -1958.61 | 2008-10-01 | 2009-09-30 | 2008-10-17 | 2008-10-17 | 2009-10-17 | 2009-10-17
| 050.22044 | 050.2618.Shoring Boxes | Purchase 2 Shoring Boxes & end panels | 17275.46 | 21196.81 | -3921.35 | -18.5% | 0.09931% | 17275.46 | 21196.81 | -3921.35 | 2008-10-01 | 2009-09-30 | 2009-05-22 | 2009-05-22 | 2009-09-28 | 2009-09-28
| 050.19604 | Owensboro 08 Growth | Owensboro 08 Growth | 17420 | Not Budgeted | - | - | 3.22% | 560148.62 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20447 | 050.HOPK.HWY 41 RELOC. | HWY 41 8" & 6" RELOC. - HOPKINSVILLE | 17612.17 | 11486 | 283837.65 | 2471% | 1.698% | 295323.65 | 11486 | 283837.65 | 2008-10-01 | 2009-09-30 | 2008-02-06 | 2008-02-06 | 2009-02-06 | 2009-02-06
| 050.21932 | 050.3351.M & R Test Equip | Test equipment for m & R personnel in the 3351 sub-region | 17881.4 | 14795.44 | 3085.96 | 20.86% | 0.1028% | 17881.4 | 14795.44 | 3085.96 | 2008-10-01 | 2009-09-30 | 2009-03-17 | 2009-03-17 | 2010-03-02 | 2010-03-02
| 050.20660 | 050.2635.Marion Bare Replace | Replace app. 1,800' - 4" bare with 4" PE in Marion, KY | 17952.22 | 42749.99 | 77008.5 | 180.1% | 0.6884% | 119758.49 | 42749.99 | 77008.5 | 2008-10-01 | 2009-09-30 | 2008-05-13 | 2008-05-13 | 2009-05-01 | 2009-05-01
| 050.19594 | Danville 08 Growth | Danville 08 Growth | 18041.13 | Not Budgeted | - | - | 1.55% | 269675.7 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22397 | 050.KY.MadisonIntegFunct2010 | 050.KY.MadisonIntegFunct2010 | 18135.35 | Not Budgeted | - | - | 0.1043% | 18135.35 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20533 | 050.BGR,GLS.LONGHUNTERS sQ. | 3270 FT - 2' PE - LONGHUNTERS SQUARE - GLASGOW | 18159.31 | 12110 | 14682.31 | 121.2% | 0.154% | 26792.31 | 12110 | 14682.31 | 2008-10-01 | 2009-09-30 | 2008-03-17 | 2008-03-17 | 2009-03-17 | 2009-03-17
| 050.22400 | 050.KY.PaducahIntegFunct2010 | 050.KY.PaducahIntegFunct2010 | 18187.19 | Not Budgeted | - | - | 0.1045% | 18187.19 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21667 | 2739.SUMMERSFIELD SEC I | INSTALL 2000' OF 2" PE FOR SUMMERSFIELD SEC I, INCLUDES 11 LONGSIDE SERVICES | 18614.39 | 20560 | -1945.61 | -9.463% | 0.107% | 18614.39 | 20560 | -1945.61 | 2008-10-01 | 2009-09-30 | 2008-11-17 | 2008-11-17 | 2009-11-17 | 2009-11-17
| 050.20887 | 2739.3rd PARTY.SVILLE 6" ST | KAY & KAY DAMAGE 6" STEEL AT HWY 55 AND HWY 60.SVILLE BYPASS - ALCAN LINE | 19207.92 | 36053 | -19630.27 | -54.45% | 0.09441% | 16422.73 | 36053 | -19630.27 | 2008-10-01 | 2009-09-30 | 2008-08-18 | 2008-08-18 | 2008-11-01 | 2008-11-01
| 050.21880 | 050.BGR.BRENNER ST. 2" eXT | 1630 FT. OF 2"PE - BRENNER ST. - B.G. | 19286.05 | 24833 | -5546.95 | -22.34% | 0.1109% | 19286.05 | 24833 | -5546.95 | 2008-10-01 | 2009-09-30 | 2009-02-18 | 2009-02-18 | 2010-02-18 | 2010-02-18
| 050.19598 | Shelbyville 08 Growth | Shelbyville 08 Growth | 19778.65 | Not Budgeted | - | - | 2.105% | 366204.15 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22118 | 050.2637.Palma Purch Imp | This project is for improvements at our Palma, KY purchase station. Improvements include purchasing a new fiberglass bldg and putting our electronics (incl. ROC) inside out of the elements. This is a revision 6/19 | 19876.73 | 13511 | 6365.73 | 47.12% | 0.1143% | 19876.73 | 13511 | 6365.73 | 2008-10-01 | 2009-09-30 | 2009-06-23 | 2009-06-23 | 2009-09-30 | 2009-09-30
| 050.20795 | 050.BGR.FIRESTON REG REPLC | REGULATOR REPLACEMENT - FIRESTONE PURCHASE - BOWLING GREEN | 20552.15 | 22822 | -2022.09 | -8.86% | 0.1196% | 20799.91 | 22822 | -2022.09 | 2008-10-01 | 2009-09-30 | 2008-07-18 | 2008-07-18 | 2009-07-18 | 2009-07-18
| 050.20899 | 050.2636.Fordsville TB Rplmnt. | Replace Fordsville TB Station | 20757.2 | 24163.66 | -3406.46 | -14.1% | 0.1193% | 20757.2 | 24163.66 | -3406.46 | 2008-10-01 | 2009-09-30 | 2008-08-25 | 2008-08-25 | 2008-09-28 | 2008-09-28
| 050.22113 | 050.2736.Mooney Regs. | Purchase New Mooney Regs. for Hopkinsville TB 1 | 20821.33 | 23254.28 | -2432.95 | -10.46% | 0.1197% | 20821.33 | 23254.28 | -2432.95 | 2008-10-01 | 2009-09-30 | 2009-06-22 | 2009-06-22 | 2009-09-28 | 2009-09-28
| 050.19593 | Hopkinsville 08 Non Growth | Hopkinsville 08 Non Growth | 20854.94 | Not Budgeted | - | - | 2.2% | 382720.05 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19597 | Campbellsville 08 Non Growth | Campbellsville 08 Non Growth | 20960.17 | Not Budgeted | - | - | 2.114% | 367789.81 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20850 | 050.BGR.BELLE HAVEN I | 3975 FT. OF 2" PE - BELLE HAVEN PHASE I - B.G. | 21011.49 | 14018 | 7321.3 | 52.23% | 0.1227% | 21339.3 | 14018 | 7321.3 | 2008-10-01 | 2009-09-30 | 2008-08-06 | 2008-08-06 | 2009-08-06 | 2009-08-06
| 050.22470 | 050.3305.Boiler Replacement | Replace Boiler leased property 2410 New Hartford Rd. | 21517.07 | 28759.57 | -7242.5 | -25.18% | 0.1237% | 21517.07 | 28759.57 | -7242.5 | 2008-10-01 | 2009-09-30 | 2009-09-29 | 2009-09-29 | 2009-09-30 | 2009-09-30
| 050.19591 | Glasgow 08 Non Growth | Glasgow 08 Non Growth | 21684.78 | Not Budgeted | - | - | 2.82% | 490554.67 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2009-05-13 | 2009-05-13
| 050.21849 | 050.2636.Habit 12" | Rework Habit Station | 21695.69 | 22621.54 | -925.85 | -4.093% | 0.1247% | 21695.69 | 22621.54 | -925.85 | 2008-10-01 | 2009-09-30 | 2009-02-03 | 2009-02-03 | 2009-07-01 | 2009-07-01
| 050.21856 | 050.2636.Maple Ave.Replacement | Replace 693' 4" LP Bare pipe with 2" PE IP | 21738.36 | 15222.87 | 6515.49 | 42.8% | 0.125% | 21738.36 | 15222.87 | 6515.49 | 2008-10-01 | 2009-09-30 | 2009-02-05 | 2009-02-05 | 2009-05-01 | 2009-05-01
| 050.20686 | 050.BGR.INDIANOLA REPLC. | 1340 FT. 2" BARE ST. REPLC - INDIANOLA - B.G. | 22174.47 | 143335 | -20932.13 | -14.6% | 0.7036% | 122402.87 | 143335 | -20932.13 | 2008-10-01 | 2009-09-30 | 2008-05-29 | 2008-05-29 | 2009-05-29 | 2009-05-29
| 050.19603 | Princeton 08 Non Growth | Princeton 08 Non Growth | 24739.99 | Not Budgeted | - | - | 1.379% | 239900.94 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19606 | Paducah 08 Growth | Paducah 08 Growth | 24843.84 | Not Budgeted | - | - | 2.769% | 481743.91 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22207 | 050.2734.4 in Wn Gate Valves | Replace two 4 inch Williamson gate valves, Bowling Green | 26718.39 | 28832.8 | -2114.41 | -7.333% | 0.1536% | 26718.39 | 28832.8 | -2114.41 | 2008-10-01 | 2009-09-30 | 2009-08-06 | 2009-08-06 | 2009-09-29 | 2009-09-29
| 050.22399 | 050.KY.OboroIntegFunct2010 | 050.KY.OboroIntegFunct2010 | 26912.62 | Not Budgeted | - | - | 0.1547% | 26912.62 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22437 | 050.KY.OboroLeakFunct2010 | 050.KY.OboroLeakFunct2010 | 28106.61 | Not Budgeted | - | - | 0.1616% | 28106.61 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20778 | 050.2636.Habit YZ Odorizer | Replace Odorizer at Habit purchase | 28923.88 | 24934.05 | 3989.83 | 16% | 0.1663% | 28923.88 | 24934.05 | 3989.83 | 2008-10-01 | 2009-09-30 | 2008-07-10 | 2008-07-10 | 2008-09-28 | 2008-09-28
| 050.19609 | Mayfield 08 Non Growth | Mayfield 08 Non Growth | 31015.92 | Not Budgeted | - | - | 2.332% | 405727.3 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22433 | 050.KY.CampbellLeakFunct2010 | 050.KY.CampbellLeakFunct2010 | 32951.98 | Not Budgeted | - | - | 0.1894% | 32951.98 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.20934 | 050.BGR.HOE RAM | HOE RAM - BOWLING GREEN AREA | 33280.85 | 24272 | 9008.85 | 37.12% | 0.1913% | 33280.85 | 24272 | 9008.85 | 2008-10-01 | 2009-09-30 | 2008-09-03 | 2008-09-03 | 2009-09-03 | 2009-09-03
| 040.13099 | 040.2739.SUMMERFIELD PH-I | INSTALL 3500' OF 2" PE FOR SUMMERFIELD PH I | 33489 | 27357 | -2879.38 | -10.53% | 0.1407% | 24477.62 | 27357 | -2879.38 | 2008-10-01 | 2009-09-30 | 2006-08-15 | 2006-08-15 | 2007-08-15 | 2007-08-15
| 050.19601 | Madisonville 08 Non Growth | Madisonville 08 Non Growth | 34427.62 | Not Budgeted | - | - | 2.809% | 488721.61 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19595 | Danville 08 Non Growth | Danville 08 Non Growth | 35482.33 | Not Budgeted | - | - | 4.061% | 706509.63 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22195 | 050.009.2734.TB3Replacement | TB 3 relocation in cojunction with Highland Way Replacement | 37980.29 | 50336.17 | -12355.88 | -24.55% | 0.2183% | 37980.29 | 50336.17 | -12355.88 | 2008-10-01 | 2009-09-30 | 2009-07-30 | 2009-07-30 | 2009-09-28 | 2009-09-28
| 050.20773 | 2739.TBS.HOSPITAL STATION | REBUILD THE HOSPITAL TBS STATION | 38263.67 | 48407 | 3959.51 | 8.18% | 0.301% | 52366.51 | 48407 | 3959.51 | 2008-10-01 | 2009-09-30 | 2008-07-09 | 2008-07-09 | 2008-12-12 | 2008-12-12
| 050.19588 | Bowling Green 08 Growth | Bowling Green 08 Growth | 40988.81 | Not Budgeted | - | - | 6.404% | 1114047.31 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.21530 | TchSvr.Mea.Meters-Large Volume | Large Volume Meters for Replacement of Damage Meters | 41300.64 | 23435 | 17865.64 | 76.23% | 0.2374% | 41300.64 | 23435 | 17865.64 | 2008-10-01 | 2009-09-30 | 2008-10-15 | 2008-10-15 | 2009-09-30 | 2009-09-30
| 050.21958 | 050.2602 Replace PCs | Replace dated PCs | 41353.2 | 168326.32 | -126973.12 | -75.43% | 0.2377% | 41353.2 | 168326.32 | -126973.12 | 2008-10-01 | 2009-09-30 | 2009-03-27 | 2009-03-27 | 2009-09-25 | 2009-09-25
| 050.21628 | 050.BGR.GLS.HWY 31W RELOC. | 1100 FT OF 2" PE - HYW 31W - MUNFORDVILLE | 43233.68 | 53495 | -10261.32 | -19.18% | 0.2485% | 43233.68 | 53495 | -10261.32 | 2008-10-01 | 2009-09-30 | 2008-11-11 | 2008-11-11 | 2009-11-11 | 2009-11-11
| 050.22320 | 050.2602.Replace MDTs2 | Replace dated MDTs | 43608.81 | 156386.6 | -112777.79 | -72.11% | 0.2507% | 43608.81 | 156386.6 | -112777.79 | 2008-10-01 | 2009-09-30 | 2009-09-08 | 2009-09-08 | 2009-09-28 | 2009-09-28
| 050.22117 | 050.2636.Vapor Extractor | Purchase Vapor Extractor and Trailer | 43799.83 | 46787.04 | -2987.21 | -6.385% | 0.2518% | 43799.83 | 46787.04 | -2987.21 | 2008-10-01 | 2009-09-30 | 2009-06-23 | 2009-06-23 | 2009-09-28 | 2009-09-28
| 050.19607 | Paducah 08 Non Growth | Paducah 08 Non Growth | 47651.24 | Not Budgeted | - | - | 5.446% | 947463.09 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.22140 | 050.2637.Odorizer - Calvert | We plan to install an odorizer in the Calvert industrial park and abandon a dozen smaller individual drip pots.We will then dispose of these smaller units a few every year, as this is an expensive procedure. | 47954.69 | 97154 | -49199.31 | -50.64% | 0.2757% | 47954.69 | 97154 | -49199.31 | 2008-10-01 | 2009-09-30 | 2009-07-02 | 2009-07-02 | 2009-09-29 | 2009-09-29
| 050.21963 | 050.2636.Hale Ave.Reg.Sta. | Replace Regulator Station damaged in car accident | 49049.12 | 51834.59 | -2785.47 | -5.374% | 0.282% | 49049.12 | 51834.59 | -2785.47 | 2008-10-01 | 2009-09-30 | 2009-03-31 | 2009-03-31 | 2009-08-03 | 2009-08-03
| 050.22352 | 050.KY.BowlgGrnGrowthFunct2010 | 050.KY.BowlgGrnGrowthFunct2010 | 50233.11 | Not Budgeted | - | - | 0.2888% | 50233.11 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.22319 | 050.2602 Replace PCs2 | Replace dated PCs | 50664.4 | 156668.66 | -106004.26 | -67.66% | 0.2912% | 50664.4 | 156668.66 | -106004.26 | 2008-10-01 | 2009-09-30 | 2009-09-08 | 2009-09-08 | 2009-09-28 | 2009-09-28
| 050.22164 | 050.2636.Wing Ave. Rplmnt | Replace 1254 feet of 3 Inch LP Steel with 2 Inch & 1 1/4 inch IP PE. 30 services involved | 56129.12 | 78997.97 | -22868.85 | -28.95% | 0.3227% | 56129.12 | 78997.97 | -22868.85 | 2008-10-01 | 2009-09-30 | 2009-07-10 | 2009-07-10 | 2009-09-28 | 2009-09-28
| 050.20986 | 050.2634.Hanson Upgrade | Install 280' 4" PE, 120' 4" Stl. & 2" Reg Sta. | 56459.87 | 49979.77 | 6480.1 | 12.97% | 0.3246% | 56459.87 | 49979.77 | 6480.1 | 2008-10-01 | 2009-09-30 | 2008-09-22 | 2008-09-22 | 2008-11-07 | 2008-11-07
| 050.22108 | 050.2737.HUSTONVILLE TBS | REBUILD HUSTONVILLE TBS - TENNESSEE GAS TO CHANGE REGULATION AND WE NEED TO ADD REGULATOR RUN WITH GAS HEATER AND FILTRATION | 56839.01 | 122382 | -65542.99 | -53.56% | 0.3267% | 56839.01 | 122382 | -65542.99 | 2008-10-01 | 2009-09-30 | 2009-06-18 | 2009-06-18 | 2009-10-01 | 2009-10-01
| 050.21959 | 050.2602 Replace MDTs | Replace dated MDTs | 58331.75 | 168292.66 | -109960.91 | -65.34% | 0.3353% | 58331.75 | 168292.66 | -109960.91 | 2008-10-01 | 2009-09-30 | 2009-03-27 | 2009-03-27 | 2009-09-28 | 2009-09-28
| 050.21084 | Mayfield 09 Growth | Mayfield 09 Growth | 67361.36 | Not Budgeted | - | - | 0.3872% | 67361.36 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20764 | 050.2636.Hwy 60 By Pass 1 | Hwy Relocation install 2,516' 4" PE, 246' 8" Stl., 187' 2" PE | 69227.13 | 57691.78 | 39582.27 | 68.61% | 0.5592% | 97274.05 | 57691.78 | 39582.27 | 2008-10-01 | 2009-09-30 | 2008-07-07 | 2008-07-07 | 2008-09-28 | 2008-09-28
| 050.21770 | 050.2636.Warehouse Shelving | Purchase Shelving for New Warehouse | 69290.04 | 66627.21 | 2662.83 | 3.997% | 0.3983% | 69290.04 | 66627.21 | 2662.83 | 2008-10-01 | 2009-09-30 | 2008-12-14 | 2008-12-14 | 2009-06-01 | 2009-06-01
| 050.19605 | Owensboro 08 Non Growth | Owensboro 08 Non Growth | 73068.92 | Not Budgeted | - | - | 8.478% | 1474828.56 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20977 | 050.2637.Pad Office Repairs | Repairs to Paducah office incurred on Sunday, September 14th from winds of tropical depression "Ike" | 76355.9 | 47918.31 | 30937.87 | 64.56% | 0.4533% | 78856.18 | 47918.31 | 30937.87 | 2008-10-01 | 2009-09-30 | 2008-09-15 | 2008-09-15 | 2009-09-02 | 2009-09-02
| 050.20799 | 2739.NORTHRIDGE VILLAS PH I | INSTALL 2"' AND 4" PE FOR NORTHRIDGE VILLAS OFF HWY 53 | 78567.31 | 49188 | 29379.31 | 59.73% | 0.4516% | 78567.31 | 49188 | 29379.31 | 2008-10-01 | 2009-09-30 | 2008-07-21 | 2008-07-21 | 2009-07-21 | 2009-07-21
| 050.22002 | 050.2637.Facility Repair Pad | We had a "equipment/material" shed damaged by straight line winds on April 12,2009 at our Paducah, KY office.Roof was completely blown off, severe damage to the trusses, electrical system, etc. | 80842.97 | 67634.85 | 13208.12 | 19.53% | 0.4647% | 80842.97 | 67634.85 | 13208.12 | 2008-10-01 | 2009-09-30 | 2009-04-28 | 2009-04-28 | 2009-09-25 | 2009-09-25
| 050.22194 | 050.2734.Covington Replc. | 050.2734.Covington Bare Steel Replc. | 85865.1 | 113411.92 | -27546.82 | -24.29% | 0.4936% | 85865.1 | 113411.92 | -27546.82 | 2008-10-01 | 2009-09-30 | 2009-07-30 | 2009-07-30 | 2009-09-25 | 2009-09-25
| 050.21072 | Campbellsville 09 Growth | Campbellsville 09 Growth | 90485.53 | Not Budgeted | - | - | 0.5202% | 90485.53 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.19589 | Bowling Green 08 Non Growth | Bowling Green 08 Non Growth | 94656.73 | Not Budgeted | - | - | 12.19% | 2120851.55 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.21004 | 050.2602.NBUILD.PHONESYS | Installing phone system in the new Owensboro, KY office | 95704.25 | 116521.23 | -20816.98 | -17.87% | 0.5502% | 95704.25 | 116521.23 | -20816.98 | 2008-10-01 | 2009-09-30 | 2008-09-26 | 2008-09-26 | 2008-09-29 | 2008-09-29
| 050.22149 | 2738.N FOREST REPLACEMENT | REPLACE STEEL MAIN ON NORTH FOREST BETWEEN HOOD AND BOLDRICK | 105296.39 | 84801.69 | 20494.7 | 24.17% | 0.6053% | 105296.39 | 84801.69 | 20494.7 | 2008-10-01 | 2009-09-30 | 2009-07-07 | 2009-07-07 | 2010-06-01 | 2010-06-01
| 050.21066 | Glasgow 09 Growth | Glasgow 09 Growth | 108295.92 | Not Budgeted | - | - | 0.6225% | 108295.92 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21078 | Princeton 09 Growth | Princeton 09 Growth | 112472.64 | Not Budgeted | - | - | 0.6465% | 112472.64 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21068 | Hopkinsville 09 Growth | Hopkinsville 09 Growth | 123564.34 | Not Budgeted | - | - | 0.7103% | 123564.34 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20824 | 050.BGR.OLIVERR ST. REPLC. | 2700' OF 2" PE - OLIVER ST. 4" BARE REPLC.. - B.G | 127730.02 | 198079 | -6596.06 | -3.33% | 1.101% | 191482.94 | 198079 | -6596.06 | 2008-10-01 | 2009-09-30 | 2008-07-25 | 2008-07-25 | 2009-07-25 | 2009-07-25
| 050.20484 | 050.2609.Bon Harbor Well # 9 | Workover Well # 9 Bon Harbor | 128693.25 | 183203.93 | 3009.08 | 1.642% | 1.07% | 186213.01 | 183203.93 | 3009.08 | 2008-10-01 | 2009-09-30 | 2008-02-21 | 2008-02-21 | 2009-08-01 | 2009-08-01
| 050.20923 | 050.2609.Bon Harbor Well #7 | Workover Bon Harbor Well #7 | 132676.92 | 183551.6 | 6830.89 | 3.722% | 1.094% | 190382.49 | 183551.6 | 6830.89 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20924 | 050.2609.Bon Harbor Well #8 | Workover Bon Harbor Well #8 | 138620.16 | 183551.6 | 6725.89 | 3.664% | 1.094% | 190277.49 | 183551.6 | 6725.89 | 2008-10-01 | 2009-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.21074 | Shelbyville 09 Growth | Shelbyville 09 Growth | 143915.79 | Not Budgeted | - | - | 0.8273% | 143915.79 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20483 | 050.2609.Bon Harbor Well # 5 | Workover Bon Harbor Well # 5 | 152440.81 | 183203.93 | 28665.1 | 15.65% | 1.218% | 211869.03 | 183203.93 | 28665.1 | 2008-10-01 | 2009-09-30 | 2008-02-20 | 2008-02-20 | 2009-08-01 | 2009-08-01
| 050.21630 | 050.BGR.BROADWAY & KENTON | 1645 FT. OF 2" PE- BROADWAY & KENTON REPLACEMENT | 152899.64 | 246330 | -93430.36 | -37.93% | 0.8789% | 152899.64 | 246330 | -93430.36 | 2008-10-01 | 2009-09-30 | 2008-11-12 | 2008-11-12 | 2009-11-12 | 2009-11-12
| 050.22429 | 050.KY.BowlGrnLeakFunct2010 | 050.KY.BowlGrnLeakFunct2010 | 161223.62 | Not Budgeted | - | - | 0.9268% | 161223.62 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21079 | Princeton 09 Non Growth | Princeton 09 Non Growth | 188838.88 | Not Budgeted | - | - | 1.086% | 188838.88 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20695 | 050.BGR.HOP.MAIN ST.REPLC. | MAIN ST. BARE STEEL REPLC. - HOPKINSVILLE | 206243.86 | 229480.7 | -4186.3 | -1.824% | 1.295% | 225294.4 | 229480.7 | -4186.3 | 2008-10-01 | 2009-09-30 | 2008-06-09 | 2008-06-09 | 2008-06-09 | 2008-06-09
| 050.21076 | Madisonville 09 Growth | Madisonville 09 Growth | 209653.02 | Not Budgeted | - | - | 1.205% | 209653.02 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21070 | Danville 09 Growth | Danville 09 Growth | 209985.66 | Not Budgeted | - | - | 1.209% | 210261.84 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21864 | 050.BGR.HIGHLAND ST. REPLC. | 3200 FT. OF 4" REPLC. - HIGHLAND ST. - B.G. | 218390.86 | 248331 | -29940.14 | -12.06% | 1.255% | 218390.86 | 248331 | -29940.14 | 2008-10-01 | 2009-09-30 | 2009-02-10 | 2009-02-10 | 2010-02-11 | 2010-02-11
| 050.21528 | TchSvr.Mea.Outsourced Meters | Oursourced meter retirments and new meter purchases | 293261.84 | 195288 | 97973.84 | 50.17% | 1.686% | 293261.84 | 195288 | 97973.84 | 2008-10-01 | 2009-09-30 | 2008-10-15 | 2008-10-15 | 2009-09-30 | 2009-09-30
| 050.21075 | Shelbyville 09 Non Growth | Shelbyville 09 Non Growth | 314584.72 | Not Budgeted | - | - | 1.808% | 314584.72 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21085 | Mayfield 09 Non Growth | Mayfield 09 Non Growth | 338043.01 | Not Budgeted | - | - | 1.943% | 338043.01 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21082 | Paducah 09 Growth | Paducah 09 Growth | 362494.94 | Not Budgeted | - | - | 2.084% | 362494.94 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21080 | Owensboro 09 Growth | Owensboro 09 Growth | 408047.71 | Not Budgeted | - | - | 2.346% | 408047.71 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21067 | Glasgow 09 Non Growth | Glasgow 09 Non Growth | 439684.2 | Not Budgeted | - | - | 2.528% | 439684.2 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21069 | Hopkinsville 09 Non Growth | Hopkinsville 09 Non Growth | 472239.42 | Not Budgeted | - | - | 2.715% | 472239.42 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.22391 | 050.KY.BowlGrnIntegFunct2010 | 050.KY.BowlGrnIntegFunct2010 | 510854.27 | Not Budgeted | - | - | 2.937% | 510854.27 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2009-09-10 | 2009-09-10 | 2010-09-30 | 2010-09-30
| 050.21584 | 050.2636.FURNITURE09 | Purchase furniture for the new Owensboro office in KY | 531732.28 | 499800 | 31932.28 | 6.389% | 3.057% | 531732.28 | 499800 | 31932.28 | 2008-10-01 | 2009-09-30 | 2008-10-30 | 2008-10-30 | 2009-06-24 | 2009-06-24
| 050.21917 | 050.2609.Nort'ville Hwy 62 12" | 050.2609 Replace 10" 90-159-10 at Hwy 62 w/ 12" | 542806.19 | 638316.21 | -95510.02 | -14.96% | 3.12% | 542806.19 | 638316.21 | -95510.02 | 2008-10-01 | 2009-09-30 | 2009-03-09 | 2009-03-09 | 2009-09-25 | 2009-09-25
| 050.21073 | Campbellsville 09 Non Growth | Campbellsville 09 Non Growth | 582115.41 | Not Budgeted | - | - | 3.346% | 582115.41 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21077 | Madisonville 09 Non Growth | Madisonville 09 Non Growth | 628272.25 | Not Budgeted | - | - | 3.612% | 628272.25 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21071 | Danville 09 Non Growth | Danville 09 Non Growth | 652097.67 | Not Budgeted | - | - | 3.755% | 653195.51 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21064 | Bowling Green 09 Growth | Bowling Green 09 Growth | 697946.09 | Not Budgeted | - | - | 4.012% | 697946.09 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21083 | Paducah 09 Non Growth | Paducah 09 Non Growth | 951138.55 | Not Budgeted | - | - | 5.468% | 951138.55 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20663 | 050.2609.Hopkinsville 10" | Replacing 2 miles of 10" Stl. with 12" Stl. | 1181206.35 | 2088080.62 | 625043.32 | 29.93% | 15.6% | 2713123.94 | 2088080.62 | 625043.32 | 2008-10-01 | 2009-09-30 | 2008-05-15 | 2008-05-15 | 2008-12-31 | 2008-12-31
| 050.21081 | Owensboro 09 Non Growth | Owensboro 09 Non Growth | 1454329.55 | Not Budgeted | - | - | 8.362% | 1454571.97 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.21065 | Bowling Green 09 Non Growth | Bowling Green 09 Non Growth | 1613176.97 | Not Budgeted | - | - | 9.273% | 1613176.97 | Not Budgeted | - | 2008-10-01 | 2009-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20823 | 050.BGR.8"CENTER LINE HPD | 8" CENTER LINE HPD RELOC PHASE I - B.G. | 2278178.1 | 1398465 | 880891.86 | 62.99% | 13.1% | 2279356.86 | 1398465 | 880891.86 | 2008-10-01 | 2009-09-30 | 2008-07-25 | 2008-07-25 | 2009-07-25 | 2009-07-25

## 2008a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2008
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2008 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 050.21101 | 050.2634.918125-02 | MEC Forfeiture | -219182.3 | Not Budgeted | - | - | -1.165% | -219182.3 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.19508 | 05.BGR.HOP.8" LINE CUT | 8" HP LINE CUT - HOPKINSVILLE | -55499.6 | 7451.53 | -52452.7 | -703.9% | -0.2392% | -45001.17 | 7451.53 | -52452.7 | 2007-10-01 | 2008-09-30 | 2007-08-30 | 2007-08-30 | 2008-08-30 | 2008-08-30
| 050.21104 | 050.2637.0918433-01 | MEC Forfeiture | -39371 | Not Budgeted | - | - | -0.2092% | -39371 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.18693 | 050.2738.LEB BYPASS RELOCAT | RELOCATE 1400' OF 4" PE FOR THE LEBANON BYPASS - STATE PROJECT | -28619.13 | -11727.9 | 13318.53 | -113.6% | 0.008454% | 1590.63 | -11727.9 | 13318.53 | 2007-10-01 | 2008-09-30 | 2006-11-27 | 2006-11-27 | 2007-12-11 | 2007-12-11
| 050.21099 | 050.2636.918024 | MEC Forfeiture | -28347 | Not Budgeted | - | - | -0.1507% | -28347 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.21091 | 050.2637.0918285-02 | MEC Forfeiture | -27785.5 | Not Budgeted | - | - | -0.1477% | -27785.5 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.21097 | 050.2637.0918185-01 | MEC Forfeiture | -23410 | Not Budgeted | - | - | -0.1244% | -23410 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.20229 | 050.2638.Progress Rail | Relocation. Retire 4" steel, install 6" Pls | -23035.81 | 22875.06 | -45910.87 | -200.7% | -0.1224% | -23035.81 | 22875.06 | -45910.87 | 2007-10-01 | 2008-09-30 | 2007-10-19 | 2007-10-19 | 2008-10-17 | 2008-10-17
| 050.20317 | 050.2732.918025-1 | MEC Forfeiture | -22190 | Not Budgeted | - | - | -0.1179% | -22190 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-11-26 | 2007-11-26 | 2007-11-26 | 2007-11-26
| 050.19062 | transpark cosmo 4"HPD | 1300' OF 4" HPD TRANSPARK COSMO BG | -21281.08 | 23887 | -615.21 | -2.576% | 0.1237% | 23271.79 | 23887 | -615.21 | 2007-10-01 | 2008-09-30 | 2007-04-05 | 2007-04-05 | 2008-04-05 | 2008-04-05
| 050.21089 | 050.2734.0918176-01 | MEC Forfeiture | -19085 | Not Budgeted | - | - | -0.1014% | -19085 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.19353 | 050.2637.Retire Backhoe 6465 | Retire '95 Case model 580 L backhoe | -18718.9 | -22000 | 3281.1 | -14.91% | -0.09949% | -18718.9 | -22000 | 3281.1 | 2007-10-01 | 2008-09-30 | 2007-07-18 | 2007-07-18 | 2008-07-17 | 2008-07-17
| 050.21095 | 050.2636.917944 | MEC Forfeiture | -17607 | Not Budgeted | - | - | -0.09358% | -17607 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.18998 | 2739.RETIRE 6596.BACKHOE | RETIRE ASSET 16979895 UNIT 6596 | -16253.22 | -5000 | -11253.22 | 225.1% | -0.08638% | -16253.22 | -5000 | -11253.22 | 2007-10-01 | 2008-09-30 | 2007-03-13 | 2007-03-13 | 2008-03-13 | 2008-03-13
| 050.21102 | 050.2736.0918064-01 | MEC Forfeiture | -16012 | Not Budgeted | - | - | -0.0851% | -16012 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.18989 | 050.BGR.TRADITIONS SUB | 6579' -2' PE & 925 -6" PE - TRADITIONS SUB - BOWLING GREEN | -15858 | 24915 | -19207.12 | -77.09% | 0.03034% | 5707.88 | 24915 | -19207.12 | 2007-10-01 | 2008-09-30 | 2007-03-09 | 2007-03-09 | 2008-03-09 | 2008-03-09
| 050.19357 | 050.BGR.TRANSPARK 5-2 | 950 FT. OF 4" HPD - TRANSPARK LOT 5-2 | -15350.18 | 8078 | -6185.36 | -76.57% | 0.01006% | 1892.64 | 8078 | -6185.36 | 2007-10-01 | 2008-09-30 | 2007-07-19 | 2007-07-19 | 2008-07-18 | 2008-07-18
| 050.21098 | 050.2637.0918026-01 | MEC Forfeiture | -14667 | Not Budgeted | - | - | -0.07795% | -14667 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.18349 | Madisonville 07 Non Growth | Madisonville 07 Non Growth Functional | -14614.23 | Not Budgeted | - | - | 3.454% | 649943.24 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.21094 | 050.2734.0917149-01 | MEC Forfeiture | -13900 | Not Budgeted | - | - | -0.07387% | -13900 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.18341 | Hopkinsville 07 Non Growth | Hopkinsville 07 Non Growth Functional | -13598.79 | Not Budgeted | - | - | 3.222% | 606322.11 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.21096 | 050.2734.0918436-02 | MEC Forfeiture | -13056.12 | Not Budgeted | - | - | -0.06939% | -13056.12 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.21100 | 050.2634.0917950-01 | MEC Forfeiture | -12376 | Not Budgeted | - | - | -0.06577% | -12376 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.19041 | 050.BGR.MT.VIC.OLDE.TWN | 3073'of 6" and 2600' of 2" -Mt. VICTOR OLDE TOWN -B.G. | -11992.9 | 23230 | 9394.63 | 40.44% | 0.1734% | 32624.63 | 23230 | 9394.63 | 2007-10-01 | 2008-09-30 | 2007-03-30 | 2007-03-30 | 2007-03-30 | 2007-03-30
| 050.19367 | 050.2605.Gas Plant Property | Purchase Old Gas Plant Property | -11745.15 | 110000 | -110000 | -100% | 0% | 0 | 110000 | -110000 | 2007-10-01 | 2008-09-30 | 2007-07-24 | 2007-07-24 | 2007-09-20 | 2007-09-20
| 050.20323 | Retire D/W Trailer | Retire DitchWitch Trailer # 5862 | -10592.92 | 0 | -10592.92 | - | -0.0563% | -10592.92 | 0 | -10592.92 | 2007-10-01 | 2008-09-30 | 2007-11-28 | 2007-11-28 | 2007-11-29 | 2007-11-29
| 050.21103 | 050.2736.0918494-01 | MEC Forfeiture | -9872 | Not Budgeted | - | - | -0.05247% | -9872 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.21090 | 050.2638.0916799-01 | MEC Forfeiture | -9092 | Not Budgeted | - | - | -0.04832% | -9092 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 040.10452 | WKG.PAD.Hwy 121 relocate BU040 | Highway relocation | -8653.93 | 5596 | -7109.3 | -127% | -0.008043% | -1513.3 | 5596 | -7109.3 | 2007-10-01 | 2008-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.21092 | 050.2734.0918357-01 | MEC Forfeiture | -7763 | Not Budgeted | - | - | -0.04126% | -7763 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.20490 | 2738.DUMP TRUCK RETIREMENT | RETIRE CHEVY 2-TON DUMP TRUCK | -7500 | -4500 | -3000 | 66.67% | -0.03986% | -7500 | -4500 | -3000 | 2007-10-01 | 2008-09-30 | 2008-02-22 | 2008-02-22 | 2008-12-23 | 2008-12-23
| 050.19068 | 050.2738.SPRF.BALLARD RELOCATE | RELOCATE 250' OF 4" STEEL ON BALLARD ST SPRINGFIELD | -6527.71 | 11020 | -14718.14 | -133.6% | -0.01965% | -3698.14 | 11020 | -14718.14 | 2007-10-01 | 2008-09-30 | 2007-04-09 | 2007-04-09 | 2008-04-04 | 2008-04-04
| 050.18339 | Glasgow 07 Non Growth | Glasgow 07 Non Growth Functional | -6280.87 | Not Budgeted | - | - | 3.079% | 579264.99 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19269 | 050.BGR.FRK.DAVIS DR. 2" EXT | 900 FT. OF 2' STL. EXT. - DAVIS DR. - FRANKLIN | -5767.86 | 3874 | -3660.41 | -94.49% | 0.001135% | 213.59 | 3874 | -3660.41 | 2007-10-01 | 2008-09-30 | 2007-06-14 | 2007-06-14 | 2008-06-14 | 2008-06-14
| 050.21093 | 050.2734.0918482-01 | MEC Forfeiture | -5541 | Not Budgeted | - | - | -0.02945% | -5541 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-10-02 | 2008-10-02 | 2008-10-02 | 2008-10-02
| 050.18653 | 050.2612.METER REBUILD | REBUILD METERS FOR METER DEPARTMENT | -4434.73 | 249936.11 | -138517.93 | -55.42% | 0.5922% | 111418.18 | 249936.11 | -138517.93 | 2007-10-01 | 2008-09-30 | 2006-11-08 | 2006-11-08 | 2007-11-07 | 2007-11-07
| 050.20640 | 050.2634.Midtown Commons 2 | Relocate 90' 4" Stl. & Install 325' 2" PE | -3707.62 | -4.5475e-13 | -3707.62 | - | -0.0197% | -3707.62 | -4.5475e-13 | -3707.62 | 2007-10-01 | 2008-09-30 | 2008-05-07 | 2008-05-07 | 2008-07-01 | 2008-07-01
| 050.20694 | 050.2609.Retire Tractor | Retire 1986 Tractor Unit # 5136 | -3540 | -4500 | 960 | -21.33% | -0.01881% | -3540 | -4500 | 960 | 2007-10-01 | 2008-09-30 | 2008-06-09 | 2008-06-09 | 2008-08-29 | 2008-08-29
| 050.20877 | 2738.WOODLAND HEIGHTS APPROACH | INSTALL 925' OF 2" PE FROM FROEST HILLS TO WOODLAND HEIGHTS PARKWAY | -3182 | 3585 | -6126.08 | -170.9% | -0.01351% | -2541.08 | 3585 | -6126.08 | 2007-10-01 | 2008-09-30 | 2008-08-14 | 2008-08-14 | 2009-08-15 | 2009-08-15
| 050.20372 | 050.2736.918063 | MEC Forfeiture | -2877 | Not Budgeted | - | - | -0.01529% | -2877 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-01-03 | 2008-01-03 | 2008-01-03 | 2008-01-03
| 050.20887 | 2739.3rd PARTY.SVILLE 6" ST | KAY & KAY DAMAGE 6" STEEL AT HWY 55 AND HWY 60.SVILLE BYPASS - ALCAN LINE | -2785.19 | 36053 | -19630.27 | -54.45% | 0.08728% | 16422.73 | 36053 | -19630.27 | 2007-10-01 | 2008-09-30 | 2008-08-18 | 2008-08-18 | 2008-11-01 | 2008-11-01
| 050.18999 | 2738.RETIRE TRAILER BACKHOE | RETIRE BACKHOE TRAILER 16979971 | -2350 | -3500 | 1150 | -32.86% | -0.01249% | -2350 | -3500 | 1150 | 2007-10-01 | 2008-09-30 | 2007-03-13 | 2007-03-13 | 2008-03-13 | 2008-03-13
| 050.19346 | EFM. T Marzetti Company | EFM for T. Marzetti Company in Horse Cave | -2302.27 | 4714 | -3780.1 | -80.19% | 0.004963% | 933.9 | 4714 | -3780.1 | 2007-10-01 | 2008-09-30 | 2007-07-16 | 2007-07-16 | 2007-09-30 | 2007-09-30
| 050.20785 | 050.2637.Eich Rd Rev Ext | 2,300' - 2" PE for new Fed Ex building | -1552.13 | 2395.99 | -543.57 | -22.69% | 0.009845% | 1852.42 | 2395.99 | -543.57 | 2007-10-01 | 2008-09-30 | 2008-07-14 | 2008-07-14 | 2009-07-10 | 2009-07-10
| 050.20371 | 050.2736.918062 | MEC Forfeiture | -1365 | Not Budgeted | - | - | -0.007255% | -1365 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-01-03 | 2008-01-03 | 2008-01-03 | 2008-01-03
| 050.19153 | PARK CITY IND. PK 2" PE EXT | 450' OF 2" PE - PARK CITY INDUSTRIAL PARK | -1276.34 | 404.29 | -208.14 | -51.48% | 0.001042% | 196.15 | 404.29 | -208.14 | 2007-10-01 | 2008-09-30 | 2007-04-27 | 2007-04-27 | 2008-04-27 | 2008-04-27
| 050.20457 | 050.2634.Otter Lake Loop | Install 280' 2" PE | -1124.09 | 1096.15 | -2220.24 | -202.5% | -0.005974% | -1124.09 | 1096.15 | -2220.24 | 2007-10-01 | 2008-09-30 | 2008-02-12 | 2008-02-12 | 2008-09-25 | 2008-09-25
| 050.20214 | 050.2634.Welder Retirement | Retire Bobcat Welder | -1027 | -500 | -527 | 105.4% | -0.005458% | -1027 | -500 | -527 | 2007-10-01 | 2008-09-30 | 2007-10-15 | 2007-10-15 | 2007-12-28 | 2007-12-28
| 050.20929 | 050.2637.Hansen Rd Rev Ext | 315' extension for one existing residential customer (JW Wallace) | -821.76 | 2162.99 | 1409.05 | 65.14% | 0.01898% | 3572.04 | 2162.99 | 1409.05 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-09-01 | 2009-09-01
| 050.20559 | 050.2736.918440 | Mec Forfeitures | -750 | Not Budgeted | - | - | -0.003986% | -750 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31
| OH.050.17884 | WKG State A&G Overhead | WKG State A&G Overhead Project | -380.21 | 0 | -1.8626e-09 | #DIV/0! | -9.899e-15% | -1.8626e-09 | 0 | -1.8626e-09 | 2007-10-01 | 2008-09-30 | Over | head | Over | head
| 050.20525 | 050.2636.E.24th. & McConnell | Relocate 350' 2" Stl. with 2" PE. | -326.42 | 0.01 | -326.43 | - | -0.001735% | -326.42 | 0.01 | -326.43 | 2007-10-01 | 2008-09-30 | 2008-03-11 | 2008-03-11 | 2008-09-28 | 2008-09-28
| 050.19222 | 050.2609.STO Reed Minerals 4" | Replace Section of Reed Minerals 4" | -104.31 | 12351.27 | 11970.06 | 96.91% | 0.1293% | 24321.33 | 12351.27 | 11970.06 | 2007-10-01 | 2008-09-30 | 2007-05-23 | 2007-05-23 | 2007-09-28 | 2007-09-28
| 050.19257 | 050.2634.Brank St. Ground Bed | Replace depleted ground bed | -44.29 | 20322.47 | 993.05 | 4.886% | 0.1133% | 21315.52 | 20322.47 | 993.05 | 2007-10-01 | 2008-09-30 | 2007-06-07 | 2007-06-07 | 2007-09-20 | 2007-09-20
| 040.12904 | 040.PAD.N Friendship Rd Ext | 250' reveneue extension for new church | -36.99 | 896 | 4060.67 | 453.2% | 0.02634% | 4956.67 | 896 | 4060.67 | 2007-10-01 | 2008-09-30 | 2005-12-27 | 2005-12-27 | 2006-09-22 | 2006-09-22
| 050.19315 | 050.BGR.CUMBERLAND RIDGE IV | 2295 FT, OF 2" PE - CUMBERLAND RIDGE IV | -23.26 | 8305 | -4036.81 | -48.61% | 0.02268% | 4268.19 | 8305 | -4036.81 | 2007-10-01 | 2008-09-30 | 2007-07-06 | 2007-07-06 | 2008-07-05 | 2008-07-05
| 050.19311 | 050.BGR.GLS.LONHUNTERS RELOC. | 800 FT. OF 4' PE RELOCATION - LONGHUNTERS SQUARE - GLASGOW | -20.94 | 0 | 8601.42 | - | 0.04571% | 8601.42 | 0 | 8601.42 | 2007-10-01 | 2008-09-30 | 2007-07-05 | 2007-07-05 | 2008-07-05 | 2008-07-05
| 050.19264 | 2739.1100 MAIN.CAST IRON-MAIN | REPLACE CAST IRON FROM ALTON ROAD TO 10TH ON MAIN ST | -18.7 | 115700 | -56030.23 | -48.43% | 0.3171% | 59669.77 | 115700 | -56030.23 | 2007-10-01 | 2008-09-30 | 2007-06-12 | 2007-06-12 | 2007-12-13 | 2007-12-13
| 050.19263 | 050.2635.Replace-Marion | Replace 800' 2" bare main in Marion, KY. Some under new garage | -16.34 | 18263.34 | -11817.46 | -64.71% | 0.03426% | 6445.88 | 18263.34 | -11817.46 | 2007-10-01 | 2008-09-30 | 2007-06-11 | 2007-06-11 | 2008-06-11 | 2008-06-11
| 050.18722 | 050.BGR.RUSS.LOGAN PUR. REG | LOGAN PURCHASE REGULATOR STATION - L | -15.37 | 37786 | 27462.44 | 72.68% | 0.3468% | 65248.44 | 37786 | 27462.44 | 2007-10-01 | 2008-09-30 | 2006-12-08 | 2006-12-08 | 2007-12-09 | 2007-12-09
| 050.20576 | 2737.RETIRE DUMP TRUCK 5259 | RETIRE 5259 F600 DUMP TRUCK | -15 | -3000 | 2985 | -99.5% | -7.972e-05% | -15 | -3000 | 2985 | 2007-10-01 | 2008-09-30 | 2008-04-07 | 2008-04-07 | 2008-08-28 | 2008-08-28
| 050.19276 | 050.2636.Days Inn | Install 330' 2" PE | -13.91 | 2280.14 | 929.93 | 40.78% | 0.01706% | 3210.07 | 2280.14 | 929.93 | 2007-10-01 | 2008-09-30 | 2007-06-19 | 2007-06-19 | 2007-08-23 | 2007-08-23
| 050.19316 | 050.BGR.MCLELLAN FARMS II | 1860 FT. OF 2" PE - MCLELLANS FARMS II - B.G. | -13.89 | 6361 | -3804.61 | -59.81% | 0.01359% | 2556.39 | 6361 | -3804.61 | 2007-10-01 | 2008-09-30 | 2007-07-06 | 2007-07-06 | 2008-07-05 | 2008-07-05
| 050.19417 | 050.2636 Fountain View Ct. | Install 524' 2" PE | -13.15 | 3341.18 | -426.3 | -12.76% | 0.01549% | 2914.88 | 3341.18 | -426.3 | 2007-10-01 | 2008-09-30 | 2007-08-16 | 2007-08-16 | 2007-08-31 | 2007-08-31
| 050.18895 | 050.BGR.HOP.CHAMBERS CT. EXT. | 700 FT OF 2" PE - CHAMBERS CT. - HOPKINSVILLE | -12.48 | 5157 | -1207.95 | -23.42% | 0.02099% | 3949.05 | 5157 | -1207.95 | 2007-10-01 | 2008-09-30 | 2007-01-29 | 2007-01-29 | 2008-01-29 | 2008-01-29
| 050.18835 | 050.BGR.HOP.GREAT OAKS 15-2 | 1455 FT. OF 2" PE - GREAT OAKS 15-2 - HOPKINSVILLE | -11.44 | 7775 | 1105 | 14.21% | 0.04719% | 8880 | 7775 | 1105 | 2007-10-01 | 2008-09-30 | 2007-01-09 | 2007-01-09 | 2008-01-09 | 2008-01-09
| 050.19399 | 050.3345.Front St Relocation | Replace 400' - 2" PE. City of Metropolis improving Front Strret, small amount of 2" PE is affected. | -10.86 | 3777.71 | 1050.7 | 27.81% | 0.02566% | 4828.41 | 3777.71 | 1050.7 | 2007-10-01 | 2008-09-30 | 2007-08-03 | 2007-08-03 | 2008-08-01 | 2008-08-01
| 050.19286 | 050.2636.Sutherland Rd. | Install 100' 2" PE | -9.84 | 1607.66 | 224.3 | 13.95% | 0.009736% | 1831.96 | 1607.66 | 224.3 | 2007-10-01 | 2008-09-30 | 2007-06-25 | 2007-06-25 | 2007-08-17 | 2007-08-17
| 050.18873 | 050.OBO. Chart Recorders | Purchase Chart Recorders | -8.84 | 33346.49 | 2426.75 | 7.277% | 0.1901% | 35773.24 | 33346.49 | 2426.75 | 2007-10-01 | 2008-09-30 | 2007-01-19 | 2007-01-19 | 2007-07-31 | 2007-07-31
| OH.040.10000 | WKG BU A&G Overhead | WKG Business Unit A&G Overhead Project | -8.54 | 0 | -38000 | #DIV/0! | -0.202% | -38000 | 0 | -38000 | 2007-10-01 | 2008-09-30 | Over | head | Over | head
| 050.18988 | 050.2737.PREMIER VILLAGE | INSTALL 3000' OF 2" PE IN PREMIER VILLAGE | -7.03 | 18000 | 4699.88 | 26.11% | 0.1206% | 22699.88 | 18000 | 4699.88 | 2007-10-01 | 2008-09-30 | 2007-03-08 | 2007-03-08 | 2008-03-08 | 2008-03-08
| 050.19287 | 050.2636.Nicholas Dr. | Install 295' 2" PE | -6.89 | 3773.5 | -1285.44 | -34.06% | 0.01322% | 2488.06 | 3773.5 | -1285.44 | 2007-10-01 | 2008-09-30 | 2007-06-25 | 2007-06-25 | 2007-08-24 | 2007-08-24
| 050.19008 | 050.BGR.B.G.CHAMBER RELOC | 790 FT. OF 2" PE - B.G. CHAMBER RELOC. | -6.77 | 7008 | -3875.99 | -55.31% | 0.01665% | 3132.01 | 7008 | -3875.99 | 2007-10-01 | 2008-09-30 | 2007-03-15 | 2007-03-15 | 2008-03-15 | 2008-03-15
| 050.19192 | 050.2636.Earl Russell Court 1 | Install 202' 2" PE | -4.83 | 1892.66 | 17.89 | 0.9452% | 0.01015% | 1910.55 | 1892.66 | 17.89 | 2007-10-01 | 2008-09-30 | 2007-05-09 | 2007-05-09 | 2007-08-31 | 2007-08-31
| 050.18652 | 050.PTON.Cadiz Sys Imp | Install 330' - 4" PE as well as 330' - 8" steel casing pipe | -4.18 | 18682.35 | 5206.1 | 27.87% | 0.127% | 23888.45 | 18682.35 | 5206.1 | 2007-10-01 | 2008-09-30 | 2006-11-08 | 2006-11-08 | 2007-11-08 | 2007-11-08
| 050.19670 | 050.3351.F I Unit | Purchase F I unit DP-4 Heath | -3.77 | 7995.58 | -1447.28 | -18.1% | 0.0348% | 6548.3 | 7995.58 | -1447.28 | 2007-10-01 | 2008-09-30 | 2007-10-01 | 2007-10-01 | 2008-10-06 | 2008-10-06
| 040.13040 | 040.OBO.E.24TH. & BOLIVAR | INSTALL 729' 2" PE RETIRE 3" & 4" STL. | -3.47 | 29817.96 | -12757.38 | -42.78% | 0.09067% | 17060.58 | 29817.96 | -12757.38 | 2007-10-01 | 2008-09-30 | 2006-06-15 | 2006-06-15 | 2006-08-31 | 2006-08-31
| 050.19322 | 050.BGR.FRK.BRICK ST EXT | 100 FT. OF 2' PE - BRICK ST - FRANKLIN | -2.18 | 3604 | -3163.16 | -87.77% | 0.002343% | 440.84 | 3604 | -3163.16 | 2007-10-01 | 2008-09-30 | 2007-07-06 | 2007-07-06 | 2008-07-05 | 2008-07-05
| 050.18848 | 2739.TWIN SPRINGS.JOINT TRENCH | INSTALL 2100' OF 2",900' OF 4"-JOINT TRENCH | -1.31 | 30110 | 4339.01 | 14.41% | 0.1831% | 34449.01 | 30110 | 4339.01 | 2007-10-01 | 2008-09-30 | 2007-01-10 | 2007-01-10 | 2008-01-10 | 2008-01-10
| 050.20471 | 050.2609.Bon Harbor Shutdown | Safety Shutdown for Bon Harbor Compressor | 0 | 9066.35 | -9066.35 | -100% | 0% | 0 | 9066.35 | -9066.35 | 2007-10-01 | 2008-09-30 | 2008-02-15 | 2008-02-15 | 2008-09-26 | 2008-09-26
| 050.20474 | 050.2609.Grandview Shutdown | Safety Shutdown Grandview Compressor | 0 | 9066.35 | -9066.35 | -100% | 0% | 0 | 9066.35 | -9066.35 | 2007-10-01 | 2008-09-30 | 2008-02-17 | 2008-02-17 | 2008-09-26 | 2008-09-26
| 040.12779 | Owensboro 06 Non Growth | Owensboro 06 Non Growth | 1.28 | Not Budgeted | - | - | 8.939% | 1681927.02 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.20826 | 050.2637.Ky Dam Rd Rev Ext | 275' - 2" PE for two new homes | 1.45 | 1538.01 | 1230.14 | 79.98% | 0.01471% | 2768.15 | 1538.01 | 1230.14 | 2007-10-01 | 2008-09-30 | 2008-07-28 | 2008-07-28 | 2009-07-10 | 2009-07-10
| 050.19429 | 2739.TAYLORSVILLE ROAD 3RD | PROJECT FOR REPAIR OF DAMAGED HP LINE | 7.53 | 14703 | -14058 | -95.61% | 0.003428% | 645 | 14703 | -14058 | 2007-10-01 | 2008-09-30 | 2007-08-20 | 2007-08-20 | 2007-11-01 | 2007-11-01
| 050.19407 | 2738.LEB.PART LAND SALE | SALE OF PART OF THE LAND TOWN OPERATORS OFFICE.PROPANE PLANT | 11.49 | -24825 | 11.49 | -0.04628% | -0.1319% | -24813.51 | -24825 | 11.49 | 2007-10-01 | 2008-09-30 | 2007-08-10 | 2007-08-10 | 2008-01-01 | 2008-01-01
| 050.19418 | 050.2602RETIRE4PC07 | Retire 4 drafting PCs | 12.74 | 350 | -283.69 | -81.05% | 0.0003524% | 66.31 | 350 | -283.69 | 2007-10-01 | 2008-09-30 | 2007-08-17 | 2007-08-17 | 2007-09-27 | 2007-09-27
| 050.19339 | 050.2636.Warehouse Rd. | Install 1008' 2" PE | 22.99 | 1869.71 | -2061.56 | -110.3% | -0.00102% | -191.85 | 1869.71 | -2061.56 | 2007-10-01 | 2008-09-30 | 2007-07-11 | 2007-07-11 | 2007-09-26 | 2007-09-26
| 050.20253 | 050.BGR.FRK.FEDERAL ST. | 360 FT. OF 2" PE - FEDERAL ST. - FRANKLIN | 40.4 | 1047 | -1006.6 | -96.14% | 0.0002147% | 40.4 | 1047 | -1006.6 | 2007-10-01 | 2008-09-30 | 2007-10-29 | 2007-10-29 | 2008-10-29 | 2008-10-29
| 050.18885 | 2739.CARDINAL OAKS 2a | INSTALL 600' FOR 8 PATIO HOMES CARDINAL OAKS | 42.05 | 2070 | -395 | -19.08% | 0.008902% | 1675 | 2070 | -395 | 2007-10-01 | 2008-09-30 | 2007-01-24 | 2007-01-24 | 2008-02-01 | 2008-02-01
| 050.19404 | 050.2635.Fence Replace TB 1 | Replace "old" fence | 55.05 | 6103.55 | 299.08 | 4.9% | 0.03403% | 6402.63 | 6103.55 | 299.08 | 2007-10-01 | 2008-09-30 | 2007-08-08 | 2007-08-08 | 2008-08-08 | 2008-08-08
| 050.19345 | EFM.Taylor Co Hospital | EFM for Taylor County Hospital in Campbellville | 58.23 | 4714 | -1419.6 | -30.11% | 0.01751% | 3294.4 | 4714 | -1419.6 | 2007-10-01 | 2008-09-30 | 2007-07-16 | 2007-07-16 | 2007-09-30 | 2007-09-30
| 050.19432 | 2738.COX INTERIOR RETIREMENT | RETIRE 500' OF 4" PE AND 1 2" PE SERVICE | 86.4 | 1103 | -551.48 | -50% | 0.002931% | 551.52 | 1103 | -551.48 | 2007-10-01 | 2008-09-30 | 2007-08-21 | 2007-08-21 | 2007-12-01 | 2007-12-01
| 050.19433 | EFM.IL Transportation Cust. | EFM for IL. Honeywell, Lafarge, & Thermic | 142.66 | 7231 | -2455.16 | -33.95% | 0.02538% | 4775.84 | 7231 | -2455.16 | 2007-10-01 | 2008-09-30 | 2007-08-21 | 2007-08-21 | 2007-11-30 | 2007-11-30
| 050.19296 | 050.2637.C.G.I - Bridges | New CGI for Mike Bridges, corrosion tech | 153.35 | 2150.91 | 222.82 | 10.36% | 0.01262% | 2373.73 | 2150.91 | 222.82 | 2007-10-01 | 2008-09-30 | 2007-06-28 | 2007-06-28 | 2008-06-26 | 2008-06-26
| 050.18350 | Princeton 07 Growth | Princeton 07 Growth Functional | 221.95 | Not Budgeted | - | - | 0.1038% | 19532.7 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19344 | 050.2635.Depot St Retire | Abandon 380' - 2" steel pipe | 235.35 | 2196.17 | 1177.15 | 53.6% | 0.01793% | 3373.32 | 2196.17 | 1177.15 | 2007-10-01 | 2008-09-30 | 2007-07-13 | 2007-07-13 | 2008-07-11 | 2008-07-11
| 050.21081 | Owensboro 09 Non Growth | Owensboro 09 Non Growth | 242.42 | Not Budgeted | - | - | 7.731% | 1454571.97 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.18709 | 050.2739.MIDLAND RETIRE | RETIRE 850' ON MIDLAND INDUSTRIAL DRIVE FOR HWY BYPASS | 246.36 | 7020 | -3287.33 | -46.83% | 0.01984% | 3732.67 | 7020 | -3287.33 | 2007-10-01 | 2008-09-30 | 2006-12-01 | 2006-12-01 | 2007-06-09 | 2007-06-09
| 050.20795 | 050.BGR.FIRESTON REG REPLC | REGULATOR REPLACEMENT - FIRESTONE PURCHASE - BOWLING GREEN | 247.76 | 22822 | -2022.09 | -8.86% | 0.1105% | 20799.91 | 22822 | -2022.09 | 2007-10-01 | 2008-09-30 | 2008-07-18 | 2008-07-18 | 2009-07-18 | 2009-07-18
| 050.19675 | 050.3376.C.G.I's | 2 CGI's for use in Malden area | 270.17 | 4415.88 | 494.87 | 11.21% | 0.0261% | 4910.75 | 4415.88 | 494.87 | 2007-10-01 | 2008-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 050.21070 | Danville 09 Growth | Danville 09 Growth | 276.18 | Not Budgeted | - | - | 1.117% | 210261.84 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20489 | 050.BGR.COLLEGEVIEW 2" REPLC. | 470 FT. - 2" BARE REPLACEMENT - COLLEGEVIEW - B.G. | 310.15 | 9878 | -7796.1 | -78.92% | 0.01106% | 2081.9 | 9878 | -7796.1 | 2007-10-01 | 2008-09-30 | 2008-02-22 | 2008-02-22 | 2009-02-22 | 2009-02-22
| 050.20850 | 050.BGR.BELLE HAVEN I | 3975 FT. OF 2" PE - BELLE HAVEN PHASE I - B.G. | 327.81 | 14018 | 7321.3 | 52.23% | 0.1134% | 21339.3 | 14018 | 7321.3 | 2007-10-01 | 2008-09-30 | 2008-08-06 | 2008-08-06 | 2009-08-06 | 2009-08-06
| 050.19663 | 2737.DANVILLE EQUIPMENT | 2 DITCH WITCH LOCATORS, 1 CONCRETE SAW | 350.26 | 14216 | 3720.58 | 26.17% | 0.09533% | 17936.58 | 14216 | 3720.58 | 2007-10-01 | 2008-09-30 | 2007-09-28 | 2007-09-28 | 2007-11-01 | 2007-11-01
| 050.18344 | Campbellsville 07 Growth | Campbellsville 07 Growth Functional | 376.88 | Not Budgeted | - | - | 0.2801% | 52701.09 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19624 | 050.2637.Pipe locators | Purchase 2 pipe locators for use in Paducah | 392.36 | 5230.51 | 843.32 | 16.12% | 0.03228% | 6073.83 | 5230.51 | 843.32 | 2007-10-01 | 2008-09-30 | 2007-09-24 | 2007-09-24 | 2008-09-26 | 2008-09-26
| 050.20252 | 050.BGR.BRITE WAY 2" PE | 140 FT. OF 2" PE - BRITW WAY - BOWLING GREEN | 399.58 | 2443 | -1451.09 | -59.4% | 0.005272% | 991.91 | 2443 | -1451.09 | 2007-10-01 | 2008-09-30 | 2007-10-29 | 2007-10-29 | 2008-10-29 | 2008-10-29
| 050.18740 | 050.OBO.Lot Improvement | Grade & Gravel lot, New Fence SRV. CNTR. | 433.33 | 58717.6 | 12757.53 | 21.73% | 0.3799% | 71475.13 | 58717.6 | 12757.53 | 2007-10-01 | 2008-09-30 | 2006-12-15 | 2006-12-15 | 2007-07-27 | 2007-07-27
| 050.18338 | Glasgow 07 Growth | Glasgow 07 Growth Functional | 439.56 | Not Budgeted | - | - | 0.6535% | 122951.8 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19358 | 050.BGR.HOP.PIPE TRAILER | PLASTIC PIPE TRAILER - HOPKINSVILLE | 451.95 | 6490 | 506.23 | 7.8% | 0.03718% | 6996.23 | 6490 | 506.23 | 2007-10-01 | 2008-09-30 | 2007-07-19 | 2007-07-19 | 2008-07-19 | 2008-07-19
| 050.19677 | 050.3374.Odorator | Purchase DTEX Odorator for use in Sikeston area | 453.23 | 3257.2 | 1405.64 | 43.15% | 0.02478% | 4662.84 | 3257.2 | 1405.64 | 2007-10-01 | 2008-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 050.20851 | 050.BGR.HOPK.MARIE DR. EXT. | 230 FT. OF 2" PE -MARIEI DR. - HOPKINSVILLE | 458.04 | 2726 | -585.34 | -21.47% | 0.01138% | 2140.66 | 2726 | -585.34 | 2007-10-01 | 2008-09-30 | 2008-08-06 | 2008-08-06 | 2009-08-06 | 2009-08-06
| 050.20941 | 2738.SPR.BONNIE FARMS | INSTALL FARM TAP AND MAIN FOR BONNIE FARMS GREEN HOUSES ON HWY 55 | 460.99 | 5854 | 9132.11 | 156% | 0.07965% | 14986.11 | 5854 | 9132.11 | 2007-10-01 | 2008-09-30 | 2008-09-04 | 2008-09-04 | 2009-09-04 | 2009-09-04
| 050.19659 | 050.2634.Misc. Equipment | Purchase Pipeline Welder & Goldak locator | 507.54 | 18851.44 | 1060.54 | 5.626% | 0.1058% | 19911.98 | 18851.44 | 1060.54 | 2007-10-01 | 2008-09-30 | 2007-09-28 | 2007-09-28 | 2007-09-30 | 2007-09-30
| 050.19271 | 050.2636.Pipe Trailer | Purchase Pipe Trailer | 516.79 | 6489.84 | 1692.09 | 26.07% | 0.04348% | 8181.93 | 6489.84 | 1692.09 | 2007-10-01 | 2008-09-30 | 2007-06-15 | 2007-06-15 | 2007-09-14 | 2007-09-14
| 050.19535 | 050.3345. Pipe Locators (2) | 2 Rycom pipe locators for use in Metropolis, IL | 521.81 | 5851.04 | 290.43 | 4.964% | 0.03264% | 6141.47 | 5851.04 | 290.43 | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-09-17 | 2008-09-17
| 050.18348 | Madisonville 07 Growth | Madisonville 07 Growth Functional | 565.66 | Not Budgeted | - | - | 0.6709% | 126239.45 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20743 | 050.BGR.E 8TH 3" BARE RET. | RETIRE 335 FT. OF 3' BARE STEEL - E 8TH - B.G. | 619.47 | 1807 | -237.28 | -13.13% | 0.008343% | 1569.72 | 1807 | -237.28 | 2007-10-01 | 2008-09-30 | 2008-06-26 | 2008-06-26 | 2009-06-26 | 2009-06-26
| 050.18340 | Hopkinsville 07 Growth | Hopkinsville 07 Growth Functional | 625.2 | Not Budgeted | - | - | 0.851% | 160117.1 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18970 | 050.2609.BON HARBOR BUILDING | INSTALL NEW BUILDING AT BON HARBOR | 661.06 | 23100 | -19835.35 | -85.87% | 0.01735% | 3264.65 | 23100 | -19835.35 | 2007-10-01 | 2008-09-30 | 2007-03-02 | 2007-03-02 | 2008-03-01 | 2008-03-01
| 050.18351 | Princeton 07 Non Growth | Princeton 07 Non Growth Functional | 805.99 | Not Budgeted | - | - | 1.495% | 281282.44 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19093 | 050.2637.Reg Sta - Sys Int | Regulator station repairs and improvements | 838.7 | 9271.2 | -1907.9 | -20.58% | 0.03913% | 7363.3 | 9271.2 | -1907.9 | 2007-10-01 | 2008-09-30 | 2007-04-24 | 2007-04-24 | 2008-04-21 | 2008-04-21
| 050.19272 | 050.BGR.RETIRE REG. STA.-US31W | RETIRE LP REG STA - US31W - BGMU WATER PLANT | 839.7 | 8120 | -3492.39 | -43.01% | 0.02459% | 4627.61 | 8120 | -3492.39 | 2007-10-01 | 2008-09-30 | 2007-06-19 | 2007-06-19 | 2008-06-19 | 2008-06-19
| 050.18990 | 050.2738.LEB.METTS DR TIE-IN | INSTALL 1500' OF 4" PE ALONG HP LINE OFF METTS DRIVE | 853.25 | 17340 | -1956.57 | -11.28% | 0.08176% | 15383.43 | 17340 | -1956.57 | 2007-10-01 | 2008-09-30 | 2007-03-09 | 2007-03-09 | 2008-03-09 | 2008-03-09
| 050.20848 | 050.2636.Fairview Dr. Rt. | Retire 629' 1-1/4" PE | 883.97 | 670.32 | 213.65 | 31.87% | 0.004698% | 883.97 | 670.32 | 213.65 | 2007-10-01 | 2008-09-30 | 2008-08-05 | 2008-08-05 | 2008-09-28 | 2008-09-28
| 050.19497 | 2739.LOCUST CRK 5B | INSTALL 700' OF 2" PE IN LOCUST CREEK SECTION 5B | 971.35 | 5032 | -4060.65 | -80.7% | 0.005162% | 971.35 | 5032 | -4060.65 | 2007-10-01 | 2008-09-30 | 2007-08-28 | 2007-08-28 | 2008-01-01 | 2008-01-01
| 050.20452 | 050.GLS.METERS-REGS-RET. | METERS - REGULATOES - RETIREMENTS - GLASGOW | 1004.07 | 28349 | -27322.82 | -96.38% | 0.005454% | 1026.18 | 28349 | -27322.82 | 2007-10-01 | 2008-09-30 | 2008-02-07 | 2008-02-07 | 2009-02-07 | 2009-02-07
| 050.19437 | A.KY.TechServ.EFM.Emhart Tech. | EFM for Emhart Technologies-Hopkinsville-Transportation Contract | 1044.44 | 4714 | -3669.56 | -77.84% | 0.005551% | 1044.44 | 4714 | -3669.56 | 2007-10-01 | 2008-09-30 | 2007-08-22 | 2007-08-22 | 2007-11-30 | 2007-11-30
| 050.20442 | 050.2636.Scholar House | Install 617' 2" PE | 1060.63 | 800.8 | 259.83 | 32.45% | 0.005637% | 1060.63 | 800.8 | 259.83 | 2007-10-01 | 2008-09-30 | 2008-01-31 | 2008-01-31 | 2008-08-29 | 2008-08-29
| 050.19265 | 2739.1100 MAIN.CAST IRON-SERV | REPLACE SERVICES ON MAIN STREET FOR CAST IRON REPLACEMENT | 1068.06 | 56945 | 12721.47 | 22.34% | 0.3703% | 69666.47 | 56945 | 12721.47 | 2007-10-01 | 2008-09-30 | 2007-06-12 | 2007-06-12 | 2007-12-31 | 2007-12-31
| 050.18872 | 2739.LAW.HWY 127 4 ST RELOCATE | RELOCATE 600' OF 4" STEEL ON HWY 127 SOUTH OF HWY 44 | 1095.3 | 85200 | -28834.69 | -33.84% | 0.2996% | 56365.31 | 85200 | -28834.69 | 2007-10-01 | 2008-09-30 | 2007-01-18 | 2007-01-18 | 2008-03-01 | 2008-03-01
| 050.21071 | Danville 09 Non Growth | Danville 09 Non Growth | 1097.84 | Not Budgeted | - | - | 3.472% | 653195.51 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2008-09-29 | 2008-09-29 | 2009-10-31 | 2009-10-31
| 050.20823 | 050.BGR.8"CENTER LINE HPD | 8" CENTER LINE HPD RELOC PHASE I - B.G. | 1178.76 | 1398465 | 880891.86 | 62.99% | 12.11% | 2279356.86 | 1398465 | 880891.86 | 2007-10-01 | 2008-09-30 | 2008-07-25 | 2008-07-25 | 2009-07-25 | 2009-07-25
| 050.20774 | 050.BGR.OLDE STONE RELOC. | 810FT. 2" PE RELOC. - OLDE STONE - B.G. | 1193.91 | 0 | 1193.91 | - | 0.006345% | 1193.91 | 0 | 1193.91 | 2007-10-01 | 2008-09-30 | 2008-07-09 | 2008-07-09 | 2009-07-09 | 2009-07-09
| 050.19172 | 050.2737.607 E MAIN.LINE BREAK | REPAIR OF LINE BREAK AT CENTRE COLLEGE | 1254.86 | 11375 | -2610.93 | -22.95% | 0.04658% | 8764.07 | 11375 | -2610.93 | 2007-10-01 | 2008-09-30 | 2007-05-03 | 2007-05-03 | 2007-09-28 | 2007-09-28
| 050.19430 | 2738.TAYLOR CO HOSPT COMM DEV | INSTALL 1800' OF 2" PE FOR TAYLOR COUNTY HOSPITAL COMMERICAL DEVELOPMENT | 1271.65 | 12120 | -1426.51 | -11.77% | 0.05683% | 10693.49 | 12120 | -1426.51 | 2007-10-01 | 2008-09-30 | 2007-08-21 | 2007-08-21 | 2008-08-01 | 2008-08-01
| 050.19295 | 050.2636.Salem Dr | Install 704' 2" PE | 1309.37 | 8983.05 | 1848.41 | 20.58% | 0.05757% | 10831.46 | 8983.05 | 1848.41 | 2007-10-01 | 2008-09-30 | 2007-06-27 | 2007-06-27 | 2007-08-31 | 2007-08-31
| 050.18959 | 050.PAD.Little Lake Village | 2,420' - 2" PE revenue extension for 32 new residential lots | 1492.53 | 11132.7 | 2411.74 | 21.66% | 0.07198% | 13544.44 | 11132.7 | 2411.74 | 2007-10-01 | 2008-09-30 | 2007-02-23 | 2007-02-23 | 2008-02-22 | 2008-02-22
| 050.19349 | 050.3338.N 6th St Rev Ext | Install 300' - 2" PE for Union City Grain on N 6th Street | 1508.75 | 1799.81 | 179.46 | 9.971% | 0.01052% | 1979.27 | 1799.81 | 179.46 | 2007-10-01 | 2008-09-30 | 2007-07-16 | 2007-07-16 | 2008-07-16 | 2008-07-16
| 050.20641 | 2739.LAW.ANDERSON CO ELEM 6 ST | RELOCATE 400' OF 6" STEEL AT ANDERSON CO ELEMANTARY SCHOOL | 1517.7 | 23900 | -22382.3 | -93.65% | 0.008066% | 1517.7 | 23900 | -22382.3 | 2007-10-01 | 2008-09-30 | 2008-05-08 | 2008-05-08 | 2009-09-01 | 2009-09-01
| 050.19660 | 050.2609.STO Equipment | Purchase of New Equipment | 1574.34 | 9998.99 | 652.33 | 6.524% | 0.05661% | 10651.32 | 9998.99 | 652.33 | 2007-10-01 | 2008-09-30 | 2007-09-28 | 2007-09-28 | 2007-09-28 | 2007-09-28
| 050.19338 | 050.2637.Holt Rd Rev Ext | Install 330' 2" PE for one new commercial customer (Paducah Fed Credit Union) | 1576.82 | 1779 | 663.27 | 37.28% | 0.01298% | 2442.27 | 1779 | 663.27 | 2007-10-01 | 2008-09-30 | 2007-07-11 | 2007-07-11 | 2008-07-11 | 2008-07-11
| 050.20390 | 050.BGR.HIGH RAIL WAY 2" PE | 1300 FT. OF 2" PE - HIGH RAIL WAY - B.G. | 1576.97 | 1116 | 460.97 | 41.31% | 0.008381% | 1576.97 | 1116 | 460.97 | 2007-10-01 | 2008-09-30 | 2008-01-09 | 2008-01-09 | 2009-01-09 | 2009-01-09
| 050.20777 | TechSvr.Mea.EFM.Modine | EFM for Modine in Harrodsburg | 1615.41 | 4161 | -2438.69 | -58.61% | 0.009154% | 1722.31 | 4161 | -2438.69 | 2007-10-01 | 2008-09-30 | 2008-07-10 | 2008-07-10 | 2008-09-30 | 2008-09-30
| 050.18356 | Mayfield 07 Growth | Mayfield 07 Growth Functional | 1635.25 | Not Budgeted | - | - | 0.6941% | 130596.04 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20577 | 2737.OFFICE IMPROVEMENTS | NEW LANDSCAPE AROUND OFFICE | 1672.77 | 1439 | 233.77 | 16.25% | 0.00889% | 1672.77 | 1439 | 233.77 | 2007-10-01 | 2008-09-30 | 2008-04-07 | 2008-04-07 | 2008-08-28 | 2008-08-28
| 050.19207 | 050.BGR.RUSS.LOGAN PUR 6" | 60 FT. OF 6" STL. - LOGAN PURCHASE STATION | 1708 | 24659 | 1612.42 | 6.539% | 0.1396% | 26271.42 | 24659 | 1612.42 | 2007-10-01 | 2008-09-30 | 2007-05-17 | 2007-05-17 | 2008-05-17 | 2008-05-17
| 050.19314 | 050.2634.Liberty Church Sta. | Upgrade Reg. Station | 1743.08 | 7333.02 | 172.17 | 2.348% | 0.03989% | 7505.19 | 7333.02 | 172.17 | 2007-10-01 | 2008-09-30 | 2007-07-05 | 2007-07-05 | 2007-09-28 | 2007-09-28
| 050.20240 | 050.2637.Brenna Dr Main Ext | Install 13' - 2" PE for one new residential customer, Steve Mills is bldr | 1756.89 | 875.99 | 880.9 | 100.6% | 0.009337% | 1756.89 | 875.99 | 880.9 | 2007-10-01 | 2008-09-30 | 2007-10-23 | 2007-10-23 | 2008-10-23 | 2008-10-23
| 050.20535 | 050.BGR.FRK.HWY1008&BROWN EXT | 1525 FT. OF 2"PE - HWY 1008 & BROWN RD. - FRANKLIN | 1899 | 1088 | 811 | 74.54% | 0.01009% | 1899 | 1088 | 811 | 2007-10-01 | 2008-09-30 | 2008-03-17 | 2008-03-17 | 2009-03-17 | 2009-03-17
| 050.20620 | 050.2637.Terra Villa Rev Ext | 230' - 2" PE for one new res home (Waldridge) and two vacant lots | 1905.53 | 1541.47 | 364.06 | 23.62% | 0.01013% | 1905.53 | 1541.47 | 364.06 | 2007-10-01 | 2008-09-30 | 2008-04-29 | 2008-04-29 | 2009-04-01 | 2009-04-01
| 050.20579 | 050.2635.Marker Ball Locator | Purchase model 8890 or 8891 Rycom marker ball locator for use in the Princeton area | 1909.24 | 1496.46 | 412.78 | 27.58% | 0.01015% | 1909.24 | 1496.46 | 412.78 | 2007-10-01 | 2008-09-30 | 2008-04-08 | 2008-04-08 | 2009-04-07 | 2009-04-07
| 050.19716 | 050.2636.Highland Pointe 2 | Install 850' 2" PE | 2017.47 | 1390.15 | 627.32 | 45.13% | 0.01072% | 2017.47 | 1390.15 | 627.32 | 2007-10-01 | 2008-09-30 | 2007-10-09 | 2007-10-09 | 2007-11-30 | 2007-11-30
| 050.20454 | 2737.HARRODSBURG TBS FENCE | INSTALL FENCE AT HARRODSBURG TOWN BORDER STATION | 2020.38 | 3473 | -1452.62 | -41.83% | 0.01074% | 2020.38 | 3473 | -1452.62 | 2007-10-01 | 2008-09-30 | 2008-02-09 | 2008-02-09 | 2008-06-01 | 2008-06-01
| 050.20704 | 050.2637.Barkley Field I | 730' rev ext for new National Guard armory | 2065.15 | 18550 | -16074.79 | -86.66% | 0.01316% | 2475.21 | 18550 | -16074.79 | 2007-10-01 | 2008-09-30 | 2008-06-12 | 2008-06-12 | 2009-06-12 | 2009-06-12
| 050.20421 | 050.BGR.GLS.MARKER BALL LOC | RYCOM MARKER BALL LOCATOR - GLASGOW | 2072.59 | 1425 | 647.59 | 45.44% | 0.01102% | 2072.59 | 1425 | 647.59 | 2007-10-01 | 2008-09-30 | 2008-01-24 | 2008-01-24 | 2009-01-24 | 2009-01-24
| 050.20420 | 050.BGR.MARKER BALL LOCATOR | RYCOM MARKER BALL LOCATOR - BOWLING GREEN | 2072.62 | 1425 | 647.62 | 45.45% | 0.01102% | 2072.62 | 1425 | 647.62 | 2007-10-01 | 2008-09-30 | 2008-01-24 | 2008-01-24 | 2009-01-24 | 2009-01-24
| 050.19279 | 050.2618.SAFETY07B | Purchase of 2 SCBA units and 1 lifeline tripod | 2098.63 | 13006.96 | 29298.68 | 225.3% | 0.2248% | 42305.64 | 13006.96 | 29298.68 | 2007-10-01 | 2008-09-30 | 2007-06-20 | 2007-06-20 | 2007-09-26 | 2007-09-26
| 040.10219 | wkg.dan.cam.ret.woody | Retire vehicle #5255-woody | 2120 | -2500 | 4620 | -184.8% | 0.01127% | 2120 | -2500 | 4620 | 2007-10-01 | 2008-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.19254 | 2739.PHEASANT GLEN PH I | INSTALL 2" PE IN PHEASANT GLEN OFF BRASSFIELD RD | 2260.06 | 7780 | -1894.52 | -24.35% | 0.03128% | 5885.48 | 7780 | -1894.52 | 2007-10-01 | 2008-09-30 | 2007-06-06 | 2007-06-06 | 2008-06-06 | 2008-06-06
| 050.18599 | 050.2739.HI PONIT PH II | INSTALL 800' OF 4" PE FOR HI POINT INDUST PH II | 2261.04 | 10150 | -1865.24 | -18.38% | 0.04403% | 8284.76 | 10150 | -1865.24 | 2007-10-01 | 2008-09-30 | 2006-10-23 | 2006-10-23 | 2007-10-23 | 2007-10-23
| 050.20391 | 050.BGR. OLD LOVERS - MT. VIC. | 250 FT. OF 2" PE - OLD LOVERS & MT. VICTOR - B.G. | 2431.23 | 947 | 1484.23 | 156.7% | 0.01292% | 2431.23 | 947 | 1484.23 | 2007-10-01 | 2008-09-30 | 2008-01-09 | 2008-01-09 | 2009-01-09 | 2009-01-09
| 050.19218 | 050.2638.Jimtown Road Relocate | Install 4,000' - 2" PE/ 76% Reimburseable | 2491.48 | 10792.5 | 56024.25 | 519.1% | 0.3551% | 66816.75 | 10792.5 | 56024.25 | 2007-10-01 | 2008-09-30 | 2007-05-22 | 2007-05-22 | 2007-05-31 | 2007-05-31
| 050.20977 | 050.2637.Pad Office Repairs | Repairs to Paducah office incurred on Sunday, September 14th from winds of tropical depression "Ike" | 2500.28 | 47918.31 | 30937.87 | 64.56% | 0.4191% | 78856.18 | 47918.31 | 30937.87 | 2007-10-01 | 2008-09-30 | 2008-09-15 | 2008-09-15 | 2009-09-02 | 2009-09-02
| 050.19674 | 050.3338.Squeeze-Off | purchase 1/2" - 2" squeeze-off tool for use in Union City | 2602.62 | 897.62 | 2520.43 | 280.8% | 0.01817% | 3418.05 | 897.62 | 2520.43 | 2007-10-01 | 2008-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 050.19436 | 050.2635.Cassidy St Replace | Cassidy St replacement in Fredonia, KY 310 feet | 2629.5 | 5851.86 | -3222.36 | -55.07% | 0.01398% | 2629.5 | 5851.86 | -3222.36 | 2007-10-01 | 2008-09-30 | 2007-08-22 | 2007-08-22 | 2008-08-20 | 2008-08-20
| 050.20513 | TchSvr.Mea.EFM Logan Uniform | EFM for Logan Uniform in Shelbyville | 2650.41 | 4161 | -1378.19 | -33.12% | 0.01479% | 2782.81 | 4161 | -1378.19 | 2007-10-01 | 2008-09-30 | 2008-03-06 | 2008-03-06 | 2008-09-30 | 2008-09-30
| 050.20423 | TechServ.Meas.EFM.Hitachi | EFM for Hitachi in Harrodsburg going transportation | 2836.46 | 4161 | -1182.87 | -28.43% | 0.01583% | 2978.13 | 4161 | -1182.87 | 2007-10-01 | 2008-09-30 | 2008-01-25 | 2008-01-25 | 2008-09-30 | 2008-09-30
| 050.20963 | Utility Trailer | Measurement Dept. Utility Trailer | 2893.95 | 3675 | -770.22 | -20.96% | 0.01544% | 2904.78 | 3675 | -770.22 | 2007-10-01 | 2008-09-30 | 2008-09-09 | 2008-09-09 | 2008-09-30 | 2008-09-30
| 050.20497 | 2737.BUILDING IMPROVEMENT | INSTALL ROOF EDGE ON OFFICE AND WAREHOUSE | 2921.64 | 2267 | 654.64 | 28.88% | 0.01553% | 2921.64 | 2267 | 654.64 | 2007-10-01 | 2008-09-30 | 2008-02-27 | 2008-02-27 | 2008-10-01 | 2008-10-01
| 050.20894 | 2739.CARDINAL OAKS PATIO PH II | INSTALL 1200' OF 2" PE CARDINAL OAKS PH II | 2923.67 | 11094 | -7057.01 | -63.61% | 0.02146% | 4036.99 | 11094 | -7057.01 | 2007-10-01 | 2008-09-30 | 2008-08-21 | 2008-08-21 | 2009-08-21 | 2009-08-21
| 050.20231 | 050.HOP.NEW TOWN STATION | 1260 FT. OF 4" PE - NEW TOWN STATION - HOPK. | 3036.47 | 3626 | 7960.17 | 219.5% | 0.06158% | 11586.17 | 3626 | 7960.17 | 2007-10-01 | 2008-09-30 | 2007-10-19 | 2007-10-19 | 2008-10-18 | 2008-10-18
| 050.20328 | 050.2634.Hampton Inn | Install 424' 2" PE | 3103.02 | 4964.6 | -1861.58 | -37.5% | 0.01649% | 3103.02 | 4964.6 | -1861.58 | 2007-10-01 | 2008-09-30 | 2007-11-30 | 2007-11-30 | 2008-02-28 | 2008-02-28
| 050.20482 | 050.2637.Sarakatsannis Ext | Sarakatsannis subd rev ext/ 1,370' - 2" PE for 16 new residential lots | 3230.72 | 6184.81 | -6184.74 | -100% | 3.72e-07% | 0.07 | 6184.81 | -6184.74 | 2007-10-01 | 2008-09-30 | 2008-02-20 | 2008-02-20 | 2009-02-20 | 2009-02-20
| 050.20241 | 050.2637.Regina Drive Rev Ext | Install 575' - 2" PE for one new residential customer | 3289.27 | 1859.99 | 524.56 | 28.2% | 0.01267% | 2384.55 | 1859.99 | 524.56 | 2007-10-01 | 2008-09-30 | 2007-10-23 | 2007-10-23 | 2008-10-23 | 2008-10-23
| 050.20821 | 050.BGR 7TH & CENTER RELOC | 1700 FT. OF 2" PE 7TH & CENTER RELOC. - B.G. | 3293.07 | 0 | 3413.64 | - | 0.01814% | 3413.64 | 0 | 3413.64 | 2007-10-01 | 2008-09-30 | 2008-07-24 | 2008-07-24 | 2009-07-24 | 2009-07-24
| 050.19644 | 050.3351.Beveling Machine | 12" bevelin machine for Jeff McMullen | 3345.24 | 2985.14 | 360.1 | 12.06% | 0.01778% | 3345.24 | 2985.14 | 360.1 | 2007-10-01 | 2008-09-30 | 2007-09-27 | 2007-09-27 | 2008-09-24 | 2008-09-24
| 050.20912 | 050.MO.HANNIBALRAILROAD307018 | Burlington Norhtern Railroad Permit 307018 | 3441.1 | 2500 | 941.1 | 37.64% | 0.01829% | 3441.1 | 2500 | 941.1 | 2007-10-01 | 2008-09-30 | 2008-08-27 | 2008-08-27 | 2008-09-30 | 2008-09-30
| 050.20668 | 050.2637.Grill/Smoker | Purchase a used Traeger model 190 pellet grill/smoker | 3545.83 | 9936.09 | -6390.26 | -64.31% | 0.01885% | 3545.83 | 9936.09 | -6390.26 | 2007-10-01 | 2008-09-30 | 2008-05-16 | 2008-05-16 | 2009-05-01 | 2009-05-01
| 050.18354 | Paducah 07 Growth | Paducah 07 Growth Functional | 3645.25 | Not Budgeted | - | - | 2.694% | 506801.4 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20601 | 050.2637.Ascot Downs II | 530' revenue extension for Rodney Vaughn for 18 customers | 3651.09 | 2989.4 | 731.45 | 24.47% | 0.01978% | 3720.85 | 2989.4 | 731.45 | 2007-10-01 | 2008-09-30 | 2008-04-21 | 2008-04-21 | 2009-04-02 | 2009-04-02
| 050.20741 | 050.2634.Anton TB Replacement | Replace TB Station with MT Deason 3/4" Reg. Station | 3738.13 | 6823.05 | -3084.92 | -45.21% | 0.01987% | 3738.13 | 6823.05 | -3084.92 | 2007-10-01 | 2008-09-30 | 2008-06-25 | 2008-06-25 | 2008-09-26 | 2008-09-26
| 050.19066 | Large Volume Meters | Large Volume Meters Blanket Project | 3740.32 | 43580 | -20380.92 | -46.77% | 0.1233% | 23199.08 | 43580 | -20380.92 | 2007-10-01 | 2008-09-30 | 2007-04-09 | 2007-04-09 | 2007-09-30 | 2007-09-30
| 050.19496 | 050.BGR.ELKTON ODORANT TANK | REPLACE ODORANT TANK - ELKTON PURCHASE | 3856.03 | 0 | 7583.67 | - | 0.0403% | 7583.67 | 0 | 7583.67 | 2007-10-01 | 2008-09-30 | 2007-08-28 | 2007-08-28 | 2008-08-28 | 2008-08-28
| 050.18355 | Paducah 07 Non Growth | Paducah 07 Non Growth Functional | 3879.29 | Not Budgeted | - | - | 8.218% | 1546196.67 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20384 | TechSrv.Mea.EFM.ABSKY Corp | EFM for ABSKY Corporation in Danville | 3888.98 | 4161 | -272.02 | -6.537% | 0.02067% | 3888.98 | 4161 | -272.02 | 2007-10-01 | 2008-09-30 | 2008-01-08 | 2008-01-08 | 2008-09-30 | 2008-09-30
| 050.20385 | TechSvr.Mea.EFM.Pan Olson | EFM for Pan Olson in | 3888.98 | 4161 | -272.02 | -6.537% | 0.02067% | 3888.98 | 4161 | -272.02 | 2007-10-01 | 2008-09-30 | 2008-01-09 | 2008-01-09 | 2008-08-31 | 2008-08-31
| 050.20389 | TechSvs.Mea.EFM.Arvin Meritor | EFM for Arvin Meritor in Franklin, KY | 3891.55 | 4161 | -269.45 | -6.476% | 0.02068% | 3891.55 | 4161 | -269.45 | 2007-10-01 | 2008-09-30 | 2008-01-09 | 2008-01-09 | 2008-08-31 | 2008-08-31
| 050.19356 | 050.2638.Meadow Subd Ext III | Install 1,060' for 19 new residential lots in phase III of this subd. for John Smith | 3940.66 | 5437.35 | -1496.69 | -27.53% | 0.02094% | 3940.66 | 5437.35 | -1496.69 | 2007-10-01 | 2008-09-30 | 2007-07-19 | 2007-07-19 | 2008-07-18 | 2008-07-18
| 050.19532 | 2738.BLEVINS PARK PH II | INSTALL 1200' OF 2" PE FOR BLEVINS PARK PH II ON CVILLE BYPASS | 4107.59 | 5043 | -935.41 | -18.55% | 0.02183% | 4107.59 | 5043 | -935.41 | 2007-10-01 | 2008-09-30 | 2007-09-17 | 2007-09-17 | 2008-09-17 | 2008-09-17
| 050.18720 | 050.BGR.TRANSPARK PHASE II | 400 FT. OF 4 ST. - TRANSPARK PHASE II - B.G. | 4143.51 | 8385 | 9568.38 | 114.1% | 0.09542% | 17953.38 | 8385 | 9568.38 | 2007-10-01 | 2008-09-30 | 2006-12-07 | 2006-12-07 | 2008-09-29 | 2008-09-29
| 050.20348 | Crystal Calibrator | Crystal Calibrator for Lester Finley | 4195.71 | 8263.3 | -4067.59 | -49.22% | 0.0223% | 4195.71 | 8263.3 | -4067.59 | 2007-10-01 | 2008-09-30 | 2007-12-11 | 2007-12-11 | 2008-03-31 | 2008-03-31
| 050.20318 | 2738.HIDDEN MEADOWS.SEC H | INSTALL 1500' OF 2" PE FOR 22 LOTS | 4196.38 | 7635 | -3438.62 | -45.04% | 0.0223% | 4196.38 | 7635 | -3438.62 | 2007-10-01 | 2008-09-30 | 2007-11-26 | 2007-11-26 | 2008-11-11 | 2008-11-11
| 050.20230 | 050.HOP.KOUNTRY ACRES | 530 FT. OF 2" PE - KOUNTRY ACRES - HOPK. | 4260.61 | 5137 | -876.39 | -17.06% | 0.02264% | 4260.61 | 5137 | -876.39 | 2007-10-01 | 2008-09-30 | 2007-10-19 | 2007-10-19 | 2008-10-19 | 2008-10-19
| 050.19717 | 050.2636.Chambers Dr. | Install 650' 2" PE | 4340.73 | 2843.67 | 1497.06 | 52.65% | 0.02307% | 4340.73 | 2843.67 | 1497.06 | 2007-10-01 | 2008-09-30 | 2007-10-09 | 2007-10-09 | 2008-01-17 | 2008-01-17
| 050.18345 | Campbellsville 07 Non Growth | Campbellsville 07 Non Growth Functional | 4349.89 | Not Budgeted | - | - | 2.438% | 458712.67 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20422 | 2739.LP STATION RETIREMENT-3 | RETIRE ALTON RD, BROWN ST AND HENRY CLAY-8TH LP STATIONS | 4364.03 | 17793 | -11523.75 | -64.77% | 0.03332% | 6269.25 | 17793 | -11523.75 | 2007-10-01 | 2008-09-30 | 2008-01-24 | 2008-01-24 | 2008-01-24 | 2008-01-24
| 050.20715 | 050.2637.Locator - Bridges | Purchase Rycom model #8879 - CP for use by Mike Bridges | 4448.54 | 22026.16 | -17577.62 | -79.8% | 0.02364% | 4448.54 | 22026.16 | -17577.62 | 2007-10-01 | 2008-09-30 | 2008-06-16 | 2008-06-16 | 2009-06-16 | 2009-06-16
| 050.20723 | 050.2636.Village Run Phase 3 | Install 995' 2" Pe | 4517.76 | 6929.8 | -1948.74 | -28.12% | 0.02647% | 4981.06 | 6929.8 | -1948.74 | 2007-10-01 | 2008-09-30 | 2008-06-20 | 2008-06-20 | 2008-09-28 | 2008-09-28
| 050.20936 | 2738.COLUMBIA AVE.REPLACEMENT | REPLACE 4" STEEL IP ON COLUMBIA AVE WITH 2" PE IP | 4552.65 | 14987 | 2181.71 | 14.56% | 0.09125% | 17168.71 | 14987 | 2181.71 | 2007-10-01 | 2008-09-30 | 2008-09-03 | 2008-09-03 | 2009-09-02 | 2009-09-02
| 050.20913 | 050.IA.KEOKUKRAILROAD300212 | Burlington Northern Railroad Permit 300212 | 4747.72 | 2500 | 2247.72 | 89.91% | 0.02523% | 4747.72 | 2500 | 2247.72 | 2007-10-01 | 2008-09-30 | 2008-08-27 | 2008-08-27 | 2008-09-30 | 2008-09-30
| 050.19190 | EFM for West KY Corrections | EFM for West KY Correctional Complex | 4777.54 | 6570 | -1792.46 | -27.28% | 0.02539% | 4777.54 | 6570 | -1792.46 | 2007-10-01 | 2008-09-30 | 2007-05-08 | 2007-05-08 | 2007-09-30 | 2007-09-30
| 050.19503 | 2739.BREIGHTON BUSS CENTER | INSTALL 800' OF 4" PE FOR 5 LOTS AT BREIGHTON BUSSINESS CENTER | 4787.41 | 7921 | -3133.59 | -39.56% | 0.02544% | 4787.41 | 7921 | -3133.59 | 2007-10-01 | 2008-09-30 | 2007-08-29 | 2007-08-29 | 2008-08-28 | 2008-08-28
| 050.20849 | MEA.TCHSVR.TRANSMITTERS | Pressure and Temperature Transmitters to replace damaged units | 4810.81 | 7812 | -830.08 | -10.63% | 0.03711% | 6981.92 | 7812 | -830.08 | 2007-10-01 | 2008-09-30 | 2008-08-05 | 2008-08-05 | 2008-09-30 | 2008-09-30
| 050.19253 | 2739.BRIAR CRK CROS PH I | INSTALL 800' OF 4" PE HWY 44-HWY 127 | 4852.75 | 12265 | -271.24 | -2.211% | 0.06374% | 11993.76 | 12265 | -271.24 | 2007-10-01 | 2008-09-30 | 2007-06-06 | 2007-06-06 | 2008-06-06 | 2008-06-06
| 050.20580 | 2739.AIKEN RD ODORIZOR REBUILD | REBUILD ODORIZOR NEW SCRUBBERS AND PUMPS | 4926.09 | 5660 | -733.91 | -12.97% | 0.02618% | 4926.09 | 5660 | -733.91 | 2007-10-01 | 2008-09-30 | 2008-04-08 | 2008-04-08 | 2008-08-01 | 2008-08-01
| 050.19530 | 050.BGR.SPRINGFIELD BLVD 4" | 1150 FT. OF 4" PE EXT. - SPRINGFIELD BLVD - B.G. | 5015.77 | 7416 | 3257.92 | 43.93% | 0.05673% | 10673.92 | 7416 | 3257.92 | 2007-10-01 | 2008-09-30 | 2007-09-12 | 2007-09-12 | 2008-09-12 | 2008-09-12
| 050.20380 | 050.2636.Timber Ridge Phase 2 | Install , 2058' 2" PE | 5065.38 | 13645.17 | -146.37 | -1.073% | 0.07174% | 13498.8 | 13645.17 | -146.37 | 2007-10-01 | 2008-09-30 | 2008-01-07 | 2008-01-07 | 2008-07-30 | 2008-07-30
| 050.19511 | 2739.MEADOWBROOK PH II | INSTALL 1500' OF 2" PE FOR MEADOWBRROK PH II | 5136.4 | 13569 | -8432.6 | -62.15% | 0.0273% | 5136.4 | 13569 | -8432.6 | 2007-10-01 | 2008-09-30 | 2007-09-04 | 2007-09-04 | 2008-10-01 | 2008-10-01
| 050.20554 | 2739.LOCUST CREEK 5B-2 | INSTALL 800' OF 2" PE IN LOCUST CREEK 5B-2 ON PARK CREEK CIRCLE | 5361.71 | 5569 | -207.29 | -3.722% | 0.0285% | 5361.71 | 5569 | -207.29 | 2007-10-01 | 2008-09-30 | 2008-03-27 | 2008-03-27 | 2009-03-27 | 2009-03-27
| 050.20412 | 050.2636.Hwy 54 & Ward Rd. | Replace 400' 2" PE | 5377.62 | 7934.33 | -2556.71 | -32.22% | 0.02858% | 5377.62 | 7934.33 | -2556.71 | 2007-10-01 | 2008-09-30 | 2008-01-21 | 2008-01-21 | 2008-07-31 | 2008-07-31
| 050.20581 | 050.2636.Brookstone | Install 655' 2" PE | 5431.94 | 5320.87 | 111.07 | 2.087% | 0.02887% | 5431.94 | 5320.87 | 111.07 | 2007-10-01 | 2008-09-30 | 2008-04-10 | 2008-04-10 | 2008-09-28 | 2008-09-28
| 050.20383 | TechSvs.Mea.EFM.Caldwell Hosp. | EFM for Caldwell County Hospital in Princeton | 5628.91 | 4161 | 1467.91 | 35.28% | 0.02992% | 5628.91 | 4161 | 1467.91 | 2007-10-01 | 2008-09-30 | 2008-01-08 | 2008-01-08 | 2008-09-30 | 2008-09-30
| 050.20270 | 050.2609.STO R-O-W Repair | Repair 12" R-O-W Erosion | 5715.78 | 14396 | -8680.22 | -60.3% | 0.03038% | 5715.78 | 14396 | -8680.22 | 2007-10-01 | 2008-09-30 | 2007-11-05 | 2007-11-05 | 2008-09-26 | 2008-09-26
| 050.18342 | Danville 07 Growth | Danville 07 Growth Functional | 5717.15 | Not Budgeted | - | - | 2.152% | 404906.47 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20237 | 050.2638.E Tucker Rd Ext | 655' 2" PE rev ext for Robbie Castleman | 5760.38 | 1208 | 4552.38 | 376.9% | 0.03061% | 5760.38 | 1208 | 4552.38 | 2007-10-01 | 2008-09-30 | 2007-10-22 | 2007-10-22 | 2008-10-20 | 2008-10-20
| 050.20880 | 050.BGR.FENCE AT VALVE PIT | 8" & 6" TIE-IN - FENCE AT PIT | 5805.85 | 5894 | -88.15 | -1.496% | 0.03086% | 5805.85 | 5894 | -88.15 | 2007-10-01 | 2008-09-30 | 2008-08-14 | 2008-08-14 | 2009-08-14 | 2009-08-14
| 050.20280 | 050.KMD PC REPLACEMENTS 2008 | 050.KMD PC REPLACEMENTS 2008 | 5811.96 | 130455.74 | -124643.78 | -95.54% | 0.03089% | 5811.96 | 130455.74 | -124643.78 | 2007-10-01 | 2008-09-30 | 2007-11-07 | 2007-11-07 | 2008-09-30 | 2008-09-30
| 050.19428 | 050.2739.LAW.SOUTH MAIN 3RD | INSTALL 4" STEEL FOR 3RD PARTY DAMAGE BY WATTS BROTHERS IN LAWRENCEBURG SOUTH MAIN | 5831.62 | 24604 | -18772.38 | -76.3% | 0.03099% | 5831.62 | 24604 | -18772.38 | 2007-10-01 | 2008-09-30 | 2007-08-20 | 2007-08-20 | 2007-11-01 | 2007-11-01
| 050.20708 | 050.2637.Barkley Field II | 670' extension for new Paxton Media Group hanger | 5851.7 | 8625 | -1523.07 | -17.66% | 0.03774% | 7101.93 | 8625 | -1523.07 | 2007-10-01 | 2008-09-30 | 2008-06-13 | 2008-06-13 | 2009-06-12 | 2009-06-12
| 050.20933 | 050.BGR.GLS.ELECTRO FUSE EQUIP | 4" ELECTROFUSION EQUIPMENT - GLASGOW | 5973.82 | 6406 | 27.16 | 0.424% | 0.03419% | 6433.16 | 6406 | 27.16 | 2007-10-01 | 2008-09-30 | 2008-09-03 | 2008-09-03 | 2008-08-03 | 2008-08-03
| 050.19031 | 050.PAD.Starlite Subd Rev Ext | Install 1,480' - 2" PE for nine new commercial lots | 5997.01 | 4572 | 1210.39 | 26.47% | 0.03073% | 5782.39 | 4572 | 1210.39 | 2007-10-01 | 2008-09-30 | 2007-03-27 | 2007-03-27 | 2008-03-21 | 2008-03-21
| 050.20892 | 050.BGR.HOP.ELECTROFUSE EQUIP | ELECTROFUSION EQUIPMENT - HOPKINSVILLE | 6155.66 | 5182 | 1244.93 | 24.02% | 0.03416% | 6426.93 | 5182 | 1244.93 | 2007-10-01 | 2008-09-30 | 2008-08-19 | 2008-08-19 | 2009-08-19 | 2009-08-19
| 050.20213 | 050.2636. Aqua Ln. | Install 1,015' 4" PE | 6223.15 | 798 | 5425.15 | 679.8% | 0.03307% | 6223.15 | 798 | 5425.15 | 2007-10-01 | 2008-09-30 | 2007-10-15 | 2007-10-15 | 2007-12-28 | 2007-12-28
| 050.20890 | 050.2609.Retire Dehy Plant | Retire Grandview Dehy Plant | 6316.66 | 5988.4 | -577.24 | -9.639% | 0.02876% | 5411.16 | 5988.4 | -577.24 | 2007-10-01 | 2008-09-30 | 2008-08-18 | 2008-08-18 | 2008-09-28 | 2008-09-28
| 050.20614 | 050.2636.Settles Rd. | Install 161' 2" PE | 6446.56 | 5799.83 | 646.73 | 11.15% | 0.03426% | 6446.56 | 5799.83 | 646.73 | 2007-10-01 | 2008-09-30 | 2008-04-28 | 2008-04-28 | 2008-09-28 | 2008-09-28
| 050.20714 | 050.2634.Slaughters 2" RPLMT | Replace exposed 2" Stl. with 2" PE | 6449.19 | 11334.87 | -3708.65 | -32.72% | 0.04053% | 7626.22 | 11334.87 | -3708.65 | 2007-10-01 | 2008-09-30 | 2008-06-16 | 2008-06-16 | 2008-09-28 | 2008-09-28
| 050.20846 | 050.2637.T.B# 3 Reg Replace | Replace jetstream wth Mooney | 6464.44 | 4047.25 | 5227.97 | 129.2% | 0.0493% | 9275.22 | 4047.25 | 5227.97 | 2007-10-01 | 2008-09-30 | 2008-08-04 | 2008-08-04 | 2009-08-03 | 2009-08-03
| 050.20236 | 2737.HAR.HARRODSBURG SHOPS | INSTALL 1400' OF 2" PE TO SERVE THE SHOPS NEXT TO NEW WALMART | 6525.48 | 12777 | -6251.52 | -48.93% | 0.03468% | 6525.48 | 12777 | -6251.52 | 2007-10-01 | 2008-09-30 | 2007-10-22 | 2007-10-22 | 2008-10-22 | 2008-10-22
| 050.20810 | 050.2637.Paducah Area Sta Imp | Improvements at Trunkline Purchase Station and Schaeffer Rd T.B | 6815.48 | 7424.61 | -609.13 | -8.204% | 0.03622% | 6815.48 | 7424.61 | -609.13 | 2007-10-01 | 2008-09-30 | 2008-07-22 | 2008-07-22 | 2008-09-26 | 2008-09-26
| 050.19386 | 050.2635.T.B 1 Reg Replace | Replace the 4 existing regulators w/ 4 new 2" Fisher EZR's | 6875.06 | 14328.64 | -5935.94 | -41.43% | 0.0446% | 8392.7 | 14328.64 | -5935.94 | 2007-10-01 | 2008-09-30 | 2007-08-02 | 2007-08-02 | 2008-08-01 | 2008-08-01
| 050.20238 | 050.2636.Spring Ridgee Pkwy. | Install 938' 2" PE | 6881.54 | 7134.53 | -252.99 | -3.546% | 0.03657% | 6881.54 | 7134.53 | -252.99 | 2007-10-01 | 2008-09-30 | 2007-10-22 | 2007-10-22 | 2008-01-31 | 2008-01-31
| 050.18357 | Mayfield 07 Non Growth | Mayfield 07 Non Growth Functional | 6983.93 | Not Budgeted | - | - | 2.082% | 391751.89 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20277 | 050.2636.Graystone Phase 3 | Install 720' 2" PE | 6993.77 | 5391.4 | 1602.37 | 29.72% | 0.03717% | 6993.77 | 5391.4 | 1602.37 | 2007-10-01 | 2008-09-30 | 2007-11-06 | 2007-11-06 | 2008-01-31 | 2008-01-31
| 050.18347 | Shelbyville 07 Non Growth | Shelbyville 07 Non Growth Functional | 7074.46 | Not Budgeted | - | - | 1.728% | 325210.71 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20417 | 2739.RAYCON MARKERBALL LOCATOR | LOCATOR TO FIND THE MARKER BALLS - DANVILLE DISTRIC | 7212.99 | 1439 | 5773.99 | 401.3% | 0.03833% | 7212.99 | 1439 | 5773.99 | 2007-10-01 | 2008-09-30 | 2008-01-23 | 2008-01-23 | 2008-01-23 | 2008-01-23
| 050.20440 | 050.BGR.GLS. FURN. FRONT OFF | FURNACE REPLACEMENT - FRONT OFFICE - GLASGOW | 7213.57 | 5111 | 2102.57 | 41.14% | 0.03834% | 7213.57 | 5111 | 2102.57 | 2007-10-01 | 2008-09-30 | 2008-01-31 | 2008-01-31 | 2009-01-31 | 2009-01-31
| 050.20393 | 050.2637.Fence - 14th & Ky Ave | we recently tore down bldg that contained this station, we would like to install a privacy fence around this station, it is in the middle of city adjacent to police department | 7535.62 | 5922.52 | 1613.1 | 27.24% | 0.04005% | 7535.62 | 5922.52 | 1613.1 | 2007-10-01 | 2008-09-30 | 2008-01-10 | 2008-01-10 | 2008-09-26 | 2008-09-26
| 050.20625 | 050.2636.Summer Valley Ln. | Install 956' 2" PE | 7650.09 | 5713.57 | 2592.46 | 45.37% | 0.04414% | 8306.03 | 5713.57 | 2592.46 | 2007-10-01 | 2008-09-30 | 2008-04-30 | 2008-04-30 | 2008-09-28 | 2008-09-28
| 050.20845 | 050.2634.Sebree Reg. Sta. Rt. | Retire Reg Station | 7736.63 | 8442.37 | -705.74 | -8.36% | 0.04112% | 7736.63 | 8442.37 | -705.74 | 2007-10-01 | 2008-09-30 | 2008-08-04 | 2008-08-04 | 2008-09-28 | 2008-09-28
| 050.20443 | 050.2637.Village Sq Dr Ext | Install 655' - 4" PE for new Paducah Bank | 7966.76 | 481.52 | 7485.24 | 1555% | 0.04234% | 7966.76 | 481.52 | 7485.24 | 2007-10-01 | 2008-09-30 | 2008-02-01 | 2008-02-01 | 2009-01-30 | 2009-01-30
| 050.20523 | 050.2637.Grove II Subd | Install 1,920' - 2" PE into Grove Subdivision phase II for 26 new residential lots | 7986.42 | 8326.26 | -339.84 | -4.082% | 0.04245% | 7986.42 | 8326.26 | -339.84 | 2007-10-01 | 2008-09-30 | 2008-03-10 | 2008-03-10 | 2008-09-26 | 2008-09-26
| 050.20772 | 050.BGR.FRK.CHERRY ST.REPLC. | CHERRY ST. 4" BARE STEEL REPLACEMENT - FRANKLIN | 8129.41 | 11631 | -3501.59 | -30.11% | 0.04321% | 8129.41 | 11631 | -3501.59 | 2007-10-01 | 2008-09-30 | 2008-07-09 | 2008-07-09 | 2009-07-09 | 2009-07-09
| 050.20378 | 2739.CLOVERBROOK SEC 4 | INSTALL 900' OF 2" PE | 8134.85 | 8718 | -583.15 | -6.689% | 0.04323% | 8134.85 | 8718 | -583.15 | 2007-10-01 | 2008-09-30 | 2008-01-07 | 2008-01-07 | 2008-12-01 | 2008-12-01
| 050.20239 | 050.2636.Mallard Creek Drive | Install 695' 2" PE | 8146.82 | 5761.05 | 2385.77 | 41.41% | 0.0433% | 8146.82 | 5761.05 | 2385.77 | 2007-10-01 | 2008-09-30 | 2007-10-22 | 2007-10-22 | 2008-01-31 | 2008-01-31
| 050.20382 | 050.BGR.HOP.METER-REG. | METERS & REGULATORS - HOPKINSVILLE | 8423.64 | 44155 | -35678.61 | -80.8% | 0.04505% | 8476.39 | 44155 | -35678.61 | 2007-10-01 | 2008-09-30 | 2008-01-08 | 2008-01-08 | 2009-01-07 | 2009-01-07
| 050.20847 | 050.2637.T.B #2 Improvements | Paint station, new chain link fence around facility | 8594.4 | 9434.21 | -839.81 | -8.902% | 0.04568% | 8594.4 | 9434.21 | -839.81 | 2007-10-01 | 2008-09-30 | 2008-08-04 | 2008-08-04 | 2009-08-03 | 2009-08-03
| 050.20533 | 050.BGR,GLS.LONGHUNTERS sQ. | 3270 FT - 2' PE - LONGHUNTERS SQUARE - GLASGOW | 8633 | 12110 | 14682.31 | 121.2% | 0.1424% | 26792.31 | 12110 | 14682.31 | 2007-10-01 | 2008-09-30 | 2008-03-17 | 2008-03-17 | 2009-03-17 | 2009-03-17
| 050.19267 | 050.2635.Pipe trailer | new pipe trailer for princeton. KY area | 8652.08 | 6489.84 | 2162.24 | 33.32% | 0.04598% | 8652.08 | 6489.84 | 2162.24 | 2007-10-01 | 2008-09-30 | 2007-06-14 | 2007-06-14 | 2008-06-13 | 2008-06-13
| 050.20971 | WKG.PAD.HWY 121 relocate BU050 | Highway 121 relocation | 8653.93 | -6926.93 | 15580.86 | -224.9% | 0.04599% | 8653.93 | -6926.93 | 15580.86 | 2007-10-01 | 2008-09-30 | 2008-09-11 | 2008-09-11 | 2008-09-30 | 2008-09-30
| 050.18343 | Danville 07 Non Growth | Danville 07 Non Growth Functional | 8699.67 | Not Budgeted | - | - | 3.353% | 630897.39 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20332 | 050.2636.Timber Ridge Phase 1 | Install 578' 2" PE | 8830.87 | 1903.86 | 6927.01 | 363.8% | 0.04693% | 8830.87 | 1903.86 | 6927.01 | 2007-10-01 | 2008-09-30 | 2007-12-05 | 2007-12-05 | 2008-07-31 | 2008-07-31
| 050.18346 | Shelbyville 07 Growth | Shelbyville 07 Growth Functional | 8888.51 | Not Budgeted | - | - | 2.515% | 473190.08 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19662 | 2739.SHELBYVILLE.EQUIPMENT | 2 - DITCH WITCH LOCATORS, 1 - FLAME PAK | 8912.1 | 15759 | 1689.72 | 10.72% | 0.09273% | 17448.72 | 15759 | 1689.72 | 2007-10-01 | 2008-09-30 | 2007-09-28 | 2007-09-28 | 2008-12-23 | 2008-12-23
| 050.20624 | 2739.MIDLAND TRAIL-LEAK | REPLACE 2" STEEL ACROSS HWY 60 WITH 2" PE BEHIND COMMWEALTH B&T | 9277.54 | 11820 | -2498.39 | -21.14% | 0.04954% | 9321.61 | 11820 | -2498.39 | 2007-10-01 | 2008-09-30 | 2008-04-30 | 2008-04-30 | 2008-09-28 | 2008-09-28
| 050.20945 | 2737.DP-4 HEATH CONSUL FI.CGI | PURCHASE DP-4 FI.CGI FOR SD SURVEY | 9491.01 | 7198 | 2443.24 | 33.94% | 0.05124% | 9641.24 | 7198 | 2443.24 | 2007-10-01 | 2008-09-30 | 2008-09-05 | 2008-09-05 | 2008-12-12 | 2008-12-12
| 050.19366 | 050.2636.Hill Bridge Rd. | Install 910' 2" PE | 9621.22 | 3412.37 | 1325.83 | 38.85% | 0.02518% | 4738.2 | 3412.37 | 1325.83 | 2007-10-01 | 2008-09-30 | 2007-07-24 | 2007-07-24 | 2007-09-27 | 2007-09-27
| 050.20354 | 050.2634.Welborn Dr. | Install 525' 2" PE,Retire 2" Stl. | 9645.88 | 7249.46 | 2396.42 | 33.06% | 0.05127% | 9645.88 | 7249.46 | 2396.42 | 2007-10-01 | 2008-09-30 | 2007-12-13 | 2007-12-13 | 2008-02-29 | 2008-02-29
| 050.20460 | 2738.TAYLOR CO DETENTION | INSTALL 1000' OF 2" PE TO THE TAYLOR CO DETENTION CENTER ON CENTRAL AVE | 9913.26 | 7063 | 2850.26 | 40.35% | 0.05269% | 9913.26 | 7063 | 2850.26 | 2007-10-01 | 2008-09-30 | 2008-02-13 | 2008-02-13 | 2009-01-12 | 2009-01-12
| 050.20711 | 050.2637.Electronic Recorders | Purchase 6 electronic pressure recorders for use in the Paducah area | 10158.95 | 47911.35 | -37752.4 | -78.8% | 0.05399% | 10158.95 | 47911.35 | -37752.4 | 2007-10-01 | 2008-09-30 | 2008-06-16 | 2008-06-16 | 2009-06-15 | 2009-06-15
| 050.20833 | 050.2634.TB Valve Rplmt | Replace valves on Slaughters TB | 10189.31 | 11560.74 | -1059.83 | -9.167% | 0.05581% | 10500.91 | 11560.74 | -1059.83 | 2007-10-01 | 2008-09-30 | 2008-07-28 | 2008-07-28 | 2008-09-28 | 2008-09-28
| 050.18789 | 050.2739.LAW.EAGLE LAKE LOT 10 | INSTALL REG STATION AND 800' OF 2" PE FOR EAGLE LAKE LOT 10 | 10343.84 | 19000 | -548.12 | -2.885% | 0.09807% | 18451.88 | 19000 | -548.12 | 2007-10-01 | 2008-09-30 | 2006-12-28 | 2006-12-28 | 2007-12-01 | 2007-12-01
| 050.20324 | 2739.MEADOW GLEN SEC II | INSTALL 900' OF 2" PE AND 3 SERVICES | 10476.41 | 7632 | 3022.21 | 39.6% | 0.05662% | 10654.21 | 7632 | 3022.21 | 2007-10-01 | 2008-09-30 | 2007-11-29 | 2007-11-29 | 2008-11-29 | 2008-11-29
| 040.12117 | 040.MAD.RETIRE D/W TRAILER | RETIRE DITCH WITCH TRAILER # 5862 | 10592.92 | -100 | 10692.92 | -10693% | 0.0563% | 10592.92 | -100 | 10692.92 | 2007-10-01 | 2008-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.20844 | 050.2637.Calvert City Reg Imp | Improvements to regulators at two sations in Calvert, one at Calvert City Purchase, one at Westlake Chem Sales sta | 10605.65 | 12451.49 | 4364.45 | 35.05% | 0.08937% | 16815.94 | 12451.49 | 4364.45 | 2007-10-01 | 2008-09-30 | 2008-08-04 | 2008-08-04 | 2009-08-03 | 2009-08-03
| 050.20874 | 050.2634.Replace Phone System | Replace outdated Phone System | 10636 | 11321.12 | -685.12 | -6.052% | 0.05653% | 10636 | 11321.12 | -685.12 | 2007-10-01 | 2008-09-30 | 2008-08-14 | 2008-08-14 | 2008-09-28 | 2008-09-28
| 050.19702 | 050.2635.Mtrs/Regs/Retire | purchase of meters, regs, & retirements for fy '08 | 10885.13 | 52629.51 | -38138.34 | -72.47% | 0.07702% | 14491.17 | 52629.51 | -38138.34 | 2007-10-01 | 2008-09-30 | 2007-10-04 | 2007-10-04 | 2008-10-03 | 2008-10-03
| 050.20860 | 050.BGR.RUSS.PUR 2 REG. REPLC. | rUSSELLVILLE PURCHASE #2 REGULATOR REPLACEMENT | 11207.9 | 14563 | -2503.07 | -17.19% | 0.06409% | 12059.93 | 14563 | -2503.07 | 2007-10-01 | 2008-09-30 | 2008-08-08 | 2008-08-08 | 2009-08-08 | 2009-08-08
| 050.19083 | 050.2737.LANCASTER PUR UPGRADE | REPLACE THE PURCHASE STATION ON HWY 27 FOR LANCASTER AND STANFORD | 11404.8 | 59490 | 23340.1 | 39.23% | 0.4402% | 82830.1 | 59490 | 23340.1 | 2007-10-01 | 2008-09-30 | 2007-04-17 | 2007-04-17 | 2008-04-12 | 2008-04-12
| 050.18790 | 050.2739.EQUIPMENT.DANVILLE | PURCHASE SENSIT GOLD,DETEX,LOCATOR,ELECFUS,AIR HAMMER FOR DANVILLE | 12333.06 | 16500 | 3964.09 | 24.02% | 0.1088% | 20464.09 | 16500 | 3964.09 | 2007-10-01 | 2008-09-30 | 2006-12-28 | 2006-12-28 | 2007-12-01 | 2007-12-01
| 050.20937 | 050.BGR.PIPE JEEP | PIPE JEEP - BOWLING GREEN | 12418.85 | 5912 | 7452.17 | 126.1% | 0.07103% | 13364.17 | 5912 | 7452.17 | 2007-10-01 | 2008-09-30 | 2008-09-03 | 2008-09-03 | 2009-09-03 | 2009-09-03
| 050.20429 | 2751.METER CALIBRATION EQUIP | CRYSTAL CALIBRATION FOR MEASUREMENT TECH | 12454.85 | 9077 | 3377.85 | 37.21% | 0.06619% | 12454.85 | 9077 | 3377.85 | 2007-10-01 | 2008-09-30 | 2008-01-28 | 2008-01-28 | 2009-01-28 | 2009-01-28
| 050.20331 | 050.2636.Segway | Purchase & Repair Segway | 12624.55 | 9447.73 | 3176.82 | 33.63% | 0.0671% | 12624.55 | 9447.73 | 3176.82 | 2007-10-01 | 2008-09-30 | 2007-12-05 | 2007-12-05 | 2008-03-28 | 2008-03-28
| 050.20911 | 050.MO.CARUTHERSRAILROAD303808 | Burlington Northern RR Permit 303808 Lilbourn | 12904.19 | 9375 | 3529.19 | 37.64% | 0.06858% | 12904.19 | 9375 | 3529.19 | 2007-10-01 | 2008-09-30 | 2008-08-27 | 2008-08-27 | 2008-09-30 | 2008-09-30
| 050.19260 | 050.2634.Midtown Commons | Relocate 1,076' 4" Stl with 1,456' 4" Stl due to commercial development | 13117.36 | 0 | 3231.36 | - | 0.01717% | 3231.36 | 0 | 3231.36 | 2007-10-01 | 2008-09-30 | 2007-06-07 | 2007-06-07 | 2007-10-24 | 2007-10-24
| 050.20889 | 2738.LEB.CALVARY RD 4 ST | RELOCATE 4" STEEL ON CALVARY RD FOR INDUSTRIAL DR ROAD EXTENSION | 13689.67 | -13134.5 | 19749.15 | -150.4% | 0.03515% | 6614.65 | -13134.5 | 19749.15 | 2007-10-01 | 2008-09-30 | 2008-08-18 | 2008-08-18 | 2009-08-18 | 2009-08-18
| 050.20713 | 050.2637.Palma Bulding | The puchase of a building to cover the ROC and electronics | 13713.35 | 18703.2 | -4485.74 | -23.98% | 0.07556% | 14217.46 | 18703.2 | -4485.74 | 2007-10-01 | 2008-09-30 | 2008-06-16 | 2008-06-16 | 2009-06-15 | 2009-06-15
| 050.20884 | 050.2634.S.Main&Broadway Rplmt | Install 803' 2" Pe IP Retire 6",4",3",2", Bare pipe | 13975.31 | 21805.2 | -5739.06 | -26.32% | 0.08539% | 16066.14 | 21805.2 | -5739.06 | 2007-10-01 | 2008-09-30 | 2008-08-15 | 2008-08-15 | 2008-09-28 | 2008-09-28
| 050.20773 | 2739.TBS.HOSPITAL STATION | REBUILD THE HOSPITAL TBS STATION | 14102.84 | 48407 | 3959.51 | 8.18% | 0.2783% | 52366.51 | 48407 | 3959.51 | 2007-10-01 | 2008-09-30 | 2008-07-09 | 2008-07-09 | 2008-12-12 | 2008-12-12
| 050.20841 | 050.2637.Heath Detector | Leak detector model DP-IR | 14392.61 | 14806.7 | -414.09 | -2.797% | 0.07649% | 14392.61 | 14806.7 | -414.09 | 2007-10-01 | 2008-09-30 | 2008-07-31 | 2008-07-31 | 2009-07-01 | 2009-07-01
| 050.20770 | 2737.HAR.SKYLARS LANDING PH I | INSTALL 1800' OF 2" PE FOR SKYLARS LANDINING | 14886.82 | 10475 | 4793.92 | 45.77% | 0.08115% | 15268.92 | 10475 | 4793.92 | 2007-10-01 | 2008-09-30 | 2008-07-09 | 2008-07-09 | 2009-07-09 | 2009-07-09
| 050.20859 | 050.2634.S. Franklin St.Rplmt. | Install 1,256' 2" PE to replace Bare LP Pipe | 14920 | 29876.08 | -12290.48 | -41.14% | 0.09346% | 17585.6 | 29876.08 | -12290.48 | 2007-10-01 | 2008-09-30 | 2008-08-07 | 2008-08-07 | 2008-09-28 | 2008-09-28
| 050.20418 | 050.2635.Electronic Recorder | (5) electronic pressure recorders for use in the Princeton area | 16320.64 | 8011.38 | 8309.26 | 103.7% | 0.08674% | 16320.64 | 8011.38 | 8309.26 | 2007-10-01 | 2008-09-30 | 2008-01-23 | 2008-01-23 | 2008-09-26 | 2008-09-26
| 050.20247 | 050.HOPK.2ND & KY REG. STA | REPLACE LP REG. STA. - 2ND & KY - HOPKINSVILLE | 16334.68 | 10382 | 5952.68 | 57.34% | 0.08681% | 16334.68 | 10382 | 5952.68 | 2007-10-01 | 2008-09-30 | 2007-10-26 | 2007-10-26 | 2008-10-26 | 2008-10-26
| 050.20665 | 2737.STANFORD RD 4" ST RELOC | RELOCATE 15' OF 4" STEEL ON STANFORD RD NEXT TO KSD APARTMENTS | 17097.19 | 9977 | 7120.19 | 71.37% | 0.09087% | 17097.19 | 9977 | 7120.19 | 2007-10-01 | 2008-09-30 | 2008-05-16 | 2008-05-16 | 2008-10-01 | 2008-10-01
| 050.20334 | 050.BGR.THAMES VALLEY - RELOC | THAMES VALLEY / VETERANS MEMORIAL 2" HPD, 2" IP & REG STA. RELOC. | 17638.61 | 0 | 17638.61 | - | 0.09374% | 17638.61 | 0 | 17638.61 | 2007-10-01 | 2008-09-30 | 2007-12-06 | 2007-12-06 | 2008-12-06 | 2008-12-06
| 050.20809 | 050.2637.Perkins Creek Imp | 70'-75' of 8" T'line exposed in creek, this project is for improvements we rerouted creek channel and covered 8" line with dirt and rip rap | 17771.71 | 19309.46 | -1537.75 | -7.964% | 0.09445% | 17771.71 | 19309.46 | -1537.75 | 2007-10-01 | 2008-09-30 | 2008-07-22 | 2008-07-22 | 2008-09-26 | 2008-09-26
| 050.20356 | 050.KMD PHONE REPLACE 2008 | KMD PHONE REPLACEMENTS 2008 | 17790.74 | 39372.98 | -21582.24 | -54.81% | 0.09455% | 17790.74 | 39372.98 | -21582.24 | 2007-10-01 | 2008-09-30 | 2007-12-14 | 2007-12-14 | 2008-09-30 | 2008-09-30
| 050.20431 | TchSrv.Mea.Pres. Monitor | Pressure Monitororing Equipment for IL & MO | 17796.53 | 7810 | 9986.53 | 127.9% | 0.09458% | 17796.53 | 7810 | 9986.53 | 2007-10-01 | 2008-09-30 | 2008-01-28 | 2008-01-28 | 2008-09-30 | 2008-09-30
| 050.20592 | Measurement Transmitters | Misc. Pres. & Temp. Transmitters | 18208.42 | 7812 | 10614.65 | 135.9% | 0.09793% | 18426.65 | 7812 | 10614.65 | 2007-10-01 | 2008-09-30 | 2008-04-18 | 2008-04-18 | 2008-09-30 | 2008-09-30
| 050.20426 | 050.2636.Keenland Phase 1 | Install 2,802' 2" PE | 18559.31 | 16564.8 | 2814.47 | 16.99% | 0.103% | 19379.27 | 16564.8 | 2814.47 | 2007-10-01 | 2008-09-30 | 2008-01-25 | 2008-01-25 | 2008-07-31 | 2008-07-31
| 050.20861 | 050.2609.St.CharlesShedRestore | Restore equipment shed at St Charles | 18834.99 | 20154.4 | -1319.41 | -6.547% | 0.1001% | 18834.99 | 20154.4 | -1319.41 | 2007-10-01 | 2008-09-30 | 2008-08-08 | 2008-08-08 | 2008-09-28 | 2008-09-28
| 050.20695 | 050.BGR.HOP.MAIN ST.REPLC. | MAIN ST. BARE STEEL REPLC. - HOPKINSVILLE | 19050.54 | 229480.7 | -4186.3 | -1.824% | 1.197% | 225294.4 | 229480.7 | -4186.3 | 2007-10-01 | 2008-09-30 | 2008-06-09 | 2008-06-09 | 2008-06-09 | 2008-06-09
| 050.20395 | 050.2636.Harbor Hills Trace 2 | Install 2,596' 2" PE | 19112.99 | 11747.47 | 9050.87 | 77.05% | 0.1105% | 20798.34 | 11747.47 | 9050.87 | 2007-10-01 | 2008-09-30 | 2008-01-11 | 2008-01-11 | 2008-07-31 | 2008-07-31
| 050.20243 | 050.2637.Westwood Rev Ext | Install 3,160' - 2" PE into Westwood Hills Subdivision for 65 new residential lots | 19139.76 | 16447.63 | 3110.64 | 18.91% | 0.1039% | 19558.27 | 16447.63 | 3110.64 | 2007-10-01 | 2008-09-30 | 2007-10-24 | 2007-10-24 | 2008-10-24 | 2008-10-24
| 050.20555 | 050.2634.Misc. Equip.Storage | Purchase Misc. Equipment for Storage | 20045.58 | 20154.4 | -108.82 | -0.5399% | 0.1065% | 20045.58 | 20154.4 | -108.82 | 2007-10-01 | 2008-09-30 | 2008-03-28 | 2008-03-28 | 2008-09-28 | 2008-09-28
| 050.19650 | 050.BGR. EQUIP. - B.G. | EQUIPMENT - BOWLING GREEN AREA | 20120.6 | 48831 | 2642.78 | 5.412% | 0.2736% | 51473.78 | 48831 | 2642.78 | 2007-10-01 | 2008-09-30 | 2007-09-27 | 2007-09-27 | 2008-09-09 | 2008-09-09
| 050.19381 | 050.2739.COLLEGE ST CI REPLACE | REPLACE 650' OF 8" CAST IRON ON COLLEGE STREET | 20547.24 | 49360 | 15067.32 | 30.53% | 0.3424% | 64427.32 | 49360 | 15067.32 | 2007-10-01 | 2008-09-30 | 2007-08-01 | 2007-08-01 | 2008-08-08 | 2008-08-08
| 050.20862 | 050.2609.St.CharlesOfficeRest | Restore St. Charles Office & Compressor Building | 20633.84 | 20154.4 | 479.44 | 2.379% | 0.1097% | 20633.84 | 20154.4 | 479.44 | 2007-10-01 | 2008-09-30 | 2008-08-08 | 2008-08-08 | 2008-09-28 | 2008-09-28
| 050.20485 | 050.2609.St. Charles Muffler | Install new Muffler St. Charles Compressor | 20803.7 | 22022.75 | -1124 | -5.104% | 0.1111% | 20898.75 | 22022.75 | -1124 | 2007-10-01 | 2008-09-30 | 2008-02-21 | 2008-02-21 | 2008-09-28 | 2008-09-28
| 050.19379 | 050.2637.Reidland Rd Relocate | Reidland Rd state highway project relocation | 21073.46 | 94279.84 | 5244.46 | 5.563% | 0.5289% | 99524.3 | 94279.84 | 5244.46 | 2007-10-01 | 2008-09-30 | 2007-07-31 | 2007-07-31 | 2008-07-28 | 2008-07-28
| 050.19646 | Mooney Regulators | Mooney Regulators for MO, IA, & ILL | 21256.46 | 41822.13 | -20565.67 | -49.17% | 0.113% | 21256.46 | 41822.13 | -20565.67 | 2007-10-01 | 2008-09-30 | 2007-09-27 | 2007-09-27 | 2007-11-15 | 2007-11-15
| 050.20691 | 2737.4TH STREET STATION | INSTALL NEW VALVES AND REGULATORS AT THE 4TH STREET STATION | 21256.56 | 15124 | 8598.89 | 56.86% | 0.1261% | 23722.89 | 15124 | 8598.89 | 2007-10-01 | 2008-09-30 | 2008-06-03 | 2008-06-03 | 2009-09-29 | 2009-09-29
| 050.20999 | 050.2634.Meadowlark | Reimbursement for 2005 Job | 22395.05 | 22395.05 | 0 | 0% | 0.119% | 22395.05 | 22395.05 | 0 | 2007-10-01 | 2008-09-30 | 2008-09-25 | 2008-09-25 | 2008-09-28 | 2008-09-28
| 050.20664 | 050.2636.S.Griffith Rplmt. | Replace 4" LP Stl. with 1600' 2" IP PE | 22822.04 | 35752.89 | -7445.83 | -20.83% | 0.1504% | 28307.06 | 35752.89 | -7445.83 | 2007-10-01 | 2008-09-30 | 2008-05-15 | 2008-05-15 | 2008-09-28 | 2008-09-28
| 050.18841 | 050.BGR.31W IP RELOC. - B.G. | HWY 31W IP RELOC - CO. LAB & MAT. - B.G. | 22882.8 | 159443 | 359073.78 | 225.2% | 2.756% | 518516.78 | 159443 | 359073.78 | 2007-10-01 | 2008-09-30 | 2007-01-09 | 2007-01-09 | 2008-01-09 | 2008-01-09
| 050.18352 | Owensboro 07 Growth | Owensboro 07 Growth Functional | 23234.05 | Not Budgeted | - | - | 3.511% | 660546.86 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20563 | 050.2609.Bon Harbor Fence | Install new security fence Bon Harbor | 23260.89 | 24473.2 | -747.74 | -3.055% | 0.1261% | 23725.46 | 24473.2 | -747.74 | 2007-10-01 | 2008-09-30 | 2008-04-01 | 2008-04-01 | 2008-09-28 | 2008-09-28
| 050.19498 | 2739.LOCUST CREEK SEC 7 | INSTALL 1500' OF 2" PE FOR LOCUST CREEK SEC 7 2008 HOMARAMA | 23310.13 | 15173 | 8137.13 | 53.63% | 0.1239% | 23310.13 | 15173 | 8137.13 | 2007-10-01 | 2008-09-30 | 2007-08-28 | 2007-08-28 | 2008-01-01 | 2008-01-01
| 050.19294 | 2739.LAW.SCHOOL RELOCAT 6 ST | RELOCATE 800' OF 6" STEEL FOR ELEMENTARY SCHOOL.LAWRENCEBURG | 23464.91 | 48300 | -43068.04 | -89.17% | 0.02781% | 5231.96 | 48300 | -43068.04 | 2007-10-01 | 2008-09-30 | 2007-06-27 | 2007-06-27 | 2008-06-06 | 2008-06-06
| 050.20575 | 050.2609.Grandview Fence | Install security fence at Grandview | 24333.43 | 24617.16 | 157.8 | 0.641% | 0.1317% | 24774.96 | 24617.16 | 157.8 | 2007-10-01 | 2008-09-30 | 2008-04-03 | 2008-04-03 | 2008-09-28 | 2008-09-28
| 050.19661 | 050.3351.John Deere Gator | John Deere Gator for use in Paducah area | 25067.89 | 18017.03 | 7050.86 | 39.13% | 0.1332% | 25067.89 | 18017.03 | 7050.86 | 2007-10-01 | 2008-09-30 | 2007-09-28 | 2007-09-28 | 2008-09-26 | 2008-09-26
| 050.20250 | 2737.DANVILLE FURNITURE | PURCHASE NEW OFFICE FURNITURE | 25427.17 | 11516 | 15286.75 | 132.7% | 0.1424% | 26802.75 | 11516 | 15286.75 | 2007-10-01 | 2008-09-30 | 2007-10-29 | 2007-10-29 | 2008-02-02 | 2008-02-02
| 050.19701 | 050.2638.Mtrs/Regs/Retire | purchase of meters, regs, & retirements for fy '08 | 25817.39 | 74254.59 | -44320.07 | -59.69% | 0.1591% | 29934.52 | 74254.59 | -44320.07 | 2007-10-01 | 2008-09-30 | 2007-10-04 | 2007-10-04 | 2008-10-03 | 2008-10-03
| 050.18336 | Bowling Green 07 Growth | Bowling Green 07 Growth Functional | 26358.54 | Not Budgeted | - | - | 6.843% | 1287551.04 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18353 | Owensboro 07 Non Growth | Owensboro 07 Non Growth Functional | 27437.06 | Not Budgeted | - | - | 11.71% | 2203689.69 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20764 | 050.2636.Hwy 60 By Pass 1 | Hwy Relocation install 2,516' 4" PE, 246' 8" Stl., 187' 2" PE | 28046.92 | 57691.78 | 39582.27 | 68.61% | 0.517% | 97274.05 | 57691.78 | 39582.27 | 2007-10-01 | 2008-09-30 | 2008-07-07 | 2008-07-07 | 2008-09-28 | 2008-09-28
| 050.20767 | 050.2636.Mosleyville Odor Tank | Replace Mosleyville Odorant Tank | 28757.36 | 14156.64 | -3650.8 | -25.79% | 0.05584% | 10505.84 | 14156.64 | -3650.8 | 2007-10-01 | 2008-09-30 | 2008-07-08 | 2008-07-08 | 2008-09-28 | 2008-09-28
| 050.20473 | 050.2634.Parkrow | Replace 366' 4" Bare Stl. | 29809.62 | 24975.57 | 4834.05 | 19.36% | 0.1584% | 29809.62 | 24975.57 | 4834.05 | 2007-10-01 | 2008-09-30 | 2008-02-15 | 2008-02-15 | 2008-09-26 | 2008-09-26
| 050.20387 | 050.BGR.VIKING ENERGY | 6" PE & REG STA - VIKING ENERGY - B.G. | 30181.41 | 0 | 273.95 | - | 0.001456% | 273.95 | 0 | 273.95 | 2007-10-01 | 2008-09-30 | 2008-01-09 | 2008-01-09 | 2009-01-08 | 2009-01-08
| 050.19033 | 050.MAY.Fountainhead Subd | Rev Ext - 5,480' - 2" PE | 31570.45 | 21756.45 | 13176.64 | 60.56% | 0.1857% | 34933.09 | 21756.45 | 13176.64 | 2007-10-01 | 2008-09-30 | 2007-03-27 | 2007-03-27 | 2008-03-21 | 2008-03-21
| 050.20756 | 050.2634.S.Kentucky Ave.Rplmt. | Replace approximately 2,060' Bare LP pipe | 32233.92 | 55393.22 | -21464.4 | -38.75% | 0.1803% | 33928.82 | 55393.22 | -21464.4 | 2007-10-01 | 2008-09-30 | 2008-07-01 | 2008-07-01 | 2008-09-28 | 2008-09-28
| 050.20692 | 2738.C-VILLE WAREHOUSE TBS | INSTALL NEW REGULATORS AND VALVES AT THE TBS AT THE WAREHOUSE | 34471.3 | 25000 | 9471.3 | 37.89% | 0.1832% | 34471.3 | 25000 | 9471.3 | 2007-10-01 | 2008-09-30 | 2008-06-03 | 2008-06-03 | 2009-09-29 | 2009-09-29
| 050.20496 | 050.2634.Waterfall Court | Install 515' 2" PE, 100' 2" Stl, 1-Farm Tap Sta. | 35061.12 | 16272.33 | 18788.79 | 115.5% | 0.1863% | 35061.12 | 16272.33 | 18788.79 | 2007-10-01 | 2008-09-30 | 2008-02-27 | 2008-02-27 | 2008-09-28 | 2008-09-28
| 050.20693 | 2738.C-VILLE OFFICE IMPROVE | INTERIOR REMODELING OF THE CAMPBELLSVILLE OFFICE | 36482.38 | 31420 | 11637.39 | 37.04% | 0.2288% | 43057.39 | 31420 | 11637.39 | 2007-10-01 | 2008-09-30 | 2008-06-03 | 2008-06-03 | 2009-09-29 | 2009-09-29
| 050.19612 | 2738.LEB.WALMART | INSTALL 800' OF 4" PE AND 2000' 2" PE | 36989.46 | 46257 | -9267.54 | -20.03% | 0.1966% | 36989.46 | 46257 | -9267.54 | 2007-10-01 | 2008-09-30 | 2007-09-21 | 2007-09-21 | 2008-06-06 | 2008-06-06
| 050.19383 | 050.2739.CAST IRON PH II-SERV | REPLACE SERVICES ON MAIN AND 8TH STREETS WITH CAST IRON MAIN REPLACEMENT | 37189.19 | 63687 | 39540.41 | 62.09% | 0.5486% | 103227.41 | 63687 | 39540.41 | 2007-10-01 | 2008-09-30 | 2007-08-01 | 2007-08-01 | 2008-08-08 | 2008-08-08
| 050.19602 | Princeton 08 Growth | Princeton 08 Growth | 39179.63 | Not Budgeted | - | - | 0.2181% | 41037.72 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20515 | 050.2636.Electronic Recorders | Install 21 Electronic Recorders | 43821.32 | 36009.67 | 8706.83 | 24.18% | 0.2377% | 44716.5 | 36009.67 | 8706.83 | 2007-10-01 | 2008-09-30 | 2008-03-06 | 2008-03-06 | 2008-09-28 | 2008-09-28
| 050.20888 | 2738.LEB.INDST RD RELOCATION | RELOCATE 4" PE AND 2" PE ON INDUSTRIAL DR LEBANON | 45591.13 | -8938.61 | 31942.97 | -357.4% | 0.1223% | 23004.36 | -8938.61 | 31942.97 | 2007-10-01 | 2008-09-30 | 2008-08-18 | 2008-08-18 | 2009-08-18 | 2009-08-18
| 050.20349 | 050.2618.SAFETY08 | Purchase various safety equipment budgeted for fiscal 2008 | 48694.03 | 45044.83 | 3649.2 | 8.101% | 0.2588% | 48694.03 | 45044.83 | 3649.2 | 2007-10-01 | 2008-09-30 | 2007-12-12 | 2007-12-12 | 2008-09-25 | 2008-09-25
| 050.20873 | 050.2638.North St Bare Replace | Replace app 2,750' of bare main in downtown Mayfield | 49650.14 | 81350.92 | -16328.71 | -20.07% | 0.3456% | 65022.21 | 81350.92 | -16328.71 | 2007-10-01 | 2008-09-30 | 2008-08-13 | 2008-08-13 | 2009-08-13 | 2009-08-13
| 050.20922 | 050.2609.Bon Harbor Well #1 | Workover Well # 1 Bon Harbor | 51657.33 | 58152.69 | -617.95 | -1.063% | 0.3058% | 57534.74 | 58152.69 | -617.95 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20924 | 050.2609.Bon Harbor Well #8 | Workover Bon Harbor Well #8 | 51657.33 | 183551.6 | 6725.89 | 3.664% | 1.011% | 190277.49 | 183551.6 | 6725.89 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20925 | 050.2609.Bon Harbor Well #6 | Workover Bon Harbor Well #6 | 51657.33 | 58152.69 | -617.95 | -1.063% | 0.3058% | 57534.74 | 58152.69 | -617.95 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20926 | 050.2609.Bon Harbor Well #2 | Workover Bon Harbor Well #2 | 55888.38 | 58152.69 | 4124 | 7.092% | 0.331% | 62276.69 | 58152.69 | 4124 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20927 | 050.2609.Bon Harbor Well #4 | Workover Bonharbor Well #4 | 55888.38 | 58152.69 | 4124 | 7.092% | 0.331% | 62276.69 | 58152.69 | 4124 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.19382 | 050.2739.CAST IRON PH II.MAIN | REPLACE 1700' OF CAST IRON ON MAIN AND 8TH STREET | 56540.25 | 98674 | 54606.61 | 55.34% | 0.8146% | 153280.61 | 98674 | 54606.61 | 2007-10-01 | 2008-09-30 | 2007-08-01 | 2007-08-01 | 2008-08-08 | 2008-08-08
| 050.20484 | 050.2609.Bon Harbor Well # 9 | Workover Well # 9 Bon Harbor | 57519.76 | 183203.93 | 3009.08 | 1.642% | 0.9897% | 186213.01 | 183203.93 | 3009.08 | 2007-10-01 | 2008-09-30 | 2008-02-21 | 2008-02-21 | 2009-08-01 | 2009-08-01
| 050.20923 | 050.2609.Bon Harbor Well #7 | Workover Bon Harbor Well #7 | 57705.57 | 183551.6 | 6830.89 | 3.722% | 1.012% | 190382.49 | 183551.6 | 6830.89 | 2007-10-01 | 2008-09-30 | 2008-09-02 | 2008-09-02 | 2009-08-01 | 2009-08-01
| 050.20483 | 050.2609.Bon Harbor Well # 5 | Workover Bon Harbor Well # 5 | 59428.22 | 183203.93 | 28665.1 | 15.65% | 1.126% | 211869.03 | 183203.93 | 28665.1 | 2007-10-01 | 2008-09-30 | 2008-02-20 | 2008-02-20 | 2009-08-01 | 2009-08-01
| 050.20386 | 050.2637.Monroe St Replace | Replace one block (2300) of gas main on Monroe St | 60149.68 | 45102.25 | 15047.43 | 33.36% | 0.3197% | 60149.68 | 45102.25 | 15047.43 | 2007-10-01 | 2008-09-30 | 2008-01-09 | 2008-01-09 | 2008-09-26 | 2008-09-26
| 050.18337 | Bowling Green 07 Non Growth | Bowling Green 07 Non Growth Functional | 60442.06 | Not Budgeted | - | - | 10.69% | 2012029.34 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.20967 | 050.2638.M'field Reinforcement | Purchase 12,000 feet of 4" High Density PE pipe to run from Pryorsburg system to the Mayfield system | 62920.47 | 68645.61 | -5725.14 | -8.34% | 0.3344% | 62920.47 | 68645.61 | -5725.14 | 2007-10-01 | 2008-09-30 | 2008-09-09 | 2008-09-09 | 2009-09-01 | 2009-09-01
| 050.20488 | 050.BGR.GLS.DART 9 METER SET | DART #9 TURBINE METER, SET & REGULATORS | 63671.03 | 46551.02 | 16642.27 | 35.75% | 0.3359% | 63193.29 | 46551.02 | 16642.27 | 2007-10-01 | 2008-09-30 | 2008-02-22 | 2008-02-22 | 2009-02-22 | 2009-02-22
| 050.20824 | 050.BGR.OLIVERR ST. REPLC. | 2700' OF 2" PE - OLIVER ST. 4" BARE REPLC.. - B.G | 63752.92 | 198079 | -6596.06 | -3.33% | 1.018% | 191482.94 | 198079 | -6596.06 | 2007-10-01 | 2008-09-30 | 2008-07-25 | 2008-07-25 | 2009-07-25 | 2009-07-25
| 050.19706 | 050.2636.Owensboro meters | Purchase Meters & Regs. for Owensboro | 66317.05 | 91677.11 | -20305.25 | -22.15% | 0.3793% | 71371.86 | 91677.11 | -20305.25 | 2007-10-01 | 2008-09-30 | 2007-10-08 | 2007-10-08 | 2008-09-26 | 2008-09-26
| 050.20405 | 050.BGR.VAPOR EXTRACT UNIT | VAPRO EXTRACTION UNIT - BOWLING GREEN | 66837.69 | 46196 | 20641.69 | 44.68% | 0.3552% | 66837.69 | 46196 | 20641.69 | 2007-10-01 | 2008-09-30 | 2008-01-17 | 2008-01-17 | 2009-01-17 | 2009-01-17
| 050.20659 | 050.2635.Marion TB Relocate | Project to relocate our Marion, KY town border station upstream nearly a mile | 68360.61 | 79761.14 | 4178.75 | 5.239% | 0.4461% | 83939.89 | 79761.14 | 4178.75 | 2007-10-01 | 2008-09-30 | 2008-05-13 | 2008-05-13 | 2009-05-01 | 2009-05-01
| 050.20249 | 2737.DANVILLE OFFICE REMODEL | REMODEL DANVILLE OFFICE - SERVICE AND CONSTRUCTION | 69587.63 | 47506 | 23444.25 | 49.35% | 0.3771% | 70950.25 | 47506 | 23444.25 | 2007-10-01 | 2008-09-30 | 2007-10-29 | 2007-10-29 | 2008-02-02 | 2008-02-02
| 050.20608 | 2738.MAGNOLIA ST - CI REPLACE | REPLACE 4" CAST IRON AND LP SERVICES | 71157.27 | 62030 | 9127.27 | 14.71% | 0.3782% | 71157.27 | 62030 | 9127.27 | 2007-10-01 | 2008-09-30 | 2008-04-23 | 2008-04-23 | 2009-09-01 | 2009-09-01
| 050.19596 | Campbellsville 08 Growth | Campbellsville 08 Growth | 74210.38 | Not Budgeted | - | - | 0.4261% | 80165.08 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19708 | 050.2634.METER & REG PURCHASE | Purchase & retire meters &regulators | 74524.91 | 68688.95 | 9841.93 | 14.33% | 0.4174% | 78530.88 | 68688.95 | 9841.93 | 2007-10-01 | 2008-09-30 | 2007-10-08 | 2007-10-08 | 2008-09-26 | 2008-09-26
| 050.19700 | 050.2637.Mtrs/Regs/Retire | purchase meters, regs, & retirements | 77343.18 | 178972.79 | -97061.22 | -54.23% | 0.4353% | 81911.57 | 178972.79 | -97061.22 | 2007-10-01 | 2008-09-30 | 2007-10-04 | 2007-10-04 | 2008-10-03 | 2008-10-03
| 050.20216 | 050.2634.Stage Coach Rd. | Install 3,313' 4" PE | 89895.65 | 87706.77 | 2188.88 | 2.496% | 0.4778% | 89895.65 | 87706.77 | 2188.88 | 2007-10-01 | 2008-09-30 | 2007-10-16 | 2007-10-16 | 2007-12-31 | 2007-12-31
| 050.19074 | 050.2738.CVILLE INDUST PARK | INSTALL 6800' OF 4" PE FOR THE INDUSTRIAL APRK ON HWY 55 SOUTH | 90136.29 | 11332 | 154520.36 | 1364% | 0.8815% | 165852.36 | 11332 | 154520.36 | 2007-10-01 | 2008-09-30 | 2007-04-11 | 2007-04-11 | 2008-04-11 | 2008-04-11
| 050.19608 | Mayfield 08 Growth | Mayfield 08 Growth | 93535.54 | Not Budgeted | - | - | 0.5352% | 100711.08 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19208 | 050.BGR.LOVERS LN. PHASE I | 3000 FT - 6' PE, 150 FT. - 6' STL. & 100' - 2"PE - LOVERS LN. PHASE I | 96149.33 | 227641 | 123112.58 | 54.08% | 1.864% | 350753.58 | 227641 | 123112.58 | 2007-10-01 | 2008-09-30 | 2007-05-17 | 2007-05-17 | 2008-05-17 | 2008-05-17
| 050.20686 | 050.BGR.INDIANOLA REPLC. | 1340 FT. 2" BARE ST. REPLC - INDIANOLA - B.G. | 100228.4 | 143335 | -20932.13 | -14.6% | 0.6505% | 122402.87 | 143335 | -20932.13 | 2007-10-01 | 2008-09-30 | 2008-05-29 | 2008-05-29 | 2009-05-29 | 2009-05-29
| 050.20660 | 050.2635.Marion Bare Replace | Replace app. 1,800' - 4" bare with 4" PE in Marion, KY | 101806.27 | 42749.99 | 77008.5 | 180.1% | 0.6365% | 119758.49 | 42749.99 | 77008.5 | 2007-10-01 | 2008-09-30 | 2008-05-13 | 2008-05-13 | 2009-05-01 | 2009-05-01
| 050.19600 | Madisonville 08 Growth | Madisonville 08 Growth | 102228.77 | Not Budgeted | - | - | 0.565% | 106310.38 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.18672 | 050.KYMS.PC REPLACEMENTS 2007 | FY2007 PC REPLACEMENTS FOR KY & MID-STATES | 102468.22 | 79236 | 118259.71 | 149.2% | 1.05% | 197495.71 | 79236 | 118259.71 | 2007-10-01 | 2008-09-30 | 2006-11-10 | 2006-11-10 | 2006-12-06 | 2006-12-06
| 050.20466 | 050.2609.Bon Harbor Compressor | Overhaul Bon Harbor Compressor | 107473.64 | 116904.9 | -9431.26 | -8.067% | 0.5712% | 107473.64 | 116904.9 | -9431.26 | 2007-10-01 | 2008-09-30 | 2008-02-14 | 2008-02-14 | 2008-09-26 | 2008-09-26
| 050.20278 | 050.BGR.CEMETERY RD. SYS. IMP. | 1800 FT. OF 4" PE - CEMETERY RD. SYSTEM IMPROVEMENT | 114028.42 | 113732.7 | 295.72 | 0.26% | 0.606% | 114028.42 | 113732.7 | 295.72 | 2007-10-01 | 2008-09-30 | 2007-11-07 | 2007-11-07 | 2008-11-07 | 2008-11-07
| 050.19592 | Hopkinsville 08 Growth | Hopkinsville 08 Growth | 116228.69 | Not Budgeted | - | - | 0.6637% | 124882.53 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.18673 | 050.KYMS.MDT HARDWARE 2007 | FY 2007 MDT HARDWARE | 117850.69 | 571106 | 100190.3 | 17.54% | 3.568% | 671296.3 | 571106 | 100190.3 | 2007-10-01 | 2008-09-30 | 2006-11-10 | 2006-11-10 | 2006-12-06 | 2006-12-06
| 050.20233 | Meters - Outsourced | Blanket Project for Outsourced Meters | 118157.78 | 247776 | -135915.58 | -54.85% | 0.5945% | 111860.42 | 247776 | -135915.58 | 2007-10-01 | 2008-09-30 | 2007-10-22 | 2007-10-22 | 2008-10-01 | 2008-10-01
| 050.19590 | Glasgow 08 Growth | Glasgow 08 Growth | 163206.73 | Not Budgeted | - | - | 0.9081% | 170870.75 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19599 | Shelbyville 08 Non Growth | Shelbyville 08 Non Growth | 197978.97 | Not Budgeted | - | - | 1.13% | 212548.08 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19603 | Princeton 08 Non Growth | Princeton 08 Non Growth | 215061.23 | Not Budgeted | - | - | 1.275% | 239900.94 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19594 | Danville 08 Growth | Danville 08 Growth | 251634.57 | Not Budgeted | - | - | 1.433% | 269675.7 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20493 | 050.BGR.GLS.HAPPY VALLEY REPLC | 6" BARE STEEL REPLC. - HAPPY VALLEY RD. - GLASGOW | 255336.84 | 218320.48 | 37016.36 | 16.96% | 1.357% | 255336.84 | 218320.48 | 37016.36 | 2007-10-01 | 2008-09-30 | 2008-02-26 | 2008-02-26 | 2009-02-26 | 2009-02-26
| 050.20447 | 050.HOPK.HWY 41 RELOC. | HWY 41 8" & 6" RELOC. - HOPKINSVILLE | 277711.48 | 11486 | 283837.65 | 2471% | 1.57% | 295323.65 | 11486 | 283837.65 | 2007-10-01 | 2008-09-30 | 2008-02-06 | 2008-02-06 | 2009-02-06 | 2009-02-06
| 050.20364 | 050.BGR.CHESTNUT ST REPLC | 1000,1100 & 1200 BLKS. - CHESTNUT ST REPLC. - B.G. | 290851.87 | 242742 | 48099.08 | 19.81% | 1.546% | 290841.08 | 242742 | 48099.08 | 2007-10-01 | 2008-09-30 | 2007-12-21 | 2007-12-21 | 2008-12-21 | 2008-12-21
| 050.19209 | 050.BGR.LOVERS LN. PHASE II | 2200 FT. - 6" PE , 200' - 6" STL. 7 200' - 2 PE - LOVERS LN. PHASE II | 297681.58 | 246240.25 | 51441.33 | 20.89% | 1.582% | 297681.58 | 246240.25 | 51441.33 | 2007-10-01 | 2008-09-30 | 2007-05-17 | 2007-05-17 | 2008-05-17 | 2008-05-17
| 050.19598 | Shelbyville 08 Growth | Shelbyville 08 Growth | 346425.5 | Not Budgeted | - | - | 1.946% | 366204.15 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19597 | Campbellsville 08 Non Growth | Campbellsville 08 Non Growth | 346829.64 | Not Budgeted | - | - | 1.955% | 367789.81 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19593 | Hopkinsville 08 Non Growth | Hopkinsville 08 Non Growth | 361865.11 | Not Budgeted | - | - | 2.034% | 382720.05 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19609 | Mayfield 08 Non Growth | Mayfield 08 Non Growth | 374711.38 | Not Budgeted | - | - | 2.156% | 405727.3 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19601 | Madisonville 08 Non Growth | Madisonville 08 Non Growth | 454293.99 | Not Budgeted | - | - | 2.597% | 488721.61 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19606 | Paducah 08 Growth | Paducah 08 Growth | 456900.07 | Not Budgeted | - | - | 2.56% | 481743.91 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19591 | Glasgow 08 Non Growth | Glasgow 08 Non Growth | 468869.89 | Not Budgeted | - | - | 2.607% | 490554.67 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2009-05-13 | 2009-05-13
| 050.19604 | Owensboro 08 Growth | Owensboro 08 Growth | 542305.85 | Not Budgeted | - | - | 2.977% | 560148.62 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20287 | 050.BGR.GLS.HART CO. IND. | HART CO. INDUSTRIAL PUR. STA. & 4" STL. EXT. | 659253.51 | 583548 | -196895.12 | -33.74% | 2.055% | 386652.88 | 583548 | -196895.12 | 2007-10-01 | 2008-09-30 | 2007-11-09 | 2007-11-09 | 2008-11-09 | 2008-11-09
| 050.19595 | Danville 08 Non Growth | Danville 08 Non Growth | 671027.3 | Not Budgeted | - | - | 3.755% | 706509.63 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19607 | Paducah 08 Non Growth | Paducah 08 Non Growth | 899811.85 | Not Budgeted | - | - | 5.035% | 947463.09 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19588 | Bowling Green 08 Growth | Bowling Green 08 Growth | 1073058.5 | Not Budgeted | - | - | 5.921% | 1114047.31 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19605 | Owensboro 08 Non Growth | Owensboro 08 Non Growth | 1397017.03 | Not Budgeted | - | - | 7.838% | 1474828.56 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.20663 | 050.2609.Hopkinsville 10" | Replacing 2 miles of 10" Stl. with 12" Stl. | 1531917.59 | 2088080.62 | 625043.32 | 29.93% | 14.42% | 2713123.94 | 2088080.62 | 625043.32 | 2007-10-01 | 2008-09-30 | 2008-05-15 | 2008-05-15 | 2008-12-31 | 2008-12-31
| 050.19589 | Bowling Green 08 Non Growth | Bowling Green 08 Non Growth | 2026194.82 | Not Budgeted | - | - | 11.27% | 2120851.55 | Not Budgeted | - | 2007-10-01 | 2008-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31

## 2007a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2007
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2007 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 040.10318 | WKG.PAD.MAINT.FUNCT | FUNCTIONAL MAINTENANCE | -858771.34 | Not Budgeted | - | - | 1.747% | 293494.15 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.12922 | St. Charles Engine Overhaul | Overhaul St. Charles Compressor Engine | -711129.23 | 245177 | -59660.99 | -24.33% | 1.104% | 185516.01 | 245177 | -59660.99 | 2006-10-01 | 2007-09-30 | 2006-01-23 | 2006-01-23 | 2006-09-28 | 2006-09-28
| 040.10316 | WKG.OBORO.MAINT.FUNCT | FUNCTIONAL MAINTENANCE | -406342.76 | Not Budgeted | - | - | -2.419% | -406342.76 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 1999-10-01 | 1999-10-01 | 2006-09-27 | 2006-09-27
| 050.19449 | 050.2634.917614 | MEC Forfeiture | -346710.6 | Not Budgeted | - | - | -2.064% | -346710.6 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.10317 | WKG.MAD.MAINT.FUNCT | FUNCTION MAINTENANCE | -182955.85 | Not Budgeted | - | - | -0.41% | -68879.29 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.12763 | Bowling Green 06 Non Growth | Bowling Green 06 Non Growth | -116967.53 | Not Budgeted | - | - | 9.304% | 1562884.63 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12793 | 040.2739.HWY 60 RELOCATE | INSTALL 540' OF 6" STEEL ON HWY 60-STATE RELOCATE | -113317.37 | -39540 | 168463.1 | -426.1% | 0.7675% | 128923.1 | -39540 | 168463.1 | 2006-10-01 | 2007-09-30 | 2005-10-18 | 2005-10-18 | 2005-12-25 | 2005-12-25
| 040.11125 | WKG.02.Oboro.Maint.Functional | Owensboro Maint Functional 2002 | -109858.38 | Not Budgeted | - | - | -0.654% | -109858.38 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2001-09-26 | 2001-09-26 | 2006-09-27 | 2006-09-27
| 040.12361 | Hopkinsville 05 Non Growth | Hopkinsville 05 Non Growth | -97081.87 | Not Budgeted | - | - | 1.905% | 320059.85 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19302 | 040.2737.917774 | MEC Forfeiture | -83379.82 | Not Budgeted | - | - | -0.4964% | -83379.82 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-07-02 | 2007-07-02 | 2007-07-02 | 2007-07-02
| 040.11937 | Bowling Green.040.NonG F | Bowling Green.04.Non Growth Functional | -69272.63 | Not Budgeted | - | - | -0.3238% | -54398.44 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.10314 | WKG.BRG.MAINT.FUNCT | FUNCTIONAL MAINTENANCE | -63384.1 | Not Budgeted | - | - | -0.3773% | -63384.1 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 1999-10-01 | 1999-10-01 | 2006-09-27 | 2006-09-27
| 040.11941 | Hopkins.04.Non Gr Funct | Hopkinsville.04.Non Growth Functional | -51338.13 | Not Budgeted | - | - | -0.3112% | -52273.09 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.11131 | WKG.02.Paducah.Maint.Function | Paducah Maint Functional 2002 | -48360.8 | Not Budgeted | - | - | -0.2879% | -48360.8 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2001-09-26 | 2001-09-26 | 2006-09-27 | 2006-09-27
| 040.11562 | WKG.PAD.O3.NON-GROWTH FUNCTION | PADUCAH NON-GROWTH FUNCTIONAL | -43735.2 | Not Budgeted | - | - | -0.2604% | -43735.2 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2002-09-27 | 2002-09-27 | 2006-09-27 | 2006-09-27
| 040.11559 | WKG.MAD.03.NON-GROWTH FUNCTION | MADISONVILLE NON-GROWTH FUNCTIONAL | -42494.18 | Not Budgeted | - | - | -0.253% | -42494.18 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.11939 | Glsgow.04.Non Grow Func | Glasgow.04.Non Growth Functional | -40582.52 | Not Budgeted | - | - | -0.2416% | -40582.52 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2003-09-25 | 2003-09-25 | 2006-09-27 | 2006-09-27
| 040.11553 | WKG.BG.03.NON-GROWTH FUNCTIONA | BOWLING GREEN NON-GROWTH FUNCTIONAL | -40525.24 | Not Budgeted | - | - | -0.2412% | -40525.24 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2002-09-27 | 2002-09-27 | 2006-09-27 | 2006-09-27
| 050.19617 | 050.2734.917620 | MEC Forfeiture | -39533 | Not Budgeted | - | - | -0.2353% | -39533 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 040.11556 | WKG.DAN.03.NON-GROWTH FUNCTION | DANVILLE NON-GROWTH FUNCTIONAL | -33009.87 | Not Budgeted | - | - | -0.1965% | -33009.87 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2002-09-27 | 2002-09-27 | 2006-09-27 | 2006-09-27
| 040.11140 | WKG.02.Princeton.Maint.Func | Princeton 2002 Maintance Functional | -32305.86 | Not Budgeted | - | - | -0.1923% | -32305.86 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.11134 | WKG.02.Glasgow.Maint.Func | Glasgow 2002 Maintance Functional | -29287.88 | Not Budgeted | - | - | -0.1744% | -29287.88 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2001-09-26 | 2001-09-26 | 2006-09-27 | 2006-09-27
| 040.13016 | 040.PAD.Pecan 8 inch Relocate | Install 1,150 ' of 8" T'Line | -28986.71 | 73675.49 | 63645.6 | 86.39% | 0.8175% | 137321.09 | 73675.49 | 63645.6 | 2006-10-01 | 2007-09-30 | 2006-04-10 | 2006-04-10 | 2006-09-22 | 2006-09-22
| 040.11554 | WKG.GLA.03.NON-GROWTH FUNCTION | GLASGOW NON-GROWTH FUNCTIONAL | -28454.93 | Not Budgeted | - | - | -0.1694% | -28454.93 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.19452 | 050.2636.917063 | MEC Forfeiture | -28410 | Not Budgeted | - | - | -0.1691% | -28410 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.11560 | WKG.PTON.O3.NON-GROWTH FUNCTIO | PRINCETON NON-GROWTH FUNCTIONAL | -28304 | Not Budgeted | - | - | -0.1685% | -28304 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.18576 | 050.2734.916537 | MEC Forfeiture | -28203 | Not Budgeted | - | - | -0.1679% | -28203 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 040.10008 | WKG[9500] Conv Maint Funct | WKG Owensboro Blanket Group - 9500 Maintenance Functional Conversion | -28146.65 | Not Budgeted | - | - | -0.1676% | -28146.65 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.11955 | Pad.04.Non Grow Func | Paducah.04.Non Growth Functional | -26709.78 | Not Budgeted | - | - | -0.1599% | -26853.68 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19407 | 2738.LEB.PART LAND SALE | SALE OF PART OF THE LAND TOWN OPERATORS OFFICE.PROPANE PLANT | -24825 | -24825 | 11.49 | -0.04628% | -0.1477% | -24813.51 | -24825 | 11.49 | 2006-10-01 | 2007-09-30 | 2007-08-10 | 2007-08-10 | 2008-01-01 | 2008-01-01
| 050.19494 | 050.2734.917584 | MEC Forfeiture | -24538 | Not Budgeted | - | - | -0.1461% | -24538 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19613 | 050.2637.916999 | MEC Forfeiture | -23710 | Not Budgeted | - | - | -0.1411% | -23710 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 040.11949 | Mad.04.Non Grow Func | Madisonville.04.Non Growth Functional | -20861.88 | Not Budgeted | - | - | -0.1242% | -20861.88 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2003-09-25 | 2003-09-25 | 2006-09-27 | 2006-09-27
| 040.12367 | Shelbyville 05 Non Growth | Shelbyville 05 Non Growth | -20118.32 | Not Budgeted | - | - | 1.375% | 230938.6 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.11957 | Mayf.04.Non Grow Func | Mayfield.04.Non Growth Functional | -19156.1 | Not Budgeted | - | - | -0.114% | -19156.1 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2003-09-25 | 2003-09-25 | 2006-09-27 | 2006-09-27
| 050.19303 | 040.2737.917154 | MEC Forfeiture | -18244.21 | Not Budgeted | - | - | -0.1086% | -18244.21 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-07-02 | 2007-07-02 | 2007-07-02 | 2007-07-02
| 050.19294 | 2739.LAW.SCHOOL RELOCAT 6 ST | RELOCATE 800' OF 6" STEEL FOR ELEMENTARY SCHOOL.LAWRENCEBURG | -18232.95 | 48300 | -43068.04 | -89.17% | 0.03115% | 5231.96 | 48300 | -43068.04 | 2006-10-01 | 2007-09-30 | 2007-06-27 | 2007-06-27 | 2008-06-06 | 2008-06-06
| 040.11555 | WKG.HOP.O3.NON-GROWTH FUNCTION | HOPKINSVILLE NON-GROWTH FUNCTIONAL | -18225.48 | Not Budgeted | - | - | -0.1085% | -18225.48 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.18578 | 050.2734.916627 | MEC Forfeiture | -18159 | Not Budgeted | - | - | -0.1081% | -18159 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 040.10019 | WKG[009]Maint.Funct | WKG[009] Rate Div Maintenance Functional | -15921.2 | Not Budgeted | - | - | -0.1339% | -22488.63 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19095 | 050.2737.917029 | MEC Foreirture | -15852 | Not Budgeted | - | - | -0.09437% | -15852 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-04-24 | 2007-04-24 | 2007-04-24 | 2007-04-24
| 040.11945 | Cam.04.Non Grow Funct | Campbellsville.04.Non Growth Functional | -15014.26 | Not Budgeted | - | - | -0.08938% | -15014.26 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2003-09-25 | 2003-09-25 | 2006-09-27 | 2006-09-27
| 040.11943 | Danv.04.Non Gr Funct | Danville.04.Non Growth Functional | -14659.31 | Not Budgeted | - | - | -0.08727% | -14659.31 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2003-09-25 | 2003-09-25 | 2006-09-27 | 2006-09-27
| 040.12534 | 040.DAN.CORNISHVILLE BRDG RELO | RELOCATE 610' OF 2" PE ON CORNISHVILLE ROAD AT THE BRIDGE | -14140.5 | 214.5 | 2543.61 | 1186% | 0.01642% | 2758.11 | 214.5 | 2543.61 | 2006-10-01 | 2007-09-30 | 2005-03-01 | 2005-03-01 | 2005-08-01 | 2005-08-01
| 050.19094 | 050.2737.917031 | MEC Foreirture | -13788 | Not Budgeted | - | - | -0.08208% | -13788 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-04-24 | 2007-04-24 | 2007-04-24 | 2007-04-24
| 050.19451 | 050.2636.916932 | MEC Forfeiture | -13316 | Not Budgeted | - | - | -0.07927% | -13316 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19623 | 050.2734.917827 | MEC Forfeiture | -12331 | Not Budgeted | - | - | -0.07341% | -12331 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.19485 | 050.2637.917342 | MEC Forfeiture | -11626 | Not Budgeted | - | - | -0.06921% | -11626 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.11558 | WKG.SVILLE.03.NON-GROWTH FUNCT | SHELBYVILLE NON-GROWTH FUNCTIONAL | -10433.78 | Not Budgeted | - | - | -5.414e-18% | -9.0949e-13 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.19260 | 050.2634.Midtown Commons | Relocate 1,076' 4" Stl with 1,456' 4" Stl due to commercial development | -9886 | 0 | 3231.36 | - | 0.01924% | 3231.36 | 0 | 3231.36 | 2006-10-01 | 2007-09-30 | 2007-06-07 | 2007-06-07 | 2007-10-24 | 2007-10-24
| 050.19492 | 050.2734.917146 | MEC Forfeiture | -9799 | Not Budgeted | - | - | -0.05833% | -9799 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19458 | 050.2636.917598 | MEC Forfeiture | -9792 | Not Budgeted | - | - | -0.05829% | -9792 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.18577 | 050.2734.916322 | MEC Forfeiture | -9535 | Not Budgeted | - | - | -0.05676% | -9535 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.19622 | 050.2734.917775 | MEC Forfeiture | -9205 | Not Budgeted | - | - | -0.0548% | -9205 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.19307 | 040.2737.916948 | MEC Forfeiture | -8851.05 | Not Budgeted | - | - | -0.05269% | -8851.05 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-07-02 | 2007-07-02 | 2007-07-02 | 2007-07-02
| 050.19614 | 050.2636.917795 | MEC Forfeiture | -8721 | Not Budgeted | - | - | -0.05192% | -8721 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.19457 | 050.2636.917597 | MEC Forfeiture | -8647 | Not Budgeted | - | - | -0.05148% | -8647 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19175 | 050.2737.91698501 | MEC Forfeiture | -8410 | Not Budgeted | - | - | -0.05006% | -8410 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 050.19470 | 050.2637.917797 | MEC Forfeiture | -7635 | Not Budgeted | - | - | -0.04545% | -7635 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.18626 | EFM for B.G. Med Center | EFM for Bowling Green Medical Center | -6680.36 | 2782 | -9462.36 | -340.1% | -0.03977% | -6680.36 | 2782 | -9462.36 | 2006-10-01 | 2007-09-30 | 2006-10-30 | 2006-10-30 | 2008-02-01 | 2008-02-01
| 040.12836 | Shetland Hills #2 MEC Forf | MEC Forfeiture Eastern Hill Developer | -6357 | Not Budgeted | - | - | -0.03784% | -6357 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-12-01 | 2005-12-01 | 2005-12-30 | 2005-12-30
| 040.11122 | WKG.02.Danv.Maint.Functional | Danville Maintenance Functional 2002 | -6301.01 | Not Budgeted | - | - | -0.03751% | -6301.01 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2001-09-26 | 2001-09-26 | 2006-09-27 | 2006-09-27
| 040.13036 | 040.PAD.Jim Smith Meter Set | Costs to cover new mtr set for Jim Smith new asphalt plant | -6247.73 | 0 | 8965.99 | - | 0.05337% | 8965.99 | 0 | 8965.99 | 2006-10-01 | 2007-09-30 | 2006-06-01 | 2006-06-01 | 2006-09-22 | 2006-09-22
| 040.12655 | 040.OBO.Whispering Meadows | INSTALL 364' 4" PE | -6030.03 | 16275.66 | -13325.01 | -81.87% | 0.01757% | 2950.65 | 16275.66 | -13325.01 | 2006-10-01 | 2007-09-30 | 2005-08-08 | 2005-08-08 | 2005-08-26 | 2005-08-26
| 040.13020 | 040.PAD.Olivet Ch Relocate IV | City adding turn lane at Sanders Blvd/ Install 670' - 2" PE | -6000 | 518.55 | 1148.26 | 221.4% | 0.009923% | 1666.81 | 518.55 | 1148.26 | 2006-10-01 | 2007-09-30 | 2006-04-20 | 2006-04-20 | 2006-09-22 | 2006-09-22
| 040.10014 | WKG[9560] Conv Maint Funct | WKG Bowling Green Blanket Group - 9560 Maintenance Functional Conversion | -5781.63 | Not Budgeted | - | - | -0.03442% | -5781.63 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.11557 | WKG.CVILLE.O3.NON-GROWTH FUNCT | CAMPBELLSVILLE NON-GROWTH FUNCTIONAL | -5484.77 | Not Budgeted | - | - | -0.03265% | -5484.77 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2002-09-27 | 2002-09-27 | 2006-09-27 | 2006-09-27
| 050.19395 | 050.2737.917551 | MEC Forfeiture | -5075.99 | Not Budgeted | - | - | -0.03022% | -5075.99 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 040.10315 | WKG.DAN.MAINT.FUNCT | FUNCTIONAL MAINTENANCE | -4970.49 | Not Budgeted | - | - | -0.02959% | -4970.49 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 1999-10-01 | 1999-10-01 | 2006-09-27 | 2006-09-27
| 050.19366 | 050.2636.Hill Bridge Rd. | Install 910' 2" PE | -4883.02 | 3412.37 | 1325.83 | 38.85% | 0.02821% | 4738.2 | 3412.37 | 1325.83 | 2006-10-01 | 2007-09-30 | 2007-07-24 | 2007-07-24 | 2007-09-27 | 2007-09-27
| 050.18572 | 050.2636.916931 | MEC Forfeiture | -4759 | Not Budgeted | - | - | -0.02833% | -4759 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.19479 | 050.2637.917687 | MEC Forfeiture | -4749 | Not Budgeted | - | - | -0.02827% | -4749 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19475 | 050.2637.917000 | MEC Forfeiture | -4618 | Not Budgeted | - | - | -0.02749% | -4618 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12631 | 040.MAY.New Office Accessories | Office furniture and accessories for the new Mayfield, KY office | -4613.19 | 48124.48 | 31988.29 | 66.47% | 0.4769% | 80112.77 | 48124.48 | 31988.29 | 2006-10-01 | 2007-09-30 | 2005-07-06 | 2005-07-06 | 2005-09-23 | 2005-09-23
| 040.13046 | AKY.TCSVC.MEAS.EFM.FP INT. | INSTALLATION OF EFM @ FP INTERNATIONAL | -4528 | 5622.24 | -6655.57 | -118.4% | -0.006151% | -1033.33 | 5622.24 | -6655.57 | 2006-10-01 | 2007-09-30 | 2006-06-24 | 2006-06-24 | 2006-09-28 | 2006-09-28
| 050.18723 | 050.2636.917264 | MEC Forfeiture | -4221 | Not Budgeted | - | - | -0.02513% | -4221 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-12-11 | 2006-12-11 | 2006-12-12 | 2006-12-12
| 050.19616 | 050.2636.917752 | MEC Forfeiture | -4066 | Not Budgeted | - | - | -0.0242% | -4066 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.19398 | 050.2736.917008 | MEC Forfeiture | -3969 | Not Budgeted | - | - | -0.02363% | -3969 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 040.11563 | WKG.MAY.O3.NON-FUNCTIONAL | MAYFIELD NON-FUNCTIONAL | -3769.9 | Not Budgeted | - | - | -0.02244% | -3769.9 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.19283 | 50.BGR,RETIRE 2-TON DUMP TRK. | RETIRE UNIT #7304 - 2-TON DUMP TRUCK - BOWLING GREEN | -3730 | -2500 | -1230 | 49.2% | -0.0222% | -3730 | -2500 | -1230 | 2006-10-01 | 2007-09-30 | 2007-06-21 | 2007-06-21 | 2007-09-28 | 2007-09-28
| 050.19393 | 050.2737.917208 | MEC Forfeiture | -3622.53 | Not Budgeted | - | - | -0.02156% | -3622.53 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19180 | 050.2734.917141 | MEC Forfeiture | -3474 | Not Budgeted | - | - | -0.02068% | -3474 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 050.19392 | 050.2737.917696 | MEC Forfeiture | -3471 | Not Budgeted | - | - | -0.02066% | -3471 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19184 | 050.2734.917211 | MEC Forfeiture | -3403 | Not Budgeted | - | - | -0.02026% | -3403 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 050.19446 | 050.2634.917518 | MEC Forfeiture | -3398 | Not Budgeted | - | - | -0.02023% | -3398 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.11119 | WKG.02.BG.Maintenance.Function | Bowling Green Maintenance Functional | -3335.81 | Not Budgeted | - | - | -0.01986% | -3335.81 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2001-09-26 | 2001-09-26 | 2006-09-27 | 2006-09-27
| 050.19445 | 050.2634.917890 | MEC Forfeiture | -3222 | Not Budgeted | - | - | -0.01918% | -3222 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19466 | 050.2637.917341 | MEC Forfeiture | -3200 | Not Budgeted | - | - | -0.01905% | -3200 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19394 | 050.2737.917699 | MEC Forfeiture | -3169.32 | Not Budgeted | - | - | -0.01887% | -3169.32 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19454 | 050.2636.917720 | MEC Forfeiture | -2832 | Not Budgeted | - | - | -0.01686% | -2832 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19482 | 050.2637.917710 | MEC Forfeiture | -2547.28 | Not Budgeted | - | - | -0.01516% | -2547.28 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19459 | 050.2636.917715 | MEC Forfeiture | -2490 | Not Budgeted | - | - | -0.01482% | -2490 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19241 | Tech.Serv.Mea.EFM.Felker Bros | EFM for Felker Brothers Corp. - Glasgow | -2324.93 | 3860 | -6184.93 | -160.2% | -0.01384% | -2324.93 | 3860 | -6184.93 | 2006-10-01 | 2007-09-30 | 2007-06-01 | 2007-06-01 | 2007-09-30 | 2007-09-30
| 050.19489 | 050.2637.917610 | MEC Forfeiture | -2300 | Not Budgeted | - | - | -0.01369% | -2300 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.18574 | 050.2636.916930 | MEC Forfeiture | -2287 | Not Budgeted | - | - | -0.01361% | -2287 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.18569 | 050.2636.915143 | MEC Forfeiture | -2265 | Not Budgeted | - | - | -0.01348% | -2265 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 040.11953 | Owen.04.Non Grow Func | Owensboro.04.Non Growth Functional | -2145.04 | Not Budgeted | - | - | -0.01797% | -3018.51 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-06-03 | 2005-06-03 | 2005-06-03 | 2005-06-03
| 050.19176 | 050.2737.916984 | MEC Forfeiture | -2121 | Not Budgeted | - | - | -0.01263% | -2121 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 050.18570 | 050.2636.916867 | MEC Forfeiture | -2102 | Not Budgeted | - | - | -0.01251% | -2102 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.19463 | 050.2637.917336 | MEC Forfeiture | -2023 | Not Budgeted | - | - | -0.01204% | -2023 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19484 | 050.2637.916791 | MEC Forfeiture | -1937 | Not Budgeted | - | - | -0.01153% | -1937 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19182 | 050.2734.916334 | MEC Forfeiture | -1899.95 | Not Budgeted | - | - | -0.01131% | -1899.95 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 050.19476 | 050.2637.917078 | MEC Forfeiture | -1845 | Not Budgeted | - | - | -0.01098% | -1845 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19447 | 050.2634.917751 | MEC Forfeiture | -1841 | Not Budgeted | - | - | -0.01096% | -1841 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19625 | 050.2736.917847 | MEC Forfeiture | -1736 | Not Budgeted | - | - | -0.01033% | -1736 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-24 | 2007-09-24 | 2007-09-25 | 2007-09-25
| 050.18886 | 2737.HUB BUILDING | INSTALL 250' OF 2" PE FOR THE HUB BUILDING | -1685.55 | 1592 | -3277.55 | -205.9% | -0.01003% | -1685.55 | 1592 | -3277.55 | 2006-10-01 | 2007-09-30 | 2007-01-24 | 2007-01-24 | 2008-01-24 | 2008-01-24
| 050.19453 | 050.2636.917139 | MEC Forfeiture | -1553 | Not Budgeted | - | - | -0.009245% | -1553 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19626 | 050.2734.917142 | MEC Forfeiture | -1521 | Not Budgeted | - | - | -0.009055% | -1521 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-24 | 2007-09-24 | 2007-09-25 | 2007-09-25
| 050.19397 | 050.2737.917513 | MEC Forfeiture | -1509 | Not Budgeted | - | - | -0.008983% | -1509 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.18530 | 050.2734.916829 | Mec Forfeitures | -1507 | Not Budgeted | - | - | -0.008971% | -1507 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-09 | 2006-10-09 | 2006-10-10 | 2006-10-10
| 050.19396 | 050.2737.917004 | MEC Forfeiture | -1463 | Not Budgeted | - | - | -0.008709% | -1463 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19456 | 050.2636.917596 | MEC Forfeiture | -1355 | Not Budgeted | - | - | -0.008066% | -1355 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19478 | 050.2637.917628 | MEC Forfeiture | -1339 | Not Budgeted | - | - | -0.007971% | -1339 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.11138 | WKG.02.Camp'ville.Maint.Func | Campsville 2002 Maintance Functional | -1306.92 | Not Budgeted | - | - | -0.00778% | -1306.92 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2001-09-26 | 2001-09-26 | 2006-09-27 | 2006-09-27
| 050.18529 | 050.2734.916865 | Mec Forfeitures | -1236 | Not Budgeted | - | - | -0.007358% | -1236 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-09 | 2006-10-09 | 2006-10-10 | 2006-10-10
| 050.19620 | 050.2734.917275 | MEC Forfeiture | -1233 | Not Budgeted | - | - | -0.00734% | -1233 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.18571 | 050.2636.916873 | MEC Forfeiture | -1130 | Not Budgeted | - | - | -0.006727% | -1130 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.18575 | 050.2636.916988 | MEC Forfeiture | -1035.52 | Not Budgeted | - | - | -0.006164% | -1035.52 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.19473 | 050.2637.916943 | MEC Forfeiture | -1018 | Not Budgeted | - | - | -0.00606% | -1018 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19483 | 050.2637.917877 | MEC Forfeiture | -1008 | Not Budgeted | - | - | -0.006001% | -1008 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.13100 | 040.BGR.RETIRE UNIT8455 | TRETIRE UNIT8455 ISSUED TO BUDDY WHITE - B.G. | -1000 | -2500 | 1500 | -60% | -0.005953% | -1000 | -2500 | 1500 | 2006-10-01 | 2007-09-30 | 2006-08-16 | 2006-08-16 | 2006-09-28 | 2006-09-28
| 050.18573 | 050.2636.916929 | MEC FORFEITUE | -944 | Not Budgeted | - | - | -0.00562% | -944 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-10-19 | 2006-10-19
| 050.19621 | 050.2734.917359 | MEC Forfeiture | -941 | Not Budgeted | - | - | -0.005602% | -941 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.18708 | KY.MEA.EFM.LAND O FROST | EFM FOR LAND O FROST IN MADISONVILLE | -881.38 | 2782 | -3663.38 | -131.7% | -0.005247% | -881.38 | 2782 | -3663.38 | 2006-10-01 | 2007-09-30 | 2006-11-30 | 2006-11-30 | 2007-11-30 | 2007-11-30
| 050.19615 | 050.2636.917794 | MEC Forfeiture | -879 | Not Budgeted | - | - | -0.005233% | -879 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 040.12368 | Madisonville 05 Growth | Madisonville 05 Growth | -835.06 | Not Budgeted | - | - | 1.008% | 169286.52 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19618 | 050.2734.917629 | MEC Forfeiture | -810 | Not Budgeted | - | - | -0.004822% | -810 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.19467 | 050.2637.917703 | MEC Forfeiture | -809 | Not Budgeted | - | - | -0.004816% | -809 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19474 | 050.2637.916965 | MEC Forfeiture | -803 | Not Budgeted | - | - | -0.00478% | -803 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12269 | 040.Sto. Retire Bushhogs | Retire 2 model 406 Bushhogs | -785 | -410 | -693.66 | 169.2% | -0.00657% | -1103.66 | -410 | -693.66 | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.19462 | 050.2637.917248 | MEC Forfeiture | -772 | Not Budgeted | - | - | -0.004596% | -772 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19692 | 050.2734.917227 | MEC Forfeiture | -768 | Not Budgeted | - | - | -0.004572% | -768 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-10-03 | 2007-10-03 | 2007-10-03 | 2007-10-03
| 050.19391 | 050.2737.916956 | MEC Forfeiture | -748 | Not Budgeted | - | - | -0.004453% | -748 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19448 | 050.2634.917409 | MEC Forfeiture | -744 | Not Budgeted | - | - | -0.004429% | -744 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19461 | 050.2636.917844 | MEC Forfeiture | -720 | Not Budgeted | - | - | -0.004286% | -720 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19177 | 050.2737.91719001 | MEC Forfeiture | -691 | Not Budgeted | - | - | -0.004114% | -691 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 050.19465 | 050.2637.917339 | MEC Forfeiture | -690 | Not Budgeted | - | - | -0.004108% | -690 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19389 | 050.2737.917345 | MEC Forfeiture | -687 | Not Budgeted | - | - | -0.00409% | -687 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19486 | 050.2637.917362 | MEC Forfeiture | -685 | Not Budgeted | - | - | -0.004078% | -685 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19493 | 050.2734.917007 | MEC Forfeiture | -661 | Not Budgeted | - | - | -0.003935% | -661 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19387 | 050.2737.917147 | MEC Forfeiture | -653 | Not Budgeted | - | - | -0.003887% | -653 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19490 | 050.2638.916992 | MEC Forfeiture | -629 | Not Budgeted | - | - | -0.003744% | -629 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.10010 | WKG[9515] Conv Maint Funct | WKG Madisonville Blanket Group - 9515 Maintenance Functional Conversion | -606.52 | Not Budgeted | - | - | -0.04464% | -7497.96 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19619 | 050.2734.917068 | MEC Forfeiture | -597 | Not Budgeted | - | - | -0.003554% | -597 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-21 | 2007-09-21 | 2007-09-25 | 2007-09-25
| 050.19388 | 050.2737.916958 | MEC Forfeiture | -588 | Not Budgeted | - | - | -0.0035% | -588 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 050.19488 | 050.2637.917609 | MEC Forfeiture | -585 | Not Budgeted | - | - | -0.003483% | -585 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19691 | 050.2734.917210 | MEC Forfeiture | -579 | Not Budgeted | - | - | -0.003447% | -579 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-10-03 | 2007-10-03 | 2007-10-03 | 2007-10-03
| 050.19450 | 050.2634.917783 | MEC Forfeiture | -570 | Not Budgeted | - | - | -0.003393% | -570 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19059 | TCHSVR.MEA.EFM.KERR FORREST | EFM FOR KERR FOREST PRODUCTS IN BOWLING GREEN | -537.7 | 3860 | -4397.7 | -113.9% | -0.003201% | -537.7 | 3860 | -4397.7 | 2006-10-01 | 2007-09-30 | 2007-04-04 | 2007-04-04 | 2007-09-30 | 2007-09-30
| 050.19464 | 050.2637.917338 | MEC Forfeiture | -513 | Not Budgeted | - | - | -0.003054% | -513 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.18823 | 050.2636.917158 | MEC Forfeiture | -506 | Not Budgeted | - | - | -0.003012% | -506 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-01-04 | 2007-01-04 | 2007-01-05 | 2007-01-05
| 040.11139 | WKG.02.Shelbyville.Maint.Func | Shelbyville 2002 Maintance Functional | -497.72 | Not Budgeted | - | - | -0.001255% | -210.83 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.12357 | Bowling Green 05 Non Growth | Bowling Green 05 Non Growth | -474.78 | Not Budgeted | - | - | 8.638% | 1451034.84 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19481 | 050.2637.917697 | MEC Forfeiture | -456 | Not Budgeted | - | - | -0.002715% | -456 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19477 | 050.2637.917626 | MEC Forfeiture | -440 | Not Budgeted | - | - | -0.002619% | -440 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19487 | 050.2637.917608 | MEC Forfeiture | -422 | Not Budgeted | - | - | -0.002512% | -422 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19495 | 050.2736.917215 | MEC Forfeiture | -417 | Not Budgeted | - | - | -0.002482% | -417 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12369 | Madisonville 05 Non Growth | Madisonville 05 Non Growth | -409.17 | Not Budgeted | - | - | 4.01% | 673666.4 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19179 | 050.2734.0915413 | MEC Forfeiture | -378 | Not Budgeted | - | - | -0.00225% | -378 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-05-06 | 2007-05-06
| 040.12401 | 040.tcsvc.Meas.Rotary Meters | Dresser Rotary Meters | -368.82 | 59150 | -7365.3 | -12.45% | 0.3083% | 51784.7 | 59150 | -7365.3 | 2006-10-01 | 2007-09-30 | 2004-10-19 | 2004-10-19 | 2005-07-15 | 2005-07-15
| 050.19460 | 050.2636.917736 | MEC Forfeiture | -346 | Not Budgeted | - | - | -0.00206% | -346 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12774 | Madisonville 06 Growth | Madisonville 06 Growth | -318.77 | Not Budgeted | - | - | 0.8934% | 150077.06 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19491 | 050.2638.917363 | MEC Forfeiture | -264 | Not Budgeted | - | - | -0.001572% | -264 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12375 | Paducah 05 Non Growth | Paducah 05 Non Growth | -259.34 | Not Budgeted | - | - | 2.65% | 445168.43 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19469 | 050.2637.917727 | MEC Forfeiture | -253 | Not Budgeted | - | - | -0.001506% | -253 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12760 | 040.PAD.Cedar Ridge Rev Ext | 900' - 2" PE for 13 lots | -245.05 | 4481.07 | -249.8 | -5.575% | 0.02519% | 4231.27 | 4481.07 | -249.8 | 2006-10-01 | 2007-09-30 | 2005-10-03 | 2005-10-03 | 2006-09-22 | 2006-09-22
| 050.19455 | 050.2636.917737 | MEC Forfeiture | -245 | Not Budgeted | - | - | -0.001458% | -245 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19472 | 050.2637.916926 | MEC Forfeiture | -240 | Not Budgeted | - | - | -0.001429% | -240 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19339 | 050.2636.Warehouse Rd. | Install 1008' 2" PE | -214.84 | 1869.71 | -2061.56 | -110.3% | -0.001142% | -191.85 | 1869.71 | -2061.56 | 2006-10-01 | 2007-09-30 | 2007-07-11 | 2007-07-11 | 2007-09-26 | 2007-09-26
| 040.12373 | Owensboro 05 Non Growth | Owensboro 05 Non Growth | -204.94 | Not Budgeted | - | - | 8.747% | 1469337.62 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12594 | 040.PAD.Misc Work Equip | Pls and steel squeeze-off tools | -199.49 | 26389 | -1512.62 | -5.732% | 0.1481% | 24876.38 | 26389 | -1512.62 | 2006-10-01 | 2007-09-30 | 2005-05-27 | 2005-05-27 | 2005-09-23 | 2005-09-23
| 040.12372 | Owensboro 05 Growth | Ownesboro 05 Growth | -197.31 | Not Budgeted | - | - | 2.905% | 487910.59 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12426 | aky.tcssvc.meas.regulators | Regulators for engineered applications | -194.35 | 24986 | 8479.98 | 33.94% | 0.1992% | 33465.98 | 24986 | 8479.98 | 2006-10-01 | 2007-09-30 | 2004-12-01 | 2004-12-01 | 2005-09-28 | 2005-09-28
| 050.19480 | 050.2637.917695 | MEC Forfeiture | -189 | Not Budgeted | - | - | -0.001125% | -189 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12622 | 040.OBO.BOETLER RD. ODORIZER | INSTALL ODORIZER | -180.81 | 40607.6 | -1680.61 | -4.139% | 0.2317% | 38926.99 | 40607.6 | -1680.61 | 2006-10-01 | 2007-09-30 | 2005-06-24 | 2005-06-24 | 2005-08-05 | 2005-08-05
| 040.12363 | Danville 05 Non Growth | Danville 05 Non Growth | -174.48 | Not Budgeted | - | - | 2.685% | 451003.86 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19468 | 050.2637.917713 | MEC Forfeiture | -170 | Not Budgeted | - | - | -0.001012% | -170 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 050.19308 | 040.2737.916959 | MEC Forfeiture | -161 | Not Budgeted | - | - | -0.0009584% | -161 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-07-02 | 2007-07-02 | 2007-07-02 | 2007-07-02
| 040.12790 | 040.PAD.Highland Rd Ext III | Install 900' - 2" PE for four existing and one new residential customer | -158.02 | 3012 | -939.36 | -31.19% | 0.01234% | 2072.64 | 3012 | -939.36 | 2006-10-01 | 2007-09-30 | 2005-10-11 | 2005-10-11 | 2006-09-22 | 2006-09-22
| 050.19471 | 050.2637.916429 | MEC Forfeiture | -157 | Not Budgeted | - | - | -0.0009346% | -157 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2007-08-31 | 2007-08-31
| 040.12804 | 040.PAD.Burldeen Dr Main Ext | Install 100' - 2" PE for one existing customer wanting to convert heat from elec | -127.36 | 1087.75 | 1546.48 | 142.2% | 0.01568% | 2634.23 | 1087.75 | 1546.48 | 2006-10-01 | 2007-09-30 | 2005-10-27 | 2005-10-27 | 2006-09-22 | 2006-09-22
| 040.12371 | Princeton 05 Non Growth | Princeton 05 Non Growth | -124.56 | Not Budgeted | - | - | 0.8939% | 150164.46 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12433 | 040.BGR.CUMBERLAND TRC. | CUMBERLABD TRACE 6" PE TIE-IN - B.G. | -111.58 | 127836 | -33782.22 | -26.43% | 0.5599% | 94053.78 | 127836 | -33782.22 | 2006-10-01 | 2007-09-30 | 2004-12-14 | 2004-12-14 | 2005-04-04 | 2005-04-04
| 040.12358 | Glasgow 05 Growth | Glasgow 05 Growth | -92.46 | Not Budgeted | - | - | 1.108% | 186132.4 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12359 | Glasgow 05 Non Growth | Glasgow 05 Non Growth | -92.46 | Not Budgeted | - | - | 3.493% | 586771.84 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12366 | Shelbyville 05 Growth | Shelbyville 05 Growth | -92.46 | Not Budgeted | - | - | 2.481% | 416803.53 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12374 | Paducah 05 Growth | Paducah 05 Growth | -92.46 | Not Budgeted | - | - | 1.85% | 310736.8 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.10113 | WKG.OBO.DITTO RD EXT | DITTO ROAD MAIN EXTENTION [WKG121] | -88.31 | 415 | -503.31 | -121.3% | -0.0005257% | -88.31 | 415 | -503.31 | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.10313 | WKG.TECH SVC.MAINT.FUNCT | FUNCTIONAL MAINTENANCE | -86.67 | Not Budgeted | - | - | -0.0005159% | -86.67 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.19390 | 050.2737.917053 | MEC Forfeiture | -76 | Not Budgeted | - | - | -0.0004524% | -76 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2007-08-03 | 2007-08-03
| 040.12356 | Bowling Green 05 Growth Func | Bowling Green 05 Growth Func | -59.78 | Not Budgeted | - | - | 5.662% | 951080.52 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12377 | Mayfield 05 Non Growth | Mayfield 05 Non Growth | -59.63 | Not Budgeted | - | - | 1.353% | 227199.87 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12788 | 040.MAY.N St Paul St Rev Ext | 100' 2"P extension for one customer ( Roy Bunch) | -56.45 | 1543.9 | -517.56 | -33.52% | 0.00611% | 1026.34 | 1543.9 | -517.56 | 2006-10-01 | 2007-09-30 | 2005-10-11 | 2005-10-11 | 2006-09-22 | 2006-09-22
| 040.12365 | Campbellsville 05 Non Growth | Campbellsville 05 Non Growth | -41.6 | Not Budgeted | - | - | 2.938% | 493477.76 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.10016 | WKG[9580] Conv Maint Funct | WKG Danville Blanket Group - 9580 Maintenance Functional Conversion | -31.02 | Not Budgeted | - | - | -0.07778% | -13065.66 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12614 | 040.PAD.Lydon Rd Rev Ext | 800' - 2" PE pipe for four existing customers and one new construction | -27.89 | 2525 | 2097.78 | 83.08% | 0.02752% | 4622.78 | 2525 | 2097.78 | 2006-10-01 | 2007-09-30 | 2005-06-21 | 2005-06-21 | 2005-09-23 | 2005-09-23
| 040.12364 | Campbellsville 05 Growth | Campbellsville 05 Growth | -19.47 | Not Budgeted | - | - | 0.7501% | 125997.82 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12599 | 040.BGR.MISC. EQUIP - B.G | SQUEEZE OFF TOOLS & LINE LOCATORS - B.G. | -5.57 | 20482 | 15191.98 | 74.17% | 0.2124% | 35673.98 | 20482 | 15191.98 | 2006-10-01 | 2007-09-30 | 2005-06-07 | 2005-06-07 | 2005-09-28 | 2005-09-28
| 040.12826 | 040.Sto Madisonville Tornado | Labor and material for Madisonville tornado | 0 | 40557 | 5233.66 | 12.9% | 0.2726% | 45790.66 | 40557 | 5233.66 | 2006-10-01 | 2007-09-30 | 2005-11-16 | 2005-11-16 | 2006-09-28 | 2006-09-28
| 040.13043 | 040.2737.EPHRAIM.FIGG-MLK | INSTALL 2" PE ON FIGG ALLEY AND RETIRE LINE ON MLK BLVD | 0 | -150 | -29573.42 | 19716% | -0.1769% | -29723.42 | -150 | -29573.42 | 2006-10-01 | 2007-09-30 | 2006-06-19 | 2006-06-19 | 2007-06-01 | 2007-06-01
| 040.13087 | 040.MAD.PRITCHETT AVE. | RETIRE 1 1/4" PE 455' | 0 | 522.35 | -92.49 | -17.71% | 0.002559% | 429.86 | 522.35 | -92.49 | 2006-10-01 | 2007-09-30 | 2006-08-08 | 2006-08-08 | 2006-08-11 | 2006-08-11
| 040.13109 | 040.MAD.Kenny Brasher Ret. | Retire Bare Unprotected main | 0 | 11802.96 | -3687.22 | -31.24% | 0.04831% | 8115.74 | 11802.96 | -3687.22 | 2006-10-01 | 2007-09-30 | 2006-08-28 | 2006-08-28 | 2006-09-22 | 2006-09-22
| OH.050.17884 | WKG State A&G Overhead | WKG State A&G Overhead Project | 0 | 0 | -1.8626e-09 | #DIV/0! | -1.109e-14% | -1.8626e-09 | 0 | -1.8626e-09 | 2006-10-01 | 2007-09-30 | Over | head | Over | head
| OH.040.10000 | WKG BU A&G Overhead | WKG Business Unit A&G Overhead Project | 1.4552e-11 | 0 | -38000 | #DIV/0! | -0.2262% | -38000 | 0 | -38000 | 2006-10-01 | 2007-09-30 | Over | head | Over | head
| 050.18721 | 050.2609.CroftonHCA12" | material needed to finish the HCA transmission line replacement in Crofton KY | 2.9104e-11 | 8726 | -8726 | -100% | 0% | 0 | 8726 | -8726 | 2006-10-01 | 2007-09-30 | 2006-12-07 | 2006-12-07 | 2006-12-11 | 2006-12-11
| 040.12278 | 040.Mea.Tecsvc.Regulators | Regulators for engineered applications | 10.93 | 23760 | -22681.13 | -95.46% | 0.006423% | 1078.87 | 23760 | -22681.13 | 2006-10-01 | 2007-09-30 | 2004-07-06 | 2004-07-06 | 2006-03-31 | 2006-03-31
| 040.13027 | 040.BGR.CHANDLER BLVD. 2"EXT | 1033 FT. OF 2" PE - CHANDLER BLVD. B.G. | 13.87 | 1605 | 1594.48 | 99.34% | 0.01905% | 3199.48 | 1605 | 1594.48 | 2006-10-01 | 2007-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.12764 | Glasgow 06 Growth | Glasgow 06 Growth | 14.84 | Not Budgeted | - | - | 0.6869% | 115387.19 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12559 | 040.OBO.2005 REG INSPECTIONS | 2005 REG.INSPECTIONS | 17.71 | 74657 | 272.17 | 0.3646% | 0.4461% | 74929.17 | 74657 | 272.17 | 2006-10-01 | 2007-09-30 | 2005-04-11 | 2005-04-11 | 2005-09-28 | 2005-09-28
| 040.13028 | 040.BGR.THE SUMMIT 2" PE EXT | 2" PE EXTENSION - THE SUMMIT PHASE I - B.G. | 27.72 | 19169 | -2189.61 | -11.42% | 0.1011% | 16979.39 | 19169 | -2189.61 | 2006-10-01 | 2007-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.13033 | 040.BGR.HOP.AMBULATORY CTR | 300 FT. OF 4" PE - EAGLE BYPASS - AMBULATORY CTR. - HOPK. | 27.72 | 2318 | -2261.01 | -97.54% | 0.0003393% | 56.99 | 2318 | -2261.01 | 2006-10-01 | 2007-09-30 | 2006-05-23 | 2006-05-23 | 2006-09-28 | 2006-09-28
| 040.13034 | 040.BGR.SUTHERLAND FARMS II-B | 1395 FT. OF 2" PE - SUTHERLAND FARMS II-B - B.G. | 27.72 | 5667 | -3660.28 | -64.59% | 0.01195% | 2006.72 | 5667 | -3660.28 | 2006-10-01 | 2007-09-30 | 2006-05-25 | 2006-05-25 | 2006-09-28 | 2006-09-28
| 040.12799 | 040.MAY.N Sutton Ln Ext | Install 325' - 2" PE for one existing home & one exist mobile home | 30.22 | 1074 | 587.11 | 54.67% | 0.009889% | 1661.11 | 1074 | 587.11 | 2006-10-01 | 2007-09-30 | 2005-10-24 | 2005-10-24 | 2006-09-22 | 2006-09-22
| 040.12834 | 040.PTON.Meter Purchase 2006 | the purchase of class 1 through 4 meters for Princeton for FY '06 | 37.96 | 29253.66 | -13054.68 | -44.63% | 0.09643% | 16198.98 | 29253.66 | -13054.68 | 2006-10-01 | 2007-09-30 | 2005-11-30 | 2005-11-30 | 2006-09-22 | 2006-09-22
| 040.12678 | 040.DAN.OFFICE FURNITURE | FURNITURE FOR OPERATION SUPERVISOR | 46.75 | 9910 | 1739.77 | 17.56% | 0.06935% | 11649.77 | 9910 | 1739.77 | 2006-10-01 | 2007-09-30 | 2005-09-22 | 2005-09-22 | 2005-10-01 | 2005-10-01
| 050.19418 | 050.2602RETIRE4PC07 | Retire 4 drafting PCs | 53.57 | 350 | -283.69 | -81.05% | 0.0003947% | 66.31 | 350 | -283.69 | 2006-10-01 | 2007-09-30 | 2007-08-17 | 2007-08-17 | 2007-09-27 | 2007-09-27
| 040.12776 | Princeton 06 Growth | Princeton 06 Growth | 55.45 | Not Budgeted | - | - | 0.2068% | 34738.06 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12770 | Campbellsville 06 Growth | Campbellsville 06 Growth | 59.49 | Not Budgeted | - | - | 0.476% | 79962.84 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12668 | aky.tcsvc.meas.Teledyne | Retirement of Teledyne Forklift | 60.22 | -5955 | 6751.86 | -113.4% | 0.004744% | 796.86 | -5955 | 6751.86 | 2006-10-01 | 2007-09-30 | 2005-08-23 | 2005-08-23 | 2005-09-23 | 2005-09-23
| 040.13058 | 040.OBO Mount Moriah Avenue | Install 100' 1 1/4" PE | 71.61 | 1656.01 | -261.98 | -15.82% | 0.008299% | 1394.03 | 1656.01 | -261.98 | 2006-10-01 | 2007-09-30 | 2006-07-05 | 2006-07-05 | 2006-09-22 | 2006-09-22
| 040.13118 | 040.B.G.LEE'S SQUARE REPLC. | 345 FT. OF 4" REPLC. LEE'S SQUARE - B.G. | 72.51 | 0 | 3993.86 | - | 0.02378% | 3993.86 | 0 | 3993.86 | 2006-10-01 | 2007-09-30 | 2006-09-13 | 2006-09-13 | 2007-09-13 | 2007-09-13
| 040.12929 | 040.MAD.2" MUELLER EQ. | PURCHASE 2" MUELLER EQUIPMENT | 78.8 | 44000 | 2625.4 | 5.967% | 0.2776% | 46625.4 | 44000 | 2625.4 | 2006-10-01 | 2007-09-30 | 2006-01-27 | 2006-01-27 | 2006-02-24 | 2006-02-24
| 040.13107 | 040.OBO.Recorders | Purchase 6 Electronic Recoerders | 86.63 | 13871.88 | 1717.96 | 12.38% | 0.09281% | 15589.84 | 13871.88 | 1717.96 | 2006-10-01 | 2007-09-30 | 2006-08-22 | 2006-08-22 | 2006-09-27 | 2006-09-27
| 040.13122 | 040.BGR.HOPK.OFFICE FUR. | OFFICE FURNITURE - VINDA PARKER - HOPKINSVILLE | 91.24 | 9366.83 | -1129.34 | -12.06% | 0.04904% | 8237.49 | 9366.83 | -1129.34 | 2006-10-01 | 2007-09-30 | 2006-09-22 | 2006-09-22 | 2007-09-22 | 2007-09-22
| 050.19603 | Princeton 08 Non Growth | Princeton 08 Non Growth | 99.72 | Not Budgeted | - | - | 1.428% | 239900.94 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 040.13102 | 040.BGR.EAGLESTONE VILLAS | 2180 FT.OF 2" PE - EAGLESTONE VILLAS - B.G. | 100.89 | 9900 | -4342.01 | -43.86% | 0.03309% | 5557.99 | 9900 | -4342.01 | 2006-10-01 | 2007-09-30 | 2006-08-16 | 2006-08-16 | 2006-12-29 | 2006-12-29
| 040.13067 | TCHSRV.MEA.EFM MUHL HOSP | EFM FOR MUHLENBERG COM HOSPITAL | 104.06 | 6276 | -1271.31 | -20.26% | 0.02979% | 5004.69 | 6276 | -1271.31 | 2006-10-01 | 2007-09-30 | 2006-07-21 | 2006-07-21 | 2006-09-28 | 2006-09-28
| 040.13068 | TCHSVC.MEA.EFM.JS STUART | EFM FOR JS STUART MED CENTER | 104.06 | 6276 | -1271.31 | -20.26% | 0.02979% | 5004.69 | 6276 | -1271.31 | 2006-10-01 | 2007-09-30 | 2006-07-21 | 2006-07-21 | 2006-09-28 | 2006-09-28
| 040.12831 | 040.MAD.2006 METER PROJECT | 2006 METER PURCHASE PROJECT FOR MADISONVILLE | 110.65 | 59323.52 | -12099.72 | -20.4% | 0.2811% | 47223.8 | 59323.52 | -12099.72 | 2006-10-01 | 2007-09-30 | 2005-11-22 | 2005-11-22 | 2006-09-28 | 2006-09-28
| 040.12590 | 040.OBO.MISC. EQUIPMENT | PE&STL. SQUEEZE OFF TOOLS,LINE LOCATORS | 114.47 | 48094.2 | 1549.55 | 3.222% | 0.2955% | 49643.75 | 48094.2 | 1549.55 | 2006-10-01 | 2007-09-30 | 2005-05-25 | 2005-05-25 | 2005-06-14 | 2005-06-14
| 040.13089 | 040.BGR.NORTHRIDGE IV-A | 2503 FT. OF 2" PE - NORTHRIDGE IV-A -- B.G. | 115 | 8734.11 | 545.74 | 6.248% | 0.05524% | 9279.85 | 8734.11 | 545.74 | 2006-10-01 | 2007-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 040.12785 | 040.DAN.3B 4 STEEL-IND PARK | INSTALL 800' OF 4" STEEL ON INDUSTRIAL DR IN THE HUNT INDUSTRIAL PARK FOR 3B COR | 117.74 | 21500 | 39943.1 | 185.8% | 0.3658% | 61443.1 | 21500 | 39943.1 | 2006-10-01 | 2007-09-30 | 2005-10-03 | 2005-10-03 | 2005-11-01 | 2005-11-01
| 040.12913 | AKY.TCSVS.MEAS.METERS | PURCHASE OF SPECIAL LARGE ROTARY METERS | 139.36 | 19689 | -868.84 | -4.413% | 0.112% | 18820.16 | 19689 | -868.84 | 2006-10-01 | 2007-09-30 | 2006-01-05 | 2006-01-05 | 2006-09-28 | 2006-09-28
| 040.12820 | 040.BGR.PARK HILL V - B | 2039 FT. OF 2" PE - PARK HILL V - B.G. | 158 | 9547 | -824 | -8.631% | 0.05193% | 8723 | 9547 | -824 | 2006-10-01 | 2007-09-30 | 2005-11-08 | 2005-11-08 | 2006-09-28 | 2006-09-28
| 040.13030 | 040.BGR.RUSS. THURSTON III | 1585 FT. OF 2" PE - THURSTON PROPERTIES - RUSS. | 161.58 | 4721 | -612.36 | -12.97% | 0.02446% | 4108.64 | 4721 | -612.36 | 2006-10-01 | 2007-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.13085 | 040.OBO. Lake Forrest Drive | Install 1,391' 2" PE | 165.01 | 12592.23 | -2872.63 | -22.81% | 0.05786% | 9719.6 | 12592.23 | -2872.63 | 2006-10-01 | 2007-09-30 | 2006-08-02 | 2006-08-02 | 2006-08-31 | 2006-08-31
| 040.12422 | 040.PAD.Perkins Creek Rev Ext | Seven new commercial lots being developed by Mike Falconite adjacent being devel | 168.92 | 4168.97 | 5157.85 | 123.7% | 0.05552% | 9326.82 | 4168.97 | 5157.85 | 2006-10-01 | 2007-09-30 | 2004-11-23 | 2004-11-23 | 2005-05-27 | 2005-05-27
| 050.18930 | 050.PAD.Retire Bldg - Palma | Demolish building at Palma Purchase | 174.69 | 12800.44 | -12625.75 | -98.64% | 0.00104% | 174.69 | 12800.44 | -12625.75 | 2006-10-01 | 2007-09-30 | 2007-02-07 | 2007-02-07 | 2008-02-07 | 2008-02-07
| 040.12830 | 040.OBO.2006 METER PROJECT | PROJECT FOR 2006 METER PURCHASES OWENSBORO | 220.76 | 129955.62 | -35737.64 | -27.5% | 0.5609% | 94217.98 | 129955.62 | -35737.64 | 2006-10-01 | 2007-09-30 | 2005-11-22 | 2005-11-22 | 2006-09-28 | 2006-09-28
| 040.12921 | 040.PAD.Odorant Contoller | Odorant Injector Controller | 227.05 | 4494.6 | 289.46 | 6.44% | 0.02848% | 4784.06 | 4494.6 | 289.46 | 2006-10-01 | 2007-09-30 | 2006-01-20 | 2006-01-20 | 2006-09-22 | 2006-09-22
| 050.18947 | 050.PAD.Elec Svc - Demolish | We are demolishing three station bldgs. we need to run some elect service. | 245.83 | 2432.15 | -2186.32 | -89.89% | 0.001463% | 245.83 | 2432.15 | -2186.32 | 2006-10-01 | 2007-09-30 | 2007-02-15 | 2007-02-15 | 2008-02-15 | 2008-02-15
| 040.12607 | 040.MAD.LAND O FROST | INSTALL6,360' 4" STL. | 281.56 | 305025.34 | -65943.38 | -21.62% | 1.423% | 239081.96 | 305025.34 | -65943.38 | 2006-10-01 | 2007-09-30 | 2005-06-10 | 2005-06-10 | 2005-10-20 | 2005-10-20
| 050.18582 | 050.2736.HOP.FT.CAMP.EXT. | 250 FT.- 2" PE - FT. CAMPBELL BLVD. - RITE-AIDD | 288.6 | 666 | -377.4 | -56.67% | 0.001718% | 288.6 | 666 | -377.4 | 2006-10-01 | 2007-09-30 | 2006-10-19 | 2006-10-19 | 2007-10-19 | 2007-10-19
| 040.13090 | 040.BGR.NORTHRIDGEIV-B | 4095 FT.OF 2" PE - NORTHRIDGEIV-B -- B.G. | 341.26 | 16037.5 | -1498.07 | -9.341% | 0.08655% | 14539.43 | 16037.5 | -1498.07 | 2006-10-01 | 2007-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 040.12835 | 040.MAY.'06 Meter Purchase | costs to purchase class 1 through class 4 meters for Mayfield | 401.65 | 58641.76 | -36517.25 | -62.27% | 0.1317% | 22124.51 | 58641.76 | -36517.25 | 2006-10-01 | 2007-09-30 | 2005-12-01 | 2005-12-01 | 2006-09-22 | 2006-09-22
| 040.13083 | 040.2739.TOWN AND COUNTRY XI | INSTALL 1500' OF 2" PE IN TOWN AND COUNTRY XI | 401.91 | 10750 | -7170.43 | -66.7% | 0.02131% | 3579.57 | 10750 | -7170.43 | 2006-10-01 | 2007-09-30 | 2006-07-25 | 2006-07-25 | 2007-07-25 | 2007-07-25
| 040.13049 | 040.2739.KNOBVIEW | INSTALL 1500' OF 2" PE AND 3 LS SERVICES ON KNOB STREET AND BYERS CT | 409.44 | 14100 | -965.45 | -6.847% | 0.07819% | 13134.55 | 14100 | -965.45 | 2006-10-01 | 2007-09-30 | 2006-06-27 | 2006-06-27 | 2007-06-27 | 2007-06-27
| 040.12818 | 040.BGR.PINE TERRACE 2" EXT. | 604 FT. OF 2" PE - PINE TERRACE - B.G. | 420.03 | 3234 | 3363.79 | 104% | 0.03928% | 6597.79 | 3234 | 3363.79 | 2006-10-01 | 2007-09-30 | 2005-11-08 | 2005-11-08 | 2006-09-28 | 2006-09-28
| 050.19604 | Owensboro 08 Growth | Owensboro 08 Growth | 422.77 | Not Budgeted | - | - | 3.335% | 560148.62 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 040.12766 | Hopkinsville 06 Growth | Hopkinsville 06 Growth | 432.94 | Not Budgeted | - | - | 0.8541% | 143466.49 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19322 | 050.BGR.FRK.BRICK ST EXT | 100 FT. OF 2' PE - BRICK ST - FRANKLIN | 443.02 | 3604 | -3163.16 | -87.77% | 0.002624% | 440.84 | 3604 | -3163.16 | 2006-10-01 | 2007-09-30 | 2007-07-06 | 2007-07-06 | 2008-07-05 | 2008-07-05
| 050.19432 | 2738.COX INTERIOR RETIREMENT | RETIRE 500' OF 4" PE AND 1 2" PE SERVICE | 465.12 | 1103 | -551.48 | -50% | 0.003283% | 551.52 | 1103 | -551.48 | 2006-10-01 | 2007-09-30 | 2007-08-21 | 2007-08-21 | 2007-12-01 | 2007-12-01
| 050.19349 | 050.3338.N 6th St Rev Ext | Install 300' - 2" PE for Union City Grain on N 6th Street | 470.52 | 1799.81 | 179.46 | 9.971% | 0.01178% | 1979.27 | 1799.81 | 179.46 | 2006-10-01 | 2007-09-30 | 2007-07-16 | 2007-07-16 | 2008-07-16 | 2008-07-16
| 040.13092 | 040.BGR.800 BLK. WAKEFIELD | 310 FT. OF 4"PE -800 BLK WAKEFIELD REPLC - B.G. | 531.35 | 13496.31 | -2376.87 | -17.61% | 0.06619% | 11119.44 | 13496.31 | -2376.87 | 2006-10-01 | 2007-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 050.18604 | 050.OBO.Highland Pointe Dr. | Retire 308' 2" PE | 612.82 | 607.11 | 5.71 | 0.9405% | 0.003648% | 612.82 | 607.11 | 5.71 | 2006-10-01 | 2007-09-30 | 2006-10-24 | 2006-10-24 | 2006-11-24 | 2006-11-24
| 050.19429 | 2739.TAYLORSVILLE ROAD 3RD | PROJECT FOR REPAIR OF DAMAGED HP LINE | 637.47 | 14703 | -14058 | -95.61% | 0.00384% | 645 | 14703 | -14058 | 2006-10-01 | 2007-09-30 | 2007-08-20 | 2007-08-20 | 2007-11-01 | 2007-11-01
| 040.13022 | 040.PAD.Warehouse Improve II | Warehouse Improvements II incl ceiling, blinds, rear door, office furniture, ref | 668.02 | 28490 | 46071.31 | 161.7% | 0.4439% | 74561.31 | 28490 | 46071.31 | 2006-10-01 | 2007-09-30 | 2006-04-25 | 2006-04-25 | 2006-09-22 | 2006-09-22
| 040.13108 | 040.BGR.HWY31-W RELOC.B.G. | 6" HP RELOC. - HYW 31-W - B.G. PIPE ONLY | 774.31 | 32796.04 | 9856.71 | 30.05% | 0.2539% | 42652.75 | 32796.04 | 9856.71 | 2006-10-01 | 2007-09-30 | 2006-08-25 | 2006-08-25 | 2006-12-29 | 2006-12-29
| 040.12822 | AKY.TCSVC.MEAS.OUTSOURCER | Outsourcing of Meter repair for 2006 PC Year | 775.48 | 67200 | 108977.55 | 162.2% | 1.049% | 176177.55 | 67200 | 108977.55 | 2006-10-01 | 2007-09-30 | 2005-11-14 | 2005-11-14 | 2006-09-28 | 2006-09-28
| 040.12277 | 040.Sto Bushhog Purchase | Purchase 2 Bushhogs | 785 | 15463 | -15463 | -100% | 0.09851% | 16547.79 | 15463 | 1084.79 | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 040.12910 | 040.BGR.CEMETERY RD @ FOUNTAIN | 1100 FT.OF 4" PE - CEMETERY RD. @ FOUNTAIN TRACE - B.G. | 800.73 | 11939 | 3268 | 27.37% | 0.09053% | 15207 | 11939 | 3268 | 2006-10-01 | 2007-09-30 | 2005-12-29 | 2005-12-29 | 2006-09-28 | 2006-09-28
| 050.19674 | 050.3338.Squeeze-Off | purchase 1/2" - 2" squeeze-off tool for use in Union City | 815.43 | 897.62 | 2520.43 | 280.8% | 0.02035% | 3418.05 | 897.62 | 2520.43 | 2006-10-01 | 2007-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 050.19338 | 050.2637.Holt Rd Rev Ext | Install 330' 2" PE for one new commercial customer (Paducah Fed Credit Union) | 865.45 | 1779 | 663.27 | 37.28% | 0.01454% | 2442.27 | 1779 | 663.27 | 2006-10-01 | 2007-09-30 | 2007-07-11 | 2007-07-11 | 2008-07-11 | 2008-07-11
| 050.18630 | 050.MAD. Wendall Ford | Install 1,300' 2" PE | 971.06 | 0 | 971.06 | - | 0.005781% | 971.06 | 0 | 971.06 | 2006-10-01 | 2007-09-30 | 2006-10-30 | 2006-10-30 | 2007-01-31 | 2007-01-31
| 040.13056 | 040.PAD.Odorizer Awning | Awnings will cover odorizers to keep direct sunshine off odorizers | 1036.1 | 5622.32 | -773.3 | -13.75% | 0.02887% | 4849.02 | 5622.32 | -773.3 | 2006-10-01 | 2007-09-30 | 2006-06-29 | 2006-06-29 | 2006-09-22 | 2006-09-22
| 050.18697 | 050.2738.JACKSON RETIREMENT | FINISH RETIRING ITEMS AND PAYUMENTS FOR BARE STEEL REPLACEMENT | 1046.33 | 7800 | -6753.67 | -86.59% | 0.006229% | 1046.33 | 7800 | -6753.67 | 2006-10-01 | 2007-09-30 | 2006-11-27 | 2006-11-27 | 2007-12-01 | 2007-12-01
| 050.19340 | 050.2634.locator | Purchase Pipeline Locator | 1100.87 | 1390.68 | -289.81 | -20.84% | 0.006553% | 1100.87 | 1390.68 | -289.81 | 2006-10-01 | 2007-09-30 | 2007-07-12 | 2007-07-12 | 2007-09-14 | 2007-09-14
| 050.18623 | 050.PTON.Pheonix dr Rev Ext | Install 80' - 2" PE for one new commercial customer | 1115.44 | 1282.67 | -167.23 | -13.04% | 0.00664% | 1115.44 | 1282.67 | -167.23 | 2006-10-01 | 2007-09-30 | 2006-10-27 | 2006-10-27 | 2007-10-27 | 2007-10-27
| 040.13044 | 040.BGR.14TH ST. RELOCATION | 14TH ST. RELOCATION FROM COLLEGE TO KENTUCKY - B.G. | 1145.4 | 0 | 11051.06 | - | 0.06579% | 11051.06 | 0 | 11051.06 | 2006-10-01 | 2007-09-30 | 2006-06-20 | 2006-06-20 | 2006-09-28 | 2006-09-28
| 040.13063 | 040.PAD.Brookhaven II | Brookhaven subd. phase II 3,005' for 26 new residential lots | 1193.57 | 12480 | 409.18 | 3.279% | 0.07673% | 12889.18 | 12480 | 409.18 | 2006-10-01 | 2007-09-30 | 2006-07-18 | 2006-07-18 | 2006-09-22 | 2006-09-22
| 040.11419 | WKG.PAD.Olivet Ch Rd Relocate | (Phase I) 8" T'Line | 1306.21 | 0 | -414.81 | - | -0.002469% | -414.81 | 0 | -414.81 | 2006-10-01 | 2007-09-30 | 2005-09-23 | 2005-09-23 | 2005-09-23 | 2005-09-23
| 040.13095 | 040.PAD.Industrial Parkway Ext | Install 110' - 2" PE for new commercial duplex | 1421.15 | 1643.55 | -222.4 | -13.53% | 0.00846% | 1421.15 | 1643.55 | -222.4 | 2006-10-01 | 2007-09-30 | 2006-08-14 | 2006-08-14 | 2006-09-22 | 2006-09-22
| 050.19153 | PARK CITY IND. PK 2" PE EXT | 450' OF 2" PE - PARK CITY INDUSTRIAL PARK | 1472.49 | 404.29 | -208.14 | -51.48% | 0.001168% | 196.15 | 404.29 | -208.14 | 2006-10-01 | 2007-09-30 | 2007-04-27 | 2007-04-27 | 2008-04-27 | 2008-04-27
| 050.19386 | 050.2635.T.B 1 Reg Replace | Replace the 4 existing regulators w/ 4 new 2" Fisher EZR's | 1517.64 | 14328.64 | -5935.94 | -41.43% | 0.04996% | 8392.7 | 14328.64 | -5935.94 | 2006-10-01 | 2007-09-30 | 2007-08-02 | 2007-08-02 | 2008-08-01 | 2008-08-01
| 040.12775 | Madisonville 06 Non Growth | Madisonville 06 Non Growth | 1531.04 | Not Budgeted | - | - | 3.333% | 559886.75 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12782 | Mayfield 06 Growth | Mayfield 06 Growth | 1619.36 | Not Budgeted | - | - | 0.7079% | 118922.55 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.18885 | 2739.CARDINAL OAKS 2a | INSTALL 600' FOR 8 PATIO HOMES CARDINAL OAKS | 1632.95 | 2070 | -395 | -19.08% | 0.009971% | 1675 | 2070 | -395 | 2006-10-01 | 2007-09-30 | 2007-01-24 | 2007-01-24 | 2008-02-01 | 2008-02-01
| 040.13084 | 040.STO Marker Posts | Installation of additional R-O-W markers | 1686.96 | 29766 | -2030.64 | -6.822% | 0.1651% | 27735.36 | 29766 | -2030.64 | 2006-10-01 | 2007-09-30 | 2006-07-27 | 2006-07-27 | 2006-09-28 | 2006-09-28
| 050.18579 | 050.OBO.Village Run | Install 318' 2"PE | 1726.28 | 2562.67 | -836.39 | -32.64% | 0.01028% | 1726.28 | 2562.67 | -836.39 | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2006-12-01 | 2006-12-01
| 050.19286 | 050.2636.Sutherland Rd. | Install 100' 2" PE | 1841.8 | 1607.66 | 224.3 | 13.95% | 0.01091% | 1831.96 | 1607.66 | 224.3 | 2006-10-01 | 2007-09-30 | 2007-06-25 | 2007-06-25 | 2007-08-17 | 2007-08-17
| 050.18902 | 050.OBO.Lake Forrest 2 | Install 292' 2" PE | 1843.17 | 1589.33 | 253.84 | 15.97% | 0.01097% | 1843.17 | 1589.33 | 253.84 | 2006-10-01 | 2007-09-30 | 2007-01-30 | 2007-01-30 | 2007-05-31 | 2007-05-31
| 050.19192 | 050.2636.Earl Russell Court 1 | Install 202' 2" PE | 1915.38 | 1892.66 | 17.89 | 0.9452% | 0.01137% | 1910.55 | 1892.66 | 17.89 | 2006-10-01 | 2007-09-30 | 2007-05-09 | 2007-05-09 | 2007-08-31 | 2007-08-31
| 050.19162 | 050.2609.STO Tilt Trailer | Purchase Tilt Trailer for St. Charles | 1953.88 | 1699.72 | 254.16 | 14.95% | 0.01163% | 1953.88 | 1699.72 | 254.16 | 2006-10-01 | 2007-09-30 | 2007-04-30 | 2007-04-30 | 2007-09-28 | 2007-09-28
| 040.13026 | 040.2739.BRIDLEWOOD SEC I | INSTALL 2800' OF 2" PE AND REG STATION | 1985.23 | 37255 | 13211.02 | 35.46% | 0.3004% | 50466.02 | 37255 | 13211.02 | 2006-10-01 | 2007-09-30 | 2006-05-10 | 2006-05-10 | 2006-09-28 | 2006-09-28
| 040.12901 | 040.2737.HAR.DON YATES | INSTALL 550' OF 2" PE FOR DON YATES OFF SPARROW LANE FOR NEW COMMERICAL LAND | 2044.48 | 9475 | -7430.52 | -78.42% | 0.01217% | 2044.48 | 9475 | -7430.52 | 2006-10-01 | 2007-09-30 | 2005-12-20 | 2005-12-20 | 2006-02-01 | 2006-02-01
| 050.19065 | 050.2634.Princeton Rd. Ret. | Retire 4" & 2" main | 2048.43 | 2190.54 | -142.11 | -6.487% | 0.01219% | 2048.43 | 2190.54 | -142.11 | 2006-10-01 | 2007-09-30 | 2007-04-05 | 2007-04-05 | 2007-07-27 | 2007-07-27
| 050.19098 | 050.2634.Hawkins St. Retire | Retire 633' 2" Stl. | 2068.97 | 1637.39 | 431.58 | 26.36% | 0.01232% | 2068.97 | 1637.39 | 431.58 | 2006-10-01 | 2007-09-30 | 2007-04-26 | 2007-04-26 | 2007-06-29 | 2007-06-29
| 050.18869 | 050.Sto. Overhead Door | Replace overhead door at the Storage Whse | 2110.47 | 1630 | 480.47 | 29.48% | 0.01256% | 2110.47 | 1630 | 480.47 | 2006-10-01 | 2007-09-30 | 2007-01-17 | 2007-01-17 | 2007-04-30 | 2007-04-30
| 040.12781 | Paducah 06 Non Growth | Paducah 06 Non Growth | 2162.35 | Not Budgeted | - | - | 2.379% | 399553.28 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.18692 | 050.PAD.Orchard Ln Ext | 260' - 2" PE main extension for one new residential customer (Noonan) | 2185.23 | 1904.16 | 281.07 | 14.76% | 0.01301% | 2185.23 | 1904.16 | 281.07 | 2006-10-01 | 2007-09-30 | 2006-11-27 | 2006-11-27 | 2007-11-27 | 2007-11-27
| 050.19296 | 050.2637.C.G.I - Bridges | New CGI for Mike Bridges, corrosion tech | 2220.38 | 2150.91 | 222.82 | 10.36% | 0.01413% | 2373.73 | 2150.91 | 222.82 | 2006-10-01 | 2007-09-30 | 2007-06-28 | 2007-06-28 | 2008-06-26 | 2008-06-26
| 050.18714 | 050.BGR.HOP.DAIRY QUEEN | 500 FYT. OF 2" PE - DAIRY QUEEN - HOPK. | 2358.76 | 1242 | 1116.76 | 89.92% | 0.01404% | 2358.76 | 1242 | 1116.76 | 2006-10-01 | 2007-09-30 | 2006-12-05 | 2006-12-05 | 2007-12-05 | 2007-12-05
| 040.12837 | 040.PAD.'06 Meter Purchases | project to purchase class 1 through class 4 meters for FY 2006 | 2426.72 | 96960.75 | 19754.83 | 20.37% | 0.6948% | 116715.58 | 96960.75 | 19754.83 | 2006-10-01 | 2007-09-30 | 2005-12-01 | 2005-12-01 | 2006-09-22 | 2006-09-22
| 040.12780 | Paducah 06 Growth | Paducah 06 Growth | 2437.69 | Not Budgeted | - | - | 2.772% | 465570.11 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.18627 | EFM for B.G. Med Cen Laundry | EFM fro Bowling Green Medical Center Laundry | 2483.73 | 2782 | -298.27 | -10.72% | 0.01479% | 2483.73 | 2782 | -298.27 | 2006-10-01 | 2007-09-30 | 2006-10-30 | 2006-10-30 | 2007-02-01 | 2007-02-01
| 050.19287 | 050.2636.Nicholas Dr. | Install 295' 2" PE | 2494.95 | 3773.5 | -1285.44 | -34.06% | 0.01481% | 2488.06 | 3773.5 | -1285.44 | 2006-10-01 | 2007-09-30 | 2007-06-25 | 2007-06-25 | 2007-08-24 | 2007-08-24
| 040.12777 | Princeton 06 Non Growth | Princeton 06 Non Growth | 2503.56 | Not Budgeted | - | - | 1.74% | 292267.41 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.18921 | 050.OBO. Vincent Station Rd. 4 | Install 100' 2" PE | 2520.99 | 1749.77 | 771.22 | 44.08% | 0.01501% | 2520.99 | 1749.77 | 771.22 | 2006-10-01 | 2007-09-30 | 2007-02-05 | 2007-02-05 | 2007-08-31 | 2007-08-31
| 040.12772 | Shelbyville 06 Growth | Shelbyville 06 Growth | 2549.66 | Not Budgeted | - | - | 4.11% | 690488.77 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19316 | 050.BGR.MCLELLAN FARMS II | 1860 FT. OF 2" PE - MCLELLANS FARMS II - B.G. | 2570.28 | 6361 | -3804.61 | -59.81% | 0.01522% | 2556.39 | 6361 | -3804.61 | 2006-10-01 | 2007-09-30 | 2007-07-06 | 2007-07-06 | 2008-07-05 | 2008-07-05
| 050.18970 | 050.2609.BON HARBOR BUILDING | INSTALL NEW BUILDING AT BON HARBOR | 2603.59 | 23100 | -19835.35 | -85.87% | 0.01943% | 3264.65 | 23100 | -19835.35 | 2006-10-01 | 2007-09-30 | 2007-03-02 | 2007-03-02 | 2008-03-01 | 2008-03-01
| 050.19031 | 050.PAD.Starlite Subd Rev Ext | Install 1,480' - 2" PE for nine new commercial lots | 2728.7 | 4572 | 1210.39 | 26.47% | 0.03442% | 5782.39 | 4572 | 1210.39 | 2006-10-01 | 2007-09-30 | 2007-03-27 | 2007-03-27 | 2008-03-21 | 2008-03-21
| 050.19068 | 050.2738.SPRF.BALLARD RELOCATE | RELOCATE 250' OF 4" STEEL ON BALLARD ST SPRINGFIELD | 2829.57 | 11020 | -14718.14 | -133.6% | -0.02202% | -3698.14 | 11020 | -14718.14 | 2006-10-01 | 2007-09-30 | 2007-04-09 | 2007-04-09 | 2008-04-04 | 2008-04-04
| 050.19417 | 050.2636 Fountain View Ct. | Install 524' 2" PE | 2928.03 | 3341.18 | -426.3 | -12.76% | 0.01735% | 2914.88 | 3341.18 | -426.3 | 2006-10-01 | 2007-09-30 | 2007-08-16 | 2007-08-16 | 2007-08-31 | 2007-08-31
| 050.18927 | 050.OBO. Digital Voltmeters | Purchase 4 Tinker & Rasor Digital Voltmeters & accessories | 2983.88 | 2595.93 | 387.95 | 14.94% | 0.01776% | 2983.88 | 2595.93 | 387.95 | 2006-10-01 | 2007-09-30 | 2007-02-06 | 2007-02-06 | 2007-05-31 | 2007-05-31
| 050.18904 | 050.BGR.SCNDLE WOOD SUITES | 690 FT. OF 2' PE - CANDLEWOOD SUITES - WALL ST. - B.G. | 3034.74 | 400 | 2634.74 | 658.7% | 0.01807% | 3034.74 | 400 | 2634.74 | 2006-10-01 | 2007-09-30 | 2007-01-31 | 2007-01-31 | 2008-01-31 | 2008-01-31
| 050.19344 | 050.2635.Depot St Retire | Abandon 380' - 2" steel pipe | 3137.97 | 2196.17 | 1177.15 | 53.6% | 0.02008% | 3373.32 | 2196.17 | 1177.15 | 2006-10-01 | 2007-09-30 | 2007-07-13 | 2007-07-13 | 2008-07-11 | 2008-07-11
| 050.19008 | 050.BGR.B.G.CHAMBER RELOC | 790 FT. OF 2" PE - B.G. CHAMBER RELOC. | 3138.78 | 7008 | -3875.99 | -55.31% | 0.01864% | 3132.01 | 7008 | -3875.99 | 2006-10-01 | 2007-09-30 | 2007-03-15 | 2007-03-15 | 2008-03-15 | 2008-03-15
| 050.18710 | 050.MAY.Chariot Cr Rev Ext | Install 370' - 2" PE for four new vacant residential lots plus one new home nearly completed | 3161.24 | 2689.26 | 471.98 | 17.55% | 0.01882% | 3161.24 | 2689.26 | 471.98 | 2006-10-01 | 2007-09-30 | 2006-12-01 | 2006-12-01 | 2007-12-01 | 2007-12-01
| 050.18867 | TCHSVR.MEA.EFM.JEWISH HOSP | EFM FOR JEWISH HOSPITAL IN SHELBYVILLE | 3178.62 | 2782 | 396.62 | 14.26% | 0.01892% | 3178.62 | 2782 | 396.62 | 2006-10-01 | 2007-09-30 | 2007-01-17 | 2007-01-17 | 2007-04-30 | 2007-04-30
| 050.19276 | 050.2636.Days Inn | Install 330' 2" PE | 3223.98 | 2280.14 | 929.93 | 40.78% | 0.01911% | 3210.07 | 2280.14 | 929.93 | 2006-10-01 | 2007-09-30 | 2007-06-19 | 2007-06-19 | 2007-08-23 | 2007-08-23
| 050.18562 | 050.OBO.Paddock Pointe Cove | Install 368' 2" PE | 3232.98 | 3437.97 | -204.99 | -5.963% | 0.01925% | 3232.98 | 3437.97 | -204.99 | 2006-10-01 | 2007-09-30 | 2006-10-18 | 2006-10-18 | 2007-01-26 | 2007-01-26
| 050.19345 | EFM.Taylor Co Hospital | EFM for Taylor County Hospital in Campbellville | 3236.17 | 4714 | -1419.6 | -30.11% | 0.01961% | 3294.4 | 4714 | -1419.6 | 2006-10-01 | 2007-09-30 | 2007-07-16 | 2007-07-16 | 2007-09-30 | 2007-09-30
| 050.19346 | EFM. T Marzetti Company | EFM for T. Marzetti Company in Horse Cave | 3236.17 | 4714 | -3780.1 | -80.19% | 0.00556% | 933.9 | 4714 | -3780.1 | 2006-10-01 | 2007-09-30 | 2007-07-16 | 2007-07-16 | 2007-09-30 | 2007-09-30
| 050.19079 | 050.2634.Pipeline locator | Purchase Rycom Pipeline Locator | 3293.12 | 4017.52 | -724.4 | -18.03% | 0.0196% | 3293.12 | 4017.52 | -724.4 | 2006-10-01 | 2007-09-30 | 2007-04-13 | 2007-04-13 | 2007-07-27 | 2007-07-27
| 050.19033 | 050.MAY.Fountainhead Subd | Rev Ext - 5,480' - 2" PE | 3362.64 | 21756.45 | 13176.64 | 60.56% | 0.208% | 34933.09 | 21756.45 | 13176.64 | 2006-10-01 | 2007-09-30 | 2007-03-27 | 2007-03-27 | 2008-03-21 | 2008-03-21
| 050.18961 | TECHSVR.MEA.EFM.W. BAPT HOSP | EFM FOR WESTERN BAPTIST HOSPITAL IN PADUCAH | 3433.48 | 3860 | -426.52 | -11.05% | 0.02044% | 3433.48 | 3860 | -426.52 | 2006-10-01 | 2007-09-30 | 2007-02-26 | 2007-02-26 | 2007-09-30 | 2007-09-30
| 040.13104 | 040.Mike Smith Toyota Rev Ext | Install 855' - 2" PE for three new commercial lots located just off Coleman Rd | 3478.3 | 3438.18 | 40.12 | 1.167% | 0.02071% | 3478.3 | 3438.18 | 40.12 | 2006-10-01 | 2007-09-30 | 2006-08-17 | 2006-08-17 | 2006-09-22 | 2006-09-22
| 040.13045 | 040.PTON.Washington St Replace | In alley behind Washington Street install 310' - 2" PE; retire 315' - 2" | 3485.4 | 13355.49 | -7790.44 | -58.33% | 0.03313% | 5565.05 | 13355.49 | -7790.44 | 2006-10-01 | 2007-09-30 | 2006-06-21 | 2006-06-21 | 2006-09-22 | 2006-09-22
| 050.18709 | 050.2739.MIDLAND RETIRE | RETIRE 850' ON MIDLAND INDUSTRIAL DRIVE FOR HWY BYPASS | 3486.31 | 7020 | -3287.33 | -46.83% | 0.02222% | 3732.67 | 7020 | -3287.33 | 2006-10-01 | 2007-09-30 | 2006-12-01 | 2006-12-01 | 2007-06-09 | 2007-06-09
| 050.18922 | 050.OBO.Highland Pointe 1 | Install 1,369' 2" PE | 3614.95 | 0 | 3614.95 | - | 0.02152% | 3614.95 | -2.2737e-13 | 3614.95 | 2006-10-01 | 2007-09-30 | 2007-02-05 | 2007-02-05 | 2007-07-27 | 2007-07-27
| 050.19254 | 2739.PHEASANT GLEN PH I | INSTALL 2" PE IN PHEASANT GLEN OFF BRASSFIELD RD | 3625.42 | 7780 | -1894.52 | -24.35% | 0.03504% | 5885.48 | 7780 | -1894.52 | 2006-10-01 | 2007-09-30 | 2007-06-06 | 2007-06-06 | 2008-06-06 | 2008-06-06
| 040.12771 | Campbellsville 06 Non Growth | Campbellsville 06 Non Growth | 3647.51 | Not Budgeted | - | - | 2.746% | 461237.48 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.18705 | KY.MEA.EFM.INGERSOLL RAND | EFM FOR INGERSOLL RAND IN CAMPBELLSVILL | 3659.48 | 2782 | 877.48 | 31.54% | 0.02178% | 3659.48 | 2782 | 877.48 | 2006-10-01 | 2007-09-30 | 2006-11-30 | 2006-11-30 | 2007-11-30 | 2007-11-30
| 040.13120 | 040.BGR.MCLELLAN FARMS | 2520 FT-2' & 1959' - 4" - MSLELLEN FARMS - B.G. | 3659.63 | 30749.84 | -7133.25 | -23.2% | 0.1406% | 23616.59 | 30749.84 | -7133.25 | 2006-10-01 | 2007-09-30 | 2006-09-13 | 2006-09-13 | 2007-09-13 | 2007-09-13
| 050.18882 | TCHSVR.MEA.EFM.YKK SNAP FASTEN | EFM FOR YKK SNAP FASTENERS-LAWENCEBURG, KY | 3678.4 | 3689 | -10.6 | -0.2873% | 0.0219% | 3678.4 | 3689 | -10.6 | 2006-10-01 | 2007-09-30 | 2007-01-22 | 2007-01-22 | 2007-09-30 | 2007-09-30
| 050.19496 | 050.BGR.ELKTON ODORANT TANK | REPLACE ODORANT TANK - ELKTON PURCHASE | 3727.64 | 0 | 7583.67 | - | 0.04515% | 7583.67 | 0 | 7583.67 | 2006-10-01 | 2007-09-30 | 2007-08-28 | 2007-08-28 | 2008-08-28 | 2008-08-28
| 050.19272 | 050.BGR.RETIRE REG. STA.-US31W | RETIRE LP REG STA - US31W - BGMU WATER PLANT | 3787.91 | 8120 | -3492.39 | -43.01% | 0.02755% | 4627.61 | 8120 | -3492.39 | 2006-10-01 | 2007-09-30 | 2007-06-19 | 2007-06-19 | 2008-06-19 | 2008-06-19
| 040.13096 | 040.MAY.Northside Subd Ext | Install 1,965' - 2" PE for 18 commercial lots. Developer is Nathan Sholar | 3805.18 | 8106.9 | 1440.55 | 17.77% | 0.05684% | 9547.45 | 8106.9 | 1440.55 | 2006-10-01 | 2007-09-30 | 2006-08-15 | 2006-08-15 | 2006-09-22 | 2006-09-22
| 050.19679 | 050.3374.Pipe Locator | Purchase Ditch Witch pipe locator for use in the Sikeston area | 3818.67 | 2768.62 | 1050.05 | 37.93% | 0.02273% | 3818.67 | 2768.62 | 1050.05 | 2006-10-01 | 2007-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 050.19015 | 050.OBO.Fulton Dr. | Install 100' 2" PE | 3879.97 | 1873.52 | 2006.45 | 107.1% | 0.0231% | 3879.97 | 1873.52 | 2006.45 | 2006-10-01 | 2007-09-30 | 2007-03-19 | 2007-03-19 | 2007-07-27 | 2007-07-27
| 050.18895 | 050.BGR.HOP.CHAMBERS CT. EXT. | 700 FT OF 2" PE - CHAMBERS CT. - HOPKINSVILLE | 3961.53 | 5157 | -1207.95 | -23.42% | 0.02351% | 3949.05 | 5157 | -1207.95 | 2006-10-01 | 2007-09-30 | 2007-01-29 | 2007-01-29 | 2008-01-29 | 2008-01-29
| 040.12778 | Owensboro 06 Growth | Owensboro 06 Growth | 4131.41 | Not Budgeted | - | - | 3.975% | 667756.84 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19677 | 050.3374.Odorator | Purchase DTEX Odorator for use in Sikeston area | 4209.61 | 3257.2 | 1405.64 | 43.15% | 0.02776% | 4662.84 | 3257.2 | 1405.64 | 2006-10-01 | 2007-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 040.12783 | Mayfield 06 Non Growth | Mayfield 06 Non Growth | 4249.57 | Not Budgeted | - | - | 1.812% | 304302.05 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19315 | 050.BGR.CUMBERLAND RIDGE IV | 2295 FT, OF 2" PE - CUMBERLAND RIDGE IV | 4291.45 | 8305 | -4036.81 | -48.61% | 0.02541% | 4268.19 | 8305 | -4036.81 | 2006-10-01 | 2007-09-30 | 2007-07-06 | 2007-07-06 | 2008-07-05 | 2008-07-05
| 050.19433 | EFM.IL Transportation Cust. | EFM for IL. Honeywell, Lafarge, & Thermic | 4633.18 | 7231 | -2455.16 | -33.95% | 0.02843% | 4775.84 | 7231 | -2455.16 | 2006-10-01 | 2007-09-30 | 2007-08-21 | 2007-08-21 | 2007-11-30 | 2007-11-30
| 050.19675 | 050.3376.C.G.I's | 2 CGI's for use in Malden area | 4640.58 | 4415.88 | 494.87 | 11.21% | 0.02923% | 4910.75 | 4415.88 | 494.87 | 2006-10-01 | 2007-09-30 | 2007-10-01 | 2007-10-01 | 2008-09-26 | 2008-09-26
| 050.18788 | 050.2737.BLUEGRASS STOCKYARD | INSTALL 1500' OF 2" PE FOR BLUEGRASS STOCKYARD - STANFORD | 4713.89 | 766 | 3947.89 | 515.4% | 0.02806% | 4713.89 | 766 | 3947.89 | 2006-10-01 | 2007-09-30 | 2006-12-28 | 2006-12-28 | 2007-12-01 | 2007-12-01
| 040.12767 | Hopkinsville 06 Non Growth | Hopkinsville 06 Non Growth | 4718.3 | Not Budgeted | - | - | 3.067% | 515205.3 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19605 | Owensboro 08 Non Growth | Owensboro 08 Non Growth | 4742.61 | Not Budgeted | - | - | 8.78% | 1474828.56 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2007-09-18 | 2007-09-18 | 2008-10-31 | 2008-10-31
| 050.19399 | 050.3345.Front St Relocation | Replace 400' - 2" PE. City of Metropolis improving Front Strret, small amount of 2" PE is affected. | 4839.27 | 3777.71 | 1050.7 | 27.81% | 0.02874% | 4828.41 | 3777.71 | 1050.7 | 2006-10-01 | 2007-09-30 | 2007-08-03 | 2007-08-03 | 2008-08-01 | 2008-08-01
| 050.18979 | TCHSVR.MEA.EFM.KYCOOPERAGE | EFM FOR KENTUCKY COOPERAGE | 4845.95 | 3860 | 985.95 | 25.54% | 0.02885% | 4845.95 | 3860 | 985.95 | 2006-10-01 | 2007-09-30 | 2007-03-05 | 2007-03-05 | 2007-09-30 | 2007-09-30
| 040.12765 | Glasgow 06 Non Growth | Glasgow 06 Non Growth | 5044.05 | Not Budgeted | - | - | 3.951% | 663699.29 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2009-05-13 | 2009-05-13
| 040.13032 | 040.2737.COLONIAL WAY | INSTALL 1750' OF 2" PE ON POPPY COURT, GRABRUK AND COLONIAL WAY | 5118.03 | 7500 | -1418.15 | -18.91% | 0.03621% | 6081.85 | 7500 | -1418.15 | 2006-10-01 | 2007-09-30 | 2006-05-23 | 2006-05-23 | 2006-09-28 | 2006-09-28
| 050.19664 | 050.BGR.GLS. PIPE LOCATORS | 4 - PIPE LOCATORS - GLASGOW | 5304.42 | 5098 | 206.42 | 4.049% | 0.03158% | 5304.42 | 5098 | 206.42 | 2006-10-01 | 2007-09-30 | 2007-09-28 | 2007-09-28 | 2008-09-28 | 2008-09-28
| 050.18606 | 050.PAD.Olivet Ch Rd Relocate | Relocate 580' - 2" PE | 5374.63 | 4208.29 | 1166.34 | 27.72% | 0.032% | 5374.63 | 4208.29 | 1166.34 | 2006-10-01 | 2007-09-30 | 2006-10-24 | 2006-10-24 | 2007-10-24 | 2007-10-24
| 050.18929 | 050.PAD.Reg Replace Jim Smith | replace 2" jetstream w/2" Mooney at Jim Smith Contractors | 5408.04 | 2608.3 | 2799.74 | 107.3% | 0.03219% | 5408.04 | 2608.3 | 2799.74 | 2006-10-01 | 2007-09-30 | 2007-02-07 | 2007-02-07 | 2007-09-28 | 2007-09-28
| 050.19384 | 050.2636.Mobile Survey Eq. | Purchase additional equipment needed for mobile surveying. | 5438.44 | 5196.51 | 241.93 | 4.656% | 0.03238% | 5438.44 | 5196.51 | 241.93 | 2006-10-01 | 2007-09-30 | 2007-08-01 | 2007-08-01 | 2007-09-27 | 2007-09-27
| 040.12769 | Danville 06 Non Growth | Danville 06 Non Growth | 5471.29 | Not Budgeted | - | - | 2.836% | 476385.22 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12362 | Danville 05 Growth | Danville 05 Growth | 5581.79 | Not Budgeted | - | - | 1.732% | 290919.06 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 050.19535 | 050.3345. Pipe Locators (2) | 2 Rycom pipe locators for use in Metropolis, IL | 5619.66 | 5851.04 | 290.43 | 4.964% | 0.03656% | 6141.47 | 5851.04 | 290.43 | 2006-10-01 | 2007-09-30 | 2007-09-18 | 2007-09-18 | 2008-09-17 | 2008-09-17
| 050.18786 | 050.MAD.2" Squeeze Off Tool | Purchase 2" Squeeze off Tool | 5635.8 | 4003.61 | 1632.19 | 40.77% | 0.03355% | 5635.8 | 4003.61 | 1632.19 | 2006-10-01 | 2007-09-30 | 2006-12-21 | 2006-12-21 | 2007-02-28 | 2007-02-28
| 040.12842 | AKY.TCSVC.MEAS.ROTARY METERS | PURCHASE OF DRESSER METERS | 5645.41 | 24188 | 563.02 | 2.328% | 0.1473% | 24751.02 | 24188 | 563.02 | 2006-10-01 | 2007-09-30 | 2005-12-09 | 2005-12-09 | 2006-09-28 | 2006-09-28
| 050.19530 | 050.BGR.SPRINGFIELD BLVD 4" | 1150 FT. OF 4" PE EXT. - SPRINGFIELD BLVD - B.G. | 5658.15 | 7416 | 3257.92 | 43.93% | 0.06354% | 10673.92 | 7416 | 3257.92 | 2006-10-01 | 2007-09-30 | 2007-09-12 | 2007-09-12 | 2008-09-12 | 2008-09-12
| 050.19624 | 050.2637.Pipe locators | Purchase 2 pipe locators for use in Paducah | 5681.47 | 5230.51 | 843.32 | 16.12% | 0.03616% | 6073.83 | 5230.51 | 843.32 | 2006-10-01 | 2007-09-30 | 2007-09-24 | 2007-09-24 | 2008-09-26 | 2008-09-26
| 050.19314 | 050.2634.Liberty Church Sta. | Upgrade Reg. Station | 5762.11 | 7333.02 | 172.17 | 2.348% | 0.04468% | 7505.19 | 7333.02 | 172.17 | 2006-10-01 | 2007-09-30 | 2007-07-05 | 2007-07-05 | 2007-09-28 | 2007-09-28
| 050.19269 | 050.BGR.FRK.DAVIS DR. 2" EXT | 900 FT. OF 2' STL. EXT. - DAVIS DR. - FRANKLIN | 5981.45 | 3874 | -3660.41 | -94.49% | 0.001272% | 213.59 | 3874 | -3660.41 | 2006-10-01 | 2007-09-30 | 2007-06-14 | 2007-06-14 | 2008-06-14 | 2008-06-14
| 050.18599 | 050.2739.HI PONIT PH II | INSTALL 800' OF 4" PE FOR HI POINT INDUST PH II | 6023.72 | 10150 | -1865.24 | -18.38% | 0.04932% | 8284.76 | 10150 | -1865.24 | 2006-10-01 | 2007-09-30 | 2006-10-23 | 2006-10-23 | 2007-10-23 | 2007-10-23
| 040.13048 | 040.2739.DOGWOOD VILLAS | INSTALL 1100' OF 2" PE FOR 34 CONDOS DOGWOOD VILLAS | 6058.25 | 13900 | -2735.13 | -19.68% | 0.06646% | 11164.87 | 13900 | -2735.13 | 2006-10-01 | 2007-09-30 | 2006-06-27 | 2006-06-27 | 2007-06-27 | 2007-06-27
| 050.18907 | 050.PAD.Coleman Crossing Ext | 1,150' - 2" PE extension for 7 new commercial lots located just off Coleman Road | 6315.03 | 2718.01 | 3597.02 | 132.3% | 0.03759% | 6315.03 | 2718.01 | 3597.02 | 2006-10-01 | 2007-09-30 | 2007-02-01 | 2007-02-01 | 2008-02-01 | 2008-02-01
| 050.19404 | 050.2635.Fence Replace TB 1 | Replace "old" fence | 6347.58 | 6103.55 | 299.08 | 4.9% | 0.03811% | 6402.63 | 6103.55 | 299.08 | 2006-10-01 | 2007-09-30 | 2007-08-08 | 2007-08-08 | 2008-08-08 | 2008-08-08
| 050.19263 | 050.2635.Replace-Marion | Replace 800' 2" bare main in Marion, KY. Some under new garage | 6462.22 | 18263.34 | -11817.46 | -64.71% | 0.03837% | 6445.88 | 18263.34 | -11817.46 | 2006-10-01 | 2007-09-30 | 2007-06-11 | 2007-06-11 | 2008-06-11 | 2008-06-11
| 040.13062 | 040.MAY.Commonwealth Rev Ext | Commonwealth Dr Rev Ext for new Lowes store in Mayfield | 6491.85 | 13117.28 | 2714.83 | 20.7% | 0.09425% | 15832.11 | 13117.28 | 2714.83 | 2006-10-01 | 2007-09-30 | 2006-07-18 | 2006-07-18 | 2006-09-22 | 2006-09-22
| 050.19093 | 050.2637.Reg Sta - Sys Int | Regulator station repairs and improvements | 6524.6 | 9271.2 | -1907.9 | -20.58% | 0.04383% | 7363.3 | 9271.2 | -1907.9 | 2006-10-01 | 2007-09-30 | 2007-04-24 | 2007-04-24 | 2008-04-21 | 2008-04-21
| 050.19358 | 050.BGR.HOP.PIPE TRAILER | PLASTIC PIPE TRAILER - HOPKINSVILLE | 6544.28 | 6490 | 506.23 | 7.8% | 0.04165% | 6996.23 | 6490 | 506.23 | 2006-10-01 | 2007-09-30 | 2007-07-19 | 2007-07-19 | 2008-07-19 | 2008-07-19
| 050.19670 | 050.3351.F I Unit | Purchase F I unit DP-4 Heath | 6551.74 | 7995.58 | -1447.28 | -18.1% | 0.03898% | 6548.3 | 7995.58 | -1447.28 | 2006-10-01 | 2007-09-30 | 2007-10-01 | 2007-10-01 | 2008-10-06 | 2008-10-06
| 040.13098 | 040.2739.LAW.LAWRENCEBURG XING | INSTALL 1500' OF 2" PE AND RETIRE 1300' OF 2" STEEL | 6840.8 | 9459 | -2727.21 | -28.83% | 0.04007% | 6731.79 | 9459 | -2727.21 | 2006-10-01 | 2007-09-30 | 2006-08-15 | 2006-08-15 | 2007-08-15 | 2007-08-15
| 050.19030 | 050.BGR.CHARLESTON II | 2394 FT. OF 2" PE - CHARLESTON II - B.G. | 6960.52 | 7327 | -366.48 | -5.002% | 0.04144% | 6960.52 | 7327 | -366.48 | 2006-10-01 | 2007-09-30 | 2007-03-27 | 2007-03-27 | 2007-03-27 | 2007-03-27
| 050.19253 | 2739.BRIAR CRK CROS PH I | INSTALL 800' OF 4" PE HWY 44-HWY 127 | 7141.01 | 12265 | -271.24 | -2.211% | 0.0714% | 11993.76 | 12265 | -271.24 | 2006-10-01 | 2007-09-30 | 2007-06-06 | 2007-06-06 | 2008-06-06 | 2008-06-06
| 050.19172 | 050.2737.607 E MAIN.LINE BREAK | REPAIR OF LINE BREAK AT CENTRE COLLEGE | 7509.21 | 11375 | -2610.93 | -22.95% | 0.05217% | 8764.07 | 11375 | -2610.93 | 2006-10-01 | 2007-09-30 | 2007-05-03 | 2007-05-03 | 2007-09-28 | 2007-09-28
| 050.19092 | PIPE LOCATOR | RYCOM PIPE LOCATOR # 8869 AND 8877 | 7567.27 | 6939 | 628.27 | 9.054% | 0.04505% | 7567.27 | 6939 | 628.27 | 2006-10-01 | 2007-09-30 | 2007-04-24 | 2007-04-24 | 2008-04-24 | 2008-04-24
| 050.19271 | 050.2636.Pipe Trailer | Purchase Pipe Trailer | 7665.14 | 6489.84 | 1692.09 | 26.07% | 0.04871% | 8181.93 | 6489.84 | 1692.09 | 2006-10-01 | 2007-09-30 | 2007-06-15 | 2007-06-15 | 2007-09-14 | 2007-09-14
| 040.12144 | 040.PAD.Olivet Ch Rd Relocate | Transportation Cabinet Relocation/ 94% Reimbursement/ Olivet Ch Rd | 7795.18 | 1467.79 | -15702.26 | -1070% | -0.08474% | -14234.47 | 1467.79 | -15702.26 | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.18789 | 050.2739.LAW.EAGLE LAKE LOT 10 | INSTALL REG STATION AND 800' OF 2" PE FOR EAGLE LAKE LOT 10 | 8108.04 | 19000 | -548.12 | -2.885% | 0.1098% | 18451.88 | 19000 | -548.12 | 2006-10-01 | 2007-09-30 | 2006-12-28 | 2006-12-28 | 2007-12-01 | 2007-12-01
| 050.18790 | 050.2739.EQUIPMENT.DANVILLE | PURCHASE SENSIT GOLD,DETEX,LOCATOR,ELECFUS,AIR HAMMER FOR DANVILLE | 8131.03 | 16500 | 3964.09 | 24.02% | 0.1218% | 20464.09 | 16500 | 3964.09 | 2006-10-01 | 2007-09-30 | 2006-12-28 | 2006-12-28 | 2007-12-01 | 2007-12-01
| 050.19227 | 050.2636.2" Williamson Eq. | Purchase 2" Williamson Equipment | 8484.18 | 7099.83 | 1384.35 | 19.5% | 0.05051% | 8484.18 | 7099.83 | 1384.35 | 2006-10-01 | 2007-09-30 | 2007-05-24 | 2007-05-24 | 2007-08-01 | 2007-08-01
| 050.19216 | 2738.GRN. 4"PE HIGHWAY PROJ | REPLACE AND RETIRE 4" PE DUE TO HIGHWAY REDISIGN | 8529.96 | 15 | 8514.96 | 56766% | 0.05078% | 8529.96 | 15 | 8514.96 | 2006-10-01 | 2007-09-30 | 2007-05-21 | 2007-05-21 | 2007-09-28 | 2007-09-28
| 050.18584 | 050.2736.HOP.KEETON ST 4" EXT | 1250 FT. OF 4" PE - KEETON ST. - HOPK | 8619.81 | 14072.69 | -5452.88 | -38.75% | 0.05131% | 8619.81 | 14072.69 | -5452.88 | 2006-10-01 | 2007-09-30 | 2006-10-19 | 2006-10-19 | 2007-10-19 | 2007-10-19
| 050.19311 | 050.BGR.GLS.LONHUNTERS RELOC. | 800 FT. OF 4' PE RELOCATION - LONGHUNTERS SQUARE - GLASGOW | 8622.36 | 0 | 8601.42 | - | 0.0512% | 8601.42 | 0 | 8601.42 | 2006-10-01 | 2007-09-30 | 2007-07-05 | 2007-07-05 | 2008-07-05 | 2008-07-05
| 050.19035 | 050.2605.OFFICE.FURNITURE | Purchase of office furniture needed for additional offices constructed at the Owensboro Corp. office | 8786.34 | 12259.64 | -3473.3 | -28.33% | 0.05231% | 8786.34 | 12259.64 | -3473.3 | 2006-10-01 | 2007-09-30 | 2007-03-27 | 2007-03-27 | 2007-03-29 | 2007-03-29
| 050.18835 | 050.BGR.HOP.GREAT OAKS 15-2 | 1455 FT. OF 2" PE - GREAT OAKS 15-2 - HOPKINSVILLE | 8891.44 | 7775 | 1105 | 14.21% | 0.05286% | 8880 | 7775 | 1105 | 2006-10-01 | 2007-09-30 | 2007-01-09 | 2007-01-09 | 2008-01-09 | 2008-01-09
| 050.19660 | 050.2609.STO Equipment | Purchase of New Equipment | 9076.98 | 9998.99 | 652.33 | 6.524% | 0.06341% | 10651.32 | 9998.99 | 652.33 | 2006-10-01 | 2007-09-30 | 2007-09-28 | 2007-09-28 | 2007-09-28 | 2007-09-28
| 040.12773 | Shelbyville 06 Non Growth | Shelbyville 06 Non Growth | 9137.49 | Not Budgeted | - | - | 2.144% | 360200.53 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19086 | 050.2636.Heath Flamepack | Purchase Heath Flamepack | 9230.13 | 7389.14 | 1840.99 | 24.91% | 0.05495% | 9230.13 | 7389.14 | 1840.99 | 2006-10-01 | 2007-09-30 | 2007-04-18 | 2007-04-18 | 2007-07-31 | 2007-07-31
| 050.19430 | 2738.TAYLOR CO HOSPT COMM DEV | INSTALL 1800' OF 2" PE FOR TAYLOR COUNTY HOSPITAL COMMERICAL DEVELOPMENT | 9421.84 | 12120 | -1426.51 | -11.77% | 0.06366% | 10693.49 | 12120 | -1426.51 | 2006-10-01 | 2007-09-30 | 2007-08-21 | 2007-08-21 | 2008-08-01 | 2008-08-01
| 040.13103 | 040.OBO.Fiddlesticks Phase 1 | Install 3,075' 2" PE | 9498.71 | 25068.65 | -5444.95 | -21.72% | 0.1168% | 19623.7 | 25068.65 | -5444.95 | 2006-10-01 | 2007-09-30 | 2006-08-17 | 2006-08-17 | 2006-09-22 | 2006-09-22
| 050.19295 | 050.2636.Salem Dr | Install 704' 2" PE | 9522.09 | 8983.05 | 1848.41 | 20.58% | 0.06448% | 10831.46 | 8983.05 | 1848.41 | 2006-10-01 | 2007-09-30 | 2007-06-27 | 2007-06-27 | 2007-08-31 | 2007-08-31
| 050.19002 | 050.MAD.Liberty Church Reloc. | Relocate 400' 2" PE Due to road widening | 9540.58 | 8862.73 | 677.85 | 7.648% | 0.0568% | 9540.58 | 8862.73 | 677.85 | 2006-10-01 | 2007-09-30 | 2007-03-14 | 2007-03-14 | 2007-08-22 | 2007-08-22
| 050.18642 | 050.OBO.Whispering Meadows 3 | Install 1,172' 2" PE | 9618.55 | 6709.48 | 2909.07 | 43.36% | 0.05726% | 9618.55 | 6709.48 | 2909.07 | 2006-10-01 | 2007-09-30 | 2006-11-02 | 2006-11-02 | 2007-03-30 | 2007-03-30
| 050.18689 | 050.BGR.CUMBERLAND RIDGE III | 2755 FT. OF 2" PE - CUMBERLAND RIDGE III - B.G. | 9631.26 | 7974 | 1657.26 | 20.78% | 0.05733% | 9631.26 | 7974 | 1657.26 | 2006-10-01 | 2007-09-30 | 2006-11-21 | 2006-11-21 | 2007-11-21 | 2007-11-21
| 040.12762 | Bowling Green 06 Growth | Bowling Green 06 Growth Func | 10025 | Not Budgeted | - | - | 6.877% | 1155244.49 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19088 | 050.2636.Crooked Creek Rd. | Repair undermined ground around 2" PE | 10151.48 | 8393.99 | 1757.49 | 20.94% | 0.06043% | 10151.48 | 8393.99 | 1757.49 | 2006-10-01 | 2007-09-30 | 2007-04-19 | 2007-04-19 | 2007-08-31 | 2007-08-31
| 050.19171 | 050.2634.Reg. Sta. Retirement | Retire 2 Low Pressure Reg. Stations | 10207.93 | 11247.42 | -1039.49 | -9.242% | 0.06077% | 10207.93 | 11247.42 | -1039.49 | 2006-10-01 | 2007-09-30 | 2007-05-02 | 2007-05-02 | 2007-08-31 | 2007-08-31
| 050.18736 | 050.Princ.Segway | Purchase Segway | 10236.32 | 8498.6 | 1737.72 | 20.45% | 0.06094% | 10236.32 | 8498.6 | 1737.72 | 2006-10-01 | 2007-09-30 | 2006-12-14 | 2006-12-14 | 2007-04-27 | 2007-04-27
| 050.18734 | 050.MAD.Segway | Purchase Segway | 10271.47 | 8498.6 | 1772.87 | 20.86% | 0.06115% | 10271.47 | 8498.6 | 1772.87 | 2006-10-01 | 2007-09-30 | 2006-12-13 | 2006-12-13 | 2007-04-27 | 2007-04-27
| 050.19508 | 05.BGR.HOP.8" LINE CUT | 8" HP LINE CUT - HOPKINSVILLE | 10498.43 | 7451.53 | -52452.7 | -703.9% | -0.2679% | -45001.17 | 7451.53 | -52452.7 | 2006-10-01 | 2007-09-30 | 2007-08-30 | 2007-08-30 | 2008-08-30 | 2008-08-30
| 040.12779 | Owensboro 06 Non Growth | Owensboro 06 Non Growth | 11172.67 | Not Budgeted | - | - | 10.01% | 1681927.02 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19367 | 050.2605.Gas Plant Property | Purchase Old Gas Plant Property | 11745.15 | 110000 | -110000 | -100% | 0% | 0 | 110000 | -110000 | 2006-10-01 | 2007-09-30 | 2007-07-24 | 2007-07-24 | 2007-09-20 | 2007-09-20
| 050.19034 | 050.2605.OFFICE.EXPANSION | Renovating office space at the Owensboro Corp. office | 11754.98 | 13119 | -1364.02 | -10.4% | 0.06998% | 11754.98 | 13119 | -1364.02 | 2006-10-01 | 2007-09-30 | 2007-03-27 | 2007-03-27 | 2007-03-29 | 2007-03-29
| 050.18959 | 050.PAD.Little Lake Village | 2,420' - 2" PE revenue extension for 32 new residential lots | 12051.91 | 11132.7 | 2411.74 | 21.66% | 0.08063% | 13544.44 | 11132.7 | 2411.74 | 2006-10-01 | 2007-09-30 | 2007-02-23 | 2007-02-23 | 2008-02-22 | 2008-02-22
| 050.18586 | 050.OBO.The Trails Heartland | Install 1,804' 2" PE | 12137.31 | 13059.2 | -921.89 | -7.059% | 0.07225% | 12137.31 | 13059.2 | -921.89 | 2006-10-01 | 2007-09-30 | 2006-10-19 | 2006-10-19 | 2007-01-31 | 2007-01-31
| 050.19378 | 050.2605.TSV Roof | Install Roofing Sealer | 12585.08 | 16193.69 | -3608.61 | -22.28% | 0.07492% | 12585.08 | 16193.69 | -3608.61 | 2006-10-01 | 2007-09-30 | 2007-07-31 | 2007-07-31 | 2007-09-28 | 2007-09-28
| 040.13093 | 040.2715.TBS REGULATOR REPLACE | REPLACE REGULATORS AND RESTRICTORS AT TBS | 12642.2 | 15000 | -2217.15 | -14.78% | 0.0761% | 12782.85 | 15000 | -2217.15 | 2006-10-01 | 2007-09-30 | 2006-08-10 | 2006-08-10 | 2007-08-08 | 2007-08-08
| 050.18969 | 050.BGR.GLS.W.UNION REPLC | WEST UNION 1 1/4' BARE REPLC. - MUNFORDVILLE | 12764.01 | 19846 | -7081.99 | -35.68% | 0.07598% | 12764.01 | 19846 | -7081.99 | 2006-10-01 | 2007-09-30 | 2007-03-02 | 2007-03-02 | 2008-09-28 | 2008-09-28
| 050.18591 | 050.OBO.Harbor Hills Trace | Install 1,243' 2" PE | 13107.53 | 8417.11 | 4690.42 | 55.72% | 0.07803% | 13107.53 | 8417.11 | 4690.42 | 2006-10-01 | 2007-09-30 | 2006-10-20 | 2006-10-20 | 2006-12-31 | 2006-12-31
| 050.18804 | 050.OBO.MISC. Equipment | Purchase1- 2" Stl. Squeeze off, 1 Sensit Gold, 1 Detex Odorometer | 13433.75 | 10223.04 | 3210.71 | 31.41% | 0.07997% | 13433.75 | 10223.04 | 3210.71 | 2006-10-01 | 2007-09-30 | 2007-01-02 | 2007-01-02 | 2007-02-28 | 2007-02-28
| 050.18720 | 050.BGR.TRANSPARK PHASE II | 400 FT. OF 4 ST. - TRANSPARK PHASE II - B.G. | 13809.87 | 8385 | 9568.38 | 114.1% | 0.1069% | 17953.38 | 8385 | 9568.38 | 2006-10-01 | 2007-09-30 | 2006-12-07 | 2006-12-07 | 2008-09-29 | 2008-09-29
| 040.12768 | Danville 06 Growth | Danville 06 Growth | 14127.37 | Not Budgeted | - | - | 1.88% | 315776.48 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 050.19662 | 2739.SHELBYVILLE.EQUIPMENT | 2 - DITCH WITCH LOCATORS, 1 - FLAME PAK | 14410.37 | 15759 | 1689.72 | 10.72% | 0.1039% | 17448.72 | 15759 | 1689.72 | 2006-10-01 | 2007-09-30 | 2007-09-28 | 2007-09-28 | 2008-12-23 | 2008-12-23
| 040.13040 | 040.OBO.E.24TH. & BOLIVAR | INSTALL 729' 2" PE RETIRE 3" & 4" STL. | 14485.28 | 29817.96 | -12757.38 | -42.78% | 0.1016% | 17060.58 | 29817.96 | -12757.38 | 2006-10-01 | 2007-09-30 | 2006-06-15 | 2006-06-15 | 2006-08-31 | 2006-08-31
| 050.18990 | 050.2738.LEB.METTS DR TIE-IN | INSTALL 1500' OF 4" PE ALONG HP LINE OFF METTS DRIVE | 14530.18 | 17340 | -1956.57 | -11.28% | 0.09158% | 15383.43 | 17340 | -1956.57 | 2006-10-01 | 2007-09-30 | 2007-03-09 | 2007-03-09 | 2008-03-09 | 2008-03-09
| 050.19056 | 050.2637.Retire 14th & Ky | Retire building at 14th & Ky Ave. | 14567.15 | 15589.52 | -1022.37 | -6.558% | 0.08672% | 14567.15 | 15589.52 | -1022.37 | 2006-10-01 | 2007-09-30 | 2007-04-04 | 2007-04-04 | 2008-04-04 | 2008-04-04
| 040.13041 | 040.MAD.Henderson Reg.Relocte | Move Finley Reg. Sta. due to HWY Project | 14576.05 | 70647.63 | -27040.7 | -38.28% | 0.2596% | 43606.93 | 70647.63 | -27040.7 | 2006-10-01 | 2007-09-30 | 2006-06-16 | 2006-06-16 | 2006-09-08 | 2006-09-08
| 040.12314 | 040.CAM.GREENSBURG CONNECTOR | REPLACE 1300' OF 2" PE W/ 1700' OF 4" PE AND 100' 2" PE RETIRE 2" STEEL AND PE | 15488.4 | 14494.79 | -34595.13 | -238.7% | -0.1197% | -20100.34 | 14494.79 | -34595.13 | 2006-10-01 | 2007-09-30 | 2005-05-04 | 2005-05-04 | 2005-05-04 | 2005-05-04
| 050.18703 | Shelbyville Odor Upgrade | Upgrade for Shelbyville YZ Odorzer | 15595.62 | 9270 | 6325.62 | 68.24% | 0.09284% | 15595.62 | 9270 | 6325.62 | 2006-10-01 | 2007-09-30 | 2006-11-29 | 2006-11-29 | 2007-11-26 | 2007-11-26
| 050.18985 | Storage Mueller Equipment | Purchase Mueller Bottom Out Stoppers | 16197.35 | 13598 | 2599.35 | 19.12% | 0.09642% | 16197.35 | 13598 | 2599.35 | 2006-10-01 | 2007-09-30 | 2007-03-06 | 2007-03-06 | 2007-08-31 | 2007-08-31
| 050.18700 | t.050.PTON.Sturgis Rd Replace | Replace app 400' of 4" bare steel with 4" PE due to leakage | 16622.81 | 11889.66 | 4733.15 | 39.81% | 0.09896% | 16622.81 | 11889.66 | 4733.15 | 2006-10-01 | 2007-09-30 | 2006-11-29 | 2006-11-29 | 2007-11-29 | 2007-11-29
| 050.18931 | 050.PAD.Retire bldg - T.B 2 | Demolish building at town border 2 (Lourdes Hospital) | 16723.65 | 14691.77 | 2031.88 | 13.83% | 0.09956% | 16723.65 | 14691.77 | 2031.88 | 2006-10-01 | 2007-09-30 | 2007-02-07 | 2007-02-07 | 2008-02-05 | 2008-02-05
| 050.19357 | 050.BGR.TRANSPARK 5-2 | 950 FT. OF 4" HPD - TRANSPARK LOT 5-2 | 17242.82 | 8078 | -6185.36 | -76.57% | 0.01127% | 1892.64 | 8078 | -6185.36 | 2006-10-01 | 2007-09-30 | 2007-07-19 | 2007-07-19 | 2008-07-18 | 2008-07-18
| 050.19663 | 2737.DANVILLE EQUIPMENT | 2 DITCH WITCH LOCATORS, 1 CONCRETE SAW | 17586.32 | 14216 | 3720.58 | 26.17% | 0.1068% | 17936.58 | 14216 | 3720.58 | 2006-10-01 | 2007-09-30 | 2007-09-28 | 2007-09-28 | 2007-11-01 | 2007-11-01
| 050.18605 | 050.PAD.Meadow Ridge Ext | 1,850' - 2" PE into Meadow Ridge Subd | 18269.23 | 9803.09 | 8466.14 | 86.36% | 0.1088% | 18269.23 | 9803.09 | 8466.14 | 2006-10-01 | 2007-09-30 | 2006-10-24 | 2006-10-24 | 2007-09-30 | 2007-09-30
| 050.19039 | 050.2635.Purchase Lot Dawson | purchase 30 x 60 lot that houses Dawson Springs TB | 18682.45 | 16224.6 | 2457.85 | 15.15% | 0.1112% | 18682.45 | 16224.6 | 2457.85 | 2006-10-01 | 2007-09-30 | 2007-03-29 | 2007-03-29 | 2008-03-28 | 2008-03-28
| 050.18648 | 050.PAD.Olivet Village Ext | Install 3,315' - 2" PE for 72 new residential lots | 19171.81 | 17488.06 | 1683.75 | 9.628% | 0.1141% | 19171.81 | 17488.06 | 1683.75 | 2006-10-01 | 2007-09-30 | 2006-11-07 | 2006-11-07 | 2007-11-07 | 2007-11-07
| 050.18350 | Princeton 07 Growth | Princeton 07 Growth Functional | 19310.75 | Not Budgeted | - | - | 0.1163% | 19532.7 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.19659 | 050.2634.Misc. Equipment | Purchase Pipeline Welder & Goldak locator | 19404.44 | 18851.44 | 1060.54 | 5.626% | 0.1185% | 19911.98 | 18851.44 | 1060.54 | 2006-10-01 | 2007-09-30 | 2007-09-28 | 2007-09-28 | 2007-09-30 | 2007-09-30
| 050.19066 | Large Volume Meters | Large Volume Meters Blanket Project | 19458.76 | 43580 | -20380.92 | -46.77% | 0.1381% | 23199.08 | 43580 | -20380.92 | 2006-10-01 | 2007-09-30 | 2007-04-09 | 2007-04-09 | 2007-09-30 | 2007-09-30
| 050.18747 | 050.HOPK.OLD MADISONVILLE EXT. | 1550 FT. OF 2" PE & SERVICES - OLD MADISONVILLE - HOPK. | 19705.95 | 18487.76 | 1218.19 | 6.589% | 0.1173% | 19705.95 | 18487.76 | 1218.19 | 2006-10-01 | 2007-09-30 | 2006-12-19 | 2006-12-19 | 2007-12-19 | 2007-12-19
| 050.18825 | 050.2734.MISC. EQUIPMENT | SEGWAY, SENSIT GOLD CGI'S AND STEEL SQUEEZE OFF TOLLS - B.G. | 20184.31 | 16906 | 3278.31 | 19.39% | 0.1202% | 20184.31 | 16906 | 3278.31 | 2006-10-01 | 2007-09-30 | 2007-01-05 | 2007-01-05 | 2008-01-05 | 2008-01-05
| 050.19257 | 050.2634.Brank St. Ground Bed | Replace depleted ground bed | 21359.81 | 20322.47 | 993.05 | 4.886% | 0.1269% | 21315.52 | 20322.47 | 993.05 | 2006-10-01 | 2007-09-30 | 2007-06-07 | 2007-06-07 | 2007-09-20 | 2007-09-20
| 050.18989 | 050.BGR.TRADITIONS SUB | 6579' -2' PE & 925 -6" PE - TRADITIONS SUB - BOWLING GREEN | 21565.88 | 24915 | -19207.12 | -77.09% | 0.03398% | 5707.88 | 24915 | -19207.12 | 2006-10-01 | 2007-09-30 | 2007-03-09 | 2007-03-09 | 2008-03-09 | 2008-03-09
| 040.13099 | 040.2739.SUMMERFIELD PH-I | INSTALL 3500' OF 2" PE FOR SUMMERFIELD PH I | 22141.82 | 27357 | -2879.38 | -10.53% | 0.1457% | 24477.62 | 27357 | -2879.38 | 2006-10-01 | 2007-09-30 | 2006-08-15 | 2006-08-15 | 2007-08-15 | 2007-08-15
| 050.18988 | 050.2737.PREMIER VILLAGE | INSTALL 3000' OF 2" PE IN PREMIER VILLAGE | 22706.91 | 18000 | 4699.88 | 26.11% | 0.1351% | 22699.88 | 18000 | 4699.88 | 2006-10-01 | 2007-09-30 | 2007-03-08 | 2007-03-08 | 2008-03-08 | 2008-03-08
| 050.18755 | Regs. for Scotty's Woodburn | Regulator and Relief Valve for Scotty's Asphalt in Woodburn | 23514.55 | 23431 | 83.55 | 0.3566% | 0.14% | 23514.55 | 23431 | 83.55 | 2006-10-01 | 2007-09-30 | 2006-12-20 | 2006-12-20 | 2007-03-01 | 2007-03-01
| 040.13038 | 040.2739.NOTTING HILLS 1b | INSTALL 1700' OF 2" AND 4" PE FOR 10 SERVICES = 40 MTR SETS | 23521.7 | 22800 | 18300.73 | 80.27% | 0.2447% | 41100.73 | 22800 | 18300.73 | 2006-10-01 | 2007-09-30 | 2006-06-12 | 2006-06-12 | 2007-07-07 | 2007-07-07
| 050.18652 | 050.PTON.Cadiz Sys Imp | Install 330' - 4" PE as well as 330' - 8" steel casing pipe | 23892.63 | 18682.35 | 5206.1 | 27.87% | 0.1422% | 23888.45 | 18682.35 | 5206.1 | 2006-10-01 | 2007-09-30 | 2006-11-08 | 2006-11-08 | 2007-11-08 | 2007-11-08
| 050.19222 | 050.2609.STO Reed Minerals 4" | Replace Section of Reed Minerals 4" | 24425.64 | 12351.27 | 11970.06 | 96.91% | 0.1448% | 24321.33 | 12351.27 | 11970.06 | 2006-10-01 | 2007-09-30 | 2007-05-23 | 2007-05-23 | 2007-09-28 | 2007-09-28
| 050.19207 | 050.BGR.RUSS.LOGAN PUR 6" | 60 FT. OF 6" STL. - LOGAN PURCHASE STATION | 24631.55 | 24659 | 1612.42 | 6.539% | 0.1564% | 26271.42 | 24659 | 1612.42 | 2006-10-01 | 2007-09-30 | 2007-05-17 | 2007-05-17 | 2008-05-17 | 2008-05-17
| 050.18905 | 050.BGR.SO.IND 4" PE EXT. | 2600 FT. OF 4" PE - SOUTH INDUSTRIAL - B.G. | 28014.78 | 24937 | 3077.78 | 12.34% | 0.1668% | 28014.78 | 24937 | 3077.78 | 2006-10-01 | 2007-09-30 | 2007-01-31 | 2007-01-31 | 2008-01-31 | 2008-01-31
| 050.18954 | 050.PAD.C.P Equipment | 3 pieces of C.P equipment to be used in the "Swain" sub-region | 28894.98 | 23860.98 | 5034 | 21.1% | 0.172% | 28894.98 | 23860.98 | 5034 | 2006-10-01 | 2007-09-30 | 2007-02-20 | 2007-02-20 | 2008-02-20 | 2008-02-20
| 050.18693 | 050.2738.LEB BYPASS RELOCAT | RELOCATE 1400' OF 4" PE FOR THE LEBANON BYPASS - STATE PROJECT | 30209.76 | -11727.9 | 13318.53 | -113.6% | 0.009469% | 1590.63 | -11727.9 | 13318.53 | 2006-10-01 | 2007-09-30 | 2006-11-27 | 2006-11-27 | 2007-12-11 | 2007-12-11
| 050.19650 | 050.BGR. EQUIP. - B.G. | EQUIPMENT - BOWLING GREEN AREA | 31353.18 | 48831 | 2642.78 | 5.412% | 0.3064% | 51473.78 | 48831 | 2642.78 | 2006-10-01 | 2007-09-30 | 2007-09-27 | 2007-09-27 | 2008-09-09 | 2008-09-09
| 050.18933 | 050.2618.SAFETY07SCBA | Purchase 4 SCBA units and 3 shoring boxes for distribution throughout KY & MidStates | 32091.23 | 34311.22 | -2219.99 | -6.47% | 0.191% | 32091.23 | 34311.22 | -2219.99 | 2006-10-01 | 2007-09-30 | 2007-02-08 | 2007-02-08 | 2007-02-14 | 2007-02-14
| 040.13065 | 040.2738.DUF-JACK-WICK SERVICE | REPLACE SERVICES ON DUFFY,JACKSON,WICKLIFFE | 32288.73 | 110185 | 10825.69 | 9.825% | 0.7204% | 121010.69 | 110185 | 10825.69 | 2006-10-01 | 2007-09-30 | 2006-07-20 | 2006-07-20 | 2008-04-01 | 2008-04-01
| 050.18848 | 2739.TWIN SPRINGS.JOINT TRENCH | INSTALL 2100' OF 2",900' OF 4"-JOINT TRENCH | 34450.32 | 30110 | 4339.01 | 14.41% | 0.2051% | 34449.01 | 30110 | 4339.01 | 2006-10-01 | 2007-09-30 | 2007-01-10 | 2007-01-10 | 2008-01-10 | 2008-01-10
| 050.18873 | 050.OBO. Chart Recorders | Purchase Chart Recorders | 35782.08 | 33346.49 | 2426.75 | 7.277% | 0.213% | 35773.24 | 33346.49 | 2426.75 | 2006-10-01 | 2007-09-30 | 2007-01-19 | 2007-01-19 | 2007-07-31 | 2007-07-31
| 040.13064 | 040.2738.DUFF-JACKS-WICKL MAIN | REPLACE BARE STEEL MAIN ON DUFFY,JACKSON AND WICKLIFFE STREETS | 37505.52 | 151600 | -50352.64 | -33.21% | 0.6027% | 101247.36 | 151600 | -50352.64 | 2006-10-01 | 2007-09-30 | 2006-07-20 | 2006-07-20 | 2008-04-01 | 2008-04-01
| 050.18870 | 050.PAD.Lone Oak Rd Relocate | Relocate 280' - 6" S.K pipe Lone Oak Rd between Bleich Rd and Glenn St | 38657.42 | 28109.67 | 10547.75 | 37.52% | 0.2301% | 38657.42 | 28109.67 | 10547.75 | 2006-10-01 | 2007-09-30 | 2007-01-17 | 2007-01-17 | 2007-09-28 | 2007-09-28
| 050.19279 | 050.2618.SAFETY07B | Purchase of 2 SCBA units and 1 lifeline tripod | 40207.01 | 13006.96 | 29298.68 | 225.3% | 0.2518% | 42305.64 | 13006.96 | 29298.68 | 2006-10-01 | 2007-09-30 | 2007-06-20 | 2007-06-20 | 2007-09-26 | 2007-09-26
| 050.19381 | 050.2739.COLLEGE ST CI REPLACE | REPLACE 650' OF 8" CAST IRON ON COLLEGE STREET | 43880.08 | 49360 | 15067.32 | 30.53% | 0.3835% | 64427.32 | 49360 | 15067.32 | 2006-10-01 | 2007-09-30 | 2007-08-01 | 2007-08-01 | 2008-08-08 | 2008-08-08
| 050.19062 | transpark cosmo 4"HPD | 1300' OF 4" HPD TRANSPARK COSMO BG | 44552.87 | 23887 | -615.21 | -2.576% | 0.1385% | 23271.79 | 23887 | -615.21 | 2006-10-01 | 2007-09-30 | 2007-04-05 | 2007-04-05 | 2008-04-05 | 2008-04-05
| 050.19041 | 050.BGR.MT.VIC.OLDE.TWN | 3073'of 6" and 2600' of 2" -Mt. VICTOR OLDE TOWN -B.G. | 44617.53 | 23230 | 9394.63 | 40.44% | 0.1942% | 32624.63 | 23230 | 9394.63 | 2006-10-01 | 2007-09-30 | 2007-03-30 | 2007-03-30 | 2007-03-30 | 2007-03-30
| 040.13119 | 040.B.G.WOODBURN PUR REPLC. | REPLACE WOODBURN PURCHASE REG. STATION | 47071.45 | 62391 | 10616.5 | 17.02% | 0.4346% | 73007.5 | 62391 | 10616.5 | 2006-10-01 | 2007-09-30 | 2006-09-13 | 2006-09-13 | 2007-09-13 | 2007-09-13
| 050.18344 | Campbellsville 07 Growth | Campbellsville 07 Growth Functional | 52324.21 | Not Budgeted | - | - | 0.3137% | 52701.09 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18872 | 2739.LAW.HWY 127 4 ST RELOCATE | RELOCATE 600' OF 4" STEEL ON HWY 127 SOUTH OF HWY 44 | 55270.01 | 85200 | -28834.69 | -33.84% | 0.3355% | 56365.31 | 85200 | -28834.69 | 2006-10-01 | 2007-09-30 | 2007-01-18 | 2007-01-18 | 2008-03-01 | 2008-03-01
| 050.18862 | 050.MAD.Boring Machine & Trl. | Purchase Boring Machine & trailer | 59532.23 | 48118.58 | 11413.65 | 23.72% | 0.3544% | 59532.23 | 48118.58 | 11413.65 | 2006-10-01 | 2007-09-30 | 2007-01-16 | 2007-01-16 | 2007-02-28 | 2007-02-28
| 050.19264 | 2739.1100 MAIN.CAST IRON-MAIN | REPLACE CAST IRON FROM ALTON ROAD TO 10TH ON MAIN ST | 59688.47 | 115700 | -56030.23 | -48.43% | 0.3552% | 59669.77 | 115700 | -56030.23 | 2006-10-01 | 2007-09-30 | 2007-06-12 | 2007-06-12 | 2007-12-13 | 2007-12-13
| 040.12920 | 040.STO Squire Rd Xing Repl. | Line No. 90-159-00 Nortonville/Fruithill 10" Road Crossing Replacement | 61057.86 | 230378 | -160639.18 | -69.73% | 0.4152% | 69738.82 | 230378 | -160639.18 | 2006-10-01 | 2007-09-30 | 2006-01-19 | 2006-01-19 | 2006-09-28 | 2006-09-28
| 050.18645 | 050.2739.NOTTING HILLS SEC II | INSTALL 3600' OF 2" PE AND 1500' OF 4" PE | 63319.11 | 47900 | 15419.11 | 32.19% | 0.3769% | 63319.11 | 47900 | 15419.11 | 2006-10-01 | 2007-09-30 | 2006-11-02 | 2006-11-02 | 2007-11-01 | 2007-11-01
| 050.19218 | 050.2638.Jimtown Road Relocate | Install 4,000' - 2" PE/ 76% Reimburseable | 64325.27 | 10792.5 | 56024.25 | 519.1% | 0.3978% | 66816.75 | 10792.5 | 56024.25 | 2006-10-01 | 2007-09-30 | 2007-05-22 | 2007-05-22 | 2007-05-31 | 2007-05-31
| 050.18722 | 050.BGR.RUSS.LOGAN PUR. REG | LOGAN PURCHASE REGULATOR STATION - L | 65263.81 | 37786 | 27462.44 | 72.68% | 0.3884% | 65248.44 | 37786 | 27462.44 | 2006-10-01 | 2007-09-30 | 2006-12-08 | 2006-12-08 | 2007-12-09 | 2007-12-09
| 050.19383 | 050.2739.CAST IRON PH II-SERV | REPLACE SERVICES ON MAIN AND 8TH STREETS WITH CAST IRON MAIN REPLACEMENT | 66038.22 | 63687 | 39540.41 | 62.09% | 0.6145% | 103227.41 | 63687 | 39540.41 | 2006-10-01 | 2007-09-30 | 2007-08-01 | 2007-08-01 | 2008-08-08 | 2008-08-08
| 050.19265 | 2739.1100 MAIN.CAST IRON-SERV | REPLACE SERVICES ON MAIN STREET FOR CAST IRON REPLACEMENT | 68598.41 | 56945 | 12721.47 | 22.34% | 0.4147% | 69666.47 | 56945 | 12721.47 | 2006-10-01 | 2007-09-30 | 2007-06-12 | 2007-06-12 | 2007-12-31 | 2007-12-31
| 050.18740 | 050.OBO.Lot Improvement | Grade & Gravel lot, New Fence SRV. CNTR. | 71041.8 | 58717.6 | 12757.53 | 21.73% | 0.4255% | 71475.13 | 58717.6 | 12757.53 | 2006-10-01 | 2007-09-30 | 2006-12-15 | 2006-12-15 | 2007-07-27 | 2007-07-27
| 050.19083 | 050.2737.LANCASTER PUR UPGRADE | REPLACE THE PURCHASE STATION ON HWY 27 FOR LANCASTER AND STANFORD | 71425.3 | 59490 | 23340.1 | 39.23% | 0.4931% | 82830.1 | 59490 | 23340.1 | 2006-10-01 | 2007-09-30 | 2007-04-17 | 2007-04-17 | 2008-04-12 | 2008-04-12
| 050.19074 | 050.2738.CVILLE INDUST PARK | INSTALL 6800' OF 4" PE FOR THE INDUSTRIAL APRK ON HWY 55 SOUTH | 75716.07 | 11332 | 154520.36 | 1364% | 0.9873% | 165852.36 | 11332 | 154520.36 | 2006-10-01 | 2007-09-30 | 2007-04-11 | 2007-04-11 | 2008-04-11 | 2008-04-11
| 050.19379 | 050.2637.Reidland Rd Relocate | Reidland Rd state highway project relocation | 78450.84 | 94279.84 | 5244.46 | 5.563% | 0.5925% | 99524.3 | 94279.84 | 5244.46 | 2006-10-01 | 2007-09-30 | 2007-07-31 | 2007-07-31 | 2008-07-28 | 2008-07-28
| 050.18585 | 050.BGR.HWY 31W CONTRACC LAB | CONTRACT LABOR - HWY 31W RELOC. - B.G. | 94560.87 | 74154 | 20406.87 | 27.52% | 0.5629% | 94560.87 | 74154 | 20406.87 | 2006-10-01 | 2007-09-30 | 2006-10-19 | 2006-10-19 | 2006-10-19 | 2006-10-19
| 050.18672 | 050.KYMS.PC REPLACEMENTS 2007 | FY2007 PC REPLACEMENTS FOR KY & MID-STATES | 95027.49 | 79236 | 118259.71 | 149.2% | 1.176% | 197495.71 | 79236 | 118259.71 | 2006-10-01 | 2007-09-30 | 2006-11-10 | 2006-11-10 | 2006-12-06 | 2006-12-06
| 050.19382 | 050.2739.CAST IRON PH II.MAIN | REPLACE 1700' OF CAST IRON ON MAIN AND 8TH STREET | 96740.36 | 98674 | 54606.61 | 55.34% | 0.9125% | 153280.61 | 98674 | 54606.61 | 2006-10-01 | 2007-09-30 | 2007-08-01 | 2007-08-01 | 2008-08-08 | 2008-08-08
| 050.18653 | 050.2612.METER REBUILD | REBUILD METERS FOR METER DEPARTMENT | 115804.41 | 249936.11 | -138517.93 | -55.42% | 0.6633% | 111418.18 | 249936.11 | -138517.93 | 2006-10-01 | 2007-09-30 | 2006-11-08 | 2006-11-08 | 2007-11-07 | 2007-11-07
| 050.18338 | Glasgow 07 Growth | Glasgow 07 Growth Functional | 122512.24 | Not Budgeted | - | - | 0.7319% | 122951.8 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18348 | Madisonville 07 Growth | Madisonville 07 Growth Functional | 125673.79 | Not Budgeted | - | - | 0.7515% | 126239.45 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18356 | Mayfield 07 Growth | Mayfield 07 Growth Functional | 128960.79 | Not Budgeted | - | - | 0.7774% | 130596.04 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18340 | Hopkinsville 07 Growth | Hopkinsville 07 Growth Functional | 159491.9 | Not Budgeted | - | - | 0.9532% | 160117.1 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18640 | 050.2734.HWY 31W CONTRACT LAB | CONTRACT LABOR ONLY - HWY 31W RELOCATION - BOWLING GREEN | 226197.68 | 182476 | 43721.68 | 23.96% | 1.347% | 226197.68 | 182476 | 43721.68 | 2006-10-01 | 2007-09-30 | 2006-11-02 | 2006-11-02 | 2007-11-02 | 2007-11-02
| 050.19208 | 050.BGR.LOVERS LN. PHASE I | 3000 FT - 6' PE, 150 FT. - 6' STL. & 100' - 2"PE - LOVERS LN. PHASE I | 254604.25 | 227641 | 123112.58 | 54.08% | 2.088% | 350753.58 | 227641 | 123112.58 | 2006-10-01 | 2007-09-30 | 2007-05-17 | 2007-05-17 | 2008-05-17 | 2008-05-17
| 050.18842 | 050.BGR.31W CONT.LAB.- B.G. | HWY 31W IP RELOC - CONTRACT LABOR - B.G. | 270665.56 | 220077 | 50588.56 | 22.99% | 1.611% | 270665.56 | 220077 | 50588.56 | 2006-10-01 | 2007-09-30 | 2007-01-09 | 2007-01-09 | 2008-01-09 | 2008-01-09
| 050.18351 | Princeton 07 Non Growth | Princeton 07 Non Growth Functional | 280476.45 | Not Budgeted | - | - | 1.674% | 281282.44 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18347 | Shelbyville 07 Non Growth | Shelbyville 07 Non Growth Functional | 318136.25 | Not Budgeted | - | - | 1.936% | 325210.71 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18357 | Mayfield 07 Non Growth | Mayfield 07 Non Growth Functional | 384767.96 | Not Budgeted | - | - | 2.332% | 391751.89 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18342 | Danville 07 Growth | Danville 07 Growth Functional | 399189.32 | Not Budgeted | - | - | 2.41% | 404906.47 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 040.13094 | 040.2609 STO HCA Replacement | Replace 10" with 12" in HCA at Gordon Park | 435948.8 | 248949 | 274137.38 | 110.1% | 3.114% | 523086.38 | 248949 | 274137.38 | 2006-10-01 | 2007-09-30 | 2006-08-11 | 2006-08-11 | 2007-09-28 | 2007-09-28
| 050.18345 | Campbellsville 07 Non Growth | Campbellsville 07 Non Growth Functional | 454362.78 | Not Budgeted | - | - | 2.731% | 458712.67 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18346 | Shelbyville 07 Growth | Shelbyville 07 Growth Functional | 464301.57 | Not Budgeted | - | - | 2.817% | 473190.08 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18841 | 050.BGR.31W IP RELOC. - B.G. | HWY 31W IP RELOC - CO. LAB & MAT. - B.G. | 495633.98 | 159443 | 359073.78 | 225.2% | 3.087% | 518516.78 | 159443 | 359073.78 | 2006-10-01 | 2007-09-30 | 2007-01-09 | 2007-01-09 | 2008-01-09 | 2008-01-09
| 050.18354 | Paducah 07 Growth | Paducah 07 Growth Functional | 503156.15 | Not Budgeted | - | - | 3.017% | 506801.4 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18673 | 050.KYMS.MDT HARDWARE 2007 | FY 2007 MDT HARDWARE | 553445.61 | 571106 | 100190.3 | 17.54% | 3.996% | 671296.3 | 571106 | 100190.3 | 2006-10-01 | 2007-09-30 | 2006-11-10 | 2006-11-10 | 2006-12-06 | 2006-12-06
| 050.18339 | Glasgow 07 Non Growth | Glasgow 07 Non Growth Functional | 585894.88 | Not Budgeted | - | - | 3.448% | 579264.99 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18341 | Hopkinsville 07 Non Growth | Hopkinsville 07 Non Growth Functional | 619920.9 | Not Budgeted | - | - | 3.609% | 606322.11 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18343 | Danville 07 Non Growth | Danville 07 Non Growth Functional | 622197.72 | Not Budgeted | - | - | 3.756% | 630897.39 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18352 | Owensboro 07 Growth | Owensboro 07 Growth Functional | 637312.81 | Not Budgeted | - | - | 3.932% | 660546.86 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 040.12928 | 040.STO Line 9015900 Swamp | Line 90-159-00 Replacement in Swamp Due to Leakage | 637656.1 | 248936 | 586624.52 | 235.7% | 4.974% | 835560.52 | 248936 | 586624.52 | 2006-10-01 | 2007-09-30 | 2006-01-27 | 2006-01-27 | 2006-09-28 | 2006-09-28
| 050.18349 | Madisonville 07 Non Growth | Madisonville 07 Non Growth Functional | 665490.05 | Not Budgeted | - | - | 3.869% | 649943.24 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18336 | Bowling Green 07 Growth | Bowling Green 07 Growth Functional | 1261192.5 | Not Budgeted | - | - | 7.665% | 1287551.04 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 040.12919 | 040.STO Hwy 800 Xing Repl. | Line No. 90-159-00 Nortonville/Fruithill 10" Replace Highway 800 Road Crossing | 1331637.23 | 230378 | 1131517.55 | 491.2% | 8.107% | 1361895.55 | 230378 | 1131517.55 | 2006-10-01 | 2007-09-30 | 2006-01-19 | 2006-01-19 | 2006-09-28 | 2006-09-28
| 050.18355 | Paducah 07 Non Growth | Paducah 07 Non Growth Functional | 1542317.38 | Not Budgeted | - | - | 9.205% | 1546196.67 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18337 | Bowling Green 07 Non Growth | Bowling Green 07 Non Growth Functional | 1951587.28 | Not Budgeted | - | - | 11.98% | 2012029.34 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29
| 050.18353 | Owensboro 07 Non Growth | Owensboro 07 Non Growth Functional | 2176252.63 | Not Budgeted | - | - | 13.12% | 2203689.69 | Not Budgeted | - | 2006-10-01 | 2007-09-30 | 2006-10-05 | 2006-10-05 | 2007-09-29 | 2007-09-29

## 2006a
Atmos Energy Corporation
(Kentucky Division)
Case No. 2015-00343
Construction Projects 2006
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised | [12 empty] | Schedule 13a
Workpaper Reference No(s).: DR-1 Item 13a | [12 empty] | Witness Responsible: GKW-1
| Project No. | Project Title / Description |  | Annual Actual Cost 2006 | Annual Original P&N Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total P&N Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
| 040.13069 | 040.2652.916303 | MEC Forfeiture | -65938.52 | Not Budgeted | - | - | -0.4648% | -65938.52 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.13099 | 040.2739.SUMMERFIELD PH-I | INSTALL 3500' OF 2" PE FOR SUMMERFIELD PH I | -31153.2 | 27357 | -2879.38 | -10.53% | 0.1726% | 24477.62 | 27357 | -2879.38 | 2005-10-01 | 2006-09-30 | 2006-08-15 | 2006-08-15 | 2007-08-15 | 2007-08-15
| 040.13147 | 040.2737.91669201 | MEC Forfeiture | -30607 | Not Budgeted | - | - | -0.2158% | -30607 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12428 | Aky.tcsvc.meas.Logan Aluminum | Install Separator/Knockout tank @ Logan Aluminum | -30000 | 52550 | -14706.37 | -27.99% | 0.2668% | 37843.63 | 52550 | -14706.37 | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.13043 | 040.2737.EPHRAIM.FIGG-MLK | INSTALL 2" PE ON FIGG ALLEY AND RETIRE LINE ON MLK BLVD | -29723.42 | -150 | -29573.42 | 19716% | -0.2095% | -29723.42 | -150 | -29573.42 | 2005-10-01 | 2006-09-30 | 2006-06-19 | 2006-06-19 | 2007-06-01 | 2007-06-01
| 040.12970 | 040.2734.HartCounty | MEC Forfeiture | -23620.1 | Not Budgeted | - | - | -0.1665% | -23620.1 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12959 | 040.2734.GlasgowInd | MEC Forfeiture | -21163.05 | Not Budgeted | - | - | -0.1492% | -21163.05 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12525 | 040.CAM.GREENSBURG-FEB OUTAGE | CAPTURE COSTS WITH ACCIDENT IN GREENSBURG 2-8-05.RELIGHT AND REBUILD STATION | -19500 | 80550 | -82077.58 | -101.9% | -0.01077% | -1527.58 | 80550 | -82077.58 | 2005-10-01 | 2006-09-30 | 2005-02-10 | 2005-02-10 | 2005-03-01 | 2005-03-01
| 040.12792 | Windmere Place MEC Forfeiture | Windmere Place MEC Forfeiture | -15437 | Not Budgeted | - | - | -0.1088% | -15437 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-17 | 2005-10-17 | 2005-10-30 | 2005-10-30
| 040.13003 | 040.2734.0916315-02 | MEC Forfeiture | -14737 | Not Budgeted | - | - | -0.1039% | -14737 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12995 | 040.2636.0916076 | MEC Forfeiture | -14100 | Not Budgeted | - | - | -0.0994% | -14100 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13129 | 040.2737.916643 | Mec Forfeitures | -11624 | Not Budgeted | - | - | -0.08194% | -11624 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-25 | 2006-09-25 | 2006-09-26 | 2006-09-26
| 040.13141 | 040.2734.91639402 | MEC Forfeiture | -10359 | Not Budgeted | - | - | -0.07303% | -10359 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12975 | 040.2636.WilliamMBratcher | MEC Forfeiture | -9745 | Not Budgeted | - | - | -0.0687% | -9745 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13098 | 040.2739.LAW.LAWRENCEBURG XING | INSTALL 1500' OF 2" PE AND RETIRE 1300' OF 2" STEEL | -9414.01 | 9459 | -2727.21 | -28.83% | 0.04746% | 6731.79 | 9459 | -2727.21 | 2005-10-01 | 2006-09-30 | 2006-08-15 | 2006-08-15 | 2007-08-15 | 2007-08-15
| 040.12674 | 040.BGR.RUSS WAL-MART RELOC | 1130 FT. OF 2" PE RELOCATION - WAL-MART - RUSS | -8834.35 | Not Budgeted | - | - | -0.05609% | -7956.56 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-09-02 | 2005-09-02 | 2005-09-28 | 2005-09-28
| 040.12942 | 040.Glen Shearer | Glen Shearer Forfeiture | -8628 | Not Budgeted | - | - | -0.06082% | -8628 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13138 | 040.2736.9168661 | MEC Forfeiture | -8618 | Not Budgeted | - | - | -0.06075% | -8618 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12357 | Bowling Green 05 Non Growth | Bowling Green 05 Non Growth | -7962.67 | Not Budgeted | - | - | 10.23% | 1451034.84 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12669 | 040.CAM.IMI - HWY 68 | INSTALL 2000' OF 2" PE FOR IMI CONCRETE ON HWY 68 | -7809.72 | 2100 | 1042.89 | 49.66% | 0.02216% | 3142.89 | 2100 | 1042.89 | 2005-10-01 | 2006-09-30 | 2005-08-25 | 2005-08-25 | 2005-10-15 | 2005-10-15
| 040.12556 | 040.BGR.HOP.PENNYRILE FORD | 925 FT. OF 2"PE - PENNYRILE FORD - HOPKINSVILLE | -7723.96 | 726 | -3837.29 | -528.6% | -0.02193% | -3111.29 | 726 | -3837.29 | 2005-10-01 | 2006-09-30 | 2005-04-08 | 2005-04-08 | 2005-09-28 | 2005-09-28
| 040.13076 | 040.2652.916655 | MEC Forfeiture | -7563 | Not Budgeted | - | - | -0.05332% | -7563 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12976 | 040.2636.Larry Yates | MEC Forfeiture | -7271 | Not Budgeted | - | - | -0.05126% | -7271 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13111 | 040.2636.91681901 | MEC Forfeiture | -6961 | Not Budgeted | - | - | -0.04907% | -6961 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.13146 | 040.2737.91688901 | MEC Forfeiture | -6957.6 | Not Budgeted | - | - | -0.04905% | -6957.6 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12784 | 040.DAN.ABSC 4 STEEL-IND PARK | INSTALL 2000' OF 4" STEEL ON INDUSTRIAL DR IN THE HUNT INDUSTRIAL PARK FOR ABSC | -6881.55 | -18350 | 11468.45 | -62.5% | -0.04851% | -6881.55 | -18350 | 11468.45 | 2005-10-01 | 2006-09-30 | 2005-10-03 | 2005-10-03 | 2005-11-01 | 2005-11-01
| 040.13116 | 040.2737.91653001 | MEC Forfeiture | -6596 | Not Budgeted | - | - | -0.0465% | -6596 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.13074 | 040.2652.916381 | MEC Forfeiture | -6499 | Not Budgeted | - | - | -0.04582% | -6499 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12963 | 040.2737.RodesDevl | MEC Forfeiture | -6136 | Not Budgeted | - | - | -0.04326% | -6136 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.13115 | 040.2737.91655201 | MEC Forfeiture | -5543 | Not Budgeted | - | - | -0.03908% | -5543 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.12990 | 040.2636.0916798 | MEC Forfeiture | -5240 | Not Budgeted | - | - | -0.03694% | -5240 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12935 | 040.P&G Devl | P&G Development Forfeiture | -5239 | Not Budgeted | - | - | -0.03693% | -5239 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.12945 | 040.915852-01 | Keybottom Road 915852-01 Forfeiture | -4644 | Not Budgeted | - | - | -0.03274% | -4644 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.12550 | 040.BGR.EWING FORD PL. | 2" PE EXT. EWING FORD PL. - B.G. | -4517.22 | 16825.78 | -6628.84 | -39.4% | 0.07188% | 10196.94 | 16825.78 | -6628.84 | 2005-10-01 | 2006-09-30 | 2005-04-01 | 2005-04-01 | 2005-07-30 | 2005-07-30
| 040.12943 | 040.ClearCreek | Clear Creek Properties Forfeiture | -4252 | Not Budgeted | - | - | -0.02997% | -4252 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13000 | 040.2734.0915634 | MEC Forfeiture | -3771 | Not Budgeted | - | - | -0.02658% | -3771 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13113 | 040.2651.91681801 | MEC Forfeiture | -3417 | Not Budgeted | - | - | -0.02409% | -3417 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.13112 | 040.2636.091679701 | MEC Forfeiture | -3286 | Not Budgeted | - | - | -0.02316% | -3286 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.12961 | 040.2734.GlasgowIndFound | MEC Forfeiture | -3174 | Not Budgeted | - | - | -0.02238% | -3174 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12992 | 040.2636.0916725 | MEC Forfeiture | -3131 | Not Budgeted | - | - | -0.02207% | -3131 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12941 | 040.RichMorMicJar | R Moraja & M Jarboe Forfeiture | -3092 | Not Budgeted | - | - | -0.0218% | -3092 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.12972 | 040.2635.JohnJoyce | MEC Forfeiture | -3082 | Not Budgeted | - | - | -0.02173% | -3082 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13075 | 040.2652.916448 | MEC Forfeiture | -3065 | Not Budgeted | - | - | -0.02161% | -3065 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12938 | 040.KYLandCo | Kentucky Landmark Co Forfeiture | -3022 | Not Budgeted | - | - | -0.0213% | -3022 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13082 | 040.2737.RETIRE LAND - HARRODS | RETIRE LOT 12 ON MAPLE ST IN HARRODSBURG AND ASSOC ASSETS | -3000 | Not Budgeted | - | - | -0.02115% | -3000 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-25 | 2006-07-25 | 2006-09-30 | 2006-09-30
| 040.13001 | 040.2734.0915492-02 | MEC Forfeiture | -2966 | Not Budgeted | - | - | -0.02091% | -2966 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12982 | 040.2634.WilliamBWest | MEC Forfeiture | -2410 | Not Budgeted | - | - | -0.01699% | -2410 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.12640 | 040.BGR.CRIMSON RIDGE | 2254 FT. OF 2" PE - CRIMSON RIDGE - B.G. | -2322.86 | 3605 | 95.19 | 2.64% | 0.02608% | 3700.19 | 3605 | 95.19 | 2005-10-01 | 2006-09-30 | 2005-07-12 | 2005-07-12 | 2005-09-28 | 2005-09-28
| 040.12969 | 040.2734.RealEstateHold | MEC Forfeiture | -2210 | Not Budgeted | - | - | -0.01558% | -2210 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12936 | 040.Herald Gaddis | Herald Gaddis Forfeiture | -2199 | Not Budgeted | - | - | -0.0155% | -2199 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13117 | 040.2737.91633001 | MEC Forfeiture | -2151.36 | Not Budgeted | - | - | -0.01517% | -2151.36 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.13134 | 040.2634.916842 | MEC Forfeiture | -2052 | Not Budgeted | - | - | -0.01447% | -2052 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.13072 | 040.2652.916626 | MEC Forfeiture | -1997 | Not Budgeted | - | - | -0.01408% | -1997 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.13077 | 040.2652.916382 | MEC Forfeiture | -1985 | Not Budgeted | - | - | -0.01399% | -1985 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12939 | 040.Shelby Christian Ch | Shelby Christian Church Forfeiture | -1955 | Not Budgeted | - | - | -0.01378% | -1955 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.12998 | 040.2734.0916197-02 | MEC Forfeiture | -1844 | Not Budgeted | - | - | -0.013% | -1844 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13114 | 040.2636.91687401 | MEC Forfeiture | -1838 | Not Budgeted | - | - | -0.01296% | -1838 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-08-31
| 040.13137 | 040.2635.916769 | MEC Forfeiture | -1778 | Not Budgeted | - | - | -0.01253% | -1778 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.13004 | 040.2737.0915754-01 | MEC Forfeiture | -1741 | Not Budgeted | - | - | -0.01227% | -1741 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13073 | 040.2652.916625 | MEC Forfeiture | -1673 | Not Budgeted | - | - | -0.01179% | -1673 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12978 | 040.2634.MarkYoung | MEC Forfeiture | -1659 | Not Budgeted | - | - | -0.0117% | -1659 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13140 | 040.2734.91605302 | MEC Forfeiture | -1640 | Not Budgeted | - | - | -0.01156% | -1640 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12993 | 040.2636.0915973 | MEC Forfeiture | -1598 | Not Budgeted | - | - | -0.01127% | -1598 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12947 | 040.916371 | Mayfield 916371 Forfeiture | -1596 | Not Budgeted | - | - | -0.01125% | -1596 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13051 | 040.2737.916771-01 | MEC Forfeiture | -1542 | Not Budgeted | - | - | -0.01087% | -1542 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2006-06-30 | 2006-06-30
| 040.13086 | 040.2739.RETIRE VEH 06897 | RETIRE CHEVY TRUCK #06897 VIN 1GCEC14RXVZ238081 | -1525 | -1 | -1524 | 152400% | -0.01075% | -1525 | -1 | -1524 | 2005-10-01 | 2006-09-30 | 2006-08-02 | 2006-08-02 | 2006-10-01 | 2006-10-01
| 040.12977 | 040.2634.SusanVanover | MEC Forfeiture | -1517 | Not Budgeted | - | - | -0.01069% | -1517 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.12991 | 040.2636.0916713 | MEC Forfeiture | -1488 | Not Budgeted | - | - | -0.01049% | -1488 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13132 | 040.2634.0916857 | MEC Forfeiture | -1413 | Not Budgeted | - | - | -0.009961% | -1413 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12996 | 040.2636.0916404 | MEC Forfeiture | -1406 | Not Budgeted | - | - | -0.009912% | -1406 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12981 | 040.2634.ShirleyVandygriff | MEC Forfeiture | -1395 | Not Budgeted | - | - | -0.009834% | -1395 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13070 | 040.2652.916745 | MEC Forfeiture | -1381 | Not Budgeted | - | - | -0.009735% | -1381 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12989 | 040.2636.0916481 | MEC Forfeiture | -1349 | Not Budgeted | - | - | -0.00951% | -1349 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12999 | 040.2734.0916091-02 | MEC Forfeiture | -1339 | Not Budgeted | - | - | -0.009439% | -1339 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12994 | 040.2636.0916712 | MEC Forfeiture | -1292 | Not Budgeted | - | - | -0.009108% | -1292 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13050 | 040.2636.916816 | MEC Forfeiture | -1262 | Not Budgeted | - | - | -0.008897% | -1262 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2006-06-30 | 2006-06-30
| 040.13007 | 040.2737.0914071-01 | MEC Forfeiture | -1216 | Not Budgeted | - | - | -0.008572% | -1216 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12375 | Paducah 05 Non Growth | Paducah 05 Non Growth | -1198.22 | Not Budgeted | - | - | 3.138% | 445168.43 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.13139 | 040.2734.91673102 | MEC Forfeiture | -1185 | Not Budgeted | - | - | -0.008354% | -1185 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12979 | 040.2634.MorrisHobgood | MEC Forfeiture | -1148 | Not Budgeted | - | - | -0.008093% | -1148 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13055 | 040.2737.916644 | MEC Forfeiture | -1123 | Not Budgeted | - | - | -0.007917% | -1123 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2006-06-30 | 2006-06-30
| 040.13142 | 040.2734.91605102 | MEC Forfeiture | -1099 | Not Budgeted | - | - | -0.007747% | -1099 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12973 | 040.2652.RezaDanesh | MEC Forfeiture | -1080 | Not Budgeted | - | - | -0.007614% | -1080 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.12373 | Owensboro 05 Non Growth | Owensboro 05 Non Growth | -1067.14 | Not Budgeted | - | - | 10.36% | 1469337.62 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.13135 | 040.2635.916793 | MEC Forfeiture | -1065 | Not Budgeted | - | - | -0.007508% | -1065 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.13002 | 040.2734.0915704-02 | MEC Forfeiture | -1023 | Not Budgeted | - | - | -0.007212% | -1023 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.13005 | 040.2737.0915966-01 | MEC Forfeiture | -956 | Not Budgeted | - | - | -0.006739% | -956 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12946 | 040.915872-01 | Fantasy Lane 915872-01 Forfeiture | -873 | Not Budgeted | - | - | -0.006154% | -873 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.12948 | 040.916414 | Princeton 916414 Forfeiture | -825 | Not Budgeted | - | - | -0.005816% | -825 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13078 | 040.2652.916568 | MEC Forfeiture | -812 | Not Budgeted | - | - | -0.005724% | -812 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12828 | 040.OBO.OBO CHRISTIAN CHURCH | RELOCATE 689' 2" STEEL FOR CHURCH EXPANSION | -688.29 | 3374.04 | -4062.33 | -120.4% | -0.004852% | -688.29 | 3374.04 | -4062.33 | 2005-10-01 | 2006-09-30 | 2005-11-21 | 2005-11-21 | 2005-12-16 | 2005-12-16
| 040.13144 | 040.2734.91605202 | MEC Forfeiture | -604 | Not Budgeted | - | - | -0.004258% | -604 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12966 | 040.2734.WhisperingHills | MEC Forfeiture | -595 | Not Budgeted | - | - | -0.004195% | -595 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12967 | 040.2734.PembrokeRd | MEC Forfeiture | -584 | Not Budgeted | - | - | -0.004117% | -584 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.13133 | 040.2634.916482 | MEC Forfeiture | -580 | Not Budgeted | - | - | -0.004089% | -580 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12968 | 040.2734.SequoiaSt | MEC Forfeiture | -570 | Not Budgeted | - | - | -0.004018% | -570 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.13080 | 040.2638.916747 | MEC Forfeiture | -553 | Not Budgeted | - | - | -0.003898% | -553 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.13136 | 040.2635.916919 | MEC Forfeiture | -546 | Not Budgeted | - | - | -0.003849% | -546 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.13071 | 040.2652.916657 | MEC Forfeiture | -538 | Not Budgeted | - | - | -0.003793% | -538 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.13149 | 040.2737.91685301 | MEC Forfeiture | -534 | Not Budgeted | - | - | -0.003764% | -534 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.13052 | 040.2737.916740-01 | MEC Forfeiture | -493 | Not Budgeted | - | - | -0.003475% | -493 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2006-06-30 | 2006-06-30
| 040.12759 | 040.OBO.WOOD LAND PLAZA | INSTALL 1400' 2" PE | -475.85 | Not Budgeted | - | - | -0.003355% | -475.85 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-09-30 | 2005-09-30 | 2005-11-25 | 2005-11-25
| 040.11953 | Owen.04.Non Grow Func | Owensboro.04.Non Growth Functional | -465.86 | Not Budgeted | - | - | 13.32% | 1890123.33 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-06-03 | 2005-06-03 | 2005-06-03 | 2005-06-03
| 040.12962 | 040.2737.KevinCooley | MEC Forfeiture | -451 | Not Budgeted | - | - | -0.003179% | -451 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12937 | 040.BradVictMur | Brad & Victoria Murphy Forfeiture | -449 | Not Budgeted | - | - | -0.003165% | -449 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13008 | 040.2737.0916242-01 | MEC Forfeiture | -406 | Not Budgeted | - | - | -0.002862% | -406 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12655 | 040.OBO.Whispering Meadows | INSTALL 364' 4" PE | -370.3 | 16275.66 | -13325.01 | -81.87% | 0.0208% | 2950.65 | 16275.66 | -13325.01 | 2005-10-01 | 2006-09-30 | 2005-08-08 | 2005-08-08 | 2005-08-26 | 2005-08-26
| 040.13131 | 040.2634.0916707 | MEC Forfeiture | -351 | Not Budgeted | - | - | -0.002474% | -351 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12980 | 040.2634.CarlosTatum | MEC Forfeiture | -318 | Not Budgeted | - | - | -0.002242% | -318 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.13145 | 040.2737.91681301 | MEC Forfeiture | -302 | Not Budgeted | - | - | -0.002129% | -302 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.11936 | Bowling Green.04.Gr Func | Bowling Green.04.Gr Func | -301.74 | Not Budgeted | - | - | 9.517% | 1350031.64 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12940 | 040.JamesMShuck | James M Shuck Forfeiture | -299 | Not Budgeted | - | - | -0.002108% | -299 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.12800 | 040.OBO.RALPH AVE.RELOC. | INSTALL 615' 2"PE RETIRES 2" STEEL | -282.91 | Not Budgeted | - | - | -0.001994% | -282.91 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-25 | 2005-10-25 | 2005-11-30 | 2005-11-30
| 040.13054 | 040.2737.916444-01 | MEC Forfeiture | -278 | Not Budgeted | - | - | -0.00196% | -278 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2006-06-30 | 2006-06-30
| 040.13143 | 040.2734.91607502 | MEC Forfeiture | -276 | Not Budgeted | - | - | -0.001946% | -276 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12259 | 040.2609.ODORTANK DISP WEST | DISPOSAL OF 10 ODORANT TANKS AND 4 DRUMS AND MISC ITEMS | -273.49 | 98207 | -40036.77 | -40.77% | 0.4101% | 58170.23 | 98207 | -40036.77 | 2005-10-01 | 2006-09-30 | 2004-06-18 | 2004-06-18 | 2004-12-30 | 2004-12-30
| 040.12258 | 040.2609.ODORTANK DISP EAST | DISPOSAL OF 12 ODORANT TANKS | -228.49 | 96187 | -47525.01 | -49.41% | 0.343% | 48661.99 | 96187 | -47525.01 | 2005-10-01 | 2006-09-30 | 2004-06-18 | 2004-06-18 | 2004-12-30 | 2004-12-30
| 040.13006 | 040.2737.0915967-01 | MEC Forfeiture | -221 | Not Budgeted | - | - | -0.001558% | -221 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-24 | 2006-03-24 | 2006-03-24 | 2006-03-24
| 040.12361 | Hopkinsville 05 Non Growth | Hopkinsville 05 Non Growth | -204.68 | Not Budgeted | - | - | 2.256% | 320059.85 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12145 | 040.SHV.LAW.EAGLE LAKE RELOC | RELOCATE 1500' OF 6" HIGH PRESSURE STEEL AT 151 & 127 EAGLE LAKE | -188.32 | 51200 | 94065.78 | 183.7% | 1.024% | 145265.78 | 51200 | 94065.78 | 2005-10-01 | 2006-09-30 | 2005-05-02 | 2005-05-02 | 2005-05-02 | 2005-05-02
| 040.12974 | 040.2652.WilliamsConstruction | MEC Forfeiture | -181 | Not Budgeted | - | - | -0.001276% | -181 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-15 | 2006-03-15 | 2006-03-31 | 2006-03-31
| 040.12334 | 040.PAD.Plantation Village Ext | 2,060' - 2" P.E Revenue Extension for Mike Falconite/ 54 residential lots | -173.4 | 9294.23 | 490.81 | 5.281% | 0.06898% | 9785.04 | 9294.23 | 490.81 | 2005-10-01 | 2006-09-30 | 2004-08-31 | 2004-08-31 | 2005-04-18 | 2005-04-18
| 040.13081 | 040.2638.916783 | MEC Forfeiture | -134 | Not Budgeted | - | - | -0.0009446% | -134 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.13079 | 040.2638.916757 | MEC Forfeiture | -126 | Not Budgeted | - | - | -0.0008882% | -126 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-07-21 | 2006-07-21
| 040.12333 | 040.PAD.Holt Road Sys Imp | Install 620' - 2" P.E to tie two systems together | -107.89 | 4650.77 | 1273.95 | 27.39% | 0.04177% | 5924.72 | 4650.77 | 1273.95 | 2005-10-01 | 2006-09-30 | 2004-08-30 | 2004-08-30 | 2005-04-18 | 2005-04-18
| 040.12964 | 040.2737.Gene Middleton | MEC Forfeiture | -100 | Not Budgeted | - | - | -0.000705% | -100 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-03-31 | 2006-03-31
| 040.12944 | 040.915733-01 | Green Oaks 915733-01 Forfeiture | -52 | Not Budgeted | - | - | -0.0003666% | -52 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-02-28 | 2006-02-28
| 040.13148 | 040.2737.91682301 | MEC Forfeiture | -49 | Not Budgeted | - | - | -0.0003454% | -49 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-30 | 2006-09-30 | 2006-10-01 | 2006-10-01
| 040.12615 | AKY.TCSSVC.MEAS.EFM.TOYOTETSU | EFM INSTALLATION @ TOYOTETSU MID AMERICA | -37.38 | 5521.24 | 3002.62 | 54.38% | 0.06009% | 8523.86 | 5521.24 | 3002.62 | 2005-10-01 | 2006-09-30 | 2005-06-21 | 2005-06-21 | 2005-09-28 | 2005-09-28
| 040.13025 | 040.2636.0915977 | MEC Forfeiture | -33 | Not Budgeted | - | - | -0.0002326% | -33 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-05-02 | 2006-05-02 | 2006-05-02 | 2006-05-02
| 040.12508 | 040.PAD.Ken-Bar Boiler Install | This project is for the installation of boiler at Ken-Bar purchase station | -15.96 | 10186.6 | 3070.73 | 30.14% | 0.09346% | 13257.33 | 10186.6 | 3070.73 | 2005-10-01 | 2006-09-30 | 2005-01-12 | 2005-01-12 | 2005-04-29 | 2005-04-29
| 040.12637 | aky.tcssvc.meas.Amfine EFM | Installation of EFM @ Amfine Chemical | -13.88 | 5521.24 | 3334.86 | 60.4% | 0.06243% | 8856.1 | 5521.24 | 3334.86 | 2005-10-01 | 2006-09-30 | 2005-07-11 | 2005-07-11 | 2005-09-28 | 2005-09-28
| 040.12592 | Aky.Tcssvc.Meas.New Mather | EFM Installation @ New Mather Metal | -7.3 | 5521.24 | -942.53 | -17.07% | 0.03228% | 4578.71 | 5521.24 | -942.53 | 2005-10-01 | 2006-09-30 | 2005-05-26 | 2005-05-26 | 2005-09-28 | 2005-09-28
| 040.12577 | Aky.Tcssvc.Meas.EFM.TWN | Installation of EFM @ TWN Fasteners | -6.05 | 5521.24 | -1724.59 | -31.24% | 0.02676% | 3796.65 | 5521.24 | -1724.59 | 2005-10-01 | 2006-09-30 | 2005-05-09 | 2005-05-09 | 2005-09-28 | 2005-09-28
| 040.12642 | aky.tcssvc.meas.Holly EFM | Installation of EFM @ Holly Performance Prod. | -5.51 | 5521.24 | -1906.48 | -34.53% | 0.02548% | 3614.76 | 5521.24 | -1906.48 | 2005-10-01 | 2006-09-30 | 2005-07-12 | 2005-07-12 | 2005-09-28 | 2005-09-28
| 040.12522 | 040.TCSVS.MEAS.ICT EFM | EFM INSTALLATION @ ICT | -0.14 | 5521.25 | 423.57 | 7.672% | 0.04191% | 5944.82 | 5521.25 | 423.57 | 2005-10-01 | 2006-09-30 | 2005-02-07 | 2005-02-07 | 2005-07-29 | 2005-07-29
| 040.12679 | 040.SHV.DUMP BED - 2 TON TRUCK | INSTALL DUNP BED ON 2 TON TRUCK | 0 | 24300 | -13266.46 | -54.59% | 0.07778% | 11033.54 | 24300 | -13266.46 | 2005-10-01 | 2006-09-30 | 2005-09-22 | 2005-09-22 | 2005-10-01 | 2005-10-01
| 040.12836 | Shetland Hills #2 MEC Forf | MEC Forfeiture Eastern Hill Developer | 0 | Not Budgeted | - | - | -0.04481% | -6357 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-12-01 | 2005-12-01 | 2005-12-30 | 2005-12-30
| 040.12566 | 040.SHV.CARRINGTON PLACE III | INSTALL 600' OF 2" PE FOR 36 UNITS AT CARRINGTON PLACE | 3.2 | 5835 | -5756.71 | -98.66% | 0.0005519% | 78.29 | 5835 | -5756.71 | 2005-10-01 | 2006-09-30 | 2005-04-21 | 2005-04-21 | 2005-05-30 | 2005-05-30
| 040.12653 | 040.PAD.Krebs Sta Rd Rev Ext | Install 200' - 2" P.E for one new residential customer | 5.85 | 2514.02 | -2353.61 | -93.62% | 0.001131% | 160.41 | 2514.02 | -2353.61 | 2005-10-01 | 2006-09-30 | 2005-08-02 | 2005-08-02 | 2005-09-23 | 2005-09-23
| 040.12542 | 040.BGR.REG.PARTS/INSPEC | REGULATOR PARTS / INSPECTION - B.G. | 7.08 | 24750 | -12099.78 | -48.89% | 0.08918% | 12650.22 | 24750 | -12099.78 | 2005-10-01 | 2006-09-30 | 2005-03-21 | 2005-03-21 | 2005-09-28 | 2005-09-28
| 040.12546 | 040.PTON.E Noel Dr Rev Ext II | 1,050' main extension from Chasity Ln to new unnamed rd off E Noel for Dennis Th | 22.84 | 968.24 | 1778.77 | 183.7% | 0.01937% | 2747.01 | 968.24 | 1778.77 | 2005-10-01 | 2006-09-30 | 2005-03-23 | 2005-03-23 | 2005-06-30 | 2005-06-30
| 040.12821 | 040.OBO.LITTLE HICKORY RD. | INSTALL 290' 2" PE | 28.65 | Not Budgeted | - | - | 0.000202% | 28.65 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-11-14 | 2005-11-14 | 2005-11-25 | 2005-11-25
| 040.13033 | 040.BGR.HOP.AMBULATORY CTR | 300 FT. OF 4" PE - EAGLE BYPASS - AMBULATORY CTR. - HOPK. | 29.27 | 2318 | -2261.01 | -97.54% | 0.0004018% | 56.99 | 2318 | -2261.01 | 2005-10-01 | 2006-09-30 | 2006-05-23 | 2006-05-23 | 2006-09-28 | 2006-09-28
| 040.12579 | Aky.Tcsvc.EFM. State ICF | Install EFM @ State ICF | 39.52 | 5521.24 | -2823.61 | -51.14% | 0.01902% | 2697.63 | 5521.24 | -2823.61 | 2005-10-01 | 2006-09-30 | 2005-05-09 | 2005-05-09 | 2005-09-28 | 2005-09-28
| 040.12262 | 040.BGR.FRK KV REPLC W. MAD. | WEST MADISON & JOHN J. JOHNSON KV REPLC. - FRANKLIN | 39.66 | 18547 | -6450.67 | -34.78% | 0.08527% | 12096.33 | 18547 | -6450.67 | 2005-10-01 | 2006-09-30 | 2004-06-21 | 2004-06-21 | 2005-04-18 | 2005-04-18
| 040.12651 | 040.MAD.GREENVILLE GROUNDBED | INSTALL NEW RECTIFIER & GROUNDBED | 40.04 | 36979.8 | -12612.85 | -34.11% | 0.1718% | 24366.95 | 36979.8 | -12612.85 | 2005-10-01 | 2006-09-30 | 2005-08-01 | 2005-08-01 | 2005-09-23 | 2005-09-23
| 040.12358 | Glasgow 05 Growth | Glasgow 05 Growth | 51.78 | Not Budgeted | - | - | 1.312% | 186132.4 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.13091 | 040.BGR.GLS.MONTESSORI ACADEMY | 550 FT. OF 2'PE - MONTESSORI ACADEMY - GLASGOW | 55.28 | 2504.84 | -2449.56 | -97.79% | 0.0003897% | 55.28 | 2504.84 | -2449.56 | 2005-10-01 | 2006-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 040.12366 | Shelbyville 05 Growth | Shelbyville 05 Growth | 68.35 | Not Budgeted | - | - | 2.938% | 416803.53 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12371 | Princeton 05 Non Growth | Princeton 05 Non Growth | 69.72 | Not Budgeted | - | - | 1.059% | 150164.46 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12367 | Shelbyville 05 Non Growth | Shelbyville 05 Non Growth | 79.8 | Not Budgeted | - | - | 1.628% | 230938.6 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12645 | 040.Storage Anodes | Install anodes on the Hartford/Beaver Dam Line | 81.9 | 7055 | -4799.91 | -68.04% | 0.0159% | 2255.09 | 7055 | -4799.91 | 2005-10-01 | 2006-09-30 | 2005-07-13 | 2005-07-13 | 2005-09-28 | 2005-09-28
| 040.12362 | Danville 05 Growth | Danville 05 Growth | 82.21 | Not Budgeted | - | - | 2.051% | 290919.06 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12376 | Mayfield 05 Growth | Mayfield 05 Non Growth | 83.86 | Not Budgeted | - | - | 0.7321% | 103846.76 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12587 | 040.BGR.HOPK.FARM TAP REG. | FARM TAP REG. STAT & EFV - HOPKINSVILLE AREA | 90.18 | 41949 | -14447.53 | -34.44% | 0.1939% | 27501.47 | 41949 | -14447.53 | 2005-10-01 | 2006-09-30 | 2005-05-20 | 2005-05-20 | 2005-09-28 | 2005-09-28
| 040.12363 | Danville 05 Non Growth | Danville 05 Non Growth | 97.7 | Not Budgeted | - | - | 3.179% | 451003.86 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.13093 | 040.2715.TBS REGULATOR REPLACE | REPLACE REGULATORS AND RESTRICTORS AT TBS | 140.65 | 15000 | -2217.15 | -14.78% | 0.09011% | 12782.85 | 15000 | -2217.15 | 2005-10-01 | 2006-09-30 | 2006-08-10 | 2006-08-10 | 2007-08-08 | 2007-08-08
| 040.12365 | Campbellsville 05 Non Growth | Campbellsville 05 Non Growth | 149.13 | Not Budgeted | - | - | 3.479% | 493477.76 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12364 | Campbellsville 05 Growth | Campbellsville 05 Growth | 152.39 | Not Budgeted | - | - | 0.8882% | 125997.82 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12614 | 040.PAD.Lydon Rd Rev Ext | 800' - 2" PE pipe for four existing customers and one new construction | 164.24 | 2525 | 2097.78 | 83.08% | 0.03259% | 4622.78 | 2525 | 2097.78 | 2005-10-01 | 2006-09-30 | 2005-06-21 | 2005-06-21 | 2005-09-23 | 2005-09-23
| 040.12270 | 040.BGR.10TH 3" BARE RET. | RETIRE 550' OF 3" BARE - 100 BLK. 10TH.- B.G. | 175.89 | Not Budgeted | - | - | 0.00124% | 175.89 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2004-06-23 | 2004-06-23 | 2005-05-04 | 2005-05-04
| 040.12551 | 040.PAD.Walden Subd Rev Ext | 950' - 2" PE along Walt Defreitas Dr for 9 lots | 196.33 | 4274.81 | 1130.64 | 26.45% | 0.03811% | 5405.45 | 4274.81 | 1130.64 | 2005-10-01 | 2006-09-30 | 2004-05-14 | 2004-05-14 | 2005-09-23 | 2005-09-23
| 040.12369 | Madisonville 05 Non Growth | Madisonville 05 Non Growth | 250.96 | Not Budgeted | - | - | 4.749% | 673666.4 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12372 | Owensboro 05 Growth | Ownesboro 05 Growth | 254.11 | Not Budgeted | - | - | 3.44% | 487910.59 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12374 | Paducah 05 Growth | Paducah 05 Growth | 259.22 | Not Budgeted | - | - | 2.191% | 310736.8 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12805 | 040.BGR.HOP.BURLEY DR. EXT | 800 FT. OF 2" PE - BURLEY DR. - DOT'S RESTAURANT - B.G. | 287.62 | 2277 | -1989.38 | -87.37% | 0.002028% | 287.62 | 2277 | -1989.38 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2005-09-28 | 2005-09-28
| 040.12401 | 040.tcsvc.Meas.Rotary Meters | Dresser Rotary Meters | 295.71 | 59150 | -7365.3 | -12.45% | 0.3651% | 51784.7 | 59150 | -7365.3 | 2005-10-01 | 2006-09-30 | 2004-10-19 | 2004-10-19 | 2005-07-15 | 2005-07-15
| 040.12377 | Mayfield 05 Non Growth | Mayfield 05 Non Growth | 344.99 | Not Budgeted | - | - | 1.602% | 227199.87 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12630 | 040.MAD.Meadowbrook Estates | INSTALL 2,412' 2" PE | 384.95 | 15493.72 | -6082.17 | -39.26% | 0.06635% | 9411.55 | 15493.72 | -6082.17 | 2005-10-01 | 2006-09-30 | 2005-07-05 | 2005-07-05 | 2005-09-14 | 2005-09-14
| 040.12359 | Glasgow 05 Non Growth | Glasgow 05 Non Growth | 408.56 | Not Budgeted | - | - | 4.136% | 586771.84 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12838 | 040.OBO.Pleasant Valley Rd. | Install 885' 2" Pe | 416.23 | 699.26 | -283.03 | -40.48% | 0.002934% | 416.23 | 699.26 | -283.03 | 2005-10-01 | 2006-09-30 | 2005-12-05 | 2005-12-05 | 2006-01-18 | 2006-01-18
| 040.13087 | 040.MAD.PRITCHETT AVE. | RETIRE 1 1/4" PE 455' | 429.86 | 522.35 | -92.49 | -17.71% | 0.00303% | 429.86 | 522.35 | -92.49 | 2005-10-01 | 2006-09-30 | 2006-08-08 | 2006-08-08 | 2006-08-11 | 2006-08-11
| 040.12597 | 040.DAN.EQUIPMENT 6-2005 | PURCHASE 7-PE SQUEEZE OFF 1",1-PE SQUEEZE OFF 2",2-CGI SENSI GOLD,1-LINE LOCATOR | 468.99 | 17750 | -4676.15 | -26.34% | 0.09217% | 13073.85 | 17750 | -4676.15 | 2005-10-01 | 2006-09-30 | 2005-06-20 | 2005-06-20 | 2005-06-23 | 2005-06-23
| 040.12612 | 040.BGR.GARY FARMS 2" EXT | 3200 FT. OF 2" PE - GARY FARMS - B.G. | 496.35 | 9848 | 148.04 | 1.503% | 0.07047% | 9996.04 | 9848 | 148.04 | 2005-10-01 | 2006-09-30 | 2005-06-17 | 2005-06-17 | 2005-09-28 | 2005-09-28
| 040.12582 | 040 PAD.Carriage Park Rev Ext | Install 2,800' 2" PE in Carriage Park Subd off Steele Rd for Sharon Sanderson | 504.89 | 13031.92 | 869.45 | 6.672% | 0.098% | 13901.37 | 13031.92 | 869.45 | 2005-10-01 | 2006-09-30 | 2005-05-09 | 2005-05-09 | 2005-09-23 | 2005-09-23
| 040.12816 | 040.OBO.TRAIL-A-WAY RETIREMENT | RETIRE ,1362' 2"PE,84' 2" STL. | 534.06 | 320.56 | 213.5 | 66.6% | 0.003765% | 534.06 | 320.56 | 213.5 | 2005-10-01 | 2006-09-30 | 2005-11-07 | 2005-11-07 | 2005-11-18 | 2005-11-18
| 040.12260 | 040.BGR.FRK.COLLEGE ST REPLC | 900 FT. OF 2" PE - COLLEGE ST. REPLC. - FRANKLIN | 537.39 | 25319 | -12860.31 | -50.79% | 0.08783% | 12458.69 | 25319 | -12860.31 | 2005-10-01 | 2006-09-30 | 2004-06-18 | 2004-06-18 | 2005-04-18 | 2005-04-18
| 040.12413 | 040.OBO.ALVEY PARK DRIVE | INSTALL 813' 2" PE | 556 | 3345.53 | -283.66 | -8.479% | 0.02158% | 3061.87 | 3345.53 | -283.66 | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12559 | 040.OBO.2005 REG INSPECTIONS | 2005 REG.INSPECTIONS | 591.66 | 74657 | 272.17 | 0.3646% | 0.5282% | 74929.17 | 74657 | 272.17 | 2005-10-01 | 2006-09-30 | 2005-04-11 | 2005-04-11 | 2005-09-28 | 2005-09-28
| 040.12613 | 040.MAY.Meadow Subd Rev Ext | 3,690' - 2" PE for 43 new residential lots | 596.44 | 14484.86 | 1935.86 | 13.36% | 0.1158% | 16420.72 | 14484.86 | 1935.86 | 2005-10-01 | 2006-09-30 | 2005-06-20 | 2005-06-20 | 2005-09-23 | 2005-09-23
| 040.12600 | 040.BGR.GLS.MISC EQUIP | SQUEEZE OFF TOOL & SENSIT GOLD - GLASGOW | 603.86 | 15111 | -5081.43 | -33.63% | 0.0707% | 10029.57 | 15111 | -5081.43 | 2005-10-01 | 2006-09-30 | 2005-06-07 | 2005-06-07 | 2005-09-28 | 2005-09-28
| 040.13061 | 040.MAY.Meadows II | Meadows Subd Rev Ext II 200' for 2 new res lots John Smith | 618.32 | 1202.28 | -583.96 | -48.57% | 0.004359% | 618.32 | 1202.28 | -583.96 | 2005-10-01 | 2006-09-30 | 2006-07-18 | 2006-07-18 | 2006-09-22 | 2006-09-22
| 040.12360 | Hopkinsville 05 Growth | Hopkinsville 05 Growth | 652.65 | Not Budgeted | - | - | 0.888% | 125962.79 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12368 | Madisonville 05 Growth | Madisonville 05 Growth | 720.29 | Not Budgeted | - | - | 1.193% | 169286.52 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12604 | 040.BGR.RUSS. FARM TAP/EFV | FARM tAPS & EFV - RUSSELLVILLE AREA | 729.02 | 27150 | -12469 | -45.93% | 0.1035% | 14681 | 27150 | -12469 | 2005-10-01 | 2006-09-30 | 2005-06-08 | 2005-06-08 | 2005-09-28 | 2005-09-28
| 040.12668 | aky.tcsvc.meas.Teledyne | Retirement of Teledyne Forklift | 736.64 | -5955 | 6751.86 | -113.4% | 0.005618% | 796.86 | -5955 | 6751.86 | 2005-10-01 | 2006-09-30 | 2005-08-23 | 2005-08-23 | 2005-09-23 | 2005-09-23
| 040.12599 | 040.BGR.MISC. EQUIP - B.G | SQUEEZE OFF TOOLS & LINE LOCATORS - B.G. | 790.84 | 20482 | 15191.98 | 74.17% | 0.2515% | 35673.98 | 20482 | 15191.98 | 2005-10-01 | 2006-09-30 | 2005-06-07 | 2005-06-07 | 2005-09-28 | 2005-09-28
| 040.12641 | Marker Post | Install additional marker post on right-of-ways | 817.15 | 24800 | -2308.29 | -9.308% | 0.1586% | 22491.71 | 24800 | -2308.29 | 2005-10-01 | 2006-09-30 | 2005-07-12 | 2005-07-12 | 2005-09-28 | 2005-09-28
| 040.12351 | 040.PAD.Ken-Bar Boiler | This project is to purchase boiler only. Seperate project for installation | 822.45 | 18025.82 | -15478.09 | -85.87% | 0.01796% | 2547.73 | 18025.82 | -15478.09 | 2005-10-01 | 2006-09-30 | 2004-09-20 | 2004-09-20 | 2005-04-18 | 2005-04-18
| 040.12666 | 040.BGR.RUSS.WILHELM RD, 2" PE | 150 FT. OF 2" PE - WILHELM RD. - RUSS | 907.35 | 1886 | -978.65 | -51.89% | 0.006396% | 907.35 | 1886 | -978.65 | 2005-10-01 | 2006-09-30 | 2005-08-19 | 2005-08-19 | 2005-09-28 | 2005-09-28
| 040.12646 | 040.SHV.NOTTING HILLS PH 1a | INSTALL 3300' OF 2" PE, 1500' OF 4" PE AND REG STATION FOR NOTTING HILLS PH 1a | 935.38 | 80100 | -6160.31 | -7.691% | 0.5212% | 73939.69 | 80100 | -6160.31 | 2005-10-01 | 2006-09-30 | 2005-07-15 | 2005-07-15 | 2005-08-15 | 2005-08-15
| 040.13032 | 040.2737.COLONIAL WAY | INSTALL 1750' OF 2" PE ON POPPY COURT, GRABRUK AND COLONIAL WAY | 963.82 | 7500 | -1418.15 | -18.91% | 0.04287% | 6081.85 | 7500 | -1418.15 | 2005-10-01 | 2006-09-30 | 2006-05-23 | 2006-05-23 | 2006-09-28 | 2006-09-28
| 040.13035 | 040.PAD.Brush Cutter | Purchase D R Trimmer/mower | 1037.22 | 816.2 | 221.02 | 27.08% | 0.007312% | 1037.22 | 816.2 | 221.02 | 2005-10-01 | 2006-09-30 | 2006-05-26 | 2006-05-26 | 2006-09-22 | 2006-09-22
| 040.12644 | aky.tcsvc.meas.Moisture An. | Portable moisture analyzer | 1061.44 | 14396 | 174.13 | 1.21% | 0.1027% | 14570.13 | 14396 | 174.13 | 2005-10-01 | 2006-09-30 | 2005-07-13 | 2005-07-13 | 2005-09-28 | 2005-09-28
| 040.12278 | 040.Mea.Tecsvc.Regulators | Regulators for engineered applications | 1067.94 | 23760 | -6120.85 | -25.76% | 0.1243% | 17639.15 | 23760 | -6120.85 | 2005-10-01 | 2006-09-30 | 2004-07-06 | 2004-07-06 | 2006-03-31 | 2006-03-31
| 040.12788 | 040.MAY.N St Paul St Rev Ext | 100' 2"P extension for one customer ( Roy Bunch) | 1082.79 | 1543.9 | -517.56 | -33.52% | 0.007235% | 1026.34 | 1543.9 | -517.56 | 2005-10-01 | 2006-09-30 | 2005-10-11 | 2005-10-11 | 2006-09-22 | 2006-09-22
| 040.12634 | 040.BGR.OXFORD CENTER | 3293 FT. OF 2" PE - OXFORD CENTER COMMERCIAL - B.G. | 1149.46 | 4249.71 | 3287.61 | 77.36% | 0.05313% | 7537.32 | 4249.71 | 3287.61 | 2005-10-01 | 2006-09-30 | 2005-07-08 | 2005-07-08 | 2005-09-28 | 2005-09-28
| 040.12953 | 040.2738.SPRINGVIEW MED-LEB | INSTALL 400' OF 2" PE FOR SPRINGVIEW MEDICAL CENTER IN LEBANON | 1150.94 | 3900 | -2749.06 | -70.49% | 0.008114% | 1150.94 | 3900 | -2749.06 | 2005-10-01 | 2006-09-30 | 2006-02-17 | 2006-02-17 | 2006-02-17 | 2006-02-17
| 040.12198 | 040.OBO.FARMTAP PROJECT | CHANGING OVER FARMTAPS | 1171.4 | 117910.09 | 59627.05 | 50.57% | 1.252% | 177537.14 | 117910.09 | 59627.05 | 2005-10-01 | 2006-09-30 | 2004-05-12 | 2004-05-12 | 2005-09-28 | 2005-09-28
| 040.12426 | aky.tcssvc.meas.regulators | Regulators for engineered applications | 1226.72 | 24986 | 8479.98 | 33.94% | 0.2359% | 33465.98 | 24986 | 8479.98 | 2005-10-01 | 2006-09-30 | 2004-12-01 | 2004-12-01 | 2005-09-28 | 2005-09-28
| 040.12924 | 040.MAY.Terri-Aire Ext | Install 685 ' North along Terri-Aire Drive from Lake Terry Drive. One new custo. | 1267.16 | 2036.1 | -768.94 | -37.77% | 0.008933% | 1267.16 | 2036.1 | -768.94 | 2005-10-01 | 2006-09-30 | 2006-01-23 | 2006-01-23 | 2006-09-22 | 2006-09-22
| 040.13058 | 040.OBO Mount Moriah Avenue | Install 100' 1 1/4" PE | 1322.42 | 1656.01 | -261.98 | -15.82% | 0.009827% | 1394.03 | 1656.01 | -261.98 | 2005-10-01 | 2006-09-30 | 2006-07-05 | 2006-07-05 | 2006-09-22 | 2006-09-22
| 040.12590 | 040.OBO.MISC. EQUIPMENT | PE&STL. SQUEEZE OFF TOOLS,LINE LOCATORS | 1333.41 | 48094.2 | 1549.55 | 3.222% | 0.35% | 49643.75 | 48094.2 | 1549.55 | 2005-10-01 | 2006-09-30 | 2005-05-25 | 2005-05-25 | 2005-06-14 | 2005-06-14
| 040.12526 | 040.PAD. Reg Sta - Sys Int | Project to cover new regulator parts & labor for FY '05 | 1408.96 | 49585.8 | -5575.82 | -11.24% | 0.3103% | 44009.98 | 49585.8 | -5575.82 | 2005-10-01 | 2006-09-30 | 2004-05-14 | 2004-05-14 | 2005-09-23 | 2005-09-23
| 040.12595 | 040.MAY.Misc Work Equip | Pls and steel squeeze-off tools | 1519.58 | 34400 | -11780.41 | -34.25% | 0.1595% | 22619.59 | 34400 | -11780.41 | 2005-10-01 | 2006-09-30 | 2005-05-27 | 2005-05-27 | 2005-09-23 | 2005-09-23
| 040.12422 | 040.PAD.Perkins Creek Rev Ext | Seven new commercial lots being developed by Mike Falconite adjacent being devel | 1582 | 4168.97 | 5157.85 | 123.7% | 0.06575% | 9326.82 | 4168.97 | 5157.85 | 2005-10-01 | 2006-09-30 | 2004-11-23 | 2004-11-23 | 2005-05-27 | 2005-05-27
| 040.12799 | 040.MAY.N Sutton Ln Ext | Install 325' - 2" PE for one existing home & one exist mobile home | 1630.89 | 1074 | 587.11 | 54.67% | 0.01171% | 1661.11 | 1074 | 587.11 | 2005-10-01 | 2006-09-30 | 2005-10-24 | 2005-10-24 | 2006-09-22 | 2006-09-22
| 040.12594 | 040.PAD.Misc Work Equip | Pls and steel squeeze-off tools | 1714.91 | 26389 | -1512.62 | -5.732% | 0.1754% | 24876.38 | 26389 | -1512.62 | 2005-10-01 | 2006-09-30 | 2005-05-27 | 2005-05-27 | 2005-09-23 | 2005-09-23
| 040.12757 | 040.OBO.HIGHLAND GARDEN POINTE | INSTALL 403' 2" PE | 1764.68 | 2832.24 | -1067.56 | -37.69% | 0.01244% | 1764.68 | 2832.24 | -1067.56 | 2005-10-01 | 2006-09-30 | 2005-09-30 | 2005-09-30 | 2005-11-25 | 2005-11-25
| 040.13011 | 040.OBO.LIVIA RETIREMENT | RETIRE OLD LONDON ALUMINUM LINE | 1812.37 | 2445.76 | -633.39 | -25.9% | 0.01278% | 1812.37 | 2445.76 | -633.39 | 2005-10-01 | 2006-09-30 | 2006-03-28 | 2006-03-28 | 2006-04-21 | 2006-04-21
| 040.12601 | 040.BGR.HOP.MISC EQUIP | SQUEEZE OFF TOOLS & LINE LOCATORS - HOPKINSVILLE | 1831.73 | 20335 | 22804.1 | 112.1% | 0.3041% | 43139.1 | 20335 | 22804.1 | 2005-10-01 | 2006-09-30 | 2005-06-07 | 2005-06-07 | 2005-09-28 | 2005-09-28
| 040.12958 | 040.MAD.BLAKE RICHEY GRNVILLE | INSTALL 520' 2" PE | 1873.59 | 1472.54 | 401.05 | 27.24% | 0.01321% | 1873.59 | 1472.54 | 401.05 | 2005-10-01 | 2006-09-30 | 2006-03-03 | 2006-03-03 | 2006-03-30 | 2006-03-30
| 040.12215 | 040.SHV.EH-5 MUELLER TAP EQUIP | EH-5 MUELLER TAPPING EQUIPMENT | 1902.63 | 12200 | 5063.96 | 41.51% | 0.1217% | 17263.96 | 12200 | 5063.96 | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.12926 | 040.MAD.PIN OAK DR. | INSTALL 133' 2' PE | 1918.2 | 1280.8 | 637.4 | 49.77% | 0.01352% | 1918.2 | 1280.8 | 637.4 | 2005-10-01 | 2006-09-30 | 2006-01-24 | 2006-01-24 | 2006-02-17 | 2006-02-17
| 040.12618 | 040.PTON.Crayne Sys Imp | Install sm capacity regulator, 2,500' - 2" PE, convert 18 services from HPD to d | 1949.94 | 37180.73 | 398.1 | 1.071% | 0.2649% | 37578.83 | 37180.73 | 398.1 | 2005-10-01 | 2006-09-30 | 2005-06-22 | 2005-06-22 | 2005-09-23 | 2005-09-23
| 040.12925 | 040.MAY.Shelby Ln Extension | Install 350' - 2" P along Shelby Ln for one new res. customer | 1955.25 | 1106.01 | 849.24 | 76.78% | 0.01378% | 1955.25 | 1106.01 | 849.24 | 2005-10-01 | 2006-09-30 | 2006-01-23 | 2006-01-23 | 2006-09-22 | 2006-09-22
| 040.13034 | 040.BGR.SUTHERLAND FARMS II-B | 1395 FT. OF 2" PE - SUTHERLAND FARMS II-B - B.G. | 1979 | 5667 | -3660.28 | -64.59% | 0.01415% | 2006.72 | 5667 | -3660.28 | 2005-10-01 | 2006-09-30 | 2006-05-25 | 2006-05-25 | 2006-09-28 | 2006-09-28
| 040.12797 | 040.PAD.5th Ave Main Ext | Install 250' - 2" PE in order to relocate double meter loop in the way of new li | 2071.54 | Not Budgeted | - | - | 0.0146% | 2071.54 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-20 | 2005-10-20 | 2006-09-22 | 2006-09-22
| 040.13045 | 040.PTON.Washington St Replace | In alley behind Washington Street install 310' - 2" PE; retire 315' - 2" | 2079.65 | 13355.49 | -7790.44 | -58.33% | 0.03923% | 5565.05 | 13355.49 | -7790.44 | 2005-10-01 | 2006-09-30 | 2006-06-21 | 2006-06-21 | 2006-09-22 | 2006-09-22
| 040.12606 | 040.MAD.BEAN CEMETERY RD. | INSTALL 2,120' 4" STL. | 2112.01 | 143555.5 | 18508.41 | 12.89% | 1.142% | 162063.91 | 143555.5 | 18508.41 | 2005-10-01 | 2006-09-30 | 2005-06-10 | 2005-06-10 | 2005-10-28 | 2005-10-28
| 040.12648 | 040.DAN.STONEHILL P II | INSTALL 1400' 2" PE FOR 12 LOTS | 2207.78 | 8450 | -2708.16 | -32.05% | 0.04048% | 5741.84 | 8450 | -2708.16 | 2005-10-01 | 2006-09-30 | 2005-07-19 | 2005-07-19 | 2005-09-15 | 2005-09-15
| 040.12790 | 040.PAD.Highland Rd Ext III | Install 900' - 2" PE for four existing and one new residential customer | 2230.66 | 3012 | -939.36 | -31.19% | 0.01461% | 2072.64 | 3012 | -939.36 | 2005-10-01 | 2006-09-30 | 2005-10-11 | 2005-10-11 | 2006-09-22 | 2006-09-22
| 040.12338 | 040.CAM.LEB.HENDRICKSON DR | INSTALL 850' OF 4" PE AND FARM TAP STATION W/BYPASS | 2260 | 17150 | 4751.9 | 27.71% | 0.1544% | 21901.9 | 17150 | 4751.9 | 2005-10-01 | 2006-09-30 | 2004-09-01 | 2004-09-01 | 2005-01-01 | 2005-01-01
| 040.12433 | 040.BGR.CUMBERLAND TRC. | CUMBERLABD TRACE 6" PE TIE-IN - B.G. | 2287.36 | 127836 | -33782.22 | -26.43% | 0.663% | 94053.78 | 127836 | -33782.22 | 2005-10-01 | 2006-09-30 | 2004-12-14 | 2004-12-14 | 2005-04-04 | 2005-04-04
| 040.12650 | 040.BGR.GLS.BYPASS EXT | 1250 FT. OF 2" PE - BYPASS @ WALMART - GLASGOW | 2476.64 | 3109 | -632.36 | -20.34% | 0.01746% | 2476.64 | 3109 | -632.36 | 2005-10-01 | 2006-09-30 | 2005-07-29 | 2005-07-29 | 2005-09-28 | 2005-09-28
| 040.13040 | 040.OBO.E.24TH. & BOLIVAR | INSTALL 729' 2" PE RETIRE 3" & 4" STL. | 2578.77 | 29817.96 | -12757.38 | -42.78% | 0.1203% | 17060.58 | 29817.96 | -12757.38 | 2005-10-01 | 2006-09-30 | 2006-06-15 | 2006-06-15 | 2006-08-31 | 2006-08-31
| 040.12787 | 040.2739.DALE ESTATES | INSTALL 1800' OF 2" PE IN DALE ESTATES | 2739.4 | 6275 | -3535.6 | -56.34% | 0.01931% | 2739.4 | 6275 | -3535.6 | 2005-10-01 | 2006-09-30 | 2005-10-11 | 2005-10-11 | 2005-10-27 | 2005-10-27
| 040.12804 | 040.PAD.Burldeen Dr Main Ext | Install 100' - 2" PE for one existing customer wanting to convert heat from elec | 2761.59 | 1087.75 | 1546.48 | 142.2% | 0.01857% | 2634.23 | 1087.75 | 1546.48 | 2005-10-01 | 2006-09-30 | 2005-10-27 | 2005-10-27 | 2006-09-22 | 2006-09-22
| 040.12949 | 040.PTON.Rectifier Dawson | Replace damaged rectifier in Dawson Spring, KY rectifier was hit by auto. | 2834.86 | 6102.4 | -3267.54 | -53.55% | 0.01998% | 2834.86 | 6102.4 | -3267.54 | 2005-10-01 | 2006-09-30 | 2006-02-03 | 2006-02-03 | 2006-06-30 | 2006-06-30
| 040.13083 | 040.2739.TOWN AND COUNTRY XI | INSTALL 1500' OF 2" PE IN TOWN AND COUNTRY XI | 3177.66 | 10750 | -7170.43 | -66.7% | 0.02523% | 3579.57 | 10750 | -7170.43 | 2005-10-01 | 2006-09-30 | 2006-07-25 | 2006-07-25 | 2007-07-25 | 2007-07-25
| 040.13027 | 040.BGR.CHANDLER BLVD. 2"EXT | 1033 FT. OF 2" PE - CHANDLER BLVD. B.G. | 3185.61 | 1605 | 1594.48 | 99.34% | 0.02255% | 3199.48 | 1605 | 1594.48 | 2005-10-01 | 2006-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.13039 | 040.2618.OWBEXIT | REPAIR EXIT LIGHTS AT THE OWENSBORO OFFICE | 3187.27 | 3458.2 | -270.93 | -7.834% | 0.02247% | 3187.27 | 3458.2 | -270.93 | 2005-10-01 | 2006-09-30 | 2006-06-14 | 2006-06-14 | 2006-09-27 | 2006-09-27
| 040.12796 | 040.BGR.RUSS.STONEWALL III& iv | 2" PE EXT. - STONEWALL III & IV- RUSS. | 3264.73 | 10548 | -7283.27 | -69.05% | 0.02301% | 3264.73 | 10548 | -7283.27 | 2005-10-01 | 2006-09-30 | 2005-10-20 | 2005-10-20 | 2005-10-20 | 2005-10-20
| 040.12584 | 040.LEB.IND PARK-JOY MINING | INSTALL 1700' OF 4" PE TO SERVE JOY MINING AND TO RETIRE A FARM TAP REGULATOR | 3338.44 | 18950 | 1842.8 | 9.725% | 0.1466% | 20792.8 | 18950 | 1842.8 | 2005-10-01 | 2006-09-30 | 2005-05-11 | 2005-05-11 | 2005-07-15 | 2005-07-15
| 040.13013 | 040.BGR.CROSSINGS IV 2" EXT. | 1370 FT. OF 2" PE - CROSSINGS IV - B.G. | 3452.75 | 5172 | -1719.25 | -33.24% | 0.02434% | 3452.75 | 5172 | -1719.25 | 2005-10-01 | 2006-09-30 | 2006-04-03 | 2006-04-03 | 2006-09-28 | 2006-09-28
| 040.13046 | AKY.TCSVC.MEAS.EFM.FP INT. | INSTALLATION OF EFM @ FP INTERNATIONAL | 3494.67 | 5622.24 | -6655.57 | -118.4% | -0.007285% | -1033.33 | 5622.24 | -6655.57 | 2005-10-01 | 2006-09-30 | 2006-06-24 | 2006-06-24 | 2006-09-28 | 2006-09-28
| 040.12811 | 040.BGR.PARKER MILLER - B..G | 835 FT.OF 2" PE- DAHLIA WAY - PARKER MILLER - B.G. | 3543.36 | 5817 | -2273.64 | -39.09% | 0.02498% | 3543.36 | 5817 | -2273.64 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-09-28 | 2006-09-28
| 040.12808 | 040.BGR.GLS.GARET WAY | 625 FT. OF 2" PE - GARET WAY - GLASGOW | 3622.52 | 3716 | -93.48 | -2.516% | 0.02554% | 3622.52 | 3716 | -93.48 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-09-28 | 2006-09-28
| 040.12806 | 040.BGR.FRK.SAM WALTON DR. EXT | 1550 FT. OF 2" PE - SAMWALTON DR. - RUSS | 3759.1 | 662 | 3097.1 | 467.8% | 0.0265% | 3759.1 | 662 | 3097.1 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-09-28 | 2006-09-28
| 040.13056 | 040.PAD.Odorizer Awning | Awnings will cover odorizers to keep direct sunshine off odorizers | 3812.92 | 5622.32 | -773.3 | -13.75% | 0.03418% | 4849.02 | 5622.32 | -773.3 | 2005-10-01 | 2006-09-30 | 2006-06-29 | 2006-06-29 | 2006-09-22 | 2006-09-22
| 040.12841 | 040.PTON.Eagan St Replacement | Replace 325' - 2" bare pipe with 325' - 2" PE. we have two grade II leaks | 3897.01 | 4581.39 | -684.38 | -14.94% | 0.02747% | 3897.01 | 4581.39 | -684.38 | 2005-10-01 | 2006-09-30 | 2005-12-07 | 2005-12-07 | 2006-09-22 | 2006-09-22
| 040.13118 | 040.B.G.LEE'S SQUARE REPLC. | 345 FT. OF 4" REPLC. LEE'S SQUARE - B.G. | 3921.35 | Not Budgeted | - | - | 0.02816% | 3993.86 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-09-13 | 2006-09-13 | 2007-09-13 | 2007-09-13
| 040.13030 | 040.BGR.RUSS. THURSTON III | 1585 FT. OF 2" PE - THURSTON PROPERTIES - RUSS. | 3947.06 | 4721 | -612.36 | -12.97% | 0.02896% | 4108.64 | 4721 | -612.36 | 2005-10-01 | 2006-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.12714 | Jarrett Embry MEC Forfeiture | Jarrett Embry MEC Forfeiture | 4111 | Not Budgeted | - | - | 0% | 0 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-09-29 | 2005-09-29 | 2005-09-30 | 2005-09-30
| 040.12567 | 040.SHV.MIDLAND SEC 8 | INSTALL 750' OF 2" PE FOR 21 LOTS MIDLAND SEC 8 | 4237.16 | 5735 | 1874.95 | 32.69% | 0.05365% | 7609.95 | 5735 | 1874.95 | 2005-10-01 | 2006-09-30 | 2005-04-21 | 2005-04-21 | 2005-06-15 | 2005-06-15
| 040.13024 | 040.OBO.LEE RUDY RD. | INSTALL 750' 2" PE | 4319.11 | 6852.19 | -2533.08 | -36.97% | 0.03045% | 4319.11 | 6852.19 | -2533.08 | 2005-10-01 | 2006-09-30 | 2006-04-28 | 2006-04-28 | 2006-05-26 | 2006-05-26
| 040.12801 | 040.OBO.EAST BYERS AVE. | INSTALL 482' 2" PE | 4400.76 | 3416.45 | 984.31 | 28.81% | 0.03102% | 4400.76 | 3416.45 | 984.31 | 2005-10-01 | 2006-09-30 | 2005-10-25 | 2005-10-25 | 2005-11-04 | 2005-11-04
| 040.12789 | 040.OBO.GRAYSTONE/CAMDEN | INSTALL 782' 2" PE | 4450.86 | 4829.44 | -378.58 | -7.839% | 0.03138% | 4450.86 | 4829.44 | -378.58 | 2005-10-01 | 2006-09-30 | 2005-10-11 | 2005-10-11 | 2005-12-30 | 2005-12-30
| 040.12760 | 040.PAD.Cedar Ridge Rev Ext | 900' - 2" PE for 13 lots | 4476.32 | 4481.07 | -249.8 | -5.575% | 0.02983% | 4231.27 | 4481.07 | -249.8 | 2005-10-01 | 2006-09-30 | 2005-10-03 | 2005-10-03 | 2006-09-22 | 2006-09-22
| 040.13014 | 040.BGR.BAILEY'S FARM II-A | 1760 FT. OF 2" PE - BAILEY'S FARM II-A - B.G. | 4524.73 | 6846 | -2321.27 | -33.91% | 0.0319% | 4524.73 | 6846 | -2321.27 | 2005-10-01 | 2006-09-30 | 2006-04-03 | 2006-04-03 | 2006-09-28 | 2006-09-28
| 040.12921 | 040.PAD.Odorant Contoller | Odorant Injector Controller | 4557.01 | 4494.6 | 289.46 | 6.44% | 0.03373% | 4784.06 | 4494.6 | 289.46 | 2005-10-01 | 2006-09-30 | 2006-01-20 | 2006-01-20 | 2006-09-22 | 2006-09-22
| 040.12810 | 040.BGR.GLS.HARLOW TRAIL | 1210 FT. OF 2" PE HARLOW TRAIL - GLASGOW | 4707.11 | 4430 | 277.11 | 6.255% | 0.03318% | 4707.11 | 4430 | 277.11 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-09-28 | 2006-09-28
| 040.13066 | AKY.TCSVC.MEAS.EFM.TG AUTO | INSTALL EFM AT TG AUTOMOTIVE | 4900.63 | 6065 | -1164.37 | -19.2% | 0.03455% | 4900.63 | 6065 | -1164.37 | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-09-28 | 2006-09-28
| 040.13067 | TCHSRV.MEA.EFM MUHL HOSP | EFM FOR MUHLENBERG COM HOSPITAL | 4900.63 | 6276 | -1271.31 | -20.26% | 0.03528% | 5004.69 | 6276 | -1271.31 | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-09-28 | 2006-09-28
| 040.13068 | TCHSVC.MEA.EFM.JS STUART | EFM FOR JS STUART MED CENTER | 4900.63 | 6276 | -1271.31 | -20.26% | 0.03528% | 5004.69 | 6276 | -1271.31 | 2005-10-01 | 2006-09-30 | 2006-07-21 | 2006-07-21 | 2006-09-28 | 2006-09-28
| 040.12904 | 040.PAD.N Friendship Rd Ext | 250' reveneue extension for new church | 4993.66 | 896 | 4060.67 | 453.2% | 0.03494% | 4956.67 | 896 | 4060.67 | 2005-10-01 | 2006-09-30 | 2005-12-27 | 2005-12-27 | 2006-09-22 | 2006-09-22
| 040.13048 | 040.2739.DOGWOOD VILLAS | INSTALL 1100' OF 2" PE FOR 34 CONDOS DOGWOOD VILLAS | 5106.62 | 13900 | -2735.13 | -19.68% | 0.07871% | 11164.87 | 13900 | -2735.13 | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2007-06-27 | 2007-06-27
| 040.13057 | 040.STO Ultrasonic Equipment | Purchase of Ultrasonic Thickness Gauges | 5188.26 | 5500 | -311.74 | -5.668% | 0.03658% | 5188.26 | 5500 | -311.74 | 2005-10-01 | 2006-09-30 | 2006-07-05 | 2006-07-05 | 2006-09-27 | 2006-09-27
| 040.13031 | 040.PAD.Ballard Cr Rev Ext | Install 765' - 2" PE along Ballard Cr in Information Age Park for Marquette Tran | 5274.58 | 3979.45 | 1295.13 | 32.55% | 0.03718% | 5274.58 | 3979.45 | 1295.13 | 2005-10-01 | 2006-09-30 | 2006-05-22 | 2006-05-22 | 2006-09-22 | 2006-09-22
| 040.12952 | 040.BGR.MARIA & DETOUR EXT | 3240FT.OF 2" PE -MARIA & DETOUR - B.G. | 5355.87 | 7696 | -2340.13 | -30.41% | 0.03776% | 5355.87 | 7696 | -2340.13 | 2005-10-01 | 2006-09-30 | 2006-02-16 | 2006-02-16 | 2006-09-28 | 2006-09-28
| 040.13059 | 040.OBO.Locust St Replmnt | Install 170' 2" PE retire 4" Stl LP | 5439.37 | 9978.52 | -4539.15 | -45.49% | 0.03835% | 5439.37 | 9978.52 | -4539.15 | 2005-10-01 | 2006-09-30 | 2006-07-11 | 2006-07-11 | 2006-09-22 | 2006-09-22
| 040.13102 | 040.BGR.EAGLESTONE VILLAS | 2180 FT.OF 2" PE - EAGLESTONE VILLAS - B.G. | 5457.1 | 9900 | -4342.01 | -43.86% | 0.03918% | 5557.99 | 9900 | -4342.01 | 2005-10-01 | 2006-09-30 | 2006-08-16 | 2006-08-16 | 2006-12-29 | 2006-12-29
| 040.13096 | 040.MAY.Northside Subd Ext | Install 1,965' - 2" PE for 18 commercial lots. Developer is Nathan Sholar | 5742.27 | 8106.9 | 1440.55 | 17.77% | 0.06731% | 9547.45 | 8106.9 | 1440.55 | 2005-10-01 | 2006-09-30 | 2006-08-15 | 2006-08-15 | 2006-09-22 | 2006-09-22
| 040.12616 | AKY.TCSVS.MEAS.EFM.NESTAWAY | INSTALL EFM @ NESTAWAY | 5781.36 | 5521.24 | 6057.12 | 109.7% | 0.08162% | 11578.36 | 5521.24 | 6057.12 | 2005-10-01 | 2006-09-30 | 2005-06-21 | 2005-06-21 | 2005-09-28 | 2005-09-28
| 040.12825 | AKY.TCSVC.MEAS.EFM.WKU | Installation of EFM @ WKU Steamplant | 6066.64 | 5521.24 | 545.4 | 9.878% | 0.04277% | 6066.64 | 5521.24 | 545.4 | 2005-10-01 | 2006-09-30 | 2005-11-16 | 2005-11-16 | 2006-09-28 | 2006-09-28
| 040.12916 | 040.PTON.Varmint Trace Replace | Replace 50' - 3/4", 60' - 1 1/4", & 105' - 2" steel pipe with 215' - 2" PE | 6159.97 | 5105.42 | 1054.55 | 20.66% | 0.04343% | 6159.97 | 5105.42 | 1054.55 | 2005-10-01 | 2006-09-30 | 2006-01-11 | 2006-01-11 | 2006-09-22 | 2006-09-22
| 040.12818 | 040.BGR.PINE TERRACE 2" EXT. | 604 FT. OF 2" PE - PINE TERRACE - B.G. | 6177.76 | 3234 | 3363.79 | 104% | 0.04651% | 6597.79 | 3234 | 3363.79 | 2005-10-01 | 2006-09-30 | 2005-11-08 | 2005-11-08 | 2006-09-28 | 2006-09-28
| 040.12563 | 040.DAN.REGIONAL REG REPAIR-05 | REPLACE BOOTS AND REPAIR REGULATORS IN THE DANVILLE REGION | 6322.85 | 24400 | 19645.95 | 80.52% | 0.3105% | 44045.95 | 24400 | 19645.95 | 2005-10-01 | 2006-09-30 | 2004-05-14 | 2004-05-14 | 2005-09-28 | 2005-09-28
| 040.12971 | 040.2737.H17012 2" VALVE CHGR | H-17012 1-1/2" AND 2" NO-BLO VALVE CHANGER | 6431.57 | 6700 | -268.43 | -4.006% | 0.04534% | 6431.57 | 6700 | -268.43 | 2005-10-01 | 2006-09-30 | 2006-03-13 | 2006-03-13 | 2006-04-15 | 2006-04-15
| 040.12622 | 040.OBO.BOETLER RD. ODORIZER | INSTALL ODORIZER | 6567.83 | 40607.6 | -1680.61 | -4.139% | 0.2744% | 38926.99 | 40607.6 | -1680.61 | 2005-10-01 | 2006-09-30 | 2005-06-24 | 2005-06-24 | 2005-08-05 | 2005-08-05
| 040.12840 | 040.OBO.CROSS CREEK PHASE 4 | INSTALL 888' 2" PE | 6594.35 | 7271.11 | -676.76 | -9.308% | 0.04649% | 6594.35 | 7271.11 | -676.76 | 2005-10-01 | 2006-09-30 | 2005-12-05 | 2005-12-05 | 2006-02-27 | 2006-02-27
| 040.12909 | 040.BGR.CEMETERY RD. / IDLE | 730 FT. OF 4" PE CEMETERY RD. @ IDLE - B.G. | 6649.03 | 4894 | 1755.03 | 35.86% | 0.04687% | 6649.03 | 4894 | 1755.03 | 2005-10-01 | 2006-09-30 | 2005-12-29 | 2005-12-29 | 2006-09-28 | 2006-09-28
| 040.12390 | 040.DAN.FARM TAP - 150 BYPASS | INSTALL NEW REGULATOR STATION AT RAILROAD AND BYPASS FOR FIRESIDE DRIVE | 6696.82 | 15650 | -2688.16 | -17.18% | 0.09138% | 12961.84 | 15650 | -2688.16 | 2005-10-01 | 2006-09-30 | 2004-10-12 | 2004-10-12 | 2005-01-01 | 2005-01-01
| 040.12676 | 040.DAN.HUBLE RD-HILLTOPPER | INSTALL 500' OF 2" PE ACROSS HUBLE RD AT HILLTOPPER IN STANFORD FOR SYSTEM TIE-I | 6783.62 | 6950 | -166.38 | -2.394% | 0.04782% | 6783.62 | 6950 | -166.38 | 2005-10-01 | 2006-09-30 | 2005-09-19 | 2005-09-19 | 2005-10-01 | 2005-10-01
| 040.12638 | 040.CAM.GREENSBURG STATION | INSTALL REGULATOR STATION ON TUNNEL RAOD IN GREENSBURG | 6883.42 | 23425 | -5843.7 | -24.95% | 0.1239% | 17581.3 | 23425 | -5843.7 | 2005-10-01 | 2006-09-30 | 2005-07-11 | 2005-07-11 | 2005-08-01 | 2005-08-01
| 040.12915 | 040.OBO.LINCOLN RANGER 250 | PURCHASE LINCOLN RANGER 250 WELDER | 7057.68 | 6963 | 94.68 | 1.36% | 0.04975% | 7057.68 | 6963 | 94.68 | 2005-10-01 | 2006-09-30 | 2006-01-06 | 2006-01-06 | 2006-01-27 | 2006-01-27
| 040.12631 | 040.MAY.New Office Accessories | Office furniture and accessories for the new Mayfield, KY office | 7118.26 | 48124.48 | 31988.29 | 66.47% | 0.5648% | 80112.77 | 48124.48 | 31988.29 | 2005-10-01 | 2006-09-30 | 2005-07-06 | 2005-07-06 | 2005-09-23 | 2005-09-23
| 040.12807 | 040.BGR.FRK.COTTAGE GROVE | 3288 FT. OF 2" PE - COTTAGE GROVE - FRK. | 7129.46 | 10662 | -3532.54 | -33.13% | 0.05026% | 7129.46 | 10662 | -3532.54 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-09-28 | 2006-09-28
| 040.13018 | 040.OBO.GLENCREST DR. | INSTALL1,260' 2" PE | 7533.13 | 7204.05 | 329.08 | 4.568% | 0.05311% | 7533.13 | 7204.05 | 329.08 | 2005-10-01 | 2006-09-30 | 2006-04-12 | 2006-04-12 | 2006-05-12 | 2006-05-12
| 040.13020 | 040.PAD.Olivet Ch Relocate IV | City adding turn lane at Sanders Blvd/ Install 670' - 2" PE | 7666.81 | 518.55 | 1148.26 | 221.4% | 0.01175% | 1666.81 | 518.55 | 1148.26 | 2005-10-01 | 2006-09-30 | 2006-04-20 | 2006-04-20 | 2006-09-22 | 2006-09-22
| 040.12632 | 040.BGR.IVAN DOWNS PHSE.I | 7420 FT. OF 2" PE - IVAN DOWNS PHASE I - B.G. | 7936.14 | 27384 | 1136.66 | 4.151% | 0.2011% | 28520.66 | 27384 | 1136.66 | 2005-10-01 | 2006-09-30 | 2005-07-08 | 2005-07-08 | 2005-09-28 | 2005-09-28
| 040.13009 | 040.OBO.HARDINSBURG ODORIZOR | REPLACE AGING HARDINSBURG TB 1 ODORIZOR | 7982.07 | 9954.98 | -1972.91 | -19.82% | 0.05627% | 7982.07 | 9954.98 | -1972.91 | 2005-10-01 | 2006-09-30 | 2006-03-27 | 2006-03-27 | 2006-04-28 | 2006-04-28
| 040.12639 | 040.CAM.HWY 527-BYPASS | INSTALL 1500' OF 2" FROM HWY 527 TO C-VILLE BYPASS | 8063.09 | 7300 | -1236.91 | -16.94% | 0.04274% | 6063.09 | 7300 | -1236.91 | 2005-10-01 | 2006-09-30 | 2005-07-11 | 2005-07-11 | 2005-08-01 | 2005-08-01
| 040.13109 | 040.MAD.Kenny Brasher Ret. | Retire Bare Unprotected main | 8115.74 | 11802.96 | -3687.22 | -31.24% | 0.05721% | 8115.74 | 11802.96 | -3687.22 | 2005-10-01 | 2006-09-30 | 2006-08-28 | 2006-08-28 | 2006-09-22 | 2006-09-22
| 040.13122 | 040.BGR.HOPK.OFFICE FUR. | OFFICE FURNITURE - VINDA PARKER - HOPKINSVILLE | 8146.25 | 9366.83 | -1129.34 | -12.06% | 0.05807% | 8237.49 | 9366.83 | -1129.34 | 2005-10-01 | 2006-09-30 | 2006-09-22 | 2006-09-22 | 2007-09-22 | 2007-09-22
| 040.13047 | AKY.TCSVC.MEAS.EFM.CCB CO. | INSTALLATION OF EFM @ CLOVER CREEK BRICK CO. | 8243.09 | 5622.24 | 2620.85 | 46.62% | 0.05811% | 8243.09 | 5622.24 | 2620.85 | 2005-10-01 | 2006-09-30 | 2006-06-24 | 2006-06-24 | 2006-09-28 | 2006-09-28
| 040.12827 | AKY.TCSVC.MEAS.EFM.ABSKY | Installation of EFM @ ABSKY | 8295.47 | 5521.24 | 2774.23 | 50.25% | 0.05848% | 8295.47 | 5521.24 | 2774.23 | 2005-10-01 | 2006-09-30 | 2005-11-16 | 2005-11-16 | 2006-09-28 | 2006-09-28
| 040.13106 | 040.BGR. EAST 13TH REPLC. | 622 FT. ODF 2" PE - E. 13TH ST. - B.G. | 8556.3 | 24976 | -16419.7 | -65.74% | 0.06032% | 8556.3 | 24976 | -16419.7 | 2005-10-01 | 2006-09-30 | 2006-08-21 | 2006-08-21 | 2006-12-29 | 2006-12-29
| 040.12820 | 040.BGR.PARK HILL V - B | 2039 FT. OF 2" PE - PARK HILL V - B.G. | 8565 | 9547 | -824 | -8.631% | 0.06149% | 8723 | 9547 | -824 | 2005-10-01 | 2006-09-30 | 2005-11-08 | 2005-11-08 | 2006-09-28 | 2006-09-28
| 040.12920 | 040.STO Squire Rd Xing Repl. | Line No. 90-159-00 Nortonville/Fruithill 10" Road Crossing Replacement | 8680.96 | 230378 | -160639.18 | -69.73% | 0.4916% | 69738.82 | 230378 | -160639.18 | 2005-10-01 | 2006-09-30 | 2006-01-19 | 2006-01-19 | 2006-09-28 | 2006-09-28
| 040.12907 | 040.BGR.FRK.WILLIAMSBURG I | 1910 FT. OF 2" PE - WILLIAMSBURG PARK I - FRANKLIN | 8688.5 | 7812 | 876.5 | 11.22% | 0.06125% | 8688.5 | 7812 | 876.5 | 2005-10-01 | 2006-09-30 | 2005-12-29 | 2005-12-29 | 2005-09-28 | 2005-09-28
| 040.13010 | Aky.Tcsv.EFM.Kenway | Install EFM @ Kenway Pavers, LLC | 8805.35 | 5741.25 | 3064.1 | 53.37% | 0.06207% | 8805.35 | 5741.25 | 3064.1 | 2005-10-01 | 2006-09-30 | 2006-03-28 | 2006-03-28 | 2006-09-28 | 2006-09-28
| 040.12678 | 040.DAN.OFFICE FURNITURE | FURNITURE FOR OPERATION SUPERVISOR | 8968.69 | 9910 | 1739.77 | 17.56% | 0.08213% | 11649.77 | 9910 | 1739.77 | 2005-10-01 | 2006-09-30 | 2005-09-22 | 2005-09-22 | 2005-10-01 | 2005-10-01
| 040.13089 | 040.BGR.NORTHRIDGE IV-A | 2503 FT. OF 2" PE - NORTHRIDGE IV-A -- B.G. | 9164.85 | 8734.11 | 545.74 | 6.248% | 0.06542% | 9279.85 | 8734.11 | 545.74 | 2005-10-01 | 2006-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 040.13062 | 040.MAY.Commonwealth Rev Ext | Commonwealth Dr Rev Ext for new Lowes store in Mayfield | 9340.26 | 13117.28 | 2714.83 | 20.7% | 0.1116% | 15832.11 | 13117.28 | 2714.83 | 2005-10-01 | 2006-09-30 | 2006-07-18 | 2006-07-18 | 2006-09-22 | 2006-09-22
| 040.13085 | 040.OBO. Lake Forrest Drive | Install 1,391' 2" PE | 9554.59 | 12592.23 | -2872.63 | -22.81% | 0.06852% | 9719.6 | 12592.23 | -2872.63 | 2005-10-01 | 2006-09-30 | 2006-08-02 | 2006-08-02 | 2006-08-31 | 2006-08-31
| 040.12635 | 040.OBO.21ST. & ALLEN REPLMNT. | INSTALL 2,425' 2" PE & 1,100' 4" PE | 9582.75 | 81799.99 | 34811.53 | 42.56% | 0.8221% | 116611.52 | 81799.99 | 34811.53 | 2005-10-01 | 2006-09-30 | 2005-07-08 | 2005-07-08 | 2006-04-07 | 2006-04-07
| 040.12824 | AKY.TCSVS.MEAS.EFM.COPAR | EFM Installation @ Copar | 9747.55 | 5521.24 | 4226.31 | 76.55% | 0.06872% | 9747.55 | 5521.24 | 4226.31 | 2005-10-01 | 2006-09-30 | 2005-11-16 | 2005-11-16 | 2006-09-28 | 2006-09-28
| 040.12356 | Bowling Green 05 Growth Func | Bowling Green 05 Growth Func | 9780.31 | Not Budgeted | - | - | 9.722% | 1379155.52 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-04-18 | 2005-04-18 | 2005-04-18 | 2005-04-18
| 040.13044 | 040.BGR.14TH ST. RELOCATION | 14TH ST. RELOCATION FROM COLLEGE TO KENTUCKY - B.G. | 9905.66 | Not Budgeted | - | - | 0.07791% | 11051.06 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-20 | 2006-06-20 | 2006-09-28 | 2006-09-28
| 040.13103 | 040.OBO.Fiddlesticks Phase 1 | Install 3,075' 2" PE | 10124.99 | 25068.65 | -5444.95 | -21.72% | 0.1383% | 19623.7 | 25068.65 | -5444.95 | 2005-10-01 | 2006-09-30 | 2006-08-17 | 2006-08-17 | 2006-09-22 | 2006-09-22
| 040.12833 | 040.BGR.RIVERBEND III - B.G. | 1860 FT.OF 2" PE - RIVERBEND III - B.G. | 10141.06 | 7273 | 2868.06 | 39.43% | 0.07149% | 10141.06 | 7273 | 2868.06 | 2005-10-01 | 2006-09-30 | 2005-11-30 | 2005-11-30 | 2006-09-28 | 2006-09-28
| 040.12839 | 040.OBO.THE BROOKS PHASE 3 | INSTALL 1,146' 2" PE | 10384.06 | 7895.86 | 2488.2 | 31.51% | 0.0732% | 10384.06 | 7895.86 | 2488.2 | 2005-10-01 | 2006-09-30 | 2005-12-05 | 2005-12-05 | 2006-02-22 | 2006-02-22
| 040.13092 | 040.BGR.800 BLK. WAKEFIELD | 310 FT. OF 4"PE -800 BLK WAKEFIELD REPLC - B.G. | 10588.09 | 13496.31 | -2376.87 | -17.61% | 0.07839% | 11119.44 | 13496.31 | -2376.87 | 2005-10-01 | 2006-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 040.12819 | 040.SPRINGFIELD V & VI - B.G. | 3410 FT. OF 2" PE - SPRINGFIELD V & VI - B.G. | 10645.21 | 11279 | -633.79 | -5.619% | 0.07504% | 10645.21 | 11279 | -633.79 | 2005-10-01 | 2006-09-30 | 2005-11-08 | 2005-11-08 | 2006-09-28 | 2006-09-28
| 040.12912 | AKY.TCSVC.MEAS.ALCAN REGS | REGULATORS FOR INSTALLATION @ ALCAN | 10647.21 | 20079 | -9431.79 | -46.97% | 0.07506% | 10647.21 | 20079 | -9431.79 | 2005-10-01 | 2006-09-30 | 2006-01-05 | 2006-01-05 | 2006-09-28 | 2006-09-28
| 040.12795 | 040.BGR.CUMBERLAND RIDGE | 2" PE EXT. - CUMBERLAND RIDGE - B.G. | 10658.04 | 10738 | -79.96 | -0.7446% | 0.07513% | 10658.04 | 10738 | -79.96 | 2005-10-01 | 2006-09-30 | 2005-10-19 | 2005-10-19 | 2006-09-28 | 2006-09-28
| 040.12534 | 040.DAN.CORNISHVILLE BRDG RELO | RELOCATE 610' OF 2" PE ON CORNISHVILLE ROAD AT THE BRIDGE | 10692.44 | 214.5 | 19658.82 | 9165% | 0.1401% | 19873.32 | 214.5 | 19658.82 | 2005-10-01 | 2006-09-30 | 2005-03-01 | 2005-03-01 | 2005-08-01 | 2005-08-01
| 040.13037 | AKY.TCSSVC.MEAS.RTU | Fisher ROC 312 and EFM/RTU equipment | 10940.81 | 14625 | -3684.19 | -25.19% | 0.07713% | 10940.81 | 14625 | -3684.19 | 2005-10-01 | 2006-09-30 | 2006-06-05 | 2006-06-05 | 2006-09-28 | 2006-09-28
| 040.12565 | 040.SHV.CLOVERBROOK PH II | INSTALL 2500' 2" PE IN CLOOVERBROOK | 11361.75 | 18175 | -216.43 | -1.191% | 0.1266% | 17958.57 | 18175 | -216.43 | 2005-10-01 | 2006-09-30 | 2004-05-14 | 2004-05-14 | 2005-06-15 | 2005-06-15
| 040.13063 | 040.PAD.Brookhaven II | Brookhaven subd. phase II 3,005' for 26 new residential lots | 11695.61 | 12480 | 409.18 | 3.279% | 0.09086% | 12889.18 | 12480 | 409.18 | 2005-10-01 | 2006-09-30 | 2006-07-18 | 2006-07-18 | 2006-09-22 | 2006-09-22
| 040.12911 | 040.2739.OSPREY COVE VI DUPLEX | INSTALL 2300' OF 2" PE IN OSPREY COVE DUPLEXES | 11715.5 | 12300 | -584.5 | -4.752% | 0.08259% | 11715.5 | 12300 | -584.5 | 2005-10-01 | 2006-09-30 | 2006-01-04 | 2006-01-04 | 2006-02-15 | 2006-02-15
| 040.12803 | 040.NGR.HOP.PENNYRILE RELOC. | 200' OF 4" PE RELOC. - PENNYRILE PKWY. - HOPK. | 12137.17 | 14307 | -2169.83 | -15.17% | 0.08556% | 12137.17 | 14307 | -2169.83 | 2005-10-01 | 2006-09-30 | 2005-10-26 | 2005-10-26 | 2006-09-28 | 2006-09-28
| 040.13049 | 040.2739.KNOBVIEW | INSTALL 1500' OF 2" PE AND 3 LS SERVICES ON KNOB STREET AND BYERS CT | 12725.11 | 14100 | -965.45 | -6.847% | 0.09259% | 13134.55 | 14100 | -965.45 | 2005-10-01 | 2006-09-30 | 2006-06-27 | 2006-06-27 | 2007-06-27 | 2007-06-27
| 040.12965 | 040.2738.SY IMP-FARM TAP R-LEB | RETIRE 3 FARM TAPS ON THE SOUTH OF LEBANON-INSTALL 1600' 2" PE | 13348.61 | 23750 | -10401.39 | -43.8% | 0.0941% | 13348.61 | 23750 | -10401.39 | 2005-10-01 | 2006-09-30 | 2006-03-06 | 2006-03-06 | 2006-05-10 | 2006-05-10
| 040.12662 | 040.SHV.CARD CLUB-LINKS | INSTALL 2" PE ON LINKS DR IN CARDINAL CLUB | 14084.44 | 15950 | -1865.56 | -11.7% | 0.09929% | 14084.44 | 15950 | -1865.56 | 2005-10-01 | 2006-09-30 | 2005-08-19 | 2005-08-19 | 2005-10-01 | 2005-10-01
| 040.13090 | 040.BGR.NORTHRIDGEIV-B | 4095 FT.OF 2" PE - NORTHRIDGEIV-B -- B.G. | 14198.17 | 16037.5 | -1498.07 | -9.341% | 0.1025% | 14539.43 | 16037.5 | -1498.07 | 2005-10-01 | 2006-09-30 | 2006-08-09 | 2006-08-09 | 2006-09-28 | 2006-09-28
| 040.12910 | 040.BGR.CEMETERY RD @ FOUNTAIN | 1100 FT.OF 4" PE - CEMETERY RD. @ FOUNTAIN TRACE - B.G. | 14406.27 | 11939 | 3268 | 27.37% | 0.1072% | 15207 | 11939 | 3268 | 2005-10-01 | 2006-09-30 | 2005-12-29 | 2005-12-29 | 2006-09-28 | 2006-09-28
| 040.12617 | 040.LAW.ORIELLYS-HWY 44 | INSTALL 1000' OF 4" PE ON HWY 44 FOR O'RIELLYS AUTO PARTS | 14517.9 | 18585 | -3838.22 | -20.65% | 0.104% | 14746.78 | 18585 | -3838.22 | 2005-10-01 | 2006-09-30 | 2005-06-21 | 2005-06-21 | 2005-08-01 | 2005-08-01
| 040.13029 | 040.BGR. HUNTERS CROSSING IV-B | 2565 FT. OF 2" PE - HUNTERS CROSSING IV-B - B.G. | 14519.77 | 10213 | 4306.77 | 42.17% | 0.1024% | 14519.77 | 10213 | 4306.77 | 2005-10-01 | 2006-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.13036 | 040.PAD.Jim Smith Meter Set | Costs to cover new mtr set for Jim Smith new asphalt plant | 15213.72 | Not Budgeted | - | - | 0.06321% | 8965.99 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2006-06-01 | 2006-06-01 | 2006-09-22 | 2006-09-22
| 040.13107 | 040.OBO.Recorders | Purchase 6 Electronic Recoerders | 15503.21 | 13871.88 | 1717.96 | 12.38% | 0.1099% | 15589.84 | 13871.88 | 1717.96 | 2005-10-01 | 2006-09-30 | 2006-08-22 | 2006-08-22 | 2006-09-27 | 2006-09-27
| 040.12932 | 040.MAY.Fence Mayfield | Cost of wooden fence at new Mayfield office, was an add-on to the contract | 16098.51 | 15878.02 | 220.49 | 1.389% | 0.1135% | 16098.51 | 15878.02 | 220.49 | 2005-10-01 | 2006-09-30 | 2006-01-31 | 2006-01-31 | 2006-09-22 | 2006-09-22
| 040.12834 | 040.PTON.Meter Purchase 2006 | the purchase of class 1 through 4 meters for Princeton for FY '06 | 16161.02 | 29253.66 | -13054.68 | -44.63% | 0.1142% | 16198.98 | 29253.66 | -13054.68 | 2005-10-01 | 2006-09-30 | 2005-11-30 | 2005-11-30 | 2006-09-22 | 2006-09-22
| 040.13021 | 040.2737.RECTIFIER POLE REPLAC | REPLACE RECTIFIER POLES AT BURGIN,JC,STANFORD | 16169.57 | 16450 | -280.43 | -1.705% | 0.114% | 16169.57 | 16450 | -280.43 | 2005-10-01 | 2006-09-30 | 2006-04-21 | 2006-04-21 | 2006-06-01 | 2006-06-01
| 040.13019 | 040.PAD.N Friendship Relocate | D.O.T project to relocate 2" pe and two services along north friendship rd | 16317.22 | 4513.37 | 11803.85 | 261.5% | 0.115% | 16317.22 | 4513.37 | 11803.85 | 2005-10-01 | 2006-09-30 | 2006-04-17 | 2006-04-17 | 2006-09-22 | 2006-09-22
| 040.13028 | 040.BGR.THE SUMMIT 2" PE EXT | 2" PE EXTENSION - THE SUMMIT PHASE I - B.G. | 16951.67 | 19169 | -2189.61 | -11.42% | 0.1197% | 16979.39 | 19169 | -2189.61 | 2005-10-01 | 2006-09-30 | 2006-05-18 | 2006-05-18 | 2006-09-28 | 2006-09-28
| 040.13015 | 040.MAD.HWY 62 REPLACEMENT | REPLACE 550' 2" STL. WITH 2" PE | 17374.13 | 23603.66 | -6229.53 | -26.39% | 0.1225% | 17374.13 | 23603.66 | -6229.53 | 2005-10-01 | 2006-09-30 | 2006-04-06 | 2006-04-06 | 2006-07-31 | 2006-07-31
| 040.13038 | 040.2739.NOTTING HILLS 1b | INSTALL 1700' OF 2" AND 4" PE FOR 10 SERVICES = 40 MTR SETS | 17579.03 | 22800 | 18300.73 | 80.27% | 0.2897% | 41100.73 | 22800 | 18300.73 | 2005-10-01 | 2006-09-30 | 2006-06-12 | 2006-06-12 | 2007-07-07 | 2007-07-07
| 040.12659 | 040.SHV.LOWES HWY 55 | INSTALL 900' OF 2" PE ON HWY 55 FOR LOWES | 17972.38 | 2700 | 4527.35 | 167.7% | 0.05095% | 7227.35 | 2700 | 4527.35 | 2005-10-01 | 2006-09-30 | 2005-08-15 | 2005-08-15 | 2005-09-01 | 2005-09-01
| 040.12913 | AKY.TCSVS.MEAS.METERS | PURCHASE OF SPECIAL LARGE ROTARY METERS | 18680.8 | 19689 | -868.84 | -4.413% | 0.1327% | 18820.16 | 19689 | -868.84 | 2005-10-01 | 2006-09-30 | 2006-01-05 | 2006-01-05 | 2006-09-28 | 2006-09-28
| 040.12643 | 040.BGR.MCCOY PL. 2" EXT | 6970 FT. OF 2" PE - MCCOY PL EXT. - B.G. | 18757.52 | 24336 | -5578.48 | -22.92% | 0.1322% | 18757.52 | 24336 | -5578.48 | 2005-10-01 | 2006-09-30 | 2005-07-12 | 2005-07-12 | 2005-09-28 | 2005-09-28
| 040.12842 | AKY.TCSVC.MEAS.ROTARY METERS | PURCHASE OF DRESSER METERS | 19105.61 | 24188 | 563.02 | 2.328% | 0.1745% | 24751.02 | 24188 | 563.02 | 2005-10-01 | 2006-09-30 | 2005-12-09 | 2005-12-09 | 2006-09-28 | 2006-09-28
| 040.13120 | 040.BGR.MCLELLAN FARMS | 2520 FT-2' & 1959' - 4" - MSLELLEN FARMS - B.G. | 19956.96 | 30749.84 | -7133.25 | -23.2% | 0.1665% | 23616.59 | 30749.84 | -7133.25 | 2005-10-01 | 2006-09-30 | 2006-09-13 | 2006-09-13 | 2007-09-13 | 2007-09-13
| 040.12900 | 040.PAD.Peppers' Mill II | Install 3,075' - 2" PE into phase II of Peppers' Mill Subdivision | 20594.78 | 14704.61 | 5890.17 | 40.06% | 0.1452% | 20594.78 | 14704.61 | 5890.17 | 2005-10-01 | 2006-09-30 | 2005-12-16 | 2005-12-16 | 2006-04-14 | 2006-04-14
| 040.12835 | 040.MAY.'06 Meter Purchase | costs to purchase class 1 through class 4 meters for Mayfield | 21722.86 | 58641.76 | -36517.25 | -62.27% | 0.156% | 22124.51 | 58641.76 | -36517.25 | 2005-10-01 | 2006-09-30 | 2005-12-01 | 2005-12-01 | 2006-09-22 | 2006-09-22
| 040.12914 | AKY.TCSVS.MEAS.CALIBRATORS | PURCHASE OF CRYSTAL CALIBRATORS | 24019.02 | 18528 | 5491.02 | 29.64% | 0.1693% | 24019.02 | 18528 | 5491.02 | 2005-10-01 | 2006-09-30 | 2006-01-05 | 2006-01-05 | 2006-09-28 | 2006-09-28
| 040.12791 | 040.OBO. HWY 54& MILLERS MILL | INSTALL 720' 4" PE, RETIRE 2" STL. | 24372.76 | 22549.8 | 1822.96 | 8.084% | 0.1718% | 24372.76 | 22549.8 | 1822.96 | 2005-10-01 | 2006-09-30 | 2005-10-11 | 2005-10-11 | 2005-12-30 | 2005-12-30
| 040.12984 | 040.OBO.W.12TH.&CEDAR REPLMNT. | INSTALL 855' 2" PE | 24804.62 | 42687.8 | -17883.18 | -41.89% | 0.1749% | 24804.62 | 42687.8 | -17883.18 | 2005-10-01 | 2006-09-30 | 2006-03-16 | 2006-03-16 | 2006-06-30 | 2006-06-30
| 040.12987 | 040.PTON.E Main St Replace | Install 540' - 2" PE along E Main St Retire 450' - 4" & 78' - 2" Bare | 25216.94 | 23087.49 | 2129.45 | 9.223% | 0.1778% | 25216.94 | 23087.49 | 2129.45 | 2005-10-01 | 2006-09-30 | 2006-03-22 | 2006-03-22 | 2006-09-22 | 2006-09-22
| 040.12918 | 040.2739.LAW.WALMART | INSTALL 2200' OF 4" PE FOR WALMART OUTPARCELS | 25651.99 | 8860 | 16791.99 | 189.5% | 0.1808% | 25651.99 | 8860 | 16791.99 | 2005-10-01 | 2006-09-30 | 2006-01-17 | 2006-01-17 | 2006-02-15 | 2006-02-15
| 040.13119 | 040.B.G.WOODBURN PUR REPLC. | REPLACE WOODBURN PURCHASE REG. STATION | 25936.05 | 62391 | 10616.5 | 17.02% | 0.5147% | 73007.5 | 62391 | 10616.5 | 2005-10-01 | 2006-09-30 | 2006-09-13 | 2006-09-13 | 2007-09-13 | 2007-09-13
| 040.13084 | 040.STO Marker Posts | Installation of additional R-O-W markers | 26048.4 | 29766 | -2030.64 | -6.822% | 0.1955% | 27735.36 | 29766 | -2030.64 | 2005-10-01 | 2006-09-30 | 2006-07-27 | 2006-07-27 | 2006-09-28 | 2006-09-28
| 040.12575 | 040.SHV.FARM TAP REBUILD 1 | REBUILD 6 FARM TAPS USING REGULATORS AND SERVICES | 26383.37 | 16450 | 58193.63 | 353.8% | 0.5262% | 74643.63 | 16450 | 58193.63 | 2005-10-01 | 2006-09-30 | 2005-04-29 | 2005-04-29 | 2005-07-01 | 2005-07-01
| 040.12798 | 040.PAD.Cimerron Cove Ext | Install 6,300' - 2" PE in Cimerron Cove Subd. for Jeff James | 26897.72 | 25281.08 | 1616.64 | 6.395% | 0.1896% | 26897.72 | 25281.08 | 1616.64 | 2005-10-01 | 2006-09-30 | 2005-10-21 | 2005-10-21 | 2006-09-22 | 2006-09-22
| 040.12786 | 040.PTON.Ind Park #3 Rev Ext | Install 3,300' - 4" PE into Cadiz Industrial Park #3 for Benson International | 27503.6 | 38180 | -10676.4 | -27.96% | 0.1939% | 27503.6 | 38180 | -10676.4 | 2005-10-01 | 2006-09-30 | 2005-10-04 | 2005-10-04 | 2006-09-22 | 2006-09-22
| 040.12930 | 040.DAN.CAM.PIPE TRAILERS | 2-PIPE TRAILERS FOR DANVILLE AND CAMPBELLSVILLE | 27567.73 | 24000 | 3567.73 | 14.87% | 0.1943% | 27567.73 | 24000 | 3567.73 | 2005-10-01 | 2006-09-30 | 2006-01-27 | 2006-01-27 | 2006-03-15 | 2006-03-15
| 040.12902 | 040.STO Office Furniture | Purchase of Conference Room Furniture | 28274.62 | 27500 | 774.62 | 2.817% | 0.1993% | 28274.62 | 27500 | 774.62 | 2005-10-01 | 2006-09-30 | 2005-12-21 | 2005-12-21 | 2006-09-28 | 2006-09-28
| 040.13041 | 040.MAD.Henderson Reg.Relocte | Move Finley Reg. Sta. due to HWY Project | 29030.88 | 70647.63 | -27040.7 | -38.28% | 0.3074% | 43606.93 | 70647.63 | -27040.7 | 2005-10-01 | 2006-09-30 | 2006-06-16 | 2006-06-16 | 2006-09-08 | 2006-09-08
| 040.12951 | 040.2739.HI POINT IND PARK | INSTALL 5200' OF 4" PE AND SERVICES FOR HI POINT INDUSTRIAL PARK | 29546.99 | 42350 | -12803.01 | -30.23% | 0.2083% | 29546.99 | 42350 | -12803.01 | 2005-10-01 | 2006-09-30 | 2006-02-10 | 2006-02-10 | 2006-04-15 | 2006-04-15
| 040.12903 | 040.STO PC Replacements | Purchase Computers for Company Replacements | 29800.02 | 44000 | -14199.98 | -32.27% | 0.2101% | 29800.02 | 44000 | -14199.98 | 2005-10-01 | 2006-09-30 | 2005-12-21 | 2005-12-21 | 2006-09-28 | 2006-09-28
| 040.12919 | 040.STO Hwy 800 Xing Repl. | Line No. 90-159-00 Nortonville/Fruithill 10" Replace Highway 800 Road Crossing | 30258.32 | 230378 | 1131517.55 | 491.2% | 9.601% | 1361895.55 | 230378 | 1131517.55 | 2005-10-01 | 2006-09-30 | 2006-01-19 | 2006-01-19 | 2006-09-28 | 2006-09-28
| 040.12927 | 040.MAD.ARCH ST. REPLACEMENT | REPLACE 635' 4" STL. WITH 4" PE. | 31403.17 | 28135.29 | 3267.88 | 11.61% | 0.2214% | 31403.17 | 28135.29 | 3267.88 | 2005-10-01 | 2006-09-30 | 2006-01-27 | 2006-01-27 | 2006-02-28 | 2006-02-28
| 040.12815 | 040.2739.RESERVE BENSON CRK I | INSTALL 2" PE IN THE RESERVE AT BENSON CREEK PHASE I | 31877.2 | 36800 | -4922.8 | -13.38% | 0.2247% | 31877.2 | 36800 | -4922.8 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-02-01 | 2006-02-01
| 040.12776 | Princeton 06 Growth | Princeton 06 Growth | 34682.61 | Not Budgeted | - | - | 0.2449% | 34738.06 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.13023 | Aky.Tcsvc.Meas.Jim Smith | Regulators for Jim Smith Contracting | 35816.23 | 24401 | 11415.23 | 46.78% | 0.2525% | 35816.23 | 24401 | 11415.23 | 2005-10-01 | 2006-09-30 | 2006-04-26 | 2006-04-26 | 2006-09-28 | 2006-09-28
| 040.12823 | AKY.TCSVC.MEAS.ENGINEERED REGS | OUTSOURCER METER TESTING AND REPAIR | 36547.5 | 34957 | 1590.5 | 4.55% | 0.2576% | 36547.5 | 34957 | 1590.5 | 2005-10-01 | 2006-09-30 | 2005-11-15 | 2005-11-15 | 2006-09-28 | 2006-09-28
| 040.12954 | 040.PAD.Warehouse Improvements | Paint and install carpet at Paducah warehouse | 38842.81 | 17228.61 | 21614.2 | 125.5% | 0.2738% | 38842.81 | 17228.61 | 21614.2 | 2005-10-01 | 2006-09-30 | 2006-02-22 | 2006-02-22 | 2006-09-22 | 2006-09-22
| 040.13108 | 040.BGR.HWY31-W RELOC.B.G. | 6" HP RELOC. - HYW 31-W - B.G. PIPE ONLY | 41878.44 | 32796.04 | 9856.71 | 30.05% | 0.3007% | 42652.75 | 32796.04 | 9856.71 | 2005-10-01 | 2006-09-30 | 2006-08-25 | 2006-08-25 | 2006-12-29 | 2006-12-29
| 040.12610 | 040.BGR.6TH ST BYPASS - B | PARTR B - 6TH ST. BYPASS RELOC - B.G. | 42302.22 | 98122 | 8905.23 | 9.076% | 0.7545% | 107027.23 | 98122 | 8905.23 | 2005-10-01 | 2006-09-30 | 2005-06-17 | 2005-06-17 | 2005-09-28 | 2005-09-28
| 040.12611 | 040.BGR.6TH ST. BYPASS- C | PART C - 6TH ST. BYPASS - B.G. | 43587.92 | 58740 | 4777.88 | 8.134% | 0.4478% | 63517.88 | 58740 | 4777.88 | 2005-10-01 | 2006-09-30 | 2005-06-17 | 2005-06-17 | 2005-09-28 | 2005-09-28
| 040.12988 | 040.2618.AED2006 | Owensboro: Purchase of 15 AED Units for Cost Center 2618 | 44140.92 | 46314 | -2173.08 | -4.692% | 0.3112% | 44140.92 | 46314 | -2173.08 | 2005-10-01 | 2006-09-30 | 2006-03-23 | 2006-03-23 | 2006-09-28 | 2006-09-28
| 040.12826 | 040.Sto Madisonville Tornado | Labor and material for Madisonville tornado | 45790.66 | 40557 | 5233.66 | 12.9% | 0.3228% | 45790.66 | 40557 | 5233.66 | 2005-10-01 | 2006-09-30 | 2005-11-16 | 2005-11-16 | 2006-09-28 | 2006-09-28
| 040.12929 | 040.MAD.2" MUELLER EQ. | PURCHASE 2" MUELLER EQUIPMENT | 46546.6 | 44000 | 2625.4 | 5.967% | 0.3287% | 46625.4 | 44000 | 2625.4 | 2005-10-01 | 2006-09-30 | 2006-01-27 | 2006-01-27 | 2006-02-24 | 2006-02-24
| 040.12831 | 040.MAD.2006 METER PROJECT | 2006 METER PURCHASE PROJECT FOR MADISONVILLE | 47113.15 | 59323.52 | -12099.72 | -20.4% | 0.3329% | 47223.8 | 59323.52 | -12099.72 | 2005-10-01 | 2006-09-30 | 2005-11-22 | 2005-11-22 | 2006-09-28 | 2006-09-28
| 040.12608 | 040.BGR.6TH ST BYPASS - A | 950 FT.OF 6" PE - 6TH ST RELOC. PART A - B.G. | 47684.15 | 118009 | 11841.26 | 10.03% | 0.9154% | 129850.26 | 118009 | 11841.26 | 2005-10-01 | 2006-09-30 | 2005-06-15 | 2005-06-15 | 2005-09-28 | 2005-09-28
| 040.13026 | 040.2739.BRIDLEWOOD SEC I | INSTALL 2800' OF 2" PE AND REG STATION | 48480.79 | 37255 | 13211.02 | 35.46% | 0.3558% | 50466.02 | 37255 | 13211.02 | 2005-10-01 | 2006-09-30 | 2006-05-10 | 2006-05-10 | 2006-09-28 | 2006-09-28
| 040.12983 | 040.BGR.1100 BLK PARK REPLC | 1100 BLK. PARK ST. REPLC.- B.G. | 53693.59 | 48226 | 5467.59 | 11.34% | 0.3785% | 53693.59 | 48226 | 5467.59 | 2005-10-01 | 2006-09-30 | 2006-03-16 | 2006-03-16 | 2006-09-28 | 2006-09-28
| 040.12931 | 040.EQUIPMENT - DIVISION AREA | EQUIPMENT FOR KENTUCKY DIVISION | 58384.1 | 63300 | -4915.9 | -7.766% | 0.4116% | 58384.1 | 63300 | -4915.9 | 2005-10-01 | 2006-09-30 | 2006-01-30 | 2006-01-30 | 2006-06-15 | 2006-06-15
| 040.12785 | 040.DAN.3B 4 STEEL-IND PARK | INSTALL 800' OF 4" STEEL ON INDUSTRIAL DR IN THE HUNT INDUSTRIAL PARK FOR 3B COR | 61325.36 | 21500 | 39943.1 | 185.8% | 0.4331% | 61443.1 | 21500 | 39943.1 | 2005-10-01 | 2006-09-30 | 2005-10-03 | 2005-10-03 | 2005-11-01 | 2005-11-01
| 040.13064 | 040.2738.DUFF-JACKS-WICKL MAIN | REPLACE BARE STEEL MAIN ON DUFFY,JACKSON AND WICKLIFFE STREETS | 63741.84 | 151600 | -50352.64 | -33.21% | 0.7138% | 101247.36 | 151600 | -50352.64 | 2005-10-01 | 2006-09-30 | 2006-07-20 | 2006-07-20 | 2008-04-01 | 2008-04-01
| 040.12607 | 040.MAD.LAND O FROST | INSTALL6,360' 4" STL. | 64048.5 | 305025.34 | -65943.38 | -21.62% | 1.685% | 239081.96 | 305025.34 | -65943.38 | 2005-10-01 | 2006-09-30 | 2005-06-10 | 2005-06-10 | 2005-10-20 | 2005-10-20
| 040.12661 | 040.SHV.BROWN-CI SERVICES | REPLACE SERVICES ON THE CAST IRON ON BROWN STREET | 66580.01 | 110300 | -27478.78 | -24.91% | 0.5839% | 82821.22 | 110300 | -27478.78 | 2005-10-01 | 2006-09-30 | 2005-08-16 | 2005-08-16 | 2005-10-15 | 2005-10-15
| 040.13012 | 040.IT Laptop Replacements | Replace Laptop Computers | 67300.92 | 74800 | -7499.08 | -10.03% | 0.4744% | 67300.92 | 74800 | -7499.08 | 2005-10-01 | 2006-09-30 | 2006-03-29 | 2006-03-29 | 2006-09-28 | 2006-09-28
| 040.13022 | 040.PAD.Warehouse Improve II | Warehouse Improvements II incl ceiling, blinds, rear door, office furniture, ref | 73893.29 | 28490 | 46071.31 | 161.7% | 0.5256% | 74561.31 | 28490 | 46071.31 | 2005-10-01 | 2006-09-30 | 2006-04-25 | 2006-04-25 | 2006-09-22 | 2006-09-22
| 040.13017 | 040.PAD.Pecan Dr 2" Relocation | Install 2,865' - 2" PE | 76347.63 | 60736.18 | 15611.45 | 25.7% | 0.5382% | 76347.63 | 60736.18 | 15611.45 | 2005-10-01 | 2006-09-30 | 2006-04-10 | 2006-04-10 | 2006-09-22 | 2006-09-22
| 040.12832 | 040.2737.BAILEY IND PARK 2006 | INSTALL 1075' OF 4" STEEL FROM 3B TOWARDS HWY 34 | 77247.4 | 145 | 77102.4 | 53174% | 0.5446% | 77247.4 | 145 | 77102.4 | 2005-10-01 | 2006-09-30 | 2005-11-29 | 2005-11-29 | 2006-04-15 | 2006-04-15
| 040.12770 | Campbellsville 06 Growth | Campbellsville 06 Growth | 79903.35 | Not Budgeted | - | - | 0.5637% | 79962.84 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12986 | 040.BGR.TRANSPARK 4" STL EXT | 2700 FT.OF 4"STL. - TRANSPARK - BOWLING GREEN | 80738.58 | 89910 | -9171.42 | -10.2% | 0.5692% | 80738.58 | 89910 | -9171.42 | 2005-10-01 | 2006-09-30 | 2006-03-21 | 2006-03-21 | 2006-09-28 | 2006-09-28
| 040.12761 | 040.OBO.2006 FARM TAP PROECT | REPLACE FARM TAPS/PREFAB STATIONS | 83879.14 | 114272.4 | -30393.26 | -26.6% | 0.5913% | 83879.14 | 114272.4 | -30393.26 | 2005-10-01 | 2006-09-30 | 2005-10-03 | 2005-10-03 | 2006-02-28 | 2006-02-28
| 040.13094 | 040.2609 STO HCA Replacement | Replace 10" with 12" in HCA at Gordon Park | 87137.58 | 248949 | 274137.38 | 110.1% | 3.688% | 523086.38 | 248949 | 274137.38 | 2005-10-01 | 2006-09-30 | 2006-08-11 | 2006-08-11 | 2007-09-28 | 2007-09-28
| 040.13065 | 040.2738.DUF-JACK-WICK SERVICE | REPLACE SERVICES ON DUFFY,JACKSON,WICKLIFFE | 88721.96 | 110185 | 10825.69 | 9.825% | 0.8531% | 121010.69 | 110185 | 10825.69 | 2005-10-01 | 2006-09-30 | 2006-07-20 | 2006-07-20 | 2008-04-01 | 2008-04-01
| 040.12830 | 040.OBO.2006 METER PROJECT | PROJECT FOR 2006 METER PURCHASES OWENSBORO | 93997.22 | 129955.62 | -35737.64 | -27.5% | 0.6642% | 94217.98 | 129955.62 | -35737.64 | 2005-10-01 | 2006-09-30 | 2005-11-22 | 2005-11-22 | 2006-09-28 | 2006-09-28
| 040.12934 | 040.OBO.LAND PURCHASE | PURCHASE 150X250 LOT 3415 NEW HARTFORD RD. | 99106.22 | 99106.22 | 0 | 0% | 0.6987% | 99106.22 | 99106.22 | 0 | 2005-10-01 | 2006-09-30 | 2006-01-31 | 2006-01-31 | 2006-03-17 | 2006-03-17
| 040.12660 | 040.SHV.BROWN ST-CI MAIN | REPLACE 6" CAST IRON AND 2" STEEL MAIN | 102295.45 | 153850 | -41366.45 | -26.89% | 0.793% | 112483.55 | 153850 | -41366.45 | 2005-10-01 | 2006-09-30 | 2005-08-16 | 2005-08-16 | 2005-10-15 | 2005-10-15
| 040.12812 | 040.2739.LOCUST CRK SEC 6 | INSTALL 2" AND 4" PE IN LOCUST CREEK IN SECTION 6 | 112002.23 | 88675 | 23327.23 | 26.31% | 0.7896% | 112002.23 | 88675 | 23327.23 | 2005-10-01 | 2006-09-30 | 2005-11-04 | 2005-11-04 | 2006-01-01 | 2006-01-01
| 040.12837 | 040.PAD.'06 Meter Purchases | project to purchase class 1 through class 4 meters for FY 2006 | 114288.86 | 96960.75 | 19754.83 | 20.37% | 0.8228% | 116715.58 | 96960.75 | 19754.83 | 2005-10-01 | 2006-09-30 | 2005-12-01 | 2005-12-01 | 2006-09-22 | 2006-09-22
| 040.12764 | Glasgow 06 Growth | Glasgow 06 Growth | 115372.35 | Not Budgeted | - | - | 0.8134% | 115387.19 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12782 | Mayfield 06 Growth | Mayfield 06 Growth | 117303.19 | Not Budgeted | - | - | 0.8384% | 118922.55 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12766 | Hopkinsville 06 Growth | Hopkinsville 06 Growth | 143033.55 | Not Budgeted | - | - | 1.011% | 143466.49 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12774 | Madisonville 06 Growth | Madisonville 06 Growth | 150395.83 | Not Budgeted | - | - | 1.058% | 150077.06 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.13016 | 040.PAD.Pecan 8 inch Relocate | Install 1,150 ' of 8" T'Line | 166307.8 | 73675.49 | 63645.6 | 86.39% | 0.9681% | 137321.09 | 73675.49 | 63645.6 | 2005-10-01 | 2006-09-30 | 2006-04-10 | 2006-04-10 | 2006-09-22 | 2006-09-22
| 040.12822 | AKY.TCSVC.MEAS.OUTSOURCER | Outsourcing of Meter repair for 2006 PC Year | 175402.07 | 67200 | 108977.55 | 162.2% | 1.242% | 176177.55 | 67200 | 108977.55 | 2005-10-01 | 2006-09-30 | 2005-11-14 | 2005-11-14 | 2006-09-28 | 2006-09-28
| 040.12928 | 040.STO Line 9015900 Swamp | Line 90-159-00 Replacement in Swamp Due to Leakage | 197904.42 | 248936 | 586624.52 | 235.7% | 5.89% | 835560.52 | 248936 | 586624.52 | 2005-10-01 | 2006-09-30 | 2006-01-27 | 2006-01-27 | 2006-09-28 | 2006-09-28
| 040.12793 | 040.2739.HWY 60 RELOCATE | INSTALL 540' OF 6" STEEL ON HWY 60-STATE RELOCATE | 242240.47 | -39540 | 168463.1 | -426.1% | 0.9089% | 128923.1 | -39540 | 168463.1 | 2005-10-01 | 2006-09-30 | 2005-10-18 | 2005-10-18 | 2005-12-25 | 2005-12-25
| 040.12794 | 040.2739.ALCAN 6" STEEL-BYPASS | INSTALL 3160' OF 6" STEEL FOR ALCAN | 288618.74 | 223400 | 65218.74 | 29.19% | 2.035% | 288618.74 | 223400 | 65218.74 | 2005-10-01 | 2006-09-30 | 2005-10-18 | 2005-10-18 | 2005-12-25 | 2005-12-25
| 040.12777 | Princeton 06 Non Growth | Princeton 06 Non Growth | 289763.85 | Not Budgeted | - | - | 2.06% | 292267.41 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12783 | Mayfield 06 Non Growth | Mayfield 06 Non Growth | 300052.48 | Not Budgeted | - | - | 2.145% | 304302.05 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12768 | Danville 06 Growth | Danville 06 Growth | 301649.11 | Not Budgeted | - | - | 2.226% | 315776.48 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12773 | Shelbyville 06 Non Growth | Shelbyville 06 Non Growth | 351063.04 | Not Budgeted | - | - | 2.539% | 360200.53 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12781 | Paducah 06 Non Growth | Paducah 06 Non Growth | 397390.93 | Not Budgeted | - | - | 2.817% | 399553.28 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| OH.040.10000 | WKG BU A&G Overhead | WKG Business Unit A&G Overhead Project | 413668.6 | 0 | -38000 | #DIV/0! | -0.2679% | -38000 | 0 | -38000 | 2005-10-01 | 2006-09-30 | Over | Heads | Over | Heads
| 040.12771 | Campbellsville 06 Non Growth | Campbellsville 06 Non Growth | 457589.97 | Not Budgeted | - | - | 3.252% | 461237.48 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12780 | Paducah 06 Growth | Paducah 06 Growth | 463132.42 | Not Budgeted | - | - | 3.282% | 465570.11 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12769 | Danville 06 Non Growth | Danville 06 Non Growth | 470913.93 | Not Budgeted | - | - | 3.358% | 476385.22 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12767 | Hopkinsville 06 Non Growth | Hopkinsville 06 Non Growth | 510487 | Not Budgeted | - | - | 3.632% | 515205.3 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12775 | Madisonville 06 Non Growth | Madisonville 06 Non Growth | 558355.71 | Not Budgeted | - | - | 3.947% | 559886.75 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12765 | Glasgow 06 Non Growth | Glasgow 06 Non Growth | 658692.66 | Not Budgeted | - | - | 4.679% | 663699.29 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2009-05-13 | 2009-05-13
| 040.12778 | Owensboro 06 Growth | Owensboro 06 Growth | 663625.43 | Not Budgeted | - | - | 4.707% | 667756.84 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12772 | Shelbyville 06 Growth | Shelbyville 06 Growth | 687939.11 | Not Budgeted | - | - | 4.868% | 690488.77 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12922 | St. Charles Engine Overhaul | Overhaul St. Charles Compressor Engine | 896645.24 | 245177 | -59660.99 | -24.33% | 1.308% | 185516.01 | 245177 | -59660.99 | 2005-10-01 | 2006-09-30 | 2006-01-23 | 2006-01-23 | 2006-09-28 | 2006-09-28
| 040.12762 | Bowling Green 06 Growth | Bowling Green 06 Growth Func | 1145219.49 | Not Budgeted | - | - | 8.144% | 1155244.49 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12779 | Owensboro 06 Non Growth | Owensboro 06 Non Growth | 1670753.07 | Not Budgeted | - | - | 11.86% | 1681927.02 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07
| 040.12763 | Bowling Green 06 Non Growth | Bowling Green 06 Non Growth | 1679852.16 | Not Budgeted | - | - | 11.02% | 1562884.63 | Not Budgeted | - | 2005-10-01 | 2006-09-30 | 2005-10-07 | 2005-10-07 | 2005-10-07 | 2005-10-07