## KY 2015 1-18
Atmos Energy Corporation, Kentucky/Mid-States
CWIP Analysis
**Please note that the estimate includes the last approved estimate routed for approval which does not include AIC and reimbursements.
Actuals do include AIC and reimbursements since they are part of our total project charges.
Month | Project | Project Description | Est. start date | Est. complete date | Percent of Elapsed Time | Orginal Budget Estimate** | Most Recent Budget Estimate** | Total Project CWIP Expenditures as of August 31, 2015 | Project Type | Percent of Total Expenditures
201403 | 050.21628 | 050.BGR.GLS.HWY 31W RELOC. | 2008-11-11 | 2009-11-11 | 100% | 53495 | 53495 | 68172.24 | Main Extension Contract | 78.47% | 2485 | 365 | 2015-09-01
201403 | 050.26121 | PRP.050.2734.Pritchardsville | 2011-06-01 | 2011-09-28 | 100% | 140915.71 | 140915.71 | 156243.1 | Non Functional | 90.19% | 1553 | 119 | 2015-09-01
201403 | 050.30574 | PRP.2735.Duke-2nd-Cave City | 2012-04-30 | 2012-09-28 | 100% | 3692.22 | 3692.22 | 789.09 | Non Functional | 467.9% | 1219 | 151 | 2015-09-01
201403 | 050.30863 | 050.2734.northridge VI | 2012-06-04 | 2012-09-28 | 100% | 10147.78 | 10147.78 | 4946.8 | Non Functional | 205.1% | 1184 | 116 | 2015-09-01
201403 | 050.32930 | PRP.2737.HAR.COLLEGE-CORNISH | 2012-09-14 | 2015-09-30 | 97.39% | 665397.26 | 665397.26 | 1253138.73 | Non Functional | 53.1% | 1082 | 1111 | 2015-09-01
201403 | 050.32960 | 050.2734.Hwy31W Reloc - Frk | 2012-11-26 | 2015-09-30 | 97.21% | 225067.56 | 225067.56 | 157598.65 | Non Functional | 142.8% | 1009 | 1038 | 2015-09-01
201403 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201403 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201403 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201403 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201403 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201403 | 050.33087 | PRP.2734.EAST 2ND ST | 2013-05-11 | 2013-05-11 | 100% | 58081.4 | 58081.4 | 44266.05 | Non Functional | 131.2% | 843 | 0 | 2015-09-01
201403 | 050.33144 | PRP Horse Cave SE 2013 | 2013-01-19 | 2015-09-30 | 97.05% | 519599.52 | 519599.52 | 623152.51 | Non Functional | 83.38% | 955 | 984 | 2015-09-01
201403 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201403 | 050.33425 | PRP.2636.Glendale Dr. | 2013-02-05 | 2013-09-28 | 100% | 7245.23 | 7245.23 | 6877.64 | Non Functional | 105.3% | 938 | 235 | 2015-09-01
201403 | 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | 2013-05-01 | 2015-05-01 | 100% | 19511.4 | 19511.4 | 12144.97 | Non Functional | 160.7% | 853 | 730 | 2015-09-01
201403 | 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | 2013-03-01 | 2015-03-01 | 100% | 37316.65 | 37316.65 | 53605.8 | Non Functional | 69.61% | 914 | 730 | 2015-09-01
201403 | 050.34184 | 050.2634.Basket Boiler | 2013-06-01 | 2013-09-28 | 100% | 58782.52 | 58782.52 | 61678.16 | Non Functional | 95.31% | 822 | 119 | 2015-09-01
201403 | 050.34295 | 050.2634.Basket TBS Relo. | 2013-06-01 | 2013-09-28 | 100% | 28790.67 | 28790.67 | 11781.77 | Non Functional | 244.4% | 822 | 119 | 2015-09-01
201403 | 050.34324 | 2737.HAR.PURCH ODOR REPLACE | 2012-10-01 | 2014-09-30 | 100% | 66681.61 | 66681.61 | 59176.21 | Non Functional | 112.7% | 1065 | 729 | 2015-09-01
201403 | 050.34460 | 050.2636.Lafayette St. | 2013-03-15 | 2013-09-28 | 100% | 12046.61 | 12046.61 | 16943.88 | Non Functional | 71.1% | 900 | 197 | 2015-09-01
201403 | 050.34598 | PRP.2738.SOUTH C-VILLE 2013 | 2013-06-01 | 2014-06-01 | 100% | 606799.55 | 606799.55 | 246021.64 | Non Functional | 246.6% | 822 | 365 | 2015-09-01
201403 | 050.34783 | Install 3 inch Mooneys | 2013-08-12 | 2013-09-28 | 100% | 11373.94 | 11373.94 | 8868.76 | Non Functional | 128.2% | 750 | 47 | 2015-09-01
201403 | 050.34794 | 050.2637.Hovekamp Valve | 2013-07-29 | 2013-09-28 | 100% | 5866.24 | 5866.24 | 3660.95 | Non Functional | 160.2% | 764 | 61 | 2015-09-01
201403 | 050.34824 | 2737.STAN.HUBBLE RD HP RELO | 2013-07-29 | 2014-09-02 | 100% | 29706.05 | 29706.05 | 1272.25 | Non Functional | 2335% | 764 | 400 | 2015-09-01
201403 | 050.34844 | PRP.Nashville Rd. Bare Replc | 2013-08-01 | 2013-12-31 | 100% | 12252.7 | 12252.7 | 5568.23 | Non Functional | 220% | 761 | 152 | 2015-09-01
201403 | 050.34845 | PRP.2734.Barren River & Wdfrd | 2013-08-01 | 2013-12-31 | 100% | 123893.13 | 123893.13 | 137769.76 | Non Functional | 89.93% | 761 | 152 | 2015-09-01
201403 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201403 | 050.35002 | 050.2637.13th St Replace | 2013-08-28 | 2013-09-28 | 100% | 3844.33 | 3844.33 | 5144.71 | Non Functional | 74.72% | 734 | 31 | 2015-09-01
201403 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201403 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201403 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201403 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201403 | 050.35072 | 050.3436.OFFICE IMPROVEMENTS | 2013-09-06 | 2013-10-30 | 100% | 25855.2 | 25855.2 | 27843.88 | Non Functional | 92.86% | 725 | 54 | 2015-09-01
201403 | 050.35624 | 050.2636.Circle Dr. | 2013-10-01 | 2014-09-28 | 100% | 2286.7 | 2286.7 | 3724.32 | Non Functional | 61.4% | 700 | 362 | 2015-09-01
201403 | 050.35635 | 2739.OLD MILL SEC 3 2014 | 2013-07-01 | 2014-09-30 | 100% | 10143.73 | 10143.73 | 18477.12 | Non Functional | 54.9% | 792 | 456 | 2015-09-01
201403 | 050.35638 | 2739.HAVEN HILL RD 2014 | 2013-08-01 | 2014-08-01 | 100% | 5036.97 | 5036.97 | -853.14 | Non Functional | -590.4% | 761 | 365 | 2015-09-01
201403 | 050.35644 | 050.2637.Hwy 95 Main Ext | 2013-11-11 | 2014-09-28 | 100% | 2821.01 | 2821.01 | 4484.46 | Non Functional | 62.91% | 659 | 321 | 2015-09-01
201403 | 050.35649 | 2737.DANVILLE EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 42294 | 42294 | 33843.42 | Non Functional | 125% | 700 | 364 | 2015-09-01
201403 | 050.35650 | 2735.GLASGOW EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 39615.31 | 39615.31 | 34454.32 | Non Functional | 115% | 700 | 364 | 2015-09-01
201403 | 050.35652 | 2739.S-VILLE EQUIPMENT 2014 | 2013-10-01 | 2014-11-30 | 100% | 35103.92 | 35103.92 | 39330.85 | Non Functional | 89.25% | 700 | 425 | 2015-09-01
201403 | 050.35664 | 050.2634.Sercice Center Roof | 2013-10-21 | 2014-09-28 | 100% | 56565.21 | 56565.21 | 56690.41 | Non Functional | 99.78% | 680 | 342 | 2015-09-01
201403 | 050.35669 | 050.2602.KMD North PCs | 2013-10-21 | 2014-09-28 | 100% | 130505.38 | 130505.38 | 130764.19 | Non Functional | 99.8% | 680 | 342 | 2015-09-01
201403 | 050.35675 | PRP.2738.Grn.Henry St | 2013-10-01 | 2014-10-01 | 100% | 376921.09 | 376921.09 | 145668.38 | Non Functional | 258.8% | 700 | 365 | 2015-09-01
201403 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201403 | 050.35692 | PRP.2636.E 6TH TRIP REPL | 2013-10-01 | 2014-09-28 | 100% | 417982.34 | 417982.34 | 456648.34 | Non Functional | 91.53% | 700 | 362 | 2015-09-01
201403 | 050.35695 | PRP.2737.Har.Cane Run 2014 | 2013-10-02 | 2014-09-30 | 100% | 477460.6 | 477460.6 | 691586.7 | Non Functional | 69.04% | 699 | 363 | 2015-09-01
201403 | 050.35739 | 050.2609.Wells St. Charles | 2013-11-01 | 2014-09-30 | 100% | 1317457.69 | 1317457.69 | 1165282.64 | Non Functional | 113.1% | 669 | 333 | 2015-09-01
201403 | 050.35762 | WMR for downtown and mall area | 2013-10-01 | 2014-09-30 | 100% | 32030.6 | 32030.6 | 21434.67 | Non Functional | 149.4% | 700 | 364 | 2015-09-01
201403 | 050.35764 | 050.2637.Noble Rd Ext | 2013-11-18 | 2014-09-28 | 100% | 1665.93 | 1665.93 | 2988.38 | Non Functional | 55.75% | 652 | 314 | 2015-09-01
201403 | 050.35780 | 050.2636.TRIP ST SYS IMP REPL | 2013-10-01 | 2014-09-28 | 100% | 451231.73 | 451231.73 | 410376.78 | Non Functional | 110% | 700 | 362 | 2015-09-01
201403 | 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | 2013-09-30 | 2014-10-01 | 100% | 420919.56 | 420919.56 | 192841.68 | Non Functional | 218.3% | 701 | 366 | 2015-09-01
201403 | 050.35827 | 050.2634.University Circle 2 | 2013-11-01 | 2014-09-28 | 100% | 3817.03 | 3817.03 | 3800.22 | Non Functional | 100.4% | 669 | 331 | 2015-09-01
201403 | 050.35840 | 050.2636.Challenger Center 3 | 2013-11-04 | 2014-09-28 | 100% | 3359.12 | 3359.12 | 3654.5 | Non Functional | 91.92% | 666 | 328 | 2015-09-01
201403 | 050.35843 | 050.2638.Torian Cr Relocate | 2013-11-18 | 2014-09-28 | 100% | 22080.05 | 22080.05 | 2738.15 | Non Functional | 806.4% | 652 | 314 | 2015-09-01
201403 | 050.35858 | PRP.2734.BG-11TH & ELM ST | 2013-10-01 | 2014-09-30 | 100% | 85039.34 | 85039.34 | 453860.48 | Non Functional | 18.74% | 700 | 364 | 2015-09-01
201403 | 050.35859 | PRP.2734.OLD LVILLE RD TO RED | 2013-10-01 | 2014-09-30 | 100% | 114299.19 | 114299.19 | 337852.15 | Non Functional | 33.83% | 700 | 364 | 2015-09-01
201403 | 050.35882 | 050.2637.Royal Park Estates | 2013-11-11 | 2014-09-28 | 100% | 10321.68 | 10321.68 | 27396.2 | Non Functional | 37.68% | 659 | 321 | 2015-09-01
201403 | 050.35899 | PRP.2634.S. Seminary St. | 2013-11-01 | 2014-09-28 | 100% | 75764.99 | 137126.81 | 149841.51 | Non Functional | 91.51% | 669 | 331 | 2015-09-01
201403 | 050.35934 | 2739.LOCUST CREEK 10a 2014 | 2013-10-01 | 2014-10-01 | 100% | 7036.14 | 7036.14 | 4522.17 | Non Functional | 155.6% | 700 | 365 | 2015-09-01
201403 | 050.35935 | 2739.HP.HCA.CARDINAL CLUB | 2013-12-01 | 2014-12-01 | 100% | 348793.34 | 348793.34 | 385518.24 | Non Functional | 90.47% | 639 | 365 | 2015-09-01
201403 | 050.35961 | 2735.MUN.HWY 31W RELOCATE | 2013-11-01 | 2014-11-01 | 100% | 52272.79 | 52272.79 | 124462.66 | Non Functional | 42% | 669 | 365 | 2015-09-01
201403 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201403 | 050.36031 | 2737.OFFICE REMODELING 2014 | 2013-10-01 | 2014-09-30 | 100% | 38805.28 | 38805.28 | 67847.76 | Non Functional | 57.19% | 700 | 364 | 2015-09-01
201403 | 050.36032 | 2737.FURN-APPLIANCE 2014 | 2013-10-01 | 2014-09-30 | 100% | 31737.06 | 31737.06 | 45297.56 | Non Functional | 70.06% | 700 | 364 | 2015-09-01
201403 | 050.36058 | 050.2636.Millers Mill Rd. | 2013-11-20 | 2014-09-28 | 100% | 22834.5 | 22834.5 | 23630.41 | Non Functional | 96.63% | 650 | 312 | 2015-09-01
201403 | 050.36059 | 050.2609.Misc EQ. | 2013-12-10 | 2014-11-28 | 100% | 20095.67 | 20095.67 | 20747.91 | Non Functional | 96.86% | 630 | 353 | 2015-09-01
201403 | 050.36074 | 2737.MINOR DRIVE.2014 | 2013-10-01 | 2014-10-01 | 100% | 5496.39 | 5496.39 | 7874.12 | Non Functional | 69.8% | 700 | 365 | 2015-09-01
201403 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201403 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201403 | 050.36132 | PRP.2734.B.G.-Auburn 2014 | 2013-10-14 | 2014-09-30 | 100% | 450096.88 | 450096.88 | 318619.41 | Non Functional | 141.3% | 687 | 351 | 2015-09-01
201403 | 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | 2013-10-02 | 2014-09-30 | 100% | 357169.26 | 357169.26 | 435365.71 | Non Functional | 82.04% | 699 | 363 | 2015-09-01
201403 | 050.36198 | Sensit purchase | 2013-10-01 | 2013-11-30 | 100% | 15677.61 | 15677.61 | 16672.32 | Non Functional | 94.03% | 700 | 60 | 2015-09-01
201403 | 050.36207 | 050.2602.GPS Modems | 2013-12-22 | 2014-09-28 | 100% | 95952 | 95952 | 82165.27 | Non Functional | 116.8% | 618 | 280 | 2015-09-01
201403 | 050.36212 | 050.2734.Equipment FY2014 | 2013-12-26 | 2014-09-30 | 100% | 72368.94 | 72368.94 | 66336.82 | Non Functional | 109.1% | 614 | 278 | 2015-09-01
201403 | 050.36237 | 050.2736.Linneth Dr Ext | 2014-01-16 | 2014-09-28 | 100% | 1085.62 | 1085.62 | 1980.96 | Non Functional | 54.8% | 593 | 255 | 2015-09-01
201403 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201403 | 050.36303 | PRP.2738.GRN.W COL AVE 2014 | 2013-10-02 | 2014-09-30 | 100% | 311198.5 | 311198.5 | 237404.34 | Non Functional | 131.1% | 699 | 363 | 2015-09-01
201403 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201403 | 050.36324 | 2014 Equipment - Mayfield | 2013-10-01 | 2014-09-28 | 100% | 77017.2 | 77017.2 | 79198.46 | Non Functional | 97.25% | 700 | 362 | 2015-09-01
201403 | 050.36349 | 2739.RONNIE LN REG ST SUPPLY | 2014-01-13 | 2015-01-13 | 100% | 9413.03 | 9413.03 | 8037.33 | Non Functional | 117.1% | 596 | 365 | 2015-09-01
201403 | 050.36367 | Equipment Purchase - Princeton | 2013-10-01 | 2014-09-28 | 100% | 2609.59 | 2609.59 | 2904.87 | Non Functional | 89.84% | 700 | 362 | 2015-09-01
201403 | 050.36378 | PRP.2737.E FACTORY-BARE JT | 2014-01-08 | 2015-01-08 | 100% | 131431.43 | 131431.43 | 277467.55 | Non Functional | 47.37% | 601 | 365 | 2015-09-01
201403 | 050.36380 | 2739.CLOVERBROOK 9a 2014 | 2013-10-01 | 2014-10-01 | 100% | 9738.87 | 9738.87 | 11169.68 | Non Functional | 87.19% | 700 | 365 | 2015-09-01
201403 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201403 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201403 | 050.36416 | 2737.BONTA LN 2014 | 2014-02-01 | 2015-02-01 | 100% | 1458.1 | 1458.1 | -15.27 | Non Functional | -9549% | 577 | 365 | 2015-09-01
201403 | 050.36417 | 2737.FURN ST 2014 | 2013-12-01 | 2014-12-01 | 100% | 821.82 | 821.82 | 2243.25 | Non Functional | 36.64% | 639 | 365 | 2015-09-01
201403 | 050.36427 | Paducah Equip Purchases | 2013-10-01 | 2013-11-30 | 100% | 75146.28 | 75146.28 | 86397.13 | Non Functional | 86.98% | 700 | 60 | 2015-09-01
201403 | 050.36475 | 2734.TRENCHER-WALK W/TRAILER | 2013-10-01 | 2014-09-30 | 100% | 21481.5 | 21481.5 | 22648.19 | Non Functional | 94.85% | 700 | 364 | 2015-09-01
201403 | 050.36511 | 050.2609.St Charles Building | 2014-02-01 | 2014-09-28 | 100% | 90000 | 90000 | 85727.13 | Non Functional | 105% | 577 | 239 | 2015-09-01
201403 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201403 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201403 | 050.36577 | Replace ground bed - G.R | 2013-10-01 | 2014-09-28 | 100% | 8460.22 | 8460.22 | 17960.5 | Non Functional | 47.1% | 700 | 362 | 2015-09-01
201403 | 050.36611 | PRP.2735.MUN.E UNION ST 2014 | 2013-10-04 | 2014-09-30 | 100% | 141792.06 | 141792.06 | 150044.31 | Non Functional | 94.5% | 697 | 361 | 2015-09-01
201403 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201403 | 050.36655 | PRP.2735.MUN.MILL ST 2014 | 2014-01-01 | 2015-01-01 | 100% | 180214.35 | 180214.35 | 129421.42 | Non Functional | 139.2% | 608 | 365 | 2015-09-01
201403 | 050.36696 | 050.2634.Robards TB Station | 2014-02-01 | 2014-10-28 | 100% | 146685.57 | 146685.57 | 157690.6 | Non Functional | 93.02% | 577 | 269 | 2015-09-01
201403 | 050.36708 | PRP.2737.N MAIN.PRICE 2014 | 2014-03-01 | 2015-03-01 | 100% | 374542.02 | 374542.02 | 492199.27 | Non Functional | 76.1% | 549 | 365 | 2015-09-01
201403 | 050.36740 | 050.2637.Chappell Rd Rev Ext | 2014-03-24 | 2014-09-28 | 100% | 2006.5 | 2006.5 | 4028.36 | Non Functional | 49.81% | 526 | 188 | 2015-09-01
201403 | 050.36765 | 2738.NOE_RD_CHICKEN_HOUSES | 2014-02-01 | 2015-02-01 | 100% | 69507.65 | 69507.65 | 43654.45 | Non Functional | 159.2% | 577 | 365 | 2015-09-01
201403 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201403 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201403 | 050.36902 | 050.2734.Hwy31W Public Imprv | 2014-02-17 | 2014-09-28 | 100% | 246623.13 | 246623.13 | -2297.86 | Non Functional | -10733% | 561 | 223 | 2015-09-01
201403 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201403 | 050.37008 | 050.2637.Royal Park 2 | 2014-04-14 | 2014-05-01 | 100% | 2325.49 | 2325.49 | 2054.07 | Non Functional | 113.2% | 505 | 17 | 2015-09-01
201403 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201404 | 050.21628 | 050.BGR.GLS.HWY 31W RELOC. | 2008-11-11 | 2009-11-11 | 100% | 53495 | 53495 | 68172.24 | Non Functional | 78.47% | 2485 | 365 | 2015-09-01
201404 | 050.26121 | PRP.050.2734.Pritchardsville | 2011-06-01 | 2011-09-28 | 100% | 140915.71 | 140915.71 | 156243.1 | Non Functional | 90.19% | 1553 | 119 | 2015-09-01
201404 | 050.30574 | PRP.2735.Duke-2nd-Cave City | 2012-04-30 | 2012-09-28 | 100% | 3692.22 | 3692.22 | 789.09 | Non Functional | 467.9% | 1219 | 151 | 2015-09-01
201404 | 050.30863 | 050.2734.northridge VI | 2012-06-04 | 2012-09-28 | 100% | 10147.78 | 10147.78 | 4946.8 | Non Functional | 205.1% | 1184 | 116 | 2015-09-01
201404 | 050.32960 | 050.2734.Hwy31W Reloc - Frk | 2012-11-26 | 2015-09-30 | 97.21% | 225067.56 | 225067.56 | 157598.65 | Non Functional | 142.8% | 1009 | 1038 | 2015-09-01
201404 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201404 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201404 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201404 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201404 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201404 | 050.33087 | PRP.2734.EAST 2ND ST | 2013-05-11 | 2013-05-11 | 100% | 58081.4 | 58081.4 | 44266.05 | Non Functional | 131.2% | 843 | 0 | 2015-09-01
201404 | 050.33144 | PRP Horse Cave SE 2013 | 2013-01-19 | 2015-09-30 | 97.05% | 519599.52 | 519599.52 | 623152.51 | Non Functional | 83.38% | 955 | 984 | 2015-09-01
201404 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201404 | 050.33425 | PRP.2636.Glendale Dr. | 2013-02-05 | 2013-09-28 | 100% | 7245.23 | 7245.23 | 6877.64 | Non Functional | 105.3% | 938 | 235 | 2015-09-01
201404 | 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | 2013-05-01 | 2015-05-01 | 100% | 19511.4 | 19511.4 | 12144.97 | Non Functional | 160.7% | 853 | 730 | 2015-09-01
201404 | 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | 2013-03-01 | 2015-03-01 | 100% | 37316.65 | 37316.65 | 53605.8 | Non Functional | 69.61% | 914 | 730 | 2015-09-01
201404 | 050.34184 | 050.2634.Basket Boiler | 2013-06-01 | 2013-09-28 | 100% | 58782.52 | 58782.52 | 61678.16 | Non Functional | 95.31% | 822 | 119 | 2015-09-01
201404 | 050.34295 | 050.2634.Basket TBS Relo. | 2013-06-01 | 2013-09-28 | 100% | 28790.67 | 28790.67 | 11781.77 | Non Functional | 244.4% | 822 | 119 | 2015-09-01
201404 | 050.34324 | 2737.HAR.PURCH ODOR REPLACE | 2012-10-01 | 2014-09-30 | 100% | 66681.61 | 66681.61 | 59176.21 | Non Functional | 112.7% | 1065 | 729 | 2015-09-01
201404 | 050.34460 | 050.2636.Lafayette St. | 2013-03-15 | 2013-09-28 | 100% | 12046.61 | 12046.61 | 16943.88 | Non Functional | 71.1% | 900 | 197 | 2015-09-01
201404 | 050.34783 | Install 3 inch Mooneys | 2013-08-12 | 2013-09-28 | 100% | 11373.94 | 11373.94 | 8868.76 | Non Functional | 128.2% | 750 | 47 | 2015-09-01
201404 | 050.34794 | 050.2637.Hovekamp Valve | 2013-07-29 | 2013-09-28 | 100% | 5866.24 | 5866.24 | 3660.95 | Non Functional | 160.2% | 764 | 61 | 2015-09-01
201404 | 050.34824 | 2737.STAN.HUBBLE RD HP RELO | 2013-07-29 | 2014-09-02 | 100% | 29706.05 | 29706.05 | 1272.25 | Non Functional | 2335% | 764 | 400 | 2015-09-01
201404 | 050.34844 | PRP.Nashville Rd. Bare Replc | 2013-08-01 | 2013-12-31 | 100% | 12252.7 | 12252.7 | 5568.23 | Non Functional | 220% | 761 | 152 | 2015-09-01
201404 | 050.34845 | PRP.2734.Barren River & Wdfrd | 2013-08-01 | 2013-12-31 | 100% | 123893.13 | 123893.13 | 137769.76 | Non Functional | 89.93% | 761 | 152 | 2015-09-01
201404 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201404 | 050.35002 | 050.2637.13th St Replace | 2013-08-28 | 2013-09-28 | 100% | 3844.33 | 3844.33 | 5144.71 | Non Functional | 74.72% | 734 | 31 | 2015-09-01
201404 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201404 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201404 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201404 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201404 | 050.35072 | 050.3436.OFFICE IMPROVEMENTS | 2013-09-06 | 2013-10-30 | 100% | 25855.2 | 25855.2 | 27843.88 | Non Functional | 92.86% | 725 | 54 | 2015-09-01
201404 | 050.35635 | 2739.OLD MILL SEC 3 2014 | 2013-07-01 | 2014-09-30 | 100% | 10143.73 | 10143.73 | 18477.12 | Non Functional | 54.9% | 792 | 456 | 2015-09-01
201404 | 050.35644 | 050.2637.Hwy 95 Main Ext | 2013-11-11 | 2014-09-28 | 100% | 2821.01 | 2821.01 | 4484.46 | Non Functional | 62.91% | 659 | 321 | 2015-09-01
201404 | 050.35649 | 2737.DANVILLE EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 42294 | 42294 | 33843.42 | Non Functional | 125% | 700 | 364 | 2015-09-01
201404 | 050.35650 | 2735.GLASGOW EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 39615.31 | 39615.31 | 34454.32 | Non Functional | 115% | 700 | 364 | 2015-09-01
201404 | 050.35652 | 2739.S-VILLE EQUIPMENT 2014 | 2013-10-01 | 2014-11-30 | 100% | 35103.92 | 35103.92 | 39330.85 | Non Functional | 89.25% | 700 | 425 | 2015-09-01
201404 | 050.35664 | 050.2634.Sercice Center Roof | 2013-10-21 | 2014-09-28 | 100% | 56565.21 | 56565.21 | 56690.41 | Non Functional | 99.78% | 680 | 342 | 2015-09-01
201404 | 050.35669 | 050.2602.KMD North PCs | 2013-10-21 | 2014-09-28 | 100% | 130505.38 | 130505.38 | 130764.19 | Non Functional | 99.8% | 680 | 342 | 2015-09-01
201404 | 050.35675 | PRP.2738.Grn.Henry St | 2013-10-01 | 2014-10-01 | 100% | 376921.09 | 376921.09 | 145668.38 | Non Functional | 258.8% | 700 | 365 | 2015-09-01
201404 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201404 | 050.35692 | PRP.2636.E 6TH TRIP REPL | 2013-10-01 | 2014-09-28 | 100% | 417982.34 | 417982.34 | 456648.34 | Non Functional | 91.53% | 700 | 362 | 2015-09-01
201404 | 050.35695 | PRP.2737.Har.Cane Run 2014 | 2013-10-02 | 2014-09-30 | 100% | 477460.6 | 477460.6 | 691586.7 | Non Functional | 69.04% | 699 | 363 | 2015-09-01
201404 | 050.35739 | 050.2609.Wells St. Charles | 2013-11-01 | 2014-09-30 | 100% | 1317457.69 | 1317457.69 | 1165282.64 | Non Functional | 113.1% | 669 | 333 | 2015-09-01
201404 | 050.35762 | WMR for downtown and mall area | 2013-10-01 | 2014-09-30 | 100% | 32030.6 | 32030.6 | 21434.67 | Non Functional | 149.4% | 700 | 364 | 2015-09-01
201404 | 050.35764 | 050.2637.Noble Rd Ext | 2013-11-18 | 2014-09-28 | 100% | 1665.93 | 1665.93 | 2988.38 | Non Functional | 55.75% | 652 | 314 | 2015-09-01
201404 | 050.35780 | 050.2636.TRIP ST SYS IMP REPL | 2013-10-01 | 2014-09-28 | 100% | 451231.73 | 451231.73 | 410376.78 | Non Functional | 110% | 700 | 362 | 2015-09-01
201404 | 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | 2013-09-30 | 2014-10-01 | 100% | 420919.56 | 420919.56 | 192841.68 | Non Functional | 218.3% | 701 | 366 | 2015-09-01
201404 | 050.35843 | 050.2638.Torian Cr Relocate | 2013-11-18 | 2014-09-28 | 100% | 22080.05 | 22080.05 | 2738.15 | Non Functional | 806.4% | 652 | 314 | 2015-09-01
201404 | 050.35856 | ERX's for use in Graves County | 2013-10-01 | 2014-09-30 | 100% | 18293.88 | 18293.88 | 18364.45 | Non Functional | 99.62% | 700 | 364 | 2015-09-01
201404 | 050.35858 | PRP.2734.BG-11TH & ELM ST | 2013-10-01 | 2014-09-30 | 100% | 85039.34 | 85039.34 | 453860.48 | Non Functional | 18.74% | 700 | 364 | 2015-09-01
201404 | 050.35859 | PRP.2734.OLD LVILLE RD TO RED | 2013-10-01 | 2014-09-30 | 100% | 114299.19 | 114299.19 | 337852.15 | Non Functional | 33.83% | 700 | 364 | 2015-09-01
201404 | 050.35882 | 050.2637.Royal Park Estates | 2013-11-11 | 2014-09-28 | 100% | 10321.68 | 10321.68 | 27396.2 | Non Functional | 37.68% | 659 | 321 | 2015-09-01
201404 | 050.35899 | PRP.2634.S. Seminary St. | 2013-11-01 | 2014-09-28 | 100% | 75764.99 | 137126.81 | 149841.51 | Non Functional | 91.51% | 669 | 331 | 2015-09-01
201404 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201404 | 050.36032 | 2737.FURN-APPLIANCE 2014 | 2013-10-01 | 2014-09-30 | 100% | 31737.06 | 31737.06 | 45297.56 | Non Functional | 70.06% | 700 | 364 | 2015-09-01
201404 | 050.36059 | 050.2609.Misc EQ. | 2013-12-10 | 2014-11-28 | 100% | 20095.67 | 20095.67 | 20747.91 | Non Functional | 96.86% | 630 | 353 | 2015-09-01
201404 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201404 | 050.36120 | Large Com/Indus Meter KY | 2013-12-09 | 2014-02-01 | 100% | 22930.23 | 22930.23 | 1909.16 | Non Functional | 1201% | 631 | 54 | 2015-09-01
201404 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201404 | 050.36132 | PRP.2734.B.G.-Auburn 2014 | 2013-10-14 | 2014-09-30 | 100% | 450096.88 | 450096.88 | 318619.41 | Non Functional | 141.3% | 687 | 351 | 2015-09-01
201404 | 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | 2013-10-02 | 2014-09-30 | 100% | 357169.26 | 357169.26 | 435365.71 | Non Functional | 82.04% | 699 | 363 | 2015-09-01
201404 | 050.36207 | 050.2602.GPS Modems | 2013-12-22 | 2014-09-28 | 100% | 95952 | 95952 | 82165.27 | Non Functional | 116.8% | 618 | 280 | 2015-09-01
201404 | 050.36212 | 050.2734.Equipment FY2014 | 2013-12-26 | 2014-09-30 | 100% | 72368.94 | 72368.94 | 66336.82 | Non Functional | 109.1% | 614 | 278 | 2015-09-01
201404 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201404 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201404 | 050.36303 | PRP.2738.GRN.W COL AVE 2014 | 2013-10-02 | 2014-09-30 | 100% | 311198.5 | 311198.5 | 237404.34 | Non Functional | 131.1% | 699 | 363 | 2015-09-01
201404 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201404 | 050.36324 | 2014 Equipment - Mayfield | 2013-10-01 | 2014-09-28 | 100% | 77017.2 | 77017.2 | 79198.46 | Non Functional | 97.25% | 700 | 362 | 2015-09-01
201404 | 050.36378 | PRP.2737.E FACTORY-BARE JT | 2014-01-08 | 2015-01-08 | 100% | 131431.43 | 131431.43 | 277467.55 | Non Functional | 47.37% | 601 | 365 | 2015-09-01
201404 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201404 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201404 | 050.36427 | Paducah Equip Purchases | 2013-10-01 | 2013-11-30 | 100% | 75146.28 | 75146.28 | 86397.13 | Non Functional | 86.98% | 700 | 60 | 2015-09-01
201404 | 050.36475 | 2734.TRENCHER-WALK W/TRAILER | 2013-10-01 | 2014-09-30 | 100% | 21481.5 | 21481.5 | 22648.19 | Non Functional | 94.85% | 700 | 364 | 2015-09-01
201404 | 050.36511 | 050.2609.St Charles Building | 2014-02-01 | 2014-09-28 | 100% | 90000 | 90000 | 85727.13 | Non Functional | 105% | 577 | 239 | 2015-09-01
201404 | 050.36519 | 050.2734.North-South2inchRep | 2013-12-03 | 2014-09-28 | 100% | 3211.56 | 3211.56 | 788.51 | Non Functional | 407.3% | 637 | 299 | 2015-09-01
201404 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201404 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201404 | 050.36577 | Replace ground bed - G.R | 2013-10-01 | 2014-09-28 | 100% | 8460.22 | 8460.22 | 17960.5 | Non Functional | 47.1% | 700 | 362 | 2015-09-01
201404 | 050.36611 | PRP.2735.MUN.E UNION ST 2014 | 2013-10-04 | 2014-09-30 | 100% | 141792.06 | 141792.06 | 150044.31 | Non Functional | 94.5% | 697 | 361 | 2015-09-01
201404 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201404 | 050.36655 | PRP.2735.MUN.MILL ST 2014 | 2014-01-01 | 2015-01-01 | 100% | 180214.35 | 180214.35 | 129421.42 | Non Functional | 139.2% | 608 | 365 | 2015-09-01
201404 | 050.36696 | 050.2634.Robards TB Station | 2014-02-01 | 2014-10-28 | 100% | 146685.57 | 146685.57 | 157690.6 | Non Functional | 93.02% | 577 | 269 | 2015-09-01
201404 | 050.36708 | PRP.2737.N MAIN.PRICE 2014 | 2014-03-01 | 2015-03-01 | 100% | 374542.02 | 374542.02 | 492199.27 | Non Functional | 76.1% | 549 | 365 | 2015-09-01
201404 | 050.36740 | 050.2637.Chappell Rd Rev Ext | 2014-03-24 | 2014-09-28 | 100% | 2006.5 | 2006.5 | 4028.36 | Non Functional | 49.81% | 526 | 188 | 2015-09-01
201404 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201404 | 050.36790 | 050.2636.Hwy 951 Phase 2 | 2014-04-25 | 2014-09-28 | 100% | 10923.28 | 10923.28 | 6933.08 | Non Functional | 157.6% | 494 | 156 | 2015-09-01
201404 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201404 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201404 | 050.36902 | 050.2734.Hwy31W Public Imprv | 2014-02-17 | 2014-09-28 | 100% | 246623.13 | 246623.13 | -2297.86 | Non Functional | -10733% | 561 | 223 | 2015-09-01
201404 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201404 | 050.37007 | 050.2634.College Dr. Reloc. | 2014-05-01 | 2014-09-28 | 100% | 23277.86 | 23277.86 | -5957.89 | Non Functional | -390.7% | 488 | 150 | 2015-09-01
201404 | 050.37008 | 050.2637.Royal Park 2 | 2014-04-14 | 2014-05-01 | 100% | 2325.49 | 2325.49 | 2054.07 | Non Functional | 113.2% | 505 | 17 | 2015-09-01
201404 | 050.37016 | 050.2637.Ky Dam Rd Ext | 2014-04-15 | 2014-05-15 | 100% | 1508.22 | 1508.22 | 2568.99 | Non Functional | 58.71% | 504 | 30 | 2015-09-01
201404 | 050.37025 | 050.2636.Hill Bridge | 2014-05-01 | 2014-09-28 | 100% | 7807.26 | 7807.26 | 7092.91 | Non Functional | 110.1% | 488 | 150 | 2015-09-01
201404 | 050.37031 | 050.2636.Sterling Park 2 | 2014-04-01 | 2014-09-28 | 100% | 12497.42 | 12497.42 | 11629.92 | Non Functional | 107.5% | 518 | 180 | 2015-09-01
201404 | 050.37040 | 050.2734.Massey Springs III | 2014-03-31 | 2014-09-28 | 100% | 5269.9 | 5269.9 | 3957.59 | Non Functional | 133.2% | 519 | 181 | 2015-09-01
201404 | 050.37054 | 050.2734.2 inchExt.Cableas | 2014-04-01 | 2014-09-28 | 100% | 8137.88 | 8137.88 | 5041.95 | Non Functional | 161.4% | 518 | 180 | 2015-09-01
201404 | 050.37067 | 050.2636.Thompson Dr. | 2014-06-20 | 2014-09-28 | 100% | 5171.35 | 5171.35 | 5999.26 | Non Functional | 86.2% | 438 | 100 | 2015-09-01
201404 | 050.37077 | 050.2734.ThreeSprings II.Hwy | 2014-03-31 | 2014-09-28 | 100% | 730962.37 | 730962.37 | 101956.53 | Non Functional | 716.9% | 519 | 181 | 2015-09-01
201404 | 050.37105 | 2738. WEST MARTIN 2014 | 2014-03-01 | 2015-03-01 | 100% | 4953.9 | 4953.9 | 2833.03 | Non Functional | 174.9% | 549 | 365 | 2015-09-01
201404 | 050.37108 | 050.2637.Londonderry Ln Ext | 2014-04-14 | 2014-05-14 | 100% | 1172.63 | 1172.63 | 4821.5 | Non Functional | 24.32% | 505 | 30 | 2015-09-01
201404 | 050.37118 | 050.2636.Sir Wren | 2014-06-10 | 2014-09-28 | 100% | 5242.61 | 5242.61 | 3765.79 | Non Functional | 139.2% | 448 | 110 | 2015-09-01
201404 | 050.37132 | 050.2636.Middleground Dr.2 | 2014-07-01 | 2014-09-28 | 100% | 4234.18 | 4234.18 | 3809.35 | Non Functional | 111.2% | 427 | 89 | 2015-09-01
201404 | 050.37169 | 2739.BOONE STAT 6 PE-SYS IMPR | 2014-05-01 | 2015-05-01 | 100% | 53220.11 | 53220.11 | 54715.65 | Non Functional | 97.27% | 488 | 365 | 2015-09-01
201404 | 050.37185 | PRP.2635.Dawson Road Repl | 2014-04-15 | 2014-06-01 | 100% | 3095.75 | 3095.75 | 3322.12 | Non Functional | 93.19% | 504 | 47 | 2015-09-01
201404 | 050.37232 | 2738.NOE RD. SYS IMP 2014 | 2014-04-15 | 2015-04-15 | 100% | 6665.6 | 6665.6 | 4088.41 | Non Functional | 163% | 504 | 365 | 2015-09-01
201404 | 050.37233 | 2738.SALOMA RD 2014 | 2014-04-15 | 2015-04-15 | 100% | 8584.68 | 8584.68 | 1497.18 | Non Functional | 573.4% | 504 | 365 | 2015-09-01
201404 | 050.37250 | 050.2636.Bridgewood | 2014-06-01 | 2014-08-01 | 100% | 9815.13 | 9815.13 | 11316.37 | Non Functional | 86.73% | 457 | 61 | 2015-09-01
201404 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201404 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201405 | 050.30574 | PRP.2735.Duke-2nd-Cave City | 2012-04-30 | 2012-09-28 | 100% | 3692.22 | 3692.22 | 789.09 | Non Functional | 467.9% | 1219 | 151 | 2015-09-01
201405 | 050.30863 | 050.2734.northridge VI | 2012-06-04 | 2012-09-28 | 100% | 10147.78 | 10147.78 | 4946.8 | Non Functional | 205.1% | 1184 | 116 | 2015-09-01
201405 | 050.32960 | 050.2734.Hwy31W Reloc - Frk | 2012-11-26 | 2015-09-30 | 97.21% | 225067.56 | 225067.56 | 157598.65 | Non Functional | 142.8% | 1009 | 1038 | 2015-09-01
201405 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201405 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201405 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201405 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201405 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201405 | 050.33087 | PRP.2734.EAST 2ND ST | 2013-05-11 | 2013-05-11 | 100% | 58081.4 | 58081.4 | 44266.05 | Non Functional | 131.2% | 843 | 0 | 2015-09-01
201405 | 050.33144 | PRP Horse Cave SE 2013 | 2013-01-19 | 2015-09-30 | 97.05% | 519599.52 | 519599.52 | 623152.51 | Non Functional | 83.38% | 955 | 984 | 2015-09-01
201405 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201405 | 050.33425 | PRP.2636.Glendale Dr. | 2013-02-05 | 2013-09-28 | 100% | 7245.23 | 7245.23 | 6877.64 | Non Functional | 105.3% | 938 | 235 | 2015-09-01
201405 | 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | 2013-05-01 | 2015-05-01 | 100% | 19511.4 | 19511.4 | 12144.97 | Non Functional | 160.7% | 853 | 730 | 2015-09-01
201405 | 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | 2013-03-01 | 2015-03-01 | 100% | 37316.65 | 37316.65 | 53605.8 | Non Functional | 69.61% | 914 | 730 | 2015-09-01
201405 | 050.34184 | 050.2634.Basket Boiler | 2013-06-01 | 2013-09-28 | 100% | 58782.52 | 58782.52 | 61678.16 | Non Functional | 95.31% | 822 | 119 | 2015-09-01
201405 | 050.34295 | 050.2634.Basket TBS Relo. | 2013-06-01 | 2013-09-28 | 100% | 28790.67 | 28790.67 | 11781.77 | Non Functional | 244.4% | 822 | 119 | 2015-09-01
201405 | 050.34324 | 2737.HAR.PURCH ODOR REPLACE | 2012-10-01 | 2014-09-30 | 100% | 66681.61 | 66681.61 | 59176.21 | Non Functional | 112.7% | 1065 | 729 | 2015-09-01
201405 | 050.34460 | 050.2636.Lafayette St. | 2013-03-15 | 2013-09-28 | 100% | 12046.61 | 12046.61 | 16943.88 | Non Functional | 71.1% | 900 | 197 | 2015-09-01
201405 | 050.34824 | 2737.STAN.HUBBLE RD HP RELO | 2013-07-29 | 2014-09-02 | 100% | 29706.05 | 29706.05 | 1272.25 | Non Functional | 2335% | 764 | 400 | 2015-09-01
201405 | 050.34844 | PRP.Nashville Rd. Bare Replc | 2013-08-01 | 2013-12-31 | 100% | 12252.7 | 12252.7 | 5568.23 | Non Functional | 220% | 761 | 152 | 2015-09-01
201405 | 050.34845 | PRP.2734.Barren River & Wdfrd | 2013-08-01 | 2013-12-31 | 100% | 123893.13 | 123893.13 | 137769.76 | Non Functional | 89.93% | 761 | 152 | 2015-09-01
201405 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201405 | 050.35002 | 050.2637.13th St Replace | 2013-08-28 | 2013-09-28 | 100% | 3844.33 | 3844.33 | 5144.71 | Non Functional | 74.72% | 734 | 31 | 2015-09-01
201405 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201405 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201405 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201405 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201405 | 050.35635 | 2739.OLD MILL SEC 3 2014 | 2013-07-01 | 2014-09-30 | 100% | 10143.73 | 10143.73 | 18477.12 | Non Functional | 54.9% | 792 | 456 | 2015-09-01
201405 | 050.35649 | 2737.DANVILLE EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 42294 | 42294 | 33843.42 | Non Functional | 125% | 700 | 364 | 2015-09-01
201405 | 050.35650 | 2735.GLASGOW EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 39615.31 | 39615.31 | 34454.32 | Non Functional | 115% | 700 | 364 | 2015-09-01
201405 | 050.35652 | 2739.S-VILLE EQUIPMENT 2014 | 2013-10-01 | 2014-11-30 | 100% | 35103.92 | 35103.92 | 39330.85 | Non Functional | 89.25% | 700 | 425 | 2015-09-01
201405 | 050.35669 | 050.2602.KMD North PCs | 2013-10-21 | 2014-09-28 | 100% | 130505.38 | 130505.38 | 130764.19 | Non Functional | 99.8% | 680 | 342 | 2015-09-01
201405 | 050.35675 | PRP.2738.Grn.Henry St | 2013-10-01 | 2014-10-01 | 100% | 376921.09 | 376921.09 | 145668.38 | Non Functional | 258.8% | 700 | 365 | 2015-09-01
201405 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201405 | 050.35692 | PRP.2636.E 6TH TRIP REPL | 2013-10-01 | 2014-09-28 | 100% | 417982.34 | 417982.34 | 456648.34 | Non Functional | 91.53% | 700 | 362 | 2015-09-01
201405 | 050.35695 | PRP.2737.Har.Cane Run 2014 | 2013-10-02 | 2014-09-30 | 100% | 477460.6 | 477460.6 | 691586.7 | Non Functional | 69.04% | 699 | 363 | 2015-09-01
201405 | 050.35739 | 050.2609.Wells St. Charles | 2013-11-01 | 2014-09-30 | 100% | 1317457.69 | 1317457.69 | 1165282.64 | Non Functional | 113.1% | 669 | 333 | 2015-09-01
201405 | 050.35762 | WMR for downtown and mall area | 2013-10-01 | 2014-09-30 | 100% | 32030.6 | 32030.6 | 21434.67 | Non Functional | 149.4% | 700 | 364 | 2015-09-01
201405 | 050.35780 | 050.2636.TRIP ST SYS IMP REPL | 2013-10-01 | 2014-09-28 | 100% | 451231.73 | 451231.73 | 410376.78 | Non Functional | 110% | 700 | 362 | 2015-09-01
201405 | 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | 2013-09-30 | 2014-10-01 | 100% | 420919.56 | 420919.56 | 192841.68 | Non Functional | 218.3% | 701 | 366 | 2015-09-01
201405 | 050.35856 | ERX's for use in Graves County | 2013-10-01 | 2014-09-30 | 100% | 18293.88 | 18293.88 | 18364.45 | Non Functional | 99.62% | 700 | 364 | 2015-09-01
201405 | 050.35858 | PRP.2734.BG-11TH & ELM ST | 2013-10-01 | 2014-09-30 | 100% | 85039.34 | 85039.34 | 453860.48 | Non Functional | 18.74% | 700 | 364 | 2015-09-01
201405 | 050.35859 | PRP.2734.OLD LVILLE RD TO RED | 2013-10-01 | 2014-09-30 | 100% | 114299.19 | 114299.19 | 337852.15 | Non Functional | 33.83% | 700 | 364 | 2015-09-01
201405 | 050.35899 | PRP.2634.S. Seminary St. | 2013-11-01 | 2014-09-28 | 100% | 75764.99 | 137126.81 | 149841.51 | Non Functional | 91.51% | 669 | 331 | 2015-09-01
201405 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201405 | 050.36032 | 2737.FURN-APPLIANCE 2014 | 2013-10-01 | 2014-09-30 | 100% | 31737.06 | 31737.06 | 45297.56 | Non Functional | 70.06% | 700 | 364 | 2015-09-01
201405 | 050.36059 | 050.2609.Misc EQ. | 2013-12-10 | 2014-11-28 | 100% | 20095.67 | 20095.67 | 20747.91 | Non Functional | 96.86% | 630 | 353 | 2015-09-01
201405 | 050.36061 | 050.2609.Rectifier & Pumps | 2013-12-10 | 2014-09-28 | 100% | 20854.8 | 20854.8 | 10237.72 | Non Functional | 203.7% | 630 | 292 | 2015-09-01
201405 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201405 | 050.36109 | ECAT Replacement KY | 2013-12-09 | 2014-04-01 | 100% | 53041.48 | 53041.48 | 51711.08 | Non Functional | 102.6% | 631 | 113 | 2015-09-01
201405 | 050.36113 | Electronic Correctors KY | 2013-12-09 | 2014-10-01 | 100% | 34518.05 | 34518.05 | 17984.32 | Non Functional | 191.9% | 631 | 296 | 2015-09-01
201405 | 050.36117 | Emergency Regulators KY | 2013-12-09 | 2014-09-01 | 100% | 31904.24 | 31904.24 | 1778.7 | Non Functional | 1794% | 631 | 266 | 2015-09-01
201405 | 050.36120 | Large Com/Indus Meter KY | 2013-12-09 | 2014-02-01 | 100% | 22930.23 | 22930.23 | 1909.16 | Non Functional | 1201% | 631 | 54 | 2015-09-01
201405 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201405 | 050.36132 | PRP.2734.B.G.-Auburn 2014 | 2013-10-14 | 2014-09-30 | 100% | 450096.88 | 450096.88 | 318619.41 | Non Functional | 141.3% | 687 | 351 | 2015-09-01
201405 | 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | 2013-10-02 | 2014-09-30 | 100% | 357169.26 | 357169.26 | 435365.71 | Non Functional | 82.04% | 699 | 363 | 2015-09-01
201405 | 050.36207 | 050.2602.GPS Modems | 2013-12-22 | 2014-09-28 | 100% | 95952 | 95952 | 82165.27 | Non Functional | 116.8% | 618 | 280 | 2015-09-01
201405 | 050.36212 | 050.2734.Equipment FY2014 | 2013-12-26 | 2014-09-30 | 100% | 72368.94 | 72368.94 | 66336.82 | Non Functional | 109.1% | 614 | 278 | 2015-09-01
201405 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201405 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201405 | 050.36302 | PRP.2737.HAR.GREENBR SUB 2014 | 2013-09-26 | 2014-10-01 | 100% | 770435.2 | 770435.2 | 372242.77 | Non Functional | 207% | 705 | 370 | 2015-09-01
201405 | 050.36303 | PRP.2738.GRN.W COL AVE 2014 | 2013-10-02 | 2014-09-30 | 100% | 311198.5 | 311198.5 | 237404.34 | Non Functional | 131.1% | 699 | 363 | 2015-09-01
201405 | 050.36306 | ERX project - Hopkinsville | 2013-10-01 | 2014-09-30 | 100% | 7544.83 | 7544.83 | 9034.64 | Non Functional | 83.51% | 700 | 364 | 2015-09-01
201405 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201405 | 050.36324 | 2014 Equipment - Mayfield | 2013-10-01 | 2014-09-28 | 100% | 77017.2 | 77017.2 | 79198.46 | Non Functional | 97.25% | 700 | 362 | 2015-09-01
201405 | 050.36378 | PRP.2737.E FACTORY-BARE JT | 2014-01-08 | 2015-01-08 | 100% | 131431.43 | 131431.43 | 277467.55 | Non Functional | 47.37% | 601 | 365 | 2015-09-01
201405 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201405 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201405 | 050.36427 | Paducah Equip Purchases | 2013-10-01 | 2013-11-30 | 100% | 75146.28 | 75146.28 | 86397.13 | Non Functional | 86.98% | 700 | 60 | 2015-09-01
201405 | 050.36475 | 2734.TRENCHER-WALK W/TRAILER | 2013-10-01 | 2014-09-30 | 100% | 21481.5 | 21481.5 | 22648.19 | Non Functional | 94.85% | 700 | 364 | 2015-09-01
201405 | 050.36511 | 050.2609.St Charles Building | 2014-02-01 | 2014-09-28 | 100% | 90000 | 90000 | 85727.13 | Non Functional | 105% | 577 | 239 | 2015-09-01
201405 | 050.36519 | 050.2734.North-South2inchRep | 2013-12-03 | 2014-09-28 | 100% | 3211.56 | 3211.56 | 788.51 | Non Functional | 407.3% | 637 | 299 | 2015-09-01
201405 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201405 | 050.36528 | 050.2609.St. Charles Furniture | 2014-06-01 | 2014-09-28 | 100% | 7109.04 | 7109.04 | 11079.86 | Non Functional | 64.16% | 457 | 119 | 2015-09-01
201405 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201405 | 050.36611 | PRP.2735.MUN.E UNION ST 2014 | 2013-10-04 | 2014-09-30 | 100% | 141792.06 | 141792.06 | 150044.31 | Non Functional | 94.5% | 697 | 361 | 2015-09-01
201405 | 050.36614 | 2738.LAND. NEW OFFICE 2014 | 2014-03-01 | 2014-03-31 | 100% | 110000 | 110000 | 100071.29 | Non Functional | 109.9% | 549 | 30 | 2015-09-01
201405 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201405 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201405 | 050.36655 | PRP.2735.MUN.MILL ST 2014 | 2014-01-01 | 2015-01-01 | 100% | 180214.35 | 180214.35 | 129421.42 | Non Functional | 139.2% | 608 | 365 | 2015-09-01
201405 | 050.36696 | 050.2634.Robards TB Station | 2014-02-01 | 2014-10-28 | 100% | 146685.57 | 146685.57 | 157690.6 | Non Functional | 93.02% | 577 | 269 | 2015-09-01
201405 | 050.36708 | PRP.2737.N MAIN.PRICE 2014 | 2014-03-01 | 2015-03-01 | 100% | 374542.02 | 374542.02 | 492199.27 | Non Functional | 76.1% | 549 | 365 | 2015-09-01
201405 | 050.36740 | 050.2637.Chappell Rd Rev Ext | 2014-03-24 | 2014-09-28 | 100% | 2006.5 | 2006.5 | 4028.36 | Non Functional | 49.81% | 526 | 188 | 2015-09-01
201405 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201405 | 050.36790 | 050.2636.Hwy 951 Phase 2 | 2014-04-25 | 2014-09-28 | 100% | 10923.28 | 10923.28 | 6933.08 | Non Functional | 157.6% | 494 | 156 | 2015-09-01
201405 | 050.36799 | 2737.DAN.ERX INSTALLATION | 2013-10-01 | 2014-09-30 | 100% | 29827.38 | 29827.38 | 16759.91 | Non Functional | 178% | 700 | 364 | 2015-09-01
201405 | 050.36801 | 2738.GRNBURG.CAMP-RECTIFIER | 2013-10-01 | 2014-09-30 | 100% | 47902.59 | 47902.59 | 15083.1 | Non Functional | 317.6% | 700 | 364 | 2015-09-01
201405 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201405 | 050.36878 | PRP.2734.BG-Normal to Regents | 2013-10-23 | 2014-09-30 | 100% | 280654.79 | 280654.79 | 198269.87 | Non Functional | 141.6% | 678 | 342 | 2015-09-01
201405 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201405 | 050.36902 | 050.2734.Hwy31W Public Imprv | 2014-02-17 | 2014-09-28 | 100% | 246623.13 | 246623.13 | -2297.86 | Non Functional | -10733% | 561 | 223 | 2015-09-01
201405 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201405 | 050.37007 | 050.2634.College Dr. Reloc. | 2014-05-01 | 2014-09-28 | 100% | 23277.86 | 23277.86 | -5957.89 | Non Functional | -390.7% | 488 | 150 | 2015-09-01
201405 | 050.37025 | 050.2636.Hill Bridge | 2014-05-01 | 2014-09-28 | 100% | 7807.26 | 7807.26 | 7092.91 | Non Functional | 110.1% | 488 | 150 | 2015-09-01
201405 | 050.37031 | 050.2636.Sterling Park 2 | 2014-04-01 | 2014-09-28 | 100% | 12497.42 | 12497.42 | 11629.92 | Non Functional | 107.5% | 518 | 180 | 2015-09-01
201405 | 050.37040 | 050.2734.Massey Springs III | 2014-03-31 | 2014-09-28 | 100% | 5269.9 | 5269.9 | 3957.59 | Non Functional | 133.2% | 519 | 181 | 2015-09-01
201405 | 050.37054 | 050.2734.2 inchExt.Cableas | 2014-04-01 | 2014-09-28 | 100% | 8137.88 | 8137.88 | 5041.95 | Non Functional | 161.4% | 518 | 180 | 2015-09-01
201405 | 050.37067 | 050.2636.Thompson Dr. | 2014-06-20 | 2014-09-28 | 100% | 5171.35 | 5171.35 | 5999.26 | Non Functional | 86.2% | 438 | 100 | 2015-09-01
201405 | 050.37077 | 050.2734.ThreeSprings II.Hwy | 2014-03-31 | 2014-09-28 | 100% | 730962.37 | 730962.37 | 101956.53 | Non Functional | 716.9% | 519 | 181 | 2015-09-01
201405 | 050.37105 | 2738. WEST MARTIN 2014 | 2014-03-01 | 2015-03-01 | 100% | 4953.9 | 4953.9 | 2833.03 | Non Functional | 174.9% | 549 | 365 | 2015-09-01
201405 | 050.37119 | 2739.THOROUGHBRED 2014 | 2013-11-01 | 2014-11-01 | 100% | 2901.52 | 2901.52 | 2963.36 | Non Functional | 97.91% | 669 | 365 | 2015-09-01
201405 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201405 | 050.37169 | 2739.BOONE STAT 6 PE-SYS IMPR | 2014-05-01 | 2015-05-01 | 100% | 53220.11 | 53220.11 | 54715.65 | Non Functional | 97.27% | 488 | 365 | 2015-09-01
201405 | 050.37185 | PRP.2635.Dawson Road Repl | 2014-04-15 | 2014-06-01 | 100% | 3095.75 | 3095.75 | 3322.12 | Non Functional | 93.19% | 504 | 47 | 2015-09-01
201405 | 050.37232 | 2738.NOE RD. SYS IMP 2014 | 2014-04-15 | 2015-04-15 | 100% | 6665.6 | 6665.6 | 4088.41 | Non Functional | 163% | 504 | 365 | 2015-09-01
201405 | 050.37233 | 2738.SALOMA RD 2014 | 2014-04-15 | 2015-04-15 | 100% | 8584.68 | 8584.68 | 1497.18 | Non Functional | 573.4% | 504 | 365 | 2015-09-01
201405 | 050.37250 | 050.2636.Bridgewood | 2014-06-01 | 2014-08-01 | 100% | 9815.13 | 9815.13 | 11316.37 | Non Functional | 86.73% | 457 | 61 | 2015-09-01
201405 | 050.37255 | 2738.COMMONWEALTH -NEW OFFICE | 2014-04-21 | 2015-04-21 | 100% | 14822.55 | 14822.55 | 3747.03 | Non Functional | 395.6% | 498 | 365 | 2015-09-01
201405 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201405 | 050.37296 | 050.2734.Sunnitt Phase IV | 2014-03-24 | 2014-09-28 | 100% | 23165.19 | 23165.19 | 17510.41 | Non Functional | 132.3% | 526 | 188 | 2015-09-01
201405 | 050.37301 | 2739.SVILLE.8th - COLLEGE LP | 2012-02-01 | 2014-09-30 | 100% | 38918.57 | 38918.57 | 34704.87 | Non Functional | 112.1% | 1308 | 972 | 2015-09-01
201405 | 050.37346 | 2739.FRIESIAN CT 2014 | 2014-04-10 | 2015-04-10 | 100% | 2894.23 | 6568.17 | 7404.78 | Non Functional | 88.7% | 509 | 365 | 2015-09-01
201405 | 050.37351 | 050.2634.Slaughters upgrade | 2014-07-20 | 2014-09-28 | 100% | 62262.85 | 62262.85 | 63661.47 | Non Functional | 97.8% | 408 | 70 | 2015-09-01
201405 | 050.37445 | PRP.2635.Franklin Alley | 2014-06-01 | 2014-07-01 | 100% | 1081.18 | 1081.18 | 5514.06 | Non Functional | 19.61% | 457 | 30 | 2015-09-01
201405 | 050.37538 | PRP.2635.1st Street Replace | 2014-05-20 | 2014-06-30 | 100% | 2666.95 | 2666.95 | 534.3 | Non Functional | 499.1% | 469 | 41 | 2015-09-01
201405 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201406 | 050.30574 | PRP.2735.Duke-2nd-Cave City | 2012-04-30 | 2012-09-28 | 100% | 3692.22 | 3692.22 | 789.09 | Non Functional | 467.9% | 1219 | 151 | 2015-09-01
201406 | 050.30863 | 050.2734.northridge VI | 2012-06-04 | 2012-09-28 | 100% | 10147.78 | 10147.78 | 4946.8 | Non Functional | 205.1% | 1184 | 116 | 2015-09-01
201406 | 050.32960 | 050.2734.Hwy31W Reloc - Frk | 2012-11-26 | 2015-09-30 | 97.21% | 225067.56 | 225067.56 | 157598.65 | Non Functional | 142.8% | 1009 | 1038 | 2015-09-01
201406 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201406 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201406 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201406 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201406 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201406 | 050.33087 | PRP.2734.EAST 2ND ST | 2013-05-11 | 2013-05-11 | 100% | 58081.4 | 58081.4 | 44266.05 | Non Functional | 131.2% | 843 | 0 | 2015-09-01
201406 | 050.33144 | PRP Horse Cave SE 2013 | 2013-01-19 | 2015-09-30 | 97.05% | 519599.52 | 519599.52 | 623152.51 | Non Functional | 83.38% | 955 | 984 | 2015-09-01
201406 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201406 | 050.33425 | PRP.2636.Glendale Dr. | 2013-02-05 | 2013-09-28 | 100% | 7245.23 | 7245.23 | 6877.64 | Non Functional | 105.3% | 938 | 235 | 2015-09-01
201406 | 050.34128 | 2737.JC.MILL ST.RECTIF REPLAC | 2013-05-01 | 2015-05-01 | 100% | 19511.4 | 19511.4 | 12144.97 | Non Functional | 160.7% | 853 | 730 | 2015-09-01
201406 | 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | 2013-03-01 | 2015-03-01 | 100% | 37316.65 | 37316.65 | 53605.8 | Non Functional | 69.61% | 914 | 730 | 2015-09-01
201406 | 050.34184 | 050.2634.Basket Boiler | 2013-06-01 | 2013-09-28 | 100% | 58782.52 | 58782.52 | 61678.16 | Non Functional | 95.31% | 822 | 119 | 2015-09-01
201406 | 050.34295 | 050.2634.Basket TBS Relo. | 2013-06-01 | 2013-09-28 | 100% | 28790.67 | 28790.67 | 11781.77 | Non Functional | 244.4% | 822 | 119 | 2015-09-01
201406 | 050.34324 | 2737.HAR.PURCH ODOR REPLACE | 2012-10-01 | 2014-09-30 | 100% | 66681.61 | 66681.61 | 59176.21 | Non Functional | 112.7% | 1065 | 729 | 2015-09-01
201406 | 050.34460 | 050.2636.Lafayette St. | 2013-03-15 | 2013-09-28 | 100% | 12046.61 | 12046.61 | 16943.88 | Non Functional | 71.1% | 900 | 197 | 2015-09-01
201406 | 050.34824 | 2737.STAN.HUBBLE RD HP RELO | 2013-07-29 | 2014-09-02 | 100% | 29706.05 | 29706.05 | 1272.25 | Non Functional | 2335% | 764 | 400 | 2015-09-01
201406 | 050.34844 | PRP.Nashville Rd. Bare Replc | 2013-08-01 | 2013-12-31 | 100% | 12252.7 | 12252.7 | 5568.23 | Non Functional | 220% | 761 | 152 | 2015-09-01
201406 | 050.34845 | PRP.2734.Barren River & Wdfrd | 2013-08-01 | 2013-12-31 | 100% | 123893.13 | 123893.13 | 137769.76 | Non Functional | 89.93% | 761 | 152 | 2015-09-01
201406 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201406 | 050.35002 | 050.2637.13th St Replace | 2013-08-28 | 2013-09-28 | 100% | 3844.33 | 3844.33 | 5144.71 | Non Functional | 74.72% | 734 | 31 | 2015-09-01
201406 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201406 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201406 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201406 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201406 | 050.35635 | 2739.OLD MILL SEC 3 2014 | 2013-07-01 | 2014-09-30 | 100% | 10143.73 | 10143.73 | 18477.12 | Non Functional | 54.9% | 792 | 456 | 2015-09-01
201406 | 050.35649 | 2737.DANVILLE EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 42294 | 42294 | 33843.42 | Non Functional | 125% | 700 | 364 | 2015-09-01
201406 | 050.35650 | 2735.GLASGOW EQUIPMENT 2014 | 2013-10-01 | 2014-09-30 | 100% | 39615.31 | 39615.31 | 34454.32 | Non Functional | 115% | 700 | 364 | 2015-09-01
201406 | 050.35652 | 2739.S-VILLE EQUIPMENT 2014 | 2013-10-01 | 2014-11-30 | 100% | 35103.92 | 35103.92 | 39330.85 | Non Functional | 89.25% | 700 | 425 | 2015-09-01
201406 | 050.35669 | 050.2602.KMD North PCs | 2013-10-21 | 2014-09-28 | 100% | 130505.38 | 130505.38 | 130764.19 | Non Functional | 99.8% | 680 | 342 | 2015-09-01
201406 | 050.35675 | PRP.2738.Grn.Henry St | 2013-10-01 | 2014-10-01 | 100% | 376921.09 | 376921.09 | 145668.38 | Non Functional | 258.8% | 700 | 365 | 2015-09-01
201406 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201406 | 050.35692 | PRP.2636.E 6TH TRIP REPL | 2013-10-01 | 2014-09-28 | 100% | 417982.34 | 417982.34 | 456648.34 | Non Functional | 91.53% | 700 | 362 | 2015-09-01
201406 | 050.35695 | PRP.2737.Har.Cane Run 2014 | 2013-10-02 | 2014-09-30 | 100% | 477460.6 | 477460.6 | 691586.7 | Non Functional | 69.04% | 699 | 363 | 2015-09-01
201406 | 050.35739 | 050.2609.Wells St. Charles | 2013-11-01 | 2014-09-30 | 100% | 1317457.69 | 1317457.69 | 1165282.64 | Non Functional | 113.1% | 669 | 333 | 2015-09-01
201406 | 050.35762 | WMR for downtown and mall area | 2013-10-01 | 2014-09-30 | 100% | 32030.6 | 32030.6 | 21434.67 | Non Functional | 149.4% | 700 | 364 | 2015-09-01
201406 | 050.35780 | 050.2636.TRIP ST SYS IMP REPL | 2013-10-01 | 2014-09-28 | 100% | 451231.73 | 451231.73 | 410376.78 | Non Functional | 110% | 700 | 362 | 2015-09-01
201406 | 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | 2013-09-30 | 2014-10-01 | 100% | 420919.56 | 420919.56 | 192841.68 | Non Functional | 218.3% | 701 | 366 | 2015-09-01
201406 | 050.35856 | ERX's for use in Graves County | 2013-10-01 | 2014-09-30 | 100% | 18293.88 | 18293.88 | 18364.45 | Non Functional | 99.62% | 700 | 364 | 2015-09-01
201406 | 050.35858 | PRP.2734.BG-11TH & ELM ST | 2013-10-01 | 2014-09-30 | 100% | 85039.34 | 85039.34 | 453860.48 | Non Functional | 18.74% | 700 | 364 | 2015-09-01
201406 | 050.35859 | PRP.2734.OLD LVILLE RD TO RED | 2013-10-01 | 2014-09-30 | 100% | 114299.19 | 114299.19 | 337852.15 | Non Functional | 33.83% | 700 | 364 | 2015-09-01
201406 | 050.35899 | PRP.2634.S. Seminary St. | 2013-11-01 | 2014-09-28 | 100% | 75764.99 | 137126.81 | 149841.51 | Non Functional | 91.51% | 669 | 331 | 2015-09-01
201406 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201406 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201406 | 050.36109 | ECAT Replacement KY | 2013-12-09 | 2014-04-01 | 100% | 53041.48 | 53041.48 | 51711.08 | Non Functional | 102.6% | 631 | 113 | 2015-09-01
201406 | 050.36113 | Electronic Correctors KY | 2013-12-09 | 2014-10-01 | 100% | 34518.05 | 34518.05 | 17984.32 | Non Functional | 191.9% | 631 | 296 | 2015-09-01
201406 | 050.36117 | Emergency Regulators KY | 2013-12-09 | 2014-09-01 | 100% | 31904.24 | 31904.24 | 1778.7 | Non Functional | 1794% | 631 | 266 | 2015-09-01
201406 | 050.36119 | Habit Purchase Heater KY | 2013-12-09 | 2014-10-01 | 100% | 141587.83 | 141587.83 | 176580.15 | Non Functional | 80.18% | 631 | 296 | 2015-09-01
201406 | 050.36120 | Large Com/Indus Meter KY | 2013-12-09 | 2014-02-01 | 100% | 22930.23 | 22930.23 | 1909.16 | Non Functional | 1201% | 631 | 54 | 2015-09-01
201406 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201406 | 050.36132 | PRP.2734.B.G.-Auburn 2014 | 2013-10-14 | 2014-09-30 | 100% | 450096.88 | 450096.88 | 318619.41 | Non Functional | 141.3% | 687 | 351 | 2015-09-01
201406 | 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | 2013-10-02 | 2014-09-30 | 100% | 357169.26 | 357169.26 | 435365.71 | Non Functional | 82.04% | 699 | 363 | 2015-09-01
201406 | 050.36207 | 050.2602.GPS Modems | 2013-12-22 | 2014-09-28 | 100% | 95952 | 95952 | 82165.27 | Non Functional | 116.8% | 618 | 280 | 2015-09-01
201406 | 050.36212 | 050.2734.Equipment FY2014 | 2013-12-26 | 2014-09-30 | 100% | 72368.94 | 72368.94 | 66336.82 | Non Functional | 109.1% | 614 | 278 | 2015-09-01
201406 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201406 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201406 | 050.36301 | 050.2634.Tyson Boiler | 2014-01-20 | 2014-09-28 | 100% | 116757.23 | 116757.23 | 96324.38 | Non Functional | 121.2% | 589 | 251 | 2015-09-01
201406 | 050.36302 | PRP.2737.HAR.GREENBR SUB 2014 | 2013-09-26 | 2014-10-01 | 100% | 770435.2 | 770435.2 | 372242.77 | Non Functional | 207% | 705 | 370 | 2015-09-01
201406 | 050.36303 | PRP.2738.GRN.W COL AVE 2014 | 2013-10-02 | 2014-09-30 | 100% | 311198.5 | 311198.5 | 237404.34 | Non Functional | 131.1% | 699 | 363 | 2015-09-01
201406 | 050.36306 | ERX project - Hopkinsville | 2013-10-01 | 2014-09-30 | 100% | 7544.83 | 7544.83 | 9034.64 | Non Functional | 83.51% | 700 | 364 | 2015-09-01
201406 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201406 | 050.36324 | 2014 Equipment - Mayfield | 2013-10-01 | 2014-09-28 | 100% | 77017.2 | 77017.2 | 79198.46 | Non Functional | 97.25% | 700 | 362 | 2015-09-01
201406 | 050.36378 | PRP.2737.E FACTORY-BARE JT | 2014-01-08 | 2015-01-08 | 100% | 131431.43 | 131431.43 | 277467.55 | Non Functional | 47.37% | 601 | 365 | 2015-09-01
201406 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201406 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201406 | 050.36475 | 2734.TRENCHER-WALK W/TRAILER | 2013-10-01 | 2014-09-30 | 100% | 21481.5 | 21481.5 | 22648.19 | Non Functional | 94.85% | 700 | 364 | 2015-09-01
201406 | 050.36511 | 050.2609.St Charles Building | 2014-02-01 | 2014-09-28 | 100% | 90000 | 90000 | 85727.13 | Non Functional | 105% | 577 | 239 | 2015-09-01
201406 | 050.36519 | 050.2734.North-South2inchRep | 2013-12-03 | 2014-09-28 | 100% | 3211.56 | 3211.56 | 788.51 | Non Functional | 407.3% | 637 | 299 | 2015-09-01
201406 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201406 | 050.36528 | 050.2609.St. Charles Furniture | 2014-06-01 | 2014-09-28 | 100% | 7109.04 | 7109.04 | 11079.86 | Non Functional | 64.16% | 457 | 119 | 2015-09-01
201406 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201406 | 050.36611 | PRP.2735.MUN.E UNION ST 2014 | 2013-10-04 | 2014-09-30 | 100% | 141792.06 | 141792.06 | 150044.31 | Non Functional | 94.5% | 697 | 361 | 2015-09-01
201406 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201406 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201406 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201406 | 050.36655 | PRP.2735.MUN.MILL ST 2014 | 2014-01-01 | 2015-01-01 | 100% | 180214.35 | 180214.35 | 129421.42 | Non Functional | 139.2% | 608 | 365 | 2015-09-01
201406 | 050.36696 | 050.2634.Robards TB Station | 2014-02-01 | 2014-10-28 | 100% | 146685.57 | 146685.57 | 157690.6 | Non Functional | 93.02% | 577 | 269 | 2015-09-01
201406 | 050.36708 | PRP.2737.N MAIN.PRICE 2014 | 2014-03-01 | 2015-03-01 | 100% | 374542.02 | 374542.02 | 492199.27 | Non Functional | 76.1% | 549 | 365 | 2015-09-01
201406 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201406 | 050.36799 | 2737.DAN.ERX INSTALLATION | 2013-10-01 | 2014-09-30 | 100% | 29827.38 | 29827.38 | 16759.91 | Non Functional | 178% | 700 | 364 | 2015-09-01
201406 | 050.36801 | 2738.GRNBURG.CAMP-RECTIFIER | 2013-10-01 | 2014-09-30 | 100% | 47902.59 | 47902.59 | 15083.1 | Non Functional | 317.6% | 700 | 364 | 2015-09-01
201406 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201406 | 050.36878 | PRP.2734.BG-Normal to Regents | 2013-10-23 | 2014-09-30 | 100% | 280654.79 | 280654.79 | 198269.87 | Non Functional | 141.6% | 678 | 342 | 2015-09-01
201406 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201406 | 050.36902 | 050.2734.Hwy31W Public Imprv | 2014-02-17 | 2014-09-28 | 100% | 246623.13 | 246623.13 | -2297.86 | Non Functional | -10733% | 561 | 223 | 2015-09-01
201406 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201406 | 050.37007 | 050.2634.College Dr. Reloc. | 2014-05-01 | 2014-09-28 | 100% | 23277.86 | 23277.86 | -5957.89 | Non Functional | -390.7% | 488 | 150 | 2015-09-01
201406 | 050.37025 | 050.2636.Hill Bridge | 2014-05-01 | 2014-09-28 | 100% | 7807.26 | 7807.26 | 7092.91 | Non Functional | 110.1% | 488 | 150 | 2015-09-01
201406 | 050.37031 | 050.2636.Sterling Park 2 | 2014-04-01 | 2014-09-28 | 100% | 12497.42 | 12497.42 | 11629.92 | Non Functional | 107.5% | 518 | 180 | 2015-09-01
201406 | 050.37040 | 050.2734.Massey Springs III | 2014-03-31 | 2014-09-28 | 100% | 5269.9 | 5269.9 | 3957.59 | Non Functional | 133.2% | 519 | 181 | 2015-09-01
201406 | 050.37054 | 050.2734.2 inchExt.Cableas | 2014-04-01 | 2014-09-28 | 100% | 8137.88 | 8137.88 | 5041.95 | Non Functional | 161.4% | 518 | 180 | 2015-09-01
201406 | 050.37077 | 050.2734.ThreeSprings II.Hwy | 2014-03-31 | 2014-09-28 | 100% | 730962.37 | 730962.37 | 101956.53 | Non Functional | 716.9% | 519 | 181 | 2015-09-01
201406 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201406 | 050.37169 | 2739.BOONE STAT 6 PE-SYS IMPR | 2014-05-01 | 2015-05-01 | 100% | 53220.11 | 53220.11 | 54715.65 | Non Functional | 97.27% | 488 | 365 | 2015-09-01
201406 | 050.37185 | PRP.2635.Dawson Road Repl | 2014-04-15 | 2014-06-01 | 100% | 3095.75 | 3095.75 | 3322.12 | Non Functional | 93.19% | 504 | 47 | 2015-09-01
201406 | 050.37250 | 050.2636.Bridgewood | 2014-06-01 | 2014-08-01 | 100% | 9815.13 | 9815.13 | 11316.37 | Non Functional | 86.73% | 457 | 61 | 2015-09-01
201406 | 050.37255 | 2738.COMMONWEALTH -NEW OFFICE | 2014-04-21 | 2015-04-21 | 100% | 14822.55 | 14822.55 | 3747.03 | Non Functional | 395.6% | 498 | 365 | 2015-09-01
201406 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201406 | 050.37296 | 050.2734.Sunnitt Phase IV | 2014-03-24 | 2014-09-28 | 100% | 23165.19 | 23165.19 | 17510.41 | Non Functional | 132.3% | 526 | 188 | 2015-09-01
201406 | 050.37301 | 2739.SVILLE.8th - COLLEGE LP | 2012-02-01 | 2014-09-30 | 100% | 38918.57 | 38918.57 | 34704.87 | Non Functional | 112.1% | 1308 | 972 | 2015-09-01
201406 | 050.37312 | TDW Equipment | 2014-04-28 | 2014-06-30 | 100% | 49484.06 | 49484.06 | 61380.46 | Non Functional | 80.62% | 491 | 63 | 2015-09-01
201406 | 050.37346 | 2739.FRIESIAN CT 2014 | 2014-04-10 | 2015-04-10 | 100% | 2894.23 | 6568.17 | 7404.78 | Non Functional | 88.7% | 509 | 365 | 2015-09-01
201406 | 050.37351 | 050.2634.Slaughters upgrade | 2014-07-20 | 2014-09-28 | 100% | 62262.85 | 62262.85 | 63661.47 | Non Functional | 97.8% | 408 | 70 | 2015-09-01
201406 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201406 | 050.37445 | PRP.2635.Franklin Alley | 2014-06-01 | 2014-07-01 | 100% | 1081.18 | 1081.18 | 5514.06 | Non Functional | 19.61% | 457 | 30 | 2015-09-01
201406 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201406 | 050.37538 | PRP.2635.1st Street Replace | 2014-05-20 | 2014-06-30 | 100% | 2666.95 | 2666.95 | 534.3 | Non Functional | 499.1% | 469 | 41 | 2015-09-01
201406 | 050.37614 | PRP.2636.Hwy 181 | 2014-05-20 | 2014-07-01 | 100% | 33963.34 | 33963.34 | 22627.52 | Non Functional | 150.1% | 469 | 42 | 2015-09-01
201406 | 050.37668 | PRP.2635.Brook St Replace | 2014-06-02 | 2014-07-30 | 100% | 5257.15 | 5257.15 | 10448.21 | Non Functional | 50.32% | 456 | 58 | 2015-09-01
201406 | 050.37682 | 050.2636.Elwood Ct. | 2014-06-20 | 2014-07-01 | 100% | 6527.3 | 6527.3 | 8078.32 | Non Functional | 80.8% | 438 | 11 | 2015-09-01
201406 | 050.37683 | 050.2636.Meridian Ct | 2014-06-20 | 2014-07-01 | 100% | 6527.3 | 6527.3 | 9413.42 | Non Functional | 69.34% | 438 | 11 | 2015-09-01
201406 | 050.37684 | 050.2636.Thorn Ridge Crossing | 2014-07-15 | 2014-08-25 | 100% | 4427.52 | 4427.52 | 2447.4 | Non Functional | 180.9% | 413 | 41 | 2015-09-01
201406 | 050.37704 | 050.2636.Whispering Meadows 4 | 2014-07-01 | 2014-09-28 | 100% | 16390.67 | 16390.67 | 14413.77 | Non Functional | 113.7% | 427 | 89 | 2015-09-01
201406 | 050.37719 | 050.2636.Spring Haven Trace | 2014-07-01 | 2014-08-20 | 100% | 1671.96 | 1671.96 | 1112.89 | Non Functional | 150.2% | 427 | 50 | 2015-09-01
201406 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201407 | 050.30574 | PRP.2735.Duke-2nd-Cave City | 2012-04-30 | 2012-09-28 | 100% | 3692.22 | 3692.22 | 789.09 | Non Functional | 467.9% | 1219 | 151 | 2015-09-01
201407 | 050.30863 | 050.2734.northridge VI | 2012-06-04 | 2012-09-28 | 100% | 10147.78 | 10147.78 | 4946.8 | Non Functional | 205.1% | 1184 | 116 | 2015-09-01
201407 | 050.32960 | 050.2734.Hwy31W Reloc - Frk | 2012-11-26 | 2015-09-30 | 97.21% | 225067.56 | 225067.56 | 157598.65 | Non Functional | 142.8% | 1009 | 1038 | 2015-09-01
201407 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201407 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201407 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201407 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201407 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201407 | 050.33087 | PRP.2734.EAST 2ND ST | 2013-05-11 | 2013-05-11 | 100% | 58081.4 | 58081.4 | 44266.05 | Non Functional | 131.2% | 843 | 0 | 2015-09-01
201407 | 050.33144 | PRP Horse Cave SE 2013 | 2013-01-19 | 2015-09-30 | 97.05% | 519599.52 | 519599.52 | 623152.51 | Non Functional | 83.38% | 955 | 984 | 2015-09-01
201407 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201407 | 050.33425 | PRP.2636.Glendale Dr. | 2013-02-05 | 2013-09-28 | 100% | 7245.23 | 7245.23 | 6877.64 | Non Functional | 105.3% | 938 | 235 | 2015-09-01
201407 | 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | 2013-03-01 | 2015-03-01 | 100% | 37316.65 | 37316.65 | 53605.8 | Non Functional | 69.61% | 914 | 730 | 2015-09-01
201407 | 050.34184 | 050.2634.Basket Boiler | 2013-06-01 | 2013-09-28 | 100% | 58782.52 | 58782.52 | 61678.16 | Non Functional | 95.31% | 822 | 119 | 2015-09-01
201407 | 050.34295 | 050.2634.Basket TBS Relo. | 2013-06-01 | 2013-09-28 | 100% | 28790.67 | 28790.67 | 11781.77 | Non Functional | 244.4% | 822 | 119 | 2015-09-01
201407 | 050.34460 | 050.2636.Lafayette St. | 2013-03-15 | 2013-09-28 | 100% | 12046.61 | 12046.61 | 16943.88 | Non Functional | 71.1% | 900 | 197 | 2015-09-01
201407 | 050.34824 | 2737.STAN.HUBBLE RD HP RELO | 2013-07-29 | 2014-09-02 | 100% | 29706.05 | 29706.05 | 1272.25 | Non Functional | 2335% | 764 | 400 | 2015-09-01
201407 | 050.34844 | PRP.Nashville Rd. Bare Replc | 2013-08-01 | 2013-12-31 | 100% | 12252.7 | 12252.7 | 5568.23 | Non Functional | 220% | 761 | 152 | 2015-09-01
201407 | 050.34845 | PRP.2734.Barren River & Wdfrd | 2013-08-01 | 2013-12-31 | 100% | 123893.13 | 123893.13 | 137769.76 | Non Functional | 89.93% | 761 | 152 | 2015-09-01
201407 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201407 | 050.35002 | 050.2637.13th St Replace | 2013-08-28 | 2013-09-28 | 100% | 3844.33 | 3844.33 | 5144.71 | Non Functional | 74.72% | 734 | 31 | 2015-09-01
201407 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201407 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201407 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201407 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201407 | 050.35635 | 2739.OLD MILL SEC 3 2014 | 2013-07-01 | 2014-09-30 | 100% | 10143.73 | 10143.73 | 18477.12 | Non Functional | 54.9% | 792 | 456 | 2015-09-01
201407 | 050.35669 | 050.2602.KMD North PCs | 2013-10-21 | 2014-09-28 | 100% | 130505.38 | 130505.38 | 130764.19 | Non Functional | 99.8% | 680 | 342 | 2015-09-01
201407 | 050.35675 | PRP.2738.Grn.Henry St | 2013-10-01 | 2014-10-01 | 100% | 376921.09 | 376921.09 | 145668.38 | Non Functional | 258.8% | 700 | 365 | 2015-09-01
201407 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201407 | 050.35695 | PRP.2737.Har.Cane Run 2014 | 2013-10-02 | 2014-09-30 | 100% | 477460.6 | 477460.6 | 691586.7 | Non Functional | 69.04% | 699 | 363 | 2015-09-01
201407 | 050.35739 | 050.2609.Wells St. Charles | 2013-11-01 | 2014-09-30 | 100% | 1317457.69 | 1317457.69 | 1165282.64 | Non Functional | 113.1% | 669 | 333 | 2015-09-01
201407 | 050.35762 | WMR for downtown and mall area | 2013-10-01 | 2014-09-30 | 100% | 32030.6 | 32030.6 | 21434.67 | Non Functional | 149.4% | 700 | 364 | 2015-09-01
201407 | 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | 2013-09-30 | 2014-10-01 | 100% | 420919.56 | 420919.56 | 192841.68 | Non Functional | 218.3% | 701 | 366 | 2015-09-01
201407 | 050.35856 | ERX's for use in Graves County | 2013-10-01 | 2014-09-30 | 100% | 18293.88 | 18293.88 | 18364.45 | Non Functional | 99.62% | 700 | 364 | 2015-09-01
201407 | 050.35858 | PRP.2734.BG-11TH & ELM ST | 2013-10-01 | 2014-09-30 | 100% | 85039.34 | 85039.34 | 453860.48 | Non Functional | 18.74% | 700 | 364 | 2015-09-01
201407 | 050.35859 | PRP.2734.OLD LVILLE RD TO RED | 2013-10-01 | 2014-09-30 | 100% | 114299.19 | 114299.19 | 337852.15 | Non Functional | 33.83% | 700 | 364 | 2015-09-01
201407 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201407 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201407 | 050.36109 | ECAT Replacement KY | 2013-12-09 | 2014-04-01 | 100% | 53041.48 | 53041.48 | 51711.08 | Non Functional | 102.6% | 631 | 113 | 2015-09-01
201407 | 050.36113 | Electronic Correctors KY | 2013-12-09 | 2014-10-01 | 100% | 34518.05 | 34518.05 | 17984.32 | Non Functional | 191.9% | 631 | 296 | 2015-09-01
201407 | 050.36117 | Emergency Regulators KY | 2013-12-09 | 2014-09-01 | 100% | 31904.24 | 31904.24 | 1778.7 | Non Functional | 1794% | 631 | 266 | 2015-09-01
201407 | 050.36119 | Habit Purchase Heater KY | 2013-12-09 | 2014-10-01 | 100% | 141587.83 | 141587.83 | 176580.15 | Non Functional | 80.18% | 631 | 296 | 2015-09-01
201407 | 050.36120 | Large Com/Indus Meter KY | 2013-12-09 | 2014-02-01 | 100% | 22930.23 | 22930.23 | 1909.16 | Non Functional | 1201% | 631 | 54 | 2015-09-01
201407 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201407 | 050.36132 | PRP.2734.B.G.-Auburn 2014 | 2013-10-14 | 2014-09-30 | 100% | 450096.88 | 450096.88 | 318619.41 | Non Functional | 141.3% | 687 | 351 | 2015-09-01
201407 | 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | 2013-10-02 | 2014-09-30 | 100% | 357169.26 | 357169.26 | 435365.71 | Non Functional | 82.04% | 699 | 363 | 2015-09-01
201407 | 050.36207 | 050.2602.GPS Modems | 2013-12-22 | 2014-09-28 | 100% | 95952 | 95952 | 82165.27 | Non Functional | 116.8% | 618 | 280 | 2015-09-01
201407 | 050.36212 | 050.2734.Equipment FY2014 | 2013-12-26 | 2014-09-30 | 100% | 72368.94 | 72368.94 | 66336.82 | Non Functional | 109.1% | 614 | 278 | 2015-09-01
201407 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201407 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201407 | 050.36301 | 050.2634.Tyson Boiler | 2014-01-20 | 2014-09-28 | 100% | 116757.23 | 116757.23 | 96324.38 | Non Functional | 121.2% | 589 | 251 | 2015-09-01
201407 | 050.36302 | PRP.2737.HAR.GREENBR SUB 2014 | 2013-09-26 | 2014-10-01 | 100% | 770435.2 | 770435.2 | 372242.77 | Non Functional | 207% | 705 | 370 | 2015-09-01
201407 | 050.36303 | PRP.2738.GRN.W COL AVE 2014 | 2013-10-02 | 2014-09-30 | 100% | 311198.5 | 311198.5 | 237404.34 | Non Functional | 131.1% | 699 | 363 | 2015-09-01
201407 | 050.36306 | ERX project - Hopkinsville | 2013-10-01 | 2014-09-30 | 100% | 7544.83 | 7544.83 | 9034.64 | Non Functional | 83.51% | 700 | 364 | 2015-09-01
201407 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201407 | 050.36324 | 2014 Equipment - Mayfield | 2013-10-01 | 2014-09-28 | 100% | 77017.2 | 77017.2 | 79198.46 | Non Functional | 97.25% | 700 | 362 | 2015-09-01
201407 | 050.36378 | PRP.2737.E FACTORY-BARE JT | 2014-01-08 | 2015-01-08 | 100% | 131431.43 | 131431.43 | 277467.55 | Non Functional | 47.37% | 601 | 365 | 2015-09-01
201407 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201407 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201407 | 050.36475 | 2734.TRENCHER-WALK W/TRAILER | 2013-10-01 | 2014-09-30 | 100% | 21481.5 | 21481.5 | 22648.19 | Non Functional | 94.85% | 700 | 364 | 2015-09-01
201407 | 050.36478 | 2734.BG.FRAN.MADISON REG REP | 2013-10-01 | 2014-09-30 | 100% | 14298.69 | 14298.69 | 10279.06 | Non Functional | 139.1% | 700 | 364 | 2015-09-01
201407 | 050.36519 | 050.2734.North-South2inchRep | 2013-12-03 | 2014-09-28 | 100% | 3211.56 | 3211.56 | 788.51 | Non Functional | 407.3% | 637 | 299 | 2015-09-01
201407 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201407 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201407 | 050.36611 | PRP.2735.MUN.E UNION ST 2014 | 2013-10-04 | 2014-09-30 | 100% | 141792.06 | 141792.06 | 150044.31 | Non Functional | 94.5% | 697 | 361 | 2015-09-01
201407 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201407 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201407 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201407 | 050.36655 | PRP.2735.MUN.MILL ST 2014 | 2014-01-01 | 2015-01-01 | 100% | 180214.35 | 180214.35 | 129421.42 | Non Functional | 139.2% | 608 | 365 | 2015-09-01
201407 | 050.36696 | 050.2634.Robards TB Station | 2014-02-01 | 2014-10-28 | 100% | 146685.57 | 146685.57 | 157690.6 | Non Functional | 93.02% | 577 | 269 | 2015-09-01
201407 | 050.36708 | PRP.2737.N MAIN.PRICE 2014 | 2014-03-01 | 2015-03-01 | 100% | 374542.02 | 374542.02 | 492199.27 | Non Functional | 76.1% | 549 | 365 | 2015-09-01
201407 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201407 | 050.36799 | 2737.DAN.ERX INSTALLATION | 2013-10-01 | 2014-09-30 | 100% | 29827.38 | 29827.38 | 16759.91 | Non Functional | 178% | 700 | 364 | 2015-09-01
201407 | 050.36801 | 2738.GRNBURG.CAMP-RECTIFIER | 2013-10-01 | 2014-09-30 | 100% | 47902.59 | 47902.59 | 15083.1 | Non Functional | 317.6% | 700 | 364 | 2015-09-01
201407 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201407 | 050.36878 | PRP.2734.BG-Normal to Regents | 2013-10-23 | 2014-09-30 | 100% | 280654.79 | 280654.79 | 198269.87 | Non Functional | 141.6% | 678 | 342 | 2015-09-01
201407 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201407 | 050.36902 | 050.2734.Hwy31W Public Imprv | 2014-02-17 | 2014-09-28 | 100% | 246623.13 | 246623.13 | -2297.86 | Non Functional | -10733% | 561 | 223 | 2015-09-01
201407 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201407 | 050.37007 | 050.2634.College Dr. Reloc. | 2014-05-01 | 2014-09-28 | 100% | 23277.86 | 23277.86 | -5957.89 | Non Functional | -390.7% | 488 | 150 | 2015-09-01
201407 | 050.37040 | 050.2734.Massey Springs III | 2014-03-31 | 2014-09-28 | 100% | 5269.9 | 5269.9 | 3957.59 | Non Functional | 133.2% | 519 | 181 | 2015-09-01
201407 | 050.37054 | 050.2734.2 inchExt.Cableas | 2014-04-01 | 2014-09-28 | 100% | 8137.88 | 8137.88 | 5041.95 | Non Functional | 161.4% | 518 | 180 | 2015-09-01
201407 | 050.37077 | 050.2734.ThreeSprings II.Hwy | 2014-03-31 | 2014-09-28 | 100% | 730962.37 | 730962.37 | 101956.53 | Non Functional | 716.9% | 519 | 181 | 2015-09-01
201407 | 050.37154 | Install Infrared red heater | 2014-06-01 | 2014-08-01 | 100% | 51622.76 | 51622.76 | 37731.96 | Non Functional | 136.8% | 457 | 61 | 2015-09-01
201407 | 050.37169 | 2739.BOONE STAT 6 PE-SYS IMPR | 2014-05-01 | 2015-05-01 | 100% | 53220.11 | 53220.11 | 54715.65 | Non Functional | 97.27% | 488 | 365 | 2015-09-01
201407 | 050.37185 | PRP.2635.Dawson Road Repl | 2014-04-15 | 2014-06-01 | 100% | 3095.75 | 3095.75 | 3322.12 | Non Functional | 93.19% | 504 | 47 | 2015-09-01
201407 | 050.37255 | 2738.COMMONWEALTH -NEW OFFICE | 2014-04-21 | 2015-04-21 | 100% | 14822.55 | 14822.55 | 3747.03 | Non Functional | 395.6% | 498 | 365 | 2015-09-01
201407 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201407 | 050.37296 | 050.2734.Sunnitt Phase IV | 2014-03-24 | 2014-09-28 | 100% | 23165.19 | 23165.19 | 17510.41 | Non Functional | 132.3% | 526 | 188 | 2015-09-01
201407 | 050.37301 | 2739.SVILLE.8th - COLLEGE LP | 2012-02-01 | 2014-09-30 | 100% | 38918.57 | 38918.57 | 34704.87 | Non Functional | 112.1% | 1308 | 972 | 2015-09-01
201407 | 050.37312 | TDW Equipment | 2014-04-28 | 2014-06-30 | 100% | 49484.06 | 49484.06 | 61380.46 | Non Functional | 80.62% | 491 | 63 | 2015-09-01
201407 | 050.37346 | 2739.FRIESIAN CT 2014 | 2014-04-10 | 2015-04-10 | 100% | 2894.23 | 6568.17 | 7404.78 | Non Functional | 88.7% | 509 | 365 | 2015-09-01
201407 | 050.37351 | 050.2634.Slaughters upgrade | 2014-07-20 | 2014-09-28 | 100% | 62262.85 | 62262.85 | 63661.47 | Non Functional | 97.8% | 408 | 70 | 2015-09-01
201407 | 050.37407 | 050.2734.CalBastel 2 inch Ext | 2014-05-08 | 2014-09-28 | 100% | 2130.18 | 2130.18 | 1634.83 | Non Functional | 130.3% | 481 | 143 | 2015-09-01
201407 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201407 | 050.37425 | Ground Bed 45 S | 2014-06-03 | 2015-09-30 | 94.01% | 11584.56 | 11584.56 | 8666.4 | Non Functional | 133.7% | 455 | 484 | 2015-09-01
201407 | 050.37445 | PRP.2635.Franklin Alley | 2014-06-01 | 2014-07-01 | 100% | 1081.18 | 1081.18 | 5514.06 | Non Functional | 19.61% | 457 | 30 | 2015-09-01
201407 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201407 | 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | 2013-10-03 | 2014-11-30 | 100% | 135880.55 | 135880.55 | 261192.99 | Non Functional | 52.02% | 698 | 423 | 2015-09-01
201407 | 050.37538 | PRP.2635.1st Street Replace | 2014-05-20 | 2014-06-30 | 100% | 2666.95 | 2666.95 | 534.3 | Non Functional | 499.1% | 469 | 41 | 2015-09-01
201407 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201407 | 050.37614 | PRP.2636.Hwy 181 | 2014-05-20 | 2014-07-01 | 100% | 33963.34 | 33963.34 | 22627.52 | Non Functional | 150.1% | 469 | 42 | 2015-09-01
201407 | 050.37668 | PRP.2635.Brook St Replace | 2014-06-02 | 2014-07-30 | 100% | 5257.15 | 5257.15 | 10448.21 | Non Functional | 50.32% | 456 | 58 | 2015-09-01
201407 | 050.37682 | 050.2636.Elwood Ct. | 2014-06-20 | 2014-07-01 | 100% | 6527.3 | 6527.3 | 8078.32 | Non Functional | 80.8% | 438 | 11 | 2015-09-01
201407 | 050.37683 | 050.2636.Meridian Ct | 2014-06-20 | 2014-07-01 | 100% | 6527.3 | 6527.3 | 9413.42 | Non Functional | 69.34% | 438 | 11 | 2015-09-01
201407 | 050.37698 | 2739.LAW.EVERGREEN TBS 2014 | 2013-10-01 | 2014-09-30 | 100% | 38690.79 | 38690.79 | 30753.25 | Non Functional | 125.8% | 700 | 364 | 2015-09-01
201407 | 050.37743 | 050.2734.Henderson Ind.Park | 2014-07-31 | 2014-09-28 | 100% | 69842.85 | 69842.85 | 16580.26 | Non Functional | 421.2% | 397 | 59 | 2015-09-01
201407 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201407 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201407 | 050.37863 | x | 2014-06-30 | 2014-09-28 | 100% | 40990.13 | 40990.13 | 64851.14 | Non Functional | 63.21% | 428 | 90 | 2015-09-01
201407 | 050.37890 | 050.2637.Eva Dr Main Ext | 2014-07-07 | 2014-07-31 | 100% | 733.55 | 733.55 | 1208.87 | Non Functional | 60.68% | 421 | 24 | 2015-09-01
201407 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201407 | 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | 2014-07-22 | 2014-12-31 | 100% | 47164.67 | 47164.67 | 39204.28 | Non Functional | 120.3% | 406 | 162 | 2015-09-01
201407 | 050.37959 | 050.2637.Hwy 95 Relocate | 2014-07-17 | 2014-08-30 | 100% | 3042.73 | 3042.73 | 785.66 | Non Functional | 387.3% | 411 | 44 | 2015-09-01
201407 | 050.37965 | 050.2636.Greenville 6 Inch Re | 2014-07-10 | 2014-11-28 | 100% | 123381.36 | 123381.36 | 119846.93 | Non Functional | 102.9% | 418 | 141 | 2015-09-01
201407 | 050.37999 | 050.2734.BelleHaven III | 2014-07-14 | 2014-09-28 | 100% | 7925.37 | 7925.37 | 4168.1 | Non Functional | 190.1% | 414 | 76 | 2015-09-01
201407 | 050.38086 | 050.2734.Northridge VII | 2014-06-16 | 2014-09-28 | 100% | 12478.77 | 12478.77 | 6686.88 | Non Functional | 186.6% | 442 | 104 | 2015-09-01
201407 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201407 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201408 | 050.30574 | PRP.2735.Duke-2nd-Cave City | 2012-04-30 | 2012-09-28 | 100% | 3692.22 | 3692.22 | 789.09 | Non Functional | 467.9% | 1219 | 151 | 2015-09-01
201408 | 050.30863 | 050.2734.northridge VI | 2012-06-04 | 2012-09-28 | 100% | 10147.78 | 10147.78 | 4946.8 | Non Functional | 205.1% | 1184 | 116 | 2015-09-01
201408 | 050.32960 | 050.2734.Hwy31W Reloc - Frk | 2012-11-26 | 2015-09-30 | 97.21% | 225067.56 | 225067.56 | 157598.65 | Non Functional | 142.8% | 1009 | 1038 | 2015-09-01
201408 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201408 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201408 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201408 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201408 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201408 | 050.33087 | PRP.2734.EAST 2ND ST | 2013-05-11 | 2013-05-11 | 100% | 58081.4 | 58081.4 | 44266.05 | Non Functional | 131.2% | 843 | 0 | 2015-09-01
201408 | 050.33144 | PRP Horse Cave SE 2013 | 2013-01-19 | 2015-09-30 | 97.05% | 519599.52 | 519599.52 | 623152.51 | Non Functional | 83.38% | 955 | 984 | 2015-09-01
201408 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201408 | 050.33425 | PRP.2636.Glendale Dr. | 2013-02-05 | 2013-09-28 | 100% | 7245.23 | 7245.23 | 6877.64 | Non Functional | 105.3% | 938 | 235 | 2015-09-01
201408 | 050.34162 | 2737.STAN.HUBBLE STAT REPLACE | 2013-03-01 | 2015-03-01 | 100% | 37316.65 | 37316.65 | 53605.8 | Non Functional | 69.61% | 914 | 730 | 2015-09-01
201408 | 050.34460 | 050.2636.Lafayette St. | 2013-03-15 | 2013-09-28 | 100% | 12046.61 | 12046.61 | 16943.88 | Non Functional | 71.1% | 900 | 197 | 2015-09-01
201408 | 050.34824 | 2737.STAN.HUBBLE RD HP RELO | 2013-07-29 | 2014-09-02 | 100% | 29706.05 | 29706.05 | 1272.25 | Non Functional | 2335% | 764 | 400 | 2015-09-01
201408 | 050.34844 | PRP.Nashville Rd. Bare Replc | 2013-08-01 | 2013-12-31 | 100% | 12252.7 | 12252.7 | 5568.23 | Non Functional | 220% | 761 | 152 | 2015-09-01
201408 | 050.34845 | PRP.2734.Barren River & Wdfrd | 2013-08-01 | 2013-12-31 | 100% | 123893.13 | 123893.13 | 137769.76 | Non Functional | 89.93% | 761 | 152 | 2015-09-01
201408 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201408 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201408 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201408 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201408 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201408 | 050.35635 | 2739.OLD MILL SEC 3 2014 | 2013-07-01 | 2014-09-30 | 100% | 10143.73 | 10143.73 | 18477.12 | Non Functional | 54.9% | 792 | 456 | 2015-09-01
201408 | 050.35669 | 050.2602.KMD North PCs | 2013-10-21 | 2014-09-28 | 100% | 130505.38 | 130505.38 | 130764.19 | Non Functional | 99.8% | 680 | 342 | 2015-09-01
201408 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201408 | 050.35739 | 050.2609.Wells St. Charles | 2013-11-01 | 2014-09-30 | 100% | 1317457.69 | 1317457.69 | 1165282.64 | Non Functional | 113.1% | 669 | 333 | 2015-09-01
201408 | 050.35791 | PRP.2735.HC.CHERRY.MAPLE.BED | 2013-09-30 | 2014-10-01 | 100% | 420919.56 | 420919.56 | 192841.68 | Non Functional | 218.3% | 701 | 366 | 2015-09-01
201408 | 050.35858 | PRP.2734.BG-11TH & ELM ST | 2013-10-01 | 2014-09-30 | 100% | 85039.34 | 85039.34 | 453860.48 | Non Functional | 18.74% | 700 | 364 | 2015-09-01
201408 | 050.35859 | PRP.2734.OLD LVILLE RD TO RED | 2013-10-01 | 2014-09-30 | 100% | 114299.19 | 114299.19 | 337852.15 | Non Functional | 33.83% | 700 | 364 | 2015-09-01
201408 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201408 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201408 | 050.36109 | ECAT Replacement KY | 2013-12-09 | 2014-04-01 | 100% | 53041.48 | 53041.48 | 51711.08 | Non Functional | 102.6% | 631 | 113 | 2015-09-01
201408 | 050.36113 | Electronic Correctors KY | 2013-12-09 | 2014-10-01 | 100% | 34518.05 | 34518.05 | 17984.32 | Non Functional | 191.9% | 631 | 296 | 2015-09-01
201408 | 050.36117 | Emergency Regulators KY | 2013-12-09 | 2014-09-01 | 100% | 31904.24 | 31904.24 | 1778.7 | Non Functional | 1794% | 631 | 266 | 2015-09-01
201408 | 050.36119 | Habit Purchase Heater KY | 2013-12-09 | 2014-10-01 | 100% | 141587.83 | 141587.83 | 176580.15 | Non Functional | 80.18% | 631 | 296 | 2015-09-01
201408 | 050.36120 | Large Com/Indus Meter KY | 2013-12-09 | 2014-02-01 | 100% | 22930.23 | 22930.23 | 1909.16 | Non Functional | 1201% | 631 | 54 | 2015-09-01
201408 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201408 | 050.36132 | PRP.2734.B.G.-Auburn 2014 | 2013-10-14 | 2014-09-30 | 100% | 450096.88 | 450096.88 | 318619.41 | Non Functional | 141.3% | 687 | 351 | 2015-09-01
201408 | 050.36175 | PRP.2735.HC.GREEN-MAIN 2014 | 2013-10-02 | 2014-09-30 | 100% | 357169.26 | 357169.26 | 435365.71 | Non Functional | 82.04% | 699 | 363 | 2015-09-01
201408 | 050.36207 | 050.2602.GPS Modems | 2013-12-22 | 2014-09-28 | 100% | 95952 | 95952 | 82165.27 | Non Functional | 116.8% | 618 | 280 | 2015-09-01
201408 | 050.36212 | 050.2734.Equipment FY2014 | 2013-12-26 | 2014-09-30 | 100% | 72368.94 | 72368.94 | 66336.82 | Non Functional | 109.1% | 614 | 278 | 2015-09-01
201408 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201408 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201408 | 050.36301 | 050.2634.Tyson Boiler | 2014-01-20 | 2014-09-28 | 100% | 116757.23 | 116757.23 | 96324.38 | Non Functional | 121.2% | 589 | 251 | 2015-09-01
201408 | 050.36302 | PRP.2737.HAR.GREENBR SUB 2014 | 2013-09-26 | 2014-10-01 | 100% | 770435.2 | 770435.2 | 372242.77 | Non Functional | 207% | 705 | 370 | 2015-09-01
201408 | 050.36303 | PRP.2738.GRN.W COL AVE 2014 | 2013-10-02 | 2014-09-30 | 100% | 311198.5 | 311198.5 | 237404.34 | Non Functional | 131.1% | 699 | 363 | 2015-09-01
201408 | 050.36306 | ERX project - Hopkinsville | 2013-10-01 | 2014-09-30 | 100% | 7544.83 | 7544.83 | 9034.64 | Non Functional | 83.51% | 700 | 364 | 2015-09-01
201408 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201408 | 050.36378 | PRP.2737.E FACTORY-BARE JT | 2014-01-08 | 2015-01-08 | 100% | 131431.43 | 131431.43 | 277467.55 | Non Functional | 47.37% | 601 | 365 | 2015-09-01
201408 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201408 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201408 | 050.36475 | 2734.TRENCHER-WALK W/TRAILER | 2013-10-01 | 2014-09-30 | 100% | 21481.5 | 21481.5 | 22648.19 | Non Functional | 94.85% | 700 | 364 | 2015-09-01
201408 | 050.36478 | 2734.BG.FRAN.MADISON REG REP | 2013-10-01 | 2014-09-30 | 100% | 14298.69 | 14298.69 | 10279.06 | Non Functional | 139.1% | 700 | 364 | 2015-09-01
201408 | 050.36519 | 050.2734.North-South2inchRep | 2013-12-03 | 2014-09-28 | 100% | 3211.56 | 3211.56 | 788.51 | Non Functional | 407.3% | 637 | 299 | 2015-09-01
201408 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201408 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201408 | 050.36611 | PRP.2735.MUN.E UNION ST 2014 | 2013-10-04 | 2014-09-30 | 100% | 141792.06 | 141792.06 | 150044.31 | Non Functional | 94.5% | 697 | 361 | 2015-09-01
201408 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201408 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201408 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201408 | 050.36655 | PRP.2735.MUN.MILL ST 2014 | 2014-01-01 | 2015-01-01 | 100% | 180214.35 | 180214.35 | 129421.42 | Non Functional | 139.2% | 608 | 365 | 2015-09-01
201408 | 050.36696 | 050.2634.Robards TB Station | 2014-02-01 | 2014-10-28 | 100% | 146685.57 | 146685.57 | 157690.6 | Non Functional | 93.02% | 577 | 269 | 2015-09-01
201408 | 050.36708 | PRP.2737.N MAIN.PRICE 2014 | 2014-03-01 | 2015-03-01 | 100% | 374542.02 | 374542.02 | 492199.27 | Non Functional | 76.1% | 549 | 365 | 2015-09-01
201408 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201408 | 050.36799 | 2737.DAN.ERX INSTALLATION | 2013-10-01 | 2014-09-30 | 100% | 29827.38 | 29827.38 | 16759.91 | Non Functional | 178% | 700 | 364 | 2015-09-01
201408 | 050.36801 | 2738.GRNBURG.CAMP-RECTIFIER | 2013-10-01 | 2014-09-30 | 100% | 47902.59 | 47902.59 | 15083.1 | Non Functional | 317.6% | 700 | 364 | 2015-09-01
201408 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201408 | 050.36878 | PRP.2734.BG-Normal to Regents | 2013-10-23 | 2014-09-30 | 100% | 280654.79 | 280654.79 | 198269.87 | Non Functional | 141.6% | 678 | 342 | 2015-09-01
201408 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201408 | 050.36902 | 050.2734.Hwy31W Public Imprv | 2014-02-17 | 2014-09-28 | 100% | 246623.13 | 246623.13 | -2297.86 | Non Functional | -10733% | 561 | 223 | 2015-09-01
201408 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201408 | 050.37007 | 050.2634.College Dr. Reloc. | 2014-05-01 | 2014-09-28 | 100% | 23277.86 | 23277.86 | -5957.89 | Non Functional | -390.7% | 488 | 150 | 2015-09-01
201408 | 050.37040 | 050.2734.Massey Springs III | 2014-03-31 | 2014-09-28 | 100% | 5269.9 | 5269.9 | 3957.59 | Non Functional | 133.2% | 519 | 181 | 2015-09-01
201408 | 050.37054 | 050.2734.2 inchExt.Cableas | 2014-04-01 | 2014-09-28 | 100% | 8137.88 | 8137.88 | 5041.95 | Non Functional | 161.4% | 518 | 180 | 2015-09-01
201408 | 050.37077 | 050.2734.ThreeSprings II.Hwy | 2014-03-31 | 2014-09-28 | 100% | 730962.37 | 730962.37 | 101956.53 | Non Functional | 716.9% | 519 | 181 | 2015-09-01
201408 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201408 | 050.37154 | Install Infrared red heater | 2014-06-01 | 2014-08-01 | 100% | 51622.76 | 51622.76 | 37731.96 | Non Functional | 136.8% | 457 | 61 | 2015-09-01
201408 | 050.37185 | PRP.2635.Dawson Road Repl | 2014-04-15 | 2014-06-01 | 100% | 3095.75 | 3095.75 | 3322.12 | Non Functional | 93.19% | 504 | 47 | 2015-09-01
201408 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201408 | 050.37296 | 050.2734.Sunnitt Phase IV | 2014-03-24 | 2014-09-28 | 100% | 23165.19 | 23165.19 | 17510.41 | Non Functional | 132.3% | 526 | 188 | 2015-09-01
201408 | 050.37301 | 2739.SVILLE.8th - COLLEGE LP | 2012-02-01 | 2014-09-30 | 100% | 38918.57 | 38918.57 | 34704.87 | Non Functional | 112.1% | 1308 | 972 | 2015-09-01
201408 | 050.37351 | 050.2634.Slaughters upgrade | 2014-07-20 | 2014-09-28 | 100% | 62262.85 | 62262.85 | 63661.47 | Non Functional | 97.8% | 408 | 70 | 2015-09-01
201408 | 050.37407 | 050.2734.CalBastel 2 inch Ext | 2014-05-08 | 2014-09-28 | 100% | 2130.18 | 2130.18 | 1634.83 | Non Functional | 130.3% | 481 | 143 | 2015-09-01
201408 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201408 | 050.37445 | PRP.2635.Franklin Alley | 2014-06-01 | 2014-07-01 | 100% | 1081.18 | 1081.18 | 5514.06 | Non Functional | 19.61% | 457 | 30 | 2015-09-01
201408 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201408 | 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | 2013-10-03 | 2014-11-30 | 100% | 135880.55 | 135880.55 | 261192.99 | Non Functional | 52.02% | 698 | 423 | 2015-09-01
201408 | 050.37534 | 050.2602.MDT XP Non Support | 2014-05-25 | 2014-08-20 | 100% | 142725.32 | 142725.32 | 111117.14 | Non Functional | 128.4% | 464 | 87 | 2015-09-01
201408 | 050.37538 | PRP.2635.1st Street Replace | 2014-05-20 | 2014-06-30 | 100% | 2666.95 | 2666.95 | 534.3 | Non Functional | 499.1% | 469 | 41 | 2015-09-01
201408 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201408 | 050.37614 | PRP.2636.Hwy 181 | 2014-05-20 | 2014-07-01 | 100% | 33963.34 | 33963.34 | 22627.52 | Non Functional | 150.1% | 469 | 42 | 2015-09-01
201408 | 050.37668 | PRP.2635.Brook St Replace | 2014-06-02 | 2014-07-30 | 100% | 5257.15 | 5257.15 | 10448.21 | Non Functional | 50.32% | 456 | 58 | 2015-09-01
201408 | 050.37682 | 050.2636.Elwood Ct. | 2014-06-20 | 2014-07-01 | 100% | 6527.3 | 6527.3 | 8078.32 | Non Functional | 80.8% | 438 | 11 | 2015-09-01
201408 | 050.37683 | 050.2636.Meridian Ct | 2014-06-20 | 2014-07-01 | 100% | 6527.3 | 6527.3 | 9413.42 | Non Functional | 69.34% | 438 | 11 | 2015-09-01
201408 | 050.37698 | 2739.LAW.EVERGREEN TBS 2014 | 2013-10-01 | 2014-09-30 | 100% | 38690.79 | 38690.79 | 30753.25 | Non Functional | 125.8% | 700 | 364 | 2015-09-01
201408 | 050.37743 | 050.2734.Henderson Ind.Park | 2014-07-31 | 2014-09-28 | 100% | 69842.85 | 69842.85 | 16580.26 | Non Functional | 421.2% | 397 | 59 | 2015-09-01
201408 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201408 | 050.37808 | 2738.SPR.HWY 150.CORNERSTONE | 2014-01-01 | 2014-09-30 | 100% | 24903.49 | 24903.49 | 17964.24 | Non Functional | 138.6% | 608 | 272 | 2015-09-01
201408 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201408 | 050.37863 | x | 2014-06-30 | 2014-09-28 | 100% | 40990.13 | 40990.13 | 64851.14 | Non Functional | 63.21% | 428 | 90 | 2015-09-01
201408 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201408 | 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | 2014-07-22 | 2014-12-31 | 100% | 47164.67 | 47164.67 | 39204.28 | Non Functional | 120.3% | 406 | 162 | 2015-09-01
201408 | 050.37948 | 050.2736.W 8th St Relocate | 2014-07-28 | 2014-08-30 | 100% | 8280.47 | 8280.47 | 11018.06 | Non Functional | 75.15% | 400 | 33 | 2015-09-01
201408 | 050.37959 | 050.2637.Hwy 95 Relocate | 2014-07-17 | 2014-08-30 | 100% | 3042.73 | 3042.73 | 785.66 | Non Functional | 387.3% | 411 | 44 | 2015-09-01
201408 | 050.37965 | 050.2636.Greenville 6 Inch Re | 2014-07-10 | 2014-11-28 | 100% | 123381.36 | 123381.36 | 119846.93 | Non Functional | 102.9% | 418 | 141 | 2015-09-01
201408 | 050.37999 | 050.2734.BelleHaven III | 2014-07-14 | 2014-09-28 | 100% | 7925.37 | 7925.37 | 4168.1 | Non Functional | 190.1% | 414 | 76 | 2015-09-01
201408 | 050.38038 | 050.2638.Douthitt St Ext | 2014-07-28 | 2014-08-30 | 100% | 5350.57 | 5350.57 | 11161.29 | Non Functional | 47.94% | 400 | 33 | 2015-09-01
201408 | 050.38046 | 050.2636.Vincent Station Rd. | 2014-08-01 | 2014-08-30 | 100% | 2243.9 | 2243.9 | 1562.93 | Non Functional | 143.6% | 396 | 29 | 2015-09-01
201408 | 050.38086 | 050.2734.Northridge VII | 2014-06-16 | 2014-09-28 | 100% | 12478.77 | 12478.77 | 6686.88 | Non Functional | 186.6% | 442 | 104 | 2015-09-01
201408 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201408 | 050.38155 | 050.2638.Commonwealth Dr Ext | 2014-08-04 | 2014-09-30 | 100% | 5918.05 | 5918.05 | 2838.64 | Non Functional | 208.5% | 393 | 57 | 2015-09-01
201408 | 050.38179 | 2735.WALL ST 2014 | 2014-08-01 | 2014-09-30 | 100% | 1340.89 | 1340.89 | 901.5 | Non Functional | 148.7% | 396 | 60 | 2015-09-01
201408 | 050.38187 | 050.2636.Aldi Hwy 54 | 2014-08-01 | 2014-08-30 | 100% | 12037.3 | 12037.3 | -2912.02 | Non Functional | -413.4% | 396 | 29 | 2015-09-01
201408 | 050.38210 | 050.2636.Medley Rd. | 2014-08-10 | 2014-09-28 | 100% | 10559.59 | 10559.59 | 4319.45 | Non Functional | 244.5% | 387 | 49 | 2015-09-01
201408 | 050.38212 | 2737.JC.MARGUS DR 2014 | 2014-08-01 | 2015-08-01 | 100% | 4226.75 | 4226.75 | 5651.79 | Non Functional | 74.79% | 396 | 365 | 2015-09-01
201408 | 050.38233 | PRP.2735.HISE.CORAL HILL 14 | 2014-08-08 | 2014-09-30 | 100% | 21569.11 | 21569.11 | 17140.03 | Non Functional | 125.8% | 389 | 53 | 2015-09-01
201408 | 050.38244 | 2737.JC.HWY 2141 2014 | 2014-06-01 | 2014-09-30 | 100% | 4333.33 | 4333.33 | 1197.13 | Non Functional | 362% | 457 | 121 | 2015-09-01
201408 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201408 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201408 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201409 | 050.32986 | RTU upgrades KY | 2012-10-12 | 2014-09-30 | 100% | 7177.44 | 7177.44 | 13428.71 | Non Functional | 53.45% | 1054 | 718 | 2015-09-01
201409 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201409 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201409 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201409 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201409 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201409 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201409 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201409 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201409 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201409 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201409 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201409 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201409 | 050.36107 | KY Kinder Morgan ROC Cont | 2013-12-09 | 2014-05-01 | 100% | 56126.59 | 56126.59 | 70451.79 | Non Functional | 79.67% | 631 | 143 | 2015-09-01
201409 | 050.36109 | ECAT Replacement KY | 2013-12-09 | 2014-04-01 | 100% | 53041.48 | 53041.48 | 51711.08 | Non Functional | 102.6% | 631 | 113 | 2015-09-01
201409 | 050.36113 | Electronic Correctors KY | 2013-12-09 | 2014-10-01 | 100% | 34518.05 | 34518.05 | 17984.32 | Non Functional | 191.9% | 631 | 296 | 2015-09-01
201409 | 050.36117 | Emergency Regulators KY | 2013-12-09 | 2014-09-01 | 100% | 31904.24 | 31904.24 | 1778.7 | Non Functional | 1794% | 631 | 266 | 2015-09-01
201409 | 050.36119 | Habit Purchase Heater KY | 2013-12-09 | 2014-10-01 | 100% | 141587.83 | 141587.83 | 176580.15 | Non Functional | 80.18% | 631 | 296 | 2015-09-01
201409 | 050.36120 | Large Com/Indus Meter KY | 2013-12-09 | 2014-02-01 | 100% | 22930.23 | 22930.23 | 1909.16 | Non Functional | 1201% | 631 | 54 | 2015-09-01
201409 | 050.36121 | ROC Upgrades KY | 2013-12-09 | 2014-07-01 | 100% | 23747.27 | 23747.27 | 39471.98 | Non Functional | 60.16% | 631 | 204 | 2015-09-01
201409 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201409 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201409 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201409 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201409 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201409 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201409 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201409 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201409 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201409 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201409 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201409 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201409 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201409 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201409 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201409 | 050.37154 | Install Infrared red heater | 2014-06-01 | 2014-08-01 | 100% | 51622.76 | 51622.76 | 37731.96 | Non Functional | 136.8% | 457 | 61 | 2015-09-01
201409 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201409 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201409 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201409 | 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | 2013-10-03 | 2014-11-30 | 100% | 135880.55 | 135880.55 | 261192.99 | Non Functional | 52.02% | 698 | 423 | 2015-09-01
201409 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201409 | 050.37575 | 2738.Lebanon Waterbath Heater | 2014-05-29 | 2014-11-30 | 100% | 64276.66 | 64276.66 | 65483.87 | Non Functional | 98.16% | 460 | 185 | 2015-09-01
201409 | 050.37743 | 050.2734.Henderson Ind.Park | 2014-07-31 | 2014-09-28 | 100% | 69842.85 | 69842.85 | 16580.26 | Non Functional | 421.2% | 397 | 59 | 2015-09-01
201409 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201409 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201409 | 050.37863 | x | 2014-06-30 | 2014-09-28 | 100% | 40990.13 | 40990.13 | 64851.14 | Non Functional | 63.21% | 428 | 90 | 2015-09-01
201409 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201409 | 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | 2014-07-22 | 2014-12-31 | 100% | 47164.67 | 47164.67 | 39204.28 | Non Functional | 120.3% | 406 | 162 | 2015-09-01
201409 | 050.37965 | 050.2636.Greenville 6 Inch Re | 2014-07-10 | 2014-11-28 | 100% | 123381.36 | 123381.36 | 119846.93 | Non Functional | 102.9% | 418 | 141 | 2015-09-01
201409 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201409 | 050.38009 | 050.2637.Noble Road Relocatio | 2014-08-04 | 2014-08-22 | 100% | 5932.5 | 5932.5 | 21764.64 | Non Functional | 27.26% | 393 | 18 | 2015-09-01
201409 | 050.38046 | 050.2636.Vincent Station Rd. | 2014-08-01 | 2014-08-30 | 100% | 2243.9 | 2243.9 | 1562.93 | Non Functional | 143.6% | 396 | 29 | 2015-09-01
201409 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201409 | 050.38187 | 050.2636.Aldi Hwy 54 | 2014-08-01 | 2014-08-30 | 100% | 12037.3 | 12037.3 | -2912.02 | Non Functional | -413.4% | 396 | 29 | 2015-09-01
201409 | 050.38233 | PRP.2735.HISE.CORAL HILL 14 | 2014-08-08 | 2014-09-30 | 100% | 21569.11 | 21569.11 | 17140.03 | Non Functional | 125.8% | 389 | 53 | 2015-09-01
201409 | 050.38278 | 050.2635.Eddyville Mall Ext | 2014-08-30 | 2014-09-28 | 100% | 1508.21 | 1508.21 | 238.94 | Non Functional | 631.2% | 367 | 29 | 2015-09-01
201409 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201409 | 050.38364 | 050.2635.Marion Ind Park | 2014-09-02 | 2014-09-28 | 100% | 15330.99 | 15330.99 | -1545.03 | Non Functional | -992.3% | 364 | 26 | 2015-09-01
201409 | 050.38374 | 050.2637.Lovelaceville Rd Ext | 2014-09-08 | 2014-10-30 | 100% | 6615.85 | 6615.85 | 7596.74 | Non Functional | 87.09% | 358 | 52 | 2015-09-01
201409 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201409 | 050.38415 | PRP.2734.Riverview & College | 2014-07-28 | 2015-02-28 | 100% | 1001570.07 | 1001570.07 | 429071.83 | Non Functional | 233.4% | 400 | 215 | 2015-09-01
201409 | 050.38537 | 050.2636.Boston Laffon Rd. | 2014-09-22 | 2014-10-31 | 100% | 8972.87 | 8972.87 | -145.03 | Non Functional | -6187% | 344 | 39 | 2015-09-01
201409 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201410 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201410 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201410 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201410 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201410 | 050.33413 | 050.2634.Northern Star Way | 2013-02-11 | 2014-11-30 | 100% | 7687.81 | 7687.81 | 13010.33 | Non Functional | 59.09% | 932 | 657 | 2015-09-01
201410 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201410 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201410 | 050.35013 | PRP.2609.Fruithill Hoptown 2 | 2013-10-01 | 2014-12-31 | 100% | 1103330.85 | 7419912.38 | 6451425.23 | Non Functional | 115% | 700 | 456 | 2015-09-01
201410 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201410 | 050.35065 | 050.3439.TC.AIRPORT.STA.EQUIP | 2013-09-05 | 2014-08-15 | 100% | 53963.3 | 53963.3 | 11896.23 | Non Functional | 453.6% | 726 | 344 | 2015-09-01
201410 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201410 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201410 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201410 | 050.36288 | New Paducah Office | 2014-03-01 | 2014-11-30 | 100% | 1362000 | 1362000 | 1642077.26 | Non Functional | 82.94% | 549 | 274 | 2015-09-01
201410 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201410 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201410 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201410 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201410 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201410 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201410 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201410 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201410 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201410 | 050.36850 | 050.2736.8 Inch Improvement | 2014-02-20 | 2014-11-30 | 100% | 1507485.01 | 6639868.23 | 6453262.46 | Non Functional | 102.9% | 558 | 283 | 2015-09-01
201410 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201410 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201410 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201410 | 050.37154 | Install Infrared red heater | 2014-06-01 | 2014-08-01 | 100% | 51622.76 | 51622.76 | 37731.96 | Non Functional | 136.8% | 457 | 61 | 2015-09-01
201410 | 050.37261 | 050.2635.Fox Road Rev Ext | 2014-05-15 | 2014-07-15 | 100% | 18037.76 | 18037.76 | -4545.68 | Non Functional | -396.8% | 474 | 61 | 2015-09-01
201410 | 050.37370 | 050.2636.Reg.Station Imp. | 2013-10-01 | 2014-11-30 | 100% | 24779.23 | 24779.23 | 16914.44 | Non Functional | 146.5% | 700 | 425 | 2015-09-01
201410 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201410 | 050.37442 | 050.2634.Reg & ERX Rplmnt | 2014-05-20 | 2014-10-28 | 100% | 77135.3 | 77135.3 | 67327.98 | Non Functional | 114.6% | 469 | 161 | 2015-09-01
201410 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201410 | 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | 2013-10-03 | 2014-11-30 | 100% | 135880.55 | 135880.55 | 261192.99 | Non Functional | 52.02% | 698 | 423 | 2015-09-01
201410 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201410 | 050.37575 | 2738.Lebanon Waterbath Heater | 2014-05-29 | 2014-11-30 | 100% | 64276.66 | 64276.66 | 65483.87 | Non Functional | 98.16% | 460 | 185 | 2015-09-01
201410 | 050.37743 | 050.2734.Henderson Ind.Park | 2014-07-31 | 2014-09-28 | 100% | 69842.85 | 69842.85 | 16580.26 | Non Functional | 421.2% | 397 | 59 | 2015-09-01
201410 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201410 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201410 | 050.37863 | x | 2014-06-30 | 2014-09-28 | 100% | 40990.13 | 40990.13 | 64851.14 | Non Functional | 63.21% | 428 | 90 | 2015-09-01
201410 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201410 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201410 | 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | 2014-07-22 | 2014-12-31 | 100% | 47164.67 | 47164.67 | 39204.28 | Non Functional | 120.3% | 406 | 162 | 2015-09-01
201410 | 050.37965 | 050.2636.Greenville 6 Inch Re | 2014-07-10 | 2014-11-28 | 100% | 123381.36 | 123381.36 | 119846.93 | Non Functional | 102.9% | 418 | 141 | 2015-09-01
201410 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201410 | 050.38009 | 050.2637.Noble Road Relocatio | 2014-08-04 | 2014-08-22 | 100% | 5932.5 | 5932.5 | 21764.64 | Non Functional | 27.26% | 393 | 18 | 2015-09-01
201410 | 050.38046 | 050.2636.Vincent Station Rd. | 2014-08-01 | 2014-08-30 | 100% | 2243.9 | 2243.9 | 1562.93 | Non Functional | 143.6% | 396 | 29 | 2015-09-01
201410 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201410 | 050.38187 | 050.2636.Aldi Hwy 54 | 2014-08-01 | 2014-08-30 | 100% | 12037.3 | 12037.3 | -2912.02 | Non Functional | -413.4% | 396 | 29 | 2015-09-01
201410 | 050.38278 | 050.2635.Eddyville Mall Ext | 2014-08-30 | 2014-09-28 | 100% | 1508.21 | 1508.21 | 238.94 | Non Functional | 631.2% | 367 | 29 | 2015-09-01
201410 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201410 | 050.38364 | 050.2635.Marion Ind Park | 2014-09-02 | 2014-09-28 | 100% | 15330.99 | 15330.99 | -1545.03 | Non Functional | -992.3% | 364 | 26 | 2015-09-01
201410 | 050.38374 | 050.2637.Lovelaceville Rd Ext | 2014-09-08 | 2014-10-30 | 100% | 6615.85 | 6615.85 | 7596.74 | Non Functional | 87.09% | 358 | 52 | 2015-09-01
201410 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201410 | 050.38415 | PRP.2734.Riverview & College | 2014-07-28 | 2015-02-28 | 100% | 1001570.07 | 1001570.07 | 429071.83 | Non Functional | 233.4% | 400 | 215 | 2015-09-01
201410 | 050.38536 | 2735.CORAL HILL 2014 | 2014-10-01 | 2014-11-01 | 100% | 22972.84 | 22972.84 | 40379 | Non Functional | 56.89% | 335 | 31 | 2015-09-01
201410 | 050.38537 | 050.2636.Boston Laffon Rd. | 2014-09-22 | 2014-10-31 | 100% | 8972.87 | 8972.87 | -145.03 | Non Functional | -6187% | 344 | 39 | 2015-09-01
201410 | 050.38863 | 050.2636.Milton Rd. Ext | 2014-10-01 | 2014-12-30 | 100% | 19806.92 | 19806.92 | 24481.54 | Non Functional | 80.91% | 335 | 90 | 2015-09-01
201410 | 050.38881 | 050.2734.CumberlandRdg.VI | 2014-10-06 | 2014-12-15 | 100% | 9525.65 | 9525.65 | 5636.22 | Non Functional | 169% | 330 | 70 | 2015-09-01
201410 | 050.38897 | PRP.2738.W HODGENVILL-McCULLE | 2014-10-01 | 2015-02-28 | 100% | 190161.96 | 190161.96 | 210266.02 | Non Functional | 90.44% | 335 | 150 | 2015-09-01
201410 | 050.38903 | PRP.2735.Glasgow.E. Main St | 2014-10-01 | 2015-05-30 | 100% | 216264.06 | 346825.84 | 363011.29 | Non Functional | 95.54% | 335 | 241 | 2015-09-01
201410 | 050.38912 | 2637.New Office Furniture | 2014-10-01 | 2014-12-30 | 100% | 118659.55 | 118659.55 | 124405.32 | Non Functional | 95.38% | 335 | 90 | 2015-09-01
201410 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201410 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201410 | 050.38968 | PRP.2734.Bristow Rd. Replc | 2014-10-01 | 2015-05-30 | 100% | 135278.75 | 135278.75 | 77763.54 | Non Functional | 174% | 335 | 241 | 2015-09-01
201410 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201410 | 050.38970 | 050.2636WhisperingMeadows II | 2014-10-20 | 2015-01-28 | 100% | 5468.51 | 5468.51 | 4930.96 | Non Functional | 110.9% | 316 | 100 | 2015-09-01
201410 | 050.38971 | 050.2636.DeerValleyExt. | 2014-10-15 | 2014-11-30 | 100% | 11847.32 | 11847.32 | 10787.4 | Non Functional | 109.8% | 321 | 46 | 2015-09-01
201410 | 050.38972 | PRP.2734.Nashville Rd. Replc. | 2014-09-22 | 2014-10-31 | 100% | 24151.33 | 24151.33 | 13669.67 | Non Functional | 176.7% | 344 | 39 | 2015-09-01
201410 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201410 | 050.39096 | 050.2637.Highland Ch Rd Ext | 2014-11-03 | 2014-12-30 | 100% | 1844.87 | 1844.87 | 4774.2 | Non Functional | 38.64% | 302 | 57 | 2015-09-01
201410 | 050.39097 | 050.2637.Strathmoore Ext | 2014-10-27 | 2014-12-30 | 100% | 1635.55 | 1635.55 | 1856.5 | Non Functional | 88.1% | 309 | 64 | 2015-09-01
201410 | 050.39151 | 2634.Woodlawn.Dr.Lot.Pur.FY15 | 2014-11-04 | 2014-12-30 | 100% | 2000 | 2000 | 2723.21 | Non Functional | 73.44% | 301 | 56 | 2015-09-01
201410 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201411 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201411 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201411 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201411 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201411 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201411 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201411 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201411 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201411 | 050.35970 | PRP.2736.Hville-W Side South | 2013-10-10 | 2015-01-30 | 100% | 475995.86 | 727947.71 | 761624.8 | Non Functional | 95.58% | 691 | 477 | 2015-09-01
201411 | 050.36287 | PRP.2609.Fruithill 4 Inch PE | 2014-01-15 | 2014-11-15 | 100% | 480743.64 | 480743.64 | 429283.33 | Non Functional | 112% | 594 | 304 | 2015-09-01
201411 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201411 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201411 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201411 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201411 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201411 | 050.36618 | 2738.OFFICE BUILDING 2014 | 2014-04-01 | 2014-10-31 | 100% | 690000 | 690000 | 873664.21 | Non Functional | 78.98% | 518 | 213 | 2015-09-01
201411 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201411 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201411 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201411 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201411 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201411 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201411 | 050.37154 | Install Infrared red heater | 2014-06-01 | 2014-08-01 | 100% | 51622.76 | 51622.76 | 37731.96 | Non Functional | 136.8% | 457 | 61 | 2015-09-01
201411 | 050.37370 | 050.2636.Reg.Station Imp. | 2013-10-01 | 2014-11-30 | 100% | 24779.23 | 24779.23 | 16914.44 | Non Functional | 146.5% | 700 | 425 | 2015-09-01
201411 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201411 | 050.37442 | 050.2634.Reg & ERX Rplmnt | 2014-05-20 | 2014-10-28 | 100% | 77135.3 | 77135.3 | 67327.98 | Non Functional | 114.6% | 469 | 161 | 2015-09-01
201411 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201411 | 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | 2013-10-03 | 2014-11-30 | 100% | 135880.55 | 135880.55 | 261192.99 | Non Functional | 52.02% | 698 | 423 | 2015-09-01
201411 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201411 | 050.37743 | 050.2734.Henderson Ind.Park | 2014-07-31 | 2014-09-28 | 100% | 69842.85 | 69842.85 | 16580.26 | Non Functional | 421.2% | 397 | 59 | 2015-09-01
201411 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201411 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201411 | 050.37863 | x | 2014-06-30 | 2014-09-28 | 100% | 40990.13 | 40990.13 | 64851.14 | Non Functional | 63.21% | 428 | 90 | 2015-09-01
201411 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201411 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201411 | 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | 2014-07-22 | 2014-12-31 | 100% | 47164.67 | 47164.67 | 39204.28 | Non Functional | 120.3% | 406 | 162 | 2015-09-01
201411 | 050.37965 | 050.2636.Greenville 6 Inch Re | 2014-07-10 | 2014-11-28 | 100% | 123381.36 | 123381.36 | 119846.93 | Non Functional | 102.9% | 418 | 141 | 2015-09-01
201411 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201411 | 050.38009 | 050.2637.Noble Road Relocatio | 2014-08-04 | 2014-08-22 | 100% | 5932.5 | 5932.5 | 21764.64 | Non Functional | 27.26% | 393 | 18 | 2015-09-01
201411 | 050.38046 | 050.2636.Vincent Station Rd. | 2014-08-01 | 2014-08-30 | 100% | 2243.9 | 2243.9 | 1562.93 | Non Functional | 143.6% | 396 | 29 | 2015-09-01
201411 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201411 | 050.38187 | 050.2636.Aldi Hwy 54 | 2014-08-01 | 2014-08-30 | 100% | 12037.3 | 12037.3 | -2912.02 | Non Functional | -413.4% | 396 | 29 | 2015-09-01
201411 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201411 | 050.38374 | 050.2637.Lovelaceville Rd Ext | 2014-09-08 | 2014-10-30 | 100% | 6615.85 | 6615.85 | 7596.74 | Non Functional | 87.09% | 358 | 52 | 2015-09-01
201411 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201411 | 050.38415 | PRP.2734.Riverview & College | 2014-07-28 | 2015-02-28 | 100% | 1001570.07 | 1001570.07 | 429071.83 | Non Functional | 233.4% | 400 | 215 | 2015-09-01
201411 | 050.38537 | 050.2636.Boston Laffon Rd. | 2014-09-22 | 2014-10-31 | 100% | 8972.87 | 8972.87 | -145.03 | Non Functional | -6187% | 344 | 39 | 2015-09-01
201411 | 050.38863 | 050.2636.Milton Rd. Ext | 2014-10-01 | 2014-12-30 | 100% | 19806.92 | 19806.92 | 24481.54 | Non Functional | 80.91% | 335 | 90 | 2015-09-01
201411 | 050.38881 | 050.2734.CumberlandRdg.VI | 2014-10-06 | 2014-12-15 | 100% | 9525.65 | 9525.65 | 5636.22 | Non Functional | 169% | 330 | 70 | 2015-09-01
201411 | 050.38897 | PRP.2738.W HODGENVILL-McCULLE | 2014-10-01 | 2015-02-28 | 100% | 190161.96 | 190161.96 | 210266.02 | Non Functional | 90.44% | 335 | 150 | 2015-09-01
201411 | 050.38903 | PRP.2735.Glasgow.E. Main St | 2014-10-01 | 2015-05-30 | 100% | 216264.06 | 346825.84 | 363011.29 | Non Functional | 95.54% | 335 | 241 | 2015-09-01
201411 | 050.38912 | 2637.New Office Furniture | 2014-10-01 | 2014-12-30 | 100% | 118659.55 | 118659.55 | 124405.32 | Non Functional | 95.38% | 335 | 90 | 2015-09-01
201411 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201411 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201411 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201411 | 050.38968 | PRP.2734.Bristow Rd. Replc | 2014-10-01 | 2015-05-30 | 100% | 135278.75 | 135278.75 | 77763.54 | Non Functional | 174% | 335 | 241 | 2015-09-01
201411 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201411 | 050.38970 | 050.2636WhisperingMeadows II | 2014-10-20 | 2015-01-28 | 100% | 5468.51 | 5468.51 | 4930.96 | Non Functional | 110.9% | 316 | 100 | 2015-09-01
201411 | 050.38971 | 050.2636.DeerValleyExt. | 2014-10-15 | 2014-11-30 | 100% | 11847.32 | 11847.32 | 10787.4 | Non Functional | 109.8% | 321 | 46 | 2015-09-01
201411 | 050.38972 | PRP.2734.Nashville Rd. Replc. | 2014-09-22 | 2014-10-31 | 100% | 24151.33 | 24151.33 | 13669.67 | Non Functional | 176.7% | 344 | 39 | 2015-09-01
201411 | 050.39019 | 050.2736.E Pton Rd Ext | 2014-10-20 | 2015-02-27 | 100% | 15534.97 | 15534.97 | 15672.66 | Non Functional | 99.12% | 316 | 130 | 2015-09-01
201411 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201411 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201411 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201411 | 050.39096 | 050.2637.Highland Ch Rd Ext | 2014-11-03 | 2014-12-30 | 100% | 1844.87 | 1844.87 | 4774.2 | Non Functional | 38.64% | 302 | 57 | 2015-09-01
201411 | 050.39097 | 050.2637.Strathmoore Ext | 2014-10-27 | 2014-12-30 | 100% | 1635.55 | 1635.55 | 1856.5 | Non Functional | 88.1% | 309 | 64 | 2015-09-01
201411 | 050.39098 | 050.2637.Park Ave Relocate | 2014-10-30 | 2015-02-28 | 100% | 2856.57 | 2856.57 | 8726.84 | Non Functional | 32.73% | 306 | 121 | 2015-09-01
201411 | 050.39099 | 050.2637.Key Dr Rev Ext | 2014-11-01 | 2015-02-27 | 100% | 1069 | 1069 | 4259.16 | Non Functional | 25.1% | 304 | 118 | 2015-09-01
201411 | 050.39101 | 050.2637.Lakes of Paducah | 2014-11-01 | 2015-02-27 | 100% | 6696.85 | 6696.85 | -1950.16 | Non Functional | -343.4% | 304 | 118 | 2015-09-01
201411 | 050.39106 | 050.2637.Krebs Sta Rd Ext | 2014-12-01 | 2015-02-27 | 100% | 2084.16 | 2084.16 | 3370.99 | Non Functional | 61.83% | 274 | 88 | 2015-09-01
201411 | 050.39115 | 050.2635.Cerulean Rd Replace | 2014-11-03 | 2014-12-31 | 100% | 1569.67 | 1569.67 | 929.79 | Non Functional | 168.8% | 302 | 58 | 2015-09-01
201411 | 050.39151 | 2634.Woodlawn.Dr.Lot.Pur.FY15 | 2014-11-04 | 2014-12-30 | 100% | 2000 | 2000 | 2723.21 | Non Functional | 73.44% | 301 | 56 | 2015-09-01
201411 | 050.39179 | 2735.CHEVY LN 2015 | 2014-11-01 | 2015-02-01 | 100% | 1495.48 | 1495.48 | 4157.38 | Non Functional | 35.97% | 304 | 92 | 2015-09-01
201411 | 050.39270 | 050.2634.McCoy Ave Ext | 2014-11-05 | 2014-12-31 | 100% | 1219.65 | 1219.65 | 1523.84 | Non Functional | 80.04% | 300 | 56 | 2015-09-01
201411 | 050.39271 | 050.2736.Russellville Rd Ext | 2014-11-01 | 2015-02-27 | 100% | 21100.66 | 21100.66 | 16586.55 | Non Functional | 127.2% | 304 | 118 | 2015-09-01
201411 | 050.39281 | 050.2635.Mechanic St Ext | 2014-12-01 | 2014-12-31 | 100% | 1312.53 | 1312.53 | 2760.53 | Non Functional | 47.55% | 274 | 30 | 2015-09-01
201411 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201412 | 050.32989 | 050.2612 KY Correctors | 2012-12-06 | 2013-09-29 | 100% | 11165.3 | 11165.3 | 810.51 | Non Functional | 1378% | 999 | 297 | 2015-09-01
201412 | 050.32990 | 050.2612 TN ECAT Replacement | 2012-12-06 | 2013-09-29 | 100% | 9569.6 | 9569.6 | 19247.78 | Non Functional | 49.72% | 999 | 297 | 2015-09-01
201412 | 050.32998 | 050.2612 ECAT Replacement KY | 2012-12-06 | 2013-09-29 | 100% | 5741.7 | 5741.7 | 8290.56 | Non Functional | 69.26% | 999 | 297 | 2015-09-01
201412 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201412 | 050.34850 | PRP.2nd at Bethel - Russ | 2013-08-05 | 2013-12-31 | 100% | 24440.03 | 24440.03 | 10755.09 | Non Functional | 227.2% | 757 | 148 | 2015-09-01
201412 | 050.35012 | PRP.2609.Greenriver Steel | 2013-08-25 | 2014-12-31 | 100% | 1230804.04 | 1230804.04 | 1365758.73 | Non Functional | 90.12% | 737 | 493 | 2015-09-01
201412 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201412 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201412 | 050.36320 | PRP.2738.GRN.DEPOT ST 2014 | 2013-10-04 | 2014-11-30 | 100% | 343251.89 | 343251.89 | 259165.18 | Non Functional | 132.4% | 697 | 422 | 2015-09-01
201412 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201412 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201412 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201412 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201412 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201412 | 050.36649 | PRP.2734.Gayle at Normalview | 2014-02-06 | 2014-09-28 | 100% | 7662.19 | 7662.19 | 1654.76 | Non Functional | 463% | 572 | 234 | 2015-09-01
201412 | 050.36776 | PRP.2736.Hville-W_Side_North | 2013-10-09 | 2015-01-30 | 100% | 352421.25 | 441006.96 | 458125.67 | Non Functional | 96.26% | 692 | 478 | 2015-09-01
201412 | 050.36898 | PRP.2734.South Way Replc. | 2014-03-12 | 2014-09-28 | 100% | 8039.75 | 8039.75 | 3953.08 | Non Functional | 203.4% | 538 | 200 | 2015-09-01
201412 | 050.36905 | PRP.2734.BG-Oaklawn-Loving-Rh | 2013-10-10 | 2014-09-30 | 100% | 330281.61 | 330281.61 | 0 | Non Functional | 0% | 691 | 355 | 2015-09-01
201412 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201412 | 050.37154 | Install Infrared red heater | 2014-06-01 | 2014-08-01 | 100% | 51622.76 | 51622.76 | 37731.96 | Non Functional | 136.8% | 457 | 61 | 2015-09-01
201412 | 050.37420 | 050.2637.Hansen Rd Rev-Ext | 2014-06-01 | 2014-09-28 | 100% | 3127.09 | 3127.09 | 1768.71 | Non Functional | 176.8% | 457 | 119 | 2015-09-01
201412 | 050.37446 | PRP.2734.W.5th-S.Main Replc | 2014-05-02 | 2014-09-28 | 100% | 3559.5 | 3559.5 | 5213.65 | Non Functional | 68.27% | 487 | 149 | 2015-09-01
201412 | 050.37476 | PRP.2737.LAN. ELLIOT ST 2014 | 2013-10-03 | 2014-11-30 | 100% | 135880.55 | 135880.55 | 261192.99 | Non Functional | 52.02% | 698 | 423 | 2015-09-01
201412 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201412 | 050.37743 | 050.2734.Henderson Ind.Park | 2014-07-31 | 2014-09-28 | 100% | 69842.85 | 69842.85 | 16580.26 | Non Functional | 421.2% | 397 | 59 | 2015-09-01
201412 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201412 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201412 | 050.37863 | x | 2014-06-30 | 2014-09-28 | 100% | 40990.13 | 40990.13 | 64851.14 | Non Functional | 63.21% | 428 | 90 | 2015-09-01
201412 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201412 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201412 | 050.37902 | PRP.2636.ORCHARD & MAPLE REPL | 2014-07-22 | 2014-12-31 | 100% | 47164.67 | 47164.67 | 39204.28 | Non Functional | 120.3% | 406 | 162 | 2015-09-01
201412 | 050.37965 | 050.2636.Greenville 6 Inch Re | 2014-07-10 | 2014-11-28 | 100% | 123381.36 | 123381.36 | 119846.93 | Non Functional | 102.9% | 418 | 141 | 2015-09-01
201412 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201412 | 050.38009 | 050.2637.Noble Road Relocatio | 2014-08-04 | 2014-08-22 | 100% | 5932.5 | 5932.5 | 21764.64 | Non Functional | 27.26% | 393 | 18 | 2015-09-01
201412 | 050.38046 | 050.2636.Vincent Station Rd. | 2014-08-01 | 2014-08-30 | 100% | 2243.9 | 2243.9 | 1562.93 | Non Functional | 143.6% | 396 | 29 | 2015-09-01
201412 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201412 | 050.38187 | 050.2636.Aldi Hwy 54 | 2014-08-01 | 2014-08-30 | 100% | 12037.3 | 12037.3 | -2912.02 | Non Functional | -413.4% | 396 | 29 | 2015-09-01
201412 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201412 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201412 | 050.38374 | 050.2637.Lovelaceville Rd Ext | 2014-09-08 | 2014-10-30 | 100% | 6615.85 | 6615.85 | 7596.74 | Non Functional | 87.09% | 358 | 52 | 2015-09-01
201412 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201412 | 050.38415 | PRP.2734.Riverview & College | 2014-07-28 | 2015-02-28 | 100% | 1001570.07 | 1001570.07 | 429071.83 | Non Functional | 233.4% | 400 | 215 | 2015-09-01
201412 | 050.38537 | 050.2636.Boston Laffon Rd. | 2014-09-22 | 2014-10-31 | 100% | 8972.87 | 8972.87 | -145.03 | Non Functional | -6187% | 344 | 39 | 2015-09-01
201412 | 050.38863 | 050.2636.Milton Rd. Ext | 2014-10-01 | 2014-12-30 | 100% | 19806.92 | 19806.92 | 24481.54 | Non Functional | 80.91% | 335 | 90 | 2015-09-01
201412 | 050.38881 | 050.2734.CumberlandRdg.VI | 2014-10-06 | 2014-12-15 | 100% | 9525.65 | 9525.65 | 5636.22 | Non Functional | 169% | 330 | 70 | 2015-09-01
201412 | 050.38897 | PRP.2738.W HODGENVILL-McCULLE | 2014-10-01 | 2015-02-28 | 100% | 190161.96 | 190161.96 | 210266.02 | Non Functional | 90.44% | 335 | 150 | 2015-09-01
201412 | 050.38903 | PRP.2735.Glasgow.E. Main St | 2014-10-01 | 2015-05-30 | 100% | 216264.06 | 346825.84 | 363011.29 | Non Functional | 95.54% | 335 | 241 | 2015-09-01
201412 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201412 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201412 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201412 | 050.38968 | PRP.2734.Bristow Rd. Replc | 2014-10-01 | 2015-05-30 | 100% | 135278.75 | 135278.75 | 77763.54 | Non Functional | 174% | 335 | 241 | 2015-09-01
201412 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201412 | 050.38970 | 050.2636WhisperingMeadows II | 2014-10-20 | 2015-01-28 | 100% | 5468.51 | 5468.51 | 4930.96 | Non Functional | 110.9% | 316 | 100 | 2015-09-01
201412 | 050.38971 | 050.2636.DeerValleyExt. | 2014-10-15 | 2014-11-30 | 100% | 11847.32 | 11847.32 | 10787.4 | Non Functional | 109.8% | 321 | 46 | 2015-09-01
201412 | 050.38972 | PRP.2734.Nashville Rd. Replc. | 2014-09-22 | 2014-10-31 | 100% | 24151.33 | 24151.33 | 13669.67 | Non Functional | 176.7% | 344 | 39 | 2015-09-01
201412 | 050.39019 | 050.2736.E Pton Rd Ext | 2014-10-20 | 2015-02-27 | 100% | 15534.97 | 15534.97 | 15672.66 | Non Functional | 99.12% | 316 | 130 | 2015-09-01
201412 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201412 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201412 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201412 | 050.39098 | 050.2637.Park Ave Relocate | 2014-10-30 | 2015-02-28 | 100% | 2856.57 | 2856.57 | 8726.84 | Non Functional | 32.73% | 306 | 121 | 2015-09-01
201412 | 050.39099 | 050.2637.Key Dr Rev Ext | 2014-11-01 | 2015-02-27 | 100% | 1069 | 1069 | 4259.16 | Non Functional | 25.1% | 304 | 118 | 2015-09-01
201412 | 050.39101 | 050.2637.Lakes of Paducah | 2014-11-01 | 2015-02-27 | 100% | 6696.85 | 6696.85 | -1950.16 | Non Functional | -343.4% | 304 | 118 | 2015-09-01
201412 | 050.39106 | 050.2637.Krebs Sta Rd Ext | 2014-12-01 | 2015-02-27 | 100% | 2084.16 | 2084.16 | 3370.99 | Non Functional | 61.83% | 274 | 88 | 2015-09-01
201412 | 050.39117 | 2738.ROLAND ST-MOBILE HOME 15 | 2015-01-01 | 2015-06-01 | 100% | 4200.32 | 4200.32 | 4632.36 | Non Functional | 90.67% | 243 | 151 | 2015-09-01
201412 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201412 | 050.39179 | 2735.CHEVY LN 2015 | 2014-11-01 | 2015-02-01 | 100% | 1495.48 | 1495.48 | 4157.38 | Non Functional | 35.97% | 304 | 92 | 2015-09-01
201412 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201412 | 050.39258 | 2739.CLOVERBROOK SEC 9-PH 2 | 2014-11-15 | 2015-03-01 | 100% | 6317.51 | 6317.51 | 14157.41 | Non Functional | 44.62% | 290 | 106 | 2015-09-01
201412 | 050.39271 | 050.2736.Russellville Rd Ext | 2014-11-01 | 2015-02-27 | 100% | 21100.66 | 21100.66 | 16586.55 | Non Functional | 127.2% | 304 | 118 | 2015-09-01
201412 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201412 | 050.39294 | PRP.2734.Church & Nugent St. | 2014-11-30 | 2015-06-30 | 100% | 187511.1 | 187511.1 | 132382.84 | Non Functional | 141.6% | 275 | 212 | 2015-09-01
201412 | 050.39297 | 2739.HERITAGE PARK 2014 | 2014-11-15 | 2015-03-01 | 100% | 21360.7 | 21360.7 | 12990.21 | Non Functional | 164.4% | 290 | 106 | 2015-09-01
201412 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201412 | 050.39373 | 2612.RTU Upgrades.KY.15 | 2014-12-04 | 2015-03-31 | 100% | 43420.04 | 43420.04 | 26563.14 | Non Functional | 163.5% | 271 | 117 | 2015-09-01
201412 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201412 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201412 | 050.39399 | 050.2637.H C Mathis Ext | 2014-12-08 | 2015-02-28 | 100% | 1865.07 | 1865.07 | 8301.39 | Non Functional | 22.47% | 267 | 82 | 2015-09-01
201412 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201412 | 050.39436 | 050.2638.Ken Tex Rd Ext | 2014-11-17 | 2015-02-27 | 100% | 6937.24 | 6937.24 | 1734.66 | Non Functional | 399.9% | 288 | 102 | 2015-09-01
201412 | 050.39453 | 050.2636.GoshenRd. Ext | 2014-12-15 | 2015-02-15 | 100% | 6930.65 | 6930.65 | 4686.67 | Non Functional | 147.9% | 260 | 62 | 2015-09-01
201412 | 050.39474 | PRP.2636.Walnut St.Rpl | 2014-12-10 | 2015-04-30 | 100% | 38007.74 | 38007.74 | 35369.57 | Non Functional | 107.5% | 265 | 141 | 2015-09-01
201412 | 050.39477 | 050.2636.Brownwood Oaks II | 2014-11-10 | 2015-12-10 | 74.68% | 4259.96 | 4259.96 | 5814.05 | Non Functional | 73.27% | 295 | 395 | 2015-09-01
201412 | 050.39478 | 050.2734.EaglestoneReloc.B.G. | 2014-12-16 | 2015-02-18 | 100% | 7088.5 | 7088.5 | 5536.12 | Non Functional | 128% | 259 | 64 | 2015-09-01
201412 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201501 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201501 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201501 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201501 | 050.36250 | Building Cost, Paducah Office | 2013-10-01 | 2013-11-30 | 100% | 0 | 0 | 0 | Non Functional | 0% | 700 | 60 | 2015-09-01
201501 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201501 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201501 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201501 | 050.36573 | 2734.BG.I65 31W CONN.COSMA DR | 2014-02-01 | 2015-03-13 | 100% | 102136.48 | 102136.48 | 51891.49 | Non Functional | 196.8% | 577 | 405 | 2015-09-01
201501 | 050.36619 | 2738.FURNITURE 2014 | 2014-07-01 | 2015-03-30 | 100% | 15000 | 15000 | 51900.35 | Non Functional | 28.9% | 427 | 272 | 2015-09-01
201501 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201501 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201501 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201501 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201501 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201501 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201501 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201501 | 050.38009 | 050.2637.Noble Road Relocatio | 2014-08-04 | 2014-08-22 | 100% | 5932.5 | 5932.5 | 21764.64 | Non Functional | 27.26% | 393 | 18 | 2015-09-01
201501 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201501 | 050.38187 | 050.2636.Aldi Hwy 54 | 2014-08-01 | 2014-08-30 | 100% | 12037.3 | 12037.3 | -2912.02 | Non Functional | -413.4% | 396 | 29 | 2015-09-01
201501 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201501 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201501 | 050.38374 | 050.2637.Lovelaceville Rd Ext | 2014-09-08 | 2014-10-30 | 100% | 6615.85 | 6615.85 | 7596.74 | Non Functional | 87.09% | 358 | 52 | 2015-09-01
201501 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201501 | 050.38415 | PRP.2734.Riverview & College | 2014-07-28 | 2015-02-28 | 100% | 1001570.07 | 1001570.07 | 429071.83 | Non Functional | 233.4% | 400 | 215 | 2015-09-01
201501 | 050.38897 | PRP.2738.W HODGENVILL-McCULLE | 2014-10-01 | 2015-02-28 | 100% | 190161.96 | 190161.96 | 210266.02 | Non Functional | 90.44% | 335 | 150 | 2015-09-01
201501 | 050.38903 | PRP.2735.Glasgow.E. Main St | 2014-10-01 | 2015-05-30 | 100% | 216264.06 | 346825.84 | 363011.29 | Non Functional | 95.54% | 335 | 241 | 2015-09-01
201501 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201501 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201501 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201501 | 050.38964 | 2739.ERX FOR SHELBYVILLE | 2014-10-20 | 2015-06-28 | 100% | 16264.25 | 16264.25 | 19456.41 | Non Functional | 83.59% | 316 | 251 | 2015-09-01
201501 | 050.38968 | PRP.2734.Bristow Rd. Replc | 2014-10-01 | 2015-05-30 | 100% | 135278.75 | 135278.75 | 77763.54 | Non Functional | 174% | 335 | 241 | 2015-09-01
201501 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201501 | 050.38970 | 050.2636WhisperingMeadows II | 2014-10-20 | 2015-01-28 | 100% | 5468.51 | 5468.51 | 4930.96 | Non Functional | 110.9% | 316 | 100 | 2015-09-01
201501 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201501 | 050.39035 | 2602.KY.Laptop.Replc.FY15 | 2014-10-21 | 2015-07-31 | 100% | 42143.5 | 42143.5 | 29769.7 | Non Functional | 141.6% | 315 | 283 | 2015-09-01
201501 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201501 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201501 | 050.39098 | 050.2637.Park Ave Relocate | 2014-10-30 | 2015-02-28 | 100% | 2856.57 | 2856.57 | 8726.84 | Non Functional | 32.73% | 306 | 121 | 2015-09-01
201501 | 050.39099 | 050.2637.Key Dr Rev Ext | 2014-11-01 | 2015-02-27 | 100% | 1069 | 1069 | 4259.16 | Non Functional | 25.1% | 304 | 118 | 2015-09-01
201501 | 050.39101 | 050.2637.Lakes of Paducah | 2014-11-01 | 2015-02-27 | 100% | 6696.85 | 6696.85 | -1950.16 | Non Functional | -343.4% | 304 | 118 | 2015-09-01
201501 | 050.39106 | 050.2637.Krebs Sta Rd Ext | 2014-12-01 | 2015-02-27 | 100% | 2084.16 | 2084.16 | 3370.99 | Non Functional | 61.83% | 274 | 88 | 2015-09-01
201501 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201501 | 050.39190 | 2737.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 56185.08 | 56185.08 | 44380.4 | Non Functional | 126.6% | 342 | 402 | 2015-09-01
201501 | 050.39194 | 2737.INTERIOR RENOVATION 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 30000 | 30000 | 40489.38 | Non Functional | 74.09% | 342 | 402 | 2015-09-01
201501 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201501 | 050.39258 | 2739.CLOVERBROOK SEC 9-PH 2 | 2014-11-15 | 2015-03-01 | 100% | 6317.51 | 6317.51 | 14157.41 | Non Functional | 44.62% | 290 | 106 | 2015-09-01
201501 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201501 | 050.39294 | PRP.2734.Church & Nugent St. | 2014-11-30 | 2015-06-30 | 100% | 187511.1 | 187511.1 | 132382.84 | Non Functional | 141.6% | 275 | 212 | 2015-09-01
201501 | 050.39297 | 2739.HERITAGE PARK 2014 | 2014-11-15 | 2015-03-01 | 100% | 21360.7 | 21360.7 | 12990.21 | Non Functional | 164.4% | 290 | 106 | 2015-09-01
201501 | 050.39314 | 050.2637.Ridge Rd Ext | 2015-01-01 | 2015-02-28 | 100% | 3138.03 | 27610.13 | 25052.93 | Non Functional | 110.2% | 243 | 58 | 2015-09-01
201501 | 050.39371 | Madisonville Equipment | 2015-01-01 | 2015-03-31 | 100% | 49528.08 | 49528.08 | 50311.92 | Non Functional | 98.44% | 243 | 89 | 2015-09-01
201501 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201501 | 050.39373 | 2612.RTU Upgrades.KY.15 | 2014-12-04 | 2015-03-31 | 100% | 43420.04 | 43420.04 | 26563.14 | Non Functional | 163.5% | 271 | 117 | 2015-09-01
201501 | 050.39376 | 2612.Comm&Indus Meters.KY.15 | 2015-02-01 | 2015-07-28 | 100% | 14453.63 | 14453.63 | 14253.58 | Non Functional | 101.4% | 212 | 177 | 2015-09-01
201501 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201501 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201501 | 050.39399 | 050.2637.H C Mathis Ext | 2014-12-08 | 2015-02-28 | 100% | 1865.07 | 1865.07 | 8301.39 | Non Functional | 22.47% | 267 | 82 | 2015-09-01
201501 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201501 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201501 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201501 | 050.39436 | 050.2638.Ken Tex Rd Ext | 2014-11-17 | 2015-02-27 | 100% | 6937.24 | 6937.24 | 1734.66 | Non Functional | 399.9% | 288 | 102 | 2015-09-01
201501 | 050.39474 | PRP.2636.Walnut St.Rpl | 2014-12-10 | 2015-04-30 | 100% | 38007.74 | 38007.74 | 35369.57 | Non Functional | 107.5% | 265 | 141 | 2015-09-01
201501 | 050.39478 | 050.2734.EaglestoneReloc.B.G. | 2014-12-16 | 2015-02-18 | 100% | 7088.5 | 7088.5 | 5536.12 | Non Functional | 128% | 259 | 64 | 2015-09-01
201501 | 050.39482 | Mayfield Equipment | 2014-12-17 | 2015-05-30 | 100% | 40075.12 | 40075.12 | 44323.22 | Non Functional | 90.42% | 258 | 164 | 2015-09-01
201501 | 050.39531 | PRP.2735.HC Woodlawn | 2015-02-01 | 2015-09-30 | 87.97% | 490994.76 | 490994.76 | 424459.67 | Non Functional | 115.7% | 212 | 241 | 2015-09-01
201501 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201501 | 050.39546 | 050.2637.Fisher Blvd Ext | 2015-01-26 | 2015-02-27 | 100% | 2572.83 | 20715.76 | 19532.2 | Non Functional | 106.1% | 218 | 32 | 2015-09-01
201501 | 050.39549 | 050.2637.Royal Park Dr 3 | 2015-02-09 | 2015-03-31 | 100% | 3008.7 | 15028.27 | 14857.87 | Non Functional | 101.1% | 204 | 50 | 2015-09-01
201501 | 050.39552 | 050.2637.Lakewood Villas - 1 | 2015-02-16 | 2015-03-31 | 100% | 2897.73 | 2897.73 | 13014.89 | Non Functional | 22.26% | 197 | 43 | 2015-09-01
201501 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201501 | 050.39584 | PRP.2734.Vine St | 2015-01-15 | 2015-08-30 | 100% | 48442.09 | 48442.09 | 42459.91 | Non Functional | 114.1% | 229 | 227 | 2015-09-01
201501 | 050.39589 | 050.2734.North-South Replc | 2015-01-19 | 407336 | 0.06159% | 12126.26 | 12126.26 | 3612.69 | Non Functional | 335.7% | 225 | 365313 | 2015-09-01
201501 | 050.39614 | PRP.2637.Monroe St | 2015-01-25 | 2015-03-30 | 100% | 22703.7 | 22703.7 | 31735.9 | Non Functional | 71.54% | 219 | 64 | 2015-09-01
201501 | 050.39661 | 050.2636.Worthington Rd. Ext. | 2015-01-19 | 2015-03-30 | 100% | 2955.4 | 2955.4 | 2805.46 | Non Functional | 105.3% | 225 | 70 | 2015-09-01
201501 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201502 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201502 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201502 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201502 | 050.36250 | Building Cost, Paducah Office | 2013-10-01 | 2013-11-30 | 100% | 0 | 0 | 0 | Non Functional | 0% | 700 | 60 | 2015-09-01
201502 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201502 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201502 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201502 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201502 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201502 | 050.37745 | 2636.WMR.Sensus Endpoints | 2014-07-01 | 2015-06-30 | 100% | 1586909.8 | 1586909.8 | 1716953.26 | Non Functional | 92.43% | 427 | 364 | 2015-09-01
201502 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201502 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201502 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201502 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201502 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201502 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201502 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201502 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201502 | 050.38415 | PRP.2734.Riverview & College | 2014-07-28 | 2015-02-28 | 100% | 1001570.07 | 1001570.07 | 429071.83 | Non Functional | 233.4% | 400 | 215 | 2015-09-01
201502 | 050.38897 | PRP.2738.W HODGENVILL-McCULLE | 2014-10-01 | 2015-02-28 | 100% | 190161.96 | 190161.96 | 210266.02 | Non Functional | 90.44% | 335 | 150 | 2015-09-01
201502 | 050.38903 | PRP.2735.Glasgow.E. Main St | 2014-10-01 | 2015-05-30 | 100% | 216264.06 | 346825.84 | 363011.29 | Non Functional | 95.54% | 335 | 241 | 2015-09-01
201502 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201502 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201502 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201502 | 050.38964 | 2739.ERX FOR SHELBYVILLE | 2014-10-20 | 2015-06-28 | 100% | 16264.25 | 16264.25 | 19456.41 | Non Functional | 83.59% | 316 | 251 | 2015-09-01
201502 | 050.38968 | PRP.2734.Bristow Rd. Replc | 2014-10-01 | 2015-05-30 | 100% | 135278.75 | 135278.75 | 77763.54 | Non Functional | 174% | 335 | 241 | 2015-09-01
201502 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201502 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201502 | 050.39035 | 2602.KY.Laptop.Replc.FY15 | 2014-10-21 | 2015-07-31 | 100% | 42143.5 | 42143.5 | 29769.7 | Non Functional | 141.6% | 315 | 283 | 2015-09-01
201502 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201502 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201502 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201502 | 050.39190 | 2737.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 56185.08 | 56185.08 | 44380.4 | Non Functional | 126.6% | 342 | 402 | 2015-09-01
201502 | 050.39194 | 2737.INTERIOR RENOVATION 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 30000 | 30000 | 40489.38 | Non Functional | 74.09% | 342 | 402 | 2015-09-01
201502 | 050.39195 | 2737.BUILD ADD-TRUCK BAY 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 62000 | 62000 | 108429.09 | Non Functional | 57.18% | 342 | 402 | 2015-09-01
201502 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201502 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201502 | 050.39294 | PRP.2734.Church & Nugent St. | 2014-11-30 | 2015-06-30 | 100% | 187511.1 | 187511.1 | 132382.84 | Non Functional | 141.6% | 275 | 212 | 2015-09-01
201502 | 050.39366 | PRP.2734.Russell W.9th St. | 2014-12-01 | 2015-08-30 | 100% | 345134.63 | 345134.63 | 317771.71 | Non Functional | 108.6% | 274 | 272 | 2015-09-01
201502 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201502 | 050.39373 | 2612.RTU Upgrades.KY.15 | 2014-12-04 | 2015-03-31 | 100% | 43420.04 | 43420.04 | 26563.14 | Non Functional | 163.5% | 271 | 117 | 2015-09-01
201502 | 050.39376 | 2612.Comm&Indus Meters.KY.15 | 2015-02-01 | 2015-07-28 | 100% | 14453.63 | 14453.63 | 14253.58 | Non Functional | 101.4% | 212 | 177 | 2015-09-01
201502 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201502 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201502 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201502 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201502 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201502 | 050.39474 | PRP.2636.Walnut St.Rpl | 2014-12-10 | 2015-04-30 | 100% | 38007.74 | 38007.74 | 35369.57 | Non Functional | 107.5% | 265 | 141 | 2015-09-01
201502 | 050.39482 | Mayfield Equipment | 2014-12-17 | 2015-05-30 | 100% | 40075.12 | 40075.12 | 44323.22 | Non Functional | 90.42% | 258 | 164 | 2015-09-01
201502 | 050.39492 | Paducah Equipment | 2014-12-19 | 2015-07-31 | 100% | 39942 | 39942 | 49686.41 | Non Functional | 80.39% | 256 | 224 | 2015-09-01
201502 | 050.39531 | PRP.2735.HC Woodlawn | 2015-02-01 | 2015-09-30 | 87.97% | 490994.76 | 490994.76 | 424459.67 | Non Functional | 115.7% | 212 | 241 | 2015-09-01
201502 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201502 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201502 | 050.39584 | PRP.2734.Vine St | 2015-01-15 | 2015-08-30 | 100% | 48442.09 | 48442.09 | 42459.91 | Non Functional | 114.1% | 229 | 227 | 2015-09-01
201502 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201502 | 050.39623 | PRP.2738.Legion Park Penick | 2015-02-15 | 2015-07-30 | 100% | 306532.41 | 306532.41 | 180371.28 | Non Functional | 169.9% | 198 | 165 | 2015-09-01
201502 | 050.39647 | 2602.ITRON.Replacement.FY15 | 2015-02-01 | 2015-06-30 | 100% | 16857.4 | 16857.4 | 17004.97 | Non Functional | 99.13% | 212 | 149 | 2015-09-01
201502 | 050.39660 | 050.2636.Celebration Circle | 2015-01-12 | 2015-07-01 | 100% | 16810.46 | 16810.46 | 9846.65 | Non Functional | 170.7% | 232 | 170 | 2015-09-01
201502 | 050.39664 | 050.2609.6 Well Head Replc.15 | 2015-02-02 | 2015-09-28 | 88.66% | 931672.82 | 931672.82 | 780477.32 | Non Functional | 119.4% | 211 | 238 | 2015-09-01
201502 | 050.39686 | PRP.2634.Main St Sebree | 2015-01-27 | 2015-07-30 | 100% | 57620.33 | 57620.33 | 46632.88 | Non Functional | 123.6% | 217 | 184 | 2015-09-01
201502 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201502 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201502 | 050.39776 | 050.2634.Grapevine Rd Ext | 2015-02-09 | 2015-05-08 | 100% | 3119.38 | 3119.38 | 962.22 | Non Functional | 324.2% | 204 | 88 | 2015-09-01
201502 | 050.39801 | 2609.Storage.Equipment.FY15 | 2015-02-02 | 2015-07-31 | 100% | 21302.4 | 21302.4 | 28210.5 | Non Functional | 75.51% | 211 | 179 | 2015-09-01
201502 | 050.39824 | 2738.REYNOLDS RD 2015 | 2015-02-15 | 2015-04-15 | 100% | 3770.82 | 3770.82 | 1342.32 | Non Functional | 280.9% | 198 | 59 | 2015-09-01
201502 | 050.39898 | 050.2634.Mahr Park Main Ext | 2015-04-01 | 2015-04-30 | 100% | 3560.19 | 3560.19 | 4062.4 | Non Functional | 87.64% | 153 | 29 | 2015-09-01
201502 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201503 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201503 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201503 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201503 | 050.36250 | Building Cost, Paducah Office | 2013-10-01 | 2013-11-30 | 100% | 0 | 0 | 0 | Non Functional | 0% | 700 | 60 | 2015-09-01
201503 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201503 | 050.36387 | PRP.2734.BG-Coll-10th to 13th | 2013-10-01 | 2015-03-31 | 100% | 247075.12 | 247075.12 | 679605.69 | Non Functional | 36.36% | 700 | 546 | 2015-09-01
201503 | 050.36522 | PRP.2636.PARRISH AVE NORTH | 2013-10-09 | 2015-03-30 | 100% | 1178822.63 | 1178822.63 | 1163769 | Non Functional | 101.3% | 692 | 537 | 2015-09-01
201503 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201503 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201503 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201503 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201503 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201503 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201503 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201503 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201503 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201503 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201503 | 050.38897 | PRP.2738.W HODGENVILL-McCULLE | 2014-10-01 | 2015-02-28 | 100% | 190161.96 | 190161.96 | 210266.02 | Non Functional | 90.44% | 335 | 150 | 2015-09-01
201503 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201503 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201503 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201503 | 050.38964 | 2739.ERX FOR SHELBYVILLE | 2014-10-20 | 2015-06-28 | 100% | 16264.25 | 16264.25 | 19456.41 | Non Functional | 83.59% | 316 | 251 | 2015-09-01
201503 | 050.38968 | PRP.2734.Bristow Rd. Replc | 2014-10-01 | 2015-05-30 | 100% | 135278.75 | 135278.75 | 77763.54 | Non Functional | 174% | 335 | 241 | 2015-09-01
201503 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201503 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201503 | 050.39035 | 2602.KY.Laptop.Replc.FY15 | 2014-10-21 | 2015-07-31 | 100% | 42143.5 | 42143.5 | 29769.7 | Non Functional | 141.6% | 315 | 283 | 2015-09-01
201503 | 050.39036 | 2602.KY.MDT.Replac.FY15 | 2014-10-21 | 2015-06-30 | 100% | 120410 | 120410 | 120230.51 | Non Functional | 100.1% | 315 | 252 | 2015-09-01
201503 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201503 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201503 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201503 | 050.39190 | 2737.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 56185.08 | 56185.08 | 44380.4 | Non Functional | 126.6% | 342 | 402 | 2015-09-01
201503 | 050.39194 | 2737.INTERIOR RENOVATION 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 30000 | 30000 | 40489.38 | Non Functional | 74.09% | 342 | 402 | 2015-09-01
201503 | 050.39195 | 2737.BUILD ADD-TRUCK BAY 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 62000 | 62000 | 108429.09 | Non Functional | 57.18% | 342 | 402 | 2015-09-01
201503 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201503 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201503 | 050.39294 | PRP.2734.Church & Nugent St. | 2014-11-30 | 2015-06-30 | 100% | 187511.1 | 187511.1 | 132382.84 | Non Functional | 141.6% | 275 | 212 | 2015-09-01
201503 | 050.39366 | PRP.2734.Russell W.9th St. | 2014-12-01 | 2015-08-30 | 100% | 345134.63 | 345134.63 | 317771.71 | Non Functional | 108.6% | 274 | 272 | 2015-09-01
201503 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201503 | 050.39373 | 2612.RTU Upgrades.KY.15 | 2014-12-04 | 2015-03-31 | 100% | 43420.04 | 43420.04 | 26563.14 | Non Functional | 163.5% | 271 | 117 | 2015-09-01
201503 | 050.39376 | 2612.Comm&Indus Meters.KY.15 | 2015-02-01 | 2015-07-28 | 100% | 14453.63 | 14453.63 | 14253.58 | Non Functional | 101.4% | 212 | 177 | 2015-09-01
201503 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201503 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201503 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201503 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201503 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201503 | 050.39482 | Mayfield Equipment | 2014-12-17 | 2015-05-30 | 100% | 40075.12 | 40075.12 | 44323.22 | Non Functional | 90.42% | 258 | 164 | 2015-09-01
201503 | 050.39492 | Paducah Equipment | 2014-12-19 | 2015-07-31 | 100% | 39942 | 39942 | 49686.41 | Non Functional | 80.39% | 256 | 224 | 2015-09-01
201503 | 050.39531 | PRP.2735.HC Woodlawn | 2015-02-01 | 2015-09-30 | 87.97% | 490994.76 | 490994.76 | 424459.67 | Non Functional | 115.7% | 212 | 241 | 2015-09-01
201503 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201503 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201503 | 050.39584 | PRP.2734.Vine St | 2015-01-15 | 2015-08-30 | 100% | 48442.09 | 48442.09 | 42459.91 | Non Functional | 114.1% | 229 | 227 | 2015-09-01
201503 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201503 | 050.39623 | PRP.2738.Legion Park Penick | 2015-02-15 | 2015-07-30 | 100% | 306532.41 | 306532.41 | 180371.28 | Non Functional | 169.9% | 198 | 165 | 2015-09-01
201503 | 050.39647 | 2602.ITRON.Replacement.FY15 | 2015-02-01 | 2015-06-30 | 100% | 16857.4 | 16857.4 | 17004.97 | Non Functional | 99.13% | 212 | 149 | 2015-09-01
201503 | 050.39660 | 050.2636.Celebration Circle | 2015-01-12 | 2015-07-01 | 100% | 16810.46 | 16810.46 | 9846.65 | Non Functional | 170.7% | 232 | 170 | 2015-09-01
201503 | 050.39664 | 050.2609.6 Well Head Replc.15 | 2015-02-02 | 2015-09-28 | 88.66% | 931672.82 | 931672.82 | 780477.32 | Non Functional | 119.4% | 211 | 238 | 2015-09-01
201503 | 050.39686 | PRP.2634.Main St Sebree | 2015-01-27 | 2015-07-30 | 100% | 57620.33 | 57620.33 | 46632.88 | Non Functional | 123.6% | 217 | 184 | 2015-09-01
201503 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201503 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201503 | 050.39776 | 050.2634.Grapevine Rd Ext | 2015-02-09 | 2015-05-08 | 100% | 3119.38 | 3119.38 | 962.22 | Non Functional | 324.2% | 204 | 88 | 2015-09-01
201503 | 050.39784 | PRP.2734.High St. Cabell-14th | 2015-02-01 | 2015-10-30 | 78.23% | 273210.75 | 273210.75 | 153308.96 | Non Functional | 178.2% | 212 | 271 | 2015-09-01
201503 | 050.39801 | 2609.Storage.Equipment.FY15 | 2015-02-02 | 2015-07-31 | 100% | 21302.4 | 21302.4 | 28210.5 | Non Functional | 75.51% | 211 | 179 | 2015-09-01
201503 | 050.39824 | 2738.REYNOLDS RD 2015 | 2015-02-15 | 2015-04-15 | 100% | 3770.82 | 3770.82 | 1342.32 | Non Functional | 280.9% | 198 | 59 | 2015-09-01
201503 | 050.39898 | 050.2634.Mahr Park Main Ext | 2015-04-01 | 2015-04-30 | 100% | 3560.19 | 3560.19 | 4062.4 | Non Functional | 87.64% | 153 | 29 | 2015-09-01
201503 | 050.39906 | 050.2634.Hwy 351 Relocation | 2015-02-23 | 2015-05-08 | 100% | 9549.9 | 9549.9 | 7161.09 | Non Functional | 133.4% | 190 | 74 | 2015-09-01
201503 | 050.39913 | 050.2636.Palomino Pl. Ext. | 2015-02-09 | 2015-06-30 | 100% | 7366.41 | 7366.41 | 6306.91 | Non Functional | 116.8% | 204 | 141 | 2015-09-01
201503 | 050.39930 | 050.2734.McCoy Place II-A | 2015-02-05 | 2015-09-28 | 88.51% | 31427.89 | 31427.89 | 28704.87 | Non Functional | 109.5% | 208 | 235 | 2015-09-01
201503 | 050.39996 | 2739.DIAGEO PHASE 1 2015 | 2015-03-01 | 2015-09-30 | 86.38% | 179870.01 | 179870.01 | -455893.68 | Non Functional | -39.45% | 184 | 213 | 2015-09-01
201503 | 050.40009 | 050.2636.EByersRegSta | 2015-03-02 | 2015-07-30 | 100% | 30507.85 | 30507.85 | 47382.24 | Non Functional | 64.39% | 183 | 150 | 2015-09-01
201503 | 050.40010 | 050.2636.UnionStRelocHartford | 2015-03-02 | 2015-06-30 | 100% | 28075.76 | 28075.76 | 11978.89 | Non Functional | 234.4% | 183 | 120 | 2015-09-01
201503 | 050.40023 | PRP.2734.Hwy 31W | 2015-03-09 | 2015-06-30 | 100% | 34516.3 | 34516.3 | 50806.42 | Non Functional | 67.94% | 176 | 113 | 2015-09-01
201503 | 050.40035 | 050.2734.Technology6inchPE | 2015-02-06 | 2015-09-28 | 88.46% | 32269.77 | 32269.77 | -9865.11 | Non Functional | -327.1% | 207 | 234 | 2015-09-01
201503 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-03-25 | -77.59% | 13697.21 | 13697.21 | 2365.26 | Non Functional | 579.1% | -90 | 116 | 2015-09-01
201503 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201504 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201504 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201504 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201504 | 050.36250 | Building Cost, Paducah Office | 2013-10-01 | 2013-11-30 | 100% | 0 | 0 | 0 | Non Functional | 0% | 700 | 60 | 2015-09-01
201504 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201504 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201504 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201504 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201504 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201504 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201504 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201504 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201504 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201504 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201504 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201504 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201504 | 050.38935 | PRP.2735.HC Dale Heights_ | 2014-10-01 | 2015-04-30 | 100% | 218909.64 | 218909.64 | 183637.23 | Non Functional | 119.2% | 335 | 211 | 2015-09-01
201504 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201504 | 050.38964 | 2739.ERX FOR SHELBYVILLE | 2014-10-20 | 2015-06-28 | 100% | 16264.25 | 16264.25 | 19456.41 | Non Functional | 83.59% | 316 | 251 | 2015-09-01
201504 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201504 | 050.39034 | 2602.KY.Desktop.Repl.FY15 | 2014-09-22 | 2015-06-30 | 100% | 33714.8 | 33714.8 | 43167.84 | Non Functional | 78.1% | 344 | 281 | 2015-09-01
201504 | 050.39035 | 2602.KY.Laptop.Replc.FY15 | 2014-10-21 | 2015-07-31 | 100% | 42143.5 | 42143.5 | 29769.7 | Non Functional | 141.6% | 315 | 283 | 2015-09-01
201504 | 050.39036 | 2602.KY.MDT.Replac.FY15 | 2014-10-21 | 2015-06-30 | 100% | 120410 | 120410 | 120230.51 | Non Functional | 100.1% | 315 | 252 | 2015-09-01
201504 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201504 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201504 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201504 | 050.39190 | 2737.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 56185.08 | 56185.08 | 44380.4 | Non Functional | 126.6% | 342 | 402 | 2015-09-01
201504 | 050.39195 | 2737.BUILD ADD-TRUCK BAY 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 62000 | 62000 | 108429.09 | Non Functional | 57.18% | 342 | 402 | 2015-09-01
201504 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201504 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201504 | 050.39294 | PRP.2734.Church & Nugent St. | 2014-11-30 | 2015-06-30 | 100% | 187511.1 | 187511.1 | 132382.84 | Non Functional | 141.6% | 275 | 212 | 2015-09-01
201504 | 050.39366 | PRP.2734.Russell W.9th St. | 2014-12-01 | 2015-08-30 | 100% | 345134.63 | 345134.63 | 317771.71 | Non Functional | 108.6% | 274 | 272 | 2015-09-01
201504 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201504 | 050.39373 | 2612.RTU Upgrades.KY.15 | 2014-12-04 | 2015-03-31 | 100% | 43420.04 | 43420.04 | 26563.14 | Non Functional | 163.5% | 271 | 117 | 2015-09-01
201504 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201504 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201504 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201504 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201504 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201504 | 050.39482 | Mayfield Equipment | 2014-12-17 | 2015-05-30 | 100% | 40075.12 | 40075.12 | 44323.22 | Non Functional | 90.42% | 258 | 164 | 2015-09-01
201504 | 050.39492 | Paducah Equipment | 2014-12-19 | 2015-07-31 | 100% | 39942 | 39942 | 49686.41 | Non Functional | 80.39% | 256 | 224 | 2015-09-01
201504 | 050.39531 | PRP.2735.HC Woodlawn | 2015-02-01 | 2015-09-30 | 87.97% | 490994.76 | 490994.76 | 424459.67 | Non Functional | 115.7% | 212 | 241 | 2015-09-01
201504 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201504 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201504 | 050.39584 | PRP.2734.Vine St | 2015-01-15 | 2015-08-30 | 100% | 48442.09 | 48442.09 | 42459.91 | Non Functional | 114.1% | 229 | 227 | 2015-09-01
201504 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201504 | 050.39623 | PRP.2738.Legion Park Penick | 2015-02-15 | 2015-07-30 | 100% | 306532.41 | 306532.41 | 180371.28 | Non Functional | 169.9% | 198 | 165 | 2015-09-01
201504 | 050.39647 | 2602.ITRON.Replacement.FY15 | 2015-02-01 | 2015-06-30 | 100% | 16857.4 | 16857.4 | 17004.97 | Non Functional | 99.13% | 212 | 149 | 2015-09-01
201504 | 050.39660 | 050.2636.Celebration Circle | 2015-01-12 | 2015-07-01 | 100% | 16810.46 | 16810.46 | 9846.65 | Non Functional | 170.7% | 232 | 170 | 2015-09-01
201504 | 050.39664 | 050.2609.6 Well Head Replc.15 | 2015-02-02 | 2015-09-28 | 88.66% | 931672.82 | 931672.82 | 780477.32 | Non Functional | 119.4% | 211 | 238 | 2015-09-01
201504 | 050.39677 | 050.2734.Mics Equipment - B.G. | 2015-02-02 | 2015-09-28 | 88.66% | 73440.02 | 73440.02 | 70403.64 | Non Functional | 104.3% | 211 | 238 | 2015-09-01
201504 | 050.39686 | PRP.2634.Main St Sebree | 2015-01-27 | 2015-07-30 | 100% | 57620.33 | 57620.33 | 46632.88 | Non Functional | 123.6% | 217 | 184 | 2015-09-01
201504 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201504 | 050.39729 | 2738.NEWCOMB.MEADOW CRK 2015 | 2015-01-01 | 2015-09-01 | 100% | 37189.37 | 37189.37 | 22417.16 | Non Functional | 165.9% | 243 | 243 | 2015-09-01
201504 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201504 | 050.39776 | 050.2634.Grapevine Rd Ext | 2015-02-09 | 2015-05-08 | 100% | 3119.38 | 3119.38 | 962.22 | Non Functional | 324.2% | 204 | 88 | 2015-09-01
201504 | 050.39784 | PRP.2734.High St. Cabell-14th | 2015-02-01 | 2015-10-30 | 78.23% | 273210.75 | 273210.75 | 153308.96 | Non Functional | 178.2% | 212 | 271 | 2015-09-01
201504 | 050.39801 | 2609.Storage.Equipment.FY15 | 2015-02-02 | 2015-07-31 | 100% | 21302.4 | 21302.4 | 28210.5 | Non Functional | 75.51% | 211 | 179 | 2015-09-01
201504 | 050.39824 | 2738.REYNOLDS RD 2015 | 2015-02-15 | 2015-04-15 | 100% | 3770.82 | 3770.82 | 1342.32 | Non Functional | 280.9% | 198 | 59 | 2015-09-01
201504 | 050.39858 | 050.2734.BrennerSt.StationRep | 2015-02-13 | 2015-09-28 | 88.11% | 39193.59 | 39193.59 | 12517.52 | Non Functional | 313.1% | 200 | 227 | 2015-09-01
201504 | 050.39898 | 050.2634.Mahr Park Main Ext | 2015-04-01 | 2015-04-30 | 100% | 3560.19 | 3560.19 | 4062.4 | Non Functional | 87.64% | 153 | 29 | 2015-09-01
201504 | 050.39906 | 050.2634.Hwy 351 Relocation | 2015-02-23 | 2015-05-08 | 100% | 9549.9 | 9549.9 | 7161.09 | Non Functional | 133.4% | 190 | 74 | 2015-09-01
201504 | 050.39913 | 050.2636.Palomino Pl. Ext. | 2015-02-09 | 2015-06-30 | 100% | 7366.41 | 7366.41 | 6306.91 | Non Functional | 116.8% | 204 | 141 | 2015-09-01
201504 | 050.39930 | 050.2734.McCoy Place II-A | 2015-02-05 | 2015-09-28 | 88.51% | 31427.89 | 31427.89 | 28704.87 | Non Functional | 109.5% | 208 | 235 | 2015-09-01
201504 | 050.39996 | 2739.DIAGEO PHASE 1 2015 | 2015-03-01 | 2015-09-30 | 86.38% | 179870.01 | 179870.01 | -455893.68 | Non Functional | -39.45% | 184 | 213 | 2015-09-01
201504 | 050.40009 | 050.2636.EByersRegSta | 2015-03-02 | 2015-07-30 | 100% | 30507.85 | 30507.85 | 47382.24 | Non Functional | 64.39% | 183 | 150 | 2015-09-01
201504 | 050.40010 | 050.2636.UnionStRelocHartford | 2015-03-02 | 2015-06-30 | 100% | 28075.76 | 28075.76 | 11978.89 | Non Functional | 234.4% | 183 | 120 | 2015-09-01
201504 | 050.40023 | PRP.2734.Hwy 31W | 2015-03-09 | 2015-06-30 | 100% | 34516.3 | 34516.3 | 50806.42 | Non Functional | 67.94% | 176 | 113 | 2015-09-01
201504 | 050.40035 | 050.2734.Technology6inchPE | 2015-02-06 | 2015-09-28 | 88.46% | 32269.77 | 32269.77 | -9865.11 | Non Functional | -327.1% | 207 | 234 | 2015-09-01
201504 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-03-25 | -77.59% | 13697.21 | 13697.21 | 2365.26 | Non Functional | 579.1% | -90 | 116 | 2015-09-01
201504 | 050.40044 | 2738.GRE.WILLIAM DIAL RD 15 | 2015-04-01 | 2015-07-01 | 100% | 24490.86 | 24490.86 | 21104.43 | Non Functional | 116% | 153 | 91 | 2015-09-01
201504 | 050.40112 | 050.2636.Fiddlesticks Phase 3 | 2015-04-02 | 2015-06-30 | 100% | 7508.77 | 7508.77 | 5334.78 | Non Functional | 140.8% | 152 | 89 | 2015-09-01
201504 | 050.40132 | 050.2637.USEC.MeterSet.FY15 | 2015-05-01 | 2015-08-31 | 100% | 294000.15 | 294000.15 | -64625.11 | Non Functional | -454.9% | 123 | 122 | 2015-09-01
201504 | 050.40153 | 050.2736.Commerce Ct Ext | 2015-05-01 | 2015-08-30 | 100% | 10375.37 | 10375.37 | 6349.38 | Non Functional | 163.4% | 123 | 121 | 2015-09-01
201504 | 050.40218 | PRP.2735.East Back MUN. | 2015-05-01 | 2015-09-30 | 80.92% | 208562.05 | 208562.05 | 70989.21 | Non Functional | 293.8% | 123 | 152 | 2015-09-01
201504 | 050.40270 | 050.2734.Champion Pet Foods | 2015-04-20 | 2015-11-30 | 59.82% | 876504.36 | 876504.36 | -392856.35 | Non Functional | -223.1% | 134 | 224 | 2015-09-01
201504 | 050.40271 | 050.2637.Ohio Ct Main Ext | 2015-05-01 | 2015-09-28 | 82% | 1283.43 | 1283.43 | 954.97 | Non Functional | 134.4% | 123 | 150 | 2015-09-01
201504 | 050.40277 | 050.2637.Ky Ave Replacements | 2015-03-01 | 2015-09-28 | 87.2% | 27907.58 | 56401.89 | 58219.93 | Non Functional | 96.88% | 184 | 211 | 2015-09-01
201504 | 050.40290 | 050.2637.Fantasy Ln Ext | 2015-04-01 | 2015-11-30 | 62.96% | 1293.7 | 1293.7 | -123.2 | Non Functional | -1050% | 153 | 243 | 2015-09-01
201504 | 050.40291 | 050.2637.Pecan Dr Rev Ext | 2015-04-06 | 2015-09-28 | 84.57% | 3233.97 | 3233.97 | -72.38 | Non Functional | -4468% | 148 | 175 | 2015-09-01
201504 | 050.40292 | 050.2637.Bruce Ave Rev Ext | 2015-07-01 | 2015-07-30 | 100% | 2598.6 | 2598.6 | 449.32 | Non Functional | 578.3% | 62 | 29 | 2015-09-01
201504 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201505 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201505 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201505 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201505 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201505 | 050.37137 | 2737.RUSSELL ST ALDYL REPLACE | 2014-04-10 | 2015-04-10 | 100% | 20649.3 | 20649.3 | 15256.31 | Non Functional | 135.3% | 509 | 365 | 2015-09-01
201505 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201505 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201505 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201505 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201505 | 050.37992 | PRP.2635.Marion Westside | 2013-10-17 | 2015-07-15 | 100% | 404045.26 | 404045.26 | 467866.15 | Non Functional | 86.36% | 684 | 636 | 2015-09-01
201505 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201505 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201505 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201505 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201505 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201505 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201505 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201505 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201505 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201505 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201505 | 050.39190 | 2737.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 56185.08 | 56185.08 | 44380.4 | Non Functional | 126.6% | 342 | 402 | 2015-09-01
201505 | 050.39195 | 2737.BUILD ADD-TRUCK BAY 2015 | 2014-09-24 | 2015-10-31 | 85.07% | 62000 | 62000 | 108429.09 | Non Functional | 57.18% | 342 | 402 | 2015-09-01
201505 | 050.39201 | Bon Harbor/ANR RTU.15 | 2014-11-10 | 2015-09-15 | 95.47% | 32766.87 | 32766.87 | 21539.92 | Non Functional | 152.1% | 295 | 309 | 2015-09-01
201505 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201505 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201505 | 050.39294 | PRP.2734.Church & Nugent St. | 2014-11-30 | 2015-06-30 | 100% | 187511.1 | 187511.1 | 132382.84 | Non Functional | 141.6% | 275 | 212 | 2015-09-01
201505 | 050.39366 | PRP.2734.Russell W.9th St. | 2014-12-01 | 2015-08-30 | 100% | 345134.63 | 345134.63 | 317771.71 | Non Functional | 108.6% | 274 | 272 | 2015-09-01
201505 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201505 | 050.39373 | 2612.RTU Upgrades.KY.15 | 2014-12-04 | 2015-03-31 | 100% | 43420.04 | 43420.04 | 26563.14 | Non Functional | 163.5% | 271 | 117 | 2015-09-01
201505 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201505 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201505 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201505 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201505 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201505 | 050.39492 | Paducah Equipment | 2014-12-19 | 2015-07-31 | 100% | 39942 | 39942 | 49686.41 | Non Functional | 80.39% | 256 | 224 | 2015-09-01
201505 | 050.39531 | PRP.2735.HC Woodlawn | 2015-02-01 | 2015-09-30 | 87.97% | 490994.76 | 490994.76 | 424459.67 | Non Functional | 115.7% | 212 | 241 | 2015-09-01
201505 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201505 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201505 | 050.39584 | PRP.2734.Vine St | 2015-01-15 | 2015-08-30 | 100% | 48442.09 | 48442.09 | 42459.91 | Non Functional | 114.1% | 229 | 227 | 2015-09-01
201505 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201505 | 050.39623 | PRP.2738.Legion Park Penick | 2015-02-15 | 2015-07-30 | 100% | 306532.41 | 306532.41 | 180371.28 | Non Functional | 169.9% | 198 | 165 | 2015-09-01
201505 | 050.39647 | 2602.ITRON.Replacement.FY15 | 2015-02-01 | 2015-06-30 | 100% | 16857.4 | 16857.4 | 17004.97 | Non Functional | 99.13% | 212 | 149 | 2015-09-01
201505 | 050.39660 | 050.2636.Celebration Circle | 2015-01-12 | 2015-07-01 | 100% | 16810.46 | 16810.46 | 9846.65 | Non Functional | 170.7% | 232 | 170 | 2015-09-01
201505 | 050.39664 | 050.2609.6 Well Head Replc.15 | 2015-02-02 | 2015-09-28 | 88.66% | 931672.82 | 931672.82 | 780477.32 | Non Functional | 119.4% | 211 | 238 | 2015-09-01
201505 | 050.39677 | 050.2734.Mics Equipment - B.G. | 2015-02-02 | 2015-09-28 | 88.66% | 73440.02 | 73440.02 | 70403.64 | Non Functional | 104.3% | 211 | 238 | 2015-09-01
201505 | 050.39686 | PRP.2634.Main St Sebree | 2015-01-27 | 2015-07-30 | 100% | 57620.33 | 57620.33 | 46632.88 | Non Functional | 123.6% | 217 | 184 | 2015-09-01
201505 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201505 | 050.39729 | 2738.NEWCOMB.MEADOW CRK 2015 | 2015-01-01 | 2015-09-01 | 100% | 37189.37 | 37189.37 | 22417.16 | Non Functional | 165.9% | 243 | 243 | 2015-09-01
201505 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201505 | 050.39784 | PRP.2734.High St. Cabell-14th | 2015-02-01 | 2015-10-30 | 78.23% | 273210.75 | 273210.75 | 153308.96 | Non Functional | 178.2% | 212 | 271 | 2015-09-01
201505 | 050.39801 | 2609.Storage.Equipment.FY15 | 2015-02-02 | 2015-07-31 | 100% | 21302.4 | 21302.4 | 28210.5 | Non Functional | 75.51% | 211 | 179 | 2015-09-01
201505 | 050.39824 | 2738.REYNOLDS RD 2015 | 2015-02-15 | 2015-04-15 | 100% | 3770.82 | 3770.82 | 1342.32 | Non Functional | 280.9% | 198 | 59 | 2015-09-01
201505 | 050.39858 | 050.2734.BrennerSt.StationRep | 2015-02-13 | 2015-09-28 | 88.11% | 39193.59 | 39193.59 | 12517.52 | Non Functional | 313.1% | 200 | 227 | 2015-09-01
201505 | 050.39907 | PRP.2635.Maple St. | 2015-03-20 | 2015-11-30 | 64.71% | 357374.02 | 357374.02 | 98345.98 | Non Functional | 363.4% | 165 | 255 | 2015-09-01
201505 | 050.39911 | 2015 WMR | 2014-09-22 | 2015-10-22 | 87.09% | 32239.71 | 32239.71 | 28310.17 | Non Functional | 113.9% | 344 | 395 | 2015-09-01
201505 | 050.39913 | 050.2636.Palomino Pl. Ext. | 2015-02-09 | 2015-06-30 | 100% | 7366.41 | 7366.41 | 6306.91 | Non Functional | 116.8% | 204 | 141 | 2015-09-01
201505 | 050.39930 | 050.2734.McCoy Place II-A | 2015-02-05 | 2015-09-28 | 88.51% | 31427.89 | 31427.89 | 28704.87 | Non Functional | 109.5% | 208 | 235 | 2015-09-01
201505 | 050.39996 | 2739.DIAGEO PHASE 1 2015 | 2015-03-01 | 2015-09-30 | 86.38% | 179870.01 | 179870.01 | -455893.68 | Non Functional | -39.45% | 184 | 213 | 2015-09-01
201505 | 050.40009 | 050.2636.EByersRegSta | 2015-03-02 | 2015-07-30 | 100% | 30507.85 | 30507.85 | 47382.24 | Non Functional | 64.39% | 183 | 150 | 2015-09-01
201505 | 050.40010 | 050.2636.UnionStRelocHartford | 2015-03-02 | 2015-06-30 | 100% | 28075.76 | 28075.76 | 11978.89 | Non Functional | 234.4% | 183 | 120 | 2015-09-01
201505 | 050.40023 | PRP.2734.Hwy 31W | 2015-03-09 | 2015-06-30 | 100% | 34516.3 | 34516.3 | 50806.42 | Non Functional | 67.94% | 176 | 113 | 2015-09-01
201505 | 050.40035 | 050.2734.Technology6inchPE | 2015-02-06 | 2015-09-28 | 88.46% | 32269.77 | 32269.77 | -9865.11 | Non Functional | -327.1% | 207 | 234 | 2015-09-01
201505 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-03-25 | -77.59% | 13697.21 | 13697.21 | 2365.26 | Non Functional | 579.1% | -90 | 116 | 2015-09-01
201505 | 050.40044 | 2738.GRE.WILLIAM DIAL RD 15 | 2015-04-01 | 2015-07-01 | 100% | 24490.86 | 24490.86 | 21104.43 | Non Functional | 116% | 153 | 91 | 2015-09-01
201505 | 050.40112 | 050.2636.Fiddlesticks Phase 3 | 2015-04-02 | 2015-06-30 | 100% | 7508.77 | 7508.77 | 5334.78 | Non Functional | 140.8% | 152 | 89 | 2015-09-01
201505 | 050.40132 | 050.2637.USEC.MeterSet.FY15 | 2015-05-01 | 2015-08-31 | 100% | 294000.15 | 294000.15 | -64625.11 | Non Functional | -454.9% | 123 | 122 | 2015-09-01
201505 | 050.40153 | 050.2736.Commerce Ct Ext | 2015-05-01 | 2015-08-30 | 100% | 10375.37 | 10375.37 | 6349.38 | Non Functional | 163.4% | 123 | 121 | 2015-09-01
201505 | 050.40218 | PRP.2735.East Back MUN. | 2015-05-01 | 2015-09-30 | 80.92% | 208562.05 | 208562.05 | 70989.21 | Non Functional | 293.8% | 123 | 152 | 2015-09-01
201505 | 050.40270 | 050.2734.Champion Pet Foods | 2015-04-20 | 2015-11-30 | 59.82% | 876504.36 | 876504.36 | -392856.35 | Non Functional | -223.1% | 134 | 224 | 2015-09-01
201505 | 050.40271 | 050.2637.Ohio Ct Main Ext | 2015-05-01 | 2015-09-28 | 82% | 1283.43 | 1283.43 | 954.97 | Non Functional | 134.4% | 123 | 150 | 2015-09-01
201505 | 050.40277 | 050.2637.Ky Ave Replacements | 2015-03-01 | 2015-09-28 | 87.2% | 27907.58 | 56401.89 | 58219.93 | Non Functional | 96.88% | 184 | 211 | 2015-09-01
201505 | 050.40284 | 050.2635.Charleston TB Reloc | 2015-04-06 | 2015-09-28 | 84.57% | 11889.51 | 11889.51 | 18026.79 | Non Functional | 65.95% | 148 | 175 | 2015-09-01
201505 | 050.40290 | 050.2637.Fantasy Ln Ext | 2015-04-01 | 2015-11-30 | 62.96% | 1293.7 | 1293.7 | -123.2 | Non Functional | -1050% | 153 | 243 | 2015-09-01
201505 | 050.40291 | 050.2637.Pecan Dr Rev Ext | 2015-04-06 | 2015-09-28 | 84.57% | 3233.97 | 3233.97 | -72.38 | Non Functional | -4468% | 148 | 175 | 2015-09-01
201505 | 050.40292 | 050.2637.Bruce Ave Rev Ext | 2015-07-01 | 2015-07-30 | 100% | 2598.6 | 2598.6 | 449.32 | Non Functional | 578.3% | 62 | 29 | 2015-09-01
201505 | 050.40375 | 2602.Oboro.Server.Replc.15 | 2015-05-12 | 2015-11-28 | 56% | 27092.25 | 27092.25 | 4604.46 | Non Functional | 588.4% | 112 | 200 | 2015-09-01
201505 | 050.40377 | 2602.KY.Laptop.Purch.FY15.2 | 2015-05-12 | 2015-07-15 | 100% | 4061.92 | 4061.92 | 4170.5 | Non Functional | 97.4% | 112 | 64 | 2015-09-01
201505 | 050.40425 | PRP.2636.River Rd. | 2015-05-15 | 2015-10-30 | 64.88% | 441675.05 | 441675.05 | 166240.28 | Non Functional | 265.7% | 109 | 168 | 2015-09-01
201505 | 050.40434 | 050.2636.Newbolt Rd. Ext | 2015-02-02 | 2015-07-30 | 100% | 4827.24 | 4827.24 | 4817.67 | Non Functional | 100.2% | 211 | 178 | 2015-09-01
201505 | 050.40452 | 050.2638.Graham Dr Ext 2 | 2015-06-01 | 2015-09-28 | 77.31% | 1876.23 | 1876.23 | 1425.53 | Non Functional | 131.6% | 92 | 119 | 2015-09-01
201505 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201506 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201506 | 050.35055 | PRP.Woodburn-Franklin HPD | 2013-08-30 | 2015-09-28 | 96.44% | 4133795.54 | 4133795.54 | 5473654.76 | Non Functional | 75.52% | 732 | 759 | 2015-09-01
201506 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201506 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201506 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201506 | 050.37849 | 2738.GRE.NALLEY-HAYDON 2014 | 2014-06-01 | 2015-07-31 | 100% | 204242.45 | 204242.45 | 194206.18 | Non Functional | 105.2% | 457 | 425 | 2015-09-01
201506 | 050.37880 | 2738.GRN.NALLEY-HAYDON STAT | 2014-08-01 | 2015-08-31 | 100% | 41927.53 | 41927.53 | 12496.35 | Non Functional | 335.5% | 396 | 395 | 2015-09-01
201506 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201506 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201506 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201506 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201506 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201506 | 050.38923 | PRP.2636.E 17 th St Repl | 2014-10-01 | 2015-07-15 | 100% | 213543.57 | 213543.57 | 162100.32 | Non Functional | 131.7% | 335 | 287 | 2015-09-01
201506 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201506 | 050.38969 | 050.2734.BristowMoorman PI | 2014-10-01 | 2015-08-01 | 100% | 212211.47 | 212211.47 | 150321.38 | Non Functional | 141.2% | 335 | 304 | 2015-09-01
201506 | 050.39044 | 2737.JC.W EADES AVE 15 | 2014-12-01 | 2015-08-01 | 100% | 2643.32 | 2643.32 | 294.65 | Non Functional | 897.1% | 274 | 243 | 2015-09-01
201506 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201506 | 050.39171 | 2738.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 26628.03 | 26628.03 | 26991.08 | Non Functional | 98.65% | 342 | 402 | 2015-09-01
201506 | 050.39190 | 2737.2015 EQUIPMENT | 2014-09-24 | 2015-10-31 | 85.07% | 56185.08 | 56185.08 | 44380.4 | Non Functional | 126.6% | 342 | 402 | 2015-09-01
201506 | 050.39201 | Bon Harbor/ANR RTU.15 | 2014-11-10 | 2015-09-15 | 95.47% | 32766.87 | 32766.87 | 21539.92 | Non Functional | 152.1% | 295 | 309 | 2015-09-01
201506 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201506 | 050.39272 | PRP.2636.Coast Guard Ln. | 2014-12-01 | 2015-08-01 | 100% | 37779.19 | 37779.19 | 25420.58 | Non Functional | 148.6% | 274 | 243 | 2015-09-01
201506 | 050.39366 | PRP.2734.Russell W.9th St. | 2014-12-01 | 2015-08-30 | 100% | 345134.63 | 345134.63 | 317771.71 | Non Functional | 108.6% | 274 | 272 | 2015-09-01
201506 | 050.39372 | Princeton Equipment | 2015-01-01 | 2015-07-31 | 100% | 31114.87 | 31114.87 | 29628.29 | Non Functional | 105% | 243 | 211 | 2015-09-01
201506 | 050.39378 | 2612.CorrectorModemUpg.KY.15 | 2015-03-01 | 2015-07-31 | 100% | 19306.16 | 19306.16 | 20918.77 | Non Functional | 92.29% | 184 | 152 | 2015-09-01
201506 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201506 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201506 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201506 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201506 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201506 | 050.39492 | Paducah Equipment | 2014-12-19 | 2015-07-31 | 100% | 39942 | 39942 | 49686.41 | Non Functional | 80.39% | 256 | 224 | 2015-09-01
201506 | 050.39531 | PRP.2735.HC Woodlawn | 2015-02-01 | 2015-09-30 | 87.97% | 490994.76 | 490994.76 | 424459.67 | Non Functional | 115.7% | 212 | 241 | 2015-09-01
201506 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201506 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201506 | 050.39584 | PRP.2734.Vine St | 2015-01-15 | 2015-08-30 | 100% | 48442.09 | 48442.09 | 42459.91 | Non Functional | 114.1% | 229 | 227 | 2015-09-01
201506 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201506 | 050.39623 | PRP.2738.Legion Park Penick | 2015-02-15 | 2015-07-30 | 100% | 306532.41 | 306532.41 | 180371.28 | Non Functional | 169.9% | 198 | 165 | 2015-09-01
201506 | 050.39647 | 2602.ITRON.Replacement.FY15 | 2015-02-01 | 2015-06-30 | 100% | 16857.4 | 16857.4 | 17004.97 | Non Functional | 99.13% | 212 | 149 | 2015-09-01
201506 | 050.39664 | 050.2609.6 Well Head Replc.15 | 2015-02-02 | 2015-09-28 | 88.66% | 931672.82 | 931672.82 | 780477.32 | Non Functional | 119.4% | 211 | 238 | 2015-09-01
201506 | 050.39677 | 050.2734.Mics Equipment - B.G. | 2015-02-02 | 2015-09-28 | 88.66% | 73440.02 | 73440.02 | 70403.64 | Non Functional | 104.3% | 211 | 238 | 2015-09-01
201506 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201506 | 050.39729 | 2738.NEWCOMB.MEADOW CRK 2015 | 2015-01-01 | 2015-09-01 | 100% | 37189.37 | 37189.37 | 22417.16 | Non Functional | 165.9% | 243 | 243 | 2015-09-01
201506 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201506 | 050.39784 | PRP.2734.High St. Cabell-14th | 2015-02-01 | 2015-10-30 | 78.23% | 273210.75 | 273210.75 | 153308.96 | Non Functional | 178.2% | 212 | 271 | 2015-09-01
201506 | 050.39801 | 2609.Storage.Equipment.FY15 | 2015-02-02 | 2015-07-31 | 100% | 21302.4 | 21302.4 | 28210.5 | Non Functional | 75.51% | 211 | 179 | 2015-09-01
201506 | 050.39824 | 2738.REYNOLDS RD 2015 | 2015-02-15 | 2015-04-15 | 100% | 3770.82 | 3770.82 | 1342.32 | Non Functional | 280.9% | 198 | 59 | 2015-09-01
201506 | 050.39858 | 050.2734.BrennerSt.StationRep | 2015-02-13 | 2015-09-28 | 88.11% | 39193.59 | 39193.59 | 12517.52 | Non Functional | 313.1% | 200 | 227 | 2015-09-01
201506 | 050.39907 | PRP.2635.Maple St. | 2015-03-20 | 2015-11-30 | 64.71% | 357374.02 | 357374.02 | 98345.98 | Non Functional | 363.4% | 165 | 255 | 2015-09-01
201506 | 050.39911 | 2015 WMR | 2014-09-22 | 2015-10-22 | 87.09% | 32239.71 | 32239.71 | 28310.17 | Non Functional | 113.9% | 344 | 395 | 2015-09-01
201506 | 050.39930 | 050.2734.McCoy Place II-A | 2015-02-05 | 2015-09-28 | 88.51% | 31427.89 | 31427.89 | 28704.87 | Non Functional | 109.5% | 208 | 235 | 2015-09-01
201506 | 050.39996 | 2739.DIAGEO PHASE 1 2015 | 2015-03-01 | 2015-09-30 | 86.38% | 179870.01 | 179870.01 | -455893.68 | Non Functional | -39.45% | 184 | 213 | 2015-09-01
201506 | 050.40009 | 050.2636.EByersRegSta | 2015-03-02 | 2015-07-30 | 100% | 30507.85 | 30507.85 | 47382.24 | Non Functional | 64.39% | 183 | 150 | 2015-09-01
201506 | 050.40035 | 050.2734.Technology6inchPE | 2015-02-06 | 2015-09-28 | 88.46% | 32269.77 | 32269.77 | -9865.11 | Non Functional | -327.1% | 207 | 234 | 2015-09-01
201506 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-03-25 | -77.59% | 13697.21 | 13697.21 | 2365.26 | Non Functional | 579.1% | -90 | 116 | 2015-09-01
201506 | 050.40044 | 2738.GRE.WILLIAM DIAL RD 15 | 2015-04-01 | 2015-07-01 | 100% | 24490.86 | 24490.86 | 21104.43 | Non Functional | 116% | 153 | 91 | 2015-09-01
201506 | 050.40132 | 050.2637.USEC.MeterSet.FY15 | 2015-05-01 | 2015-08-31 | 100% | 294000.15 | 294000.15 | -64625.11 | Non Functional | -454.9% | 123 | 122 | 2015-09-01
201506 | 050.40153 | 050.2736.Commerce Ct Ext | 2015-05-01 | 2015-08-30 | 100% | 10375.37 | 10375.37 | 6349.38 | Non Functional | 163.4% | 123 | 121 | 2015-09-01
201506 | 050.40218 | PRP.2735.East Back MUN. | 2015-05-01 | 2015-09-30 | 80.92% | 208562.05 | 208562.05 | 70989.21 | Non Functional | 293.8% | 123 | 152 | 2015-09-01
201506 | 050.40232 | PRP.2735.Washington St.MUN | 2015-05-01 | 2015-09-30 | 80.92% | 347110.72 | 347110.72 | 125546.61 | Non Functional | 276.5% | 123 | 152 | 2015-09-01
201506 | 050.40270 | 050.2734.Champion Pet Foods | 2015-04-20 | 2015-11-30 | 59.82% | 876504.36 | 876504.36 | -392856.35 | Non Functional | -223.1% | 134 | 224 | 2015-09-01
201506 | 050.40271 | 050.2637.Ohio Ct Main Ext | 2015-05-01 | 2015-09-28 | 82% | 1283.43 | 1283.43 | 954.97 | Non Functional | 134.4% | 123 | 150 | 2015-09-01
201506 | 050.40277 | 050.2637.Ky Ave Replacements | 2015-03-01 | 2015-09-28 | 87.2% | 27907.58 | 56401.89 | 58219.93 | Non Functional | 96.88% | 184 | 211 | 2015-09-01
201506 | 050.40284 | 050.2635.Charleston TB Reloc | 2015-04-06 | 2015-09-28 | 84.57% | 11889.51 | 11889.51 | 18026.79 | Non Functional | 65.95% | 148 | 175 | 2015-09-01
201506 | 050.40290 | 050.2637.Fantasy Ln Ext | 2015-04-01 | 2015-11-30 | 62.96% | 1293.7 | 1293.7 | -123.2 | Non Functional | -1050% | 153 | 243 | 2015-09-01
201506 | 050.40291 | 050.2637.Pecan Dr Rev Ext | 2015-04-06 | 2015-09-28 | 84.57% | 3233.97 | 3233.97 | -72.38 | Non Functional | -4468% | 148 | 175 | 2015-09-01
201506 | 050.40292 | 050.2637.Bruce Ave Rev Ext | 2015-07-01 | 2015-07-30 | 100% | 2598.6 | 2598.6 | 449.32 | Non Functional | 578.3% | 62 | 29 | 2015-09-01
201506 | 050.40375 | 2602.Oboro.Server.Replc.15 | 2015-05-12 | 2015-11-28 | 56% | 27092.25 | 27092.25 | 4604.46 | Non Functional | 588.4% | 112 | 200 | 2015-09-01
201506 | 050.40377 | 2602.KY.Laptop.Purch.FY15.2 | 2015-05-12 | 2015-07-15 | 100% | 4061.92 | 4061.92 | 4170.5 | Non Functional | 97.4% | 112 | 64 | 2015-09-01
201506 | 050.40425 | PRP.2636.River Rd. | 2015-05-15 | 2015-10-30 | 64.88% | 441675.05 | 441675.05 | 166240.28 | Non Functional | 265.7% | 109 | 168 | 2015-09-01
201506 | 050.40434 | 050.2636.Newbolt Rd. Ext | 2015-02-02 | 2015-07-30 | 100% | 4827.24 | 4827.24 | 4817.67 | Non Functional | 100.2% | 211 | 178 | 2015-09-01
201506 | 050.40452 | 050.2638.Graham Dr Ext 2 | 2015-06-01 | 2015-09-28 | 77.31% | 1876.23 | 1876.23 | 1425.53 | Non Functional | 131.6% | 92 | 119 | 2015-09-01
201506 | 050.40453 | 050.2637.Krebs Sta Rd Ext 3 | 2015-06-01 | 2015-09-28 | 77.31% | 1820.17 | 1820.17 | 520.41 | Non Functional | 349.8% | 92 | 119 | 2015-09-01
201506 | 050.40471 | PRP.2734.Crewdson Ln. | 2015-05-30 | 2016-01-30 | 38.37% | 1065458.52 | 1065458.52 | 305790.63 | Non Functional | 348.4% | 94 | 245 | 2015-09-01
201506 | 050.40488 | 050.2637.Creek Replacements | 2015-06-15 | 2015-07-30 | 100% | 25540.33 | 25540.33 | 3335.57 | Non Functional | 765.7% | 78 | 45 | 2015-09-01
201506 | 050.40489 | 050.2736.Katie Peden Dr Ext | 2015-06-01 | 2015-07-30 | 100% | 12468.95 | 12468.95 | 8206.21 | Non Functional | 151.9% | 92 | 59 | 2015-09-01
201506 | 050.40506 | PRP.2635. H ville St Replace | 2015-05-01 | 2015-07-31 | 100% | 3483.23 | 3483.23 | 3823.94 | Non Functional | 91.09% | 123 | 91 | 2015-09-01
201506 | 050.40532 | 050.2637.Ham Rd Rev Ext | 2015-06-15 | 2015-10-30 | 56.93% | 7785.07 | 7785.07 | -4071.92 | Non Functional | -191.2% | 78 | 137 | 2015-09-01
201506 | 050.40534 | PRP.2637.Madison | 2015-06-10 | 2015-12-22 | 42.56% | 493772.76 | 493772.76 | 412284.83 | Non Functional | 119.8% | 83 | 195 | 2015-09-01
201506 | 050.40556 | 050.2638.Dale Dr Rev Ext | 2015-07-01 | 2015-07-31 | 100% | 2477.78 | 2477.78 | 4480.11 | Non Functional | 55.31% | 62 | 30 | 2015-09-01
201506 | 050.40557 | 050.2634.Versnick Dr Rev Ext | 2015-07-01 | 2015-07-31 | 100% | 2744.34 | 2744.34 | 3673.64 | Non Functional | 74.7% | 62 | 30 | 2015-09-01
201506 | 050.40577 | 050.2638.S 17th St Ext | 2015-07-01 | 2015-07-31 | 100% | 1274.88 | 1274.88 | 3253.21 | Non Functional | 39.19% | 62 | 30 | 2015-09-01
201506 | 050.40615 | 050.2637.CANDLELIGHT EXT 2 | 2015-07-01 | 2015-11-30 | 40.79% | 30795.68 | 30795.68 | 1094.33 | Non Functional | 2814% | 62 | 152 | 2015-09-01
201506 | 050.40693 | 050.2735.TB1Reloc.HorseCave | 2015-06-15 | 2015-11-30 | 46.43% | 265806.85 | 265806.85 | -221805.67 | Non Functional | -119.8% | 78 | 168 | 2015-09-01
201506 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201507 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201507 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201507 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201507 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201507 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201507 | 050.38089 | 050.2734.Boston Pk.Traditions | 2014-06-16 | 2015-06-30 | 100% | 6173.13 | 6173.13 | 1513.49 | Non Functional | 407.9% | 442 | 379 | 2015-09-01
201507 | 050.38277 | 050.2637.Olivet Relocation | 2014-09-02 | 2015-06-30 | 100% | 42402.58 | 42402.58 | 81090.13 | Non Functional | 52.29% | 364 | 301 | 2015-09-01
201507 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201507 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201507 | 050.38950 | PRP.2737.MARIMON-OFFICE-HIGH | 2014-10-01 | 2015-09-28 | 92.54% | 521630.2 | 1212179.37 | 1190799.43 | Non Functional | 101.8% | 335 | 362 | 2015-09-01
201507 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201507 | 050.39201 | Bon Harbor/ANR RTU.15 | 2014-11-10 | 2015-09-15 | 95.47% | 32766.87 | 32766.87 | 21539.92 | Non Functional | 152.1% | 295 | 309 | 2015-09-01
201507 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201507 | 050.39385 | 2739.BRUNERSTOWN RD-TSC RELO | 2014-11-01 | 2015-04-01 | 100% | 33172.6 | 33172.6 | -4792.86 | Non Functional | -692.1% | 304 | 151 | 2015-09-01
201507 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201507 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201507 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201507 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201507 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201507 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201507 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201507 | 050.39664 | 050.2609.6 Well Head Replc.15 | 2015-02-02 | 2015-09-28 | 88.66% | 931672.82 | 931672.82 | 780477.32 | Non Functional | 119.4% | 211 | 238 | 2015-09-01
201507 | 050.39677 | 050.2734.Mics Equipment - B.G. | 2015-02-02 | 2015-09-28 | 88.66% | 73440.02 | 73440.02 | 70403.64 | Non Functional | 104.3% | 211 | 238 | 2015-09-01
201507 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201507 | 050.39729 | 2738.NEWCOMB.MEADOW CRK 2015 | 2015-01-01 | 2015-09-01 | 100% | 37189.37 | 37189.37 | 22417.16 | Non Functional | 165.9% | 243 | 243 | 2015-09-01
201507 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201507 | 050.39784 | PRP.2734.High St. Cabell-14th | 2015-02-01 | 2015-10-30 | 78.23% | 273210.75 | 273210.75 | 153308.96 | Non Functional | 178.2% | 212 | 271 | 2015-09-01
201507 | 050.39824 | 2738.REYNOLDS RD 2015 | 2015-02-15 | 2015-04-15 | 100% | 3770.82 | 3770.82 | 1342.32 | Non Functional | 280.9% | 198 | 59 | 2015-09-01
201507 | 050.39858 | 050.2734.BrennerSt.StationRep | 2015-02-13 | 2015-09-28 | 88.11% | 39193.59 | 39193.59 | 12517.52 | Non Functional | 313.1% | 200 | 227 | 2015-09-01
201507 | 050.39907 | PRP.2635.Maple St. | 2015-03-20 | 2015-11-30 | 64.71% | 357374.02 | 357374.02 | 98345.98 | Non Functional | 363.4% | 165 | 255 | 2015-09-01
201507 | 050.39911 | 2015 WMR | 2014-09-22 | 2015-10-22 | 87.09% | 32239.71 | 32239.71 | 28310.17 | Non Functional | 113.9% | 344 | 395 | 2015-09-01
201507 | 050.39930 | 050.2734.McCoy Place II-A | 2015-02-05 | 2015-09-28 | 88.51% | 31427.89 | 31427.89 | 28704.87 | Non Functional | 109.5% | 208 | 235 | 2015-09-01
201507 | 050.39996 | 2739.DIAGEO PHASE 1 2015 | 2015-03-01 | 2015-09-30 | 86.38% | 179870.01 | 179870.01 | -455893.68 | Non Functional | -39.45% | 184 | 213 | 2015-09-01
201507 | 050.40035 | 050.2734.Technology6inchPE | 2015-02-06 | 2015-09-28 | 88.46% | 32269.77 | 32269.77 | -9865.11 | Non Functional | -327.1% | 207 | 234 | 2015-09-01
201507 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-03-25 | -77.59% | 13697.21 | 13697.21 | 2365.26 | Non Functional | 579.1% | -90 | 116 | 2015-09-01
201507 | 050.40132 | 050.2637.USEC.MeterSet.FY15 | 2015-05-01 | 2015-08-31 | 100% | 294000.15 | 294000.15 | -64625.11 | Non Functional | -454.9% | 123 | 122 | 2015-09-01
201507 | 050.40172 | Bowling Green Office Furniture | 2015-05-01 | 2015-09-28 | 82% | 46599 | 46599 | 29220.41 | Non Functional | 159.5% | 123 | 150 | 2015-09-01
201507 | 050.40218 | PRP.2735.East Back MUN. | 2015-05-01 | 2015-09-30 | 80.92% | 208562.05 | 208562.05 | 70989.21 | Non Functional | 293.8% | 123 | 152 | 2015-09-01
201507 | 050.40232 | PRP.2735.Washington St.MUN | 2015-05-01 | 2015-09-30 | 80.92% | 347110.72 | 347110.72 | 125546.61 | Non Functional | 276.5% | 123 | 152 | 2015-09-01
201507 | 050.40270 | 050.2734.Champion Pet Foods | 2015-04-20 | 2015-11-30 | 59.82% | 876504.36 | 876504.36 | -392856.35 | Non Functional | -223.1% | 134 | 224 | 2015-09-01
201507 | 050.40278 | Calvert Purchase Upgrade | 2014-09-22 | 2016-03-30 | 61.98% | 23946.76 | 23946.76 | 10397.92 | Non Functional | 230.3% | 344 | 555 | 2015-09-01
201507 | 050.40284 | 050.2635.Charleston TB Reloc | 2015-04-06 | 2015-09-28 | 84.57% | 11889.51 | 11889.51 | 18026.79 | Non Functional | 65.95% | 148 | 175 | 2015-09-01
201507 | 050.40290 | 050.2637.Fantasy Ln Ext | 2015-04-01 | 2015-11-30 | 62.96% | 1293.7 | 1293.7 | -123.2 | Non Functional | -1050% | 153 | 243 | 2015-09-01
201507 | 050.40291 | 050.2637.Pecan Dr Rev Ext | 2015-04-06 | 2015-09-28 | 84.57% | 3233.97 | 3233.97 | -72.38 | Non Functional | -4468% | 148 | 175 | 2015-09-01
201507 | 050.40292 | 050.2637.Bruce Ave Rev Ext | 2015-07-01 | 2015-07-30 | 100% | 2598.6 | 2598.6 | 449.32 | Non Functional | 578.3% | 62 | 29 | 2015-09-01
201507 | 050.40375 | 2602.Oboro.Server.Replc.15 | 2015-05-12 | 2015-11-28 | 56% | 27092.25 | 27092.25 | 4604.46 | Non Functional | 588.4% | 112 | 200 | 2015-09-01
201507 | 050.40425 | PRP.2636.River Rd. | 2015-05-15 | 2015-10-30 | 64.88% | 441675.05 | 441675.05 | 166240.28 | Non Functional | 265.7% | 109 | 168 | 2015-09-01
201507 | 050.40452 | 050.2638.Graham Dr Ext 2 | 2015-06-01 | 2015-09-28 | 77.31% | 1876.23 | 1876.23 | 1425.53 | Non Functional | 131.6% | 92 | 119 | 2015-09-01
201507 | 050.40453 | 050.2637.Krebs Sta Rd Ext 3 | 2015-06-01 | 2015-09-28 | 77.31% | 1820.17 | 1820.17 | 520.41 | Non Functional | 349.8% | 92 | 119 | 2015-09-01
201507 | 050.40471 | PRP.2734.Crewdson Ln. | 2015-05-30 | 2016-01-30 | 38.37% | 1065458.52 | 1065458.52 | 305790.63 | Non Functional | 348.4% | 94 | 245 | 2015-09-01
201507 | 050.40488 | 050.2637.Creek Replacements | 2015-06-15 | 2015-07-30 | 100% | 25540.33 | 25540.33 | 3335.57 | Non Functional | 765.7% | 78 | 45 | 2015-09-01
201507 | 050.40489 | 050.2736.Katie Peden Dr Ext | 2015-06-01 | 2015-07-30 | 100% | 12468.95 | 12468.95 | 8206.21 | Non Functional | 151.9% | 92 | 59 | 2015-09-01
201507 | 050.40491 | 050.2739.WalkerLnStaRebuild | 2015-06-01 | 2015-09-28 | 77.31% | 186193.05 | 186193.05 | 31221.02 | Non Functional | 596.4% | 92 | 119 | 2015-09-01
201507 | 050.40532 | 050.2637.Ham Rd Rev Ext | 2015-06-15 | 2015-10-30 | 56.93% | 7785.07 | 7785.07 | -4071.92 | Non Functional | -191.2% | 78 | 137 | 2015-09-01
201507 | 050.40534 | PRP.2637.Madison | 2015-06-10 | 2015-12-22 | 42.56% | 493772.76 | 493772.76 | 412284.83 | Non Functional | 119.8% | 83 | 195 | 2015-09-01
201507 | 050.40556 | 050.2638.Dale Dr Rev Ext | 2015-07-01 | 2015-07-31 | 100% | 2477.78 | 2477.78 | 4480.11 | Non Functional | 55.31% | 62 | 30 | 2015-09-01
201507 | 050.40557 | 050.2634.Versnick Dr Rev Ext | 2015-07-01 | 2015-07-31 | 100% | 2744.34 | 2744.34 | 3673.64 | Non Functional | 74.7% | 62 | 30 | 2015-09-01
201507 | 050.40566 | 2609.HickoryStorageBuilding.15 | 2015-07-01 | 2015-11-30 | 40.79% | 153468 | 153468 | 70012.72 | Non Functional | 219.2% | 62 | 152 | 2015-09-01
201507 | 050.40577 | 050.2638.S 17th St Ext | 2015-07-01 | 2015-07-31 | 100% | 1274.88 | 1274.88 | 3253.21 | Non Functional | 39.19% | 62 | 30 | 2015-09-01
201507 | 050.40587 | PRP.2636.Dublin LN | 2015-06-25 | 2015-11-30 | 43.04% | 497699.56 | 497699.56 | 196602.65 | Non Functional | 253.1% | 68 | 158 | 2015-09-01
201507 | 050.40590 | 050.2739.Grade3LeakRepaieSlbyv | 2015-06-17 | 2015-09-28 | 73.79% | 20334.38 | 20334.38 | 10988.46 | Non Functional | 185.1% | 76 | 103 | 2015-09-01
201507 | 050.40615 | 050.2637.CANDLELIGHT EXT 2 | 2015-07-01 | 2015-11-30 | 40.79% | 30795.68 | 30795.68 | 1094.33 | Non Functional | 2814% | 62 | 152 | 2015-09-01
201507 | 050.40639 | PRP.2734.Clay-Stubbins | 2015-06-30 | 2015-09-28 | 70% | 345210.5 | 345210.5 | 111030.24 | Non Functional | 310.9% | 63 | 90 | 2015-09-01
201507 | 050.40672 | PRP.2734.Henry-McElroy | 2015-06-25 | 2015-09-30 | 70.1% | 83674.41 | 83674.41 | 33853.76 | Non Functional | 247.2% | 68 | 97 | 2015-09-01
201507 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-04-30 | 20.39% | 94340.72 | 94340.72 | 22271.3 | Non Functional | 423.6% | 62 | 304 | 2015-09-01
201507 | 050.40687 | PRP.2636.Kennedy Dr. | 2015-06-29 | 2015-08-28 | 100% | 20054.03 | 20054.03 | 23767.93 | Non Functional | 84.37% | 64 | 60 | 2015-09-01
201507 | 050.40693 | 050.2735.TB1Reloc.HorseCave | 2015-06-15 | 2015-11-30 | 46.43% | 265806.85 | 265806.85 | -221805.67 | Non Functional | -119.8% | 78 | 168 | 2015-09-01
201507 | 050.40699 | 050.2634.St Charles TB Repl | 2015-07-01 | 2015-10-30 | 51.24% | 23657.48 | 23657.48 | 20887.08 | Non Functional | 113.3% | 62 | 121 | 2015-09-01
201507 | 050.40703 | 050.2634.Liberty Sta Rebuild | 2015-08-01 | 2015-11-30 | 25.62% | 114318.3 | 114318.3 | 16319.45 | Non Functional | 700.5% | 31 | 121 | 2015-09-01
201507 | 050.40709 | 050.2637.Lourdes HCA Removal | 2015-07-25 | 2015-08-31 | 100% | 402594.45 | 402594.45 | 247363.44 | Non Functional | 162.8% | 38 | 37 | 2015-09-01
201507 | 050.40723 | 050.2638.Sedalia Rd Sys Imp | 2015-07-15 | 2015-12-30 | 28.57% | 52567.13 | 52567.13 | 59958.73 | Non Functional | 87.67% | 48 | 168 | 2015-09-01
201507 | 050.40733 | 050.2636.Avondale Reg. Repl. | 2015-06-18 | 2015-11-30 | 45.45% | 30420.87 | 30420.87 | 32522.43 | Non Functional | 93.54% | 75 | 165 | 2015-09-01
201507 | 050.40736 | PRP.2735.Buckner-Main St.MUN | 2015-07-15 | 2015-10-28 | 45.71% | 345285.8 | 345285.8 | 135646.02 | Non Functional | 254.5% | 48 | 105 | 2015-09-01
201507 | 050.40737 | PRP.2637.Madison-Harrison | 2015-08-01 | 2015-12-15 | 22.79% | 519852.6 | 519852.6 | 42330.38 | Non Functional | 1228% | 31 | 136 | 2015-09-01
201507 | 050.40757 | 050.2736.Davenport Ln Ext | 2015-07-15 | 2015-08-30 | 100% | 19387.44 | 19387.44 | 9941.59 | Non Functional | 195% | 48 | 46 | 2015-09-01
201507 | 050.40793 | 2737.HAR.NORTH REG STATION | 2015-05-29 | 2016-01-01 | 43.78% | 386221.96 | 386221.96 | 175326.25 | Non Functional | 220.3% | 95 | 217 | 2015-09-01
201507 | 050.40807 | 2739.LOCUST CRK 10b 2015 | 2015-05-01 | 2015-11-30 | 57.75% | 7510.03 | 7510.03 | 667.48 | Non Functional | 1125% | 123 | 213 | 2015-09-01
201507 | 050.40849 | 050.2739.Ninevah Road | 2015-07-16 | 2015-08-31 | 100% | 2976.74 | 2976.74 | 2517.3 | Non Functional | 118.3% | 47 | 46 | 2015-09-01
201507 | 050.40855 | 2602.Desktop.Laptop Purch.15 | 2015-07-23 | 2015-08-31 | 100% | 24997.6 | 24997.6 | 28055.69 | Non Functional | 89.1% | 40 | 39 | 2015-09-01
201507 | 050.40866 | PRP.2736.Robin Rd. | 2015-07-29 | 2015-09-29 | 54.84% | 32894.21 | 32894.21 | 12639.07 | Non Functional | 260.3% | 34 | 62 | 2015-09-01
201507 | 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 2015-08-03 | 2015-12-31 | 19.33% | 192654.19 | 192654.19 | -144010.31 | Non Functional | -133.8% | 29 | 150 | 2015-09-01
201507 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01
201508 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 97.18% | 14354.4 | 14354.4 | 10736.28 | Non Functional | 133.7% | 999 | 1028 | 2015-09-01
201508 | 050.35688 | 050.2609.Southwire | 2013-10-18 | 2015-11-15 | 90.11% | 18470.31 | 18470.31 | 16689.49 | Non Functional | 110.7% | 683 | 758 | 2015-09-01
201508 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 100% | 4043.35 | 4043.35 | 1971.61 | Non Functional | 205.1% | 595 | 486 | 2015-09-01
201508 | 050.37560 | 2735.Glasgow Office Land | 2014-06-01 | 2015-09-30 | 94.03% | 60000 | 60000 | 10136.05 | Non Functional | 591.9% | 457 | 486 | 2015-09-01
201508 | 050.37892 | PRP.2638.Mayfield 2014 | 2014-08-01 | 2015-07-29 | 100% | 666602.24 | 666602.24 | 735453.42 | Non Functional | 90.64% | 396 | 362 | 2015-09-01
201508 | 050.38279 | 050.2638.Pryorsburg TB Repl | 2014-09-02 | 2015-07-30 | 100% | 15584.5 | 15584.5 | 49801.7 | Non Functional | 31.29% | 364 | 331 | 2015-09-01
201508 | 050.38385 | MEC Forfeiture 040.009 FY14 | 2014-08-29 | 2015-10-31 | 85.98% | -208885.04 | -208885.04 | -898339.54 | Non Functional | 23.25% | 368 | 428 | 2015-09-01
201508 | 050.39087 | PRP.2635.Marion Eastside | 2014-12-01 | 2015-11-30 | 75.27% | 292646.32 | 292646.32 | 205026.33 | Non Functional | 142.7% | 274 | 364 | 2015-09-01
201508 | 050.39210 | Replace ECAT Correctors.KY.15 | 2014-12-02 | 2015-09-30 | 90.4% | 18067.03 | 18067.03 | 24710.68 | Non Functional | 73.11% | 273 | 302 | 2015-09-01
201508 | 050.39211 | Electronic Corr. Trans. KY.15 | 2014-12-02 | 2015-09-30 | 90.4% | 24230.25 | 24230.25 | 24391.51 | Non Functional | 99.34% | 273 | 302 | 2015-09-01
201508 | 050.39218 | 050.2636.Equipment FY 2015 | 2014-11-12 | 2015-09-28 | 91.56% | 24143.61 | 24143.61 | 22900.86 | Non Functional | 105.4% | 293 | 320 | 2015-09-01
201508 | 050.39380 | 2612.Emergency Regs.KY.15 | 2015-04-01 | 2015-09-30 | 84.07% | 30125.55 | 30125.55 | 2739.5 | Non Functional | 1100% | 153 | 182 | 2015-09-01
201508 | 050.39394 | 2735.GLASGOW EQUIPMENT 2015 | 2015-01-01 | 2015-06-01 | 100% | 43337.08 | 43337.08 | 44266.38 | Non Functional | 97.9% | 243 | 151 | 2015-09-01
201508 | 050.39403 | Hopkinsville Equipment | 2014-12-09 | 2015-09-28 | 90.78% | 43050.8 | 43050.8 | 38949.34 | Non Functional | 110.5% | 266 | 293 | 2015-09-01
201508 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-01-30 | 63.7% | 4431548.97 | 16281504.53 | 10974283.13 | Non Functional | 148.4% | 265 | 416 | 2015-09-01
201508 | 050.39408 | 2739.SHELBYVILLE EQUIP 2015 | 2015-01-01 | 2015-09-01 | 100% | 31287.91 | 31287.91 | 33221.2 | Non Functional | 94.18% | 243 | 243 | 2015-09-01
201508 | 050.39533 | PRP.2635.Sturgis Rd. | 2014-12-30 | 2015-11-20 | 75.38% | 486298.95 | 486298.95 | 470673.99 | Non Functional | 103.3% | 245 | 325 | 2015-09-01
201508 | 050.39578 | 050.2734.MackenzieMeadows | 2014-11-01 | 2015-09-28 | 91.84% | 12797.59 | 12797.59 | 9423.35 | Non Functional | 135.8% | 304 | 331 | 2015-09-01
201508 | 050.39588 | 2738.SUM.D HALL LN.CHICK 15 | 2015-01-01 | 2015-06-01 | 100% | 5975.42 | 5975.42 | -1350.41 | Non Functional | -442.5% | 243 | 151 | 2015-09-01
201508 | 050.39677 | 050.2734.Mics Equipment - B.G. | 2015-02-02 | 2015-09-28 | 88.66% | 73440.02 | 73440.02 | 70403.64 | Non Functional | 104.3% | 211 | 238 | 2015-09-01
201508 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2015-11-30 | 77.16% | 64381.86 | 64381.86 | 1688.99 | Non Functional | 3812% | 304 | 394 | 2015-09-01
201508 | 050.39756 | PRP.2737.Lexington-Greenville | 2015-02-09 | 2015-11-30 | 69.39% | 524520.52 | 928693.34 | 744259.61 | Non Functional | 124.8% | 204 | 294 | 2015-09-01
201508 | 050.39784 | PRP.2734.High St. Cabell-14th | 2015-02-01 | 2015-10-30 | 78.23% | 273210.75 | 273210.75 | 153308.96 | Non Functional | 178.2% | 212 | 271 | 2015-09-01
201508 | 050.39858 | 050.2734.BrennerSt.StationRep | 2015-02-13 | 2015-09-28 | 88.11% | 39193.59 | 39193.59 | 12517.52 | Non Functional | 313.1% | 200 | 227 | 2015-09-01
201508 | 050.39907 | PRP.2635.Maple St. | 2015-03-20 | 2015-11-30 | 64.71% | 357374.02 | 357374.02 | 98345.98 | Non Functional | 363.4% | 165 | 255 | 2015-09-01
201508 | 050.39911 | 2015 WMR | 2014-09-22 | 2015-10-22 | 87.09% | 32239.71 | 32239.71 | 28310.17 | Non Functional | 113.9% | 344 | 395 | 2015-09-01
201508 | 050.39996 | 2739.DIAGEO PHASE 1 2015 | 2015-03-01 | 2015-09-30 | 86.38% | 179870.01 | 179870.01 | -455893.68 | Non Functional | -39.45% | 184 | 213 | 2015-09-01
201508 | 050.40035 | 050.2734.Technology6inchPE | 2015-02-06 | 2015-09-28 | 88.46% | 32269.77 | 32269.77 | -9865.11 | Non Functional | -327.1% | 207 | 234 | 2015-09-01
201508 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-03-25 | -77.59% | 13697.21 | 13697.21 | 2365.26 | Non Functional | 579.1% | -90 | 116 | 2015-09-01
201508 | 050.40092 | 050.2636.ERX, regs, guages | 2015-04-01 | 2015-09-30 | 84.07% | 31239.42 | 31239.42 | 27663.59 | Non Functional | 112.9% | 153 | 182 | 2015-09-01
201508 | 050.40132 | 050.2637.USEC.MeterSet.FY15 | 2015-05-01 | 2015-08-31 | 100% | 294000.15 | 294000.15 | -64625.11 | Non Functional | -454.9% | 123 | 122 | 2015-09-01
201508 | 050.40218 | PRP.2735.East Back MUN. | 2015-05-01 | 2015-09-30 | 80.92% | 208562.05 | 208562.05 | 70989.21 | Non Functional | 293.8% | 123 | 152 | 2015-09-01
201508 | 050.40232 | PRP.2735.Washington St.MUN | 2015-05-01 | 2015-09-30 | 80.92% | 347110.72 | 347110.72 | 125546.61 | Non Functional | 276.5% | 123 | 152 | 2015-09-01
201508 | 050.40270 | 050.2734.Champion Pet Foods | 2015-04-20 | 2015-11-30 | 59.82% | 876504.36 | 876504.36 | -392856.35 | Non Functional | -223.1% | 134 | 224 | 2015-09-01
201508 | 050.40278 | Calvert Purchase Upgrade | 2014-09-22 | 2016-03-30 | 61.98% | 23946.76 | 23946.76 | 10397.92 | Non Functional | 230.3% | 344 | 555 | 2015-09-01
201508 | 050.40284 | 050.2635.Charleston TB Reloc | 2015-04-06 | 2015-09-28 | 84.57% | 11889.51 | 11889.51 | 18026.79 | Non Functional | 65.95% | 148 | 175 | 2015-09-01
201508 | 050.40290 | 050.2637.Fantasy Ln Ext | 2015-04-01 | 2015-11-30 | 62.96% | 1293.7 | 1293.7 | -123.2 | Non Functional | -1050% | 153 | 243 | 2015-09-01
201508 | 050.40291 | 050.2637.Pecan Dr Rev Ext | 2015-04-06 | 2015-09-28 | 84.57% | 3233.97 | 3233.97 | -72.38 | Non Functional | -4468% | 148 | 175 | 2015-09-01
201508 | 050.40292 | 050.2637.Bruce Ave Rev Ext | 2015-07-01 | 2015-07-30 | 100% | 2598.6 | 2598.6 | 449.32 | Non Functional | 578.3% | 62 | 29 | 2015-09-01
201508 | 050.40375 | 2602.Oboro.Server.Replc.15 | 2015-05-12 | 2015-11-28 | 56% | 27092.25 | 27092.25 | 4604.46 | Non Functional | 588.4% | 112 | 200 | 2015-09-01
201508 | 050.40425 | PRP.2636.River Rd. | 2015-05-15 | 2015-10-30 | 64.88% | 441675.05 | 441675.05 | 166240.28 | Non Functional | 265.7% | 109 | 168 | 2015-09-01
201508 | 050.40452 | 050.2638.Graham Dr Ext 2 | 2015-06-01 | 2015-09-28 | 77.31% | 1876.23 | 1876.23 | 1425.53 | Non Functional | 131.6% | 92 | 119 | 2015-09-01
201508 | 050.40453 | 050.2637.Krebs Sta Rd Ext 3 | 2015-06-01 | 2015-09-28 | 77.31% | 1820.17 | 1820.17 | 520.41 | Non Functional | 349.8% | 92 | 119 | 2015-09-01
201508 | 050.40471 | PRP.2734.Crewdson Ln. | 2015-05-30 | 2016-01-30 | 38.37% | 1065458.52 | 1065458.52 | 305790.63 | Non Functional | 348.4% | 94 | 245 | 2015-09-01
201508 | 050.40488 | 050.2637.Creek Replacements | 2015-06-15 | 2015-07-30 | 100% | 25540.33 | 25540.33 | 3335.57 | Non Functional | 765.7% | 78 | 45 | 2015-09-01
201508 | 050.40489 | 050.2736.Katie Peden Dr Ext | 2015-06-01 | 2015-07-30 | 100% | 12468.95 | 12468.95 | 8206.21 | Non Functional | 151.9% | 92 | 59 | 2015-09-01
201508 | 050.40491 | 050.2739.WalkerLnStaRebuild | 2015-06-01 | 2015-09-28 | 77.31% | 186193.05 | 186193.05 | 31221.02 | Non Functional | 596.4% | 92 | 119 | 2015-09-01
201508 | 050.40532 | 050.2637.Ham Rd Rev Ext | 2015-06-15 | 2015-10-30 | 56.93% | 7785.07 | 7785.07 | -4071.92 | Non Functional | -191.2% | 78 | 137 | 2015-09-01
201508 | 050.40534 | PRP.2637.Madison | 2015-06-10 | 2015-12-22 | 42.56% | 493772.76 | 493772.76 | 412284.83 | Non Functional | 119.8% | 83 | 195 | 2015-09-01
201508 | 050.40556 | 050.2638.Dale Dr Rev Ext | 2015-07-01 | 2015-07-31 | 100% | 2477.78 | 2477.78 | 4480.11 | Non Functional | 55.31% | 62 | 30 | 2015-09-01
201508 | 050.40557 | 050.2634.Versnick Dr Rev Ext | 2015-07-01 | 2015-07-31 | 100% | 2744.34 | 2744.34 | 3673.64 | Non Functional | 74.7% | 62 | 30 | 2015-09-01
201508 | 050.40566 | 2609.HickoryStorageBuilding.15 | 2015-07-01 | 2015-11-30 | 40.79% | 153468 | 153468 | 70012.72 | Non Functional | 219.2% | 62 | 152 | 2015-09-01
201508 | 050.40577 | 050.2638.S 17th St Ext | 2015-07-01 | 2015-07-31 | 100% | 1274.88 | 1274.88 | 3253.21 | Non Functional | 39.19% | 62 | 30 | 2015-09-01
201508 | 050.40578 | New roof on TB 1 | 2014-09-22 | 2015-10-22 | 87.09% | 10000 | 10000 | 13325.48 | Non Functional | 75.04% | 344 | 395 | 2015-09-01
201508 | 050.40587 | PRP.2636.Dublin LN | 2015-06-25 | 2015-11-30 | 43.04% | 497699.56 | 497699.56 | 196602.65 | Non Functional | 253.1% | 68 | 158 | 2015-09-01
201508 | 050.40590 | 050.2739.Grade3LeakRepaieSlbyv | 2015-06-17 | 2015-09-28 | 73.79% | 20334.38 | 20334.38 | 10988.46 | Non Functional | 185.1% | 76 | 103 | 2015-09-01
201508 | 050.40615 | 050.2637.CANDLELIGHT EXT 2 | 2015-07-01 | 2015-11-30 | 40.79% | 30795.68 | 30795.68 | 1094.33 | Non Functional | 2814% | 62 | 152 | 2015-09-01
201508 | 050.40639 | PRP.2734.Clay-Stubbins | 2015-06-30 | 2015-09-28 | 70% | 345210.5 | 345210.5 | 111030.24 | Non Functional | 310.9% | 63 | 90 | 2015-09-01
201508 | 050.40672 | PRP.2734.Henry-McElroy | 2015-06-25 | 2015-09-30 | 70.1% | 83674.41 | 83674.41 | 33853.76 | Non Functional | 247.2% | 68 | 97 | 2015-09-01
201508 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-04-30 | 20.39% | 94340.72 | 94340.72 | 22271.3 | Non Functional | 423.6% | 62 | 304 | 2015-09-01
201508 | 050.40693 | 050.2735.TB1Reloc.HorseCave | 2015-06-15 | 2015-11-30 | 46.43% | 265806.85 | 265806.85 | -221805.67 | Non Functional | -119.8% | 78 | 168 | 2015-09-01
201508 | 050.40699 | 050.2634.St Charles TB Repl | 2015-07-01 | 2015-10-30 | 51.24% | 23657.48 | 23657.48 | 20887.08 | Non Functional | 113.3% | 62 | 121 | 2015-09-01
201508 | 050.40703 | 050.2634.Liberty Sta Rebuild | 2015-08-01 | 2015-11-30 | 25.62% | 114318.3 | 114318.3 | 16319.45 | Non Functional | 700.5% | 31 | 121 | 2015-09-01
201508 | 050.40709 | 050.2637.Lourdes HCA Removal | 2015-07-25 | 2015-08-31 | 100% | 402594.45 | 402594.45 | 247363.44 | Non Functional | 162.8% | 38 | 37 | 2015-09-01
201508 | 050.40723 | 050.2638.Sedalia Rd Sys Imp | 2015-07-15 | 2015-12-30 | 28.57% | 52567.13 | 52567.13 | 59958.73 | Non Functional | 87.67% | 48 | 168 | 2015-09-01
201508 | 050.40733 | 050.2636.Avondale Reg. Repl. | 2015-06-18 | 2015-11-30 | 45.45% | 30420.87 | 30420.87 | 32522.43 | Non Functional | 93.54% | 75 | 165 | 2015-09-01
201508 | 050.40736 | PRP.2735.Buckner-Main St.MUN | 2015-07-15 | 2015-10-28 | 45.71% | 345285.8 | 345285.8 | 135646.02 | Non Functional | 254.5% | 48 | 105 | 2015-09-01
201508 | 050.40737 | PRP.2637.Madison-Harrison | 2015-08-01 | 2015-12-15 | 22.79% | 519852.6 | 519852.6 | 42330.38 | Non Functional | 1228% | 31 | 136 | 2015-09-01
201508 | 050.40757 | 050.2736.Davenport Ln Ext | 2015-07-15 | 2015-08-30 | 100% | 19387.44 | 19387.44 | 9941.59 | Non Functional | 195% | 48 | 46 | 2015-09-01
201508 | 050.40779 | PRP.2734.Centerline Phase 2 | 2015-07-20 | 2016-02-29 | 19.2% | 504034.42 | 4308210.9 | 392475.03 | Non Functional | 1098% | 43 | 224 | 2015-09-01
201508 | 050.40793 | 2737.HAR.NORTH REG STATION | 2015-05-29 | 2016-01-01 | 43.78% | 386221.96 | 386221.96 | 175326.25 | Non Functional | 220.3% | 95 | 217 | 2015-09-01
201508 | 050.40807 | 2739.LOCUST CRK 10b 2015 | 2015-05-01 | 2015-11-30 | 57.75% | 7510.03 | 7510.03 | 667.48 | Non Functional | 1125% | 123 | 213 | 2015-09-01
201508 | 050.40866 | PRP.2736.Robin Rd. | 2015-07-29 | 2015-09-29 | 54.84% | 32894.21 | 32894.21 | 12639.07 | Non Functional | 260.3% | 34 | 62 | 2015-09-01
201508 | 050.40909 | 050.2636.DeerValley3 | 2015-07-01 | 2015-09-28 | 69.66% | 54933.77 | 54933.77 | 41448.84 | Non Functional | 132.5% | 62 | 89 | 2015-09-01
201508 | 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 2015-08-03 | 2015-12-31 | 19.33% | 192654.19 | 192654.19 | -144010.31 | Non Functional | -133.8% | 29 | 150 | 2015-09-01
201508 | 050.40936 | 050.2637.Maxon Rd Relocation | 2015-08-24 | 2015-10-30 | 11.94% | 753263.09 | 753263.09 | 44884.91 | Non Functional | 1678% | 8 | 67 | 2015-09-01
201508 | 050.40982 | 050.2734.Hunts Ln. Ext | 2014-08-01 | 2015-09-28 | 93.62% | 15248.4 | 15248.4 | 6408.03 | Non Functional | 238% | 396 | 423 | 2015-09-01
201508 | 050.40986 | PRP.2609.Dawson Springs | 2015-08-13 | 2016-07-28 | 5.429% | 505547.54 | 1460629.1 | 74831.8 | Non Functional | 1952% | 19 | 350 | 2015-09-01
201508 | 050.41011 | 050.2637.Walton Rd Rev Ext | 2015-08-15 | 2015-09-28 | 38.64% | 3168.84 | 3168.84 | -861.27 | Non Functional | -367.9% | 17 | 44 | 2015-09-01
201508 | 050.41037 | 050.2637.Central Rd Rev Ext | 2015-09-01 | 2015-09-28 | 0% | 1309.6 | 1309.6 | 51.08 | Non Functional | 2564% | 0 | 27 | 2015-09-01
201508 | 050.41042 | 060.2636.BuffaloTrace Ext | 2015-08-05 | 2015-09-29 | 49.09% | 18158.76 | 18158.76 | 410.64 | Non Functional | 4422% | 27 | 55 | 2015-09-01
201508 | 050.41043 | 050.2636.Wright Ave Est | 2015-02-16 | 2015-09-28 | 87.95% | 2650.94 | 2650.94 | 531.7 | Non Functional | 498.6% | 197 | 224 | 2015-09-01
201508 | 050.41056 | 050.2637.Riley Cr Ext | 2015-08-18 | 2015-09-29 | 33.33% | 2815.24 | 2815.24 | -2961.95 | Non Functional | -95.05% | 14 | 42 | 2015-09-01
201508 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 | 87.03% | 0 | 0 | -414345.88 | Capital State Ovhd | 0% | 3268 | 3755 | 2015-09-01