## 2015
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2015
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2015
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | I12-020047 | Field Ops Road Replacement | Weather delays and additional subgrade work effected project completion | 352752.28 | 327458.11 | 2014-10-27 | 2015-01-30 | 2014-10-27 | 2015-05-08
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 2452788 | 2000000 | 452788 | 122.6% | 6.823%
A | MAINS - NEW | 688393 | 750000 | -61607 | 91.79% | 2.559%
B | MAINS - REPLACED/RESTORED | 5268365 | 3117000 | 2151365 | 169% | 10.63% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 352752.28 | 327458.11
C | MAINS - UNSCHEDULED | 198121 | 335000 | -136879 | 59.14% | 1.143%
D | MAINS - RELOCATED | 456058 | 785000 | -328942 | 58.1% | 2.678%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 158724 | 200100 | -41376 | 79.32% | 0.6826%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 1517543 | 332150 | 1185393 | 456.9% | 1.133%
G | SERVICES AND LATERALS - NEW | 968162 | 1030080 | -61918 | 93.99% | 3.514%
H | SERVICES AND LATERALS - REPLACED | 400865 | 650000 | -249135 | 61.67% | 2.217%
I | METERS - NEW | 618848 | 542412 | 76436 | 114.1% | 1.85%
J | METERS - REPLACED | 551455 | 937917 | -386462 | 58.8% | 3.2%
K | ITS EQUIPMENT AND SYSTEMS | 136935 | 131221 | 5714 | 104.4% | 0.4476%
L | SCADA EQUIPMENT AND SYSTEMS | 305610 | 140000 | 165610 | 218.3% | 0.4776%
M | SECURITY EQUIPMENT AND SYSTEMS | 165138 | 245000 | -79862 | 67.4% | 0.8358%
N | OFFICES AND OPERATIONS CENTERS | 93664 | 150000 | -56336 | 62.44% | 0.5117%
O | VEHICLES | 584522 | 552000 | 32522 | 105.9% | 1.883%
P | TOOLS AND EQUIPMENT | 567056 | 305000 | 262056 | 185.9% | 1.04%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 2311469 | 1454875 | 856594 | 158.9% | 4.963%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 0 | 0 | 0 |  | 0%
S | ENGINEERING STUDIES | 449091 | 42020 | 407071 | 1069% | 0.1433%
| TOTAL | 17892807 | 13699775 | 4193032 | 130.6%
| ENTER ITEM DV AND SUBTRACT | 2452788 | 2000000 | 452788
| TOTAL ITEM A - S | 15440019 | 11699775 | 3740244 | 132%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2015
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
I12-020010 | Leestown Road | -2903 | 0 | -2903 |  | 0% |  |  | 0 | 2010-01-01 | 2014-12-31 | 2010-10-01 | 2014-05-14
I12-020011 | New Circle Rd Main Relocation | 2450776 | 1009593 | 1441183 | 242.7% | 3.444% |  |  | 0 | 2012-01-01 | 2016-12-31 | 2015-03-24
I12-020012 | KRS High Service Pumps | 727565 | 0 | 727565 |  | 0% |  |  |  | 2016-01-04 | 2017-12-29 | 2015-02-27
I12-020017 | KRS Valve House Rehabilitation | 964373 | 0 | 964373 |  | 0% |  |  | 0 | 2014-01-02 | 2015-12-31 | 2014-07-25
I12-020056 | KRS Valve House 2 | 496064 | 0 | 496064 |  | 0% |  |  | 0 | 2015-06-23 | 2016-02-26 | 2015-06-26
I12-020032 | RRS Filter Building Replacement | 10539887 | 11925000 | -1385113 | 88.38% | 40.68% |  |  | 0 | 2013-01-01 | 2016-12-31 | 2015-02-01
I12-020033 | KY 341 Interconnect | 460667 | 0 | 460667 |  | 0% |  |  | 0 | 2013-01-01 | 2014-12-31 | 2014-08-26
I12-020040 | KRS Valve House Rehabilitation Ph 2 | 0 | 1000000 | -1000000 | 0% | 3.411% |  |  | 0 | 2015-08-03 | 2015-12-31
I12-020043 | Athens Boonesboro main Extension | 0 | 400000 | -400000 | 0% | 1.365% |  |  | 0 | 2015-01-02 | 2016-12-30
I12-020045 | Main Office Roof Replacement | 2506 | 0 | 2506 |  | 0% |  |  | 0 | 2014-08-18 | 2014-11-14 | 2014-08-26 | 2014-12-31
I12-020046 | KRS I Raw Water Intake Actuator Repl | 191174 | 0 | 191174 |  | 0% |  |  | 0 | 2014-09-29 | 2015-02-27 | 2014-09-30
I12-020047 | Field Ops Road Replacement | 18809 | 0 | 18809 |  | 0% | 352752.28 | 327458.11 | 25294.17 | 2014-10-27 | 2015-01-30 | 2014-10-27 | 2015-05-08
I12-020048 | Security Upgrades Richmond Rd Campus | 31242 | 0 | 31242 |  | 0% |  |  | 0 | 2014-10-15 | 2014-12-31 | 2014-10-27 | 2014-12-31
I12-020057 | Sludge Thickener Drive Upgrade | 521564 | 0 | 521564 |  | 0% |  |  | 0 | 2015-07-01 | 2015-12-01 | 2015-08-31
I12-020058 | KRS2 Intake Pump Replacement | 601163 | 0 | 601163 |  | 0% |  |  | 0 | 2015-08-24 | 2016-04-29 | 2015-08-31
I12-020059 | KRS2 Transfer Switch | 66400 | 0 | 66400 |  | 0% |  |  | 0 | 2015-10-29 | 2017-12-01
I12-020060 | KRS Reeves Drive | 5740 |  | 5740 |  | 0% |  |  | 0 | 2015-10-29 | 2016-05-02 | 2015-10-30
I12-300003 | Northern Division Connection | 49119 |  | 49119 |  | 0% |  |  | 0 | 2011-02-01 | 2014-02-28 | 2013-03-19 | 2014-05-07
T12-0102 | Business Transformation | -228820 |  | -228820 |  | 0% |  |  | 0 | 2011-09-01 | 2014-12-01 | 2011-10-01 | 2014-12-31
R12-K | ITS Centrally Sponsored | 1690479 | 0 | 1690479 |  |  |  |  | 0 | n/a | n/a | n/a | n/a
I12-000001 | Acquisitions | 0 | 1279427 | -1279427 | 0% | 4.365% |  |  | 0 | 2014-01-01 | 2014-12-01 | n/a | n/a
|  | 18585805 | 15614020 | 2971785 | 119%

## 2014
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2014
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2014
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | I12-020010 | Leestown Road | The project schedule was delayed do to issue with KTC Notice to Proceed. | 2058699.22 | 2182564.93 | 2010-01-01 | 2014-12-31 | 2010-10-01 | 2014-05-14
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | I12-020034 | RRS Chlorine Scrubber | Equipment delivery delay caused and extension of the construction schedule. Favorable bids reduced overall cost of project. | 311682.03 | 450000 | 2013-04-18 | 2013-12-31 | 2013-04-30 | 2014-07-31
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 3214462 | 1890900 | 1323562 | 170% | 8.825% | [7 empty] | I12-020045 | Main Office Roof Replacement | Weather delay for moving existing roof top equipment caused slip of final completion. Favorable installation bids accounted for project savings. | 393806.51 | 405875.16 | 2014-08-18 | 2014-11-14 | 2014-08-26 | 2014-12-31
A | MAINS - NEW | 982178 | 449956 | 532222 | 218.3% | 2.1% | [7 empty] | I12-020048 | Security Upgrades Richmond Rd Campus | Scope was expanded during project to account for additional securty improvements on Richmond Road Campus. | 459754.24 | 429450.14 | 2014-10-15 | 2014-12-31 | 2014-10-27 | 2014-12-31
B | MAINS - REPLACED/RESTORED | 3662352 | 5106000 | -1443648 | 71.73% | 23.83% | [7 empty] | I12-300003 | Northern Division Connection | Weather delays and tough laying conditions delayed project and added to scope of project. | 15308044.28 | 14104868 | 2011-02-01 | 2014-02-28 | 2013-03-19 | 2014-05-07
C | MAINS - UNSCHEDULED | 291349 | 275484 | 15865 | 105.8% | 1.286% | [7 empty] | T12-0102 | Business Transformation | On schedule, construction costs slightly lower than anticipated. | 10683881.88 | 11167479 | 2010-01-01 | 2014-12-01 | 2010-02-01 | 2014-12-31
D | MAINS - RELOCATED | 921918 | 515079 | 406839 | 179% | 2.404% | [7 empty] | T12-0103 | Business Transformation Other | On schedule, construction costs higher than anticipated. | 1000691.23 | 784479 | 2011-09-01 | 2014-12-01 | 2011-10-01 | 2014-12-31
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 201082 | 201500 | -418 | 99.79% | 0.9405% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 29215868.16 | 28740237.23
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 759112 | 340764 | 418348 | 222.8% | 1.59%
G | SERVICES AND LATERALS - NEW | 562611 | 1101429 | -538818 | 51.08% | 5.141%
H | SERVICES AND LATERALS - REPLACED | 397836 | 451903 | -54067 | 88.04% | 2.109%
I | METERS - NEW | 313704 | 545701 | -231997 | 57.49% | 2.547%
J | METERS - REPLACED | 802895 | 1194748 | -391853 | 67.2% | 5.576%
K | ITS EQUIPMENT AND SYSTEMS | 287264 | 279455 | 7809 | 102.8% | 1.304%
L | SCADA EQUIPMENT AND SYSTEMS | 40279 | 131313 | -91034 | 30.67% | 0.6129%
M | SECURITY EQUIPMENT AND SYSTEMS | 157258 | 157575 | -317 | 99.8% | 0.7355%
N | OFFICES AND OPERATIONS CENTERS | 207245 | 126060 | 81185 | 164.4% | 0.5884%
O | VEHICLES | 691672 | 562018 | 129654 | 123.1% | 2.623%
P | TOOLS AND EQUIPMENT | 241065 | 303463 | -62398 | 79.44% | 1.416%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 3162463 | 1242000 | 1920463 | 254.6% | 5.797%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 0 | 0 | 0 |  | 0%
S | ENGINEERING STUDIES | 261770 | 42020 | 219750 | 623% | 0.1961%
| TOTAL | 17158515 | 14917368 | 2241147 | 115%
| ENTER ITEM DV AND SUBTRACT | 3214462 | 1890900 | 1323562
| TOTAL ITEM A - S | 13944053 | 13026468 | 917585 | 107%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2014
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
I12-020001 | WTP for Pool 3 | 33935 | 0 | 33935 |  | 0% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01 | 2012-02-23
I12-020007 | North Upper St Main Repl | 0 | 1000000 | -1000000 | 0% | 4.667% |  |  | 0 | 2013-01-01 | 2014-12-31
I12-020010 | Leestown Road | 152963 | 0 | 152963 |  | 0% | 2058699.22 | 2182564.93 | -123865.71 | 2010-01-01 | 2014-12-31 | 2010-10-01 | 2014-05-14
I12-020011 | New Circle Rd Main Relocation | 287933 | 1099899 | -811966 | 26.18% | 5.134% |  |  | 0 | 2012-01-01 | 2016-12-31
I12-020017 | KRS Valve House Rehabilitation | 691347 | 1000000 | -308653 | 69.13% | 4.667% |  |  | 0 | 2014-01-02 | 2015-12-31 | 2014-07-25
I12-020025 | Pump Efficiency Repl Phase 1 | 18370 | 0 | 18370 |  | 0% |  |  | 0 | 2012-01-01 | 2014-12-31 | 2013-03-19 | 2013-08-01
I12-020027 | Russell Cave Rd | -2188 | 0 | -2188 |  | 0% |  |  | 0 | 2011-01-01 | 2013-12-31 | 2011-10-01 | 2013-08-30
I12-020032 | RRS Filter Building Replacement | 709175 | 775000 | -65825 | 91.51% | 3.617% |  |  | 0 | 2013-01-01 | 2016-12-31 | 2015-02-01
I12-020033 | KY 341 Interconnect | 758006 | 586021 | 171985 | 129.3% | 2.735% |  |  | 0 | 2013-01-01 | 2014-12-31 | 2014-08-26
I12-020034 | RRS Chlorine Scrubber | 20317 | 0 | 20317 |  | 0% | 311682.03 | 450000 | -138317.97 | 2013-04-18 | 2013-12-31 | 2013-04-30 | 2014-07-31
I12-020036 | Storage Tank and System Nitrification | 0 | 350000 | -350000 | 0% | 1.634% |  |  | 0 | 2014-01-02 | 2014-12-31
I12-020045 | Main Office Roof Replacement | 391301 | 0 | 391301 |  | 0% | 393806.51 | 405875.16 | -12068.65 | 2014-08-18 | 2014-11-14 | 2014-08-26 | 2014-12-31
I12-020046 | KRS I Raw Water Intake Actuator Repl | 487670 | 0 | 487670 |  | 0% |  |  | 0 | 2014-09-29 | 2015-02-27 | 2014-09-30
I12-020047 | Field Ops Road Replacement | 333943 | 0 | 333943 |  | 0% |  |  | 0 | 2014-10-27 | 2015-01-30 | 2014-10-27
I12-020048 | Security Upgrades Richmond Rd Campus | 428512 | 0 | 428512 |  | 0% | 459754.24 | 429450.14 | 30304.1 | 2014-10-15 | 2014-12-31 | 2014-10-27 | 2014-12-31
I12-300003 | Northern Division Connection | 369307 | 118110 | 251197 | 312.7% | 0.5513% | 15308044.28 | 14104868 | 1203176.28 | 2011-02-01 | 2014-02-28 | 2013-03-19 | 2014-05-07
I12-300005 | Fairgrounds Tank Area |  | 500000 | -500000 | 0% | 2.334% |  |  | 0 | 2014-01-02 | 2014-07-31
T12-0102 | Business Transformation | 350389 | 117256 | 233133 | 298.8% | 0.5473% | 10683881.88 | 11167479 | -483597.12 | 2010-01-01 | 2014-12-01 | 2010-02-01 | 2014-12-31
T12-0103 | Business Transformation Other | 32 |  | 32 |  | 0% | 1000691.23 | 784479 | 216212.23 | 2011-09-01 | 2014-12-01 | 2011-10-01 | 2014-12-31
R12-K | ITS Centrally Sponsored | 1336514 | 319464 | 1017050 | 418.4% |  |  |  | 0 | n/a | n/a | n/a | n/a
| Acquisitions | 0 | 642349 | -642349 | 0% | 2.998% |  |  | 0 | 2014-01-01 | 2014-12-01 | n/a | n/a
|  | 6367526 | 6508099 | -140573 | 97.84%

## 2013
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2013
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2013
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | I12-020009 | US 25 Relocation - Item 7-122.50 | The project schedule was delayed do to issue with KTC Notice to Proceed. | 1079811.12 | 1147026 | 2010-02-01 | 2010-10-01 | 2010-09-01 | 2013-01-24
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | I12-020025 | Pump Efficiency Repl Phase 1 | On schedule, construction costs slightly lower than anticipated. | 3559485.24 | 3545583.8 | 2012-01-01 | 2014-12-31 | 2013-03-19 | 2013-08-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 1972625 | 1726546 | 246079 | 114.3% | 6.698% | [7 empty] | I12-020027 | Russell Cave Rd Sys Improvements | Project was delayed due to additional modeling and design work needed to ensure proper implementation of intented project. The project cost benefited from better construction bids and revisions to project that eliminated minor elements from project. | 564633.81 | 749989 | 2011-01-01 | 2013-12-31 | 2011-10-01 | 2013-08-30
A | MAINS - NEW | 849856 | 259999 | 589857 | 326.9% | 1.009%
B | MAINS - REPLACED/RESTORED | 1645060 | 2000000 | -354940 | 82.25% | 7.759%
C | MAINS - UNSCHEDULED | 369365 | 275484 | 93881 | 134.1% | 1.069% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 5203930.17 | 5442598.8
D | MAINS - RELOCATED | 165758 | 480079 | -314321 | 34.53% | 1.862%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 151975 | 184993 | -33018 | 82.15% | 0.7177%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 628707 | 305696 | 323011 | 205.7% | 1.186%
G | SERVICES AND LATERALS - NEW | 922914 | 1042445 | -119531 | 88.53% | 4.044%
H | SERVICES AND LATERALS - REPLACED | 655250 | 1011321 | -356071 | 64.79% | 3.923%
I | METERS - NEW | 747902 | 504240 | 243662 | 148.3% | 1.956%
J | METERS - REPLACED | 2691058 | 2862739 | -171681 | 94% | 11.11%
K | ITS EQUIPMENT AND SYSTEMS | 216174 | 315805 | -99631 | 68.45% | 1.225%
L | SCADA EQUIPMENT AND SYSTEMS | 1006570 | 1113688 | -107118 | 90.38% | 4.32%
M | SECURITY EQUIPMENT AND SYSTEMS | 83068 | 210100 | -127032 | 39.54% | 0.8151%
N | OFFICES AND OPERATIONS CENTERS | 10231 | 105050 | -94819 | 9.739% | 0.4075%
O | VEHICLES | 475115 | 541008 | -65893 | 87.82% | 2.099%
P | TOOLS AND EQUIPMENT | 655282 | 307797 | 347485 | 212.9% | 1.194%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1382796 | 1201991 | 180805 | 115% | 4.663%
R | CAPITALIZED TANK REHABILIATION/PAINTING |  | 0 | 0 |  | 0%
S | ENGINEERING STUDIES | 54556 | 42020 | 12536 | 129.8% | 0.163%
| TOTAL | 14684262 | 14491001 | 193261 | 101.3%
| ENTER ITEM DV AND SUBTRACT | 1972625 | 1726546 | 246079
| TOTAL ITEM A - S | 12711637 | 12764455 | -52818 | 99.59%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2013
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
I12-020001 | New WTP On Pool 3 of Kentucky | 29379 | 0 | 29379 |  | 0% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01 | 2012-02-23
I12-020009 | US 25 Relocation - Item 7-122.50 | -1612868 | 0 | -1612868 |  | 0% | 1079811.12 | 1147026 | -67214.88 | 2010-02-01 | 2010-10-01 | 2010-09-01 | 2013-01-24
I12-020010 | Leestown Road - Item 7-223.00 | 1284533 | 0 | 1284533 |  | 0% |  |  | 0 | 2010-01-01 | 2014-12-31 | 2010-10-01
I12-020025 | Pump Efficiency Repl Phase 1 | 2570262 | 0 | 2570262 |  | 0% | 3559485.24 | 3545583.8 | 13901.44 | 2012-01-01 | 2014-12-31 | 2013-03-19 | 2013-08-01
I12-020026 | Pump Efficiency Repl Phase 2 | 0 | 600000 | -600000 | 0% | 2.328% |  |  | 0 | 2011-08-01 | 2011-12-01 | n/a | n/a
I12-020027 | Russell Cave Rd Sys Improvements | 38957 | 0 | 38957 |  | 0% | 564633.81 | 749989 | -185355.19 | 2011-10-01 | 2012-07-01 | 2011-10-01 | 2013-08-30
I12-020032 | RRS Filter Building Replacement | 54256 | 0 | 54256 |  | 0% |  |  | 0 | 2013-01-01 | 2016-12-31
I12-020033 | KY 341 Interconnect | 86925 | 0 | 86925 |  | 0% |  |  | 0 | 2013-01-01 | 2014-12-31
I12-020034 | RRS Chlorine Scrubber | 291365 | 0 | 291365 |  | 0% |  |  | 0 | 2013-04-18 | 2013-12-31 | 2013-04-30
I12-300003 | Northern Division Connection | 10920412 | 8959758 | 1960654 | 121.9% | 34.76% |  |  |  | 2011-02-01 | 2014-02-28 | 2013-03-19
T12-0102 | Business Transformation | 2355991 | 1694289 | 661702 | 139.1% | 6.573% |  |  |  | 2010-01-01 | 2014-12-01 | 2010-02-01
T12-0103 | Business Transformation Other | 145601 | 32257 | 113344 | 451.4% | 0.1251% |  |  |  | 2011-09-01 | 2014-12-01 | 2011-10-01 | n/a
I12--010001 | IP Project Unbudgeted Capital | -5255 |  | -5255 |  | 0% |  |  |  | 2009-01-01 | n/a | n/a | n/a
|  | 16159558 | 11286304 | 4873254 | 143.2%

## 2012
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2012
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2012
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | I12-020001 | New WTP On Pool 3 of Kentucky | Project was used and useful in 2010, and project completion was during the first part of 2012 Additional cost was associated with scope changes during construction. | 164186132.26 | 162297120 | 2006-05-01 | 2010-12-01 | 2006-05-01 | 2012-02-23
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 2252402 | 1600000 | 652402 | 140.8% | 6.107%
A | MAINS - NEW | 52013 | 500000 | -447987 | 10.4% | 1.908%
B | MAINS - REPLACED/RESTORED | 673049 | 1015300 | -342251 | 66.29% | 3.875% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 164186132.26 | 162297120
C | MAINS - UNSCHEDULED | 372392 | 239400 | 132992 | 155.6% | 0.9137%
D | MAINS - RELOCATED | -75499 | 1050300 | -1125799 | -7.188% | 4.009%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 93539 | 210000 | -116461 | 44.54% | 0.8015%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 229888 | 205000 | 24888 | 112.1% | 0.7824%
G | SERVICES AND LATERALS - NEW | 910629 | 1079580 | -168951 | 84.35% | 4.12%
H | SERVICES AND LATERALS - REPLACED | 449290 | 1605000 | -1155710 | 27.99% | 6.126%
I | METERS - NEW | 894302 | 1200000 | -305698 | 74.53% | 4.58%
J | METERS - REPLACED | 3601691 | 2050000 | 1551691 | 175.7% | 7.824%
K | ITS EQUIPMENT AND SYSTEMS | 712828 | 265850 | 446978 | 268.1% | 1.015%
L | SCADA EQUIPMENT AND SYSTEMS | 1029901 | 659025 | 370876 | 156.3% | 2.515%
M | SECURITY EQUIPMENT AND SYSTEMS | 21266 | 20000 | 1266 | 106.3% | 0.07633%
N | OFFICES AND OPERATIONS CENTERS | 465392 | 80000 | 385392 | 581.7% | 0.3053%
O | VEHICLES | 925249 | 500000 | 425249 | 185% | 1.908%
P | TOOLS AND EQUIPMENT | 243251 | 220500 | 22751 | 110.3% | 0.8416%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1962058 | 1095000 | 867058 | 179.2% | 4.179%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 0 | 0 | 0 |  | 0%
S | ENGINEERING STUDIES | -267774 | 120000 | -387774 | -223.1% | 0.458%
| TOTAL | 14545867 | 13714955 | 830912 | 106.1%
| ENTER ITEM DV AND SUBTRACT | 2252402 | 1600000 | 652402
| TOTAL ITEM A - S | 12293465 | 12114955 | 178510 | 101.5%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2012
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
I12-020001 | New WTP On Pool 3 of Kentucky | 2854 | 0 | 2854 |  | 0% | 164186132.26 | 162297120 | 1889012.26 | 2006-05-01 | 2010-12-01 | 2006-05-01 | 2012-02-23
IP-1202-6 | Carrick Pike Main Extension | 0 | 50000 | -50000 |  | 0.1908% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01
IP-1202-9 | Todds and Cleveland Rd Main Ext | 0 | 799594 | -799594 | 0% | 3.052% |  |  | 0 | 2010-01-01 | 2011-12-31
I12-0020009 | US 25 Relocation | 1225541 | 439188 | 786353 |  | 1.676% |  |  | 0 | 2010-02-01 | 2010-10-01 | 2010-09-01
I12-0200010 | Leestown Road | 228927 | 809540 | -580613 | 28.28% | 3.09% |  |  | 0 | 2010-01-01 | 2014-12-31 | 2010-10-01
IP-1202-20 | KY Major Highway | 0 | 655000 | -655000 | 0% | 2.5% |  |  | 0
I12-020027 | Russell Cave Road Sys Impr | 89292 | 0 | 89292 |  | 0% |  |  | 0 | 2011-10-01 | 2012-07-01 | 2011-10-01
I12-020025 | Pump Efficiency Replacement Phase 1 | 953765 | 775348 | 178417 | 123% | 2.959% |  |  | 0 | 2011-08-01
IP-1202-37 | Pump Efficiency Replacement Phase 2 | 0 | 775002 | -775002 | 0% | 2.958% |  |  |  | 2010-03-01
I12-300003 | Northern Division Connection | 3978519 | 3830000 | 148519 | 103.9% | 14.62% |  |  | 0 | 2011-02-01 | 2014-02-28
IP-1232-3 | Northern Division Connection | -346828 | 0 | -346828 |  | 0% |  |  | 0 | 2011-02-01
CS-1201-1 | Business Transformation CPS | 0 | 0 | 0 |  | 0% |  |  | 0 | 2011-04-01 | 2011-07-01 | n/a | n/a
T12-0102-P | Business Transformation | 3835463 | 4130414 | -294951 | 92.86% | 15.76% |  |  |  | 2010-01-01 | 2014-12-01 | 2010-02-01
T12-0103-P | Business Transformation Other | 562289 | 91026 | 471263 | 617.7% | 0.3474% |  |  |  | 2011-09-01 | 2014-12-01 | 2011-10-01
| Acquisitions | 0 | 131369 | -131369 | 0% | 0.5014% |  |  |  | 2012-01-01 | 2012-12-01 | n/a | n/a
I12-010001 | IP Project Unbudgeted Capital | -214 |  | -214 |  | 0% |  |  |  | 2009-01-01 | n/a | n/a | n/a
|  | 10529608 | 12486481 | -1956873 | 84.33%

## 2011
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2011
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2011
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | IP-1202-5 | North Broadway Main Replacement | Project design and construction was delayed due to the Kentucky Transportation Cabinet. | 3049717.73 | 3136145 | 2007-12-01 | 2009-06-01 | 2008-03-01 | 2011-10-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | IP-1202-17 | South Limestone Replacement | Project design and construction was delayed due to the scheduel and funding of the LFUCG. | 549821.23 | 532854 | 2009-05-01 | 2009-07-01 | 2010-06-01 | 2011-01-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 1820567.53 | 2300000 | -479432.47 | 79.16% | 8.999% | [7 empty] | IP-1202-32 | Lexington Operations Center | Project was used and useful in 2010, a few change orders remained open until Nov. 2011. | 2808875.57 | 2756632 | 2010-03-01 | 2010-12-01 | 2010-05-01 | 2011-11-01
A | MAINS - NEW | 165527.32 | 489000 | -323472.68 | 33.85% | 1.913%
B | MAINS - REPLACED/RESTORED | 1884555.13 | 1005300 | 879255.13 | 187.5% | 3.933% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 6408414.53 | 6425631
C | MAINS - UNSCHEDULED | 272448.69 | 138500 | 133948.69 | 196.7% | 0.5419%
D | MAINS - RELOCATED | 375491.54 | 1050300 | -674808.46 | 35.75% | 4.109%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 148799.15 | 195000 | -46200.85 | 76.31% | 0.763%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 283383.12 | 131500 | 151883.12 | 215.5% | 0.5145%
G | SERVICES AND LATERALS - NEW | 592605.62 | 750000 | -157394.38 | 79.01% | 2.935%
H | SERVICES AND LATERALS - REPLACED | 633636.39 | 267000 | 366636.39 | 237.3% | 1.045%
I | METERS - NEW | 861939.01 | 600000 | 261939.01 | 143.7% | 2.348%
J | METERS - REPLACED | 5403894.63 | 3769751 | 1634143.63 | 143.3% | 14.75%
K | ITS EQUIPMENT AND SYSTEMS | 175355.71 | 155540 | 19815.71 | 112.7% | 0.6086%
L | SCADA EQUIPMENT AND SYSTEMS | 1088481.82 | 200000 | 888481.82 | 544.2% | 0.7825%
M | SECURITY EQUIPMENT AND SYSTEMS | 51694.09 | 20000 | 31694.09 | 258.5% | 0.07825%
N | OFFICES AND OPERATIONS CENTERS | 548021.33 | 80000 | 468021.33 | 685% | 0.313%
O | VEHICLES | 559415.48 | 500000 | 59415.48 | 111.9% | 1.956%
P | TOOLS AND EQUIPMENT | 160725.45 | 160000 | 725.45 | 100.5% | 0.626%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1891192.33 | 1085000 | 806192.33 | 174.3% | 4.245%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 197662.51 | 0 | 197662.51 |  | 0%
S | ENGINEERING STUDIES | 470794.21 | 400000 | 70794.21 | 117.7% | 1.565%
| TOTAL | 17586191.06 | 13296891 | 4289300.06 | 132.3%
| ENTER ITEM DV AND SUBTRACT | 1820567.53 | 2300000 | -479432.47
| TOTAL ITEM A - S | 15765623.53 | 10996891 | 4768732.53 | 143.4%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2011
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
12020204 | Source of Supply Project Dev | 0 |  | 0 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01 | 2010-11-01
12020607 | New WTP On Pool 3 of Kentucky | 713639.1 | 199999.9 | 513639.2 | 356.8% | 0.7825% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
IP-1202-5 | North Broadway Main Replacement | -79129.33 |  | -79129.33 |  | 0% | 3049717.73 | 3136145 | -86427.27 | 2007-12-01 | 2009-06-01 | 2008-03-01 | 2011-10-01
IP-1202-6 | Carrick Pike Main Extension | -129988.6 | 980513 | -1110501.6 | -13.26% | 3.836% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01 | n/a
IP-1202-17 | South Limestone Replacement | -107.77 |  | -107.77 |  | 0% | 549821.23 | 532854 | 16967.23 | 2009-05-01 | 2009-07-01 | 2010-06-01 | 2011-01-01
IP-1202-18 | US 25 Relocation | 415236.31 | 897983 | -482746.69 | 46.24% | 3.514% |  |  | 0 | 2010-02-01 | 2010-10-01 | 2010-09-01
IP-1202-19 | Leestown Road | 666047.27 | 1263746 | -597698.73 | 52.7% | 4.945% |  |  | 0 | 2011-04-01 | 2011-10-01 | 2010-10-01
IP-1202-21 | KRS High Service Pumping | 0 | 660000 | -660000 | 0% | 2.582% |  |  | 0 | 2011-10-01 | 2012-09-01 | n/a | n/a
IP-1202-31 | KRS Raw Water Access | 0 | 1000000 | -1000000 | 0% | 3.913% |  |  | 0 | 2011-08-01 | 2011-12-01 | n/a | n/a
IP-1202-32 | Lexington Operations Center | 138043.15 |  | 138043.15 |  | 0% | 2808875.57 | 2756632 | 52243.57 | 2010-03-01 | 2010-12-01 | 2010-05-01 | 2011-11-01
IP-1202-38 | Russell Cave Road Sys Impr | 447813.89 |  | 447813.89 |  | 0% |  |  | 0 | 2011-10-01 | 2012-07-01 | 2011-10-01
IP-1232-3 | Northern Division Connection | 344375.07 | 4700000 | -4355624.93 | 7.327% | 18.39% |  |  | 0 | 2011-02-01 | n/a | n/a | n/a
IP-1233-1 | Owenton WWTP Phosphorous | 0 | 140000 | -140000 | 0% | 0.5478% |  |  | 0 | 2011-04-01 | 2011-07-01 | n/a | n/a
CS-1201-3 | Business Transformation | 3511543.81 | 2304462 | 1207081.81 | 152.4% | 9.017% |  |  |  | 2010-01-01 | 2014-12-01 | 2010-02-01
CS-1201-4 | Business Transformation Other | 300972.07 |  | 300972.07 |  | 0% |  |  |  | 2011-09-01 | 2014-12-01 | 2011-10-01
| Acquisitions | 0 | 114262.32 | -114262.32 | 0% | 0.4471% |  |  |  | 2011-01-01 | 2011-12-01 | n/a | n/a
IP-1232-1 | Owenton Chemical Bulk Storage/Owenton Post Acquisition Phase 2 | -83705.15 |  | -83705.15 |  | 0% |  |  |  |  | n/a | n/a | n/a
IP-1201-9 | IP Project Unbudgeted Capital | -1090.75 |  | -1090.75 |  | 0% |  |  |  | 2009-01-01 | n/a | n/a | n/a
|  | 6243649.07 | 12260966.22 | -6017317.15 | 50.92%

## 2010
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2010
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2010
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 12020204 | Source of Supply Project Dev | Project was delayed due to the final approval and construction of KRS2. | 2133802 | 2200060 | 2002-04-01 | 2003-12-01 | 2001-06-01 | 2010-11-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 2112707.45 | 3560000 | -1447292.55 | 59.35% | 7.017%
A | MAINS - NEW | 82272.64 | 400000 | -317727.36 | 20.57% | 0.7884%
B | MAINS - REPLACED/RESTORED | 999913.76 | 565000 | 434913.76 | 177% | 1.114% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 2133802 | 2200060
C | MAINS - UNSCHEDULED | 269041.7 | 244400 | 24641.7 | 110.1% | 0.4817%
D | MAINS - RELOCATED | 727692.99 | 950000 | -222307.01 | 76.6% | 1.872%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 107570.94 | 200000 | -92429.06 | 53.79% | 0.3942%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 162530.41 | 175000 | -12469.59 | 92.87% | 0.3449%
G | SERVICES AND LATERALS - NEW | 611401.46 | 874660 | -263258.54 | 69.9% | 1.724%
H | SERVICES AND LATERALS - REPLACED | 294286.13 | 1240975 | -946688.87 | 23.71% | 2.446%
I | METERS - NEW | 436639.89 | 971340 | -534700.11 | 44.95% | 1.914%
J | METERS - REPLACED | 2666026.57 | 1584929 | 1081097.57 | 168.2% | 3.124%
K | ITS EQUIPMENT AND SYSTEMS | 139407.75 | 111090 | 28317.75 | 125.5% | 0.219%
L | SCADA EQUIPMENT AND SYSTEMS | 487125.09 | 103500 | 383625.09 | 470.7% | 0.204%
M | SECURITY EQUIPMENT AND SYSTEMS | 25404.8 | 10000 | 15404.8 | 254% | 0.01971%
N | OFFICES AND OPERATIONS CENTERS | 147296.29 | 80000 | 67296.29 | 184.1% | 0.1577%
O | VEHICLES | 814084.24 | 250000 | 564084.24 | 325.6% | 0.4927%
P | TOOLS AND EQUIPMENT | 129297.22 | 117000 | 12297.22 | 110.5% | 0.2306%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1882344.36 | 750000 | 1132344.36 | 251% | 1.478%
R | CAPITALIZED TANK REHABILIATION/PAINTING | -11627.94 | 0 | -11627.94 | #DIV/0! | 0%
S | ENGINEERING STUDIES | -46.07 | 100000 | -100046.07 | -0.04607% | 0.1971%
| TOTAL | 12083369.68 | 12287894 | -204524.32 | 98.34%
| ENTER ITEM DV AND SUBTRACT | 2112707.45 | 3560000 | -1447292.55
| TOTAL ITEM A - S | 9970662.23 | 8727894 | 1242768.23 | 114.2%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2010
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
12020204 | Source of Supply Project Dev | -2114107.58 | 128360 | -2242467.58 | -1647% | 0.253% | 2133802 | 2200060 | -66258 | 2002-04-01 | 2003-12-01 | 2001-06-01 | 2010-11-01
12020607 | New WTP On Pool 3 of Kentucky | 30789846.79 | 29181785.1 | 1608061.69 | 105.5% | 57.52% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
12020702 | KY Major Highway | -91967.18 | 0 | -91967.18 |  | 0% |  |  | 0 | 2007-01-01 | n/a | n/a | n/a
IP-1202-5 | North Broadway Main Replacement | 1565365.02 | 1151928.69 | 413436.33 | 135.9% | 2.27% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
IP-1202-6 | Carrick Pike Main Extension | 41892.66 | 0 | 41892.66 |  | 0% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01 | n/a
IP-1202-17 | South Limestone Replacement | 549929 | 532854 | 17075 | 103.2% | 1.05% |  |  | 0 | 2009-05-01 | 2009-07-01 | 2010-06-01
IP-1202-18 | US 25 Relocation | 1215244.17 | 3200000 | -1984755.83 | 37.98% | 6.307% |  |  | 0 | 2010-02-01 | 2010-10-01 | 2010-09-01
IP-1202-19 | Leestown Road | 243564.41 | 0 | 243564.41 |  | 0% |  |  | 0 | 2011-04-01 | 2011-10-01 | 2010-10-01
IP-1202-31 | KRS Raw Water Access | 0 | 50000 | -50000 | 0% | 0.09855% |  |  | 0 | 2010-11-01 | 2011-09-01 | n/a | n/a
IP-1202-32 | Lexington Operations Center | 2670832.42 |  | 2670832.42 |  | 0% |  |  | 0 | 2010-03-01 | 2010-12-01 | 2010-05-01
CS-1201-1 | Business Transformation CPS | 984.17 | 0 | 984.17 |  | 0% |  |  | 0 | 2009-01-01 | 2009-12-31 | 2009-01-01
CS-1201-3 | Business Transformation CPS | 1011336.08 | 4036079.01 | -3024742.93 | 25.06% | 7.955% |  |  | 0 | 2010-01-01 | 2014-12-01 | 2010-02-01
IP-1201-10 | Unallocated Eng Clearing | -943.29 |  | -943.29 |  | 0% |  |  | 0 | 2010-01-01 | 2010-12-01 | 2010-01-01 | n/a
12020201 | Leestown Rd Main Improvements | -150954.98 | 0 | -150954.98 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01 | n/a
12020402 | KY Major Highway Relocations | -36976.84 | 0 | -36976.84 |  | 0% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
IP-1201-9 | IP Project Unbudgeted Capital | -989.46 | 0 | -989.46 |  | 0% |  |  | 0 | 2009-01-01 | n/a | n/a | n/a
| Acquisitions | 0 | 168000 | -168000 | 0% | 0.3311% |  |  | 0 | 2010-01-01 | 2010-12-01 | n/a | n/a
|  | 0 | 0 | 0 |  | 0%
|  | 35693055.39 | 38449006.8 | -2755951.41 | 92.83%

## 2009
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2009
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2009
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 05-08 | KENTUCKY RELIABILITY IMPROVEMENT | Construction was shutdown during peak demand. Bids exceeded original estimate and scope was expanded during construction. | 7529869.92 | 6239562 | 2005-12-01 | 2007-07-01 | 2005-12-01 | 2009-07-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 06-02 | YARNALLTON ROAD MAIN EXTENSION | KAW was looking to increase the size of Yarnalltion as a possible secondary feed to the 42-inch tranmission main. After careful consideration it was determined not to be effective. Scope was expanded during construction from original budget. | 442102.82 | 200000 | 2006-03-01 | 2007-09-01 | 2006-08-01 | 2009-01-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 2547150.64 | 4700000 | -2152849.36 | 54.19% | 5.692%
A | MAINS - NEW | 641032.49 | 560000 | 81032.49 | 114.5% | 0.6782%
B | MAINS - REPLACED/RESTORED | 592722.95 | 1005300 | -412577.05 | 58.96% | 1.218% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 7971972.74 | 6439562
C | MAINS - UNSCHEDULED | 198333.89 | 239400 | -41066.11 | 82.85% | 0.2899%
D | MAINS - RELOCATED | 1540243.32 | 1005300 | 534943.32 | 153.2% | 1.218%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 65172.82 | 192000 | -126827.18 | 33.94% | 0.2325%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 182670.67 | 150000 | 32670.67 | 121.8% | 0.1817%
G | SERVICES AND LATERALS - NEW | 1297272.78 | 980000 | 317272.78 | 132.4% | 1.187%
H | SERVICES AND LATERALS - REPLACED | 735602.13 | 1400000 | -664397.87 | 52.54% | 1.696%
I | METERS - NEW | 615748.27 | 1215048 | -599299.73 | 50.68% | 1.472%
J | METERS - REPLACED | 1904051.61 | 2000000 | -95948.39 | 95.2% | 2.422%
K | ITS EQUIPMENT AND SYSTEMS | 117123.33 | 102000 | 15123.33 | 114.8% | 0.1235%
L | SCADA EQUIPMENT AND SYSTEMS | 64074.32 | 90000 | -25925.68 | 71.19% | 0.109%
M | SECURITY EQUIPMENT AND SYSTEMS | 14279.9 | 10000 | 4279.9 | 142.8% | 0.01211%
N | OFFICES AND OPERATIONS CENTERS | 1039331.44 | 560000 | 479331.44 | 185.6% | 0.6782%
O | VEHICLES | 141312.41 | 500000 | -358687.59 | 28.26% | 0.6056%
P | TOOLS AND EQUIPMENT | 51034.7 | 257200 | -206165.3 | 19.84% | 0.3115%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 720747.81 | 800000 | -79252.19 | 90.09% | 0.9689%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 58419.74 | 40000 | 18419.74 | 146% | 0.04844%
S | ENGINEERING STUDIES | 38832.03 | 150000 | -111167.97 | 25.89% | 0.1817%
| TOTAL | 12565157.25 | 15956248 | -3391090.75 | 78.75%
| ENTER ITEM DV AND SUBTRACT | 2547150.64 | 4700000 | -2152849.36
| TOTAL ITEM A - S | 10018006.61 | 11256248 | -1238241.39 | 89%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2009
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 19206.22 | 0 | 19206.22 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 106607.45 | 64200 | 42407.45 | 166.1% | 0.07775% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 267429 | 0 | 267429 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 25968.79 | 49930 | -23961.21 | 52.01% | 0.06047% |  |  | 0 | 2004-01-01 | N/A | n/a | n/a
05-01 | GROUND STORAGE TANK | 0 | 122869.69 | -122869.69 | 0% | 0.1488% |  |  | 0 | 2005-07-01 | 2007-12-01 | n/a | n/a
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 163785.98 | 80000 | 83785.98 | 204.7% | 0.09689% | 7529869.92 | 6239562 | 1290307.92 | 2005-12-01 | 2007-07-01 | 2005-12-01 | 2009-07-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | -1929.18 | 0 | -1929.18 |  | 0% | 442102.82 | 200000 | 242102.82 | 2006-03-01 | 2007-09-01 | 2006-08-01 | 2009-01-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 86106959.74 | 59986790 | 26120169.74 | 143.5% | 72.65% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
12020701 | INCLINE CAR REPLACEMENT AT KRS | 0 | 815288 | -815288 | 0% | 0.9874% |  |  | 0 | 2007-01-01 | 2009-10-01 | 2007-02-01 | 2008-12-01
12020702 | MAJOR HIGHWAY RELOCATIONS 2007 | -23290.19 | 0 | -23290.19 |  | 0% |  |  | 0 | 2007-01-01 | 2007-12-01 | 2007-03-01
1202-5 | NORTH BROADWAY MAIN REPLACEMENT | 1264105.24 | 2470076 | -1205970.76 | 51.18% | 2.992% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
1232-1 | OWENTON CHEMICAL BULK STORAGE | 2185.07 | 29123 | -26937.93 | 7.503% | 0.03527% |  |  | 0 | 2008-04-01 | 2009-01-01 | 2008-04-01
1202-6 | CARRICK ROAD MAIN EXTENSION | 25590.42 | 2637494 | -2611903.58 | 0.9703% | 3.194% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01
CS-1201-1 | BUSINESS TRANSFORMATION | 211055.62 | 356822 | -145766.38 | 59.15% | 0.4322% |  |  | 0 | 2009-01-01 | 2009-12-31 | 2009-01-01
|  | 0 | 0 | 0 |  | 0%
|  | 88167674.16 | 66612592.69 | 21555081.47 | 132.4%

## 2008
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2008
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2008
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | Weather delays and tough laying conditions delayed project. | 2285900.34 | 2150001 | 2004-10-01 | 2007-12-01 | 2004-10-01 | 2008-09-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | Construction was shutdown during peak demand which delayed schedule and increased contractor costs. | 1236263.92 | 994000 | 2005-04-01 | 2006-12-01 | 2005-04-01 | 2008-11-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 4188865.53 | 4000000 | 188865.53 | 104.7% | 7.236% | [7 empty] | 05-06 | SLUDGE HANDLING IMPROVEMENT | Construction was shutdown during peak demand which delayed schedule and increased contractor costs. | 2199181.21 | 1910000 | 2005-04-01 | 2008-12-01 | 2005-04-01 | 2008-10-01
A | MAINS - NEW | 49941.21 | 535000 | -485058.79 | 9.335% | 0.9678% | [7 empty] | 12020701 | INCLINE CAR REPLACEMENT AT KRS | Project was put on hold to conduct a study. Phase one was completed for safety. | 194940.26 | 1150000 | 2007-01-01 | 2009-10-01 | 2007-02-01 | 2008-12-01
B | MAINS - REPLACED/RESTORED | 992301.17 | 1886000 | -893698.83 | 52.61% | 3.412% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 5916285.73 | 6204001
C | MAINS - UNSCHEDULED | 271187.06 | 221937 | 49250.06 | 122.2% | 0.4015%
D | MAINS - RELOCATED | 145362.95 | 0 | 145362.95 |  | 0%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 110740.4 | 427992 | -317251.6 | 25.87% | 0.7742%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 129359.57 | 125000 | 4359.57 | 103.5% | 0.2261%
G | SERVICES AND LATERALS - NEW | 1157819.34 | 855915 | 301904.34 | 135.3% | 1.548%
H | SERVICES AND LATERALS - REPLACED | 1137151.36 | 641603 | 495548.36 | 177.2% | 1.161%
I | METERS - NEW | 656982.99 | 1149930 | -492947.01 | 57.13% | 2.08%
J | METERS - REPLACED | 1656512.75 | 1473399 | 183113.75 | 112.4% | 2.665%
K | ITS EQUIPMENT AND SYSTEMS | 259958.08 | 259750 | 208.08 | 100.1% | 0.4699%
L | SCADA EQUIPMENT AND SYSTEMS | 45277.97 | 51000 | -5722.03 | 88.78% | 0.09226%
M | SECURITY EQUIPMENT AND SYSTEMS | 36285.69 | 10000 | 26285.69 | 362.9% | 0.01809%
N | OFFICES AND OPERATIONS CENTERS | 1800000 | 146300 | 1653700 | 1230% | 0.2647%
O | VEHICLES | 455969.68 | 500000 | -44030.32 | 91.19% | 0.9045%
P | TOOLS AND EQUIPMENT | 224127.59 | 218014 | 6113.59 | 102.8% | 0.3944%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 858215.95 | 820600 | 37615.95 | 104.6% | 1.484%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 97252.28 | 0 | 97252.28 |  | 0%
S | ENGINEERING STUDIES | 105355.43 | 81000 | 24355.43 | 130.1% | 0.1465%
| TOTAL | 14378667 | 13403440 | 975227 | 107.3%
| ENTER ITEM DV AND SUBTRACT | 4188865.53 | 4000000 | 188865.53
| TOTAL ITEM A - S | 10189801.47 | 9403440 | 786361.47 | 108.4%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2008
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 40.4 | 0 | 40.4 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 348733.67 | 64200 | 284533.67 | 543.2% | 0.1161% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | -30.6 | 0 | -30.6 |  | 0% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 337 | 0 | 337 |  | 0% |  |  | 0 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 290942.05 | 2935000 | -2644057.95 | 9.913% | 5.309% |  |  | 0 | 2004-01-01 | N/A | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 316963.01 | 0 | 316963.01 |  | 0% | 2285900.34 | 2150001 | 135899.34 | 2004-10-01 | 2007-12-01 | 2004-10-01 | 2008-09-01
05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | -195.69 | 0 | -195.69 |  | 0% |  |  | 0 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | 96036.5 | 0 | 96036.5 |  | 0% | 1236263.92 | 994000 | 242263.92 | 2005-04-01 | 2006-12-01 | 2005-04-01 | 2008-11-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 172653.36 | 50000 | 122653.36 | 345.3% | 0.09045% | 2199181.21 | 1910000 | 289181.21 | 2005-04-01 | 2008-12-01 | 2005-04-01 | 2008-10-01
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 1359116.86 | 1210964 | 148152.86 | 112.2% | 2.191% |  |  | 0 | 2005-12-01 | 2007-07-01 | 2005-12-01
06-01 | VALVE HOUSE UPGRADES AT KRS | -38141.61 | 0 | -38141.61 |  | 0% |  |  | 0 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | 414412.41 | 0 | 414412.41 |  | 0% |  |  | 0 | 2006-03-01 | 2007-09-01 | 2006-08-01
06-04 | OWEN COUNTY SCADA SYSTEM | 3004.64 | 0 | 3004.64 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-04-01 | 2007-11-01
06-05 | MALLARD POINT PRESSURE | 269.52 | 0 | 269.52 |  | 0% |  |  | 0 | 2006-01-01 | 2006-11-01 | 2006-03-01 | 2007-08-01
06-06 | PARKER'S MILL PUMP & DIESEL | -394.42 | 0 | -394.42 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-03-01 | 2007-10-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 41822904.81 | 33310430 | 8512474.81 | 125.6% | 60.26% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
06-13 | HIGHWAY RELOCATION - CLAYS MILL | 0 | 850000 | -850000 | 0% | 1.538% |  |  | 0 | 2006-01-01 | 2007-04-01 | 2006-07-01 | n/a
12020701 | INCLINE CAR REPLACEMENT AT KRS | 138047.11 | 280709 | -142661.89 | 49.18% | 0.5078% | 194940.26 | 1150000 | -955059.74 | 2007-01-01 | 2009-10-01 | 2007-02-01 | 2008-12-01
12020702 | MAJOR HIGHWAY RELOCATIONS 2007 | -102688.45 | 0 | -102688.45 |  | 0% |  |  | 0 | 2007-01-01 | 2007-12-01 | 2007-03-01
1202-5 | NORTH BROADWAY MAIN REPLACEMENT | 299376.8 | 2350000 | -2050623.2 | 12.74% | 4.251% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
1232-1 | OWENTON CHEMICAL BULK STORAGE | 81520.08 | 824836 | -743315.92 | 9.883% | 1.492% |  |  | 0 | 2008-04-01 | 2009-01-01 | 2008-04-01
1202-6 | CARRICK ROAD MAIN EXTENSION | 62505.52 | 0 | 62505.52 |  | 0% |  |  | 0 | 2008-05-01 | 2009-05-01 | 2008-05-01
12320507 | CHEMICAL FEED IMPROVEMENTS | -37669.8 | 0 | -37669.8 |  | 0% |  |  | 0 | 2005-12-01 | 2006-11-01 | 2006-06-01 | 2007-09-01
|  | 0 | 0 | 0 |  | 0%
|  | 0 | 0 | 0 |  | 0%
|  | 45227743.17 | 41876139 | 3351604.17 | 108%

## 2007
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2007
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2007
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 05-07 | CHEMICAL FEED IMPROVEMENTS | Project design delayed to accommodate Division of Water requirements. | 488756 | 480000 | 2005-12-01 | 2006-11-01 | 2006-06-01 | 2007-09-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 06-04 | OWEN COUNTY SCADA SYSTEM | Construction bids higher than anticipated. Project delayed for programming. | 610985 | 500000 | 2006-02-01 | 2006-12-01 | 2006-04-01 | 2007-11-01
DV | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 3137371 | 5999999.5 | -2862628.5 | 52.29% | 21.88% | [7 empty] | 06-05 | MALLARD POINT PRESSURE | Pump manufacturer delayed delivery of booster station. | 332155 | 325000 | 2006-01-01 | 2006-11-01 | 2006-03-01 | 2007-08-01
A | MAINS - NEW | 489878 | 750000 | -260122 | 65.32% | 2.736% | [7 empty] | 06-06 | PARKER'S MILL PUMP & DIESEL | Project scope expanded in preliminary stage, delayed project start. | 806166 | 350000 | 2006-02-01 | 2006-12-01 | 2006-03-01 | 2007-10-01
B | MAINS - REPLACED/RESTORED | 2473473 | 2249999.74 | 223473.26 | 109.9% | 8.207% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 2238062 | 1655000
C | MAINS - UNSCHEDULED | 101183 | 0 | 101183 |  | 0%
D | MAINS - RELOCATED | 16024 | 0 | 16024 |  | 0%
E | HYDRANTS, VALVES, AND MANHOLES - NEW | 244947 | 520000 | -275053 | 47.11% | 1.897%
F | HYDRANTS, VALVES, AND MANHOLES - REPLACED | 19096 | 100000 | -80904 | 19.1% | 0.3647%
G | SERVICES AND LATERALS - NEW | 1087103 | 1303700 | -216597 | 83.39% | 4.755%
H | SERVICES AND LATERALS - REPLACED | 1242660 | 1200000 | 42660 | 103.6% | 4.377%
I | METERS - NEW | 1701718 | 1150400 | 551318 | 147.9% | 4.196%
J | METERS - REPLACED | 1330358 | 1150000 | 180358 | 115.7% | 4.195%
K | ITS EQUIPMENT AND SYSTEMS | 253947 | 100000 | 153947 | 253.9% | 0.3647%
L | SCADA EQUIPMENT AND SYSTEMS | 59013 | 0 | 59013 |  | 0%
M | SECURITY EQUIPMENT AND SYSTEMS | 0 | 0 | 0 |  | 0%
N | OFFICES AND OPERATIONS CENTERS | 140932 | 80000 | 60932 | 176.2% | 0.2918%
O | VEHICLES | 576684 | 0 | 576684 |  | 0%
P | TOOLS AND EQUIPMENT | 339773 | 154999.5 | 184773.5 | 219.2% | 0.5653%
Q | PROCESS PLANT FACILITIES AND EQUIPMENT | 1127337 | 650000 | 477337 | 173.4% | 2.371%
R | CAPITALIZED TANK REHABILIATION/PAINTING | 4601 | 0 | 4601 |  | 0%
S | ENGINEERING STUDIES | 61018 | 100000 | -38982 | 61.02% | 0.3647%
| TOTAL | 14407116 | 15509098.74 | -1101982.74 | 92.89%
| ENTER ITEM DV AND SUBTRACT | 3137371 | 5999999.5 | -2862628.5
| TOTAL ITEM A - S | 11269745 | 9509099.24 | 1760645.76 | 118.5%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2007
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 5976 | 0 | 5976 |  | 0% |  |  | 0 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-07 | MAJOR HIGHWAY RELOCATIONS | -215782 | 0 | -215782 |  | 0% |  |  | 0 | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 6402.54 | 0 | 6402.54 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | -97.16 | 0 | -97.16 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 694808 | 0 | 694808 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | -16010.01 | 0 | -16010.01 |  | 0% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 1004584 | 0 | 1004584 |  | 0% |  |  | 0 | 2004-01-01 | N/A | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 1232752 | 440000 | 792752 | 280.2% | 1.605% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | -278.43 | 0 | -278.43 |  | 0% |  |  | 0 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
05-01 | GROUND STORAGE TANK - 3.0 MG (342) | 0 | 0 | 0 |  | 0% |  |  | 0 | 2005-07-01 | 2007-12-01
05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | 68037 | 0 | 68037 |  | 0% |  |  | 0 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | 801015 | 553000 | 248015 | 144.8% | 2.017% |  |  | 0 | 2005-04-01 | 2006-12-01 | 2005-04-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 1544166 | 711000 | 833166 | 217.2% | 2.593% |  |  | 0 | 2005-04-01 | 2008-12-01 | 2005-04-01
05-07 | CHEMICAL FEED IMPROVEMENTS | 211772 | 150000 | 61772 | 141.2% | 0.5471% | 488756 | 480000 | 8756 | 2005-12-01 | 2006-11-01 | 2006-06-01 | 2007-09-01
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 5064222 | 3800000 | 1264222 | 133.3% | 13.86% |  |  | 0 | 2005-12-01 | 2007-07-01 | 2005-12-01
06-01 | VALVE HOUSE UPGRADES AT KRS | 89096 | 0 | 89096 |  | 0% |  |  | 0 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | 6319.59 | 0 | 6319.59 |  | 0% |  |  | 0 | 2006-03-01 | 2007-09-01 | 2006-08-01
06-04 | OWEN COUNTY SCADA SYSTEM | 163461 | 0 | 163461 |  | 0% | 610985 | 500000 | 110985 | 2006-02-01 | 2006-12-01 | 2006-04-01 | 2007-11-01
06-05 | MALLARD POINT PRESSURE | 82191 | 0 | 82191 |  | 0% | 332155 | 325000 | 7155 | 2006-01-01 | 2006-11-01 | 2006-03-01 | 2007-08-01
06-06 | PARKER'S MILL PUMP & DIESEL | 749453 | 659000 | 90453 | 113.7% | 2.404% | 806166 | 350000 | 456166 | 2006-02-01 | 2006-12-01 | 2006-03-01 | 2007-10-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 2992224 | 3917000 | -924776 | 76.39% | 14.29% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
06-13 | HIGHWAY RELOCATION - CLAYS MILL | -48 | 100000 | -100048 | -0.048% | 0.3647% |  |  | 0 | 2006-01-01 | 2007-04-01 | 2006-07-01
12020701 | INCLINE CAR REPLACEMENT AT KRS | 56893 | 250000 | -193107 | 22.76% | 0.9118% |  |  | 0 | 2007-01-01 | 2009-10-01 | 2007-02-01
12020702 | MAJOR HIGHWAY RELOCATIONS 2007 | 1811645 | 1000000 | 811645 | 181.2% | 3.647% |  |  | 0 | 2007-01-01 | 2007-12-01 | 2007-03-01
1202-5 | NORTH BROADWAY MAIN REPLACEMENT | 0 | 50000 |  | 0% | 0.1824% |  |  | 0 | 2007-12-01 | 2009-06-01 | 2008-03-01
| KY NRW | 0 | 100000 |  | 0% | 0.3647% |  |  | 0 | 2007-05-01 | 2007-09-01
| SYSTEM-WIDE ENHANCEMENT | 0 | 177707 | -177707 | 0% | 0.6482% |  |  | 0 | 2007-12-01 | 2011-12-01
|  | 16352801.53 | 11907707 | 4595094.53 | 137.3%

## 2006
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2006
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2006
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 98-01 | INTEGRATED RESOURCE PLAN | Completion delayed on source of supply. | 657269 | 350000 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | Construction bids favorable. | 1309064 | 1800000 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
80 | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 6486689.89 | 4500000 | 1986689.89 | 144.1% | 30.09% | [7 empty] | 05-04 | KRS IMPROVEMENTS | Bids favorable. | 191379 | 350000 | 2005-02-01 | 2005-10-01 | 2005-08-01 | 2006-01-01
81 | NETWORK - REPLACEMENT/RENEWAL | 2126150.99 | 650000 | 1476150.99 | 327.1% | 4.347% | [7 empty] | 06-01 | VALVE HOUSE UPGRADES AT KRS | Bids higher than anticipated. | 462866 | 350000 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
82 | NETWORK - EXTENSION | 651508.55 | 460000 | 191508.55 | 141.6% | 3.076% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 2620578 | 2850000
83 | HYDRANTS - REPLACEMENTS | 176730.09 | 26000 | 150730.09 | 679.7% | 0.1739%
84 | HYDRANTS - NEW | 492568.16 | 506000 | -13431.84 | 97.35% | 3.384%
85 | SERVICES - REPLACEMENT | 868071.04 | 525000 | 343071.04 | 165.3% | 3.511%
86 | SERVICES - NEW | 1326577.69 | 1180100 | 146477.69 | 112.4% | 7.892%
87 | METERS - REPLACEMENT | 1297577.01 | 600000 | 697577.01 | 216.3% | 4.012%
88 | METERS - NEW | 1551511.35 | 1118900 | 432611.35 | 138.7% | 7.483%
89 | ITS EQUIPMENT & SYSTEMS | 146309.88 | 100000 | 46309.88 | 146.3% | 0.6687%
90 | OFFICES AND OPERATIONS CENTERS | 79427.87 | 54000 | 25427.87 | 147.1% | 0.3611%
91 | VEHICLES | 694764.72 | 0 | 694764.72 |  | 0%
92 | TOOLS AND EQUIPMENT | 590832.02 | 150000 | 440832.02 | 393.9% | 1.003%
93 | PROCESS PLANT - REPLACEMENTS | 845296.88 | 225000 | 620296.88 | 375.7% | 1.505%
94 | PROCESS PLANT - ADDITIONS | 196118.18 | 50000 | 146118.18 | 392.2% | 0.3344%
95 | TREATMENT MEDIA REPLACEMENT & PROCESS REHAB (if capitalized) | 7020 | 0 | 7020 |  | 0%
96 | TANK REHABILITATION/PAINTING (if capitalized) | 0 | 0 | 0 |  | 0%
97 | COMPREHENSIVE PLANNING STUDIES (if capitalized) | 65926 | 300000 | -234074 | 21.98% | 2.006%
| TOTAL | 17603080.32 | 10445000 | 7158080.32 | 168.5%
| ENTER ITEM 80 AND SUBTRACT | 6486689.89 | 4500000 | 1986689.89
| TOTAL ITEM 81 - 97 | 11116390.43 | 5945000 | 5171390.43 | 187%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2006
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-02 | GROUND STORAGE TANK - 3.0 MG | -731.77 | 0 | -731.77 |  | 0% |  |  | 0 | 2001-03-01 | 2003-12-01 | 2001-02-01 | 2004-08-01
01-03 | SCADA IMPROVEMENTS | 9468.33 | 0 | 9468.33 |  | 0% |  |  | 0 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 209887.82 | 0 | 209887.82 |  | 0% |  |  | 0 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-07 | MAJOR HIGHWAY RELOCATIONS | 215782 | 0 | 215782 |  | 0% |  |  | 0 | 2001-01-01 | 2001-12-01 | 2001-01-01 | 2002-03-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 9770.67 | 0 | 9770.67 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 219992.39 | 0 | 219992.39 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 436623.84 | 180000 | 256623.84 | 242.6% | 1.204% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | 270296.5 | 0 | 270296.5 |  | 0% |  |  | 0 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 30.76 | 0 | 30.76 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 20805.37 | 0 | 20805.37 |  | 0% |  |  | 0 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS (343) | 478850.85 | 530000 | -51149.15 | 90.35% | 3.544% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 543523.25 | 170000 | 373523.25 | 319.7% | 1.137% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | -208706.93 | 700000 | -908706.93 | -29.82% | 4.681% | 632906 | 1190593 | -557687 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
05-01 | GROUND STORAGE TANK - 3.0 MG (342) | 0 | 750000 | -750000 | 0% | 5.016% |  |  | 0 | 2005-07-01 | 2007-12-01
05-02 | RUSSELL CAVE ROAD MAIN - 34,000' OF 12" (343) | 799571.91 | 800000 | -428.09 | 99.95% | 5.35% | 1309064 | 1800000 | -490936 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-04 | KRS IMPROVEMENTS | -8512.91 | 0 | -8512.91 |  | 0% | 191379 | 350000 | -158621 | 2005-02-01 | 2005-10-01 | 2005-08-01 | 2006-01-01
05-05 | REPLACE TRAC-VAC SYSTEM AT RRS (332) | 339611.53 | 725000 | -385388.47 | 46.84% | 4.848% |  |  | 0 | 2005-04-01 | 2006-12-01 | 2005-04-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 314092.75 | 0 | 314092.75 |  | 0% |  |  | 0 | 2005-04-01 | 2008-12-01 | 2005-04-01
05-07 | CHEMICAL FEED IMPROVEMENTS | 276984 | 228460 | 48524 | 121.2% | 1.528% |  |  | 0 | 2005-12-01 | 2006-11-01 | 2006-06-01
05-08 | KENTUCKY RELIABILITY IMPROVEMENT | 944837.33 | 25000 | 919837.33 | 3779% | 0.1672% |  |  | 0 | 2005-12-01 | 2007-07-01 | 2005-12-01
06-01 | VALVE HOUSE UPGRADES AT KRS | 380264.17 | 350000 | 30264.17 | 108.6% | 2.341% | 462866 | 350000 | 112866 | 2006-01-01 | 2006-12-01 | 2006-01-01 | 2006-12-01
06-02 | YARNALLTON ROAD MAIN EXTENSION | 23300 | 50000 | -26700 | 46.6% | 0.3344% |  |  | 0 | 2006-03-01 | 2007-09-01 | 2006-08-01
06-04 | OWEN COUNTY SCADA SYSTEM | 447523.83 | 0 | 447523.83 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-04-01
06-05 | MALLARD POINT PRESSURE | 249694.67 | 0 | 249694.67 |  | 0% |  |  | 0 | 2006-01-01 | 2006-11-01 | 2006-03-01
06-06 | PARKER'S MILL PUMP & DIESEL | 57400 | 0 | 57400 |  | 0% |  |  | 0 | 2006-02-01 | 2006-12-01 | 2006-03-01
06-07 | NEW WTP POOL 3 OF KENTUCKY | 1676933.11 | 0 | 1676933.11 |  | 0% |  |  | 0 | 2006-05-01 | 2010-12-01 | 2006-05-01
06-13 | HIGHWAY RELOCATION - CLAYS MILL | 47.71 | 0 | 47.71 |  | 0% |  |  | 0 | 2006-01-01 | 2007-04-01 | 2006-07-01
92-12 | BLUEGRASS WATER PROJECT | 37268.77 | 0 | 37268.77 |  | 0% |  |  | 0 | 1992-07-01 | 1996-12-01 | 1992-09-01
98-01 | INTEGRATED RESOURCE PLAN | 15839.97 | 0 | 15839.97 |  | 0% | 657269 | 350000 | 307269 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
|  | 7760449.92 | 4508460 | 3251989.92 | 172.1%

## 2005
Kentucky American Water
Case No. 2015-00418 | [20 empty] | PSC Data Request 1
Construction Projects | [20 empty] | Item 11b
|  |  | As of | 2005
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________ | [13 empty] | KENTUCKY AMERICAN WATER - COMPARISON OF ACTUAL VS. BUDGETED CONSTRUCTION EXPENDITURES -
[11 empty] | Witness Responsible: | [7 empty] | FOR THE YEAR 2005
Brent O'Neill
ORIGINAL
[17 empty] | ACTUAL | INVESTMENT | ORIGINAL
[7 empty] | Total | Total |  | Date | Date | [5 empty] | PROJECT | PROJECT | BUDGET
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date |  | INVESTMENT PROJECTS | EXPLANATION | COST | COST | START | END | START | END
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual | 01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | Property acquisition longer than anticipated. | 1755786 | 1300000 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End | 03-01 | ELEVATED STORAGE TANK - 2.0 MG | On schedule, construction costs higher than anticipated. | 3744744 | 3000000 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
80 | DEVELOPER/GOVERNMENTAL CONTRIBUTIONS | 6000465.36 | 4080000 | 1920465.36 | 147.1% | 23.71% | [7 empty] | 03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | Equipment delivery delayed on switchgear. | 999181 | 1320000 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
81 | NETWORK - REPLACEMENT/RENEWAL | 489069.49 | 600000 | -110930.51 | 81.51% | 3.486% | [7 empty] | 01-03 | SCADA IMPROVEMENTS | Delay in completing programming. | 675097 | 650000 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
82 | NETWORK - EXTENSION | 676942.06 | 255000 | 421942.06 | 265.5% | 1.482% | [8 empty] | GRAND TOTAL COMPLETED BP'S |  | 7174808 | 6270000
83 | HYDRANTS - REPLACEMENTS | 23369.65 | 25500 | -2130.35 | 91.65% | 0.1482%
84 | HYDRANTS - NEW | 547823.42 | 300000 | 247823.42 | 182.6% | 1.743%
85 | SERVICES - REPLACEMENT | 738960.46 | 500000 | 238960.46 | 147.8% | 2.905%
86 | SERVICES - NEW | 1281489.73 | 1157000 | 124489.73 | 110.8% | 6.723%
87 | METERS - REPLACEMENT | 485925.15 | 416800 | 69125.15 | 116.6% | 2.422%
88 | METERS - NEW | 1064680.58 | 1121500 | -56819.42 | 94.93% | 6.517%
89 | ITS EQUIPMENT & SYSTEMS | 81510.92 | 75500 | 6010.92 | 108% | 0.4387%
90 | OFFICES AND OPERATIONS CENTERS | 93531.1 | 55000 | 38531.1 | 170.1% | 0.3196%
91 | VEHICLES | 6532.95 | 0 | 6532.95 |  | 0%
92 | TOOLS AND EQUIPMENT | 202115.7 | 160000 | 42115.7 | 126.3% | 0.9297%
93 | PROCESS PLANT - REPLACEMENTS | 441262.88 | 350000 | 91262.88 | 126.1% | 2.034%
94 | PROCESS PLANT - ADDITIONS | 10170.33 | 50000 | -39829.67 | 20.34% | 0.2905%
95 | TREATMENT MEDIA REPLACEMENT & PROCESS REHAB (if capitalized) | 167211.77 | 0 | 167211.77 |  | 0%
96 | TANK REHABILITATION/PAINTING (if capitalized) | 0 | 0 | 0 |  | 0%
97 | COMPREHENSIVE PLANNING STUDIES (if capitalized) | 0 | 0 | 0 |  | 0%
| TOTAL | 12311061.55 | 9146300 | 3164761.55 | 134.6%
| ENTER ITEM 80 AND SUBTRACT | 6000465.36 | 4080000 | 1920465.36
| TOTAL ITEM 81 - 97 | 6310596.19 | 5066300 | 1244296.19 | 124.6%
Kentucky American Water
Case No. 2015-00418
Construction Projects
|  |  | As of | 2005
Type of Filing:_X__Original _____Updated _____Revised | [10 empty] | Schedule 1
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
[7 empty] | Total | Total |  | Date | Date
|  |  | Annual |  |  | Percent | Actual | Budget |  | Original | Original | Date | Date
|  | Annual | Original | Variance | Variance | of | Project | Project |  | Budget | Budget | Actual | Actual
Item | Description | Actual | Budget | Dollars | Percent | Budget | Cost | Cost | Variance | Start | End | Start | End
BUDGET PROJECTS
01-02 | GROUND STORAGE TANK - 3.0 MG | 11297.5 | 0 | 11297.5 |  | 0% |  |  | 0 | 2001-03-01 | 2003-12-01 | 2001-02-01 | 2004-08-01
01-03 | SCADA IMPROVEMENTS | 7866.43 | 0 | 7866.43 |  | 0% | 675097 | 650000 | 25097 | 2001-01-01 | 2003-05-01 | 2002-09-01 | 2005-12-01
01-05 | RUSSELL CAVE ROAD TANK - 1.0 MG | 928000.47 | 766600 | 161400.47 | 121.1% | 4.454% | 1755786 | 1300000 | 455786 | 2001-01-01 | 2004-12-01 | 2001-02-01 | 2005-12-01
01-11 | NEW COLUMBUS PROJECT | 22612.72 | 0 | 22612.72 |  | 0% |  |  | 0 | 2001-10-01 | 2003-05-01 | 2002-02-01
02-01 | LEESTOWN ROAD MAIN IMPROVEMENTS | 9467.02 | 0 | 9467.02 |  | 0% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2002-03-01
02-02 | 2002 MAJOR HIGHWAY RELOCATIONS | 446.31 | 0 | 446.31 |  | 0% |  |  | 0 | 2002-01-01 | 2002-12-01 | 2002-01-01 | 2002-11-01
02-03 | REPLACE TRAVELLING SCREEN & HOUSING | 11979.81 | 0 | 11979.81 |  | 0% |  |  | 0 | 2002-08-01 | 2003-04-01 | 2003-12-01
02-04 | SOURCE OF SUPPLY DEVELOPMENT | 136001.48 | 1500000 | -1363998.52 | 9.067% | 8.716% |  |  | 0 | 2002-04-01 | 2003-12-01 | 2001-06-01
03-01 | ELEVATED STORAGE TANK - 2.0 MG | 3032909.37 | 2180000 | 852909.37 | 139.1% | 12.67% | 3744744 | 3000000 | 744744 | 2003-05-01 | 2005-12-01 | 2003-07-01 | 2005-12-01
03-02 | MAJOR HIGHWAY RELOCATIONS | 17816.69 | 0 | 17816.69 |  | 0% |  |  | 0 | 2003-01-01 | 2003-12-01 | 2003-01-01 | 2003-10-01
03-03 | ELECTRICAL & RELIABILITY IMPROVEMENTS | 257105.57 | 219800 | 37305.57 | 117% | 1.277% | 999181 | 1320000 | -320819 | 2003-01-01 | 2004-07-01 | 2003-06-01 | 2005-12-01
04-02 | MAJOR HIGHWAY RELOCATIONS | 1271759.76 | 910000 | 361759.76 | 139.8% | 5.288% |  |  | 0 | 2004-01-01 | n/a | n/a | n/a
04-03 | OWEN COUNTY MAIN EXTENSIONS (343) | 214796.9 | 240000 | -25203.1 | 89.5% | 1.395% |  |  | 0 | 2004-10-01 | 2007-12-01 | 2004-10-01
04-04 | BUSINESS PROCESS EFFCIENCY PROJECT & ORCOM BUDGET | 0 | 1322035 | -1322035 | 0% | 7.682% |  |  | 0 | 2004-01-01 | 2004-12-01 | 2004-01-01 | 2006-01-01
04-06 | REPLACE FILTER MEDIA 3 & 4 | 1294.28 | 0 | 1294.28 |  | 0% |  |  | 0 | 2005-03-01 | 2005-07-01 | 2004-09-01 | 2004-12-01
05-01 | GROUND STORAGE TANK - 3.0 MG (342) | 0 | 75000 | -75000 | 0% | 0.4358% |  |  | 0 | 2005-07-01 | 2007-12-01
05-02 | RUSSELL CAVE ROAD MAIN | 392914.33 | 500000 | -107085.67 | 78.58% | 2.905% |  |  | 0 | 2005-04-01 | 2007-12-01 | 2005-08-01 | 2006-12-01
05-04 | KRS VALVE MECHANICAL IMPROVEMENT | 199892.31 | 350000 | -150107.69 | 57.11% | 2.034% |  |  | 0 | 2005-02-01 | 2005-10-01 | 2005-08-01 | 2006-01-01
05-05 | REPLACE TRAC-VAC SYSTEM | 340.85 | 0 | 340.85 |  | 0% |  |  | 0 | 2005-04-01 | 2006-12-01 | 2005-04-01
05-06 | SLUDGE HANDLING IMPROVEMENT | 12041.25 | 0 | 12041.25 |  | 0% |  |  | 0 | 2005-04-01 | 2008-12-01 | 2005-04-01
92-12 | BLUEGRASS WATER PROJECT | 6754.25 | 0 | 6754.25 |  | 0% |  |  | 0 | 1992-07-01 | 1996-12-01 | 1992-09-01
96-19 | CUSTOMER SERVICE SOFTWARE | 55.57 | 0 | 55.57 |  | 0% |  |  | 0 | 1996-12-01 | 1999-06-01 | 1996-11-01 | 2003-12-01
98-01 | INTEGRATED RESOURCE PLAN | 31183.95 | 0 | 31183.95 |  | 0% |  |  | 0 | 1998-02-01 | 1999-09-01 | 1999-02-01 | 2006-12-01
98-08 | SURGE PROTECTION KRS | 1754.19 | 0 | 1754.19 |  | 0% |  |  | 0 | 1998-04-01 | 1999-11-01 | 1998-08-01
|  | 6568291.01 | 8063435 | -1495143.99 | 81.46%