## Table 3
Table 3: Breakdown of Investments within DA Plan — 2016–2022
(All Dollars in Thousands)
DA Plan Detail |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total Spend
Reclosers | $ |  | 7120 | 21672 | 20675 | 17608 | 17608 | 17617 | 102300
DMS/DSCADA |  | 2017: 2500; 2018: 2922; (All Dollars in Thousands) 2019: 700 | 6122
Communication |  | 80 | 800 | 656 | 625 | 595 | 595 | 584 | 3935
Total | $ | 80 | 10420 | 25250 | 22000 | 18203 | 18203 | 18201 | 112357

## Table 4
Table 4 - Proposed Revision to the Companies DA Program Schedule
(All Dollars in Thousands)
DA Plan Detail | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total Spend
Reclosers |  |  | 7120 | 21672 | 20675 | 17608 | 17608 | 17617 | 102300
DMS/DSCADA | 2500 | 2922 | 700 | [5 empty] | 6122
Communication | 205 | 61 | 800 | 656 | 625 | 595 | 595 | 584 | 4121
Total | 2705 | 2983 | 8620 | 22328 | 21300 | 18203 | 18203 | 18201 | 112543
Note: assume communication reduction by $595 for 2017 and 2018 to reflect recloser delay

## Table 5
Table 5 - Reduction to FFTY DA Expenditures from Recloser Delay
(All Dollars in Thousands)
DA Plan Investment | 2017 | 2018 | FFTY
Company Proposed Reclosers | 7120 | 21672 | 14396
Recommended Recloser Delay | 0 | 0 | 0
Adjustment to FERC Acct 365 | -7120 | -21672 | -14396
Company Proposed Communication | 800 | 656 | 728
Recommended Recloser Delay | 205 | 61 | 133
Adjustment to FERC Acct 397 | -595 | -595 | -595

## Table 6
Table 6 - Reduction to FFTY DA Expenditures from Recloser Delay for KU and LG&E Electric Distribution
(All Dollars in Thousands)
DA Plan Investment | 2017 | 2018 | FFTY
Proposed KU Recloser Investment | 2848 | 8668.8 | 5758.4 | 0.4
Proposed LG&E Recloser Investment | 4272 | 13003.2 | 8637.6 | 0.6
Overall Account 365 Adjustment | -7120 | -21672 | -14396
Overall Account 397 Adjustment | -595 | -595 | -595
KU Account 365 Adjustment | -2848 | -8668.8 | -5758.4
KU Account 397 Adjustment | -238 | -238 | -238 | 0.4
LG&E Account 365 Adjustment | -4272 | -13003.2 | -8637.6
LG&E Account 397 Adjustment | -357 | -357 | -357 | 0.6
For 2017 and 2018 investment on a KU/LG&E basis see 2016-00370 PSC1-54, ratio used to allocate adjustment
| KU 5 year reclosers | 40440 | 0.4
| LG&E 5 year reclosers | 60660 | 0.6
| Total | 101100

## KU DA
Financial Summary for
Distribution Automation KU
Project Number
Electric Distribution: Denise Simon
KU
Financial Analysis - Project Summary | RECOMMEND-ATION | Alternative #2 (Recloser/Contingency Upgrades) | Alternative #2 | Alternative #3
Total Capital Expenditures Requested, $000s | 42494 | 40440 | 0 | 0
Total Cost Savings/(Incremental Costs), $000s | 2310.3651 | -18763.389 | -176285.3245 | 0
NPV Revenue Requirements, $000s | 43918.5212 | 48601.7133 | 51714.892 | 0
NPV Cash Flows (unlevered), $000s | 203.1986 | 182.365 | 0 | 0
IRR (unlevered) | 6.582% | 6.577% | 0% | 0%
ROE | 0% | 0% | 0% | 0%
RECOMMENDATION
| 5-Year Total | [5 empty] | Life
Financial Analysis - By Year | 2016-2020 | 2016 | 2017 | 2018 | 2019 | 2020 | 2016-2051
Capital Expenditures Requested, $000s | 27932 | 32 | 3168 | 8931 | 8520 | 7281 | 42494
Cost Savings/(Incremental Costs), $000s | 37 | 0 | 0 | -4 | 12 | 29 | 960.0986
EBIT, $000s | 4600.6471 | 0.62566 | 374.6744 | 653.3077 | 1541.459 | 2030.5804 | 0
Net Income, $000s | 2188.3259 | 0 | 198.7889 | 282.2185 | 742.1675 | 965.151 | 0
ROE | 7.929% | 0% | 14.68% | 7.371% | 7.293% | 8.098% | 0%
NPVRR general rules:
If the NPV is zero, the IRR should be equal to the 'hurdle rate' or cost of capital (6.49%). If the NPV is positive, the IRR should be greater than the cost of capital.
If the NPV is negative, the IRR should be less than the cost of capital. Projects that have a positive NPV and IRR greater than the cost of
capital earn a rate of return higher than the borrowing cost of the capital being spent.
The NPVRR is the present value of the cost to the customer, so the option with the lowest NPVRR is best. NPVRR can be negative if savings are put into the model,
in which case the biggest negative number is best as it represents the most benefit to the customer.
Note Summary from PSC 1-54

## LGE DA
Financial Summary for
Distribution Automation LGE
Project Number
Electric Distribution: Denise Simon
KU
Financial Analysis - Project Summary | RECOMMEND-ATION | Recloser/Contingency Upgrades | Do Nothing | Alternative #3
Total Capital Expenditures Requested, $000s | 63741 | 60660 | 0 | 0
Total Cost Savings/(Incremental Costs), $000s | 3425.7555 | -25991.496 | -264427.9867 | 0
NPV Revenue Requirements, $000s | 66843.6803 | 73593.1248 | 81435.4009 | 0
NPV Cash Flows (unlevered), $000s | 328.2805 | 284.6609 | 0 | 0
IRR (unlevered) | 6.586% | 6.578% | 0% | 0%
ROE | 0% | 0% | 0% | 0%
RECOMMENDATION
| 5-Year Total | [5 empty] | Life
Financial Analysis - By Year | 2016-2020 | 2016 | 2017 | 2018 | 2019 | 2020 | 2016-2053
Capital Expenditures Requested, $000s | 41899 | 48 | 4752 | 13397 | 12780 | 10922 | 63741
Cost Savings/(Incremental Costs), $000s | 54 | 0 | -1 | -6 | 18 | 43 | 1424.4675
EBIT, $000s | 6933.8023 | 0.9385 | 559.8745 | 991.0321 | 2322.1736 | 3059.7837 | 0
Net Income, $000s | 3299.8343 | 0 | 296.8277 | 429.7981 | 1118.5479 | 1454.6606 | 0
ROE | 7.951% | 0% | 14.6% | 7.412% | 7.332% | 8.11% | 0%
NPVRR general rules:
If the NPV is zero, the IRR should be equal to the 'hurdle rate' or cost of capital (6.49%). If the NPV is positive, the IRR should be greater than the cost of capital.
If the NPV is negative, the IRR should be less than the cost of capital. Projects that have a positive NPV and IRR greater than the cost of
capital earn a rate of return higher than the borrowing cost of the capital being spent.
The NPVRR is the present value of the cost to the customer, so the option with the lowest NPVRR is best. NPVRR can be negative if savings are put into the model,
in which case the biggest negative number is best as it represents the most benefit to the customer.
Note Summary from PSC 1-54