## Exhibit EGP5
Year | Original Exhibit 9, 5 Year Cycle (Case No 2014-00396) | Recommend Proposal (Case No. 2017-00179) 5 Year Cycle | Alternative Considered (Case No. 2017-00179) 6 Year Cycle
2015 | 22327777 | 23067891 | 23067891
2016 | 27664598.1635 | 27774546 | 27774546
2017 | 27661948.9583 | 27661059.5057 | 27661059.5057
2018 | 27664088.5401 | 21638765.6875 | 19573483.1052
2019 | 21534740 | 21283946.0477 | 19612726.7189
2020 | 16039442.7544 | 21472776.9236 | 19783616.0869
2021 | 15879048.3268 | 21688685.327 | 19969975.9268
2022 | 15720257.8436 | 21881311.7194 | 20158199.0577
2023 | 15563055.2651 | 22101559.281 | 20348304.3931
2024 |  |  | 20540310.8
TOTAL | 190054956.8517 | 208570541.492 | 218490112.5943
3 year Average (2018, 2019, 2020) | 21746090 | 21465162.8863 | 19656608.637
Cost for Cycle after 2018 | 15880652 | 21685655.8598 | 20068855.4972
Avg Yrs Growth for Cycle | - | 4.9375 | 5.6524

## 2017 5 Yr Plan
2017 Projected Plan to Transition to 5 Year Cycle with Initial Clear Completed by April 1, 2018
Average Year Tree Growth for Recommended 2017 Plan
Year | Miles Cut |  | Tot. Mi. Cut | T1 Cuml. Mi. | Variance | 5 Yr Cycle |  | Years Growth
| T1 | T2 |  |  |  | Year | T2 Offset
2010 | 345 |  | 345 | 345 | -89 | 2015 | -89 | 4.79
2011 | 942 |  | 942 | 1287 | 142 | 2016 | 142 | 5.12
2012 | 866 |  | 866 | 2153 | 695 | 2017 | 695 | 5.422
2013 | 831 |  | 831 | 2984 | 46.6149 | 2018 | 46.6149 | 5.0287
2014 | 1155 |  | 1155 | 4139 | -421.3636 | 2019 | -421.3636 | 4.7404
2015 | 1402 | 434 | 1836 | 5541 | -207.3956 | 2020 | -207.3956 | 4.8721
2016 | 1093.8302 | 711 | 1804.8302 | 6634.8302 | -25.5443 | 2021 | -25.5443 | 4.9843
2017 | 1333.9999 | 313 | 1646.9999 | 7968.8301 | -0.57571 | 2022 | -0.57571 | 4.9996
2018 | 144 | 1479.3852 | 1623.3852 | 8112.8302 | -0.16971 | 2023 | -0.16971 | 4.9999
Sum | 8112.8302 | 2937.3851
|  |  | Average Yrs Growth for 2018 -2023 = |  |  |  |  | 4.9375
Review of Miles Trimmed and Funding Requirements
2017 Projected Plan to Transition to 5 Year Cycle - Miles of Re-clear | [14 empty] | 2017 Projected Plan to Transition to 5 Year Cycle - Funding Requirements
| 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 |  | 2016 | Internal Labor | Total Cost/Mile
[23 empty] | Task 1 | 17089329.96 | 403475.95 | 15992.25
Yr 1 Miles | 345 |  |  |  |  | 434 |  |  |  | 1622.9785 |  |  |  |  | Yr 1 Miles |  |  | 21283946.0477 |  |  |  |  | Task 2 | 9979139.28 | 302600.29 | 14460.9558
Yr 2 Miles |  | 942 |  |  |  |  | 711 |  |  |  | 1622.032 |  |  |  | Yr 2 Miles |  |  |  | 21472776.9236 |  |  |  | Task 2 Rev | 8009850.02 | 302600.29 | 11691.21
Yr 3 Miles |  |  | 866 |  |  |  |  | 313 |  |  |  | 1622.9788 |  |  | Yr 3 Miles | 4004999.8731 |  |  |  | 21688685.327
Yr 4 Miles |  |  |  | 831 |  |  |  |  | 1479.3852 |  |  |  | 1622.0314 |  | Yr 4 Miles |  | 19219117.7124 |  |  |  | 21881311.7194
Yr 5 Miles |  |  |  |  | 1155 | [8 empty] | 1622.9792 | Yr 5 Miles | [6 empty] | 22101559.281 |  | Task 1 | Task 2 & 3 | Annual Cost
Yr 6 Miles | [5 empty] | 1402 | [8 empty] | Yr 6 Miles | [7 empty] | 2018 | 16803.1051 | 12991.2874 | 21638765.6875
Yr 7 Miles | [6 empty] | 1093.8302 | [7 empty] | Yr 7 Miles | [7 empty] | 2019 | 16971.1362 | 13114.1273 | 21283946.0477
Yr 8 Miles | [7 empty] | 1333.9999 | [6 empty] | Yr 8 Miles | 23656059.6325 | [6 empty] | 2020 | 17140.8475 | 13238.1956 | 21472776.9236 | (3 Contractors) | 6831.32
Yr 9 Miles | [8 empty] | 144 | [5 empty] | Yr 9 Miles |  | 2419647.9751 | [5 empty] | 2021 | 17312.256 | 13363.5046 | 21688685.327 | Mileage | 168
Program Miles | 345 | 942 | 866 | 831 | 1155 | 1836 | 1805 | 1646.9999 | 1623.3852 | 1622.9785 | 1622.032 | 1622.9788 | 1622.0314 | 1622.9792 | Program Miles | 27661059.5057 | 21638765.6875 | 21283946.0477 | 21472776.9236 | 21688685.327 | 21881311.7194 | 22101559.281 | 2022 | 17485.3786 | 13490.0667 | 21881311.7194 | Total | 1147661.76
[23 empty] | 2023 | 17660.2323 | 13617.8944 | 22101559.281
[6 empty] | Task 1 - Initial Re-clear | [11 empty] | Task 1 - Initial Re-clear
[6 empty] | Task 2 - Interim Re-clear | [11 empty] | Task 2 - Interim Re-Clear
[6 empty] | Task 3 - 5 Year Cycle Trim | [11 empty] | Task 3 - 5 Year Cycle Trim

## 2017 Alternative 6 Yr Plan
Alternative 2017 Projected Plan to Transition to 6 Year Cycle with Initial Clear Completed by April 1, 2018
Averager Year Tree Growth for Alternative Plan
Year | Miles Cut |  | Tot. Mi. Cut | T1 Cuml. Mi. | Variance | 5 Yr Cycle |  | Years Growth
| T1 | T2 |  |  |  | Year | T2 Offset
2010 | 345 |  | 345 | 345 | -89 | 2015 | -89 | 4.79
2011 | 942 |  | 942 | 1287 | 142 | 2016 | 142 | 5.12
2012 | 866 |  | 866 | 2153 | 695 | 2017 | 695 | 5.4594
2013 | 831 |  | 831 | 2984 | 331.5385 | 2018 | 331.5385 | 5.2091
2014 | 1155 |  | 1155 | 4139 | 133.5886 | 2019 | 133.5886 | 5.0987
2015 | 1402 | 434 | 1836 | 5541 | 617.5787 | 2020 | 617.5787 | 5.4568
2016 | 1093.8302 | 711 | 1804.8302 | 6634.8302 | 1070.3991 | 2021 | 1070.3991 | 5.7917
2017 | 1333.9999 | 313 | 1646.9999 | 7968.8301 | 1365.3893 | 2022 | 1365.3893 | 6.0099
2018 | 144 | 1194.4615 | 1338.4615 | 8112.8301 | 1351.8411 | 2023 | 1351.8411 | 5.9999
2019 |  | 1353 | 1353 |  | 1353 | 2024 | 1353 | 6.0007
Sum | 8112.8301 | 2652.4615 | Average Yrs Growth for 2018-2023 = |  |  |  |  | 5.6524
Review of Miles Trimmed and Funding Requirements
Alternative 2017 Projected Plan toTransition to 6 Year Cycle - Circuit Miles Re-Cleared | [15 empty] | Alternative 2017 Projected Plan to Transition to 6 Year Cycle - Funding Requirements
| 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |  | 2016 | Internal Labor |  | Total Cost/Mile
[25 empty] | Task 1 | 17089329.96 | 403475.95 |  | 15992.25
Yr 1 Miles | 345 |  |  |  |  | 434 |  |  |  | 1352.9499 | [5 empty] | Yr 1 Miles |  |  | 19612726.7189 | [5 empty] | Task 2 | 9979139.28 | 302600.29 |  | 14460.9558
Yr 2 Miles |  | 942 |  |  |  |  | 711 |  |  |  | 1352.0099 |  |  |  |  | Yr 2 Miles |  |  |  | 19783616.0869 |  |  |  |  | Task 2 Rev | 8009850.02 | 302600.29 |  | 11691.21
Yr 3 Miles |  |  | 866 |  |  |  |  | 313 |  |  |  | 1352.0098 |  |  |  | Yr 3 Miles | 4004999.8731 |  |  |  | 19969975.9268
Yr 4 Miles |  |  |  | 831 |  |  |  |  | 1194.4615 |  |  |  | 1352.0097 |  |  | Yr 4 Miles |  | 17153835.9703 |  |  |  | 20158199.0577
Yr 5 Miles |  |  |  |  | 1155 | [8 empty] | 1352.0096 |  | Yr 5 Miles | [6 empty] | 20348304.3931 |  |  | Task 1 | 5 yr Cycle | 6 yr Cycle | Annual Cost
Yr 6 Miles | [5 empty] | 1402 | [8 empty] | 1352.0096 | Yr 6 Miles | [7 empty] | 20540310.8 | 2018 | 16803.1051 | 12283.9894 | 14361.146 | 19573483.1052
Yr 7 Miles | [6 empty] | 1093.8302 | [8 empty] | Yr 7 Miles | [8 empty] | 2019 | 16971.1362 | 12406.8293 | 14496.2699 | 19612726.7189
Yr 8 Miles | [7 empty] | 1333.9999 | [7 empty] | Yr 8 Miles | 23656059.6325 | [7 empty] | 2020 | 17140.8475 | 12530.8976 | 14632.745 | 19783616.0869 | (3 Contractors) | 6831.32
Yr 9 Miles | [8 empty] | 144 | [6 empty] | Yr 9 Miles |  | 2419647.1349 | [6 empty] | 2021 | 17312.256 | 12656.2066 | 14770.5849 | 19969975.9268 | Mileage | 168
Program Miles | 345 | 942 | 866 | 831 | 1155 | 1836 | 1805 | 1512.977 | 1585.3402 | 1352.9499 | 1352.0099 | 1352.0098 | 1352.0097 | 1352.0096 | 1352.0096 | Program Miles | 27661059.5057 | 19573483.1052 | 19612726.7189 | 19783616.0869 | 19969975.9268 | 20158199.0577 | 20348304.3931 | 20540310.8 | 2022 | 17485.3786 | 12782.7686 | 14909.8031 | 20158199.0577 | Total | 1147661.76
[25 empty] | 2023 | 17660.2323 | 12910.5963 | 15050.4136 | 20348304.3931
[6 empty] | Task 1 - Initial Re-clear | [12 empty] | Task 1 - Initial Re-clear | [5 empty] | 2024 | 17836.8347 | 13039.7023 | 15192.4301 | 20540310.8
[6 empty] | Task 2 - Interim Re-clear | [12 empty] | Task 2 - Interim Re-clear
[6 empty] | Task 3 - 5 Year Cycle Trim | [12 empty] | Task 3 - 5 Year Cycle Trim