## KY 2017 1-18
Atmos Energy Corporation
CWIP Analysis
**Please note that the estimate includes the last approved estimate routed for approval which does not include AIC and reimbursements.
Actuals do include AIC and reimbursements since they are part of our total project charges.
Month | Project | Project Description | Est. start date | Est. complete date | Orginal Budget Estimate | Most Recent Budget Estimate | Total Project CWIP Expenditures As of August 31, 2017 | Project Type
201601 | 050.33000 | 050.2612 KY YZ Covers | 2012-12-06 | 2015-09-30 | 14354.4 | 14354.4 | 10736.28 | Non Functional
201601 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201601 | 050.39380 | 2612.Emergency Regs.KY.15 | 2015-04-01 | 2015-09-30 | 30125.55 | 30125.55 | 29027.66 | Non Functional
201601 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-03-30 | 4431548.97 | 16281504.53 | 17661536.23 | Non Functional
201601 | 050.39688 | 050.2734.HPDRiverRelocAdvl | 2014-11-01 | 2016-02-02 | 64381.86 | 64381.86 | 21527.37 | Non Functional
201601 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201601 | 050.40278 | Calvert Purchase Upgrade | 2014-09-22 | 2016-03-30 | 23946.76 | 23946.76 | 16715.74 | Non Functional
201601 | 050.40471 | PRP.2734.Crewdson Ln. | 2015-05-30 | 2016-05-30 | 1065458.52 | 1065458.52 | 928535.9 | Non Functional
201601 | 050.40596 | 050.2739.McCormack Ext. | 2015-05-08 | 2016-02-29 | 15018.69 | 15018.69 | 11152.05 | Non Functional
201601 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-09-28 | 94340.72 | 94340.72 | 63111 | Non Functional
201601 | 050.40693 | 050.2735.TB1Reloc.HorseCave | 2015-06-15 | 2016-06-30 | 265806.85 | 265806.85 | -48557.25 | Non Functional
201601 | 050.40733 | 050.2636.Avondale Reg. Repl. | 2015-06-18 | 2016-06-30 | 30420.87 | 55882.71 | 54907.83 | Non Functional
201601 | 050.40779 | PRP.2734.Centerline Phase 2 | 2015-07-20 | 2016-07-30 | 504034.42 | 4629705.8 | 4505927.78 | Non Functional
201601 | 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 2015-08-03 | 2016-02-29 | 192654.19 | 192654.19 | 4075.36 | Non Functional
201601 | 050.40986 | PRP.2609.Dawson Springs | 2015-08-13 | 2016-06-30 | 505547.54 | 1709928.9 | 1678291.46 | Non Functional
201601 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201601 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201601 | 050.41124 | 050.2734.KY 181 PI elkton | 2015-09-01 | 2016-03-31 | 403522.8 | 467284.84 | 445847.63 | Non Functional
201601 | 050.41195 | PRP.2637.N.14th St Phase 2 | 2015-10-01 | 2015-12-31 | 460314.1 | 460314.1 | 413948.36 | Non Functional
201601 | 050.41199 | PRP.2736.E.7th St. | 2015-10-01 | 2016-03-15 | 212134.44 | 212134.44 | 115480.68 | Non Functional
201601 | 050.41227 | Hardeman TB Replace | 2015-10-01 | 2016-04-30 | 76606.5 | 76606.5 | 36443.95 | Non Functional
201601 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201601 | 050.41238 | Replace Relief Valve | 2015-10-01 | 2016-02-28 | 68157.98 | 68157.98 | 40284.62 | Non Functional
201601 | 050.41248 | Trunkline Wtr Bath Htr | 2015-10-01 | 2016-07-30 | 215687.98 | 215687.98 | 116444.76 | Non Functional
201601 | 050.41251 | 050.2738.Campbellsville Reinf | 2015-10-01 | 2016-02-19 | 529562.14 | 529562.14 | 200226.31 | Non Functional
201601 | 050.41280 | PRP.2634.US Hwy 41 | 2015-10-01 | 2016-04-30 | 136509.73 | 136509.73 | 84463.06 | Non Functional
201601 | 050.41596 | 2636.Owensboro.WMR.FY16 | 2015-10-01 | 2016-09-30 | 1067365.32 | 1067365.32 | 1116028.55 | Non Functional
201601 | 050.41599 | 2602.KY.MDT.Replacements.FY16 | 2015-11-01 | 2016-03-31 | 261675 | 261675 | 253108.12 | Non Functional
201601 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201601 | 050.41614 | 2612.Modems.Upgrade.KY.FY16 | 2015-10-01 | 2016-06-30 | 23342.1 | 23342.1 | 26690.89 | Non Functional
201601 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201601 | 050.41620 | 2609.Equipment.Purchases.FY16 | 2015-10-01 | 2016-02-29 | 49420.8 | 49420.8 | 48734.26 | Non Functional
201601 | 050.41621 | Madisonville.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 25977.6 | 25977.6 | 24775.79 | Non Functional
201601 | 050.41622 | Princeton.Equipment.FY16 | 2015-10-01 | 2016-09-28 | 20275.2 | 20275.2 | 16063.5 | Non Functional
201601 | 050.41624 | Paducah.Equipment.FY16 | 2015-10-01 | 2016-04-30 | 37762.56 | 37762.56 | 32999.27 | Non Functional
201601 | 050.41626 | Shelbyville.KY.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 34214.4 | 34214.4 | 33925.41 | Non Functional
201601 | 050.41627 | Campbellsville.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 60192 | 60192 | 61662.15 | Non Functional
201601 | 050.41628 | Danville.Equipment.FY16 | 2015-10-01 | 2016-03-31 | 50497.91 | 50497.91 | 54565.42 | Non Functional
201601 | 050.41630 | Glasgow.Equipment.FY16 | 2015-10-01 | 2016-01-31 | 52905.6 | 52905.6 | 53766.34 | Non Functional
201601 | 050.41631 | Bowling Green.Equipment.FY16 | 2015-10-01 | 2016-03-31 | 46506.24 | 46506.24 | 46321.94 | Non Functional
201601 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201601 | 050.41705 | 2637 - CATCO Heaters | 2015-10-01 | 2016-12-31 | 5686.8 | 5686.8 | 4653.44 | Non Functional
201601 | 050.41719 | 050.2739.Locust Creek 8B | 2015-10-01 | 2016-05-04 | 3403.84 | 3403.84 | 3366.59 | Non Functional
201601 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201601 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201601 | 050.41730 | 050.2734.Hunters Crossinh I | 2015-10-26 | 2016-02-29 | 1739.08 | 1739.08 | 440.5 | Non Functional
201601 | 050.41739 | 050.2734.OldPorterPikeConcor | 2015-10-19 | 2016-04-29 | 2227.72 | 2227.72 | 926.38 | Non Functional
201601 | 050.41786 | 2637.T.D Williamson.Equip.FY16 | 2015-11-01 | 2016-09-28 | 46242.93 | 46242.93 | 56982.11 | Non Functional
201601 | 050.41788 | 050.2637.Deer Lick Pl Ext | 2015-12-01 | 2016-03-28 | 5320.15 | 5320.15 | 11268.41 | Non Functional
201601 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201601 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201601 | 050.41813 | PRP. 2734.Ogden Ave. CO Crew | 2015-10-28 | 2016-04-28 | 96361.12 | 143979.51 | 137528.24 | Non Functional
201601 | 050.41815 | PRP.2634.Dean Ln. | 2015-12-08 | 2016-05-12 | 588771.17 | 588771.17 | 290545.8 | Non Functional
201601 | 050.41849 | 050.2738.ElkhornExt.B | 2015-11-03 | 2016-05-31 | 1711.69 | 1711.69 | 2934.12 | Non Functional
201601 | 050.41850 | 050.2739.Notting Hills | 2015-11-03 | 2016-03-31 | 13337.7 | 13337.7 | 8620.15 | Non Functional
201601 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201601 | 050.41865 | PRP.2734.Woodburn Station | 2015-11-02 | 2016-04-30 | 101571.7 | 216213.42 | 214446.85 | Non Functional
201601 | 050.41866 | PRP.2734.Ogden-Cabell St. | 2015-11-14 | 2016-08-30 | 393549.08 | 394936.71 | 374831.76 | Non Functional
201601 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201601 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201601 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201601 | 050.41894 | 050.2637.Ky Ave South Lanes | 2015-10-01 | 2016-12-31 | 37168.38 | 37168.38 | 3877.2 | Non Functional
201601 | 050.41903 | 050.2635.Varmint Trace Rd Ext | 2015-12-01 | 2016-02-28 | 1909.03 | 1909.03 | 363.25 | Non Functional
201601 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201601 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201601 | 050.41919 | 050.2637.New Holt Rd Ext | 2016-01-01 | 2016-09-28 | 2520.35 | 2520.35 | 4665.59 | Non Functional
201601 | 050.41920 | 050.2638.Story Place Rev Ext | 2016-01-01 | 2016-04-30 | 2828.64 | 2828.64 | 3073.42 | Non Functional
201601 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201601 | 050.41956 | 050.2636.Heartland Crossings | 2016-02-01 | 2016-04-01 | 4555.82 | 4555.82 | 2086.65 | Non Functional
201601 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201601 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201601 | 050.42022 | PRP.2734.Glendale-kirby | 2015-02-14 | 2016-05-30 | 230761.95 | 230552.41 | 157106.39 | Non Functional
201601 | 050.42024 | 050.2637.May-Met Rd Ext 2 | 2016-01-01 | 2016-02-28 | 4320.38 | 4320.38 | 4488.57 | Non Functional
201601 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201601 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201601 | 050.42067 | PRP.2636.West St Co Crew | 2015-12-19 | 2016-02-15 | 23183.95 | 23183.95 | 18277.16 | Non Functional
201601 | 050.42085 | PRP.2734.High St.Co. Crew | 2015-12-15 | 2015-12-31 | 4887.59 | 4887.59 | 3351.92 | Non Functional
201601 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201601 | 050.42184 | 050.2637.Olivet Ch Rd Rev Ext | 2016-01-11 | 2016-02-29 | 2222.63 | 2222.63 | -387.27 | Non Functional
201601 | 050.42185 | 050.2637.Lakewood Villas Rev | 2016-01-14 | 2016-01-31 | 2539.92 | 2539.92 | 2551.24 | Non Functional
201601 | 050.42186 | 050.2635.Fairview Ave Rev Ext | 2016-01-18 | 2016-09-28 | 1381.98 | 1381.98 | 3642.86 | Non Functional
201601 | 050.42218 | 050.2637.Woodbine Dr Rev Ext | 2016-02-28 | 2016-09-28 | 2988.83 | 2988.83 | 4359.29 | Non Functional
201601 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201601 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201602 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201602 | 050.39380 | 2612.Emergency Regs.KY.15 | 2015-04-01 | 2015-09-30 | 30125.55 | 30125.55 | 29027.66 | Non Functional
201602 | 050.39405 | PRP.2739.Shelbyville 12 Inch | 2014-12-10 | 2016-03-30 | 4431548.97 | 16281504.53 | 17661536.23 | Non Functional
201602 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201602 | 050.40471 | PRP.2734.Crewdson Ln. | 2015-05-30 | 2016-05-30 | 1065458.52 | 1065458.52 | 928535.9 | Non Functional
201602 | 050.40596 | 050.2739.McCormack Ext. | 2015-05-08 | 2016-02-29 | 15018.69 | 15018.69 | 11152.05 | Non Functional
201602 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-09-28 | 94340.72 | 94340.72 | 63111 | Non Functional
201602 | 050.40693 | 050.2735.TB1Reloc.HorseCave | 2015-06-15 | 2016-06-30 | 265806.85 | 265806.85 | -48557.25 | Non Functional
201602 | 050.40733 | 050.2636.Avondale Reg. Repl. | 2015-06-18 | 2016-06-30 | 30420.87 | 55882.71 | 54907.83 | Non Functional
201602 | 050.40779 | PRP.2734.Centerline Phase 2 | 2015-07-20 | 2016-07-30 | 504034.42 | 4629705.8 | 4505927.78 | Non Functional
201602 | 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 2015-08-03 | 2016-02-29 | 192654.19 | 192654.19 | 4075.36 | Non Functional
201602 | 050.40986 | PRP.2609.Dawson Springs | 2015-08-13 | 2016-06-30 | 505547.54 | 1709928.9 | 1678291.46 | Non Functional
201602 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201602 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201602 | 050.41124 | 050.2734.KY 181 PI elkton | 2015-09-01 | 2016-03-31 | 403522.8 | 467284.84 | 445847.63 | Non Functional
201602 | 050.41199 | PRP.2736.E.7th St. | 2015-10-01 | 2016-03-15 | 212134.44 | 212134.44 | 115480.68 | Non Functional
201602 | 050.41227 | Hardeman TB Replace | 2015-10-01 | 2016-04-30 | 76606.5 | 76606.5 | 36443.95 | Non Functional
201602 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201602 | 050.41248 | Trunkline Wtr Bath Htr | 2015-10-01 | 2016-07-30 | 215687.98 | 215687.98 | 116444.76 | Non Functional
201602 | 050.41280 | PRP.2634.US Hwy 41 | 2015-10-01 | 2016-04-30 | 136509.73 | 136509.73 | 84463.06 | Non Functional
201602 | 050.41596 | 2636.Owensboro.WMR.FY16 | 2015-10-01 | 2016-09-30 | 1067365.32 | 1067365.32 | 1116028.55 | Non Functional
201602 | 050.41599 | 2602.KY.MDT.Replacements.FY16 | 2015-11-01 | 2016-03-31 | 261675 | 261675 | 253108.12 | Non Functional
201602 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201602 | 050.41614 | 2612.Modems.Upgrade.KY.FY16 | 2015-10-01 | 2016-06-30 | 23342.1 | 23342.1 | 26690.89 | Non Functional
201602 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201602 | 050.41620 | 2609.Equipment.Purchases.FY16 | 2015-10-01 | 2016-02-29 | 49420.8 | 49420.8 | 48734.26 | Non Functional
201602 | 050.41622 | Princeton.Equipment.FY16 | 2015-10-01 | 2016-09-28 | 20275.2 | 20275.2 | 16063.5 | Non Functional
201602 | 050.41626 | Shelbyville.KY.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 34214.4 | 34214.4 | 33925.41 | Non Functional
201602 | 050.41627 | Campbellsville.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 60192 | 60192 | 61662.15 | Non Functional
201602 | 050.41628 | Danville.Equipment.FY16 | 2015-10-01 | 2016-03-31 | 50497.91 | 50497.91 | 54565.42 | Non Functional
201602 | 050.41631 | Bowling Green.Equipment.FY16 | 2015-10-01 | 2016-03-31 | 46506.24 | 46506.24 | 46321.94 | Non Functional
201602 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201602 | 050.41719 | 050.2739.Locust Creek 8B | 2015-10-01 | 2016-05-04 | 3403.84 | 3403.84 | 3366.59 | Non Functional
201602 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201602 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201602 | 050.41730 | 050.2734.Hunters Crossinh I | 2015-10-26 | 2016-02-29 | 1739.08 | 1739.08 | 440.5 | Non Functional
201602 | 050.41739 | 050.2734.OldPorterPikeConcor | 2015-10-19 | 2016-04-29 | 2227.72 | 2227.72 | 926.38 | Non Functional
201602 | 050.41786 | 2637.T.D Williamson.Equip.FY16 | 2015-11-01 | 2016-09-28 | 46242.93 | 46242.93 | 56982.11 | Non Functional
201602 | 050.41788 | 050.2637.Deer Lick Pl Ext | 2015-12-01 | 2016-03-28 | 5320.15 | 5320.15 | 11268.41 | Non Functional
201602 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201602 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201602 | 050.41813 | PRP. 2734.Ogden Ave. CO Crew | 2015-10-28 | 2016-04-28 | 96361.12 | 143979.51 | 137528.24 | Non Functional
201602 | 050.41815 | PRP.2634.Dean Ln. | 2015-12-08 | 2016-05-12 | 588771.17 | 588771.17 | 290545.8 | Non Functional
201602 | 050.41849 | 050.2738.ElkhornExt.B | 2015-11-03 | 2016-05-31 | 1711.69 | 1711.69 | 2934.12 | Non Functional
201602 | 050.41850 | 050.2739.Notting Hills | 2015-11-03 | 2016-03-31 | 13337.7 | 13337.7 | 8620.15 | Non Functional
201602 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201602 | 050.41865 | PRP.2734.Woodburn Station | 2015-11-02 | 2016-04-30 | 101571.7 | 216213.42 | 214446.85 | Non Functional
201602 | 050.41866 | PRP.2734.Ogden-Cabell St. | 2015-11-14 | 2016-08-30 | 393549.08 | 394936.71 | 374831.76 | Non Functional
201602 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201602 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201602 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201602 | 050.41894 | 050.2637.Ky Ave South Lanes | 2015-10-01 | 2016-12-31 | 37168.38 | 37168.38 | 3877.2 | Non Functional
201602 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201602 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201602 | 050.41919 | 050.2637.New Holt Rd Ext | 2016-01-01 | 2016-09-28 | 2520.35 | 2520.35 | 4665.59 | Non Functional
201602 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201602 | 050.41956 | 050.2636.Heartland Crossings | 2016-02-01 | 2016-04-01 | 4555.82 | 4555.82 | 2086.65 | Non Functional
201602 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201602 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201602 | 050.42022 | PRP.2734.Glendale-kirby | 2015-02-14 | 2016-05-30 | 230761.95 | 230552.41 | 157106.39 | Non Functional
201602 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201602 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201602 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201602 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201602 | 050.42184 | 050.2637.Olivet Ch Rd Rev Ext | 2016-01-11 | 2016-02-29 | 2222.63 | 2222.63 | -387.27 | Non Functional
201602 | 050.42186 | 050.2635.Fairview Ave Rev Ext | 2016-01-18 | 2016-09-28 | 1381.98 | 1381.98 | 3642.86 | Non Functional
201602 | 050.42200 | 050.2734.SoGlenGables.II | 2015-10-01 | 2016-08-28 | 25788.94 | 25788.94 | 19020.71 | Non Functional
201602 | 050.42218 | 050.2637.Woodbine Dr Rev Ext | 2016-02-28 | 2016-09-28 | 2988.83 | 2988.83 | 4359.29 | Non Functional
201602 | 050.42229 | 050.2636.Longshot Cove | 2016-01-19 | 2016-04-22 | 4742.06 | 4742.06 | 2577.5 | Non Functional
201602 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201602 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201602 | 050.42277 | PRP.2634.Sebree North | 2016-02-20 | 2016-05-30 | 412350.09 | 404564.37 | 326188.01 | Non Functional
201602 | 050.42316 | 050.2735.Ashkirk.Ln.Ext | 2016-02-01 | 2016-02-27 | 2884.11 | 2884.11 | 2427.64 | Non Functional
201602 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201602 | 050.42341 | 050.2636.VistaPointReloc. | 2016-02-03 | 2016-02-29 | 9619.43 | 9619.43 | 977.45 | Non Functional
201602 | 050.42343 | 050.2637.Hinkleville Rd Imp | 2016-02-15 | 2016-09-28 | 10449.95 | 10449.95 | 17341.91 | Non Functional
201602 | 050.42351 | 050.2736.Woodmill Sys Imp | 2016-02-10 | 2016-03-31 | 21929.97 | 21929.97 | 10917.93 | Non Functional
201602 | 050.42361 | 050.2609.Kirkwood St. RV | 2016-02-09 | 2016-08-31 | 8176.14 | 8176.14 | 6263.79 | Non Functional
201602 | 050.42369 | 050.2738.Skyview.Summersville | 2016-02-09 | 2016-03-31 | 4138.68 | 4138.68 | 1657.01 | Non Functional
201602 | 050.42377 | 050.2635.Second St Ext | 2016-02-15 | 2016-04-30 | 1109.64 | 1109.64 | 394.44 | Non Functional
201602 | 050.42381 | 050.2634.New Liberty Rd Ext | 2016-02-15 | 2016-07-30 | 1580.14 | 1580.14 | 4003.67 | Non Functional
201602 | 050.42382 | 050.2637.Bleich Rd Rev Ext | 2016-02-15 | 2016-04-30 | 2454.58 | 2454.58 | 2526.31 | Non Functional
201602 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201602 | 050.42391 | PRP.2636.E.21St. Co Crew | 2016-02-10 | 2016-04-30 | 50266.4 | 50266.4 | 34678.56 | Non Functional
201602 | 050.42398 | 050.2635.Christopher Sys Imp | 2016-03-01 | 2016-09-28 | 7903.46 | 7903.46 | 9883.2 | Non Functional
201602 | 050.42410 | 050.2736.Fruithill Rd Sys Imp | 2016-02-15 | 2016-09-28 | 6115.65 | 6115.65 | 4666.38 | Non Functional
201602 | 050.42414 | PRP.2738.Carnation St | 2016-02-22 | 2016-03-25 | 9798.22 | 9798.22 | 21378.96 | Non Functional
201602 | 050.42419 | 050.2734.Suwanee.Trl.Ext | 2016-02-09 | 2016-03-31 | 4318.81 | 4318.81 | 1642.82 | Non Functional
201602 | 050.42460 | 050.2737.Kate Ave Ext | 2016-02-19 | 2016-03-31 | 3821.34 | 3821.34 | 1472.5 | Non Functional
201602 | 050.42482 | PRP.2635.McGoodwin Ave.CC | 2016-02-23 | 2016-03-31 | 14013.06 | 32924.24 | 25004.22 | Non Functional
201602 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201603 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201603 | 050.39380 | 2612.Emergency Regs.KY.15 | 2015-04-01 | 2015-09-30 | 30125.55 | 30125.55 | 29027.66 | Non Functional
201603 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201603 | 050.40471 | PRP.2734.Crewdson Ln. | 2015-05-30 | 2016-05-30 | 1065458.52 | 1065458.52 | 928535.9 | Non Functional
201603 | 050.40596 | 050.2739.McCormack Ext. | 2015-05-08 | 2016-02-29 | 15018.69 | 15018.69 | 11152.05 | Non Functional
201603 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-09-28 | 94340.72 | 94340.72 | 63111 | Non Functional
201603 | 050.40733 | 050.2636.Avondale Reg. Repl. | 2015-06-18 | 2016-06-30 | 30420.87 | 55882.71 | 54907.83 | Non Functional
201603 | 050.40779 | PRP.2734.Centerline Phase 2 | 2015-07-20 | 2016-07-30 | 504034.42 | 4629705.8 | 4505927.78 | Non Functional
201603 | 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 2015-08-03 | 2016-02-29 | 192654.19 | 192654.19 | 4075.36 | Non Functional
201603 | 050.40986 | PRP.2609.Dawson Springs | 2015-08-13 | 2016-06-30 | 505547.54 | 1709928.9 | 1678291.46 | Non Functional
201603 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201603 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201603 | 050.41227 | Hardeman TB Replace | 2015-10-01 | 2016-04-30 | 76606.5 | 76606.5 | 36443.95 | Non Functional
201603 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201603 | 050.41248 | Trunkline Wtr Bath Htr | 2015-10-01 | 2016-07-30 | 215687.98 | 215687.98 | 116444.76 | Non Functional
201603 | 050.41596 | 2636.Owensboro.WMR.FY16 | 2015-10-01 | 2016-09-30 | 1067365.32 | 1067365.32 | 1116028.55 | Non Functional
201603 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201603 | 050.41604 | 2602.Replace Oboro IT Gear.16 | 2015-11-01 | 2016-09-28 | 46520 | 46520 | 39971.36 | Non Functional
201603 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201603 | 050.41614 | 2612.Modems.Upgrade.KY.FY16 | 2015-10-01 | 2016-06-30 | 23342.1 | 23342.1 | 26690.89 | Non Functional
201603 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201603 | 050.41620 | 2609.Equipment.Purchases.FY16 | 2015-10-01 | 2016-02-29 | 49420.8 | 49420.8 | 48734.26 | Non Functional
201603 | 050.41622 | Princeton.Equipment.FY16 | 2015-10-01 | 2016-09-28 | 20275.2 | 20275.2 | 16063.5 | Non Functional
201603 | 050.41626 | Shelbyville.KY.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 34214.4 | 34214.4 | 33925.41 | Non Functional
201603 | 050.41627 | Campbellsville.Equipment.FY16 | 2015-10-01 | 2016-02-29 | 60192 | 60192 | 61662.15 | Non Functional
201603 | 050.41628 | Danville.Equipment.FY16 | 2015-10-01 | 2016-03-31 | 50497.91 | 50497.91 | 54565.42 | Non Functional
201603 | 050.41631 | Bowling Green.Equipment.FY16 | 2015-10-01 | 2016-03-31 | 46506.24 | 46506.24 | 46321.94 | Non Functional
201603 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201603 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201603 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201603 | 050.41739 | 050.2734.OldPorterPikeConcor | 2015-10-19 | 2016-04-29 | 2227.72 | 2227.72 | 926.38 | Non Functional
201603 | 050.41786 | 2637.T.D Williamson.Equip.FY16 | 2015-11-01 | 2016-09-28 | 46242.93 | 46242.93 | 56982.11 | Non Functional
201603 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201603 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201603 | 050.41813 | PRP. 2734.Ogden Ave. CO Crew | 2015-10-28 | 2016-04-28 | 96361.12 | 143979.51 | 137528.24 | Non Functional
201603 | 050.41815 | PRP.2634.Dean Ln. | 2015-12-08 | 2016-05-12 | 588771.17 | 588771.17 | 290545.8 | Non Functional
201603 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201603 | 050.41865 | PRP.2734.Woodburn Station | 2015-11-02 | 2016-04-30 | 101571.7 | 216213.42 | 214446.85 | Non Functional
201603 | 050.41866 | PRP.2734.Ogden-Cabell St. | 2015-11-14 | 2016-08-30 | 393549.08 | 394936.71 | 374831.76 | Non Functional
201603 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201603 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201603 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201603 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201603 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201603 | 050.41919 | 050.2637.New Holt Rd Ext | 2016-01-01 | 2016-09-28 | 2520.35 | 2520.35 | 4665.59 | Non Functional
201603 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201603 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201603 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201603 | 050.42022 | PRP.2734.Glendale-kirby | 2015-02-14 | 2016-05-30 | 230761.95 | 230552.41 | 157106.39 | Non Functional
201603 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201603 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201603 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201603 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201603 | 050.42184 | 050.2637.Olivet Ch Rd Rev Ext | 2016-01-11 | 2016-02-29 | 2222.63 | 2222.63 | -387.27 | Non Functional
201603 | 050.42186 | 050.2635.Fairview Ave Rev Ext | 2016-01-18 | 2016-09-28 | 1381.98 | 1381.98 | 3642.86 | Non Functional
201603 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201603 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201603 | 050.42277 | PRP.2634.Sebree North | 2016-02-20 | 2016-05-30 | 412350.09 | 404564.37 | 326188.01 | Non Functional
201603 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201603 | 050.42326 | Madisonville.WMR.Antenna.FY16 | 2016-02-03 | 2016-09-28 | 50740.06 | 72339.92 | 72199.29 | Non Functional
201603 | 050.42343 | 050.2637.Hinkleville Rd Imp | 2016-02-15 | 2016-09-28 | 10449.95 | 10449.95 | 17341.91 | Non Functional
201603 | 050.42351 | 050.2736.Woodmill Sys Imp | 2016-02-10 | 2016-03-31 | 21929.97 | 21929.97 | 10917.93 | Non Functional
201603 | 050.42360 | 050.2638.Mallard Cove Rev Ext | 2016-02-15 | 2016-04-30 | 6843.59 | 6843.59 | 1176.7 | Non Functional
201603 | 050.42361 | 050.2609.Kirkwood St. RV | 2016-02-09 | 2016-08-31 | 8176.14 | 8176.14 | 6263.79 | Non Functional
201603 | 050.42377 | 050.2635.Second St Ext | 2016-02-15 | 2016-04-30 | 1109.64 | 1109.64 | 394.44 | Non Functional
201603 | 050.42381 | 050.2634.New Liberty Rd Ext | 2016-02-15 | 2016-07-30 | 1580.14 | 1580.14 | 4003.67 | Non Functional
201603 | 050.42382 | 050.2637.Bleich Rd Rev Ext | 2016-02-15 | 2016-04-30 | 2454.58 | 2454.58 | 2526.31 | Non Functional
201603 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201603 | 050.42391 | PRP.2636.E.21St. Co Crew | 2016-02-10 | 2016-04-30 | 50266.4 | 50266.4 | 34678.56 | Non Functional
201603 | 050.42398 | 050.2635.Christopher Sys Imp | 2016-03-01 | 2016-09-28 | 7903.46 | 7903.46 | 9883.2 | Non Functional
201603 | 050.42410 | 050.2736.Fruithill Rd Sys Imp | 2016-02-15 | 2016-09-28 | 6115.65 | 6115.65 | 4666.38 | Non Functional
201603 | 050.42413 | PRP.2734.E.11th Ave | 2016-02-20 | 2016-06-30 | 287432.02 | 287432.02 | 124174.78 | Non Functional
201603 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201603 | 050.42449 | 050.2636.Regulator Replacement | 2016-02-22 | 2016-12-30 | 79378.24 | 79378.24 | 51777.76 | Non Functional
201603 | 050.42485 | PRP.2637.Clay St. | 2016-03-04 | 2016-08-30 | 349260.39 | 349260.39 | 262686.96 | Non Functional
201603 | 050.42488 | 050.2734.Pennyroyal.Farms.Ext | 2016-02-19 | 2016-09-27 | 17496.97 | 17496.97 | 17032.56 | Non Functional
201603 | 050.42507 | Replace 6 inch valve | 2016-07-01 | 2016-09-30 | 22054.25 | 22054.25 | 6213.78 | Non Functional
201603 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201603 | 050.42550 | 050.2736.Eagle Way Rev Ext | 2016-03-03 | 2016-09-28 | 6576.26 | 6576.26 | 5488.75 | Non Functional
201603 | 050.42553 | 050.2634.Watkins.Sys Imp | 2016-03-14 | 2016-05-28 | 350925.02 | 350925.02 | 265028.12 | Non Functional
201603 | 050.42564 | PRP.2735.Old Cavalry Dr.Reloc | 2016-03-10 | 2016-05-30 | 127766.01 | 127766.01 | 58424.67 | Non Functional
201603 | 050.42568 | 050.2738.Vet Mem Hwy | 2016-02-29 | 2016-06-03 | 25628.66 | 25628.66 | 1100.43 | Non Functional
201603 | 050.42595 | 050.2737.ElmLoop 16 | 2016-03-09 | 2016-09-30 | 3240.24 | 3240.24 | 827.99 | Non Functional
201603 | 050.42657 | 050.2734.Summit.Phase5.1 | 2016-02-23 | 2016-05-31 | 23312.98 | 23312.98 | 13936.69 | Non Functional
201603 | 050.42660 | 050.2734.Hunters Crossing II | 2015-10-26 | 2016-09-28 | 13345.29 | 13345.29 | 9228.98 | Non Functional
201603 | 050.42661 | 050.2734.Scottsville.Rd.Ext | 2016-03-22 | 2016-05-30 | 5203.47 | 5203.47 | 2214.68 | Non Functional
201603 | 050.42664 | 050.2636.Kasinger Ln. Ext | 2016-02-25 | 2016-04-15 | 7799.37 | 7799.37 | 8041.29 | Non Functional
201603 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201603 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201604 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201604 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201604 | 050.40596 | 050.2739.McCormack Ext. | 2015-05-08 | 2016-02-29 | 15018.69 | 15018.69 | 11152.05 | Non Functional
201604 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-09-28 | 94340.72 | 94340.72 | 63111 | Non Functional
201604 | 050.40733 | 050.2636.Avondale Reg. Repl. | 2015-06-18 | 2016-06-30 | 30420.87 | 55882.71 | 54907.83 | Non Functional
201604 | 050.40779 | PRP.2734.Centerline Phase 2 | 2015-07-20 | 2016-07-30 | 504034.42 | 4629705.8 | 4505927.78 | Non Functional
201604 | 050.40910 | 050.2734.DeweeseAsphalt.Frk. | 2015-08-03 | 2016-02-29 | 192654.19 | 192654.19 | 4075.36 | Non Functional
201604 | 050.40986 | PRP.2609.Dawson Springs | 2015-08-13 | 2016-06-30 | 505547.54 | 1709928.9 | 1678291.46 | Non Functional
201604 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201604 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201604 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201604 | 050.41248 | Trunkline Wtr Bath Htr | 2015-10-01 | 2016-07-30 | 215687.98 | 215687.98 | 116444.76 | Non Functional
201604 | 050.41596 | 2636.Owensboro.WMR.FY16 | 2015-10-01 | 2016-09-30 | 1067365.32 | 1067365.32 | 1116028.55 | Non Functional
201604 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201604 | 050.41604 | 2602.Replace Oboro IT Gear.16 | 2015-11-01 | 2016-09-28 | 46520 | 46520 | 39971.36 | Non Functional
201604 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201604 | 050.41614 | 2612.Modems.Upgrade.KY.FY16 | 2015-10-01 | 2016-06-30 | 23342.1 | 23342.1 | 26690.89 | Non Functional
201604 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201604 | 050.41622 | Princeton.Equipment.FY16 | 2015-10-01 | 2016-09-28 | 20275.2 | 20275.2 | 16063.5 | Non Functional
201604 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201604 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201604 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201604 | 050.41739 | 050.2734.OldPorterPikeConcor | 2015-10-19 | 2016-04-29 | 2227.72 | 2227.72 | 926.38 | Non Functional
201604 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201604 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201604 | 050.41813 | PRP. 2734.Ogden Ave. CO Crew | 2015-10-28 | 2016-04-28 | 96361.12 | 143979.51 | 137528.24 | Non Functional
201604 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201604 | 050.41866 | PRP.2734.Ogden-Cabell St. | 2015-11-14 | 2016-08-30 | 393549.08 | 394936.71 | 374831.76 | Non Functional
201604 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201604 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201604 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201604 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201604 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201604 | 050.41919 | 050.2637.New Holt Rd Ext | 2016-01-01 | 2016-09-28 | 2520.35 | 2520.35 | 4665.59 | Non Functional
201604 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201604 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201604 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201604 | 050.42022 | PRP.2734.Glendale-kirby | 2015-02-14 | 2016-05-30 | 230761.95 | 230552.41 | 157106.39 | Non Functional
201604 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201604 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201604 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201604 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201604 | 050.42186 | 050.2635.Fairview Ave Rev Ext | 2016-01-18 | 2016-09-28 | 1381.98 | 1381.98 | 3642.86 | Non Functional
201604 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201604 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201604 | 050.42277 | PRP.2634.Sebree North | 2016-02-20 | 2016-05-30 | 412350.09 | 404564.37 | 326188.01 | Non Functional
201604 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201604 | 050.42324 | 2735.New.Glasgow.Office.FY16 | 2016-02-01 | 2016-10-31 | 1000000 | 1000000 | 1106623.62 | Non Functional
201604 | 050.42326 | Madisonville.WMR.Antenna.FY16 | 2016-02-03 | 2016-09-28 | 50740.06 | 72339.92 | 72199.29 | Non Functional
201604 | 050.42343 | 050.2637.Hinkleville Rd Imp | 2016-02-15 | 2016-09-28 | 10449.95 | 10449.95 | 17341.91 | Non Functional
201604 | 050.42345 | PRP.2634.Mill St.Hanson | 2016-02-10 | 2016-06-30 | 102426.59 | 98964.66 | 107683.95 | Non Functional
201604 | 050.42361 | 050.2609.Kirkwood St. RV | 2016-02-09 | 2016-08-31 | 8176.14 | 8176.14 | 6263.79 | Non Functional
201604 | 050.42384 | PRP.2738.Legion Barbara | 2016-02-15 | 2016-09-30 | 412278.31 | 411410.34 | 297487.93 | Non Functional
201604 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201604 | 050.42391 | PRP.2636.E.21St. Co Crew | 2016-02-10 | 2016-04-30 | 50266.4 | 50266.4 | 34678.56 | Non Functional
201604 | 050.42398 | 050.2635.Christopher Sys Imp | 2016-03-01 | 2016-09-28 | 7903.46 | 7903.46 | 9883.2 | Non Functional
201604 | 050.42410 | 050.2736.Fruithill Rd Sys Imp | 2016-02-15 | 2016-09-28 | 6115.65 | 6115.65 | 4666.38 | Non Functional
201604 | 050.42413 | PRP.2734.E.11th Ave | 2016-02-20 | 2016-06-30 | 287432.02 | 287432.02 | 124174.78 | Non Functional
201604 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201604 | 050.42449 | 050.2636.Regulator Replacement | 2016-02-22 | 2016-12-30 | 79378.24 | 79378.24 | 51777.76 | Non Functional
201604 | 050.42468 | 2636.Taffy.WMR.Tower.FY16 | 2016-03-01 | 2016-05-31 | 62865.74 | 62865.74 | 71016.67 | Non Functional
201604 | 050.42470 | 2636.WMR.Reynolds.Stat.Tower | 2016-03-01 | 2016-05-31 | 62835.42 | 62835.42 | 79180.77 | Non Functional
201604 | 050.42472 | 2636.WMR.Hardinsburg.Tower | 2016-03-01 | 2016-05-31 | 62835.42 | 62835.42 | 75088.04 | Non Functional
201604 | 050.42473 | 2636.WMR.Hawesville.Tower | 2016-03-01 | 2016-05-31 | 57083.72 | 57083.72 | 48926.05 | Non Functional
201604 | 050.42485 | PRP.2637.Clay St. | 2016-03-04 | 2016-08-30 | 349260.39 | 349260.39 | 262686.96 | Non Functional
201604 | 050.42488 | 050.2734.Pennyroyal.Farms.Ext | 2016-02-19 | 2016-09-27 | 17496.97 | 17496.97 | 17032.56 | Non Functional
201604 | 050.42507 | Replace 6 inch valve | 2016-07-01 | 2016-09-30 | 22054.25 | 22054.25 | 6213.78 | Non Functional
201604 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201604 | 050.42550 | 050.2736.Eagle Way Rev Ext | 2016-03-03 | 2016-09-28 | 6576.26 | 6576.26 | 5488.75 | Non Functional
201604 | 050.42553 | 050.2634.Watkins.Sys Imp | 2016-03-14 | 2016-05-28 | 350925.02 | 350925.02 | 265028.12 | Non Functional
201604 | 050.42568 | 050.2738.Vet Mem Hwy | 2016-02-29 | 2016-06-03 | 25628.66 | 25628.66 | 1100.43 | Non Functional
201604 | 050.42591 | PRP.2734.Center St | 2016-03-20 | 2016-10-30 | 855695.65 | 855695.65 | 833944.82 | Non Functional
201604 | 050.42595 | 050.2737.ElmLoop 16 | 2016-03-09 | 2016-09-30 | 3240.24 | 3240.24 | 827.99 | Non Functional
201604 | 050.42627 | 2637.Pad.Mall.Route.WMR | 2016-04-01 | 2016-09-30 | 43113.66 | 43113.66 | 51077.55 | Non Functional
201604 | 050.42657 | 050.2734.Summit.Phase5.1 | 2016-02-23 | 2016-05-31 | 23312.98 | 23312.98 | 13936.69 | Non Functional
201604 | 050.42660 | 050.2734.Hunters Crossing II | 2015-10-26 | 2016-09-28 | 13345.29 | 13345.29 | 9228.98 | Non Functional
201604 | 050.42661 | 050.2734.Scottsville.Rd.Ext | 2016-03-22 | 2016-05-30 | 5203.47 | 5203.47 | 2214.68 | Non Functional
201604 | 050.42664 | 050.2636.Kasinger Ln. Ext | 2016-02-25 | 2016-04-15 | 7799.37 | 7799.37 | 8041.29 | Non Functional
201604 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201604 | 050.42688 | 050.2636.KY.69. - Relocation | 2016-02-17 | 2016-09-30 | 172548.08 | 172548.08 | 130725.58 | Non Functional
201604 | 050.42710 | 050.2739.Jeptha Creed Dist | 2016-03-08 | 2016-06-10 | 27511.38 | 27511.38 | 20921.89 | Non Functional
201604 | 050.42726 | 050.2738.Skyview.Dr.II | 2016-04-01 | 2016-05-31 | 2055.36 | 2055.36 | 1253.8 | Non Functional
201604 | 050.42730 | 050.2637.Villas - Phase I | 2016-05-01 | 2016-09-28 | 1843.8 | 1843.8 | 9331.42 | Non Functional
201604 | 050.42731 | 050.2637.Kenmar Rd Rev Ext | 2016-04-12 | 2016-09-28 | 2175.51 | 2175.51 | 296.29 | Non Functional
201604 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201604 | 050.42769 | 050.2736.S Campbell Relocate | 2016-04-13 | 2016-09-28 | 87501.74 | 87501.74 | 62174.23 | Non Functional
201604 | 050.42792 | PRP.2734.Armstrong St.CC | 2016-04-18 | 2016-09-30 | 38097.63 | 52921.74 | 40738.99 | Non Functional
201604 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201604 | 050.42822 | 050.2636.MaplrDr.Greenville | 2016-02-03 | 2016-09-30 | 4568.89 | 4568.89 | 1955.87 | Non Functional
201604 | 050.42823 | 050.2636.Kennedy.Rd.Ext.B.Dam | 2016-03-28 | 2016-05-31 | 3218.67 | 3218.67 | 570.53 | Non Functional
201604 | 050.42839 | 050.2636.S.Hampton Ext | 2016-04-18 | 2016-09-30 | 4751.32 | 4751.32 | 1707.77 | Non Functional
201604 | 050.42841 | 050.2636.Magnolia.CentralCity | 2016-04-18 | 2016-09-30 | 3022.32 | 3022.32 | 2718.12 | Non Functional
201604 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201604 | 050.42890 | 050.2735.Glasgow SAFTStopper | 2016-04-28 | 2016-09-30 | 11404.8 | 11404.8 | 12737.28 | Non Functional
201604 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201605 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201605 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201605 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-09-28 | 94340.72 | 94340.72 | 63111 | Non Functional
201605 | 050.40779 | PRP.2734.Centerline Phase 2 | 2015-07-20 | 2016-07-30 | 504034.42 | 4629705.8 | 4505927.78 | Non Functional
201605 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201605 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201605 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201605 | 050.41248 | Trunkline Wtr Bath Htr | 2015-10-01 | 2016-07-30 | 215687.98 | 215687.98 | 116444.76 | Non Functional
201605 | 050.41596 | 2636.Owensboro.WMR.FY16 | 2015-10-01 | 2016-09-30 | 1067365.32 | 1067365.32 | 1116028.55 | Non Functional
201605 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201605 | 050.41604 | 2602.Replace Oboro IT Gear.16 | 2015-11-01 | 2016-09-28 | 46520 | 46520 | 39971.36 | Non Functional
201605 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201605 | 050.41614 | 2612.Modems.Upgrade.KY.FY16 | 2015-10-01 | 2016-06-30 | 23342.1 | 23342.1 | 26690.89 | Non Functional
201605 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201605 | 050.41622 | Princeton.Equipment.FY16 | 2015-10-01 | 2016-09-28 | 20275.2 | 20275.2 | 16063.5 | Non Functional
201605 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201605 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201605 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201605 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201605 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201605 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201605 | 050.41866 | PRP.2734.Ogden-Cabell St. | 2015-11-14 | 2016-08-30 | 393549.08 | 394936.71 | 374831.76 | Non Functional
201605 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201605 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201605 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201605 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201605 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201605 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201605 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201605 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201605 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201605 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201605 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201605 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201605 | 050.42186 | 050.2635.Fairview Ave Rev Ext | 2016-01-18 | 2016-09-28 | 1381.98 | 1381.98 | 3642.86 | Non Functional
201605 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201605 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201605 | 050.42277 | PRP.2634.Sebree North | 2016-02-20 | 2016-05-30 | 412350.09 | 404564.37 | 326188.01 | Non Functional
201605 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201605 | 050.42324 | 2735.New.Glasgow.Office.FY16 | 2016-02-01 | 2016-10-31 | 1000000 | 1000000 | 1106623.62 | Non Functional
201605 | 050.42326 | Madisonville.WMR.Antenna.FY16 | 2016-02-03 | 2016-09-28 | 50740.06 | 72339.92 | 72199.29 | Non Functional
201605 | 050.42340 | 2737.Harrodsburg.Boiler.FY16 | 2016-02-05 | 2016-09-30 | 53336 | 53336 | 56017.54 | Non Functional
201605 | 050.42343 | 050.2637.Hinkleville Rd Imp | 2016-02-15 | 2016-09-28 | 10449.95 | 10449.95 | 17341.91 | Non Functional
201605 | 050.42345 | PRP.2634.Mill St.Hanson | 2016-02-10 | 2016-06-30 | 102426.59 | 98964.66 | 107683.95 | Non Functional
201605 | 050.42361 | 050.2609.Kirkwood St. RV | 2016-02-09 | 2016-08-31 | 8176.14 | 8176.14 | 6263.79 | Non Functional
201605 | 050.42384 | PRP.2738.Legion Barbara | 2016-02-15 | 2016-09-30 | 412278.31 | 411410.34 | 297487.93 | Non Functional
201605 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201605 | 050.42398 | 050.2635.Christopher Sys Imp | 2016-03-01 | 2016-09-28 | 7903.46 | 7903.46 | 9883.2 | Non Functional
201605 | 050.42410 | 050.2736.Fruithill Rd Sys Imp | 2016-02-15 | 2016-09-28 | 6115.65 | 6115.65 | 4666.38 | Non Functional
201605 | 050.42413 | PRP.2734.E.11th Ave | 2016-02-20 | 2016-06-30 | 287432.02 | 287432.02 | 124174.78 | Non Functional
201605 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201605 | 050.42449 | 050.2636.Regulator Replacement | 2016-02-22 | 2016-12-30 | 79378.24 | 79378.24 | 51777.76 | Non Functional
201605 | 050.42485 | PRP.2637.Clay St. | 2016-03-04 | 2016-08-30 | 349260.39 | 349260.39 | 262686.96 | Non Functional
201605 | 050.42488 | 050.2734.Pennyroyal.Farms.Ext | 2016-02-19 | 2016-09-27 | 17496.97 | 17496.97 | 17032.56 | Non Functional
201605 | 050.42507 | Replace 6 inch valve | 2016-07-01 | 2016-09-30 | 22054.25 | 22054.25 | 6213.78 | Non Functional
201605 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201605 | 050.42550 | 050.2736.Eagle Way Rev Ext | 2016-03-03 | 2016-09-28 | 6576.26 | 6576.26 | 5488.75 | Non Functional
201605 | 050.42568 | 050.2738.Vet Mem Hwy | 2016-02-29 | 2016-06-03 | 25628.66 | 25628.66 | 1100.43 | Non Functional
201605 | 050.42591 | PRP.2734.Center St | 2016-03-20 | 2016-10-30 | 855695.65 | 855695.65 | 833944.82 | Non Functional
201605 | 050.42595 | 050.2737.ElmLoop 16 | 2016-03-09 | 2016-09-30 | 3240.24 | 3240.24 | 827.99 | Non Functional
201605 | 050.42606 | PRP.2637.North 21st-25th | 2016-05-17 | 2016-09-30 | 443163.32 | 544616.96 | 525334.98 | Non Functional
201605 | 050.42627 | 2637.Pad.Mall.Route.WMR | 2016-04-01 | 2016-09-30 | 43113.66 | 43113.66 | 51077.55 | Non Functional
201605 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201605 | 050.42688 | 050.2636.KY.69. - Relocation | 2016-02-17 | 2016-09-30 | 172548.08 | 172548.08 | 130725.58 | Non Functional
201605 | 050.42710 | 050.2739.Jeptha Creed Dist | 2016-03-08 | 2016-06-10 | 27511.38 | 27511.38 | 20921.89 | Non Functional
201605 | 050.42730 | 050.2637.Villas - Phase I | 2016-05-01 | 2016-09-28 | 1843.8 | 1843.8 | 9331.42 | Non Functional
201605 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201605 | 050.42746 | WMR.Device Purch.2.FY16 | 2016-05-01 | 2016-09-30 | 556509.61 | 556509.61 | 542516.96 | Non Functional
201605 | 050.42791 | 050.2736.Country Club Ln 4 in | 2016-04-25 | 2016-09-28 | 13322.66 | 15513.71 | 4388.06 | Non Functional
201605 | 050.42792 | PRP.2734.Armstrong St.CC | 2016-04-18 | 2016-09-30 | 38097.63 | 52921.74 | 40738.99 | Non Functional
201605 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201605 | 050.42822 | 050.2636.MaplrDr.Greenville | 2016-02-03 | 2016-09-30 | 4568.89 | 4568.89 | 1955.87 | Non Functional
201605 | 050.42823 | 050.2636.Kennedy.Rd.Ext.B.Dam | 2016-03-28 | 2016-05-31 | 3218.67 | 3218.67 | 570.53 | Non Functional
201605 | 050.42839 | 050.2636.S.Hampton Ext | 2016-04-18 | 2016-09-30 | 4751.32 | 4751.32 | 1707.77 | Non Functional
201605 | 050.42841 | 050.2636.Magnolia.CentralCity | 2016-04-18 | 2016-09-30 | 3022.32 | 3022.32 | 2718.12 | Non Functional
201605 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201605 | 050.42873 | PRP.2636.Sheridan Pl CC | 2016-07-12 | 2016-10-30 | 26294.3 | 26294.3 | 19271.96 | Non Functional
201605 | 050.42890 | 050.2735.Glasgow SAFTStopper | 2016-04-28 | 2016-09-30 | 11404.8 | 11404.8 | 12737.28 | Non Functional
201605 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201605 | 050.42908 | 050.2737.Watershore.Ext | 2016-03-21 | 2016-08-29 | 6430.05 | 6430.05 | 10406.36 | Non Functional
201605 | 050.42914 | PRP.2635.N.Seminary St.CC | 2016-04-29 | 2016-06-30 | 61645.15 | 56807.17 | 49151.02 | Non Functional
201605 | 050.42933 | 050.2638.Brian Dr Relocate | 2016-05-02 | 2016-06-28 | 4210.82 | 4210.82 | 1472.95 | Non Functional
201605 | 050.42940 | 050.2637.Baggett Ln Replace | 2016-05-09 | 2017-09-28 | 12317.5 | 110482.79 | 123870.25 | Non Functional
201605 | 050.42948 | 050.2737.Dedman Street Reinf | 2016-04-19 | 2016-08-29 | 27308.26 | 27308.26 | 29250.64 | Non Functional
201605 | 050.42949 | 050.2737.West Lane Reinf | 2016-04-19 | 2016-08-12 | 107926.76 | 106300.9 | 108681.43 | Non Functional
201605 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201605 | 050.42979 | 2734.All Pro Locator.FY16 | 2016-05-06 | 2016-09-30 | 4328.13 | 4328.13 | 4544.81 | Non Functional
201605 | 050.43009 | PRP.2636.Colonial Ct. | 2016-06-01 | 2016-07-30 | 219778.37 | 202250.84 | 111107.82 | Non Functional
201605 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201605 | 050.43070 | 050.2738.Ashwood.Dr.Ext | 2016-05-16 | 2016-09-30 | 841.5 | 841.5 | 1465.29 | Non Functional
201605 | 050.43073 | 050.2638.I-69 Relocate | 2016-05-09 | 2016-07-30 | 18826.74 | 18826.74 | 18738.18 | Non Functional
201605 | 050.43130 | 050.2634.Formosa Dr Ext | 2016-06-06 | 2016-06-28 | 1109.49 | 1109.49 | 1968.86 | Non Functional
201605 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201606 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201606 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201606 | 050.40679 | 050.2637.Schneidman Relocate | 2015-07-01 | 2016-09-28 | 94340.72 | 94340.72 | 63111 | Non Functional
201606 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201606 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201606 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201606 | 050.41248 | Trunkline Wtr Bath Htr | 2015-10-01 | 2016-07-30 | 215687.98 | 215687.98 | 116444.76 | Non Functional
201606 | 050.41596 | 2636.Owensboro.WMR.FY16 | 2015-10-01 | 2016-09-30 | 1067365.32 | 1067365.32 | 1116028.55 | Non Functional
201606 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201606 | 050.41604 | 2602.Replace Oboro IT Gear.16 | 2015-11-01 | 2016-09-28 | 46520 | 46520 | 39971.36 | Non Functional
201606 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201606 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201606 | 050.41622 | Princeton.Equipment.FY16 | 2015-10-01 | 2016-09-28 | 20275.2 | 20275.2 | 16063.5 | Non Functional
201606 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201606 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201606 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201606 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201606 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201606 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201606 | 050.41866 | PRP.2734.Ogden-Cabell St. | 2015-11-14 | 2016-08-30 | 393549.08 | 394936.71 | 374831.76 | Non Functional
201606 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201606 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201606 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201606 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201606 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201606 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201606 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201606 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201606 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201606 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201606 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201606 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201606 | 050.42186 | 050.2635.Fairview Ave Rev Ext | 2016-01-18 | 2016-09-28 | 1381.98 | 1381.98 | 3642.86 | Non Functional
201606 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201606 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201606 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201606 | 050.42324 | 2735.New.Glasgow.Office.FY16 | 2016-02-01 | 2016-10-31 | 1000000 | 1000000 | 1106623.62 | Non Functional
201606 | 050.42326 | Madisonville.WMR.Antenna.FY16 | 2016-02-03 | 2016-09-28 | 50740.06 | 72339.92 | 72199.29 | Non Functional
201606 | 050.42340 | 2737.Harrodsburg.Boiler.FY16 | 2016-02-05 | 2016-09-30 | 53336 | 53336 | 56017.54 | Non Functional
201606 | 050.42343 | 050.2637.Hinkleville Rd Imp | 2016-02-15 | 2016-09-28 | 10449.95 | 10449.95 | 17341.91 | Non Functional
201606 | 050.42361 | 050.2609.Kirkwood St. RV | 2016-02-09 | 2016-08-31 | 8176.14 | 8176.14 | 6263.79 | Non Functional
201606 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201606 | 050.42384 | PRP.2738.Legion Barbara | 2016-02-15 | 2016-09-30 | 412278.31 | 411410.34 | 297487.93 | Non Functional
201606 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201606 | 050.42398 | 050.2635.Christopher Sys Imp | 2016-03-01 | 2016-09-28 | 7903.46 | 7903.46 | 9883.2 | Non Functional
201606 | 050.42410 | 050.2736.Fruithill Rd Sys Imp | 2016-02-15 | 2016-09-28 | 6115.65 | 6115.65 | 4666.38 | Non Functional
201606 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201606 | 050.42449 | 050.2636.Regulator Replacement | 2016-02-22 | 2016-12-30 | 79378.24 | 79378.24 | 51777.76 | Non Functional
201606 | 050.42485 | PRP.2637.Clay St. | 2016-03-04 | 2016-08-30 | 349260.39 | 349260.39 | 262686.96 | Non Functional
201606 | 050.42488 | 050.2734.Pennyroyal.Farms.Ext | 2016-02-19 | 2016-09-27 | 17496.97 | 17496.97 | 17032.56 | Non Functional
201606 | 050.42507 | Replace 6 inch valve | 2016-07-01 | 2016-09-30 | 22054.25 | 22054.25 | 6213.78 | Non Functional
201606 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201606 | 050.42550 | 050.2736.Eagle Way Rev Ext | 2016-03-03 | 2016-09-28 | 6576.26 | 6576.26 | 5488.75 | Non Functional
201606 | 050.42591 | PRP.2734.Center St | 2016-03-20 | 2016-10-30 | 855695.65 | 855695.65 | 833944.82 | Non Functional
201606 | 050.42595 | 050.2737.ElmLoop 16 | 2016-03-09 | 2016-09-30 | 3240.24 | 3240.24 | 827.99 | Non Functional
201606 | 050.42606 | PRP.2637.North 21st-25th | 2016-05-17 | 2016-09-30 | 443163.32 | 544616.96 | 525334.98 | Non Functional
201606 | 050.42627 | 2637.Pad.Mall.Route.WMR | 2016-04-01 | 2016-09-30 | 43113.66 | 43113.66 | 51077.55 | Non Functional
201606 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201606 | 050.42688 | 050.2636.KY.69. - Relocation | 2016-02-17 | 2016-09-30 | 172548.08 | 172548.08 | 130725.58 | Non Functional
201606 | 050.42730 | 050.2637.Villas - Phase I | 2016-05-01 | 2016-09-28 | 1843.8 | 1843.8 | 9331.42 | Non Functional
201606 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201606 | 050.42746 | WMR.Device Purch.2.FY16 | 2016-05-01 | 2016-09-30 | 556509.61 | 556509.61 | 542516.96 | Non Functional
201606 | 050.42791 | 050.2736.Country Club Ln 4 in | 2016-04-25 | 2016-09-28 | 13322.66 | 15513.71 | 4388.06 | Non Functional
201606 | 050.42792 | PRP.2734.Armstrong St.CC | 2016-04-18 | 2016-09-30 | 38097.63 | 52921.74 | 40738.99 | Non Functional
201606 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201606 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201606 | 050.42873 | PRP.2636.Sheridan Pl CC | 2016-07-12 | 2016-10-30 | 26294.3 | 26294.3 | 19271.96 | Non Functional
201606 | 050.42890 | 050.2735.Glasgow SAFTStopper | 2016-04-28 | 2016-09-30 | 11404.8 | 11404.8 | 12737.28 | Non Functional
201606 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201606 | 050.42914 | PRP.2635.N.Seminary St.CC | 2016-04-29 | 2016-06-30 | 61645.15 | 56807.17 | 49151.02 | Non Functional
201606 | 050.42928 | 2609.St.Charles.Storage.Office | 2016-07-01 | 2016-09-30 | 65283.61 | 65283.61 | 71301.67 | Non Functional
201606 | 050.42940 | 050.2637.Baggett Ln Replace | 2016-05-09 | 2017-09-28 | 12317.5 | 110482.79 | 123870.25 | Non Functional
201606 | 050.42948 | 050.2737.Dedman Street Reinf | 2016-04-19 | 2016-08-29 | 27308.26 | 27308.26 | 29250.64 | Non Functional
201606 | 050.42949 | 050.2737.West Lane Reinf | 2016-04-19 | 2016-08-12 | 107926.76 | 106300.9 | 108681.43 | Non Functional
201606 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201606 | 050.42979 | 2734.All Pro Locator.FY16 | 2016-05-06 | 2016-09-30 | 4328.13 | 4328.13 | 4544.81 | Non Functional
201606 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201606 | 050.43009 | PRP.2636.Colonial Ct. | 2016-06-01 | 2016-07-30 | 219778.37 | 202250.84 | 111107.82 | Non Functional
201606 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201606 | 050.43070 | 050.2738.Ashwood.Dr.Ext | 2016-05-16 | 2016-09-30 | 841.5 | 841.5 | 1465.29 | Non Functional
201606 | 050.43073 | 050.2638.I-69 Relocate | 2016-05-09 | 2016-07-30 | 18826.74 | 18826.74 | 18738.18 | Non Functional
201606 | 050.43130 | 050.2634.Formosa Dr Ext | 2016-06-06 | 2016-06-28 | 1109.49 | 1109.49 | 1968.86 | Non Functional
201606 | 050.43181 | 050.2637.Twinson Ct Rev Ext | 2016-06-01 | 2016-11-30 | 4861.89 | 4861.89 | 7024.83 | Non Functional
201606 | 050.43183 | PRP.2636.Ford Ave | 2016-07-14 | 2016-09-30 | 599662.96 | 599662.96 | 461507.04 | Non Functional
201606 | 050.43207 | Southern.Cross.Flame.Pack.400 | 2016-06-09 | 2016-09-28 | 8236.8 | 8236.8 | 8524.27 | Non Functional
201606 | 050.43228 | 050.2636ForrestDr.-Red Oak | 2016-06-09 | 2016-09-29 | 12818.92 | 12818.92 | 6482.36 | Non Functional
201606 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201606 | 050.43364 | PRP.2736.2nd.- 7th St. CC | 2016-06-14 | 2016-07-30 | 58949.67 | 94335.83 | 82661.18 | Non Functional
201606 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201607 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201607 | 050.40037 | 2739.CLOVERBROOK SEC 8 P 1 15 | 2015-11-30 | 2016-04-30 | 13697.21 | 13697.21 | 22439.12 | Non Functional
201607 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201607 | 050.41113 | 31W.Mizpah Rd.Interconnect | 2015-09-02 | 2016-08-31 | 240507.99 | 240507.99 | -2.3192e-11 | Non Functional
201607 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201607 | 050.41592 | 2602.KY.Desktop.Repl.FY16 | 2015-10-01 | 2016-09-28 | 42021 | 42021 | 13503.47 | Non Functional
201607 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201607 | 050.41604 | 2602.Replace Oboro IT Gear.16 | 2015-11-01 | 2016-09-28 | 46520 | 46520 | 39971.36 | Non Functional
201607 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201607 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201607 | 050.41704 | 050.2734.Commonwealth | 2015-10-01 | 2016-05-31 | 362343.96 | 439664.96 | 438675.86 | Non Functional
201607 | 050.41722 | 7160.Brunerstown.Rd.Damage | 2015-10-01 | 2016-09-30 | 126799.86 | 126799.86 | 133021.28 | Non Functional
201607 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201607 | 050.41802 | PRP.2735.Grinstead CC | 2015-10-12 | 2016-08-30 | 356615.26 | 356615.26 | 126618.99 | Non Functional
201607 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201607 | 050.41858 | 050.2734.MemphisJunct.Apprch | 2015-11-09 | 2016-04-29 | 192894.99 | 192894.99 | 151737.89 | Non Functional
201607 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201607 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201607 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201607 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201607 | 050.41914 | 2609.Kirkwood.Well.Workover.16 | 2015-11-01 | 2016-09-30 | 1037071.29 | 1037071.29 | 894413.79 | Non Functional
201607 | 050.41948 | 050.HWY100 Public Imprv. | 2015-11-16 | 2016-08-30 | 509005.92 | 1793174.85 | 239126.93 | Non Functional
201607 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201607 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201607 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201607 | 050.42048 | 050.2739.Mortown Way | 2016-01-04 | 2016-08-26 | 19673.93 | 63272.01 | 59087.17 | Non Functional
201607 | 050.42058 | PRP.2637.N.14th Street | 2015-12-31 | 2016-08-31 | 875650.78 | 875650.78 | 535138.93 | Non Functional
201607 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201607 | 050.42146 | 050.2734.PinOakEst. 4 inch | 2016-01-15 | 2016-09-04 | 63766.75 | 63766.75 | 29483.58 | Non Functional
201607 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201607 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201607 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201607 | 050.42324 | 2735.New.Glasgow.Office.FY16 | 2016-02-01 | 2016-10-31 | 1000000 | 1000000 | 1106623.62 | Non Functional
201607 | 050.42340 | 2737.Harrodsburg.Boiler.FY16 | 2016-02-05 | 2016-09-30 | 53336 | 53336 | 56017.54 | Non Functional
201607 | 050.42361 | 050.2609.Kirkwood St. RV | 2016-02-09 | 2016-08-31 | 8176.14 | 8176.14 | 6263.79 | Non Functional
201607 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201607 | 050.42384 | PRP.2738.Legion Barbara | 2016-02-15 | 2016-09-30 | 412278.31 | 411410.34 | 297487.93 | Non Functional
201607 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201607 | 050.42398 | 050.2635.Christopher Sys Imp | 2016-03-01 | 2016-09-28 | 7903.46 | 7903.46 | 9883.2 | Non Functional
201607 | 050.42410 | 050.2736.Fruithill Rd Sys Imp | 2016-02-15 | 2016-09-28 | 6115.65 | 6115.65 | 4666.38 | Non Functional
201607 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201607 | 050.42449 | 050.2636.Regulator Replacement | 2016-02-22 | 2016-12-30 | 79378.24 | 79378.24 | 51777.76 | Non Functional
201607 | 050.42485 | PRP.2637.Clay St. | 2016-03-04 | 2016-08-30 | 349260.39 | 349260.39 | 262686.96 | Non Functional
201607 | 050.42488 | 050.2734.Pennyroyal.Farms.Ext | 2016-02-19 | 2016-09-27 | 17496.97 | 17496.97 | 17032.56 | Non Functional
201607 | 050.42507 | Replace 6 inch valve | 2016-07-01 | 2016-09-30 | 22054.25 | 22054.25 | 6213.78 | Non Functional
201607 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201607 | 050.42591 | PRP.2734.Center St | 2016-03-20 | 2016-10-30 | 855695.65 | 855695.65 | 833944.82 | Non Functional
201607 | 050.42595 | 050.2737.ElmLoop 16 | 2016-03-09 | 2016-09-30 | 3240.24 | 3240.24 | 827.99 | Non Functional
201607 | 050.42606 | PRP.2637.North 21st-25th | 2016-05-17 | 2016-09-30 | 443163.32 | 544616.96 | 525334.98 | Non Functional
201607 | 050.42627 | 2637.Pad.Mall.Route.WMR | 2016-04-01 | 2016-09-30 | 43113.66 | 43113.66 | 51077.55 | Non Functional
201607 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201607 | 050.42688 | 050.2636.KY.69. - Relocation | 2016-02-17 | 2016-09-30 | 172548.08 | 172548.08 | 130725.58 | Non Functional
201607 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201607 | 050.42746 | WMR.Device Purch.2.FY16 | 2016-05-01 | 2016-09-30 | 556509.61 | 556509.61 | 542516.96 | Non Functional
201607 | 050.42791 | 050.2736.Country Club Ln 4 in | 2016-04-25 | 2016-09-28 | 13322.66 | 15513.71 | 4388.06 | Non Functional
201607 | 050.42792 | PRP.2734.Armstrong St.CC | 2016-04-18 | 2016-09-30 | 38097.63 | 52921.74 | 40738.99 | Non Functional
201607 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201607 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201607 | 050.42873 | PRP.2636.Sheridan Pl CC | 2016-07-12 | 2016-10-30 | 26294.3 | 26294.3 | 19271.96 | Non Functional
201607 | 050.42890 | 050.2735.Glasgow SAFTStopper | 2016-04-28 | 2016-09-30 | 11404.8 | 11404.8 | 12737.28 | Non Functional
201607 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201607 | 050.42928 | 2609.St.Charles.Storage.Office | 2016-07-01 | 2016-09-30 | 65283.61 | 65283.61 | 71301.67 | Non Functional
201607 | 050.42940 | 050.2637.Baggett Ln Replace | 2016-05-09 | 2017-09-28 | 12317.5 | 110482.79 | 123870.25 | Non Functional
201607 | 050.42948 | 050.2737.Dedman Street Reinf | 2016-04-19 | 2016-08-29 | 27308.26 | 27308.26 | 29250.64 | Non Functional
201607 | 050.42949 | 050.2737.West Lane Reinf | 2016-04-19 | 2016-08-12 | 107926.76 | 106300.9 | 108681.43 | Non Functional
201607 | 050.42952 | PRP.2734.Nashville Rd.2 | 2016-06-13 | 2016-09-30 | 228717.26 | 274740.34 | 245420.29 | Non Functional
201607 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201607 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201607 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201607 | 050.43070 | 050.2738.Ashwood.Dr.Ext | 2016-05-16 | 2016-09-30 | 841.5 | 841.5 | 1465.29 | Non Functional
201607 | 050.43181 | 050.2637.Twinson Ct Rev Ext | 2016-06-01 | 2016-11-30 | 4861.89 | 4861.89 | 7024.83 | Non Functional
201607 | 050.43183 | PRP.2636.Ford Ave | 2016-07-14 | 2016-09-30 | 599662.96 | 599662.96 | 461507.04 | Non Functional
201607 | 050.43207 | Southern.Cross.Flame.Pack.400 | 2016-06-09 | 2016-09-28 | 8236.8 | 8236.8 | 8524.27 | Non Functional
201607 | 050.43214 | 050.2738.Circle Dr.Ext | 2016-06-10 | 2016-09-30 | 1509.79 | 1509.79 | 1424.96 | Non Functional
201607 | 050.43215 | 050.2738.AnnAveExt | 2016-06-10 | 2016-09-30 | 3182.97 | 3182.97 | 2029.77 | Non Functional
201607 | 050.43228 | 050.2636ForrestDr.-Red Oak | 2016-06-09 | 2016-09-29 | 12818.92 | 12818.92 | 6482.36 | Non Functional
201607 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201607 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201607 | 050.43275 | 050.2637.Leeds Dr Ext | 2016-06-06 | 2016-11-30 | 1077.32 | 1077.32 | 1285.84 | Non Functional
201607 | 050.43293 | 2609.Cromwell Perdue Station | 2016-06-13 | 2016-12-30 | 99943.99 | 99943.99 | -9.6634e-13 | Non Functional
201607 | 050.43298 | 050.2738.Greensburg Reloc | 2016-06-14 | 2016-09-30 | 85934.79 | 123820.47 | 103868.06 | Non Functional
201607 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201607 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201607 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201607 | 050.43339 | 050.2636.Phelps.Ln.B.Dam | 2016-03-29 | 2016-08-30 | 6425.45 | 6425.45 | 2597.92 | Non Functional
201607 | 050.43361 | 050.2738.Summersville TB | 2016-06-01 | 2016-12-30 | 619888.66 | 619888.66 | 201342.71 | Non Functional
201607 | 050.43364 | PRP.2736.2nd.- 7th St. CC | 2016-06-14 | 2016-07-30 | 58949.67 | 94335.83 | 82661.18 | Non Functional
201607 | 050.43396 | 050.2739.Freedoms Way | 2016-06-29 | 2016-08-26 | 14127.46 | 14127.46 | 10812.69 | Non Functional
201607 | 050.43404 | PRP 2636 Glendale-Parkdale | 2016-07-09 | 2016-09-30 | 127511.13 | 127511.13 | 80324.98 | Non Functional
201607 | 050.43405 | 050.2736.Hwy 41 Ext Crofton | 2016-06-10 | 2016-08-04 | 4689.96 | 4689.96 | 877.24 | Non Functional
201607 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201607 | 050.43427 | 050.2637.Rail Services Ext | 2016-07-05 | 2016-10-30 | 16845.8 | 35695.86 | 18541.72 | Non Functional
201607 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201607 | 050.43525 | 050.2636.MillersMillExt | 2016-04-25 | 2016-09-30 | 6724.2 | 6724.2 | 3597.69 | Non Functional
201607 | 050.43546 | 050.2734.Lovers Ln. Tie-In | 2016-07-01 | 2016-12-30 | 43318.51 | 43318.51 | 47110.53 | Non Functional
201607 | 050.43572 | 050.2734.ChestnutSt Franklin | 2016-07-01 | 2016-09-28 | 17972.87 | 17972.87 | 4887.45 | Non Functional
201607 | 050.43579 | 050.2734.WittRd.Franklin | 2016-07-01 | 2016-09-28 | 25208.91 | 25208.91 | 6067.78 | Non Functional
201607 | 050.43587 | 050.2634.Hickory Hollow Ext | 2016-07-18 | 2016-09-30 | 1681.31 | 1681.31 | 2538.49 | Non Functional
201607 | 050.43588 | 050.2634.N Atkinson Ave Ext | 2016-07-19 | 2016-09-30 | 2263.31 | 2263.31 | 1349.07 | Non Functional
201607 | 050.43589 | 050.2634.Hwy 85 Main Ext | 2016-07-19 | 2016-09-30 | 4437.55 | 4437.55 | 7174.94 | Non Functional
201607 | 050.43605 | 2609.John Deere 6330.FY16 | 2016-07-20 | 2016-08-31 | 39361.76 | 39361.76 | 33009.95 | Non Functional
201607 | 050.43606 | PRP.2736.High St.CC | 2016-07-16 | 2016-09-20 | 48207.47 | 48207.47 | 31806.29 | Non Functional
201607 | 050.43708 | 050.2636.Fiddlesticks V | 2016-07-20 | 2016-09-29 | 6412.9 | 6412.9 | 4755.28 | Non Functional
201607 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201608 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201608 | 050.41020 | 050.2609.MoslyvlVlvRepl | 2016-07-04 | 2016-09-30 | 26049 | 75460.54 | 80954.77 | Non Functional
201608 | 050.41233 | PRP.2737.S.Chilles-Moreland | 2015-10-01 | 2016-08-30 | 1007457.5 | 1448683.64 | 1245187.42 | Non Functional
201608 | 050.41600 | 2602.KY.Laptop.Replace.FY16 | 2015-10-01 | 2016-12-30 | 69780 | 69780 | 5159.65 | Non Functional
201608 | 050.41604 | 2602.Replace Oboro IT Gear.16 | 2015-11-01 | 2016-09-28 | 46520 | 46520 | 39971.36 | Non Functional
201608 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201608 | 050.41613 | Comm.Industrial.Meters.KY.FY16 | 2015-10-01 | 2016-09-30 | 9313.38 | 9313.38 | 6075.04 | Non Functional
201608 | 050.41617 | 2612.RTU.Upgrades.KY.FY16 | 2015-10-01 | 2016-09-30 | 78285.12 | 78285.12 | 52745.12 | Non Functional
201608 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201608 | 050.41803 | PRP.2735.Gillenwater St.CC | 2015-10-13 | 2016-08-31 | 878167.15 | 461109.05 | 425671.04 | Non Functional
201608 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201608 | 050.41873 | PRP.2739.Aiken Road.Phase 2 | 2015-11-12 | 2016-08-30 | 4805419.01 | 4805419.01 | 3878483.92 | Non Functional
201608 | 050.41881 | 050.2634.Barnsley Gas Sys | 2015-11-01 | 2016-09-28 | 176658.49 | 545383.9 | 555377.42 | Non Functional
201608 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201608 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201608 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201608 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201608 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201608 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201608 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201608 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201608 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201608 | 050.42324 | 2735.New.Glasgow.Office.FY16 | 2016-02-01 | 2016-10-31 | 1000000 | 1000000 | 1106623.62 | Non Functional
201608 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201608 | 050.42384 | PRP.2738.Legion Barbara | 2016-02-15 | 2016-09-30 | 412278.31 | 411410.34 | 297487.93 | Non Functional
201608 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201608 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201608 | 050.42449 | 050.2636.Regulator Replacement | 2016-02-22 | 2016-12-30 | 79378.24 | 79378.24 | 51777.76 | Non Functional
201608 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201608 | 050.42591 | PRP.2734.Center St | 2016-03-20 | 2016-10-30 | 855695.65 | 855695.65 | 833944.82 | Non Functional
201608 | 050.42595 | 050.2737.ElmLoop 16 | 2016-03-09 | 2016-09-30 | 3240.24 | 3240.24 | 827.99 | Non Functional
201608 | 050.42606 | PRP.2637.North 21st-25th | 2016-05-17 | 2016-09-30 | 443163.32 | 544616.96 | 525334.98 | Non Functional
201608 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201608 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201608 | 050.42746 | WMR.Device Purch.2.FY16 | 2016-05-01 | 2016-09-30 | 556509.61 | 556509.61 | 542516.96 | Non Functional
201608 | 050.42791 | 050.2736.Country Club Ln 4 in | 2016-04-25 | 2016-09-28 | 13322.66 | 15513.71 | 4388.06 | Non Functional
201608 | 050.42792 | PRP.2734.Armstrong St.CC | 2016-04-18 | 2016-09-30 | 38097.63 | 52921.74 | 40738.99 | Non Functional
201608 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201608 | 050.42844 | PRP.2734.E.Second St.CC | 2016-07-01 | 2016-09-30 | 39085 | 38184.81 | 9094.2 | Non Functional
201608 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201608 | 050.42873 | PRP.2636.Sheridan Pl CC | 2016-07-12 | 2016-10-30 | 26294.3 | 26294.3 | 19271.96 | Non Functional
201608 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201608 | 050.42940 | 050.2637.Baggett Ln Replace | 2016-05-09 | 2017-09-28 | 12317.5 | 110482.79 | 123870.25 | Non Functional
201608 | 050.42948 | 050.2737.Dedman Street Reinf | 2016-04-19 | 2016-08-29 | 27308.26 | 27308.26 | 29250.64 | Non Functional
201608 | 050.42949 | 050.2737.West Lane Reinf | 2016-04-19 | 2016-08-12 | 107926.76 | 106300.9 | 108681.43 | Non Functional
201608 | 050.42952 | PRP.2734.Nashville Rd.2 | 2016-06-13 | 2016-09-30 | 228717.26 | 274740.34 | 245420.29 | Non Functional
201608 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201608 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201608 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201608 | 050.43181 | 050.2637.Twinson Ct Rev Ext | 2016-06-01 | 2016-11-30 | 4861.89 | 4861.89 | 7024.83 | Non Functional
201608 | 050.43183 | PRP.2636.Ford Ave | 2016-07-14 | 2016-09-30 | 599662.96 | 599662.96 | 461507.04 | Non Functional
201608 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201608 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201608 | 050.43275 | 050.2637.Leeds Dr Ext | 2016-06-06 | 2016-11-30 | 1077.32 | 1077.32 | 1285.84 | Non Functional
201608 | 050.43293 | 2609.Cromwell Perdue Station | 2016-06-13 | 2016-12-30 | 99943.99 | 99943.99 | -9.6634e-13 | Non Functional
201608 | 050.43298 | 050.2738.Greensburg Reloc | 2016-06-14 | 2016-09-30 | 85934.79 | 123820.47 | 103868.06 | Non Functional
201608 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201608 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201608 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201608 | 050.43361 | 050.2738.Summersville TB | 2016-06-01 | 2016-12-30 | 619888.66 | 619888.66 | 201342.71 | Non Functional
201608 | 050.43404 | PRP 2636 Glendale-Parkdale | 2016-07-09 | 2016-09-30 | 127511.13 | 127511.13 | 80324.98 | Non Functional
201608 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201608 | 050.43427 | 050.2637.Rail Services Ext | 2016-07-05 | 2016-10-30 | 16845.8 | 35695.86 | 18541.72 | Non Functional
201608 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201608 | 050.43525 | 050.2636.MillersMillExt | 2016-04-25 | 2016-09-30 | 6724.2 | 6724.2 | 3597.69 | Non Functional
201608 | 050.43546 | 050.2734.Lovers Ln. Tie-In | 2016-07-01 | 2016-12-30 | 43318.51 | 43318.51 | 47110.53 | Non Functional
201608 | 050.43572 | 050.2734.ChestnutSt Franklin | 2016-07-01 | 2016-09-28 | 17972.87 | 17972.87 | 4887.45 | Non Functional
201608 | 050.43579 | 050.2734.WittRd.Franklin | 2016-07-01 | 2016-09-28 | 25208.91 | 25208.91 | 6067.78 | Non Functional
201608 | 050.43587 | 050.2634.Hickory Hollow Ext | 2016-07-18 | 2016-09-30 | 1681.31 | 1681.31 | 2538.49 | Non Functional
201608 | 050.43589 | 050.2634.Hwy 85 Main Ext | 2016-07-19 | 2016-09-30 | 4437.55 | 4437.55 | 7174.94 | Non Functional
201608 | 050.43601 | 2636.WMR.Endpoint.#3.FY16 | 2016-07-19 | 2017-05-31 | 525868.81 | 525868.81 | 536296.71 | Non Functional
201608 | 050.43606 | PRP.2736.High St.CC | 2016-07-16 | 2016-09-20 | 48207.47 | 48207.47 | 31806.29 | Non Functional
201608 | 050.43625 | 050.2637.Harris Cr Replace | 2016-07-25 | 2016-12-31 | 2256.7 | 2256.7 | 4715.11 | Non Functional
201608 | 050.43627 | 2735.Glasgow.Office.Furniture | 2016-08-01 | 2016-11-30 | 76032 | 76032 | 68570.31 | Non Functional
201608 | 050.43719 | 050.2637.Buckner Ln main Ext | 2016-08-01 | 2016-09-28 | 4824.03 | 6891.05 | 6793.67 | Non Functional
201608 | 050.43749 | 050.2737.Stanford HP Line | 2016-08-08 | 2016-09-12 | 50810.27 | 50810.27 | 62270.64 | Non Functional
201608 | 050.43802 | 050.2635.Lafayette St Ext | 2016-08-01 | 2016-09-28 | 2056.32 | 2056.32 | -700.31 | Non Functional
201608 | 050.43835 | 2734.Front.Parking.Lot.Repair | 2016-08-04 | 2016-09-30 | 139392 | 139392 | 136547.04 | Non Functional
201608 | 050.43846 | 050.2637.Royal Park Dr Ext 4 | 2016-08-03 | 2016-11-30 | 3112.16 | 3112.16 | 2513.67 | Non Functional
201608 | 050.43903 | 050.2636.Hwy62TieInPowderly | 2016-06-23 | 2016-09-29 | 11547.35 | 11547.35 | 1856.24 | Non Functional
201608 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201608 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201609 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201609 | 050.41607 | 2612.ECATReplacement.KY.FY16 | 2016-04-30 | 2016-10-30 | 17462.6 | 17462.6 | 17971.01 | Non Functional
201609 | 050.41608 | ElectronicCorrector.Trans.KY16 | 2015-10-01 | 2016-10-30 | 32662.52 | 32662.52 | 33989.11 | Non Functional
201609 | 050.41609 | 2612.Emergency.Regs.KY.FY16 | 2015-10-01 | 2016-10-30 | 17462.6 | 17462.6 | 18163.86 | Non Functional
201609 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201609 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201609 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201609 | 050.41970 | 050.2637.HCA - Blandville Rd | 2016-01-01 | 2016-09-30 | 1052416.91 | 1052416.91 | 851960.43 | Non Functional
201609 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201609 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201609 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201609 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201609 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201609 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201609 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201609 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201609 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201609 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201609 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201609 | 050.42591 | PRP.2734.Center St | 2016-03-20 | 2016-10-30 | 855695.65 | 855695.65 | 833944.82 | Non Functional
201609 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201609 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201609 | 050.42746 | WMR.Device Purch.2.FY16 | 2016-05-01 | 2016-09-30 | 556509.61 | 556509.61 | 542516.96 | Non Functional
201609 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201609 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201609 | 050.42873 | PRP.2636.Sheridan Pl CC | 2016-07-12 | 2016-10-30 | 26294.3 | 26294.3 | 19271.96 | Non Functional
201609 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201609 | 050.42940 | 050.2637.Baggett Ln Replace | 2016-05-09 | 2017-09-28 | 12317.5 | 110482.79 | 123870.25 | Non Functional
201609 | 050.42952 | PRP.2734.Nashville Rd.2 | 2016-06-13 | 2016-09-30 | 228717.26 | 274740.34 | 245420.29 | Non Functional
201609 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201609 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201609 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201609 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201609 | 050.43181 | 050.2637.Twinson Ct Rev Ext | 2016-06-01 | 2016-11-30 | 4861.89 | 4861.89 | 7024.83 | Non Functional
201609 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201609 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201609 | 050.43275 | 050.2637.Leeds Dr Ext | 2016-06-06 | 2016-11-30 | 1077.32 | 1077.32 | 1285.84 | Non Functional
201609 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201609 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201609 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201609 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201609 | 050.43427 | 050.2637.Rail Services Ext | 2016-07-05 | 2016-10-30 | 16845.8 | 35695.86 | 18541.72 | Non Functional
201609 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201609 | 050.43546 | 050.2734.Lovers Ln. Tie-In | 2016-07-01 | 2016-12-30 | 43318.51 | 43318.51 | 47110.53 | Non Functional
201609 | 050.43601 | 2636.WMR.Endpoint.#3.FY16 | 2016-07-19 | 2017-05-31 | 525868.81 | 525868.81 | 536296.71 | Non Functional
201609 | 050.43625 | 050.2637.Harris Cr Replace | 2016-07-25 | 2016-12-31 | 2256.7 | 2256.7 | 4715.11 | Non Functional
201609 | 050.43627 | 2735.Glasgow.Office.Furniture | 2016-08-01 | 2016-11-30 | 76032 | 76032 | 68570.31 | Non Functional
201609 | 050.43846 | 050.2637.Royal Park Dr Ext 4 | 2016-08-03 | 2016-11-30 | 3112.16 | 3112.16 | 2513.67 | Non Functional
201609 | 050.43924 | 050.2636.Hwy60.atWorthington | 2016-07-27 | 2017-01-30 | 12837.79 | 12837.79 | 6433.07 | Non Functional
201609 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201609 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201609 | 050.44052 | 050.2734.Cemetery Rd. PI | 2016-09-02 | 2016-10-31 | 103253.48 | 103253.48 | 16393.81 | Non Functional
201609 | 050.44068 | 050.2636.Deer Valley III | 2016-09-07 | 2016-10-31 | 19644.8 | 19644.8 | 13663.61 | Non Functional
201609 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201609 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201609 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201609 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201609 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201609 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201610 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201610 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201610 | 050.41868 | 050.2739.Shelbyville8Lateral | 2015-10-27 | 2016-12-31 | 2171766.92 | 8347969.26 | 8437770 | Non Functional
201610 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201610 | 050.41971 | 050.2637.HCA - Lone Oak Rd | 2015-12-01 | 2017-09-28 | 939820.67 | 1231985.1 | 1194557.03 | Non Functional
201610 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201610 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201610 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201610 | 050.42267 | 050.2634.Hanson Hills Ext | 2016-01-25 | 2017-09-28 | 12408.29 | 12408.29 | 22016.11 | Non Functional
201610 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201610 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201610 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201610 | 050.42386 | Fisher Park HCA Trans.Retire | 2016-05-03 | 2016-10-31 | 1336085.36 | 1336085.36 | -7.3044e-12 | Non Functional
201610 | 050.42445 | 050.2634.Hanson 4 Inch Imp | 2016-02-17 | 2016-10-30 | 175082.48 | 270963.44 | 253895.47 | Non Functional
201610 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201610 | 050.42681 | 050.2636.Fisher Park HCA Dist | 2016-05-02 | 2017-02-28 | 1336085.36 | 1403219.52 | 1462874.14 | Non Functional
201610 | 050.42734 | PRP.2737.West Main St.Burgin | 2016-04-14 | 2016-10-30 | 1019995.13 | 1018431.8 | 468193.25 | Non Functional
201610 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201610 | 050.42845 | 050.2637.Ken-Bar T.B Relocate | 2016-06-01 | 2017-05-30 | 61515.26 | 61515.26 | 56970.65 | Non Functional
201610 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201610 | 050.42940 | 050.2637.Baggett Ln Replace | 2016-05-09 | 2017-09-28 | 12317.5 | 110482.79 | 123870.25 | Non Functional
201610 | 050.42952 | PRP.2734.Nashville Rd.2 | 2016-06-13 | 2016-09-30 | 228717.26 | 274740.34 | 245420.29 | Non Functional
201610 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201610 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201610 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201610 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201610 | 050.43181 | 050.2637.Twinson Ct Rev Ext | 2016-06-01 | 2016-11-30 | 4861.89 | 4861.89 | 7024.83 | Non Functional
201610 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201610 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201610 | 050.43275 | 050.2637.Leeds Dr Ext | 2016-06-06 | 2016-11-30 | 1077.32 | 1077.32 | 1285.84 | Non Functional
201610 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201610 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201610 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201610 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201610 | 050.43427 | 050.2637.Rail Services Ext | 2016-07-05 | 2016-10-30 | 16845.8 | 35695.86 | 18541.72 | Non Functional
201610 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201610 | 050.43546 | 050.2734.Lovers Ln. Tie-In | 2016-07-01 | 2016-12-30 | 43318.51 | 43318.51 | 47110.53 | Non Functional
201610 | 050.43601 | 2636.WMR.Endpoint.#3.FY16 | 2016-07-19 | 2017-05-31 | 525868.81 | 525868.81 | 536296.71 | Non Functional
201610 | 050.43625 | 050.2637.Harris Cr Replace | 2016-07-25 | 2016-12-31 | 2256.7 | 2256.7 | 4715.11 | Non Functional
201610 | 050.43627 | 2735.Glasgow.Office.Furniture | 2016-08-01 | 2016-11-30 | 76032 | 76032 | 68570.31 | Non Functional
201610 | 050.43846 | 050.2637.Royal Park Dr Ext 4 | 2016-08-03 | 2016-11-30 | 3112.16 | 3112.16 | 2513.67 | Non Functional
201610 | 050.43897 | PRP.2736.Hope Street | 2016-10-01 | 2017-02-01 | 291666.66 | 291666.66 | 300002.77 | Non Functional
201610 | 050.43898 | PRP.2637.Cardinal Point Apts | 2016-10-01 | 2017-02-28 | 204349.33 | 204349.33 | 131665.56 | Non Functional
201610 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201610 | 050.43924 | 050.2636.Hwy60.atWorthington | 2016-07-27 | 2017-01-30 | 12837.79 | 12837.79 | 6433.07 | Non Functional
201610 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201610 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201610 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201610 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201610 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201610 | 050.43994 | PRP.2635.South Marion | 2016-10-01 | 2017-01-31 | 522086.63 | 522086.63 | 431299.14 | Non Functional
201610 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201610 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201610 | 050.44052 | 050.2734.Cemetery Rd. PI | 2016-09-02 | 2016-10-31 | 103253.48 | 103253.48 | 16393.81 | Non Functional
201610 | 050.44068 | 050.2636.Deer Valley III | 2016-09-07 | 2016-10-31 | 19644.8 | 19644.8 | 13663.61 | Non Functional
201610 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201610 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201610 | 050.44104 | PRP.2734.KY 73 -Parkway CC | 2016-10-04 | 2017-02-28 | 63667.5 | 63667.5 | 13156.35 | Non Functional
201610 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201610 | 050.44116 | 050.2737.office Improvements | 2016-10-01 | 2016-12-31 | 12355.21 | 12355.21 | 11017 | Non Functional
201610 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201610 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201610 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201610 | 050.44394 | 050.2637.Reidland Reinforce | 2016-10-01 | 2017-06-30 | 86647.05 | 175192.8 | 161503.98 | Non Functional
201610 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201610 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201610 | 050.44457 | 050.2736.Burley Ave Rev Ext | 2016-10-01 | 2016-10-31 | 1095.83 | 1095.83 | 349.43 | Non Functional
201610 | 050.44458 | 050.2637.Coleman Rd Sys Imp | 2016-10-17 | 2017-05-30 | 4077.15 | 4077.15 | 4599.11 | Non Functional
201610 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201610 | 050.44464 | 050.2638.Paris Rd Rev Ext | 2016-10-01 | 2017-05-30 | 3282.86 | 3282.86 | 2417.04 | Non Functional
201610 | 050.44465 | 050.2637.Downs Rd Rev Ext | 2016-10-01 | 2017-05-30 | 1406.94 | 1406.94 | 1958.81 | Non Functional
201610 | 050.44466 | 050.2637.Valleyview Dr Ext | 2016-10-10 | 2017-05-30 | 2721.97 | 2721.97 | 3579.1 | Non Functional
201610 | 050.44492 | 050.2636.2737 Hwy81.Calhoun | 2016-10-31 | 2016-12-30 | 2341.03 | 2341.03 | 1861.23 | Non Functional
201610 | 050.44493 | 050.2636.Marseille Dr. Oboro | 2016-10-14 | 2017-01-30 | 4049.4 | 4049.4 | 2613 | Non Functional
201610 | 050.44496 | 050.2636.BarnettRd.Stanley | 2016-10-17 | 2017-01-30 | 2800.99 | 2800.99 | 4889.99 | Non Functional
201610 | 050.44498 | 050.2636.189Bypass.Powderly | 2016-10-14 | 2017-03-31 | 30420.81 | 30420.81 | -15469.65 | Non Functional
201610 | 050.44516 | 050.2636. TSC - Hsy 60 | 2016-10-15 | 2016-12-30 | 6200.55 | 6200.55 | 1719.66 | Non Functional
201610 | 050.44521 | 050.2635.Chestnut Rd Rev Ext | 2016-10-10 | 2016-10-31 | 2367.92 | 2367.92 | 4096.4 | Non Functional
201610 | 050.44536 | 2635.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 26760.87 | 26760.87 | 27624.36 | Non Functional
201610 | 050.44544 | PRP.2637.North 32nd St. | 2016-11-11 | 2017-03-31 | 590823.41 | 590823.41 | 370581.86 | Non Functional
201610 | 050.44559 | 050.2738.Eastport Rd | 2016-10-25 | 2016-11-26 | 1949.73 | 1949.73 | 1919.58 | Non Functional
201610 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201610 | 050.44564 | 050.2734.Henderson.Ind.Pk.Frk | 2016-10-18 | 2017-01-30 | 146991.53 | 146991.53 | 53831.17 | Non Functional
201610 | 050.44572 | 050.2734.Hunters Crssing- Frk | 2016-10-18 | 2016-11-30 | 6541.71 | 6541.71 | 4764.46 | Non Functional
201610 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201611 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201611 | 050.41729 | 050.2734.LouisvilleRd.Lowe | 2015-10-26 | 2016-12-30 | 7407.4 | 7407.4 | 5933.57 | Non Functional
201611 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201611 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201611 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201611 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201611 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201611 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201611 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201611 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201611 | 050.42819 | 050.2734.Industrial.Dr.RegSta | 2016-06-01 | 2016-12-30 | 32768.63 | 38719.46 | 38400.58 | Non Functional
201611 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201611 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201611 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201611 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201611 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201611 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201611 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201611 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201611 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201611 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201611 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201611 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201611 | 050.43546 | 050.2734.Lovers Ln. Tie-In | 2016-07-01 | 2016-12-30 | 43318.51 | 43318.51 | 47110.53 | Non Functional
201611 | 050.43601 | 2636.WMR.Endpoint.#3.FY16 | 2016-07-19 | 2017-05-31 | 525868.81 | 525868.81 | 536296.71 | Non Functional
201611 | 050.43627 | 2735.Glasgow.Office.Furniture | 2016-08-01 | 2016-11-30 | 76032 | 76032 | 68570.31 | Non Functional
201611 | 050.43897 | PRP.2736.Hope Street | 2016-10-01 | 2017-02-01 | 291666.66 | 291666.66 | 300002.77 | Non Functional
201611 | 050.43898 | PRP.2637.Cardinal Point Apts | 2016-10-01 | 2017-02-28 | 204349.33 | 204349.33 | 131665.56 | Non Functional
201611 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201611 | 050.43924 | 050.2636.Hwy60.atWorthington | 2016-07-27 | 2017-01-30 | 12837.79 | 12837.79 | 6433.07 | Non Functional
201611 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201611 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201611 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201611 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201611 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201611 | 050.43994 | PRP.2635.South Marion | 2016-10-01 | 2017-01-31 | 522086.63 | 522086.63 | 431299.14 | Non Functional
201611 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201611 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201611 | 050.44052 | 050.2734.Cemetery Rd. PI | 2016-09-02 | 2016-10-31 | 103253.48 | 103253.48 | 16393.81 | Non Functional
201611 | 050.44068 | 050.2636.Deer Valley III | 2016-09-07 | 2016-10-31 | 19644.8 | 19644.8 | 13663.61 | Non Functional
201611 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201611 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201611 | 050.44104 | PRP.2734.KY 73 -Parkway CC | 2016-10-04 | 2017-02-28 | 63667.5 | 63667.5 | 13156.35 | Non Functional
201611 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201611 | 050.44116 | 050.2737.office Improvements | 2016-10-01 | 2016-12-31 | 12355.21 | 12355.21 | 11017 | Non Functional
201611 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201611 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201611 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201611 | 050.44394 | 050.2637.Reidland Reinforce | 2016-10-01 | 2017-06-30 | 86647.05 | 175192.8 | 161503.98 | Non Functional
201611 | 050.44424 | PRP.2636.St.Elizabeth St.CC | 2016-10-11 | 2017-01-30 | 47841.34 | 47841.34 | 19736.62 | Non Functional
201611 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201611 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201611 | 050.44458 | 050.2637.Coleman Rd Sys Imp | 2016-10-17 | 2017-05-30 | 4077.15 | 4077.15 | 4599.11 | Non Functional
201611 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201611 | 050.44464 | 050.2638.Paris Rd Rev Ext | 2016-10-01 | 2017-05-30 | 3282.86 | 3282.86 | 2417.04 | Non Functional
201611 | 050.44465 | 050.2637.Downs Rd Rev Ext | 2016-10-01 | 2017-05-30 | 1406.94 | 1406.94 | 1958.81 | Non Functional
201611 | 050.44466 | 050.2637.Valleyview Dr Ext | 2016-10-10 | 2017-05-30 | 2721.97 | 2721.97 | 3579.1 | Non Functional
201611 | 050.44492 | 050.2636.2737 Hwy81.Calhoun | 2016-10-31 | 2016-12-30 | 2341.03 | 2341.03 | 1861.23 | Non Functional
201611 | 050.44493 | 050.2636.Marseille Dr. Oboro | 2016-10-14 | 2017-01-30 | 4049.4 | 4049.4 | 2613 | Non Functional
201611 | 050.44496 | 050.2636.BarnettRd.Stanley | 2016-10-17 | 2017-01-30 | 2800.99 | 2800.99 | 4889.99 | Non Functional
201611 | 050.44498 | 050.2636.189Bypass.Powderly | 2016-10-14 | 2017-03-31 | 30420.81 | 30420.81 | -15469.65 | Non Functional
201611 | 050.44506 | 2739.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 24562.35 | 25248.42 | 25248.42 | Non Functional
201611 | 050.44507 | 2738.Equipment.FY2017 | 2016-10-01 | 2017-01-31 | 21323.2 | 21323.2 | 23405 | Non Functional
201611 | 050.44508 | 2737.Equipment.FY2017 | 2016-10-01 | 2017-05-28 | 18565.28 | 18565.28 | 22693.55 | Non Functional
201611 | 050.44516 | 050.2636. TSC - Hsy 60 | 2016-10-15 | 2016-12-30 | 6200.55 | 6200.55 | 1719.66 | Non Functional
201611 | 050.44529 | 2735.Glasgow Equipment.17 | 2016-10-01 | 2016-12-31 | 16745.39 | 16745.39 | 16656.84 | Non Functional
201611 | 050.44530 | 2736.Equipment.FY2017 | 2016-10-01 | 2017-05-31 | 18522.53 | 18522.53 | 21583.95 | Non Functional
201611 | 050.44532 | 2637.Equipment.FY2017 | 2016-10-01 | 2016-12-31 | 25038.7 | 25038.7 | 34125.7 | Non Functional
201611 | 050.44533 | 2638.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 38420.36 | 38420.36 | 38834.24 | Non Functional
201611 | 050.44535 | 2634.Misc.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 23817.3 | 25953.76 | 29524.35 | Non Functional
201611 | 050.44536 | 2635.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 26760.87 | 26760.87 | 27624.36 | Non Functional
201611 | 050.44544 | PRP.2637.North 32nd St. | 2016-11-11 | 2017-03-31 | 590823.41 | 590823.41 | 370581.86 | Non Functional
201611 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201611 | 050.44564 | 050.2734.Henderson.Ind.Pk.Frk | 2016-10-18 | 2017-01-30 | 146991.53 | 146991.53 | 53831.17 | Non Functional
201611 | 050.44572 | 050.2734.Hunters Crssing- Frk | 2016-10-18 | 2016-11-30 | 6541.71 | 6541.71 | 4764.46 | Non Functional
201611 | 050.44580 | 2636.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 58693.15 | 58693.15 | 64576.18 | Non Functional
201611 | 050.44581 | 2734.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 72349.62 | 72349.62 | 78487.97 | Non Functional
201611 | 050.44587 | PRP.2635. North East Marion | 2016-11-08 | 2017-05-30 | 743963.21 | 743963.21 | 482978.59 | Non Functional
201611 | 050.44598 | 2734.Timble Geo 7X.GPS | 2016-10-01 | 2016-12-31 | 12479.35 | 12479.35 | 13809.41 | Non Functional
201611 | 050.44624 | PRP.2737. KY 300 Stanford | 2016-11-01 | 2016-12-30 | 35784.06 | 46380.06 | 44093.16 | Non Functional
201611 | 050.44626 | PRP.2637. Freedom Waste | 2016-11-02 | 2016-12-30 | 603894.84 | 603894.84 | 529256.48 | Non Functional
201611 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201611 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201611 | 050.44670 | 050.2734.Mackenzie.1-A | 2016-10-25 | 2017-01-31 | 8690.15 | 8690.15 | 6103.63 | Non Functional
201611 | 050.44671 | 050.2734.StillwaterPhs.2-3 | 2016-10-25 | 2017-02-28 | 9242.06 | 9242.06 | 8653.29 | Non Functional
201611 | 050.44706 | 050.2739Pembrigde Ct. | 2016-10-26 | 2017-02-28 | 5972.77 | 10767.95 | 10767.95 | Non Functional
201611 | 050.44711 | 050.2739.Locust Creek.XI | 2016-11-14 | 2017-01-30 | 11572.34 | 11572.34 | 12359.99 | Non Functional
201611 | 050.44715 | 050.2734.Elrod Rd. Tie-In | 2016-11-07 | 2017-04-28 | 33216.06 | 33216.06 | 14350.3 | Non Functional
201611 | 050.44718 | 050.2636.Whispering Meadows 7 | 2016-10-19 | 2017-01-31 | 11054.28 | 11054.28 | 10570.99 | Non Functional
201611 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201611 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201611 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201611 | 050.44777 | 050.2637.N 11th Street Ext | 2016-11-21 | 2017-05-30 | 2143.62 | 2143.62 | 6.3949e-14 | Non Functional
201611 | 050.44806 | 050.2739.Windhurst Lowering | 2016-11-21 | 2017-02-10 | 133984.65 | 152765.12 | 10772.94 | Non Functional
201611 | 050.44817 | 050.2634.S. Main St Main Ext | 2016-11-21 | 2017-05-30 | 3989.51 | 3989.51 | 4538.02 | Non Functional
201611 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201612 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201612 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201612 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201612 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201612 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201612 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201612 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201612 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201612 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201612 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201612 | 050.42954 | 050.2734.Smallhouse Rd. Relo | 2016-05-01 | 2017-03-28 | 539797.83 | 539797.83 | 540907.84 | Non Functional
201612 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201612 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201612 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201612 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201612 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201612 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201612 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201612 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201612 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201612 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201612 | 050.43601 | 2636.WMR.Endpoint.#3.FY16 | 2016-07-19 | 2017-05-31 | 525868.81 | 525868.81 | 536296.71 | Non Functional
201612 | 050.43897 | PRP.2736.Hope Street | 2016-10-01 | 2017-02-01 | 291666.66 | 291666.66 | 300002.77 | Non Functional
201612 | 050.43898 | PRP.2637.Cardinal Point Apts | 2016-10-01 | 2017-02-28 | 204349.33 | 204349.33 | 131665.56 | Non Functional
201612 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201612 | 050.43924 | 050.2636.Hwy60.atWorthington | 2016-07-27 | 2017-01-30 | 12837.79 | 12837.79 | 6433.07 | Non Functional
201612 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201612 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201612 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201612 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201612 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201612 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201612 | 050.43994 | PRP.2635.South Marion | 2016-10-01 | 2017-01-31 | 522086.63 | 522086.63 | 431299.14 | Non Functional
201612 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201612 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201612 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201612 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201612 | 050.44104 | PRP.2734.KY 73 -Parkway CC | 2016-10-04 | 2017-02-28 | 63667.5 | 63667.5 | 13156.35 | Non Functional
201612 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201612 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201612 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201612 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201612 | 050.44394 | 050.2637.Reidland Reinforce | 2016-10-01 | 2017-06-30 | 86647.05 | 175192.8 | 161503.98 | Non Functional
201612 | 050.44424 | PRP.2636.St.Elizabeth St.CC | 2016-10-11 | 2017-01-30 | 47841.34 | 47841.34 | 19736.62 | Non Functional
201612 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201612 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201612 | 050.44458 | 050.2637.Coleman Rd Sys Imp | 2016-10-17 | 2017-05-30 | 4077.15 | 4077.15 | 4599.11 | Non Functional
201612 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201612 | 050.44464 | 050.2638.Paris Rd Rev Ext | 2016-10-01 | 2017-05-30 | 3282.86 | 3282.86 | 2417.04 | Non Functional
201612 | 050.44465 | 050.2637.Downs Rd Rev Ext | 2016-10-01 | 2017-05-30 | 1406.94 | 1406.94 | 1958.81 | Non Functional
201612 | 050.44466 | 050.2637.Valleyview Dr Ext | 2016-10-10 | 2017-05-30 | 2721.97 | 2721.97 | 3579.1 | Non Functional
201612 | 050.44493 | 050.2636.Marseille Dr. Oboro | 2016-10-14 | 2017-01-30 | 4049.4 | 4049.4 | 2613 | Non Functional
201612 | 050.44496 | 050.2636.BarnettRd.Stanley | 2016-10-17 | 2017-01-30 | 2800.99 | 2800.99 | 4889.99 | Non Functional
201612 | 050.44498 | 050.2636.189Bypass.Powderly | 2016-10-14 | 2017-03-31 | 30420.81 | 30420.81 | -15469.65 | Non Functional
201612 | 050.44506 | 2739.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 24562.35 | 25248.42 | 25248.42 | Non Functional
201612 | 050.44508 | 2737.Equipment.FY2017 | 2016-10-01 | 2017-05-28 | 18565.28 | 18565.28 | 22693.55 | Non Functional
201612 | 050.44530 | 2736.Equipment.FY2017 | 2016-10-01 | 2017-05-31 | 18522.53 | 18522.53 | 21583.95 | Non Functional
201612 | 050.44532 | 2637.Equipment.FY2017 | 2016-10-01 | 2016-12-31 | 25038.7 | 25038.7 | 34125.7 | Non Functional
201612 | 050.44533 | 2638.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 38420.36 | 38420.36 | 38834.24 | Non Functional
201612 | 050.44535 | 2634.Misc.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 23817.3 | 25953.76 | 29524.35 | Non Functional
201612 | 050.44536 | 2635.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 26760.87 | 26760.87 | 27624.36 | Non Functional
201612 | 050.44544 | PRP.2637.North 32nd St. | 2016-11-11 | 2017-03-31 | 590823.41 | 590823.41 | 370581.86 | Non Functional
201612 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201612 | 050.44564 | 050.2734.Henderson.Ind.Pk.Frk | 2016-10-18 | 2017-01-30 | 146991.53 | 146991.53 | 53831.17 | Non Functional
201612 | 050.44580 | 2636.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 58693.15 | 58693.15 | 64576.18 | Non Functional
201612 | 050.44581 | 2734.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 72349.62 | 72349.62 | 78487.97 | Non Functional
201612 | 050.44587 | PRP.2635. North East Marion | 2016-11-08 | 2017-05-30 | 743963.21 | 743963.21 | 482978.59 | Non Functional
201612 | 050.44593 | PRP.2734.Claire-Hwy31 CC | 2017-01-04 | 2017-06-30 | 80105.09 | 80105.09 | 38476.83 | Non Functional
201612 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201612 | 050.44624 | PRP.2737. KY 300 Stanford | 2016-11-01 | 2016-12-30 | 35784.06 | 46380.06 | 44093.16 | Non Functional
201612 | 050.44626 | PRP.2637. Freedom Waste | 2016-11-02 | 2016-12-30 | 603894.84 | 603894.84 | 529256.48 | Non Functional
201612 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201612 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201612 | 050.44670 | 050.2734.Mackenzie.1-A | 2016-10-25 | 2017-01-31 | 8690.15 | 8690.15 | 6103.63 | Non Functional
201612 | 050.44671 | 050.2734.StillwaterPhs.2-3 | 2016-10-25 | 2017-02-28 | 9242.06 | 9242.06 | 8653.29 | Non Functional
201612 | 050.44706 | 050.2739Pembrigde Ct. | 2016-10-26 | 2017-02-28 | 5972.77 | 10767.95 | 10767.95 | Non Functional
201612 | 050.44711 | 050.2739.Locust Creek.XI | 2016-11-14 | 2017-01-30 | 11572.34 | 11572.34 | 12359.99 | Non Functional
201612 | 050.44715 | 050.2734.Elrod Rd. Tie-In | 2016-11-07 | 2017-04-28 | 33216.06 | 33216.06 | 14350.3 | Non Functional
201612 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201612 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201612 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201612 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201612 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201612 | 050.44777 | 050.2637.N 11th Street Ext | 2016-11-21 | 2017-05-30 | 2143.62 | 2143.62 | 6.3949e-14 | Non Functional
201612 | 050.44806 | 050.2739.Windhurst Lowering | 2016-11-21 | 2017-02-10 | 133984.65 | 152765.12 | 10772.94 | Non Functional
201612 | 050.44817 | 050.2634.S. Main St Main Ext | 2016-11-21 | 2017-05-30 | 3989.51 | 3989.51 | 4538.02 | Non Functional
201612 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201612 | 050.44901 | PRP.2735.KY 335 Rowletts | 2016-12-15 | 2017-02-28 | 43159.89 | 43159.89 | 39524.81 | Non Functional
201612 | 050.44923 | PRP.2635.Ratliff CC | 2016-12-10 | 2017-03-31 | 83100.4 | 83100.4 | 60536.46 | Non Functional
201612 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201612 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201701 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201701 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201701 | 050.42047 | 050.2739.Old Mill | 2016-02-15 | 2017-01-27 | 11578.2 | 11578.2 | 13871.05 | Non Functional
201701 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201701 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201701 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201701 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201701 | 050.42363 | Releif Valve Replace | 2015-10-01 | 2017-05-30 | 19080.51 | 19080.51 | 7048.04 | Non Functional
201701 | 050.42532 | 050.2637.Hansen Road Rev Ext | 2016-04-01 | 2017-01-30 | 3486.11 | 3486.11 | 3617.14 | Non Functional
201701 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201701 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201701 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201701 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201701 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201701 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201701 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201701 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201701 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201701 | 050.43426 | 050.2637.Husband Rd Replace | 2016-07-05 | 2017-05-30 | 11447.78 | 11447.78 | 15820.12 | Non Functional
201701 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201701 | 050.43897 | PRP.2736.Hope Street | 2016-10-01 | 2017-02-01 | 291666.66 | 291666.66 | 300002.77 | Non Functional
201701 | 050.43898 | PRP.2637.Cardinal Point Apts | 2016-10-01 | 2017-02-28 | 204349.33 | 204349.33 | 131665.56 | Non Functional
201701 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201701 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201701 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201701 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201701 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201701 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201701 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201701 | 050.43994 | PRP.2635.South Marion | 2016-10-01 | 2017-01-31 | 522086.63 | 522086.63 | 431299.14 | Non Functional
201701 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201701 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201701 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201701 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201701 | 050.44104 | PRP.2734.KY 73 -Parkway CC | 2016-10-04 | 2017-02-28 | 63667.5 | 63667.5 | 13156.35 | Non Functional
201701 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201701 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201701 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201701 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201701 | 050.44394 | 050.2637.Reidland Reinforce | 2016-10-01 | 2017-06-30 | 86647.05 | 175192.8 | 161503.98 | Non Functional
201701 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201701 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201701 | 050.44458 | 050.2637.Coleman Rd Sys Imp | 2016-10-17 | 2017-05-30 | 4077.15 | 4077.15 | 4599.11 | Non Functional
201701 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201701 | 050.44464 | 050.2638.Paris Rd Rev Ext | 2016-10-01 | 2017-05-30 | 3282.86 | 3282.86 | 2417.04 | Non Functional
201701 | 050.44465 | 050.2637.Downs Rd Rev Ext | 2016-10-01 | 2017-05-30 | 1406.94 | 1406.94 | 1958.81 | Non Functional
201701 | 050.44466 | 050.2637.Valleyview Dr Ext | 2016-10-10 | 2017-05-30 | 2721.97 | 2721.97 | 3579.1 | Non Functional
201701 | 050.44498 | 050.2636.189Bypass.Powderly | 2016-10-14 | 2017-03-31 | 30420.81 | 30420.81 | -15469.65 | Non Functional
201701 | 050.44527 | 2609.C136.Mueller.Tapping. | 2016-10-01 | 2017-03-28 | 34682.87 | 34682.87 | 36998.92 | Non Functional
201701 | 050.44528 | 2609.Mueller Stopper Ftgs | 2016-10-01 | 2017-02-28 | 18049.85 | 18049.85 | 19422.82 | Non Functional
201701 | 050.44530 | 2736.Equipment.FY2017 | 2016-10-01 | 2017-05-31 | 18522.53 | 18522.53 | 21583.95 | Non Functional
201701 | 050.44532 | 2637.Equipment.FY2017 | 2016-10-01 | 2016-12-31 | 25038.7 | 25038.7 | 34125.7 | Non Functional
201701 | 050.44535 | 2634.Misc.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 23817.3 | 25953.76 | 29524.35 | Non Functional
201701 | 050.44544 | PRP.2637.North 32nd St. | 2016-11-11 | 2017-03-31 | 590823.41 | 590823.41 | 370581.86 | Non Functional
201701 | 050.44545 | PRP.2637.River Oaks | 2017-03-01 | 2017-06-30 | 639660.62 | 639660.62 | 474063.43 | Non Functional
201701 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201701 | 050.44564 | 050.2734.Henderson.Ind.Pk.Frk | 2016-10-18 | 2017-01-30 | 146991.53 | 146991.53 | 53831.17 | Non Functional
201701 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201701 | 050.44580 | 2636.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 58693.15 | 58693.15 | 64576.18 | Non Functional
201701 | 050.44581 | 2734.Equipment.FY2017 | 2016-10-01 | 2017-02-28 | 72349.62 | 72349.62 | 78487.97 | Non Functional
201701 | 050.44587 | PRP.2635. North East Marion | 2016-11-08 | 2017-05-30 | 743963.21 | 743963.21 | 482978.59 | Non Functional
201701 | 050.44593 | PRP.2734.Claire-Hwy31 CC | 2017-01-04 | 2017-06-30 | 80105.09 | 80105.09 | 38476.83 | Non Functional
201701 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201701 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201701 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201701 | 050.44671 | 050.2734.StillwaterPhs.2-3 | 2016-10-25 | 2017-02-28 | 9242.06 | 9242.06 | 8653.29 | Non Functional
201701 | 050.44706 | 050.2739Pembrigde Ct. | 2016-10-26 | 2017-02-28 | 5972.77 | 10767.95 | 10767.95 | Non Functional
201701 | 050.44715 | 050.2734.Elrod Rd. Tie-In | 2016-11-07 | 2017-04-28 | 33216.06 | 33216.06 | 14350.3 | Non Functional
201701 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201701 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201701 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201701 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201701 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201701 | 050.44777 | 050.2637.N 11th Street Ext | 2016-11-21 | 2017-05-30 | 2143.62 | 2143.62 | 6.3949e-14 | Non Functional
201701 | 050.44806 | 050.2739.Windhurst Lowering | 2016-11-21 | 2017-02-10 | 133984.65 | 152765.12 | 10772.94 | Non Functional
201701 | 050.44817 | 050.2634.S. Main St Main Ext | 2016-11-21 | 2017-05-30 | 3989.51 | 3989.51 | 4538.02 | Non Functional
201701 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201701 | 050.44848 | WMR.2634.Henderson.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 56145.88 | Non Functional
201701 | 050.44850 | WMR.2634.DawsonSpring.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 62609.82 | Non Functional
201701 | 050.44851 | WMR.2634.Eddyville.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 52905.27 | Non Functional
201701 | 050.44852 | WMR.2634.Morton Gap.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 55388.49 | Non Functional
201701 | 050.44853 | WMR.2634.Princeton.Tower | 2016-11-30 | 2017-07-31 | 61241 | 61241 | 65312.24 | Non Functional
201701 | 050.44857 | WMR.2634.Marion.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 64898.07 | Non Functional
201701 | 050.44865 | 050.2734.BrentwoodSub.Sec.III | 2016-11-30 | 2017-04-28 | 12402.51 | 12402.51 | 13624.46 | Non Functional
201701 | 050.44901 | PRP.2735.KY 335 Rowletts | 2016-12-15 | 2017-02-28 | 43159.89 | 43159.89 | 39524.81 | Non Functional
201701 | 050.44903 | 050.2734.Bypass Station | 2016-12-07 | 2017-06-01 | 27447.3 | 27447.3 | 30372.6 | Non Functional
201701 | 050.44923 | PRP.2635.Ratliff CC | 2016-12-10 | 2017-03-31 | 83100.4 | 83100.4 | 60536.46 | Non Functional
201701 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201701 | 050.44992 | 050.2636.BrookfieldSub.Phs.I | 2017-01-03 | 2017-03-31 | 11698.03 | 11698.03 | 10126.09 | Non Functional
201701 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201701 | 050.45080 | 050.2638.Stacks Ln Replace | 2017-01-10 | 2017-09-28 | 19632.22 | 37206.63 | 32865.7 | Non Functional
201701 | 050.45128 | 050.2739.SummersvilleSec.II | 2017-01-16 | 2017-05-31 | 20832.68 | 20832.68 | 15864.76 | Non Functional
201701 | 050.45152 | 2637.Calvert.City.Endpoints.17 | 2017-01-19 | 2017-05-31 | 156874.03 | 156874.03 | 161297.13 | Non Functional
201701 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201701 | 050.45160 | 050.2637.J Sanders Blvd Ext 2 | 2017-01-20 | 2017-09-30 | 5172.89 | 5172.89 | 7784.39 | Non Functional
201701 | 050.45190 | Palmer.Jenkins.Easement.Purch | 2017-01-27 | 2017-04-30 | 183713.83 | 183713.83 | 182764.58 | Non Functional
201701 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201702 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201702 | 050.41905 | PRP.2636. Greenville 4 Inch | 2015-11-06 | 2017-03-15 | 1240452.94 | 1475538.04 | 1460457.89 | Non Functional
201702 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201702 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201702 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201702 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201702 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201702 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201702 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201702 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201702 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201702 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201702 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201702 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201702 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201702 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201702 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201702 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201702 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201702 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201702 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201702 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201702 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201702 | 050.43994 | PRP.2635.South Marion | 2016-10-01 | 2017-01-31 | 522086.63 | 522086.63 | 431299.14 | Non Functional
201702 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201702 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201702 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201702 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201702 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201702 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201702 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201702 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201702 | 050.44394 | 050.2637.Reidland Reinforce | 2016-10-01 | 2017-06-30 | 86647.05 | 175192.8 | 161503.98 | Non Functional
201702 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201702 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201702 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201702 | 050.44498 | 050.2636.189Bypass.Powderly | 2016-10-14 | 2017-03-31 | 30420.81 | 30420.81 | -15469.65 | Non Functional
201702 | 050.44528 | 2609.Mueller Stopper Ftgs | 2016-10-01 | 2017-02-28 | 18049.85 | 18049.85 | 19422.82 | Non Functional
201702 | 050.44530 | 2736.Equipment.FY2017 | 2016-10-01 | 2017-05-31 | 18522.53 | 18522.53 | 21583.95 | Non Functional
201702 | 050.44535 | 2634.Misc.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 23817.3 | 25953.76 | 29524.35 | Non Functional
201702 | 050.44544 | PRP.2637.North 32nd St. | 2016-11-11 | 2017-03-31 | 590823.41 | 590823.41 | 370581.86 | Non Functional
201702 | 050.44545 | PRP.2637.River Oaks | 2017-03-01 | 2017-06-30 | 639660.62 | 639660.62 | 474063.43 | Non Functional
201702 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201702 | 050.44564 | 050.2734.Henderson.Ind.Pk.Frk | 2016-10-18 | 2017-01-30 | 146991.53 | 146991.53 | 53831.17 | Non Functional
201702 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201702 | 050.44587 | PRP.2635. North East Marion | 2016-11-08 | 2017-05-30 | 743963.21 | 743963.21 | 482978.59 | Non Functional
201702 | 050.44593 | PRP.2734.Claire-Hwy31 CC | 2017-01-04 | 2017-06-30 | 80105.09 | 80105.09 | 38476.83 | Non Functional
201702 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201702 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201702 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201702 | 050.44671 | 050.2734.StillwaterPhs.2-3 | 2016-10-25 | 2017-02-28 | 9242.06 | 9242.06 | 8653.29 | Non Functional
201702 | 050.44706 | 050.2739Pembrigde Ct. | 2016-10-26 | 2017-02-28 | 5972.77 | 10767.95 | 10767.95 | Non Functional
201702 | 050.44715 | 050.2734.Elrod Rd. Tie-In | 2016-11-07 | 2017-04-28 | 33216.06 | 33216.06 | 14350.3 | Non Functional
201702 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201702 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201702 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201702 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201702 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201702 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201702 | 050.44777 | 050.2637.N 11th Street Ext | 2016-11-21 | 2017-05-30 | 2143.62 | 2143.62 | 6.3949e-14 | Non Functional
201702 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201702 | 050.44848 | WMR.2634.Henderson.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 56145.88 | Non Functional
201702 | 050.44850 | WMR.2634.DawsonSpring.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 62609.82 | Non Functional
201702 | 050.44851 | WMR.2634.Eddyville.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 52905.27 | Non Functional
201702 | 050.44852 | WMR.2634.Morton Gap.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 55388.49 | Non Functional
201702 | 050.44853 | WMR.2634.Princeton.Tower | 2016-11-30 | 2017-07-31 | 61241 | 61241 | 65312.24 | Non Functional
201702 | 050.44857 | WMR.2634.Marion.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 64898.07 | Non Functional
201702 | 050.44865 | 050.2734.BrentwoodSub.Sec.III | 2016-11-30 | 2017-04-28 | 12402.51 | 12402.51 | 13624.46 | Non Functional
201702 | 050.44866 | PRP.2636.West 3rd St | 2017-03-02 | 2017-06-24 | 436177.98 | 436177.98 | 346163.01 | Non Functional
201702 | 050.44876 | PRP.2636. W.5th. St. | 2017-02-02 | 2017-07-31 | 386952.38 | 386952.38 | 306816.45 | Non Functional
201702 | 050.44901 | PRP.2735.KY 335 Rowletts | 2016-12-15 | 2017-02-28 | 43159.89 | 43159.89 | 39524.81 | Non Functional
201702 | 050.44923 | PRP.2635.Ratliff CC | 2016-12-10 | 2017-03-31 | 83100.4 | 83100.4 | 60536.46 | Non Functional
201702 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201702 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201702 | 050.45080 | 050.2638.Stacks Ln Replace | 2017-01-10 | 2017-09-28 | 19632.22 | 37206.63 | 32865.7 | Non Functional
201702 | 050.45128 | 050.2739.SummersvilleSec.II | 2017-01-16 | 2017-05-31 | 20832.68 | 20832.68 | 15864.76 | Non Functional
201702 | 050.45138 | 050.2739.TripleCrown I | 2017-02-01 | 2017-04-28 | 24626.39 | 24626.39 | 21237.7 | Non Functional
201702 | 050.45152 | 2637.Calvert.City.Endpoints.17 | 2017-01-19 | 2017-05-31 | 156874.03 | 156874.03 | 161297.13 | Non Functional
201702 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201702 | 050.45160 | 050.2637.J Sanders Blvd Ext 2 | 2017-01-20 | 2017-09-30 | 5172.89 | 5172.89 | 7784.39 | Non Functional
201702 | 050.45177 | 2638.South Reinforcement | 2017-03-01 | 2017-09-30 | 351519.27 | 351519.27 | 280306.14 | Non Functional
201702 | 050.45190 | Palmer.Jenkins.Easement.Purch | 2017-01-27 | 2017-04-30 | 183713.83 | 183713.83 | 182764.58 | Non Functional
201702 | 050.45198 | 050.2736.Crofton TB Replace | 2017-03-01 | 2017-09-28 | 54149.59 | 54149.59 | 45432.13 | Non Functional
201702 | 050.45274 | 050.2737.Centre College Repl | 2017-02-20 | 2017-03-31 | 114351.29 | 114351.29 | 86732.07 | Non Functional
201702 | 050.45304 | 050.2739.DogwoodVillaDr. | 2017-02-10 | 2017-03-31 | 3458.12 | 9345.54 | 9345.54 | Non Functional
201702 | 050.45316 | 050.2636.JR.Thompson.Dr | 2017-02-10 | 2017-04-28 | 11055.98 | 11055.98 | 8809.44 | Non Functional
201702 | 050.45317 | 050.2636.Keenland Trace | 2017-02-08 | 2017-04-29 | 11976.12 | 11976.12 | 11506.57 | Non Functional
201702 | 050.45318 | 050.2636.PleasantValley | 2017-01-17 | 2017-03-31 | 3099.04 | 3099.04 | 1809.68 | Non Functional
201702 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201702 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201703 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201703 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201703 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201703 | 050.42272 | PRP.2737.East Main St. | 2016-03-01 | 2017-06-30 | 542300.52 | 542300.52 | 362522.19 | Non Functional
201703 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201703 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201703 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201703 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201703 | 050.43164 | 2637.Calvert.City.WMR.Tower.16 | 2016-08-01 | 2017-09-28 | 95131.9 | 121827.11 | 121826.29 | Non Functional
201703 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201703 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201703 | 050.43303 | 050.2739.SvillePurStaUpgrade | 2016-06-01 | 2017-04-28 | 776019.44 | 776019.44 | 869114.9 | Non Functional
201703 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201703 | 050.43336 | 050.2609.Cooper Creek Replc | 2016-06-22 | 2016-12-30 | 44525.57 | 44525.57 | 66075.19 | Non Functional
201703 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201703 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201703 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201703 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201703 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201703 | 050.43951 | 050.2609.Jet Stream Replc. | 2016-08-22 | 2017-01-30 | 47629.18 | 47629.18 | 37618.2 | Non Functional
201703 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201703 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201703 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201703 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201703 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201703 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201703 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201703 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201703 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201703 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201703 | 050.44394 | 050.2637.Reidland Reinforce | 2016-10-01 | 2017-06-30 | 86647.05 | 175192.8 | 161503.98 | Non Functional
201703 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201703 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201703 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201703 | 050.44498 | 050.2636.189Bypass.Powderly | 2016-10-14 | 2017-03-31 | 30420.81 | 30420.81 | -15469.65 | Non Functional
201703 | 050.44528 | 2609.Mueller Stopper Ftgs | 2016-10-01 | 2017-02-28 | 18049.85 | 18049.85 | 19422.82 | Non Functional
201703 | 050.44530 | 2736.Equipment.FY2017 | 2016-10-01 | 2017-05-31 | 18522.53 | 18522.53 | 21583.95 | Non Functional
201703 | 050.44535 | 2634.Misc.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 23817.3 | 25953.76 | 29524.35 | Non Functional
201703 | 050.44545 | PRP.2637.River Oaks | 2017-03-01 | 2017-06-30 | 639660.62 | 639660.62 | 474063.43 | Non Functional
201703 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201703 | 050.44564 | 050.2734.Henderson.Ind.Pk.Frk | 2016-10-18 | 2017-01-30 | 146991.53 | 146991.53 | 53831.17 | Non Functional
201703 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201703 | 050.44587 | PRP.2635. North East Marion | 2016-11-08 | 2017-05-30 | 743963.21 | 743963.21 | 482978.59 | Non Functional
201703 | 050.44593 | PRP.2734.Claire-Hwy31 CC | 2017-01-04 | 2017-06-30 | 80105.09 | 80105.09 | 38476.83 | Non Functional
201703 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201703 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201703 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201703 | 050.44671 | 050.2734.StillwaterPhs.2-3 | 2016-10-25 | 2017-02-28 | 9242.06 | 9242.06 | 8653.29 | Non Functional
201703 | 050.44706 | 050.2739Pembrigde Ct. | 2016-10-26 | 2017-02-28 | 5972.77 | 10767.95 | 10767.95 | Non Functional
201703 | 050.44715 | 050.2734.Elrod Rd. Tie-In | 2016-11-07 | 2017-04-28 | 33216.06 | 33216.06 | 14350.3 | Non Functional
201703 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201703 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201703 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201703 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201703 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201703 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201703 | 050.44777 | 050.2637.N 11th Street Ext | 2016-11-21 | 2017-05-30 | 2143.62 | 2143.62 | 6.3949e-14 | Non Functional
201703 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201703 | 050.44848 | WMR.2634.Henderson.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 56145.88 | Non Functional
201703 | 050.44850 | WMR.2634.DawsonSpring.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 62609.82 | Non Functional
201703 | 050.44851 | WMR.2634.Eddyville.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 52905.27 | Non Functional
201703 | 050.44852 | WMR.2634.Morton Gap.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 55388.49 | Non Functional
201703 | 050.44853 | WMR.2634.Princeton.Tower | 2016-11-30 | 2017-07-31 | 61241 | 61241 | 65312.24 | Non Functional
201703 | 050.44857 | WMR.2634.Marion.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 64898.07 | Non Functional
201703 | 050.44865 | 050.2734.BrentwoodSub.Sec.III | 2016-11-30 | 2017-04-28 | 12402.51 | 12402.51 | 13624.46 | Non Functional
201703 | 050.44866 | PRP.2636.West 3rd St | 2017-03-02 | 2017-06-24 | 436177.98 | 436177.98 | 346163.01 | Non Functional
201703 | 050.44876 | PRP.2636. W.5th. St. | 2017-02-02 | 2017-07-31 | 386952.38 | 386952.38 | 306816.45 | Non Functional
201703 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201703 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201703 | 050.45027 | 050.2637.Villa Ridge Dr Ext | 2017-03-01 | 2017-12-28 | 3444.54 | 3444.54 | 819.9 | Non Functional
201703 | 050.45080 | 050.2638.Stacks Ln Replace | 2017-01-10 | 2017-09-28 | 19632.22 | 37206.63 | 32865.7 | Non Functional
201703 | 050.45128 | 050.2739.SummersvilleSec.II | 2017-01-16 | 2017-05-31 | 20832.68 | 20832.68 | 15864.76 | Non Functional
201703 | 050.45138 | 050.2739.TripleCrown I | 2017-02-01 | 2017-04-28 | 24626.39 | 24626.39 | 21237.7 | Non Functional
201703 | 050.45152 | 2637.Calvert.City.Endpoints.17 | 2017-01-19 | 2017-05-31 | 156874.03 | 156874.03 | 161297.13 | Non Functional
201703 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201703 | 050.45160 | 050.2637.J Sanders Blvd Ext 2 | 2017-01-20 | 2017-09-30 | 5172.89 | 5172.89 | 7784.39 | Non Functional
201703 | 050.45177 | 2638.South Reinforcement | 2017-03-01 | 2017-09-30 | 351519.27 | 351519.27 | 280306.14 | Non Functional
201703 | 050.45198 | 050.2736.Crofton TB Replace | 2017-03-01 | 2017-09-28 | 54149.59 | 54149.59 | 45432.13 | Non Functional
201703 | 050.45251 | PRP.2736.Hwy 41 Crofton CC | 2017-03-02 | 2017-04-26 | 36044.03 | 36044.03 | 54111.67 | Non Functional
201703 | 050.45273 | 050.2737.Metker Trail Station | 2017-02-13 | 2017-06-23 | 99939.36 | 99939.36 | 82534.27 | Non Functional
201703 | 050.45274 | 050.2737.Centre College Repl | 2017-02-20 | 2017-03-31 | 114351.29 | 114351.29 | 86732.07 | Non Functional
201703 | 050.45304 | 050.2739.DogwoodVillaDr. | 2017-02-10 | 2017-03-31 | 3458.12 | 9345.54 | 9345.54 | Non Functional
201703 | 050.45316 | 050.2636.JR.Thompson.Dr | 2017-02-10 | 2017-04-28 | 11055.98 | 11055.98 | 8809.44 | Non Functional
201703 | 050.45317 | 050.2636.Keenland Trace | 2017-02-08 | 2017-04-29 | 11976.12 | 11976.12 | 11506.57 | Non Functional
201703 | 050.45318 | 050.2636.PleasantValley | 2017-01-17 | 2017-03-31 | 3099.04 | 3099.04 | 1809.68 | Non Functional
201703 | 050.45319 | 050.2637.Old Hwy 45 Rev Ext | 2017-03-01 | 2017-09-30 | 6052.17 | 13390.7 | 12175.21 | Non Functional
201703 | 050.45347 | 050.2636.Caseys.Hwy431.Ext | 2017-02-13 | 2017-03-31 | 8474.13 | 8474.13 | 2734.23 | Non Functional
201703 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201703 | 050.45481 | 050.2636.BreckenridgeRetire | 2017-03-01 | 2017-03-31 | 3283.61 | 3283.61 | 501.8 | Non Functional
201703 | 050.45482 | 050.2636.MillSt.Greenville | 2017-03-01 | 2017-03-31 | 3176.08 | 3176.08 | 5558.72 | Non Functional
201703 | 050.45523 | 050.2638.Beadlestown Replace | 2016-10-01 | 2017-11-30 | 201029.75 | 201029.75 | 106305.53 | Non Functional
201703 | 050.45625 | 050.2734.ViningsApproach | 2017-03-31 | 2017-07-29 | 118033.64 | 118033.64 | 79972.58 | Non Functional
201703 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201704 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201704 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201704 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201704 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201704 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201704 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201704 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201704 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201704 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201704 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201704 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201704 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201704 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201704 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201704 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201704 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201704 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201704 | 050.44029 | PRP.2734.State Street | 2016-10-01 | 2017-06-30 | 756115.59 | 756115.59 | 424662.95 | Non Functional
201704 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201704 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201704 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201704 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201704 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201704 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201704 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201704 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201704 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201704 | 050.44463 | 050.2637.Delcrest Main Ext | 2016-10-01 | 2016-12-21 | 1900.15 | 1900.15 | 951 | Non Functional
201704 | 050.44530 | 2736.Equipment.FY2017 | 2016-10-01 | 2017-05-31 | 18522.53 | 18522.53 | 21583.95 | Non Functional
201704 | 050.44535 | 2634.Misc.Equipment.FY2017 | 2016-10-01 | 2017-05-30 | 23817.3 | 25953.76 | 29524.35 | Non Functional
201704 | 050.44545 | PRP.2637.River Oaks | 2017-03-01 | 2017-06-30 | 639660.62 | 639660.62 | 474063.43 | Non Functional
201704 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201704 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201704 | 050.44593 | PRP.2734.Claire-Hwy31 CC | 2017-01-04 | 2017-06-30 | 80105.09 | 80105.09 | 38476.83 | Non Functional
201704 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201704 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201704 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201704 | 050.44715 | 050.2734.Elrod Rd. Tie-In | 2016-11-07 | 2017-04-28 | 33216.06 | 33216.06 | 14350.3 | Non Functional
201704 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201704 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201704 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201704 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201704 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201704 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201704 | 050.44837 | PRP.2637.Glenwood Dr | 2017-07-05 | 2017-09-29 | 863980.83 | 863980.83 | 430797.61 | Non Functional
201704 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201704 | 050.44848 | WMR.2634.Henderson.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 56145.88 | Non Functional
201704 | 050.44850 | WMR.2634.DawsonSpring.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 62609.82 | Non Functional
201704 | 050.44851 | WMR.2634.Eddyville.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 52905.27 | Non Functional
201704 | 050.44852 | WMR.2634.Morton Gap.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 55388.49 | Non Functional
201704 | 050.44853 | WMR.2634.Princeton.Tower | 2016-11-30 | 2017-07-31 | 61241 | 61241 | 65312.24 | Non Functional
201704 | 050.44857 | WMR.2634.Marion.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 64898.07 | Non Functional
201704 | 050.44866 | PRP.2636.West 3rd St | 2017-03-02 | 2017-06-24 | 436177.98 | 436177.98 | 346163.01 | Non Functional
201704 | 050.44876 | PRP.2636. W.5th. St. | 2017-02-02 | 2017-07-31 | 386952.38 | 386952.38 | 306816.45 | Non Functional
201704 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201704 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201704 | 050.45027 | 050.2637.Villa Ridge Dr Ext | 2017-03-01 | 2017-12-28 | 3444.54 | 3444.54 | 819.9 | Non Functional
201704 | 050.45080 | 050.2638.Stacks Ln Replace | 2017-01-10 | 2017-09-28 | 19632.22 | 37206.63 | 32865.7 | Non Functional
201704 | 050.45128 | 050.2739.SummersvilleSec.II | 2017-01-16 | 2017-05-31 | 20832.68 | 20832.68 | 15864.76 | Non Functional
201704 | 050.45138 | 050.2739.TripleCrown I | 2017-02-01 | 2017-04-28 | 24626.39 | 24626.39 | 21237.7 | Non Functional
201704 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201704 | 050.45160 | 050.2637.J Sanders Blvd Ext 2 | 2017-01-20 | 2017-09-30 | 5172.89 | 5172.89 | 7784.39 | Non Functional
201704 | 050.45177 | 2638.South Reinforcement | 2017-03-01 | 2017-09-30 | 351519.27 | 351519.27 | 280306.14 | Non Functional
201704 | 050.45198 | 050.2736.Crofton TB Replace | 2017-03-01 | 2017-09-28 | 54149.59 | 54149.59 | 45432.13 | Non Functional
201704 | 050.45251 | PRP.2736.Hwy 41 Crofton CC | 2017-03-02 | 2017-04-26 | 36044.03 | 36044.03 | 54111.67 | Non Functional
201704 | 050.45273 | 050.2737.Metker Trail Station | 2017-02-13 | 2017-06-23 | 99939.36 | 99939.36 | 82534.27 | Non Functional
201704 | 050.45319 | 050.2637.Old Hwy 45 Rev Ext | 2017-03-01 | 2017-09-30 | 6052.17 | 13390.7 | 12175.21 | Non Functional
201704 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201704 | 050.45379 | PRP.2735. Old Bardstown Rd. | 2017-03-02 | 2017-09-20 | 791469.23 | 791469.23 | 243755.31 | Non Functional
201704 | 050.45472 | 050.2609.BonHarbor.P&AWells | 2017-03-01 | 2017-07-24 | 330026.86 | 239760.53 | 134910.24 | Non Functional
201704 | 050.45481 | 050.2636.BreckenridgeRetire | 2017-03-01 | 2017-03-31 | 3283.61 | 3283.61 | 501.8 | Non Functional
201704 | 050.45506 | 050.2634.YZ Replace | 2017-04-01 | 2017-09-30 | 61675.86 | 66486.12 | 66991.71 | Non Functional
201704 | 050.45523 | 050.2638.Beadlestown Replace | 2016-10-01 | 2017-11-30 | 201029.75 | 201029.75 | 106305.53 | Non Functional
201704 | 050.45546 | 050.2636.Fairview.Spur.Reg | 2017-03-10 | 2018-09-30 | 42153.37 | 42153.37 | 22417.81 | Non Functional
201704 | 050.45547 | 050.2637.KY-Dam Rd Rev Ext | 2017-04-01 | 2017-09-28 | 1238.4 | 1238.4 | 2519.79 | Non Functional
201704 | 050.45563 | 050.2609.Hickory VLV Dist. | 2017-02-13 | 2018-02-13 | 310881.47 | 310881.47 | 306699.69 | Non Functional
201704 | 050.45564 | 050.2609.Hickory Valve Lot | 2017-02-09 | 2018-02-09 | 713632.54 | 713632.54 | 223451.49 | Non Functional
201704 | 050.45572 | 050.2734.ViningsSub. | 2017-02-01 | 2017-08-31 | 15214.43 | 15214.43 | 2164.41 | Non Functional
201704 | 050.45584 | 3302.KY.Laptop.Replc.FY17 | 2017-03-14 | 2017-05-31 | 13609.2 | 13609.2 | 14702.13 | Non Functional
201704 | 050.45586 | 3302.KY.Desktop.Replc.FY17 | 2017-03-14 | 2017-08-10 | 20413.8 | 20413.8 | 10525.23 | Non Functional
201704 | 050.45625 | 050.2734.ViningsApproach | 2017-03-31 | 2017-07-29 | 118033.64 | 118033.64 | 79972.58 | Non Functional
201704 | 050.45627 | 050.2734.Plano Rd Reg Sta | 2017-03-21 | 2017-09-29 | 91208.89 | 91208.89 | 59966.36 | Non Functional
201704 | 050.45687 | 050.2736.Calvin Dr Station | 2017-04-01 | 2017-09-28 | 18243.77 | 47963.64 | 46333.82 | Non Functional
201704 | 050.45730 | Groebner.Short.Locator.PD/S.17 | 2017-04-07 | 2017-06-15 | 2908.46 | 2908.46 | 1636.57 | Non Functional
201704 | 050.45762 | 050.2739.Commerce Crossing | 2017-04-10 | 2017-09-30 | 71496.47 | 71496.47 | 34722.93 | Non Functional
201704 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201705 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201705 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201705 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201705 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201705 | 050.42892 | 050.2637.New Liberty Rd Ext | 2016-06-01 | 2017-09-30 | 22621.11 | 22621.11 | 16757.42 | Non Functional
201705 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201705 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201705 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201705 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201705 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201705 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201705 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201705 | 050.43931 | 050.2609.Aleris.Storage.Retire | 2016-08-25 | 2017-01-30 | 169983.56 | 169983.56 | -1.4211e-12 | Non Functional
201705 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201705 | 050.43940 | PRP.2738.S.Central- Carnation | 2016-10-01 | 2017-05-30 | 617607.19 | 617607.19 | 356576.78 | Non Functional
201705 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201705 | 050.43993 | PRP.2734.Montague-Liberty | 2016-10-01 | 2017-06-15 | 390028.98 | 390028.98 | 402331.68 | Non Functional
201705 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201705 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201705 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201705 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201705 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201705 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201705 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201705 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201705 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201705 | 050.44545 | PRP.2637.River Oaks | 2017-03-01 | 2017-06-30 | 639660.62 | 639660.62 | 474063.43 | Non Functional
201705 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201705 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201705 | 050.44593 | PRP.2734.Claire-Hwy31 CC | 2017-01-04 | 2017-06-30 | 80105.09 | 80105.09 | 38476.83 | Non Functional
201705 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201705 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201705 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201705 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201705 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201705 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201705 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201705 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201705 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201705 | 050.44837 | PRP.2637.Glenwood Dr | 2017-07-05 | 2017-09-29 | 863980.83 | 863980.83 | 430797.61 | Non Functional
201705 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201705 | 050.44848 | WMR.2634.Henderson.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 56145.88 | Non Functional
201705 | 050.44850 | WMR.2634.DawsonSpring.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 62609.82 | Non Functional
201705 | 050.44851 | WMR.2634.Eddyville.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 52905.27 | Non Functional
201705 | 050.44852 | WMR.2634.Morton Gap.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 55388.49 | Non Functional
201705 | 050.44853 | WMR.2634.Princeton.Tower | 2016-11-30 | 2017-07-31 | 61241 | 61241 | 65312.24 | Non Functional
201705 | 050.44857 | WMR.2634.Marion.Tower | 2016-11-29 | 2017-07-31 | 61241 | 61241 | 64898.07 | Non Functional
201705 | 050.44866 | PRP.2636.West 3rd St | 2017-03-02 | 2017-06-24 | 436177.98 | 436177.98 | 346163.01 | Non Functional
201705 | 050.44876 | PRP.2636. W.5th. St. | 2017-02-02 | 2017-07-31 | 386952.38 | 386952.38 | 306816.45 | Non Functional
201705 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201705 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201705 | 050.45027 | 050.2637.Villa Ridge Dr Ext | 2017-03-01 | 2017-12-28 | 3444.54 | 3444.54 | 819.9 | Non Functional
201705 | 050.45080 | 050.2638.Stacks Ln Replace | 2017-01-10 | 2017-09-28 | 19632.22 | 37206.63 | 32865.7 | Non Functional
201705 | 050.45083 | PRP.2734.Alumni Ave | 2017-04-01 | 2017-09-28 | 276511.07 | 276511.07 | 214785.96 | Non Functional
201705 | 050.45099 | 050.2734.WilkeyIndPkExt | 2017-01-10 | 2017-07-31 | 31557.04 | 31557.04 | 14829.29 | Non Functional
201705 | 050.45128 | 050.2739.SummersvilleSec.II | 2017-01-16 | 2017-05-31 | 20832.68 | 20832.68 | 15864.76 | Non Functional
201705 | 050.45138 | 050.2739.TripleCrown I | 2017-02-01 | 2017-04-28 | 24626.39 | 24626.39 | 21237.7 | Non Functional
201705 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201705 | 050.45160 | 050.2637.J Sanders Blvd Ext 2 | 2017-01-20 | 2017-09-30 | 5172.89 | 5172.89 | 7784.39 | Non Functional
201705 | 050.45177 | 2638.South Reinforcement | 2017-03-01 | 2017-09-30 | 351519.27 | 351519.27 | 280306.14 | Non Functional
201705 | 050.45198 | 050.2736.Crofton TB Replace | 2017-03-01 | 2017-09-28 | 54149.59 | 54149.59 | 45432.13 | Non Functional
201705 | 050.45251 | PRP.2736.Hwy 41 Crofton CC | 2017-03-02 | 2017-04-26 | 36044.03 | 36044.03 | 54111.67 | Non Functional
201705 | 050.45273 | 050.2737.Metker Trail Station | 2017-02-13 | 2017-06-23 | 99939.36 | 99939.36 | 82534.27 | Non Functional
201705 | 050.45319 | 050.2637.Old Hwy 45 Rev Ext | 2017-03-01 | 2017-09-30 | 6052.17 | 13390.7 | 12175.21 | Non Functional
201705 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201705 | 050.45377 | PRP.2734.6Th.&BlakeyCC | 2017-07-05 | 2017-08-25 | 52467.73 | 52467.73 | 40794.13 | Non Functional
201705 | 050.45379 | PRP.2735. Old Bardstown Rd. | 2017-03-02 | 2017-09-20 | 791469.23 | 791469.23 | 243755.31 | Non Functional
201705 | 050.45461 | 050.2734.ERX - B.G. | 2017-02-27 | 2017-09-28 | 27520.28 | 27520.28 | 23098.25 | Non Functional
201705 | 050.45462 | 050.2735.ERX - Glagow | 2017-02-27 | 2017-09-28 | 7057.05 | 7057.05 | 4019.63 | Non Functional
201705 | 050.45472 | 050.2609.BonHarbor.P&AWells | 2017-03-01 | 2017-07-24 | 330026.86 | 239760.53 | 134910.24 | Non Functional
201705 | 050.45481 | 050.2636.BreckenridgeRetire | 2017-03-01 | 2017-03-31 | 3283.61 | 3283.61 | 501.8 | Non Functional
201705 | 050.45488 | PRP.2738.S.Columbia-Gowdy | 2017-03-02 | 2017-09-27 | 584142.3 | 584142.3 | 348820.65 | Non Functional
201705 | 050.45506 | 050.2634.YZ Replace | 2017-04-01 | 2017-09-30 | 61675.86 | 66486.12 | 66991.71 | Non Functional
201705 | 050.45523 | 050.2638.Beadlestown Replace | 2016-10-01 | 2017-11-30 | 201029.75 | 201029.75 | 106305.53 | Non Functional
201705 | 050.45546 | 050.2636.Fairview.Spur.Reg | 2017-03-10 | 2018-09-30 | 42153.37 | 42153.37 | 22417.81 | Non Functional
201705 | 050.45547 | 050.2637.KY-Dam Rd Rev Ext | 2017-04-01 | 2017-09-28 | 1238.4 | 1238.4 | 2519.79 | Non Functional
201705 | 050.45563 | 050.2609.Hickory VLV Dist. | 2017-02-13 | 2018-02-13 | 310881.47 | 310881.47 | 306699.69 | Non Functional
201705 | 050.45564 | 050.2609.Hickory Valve Lot | 2017-02-09 | 2018-02-09 | 713632.54 | 713632.54 | 223451.49 | Non Functional
201705 | 050.45572 | 050.2734.ViningsSub. | 2017-02-01 | 2017-08-31 | 15214.43 | 15214.43 | 2164.41 | Non Functional
201705 | 050.45584 | 3302.KY.Laptop.Replc.FY17 | 2017-03-14 | 2017-05-31 | 13609.2 | 13609.2 | 14702.13 | Non Functional
201705 | 050.45586 | 3302.KY.Desktop.Replc.FY17 | 2017-03-14 | 2017-08-10 | 20413.8 | 20413.8 | 10525.23 | Non Functional
201705 | 050.45625 | 050.2734.ViningsApproach | 2017-03-31 | 2017-07-29 | 118033.64 | 118033.64 | 79972.58 | Non Functional
201705 | 050.45627 | 050.2734.Plano Rd Reg Sta | 2017-03-21 | 2017-09-29 | 91208.89 | 91208.89 | 59966.36 | Non Functional
201705 | 050.45687 | 050.2736.Calvin Dr Station | 2017-04-01 | 2017-09-28 | 18243.77 | 47963.64 | 46333.82 | Non Functional
201705 | 050.45730 | Groebner.Short.Locator.PD/S.17 | 2017-04-07 | 2017-06-15 | 2908.46 | 2908.46 | 1636.57 | Non Functional
201705 | 050.45762 | 050.2739.Commerce Crossing | 2017-04-10 | 2017-09-30 | 71496.47 | 71496.47 | 34722.93 | Non Functional
201705 | 050.45775 | PRP.2636.Westview - Wink | 2017-05-01 | 2017-09-28 | 450873.9 | 450873.9 | 261193.68 | Non Functional
201705 | 050.45832 | 050.2734.ElktonTB.Reloc | 2017-03-31 | 2017-09-29 | 118496.48 | 118496.48 | 31050.46 | Non Functional
201705 | 050.45834 | 050.2636.DeerValleyTieBack | 2017-04-19 | 2017-05-31 | 12471.56 | 12471.56 | 10075.67 | Non Functional
201705 | 050.45861 | 050.2735CastleridgeReloc | 2017-04-21 | 2017-06-30 | 47798.63 | 47798.63 | 39620.4 | Non Functional
201705 | 050.45862 | Husband.Clarkline.Rd.Easement | 2017-04-27 | 2017-09-28 | 7338.18 | 7338.18 | 3464.98 | Non Functional
201705 | 050.45870 | 050.2635.McBith Lane Main Ext | 2017-05-01 | 2017-09-28 | 1205.48 | 1205.48 | 2524.3 | Non Functional
201705 | 050.45878 | 050.2634.Thornridge Tie-back | 2017-05-01 | 2017-09-28 | 6120.47 | 6120.47 | 6399.56 | Non Functional
201705 | 050.45902 | 050.2734.Fox.Chase.Ext | 2017-04-28 | 2017-06-30 | 14469.62 | 14469.62 | 9191.65 | Non Functional
201705 | 050.45983 | 050.2734.Hwy31W Ext-Buchanon | 2017-05-15 | 2017-09-30 | 49153.71 | 49153.71 | 44799.33 | Non Functional
201705 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201706 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201706 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201706 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201706 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201706 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201706 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201706 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201706 | 050.43273 | 050.2637.Greenway Village Ext | 2016-07-01 | 2017-09-30 | 10683.88 | 10683.88 | 29092.38 | Non Functional
201706 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201706 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201706 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201706 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201706 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201706 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201706 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201706 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201706 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201706 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201706 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201706 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201706 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201706 | 050.44441 | Paducah Leak Repairs | 2016-10-01 | 2017-12-31 | 134735.54 | 322051.46 | 254373.71 | Non Functional
201706 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201706 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201706 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201706 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201706 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201706 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201706 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201706 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201706 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201706 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201706 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201706 | 050.44837 | PRP.2637.Glenwood Dr | 2017-07-05 | 2017-09-29 | 863980.83 | 863980.83 | 430797.61 | Non Functional
201706 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201706 | 050.44876 | PRP.2636. W.5th. St. | 2017-02-02 | 2017-07-31 | 386952.38 | 386952.38 | 306816.45 | Non Functional
201706 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201706 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201706 | 050.45027 | 050.2637.Villa Ridge Dr Ext | 2017-03-01 | 2017-12-28 | 3444.54 | 3444.54 | 819.9 | Non Functional
201706 | 050.45080 | 050.2638.Stacks Ln Replace | 2017-01-10 | 2017-09-28 | 19632.22 | 37206.63 | 32865.7 | Non Functional
201706 | 050.45083 | PRP.2734.Alumni Ave | 2017-04-01 | 2017-09-28 | 276511.07 | 276511.07 | 214785.96 | Non Functional
201706 | 050.45099 | 050.2734.WilkeyIndPkExt | 2017-01-10 | 2017-07-31 | 31557.04 | 31557.04 | 14829.29 | Non Functional
201706 | 050.45128 | 050.2739.SummersvilleSec.II | 2017-01-16 | 2017-05-31 | 20832.68 | 20832.68 | 15864.76 | Non Functional
201706 | 050.45138 | 050.2739.TripleCrown I | 2017-02-01 | 2017-04-28 | 24626.39 | 24626.39 | 21237.7 | Non Functional
201706 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201706 | 050.45160 | 050.2637.J Sanders Blvd Ext 2 | 2017-01-20 | 2017-09-30 | 5172.89 | 5172.89 | 7784.39 | Non Functional
201706 | 050.45177 | 2638.South Reinforcement | 2017-03-01 | 2017-09-30 | 351519.27 | 351519.27 | 280306.14 | Non Functional
201706 | 050.45198 | 050.2736.Crofton TB Replace | 2017-03-01 | 2017-09-28 | 54149.59 | 54149.59 | 45432.13 | Non Functional
201706 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201706 | 050.45377 | PRP.2734.6Th.&BlakeyCC | 2017-07-05 | 2017-08-25 | 52467.73 | 52467.73 | 40794.13 | Non Functional
201706 | 050.45379 | PRP.2735. Old Bardstown Rd. | 2017-03-02 | 2017-09-20 | 791469.23 | 791469.23 | 243755.31 | Non Functional
201706 | 050.45416 | PRP.2734.7TH. and Winter | 2017-07-05 | 2017-09-29 | 354813.1 | 354813.1 | 164437.62 | Non Functional
201706 | 050.45461 | 050.2734.ERX - B.G. | 2017-02-27 | 2017-09-28 | 27520.28 | 27520.28 | 23098.25 | Non Functional
201706 | 050.45462 | 050.2735.ERX - Glagow | 2017-02-27 | 2017-09-28 | 7057.05 | 7057.05 | 4019.63 | Non Functional
201706 | 050.45472 | 050.2609.BonHarbor.P&AWells | 2017-03-01 | 2017-07-24 | 330026.86 | 239760.53 | 134910.24 | Non Functional
201706 | 050.45481 | 050.2636.BreckenridgeRetire | 2017-03-01 | 2017-03-31 | 3283.61 | 3283.61 | 501.8 | Non Functional
201706 | 050.45488 | PRP.2738.S.Columbia-Gowdy | 2017-03-02 | 2017-09-27 | 584142.3 | 584142.3 | 348820.65 | Non Functional
201706 | 050.45506 | 050.2634.YZ Replace | 2017-04-01 | 2017-09-30 | 61675.86 | 66486.12 | 66991.71 | Non Functional
201706 | 050.45523 | 050.2638.Beadlestown Replace | 2016-10-01 | 2017-11-30 | 201029.75 | 201029.75 | 106305.53 | Non Functional
201706 | 050.45546 | 050.2636.Fairview.Spur.Reg | 2017-03-10 | 2018-09-30 | 42153.37 | 42153.37 | 22417.81 | Non Functional
201706 | 050.45547 | 050.2637.KY-Dam Rd Rev Ext | 2017-04-01 | 2017-09-28 | 1238.4 | 1238.4 | 2519.79 | Non Functional
201706 | 050.45563 | 050.2609.Hickory VLV Dist. | 2017-02-13 | 2018-02-13 | 310881.47 | 310881.47 | 306699.69 | Non Functional
201706 | 050.45564 | 050.2609.Hickory Valve Lot | 2017-02-09 | 2018-02-09 | 713632.54 | 713632.54 | 223451.49 | Non Functional
201706 | 050.45572 | 050.2734.ViningsSub. | 2017-02-01 | 2017-08-31 | 15214.43 | 15214.43 | 2164.41 | Non Functional
201706 | 050.45583 | Bowling Green.Phone.System | 2017-03-14 | 2017-08-31 | 20413.8 | 20413.8 | 22147.14 | Non Functional
201706 | 050.45586 | 3302.KY.Desktop.Replc.FY17 | 2017-03-14 | 2017-08-10 | 20413.8 | 20413.8 | 10525.23 | Non Functional
201706 | 050.45625 | 050.2734.ViningsApproach | 2017-03-31 | 2017-07-29 | 118033.64 | 118033.64 | 79972.58 | Non Functional
201706 | 050.45627 | 050.2734.Plano Rd Reg Sta | 2017-03-21 | 2017-09-29 | 91208.89 | 91208.89 | 59966.36 | Non Functional
201706 | 050.45687 | 050.2736.Calvin Dr Station | 2017-04-01 | 2017-09-28 | 18243.77 | 47963.64 | 46333.82 | Non Functional
201706 | 050.45730 | Groebner.Short.Locator.PD/S.17 | 2017-04-07 | 2017-06-15 | 2908.46 | 2908.46 | 1636.57 | Non Functional
201706 | 050.45762 | 050.2739.Commerce Crossing | 2017-04-10 | 2017-09-30 | 71496.47 | 71496.47 | 34722.93 | Non Functional
201706 | 050.45775 | PRP.2636.Westview - Wink | 2017-05-01 | 2017-09-28 | 450873.9 | 450873.9 | 261193.68 | Non Functional
201706 | 050.45832 | 050.2734.ElktonTB.Reloc | 2017-03-31 | 2017-09-29 | 118496.48 | 118496.48 | 31050.46 | Non Functional
201706 | 050.45861 | 050.2735CastleridgeReloc | 2017-04-21 | 2017-06-30 | 47798.63 | 47798.63 | 39620.4 | Non Functional
201706 | 050.45862 | Husband.Clarkline.Rd.Easement | 2017-04-27 | 2017-09-28 | 7338.18 | 7338.18 | 3464.98 | Non Functional
201706 | 050.45870 | 050.2635.McBith Lane Main Ext | 2017-05-01 | 2017-09-28 | 1205.48 | 1205.48 | 2524.3 | Non Functional
201706 | 050.45878 | 050.2634.Thornridge Tie-back | 2017-05-01 | 2017-09-28 | 6120.47 | 6120.47 | 6399.56 | Non Functional
201706 | 050.45882 | 2636.Knottsville-Mount Zion | 2017-04-20 | 2017-09-30 | 14023.91 | 33338.95 | 7982.33 | Non Functional
201706 | 050.45899 | 050.2734.ShakerMuseumRd | 2017-05-02 | 2017-06-30 | 7313.32 | 7313.32 | 8551.49 | Non Functional
201706 | 050.45900 | 050.2734.Lexington.Pl-Frk | 2017-05-02 | 2017-07-29 | 13721.4 | 13721.4 | 14350.47 | Non Functional
201706 | 050.45902 | 050.2734.Fox.Chase.Ext | 2017-04-28 | 2017-06-30 | 14469.62 | 14469.62 | 9191.65 | Non Functional
201706 | 050.45983 | 050.2734.Hwy31W Ext-Buchanon | 2017-05-15 | 2017-09-30 | 49153.71 | 49153.71 | 44799.33 | Non Functional
201706 | 050.46010 | 050.2637.Hillmont Main Ext | 2017-05-30 | 2017-09-28 | 2448.19 | 2448.19 | 2115.79 | Non Functional
201706 | 050.46065 | Danville.Phone.System. | 2017-05-28 | 2017-07-31 | 13609.2 | 13609.2 | 8339.94 | Non Functional
201706 | 050.46066 | Madisonville KY Phone System | 2017-05-28 | 2017-07-31 | 13609.2 | 13609.2 | 8270.88 | Non Functional
201706 | 050.46079 | 2734.McGinnisQuarryTGT.Tap | 2017-06-01 | 2017-11-30 | 1135743.21 | 1135743.21 | 841312.1 | Non Functional
201706 | 050.46127 | 050.2734.McCoy Pl. - III | 2017-04-04 | 2017-06-30 | 12739.97 | 12739.97 | 9581.91 | Non Functional
201706 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201707 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201707 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201707 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201707 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201707 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201707 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201707 | 050.43270 | 050.2736.Lovers Lane Main Ext | 2016-07-01 | 2017-09-28 | 29547.68 | 29547.68 | 36027.28 | Non Functional
201707 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201707 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201707 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201707 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201707 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201707 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201707 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201707 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201707 | 050.44113 | 050.2637.Towne Center Ext. | 2016-09-26 | 2017-09-28 | 7958.22 | 20486.72 | 19757.97 | Non Functional
201707 | 050.44129 | 2739.Hwy53 to Lat Line 12 HPS | 2016-10-03 | 2017-09-30 | 7569187.31 | 7569187.31 | 7703034.05 | Non Functional
201707 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201707 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201707 | 050.44433 | 2612.KY.ERX Modems Upgrades | 2016-10-01 | 2017-06-30 | 11712.97 | 11712.97 | 12795.1 | Non Functional
201707 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201707 | 050.44579 | Hickory.Grandview Rectifiers | 2016-10-01 | 2017-07-31 | 13330.11 | 13330.11 | 10540.12 | Non Functional
201707 | 050.44597 | BonHarbor.Wireless.Transmitter | 2016-10-01 | 2017-07-31 | 58516.3 | 58516.3 | 44536.09 | Non Functional
201707 | 050.44662 | KY.Transp.Modem.Upgrade | 2016-11-01 | 2017-04-28 | 44003.08 | 44003.08 | 46432.97 | Non Functional
201707 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201707 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201707 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201707 | 050.44724 | 050.2609.Grandview.Wells | 2016-11-09 | 2017-08-08 | 1059737.06 | 1059737.06 | 923001.92 | Non Functional
201707 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201707 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201707 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201707 | 050.44837 | PRP.2637.Glenwood Dr | 2017-07-05 | 2017-09-29 | 863980.83 | 863980.83 | 430797.61 | Non Functional
201707 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201707 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201707 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201707 | 050.45027 | 050.2637.Villa Ridge Dr Ext | 2017-03-01 | 2017-12-28 | 3444.54 | 3444.54 | 819.9 | Non Functional
201707 | 050.45083 | PRP.2734.Alumni Ave | 2017-04-01 | 2017-09-28 | 276511.07 | 276511.07 | 214785.96 | Non Functional
201707 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201707 | 050.45198 | 050.2736.Crofton TB Replace | 2017-03-01 | 2017-09-28 | 54149.59 | 54149.59 | 45432.13 | Non Functional
201707 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201707 | 050.45377 | PRP.2734.6Th.&BlakeyCC | 2017-07-05 | 2017-08-25 | 52467.73 | 52467.73 | 40794.13 | Non Functional
201707 | 050.45379 | PRP.2735. Old Bardstown Rd. | 2017-03-02 | 2017-09-20 | 791469.23 | 791469.23 | 243755.31 | Non Functional
201707 | 050.45416 | PRP.2734.7TH. and Winter | 2017-07-05 | 2017-09-29 | 354813.1 | 354813.1 | 164437.62 | Non Functional
201707 | 050.45454 | PRP.2635.Baldwin Ave | 2017-06-06 | 2017-09-30 | 69918.64 | 96755.23 | 56642.3 | Non Functional
201707 | 050.45461 | 050.2734.ERX - B.G. | 2017-02-27 | 2017-09-28 | 27520.28 | 27520.28 | 23098.25 | Non Functional
201707 | 050.45462 | 050.2735.ERX - Glagow | 2017-02-27 | 2017-09-28 | 7057.05 | 7057.05 | 4019.63 | Non Functional
201707 | 050.45472 | 050.2609.BonHarbor.P&AWells | 2017-03-01 | 2017-07-24 | 330026.86 | 239760.53 | 134910.24 | Non Functional
201707 | 050.45481 | 050.2636.BreckenridgeRetire | 2017-03-01 | 2017-03-31 | 3283.61 | 3283.61 | 501.8 | Non Functional
201707 | 050.45488 | PRP.2738.S.Columbia-Gowdy | 2017-03-02 | 2017-09-27 | 584142.3 | 584142.3 | 348820.65 | Non Functional
201707 | 050.45506 | 050.2634.YZ Replace | 2017-04-01 | 2017-09-30 | 61675.86 | 66486.12 | 66991.71 | Non Functional
201707 | 050.45523 | 050.2638.Beadlestown Replace | 2016-10-01 | 2017-11-30 | 201029.75 | 201029.75 | 106305.53 | Non Functional
201707 | 050.45546 | 050.2636.Fairview.Spur.Reg | 2017-03-10 | 2018-09-30 | 42153.37 | 42153.37 | 22417.81 | Non Functional
201707 | 050.45563 | 050.2609.Hickory VLV Dist. | 2017-02-13 | 2018-02-13 | 310881.47 | 310881.47 | 306699.69 | Non Functional
201707 | 050.45564 | 050.2609.Hickory Valve Lot | 2017-02-09 | 2018-02-09 | 713632.54 | 713632.54 | 223451.49 | Non Functional
201707 | 050.45572 | 050.2734.ViningsSub. | 2017-02-01 | 2017-08-31 | 15214.43 | 15214.43 | 2164.41 | Non Functional
201707 | 050.45586 | 3302.KY.Desktop.Replc.FY17 | 2017-03-14 | 2017-08-10 | 20413.8 | 20413.8 | 10525.23 | Non Functional
201707 | 050.45625 | 050.2734.ViningsApproach | 2017-03-31 | 2017-07-29 | 118033.64 | 118033.64 | 79972.58 | Non Functional
201707 | 050.45627 | 050.2734.Plano Rd Reg Sta | 2017-03-21 | 2017-09-29 | 91208.89 | 91208.89 | 59966.36 | Non Functional
201707 | 050.45687 | 050.2736.Calvin Dr Station | 2017-04-01 | 2017-09-28 | 18243.77 | 47963.64 | 46333.82 | Non Functional
201707 | 050.45730 | Groebner.Short.Locator.PD/S.17 | 2017-04-07 | 2017-06-15 | 2908.46 | 2908.46 | 1636.57 | Non Functional
201707 | 050.45762 | 050.2739.Commerce Crossing | 2017-04-10 | 2017-09-30 | 71496.47 | 71496.47 | 34722.93 | Non Functional
201707 | 050.45775 | PRP.2636.Westview - Wink | 2017-05-01 | 2017-09-28 | 450873.9 | 450873.9 | 261193.68 | Non Functional
201707 | 050.45832 | 050.2734.ElktonTB.Reloc | 2017-03-31 | 2017-09-29 | 118496.48 | 118496.48 | 31050.46 | Non Functional
201707 | 050.45861 | 050.2735CastleridgeReloc | 2017-04-21 | 2017-06-30 | 47798.63 | 47798.63 | 39620.4 | Non Functional
201707 | 050.45862 | Husband.Clarkline.Rd.Easement | 2017-04-27 | 2017-09-28 | 7338.18 | 7338.18 | 3464.98 | Non Functional
201707 | 050.45878 | 050.2634.Thornridge Tie-back | 2017-05-01 | 2017-09-28 | 6120.47 | 6120.47 | 6399.56 | Non Functional
201707 | 050.45882 | 2636.Knottsville-Mount Zion | 2017-04-20 | 2017-09-30 | 14023.91 | 33338.95 | 7982.33 | Non Functional
201707 | 050.45899 | 050.2734.ShakerMuseumRd | 2017-05-02 | 2017-06-30 | 7313.32 | 7313.32 | 8551.49 | Non Functional
201707 | 050.45902 | 050.2734.Fox.Chase.Ext | 2017-04-28 | 2017-06-30 | 14469.62 | 14469.62 | 9191.65 | Non Functional
201707 | 050.45983 | 050.2734.Hwy31W Ext-Buchanon | 2017-05-15 | 2017-09-30 | 49153.71 | 49153.71 | 44799.33 | Non Functional
201707 | 050.46079 | 2734.McGinnisQuarryTGT.Tap | 2017-06-01 | 2017-11-30 | 1135743.21 | 1135743.21 | 841312.1 | Non Functional
201707 | 050.46084 | 050.2636.Lyddane Bridge Rd. | 2017-07-05 | 2017-09-15 | 7863.45 | 7863.45 | 5760.7 | Non Functional
201707 | 050.46142 | 050.2736.Canton Pike Rev Ext | 2017-06-12 | 2017-09-30 | 10209.12 | 10209.12 | 2506.77 | Non Functional
201707 | 050.46166 | South.Reinforce.Ph 2 Easements | 2017-06-01 | 2017-09-30 | 122311.94 | 122311.94 | 77366.92 | Non Functional
201707 | 050.46190 | 050.2634.Westside Vlv Replace | 2017-06-19 | 2017-12-31 | 6079.01 | 6079.01 | 3999.13 | Non Functional
201707 | 050.46206 | 050.2637.Husband Rd Relocate | 2017-08-01 | 2017-11-30 | 40425.94 | 40425.94 | 11596.08 | Non Functional
201707 | 050.46278 | 2734.DrakesRidge.Phas.I | 2017-06-30 | 2017-09-30 | 40266.48 | 40266.48 | 18977.08 | Non Functional
201707 | 050.46282 | 050.2635.Rogers Group Retire | 2017-07-01 | 2017-09-28 | 1033.54 | 1033.54 | 1.12 | Non Functional
201707 | 050.46325 | PRP.2737.Buckeye Rd | 2017-07-11 | 2017-09-28 | 101796.31 | 101796.31 | 43368.07 | Non Functional
201707 | 050.46333 | 050.2637.A.T Massa Dr Replace | 2017-08-01 | 2017-12-31 | 6282.72 | 6282.72 | 655.13 | Non Functional
201707 | 050.46334 | 2636. Mulberry Place | 2017-07-06 | 2017-08-31 | 2878.24 | 11176.57 | 11176.57 | Non Functional
201707 | 050.46365 | 050.2737.Bypass Centre | 2017-07-24 | 2017-09-15 | 2029.97 | 2029.97 | 2613.1 | Non Functional
201707 | 050.46366 | 050.2738.Rose Estate | 2017-07-24 | 2017-08-25 | 2204.66 | 2204.66 | 370.2 | Non Functional
201707 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd
201708 | 050.36386 | 050.2734.Swanee Trail 2 inch | 2014-01-14 | 2015-05-15 | 4043.35 | 4043.35 | 1971.61 | Non Functional
201708 | 050.42070 | HCA Retire - Lone Oak Rd | 2016-01-01 | 2016-10-30 | 1521.32 | 1521.32 | 0.12 | Non Functional
201708 | 050.42071 | HCA Retire - Blandville Rd | 2016-02-15 | 2017-09-28 | 1521.32 | 1521.32 | 436.59 | Non Functional
201708 | 050.42322 | 050.2636.Breck.CO.Ind.RegSta | 2016-03-01 | 2017-09-29 | 112586.2 | 112586.2 | 81638.33 | Non Functional
201708 | 050.42995 | Midwestern Trans.Purch.Boiler | 2016-09-01 | 2018-09-28 | 256810.41 | 256810.41 | 139206 | Non Functional
201708 | 050.43064 | 050.2636.Gateway. Commons | 2016-03-29 | 2017-09-29 | 101867.52 | 101867.52 | 115869.35 | Non Functional
201708 | 050.43309 | 050.2638.Hopewell Rd Relocate | 2016-09-01 | 2017-09-28 | 4528.06 | 4528.06 | 10777.84 | Non Functional
201708 | 050.43475 | 050.2637.N.26th Street Ext | 2016-07-11 | 2017-09-30 | 1449.79 | 1449.79 | 1727.64 | Non Functional
201708 | 050.43914 | PRP.2737.South Marimon | 2016-10-01 | 2017-09-28 | 1690721.08 | 1690721.08 | 1494391.17 | Non Functional
201708 | 050.43932 | WMR.Madisonville.Endpoints.17 | 2016-10-01 | 2017-09-30 | 1385946.76 | 1385946.76 | 1171102.77 | Non Functional
201708 | 050.43972 | PRP.2734.Park-14th | 2016-10-01 | 2017-09-28 | 729341.68 | 729341.68 | 571404.97 | Non Functional
201708 | 050.44038 | PRP.2735.Duke-Ash-Owen St. | 2016-10-01 | 2017-09-28 | 1147772.2 | 1147772.2 | 571463.38 | Non Functional
201708 | 050.44080 | PRP.2637.Lake - City | 2016-10-01 | 2017-09-30 | 4794833.55 | 5695253.01 | 4056683.52 | Non Functional
201708 | 050.44088 | 050.2734.Hwy 31W PI SGlen | 2016-09-12 | 2018-01-31 | 1174025.58 | 1174025.58 | 64092.36 | Non Functional
201708 | 050.44133 | PRP.2635.Marion to Fredonia | 2016-10-03 | 2018-09-29 | 7454960.17 | 7454960.17 | 5582351.79 | Non Functional
201708 | 050.44145 | PRP.2738.Springfield Calvary | 2016-10-01 | 2018-09-30 | 5127834.75 | 5127834.75 | 5086883.87 | Non Functional
201708 | 050.44561 | 050.2637.Cypress Creek Dr | 2016-10-21 | 2017-12-31 | 9823.22 | 9823.22 | 3134.36 | Non Functional
201708 | 050.44665 | 2612.RTU Upgrade.KY.FY17 | 2016-11-01 | 2017-09-30 | 49594.72 | 49594.72 | 37084.25 | Non Functional
201708 | 050.44721 | PRP.2636.E.22nd St | 2017-01-11 | 2017-08-31 | 48753.9 | 98551.4 | 56137.4 | Non Functional
201708 | 050.44722 | PRP.2636.E.20th.St.CC | 2017-02-08 | 2017-09-20 | 19531.75 | 19531.75 | 67.47 | Non Functional
201708 | 050.44726 | KY.Modems.Replc.FY 2017 | 2016-10-01 | 2017-10-31 | 41678.18 | 75496.2 | 75496.2 | Non Functional
201708 | 050.44727 | 050.2734.BG.Pur.Sta.1.Replc. | 2016-11-10 | 2017-07-31 | 919758.49 | 919758.49 | 610365.7 | Non Functional
201708 | 050.44762 | 050.2634.Ruby Dr Rev Ext | 2016-11-14 | 2017-09-30 | 8823.23 | 8823.23 | 3178.12 | Non Functional
201708 | 050.44837 | PRP.2637.Glenwood Dr | 2017-07-05 | 2017-09-29 | 863980.83 | 863980.83 | 430797.61 | Non Functional
201708 | 050.44843 | PRP.2637.Lone Oak | 2016-12-06 | 2017-09-30 | 575102.02 | 575102.02 | 323923.85 | Non Functional
201708 | 050.44957 | PRP.2735.Broadway-Kentucky St | 2017-01-03 | 2017-09-01 | 1016007.01 | 1016007.01 | 742827.67 | Non Functional
201708 | 050.45026 | 050.2637.J Sanders Blvd Ext | 2017-01-03 | 2017-09-30 | 3068.98 | 3068.98 | 1602.93 | Non Functional
201708 | 050.45027 | 050.2637.Villa Ridge Dr Ext | 2017-03-01 | 2017-12-28 | 3444.54 | 3444.54 | 819.9 | Non Functional
201708 | 050.45083 | PRP.2734.Alumni Ave | 2017-04-01 | 2017-09-28 | 276511.07 | 276511.07 | 214785.96 | Non Functional
201708 | 050.45158 | 2737.TBS REPLACEMENTSFY17 | 2017-01-16 | 2017-11-30 | 1648301.87 | 1648301.87 | 935076.77 | Non Functional
201708 | 050.45376 | PRP.2736.Kirkman-Liberty | 2017-04-01 | 2018-03-30 | 1504037.13 | 1504037.13 | 1019879.42 | Non Functional
201708 | 050.45377 | PRP.2734.6Th.&BlakeyCC | 2017-07-05 | 2017-08-25 | 52467.73 | 52467.73 | 40794.13 | Non Functional
201708 | 050.45379 | PRP.2735. Old Bardstown Rd. | 2017-03-02 | 2017-09-20 | 791469.23 | 791469.23 | 243755.31 | Non Functional
201708 | 050.45416 | PRP.2734.7TH. and Winter | 2017-07-05 | 2017-09-29 | 354813.1 | 354813.1 | 164437.62 | Non Functional
201708 | 050.45451 | PRP.2635.North Franklin | 2017-07-06 | 2017-09-30 | 26731.86 | 34292.82 | 1703.28 | Non Functional
201708 | 050.45453 | PRP.2635.Darby St | 2017-06-06 | 2017-09-30 | 22890.29 | 22890.29 | 18143.29 | Non Functional
201708 | 050.45454 | PRP.2635.Baldwin Ave | 2017-06-06 | 2017-09-30 | 69918.64 | 96755.23 | 56642.3 | Non Functional
201708 | 050.45455 | PRP. 2734 Edgewood C.C. | 2017-08-01 | 2017-09-22 | 79868.79 | 79868.79 | 1900.39 | Non Functional
201708 | 050.45461 | 050.2734.ERX - B.G. | 2017-02-27 | 2017-09-28 | 27520.28 | 27520.28 | 23098.25 | Non Functional
201708 | 050.45462 | 050.2735.ERX - Glagow | 2017-02-27 | 2017-09-28 | 7057.05 | 7057.05 | 4019.63 | Non Functional
201708 | 050.45472 | 050.2609.BonHarbor.P&AWells | 2017-03-01 | 2017-07-24 | 330026.86 | 239760.53 | 134910.24 | Non Functional
201708 | 050.45481 | 050.2636.BreckenridgeRetire | 2017-03-01 | 2017-03-31 | 3283.61 | 3283.61 | 501.8 | Non Functional
201708 | 050.45488 | PRP.2738.S.Columbia-Gowdy | 2017-03-02 | 2017-09-27 | 584142.3 | 584142.3 | 348820.65 | Non Functional
201708 | 050.45506 | 050.2634.YZ Replace | 2017-04-01 | 2017-09-30 | 61675.86 | 66486.12 | 66991.71 | Non Functional
201708 | 050.45523 | 050.2638.Beadlestown Replace | 2016-10-01 | 2017-11-30 | 201029.75 | 201029.75 | 106305.53 | Non Functional
201708 | 050.45546 | 050.2636.Fairview.Spur.Reg | 2017-03-10 | 2018-09-30 | 42153.37 | 42153.37 | 22417.81 | Non Functional
201708 | 050.45563 | 050.2609.Hickory VLV Dist. | 2017-02-13 | 2018-02-13 | 310881.47 | 310881.47 | 306699.69 | Non Functional
201708 | 050.45564 | 050.2609.Hickory Valve Lot | 2017-02-09 | 2018-02-09 | 713632.54 | 713632.54 | 223451.49 | Non Functional
201708 | 050.45572 | 050.2734.ViningsSub. | 2017-02-01 | 2017-08-31 | 15214.43 | 15214.43 | 2164.41 | Non Functional
201708 | 050.45625 | 050.2734.ViningsApproach | 2017-03-31 | 2017-07-29 | 118033.64 | 118033.64 | 79972.58 | Non Functional
201708 | 050.45627 | 050.2734.Plano Rd Reg Sta | 2017-03-21 | 2017-09-29 | 91208.89 | 91208.89 | 59966.36 | Non Functional
201708 | 050.45687 | 050.2736.Calvin Dr Station | 2017-04-01 | 2017-09-28 | 18243.77 | 47963.64 | 46333.82 | Non Functional
201708 | 050.45730 | Groebner.Short.Locator.PD/S.17 | 2017-04-07 | 2017-06-15 | 2908.46 | 2908.46 | 1636.57 | Non Functional
201708 | 050.45762 | 050.2739.Commerce Crossing | 2017-04-10 | 2017-09-30 | 71496.47 | 71496.47 | 34722.93 | Non Functional
201708 | 050.45775 | PRP.2636.Westview - Wink | 2017-05-01 | 2017-09-28 | 450873.9 | 450873.9 | 261193.68 | Non Functional
201708 | 050.45832 | 050.2734.ElktonTB.Reloc | 2017-03-31 | 2017-09-29 | 118496.48 | 118496.48 | 31050.46 | Non Functional
201708 | 050.45841 | Emergency regs KY | 2017-04-25 | 2017-09-30 | 17011.5 | 18201.92 | 18201.92 | Non Functional
201708 | 050.45862 | Husband.Clarkline.Rd.Easement | 2017-04-27 | 2017-09-28 | 7338.18 | 7338.18 | 3464.98 | Non Functional
201708 | 050.45878 | 050.2634.Thornridge Tie-back | 2017-05-01 | 2017-09-28 | 6120.47 | 6120.47 | 6399.56 | Non Functional
201708 | 050.45882 | 2636.Knottsville-Mount Zion | 2017-04-20 | 2017-09-30 | 14023.91 | 33338.95 | 7982.33 | Non Functional
201708 | 050.45899 | 050.2734.ShakerMuseumRd | 2017-05-02 | 2017-06-30 | 7313.32 | 7313.32 | 8551.49 | Non Functional
201708 | 050.45983 | 050.2734.Hwy31W Ext-Buchanon | 2017-05-15 | 2017-09-30 | 49153.71 | 49153.71 | 44799.33 | Non Functional
201708 | 050.46079 | 2734.McGinnisQuarryTGT.Tap | 2017-06-01 | 2017-11-30 | 1135743.21 | 1135743.21 | 841312.1 | Non Functional
201708 | 050.46142 | 050.2736.Canton Pike Rev Ext | 2017-06-12 | 2017-09-30 | 10209.12 | 10209.12 | 2506.77 | Non Functional
201708 | 050.46166 | South.Reinforce.Ph 2 Easements | 2017-06-01 | 2017-09-30 | 122311.94 | 122311.94 | 77366.92 | Non Functional
201708 | 050.46190 | 050.2634.Westside Vlv Replace | 2017-06-19 | 2017-12-31 | 6079.01 | 6079.01 | 3999.13 | Non Functional
201708 | 050.46206 | 050.2637.Husband Rd Relocate | 2017-08-01 | 2017-11-30 | 40425.94 | 40425.94 | 11596.08 | Non Functional
201708 | 050.46278 | 2734.DrakesRidge.Phas.I | 2017-06-30 | 2017-09-30 | 40266.48 | 40266.48 | 18977.08 | Non Functional
201708 | 050.46282 | 050.2635.Rogers Group Retire | 2017-07-01 | 2017-09-28 | 1033.54 | 1033.54 | 1.12 | Non Functional
201708 | 050.46325 | PRP.2737.Buckeye Rd | 2017-07-11 | 2017-09-28 | 101796.31 | 101796.31 | 43368.07 | Non Functional
201708 | 050.46333 | 050.2637.A.T Massa Dr Replace | 2017-08-01 | 2017-12-31 | 6282.72 | 6282.72 | 655.13 | Non Functional
201708 | 050.46470 | 2636JamesTerraceDr | 2017-08-02 | 2017-09-21 | 6094.58 | 6094.58 | 655.37 | Non Functional
201708 | 050.46537 | 2739.Waddy Line Ph 2 | 2017-10-01 | 2019-03-30 | 12139301.77 | 12139301.77 | 495619.72 | Non Functional
201708 | OH.050.17884 | WKG State A&G Overhead | 2006-09-20 | 2016-12-31 |  | 0 | -219961.13 | Capital State Ovhd