## 2019 PRP
[12 empty] | DIRECT COSTS |  |  | INDIRECT COSTS
Town | Project Title: | Overall Project Description: | Project / CB Number | Main Installed (ft): | Main Retired | Main Size: |  | # Services Replaced: |  | LP / IP / HP |  | Contract Labor $ | ATO Labor $ | Material $ | Labor OH $ | Stores OH $ | SSU OH $ | BU OH $ | State OH $ | Grand Total
Madisonville | 2634
| PRP.2634.Grapevine Rd | Replace 192' of 4" Epoxy, 4208' of 3" Bare Stl., with 4199' of 4" PE. with 104 Services. | 050.00000 - 00000 | 4199 |  | 4" | 104 | 104 |  | IP/IP | 221707 | 231869 | 13857 | 21940 | 11372.4399 | 1974.6 | 16630.7024 | 18007.4162 | 23541.8056 | 339192.9641
| PRP.2634.Princeton Rd | Replace143' of 1.25" Bare Stl., 490' of 6" Bare Stl., 96' of 2" PE,1,167' of 3" Epoxy, 3,001' of 4" Epoxy, 273' of 2" Bare Stl., 3,929' of 3" Bare Stl., 613' of 2" Epoxy, 5,034' of 4" Bare Stl.,LP with 13,951' of 2" PE IP. Eliminates 4 LP Regulator Stations, 277 Services | 050.00000 - 00000 | 13951 |  | 2" |  | 277 |  | LP/IP |  | 770374 | 46038 | 26856 | 37783.3866 | 2417.04 | 52223.6325 | 56546.7809 | 73925.8374 | 1066164.6774
| PRP.2634.Lunsford St | Replace 323 of 2" Bare Stl LP with 325' of 4" PE LP | 050.47033 - 47026 | 332' |  | 2" |  | 3 |  | LP/LP |  | 11000 | 7604 | 2610 | 6240.6028 | 234.9 | 1484.5079 | 1607.3977 | 2101.4144 | 32882.8228
Hanson | 2634
| PRP.2634.Hanson-Sunset Rd. | Replace 899' of 2" Epoxy, 1827' of 2" Bare Stl., 175' of 1.25" N/A Plastic,with 2217' of 2" PE. with 50 Services | 050.00000 - 00000 | 2217 |  | 2" | 50 | 50 |  | IP/IP | 117058 | 122423 | 7316 | 4267 | 6004.2412 | 384.03 | 8298.9941 | 8985.9969 | 11747.7482 | 169427.0104
Robards | 2634
| PRP.2634.Robards | Replace12' of 2" PE, 71' of 1.25 Epoxy, 3573' of 2" Epoxy,5341' of 2" Bare Stl., 14' of 2" Epoxy, 167' of 1" Epoxy, 684' of 2" N/A Plastic, with9829' of 2" PE., with 108 Services | 050.00000 - 00000 | 9829 |  | 2" | 108 | 108 |  | IP/IP | 524474 | 542757 | 32436 | 18920 | 26620.2252 | 1702.8 | 36793.4581 | 39839.2742 | 52083.4548 | 751152.2123
Slaughters | 2634
| PRP.2634.Slaughters | Replace 7554' of 2" Epoxy, 4604' of 2" Bare Stl., 830' of 1" Epoxy, 333' of 2" N/A Plastic, 1222' of 1.25" N/A Plastic, with12763' of 2" PE., with 99 Services | 050.00000 - 00000 | 12763 |  | 2" | 99 | 99 |  | IP/IP | 679386 | 704772 | 42118 | 24568 | 34566.2426 | 2211.12 | 47776.4409 | 51731.4443 | 67630.5579 | 975373.8057
Princeton | 2635
| PRP.2635.Princeton South Jefferson | Replace 118' of 1.25 Bare Stl. 480' of Unknown, 355' of 4" Epoxy, 87' of 4" PE, 872' of of 3" Bare Stl., 3229' of 2" Bare Stl., 5' of 3" Epoxy, with 2445' of 2" PE. and 2560' of 4" PE, with 70 Services | 050.00000 - 00000 | 5015 |  | 2", 4" | 70 | 70 |  | IP/IP | 414777 | 459803 | 16549 | 18101.88 | 13581.7643 | 1629.1692 | 30374.7349 | 32889.1998 | 42997.3483 | 615926.0965
| PRP.2635.Princeton Southwest | Replace 1268' of 2" Epoxy,527' of 1.25 Bare Stl., 63' of 3" Epoxy, 218' of 2" N/A Plastic, 108' of 1" Bare Stl.,2491' of 2" Bare Stl., 1684' of 3" Bare Stl., 130' of 1.25 PE, with 6610' of 2" PE. with 123 Services | 050.00000 - 00000 | 7810 |  | 2" | 155 | 155 |  | IP/IP | 441353 | 397289 | 21813 | 12724 | 17901.9291 | 1145.16 | 26693.6115 | 28903.3475 | 37786.4864 | 544256.5345
| PRP.2635.Princeton West | Replace 131' of 1" Bare Stl.,234' of 1.25 Bare Stl., 100' of 1.25 N/A PE.,1424' of 2" Epoxy,3913' of 2"Bare Stl., 117' of MDPE 2", 793' of 4" Bare Stl., 317' of 4" Epoxy, with 145 Services | 050.00000 - 00000 | 8676 |  | 2", 4" |  | 145 |  | IP/IP |  | 586889 | 28631 | 20734 | 23497.4617 | 1866.06 | 39254.0637 | 42503.5723 | 55566.5968 | 798941.7544
| PRP.2635.Princeton North | Replace28' of 2" Mill Wrap,286' of 1.25 Epoxy, 828' of 2' PE,461' of 1.25 Bare Stl.,6718' of 2" Bare Stl., 912' of 4" Epoxy, 736' of 2" Epoxy, 97' of Unknown, 435' of 4" Bare Stl.,71' of 1" Bare Stl., 687' of 1.25 N/A Plastic, 2289' of 3" Bare Stl.,and 110' of Epoxy, with 7061' of 2' PE. and 4115' of 4" PE. with 7454 of 2" PE. and 1222' of 4" PE. with 162 Services | 050.00000 - 00000 | 11176 |  | 2", 4" |  | 160 |  | IP/IP |  | 671314 | 36881 | 35093 | 30268.2367 | 3158.37 | 46002.0233 | 49810.1378 | 65118.7581 | 937645.5258
| PRP.2635.Princeton East | Replace 2401' of 3 Bare Stl., 4128' of 2" Bare Stl., 1769' of 2' Epoxy, 30' of 3" Epoxy, 192' of 1.25 Bare Stl.,311' of 4" Bare Stl.,1381' of 4" Epoxy, 197' of 2" Plastic, with 6378' of 2"PE., and 458' of 4" PE. with190 Services | 050.00000 - 00000 | 6836 |  | 2", 4" |  | 165 |  | IP/IP |  | 483798 | 22549 | 14671 | 18505.9643 | 1320.39 | 32109.6851 | 34767.7716 | 45453.2794 | 653175.0905
| PRP.2635.Whipporwill | Replace 3404' of 2" Epoxy, 1422' of 1" Epoxy, 91' of 2" N/A Plastic, 31' of 1" N/A Plastic, with 4948' of 2" PE. with 45 Services | 050.00000 - 00000 | 4948 |  | 2" |  | 45 |  | IP/IP |  | 273228 | 16328 | 9525 | 13400.3896 | 857.25 | 18522.0962 | 20055.3823 | 26219.1925 | 378135.3106
Owensboro | 2636
| PRP.2636.14th St | Replace 763' of 6" Hot Tar, 1,320' of 8" Epoxy, 249' of 1.25" Hot Tar, 208' of 1.25" Epoxy, 894' of8" Hot Tar, 2.345' of 2" Epoxy, 20' of 6" PE, 231' of 4" Epoxy, 766' of 2" PE, 923' of 2" Hot Tar, 309' of 6" Epoxy IP, with 4,780' of 2" PE and 4,200' of 6" PE IP. 67 Services | 050.00000 - 00000 | 8980 |  | 2",6" |  | 67 |  | IP/IP |  | 513036 | 29634 | 50782 | 24320.6238 | 4570.38 | 36857.093 | 39908.1768 | 52173.5339 | 751281.8075
| PRP.2636.Carter - Bosley Rd | Replace 677' of 4" Mill Wrap, 260' of 4" PE, 1,289, of 4" Hot Tar, 212' of 2" PE, 2,695' of 2" Mill Wrap Bare Joint, 8' of 4" PE, 3,875' of 4" Mill Wrap Bare Joint, 4,115' of 2" Epoxy, 1,099' of 4" Epoxy, 1,041' of 2" Mill Wrap IP, with 6,584' of 2" PE, 4,562' of 4" PE and 3,110' of 6" PE IP. 265 Services | 050.00000 - 00000 | 14256 |  | 2",4",6" |  | 265 |  | IP/IP |  | 787216 | 47045 | 67300 | 38609.8315 | 6057 | 55989.4119 | 60624.2969 | 79256.535 | 1142098.0753
| PRP.2636.Ford & Robin Rd | Replace 844' of 2" Hot Tar, 1,569' of 2" Mill Wrap, 271' of 2" Epoxy, 1,213' of 6" Epoxy, 939' of 2" Mill Wrap Bare Joint, 102' of 2" PE with 1,210' of 6" PE and 2,994' of 2" PE IP, 55 Services | 050.00000 - 00000 | 4204 |  | 2',6" |  | 55 |  | IP/IP & LP/IP |  | 238580 | 13873 | 17742 | 11385.5711 | 1596.78 | 16761.0314 | 18148.534 | 23726.2944 | 341813.2109
| PRP.2636.Glenn Ct | Replace 209' of 2" PE, 95' of 4" Epoxy, 1,299' of 3" Epoxy, 982' of 2" Epoxy, 1,678' of 4" Hot Tar IP, with 2,800' of 2" PE and 1,767 of 4" PE IP. 91 Services | 050.00000 - 00000 | 4567 |  | 2",4" |  | 91 |  | IP/IP |  | 252190 | 15070 | 14623 | 12367.949 | 1316.07 | 17479.7827 | 18926.7845 | 24743.7321 | 356717.3182
| PRP.2636.Eastwood Dr | Replace 78' of 3" Epoxy, 48' of 2" PE, 1,200' of 2" Epoxy, 45' of .75" Hot Tar, 10' of 4" PE, 4,449' of 3" Hot Tar, 45' of 2" Mill Wrap, 441' of 2" Hot Tar. | 050.00000 - 00000 | 6300 |  | 2",4" |  | 71 |  | IP/IP |  | 347886 | 20790 | 17136 | 17062.353 | 1542.24 | 23912.9232 | 25892.4699 | 33850.2473 | 488072.2334
| PRP.2636.W 6th & Crabtree | Replace 152' of 2" Hot Tar, 970' of 3" Hot Tar with 1,121' of 2" PE IP | 050.00000 - 00000 | 1121 |  | 2" |  | 24 |  | IP/IP |  | 18422 | 8712 | 2158 | 7149.9384 | 194.22 | 1997.501 | 2162.857 | 2827.5883 | 43624.1047
| PRP.2636.Plum Street | Replace 541' of 4" Hot Tar, 279' of 4" Epoxy, 16' of 2" Epoxy with 840' of 2" PE IP. 23 Services | 050.00000 - 00000 | 840' |  | 2" |  | 23 |  | IP/IP |  | 13269 | 6336 | 1671 | 5199.9552 | 150.39 | 1451.6327 | 1571.801 | 2054.8774 | 31704.6563
| PRP.2636.Davies Dr (Hawesville) | Replace 381' of 2" Hot Tar with 400' of 2" PE. 6 Services | 050.00000 - 00000 | 400 |  | 2" |  | 6 |  | IP/IP |  | 6687 | 4752 | 6120 | 3899.9664 | 550.8 | 1211.941 | 1312.2672 | 1715.5787 | 26249.5533
Hopkinsville | 2736
| PRP.2736.Central Ave | Replace 295' of 4" N/A Plastic, 865' of 2" Epoxy, 1474' of 4" Bare Stl., 1197' of 6" Bare Stl., 4000' of 4" Epoxy, 271' of 2" N/A Plastic, with 6855' of 2" PE., 2130' of 4" PE.,116 Services. 3-Grade 3 Leaks | 050.00000 - 46853 | 8985 |  | 2", 4" |  | 116 |  | LP/IP |  | 496152 | 29651 | 24325 | 24334.5757 | 2189.25 | 34096.9256 | 36919.5188 | 48266.3434 | 695934.6136
| PRP.2736.East 19th St | Replace 1551' of of 4" Bare Stl., 966' of 6" Bare Stl., 1633' of 2" Epoxy, 952' of 2" Bare Stl., 165' of 6" Epoxy, 182' of 2" Plastic,4769' of 4" Epoxy, 177' of 4" PE., with 8855' of 2" PE., 1560' of 4" PE., with 154 Services. 1-Grade 3 Leak | 050.00000 - 00000 | 10415 |  | 2", 4" |  | 154 |  | IP/IP |  | 475116 | 34370 | 25197 | 28207.459 | 2267.73 | 33286.0767 | 36041.5466 | 47118.5357 | 681604.348
| PRP.2736.Phelps Ave | Replace 444' of 2" Bare Stl., 1709' of 4" Bare Stl., 196' of 3" Bare Stl., 338' of 6" Bare Stl., 350' of 2" Plastic,613' of 2" Epoxy, 1303' of 4" PE, 2256' of 4" Epoxy,850' of 6" Epoxy, with 7160' of 2" PE., 2692' Of 4" PE with 151 Services | 050.00000 - 00000 | 9852 |  | 2", 4" |  | 151 |  | IP/IP |  | 544027 | 32511 | 27849 | 26681.7777 | 2506.41 | 37464.4099 | 40565.7683 | 53033.2292 | 764638.5951
Paducah | 2637
| PRP.2637.Clark St Phase 1 | Replace 292' of 1.25" Epoxy, 3,908' of 2" Bare Stl., 101' of 2" Epoxy, 495' 2" PE, 718' of Bare 3" Stl., 1,721' of 4" Bare Stl.,35' of 4" Epoxy, 383' of 6" Bare Stl. IP with 8,041' of 2" PE IP. 92 Services | 050.00000 - 46808 | 8041 |  | 2" |  | 92 |  | IP/IP |  | 489134 | 26535 | 35479 | 21777.2745 | 3193.11 | 34141.7199 | 36968.0212 | 48329.7524 | 695557.878
| PRP.2637.Mississippi-Georgia | Replace 3664' of 2" Bare Stl., 34' of 2" Epoxy Stl., 262' of 2" Plastic746' of 4" Bare Stl. and 40' 0f 4" Epoxy Stl., with 4140" of 2" PE., and 765" of 4" PE. with 115 Services No Leaks, Fence Jumper Route | 050.47397 - 46806 | 9662 |  | 2", 4" |  | 218 |  | IP/IP |  | 562211 | 23815 | 29472 | 19544.9705 | 2652.48 | 37928.2013 | 41067.9531 | 53689.7551 | 770381.36
| PRP.2637.North 26th St | Replace 212' of 1.25" Bare Stl, 392' of 2" PE, 2,367' of 2" Epoxy, 11,318' of 2" Bare Stl. and 1,967' of 6" Bare Stl. with 11,711' of 2" PE,1,492' of 4" PE, and 1,681' of 6" PE. 10-Grade 3 Leaks 391 Services | 050.00000 - 00000 | 14884 |  | 2",4",6" |  | 391 |  | IP/IP |  | 905394 | 49117 | 46981 | 40310.3219 | 4228.29 | 61966.2889 | 67095.9486 | 87717.1805 | 1262810.0299
| PRP.2637.Ohio Street | Replace, 2,890' of 2" Bare Stl., 1,955' of 4" Bare Stl., 307' of 3" Bare Stl., 157' of 2" PE IP, with 2,436' of 2" PE, 2,819' of 4" PE IP. | 050.00000 - 00000 | 5255 |  | 2",4" |  | 50 |  | IP/IP |  | 341112 | 17342 | 19418 | 14232.5794 | 1747.62 | 23360.0535 | 25293.8328 | 33067.6254 | 475573.7111
Russellville | 2734
| PRP.2734.West Russellville HPD | Replace approximately 1.6 miles of 4" Bare Stl., with 5,700' of 6" Stl., and 2,900' of 6" Poly. Replace 5,900' of 2" Coated Stl. to eliminate Isolated Stl. | 050.00000 - 00000 | 14500 |  | 6" |  | 90 |  | HPD/HPD |  | 3059974 | 26001 | 713194 | 21339.0207 | 64187.46 | 233992.9746 | 253363.254 | 331231.777 | 4703283.4863
Bowling Green | 2734
| PRP.2734.Schweizer Rd | Replace approximately 4.8 Miles of 6" Stl Bare HPD pipe with 6" HPD Steel. | 050.00000 - 00000 | 25344 |  | 6" |  |  |  | HPD |  | 4296763 | 24958 | 952392 | 20483.0306 | 85715.28 | 324353.9492 | 351204.4417 | 459143.4215 | 6515013.123
| PRP.2734.Boatlanding Rd. | Replace 185' of 2" unkown Coating, 572' of 2" Epoxy, and 1,121' 2" Bare Stl. with 1,600' of 2" PE. There has been 4 leaks on this pipe in the last year. 17 services | 050.00000 - 00000 | 1600 |  | 2" |  | 17 |  | IP/IP |  | 171380 | 5280 | 3080 | 4333.296 | 277.2 | 11004.2712 | 11915.2208 | 15577.2382 | 222847.2261
| PRP.2734.Jackson & Pearl St | Replace 273' of 1.25" Epoxy, 262' of 2" Epoxy, 1,184' of 6" Epoxy, and 2,501 of 6" Bare Stl. with 4,500' of 6" PE This pipe has a history of leakage and has several leak clamps on it. 15 Services | 050.00000 - 00000 | 4500 |  | 6" |  | 15 |  | IP/IP |  | 327274 | 14850 | 44550 | 12187.395 | 4009.5 | 23966.3742 | 25950.3456 | 33925.9105 | 486713.5253
| PRP.2734.Morgantown Rd & S Sunrise | Replace 3,224' of 1.25" Epoxy ,6' of 1.25" PE, 1,524' of 2" Epoxy, 3,308' of 2" Bare Stl., 2,108' 3" Bare Stl., 269' of 2" unknown coating, 544' of 2" PE, 78' of 4" PE. with 5,810' of 2" PE. 155 services | 050.00000 - 00000 | 5810 |  | 2" |  | 155 |  | IP/IP |  | 446114 | 19173 | 11184 | 15735.2811 | 1006.56 | 29316.1819 | 31743.0181 | 41498.8998 | 595770.9409
| PRP.2734.Nutwood & 10th | Replace 240' of 2" Pe, 27' of 2" Epoxy, 261' of 3" Bare, 167' of 4" Pe, 568' of 4" Epoxy, 3,422' of 4" Bare Stl LP., with 4,800' of 2" IP PE, Retire 2-LP Regulator Stations, 104 services | 050.00000 - 00000 | 4800 |  | 2" |  | 104 |  | LP/IP |  | 574695 | 15840 | 9240 | 12999.888 | 831.6 | 36670.3355 | 39705.9593 | 51909.167 | 741891.9498
| PRP.2734.Glen Lilly & N Sunrise | Replace 2,671' of 1.25" Epoxy, 195' of 2" Epoxy, 122' of 1.25" PE, 4,207' of 2" Epoxy, 1,764' of 2" Bare Stl.,364' of 3" Epoxy, and 357' of 4" Epoxy with 7,814' of 2" PE. 133 services | 050.00000 - 00000 | 7814 |  | 2" |  | 133 |  | IP/IP |  | 570987 | 25786 | 15042 | 21162.5702 | 1353.78 | 37676.295 | 40795.1936 | 53333.166 | 766136.0048
| PRP.2734.WKU Normal Dr - Dogwood Dr. | Replace 393' of 2" Epxoy, 64' of 6" Epoxy, 826' of 6" Bare Stl., 761' of 6" Mill Wrap., with I,800' of 6" PE. Pipe has a history of leakage. 6 Services | 050.00000 - 00000 | 1800 |  | 6" |  | 6 |  | IP/IP |  | 235620 | 5940 | 17820 | 4874.958 | 1603.8 | 15911.0578 | 17228.1984 | 22523.1034 | 321521.1176
| PRP.2734.Holly Dr | Retire 1,400' of 2" Bare Stl. in Holly Trailer Court no meters for 3yrs. | 050.00000 - 00000 |  | 1400 | 2" | [6 empty] | 1584 | 250 | 1299.9888 | 22.5 | 151.5023 | 164.0439 | 214.461 | 3686.496
| PRP.2734.Church Ave | Replace 314' of 1.25" Epoxy, 1,592' of 4" Bare Stl., 430' of 4" Epoxy with 1,900' of 2" PE. History of leaks & several existing leak clamps. 5 srevices. | 050.00000 - 00000 | 1900 |  | 2" |  | 5 |  | IP/IP |  | 21060 | 9504 | 3658 | 7799.9328 | 329.22 | 2323.1118 | 2515.4224 | 3288.5109 | 50478.1979
| PRP.2734.Centerline phase III | Install 22,750' 8" steel to retire 1930 and 1938 Texas Gas lines; Magnolia River design and land rights - construction 2020 | 050.00000 - 00000 | [6 empty] | HPD |  | 1000000 |  |  | 0 | 0 | 60400 | 65400 | 85500 | 1211300
Franklin | 2734
| PRP.2734.Cedar & High St | Replace 129' of 1.25" Bare Stl., 817' of 3" Epoxy, 45' of 2" Epoxy, 132' of 4" PE, 1,078' of 4" Epoxy, 78' of 2" PE LP with 1350' of 2" PE LP. 25 Services | 050.00000 - 00000 | 1350 |  | 2" |  | 25 |  | LP/IP | 11302.5 | 21747 | 35640 | 2600 | 29249.748 | 234 | 4523.1663 | 4897.6006 | 6402.8265 | 105294.3415
Rowletts | 2735
| PRP.2735.Hwy 31W Rowletts | Replace 2800' of 2" Bare Stl., 46' of 2" PE,371' Hot Tar, 987' of 2" Mill Wrap, 900' of 2" Epoxy with 4800' of 2" PE., with 42 Services. No Leaks | 050.00000 - 00000 | 4800 |  | 2" | 2" and 4" | 42 | 71 | IP/IP | 447830 | 385440 | 15840 | 36240 | 12999.888 | 3261.6 | 27016.9055 | 29253.4043 | 38244.1295 | 548295.9273
Cave City | 2735
Oakland | 2735
| PRP.2735.Church St. | Replace 19' of 4" PE, 637' of 1.25" Bare Stl., 2514' of 2" Bare Stl., 1038' of 2" Epoxy, 143' of 2" Hot Tar, 25' of 2" Mill Wrtap, 2110' of 1.25" Epoxy, 54' 0f 1.25" Hot Tar, with 1300' of 2" PE., 2700' of 4" PE., with 27 Services. No Leaks | 050.00000 - 00000 | 4000 |  | 2", 4" |  | 27 |  | IP/IP |  | 328200 | 13200 | 19450 | 10833.24 | 1750.5 | 22229.1509 | 24069.3124 | 31466.7617 | 451198.965
Munfordville/ Woodsonville | 2735
| PRP.2735.South St | Replace 35' of 2" PE, 338' of 4" Epoxy, 180' of 3" Epoxy 1,597' of 2" Epoxy 341' of 4" Mill Wrao, 98' of 1.25" Epoxy, 598' of 2" Mill Wrap., with 3,724' of 2" PE. 30 services. | 050.00000 - 00000 | 3724 |  | 2" |  | 48 |  | IP/IP |  | 325052 | 12289 | 7169 | 10085.5823 | 645.21 | 21152.8129 | 22903.8735 | 29943.1374 | 429240.6161
| PRP.2735.Woodsonville Rd | Replace 477' of 2" Epoxy, 186' of 1.25" Hot Tar, 555' of 2" Mill Wrap, 127' of 1" Hot Tar, 568' of 2" PE, 386' of 4" Epoxy, 1,220' of 1.5" Bare Stl., 2,238' of 1.5" Adyl PE unlocateable, 82' of 2" Adyl PE unlocateable, 298' of 1.25" Epoxy, 125' of 1.5" Epoxy, 42' of 2" Hot Tar, with 5,263' of 2" PE. Replace Woodsonville TBS and retire 1- Reg Station with 2" Distibution Tie back. 28 services. | 050.00000 - 00000 | 5263 |  | 2" |  | 28 |  | IP/IP |  | 370978 | 17368 | 42131 | 14253.9176 | 3791.79 | 26661.5096 | 28868.5882 | 37741.0442 | 541793.8497
Burgin | 2737
| PRP.2737.KY 33 | Replace 333' of 1.25" Mill Wrap Bare Joint, 4,186',2" Mill Wrap bare Joint, 4,007' of 4" Epoxy, 1,975' of 2" PE of which some is unlocateable, 170' of 3" Epoxy, 1,360' of 2" Epoxy.164 Services. | 050.00000 - 00000 | 10295 |  | 2",4" |  | 164 |  | IP/IP |  | 742887 | 33974 | 33348 | 27882.4618 | 3001.32 | 49962.3135 | 54098.2666 | 70724.7981 | 1015878.16
Lancaster | 2737
| PRP.2737.W.Maple Ave | Replace 28' of 6" Mill-Wrap Bare Joint, 198' of Plastic, 676' of 4" Mill Wrap- Bare Joint, 5495' of 2" Mill Wrap - Bare Joint, 9711' of 2" Epoxy with 8450' of 2" PE., 1300' of 4" PE., with 125 Services | 050.00000 - 00000 | 9750 |  | 2", 4" |  | 125 |  | IP/IP |  | 897325 | 24131 | 23059 | 19804.3117 | 2075.31 | 57773.8211 | 62556.4222 | 81782.4785 | 1168507.3434
| PRP.2737.Cowden Ct | Replace 4,745' of Bare 2" Stl. with 4,745' of 2" PE | 050.00000 - 00000 | 4745 |  | 2" |  | 92 |  | IP/IP |  | 342399 | 15659 | 9134 | 12851.3413 | 822.06 | 22617.2474 | 24489.5361 | 32016.1366 | 459988.3214
Danville | 2737
| PRP.2737.Hwy150 | Replace 4,750' 4" Bare Stl,IP with 6" PE IP & 1,525' 2" Bare IP Stl. With 2" PE IP. Allen Asphalt on the 4" line new 6" PE will eliminate pressure issues. | 050.00000 - 00000 | 6275 |  | 2',6" | 40 | 40 | IP/IP | IP/IP | 468682 | 485529 | 20708 | 49960 | 16995.0556 | 4496.4 | 34380.5704 | 37226.6441 | 48667.8604 | 697963.5306
Burgin | 2737
| PRP.2737.Burgin HPD -Shakertown | Replace 10,000' 2" bare with 4" steel; replace 28,000 3" bare with 6" PE | 050.00000 - 0000 | 38000 |  | 4",6" |  |  |  | HPD/IP |  | 2210218 | 4148 | 870794 | 3404.2636 | 78371.46 | 191180.3971 | 207006.5889 | 270627.88 | 3835750.5895
Campbellsville | 2738
| PRP.2738.Robinson Ave | Replace 8335' of Bare Stl. LP with 7735' of 2" & 600' 4" PE IP retire 3-LP Stations | 050.00000 - 00000 | 8335 |  | 2", 4" |  | 107 |  | LP/IP |  | 665803 | 27506 | 18025 | 22574.1742 | 1622.25 | 43746.2081 | 47367.583 | 61925.5098 | 888569.7251
| PRP.2738.Baptist St | Replace 4,345' of 2" Epoxy, 277' of 4" Bare Stl., 663' of 4" PE, 140' of 2" Bare Stl, 34' of 4" Epoxy LP with 5,442' of 2" PE IP. retire 2-LP Reg Sations, 43 Services | 050.00000 - 00000 | 5442 |  | 2" |  | 43 |  | LP/IP |  | 447805 | 17959 | 10476 | 14738.9513 | 942.84 | 29268.2073 | 31691.0721 | 41430.9888 | 594312.0595
| PRP.2738.Springfield Calvary | Replace 16 miles of 4" bare with 6" steel - carried from F18 | 050.44145 - 43698 | 52800 |  | 6" |  |  |  | HPD |  | 5014620 |  |  | 0 | 0 | 302883.048 | 327956.148 | 428750.01 | 6074209.206
|  |  |  | 417189 | [7 empty] | 34187818 | 1039011 | 3489058.88 | 852716.3277 | 314015.2992 | 2383230.3548 | 2580517.6359 | 3373612.5056 | 48219980.0032

## 2020-2022 PRP
FY 2020 - 2022 KY PRP Project Identification | [6 empty] | DIRECT COSTS |  |  | INDIRECT COSTS
Town | Cost Center | Description | Replacement Footage | Main Size: | # Services | LP / IP / HP | Contract Labor | ATO Labor | Material $ | Labor OH $ | Stores OH $ | SSU OH $ | BU OH $ | State OH $ | Grand Total
Hopkinsville | 2736
| PRP.2736.N.19th & S. Main | Replace 306' of 4" N/A Plastic, 360' of 2" Bare Stl., 1285' of 2" Epoxy, 1322' of 4" Bare Stl., 1304' of 6" Bare Stl., 452' of 2" Plastic,18' of 6" Epoxy, 1722' of 4" Epoxy, with 4045' of 2" PE., 2345' of 4" PE., with 95 Services | 6390 | 2", 4" | 95 | IP/IP | 338492 | 15815 | 20039 | 12979.3705 | 1803.51 | 23112.5059 | 25025.7928 | 32717.2062 | 469984.3854
Paducah | 2637
| PRP.2637.Paducah Lateral Replacement | Install 62,900' 12" steel to replace 6" bare steel from Texas Gas Purchase to Meachem Lane; downrate 8" existing 1955 transmission line to distribution; Magnolia River design, land, material only for 2020 |  |  |  |  | 4000000 |  |  | 0 | 0 | 241600 | 261600 | 342000 | 4845200
| PRP.2637.Paducah Lateral Replacement | Install 62,900' 12" steel to replace 6" bare steel from Texas Gas Purchase to Meachem Lane; downrate 8" existing 1955 transmission line to distribution; Magnolia River turnkey; construction for 2021, 2022 | 11650 |  |  | HPD | 5000000 |  |  | 0 | 0 | 302000 | 327000 | 427500 | 6056500
Storage | 2609
| PRP.2609.Fruithill to Elkton replacement | Install 14 miles 12" steel from Fruithill to Elkton, to replace 10" bare steel; rebuild purchase station; Magnolia River turnkey project -- design, material, land for 2022 |  |  |  | HPD | 7000000 |  |  | 0 | 0 | 422800 | 457800 | 598500 | 8479100
| PRP.2609.Fruithill to Elkton replacement | Install 14 miles 12" steel from Fruithill to Elkton, to replace 10" bare steel; rebuild purchase station; Magnolia River turnkey project -- construction for 2023 | 73920 |  |  | HPD | 33000000 |  |  | 0 | 0 | 1993200 | 2158200 | 2821500 | 39972900
Bowling Green | 2734
| PRP.2734.Centerline phase III | Phase II from F19: Install 22,750' 8" steel to retire 1930 and 1938 Texas Gas lines; Magnolia River turnkey - construction 2020 | 22750 |  |  | HPD | 9000000 |  |  | 0 | 0 | 543600 | 588600 | 769500 | 10901700
Russellville | 2734
| Russellville, 9th. St. | Replace 2000' of 2" bare and 5000' of 4" bare with PE | 7000 | 2",4" | 71 |  | 447830 | 17325 | 29975 | 14218.6275 | 2697.75 | 30499.402 | 33024.187 | 43173.8224 | 618743.789
Owensboro | 2636
| PRP.2634.Old Hartford Rd Replacement | Replace one mile 8" bare steel along Old Hartford Road | 5280 |  |  | HPD | 2500000 |  |  | 0 | 0 | 151000 | 163500 | 213750 | 3028250
Harrodsburg | 2737
| PRP.2737.Harrodsburg Lateral Replacement | Install 52,800' 12" steel from Tennessee Gas Pipeline to Harrodsburg, to replace 6" bare steel; Magnolia River design, land, material only for 2020 |  |  |  |  | 3000000 |  |  | 0 | 0 | 181200 | 196200 | 256500 | 3633900
| PRP.2737.Harrodsburg Lateral Replacement | Install 52,800' 12" steel from Tennessee Gas Pipeline to Harrodsburg, to replace 6" bare steel; Magnolia River turnkey - construction 2021, 2022 | 26400 |  |  |  | 11500000 |  |  | 0 | 0 | 694600 | 752100 | 983250 | 13929950
| PRP.2737.Harrodsburg Lateral Replacement | Install 52,800' 12" steel from Tennessee Gas Pipeline to Harrodsburg, to replace 6" bare steel; Magnolia River turnkey - construction 2021, 2022 | 26400 |  |  | HPD | 11500000 |  |  | 0 | 0 | 694600 | 752100 | 983250 | 13929950
Lancaster | 2737
Project 1: | PRP.2737.KY 52-Danville St | Replace 2749' of 6" Mill Wrap - Bare Joint, 946' of 4" Mill Wrap - Bare Joint, 21' of 4" Epoxy, 329' of 2" Mill Wrap - Bare Joint, with 510' of 2" PE., 2125' of 4" PE., 4050' of 6" PE., with 125 Services | 6685 | 2", 4", 6" | 125 | IP/IP | 545496 | 16545 | 52180 | 13578.4815 | 4696.2 | 37793.8182 | 40922.4456 | 53499.5275 | 764711.4728
| PRP.2737.Campbell St | Replace 104' of 1.25 Epoxy, 215' of 1.25 Bare Stl., 7151' of 2" Mill Wrap - Bare Joint, 192' of 2' Bare Stl., 751' of 2" Epoxy, 746' of 4" Mill Wrap - Bare joint, 43' of Plastic, 97' of 4" Epoxy, with 6745' of 2" PE., 825' of 4" PE., with 112 Services | 7570 | 2", 4" | 112 | IP/IP | 828751 | 18736 | 17295 | 15376.6352 | 1556.55 | 52792.5242 | 57162.7663 | 74731.1394 | 1066401.6151
| PRP.2737.Lancaster to Stanford bare replacement | Install 11 miles 6" steel from Lancaster to Stanford, to replace 4" bare steel; rebuild purchase station; Magnolia River turnkey project -- design, material, land for 2022 |  |  |  | HPD | 3000000 |  |  | 0 | 0 | 181200 | 196200 | 256500 | 3633900
| PRP.2737.Lancaster to Stanford bare replacement | Install 11 miles 6" steel from Lancaster to Stanford, to replace 4" bare steel; rebuild purchase station; Magnolia River turnkey project -- construction for 2023 | 58080 |  |  | HPD | 22000000 |  |  | 0 | 0 | 1328800 | 1438800 | 1881000 | 26648600
|  |  | 252125 |  |  |  | 113660569 | 68421 | 119489 | 56153.1147 | 10754.01 | 6878798.2504 | 7448235.1916 | 9737371.6955 | 137979791.2622