## 2008
Duke Energy Kentucky Gas
Year 2008
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 22062.24 |  |  |  |  | 22062.24 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | 3CMN70 | Install New C-M 3" - Kentucky | 7269.03 |  |  |  |  | 7269.03 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 3MCN70 | Install New M-C 3" - Kentucky | 5548.25 |  |  |  |  | 5548.25 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 578.49 |  |  |  |  | 578.49 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 4CMR70 | Replace C-M 4" Kentucky Blanket | 644.36 |  |  |  |  | 644.36 |  |  | 2008-07-31 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 4MCN70 | Install New M-C 4" - Kentucky | 3487.87 |  |  |  |  | 3487.87 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 280.44 |  |  |  |  | 280.44 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 6CMN70 | Install New C-M 6" - Kentucky | 1091.58 |  |  |  |  | 1091.58 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 6MCN70 | Install New M-C 6" - Kentucky | 1749.14 |  |  |  |  | 1749.14 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | KYCIBS07 | CMAP70 | Replace AMRP C-M Plastic | 1245782.58 |  |  |  |  | 1245782.58 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | CMNP70 | New C-M Plastic 2 inch and Under Se | 103842.72 |  |  |  |  | 103842.72 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 196333.33 |  |  |  |  | 196333.33 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7MAINS | D2428 | PP 876161/MARJORIE MANYET | 14647.2 |  |  |  |  | 14647.2 |  |  | 2008-01-03 | 2050-12-31 | 2008-04-01 | 2008-10-21
75086 | WALTONBP | D2467 | PP917529/CHRIS AMPHER | 244084.22 |  |  |  |  | 244084.22 |  |  | 2008-01-04 | 2009-06-30 | 2008-03-01 | 2009-05-15
75086 | WALTONBP | D2468 | PP934616/CHRIS AMPHER | 6774.12 |  |  |  |  | 6774.12 |  |  | 2008-01-04 | 2009-06-30 | 2008-02-01 | 2008-09-05
75086 | WALTONBP | D2469 | PP934619/CHRIS AMPHER | 6439.19 |  |  |  |  | 6439.19 |  |  | 2008-01-04 | 2009-06-30 | 2008-02-01 | 2008-09-05
75086 | G7MAINS | D2582 | PP960454/DONNA CARMACK | 21277.41 |  |  |  |  | 21277.41 |  |  | 2008-01-23 | 2050-12-31 | 2008-02-01 | 2008-10-30
75086 | G7MAINS | D2772 | PP 709296/DONNA CARMACK | 5938.68 |  |  |  |  | 5938.68 |  |  | 2008-02-08 | 2050-12-31 | 2008-02-01 | 2008-10-10
75086 | G7MSCPRD | D2775 | ERLANGER GAS PLANT/DZB | 29952.71 |  |  |  |  | 29952.71 |  |  | 2008-02-08 | 2050-12-31 | 2008-04-01 | 2008-09-05
75086 | G7PUBIMP | D3033 | PP 848340/LAURA MATE | 56245.8 |  |  |  |  | 56245.8 |  |  | 2008-03-04 | 2050-12-31 | 2008-03-01 | 2008-12-05
75086 | G7MAINS | D3074 | PP 976606/JOE GROESCHEN | 17819.71 |  |  |  |  | 17819.71 |  |  | 2008-03-09 | 2050-12-31 | 2008-03-01 | 2008-10-01
75086 | G7MAINS | D3136 | WILDER CROSSINGS PP 980705 AR | 19842.13 |  |  |  |  | 19842.13 |  |  | 2008-03-23 | 2050-12-31 | 2008-05-01 | 2008-08-20
75086 | G7PUBIMP | D3153 | PP 825665/LAURA MATE | 26874.67 |  |  |  |  | 26874.67 |  |  | 2008-03-25 | 2050-12-31 | 2008-04-01 | 2008-08-19
75086 | G7MAINS | D3167 | Turfrider Ct PP 981670 JF | 2037.34 |  |  |  |  | 2037.34 |  |  | 2008-03-27 | 2050-12-31 | 2008-03-01 | 2008-04-09
75086 | KYCIBS08 | D3168 | 2008 KY CIBS MOD 597/JEB | 484483.15 |  |  |  |  | 484483.15 |  |  | 2008-03-27 | 2050-12-31 | 2008-04-01 | 2009-03-12
75086 | KYCIBS02 | D3180 | MODULE 250/DJS close to A9126 | 20850.65 |  |  |  |  | 20850.65 |  |  | 2008-03-28 | 2008-12-31 | 2008-03-01 | 2003-03-18
75086 | KYCIBS05 | D3181 | DIXIE HWY/DJS close to B8053 | 34469.66 |  |  |  |  | 34469.66 |  |  | 2008-03-28 | 2008-12-31 | 2008-03-01 | 2005-10-21
75086 | KYCIBS05 | D3203 | KY CIBS MOD 313 close to B8008 | 8927.62 |  |  |  |  | 8927.62 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2005-09-13
75086 | KYCIBS05 | D3204 | KY CIBS MOD 319 close to B8009 | 28977.34 |  |  |  |  | 28977.34 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2008-08-02
75086 | KYCIBS05 | D3205 | KY CIBS MOD 348 close to B8013 | 369728.14 |  |  |  |  | 369728.14 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-07-12
75086 | KYCIBS05 | D3206 | KY CIBS MOD 352 close to B8017 | 19292.05 |  |  |  |  | 19292.05 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-09-12
75086 | KYCIBS05 | D3207 | KY CIBS MOD 306 close to B7913 | 32963.26 |  |  |  |  | 32963.26 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-03-08
75086 | KYCIBS05 | D3208 | KY CIBS MOD 307 close to B7914 | 18298.98 |  |  |  |  | 18298.98 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-02-15
75086 | KYCIBS05 | D3209 | KY CIBS MOD 311 close to B7915 | 373689.43 |  |  |  |  | 373689.43 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-11-11
75086 | KYCIBS05 | D3210 | KY CIBS MOD 312 close to B7916 | 358471.59 |  |  |  |  | 358471.59 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-10-05
75086 | KYCIBS05 | D3211 | KY CIBS MOD 314 close to B7917 | 30724.91 |  |  |  |  | 30724.91 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2005-09-01
75086 | KYCIBS05 | D3212 | KY CIBS MOD 341 close to B8012 | -1808.16 |  |  |  |  | -1808.16 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-05-31
75086 | KYCIBS06 | D3213 | KY MOD 371 close to C5036 | 350599.44 |  |  |  |  | 350599.44 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-10-05
75086 | G7PUBIMP | D3214 | GRANDVIEW AVE close to C6457 | 101159.71 |  |  |  |  | 101159.71 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-11-17
75086 | G7PUBIMP | D3215 | WALDEN LN close to C6341 | 7123.75 |  |  |  |  | 7123.75 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-12-05
75086 | G7PUBIMP | D3216 | WESLY HLS close to C6343 | 52155.21 |  |  |  |  | 52155.21 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-12-21
75086 | G7PUBIMP | D3243 | PP 983364/ LLM | 86403.53 |  |  |  |  | 86403.53 |  |  | 2008-04-04 | 2050-12-31 | 2008-04-01 | 2009-01-30
75086 | G7MAINS | D3292 | PP 984314/DONNA CARMACK | 4183.39 |  |  |  |  | 4183.39 |  |  | 2008-04-15 | 2050-12-31 | 2008-04-01 | 2008-09-11
75086 | G7PUBIMP | D3299 | PP 978761/LLM | 90301.87 |  |  |  |  | 90301.87 |  |  | 2008-04-15 | 2050-12-31 | 2008-04-01 | 2008-08-28
75086 | G7MAINS | D3343 | PP987555 HARMONY SUBD | -1508.13 |  |  |  |  | -1508.13 |  |  | 2008-04-23 | 2050-12-31 | 2008-05-01 | 2008-08-12
75086 | G7PUBIMP | D3344 | PP 959891/ LLM | 865568.3 |  |  |  |  | 865568.3 |  |  | 2008-04-23 | 2050-12-31 | 2008-05-01 | 2008-12-22
75086 | G7PUBIMP | D3381 | PP 982824/LLM | 19372.63 |  |  |  |  | 19372.63 |  |  | 2008-04-29 | 2050-12-31 | 2008-05-01 | 2008-08-20
75086 | G7PUBIMP | D3411 | PP 967867/LLM | 37.52 |  |  |  |  | 37.52 |  |  | 2008-05-01 | 2050-12-31 | 2008-05-01 | 2008-09-03
75086 | G7PUBIMP | D3413 | PP 980245/LAURA MATE | 55070.45 |  |  |  |  | 55070.45 |  |  | 2008-05-01 | 2050-12-31 | 2008-05-01 | 2008-09-30
75086 | G7PUBIMP | D3414 | PP 967604/LAURA MATE | 129581.9 |  |  |  |  | 129581.9 |  |  | 2008-05-01 | 2050-12-31 | 2008-07-01 | 2008-11-28
75086 | G7MAINS | D3458 | PP990266 WILLIAMS CREEK | 14132.5 |  |  |  |  | 14132.5 |  |  | 2008-05-07 | 2050-12-31 | 2008-05-01 | 2008-09-30
75086 | G7PUBIMP | D3478 | PP 978790 LLM | 14846.93 |  |  |  |  | 14846.93 |  |  | 2008-05-09 | 2050-12-31 | 2008-06-01 | 2008-10-24
75086 | G7LGMR | D3481 | STA 793-CAMP ERNST/CWA | 4826.12 |  |  |  |  | 4826.12 |  |  | 2008-05-09 | 2010-12-31 | 2008-05-01 | 2010-02-24
75086 | KYCIBS08 | D3510 | CIBS MODULE 381/JEB | 813937.27 |  |  |  |  | 813937.27 |  |  | 2008-05-13 | 2050-12-31 | 2008-05-01 | 2009-01-06
75086 | KYCIBS09 | D3576 | KY CIBS MOD 557/JEB | 38456.39 |  |  |  |  | 38456.39 |  |  | 2008-05-23 | 2013-05-22 | 2008-05-01 | 2009-07-13
75086 | KYCIBS08 | D3577 | KY CIBS MOD 383/JEB | 346377.25 |  |  |  |  | 346377.25 |  |  | 2008-05-23 | 2050-12-31 | 2008-05-01 | 2009-06-03
75086 | G7MSCPRD | D3578 | INSTALL BOILER ERL/DZB | 16523.41 |  |  |  |  | 16523.41 |  |  | 2008-05-23 | 2050-12-31 | 2008-07-01 | 2008-10-31
75086 | G7MAINS | D3594 | 4800 bk Far Hill Dr Indep KY | 325.77 |  |  |  |  | 325.77 |  |  | 2008-05-30 | 2050-12-31 | 2008-05-01 | 2008-07-29
75086 | BETMEAIN | D3607 | PP 982909/ CWA | 11615.04 |  |  |  |  | 11615.04 |  |  | 2008-06-01 | 2050-12-31 | 2008-07-01 | 2009-02-17
75086 | BETMEAIN | D3608 | PP 982905/CWA | 1835.42 |  |  |  |  | 1835.42 |  |  | 2008-06-01 | 2050-12-31 | 2008-07-01 | 2009-02-17
75086 | G7MSCPRD | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 19187.12 |  |  |  |  | 19187.12 |  |  | 2008-06-15 | 2050-12-31 | 2008-07-01 | 2008-10-31
75086 | G7LGMR | D3747 | REG 112K-WATERWORKS/CWA | 38717.97 |  |  |  |  | 38717.97 |  |  | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7MAINS | D3748 | PP 985355/CWA | 117940.54 |  |  |  |  | 117940.54 |  |  | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7MAINS | D3759 | PP 1002389/DONNA CARMACK | 5527.21 |  |  |  |  | 5527.21 |  |  | 2008-06-26 | 2010-12-31 | 2008-11-01 | 2009-05-11
75086 | G7MAINS | E0001 | LONGBRANCH ROAD PRI PH 1 | 37595.91 |  |  |  |  | 37595.91 |  |  | 2008-07-02 | 2013-07-02 | 2008-07-01 | 2008-12-02
75086 | G7PUBIMP | E0002 | BRECKENRIDGE RD | 12651.58 |  |  |  |  | 12651.58 |  |  | 2008-07-02 | 2013-07-02 | 2008-07-01 | 2008-07-24
75086 | G7MAINS | E0047 | PP #1005553 Joe Groeschen | 10238.5 |  |  |  |  | 10238.5 |  |  | 2008-07-10 | 2013-07-09 | 2008-08-01 | 2008-11-04
75086 | G7MAINS | E0116 | PP#1005016 Marjorie Manyet | 1738.92 |  |  |  |  | 1738.92 |  |  | 2008-07-14 | 2013-12-31 | 2008-08-01 | 2008-12-12
75086 | G7PUBIMP | E0125 | Lawrence Dr | 19657.29 |  |  |  |  | 19657.29 |  |  | 2008-07-15 | 2008-12-31 | 2008-07-01 | 2008-10-09
75086 | KYCIBS09 | E0172 | MOD 310 | 33415.95 |  |  |  |  | 33415.95 |  |  | 2008-07-23 | 2013-07-01 | 2008-07-01 | 2009-08-26
75086 | KYCIBS09 | E0192 | MOD 376 | 34153.04 |  |  |  |  | 34153.04 |  |  | 2008-07-23 | 2013-07-01 | 2008-07-01 | 2009-07-27
75086 | KYCIBS09 | E0193 | MOD 600 | 33173.57 |  |  |  |  | 33173.57 |  |  | 2008-07-23 | 2010-12-31 | 2008-07-01 | 2009-09-10
75086 | KYCIBS09 | E0194 | MOD 601 | 51653.37 |  |  |  |  | 51653.37 |  |  | 2008-07-23 | 2013-07-30 | 2008-07-01 | 2009-09-22
75086 | KYCIBS09 | E0216 | MOD 384 | 20149.97 |  |  |  |  | 20149.97 |  |  | 2008-07-24 | 2011-12-31 | 2008-08-01 | 2010-01-07
75086 | KYCIBS10 | E0217 | MOD 605 | 20070.48 |  |  |  |  | 20070.48 |  |  | 2008-07-24 | 2010-12-31 | 2008-08-01 | 2010-02-03
75086 | G7PUBIMP | E0294 | Hilton Dr | 1198.94 |  |  |  |  | 1198.94 |  |  | 2008-07-29 | 2009-12-31 | 2008-08-01 | 2009-04-15
75086 | G7REPL | E0318 | AM01 Repl Covington | 120410.1 |  |  |  |  | 120410.1 |  |  | 2008-08-01 | 2008-12-31 | 2008-08-01 | 2009-04-24
75086 | G7MAINS | E0323 | ORLEANS SOUTH PH D PT 3 | 6364.75 |  |  |  |  | 6364.75 |  |  | 2008-08-01 | 2050-12-31 | 2008-08-01 | 2008-10-29
75086 | G7LGMR | E0353 | Install Metretek Equip | 22545.36 |  |  |  |  | 22545.36 |  |  | 2008-08-06 | 2009-12-31 | 2008-08-01 | 2008-10-22
75086 | G7MAINS | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 15150.64 |  |  |  |  | 15150.64 |  |  | 2008-08-11 | 2050-12-31 | 2008-09-01 | 2008-12-05
75086 | G7MAINS | E0468 | Sta 795 Outlet Piping | 10224.03 |  |  |  |  | 10224.03 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7MAINS | E0469 | Sta 795 Inlet Piping | 6703.32 |  |  |  |  | 6703.32 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7LGMR | E0472 | Sta 795 Sandman Dr | 17192.58 |  |  |  |  | 17192.58 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7REPL | E0492 | Scott St. Dry Ridge | 4569.85 |  |  |  |  | 4569.85 |  |  | 2008-08-13 | 2050-12-31 | 2008-08-01 | 2008-10-23
75086 | KYCIBS10 | E0623 | MOD 604 | 15921.19 |  |  |  |  | 15921.19 |  |  | 2008-08-21 | 2013-12-31 | 2008-08-01 | 2010-09-17
75086 | G7MAINS | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 10015.34 |  |  |  |  | 10015.34 |  |  | 2008-08-25 | 2050-12-31 | 2008-09-01 | 2009-01-22
75086 | G7LGMR | E0838 | Sta 794 Shorland Drive | 53745.04 |  |  |  |  | 53745.04 |  |  | 2008-09-02 | 2013-09-02 | 2008-10-01 | 2009-03-05
75086 | G7MAINS | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 1133.03 |  |  |  |  | 1133.03 |  |  | 2008-09-05 | 2051-03-31 | 2008-11-01 | 2009-01-21
75086 | G7PUBIMP | E0916 | KY 17 Moreland Property | 38954.31 |  |  |  |  | 38954.31 |  |  | 2008-09-08 | 2013-09-04 | 2008-09-01 | 2009-03-27
75086 | G7MAINS | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 151.22 |  |  |  |  | 151.22 |  |  | 2008-09-09 | 2050-12-31 | 2008-12-01 | 2010-01-02
75086 | G7MAINS | E1216 | Sta 795 Outlet Piping | 19666.6 |  |  |  |  | 19666.6 |  |  | 2008-09-19 | 2013-09-12 | 2008-10-01 | 2009-03-05
75086 | G7MAINS | E1217 | Sta 794 Inlet Piping | 28375.89 |  |  |  |  | 28375.89 |  |  | 2008-09-19 | 2013-09-12 | 2008-10-01 | 2009-03-05
75086 | G7PUBIMP | E1221 | Brookwood Dr Edgewood | 104087.51 |  |  |  |  | 104087.51 |  |  | 2008-09-19 | 2013-09-17 | 2008-09-01 | 2009-04-22
75086 | LONGBRAN | E1354 | Longbranch PRI Ph2 | 67473.4 |  |  |  |  | 67473.4 |  |  | 2008-09-26 | 2013-09-25 | 2008-11-01 | 2009-10-17
75086 | G7BUPG | E1396 | 19th & Augustine windows | 82167.79 |  |  |  |  | 82167.79 |  |  | 2008-09-30 | 2009-09-30 | 2008-10-01 | 2008-12-18
75086 | G7MAINS | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 503.1 |  |  |  |  | 503.1 |  |  | 2008-10-03 | 2013-08-13 | 2008-12-01 | 2009-02-26
75086 | G7LGMR | E1512 | Reg 113K-8th & Greenup | 56366.43 |  |  |  |  | 56366.43 |  |  | 2008-10-07 | 2013-10-07 | 2008-10-01 | 2009-02-12
75086 | G7MAINS | E1513 | STA 796 Inlet Piping | 43020.2 |  |  |  |  | 43020.2 |  |  | 2008-10-07 | 2013-10-07 | 2008-10-01 | 2009-05-06
75086 | G7LGMR | E1514 | STA 796 - Longbranch Rd | 73554.1 |  |  |  |  | 73554.1 |  |  | 2008-10-07 | 2013-10-07 | 2008-10-01 | 2009-05-06
75086 | G7PUBIMP | E1596 | Grand Ave Main Recloc Newport | 81899.94 |  |  |  |  | 81899.94 |  |  | 2008-10-10 | 2013-10-07 | 2008-10-01 | 2009-02-07
75086 | GITKYCAP | E1653 | Gas Odor Correlation Kentucky | 7100.86 |  |  |  |  | 7100.86 |  |  | 2008-10-14 | 2013-10-01 | 2008-10-01 | 2010-04-25
75086 | G7MAINS | E1732 | Hickory Valley Sub PhA Pt 3 | 526.52 |  |  |  |  | 526.52 |  |  | 2008-10-17 | 2050-12-31 | 2008-11-01 | 2009-04-08
75086 | KYCIBS09 | E2016 | MOD 385 | 29449.54 |  |  |  |  | 29449.54 |  |  | 2008-10-31 | 2013-10-30 | 2008-11-01 | 2010-02-18
75086 | G7LGMR | E2017 | AM3 Telemeter | 2678.64 |  |  |  |  | 2678.64 |  |  | 2008-10-31 | 2013-10-31 | 2008-12-01 | 2009-01-19
75086 | G7MAINS | E2203 | F/L UL-55 Caulk Lane Walton | 5294.49 |  |  |  |  | 5294.49 |  |  | 2008-11-10 | 2013-11-10 | 2008-11-01 | 2009-02-02
75086 | G7MAINS | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 5300.28 |  |  |  |  | 5300.28 |  |  | 2008-11-13 | 2050-12-31 | 2008-11-01 | 2009-03-26
75086 | KYCIBS07 | MCAP70 | Replace AMRP M-C Plastic | 1371974.96 |  |  |  |  | 1371974.96 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2008-12-20
75086 | G7SERVMC | MCNP70 | New M-C Plastic 2 inch and Under Se | 346768.53 |  |  |  |  | 346768.53 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCNS70 | New M-C Steel 2 inch and Under Serv | 9196.52 |  |  |  |  | 9196.52 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 419909.79 |  |  |  |  | 419909.79 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 20706.96 |  |  |  |  | 20706.96 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | OM75086 | NUREVRENI | NUREVRENI | -210 |  |  |  |  | -210 |  |  | 2008-07-01 | 2008-06-28 21:34 | 2008-08-01 | 2009-06-01
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2009
Duke Energy Kentucky Gas
Year 2009
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 417.12 |  |  |  |  | 22479.36 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | 3CMN70 | Install New C-M 3" - Kentucky | 13285 |  |  |  |  | 20554.03 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 3CMR70 | Replace C-M 3" Kentucky Blanket | -41.12 |  |  |  |  | -41.12 |  |  | 2008-07-31 | 2050-12-31 | 2009-04-01
75086 | G7SERVMC | 3MCN70 | Install New M-C 3" - Kentucky | 15154.91 |  |  |  |  | 20703.16 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 2219.24 |  |  |  |  | 2797.73 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 4CMN70 | Install New C-M 4" - Kentucky | 2831.48 |  |  |  |  | 2831.48 |  |  | 2008-07-01 | 2050-12-31 | 2009-01-01 | 2011-03-31
75086 | G7SERVMC | 4MCN70 | Install New M-C 4" - Kentucky | 8177.4 |  |  |  |  | 11665.27 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 508.95 |  |  |  |  | 789.39 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 6CMN70 | Install New C-M 6" - Kentucky | 656 |  |  |  |  | 1747.58 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | KYCIBS07 | CMAP70 | Replace AMRP C-M Plastic | 2523427.58 |  |  |  |  | 3769210.16 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | CMNP70 | New C-M Plastic 2 inch and Under Se | 265824.72 |  |  |  |  | 369667.44 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 377283.65 |  |  |  |  | 573616.98 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7MAINS | D2428 | PP 876161/MARJORIE MANYET | 405.7 |  |  |  |  | 15052.9 |  |  | 2008-01-03 | 2050-12-31 | 2008-04-01 | 2008-10-21
75086 | G7MSCPRD | D2775 | ERLANGER GAS PLANT/DZB | 1014.49 |  |  |  |  | 30967.2 |  |  | 2008-02-08 | 2050-12-31 | 2008-04-01 | 2008-09-05
75086 | KYCIBS08 | D3168 | 2008 KY CIBS MOD 597/JEB | 103372.62 |  |  |  |  | 587855.77 |  |  | 2008-03-27 | 2050-12-31 | 2008-04-01 | 2009-03-12
75086 | KYCIBS02 | D3180 | MODULE 250/DJS close to A9126 | -762.58 |  |  |  |  | 20088.07 |  |  | 2008-03-28 | 2008-12-31 | 2008-03-01 | 2003-03-18
75086 | KYCIBS05 | D3181 | DIXIE HWY/DJS close to B8053 | -1260.66 |  |  |  |  | 33209 |  |  | 2008-03-28 | 2008-12-31 | 2008-03-01 | 2005-10-21
75086 | KYCIBS05 | D3203 | KY CIBS MOD 313 close to B8008 | -326.5 |  |  |  |  | 8601.12 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2005-09-13
75086 | KYCIBS05 | D3204 | KY CIBS MOD 319 close to B8009 | -1250.87 |  |  |  |  | 27726.47 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2008-08-02
75086 | KYCIBS05 | D3205 | KY CIBS MOD 348 close to B8013 | -13522.03 |  |  |  |  | 356206.11 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-07-12
75086 | KYCIBS05 | D3206 | KY CIBS MOD 352 close to B8017 | -705.56 |  |  |  |  | 18586.49 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-09-12
75086 | KYCIBS05 | D3207 | KY CIBS MOD 306 close to B7913 | -1205.56 |  |  |  |  | 31757.7 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-03-08
75086 | KYCIBS05 | D3208 | KY CIBS MOD 307 close to B7914 | -669.25 |  |  |  |  | 17629.73 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-02-15
75086 | KYCIBS05 | D3209 | KY CIBS MOD 311 close to B7915 | -13666.89 |  |  |  |  | 360022.54 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-11-11
75086 | KYCIBS05 | D3210 | KY CIBS MOD 312 close to B7916 | -13110.34 |  |  |  |  | 345361.25 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-10-05
75086 | KYCIBS05 | D3211 | KY CIBS MOD 314 close to B7917 | -1091.37 |  |  |  |  | 29633.54 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2005-09-01
75086 | KYCIBS06 | D3213 | KY MOD 371 close to C5036 | -12822.44 |  |  |  |  | 337777 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-10-05
75086 | G7PUBIMP | D3214 | GRANDVIEW AVE close to C6457 | -3699.7 |  |  |  |  | 97460.01 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-11-17
75086 | G7PUBIMP | D3215 | WALDEN LN close to C6341 | -260.54 |  |  |  |  | 6863.21 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-12-05
75086 | G7PUBIMP | D3216 | WESLY HLS close to C6343 | -1907.48 |  |  |  |  | 50247.73 |  |  | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-12-21
75086 | G7PUBIMP | D3243 | PP 983364/ LLM | 6372.26 |  |  |  |  | 92775.79 |  |  | 2008-04-04 | 2050-12-31 | 2008-04-01 | 2009-01-30
75086 | G7PUBIMP | D3344 | PP 959891/ LLM | -28574.86 |  |  |  |  | 836993.44 |  |  | 2008-04-23 | 2050-12-31 | 2008-05-01 | 2008-12-22
75086 | G7PUBIMP | D3414 | PP 967604/LAURA MATE | 4485.62 |  |  |  |  | 134067.52 |  |  | 2008-05-01 | 2050-12-31 | 2008-07-01 | 2008-11-28
75086 | G7LGMR | D3481 | STA 793-CAMP ERNST/CWA | 98644.79 |  |  |  |  | 103470.91 |  |  | 2008-05-09 | 2010-12-31 | 2008-05-01 | 2010-02-24
75086 | KYCIBS08 | D3510 | CIBS MODULE 381/JEB | 35577.22 |  |  |  |  | 849514.49 |  |  | 2008-05-13 | 2050-12-31 | 2008-05-01 | 2009-01-06
75086 | KYCIBS09 | D3576 | KY CIBS MOD 557/JEB | 459068.93 |  |  |  |  | 497525.32 |  |  | 2008-05-23 | 2013-05-22 | 2008-05-01 | 2009-07-13
75086 | KYCIBS08 | D3577 | KY CIBS MOD 383/JEB | 83677.18 |  |  |  |  | 430054.43 |  |  | 2008-05-23 | 2050-12-31 | 2008-05-01 | 2009-06-03
75086 | G7MSCPRD | D3578 | INSTALL BOILER ERL/DZB | 1316.75 |  |  |  |  | 17840.16 |  |  | 2008-05-23 | 2050-12-31 | 2008-07-01 | 2008-10-31
75086 | G7MSCPRD | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | -524.82 |  |  |  |  | 18662.3 |  |  | 2008-06-15 | 2050-12-31 | 2008-07-01 | 2008-10-31
75086 | G7LGMR | D3747 | REG 112K-WATERWORKS/CWA | -756.14 |  |  |  |  | 37961.83 |  |  | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7MAINS | D3748 | PP 985355/CWA | 12804.29 |  |  |  |  | 130744.83 |  |  | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7MAINS | D3759 | PP 1002389/DONNA CARMACK | 11422.64 |  |  |  |  | 16949.85 |  |  | 2008-06-26 | 2010-12-31 | 2008-11-01 | 2009-05-11
75086 | G7MAINS | E0111 | PP #1006234 Serenity Way | 4548.73 |  |  |  |  | 4548.73 |  |  | 2008-07-14 | 2013-03-31 | 2009-09-01 | 2010-01-10
75086 | G7PUBIMP | E0125 | Lawrence Dr | 0 |  |  |  |  | 19657.29 |  |  | 2008-07-15 | 2008-12-31 | 2008-07-01 | 2008-10-09
75086 | KYCIBS09 | E0172 | MOD 310 | 2448283.8 |  |  |  |  | 2481699.75 |  |  | 2008-07-23 | 2013-07-01 | 2008-07-01 | 2009-08-26
75086 | KYCIBS09 | E0192 | MOD 376 | 858508.66 |  |  |  |  | 892661.7 |  |  | 2008-07-23 | 2013-07-01 | 2008-07-01 | 2009-07-27
75086 | KYCIBS09 | E0193 | MOD 600 | 1709033.78 |  |  |  |  | 1742207.35 |  |  | 2008-07-23 | 2010-12-31 | 2008-07-01 | 2009-09-10
75086 | KYCIBS09 | E0194 | MOD 601 | 1985158.41 |  |  |  |  | 2036811.78 |  |  | 2008-07-23 | 2013-07-30 | 2008-07-01 | 2009-09-22
75086 | KYCIBS09 | E0216 | MOD 384 | 167528.01 |  |  |  |  | 187677.98 |  |  | 2008-07-24 | 2011-12-31 | 2008-08-01 | 2010-01-07
75086 | KYCIBS10 | E0217 | MOD 605 | 504478.31 |  |  |  |  | 524548.79 |  |  | 2008-07-24 | 2010-12-31 | 2008-08-01 | 2010-02-03
75086 | G7MAINS | E0351 | Reg 51 Inlet & Outlet | 295.38 |  |  |  |  | 295.38 |  |  | 2008-08-06 | 2009-12-31 | 2009-06-01 | 2008-08-06
75086 | G7MAINS | E0468 | Sta 795 Outlet Piping | 789.47 |  |  |  |  | 11013.5 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7MAINS | E0469 | Sta 795 Inlet Piping | 167.94 |  |  |  |  | 6871.26 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7LGMR | E0472 | Sta 795 Sandman Dr | 430.71 |  |  |  |  | 17623.29 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | KYCIBS10 | E0623 | MOD 604 | 30999.11 |  |  |  |  | 46920.3 |  |  | 2008-08-21 | 2013-12-31 | 2008-08-01 | 2010-09-17
75086 | G7MAINS | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | -1055.75 |  |  |  |  | 8959.59 |  |  | 2008-08-25 | 2050-12-31 | 2008-09-01 | 2009-01-22
75086 | G7LGMR | E0838 | Sta 794 Shorland Drive | 1288.8 |  |  |  |  | 55033.84 |  |  | 2008-09-02 | 2013-09-02 | 2008-10-01 | 2009-03-05
75086 | G7MAINS | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 2702.82 |  |  |  |  | 3835.85 |  |  | 2008-09-05 | 2051-03-31 | 2008-11-01 | 2009-01-21
75086 | G7PUBIMP | E0916 | KY 17 Moreland Property | -0.58 |  |  |  |  | 38953.73 |  |  | 2008-09-08 | 2013-09-04 | 2008-09-01 | 2009-03-27
75086 | G7MAINS | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 1804.84 |  |  |  |  | 1956.06 |  |  | 2008-09-09 | 2050-12-31 | 2008-12-01 | 2010-01-02
75086 | G7MAINS | E1216 | Sta 795 Outlet Piping | -59.92 |  |  |  |  | 19606.68 |  |  | 2008-09-19 | 2013-09-12 | 2008-10-01 | 2009-03-05
75086 | G7MAINS | E1217 | Sta 794 Inlet Piping | 364.43 |  |  |  |  | 28740.32 |  |  | 2008-09-19 | 2013-09-12 | 2008-10-01 | 2009-03-05
75086 | G7PUBIMP | E1221 | Brookwood Dr Edgewood | 14510.6 |  |  |  |  | 118598.11 |  |  | 2008-09-19 | 2013-09-17 | 2008-09-01 | 2009-04-22
75086 | LONGBRAN | E1354 | Longbranch PRI Ph2 | 53023.81 |  |  |  |  | 120497.21 |  |  | 2008-09-26 | 2013-09-25 | 2008-11-01 | 2009-10-17
75086 | G7BUPG | E1396 | 19th & Augustine windows | -85156.43 |  |  |  |  | -2988.64 |  |  | 2008-09-30 | 2009-09-30 | 2008-10-01 | 2008-12-18
75086 | G7MAINS | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 7130.01 |  |  |  |  | 7633.11 |  |  | 2008-10-03 | 2013-08-13 | 2008-12-01 | 2009-02-26
75086 | G7LGMR | E1512 | Reg 113K-8th & Greenup | 1436.1 |  |  |  |  | 57802.53 |  |  | 2008-10-07 | 2013-10-07 | 2008-10-01 | 2009-02-12
75086 | G7MAINS | E1513 | STA 796 Inlet Piping | -770.41 |  |  |  |  | 42249.79 |  |  | 2008-10-07 | 2013-10-07 | 2008-10-01 | 2009-05-06
75086 | G7LGMR | E1514 | STA 796 - Longbranch Rd | 57.52 |  |  |  |  | 73611.62 |  |  | 2008-10-07 | 2013-10-07 | 2008-10-01 | 2009-05-06
75086 | G7PUBIMP | E1596 | Grand Ave Main Recloc Newport | -75000 |  |  |  |  | 6899.94 |  |  | 2008-10-10 | 2013-10-07 | 2008-10-01 | 2009-02-07
75086 | GITKYCAP | E1653 | Gas Odor Correlation Kentucky | 51744.25 |  |  |  |  | 58845.11 |  |  | 2008-10-14 | 2013-10-01 | 2008-10-01 | 2010-04-25
75086 | G7MAINS | E1732 | Hickory Valley Sub PhA Pt 3 | 8801.43 |  |  |  |  | 9327.95 |  |  | 2008-10-17 | 2050-12-31 | 2008-11-01 | 2009-04-08
75086 | KYCIBS09 | E2016 | MOD 385 | 1121831.5 |  |  |  |  | 1151281.04 |  |  | 2008-10-31 | 2013-10-30 | 2008-11-01 | 2010-02-18
75086 | G7LGMR | E2017 | AM3 Telemeter | 12110.28 |  |  |  |  | 14788.92 |  |  | 2008-10-31 | 2013-10-31 | 2008-12-01 | 2009-01-19
75086 | G7MAINS | E2203 | F/L UL-55 Caulk Lane Walton | 10404.74 |  |  |  |  | 15699.23 |  |  | 2008-11-10 | 2013-11-10 | 2008-11-01 | 2009-02-02
75086 | G7MAINS | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | -22.66 |  |  |  |  | 5277.62 |  |  | 2008-11-13 | 2050-12-31 | 2008-11-01 | 2009-03-26
75086 | G7MAINS | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 76697.26 |  |  |  |  | 76697.26 |  |  | 2008-11-14 | 2050-12-31 | 2009-02-01 | 2009-12-18
75086 | G7MAINS | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 9578.35 |  |  |  |  | 9578.35 |  |  | 2008-11-14 | 2050-12-31 | 2009-02-01 | 2009-02-19
75086 | G7MAINS | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 26158.49 |  |  |  |  | 26158.49 |  |  | 2008-11-17 | 2050-12-31 | 2009-06-01 | 2009-12-25
75086 | G7MAINS | E2592 | PP#1035992 Madison Heights | 30043.44 |  |  |  |  | 30043.44 |  |  | 2008-11-24 | 2050-12-31 | 2009-01-01 | 2009-06-11
75086 | G7MAINS | E2594 | PP#1035916 Gunpowder Trails | 14123.96 |  |  |  |  | 14123.96 |  |  | 2008-11-24 | 2050-12-31 | 2009-01-01 | 2009-05-14
75086 | G7MAINS | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 9036.71 |  |  |  |  | 9036.71 |  |  | 2008-11-24 | 2050-12-31 | 2009-06-01 | 2010-02-28
75086 | G7MAINS | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 5760.39 |  |  |  |  | 5760.39 |  |  | 2008-12-18 | 2013-12-03 | 2009-09-01 | 2010-01-17
75086 | G7MAINS | E3615 | Violet Drive | 13285.37 |  |  |  |  | 13285.37 |  |  | 2009-01-14 | 2014-01-14 | 2009-01-01 | 2009-03-20
75086 | G7REPL | E4280 | Dry Creek LP03 R/W | 20.35 |  |  |  |  | 20.35 |  |  | 2009-02-11 | 2014-02-11 | 2009-05-01 | 2009-09-10
75086 | G7LGMR | E4533 | Reg 111K - 5th & Craig | 74712.21 |  |  |  |  | 74712.21 |  |  | 2009-02-24 | 2014-02-23 | 2009-03-01 | 2010-03-08
75086 | G7LGMR | E4592 | Reg 108K - Hwy & David | 57856.87 |  |  |  |  | 57856.87 |  |  | 2009-02-27 | 2014-02-24 | 2009-04-01 | 2010-01-28
75086 | G7PUBIMP | E4594 | Rogers Rd Villa Hills | 119698.96 |  |  |  |  | 119698.96 |  |  | 2009-02-27 | 2014-02-27 | 2009-04-01 | 2009-09-24
75086 | G7MAINS | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 16365.66 |  |  |  |  | 16365.66 |  |  | 2009-03-02 | 2014-12-31 | 2009-04-01 | 2009-07-20
75086 | G7MAINS | E4954 | PP#1055138 2344 AMSTERDAM RD | 14126.47 |  |  |  |  | 14126.47 |  |  | 2009-03-19 | 2010-12-31 | 2009-06-01 | 2009-10-01
75086 | G7MAINS | E5274 | REG 108K-INLET & OUTLET | 27618.62 |  |  |  |  | 27618.62 |  |  | 2009-03-30 | 2014-03-10 | 2009-04-01 | 2010-01-28
75086 | G7MAINS | E5277 | REG 111K INLET & OUTLET | 105667.82 |  |  |  |  | 105667.82 |  |  | 2009-03-30 | 2014-03-11 | 2009-04-01 | 2009-10-21
75086 | G7MAINS | E5278 | STA 793 INLET PIPING | 26909.64 |  |  |  |  | 26909.64 |  |  | 2009-03-30 | 2014-03-10 | 2009-04-01 | 2010-02-24
75086 | G7MAINS | E5285 | STA 793 - Outlet Piping | 20947.78 |  |  |  |  | 20947.78 |  |  | 2009-03-31 | 2014-03-11 | 2009-04-01 | 2010-02-24
75086 | G7MAINS | E5367 | PP1057596 Hickory Valley Subd | 4181.67 |  |  |  |  | 4181.67 |  |  | 2009-04-02 | 2012-04-01 | 2009-08-01 | 2010-01-03
75086 | LONGBRAN | E5466 | Longbranch Rd/Boone Co | 261742.82 |  |  |  |  | 261742.82 |  |  | 2009-04-07 | 2014-04-07 | 2009-04-01 | 2009-10-16
75086 | G7PUBIMP | E5484 | Dry Creek LP03 Relocation | 26089.45 |  |  |  |  | 26089.45 |  |  | 2009-04-07 | 2014-04-07 | 2009-05-01 | 2009-09-10
75086 | G7PRESIM | E5747 | Legends Way | 63301.63 |  |  |  |  | 63301.63 |  |  | 2009-04-21 | 2014-04-21 | 2009-05-01 | 2009-08-29
75086 | G7MAINS | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 9414.69 |  |  |  |  | 9414.69 |  |  | 2009-04-24 | 2012-04-17 | 2009-09-01 | 2010-01-03
75086 | G7PUBIMP | E6024 | Spillman Dr | 75919.56 |  |  |  |  | 75919.56 |  |  | 2009-04-29 | 2014-04-28 | 2009-05-01 | 2009-09-01
75086 | G7PUBIMP | E6264 | Conrad Ln / North Bend Rd | 35500.38 |  |  |  |  | 35500.38 |  |  | 2009-05-11 | 2014-05-08 | 2009-05-01 | 2009-09-05
75086 | KYCIBS10 | E6366 | MOD 602 | 68584.23 |  |  |  |  | 68584.23 |  |  | 2009-05-15 | 2014-05-14 | 2009-05-01 | 2010-06-26
75086 | KYCIBS10 | E6367 | MOD 377 | 43298.15 |  |  |  |  | 43298.15 |  |  | 2009-05-15 | 2014-05-14 | 2009-05-01 | 2010-07-15
75086 | G7MAINS | E6689 | Delta Ave | 23112.61 |  |  |  |  | 23112.61 |  |  | 2009-05-29 | 2014-05-19 | 2009-07-01 | 2009-12-29
75086 | G7MAINS | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 8412.09 |  |  |  |  | 8412.09 |  |  | 2009-06-04 | 2009-12-31 | 2009-08-01 | 2009-11-24
75086 | G7PUBIMP | E6947 | East Drive/Ft Mitchell | 30944.79 |  |  |  |  | 30944.79 |  |  | 2009-06-09 | 2014-06-05 | 2009-08-01 | 2009-12-16
75086 | G7PRESIM | E7028 | Covington Ave Main Rplc | 80487.54 |  |  |  |  | 80487.54 |  |  | 2009-06-11 | 2014-06-11 | 2009-06-01 | 2010-01-09
75086 | GITKYCAP | E7325 | EXT.004 Outbound Calling | 118851.96 |  |  |  |  | 118851.96 |  |  | 2009-06-24 | 2014-06-01 | 2009-07-01 | 2010-02-20
75086 | G712THST | E7330 | 12TH STREET, COVINGTON | 119236.46 |  |  |  |  | 119236.46 |  |  | 2009-06-24 | 2014-06-24 | 2009-08-01 | 2010-10-22
75086 | G7MAINS | E7331 | STA 535 Inlet Valve | 41629.91 |  |  |  |  | 41629.91 |  |  | 2009-06-24 | 2014-06-23 | 2009-07-01 | 2009-12-17
75086 | G7LGMR | E7332 | STA 535 - F/L UL33 to AM3 | 138633.99 |  |  |  |  | 138633.99 |  |  | 2009-06-24 | 2014-06-23 | 2009-07-01 | 2009-12-17
75086 | G7REPL | E7527 | Stevenson Rd | 68958.5 |  |  |  |  | 68958.5 |  |  | 2009-07-02 | 2014-07-01 | 2009-07-01 | 2010-02-17
75086 | G7MAINS | E7585 | PP#1073980 THORNWILDE PH O | 7612.19 |  |  |  |  | 7612.19 |  |  | 2009-07-08 | 2012-07-07 | 2009-10-01 | 2010-02-28
75086 | G7PUBIMP | E8264 | Vidot Court | 21622.55 |  |  |  |  | 21622.55 |  |  | 2009-07-30 | 2014-07-30 | 2009-08-01 | 2009-12-05
75086 | GITKYCAP | E8625 | Gas Valve Numbering KY | 73510.61 |  |  |  |  | 73510.61 |  |  | 2009-08-05 | 2010-02-26 | 2009-08-01 | 2010-03-11
75086 | G7PUBIMP | E8645 | Newport Pavilion | 64707.7 |  |  |  |  | 64707.7 |  |  | 2009-08-05 | 2014-08-05 | 2009-08-01 | 2010-01-27
75086 | G7MAINS | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 7959.33 |  |  |  |  | 7959.33 |  |  | 2009-08-10 | 2010-08-10 | 2009-11-01 | 2010-03-07
75086 | G7MAINS | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 2291.7 |  |  |  |  | 2291.7 |  |  | 2009-08-11 | 2014-12-10 | 2009-11-01 | 2010-03-21
75086 | GITKYCAP | E9605 | GPI NPMS KY | 17579.75 |  |  |  |  | 17579.75 |  |  | 2009-08-27 | 2011-03-31 | 2009-09-01 | 2011-02-12
75086 | G7MAINS | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 3999.66 |  |  |  |  | 3999.66 |  |  | 2009-09-04 | 2012-09-03 | 2009-09-01 | 2010-01-31
75086 | G712THST | F0844 | Madison Ave | 79091.55 |  |  |  |  | 79091.55 |  |  | 2009-10-01 | 2014-10-01 | 2009-10-01 | 2010-06-10
75086 | G7MAINS | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 446.72 |  |  |  |  | 446.72 |  |  | 2009-10-20 | 2014-10-19 | 2009-12-01 | 2010-03-31
75086 | G7PUBIMP | F1504 | S.R. 35 Warsaw | 6054.46 |  |  |  |  | 6054.46 |  |  | 2009-10-21 | 2014-10-21 | 2009-10-01 | 2010-02-06
75086 | G7BUPG | F2104 | Automatic Gates 19th & Augustine | 144689.3 |  |  |  |  | 144689.3 |  |  | 2009-11-10 | 2010-03-15 | 2009-11-01 | 2010-03-22
75086 | G7LGMR | F2907 | STA 804 Lookaway Drive | 718.03 |  |  |  |  | 718.03 |  |  | 2009-12-09 | 2012-06-30 | 2009-12-01 | 2011-06-24
75086 | GITKYCAP | F3126 | GASTRAN KY PORTION | 1214656.25 |  |  |  |  | 1214656.25 |  |  | 2009-12-16 | 2009-12-31 | 2009-12-01 | 2009-08-11
75086 | FGISEAMGK | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 1047.41 |  |  |  |  | 1047.41 |  |  | 2009-10-21 | 2011-03-30 | 2009-11-01 | 2011-05-01
75086 | KYCIBS07 | MCAP70 | Replace AMRP M-C Plastic | 3900122.18 |  |  |  |  | 5272097.14 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2008-12-20
75086 | G7SERVMC | MCNP70 | New M-C Plastic 2 inch and Under Se | 416995.9 |  |  |  |  | 763764.43 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCNS70 | New M-C Steel 2 inch and Under Serv | 8011.52 |  |  |  |  | 17208.04 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 575250.6 |  |  |  |  | 995160.39 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 8539.27 |  |  |  |  | 29246.23 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | OM75086 | NUREVRENI | NUREVRENI | 210 |  |  |  |  | 0 |  |  | 2008-07-01 | 2008-06-28 21:34 | 2008-08-01 | 2009-06-01
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2010
Duke Energy Kentucky Gas
Year 2010
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | -7067.71 |  |  |  |  | 15411.65 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | 3CMN70 | Install New C-M 3" - Kentucky | 22026.06 |  |  |  |  | 42580.09 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 3CMR70 | Replace C-M 3" Kentucky Blanket | 3043.47 |  |  |  |  | 3002.35 |  |  | 2008-07-31 | 2050-12-31 | 2009-04-01
75086 | G7SERVMC | 3MCN70 | Install New M-C 3" - Kentucky | 18975.32 |  |  |  |  | 39678.48 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 2078.2 |  |  |  |  | 4875.93 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 4CMN70 | Install New C-M 4" - Kentucky | 4801.09 |  |  |  |  | 7632.57 |  |  | 2008-07-01 | 2050-12-31 | 2009-01-01 | 2011-03-31
75086 | G7SERVMC | 4MCN70 | Install New M-C 4" - Kentucky | 395.84 |  |  |  |  | 12061.11 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | KYCIBS07 | CMAP70 | Replace AMRP C-M Plastic | 1515621.49 |  |  |  |  | 5284831.65 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | CMNP70 | New C-M Plastic 2 inch and Under Se | 506882.24 |  |  |  |  | 876549.68 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 818638.51 |  |  |  |  | 1392255.49 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7MSCPRD | D2753 | CONSTANCE CAVERN/DZB | 18130.23 |  |  |  |  | 18130.23 |  |  | 2008-02-06 | 2011-10-31 | 2010-06-01 | 2011-09-23
75086 | G7PUBIMP | D3344 | PP 959891/ LLM | 4534.1 |  |  |  |  | 841527.54 |  |  | 2008-04-23 | 2050-12-31 | 2008-05-01 | 2008-12-22
75086 | G7LGMR | D3481 | STA 793-CAMP ERNST/CWA | 16478.06 |  |  |  |  | 119948.97 |  |  | 2008-05-09 | 2010-12-31 | 2008-05-01 | 2010-02-24
75086 | G7MAINS | D3748 | PP 985355/CWA | 1121.35 |  |  |  |  | 131866.18 |  |  | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7MAINS | D3759 | PP 1002389/DONNA CARMACK | -550.68 |  |  |  |  | 16399.17 |  |  | 2008-06-26 | 2010-12-31 | 2008-11-01 | 2009-05-11
75086 | G7MAINS | E0111 | PP #1006234 Serenity Way | 146.26 |  |  |  |  | 4694.99 |  |  | 2008-07-14 | 2013-03-31 | 2009-09-01 | 2010-01-10
75086 | KYCIBS09 | E0172 | MOD 310 | 113452.4 |  |  |  |  | 2595152.15 |  |  | 2008-07-23 | 2013-07-01 | 2008-07-01 | 2009-08-26
75086 | KYCIBS09 | E0192 | MOD 376 | -74713.28 |  |  |  |  | 817948.42 |  |  | 2008-07-23 | 2013-07-01 | 2008-07-01 | 2009-07-27
75086 | KYCIBS09 | E0193 | MOD 600 | -147600.01 |  |  |  |  | 1594607.34 |  |  | 2008-07-23 | 2010-12-31 | 2008-07-01 | 2009-09-10
75086 | KYCIBS09 | E0194 | MOD 601 | 186494.96 |  |  |  |  | 2223306.74 |  |  | 2008-07-23 | 2013-07-30 | 2008-07-01 | 2009-09-22
75086 | KYCIBS09 | E0216 | MOD 384 | 12528.12 |  |  |  |  | 200206.1 |  |  | 2008-07-24 | 2011-12-31 | 2008-08-01 | 2010-01-07
75086 | KYCIBS10 | E0217 | MOD 605 | 91517.71 |  |  |  |  | 616066.5 |  |  | 2008-07-24 | 2010-12-31 | 2008-08-01 | 2010-02-03
75086 | G7REPL | E0318 | AM01 Repl Covington | 1293.45 |  |  |  |  | 121703.55 |  |  | 2008-08-01 | 2008-12-31 | 2008-08-01 | 2009-04-24
75086 | KYCIBS10 | E0623 | MOD 604 | 902442.06 |  |  |  |  | 949362.36 |  |  | 2008-08-21 | 2013-12-31 | 2008-08-01 | 2010-09-17
75086 | G7MAINS | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 8917.5 |  |  |  |  | 17877.09 |  |  | 2008-08-25 | 2050-12-31 | 2008-09-01 | 2009-01-22
75086 | G7LGMR | E0838 | Sta 794 Shorland Drive | 7276.8 |  |  |  |  | 62310.64 |  |  | 2008-09-02 | 2013-09-02 | 2008-10-01 | 2009-03-05
75086 | G7PUBIMP | E1221 | Brookwood Dr Edgewood | 1131.79 |  |  |  |  | 119729.9 |  |  | 2008-09-19 | 2013-09-17 | 2008-09-01 | 2009-04-22
75086 | GITKYCAP | E1653 | Gas Odor Correlation Kentucky | 2971.09 |  |  |  |  | 61816.2 |  |  | 2008-10-14 | 2013-10-01 | 2008-10-01 | 2010-04-25
75086 | KYCIBS09 | E2016 | MOD 385 | 232198.12 |  |  |  |  | 1383479.16 |  |  | 2008-10-31 | 2013-10-30 | 2008-11-01 | 2010-02-18
75086 | G7MAINS | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | -2769.57 |  |  |  |  | 73927.69 |  |  | 2008-11-14 | 2050-12-31 | 2009-02-01 | 2009-12-18
75086 | G7MAINS | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | -8.32 |  |  |  |  | 9570.03 |  |  | 2008-11-14 | 2050-12-31 | 2009-02-01 | 2009-02-19
75086 | G7MAINS | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 262470.96 |  |  |  |  | 288629.45 |  |  | 2008-11-17 | 2050-12-31 | 2009-06-01 | 2009-12-25
75086 | G7MAINS | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 290.58 |  |  |  |  | 9327.29 |  |  | 2008-11-24 | 2050-12-31 | 2009-06-01 | 2010-02-28
75086 | G7MAINS | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 1282.51 |  |  |  |  | 7042.9 |  |  | 2008-12-18 | 2013-12-03 | 2009-09-01 | 2010-01-17
75086 | G7LGMR | E4533 | Reg 111K - 5th & Craig | 20996.39 |  |  |  |  | 95708.6 |  |  | 2009-02-24 | 2014-02-23 | 2009-03-01 | 2010-03-08
75086 | G7LGMR | E4592 | Reg 108K - Hwy & David | 1224 |  |  |  |  | 59080.87 |  |  | 2009-02-27 | 2014-02-24 | 2009-04-01 | 2010-01-28
75086 | G7LGMR | E4656 | Abandon System STA 58 | 1284.16 |  |  |  |  | 1284.16 |  |  | 2009-03-03 | 2011-04-30 | 2010-03-01 | 2009-11-24
75086 | G7MAINS | E4954 | PP#1055138 2344 AMSTERDAM RD | 672.42 |  |  |  |  | 14798.89 |  |  | 2009-03-19 | 2010-12-31 | 2009-06-01 | 2009-10-01
75086 | G7MAINS | E5274 | REG 108K-INLET & OUTLET | -71.68 |  |  |  |  | 27546.94 |  |  | 2009-03-30 | 2014-03-10 | 2009-04-01 | 2010-01-28
75086 | G7MAINS | E5277 | REG 111K INLET & OUTLET | -8122.43 |  |  |  |  | 97545.39 |  |  | 2009-03-30 | 2014-03-11 | 2009-04-01 | 2009-10-21
75086 | G7MAINS | E5278 | STA 793 INLET PIPING | 2748.21 |  |  |  |  | 29657.85 |  |  | 2009-03-30 | 2014-03-10 | 2009-04-01 | 2010-02-24
75086 | G7MAINS | E5285 | STA 793 - Outlet Piping | 2592.1 |  |  |  |  | 23539.88 |  |  | 2009-03-31 | 2014-03-11 | 2009-04-01 | 2010-02-24
75086 | LONGBRAN | E5466 | Longbranch Rd/Boone Co | -1845.45 |  |  |  |  | 259897.37 |  |  | 2009-04-07 | 2014-04-07 | 2009-04-01 | 2009-10-16
75086 | G7PUBIMP | E5484 | Dry Creek LP03 Relocation | 919.07 |  |  |  |  | 27008.52 |  |  | 2009-04-07 | 2014-04-07 | 2009-05-01 | 2009-09-10
75086 | G7PUBIMP | E6024 | Spillman Dr | 2538.61 |  |  |  |  | 78458.17 |  |  | 2009-04-29 | 2014-04-28 | 2009-05-01 | 2009-09-01
75086 | KYCIBS10 | E6366 | MOD 602 | 1025553.31 |  |  |  |  | 1094137.54 |  |  | 2009-05-15 | 2014-05-14 | 2009-05-01 | 2010-06-26
75086 | KYCIBS10 | E6367 | MOD 377 | 674825 |  |  |  |  | 718123.15 |  |  | 2009-05-15 | 2014-05-14 | 2009-05-01 | 2010-07-15
75086 | G7MAINS | E6689 | Delta Ave | 26569.8 |  |  |  |  | 49682.41 |  |  | 2009-05-29 | 2014-05-19 | 2009-07-01 | 2009-12-29
75086 | GITKYCAP | E7325 | EXT.004 Outbound Calling | 2203.09 |  |  |  |  | 121055.05 |  |  | 2009-06-24 | 2014-06-01 | 2009-07-01 | 2010-02-20
75086 | G712THST | E7330 | 12TH STREET, COVINGTON | 745970.15 |  |  |  |  | 865206.61 |  |  | 2009-06-24 | 2014-06-24 | 2009-08-01 | 2010-10-22
75086 | G7LGMR | E7332 | STA 535 - F/L UL33 to AM3 | 961.78 |  |  |  |  | 139595.77 |  |  | 2009-06-24 | 2014-06-23 | 2009-07-01 | 2009-12-17
75086 | G7REPL | E7527 | Stevenson Rd | 21410.83 |  |  |  |  | 90369.33 |  |  | 2009-07-02 | 2014-07-01 | 2009-07-01 | 2010-02-17
75086 | G7MAINS | E7585 | PP#1073980 THORNWILDE PH O | 8739.97 |  |  |  |  | 16352.16 |  |  | 2009-07-08 | 2012-07-07 | 2009-10-01 | 2010-02-28
75086 | G7MAINS | E8184 | PP 1077275 Ripple Creek Subd | 10425.85 |  |  |  |  | 10425.85 |  |  | 2009-07-27 | 2012-07-24 | 2010-02-01 | 2010-07-10
75086 | GITKYCAP | E8625 | Gas Valve Numbering KY | 5288.73 |  |  |  |  | 78799.34 |  |  | 2009-08-05 | 2010-02-26 | 2009-08-01 | 2010-03-11
75086 | G7PUBIMP | E8645 | Newport Pavilion | -540.21 |  |  |  |  | 64167.49 |  |  | 2009-08-05 | 2014-08-05 | 2009-08-01 | 2010-01-27
75086 | G7MAINS | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | -714.21 |  |  |  |  | 7245.12 |  |  | 2009-08-10 | 2010-08-10 | 2009-11-01 | 2010-03-07
75086 | G7MAINS | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 8693.1 |  |  |  |  | 10984.8 |  |  | 2009-08-11 | 2014-12-10 | 2009-11-01 | 2010-03-21
75086 | GITKYCAP | E9605 | GPI NPMS KY | 99621.8 |  |  |  |  | 117201.55 |  |  | 2009-08-27 | 2011-03-31 | 2009-09-01 | 2011-02-12
75086 | G7MAINS | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 3401.94 |  |  |  |  | 3401.94 |  |  | 2009-09-02 | 2012-09-01 | 2010-08-01 | 2010-11-28
75086 | G712THST | F0844 | Madison Ave | 85919.32 |  |  |  |  | 165010.87 |  |  | 2009-10-01 | 2014-10-01 | 2009-10-01 | 2010-06-10
75086 | CPERNST1 | F0904 | KY 237 Imp Pleasant Valley | 13530.26 |  |  |  |  | 13530.26 |  |  | 2009-10-05 | 2013-02-28 | 2010-10-01 | 2012-11-01
75086 | G7MAINS | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 6407.35 |  |  |  |  | 6854.07 |  |  | 2009-10-20 | 2014-10-19 | 2009-12-01 | 2010-03-31
75086 | G7MAINS | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 13787.58 |  |  |  |  | 13787.58 |  |  | 2009-10-20 | 2014-10-19 | 2010-02-01 | 2010-06-24
75086 | G7BUPG | F2104 | Automatic Gates 19th & Augustine | 1686.47 |  |  |  |  | 146375.77 |  |  | 2009-11-10 | 2010-03-15 | 2009-11-01 | 2010-03-22
75086 | G7LGMR | F2907 | STA 804 Lookaway Drive | 32144.21 |  |  |  |  | 32862.24 |  |  | 2009-12-09 | 2012-06-30 | 2009-12-01 | 2011-06-24
75086 | GITKYCAP | F3126 | GASTRAN KY PORTION | -3770.22 |  |  |  |  | 1210886.03 |  |  | 2009-12-16 | 2009-12-31 | 2009-12-01 | 2009-08-11
75086 | G7MAINS | F3804 | PP#1078349 2025 DECLARATION DR, | 83.49 |  |  |  |  | 83.49 |  |  | 2010-01-08 | 2013-12-31 | 2010-01-01 | 2010-03-25
75086 | G7LGMR | F4704 | STA 149 Gas Heater Removal | 4937.16 |  |  |  |  | 4937.16 |  |  | 2010-01-29 | 2011-06-30 | 2010-07-01 | 2010-10-24
75086 | KYCIBS10 | F6364 | MOD 616 | 44808.8 |  |  |  |  | 44808.8 |  |  | 2010-03-16 | 2010-12-31 | 2010-03-01 | 2010-08-03
75086 | GITKYCAP | F6445 | Gas Telemeter - KY | 34220.69 |  |  |  |  | 34220.69 |  |  | 2010-03-17 | 2010-12-31 | 2010-03-01 | 2010-11-30
75086 | G7LGMR | F6526 | RTU cabinet at LaFarge | 3681.85 |  |  |  |  | 3681.85 |  |  | 2010-03-23 | 2012-09-30 | 2010-03-01 | 2010-06-22
75086 | G7MSCPRD | F6544 | Install backup generator at Erlange | 10055.68 |  |  |  |  | 10055.68 |  |  | 2010-03-23 | 2012-06-30 | 2010-05-01 | 2011-08-01
75086 | G7LGMR | F6547 | Install backup gener Three Mile | 8901.26 |  |  |  |  | 8901.26 |  |  | 2010-03-23 | 2012-03-30 | 2010-04-01 | 2011-10-12
75086 | G7MSCPRD | F6566 | Inst no-flow pump cutoffs Constance | 5007.82 |  |  |  |  | 5007.82 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2011-10-15
75086 | G7MSCPRD | F6567 | Inst flame detectors Constance Cav | 2800.5 |  |  |  |  | 2800.5 |  |  | 2010-03-24 | 2012-06-30 | 2010-06-01 | 2012-09-30
75086 | KYCIBS10 | F6568 | MOD 483 | 206893.98 |  |  |  |  | 206893.98 |  |  | 2010-03-24 | 2010-12-31 | 2010-06-01 | 2010-10-06
75086 | KYCIBS10 | F6569 | MOD 619 | 228575.65 |  |  |  |  | 228575.65 |  |  | 2010-03-24 | 2010-12-31 | 2010-04-01 | 2010-10-19
75086 | KYCIBS10 | F6570 | MOD 620 | 257506.71 |  |  |  |  | 257506.71 |  |  | 2010-03-24 | 2010-12-31 | 2010-06-01 | 2011-01-01
75086 | G7MSCPRD | F6571 | Inst Odorizer and Flame Det Erlange | 125655.46 |  |  |  |  | 125655.46 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2012-01-15
75086 | KYCIBS10 | F7024 | MOD 618 | 309024.04 |  |  |  |  | 309024.04 |  |  | 2010-04-07 | 2010-12-31 | 2010-06-01 | 2010-11-26
75086 | G7LGMR | F7286 | Radio Master Erlanger Tower | 53312.76 |  |  |  |  | 53312.76 |  |  | 2010-04-16 | 2012-12-31 | 2010-05-01 | 2012-09-13
75086 | KYCIBS10 | F7664 | MOD 617 | 251933.65 |  |  |  |  | 251933.65 |  |  | 2010-04-26 | 2010-12-31 | 2010-06-01 | 2011-02-02
75086 | G7MAINS | F7725 | 420 Independence Station Rd | 49095.19 |  |  |  |  | 49095.19 |  |  | 2010-04-26 | 2011-12-31 | 2010-09-01 | 2011-02-16
75086 | GMAINS | F7884 | EMAX 537828 Harmony Subd Ph C | 13717.11 |  |  |  |  | 13717.11 |  |  | 2010-04-28 | 2010-07-30 | 2010-08-01 | 2010-12-11
75086 | G7MAINS | F9305 | EMAX #607352 Treetop Estates Subd | 16630.79 |  |  |  |  | 16630.79 |  |  | 2010-06-08 | 2050-12-31 | 2010-09-01 | 2011-01-22
75086 | G7LGMR | F9465 | Gas Control Router Upgrade KY | 14345.42 |  |  |  |  | 14345.42 |  |  | 2010-06-11 | 2011-03-31 | 2010-06-01 | 2011-03-31
75086 | KYCIBS10 | F9665 | MOD 628 | 440522.92 |  |  |  |  | 440522.92 |  |  | 2010-06-18 | 2010-12-31 | 2010-06-01 | 2010-12-29
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 442.69 |  |  |  |  | 442.69 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | G7LGMR | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 122563.35 |  |  |  |  | 122563.35 |  |  | 2010-07-15 | 2011-04-01 | 2010-08-01 | 2011-02-02
75086 | G7MAINS | G0582 | Reg 114K Inlet & Outlet | 13234.59 |  |  |  |  | 13234.59 |  |  | 2010-07-27 | 2011-04-01 | 2010-08-01 | 2011-02-02
75086 | G7MAINS | G0606 | Sta 804 Inlet Piping | 19035.17 |  |  |  |  | 19035.17 |  |  | 2010-08-02 | 2012-06-30 | 2010-09-01 | 2011-06-24
75086 | G7MAINS | G0607 | Sta 804 Outlet Piping | 14664.87 |  |  |  |  | 14664.87 |  |  | 2010-08-02 | 2012-04-30 | 2010-09-01 | 2011-06-24
75086 | G7MAINS | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 4266.17 |  |  |  |  | 4266.17 |  |  | 2010-08-06 | 2012-02-29 | 2010-10-01 | 2011-02-13
75086 | G7PUBIMP | G0795 | Edgecliff Rd | 34575.21 |  |  |  |  | 34575.21 |  |  | 2010-08-26 | 2011-08-01 | 2010-09-01 | 2011-04-11
75086 | G7PUBIMP | G0796 | Hay & Willow Sts | 26880.28 |  |  |  |  | 26880.28 |  |  | 2010-08-26 | 2011-03-31 | 2010-09-01 | 2010-12-13
75086 | G7MAINS | G0802 | EMAX 919073 Villa Grande Sec 4 | 8428.08 |  |  |  |  | 8428.08 |  |  | 2010-08-27 | 2011-12-31 | 2010-10-01 | 2012-02-14
75086 | G7REPL | G0860 | Tammy Lane | 2221.09 |  |  |  |  | 2221.09 |  |  | 2010-09-03 | 2011-10-15 | 2010-09-01 | 2011-06-19
75086 | G7MAINS | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 8026.9 |  |  |  |  | 8026.9 |  |  | 2010-09-21 | 2011-05-31 | 2010-11-01 | 2011-03-11
75086 | G7MAINS | G1098 | Millakin Place | 66785.93 |  |  |  |  | 66785.93 |  |  | 2010-09-27 | 2011-12-31 | 2010-10-01 | 2011-02-03
75086 | G7MSCPRD | G1322 | Replace Air Dryer Erlanger | 24495.05 |  |  |  |  | 24495.05 |  |  | 2010-10-13 | 2012-06-30 | 2010-12-01 | 2011-05-11
75086 | GITKYCAP | G1357 | Gas Image Project - KY | 26870.12 |  |  |  |  | 26870.12 |  |  | 2010-10-20 | 2011-10-29 | 2010-11-01 | 2011-07-12
75086 | G7REPL | G1427 | Comair Blvd | 35220.02 |  |  |  |  | 35220.02 |  |  | 2010-10-29 | 2011-09-01 | 2010-11-01 | 2011-01-23
75086 | G7REPL | G1456 | UL27 Falmouth Bridge | 148106.7 |  |  |  |  | 148106.7 |  |  | 2010-11-04 | 2011-09-30 | 2010-11-01 | 2011-03-10
75086 | FGISEAMGK | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 15243.15 |  |  |  |  | 16290.56 |  |  | 2009-10-21 | 2011-03-30 | 2009-11-01 | 2011-05-01
75086 | KYCIBS07 | MCAP70 | Replace AMRP M-C Plastic | 1735042.26 |  |  |  |  | 7007139.4 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2008-12-20
75086 | G7SERVMC | MCNP70 | New M-C Plastic 2 inch and Under Se | 438342.13 |  |  |  |  | 1202106.56 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCNS70 | New M-C Steel 2 inch and Under Serv | 4424.85 |  |  |  |  | 21632.89 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 725131.94 |  |  |  |  | 1720292.33 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 10282.72 |  |  |  |  | 39528.95 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | SGITOMSGI | SGARCSRVC | Smart Grid ARC Server Project | -10234.64 |  |  |  |  | -10234.64 |  |  | 2010-09-24 | 2011-01-31 | 2010-10-01 | 2011-03-08
75086 | SGKYCS | SGCSDCI3 | ECS daily usage cap | 12022.52 |  |  |  |  | 12022.52 |  |  | 2010-10-01 | 2014-12-31 | 2010-09-01 | 2010-06-24
75086 | SGKYCS | SGCSECS | Enterprise Cust systems cap | -69710.35 |  |  |  |  | -69710.35 |  |  | 2010-10-01 | 2014-12-31 | 2010-09-01
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | 75.98 |  |  |  |  | 75.98 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | SGKYMTRSY | SGSTRGC | Smart Grid Storage Project | 150106.42 |  |  |  |  | 150106.42 |  |  | 2010-06-16 | 2010-11-30 | 2010-09-01 | 2011-02-17
75086 | SGKYMTRSY | SGSYED11 | EDM.11 SG Scaling/Tech Hlth | 100572.45 |  |  |  |  | 100572.45 |  |  | 2010-09-30 | 2010-03-04 | 2010-09-01 | 2010-06-04
75086 | SGITMTRSY | SGSYED15 | SG EDM.15 EDMS Scalability-Hardware | 16211.86 |  |  |  |  | 16211.86 |  |  | 2010-09-14 | 2010-09-30 | 2010-09-01 | 2011-02-24
75086 | SGITMTRSY | SGSYEDP2 | SG Scalability Phase 2 EDM064 | -19042.48 |  |  |  |  | -19042.48 |  |  | 2010-08-13 | 2012-01-15 | 2010-09-01 | 2011-08-13
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2011
Duke Energy Kentucky Gas
Year 2011
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 49182.32 |  |  |  |  | 64593.97 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | 3CMN70 | Install New C-M 3" - Kentucky | 131.38 |  |  |  |  | 42711.47 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 29092.89 |  |  |  |  | 29092.89 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3CMR70 | Replace C-M 3" Kentucky Blanket | 1662.86 |  |  |  |  | 4665.21 |  |  | 2008-07-31 | 2050-12-31 | 2009-04-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 21498.74 |  |  |  |  | 21498.74 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 5350.98 |  |  |  |  | 10226.91 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVMC | 4CMN70 | Install New C-M 4" - Kentucky | 0 |  |  |  |  | 7632.57 |  |  | 2008-07-01 | 2050-12-31 | 2009-01-01 | 2011-03-31
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 14681.69 |  |  |  |  | 14681.69 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4CMR70 | Replace C-M 4" Kentucky Blanket | 6995.66 |  |  |  |  | 7640.02 |  |  | 2008-07-31 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 14808.5 |  |  |  |  | 14808.5 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 1309.19 |  |  |  |  | 2098.58 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 15415.6 |  |  |  |  | 15415.6 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 2743.55 |  |  |  |  | 2743.55 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | KYCIBS07 | CMAP70 | Replace AMRP C-M Plastic | 11374.25 |  |  |  |  | 5296205.9 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 389350.96 |  |  |  |  | 389350.96 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 |  |  |  |  | 876549.68 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2011-03-31
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 1535091.97 |  |  |  |  | 2927347.46 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7MSCPRD | D2753 | CONSTANCE CAVERN/DZB | 15520.61 |  |  |  |  | 33650.84 |  |  | 2008-02-06 | 2011-10-31 | 2010-06-01 | 2011-09-23
75086 | BETMEAIN | D3607 | PP 982909/ CWA | 19385 |  |  |  |  | 31000.04 |  |  | 2008-06-01 | 2050-12-31 | 2008-07-01 | 2009-02-17
75086 | BETMEAIN | D3608 | PP 982905/CWA | 27565 |  |  |  |  | 29400.42 |  |  | 2008-06-01 | 2050-12-31 | 2008-07-01 | 2009-02-17
75086 | KYCIBS09 | E0194 | MOD 601 | -987.27 |  |  |  |  | 2222319.47 |  |  | 2008-07-23 | 2013-07-30 | 2008-07-01 | 2009-09-22
75086 | G7MAINS | E2595 | 08-2055-5 Thornwilde PH O PT 1 | -325.66 |  |  |  |  | 9001.63 |  |  | 2008-11-24 | 2050-12-31 | 2009-06-01 | 2010-02-28
75086 | G7LGMR | E4656 | Abandon System STA 58 | -44.17 |  |  |  |  | 1239.99 |  |  | 2009-03-03 | 2011-04-30 | 2010-03-01 | 2009-11-24
75086 | KYCIBS10 | E6367 | MOD 377 | 13086.7 |  |  |  |  | 731209.85 |  |  | 2009-05-15 | 2014-05-14 | 2009-05-01 | 2010-07-15
75086 | G712THST | E7330 | 12TH STREET, COVINGTON | 921.04 |  |  |  |  | 866127.65 |  |  | 2009-06-24 | 2014-06-24 | 2009-08-01 | 2010-10-22
75087 | FEBPE1A | EBPE1 | Electronic Billing & Payment Ex Ph1 | 51526.61 |  |  |  |  | 51526.61 |  |  | 2011-05-20 | 2011-12-31 | 2011-06-01 | 2012-03-31
75087 | SGITCS | ECSDCI1 | Enterprise Cust syst DCI1 Capital | 42635.05 |  |  |  |  | 42635.05 |  |  | 2011-02-28 | 2015-06-30 | 2011-03-01 | 2010-09-18
75087 | SGITCS | ECSDCI2 | Enterprise Cust system DCI2 Capital | -34961.93 |  |  |  |  | -34961.93 |  |  | 2011-04-13 | 2015-03-31 | 2011-04-01 | 2011-11-30
75087 | SGITCS | ECSPH2 | Enterprise Cust systems Ph2 Capital | 3.638e-12 |  |  |  |  | 0 |  |  | 2011-02-28 | 2015-06-30 | 2011-03-01
75086 | G7MAINS | F0705 | EMAX 201475 Red Stone Village | 30366.67 |  |  |  |  | 30366.67 |  |  | 2009-09-25 | 2012-12-24 | 2011-09-01 | 2012-01-30
75086 | G712THST | F0844 | Madison Ave | 438.44 |  |  |  |  | 165449.31 |  |  | 2009-10-01 | 2014-10-01 | 2009-10-01 | 2010-06-10
75086 | CPERNST1 | F0904 | KY 237 Imp Pleasant Valley | 328548.81 |  |  |  |  | 342079.07 |  |  | 2009-10-05 | 2013-02-28 | 2010-10-01 | 2012-11-01
75086 | G7MAINS | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 343.32 |  |  |  |  | 14130.9 |  |  | 2009-10-20 | 2014-10-19 | 2010-02-01 | 2010-06-24
75086 | G7LGMR | F2907 | STA 804 Lookaway Drive | 25480.74 |  |  |  |  | 58342.98 |  |  | 2009-12-09 | 2012-06-30 | 2009-12-01 | 2011-06-24
75086 | G7LGMR | F4704 | STA 149 Gas Heater Removal | -136.49 |  |  |  |  | 4800.67 |  |  | 2010-01-29 | 2011-06-30 | 2010-07-01 | 2010-10-24
75086 | G7MSCPRD | F6544 | Install backup generator at Erlange | 4871.43 |  |  |  |  | 14927.11 |  |  | 2010-03-23 | 2012-06-30 | 2010-05-01 | 2011-08-01
75086 | G7LGMR | F6547 | Install backup gener Three Mile | 670.95 |  |  |  |  | 9572.21 |  |  | 2010-03-23 | 2012-03-30 | 2010-04-01 | 2011-10-12
75086 | G7MSCPRD | F6566 | Inst no-flow pump cutoffs Constance | 7763.18 |  |  |  |  | 12771 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2011-10-15
75086 | G7MSCPRD | F6567 | Inst flame detectors Constance Cav | 4311.09 |  |  |  |  | 7111.59 |  |  | 2010-03-24 | 2012-06-30 | 2010-06-01 | 2012-09-30
75086 | KYCIBS10 | F6569 | MOD 619 | 554.83 |  |  |  |  | 229130.48 |  |  | 2010-03-24 | 2010-12-31 | 2010-04-01 | 2010-10-19
75086 | KYCIBS10 | F6570 | MOD 620 | 16705.46 |  |  |  |  | 274212.17 |  |  | 2010-03-24 | 2010-12-31 | 2010-06-01 | 2011-01-01
75086 | G7MSCPRD | F6571 | Inst Odorizer and Flame Det Erlange | 25129.55 |  |  |  |  | 150785.01 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2012-01-15
75086 | KYCIBS10 | F7024 | MOD 618 | 9157.44 |  |  |  |  | 318181.48 |  |  | 2010-04-07 | 2010-12-31 | 2010-06-01 | 2010-11-26
75086 | G7LGMR | F7286 | Radio Master Erlanger Tower | 20570.51 |  |  |  |  | 73883.27 |  |  | 2010-04-16 | 2012-12-31 | 2010-05-01 | 2012-09-13
75086 | KYCIBS10 | F7664 | MOD 617 | 35440.43 |  |  |  |  | 287374.08 |  |  | 2010-04-26 | 2010-12-31 | 2010-06-01 | 2011-02-02
75086 | G7MAINS | F7725 | 420 Independence Station Rd | -2253.77 |  |  |  |  | 46841.42 |  |  | 2010-04-26 | 2011-12-31 | 2010-09-01 | 2011-02-16
75086 | G7LGMR | F9125 | STA 806 - Grand Ave | 93162.57 |  |  |  |  | 93162.57 |  |  | 2010-06-03 | 2012-09-15 | 2011-01-01 | 2012-01-28
75086 | G7LGMR | F9465 | Gas Control Router Upgrade KY | 2384.36 |  |  |  |  | 16729.78 |  |  | 2010-06-11 | 2011-03-31 | 2010-06-01 | 2011-03-31
75086 | KYCIBS10 | F9665 | MOD 628 | 19141.61 |  |  |  |  | 459664.53 |  |  | 2010-06-18 | 2010-12-31 | 2010-06-01 | 2010-12-29
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 4165.46 |  |  |  |  | 4608.15 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | G7LGMR | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 7535.21 |  |  |  |  | 130098.56 |  |  | 2010-07-15 | 2011-04-01 | 2010-08-01 | 2011-02-02
75086 | G7MAINS | G0506 | EMAX #701496 Independence Oaks | 10132.98 |  |  |  |  | 10132.98 |  |  | 2010-07-19 | 2012-06-30 | 2011-08-01 | 2012-01-05
75086 | INDUSTRD | G0543 | Industrial Road | 635839.49 |  |  |  |  | 635839.49 |  |  | 2010-07-22 | 2011-10-30 | 2011-02-01 | 2011-09-23
75086 | G7MAINS | G0582 | Reg 114K Inlet & Outlet | 402.08 |  |  |  |  | 13636.67 |  |  | 2010-07-27 | 2011-04-01 | 2010-08-01 | 2011-02-02
75086 | G7MAINS | G0606 | Sta 804 Inlet Piping | 36205.51 |  |  |  |  | 55240.68 |  |  | 2010-08-02 | 2012-06-30 | 2010-09-01 | 2011-06-24
75086 | G7MAINS | G0607 | Sta 804 Outlet Piping | 16666.97 |  |  |  |  | 31331.84 |  |  | 2010-08-02 | 2012-04-30 | 2010-09-01 | 2011-06-24
75086 | G7MAINS | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | -36.84 |  |  |  |  | 4229.33 |  |  | 2010-08-06 | 2012-02-29 | 2010-10-01 | 2011-02-13
75086 | G7PUBIMP | G0795 | Edgecliff Rd | 71.88 |  |  |  |  | 34647.09 |  |  | 2010-08-26 | 2011-08-01 | 2010-09-01 | 2011-04-11
75086 | G7PUBIMP | G0796 | Hay & Willow Sts | 283.78 |  |  |  |  | 27164.06 |  |  | 2010-08-26 | 2011-03-31 | 2010-09-01 | 2010-12-13
75086 | G7MAINS | G0802 | EMAX 919073 Villa Grande Sec 4 | 220.08 |  |  |  |  | 8648.16 |  |  | 2010-08-27 | 2011-12-31 | 2010-10-01 | 2012-02-14
75086 | G7REPL | G0860 | Tammy Lane | 74094.84 |  |  |  |  | 76315.93 |  |  | 2010-09-03 | 2011-10-15 | 2010-09-01 | 2011-06-19
75086 | G7PUBIMP | G0899 | Barnes Rd | 34539.27 |  |  |  |  | 34539.27 |  |  | 2010-09-07 | 2013-07-31 | 2011-11-01 | 2012-05-23
75086 | G7PUBIMP | G0965 | Johns Hill Rd | 49027.12 |  |  |  |  | 49027.12 |  |  | 2010-09-13 | 2013-04-01 | 2011-09-01 | 2012-09-13
75086 | G7MAINS | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 425.85 |  |  |  |  | 8452.75 |  |  | 2010-09-21 | 2011-05-31 | 2010-11-01 | 2011-03-11
75086 | G7MAINS | G1098 | Millakin Place | -647.51 |  |  |  |  | 66138.42 |  |  | 2010-09-27 | 2011-12-31 | 2010-10-01 | 2011-02-03
75086 | G7MAINS | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 8714.57 |  |  |  |  | 8714.57 |  |  | 2010-10-01 | 2012-03-31 | 2011-08-01 | 2011-12-10
75086 | G7MSCPRD | G1319 | Install MCCI at Erlanger GP | 105368.81 |  |  |  |  | 105368.81 |  |  | 2010-10-12 | 2012-06-30 | 2011-03-01 | 2011-12-01
75086 | G7MSCPRD | G1322 | Replace Air Dryer Erlanger | 802.67 |  |  |  |  | 25297.72 |  |  | 2010-10-13 | 2012-06-30 | 2010-12-01 | 2011-05-11
75086 | G7MAINS | G1354 | EMAX 1279677 French Quarter | 29679.61 |  |  |  |  | 29679.61 |  |  | 2010-10-20 | 2011-11-28 | 2011-01-01 | 2011-06-01
75086 | GITKYCAP | G1357 | Gas Image Project - KY | 36544.71 |  |  |  |  | 63414.83 |  |  | 2010-10-20 | 2011-10-29 | 2010-11-01 | 2011-07-12
75086 | G7REPL | G1427 | Comair Blvd | -950.93 |  |  |  |  | 34269.09 |  |  | 2010-10-29 | 2011-09-01 | 2010-11-01 | 2011-01-23
75086 | G7REPL | G1456 | UL27 Falmouth Bridge | 30549.36 |  |  |  |  | 178656.06 |  |  | 2010-11-04 | 2011-09-30 | 2010-11-01 | 2011-03-10
75086 | GMAINS | G1655 | EMAX 1585263 Harmony Subd Ph D | 8307.85 |  |  |  |  | 8307.85 |  |  | 2010-12-13 | 2011-12-30 | 2011-07-01 | 2011-11-06
75086 | G7PUBIMP | G1877 | Comair Blvd - DHL Expansion | 263918.41 |  |  |  |  | 263918.41 |  |  | 2011-01-14 | 2012-11-15 | 2011-02-01 | 2011-08-14
75086 | G7LGMR | G1920 | Sale of easement Dayton Valve House | 4 |  |  |  |  | 4 |  |  | 2011-01-19 | 2012-05-30 | 2011-02-01 | 2011-05-10
75086 | G7LGMR | G1978 | STA 810 - Taylor Mill South | 82667.95 |  |  |  |  | 82667.95 |  |  | 2011-01-26 | 2013-06-01 | 2011-02-01 | 2012-02-04
75086 | G7MAINS | G1998 | STA 810 Inlet Piping F/L UL16 | 17984.29 |  |  |  |  | 17984.29 |  |  | 2011-01-27 | 2013-06-01 | 2011-04-01 | 2012-02-04
75086 | G7MAINS | G1999 | STA 810 Outlet Piping F/L AM3 | 16829.23 |  |  |  |  | 16829.23 |  |  | 2011-01-27 | 2013-06-01 | 2011-04-01 | 2012-02-04
75086 | G7LGMR | G2041 | REG 55K Modifications Wright& Sprin | 59814.06 |  |  |  |  | 59814.06 |  |  | 2011-01-31 | 2012-04-01 | 2011-03-01 | 2011-12-26
75086 | G7REPL | G2173 | Saratogo St Main Replacement | 196102.34 |  |  |  |  | 196102.34 |  |  | 2011-02-08 | 2012-06-30 | 2011-04-01 | 2012-01-14
75086 | G7MAINS | G2305 | EMAX 1928423 Granite Springs 3B | 5874.52 |  |  |  |  | 5874.52 |  |  | 2011-02-15 | 2012-07-31 | 2011-09-01 | 2012-01-10
75086 | G7PUBIMP | G2527 | Silver Ave | 74741.4 |  |  |  |  | 74741.4 |  |  | 2011-03-03 | 2011-11-30 | 2011-03-01 | 2011-07-11
75086 | G7LGMR | G2537 | Rpl SCADA Radio Equip KY | 231987.05 |  |  |  |  | 231987.05 |  |  | 2011-03-04 | 2014-07-31 | 2011-03-01 | 2013-03-15
75086 | G7PUBIMP | G2573 | S Airfield Connector | 151286.17 |  |  |  |  | 151286.17 |  |  | 2011-03-08 | 2013-01-01 | 2011-04-01 | 2012-02-02
75086 | G7MAINS | G2632 | EMAX 2114122 Grant Park Subd | 6053.14 |  |  |  |  | 6053.14 |  |  | 2011-03-15 | 2011-12-31 | 2011-04-01 | 2011-10-23
75086 | TAYLRMIL | G2776 | Taylor Mill Rd F/L AM03 | 502660.24 |  |  |  |  | 502660.24 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | TAYLRMIL | G2777 | Taylor Mill Rd Distribution Line | 287811.97 |  |  |  |  | 287811.97 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | G7MAINS | G2934 | EMAX 2179169 Triple Crown Sec 24 | 7911.87 |  |  |  |  | 7911.87 |  |  | 2011-04-06 | 2011-12-31 | 2011-05-01 | 2012-03-21
75086 | G7REPL | G2962 | Moore St | 200.54 |  |  |  |  | 200.54 |  |  | 2011-04-08 | 2011-10-15 | 2011-11-01 | 2010-11-03
75086 | G7REPL | G3073 | Ky Copper Mod 629 | 277604.17 |  |  |  |  | 277604.17 |  |  | 2011-04-21 | 2012-06-30 | 2011-04-01 | 2012-04-30
75086 | G7MAINS | G3097 | EMAX 2225209 Harmony Sub Ph C | 8272.66 |  |  |  |  | 8272.66 |  |  | 2011-04-25 | 2012-06-30 | 2011-07-01 | 2011-11-17
75086 | G7LGMR | G3136 | 1340 KY HWY 177E | 5717 |  |  |  |  | 5717 |  |  | 2011-04-27 | 2012-06-30 | 2011-06-01 | 2011-11-30
75086 | G7MAINS | G3139 | EMAX 2197891 Sherbourne Ph F | 13766.35 |  |  |  |  | 13766.35 |  |  | 2011-04-27 | 2011-12-31 | 2011-06-01 | 2012-02-29
75086 | GITKYCAP | G3257 | GAMRS (GSMD and Metretek Backoff KY | 154996.96 |  |  |  |  | 154996.96 |  |  | 2011-05-04 | 2013-01-29 | 2011-05-01 | 2012-08-14
75086 | G7PUBIMP | G3515 | Orland Drive | 53197.7 |  |  |  |  | 53197.7 |  |  | 2011-05-31 | 2012-10-30 | 2011-06-01 | 2011-09-28
75086 | G7MAINS | G3537 | EMAX 2317816 Claiborne Ph 5 D | 72.98 |  |  |  |  | 72.98 |  |  | 2011-06-01 | 2013-03-31 | 2011-06-01 | 2012-08-09
75086 | G7MAINS | G3557 | EMAX 2321346 Weideman Hill | 1795.05 |  |  |  |  | 1795.05 |  |  | 2011-06-02 | 2012-03-31 | 2011-08-01 | 2011-12-17
75086 | G7MAINS | G3688 | STA 806 Outlet Piping | 94092.89 |  |  |  |  | 94092.89 |  |  | 2011-06-15 | 2012-06-30 | 2011-07-01 | 2012-01-28
75086 | G7MAINS | G3690 | STA 806 Inlet Piping | 37632.09 |  |  |  |  | 37632.09 |  |  | 2011-06-15 | 2012-03-31 | 2011-07-01 | 2012-01-28
75086 | GITKYCAP | G3715 | Gas Area Load Forecast Sys KY | 52494.45 |  |  |  |  | 52494.45 |  |  | 2011-06-17 | 2012-11-09 | 2011-07-01 | 2012-09-15
75086 | TAYLRMIL | G3774 | Sipple Dr | 1150.99 |  |  |  |  | 1150.99 |  |  | 2011-06-23 | 2013-05-15 | 2011-07-01 | 2013-01-03
75086 | G7LGMR | G3775 | Lafarge Install Cover-Meas STA 704 | 801.94 |  |  |  |  | 801.94 |  |  | 2011-06-23 | 2012-06-30 | 2011-08-01 | 2011-12-20
75086 | G7LGMR | G3790 | Rpl Transmitters KY | 12803.41 |  |  |  |  | 12803.41 |  |  | 2011-06-24 | 2014-06-30 | 2011-11-01 | 2014-12-01
75086 | G7LGMR | G3792 | Rpl CDMA Radios for Telemeters KY | 326.6 |  |  |  |  | 326.6 |  |  | 2011-06-24 | 2013-06-30 | 2011-11-01 | 2013-02-28
75086 | G7MAINS | G3854 | EMAX 2394542 Johanna Ln | 5115.72 |  |  |  |  | 5115.72 |  |  | 2011-06-29 | 2011-12-31 | 2011-08-01 | 2011-11-26
75086 | G7LGMR | G3997 | Reg 110K - Woodfill Ave @ US 27 | 25792.85 |  |  |  |  | 25792.85 |  |  | 2011-07-08 | 2013-02-10 | 2011-09-01 | 2012-11-17
75086 | G7MAINS | G3999 | 7 & 9 Apple Ln inst hp main | 970.44 |  |  |  |  | 970.44 |  |  | 2011-07-11 | 2011-12-31 | 2011-07-01 | 2011-10-07
75086 | G7MAINS | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 202879.17 |  |  |  |  | 202879.17 |  |  | 2011-07-12 | 2012-06-30 | 2011-07-01 | 2011-11-30
75086 | G7MSCPRD | G4116 | LP-03 Erlanger KY | 102502.46 |  |  |  |  | 102502.46 |  |  | 2011-07-21 | 2012-08-01 | 2011-08-01 | 2011-12-13
75086 | G7MAINS | G4145 | EMAX 2455730 Saylor Estates | 5671.87 |  |  |  |  | 5671.87 |  |  | 2011-07-22 | 2012-04-30 | 2011-09-01 | 2012-01-22
75086 | G7MSCPRD | G4181 | Replace F/L LP-03 under I-75 | 258727.42 |  |  |  |  | 258727.42 |  |  | 2011-07-27 | 2012-08-01 | 2011-08-01 | 2012-02-11
75086 | G7LGMR | G4281 | Ky Hwy 177 East | 4574.82 |  |  |  |  | 4574.82 |  |  | 2011-08-03 | 2012-06-20 | 2011-08-01 | 2012-01-21
75086 | G7SERVNEW | G4282 | Ky Hwy 177 East 3 in steel M-C | 57068.44 |  |  |  |  | 57068.44 |  |  | 2011-08-03 | 2012-06-20 | 2011-08-01 | 2011-11-30
75086 | G7SERVNEW | G4283 | 1340 Ky Hwy 177 E 3 in steel M-C | 37056.58 |  |  |  |  | 37056.58 |  |  | 2011-08-03 | 2012-06-30 | 2011-08-01 | 2011-11-30
75086 | G7LGMR | G4494 | Replace generator at Foster Sta | 2953.45 |  |  |  |  | 2953.45 |  |  | 2011-08-16 | 2012-02-12 | 2011-08-01 | 2011-11-10
75086 | G7REPL | G4517 | F/L 'UL07' McCullum Rd Slide | 58330.52 |  |  |  |  | 58330.52 |  |  | 2011-08-17 | 2012-06-01 | 2011-09-01 | 2012-03-17
75086 | G7BUPG | G4602 | Install Auto Gate -Erlanger Gas Pl | 27336.02 |  |  |  |  | 27336.02 |  |  | 2011-08-23 | 2013-05-15 | 2011-11-01 | 2012-12-27
75086 | G7REPL | G4641 | KY Copper MOD 640 | 12230.41 |  |  |  |  | 12230.41 |  |  | 2011-08-26 | 2013-06-30 | 2011-12-01 | 2012-06-27
75086 | PROPCONKY | G4714 | Marilyn Drive PROPCONKY | 39712.91 |  |  |  |  | 39712.91 |  |  | 2011-08-31 | 2012-04-15 | 2011-10-01 | 2012-01-18
75086 | G7PRESIM | G4955 | Carothers Rd Pres Imp | 1588.15 |  |  |  |  | 1588.15 |  |  | 2011-09-14 | 2013-06-30 | 2011-12-01 | 2012-11-22
75086 | G7MSCPRD | G5034 | LP-03 Launcher/Receiver | 28341.08 |  |  |  |  | 28341.08 |  |  | 2011-09-21 | 2013-02-28 | 2011-10-01 | 2012-11-30
75086 | G7MSCPRD | G5035 | Replace arrestors Erlanger Gas Pl | 2948 |  |  |  |  | 2948 |  |  | 2011-09-21 | 2012-06-30 | 2011-09-01 | 2012-03-03
75086 | G7REPL | G5376 | Belmont Rd | 8050.74 |  |  |  |  | 8050.74 |  |  | 2011-10-18 | 2012-05-28 | 2011-10-01 | 2012-02-14
75086 | G7PUINMR | G5920 | Meters - Replacement | 2349.12 |  |  |  |  | 2349.12 |  |  | 2011-11-22 | 2013-06-30 | 2011-12-01
75086 | FGISEAMGK | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 179.26 |  |  |  |  | 16469.82 |  |  | 2009-10-21 | 2011-03-30 | 2009-11-01 | 2011-05-01
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 467812.08 |  |  |  |  | 467812.08 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 48206.86 |  |  |  |  | 48206.86 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCNP70 | New M-C Plastic 2 inch and Under Se | 493.5 |  |  |  |  | 1202600.06 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1117953.82 |  |  |  |  | 2838246.15 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 10794.41 |  |  |  |  | 50323.36 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FRCSW | RCSWHWC | Cust Call Ctr Switch Repl | 89165.95 |  |  |  |  | 89165.95 |  |  | 2011-07-22 | 2011-12-31 | 2011-08-01 | 2012-03-31
75087 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | 166937.2 |  |  |  |  | 166937.2 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75087 | FRCSW | RCSWTELC | Cust Call Ctr Switch Repl | 7780 |  |  |  |  | 7780 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75086 | SGITOMSGI | SGARCSRVC | Smart Grid ARC Server Project | -483.21 |  |  |  |  | -10717.85 |  |  | 2010-09-24 | 2011-01-31 | 2010-10-01 | 2011-03-08
75086 | SGITMTRSY | SGBRWTRH | Bridgewater AAA Implement HW | 1308.6 |  |  |  |  | 1308.6 |  |  | 2011-12-08 | 2009-02-19 | 2011-12-01 | 2009-05-19
75086 | SGITMTRSY | SGBRWTRS | Bridgewater AAA Implement SW | 3088.72 |  |  |  |  | 3088.72 |  |  | 2011-12-02 | 2009-02-19 | 2011-12-01 | 2009-05-19
75086 | SGKYCS | SGCSDCI3 | ECS daily usage cap | -1618.73 |  |  |  |  | 10403.79 |  |  | 2010-10-01 | 2014-12-31 | 2010-09-01 | 2010-06-24
75086 | SGKYCS | SGCSECS | Enterprise Cust systems cap | 69710.35 |  |  |  |  | 1.4552e-11 |  |  | 2010-10-01 | 2014-12-31 | 2010-09-01
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 11268.56 |  |  |  |  | 11268.56 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 81677.62 |  |  |  |  | 81677.62 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGITRNSLH | ITRON SG Solutions Hardware | 119.75 |  |  |  |  | 119.75 |  |  | 2011-07-14 | 2012-06-30 | 2011-10-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMS | Meter Data Management System | 177786 |  |  |  |  | 177786 |  |  | 2011-11-30 | 2010-06-18 | 2011-11-01 | 2010-09-18
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -34.41 |  |  |  |  | 41.57 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | SGKYMTRSY | SGSTRGC | Smart Grid Storage Project | -23441.65 |  |  |  |  | 126664.77 |  |  | 2010-06-16 | 2010-11-30 | 2010-09-01 | 2011-02-17
75086 | SGKYMTRSY | SGSYED11 | EDM.11 SG Scaling/Tech Hlth | 18237 |  |  |  |  | 118809.45 |  |  | 2010-09-30 | 2010-03-04 | 2010-09-01 | 2010-06-04
75086 | SGITMTRSY | SGSYED15 | SG EDM.15 EDMS Scalability-Hardware | 28042.21 |  |  |  |  | 44254.07 |  |  | 2010-09-14 | 2010-09-30 | 2010-09-01 | 2011-02-24
75086 | SGITMTRSY | SGSYEDP2 | SG Scalability Phase 2 EDM064 | 49323.63 |  |  |  |  | 30281.15 |  |  | 2010-08-13 | 2012-01-15 | 2010-09-01 | 2011-08-13
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2012
Duke Energy Kentucky Gas
Year 2012
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | -15463.08 |  |  |  |  | 49130.89 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 2375.77 |  |  |  |  | 31468.66 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3CMR70 | Replace C-M 3" Kentucky Blanket | 53.2 |  |  |  |  | 4718.41 |  |  | 2008-07-31 | 2050-12-31 | 2009-04-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 2995.45 |  |  |  |  | 24494.19 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 243.9 |  |  |  |  | 10470.81 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 9528.22 |  |  |  |  | 24209.91 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4CMR70 | Replace C-M 4" Kentucky Blanket | -464.21 |  |  |  |  | 7175.81 |  |  | 2008-07-31 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 25328.84 |  |  |  |  | 40137.34 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 174.65 |  |  |  |  | 2273.23 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 988.51 |  |  |  |  | 16404.11 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 2794.72 |  |  |  |  | 5538.27 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 6MCR70 | Replace M-C 6" - Kentucky | 140.98 |  |  |  |  | 140.98 |  |  | 2008-07-01 | 2050-12-31 | 2012-07-01
75086 | G7SERVNEW | 8CMNEW70 | Install New C-M 8" | 5832.28 |  |  |  |  | 5832.28 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVNEW | 8MCNEW70 | Install New M-C 8" | 890.15 |  |  |  |  | 890.15 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 534216.21 |  |  |  |  | 923567.17 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 1501811.63 |  |  |  |  | 4429159.09 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | KYCIBS09 | E0194 | MOD 601 | 1947.01 |  |  |  |  | 2224266.48 |  |  | 2008-07-23 | 2013-07-30 | 2008-07-01 | 2009-09-22
75086 | G7LGMR | E4656 | Abandon System STA 58 | 0.01 |  |  |  |  | 1240 |  |  | 2009-03-03 | 2011-04-30 | 2010-03-01 | 2009-11-24
75086 | KYCIBS10 | E6367 | MOD 377 | 2236.5 |  |  |  |  | 733446.35 |  |  | 2009-05-15 | 2014-05-14 | 2009-05-01 | 2010-07-15
75086 | G7MAINS | E7331 | STA 535 Inlet Valve | 181.6 |  |  |  |  | 41811.51 |  |  | 2009-06-24 | 2014-06-23 | 2009-07-01 | 2009-12-17
75087 | FEBPE1A | EBPE1 | Electronic Billing & Payment Ex Ph1 | 118.38 |  |  |  |  | 51644.99 |  |  | 2011-05-20 | 2011-12-31 | 2011-06-01 | 2012-03-31
75087 | FEBPE1A | EBPE2 | EBPE Phase 2 | 33007.95 |  |  |  |  | 33007.95 |  |  | 2012-02-20 | 2012-12-31 | 2012-02-01 | 2012-12-17
75087 | SGITCS | ECSDCI2 | Enterprise Cust system DCI2 Capital | 38478.54 |  |  |  |  | 3516.61 |  |  | 2011-04-13 | 2015-03-31 | 2011-04-01 | 2011-11-30
75086 | CPERNST1 | F0904 | KY 237 Imp Pleasant Valley | 217746.19 |  |  |  |  | 559825.26 |  |  | 2009-10-05 | 2013-02-28 | 2010-10-01 | 2012-11-01
75086 | G7LGMR | F6547 | Install backup gener Three Mile | -333.63 |  |  |  |  | 9238.58 |  |  | 2010-03-23 | 2012-03-30 | 2010-04-01 | 2011-10-12
75086 | G7MSCPRD | F6566 | Inst no-flow pump cutoffs Constance | 2556.52 |  |  |  |  | 15327.52 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2011-10-15
75086 | G7MSCPRD | F6571 | Inst Odorizer and Flame Det Erlange | 6873.54 |  |  |  |  | 157658.55 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2012-01-15
75086 | GITKYCAP | F7146 | Itron FCS Kentucky Gas | 421.64 |  |  |  |  | 421.64 |  |  | 2010-04-12 | 2013-05-15 | 2012-01-01 | 2012-02-07
75086 | G7LGMR | F7286 | Radio Master Erlanger Tower | 3249.25 |  |  |  |  | 77132.52 |  |  | 2010-04-16 | 2012-12-31 | 2010-05-01 | 2012-09-13
75086 | G7LGMR | F9125 | STA 806 - Grand Ave | 4339.7 |  |  |  |  | 97502.27 |  |  | 2010-06-03 | 2012-09-15 | 2011-01-01 | 2012-01-28
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 143.72 |  |  |  |  | 4751.87 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | INDUSTRD | G0543 | Industrial Road | 127374.11 |  |  |  |  | 763213.6 |  |  | 2010-07-22 | 2011-10-30 | 2011-02-01 | 2011-09-23
75086 | G7MAINS | G0606 | Sta 804 Inlet Piping | -2638.82 |  |  |  |  | 52601.86 |  |  | 2010-08-02 | 2012-06-30 | 2010-09-01 | 2011-06-24
75086 | G7MAINS | G0607 | Sta 804 Outlet Piping | -1390.04 |  |  |  |  | 29941.8 |  |  | 2010-08-02 | 2012-04-30 | 2010-09-01 | 2011-06-24
75086 | G7PUBIMP | G0795 | Edgecliff Rd | 473.28 |  |  |  |  | 35120.37 |  |  | 2010-08-26 | 2011-08-01 | 2010-09-01 | 2011-04-11
75086 | G7MSCPRD | G0823 | Pneumatic guages Erlanger GP | 4946.53 |  |  |  |  | 4946.53 |  |  | 2010-08-30 | 2012-06-30 | 2012-03-01 | 2011-03-31
75086 | G7PUBIMP | G0899 | Barnes Rd | 82470.81 |  |  |  |  | 117010.08 |  |  | 2010-09-07 | 2013-07-31 | 2011-11-01 | 2012-05-23
75086 | G7PUBIMP | G0965 | Johns Hill Rd | 153649.19 |  |  |  |  | 202676.31 |  |  | 2010-09-13 | 2013-04-01 | 2011-09-01 | 2012-09-13
75086 | G7MAINS | G1178 | 1115901 J GROESCHEN Gunpowder Trail | -398.98 |  |  |  |  | 8315.59 |  |  | 2010-10-01 | 2012-03-31 | 2011-08-01 | 2011-12-10
75086 | G7MSCPRD | G1319 | Install MCCI at Erlanger GP | -2154.16 |  |  |  |  | 103214.65 |  |  | 2010-10-12 | 2012-06-30 | 2011-03-01 | 2011-12-01
75086 | G7MSCPRD | G1322 | Replace Air Dryer Erlanger | -587.83 |  |  |  |  | 24709.89 |  |  | 2010-10-13 | 2012-06-30 | 2010-12-01 | 2011-05-11
75086 | G7PUBIMP | G1874 | Pleasant Ridge Ave | 86530.33 |  |  |  |  | 86530.33 |  |  | 2011-01-14 | 2011-11-01 | 2012-03-01 | 2012-07-24
75086 | G7PUBIMP | G1877 | Comair Blvd - DHL Expansion | -12150.11 |  |  |  |  | 251768.3 |  |  | 2011-01-14 | 2012-11-15 | 2011-02-01 | 2011-08-14
75086 | G7LGMR | G1920 | Sale of easement Dayton Valve House | -4 |  |  |  |  | 0 |  |  | 2011-01-19 | 2012-05-30 | 2011-02-01 | 2011-05-10
75086 | G7LGMR | G1978 | STA 810 - Taylor Mill South | 92128.12 |  |  |  |  | 174796.07 |  |  | 2011-01-26 | 2013-06-01 | 2011-02-01 | 2012-02-04
75086 | G7MAINS | G1998 | STA 810 Inlet Piping F/L UL16 | 3193.78 |  |  |  |  | 21178.07 |  |  | 2011-01-27 | 2013-06-01 | 2011-04-01 | 2012-02-04
75086 | G7MAINS | G1999 | STA 810 Outlet Piping F/L AM3 | -114.84 |  |  |  |  | 16714.39 |  |  | 2011-01-27 | 2013-06-01 | 2011-04-01 | 2012-02-04
75086 | G7LGMR | G2041 | REG 55K Modifications Wright& Sprin | 95.73 |  |  |  |  | 59909.79 |  |  | 2011-01-31 | 2012-04-01 | 2011-03-01 | 2011-12-26
75086 | G7REPL | G2173 | Saratogo St Main Replacement | 3873.17 |  |  |  |  | 199975.51 |  |  | 2011-02-08 | 2012-06-30 | 2011-04-01 | 2012-01-14
75086 | G7PUBIMP | G2527 | Silver Ave | 30909.44 |  |  |  |  | 105650.84 |  |  | 2011-03-03 | 2011-11-30 | 2011-03-01 | 2011-07-11
75086 | G7LGMR | G2537 | Rpl SCADA Radio Equip KY | 48458.83 |  |  |  |  | 280445.88 |  |  | 2011-03-04 | 2014-07-31 | 2011-03-01 | 2013-03-15
75086 | G7PUBIMP | G2573 | S Airfield Connector | -1737.83 |  |  |  |  | 149548.34 |  |  | 2011-03-08 | 2013-01-01 | 2011-04-01 | 2012-02-02
75086 | TAYLRMIL | G2776 | Taylor Mill Rd F/L AM03 | 555049.11 |  |  |  |  | 1057709.35 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | TAYLRMIL | G2777 | Taylor Mill Rd Distribution Line | 379653.76 |  |  |  |  | 667465.73 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | G7MAINS | G2934 | EMAX 2179169 Triple Crown Sec 24 | 13686.09 |  |  |  |  | 21597.96 |  |  | 2011-04-06 | 2011-12-31 | 2011-05-01 | 2012-03-21
75086 | G7REPL | G3073 | Ky Copper Mod 629 | 80595.56 |  |  |  |  | 358199.73 |  |  | 2011-04-21 | 2012-06-30 | 2011-04-01 | 2012-04-30
75086 | TAYLRMIL | G3074 | Taylor Mill Rd/I-275 to Taylor Cr | 18302.11 |  |  |  |  | 18302.11 |  |  | 2011-04-21 | 2014-01-31 | 2012-11-01 | 2013-07-17
75086 | GITKYCAP | G3257 | GAMRS (GSMD and Metretek Backoff KY | 80403.06 |  |  |  |  | 235400.02 |  |  | 2011-05-04 | 2013-01-29 | 2011-05-01 | 2012-08-14
75086 | G7PUBIMP | G3515 | Orland Drive | -495.55 |  |  |  |  | 52702.15 |  |  | 2011-05-31 | 2012-10-30 | 2011-06-01 | 2011-09-28
75086 | G7MAINS | G3537 | EMAX 2317816 Claiborne Ph 5 D | 6075.67 |  |  |  |  | 6148.65 |  |  | 2011-06-01 | 2013-03-31 | 2011-06-01 | 2012-08-09
75086 | G7MAINS | G3688 | STA 806 Outlet Piping | -14053.14 |  |  |  |  | 80039.75 |  |  | 2011-06-15 | 2012-06-30 | 2011-07-01 | 2012-01-28
75086 | GITKYCAP | G3715 | Gas Area Load Forecast Sys KY | 51752.76 |  |  |  |  | 104247.21 |  |  | 2011-06-17 | 2012-11-09 | 2011-07-01 | 2012-09-15
75086 | TAYLRMIL | G3774 | Sipple Dr | 48213.98 |  |  |  |  | 49364.97 |  |  | 2011-06-23 | 2013-05-15 | 2011-07-01 | 2013-01-03
75086 | G7LGMR | G3775 | Lafarge Install Cover-Meas STA 704 | -16.48 |  |  |  |  | 785.46 |  |  | 2011-06-23 | 2012-06-30 | 2011-08-01 | 2011-12-20
75086 | G7LGMR | G3790 | Rpl Transmitters KY | 399.3 |  |  |  |  | 13202.71 |  |  | 2011-06-24 | 2014-06-30 | 2011-11-01 | 2014-12-01
75086 | G7LGMR | G3792 | Rpl CDMA Radios for Telemeters KY | 23721.93 |  |  |  |  | 24048.53 |  |  | 2011-06-24 | 2013-06-30 | 2011-11-01 | 2013-02-28
75086 | G7LGMR | G3997 | Reg 110K - Woodfill Ave @ US 27 | 143945.14 |  |  |  |  | 169737.99 |  |  | 2011-07-08 | 2013-02-10 | 2011-09-01 | 2012-11-17
75086 | G7MAINS | G3999 | 7 & 9 Apple Ln inst hp main | -28.2 |  |  |  |  | 942.24 |  |  | 2011-07-11 | 2011-12-31 | 2011-07-01 | 2011-10-07
75086 | G7MAINS | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | -1923.86 |  |  |  |  | 200955.31 |  |  | 2011-07-12 | 2012-06-30 | 2011-07-01 | 2011-11-30
75086 | G7MSCPRD | G4116 | LP-03 Erlanger KY | -1955.21 |  |  |  |  | 100547.25 |  |  | 2011-07-21 | 2012-08-01 | 2011-08-01 | 2011-12-13
75086 | G7MSCPRD | G4181 | Replace F/L LP-03 under I-75 | -754.05 |  |  |  |  | 257973.37 |  |  | 2011-07-27 | 2012-08-01 | 2011-08-01 | 2012-02-11
75086 | G7SERVNEW | G4282 | Ky Hwy 177 East 3 in steel M-C | -1564.08 |  |  |  |  | 55504.36 |  |  | 2011-08-03 | 2012-06-20 | 2011-08-01 | 2011-11-30
75086 | G7SERVNEW | G4283 | 1340 Ky Hwy 177 E 3 in steel M-C | -326.78 |  |  |  |  | 36729.8 |  |  | 2011-08-03 | 2012-06-30 | 2011-08-01 | 2011-11-30
75086 | G7PUBIMP | G4496 | KY 22 Bridge | 205029.35 |  |  |  |  | 205029.35 |  |  | 2011-08-16 | 2013-03-30 | 2012-03-01 | 2013-01-11
75086 | G7REPL | G4517 | F/L 'UL07' McCullum Rd Slide | 39161.54 |  |  |  |  | 97492.06 |  |  | 2011-08-17 | 2012-06-01 | 2011-09-01 | 2012-03-17
75086 | G7BUPG | G4602 | Install Auto Gate -Erlanger Gas Pl | 73046.54 |  |  |  |  | 100382.56 |  |  | 2011-08-23 | 2013-05-15 | 2011-11-01 | 2012-12-27
75086 | G7REPL | G4641 | KY Copper MOD 640 | 145083.47 |  |  |  |  | 157313.88 |  |  | 2011-08-26 | 2013-06-30 | 2011-12-01 | 2012-06-27
75086 | G7PRESIM | G4955 | Carothers Rd Pres Imp | 44747.44 |  |  |  |  | 46335.59 |  |  | 2011-09-14 | 2013-06-30 | 2011-12-01 | 2012-11-22
75086 | G7PUBIMP | G4998 | Summit Dr | 73756.29 |  |  |  |  | 73756.29 |  |  | 2011-09-16 | 2012-08-28 | 2012-01-01 | 2012-07-01
75086 | G7MSCPRD | G5034 | LP-03 Launcher/Receiver | 68696.48 |  |  |  |  | 97037.56 |  |  | 2011-09-21 | 2013-02-28 | 2011-10-01 | 2012-11-30
75086 | G7MAINS | G5073 | EMAX 2609059 Province Pointe Subd | 594.17 |  |  |  |  | 594.17 |  |  | 2011-09-25 | 2013-06-30 | 2012-12-01 | 2013-04-15
75086 | G7MAINS | G5113 | REG 110K Inlet & Outlet Piping | 89602.34 |  |  |  |  | 89602.34 |  |  | 2011-09-28 | 2013-02-10 | 2012-06-01 | 2012-11-17
75086 | G7MAINS | G5254 | 1305 Monmouth St Newport Ky | 59894.13 |  |  |  |  | 59894.13 |  |  | 2011-10-06 | 2012-04-30 | 2012-02-01 | 2012-06-19
75086 | G7PUINMR | G5920 | Meters - Replacement | 137700.64 |  |  |  |  | 140049.76 |  |  | 2011-11-22 | 2013-06-30 | 2011-12-01
75086 | G7PRESIM | G6396 | Turkeyfoot Rd @ Autumn | 231341.75 |  |  |  |  | 231341.75 |  |  | 2012-01-04 | 2013-01-03 | 2012-04-01 | 2012-09-29
75086 | G7PUBIMP | G6413 | Mall Rd Kroger Marketplace | -31326.16 |  |  |  |  | -31326.16 |  |  | 2012-01-06 | 2014-02-28 | 2012-01-01 | 2013-09-15
75086 | G7MAINS | G6542 | EMAX 2911813 Triple Crown Ctry Club | 8902.47 |  |  |  |  | 8902.47 |  |  | 2012-01-23 | 2013-03-31 | 2012-10-01 | 2013-02-01
75086 | G7LGMR | G6589 | Easement Dayton Valve house | 152.55 |  |  |  |  | 152.55 |  |  | 2012-01-27 | 2012-02-29 | 2012-01-01 | 2012-10-31
75086 | G7MAINS | G6918 | Burnet Ridge | 83552.09 |  |  |  |  | 83552.09 |  |  | 2012-02-28 | 2013-05-30 | 2012-06-01 | 2012-12-06
75086 | G7MAINS | G6964 | Wendell Ford Blvd | 62320.24 |  |  |  |  | 62320.24 |  |  | 2012-03-06 | 2013-02-28 | 2012-04-01 | 2012-08-14
75086 | G7MAINS | G6968 | EMAX 3021646 Triple Crown Country | 31635.17 |  |  |  |  | 31635.17 |  |  | 2012-03-07 | 2013-09-30 | 2012-09-01 | 2013-02-01
75086 | G7LGMR | G6976 | Concrete Stairwell Rpl | 12665.32 |  |  |  |  | 12665.32 |  |  | 2012-03-07 | 2013-03-10 | 2012-07-01 | 2012-11-01
75086 | G7MSCPRD | G7058 | F/L LP-03 Under I-275 | 140534.02 |  |  |  |  | 140534.02 |  |  | 2012-03-21 | 2013-02-21 | 2012-07-01 | 2012-12-20
75086 | G7MSCPRD | G7059 | Constance Cavern Recondition | 73458.57 |  |  |  |  | 73458.57 |  |  | 2012-03-21 | 2013-02-21 | 2012-07-01 | 2013-01-08
75086 | G7MAINS | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 8659.71 |  |  |  |  | 8659.71 |  |  | 2012-03-28 | 2013-03-31 | 2012-06-01 | 2012-09-28
75086 | G7MSCPRD | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 108521.98 |  |  |  |  | 108521.98 |  |  | 2012-04-17 | 2013-08-15 | 2012-07-01 | 2013-06-01
75086 | G7MAINS | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 6555.25 |  |  |  |  | 6555.25 |  |  | 2012-05-03 | 2013-04-30 | 2012-08-01 | 2012-11-22
75086 | G7MAINS | G7425 | JT emax 3155555 Olde Ft Mitchell | 4216.67 |  |  |  |  | 4216.67 |  |  | 2012-05-07 | 2013-05-31 | 2012-10-01 | 2013-02-19
75086 | G7MAINS | G7596 | Harold Mason Lane | 45451.96 |  |  |  |  | 45451.96 |  |  | 2012-05-21 | 2013-01-20 | 2012-06-01 | 2012-11-04
75086 | CPERNST2 | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 10358.7 |  |  |  |  | 10358.7 |  |  | 2012-05-22 | 2015-01-15 | 2012-12-01 | 2014-07-01
75086 | CASINGKY | G7638 | Casing AM07 Dixie Hwy | 609561.22 |  |  |  |  | 609561.22 |  |  | 2012-05-24 | 2013-04-22 | 2012-06-01 | 2013-01-16
75086 | G7MAINS | G7648 | emax 3195744 Harmony Sub Ph D | 5191.04 |  |  |  |  | 5191.04 |  |  | 2012-05-24 | 2013-02-28 | 2012-10-01 | 2013-01-05
75086 | PROPCONKY | G7687 | Vine Street Wilder | 118737.68 |  |  |  |  | 118737.68 |  |  | 2012-05-29 | 2013-04-30 | 2012-08-01 | 2012-12-29
75086 | CASINGKY | G7750 | Casing Crescent Springs LP03 | 80475.19 |  |  |  |  | 80475.19 |  |  | 2012-06-05 | 2013-06-30 | 2012-07-01 | 2012-11-03
75086 | CASINGKY | G7751 | Casing BS #48 AM07 | 675223.43 |  |  |  |  | 675223.43 |  |  | 2012-06-05 | 2013-06-30 | 2012-06-01 | 2012-12-12
75086 | CASINGKY | G7752 | Casing #87 BS Turkeyfoot AM07 | 642742.21 |  |  |  |  | 642742.21 |  |  | 2012-06-05 | 2013-06-30 | 2012-08-01 | 2013-01-01
75086 | G7REPL | G7849 | Reg 109K - Inlet & Outlet Piping | 69181.07 |  |  |  |  | 69181.07 |  |  | 2012-06-12 | 2013-06-30 | 2012-08-01 | 2012-12-15
75086 | G7LGMR | G7850 | Reg 109K - Main St @ Dixie Hwy | 103046.78 |  |  |  |  | 103046.78 |  |  | 2012-06-12 | 2013-06-30 | 2012-08-01 | 2012-12-15
75086 | G7LGMR | G7851 | 4th & Saratogo (Rpl Reg 18K) | 135636.62 |  |  |  |  | 135636.62 |  |  | 2012-06-12 | 2013-07-31 | 2012-09-01 | 2013-03-05
75086 | G7MAINS | G7950 | JT emax 3259578 Madison Heights | 20281.47 |  |  |  |  | 20281.47 |  |  | 2012-06-25 | 2013-03-31 | 2012-09-01 | 2013-01-06
75086 | G7MAINS | G7959 | JT emax 3268308 Triple Crown Sec 27 | 7952.22 |  |  |  |  | 7952.22 |  |  | 2012-06-26 | 2013-07-31 | 2012-09-01 | 2013-02-05
75086 | G7MAINS | G7982 | JT emax 3275676 Rainbow Terrace | 6029.56 |  |  |  |  | 6029.56 |  |  | 2012-06-29 | 2013-03-31 | 2012-09-01 | 2013-01-16
75086 | G7REPL | G8159 | Reg 115K - Inlet & Outlet Piping | 19478.13 |  |  |  |  | 19478.13 |  |  | 2012-07-30 | 2013-06-30 | 2012-09-01 | 2013-03-05
75086 | GITKYCAP | G8162 | EMAX CHANGE/INSIDE PIPING-KY | 26007.59 |  |  |  |  | 26007.59 |  |  | 2012-07-30 | 2013-05-15 | 2012-08-01 | 2013-02-12
75086 | G7MAINS | G8210 | JT emax 3371929 Triple Crown Sec 24 | 8387.92 |  |  |  |  | 8387.92 |  |  | 2012-08-10 | 2013-06-30 | 2012-10-01 | 2013-02-01
75086 | G7LGMR | G8248 | REG 116K - Holman and Watkins | 14363.17 |  |  |  |  | 14363.17 |  |  | 2012-08-16 | 2013-12-01 | 2012-10-01 | 2013-05-21
75086 | G7REPL | G8249 | REG 116K Inlet & Outlet Lines | 3333.42 |  |  |  |  | 3333.42 |  |  | 2012-08-16 | 2013-12-01 | 2012-10-01 | 2013-05-21
75086 | G7MAINS | G8345 | JT emax 3409638 Cool Springs Ph 4B | 5746.34 |  |  |  |  | 5746.34 |  |  | 2012-08-28 | 2013-10-30 | 2012-11-01 | 2013-03-01
75086 | G7MAINS | G8400 | JT emax 3437972 Thornwilde Ph O | 5445.39 |  |  |  |  | 5445.39 |  |  | 2012-09-06 | 2013-06-30 | 2012-11-01 | 2013-03-12
75086 | G7MAINS | G8498 | STA 792 Outlet | 1033.51 |  |  |  |  | 1033.51 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7MAINS | G8499 | STA 792 Inlet | 3749.98 |  |  |  |  | 3749.98 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7LGMR | G8500 | STA 792 - Arcadia Dr | 12508.79 |  |  |  |  | 12508.79 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7REPL | G8688 | Exposed Main Old Union Rd & US 42 | 4570.28 |  |  |  |  | 4570.28 |  |  | 2012-10-17 | 2013-02-09 | 2012-11-01 | 2012-11-09
75086 | G7MAINS | G8766 | GM 100 Richwood Rd | 1891.65 |  |  |  |  | 1891.65 |  |  | 2012-10-31 | 2013-12-31 | 2012-12-01 | 2013-04-08
75086 | G7REPL | G9007 | Miller St. Newport | 2714.17 |  |  |  |  | 2714.17 |  |  | 2012-11-29 | 2013-07-02 | 2012-12-01 | 2013-04-14
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 697786.88 |  |  |  |  | 1165598.96 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 14107.91 |  |  |  |  | 62314.77 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1547358.34 |  |  |  |  | 4385604.49 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 35851.74 |  |  |  |  | 86175.1 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | MFEOLREPL | Mainframe EOL Repl | 36193.85 |  |  |  |  | 36193.85 |  |  | 2012-05-31 | 2012-09-30 | 2012-06-01 | 2012-12-19
75088 | OM75088 | OMGPCVNTN | MGP Reserve - Covington | 225 |  |  |  |  | 225 |  |  | 2009-11-04 | 2051-03-31 | 2012-08-01
75088 | OM75088 | OMGPNWPRT | MGP Reserve - Newport | 270 |  |  |  |  | 270 |  |  | 2009-11-04 | 2051-03-31 | 2012-08-01
75087 | FPIT | RCIVRMKG | IVR Monitoring System | 2219.09 |  |  |  |  | 2219.09 |  |  | 2012-06-13 | 2012-12-31 | 2012-09-01 | 2013-03-31
75087 | FRCSW | RCSWHWC | Cust Call Ctr Switch Repl | -1699.65 |  |  |  |  | 87466.3 |  |  | 2011-07-22 | 2011-12-31 | 2011-08-01 | 2012-03-31
75087 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | -2431.57 |  |  |  |  | 164505.63 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75087 | FRCSW | RCSWTELC | Cust Call Ctr Switch Repl | -439.79 |  |  |  |  | 7340.21 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75086 | SGITOMSGI | SGARCSRVC | Smart Grid ARC Server Project | 32437.94 |  |  |  |  | 21720.09 |  |  | 2010-09-24 | 2011-01-31 | 2010-10-01 | 2011-03-08
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 47074.1 |  |  |  |  | 58342.66 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 41160.78 |  |  |  |  | 122838.4 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGITRNSLH | ITRON SG Solutions Hardware | 3550.51 |  |  |  |  | 3670.26 |  |  | 2011-07-14 | 2012-06-30 | 2011-10-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 1763.18 |  |  |  |  | 1763.18 |  |  | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75086 | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 7750.76 |  |  |  |  | 7750.76 |  |  | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75086 | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | 22773.04 |  |  |  |  | 22773.04 |  |  | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -3033.02 |  |  |  |  | -2991.45 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | SGITMTRSY | SGSYEDP2 | SG Scalability Phase 2 EDM064 | 170700.4 |  |  |  |  | 200981.55 |  |  | 2010-08-13 | 2012-01-15 | 2010-09-01 | 2011-08-13
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2013
Duke Energy Kentucky Gas
Year 2013
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 47352.41 |  |  |  |  | 96483.3 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 13104.95 |  |  |  |  | 44573.61 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 18062.7 |  |  |  |  | 42556.89 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 188.27 |  |  |  |  | 10659.08 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 3486.97 |  |  |  |  | 27696.88 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4CMR70 | Replace C-M 4" Kentucky Blanket | 12555.52 |  |  |  |  | 19731.33 |  |  | 2008-07-31 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 9501.45 |  |  |  |  | 49638.79 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 6156.64 |  |  |  |  | 8429.87 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 7745.65 |  |  |  |  | 24149.76 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 6967.07 |  |  |  |  | 12505.34 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 6MCR70 | Replace M-C 6" - Kentucky | 13026.14 |  |  |  |  | 13167.12 |  |  | 2008-07-01 | 2050-12-31 | 2012-07-01
75086 | G7SERVNEW | 8CMNEW70 | Install New C-M 8" | 5842.63 |  |  |  |  | 11674.91 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVMC | 8MCR70 | Replace M-C 8" and Greater | 3451.56 |  |  |  |  | 3451.56 |  |  | 2010-05-05 | 2050-12-31 | 2013-03-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 670134.5 |  |  |  |  | 1593701.67 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 1234526.24 |  |  |  |  | 5663685.33 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7MAINS | E0111 | PP #1006234 Serenity Way | -188.6 |  |  |  |  | 4506.39 |  |  | 2008-07-14 | 2013-03-31 | 2009-09-01 | 2010-01-10
75086 | CPERNST1 | F0904 | KY 237 Imp Pleasant Valley | 358408.89 |  |  |  |  | 918234.15 |  |  | 2009-10-05 | 2013-02-28 | 2010-10-01 | 2012-11-01
75086 | G7LGMR | F2907 | STA 804 Lookaway Drive | 185.68 |  |  |  |  | 58528.66 |  |  | 2009-12-09 | 2012-06-30 | 2009-12-01 | 2011-06-24
75086 | G7MSCPRD | F6566 | Inst no-flow pump cutoffs Constance | 12548.29 |  |  |  |  | 27875.81 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2011-10-15
75086 | G7MSCPRD | F6571 | Inst Odorizer and Flame Det Erlange | -6610.26 |  |  |  |  | 151048.29 |  |  | 2010-03-24 | 2014-07-31 | 2010-04-01 | 2012-01-15
75086 | KYCIBS10 | F7024 | MOD 618 | 0 |  |  |  |  | 318181.48 |  |  | 2010-04-07 | 2010-12-31 | 2010-06-01 | 2010-11-26
75086 | G7LGMR | F9125 | STA 806 - Grand Ave | 1114.88 |  |  |  |  | 98617.15 |  |  | 2010-06-03 | 2012-09-15 | 2011-01-01 | 2012-01-28
75086 | INDUSTRD | G0543 | Industrial Road | 6988.69 |  |  |  |  | 770202.29 |  |  | 2010-07-22 | 2011-10-30 | 2011-02-01 | 2011-09-23
75086 | G7PUBIMP | G0899 | Barnes Rd | -290.11 |  |  |  |  | 116719.97 |  |  | 2010-09-07 | 2013-07-31 | 2011-11-01 | 2012-05-23
75086 | G7PUBIMP | G0965 | Johns Hill Rd | 7887.53 |  |  |  |  | 210563.84 |  |  | 2010-09-13 | 2013-04-01 | 2011-09-01 | 2012-09-13
75086 | G7LGMR | G1978 | STA 810 - Taylor Mill South | 2488.9 |  |  |  |  | 177284.97 |  |  | 2011-01-26 | 2013-06-01 | 2011-02-01 | 2012-02-04
75086 | G7LGMR | G2537 | Rpl SCADA Radio Equip KY | -898.36 |  |  |  |  | 279547.52 |  |  | 2011-03-04 | 2014-07-31 | 2011-03-01 | 2013-03-15
75086 | TAYLRMIL | G2776 | Taylor Mill Rd F/L AM03 | 60731.41 |  |  |  |  | 1118440.76 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | TAYLRMIL | G2777 | Taylor Mill Rd Distribution Line | 53142.91 |  |  |  |  | 720608.64 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | G7REPL | G3073 | Ky Copper Mod 629 | 2712.87 |  |  |  |  | 360912.6 |  |  | 2011-04-21 | 2012-06-30 | 2011-04-01 | 2012-04-30
75086 | TAYLRMIL | G3074 | Taylor Mill Rd/I-275 to Taylor Cr | 253059.27 |  |  |  |  | 271361.38 |  |  | 2011-04-21 | 2014-01-31 | 2012-11-01 | 2013-07-17
75086 | G7MAINS | G3688 | STA 806 Outlet Piping | -1114.88 |  |  |  |  | 78924.87 |  |  | 2011-06-15 | 2012-06-30 | 2011-07-01 | 2012-01-28
75086 | TAYLRMIL | G3774 | Sipple Dr | 81.34 |  |  |  |  | 49446.31 |  |  | 2011-06-23 | 2013-05-15 | 2011-07-01 | 2013-01-03
75086 | G7LGMR | G3790 | Rpl Transmitters KY | 2457.57 |  |  |  |  | 15660.28 |  |  | 2011-06-24 | 2014-06-30 | 2011-11-01 | 2014-12-01
75086 | G7LGMR | G3792 | Rpl CDMA Radios for Telemeters KY | 782.02 |  |  |  |  | 24830.55 |  |  | 2011-06-24 | 2013-06-30 | 2011-11-01 | 2013-02-28
75086 | G7MSCPRD | G4116 | LP-03 Erlanger KY | -50275.72 |  |  |  |  | 50271.53 |  |  | 2011-07-21 | 2012-08-01 | 2011-08-01 | 2011-12-13
75086 | G7MSCPRD | G4181 | Replace F/L LP-03 under I-75 | 13944.3 |  |  |  |  | 271917.67 |  |  | 2011-07-27 | 2012-08-01 | 2011-08-01 | 2012-02-11
75086 | G7PUBIMP | G4496 | KY 22 Bridge | 102.84 |  |  |  |  | 205132.19 |  |  | 2011-08-16 | 2013-03-30 | 2012-03-01 | 2013-01-11
75086 | G7REPL | G4641 | KY Copper MOD 640 | 5958.69 |  |  |  |  | 163272.57 |  |  | 2011-08-26 | 2013-06-30 | 2011-12-01 | 2012-06-27
75086 | G7PRESIM | G4955 | Carothers Rd Pres Imp | 1348.53 |  |  |  |  | 47684.12 |  |  | 2011-09-14 | 2013-06-30 | 2011-12-01 | 2012-11-22
75086 | G7MSCPRD | G5034 | LP-03 Launcher/Receiver | 52.04 |  |  |  |  | 97089.6 |  |  | 2011-09-21 | 2013-02-28 | 2011-10-01 | 2012-11-30
75086 | G7MAINS | G5073 | EMAX 2609059 Province Pointe Subd | 5229.98 |  |  |  |  | 5824.15 |  |  | 2011-09-25 | 2013-06-30 | 2012-12-01 | 2013-04-15
75086 | G7MAINS | G5254 | 1305 Monmouth St Newport Ky | 423.56 |  |  |  |  | 60317.69 |  |  | 2011-10-06 | 2012-04-30 | 2012-02-01 | 2012-06-19
75086 | G7PRESIM | G6396 | Turkeyfoot Rd @ Autumn | 74.65 |  |  |  |  | 231416.4 |  |  | 2012-01-04 | 2013-01-03 | 2012-04-01 | 2012-09-29
75086 | G7PUBIMP | G6413 | Mall Rd Kroger Marketplace | 59891.75 |  |  |  |  | 28565.59 |  |  | 2012-01-06 | 2014-02-28 | 2012-01-01 | 2013-09-15
75086 | G7MAINS | G6542 | EMAX 2911813 Triple Crown Ctry Club | -71.6 |  |  |  |  | 8830.87 |  |  | 2012-01-23 | 2013-03-31 | 2012-10-01 | 2013-02-01
75086 | G7MAINS | G6918 | Burnet Ridge | 980.91 |  |  |  |  | 84533 |  |  | 2012-02-28 | 2013-05-30 | 2012-06-01 | 2012-12-06
75086 | G7MAINS | G6968 | EMAX 3021646 Triple Crown Country | -368.74 |  |  |  |  | 31266.43 |  |  | 2012-03-07 | 2013-09-30 | 2012-09-01 | 2013-02-01
75086 | G7MSCPRD | G7058 | F/L LP-03 Under I-275 | 63036.44 |  |  |  |  | 203570.46 |  |  | 2012-03-21 | 2013-02-21 | 2012-07-01 | 2012-12-20
75086 | G7MSCPRD | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 80771.81 |  |  |  |  | 189293.79 |  |  | 2012-04-17 | 2013-08-15 | 2012-07-01 | 2013-06-01
75086 | G7MAINS | G7425 | JT emax 3155555 Olde Ft Mitchell | -110.64 |  |  |  |  | 4106.03 |  |  | 2012-05-07 | 2013-05-31 | 2012-10-01 | 2013-02-19
75086 | CPERNST2 | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 471047.04 |  |  |  |  | 481405.74 |  |  | 2012-05-22 | 2015-01-15 | 2012-12-01 | 2014-07-01
75086 | CASINGKY | G7638 | Casing AM07 Dixie Hwy | 29492.06 |  |  |  |  | 639053.28 |  |  | 2012-05-24 | 2013-04-22 | 2012-06-01 | 2013-01-16
75086 | G7MAINS | G7648 | emax 3195744 Harmony Sub Ph D | -285.63 |  |  |  |  | 4905.41 |  |  | 2012-05-24 | 2013-02-28 | 2012-10-01 | 2013-01-05
75086 | PROPCONKY | G7687 | Vine Street Wilder | -108.89 |  |  |  |  | 118628.79 |  |  | 2012-05-29 | 2013-04-30 | 2012-08-01 | 2012-12-29
75086 | CASINGKY | G7750 | Casing Crescent Springs LP03 | 1486.29 |  |  |  |  | 81961.48 |  |  | 2012-06-05 | 2013-06-30 | 2012-07-01 | 2012-11-03
75086 | CASINGKY | G7751 | Casing BS #48 AM07 | 4114.5 |  |  |  |  | 679337.93 |  |  | 2012-06-05 | 2013-06-30 | 2012-06-01 | 2012-12-12
75086 | CASINGKY | G7752 | Casing #87 BS Turkeyfoot AM07 | 18296.42 |  |  |  |  | 661038.63 |  |  | 2012-06-05 | 2013-06-30 | 2012-08-01 | 2013-01-01
75086 | G7REPL | G7849 | Reg 109K - Inlet & Outlet Piping | 9244.98 |  |  |  |  | 78426.05 |  |  | 2012-06-12 | 2013-06-30 | 2012-08-01 | 2012-12-15
75086 | G7LGMR | G7850 | Reg 109K - Main St @ Dixie Hwy | 3313.76 |  |  |  |  | 106360.54 |  |  | 2012-06-12 | 2013-06-30 | 2012-08-01 | 2012-12-15
75086 | G7LGMR | G7851 | 4th & Saratogo (Rpl Reg 18K) | 9643.87 |  |  |  |  | 145280.49 |  |  | 2012-06-12 | 2013-07-31 | 2012-09-01 | 2013-03-05
75086 | G7MAINS | G7959 | JT emax 3268308 Triple Crown Sec 27 | 2719.13 |  |  |  |  | 10671.35 |  |  | 2012-06-26 | 2013-07-31 | 2012-09-01 | 2013-02-05
75086 | G7MAINS | G8058 | JT emax 3298935 Arcadia Ph A | -23283.89 |  |  |  |  | -23283.89 |  |  | 2012-07-13 | 2014-11-30 | 2013-07-01 | 2014-02-26
75086 | G7MAINS | G8091 | JT emax 3329101 Berlander Rd | 17876.3 |  |  |  |  | 17876.3 |  |  | 2012-07-23 | 2014-07-31 | 2013-08-01 | 2013-11-30
75086 | G7REPL | G8159 | Reg 115K - Inlet & Outlet Piping | 7322.63 |  |  |  |  | 26800.76 |  |  | 2012-07-30 | 2013-06-30 | 2012-09-01 | 2013-03-05
75086 | GITKYCAP | G8162 | EMAX CHANGE/INSIDE PIPING-KY | 242.84 |  |  |  |  | 26250.43 |  |  | 2012-07-30 | 2013-05-15 | 2012-08-01 | 2013-02-12
75086 | G7MAINS | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 8441.19 |  |  |  |  | 8441.19 |  |  | 2012-08-06 | 2013-08-31 | 2013-01-01 | 2013-05-16
75086 | G7MAINS | G8202 | JT emax 3366483 Ormond, Bistro | 12094.93 |  |  |  |  | 12094.93 |  |  | 2012-08-08 | 2013-08-31 | 2013-01-01 | 2013-05-16
75086 | G7MAINS | G8210 | JT emax 3371929 Triple Crown Sec 24 | -58.69 |  |  |  |  | 8329.23 |  |  | 2012-08-10 | 2013-06-30 | 2012-10-01 | 2013-02-01
75086 | G7PUBIMP | G8242 | AM00 - NKU | 15473.94 |  |  |  |  | 15473.94 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | G7LGMR | G8248 | REG 116K - Holman and Watkins | 214844.98 |  |  |  |  | 229208.15 |  |  | 2012-08-16 | 2013-12-01 | 2012-10-01 | 2013-05-21
75086 | G7REPL | G8249 | REG 116K Inlet & Outlet Lines | 65357.64 |  |  |  |  | 68691.06 |  |  | 2012-08-16 | 2013-12-01 | 2012-10-01 | 2013-05-21
75086 | G7MAINS | G8345 | JT emax 3409638 Cool Springs Ph 4B | -40.81 |  |  |  |  | 5705.53 |  |  | 2012-08-28 | 2013-10-30 | 2012-11-01 | 2013-03-01
75086 | G7MAINS | G8400 | JT emax 3437972 Thornwilde Ph O | 6395.03 |  |  |  |  | 11840.42 |  |  | 2012-09-06 | 2013-06-30 | 2012-11-01 | 2013-03-12
75086 | G7MAINS | G8498 | STA 792 Outlet | 8301.15 |  |  |  |  | 9334.66 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7MAINS | G8499 | STA 792 Inlet | 36038.51 |  |  |  |  | 39788.49 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7LGMR | G8500 | STA 792 - Arcadia Dr | 38435.18 |  |  |  |  | 50943.97 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7REPL | G8688 | Exposed Main Old Union Rd & US 42 | 4396.37 |  |  |  |  | 8966.65 |  |  | 2012-10-17 | 2013-02-09 | 2012-11-01 | 2012-11-09
75086 | G7MAINS | G8766 | GM 100 Richwood Rd | 14236.73 |  |  |  |  | 16128.38 |  |  | 2012-10-31 | 2013-12-31 | 2012-12-01 | 2013-04-08
75086 | G7MAINS | G8918 | JT emax 3537650 Tree Tops Ph 3B | 7758.82 |  |  |  |  | 7758.82 |  |  | 2012-11-15 | 2014-03-31 | 2013-08-01 | 2013-11-17
75086 | G7MAINS | G8937 | JT emax 3624651 Dominion Trail | 24071.08 |  |  |  |  | 24071.08 |  |  | 2012-11-16 | 2014-03-30 | 2013-09-01 | 2014-02-04
75086 | G7MAINS | G8993 | JT emax 3484085 Battle Ridge Subd | 13726.46 |  |  |  |  | 13726.46 |  |  | 2012-11-27 | 2014-05-31 | 2013-09-01 | 2013-12-27
75086 | G7REPL | G9007 | Miller St. Newport | 42527.92 |  |  |  |  | 45242.09 |  |  | 2012-11-29 | 2013-07-02 | 2012-12-01 | 2013-04-14
75086 | G7MAINS | G9170 | JT emax 3744516 Villa Grande Ph 4B | 5397.25 |  |  |  |  | 5397.25 |  |  | 2013-01-03 | 2014-02-28 | 2013-04-01 | 2013-08-15
75086 | G7MAINS | G9221 | JT emax 3759761 Ridgewood Valley | 6166.78 |  |  |  |  | 6166.78 |  |  | 2013-01-09 | 2013-10-31 | 2013-02-01 | 2013-06-02
75086 | FPCTAVMKY | G9238 | Vegetation Mgmt Kentucky | 17282.21 |  |  |  |  | 17282.21 |  |  | 2013-01-10 | 2017-08-30 | 2013-01-01 | 2015-02-28
75086 | G7MAINS | G9353 | JT emax 3806491 Villa Grande Ph 3A | 5397.89 |  |  |  |  | 5397.89 |  |  | 2013-01-23 | 2014-03-31 | 2013-05-01 | 2013-08-15
75086 | G7FRAME | G9421 | Frame Relay Kentucky | 26532.69 |  |  |  |  | 26532.69 |  |  | 2013-02-01 | 2014-06-30 | 2013-02-01 | 2014-12-01
75086 | G7MAINS | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 9283.76 |  |  |  |  | 9283.76 |  |  | 2013-02-08 | 2014-03-31 | 2013-06-01 | 2013-10-16
75086 | TAYLRMIL | G9552 | Taylor Mill Rd PH 3 - AM03 | 559454.42 |  |  |  |  | 559454.42 |  |  | 2013-02-19 | 2015-02-01 | 2013-05-01 | 2014-01-23
75086 | TAYLRMIL | G9553 | Taylor Mill Rd PH 3 - HP | 546721.06 |  |  |  |  | 546721.06 |  |  | 2013-02-19 | 2015-02-01 | 2013-05-01 | 2014-01-23
75086 | G7PUBIMP | G9648 | Pleasant Ridge Ave | 172436.3 |  |  |  |  | 172436.3 |  |  | 2013-02-27 | 2014-01-01 | 2013-04-01 | 2013-09-27
75086 | G7MAINS | G9755 | GM 3941287 Grant Park PH 3 | 21327.35 |  |  |  |  | 21327.35 |  |  | 2013-03-13 | 2014-03-31 | 2013-07-01 | 2013-10-20
75086 | G7MAINS | G9828 | JT emax 3972664 Thornwilde Ph O | 14536.93 |  |  |  |  | 14536.93 |  |  | 2013-03-25 | 2014-04-30 | 2013-07-01 | 2013-11-05
75086 | G7MAINS | G9876 | JT emax 3996921 Arbor Springs | 5020.42 |  |  |  |  | 5020.42 |  |  | 2013-04-01 | 2014-04-30 | 2013-08-01 | 2013-12-10
75086 | G7REPL | G9930 | Exposed Main on Petersburg Rd | 29781.21 |  |  |  |  | 29781.21 |  |  | 2013-04-12 | 2014-04-30 | 2013-06-01 | 2013-09-29
75086 | G7MAINS | H0053 | JT emax 4081400 Cauthen Run Subd | 528.88 |  |  |  |  | 528.88 |  |  | 2013-05-03 | 2014-05-31 | 2013-12-01 | 2014-05-17
75086 | G7REPL | H0070 | Exposed main SR 10 UL -27 | 47848.38 |  |  |  |  | 47848.38 |  |  | 2013-05-08 | 2014-04-01 | 2013-06-01 | 2013-11-08
75086 | G7MAINS | H0199 | JT emax 4158153 Triple Crown Sec 26 | 7798.72 |  |  |  |  | 7798.72 |  |  | 2013-06-03 | 2014-05-31 | 2013-11-01 | 2014-03-19
75086 | G7MAINS | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 5955.85 |  |  |  |  | 5955.85 |  |  | 2013-06-05 | 2014-05-31 | 2013-09-01 | 2014-01-07
75086 | G7REPL | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 10800.01 |  |  |  |  | 10800.01 |  |  | 2013-06-11 | 2014-04-01 | 2013-06-01 | 2013-09-17
75086 | G7PUBIMP | H0260 | Langview Dr, Wilder KY | 40442.63 |  |  |  |  | 40442.63 |  |  | 2013-06-13 | 2014-04-01 | 2013-07-01 | 2013-11-06
75086 | G7MAINS | H0335 | Cold Springs Main Extension | 4028.6 |  |  |  |  | 4028.6 |  |  | 2013-06-27 | 2014-04-04 | 2013-08-01 | 2014-01-07
75086 | G7LGMR | H0350 | STA 535K1 (UL33 to HP) Modification | 36.36 |  |  |  |  | 36.36 |  |  | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7REPL | H0383 | REG 117K - Inlet & Outlet Piping | 7094.78 |  |  |  |  | 7094.78 |  |  | 2013-07-05 | 2015-06-30 | 2013-12-01 | 2014-07-24
75086 | G7LGMR | H0384 | Reg 117K-Amsterdam & Redwood | 5191.66 |  |  |  |  | 5191.66 |  |  | 2013-07-05 | 2015-06-30 | 2013-10-01 | 2014-07-24
75086 | G7LGMR | H0485 | Reg 21K Improvements-Grand & Ft Tho | 1278.71 |  |  |  |  | 1278.71 |  |  | 2013-07-29 | 2015-06-30 | 2013-11-01 | 2014-02-11
75086 | G7MAINS | H0511 | Install Main Pavilion Pkwy Newport | 7638.68 |  |  |  |  | 7638.68 |  |  | 2013-08-05 | 2014-04-01 | 2013-08-01 | 2014-02-01
75086 | G7MAINS | H0550 | JT emax 4358713 Sherbourne Ph G | 5765.51 |  |  |  |  | 5765.51 |  |  | 2013-08-13 | 2014-06-30 | 2013-12-01 | 2014-04-13
75086 | G7MAINS | H0554 | JT emax 4332613 Shadybrook Bluffs | 9271.7 |  |  |  |  | 9271.7 |  |  | 2013-08-13 | 2014-09-30 | 2013-10-01 | 2014-02-18
75086 | G7REPL | H0613 | W. Fifth Street | 36942.54 |  |  |  |  | 36942.54 |  |  | 2013-08-22 | 2014-02-28 | 2013-08-01 | 2013-12-04
75086 | G7MAINS | H0644 | Independence Rd Main Extension | 22716.97 |  |  |  |  | 22716.97 |  |  | 2013-08-27 | 2014-04-01 | 2013-10-01 | 2014-02-05
75086 | G7MAINS | H0665 | Transport Dr Main Extension | 10048.22 |  |  |  |  | 10048.22 |  |  | 2013-08-29 | 2014-09-30 | 2013-10-01 | 2014-08-08
75086 | G7MAINS | H0688 | McCullum Dr & Courthouse Cr Ext | 12531.25 |  |  |  |  | 12531.25 |  |  | 2013-09-04 | 2014-04-01 | 2013-10-01 | 2014-03-03
75086 | G7MAINS | H0830 | Lakemont PT 2 | 2859.52 |  |  |  |  | 2859.52 |  |  | 2013-09-17 | 2014-08-15 | 2013-10-01 | 2014-05-14
75086 | G7MAINS | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 2216.59 |  |  |  |  | 2216.59 |  |  | 2013-09-24 | 2014-09-30 | 2013-11-01 | 2014-03-10
75086 | GMAINS | H1294 | JT 4503900 BALLYSHANNON S1 PH 1 | 10305.78 |  |  |  |  | 10305.78 |  |  | 2013-11-22 | 2014-11-30 | 2013-12-01 | 2014-06-11
75086 | GITKYCAP | H1423 | GTMS Upgrade | 5272.15 |  |  |  |  | 5272.15 |  |  | 2013-12-10 | 2014-11-30 | 2013-12-01 | 2014-07-29
75086 | GITKYCAP | H1444 | PCS Upgrade | 2760.6 |  |  |  |  | 2760.6 |  |  | 2013-12-11 | 2014-06-30 | 2013-12-01 | 2014-03-31
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 829885.73 |  |  |  |  | 1995484.69 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 10584.51 |  |  |  |  | 72899.28 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1702361.6 |  |  |  |  | 6087966.09 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 23722.06 |  |  |  |  | 109897.16 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | PCTA175AC | Customer Contact Preference Center | 20229.47 |  |  |  |  | 20229.47 |  |  | 2013-08-01 | 2014-10-14 | 2013-08-01 | 2014-10-14
75087 | FPIT | PCTA210C | Contact Channels Datamart & Dashboa | 2239.22 |  |  |  |  | 2239.22 |  |  | 2013-10-22 | 2014-09-23 | 2013-11-01 | 2014-09-23
75087 | FPIT | PCTAIT17X | Mobile Web Phase 1 | 3370.74 |  |  |  |  | 3370.74 |  |  | 2013-01-20 | 2013-10-30 | 2013-03-01 | 2014-01-31
75087 | FPIT | PCTAIVRSW | IVR Software and Licenses | 52868.96 |  |  |  |  | 52868.96 |  |  | 2013-03-12 | 2014-07-31 | 2013-05-01 | 2014-08-15
75087 | FPIT | RCIVRMKG | IVR Monitoring System | -0.42 |  |  |  |  | 2218.67 |  |  | 2012-06-13 | 2012-12-31 | 2012-09-01 | 2013-03-31
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 89.57 |  |  |  |  | 58432.23 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGITMTRSY | SGMDMMMH | SG MDM Mass Market Hardware | 7992.01 |  |  |  |  | 7992.01 |  |  | 2013-07-10 | 2014-09-30 | 2013-12-01 | 2014-08-19
75086 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 97854.85 |  |  |  |  | 97854.85 |  |  | 2013-07-12 | 2014-09-30 | 2013-07-01 | 2014-08-19
75086 | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 54546.82 |  |  |  |  | 56310 |  |  | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75086 | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 182.91 |  |  |  |  | 7933.67 |  |  | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75086 | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | 33032.8 |  |  |  |  | 55805.84 |  |  | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | 250.51 |  |  |  |  | -2740.94 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2014
Duke Energy Kentucky Gas
Year 2014
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 69579.15 |  |  |  |  | 166062.45 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 22568.85 |  |  |  |  | 67142.46 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3CMR70 | Replace C-M 3" Kentucky Blanket | 3279.63 |  |  |  |  | 7998.04 |  |  | 2008-07-31 | 2050-12-31 | 2009-04-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 43547.33 |  |  |  |  | 86104.22 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 4012.96 |  |  |  |  | 14672.04 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 6870.4 |  |  |  |  | 34567.28 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4CMR70 | Replace C-M 4" Kentucky Blanket | 1459.22 |  |  |  |  | 21190.55 |  |  | 2008-07-31 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 3944.66 |  |  |  |  | 53583.45 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 117.38 |  |  |  |  | 8547.25 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 3033.53 |  |  |  |  | 27183.29 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 6CMR70 | Replace C-M 6" Kentucky Blanket | 32490.6 |  |  |  |  | 32490.6 |  |  | 2008-07-31 | 2050-12-31 | 2014-05-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 16971.22 |  |  |  |  | 29476.56 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 6MCR70 | Replace M-C 6" - Kentucky | 5854.67 |  |  |  |  | 19021.79 |  |  | 2008-07-01 | 2050-12-31 | 2012-07-01
75086 | G7SERVNEW | 8CMNEW70 | Install New C-M 8" | 17279.52 |  |  |  |  | 28954.43 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVNEW | 8MCNEW70 | Install New M-C 8" | -82.38 |  |  |  |  | 807.77 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVMC | 8MCR70 | Replace M-C 8" and Greater | 243.83 |  |  |  |  | 3695.39 |  |  | 2010-05-05 | 2050-12-31 | 2013-03-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 1201082.19 |  |  |  |  | 2794783.86 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 1127460.7 |  |  |  |  | 6791146.03 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | KYCIBS08 | D3168 | 2008 KY CIBS MOD 597/JEB | -19388.73 |  |  |  |  | 568467.04 |  |  | 2008-03-27 | 2050-12-31 | 2008-04-01 | 2009-03-12
75086 | G7PUBIMP | D3344 | PP 959891/ LLM | -1948.36 |  |  |  |  | 839579.18 |  |  | 2008-04-23 | 2050-12-31 | 2008-05-01 | 2008-12-22
75086 | KYCIBS09 | D3576 | KY CIBS MOD 557/JEB | -13839.01 |  |  |  |  | 483686.31 |  |  | 2008-05-23 | 2013-05-22 | 2008-05-01 | 2009-07-13
75086 | G7LGMR | E0472 | Sta 795 Sandman Dr | 56556.07 |  |  |  |  | 74179.36 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7MAINS | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | -215872.98 |  |  |  |  | 72756.47 |  |  | 2008-11-17 | 2050-12-31 | 2009-06-01 | 2009-12-25
75086 | G7LGMR | G0446 | Reg 114K - Amsterdam Rd at Hamilton | -461.03 |  |  |  |  | 129637.53 |  |  | 2010-07-15 | 2011-04-01 | 2010-08-01 | 2011-02-02
75086 | INDUSTRD | G0543 | Industrial Road | 18098.58 |  |  |  |  | 788300.87 |  |  | 2010-07-22 | 2011-10-30 | 2011-02-01 | 2011-09-23
75086 | G7MAINS | G0582 | Reg 114K Inlet & Outlet | 82.38 |  |  |  |  | 13719.05 |  |  | 2010-07-27 | 2011-04-01 | 2010-08-01 | 2011-02-02
75086 | TAYLRMIL | G2776 | Taylor Mill Rd F/L AM03 | 3683.1 |  |  |  |  | 1122123.86 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | TAYLRMIL | G3074 | Taylor Mill Rd/I-275 to Taylor Cr | 89928.01 |  |  |  |  | 361289.39 |  |  | 2011-04-21 | 2014-01-31 | 2012-11-01 | 2013-07-17
75086 | G7LGMR | G3790 | Rpl Transmitters KY | 491.36 |  |  |  |  | 16151.64 |  |  | 2011-06-24 | 2014-06-30 | 2011-11-01 | 2014-12-01
75086 | G7LGMR | G3997 | Reg 110K - Woodfill Ave @ US 27 | 804.49 |  |  |  |  | 170542.48 |  |  | 2011-07-08 | 2013-02-10 | 2011-09-01 | 2012-11-17
75086 | G7MSCPRD | G5034 | LP-03 Launcher/Receiver | 3231.11 |  |  |  |  | 100320.71 |  |  | 2011-09-21 | 2013-02-28 | 2011-10-01 | 2012-11-30
75086 | G7MAINS | G5113 | REG 110K Inlet & Outlet Piping | 309.97 |  |  |  |  | 89912.31 |  |  | 2011-09-28 | 2013-02-10 | 2012-06-01 | 2012-11-17
75086 | G7MAINS | G5254 | 1305 Monmouth St Newport Ky | 185.37 |  |  |  |  | 60503.06 |  |  | 2011-10-06 | 2012-04-30 | 2012-02-01 | 2012-06-19
75086 | G7REPL | G5376 | Belmont Rd | -907.87 |  |  |  |  | 7142.87 |  |  | 2011-10-18 | 2012-05-28 | 2011-10-01 | 2012-02-14
75086 | G7PUBIMP | G6413 | Mall Rd Kroger Marketplace | 575.11 |  |  |  |  | 29140.7 |  |  | 2012-01-06 | 2014-02-28 | 2012-01-01 | 2013-09-15
75086 | G7LGMR | G6976 | Concrete Stairwell Rpl | 1295.21 |  |  |  |  | 13960.53 |  |  | 2012-03-07 | 2013-03-10 | 2012-07-01 | 2012-11-01
75086 | G7MSCPRD | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 5451.41 |  |  |  |  | 194745.2 |  |  | 2012-04-17 | 2013-08-15 | 2012-07-01 | 2013-06-01
75086 | CPERNST2 | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 44672.5 |  |  |  |  | 526078.24 |  |  | 2012-05-22 | 2015-01-15 | 2012-12-01 | 2014-07-01
75086 | CASINGKY | G7638 | Casing AM07 Dixie Hwy | -990.93 |  |  |  |  | 638062.35 |  |  | 2012-05-24 | 2013-04-22 | 2012-06-01 | 2013-01-16
75086 | CASINGKY | G7750 | Casing Crescent Springs LP03 | -313.65 |  |  |  |  | 81647.83 |  |  | 2012-06-05 | 2013-06-30 | 2012-07-01 | 2012-11-03
75086 | CASINGKY | G7751 | Casing BS #48 AM07 | -4676.61 |  |  |  |  | 674661.32 |  |  | 2012-06-05 | 2013-06-30 | 2012-06-01 | 2012-12-12
75086 | CASINGKY | G7752 | Casing #87 BS Turkeyfoot AM07 | -3815.94 |  |  |  |  | 657222.69 |  |  | 2012-06-05 | 2013-06-30 | 2012-08-01 | 2013-01-01
75086 | G7LGMR | G7851 | 4th & Saratogo (Rpl Reg 18K) | 5429.45 |  |  |  |  | 150709.94 |  |  | 2012-06-12 | 2013-07-31 | 2012-09-01 | 2013-03-05
75086 | G7MAINS | G8058 | JT emax 3298935 Arcadia Ph A | 5035.02 |  |  |  |  | -18248.87 |  |  | 2012-07-13 | 2014-11-30 | 2013-07-01 | 2014-02-26
75086 | G7REPL | G8159 | Reg 115K - Inlet & Outlet Piping | 2445.76 |  |  |  |  | 29246.52 |  |  | 2012-07-30 | 2013-06-30 | 2012-09-01 | 2013-03-05
75086 | G7PUBIMP | G8242 | AM00 - NKU | 237.32 |  |  |  |  | 15711.26 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | G7LGMR | G8248 | REG 116K - Holman and Watkins | -1235.39 |  |  |  |  | 227972.76 |  |  | 2012-08-16 | 2013-12-01 | 2012-10-01 | 2013-05-21
75086 | G7REPL | G8249 | REG 116K Inlet & Outlet Lines | 2433.69 |  |  |  |  | 71124.75 |  |  | 2012-08-16 | 2013-12-01 | 2012-10-01 | 2013-05-21
75086 | G7MAINS | G8499 | STA 792 Inlet | 5979.26 |  |  |  |  | 45767.75 |  |  | 2012-09-25 | 2014-04-01 | 2012-12-01 | 2014-01-18
75086 | G7REPL | G8688 | Exposed Main Old Union Rd & US 42 | -628.54 |  |  |  |  | 8338.11 |  |  | 2012-10-17 | 2013-02-09 | 2012-11-01 | 2012-11-09
75086 | FPCTAVMKY | G9238 | Vegetation Mgmt Kentucky | -15904.18 |  |  |  |  | 1378.03 |  |  | 2013-01-10 | 2017-08-30 | 2013-01-01 | 2015-02-28
75086 | G7FRAME | G9421 | Frame Relay Kentucky | 22674.68 |  |  |  |  | 49207.37 |  |  | 2013-02-01 | 2014-06-30 | 2013-02-01 | 2014-12-01
75086 | TAYLRMIL | G9552 | Taylor Mill Rd PH 3 - AM03 | 16173.82 |  |  |  |  | 575628.24 |  |  | 2013-02-19 | 2015-02-01 | 2013-05-01 | 2014-01-23
75086 | TAYLRMIL | G9553 | Taylor Mill Rd PH 3 - HP | 17828.17 |  |  |  |  | 564549.23 |  |  | 2013-02-19 | 2015-02-01 | 2013-05-01 | 2014-01-23
75086 | G7MAINS | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 9097.51 |  |  |  |  | 9097.51 |  |  | 2013-02-23 | 2014-03-11 | 2014-02-01 | 2014-06-13
75086 | G7PUBIMP | G9648 | Pleasant Ridge Ave | 38167.99 |  |  |  |  | 210604.29 |  |  | 2013-02-27 | 2014-01-01 | 2013-04-01 | 2013-09-27
75086 | G7MAINS | G9755 | GM 3941287 Grant Park PH 3 | -440.12 |  |  |  |  | 20887.23 |  |  | 2013-03-13 | 2014-03-31 | 2013-07-01 | 2013-10-20
75086 | G7MAINS | G9799 | GM 3941206 Stillbrooke Subd | 17139.01 |  |  |  |  | 17139.01 |  |  | 2013-03-19 | 2014-11-30 | 2014-03-01 | 2014-07-18
75086 | G7REPL | G9930 | Exposed Main on Petersburg Rd | -109.18 |  |  |  |  | 29672.03 |  |  | 2013-04-12 | 2014-04-30 | 2013-06-01 | 2013-09-29
75086 | G7MAINS | H0034 | JT emax 3548558 Orleans South Ph D | 10434.04 |  |  |  |  | 10434.04 |  |  | 2013-04-30 | 2015-03-01 | 2014-07-01 | 2014-11-30
75086 | G7MAINS | H0053 | JT emax 4081400 Cauthen Run Subd | 2999.82 |  |  |  |  | 3528.7 |  |  | 2013-05-03 | 2014-05-31 | 2013-12-01 | 2014-05-17
75086 | G7REPL | H0070 | Exposed main SR 10 UL -27 | 16262.22 |  |  |  |  | 64110.6 |  |  | 2013-05-08 | 2014-04-01 | 2013-06-01 | 2013-11-08
75086 | G7MAINS | H0199 | JT emax 4158153 Triple Crown Sec 26 | 24401.39 |  |  |  |  | 32200.11 |  |  | 2013-06-03 | 2014-05-31 | 2013-11-01 | 2014-03-19
75086 | G7PUBIMP | H0260 | Langview Dr, Wilder KY | -767.68 |  |  |  |  | 39674.95 |  |  | 2013-06-13 | 2014-04-01 | 2013-07-01 | 2013-11-06
75086 | G7LGMR | H0264 | Reg 118K Inlet & Outlet Piping | 4606.92 |  |  |  |  | 4606.92 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0265 | Reg 118K Installation | 11563.5 |  |  |  |  | 11563.5 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7MAINS | H0337 | Meadow Glen Main Extension | 60619.85 |  |  |  |  | 60619.85 |  |  | 2013-06-27 | 2015-01-01 | 2014-05-01 | 2014-10-17
75086 | G7LGMR | H0350 | STA 535K1 (UL33 to HP) Modification | 6947.58 |  |  |  |  | 6983.94 |  |  | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7REPL | H0383 | REG 117K - Inlet & Outlet Piping | 150088.34 |  |  |  |  | 157183.12 |  |  | 2013-07-05 | 2015-06-30 | 2013-12-01 | 2014-07-24
75086 | G7LGMR | H0384 | Reg 117K-Amsterdam & Redwood | 126761.06 |  |  |  |  | 131952.72 |  |  | 2013-07-05 | 2015-06-30 | 2013-10-01 | 2014-07-24
75086 | G7MAINS | H0440 | JT emax 4279992 Manhattan Harbour | 26833.94 |  |  |  |  | 26833.94 |  |  | 2013-07-18 | 2014-11-30 | 2014-04-01 | 2014-08-31
75086 | G7MAINS | H0511 | Install Main Pavilion Pkwy Newport | 13965.32 |  |  |  |  | 21604 |  |  | 2013-08-05 | 2014-04-01 | 2013-08-01 | 2014-02-01
75086 | G7MAINS | H0550 | JT emax 4358713 Sherbourne Ph G | 21240.58 |  |  |  |  | 27006.09 |  |  | 2013-08-13 | 2014-06-30 | 2013-12-01 | 2014-04-13
75086 | G7MAINS | H0554 | JT emax 4332613 Shadybrook Bluffs | -83 |  |  |  |  | 9188.7 |  |  | 2013-08-13 | 2014-09-30 | 2013-10-01 | 2014-02-18
75086 | G7MAINS | H0665 | Transport Dr Main Extension | 38922.01 |  |  |  |  | 48970.23 |  |  | 2013-08-29 | 2014-09-30 | 2013-10-01 | 2014-08-08
75086 | G7MAINS | H0688 | McCullum Dr & Courthouse Cr Ext | 113020.06 |  |  |  |  | 125551.31 |  |  | 2013-09-04 | 2014-04-01 | 2013-10-01 | 2014-03-03
75086 | G7MAINS | H0779 | JT 4446105 Lakemont Main Ext | 12407.97 |  |  |  |  | 12407.97 |  |  | 2013-09-13 | 2014-06-30 | 2014-06-01 | 2014-10-19
75086 | G7MAINS | H0780 | JT 4448657 Triple Crown Cntry Clb | 30012.29 |  |  |  |  | 30012.29 |  |  | 2013-09-13 | 2014-07-31 | 2014-02-01 | 2014-07-16
75086 | G7MAINS | H0830 | Lakemont PT 2 | 15403.2 |  |  |  |  | 18262.72 |  |  | 2013-09-17 | 2014-08-15 | 2013-10-01 | 2014-05-14
75086 | G7REPL | H0835 | Stevenson Rd Erlanger | 49125.73 |  |  |  |  | 49125.73 |  |  | 2013-09-17 | 2014-08-15 | 2014-02-01 | 2014-07-01
75086 | G7MAINS | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 4978.76 |  |  |  |  | 7195.35 |  |  | 2013-09-24 | 2014-09-30 | 2013-11-01 | 2014-03-10
75086 | G7MAINS | H0951 | 204 Hayes Station Rd Main Ext | 12754.98 |  |  |  |  | 12754.98 |  |  | 2013-10-02 | 2014-07-31 | 2014-01-01 | 2014-05-11
75086 | G7MAINS | H1290 | Ferguson Blvd Dry Ridge | 68497.7 |  |  |  |  | 68497.7 |  |  | 2013-11-22 | 2014-09-01 | 2014-01-01 | 2014-06-02
75086 | GMAINS | H1294 | JT 4503900 BALLYSHANNON S1 PH 1 | 37866.82 |  |  |  |  | 48172.6 |  |  | 2013-11-22 | 2014-11-30 | 2013-12-01 | 2014-06-11
75086 | G7MAINS | H1380 | JT 4629095 Arcadia West PH A gas | 23478.72 |  |  |  |  | 23478.72 |  |  | 2013-12-04 | 2014-11-26 | 2014-02-01 | 2014-07-21
75086 | GITKYCAP | H1423 | GTMS Upgrade | 20994.85 |  |  |  |  | 26267 |  |  | 2013-12-10 | 2014-11-30 | 2013-12-01 | 2014-07-29
75086 | GITKYCAP | H1444 | PCS Upgrade | 203.87 |  |  |  |  | 2964.47 |  |  | 2013-12-11 | 2014-06-30 | 2013-12-01 | 2014-03-31
75086 | G7MAINS | H1463 | Sutter Drive Main Extension | 23406.5 |  |  |  |  | 23406.5 |  |  | 2013-12-13 | 2014-11-30 | 2014-01-01 | 2014-05-19
75086 | G7SERVMC | H1529 | 7080 Industrial Rd | 2505.46 |  |  |  |  | 2505.46 |  |  | 2013-12-19 | 2014-06-30 | 2014-03-01 | 2011-09-24
75086 | G7SERVMC | H1530 | 7100 Industrial Rd | 3115.06 |  |  |  |  | 3115.06 |  |  | 2013-12-19 | 2014-06-30 | 2014-03-01 | 2011-09-08
75086 | G7SERVMC | H1531 | 6850 Industrial Rd | 3101.64 |  |  |  |  | 3101.64 |  |  | 2013-12-19 | 2014-07-31 | 2014-03-01 | 2011-09-23
75086 | G7SERVMC | H1532 | 7090 Industrial Rd | 2234.79 |  |  |  |  | 2234.79 |  |  | 2013-12-19 | 2014-07-31 | 2014-03-01 | 2011-09-16
75086 | G7MAINS | H1534 | JT 4172674 Cauthen Run PH 4 | 5111.86 |  |  |  |  | 5111.86 |  |  | 2013-12-20 | 2014-10-31 | 2014-07-01 | 2014-10-12
75086 | G7REPL | H1646 | Caroline Ave | 229.53 |  |  |  |  | 229.53 |  |  | 2014-01-10 | 2014-07-31 | 2014-01-01 | 2014-04-30
75086 | G7MAINS | H1710 | Southside Church Rd | 20282.67 |  |  |  |  | 20282.67 |  |  | 2014-01-27 | 2014-12-01 | 2014-06-01 | 2014-10-10
75086 | G7MSCPRD | I6105 | Replace Erlanger GP RTU's | 162785.66 |  |  |  |  | 162785.66 |  |  | 2014-03-18 | 2015-06-30 | 2014-03-01 | 2015-06-01
75086 | G7PUBIMP | J0107 | Upland Ave | 35928.51 |  |  |  |  | 35928.51 |  |  | 2014-03-24 | 2014-10-11 | 2014-04-01 | 2014-07-31
75086 | G7MAINS | J9116 | JT 5303098 Arc Highlnds PH 1 | 6109.02 |  |  |  |  | 6109.02 |  |  | 2014-04-11 | 2015-05-14 | 2014-10-01 | 2015-04-09
75086 | G7MAINS | K0115 | JT 5293782 Villa Grande | 2425.77 |  |  |  |  | 2425.77 |  |  | 2014-04-14 | 2015-07-08 | 2014-11-01 | 2015-03-09
75086 | G7MAINS | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 20602.74 |  |  |  |  | 20602.74 |  |  | 2014-04-16 | 2015-03-31 | 2014-06-01 | 2014-10-25
75086 | G7REPL | K5112 | Fox Street | 9277.92 |  |  |  |  | 9277.92 |  |  | 2014-04-24 | 2014-12-30 | 2014-05-01 | 2014-08-28
75086 | G7IMPRPL | K9112 | Install O2 and H2S Sensors at Foste | 92257.68 |  |  |  |  | 92257.68 |  |  | 2014-05-02 | 2015-04-30 | 2014-06-01 | 2015-06-01
75086 | G7MAINS | L1104 | JT 5457387 Harmony Ph D-3 | 2168.08 |  |  |  |  | 2168.08 |  |  | 2014-05-06 | 2015-10-26 | 2014-11-01 | 2015-04-12
75086 | G7MSCPRD | L4115 | Replace Control Valves at Constance | 32979.79 |  |  |  |  | 32979.79 |  |  | 2014-05-13 | 2015-06-30 | 2014-06-01 | 2014-11-01
75086 | G7MAINS | L5120 | JT 5512293 Aosta Valley Ph 3 | 10287.87 |  |  |  |  | 10287.87 |  |  | 2014-05-14 | 2015-03-31 | 2014-09-01 | 2015-02-01
75086 | G7MAINS | M5109 | JT 5667493 Lakemont Ph 2C | 14838.15 |  |  |  |  | 14838.15 |  |  | 2014-06-10 | 2015-06-30 | 2014-07-01 | 2014-11-15
75086 | G7MSCPRD | M6102 | Replace Compress 6&7 oil lube sys | 53357.88 |  |  |  |  | 53357.88 |  |  | 2014-06-11 | 2016-06-30 | 2014-09-01 | 2015-01-14
75086 | G7MSCPRD | M6103 | Erlanger GP Aftercooler Retube | 78724.11 |  |  |  |  | 78724.11 |  |  | 2014-06-11 | 2016-06-30 | 2014-06-01 | 2015-01-21
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 532964.96 |  |  |  |  | 2528449.65 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 21930.44 |  |  |  |  | 94829.72 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1535389.36 |  |  |  |  | 7623355.45 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 103482.15 |  |  |  |  | 213379.31 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7MAINS | N0103 | JT 5704778 North Walton Pointe Ph 2 | 2097.16 |  |  |  |  | 2097.16 |  |  | 2014-06-17 | 2015-09-30 | 2014-11-01 | 2015-04-13
75086 | G7MAINS | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 37467.84 |  |  |  |  | 37467.84 |  |  | 2014-06-23 | 2015-07-31 | 2014-09-01 | 2015-01-28
75086 | G7MAINS | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 9247.45 |  |  |  |  | 9247.45 |  |  | 2014-07-01 | 2015-05-31 | 2014-08-01 | 2015-02-07
75086 | G7PUBIMP | N8164 | Summit Lane | 101481.55 |  |  |  |  | 101481.55 |  |  | 2014-07-03 | 2015-02-01 | 2014-07-01 | 2014-10-16
75087 | FPIT | NINT1024C | NINT1024 Knowledge Management Tool | 12597.33 |  |  |  |  | 12597.33 |  |  | 2014-01-13 | 2014-12-30 | 2014-02-01 | 2014-11-23
75086 | NINT686FP | NINT686 | NINT686 IEE C+I Upgrade Project | 41.72 |  |  |  |  | 41.72 |  |  | 2014-06-13 | 2014-10-23 | 2014-10-01 | 2015-04-15
75087 | FPIT | NINT979C | NINT979C Combined Mobile SMS TXT | 17613.58 |  |  |  |  | 17613.58 |  |  | 2014-10-01 | 2014-12-31 | 2014-10-01 | 2015-05-20
75086 | G7MAINS | O3114 | JT 5843063 Reveres Crossing Ph 4 | 6580.93 |  |  |  |  | 6580.93 |  |  | 2014-07-16 | 2015-07-30 | 2014-09-01 | 2015-03-26
75086 | G7MAINS | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 8006.32 |  |  |  |  | 8006.32 |  |  | 2014-07-23 | 2015-07-25 | 2014-09-01 | 2015-01-11
75086 | G7PUBIMP | O4165 | Dudley Rd Improvement | 105811.75 |  |  |  |  | 105811.75 |  |  | 2014-07-23 | 2015-03-01 | 2014-08-01 | 2014-11-01
75086 | G7MAINS | P3113 | JT 5557980 Harmony Ph C3 | 1451.02 |  |  |  |  | 1451.02 |  |  | 2014-08-07 | 2015-07-01 | 2014-11-01 | 2015-04-22
75086 | G7MAINS | P4102 | JT 6024610 50-58 Orphange Rd | 2832.81 |  |  |  |  | 2832.81 |  |  | 2014-08-08 | 2015-07-01 | 2014-10-01 | 2015-02-08
75086 | G7PUBIMP | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 8422.87 |  |  |  |  | 8422.87 |  |  | 2014-08-22 | 2015-06-28 | 2014-12-01 | 2015-08-05
75086 | G7MAINS | P6206 | JT 4940830 Williams Woods Ph 4 | 25172.15 |  |  |  |  | 25172.15 |  |  | 2014-08-27 | 2015-07-01 | 2014-09-01 | 2015-01-13
75086 | G7MAINS | P6292 | JT 5702282 Alson Place Ph 2 | 927.25 |  |  |  |  | 927.25 |  |  | 2014-09-10 | 2015-10-15 | 2014-12-01 | 2015-04-16
75086 | G7REPL | P6335 | Dudley Rd - Relocation For Rstorm | 98594.17 |  |  |  |  | 98594.17 |  |  | 2014-09-19 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7MAINS | P6377 | JT 5666593 Sycamore Creek Ph 2 | 3236.01 |  |  |  |  | 3236.01 |  |  | 2014-09-24 | 2015-09-15 | 2014-12-01 | 2015-04-30
75086 | G7PUBIMP | P6497 | Hayes Station Rd | 10960.84 |  |  |  |  | 10960.84 |  |  | 2014-10-03 | 2015-04-10 | 2014-10-01 | 2014-12-05
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | 13402.76 |  |  |  |  | 13402.76 |  |  | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7PUBIMP | P6551 | Dudley Rd - Relocation for Storm | 9692.78 |  |  |  |  | 9692.78 |  |  | 2014-10-09 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7MAINS | P6634 | Lauren Dr MEA | 2884.96 |  |  |  |  | 2884.96 |  |  | 2014-10-16 | 2015-08-28 | 2014-11-01 | 2015-03-20
75086 | G7IMPRPL | P6709 | Deep Well Erlanger Gas Plant | 58207.72 |  |  |  |  | 58207.72 |  |  | 2014-10-31 | 2015-04-27 | 2014-11-01 | 2015-03-10
75086 | G7IMPRPL | P6754 | T/L AM07 - Install Corrosion Monito | 17913.77 |  |  |  |  | 17913.77 |  |  | 2014-11-05 | 2015-11-01 | 2014-12-01 | 2015-10-15
75086 | G7IMPRPL | P6758 | T/L UL02 - Install Corrosion Monito | 18477.04 |  |  |  |  | 18477.04 |  |  | 2014-11-05 | 2015-05-30 | 2014-12-01 | 2015-02-28
75087 | FPIT | PCTA1049C | INT1049 BRNR | 15983.03 |  |  |  |  | 15983.03 |  |  | 2014-10-23 | 2015-07-31 | 2014-11-01 | 2015-10-17
75087 | FPIT | PCTA175AC | Customer Contact Preference Center | 10301.11 |  |  |  |  | 30530.58 |  |  | 2013-08-01 | 2014-10-14 | 2013-08-01 | 2014-10-14
75087 | FPIT | PCTA175BS | PCTA175BS CDS | 206.4 |  |  |  |  | 206.4 |  |  | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75087 | FPIT | PCTA210C | Contact Channels Datamart & Dashboa | 3129.97 |  |  |  |  | 5369.19 |  |  | 2013-10-22 | 2014-09-23 | 2013-11-01 | 2014-09-23
75087 | FPIT | PCTA481AC | CA Lisa | 8221.76 |  |  |  |  | 8221.76 |  |  | 2014-10-21 | 2015-11-30 | 2014-11-01 | 2015-03-31
75087 | FPIT | PCTA481AH | INT481A CDP Hardware Implementation | 6449.4 |  |  |  |  | 6449.4 |  |  | 2014-10-23 | 2015-11-30 | 2014-11-01 | 2015-03-31
75087 | FPIT | PCTA481AS | Sitecore | 150656.05 |  |  |  |  | 150656.05 |  |  | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75087 | FPIT | PCTAIT17X | Mobile Web Phase 1 | -41.95 |  |  |  |  | 3328.79 |  |  | 2013-01-20 | 2013-10-30 | 2013-03-01 | 2014-01-31
75086 | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 16286.05 |  |  |  |  | 16286.05 |  |  | 2014-07-22 | 2015-07-30 | 2014-07-01 | 2015-12-28
75086 | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | 5807.71 |  |  |  |  | 5807.71 |  |  | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75087 | FPIT | PCTAIVRSW | IVR Software and Licenses | 7648.85 |  |  |  |  | 60517.81 |  |  | 2013-03-12 | 2014-07-31 | 2013-05-01 | 2014-08-15
75087 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | 0 |  |  |  |  | 164505.63 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | -267.49 |  |  |  |  | 58164.74 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | -42.58 |  |  |  |  | 122795.82 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMMM2C | SG MDM Mass Market 2 - CMS Work | 2.53 |  |  |  |  | 2.53 |  |  | 2014-11-03 | 2015-02-15 | 2014-11-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 37560.12 |  |  |  |  | 37560.12 |  |  | 2014-04-28 | 2015-02-15 | 2014-04-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMMH | SG MDM Mass Market Hardware | 3100.4 |  |  |  |  | 11092.41 |  |  | 2013-07-10 | 2014-09-30 | 2013-12-01 | 2014-08-19
75086 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 82542.31 |  |  |  |  | 180397.16 |  |  | 2013-07-12 | 2014-09-30 | 2013-07-01 | 2014-08-19
75086 | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 11987.22 |  |  |  |  | 68297.22 |  |  | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75086 | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 5661.4 |  |  |  |  | 5661.4 |  |  | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75086 | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 0 |  |  |  |  | 7933.67 |  |  | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75086 | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | 0 |  |  |  |  | 55805.84 |  |  | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75086 | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 3316.57 |  |  |  |  | 3316.57 |  |  | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75086 | SGNNT1021 | SGNT1021B | SG NINT1021B - SERVERS | 153.75 |  |  |  |  | 153.75 |  |  | 2014-04-30 | 2014-11-30 | 2014-08-01 | 2015-02-01
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | 3403.73 |  |  |  |  | 662.79 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | GSMARTK | SMARTKYP1 | Gas Smart Implementation Phase 1 | 62749.5 |  |  |  |  | 62749.5 |  |  | 2014-07-02 | 2017-02-07 | 2014-07-01 | 2016-03-14
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2015
Duke Energy Kentucky Gas
Year 2015
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 31106.31 |  |  |  |  | 197168.76 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 4810.21 |  |  |  |  | 71952.67 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3CMR70 | Replace C-M 3" Kentucky Blanket | 25827.27 |  |  |  |  | 33825.31 |  |  | 2008-07-31 | 2050-12-31 | 2009-04-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 16786.86 |  |  |  |  | 102891.08 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 35175.93 |  |  |  |  | 49847.97 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 130642.54 |  |  |  |  | 165209.82 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4CMR70 | Replace C-M 4" Kentucky Blanket | 5250.52 |  |  |  |  | 26441.07 |  |  | 2008-07-31 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 37500.07 |  |  |  |  | 91083.52 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 4MCR70 | Replace M-C 4" - Kentucky | 25420.53 |  |  |  |  | 33967.78 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 9313.73 |  |  |  |  | 36497.02 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 6CMR70 | Replace C-M 6" Kentucky Blanket | 1365.5 |  |  |  |  | 33856.1 |  |  | 2008-07-31 | 2050-12-31 | 2014-05-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 6462.49 |  |  |  |  | 35939.05 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 6MCR70 | Replace M-C 6" - Kentucky | 1084.78 |  |  |  |  | 20106.57 |  |  | 2008-07-01 | 2050-12-31 | 2012-07-01
75086 | G7SERVNEW | 8CMNEW70 | Install New C-M 8" | 12394.73 |  |  |  |  | 41349.16 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVNEW | 8MCNEW70 | Install New M-C 8" | 21699.2 |  |  |  |  | 22506.97 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 79173.5 |  |  |  |  | 79173.5 |  |  | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 1027379.81 |  |  |  |  | 1027379.81 |  |  | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 8.67 |  |  |  |  | 8.67 |  |  | 2015-03-30 16:20 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 16830.02 |  |  |  |  | 16830.02 |  |  | 2015-03-30 16:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 7.09 |  |  |  |  | 7.09 |  |  | 2015-03-30 14:15 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | FENABLES | ARMS | Enable ARM Scheduler Software | 31467.79 |  |  |  |  | 31467.79 |  |  | 2015-03-30 16:26 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | GITKYCAP | BOES | Boes Replacement (AGOES) for Gas | 40417.8 |  |  |  |  | 40417.8 |  |  | 2015-05-01 11:05 | 2016-06-30 | 2015-08-01 | 2017-01-25
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 18543.28 |  |  |  |  | 18543.28 |  |  | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 40921.33 |  |  |  |  | 40921.33 |  |  | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 28068.82 |  |  |  |  | 28068.82 |  |  | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 1064788.61 |  |  |  |  | 3859572.47 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 1003801.29 |  |  |  |  | 7794947.32 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 188680.78 |  |  |  |  | 188680.78 |  |  | 2015-03-04 11:36 | 2022-12-31 | 2015-07-01
75086 | G7MAINS | E0468 | Sta 795 Outlet Piping | -853.91 |  |  |  |  | 10159.59 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7MAINS | E0469 | Sta 795 Inlet Piping | -266.05 |  |  |  |  | 6605.21 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7LGMR | E0472 | Sta 795 Sandman Dr | -1647.98 |  |  |  |  | 72531.38 |  |  | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 3673.12 |  |  |  |  | 3673.12 |  |  | 2015-03-30 16:52 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | EGISH | Enable EGIS Hardware | 405.89 |  |  |  |  | 405.89 |  |  | 2015-03-30 15:51 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | EGISS | Enable EGIS Software | 70926.14 |  |  |  |  | 70926.14 |  |  | 2015-03-30 16:42 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | 113333.43 |  |  |  |  | 113333.43 |  |  | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01
75086 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 49.09 |  |  |  |  | 49.09 |  |  | 2015-03-30 14:50 | 2017-10-31 | 2015-08-01 | 2017-11-07
75086 | FENABLES | EXPDS | Enable Expert Designer Software | 30168.92 |  |  |  |  | 30168.92 |  |  | 2015-03-30 16:33 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | TAYLRMIL | G2776 | Taylor Mill Rd F/L AM03 | -9629.68 |  |  |  |  | 1112494.18 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | TAYLRMIL | G2777 | Taylor Mill Rd Distribution Line | 29301.8 |  |  |  |  | 749910.44 |  |  | 2011-03-25 | 2013-06-30 | 2011-04-01 | 2012-10-27
75086 | CPERNST2 | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | -891.95 |  |  |  |  | 525186.29 |  |  | 2012-05-22 | 2015-01-15 | 2012-12-01 | 2014-07-01
75086 | G7PUBIMP | G8241 | Sunset Drive - Three Mile Rd Imp | 136816.95 |  |  |  |  | 136816.95 |  |  | 2012-08-16 | 2016-01-31 | 2015-02-01 | 2016-02-05
75086 | G7PUBIMP | G8242 | AM00 - NKU | 954366.71 |  |  |  |  | 970077.97 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | FPCTAVMKY | G9238 | Vegetation Mgmt Kentucky | 12.62 |  |  |  |  | 1390.65 |  |  | 2013-01-10 | 2017-08-30 | 2013-01-01 | 2015-02-28
75086 | G7FRAME | G9421 | Frame Relay Kentucky | -631.94 |  |  |  |  | 48575.43 |  |  | 2013-02-01 | 2014-06-30 | 2013-02-01 | 2014-12-01
75086 | OM75086 | GASKYIND | Indirect Pool | 73.54 |  |  |  |  | 73.54 |  |  | 2008-07-01 | 2020-12-31 | 2008-07-01
75086 | G7LGMR | H0264 | Reg 118K Inlet & Outlet Piping | 76033.06 |  |  |  |  | 80639.98 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0265 | Reg 118K Installation | 190985.02 |  |  |  |  | 202548.52 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0350 | STA 535K1 (UL33 to HP) Modification | 15874.69 |  |  |  |  | 22858.63 |  |  | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7LGMR | H0384 | Reg 117K-Amsterdam & Redwood | 800.02 |  |  |  |  | 132752.74 |  |  | 2013-07-05 | 2015-06-30 | 2013-10-01 | 2014-07-24
75086 | G7MAINS | H1364 | Sutter Drive Main Extension | 557.23 |  |  |  |  | 557.23 |  |  | 2013-12-02 | 2014-11-30 | 2015-08-01 | 2015-12-09
75086 | GITKYCAP | H1423 | GTMS Upgrade | -771.97 |  |  |  |  | 25495.03 |  |  | 2013-12-10 | 2014-11-30 | 2013-12-01 | 2014-07-29
75086 | G7MSCPRD | I6105 | Replace Erlanger GP RTU's | 6961.96 |  |  |  |  | 169747.62 |  |  | 2014-03-18 | 2015-06-30 | 2014-03-01 | 2015-06-01
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 90289.68 |  |  |  |  | 90289.68 |  |  | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7MAINS | J9116 | JT 5303098 Arc Highlnds PH 1 | 4533.34 |  |  |  |  | 10642.36 |  |  | 2014-04-11 | 2015-05-14 | 2014-10-01 | 2015-04-09
75086 | G7MAINS | K0115 | JT 5293782 Villa Grande | 6576.95 |  |  |  |  | 9002.72 |  |  | 2014-04-14 | 2015-07-08 | 2014-11-01 | 2015-03-09
75086 | G7IMPRPL | K9112 | Install O2 and H2S Sensors at Foste | 13784.18 |  |  |  |  | 106041.86 |  |  | 2014-05-02 | 2015-04-30 | 2014-06-01 | 2015-06-01
75086 | G7MAINS | L1104 | JT 5457387 Harmony Ph D-3 | 6402.23 |  |  |  |  | 8570.31 |  |  | 2014-05-06 | 2015-10-26 | 2014-11-01 | 2015-04-12
75086 | G7MSCPRD | L4115 | Replace Control Valves at Constance | -341.43 |  |  |  |  | 32638.36 |  |  | 2014-05-13 | 2015-06-30 | 2014-06-01 | 2014-11-01
75086 | G7MAINS | L5120 | JT 5512293 Aosta Valley Ph 3 | 21.16 |  |  |  |  | 10309.03 |  |  | 2014-05-14 | 2015-03-31 | 2014-09-01 | 2015-02-01
75086 | G7MAINS | M5109 | JT 5667493 Lakemont Ph 2C | -185.69 |  |  |  |  | 14652.46 |  |  | 2014-06-10 | 2015-06-30 | 2014-07-01 | 2014-11-15
75086 | G7MSCPRD | M6102 | Replace Compress 6&7 oil lube sys | 304.3 |  |  |  |  | 53662.18 |  |  | 2014-06-11 | 2016-06-30 | 2014-09-01 | 2015-01-14
75086 | G7MSCPRD | M6103 | Erlanger GP Aftercooler Retube | 10344.23 |  |  |  |  | 89068.34 |  |  | 2014-06-11 | 2016-06-30 | 2014-06-01 | 2015-01-21
75086 | GITKYCAP | MAOP7SFTW | Maximum Allowable Operating Pressur | 35949.1 |  |  |  |  | 35949.1 |  |  | 2015-03-12 12:19 | 2016-04-30 | 2015-04-01 | 2016-12-12
75086 | FENABLEH | MAXH | Enable Maximo Hardware | 493.57 |  |  |  |  | 493.57 |  |  | 2015-03-30 13:58 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | MAXS | Enable Maximo Software | 233994.91 |  |  |  |  | 233994.91 |  |  | 2015-03-30 16:21 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 1368428.49 |  |  |  |  | 3896878.14 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 24056.45 |  |  |  |  | 118886.17 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1123611.15 |  |  |  |  | 8746966.6 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 74926.62 |  |  |  |  | 288305.93 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 408894.06 |  |  |  |  | 408894.06 |  |  | 2015-03-04 11:18 | 2022-12-31 | 2015-07-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 2025.06 |  |  |  |  | 2025.06 |  |  | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | 101708.53 |  |  |  |  | 101708.53 |  |  | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7MAINS | N0103 | JT 5704778 North Walton Pointe Ph 2 | 1724.24 |  |  |  |  | 3821.4 |  |  | 2014-06-17 | 2015-09-30 | 2014-11-01 | 2015-04-13
75086 | G7MAINS | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 1865.91 |  |  |  |  | 39333.75 |  |  | 2014-06-23 | 2015-07-31 | 2014-09-01 | 2015-01-28
75086 | G7PUBIMP | N8164 | Summit Lane | 910.35 |  |  |  |  | 102391.9 |  |  | 2014-07-03 | 2015-02-01 | 2014-07-01 | 2014-10-16
75087 | FPIT | NINT1024C | NINT1024 Knowledge Management Tool | 123.77 |  |  |  |  | 12721.1 |  |  | 2014-01-13 | 2014-12-30 | 2014-02-01 | 2014-11-23
75087 | FPIT | NINT1139H | NINT1139 CCO TPO MODEL | 462.15 |  |  |  |  | 462.15 |  |  | 2014-12-17 | 2014-12-31 | 2015-01-01 | 2015-08-18
75087 | FPIT | NINT1139L | NINT1139 CCO TPO MODEL | 2294.82 |  |  |  |  | 2294.82 |  |  | 2014-12-17 | 2014-12-31 | 2015-04-01 | 2016-03-31
75087 | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 7.59 |  |  |  |  | 7.59 |  |  | 2015-11-16 14:22 | 2016-09-30 | 2015-12-01 | 2017-03-27
75086 | NINT686FP | NINT686 | NINT686 IEE C+I Upgrade Project | 0.1 |  |  |  |  | 41.82 |  |  | 2014-06-13 | 2014-10-23 | 2014-10-01 | 2015-04-15
75087 | FPIT | NINT979C | NINT979C Combined Mobile SMS TXT | 1907.24 |  |  |  |  | 19520.82 |  |  | 2014-10-01 | 2014-12-31 | 2014-10-01 | 2015-05-20
75086 | G7MAINS | O3114 | JT 5843063 Reveres Crossing Ph 4 | 832.8 |  |  |  |  | 7413.73 |  |  | 2014-07-16 | 2015-07-30 | 2014-09-01 | 2015-03-26
75086 | G7MAINS | O4163 | JT 5925052 Arcadia Ph A Pt 2 | -9.86 |  |  |  |  | 7996.46 |  |  | 2014-07-23 | 2015-07-25 | 2014-09-01 | 2015-01-11
75086 | G7MAINS | P3113 | JT 5557980 Harmony Ph C3 | 6733.98 |  |  |  |  | 8185 |  |  | 2014-08-07 | 2015-07-01 | 2014-11-01 | 2015-04-22
75086 | G7PUBIMP | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 237839.52 |  |  |  |  | 246262.39 |  |  | 2014-08-22 | 2015-06-28 | 2014-12-01 | 2015-08-05
75086 | G7MAINS | P6206 | JT 4940830 Williams Woods Ph 4 | 4723.18 |  |  |  |  | 29895.33 |  |  | 2014-08-27 | 2015-07-01 | 2014-09-01 | 2015-01-13
75086 | G7MAINS | P6292 | JT 5702282 Alson Place Ph 2 | 9043.71 |  |  |  |  | 9970.96 |  |  | 2014-09-10 | 2015-10-15 | 2014-12-01 | 2015-04-16
75086 | G7LGMR | P6323 | Install Mercaptan Meas at Alexandri | 24558.55 |  |  |  |  | 24558.55 |  |  | 2014-09-16 | 2015-06-30 | 2015-01-01 | 2015-06-01
75086 | G7LGMR | P6324 | Install Mercaptan Meas at Cold Spri | 14702.8 |  |  |  |  | 14702.8 |  |  | 2014-09-16 | 2015-06-30 | 2015-01-01 | 2015-08-01
75086 | G7REPL | P6335 | Dudley Rd - Relocation For Rstorm | -372.88 |  |  |  |  | 98221.29 |  |  | 2014-09-19 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7MAINS | P6377 | JT 5666593 Sycamore Creek Ph 2 | 15693.86 |  |  |  |  | 18929.87 |  |  | 2014-09-24 | 2015-09-15 | 2014-12-01 | 2015-04-30
75086 | G7MAINS | P6491 | JT 6339925 Triple Crown Country Clb | 46910.22 |  |  |  |  | 46910.22 |  |  | 2014-10-03 | 2016-03-31 | 2015-02-01 | 2015-07-11
75086 | G7MAINS | P6505 | JT 6381321 Hidden Creek II Ph 3 | 8449.07 |  |  |  |  | 8449.07 |  |  | 2014-10-06 | 2015-12-31 | 2015-04-01 | 2015-08-30
75086 | G7MAINS | P6518 | JT 6193597 Battle Ridge Subd | 12565.27 |  |  |  |  | 12565.27 |  |  | 2014-10-07 | 2015-12-17 | 2015-09-01 | 2016-01-05
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | 23188.27 |  |  |  |  | 36591.03 |  |  | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7PUBIMP | P6551 | Dudley Rd - Relocation for Storm | 66047.16 |  |  |  |  | 75739.94 |  |  | 2014-10-09 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7MAINS | P6610 | JT 5948437 Lakemont 4C Part 4 | 9845.28 |  |  |  |  | 9845.28 |  |  | 2014-10-15 | 2016-02-01 | 2015-06-01 | 2015-10-07
75086 | G7MAINS | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 40707.57 |  |  |  |  | 40707.57 |  |  | 2014-10-16 | 2015-12-20 | 2015-02-01 | 2015-08-09
75086 | G7MAINS | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 53278.63 |  |  |  |  | 53278.63 |  |  | 2014-10-16 | 2015-12-20 | 2015-01-01 | 2015-07-02
75086 | G7MAINS | P6634 | Lauren Dr MEA | 7526.91 |  |  |  |  | 10411.87 |  |  | 2014-10-16 | 2015-08-28 | 2014-11-01 | 2015-03-20
75086 | G7MAINS | P6666 | JT 6479375 Madison Heights | 7607.7 |  |  |  |  | 7607.7 |  |  | 2014-10-22 | 2015-12-27 | 2015-01-01 | 2015-06-11
75086 | G7MAINS | P6672 | JT 6319813 Arcadia Ph B | 15610.6 |  |  |  |  | 15610.6 |  |  | 2014-10-24 | 2015-12-15 | 2015-03-01 | 2015-08-22
75086 | G7IMPRPL | P6709 | Deep Well Erlanger Gas Plant | 532.57 |  |  |  |  | 58740.29 |  |  | 2014-10-31 | 2015-04-27 | 2014-11-01 | 2015-03-10
75086 | G7IMPRPL | P6754 | T/L AM07 - Install Corrosion Monito | 9330.11 |  |  |  |  | 27243.88 |  |  | 2014-11-05 | 2015-11-01 | 2014-12-01 | 2015-10-15
75086 | G7IMPRPL | P6758 | T/L UL02 - Install Corrosion Monito | -46.56 |  |  |  |  | 18430.48 |  |  | 2014-11-05 | 2015-05-30 | 2014-12-01 | 2015-02-28
75086 | G7MAINS | P6772 | JT 6597995 North Walton Pointe | 5054.13 |  |  |  |  | 5054.13 |  |  | 2014-11-07 | 2015-09-10 | 2015-04-01 | 2015-08-08
75086 | G7MAINS | P6888 | 201 Steelman MEA | 21297.07 |  |  |  |  | 21297.07 |  |  | 2014-11-20 | 2015-08-20 | 2015-02-01 | 2015-06-14
75086 | G7MAINS | P7015 | JT 6316270 Ballyshannon Sec 1 | 49571.91 |  |  |  |  | 49571.91 |  |  | 2014-12-11 | 2015-12-16 | 2015-02-01 | 2015-07-14
75086 | G7MAINS | P7141 | Fleet Blvd MEA | 56742.22 |  |  |  |  | 56742.22 |  |  | 2014-12-22 | 2016-09-01 | 2015-07-01 | 2015-11-20
75086 | G7LGMR | P7147 | 4455 Olympic Blvd | 5107.24 |  |  |  |  | 5107.24 |  |  | 2014-12-22 | 2015-06-30 | 2015-01-01 | 2014-11-14
75086 | G7PUBIMP | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 78079.52 |  |  |  |  | 78079.52 |  |  | 2015-01-14 | 2015-09-25 | 2015-02-01 | 2015-06-20
75086 | G7SERVNEW | P7311 | KY SR 63 (ARK Encounter) | 82951.3 |  |  |  |  | 82951.3 |  |  | 2015-01-16 | 2016-02-28 | 2015-05-01 | 2016-03-16
75086 | GITKYCAP | P7638 | Gas Metretek Upgrade | 7787.75 |  |  |  |  | 7787.75 |  |  | 2015-02-05 | 2015-12-31 | 2015-03-01 | 2015-06-24
75086 | G7REPL | P7671 | Y000 - KY Portion - 16" Ohio River | 255254.46 |  |  |  |  | 255254.46 |  |  | 2015-02-09 | 2016-04-30 | 2015-03-01 | 2015-09-26
75086 | G7MAINS | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 14029.69 |  |  |  |  | 14029.69 |  |  | 2015-03-12 09:27 | 2016-01-16 | 2015-05-01 | 2015-09-13
75086 | G7MSCPRD | P8054 | Replace BTU measurement at Erlanger | 48088.62 |  |  |  |  | 48088.62 |  |  | 2015-03-12 14:27 | 2016-04-30 | 2015-07-01 | 2016-01-30
75086 | FKPIAPP | P8060 | Perf Meas App (KPI) - T&D & Gas | 129.05 |  |  |  |  | 129.05 |  |  | 2015-03-12 16:05 | 2016-02-28 | 2015-04-01 | 2016-01-30
75086 | G7MAINS | P9484 | JT 7465123 French Quarter Ph 3D | 11304.96 |  |  |  |  | 11304.96 |  |  | 2015-03-26 11:50 | 2016-02-25 | 2015-06-01 | 2015-10-18
75086 | G7LGMR | P9838 | Erlanger STA 149 | 472276.63 |  |  |  |  | 472276.63 |  |  | 2015-04-02 15:27 | 2016-03-01 | 2015-08-01 | 2016-01-15
75087 | FPIT | PCTA1049C | INT1049 BRNR | 18084.56 |  |  |  |  | 34067.59 |  |  | 2014-10-23 | 2015-07-31 | 2014-11-01 | 2015-10-17
75087 | FPIT | PCTA175BS | PCTA175BS CDS | 3301.38 |  |  |  |  | 3507.78 |  |  | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75087 | FPIT | PCTA481AC | CA Lisa | 27.54 |  |  |  |  | 8249.3 |  |  | 2014-10-21 | 2015-11-30 | 2014-11-01 | 2015-03-31
75087 | FPIT | PCTA481AH | INT481A CDP Hardware Implementation | -1.04 |  |  |  |  | 6448.36 |  |  | 2014-10-23 | 2015-11-30 | 2014-11-01 | 2015-03-31
75087 | FPIT | PCTA481AS | Sitecore | 438565.26 |  |  |  |  | 589221.31 |  |  | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75086 | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 24760.45 |  |  |  |  | 41046.5 |  |  | 2014-07-22 | 2015-07-30 | 2014-07-01 | 2015-12-28
75086 | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | 1558.77 |  |  |  |  | 7366.48 |  |  | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75086 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 204204.87 |  |  |  |  | 204204.87 |  |  | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | FENABLES | PPS | Enable PowerPlan Software | 6512.95 |  |  |  |  | 6512.95 |  |  | 2015-03-30 16:57 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | G7MAINS | Q2231 | JT 7590611 Ashford Village | 3680.42 |  |  |  |  | 3680.42 |  |  | 2015-04-22 11:00 | 2016-02-06 | 2015-09-01 | 2016-01-05
75086 | G7MAINS | Q3775 | 6th St Newport MEA | 25677.64 |  |  |  |  | 25677.64 |  |  | 2015-05-01 09:30 | 2016-02-01 | 2015-10-01 | 2016-04-21
75086 | G7MAINS | Q3776 | JT 7648670 Pond Creek Crossing | 6241.36 |  |  |  |  | 6241.36 |  |  | 2015-05-01 09:37 | 2016-01-15 | 2015-07-01 | 2015-11-01
75086 | G7MAINS | Q8319 | Lacresta Dr MEA | 12538.08 |  |  |  |  | 12538.08 |  |  | 2015-05-15 15:28 | 2016-01-20 | 2015-06-01 | 2015-10-12
75086 | G7MAINS | Q9540 | JT 7724543 Triple Crown | 18086.28 |  |  |  |  | 18086.28 |  |  | 2015-05-26 09:57 | 2016-01-15 | 2015-06-01 | 2015-10-25
75086 | G7MAINS | Q9644 | JT 7716232 Ballyshannon | 24664.65 |  |  |  |  | 24664.65 |  |  | 2015-05-28 07:54 | 2016-01-24 | 2015-07-01 | 2015-10-23
75086 | G7LGMR | Q9751 | STA 149 Hydro Test of AM07 | 328376.67 |  |  |  |  | 328376.67 |  |  | 2015-06-01 15:33 | 2016-04-01 | 2015-07-01 | 2016-01-15
75086 | G7MAINS | R0735 | JT 7988830 Gun Powder Trails | 21078.77 |  |  |  |  | 21078.77 |  |  | 2015-06-24 15:44 | 2016-03-01 | 2015-08-01 | 2015-12-15
75086 | G7MAINS | R0773 | Crown Point Subdivision | 24441.61 |  |  |  |  | 24441.61 |  |  | 2015-06-26 07:02 | 2016-09-30 | 2015-12-01 | 2016-09-02
75086 | G7IMPRPL | R0964 | Replace Banklick Rd Station Inlet P | 312894.43 |  |  |  |  | 312894.43 |  |  | 2015-07-06 15:00 | 2016-09-10 | 2015-07-01 | 2016-08-27
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | 62296.12 |  |  |  |  | 62296.12 |  |  | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7REPL | R1014 | Griffin Industries - UL-27 replacem | 181154.15 |  |  |  |  | 181154.15 |  |  | 2015-07-07 10:38 | 2016-04-15 | 2015-07-01 | 2016-01-10
75086 | G7MAINS | R1468 | Heights Blvd MEA | 25582.24 |  |  |  |  | 25582.24 |  |  | 2015-07-15 13:34 | 2016-07-15 | 2015-08-01 | 2016-03-16
75086 | G7MAINS | R1475 | Cecelia Dr MEA | 20779.7 |  |  |  |  | 20779.7 |  |  | 2015-07-15 14:10 | 2016-07-15 | 2015-09-01 | 2016-01-01
75086 | G7MAINS | R1752 | JT 8164269 Lakemont | 3571.37 |  |  |  |  | 3571.37 |  |  | 2015-07-20 17:33 | 2016-10-30 | 2015-12-01 | 2015-07-02
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 36744.23 |  |  |  |  | 36744.23 |  |  | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7MAINS | R2222 | 826 Elizabeth Dr Florence Ky MEA | 17314.18 |  |  |  |  | 17314.18 |  |  | 2015-08-05 16:31 | 2016-03-18 | 2015-09-01 | 2016-01-05
75086 | G7MAINS | R2247 | JT 8022836 Manhattan Harbour | 7229.13 |  |  |  |  | 7229.13 |  |  | 2015-08-07 09:47 | 2016-04-02 | 2015-09-01 | 2015-12-10
75086 | G7MAINS | R2479 | Regal Ridge Dr MEA | 90497.47 |  |  |  |  | 90497.47 |  |  | 2015-08-13 15:18 | 2016-06-03 | 2015-10-01 | 2016-01-21
75086 | G7MAINS | R2646 | 1418 N. Main St Williamstown MEA | 34154.95 |  |  |  |  | 34154.95 |  |  | 2015-08-26 08:20 | 2016-04-23 | 2015-10-01 | 2015-12-31
75086 | G7MAINS | R2817 | JT 8560406 Shadybrook Bluffs | 1961.45 |  |  |  |  | 1961.45 |  |  | 2015-09-04 08:23 | 2016-08-19 | 2015-12-01 | 2016-05-19
75086 | G7IMPRPL | R2898 | AM01 Exposed F/L Structure Install | 63095.12 |  |  |  |  | 63095.12 |  |  | 2015-09-10 15:41 | 2016-05-02 | 2015-09-01 | 2016-02-02
75086 | G7MAINS | R2915 | JT 8022710 Arcadia | 5467.95 |  |  |  |  | 5467.95 |  |  | 2015-09-11 09:38 | 2016-05-26 | 2015-10-01 | 2016-01-19
75086 | G7MAINS | R3114 | JT 8728425 Triple Crown Sect 32 | 10018.27 |  |  |  |  | 10018.27 |  |  | 2015-09-24 09:07 | 2016-06-14 | 2015-12-01 | 2016-05-18
75086 | G7MAINS | R3315 | Griffen Industries MEA | 19913.39 |  |  |  |  | 19913.39 |  |  | 2015-09-28 09:31 | 2016-04-30 | 2015-10-01 | 2016-01-31
75086 | G7REPL | R3316 | Glencoe - Webster/Railroad St | 7459.31 |  |  |  |  | 7459.31 |  |  | 2015-09-28 09:36 | 2016-04-09 | 2015-10-01 | 2015-12-31
75086 | G7MAINS | R3386 | Mills Rd Drees Homes MEA | 44150.64 |  |  |  |  | 44150.64 |  |  | 2015-09-30 11:50 | 2016-04-29 | 2015-10-01 | 2016-02-12
75086 | G7MAINS | R3391 | Highwater MEA | 3406.45 |  |  |  |  | 3406.45 |  |  | 2015-09-30 14:40 | 2016-06-18 | 2015-11-01 | 2016-03-11
75086 | G7LGMR | R3460 | Station 577 (Ky-17 & US-27) | 177957 |  |  |  |  | 177957 |  |  | 2015-10-05 14:36 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3461 | Station 577 Inlet Piping | 6926.48 |  |  |  |  | 6926.48 |  |  | 2015-10-05 15:02 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3462 | Station 577 Outlet Piping | 3242.82 |  |  |  |  | 3242.82 |  |  | 2015-10-05 15:10 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7MAINS | R3494 | JT 8245984 Orleans North Phase I | 2813.56 |  |  |  |  | 2813.56 |  |  | 2015-10-07 09:11 | 2016-06-21 | 2015-11-01 | 2016-04-04
75086 | G7MAINS | R3798 | JT 8022787 Brigadoon | 4318.96 |  |  |  |  | 4318.96 |  |  | 2015-10-16 14:49 | 2016-07-15 | 2015-12-01 | 2016-03-17
75086 | G7MAINS | R3801 | JT 8022212 Aosta Valley | 6004.04 |  |  |  |  | 6004.04 |  |  | 2015-10-16 14:56 | 2016-07-15 | 2015-11-01 | 2016-04-18
75086 | G7REPL | R4154 | NKU - Sunset Dr Repl | 44085.37 |  |  |  |  | 44085.37 |  |  | 2015-10-30 08:34 | 2016-08-31 | 2015-12-01 | 2016-07-05
75086 | G7MAINS | R4166 | 1513 Woodside Dr MEA | 644.55 |  |  |  |  | 644.55 |  |  | 2015-10-30 11:21 | 2016-07-25 | 2015-12-01 | 2016-05-25
75086 | G7MAINS | R4170 | 5935 Merchants St MEA | 3374.04 |  |  |  |  | 3374.04 |  |  | 2015-10-30 11:39 | 2016-07-18 | 2015-12-01 | 2016-04-20
75086 | G7IMPRPL | R4306 | AM07 Exposed T/L Project | 17971.84 |  |  |  |  | 17971.84 |  |  | 2015-11-09 13:31 | 2016-06-30 | 2015-11-01 | 2016-02-09
75086 | G7REPL | R4407 | RP 9097151 AM-01 at Covington | 169653.26 |  |  |  |  | 169653.26 |  |  | 2015-11-11 12:51 | 2017-03-01 | 2015-11-01 | 2016-02-18
75086 | G7MAINS | R4462 | GM 8830449 Coachlight | 989.75 |  |  |  |  | 989.75 |  |  | 2015-11-13 14:44 | 2016-06-30 | 2015-12-01 | 2016-04-15
75086 | G7REPL | R4609 | RP 8866200 Ripple Creek | 4699.78 |  |  |  |  | 4699.78 |  |  | 2015-11-19 12:28 | 2016-06-18 | 2015-12-01 | 2016-05-20
75086 | G7IMPRPL | R4858 | AM-09 Segment 3700 Main Rpl | 250.04 |  |  |  |  | 250.04 |  |  | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | G7MAINS | R5234 | GO 8623141 Turfway Rd | 2665.61 |  |  |  |  | 2665.61 |  |  | 2015-12-11 14:53 | 2016-07-22 | 2015-12-01 | 2016-05-01
75087 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | -20.59 |  |  |  |  | 164485.04 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75086 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 4112.23 |  |  |  |  | 4112.23 |  |  | 2015-03-30 16:38 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 297526.65 |  |  |  |  | 297526.65 |  |  | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 0 |  |  |  |  | 58164.74 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 5369.5 |  |  |  |  | 5369.5 |  |  | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 534.55 |  |  |  |  | 38094.67 |  |  | 2014-04-28 | 2015-02-15 | 2014-04-01 | 2015-02-17
75086 | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 7342.29 |  |  |  |  | 13003.69 |  |  | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75086 | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 0 |  |  |  |  | 7933.67 |  |  | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75086 | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 5.78 |  |  |  |  | 3322.35 |  |  | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -328.94 |  |  |  |  | 333.85 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | GSMARTK | SMARTKYP1 | Gas Smart Implementation Phase 1 | 244970.62 |  |  |  |  | 307720.12 |  |  | 2014-07-02 | 2017-02-07 | 2014-07-01 | 2016-03-14
75086 | GITKYCAP | SMARTPH2 | Gas Smart Data Availability Phase 2 | 4495.08 |  |  |  |  | 4495.08 |  |  | 2015-12-11 15:15 | 2018-06-30 | 2015-12-01
75086 | FVANKEG | VANKENGAS | Vehicle Area Network | 21135.73 |  |  |  |  | 21135.73 |  |  | 2015-10-09 14:02 | 2017-02-28 | 2015-10-01 | 2016-08-20
75086 | FENABLES | WRTS | Enable WRT & WMSP Software | 21365.64 |  |  |  |  | 21365.64 |  |  | 2015-03-30 16:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2016
Duke Energy Kentucky Gas
Year 2016
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 875.56 |  |  |  |  | 198044.32 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 315263BTS | 315263BTS Encryption PH2 | 3595.43 |  |  |  |  | 3595.43 |  |  | 2016-10-13 15:38 | 2016-12-31 | 2016-10-01 | 2017-04-23
75087 | FPIT | 315263GDG | 315263GDG Encryption PH2 | 4261.93 |  |  |  |  | 4261.93 |  |  | 2016-10-13 12:55 | 2016-12-31 | 2016-11-01 | 2017-06-30
75087 | FPIT | 315263VER | 315263VER Encryption PH2 | 3159.71 |  |  |  |  | 3159.71 |  |  | 2016-10-13 16:23 | 2016-12-31 | 2016-12-01 | 2017-06-30
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 110547.92 |  |  |  |  | 182500.59 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 80494.07 |  |  |  |  | 183385.15 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 407.19 |  |  |  |  | 50255.16 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 42026.26 |  |  |  |  | 207236.08 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 4736.92 |  |  |  |  | 95820.44 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 54872.15 |  |  |  |  | 91369.17 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 11328.15 |  |  |  |  | 47267.2 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 8CMNEW70 | Install New C-M 8" | -1539.3 |  |  |  |  | 39809.86 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVNEW | 8MCNEW70 | Install New M-C 8" | -7083.8 |  |  |  |  | 15423.17 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 166084.65 |  |  |  |  | 245258.15 |  |  | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 1369349.47 |  |  |  |  | 2396729.28 |  |  | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 0.35 |  |  |  |  | 9.02 |  |  | 2015-03-30 16:20 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 77635.8 |  |  |  |  | 94465.82 |  |  | 2015-03-30 16:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 0.28 |  |  |  |  | 7.37 |  |  | 2015-03-30 14:15 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | FENABLES | ARMS | Enable ARM Scheduler Software | 39547.64 |  |  |  |  | 71015.43 |  |  | 2015-03-30 16:26 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | GITKYCAP | BOES | Boes Replacement (AGOES) for Gas | 22862.22 |  |  |  |  | 63280.02 |  |  | 2015-05-01 11:05 | 2016-06-30 | 2015-08-01 | 2017-01-25
75086 | FCF53SKEG | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 4473.34 |  |  |  |  | 4473.34 |  |  | 2014-08-04 | 2017-03-31 | 2016-07-01 | 2017-03-05
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 25757.83 |  |  |  |  | 44301.11 |  |  | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 104398.85 |  |  |  |  | 145320.18 |  |  | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 19312.07 |  |  |  |  | 47380.89 |  |  | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 1275443.69 |  |  |  |  | 5135016.16 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 4950.27 |  |  |  |  | 4950.27 |  |  | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 888018.51 |  |  |  |  | 8682965.83 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | 2" or less steel C-M Replace | 3756.35 |  |  |  |  | 3756.35 |  |  | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 1072854.48 |  |  |  |  | 1261535.26 |  |  | 2015-03-04 11:36 | 2022-12-31 | 2015-07-01
75086 | FEWLANKEG | COVINGTON | Enable WLAN Remediation | 10522.97 |  |  |  |  | 10522.97 |  |  | 2016-02-03 17:41 | 2017-03-31 | 2016-03-01 | 2016-10-10
75086 | GITKYCAP | CPMANGENH | CP Manager Enhancements | 152251 |  |  |  |  | 152251 |  |  | 2016-02-22 14:06 | 2017-03-04 | 2016-03-01 | 2016-12-12
75086 | FENABLEH | ECOMH | Enable ECOM Data Hub | 106.9 |  |  |  |  | 106.9 |  |  | 2015-09-29 10:00 | 2017-10-31 | 2016-01-01 | 2017-11-07
75086 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 24919.32 |  |  |  |  | 28592.44 |  |  | 2015-03-30 16:52 | 2017-10-31 | 2015-05-01 | 2017-11-07
75087 | SGITCS | ECSPH2 | Enterprise Cust systems Ph2 Capital | 0 |  |  |  |  | 0 |  |  | 2011-02-28 | 2015-06-30 | 2011-03-01
75086 | FENABLEH | EGISH | Enable EGIS Hardware | 213.27 |  |  |  |  | 619.16 |  |  | 2015-03-30 15:51 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | EGISS | Enable EGIS Software | 147613.66 |  |  |  |  | 218539.8 |  |  | 2015-03-30 16:42 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | 232589.61 |  |  |  |  | 345923.04 |  |  | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01
75086 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 2.13 |  |  |  |  | 51.22 |  |  | 2015-03-30 14:50 | 2017-10-31 | 2015-08-01 | 2017-11-07
75086 | FENABLES | EXPDS | Enable Expert Designer Software | 49865.51 |  |  |  |  | 80034.43 |  |  | 2015-03-30 16:33 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 39389.54 |  |  |  |  | 44141.41 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | CPERNST2 | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 157977.7 |  |  |  |  | 683163.99 |  |  | 2012-05-22 | 2015-01-15 | 2012-12-01 | 2014-07-01
75086 | G7PUBIMP | G8241 | Sunset Drive - Three Mile Rd Imp | 17040.91 |  |  |  |  | 153857.86 |  |  | 2012-08-16 | 2016-01-31 | 2015-02-01 | 2016-02-05
75086 | G7PUBIMP | G8242 | AM00 - NKU | 206733.22 |  |  |  |  | 1176811.19 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | 53314.83 |  |  |  |  | 53314.83 |  |  | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01
75086 | G7LGMR | H0264 | Reg 118K Inlet & Outlet Piping | -399.94 |  |  |  |  | 80240.04 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0265 | Reg 118K Installation | 6418.16 |  |  |  |  | 208966.68 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0350 | STA 535K1 (UL33 to HP) Modification | 438.6 |  |  |  |  | 23297.23 |  |  | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7REPL | H0383 | REG 117K - Inlet & Outlet Piping | -4760.77 |  |  |  |  | 152422.35 |  |  | 2013-07-05 | 2015-06-30 | 2013-12-01 | 2014-07-24
75086 | G7LGMR | H0384 | Reg 117K-Amsterdam & Redwood | -4687.01 |  |  |  |  | 128065.73 |  |  | 2013-07-05 | 2015-06-30 | 2013-10-01 | 2014-07-24
75086 | G7LGMR | H0485 | Reg 21K Improvements-Grand & Ft Tho | 160942.05 |  |  |  |  | 162220.76 |  |  | 2013-07-29 | 2015-06-30 | 2013-11-01 | 2014-02-11
75086 | G7MAINS | H1364 | Sutter Drive Main Extension | -4.87 |  |  |  |  | 552.36 |  |  | 2013-12-02 | 2014-11-30 | 2015-08-01 | 2015-12-09
75086 | GITKYCAP | H1444 | PCS Upgrade | -119.92 |  |  |  |  | 2844.55 |  |  | 2013-12-11 | 2014-06-30 | 2013-12-01 | 2014-03-31
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 153644.98 |  |  |  |  | 243934.66 |  |  | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 89628.97 |  |  |  |  | 89628.97 |  |  | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | 5059.16 |  |  |  |  | 5059.16 |  |  | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LCMSP70 | ASRP Greater than 2" C-M Install | 808.28 |  |  |  |  | 808.28 |  |  | 2016-01-13 11:25 | 2022-12-31 | 2016-07-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 118827.24 |  |  |  |  | 118827.24 |  |  | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 2017.94 |  |  |  |  | 2017.94 |  |  | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 83837.72 |  |  |  |  | 83837.72 |  |  | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LMCSP70 | ASRP Greater than 2" M-C Replace | 5202.19 |  |  |  |  | 5202.19 |  |  | 2016-01-13 11:21 | 2022-12-31 | 2016-04-01
75086 | G7MSCPRD | M6102 | Replace Compress 6&7 oil lube sys | -879.53 |  |  |  |  | 52782.65 |  |  | 2014-06-11 | 2016-06-30 | 2014-09-01 | 2015-01-14
75086 | G7MSCPRD | M6103 | Erlanger GP Aftercooler Retube | -2530.54 |  |  |  |  | 86537.8 |  |  | 2014-06-11 | 2016-06-30 | 2014-06-01 | 2015-01-21
75086 | GITKYCAP | MAOP7SFTW | Maximum Allowable Operating Pressur | 253010.94 |  |  |  |  | 288960.04 |  |  | 2015-03-12 12:19 | 2016-04-30 | 2015-04-01 | 2016-12-12
75086 | FENABLEH | MAXH | Enable Maximo Hardware | 2194.48 |  |  |  |  | 2688.05 |  |  | 2015-03-30 13:58 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | MAXS | Enable Maximo Software | 506831.72 |  |  |  |  | 740826.63 |  |  | 2015-03-30 16:21 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 2343661.89 |  |  |  |  | 6240540.03 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 19254.83 |  |  |  |  | 138141 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1569790.26 |  |  |  |  | 10316756.86 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 141814.14 |  |  |  |  | 430120.07 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 3261747.13 |  |  |  |  | 3670641.19 |  |  | 2015-03-04 11:18 | 2022-12-31 | 2015-07-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 453409.12 |  |  |  |  | 453409.12 |  |  | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 25469.16 |  |  |  |  | 27494.22 |  |  | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | 268021.07 |  |  |  |  | 369729.6 |  |  | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUBIMP | N8164 | Summit Lane | 34602.93 |  |  |  |  | 136994.83 |  |  | 2014-07-03 | 2015-02-01 | 2014-07-01 | 2014-10-16
75087 | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 13080.63 |  |  |  |  | 13088.22 |  |  | 2015-11-16 14:22 | 2016-09-30 | 2015-12-01 | 2017-03-27
75086 | G7PUBIMP | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 3431.59 |  |  |  |  | 249693.98 |  |  | 2014-08-22 | 2015-06-28 | 2014-12-01 | 2015-08-05
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | 123011.54 |  |  |  |  | 159602.57 |  |  | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7IMPRPL | P6709 | Deep Well Erlanger Gas Plant | -740.33 |  |  |  |  | 57999.96 |  |  | 2014-10-31 | 2015-04-27 | 2014-11-01 | 2015-03-10
75086 | G7IMPRPL | P6754 | T/L AM07 - Install Corrosion Monito | 29583.71 |  |  |  |  | 56827.59 |  |  | 2014-11-05 | 2015-11-01 | 2014-12-01 | 2015-10-15
75086 | G7LGMR | P7279 | Rossford Avenue (STA #101) | 753886.31 |  |  |  |  | 753886.31 |  |  | 2015-01-14 | 2017-02-15 | 2016-04-01 | 2016-12-28
75086 | G7PUBIMP | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | -1259.74 |  |  |  |  | 76819.78 |  |  | 2015-01-14 | 2015-09-25 | 2015-02-01 | 2015-06-20
75086 | G7SERVNEW | P7311 | KY SR 63 (ARK Encounter) | -3944.35 |  |  |  |  | 79006.95 |  |  | 2015-01-16 | 2016-02-28 | 2015-05-01 | 2016-03-16
75086 | G7REPL | P7671 | Y000 - KY Portion - 16" Ohio River | 45658.83 |  |  |  |  | 300913.29 |  |  | 2015-02-09 | 2016-04-30 | 2015-03-01 | 2015-09-26
75086 | G7MSCPRD | P8054 | Replace BTU measurement at Erlanger | 5498.75 |  |  |  |  | 53587.37 |  |  | 2015-03-12 14:27 | 2016-04-30 | 2015-07-01 | 2016-01-30
75086 | FKPIAPP | P8060 | Perf Meas App (KPI) - T&D & Gas | 15.18 |  |  |  |  | 144.23 |  |  | 2015-03-12 16:05 | 2016-02-28 | 2015-04-01 | 2016-01-30
75086 | G7LGMR | P9838 | Erlanger STA 149 | 30673.78 |  |  |  |  | 502950.41 |  |  | 2015-04-02 15:27 | 2016-03-01 | 2015-08-01 | 2016-01-15
75087 | FPIT | PCTA175BS | PCTA175BS CDS | 43574.01 |  |  |  |  | 47081.79 |  |  | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75087 | FPIT | PCTA175L | PCTA175L CDS Licenses | 1886.12 |  |  |  |  | 1886.12 |  |  | 2016-08-01 10:30 | 2016-12-31 | 2016-10-01 | 2017-02-15
75087 | FPIT | PCTA481AS | Sitecore | 566763.56 |  |  |  |  | 1155984.87 |  |  | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75087 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 833298.71 |  |  |  |  | 833298.71 |  |  | 2016-02-11 12:05 | 2018-10-31 | 2016-03-01 | 2018-10-31
75086 | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 7004.74 |  |  |  |  | 48051.24 |  |  | 2014-07-22 | 2015-07-30 | 2014-07-01 | 2015-12-28
75086 | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | -56.27 |  |  |  |  | 7310.21 |  |  | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75086 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 1235606.36 |  |  |  |  | 1439811.23 |  |  | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | PCTA82F | PCTAVS82F | INT82F-EGIS Web Tool | 2878.08 |  |  |  |  | 2878.08 |  |  | 2014-07-22 | 2016-07-30 | 2016-04-01 | 2016-07-31
75086 | FENABLES | PPS | Enable PowerPlan Software | 27928.98 |  |  |  |  | 34441.93 |  |  | 2015-03-30 16:57 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | G7MAINS | Q3775 | 6th St Newport MEA | 12264.78 |  |  |  |  | 37942.42 |  |  | 2015-05-01 09:30 | 2016-02-01 | 2015-10-01 | 2016-04-21
75086 | G7MAINS | Q8319 | Lacresta Dr MEA | -208.43 |  |  |  |  | 12329.65 |  |  | 2015-05-15 15:28 | 2016-01-20 | 2015-06-01 | 2015-10-12
75086 | G7LGMR | Q9751 | STA 149 Hydro Test of AM07 | 141324.03 |  |  |  |  | 469700.7 |  |  | 2015-06-01 15:33 | 2016-04-01 | 2015-07-01 | 2016-01-15
75086 | G7MAINS | R0735 | JT 7988830 Gun Powder Trails | -335.01 |  |  |  |  | 20743.76 |  |  | 2015-06-24 15:44 | 2016-03-01 | 2015-08-01 | 2015-12-15
75086 | G7MAINS | R0738 | JT 7992398 Crown Point | 16590.18 |  |  |  |  | 16590.18 |  |  | 2015-06-24 15:55 | 2017-03-15 | 2016-02-01 | 2016-05-25
75086 | G7MAINS | R0773 | Crown Point Subdivision | 497896.82 |  |  |  |  | 522338.43 |  |  | 2015-06-26 07:02 | 2016-09-30 | 2015-12-01 | 2016-09-02
75086 | G7IMPRPL | R0964 | Replace Banklick Rd Station Inlet P | 263358 |  |  |  |  | 576252.43 |  |  | 2015-07-06 15:00 | 2016-09-10 | 2015-07-01 | 2016-08-27
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | 2017505.06 |  |  |  |  | 2079801.18 |  |  | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7IMPRPL | R0981 | WP23 "AM07" Pressure Test | 828521.39 |  |  |  |  | 828521.39 |  |  | 2015-07-06 16:45 | 2017-02-28 | 2016-02-01 | 2016-10-20
75086 | G7REPL | R1014 | Griffin Industries - UL-27 replacem | 145030.17 |  |  |  |  | 326184.32 |  |  | 2015-07-07 10:38 | 2016-04-15 | 2015-07-01 | 2016-01-10
75086 | G7MAINS | R1468 | Heights Blvd MEA | 36523.05 |  |  |  |  | 62105.29 |  |  | 2015-07-15 13:34 | 2016-07-15 | 2015-08-01 | 2016-03-16
75086 | G7MAINS | R1475 | Cecelia Dr MEA | -83.32 |  |  |  |  | 20696.38 |  |  | 2015-07-15 14:10 | 2016-07-15 | 2015-09-01 | 2016-01-01
75086 | G7MAINS | R1752 | JT 8164269 Lakemont | 24853.63 |  |  |  |  | 28425 |  |  | 2015-07-20 17:33 | 2016-10-30 | 2015-12-01 | 2015-07-02
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 1545519.39 |  |  |  |  | 1582263.62 |  |  | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7MAINS | R2222 | 826 Elizabeth Dr Florence Ky MEA | 214.49 |  |  |  |  | 17528.67 |  |  | 2015-08-05 16:31 | 2016-03-18 | 2015-09-01 | 2016-01-05
75086 | G7MAINS | R2479 | Regal Ridge Dr MEA | 2065.04 |  |  |  |  | 92562.51 |  |  | 2015-08-13 15:18 | 2016-06-03 | 2015-10-01 | 2016-01-21
75086 | G7MAINS | R2646 | 1418 N. Main St Williamstown MEA | 2647.86 |  |  |  |  | 36802.81 |  |  | 2015-08-26 08:20 | 2016-04-23 | 2015-10-01 | 2015-12-31
75086 | G7MAINS | R2817 | JT 8560406 Shadybrook Bluffs | 8282.48 |  |  |  |  | 10243.93 |  |  | 2015-09-04 08:23 | 2016-08-19 | 2015-12-01 | 2016-05-19
75086 | G7IMPRPL | R2898 | AM01 Exposed F/L Structure Install | 140674.2 |  |  |  |  | 203769.32 |  |  | 2015-09-10 15:41 | 2016-05-02 | 2015-09-01 | 2016-02-02
75086 | G7LGMR | R2900 | Cox Rd Station Rpl | 30398.68 |  |  |  |  | 30398.68 |  |  | 2015-09-10 16:08 | 2017-08-01 | 2016-02-01 | 2017-04-11
75086 | G7LGMR | R2901 | STA 838 Mineola Pike - Station | 45225.31 |  |  |  |  | 45225.31 |  |  | 2015-09-10 16:12 | 2018-05-31 | 2016-04-01 | 2018-02-14
75086 | G7MAINS | R2915 | JT 8022710 Arcadia | 1517 |  |  |  |  | 6984.95 |  |  | 2015-09-11 09:38 | 2016-05-26 | 2015-10-01 | 2016-01-19
75086 | G7MAINS | R2925 | JT 8637217 Triple Crown | 15723.83 |  |  |  |  | 15723.83 |  |  | 2015-09-11 10:58 | 2016-08-20 | 2016-01-01 | 2016-06-24
75086 | G7MAINS | R3114 | JT 8728425 Triple Crown Sect 32 | 49489.78 |  |  |  |  | 59508.05 |  |  | 2015-09-24 09:07 | 2016-06-14 | 2015-12-01 | 2016-05-18
75086 | G7MAINS | R3118 | JT 8760245 Triple Crown Sect 29 | 15976.13 |  |  |  |  | 15976.13 |  |  | 2015-09-24 09:23 | 2016-06-28 | 2016-01-01 | 2016-05-31
75086 | G7REPL | R3316 | Glencoe - Webster/Railroad St | 1623.07 |  |  |  |  | 9082.38 |  |  | 2015-09-28 09:36 | 2016-04-09 | 2015-10-01 | 2015-12-31
75086 | G7MAINS | R3386 | Mills Rd Drees Homes MEA | 1380.57 |  |  |  |  | 45531.21 |  |  | 2015-09-30 11:50 | 2016-04-29 | 2015-10-01 | 2016-02-12
75086 | G7MAINS | R3391 | Highwater MEA | 15334.55 |  |  |  |  | 18741 |  |  | 2015-09-30 14:40 | 2016-06-18 | 2015-11-01 | 2016-03-11
75086 | G7LGMR | R3460 | Station 577 (Ky-17 & US-27) | 59208.15 |  |  |  |  | 237165.15 |  |  | 2015-10-05 14:36 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3461 | Station 577 Inlet Piping | -97.56 |  |  |  |  | 6828.92 |  |  | 2015-10-05 15:02 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3462 | Station 577 Outlet Piping | -3.51 |  |  |  |  | 3239.31 |  |  | 2015-10-05 15:10 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7MAINS | R3494 | JT 8245984 Orleans North Phase I | 5987.02 |  |  |  |  | 8800.58 |  |  | 2015-10-07 09:11 | 2016-06-21 | 2015-11-01 | 2016-04-04
75086 | G7MAINS | R3798 | JT 8022787 Brigadoon | 6042.73 |  |  |  |  | 10361.69 |  |  | 2015-10-16 14:49 | 2016-07-15 | 2015-12-01 | 2016-03-17
75086 | G7MAINS | R3801 | JT 8022212 Aosta Valley | 6325.68 |  |  |  |  | 12329.72 |  |  | 2015-10-16 14:56 | 2016-07-15 | 2015-11-01 | 2016-04-18
75086 | G7REPL | R4154 | NKU - Sunset Dr Repl | 44850.6 |  |  |  |  | 88935.97 |  |  | 2015-10-30 08:34 | 2016-08-31 | 2015-12-01 | 2016-07-05
75086 | G7MAINS | R4166 | 1513 Woodside Dr MEA | 26396.59 |  |  |  |  | 27041.14 |  |  | 2015-10-30 11:21 | 2016-07-25 | 2015-12-01 | 2016-05-25
75086 | G7MAINS | R4170 | 5935 Merchants St MEA | 46749.86 |  |  |  |  | 50123.9 |  |  | 2015-10-30 11:39 | 2016-07-18 | 2015-12-01 | 2016-04-20
75086 | G7IMPRPL | R4306 | AM07 Exposed T/L Project | -20.75 |  |  |  |  | 17951.09 |  |  | 2015-11-09 13:31 | 2016-06-30 | 2015-11-01 | 2016-02-09
75086 | G7REPL | R4407 | RP 9097151 AM-01 at Covington | 291898.91 |  |  |  |  | 461552.17 |  |  | 2015-11-11 12:51 | 2017-03-01 | 2015-11-01 | 2016-02-18
75086 | G7MAINS | R4462 | GM 8830449 Coachlight | 12895.32 |  |  |  |  | 13885.07 |  |  | 2015-11-13 14:44 | 2016-06-30 | 2015-12-01 | 2016-04-15
75086 | G7MAINS | R4463 | GM 9001226 Wright Blvd | 27468.57 |  |  |  |  | 27468.57 |  |  | 2015-11-13 15:02 | 2016-08-08 | 2016-02-01 | 2016-06-03
75086 | G7REPL | R4609 | RP 8866200 Ripple Creek | 70227.5 |  |  |  |  | 74927.28 |  |  | 2015-11-19 12:28 | 2016-06-18 | 2015-12-01 | 2016-05-20
75086 | G7IMPRPL | R4858 | AM-09 Segment 3700 Main Rpl | 1458023.26 |  |  |  |  | 1458273.3 |  |  | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | GITKYCAP | R4959 | Rick Analysis Gas Transmission Line | 273.33 |  |  |  |  | 273.33 |  |  | 2015-12-07 16:48 | 2017-01-01 | 2016-04-01 | 2016-12-29
75086 | G7MAINS | R5234 | GO 8623141 Turfway Rd | 67598.71 |  |  |  |  | 70264.32 |  |  | 2015-12-11 14:53 | 2016-07-22 | 2015-12-01 | 2016-05-01
75086 | G7MAINS | R5266 | JT 9122622 Battleridge | 4916.09 |  |  |  |  | 4916.09 |  |  | 2015-12-14 15:36 | 2017-01-31 | 2016-02-01 | 2016-06-16
75086 | G7PUBIMP | R5767 | GO 8346362 KY 9 North recon | 142360.07 |  |  |  |  | 142360.07 |  |  | 2016-01-11 10:41 | 2018-06-01 | 2016-01-01 | 2016-07-12
75086 | G7MAINS | R6359 | GO 9487293 Pat Fanning Way | 73058.45 |  |  |  |  | 73058.45 |  |  | 2016-02-02 10:25 | 2016-10-01 | 2016-02-01 | 2016-07-21
75086 | G7MAINS | R6365 | GO 9487340 Cedar Ln | 27449.74 |  |  |  |  | 27449.74 |  |  | 2016-02-02 10:31 | 2016-12-01 | 2016-03-01 | 2016-07-22
75086 | G7MAINS | R6366 | GO 9609542 Grandview Rd | 79653.52 |  |  |  |  | 79653.52 |  |  | 2016-02-02 10:46 | 2016-12-01 | 2016-02-01 | 2016-07-18
75086 | G7MAINS | R6367 | GO 9487246 Autumn Ln to Low Gap | 317571.85 |  |  |  |  | 317571.85 |  |  | 2016-02-02 10:51 | 2016-10-01 | 2016-02-01 | 2016-08-05
75086 | G7MAINS | R6484 | GO 9694099 208 Vine St | 8089.92 |  |  |  |  | 8089.92 |  |  | 2016-02-04 15:33 | 2016-10-01 | 2016-02-01 | 2016-06-16
75086 | G7MAINS | R6540 | GO 9775945 AA Highway Crossover | 109728.69 |  |  |  |  | 109728.69 |  |  | 2016-02-05 15:35 | 2016-09-30 | 2016-03-01 | 2016-07-29
75086 | G7REPL | R6767 | RPL 9818927 21st St Levee | 362052.7 |  |  |  |  | 362052.7 |  |  | 2016-02-11 13:42 | 2017-04-30 | 2016-06-01 | 2016-12-13
75086 | G7PUBIMP | R6768 | STI 9359472 Robbins Ave | 31437.94 |  |  |  |  | 31437.94 |  |  | 2016-02-11 14:00 | 2016-09-30 | 2016-03-01 | 2016-07-15
75086 | GITKYCAP | R8365 | Gas Fusion Document Classes | 19402.52 |  |  |  |  | 19402.52 |  |  | 2016-03-11 13:41 | 2016-09-30 | 2016-03-01 | 2016-11-23
75086 | G7MAINS | R8374 | GO 9591573 1973 Sarah Lane | 42904.77 |  |  |  |  | 42904.77 |  |  | 2016-03-11 15:38 | 2016-11-13 | 2016-03-01 | 2016-08-19
75086 | G7IMPRPL | R9162 | INT 9146891 Henry Ct & US 27 | 162176.9 |  |  |  |  | 162176.9 |  |  | 2016-03-28 10:17 | 2017-06-30 | 2016-06-01 | 2017-03-01
75086 | GITKYCAP | RISKANSFT | Risk Analysis Software Emergent | 133504.56 |  |  |  |  | 133504.56 |  |  | 2015-12-07 16:24 | 2017-01-01 | 2016-01-01 | 2016-12-29
75086 | G7PUBIMP | S1056 | STI 10177360 Latonia Lakes Str Impr | 95709.69 |  |  |  |  | 95709.69 |  |  | 2016-04-15 16:46 | 2016-10-31 | 2016-04-01 | 2016-09-18
75086 | G7LGMR | S1094 | STA 249: Three Mile - Station | 210792.09 |  |  |  |  | 210792.09 |  |  | 2016-04-18 09:31 | 2020-01-30 | 2016-07-01 | 2017-02-16
75086 | G7MAINS | S2732 | GO 9691430 Sta 836 Inlet Piping | 166792.21 |  |  |  |  | 166792.21 |  |  | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01
75086 | G7MAINS | S2752 | GO 9691542 Sta 836 Outlet Piping | 234646.3 |  |  |  |  | 234646.3 |  |  | 2016-04-29 11:23 | 2018-05-11 | 2016-05-01 | 2016-12-28
75086 | G7PUBIMP | S4545 | STI 10221124 Altavia Ave | 43243.27 |  |  |  |  | 43243.27 |  |  | 2016-05-10 07:49 | 2016-10-31 | 2016-05-01 | 2016-09-14
75086 | G7REPL | S5697 | RPL 10420236 Ft Wright Elem | 1755.86 |  |  |  |  | 1755.86 |  |  | 2016-05-13 08:59 | 2016-10-22 | 2016-05-01 | 2016-10-16
75086 | G7REPL | S6913 | RPL 10348116 Williamstown Exp Main | 22382.27 |  |  |  |  | 22382.27 |  |  | 2016-05-23 09:47 | 2016-11-12 | 2016-07-01 | 2016-12-21
75086 | G7LGMR | S7437 | STA 10565374 Foster Station | 71565.81 |  |  |  |  | 71565.81 |  |  | 2016-06-06 12:25 | 2017-06-30 | 2016-09-01 | 2016-12-09
75086 | G7LGMR | S7568 | STA 822 Cox Rd Outlet | 22723.05 |  |  |  |  | 22723.05 |  |  | 2016-06-08 12:42 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | S7572 | STA 822 Cox Rd Inlet | 52558.51 |  |  |  |  | 52558.51 |  |  | 2016-06-08 12:51 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7PUBIMP | S7874 | STI 4844778 Thomas More Pkwy | 61698.14 |  |  |  |  | 61698.14 |  |  | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7LGMR | S8250 | STA 822 Cox Rd - Station | 106063.06 |  |  |  |  | 106063.06 |  |  | 2016-06-21 14:28 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7MAINS | S8387 | GO 10416501 279 Riverside Pkwy | 18470.94 |  |  |  |  | 18470.94 |  |  | 2016-06-23 15:08 | 2017-01-31 | 2016-06-01 | 2016-10-26
75086 | G7REPL | S8507 | Sta 809 Waterworks Rd Outlet | 1128.72 |  |  |  |  | 1128.72 |  |  | 2016-06-30 10:57 | 2018-12-31 | 2016-10-01
75086 | G7REPL | S8584 | RPL 10117658 Loomis Rd Airport | 4173.73 |  |  |  |  | 4173.73 |  |  | 2016-07-06 10:52 | 2019-04-30 | 2016-08-01
75086 | G7MAINS | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 105029.81 |  |  |  |  | 105029.81 |  |  | 2016-07-12 14:21 | 2017-06-12 | 2016-08-01 | 2016-12-17
75086 | G7PUBIMP | S8820 | STI 10670525 Edgewood & Lyndale | 280125.77 |  |  |  |  | 280125.77 |  |  | 2016-07-20 11:50 | 2017-03-16 | 2016-07-01 | 2016-12-05
75086 | G7MAINS | S8833 | GO 10529464 3876 Burlington Pk | 29062.32 |  |  |  |  | 29062.32 |  |  | 2016-07-21 14:21 | 2017-03-02 | 2016-08-01 | 2016-12-14
75086 | G7MAINS | S8847 | GO 9527853 820 Dolwick Dr | 41433.97 |  |  |  |  | 41433.97 |  |  | 2016-07-25 12:25 | 2017-03-31 | 2016-07-01 | 2017-02-15
75086 | G7MAINS | S9061 | GO 9451838 132 E. Alexandria Pike | 90519.43 |  |  |  |  | 90519.43 |  |  | 2016-08-10 13:33 | 2017-04-30 | 2016-09-01 | 2017-01-12
75086 | G7IMPRPL | S9414 | INT 11119187 AM04 Carntown | 51349.45 |  |  |  |  | 51349.45 |  |  | 2016-08-30 09:53 | 2018-12-16 | 2016-11-01 | 2018-04-15
75086 | G7MAINS | S9476 | GO 10744494 15 Sprial Dr | 167704.48 |  |  |  |  | 167704.48 |  |  | 2016-09-01 09:38 | 2017-04-21 | 2016-09-01 | 2017-02-02
75086 | G7MAINS | S9515 | GO 10692255 236 Wendel H Ford | 49426.72 |  |  |  |  | 49426.72 |  |  | 2016-09-06 10:41 | 2017-04-30 | 2016-10-01 | 2017-02-28
75086 | G7MAINS | S9567 | GO 10865647 9001 US Hwy 42 | 28431.18 |  |  |  |  | 28431.18 |  |  | 2016-09-09 11:32 | 2018-05-30 | 2016-10-01 | 2017-03-14
75086 | G7MAINS | S9584 | GO 10825411 Hawk's Landing | 97788.4 |  |  |  |  | 97788.4 |  |  | 2016-09-12 09:53 | 2017-05-11 | 2016-10-01 | 2017-03-22
75086 | G7LGMR | S9586 | STA 11212247 Erlanger Compressor | 8355.71 |  |  |  |  | 8355.71 |  |  | 2016-09-12 14:54 | 2018-12-31 | 2016-10-01
75086 | G7PUBIMP | S9644 | STI 11229534 Lyndale Rd | 10950.99 |  |  |  |  | 10950.99 |  |  | 2016-09-16 08:49 | 2017-08-28 | 2016-10-01 | 2017-06-15
75086 | G7MAINS | S9655 | GO 10945062 1495 Dolwick | 29269.73 |  |  |  |  | 29269.73 |  |  | 2016-09-16 13:35 | 2017-04-28 | 2016-10-01 | 2017-02-15
75086 | G7MAINS | S9659 | GO 10888391 5905 Merchant St | 3461.47 |  |  |  |  | 3461.47 |  |  | 2016-09-19 09:06 | 2017-08-03 | 2016-12-01 | 2017-05-11
75086 | G7MAINS | S9687 | GO 11090743 1606 Highwater | 2693.65 |  |  |  |  | 2693.65 |  |  | 2016-09-20 10:46 | 2017-06-30 | 2016-10-01 | 2017-03-20
75086 | G7MAINS | S9749 | GO 10916480 2403 Stonewall Tr | 37173.86 |  |  |  |  | 37173.86 |  |  | 2016-09-26 15:59 | 2017-03-15 | 2016-10-01 | 2017-03-08
75086 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 27135.22 |  |  |  |  | 31247.45 |  |  | 2015-03-30 16:38 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 430046.01 |  |  |  |  | 727572.66 |  |  | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SG000358F | SG358CALL | SG 358 - DEE MDM Scale CA Lisa SW | 5272.71 |  |  |  |  | 5272.71 |  |  | 2016-06-17 11:51 | 2017-06-30 | 2016-08-01 | 2017-06-26
75086 | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 58177.44 |  |  |  |  | 58177.44 |  |  | 2016-06-22 12:04 | 2017-06-30 | 2016-06-01 | 2017-06-26
75086 | SG000358F | SG358SGGL | SG 358 - DEE MDM Scale - SGG Licens | 20877.32 |  |  |  |  | 20877.32 |  |  | 2016-06-17 13:43 | 2017-06-30 | 2016-07-01 | 2017-06-26
75086 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 204.3 |  |  |  |  | 204.3 |  |  | 2016-11-01 13:58 | 2018-02-28 | 2016-11-01 | 2018-02-12
75086 | SG000448F | SG448SVR | SG DEE Openway Scale 2016 - Servers | 2120.66 |  |  |  |  | 2120.66 |  |  | 2016-07-14 08:52 | 2017-03-31 | 2016-07-01 | 2017-03-14
75086 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 595.45 |  |  |  |  | 595.45 |  |  | 2016-11-23 11:25 | 2018-12-31 | 2016-11-01
75086 | SGKYCS | SGCSECS | Enterprise Cust systems cap | 0 |  |  |  |  | 1.4552e-11 |  |  | 2010-10-01 | 2014-12-31 | 2010-09-01
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 0 |  |  |  |  | 58164.74 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 1011.54 |  |  |  |  | 6381.04 |  |  | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0 |  |  |  |  | 122795.82 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMMM2C | SG MDM Mass Market 2 - CMS Work | 2696.86 |  |  |  |  | 2699.39 |  |  | 2014-11-03 | 2015-02-15 | 2014-11-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | -2696.86 |  |  |  |  | 35397.81 |  |  | 2014-04-28 | 2015-02-15 | 2014-04-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0 |  |  |  |  | 180397.16 |  |  | 2013-07-12 | 2014-09-30 | 2013-07-01 | 2014-08-19
75086 | SGKYPMO | SGOVH | Grid Solutions Overhead Allocation | 0 |  |  |  |  | 0 |  |  | 2016-01-08 16:28 | 2050-12-31 | 2016-01-01
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -331.15 |  |  |  |  | 2.7 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | GSMARTK | SMARTKYP1 | Gas Smart Implementation Phase 1 | 32520.91 |  |  |  |  | 340241.03 |  |  | 2014-07-02 | 2017-02-07 | 2014-07-01 | 2016-03-14
75086 | GITKYCAP | SMARTPH2 | Gas Smart Data Availability Phase 2 | -3007.01 |  |  |  |  | 1488.07 |  |  | 2015-12-11 15:15 | 2018-06-30 | 2015-12-01
75086 | G7MAINS | T0386 | GO 10848852 5355 Idlewild Rd | 3087.22 |  |  |  |  | 3087.22 |  |  | 2016-11-01 15:01 | 2017-07-31 | 2016-11-01 | 2017-04-03
75086 | G7REPL | T0387 | RPL 11339902 Chesapeake St | 19351.54 |  |  |  |  | 19351.54 |  |  | 2016-11-01 15:08 | 2017-07-06 | 2016-11-01 | 2017-04-09
75086 | G7REPL | T0647 | RPL 11581212 140 Railroad St | 17402.02 |  |  |  |  | 17402.02 |  |  | 2016-11-14 10:54 | 2017-07-31 | 2016-11-01 | 2017-02-14
75086 | G73MILES | T0747 | AM00a Automation of RCV -Alexandria | 8912.87 |  |  |  |  | 8912.87 |  |  | 2016-11-18 11:23 | 2020-01-30 | 2016-12-01
75086 | G7REPL | T1130 | RPL 11859007 Ballyshannon - relocat | -39500 |  |  |  |  | -39500 |  |  | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | FVANKEG | VANKENGAS | Vehicle Area Network | 3697.45 |  |  |  |  | 24833.18 |  |  | 2015-10-09 14:02 | 2017-02-28 | 2015-10-01 | 2016-08-20
75086 | FENABLES | WRTS | Enable WRT & WMSP Software | 49929.66 |  |  |  |  | 71295.3 |  |  | 2015-03-30 16:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2017
Duke Energy Kentucky Gas
Year 2017
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget (a) | Variance in Dollars (a) | Variance as Percent (a) | Percent of Budget (a) | Total Actual Project Cost | Total Budget Project Cost (a) | Variance in Dollars (a) | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 24930.38 |  |  |  |  | 222974.7 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 307482 | Customer Mobile App | 10270.91 |  |  |  |  | 10270.91 |  |  | 2017-05-08 15:22 | 2019-01-31 | 2017-05-01
75087 | FPIT | 315263BTS | 315263BTS Encryption PH2 | 978.22 |  |  |  |  | 4573.65 |  |  | 2016-10-13 15:38 | 2016-12-31 | 2016-10-01 | 2017-04-23
75087 | FPIT | 315263GDG | 315263GDG Encryption PH2 | 117.51 |  |  |  |  | 4379.44 |  |  | 2016-10-13 12:55 | 2016-12-31 | 2016-11-01 | 2017-06-30
75087 | FPIT | 315263VER | 315263VER Encryption PH2 | 49.76 |  |  |  |  | 3209.47 |  |  | 2016-10-13 16:23 | 2016-12-31 | 2016-12-01 | 2017-06-30
75087 | CUSTCONN | 315986A | Customer Connect - Core | 253543.14 |  |  |  |  | 253543.14 |  |  | 2017-08-10 10:55 | 2022-06-30 | 2017-08-01
75087 | CUSTCONN | 315986B | Customer Connect- Analytics | 31123.7 |  |  |  |  | 31123.7 |  |  | 2017-08-10 13:13 | 2018-09-30 | 2017-08-01 | 2018-09-30
75087 | CUSTCONN | 315986C | Customer Connect- CRM | 33804.23 |  |  |  |  | 33804.23 |  |  | 2017-08-10 14:30 | 2019-02-28 | 2017-08-01
75087 | CUSTCONN | 315986D | Customer Connect- Prepaid Advantage | 72617.9 |  |  |  |  | 72617.9 |  |  | 2017-08-10 15:35 | 2019-12-30 | 2017-08-01
75087 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 52361.83 |  |  |  |  | 52361.83 |  |  | 2017-08-11 10:44 | 2020-06-30 | 2017-08-01
75087 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 62871.57 |  |  |  |  | 62871.57 |  |  | 2017-09-05 18:46 | 2018-10-01 | 2017-09-01 | 2018-10-01
75087 | CUSTCONN | 315986QC | CIS-Quality Center Licenses | 2466.28 |  |  |  |  | 2466.28 |  |  | 2017-08-02 08:14 | 2017-12-31 | 2017-07-01 | 2017-10-31
75087 | FPIT | 325480C | Watson Explorer (Replace Omnifind) | 10901.31 |  |  |  |  | 10901.31 |  |  | 2016-11-30 16:55 | 2018-05-31 | 2016-12-01 | 2018-09-08
75086 | FPIT | 336593EGP | Install CISCO Switch | 369.82 |  |  |  |  | 369.82 |  |  | 2017-07-07 16:16 | 2017-11-30 | 2017-08-01 | 2017-11-30
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 9731.26 |  |  |  |  | 216967.34 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 105.06 |  |  |  |  | 95925.5 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 6CMR70 | Replace C-M 6" Kentucky Blanket | 2754.8 |  |  |  |  | 36610.9 |  |  | 2008-07-31 | 2050-12-31 | 2014-05-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 9920.17 |  |  |  |  | 57187.37 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 8MCR70 | Replace M-C 8" and Greater | -3485 |  |  |  |  | 210.39 |  |  | 2010-05-05 | 2050-12-31 | 2013-03-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 119637.97 |  |  |  |  | 364896.12 |  |  | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 1126521.33 |  |  |  |  | 3523250.61 |  |  | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 230.65 |  |  |  |  | 239.67 |  |  | 2015-03-30 16:20 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 73870.98 |  |  |  |  | 168336.8 |  |  | 2015-03-30 16:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 19.96 |  |  |  |  | 27.33 |  |  | 2015-03-30 14:15 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | FENABLES | ARMS | Enable ARM Scheduler Software | 82982.86 |  |  |  |  | 153998.29 |  |  | 2015-03-30 16:26 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | GITKYCAP | BOES | Boes Replacement (AGOES) for Gas | 223.97 |  |  |  |  | 63503.99 |  |  | 2015-05-01 11:05 | 2016-06-30 | 2015-08-01 | 2017-01-25
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 50273.37 |  |  |  |  | 94574.48 |  |  | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 519988.05 |  |  |  |  | 665308.23 |  |  | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 72669.25 |  |  |  |  | 120050.14 |  |  | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 922829.66 |  |  |  |  | 6057845.82 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 14280.69 |  |  |  |  | 19230.96 |  |  | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 2357637.64 |  |  |  |  | 11040603.47 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | 2" or less steel C-M Replace | 11744.46 |  |  |  |  | 15500.81 |  |  | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 1789322.03 |  |  |  |  | 3050857.29 |  |  | 2015-03-04 11:36 | 2022-12-31 | 2015-07-01
75086 | FLKY0251G | DUKETCKYG | Fleet On-Road Vehicles - Gas - KY | 20774.38 |  |  |  |  | 20774.38 |  |  | 2009-08-14 | 2050-12-31 | 2010-06-01
75086 | FLKY0251G | DUKETEKYG | Fleet Off-Road Vehicles - KY | 168272.24 |  |  |  |  | 168272.24 |  |  | 2009-08-14 | 2050-12-31 | 2010-06-01
75086 | FENABLEH | ECOMH | Enable ECOM Data Hub | 407.81 |  |  |  |  | 514.71 |  |  | 2015-09-29 10:00 | 2017-10-31 | 2016-01-01 | 2017-11-07
75086 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 54215.41 |  |  |  |  | 82807.85 |  |  | 2015-03-30 16:52 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | EGISH | Enable EGIS Hardware | 363.02 |  |  |  |  | 982.18 |  |  | 2015-03-30 15:51 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | EGISS | Enable EGIS Software | 274172.11 |  |  |  |  | 492711.91 |  |  | 2015-03-30 16:42 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | -295893.51 |  |  |  |  | 50029.53 |  |  | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01
75086 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 13.83 |  |  |  |  | 65.05 |  |  | 2015-03-30 14:50 | 2017-10-31 | 2015-08-01 | 2017-11-07
75086 | FENABLES | EXPDS | Enable Expert Designer Software | 65286.94 |  |  |  |  | 145321.37 |  |  | 2015-03-30 16:33 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 9413.37 |  |  |  |  | 53554.78 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | G7PUBIMP | G8242 | AM00 - NKU | -1011414.58 |  |  |  |  | 165396.61 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | FPCTAVMKY | G9238 | Vegetation Mgmt Kentucky | -1390.65 |  |  |  |  | -6.1391e-12 |  |  | 2013-01-10 | 2017-08-30 | 2013-01-01 | 2015-02-28
75086 | FPIT | GCTA30062 | INTGO_PI SCADA Data Implementation | 71764.16 |  |  |  |  | 71764.16 |  |  | 2017-08-08 09:43 | 2019-10-30 | 2017-09-01
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | 138204.55 |  |  |  |  | 191519.38 |  |  | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01
75086 | G7LGMR | H0485 | Reg 21K Improvements-Grand & Ft Tho | 4354.55 |  |  |  |  | 166575.31 |  |  | 2013-07-29 | 2015-06-30 | 2013-11-01 | 2014-02-11
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 239782.13 |  |  |  |  | 483716.79 |  |  | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 116272.5 |  |  |  |  | 205901.47 |  |  | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | -6786.25 |  |  |  |  | -1727.09 |  |  | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LCMRS70 | Greater than 2" C-M Steel Replaceme | 8899.09 |  |  |  |  | 8899.09 |  |  | 2017-03-10 10:36 | 2050-12-31 | 2017-09-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 56545.45 |  |  |  |  | 175372.69 |  |  | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 3853.03 |  |  |  |  | 5870.97 |  |  | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 40502.36 |  |  |  |  | 124340.08 |  |  | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | Greater than 2" M-C REPL Steel | 3485 |  |  |  |  | 3485 |  |  | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | GITKYCAP | MAOP7SFTW | Maximum Allowable Operating Pressur | 3303.25 |  |  |  |  | 292263.29 |  |  | 2015-03-12 12:19 | 2016-04-30 | 2015-04-01 | 2016-12-12
75086 | FENABLEH | MAXH | Enable Maximo Hardware | 3238.01 |  |  |  |  | 5926.06 |  |  | 2015-03-30 13:58 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | MAXS | Enable Maximo Software | 561623.77 |  |  |  |  | 1302450.4 |  |  | 2015-03-30 16:21 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 994863.1 |  |  |  |  | 7235403.13 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 43958.47 |  |  |  |  | 182099.47 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 3028308.72 |  |  |  |  | 13345065.58 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 25496.4 |  |  |  |  | 455616.47 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 11567978.2 |  |  |  |  | 15238619.39 |  |  | 2015-03-04 11:18 | 2022-12-31 | 2015-07-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 984557.89 |  |  |  |  | 1437967.01 |  |  | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 70296.48 |  |  |  |  | 97790.7 |  |  | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | 348700.06 |  |  |  |  | 718429.66 |  |  | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7MAINS | MX1470330 | Extending 8" gas main 2085' to feed | 110166.28 |  |  |  |  | 110166.28 |  |  | 2017-10-13 14:01 | 2018-05-28 | 2017-10-01
75086 | G7MAINS | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 8980.59 |  |  |  |  | 8980.59 |  |  | 2017-09-19 10:01 | 2018-05-16 | 2017-10-01 | 2018-02-18
75086 | G7MAINS | MX1990005 | 8001 Veterans Memorial Dr. | 2031.48 |  |  |  |  | 2031.48 |  |  | 2017-10-10 14:01 | 2018-04-28 | 2017-11-01 | 2018-04-03
75086 | G7IMPRPL | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 26641.08 |  |  |  |  | 26641.08 |  |  | 2017-09-11 18:02 | 2019-01-30 | 2017-10-01
75086 | G7REPL | MX1998720 | Safran (Messier Bugatti) Main Rep | -392030.72 |  |  |  |  | -392030.72 |  |  | 2017-10-26 18:02 | 2018-05-01 | 2017-11-01 | 2018-05-20
75086 | G7MAINS | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 7066.93 |  |  |  |  | 7066.93 |  |  | 2017-10-20 10:01 | 2017-11-30 | 2017-11-01 | 2018-04-30
75086 | G7LGMR | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 3721.16 |  |  |  |  | 3721.16 |  |  | 2017-09-22 14:01 | 2018-01-10 | 2017-10-01
75086 | G7LGMR | MX2217911 | STA 863 - GRANDVIEW ROAD | 27825.12 |  |  |  |  | 27825.12 |  |  | 2017-09-22 14:01 | 2019-03-31 | 2017-10-01 | 2018-08-16
75086 | G7LGMR | MX2218039 | INSTALL SCADA EQUIPMENT | 82977.49 |  |  |  |  | 82977.49 |  |  | 2017-09-21 14:01 | 2018-12-31 | 2017-10-01
75086 | G7MAINS | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 4475.45 |  |  |  |  | 4475.45 |  |  | 2017-09-19 14:01 | 2018-01-01 | 2017-10-01 | 2018-04-08
75086 | G7LGMR | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 87783.06 |  |  |  |  | 87783.06 |  |  | 2017-10-06 18:03 | 2019-01-30 | 2017-11-01
75086 | G7LGMR | MX2336558 | STA 865 Southridge Dr | 2793.16 |  |  |  |  | 2793.16 |  |  | 2017-10-18 10:47 | 2018-10-15 | 2017-10-01
75086 | G7IMPRPL | MX6468802 | AM07 Casing 46 Replacement | 1306.27 |  |  |  |  | 1306.27 |  |  | 2017-12-05 14:02 | 2019-01-01 | 2017-12-01
75087 | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 139.42 |  |  |  |  | 13227.64 |  |  | 2015-11-16 14:22 | 2016-09-30 | 2015-12-01 | 2017-03-27
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | 640 |  |  |  |  | 160242.57 |  |  | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7LGMR | P7279 | Rossford Avenue (STA #101) | -482319.5 |  |  |  |  | 271566.81 |  |  | 2015-01-14 | 2017-02-15 | 2016-04-01 | 2016-12-28
75087 | FPIT | PCTA481AS | Sitecore | 14689.87 |  |  |  |  | 1170674.74 |  |  | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75087 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 1593625.32 |  |  |  |  | 2426924.03 |  |  | 2016-02-11 12:05 | 2018-10-31 | 2016-03-01 | 2018-10-31
75086 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 290419.65 |  |  |  |  | 1730230.88 |  |  | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | FENABLES | PPS | Enable PowerPlan Software | 6680.98 |  |  |  |  | 41122.91 |  |  | 2015-03-30 16:57 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | G7IMPRPL | R0964 | Replace Banklick Rd Station Inlet P | 28973.69 |  |  |  |  | 605226.12 |  |  | 2015-07-06 15:00 | 2016-09-10 | 2015-07-01 | 2016-08-27
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | 805872.03 |  |  |  |  | 2885673.21 |  |  | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 9769026.95 |  |  |  |  | 11351290.57 |  |  | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7LGMR | R2901 | STA 838 Mineola Pike - Station | 170601.73 |  |  |  |  | 215827.04 |  |  | 2015-09-10 16:12 | 2018-05-31 | 2016-04-01 | 2018-02-14
75086 | G7MAINS | R3796 | JT 8916678 Freedom Park II | 14281.38 |  |  |  |  | 14281.38 |  |  | 2015-10-16 14:44 | 2017-11-17 | 2017-03-01 | 2017-07-26
75086 | G7REPL | R4154 | NKU - Sunset Dr Repl | 2285.22 |  |  |  |  | 91221.19 |  |  | 2015-10-30 08:34 | 2016-08-31 | 2015-12-01 | 2016-07-05
75086 | G7BIGBON | R4856 | Big Bone 8" IP Main to Richwood | 195481.52 |  |  |  |  | 195481.52 |  |  | 2015-12-02 14:04 | 2018-04-30 | 2017-02-01 | 2017-12-05
75086 | G7IMPRPL | R4858 | AM-09 Segment 3700 Main Rpl | 112017.26 |  |  |  |  | 1570290.56 |  |  | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | G7PUBIMP | R5767 | GO 8346362 KY 9 North recon | 9633.94 |  |  |  |  | 151994.01 |  |  | 2016-01-11 10:41 | 2018-06-01 | 2016-01-01 | 2016-07-12
75086 | G7REPL | R6767 | RPL 9818927 21st St Levee | 242098.37 |  |  |  |  | 604151.07 |  |  | 2016-02-11 13:42 | 2017-04-30 | 2016-06-01 | 2016-12-13
75086 | G7MSCPRD | R8744 | PLNT 10059137 Erlanger Propane | 10.07 |  |  |  |  | 10.07 |  |  | 2016-03-18 09:53 | 2017-05-01 | 2017-02-01
75086 | G7IMPRPL | R9162 | INT 9146891 Henry Ct & US 27 | -383.71 |  |  |  |  | 161793.19 |  |  | 2016-03-28 10:17 | 2017-06-30 | 2016-06-01 | 2017-03-01
75087 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | -686.2 |  |  |  |  | 163798.84 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75086 | GITKYCAP | RISKANSFT | Risk Analysis Software Emergent | -26.37 |  |  |  |  | 133478.19 |  |  | 2015-12-07 16:24 | 2017-01-01 | 2016-01-01 | 2016-12-29
75086 | G7PUBIMP | S1056 | STI 10177360 Latonia Lakes Str Impr | -429.93 |  |  |  |  | 95279.76 |  |  | 2016-04-15 16:46 | 2016-10-31 | 2016-04-01 | 2016-09-18
75086 | G7LGMR | S1094 | STA 249: Three Mile - Station | 122975.62 |  |  |  |  | 333767.71 |  |  | 2016-04-18 09:31 | 2020-01-30 | 2016-07-01 | 2017-02-16
75086 | G7MAINS | S2732 | GO 9691430 Sta 836 Inlet Piping | 9791.61 |  |  |  |  | 176583.82 |  |  | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01
75086 | G7MAINS | S2752 | GO 9691542 Sta 836 Outlet Piping | -632.48 |  |  |  |  | 234013.82 |  |  | 2016-04-29 11:23 | 2018-05-11 | 2016-05-01 | 2016-12-28
75086 | G7REPL | S6913 | RPL 10348116 Williamstown Exp Main | 784.41 |  |  |  |  | 23166.68 |  |  | 2016-05-23 09:47 | 2016-11-12 | 2016-07-01 | 2016-12-21
75086 | G7LGMR | S7568 | STA 822 Cox Rd Outlet | 7115.3 |  |  |  |  | 29838.35 |  |  | 2016-06-08 12:42 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | S7572 | STA 822 Cox Rd Inlet | 15236.79 |  |  |  |  | 67795.3 |  |  | 2016-06-08 12:51 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7PUBIMP | S7874 | STI 4844778 Thomas More Pkwy | 11650.37 |  |  |  |  | 73348.51 |  |  | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7LGMR | S8250 | STA 822 Cox Rd - Station | 57937.73 |  |  |  |  | 164000.79 |  |  | 2016-06-21 14:28 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7REPL | S8375 | STA 838 Mineola Pike - Inlet | 54577.01 |  |  |  |  | 54577.01 |  |  | 2016-06-23 09:04 | 2018-12-30 | 2017-08-01 | 2018-02-14
75086 | G7REPL | S8507 | Sta 809 Waterworks Rd Outlet | 17.96 |  |  |  |  | 1146.68 |  |  | 2016-06-30 10:57 | 2018-12-31 | 2016-10-01
75086 | G7REPL | S8584 | RPL 10117658 Loomis Rd Airport | 23.22 |  |  |  |  | 4196.95 |  |  | 2016-07-06 10:52 | 2019-04-30 | 2016-08-01
75086 | G7PUBIMP | S8820 | STI 10670525 Edgewood & Lyndale | 3069.54 |  |  |  |  | 283195.31 |  |  | 2016-07-20 11:50 | 2017-03-16 | 2016-07-01 | 2016-12-05
75086 | G7MAINS | S8847 | GO 9527853 820 Dolwick Dr | 35856.54 |  |  |  |  | 77290.51 |  |  | 2016-07-25 12:25 | 2017-03-31 | 2016-07-01 | 2017-02-15
75086 | G7PUBIMP | S8867 | STI 10873483 Mt Zion Rd | 280747.38 |  |  |  |  | 280747.38 |  |  | 2016-07-26 13:07 | 2018-11-30 | 2017-01-01
75086 | G7IMPRPL | S9414 | INT 11119187 AM04 Carntown | 3538873.2 |  |  |  |  | 3590222.65 |  |  | 2016-08-30 09:53 | 2018-12-16 | 2016-11-01 | 2018-04-15
75086 | G7MAINS | S9476 | GO 10744494 15 Sprial Dr | 24825.33 |  |  |  |  | 192529.81 |  |  | 2016-09-01 09:38 | 2017-04-21 | 2016-09-01 | 2017-02-02
75086 | G7MAINS | S9515 | GO 10692255 236 Wendel H Ford | -59.47 |  |  |  |  | 49367.25 |  |  | 2016-09-06 10:41 | 2017-04-30 | 2016-10-01 | 2017-02-28
75086 | G7MAINS | S9567 | GO 10865647 9001 US Hwy 42 | 66269.38 |  |  |  |  | 94700.56 |  |  | 2016-09-09 11:32 | 2018-05-30 | 2016-10-01 | 2017-03-14
75086 | G7MAINS | S9584 | GO 10825411 Hawk's Landing | 88421.13 |  |  |  |  | 186209.53 |  |  | 2016-09-12 09:53 | 2017-05-11 | 2016-10-01 | 2017-03-22
75086 | G7LGMR | S9586 | STA 11212247 Erlanger Compressor | 181.72 |  |  |  |  | 8537.43 |  |  | 2016-09-12 14:54 | 2018-12-31 | 2016-10-01
75086 | G7PUBIMP | S9644 | STI 11229534 Lyndale Rd | 182947.69 |  |  |  |  | 193898.68 |  |  | 2016-09-16 08:49 | 2017-08-28 | 2016-10-01 | 2017-06-15
75086 | G7MAINS | S9655 | GO 10945062 1495 Dolwick | 1201.37 |  |  |  |  | 30471.1 |  |  | 2016-09-16 13:35 | 2017-04-28 | 2016-10-01 | 2017-02-15
75086 | G7MAINS | S9659 | GO 10888391 5905 Merchant St | 42139.01 |  |  |  |  | 45600.48 |  |  | 2016-09-19 09:06 | 2017-08-03 | 2016-12-01 | 2017-05-11
75086 | G7MAINS | S9687 | GO 11090743 1606 Highwater | 18282.77 |  |  |  |  | 20976.42 |  |  | 2016-09-20 10:46 | 2017-06-30 | 2016-10-01 | 2017-03-20
75086 | G7MAINS | S9749 | GO 10916480 2403 Stonewall Tr | -36.61 |  |  |  |  | 37137.25 |  |  | 2016-09-26 15:59 | 2017-03-15 | 2016-10-01 | 2017-03-08
75086 | FENABLEH | SDDTH | Enable Subdiv Design Tool Hardware | 13.23 |  |  |  |  | 13.23 |  |  | 2015-03-30 15:28 | 2017-10-31 | 2017-06-01 | 2017-11-07
75086 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 59535.28 |  |  |  |  | 90782.73 |  |  | 2015-03-30 16:38 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 1382003.08 |  |  |  |  | 2109575.74 |  |  | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SGKAMIF | SG169MTRS | SG KY AMI Gas Meters - 169 | 4606581.71 |  |  |  |  | 4606581.71 |  |  | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75086 | SG000358F | SG358CALL | SG 358 - DEE MDM Scale CA Lisa SW | 78.6 |  |  |  |  | 5351.31 |  |  | 2016-06-17 11:51 | 2017-06-30 | 2016-08-01 | 2017-06-26
75086 | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 14355.8 |  |  |  |  | 72533.24 |  |  | 2016-06-22 12:04 | 2017-06-30 | 2016-06-01 | 2017-06-26
75086 | SG000358F | SG358HW18 | SG 358 - MDM Scale Hardware Phase 3 | 59043.76 |  |  |  |  | 59043.76 |  |  | 2017-05-30 17:55 | 2018-09-30 | 2017-06-01 | 2018-08-31
75086 | SG000358F | SG358SGGL | SG 358 - DEE MDM Scale - SGG Licens | 311.21 |  |  |  |  | 21188.53 |  |  | 2016-06-17 13:43 | 2017-06-30 | 2016-07-01 | 2017-06-26
75086 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 16002.68 |  |  |  |  | 16206.98 |  |  | 2016-11-01 13:58 | 2018-02-28 | 2016-11-01 | 2018-02-12
75086 | SG000448F | SG448SVR | SG DEE Openway Scale 2016 - Servers | 249.27 |  |  |  |  | 2369.93 |  |  | 2016-07-14 08:52 | 2017-03-31 | 2016-07-01 | 2017-03-14
75086 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 21721.78 |  |  |  |  | 21721.78 |  |  | 2017-04-24 18:13 | 2018-12-31 | 2017-05-01
75086 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 13378.81 |  |  |  |  | 13974.26 |  |  | 2016-11-23 11:25 | 2018-12-31 | 2016-11-01
75086 | SG000540F | SG540SW | DEE Vehicle Area Network | 3026.84 |  |  |  |  | 3026.84 |  |  | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 0.01 |  |  |  |  | 6381.05 |  |  | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0.07 |  |  |  |  | 122795.89 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 0.07 |  |  |  |  | 35397.88 |  |  | 2014-04-28 | 2015-02-15 | 2014-04-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0.1 |  |  |  |  | 180397.26 |  |  | 2013-07-12 | 2014-09-30 | 2013-07-01 | 2014-08-19
75086 | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 0.04 |  |  |  |  | 68297.26 |  |  | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -2.7 |  |  |  |  | 2.934e-11 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | GITKYCAP | SMARTPH2 | Gas Smart Data Availability Phase 2 | 23.66 |  |  |  |  | 1511.73 |  |  | 2015-12-11 15:15 | 2018-06-30 | 2015-12-01
75086 | G7MAINS | T0386 | GO 10848852 5355 Idlewild Rd | 21912.12 |  |  |  |  | 24999.34 |  |  | 2016-11-01 15:01 | 2017-07-31 | 2016-11-01 | 2017-04-03
75086 | G7REPL | T0387 | RPL 11339902 Chesapeake St | 24526.53 |  |  |  |  | 43878.07 |  |  | 2016-11-01 15:08 | 2017-07-06 | 2016-11-01 | 2017-04-09
75086 | G7LGMR | T0425 | SCAD 11456765 Mineola Pike Sta | 24813.31 |  |  |  |  | 24813.31 |  |  | 2016-11-03 09:31 | 2018-12-01 | 2017-01-01
75086 | G7LGMR | T0645 | STA 839 Richwood Station | 79560.49 |  |  |  |  | 79560.49 |  |  | 2016-11-14 09:37 | 2018-12-28 | 2017-02-01
75086 | G7LGMR | T0646 | STA 835 Walton - Station | 34467.03 |  |  |  |  | 34467.03 |  |  | 2016-11-14 09:54 | 2018-12-01 | 2017-04-01 | 2018-09-06
75086 | G7REPL | T0647 | RPL 11581212 140 Railroad St | 323.49 |  |  |  |  | 17725.51 |  |  | 2016-11-14 10:54 | 2017-07-31 | 2016-11-01 | 2017-02-14
75086 | G7LGMR | T0746 | AM00a Automation of RCV Cold Spring | 173215.39 |  |  |  |  | 173215.39 |  |  | 2016-11-18 11:04 | 2018-12-30 | 2017-02-01
75086 | G73MILES | T0747 | AM00a Automation of RCV -Alexandria | 154222.49 |  |  |  |  | 163135.36 |  |  | 2016-11-18 11:23 | 2020-01-30 | 2016-12-01
75086 | G7BIGBON | T0881 | Big Bone Odorant Station - SCADA | 108899.64 |  |  |  |  | 108899.64 |  |  | 2016-12-01 12:00 | 2018-12-01 | 2017-04-01 | 2018-08-05
75086 | G7REPL | T1130 | RPL 11859007 Ballyshannon - relocat | 39755.61 |  |  |  |  | 255.61 |  |  | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | G7MAINS | T1131 | GO 11485457 1962 SARAH LN; | 28532.48 |  |  |  |  | 28532.48 |  |  | 2016-12-20 12:02 | 2017-07-01 | 2017-01-01 | 2017-05-15
75086 | G7MAINS | T1135 | GO 11648289 1099 KEATING DR COLD S | 12528.78 |  |  |  |  | 12528.78 |  |  | 2016-12-20 12:13 | 2017-07-01 | 2017-02-01 | 2017-05-22
75086 | G73MILES | T1437 | STA 249: Three Mile Rd | 610745.8 |  |  |  |  | 610745.8 |  |  | 2017-01-05 11:19 | 2018-06-01 | 2017-01-01
75086 | G7LGMR | T1465 | STA 855 Taylor Mill Rd - Station | 69936.98 |  |  |  |  | 69936.98 |  |  | 2017-01-06 16:24 | 2018-04-19 | 2017-03-01 | 2018-04-24
75086 | G7LGMR | T1485 | STA 855 Taylor Mill Rd - Inlet | 16747.95 |  |  |  |  | 16747.95 |  |  | 2017-01-09 11:13 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7LGMR | T1486 | STA 855 Taylor Mill Rd - Outlet | 7961.18 |  |  |  |  | 7961.18 |  |  | 2017-01-09 11:23 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7IMPRPL | T1525 | AM02 Exposed Main in Southgate, KY | 105870.05 |  |  |  |  | 105870.05 |  |  | 2017-01-12 09:24 | 2018-09-30 | 2017-01-01
75086 | G7MAINS | T1715 | GO 11582821 2400 Litton Ln | 75914.62 |  |  |  |  | 75914.62 |  |  | 2017-01-25 09:05 | 2018-04-15 | 2017-03-01 | 2017-09-02
75086 | G7MAINS | T1737 | GO 11797721 Matinee Blvd | 37889.3 |  |  |  |  | 37889.3 |  |  | 2017-01-25 13:07 | 2017-12-06 | 2017-02-01 | 2017-10-07
75086 | G7REPL | T1796 | Showcase AM07 | -514972.06 |  |  |  |  | -514972.06 |  |  | 2017-01-27 15:35 | 2018-12-31 | 2017-01-01 | 2018-08-09
75086 | G7LGMR | T2218 | STA 838 Mineola Pike - Outlet | 10414.05 |  |  |  |  | 10414.05 |  |  | 2017-02-15 15:45 | 2018-08-31 | 2017-05-01 | 2008-02-14
75086 | G7REPL | T2230 | RPL 20745900 Hudson Ave | -49319.64 |  |  |  |  | -49319.64 |  |  | 2017-02-16 14:11 | 2018-03-31 | 2017-02-01 | 2017-09-28
75086 | G7MAINS | T2639 | GO 20629592 89 Mel Lawn Dr | 3380.57 |  |  |  |  | 3380.57 |  |  | 2017-03-03 07:16 | 2017-11-30 | 2017-03-01 | 2017-06-29
75086 | G7PUINEW | T2904 | MTR 11540114 1 Carbon Way | 2064.02 |  |  |  |  | 2064.02 |  |  | 2017-03-08 13:44 | 2018-12-31 | 2017-12-01
75086 | G7LGMR | T4002 | STA 20933317 Erlanger CP | 2393.38 |  |  |  |  | 2393.38 |  |  | 2017-03-17 11:42 | 2018-12-30 | 2017-08-01
75086 | G73MILES | T4422 | AM07 Barleycorns | 72640.26 |  |  |  |  | 72640.26 |  |  | 2017-03-22 16:39 | 2020-03-31 | 2017-04-01
75086 | G7LGMR | T4893 | Mineola Pike STA Meter Rep & Panels | 33460.43 |  |  |  |  | 33460.43 |  |  | 2017-03-28 11:26 | 2018-12-30 | 2017-05-01
75086 | G7LGMR | T5473 | SCAD 21012299 Pressure Transmiitter | 47382.04 |  |  |  |  | 47382.04 |  |  | 2017-03-31 07:27 | 2018-12-01 | 2017-06-01
75086 | G7MAINS | T7104 | GO 11376429 Lot 14 Norbotten Dr | 24076.03 |  |  |  |  | 24076.03 |  |  | 2017-04-13 10:28 | 2018-02-28 | 2017-05-01 | 2017-10-05
75086 | G7IMPRPL | T7752 | AM07 Grey Stable Ln | 73105.68 |  |  |  |  | 73105.68 |  |  | 2017-05-01 16:13 | 2018-09-15 | 2017-05-01 | 2018-06-15
75086 | G7LGMR | T7778 | SCAD 21153712 KY | 421.46 |  |  |  |  | 421.46 |  |  | 2017-05-03 08:00 | 2018-06-29 | 2017-05-01
75086 | G7LGMR | T7966 | STA 859 Banklick Rd - Station | 4318.49 |  |  |  |  | 4318.49 |  |  | 2017-05-10 15:15 | 2018-07-01 | 2017-09-01 | 2018-07-17
75086 | G7MAINS | T8147 | GO 21080428 Beech Dr. | 22296.38 |  |  |  |  | 22296.38 |  |  | 2017-05-22 14:58 | 2018-04-14 | 2017-07-01 | 2017-12-11
75086 | G7REPL | T8295 | RPL 21421581 Latonia Lakes | 208485.17 |  |  |  |  | 208485.17 |  |  | 2017-05-30 16:11 | 2018-03-30 | 2017-06-01 | 2017-10-15
75086 | G7PUBIMP | T8343 | STI 20956764 Weaver Rd. | 49048.27 |  |  |  |  | 49048.27 |  |  | 2017-05-31 13:21 | 2018-05-01 | 2017-07-01 | 2017-11-29
75086 | G7LGMR | T8405 | WALTON-NICHOLS AM03 RCV Valve | 514.27 |  |  |  |  | 514.27 |  |  | 2017-06-02 11:04 | 2019-04-20 | 2017-06-01
75086 | G7LGMR | T9338 | STA 809 Waterworks Dr - Station | 16683.62 |  |  |  |  | 16683.62 |  |  | 2017-07-14 10:03 | 2018-09-01 | 2017-09-01
75086 | FENABLEH | WRTH | Enable WRT & WMSP Hardware | 16.54 |  |  |  |  | 16.54 |  |  | 2015-03-30 14:39 | 2017-10-31 | 2017-06-01 | 2017-11-07
75086 | FENABLES | WRTS | Enable WRT & WMSP Software | 78014.83 |  |  |  |  | 149310.13 |  |  | 2015-03-30 16:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level