## Schedule 18_As of Nov 30, 2017
DUKE ENERGY KENTUCKY
CASE NO. 2018-00261
CONSTRUCTION WORK IN PROGRESS - PERCENT COMPLETE
AS OF NOVEMBER 30, 2017
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (H/G)
1 | 107GASCK | 2008-07-01 | 2050-12-31 | 22.15% | 0 | 0 | 213514.651 | 0
2 | 307482 | 2017-05-01 | 2019-01-31 | 33.28% | 19937 | 19937 | 6598.39 | 33.1%
3 | 315986A | 2017-08-01 | 2022-06-30 | 6.745% | 2325960.3 | 2325960.3 | 240067.63 | 10.32%
4 | 315986B | 2017-08-01 | 2018-09-30 | 28.47% | 69801.07 | 69801.07 | 30578 | 43.81%
5 | 315986C | 2017-08-01 | 2019-02-28 | 21.01% | 187946.4 | 187946.4 | 33218.89 | 17.67%
6 | 315986D | 2017-08-01 | 2019-12-30 | 13.73% | 280416.54 | 280416.54 | 71367.73 | 25.45%
7 | 315986E | 2017-08-01 | 2020-06-30 | 11.37% | 117210.08 | 117210.08 | 51460.39 | 43.9%
8 | 315986HW1 | 2017-09-01 | 2018-10-01 | 22.78% | 43856 | 43856 | 1027.13 | 2.342%
9 | 325480C | 2016-12-01 | 2018-05-31 | 66.67% | 12926.83 | 12926.83 | 9070.32 | 70.17%
10 | DUKETCKYG | 2010-06-01 | 2050-12-31 | 18.48% | 40000 | 40000 | 20774.38 | 51.94%
11 | DUKETEKYG | 2010-06-01 | 2050-12-31 | 18.48% | 20000 | 20000 | 168272.24 | 841.4%
12 | ENABLETDG | 2015-05-01 | 2018-10-01 | 75.58% | 511967.66 | 511967.66 | 56971.22 | 11.13%
13 | G0224 | 2010-08-01 | 2018-10-01 | 89.78% | 99 | 99 | 53234.47 | 53772%
14 | GASKYIND | 2008-07-01 | 2020-12-31 | 75.32% | 0 | 0 | 73.54 | 0
15 | GCTA30062 | 2017-09-01 | 2019-10-30 | 11.41% | 133026 | 133026 | 71334.93 | 53.62%
16 | GSMRTLKSV | 2016-09-01 | 2018-03-31 | 78.99% | 136600 | 136600 | 182700.21 | 133.7%
17 | MX1470330 | 2017-10-01 | 2018-05-28 | 25.1% | 65934.9 | 65934.9 | 19232.96 | 29.17%
18 | MX1605362 | 2017-10-01 | 2018-05-16 | 26.43% | 46919.8 | 21108.51 | 2366.57 | 11.21%
19 | MX1990005 | 2017-11-01 | 2018-04-28 | 16.29% | 7192.72 | 7192.72 | 1097.6 | 15.26%
20 | MX1996777 | 2017-10-01 | 2018-08-17 | 18.75% | 436474.83 | 436474.83 | 12057.92 | 2.763%
21 | MX1998720 | 2017-11-01 | 2018-05-01 | 16.02% | 436546.75 | 436546.75 | -393092.75 | -90.05%
22 | MX2009109 | 2017-11-01 | 2017-11-30 | 100% | 98238.64 | 50913.96 | 851.86 | 1.673%
23 | MX2217622 | 2017-10-01 | 2018-01-10 | 59.41% | 87907.04 | 87907.04 | 3721.16 | 4.233%
24 | MX2217911 | 2017-10-01 | 2019-03-31 | 10.99% | 199415.83 | 199415.83 | 27016 | 13.55%
25 | MX2218039 | 2017-10-01 | 2018-12-31 | 13.16% | 43953.52 | 43953.52 | 82481.19 | 187.7%
26 | MX2272964 | 2017-10-01 | 2018-01-01 | 65.22% | 55272.86 | 30707.14 | 4439.23 | 14.46%
27 | MX2335804 | 2017-11-01 | 2019-01-30 | 6.374% | 175814.08 | 4268942.56 | 33244.85 | 0.7788%
28 | MX2336558 | 2017-10-01 | 2018-10-15 | 15.83% | 43953.52 | 77053.44 | 2776.45 | 3.603%
29 | OMGPCVNTN | 2012-08-01 | 2051-03-31 | 13.79% | 0 | 0 | 225 | 0
30 | OMGPNWPRT | 2012-08-01 | 2051-03-31 | 13.79% | 0 | 0 | 270 | 0
31 | PCTA481AU | 2016-03-01 | 2018-10-31 | 65.61% | 807214 | 807214 | 2405094.66 | 298%
32 | R2190 | 2015-10-01 | 2018-05-28 | 81.55% | 8880548.59 | 25488221 | 10443629.19 | 40.97%
33 | R2901 | 2016-04-01 | 2018-05-31 | 76.96% | 209397.6 | 209397.6 | 139392.99 | 66.57%
34 | R5767 | 2016-01-01 | 2018-06-01 | 79.25% | 335536.03 | 335536.03 | 160402.99 | 47.8%
35 | R8744 | 2017-02-01 | 2017-05-01 | 100% | 56003.95 | 0 | 10.01 | 0
36 | S1094 | 2016-07-01 | 2020-01-30 | 39.53% | 197894.45 | 197894.45 | 331460.05 | 167.5%
37 | S2732 | 2016-05-01 | 2018-12-11 | 60.59% | 91976.45 | 91976.45 | 176583.82 | 192%
38 | S8375 | 2017-08-01 | 2018-12-30 | 23.45% | 25054.56 | 33588.96 | 14359.19 | 42.75%
39 | S8507 | 2016-10-01 | 2018-12-31 | 51.77% | 11917.68 | 11917.68 | 1146.68 | 9.622%
40 | S8584 | 2016-08-01 | 2019-04-30 | 48.5% | 430743.36 | 430743.36 | 4196.95 | 0.9744%
41 | S8867 | 2017-01-01 | 2018-11-30 | 47.71% | 447690.24 | 447690.24 | 277635.35 | 62.02%
42 | S9414 | 2016-11-01 | 2018-12-16 | 50.84% | 1498750.37 | 1498750.37 | 3535642.33 | 235.9%
43 | S9586 | 2016-10-01 | 2018-12-31 | 51.77% | 28706.06 | 28706.06 | 8537.43 | 29.74%
44 | SG358HW18 | 2017-06-01 | 2018-09-30 | 37.45% | 57585 | 57585 | 11197.21 | 19.44%
45 | SG489SVRS | 2017-05-01 | 2018-12-31 | 34.98% | 31329.67 | 31329.67 | 19933.46 | 63.62%
46 | SG489SW | 2016-11-01 | 2018-12-31 | 49.87% | 16065.37 | 16065.37 | 13634.1 | 84.87%
47 | SG540SW | 2017-04-01 | 2020-12-17 | 17.92% | 107801 | 107801 | -849.78 | -0.7883%
48 | SMARTPH2 | 2015-12-01 | 2018-06-30 | 77.49% | 0 | 0 | 1511.73 | 0
49 | T0425 | 2017-01-01 | 2018-12-01 | 47.64% | 55991.76 | 55991.76 | 23752.55 | 42.42%
50 | T0645 | 2017-02-01 | 2018-12-28 | 43.45% | 157154.88 | 157154.88 | 44296.42 | 28.19%
51 | T0646 | 2017-04-01 | 2018-12-01 | 39.9% | 157154.88 | 157154.88 | 34260.87 | 21.8%
52 | T0746 | 2017-02-01 | 2018-12-30 | 43.33% | 123992.64 | 380490 | 168381.36 | 44.25%
53 | T0747 | 2016-12-01 | 2020-01-30 | 31.52% | 123992.64 | 415030 | 143082.62 | 34.48%
54 | T0881 | 2017-04-01 | 2018-12-01 | 39.9% | 351251.52 | 351251.52 | 107341.27 | 30.56%
55 | T1437 | 2017-01-01 | 2018-06-01 | 64.53% | 488958.88 | 15406228 | 603244.66 | 3.916%
56 | T1465 | 2017-03-01 | 2018-04-19 | 66.18% | 47402.5 | 83246.98 | 57974.47 | 69.64%
57 | T1485 | 2017-09-01 | 2018-04-19 | 39.13% | 8058.91 | 23969.47 | 6849.39 | 28.58%
58 | T1486 | 2017-09-01 | 2018-04-19 | 39.13% | 7449.31 | 18239.23 | 6939.89 | 38.05%
59 | T1525 | 2017-01-01 | 2018-09-30 | 52.28% | 79248 | 351129.6 | 75456.74 | 21.49%
60 | T1796 | 2017-01-01 | 2018-12-31 | 45.68% | 3379471.9 | 3379471.9 | -512820.47 | -15.17%
61 | T2218 | 2017-05-01 | 2018-08-31 | 43.74% | 26273.76 | 23225.76 | 10351.76 | 44.57%
62 | T4002 | 2017-08-01 | 2018-12-30 | 23.45% | 31943.04 | 31943.04 | 2379.06 | 7.448%
63 | T4422 | 2017-04-01 | 2020-03-31 | 22.19% | 190195.2 | 190195.2 | 72205.79 | 37.96%
64 | T4893 | 2017-05-01 | 2018-12-30 | 35.03% | 119176.8 | 119176.8 | 31153.97 | 26.14%
65 | T5473 | 2017-06-01 | 2018-12-01 | 33.21% | 91500.96 | 91500.96 | 47382.04 | 51.78%
66 | T7752 | 2017-05-01 | 2018-09-15 | 42.43% | 183855.36 | 183855.36 | 66189.55 | 36%
67 | T7778 | 2017-05-01 | 2018-06-29 | 50.24% | 165811.2 | 165811.2 | 418.94 | 0.2527%
68 | T7966 | 2017-09-01 | 2018-07-01 | 29.7% | 80040.48 | 80040.48 | 4292.66 | 5.363%
69 | T8405 | 2017-06-01 | 2019-04-20 | 26.45% | 200924.16 | 200924.16 | 511.2 | 0.2544%
70 | T9338 | 2017-09-01 | 2018-09-01 | 24.66% | 116006.88 | 116006.88 | 16583.84 | 14.3%
71 | Blank Project ID | 0 | 0 | 0 | 0 | 0 | 17430.6 | 0
19578129.701