## Summary
DUKE ENERGY KENTUCKY, INC.
CASE NO. 2018-00261
Duke Enegy Kentucky, Inc.
Calculation of Capital Construction Project Slippage Factor
Source: Schedule 13a - Construction Projects
(in millions)
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2008 | 31.4 | 32.9 | 1.5 | 4.559% | 95.44%
2009 | 31.4 | 33.7 | 2.3 | 6.825% | 93.18%
2010 | 19.3 | 24.8 | 5.5 | 22.18% | 77.82%
2011 | 13.2 | 12.7 | -0.5 | -3.937% | 103.9%
2012 | 18.2065 | 18 | -0.20648 | -1.147% | 101.1%
2013 | 9.2529 | 9 | -0.25291 | -2.81% | 102.8%
2014 | 8.38 | 14.2184 | 5.8384 | 41.06% | 58.94%
2015 | 12.8486 | 14.0891 | 1.2405 | 8.805% | 91.2%
2016 | 31.9527 | 21.9639 | -9.9889 | -45.48% | 145.5%
2017 | 49.5945 | 43.8306 | -5.7639 | -13.15% | 113.2%
10-Year Average Slippage | 225.5351 | 225.2019 | -0.33329 | -0.148% | 100.1%
Costs include AFUDC - Debt
Explanations for slippage factors in certain years, as requested:
2010 - Lower Customer Adds and project delays
2014 - Postponed East Work project, lower IT spend and lower customer adds
2016 - Higher than anticipated customer adds and integrity management partially offset accelerated service replacement project
2017 - Higher than anticipated service replacements offset by a delay in AMI meter deployment