## Budget Calendar (hidden)
PROPOSED 2013 BUDGET CALENDAR OF EVENTS
|  | Event | Responsible | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Deliverables
| 1 | (1) Reforecast '2012 (2) Prepare '2013 Margin Models (3) Forecast '2013-2015 | Planning/Finance & Rates VPs | Feb: 15; Mar: 1-30 | Update 3 year regulatory forecast and timelines
| 2 | Review Forecast with Business Units | Planning/Finance & Rates VPs | Apr: 2-23 | Review with Reg & NonReg. Make additional revisions as needed.
| 3 | 2nd Qtr QPR | All | Apr: 17
| 4 | Develop 2013 Company Targets | Exec Mgmt/Planning | Apr: 27; May: 4 | Based on Updated 2013 Forecast for Reg, NonReg & SSU
| 5 | Gather Budget Assumptions | Planning/SSU, etc. | Apr: 27; May: 18 | Meet with each Department to discuss and gather FY 2013 Budget parameters (benefits, tax, interest rates, dividends, etc.)
| 6 | Distribute Budget Targets | Exec Mgmt/Field/Planning | May: 7 | Discuss BU Jurisdictional Spending Targets for O&M and Capital
| 7 | SSU Kickoff (System open for SSU) | SSU/Planning | May: 14 | PlanIt System Available
| 8 | Input Budget Assumptions into PlanIt | Planning | May: 1-21 | Bill Print Fees, Collection Rates,Tax Rates, etc.
| 9 | Budgets Open for Field Data Entry | All | May: 21
| 10 | First Draft - SSU Budgets due | SSU's | [8 empty] | Initial draft due to support BU rollup | bar: Jun
| 11 | Second Draft - SSU Budgets due | SSU's | Jun: 8 | Semi-final draft achieving SSU departmental targets
| 12 | Review of SSU Budgets | SSU Personnel | Jun: 2-12 | Finalize SSU Budgets Achieving Departmental Targets
| 13 | Draft of BU Budgets Due | BU Officers | Jun: 15 | 2013 O&M and Capital Budgets; Income Statement Budget. Version to be presented to Management Committee the week of June 25th
| 14 | SSU Budget Reviews | Exec Mgmt/Dept VPs | Jun: 25 | Finalize SSU Budgets
| 15 | Reg BU Budget Reviews in Dallas | Exec Mgmt/SVP Ops/BU Officers/Planning | Jun: 26-27 | Review 2013 Budgets & Operating Plans
| 16 | Non-Reg Budget Reviews in Dallas | Non-Utility Officers, Planning | Jun: 28 | Review 2013 Budgets & Departmental Plans
| 17 | 3rd Qtr QPR | All | Jul: 26
Big Event | 18 | BU Budget Reviews in Dallas (this is a follow-up meeting as needed) | BU Officers/Planning/Mgmt Committee/Non-Utility Officers | Jul: 25-27 | BU's present Budgets, Review Rates & Earnings Strategies; Review Consolidated Corporate Plan; Major Capital Projects; Metrics
| 19 | Final Draft of Reg/Non-Reg Plans | Finance VP's | Jul: 30 | Final draft achieving all targets; Basis for Management Committee Presentation. Includes 2013 Annual Budget and 5 Year Plan.
| 20 | Send Final Board Package | Planning/CFO/Corp Secretary | Sep: 11
Big Event | 21 | Present Budget & Plan to the Board of Directors | Exec Mgmt/Atmos BOD | Sep: 20-22 | Approved Strategic Plan and 2013 Budget
| 22 | Measurement Date - FAS 87 & 106 | Towers Perrin/Human Resources | Sep: TBD | Other benefits expense assumptions received prior to budget

## 2019 Budget Calendar
2019 BUDGET CALENDAR OF EVENTS - Tentative and Preliminary
|  | Event | Responsible | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Deliverables
| 1 | (1) Reforecast '2018 (2) Prepare '2019 Margin Models (3) Forecast '2019-2023 | Planning/Division Finance & Rates VPs | Feb: 1-28; Mar: 1-30; Apr: 1-27 | Update 3-5 year regulatory forecast and timelines by jurisdiction
| 2 | Pre-Budget Meeting with Division Finance | Planning & Division Finance | Mar: TBD | Review key budget issues and assumptions
| 3 | 2nd Qtr QPR | All | Apr: 25
| 4 | Develop Initial 2019 Company Targets | Exec Mgmt/Planning | Feb: 1-28; Mar: 1-30; Apr: 1-27 | Based on Updated 2018 Forecast for Operations & SSU
| 5 | Gather & Input Budget Assumptions | Planning/SSU, etc. | Apr: 16; May: to 11 | Discuss and gather FY 2019 Budget Assumptions from SME's
| 6 | Distribute Budget Targets | Business Units, Planning | May: Mid-May | Distribute BU Jurisdictional Spending Targets for Capital and O&M
| 7 | Budget System Open for SSU Data Entry | SSU/Planning | May: 29 | Budget System Available for Data Entry by SSU Departments.
| 8 | Budget System Open for BU Data Entry | All | May: 29 | Budget System formally Available for BU Data Entry
| 9 | Initial Draft - SSU Budgets due | SSU's | Jun: 14 | Initial draft due to support BU budget rollups | 2017-06-15
| 10 | Final Draft - SSU Budgets due in System | SSU's | Jun: 21 | Final SSU Budgets Due | 2018-06-21
| 11 | Final (Presentation) Draft of BU Budgets Due | BU Officers | Jun: 28 | 2019 O&M and Capital Budgets; Income Statement Budget. Version to be presented to Management Committee during Budget Review | 2018-06-28
| 12 | SSU Budget Reviews in Dallas | Exec Mgmt/Dept VPs/Planning | Jul: 9 | Management Committee Review of 2019 SSU Departmental Budgets | 2018-07-09
| 13 | Operations Budget Reviews in Dallas | Exec Mgmt, BU's, Planning | Jul: 10 | Review of Business Unit FY 2019 Capital and Operating Budgets | 2018-07-10
Big Event | 14 | BU Budget Reviews in Dallas (As Needed) | BU Officers/Planning/Mgmt Committee | Jul: 11 | Follow ups with BU's and/or Executive Management in AM as needed | 2018-07-11
| 15 | 3rd Qtr QPR |  | Jul: 12
| 16 | Final Version of Detailed Budgets in System | Finance VP's | Jul: 27 | Final budget in system achieving Management Committee budget review directives; Basis for Management Committee Sept. Board Presentation. | 2018-07-27
| 17 | Review Board Package and Support | CFO, Mgmt. Comm., VP Strat Planning, Planning Group | Jul: 30; Aug: to 31 | Preparation review of Board package and supporting documentation
| 18 | Send Final Board Package to BOD | Planning/CFO/Corp Secretary | Sep: 7 |  | 2018-09-07
Big Event | 19 | Present Budget & Plan to the Board of Directors | Exec Mgmt/Atmos BOD | Sep: 18-21 | Board Approval of FY 2019 Capital and Operating Budgets
| 20 | Measurement Date - FAS 87 & 106 | Towers Perrin/Human Resources | Sep: TBD | Other benefits expense assumptions received prior to budget

## 2017 Budget Calendar (2) (hidden)
2017 BUDGET CALENDAR OF EVENTS - Tentative and Preliminary
|  | Event | Responsible | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Deliverables
| 1 | (1) Reforecast '2016 (2) Prepare '2017 Margin Models (3) Forecast '2017-2021 | Planning/Division Finance & Rates VPs | Feb: 1-29; Mar: 1-31; Apr: 1-29 | Update 3-5 year regulatory forecast and timelines by jurisdiction
| 2 | Pre-Budget Meeting with Division Finance | Planning & Division Finance | Mar: 22-23 | Review key budget issues and assumptions
| 3 | 2nd Qtr QPR | All | Apr: 27
| 4 | Develop 2017 Company Targets | Exec Mgmt/Planning | Mar: 9-31; Apr: 1-30 | Based on Updated 2017 Forecast for Reg, NonReg & SSU
| 5 | Gather & Input Budget Assumptions | Planning/SSU, etc. | Apr: 13th; May: 6th | Meet with each Department to discuss and gather FY 2017 Budget parameters (benefits, tax, interest rates, dividends, etc.)
| 6 | Distribute Budget Targets | Exec Mgmt/Field/Planning | May: 5th | Distribute BU Jurisdictional Spending Targets for Net Income, O&M and Capital
| 7 | System Soft Open for Data Input | BU's | May: 9th | System open early for data input only
| 8 | SSU Kickoff (System open for SSU) | SSU/Planning | May: 26 | PlanIt System Available
| 9 | Budget System Open for Field Data Entry | All | [8 empty] | Tentatively working toward early open of May 26th for Division wanting early access for data input | bar: Jun
| 10 | Initial Draft - SSU Budgets due | SSU's | Jun: 10 | Initial draft due to support BU rollup
| 11 | Second Draft - SSU Budgets due | SSU's | Jun: 15 | Semi-final draft achieving SSU departmental targets
| 11 | Review of SSU Budgets | SSU Personnel | Jun: 13-17 | Finalize SSU Budgets Achieving Departmental Targets
| 12 | Final Draft - SSU Budgets due | SSU's | Jun: 24 | Initial draft due to support BU rollup
| 13 | Draft of BU Budgets Due | BU Officers | Jun: 29 | 2017 O&M and Capital Budgets; Income Statement Budget. Version to be presented to Management Committee the week of July 7th
| 14 | SSU Budget Reviews | Exec Mgmt/Dept VPs/Planning | Jul: 12 | Finalize SSU Budgets
| 15 | Non-Reg/Reg Budget Reviews in Dallas | Exec Mgmt/SVP Ops/BU Officers/Planning | Jul: 13 | Review 2017 Budgets & Operating Plans
| 16 | Reg Budget Reviews in Dallas | Exec Mgmt, Non-Reg, Planning | Jul: 13 | Review 2017 Budgets & Departmental Plans
| 17 | Budget Reviews in Dallas | Exec Mgmt, BU's, Planning | Jul: TBD | Follow up meetings with Executive Management ONLY if needed
| 18 | 3rd Qtr QPR | All | Jul: 22
Big Event | 19 | BU Budget Reviews in Dallas (Only as Needed) | BU Officers/Planning/Mgmt Committee/Non-Utility Officers | Jul: 28-29 | Follow up meetings with Executive Management if needed
| 20 | Final Draft of Reg/Non-Reg Plans | Finance VP's | Jul: 29 | Final budget in system achieving Management Committee budget review directives; Basis for Management Committee Sept. Board Presentation. Includes 2017 Annual Budget and 5 Year Plan.
| 21 | Send Final Board Package to BOD | Planning/CFO/Corp Secretary | Sep: 9
Big Event | 22 | Present Budget & Plan to the Board of Directors | Exec Mgmt/Atmos BOD | Sep: 13-16 | Approved Strategic Plan and 2017 Budget
| 23 | Measurement Date - FAS 87 & 106 | Towers Perrin/Human Resources | Sep: TBD | Other benefits expense assumptions received prior to budget
+