## Main Power Station Bldg. ACM
Material | Containment/ Regulated Area | Quantity |  |  | Asbestos Abatement | [9 empty] | Disposal Costs Allocations |  |  |  |  | Conversaion to Cubic Yards of Disposal
|  | Linear Foot | Each | Square Foot | Daily Prod. | Units | Crew Size | Days | Man Days | Daily Labor Costs | Materials / Tools Costs | Disposal | TOTAL | not part of client deliverable. | lbs/unit | total lbs | Tipping Fees (100/ton) | Trucking (25% of tipping fees) | Disposal | Yard per unit of weight:
Abatement
TSI insulation with chicken wire | multiple containments |  |  | 96550 | 600 | SF | 7 | 160.9167 | 1126.4167 | 3927.28 | 80458.3333 | 42240.625 | 754663.765 |  | 7 | 675850 | 33792.5 | 8448.125 | 42240.625 | 1251.5741
TSI insulation 7" thick, under metal skin | multiple containments |  |  | 31120 | 400 | SF | 7 | 77.8 | 544.6 | 3927.28 | 38900 | 19450 | 363892.384 |  | 10 | 311200 | 15560 | 3890 | 19450 | 576.2963
TSI insulation board 3-7" thick | multiple containments |  |  | 185669 | 520 | SF | 7 | 357.0558 | 2499.3904 | 3927.28 | 178527.8846 | 116043.125 | 1696828.991 |  | 10 | 1856690 | 92834.5 | 23208.625 | 116043.125 | 3438.3148
TSI 6" thick, on turbine sections. | multiple containments |  |  | 5800 | 200 | SF | 7 | 29 | 203 | 3927.28 | 14500 | 7250 | 135641.12 |  | 20 | 116000 | 5800 | 1450 | 7250 | 214.8148
TSI 6" thick, and firebrick under metal skin | multiple containments |  |  | 144708 | 200 | SF | 7 | 723.54 | 5064.78 | 3927.28 | 361770 | 180885 | 3384199.1712 |  | 20 | 2894160 | 144708 | 36177 | 180885 | 5359.5556
Flange Gaskets (Cloth 3-4" Width) | estimated qty | 28494 |  |  | 100 | LF | 7 | 284.94 | 1994.58 | 3927.28 | 142470 | 3561.75 | 1265070.9132 |  | 2 | 56988 | 2849.4 | 712.35 | 3561.75 | 105.5333
Bitouminous coating on metal or piping | Class 2 |  |  | 36499 | 1000 | SF | 7 | 36.499 | 255.493 | 3927.28 | 18249.5 | 4562.375 | 166153.6677 |  | 2 | 72998 | 3649.9 | 912.475 | 4562.375 | 135.1815
9x9 VAT | Class 2 |  |  | 1000 | 2500 | SF | 7 | 0.4 | 2.8 | 3927.28 | 200 | 62.5 | 1833.412 |  | 1 | 1000 | 50 | 12.5 | 62.5 | 1.8519
Transite Panels | Misc. Panels Throughout |  |  | 11100 | 1000 | SF | 2 | 11.1 | 22.2 | 1122.08 | 5550 | 11100 | 29105.088 |  | 16 | 177600 | 8880 | 2220 | 11100 | 328.8889
Windows (caulking) 4'x4' ea | Exterior |  | 350 |  | 10 | EA | 4 | 35 | 140 | 2244.16 | 17500 | 3281.25 | 99326.85 |  | 150 | 52500 | 2625 | 656.25 | 3281.25 | 97.2222
ACM wiring | estimated qty | 100000 |  |  | 5000 | LF | 7 | 20 | 140 | 3927.28 | 10000 | 25000 | 113545.6 |  | 4 | 400000 | 20000 | 5000 | 25000 | 740.7407
TSI - small diameter pipe insulation up to 8" OD | Wrap/Cut or Containment | 29370 |  |  | 550 | LF | 7 | 53.4 | 373.8 | 3927.28 | 26700 | 73425 | 309841.752 |  | 40 | 1174800 | 58740 | 14685 | 73425 | 2175.5556
TSI - 8-20" OD | Wrap/Cut or Containment | 22900 |  |  | 500 | LF | 7 | 45.8 | 320.6 | 3927.28 | 22900 | 57250 | 260019.424 |  | 40 | 916000 | 45800 | 11450 | 57250 | 1696.2963
Gaskets - flange type piping | estimated qty |  | 10000 |  | 250 | EA | 4 | 40 | 160 | 2244.16 | 20000 | 31250 | 141016.4 |  | 50 | 500000 | 25000 | 6250 | 31250 | 925.9259
Fire doors | Throughout |  | 450 |  | 250 | EA | 4 | 1.8 | 7.2 | 2244.16 | 900 | 1406.25 | 6345.738 |  | 50 | 22500 | 1125 | 281.25 | 1406.25 | 41.6667
Coating on main stack #6 | Stack 6 |  |  | 82500 | 1000 | SF | 7 | 82.5 | 577.5 | 3927.28 | 41250 | 20625 | 385875.6 |  | 4 | 330000 | 16500 | 4125 | 20625 | 611.1111
Non-friable Roofing | Exterior |  |  | 188000 | 1200 | SF | 4 | 156.6667 | 626.6667 | 2244.16 | 78333.3333 | 94000 | 523918.4 |  | 8 | 1504000 | 75200 | 18800 | 94000 | 2785.1852
Subtotal | [12 empty] | 9637278.2761 | [6 empty] | 0
Work Area Setup / Containment Development | [14 empty] | total lbs | 11062286 | 553114.3 | 138278.575 | 691392.875 | 20485.7148
Polyethylene Enclosure (Boiler Unit) | Large Containment Unit 1 (1598400 CF) |  |  | 194736 | 6000 | SF | 7 | 32.456 | 227.192 | 3927.28 | 0.25 |  | 127464.0497 |  | total tons | 5531.143
Negative Air Machine Setup (18,000 CFM) | Unit 1 containment |  | 6 | [5 empty] | 0 |  | 10000 |  | 60000
Polyethylene Enclosure (Boiler Unit Containment) | Large Containment Unit 2(1598400 CF) |  |  | 194736 | 6000 | SF | 7 | 32.456 | 227.192 | 3927.28 | 0.25 |  | 127464.0497 |  |  |  | Totals | 3057.4088 | 15213.9614 | Determination of converstion to cubic yards:
Negative Air Machine Setup (18,000 CFM) | Unit 2 containment |  | 6 | [5 empty] | 0 |  | 10000 |  | 60000 |  |  |  | Working days allocated for Abatement |  | 174 | 540 lbs per cubic yard.
Polyethylene Enclosure (Boiler Unit Containment) | Large Containment Unit 3 (1598400 CF) |  |  | 194736 | 6000 | SF | 7 | 32.456 | 227.192 | 3927.28 | 0.25 |  | 127464.0497 |  |  |  | # crew per day (estimated) |  | 87.4366 | 1 asbestos bag with ACM and water represents 2 cubic feet
Negative Air Machine Setup (18,000 CFM) | Unit 3 containment |  | 6 | [5 empty] | 0 |  | 10000 |  | 60000 | [6 empty] | Each asbestos bag is no more than 40 lbs each.
Polyethylene Enclosure (Boiler Unit Containment) | Large Containment Unit 4 (1598400 CF) |  |  | 194736 | 6000 | SF | 7 | 32.456 | 227.192 | 3927.28 | 0.25 |  | 127464.0497 | [6 empty] | 1 cubic yard is 27 cubic feet / 2 = 13.5 bags x 40 lbs = 540
Negative Air Machine Setup (18,000 CFM) | Unit 4 containment |  | 6 | [5 empty] | 0 |  | 10000 |  | 60000
Polyethylene Enclosure (Mezzanine Floor) | Unit 5 containment (300,000 CF) |  |  | 100000 | 6000 | SF | 7 | 16.6667 | 116.6667 | 3927.28 | 0.25 |  | 65454.9167
Negative Air Machine Setup (18,000 CFM) | Unit 5 containment (300,000 CF) |  | 1 | [5 empty] | 0 |  | 10000 |  | 10000
Polyethylene Enclosure (Mezzanine Floor) | Unit 6 containment (300,000 CF) |  |  | 100000 | 6000 | SF | 7 | 16.6667 | 116.6667 | 3927.28 | 0.25 |  | 65454.9167
Negative Air Machine Setup (18,000 CFM) | Unit 6 containment (300,000 CF) |  | 1 | [5 empty] | 0 |  | 10000 |  | 10000
Polyethylene Enclosure (up to Typical 50' by 50') | Typical Containment |  |  | 11000 | 6000 | SF | 7 | 1.8333 | 12.8333 | 3927.28 | 0.25 |  | 7200.2633
Negative Air machine Setup (2,000 CFM) | Typical Containment (37,500 CF) |  | 2 | [5 empty] | 0 |  | 2000 |  | 2000
Subtotal | [12 empty] | 909966.2954
Equipment
OSHA / MISHA Air Testing, Asbestos, Lead | [6 empty] | 2 | 174 |  | 880 | 200 |  | 341040
Scaffolding | stack |  | 1 | [7 empty] | 225000 |  | 225000
Gradall 4 Wheel Forklift | Entire job |  | 2 |  |  |  |  | 174 | 0 |  | 150 |  | 26100
Lightweight Crane 120' |  |  | 1 |  |  |  |  | 80 |  |  | 350 |  | 28000
JLG Snorkel Lift 80' | Entire job |  | 1 |  |  |  |  | 174 | 0 |  | 275 |  | 47850
JLG Snorkel Lift 45' | Entire job |  | 1 |  |  |  |  | 174 | 0 |  | 180 |  | 31320
Subtotal | [12 empty] | 699310
General Conditions
Supervisors | [6 empty] | 8 | 174 |  | 592.8 |  |  | 825177.6
General Foreman | [6 empty] | 1 | 174 |  | 593 |  |  | 103182
Project Manager | [6 empty] | 1 | 289 | 289 | 1200 | 0 |  | 346800
Admin | [6 empty] | 1 | 289 | 289 | 800 | 0 |  | 231200
Subtotal | [12 empty] | 1506359.6
Abatement Support During Demolition
Abatement Crew | As needed | [5 empty] | 7 | 250 | 1750 | 3927.28 | 92500 | 50000 | 1124320
Gradall 4 Wheel Forklift | Entire job |  | 1 | [5 empty] | 0 |  | 23720 |  | 23720
Supervisors | [6 empty] | 1 | 250 | 250 | 592.8 | 0 |  | 148200
OSHA / MISHA Air Testing, Asbestos, Lead | [6 empty] | 1 | 250 | 250 | 880 | 200 |  | 220200
Subtotal | [12 empty] | 1516440
[12 empty] | TOTAL | 14269354.1715

## Cane Run Outstructures ACM
Material | Containment/ Regulated Area | Quantity |  |  | Asbestos Abatement | [9 empty] | Disposal Costs Allocations |  |  |  |  | Conversaion to Cubic Yards of Disposal
|  | Linear Foot | Each | Square Foot | Daily Prod. | Units | Crew Size | Days | Man Days | Daily Labor Costs | Materials / Tools Costs | Disposal | TOTAL | not part of client deliverable. | lbs/unit | total lbs | Tipping Fees (100/ton) | Trucking (25% of tipping fees) | Disposal | Yard per unit of weight:
Abatement
Plaster Coating on walls | NPE |  |  | 32200 | 2000 | SF | 7 | 16.1 | 112.7 | 3927.28 | 8050 | 20125 | 91404.208 |  | 10 | 322000 | 16100 | 4025 | 20125 | 596.2963
TSI insulation | multiple containments |  |  | 290 | 100 | SF | 7 | 2.9 | 20.3 | 3927.28 | 1450 | 181.25 | 13020.362 |  | 10 | 2900 | 145 | 36.25 | 181.25 | 5.3704
joint compound at plywood seams | intact |  |  | 360 | 500 | SF | 7 | 0.72 | 5.04 | 3927.28 | 360 | 450 | 3637.6416 |  | 20 | 7200 | 360 | 90 | 450 | 13.3333
various coatings and mastics on metals | Class 2 |  |  | 12270 | 500 | SF | 7 | 24.54 | 171.78 | 3927.28 | 12270 | 1533.75 | 110179.2012 |  | 2 | 24540 | 1227 | 306.75 | 1533.75 | 45.4444
9x9 VAT | Class 2 |  |  | 4990 | 2500 | SF | 7 | 1.996 | 13.972 | 3927.28 | 998 | 311.875 | 9148.7259 |  | 1 | 4990 | 249.5 | 62.375 | 311.875 | 9.2407
Transite Panels | Misc. Panels Throughout |  |  | 100230 | 1000 | SF | 2 | 100.23 | 200.46 | 1122.08 | 50115 | 100230 | 262811.0784 |  | 16 | 1603680 | 80184 | 20046 | 100230 | 2969.7778
Windows 4'x4' ea | Exterior |  | 124 |  | 10 | EA | 4 | 12.4 | 49.6 | 2244.16 | 6200 | 1162.5 | 35190.084 |  | 150 | 18600 | 930 | 232.5 | 1162.5 | 34.4444
TSI - small diameter pipe insulation up to 8" OD | Wrap/Cut or Containment | 77 |  |  | 200 | LF | 2 | 0.385 | 0.77 | 1122.08 | 192.5 | 192.5 | 817.0008 |  | 40 | 3080 | 154 | 38.5 | 192.5 | 5.7037
Cove Base mastic | class 2 | 20 | 0 |  | 250 | EA | 4 | 0.08 | 0.32 | 2244.16 | 40 | 62.5 | 282.0328 |  | 50 | 1000 | 50 | 12.5 | 62.5 | 1.8519
Sink Undercoat |  |  | 1 |  | 50 | EA | 2 | 0.02 | 0.04 | 1122.08 | 10 | 3.125 | 35.5666 |  | 50 | 50 | 2.5 | 0.625 | 3.125 | 0.092593
Conrete Joint Sealant | tunnels | 12775 |  | 0 | 500 | LF | 7 | 25.55 | 178.85 | 3927.28 | 12775 | 6387.5 | 119504.504 |  | 8 | 102200 | 5110 | 1277.5 | 6387.5 | 189.2593
Non-friable Roofing | Exterior |  |  | 25675 | 1200 | SF | 4 | 21.3958 | 85.5833 | 2244.16 | 10697.9167 | 12837.5 | 71551.09 |  | 8 | 205400 | 10270 | 2567.5 | 12837.5 | 380.3704
Subtotal | [7 empty] | 206.3168 |  |  | 103158.4167 |  | 717581.4953 | [6 empty] | 0
Work Area Setup / Containment Development | [14 empty] | total lbs | 2295640 | 114782 | 28695.5 | 143477.5 | 4251.1852
Small Polyethylene Enclosure | Typical Containment |  |  | 7500 | 4000 | SF | 7 | 1.875 | 13.125 | 3927.28 | 0.25 |  | 7363.9
Negative Air machine Setup (2,000 CFM) | small containments |  | 4 | [5 empty] | 0 |  | 2000 |  | 2000
Subtotal | [12 empty] | 9363.9 |  |  |  | Totals | 624.5087 | 852.5403 | Determination of converstion to cubic yards:
Equipment | [16 empty] | Working days allocated for Abatement |  | 60 | 540 lbs per cubic yard.
OSHA / MISHA Air Testing, Asbestos, Lead | [6 empty] | 1 | 60 |  | 880 | 200 |  | 64800 |  |  |  | # crew per day (estimated) |  | 14.209 | 1 asbestos bag with ACM and water represents 2 cubic feet
Gradall 4 Wheel Forklift | Entire job |  | 1 |  |  |  |  | 60 | 0 |  | 150 |  | 9000 | [6 empty] | Each asbestos bag is no more than 40 lbs each.
Lightweight Crane 120' |  |  | 1 |  |  |  |  | 60 |  |  | 350 |  | 21000 | [6 empty] | 1 cubic yard is 27 cubic feet / 2 = 13.5 bags x 40 lbs = 540
JLG Snorkel Lift 80' | Entire job |  | 1 |  |  |  |  | 30 | 0 |  | 275 |  | 8250
Subtotal | [12 empty] | 103050
General Conditions
Supervisors | [6 empty] | 1 | 60 |  | 592.8 |  |  | 35568
General Foreman | [6 empty] | 1 | 60 |  | 593 |  |  | 35580
Project Manager | [6 empty] | 1 | 90 | 120 | 1200 | 0 |  | 108000
Admin | [6 empty] | 1 | 90 | 120 | 800 | 0 |  | 72000
Subtotal | [12 empty] | 251148
Abatement Support During Demolition
Abatement Crew | As needed | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gradall 4 Wheel Forklift | Entire job |  | 1 | [5 empty] | 0 |  | 0 |  | 0
Supervisors | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0
OSHA / MISHA Air Testing, Asbestos, Lead | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0
Subtotal | [12 empty] | 0
[12 empty] | TOTAL | 1081143.3953