## Sheet1
Kentucky American Water
Case No. 2018-00358
Construction Projects
PSC Data Request 3
Type of Filing:_X__Original _____Updated _____Revised |  |  |  |  | Schedule 2
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
Source: PSC_DR3_Schedule 1
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2008 | 12880191.4 | 17969149 | -5088957.6 | -28.32% | 71.68%
2009 | 11817305.39 | 17882050.69 | -6064745.3 | -33.92% | 66.08%
2010 | 14868318.05 | 17995115.7 | -3126797.65 | -17.38% | 82.62%
2011 | 20572837.39 | 22943595 | -2370757.61 | -10.33% | 89.67%
2012 | 23077755 | 24601436 | -1523681 | -6.193% | 93.81%
2013 | 26128386 | 24050759 | 2077627 | 8.639% | 108.6%
2014 | 18446756 | 19534567 | -1087811 | -5.569% | 94.43%
2015 | 28256721 | 27313795 | 942926 | 3.452% | 103.5%
2016 | 20674381.1 | 19030344.86 | 1644036.24 | 8.639% | 108.6%
2017 | 19896804.77 | 22469449.5 | -2572644.73 | -11.45% | 88.55%
Totals | 196619456.1 | 213790261.75 | -17170805.65 | -8.032% | 91.97%
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule 1 for Public Service Commission DR3.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor for each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.