## Sheet1
Kentucky American Water
Case No. 2018-00358
PSC Data Request 4
Type of Filing:_X__Original _____Updated _____Revised |  |  |  |  | Schedule 3b
Workpaper Reference No(s).:______________________
Witness Responsible:
Brent O'Neill
Source: PSC_DR3_Schedule 5 Minus KRS2 and Multi Year Projects in 2017
Year | Actual Project Cost | Cost Approved by CIMC | Variance in Dollars | Variance as Percent | Slippage Factor
2008 | 17985586.84 | 17024299 | 961287.84 | 5.647% | 105.6%
2009 | 6646971.48 | 6255918 | 391053.48 | 6.251% | 106.3%
2010 | 10704036.1 | 10937360 | -233323.9 | -2.133% | 97.87%
2011 | 7986287.32 | 9324971 | -1338683.68 | -14.36% | 85.64%
2012 | 16084718 | 15104722 | 979996 | 6.488% | 106.5%
2013 | 20526040 | 21687648 | -1161608 | -5.356% | 94.64%
2014 | 6036531 | 6148338 | -111807 | -1.818% | 98.18%
2015 | 25257409.25 | 26246568.64 | -989159.39 | -3.769% | 96.23%
2016 | 17434019.25 | 20422643.29 | -2988624.04 | -14.63% | 85.37%
2017 | 7899859 | 7660785 | 239074 | 3.121% | 103.1%
Totals | 136561458.24 | 140813252.93 | -4251794.69 | -3.019% | 96.98%
10-Year Average Slippage |  |  |  |  | 97.94%
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule 5 for Public Service Commission DR3.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor for each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.