## Schedule H
| DUKE ENERGY KENTUCKY | [6 empty] | SCHEDULE H
CASE NO. 2019-00271
CONSTRUCTION WORK IN PROGRESS - PERCENT COMPLETE
AS OF NOVEMBER 30, 2018
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (H/G)
1 | 307600007 | 2018-11-01 | 2020-01-01 | 6.808% | 59475 | 59475 | 349 | 0.5868%
2 | 323326005 | 2018-07-01 | 2019-06-30 | 41.76% | 212265 | 212265 | 7540 | 3.552%
3 | 336593050 | 2018-08-01 | 2019-08-15 | 31.93% | 25891 | 31991 | 6656 | 20.81%
4 | 348643007 | 2018-06-01 | 2020-03-01 | 28.48% | 59330 | 59330 | 2972 | 5.009%
5 | 354154SG1 | 2018-11-01 | 2020-03-31 | 5.62% | 62115 | 62115 | 37688 | 60.67%
6 | CPADEK | 2018-03-01 | 2050-12-31 | 2.285% | 1 | 1 | 604
7 | DISOHDK | 2018-01-01 | 2026-03-31 | 11.06% | 0 |  | 8295
8 | E1214 | 2008-09-01 | 2050-12-31 | 24.2% | 0 |  | 74000
9 | ETSPDCAPK | 2008-07-01 | 2050-12-31 | 24.51% | 0 |  | -43382
10 | KMW18289A | 2018-10-01 | 2019-03-31 | 33.15% | 934250 | 934250 | 494 | 0.05288%
11 | KMW18289B | 2018-10-01 | 2019-03-31 | 33.15% | 2802750 | 2802750 | 50904 | 1.816%
12 | NINT1105K | 2017-08-01 | 2020-01-31 | 53.23% | 234263 | 234263 | 230817 | 98.53%
13 | RF17Q4DEK | 2017-12-01 | 2018-03-31 | 100% | 1504 | 1504 | 1345 | 89.43%
14 | 307600001 | 2018-01-01 | 2019-12-01 | 47.64% | 12302 | 12302 | 22788 | 185.2%
15 | 337767001 | 2018-10-01 | 2019-12-17 | 13.57% | 2357 | 2357 | 971 | 41.2%
16 | 323123DEK | 2018-01-01 | 2020-03-28 | 40.76% | 11446 | 11446 | 11702 | 102.2%
17 | CEB020290 | 2016-08-01 | 2018-11-15 | 100% | 3085662 | 3085662 | 32084 | 1.04%
18 | CEB020298 | 2016-08-01 | 2019-05-01 | 84.85% | 29960739 | 29960739 | 28531240 | 95.23%
19 | CEB020690 | 2018-10-01 | 2018-12-31 | 65.93% | 223972.13 | 223972.13 | 15921 | 7.108%
20 | CEB020768 | 2017-09-01 | 2020-03-31 | 48.3% | 976447.45 | 976447.45 | 826952 | 84.69%
21 | CEB021281 | 2018-01-01 | 2020-05-31 | 37.8% | 21601631.47 | 2346.54 | 175199 | 7466%
22 | CEB021410 | 2015-12-01 | 2018-08-30 | 100% | 6629700 | 24439593 | 41873 | 0.1713%
23 | EB020146X | 2018-10-01 | 2019-09-08 | 17.54% | 2971507.27 | 2971507.27 | 176740 | 5.948%
24 | EB020900X | 2018-11-01 | 2018-12-31 | 48.33% | 11925.38 | 11925.38 | 6772 | 56.79%
25 | EB020904X | 2018-11-01 | 2018-12-31 | 48.33% | 19840.9 | 19840.9 | 17276 | 87.07%
26 | EB020908X | 2018-11-01 | 2018-12-31 | 48.33% | 19579.33 | 19579.33 | 19990 | 102.1%
27 | EB020917X | 2018-11-01 | 2018-12-31 | 48.33% | 28065.2 | 28065.2 | 28074 | 100%
28 | EB020918X | 2018-11-01 | 2018-12-31 | 48.33% | 6740.58 | 6740.58 | 3501 | 51.94%
29 | EB021409X | 2016-05-01 | 2019-12-31 | 70.43% | 7935086.4 | 20857179.62 | 6720918 | 32.22%
30 | 307600001 | 2018-01-01 | 2019-12-01 | 47.64% | 73111 | 73111 | 22456 | 30.71%
31 | 337767001 | 2018-10-01 | 2019-12-17 | 13.57% | 1878 | 1878 | 774 | 41.21%
32 | 323123DKT | 2018-01-01 | 2020-03-28 | 40.76% | 68016 | 68016 | 10455 | 15.37%
33 | KYSCOCC | 2018-11-01 | 2019-01-01 | 47.54% | 1 | 1 | 33944
34 | KYSCPIT | 2018-01-01 | 2017-12-31 | 100% | 0 | 0 | 34041
35 | WDC00004X | 2016-08-01 | 2019-07-01 | 79.98% | 1121398.78 | 25801931.95 | 34316920 | 133%
36 | 28204 | 1996-09-01 | 2000-04-13 | 100% | 100 | 100 | 136 | 136%
37 | 30763 | 1998-09-01 | 2000-04-13 | 100% | 100 | 100 | 2 | 2%
38 | 30896 | 1998-10-01 | 2000-04-13 | 100% | 100 | 100 | 44 | 44%
39 | 35035 | 2000-06-01 | 2000-04-13 | 100% | 0 |  | -856
40 | 78906 | 1999-12-01 | 2000-04-13 | 100% | 0 |  | -473
41 | 323850001 | 2018-03-01 | 2020-01-14 | 40.06% | 31846 | 31846 | 13030 | 40.92%
42 | 338802003 | 2018-06-01 | 2020-03-30 | 27.25% | 147321.02 | 147321.02 | 15021 | 10.2%
43 | 338802004 | 2018-10-01 | 2020-03-31 | 10.97% | 60564 | 52783 | 23199 | 43.95%
44 | 338802005 | 2018-10-01 | 2020-03-30 | 10.99% | 41241 | 33459 | 10738 | 32.09%
45 | 338802008 | 2018-09-01 | 2019-05-29 | 33.33% | 52026 | 52026 | 878 | 1.688%
46 | 346954001 | 2018-05-01 | 2019-12-30 | 35.03% | 128275 | 139345 | 22338 | 16.03%
47 | 17BA31 | 2017-12-01 | 2018-03-31 | 100% | 3524.3 | 3524.3 | 5764 | 163.6%
48 | 17LTCR03 | 2017-10-01 | 2019-03-31 | 77.84% | 52076.25 | 52076.25 | 49047 | 94.18%
49 | 17TB15 | 2017-10-01 | 2019-03-31 | 77.84% | 20071.78 | 20071.78 | 7156 | 35.65%
50 | 17TB16 | 2017-10-01 | 2019-03-31 | 77.84% | 20071.78 | 20071.78 | 26559 | 132.3%
51 | 17TB17 | 2017-10-01 | 2019-03-31 | 77.84% | 15322.35 | 15322.35 | 17390 | 113.5%
52 | ARCOSSW | 2018-07-01 | 2020-03-30 | 23.82% | 129249 | 129249 | 46183 | 35.73%
53 | C9049 | 2016-06-01 | 2019-03-31 | 88.29% | 80000 | 80000 | 41159 | 51.45%
54 | C9050 | 2016-06-01 | 2019-03-31 | 88.29% | 50000 | 50000 | 40690 | 81.38%
55 | C9051 | 2016-06-01 | 2019-03-31 | 88.29% | 17000 | 17000 | 9707 | 57.1%
56 | C9052 | 2016-06-01 | 2019-03-31 | 88.29% | 75000 | 75000 | 40867 | 54.49%
57 | CAPAUTOKY | 2014-03-01 | 2020-12-31 | 69.48% | 49 | 49 | 2584 | 5273%
58 | D1912DS1 | 2016-09-01 | 2018-08-31 | 100% | 2776527.3 | 2776527.3 | 42 | 0.001513%
59 | D1929RS1 | 2016-11-01 | 2019-04-04 | 85.86% | 282613 | 282613 | 242588 | 85.84%
60 | D1931DL2 | 2017-05-01 | 2022-11-29 | 28.36% | 62 | 62 | 18153 | 29279%
61 | D1959DS1 | 2017-07-01 | 2019-04-18 | 78.81% | 290451 | 290451 | 289505 | 99.67%
62 | D2016DS1 | 2017-08-01 | 2019-12-27 | 55.35% | 4019811 | 4019811 | 666548 | 16.58%
63 | D2016DS2 | 2017-08-01 | 2020-01-16 | 54.12% | 3960624 | 3960624 | 482782 | 12.19%
64 | D2017DL1 | 2017-04-01 | 2020-03-31 | 55.53% | 94 | 94 | 73190 | 77862%
65 | D2017DL3 | 2017-07-01 | 2019-12-30 | 56.69% | 94 | 156575.23 | 2990 | 1.91%
66 | D2017DL5 | 2017-12-01 | 2020-05-31 | 39.91% | 49 | 12270.87 | 12349 | 100.6%
67 | D2018DS1 | 2017-08-01 | 2019-04-23 | 77.14% | 3407443 | 3407443 | 2248302 | 65.98%
68 | D2018TS1 | 2017-07-01 | 2019-04-23 | 78.21% | 1145705 | 1145705 | 432143 | 37.72%
69 | D2019DL1 | 2017-07-01 | 2019-11-29 | 58.68% | 94 | 246008.41 | 19265 | 7.831%
70 | D2019DL2 | 2017-05-01 | 2020-03-31 | 54.27% | 94 | 94 | 29803 | 31705%
71 | D2019DL3 | 2017-07-01 | 2020-03-31 | 51.49% | 94 | 94 | 12983 | 13812%
72 | D2020DL1 | 2017-04-01 | 2021-08-28 | 37.76% | 82 | 82 | 857 | 1045%
73 | D2131DL1 | 2017-10-01 | 2019-12-14 | 52.86% | 378745.87 | 378745.87 | 117578 | 31.04%
74 | D2131DL3 | 2017-10-01 | 2020-07-16 | 41.71% | 0 |  | 19009
75 | D2134DL2 | 2018-03-01 | 2019-12-31 | 40.9% | 529194.89 | 583483.6 | 21861 | 3.747%
76 | D2199DL1 | 2017-12-01 | 2019-11-01 | 52% | 49 | 65048.68 | 37745 | 58.03%
77 | D2199DL2 | 2017-07-01 | 2020-03-31 | 51.49% | 49 | 571187.74 | 203014 | 35.54%
78 | D2199DL3 | 2017-11-01 | 2020-03-31 | 44.72% | 49 | 450580.25 | 9979 | 2.215%
79 | D2199DL4 | 2018-03-01 | 2019-10-31 | 44.99% | 41400.28 | 67084.1 | 765 | 1.14%
80 | D2208RS1 | 2017-06-01 | 2019-03-02 | 85.6% | 382562 | 382562 | 2513267 | 657%
81 | DKY212701 | 2018-04-01 | 2019-10-15 | 43.24% | 726368 | 726368 | 50625 | 6.97%
82 | DKY212702 | 2018-04-01 | 2019-10-15 | 43.24% | 2299493 | 2299493 | 131036 | 5.698%
83 | DKY212703 | 2018-08-01 | 2019-10-15 | 27.5% | 860984 | 860984 | 53979 | 6.269%
84 | DKY213201 | 2018-09-01 | 2021-01-24 | 10.27% | 0 |  | 9320
85 | DKY213318 | 2018-04-01 | 2020-05-26 | 30.92% | 1956095 | 1956095 | 37241 | 1.904%
86 | DKY213319 | 2018-04-01 | 2020-05-29 | 30.8% | 3017877 | 3017877 | 18203 | 0.6032%
87 | DKY213321 | 2018-11-01 | 2020-03-16 | 5.788% | 0 |  | 66
88 | EMR248 | 2016-11-01 | 2018-03-31 | 100% | 5283.72 | 5283.72 | 5531 | 104.7%
89 | E-TERRASR | 2018-08-01 | 2019-11-30 | 24.9% | 264721.28 | 264721.28 | 7495 | 2.831%
90 | H0299 | 2015-06-01 | 2019-03-31 | 91.35% | 377337 | 377337 | 15231 | 4.036%
91 | H2111 | 2014-03-01 | 2019-02-16 | 95.7% | 823726 | 823726 | 1086424 | 131.9%
92 | ICCONSTRD | 2017-10-01 | 2030-09-30 | 8.953% | 1 | 1 | 3195
93 | ICCONSTRT | 2017-10-01 | 2030-09-30 | 8.953% | 1 | 1 | 3107
94 | KALRPL | 2017-10-01 | 2067-04-01 | 2.351% | 58 | 58 | 2270 | 3914%
95 | KAR851805 | 2016-09-01 | 2019-10-21 | 71.62% | 313344.88 | 313344.88 | 15229 | 4.86%
96 | KCIPLW076 | 2017-02-01 | 2019-03-31 | 84.64% | 195323 | 195323 | 3 | 0.001536%
97 | KCIPLW085 | 2017-03-01 | 2019-03-31 | 84.08% | 195323 | 195323 | 2 | 0.001024%
98 | KCIPLW999 | 2017-11-01 | 2020-03-31 | 44.72% | 29929 | 29929 | 304303 | 1017%
99 | KCMCDT | 2018-04-01 | 2067-12-31 | 1.337% | 93 | 93 | 371 | 398.9%
100 | KCMCEDT | 2018-06-01 | 2067-12-31 | 1.005% | 93 | 93 | 25571 | 27496%
101 | KCMCOWP | 2018-11-01 | 2067-12-31 | 0.1615% | 93 | 93 | 461 | 495.7%
102 | KCMCOWS | 2018-04-01 | 2067-12-31 | 1.337% | 93 | 93 | 2141 | 2302%
103 | KCMCUG | 2017-12-01 | 2067-12-31 | 1.99% | 93 | 93 | 35787 | 38481%
104 | KCRFN | 2018-06-01 | 2067-12-31 | 1.005% | 80 | 80 | 40044 | 50055%
105 | KEC920153 | 2016-09-01 | 2019-07-31 | 77.14% | 298274.18 | 121038.23 | 15890 | 13.13%
106 | KEC920154 | 2016-09-01 | 2019-12-30 | 67.49% | 150467.62 | 150467.62 | 31189 | 20.73%
107 | KEC920155 | 2016-09-01 | 2019-08-31 | 74.95% | 18342.29 | 18342.29 | 12724 | 69.37%
108 | KET135851 | 2016-05-01 | 2019-06-14 | 82.79% | 414893.11 | 97495.31 | 1478576 | 1517%
109 | KET135853 | 2016-12-01 | 2020-09-28 | 52.18% | 656630.49 | 816705.2 | 718063 | 87.92%
110 | KET135854 | 2016-12-01 | 2019-06-30 | 77.47% | 350417.94 | 401609.39 | 1191631 | 296.7%
111 | KFPLOMX | 2017-09-01 | 2067-12-31 | 2.475% | 0 |  | 9922
112 | KHR744679 | 2016-02-01 | 2020-02-01 | 70.7% | 0 |  | -1031
113 | KIA703714 | 2017-12-01 | 2019-03-01 | 80% | 56580.26 | 56580.26 | 55193 | 97.55%
114 | KIA705495 | 2017-04-01 | 2019-03-01 | 86.98% | 53637.18 | 53637.18 | 5934 | 11.06%
115 | KMODC | 2018-07-01 | 2067-12-31 | 0.8407% | 80 | 80 | 8184 | 10230%
116 | KPOLEIR | 2017-08-01 | 2067-12-31 | 2.639% | 93 | 93 | 28851 | 31023%
117 | KPPL | 2017-12-01 | 2067-12-31 | 1.99% | 2 | 2 | 12971 | 648550%
118 | KRGR | 2017-11-01 | 2067-12-31 | 2.15% | 0 |  | 15968
119 | KRMOH | 2017-08-01 | 2067-12-31 | 2.639% | 93 | 93 | 26188 | 28159%
120 | KROC | 2018-11-01 | 2067-12-31 | 0.1615% | 0 |  | 516
121 | KRTP1PH | 2018-07-01 | 2067-12-31 | 0.8407% | 93 | 93 | 2332 | 2508%
122 | KRTR3PH | 2017-10-01 | 2067-12-31 | 2.316% | 95 | 95 | 15949 | 16788%
123 | KRUCSEC | 2018-04-01 | 2067-12-31 | 1.337% | 93 | 93 | 600 | 645.2%
124 | KRUL | 2018-05-01 | 2067-04-01 | 1.192% | 91 | 91 | 2282 | 2508%
125 | KSLNOLE | 2018-02-01 | 2067-04-01 | 1.682% | 58 | 58 | 21449 | 36981%
126 | KSMF | 2018-03-01 | 2067-12-31 | 1.505% | 93 | 93 | 5397 | 5803%
127 | KSTMOH | 2017-12-01 | 2067-12-31 | 1.99% | 93 | 93 | 60069 | 64590%
128 | KSVDTUG | 2018-08-01 | 2068-03-31 | 0.667% | 0 |  | 30839
129 | KUC261112 | 2017-03-01 | 2019-03-19 | 85.43% | 360637.32 | 360637.32 | 820263 | 227.4%
130 | KUC261121 | 2017-06-01 | 2019-06-30 | 72.07% | 131529.73 | 131529.73 | 1751 | 1.331%
131 | KUC348388 | 2017-06-01 | 2019-06-30 | 72.07% | 90 | 90 | 6238 | 6931%
132 | KUC348397 | 2017-10-01 | 2019-03-01 | 82.36% | 99264.17 | 99264.17 | 206906 | 208.4%
133 | KUC348450 | 2017-10-01 | 2019-06-30 | 66.72% | 90 | 90 | 2528 | 2809%
134 | KUC348463 | 2017-07-01 | 2019-03-01 | 85.03% | 199651.38 | 203207.27 | 142592 | 70.17%
135 | KUC348474 | 2017-07-01 | 2020-06-28 | 47.3% | 190407.95 | 190407.95 | 649 | 0.3408%
136 | KYGLPR11 | 2017-05-01 | 2021-03-31 | 40.42% | 220579 | 220579 | 40733 | 18.47%
137 | KYGLPR15 | 2017-06-01 | 2020-03-31 | 52.9% | 20079 | 20079 | 9583 | 47.73%
138 | KYGLPR5 | 2016-07-01 | 2021-03-31 | 50.87% | 160000 | 160000 | 56225 | 35.14%
139 | KYPRTF2 | 2018-04-01 | 2021-03-31 | 22.19% | 27000 | 27000 | 11389 | 42.18%
140 | KYRELT02 | 2018-09-01 | 2019-09-04 | 24.46% | 1152231 | 1152231 | 5935 | 0.5151%
141 | KYRELT1 | 2015-08-01 | 2020-05-13 | 69.66% | 35000 | 35000 | 261728 | 747.8%
142 | M17011101 | 2018-08-01 | 2020-02-25 | 21.12% | 0 |  | 7781
143 | M18007702 | 2018-11-01 | 2021-05-25 | 3.098% | 0 |  | 11317
144 | M18016401 | 2018-06-01 | 2019-08-27 | 40.27% | 310204 | 310204 | 36887 | 11.89%
145 | M18034601 | 2018-08-01 | 2019-08-10 | 32.35% | 2274991 | 70332.18 | 6644 | 9.447%
146 | M18046301 | 2018-08-01 | 2019-05-08 | 43.21% | 48795.63 | 48795.63 | 13968 | 28.63%
147 | M18058101 | 2018-11-01 | 2019-04-30 | 16.11% | 736486.42 | 736486.42 | 4709 | 0.6394%
148 | MDTKE17 | 2018-01-01 | 2020-06-01 | 37.76% | 35475 | 87508.08 | 25878 | 29.57%
149 | MX0004925 | 2018-11-01 | 2019-11-29 | 7.379% | 32901.06 | 32901.06 | -4214 | -12.81%
150 | MX0076115 | 2018-10-01 | 2020-03-31 | 10.97% | 476.04 | 476.04 | 522 | 109.7%
151 | MX0077066 | 2018-11-01 | 2020-03-31 | 5.62% | 457.05 | 457.05 | 598 | 130.8%
152 | MX0088995 | 2018-11-01 | 2019-03-31 | 19.33% | 550.75 | 550.75 | 706 | 128.2%
153 | MX0089985 | 2018-11-01 | 2019-03-31 | 19.33% | 476.04 | 476.04 | 498 | 104.6%
154 | MX0090254 | 2018-06-01 | 2019-06-01 | 49.86% | 52534.55 | 52534.55 | 25037 | 47.66%
155 | MX0090256 | 2018-09-01 | 2019-06-01 | 32.97% | 120339.21 | 120339.21 | 49231 | 40.91%
156 | MX0090259 | 2018-06-01 | 2018-12-28 | 86.67% | 42782.63 | 42782.63 | 31241 | 73.02%
157 | MX0090746 | 2018-11-01 | 2020-03-31 | 5.62% | 457.05 | 457.05 | 598 | 130.8%
158 | MX0093848 | 2018-11-01 | 2019-12-31 | 6.824% | 476.04 | 466.04 | 498 | 106.9%
159 | MX0106047 | 2018-11-01 | 2020-03-31 | 5.62% | 882.31 | 895.31 | 1092 | 122%
160 | MX0655166 | 2018-11-01 | 2019-09-30 | 8.709% | 1959.83 | 1959.83 | 1874 | 95.62%
161 | MX0675382 | 2018-03-01 | 2021-03-31 | 24.33% | 228.31 | 10800.23 | 1019 | 9.435%
162 | MX0705495 | 2018-03-01 | 2019-06-01 | 59.96% | 55214.64 | 55214.66 | 58468 | 105.9%
163 | MX0920154 | 2018-06-01 | 2020-05-31 | 24.93% | 118477.7 | 845.88 | 222855 | 26346%
164 | MX1269760 | 2018-04-01 | 2020-03-30 | 33.33% | 20243.51 | 42596.62 | 7099 | 16.67%
165 | MX1661647 | 2017-12-01 | 2020-07-30 | 37.45% | 228.31 | 916538.64 | 35846 | 3.911%
166 | MX1848383 | 2018-08-01 | 2018-10-17 | 100% | 56431.9 | 57824.65 | 42002 | 72.64%
167 | MX2167589 | 2017-09-01 | 2019-06-01 | 71.32% | 228.31 | 80732.48 | 139713 | 173.1%
168 | MX2167975 | 2017-10-01 | 2019-12-29 | 51.89% | 228.31 | 242159.7 | 146169 | 60.36%
169 | MX2175246 | 2017-10-01 | 2020-01-02 | 51.64% | 228.31 | 162040.89 | 557911 | 344.3%
170 | MX2239881 | 2018-01-01 | 2019-12-31 | 45.68% | 456.62 | 145712.67 | 11932 | 8.189%
171 | MX2239929 | 2018-01-01 | 2020-01-29 | 43.93% | 456.62 | 73682.77 | 8295 | 11.26%
172 | MX2239971 | 2018-01-01 | 2020-03-30 | 40.66% | 456.62 | 145406.88 | 26092 | 17.94%
173 | MX2240021 | 2018-01-01 | 2020-03-30 | 40.66% | 456.62 | 269343.25 | 18151 | 6.739%
174 | MX2240623 | 2018-01-01 | 2020-03-30 | 40.66% | 228.31 | 228.31 | 10787 | 4725%
175 | MX6293181 | 2018-03-01 | 2019-01-30 | 81.79% | 240125.13 | 139494.66 | -185464 | -133%
176 | MX6293467 | 2018-04-01 | 2019-01-25 | 81.27% | 343744.48 | 193394.71 | -255991 | -132.4%
177 | MX6295870 | 2017-12-01 | 2019-06-01 | 66.54% | 228.31 | 118493.51 | 83073 | 70.11%
178 | MX6589455 | 2018-01-01 | 2019-03-31 | 73.35% | 7271.16 | 7271.16 | 12988 | 178.6%
179 | MX6839574 | 2018-11-01 | 2019-07-01 | 11.98% | 168944.61 | 213196.58 | 166480 | 78.09%
180 | MX6843545 | 2018-03-01 | 2019-06-22 | 57.32% | 228.31 | 17815.96 | 11570 | 64.94%
181 | MX7048752 | 2018-01-01 | 2020-03-31 | 40.61% | 7451.28 | 7451.28 | 12314 | 165.3%
182 | MX7090228 | 2018-04-01 | 2020-03-23 | 33.66% | 228.31 | 170049.61 | 9555 | 5.619%
183 | MX7090285 | 2018-04-01 | 2020-03-23 | 33.66% | 228.31 | 165743.59 | 12100 | 7.3%
184 | MX7343749 | 2018-06-01 | 2019-06-01 | 49.86% | 18473.43 | 18443.01 | 4756 | 25.79%
185 | MX7423928 | 2018-10-01 | 2019-05-01 | 28.3% | 132816.68 | 119036.97 | 69625 | 58.49%
186 | MX7600673 | 2018-08-01 | 2019-03-31 | 50% | 41644.35 | 41644.35 | 33879 | 81.35%
187 | MX7639718 | 2018-03-01 | 2020-07-30 | 31.07% | 13028.17 | 13028.17 | 943 | 7.238%
188 | MX7691568 | 2018-06-01 | 2019-07-01 | 46.08% | 38271.87 | 48280.72 | 7852 | 16.26%
189 | MX7691569 | 2018-07-01 | 2019-12-29 | 27.84% | 39899.12 | 41149.03 | 29377 | 71.39%
190 | MX7691570 | 2018-07-01 | 2019-07-30 | 38.58% | 44183.81 | 44183.81 | 26784 | 60.62%
191 | MX7691571 | 2018-07-01 | 2019-07-30 | 38.58% | 47488.34 | 58415 | 27159 | 46.49%
192 | MX7691572 | 2018-07-01 | 2019-08-14 | 37.16% | 43667.13 | 43667.13 | 33723 | 77.23%
193 | MX7691573 | 2018-07-01 | 2019-07-30 | 38.58% | 47358.03 | 48785.98 | 28218 | 57.84%
194 | MX7708497 | 2018-05-01 | 2019-06-28 | 50.35% | 228.31 | 50046.18 | -4451 | -8.894%
195 | MX7724526 | 2018-04-01 | 2019-09-01 | 46.91% | 228.31 | 493568.59 | 350503 | 71.01%
196 | MX7724611 | 2018-03-01 | 2019-12-29 | 41.02% | 228.31 | 3062414.91 | 44515 | 1.454%
197 | MX7724670 | 2018-04-01 | 2019-09-01 | 46.91% | 228.31 | 778204.8 | 234565 | 30.14%
198 | MX7724731 | 2018-08-01 | 2019-12-29 | 23.5% | 228.31 | 767223.67 | 3530 | 0.4601%
199 | MX7724805 | 2018-06-01 | 2020-01-29 | 29.98% | 228.31 | 92830.61 | 2017 | 2.173%
200 | MX7752157 | 2018-11-01 | 2019-09-02 | 9.508% | 228.31 | 163902.06 | 792 | 0.4832%
201 | MX7838790 | 2018-06-01 | 2019-11-29 | 33.33% | 228.31 | 9052.34 | -1065 | -11.76%
202 | MX7880714 | 2018-06-01 | 2019-07-31 | 42.82% | 228.31 | 24982.24 | -2193 | -8.778%
203 | MX7972270 | 2018-08-01 | 2019-09-02 | 30.48% | 87518.4 | 66003.78 | 79539 | 120.5%
204 | MX7997177 | 2018-06-01 | 2019-07-30 | 42.92% | 228.31 | 48632.94 | -17526 | -36.04%
205 | MX8430902 | 2018-09-01 | 2019-03-31 | 42.65% | 35418.31 | 35418.31 | 56965 | 160.8%
206 | MX8442100 | 2018-09-01 | 2019-03-31 | 42.65% | 35418.31 | 35418.31 | 44010 | 124.3%
207 | MX8520300 | 2018-07-01 | 2019-06-01 | 45.37% | 228.31 | 16460.02 | 25210 | 153.2%
208 | MX8593684 | 2018-06-01 | 2019-03-31 | 60.07% | 856.83 | 856.83 | 659 | 76.91%
209 | MX8667739 | 2018-08-01 | 2020-03-30 | 19.93% | 9204.03 | 9204.03 | 5836 | 63.41%
210 | MX8693329 | 2018-10-01 | 2020-03-30 | 10.99% | 9907.33 | 14515.23 | 7345 | 50.6%
211 | MX8693627 | 2018-10-01 | 2020-03-30 | 10.99% | 3280.81 | 5552.31 | 2425 | 43.68%
212 | MX8735624 | 2018-08-01 | 2019-04-18 | 46.54% | 228.31 | 22271.88 | -2096 | -9.411%
213 | MX8897771 | 2018-09-01 | 2019-03-31 | 42.65% | 43032.5 | 43032.5 | 33770 | 78.48%
214 | MX8898156 | 2018-09-01 | 2019-03-31 | 42.65% | 40659.11 | 40659.11 | 33770 | 83.06%
215 | MX9060418 | 2018-07-01 | 2019-12-01 | 29.34% | 68431.55 | 68698.51 | 33002 | 48.04%
216 | MX9127121 | 2018-09-01 | 2019-10-11 | 22.22% | 228.31 | 88590.34 | -6290 | -7.1%
217 | MX9481816 | 2018-09-01 | 2019-08-31 | 24.73% | 12428.57 | 12428.57 | -1462 | -11.76%
218 | MX9533906 | 2018-11-01 | 2019-09-01 | 9.539% | 228.31 | 5192.15 | 26 | 0.5008%
219 | MX9579446 | 2018-09-01 | 2019-08-30 | 24.79% | 228.31 | 12695.14 | -934 | -7.357%
220 | MX9612876 | 2018-09-01 | 2020-06-30 | 13.47% | 228.31 | 132976.53 | 4858 | 3.653%
221 | MX9624173 | 2018-09-01 | 2020-03-29 | 15.65% | 142487.26 | 142487.26 | 2605 | 1.828%
222 | MX9749639 | 2018-11-01 | 2020-03-31 | 5.62% | 228.31 | 228.31 | 6322 | 2769%
223 | MX9916539 | 2018-10-01 | 2019-09-01 | 17.91% | 228.31 | 5502.55 | 359 | 6.524%
224 | MX9917129 | 2018-11-01 | 2019-12-26 | 6.905% | 228.31 | 39264.85 | 71954 | 183.3%
225 | MX9998915 | 2018-05-01 | 2020-07-30 | 25.94% | 228.31 | 228.31 | 13745 | 6020%
226 | MX9998916 | 2018-05-01 | 2020-11-30 | 22.56% | 228.31 | 228.31 | 49 | 21.46%
227 | P7274 | 2015-01-01 | 2019-06-30 | 87.08% | 205737.82 | 130588.64 | 119434 | 91.46%
228 | SG223SW | 2017-05-01 | 2023-02-28 | 27.15% | 1016639 | 1016639 | 279437 | 27.49%
229 | SG305SVRS | 2016-09-01 | 2019-11-30 | 69.2% | 5323.07 | 5323.07 | 24680 | 463.6%
230 | SG305SW | 2016-08-01 | 2019-11-30 | 69.98% | 189544.12 | 189544.12 | 136546 | 72.04%
231 | SG336OUA | 2018-08-01 | 2020-04-30 | 18.97% | 73357 | 73357 | 14941 | 20.37%
232 | SG336SW | 2016-09-01 | 2021-04-01 | 49.01% | 1049863.37 | 1049863.37 | 377299 | 35.94%
233 | SG344SW | 2016-01-01 | 2019-11-30 | 74.46% | 73774 | 73774 | 47925 | 64.96%
234 | SG358HW19 | 2018-05-01 | 2019-08-18 | 44.94% | 30270.21 | 30270.21 | 43871 | 144.9%
235 | SG358SW2 | 2018-05-01 | 2019-08-18 | 44.94% | 10496.03 | 10496.03 | 10885 | 103.7%
236 | SG359SW | 2018-09-01 | 2022-12-01 | 5.799% | 229797.94 | 227863.84 | 6248 | 2.742%
237 | SG361SW | 2016-01-01 | 2021-01-31 | 57.3% | 266133.19 | 266133.19 | 2173 | 0.8165%
238 | SG438LIC | 2018-07-01 | 2020-03-31 | 23.79% | 8250 | 8250 | 39444 | 478.1%
239 | SG459FB01 | 2018-02-01 | 2019-03-31 | 71.39% | 37132 | 37132 | 11980 | 32.26%
240 | SG459FB02 | 2018-02-01 | 2019-03-31 | 71.39% | 37132 | 37132 | 2423 | 6.525%
241 | SG489SVRS | 2017-05-01 | 2018-12-31 | 94.91% | 44829.46 | 44829.46 | 41775 | 93.19%
242 | SG489SW | 2016-11-01 | 2018-12-31 | 96.08% | 22987.85 | 22987.85 | 30465 | 132.5%
243 | SG598CDEQ | 2017-09-01 | 2019-04-30 | 75.08% | 85620 | 85620 | 141279 | 165%
244 | SG601SW | 2017-06-01 | 2022-06-01 | 29.96% | 42090 | 42090 | 18921 | 44.95%
245 | SG732TR01 | 2018-09-01 | 2020-03-31 | 15.6% | 968336.2 | 968336.2 | 1948 | 0.2012%
246 | SG744MTR | 2018-07-01 | 2020-03-31 | 23.79% | 248821.93 | 248821.93 | 2153 | 0.8653%
247 | SG776MTR | 2018-03-01 | 2019-06-30 | 56.38% | 1 | 1 | 327409
248 | SG781SW | 2018-07-01 | 2020-03-31 | 23.79% | 110269.74 | 110269.74 | 24889 | 22.57%
249 | SG790TMGR | 2018-04-01 | 2019-09-30 | 44.42% | 33758.02 | 33758.02 | 18086 | 53.58%
250 | SG790VISU | 2018-04-01 | 2019-07-30 | 50.1% | 26181.24 | 26181.24 | 9220 | 35.22%
251 | SG792SW | 2018-07-01 | 2019-03-31 | 55.68% | 22428.18 | 22428.18 | 1675 | 7.468%
252 | SG794DES | 2018-06-01 | 2025-03-01 | 7.383% | 3707866 | 3707866 | 19259 | 0.5194%
253 | SG795SW | 2018-07-01 | 2019-12-15 | 28.57% | 13121 | 13121 | 375 | 2.858%
254 | SG797SVRS | 2018-09-01 | 2019-11-30 | 19.78% | 2476 | 2476 | 2677 | 108.1%
255 | SG797SW | 2018-09-01 | 2019-11-30 | 19.78% | 18436 | 18436 | 1176 | 6.379%
256 | SG829PT01 | 2018-06-01 | 2019-03-30 | 60.26% | 25644.65 | 25644.65 | 23209 | 90.5%
257 | SGCAPATKY | 2017-01-01 | 2025-12-31 | 21.24% | 83 | 83 | 70 | 84.34%
258 | SGDLSKY | 2017-05-01 | 2025-12-31 | 18.26% | 94 | 94 | 78 | 82.98%
259 | SGDMS3SW | 2016-09-01 | 2021-01-31 | 50.84% | 210242 | 210242 | 211525 | 100.6%
260 | SGETOAS | 2015-05-01 | 2020-03-31 | 72.88% | 208124 | 208124 | 409231 | 196.6%
261 | SGKAMIMGT | 2016-01-01 | 2019-06-30 | 83.39% | 603878 | 603878 | 1226900 | 203.2%
262 | SGOVH | 2016-01-01 | 2050-12-31 | 8.324% | 95 | 95 | -54 | -56.84%
263 | SGPILCKY | 2017-01-01 | 2025-12-31 | 21.24% | 83 | 83 | 121 | 145.8%
264 | SGRFSKY | 2017-01-01 | 2025-12-31 | 21.24% | 83 | 83 | 80 | 96.39%
265 | SGSELFKY | 2017-12-01 | 2025-12-31 | 12.33% | 1 | 1 | 86
266 | T1611DS1 | 2017-03-01 | 2019-04-30 | 80.89% | 1219379 | 1219379 | 411030 | 33.71%
267 | T1695TS1 | 2016-10-01 | 2020-02-24 | 63.66% | 1153424 | 1153424 | 490308 | 42.51%
268 | T1695TS2 | 2016-12-01 | 2020-04-18 | 59.08% | 352819 | 352819 | 110398 | 31.29%
269 | T1791DS1 | 2017-07-01 | 2020-02-25 | 53.35% | 3017308 | 3017308 | 596759 | 19.78%
270 | T1791TS1 | 2017-08-01 | 2020-07-31 | 44.38% | 79695 | 79695 | 108352 | 136%
271 | T1901DS1 | 2018-04-01 | 2020-01-25 | 36.6% | 3344657 | 3344657 | 306882 | 9.175%
272 | T1901TS1 | 2018-02-01 | 2020-02-29 | 39.84% | 2785992 | 2785992 | 205772 | 7.386%
273 | T1935DS1 | 2017-11-01 | 2020-02-11 | 47.36% | 342079 | 342079 | 215627 | 63.03%
274 | T2009DS1 | 2017-06-01 | 2019-04-20 | 79.51% | 1962535 | 1962535 | 510891 | 26.03%
275 | T2128TL1 | 2018-02-01 | 2020-02-29 | 39.84% | 118357 | 118357 | 12826 | 10.84%
276 | T2128TS1 | 2017-08-01 | 2020-03-17 | 50.68% | 4045269 | 4045269 | 808588 | 19.99%
277 | T2204DS1 | 2018-06-01 | 2021-02-19 | 18.31% | 2109259 | 2109259 | 8491 | 0.4026%
278 | T2227TL1 | 2018-09-01 | 2025-11-08 | 3.429% | 7186714 | 7480297 | 4619 | 0.06175%
279 | T2227TL2 | 2018-09-01 | 2025-10-13 | 3.463% | 6725687 | 6725687 | 854 | 0.0127%
280 | TKY190101 | 2018-07-01 | 2021-03-01 | 15.61% | 205975 | 205975 | 46037 | 22.35%
281 | TKYTOOL | 2017-11-01 | 2050-12-31 | 3.253% | 100 | 100 | 153782 | 153782%
282 | TOUTKY01 | 2018-11-01 | 2021-03-01 | 3.408% | 18000 | 72000 | 104085 | 144.6%
283 | URDSTSP | 2017-10-01 | 2050-12-31 | 3.5% | 49 | 49 | 1083 | 2210%
284 | 307482 | 2017-05-01 | 2019-06-25 | 73.63% | 28598 | 28598 | 38483 | 134.6%
285 | 344368 | 2017-11-01 | 2020-03-31 | 44.72% | 22936.91 | 22936.91 | 12362 | 53.9%
286 | 336593019 | 2018-03-01 | 2020-03-31 | 36.01% | 14982 | 14982 | 13148 | 87.76%
287 | 344598001 | 2018-04-01 | 2019-12-24 | 38.45% | 282698 | 282698 | 34560 | 12.23%
288 | 311803CH | 2016-01-01 | 2019-03-31 | 89.79% | 3243.47 | 3243.47 | 1149 | 35.43%
289 | 315986A | 2017-08-01 | 2022-06-30 | 27.09% | 3313201.21 | 3313201.21 | 527185 | 15.91%
290 | 315986C | 2017-08-01 | 2019-05-28 | 73.08% | 267635.67 | 406035 | 257791 | 63.49%
291 | 315986D | 2017-08-01 | 2019-12-30 | 55.16% | 399313.16 | 399313.16 | 143920 | 36.04%
292 | 315986E | 2017-08-01 | 2020-06-30 | 45.68% | 166907.14 | 166907.14 | 92303 | 55.3%
293 | 315986HW4 | 2018-08-01 | 2019-06-01 | 39.8% | 76896 | 76896 | 34784 | 45.24%
294 | 342284C | 2017-09-01 | 2020-03-31 | 48.3% | 9664.27 | 9664.27 | 26074 | 269.8%
295 | Blank Project ID | [5 empty] | -182
97978894