## 2014
Duke Energy Kentucky Electric
Year 2014
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75080-DE Kentucky Other - Elec | 75080 | CPRCRCT | CPR Corrections - Asset Acctg Only | 0 |  | 0 |  |  | 0 | 1 | -1 | 2012-08-28 | 2050-12-30 | 2012-10-01
75080-DE Kentucky Other - Elec | 75080 | KY120048 | Inst generator monitors @ KY micros | 0 |  | 0 |  |  | 27321.34 | 14739 | 12582.34 | 2012-06-11 | 2013-01-31 | 2012-06-01 | 2013-02-01
75080-DE Kentucky Other - Elec | 75080 | KY130377 | Install New Driveway @ Erlanger Ops | 27.24 |  | 27.24 | 100% |  | 89248.91 | 93211 | -3962.09 | 2013-10-02 | 2014-03-31 | 2013-10-01 | 2014-02-13
75080-DE Kentucky Other - Elec | 75080 | KY130378 | Rplce Lighting @ Erlanger Warehouse | 47.1 |  | 47.1 | 100% |  | 81198.23 | 90127 | -8928.77 | 2013-10-02 | 2014-03-31 | 2013-10-01 | 2014-02-22
75080-DE Kentucky Other - Elec | 75080 | KYF120338 | Replace Ice Machines @ Erlanger | 0 |  | 0 |  |  | 13594.66 | 15385 | -1790.34 | 2012-09-06 | 2012-12-30 | 2012-11-01 | 2013-02-12
75080-DE Kentucky Other - Elec | 75080 | KYF120365 | Replace Heaters @ Erlanger Ops | 0 |  | 0 |  |  | 14900 | 16558 | -1658 | 2012-09-25 | 2013-02-28 | 2012-12-01 | 2013-03-12
75080-DE Kentucky Other - Elec | 75080 | KYF140753 | Rplce Conf Rm Furniture @ Erlanger | 44069.37 |  | 44069.37 | 100% |  | 44069.37 | 33308 | 10761.37 | 2014-10-20 | 2015-03-31 | 2014-12-01 | 2015-03-12
75080-DE Kentucky Other - Elec | 75080 | KYP120201 | Upgrade Light Fixtures @ Erlanger | 0 |  | 0 |  |  | 40945.61 | 56806 | -15860.39 | 2012-07-26 | 2014-03-31 | 2012-08-01 | 2013-08-09
75080-DE Kentucky Other - Elec | 75080 | KYP120211 | Crew Rm Reconfig @ Erlanger Ops | 0 |  | 0 |  |  | 313373.98 | 346911 | -33537.02 | 2012-07-17 | 2013-04-30 | 2012-07-01 | 2013-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP130400 | Furniture Purchase I @ Erlanger | 20895.34 |  | 20895.34 | 100% |  | 20895.34 | 38968 | -18072.66 | 2013-12-06 | 2014-03-31 | 2014-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP130568 | Repl Overhead Doors @ Erlanger Ops | 73467.32 |  | 73467.32 | 100% |  | 73467.32 | 79238 | -5770.68 | 2014-01-13 | 2014-05-29 | 2014-01-01 | 2014-05-31
75080-DE Kentucky Other - Elec | 75080 | KYP140021 | Install Ventilation Syst @ 19 & Aug | 337992.03 |  | 337992.03 | 100% |  | 337992.03 | 323771 | 14221.03 | 2014-02-05 | 2015-03-31 | 2014-04-01 | 2014-11-01
75080-DE Kentucky Other - Elec | 75080 | KYP140165 | Inst Fire Alarm Syst @ Erlanger Ops | 73366.57 |  | 73366.57 | 100% |  | 73366.57 | 87618 | -14251.43 | 2014-04-06 | 2014-09-13 | 2014-04-01 | 2014-09-13
75080-DE Kentucky Other - Elec | 75080 | KYP140215 | Inst Fall Protection @ Erlanger Ops | 26799.89 |  | 26799.89 | 100% |  | 26799.89 | 29710 | -2910.11 | 2014-06-15 | 2014-09-30 | 2014-06-01 | 2014-09-30
75080-DE Kentucky Other - Elec | 75080 | KYP140332 | Security Upgrades @ Augustine Off | 106881.73 |  | 106881.73 | 100% |  | 106881.73 | 152592 | -45710.27 | 2014-06-26 | 2015-03-01 | 2014-07-01 | 2015-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP140750 | Install Fuel KeyCard @ Erlanger Ops | 35473.62 |  | 35473.62 | 100% |  | 35473.62 | 48746 | -13272.38 | 2014-11-04 | 2015-08-29 | 2014-11-01 | 2015-08-28
75080-DE Kentucky Other - Elec | 75080 | RETCOV | Retire Covington | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-12-20 | 2013-03-31 | 2012-12-01 | 2013-03-31
75080-DE Kentucky Other - Elec | 75080 | RETCOV2 | Retire Covington - Elec | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-12-20 | 2013-03-31 | 2012-12-01 | 2013-04-05
75080-DE Kentucky Other - Elec | 75080 | SFTWRE | Software Retirement-Asset Use Only | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-09-20 | 2026-03-30 | 2012-09-01
75080-DE Kentucky Other - Elec | 100FACKY | E0884 | Purchase Recycling Bins KY | 0 |  | 0 |  |  | 6169.61 | 6162 | 7.61 | 2008-09-05 | 2008-12-31 | 2008-12-01 | 2008-12-31
75080-DE Kentucky Other - Elec | 100FACKY | FHKYLBPRT | Label Printers - FH Use | 0 |  | 0 |  |  | 9910.13 | 3000 | 6910.13 | 2009-12-02 | 2010-01-31 | 2009-12-01 | 2010-03-31
75080-DE Kentucky Other - Elec | 100FACKY | GD080001 | 19th & Augustine Windows | 0 |  | 0 |  |  | 83669.17 | 79587 | 4082.17 | 2009-05-29 | 2009-09-30 | 2009-05-01 | 2009-03-18
75080-DE Kentucky Other - Elec | 100FACKY | KY090070 | Replace 30 Ton RTU at Augustine | 0 |  | 0 |  |  | 61918.78 | 70161 | -8242.22 | 2009-05-04 | 2009-11-01 | 2009-05-01 | 2009-12-10
75080-DE Kentucky Other - Elec | 100FACKY | KY090078 | Install VAV boxes at Erlanger Ops | 0 |  | 0 |  |  | 17038.06 | 18215 | -1176.94 | 2009-05-26 | 2009-10-01 | 2009-06-01 | 2009-12-15
75080-DE Kentucky Other - Elec | 100FACKY | KYFM09001 | Replace fire&Intrustion Monitoring | 0 |  | 0 |  |  | 10391.56 | 10386 | 5.56 | 2009-08-07 | 2009-12-15 | 2009-12-01 | 2010-03-10
75080-DE Kentucky Other - Elec | 100FACKY | NEWPORTRT | Ret Newport Plaza Cus Svc Bldg | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-04-08 | 2009-12-31 | 2011-08-01 | 2011-11-16
75080-DE Kentucky Other - Elec | 316ZBG | D1609 | Erlanger Oil separator install | 0 |  | 0 |  |  | 30771.18 | 40000 | -9228.82 | 2007-09-18 | 2008-06-25 | 2007-12-01 | 2008-03-25
75080-DE Kentucky Other - Elec | CAPBUDK | ETSFHCAPK | CAPITAL BUDGET PROJECT KENT | -668.06 |  | -668.06 | 100% |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-07-01
75080-DE Kentucky Other - Elec | CAPBUDK | ETSPDCAPK | ETS Power Delivery Cap Overhead | -110792.42 |  | -110792.42 | 100% |  | 2357.4 | 0 | 2357.4 | 2008-07-07 | 2050-12-31 | 2008-07-01
75080-DE Kentucky Other - Elec | CIS123CAP | CIS123LBS | BancTec Software and Installation | 0 |  | 0 |  |  | 35115.81 | 25979 | 9136.81 | 2010-08-13 | 2011-04-29 | 2010-08-01 | 2011-08-06
75080-DE Kentucky Other - Elec | CIS123CP2 | CIS123LBM | BancTec Prod Bckp Svr_CIS 123 Pr Mg | 0 |  | 0 |  |  | 8895.78 | 7582 | 1313.78 | 2010-08-16 | 2011-04-29 | 2010-12-01 | 2011-08-06
75080-DE Kentucky Other - Elec | CMSICNVK | F3171 | CIS.52 VB6 Conversion Kentucky | 0 |  | 0 |  |  | 334546.69 | 335000 | -453.31 | 2009-12-16 | 2011-10-31 | 2009-12-01 | 2011-11-30
75080-DE Kentucky Other - Elec | DATAP | D2539 | Private Data Circuits | 0 |  | 0 |  |  | 116092.55 | 1 | 116091.55 | 2008-01-17 | 2009-01-30 | 2008-02-01 | 2009-04-30
75080-DE Kentucky Other - Elec | DCITCD2 | D1182 | Common Design Tools Phsase 2 | 0 |  | 0 |  |  | 6581.74 | 1 | 6580.74 | 2007-07-12 | 2011-03-31 | 2007-10-01 | 2011-03-17
75080-DE Kentucky Other - Elec | DCITEDM | C8768 | EDM Project | 0 |  | 0 |  |  | 742848.83 | 1 | 742847.83 | 2007-01-04 | 2009-05-31 | 2007-03-01 | 2009-07-19
75080-DE Kentucky Other - Elec | EPS100 | D1384 | ACS Migration Project | 0 |  | 0 |  |  | 14429.4 | 18253 | -3823.6 | 2007-08-12 | 2008-12-31 | 2007-09-01 | 2008-06-27
75080-DE Kentucky Other - Elec | FBENTLEYK | G2242 | BENTLEY LDE WKFLOW/ED ENHANCEMENTS | 0 |  | 0 |  |  | 39066.41 | 14052 | 25014.41 | 2011-02-10 | 2011-06-30 | 2011-02-01 | 2012-02-14
75080-DE Kentucky Other - Elec | FBENTLYED | G1680 | BENTLEY EXPERT DESIGNER UPGR | 0 |  | 0 |  |  | 3969.45 | 8230 | -4260.55 | 2010-12-15 | 2011-06-30 | 2010-12-01 | 2011-08-27
75080-DE Kentucky Other - Elec | FEGISUPGR | EGISUPGRK | EGIS UPGRADE-HW KENTUCKY | 0 |  | 0 |  |  | 52056.02 | 56737 | -4680.98 | 2011-01-10 | 2014-04-30 | 2011-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | FEGISUPGR | G3022 | EGIS DEFECT RELEASE | 0 |  | 0 |  |  | 832.91 | 3372.07 | -2539.16 | 2011-04-13 | 2013-09-30 | 2011-04-01 | 2011-12-27
75080-DE Kentucky Other - Elec | FEGISUPGS | EGISUPGSK | EGIS UPGR-SW | 230.27 |  | 230.27 | 100% |  | 58634.24 | 124474 | -65839.76 | 2011-01-24 | 2014-04-30 | 2011-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | FEGISUPGS | PCTAIT214 | EGIS UPGR-SW | -100.23 |  | -100.23 | 100% |  | 161902.27 | 160816 | 1086.27 | 2013-10-25 | 2014-04-30 | 2013-11-01 | 2014-03-31
75080-DE Kentucky Other - Elec | FIBRUPG | FIBRKY09 | 2009 Fiber Upgrades - Kentucky | 0 |  | 0 |  |  | 39713.45 | 60000 | -20286.55 | 2009-03-11 | 2009-12-31 | 2009-05-01 | 2010-03-31
75080-DE Kentucky Other - Elec | FIDENKENT | F9006 | IDEN MIBAS UPGRADE-KENTUCKY | 0 |  | 0 |  |  | 23268.81 | 14334 | 8934.81 | 2010-06-01 | 2010-12-30 | 2010-08-01 | 2011-01-18
75080-DE Kentucky Other - Elec | FIDNEL10K | G1371 | MW iDEN RADIO UNITS & PARTS | 0 |  | 0 |  |  | -24893.88 | 73140 | -98033.88 | 2010-10-22 | 2010-12-31 | 2010-12-01 | 2011-03-31
75080-DE Kentucky Other - Elec | FITCOMKY | F9105 | IT COMMON - KENTUCKY | 0 |  | 0 |  |  | 5177.15 | 1 | 5176.15 | 2010-06-02 | 2012-12-31 | 2010-06-01
75080-DE Kentucky Other - Elec | FMAPLNKKE | G5253 | MAPLINK ENHANCEMENT-KENTUCKY | 0 |  | 0 |  |  | 64088.97 | 94938 | -30849.03 | 2011-10-06 | 2012-12-18 | 2011-10-01 | 2013-02-17
75080-DE Kentucky Other - Elec | FMWAVEKY | MW732REP | MW Comm Shelter Repl KY-NINT732 | 327211.31 |  | 327211.31 | 100% |  | 327211.31 | 430000 | -102788.69 | 2014-03-05 | 2014-12-31 | 2014-03-01 | 2015-04-30
75080-DE Kentucky Other - Elec | FMWAVEKY | MWEOLVERN | MW EOL Verona | 911.52 |  | 911.52 | 100% |  | 911.52 | 10000 | -9088.48 | 2014-05-29 | 2014-12-31 | 2014-08-01 | 2015-03-31
75080-DE Kentucky Other - Elec | FMWAVEKY | MWMWUPG | Verona Microwave Upgrades | 59212.45 |  | 59212.45 | 100% |  | 59212.45 | 60346 | -1133.55 | 2014-01-06 | 2014-12-31 | 2014-02-01 | 2014-09-17
75080-DE Kentucky Other - Elec | FWSREFPH2 | P6367 | Workstation refresh project | 714626.09 |  | 714626.09 | 100% |  | 714626.09 | 737000 | -22373.91 | 2014-09-23 | 2014-09-22 | 2014-09-01 | 2014-01-31
75080-DE Kentucky Other - Elec | GASTRAN | D1838 | Implement Gas Transportation | 0 |  | 0 |  |  | 66251.43 | 1 | 66250.43 | 2007-10-14 | 2010-03-31 | 2007-11-01 | 2009-08-11
75080-DE Kentucky Other - Elec | KYPYACCR | E1214 | Kentucky Quarterly Payroll Accrual | -7000 |  | -7000 | 100% |  | 56000 | 0 | 56000 | 2008-09-19 | 2050-12-31 | 2008-09-01
75080-DE Kentucky Other - Elec | MV90REPL | D2332 | MV90 meter reading replacement | 0 |  | 0 |  |  | 34915.31 | 1 | 34914.31 | 2007-12-12 | 2008-04-30 | 2007-12-01 | 2008-07-31
75080-DE Kentucky Other - Elec | MWAVE | FALMTHBKT | Falmouth Blanket | 0 |  | 0 |  |  | 7729.95 | 50000 | -42270.05 | 2012-06-26 | 2017-12-31 | 2012-06-01
75080-DE Kentucky Other - Elec | MWAVE | KYMWVALRM | Kentucky Microwave Alarm | 0 |  | 0 |  |  | 264495.16 | 248300 | 16195.16 | 2011-02-10 | 2011-02-28 | 2011-02-01 | 2011-06-30
75080-DE Kentucky Other - Elec | MWAVE | MWAVEKY10 | Upgrade MidW Microwave infra | 0 |  | 0 |  |  | 442410.49 | 341232 | 101178.49 | 2010-03-11 | 2011-08-31 | 2010-03-01 | 2011-11-30
75080-DE Kentucky Other - Elec | MWAVE | MWBUGENKY | Microwave Backup Generator Kentucky | 0 |  | 0 |  |  | 249540.28 | 242795.05 | 6745.23 | 2011-03-17 | 2012-04-30 | 2011-03-01 | 2012-08-15
75080-DE Kentucky Other - Elec | MWAVE | N1226UNIO | N1226 Midwest Pwr Equip Union | 1267.11 |  | 1267.11 | 100% |  | 1267.11 | 2640 | -1372.89 | 2014-07-14 | 2015-12-31 | 2014-09-01 | 2016-04-28
75080-DE Kentucky Other - Elec | MWAVE | N1226VERO | N1226 MWESTPWREQUIP EOL VERONA 2 | 95.05 |  | 95.05 | 100% |  | 95.05 | 7640 | -7544.95 | 2014-06-23 | 2015-12-31 | 2014-07-01 | 2016-01-01
75080-DE Kentucky Other - Elec | MWAVE | N1226WNKR | N1226 Midwest Pwr Equip EOL WKNR | 1296.91 |  | 1296.91 | 100% |  | 1296.91 | 2640 | -1343.09 | 2014-07-14 | 2015-12-31 | 2014-09-01 | 2015-09-23
75080-DE Kentucky Other - Elec | MWAVE | NINT1309 | Dry Ridge KY Coms Tower Acquis | 7421.67 |  | 7421.67 | 100% |  | 7421.67 | 125000 | -117578.33 | 2014-08-27 | 2014-12-31 | 2014-09-01 | 2016-10-14
75080-DE Kentucky Other - Elec | MWAVE | REPPWREQP | Midwest 2011 Power Equipment Replac | 0 |  | 0 |  |  | 14756 | 13000 | 1756 | 2011-05-18 | 2012-04-01 | 2012-07-01 | 2012-10-01
75080-DE Kentucky Other - Elec | MWAVE | TAYLORBAT | Taylor Mill Battery replacement | 427.92 |  | 427.92 | 100% |  | 3820.95 | 3800 | 20.95 | 2012-08-23 | 2012-12-31 | 2013-01-01 | 2014-11-30
75080-DE Kentucky Other - Elec | MWAVE | TAYLRMBLK | Taylor Mill, KY, Microwave Blanket | -5005.32 |  | -5005.32 | 100% |  | -5005.32 | 50000 | -55005.32 | 2014-03-03 | 2025-12-31 | 2014-03-01
75080-DE Kentucky Other - Elec | MWAVE | WILDERBAT | Wilder MW Battery Replacement | 2551.68 |  | 2551.68 | 100% |  | 2551.68 | 2500 | 51.68 | 2013-09-17 | 2013-12-31 | 2014-02-01 | 2014-11-30
75080-DE Kentucky Other - Elec | MWEAMCAP | E1460 | Kentucky EAM Capex | 0 |  | 0 |  |  | 591257.38 | 1100288.25 | -509030.87 | 2008-10-02 | (blank) | 2008-09-01 | 2010-10-31
75080-DE Kentucky Other - Elec | MWEAMPH1 | E1456 | Kentucky EAM Phase 1 in Svc | 0 |  | 0 |  |  | 387939.96 | 316630.45 | 71309.51 | 2008-10-02 | 2008-09-02 | 2008-09-01 | 2008-09-02
75080-DE Kentucky Other - Elec | MWEAMPH2 | F1844 | Kentucky EAM Phase 2 in Service | 0 |  | 0 |  |  | 974499.36 | 1 | 974498.36 | 2009-11-02 | 2009-10-31 | 2009-10-01 | 2010-01-31
75080-DE Kentucky Other - Elec | MWTELBLKT | ALEXCOOP | Alexandria Cooper Microwave Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-09-11 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | MWTELBLKT | BUTLERBKT | Butler Tower Blanket | 0 |  | 0 |  |  | 270.59 | 50000 | -49729.41 | 2013-09-05 | 2025-12-31 | 2013-09-01
75080-DE Kentucky Other - Elec | MWTELBLKT | DRYRDGBKT | Dry Ridge Microwave Blanket | 0 |  | 0 |  |  | 12554.1 | 50000 | -37445.9 | 2012-04-09 | 2015-12-31 | 2012-04-01
75080-DE Kentucky Other - Elec | MWTELBLKT | GLENCOMW | Glencoe Microwave Blanket | 1089.68 |  | 1089.68 | 100% |  | 1089.68 | 50000 | -48910.32 | 2012-07-26 | 2017-12-31 | 2013-06-01
75080-DE Kentucky Other - Elec | MWTELBLKT | ROSHUGBKT | Ross Hughes MW Blanket | 0 |  | 0 |  |  | 1060 | 50000 | -48940 | 2012-07-20 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | RYLANDBKT | Ryland Heights MW Blanket | 0 |  | 0 |  |  | 2164.69 | 50000 | -47835.31 | 2012-09-11 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | MWTELBLKT | SPARTABKT | Sparta Tower Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-02-08 | 2015-12-31 | 2012-02-01
75080-DE Kentucky Other - Elec | MWTELBLKT | VERONAMW | Verona Microwave Blanket | -2019.3 |  | -2019.3 | 100% |  | 2800.98 | 50000 | -47199.02 | 2012-07-26 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | WILDERBKT | Wilder Microwave Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-07-20 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | WNKRBLKT | WNKR Tower Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-09-05 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | NETWORK1 | NINT621 | Ops Center Technology Refresh | 0 |  | 0 |  |  | 40565.7 | 38205 | 2360.7 | 2012-11-27 | 2013-03-31 | 2012-12-01 | 2014-09-30
75080-DE Kentucky Other - Elec | NETWORK1 | WANUPGRII | WAN EOL Upgrd Phase II | 1638.13 |  | 1638.13 | 100% |  | 23902.1 | 23907 | -4.9 | 2013-09-17 | 2014-06-30 | 2013-10-01 | 2014-09-30
75080-DE Kentucky Other - Elec | OPTIMALC | D3156 | Project Optimization Sftwr-Ky | 0 |  | 0 |  |  | 949.69 | 1 | 948.69 | 2008-03-26 | 2009-12-31 | 2008-05-01 | 2009-01-31
75080-DE Kentucky Other - Elec | RADIO | CABLEKY13 | Install Pag Transmitter Cable & Ant | 22.64 |  | 22.64 | 100% |  | 14034.97 | 14034.97 | 0 | 2011-09-06 | 2013-12-31 | 2012-07-01 | 2014-04-09
75080-DE Kentucky Other - Elec | RADIO | D2524KY | 2008 IDEN Backhaul | 0 |  | 0 |  |  | 871140.98 | 866250 | 4890.98 | 2010-01-13 | 2012-12-31 | 2010-01-01 | 2010-04-30
75080-DE Kentucky Other - Elec | RADIO | IDEN08KY | iDEN In-building coverage | 0 |  | 0 |  |  | 2535.61 | 50000 | -47464.39 | 2008-09-15 | 2009-03-31 | 2009-02-01 | 2009-06-30
75080-DE Kentucky Other - Elec | RADIO | IDENKY09 | iDEN Radio additions | 0 |  | 0 |  |  | 527338.41 | 844550 | -317211.59 | 2009-04-09 | 2011-01-31 | 2009-05-01 | 2011-01-27
75080-DE Kentucky Other - Elec | RADIO | MODKY09 | Replace vehicular radio modems | 0 |  | 0 |  |  | 145687.05 | 175000 | -29312.95 | 2009-04-13 | 2009-12-31 | 2009-04-01 | 2010-03-01
75080-DE Kentucky Other - Elec | RADIO | PAGTRNKY | Pagin Transmitter replacement | 0 |  | 0 |  |  | 191767.68 | 190327.92 | 1439.76 | 2010-11-01 | 2012-12-31 | 2010-12-01 | 2012-06-30
75080-DE Kentucky Other - Elec | RADIOS07 | C9258 | RADIO REPLACEMENT PROGRAM 2007 | 0 |  | 0 |  |  | 1074336.23 | 1 | 1074335.23 | 2007-02-09 | 2008-12-31 | 2007-03-01 | 2008-12-31
75080-DE Kentucky Other - Elec | RESBLDKY | KY100094 | ERLANGER INS ALC LIGHTING CONTROLS | 0 |  | 0 |  |  | 5595.72 | 6569 | -973.28 | 2010-12-07 | 2011-03-27 | 2010-12-01 | 2011-03-28
75080-DE Kentucky Other - Elec | RESBLDKY | KY100302 | PURCHASE OF AEDS FOR AUGUSTINE | 0 |  | 0 |  |  | 1150.51 | 1255 | -104.49 | 2010-10-18 | 2011-05-08 | 2010-12-01 | 2011-03-07
75080-DE Kentucky Other - Elec | RESBLDKY | KY110306 | Office reconfig @ Erlanger Op Ctr | 0 |  | 0 |  |  | 38073.81 | 39848 | -1774.19 | 2011-09-07 | 2012-05-01 | 2011-09-01 | 2012-06-12
75080-DE Kentucky Other - Elec | RESBLDKY | KYF100333 | AUGUSTINE PAVEMENT REPLACEMENT | 0 |  | 0 |  |  | 5918.47 | 6167 | -248.53 | 2010-12-07 | 2011-12-30 | 2010-12-01 | 2011-03-31
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110233 | Replace Pavng/Retain Wall Augustine | 0 |  | 0 |  |  | 1914828.55 | 1938891 | -24062.45 | 2011-05-11 | 2013-03-01 | 2011-06-01 | 2013-01-25
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110683 | Repl Fire Extinguishers @ KY Facil | 0 |  | 0 |  |  | 3561.95 | 3987 | -425.05 | 2011-10-13 | 2012-03-14 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110713 | Rooftop Fall Protect @ Erlanger | 0 |  | 0 |  |  | 8051.17 | 8889 | -837.83 | 2011-11-15 | 2012-03-31 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110717 | Rooftop Fall Protection @ Augustine | 0 |  | 0 |  |  | 18810.1 | 19613 | -802.9 | 2011-11-15 | 2012-03-31 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10006 | Replace Concrete Drive Erlanger | -18664.76 |  | -18664.76 | 100% |  | 97989.98 | 105681 | -7691.02 | 2010-04-20 | 2010-11-30 | 2010-08-01 | 2011-02-12
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10007 | Install new ALC Board at Erlanger | 0 |  | 0 |  |  | 7613.19 | 7657 | -43.81 | 2010-05-18 | 2010-08-30 | 2011-01-01 | 2010-11-19
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10008 | WATER HEATER REPL @ AUGUSTINE | 0 |  | 0 |  |  | 24647.4 | 27241 | -2593.6 | 2010-08-30 | 2010-12-14 | 2010-12-01 | 2011-01-27
75080-DE Kentucky Other - Elec | RESBLDKY | KYP110242 | Inst Gen Monitor Equip @ KY Micro | 0 |  | 0 |  |  | 26510.69 | 23682 | 2828.69 | 2011-09-08 | 2012-04-30 | 2011-10-01 | 2012-05-01
75080-DE Kentucky Other - Elec | SCADA | SCADKY09 | 2009 SCADA projects Kentucky | 0 |  | 0 |  |  | 65109.41 | 25000 | 40109.41 | 2009-02-03 | 2009-12-31 | 2009-04-01 | 2010-03-31
75080-DE Kentucky Other - Elec | SITESVCS | BATGNKY09 | Install Backup Generators | 0 |  | 0 |  |  | 146836.04 | 146836 | 0.04 | 2009-06-03 | 2010-10-15 | 2009-11-01 | 2010-10-15
75080-DE Kentucky Other - Elec | SITESVCS | KY100273 | NEW OH/KY TELECOM GROUP | 0 |  | 0 |  |  | 308443.3 | 322675 | -14231.7 | 2010-09-16 | 2011-07-31 | 2010-10-01 | 2011-12-31
75080-DE Kentucky Other - Elec | TAGSPRO | D2484 | Implement TAGSPRO software for | 0 |  | 0 |  |  | 59046.2 | 1 | 59045.2 | 2008-01-08 | 2008-12-31 | 2008-03-01 | 2009-03-31
75080-DE Kentucky Other - Elec | TDIT | E3875 | Street Index - KY | 0 |  | 0 |  |  | 60473.27 | 82200 | -21726.73 | 2009-01-23 | 2051-03-31 | 2009-02-01 | 2009-08-15
75080-DE Kentucky Other - Elec | TELBLKT | BVRLCKBKT | Beaverlick Tower Blanket | 1.07 |  | 1.07 | 100% |  | 2165.76 | 50000 | -47834.24 | 2011-10-18 | 2019-12-31 | 2011-12-01
75080-DE Kentucky Other - Elec | TRANSPT | FIBRKY10 | Kentucky SONET additions | 0 |  | 0 |  |  | 56253.92 | 110000 | -53746.08 | 2010-01-22 | 2011-03-31 | 2010-01-01 | 2011-03-31
75081-DE Kentucky Fossil | PCTAIT137 | AIT13707H | Gas ETRM | 2.62 |  | 2.62 | 100% |  | 2.62 | 387.22 | -384.6 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTAIT137 | AIT13707S | Gas ETRM | 201.67 |  | 201.67 | 100% |  | 201.67 | 28287.7 | -28086.03 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTANT137 | AIT13708H | Gas ETRM | 271.25 |  | 271.25 | 100% |  | 271.25 | 102.93 | 168.32 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTANT137 | AIT13708S | Gas ETRM | 44481.01 |  | 44481.01 | 100% |  | 44481.01 | 7519.51 | 36961.5 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTAIT218 | AIT21808H | FSO Forecasting Consolidation | 0.42 |  | 0.42 | 100% |  | 0.42 | 1518.46 | -1518.04 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT218 | AIT21808S | FSO Forecasting Consolidation | 21.21 |  | 21.21 | 100% |  | 21.21 | 37846.81 | -37825.6 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT21C | AIT21809H | FSO Forecasting Consolidation | 504.04 |  | 504.04 | 100% |  | 504.04 | 403.64 | 100.4 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT21C | AIT21809S | FSO Forecasting Consolidation | 24790.55 |  | 24790.55 | 100% |  | 24790.55 | 10060.55 | 14730 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | EB201316 | C9122 | EBS-Precipitator Key System | 0 |  | 0 |  |  | 163463.06 | 432758 | -269294.94 | 2007-01-17 | 2008-02-13 | 2007-02-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01234 | C9145 | Circ Water Piping Anode Repl | 0 |  | 0 |  |  | 236141.69 | 356255 | -120113.31 | 2007-01-24 | 2008-01-31 | 2007-01-01 | 2007-11-30
75081-DE Kentucky Fossil | EB1472 | C9152 | Cooling Tower Fan Blades-2007 | 0 |  | 0 |  |  | 69324.01 | 90454 | -21129.99 | 2007-01-24 | 2007-12-31 | 2007-02-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01214 | C9221 | EBS-Module Inlt Turning Vanes | 0 |  | 0 |  |  | 151474.23 | 171803 | -20328.77 | 2007-02-01 | 2008-06-05 | 2007-04-01 | 2007-10-31
75081-DE Kentucky Fossil | EB201351 | C9222 | EBS-Repl B Module Demistr Trys | 0 |  | 0 |  |  | 228799.58 | 421718 | -192918.42 | 2007-02-01 | 2008-04-30 | 2007-03-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01229 | C9223 | EBS-Repl Module Inlt Exp Jnts | 0 |  | 0 |  |  | 209019.92 | 332437 | -123417.08 | 2007-02-01 | 2008-04-30 | 2007-03-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01217 | C9224 | Inlt Vanes on Sec Air Windbox | 0 |  | 0 |  |  | 31346.36 | 46224 | -14877.64 | 2007-02-01 | 2008-05-01 | 2007-02-01 | 2007-08-31
75081-DE Kentucky Fossil | EB201356 | C9318 | EBS-Repl Demin Sump Piping | 0 |  | 0 |  |  | 90123.7 | 146201 | -56077.3 | 2007-02-22 | 2008-09-28 | 2007-02-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01253 | C9847 | New Generator Flux Shield | 0 |  | 0 |  |  | 47007.22 | 74046 | -27038.78 | 2007-05-18 | 2007-08-31 | 2007-08-01 | 2007-11-30
75081-DE Kentucky Fossil | EB201219 | CEB201219 | EBS-Repl Cooling Towr Motr 07 | 0 |  | 0 |  |  | 69781.27 | 140380 | -70598.73 | 2007-02-22 | 2008-06-30 | 2007-03-01 | 2008-05-31
75081-DE Kentucky Fossil | EB201253 | CEB201253 | 2-2 Repl Ash Sluice Pump Motor | 0 |  | 0 |  |  | 40822.56 | 123326 | -82503.44 | 2008-02-21 | 2009-05-31 | 2008-04-01 | 2009-03-31
75081-DE Kentucky Fossil | EB201353 | CEB201353 | EBS-Repl Thicknr Rake Arms | 0 |  | 0 |  |  | 392542.71 | 839900 | -447357.29 | 2007-04-12 | 2008-06-30 | 2007-04-01 | 2008-12-30
75081-DE Kentucky Fossil | EB201362 | CEB201362 | Cooling Tower Gearbox 2008 | 0 |  | 0 |  |  | 218058.69 | 296068 | -78009.31 | 2008-01-24 | 2009-02-28 | 2008-02-01 | 2009-03-15
75081-DE Kentucky Fossil | EBS01209 | CEBS01209 | SAH Sootblower Addition | 0 |  | 0 |  |  | 960496.14 | 535313 | 425183.14 | 2008-04-08 | 2009-09-30 | 2008-06-01 | 2009-09-29
75081-DE Kentucky Fossil | EBS01218 | CEBS01218 | EBS-Repl Turbine Room Roof | 0 |  | 0 |  |  | 127834.06 | 216096 | -88261.94 | 2007-09-02 | 2008-04-10 | 2007-09-01 | 2008-01-13
75081-DE Kentucky Fossil | EBS01235 | CEBS01235 | EBS- Repl Security System | 0 |  | 0 |  |  | 244892.08 | 226581 | 18311.08 | 2007-04-17 | 2009-10-15 | 2007-11-01 | 2009-04-30
75081-DE Kentucky Fossil | EBS01238 | CEBS01238 | EBS-Mercury Monitoring System | -259.41 |  | -259.41 | 100% |  | 922935.79 | 966025 | -43089.21 | 2007-04-17 | 2011-07-31 | 2007-05-01 | 2011-10-25
75081-DE Kentucky Fossil | EBS01239 | CEBS01239 | 2007 Landfill Leachate Sys | 0 |  | 0 |  |  | 53575.18 | 273480 | -219904.82 | 2007-10-16 | 2008-02-29 | 2007-12-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01251 | CEBS01251 | EBS-Rmove 2-2 PA Fan Silencer | 0 |  | 0 |  |  | 0 | 4739 | -4739 | 2007-04-17 | 2007-10-31 | 2009-05-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01252 | CEBS01252 | EBS-Repl Air Compressor Contrl | 0 |  | 0 |  |  | 55964.27 | 83931 | -27966.73 | 2007-04-29 | 2008-04-01 | 2007-05-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01263 | CEBS01263 | Repl Turbine Blade Row | 0 |  | 0 |  |  | 3386310.93 | 5544195 | -2157884.07 | 2008-01-24 | 2009-11-30 | 2008-02-01 | 2009-08-25
75081-DE Kentucky Fossil | EBS01272 | CEBS01272 | Rewind 2-2 & 2-3 ID Fan Motr | 0 |  | 0 |  |  | 778291.95 | 1002753 | -224461.05 | 2007-11-06 | 2008-12-31 | 2007-12-01 | 2008-09-30
75081-DE Kentucky Fossil | EBS01274 | CEBS01274 | EBS-ED Fan Motor | 0 |  | 0 |  |  | 391358.53 | 589470 | -198111.47 | 2007-09-02 | 2008-03-31 | 2007-09-01 | 2008-03-31
75081-DE Kentucky Fossil | EBS01281 | CEBS01281 | EBS-Landfill Excavator | 0 |  | 0 |  |  | 140911.52 | 185628 | -44716.48 | 2007-09-02 | 2007-12-10 | 2007-10-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01305 | CEBS01305 | EBS-Ash Pnd Ground Wtr Monitor | 0 |  | 0 |  |  | 49419.39 | 75623 | -26203.61 | 2007-09-25 | 2008-12-31 | 2007-09-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01309 | CEBS01309 | EBS-WSP Lime Feeder Platform | 0 |  | 0 |  |  | 16993.48 | 19649 | -2655.52 | 2007-12-05 | 2008-02-29 | 2007-12-01 | 2008-01-31
75081-DE Kentucky Fossil | EBS01311 | CEBS01311 | Repl Service Wtr Strainer | 0 |  | 0 |  |  | 74479.66 | 100883 | -26403.34 | 2008-03-06 | 2009-05-31 | 2008-03-01 | 2008-12-31
75081-DE Kentucky Fossil | EBS01314 | CEBS01314 | Repl SCR Ammonia Detectors | 0 |  | 0 |  |  | 38346.04 | 7434 | 30912.04 | 2008-04-09 | 2008-12-31 | 2008-04-01 | 2009-03-22
75081-DE Kentucky Fossil | MF5506 | CMF5506 | PLC in Chem Sample Rm | 0 |  | 0 |  |  | 39451.61 | 48155 | -8703.39 | 2008-02-28 | 2009-03-31 | 2008-06-01 | 2008-12-31
75081-DE Kentucky Fossil | MF601219 | CMF601219 | LP/HP Htr Level Controls | 0 |  | 0 |  |  | 182812.04 | 188027 | -5214.96 | 2008-02-28 | 2009-06-30 | 2008-05-01 | 2009-06-22
75081-DE Kentucky Fossil | MU601213 | CMU601213 | Repl FD Fan Drives | 0 |  | 0 |  |  | 107962.71 | 214137 | -106174.29 | 2008-02-28 | 2009-04-08 | 2008-04-01 | 2009-02-01
75081-DE Kentucky Fossil | MU601216 | CMU601216 | MFS-6 Misc Valves | 5911.81 |  | 5911.81 | 100% |  | 291236.94 | 1267369 | -976132.06 | 2008-02-05 | 2019-03-31 | 2008-03-01 | 2015-06-30
75081-DE Kentucky Fossil | MU601217 | CMU601217 | MFS-6 General Equipment | 0 |  | 0 |  |  | 76017.65 | 546782 | -470764.35 | 2008-02-05 | 2010-03-31 | 2008-02-01
75081-DE Kentucky Fossil | MU601224 | CMU601224 | MFS-6 Repl Condenser Bellows | 0 |  | 0 |  |  | 9887.7 | 55073 | -45185.3 | 2007-07-23 | 2008-01-30 | 2007-09-01 | 2007-10-07
75081-DE Kentucky Fossil | MU601225 | CMU601225 | MFS-6 Repl Battery Chrgers 1&2 | 0 |  | 0 |  |  | 37574.91 | 30943 | 6631.91 | 2007-11-08 | 2008-09-30 | 2008-03-01 | 2008-10-31
75081-DE Kentucky Fossil | MU601228 | CMU601228 | MFS-6 Repl Precipitator T/R | 0 |  | 0 |  |  | 93667.23 | 81167 | 12500.23 | 2007-09-02 | 2008-07-31 | 2007-08-01 | 2008-06-30
75081-DE Kentucky Fossil | MU601231 | CMU601231 | MFS-6 Instl Coal Conveyor & Dr | 0 |  | 0 |  |  | 3770058.8 | 3015998 | 754060.8 | 2007-11-28 | 2009-11-01 | 2007-12-01 | 2009-12-22
75081-DE Kentucky Fossil | MU601232 | CMU601232 | Repl Genratr Collctr Rings | 0 |  | 0 |  |  | 223008.94 | 53858 | 169150.94 | 2008-04-09 | 2009-12-30 | 2008-05-01 | 2008-09-30
75081-DE Kentucky Fossil | PEM1202 | CPEM1202 | 070-PEM General Equipment | 0 |  | 0 |  |  | 33729.76 | 73316 | -39586.24 | 2007-05-15 | 2014-12-31 | 2007-05-01 | 2014-01-31
75081-DE Kentucky Fossil | EBS01278 | D1138 | EBS-ID Fan Motor 2-1 Rewind | 0 |  | 0 |  |  | 226305.84 | 410755 | -184449.16 | 2007-07-04 | 2008-03-31 | 2007-07-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01259 | D1148 | EBS-2-1 SAH Thrust Bearing | 0 |  | 0 |  |  | 75418.06 | 106155 | -30736.94 | 2007-07-08 | 2007-12-30 | 2007-07-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01287 | D1437 | EBS-2-1 Silo Flyash Blowr Motr | 0 |  | 0 |  |  | 40265.22 | 89245 | -48979.78 | 2007-09-02 | 2008-10-31 | 2007-09-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01307 | D1826 | EBS-Repl 2-4 Vacuum Pump Motor | 0 |  | 0 |  |  | 8819.9 | 27752 | -18932.1 | 2007-10-12 | 2008-12-31 | 2007-10-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01248 | D3122 | Ky Sales & Use Tax Vintage 07 | 0 |  | 0 |  |  | 18389.42 | 26119 | -7729.58 | 2008-03-21 | 2008-03-31 | 2008-03-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01248 | D3124 | Ky Sales & Use Tax Vintage 05 | 0 |  | 0 |  |  | 259096.82 | 368008 | -108911.18 | 2008-03-21 | 2008-03-31 | 2008-03-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01267 | D3553 | Sludge Transfr Pmp Replacemnt | 0 |  | 0 |  |  | 103059.88 | 175621 | -72561.12 | 2008-05-21 | 2009-08-24 | 2008-09-01 | 2009-02-14
75081-DE Kentucky Fossil | EB1482 | D3558 | Coolng Towr Fan Blades 2008 | 0 |  | 0 |  |  | 81896.2 | 109365 | -27468.8 | 2008-05-21 | 2009-03-31 | 2008-08-01 | 2009-02-12
75081-DE Kentucky Fossil | EBS01206 | D3666 | Replace SAH Preheat Coils | 0 |  | 0 |  |  | 1982885.62 | 2382627 | -399741.38 | 2008-06-12 | 2010-08-15 | 2008-11-01 | 2010-08-18
75081-DE Kentucky Fossil | EB021205 | EB021205X | Boiler Room Roof Replacement | 0 |  | 0 |  |  | 191888.5 | 426697 | -234808.5 | 2008-10-13 | 2009-09-16 | 2008-10-01 | 2009-04-06
75081-DE Kentucky Fossil | EB021207 | EB021207X | Coal Bunker Lighting | 0 |  | 0 |  |  | 17506.33 | 30961 | -13454.67 | 2009-03-30 | 2009-06-30 | 2009-05-01 | 2009-05-13
75081-DE Kentucky Fossil | EB021210 | EB021210X | INSTALL PARTICULATE MONTIOR | 0 |  | 0 |  |  | 164901.9 | 266016 | -101114.1 | 2011-04-26 | 2012-02-13 | 2011-05-01 | 2011-10-25
75081-DE Kentucky Fossil | EB021216 | EB021216X | SCR Winterization | 0 |  | 0 |  |  | 85622.78 | 105291 | -19668.22 | 2009-03-13 | 2009-03-30 | 2009-03-01 | 2009-06-13
75081-DE Kentucky Fossil | EB021217 | EB021217X | WSP Switchbreaker Lifter | 0 |  | 0 |  |  | 32798.36 | 44484 | -11685.64 | 2009-07-22 | 2010-01-15 | 2009-07-01 | 2010-01-01
75081-DE Kentucky Fossil | EB021219 | EB021219X | REPLACE FLOW MONITOR | 0 |  | 0 |  |  | 57213.81 | 79903 | -22689.19 | 2009-04-03 | 2009-08-07 | 2009-08-01 | 2009-08-18
75081-DE Kentucky Fossil | EB021221 | EB021221X | Purchase WSP Shovel and Loader | 0 |  | 0 |  |  | 69302.23 | 117133 | -47830.77 | 2009-03-30 | 2009-06-26 | 2009-04-01 | 2009-09-01
75081-DE Kentucky Fossil | EB021222 | EB021222X | Replace Stack Flow Monitor | 93313.85 |  | 93313.85 | 100% |  | 97762.38 | 103609 | -5846.62 | 2013-09-26 | 2014-06-01 | 2013-10-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021224 | EB021224X | Replace 3 sump pumps | 0 |  | 0 |  |  | 61100.22 | 76206 | -15105.78 | 2009-05-06 | 2010-07-31 | 2009-06-01 | 2010-07-02
75081-DE Kentucky Fossil | EB021233 | EB021233X | Replace CBU Chains and Buckets | 139444.91 |  | 139444.91 | 100% |  | 246155.48 | 357680 | -111524.52 | 2013-08-05 | 2014-08-01 | 2013-08-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021236 | EB021236X | Replace BFP Outlet Valve | 0 |  | 0 |  |  | 406884.84 | 582388 | -175503.16 | 2009-08-20 | 2010-06-22 | 2009-08-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021238 | EB021238X | ID Fan VFD Control Board Rep | 159085.05 |  | 159085.05 | 100% |  | 293202.83 | 451841 | -158638.17 | 2013-08-26 | 2014-12-31 | 2013-09-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021244 | EB021244X | Replace 2-1 BFP Outlet Valve | 0 |  | 0 |  |  | 382978.67 | 595228 | -212249.33 | 2011-07-19 | 2012-06-07 | 2011-07-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021247 | EB021247X | CBU Hoist and Electric Rm Roof | 0 |  | 0 |  |  | 6679.25 | 31973 | -25293.75 | 2012-08-21 | 2013-08-26 | 2013-04-01 | 2013-07-19
75081-DE Kentucky Fossil | EB021249 | EB021249X | CT Acid Metering Pump | 0 |  | 0 |  |  | 52269.89 | 61640 | -9370.11 | 2010-09-16 | 2011-06-20 | 2010-10-01 | 2011-04-20
75081-DE Kentucky Fossil | EB021250 | EB021250X | CBU Cable Reel and Drive | 49017.98 |  | 49017.98 | 100% |  | 168149.16 | 255347 | -87197.84 | 2012-10-22 | 2014-12-31 | 2012-12-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021257 | EB021257X | S.Thickner Tunnel E. Sump Pump | 0 |  | 0 |  |  | 84952.64 | 155583 | -70630.36 | 2012-08-31 | 2014-11-20 | 2012-09-01 | 2013-04-29
75081-DE Kentucky Fossil | EB021259 | EB021259X | 2-6 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 188695.13 | 357710 | -169014.87 | 2010-03-08 | 2011-02-01 | 2010-04-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021260 | EB021260X | 2-3 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 371837.58 | 423246 | -51408.42 | 2010-09-16 | 2011-07-27 | 2010-10-01 | 2011-02-12
75081-DE Kentucky Fossil | EB021261 | EB021261X | 2-5 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 300489.57 | 370132 | -69642.43 | 2011-08-12 | 2012-06-21 | 2011-09-01 | 2012-07-31
75081-DE Kentucky Fossil | EB021263 | EB021263X | 2-2 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 333065.96 | 544676 | -211610.04 | 2012-08-21 | 2015-05-25 | 2012-09-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021264 | EB021264X | 2-4 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 210859.45 | 358249 | -147389.55 | 2010-11-01 | 2012-10-22 | 2010-11-01 | 2011-03-15
75081-DE Kentucky Fossil | EB021270 | EB021270X | Replacement 2SR2 Transformer | 0 |  | 0 |  |  | 86017.34 | 119913 | -33895.66 | 2009-11-06 | 2010-10-20 | 2009-12-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021275 | EB021275X | Landfill Cover 2010 | 0 |  | 0 |  |  | 3.6082e-16 | 0 | 3.6082e-16 | 2010-03-04 | 2012-01-31 | 2010-09-01 | 2012-03-31
75081-DE Kentucky Fossil | EB021276 | EB021276X | Replace UAT Bushings | 0 |  | 0 |  |  | 33811.56 | 66133 | -32321.44 | 2011-08-11 | 2013-03-25 | 2011-08-01 | 2012-06-28
75081-DE Kentucky Fossil | EB021277 | EB021277X | Replace 1st Layer SCR Catalyst | 93673.31 |  | 93673.31 | 100% |  | 93673.31 | 1659977 | -1566303.69 | 2014-11-04 | 2015-12-31 | 2014-10-01 | 2015-06-30
75081-DE Kentucky Fossil | EB021278 | EB021278X | Repl 6 IDB Fan inlet exp jts | 0 |  | 0 |  |  | 260831.03 | 511099 | -250267.97 | 2012-01-26 | 2012-12-01 | 2012-02-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021279 | EB021279X | Replace FGD Transformer 2SR1 | 0 |  | 0 |  |  | 56015.87 | 108674 | -52658.13 | 2009-07-31 | 2010-06-08 | 2009-07-01 | 2009-10-20
75081-DE Kentucky Fossil | EB021280 | EB021280X | IT Capital Project Support | 0 |  | 0 |  |  | 112236.76 | 109201 | 3035.76 | 2009-08-20 | 2013-03-30 | 2009-08-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021282 | EB021282X | Repl No 2 Boiler Room Sump Pump | 0 |  | 0 |  |  | 90452.54 | 170756 | -80303.46 | 2010-03-10 | 2011-06-10 | 2010-03-01 | 2010-12-29
75081-DE Kentucky Fossil | EB021283 | EB021283X | Repl FGD Common inlet exp jt | 0 |  | 0 |  |  | 143398.84 | 218989 | -75590.16 | 2011-11-09 | 2012-10-26 | 2011-12-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021284 | EB021284X | Repl 3 IDBF Outlet Exp Jts | 225782 |  | 225782 | 100% |  | 264616.66 | 476977 | -212360.34 | 2013-08-26 | 2014-08-01 | 2013-09-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021286 | EB021286X | Replace RH Attemperator Line | 0 |  | 0 |  |  | 237323.9 | 354424 | -117100.1 | 2011-08-22 | 2012-06-08 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021291 | EB021291X | Landfill Cover 2012 | 68.14 |  | 68.14 | 100% |  | 68.14 | 0 | 68.14 | 2012-03-02 | 2014-12-31 | 2014-04-01 | 2014-03-31
75081-DE Kentucky Fossil | EB021299 | EB021299X | Replace Abs Module Outlet Duct | 525522.3 |  | 525522.3 | 100% |  | 610517.61 | 1029673 | -419155.39 | 2013-11-18 | 2014-08-01 | 2013-12-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021301 | EB021301X | Replace Radio System | 0 |  | 0 |  |  | 257396.74 | 439629 | -182232.26 | 2010-04-14 | 2011-03-03 | 2010-04-01 | 2010-12-08
75081-DE Kentucky Fossil | EB021306 | EB021306X | 2-6 Pulv Roll Wheel Repl 2014 | 4750.56 |  | 4750.56 | 100% |  | 4750.56 | 564903 | -560152.44 | 2014-11-24 | 2015-08-01 | 2014-12-01 | 2015-06-29
75081-DE Kentucky Fossil | EB021312 | EB021312X | 2-1 Pulv Roll Wheel Repl | 166542.09 |  | 166542.09 | 100% |  | 387930.93 | 581014 | -193083.07 | 2013-09-23 | 2014-12-01 | 2013-10-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021317 | EB021317X | Replace Station Phone System | 886.2 |  | 886.2 | 100% |  | 131226.88 | 256732 | -125505.12 | 2013-06-28 | 2013-12-31 | 2013-07-01 | 2014-01-21
75081-DE Kentucky Fossil | EB021319 | EB021319X | BlrRm Elevator Control Upgrade | 0 |  | 0 |  |  | 278582.04 | 312468 | -33885.96 | 2010-10-05 | 2011-09-16 | 2010-11-01 | 2011-05-04
75081-DE Kentucky Fossil | EB021325 | EB021325X | CT Gearbox Replacement 2010 | 0 |  | 0 |  |  | 91028.11 | 134310 | -43281.89 | 2009-09-25 | 2010-08-19 | 2009-09-01 | 2009-12-28
75081-DE Kentucky Fossil | EB021332 | EB021332X | RHO Pendant Replacement | 3525112.45 |  | 3525112.45 | 100% |  | 7708708.73 | 10402876 | -2694167.27 | 2012-11-02 | 2015-05-27 | 2012-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021335 | EB021335X | DRFT ELIMIN & HEADER RPLMNT | 0 |  | 0 |  |  | 150713.29 | 240023 | -89309.71 | 2011-11-07 | 2012-09-27 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021338 | EB021338A | ARO - Cooling Tower Fill | 0 |  | 0 |  |  | 2396.7 | 0 | 2396.7 | 2010-10-12 | 2013-03-31 | 2012-07-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021351 | EB021351X | Replace Pug Mill Gear Box | 4914.14 |  | 4914.14 | 100% |  | 42550.44 | 66314 | -23763.56 | 2013-12-20 | 2015-03-18 | 2013-12-01 | 2014-03-31
75081-DE Kentucky Fossil | EB021352 | EB021352X | Retube Chiller in Control Room | 0 |  | 0 |  |  | 118527.04 | 137419 | -18891.96 | 2010-11-02 | 2011-09-16 | 2010-12-01 | 2011-05-31
75081-DE Kentucky Fossil | EB021353 | EB021353X | NH3 Slip Monitor 1 | 0 |  | 0 |  |  | 266572.2 | 242755 | 23817.2 | 2011-08-12 | 2012-06-19 | 2011-08-01 | 2012-04-27
75081-DE Kentucky Fossil | EB021355 | EB021355X | Replace Cond. Control Valve | 0 |  | 0 |  |  | 188557.17 | 245177 | -56619.83 | 2011-06-06 | 2012-04-16 | 2011-06-01 | 2012-07-20
75081-DE Kentucky Fossil | EB021356 | EB021356X | Replace WSP Dust Collector | 0 |  | 0 |  |  | 172508.97 | 133042 | 39466.97 | 2010-11-01 | 2012-05-20 | 2010-12-01 | 2011-11-17
75081-DE Kentucky Fossil | EB021357 | EB021357C | Ash Sluice Pump Soft Starters | 35689.89 |  | 35689.89 | 100% |  | 35689.89 | 649561 | -613871.11 | 2014-11-12 | 2015-10-01 | 2014-11-01 | 2015-11-01
75081-DE Kentucky Fossil | EB021358 | EB021358X | Voltage Regulator Transformers | 0 |  | 0 |  |  | 72696 | 108833 | -36137 | 2010-10-07 | 2011-07-25 | 2010-11-01 | 2011-07-03
75081-DE Kentucky Fossil | EB021362 | EB021362X | New Sulferic Acid System | 0 |  | 0 |  |  | 667594.57 | 654708 | 12886.57 | 2012-08-09 | 2013-08-25 | 2012-08-01 | 2013-06-07
75081-DE Kentucky Fossil | EB021364 | EB021364X | Pugmill Gear Box Replacement | 0 |  | 0 |  |  | 14629.08 | 24709 | -10079.92 | 2010-10-07 | 2012-12-31 | 2010-10-01 | 2011-02-04
75081-DE Kentucky Fossil | EB021365 | EB021365X | STORM WATER PIPE REPLACEMENT | 0 |  | 0 |  |  | 426775.84 | 550683 | -123907.16 | 2010-11-02 | 2011-10-12 | 2010-11-01 | 2011-03-10
75081-DE Kentucky Fossil | EB021366 | EB021366X | Replace Step-up Transformer | 0 |  | 0 |  |  | 5838602.22 | 6851486 | -1012883.78 | 2011-02-23 | 2013-04-01 | 2011-03-01 | 2012-07-19
75081-DE Kentucky Fossil | EB021369 | EB021369X | CT Gearbox Oil Filter | 0 |  | 0 |  |  | 257377.12 | 216834 | 40543.12 | 2012-11-15 | 2013-10-26 | 2012-11-01 | 2013-09-14
75081-DE Kentucky Fossil | EB021370 | EB021370X | Replace FGD Service Water Line | 0 |  | 0 |  |  | 43220.45 | 81196 | -37975.55 | 2011-04-26 | 2011-09-30 | 2011-05-01 | 2011-06-30
75081-DE Kentucky Fossil | EB021373 | EB021373X | WSP Shovel | 0 |  | 0 |  |  | 318739.58 | 553812 | -235072.42 | 2012-04-05 | 2013-01-14 | 2012-06-01 | 2012-09-01
75081-DE Kentucky Fossil | EB021378 | EB021378X | Repl Flyash and Lime Scales | 0 |  | 0 |  |  | 212614.91 | 283188 | -70573.09 | 2012-08-21 | 2013-07-22 | 2012-09-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021380 | EB021380X | Ash Pond Modification | 0 |  | 0 |  |  | 123137.7 | 328913 | -205775.3 | 2012-08-02 | 2013-10-26 | 2012-09-01 | 2013-03-14
75081-DE Kentucky Fossil | EB021381 | EB021381X | Replace FGD Sludge Tank | 0 |  | 0 |  |  | 682213.74 | 758918 | -76704.26 | 2012-01-17 | 2012-11-30 | 2012-02-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021383 | EB021383X | Unit Control Simulator | 199307.63 |  | 199307.63 | 100% |  | 1013907.01 | 1656726 | -642818.99 | 2012-12-27 | 2016-12-21 | 2012-12-01 | 2017-03-15
75081-DE Kentucky Fossil | EB021384 | EB021384X | 2-2 Precip Inlet Exp Jnt Repl | 246427.48 |  | 246427.48 | 100% |  | 267696.84 | 307763 | -40066.16 | 2013-10-31 | 2014-06-01 | 2013-12-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021387 | EB021387X | East Bend EAM | 0 |  | 0 |  |  | 544126.33 | 788588.88 | -244462.55 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2010-01-31
75081-DE Kentucky Fossil | EB021394 | EB021394X | Repl Filt Overflow Sumps Pumps | 0 |  | 0 |  |  | 28449.14 | 47672 | -19222.86 | 2011-11-29 | 2012-11-27 | 2011-12-01 | 2012-03-31
75081-DE Kentucky Fossil | EB021395 | EB021395X | Repl Emer Sump Pump Motors | 0 |  | 0 |  |  | 10699.04 | 18509 | -7809.96 | 2011-11-09 | 2012-10-10 | 2011-12-01 | 2012-02-18
75081-DE Kentucky Fossil | EB021396 | EB021396X | REPL PUG MILL GEAR BOX | 0 |  | 0 |  |  | 21919.94 | 42879 | -20959.06 | 2011-11-07 | 2012-10-08 | 2011-12-01 | 2012-01-14
75081-DE Kentucky Fossil | EB021397 | EB021397X | SB Air Compressor Cooler | 0 |  | 0 |  |  | 30989.8 | 40171 | -9181.2 | 2011-12-02 | 2012-11-14 | 2011-12-01 | 2012-01-25
75081-DE Kentucky Fossil | EB021398 | EB021398X | 2LHIM Transformer Replacement | 3742.99 |  | 3742.99 | 100% |  | 60408.27 | 101667 | -41258.73 | 2013-07-15 | 2016-06-30 | 2013-07-01 | 2016-08-06
75081-DE Kentucky Fossil | EB021402 | EB021402X | FGD HVAC Replacement | 0 |  | 0 |  |  | 36950.95 | 60520 | -23569.05 | 2012-07-13 | 2012-12-31 | 2012-09-01 | 2012-12-28
75081-DE Kentucky Fossil | EB021411 | EB021411X | Filtrate Return Pumps | 0 |  | 0 |  |  | 75905.84 | 101139 | -25233.16 | 2012-10-22 | 2013-04-26 | 2012-11-01 | 2013-08-23
75081-DE Kentucky Fossil | EB021412 | EB021412X | Install 3rd Layer SCR Catalyst | 0 |  | 0 |  |  | 536263.68 | 884933 | -348669.32 | 2013-05-16 | 2013-12-31 | 2013-05-01 | 2013-07-19
75081-DE Kentucky Fossil | EB021414 | EB021414X | Replace Filtered Water Tank | 304949.55 |  | 304949.55 | 100% |  | 368991.65 | 486876 | -117884.35 | 2013-09-23 | 2014-08-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021417 | EB021417X | Station Cameras | 17456.47 |  | 17456.47 | 100% |  | 265510.44 | 248735 | 16775.44 | 2013-02-15 | 2015-01-15 | 2013-03-01 | 2014-12-31
75081-DE Kentucky Fossil | EB021418 | EB021418X | SA Preheat Coils | 0 |  | 0 |  |  | 332970.58 | 503698 | -170727.42 | 2013-02-15 | 2014-05-30 | 2013-02-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021419 | EB021419X | Fuel Oil Tank Dike Liner Repl | 0 |  | 0 |  |  | 55485.17 | 109522 | -54036.83 | 2012-09-04 | 2012-12-31 | 2012-09-01 | 2013-02-06
75081-DE Kentucky Fossil | EB021420 | EB021420X | CBU MCC HVAC Replacement | 0 |  | 0 |  |  | 8447.61 | 26482 | -18034.39 | 2012-08-21 | 2013-03-30 | 2012-11-01 | 2013-03-07
75081-DE Kentucky Fossil | EB021423 | EB021423X | Precipitator Upgrade 2014 | 5010323.5 |  | 5010323.5 | 100% |  | 6648549.35 | 6273521 | 375028.35 | 2013-05-29 | 2014-08-05 | 2013-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021424 | EB021424X | 2-2 SB Air Compressor Cooler | 0 |  | 0 |  |  | 29719.28 | 44705 | -14985.72 | 2012-08-10 | 2013-02-28 | 2012-08-01 | 2012-06-09
75081-DE Kentucky Fossil | EB021425 | EB021425X | Landfill Articulating Trucks | 0 |  | 0 |  |  | 768539.66 | 1205473 | -436933.34 | 2012-08-08 | 2012-11-30 | 2012-08-01 | 2012-11-30
75081-DE Kentucky Fossil | EB021426 | EB021426X | D6 Dozer | 0 |  | 0 |  |  | 257331.27 | 403577 | -146245.73 | 2012-08-08 | 2012-11-30 | 2012-09-01 | 2012-12-11
75081-DE Kentucky Fossil | EB021427 | EB021427X | CEMS Hg Umbilical Replacement | 0 |  | 0 |  |  | 86554.52 | 126175 | -39620.48 | 2012-08-31 | 2013-02-28 | 2012-09-01 | 2013-04-17
75081-DE Kentucky Fossil | EB021431 | EB021431X | Ash Sluice Pump Seal Water Pipe | 0 |  | 0 |  |  | 34889.91 | 37855 | -2965.09 | 2012-11-28 | 2013-11-04 | 2012-12-01 | 2013-03-28
75081-DE Kentucky Fossil | EB021432 | EB021432X | Emissions Particulate Monitor | 0 |  | 0 |  |  | 66720.12 | 173610 | -106889.88 | 2013-02-04 | 2013-05-31 | 2013-02-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021433 | EB021433X | Purchase Dredge for Pond Cleaning | 2644.34 |  | 2644.34 | 100% |  | 167911.56 | 256984 | -89072.44 | 2013-05-06 | 2013-12-21 | 2013-07-01 | 2014-01-31
75081-DE Kentucky Fossil | EB021434 | EB021434X | EB2 Precipitator T/R Sets | 0 |  | 0 |  |  | 52171.6 | 134425 | -82253.4 | 2013-04-03 | 2013-12-31 | 2013-04-01 | 2013-08-03
75081-DE Kentucky Fossil | EB021436 | EB021436X | Replace LBU Roof | 0 |  | 0 |  |  | 21739.94 | 33601 | -11861.06 | 2013-05-06 | 2013-12-31 | 2013-05-01 | 2013-07-15
75081-DE Kentucky Fossil | EB021438 | EB021438X | Replace IP Turbine Blades | 1027263.9 |  | 1027263.9 | 100% |  | 1345319.02 | 1142289 | 203030.02 | 2013-08-05 | 2014-12-05 | 2013-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021443 | EB021443X | LBU Hold & Close Drive Replacement | 211847.17 |  | 211847.17 | 100% |  | 243689.86 | 478370 | -234680.14 | 2013-08-27 | 2014-10-01 | 2013-10-01 | 2014-09-29
75081-DE Kentucky Fossil | EB021446 | EB021446X | Replace Lining in WSP Sludge Tank | 219623.72 |  | 219623.72 | 100% |  | 219996.21 | 315985 | -95988.79 | 2013-09-23 | 2014-07-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021448 | EB021448X | SSHO Partial Pendants - Mini Panels | 1213999.33 |  | 1213999.33 | 100% |  | 1634251.53 | 2712013 | -1077761.47 | 2013-10-17 | 2014-12-31 | 2013-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021457 | EB021457X | Paving Eastside Parking Lot | 0 |  | 0 |  |  | 65121.93 | 101930 | -36808.07 | 2013-08-27 | 2013-12-31 | 2013-08-01 | 2013-10-22
75081-DE Kentucky Fossil | EB021459 | EB021459X | Data Network Upgrade | 6356.91 |  | 6356.91 | 100% |  | 57380.69 | 97480 | -40099.31 | 2013-08-27 | 2015-03-31 | 2013-12-01 | 2014-09-30
75081-DE Kentucky Fossil | EB021460 | EB021460X | PCME PM CEMS Monitor | 102758.97 |  | 102758.97 | 100% |  | 102758.97 | 308070 | -205311.03 | 2014-02-20 | 2015-03-31 | 2014-05-01 | 2015-03-12
75081-DE Kentucky Fossil | EB021461 | EB021461X | Landfill Haul Road Drainage System | 31434.68 |  | 31434.68 | 100% |  | 62094.93 | 104270 | -42175.07 | 2013-09-26 | 2014-07-31 | 2013-12-01 | 2014-06-01
75081-DE Kentucky Fossil | EB021462 | EB021462X | 125 DC Station Battery 2 | 1819.14 |  | 1819.14 | 100% |  | 59344.9 | 93016 | -33671.1 | 2013-10-28 | 2014-03-31 | 2013-11-01 | 2014-06-23
75081-DE Kentucky Fossil | EB021463 | EB021463X | 2 Sec Air Water Sup Preheat Coils | 36269.26 |  | 36269.26 | 100% |  | 36269.26 | 70250 | -33980.74 | 2014-01-08 | 2014-03-31 | 2014-11-01 | 2014-02-22
75081-DE Kentucky Fossil | EB021465 | EB021465X | Replace 2SR-7 Transformer | 37056.19 |  | 37056.19 | 100% |  | 37056.19 | 58771 | -21714.81 | 2014-03-06 | 2015-03-31 | 2014-05-01 | 2014-08-20
75081-DE Kentucky Fossil | EB021466 | EB021466X | 2-2 SBAC Coolers and Controls | 193353.19 |  | 193353.19 | 100% |  | 193353.19 | 338329 | -144975.81 | 2014-05-27 | 2014-08-31 | 2014-05-01 | 2014-09-27
75081-DE Kentucky Fossil | EB021468 | EB021468X | Isophase Bus Wall Bushings | 209548.06 |  | 209548.06 | 100% |  | 209548.06 | 302597 | -93048.94 | 2014-05-23 | 2014-08-31 | 2014-05-01 | 2014-08-20
75081-DE Kentucky Fossil | EB021469 | EB021469X | Cooling Tower Motor Platforms | 38100.08 |  | 38100.08 | 100% |  | 38100.08 | 106326 | -68225.92 | 2014-05-27 | 2014-08-31 | 2014-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021470 | EB021470X | Data Network Upgrade | 57341.13 |  | 57341.13 | 100% |  | 57341.13 | 142704 | -85362.87 | 2014-10-23 | 2015-09-02 | 2014-11-01 | 2014-11-28
75081-DE Kentucky Fossil | EB021471 | EB021471X | Boiler Room Exhaust Fan Blades Set | 20556.48 |  | 20556.48 | 100% |  | 20556.48 | 52167 | -31610.52 | 2014-09-04 | 2014-12-23 | 2014-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021480 | EB021480X | Mercury CEMS | 171023.67 |  | 171023.67 | 100% |  | 171023.67 | 476412 | -305388.33 | 2014-09-04 | 2015-03-06 | 2014-09-01 | 2015-04-09
75081-DE Kentucky Fossil | EB021482 | EB021482X | CT Gearbox and Fan Blades 2-10 | 47607.18 |  | 47607.18 | 100% |  | 47607.18 | 78897 | -31289.82 | 2014-09-04 | 2014-08-31 | 2014-09-01 | 2014-11-20
75081-DE Kentucky Fossil | EB021486 | EB021486X | Replace Ash Sluice Pump Motor | 36570.97 |  | 36570.97 | 100% |  | 36570.97 | 55459 | -18888.03 | 2014-11-07 | 2015-06-30 | 2014-11-01 | 2015-03-16
75081-DE Kentucky Fossil | EB021487 | EB021487X | Cake Transfer Belt | 13703.73 |  | 13703.73 | 100% |  | 13703.73 | 20374 | -6670.27 | 2014-11-04 | 2014-11-28 | 2014-11-01 | 2015-01-21
75081-DE Kentucky Fossil | EB021488 | EB021488X | 30 Day Lime Silo Elec Bldg Roof | 4305.08 |  | 4305.08 | 100% |  | 4305.08 | 7235 | -2929.92 | 2014-11-04 | 2014-12-01 | 2014-11-01 | 2015-02-03
75081-DE Kentucky Fossil | EB021489 | EB021489X | 2-2 Fly Ash Silo to Silo Blowers | 60062.6 |  | 60062.6 | 100% |  | 60062.6 | 1072612 | -1012549.4 | 2014-12-08 | 2016-08-31 | 2014-12-01 | 2016-09-23
75081-DE Kentucky Fossil | EB021492 | EB021492X | TriState EB Parcels PP 29711 29690 | 538802.26 |  | 538802.26 | 100% |  | 538802.26 | 586108 | -47305.74 | 2014-12-31 | 2014-12-31 | 2014-12-01 | 2015-03-31
75081-DE Kentucky Fossil | EB1922 | EB02CTA13 | Cost to Achieve 2013 | 159.6 |  | 159.6 | 100% |  | 6003.2 | 9500 | -3496.8 | 2013-10-03 | 2014-12-31 | 2013-12-01 | 2014-03-31
75081-DE Kentucky Fossil | EB0822 | EB0822X | EBS U2 REPLACE CARDOX CONTROLS | 0 |  | 0 |  |  | 442775.02 | 599080 | -156304.98 | 2011-10-07 | 2012-08-24 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB1152 | EB1152X | FGD Landfill Conc Spillway | 0 |  | 0 |  |  | 62419.41 | 62578 | -158.59 | 2008-09-02 | 2009-03-31 | 2008-11-01 | 2008-12-31
75081-DE Kentucky Fossil | EB200531 | EB200531X | Thickener Tunnel Emerg Sump Pump | 0 |  | 0 |  |  | 110229.52 | 209037 | -98807.48 | 2008-09-02 | 2011-04-30 | 2008-11-01 | 2011-04-25
75081-DE Kentucky Fossil | EB201206 | EB201206X | Replace lower front wall Slope tube | 0 |  | 0 |  |  | 2780525.01 | 4190562 | -1410036.99 | 2009-01-26 | 2012-07-10 | 2009-07-01 | 2012-07-15
75081-DE Kentucky Fossil | EB201220 | EB201220X | Cooling Tower Motor Replace 08 | 0 |  | 0 |  |  | 94484.15 | 128010 | -33525.85 | 2008-07-09 | 2009-07-31 | 2008-08-01 | 2009-03-22
75081-DE Kentucky Fossil | EB201259 | EB201259X | Replace 1 CT Fan Assembly | 0 |  | 0 |  |  | 33498.15 | 83477 | -49978.85 | 2010-02-02 | 2011-01-04 | 2010-02-01 | 2010-08-14
75081-DE Kentucky Fossil | EB201333 | EB201333X | Retube Spare Hydrogen Cooler | 0 |  | 0 |  |  | 69629.15 | 120129 | -50499.85 | 2010-03-18 | 2010-12-01 | 2010-03-01 | 2010-08-07
75081-DE Kentucky Fossil | EB201341 | EB201341X | FGD Lab | 0 |  | 0 |  |  | 23931.67 | 26315 | -2383.33 | 2010-10-19 | 2012-08-14 | 2010-11-01 | 2011-03-08
75081-DE Kentucky Fossil | EB201344 | EB201344X | HVG Neutral Phase Bushing | 0 |  | 0 |  |  | 112373.23 | 283041 | -170667.77 | 2011-11-27 | 2013-04-24 | 2011-12-01 | 2012-07-20
75081-DE Kentucky Fossil | EB201348 | EB201348X | FGD Controls Upgrade | 0 |  | 0 |  |  | 3415236.25 | 3970493 | -555256.75 | 2010-12-20 | 2013-04-26 | 2010-12-01 | 2012-07-29
75081-DE Kentucky Fossil | EB201357 | EB201357X | Pulverizer Gbx Replace 1 of 6 | 0 |  | 0 |  |  | 233947.86 | 365449 | -131501.14 | 2012-02-17 | 2012-12-03 | 2012-02-01 | 2012-07-20
75081-DE Kentucky Fossil | EB201365 | EB201365X | Cooling Tower Breakr Repl PH1 | 0 |  | 0 |  |  | 222532.07 | 291225 | -68692.93 | 2010-02-15 | 2011-10-27 | 2010-03-01 | 2010-08-17
75081-DE Kentucky Fossil | EB201367 | EB201367X | CT BREAKER PHASE 2 | 0 |  | 0 |  |  | 404446.52 | 596961 | -192514.48 | 2011-10-20 | 2012-11-30 | 2011-11-01 | 2012-07-29
75081-DE Kentucky Fossil | EB201370 | EB201370X | Install Stack Lining | 2631555.3 |  | 2631555.3 | 100% |  | 6590758.75 | 10360344 | -3769585.25 | 2011-06-06 | 2014-08-01 | 2011-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB201374 | EB201374X | DCS Network Upgrade | 0 |  | 0 |  |  | 839877.54 | 978321 | -138443.46 | 2008-10-06 | 2010-05-24 | 2008-12-01 | 2009-08-25
75081-DE Kentucky Fossil | EB2922 | EB2922X | EB2-3rd Catalyst Bed-Addition | 0 |  | 0 |  |  | 1303087.13 | 2585054 | -1281966.87 | 2008-09-29 | 2009-08-20 | 2008-11-01 | 2009-08-29
75081-DE Kentucky Fossil | EBS01210 | EBS01210X | Filtrate Storage Tank Replacement | 280644.56 |  | 280644.56 | 100% |  | 330824.14 | 393318 | -62493.86 | 2013-09-10 | 2014-08-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EBS01212 | EBS01212X | Cooling Tower Gearbox 2009 | 0 |  | 0 |  |  | 252581.89 | 273031 | -20449.11 | 2009-02-05 | 2010-12-31 | 2009-02-01 | 2010-09-25
75081-DE Kentucky Fossil | EBS01213 | EBS01213X | Cooling Tower Gearbox 2010 | 0 |  | 0 |  |  | 319633.51 | 435882 | -116248.49 | 2009-04-17 | 2011-03-25 | 2009-05-01 | 2011-01-20
75081-DE Kentucky Fossil | EBS01216 | EBS01216X | Furnace Sidewall Weld Overlay | 0 |  | 0 |  |  | 903384.86 | 1069212 | -165827.14 | 2009-02-05 | 2019-12-01 | 2009-02-01 | 2009-08-15
75081-DE Kentucky Fossil | EBS01243 | EBS01243X | New East Bend Landfill | 150498.22 |  | 150498.22 | 100% |  | 166552.68 | 13966995.52 | -13800442.84 | 2013-11-19 | 2018-06-30 | 2013-12-01
75081-DE Kentucky Fossil | EBS01260 | EBS01260X | Sand Filter for WSP Serv Water | 0 |  | 0 |  |  | 28186.52 | 38177 | -9990.48 | 2008-07-09 | 2009-04-23 | 2008-09-01 | 2009-04-23
75081-DE Kentucky Fossil | EBS01261 | EBS01261X | Replace CBU Chains | 0 |  | 0 |  |  | 121020.66 | 181378 | -60357.34 | 2008-10-07 | 2010-08-15 | 2008-12-01 | 2010-08-17
75081-DE Kentucky Fossil | EBS01264 | EBS01264X | Filtered Water Pmp Replacement | 0 |  | 0 |  |  | 30048.92 | 50704 | -20655.08 | 2008-07-09 | 2009-09-21 | 2008-09-01 | 2009-05-27
75081-DE Kentucky Fossil | EBS01266 | EBS01266X | Repl Lime Conv Metal Detector | 2325.34 |  | 2325.34 | 100% |  | 29711.26 | 87248 | -57536.74 | 2013-08-01 | 2015-12-31 | 2013-09-01 | 2015-08-13
75081-DE Kentucky Fossil | EBS01277 | EBS01277X | ASH HOPPER DOWNCOMER REPLACEMT | 0 |  | 0 |  |  | 292221.11 | 358810 | -66588.89 | 2011-10-05 | 2012-10-01 | 2011-10-01 | 2012-07-20
75081-DE Kentucky Fossil | EBS01280 | EBS01280X | Deep Well Addition | 0 |  | 0 |  |  | 560388.55 | 530543 | 29845.55 | 2008-09-05 | 2010-01-31 | 2008-11-01 | 2010-02-05
75081-DE Kentucky Fossil | EBS01290 | EBS01290X | REPLACE CIRC PIP SAC ANODES | 0 |  | 0 |  |  | 139409.02 | 152815 | -13405.98 | 2011-10-07 | 2012-08-21 | 2011-10-01 | 2012-07-20
75081-DE Kentucky Fossil | EBS01315 | EBS01315X | Replace 2-2 WS Strainer | 0 |  | 0 |  |  | 143583.57 | 127793 | 15790.57 | 2009-04-22 | 2010-11-23 | 2009-07-01 | 2010-12-02
75081-DE Kentucky Fossil | EBS01317 | EBS01317X | Cooling Tower Motor Replace-09 | 0 |  | 0 |  |  | 175068.81 | 264223 | -89154.19 | 2009-06-23 | 2011-02-28 | 2009-06-01 | 2010-07-01
75081-DE Kentucky Fossil | EBS01319 | EBS01319X | Cooling Tower Motor Repl | 0 |  | 0 |  |  | 165913.64 | 282474 | -116560.36 | 2010-03-04 | 2011-12-31 | 2010-03-01 | 2011-02-05
75081-DE Kentucky Fossil | EBS01322 | EBS01322X | Replace RAT Bushings | 0 |  | 0 |  |  | 122951.63 | 195719 | -72767.37 | 2010-08-17 | 2011-09-30 | 2010-09-01 | 2011-07-14
75081-DE Kentucky Fossil | EBS01324 | EBS01324X | Bottom Turbine Oil Cooler | 0 |  | 0 |  |  | 114861.66 | 373255 | -258393.34 | 2008-11-11 | 2009-10-07 | 2009-02-01 | 2009-08-20
75081-DE Kentucky Fossil | EBS01328 | EBS01328X | Retire Turbine Doghouse | 0 |  | 0 |  |  | 1.83 | 7753 | -7751.17 | 2008-09-02 | 2008-10-31 | 2008-10-01 | 2009-03-01
75081-DE Kentucky Fossil | EBS01340 | EBS01340X | Replace Coal Handling Controls | 844624.91 |  | 844624.91 | 100% |  | 1387675.99 | 2246909 | -859233.01 | 2013-07-30 | 2014-12-31 | 2013-07-01 | 2014-09-29
75081-DE Kentucky Fossil | EBS01343 | EBS01343X | REPL ABS Pump Brkr Phase I | 0 |  | 0 |  |  | 182983.51 | 304495 | -121511.49 | 2012-11-22 | 2013-10-01 | 2012-12-01 | 2013-07-29
75081-DE Kentucky Fossil | EBS01344 | EBS01344X | Repl ABS Pump Brkrs Phase II | 1606.74 |  | 1606.74 | 100% |  | 149928.26 | 301066 | -151137.74 | 2012-11-23 | 2013-10-01 | 2012-12-01 | 2013-07-29
75081-DE Kentucky Fossil | EBS01349 | EBS01349X | Install CBU Drainage System | 0 |  | 0 |  |  | 97343.1 | 122373 | -25029.9 | 2008-09-02 | 2009-03-31 | 2008-10-01 | 2009-03-19
75081-DE Kentucky Fossil | EBS01352 | EBS01352X | Repl Emergency Pond Pumps | 0 |  | 0 |  |  | 297541.02 | 269096 | 28445.02 | 2012-08-31 | 2014-05-22 | 2012-09-01 | 2013-11-30
75081-DE Kentucky Fossil | EBS01356 | EBS01356X | Replace FGD Common Outlet Duct | 0 |  | 0 |  |  | 1184558.04 | 2703003 | -1518444.96 | 2008-09-19 | 2012-07-10 | 2008-10-01 | 2012-07-13
75081-DE Kentucky Fossil | EBS01364 | EBS01364X | SAH and PAH Gas Outlet Duct platfor | 0 |  | 0 |  |  | 31229.62 | 46278 | -15048.38 | 2010-09-16 | 2011-08-22 | 2010-11-01 | 2011-04-13
75081-DE Kentucky Fossil | EBS01374 | EBS01374X | REPLACE SEWAGE TREATMENT PLANT | 0 |  | 0 |  |  | 219250.96 | 294765 | -75514.04 | 2011-10-20 | 2013-02-28 | 2011-12-01 | 2013-03-28
75081-DE Kentucky Fossil | EBS01375 | EBS01375X | Rplc Transfer Tower Fire Det Syst | 0 |  | 0 |  |  | 153607.79 | 168413 | -14805.21 | 2012-11-21 | 2013-11-06 | 2012-12-01 | 2013-07-20
75081-DE Kentucky Fossil | EBS01376 | EBS01376X | FGD plenum PIT purge system | 0 |  | 0 |  |  | 40889.66 | 31210 | 9679.66 | 2009-04-14 | 2010-08-30 | 2009-04-01 | 2010-08-17
75081-DE Kentucky Fossil | EBS01379 | EBS01379X | Install New Trona Blower | 0 |  | 0 |  |  | 95083.85 | 32034 | 63049.85 | 2008-09-02 | 2009-11-01 | 2008-11-01 | 2009-12-03
75081-DE Kentucky Fossil | EBS01382 | EBS01382X | West Landfill Monitoring Wells | 0 |  | 0 |  |  | 150558.69 | 173717 | -23158.31 | 2008-08-24 | 2012-09-30 | 2008-11-01 | 2012-08-31
75081-DE Kentucky Fossil | EBS01383 | EBS01383X | Replace CEMS Shelter and DAS | 0 |  | 0 |  |  | 523455.62 | 867260 | -343804.38 | 2008-12-16 | 2009-06-23 | 2008-12-01 | 2009-03-31
75081-DE Kentucky Fossil | NIST1067 | INT1067A | MI P&L Analyzer Software | 7224.96 |  | 7224.96 | 100% |  | 7224.96 | 8014 | -789.04 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75081-DE Kentucky Fossil | NINT1067 | INT1067C | MI P&L Analyzer Software | 17545.19 |  | 17545.19 | 100% |  | 17545.19 | 27792 | -10246.81 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75081-DE Kentucky Fossil | PCTAIC910 | INT910C | Post Analysis (Genportal Addtl Uses | 39987.8 |  | 39987.8 | 100% |  | 39987.8 | 19037 | 20950.8 | 2014-07-04 | 2015-07-31 | 2014-07-01 | 2016-03-31
75081-DE Kentucky Fossil | MF601200 | MF601200X | SAH Racks & Pinion Gears Repl | 0 |  | 0 |  |  | 66502.26 | 80007 | -13504.74 | 2010-10-01 | 2011-07-06 | 2010-11-01 | 2011-02-21
75081-DE Kentucky Fossil | MU061200 | MU061200X | Replace 6 3 BFP Motor | 0 |  | 0 |  |  | 177463.48 | 185785 | -8321.52 | 2008-09-11 | 2008-12-31 | 2008-09-01 | 2008-12-31
75081-DE Kentucky Fossil | MU061201 | MU061201X | 6-2 BFP Motor Replace Rotor | 0 |  | 0 |  |  | 41284.97 | 76965 | -35680.03 | 2008-11-11 | 2009-05-01 | 2008-12-01 | 2009-06-17
75081-DE Kentucky Fossil | MU061236 | MU061236X | Exhauster Fan Replacement | 0 |  | 0 |  |  | 34972 | 43359 | -8387 | 2010-05-10 | 2010-09-30 | 2010-06-01 | 2010-06-24
75081-DE Kentucky Fossil | MU061238 | MU061238X | replace 6-1 ID fan motor | 0 |  | 0 |  |  | 211104.15 | 279120 | -68015.85 | 2010-05-07 | 2010-12-31 | 2010-06-01 | 2010-07-01
75081-DE Kentucky Fossil | MU061240 | MU061240X | FWH Safety Relief Tank | 0 |  | 0 |  |  | 54664.24 | 89889 | -35224.76 | 2010-10-18 | 2011-07-29 | 2010-11-01 | 2011-02-19
75081-DE Kentucky Fossil | MU061241 | MU061241X | CO2 Analyzer Replacement | 0 |  | 0 |  |  | 10716.44 | 21380 | -10663.56 | 2010-11-09 | 2012-11-24 | 2010-12-01 | 2011-05-10
75081-DE Kentucky Fossil | MU061249 | MU061249X | Miami Fort U6 EAM | 0 |  | 0 |  |  | 205409.1 | 204448.97 | 960.13 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2011-11-30
75081-DE Kentucky Fossil | MU601212 | MU601212X | Operator Console Replacement | 0 |  | 0 |  |  | 504274.86 | 513688 | -9413.14 | 2010-02-02 | 2011-03-31 | 2010-02-01 | 2011-02-21
75081-DE Kentucky Fossil | MU601236 | MU601236X | Fire Detection Sys Install | 0 |  | 0 |  |  | 100337.73 | 122554 | -22216.27 | 2009-03-03 | 2009-12-22 | 2009-03-01 | 2009-09-05
75081-DE Kentucky Fossil | MU601239 | MU601239A | Asbestos Abatement Replacement | 1844.88 |  | 1844.88 | 100% |  | 39582.61 | 0 | 39582.61 | 2009-05-06 | 2014-12-31 | 2009-05-01 | 2015-03-31
75081-DE Kentucky Fossil | FPCTAITKY | PCTAI1402 | Consolidated Fuels Mgt Pltfrm KY PH | 0 |  | 0 |  |  | 43062.05 | 62769.7 | -19707.65 | 2013-12-12 | 2013-03-31 | 2013-12-01 | 2013-03-31
75081-DE Kentucky Fossil | FPCTAITMF | PCTAI1403 | Consolidated Fuels Mgmt Pltfrm MF P | 0 |  | 0 |  |  | 17072.65 | 17052.43 | 20.22 | 2013-12-12 | 2013-03-31 | 2013-12-01 | 2013-03-31
75081-DE Kentucky Fossil | PCTAIT31 | PCTAI31 | PGO Long Range Planning Tool | 42219.61 |  | 42219.61 | 100% |  | 42219.61 | 16319 | 25900.61 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081-DE Kentucky Fossil | PCTAIT31 | PCTAI31J | PGO Long Range Planning Tool | 996.57 |  | 996.57 | 100% |  | 996.57 | 60069 | -59072.43 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081-DE Kentucky Fossil | PCTAITF2 | PCTAITH21 | INT164 Hardware | 3789.81 |  | 3789.81 | 100% |  | 3789.81 | 31034 | -27244.19 | 2014-07-14 | 2016-02-29 | 2014-09-01 | 2016-05-31
75081-DE Kentucky Fossil | PCTAITF2 | PCTAITS21 | INT164 Software | 73777.56 |  | 73777.56 | 100% |  | 73777.56 | 219741 | -145963.44 | 2014-07-14 | 2016-02-29 | 2014-08-01 | 2016-05-31
75081-DE Kentucky Fossil | EBS01204 | REBS01204 | EBS-Landfill Cover | 0 |  | 0 |  |  | 246.3 | 0 | 246.3 | 2007-03-21 | 2010-04-30 | 2008-10-01 | 2010-04-30
75081-DE Kentucky Fossil | EBS01312 | REBS01312 | Remove Bypass Ducts | 0 |  | 0 |  |  | 68197.58 | 26286 | 41911.58 | 2008-03-12 | 2009-06-30 | 2008-10-01 | 2008-07-26
75082-DE Kentucky Combustion Turbin | NINT1067 | INT1067C | MI P&L Analyzer Software | 19343.47 |  | 19343.47 | 100% |  | 19343.47 | 21400 | -2056.53 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75082-DE Kentucky Combustion Turbin | PCTAIC910 | INT910C | Post Analysis (Genportal Addtl Uses | 26206.21 |  | 26206.21 | 100% |  | 26206.21 | 53958 | -27751.79 | 2014-07-04 | 2015-07-31 | 2014-07-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT137 | AIT13709H | Gas ETRM | 225.36 |  | 225.36 | 100% |  | 225.36 | 390.53 | -165.17 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082-DE Kentucky Combustion Turbin | PCTAIT137 | AIT13709S | Gas ETRM | 29762.94 |  | 29762.94 | 100% |  | 29762.94 | 28529.33 | 1233.61 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21810H | FSO Forecasting Consolidation | 496.13 |  | 496.13 | 100% |  | 496.13 | 1531.43 | -1035.3 | 2014-04-11 | 2015-12-31 | 2014-06-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21810S | FSO Forecasting Consolidation | 37461.47 |  | 37461.47 | 100% |  | 37461.47 | 38170.08 | -708.61 | 2014-04-11 | 2015-12-31 | 2014-06-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT31 | PCTAI31 | PGO Long Range Planning Tool | 26019.14 |  | 26019.14 | 100% |  | 26019.14 | 46253 | -20233.86 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75082-DE Kentucky Combustion Turbin | PCTAITF2 | PCTAITH21 | INT164 Hardware | 3026.21 |  | 3026.21 | 100% |  | 3026.21 | 24784 | -21757.79 | 2014-07-14 | 2016-02-29 | 2014-09-01 | 2016-05-31
75082-DE Kentucky Combustion Turbin | PCTAITF2 | PCTAITS21 | INT164 Software | 102196.51 |  | 102196.51 | 100% |  | 102196.51 | 175487 | -73290.49 | 2014-07-14 | 2016-02-29 | 2014-08-01 | 2016-05-31
75082-DE Kentucky Combustion Turbin | WD011201 | WD011201X | WGS Unit 1 Excitation Controls | 0 |  | 0 |  |  | 204495.39 | 216144 | -11648.61 | 2011-09-20 | 2012-12-31 | 2011-10-01 | 2013-01-05
75082-DE Kentucky Combustion Turbin | WD021200 | WD021200X | CT2 REPLACE PROP. BLR CONTRL | 0 |  | 0 |  |  | 38713.45 | 40215 | -1501.55 | 2008-10-12 | 2008-12-31 | 2008-12-01 | 2009-02-27
75082-DE Kentucky Combustion Turbin | WD021201 | WD021201X | WGS Unit 2 Excitation Controls | 0 |  | 0 |  |  | 206734.46 | 216144 | -9409.54 | 2011-09-20 | 2012-12-31 | 2011-10-01 | 2013-01-16
75082-DE Kentucky Combustion Turbin | WD031200 | WD031200X | WGS No3 Comp Blade Replacement | 0 |  | 0 |  |  | 1050679.03 | 899845 | 150834.03 | 2009-08-18 | 2009-12-31 | 2009-08-01 | 2009-12-23
75082-DE Kentucky Combustion Turbin | WD031201 | WD031201X | WGS Unit 3 Excitation Controls | 0 |  | 0 |  |  | 387366.01 | 214039 | 173327.01 | 2013-01-31 | 2013-12-31 | 2013-02-01 | 2014-01-15
75082-DE Kentucky Combustion Turbin | WD041200 | WD041200X | WGS Unit 4 Excitation Controls | 4055.02 |  | 4055.02 | 100% |  | 368174.97 | 214039 | 154135.97 | 2013-02-07 | 2014-04-30 | 2013-02-01 | 2014-01-15
75082-DE Kentucky Combustion Turbin | WD051202 | WD051202X | WGS Unit 5 Excitation Controls | 125519.05 |  | 125519.05 | 100% |  | 260739.19 | 217275 | 43464.19 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082-DE Kentucky Combustion Turbin | WD061200 | WD061200X | WGS Unit 6 Excitation Controls | 138216.03 |  | 138216.03 | 100% |  | 272899.05 | 220214 | 52685.05 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082-DE Kentucky Combustion Turbin | WD061203 | WD061203X | WGS- U6 Compressor Blade Replc | 0 |  | 0 |  |  | 349669.18 | 2097039 | -1747369.82 | 2012-05-30 | 2012-12-31 | 2012-06-01 | 2012-09-29
75082-DE Kentucky Combustion Turbin | WD101200 | WD101200X | WGS-CT1 AA Module HVAC Units | 205.14 |  | 205.14 | 100% |  | 66542.99 | 33119 | 33423.99 | 2013-08-18 | 2015-04-25 | 2013-12-01 | 2014-03-16
75082-DE Kentucky Combustion Turbin | WD101201 | WD101201X | WGS-CT1 DD Module HVAC Unit | 257.41 |  | 257.41 | 100% |  | 29396.05 | 14963 | 14433.05 | 2013-08-18 | 2015-05-27 | 2013-12-01 | 2014-03-16
75082-DE Kentucky Combustion Turbin | WD101206 | CWD101206 | WGS CT1 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 19950.75 | 38150 | -18199.25 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-16
75082-DE Kentucky Combustion Turbin | WD101209 | WD101209X | WGS CT 1 Overhaul #2 | 0 |  | 0 |  |  | 3145560.71 | 9754682 | -6609121.29 | 2011-11-11 | 2017-08-21 | 2011-12-01 | 2017-08-12
75082-DE Kentucky Combustion Turbin | WD201202 | D1487 | WGS-CT 24V Repl Battery Bank | 0 |  | 0 |  |  | 8047.88 | 16611 | -8563.12 | 2007-08-26 | 2008-03-31 | 2007-11-01 | 2008-02-26
75082-DE Kentucky Combustion Turbin | WD201203 | CWD201203 | WGS CT2 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 20220.8 | 38150 | -17929.2 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-16
75082-DE Kentucky Combustion Turbin | WD201207 | WD201207X | WGS CT2 Major C Overhaul No1 | 0 |  | 0 |  |  | 8777822.09 | 8128498 | 649324.09 | 2010-09-28 | 2011-09-01 | 2010-11-01 | 2011-08-27
75082-DE Kentucky Combustion Turbin | WD301204 | WD301204X | WGS CT 3 Overhaul #2 | 0 |  | 0 |  |  | 7682178.86 | 8720533 | -1038354.14 | 2011-11-11 | 2012-12-31 | 2011-11-01 | 2012-08-23
75082-DE Kentucky Combustion Turbin | WD401203 | CWD401203 | WGS CT4 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 20551.77 | 38150 | -17598.23 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-19
75082-DE Kentucky Combustion Turbin | WD501200 | WD301200X | WGS-CT3 AA Module HVAC Units | 0 |  | 0 |  |  | 20730.67 | 27396 | -6665.33 | 2008-10-27 | 2008-12-31 | 2008-12-01 | 2009-02-05
75082-DE Kentucky Combustion Turbin | WD501201 | WD301201X | WGS-CT3 DD Module HVAC Unit | 0 |  | 0 |  |  | 8171.87 | 12601 | -4429.13 | 2008-10-27 | 2008-12-31 | 2008-12-01 | 2009-02-05
75082-DE Kentucky Combustion Turbin | WD501202 | WD501202X | WGS CT5 Major C Overhaul No2 | 0 |  | 0 |  |  | 7787980.27 | 9627259 | -1839278.73 | 2009-07-27 | 2010-03-31 | 2009-08-01 | 2010-03-09
75082-DE Kentucky Combustion Turbin | WD601200 | CWD601200 | WGS CT6 AA Module HVAC Units | 0 |  | 0 |  |  | 25254.92 | 1 | 25253.92 | 2007-10-04 | 2007-12-31 | 2007-12-01 | 2008-07-15
75082-DE Kentucky Combustion Turbin | WD601201 | CWD601201 | WGS CT6 DD Module HVAC Unit | 0 |  | 0 |  |  | 8503.12 | 15228 | -6724.88 | 2007-10-04 | 2007-12-31 | 2007-12-01 | 2008-07-09
75082-DE Kentucky Combustion Turbin | WD601206 | WD601206X | WGS CT6 Major C Overhaul No2 | 0 |  | 0 |  |  | 7960271.15 | 4552898 | 3407373.15 | 2009-12-22 | 2010-11-18 | 2009-12-01 | 2010-07-29
75082-DE Kentucky Combustion Turbin | WDC01201 | CWDC01201 | WGS CT1-6 CEMS XML EDR Upgrade | 0 |  | 0 |  |  | 69278.98 | 92169 | -22890.02 | 2008-02-06 | 2009-10-27 | 2008-03-01 | 2009-02-27
75082-DE Kentucky Combustion Turbin | WDC01204 | CWDC01204 | WGS RO ANALYZER REPLACEMENT | 0 |  | 0 |  |  | 27399.42 | 46944 | -19544.58 | 2007-11-14 | 2008-06-21 | 2007-12-01 | 2008-05-07
75082-DE Kentucky Combustion Turbin | WDC01208 | WDC01208X | WGS CT1-6 GEN PROT PANEL REPL | 0 |  | 0 |  |  | 1026562.98 | 880363 | 146199.98 | 2008-09-07 | 2011-12-31 | 2008-09-01 | 2012-03-07
75082-DE Kentucky Combustion Turbin | WDC01209 | CWDC01209 | INSTALL SYNC CHECK RELAY | 0 |  | 0 |  |  | 5782.47 | 46586 | -40803.53 | 2008-03-06 | 2009-05-11 | 2008-04-01 | 2009-04-01
75082-DE Kentucky Combustion Turbin | WDC01210 | WDC01210X | WDC-CAUSTIC TANK REPL | 0 |  | 0 |  |  | 117963.66 | 111095 | 6868.66 | 2008-10-12 | 2009-10-25 | 2008-11-01 | 2009-04-08
75082-DE Kentucky Combustion Turbin | WDC01217 | WDC01217X | WGS U1-6 Prop Blr Cntrl Repl | 0 |  | 0 |  |  | 172189.84 | 220432 | -48242.16 | 2011-08-23 | 2012-05-01 | 2011-10-01 | 2012-05-08
75082-DE Kentucky Combustion Turbin | WDC01223 | WDC01223X | Propane Piping Upgrade | 0 |  | 0 |  |  | 92648.07 | 49058 | 43590.07 | 2008-07-14 | 2008-12-31 | 2008-07-01 | 2008-12-15
75082-DE Kentucky Combustion Turbin | WDC01225 | WDC01225X | WGS Blk Start Controls Cab AC | 0 |  | 0 |  |  | 7263.33 | 10214 | -2950.67 | 2009-05-12 | 2009-12-31 | 2009-07-01 | 2009-09-19
75082-DE Kentucky Combustion Turbin | WDC01227 | WDC01227X | Convert WDS Phone Sys to VOIP | 0 |  | 0 |  |  | 79247.12 | 122272 | -43024.88 | 2011-09-13 | 2011-12-31 | 2011-09-01 | 2012-02-18
75082-DE Kentucky Combustion Turbin | WDC01229 | WDC01229X | IT6000 Cyber Security | 0 |  | 0 |  |  | 7406.61 | 14785 | -7378.39 | 2009-11-19 | 2009-12-31 | 2009-12-01 | 2010-02-20
75082-DE Kentucky Combustion Turbin | WDC01235 | WDC01235X | Replace Air Compressor B | 0 |  | 0 |  |  | 111830.9 | 90025 | 21805.9 | 2010-09-20 | 2011-04-30 | 2010-09-01 | 2011-04-19
75082-DE Kentucky Combustion Turbin | WDC01236 | WDC01236X | Replace Site Radios | 0 |  | 0 |  |  | 71420.41 | 45491 | 25929.41 | 2010-11-12 | 2011-12-31 | 2010-12-01 | 2011-12-13
75082-DE Kentucky Combustion Turbin | WDC01237 | WDC01237X | Gas Supply RTU | 29344.08 |  | 29344.08 | 100% |  | 144852.48 | 165623 | -20770.52 | 2012-02-15 | 2013-12-31 | 2012-02-01 | 2014-08-05
75082-DE Kentucky Combustion Turbin | WDC01241 | WDC01241X | Black Start Diesel Generator | 0 |  | 0 |  |  | 2320125.59 | 1907605 | 412520.59 | 2011-11-01 | 2013-12-31 | 2011-12-01 | 2013-08-18
75082-DE Kentucky Combustion Turbin | WDC01243 | WDC01243X | UVIR Propane Fire Prot Repl | 0 |  | 0 |  |  | 169784.14 | 184610 | -14825.86 | 2012-08-30 | 2013-03-31 | 2012-08-01 | 2013-01-18
75082-DE Kentucky Combustion Turbin | WDC01244 | WDC01244X | Sewer Discharge to Butler Co | 126102.77 |  | 126102.77 | 100% |  | 911953.83 | 533017 | 378936.83 | 2013-03-24 | 2014-08-25 | 2013-03-01 | 2014-11-01
75082-DE Kentucky Combustion Turbin | WDC01245 | WDC01245X | Network Firewall Upgrade | 0 |  | 0 |  |  | 10396.3 | 18462 | -8065.7 | 2011-09-06 | 2012-07-27 | 2011-10-01 | 2012-06-29
75082-DE Kentucky Combustion Turbin | WDC01247 | WDC01247X | Woodsdale EAM | 0 |  | 0 |  |  | 596309.5 | 596309.49 | 0.01 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2010-01-31
75082-DE Kentucky Combustion Turbin | WDC01248 | WDC01248X | Platform Ladder Swing Gates | 0 |  | 0 |  |  | 88738.57 | 44763 | 43975.57 | 2012-12-14 | 2013-12-31 | 2012-12-01 | 2014-01-31
75082-DE Kentucky Combustion Turbin | WDC01250 | WDC01250X | Diesel Fire Pump Controls | 0 |  | 0 |  |  | 17595.12 | 18229 | -633.88 | 2012-04-02 | 2012-09-30 | 2012-04-01 | 2012-04-25
75082-DE Kentucky Combustion Turbin | WDC01251 | WDC01251X | UPS Battery Replacement | 0 |  | 0 |  |  | 132075.45 | 100463 | 31612.45 | 2012-08-09 | 2012-12-31 | 2012-08-01 | 2012-12-14
75082-DE Kentucky Combustion Turbin | WDC01252 | WDC01252X | Admin Building Roof Replacement | 11264.34 |  | 11264.34 | 100% |  | 177871.24 | 243442 | -65570.76 | 2013-08-18 | 2013-12-31 | 2013-09-01 | 2014-02-15
75082-DE Kentucky Combustion Turbin | WDC01254 | WDC01254X | Stack Lighting Replacement | -360.84 |  | -360.84 | 100% |  | 52374.19 | 42673 | 9701.19 | 2013-08-18 | 2015-09-25 | 2013-11-01 | 2014-02-15
75082-DE Kentucky Combustion Turbin | WDC01257 | WDC01257X | WGS - U1-6 EHC System Replacement | 95381.84 |  | 95381.84 | 100% |  | 232722.44 | 244418 | -11695.56 | 2013-04-15 | 2015-06-30 | 2013-05-01 | 2015-07-10
75082-DE Kentucky Combustion Turbin | WDC01258 | WDC01258X | IT Uplift Project | 11831.8 |  | 11831.8 | 100% |  | 65751.56 | 56730 | 9021.56 | 2012-12-09 | 2015-03-31 | 2012-12-01 | 2015-03-18
75082-DE Kentucky Combustion Turbin | WDC01260 | WDC01260X | Admin Building HVAC Replacement | 81422.9 |  | 81422.9 | 100% |  | 81422.9 | 70725 | 10697.9 | 2014-06-16 | 2015-01-15 | 2014-06-01 | 2015-02-21
75082-DE Kentucky Combustion Turbin | WDC01262 | WDC01262X | Security Camera Upgrade | 44107.03 |  | 44107.03 | 100% |  | 106384.26 | 110085 | -3700.74 | 2013-09-26 | 2014-11-01 | 2013-10-01 | 2014-12-26
75082-DE Kentucky Combustion Turbin | WDCM1201 | WDCM1201X | RO Membrane Replacement | 0 |  | 0 |  |  | 235492.63 | 256876 | -21383.37 | 2012-11-03 | 2013-02-28 | 2012-12-01 | 2013-03-13
75082-DE Kentucky Combustion Turbin | WDCM1205 | WDCM1205X | Station Outside Lighting | 19504.87 |  | 19504.87 | 100% |  | 55049.87 | 74830 | -19780.13 | 2013-08-18 | 2014-03-30 | 2013-10-01 | 2014-05-21
75082-DE Kentucky Combustion Turbin | WDCM1206 | WDCM1206X | DC Voltage Monitoring System | 69862.5 |  | 69862.5 | 100% |  | 69862.5 | 120950 | -51087.5 | 2014-04-11 | 2015-03-31 | 2014-05-01 | 2015-09-19
75082-DE Kentucky Combustion Turbin | WG0244 | CWG0244 | WGS-CT4 Major C Overhaul | 0 |  | 0 |  |  | 6943543.25 | 7736194 | -792650.75 | 2007-08-05 | 2009-04-15 | 2007-12-01 | 2009-05-16
75082-DE Kentucky Combustion Turbin | WGS01202 | WGS01202X | WGS CT1-6 WDPF Controls Rplcmt | 0 |  | 0 |  |  | 2093936.21 | 1963732 | 130204.21 | 2011-09-08 | 2012-12-31 | 2011-09-01 | 2012-08-18
75082-DE Kentucky Combustion Turbin | WGS01204 | WGS01204X | CT1 6 Egatrol Replacement | 0 |  | 0 |  |  | 3034940.84 | 3382262 | -347321.16 | 2010-08-24 | 2012-02-29 | 2010-09-01 | 2012-03-02
75082-DE Kentucky Combustion Turbin | WGS01205 | CWGS01205 | Security Camera System | 0 |  | 0 |  |  | 19811.72 | 2 | 19809.72 | 2007-01-04 | 2007-06-30 | 2007-01-01 | 2007-11-30
75082-DE Kentucky Combustion Turbin | WGS01208 | WGS01208X | Cyber Security | 0 |  | 0 |  |  | 1013820.32 | 1021367 | -7546.68 | 2010-09-27 | 2012-02-28 | 2010-10-01 | 2012-03-02
75084-DE Kentucky Power Deliv - Ele | 75084 | RETCOV | Retire Covington | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-12-20 | 2013-01-05 | 2012-12-01 | 2013-04-05
75084-DE Kentucky Power Deliv - Ele | 75084 | SFTWRE | Software Retirements-Asset Use | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-09-20 | 2026-03-30 | 2012-09-01
75084-DE Kentucky Power Deliv - Ele | 100FACB4 | D3597 | Upgrade Erlanger Storm System | 0 |  | 0 |  |  | 57417.18 | 38692 | 18725.18 | 2008-05-30 | 2008-12-31 | 2008-09-01 | 2008-11-10
75084-DE Kentucky Power Deliv - Ele | 107DSTOH | G1407 | ROLLUP PLH IK_KY_2008 | 0 |  | 0 |  |  | 4300519.49 | 0 | 4300519.49 | 2010-10-27 | 2010-03-31 | 2010-10-01 | 2010-03-31
75084-DE Kentucky Power Deliv - Ele | 114ZUG | D2553 | pp 966522 RR HARDIN | 0 |  | 0 |  |  | 30263.28 | 18092 | 12171.28 | 2008-01-20 | 2050-12-31 | 2008-02-01 | 2009-01-21
75084-DE Kentucky Power Deliv - Ele | 302G8860 | C9599 | White Tower TB 2 Transmission | 0 |  | 0 |  |  | 80216.74 | 81470 | -1253.26 | 2007-04-17 | 2008-05-31 | 2007-05-01 | 2008-05-31
75084-DE Kentucky Power Deliv - Ele | 302H9041 | D1628 | Kenton Sub Sell Excess Prop | 0 |  | 0 |  |  | 0 | 1 | -1 | 2007-09-19 | 2008-12-31 | 2007-09-01 | 2008-01-15
75084-DE Kentucky Power Deliv - Ele | 303G8834 | D3543 | Covington Area-new Substation | 1561.58 |  | 1561.58 | 100% |  | 967794.98 | 1512745 | -544950.02 | 2008-05-20 | 2009-02-14 | 2008-05-01 | 2008-11-14
75084-DE Kentucky Power Deliv - Ele | 303G8848 | C9075 | Atlas Sub Repl Regulators | 0 |  | 0 |  |  | 271497.16 | 137087 | 134410.16 | 2007-01-10 | 2008-11-15 | 2007-07-01 | 2008-07-10
75084-DE Kentucky Power Deliv - Ele | 303G8901 | G7533 | Latonia Sub - Retire & Remove | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-05-15 | 2014-03-31 | 2014-08-01 | 2013-09-06
75084-DE Kentucky Power Deliv - Ele | 303G8919 | D3495 | KY Univ Inst New 22/4 MVA Xfmr | 0 |  | 0 |  |  | 2036293.53 | 1433432 | 602861.53 | 2008-05-20 | 2010-09-01 | 2008-08-01 | 2010-08-25
75084-DE Kentucky Power Deliv - Ele | 303G8919 | E3752 | Wilder Sub Retire DT Equipment | 0 |  | 0 |  |  | -1.5916e-12 | 1 | -1 | 2009-01-21 | 2010-12-01 | 2009-12-01 | 2010-09-18
75084-DE Kentucky Power Deliv - Ele | 303G8919 | E3753 | Silver Grove Sub Retire DT Equip | 0 |  | 0 |  |  | -3.7517e-12 | 1 | -1 | 2009-01-21 | 2010-12-01 | 2009-12-01 | 2010-09-03
75084-DE Kentucky Power Deliv - Ele | 303H9052 | D2187 | Hebron Install 22/4MVA Xfmr | 0 |  | 0 |  |  | 1497635.9 | 1031892 | 465743.9 | 2007-12-04 | 2009-09-01 | 2008-02-01 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | 303J9130 | D3431 | Richwood TB1 Install Breaker | 0 |  | 0 |  |  | 274597.65 | 85981 | 188616.65 | 2008-05-02 | 2009-09-01 | 2008-06-01 | 2009-09-12
75084-DE Kentucky Power Deliv - Ele | 303J9142 | D3694 | Kenton Relocate Driveway | 0 |  | 0 |  |  | 116611.85 | 21253 | 95358.85 | 2008-06-16 | 2009-03-31 | 2008-07-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | 303ZANLG | E1995 | Hebron Analog to Digital | 0 |  | 0 |  |  | 11503.48 | 30000 | -18496.52 | 2008-10-30 | 2010-03-31 | 2009-01-01 | 2009-07-16
75084-DE Kentucky Power Deliv - Ele | 304G8909 | C9068 | PP872798 WHITE TOWER F5967 | 0 |  | 0 |  |  | 75276.69 | 42350 | 32926.69 | 2007-01-07 | 2008-12-01 | 2007-03-01 | 2009-04-09
75084-DE Kentucky Power Deliv - Ele | 304H9033 | D1596 | PP936435 F965 UPRATE 100 C | 5535.81 |  | 5535.81 | 100% |  | 156331.49 | 146838.77 | 9492.72 | 2007-09-14 | 2011-03-31 | 2009-08-01 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9021 | ULH&P 2005 New Business | 0 |  | 0 |  |  | -2062970.85 | 2057265 | -4120235.85 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9115 | PP 863371/JOE GROESCHEN | 0 |  | 0 |  |  | -2331.3 | 5958 | -8289.3 | 2007-01-16 | 2050-12-31 | 2007-01-01 | 2007-03-26
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9737 | PP 900903 - JOE FRICKE | 0 |  | 0 |  |  | 45685.81 | 1 | 45684.81 | 2007-05-04 | 2050-12-31 | 2007-08-01 | 2007-09-18
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9850 | PP 905263 - SANDY CONNLEY | 0 |  | 0 |  |  | 214646.51 | 99195 | 115451.51 | 2007-05-20 | 2050-12-31 | 2007-06-01 | 2008-01-08
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9888 | PP 892193/DONNA CARMACK | 0 |  | 0 |  |  | 60160.94 | 71110 | -10949.06 | 2007-05-31 | 2050-12-31 | 2007-06-01 | 2007-12-18
75084-DE Kentucky Power Deliv - Ele | 310ZNB | D1912 | PP 879351 - M Billow | 0 |  | 0 |  |  | 0 | 45471 | -45471 | 2007-10-25 | 2050-12-31 | 2007-11-01 | 2008-03-06
75084-DE Kentucky Power Deliv - Ele | 310ZNB | D2771 | PP 907295/MICHAEL SMITH | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-02-08 | 2050-12-31 | 2008-02-01 | 2008-10-16
75084-DE Kentucky Power Deliv - Ele | 312ZLEL | ZE083 | OLE LIGHTING South ULHP CP3 | 0 |  | 0 |  |  | 0 | 1 | -1 | 2007-12-20 | 2009-04-01 | 2008-01-01
75084-DE Kentucky Power Deliv - Ele | 312ZLL | C9025 | ULH&P 2005 Lighting | 0 |  | 0 |  |  | -300872.38 | 300040 | -600912.38 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314G8757 | C9060 | PP872754 DAYTON 42 UNDERGRND | 0 |  | 0 |  |  | 0 | 36886 | -36886 | 2007-01-07 | 2008-12-01 | 2007-08-01 | 2008-05-19
75084-DE Kentucky Power Deliv - Ele | 314G8764 | C9062 | PP872756 DAYTON 43 UNDERGROUND | 0 |  | 0 |  |  | 120235.74 | 43139 | 77096.74 | 2007-01-07 | 2008-12-01 | 2008-04-01 | 2008-06-02
75084-DE Kentucky Power Deliv - Ele | 314G8764 | C9063 | PP872757 DAYTON 43 EXITS OH | 0 |  | 0 |  |  | 245210.98 | 3059 | 242151.98 | 2007-01-07 | 2008-12-01 | 2007-08-01 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | 314G8840 | D1639 | PP938045 COVINGTON 41 OH PART | 0 |  | 0 |  |  | 0 | 50359 | -50359 | 2007-09-20 | 2009-04-30 | 2008-02-01 | 2009-01-28
75084-DE Kentucky Power Deliv - Ele | 314G8840 | D1640 | PP938046 COVINGTON 41 UG PART | 0 |  | 0 |  |  | 890658.52 | 47242 | 843416.52 | 2007-09-20 | 2009-04-30 | 2007-11-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8844 | D1641 | PP938072 Covington 42- OH part | 0 |  | 0 |  |  | 0 | 50359 | -50359 | 2007-09-20 | 2008-12-01 | 2008-02-01 | 2009-01-17
75084-DE Kentucky Power Deliv - Ele | 314G8844 | D1642 | PP938073 Covington 42- UG part | 0 |  | 0 |  |  | 214376.63 | 47242 | 167134.63 | 2007-09-20 | 2008-12-01 | 2007-12-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8846 | D1643 | PP938163 Covington 43- OH part | 0 |  | 0 |  |  | 333618.3 | 300256.2 | 33362.1 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-11-14
75084-DE Kentucky Power Deliv - Ele | 314G8846 | D1644 | PP938164 Covington 43- UG part | 0 |  | 0 |  |  | 210161 | 47242 | 162919 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8857 | D2914 | PP974771 WHITE TOWER 41 RECON | 0 |  | 0 |  |  | 276117.72 | 275058 | 1059.72 | 2008-02-24 | 2010-09-01 | 2008-07-01 | 2010-10-09
75084-DE Kentucky Power Deliv - Ele | 314G8865 | D1309 | PP924061 WHITE TOWER 43 UG | 0 |  | 0 |  |  | 34903.51 | 31793 | 3110.51 | 2007-07-31 | 2008-12-31 | 2007-10-01 | 2008-06-27
75084-DE Kentucky Power Deliv - Ele | 314G8867 | C9067 | PP872787 WHITE TOWER 42 | 0 |  | 0 |  |  | 520813.77 | 486933 | 33880.77 | 2007-01-07 | 2008-12-31 | 2007-10-01 | 2008-09-27
75084-DE Kentucky Power Deliv - Ele | 314G8867 | D1310 | PP924057 WHITE TOWER 42 UG | 0 |  | 0 |  |  | 46150.46 | 1 | 46149.46 | 2007-07-31 | 2008-12-31 | 2007-10-01 | 2008-06-27
75084-DE Kentucky Power Deliv - Ele | 314G8867 | D2526 | White Tower 42 | 0 |  | 0 |  |  | 0 | 41272 | -41272 | 2008-01-15 | 2008-09-27 | 2008-01-01 | 2008-09-27
75084-DE Kentucky Power Deliv - Ele | 314G8900 | G4034 | Aug 44 Ext Conv Latonia 4kV | 0 |  | 0 |  |  | 665967.65 | 298387.83 | 367579.82 | 2011-07-13 | 2012-04-30 | 2011-07-01 | 2012-04-28
75084-DE Kentucky Power Deliv - Ele | 314G8914 | E6225 | KY Univ 43 New Feeder | 0 |  | 0 |  |  | 10689.14 | 708735 | -698045.86 | 2009-05-07 | 2010-10-01 | 2009-05-01
75084-DE Kentucky Power Deliv - Ele | 314G8914 | E6226 | KY Univ 43 UG Cable and Conduit | 4415.11 |  | 4415.11 | 100% |  | 1382283.91 | 1426651 | -44367.09 | 2009-05-07 | 2010-10-01 | 2009-05-01 | 2010-10-02
75084-DE Kentucky Power Deliv - Ele | 314H9053 | D2908 | PP974767 HEBRON 43 | 0 |  | 0 |  |  | 365524.39 | 224676 | 140848.39 | 2008-02-24 | 2009-09-01 | 2008-06-01 | 2009-10-14
75084-DE Kentucky Power Deliv - Ele | 314H9053 | E1996 | HEBRON 43 -Install Conduit & Cable | 0 |  | 0 |  |  | 359675.59 | 326800 | 32875.59 | 2008-10-30 | 2009-09-01 | 2008-12-01 | 2009-10-14
75084-DE Kentucky Power Deliv - Ele | 314H9054 | D2895 | PP974383 HEBRON 44 EXTEND OH | 0 |  | 0 |  |  | 0 | 70487 | -70487 | 2008-02-22 | 2012-12-31 | 2009-05-01 | 2009-09-30
75084-DE Kentucky Power Deliv - Ele | 314H9054 | D2896 | PP974384 HEBRON 44 EXTEND UG | 0 |  | 0 |  |  | 0 | 519697 | -519697 | 2008-02-22 | 2009-09-01 | 2008-07-01 | 2009-09-30
75084-DE Kentucky Power Deliv - Ele | 314H9055 | D2888 | PP974374 HEBRON 45 EXTEND UG | 0 |  | 0 |  |  | 0 | 167768 | -167768 | 2008-02-22 | 2009-09-01 | 2008-08-01 | 2009-09-15
75084-DE Kentucky Power Deliv - Ele | 314J9129 | D3435 | PP989939 RICHWOOD 41 LINE REAR | 0 |  | 0 |  |  | 0 | 178716 | -178716 | 2008-05-02 | 2010-01-31 | 2008-06-01 | 2010-02-24
75084-DE Kentucky Power Deliv - Ele | 314ZLG | C9035 | ULH&P 2005 Load Growth | 0 |  | 0 |  |  | -113979.76 | 113664 | -227643.76 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZLG | D2740 | COLD SPRING 49 CONVERSION | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-02-05 | 2013-02-01 | 2008-02-01 | 2009-04-06
75084-DE Kentucky Power Deliv - Ele | 314ZLG | D3389 | CLRYVLLE 42-CNVRT 2/4KV STPDWN | 0 |  | 0 |  |  | 176612.71 | 100 | 176512.71 | 2008-04-30 | 2013-04-01 | 2008-05-01 | 2009-01-26
75084-DE Kentucky Power Deliv - Ele | 314ZRL | C9024 | ULH&P 2005 Reliability | 0 |  | 0 |  |  | -406645.66 | 405521 | -812166.66 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZRL | D1893 | LIMABURG 42-INSTL VOLTG REG | 0 |  | 0 |  |  | 0 | 53978 | -53978 | 2007-10-23 | 2012-10-01 | 2007-10-01 | 2008-01-07
75084-DE Kentucky Power Deliv - Ele | 314ZUR | C9030 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -409635.37 | 408502 | -818137.37 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZUR | C9886 | CHELSEA S/O VILLA MADONNA | 0 |  | 0 |  |  | -1382.28 | 38775 | -40157.28 | 2007-05-30 | 2012-05-01 | 2007-06-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D1391 | CNSTNCE 42-NIEWHNR RD-UG RECON | 0 |  | 0 |  |  | 65183.82 | 60522 | 4661.82 | 2007-08-14 | 2012-08-01 | 2007-08-01 | 2008-12-20
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D1447 | WILDER 45-REMOVE 275 CROSSING | 0 |  | 0 |  |  | 46139.96 | 49284 | -3144.04 | 2007-09-02 | 2012-08-01 | 2007-08-01 | 2009-06-25
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D2139 | CRESCENT 42-UG RECONDUCTOR | 0 |  | 0 |  |  | 48020.04 | 1 | 48019.04 | 2007-11-21 | 2012-10-01 | 2007-11-01 | 2009-02-04
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D3712 | CLARYVL 42-MAIN ST-RT 10-RECON | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-06-20 | 2013-06-01 | 2008-07-01 | 2010-02-24
75084-DE Kentucky Power Deliv - Ele | 316H8978 | C9634 | Ft Mitchell Sub Land Sale | 0 |  | 0 |  |  | 15333.69 | 0 | 15333.69 | 2007-04-22 | 2010-12-31 | 2008-12-01 | 2010-07-31
75084-DE Kentucky Power Deliv - Ele | 316ZBG | C9864 | Cold Springs Site Improvements | 0 |  | 0 |  |  | 40659.35 | 35643 | 5016.35 | 2007-05-23 | 2008-07-01 | 2007-06-01 | 2008-03-15
75084-DE Kentucky Power Deliv - Ele | 903G0504 | C9339 | Dixie replace arresters TB2 | 0 |  | 0 |  |  | 6138.14 | 4423 | 1715.14 | 2007-02-25 | 2050-12-31 | 2007-05-01 | 2008-02-11
75084-DE Kentucky Power Deliv - Ele | 903G0504 | C9793 | Hands rep bush/arrest TB1 | 0 |  | 0 |  |  | 20303.93 | 15589 | 4714.93 | 2007-05-12 | 2050-12-31 | 2007-05-01 | 2007-12-23
75084-DE Kentucky Power Deliv - Ele | 903G0504 | D2883 | Crescent TB1 rem/inst ETM | 0 |  | 0 |  |  | 5479.14 | 10303 | -4823.86 | 2008-02-21 | 2050-12-31 | 2008-04-01 | 2008-05-07
75084-DE Kentucky Power Deliv - Ele | 903G0534 | D2365 | Beaver install switch and CB | 0 |  | 0 |  |  | 212250.69 | 80053 | 132197.69 | 2007-12-18 | 2050-12-31 | 2007-12-01 | 2008-02-01
75084-DE Kentucky Power Deliv - Ele | 903G7996 | D1716 | Villa rep control battery | 0 |  | 0 |  |  | 3586.35 | 5195 | -1608.65 | 2007-10-03 | 2050-12-31 | 2007-10-01 | 2007-11-03
75084-DE Kentucky Power Deliv - Ele | 903H8407X | F0824 | Alexandria Sub - Land | 0 |  | 0 |  |  | 544000 | 544000 | 0 | 2009-09-30 | 2009-09-30 | 2009-09-01 | 2001-09-30
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY10 | DIST TRANSFORMERS PUR 2010 | 1018111.3 |  | 1018111.3 | 100% |  | 1018111.3 | 1 | 1018110.3 | 2014-02-04 | 2015-12-31 | 2014-02-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY11 | DIST TRANSFORMERS PUR 2011 | 363165.36 |  | 363165.36 | 100% |  | 363165.36 | 1 | 363164.36 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY12 | DIST LINE TRANSFORMERS PUR 2012 | 300925.74 |  | 300925.74 | 100% |  | 300925.74 | 1 | 300924.74 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY13 | DIST LINE TRANSFORMERS PUR 2013 | 491191.31 |  | 491191.31 | 100% |  | 491191.31 | 1 | 491190.31 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | AMKY0035 | E9944 | Augustine 42 Dist OH Reconductor | 0 |  | 0 |  |  | 37506.59 | 29508 | 7998.59 | 2009-09-03 | 2010-05-31 | 2009-10-01 | 2010-06-09
75084-DE Kentucky Power Deliv - Ele | AMKY0035 | E9945 | Augustine 42 PILC Cable Replacement | 186.39 |  | 186.39 | 100% |  | 436906.32 | 331601 | 105305.32 | 2009-09-03 | 2010-05-31 | 2009-09-01 | 2010-06-09
75084-DE Kentucky Power Deliv - Ele | AMKY0036 | E7672 | Wilder 40 PILC Cable Replacement | 0 |  | 0 |  |  | 0 | 33130 | -33130 | 2009-07-10 | 2010-06-01 | 2009-09-01 | 2010-02-19
75084-DE Kentucky Power Deliv - Ele | AMKY0085 | G4117 | Wilder 13.2kV Bus | 826324.21 |  | 826324.21 | 100% |  | 2332545.27 | 854373 | 1478172.27 | 2011-07-21 | 2014-03-31 | 2012-06-01 | 2013-08-09
75084-DE Kentucky Power Deliv - Ele | AMKY0085A | O4164 | Wilder Inst 13kV CB 170 | 38050.41 |  | 38050.41 | 100% |  | 38050.41 | 27000 | 11050.41 | 2014-07-23 | 2015-06-30 | 2014-08-01 | 2015-01-05
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3700 | Claryville Recloser Replace | 0 |  | 0 |  |  | 465838.15 | 353172 | 112666.15 | 2011-06-16 | 2013-03-31 | 2011-07-01 | 2012-09-02
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3757 | Wilder F5962 Reclosing | 0 |  | 0 |  |  | 15848.51 | 19626 | -3777.49 | 2011-06-22 | 2013-03-31 | 2011-11-01 | 2012-09-26
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3773 | Claryville Inst Auto Throw Over | 0 |  | 0 |  |  | 97596.89 | 121949 | -24352.11 | 2011-06-23 | 2013-03-31 | 2011-07-01 | 2012-09-26
75084-DE Kentucky Power Deliv - Ele | AMKY0087 | F3404 | Dry Ridge 41 Reconductor | -10934.62 |  | -10934.62 | 100% |  | 344598.36 | 210608.08 | 133990.28 | 2009-12-22 | 2011-06-01 | 2010-04-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | AMKY0088 | G3276 | Mt Zion Rd Reconductor 2 | 2793.65 |  | 2793.65 | 100% |  | 250891.08 | 663636.23 | -412745.15 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-05-14
75084-DE Kentucky Power Deliv - Ele | AMKY0088 | G3277 | Mt Zion Rd Reconductor 2 (RLE) | 0 |  | 0 |  |  | 708.64 | 20892 | -20183.36 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-03-01
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0244 | EKP-138kv Interconn-Webster R/W | 0.14 |  | 0.14 | 100% |  | -8.5129e-12 | 85528 | -85528 | 2009-09-15 | 2011-10-01 | 2011-03-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0245 | F6282-Loop thru Webster Ring Bus | 15942.38 |  | 15942.38 | 100% |  | 1856.61 | 952790.42 | -950933.81 | 2009-09-15 | 2011-10-01 | 2009-09-01 | 2011-08-10
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0246 | Silver Grove Repl F6282 relays | 5915.07 |  | 5915.07 | 100% |  | 5210.7 | 36618 | -31407.3 | 2009-09-15 | 2011-10-01 | 2010-02-01 | 2011-09-04
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0265 | Buffington Repl F6282 relays | 0 |  | 0 |  |  | 5.8209e-13 | 97583 | -97583 | 2009-09-15 | 2011-10-01 | 2009-12-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0304 | Hands Sub Inst TB2 Transrupter | 0 |  | 0 |  |  | -2.9097e-12 | 118970 | -118970 | 2009-09-16 | 2011-10-01 | 2009-10-01 | 2011-09-04
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F5724 | Kenton Repl F6282 Carrier | 0 |  | 0 |  |  | 2.6193e-12 | 48596 | -48596 | 2010-02-23 | 2011-10-31 | 2010-04-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0290 | F2324 | Aug 44 Extension, Conv Latonia C | -96.86 |  | -96.86 | 100% |  | 198422.01 | 1 | 198421.01 | 2009-11-18 | 2010-09-01 | 2009-12-01 | 2010-09-15
75084-DE Kentucky Power Deliv - Ele | AMKY0326 | G0849 | Augustine 43 TP for Repl Cable | 0 |  | 0 |  |  | 42104.06 | 5315.07 | 36788.99 | 2010-09-01 | 2011-09-30 | 2011-03-01 | 2011-06-10
75084-DE Kentucky Power Deliv - Ele | AMKY0326 | G0852 | Augustine 43 PILC Cable Replacement | 4125.39 |  | 4125.39 | 100% |  | 167386.29 | 201531 | -34144.71 | 2010-09-01 | 2011-09-30 | 2010-10-01 | 2011-06-14
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3363 | Kenton Repl Circuit 45 Cable | 0 |  | 0 |  |  | 4132.92 | 18455 | -14322.08 | 2011-05-17 | 2012-09-30 | 2011-07-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3364 | Kenton 45 PILC Cable Replace OH | 0 |  | 0 |  |  | 109847.67 | 108000 | 1847.67 | 2011-05-17 | 2012-09-30 | 2012-10-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3365 | Kenton 45 PILC Cable Replace UG | 9578.62 |  | 9578.62 | 100% |  | 27411.39 | 39665.9 | -12254.51 | 2011-05-17 | 2012-09-30 | 2011-09-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0412 | G1816 | Wilder 44 PILC Cable Replace | 0 |  | 0 |  |  | 42551.42 | 63469 | -20917.58 | 2011-01-10 | 2011-10-31 | 2011-03-01 | 2011-06-29
75084-DE Kentucky Power Deliv - Ele | AMKY0412 | G1817 | Wilder 44 PILC Install Cable | 0 |  | 0 |  |  | 77317.2 | 22682 | 54635.2 | 2011-01-10 | 2011-10-31 | 2011-02-01 | 2011-06-29
75084-DE Kentucky Power Deliv - Ele | AMKY0474 | G2953 | Constance Install TLS | 0 |  | 0 |  |  | 255060.57 | 140864 | 114196.57 | 2011-04-07 | 2012-09-01 | 2011-04-01 | 2012-04-18
75084-DE Kentucky Power Deliv - Ele | AMKY0474 | G2957 | Villa F2862 Reclosing | 0 |  | 0 |  |  | 35714.36 | 12898 | 22816.36 | 2011-04-08 | 2012-03-31 | 2011-06-01 | 2012-02-07
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3956 | Constance 41-44 Circuits | 0 |  | 0 |  |  | 454677.69 | 262120 | 192557.69 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-04-27
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3957 | Crescent 41-44 Circuits | 0 |  | 0 |  |  | 182951.42 | 195258 | -12306.58 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-07-13
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3958 | Villa Sub 41-44 Circuits | 0 |  | 0 |  |  | 427855.42 | 195570 | 232285.42 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-09-08
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3959 | Kenton Circuits 41-46 | 0 |  | 0 |  |  | 223038.02 | 228652 | -5613.98 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-05-28
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G4465 | Villa Install F2862 TLS | 0 |  | 0 |  |  | 43036.46 | 13804 | 29232.46 | 2011-08-12 | 2012-09-01 | 2011-10-01 | 2012-09-08
75084-DE Kentucky Power Deliv - Ele | AMKY0528 | G5038 | Grant 43 City of Williamstown | 0 |  | 0 |  |  | 1218.2 | 397192 | -395973.8 | 2011-09-21 | 2012-10-01 | 2011-09-01 | 2012-10-24
75084-DE Kentucky Power Deliv - Ele | AMKY0570 | G6835 | West End 1524 Aerial on Bridge (OH) | -61545.17 |  | -61545.17 | 100% |  | 483279.82 | 98746.32 | 384533.5 | 2012-02-21 | 2013-03-31 | 2012-03-01 | 2012-12-21
75084-DE Kentucky Power Deliv - Ele | AMKY0571 | G6550 | Augustine 41 PILC Cable Replace | 0 |  | 0 |  |  | 1302481.16 | 1124875 | 177606.16 | 2012-01-24 | 2013-03-31 | 2012-02-01 | 2013-02-28
75084-DE Kentucky Power Deliv - Ele | AMKY0592 | G8851 | Wilder Replace DE KY CB741 | 149837.56 |  | 149837.56 | 100% |  | 156273.93 | 174808 | -18534.07 | 2012-11-07 | 2015-03-31 | 2012-11-01 | 2015-02-07
75084-DE Kentucky Power Deliv - Ele | AMKY0668 | G7206 | Wilder 43 Cable | 0 |  | 0 |  |  | 12864.89 | 27135 | -14270.11 | 2012-04-12 | 2013-03-31 | 2012-07-01 | 2013-01-26
75084-DE Kentucky Power Deliv - Ele | AMKY0668 | G7210 | Wilder 43 PILC Replacement | 0 |  | 0 |  |  | 30891.12 | 34209 | -3317.88 | 2012-04-12 | 2013-03-31 | 2012-10-01 | 2013-01-26
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7273 | Buffington - KY SEL Dist Ckt Imprv | 0 |  | 0 |  |  | 438957.48 | 347883 | 91074.48 | 2012-04-17 | 2014-03-31 | 2012-04-01 | 2013-02-20
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7274 | Donaldson KY SEL Dist Ckt Imprv | 46908.55 |  | 46908.55 | 100% |  | 229760.73 | 174540 | 55220.73 | 2012-04-17 | 2015-03-31 | 2012-05-01 | 2014-09-14
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7275 | Dixie KY SEL Dist Ckt Imprv | -7600 |  | -7600 | 100% |  | 246233.02 | 174540 | 71693.02 | 2012-04-17 | 2014-03-31 | 2012-04-01 | 2013-06-15
75084-DE Kentucky Power Deliv - Ele | AMKY0729 | G7002 | Dayton KY Sub Purch 825 Walnut -RLE | 0 |  | 0 |  |  | 140420.41 | 128377 | 12043.41 | 2012-03-12 | 2013-03-31 | 2012-03-01 | 2013-02-02
75084-DE Kentucky Power Deliv - Ele | AMKY0750 | G8124 | Line Capacitor Installs for KY 2012 | -1477.92 |  | -1477.92 | 100% |  | 44560.81 | 53967.22 | -9406.41 | 2012-07-27 | 2013-03-31 | 2012-08-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | AMKY0752 | G9955 | Augustine SEL Dist Upgrades | 194.36 |  | 194.36 | 100% |  | 435665.83 | 427895 | 7770.83 | 2013-04-16 | 2014-03-31 | 2013-04-01 | 2014-03-20
75084-DE Kentucky Power Deliv - Ele | AMKY0806 | G9259 | Dist Line Cap Inst for KY 2013 | 38722.64 |  | 38722.64 | 100% |  | 74827.97 | 70413.44 | 4414.53 | 2013-01-14 | 2014-03-31 | 2013-01-01 | 2013-10-08
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0296 | Crescent Install 22.4MVA TB3 | 902059.21 |  | 902059.21 | 100% |  | 932799.6 | 1654143 | -721343.4 | 2013-06-20 | 2015-09-01 | 2013-08-01 | 2015-09-03
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0298 | Crescent 45 | 8484.55 |  | 8484.55 | 100% |  | 8484.55 | 351997.91 | -343513.36 | 2013-06-21 | 2016-05-31 | 2014-10-01 | 2016-02-25
75084-DE Kentucky Power Deliv - Ele | AMKY0849 | G9410 | F5962 Re-route at NKU | 20597.93 |  | 20597.93 | 100% |  | 792.48 | 139526 | -138733.52 | 2013-01-31 | 2014-03-31 | 2013-02-01 | 2013-08-24
75084-DE Kentucky Power Deliv - Ele | AMKY0877 | H0128 | Augustine 41 Reconductor | -4480.93 |  | -4480.93 | 100% |  | 93590.12 | 119088 | -25497.88 | 2013-05-20 | 2014-09-01 | 2013-05-01 | 2014-01-10
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0000 | Silver Grove 138kV Install | 636456.3 |  | 636456.3 | 100% |  | 707880.4 | 484511 | 223369.4 | 2013-04-25 | 2015-09-01 | 2013-05-01 | 2014-07-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0009 | Silver Grove Inst TB1 & Rem Equip | 2128817.68 |  | 2128817.68 | 100% |  | 2350755.6 | 2110325 | 240430.6 | 2013-04-25 | 2015-09-01 | 2013-05-01 | 2015-01-28
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0014 | Silver Grove 41 New Feeder | 39737.82 |  | 39737.82 | 100% |  | 41124.98 | 910678.56 | -869553.58 | 2013-04-25 | 2015-09-01 | 2013-11-01 | 2015-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0016 | Silver Grove 42 43 New Feeder | 110104.11 |  | 110104.11 | 100% |  | 112878.37 | 350451.67 | -237573.3 | 2013-04-25 | 2015-09-01 | 2013-11-01 | 2015-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0017 | Silver Grove 41 42 43 UG Exits | 665769.53 |  | 665769.53 | 100% |  | 692829.06 | 674137.23 | 18691.83 | 2013-04-25 | 2015-09-01 | 2013-07-01 | 2014-12-12
75084-DE Kentucky Power Deliv - Ele | AMKY0940 | L2107 | Limaburg-Install ATO | 210191.5 |  | 210191.5 | 100% |  | 210191.5 | 214396 | -4204.5 | 2014-05-08 | 2015-03-31 | 2014-05-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | AMKY0940 | L2109 | Buffington F6763 Reclosing | 11752.75 |  | 11752.75 | 100% |  | 11752.75 | 19372 | -7619.25 | 2014-05-08 | 2015-03-31 | 2014-07-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | AMKY0941 | L9104 | Grant Install TLS | 78248.32 |  | 78248.32 | 100% |  | 78248.32 | 230617 | -152368.68 | 2014-05-21 | 2016-03-31 | 2014-06-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | AMKY0942 | M1112 | Dry Ridge TLS | 62009.59 |  | 62009.59 | 100% |  | 62009.59 | 122334 | -60324.41 | 2014-05-29 | 2015-09-30 | 2014-06-01 | 2015-08-29
75084-DE Kentucky Power Deliv - Ele | AMKY0943 | L9108 | Cold Spring TLS | 69219.52 |  | 69219.52 | 100% |  | 69219.52 | 217493 | -148273.48 | 2014-05-22 | 2015-09-30 | 2014-06-01 | 2015-08-01
75084-DE Kentucky Power Deliv - Ele | AMKY0944 | L2103 | Beaver-Install ATO | 158990.47 |  | 158990.47 | 100% |  | 158990.47 | 238543 | -79552.53 | 2014-05-08 | 2015-03-31 | 2014-05-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | AMKY0953 | J0108 | Hebron Inst 69kV CB's | 617707.79 |  | 617707.79 | 100% |  | 617707.79 | 1421424 | -803716.21 | 2014-03-24 | 2015-09-01 | 2014-03-01 | 2015-08-29
75084-DE Kentucky Power Deliv - Ele | AMKY0953 | J0109 | Villa Repl F2862 Relays | 56722.51 |  | 56722.51 | 100% |  | 56722.51 | 175606 | -118883.49 | 2014-03-24 | 2015-10-01 | 2014-03-01 | 2015-09-13
75084-DE Kentucky Power Deliv - Ele | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 52328.61 |  | 52328.61 | 100% |  | 52328.61 | 823726 | -771397.39 | 2014-02-18 | 2019-03-01 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | AMKY0974 | H1171 | Buffington-Repl CB 681 683 | 176061.88 |  | 176061.88 | 100% |  | 176061.88 | 295230 | -119168.12 | 2013-11-04 | 2015-09-01 | 2014-01-01 | 2015-06-30
75084-DE Kentucky Power Deliv - Ele | AMKY1073 | L9115 | Buffington Repl VTs | 29368.06 |  | 29368.06 | 100% |  | 29368.06 | 109828 | -80459.94 | 2014-05-22 | 2015-09-01 | 2014-06-01 | 2015-06-30
75084-DE Kentucky Power Deliv - Ele | AMKY1101 | L5122 | UG 5511344 Kenton 43 Bld New Fdr | 282706.47 |  | 282706.47 | 100% |  | 282706.47 | 529656.26 | -246949.79 | 2014-05-15 | 2016-03-31 | 2014-07-01 | 2015-07-16
75084-DE Kentucky Power Deliv - Ele | AMKY1176 | P6679 | Villa CCVT Repl | 11204.38 |  | 11204.38 | 100% |  | 11204.38 | 90805 | -79600.62 | 2014-10-27 | 2016-03-31 | 2014-11-01 | 2015-09-13
75084-DE Kentucky Power Deliv - Ele | AMKY1396 | P6550 | AM 6394804 Kenton 44 12kv | 112322.66 |  | 112322.66 | 100% |  | 112322.66 | 515418.38 | -403095.72 | 2014-10-09 | 2016-03-31 | 2014-10-01 | 2015-07-09
75084-DE Kentucky Power Deliv - Ele | AMKY1396 | P6708 | AM 6394817 Kenton 44 Pt 2 reloc | 10550.82 |  | 10550.82 | 100% |  | 10550.82 | 150744.74 | -140193.92 | 2014-10-31 | 2016-03-31 | 2014-11-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | AMOH0389 | G0347 | Augustine | 0 |  | 0 |  |  | 19869.34 | 8800 | 11069.34 | 2010-07-13 | 2011-03-31 | 2010-08-01 | 2010-12-16
75084-DE Kentucky Power Deliv - Ele | AMOH0389 | G0348 | Donaldson | 0 |  | 0 |  |  | 28793.65 | 9240 | 19553.65 | 2010-07-13 | 2011-03-31 | 2010-09-01 | 2010-12-14
75084-DE Kentucky Power Deliv - Ele | AMOH0424 | G4604 | 345kV Distr Clearance Capital (KY) | -99.16 |  | -99.16 | 100% |  | 1111.39 | 8867.53 | -7756.14 | 2011-08-24 | 2012-09-01 | 2012-02-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | G6619 | KY Dist Line Assoc w 138kV CLR | 69440.76 |  | 69440.76 | 100% |  | 619233.04 | 505780.19 | 113452.85 | 2012-01-30 | 2015-03-31 | 2013-01-01 | 2014-04-15
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | G9311 | F5967 138kV Clear Correct OH | 0 |  | 0 |  |  | 32930.29 | 26000 | 6930.29 | 2013-01-18 | 2015-03-31 | 2013-01-01 | 2014-01-05
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | H0163 | F5962 138kV Clear Corr OH | 0 |  | 0 |  |  | 10325.67 | 2500 | 7825.67 | 2013-05-23 | 2015-03-31 | 2013-07-01 | 2014-01-05
75084-DE Kentucky Power Deliv - Ele | AVAMARUPG | G9122 | EMPCS-AVAMAR UPGRADE | 0 |  | 0 |  |  | 140465.13 | 141000 | -534.87 | 2012-12-19 | 2013-05-30 | 2012-12-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G0397 | Wilder replace drive | 0 |  | 0 |  |  | 12308.24 | 16253 | -3944.76 | 2010-08-31 | 2010-12-31 | 2010-10-01 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G0819 | Alexandria South replace sidewalk | 0 |  | 0 |  |  | 4984.1 | 3390 | 1594.1 | 2010-08-30 | 2010-12-31 | 2010-09-01 | 2010-11-24
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G1662 | Dayton install drainage system | 0 |  | 0 |  |  | 3853.99 | 3447 | 406.99 | 2010-12-15 | 2011-03-31 | 2010-12-01 | 2011-03-11
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G4179 | Kenton resurface entire pavement | 0 |  | 0 |  |  | 6032.09 | 8222 | -2189.91 | 2011-07-27 | 2011-12-31 | 2011-11-01 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G5938 | Thomas More remove eye wash station | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-11-23 | 2012-03-16 | 2014-04-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6108 | Blackwell Sub security system | 0 |  | 0 |  |  | 82686.31 | 52677 | 30009.31 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6109 | Buffington Sub security system | 0 |  | 0 |  |  | 146449.24 | 90148 | 56301.24 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6112 | Silver Grove sub security system | 0 |  | 0 |  |  | 149197.11 | 91870 | 57327.11 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8409 | Limaburg Sub security system | 1538.08 |  | 1538.08 | 100% |  | 58231.92 | 40000 | 18231.92 | 2012-09-06 | 2013-09-30 | 2012-09-01 | 2014-08-31
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8420 | Donaldson Sub security system | -8.92 |  | -8.92 | 100% |  | 50345.99 | 40000 | 10345.99 | 2012-09-10 | 2013-03-31 | 2012-09-01 | 2014-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8423 | Wilder Sub security system | 0 |  | 0 |  |  | 102608.81 | 90000 | 12608.81 | 2012-09-10 | 2013-03-31 | 2012-09-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2105 | Hebron Station eye wash station | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-11 | 2012-03-16 | 2014-08-01 | 2003-03-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2111 | Mt Zion Remov eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2013-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2114 | Blackwell remove eyewas stat 7 gal | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2013-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2115 | York remove eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2012-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2116 | Dayton remove eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2012-03-16 | 2014-08-01 | 2012-05-12
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2117 | Longbranch remove eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2012-03-16 | 2014-09-01 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O4106 | Hands Sub add gravel | 1493.02 |  | 1493.02 | 100% |  | 1493.02 | 11207.12 | -9714.1 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-11-15
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O4112 | Buffington Sub Add Gravel | 805.92 |  | 805.92 | 100% |  | 805.92 | 11207.12 | -10401.2 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | C16A7995 | D3550 | Crescent rep dbl doors | 0 |  | 0 |  |  | 21018.96 | 1 | 21017.96 | 2008-05-21 | 2050-12-31 | 2008-12-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | CAPFA | CAPAUTOKY | Capacitor Automation - Kentucky | 0 |  | 0 |  |  | 0 | 49 | -49 | 2014-01-15 | 2020-12-31 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | CAPKY | Capacitor Inst/Rem | 0 |  | 0 |  |  | 200598.71 | 101 | 200497.71 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | OTVSRKY | Cap Oil to Vac Switch Repl KY | 0 |  | 0 |  |  | 0 | 100000 | -100000 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | CERTKY | Rel Major Cap T Equip Repl | -30077.28 |  | -30077.28 | 100% |  | 277770.16 | 100 | 277670.16 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | G6716 | F2862 Emergency R/P switch 547 | 0 |  | 0 |  |  | 53352.23 | 52037.34 | 1314.89 | 2012-02-08 | 2013-03-31 | 2012-02-01 | 2012-05-08
75084-DE Kentucky Power Deliv - Ele | CERTFA | LPRFUKY | Line Patrol Followup Work | 240445.35 |  | 240445.35 | 100% |  | 243484.69 | 80000 | 163484.69 | 2013-03-20 | 2050-12-31 | 2013-11-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | TLPIKY | Transm Lightning Perf Improvements | 0 |  | 0 |  |  | 15985.5 | 75000 | -59014.5 | 2012-01-04 | 2050-12-31 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | TLSRKY | Transm Line Switch Replacement | 5138.64 |  | 5138.64 | 100% |  | 5138.64 | 70000 | -64861.36 | 2012-01-04 | 2050-12-31 | 2014-07-01
75084-DE Kentucky Power Deliv - Ele | CSFA | CSKY | Circuit Sectionalization | 868.84 |  | 868.84 | 100% |  | 23726.95 | 100 | 23626.95 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | CSFA | G4676 | EMAX 2550566 G&W Viper Recloser | 0 |  | 0 |  |  | 74233.14 | 27446.94 | 46786.2 | 2011-08-30 | 2012-08-31 | 2011-09-01 | 2012-02-17
75084-DE Kentucky Power Deliv - Ele | CSFA | G6457 | EMAX 2834098 Second feed to UG syst | 0 |  | 0 |  |  | 84926.18 | 72167.47 | 12758.71 | 2012-01-11 | 2013-03-31 | 2012-01-01 | 2012-05-17
75084-DE Kentucky Power Deliv - Ele | CSFA | P6373 | CS 5062969 Cold Spring 49 | 17703.47 |  | 17703.47 | 100% |  | 17703.47 | 93658.11 | -75954.64 | 2014-09-24 | 2016-03-31 | 2014-10-01 | 2015-05-24
75084-DE Kentucky Power Deliv - Ele | CSFA | SDKYT111 | Villa 41, Crescent 41, Constance 44 | 0 |  | 0 |  |  | 179948.64 | 134316.91 | 45631.73 | 2011-08-03 | 2012-12-31 | 2011-09-01 | 2012-03-12
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT112 | Kenton 41 & Kenton 44 2012 | 0 |  | 0 |  |  | 122048.92 | 116524.81 | 5524.11 | 2011-10-31 | 2012-12-31 | 2011-11-01 | 2012-11-28
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT212 | Augustine 41 & Crescent 42 2012 | 0 |  | 0 |  |  | 77450.08 | 121431.31 | -43981.23 | 2011-10-31 | 2012-12-31 | 2011-11-01 | 2013-01-24
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT34 | SG Verona 41 & Crittenden 41 | 147.01 |  | 147.01 | 100% |  | 81187.39 | 72328.13 | 8859.26 | 2012-11-01 | 2014-03-31 | 2012-12-01 | 2013-08-30
75084-DE Kentucky Power Deliv - Ele | CSPFA | CSPKY | Transformer Retrofit | 0 |  | 0 |  |  | 153844.14 | 200 | 153644.14 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1196 | TR 4599000 Florence 46 | 44.63 |  | 44.63 | 100% |  | 1679.01 | 88196.63 | -86517.62 | 2013-11-06 | 2016-07-31 | 2013-11-01 | 2016-03-16
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1217 | TR 4597480 Florence 45 | 116058.06 |  | 116058.06 | 100% |  | 116058.06 | 145003.02 | -28944.96 | 2013-11-11 | 2015-10-31 | 2014-01-01 | 2015-08-05
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1225 | TR 4609673 Hebron 45 | 31077.51 |  | 31077.51 | 100% |  | 31077.51 | 51410.59 | -20333.08 | 2013-11-12 | 2015-07-31 | 2014-01-01 | 2015-06-18
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1236 | TR 4616175 Limaburg 41 | 14.33 |  | 14.33 | 100% |  | 673.44 | 54189.11 | -53515.67 | 2013-11-13 | 2016-12-30 | 2013-11-01 | 2016-06-08
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1372 | TR 4655448 CLARYVILLE 41 | 119057.96 |  | 119057.96 | 100% |  | 119057.96 | 331178.02 | -212120.06 | 2013-12-03 | 2016-12-30 | 2014-10-01 | 2016-09-08
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1397 | TR 4658415 Hands 41 | 135730.91 |  | 135730.91 | 100% |  | 135730.91 | 115397.25 | 20333.66 | 2013-12-05 | 2016-01-30 | 2014-05-01 | 2015-01-02
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1398 | TR 4660303 Hands 44 | 193137.38 |  | 193137.38 | 100% |  | 193137.38 | 227477.2 | -34339.82 | 2013-12-05 | 2016-06-30 | 2014-04-01 | 2016-02-15
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1446 | TR 4674272 Augustine 46 | 167862.28 |  | 167862.28 | 100% |  | 168024.83 | 214520.52 | -46495.69 | 2013-12-12 | 2015-03-31 | 2013-12-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1453 | TR 4675524 York 43 | 6.06 |  | 6.06 | 100% |  | 168.61 | 64460.38 | -64291.77 | 2013-12-12 | 2016-06-01 | 2013-12-01 | 2015-06-17
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1462 | TR 4677452 Marshall 41 | 51424.08 |  | 51424.08 | 100% |  | 51424.08 | 73276.29 | -21852.21 | 2013-12-13 | 2015-03-31 | 2014-05-01 | 2014-10-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1464 | TR 4678169 KY UNIV 43 | 72119.88 |  | 72119.88 | 100% |  | 72282.43 | 121238 | -48955.57 | 2013-12-13 | 2015-07-31 | 2013-12-01 | 2015-06-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1487 | TR 4693232 Oakbrook 41 | 20948.02 |  | 20948.02 | 100% |  | 20948.02 | 54889.34 | -33941.32 | 2013-12-17 | 2015-10-30 | 2014-12-01 | 2015-04-19
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1488 | TR 4693837 Augustine 43 | 60655.12 |  | 60655.12 | 100% |  | 60655.12 | 75566.64 | -14911.52 | 2013-12-17 | 2016-06-30 | 2014-04-01 | 2016-02-17
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1489 | TR 4694697 Verona 42 | 4.44 |  | 4.44 | 100% |  | 166.99 | 94811.65 | -94644.66 | 2013-12-17 | 2016-07-30 | 2013-12-01 | 2016-06-08
75084-DE Kentucky Power Deliv - Ele | CSPFA | J4103 | TR 5247963 Augustine 45 | 403.39 |  | 403.39 | 100% |  | 403.39 | 64518.96 | -64115.57 | 2014-03-31 | 2016-12-30 | 2014-04-01 | 2016-09-15
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | F7484 | EMAX#523406 Crescent 43 Reliability | 0 |  | 0 |  |  | 30288.5 | 26432.28 | 3856.22 | 2010-04-23 | 2010-12-31 | 2010-06-01 | 2011-02-06
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G0660 | RELIABILITY - DECLARED CIRCUIT CRES | 0 |  | 0 |  |  | 17836.89 | 1 | 17835.89 | 2010-08-06 | 2010-12-31 | 2010-08-01 | 2011-03-20
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G0763 | DECLARED CIRCUIT CRESCENT "43" | 0 |  | 0 |  |  | 111432.32 | 7845.62 | 103586.7 | 2010-08-18 | 2011-01-11 | 2010-08-01 | 2011-03-06
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1434 | EMAX 1347776 Constance 42 Decl Circ | 0 |  | 0 |  |  | 20086.8 | 14091 | 5995.8 | 2010-11-01 | 2011-12-31 | 2010-11-01 | 2011-11-19
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1435 | EMAX 1347974 Crescent 44 Decl Circ | 5757.31 |  | 5757.31 | 100% |  | 88232.35 | 25455.88 | 62776.47 | 2010-11-01 | 2013-03-31 | 2010-11-01 | 2013-01-15
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1756 | EMAX 1696749 Constance 42 Decl Circ | 0 |  | 0 |  |  | 24487.71 | 16690.26 | 7797.45 | 2011-01-04 | 2013-03-31 | 2011-01-01 | 2012-08-07
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G3736 | EMAX 2374342 Crescent 44 Decl circ | 0 |  | 0 |  |  | 14220.23 | 8850.15 | 5370.08 | 2011-06-21 | 2014-03-31 | 2011-08-01 | 2013-07-15
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G6751 | EMAX 1334817 Dixie Hwy Crescent 43 | 8364.76 |  | 8364.76 | 100% |  | 19434.1 | 45426.06 | -25991.96 | 2012-02-14 | 2013-03-31 | 2012-09-01 | 2012-12-12
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9171 | DC emax 3744831 Kenton 42 Decl | 30912.96 |  | 30912.96 | 100% |  | 43651.73 | 33907.39 | 9744.34 | 2013-01-03 | 2014-03-31 | 2013-01-01 | 2013-07-09
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9684 | DC 3925631 Kenton 42 | -2023.95 |  | -2023.95 | 100% |  | 135688.45 | 41957.09 | 93731.36 | 2013-03-05 | 2014-03-31 | 2013-04-01 | 2014-02-23
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9849 | DC emax 3983251 White Tower 41 | 0 |  | 0 |  |  | 116061.25 | 50988.41 | 65072.84 | 2013-03-26 | 2014-03-31 | 2013-04-01 | 2013-11-22
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | H1642 | DC 4759551 Verona 41 | 39465.32 |  | 39465.32 | 100% |  | 39465.32 | 37079.56 | 2385.76 | 2014-01-10 | 2015-06-30 | 2014-03-01 | 2015-03-23
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | L2102 | DC 5476661 Hebron 42 | 840.43 |  | 840.43 | 100% |  | 840.43 | 57064.06 | -56223.63 | 2014-05-08 | 2015-11-01 | 2014-06-01 | 2015-08-07
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | L2104 | DC 5476709 Villa 43 | 1727.05 |  | 1727.05 | 100% |  | 1727.05 | 85000.43 | -83273.38 | 2014-05-08 | 2016-07-30 | 2014-06-01 | 2016-06-25
75084-DE Kentucky Power Deliv - Ele | DETCONFA | F9909 | Old 17 & Hempling Deteriorated Cond | 0 |  | 0 |  |  | 50277.92 | 48874.54 | 1403.38 | 2010-06-25 | 2012-10-31 | 2010-07-01 | 2012-03-29
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0267 | Whites Tower 41 Sec 2 Hempfling Rd | 0 |  | 0 |  |  | 29428.7 | 42269.4 | -12840.7 | 2010-07-08 | 2012-06-15 | 2010-09-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0268 | Whites Tower 41 Madison Pk | 0 |  | 0 |  |  | 42418.71 | 25233.86 | 17184.85 | 2010-07-08 | 2012-07-31 | 2010-07-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0269 | Whites Tower 41 Sec 1 Madison Pk | -477.99 |  | -477.99 | 100% |  | 39341.78 | 47652.76 | -8310.98 | 2010-07-08 | 2012-07-31 | 2010-11-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0270 | Whites Tower 41 Sec 2 Madison Pk | 0 |  | 0 |  |  | 25828.63 | 34249.73 | -8421.1 | 2010-07-08 | 2012-07-31 | 2010-11-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0425 | Hempfling Rd e/o Madison Sec 3 | 0 |  | 0 |  |  | 27144.97 | 20930.73 | 6214.24 | 2010-07-14 | 2012-07-31 | 2010-07-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0529 | Old Madison Pk & Pony Dr Det Cond | 0 |  | 0 |  |  | 816.97 | 405.77 | 411.2 | 2010-07-20 | 2010-12-31 | 2010-09-01 | 2011-01-04
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0530 | Gleason Rd & Madison Pk Det Cond | 0 |  | 0 |  |  | 77346.52 | 33812.48 | 43534.04 | 2010-07-20 | 2012-07-31 | 2010-09-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0531 | Spillman & Madison Pk Det Cond | 0 |  | 0 |  |  | 3789.54 | 8361.34 | -4571.8 | 2010-07-21 | 2010-12-31 | 2010-10-01 | 2011-02-24
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G1558 | EMAX 1417885 15 Spiral Dr | -61503.51 |  | -61503.51 | 100% |  | 74303.72 | 72834.39 | 1469.33 | 2010-11-29 | 2012-04-30 | 2011-05-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G1654 | EMAX 1549494 15 Spiral Dr | -53221.11 |  | -53221.11 | 100% |  | 21078.52 | 14555.58 | 6522.94 | 2010-12-13 | 2011-12-31 | 2011-05-01 | 2011-12-08
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G2918 | EMAX 2176614 Viewpoint Dr | 2753.15 |  | 2753.15 | 100% |  | 189414.82 | 137595.61 | 51819.21 | 2011-04-05 | 2012-12-31 | 2011-04-01 | 2012-08-17
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G3813 | EMAX 2389938 Oakbrook 41 Det | 0 |  | 0 |  |  | 52381.75 | 31170 | 21211.75 | 2011-06-27 | 2011-12-31 | 2011-07-01 | 2012-02-02
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G4633 | EMAX 2541613 Richwood 41 Det Cond | -23.34 |  | -23.34 | 100% |  | 7686.57 | 6122.79 | 1563.78 | 2011-08-26 | 2012-04-30 | 2011-09-01 | 2012-03-04
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G9501 | DET emax 3873582 Murman Rd | -921.24 |  | -921.24 | 100% |  | 327179.97 | 193581.9 | 133598.07 | 2013-02-14 | 2014-03-31 | 2013-02-01 | 2014-01-02
75084-DE Kentucky Power Deliv - Ele | DETCONFA | O2107 | DC 5809390 CRESCENT 42 | 101930.71 |  | 101930.71 | 100% |  | 101930.71 | 267130.7 | -165199.99 | 2014-07-12 | 2016-01-31 | 2014-07-01 | 2015-07-14
75084-DE Kentucky Power Deliv - Ele | DETCONFA | P7106 | DET 6589503 Cold Spring 49 | 1182.61 |  | 1182.61 | 100% |  | 1182.61 | 56012.44 | -54829.83 | 2014-12-18 | 2016-03-31 | 2014-12-01 | 2015-08-26
75084-DE Kentucky Power Deliv - Ele | DETCONFA | THEFTCOND | REPL STOLEN IN-SRVC OVRHD COND - KY | 11861.28 |  | 11861.28 | 100% |  | 11861.28 | 100 | 11761.28 | 2014-06-10 | 2025-12-31 | 2014-06-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0124 | Donaldson replace control batteries | 0 |  | 0 |  |  | 9962.83 | 10964 | -1001.17 | 2010-07-06 | 2010-09-30 | 2010-08-01 | 2010-11-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0670 | Alexandria S repl control batteries | 0 |  | 0 |  |  | 2117.18 | 1690 | 427.18 | 2010-08-10 | 2010-12-31 | 2010-08-01 | 2010-12-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0691 | Buffington install LTC filter | 0 |  | 0 |  |  | 6753.79 | 10623 | -3869.21 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2010-12-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0696 | Constance install LTC filter | 0 |  | 0 |  |  | 7681.26 | 11023 | -3341.74 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2011-01-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0701 | Wilder install LTC filter | 0 |  | 0 |  |  | 9788.56 | 10623 | -834.44 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2010-12-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0732 | Grant repl station control battery | 0 |  | 0 |  |  | 1116.77 | 1690 | -573.23 | 2010-08-12 | 2010-12-30 | 2010-09-01 | 2010-12-14
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0734 | Marshall replace reclosers | 0 |  | 0 |  |  | 640.49 | 862 | -221.51 | 2010-08-13 | 2010-12-31 | 2010-08-01 | 2010-11-16
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1158 | Oakbrook repl TB 1 X3 bushing | 0 |  | 0 |  |  | 7121.45 | 4092 | 3029.45 | 2010-09-30 | 2012-06-15 | 2010-12-01 | 2013-04-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1261 | Villa inst LTC filter on TB 1 | 0 |  | 0 |  |  | 15975.45 | 10623 | 5352.45 | 2010-10-07 | 2012-06-15 | 2010-10-01 | 2012-08-11
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1561 | Claryville TB 2,3 replace fans | 0 |  | 0 |  |  | 4408.9 | 3303 | 1105.9 | 2010-11-29 | 2011-05-31 | 2011-01-01 | 2011-05-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1562 | Kentucky Univ TB 4 replace fans | 0 |  | 0 |  |  | 11272.01 | 4021 | 7251.01 | 2010-11-29 | 2011-08-31 | 2011-01-01 | 2011-05-16
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1563 | Limaburg TB 2 replace fans | 0 |  | 0 |  |  | 5044.69 | 2872 | 2172.69 | 2010-11-29 | 2011-08-31 | 2011-01-01 | 2011-05-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1564 | Marshall TB 1 replace fans | 0 |  | 0 |  |  | 5611.87 | 2872 | 2739.87 | 2010-11-29 | 2011-12-31 | 2011-01-01 | 2011-09-29
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1670 | Crescent TB 2 replace ETM | 0 |  | 0 |  |  | 10782.08 | 5953 | 4829.08 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1671 | Dixie TB2 replace ETM | 0 |  | 0 |  |  | 6817.04 | 5953 | 864.04 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-15
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1672 | Hands TB 1 replace ETM | 0 |  | 0 |  |  | 7187.2 | 5953 | 1234.2 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-19
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1675 | Wilder TB 3 replace ETM | 0 |  | 0 |  |  | 10922.24 | 5953 | 4969.24 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-21
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1950 | Buffington TB 3 replace bushing | 0 |  | 0 |  |  | 5339.87 | 5214 | 125.87 | 2011-01-24 | 2012-06-15 | 2011-04-01 | 2012-02-05
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G2222 | Donaldson TB 1 replace fans | 0 |  | 0 |  |  | 3698.38 | 4325 | -626.62 | 2011-02-09 | 2011-12-31 | 2011-03-01 | 2011-06-21
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4004 | Bellevue TB2 Install LTC Filter | 0 |  | 0 |  |  | 11027.59 | 11956 | -928.41 | 2011-07-11 | 2012-03-31 | 2011-07-01 | 2012-03-10
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4167 | Florence TB 2 instal LTC & 2 fans | 0 |  | 0 |  |  | 11201.45 | 14317 | -3115.55 | 2011-07-26 | 2011-12-31 | 2011-07-01 | 2012-03-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4174 | Donaldson TB 2 instl LTC filter | 0 |  | 0 |  |  | 11099.84 | 13136 | -2036.16 | 2011-07-27 | 2012-06-15 | 2011-07-01 | 2012-03-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5013 | Florence Install LTC filter on TB 1 | 0 |  | 0 |  |  | 10672.06 | 11351 | -678.94 | 2011-09-20 | 2012-03-31 | 2011-09-01 | 2012-02-09
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5463 | Constance instl LTC filter on TB 2 | 0 |  | 0 |  |  | 7380.68 | 10975.37 | -3594.69 | 2011-10-25 | 2012-09-30 | 2011-12-01 | 2012-04-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5484 | Augustine instl LTC filter on TB 1 | 0 |  | 0 |  |  | 7080.51 | 15041.51 | -7961 | 2011-10-26 | 2012-09-30 | 2011-12-01 | 2012-07-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5700 | Claryville repl X0,X1,X2,X3 bushing | 0 |  | 0 |  |  | 3910.89 | 14030.99 | -10120.1 | 2011-11-07 | 2012-09-30 | 2011-12-01 | 2012-08-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5800 | Hands repl cooling fans on TB 1 | 0 |  | 0 |  |  | 14912.34 | 15906.97 | -994.63 | 2011-11-14 | 2012-07-01 | 2011-12-01 | 2012-04-10
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G6611 | Dixie replace cooling fans TB 1 | 0 |  | 0 |  |  | 7584.18 | 8328.02 | -743.84 | 2012-01-30 | 2012-07-01 | 2012-02-01 | 2012-05-15
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7624 | Buffington replace ETM on TB 2 | 0 |  | 0 |  |  | 14778.92 | 6868 | 7910.92 | 2012-05-22 | 2013-03-31 | 2012-07-01 | 2012-10-25
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7630 | Buffington replace ETM TB 7 | 0 |  | 0 |  |  | 18129.78 | 7751.94 | 10377.84 | 2012-05-23 | 2013-03-31 | 2012-07-01 | 2012-11-02
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7631 | Buffington replace ETM TB 4 | 0 |  | 0 |  |  | 11288.6 | 6868 | 4420.6 | 2012-05-23 | 2013-03-31 | 2012-07-01 | 2012-10-26
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8666 | Buffington TB 1 Cooler Replacement | 181.7 |  | 181.7 | 100% |  | 209704.63 | 187956.46 | 21748.17 | 2012-10-15 | 2014-03-01 | 2013-01-01 | 2014-02-10
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8885 | Limaburg repl HS bushings&LAs TB 2 | 0 |  | 0 |  |  | 18866.47 | 12414.78 | 6451.69 | 2012-11-12 | 2013-09-28 | 2013-02-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8886 | Limaburg repl HS LAs&LS bushingsTB1 | 0 |  | 0 |  |  | 12132.74 | 10541.3 | 1591.44 | 2012-11-12 | 2013-12-27 | 2013-02-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G9113 | Bellevue TB 1 repl HS arresters | -168.21 |  | -168.21 | 100% |  | 5681.9 | 4178.77 | 1503.13 | 2012-12-18 | 2013-09-28 | 2013-02-01 | 2013-08-15
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G9825 | Silver Grove Repl fans on TB 23 | 0 |  | 0 |  |  | 34060.17 | 36332.39 | -2272.22 | 2013-03-25 | 2013-12-31 | 2013-05-01 | 2013-09-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0092 | Kenton Repl fans on TB 1 | 1240.42 |  | 1240.42 | 100% |  | 26578.59 | 15097.9 | 11480.69 | 2013-05-13 | 2013-12-31 | 2013-06-01 | 2013-09-20
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0093 | Kenton Repl fans on VR 3 | 628.39 |  | 628.39 | 100% |  | 14085.49 | 7427.65 | 6657.84 | 2013-05-13 | 2013-12-31 | 2013-06-01 | 2013-09-20
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0663 | Claryville TB 3 Repl bushings | 3988.79 |  | 3988.79 | 100% |  | 24545.18 | 27216.63 | -2671.45 | 2013-08-29 | 2014-03-31 | 2013-12-01 | 2014-11-15
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H1600 | Augustine Repl LAs on TB 5 | 9535.91 |  | 9535.91 | 100% |  | 9535.91 | 7904.73 | 1631.18 | 2014-01-03 | 2015-03-31 | 2014-04-01 | 2015-02-12
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H1601 | Marshall Repl HS LAs on TB 1 | 7616.97 |  | 7616.97 | 100% |  | 7616.97 | 3529.83 | 4087.14 | 2014-01-03 | 2015-03-31 | 2014-03-01 | 2014-07-04
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | J0111 | Augustine Repl fans on TB 5 | 11977.54 |  | 11977.54 | 100% |  | 11977.54 | 11300.35 | 677.19 | 2014-03-24 | 2015-03-31 | 2014-07-01 | 2014-10-22
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | N7108 | Wilder Repl Cooling Fans | 6432 |  | 6432 | 100% |  | 6432 | 5806.34 | 625.66 | 2014-06-27 | 2015-03-31 | 2014-08-01 | 2014-11-25
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | O5111 | Villa TB2 Repl Cooling Fans | 5699.88 |  | 5699.88 | 100% |  | 5699.88 | 4706.45 | 993.43 | 2014-07-25 | 2015-03-31 | 2014-08-01 | 2014-11-04
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | O6105 | Constance Repl TB1 Cooling Fans | 10180.71 |  | 10180.71 | 100% |  | 10180.71 | 10512.1 | -331.39 | 2014-07-28 | 2015-03-31 | 2014-08-01 | 2015-01-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P6425 | Limaburg TB1 Repl Cooling Fans | 7612.25 |  | 7612.25 | 100% |  | 7612.25 | 11376.4 | -3764.15 | 2014-09-29 | 2015-03-31 | 2014-11-01 | 2016-02-04
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E1833 | Augustine Repl TB5 Bushings | 0 |  | 0 |  |  | 15264.71 | 15584 | -319.29 | 2008-10-22 | 2050-07-08 | 2008-10-01 | 2009-01-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4062 | Crescent-Repl Arr & Bushings in TB1 | 0 |  | 0 |  |  | 11703.28 | 10372 | 1331.28 | 2009-02-03 | 2010-12-31 | 2009-02-01 | 2010-06-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4340 | Cold Spring rep HS arresters on TB1 | 0 |  | 0 |  |  | 3407.68 | 3989 | -581.32 | 2009-02-13 | 2010-03-01 | 2009-03-01 | 2010-02-09
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4816 | Empire - Install LTC Oil Filtration | 0 |  | 0 |  |  | 10212.88 | 10252 | -39.12 | 2009-03-11 | 2010-12-31 | 2009-11-01 | 2010-02-17
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E5944 | Cold Spring - Repl Recloser | 0 |  | 0 |  |  | 4300.9 | 6773 | -2472.1 | 2009-04-28 | 2009-12-30 | 2009-07-01 | 2009-07-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E6464 | Claryville - Repl Voltage Regulator | 0 |  | 0 |  |  | 12505.6 | 16933 | -4427.4 | 2009-05-19 | 2009-12-30 | 2009-05-01 | 2009-08-19
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | F1085 | Crescent -Repl Ckt 1587 Direct Trip | 0 |  | 0 |  |  | 16412.23 | 17522 | -1109.77 | 2009-10-09 | 2010-03-01 | 2009-12-01 | 2010-03-17
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | F9524 | Marshall rep VR 41 phase1 | 0 |  | 0 |  |  | 10240.99 | 6519 | 3721.99 | 2010-06-15 | 2010-08-18 | 2010-06-01 | 2010-09-16
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G0125 | Beaver replace voltage regulator | 0 |  | 0 |  |  | 10229.64 | 6232 | 3997.64 | 2010-07-06 | 2010-12-31 | 2010-07-01 | 2010-10-03
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G2254 | Decoursey replace reclosers | 0 |  | 0 |  |  | 476.75 | 431 | 45.75 | 2011-02-11 | 2011-05-31 | 2011-02-01 | 2011-05-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G2301 | Decoursey TB 3 failure | 0 |  | 0 |  |  | 33472.65 | 10066 | 23406.65 | 2011-02-15 | 2011-04-30 | 2011-02-01 | 2011-05-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G4175 | Kenton replace control battery | 0 |  | 0 |  |  | 15190.97 | 18188 | -2997.03 | 2011-07-27 | 2011-12-31 | 2011-08-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G4874 | Augustine Repl sta batteries | 0 |  | 0 |  |  | 13416.11 | 13690 | -273.89 | 2011-09-09 | 2012-03-31 | 2011-10-01 | 2012-01-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G7646 | Buffington H2 bushing changeout TB3 | 0 |  | 0 |  |  | 1847.76 | 6701.56 | -4853.8 | 2012-05-24 | 2012-08-31 | 2012-05-01 | 2012-08-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G7835 | Grant replace CB 211 after failure | 0 |  | 0 |  |  | 9123.9 | 7996.62 | 1127.28 | 2012-06-12 | 2012-12-22 | 2012-06-01 | 2012-11-16
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8347 | Wilder repl H1 bushing TB 3 | 0 |  | 0 |  |  | 7261.43 | 7496.55 | -235.12 | 2012-08-28 | 2012-12-28 | 2012-09-01 | 2013-03-06
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8416 | Claryville TB2 Bank failure | 0 |  | 0 |  |  | 22979.54 | 24962.54 | -1983 | 2012-09-10 | 2012-12-28 | 2012-09-01 | 2012-12-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8589 | Claryville CIR 42 repl Phase A VR | 0 |  | 0 |  |  | 4232.33 | 2262.25 | 1970.08 | 2012-10-05 | 2013-01-19 | 2012-10-01 | 2013-01-10
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8780 | Decoursey CIR 41 repl 3 reclosers | 0 |  | 0 |  |  | 2599.68 | 1131.12 | 1468.56 | 2012-11-01 | 2013-02-02 | 2012-11-01 | 2013-02-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | H0476 | Limaburg Repl low side bush on TB 2 | 0 |  | 0 |  |  | 19749.13 | 10247.54 | 9501.59 | 2013-07-25 | 2013-10-29 | 2013-07-01 | 2013-10-27
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | K4107 | Limaburg Repl failed TB 2 | 78277.62 |  | 78277.62 | 100% |  | 78277.62 | 62323.26 | 15954.36 | 2014-04-21 | 2014-09-30 | 2014-04-01 | 2014-08-08
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7105 | Dixie Repl Sta Batteries | 5754.53 |  | 5754.53 | 100% |  | 5754.53 | 9371.25 | -3616.72 | 2014-06-27 | 2015-03-31 | 2014-07-01 | 2014-11-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7106 | Hands Sub Repl Sta Batteries | 9574.12 |  | 9574.12 | 100% |  | 9574.12 | 10634.99 | -1060.87 | 2014-06-27 | 2015-03-31 | 2014-07-01 | 2014-11-05
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7107 | Buffington Repl Cooling Fans | 6505.08 |  | 6505.08 | 100% |  | 6505.08 | 5806.34 | 698.74 | 2014-06-27 | 2015-03-31 | 2014-08-01 | 2014-11-25
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3102 | Cresent Repl 48VDC Sta Batteries | 4033.85 |  | 4033.85 | 100% |  | 4033.85 | 10390.57 | -6356.72 | 2014-07-16 | 2015-03-31 | 2014-10-01 | 2015-06-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3103 | Bellevue Repl Sta Batteries | 8257.47 |  | 8257.47 | 100% |  | 8257.47 | 14912.34 | -6654.87 | 2014-07-16 | 2016-09-30 | 2014-10-01 | 2016-04-13
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3106 | Cold Spring Repl Sta Batteries | 10700.12 |  | 10700.12 | 100% |  | 10700.12 | 10023.94 | 676.18 | 2014-07-16 | 2015-03-31 | 2014-08-01 | 2014-11-18
75084-DE Kentucky Power Deliv - Ele | EMSBLSRV | D2508 | MW EMS Blade Server Upgrade | 0 |  | 0 |  |  | 5419.5 | 8919 | -3499.5 | 2008-01-10 | 2008-08-30 | 2008-01-01 | 2008-08-30
75084-DE Kentucky Power Deliv - Ele | EPS100 | D2185 | Erlanger Micro Upgrade | 0 |  | 0 |  |  | 1818 | 1908 | -90 | 2007-12-04 | 2008-02-28 | 2008-02-01 | 2008-01-27
75084-DE Kentucky Power Deliv - Ele | ESXIUPG14 | J9118 | 2014 ESXI Upgrade-Kentucky | 7237.96 |  | 7237.96 | 100% |  | 7237.96 | 6676 | 561.96 | 2014-04-11 | 2015-01-31 | 2014-04-01 | 2015-01-30
75084-DE Kentucky Power Deliv - Ele | F8.4ACRES | 8.4ACRESK | 8.4 ACRES FOR HEBRON SUB-KENTUCKY | 0 |  | 0 |  |  | 61500.18 | 60000 | 1500.18 | 2010-07-21 | 2010-10-01 | 2010-07-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | FAUTODESK | G3197 | AUTODESK 2012 UPGRADE | 0 |  | 0 |  |  | 10289.91 | 8429 | 1860.91 | 2011-05-02 | 2011-09-30 | 2011-05-01 | 2012-02-09
75084-DE Kentucky Power Deliv - Ele | FBLDENCLO | G6683 | CCA/NON-CCA ENCLOSURE | 0 |  | 0 |  |  | 3421.65 | 2969.7 | 451.95 | 2012-02-06 | 2012-03-15 | 2012-02-01 | 2012-08-23
75084-DE Kentucky Power Deliv - Ele | FCAORMRPL | G8039 | CAORM REPLACEMENT PROJ. | -4.27 |  | -4.27 | 100% |  | 1.0658e-14 | 1 | -1 | 2012-07-11 | 2013-08-30 | 2012-08-01 | 2013-09-25
75084-DE Kentucky Power Deliv - Ele | FDOMSIMPL | G9136 | DOMS IMPLEMENTATION W/AMI | 3702.15 |  | 3702.15 | 100% |  | 3963.25 | 216000 | -212036.75 | 2012-12-20 | 2017-03-31 | 2013-01-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | FDOMSIMPL | PCTAIT223 | DOMS IMPLEMENTATION W/AMI | 39613.24 |  | 39613.24 | 100% |  | 123903.45 | 216000 | -92096.55 | 2013-10-25 | 2016-12-31 | 2013-11-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | FEGIS/EMX | G4142 | EGIS/eMAX PD DEVICE INTEGRATION | 0 |  | 0 |  |  | 12059.65 | 16725 | -4665.35 | 2011-07-22 | 2012-10-30 | 2011-07-01 | 2012-09-28
75084-DE Kentucky Power Deliv - Ele | FEGISSYNK | EGISSYNKE | EGIS TO SYNERGEE INTERFACE | 0 |  | 0 |  |  | 47109.73 | 52945 | -5835.27 | 2011-01-27 | 2011-09-30 | 2011-02-01 | 2011-11-22
75084-DE Kentucky Power Deliv - Ele | FEMPCSITK | EMPCSITK | EMPCS CAOS/W2K8 R2 KENTUCKY | 0 |  | 0 |  |  | 2498.64 | 1396.05 | 1102.59 | 2010-08-04 | 2010-08-30 | 2010-09-01 | 2011-02-28
75084-DE Kentucky Power Deliv - Ele | FEMSFIREW | G4243 | EMS FIREWALL PROJ HW KENTUCKY | 0 |  | 0 |  |  | 988.52 | 43364.26 | -42375.74 | 2011-08-01 | 2012-04-01 | 2011-12-01 | 2012-07-31
75084-DE Kentucky Power Deliv - Ele | FEMSUPGRD | EMSUPGRVS | EMS EMP 2.6 UPGRADE PROJECT | 55926.99 |  | 55926.99 | 100% |  | 210750.47 | 211000 | -249.53 | 2011-03-30 | 2014-06-30 | 2011-09-01 | 2014-06-30
75084-DE Kentucky Power Deliv - Ele | FEMSUPGRD | G2860 | EMS EMP 2.6 UPGRADE PROJECT | 1004.89 |  | 1004.89 | 100% |  | 64278.93 | 2293 | 61985.93 | 2011-03-30 | 2014-06-30 | 2011-07-01 | 2014-06-30
75084-DE Kentucky Power Deliv - Ele | FENRGACCT | PCTASW937 | Energy Acctg. & Transm Stand. | 28396.49 |  | 28396.49 | 100% |  | 28396.49 | 96515 | -68118.51 | 2014-07-09 | 2016-04-30 | 2014-08-01 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | FESXIUPGR | G9133 | EMPCS-ESXI UPGRADE | 0 |  | 0 |  |  | 8288.7 | 8082.45 | 206.25 | 2012-12-20 | 2013-09-30 | 2012-12-01 | 2013-12-25
75084-DE Kentucky Power Deliv - Ele | FFLDMTREQ | G1528 | REPL OF FIELD METER TEST EQUIP | 0 |  | 0 |  |  | 65356.9 | 75630 | -10273.1 | 2010-11-18 | 2012-03-31 | 2011-12-01 | 2012-06-01
75084-DE Kentucky Power Deliv - Ele | FGISEAMKE | GISEAMKE | GIS-EAM R3 INTERFACE & SW-KENTUCKY | 0 |  | 0 |  |  | 24182.73 | 28545 | -4362.27 | 2009-10-20 | 2011-03-30 | 2009-11-01 | 2011-05-01
75084-DE Kentucky Power Deliv - Ele | FGISPLOTK | GISPLOTKE | GIS PLOTTING ENHANCEMENTS | 0 |  | 0 |  |  | 45184.55 | 8873 | 36311.55 | 2010-11-23 | 2011-06-30 | 2010-12-01 | 2011-08-16
75084-DE Kentucky Power Deliv - Ele | FITRNFCSK | G4864 | REPL INTEGR-ITRON FCS-KENT. | 0 |  | 0 |  |  | 41470.26 | 145532 | -104061.74 | 2011-09-08 | 2012-12-31 | 2011-09-01 | 2013-02-12
75084-DE Kentucky Power Deliv - Ele | FLKY0249E | DUKETEKYE | Fleet Off-Road Vehicles - KY | 0 |  | 0 |  |  | 121502.57 | 20000 | 101502.57 | 2009-08-11 | 2050-12-31 | 2010-05-01
75084-DE Kentucky Power Deliv - Ele | FMDT11KE | G5048 | MOBILE DISPATCH EXPANSION-KE | 0 |  | 0 |  |  | 37648.52 | 46900 | -9251.48 | 2011-09-22 | 2012-09-30 | 2011-10-01 | 2012-12-31
75084-DE Kentucky Power Deliv - Ele | FMDT11KE | G6983 | MWMS USER SW LICENSES | 0 |  | 0 |  |  | 3598.06 | 2973.6 | 624.46 | 2012-03-08 | 2012-06-30 | 2012-06-01 | 2012-09-05
75084-DE Kentucky Power Deliv - Ele | FMWCF53SK | CF53AUGUS | Purch Panasonic CF53s repl MDTs | 239003.1 |  | 239003.1 | 100% |  | 239003.1 | 158146 | 80857.1 | 2014-08-04 | 2017-03-31 | 2014-09-01 | 2017-03-05
75084-DE Kentucky Power Deliv - Ele | FMWMSW7 | H0499 | MWMS W7 REMEDIATION PROJ | 267.88 |  | 267.88 | 100% |  | 675.25 | 9972 | -9296.75 | 2013-08-01 | 2013-10-31 | 2013-08-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | FN1216KY | N1216SWKY | NINT1216 Tripwire Enterprise (TE) | 75634.8 |  | 75634.8 | 100% |  | 75634.8 | 18269 | 57365.8 | 2014-08-08 | 2015-11-30 | 2014-08-01 | 2015-07-27
75084-DE Kentucky Power Deliv - Ele | FNETSCALR | N5103 | Upgrade to Net Scaler | 5952.77 |  | 5952.77 | 100% |  | 5952.77 | 5460 | 492.77 | 2014-06-25 | 2015-06-30 | 2014-07-01 | 2015-06-20
75084-DE Kentucky Power Deliv - Ele | FNINT1229 | TRNPRIMAV | NINT1229 - Trans Primavera Upgr | 10867.48 |  | 10867.48 | 100% |  | 10867.48 | 78058.34 | -67190.86 | 2014-08-03 | 2017-10-31 | 2014-08-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | FOKY0082 | E1673 | Kenton Install Electric Fence | 0 |  | 0 |  |  | 1593.78 | 1542 | 51.78 | 2008-10-15 | 2008-12-31 | 2008-10-01 | 2008-10-29
75084-DE Kentucky Power Deliv - Ele | FORCHARDK | ORCHARDKE | 1140 ORCHARD ST-YORK SUB-KENTUCKY | 0 |  | 0 |  |  | 28802.78 | 28072.72 | 730.06 | 2010-07-21 | 2010-10-01 | 2010-07-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | FPCTAVM | PCTAVM | VEGETATION MGMT-KENTUCKY | -33533.42 |  | -33533.42 | 100% |  | 10.89 | 25919 | -25908.11 | 2012-11-30 | 2018-01-31 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | FPTLOADKE | F3706 | PTLOAD-TOOL TO RATE TRNSF-KENTUCKY | 0 |  | 0 |  |  | 13342.02 | 14000 | -657.98 | 2010-01-05 | 2010-10-31 | 2010-03-01 | 2011-03-08
75084-DE Kentucky Power Deliv - Ele | FRAC&SWCH | RAC&SWCHK | RACK & SWITCH INSTALLS | 0 |  | 0 |  |  | 3759.59 | 14463 | -10703.41 | 2010-12-02 | 2010-12-31 | 2011-03-01 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | FRADIOKY | RADIOKENT | IDEN RADIO-KENTUCKY PROJECT | 0 |  | 0 |  |  | 366057.54 | 224500 | 141557.54 | 2010-01-15 | 2011-07-31 | 2010-02-01 | 2011-09-01
75084-DE Kentucky Power Deliv - Ele | FRMRE12RR | FRM12INFR | 2012 COMM REPL INFRASTR-KEN | 0 |  | 0 |  |  | 156869.34 | 156870 | -0.66 | 2012-05-02 | 2014-04-30 | 2012-05-01 | 2014-05-31
75084-DE Kentucky Power Deliv - Ele | FRMRE13RR | FRM13INFR | 2013 PD COMM REPL INFRA-KENT | 113203.35 |  | 113203.35 | 100% |  | 142857.62 | 73868 | 68989.62 | 2013-02-22 | 2015-07-30 | 2013-03-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | FRR19&AUG | RR19&AUG | 19TH & AUGUSTINE CC RR BLKT | 3718.2 |  | 3718.2 | 100% |  | 15188.13 | 1 | 15187.13 | 2010-08-30 | 2025-12-15 | 2010-11-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRERLANG | ERLANGER CC RR BLKT | 0 |  | 0 |  |  | 27778.55 | 1 | 27777.55 | 2010-08-30 | 2025-12-15 | 2010-11-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRERLNGMW | ERLANGER MICROWAV-RR BLKT | 0 |  | 0 |  |  | 1122.18 | 1 | 1121.18 | 2011-05-09 | 2025-12-15 | 2011-10-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRKENTON | Kenton Substation Blanket | 0 |  | 0 |  |  | 139.45 | 50000 | -49860.55 | 2012-07-27 | 2025-12-15 | 2012-07-01
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANHWKE | SAN EXPANSION - EMC NS-960 | 0 |  | 0 |  |  | 17560.4 | 62997.65 | -45437.25 | 2010-11-19 | 2011-03-31 | 2010-12-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANSWKE | SAN EXPANSION SOFTWARE | 0 |  | 0 |  |  | 4451.2 | 11152.26 | -6701.06 | 2010-11-19 | 2011-03-31 | 2010-12-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANUPGRKE | SAN FIBR CHANNEL SWCH UPGR | 0 |  | 0 |  |  | 3645.7 | 4023 | -377.3 | 2012-09-05 | 2013-02-18 | 2012-10-01 | 2013-06-13
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANXP12KE | SAN EXPANSION - EMC NS-960 | 0 |  | 0 |  |  | 9398.11 | 9781 | -382.89 | 2012-03-06 | 2012-05-15 | 2012-05-01 | 2012-08-15
75084-DE Kentucky Power Deliv - Ele | FSRVCO201 | F3205 | ASSET MGMT OPT-KENTUCKY | 0 |  | 0 |  |  | 17905.67 | 13181 | 4724.67 | 2009-12-17 | 2010-09-01 | 2009-12-01 | 2009-07-04
75084-DE Kentucky Power Deliv - Ele | FSRVCO201 | F5864 | PLS-CADD TO EMAX INTEGRATION | 0 |  | 0 |  |  | 21383.16 | 21313.15 | 70.01 | 2010-02-25 | 2010-11-30 | 2010-02-01 | 2010-02-28
75084-DE Kentucky Power Deliv - Ele | FSRVCOM12 | G7280 | SUBSTATION DESIGN SOLUTION | 0 |  | 0 |  |  | 89527.8 | 770000 | -680472.2 | 2012-04-18 | 2011-07-01 | 2012-05-01 | 2011-06-25
75084-DE Kentucky Power Deliv - Ele | FSTRMTRLR | STORMTRLR | IDEN STORM TRAILER | 0 |  | 0 |  |  | 96106.51 | 124505 | -28398.49 | 2011-12-16 | 2012-11-15 | 2011-12-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | FTDITKE | TDITCHAR | PD KENTUCKY IT HARDWARE | 0 |  | 0 |  |  | 144.8 | 0 | 144.8 | 2009-08-27 | 2025-12-25 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | FTDITKY | G7195 | CC BLKT IT HW-ERLANGER, KE OP CTR | 0 |  | 0 |  |  | 15422.26 | 11000 | 4422.26 | 2012-04-10 | 2012-06-24 | 2012-05-01
75084-DE Kentucky Power Deliv - Ele | FTIMPHAII | G8986 | TIM PHASE II UPGRADE | 87264.98 |  | 87264.98 | 100% |  | 301140.04 | 187081 | 114059.04 | 2012-11-26 | 2014-12-30 | 2012-12-01 | 2014-06-24
75084-DE Kentucky Power Deliv - Ele | GLPRDFA | GLPRDKY | Pole Repl Gnd Line-D | 0 |  | 0 |  |  | 850454.86 | 200 | 850254.86 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | E3824 | Pole Repl Gnd Line-T | 0 |  | 0 |  |  | 53058 | 10742 | 42316 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | GLPRTKY | Pole Repl Gnd Line-T | 70597.48 |  | 70597.48 | 100% |  | 451092.75 | 100 | 450992.75 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | ITKY0157 | E4303 | MDT Toughbooks - Ky | 0 |  | 0 |  |  | 218435.18 | 138204 | 80231.18 | 2009-02-12 | 2009-10-31 | 2009-04-01 | 2010-02-28
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8336 | Crescent Upgrade Frame Relay Equip | 5329.37 |  | 5329.37 | 100% |  | 8564.79 | 24507 | -15942.21 | 2012-08-27 | 2014-03-31 | 2012-10-01 | 2013-12-06
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8338 | Kenton Upgrage Frame Relay Equip | -122 |  | -122 | 100% |  | 13966.48 | 40175 | -26208.52 | 2012-08-27 | 2014-03-31 | 2012-10-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8339 | Long Branch Upgrd Frame Relay Equip | -154 |  | -154 | 100% |  | 32120.9 | 49736 | -17615.1 | 2012-08-27 | 2014-03-31 | 2012-11-01 | 2013-07-17
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8340 | Oakbrook Upgrade Frame Relay Equip | -483.6 |  | -483.6 | 100% |  | 29745.64 | 49736 | -19990.36 | 2012-08-27 | 2014-03-31 | 2012-11-01 | 2014-01-02
75084-DE Kentucky Power Deliv - Ele | ITKYFR13D | G9165 | Hebron Upgrd Frame Relay Equip | -428.12 |  | -428.12 | 100% |  | 29302.18 | 39226 | -9923.82 | 2013-01-03 | 2014-09-01 | 2013-05-01 | 2013-10-10
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1124 | Blackwell Upgrd Frame Relay Equip | 19419.08 |  | 19419.08 | 100% |  | 19591.14 | 36432 | -16840.86 | 2013-10-29 | 2015-09-01 | 2013-12-01 | 2014-07-02
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1126 | Covington Upgrade Frame Relay Equip | 19491.88 |  | 19491.88 | 100% |  | 19635.46 | 36328 | -16692.54 | 2013-10-29 | 2015-09-01 | 2013-12-01 | 2014-06-05
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1128 | Dayton Upgrade Frame Relay Equip | 21872.2 |  | 21872.2 | 100% |  | 25237.59 | 36328 | -11090.41 | 2013-10-29 | 2015-09-01 | 2013-11-01 | 2014-05-14
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1129 | Mt. Zion Upgrade Frame Relay Equip | 30964.4 |  | 30964.4 | 100% |  | 30964.4 | 36328 | -5363.6 | 2013-10-29 | 2015-09-01 | 2014-01-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1134 | Thomas More Upgrd Frame Rlay Equip | 37160.8 |  | 37160.8 | 100% |  | 39392.37 | 36328 | 3064.37 | 2013-10-29 | 2015-09-01 | 2013-11-01 | 2015-02-11
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1136 | Hands Upgrade Frame Relay Equip | 30340.22 |  | 30340.22 | 100% |  | 30412.03 | 61052 | -30639.97 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-07-31
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1137 | Kentucky Univ Upgrd Frme Rlay Equip | 33138.99 |  | 33138.99 | 100% |  | 33210.8 | 61052 | -27841.2 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-10-09
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1138 | York Upgrade Frame Relay Equip | 30672.8 |  | 30672.8 | 100% |  | 30744.61 | 61052 | -30307.39 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-09-25
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1139 | Bellevue Upgrd Frame Relay Equip | 58116.64 |  | 58116.64 | 100% |  | 58116.64 | 61052 | -2935.36 | 2013-10-30 | 2015-09-01 | 2014-01-01 | 2015-01-16
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1140 | Cold Spring Upgrd Frame Relay Equip | 66994.91 |  | 66994.91 | 100% |  | 66994.91 | 63953 | 3041.91 | 2013-10-30 | 2015-09-01 | 2014-01-01 | 2014-07-16
75084-DE Kentucky Power Deliv - Ele | ITMW0195 | E5745 | Pole Inspection Replacement - KY | 0 |  | 0 |  |  | 81403.21 | 17894 | 63509.21 | 2009-04-21 | 2011-04-30 | 2009-04-01 | 2011-12-31
75084-DE Kentucky Power Deliv - Ele | MOFA | E3825 | Major Outage Followup-D | 0 |  | 0 |  |  | 0 | 13363 | -13363 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | MOFA | H1271 | OR 4599261 Bury 3PH Primary Covgtn | 49988.97 |  | 49988.97 | 100% |  | 53536.61 | 54433.57 | -896.96 | 2013-11-20 | 2014-11-25 | 2013-11-01 | 2014-11-14
75084-DE Kentucky Power Deliv - Ele | MOFA | MOKY | Major Outage Followup-D | 0 |  | 0 |  |  | -4.3201e-12 | 100 | -100 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | MTRCAPFA | ORDERTRK | Assemble Meter Sets | 1485.1 |  | 1485.1 | 100% |  | 171034.69 | 92 | 170942.69 | 2008-07-01 | 2025-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | MTRCAPFA | SCRAPMETK | Scrap Meters | 0 |  | 0 |  |  | 0 | 92 | -92 | 2008-07-01 | 2025-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | MTRTOOLFA | TBIMTRLAB | Metering Capital Tools | 2120.32 |  | 2120.32 | 100% |  | 23498.19 | 1 | 23497.19 | 2008-07-01 | 2050-12-31 | 2009-07-01
75084-DE Kentucky Power Deliv - Ele | NBFA | G4362 | EMAX 2432584 Envision Center | 0 |  | 0 |  |  | 18126.21 | 45510.74 | -27384.53 | 2011-08-08 | 2012-03-31 | 2011-08-01 | 2012-01-25
75084-DE Kentucky Power Deliv - Ele | NBFA | G5853 | EMAX 2516744 South Service Rd | 0 |  | 0 |  |  | 32109.43 | 58886.31 | -26776.88 | 2011-11-16 | 2012-12-31 | 2011-12-01 | 2012-08-21
75084-DE Kentucky Power Deliv - Ele | NBFA | G6517 | EMAX 2869082 Post Glover Co | 0 |  | 0 |  |  | 18957.6 | 23028.16 | -4070.56 | 2012-01-19 | 2012-12-31 | 2012-02-01 | 2012-06-29
75084-DE Kentucky Power Deliv - Ele | NBFA | G6573 | EMAX 2920684 15 Spiral Dr | 0 |  | 0 |  |  | 11667.36 | 3084.53 | 8582.83 | 2012-01-26 | 2012-12-31 | 2012-03-01 | 2012-06-27
75084-DE Kentucky Power Deliv - Ele | NBFA | G8713 | NB emax 3478683 1780 Anderson Blvd | 0 |  | 0 |  |  | 17799.34 | 14010.05 | 3789.29 | 2012-10-22 | 2013-10-30 | 2013-01-01 | 2013-06-04
75084-DE Kentucky Power Deliv - Ele | NBFA | G9304 | NB emax 3777704 7979 Vulcan Dr | 0 |  | 0 |  |  | 35799.65 | 16278.41 | 19521.24 | 2013-01-17 | 2014-01-31 | 2013-04-01 | 2013-10-18
75084-DE Kentucky Power Deliv - Ele | NBFA | H0049 | NB emax 4052073 Retail North Bldg | 0 |  | 0 |  |  | 7068.61 | 6544.79 | 523.82 | 2013-05-02 | 2013-11-30 | 2013-05-01 | 2013-11-16
75084-DE Kentucky Power Deliv - Ele | NBFA | H0104 | NB emax 831 Heights Blvd | 0 |  | 0 |  |  | 4493.18 | 1688.38 | 2804.8 | 2013-05-14 | 2014-03-31 | 2013-07-01 | 2013-12-10
75084-DE Kentucky Power Deliv - Ele | NBFA | H0444 | NB emax 4158179 Old Alexandria Pike | -1056.71 |  | -1056.71 | 100% |  | 69133.62 | 41057.06 | 28076.56 | 2013-07-19 | 2014-11-16 | 2013-09-01 | 2014-02-04
75084-DE Kentucky Power Deliv - Ele | NBFA | H0503 | NB emax 4314177 IDI @ 30 Transport | 79269.25 |  | 79269.25 | 100% |  | 79269.25 | 84310.49 | -5041.24 | 2013-08-05 | 2015-01-14 | 2014-01-01 | 2014-07-31
75084-DE Kentucky Power Deliv - Ele | NBFA | H0638 | NB emax 3296995 Arcadia Ph A | 380.7 |  | 380.7 | 100% |  | -65977.39 | 92754.88 | -158732.27 | 2013-08-27 | 2014-11-30 | 2013-09-01 | 2014-03-27
75084-DE Kentucky Power Deliv - Ele | NBFA | H1381 | JT 4655806 Arcadia West PH A electr | 126957.02 |  | 126957.02 | 100% |  | 73653.24 | 149749.52 | -76096.28 | 2013-12-04 | 2014-11-29 | 2013-12-01 | 2014-07-28
75084-DE Kentucky Power Deliv - Ele | NBFA | H1382 | NB 3941206 Stillbrooke Subdv Felice | 18021.21 |  | 18021.21 | 100% |  | 18021.21 | 44694.66 | -26673.45 | 2013-12-04 | 2014-11-30 | 2014-01-01 | 2014-08-08
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY1Q12 | Q1 2012 IK KY Blanket Roll Up Proj | 96158.5 |  | 96158.5 | 100% |  | 5870552.06 | 100 | 5870452.06 | 2012-02-03 | 2012-12-31 | 2012-01-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2013 | 2013 IK KY Blanket Roll Up Proj | 1002156.02 |  | 1002156.02 | 100% |  | 10494333.25 | 100 | 10494233.25 | 2012-12-21 | 2013-12-31 | 2012-12-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2014 | 2014 IK KY Blanket Roll Up Proj | 7379839.81 |  | 7379839.81 | 100% |  | 8190663.87 | 1 | 8190662.87 | 2013-12-27 | 2014-12-31 | 2013-12-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2015 | 2015 KY Dist Lines (IK) Roll | 420552.68 |  | 420552.68 | 100% |  | 420552.68 | 1 | 420551.68 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2015T | 2015 KY Dist Lines (IK) Roll - T | 682869.16 |  | 682869.16 | 100% |  | 682869.16 | 1 | 682868.16 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKYROL11 | 2011 IK KY Roll Up Blanket Project | 0 |  | 0 |  |  | 9791865.05 | 100 | 9791765.05 | 2011-12-16 | 2011-12-31 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | NBFA | K7108 | NB 4686312 512 Oak Ludlow | 7627.22 |  | 7627.22 | 100% |  | 7627.22 | 7804.98 | -177.76 | 2014-04-28 | 2015-04-28 | 2014-06-01 | 2014-09-24
75084-DE Kentucky Power Deliv - Ele | NBFA | MATRETCAP | Material Returns Capital Only | -97.34 |  | -97.34 | 100% |  | -97.34 | 10000 | -10097.34 | 2012-08-28 | 2050-12-31 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | NBFA | NBKY | Customer Adds-MW-D | 7983.86 |  | 7983.86 | 100% |  | 5029449.1 | 200 | 5029249.1 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | NBFA | O4116 | NB 4714818 4455 Olympic Blvd | 11208.75 |  | 11208.75 | 100% |  | 11208.75 | 33237.99 | -22029.24 | 2014-07-17 | 2015-11-28 | 2014-08-01 | 2014-10-17
75084-DE Kentucky Power Deliv - Ele | NBFA | O4137 | NB 4706432 629 Madison | 65860.81 |  | 65860.81 | 100% |  | 65860.81 | 25675.44 | 40185.37 | 2014-07-21 | 2015-06-14 | 2014-07-01 | 2015-01-22
75084-DE Kentucky Power Deliv - Ele | NBFA | P6718 | NB 5846054 Sunny Ridge Estates | -13846 |  | -13846 | 100% |  | -13846 | 74531.15 | -88377.15 | 2014-10-31 | 2015-11-26 | 2014-12-01 | 2015-07-28
75084-DE Kentucky Power Deliv - Ele | NBFA | P7033 | NB 6573310 15 Spiral Dr | -43124.65 |  | -43124.65 | 100% |  | -43124.65 | 91801.87 | -134926.52 | 2014-12-12 | 2015-11-01 | 2014-12-01 | 2015-08-12
75084-DE Kentucky Power Deliv - Ele | NEWCAPFA | NEWCAPKY | New Capacitors | 0 |  | 0 |  |  | 33297.67 | 101 | 33196.67 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | NINT686FP | NINT686 | NINT686 IEE C+I Upgrade Project | 4070.34 |  | 4070.34 | 100% |  | 4070.34 | 30000 | -25929.66 | 2014-06-12 | 2014-10-23 | 2014-06-01 | 2015-04-15
75084-DE Kentucky Power Deliv - Ele | NPDLOGMW | E0222 | Midwest Log Aggregation - Ky - HW | 0 |  | 0 |  |  | 14745.6 | 46258 | -31512.4 | 2008-07-24 | 2008-12-31 | 2008-07-01 | 2009-02-28
75084-DE Kentucky Power Deliv - Ele | NPDLOGMW | E0234 | Midwest Log Aggregation - Ky - SW | 0 |  | 0 |  |  | 2203.32 | 8163 | -5959.68 | 2008-07-24 | 2008-12-31 | 2008-10-01 | 2009-02-28
75084-DE Kentucky Power Deliv - Ele | NUMARAT | E4634 | EMS NUMARA - KY | 0 |  | 0 |  |  | 5551.02 | 4443 | 1108.02 | 2009-03-02 | 2009-09-30 | 2009-03-01 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | G8553 | ST emax 2178946 John Hills Rd NKU | -94.88 |  | -94.88 | 100% |  | 48605 | 105449.16 | -56844.16 | 2012-10-01 | 2014-03-15 | 2012-11-01 | 2013-06-05
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE08KY | Lighting-OLE-Inst | 0 |  | 0 |  |  | -3546.83 | 100 | -3646.83 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2008-12-20
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE11KY | Lighting-OLE-Inst-2011 | 0 |  | 0 |  |  | 0 | 100085 | -100085 | 2011-01-04 | 2012-12-31 | 2011-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE12KY | Kentucky Lighting OLE Install 2012 | 0 |  | 0 |  |  | 84224.87 | 100000 | -15775.13 | 2011-11-14 | 2013-06-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE13KY | Kentucky Lighting OLE Install 2013 | -22006.5 |  | -22006.5 | 100% |  | 0 | 50085 | -50085 | 2013-01-04 | 2014-10-01 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE14KY | Kentuck Lighting OLE Install 2014 | 0 |  | 0 |  |  | 0 | 85 | -85 | 2014-01-02 | 2015-09-30 | 2014-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE14KY | Kentuck Lighting OLE Install 2014 | 0 |  | 0 |  |  | 0 | 85 | -85 | 2014-01-02 | 2015-09-30 | 2014-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE08RPKY | Light Repl-OLE | 0 |  | 0 |  |  | 2.9559e-12 | 90 | -90 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-04-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE11RPKY | Light Repl-OLE-2011 | 0 |  | 0 |  |  | 0 | 84 | -84 | 2011-01-04 | 2050-12-31 | 2011-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE12RPKY | Kentucky Lighting Replace OLE 2012 | 0 |  | 0 |  |  | 450 | 32000 | -31550 | 2011-11-14 | 2013-06-01 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE13RPKY | Kentucky Lighting OLE Replace 2013 | -9404.88 |  | -9404.88 | 100% |  | 0 | 10083 | -10083 | 2013-01-04 | 2014-10-01 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | FNCTOFF | PD Indirect Offset | 0 |  | 0 |  |  | -2.07 | 0 | -2.07 | 2008-07-01 | 2008-06-28 21:34 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NONOLE | Overhead Non OLE Lt Insp/Maint | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2020-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NUPOLSET | Non Utility work-Exp | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NUTRANSF | Transfers-other companies-exp | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | OLEINT | OLE Interest | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-10-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | OUTAGES | Routine Outages | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | TEMPSVC | Temporary Service | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2008-06-28 21:34 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | OPTIMALC | E1235 | Project Optimization Sftwr-Ky | 0 |  | 0 |  |  | 12896.77 | 14000 | -1103.23 | 2008-09-22 | 2010-12-31 | 2008-10-01 | 2009-07-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | E1227 | Storm 12 - Ike (Kentucky) | 0 |  | 0 |  |  | 219722.62 | 9200 | 210522.62 | 2008-09-19 | 2050-12-31 | 2008-09-01 | 2008-12-18
75084-DE Kentucky Power Deliv - Ele | ORDFA | E4291 | STORM 1 - 2009 - CAPITAL | 0 |  | 0 |  |  | 0 | 39105.32 | -39105.32 | 2009-02-12 | 2009-06-01 | 2009-02-01 | 2009-03-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OLE09KY | Lighting-OLE-Inst | 0 |  | 0 |  |  | 11031.05 | 97100 | -86068.95 | 2009-01-02 | 2050-12-31 | 2009-01-01 | 2009-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | OLE09RPKY | Light Repl-OLE | 0 |  | 0 |  |  | 914.48 | 97100 | -96185.52 | 2009-01-02 | 2050-12-31 | 2009-02-01 | 2009-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | ORDKY | Outage Restoration Cap-D | 0 |  | 0 |  |  | 159705.12 | 200 | 159505.12 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OUTRFUKY | Outage Reliability FollowUp Capital | -26991.41 |  | -26991.41 | 100% |  | 0 | 50000 | -50000 | 2012-05-09 | 2050-12-31 | 2012-09-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1102CP | Journal KY storm costs O&M to CAP | 0 |  | 0 |  |  | 1931.19 | 1985.66 | -54.47 | 2011-07-01 | 2012-07-31 | 2011-06-01 | 2011-09-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1203DC | Kentucky Storm O&M to Capital | 0 |  | 0 |  |  | 34459.11 | 42865.9 | -8406.79 | 2012-09-28 | 2012-10-31 | 2012-09-01 | 2012-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1204DC | Kentucky Storm O&M to Capital | 0 |  | 0 |  |  | 2532.42 | 2000 | 532.42 | 2012-12-31 | 2013-03-31 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1302DC | KENTUCKY O&M TO CAPITAL JOURNAL Q 2 | -766.25 |  | -766.25 | 100% |  | 16563.88 | 20425.5 | -3861.62 | 2013-06-20 | 2014-03-30 | 2013-06-01 | 2013-10-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1303DC | KENTUCKY O&M TO CAPITAL JRNL Q3 & 4 | -1.74 |  | -1.74 | 100% |  | 19866.39 | 22145.46 | -2279.07 | 2013-06-20 | 2014-03-30 | 2013-12-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1401DC | KENTUCKY O&M TO CAPITAL JOURNAL Q 1 | 1486.23 |  | 1486.23 | 100% |  | 1486.23 | 1330.27 | 155.96 | 2014-04-28 | 2016-03-31 | 2014-05-01 | 2014-09-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1404DC | Kentucky O&M - CAPITAL JOURNAL Q3&4 | 18026.67 |  | 18026.67 | 100% |  | 18026.67 | 20382.68 | -2356.01 | 2014-12-30 | 2016-03-31 | 2014-12-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | ORTFA | ORTKY | Outage Restoration Cap-T | -924.18 |  | -924.18 | 100% |  | 19939.99 | 100 | 19839.99 | 2010-06-28 | 2050-12-31 | 2011-04-01
75084-DE Kentucky Power Deliv - Ele | ORTFA | SKY1201TC | Kentucky Storm O&M to cap Trans | 0 |  | 0 |  |  | 65330.32 | 66245.76 | -915.44 | 2012-03-29 | 2012-07-31 | 2012-03-01 | 2012-06-30
75084-DE Kentucky Power Deliv - Ele | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 23665.26 |  | 23665.26 | 100% |  | 23665.26 | 19870 | 3795.26 | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75084-DE Kentucky Power Deliv - Ele | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | 8282.58 |  | 8282.58 | 100% |  | 8282.58 | 9783 | -1500.42 | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75084-DE Kentucky Power Deliv - Ele | PCTAIT85C | PCTAT85C | NetMotion Implementation INT85C | 19779.27 |  | 19779.27 | 100% |  | 19779.27 | 17851 | 1928.27 | 2014-06-08 | 2017-03-30 | 2014-06-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITH31 | INT165 Hardware | 458.1 |  | 458.1 | 100% |  | 458.1 | 187177 | -186718.9 | 2014-08-14 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITS31 | INT165 Software | 2198.64 |  | 2198.64 | 100% |  | 2198.64 | 621633 | -619434.36 | 2014-08-14 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITX03 | INT165 X 1 SOFTWARE | 14088.02 |  | 14088.02 | 100% |  | 14088.02 | 54733 | -40644.98 | 2014-08-24 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITX04 | INT165 X 1 Hardware | 1739.5 |  | 1739.5 | 100% |  | 1739.5 | 14842 | -13102.5 | 2014-08-24 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITS41 | INT177 Software | 2014.59 |  | 2014.59 | 100% |  | 2014.59 | 46060 | -44045.41 | 2014-07-28 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITX07 | INT177 X 2 SOFTWARE | 2.78 |  | 2.78 | 100% |  | 2.78 | 5835 | -5832.22 | 2014-08-24 | 2018-01-31 | 2014-12-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITX10 | INT177 X 3 Software | 3489.7 |  | 3489.7 | 100% |  | 3489.7 | 1585 | 1904.7 | 2014-08-24 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF5 | PCTAITS51 | INT82b Software | 578.65 |  | 578.65 | 100% |  | 578.65 | 134548 | -133969.35 | 2014-08-17 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF6 | PCTAITH61 | INT83 Hardware | 1166.13 |  | 1166.13 | 100% |  | 1166.13 | 11602 | -10435.87 | 2014-08-18 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF6 | PCTAITS61 | INT83 Software | 1408.06 |  | 1408.06 | 100% |  | 1408.06 | 73320 | -71911.94 | 2014-08-18 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PILCFA | E1881 | NKU -Customer Switchgear | 0 |  | 0 |  |  | 0 | 71200 | -71200 | 2008-10-24 | 2009-06-01 | 2008-11-01 | 2009-09-19
75084-DE Kentucky Power Deliv - Ele | PILCFA | E3829 | UG Cable Repl-PILC | 0 |  | 0 |  |  | 0 | 14242 | -14242 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | PILCFA | L9117 | UG 5466220 Buffington 45 PILC Repl | 26825.45 |  | 26825.45 | 100% |  | 26825.45 | 23138.33 | 3687.12 | 2014-05-22 | 2015-11-30 | 2014-07-01 | 2015-02-04
75084-DE Kentucky Power Deliv - Ele | PILCFA | PILCKY | UG Cable Repl-PILC | 0 |  | 0 |  |  | 16236.36 | 100 | 16136.36 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | PILCFA | POTTKY | Dline Pothead Termination KY | 0 |  | 0 |  |  | -3.638e-12 | 60000 | -60000 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | PRDFA | F3394 | CHARGING 2009 BKTS to SPEC-KENTUCKY | 0 |  | 0 |  |  | 233994.57 | 184000 | 49994.57 | 2009-12-22 | 2009-12-31 | 2009-12-01 | 2010-03-31
75084-DE Kentucky Power Deliv - Ele | PRDFA | H1728 | PR 4841795 Emerson Electric Reroute | 53531.07 |  | 53531.07 | 100% |  | 53531.07 | 56682.07 | -3151 | 2014-01-27 | 2015-03-31 | 2014-02-01 | 2014-10-31
75084-DE Kentucky Power Deliv - Ele | PRDFA | LARCUKY | Limited Access Road Crossing Upgrad | -253478.4 |  | -253478.4 | 100% |  | 0 | 100000 | -100000 | 2012-05-23 | 2050-12-31 | 2012-10-01
75084-DE Kentucky Power Deliv - Ele | PRDFA | PRDKY | Pole Repl Other-D | 2286 |  | 2286 | 100% |  | 777107.27 | 200 | 776907.27 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | PRTFA | PRTKY | Pole Repl Other-T | 16904.3 |  | 16904.3 | 100% |  | 211886.37 | 200 | 211686.37 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RCLFA | ELASTIMOL | Elastimold e-recloser pilot | -376.32 |  | -376.32 | 100% |  | 55832.08 | 51290.35 | 4541.73 | 2012-09-06 | 2014-03-31 | 2012-09-01 | 2014-02-01
75084-DE Kentucky Power Deliv - Ele | RCLFA | RCLKY | Recloser Inst/Rem | 0 |  | 0 |  |  | 73437.47 | 200 | 73237.47 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | REGFA | E3832 | Regulator Inst/Rem | 0 |  | 0 |  |  | 0 | 19896 | -19896 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | REGFA | REGKY | Regulator Inst/Rem | -25.1 |  | -25.1 | 100% |  | -1.3074e-12 | 100 | -100 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | E1613 | PP#924827 9Sanitati District #1 | 0 |  | 0 |  |  | 0 | 21964 | -21964 | 2008-10-13 | 2009-03-31 | 2008-10-01 | 2007-12-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | E1614 | PP#949527 Sanitation District #1 | 0 |  | 0 |  |  | 0 | 151815 | -151815 | 2008-10-13 | 2009-03-31 | 2008-10-01 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | E3613 | PP#1038389 S FT THOMAS AVE @ RIVER | 54641.47 |  | 54641.47 | 100% |  | 71990.4 | 223261 | -151270.6 | 2009-01-14 | 2010-12-31 | 2009-01-01 | 2010-04-30
75084-DE Kentucky Power Deliv - Ele | RELDFA | F3824 | eMax#213832 Ky 237 Camp Ernst-Pleas | 0 |  | 0 |  |  | 179894.38 | 175000 | 4894.38 | 2010-01-08 | 2015-01-06 | 2010-01-01 | 2010-10-07
75084-DE Kentucky Power Deliv - Ele | RELDFA | F7846 | RI-Industrial Rd-Dixie to Turkeyfot | 0 |  | 0 |  |  | 96927.03 | 1295335.09 | -1198408.06 | 2010-04-27 | 2013-03-31 | 2010-05-01 | 2012-08-20
75084-DE Kentucky Power Deliv - Ele | RELDFA | F8924 | EMAX #585031 Johns Hill Rd | -1183.78 |  | -1183.78 | 100% |  | 243710.6 | 64812.17 | 178898.43 | 2010-06-01 | 2013-04-01 | 2010-06-01 | 2012-10-31
75084-DE Kentucky Power Deliv - Ele | RELDFA | F9264 | EMAX #462348 31 Eastern Avenue | 0 |  | 0 |  |  | 111543.39 | 35495.98 | 76047.41 | 2010-06-08 | 2010-12-31 | 2010-06-01 | 2010-12-21
75084-DE Kentucky Power Deliv - Ele | RELDFA | F9407 | EMAX 613555 RI-Taylor Mil Rd Recon | 0 |  | 0 |  |  | 1014861.69 | 885879.22 | 128982.47 | 2010-06-10 | 2012-05-31 | 2010-06-01 | 2012-02-11
75084-DE Kentucky Power Deliv - Ele | RELDFA | G0973 | EMAX #1009228 Taylor Mill Reconst | 0 |  | 0 |  |  | 21838.71 | 109860.93 | -88022.22 | 2010-09-14 | 2015-06-30 | 2010-09-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2194 | EMAX 1737953 NKU Univ Dr Ext | -238215.89 |  | -238215.89 | 100% |  | -617.12 | 401620.62 | -402237.74 | 2011-02-08 | 2014-09-08 | 2011-02-01 | 2013-02-08
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2456 | EMAX 1983805 RI-Hands Pk w/o KY 16 | 0 |  | 0 |  |  | 66191.75 | 39319.39 | 26872.36 | 2011-03-01 | 2015-02-01 | 2011-03-01 | 2011-08-16
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2535 | EMAX 1783672 7660 Turfway Rd | 0 |  | 0 |  |  | 73189.28 | 74947.26 | -1757.98 | 2011-03-04 | 2012-03-31 | 2011-03-01 | 2012-02-04
75084-DE Kentucky Power Deliv - Ele | RELDFA | G5515 | EMAX 2690060 377 Richwood Rd | 0 |  | 0 |  |  | 169.42 | 10846.41 | -10676.99 | 2011-10-27 | 2012-03-31 | 2011-11-01 | 2012-02-17
75084-DE Kentucky Power Deliv - Ele | RELDFA | G5905 | EMAX 2760735 Camp Ernst (KY 237) | 0 |  | 0 |  |  | 84548.91 | 99082.68 | -14533.77 | 2011-11-21 | 2012-12-31 | 2012-02-01 | 2012-08-18
75084-DE Kentucky Power Deliv - Ele | RELDFA | G6642 | EMAX 2943027 KY 16 | 868.74 |  | 868.74 | 100% |  | 393948.82 | 404447.62 | -10498.8 | 2012-02-02 | 2013-03-31 | 2012-02-01 | 2012-12-12
75084-DE Kentucky Power Deliv - Ele | RELDFA | G6791 | EMAX 2880825 Turkeyfoot Rd Dist | 2585.02 |  | 2585.02 | 100% |  | 9415.31 | 55503.22 | -46087.91 | 2012-02-16 | 2013-06-30 | 2012-03-01 | 2012-09-07
75084-DE Kentucky Power Deliv - Ele | RELDFA | G8369 | RI emax 2836864 Madison Ave | 96415.77 |  | 96415.77 | 100% |  | 125883.63 | 68931.29 | 56952.34 | 2012-08-30 | 2015-05-07 | 2012-09-01 | 2015-03-12
75084-DE Kentucky Power Deliv - Ele | RELDFA | G9056 | RI emax 2760735 Camp Ernst (KY 237) | 0 |  | 0 |  |  | 537669.43 | 530030.09 | 7639.34 | 2012-12-06 | 2013-09-07 | 2012-12-01 | 2013-06-02
75084-DE Kentucky Power Deliv - Ele | RELDFA | G9119 | RI emax 3707725 5th to 8th | 27038.65 |  | 27038.65 | 100% |  | 93035.63 | 66480.15 | 26555.48 | 2012-12-19 | 2014-10-09 | 2012-12-01 | 2014-09-04
75084-DE Kentucky Power Deliv - Ele | RELDFA | H0282 | Prospect St-Robbins St-Jacob Price | -88779.24 |  | -88779.24 | 100% |  | 14514.78 | 53475.13 | -38960.35 | 2013-06-17 | 2014-01-01 | 2013-06-01 | 2014-01-16
75084-DE Kentucky Power Deliv - Ele | RELDFA | H0669 | RI emax 4264899 95 Carothers Rd | 1150.38 |  | 1150.38 | 100% |  | 77791.3 | 53991.27 | 23800.03 | 2013-08-30 | 2014-08-31 | 2013-09-01 | 2014-06-25
75084-DE Kentucky Power Deliv - Ele | RELDFA | M2116 | DOT 5395279 Taylor Mill Rd @ Walnut | 154995.31 |  | 154995.31 | 100% |  | 154995.31 | 119791.13 | 35204.18 | 2014-06-03 | 2015-05-02 | 2014-06-01 | 2015-02-20
75084-DE Kentucky Power Deliv - Ele | RELDFA | P0104 | RI 6000526 Newport High School | 3197.16 |  | 3197.16 | 100% |  | 3197.16 | 55761.4 | -52564.24 | 2014-08-04 | 2016-11-15 | 2014-09-01 | 2016-08-22
75084-DE Kentucky Power Deliv - Ele | RELDFA | P6165 | RI 4183102 Lowell St (Rt. 9) | 21875.39 |  | 21875.39 | 100% |  | 21875.39 | 190657.24 | -168781.85 | 2014-08-22 | 2016-03-14 | 2014-10-01 | 2015-07-27
75084-DE Kentucky Power Deliv - Ele | RELDFA | RELDKY | Relocation-D | 16942.34 |  | 16942.34 | 100% |  | 656844.66 | 200 | 656644.66 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RELTFA | G4535 | EMAX 2523185 Barnes Pike | -46829.12 |  | -46829.12 | 100% |  | 59.52 | 58402.19 | -58342.67 | 2011-08-18 | 2012-12-31 | 2011-09-01 | 2012-04-12
75084-DE Kentucky Power Deliv - Ele | RELTFA | G6487 | EMAX 2876458 RI-Turkeyfoot Rd | -9256.25 |  | -9256.25 | 100% |  | 108634.47 | 83949.57 | 24684.9 | 2012-01-16 | 2013-03-31 | 2012-01-01 | 2012-09-07
75084-DE Kentucky Power Deliv - Ele | RELTFA | RELTKY | Relocation-T | 13238.19 |  | 13238.19 | 100% |  | 311641.15 | 100 | 311541.15 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RLFA | AT12KY | AT12 & Micro ATO Replace KY | -13747.85 |  | -13747.85 | 100% |  | 0 | 31339 | -31339 | 2010-12-22 | 2050-12-31 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | RLFA | FMSWGRR | Florence Mall Sw-gear Repl Program | -77173.5 |  | -77173.5 | 100% |  | 0 | 65000 | -65000 | 2013-01-29 | 2015-12-31 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | RLFA | G1416 | ROLLUP PLH IK_KY_2009 | 0 |  | 0 |  |  | 1508495.94 | 200 | 1508295.94 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1419 | ROLLUP PLH IK_KY_2007 | 0 |  | 0 |  |  | 6127147.35 | 200 | 6126947.35 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2008-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1420 | ROLLUP PLH IK_KY_2006 | 0 |  | 0 |  |  | 7382097.31 | 200 | 7381897.31 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2007-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1421 | ROLLUP PLH IK_KY_2005 | 0 |  | 0 |  |  | 3720153.83 | 200 | 3719953.83 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2006-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1422 | ROLLUP PLH IK_KY_2004 | 0 |  | 0 |  |  | 2349020.4 | 200 | 2348820.4 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2005-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1729 | ROLLUP PLH IK_KY_2010_BLKT_Rollup | 0 |  | 0 |  |  | 7488699.49 | 200 | 7488499.49 | 2010-12-22 | 2050-12-31 | 2010-12-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G9018 | NW emax 3205166 18th & Banklick | -518.01 |  | -518.01 | 100% |  | 42809.67 | 32465.77 | 10343.9 | 2012-12-03 | 2014-03-31 | 2012-12-01 | 2013-06-24
75084-DE Kentucky Power Deliv - Ele | RLFA | LPFUKY | Line Patrol Insp followup KY | 0 |  | 0 |  |  | 5.6843e-13 | 400000 | -400000 | 2010-12-22 | 2015-12-31 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | RLFA | LPSMEIKY | Dline Patrol SMEI Capital Followup | -509.56 |  | -509.56 | 100% |  | 5.1159e-13 | 75000 | -75000 | 2012-04-30 | 2050-12-31 | 2013-02-01
75084-DE Kentucky Power Deliv - Ele | RLFA | MALTKY | Malten Switchgear Replacement KY | -51897.57 |  | -51897.57 | 100% |  | 0 | 100000 | -100000 | 2012-01-13 | 2015-12-31 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | RLFA | OHPCIKY | Mandated KY Overhead Prim Clearanc | 983 |  | 983 | 100% |  | -7.276e-12 | 381049 | -381049 | 2010-12-22 | 2050-12-31 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | RLFA | RLKY | Reliability Other-FO-D | -88322.05 |  | -88322.05 | 100% |  | 713433.68 | 200 | 713233.68 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RLFA | RNOVAKY | Cooper Nova Replacement | -107535.64 |  | -107535.64 | 100% |  | 0 | 60000 | -60000 | 2012-11-02 | 2050-12-31 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | RRBLKKENT | RRCRITTEN | Critenden Substation Blanket | 0 |  | 0 |  |  | 571.41 | 50000 | -49428.59 | 2013-09-09 | 2050-12-15 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | SCFOFA | E3836 | System Capacity-FO | 0 |  | 0 |  |  | 0 | 75723 | -75723 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | SCFOFA | SCFOKY | System Capacity-FO | 0 |  | 0 |  |  | 148499.05 | 100 | 148399.05 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | 50335.37 |  | 50335.37 | 100% |  | 50335.37 | 250000 | -199664.63 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | SGAMIDMS | SGADMS33 | SG Upgrade Alstom DMS to ver 3.3 | 9.66 |  | 9.66 | 100% |  | 9.66 | 68579 | -68569.34 | 2014-12-18 | 2016-07-20 | 2014-12-01 | 2016-07-15
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGCAPRIKY | SG Kentucky Capacitors for R&I | 171142.23 |  | 171142.23 | 100% |  | 172051.27 | 230000 | -57948.73 | 2013-11-01 | 2015-03-30 | 2013-12-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGCSRIKY | Circuit Sectionalization - KY | -519347.12 |  | -519347.12 | 100% |  | 0 | 100 | -100 | 2013-05-24 | 2015-06-30 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGKTLPLC | SG DEK Trans Pole Replacement | 719.59 |  | 719.59 | 100% |  | 719.59 | 25000 | -24280.41 | 2014-09-12 | 2015-06-30 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGLSRIKY | SG KY Line Sensor Project for R&I | 248556.74 |  | 248556.74 | 100% |  | 249829.39 | 314000 | -64170.61 | 2013-11-01 | 2015-03-30 | 2013-12-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGMGTRIKY | SG KY Sectionalization R&I Mgmt Prj | 37036.67 |  | 37036.67 | 100% |  | 38986.88 | 25000 | 13986.88 | 2013-11-01 | 2015-03-30 | 2013-12-01 | 2015-03-15
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGRCRIKY | SG DEK Reserve Capacity Meters | 85222.06 |  | 85222.06 | 100% |  | 85222.06 | 115000 | -29777.94 | 2014-05-12 | 2015-03-30 | 2014-06-01 | 2015-04-30
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT36 | SG DEK Self Healing Team 36 Capital | 89408.9 |  | 89408.9 | 100% |  | 89408.9 | 206458.63 | -117049.73 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2014-12-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT37 | SG DEK Self Healing Team 37 Capital | 44264.25 |  | 44264.25 | 100% |  | 44264.25 | 71071.44 | -26807.19 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2015-01-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT38 | SG DEK Self Healing Team 38 Capital | 129078.22 |  | 129078.22 | 100% |  | 129078.22 | 122442.2 | 6636.02 | 2014-04-21 | 2015-07-31 | 2014-05-01 | 2015-04-30
75084-DE Kentucky Power Deliv - Ele | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | -379.9 |  | -379.9 | 100% |  | 61898.59 | 62278.49 | -379.9 | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGAMIDOM | SG AMI to DOMS Outage Capital | 0 |  | 0 |  |  | 39944.15 | 39944.15 | 0 | 2011-05-26 | 2011-12-16 | 2011-06-01 | 2012-03-13
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGBRWTRH | Bridgewater AAA Implement HW | 0 |  | 0 |  |  | 1860.57 | 2100 | -239.43 | 2011-12-08 | 2009-02-19 | 2011-12-01 | 2009-05-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGBRWTRS | Bridgewater AAA Implement SW | 0 |  | 0 |  |  | 4391.55 | 4800 | -408.45 | 2011-12-01 | 2009-02-19 | 2011-12-01 | 2009-05-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGCAMIHW | Smart Grid Carolinas AMI Hardware | 0 |  | 0 |  |  | 27968.85 | 15255 | 12713.85 | 2012-08-10 | 2012-12-31 | 2012-08-01 | 2013-03-20
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | -60.5 |  | -60.5 | 100% |  | 132348 | 130000 | 2348 | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGITRNSLH | ITRON SG Solutions Hardware | 0 |  | 0 |  |  | 3779.19 | 6000 | -2220.81 | 2011-07-14 | 2012-06-30 | 2011-10-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMFDHW | SG MDM Foundation Hardware | 0 |  | 0 |  |  | 73191.26 | 514545.92 | -441354.66 | 2012-04-20 | 2013-10-31 | 2012-05-01 | 2013-10-29
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMFDSW | SG MDM Foundation Custom SW | -8659.29 |  | -8659.29 | 100% |  | 509256.19 | 440000 | 69256.19 | 2012-04-20 | 2013-10-31 | 2012-04-01 | 2013-10-29
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMM2C | SG MDM Mass Market 2 - CMS Work | 3.61 |  | 3.61 | 100% |  | 3.61 | 31372 | -31368.39 | 2014-11-03 | 2015-02-16 | 2014-11-01 | 2015-02-17
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 40387.93 |  | 40387.93 | 100% |  | 40387.93 | 392765 | -352377.07 | 2014-04-28 | 2015-02-16 | 2014-04-01 | 2015-02-17
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMMH | SG MDM Mass Market Hardware | -696.26 |  | -696.26 | 100% |  | 10834.61 | 77000 | -66165.39 | 2013-07-10 | 2014-09-30 | 2013-12-01 | 2014-08-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 72570.47 |  | 72570.47 | 100% |  | 183577.67 | 33000 | 150577.67 | 2013-07-10 | 2014-09-30 | 2013-07-01 | 2014-08-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMS | Meter Data Management System | 0 |  | 0 |  |  | 197462 | 252000 | -54538 | 2011-11-30 | 2010-06-18 | 2011-11-01 | 2010-09-18
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 7735.97 |  | 7735.97 | 100% |  | 71270.12 | 33000 | 38270.12 | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG36 | NES 3.0 Upgrade SGS.036 | 0 |  | 0 |  |  | 3818.02 | 4238 | -419.98 | 2011-12-02 | 2009-03-18 | 2011-12-01 | 2009-06-18
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG38 | NES EM System SGS.038 | 0 |  | 0 |  |  | 5685.2 | 5424 | 261.2 | 2011-12-06 | 2009-10-20 | 2011-12-01 | 2010-01-20
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG45H | NES Test Envir SGS.045 HW | 0 |  | 0 |  |  | 3493.06 | 4916 | -1422.94 | 2011-12-06 | 2009-10-22 | 2011-12-01 | 2010-01-22
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG45S | NES Test Envir SGS.045 SW | 0 |  | 0 |  |  | 7913.38 | 6441 | 1472.38 | 2011-12-08 | 2009-10-22 | 2011-12-01 | 2010-01-22
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG51 | NES 4.1 Upgrade SGS.051 | 0 |  | 0 |  |  | 15797.81 | 6441 | 9356.81 | 2011-12-08 | 2010-12-10 | 2011-12-01 | 2011-03-10
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 0 |  | 0 |  |  | 7630.72 | 7630.72 | 0 | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | 0 |  | 0 |  |  | 57834.44 | 60000 | -2165.56 | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGROFEDM6 | Remote Order Fulfillment EDM.06 | 0 |  | 0 |  |  | 15632.51 | 12543 | 3089.51 | 2011-12-08 | 2009-03-19 | 2011-12-01 | 2009-06-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGSYED15 | SG EDM.15 EDMS Scalability-Hardware | 0 |  | 0 |  |  | 52213.53 | 73333 | -21119.47 | 2010-09-14 | 2010-09-30 | 2010-09-01 | 2011-02-24
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGSYEDP2 | SG Scalability Phase 2 EDM064 | 0 |  | 0 |  |  | 217795.82 | 800000 | -582204.18 | 2010-08-13 | 2011-09-30 | 2010-09-01 | 2011-08-13
75084-DE Kentucky Power Deliv - Ele | SGITOMSGI | SGARCSRVC | Smart Grid ARC Server Project | 0 |  | 0 |  |  | 24134.87 | 35517 | -11382.13 | 2010-09-24 | 2010-11-30 | 2010-10-01 | 2011-03-08
75084-DE Kentucky Power Deliv - Ele | SGITOMSGI | SGSWDOMC | SG AMI DOMS S/W Module Capital | 9635.79 |  | 9635.79 | 100% |  | 24600.05 | 37300 | -12699.95 | 2012-12-20 | 2015-08-29 | 2013-01-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1313 | Beaver Sub SG DA | 394135.52 |  | 394135.52 | 100% |  | 395070.97 | 236862 | 158208.97 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1314 | Florence Sub SG DA | 328697.91 |  | 328697.91 | 100% |  | 330451.7 | 299642 | 30809.7 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-01-14
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1315 | Limaburg Sub SG DA | 566325.97 |  | 566325.97 | 100% |  | 567067.89 | 446848 | 120219.89 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | SGKYCS | SGCSDCI3 | ECS daily usage cap | 0 |  | 0 |  |  | 12362.77 | 15000 | -2637.23 | 2010-10-01 | 2014-12-31 | 2010-09-01 | 2010-06-24
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDADMS | Dist Mgt Sys cap | 41531.19 |  | 41531.19 | 100% |  | 1489603.44 | 1511877.7 | -22274.26 | 2010-10-01 | 2014-07-30 | 2010-09-01 | 2014-05-19
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDEETHW | SG DMS Distribution DEETS HW | -168.71 |  | -168.71 | 100% |  | 7954.17 | 2373 | 5581.17 | 2011-09-30 | 2014-10-31 | 2011-11-01 | 2013-07-29
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDEETSW | SG DMS Distribution DEETS SW | -848.62 |  | -848.62 | 100% |  | 18945.76 | 23915.77 | -4970.01 | 2011-09-30 | 2014-10-31 | 2011-10-01 | 2013-07-29
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGMWSCADH | Smart Grid Midwest SCADA Hardware | 0 |  | 0 |  |  | 14317.22 | 17715 | -3397.78 | 2011-06-29 | 2011-12-31 | 2011-10-01 | 2011-08-31
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGMWSCADS | Smart Grid Midwest SCADA Software | 0 |  | 0 |  |  | 133886.34 | 168748 | -34861.66 | 2011-06-29 | 2011-12-31 | 2011-10-01 | 2011-08-31
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGECHLDA | SG Echelon Local Data Access | 0 |  | 0 |  |  | 8364.35 | 9765 | -1400.65 | 2010-09-30 | 2014-12-31 | 2010-09-01 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGNDENSW | Echelon NET SW Cap | 0 |  | 0 |  |  | 31031.1 | 20000 | 11031.1 | 2010-09-30 | 2014-12-31 | 2010-09-01 | 2011-03-10
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGSTRGC | Smart Grid Storage Project | 0 |  | 0 |  |  | 128657.15 | 169806 | -41148.85 | 2010-06-16 | 2010-11-30 | 2010-09-01 | 2011-02-17
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGSYED11 | EDM.11 SG Scaling/Tech Hlth | 0 |  | 0 |  |  | 111333.51 | 465000 | -353666.49 | 2010-09-30 | 2010-03-04 | 2010-09-01 | 2010-06-04
75084-DE Kentucky Power Deliv - Ele | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | 4865.97 |  | 4865.97 | 100% |  | 950.35 | 1 | 949.35 | 2010-09-30 | 2017-12-31 | 2010-09-01
75084-DE Kentucky Power Deliv - Ele | SGNMS | SGKIPV6ML | SG DEK ITRON Software NMS Endpoints | 585678.5 |  | 585678.5 | 100% |  | 585678.5 | 585000 | 678.5 | 2014-06-27 | 2015-01-31 | 2014-08-01 | 2014-12-31
75084-DE Kentucky Power Deliv - Ele | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 4751.66 |  | 4751.66 | 100% |  | 4751.66 | 170000 | -165248.34 | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75084-DE Kentucky Power Deliv - Ele | SGNNT1021 | SGNT1021B | SG NINT1021B - SERVERS | 220.7 |  | 220.7 | 100% |  | 220.7 | 170000 | -169779.3 | 2014-04-30 | 2014-11-30 | 2014-08-01 | 2015-02-01
75084-DE Kentucky Power Deliv - Ele | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 8081.02 |  | 8081.02 | 100% |  | 8081.02 | 43500 | -35418.98 | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI01 | SG Secure Network Infrastructure | 1658.65 |  | 1658.65 | 100% |  | 1658.65 | 50075 | -48416.35 | 2014-12-12 | 2016-08-30 | 2014-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI02 | SG Secure Network Infrastructure | 1608.72 |  | 1608.72 | 100% |  | 1608.72 | 50075 | -48466.28 | 2014-12-12 | 2016-06-30 | 2014-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SLFA | SLKY | Light Repl-Tarriff | 0 |  | 0 |  |  | 144198.34 | 299 | 143899.34 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | SUBCHAIRS | G9909 | Substation Chair Replacement | 0 |  | 0 |  |  | 1587.47 | 2040 | -452.53 | 2013-04-09 | 2013-04-22 | 2013-06-01 | 2013-10-01
75084-DE Kentucky Power Deliv - Ele | TDIT | E0857 | EMS OML Kentucky | 0 |  | 0 |  |  | 9123.03 | 8600 | 523.03 | 2008-09-03 | 2009-12-31 | 2008-12-01 | 2010-03-14
75084-DE Kentucky Power Deliv - Ele | TDIT | E2272 | EMS MH Standby Enhancement - Ky | 0 |  | 0 |  |  | 4289.25 | 4025 | 264.25 | 2008-11-12 | 2010-12-31 | 2008-12-01 | 2011-02-28
75084-DE Kentucky Power Deliv - Ele | TDIT | E5392 | EMS SQL Cluster Infrastruc - KY | 0 |  | 0 |  |  | 9055.89 | 5516 | 3539.89 | 2009-04-07 | 2009-11-30 | 2009-04-01 | 2010-03-28
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA | E1551 | Wilder - Replace Battery | 0 |  | 0 |  |  | 11727.24 | 9480 | 2247.24 | 2008-10-08 | 2050-07-10 | 2009-05-01 | 2009-08-23
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | P6216 | Wilder Repl TB1 Cooling Fans | 16403.43 |  | 16403.43 | 100% |  | 16403.43 | 16025.64 | 377.79 | 2014-08-28 | 2015-03-31 | 2014-09-01 | 2015-01-06
75084-DE Kentucky Power Deliv - Ele | TOALOGK | D2063 | Install Sun-Net TOA Kentucky | 0 |  | 0 |  |  | 38944.7 | 1 | 38943.7 | 2007-11-14 | 2010-11-30 | 2008-03-01 | 2010-10-01
75084-DE Kentucky Power Deliv - Ele | TOOL002 | D3702 | TIRE CHANGER | 0 |  | 0 |  |  | 6207.56 | 6200 | 7.56 | 2008-06-19 | 2050-12-31 | 2008-07-01 | 2008-12-15
75084-DE Kentucky Power Deliv - Ele | TOOLFA | TOOLKY | Tools & Equip | 37846.46 |  | 37846.46 | 100% |  | 830495.76 | 101 | 830394.76 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G4599 | Wilder Repl 138kV CB No. 834 | 0 |  | 0 |  |  | 82257.49 | 12073 | 70184.49 | 2011-08-23 | 2011-12-16 | 2011-09-01 | 2011-11-26
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G7235 | Wilder repl CCVT & line tuner | 0 |  | 0 |  |  | 20303.82 | 14237.74 | 6066.08 | 2012-04-13 | 2013-01-31 | 2012-04-01 | 2013-01-18
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G7406 | Silver Grove install ETM on TB 23 | 0 |  | 0 |  |  | 18593.04 | 7314.39 | 11278.65 | 2012-05-04 | 2012-11-30 | 2012-05-01 | 2012-10-13
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G8576 | Wilder rem fence & instl animal fen | -109918.51 |  | -109918.51 | 100% |  | 351875.96 | 300599.26 | 51276.7 | 2012-10-03 | 2013-03-07 | 2012-10-01 | 2013-03-21
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9064 | Wilder CB650 repl 2 bus disconnects | 1434 |  | 1434 | 100% |  | 24646.68 | 32086.93 | -7440.25 | 2012-12-10 | 2013-12-30 | 2013-10-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9117 | Wilder repl pos 1&5 bushings CB831 | 0 |  | 0 |  |  | 12011.82 | 8924.05 | 3087.77 | 2012-12-19 | 2013-06-29 | 2013-03-01 | 2013-06-18
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9139 | Florence repl sw,motor,whip ABS859 | 217.96 |  | 217.96 | 100% |  | 45937.86 | 45872.32 | 65.54 | 2012-12-26 | 2013-12-27 | 2013-02-01 | 2014-03-13
75084-DE Kentucky Power Deliv - Ele | TRLERULH | D3446 | FORKLIFT | 0 |  | 0 |  |  | 34681.99 | 31800 | 2881.99 | 2008-05-05 | 2050-12-31 | 2008-06-01 | 2008-10-28
75084-DE Kentucky Power Deliv - Ele | TRLERULH | E0933 | Erlanger ATV | 0 |  | 0 |  |  | 11770 | 12177 | -407 | 2008-09-09 | 2008-11-30 | 2008-10-01 | 2008-12-31
75084-DE Kentucky Power Deliv - Ele | U02Z7993 | C9471 | KY UNIV rep ABS 962 | 0 |  | 0 |  |  | 17071.23 | 20123 | -3051.77 | 2007-03-20 | 2050-12-31 | 2007-03-01 | 2007-03-21
75084-DE Kentucky Power Deliv - Ele | U03Z7357 | D1581 | Cold Spring TB9 failure | 0 |  | 0 |  |  | 30159.65 | 13915 | 16244.65 | 2007-09-12 | 2050-12-31 | 2007-09-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | U04ZGM | D1507 | ri-dolwick rd ginny meyer | 0 |  | 0 |  |  | 52045 | 52045 | 0 | 2007-08-30 | 2050-12-31 | 2009-11-01 | 2003-08-22
75084-DE Kentucky Power Deliv - Ele | U04ZTREE | ZV070 | DANGER TREE - TRANS - ULHP | 0 |  | 0 |  |  | 4273.99 | 1 | 4272.99 | 2007-04-26 | 2050-12-31 | 2007-04-01 | 2008-03-31
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C8961 | pp 870018/joe groeschen | 0 |  | 0 |  |  | -449.2 | 0 | -449.2 | 2007-01-03 | 2050-12-31 | 2007-02-01 | 2007-02-01
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C9034 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -208.67 | 75231 | -75439.67 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C9887 | CHELSEA S/O VILLA MADONNA-F966 | 0 |  | 0 |  |  | 645.24 | 53416 | -52770.76 | 2007-05-30 | 2012-05-01 | 2007-06-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9015 | ULH&P 2005 Government Mandate | 0 |  | 0 |  |  | -42185.33 | 42069 | -84254.33 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9564 | RI-NO BEND RD FRM I-275 NORTH | 0 |  | 0 |  |  | 11782.24 | 38177 | -26394.76 | 2007-04-10 | 2015-04-01 | 2007-04-01 | 2007-11-12
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9664 | RI-ST ELZBTH ACCESS RELO DIST | 0 |  | 0 |  |  | 23075.94 | 15263 | 7812.94 | 2007-04-27 | 2012-04-01 | 2007-05-01 | 2008-01-02
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D1727 | RI-12TH ST RECONST -I-75/SCOTT | 0 |  | 0 |  |  | 120906.9 | 60754 | 60152.9 | 2007-10-03 | 2012-10-01 | 2009-02-01 | 2009-12-15
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D1970 | RI SR 16-I-275 TO SUBRITE DR | 0 |  | 0 |  |  | 353455.74 | 516774.62 | -163318.88 | 2007-11-01 | 2012-10-01 | 2007-11-01 | 2012-03-29
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D2085 | RI-HAZELWOOD DR S/O BUTTERMILK | 0 |  | 0 |  |  | 41739.15 | 41768 | -28.85 | 2007-11-16 | 2012-11-01 | 2007-11-01 | 2008-01-13
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D3355 | RI-GRAND AVE S/O MEMORIAL PKWY | 0 |  | 0 |  |  | -5.0932e-11 | 0 | -5.0932e-11 | 2008-04-24 | 2013-04-01 | 2008-06-01 | 2010-04-07
75084-DE Kentucky Power Deliv - Ele | U14ZKV | C9013 | ULH&P 2005 Capacitors | 0 |  | 0 |  |  | -162705.78 | 162253 | -324958.78 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U14ZKVCH | ZC071 | ULHP DistLine Capacitor Switch | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-02-14 | 2050-12-31 | 2008-03-01
75084-DE Kentucky Power Deliv - Ele | U14ZTREE | ZV071 | DANGER TREE - DIST - ULHP | 0 |  | 0 |  |  | 0 | 1 | -1 | 2007-04-26 | 2050-12-31 | 2007-06-01
75084-DE Kentucky Power Deliv - Ele | U16Z7994 | D1697 | Wilder dispose mulsifyer house | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-10-02 | 2008-04-07 | 2010-08-01 | 2007-10-29
75084-DE Kentucky Power Deliv - Ele | U16Z7994 | D1754 | Kenton replace roof | 0 |  | 0 |  |  | 14429.12 | 18456 | -4026.88 | 2007-10-05 | 2050-12-31 | 2007-11-01 | 2007-12-15
75084-DE Kentucky Power Deliv - Ele | UGCIFA | CABINJKY | Underground Cable Injection - KY | 0 |  | 0 |  |  | 0 | 232000 | -232000 | 2011-03-15 | 2015-12-31 | 2011-04-01
75084-DE Kentucky Power Deliv - Ele | UGCIFA | RCABINJKY | Reactive Cable Replacement Kentucky | -16197.19 |  | -16197.19 | 100% |  | 0 | 250000 | -250000 | 2012-11-16 | 2050-12-31 | 2013-03-01
75084-DE Kentucky Power Deliv - Ele | UGCRFA | E6865 | PP#1068539 DERBY RIDGE APTS RECOND | 0 |  | 0 |  |  | 0 | 72432 | -72432 | 2009-06-04 | 2009-12-31 | 2009-07-01 | 2009-12-17
75084-DE Kentucky Power Deliv - Ele | UGCRFA | E6908 | PP#1068609 COUNTRY SQUIRE ESTATES | 0 |  | 0 |  |  | 0 | 83042 | -83042 | 2009-06-05 | 2010-06-01 | 2009-07-01 | 2010-02-19
75084-DE Kentucky Power Deliv - Ele | UGCRFA | F0709 | PP#1088919 URD 104 | 0 |  | 0 |  |  | 148789.21 | 163914.64 | -15125.43 | 2009-09-25 | 2010-12-31 | 2009-12-01 | 2010-10-07
75084-DE Kentucky Power Deliv - Ele | UGCRFA | F5109 | eMax#395612 AMSTERDAM VILLAGE | 80591.13 |  | 80591.13 | 100% |  | 113614.48 | 124734.81 | -11120.33 | 2010-02-09 | 2010-12-31 | 2010-03-01 | 2010-10-28
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G1661 | EMAX 1786573 URD 184 Richwood | 0 |  | 0 |  |  | 415673.18 | 585415.78 | -169742.6 | 2010-12-15 | 2013-03-31 | 2010-12-01 | 2011-07-29
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G3647 | EMAX 2346184 URD 105 Country Squire | 0 |  | 0 |  |  | 99612.1 | 119746.44 | -20134.34 | 2011-06-10 | 2013-03-31 | 2011-06-01 | 2012-04-19
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G9111 | CR emax 3705007 Heritage Trails | 1714.92 |  | 1714.92 | 100% |  | 106816.26 | 85982.93 | 20833.33 | 2012-12-18 | 2015-06-30 | 2013-04-01 | 2014-01-31
75084-DE Kentucky Power Deliv - Ele | UGCRFA | H1679 | UG 4765860 URD 36 Brookwood | 154132.69 |  | 154132.69 | 100% |  | 154132.69 | 142644.34 | 11488.35 | 2014-01-15 | 2015-02-28 | 2014-01-01 | 2014-08-28
75084-DE Kentucky Power Deliv - Ele | UGCRFA | N8112 | UG 5759052 URD 52 Woodside Dr | 193141.33 |  | 193141.33 | 100% |  | 193141.33 | 158779.8 | 34361.53 | 2014-06-30 | 2015-06-30 | 2014-08-01 | 2015-03-02
75084-DE Kentucky Power Deliv - Ele | UGCRFA | UGCRKY | UG Cable Repl | 0 |  | 0 |  |  | 337806.2 | 100 | 337706.2 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | VMDDTFA | VMCMCKY | R/W CKT MAINT CAP KENTUCKY | 336627.25 |  | 336627.25 | 100% |  | 1327948.41 | 1 | 1327947.41 | 2012-01-25 | 2050-12-31 | 2012-02-01
75084-DE Kentucky Power Deliv - Ele | VMDDTFA | VMDDTKY | Distr Line Clr Removal | 190806.14 |  | 190806.14 | 100% |  | 1183065.34 | 1 | 1183064.34 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | VMTDFA | VMTDKY | Trans Line Clr Removal | 39389.89 |  | 39389.89 | 100% |  | 135253.65 | 1 | 135252.65 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | X02U8310 | F4206 | Buffington - Replace CB 682 | 0 |  | 0 |  |  | 273166.29 | 170830 | 102336.29 | 2010-01-19 | 2012-03-31 | 2011-01-01 | 2012-02-11
75084-DE Kentucky Power Deliv - Ele | X02U8885 | G3793 | Wilder Replace CB 650 | 0 |  | 0 |  |  | 199403.84 | 147094 | 52309.84 | 2011-06-24 | 2013-03-31 | 2011-11-01 | 2013-03-18
75084-DE Kentucky Power Deliv - Ele | X03U8875 | G7392 | Donaldson TB1 TB2 Transrupters | 132768.42 |  | 132768.42 | 100% |  | 252759.6 | 248446 | 4313.6 | 2012-05-02 | 2015-03-31 | 2012-05-01 | 2014-09-14
75084-DE Kentucky Power Deliv - Ele | X03U9003 | G7393 | Florence TB1 TB2 TB4 | 307424.11 |  | 307424.11 | 100% |  | 599670.92 | 320573 | 279097.92 | 2012-05-02 | 2015-03-31 | 2012-05-01 | 2015-01-14
75085-DE Kentucky Cus Service - Ele | AMIKY | C8779 | AMI Mt Zion Advanced Meter | 0 |  | 0 |  |  | 79580.84 | 101605 | -22024.16 | 2007-01-04 | 2007-12-31 | 2007-01-01 | 2007-12-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9041 | AMI Hands Advanced Meter | 0 |  | 0 |  |  | 202616.61 | 153106 | 49510.61 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9042 | AMI Empire Advanced Meter | 0 |  | 0 |  |  | 117897.99 | 137706 | -19808.01 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9043 | AMI Kenton Advanced Meter | 0 |  | 0 |  |  | 179935.34 | 197559 | -17623.66 | 2007-01-07 | 2007-12-31 | 2007-01-01 | 2007-12-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9044 | AMI Wilder Advanced Meter | 0 |  | 0 |  |  | 41017.98 | 200835 | -159817.02 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9045 | AMI Donaldson Advanced Meter | 0 |  | 0 |  |  | 59674.83 | 151468 | -91793.17 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9046 | AMI Oakbrook Advanced Meter | 0 |  | 0 |  |  | 62106.41 | 94724 | -32617.59 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9047 | AMI Atlas Advanced Meter | 0 |  | 0 |  |  | 11249.91 | 93304 | -82054.09 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9048 | AMI Claryville Advanced Meter | 0 |  | 0 |  |  | 35936.31 | 158349 | -122412.69 | 2007-01-07 | 2009-08-31 | 2007-07-01 | 2009-08-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9049 | AMI Florence Advanced Meter | 0 |  | 0 |  |  | 81306.22 | 189695 | -108388.78 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9050 | AMI Villa Advanced Meter | 0 |  | 0 |  |  | 59478.75 | 150703 | -91224.25 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9051 | AMI Dixie Advanced Meter | 0 |  | 0 |  |  | 50283.84 | 154744 | -104460.16 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2008-01-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9052 | AMI Buffington Advanced Meter | 0 |  | 0 |  |  | 76372.45 | 191879 | -115506.55 | 2007-01-07 | 2008-03-15 | 2007-02-01 | 2008-06-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9449 | AMI Dry Ridge Advanced Meter | 0 |  | 0 |  |  | 56532.74 | 95052 | -38519.26 | 2007-03-16 | 2007-10-15 | 2007-04-01 | 2007-10-15
75085-DE Kentucky Cus Service - Ele | AMIKY | D1128 | AMI Thomas More Advanced Mete | 0 |  | 0 |  |  | 10657.81 | 1 | 10656.81 | 2007-07-04 | 2008-06-15 | 2007-07-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | D1144 | AMI West End Advanced Meter | 0 |  | 0 |  |  | 50286.69 | 50000 | 286.69 | 2007-07-06 | 2011-03-31 | 2007-07-01 | 2009-01-01
75085-DE Kentucky Cus Service - Ele | AMIKYCS | ZY072 | AMI GAS & ELECTRIC METERS | 0 |  | 0 |  |  | 601512.93 | 1 | 601511.93 | 2007-02-05 | 2050-12-31 | 2007-07-01 | 2008-07-01
75085-DE Kentucky Cus Service - Ele | EMSBLADE | C9288 | Midwest EMS Blade Server Infra | 0 |  | 0 |  |  | 16913.75 | 18468 | -1554.25 | 2007-02-14 | 2007-12-31 | 2007-02-01 | 2008-03-31
75085-DE Kentucky Cus Service - Ele | FEBPE1A | EBPE1 | Electronic Billing & Payment Ex Ph1 | 0 |  | 0 |  |  | 61896.29 | 72600 | -10703.71 | 2011-05-20 | 2011-12-31 | 2011-06-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FEBPE1A | EBPE2 | EBPE Phase 2 | 0 |  | 0 |  |  | 46724.42 | 47000 | -275.58 | 2012-02-20 | 2012-12-31 | 2012-02-01 | 2012-12-17
75085-DE Kentucky Cus Service - Ele | FPIT | MFEOLREPL | Mainframe EOL Repl | 0 |  | 0 |  |  | 51555.84 | 53881.98 | -2326.14 | 2012-05-31 | 2012-09-30 | 2012-06-01 | 2012-12-19
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1024C | NINT1024 Knowledge Management Tool | 17941.99 |  | 17941.99 | 100% |  | 17941.99 | 12541.38 | 5400.61 | 2014-01-13 | 2014-12-30 | 2014-02-01 | 2014-11-23
75085-DE Kentucky Cus Service - Ele | FPIT | NINT979C | NINT979C Combined Mobile SMS TXT | 29439.35 |  | 29439.35 | 100% |  | 29439.35 | 22322.04 | 7117.31 | 2014-10-01 | 2014-12-31 | 2014-10-01 | 2015-05-20
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA1049C | INT1049 BRNR | 21987.18 |  | 21987.18 | 100% |  | 21987.18 | 47222.49 | -25235.31 | 2014-10-23 | 2015-07-31 | 2014-11-01 | 2015-10-17
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175AC | Customer Contact Preference Center | 12556.36 |  | 12556.36 | 100% |  | 41139.94 | 34008 | 7131.94 | 2013-08-01 | 2014-10-14 | 2013-08-01 | 2014-10-14
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175BS | PCTA175BS CDS | 291.14 |  | 291.14 | 100% |  | 291.14 | 78939.89 | -78648.75 | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA210C | Contact Channels Datamart & Dashboa | 5446.33 |  | 5446.33 | 100% |  | 8641.02 | 7351.4 | 1289.62 | 2013-10-22 | 2014-09-23 | 2013-11-01 | 2014-09-23
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AC | CA Lisa | 11679.57 |  | 11679.57 | 100% |  | 11679.57 | 9387.72 | 2291.85 | 2014-10-21 | 2015-11-30 | 2014-11-01 | 2015-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AH | INT481A CDP Hardware Implementation | 9162.15 |  | 9162.15 | 100% |  | 9162.15 | 14924.07 | -5761.92 | 2014-10-23 | 2015-11-30 | 2014-11-01 | 2015-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AS | Sitecore | 213904.42 |  | 213904.42 | 100% |  | 213904.42 | 520043.89 | -306139.47 | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75085-DE Kentucky Cus Service - Ele | FPIT | PCTAIT17X | Mobile Web Phase 1 | -72.87 |  | -72.87 | 100% |  | 6622.7 | 3580 | 3042.7 | 2013-01-20 | 2013-10-30 | 2013-03-01 | 2014-01-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTAIVRSW | IVR Software and Licenses | 10609.23 |  | 10609.23 | 100% |  | 83234.43 | 84000 | -765.57 | 2013-03-12 | 2014-07-31 | 2013-05-01 | 2014-08-15
75085-DE Kentucky Cus Service - Ele | FPIT | RCDPSSK | Dynamic Pricing Solution System | 0 |  | 0 |  |  | 83424.32 | 84000 | -575.68 | 2012-01-31 | 2013-03-31 | 2012-02-01 | 2013-01-28
75085-DE Kentucky Cus Service - Ele | FPIT | RCDRCETK | Daily Rating Charging Estimate Tool | 0 |  | 0 |  |  | 26202.58 | 27000 | -797.42 | 2012-01-31 | 2013-03-31 | 2012-02-01 | 2013-01-28
75085-DE Kentucky Cus Service - Ele | FPIT | RCIVRMKE | IVR Monitoring Systems | 0 |  | 0 |  |  | 3320.23 | 3450 | -129.77 | 2012-06-13 | 2012-12-31 | 2012-09-01 | 2013-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWHWC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 123830.93 | 124000 | -169.07 | 2011-07-22 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 232943.03 | 162502.14 | 70440.89 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWTELC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 10402.84 | 11000 | -597.16 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | RCPSPROJ | LRIEDM42 | Load Research Interfaces EDM042 | 0 |  | 0 |  |  | 28724.53 | 315500 | -286775.47 | 2011-05-24 | 2011-11-30 | 2011-06-01 | 2012-03-01
75085-DE Kentucky Cus Service - Ele | SGITCS | ECSDCI1 | Enterprise Cust syst DCI1 Capital | 0 |  | 0 |  |  | 31257.61 | 100000 | -68742.39 | 2011-02-24 | 2015-06-30 | 2011-03-01 | 2010-09-18
75085-DE Kentucky Cus Service - Ele | SGITCS | ECSDCI2 | Enterprise Cust system DCI2 Capital | 0 |  | 0 |  |  | 3473.74 | 100000 | -96526.26 | 2011-04-13 | 2015-03-15 | 2011-04-01 | 2011-11-30
|  |  |  | 47802612.36 | 43374482.6101 | 4428129.7499 | 10.21%

## 2015
Duke Energy Kentucky Electric
Year 2015
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75080-DE Kentucky Other - Elec | FMWAVEKY | 20218019A | 20218019th & Augustine Test Equip | 2983.01 |  | 2983.01 | 100% |  | 2983.01 | 49950 | -46966.99 | 2015-06-10 17:09 | 2015-12-30 | 2015-07-01 | 2016-03-30
75080-DE Kentucky Other - Elec | MWTELBLKT | ALEXCOOP | Alexandria Cooper Microwave Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-09-11 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | SITESVCS | BATGNKY09 | Install Backup Generators | 0 |  | 0 |  |  | 146836.04 | 146836 | 0.04 | 2009-06-03 | 2010-10-15 | 2009-11-01 | 2010-10-15
75080-DE Kentucky Other - Elec | MWTELBLKT | BUTLERBKT | Butler Tower Blanket | 0 |  | 0 |  |  | 270.59 | 50000 | -49729.41 | 2013-09-05 | 2025-12-31 | 2013-09-01
75080-DE Kentucky Other - Elec | TELBLKT | BVRLCKBKT | Beaverlick Tower Blanket | 5300.54 |  | 5300.54 | 100% |  | 7466.3 | 50000 | -42533.7 | 2011-10-18 | 2019-12-31 | 2011-12-01
75080-DE Kentucky Other - Elec | DCITEDM | C8768 | EDM Project | 0 |  | 0 |  |  | 742848.83 | 1 | 742847.83 | 2007-01-04 | 2009-05-31 | 2007-03-01 | 2009-07-19
75080-DE Kentucky Other - Elec | RADIOS07 | C9258 | RADIO REPLACEMENT PROGRAM 2007 | 0 |  | 0 |  |  | 1074336.23 | 1 | 1074335.23 | 2007-02-09 | 2008-12-31 | 2007-03-01 | 2008-12-31
75080-DE Kentucky Other - Elec | RADIO | CABLEKY13 | Install Pag Transmitter Cable & Ant | 0 |  | 0 |  |  | 14034.97 | 14034.97 | 0 | 2011-09-06 | 2013-12-31 | 2012-07-01 | 2014-04-09
75080-DE Kentucky Other - Elec | CIS123CP2 | CIS123LBM | BancTec Prod Bckp Svr_CIS 123 Pr Mg | 0 |  | 0 |  |  | 8895.78 | 7582 | 1313.78 | 2010-08-16 | 2011-04-29 | 2010-12-01 | 2011-08-06
75080-DE Kentucky Other - Elec | CIS123CAP | CIS123LBS | BancTec Software and Installation | 0 |  | 0 |  |  | 35115.81 | 25979 | 9136.81 | 2010-08-13 | 2011-04-29 | 2010-08-01 | 2011-08-06
75080-DE Kentucky Other - Elec | 75080 | CPRCRCT | CPR Corrections - Asset Acctg Only | 0 |  | 0 |  |  | 0 | 1 | -1 | 2012-08-28 | 2050-12-30 | 2012-10-01
75080-DE Kentucky Other - Elec | DCITCD2 | D1182 | Common Design Tools Phsase 2 | 0 |  | 0 |  |  | 6581.74 | 1 | 6580.74 | 2007-07-12 | 2011-03-31 | 2007-10-01 | 2011-03-17
75080-DE Kentucky Other - Elec | EPS100 | D1384 | ACS Migration Project | 0 |  | 0 |  |  | 14429.4 | 18253 | -3823.6 | 2007-08-12 | 2008-12-31 | 2007-09-01 | 2008-06-27
75080-DE Kentucky Other - Elec | 316ZBG | D1609 | Erlanger Oil separator install | 0 |  | 0 |  |  | 30771.18 | 40000 | -9228.82 | 2007-09-18 | 2008-06-25 | 2007-12-01 | 2008-03-25
75080-DE Kentucky Other - Elec | GASTRAN | D1838 | Implement Gas Transportation | 0 |  | 0 |  |  | 66251.43 | 1 | 66250.43 | 2007-10-14 | 2010-03-31 | 2007-11-01 | 2009-08-11
75080-DE Kentucky Other - Elec | MV90REPL | D2332 | MV90 meter reading replacement | 0 |  | 0 |  |  | 34915.31 | 1 | 34914.31 | 2007-12-12 | 2008-04-30 | 2007-12-01 | 2008-07-31
75080-DE Kentucky Other - Elec | TAGSPRO | D2484 | Implement TAGSPRO software for | 0 |  | 0 |  |  | 59046.2 | 1 | 59045.2 | 2008-01-08 | 2008-12-31 | 2008-03-01 | 2009-03-31
75080-DE Kentucky Other - Elec | RADIO | D2524KY | 2008 IDEN Backhaul | 0 |  | 0 |  |  | 871140.98 | 866250 | 4890.98 | 2010-01-13 | 2012-12-31 | 2010-01-01 | 2010-04-30
75080-DE Kentucky Other - Elec | DATAP | D2539 | Private Data Circuits | 0 |  | 0 |  |  | 116092.55 | 1 | 116091.55 | 2008-01-17 | 2009-01-30 | 2008-02-01 | 2009-04-30
75080-DE Kentucky Other - Elec | OPTIMALC | D3156 | Project Optimization Sftwr-Ky | 0 |  | 0 |  |  | 949.69 | 1 | 948.69 | 2008-03-26 | 2009-12-31 | 2008-05-01 | 2009-01-31
75080-DE Kentucky Other - Elec | FWSREFPH2 | DEPOTRF1 | depot refresh | 9131.1 |  | 9131.1 | 100% |  | 9131.1 | 9131 | 0.1 | 2015-04-15 08:59 | 2015-04-30 | 2015-04-01 | 2015-08-31
75080-DE Kentucky Other - Elec | MWTELBLKT | DRYRDGBKT | Dry Ridge Microwave Blanket | 10678 |  | 10678 | 100% |  | 23232.1 | 50000 | -26767.9 | 2012-04-09 | 2015-12-31 | 2012-04-01
75080-DE Kentucky Other - Elec | 100FACKY | E0884 | Purchase Recycling Bins KY | 0 |  | 0 |  |  | 6169.61 | 6162 | 7.61 | 2008-09-05 | 2008-12-31 | 2008-12-01 | 2008-12-31
75080-DE Kentucky Other - Elec | KYPYACCR | E1214 | Kentucky Quarterly Payroll Accrual | 149000 |  | 149000 | 100% |  | 205000 | 0 | 205000 | 2008-09-19 | 2050-12-31 | 2008-09-01
75080-DE Kentucky Other - Elec | MWEAMPH1 | E1456 | Kentucky EAM Phase 1 in Svc | 0 |  | 0 |  |  | 387939.96 | 316630.45 | 71309.51 | 2008-10-02 | 2008-09-02 | 2008-09-01 | 2008-09-02
75080-DE Kentucky Other - Elec | MWEAMCAP | E1460 | Kentucky EAM Capex | 0 |  | 0 |  |  | 591257.38 | 1100288.25 | -509030.87 | 2008-10-02 |  | 2008-09-01 | 2010-10-31
75080-DE Kentucky Other - Elec | TDIT | E3875 | Street Index - KY | 0 |  | 0 |  |  | 60473.27 | 82200 | -21726.73 | 2009-01-23 | 2051-03-31 | 2009-02-01 | 2009-08-15
75080-DE Kentucky Other - Elec | FEGISUPGR | EGISUPGRK | EGIS UPGRADE-HW KENTUCKY | 0 |  | 0 |  |  | 52056.02 | 56737 | -4680.98 | 2011-01-10 | 2014-04-30 | 2011-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | FEGISUPGS | EGISUPGSK | EGIS UPGR-SW | 0 |  | 0 |  |  | 58634.24 | 124474 | -65839.76 | 2011-01-24 | 2014-04-30 | 2011-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | CAPBUDK | ETSFHCAPK | CAPITAL BUDGET PROJECT KENT | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-07-01
75080-DE Kentucky Other - Elec | CAPBUDK | ETSPDCAPK | ETS Power Delivery Cap Overhead | 249.07 |  | 249.07 | 100% |  | 2606.47 | 0 | 2606.47 | 2008-07-07 | 2050-12-31 | 2008-07-01
75080-DE Kentucky Other - Elec | MWEAMPH2 | F1844 | Kentucky EAM Phase 2 in Service | 0 |  | 0 |  |  | 974499.36 | 1 | 974498.36 | 2009-11-02 | 2009-10-31 | 2009-10-01 | 2010-01-31
75080-DE Kentucky Other - Elec | CMSICNVK | F3171 | CIS.52 VB6 Conversion Kentucky | 0 |  | 0 |  |  | 334546.69 | 335000 | -453.31 | 2009-12-16 | 2011-10-31 | 2009-12-01 | 2011-11-30
75080-DE Kentucky Other - Elec | FIDENKENT | F9006 | IDEN MIBAS UPGRADE-KENTUCKY | 0 |  | 0 |  |  | 23268.81 | 14334 | 8934.81 | 2010-06-01 | 2010-12-30 | 2010-08-01 | 2011-01-18
75080-DE Kentucky Other - Elec | FITCOMKY | F9105 | IT COMMON - KENTUCKY | 0 |  | 0 |  |  | 5177.15 | 1 | 5176.15 | 2010-06-02 | 2012-12-31 | 2010-06-01
75080-DE Kentucky Other - Elec | MWAVE | FALMTHBKT | Falmouth Blanket | 0 |  | 0 |  |  | 7729.95 | 50000 | -42270.05 | 2012-06-26 | 2017-12-31 | 2012-06-01
75080-DE Kentucky Other - Elec | 100FACKY | FHKYLBPRT | Label Printers - FH Use | 0 |  | 0 |  |  | 9910.13 | 3000 | 6910.13 | 2009-12-02 | 2010-01-31 | 2009-12-01 | 2010-03-31
75080-DE Kentucky Other - Elec | FIBRUPG | FIBRKY09 | 2009 Fiber Upgrades - Kentucky | 0 |  | 0 |  |  | 39713.45 | 60000 | -20286.55 | 2009-03-11 | 2009-12-31 | 2009-05-01 | 2010-03-31
75080-DE Kentucky Other - Elec | TRANSPT | FIBRKY10 | Kentucky SONET additions | 0 |  | 0 |  |  | 56253.92 | 110000 | -53746.08 | 2010-01-22 | 2011-03-31 | 2010-01-01 | 2011-03-31
75080-DE Kentucky Other - Elec | FIDNEL10K | G1371 | MW iDEN RADIO UNITS & PARTS | 0 |  | 0 |  |  | -24893.88 | 73140 | -98033.88 | 2010-10-22 | 2010-12-31 | 2010-12-01 | 2011-03-31
75080-DE Kentucky Other - Elec | FBENTLYED | G1680 | BENTLEY EXPERT DESIGNER UPGR | 0 |  | 0 |  |  | 3969.45 | 8230 | -4260.55 | 2010-12-15 | 2011-06-30 | 2010-12-01 | 2011-08-27
75080-DE Kentucky Other - Elec | FBENTLEYK | G2242 | BENTLEY LDE WKFLOW/ED ENHANCEMENTS | 0 |  | 0 |  |  | 39066.41 | 14052 | 25014.41 | 2011-02-10 | 2011-06-30 | 2011-02-01 | 2012-02-14
75080-DE Kentucky Other - Elec | FEGISUPGR | G3022 | EGIS DEFECT RELEASE | 0 |  | 0 |  |  | 832.91 | 3372.07 | -2539.16 | 2011-04-13 | 2013-09-30 | 2011-04-01 | 2011-12-27
75080-DE Kentucky Other - Elec | FMAPLNKKE | G5253 | MAPLINK ENHANCEMENT-KENTUCKY | 0 |  | 0 |  |  | 64088.97 | 94938 | -30849.03 | 2011-10-06 | 2012-12-18 | 2011-10-01 | 2013-02-17
75080-DE Kentucky Other - Elec | 100FACKY | GD080001 | 19th & Augustine Windows | 0 |  | 0 |  |  | 83669.17 | 79587 | 4082.17 | 2009-05-29 | 2009-09-30 | 2009-05-01 | 2009-03-18
75080-DE Kentucky Other - Elec | MWTELBLKT | GLENCOMW | Glencoe Microwave Blanket | 0 |  | 0 |  |  | 1089.68 | 50000 | -48910.32 | 2012-07-26 | 2017-12-31 | 2013-06-01
75080-DE Kentucky Other - Elec | RADIO | IDEN08KY | iDEN In-building coverage | 0 |  | 0 |  |  | 2535.61 | 50000 | -47464.39 | 2008-09-15 | 2009-03-31 | 2009-02-01 | 2009-06-30
75080-DE Kentucky Other - Elec | RADIO | IDENKY09 | iDEN Radio additions | 0 |  | 0 |  |  | 527338.41 | 844550 | -317211.59 | 2009-04-09 | 2011-01-31 | 2009-05-01 | 2011-01-27
75080-DE Kentucky Other - Elec | RESBLDKY | KMW150211 | Stair Replacement @ Erlanger Ops | 113582.07 |  | 113582.07 | 100% |  | 113582.07 | 121466 | -7883.93 | 2015-06-24 14:04 | 2016-03-14 | 2015-07-01 | 2016-03-14
75080-DE Kentucky Other - Elec | 100FACKY | KY090070 | Replace 30 Ton RTU at Augustine | 0 |  | 0 |  |  | 61918.78 | 70161 | -8242.22 | 2009-05-04 | 2009-11-01 | 2009-05-01 | 2009-12-10
75080-DE Kentucky Other - Elec | 100FACKY | KY090078 | Install VAV boxes at Erlanger Ops | 0 |  | 0 |  |  | 17038.06 | 18215 | -1176.94 | 2009-05-26 | 2009-10-01 | 2009-06-01 | 2009-12-15
75080-DE Kentucky Other - Elec | RESBLDKY | KY100094 | ERLANGER INS ALC LIGHTING CONTROLS | 0 |  | 0 |  |  | 5595.72 | 6569 | -973.28 | 2010-12-07 | 2011-03-27 | 2010-12-01 | 2011-03-28
75080-DE Kentucky Other - Elec | SITESVCS | KY100273 | NEW OH/KY TELECOM GROUP | 0 |  | 0 |  |  | 308443.3 | 322675 | -14231.7 | 2010-09-16 | 2011-07-31 | 2010-10-01 | 2011-12-31
75080-DE Kentucky Other - Elec | RESBLDKY | KY100302 | PURCHASE OF AEDS FOR AUGUSTINE | 0 |  | 0 |  |  | 1150.51 | 1255 | -104.49 | 2010-10-18 | 2011-05-08 | 2010-12-01 | 2011-03-07
75080-DE Kentucky Other - Elec | RESBLDKY | KY110306 | Office reconfig @ Erlanger Op Ctr | 0 |  | 0 |  |  | 38073.81 | 39848 | -1774.19 | 2011-09-07 | 2012-05-01 | 2011-09-01 | 2012-06-12
75080-DE Kentucky Other - Elec | 75080 | KY120048 | Inst generator monitors @ KY micros | 0 |  | 0 |  |  | 27321.34 | 14739 | 12582.34 | 2012-06-11 | 2013-01-31 | 2012-06-01 | 2013-02-01
75080-DE Kentucky Other - Elec | 75080 | KY130377 | Install New Driveway @ Erlanger Ops | -8924.8 |  | -8924.8 | 100% |  | 80324.11 | 93211 | -12886.89 | 2013-10-02 | 2014-03-31 | 2013-10-01 | 2014-02-13
75080-DE Kentucky Other - Elec | 75080 | KY130378 | Rplce Lighting @ Erlanger Warehouse | -8119.8 |  | -8119.8 | 100% |  | 73078.43 | 90127 | -17048.57 | 2013-10-02 | 2014-03-31 | 2013-10-01 | 2014-02-22
75080-DE Kentucky Other - Elec | RESBLDKY | KYF100333 | AUGUSTINE PAVEMENT REPLACEMENT | 0 |  | 0 |  |  | 5918.47 | 6167 | -248.53 | 2010-12-07 | 2011-12-30 | 2010-12-01 | 2011-03-31
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110233 | Replace Pavng/Retain Wall Augustine | 0 |  | 0 |  |  | 1914828.55 | 1938891 | -24062.45 | 2011-05-11 | 2013-03-01 | 2011-06-01 | 2013-01-25
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110683 | Repl Fire Extinguishers @ KY Facil | 0 |  | 0 |  |  | 3561.95 | 3987 | -425.05 | 2011-10-13 | 2012-03-14 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110713 | Rooftop Fall Protect @ Erlanger | 0 |  | 0 |  |  | 8051.17 | 8889 | -837.83 | 2011-11-15 | 2012-03-31 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110717 | Rooftop Fall Protection @ Augustine | 0 |  | 0 |  |  | 18810.1 | 19613 | -802.9 | 2011-11-15 | 2012-03-31 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | 75080 | KYF120338 | Replace Ice Machines @ Erlanger | -300 |  | -300 | 100% |  | 13294.66 | 15385 | -2090.34 | 2012-09-06 | 2012-12-30 | 2012-11-01 | 2013-02-12
75080-DE Kentucky Other - Elec | 75080 | KYF120365 | Replace Heaters @ Erlanger Ops | 0 |  | 0 |  |  | 14900 | 16558 | -1658 | 2012-09-25 | 2013-02-28 | 2012-12-01 | 2013-03-12
75080-DE Kentucky Other - Elec | 75080 | KYF140753 | Rplce Conf Rm Furniture @ Erlanger | -71.64 |  | -71.64 | 100% |  | 43997.73 | 33308 | 10689.73 | 2014-10-20 | 2015-03-31 | 2014-12-01 | 2015-03-12
75080-DE Kentucky Other - Elec | 100FACKY | KYFM09001 | Replace fire&Intrustion Monitoring | 0 |  | 0 |  |  | 10391.56 | 10386 | 5.56 | 2009-08-07 | 2009-12-15 | 2009-12-01 | 2010-03-10
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10006 | Replace Concrete Drive Erlanger | 0 |  | 0 |  |  | 97989.98 | 105681 | -7691.02 | 2010-04-20 | 2010-11-30 | 2010-08-01 | 2011-02-12
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10007 | Install new ALC Board at Erlanger | 0 |  | 0 |  |  | 7613.19 | 7657 | -43.81 | 2010-05-18 | 2010-08-30 | 2011-01-01 | 2010-11-19
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10008 | WATER HEATER REPL @ AUGUSTINE | 0 |  | 0 |  |  | 24647.4 | 27241 | -2593.6 | 2010-08-30 | 2010-12-14 | 2010-12-01 | 2011-01-27
75080-DE Kentucky Other - Elec | MWAVE | KYMWVALRM | Kentucky Microwave Alarm | 0 |  | 0 |  |  | 264495.16 | 248300 | 16195.16 | 2011-02-10 | 2011-02-28 | 2011-02-01 | 2011-06-30
75080-DE Kentucky Other - Elec | RESBLDKY | KYP110242 | Inst Gen Monitor Equip @ KY Micro | 0 |  | 0 |  |  | 26510.69 | 23682 | 2828.69 | 2011-09-08 | 2012-04-30 | 2011-10-01 | 2012-05-01
75080-DE Kentucky Other - Elec | 75080 | KYP120201 | Upgrade Light Fixtures @ Erlanger | 0 |  | 0 |  |  | 40945.61 | 56806 | -15860.39 | 2012-07-26 | 2014-03-31 | 2012-08-01 | 2013-08-09
75080-DE Kentucky Other - Elec | 75080 | KYP120211 | Crew Rm Reconfig @ Erlanger Ops | -31502.3 |  | -31502.3 | 100% |  | 281871.68 | 346911 | -65039.32 | 2012-07-17 | 2013-04-30 | 2012-07-01 | 2013-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP130400 | Furniture Purchase I @ Erlanger | 0 |  | 0 |  |  | 20895.34 | 38968 | -18072.66 | 2013-12-06 | 2014-03-31 | 2014-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP130568 | Repl Overhead Doors @ Erlanger Ops | 0 |  | 0 |  |  | 73467.32 | 79238 | -5770.68 | 2014-01-13 | 2014-05-29 | 2014-01-01 | 2014-05-31
75080-DE Kentucky Other - Elec | 75080 | KYP140021 | Install Ventilation Syst @ 19 & Aug | 0 |  | 0 |  |  | 337992.03 | 323771 | 14221.03 | 2014-02-05 | 2015-03-31 | 2014-04-01 | 2014-11-01
75080-DE Kentucky Other - Elec | 75080 | KYP140165 | Inst Fire Alarm Syst @ Erlanger Ops | 0 |  | 0 |  |  | 73366.57 | 87618 | -14251.43 | 2014-04-06 | 2014-09-13 | 2014-04-01 | 2014-09-13
75080-DE Kentucky Other - Elec | 75080 | KYP140215 | Inst Fall Protection @ Erlanger Ops | 0 |  | 0 |  |  | 26799.89 | 29710 | -2910.11 | 2014-06-15 | 2014-09-30 | 2014-06-01 | 2014-09-30
75080-DE Kentucky Other - Elec | 75080 | KYP140332 | Security Upgrades @ Augustine Off | 34255.74 |  | 34255.74 | 100% |  | 141137.47 | 152592 | -11454.53 | 2014-06-26 | 2015-03-01 | 2014-07-01 | 2015-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP140674 | Inst Veh Charging Equip @ Erlanger | 10220 |  | 10220 | 100% |  | 10220 | 16165 | -5945 | 2014-11-21 | 2015-05-06 | 2015-01-01 | 2015-03-26
75080-DE Kentucky Other - Elec | 75080 | KYP140750 | Install Fuel KeyCard @ Erlanger Ops | 1547.59 |  | 1547.59 | 100% |  | 37021.21 | 48746 | -11724.79 | 2014-11-04 | 2015-08-29 | 2014-11-01 | 2015-08-28
75080-DE Kentucky Other - Elec | RADIO | MODKY09 | Replace vehicular radio modems | 0 |  | 0 |  |  | 145687.05 | 175000 | -29312.95 | 2009-04-13 | 2009-12-31 | 2009-04-01 | 2010-03-01
75080-DE Kentucky Other - Elec | FMWAVEKY | MW732REP | MW Comm Shelter Repl KY-NINT732 | 81199.28 |  | 81199.28 | 100% |  | 408410.59 | 430000 | -21589.41 | 2014-03-05 | 2014-12-31 | 2014-03-01 | 2015-04-30
75080-DE Kentucky Other - Elec | MWAVE | MWAVEKY10 | Upgrade MidW Microwave infra | 0 |  | 0 |  |  | 442410.49 | 341232 | 101178.49 | 2010-03-11 | 2011-08-31 | 2010-03-01 | 2011-11-30
75080-DE Kentucky Other - Elec | MWAVE | MWBUGENKY | Microwave Backup Generator Kentucky | 0 |  | 0 |  |  | 249540.28 | 242795.05 | 6745.23 | 2011-03-17 | 2012-04-30 | 2011-03-01 | 2012-08-15
75080-DE Kentucky Other - Elec | FMWAVEKY | MWEOLVERN | MW EOL Verona | 4.92 |  | 4.92 | 100% |  | 916.44 | 10000 | -9083.56 | 2014-05-29 | 2014-12-31 | 2014-08-01 | 2015-03-31
75080-DE Kentucky Other - Elec | FMWAVEKY | MWMWUPG | Verona Microwave Upgrades | 4951.3 |  | 4951.3 | 100% |  | 64163.75 | 60346 | 3817.75 | 2014-01-06 | 2014-12-31 | 2014-02-01 | 2014-09-17
75080-DE Kentucky Other - Elec | MWAVE | N1226SPAR | N1226 Sparta EOL | 1716.8 |  | 1716.8 | 100% |  | 1716.8 | 3015 | -1298.2 | 2015-05-27 15:35 | 2015-12-31 | 2015-07-01 | 2016-03-15
75080-DE Kentucky Other - Elec | FMWAVEKY | N1226TAMI | N1226 Taylor Mill Equip EOL | 3565.09 |  | 3565.09 | 100% |  | 3565.09 | 3015 | 550.09 | 2015-06-11 17:36 | 2015-12-31 | 2015-08-01 | 2015-09-23
75080-DE Kentucky Other - Elec | MWAVE | N1226UNIO | N1226 Midwest Pwr Equip Union | 7.23 |  | 7.23 | 100% |  | 1274.34 | 2640 | -1365.66 | 2014-07-14 | 2015-12-31 | 2014-09-01 | 2016-04-28
75080-DE Kentucky Other - Elec | MWAVE | N1226VERO | N1226 MWESTPWREQUIP EOL VERONA 2 | 1157.47 |  | 1157.47 | 100% |  | 1252.52 | 7640 | -6387.48 | 2014-06-23 | 2015-12-31 | 2014-07-01 | 2016-01-01
75080-DE Kentucky Other - Elec | MWAVE | N1226WNKR | N1226 Midwest Pwr Equip EOL WKNR | 38757.39 |  | 38757.39 | 100% |  | 40054.3 | 2640 | 37414.3 | 2014-07-14 | 2015-12-31 | 2014-09-01 | 2015-09-23
75080-DE Kentucky Other - Elec | FMWAVEKY | N1259WNKR | N1259WNKR Tower | 29928.84 |  | 29928.84 | 100% |  | 29928.84 | 18889 | 11039.84 | 2015-04-28 14:11 | 2015-12-31 | 2015-05-01 | 2015-10-10
75080-DE Kentucky Other - Elec | 100FACKY | NEWPORTRT | Ret Newport Plaza Cus Svc Bldg | 0 |  | 0 |  |  | 0 |  | 0 | 2011-04-08 | 2009-12-31 | 2011-08-01 | 2011-11-16
75080-DE Kentucky Other - Elec | MWAVE | NINT1309 | Dry Ridge KY Coms Tower Acquis | 140044.14 |  | 140044.14 | 100% |  | 147465.81 | 125000 | 22465.81 | 2014-08-27 | 2014-12-31 | 2014-09-01 | 2016-10-14
75080-DE Kentucky Other - Elec | NETWORK1 | NINT621 | Ops Center Technology Refresh | 0 |  | 0 |  |  | 40565.7 | 38205 | 2360.7 | 2012-11-27 | 2013-03-31 | 2012-12-01 | 2014-09-30
75080-DE Kentucky Other - Elec | FWSREFPH2 | P6367 | Workstation refresh project | 0 |  | 0 |  |  | 714626.09 | 737000 | -22373.91 | 2014-09-23 | 2014-09-22 | 2014-09-01 | 2014-01-31
75080-DE Kentucky Other - Elec | RADIO | PAGTRNKY | Pagin Transmitter replacement | 0 |  | 0 |  |  | 191767.68 | 190327.92 | 1439.76 | 2010-11-01 | 2012-12-31 | 2010-12-01 | 2012-06-30
75080-DE Kentucky Other - Elec | FEGISUPGS | PCTAIT214 | EGIS UPGR-SW | 0 |  | 0 |  |  | 161902.27 | 160816 | 1086.27 | 2013-10-25 | 2014-04-30 | 2013-11-01 | 2014-03-31
75080-DE Kentucky Other - Elec | MWAVE | REPPWREQP | Midwest 2011 Power Equipment Replac | 0 |  | 0 |  |  | 14756 | 13000 | 1756 | 2011-05-18 | 2012-04-01 | 2012-07-01 | 2012-10-01
75080-DE Kentucky Other - Elec | 75080 | RETCOV | Retire Covington | 0 |  | 0 |  |  | 0 |  | 0 | 2012-12-20 | 2013-03-31 | 2012-12-01 | 2013-03-31
75080-DE Kentucky Other - Elec | 75080 | RETCOV2 | Retire Covington - Elec | 0 |  | 0 |  |  | 0 |  | 0 | 2012-12-20 | 2013-03-31 | 2012-12-01 | 2013-04-05
75080-DE Kentucky Other - Elec | MWTELBLKT | ROSHUGBKT | Ross Hughes MW Blanket | 1904 |  | 1904 | 100% |  | 2964 | 50000 | -47036 | 2012-07-20 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | RYLANDBKT | Ryland Heights MW Blanket | 0 |  | 0 |  |  | 2164.69 | 50000 | -47835.31 | 2012-09-11 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | SCADA | SCADKY09 | 2009 SCADA projects Kentucky | 0 |  | 0 |  |  | 65109.41 | 25000 | 40109.41 | 2009-02-03 | 2009-12-31 | 2009-04-01 | 2010-03-31
75080-DE Kentucky Other - Elec | 75080 | SFTWRE | Software Retirement-Asset Use Only | 0 |  | 0 |  |  | 0 |  | 0 | 2012-09-20 | 2026-03-30 | 2012-09-01
75080-DE Kentucky Other - Elec | MWTELBLKT | SPARTABKT | Sparta Tower Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-02-08 | 2015-12-31 | 2012-02-01
75080-DE Kentucky Other - Elec | MWAVE | TAYLORBAT | Taylor Mill Battery replacement | 0 |  | 0 |  |  | 3820.95 | 3800 | 20.95 | 2012-08-23 | 2012-12-31 | 2013-01-01 | 2014-11-30
75080-DE Kentucky Other - Elec | MWAVE | TAYLRMBLK | Taylor Mill, KY, Microwave Blanket | 0 |  | 0 |  |  | -5005.32 | 50000 | -55005.32 | 2014-03-03 | 2025-12-31 | 2014-03-01
75080-DE Kentucky Other - Elec | MWTELBLKT | VERONAMW | Verona Microwave Blanket | 1102.39 |  | 1102.39 | 100% |  | 3903.37 | 50000 | -46096.63 | 2012-07-26 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | NETWORK1 | WANUPGRII | WAN EOL Upgrd Phase II | 0 |  | 0 |  |  | 23902.1 | 23907 | -4.9 | 2013-09-17 | 2014-06-30 | 2013-10-01 | 2014-09-30
75080-DE Kentucky Other - Elec | MWAVE | WILDERBAT | Wilder MW Battery Replacement | 0 |  | 0 |  |  | 2551.68 | 2500 | 51.68 | 2013-09-17 | 2013-12-31 | 2014-02-01 | 2014-11-30
75080-DE Kentucky Other - Elec | MWTELBLKT | WILDERBKT | Wilder Microwave Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-07-20 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | WNKRBLKT | WNKR Tower Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-09-05 | 2025-12-31 | 2012-09-01
75081-DE Kentucky Fossil | PCTAIT137 | AIT13707H | Gas ETRM | 12.22 |  | 12.22 | 100% |  | 14.84 | 387.22 | -372.38 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTAIT137 | AIT13707S | Gas ETRM | 788.39 |  | 788.39 | 100% |  | 990.06 | 28287.7 | -27297.64 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTANT137 | AIT13708H | Gas ETRM | -2.94 |  | -2.94 | 100% |  | 268.31 | 102.93 | 165.38 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTANT137 | AIT13708S | Gas ETRM | 4120.7 |  | 4120.7 | 100% |  | 48601.71 | 7519.51 | 41082.2 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTAIT218 | AIT21808H | FSO Forecasting Consolidation | -13.72 |  | -13.72 | 100% |  | -13.3 | 1518.46 | -1531.76 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT218 | AIT21808S | FSO Forecasting Consolidation | -593.39 |  | -593.39 | 100% |  | -572.18 | 37846.81 | -38418.99 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT21C | AIT21809H | FSO Forecasting Consolidation | 10.31 |  | 10.31 | 100% |  | 514.35 | 403.64 | 110.71 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT21C | AIT21809S | FSO Forecasting Consolidation | 824.36 |  | 824.36 | 100% |  | 25614.91 | 10060.55 | 15554.36 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | EB201316 | C9122 | EBS-Precipitator Key System | 0 |  | 0 |  |  | 163463.06 | 432758 | -269294.94 | 2007-01-17 | 2008-02-13 | 2007-02-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01234 | C9145 | Circ Water Piping Anode Repl | 0 |  | 0 |  |  | 236141.69 | 356255 | -120113.31 | 2007-01-24 | 2008-01-31 | 2007-01-01 | 2007-11-30
75081-DE Kentucky Fossil | EB1472 | C9152 | Cooling Tower Fan Blades-2007 | 0 |  | 0 |  |  | 69324.01 | 90454 | -21129.99 | 2007-01-24 | 2007-12-31 | 2007-02-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01214 | C9221 | EBS-Module Inlt Turning Vanes | 0 |  | 0 |  |  | 151474.23 | 171803 | -20328.77 | 2007-02-01 | 2008-06-05 | 2007-04-01 | 2007-10-31
75081-DE Kentucky Fossil | EB201351 | C9222 | EBS-Repl B Module Demistr Trys | 0 |  | 0 |  |  | 228799.58 | 421718 | -192918.42 | 2007-02-01 | 2008-04-30 | 2007-03-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01229 | C9223 | EBS-Repl Module Inlt Exp Jnts | 0 |  | 0 |  |  | 209019.92 | 332437 | -123417.08 | 2007-02-01 | 2008-04-30 | 2007-03-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01217 | C9224 | Inlt Vanes on Sec Air Windbox | 0 |  | 0 |  |  | 31346.36 | 46224 | -14877.64 | 2007-02-01 | 2008-05-01 | 2007-02-01 | 2007-08-31
75081-DE Kentucky Fossil | EB201356 | C9318 | EBS-Repl Demin Sump Piping | 0 |  | 0 |  |  | 90123.7 | 146201 | -56077.3 | 2007-02-22 | 2008-09-28 | 2007-02-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01253 | C9847 | New Generator Flux Shield | 0 |  | 0 |  |  | 47007.22 | 74046 | -27038.78 | 2007-05-18 | 2007-08-31 | 2007-08-01 | 2007-11-30
75081-DE Kentucky Fossil | EB021410 | CEB021410 | Dry Bottom Ash Conversion | 153418.49 |  | 153418.49 | 100% |  | 153418.49 | 24439593 | -24286174.51 | 2015-10-15 14:37 | 2018-07-30 | 2015-12-01
75081-DE Kentucky Fossil | CCPCAP | CEB021493 | East Bend ByProducts Scale Mgmt Upg | 125259.8 |  | 125259.8 | 100% |  | 125259.8 | 132199 | -6939.2 | 2015-01-23 | 2017-04-30 | 2015-09-01
75081-DE Kentucky Fossil | EB201219 | CEB201219 | EBS-Repl Cooling Towr Motr 07 | 0 |  | 0 |  |  | 69781.27 | 140380 | -70598.73 | 2007-02-22 | 2008-06-30 | 2007-03-01 | 2008-05-31
75081-DE Kentucky Fossil | EB201253 | CEB201253 | 2-2 Repl Ash Sluice Pump Motor | 0 |  | 0 |  |  | 40822.56 | 123326 | -82503.44 | 2008-02-21 | 2009-05-31 | 2008-04-01 | 2009-03-31
75081-DE Kentucky Fossil | EB201353 | CEB201353 | EBS-Repl Thicknr Rake Arms | 0 |  | 0 |  |  | 392542.71 | 839900 | -447357.29 | 2007-04-12 | 2008-06-30 | 2007-04-01 | 2008-12-30
75081-DE Kentucky Fossil | EB201362 | CEB201362 | Cooling Tower Gearbox 2008 | 0 |  | 0 |  |  | 218058.69 | 296068 | -78009.31 | 2008-01-24 | 2009-02-28 | 2008-02-01 | 2009-03-15
75081-DE Kentucky Fossil | CCPCAP | CEBLD1201 | CCP East Bend-14 Primary Spillway R | 9697319.76 |  | 9697319.76 | 100% |  | 9697319.76 | 9471135 | 226184.76 | 2015-02-25 16:25 | 2015-05-30 | 2015-03-01 | 2016-05-12
75081-DE Kentucky Fossil | EBS01209 | CEBS01209 | SAH Sootblower Addition | 0 |  | 0 |  |  | 960496.14 | 535313 | 425183.14 | 2008-04-08 | 2009-09-30 | 2008-06-01 | 2009-09-29
75081-DE Kentucky Fossil | EBS01218 | CEBS01218 | EBS-Repl Turbine Room Roof | 0 |  | 0 |  |  | 127834.06 | 216096 | -88261.94 | 2007-09-02 | 2008-04-10 | 2007-09-01 | 2008-01-13
75081-DE Kentucky Fossil | EBS01235 | CEBS01235 | EBS- Repl Security System | 76938.54 |  | 76938.54 | 100% |  | 321830.62 | 226581 | 95249.62 | 2007-04-17 | 2009-10-15 | 2007-11-01 | 2009-04-30
75081-DE Kentucky Fossil | EBS01238 | CEBS01238 | EBS-Mercury Monitoring System | 298926.72 |  | 298926.72 | 100% |  | 1221862.51 | 966025 | 255837.51 | 2007-04-17 | 2011-07-31 | 2007-05-01 | 2011-10-25
75081-DE Kentucky Fossil | EBS01239 | CEBS01239 | 2007 Landfill Leachate Sys | 0 |  | 0 |  |  | 53575.18 | 273480 | -219904.82 | 2007-10-16 | 2008-02-29 | 2007-12-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01251 | CEBS01251 | EBS-Rmove 2-2 PA Fan Silencer | 0 |  | 0 |  |  | 0 | 4739 | -4739 | 2007-04-17 | 2007-10-31 | 2009-05-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01252 | CEBS01252 | EBS-Repl Air Compressor Contrl | 0 |  | 0 |  |  | 55964.27 | 83931 | -27966.73 | 2007-04-29 | 2008-04-01 | 2007-05-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01263 | CEBS01263 | Repl Turbine Blade Row | 0 |  | 0 |  |  | 3386310.93 | 5544195 | -2157884.07 | 2008-01-24 | 2009-11-30 | 2008-02-01 | 2009-08-25
75081-DE Kentucky Fossil | EBS01272 | CEBS01272 | Rewind 2-2 & 2-3 ID Fan Motr | 0 |  | 0 |  |  | 778291.95 | 1002753 | -224461.05 | 2007-11-06 | 2008-12-31 | 2007-12-01 | 2008-09-30
75081-DE Kentucky Fossil | EBS01274 | CEBS01274 | EBS-ED Fan Motor | 0 |  | 0 |  |  | 391358.53 | 589470 | -198111.47 | 2007-09-02 | 2008-03-31 | 2007-09-01 | 2008-03-31
75081-DE Kentucky Fossil | EBS01281 | CEBS01281 | EBS-Landfill Excavator | 0 |  | 0 |  |  | 140911.52 | 185628 | -44716.48 | 2007-09-02 | 2007-12-10 | 2007-10-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01305 | CEBS01305 | EBS-Ash Pnd Ground Wtr Monitor | 0 |  | 0 |  |  | 49419.39 | 75623 | -26203.61 | 2007-09-25 | 2008-12-31 | 2007-09-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01309 | CEBS01309 | EBS-WSP Lime Feeder Platform | 0 |  | 0 |  |  | 16993.48 | 19649 | -2655.52 | 2007-12-05 | 2008-02-29 | 2007-12-01 | 2008-01-31
75081-DE Kentucky Fossil | EBS01311 | CEBS01311 | Repl Service Wtr Strainer | 0 |  | 0 |  |  | 74479.66 | 100883 | -26403.34 | 2008-03-06 | 2009-05-31 | 2008-03-01 | 2008-12-31
75081-DE Kentucky Fossil | EBS01314 | CEBS01314 | Repl SCR Ammonia Detectors | 12114.94 |  | 12114.94 | 100% |  | 50460.98 | 7434 | 43026.98 | 2008-04-09 | 2008-12-31 | 2008-04-01 | 2009-03-22
75081-DE Kentucky Fossil | CGYEB115 | CGYPEB115 | CCP EB-115 T6 E. BEND GYPSUM MITIGA | 804460.51 |  | 804460.51 | 100% |  | 804460.51 | 1500000 | -695539.49 | 2015-06-04 17:33 | 2015-12-31 | 2015-08-01 | 2015-12-31
75081-DE Kentucky Fossil | MF5506 | CMF5506 | PLC in Chem Sample Rm | 0 |  | 0 |  |  | 39451.61 | 48155 | -8703.39 | 2008-02-28 | 2009-03-31 | 2008-06-01 | 2008-12-31
75081-DE Kentucky Fossil | MF601219 | CMF601219 | LP/HP Htr Level Controls | 0 |  | 0 |  |  | 182812.04 | 188027 | -5214.96 | 2008-02-28 | 2009-06-30 | 2008-05-01 | 2009-06-22
75081-DE Kentucky Fossil | MU601213 | CMU601213 | Repl FD Fan Drives | 0 |  | 0 |  |  | 107962.71 | 214137 | -106174.29 | 2008-02-28 | 2009-04-08 | 2008-04-01 | 2009-02-01
75081-DE Kentucky Fossil | MU601216 | CMU601216 | MFS-6 Misc Valves | 0 |  | 0 |  |  | 291236.94 | 1267369 | -976132.06 | 2008-02-05 | 2019-03-31 | 2008-03-01 | 2015-06-30
75081-DE Kentucky Fossil | MU601217 | CMU601217 | MFS-6 General Equipment | 0 |  | 0 |  |  | 76017.65 | 546782 | -470764.35 | 2008-02-05 | 2010-03-31 | 2008-02-01
75081-DE Kentucky Fossil | MU601224 | CMU601224 | MFS-6 Repl Condenser Bellows | 0 |  | 0 |  |  | 9887.7 | 55073 | -45185.3 | 2007-07-23 | 2008-01-30 | 2007-09-01 | 2007-10-07
75081-DE Kentucky Fossil | MU601225 | CMU601225 | MFS-6 Repl Battery Chrgers 1&2 | 0 |  | 0 |  |  | 37574.91 | 30943 | 6631.91 | 2007-11-08 | 2008-09-30 | 2008-03-01 | 2008-10-31
75081-DE Kentucky Fossil | MU601228 | CMU601228 | MFS-6 Repl Precipitator T/R | 0 |  | 0 |  |  | 93667.23 | 81167 | 12500.23 | 2007-09-02 | 2008-07-31 | 2007-08-01 | 2008-06-30
75081-DE Kentucky Fossil | MU601231 | CMU601231 | MFS-6 Instl Coal Conveyor & Dr | 0 |  | 0 |  |  | 3770058.8 | 3015998 | 754060.8 | 2007-11-28 | 2009-11-01 | 2007-12-01 | 2009-12-22
75081-DE Kentucky Fossil | MU601232 | CMU601232 | Repl Genratr Collctr Rings | 0 |  | 0 |  |  | 223008.94 | 53858 | 169150.94 | 2008-04-09 | 2009-12-30 | 2008-05-01 | 2008-09-30
75081-DE Kentucky Fossil | PEM1202 | CPEM1202 | 070-PEM General Equipment | 0 |  | 0 |  |  | 33729.76 | 73316 | -39586.24 | 2007-05-15 | 2014-12-31 | 2007-05-01 | 2014-01-31
75081-DE Kentucky Fossil | EBS01278 | D1138 | EBS-ID Fan Motor 2-1 Rewind | 0 |  | 0 |  |  | 226305.84 | 410755 | -184449.16 | 2007-07-04 | 2008-03-31 | 2007-07-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01259 | D1148 | EBS-2-1 SAH Thrust Bearing | 0 |  | 0 |  |  | 75418.06 | 106155 | -30736.94 | 2007-07-08 | 2007-12-30 | 2007-07-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01287 | D1437 | EBS-2-1 Silo Flyash Blowr Motr | 0 |  | 0 |  |  | 40265.22 | 89245 | -48979.78 | 2007-09-02 | 2008-10-31 | 2007-09-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01307 | D1826 | EBS-Repl 2-4 Vacuum Pump Motor | 0 |  | 0 |  |  | 8819.9 | 27752 | -18932.1 | 2007-10-12 | 2008-12-31 | 2007-10-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01248 | D3122 | Ky Sales & Use Tax Vintage 07 | 5934.8 |  | 5934.8 | 100% |  | 24324.22 | 26119 | -1794.78 | 2008-03-21 | 2008-03-31 | 2008-03-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01248 | D3124 | Ky Sales & Use Tax Vintage 05 | 83617.94 |  | 83617.94 | 100% |  | 342714.76 | 368008 | -25293.24 | 2008-03-21 | 2008-03-31 | 2008-03-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01267 | D3553 | Sludge Transfr Pmp Replacemnt | 33218.22 |  | 33218.22 | 100% |  | 136278.1 | 175621 | -39342.9 | 2008-05-21 | 2009-08-24 | 2008-09-01 | 2009-02-14
75081-DE Kentucky Fossil | EB1482 | D3558 | Coolng Towr Fan Blades 2008 | 0 |  | 0 |  |  | 81896.2 | 109365 | -27468.8 | 2008-05-21 | 2009-03-31 | 2008-08-01 | 2009-02-12
75081-DE Kentucky Fossil | EBS01206 | D3666 | Replace SAH Preheat Coils | 0 |  | 0 |  |  | 1982885.62 | 2382627 | -399741.38 | 2008-06-12 | 2010-08-15 | 2008-11-01 | 2010-08-18
75081-DE Kentucky Fossil | EB020027 | EB020027X | #1 Lime Conveyor Belt Replacement | 145902.38 |  | 145902.38 | 100% |  | 145902.38 | 205213.25 | -59310.87 | 2015-10-19 12:59 | 2016-10-01 | 2015-11-01 | 2016-08-06
75081-DE Kentucky Fossil | EB020033 | EB020033X | Install Tube Bundle on 2-1A,B FWH | 395844.42 |  | 395844.42 | 100% |  | 395844.42 | 990557.99 | -594713.57 | 2015-09-09 11:17 | 2016-08-01 | 2015-09-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020037 | EB020037X | Replace SAH Preheat Coils | 12591.14 |  | 12591.14 | 100% |  | 12591.14 | 323572 | -310980.86 | 2015-10-06 13:29 | 2016-12-31 | 2015-10-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020039 | EB020039X | New Relay & Maintenance Switches | 30083.69 |  | 30083.69 | 100% |  | 30083.69 | 937934.72 | -907851.03 | 2015-12-18 08:03 | 2016-08-31 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020058 | EB020058X | CT Drift Elim Rplcmnt | 235374.34 |  | 235374.34 | 100% |  | 235374.34 | 1263106.51 | -1027732.17 | 2015-10-06 11:00 | 2016-06-01 | 2015-10-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020083 | EB020083X | Replace NOx Monitors | 47681.4 |  | 47681.4 | 100% |  | 47681.4 | 366249.89 | -318568.49 | 2015-12-01 10:45 | 2016-05-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020100 | EB020100X | Demin Mixed Bed Vessel Replacement | 140721.19 |  | 140721.19 | 100% |  | 140721.19 | 138000.07 | 2721.12 | 2015-06-22 15:41 | 2015-11-01 | 2015-08-01 | 2016-01-05
75081-DE Kentucky Fossil | EB020224 | EB020224X | Replace Atomic Absorption Unit | 98943.16 |  | 98943.16 | 100% |  | 98943.16 | 95375 | 3568.16 | 2015-10-06 12:49 | 2015-12-07 | 2015-12-01 | 2016-04-08
75081-DE Kentucky Fossil | EB020250 | EB020250X | Precip Retention Wall | 62086.39 |  | 62086.39 | 100% |  | 62086.39 | 72234.75 | -10148.36 | 2015-11-17 10:58 | 2016-06-01 | 2015-12-01 | 2016-05-01
75081-DE Kentucky Fossil | EB020251 | EB020251X | Replace 2-1 Pugmill Gearbox | 16472.99 |  | 16472.99 | 100% |  | 16472.99 | 52573.25 | -36100.26 | 2015-11-17 10:29 | 2015-11-30 | 2015-12-01 | 2016-02-29
75081-DE Kentucky Fossil | EB020254 | EB020254X | Event Free: Nuva Feeder Bldg Lights | 51380.88 |  | 51380.88 | 100% |  | 51380.88 | 66165.53 | -14784.65 | 2015-12-15 14:34 | 2015-12-31 | 2015-12-01 | 2016-03-23
75081-DE Kentucky Fossil | EB020257 | EB020257X | Event Free: MSP Oil Room Lighting | 4804.36 |  | 4804.36 | 100% |  | 4804.36 | 27798.45 | -22994.09 | 2015-12-01 11:07 | 2015-12-31 | 2015-12-01 | 2016-03-23
75081-DE Kentucky Fossil | EB020261 | EB020261X | Replace North TUF Pump | 62947.45 |  | 62947.45 | 100% |  | 62947.45 | 50123.72 | 12823.73 | 2015-12-28 12:34 | 2015-04-01 | 2015-12-01 | 2015-07-01
75081-DE Kentucky Fossil | EB020263 | EB020263X | Material Handling Shelters-Event Fr | 63604.63 |  | 63604.63 | 100% |  | 63604.63 | 147117.24 | -83512.61 | 2015-12-14 08:52 | 2015-12-31 | 2015-12-01 | 2016-03-23
75081-DE Kentucky Fossil | EB020267 | EB020267X | 2-2 Condenser Vacuum Pump | 41302.83 |  | 41302.83 | 100% |  | 41302.83 | 58039.66 | -16736.83 | 2015-12-28 12:14 | 2015-12-31 | 2015-12-01 | 2016-03-10
75081-DE Kentucky Fossil | EB021205 | EB021205X | Boiler Room Roof Replacement | 0 |  | 0 |  |  | 191888.5 | 426697 | -234808.5 | 2008-10-13 | 2009-09-16 | 2008-10-01 | 2009-04-06
75081-DE Kentucky Fossil | EB021207 | EB021207X | Coal Bunker Lighting | 0 |  | 0 |  |  | 17506.33 | 30961 | -13454.67 | 2009-03-30 | 2009-06-30 | 2009-05-01 | 2009-05-13
75081-DE Kentucky Fossil | EB021210 | EB021210X | INSTALL PARTICULATE MONTIOR | 0 |  | 0 |  |  | 164901.9 | 266016 | -101114.1 | 2011-04-26 | 2012-02-13 | 2011-05-01 | 2011-10-25
75081-DE Kentucky Fossil | EB021216 | EB021216X | SCR Winterization | 0 |  | 0 |  |  | 85622.78 | 105291 | -19668.22 | 2009-03-13 | 2009-03-30 | 2009-03-01 | 2009-06-13
75081-DE Kentucky Fossil | EB021217 | EB021217X | WSP Switchbreaker Lifter | 0 |  | 0 |  |  | 32798.36 | 44484 | -11685.64 | 2009-07-22 | 2010-01-15 | 2009-07-01 | 2010-01-01
75081-DE Kentucky Fossil | EB021219 | EB021219X | REPLACE FLOW MONITOR | 0 |  | 0 |  |  | 57213.81 | 79903 | -22689.19 | 2009-04-03 | 2009-08-07 | 2009-08-01 | 2009-08-18
75081-DE Kentucky Fossil | EB021221 | EB021221X | Purchase WSP Shovel and Loader | 0 |  | 0 |  |  | 69302.23 | 117133 | -47830.77 | 2009-03-30 | 2009-06-26 | 2009-04-01 | 2009-09-01
75081-DE Kentucky Fossil | EB021222 | EB021222X | Replace Stack Flow Monitor | 42205.66 |  | 42205.66 | 100% |  | 139968.04 | 103609 | 36359.04 | 2013-09-26 | 2014-06-01 | 2013-10-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021224 | EB021224X | Replace 3 sump pumps | 0 |  | 0 |  |  | 61100.22 | 76206 | -15105.78 | 2009-05-06 | 2010-07-31 | 2009-06-01 | 2010-07-02
75081-DE Kentucky Fossil | EB021231 | EB021231X | Replace CBU Buckets & Chains | 168836.92 |  | 168836.92 | 100% |  | 168836.92 | 567317.22 | -398480.3 | 2015-09-17 10:09 | 2016-08-01 | 2015-09-01 | 2016-08-10
75081-DE Kentucky Fossil | EB021233 | EB021233X | Replace CBU Chains and Buckets | 21561.86 |  | 21561.86 | 100% |  | 267717.34 | 357680 | -89962.66 | 2013-08-05 | 2014-08-01 | 2013-08-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021236 | EB021236X | Replace BFP Outlet Valve | 0 |  | 0 |  |  | 406884.84 | 582388 | -175503.16 | 2009-08-20 | 2010-06-22 | 2009-08-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021238 | EB021238X | ID Fan VFD Control Board Rep | 45545.85 |  | 45545.85 | 100% |  | 338748.68 | 451841 | -113092.32 | 2013-08-26 | 2014-12-31 | 2013-09-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021244 | EB021244X | Replace 2-1 BFP Outlet Valve | 0 |  | 0 |  |  | 382978.67 | 595228 | -212249.33 | 2011-07-19 | 2012-06-07 | 2011-07-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021246 | EB021246X | HVAC Room Roof Replacement | 90513.45 |  | 90513.45 | 100% |  | 90513.45 | 83631 | 6882.45 | 2015-04-16 15:39 | 2015-09-01 | 2015-06-01 | 2015-09-30
75081-DE Kentucky Fossil | EB021247 | EB021247X | CBU Hoist and Electric Rm Roof | 2165.65 |  | 2165.65 | 100% |  | 8844.9 | 31973 | -23128.1 | 2012-08-21 | 2013-08-26 | 2013-04-01 | 2013-07-19
75081-DE Kentucky Fossil | EB021249 | EB021249X | CT Acid Metering Pump | 16859.68 |  | 16859.68 | 100% |  | 69129.57 | 61640 | 7489.57 | 2010-09-16 | 2011-06-20 | 2010-10-01 | 2011-04-20
75081-DE Kentucky Fossil | EB021250 | EB021250X | CBU Cable Reel and Drive | 14849.67 |  | 14849.67 | 100% |  | 182998.83 | 255347 | -72348.17 | 2012-10-22 | 2014-12-31 | 2012-12-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021257 | EB021257X | S.Thickner Tunnel E. Sump Pump | 0 |  | 0 |  |  | 84952.64 | 155583 | -70630.36 | 2012-08-31 | 2014-11-20 | 2012-09-01 | 2013-04-29
75081-DE Kentucky Fossil | EB021259 | EB021259X | 2-6 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 188695.13 | 357710 | -169014.87 | 2010-03-08 | 2011-02-01 | 2010-04-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021260 | EB021260X | 2-3 Pulverizer Roll Wheel Repl | 119996.23 |  | 119996.23 | 100% |  | 491833.81 | 423246 | 68587.81 | 2010-09-16 | 2011-07-27 | 2010-10-01 | 2011-02-12
75081-DE Kentucky Fossil | EB021261 | EB021261X | 2-5 Pulverizer Roll Wheel Repl | 95341.03 |  | 95341.03 | 100% |  | 395830.6 | 370132 | 25698.6 | 2011-08-12 | 2012-06-21 | 2011-09-01 | 2012-07-31
75081-DE Kentucky Fossil | EB021263 | EB021263X | 2-2 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 333065.96 | 544676 | -211610.04 | 2012-08-21 | 2015-05-25 | 2012-09-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021264 | EB021264X | 2-4 Pulverizer Roll Wheel Repl | 68113.48 |  | 68113.48 | 100% |  | 278972.93 | 358249 | -79276.07 | 2010-11-01 | 2012-10-22 | 2010-11-01 | 2011-03-15
75081-DE Kentucky Fossil | EB021270 | EB021270X | Replacement 2SR2 Transformer | 0 |  | 0 |  |  | 86017.34 | 119913 | -33895.66 | 2009-11-06 | 2010-10-20 | 2009-12-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021271 | EB021271X | Replace F to G Coal Chute | 223677.89 |  | 223677.89 | 100% |  | 223677.89 | 792558.1 | -568880.21 | 2015-08-28 10:35 | 2016-07-01 | 2015-09-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021275 | EB021275X | Landfill Cover 2010 | 0 |  | 0 |  |  | 3.6082e-16 |  | 3.6082e-16 | 2010-03-04 | 2012-01-31 | 2010-09-01 | 2012-03-31
75081-DE Kentucky Fossil | EB021276 | EB021276X | Replace UAT Bushings | 0 |  | 0 |  |  | 33811.56 | 66133 | -32321.44 | 2011-08-11 | 2013-03-25 | 2011-08-01 | 2012-06-28
75081-DE Kentucky Fossil | EB021277 | EB021277X | Replace 1st Layer SCR Catalyst | 1370077.91 |  | 1370077.91 | 100% |  | 1463751.22 | 1659977 | -196225.78 | 2014-11-04 | 2015-12-31 | 2014-10-01 | 2015-06-30
75081-DE Kentucky Fossil | EB021278 | EB021278X | Repl 6 IDB Fan inlet exp jts | 34352.78 |  | 34352.78 | 100% |  | 295183.81 | 511099 | -215915.19 | 2012-01-26 | 2012-12-01 | 2012-02-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021279 | EB021279X | Replace FGD Transformer 2SR1 | 18105.97 |  | 18105.97 | 100% |  | 74121.84 | 108674 | -34552.16 | 2009-07-31 | 2010-06-08 | 2009-07-01 | 2009-10-20
75081-DE Kentucky Fossil | EB021280 | EB021280X | IT Capital Project Support | 34161.23 |  | 34161.23 | 100% |  | 146397.99 | 109201 | 37196.99 | 2009-08-20 | 2013-03-30 | 2009-08-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021282 | EB021282X | Repl No 2 Boiler Room Sump Pump | 28623.12 |  | 28623.12 | 100% |  | 119075.66 | 170756 | -51680.34 | 2010-03-10 | 2011-06-10 | 2010-03-01 | 2010-12-29
75081-DE Kentucky Fossil | EB021283 | EB021283X | Repl FGD Common inlet exp jt | 31337.21 |  | 31337.21 | 100% |  | 174736.05 | 218989 | -44252.95 | 2011-11-09 | 2012-10-26 | 2011-12-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021284 | EB021284X | Repl 3 IDBF Outlet Exp Jts | 173132.81 |  | 173132.81 | 100% |  | 437749.47 | 476977 | -39227.53 | 2013-08-26 | 2014-08-01 | 2013-09-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021286 | EB021286X | Replace RH Attemperator Line | 0 |  | 0 |  |  | 237323.9 | 354424 | -117100.1 | 2011-08-22 | 2012-06-08 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021291 | EB021291X | Landfill Cover 2012 | -4535.47 |  | -4535.47 | 100% |  | -4467.33 |  | -4467.33 | 2012-03-02 | 2014-12-31 | 2014-04-01 | 2014-03-31
75081-DE Kentucky Fossil | EB021293 | EB021293X | Landfill Cover 2014 | 52098.18 |  | 52098.18 | 100% |  | 52098.18 |  | 52098.18 | 2014-09-24 | 2016-01-31 | 2015-12-01 | 2016-03-31
75081-DE Kentucky Fossil | EB021299 | EB021299X | Replace Abs Module Outlet Duct | 131414.92 |  | 131414.92 | 100% |  | 741932.53 | 1029673 | -287740.47 | 2013-11-18 | 2014-08-01 | 2013-12-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021301 | EB021301X | Replace Radio System | 0 |  | 0 |  |  | 257396.74 | 439629 | -182232.26 | 2010-04-14 | 2011-03-03 | 2010-04-01 | 2010-12-08
75081-DE Kentucky Fossil | EB021306 | EB021306X | 2-6 Pulv Roll Wheel Repl 2014 | 630071.57 |  | 630071.57 | 100% |  | 634822.13 | 564903 | 69919.13 | 2014-11-24 | 2015-08-01 | 2014-12-01 | 2015-06-29
75081-DE Kentucky Fossil | EB021308 | EB021308X | 2-3 Pulv Roll Wheel Repl | 300372.91 |  | 300372.91 | 100% |  | 300372.91 | 780026.82 | -479653.91 | 2015-09-02 14:06 | 2016-06-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021312 | EB021312X | 2-1 Pulv Roll Wheel Repl | 41914.08 |  | 41914.08 | 100% |  | 429845.01 | 581014 | -151168.99 | 2013-09-23 | 2014-12-01 | 2013-10-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021314 | EB021314X | 2-4 Pulv Roll Wheel Repl 2015-2016 | 282902.35 |  | 282902.35 | 100% |  | 282902.35 | 777419.11 | -494516.76 | 2015-09-02 14:16 | 2016-06-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021317 | EB021317X | Replace Station Phone System | 42429.71 |  | 42429.71 | 100% |  | 173656.59 | 256732 | -83075.41 | 2013-06-28 | 2013-12-31 | 2013-07-01 | 2014-01-21
75081-DE Kentucky Fossil | EB021319 | EB021319X | BlrRm Elevator Control Upgrade | 89649.03 |  | 89649.03 | 100% |  | 368231.07 | 312468 | 55763.07 | 2010-10-05 | 2011-09-16 | 2010-11-01 | 2011-05-04
75081-DE Kentucky Fossil | EB021325 | EB021325X | CT Gearbox Replacement 2010 | 0 |  | 0 |  |  | 91028.11 | 134310 | -43281.89 | 2009-09-25 | 2010-08-19 | 2009-09-01 | 2009-12-28
75081-DE Kentucky Fossil | EB021332 | EB021332X | RHO Pendant Replacement | 2672603.03 |  | 2672603.03 | 100% |  | 10381311.76 | 10402876 | -21564.24 | 2012-11-02 | 2015-05-27 | 2012-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021335 | EB021335X | DRFT ELIMIN & HEADER RPLMNT | 0 |  | 0 |  |  | 150713.29 | 240023 | -89309.71 | 2011-11-07 | 2012-09-27 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021336 | EB021336X | CT Bypass Valve Replacement 2016 | 19934.83 |  | 19934.83 | 100% |  | 19934.83 | 410058.61 | -390123.78 | 2015-10-06 11:44 | 2016-08-01 | 2015-10-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021338 | EB021338A | ARO - Cooling Tower Fill | -2697.85 |  | -2697.85 | 100% |  | -301.15 |  | -301.15 | 2010-10-12 | 2013-03-31 | 2012-07-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021351 | EB021351X | Replace Pug Mill Gear Box | 8902.53 |  | 8902.53 | 100% |  | 51452.97 | 66314 | -14861.03 | 2013-12-20 | 2015-03-18 | 2013-12-01 | 2014-03-31
75081-DE Kentucky Fossil | EB021352 | EB021352X | Retube Chiller in Control Room | 38177.74 |  | 38177.74 | 100% |  | 156704.78 | 137419 | 19285.78 | 2010-11-02 | 2011-09-16 | 2010-12-01 | 2011-05-31
75081-DE Kentucky Fossil | EB021353 | EB021353X | NH3 Slip Monitor 1 | 0 |  | 0 |  |  | 266572.2 | 242755 | 23817.2 | 2011-08-12 | 2012-06-19 | 2011-08-01 | 2012-04-27
75081-DE Kentucky Fossil | EB021355 | EB021355X | Replace Cond. Control Valve | 0 |  | 0 |  |  | 188557.17 | 245177 | -56619.83 | 2011-06-06 | 2012-04-16 | 2011-06-01 | 2012-07-20
75081-DE Kentucky Fossil | EB021356 | EB021356X | Replace WSP Dust Collector | 55122.22 |  | 55122.22 | 100% |  | 227631.19 | 133042 | 94589.19 | 2010-11-01 | 2012-05-20 | 2010-12-01 | 2011-11-17
75081-DE Kentucky Fossil | EB021357 | EB021357C | Ash Sluice Pump Soft Starters | 708611.35 |  | 708611.35 | 100% |  | 744301.24 | 649561 | 94740.24 | 2014-11-12 | 2015-10-01 | 2014-11-01 | 2015-11-01
75081-DE Kentucky Fossil | EB021358 | EB021358X | Voltage Regulator Transformers | 0 |  | 0 |  |  | 72696 | 108833 | -36137 | 2010-10-07 | 2011-07-25 | 2010-11-01 | 2011-07-03
75081-DE Kentucky Fossil | EB021362 | EB021362X | New Sulferic Acid System | 0 |  | 0 |  |  | 667594.57 | 654708 | 12886.57 | 2012-08-09 | 2013-08-25 | 2012-08-01 | 2013-06-07
75081-DE Kentucky Fossil | EB021364 | EB021364X | Pugmill Gear Box Replacement | 5361.61 |  | 5361.61 | 100% |  | 19990.69 | 24709 | -4718.31 | 2010-10-07 | 2012-12-31 | 2010-10-01 | 2011-02-04
75081-DE Kentucky Fossil | EB021365 | EB021365X | STORM WATER PIPE REPLACEMENT | 0 |  | 0 |  |  | 426775.84 | 550683 | -123907.16 | 2010-11-02 | 2011-10-12 | 2010-11-01 | 2011-03-10
75081-DE Kentucky Fossil | EB021366 | EB021366X | Replace Step-up Transformer | 0 |  | 0 |  |  | 5838602.22 | 6851486 | -1012883.78 | 2011-02-23 | 2013-04-01 | 2011-03-01 | 2012-07-19
75081-DE Kentucky Fossil | EB021369 | EB021369X | CT Gearbox Oil Filter | 79025.15 |  | 79025.15 | 100% |  | 336402.27 | 216834 | 119568.27 | 2012-11-15 | 2013-10-26 | 2012-11-01 | 2013-09-14
75081-DE Kentucky Fossil | EB021370 | EB021370X | Replace FGD Service Water Line | 13987.16 |  | 13987.16 | 100% |  | 57207.61 | 81196 | -23988.39 | 2011-04-26 | 2011-09-30 | 2011-05-01 | 2011-06-30
75081-DE Kentucky Fossil | EB021373 | EB021373X | WSP Shovel | 103151.69 |  | 103151.69 | 100% |  | 421891.27 | 553812 | -131920.73 | 2012-04-05 | 2013-01-14 | 2012-06-01 | 2012-09-01
75081-DE Kentucky Fossil | EB021375 | EB021375X | UPS Battery Replacement | 153.94 |  | 153.94 | 100% |  | 153.94 | 19621.6 | -19467.66 | 2015-11-17 11:24 | 2016-07-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021378 | EB021378X | Repl Flyash and Lime Scales | 0 |  | 0 |  |  | 212614.91 | 283188 | -70573.09 | 2012-08-21 | 2013-07-22 | 2012-09-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021380 | EB021380X | Ash Pond Modification | 39658.55 |  | 39658.55 | 100% |  | 162796.25 | 328913 | -166116.75 | 2012-08-02 | 2013-10-26 | 2012-09-01 | 2013-03-14
75081-DE Kentucky Fossil | EB021381 | EB021381X | Replace FGD Sludge Tank | 0 |  | 0 |  |  | 682213.74 | 758918 | -76704.26 | 2012-01-17 | 2012-11-30 | 2012-02-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021383 | EB021383X | Unit Control Simulator | 559720.09 |  | 559720.09 | 100% |  | 1573627.1 | 1656726 | -83098.9 | 2012-12-27 | 2016-12-21 | 2012-12-01 | 2017-03-15
75081-DE Kentucky Fossil | EB021384 | EB021384X | 2-2 Precip Inlet Exp Jnt Repl | 188698.16 |  | 188698.16 | 100% |  | 456395 | 307763 | 148632 | 2013-10-31 | 2014-06-01 | 2013-12-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021387 | EB021387X | East Bend EAM | 0 |  | 0 |  |  | 544126.33 | 788588.88 | -244462.55 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2010-01-31
75081-DE Kentucky Fossil | EB021394 | EB021394X | Repl Filt Overflow Sumps Pumps | 8640.69 |  | 8640.69 | 100% |  | 37089.83 | 47672 | -10582.17 | 2011-11-29 | 2012-11-27 | 2011-12-01 | 2012-03-31
75081-DE Kentucky Fossil | EB021395 | EB021395X | Repl Emer Sump Pump Motors | 0 |  | 0 |  |  | 10699.04 | 18509 | -7809.96 | 2011-11-09 | 2012-10-10 | 2011-12-01 | 2012-02-18
75081-DE Kentucky Fossil | EB021396 | EB021396X | REPL PUG MILL GEAR BOX | 0 |  | 0 |  |  | 21919.94 | 42879 | -20959.06 | 2011-11-07 | 2012-10-08 | 2011-12-01 | 2012-01-14
75081-DE Kentucky Fossil | EB021397 | EB021397X | SB Air Compressor Cooler | 5029.03 |  | 5029.03 | 100% |  | 36018.83 | 40171 | -4152.17 | 2011-12-02 | 2012-11-14 | 2011-12-01 | 2012-01-25
75081-DE Kentucky Fossil | EB021398 | EB021398X | 2LHIM Transformer Replacement | 33169.15 |  | 33169.15 | 100% |  | 93577.42 | 101667 | -8089.58 | 2013-07-15 | 2016-06-30 | 2013-07-01 | 2016-08-06
75081-DE Kentucky Fossil | EB021402 | EB021402X | FGD HVAC Replacement | 9958.2 |  | 9958.2 | 100% |  | 46909.15 | 60520 | -13610.85 | 2012-07-13 | 2012-12-31 | 2012-09-01 | 2012-12-28
75081-DE Kentucky Fossil | EB021411 | EB021411X | Filtrate Return Pumps | 0 |  | 0 |  |  | 75905.84 | 101139 | -25233.16 | 2012-10-22 | 2013-04-26 | 2012-11-01 | 2013-08-23
75081-DE Kentucky Fossil | EB021412 | EB021412X | Install 3rd Layer SCR Catalyst | 0 |  | 0 |  |  | 536263.68 | 884933 | -348669.32 | 2013-05-16 | 2013-12-31 | 2013-05-01 | 2013-07-19
75081-DE Kentucky Fossil | EB021414 | EB021414X | Replace Filtered Water Tank | 76708.48 |  | 76708.48 | 100% |  | 445700.13 | 486876 | -41175.87 | 2013-09-23 | 2014-08-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021416 | EB021416X | Install 2nd Layer of Catalyst | 377568.06 |  | 377568.06 | 100% |  | 377568.06 | 1636134.79 | -1258566.73 | 2015-10-30 09:26 | 2016-08-31 | 2015-11-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021417 | EB021417X | Station Cameras | 76295.8 |  | 76295.8 | 100% |  | 341806.24 | 248735 | 93071.24 | 2013-02-15 | 2015-01-15 | 2013-03-01 | 2014-12-31
75081-DE Kentucky Fossil | EB021418 | EB021418X | SA Preheat Coils | 53400.39 |  | 53400.39 | 100% |  | 386370.97 | 503698 | -117327.03 | 2013-02-15 | 2014-05-30 | 2013-02-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021419 | EB021419X | Fuel Oil Tank Dike Liner Repl | 17951.02 |  | 17951.02 | 100% |  | 73436.19 | 109522 | -36085.81 | 2012-09-04 | 2012-12-31 | 2012-09-01 | 2013-02-06
75081-DE Kentucky Fossil | EB021420 | EB021420X | CBU MCC HVAC Replacement | 733.84 |  | 733.84 | 100% |  | 9181.45 | 26482 | -17300.55 | 2012-08-21 | 2013-03-30 | 2012-11-01 | 2013-03-07
75081-DE Kentucky Fossil | EB021423 | EB021423X | Precipitator Upgrade 2014 | 2974363.31 |  | 2974363.31 | 100% |  | 9622912.66 | 6273521 | 3349391.66 | 2013-05-29 | 2014-08-05 | 2013-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021424 | EB021424X | 2-2 SB Air Compressor Cooler | 0 |  | 0 |  |  | 29719.28 | 44705 | -14985.72 | 2012-08-10 | 2013-02-28 | 2012-08-01 | 2012-06-09
75081-DE Kentucky Fossil | EB021425 | EB021425X | Landfill Articulating Trucks | 0 |  | 0 |  |  | 768539.66 | 1205473 | -436933.34 | 2012-08-08 | 2012-11-30 | 2012-08-01 | 2012-11-30
75081-DE Kentucky Fossil | EB021426 | EB021426X | D6 Dozer | 83278.51 |  | 83278.51 | 100% |  | 340609.78 | 403577 | -62967.22 | 2012-08-08 | 2012-11-30 | 2012-09-01 | 2012-12-11
75081-DE Kentucky Fossil | EB021427 | EB021427X | CEMS Hg Umbilical Replacement | 28011.11 |  | 28011.11 | 100% |  | 114565.63 | 126175 | -11609.37 | 2012-08-31 | 2013-02-28 | 2012-09-01 | 2013-04-17
75081-DE Kentucky Fossil | EB021431 | EB021431X | Ash Sluice Pump Seal Water Pipe | 0 |  | 0 |  |  | 34889.91 | 37855 | -2965.09 | 2012-11-28 | 2013-11-04 | 2012-12-01 | 2013-03-28
75081-DE Kentucky Fossil | EB021432 | EB021432X | Emissions Particulate Monitor | 21592.21 |  | 21592.21 | 100% |  | 88312.33 | 173610 | -85297.67 | 2013-02-04 | 2013-05-31 | 2013-02-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021433 | EB021433X | Purchase Dredge for Pond Cleaning | -2604.25 |  | -2604.25 | 100% |  | 165307.31 | 256984 | -91676.69 | 2013-05-06 | 2013-12-21 | 2013-07-01 | 2014-01-31
75081-DE Kentucky Fossil | EB021434 | EB021434X | EB2 Precipitator T/R Sets | 13882.26 |  | 13882.26 | 100% |  | 66053.86 | 134425 | -68371.14 | 2013-04-03 | 2013-12-31 | 2013-04-01 | 2013-08-03
75081-DE Kentucky Fossil | EB021436 | EB021436X | Replace LBU Roof | 7035.56 |  | 7035.56 | 100% |  | 28775.5 | 33601 | -4825.5 | 2013-05-06 | 2013-12-31 | 2013-05-01 | 2013-07-15
75081-DE Kentucky Fossil | EB021438 | EB021438X | Replace IP Turbine Blades | 452312.03 |  | 452312.03 | 100% |  | 1797631.05 | 1142289 | 655342.05 | 2013-08-05 | 2014-12-05 | 2013-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021443 | EB021443X | LBU Hold & Close Drive Replacement | 114435.85 |  | 114435.85 | 100% |  | 358125.71 | 478370 | -120244.29 | 2013-08-27 | 2014-10-01 | 2013-10-01 | 2014-09-29
75081-DE Kentucky Fossil | EB021444 | EB021444X | Replace 1-2 SW Strainer | 184786.86 |  | 184786.86 | 100% |  | 184786.86 | 235286 | -50499.14 | 2014-12-19 | 2015-10-01 | 2015-04-01 | 2015-08-22
75081-DE Kentucky Fossil | EB021446 | EB021446X | Replace Lining in WSP Sludge Tank | 152071.87 |  | 152071.87 | 100% |  | 372068.08 | 315985 | 56083.08 | 2013-09-23 | 2014-07-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021448 | EB021448X | SSHO Partial Pendants - Mini Panels | 741310.53 |  | 741310.53 | 100% |  | 2375562.06 | 2712013 | -336450.94 | 2013-10-17 | 2014-12-31 | 2013-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021456 | EB021456X | SmartGen Installation at East Bend | 1657764.3 |  | 1657764.3 | 100% |  | 1657764.3 | 4503175.79 | -2845411.49 | 2015-01-09 | 2017-12-31 | 2015-01-01
75081-DE Kentucky Fossil | EB021457 | EB021457X | Paving Eastside Parking Lot | 0 |  | 0 |  |  | 65121.93 | 101930 | -36808.07 | 2013-08-27 | 2013-12-31 | 2013-08-01 | 2013-10-22
75081-DE Kentucky Fossil | EB021459 | EB021459X | Data Network Upgrade | 16648.25 |  | 16648.25 | 100% |  | 74028.94 | 97480 | -23451.06 | 2013-08-27 | 2015-03-31 | 2013-12-01 | 2014-09-30
75081-DE Kentucky Fossil | EB021460 | EB021460X | PCME PM CEMS Monitor | 187630.8 |  | 187630.8 | 100% |  | 290389.77 | 308070 | -17680.23 | 2014-02-20 | 2015-03-31 | 2014-05-01 | 2015-03-12
75081-DE Kentucky Fossil | EB021461 | EB021461X | Landfill Haul Road Drainage System | 10715.39 |  | 10715.39 | 100% |  | 72810.32 | 104270 | -31459.68 | 2013-09-26 | 2014-07-31 | 2013-12-01 | 2014-06-01
75081-DE Kentucky Fossil | EB021462 | EB021462X | 125 DC Station Battery 2 | 222.68 |  | 222.68 | 100% |  | 59567.58 | 93016 | -33448.42 | 2013-10-28 | 2014-03-31 | 2013-11-01 | 2014-06-23
75081-DE Kentucky Fossil | EB021463 | EB021463X | 2 Sec Air Water Sup Preheat Coils | 16074.4 |  | 16074.4 | 100% |  | 52343.66 | 70250 | -17906.34 | 2014-01-08 | 2014-03-31 | 2014-11-01 | 2014-02-22
75081-DE Kentucky Fossil | EB021465 | EB021465X | Replace 2SR-7 Transformer | 20189.11 |  | 20189.11 | 100% |  | 57245.3 | 58771 | -1525.7 | 2014-03-06 | 2015-03-31 | 2014-05-01 | 2014-08-20
75081-DE Kentucky Fossil | EB021466 | EB021466X | 2-2 SBAC Coolers and Controls | 94212.58 |  | 94212.58 | 100% |  | 287565.77 | 338329 | -50763.23 | 2014-05-27 | 2014-08-31 | 2014-05-01 | 2014-09-27
75081-DE Kentucky Fossil | EB021468 | EB021468X | Isophase Bus Wall Bushings | 156776.27 |  | 156776.27 | 100% |  | 366324.33 | 302597 | 63727.33 | 2014-05-23 | 2014-08-31 | 2014-05-01 | 2014-08-20
75081-DE Kentucky Fossil | EB021469 | EB021469X | Cooling Tower Motor Platforms | 13364.98 |  | 13364.98 | 100% |  | 51465.06 | 106326 | -54860.94 | 2014-05-27 | 2014-08-31 | 2014-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021470 | EB021470X | Data Network Upgrade | 25383.72 |  | 25383.72 | 100% |  | 82724.85 | 142704 | -59979.15 | 2014-10-23 | 2015-09-02 | 2014-11-01 | 2014-11-28
75081-DE Kentucky Fossil | EB021471 | EB021471X | Boiler Room Exhaust Fan Blades Set | 16933.03 |  | 16933.03 | 100% |  | 37489.51 | 52167 | -14677.49 | 2014-09-04 | 2014-12-23 | 2014-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021476 | EB021476X | Rep Penthouse Front Wall Insulation | 33875.16 |  | 33875.16 | 100% |  | 33875.16 | 101816 | -67940.84 | 2015-03-09 08:14 | 2015-07-01 | 2015-03-01 | 2015-06-29
75081-DE Kentucky Fossil | EB021480 | EB021480X | Mercury CEMS | 142155.88 |  | 142155.88 | 100% |  | 313179.55 | 476412 | -163232.45 | 2014-09-04 | 2015-03-06 | 2014-09-01 | 2015-04-09
75081-DE Kentucky Fossil | EB021482 | EB021482X | CT Gearbox and Fan Blades 2-10 | 19016.4 |  | 19016.4 | 100% |  | 66623.58 | 78897 | -12273.42 | 2014-09-04 | 2014-08-31 | 2014-09-01 | 2014-11-20
75081-DE Kentucky Fossil | EB021483 | EB021483X | Remove 1st Layer SCR Catalyst | -5.6843e-14 |  | -5.6843e-14 | 100% |  | -5.6843e-14 |  | -5.6843e-14 | 2014-09-25 | 2014-12-31 | 2015-02-01 | 2014-12-08
75081-DE Kentucky Fossil | EB021486 | EB021486X | Replace Ash Sluice Pump Motor | 15945.05 |  | 15945.05 | 100% |  | 52516.02 | 55459 | -2942.98 | 2014-11-07 | 2015-06-30 | 2014-11-01 | 2015-03-16
75081-DE Kentucky Fossil | EB021487 | EB021487X | Cake Transfer Belt | 4886.08 |  | 4886.08 | 100% |  | 18589.81 | 20374 | -1784.19 | 2014-11-04 | 2014-11-28 | 2014-11-01 | 2015-01-21
75081-DE Kentucky Fossil | EB021488 | EB021488X | 30 Day Lime Silo Elec Bldg Roof | 1884.54 |  | 1884.54 | 100% |  | 6189.62 | 7235 | -1045.38 | 2014-11-04 | 2014-12-01 | 2014-11-01 | 2015-02-03
75081-DE Kentucky Fossil | EB021489 | EB021489X | 2-2 Fly Ash Silo to Silo Blowers | 1016792.46 |  | 1016792.46 | 100% |  | 1076855.06 | 1072612 | 4243.06 | 2014-12-08 | 2016-08-31 | 2014-12-01 | 2016-09-23
75081-DE Kentucky Fossil | EB021490 | EB021490X | SCR Condensate-Storm Sewer Improve | 680928.37 |  | 680928.37 | 100% |  | 680928.37 | 700221.53 | -19293.16 | 2015-01-08 | 2016-02-28 | 2015-01-01 | 2016-02-12
75081-DE Kentucky Fossil | EB021491 | EB021491X | Purchase Landfill Property | 1223446.78 |  | 1223446.78 | 100% |  | 1223446.78 | 1100611 | 122835.78 | 2015-01-08 | 2015-12-31 | 2015-10-01 | 2016-02-29
75081-DE Kentucky Fossil | EB021492 | EB021492X | TriState EB Parcels PP 29711 29690 | 56880.46 |  | 56880.46 | 100% |  | 595682.72 | 586108 | 9574.72 | 2014-12-31 | 2014-12-31 | 2014-12-01 | 2015-03-31
75081-DE Kentucky Fossil | EB021494 | EB021494X | Mixer Discharge Belt | 6127.62 |  | 6127.62 | 100% |  | 6127.62 | 9089 | -2961.38 | 2015-03-11 07:09 | 2015-06-30 | 2015-04-01 | 2015-06-07
75081-DE Kentucky Fossil | EB021495 | EB021495X | 2-1 SBAC Cooler Replacement | 85804.78 |  | 85804.78 | 100% |  | 85804.78 | 153807 | -68002.22 | 2015-03-09 10:19 | 2015-02-28 | 2015-04-01 | 2014-06-01
75081-DE Kentucky Fossil | EB1922 | EB02CTA13 | Cost to Achieve 2013 | 1725.9 |  | 1725.9 | 100% |  | 7729.1 | 9500 | -1770.9 | 2013-10-03 | 2014-12-31 | 2013-12-01 | 2014-03-31
75081-DE Kentucky Fossil | EB0822 | EB0822X | EBS U2 REPLACE CARDOX CONTROLS | 0 |  | 0 |  |  | 442775.02 | 599080 | -156304.98 | 2011-10-07 | 2012-08-24 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB1152 | EB1152X | FGD Landfill Conc Spillway | 0 |  | 0 |  |  | 62419.41 | 62578 | -158.59 | 2008-09-02 | 2009-03-31 | 2008-11-01 | 2008-12-31
75081-DE Kentucky Fossil | EB200531 | EB200531X | Thickener Tunnel Emerg Sump Pump | 33112.12 |  | 33112.12 | 100% |  | 143341.64 | 209037 | -65695.36 | 2008-09-02 | 2011-04-30 | 2008-11-01 | 2011-04-25
75081-DE Kentucky Fossil | EB201206 | EB201206X | Replace lower front wall Slope tube | 1639285.51 |  | 1639285.51 | 100% |  | 4419810.52 | 4190562 | 229248.52 | 2009-01-26 | 2012-07-10 | 2009-07-01 | 2012-07-15
75081-DE Kentucky Fossil | EB201220 | EB201220X | Cooling Tower Motor Replace 08 | 0 |  | 0 |  |  | 94484.15 | 128010 | -33525.85 | 2008-07-09 | 2009-07-31 | 2008-08-01 | 2009-03-22
75081-DE Kentucky Fossil | EB201259 | EB201259X | Replace 1 CT Fan Assembly | 0 |  | 0 |  |  | 33498.15 | 83477 | -49978.85 | 2010-02-02 | 2011-01-04 | 2010-02-01 | 2010-08-14
75081-DE Kentucky Fossil | EB201333 | EB201333X | Retube Spare Hydrogen Cooler | 0 |  | 0 |  |  | 69629.15 | 120129 | -50499.85 | 2010-03-18 | 2010-12-01 | 2010-03-01 | 2010-08-07
75081-DE Kentucky Fossil | EB201341 | EB201341X | FGD Lab | 0 |  | 0 |  |  | 23931.67 | 26315 | -2383.33 | 2010-10-19 | 2012-08-14 | 2010-11-01 | 2011-03-08
75081-DE Kentucky Fossil | EB201344 | EB201344X | HVG Neutral Phase Bushing | 91662.37 |  | 91662.37 | 100% |  | 204035.6 | 283041 | -79005.4 | 2011-11-27 | 2013-04-24 | 2011-12-01 | 2012-07-20
75081-DE Kentucky Fossil | EB201348 | EB201348X | FGD Controls Upgrade | 1088163.29 |  | 1088163.29 | 100% |  | 4503399.54 | 3970493 | 532906.54 | 2010-12-20 | 2013-04-26 | 2010-12-01 | 2012-07-29
75081-DE Kentucky Fossil | EB201357 | EB201357X | Pulverizer Gbx Replace 1 of 6 | 75131.62 |  | 75131.62 | 100% |  | 309079.48 | 365449 | -56369.52 | 2012-02-17 | 2012-12-03 | 2012-02-01 | 2012-07-20
75081-DE Kentucky Fossil | EB201365 | EB201365X | Cooling Tower Breakr Repl PH1 | 0 |  | 0 |  |  | 222532.07 | 291225 | -68692.93 | 2010-02-15 | 2011-10-27 | 2010-03-01 | 2010-08-17
75081-DE Kentucky Fossil | EB201367 | EB201367X | CT BREAKER PHASE 2 | 0 |  | 0 |  |  | 404446.52 | 596961 | -192514.48 | 2011-10-20 | 2012-11-30 | 2011-11-01 | 2012-07-29
75081-DE Kentucky Fossil | EB201370 | EB201370X | Install Stack Lining | 1989552.99 |  | 1989552.99 | 100% |  | 8580311.74 | 10360344 | -1780032.26 | 2011-06-06 | 2014-08-01 | 2011-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB201374 | EB201374X | DCS Network Upgrade | 0 |  | 0 |  |  | 839877.54 | 978321 | -138443.46 | 2008-10-06 | 2010-05-24 | 2008-12-01 | 2009-08-25
75081-DE Kentucky Fossil | EB2922 | EB2922X | EB2-3rd Catalyst Bed-Addition | 0 |  | 0 |  |  | 1303087.13 | 2585054 | -1281966.87 | 2008-09-29 | 2009-08-20 | 2008-11-01 | 2009-08-29
75081-DE Kentucky Fossil | EBS01210 | EBS01210X | Filtrate Storage Tank Replacement | 184446.66 |  | 184446.66 | 100% |  | 515270.8 | 393318 | 121952.8 | 2013-09-10 | 2014-08-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EBS01212 | EBS01212X | Cooling Tower Gearbox 2009 | 79068.6 |  | 79068.6 | 100% |  | 331650.49 | 273031 | 58619.49 | 2009-02-05 | 2010-12-31 | 2009-02-01 | 2010-09-25
75081-DE Kentucky Fossil | EBS01213 | EBS01213X | Cooling Tower Gearbox 2010 | 0 |  | 0 |  |  | 319633.51 | 435882 | -116248.49 | 2009-04-17 | 2011-03-25 | 2009-05-01 | 2011-01-20
75081-DE Kentucky Fossil | EBS01216 | EBS01216X | Furnace Sidewall Weld Overlay | 0 |  | 0 |  |  | 903384.86 | 1069212 | -165827.14 | 2009-02-05 | 2019-12-01 | 2009-02-01 | 2009-08-15
75081-DE Kentucky Fossil | EBS01243 | EBS01243X | New East Bend Landfill | 6585001.03 |  | 6585001.03 | 100% |  | 6751553.71 | 13966995.52 | -7215441.81 | 2013-11-19 | 2018-06-30 | 2013-12-01
75081-DE Kentucky Fossil | EBS01260 | EBS01260X | Sand Filter for WSP Serv Water | 0 |  | 0 |  |  | 28186.52 | 38177 | -9990.48 | 2008-07-09 | 2009-04-23 | 2008-09-01 | 2009-04-23
75081-DE Kentucky Fossil | EBS01261 | EBS01261X | Replace CBU Chains | 0 |  | 0 |  |  | 121020.66 | 181378 | -60357.34 | 2008-10-07 | 2010-08-15 | 2008-12-01 | 2010-08-17
75081-DE Kentucky Fossil | EBS01264 | EBS01264X | Filtered Water Pmp Replacement | 0 |  | 0 |  |  | 30048.92 | 50704 | -20655.08 | 2008-07-09 | 2009-09-21 | 2008-09-01 | 2009-05-27
75081-DE Kentucky Fossil | EBS01266 | EBS01266X | Repl Lime Conv Metal Detector | 18332.61 |  | 18332.61 | 100% |  | 48043.87 | 87248 | -39204.13 | 2013-08-01 | 2015-12-31 | 2013-09-01 | 2015-08-13
75081-DE Kentucky Fossil | EBS01277 | EBS01277X | ASH HOPPER DOWNCOMER REPLACEMT | 0 |  | 0 |  |  | 292221.11 | 358810 | -66588.89 | 2011-10-05 | 2012-10-01 | 2011-10-01 | 2012-07-20
75081-DE Kentucky Fossil | EBS01280 | EBS01280X | Deep Well Addition | 0 |  | 0 |  |  | 560388.55 | 530543 | 29845.55 | 2008-09-05 | 2010-01-31 | 2008-11-01 | 2010-02-05
75081-DE Kentucky Fossil | EBS01290 | EBS01290X | REPLACE CIRC PIP SAC ANODES | 44991.26 |  | 44991.26 | 100% |  | 184400.28 | 152815 | 31585.28 | 2011-10-07 | 2012-08-21 | 2011-10-01 | 2012-07-20
75081-DE Kentucky Fossil | EBS01296 | EBS01296X | Demin Acid Tank | 180359.71 |  | 180359.71 | 100% |  | 180359.71 | 348320.7 | -167960.99 | 2015-10-19 11:48 | 2016-09-30 | 2015-11-01 | 2016-10-08
75081-DE Kentucky Fossil | EBS01315 | EBS01315X | Replace 2-2 WS Strainer | 46119.48 |  | 46119.48 | 100% |  | 189703.05 | 127793 | 61910.05 | 2009-04-22 | 2010-11-23 | 2009-07-01 | 2010-12-02
75081-DE Kentucky Fossil | EBS01317 | EBS01317X | Cooling Tower Motor Replace-09 | 0 |  | 0 |  |  | 175068.81 | 264223 | -89154.19 | 2009-06-23 | 2011-02-28 | 2009-06-01 | 2010-07-01
75081-DE Kentucky Fossil | EBS01319 | EBS01319X | Cooling Tower Motor Repl | 0 |  | 0 |  |  | 165913.64 | 282474 | -116560.36 | 2010-03-04 | 2011-12-31 | 2010-03-01 | 2011-02-05
75081-DE Kentucky Fossil | EBS01322 | EBS01322X | Replace RAT Bushings | 0 |  | 0 |  |  | 122951.63 | 195719 | -72767.37 | 2010-08-17 | 2011-09-30 | 2010-09-01 | 2011-07-14
75081-DE Kentucky Fossil | EBS01324 | EBS01324X | Bottom Turbine Oil Cooler | 37027.7 |  | 37027.7 | 100% |  | 151889.36 | 373255 | -221365.64 | 2008-11-11 | 2009-10-07 | 2009-02-01 | 2009-08-20
75081-DE Kentucky Fossil | EBS01328 | EBS01328X | Retire Turbine Doghouse | -1.83 |  | -1.83 | 100% |  | 1.2434e-14 | 7753 | -7753 | 2008-09-02 | 2008-10-31 | 2008-10-01 | 2009-03-01
75081-DE Kentucky Fossil | EBS01330 | EBS01330X | Replace Service Building Roof | 183032.62 |  | 183032.62 | 100% |  | 183032.62 | 249310 | -66277.38 | 2015-04-16 13:58 | 2015-12-01 | 2015-07-01 | 2015-11-13
75081-DE Kentucky Fossil | EBS01340 | EBS01340X | Replace Coal Handling Controls | 646395.33 |  | 646395.33 | 100% |  | 2034071.32 | 2246909 | -212837.68 | 2013-07-30 | 2014-12-31 | 2013-07-01 | 2014-09-29
75081-DE Kentucky Fossil | EBS01343 | EBS01343X | REPL ABS Pump Brkr Phase I | 0 |  | 0 |  |  | 182983.51 | 304495 | -121511.49 | 2012-11-22 | 2013-10-01 | 2012-12-01 | 2013-07-29
75081-DE Kentucky Fossil | EBS01344 | EBS01344X | Repl ABS Pump Brkrs Phase II | 47315.41 |  | 47315.41 | 100% |  | 197243.67 | 301066 | -103822.33 | 2012-11-23 | 2013-10-01 | 2012-12-01 | 2013-07-29
75081-DE Kentucky Fossil | EBS01349 | EBS01349X | Install CBU Drainage System | 0 |  | 0 |  |  | 97343.1 | 122373 | -25029.9 | 2008-09-02 | 2009-03-31 | 2008-10-01 | 2009-03-19
75081-DE Kentucky Fossil | EBS01352 | EBS01352X | Repl Emergency Pond Pumps | 82690.96 |  | 82690.96 | 100% |  | 380231.98 | 269096 | 111135.98 | 2012-08-31 | 2014-05-22 | 2012-09-01 | 2013-11-30
75081-DE Kentucky Fossil | EBS01356 | EBS01356X | Replace FGD Common Outlet Duct | 0 |  | 0 |  |  | 1184558.04 | 2703003 | -1518444.96 | 2008-09-19 | 2012-07-10 | 2008-10-01 | 2012-07-13
75081-DE Kentucky Fossil | EBS01364 | EBS01364X | SAH and PAH Gas Outlet Duct platfor | 0 |  | 0 |  |  | 31229.62 | 46278 | -15048.38 | 2010-09-16 | 2011-08-22 | 2010-11-01 | 2011-04-13
75081-DE Kentucky Fossil | EBS01374 | EBS01374X | REPLACE SEWAGE TREATMENT PLANT | 0 |  | 0 |  |  | 219250.96 | 294765 | -75514.04 | 2011-10-20 | 2013-02-28 | 2011-12-01 | 2013-03-28
75081-DE Kentucky Fossil | EBS01375 | EBS01375X | Rplc Transfer Tower Fire Det Syst | 49444.97 |  | 49444.97 | 100% |  | 203052.76 | 168413 | 34639.76 | 2012-11-21 | 2013-11-06 | 2012-12-01 | 2013-07-20
75081-DE Kentucky Fossil | EBS01376 | EBS01376X | FGD plenum PIT purge system | 12904.87 |  | 12904.87 | 100% |  | 53794.53 | 31210 | 22584.53 | 2009-04-14 | 2010-08-30 | 2009-04-01 | 2010-08-17
75081-DE Kentucky Fossil | EBS01379 | EBS01379X | Install New Trona Blower | 0 |  | 0 |  |  | 95083.85 | 32034 | 63049.85 | 2008-09-02 | 2009-11-01 | 2008-11-01 | 2009-12-03
75081-DE Kentucky Fossil | EBS01382 | EBS01382X | West Landfill Monitoring Wells | 44890.43 |  | 44890.43 | 100% |  | 195449.12 | 173717 | 21732.12 | 2008-08-24 | 2012-09-30 | 2008-11-01 | 2012-08-31
75081-DE Kentucky Fossil | EBS01383 | EBS01383X | Replace CEMS Shelter and DAS | 0 |  | 0 |  |  | 523455.62 | 867260 | -343804.38 | 2008-12-16 | 2009-06-23 | 2008-12-01 | 2009-03-31
75081-DE Kentucky Fossil | NIST1067 | INT1067A | MI P&L Analyzer Software | 334.9 |  | 334.9 | 100% |  | 7559.86 | 8014 | -454.14 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75081-DE Kentucky Fossil | NINT1067 | INT1067C | MI P&L Analyzer Software | 6851.96 |  | 6851.96 | 100% |  | 24397.15 | 27792 | -3394.85 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75081-DE Kentucky Fossil | PCTAIC910 | INT910C | Post Analysis (Genportal Addtl Uses | 109700.8 |  | 109700.8 | 100% |  | 149688.6 | 19037 | 130651.6 | 2014-07-04 | 2015-07-31 | 2014-07-01 | 2016-03-31
75081-DE Kentucky Fossil | MF601200 | MF601200X | SAH Racks & Pinion Gears Repl | 0 |  | 0 |  |  | 66502.26 | 80007 | -13504.74 | 2010-10-01 | 2011-07-06 | 2010-11-01 | 2011-02-21
75081-DE Kentucky Fossil | MU061200 | MU061200X | Replace 6 3 BFP Motor | 0 |  | 0 |  |  | 177463.48 | 185785 | -8321.52 | 2008-09-11 | 2008-12-31 | 2008-09-01 | 2008-12-31
75081-DE Kentucky Fossil | MU061201 | MU061201X | 6-2 BFP Motor Replace Rotor | 0 |  | 0 |  |  | 41284.97 | 76965 | -35680.03 | 2008-11-11 | 2009-05-01 | 2008-12-01 | 2009-06-17
75081-DE Kentucky Fossil | MU061236 | MU061236X | Exhauster Fan Replacement | 0 |  | 0 |  |  | 34972 | 43359 | -8387 | 2010-05-10 | 2010-09-30 | 2010-06-01 | 2010-06-24
75081-DE Kentucky Fossil | MU061238 | MU061238X | replace 6-1 ID fan motor | 0 |  | 0 |  |  | 211104.15 | 279120 | -68015.85 | 2010-05-07 | 2010-12-31 | 2010-06-01 | 2010-07-01
75081-DE Kentucky Fossil | MU061240 | MU061240X | FWH Safety Relief Tank | 0 |  | 0 |  |  | 54664.24 | 89889 | -35224.76 | 2010-10-18 | 2011-07-29 | 2010-11-01 | 2011-02-19
75081-DE Kentucky Fossil | MU061241 | MU061241X | CO2 Analyzer Replacement | 0 |  | 0 |  |  | 10716.44 | 21380 | -10663.56 | 2010-11-09 | 2012-11-24 | 2010-12-01 | 2011-05-10
75081-DE Kentucky Fossil | MU061249 | MU061249X | Miami Fort U6 EAM | 0 |  | 0 |  |  | 205409.1 | 204448.97 | 960.13 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2011-11-30
75081-DE Kentucky Fossil | MU601212 | MU601212X | Operator Console Replacement | 0 |  | 0 |  |  | 504274.86 | 513688 | -9413.14 | 2010-02-02 | 2011-03-31 | 2010-02-01 | 2011-02-21
75081-DE Kentucky Fossil | MU601236 | MU601236X | Fire Detection Sys Install | 0 |  | 0 |  |  | 100337.73 | 122554 | -22216.27 | 2009-03-03 | 2009-12-22 | 2009-03-01 | 2009-09-05
75081-DE Kentucky Fossil | MU601239 | MU601239A | Asbestos Abatement Replacement | 1422.43 |  | 1422.43 | 100% |  | 41005.04 |  | 41005.04 | 2009-05-06 | 2014-12-31 | 2009-05-01 | 2015-03-31
75081-DE Kentucky Fossil | FPCTAITKY | PCTAI1402 | Consolidated Fuels Mgt Pltfrm KY PH | 0 |  | 0 |  |  | 43062.05 | 62769.7 | -19707.65 | 2013-12-12 | 2013-03-31 | 2013-12-01 | 2013-03-31
75081-DE Kentucky Fossil | FPCTAITMF | PCTAI1403 | Consolidated Fuels Mgmt Pltfrm MF P | 0 |  | 0 |  |  | 17072.65 | 17052.43 | 20.22 | 2013-12-12 | 2013-03-31 | 2013-12-01 | 2013-03-31
75081-DE Kentucky Fossil | PCTAIT31 | PCTAI31 | PGO Long Range Planning Tool | 34385.39 |  | 34385.39 | 100% |  | 76605 | 16319 | 60286 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081-DE Kentucky Fossil | PCTAIT31 | PCTAI31J | PGO Long Range Planning Tool | 20.36 |  | 20.36 | 100% |  | 1016.93 | 60069 | -59052.07 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081-DE Kentucky Fossil | PCTAITF2 | PCTAITH21 | INT164 Hardware | 1036.12 |  | 1036.12 | 100% |  | 4825.93 | 31034 | -26208.07 | 2014-07-14 | 2016-02-29 | 2014-09-01 | 2016-05-31
75081-DE Kentucky Fossil | PCTAITF2 | PCTAITS21 | INT164 Software | 206029.13 |  | 206029.13 | 100% |  | 279806.69 | 219741 | 60065.69 | 2014-07-14 | 2016-02-29 | 2014-08-01 | 2016-05-31
75081-DE Kentucky Fossil | EBS01204 | REBS01204 | EBS-Landfill Cover | 0 |  | 0 |  |  | 246.3 |  | 246.3 | 2007-03-21 | 2010-04-30 | 2008-10-01 | 2010-04-30
75081-DE Kentucky Fossil | EBS01312 | REBS01312 | Remove Bypass Ducts | 22070.36 |  | 22070.36 | 100% |  | 90267.94 | 26286 | 63981.94 | 2008-03-12 | 2009-06-30 | 2008-10-01 | 2008-07-26
75082-DE Kentucky Combustion Turbin | PCTAIT137 | AIT13709H | Gas ETRM | -2.51 |  | -2.51 | 100% |  | 222.85 | 390.53 | -167.68 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082-DE Kentucky Combustion Turbin | PCTAIT137 | AIT13709S | Gas ETRM | -292.67 |  | -292.67 | 100% |  | 29470.27 | 28529.33 | 940.94 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21810H | FSO Forecasting Consolidation | 26.12 |  | 26.12 | 100% |  | 522.25 | 1531.43 | -1009.18 | 2014-04-11 | 2015-12-31 | 2014-06-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21810S | FSO Forecasting Consolidation | 88349.25 |  | 88349.25 | 100% |  | 125810.72 | 38170.08 | 87640.64 | 2014-04-11 | 2015-12-31 | 2014-06-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | WD101206 | CWD101206 | WGS CT1 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 19950.75 | 38150 | -18199.25 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-16
75082-DE Kentucky Combustion Turbin | WD201203 | CWD201203 | WGS CT2 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 20220.8 | 38150 | -17929.2 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-16
75082-DE Kentucky Combustion Turbin | WD401203 | CWD401203 | WGS CT4 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 20551.77 | 38150 | -17598.23 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-19
75082-DE Kentucky Combustion Turbin | WD601200 | CWD601200 | WGS CT6 AA Module HVAC Units | 0 |  | 0 |  |  | 25254.92 | 1 | 25253.92 | 2007-10-04 | 2007-12-31 | 2007-12-01 | 2008-07-15
75082-DE Kentucky Combustion Turbin | WD601201 | CWD601201 | WGS CT6 DD Module HVAC Unit | 0 |  | 0 |  |  | 8503.12 | 15228 | -6724.88 | 2007-10-04 | 2007-12-31 | 2007-12-01 | 2008-07-09
75082-DE Kentucky Combustion Turbin | WDC01201 | CWDC01201 | WGS CT1-6 CEMS XML EDR Upgrade | 0 |  | 0 |  |  | 69278.98 | 92169 | -22890.02 | 2008-02-06 | 2009-10-27 | 2008-03-01 | 2009-02-27
75082-DE Kentucky Combustion Turbin | WDC01204 | CWDC01204 | WGS RO ANALYZER REPLACEMENT | 0 |  | 0 |  |  | 27399.42 | 46944 | -19544.58 | 2007-11-14 | 2008-06-21 | 2007-12-01 | 2008-05-07
75082-DE Kentucky Combustion Turbin | WDC01209 | CWDC01209 | INSTALL SYNC CHECK RELAY | 0 |  | 0 |  |  | 5782.47 | 46586 | -40803.53 | 2008-03-06 | 2009-05-11 | 2008-04-01 | 2009-04-01
75082-DE Kentucky Combustion Turbin | WG0244 | CWG0244 | WGS-CT4 Major C Overhaul | 0 |  | 0 |  |  | 6943543.25 | 7736194 | -792650.75 | 2007-08-05 | 2009-04-15 | 2007-12-01 | 2009-05-16
75082-DE Kentucky Combustion Turbin | WGS01205 | CWGS01205 | Security Camera System | 0 |  | 0 |  |  | 19811.72 | 2 | 19809.72 | 2007-01-04 | 2007-06-30 | 2007-01-01 | 2007-11-30
75082-DE Kentucky Combustion Turbin | WD201202 | D1487 | WGS-CT 24V Repl Battery Bank | 0 |  | 0 |  |  | 8047.88 | 16611 | -8563.12 | 2007-08-26 | 2008-03-31 | 2007-11-01 | 2008-02-26
75082-DE Kentucky Combustion Turbin | NINT1067 | INT1067C | MI P&L Analyzer Software | 898.43 |  | 898.43 | 100% |  | 20241.9 | 21400 | -1158.1 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75082-DE Kentucky Combustion Turbin | PCTAIC910 | INT910C | Post Analysis (Genportal Addtl Uses | 67117.2 |  | 67117.2 | 100% |  | 93323.41 | 53958 | 39365.41 | 2014-07-04 | 2015-07-31 | 2014-07-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT31 | PCTAI31 | PGO Long Range Planning Tool | 17047.44 |  | 17047.44 | 100% |  | 43066.58 | 46253 | -3186.42 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75082-DE Kentucky Combustion Turbin | PCTAITF2 | PCTAITH21 | INT164 Hardware | 800.22 |  | 800.22 | 100% |  | 3826.43 | 24784 | -20957.57 | 2014-07-14 | 2016-02-29 | 2014-09-01 | 2016-05-31
75082-DE Kentucky Combustion Turbin | PCTAITF2 | PCTAITS21 | INT164 Software | 277660.63 |  | 277660.63 | 100% |  | 379857.14 | 175487 | 204370.14 | 2014-07-14 | 2016-02-29 | 2014-08-01 | 2016-05-31
75082-DE Kentucky Combustion Turbin | WD011201 | WD011201X | WGS Unit 1 Excitation Controls | 0 |  | 0 |  |  | 204495.39 | 216144 | -11648.61 | 2011-09-20 | 2012-12-31 | 2011-10-01 | 2013-01-05
75082-DE Kentucky Combustion Turbin | WD021200 | WD021200X | CT2 REPLACE PROP. BLR CONTRL | 0 |  | 0 |  |  | 38713.45 | 40215 | -1501.55 | 2008-10-12 | 2008-12-31 | 2008-12-01 | 2009-02-27
75082-DE Kentucky Combustion Turbin | WD021201 | WD021201X | WGS Unit 2 Excitation Controls | 0 |  | 0 |  |  | 206734.46 | 216144 | -9409.54 | 2011-09-20 | 2012-12-31 | 2011-10-01 | 2013-01-16
75082-DE Kentucky Combustion Turbin | WD031200 | WD031200X | WGS No3 Comp Blade Replacement | 0 |  | 0 |  |  | 1050679.03 | 899845 | 150834.03 | 2009-08-18 | 2009-12-31 | 2009-08-01 | 2009-12-23
75082-DE Kentucky Combustion Turbin | WD031201 | WD031201X | WGS Unit 3 Excitation Controls | 0 |  | 0 |  |  | 387366.01 | 214039 | 173327.01 | 2013-01-31 | 2013-12-31 | 2013-02-01 | 2014-01-15
75082-DE Kentucky Combustion Turbin | WD041200 | WD041200X | WGS Unit 4 Excitation Controls | -144249.86 |  | -144249.86 | 100% |  | 223925.11 | 214039 | 9886.11 | 2013-02-07 | 2014-04-30 | 2013-02-01 | 2014-01-15
75082-DE Kentucky Combustion Turbin | WD051202 | WD051202X | WGS Unit 5 Excitation Controls | 18854.56 |  | 18854.56 | 100% |  | 279593.75 | 217275 | 62318.75 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082-DE Kentucky Combustion Turbin | WD061200 | WD061200X | WGS Unit 6 Excitation Controls | 16054.55 |  | 16054.55 | 100% |  | 288953.6 | 220214 | 68739.6 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082-DE Kentucky Combustion Turbin | WD061203 | WD061203X | WGS- U6 Compressor Blade Replc | 0 |  | 0 |  |  | 349669.18 | 2097039 | -1747369.82 | 2012-05-30 | 2012-12-31 | 2012-06-01 | 2012-09-29
75082-DE Kentucky Combustion Turbin | WD101200 | WD101200X | WGS-CT1 AA Module HVAC Units | 0 |  | 0 |  |  | 66542.99 | 33119 | 33423.99 | 2013-08-18 | 2015-04-25 | 2013-12-01 | 2014-03-16
75082-DE Kentucky Combustion Turbin | WD101201 | WD101201X | WGS-CT1 DD Module HVAC Unit | 0 |  | 0 |  |  | 29396.05 | 14963 | 14433.05 | 2013-08-18 | 2015-05-27 | 2013-12-01 | 2014-03-16
75082-DE Kentucky Combustion Turbin | WD101209 | WD101209X | WGS CT 1 Overhaul #2 | 0 |  | 0 |  |  | 3145560.71 | 9754682 | -6609121.29 | 2011-11-11 | 2017-08-21 | 2011-12-01 | 2017-08-12
75082-DE Kentucky Combustion Turbin | WD201207 | WD201207X | WGS CT2 Major C Overhaul No1 | 0 |  | 0 |  |  | 8777822.09 | 8128498 | 649324.09 | 2010-09-28 | 2011-09-01 | 2010-11-01 | 2011-08-27
75082-DE Kentucky Combustion Turbin | WD501200 | WD301200X | WGS-CT3 AA Module HVAC Units | 0 |  | 0 |  |  | 20730.67 | 27396 | -6665.33 | 2008-10-27 | 2008-12-31 | 2008-12-01 | 2009-02-05
75082-DE Kentucky Combustion Turbin | WD501201 | WD301201X | WGS-CT3 DD Module HVAC Unit | 0 |  | 0 |  |  | 8171.87 | 12601 | -4429.13 | 2008-10-27 | 2008-12-31 | 2008-12-01 | 2009-02-05
75082-DE Kentucky Combustion Turbin | WD301204 | WD301204X | WGS CT 3 Overhaul #2 | 0 |  | 0 |  |  | 7682178.86 | 8720533 | -1038354.14 | 2011-11-11 | 2012-12-31 | 2011-11-01 | 2012-08-23
75082-DE Kentucky Combustion Turbin | WD401201 | WD401201X | WGS CT4 AA MODULE HVAC Units | 51556.09 |  | 51556.09 | 100% |  | 51556.09 | 48093.68 | 3462.41 | 2015-08-02 10:19 | 2015-12-01 | 2015-08-01 | 2016-01-01
75082-DE Kentucky Combustion Turbin | WD401202 | WD401202X | WGS CT4 DD Module HVAC Unit | 32686.9 |  | 32686.9 | 100% |  | 32686.9 | 23502.24 | 9184.66 | 2015-08-02 00:37 | 2016-02-28 | 2015-08-01 | 2016-02-15
75082-DE Kentucky Combustion Turbin | WD501202 | WD501202X | WGS CT5 Major C Overhaul No2 | 0 |  | 0 |  |  | 7787980.27 | 9627259 | -1839278.73 | 2009-07-27 | 2010-03-31 | 2009-08-01 | 2010-03-09
75082-DE Kentucky Combustion Turbin | WD601206 | WD601206X | WGS CT6 Major C Overhaul No2 | 0 |  | 0 |  |  | 7960271.15 | 4552898 | 3407373.15 | 2009-12-22 | 2010-11-18 | 2009-12-01 | 2010-07-29
75082-DE Kentucky Combustion Turbin | WDC01208 | WDC01208X | WGS CT1-6 GEN PROT PANEL REPL | -2400 |  | -2400 | 100% |  | 1024162.98 | 880363 | 143799.98 | 2008-09-07 | 2011-12-31 | 2008-09-01 | 2012-03-07
75082-DE Kentucky Combustion Turbin | WDC01210 | WDC01210X | WDC-CAUSTIC TANK REPL | 0 |  | 0 |  |  | 117963.66 | 111095 | 6868.66 | 2008-10-12 | 2009-10-25 | 2008-11-01 | 2009-04-08
75082-DE Kentucky Combustion Turbin | WDC01217 | WDC01217X | WGS U1-6 Prop Blr Cntrl Repl | 0 |  | 0 |  |  | 172189.84 | 220432 | -48242.16 | 2011-08-23 | 2012-05-01 | 2011-10-01 | 2012-05-08
75082-DE Kentucky Combustion Turbin | WDC01223 | WDC01223X | Propane Piping Upgrade | 0 |  | 0 |  |  | 92648.07 | 49058 | 43590.07 | 2008-07-14 | 2008-12-31 | 2008-07-01 | 2008-12-15
75082-DE Kentucky Combustion Turbin | WDC01225 | WDC01225X | WGS Blk Start Controls Cab AC | 0 |  | 0 |  |  | 7263.33 | 10214 | -2950.67 | 2009-05-12 | 2009-12-31 | 2009-07-01 | 2009-09-19
75082-DE Kentucky Combustion Turbin | WDC01227 | WDC01227X | Convert WDS Phone Sys to VOIP | 0 |  | 0 |  |  | 79247.12 | 122272 | -43024.88 | 2011-09-13 | 2011-12-31 | 2011-09-01 | 2012-02-18
75082-DE Kentucky Combustion Turbin | WDC01229 | WDC01229X | IT6000 Cyber Security | 0 |  | 0 |  |  | 7406.61 | 14785 | -7378.39 | 2009-11-19 | 2009-12-31 | 2009-12-01 | 2010-02-20
75082-DE Kentucky Combustion Turbin | WDC01235 | WDC01235X | Replace Air Compressor B | 0 |  | 0 |  |  | 111830.9 | 90025 | 21805.9 | 2010-09-20 | 2011-04-30 | 2010-09-01 | 2011-04-19
75082-DE Kentucky Combustion Turbin | WDC01236 | WDC01236X | Replace Site Radios | 0 |  | 0 |  |  | 71420.41 | 45491 | 25929.41 | 2010-11-12 | 2011-12-31 | 2010-12-01 | 2011-12-13
75082-DE Kentucky Combustion Turbin | WDC01237 | WDC01237X | Gas Supply RTU | 0 |  | 0 |  |  | 144852.48 | 165623 | -20770.52 | 2012-02-15 | 2013-12-31 | 2012-02-01 | 2014-08-05
75082-DE Kentucky Combustion Turbin | WDC01241 | WDC01241X | Black Start Diesel Generator | 0 |  | 0 |  |  | 2320125.59 | 1907605 | 412520.59 | 2011-11-01 | 2013-12-31 | 2011-12-01 | 2013-08-18
75082-DE Kentucky Combustion Turbin | WDC01243 | WDC01243X | UVIR Propane Fire Prot Repl | 0 |  | 0 |  |  | 169784.14 | 184610 | -14825.86 | 2012-08-30 | 2013-03-31 | 2012-08-01 | 2013-01-18
75082-DE Kentucky Combustion Turbin | WDC01244 | WDC01244X | Sewer Discharge to Butler Co | 0 |  | 0 |  |  | 911953.83 | 533017 | 378936.83 | 2013-03-24 | 2014-08-25 | 2013-03-01 | 2014-11-01
75082-DE Kentucky Combustion Turbin | WDC01245 | WDC01245X | Network Firewall Upgrade | 0 |  | 0 |  |  | 10396.3 | 18462 | -8065.7 | 2011-09-06 | 2012-07-27 | 2011-10-01 | 2012-06-29
75082-DE Kentucky Combustion Turbin | WDC01247 | WDC01247X | Woodsdale EAM | 0 |  | 0 |  |  | 596309.5 | 596309.49 | 0.01 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2010-01-31
75082-DE Kentucky Combustion Turbin | WDC01248 | WDC01248X | Platform Ladder Swing Gates | 0 |  | 0 |  |  | 88738.57 | 44763 | 43975.57 | 2012-12-14 | 2013-12-31 | 2012-12-01 | 2014-01-31
75082-DE Kentucky Combustion Turbin | WDC01250 | WDC01250X | Diesel Fire Pump Controls | 0 |  | 0 |  |  | 17595.12 | 18229 | -633.88 | 2012-04-02 | 2012-09-30 | 2012-04-01 | 2012-04-25
75082-DE Kentucky Combustion Turbin | WDC01251 | WDC01251X | UPS Battery Replacement | 0 |  | 0 |  |  | 132075.45 | 100463 | 31612.45 | 2012-08-09 | 2012-12-31 | 2012-08-01 | 2012-12-14
75082-DE Kentucky Combustion Turbin | WDC01252 | WDC01252X | Admin Building Roof Replacement | 0 |  | 0 |  |  | 177871.24 | 243442 | -65570.76 | 2013-08-18 | 2013-12-31 | 2013-09-01 | 2014-02-15
75082-DE Kentucky Combustion Turbin | WDC01254 | WDC01254X | Stack Lighting Replacement | 0 |  | 0 |  |  | 52374.19 | 42673 | 9701.19 | 2013-08-18 | 2015-09-25 | 2013-11-01 | 2014-02-15
75082-DE Kentucky Combustion Turbin | WDC01256 | WDC01256X | NERC CIP V | 230.7 |  | 230.7 | 100% |  | 230.7 | 118407 | -118176.3 | 2015-08-11 12:38 | 2016-12-30 | 2015-11-01 | 2017-03-16
75082-DE Kentucky Combustion Turbin | WDC01257 | WDC01257X | WGS - U1-6 EHC System Replacement | 27381.72 |  | 27381.72 | 100% |  | 260104.16 | 244418 | 15686.16 | 2013-04-15 | 2015-06-30 | 2013-05-01 | 2015-07-10
75082-DE Kentucky Combustion Turbin | WDC01258 | WDC01258X | IT Uplift Project | 1446.8 |  | 1446.8 | 100% |  | 67198.36 | 56730 | 10468.36 | 2012-12-09 | 2015-03-31 | 2012-12-01 | 2015-03-18
75082-DE Kentucky Combustion Turbin | WDC01260 | WDC01260X | Admin Building HVAC Replacement | -219.4 |  | -219.4 | 100% |  | 81203.5 | 70725 | 10478.5 | 2014-06-16 | 2015-01-15 | 2014-06-01 | 2015-02-21
75082-DE Kentucky Combustion Turbin | WDC01261 | WDC01261X | Replace CO2 Fire Prot Panels | 354998.39 |  | 354998.39 | 100% |  | 354998.39 | 717032.11 | -362033.72 | 2015-12-01 11:46 | 2016-05-30 | 2015-12-01 | 2016-08-28
75082-DE Kentucky Combustion Turbin | WDC01262 | WDC01262X | Security Camera Upgrade | 0 |  | 0 |  |  | 106384.26 | 110085 | -3700.74 | 2013-09-26 | 2014-11-01 | 2013-10-01 | 2014-12-26
75082-DE Kentucky Combustion Turbin | WDC01266 | WDC01266X | Remote Racking Cart | 48911.22 |  | 48911.22 | 100% |  | 48911.22 | 46360 | 2551.22 | 2015-02-09 | 2015-12-31 | 2015-02-01 | 2016-01-31
75082-DE Kentucky Combustion Turbin | WDC01267 | WDC01267X | IT Site Bandwidth Upgrade | 77407.09 |  | 77407.09 | 100% |  | 77407.09 | 162944.68 | -85537.59 | 2015-05-13 08:49 | 2015-12-31 | 2015-05-01 | 2016-03-05
75082-DE Kentucky Combustion Turbin | WDC01268 | WDC01268X | Data Network Life Cycle Replacement | 85908.37 |  | 85908.37 | 100% |  | 85908.37 | 30681.83 | 55226.54 | 2015-08-02 11:21 | 2016-08-15 | 2015-08-01 | 2016-07-01
75082-DE Kentucky Combustion Turbin | WDCM1201 | WDCM1201X | RO Membrane Replacement | 0 |  | 0 |  |  | 235492.63 | 256876 | -21383.37 | 2012-11-03 | 2013-02-28 | 2012-12-01 | 2013-03-13
75082-DE Kentucky Combustion Turbin | WDCM1205 | WDCM1205X | Station Outside Lighting | 0 |  | 0 |  |  | 55049.87 | 74830 | -19780.13 | 2013-08-18 | 2014-03-30 | 2013-10-01 | 2014-05-21
75082-DE Kentucky Combustion Turbin | WDCM1206 | WDCM1206X | DC Voltage Monitoring System | 82857.06 |  | 82857.06 | 100% |  | 152719.56 | 120950 | 31769.56 | 2014-04-11 | 2015-03-31 | 2014-05-01 | 2015-09-19
75082-DE Kentucky Combustion Turbin | WDCM1209 | WDCM1209X | SmartGen Installation | 210483.26 |  | 210483.26 | 100% |  | 210483.26 | 154707 | 55776.26 | 2015-03-06 09:59 | 2017-12-30 | 2015-04-01
75082-DE Kentucky Combustion Turbin | WDCM1210 | WDCM1210X | Unit 1-3 EHC System Replacement | 182946.97 |  | 182946.97 | 100% |  | 182946.97 | 166773 | 16173.97 | 2015-03-05 13:43 | 2015-08-29 | 2015-03-01 | 2015-09-01
75082-DE Kentucky Combustion Turbin | WGS01202 | WGS01202X | WGS CT1-6 WDPF Controls Rplcmt | 0 |  | 0 |  |  | 2093936.21 | 1963732 | 130204.21 | 2011-09-08 | 2012-12-31 | 2011-09-01 | 2012-08-18
75082-DE Kentucky Combustion Turbin | WGS01204 | WGS01204X | CT1 6 Egatrol Replacement | -17000 |  | -17000 | 100% |  | 3017940.84 | 3382262 | -364321.16 | 2010-08-24 | 2012-02-29 | 2010-09-01 | 2012-03-02
75082-DE Kentucky Combustion Turbin | WGS01208 | WGS01208X | Cyber Security | 0 |  | 0 |  |  | 1013820.32 | 1021367 | -7546.68 | 2010-09-27 | 2012-02-28 | 2010-10-01 | 2012-03-02
75084-DE Kentucky Power Deliv - Ele | CP15BATK | 15BA0019 | Hebron Repl Station Batteries | 10458.05 |  | 10458.05 | 100% |  | 10458.05 | 10632.72 | -174.67 | 2015-04-17 12:18 | 2016-03-31 | 2015-06-01 | 2015-11-30
75084-DE Kentucky Power Deliv - Ele | F8.4ACRES | 8.4ACRESK | 8.4 ACRES FOR HEBRON SUB-KENTUCKY | 0 |  | 0 |  |  | 61500.18 | 60000 | 1500.18 | 2010-07-21 | 2010-10-01 | 2010-07-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 12.45 |  | 12.45 | 100% |  | 12.45 | 217 | -204.55 | 2015-03-30 16:09 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 17970.65 |  | 17970.65 | 100% |  | 17970.65 | 199412 | -181441.35 | 2015-03-30 14:59 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 9.92 |  | 9.92 | 100% |  | 9.92 | 217 | -207.08 | 2015-03-30 13:06 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | ARMS | Enable ARM Scheduler Software | 26832.84 |  | 26832.84 | 100% |  | 26832.84 | 199412 | -172579.16 | 2015-03-30 14:11 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | RLFA | AT12KY | AT12 & Micro ATO Replace KY | 0 |  | 0 |  |  | 0 | 31339 | -31339 | 2010-12-22 | 2050-12-31 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C8961 | pp 870018/joe groeschen | 0 |  | 0 |  |  | -449.2 | 0 | -449.2 | 2007-01-03 | 2050-12-31 | 2007-02-01 | 2007-02-01
75084-DE Kentucky Power Deliv - Ele | U14ZKV | C9013 | ULH&P 2005 Capacitors | 0 |  | 0 |  |  | -162705.78 | 162253 | -324958.78 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9015 | ULH&P 2005 Government Mandate | 0 |  | 0 |  |  | -42185.33 | 42069 | -84254.33 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9021 | ULH&P 2005 New Business | 0 |  | 0 |  |  | -2062970.85 | 2057265 | -4120235.85 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZRL | C9024 | ULH&P 2005 Reliability | 0 |  | 0 |  |  | -406645.66 | 405521 | -812166.66 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 312ZLL | C9025 | ULH&P 2005 Lighting | 0 |  | 0 |  |  | -300872.38 | 300040 | -600912.38 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZUR | C9030 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -409635.37 | 408502 | -818137.37 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C9034 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -208.67 | 75231 | -75439.67 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZLG | C9035 | ULH&P 2005 Load Growth | 0 |  | 0 |  |  | -113979.76 | 113664 | -227643.76 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314G8757 | C9060 | PP872754 DAYTON 42 UNDERGRND | 0 |  | 0 |  |  | 0 | 36886 | -36886 | 2007-01-07 | 2008-12-01 | 2007-08-01 | 2008-05-19
75084-DE Kentucky Power Deliv - Ele | 314G8764 | C9062 | PP872756 DAYTON 43 UNDERGROUND | 0 |  | 0 |  |  | 120235.74 | 43139 | 77096.74 | 2007-01-07 | 2008-12-01 | 2008-04-01 | 2008-06-02
75084-DE Kentucky Power Deliv - Ele | 314G8764 | C9063 | PP872757 DAYTON 43 EXITS OH | 0 |  | 0 |  |  | 245210.98 | 3059 | 242151.98 | 2007-01-07 | 2008-12-01 | 2007-08-01 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | 314G8867 | C9067 | PP872787 WHITE TOWER 42 | 0 |  | 0 |  |  | 520813.77 | 486933 | 33880.77 | 2007-01-07 | 2008-12-31 | 2007-10-01 | 2008-09-27
75084-DE Kentucky Power Deliv - Ele | 304G8909 | C9068 | PP872798 WHITE TOWER F5967 | 0 |  | 0 |  |  | 75276.69 | 42350 | 32926.69 | 2007-01-07 | 2008-12-01 | 2007-03-01 | 2009-04-09
75084-DE Kentucky Power Deliv - Ele | 303G8848 | C9075 | Atlas Sub Repl Regulators | 0 |  | 0 |  |  | 271497.16 | 137087 | 134410.16 | 2007-01-10 | 2008-11-15 | 2007-07-01 | 2008-07-10
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9115 | PP 863371/JOE GROESCHEN | 0 |  | 0 |  |  | -2331.3 | 5958 | -8289.3 | 2007-01-16 | 2050-12-31 | 2007-01-01 | 2007-03-26
75084-DE Kentucky Power Deliv - Ele | 903G0504 | C9339 | Dixie replace arresters TB2 | 0 |  | 0 |  |  | 6138.14 | 4423 | 1715.14 | 2007-02-25 | 2050-12-31 | 2007-05-01 | 2008-02-11
75084-DE Kentucky Power Deliv - Ele | U02Z7993 | C9471 | KY UNIV rep ABS 962 | 0 |  | 0 |  |  | 17071.23 | 20123 | -3051.77 | 2007-03-20 | 2050-12-31 | 2007-03-01 | 2007-03-21
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9564 | RI-NO BEND RD FRM I-275 NORTH | 0 |  | 0 |  |  | 11782.24 | 38177 | -26394.76 | 2007-04-10 | 2015-04-01 | 2007-04-01 | 2007-11-12
75084-DE Kentucky Power Deliv - Ele | 302G8860 | C9599 | White Tower TB 2 Transmission | 0 |  | 0 |  |  | 80216.74 | 81470 | -1253.26 | 2007-04-17 | 2008-05-31 | 2007-05-01 | 2008-05-31
75084-DE Kentucky Power Deliv - Ele | 316H8978 | C9634 | Ft Mitchell Sub Land Sale | -15333.69 |  | -15333.69 | 100% |  | 0 |  | 0 | 2007-04-22 | 2010-12-31 | 2008-12-01 | 2010-07-31
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9664 | RI-ST ELZBTH ACCESS RELO DIST | 0 |  | 0 |  |  | 23075.94 | 15263 | 7812.94 | 2007-04-27 | 2012-04-01 | 2007-05-01 | 2008-01-02
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9737 | PP 900903 - JOE FRICKE | 0 |  | 0 |  |  | 45685.81 | 1 | 45684.81 | 2007-05-04 | 2050-12-31 | 2007-08-01 | 2007-09-18
75084-DE Kentucky Power Deliv - Ele | 903G0504 | C9793 | Hands rep bush/arrest TB1 | 0 |  | 0 |  |  | 20303.93 | 15589 | 4714.93 | 2007-05-12 | 2050-12-31 | 2007-05-01 | 2007-12-23
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9850 | PP 905263 - SANDY CONNLEY | 0 |  | 0 |  |  | 214646.51 | 99195 | 115451.51 | 2007-05-20 | 2050-12-31 | 2007-06-01 | 2008-01-08
75084-DE Kentucky Power Deliv - Ele | 316ZBG | C9864 | Cold Springs Site Improvements | 0 |  | 0 |  |  | 40659.35 | 35643 | 5016.35 | 2007-05-23 | 2008-07-01 | 2007-06-01 | 2008-03-15
75084-DE Kentucky Power Deliv - Ele | 314ZUR | C9886 | CHELSEA S/O VILLA MADONNA | 0 |  | 0 |  |  | -1382.28 | 38775 | -40157.28 | 2007-05-30 | 2012-05-01 | 2007-06-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C9887 | CHELSEA S/O VILLA MADONNA-F966 | 0 |  | 0 |  |  | 645.24 | 53416 | -52770.76 | 2007-05-30 | 2012-05-01 | 2007-06-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9888 | PP 892193/DONNA CARMACK | 0 |  | 0 |  |  | 60160.94 | 71110 | -10949.06 | 2007-05-31 | 2050-12-31 | 2007-06-01 | 2007-12-18
75084-DE Kentucky Power Deliv - Ele | UGCIFA | CABINJKY | Underground Cable Injection - KY | 1.1369e-12 |  | 1.1369e-12 | 100% |  | 1.1369e-12 | 232000 | -232000 | 2011-03-15 | 2015-12-31 | 2011-04-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | CAPAUTOKY | Capacitor Automation - Kentucky | 0 |  | 0 |  |  | 0 | 49 | -49 | 2014-01-15 | 2020-12-31 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | CAPKY | Capacitor Inst/Rem | -3.6948e-13 |  | -3.6948e-13 | 100% |  | 200598.71 | 101 | 200497.71 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | CERTKY | Rel Major Cap T Equip Repl | -2600.94 |  | -2600.94 | 100% |  | 275169.22 | 100 | 275069.22 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FMWCF53SK | CF53AUGUS | Purch Panasonic CF53s repl MDTs | 13987.61 |  | 13987.61 | 100% |  | 252990.71 | 158146 | 94844.71 | 2014-08-04 | 2017-03-31 | 2014-09-01 | 2017-03-05
75084-DE Kentucky Power Deliv - Ele | CSFA | CSKY | Circuit Sectionalization | 40752.15 |  | 40752.15 | 100% |  | 64479.1 | 100 | 64379.1 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | CSPFA | CSPKY | Transformer Retrofit | -2.8422e-13 |  | -2.8422e-13 | 100% |  | 153844.14 | 200 | 153644.14 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | 314G8865 | D1309 | PP924061 WHITE TOWER 43 UG | 0 |  | 0 |  |  | 34903.51 | 31793 | 3110.51 | 2007-07-31 | 2008-12-31 | 2007-10-01 | 2008-06-27
75084-DE Kentucky Power Deliv - Ele | 314G8867 | D1310 | PP924057 WHITE TOWER 42 UG | 0 |  | 0 |  |  | 46150.46 | 1 | 46149.46 | 2007-07-31 | 2008-12-31 | 2007-10-01 | 2008-06-27
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D1391 | CNSTNCE 42-NIEWHNR RD-UG RECON | 0 |  | 0 |  |  | 65183.82 | 60522 | 4661.82 | 2007-08-14 | 2012-08-01 | 2007-08-01 | 2008-12-20
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D1447 | WILDER 45-REMOVE 275 CROSSING | 0 |  | 0 |  |  | 46139.96 | 49284 | -3144.04 | 2007-09-02 | 2012-08-01 | 2007-08-01 | 2009-06-25
75084-DE Kentucky Power Deliv - Ele | U04ZGM | D1507 | ri-dolwick rd ginny meyer | 0 |  | 0 |  |  | 52045 | 52045 | 0 | 2007-08-30 | 2050-12-31 | 2009-11-01 | 2003-08-22
75084-DE Kentucky Power Deliv - Ele | U03Z7357 | D1581 | Cold Spring TB9 failure | 0 |  | 0 |  |  | 30159.65 | 13915 | 16244.65 | 2007-09-12 | 2050-12-31 | 2007-09-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | 304H9033 | D1596 | PP936435 F965 UPRATE 100 C | 0 |  | 0 |  |  | 156331.49 | 146838.77 | 9492.72 | 2007-09-14 | 2011-03-31 | 2009-08-01 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | 302H9041 | D1628 | Kenton Sub Sell Excess Prop | 0 |  | 0 |  |  | 0 | 1 | -1 | 2007-09-19 | 2008-12-31 | 2007-09-01 | 2008-01-15
75084-DE Kentucky Power Deliv - Ele | 314G8840 | D1639 | PP938045 COVINGTON 41 OH PART | 0 |  | 0 |  |  | 0 | 50359 | -50359 | 2007-09-20 | 2009-04-30 | 2008-02-01 | 2009-01-28
75084-DE Kentucky Power Deliv - Ele | 314G8840 | D1640 | PP938046 COVINGTON 41 UG PART | 0 |  | 0 |  |  | 890658.52 | 47242 | 843416.52 | 2007-09-20 | 2009-04-30 | 2007-11-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8844 | D1641 | PP938072 Covington 42- OH part | 0 |  | 0 |  |  | 0 | 50359 | -50359 | 2007-09-20 | 2008-12-01 | 2008-02-01 | 2009-01-17
75084-DE Kentucky Power Deliv - Ele | 314G8844 | D1642 | PP938073 Covington 42- UG part | 0 |  | 0 |  |  | 214376.63 | 47242 | 167134.63 | 2007-09-20 | 2008-12-01 | 2007-12-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8846 | D1643 | PP938163 Covington 43- OH part | 0 |  | 0 |  |  | 333618.3 | 300256.2 | 33362.1 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-11-14
75084-DE Kentucky Power Deliv - Ele | 314G8846 | D1644 | PP938164 Covington 43- UG part | 0 |  | 0 |  |  | 210161 | 47242 | 162919 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | U16Z7994 | D1697 | Wilder dispose mulsifyer house | 0 |  | 0 |  |  | 0 |  | 0 | 2007-10-02 | 2008-04-07 | 2010-08-01 | 2007-10-29
75084-DE Kentucky Power Deliv - Ele | 903G7996 | D1716 | Villa rep control battery | 0 |  | 0 |  |  | 3586.35 | 5195 | -1608.65 | 2007-10-03 | 2050-12-31 | 2007-10-01 | 2007-11-03
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D1727 | RI-12TH ST RECONST -I-75/SCOTT | 0 |  | 0 |  |  | 120906.9 | 60754 | 60152.9 | 2007-10-03 | 2012-10-01 | 2009-02-01 | 2009-12-15
75084-DE Kentucky Power Deliv - Ele | U16Z7994 | D1754 | Kenton replace roof | 0 |  | 0 |  |  | 14429.12 | 18456 | -4026.88 | 2007-10-05 | 2050-12-31 | 2007-11-01 | 2007-12-15
75084-DE Kentucky Power Deliv - Ele | 314ZRL | D1893 | LIMABURG 42-INSTL VOLTG REG | 0 |  | 0 |  |  | 0 | 53978 | -53978 | 2007-10-23 | 2012-10-01 | 2007-10-01 | 2008-01-07
75084-DE Kentucky Power Deliv - Ele | 310ZNB | D1912 | PP 879351 - M Billow | 0 |  | 0 |  |  | 0 | 45471 | -45471 | 2007-10-25 | 2050-12-31 | 2007-11-01 | 2008-03-06
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D1970 | RI SR 16-I-275 TO SUBRITE DR | 0 |  | 0 |  |  | 353455.74 | 516774.62 | -163318.88 | 2007-11-01 | 2012-10-01 | 2007-11-01 | 2012-03-29
75084-DE Kentucky Power Deliv - Ele | TOALOGK | D2063 | Install Sun-Net TOA Kentucky | 0 |  | 0 |  |  | 38944.7 | 1 | 38943.7 | 2007-11-14 | 2010-11-30 | 2008-03-01 | 2010-10-01
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D2085 | RI-HAZELWOOD DR S/O BUTTERMILK | 0 |  | 0 |  |  | 41739.15 | 41768 | -28.85 | 2007-11-16 | 2012-11-01 | 2007-11-01 | 2008-01-13
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D2139 | CRESCENT 42-UG RECONDUCTOR | 0 |  | 0 |  |  | 48020.04 | 1 | 48019.04 | 2007-11-21 | 2012-10-01 | 2007-11-01 | 2009-02-04
75084-DE Kentucky Power Deliv - Ele | EPS100 | D2185 | Erlanger Micro Upgrade | 0 |  | 0 |  |  | 1818 | 1908 | -90 | 2007-12-04 | 2008-02-28 | 2008-02-01 | 2008-01-27
75084-DE Kentucky Power Deliv - Ele | 303H9052 | D2187 | Hebron Install 22/4MVA Xfmr | 0 |  | 0 |  |  | 1497635.9 | 1031892 | 465743.9 | 2007-12-04 | 2009-09-01 | 2008-02-01 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | 903G0534 | D2365 | Beaver install switch and CB | 0 |  | 0 |  |  | 212250.69 | 80053 | 132197.69 | 2007-12-18 | 2050-12-31 | 2007-12-01 | 2008-02-01
75084-DE Kentucky Power Deliv - Ele | EMSBLSRV | D2508 | MW EMS Blade Server Upgrade | 0 |  | 0 |  |  | 5419.5 | 8919 | -3499.5 | 2008-01-10 | 2008-08-30 | 2008-01-01 | 2008-08-30
75084-DE Kentucky Power Deliv - Ele | 314G8867 | D2526 | White Tower 42 | 0 |  | 0 |  |  | 0 | 41272 | -41272 | 2008-01-15 | 2008-09-27 | 2008-01-01 | 2008-09-27
75084-DE Kentucky Power Deliv - Ele | 114ZUG | D2553 | pp 966522 RR HARDIN | 0 |  | 0 |  |  | 30263.28 | 18092 | 12171.28 | 2008-01-20 | 2050-12-31 | 2008-02-01 | 2009-01-21
75084-DE Kentucky Power Deliv - Ele | 314ZLG | D2740 | COLD SPRING 49 CONVERSION | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-02-05 | 2013-02-01 | 2008-02-01 | 2009-04-06
75084-DE Kentucky Power Deliv - Ele | 310ZNB | D2771 | PP 907295/MICHAEL SMITH | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-02-08 | 2050-12-31 | 2008-02-01 | 2008-10-16
75084-DE Kentucky Power Deliv - Ele | 903G0504 | D2883 | Crescent TB1 rem/inst ETM | 0 |  | 0 |  |  | 5479.14 | 10303 | -4823.86 | 2008-02-21 | 2050-12-31 | 2008-04-01 | 2008-05-07
75084-DE Kentucky Power Deliv - Ele | 314H9055 | D2888 | PP974374 HEBRON 45 EXTEND UG | 0 |  | 0 |  |  | 0 | 167768 | -167768 | 2008-02-22 | 2009-09-01 | 2008-08-01 | 2009-09-15
75084-DE Kentucky Power Deliv - Ele | 314H9054 | D2895 | PP974383 HEBRON 44 EXTEND OH | 0 |  | 0 |  |  | 0 | 70487 | -70487 | 2008-02-22 | 2012-12-31 | 2009-05-01 | 2009-09-30
75084-DE Kentucky Power Deliv - Ele | 314H9054 | D2896 | PP974384 HEBRON 44 EXTEND UG | 0 |  | 0 |  |  | 0 | 519697 | -519697 | 2008-02-22 | 2009-09-01 | 2008-07-01 | 2009-09-30
75084-DE Kentucky Power Deliv - Ele | 314H9053 | D2908 | PP974767 HEBRON 43 | 0 |  | 0 |  |  | 365524.39 | 224676 | 140848.39 | 2008-02-24 | 2009-09-01 | 2008-06-01 | 2009-10-14
75084-DE Kentucky Power Deliv - Ele | 314G8857 | D2914 | PP974771 WHITE TOWER 41 RECON | 0 |  | 0 |  |  | 276117.72 | 275058 | 1059.72 | 2008-02-24 | 2010-09-01 | 2008-07-01 | 2010-10-09
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D3355 | RI-GRAND AVE S/O MEMORIAL PKWY | 0 |  | 0 |  |  | -5.0932e-11 |  | -5.0932e-11 | 2008-04-24 | 2013-04-01 | 2008-06-01 | 2010-04-07
75084-DE Kentucky Power Deliv - Ele | 314ZLG | D3389 | CLRYVLLE 42-CNVRT 2/4KV STPDWN | 0 |  | 0 |  |  | 176612.71 | 100 | 176512.71 | 2008-04-30 | 2013-04-01 | 2008-05-01 | 2009-01-26
75084-DE Kentucky Power Deliv - Ele | 303J9130 | D3431 | Richwood TB1 Install Breaker | 0 |  | 0 |  |  | 274597.65 | 85981 | 188616.65 | 2008-05-02 | 2009-09-01 | 2008-06-01 | 2009-09-12
75084-DE Kentucky Power Deliv - Ele | 314J9129 | D3435 | PP989939 RICHWOOD 41 LINE REAR | 0 |  | 0 |  |  | 0 | 178716 | -178716 | 2008-05-02 | 2010-01-31 | 2008-06-01 | 2010-02-24
75084-DE Kentucky Power Deliv - Ele | TRLERULH | D3446 | FORKLIFT | 0 |  | 0 |  |  | 34681.99 | 31800 | 2881.99 | 2008-05-05 | 2050-12-31 | 2008-06-01 | 2008-10-28
75084-DE Kentucky Power Deliv - Ele | 303G8919 | D3495 | KY Univ Inst New 22/4 MVA Xfmr | 0 |  | 0 |  |  | 2036293.53 | 1433432 | 602861.53 | 2008-05-20 | 2010-09-01 | 2008-08-01 | 2010-08-25
75084-DE Kentucky Power Deliv - Ele | 303G8834 | D3543 | Covington Area-new Substation | -25.57 |  | -25.57 | 100% |  | 967769.41 | 1512745 | -544975.59 | 2008-05-20 | 2009-02-14 | 2008-05-01 | 2008-11-14
75084-DE Kentucky Power Deliv - Ele | C16A7995 | D3550 | Crescent rep dbl doors | 0 |  | 0 |  |  | 21018.96 | 1 | 21017.96 | 2008-05-21 | 2050-12-31 | 2008-12-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | 100FACB4 | D3597 | Upgrade Erlanger Storm System | 0 |  | 0 |  |  | 57417.18 | 38692 | 18725.18 | 2008-05-30 | 2008-12-31 | 2008-09-01 | 2008-11-10
75084-DE Kentucky Power Deliv - Ele | 303J9142 | D3694 | Kenton Relocate Driveway | 0 |  | 0 |  |  | 116611.85 | 21253 | 95358.85 | 2008-06-16 | 2009-03-31 | 2008-07-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | TOOL002 | D3702 | TIRE CHANGER | 0 |  | 0 |  |  | 6207.56 | 6200 | 7.56 | 2008-06-19 | 2050-12-31 | 2008-07-01 | 2008-12-15
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D3712 | CLARYVL 42-MAIN ST-RT 10-RECON | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-06-20 | 2013-06-01 | 2008-07-01 | 2010-02-24
75084-DE Kentucky Power Deliv - Ele | 314G8917 | D8917DL | AM 8915089 KY University UG | 2670.38 |  | 2670.38 | 100% |  | 2670.38 | 218868.92 | -216198.54 | 2015-10-08 14:59 | 2016-10-29 | 2015-10-01 | 2016-09-27
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | DM0029 | Richwood Repl Sta Batt | 1684.3 |  | 1684.3 | 100% |  | 1684.3 | 2757.91 | -1073.61 | 2015-07-24 10:48 | 2016-01-31 | 2015-08-01 | 2015-11-28
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | DP0028 | Augustine Repl failed TB5 Xtr | 519935.71 |  | 519935.71 | 100% |  | 519935.71 | 891842 | -371906.29 | 2015-07-07 11:55 | 2016-06-01 | 2015-07-01 | 2015-11-26
75084-DE Kentucky Power Deliv - Ele | FLKY0249E | DUKETCKYE | Fleet On-Road Vehicles - elec - KY | 4563.83 |  | 4563.83 | 100% |  | 4563.83 | 40000 | -35436.17 | 2009-08-11 | 2050-12-31 | 2015-08-01
75084-DE Kentucky Power Deliv - Ele | FLKY0249E | DUKETEKYE | Fleet Off-Road Vehicles - KY | 72028.99 |  | 72028.99 | 100% |  | 193531.56 | 20000 | 173531.56 | 2009-08-11 | 2050-12-31 | 2010-05-01
75084-DE Kentucky Power Deliv - Ele | NPDLOGMW | E0222 | Midwest Log Aggregation - Ky - HW | 0 |  | 0 |  |  | 14745.6 | 46258 | -31512.4 | 2008-07-24 | 2008-12-31 | 2008-07-01 | 2009-02-28
75084-DE Kentucky Power Deliv - Ele | NPDLOGMW | E0234 | Midwest Log Aggregation - Ky - SW | 0 |  | 0 |  |  | 2203.32 | 8163 | -5959.68 | 2008-07-24 | 2008-12-31 | 2008-10-01 | 2009-02-28
75084-DE Kentucky Power Deliv - Ele | TDIT | E0857 | EMS OML Kentucky | 0 |  | 0 |  |  | 9123.03 | 8600 | 523.03 | 2008-09-03 | 2009-12-31 | 2008-12-01 | 2010-03-14
75084-DE Kentucky Power Deliv - Ele | TRLERULH | E0933 | Erlanger ATV | 0 |  | 0 |  |  | 11770 | 12177 | -407 | 2008-09-09 | 2008-11-30 | 2008-10-01 | 2008-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | E1227 | Storm 12 - Ike (Kentucky) | 0 |  | 0 |  |  | 219722.62 | 9200 | 210522.62 | 2008-09-19 | 2050-12-31 | 2008-09-01 | 2008-12-18
75084-DE Kentucky Power Deliv - Ele | OPTIMALC | E1235 | Project Optimization Sftwr-Ky | 0 |  | 0 |  |  | 12896.77 | 14000 | -1103.23 | 2008-09-22 | 2010-12-31 | 2008-10-01 | 2009-07-31
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA | E1551 | Wilder - Replace Battery | 0 |  | 0 |  |  | 11727.24 | 9480 | 2247.24 | 2008-10-08 | 2050-07-10 | 2009-05-01 | 2009-08-23
75084-DE Kentucky Power Deliv - Ele | RELDFA | E1613 | PP#924827 9Sanitati District #1 | 0 |  | 0 |  |  | 0 | 21964 | -21964 | 2008-10-13 | 2009-03-31 | 2008-10-01 | 2007-12-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | E1614 | PP#949527 Sanitation District #1 | 0 |  | 0 |  |  | 0 | 151815 | -151815 | 2008-10-13 | 2009-03-31 | 2008-10-01 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | FOKY0082 | E1673 | Kenton Install Electric Fence | 0 |  | 0 |  |  | 1593.78 | 1542 | 51.78 | 2008-10-15 | 2008-12-31 | 2008-10-01 | 2008-10-29
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E1833 | Augustine Repl TB5 Bushings | 0 |  | 0 |  |  | 15264.71 | 15584 | -319.29 | 2008-10-22 | 2050-07-08 | 2008-10-01 | 2009-01-24
75084-DE Kentucky Power Deliv - Ele | PILCFA | E1881 | NKU -Customer Switchgear | 0 |  | 0 |  |  | 0 | 71200 | -71200 | 2008-10-24 | 2009-06-01 | 2008-11-01 | 2009-09-19
75084-DE Kentucky Power Deliv - Ele | 303ZANLG | E1995 | Hebron Analog to Digital | 0 |  | 0 |  |  | 11503.48 | 30000 | -18496.52 | 2008-10-30 | 2010-03-31 | 2009-01-01 | 2009-07-16
75084-DE Kentucky Power Deliv - Ele | 314H9053 | E1996 | HEBRON 43 -Install Conduit & Cable | 0 |  | 0 |  |  | 359675.59 | 326800 | 32875.59 | 2008-10-30 | 2009-09-01 | 2008-12-01 | 2009-10-14
75084-DE Kentucky Power Deliv - Ele | TDIT | E2272 | EMS MH Standby Enhancement - Ky | 0 |  | 0 |  |  | 4289.25 | 4025 | 264.25 | 2008-11-12 | 2010-12-31 | 2008-12-01 | 2011-02-28
75084-DE Kentucky Power Deliv - Ele | RELDFA | E3613 | PP#1038389 S FT THOMAS AVE @ RIVER | 0 |  | 0 |  |  | 71990.4 | 223261 | -151270.6 | 2009-01-14 | 2010-12-31 | 2009-01-01 | 2010-04-30
75084-DE Kentucky Power Deliv - Ele | 303G8919 | E3752 | Wilder Sub Retire DT Equipment | 0 |  | 0 |  |  | -1.5916e-12 | 1 | -1 | 2009-01-21 | 2010-12-01 | 2009-12-01 | 2010-09-18
75084-DE Kentucky Power Deliv - Ele | 303G8919 | E3753 | Silver Grove Sub Retire DT Equip | 0 |  | 0 |  |  | -3.7517e-12 | 1 | -1 | 2009-01-21 | 2010-12-01 | 2009-12-01 | 2010-09-03
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | E3824 | Pole Repl Gnd Line-T | 0 |  | 0 |  |  | 53058 | 10742 | 42316 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | MOFA | E3825 | Major Outage Followup-D | 0 |  | 0 |  |  | 0 | 13363 | -13363 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | PILCFA | E3829 | UG Cable Repl-PILC | 0 |  | 0 |  |  | 0 | 14242 | -14242 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | REGFA | E3832 | Regulator Inst/Rem | 0 |  | 0 |  |  | 0 | 19896 | -19896 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | SCFOFA | E3836 | System Capacity-FO | 0 |  | 0 |  |  | 0 | 75723 | -75723 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4062 | Crescent-Repl Arr & Bushings in TB1 | 0 |  | 0 |  |  | 11703.28 | 10372 | 1331.28 | 2009-02-03 | 2010-12-31 | 2009-02-01 | 2010-06-24
75084-DE Kentucky Power Deliv - Ele | ORDFA | E4291 | STORM 1 - 2009 - CAPITAL | 0 |  | 0 |  |  | 0 | 39105.32 | -39105.32 | 2009-02-12 | 2009-06-01 | 2009-02-01 | 2009-03-01
75084-DE Kentucky Power Deliv - Ele | ITKY0157 | E4303 | MDT Toughbooks - Ky | 0 |  | 0 |  |  | 218435.18 | 138204 | 80231.18 | 2009-02-12 | 2009-10-31 | 2009-04-01 | 2010-02-28
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4340 | Cold Spring rep HS arresters on TB1 | 0 |  | 0 |  |  | 3407.68 | 3989 | -581.32 | 2009-02-13 | 2010-03-01 | 2009-03-01 | 2010-02-09
75084-DE Kentucky Power Deliv - Ele | NUMARAT | E4634 | EMS NUMARA - KY | 0 |  | 0 |  |  | 5551.02 | 4443 | 1108.02 | 2009-03-02 | 2009-09-30 | 2009-03-01 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4816 | Empire - Install LTC Oil Filtration | 0 |  | 0 |  |  | 10212.88 | 10252 | -39.12 | 2009-03-11 | 2010-12-31 | 2009-11-01 | 2010-02-17
75084-DE Kentucky Power Deliv - Ele | TDIT | E5392 | EMS SQL Cluster Infrastruc - KY | 0 |  | 0 |  |  | 9055.89 | 5516 | 3539.89 | 2009-04-07 | 2009-11-30 | 2009-04-01 | 2010-03-28
75084-DE Kentucky Power Deliv - Ele | ITMW0195 | E5745 | Pole Inspection Replacement - KY | 0 |  | 0 |  |  | 81403.21 | 17894 | 63509.21 | 2009-04-21 | 2011-04-30 | 2009-04-01 | 2011-12-31
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E5944 | Cold Spring - Repl Recloser | 0 |  | 0 |  |  | 4300.9 | 6773 | -2472.1 | 2009-04-28 | 2009-12-30 | 2009-07-01 | 2009-07-24
75084-DE Kentucky Power Deliv - Ele | 314G8914 | E6225 | KY Univ 43 New Feeder | 0 |  | 0 |  |  | 10689.14 | 708735 | -698045.86 | 2009-05-07 | 2010-10-01 | 2009-05-01
75084-DE Kentucky Power Deliv - Ele | 314G8914 | E6226 | KY Univ 43 UG Cable and Conduit | 0 |  | 0 |  |  | 1382283.91 | 1426651 | -44367.09 | 2009-05-07 | 2010-10-01 | 2009-05-01 | 2010-10-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E6464 | Claryville - Repl Voltage Regulator | 0 |  | 0 |  |  | 12505.6 | 16933 | -4427.4 | 2009-05-19 | 2009-12-30 | 2009-05-01 | 2009-08-19
75084-DE Kentucky Power Deliv - Ele | UGCRFA | E6865 | PP#1068539 DERBY RIDGE APTS RECOND | 0 |  | 0 |  |  | 0 | 72432 | -72432 | 2009-06-04 | 2009-12-31 | 2009-07-01 | 2009-12-17
75084-DE Kentucky Power Deliv - Ele | UGCRFA | E6908 | PP#1068609 COUNTRY SQUIRE ESTATES | 0 |  | 0 |  |  | 0 | 83042 | -83042 | 2009-06-05 | 2010-06-01 | 2009-07-01 | 2010-02-19
75084-DE Kentucky Power Deliv - Ele | AMKY0036 | E7672 | Wilder 40 PILC Cable Replacement | 0 |  | 0 |  |  | 0 | 33130 | -33130 | 2009-07-10 | 2010-06-01 | 2009-09-01 | 2010-02-19
75084-DE Kentucky Power Deliv - Ele | AMKY0035 | E9944 | Augustine 42 Dist OH Reconductor | 0 |  | 0 |  |  | 37506.59 | 29508 | 7998.59 | 2009-09-03 | 2010-05-31 | 2009-10-01 | 2010-06-09
75084-DE Kentucky Power Deliv - Ele | AMKY0035 | E9945 | Augustine 42 PILC Cable Replacement | 0 |  | 0 |  |  | 436906.32 | 331601 | 105305.32 | 2009-09-03 | 2010-05-31 | 2009-09-01 | 2010-06-09
75084-DE Kentucky Power Deliv - Ele | FENABLES | ECOMS | Enable ECOM Data Hub Software | 5637.76 |  | 5637.76 | 100% |  | 5637.76 | 117858 | -112220.24 | 2015-03-30 15:05 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLEH | EGISH | Enable EGIS Hardware | 583.18 |  | 583.18 | 100% |  | 583.18 | 1224 | -640.82 | 2015-03-30 15:31 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | EGISS | Enable EGIS Software | 97035.68 |  | 97035.68 | 100% |  | 97035.68 | 670125 | -573089.32 | 2015-03-30 14:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FEGISSYNK | EGISSYNKE | EGIS TO SYNERGEE INTERFACE | 0 |  | 0 |  |  | 47109.73 | 52945 | -5835.27 | 2011-01-27 | 2011-09-30 | 2011-02-01 | 2011-11-22
75084-DE Kentucky Power Deliv - Ele | RCLFA | ELASTIMOL | Elastimold e-recloser pilot | 0 |  | 0 |  |  | 55832.08 | 51290.35 | 4541.73 | 2012-09-06 | 2014-03-31 | 2012-09-01 | 2014-02-01
75084-DE Kentucky Power Deliv - Ele | 75084 | EMETERKY | Electric Meter Blanket | 301203.49 |  | 301203.49 | 100% |  | 301203.49 | 295697.19 | 5506.3 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01
75084-DE Kentucky Power Deliv - Ele | FEMPCSITK | EMPCSITK | EMPCS CAOS/W2K8 R2 KENTUCKY | 0 |  | 0 |  |  | 2498.64 | 1396.05 | 1102.59 | 2010-08-04 | 2010-08-30 | 2010-09-01 | 2011-02-28
75084-DE Kentucky Power Deliv - Ele | FEMSUPGRD | EMSUPGRVS | EMS EMP 2.6 UPGRADE PROJECT | 0 |  | 0 |  |  | 210750.47 | 211000 | -249.53 | 2011-03-30 | 2014-06-30 | 2011-09-01 | 2014-06-30
75084-DE Kentucky Power Deliv - Ele | FENABLES | ENABLETDG | ENABLETDG Clearing Project | 154424.75 |  | 154424.75 | 100% |  | 154424.75 | 801485.44 | -647060.69 | 2015-05-12 14:57 | 2017-10-31 | 2015-05-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | EXPDH | Enable Expert Designer Hardware | 70.33 |  | 70.33 | 100% |  | 70.33 | 136 | -65.67 | 2015-03-30 13:46 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | EXPDS | Enable Expert Designer Software | 26460.54 |  | 26460.54 | 100% |  | 26460.54 | 145274 | -118813.46 | 2015-03-30 14:25 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0244 | EKP-138kv Interconn-Webster R/W | 0 |  | 0 |  |  | -8.5129e-12 | 85528 | -85528 | 2009-09-15 | 2011-10-01 | 2011-03-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0245 | F6282-Loop thru Webster Ring Bus | 0 |  | 0 |  |  | 1856.61 | 952790.42 | -950933.81 | 2009-09-15 | 2011-10-01 | 2009-09-01 | 2011-08-10
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0246 | Silver Grove Repl F6282 relays | 0 |  | 0 |  |  | 5210.7 | 36618 | -31407.3 | 2009-09-15 | 2011-10-01 | 2010-02-01 | 2011-09-04
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0265 | Buffington Repl F6282 relays | 0 |  | 0 |  |  | 5.8209e-13 | 97583 | -97583 | 2009-09-15 | 2011-10-01 | 2009-12-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0304 | Hands Sub Inst TB2 Transrupter | 0 |  | 0 |  |  | -2.9097e-12 | 118970 | -118970 | 2009-09-16 | 2011-10-01 | 2009-10-01 | 2011-09-04
75084-DE Kentucky Power Deliv - Ele | UGCRFA | F0709 | PP#1088919 URD 104 | 0 |  | 0 |  |  | 148789.21 | 163914.64 | -15125.43 | 2009-09-25 | 2010-12-31 | 2009-12-01 | 2010-10-07
75084-DE Kentucky Power Deliv - Ele | 903H8407X | F0824 | Alexandria Sub - Land | 0 |  | 0 |  |  | 544000 | 544000 | 0 | 2009-09-30 | 2009-09-30 | 2009-09-01 | 2001-09-30
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | F1085 | Crescent -Repl Ckt 1587 Direct Trip | 0 |  | 0 |  |  | 16412.23 | 17522 | -1109.77 | 2009-10-09 | 2010-03-01 | 2009-12-01 | 2010-03-17
75084-DE Kentucky Power Deliv - Ele | AMKY0290 | F2324 | Aug 44 Extension, Conv Latonia C | 0 |  | 0 |  |  | 198422.01 | 1 | 198421.01 | 2009-11-18 | 2010-09-01 | 2009-12-01 | 2010-09-15
75084-DE Kentucky Power Deliv - Ele | FSRVCO201 | F3205 | ASSET MGMT OPT-KENTUCKY | 0 |  | 0 |  |  | 17905.67 | 13181 | 4724.67 | 2009-12-17 | 2010-09-01 | 2009-12-01 | 2009-07-04
75084-DE Kentucky Power Deliv - Ele | PRDFA | F3394 | CHARGING 2009 BKTS to SPEC-KENTUCKY | 0 |  | 0 |  |  | 233994.57 | 184000 | 49994.57 | 2009-12-22 | 2009-12-31 | 2009-12-01 | 2010-03-31
75084-DE Kentucky Power Deliv - Ele | AMKY0087 | F3404 | Dry Ridge 41 Reconductor | 0 |  | 0 |  |  | 344598.36 | 210608.08 | 133990.28 | 2009-12-22 | 2011-06-01 | 2010-04-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FPTLOADKE | F3706 | PTLOAD-TOOL TO RATE TRNSF-KENTUCKY | 0 |  | 0 |  |  | 13342.02 | 14000 | -657.98 | 2010-01-05 | 2010-10-31 | 2010-03-01 | 2011-03-08
75084-DE Kentucky Power Deliv - Ele | RELDFA | F3824 | eMax#213832 Ky 237 Camp Ernst-Pleas | 0 |  | 0 |  |  | 179894.38 | 175000 | 4894.38 | 2010-01-08 | 2015-01-06 | 2010-01-01 | 2010-10-07
75084-DE Kentucky Power Deliv - Ele | X02U8310 | F4206 | Buffington - Replace CB 682 | 0 |  | 0 |  |  | 273166.29 | 170830 | 102336.29 | 2010-01-19 | 2012-03-31 | 2011-01-01 | 2012-02-11
75084-DE Kentucky Power Deliv - Ele | UGCRFA | F5109 | eMax#395612 AMSTERDAM VILLAGE | 0 |  | 0 |  |  | 113614.48 | 124734.81 | -11120.33 | 2010-02-09 | 2010-12-31 | 2010-03-01 | 2010-10-28
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F5724 | Kenton Repl F6282 Carrier | 0 |  | 0 |  |  | 2.6193e-12 | 48596 | -48596 | 2010-02-23 | 2011-10-31 | 2010-04-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | FSRVCO201 | F5864 | PLS-CADD TO EMAX INTEGRATION | 0 |  | 0 |  |  | 21383.16 | 21313.15 | 70.01 | 2010-02-25 | 2010-11-30 | 2010-02-01 | 2010-02-28
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | F7484 | EMAX#523406 Crescent 43 Reliability | 0 |  | 0 |  |  | 30288.5 | 26432.28 | 3856.22 | 2010-04-23 | 2010-12-31 | 2010-06-01 | 2011-02-06
75084-DE Kentucky Power Deliv - Ele | RELDFA | F7846 | RI-Industrial Rd-Dixie to Turkeyfot | 0 |  | 0 |  |  | 96927.03 | 1295335.09 | -1198408.06 | 2010-04-27 | 2013-03-31 | 2010-05-01 | 2012-08-20
75084-DE Kentucky Power Deliv - Ele | RELDFA | F8924 | EMAX #585031 Johns Hill Rd | 0 |  | 0 |  |  | 243710.6 | 64812.17 | 178898.43 | 2010-06-01 | 2013-04-01 | 2010-06-01 | 2012-10-31
75084-DE Kentucky Power Deliv - Ele | RELDFA | F9264 | EMAX #462348 31 Eastern Avenue | 0 |  | 0 |  |  | 111543.39 | 35495.98 | 76047.41 | 2010-06-08 | 2010-12-31 | 2010-06-01 | 2010-12-21
75084-DE Kentucky Power Deliv - Ele | RELDFA | F9407 | EMAX 613555 RI-Taylor Mil Rd Recon | 0 |  | 0 |  |  | 1014861.69 | 885879.22 | 128982.47 | 2010-06-10 | 2012-05-31 | 2010-06-01 | 2012-02-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | F9524 | Marshall rep VR 41 phase1 | 0 |  | 0 |  |  | 10240.99 | 6519 | 3721.99 | 2010-06-15 | 2010-08-18 | 2010-06-01 | 2010-09-16
75084-DE Kentucky Power Deliv - Ele | DETCONFA | F9909 | Old 17 & Hempling Deteriorated Cond | 0 |  | 0 |  |  | 50277.92 | 48874.54 | 1403.38 | 2010-06-25 | 2012-10-31 | 2010-07-01 | 2012-03-29
75084-DE Kentucky Power Deliv - Ele | RLFA | FMSWGRR | Florence Mall Sw-gear Repl Program | 0 |  | 0 |  |  | 0 | 65000 | -65000 | 2013-01-29 | 2015-12-31 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | FNCTOFF | PD Indirect Offset | 0 |  | 0 |  |  | -2.07 |  | -2.07 | 2008-07-01 | 2008-06-28 21:34 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FRMRE12RR | FRM12INFR | 2012 COMM REPL INFRASTR-KEN | 0 |  | 0 |  |  | 156869.34 | 156870 | -0.66 | 2012-05-02 | 2014-04-30 | 2012-05-01 | 2014-05-31
75084-DE Kentucky Power Deliv - Ele | FRMRE13RR | FRM13INFR | 2013 PD COMM REPL INFRA-KENT | 26801.74 |  | 26801.74 | 100% |  | 169659.36 | 73868 | 95791.36 | 2013-02-22 | 2015-07-30 | 2013-03-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0124 | Donaldson replace control batteries | 0 |  | 0 |  |  | 9962.83 | 10964 | -1001.17 | 2010-07-06 | 2010-09-30 | 2010-08-01 | 2010-11-17
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G0125 | Beaver replace voltage regulator | 0 |  | 0 |  |  | 10229.64 | 6232 | 3997.64 | 2010-07-06 | 2010-12-31 | 2010-07-01 | 2010-10-03
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0267 | Whites Tower 41 Sec 2 Hempfling Rd | 0 |  | 0 |  |  | 29428.7 | 42269.4 | -12840.7 | 2010-07-08 | 2012-06-15 | 2010-09-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0268 | Whites Tower 41 Madison Pk | 0 |  | 0 |  |  | 42418.71 | 25233.86 | 17184.85 | 2010-07-08 | 2012-07-31 | 2010-07-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0269 | Whites Tower 41 Sec 1 Madison Pk | 0 |  | 0 |  |  | 39341.78 | 47652.76 | -8310.98 | 2010-07-08 | 2012-07-31 | 2010-11-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0270 | Whites Tower 41 Sec 2 Madison Pk | 0 |  | 0 |  |  | 25828.63 | 34249.73 | -8421.1 | 2010-07-08 | 2012-07-31 | 2010-11-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | AMOH0389 | G0347 | Augustine | 0 |  | 0 |  |  | 19869.34 | 8800 | 11069.34 | 2010-07-13 | 2011-03-31 | 2010-08-01 | 2010-12-16
75084-DE Kentucky Power Deliv - Ele | AMOH0389 | G0348 | Donaldson | 0 |  | 0 |  |  | 28793.65 | 9240 | 19553.65 | 2010-07-13 | 2011-03-31 | 2010-09-01 | 2010-12-14
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G0397 | Wilder replace drive | 0 |  | 0 |  |  | 12308.24 | 16253 | -3944.76 | 2010-08-31 | 2010-12-31 | 2010-10-01 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0425 | Hempfling Rd e/o Madison Sec 3 | 0 |  | 0 |  |  | 27144.97 | 20930.73 | 6214.24 | 2010-07-14 | 2012-07-31 | 2010-07-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0529 | Old Madison Pk & Pony Dr Det Cond | 0 |  | 0 |  |  | 816.97 | 405.77 | 411.2 | 2010-07-20 | 2010-12-31 | 2010-09-01 | 2011-01-04
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0530 | Gleason Rd & Madison Pk Det Cond | 0 |  | 0 |  |  | 77346.52 | 33812.48 | 43534.04 | 2010-07-20 | 2012-07-31 | 2010-09-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0531 | Spillman & Madison Pk Det Cond | 0 |  | 0 |  |  | 3789.54 | 8361.34 | -4571.8 | 2010-07-21 | 2010-12-31 | 2010-10-01 | 2011-02-24
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G0660 | RELIABILITY - DECLARED CIRCUIT CRES | 0 |  | 0 |  |  | 17836.89 | 1 | 17835.89 | 2010-08-06 | 2010-12-31 | 2010-08-01 | 2011-03-20
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0670 | Alexandria S repl control batteries | 0 |  | 0 |  |  | 2117.18 | 1690 | 427.18 | 2010-08-10 | 2010-12-31 | 2010-08-01 | 2010-12-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0691 | Buffington install LTC filter | 0 |  | 0 |  |  | 6753.79 | 10623 | -3869.21 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2010-12-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0696 | Constance install LTC filter | 0 |  | 0 |  |  | 7681.26 | 11023 | -3341.74 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2011-01-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0701 | Wilder install LTC filter | 0 |  | 0 |  |  | 9788.56 | 10623 | -834.44 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2010-12-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0732 | Grant repl station control battery | 0 |  | 0 |  |  | 1116.77 | 1690 | -573.23 | 2010-08-12 | 2010-12-30 | 2010-09-01 | 2010-12-14
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0734 | Marshall replace reclosers | 1758.66 |  | 1758.66 | 100% |  | 2399.15 | 862 | 1537.15 | 2010-08-13 | 2010-12-31 | 2010-08-01 | 2010-11-16
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G0763 | DECLARED CIRCUIT CRESCENT "43" | 0 |  | 0 |  |  | 111432.32 | 7845.62 | 103586.7 | 2010-08-18 | 2011-01-11 | 2010-08-01 | 2011-03-06
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G0819 | Alexandria South replace sidewalk | 0 |  | 0 |  |  | 4984.1 | 3390 | 1594.1 | 2010-08-30 | 2010-12-31 | 2010-09-01 | 2010-11-24
75084-DE Kentucky Power Deliv - Ele | AMKY0326 | G0849 | Augustine 43 TP for Repl Cable | 0 |  | 0 |  |  | 42104.06 | 5315.07 | 36788.99 | 2010-09-01 | 2011-09-30 | 2011-03-01 | 2011-06-10
75084-DE Kentucky Power Deliv - Ele | AMKY0326 | G0852 | Augustine 43 PILC Cable Replacement | 0 |  | 0 |  |  | 167386.29 | 201531 | -34144.71 | 2010-09-01 | 2011-09-30 | 2010-10-01 | 2011-06-14
75084-DE Kentucky Power Deliv - Ele | RELDFA | G0973 | EMAX #1009228 Taylor Mill Reconst | 0 |  | 0 |  |  | 21838.71 | 109860.93 | -88022.22 | 2010-09-14 | 2015-06-30 | 2010-09-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1158 | Oakbrook repl TB 1 X3 bushing | 0 |  | 0 |  |  | 7121.45 | 4092 | 3029.45 | 2010-09-30 | 2012-06-15 | 2010-12-01 | 2013-04-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1261 | Villa inst LTC filter on TB 1 | 0 |  | 0 |  |  | 15975.45 | 10623 | 5352.45 | 2010-10-07 | 2012-06-15 | 2010-10-01 | 2012-08-11
75084-DE Kentucky Power Deliv - Ele | 107DSTOH | G1407 | ROLLUP PLH IK_KY_2008 | 0 |  | 0 |  |  | 4300519.49 |  | 4300519.49 | 2010-10-27 | 2010-03-31 | 2010-10-01 | 2010-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1416 | ROLLUP PLH IK_KY_2009 | 0 |  | 0 |  |  | 1508495.94 | 200 | 1508295.94 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1419 | ROLLUP PLH IK_KY_2007 | 0 |  | 0 |  |  | 6127147.35 | 200 | 6126947.35 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2008-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1420 | ROLLUP PLH IK_KY_2006 | 0 |  | 0 |  |  | 7382097.31 | 200 | 7381897.31 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2007-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1421 | ROLLUP PLH IK_KY_2005 | 0 |  | 0 |  |  | 3720153.83 | 200 | 3719953.83 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2006-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1422 | ROLLUP PLH IK_KY_2004 | 0 |  | 0 |  |  | 2349020.4 | 200 | 2348820.4 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2005-03-31
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1434 | EMAX 1347776 Constance 42 Decl Circ | 0 |  | 0 |  |  | 20086.8 | 14091 | 5995.8 | 2010-11-01 | 2011-12-31 | 2010-11-01 | 2011-11-19
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1435 | EMAX 1347974 Crescent 44 Decl Circ | -4123.74 |  | -4123.74 | 100% |  | 84108.61 | 25455.88 | 58652.73 | 2010-11-01 | 2013-03-31 | 2010-11-01 | 2013-01-15
75084-DE Kentucky Power Deliv - Ele | FFLDMTREQ | G1528 | REPL OF FIELD METER TEST EQUIP | 0 |  | 0 |  |  | 65356.9 | 75630 | -10273.1 | 2010-11-18 | 2012-03-31 | 2011-12-01 | 2012-06-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G1558 | EMAX 1417885 15 Spiral Dr | 0 |  | 0 |  |  | 74303.72 | 72834.39 | 1469.33 | 2010-11-29 | 2012-04-30 | 2011-05-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1561 | Claryville TB 2,3 replace fans | 0 |  | 0 |  |  | 4408.9 | 3303 | 1105.9 | 2010-11-29 | 2011-05-31 | 2011-01-01 | 2011-05-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1562 | Kentucky Univ TB 4 replace fans | 0 |  | 0 |  |  | 11272.01 | 4021 | 7251.01 | 2010-11-29 | 2011-08-31 | 2011-01-01 | 2011-05-16
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1563 | Limaburg TB 2 replace fans | 0 |  | 0 |  |  | 5044.69 | 2872 | 2172.69 | 2010-11-29 | 2011-08-31 | 2011-01-01 | 2011-05-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1564 | Marshall TB 1 replace fans | 0 |  | 0 |  |  | 5611.87 | 2872 | 2739.87 | 2010-11-29 | 2011-12-31 | 2011-01-01 | 2011-09-29
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G1654 | EMAX 1549494 15 Spiral Dr | 0 |  | 0 |  |  | 21078.52 | 14555.58 | 6522.94 | 2010-12-13 | 2011-12-31 | 2011-05-01 | 2011-12-08
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G1661 | EMAX 1786573 URD 184 Richwood | 0 |  | 0 |  |  | 415673.18 | 585415.78 | -169742.6 | 2010-12-15 | 2013-03-31 | 2010-12-01 | 2011-07-29
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G1662 | Dayton install drainage system | 0 |  | 0 |  |  | 3853.99 | 3447 | 406.99 | 2010-12-15 | 2011-03-31 | 2010-12-01 | 2011-03-11
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1670 | Crescent TB 2 replace ETM | 0 |  | 0 |  |  | 10782.08 | 5953 | 4829.08 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1671 | Dixie TB2 replace ETM | 0 |  | 0 |  |  | 6817.04 | 5953 | 864.04 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-15
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1672 | Hands TB 1 replace ETM | 0 |  | 0 |  |  | 7187.2 | 5953 | 1234.2 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-19
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1675 | Wilder TB 3 replace ETM | 0 |  | 0 |  |  | 10922.24 | 5953 | 4969.24 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-21
75084-DE Kentucky Power Deliv - Ele | RLFA | G1729 | ROLLUP PLH IK_KY_2010_BLKT_Rollup | 0 |  | 0 |  |  | 7488699.49 | 200 | 7488499.49 | 2010-12-22 | 2050-12-31 | 2010-12-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1756 | EMAX 1696749 Constance 42 Decl Circ | 0 |  | 0 |  |  | 24487.71 | 16690.26 | 7797.45 | 2011-01-04 | 2013-03-31 | 2011-01-01 | 2012-08-07
75084-DE Kentucky Power Deliv - Ele | AMKY0412 | G1816 | Wilder 44 PILC Cable Replace | 0 |  | 0 |  |  | 42551.42 | 63469 | -20917.58 | 2011-01-10 | 2011-10-31 | 2011-03-01 | 2011-06-29
75084-DE Kentucky Power Deliv - Ele | AMKY0412 | G1817 | Wilder 44 PILC Install Cable | 0 |  | 0 |  |  | 77317.2 | 22682 | 54635.2 | 2011-01-10 | 2011-10-31 | 2011-02-01 | 2011-06-29
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1950 | Buffington TB 3 replace bushing | 0 |  | 0 |  |  | 5339.87 | 5214 | 125.87 | 2011-01-24 | 2012-06-15 | 2011-04-01 | 2012-02-05
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2194 | EMAX 1737953 NKU Univ Dr Ext | 10188.22 |  | 10188.22 | 100% |  | 9571.1 | 401620.62 | -392049.52 | 2011-02-08 | 2014-09-08 | 2011-02-01 | 2013-02-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G2222 | Donaldson TB 1 replace fans | 0 |  | 0 |  |  | 3698.38 | 4325 | -626.62 | 2011-02-09 | 2011-12-31 | 2011-03-01 | 2011-06-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G2254 | Decoursey replace reclosers | 1758.66 |  | 1758.66 | 100% |  | 2235.41 | 431 | 1804.41 | 2011-02-11 | 2011-05-31 | 2011-02-01 | 2011-05-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G2301 | Decoursey TB 3 failure | 0 |  | 0 |  |  | 33472.65 | 10066 | 23406.65 | 2011-02-15 | 2011-04-30 | 2011-02-01 | 2011-05-24
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2456 | EMAX 1983805 RI-Hands Pk w/o KY 16 | 0 |  | 0 |  |  | 66191.75 | 39319.39 | 26872.36 | 2011-03-01 | 2015-02-01 | 2011-03-01 | 2011-08-16
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2535 | EMAX 1783672 7660 Turfway Rd | 0 |  | 0 |  |  | 73189.28 | 74947.26 | -1757.98 | 2011-03-04 | 2012-03-31 | 2011-03-01 | 2012-02-04
75084-DE Kentucky Power Deliv - Ele | FEMSUPGRD | G2860 | EMS EMP 2.6 UPGRADE PROJECT | 0 |  | 0 |  |  | 64278.93 | 2293 | 61985.93 | 2011-03-30 | 2014-06-30 | 2011-07-01 | 2014-06-30
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G2918 | EMAX 2176614 Viewpoint Dr | 0 |  | 0 |  |  | 189414.82 | 137595.61 | 51819.21 | 2011-04-05 | 2012-12-31 | 2011-04-01 | 2012-08-17
75084-DE Kentucky Power Deliv - Ele | AMKY0474 | G2953 | Constance Install TLS | 0 |  | 0 |  |  | 255060.57 | 140864 | 114196.57 | 2011-04-07 | 2012-09-01 | 2011-04-01 | 2012-04-18
75084-DE Kentucky Power Deliv - Ele | AMKY0474 | G2957 | Villa F2862 Reclosing | 0 |  | 0 |  |  | 35714.36 | 12898 | 22816.36 | 2011-04-08 | 2012-03-31 | 2011-06-01 | 2012-02-07
75084-DE Kentucky Power Deliv - Ele | FAUTODESK | G3197 | AUTODESK 2012 UPGRADE | 0 |  | 0 |  |  | 10289.91 | 8429 | 1860.91 | 2011-05-02 | 2011-09-30 | 2011-05-01 | 2012-02-09
75084-DE Kentucky Power Deliv - Ele | AMKY0088 | G3276 | Mt Zion Rd Reconductor 2 | 0 |  | 0 |  |  | 250891.08 | 663636.23 | -412745.15 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-05-14
75084-DE Kentucky Power Deliv - Ele | AMKY0088 | G3277 | Mt Zion Rd Reconductor 2 (RLE) | 0 |  | 0 |  |  | 708.64 | 20892 | -20183.36 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-03-01
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3363 | Kenton Repl Circuit 45 Cable | 0 |  | 0 |  |  | 4132.92 | 18455 | -14322.08 | 2011-05-17 | 2012-09-30 | 2011-07-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3364 | Kenton 45 PILC Cable Replace OH | 0 |  | 0 |  |  | 109847.67 | 108000 | 1847.67 | 2011-05-17 | 2012-09-30 | 2012-10-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3365 | Kenton 45 PILC Cable Replace UG | 0 |  | 0 |  |  | 27411.39 | 39665.9 | -12254.51 | 2011-05-17 | 2012-09-30 | 2011-09-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G3647 | EMAX 2346184 URD 105 Country Squire | 0 |  | 0 |  |  | 99612.1 | 119746.44 | -20134.34 | 2011-06-10 | 2013-03-31 | 2011-06-01 | 2012-04-19
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3700 | Claryville Recloser Replace | 0 |  | 0 |  |  | 465838.15 | 353172 | 112666.15 | 2011-06-16 | 2013-03-31 | 2011-07-01 | 2012-09-02
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G3736 | EMAX 2374342 Crescent 44 Decl circ | 0 |  | 0 |  |  | 14220.23 | 8850.15 | 5370.08 | 2011-06-21 | 2014-03-31 | 2011-08-01 | 2013-07-15
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3757 | Wilder F5962 Reclosing | 0 |  | 0 |  |  | 15848.51 | 19626 | -3777.49 | 2011-06-22 | 2013-03-31 | 2011-11-01 | 2012-09-26
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3773 | Claryville Inst Auto Throw Over | 0 |  | 0 |  |  | 97596.89 | 121949 | -24352.11 | 2011-06-23 | 2013-03-31 | 2011-07-01 | 2012-09-26
75084-DE Kentucky Power Deliv - Ele | X02U8885 | G3793 | Wilder Replace CB 650 | 0 |  | 0 |  |  | 199403.84 | 147094 | 52309.84 | 2011-06-24 | 2013-03-31 | 2011-11-01 | 2013-03-18
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G3813 | EMAX 2389938 Oakbrook 41 Det | 0 |  | 0 |  |  | 52381.75 | 31170 | 21211.75 | 2011-06-27 | 2011-12-31 | 2011-07-01 | 2012-02-02
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3956 | Constance 41-44 Circuits | 0 |  | 0 |  |  | 454677.69 | 262120 | 192557.69 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-04-27
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3957 | Crescent 41-44 Circuits | 0 |  | 0 |  |  | 182951.42 | 195258 | -12306.58 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-07-13
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3958 | Villa Sub 41-44 Circuits | 0 |  | 0 |  |  | 427855.42 | 195570 | 232285.42 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-09-08
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3959 | Kenton Circuits 41-46 | 0 |  | 0 |  |  | 223038.02 | 228652 | -5613.98 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-05-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4004 | Bellevue TB2 Install LTC Filter | 0 |  | 0 |  |  | 11027.59 | 11956 | -928.41 | 2011-07-11 | 2012-03-31 | 2011-07-01 | 2012-03-10
75084-DE Kentucky Power Deliv - Ele | 314G8900 | G4034 | Aug 44 Ext Conv Latonia 4kV | 0 |  | 0 |  |  | 665967.65 | 298387.83 | 367579.82 | 2011-07-13 | 2012-04-30 | 2011-07-01 | 2012-04-28
75084-DE Kentucky Power Deliv - Ele | AMKY0085 | G4117 | Wilder 13.2kV Bus | 0 |  | 0 |  |  | 2332545.27 | 854373 | 1478172.27 | 2011-07-21 | 2014-03-31 | 2012-06-01 | 2013-08-09
75084-DE Kentucky Power Deliv - Ele | FEGIS/EMX | G4142 | EGIS/eMAX PD DEVICE INTEGRATION | 0 |  | 0 |  |  | 12059.65 | 16725 | -4665.35 | 2011-07-22 | 2012-10-30 | 2011-07-01 | 2012-09-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4167 | Florence TB 2 instal LTC & 2 fans | 0 |  | 0 |  |  | 11201.45 | 14317 | -3115.55 | 2011-07-26 | 2011-12-31 | 2011-07-01 | 2012-03-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4174 | Donaldson TB 2 instl LTC filter | 0 |  | 0 |  |  | 11099.84 | 13136 | -2036.16 | 2011-07-27 | 2012-06-15 | 2011-07-01 | 2012-03-17
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G4175 | Kenton replace control battery | 0 |  | 0 |  |  | 15190.97 | 18188 | -2997.03 | 2011-07-27 | 2011-12-31 | 2011-08-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G4179 | Kenton resurface entire pavement | 0 |  | 0 |  |  | 6032.09 | 8222 | -2189.91 | 2011-07-27 | 2011-12-31 | 2011-11-01 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | FEMSFIREW | G4243 | EMS FIREWALL PROJ HW KENTUCKY | 0 |  | 0 |  |  | 988.52 | 43364.26 | -42375.74 | 2011-08-01 | 2012-04-01 | 2011-12-01 | 2012-07-31
75084-DE Kentucky Power Deliv - Ele | NBFA | G4362 | EMAX 2432584 Envision Center | 0 |  | 0 |  |  | 18126.21 | 45510.74 | -27384.53 | 2011-08-08 | 2012-03-31 | 2011-08-01 | 2012-01-25
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G4465 | Villa Install F2862 TLS | 0 |  | 0 |  |  | 43036.46 | 13804 | 29232.46 | 2011-08-12 | 2012-09-01 | 2011-10-01 | 2012-09-08
75084-DE Kentucky Power Deliv - Ele | RELTFA | G4535 | EMAX 2523185 Barnes Pike | 0 |  | 0 |  |  | 59.52 | 58402.19 | -58342.67 | 2011-08-18 | 2012-12-31 | 2011-09-01 | 2012-04-12
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G4599 | Wilder Repl 138kV CB No. 834 | 0 |  | 0 |  |  | 82257.49 | 12073 | 70184.49 | 2011-08-23 | 2011-12-16 | 2011-09-01 | 2011-11-26
75084-DE Kentucky Power Deliv - Ele | AMOH0424 | G4604 | 345kV Distr Clearance Capital (KY) | 0 |  | 0 |  |  | 1111.39 | 8867.53 | -7756.14 | 2011-08-24 | 2012-09-01 | 2012-02-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G4633 | EMAX 2541613 Richwood 41 Det Cond | 0 |  | 0 |  |  | 7686.57 | 6122.79 | 1563.78 | 2011-08-26 | 2012-04-30 | 2011-09-01 | 2012-03-04
75084-DE Kentucky Power Deliv - Ele | CSFA | G4676 | EMAX 2550566 G&W Viper Recloser | 0 |  | 0 |  |  | 74233.14 | 27446.94 | 46786.2 | 2011-08-30 | 2012-08-31 | 2011-09-01 | 2012-02-17
75084-DE Kentucky Power Deliv - Ele | FITRNFCSK | G4864 | REPL INTEGR-ITRON FCS-KENT. | 0 |  | 0 |  |  | 41470.26 | 145532 | -104061.74 | 2011-09-08 | 2012-12-31 | 2011-09-01 | 2013-02-12
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G4874 | Augustine Repl sta batteries | 0 |  | 0 |  |  | 13416.11 | 13690 | -273.89 | 2011-09-09 | 2012-03-31 | 2011-10-01 | 2012-01-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G5009 | White Tower Repl reclosers on c 41 | 1957.04 |  | 1957.04 | 100% |  | 1957.04 | 691 | 1266.04 | 2011-09-19 | 2011-12-30 | 2015-09-01 | 2011-12-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5013 | Florence Install LTC filter on TB 1 | 0 |  | 0 |  |  | 10672.06 | 11351 | -678.94 | 2011-09-20 | 2012-03-31 | 2011-09-01 | 2012-02-09
75084-DE Kentucky Power Deliv - Ele | AMKY0528 | G5038 | Grant 43 City of Williamstown | 0 |  | 0 |  |  | 1218.2 | 397192 | -395973.8 | 2011-09-21 | 2012-10-01 | 2011-09-01 | 2012-10-24
75084-DE Kentucky Power Deliv - Ele | FMDT11KE | G5048 | MOBILE DISPATCH EXPANSION-KE | 0 |  | 0 |  |  | 37648.52 | 46900 | -9251.48 | 2011-09-22 | 2012-09-30 | 2011-10-01 | 2012-12-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5463 | Constance instl LTC filter on TB 2 | 0 |  | 0 |  |  | 7380.68 | 10975.37 | -3594.69 | 2011-10-25 | 2012-09-30 | 2011-12-01 | 2012-04-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5484 | Augustine instl LTC filter on TB 1 | 0 |  | 0 |  |  | 7080.51 | 15041.51 | -7961 | 2011-10-26 | 2012-09-30 | 2011-12-01 | 2012-07-03
75084-DE Kentucky Power Deliv - Ele | RELDFA | G5515 | EMAX 2690060 377 Richwood Rd | 0 |  | 0 |  |  | 169.42 | 10846.41 | -10676.99 | 2011-10-27 | 2012-03-31 | 2011-11-01 | 2012-02-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5700 | Claryville repl X0,X1,X2,X3 bushing | 0 |  | 0 |  |  | 3910.89 | 14030.99 | -10120.1 | 2011-11-07 | 2012-09-30 | 2011-12-01 | 2012-08-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5800 | Hands repl cooling fans on TB 1 | 0 |  | 0 |  |  | 14912.34 | 15906.97 | -994.63 | 2011-11-14 | 2012-07-01 | 2011-12-01 | 2012-04-10
75084-DE Kentucky Power Deliv - Ele | NBFA | G5853 | EMAX 2516744 South Service Rd | 0 |  | 0 |  |  | 32109.43 | 58886.31 | -26776.88 | 2011-11-16 | 2012-12-31 | 2011-12-01 | 2012-08-21
75084-DE Kentucky Power Deliv - Ele | RELDFA | G5905 | EMAX 2760735 Camp Ernst (KY 237) | -1200.26 |  | -1200.26 | 100% |  | 83348.65 | 99082.68 | -15734.03 | 2011-11-21 | 2012-12-31 | 2012-02-01 | 2012-08-18
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G5938 | Thomas More remove eye wash station | 0 |  | 0 |  |  | 0 |  | 0 | 2011-11-23 | 2012-03-16 | 2014-04-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G5939 | Covington remove eye wash station | 0 |  | 0 |  |  | 0 |  | 0 | 2011-11-23 | 2012-03-16 | 2015-07-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6108 | Blackwell Sub security system | 0 |  | 0 |  |  | 82686.31 | 52677 | 30009.31 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6109 | Buffington Sub security system | 0 |  | 0 |  |  | 146449.24 | 90148 | 56301.24 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6112 | Silver Grove sub security system | 0 |  | 0 |  |  | 149197.11 | 91870 | 57327.11 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | CSFA | G6457 | EMAX 2834098 Second feed to UG syst | -788.32 |  | -788.32 | 100% |  | 84137.86 | 72167.47 | 11970.39 | 2012-01-11 | 2013-03-31 | 2012-01-01 | 2012-05-17
75084-DE Kentucky Power Deliv - Ele | RELTFA | G6487 | EMAX 2876458 RI-Turkeyfoot Rd | 0 |  | 0 |  |  | 108634.47 | 83949.57 | 24684.9 | 2012-01-16 | 2013-03-31 | 2012-01-01 | 2012-09-07
75084-DE Kentucky Power Deliv - Ele | NBFA | G6517 | EMAX 2869082 Post Glover Co | 0 |  | 0 |  |  | 18957.6 | 23028.16 | -4070.56 | 2012-01-19 | 2012-12-31 | 2012-02-01 | 2012-06-29
75084-DE Kentucky Power Deliv - Ele | AMKY0571 | G6550 | Augustine 41 PILC Cable Replace | -12856.92 |  | -12856.92 | 100% |  | 1289624.24 | 1124875 | 164749.24 | 2012-01-24 | 2013-03-31 | 2012-02-01 | 2013-02-28
75084-DE Kentucky Power Deliv - Ele | NBFA | G6573 | EMAX 2920684 15 Spiral Dr | 0 |  | 0 |  |  | 11667.36 | 3084.53 | 8582.83 | 2012-01-26 | 2012-12-31 | 2012-03-01 | 2012-06-27
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G6611 | Dixie replace cooling fans TB 1 | 0 |  | 0 |  |  | 7584.18 | 8328.02 | -743.84 | 2012-01-30 | 2012-07-01 | 2012-02-01 | 2012-05-15
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | G6619 | KY Dist Line Assoc w 138kV CLR | 0 |  | 0 |  |  | 619233.04 | 505780.19 | 113452.85 | 2012-01-30 | 2015-03-31 | 2013-01-01 | 2014-04-15
75084-DE Kentucky Power Deliv - Ele | RELDFA | G6642 | EMAX 2943027 KY 16 | 0 |  | 0 |  |  | 393948.82 | 404447.62 | -10498.8 | 2012-02-02 | 2013-03-31 | 2012-02-01 | 2012-12-12
75084-DE Kentucky Power Deliv - Ele | FBLDENCLO | G6683 | CCA/NON-CCA ENCLOSURE | 0 |  | 0 |  |  | 3421.65 | 2969.7 | 451.95 | 2012-02-06 | 2012-03-15 | 2012-02-01 | 2012-08-23
75084-DE Kentucky Power Deliv - Ele | CERTFA | G6716 | F2862 Emergency R/P switch 547 | 0 |  | 0 |  |  | 53352.23 | 52037.34 | 1314.89 | 2012-02-08 | 2013-03-31 | 2012-02-01 | 2012-05-08
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G6751 | EMAX 1334817 Dixie Hwy Crescent 43 | 0 |  | 0 |  |  | 19434.1 | 45426.06 | -25991.96 | 2012-02-14 | 2013-03-31 | 2012-09-01 | 2012-12-12
75084-DE Kentucky Power Deliv - Ele | RELDFA | G6791 | EMAX 2880825 Turkeyfoot Rd Dist | 0 |  | 0 |  |  | 9415.31 | 55503.22 | -46087.91 | 2012-02-16 | 2013-06-30 | 2012-03-01 | 2012-09-07
75084-DE Kentucky Power Deliv - Ele | AMKY0570 | G6835 | West End 1524 Aerial on Bridge (OH) | 0 |  | 0 |  |  | 483279.82 | 98746.32 | 384533.5 | 2012-02-21 | 2013-03-31 | 2012-03-01 | 2012-12-21
75084-DE Kentucky Power Deliv - Ele | FMDT11KE | G6983 | MWMS USER SW LICENSES | 0 |  | 0 |  |  | 3598.06 | 2973.6 | 624.46 | 2012-03-08 | 2012-06-30 | 2012-06-01 | 2012-09-05
75084-DE Kentucky Power Deliv - Ele | AMKY0729 | G7002 | Dayton KY Sub Purch 825 Walnut -RLE | 0 |  | 0 |  |  | 140420.41 | 128377 | 12043.41 | 2012-03-12 | 2013-03-31 | 2012-03-01 | 2013-02-02
75084-DE Kentucky Power Deliv - Ele | FTDITKY | G7195 | CC BLKT IT HW-ERLANGER, KE OP CTR | 0 |  | 0 |  |  | 15422.26 | 11000 | 4422.26 | 2012-04-10 | 2012-06-24 | 2012-05-01
75084-DE Kentucky Power Deliv - Ele | AMKY0668 | G7206 | Wilder 43 Cable | 0 |  | 0 |  |  | 12864.89 | 27135 | -14270.11 | 2012-04-12 | 2013-03-31 | 2012-07-01 | 2013-01-26
75084-DE Kentucky Power Deliv - Ele | AMKY0668 | G7210 | Wilder 43 PILC Replacement | 0 |  | 0 |  |  | 30891.12 | 34209 | -3317.88 | 2012-04-12 | 2013-03-31 | 2012-10-01 | 2013-01-26
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G7235 | Wilder repl CCVT & line tuner | 0 |  | 0 |  |  | 20303.82 | 14237.74 | 6066.08 | 2012-04-13 | 2013-01-31 | 2012-04-01 | 2013-01-18
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7273 | Buffington - KY SEL Dist Ckt Imprv | 0 |  | 0 |  |  | 438957.48 | 347883 | 91074.48 | 2012-04-17 | 2014-03-31 | 2012-04-01 | 2013-02-20
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7274 | Donaldson KY SEL Dist Ckt Imprv | 98.49 |  | 98.49 | 100% |  | 229859.22 | 174540 | 55319.22 | 2012-04-17 | 2015-03-31 | 2012-05-01 | 2014-09-14
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7275 | Dixie KY SEL Dist Ckt Imprv | 0 |  | 0 |  |  | 246233.02 | 174540 | 71693.02 | 2012-04-17 | 2014-03-31 | 2012-04-01 | 2013-06-15
75084-DE Kentucky Power Deliv - Ele | FSRVCOM12 | G7280 | SUBSTATION DESIGN SOLUTION | 0 |  | 0 |  |  | 89527.8 | 770000 | -680472.2 | 2012-04-18 | 2011-07-01 | 2012-05-01 | 2011-06-25
75084-DE Kentucky Power Deliv - Ele | X03U8875 | G7392 | Donaldson TB1 TB2 Transrupters | 0 |  | 0 |  |  | 252759.6 | 248446 | 4313.6 | 2012-05-02 | 2015-03-31 | 2012-05-01 | 2014-09-14
75084-DE Kentucky Power Deliv - Ele | X03U9003 | G7393 | Florence TB1 TB2 TB4 | 62549.08 |  | 62549.08 | 100% |  | 662220 | 320573 | 341647 | 2012-05-02 | 2015-03-31 | 2012-05-01 | 2015-01-14
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G7406 | Silver Grove install ETM on TB 23 | 0 |  | 0 |  |  | 18593.04 | 7314.39 | 11278.65 | 2012-05-04 | 2012-11-30 | 2012-05-01 | 2012-10-13
75084-DE Kentucky Power Deliv - Ele | 303G8901 | G7533 | Latonia Sub - Retire & Remove | 0 |  | 0 |  |  | 0 |  | 0 | 2012-05-15 | 2014-03-31 | 2014-08-01 | 2013-09-06
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7624 | Buffington replace ETM on TB 2 | 0 |  | 0 |  |  | 14778.92 | 6868 | 7910.92 | 2012-05-22 | 2013-03-31 | 2012-07-01 | 2012-10-25
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7630 | Buffington replace ETM TB 7 | 0 |  | 0 |  |  | 18129.78 | 7751.94 | 10377.84 | 2012-05-23 | 2013-03-31 | 2012-07-01 | 2012-11-02
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7631 | Buffington replace ETM TB 4 | 0 |  | 0 |  |  | 11288.6 | 6868 | 4420.6 | 2012-05-23 | 2013-03-31 | 2012-07-01 | 2012-10-26
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G7646 | Buffington H2 bushing changeout TB3 | -2176.02 |  | -2176.02 | 100% |  | -328.26 | 6701.56 | -7029.82 | 2012-05-24 | 2012-08-31 | 2012-05-01 | 2012-08-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G7835 | Grant replace CB 211 after failure | -833.67 |  | -833.67 | 100% |  | 8290.23 | 7996.62 | 293.61 | 2012-06-12 | 2012-12-22 | 2012-06-01 | 2012-11-16
75084-DE Kentucky Power Deliv - Ele | FCAORMRPL | G8039 | CAORM REPLACEMENT PROJ. | 0 |  | 0 |  |  | 1.0658e-14 | 1 | -1 | 2012-07-11 | 2013-08-30 | 2012-08-01 | 2013-09-25
75084-DE Kentucky Power Deliv - Ele | AMKY0750 | G8124 | Line Capacitor Installs for KY 2012 | 0 |  | 0 |  |  | 44560.81 | 53967.22 | -9406.41 | 2012-07-27 | 2013-03-31 | 2012-08-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8336 | Crescent Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 8564.79 | 24507 | -15942.21 | 2012-08-27 | 2014-03-31 | 2012-10-01 | 2013-12-06
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8338 | Kenton Upgrage Frame Relay Equip | 0 |  | 0 |  |  | 13966.48 | 40175 | -26208.52 | 2012-08-27 | 2014-03-31 | 2012-10-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8339 | Long Branch Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 32120.9 | 49736 | -17615.1 | 2012-08-27 | 2014-03-31 | 2012-11-01 | 2013-07-17
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8340 | Oakbrook Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 29745.64 | 49736 | -19990.36 | 2012-08-27 | 2014-03-31 | 2012-11-01 | 2014-01-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8347 | Wilder repl H1 bushing TB 3 | 0 |  | 0 |  |  | 7261.43 | 7496.55 | -235.12 | 2012-08-28 | 2012-12-28 | 2012-09-01 | 2013-03-06
75084-DE Kentucky Power Deliv - Ele | RELDFA | G8369 | RI emax 2836864 Madison Ave | -82934.85 |  | -82934.85 | 100% |  | 42948.78 | 68931.29 | -25982.51 | 2012-08-30 | 2015-05-07 | 2012-09-01 | 2015-03-12
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8409 | Limaburg Sub security system | 0 |  | 0 |  |  | 58231.92 | 40000 | 18231.92 | 2012-09-06 | 2013-09-30 | 2012-09-01 | 2014-08-31
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8416 | Claryville TB2 Bank failure | 0 |  | 0 |  |  | 22979.54 | 24962.54 | -1983 | 2012-09-10 | 2012-12-28 | 2012-09-01 | 2012-12-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8420 | Donaldson Sub security system | 0 |  | 0 |  |  | 50345.99 | 40000 | 10345.99 | 2012-09-10 | 2013-03-31 | 2012-09-01 | 2014-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8423 | Wilder Sub security system | 0 |  | 0 |  |  | 102608.81 | 90000 | 12608.81 | 2012-09-10 | 2013-03-31 | 2012-09-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | G8553 | ST emax 2178946 John Hills Rd NKU | 0 |  | 0 |  |  | 48605 | 105449.16 | -56844.16 | 2012-10-01 | 2014-03-15 | 2012-11-01 | 2013-06-05
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G8576 | Wilder rem fence & instl animal fen | 0 |  | 0 |  |  | 351875.96 | 300599.26 | 51276.7 | 2012-10-03 | 2013-03-07 | 2012-10-01 | 2013-03-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8589 | Claryville CIR 42 repl Phase A VR | 8663.14 |  | 8663.14 | 100% |  | 12895.47 | 2262.25 | 10633.22 | 2012-10-05 | 2013-01-19 | 2012-10-01 | 2013-01-10
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8666 | Buffington TB 1 Cooler Replacement | 0 |  | 0 |  |  | 209704.63 | 187956.46 | 21748.17 | 2012-10-15 | 2014-03-01 | 2013-01-01 | 2014-02-10
75084-DE Kentucky Power Deliv - Ele | NBFA | G8713 | NB emax 3478683 1780 Anderson Blvd | 0 |  | 0 |  |  | 17799.34 | 14010.05 | 3789.29 | 2012-10-22 | 2013-10-30 | 2013-01-01 | 2013-06-04
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8780 | Decoursey CIR 41 repl 3 reclosers | 1758.66 |  | 1758.66 | 100% |  | 4358.34 | 1131.12 | 3227.22 | 2012-11-01 | 2013-02-02 | 2012-11-01 | 2013-02-02
75084-DE Kentucky Power Deliv - Ele | AMKY0592 | G8851 | Wilder Replace DE KY CB741 | 80950.99 |  | 80950.99 | 100% |  | 237224.92 | 174808 | 62416.92 | 2012-11-07 | 2015-03-31 | 2012-11-01 | 2015-02-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8885 | Limaburg repl HS bushings&LAs TB 2 | 0 |  | 0 |  |  | 18866.47 | 12414.78 | 6451.69 | 2012-11-12 | 2013-09-28 | 2013-02-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8886 | Limaburg repl HS LAs&LS bushingsTB1 | 0 |  | 0 |  |  | 12132.74 | 10541.3 | 1591.44 | 2012-11-12 | 2013-12-27 | 2013-02-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | FTIMPHAII | G8986 | TIM PHASE II UPGRADE | 0 |  | 0 |  |  | 301140.04 | 187081 | 114059.04 | 2012-11-26 | 2014-12-30 | 2012-12-01 | 2014-06-24
75084-DE Kentucky Power Deliv - Ele | RLFA | G9018 | NW emax 3205166 18th & Banklick | 0 |  | 0 |  |  | 42809.67 | 32465.77 | 10343.9 | 2012-12-03 | 2014-03-31 | 2012-12-01 | 2013-06-24
75084-DE Kentucky Power Deliv - Ele | RELDFA | G9056 | RI emax 2760735 Camp Ernst (KY 237) | 0 |  | 0 |  |  | 537669.43 | 530030.09 | 7639.34 | 2012-12-06 | 2013-09-07 | 2012-12-01 | 2013-06-02
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9064 | Wilder CB650 repl 2 bus disconnects | 15763.56 |  | 15763.56 | 100% |  | 40410.24 | 32086.93 | 8323.31 | 2012-12-10 | 2013-12-30 | 2013-10-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G9111 | CR emax 3705007 Heritage Trails | 1478.84 |  | 1478.84 | 100% |  | 108295.1 | 85982.93 | 22312.17 | 2012-12-18 | 2015-06-30 | 2013-04-01 | 2014-01-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G9113 | Bellevue TB 1 repl HS arresters | 0 |  | 0 |  |  | 5681.9 | 4178.77 | 1503.13 | 2012-12-18 | 2013-09-28 | 2013-02-01 | 2013-08-15
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9117 | Wilder repl pos 1&5 bushings CB831 | 0 |  | 0 |  |  | 12011.82 | 8924.05 | 3087.77 | 2012-12-19 | 2013-06-29 | 2013-03-01 | 2013-06-18
75084-DE Kentucky Power Deliv - Ele | RELDFA | G9119 | RI emax 3707725 5th to 8th | -88896.7 |  | -88896.7 | 100% |  | 4138.93 | 66480.15 | -62341.22 | 2012-12-19 | 2014-10-09 | 2012-12-01 | 2014-09-04
75084-DE Kentucky Power Deliv - Ele | AVAMARUPG | G9122 | EMPCS-AVAMAR UPGRADE | 0 |  | 0 |  |  | 140465.13 | 141000 | -534.87 | 2012-12-19 | 2013-05-30 | 2012-12-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | FESXIUPGR | G9133 | EMPCS-ESXI UPGRADE | 0 |  | 0 |  |  | 8288.7 | 8082.45 | 206.25 | 2012-12-20 | 2013-09-30 | 2012-12-01 | 2013-12-25
75084-DE Kentucky Power Deliv - Ele | FDOMSIMPL | G9136 | DOMS IMPLEMENTATION W/AMI | 5381.11 |  | 5381.11 | 100% |  | 9344.36 | 216000 | -206655.64 | 2012-12-20 | 2017-03-31 | 2013-01-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9139 | Florence repl sw,motor,whip ABS859 | 0 |  | 0 |  |  | 45937.86 | 45872.32 | 65.54 | 2012-12-26 | 2013-12-27 | 2013-02-01 | 2014-03-13
75084-DE Kentucky Power Deliv - Ele | ITKYFR13D | G9165 | Hebron Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 29302.18 | 39226 | -9923.82 | 2013-01-03 | 2014-09-01 | 2013-05-01 | 2013-10-10
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9171 | DC emax 3744831 Kenton 42 Decl | 0 |  | 0 |  |  | 43651.73 | 33907.39 | 9744.34 | 2013-01-03 | 2014-03-31 | 2013-01-01 | 2013-07-09
75084-DE Kentucky Power Deliv - Ele | AMKY0806 | G9259 | Dist Line Cap Inst for KY 2013 | 0 |  | 0 |  |  | 74827.97 | 70413.44 | 4414.53 | 2013-01-14 | 2014-03-31 | 2013-01-01 | 2013-10-08
75084-DE Kentucky Power Deliv - Ele | NBFA | G9304 | NB emax 3777704 7979 Vulcan Dr | 0 |  | 0 |  |  | 35799.65 | 16278.41 | 19521.24 | 2013-01-17 | 2014-01-31 | 2013-04-01 | 2013-10-18
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | G9311 | F5967 138kV Clear Correct OH | 0 |  | 0 |  |  | 32930.29 | 26000 | 6930.29 | 2013-01-18 | 2015-03-31 | 2013-01-01 | 2014-01-05
75084-DE Kentucky Power Deliv - Ele | AMKY0849 | G9410 | F5962 Re-route at NKU | 0 |  | 0 |  |  | 792.48 | 139526 | -138733.52 | 2013-01-31 | 2014-03-31 | 2013-02-01 | 2013-08-24
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G9501 | DET emax 3873582 Murman Rd | 0 |  | 0 |  |  | 327179.97 | 193581.9 | 133598.07 | 2013-02-14 | 2014-03-31 | 2013-02-01 | 2014-01-02
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9684 | DC 3925631 Kenton 42 | -10474.14 |  | -10474.14 | 100% |  | 125214.31 | 41957.09 | 83257.22 | 2013-03-05 | 2014-03-31 | 2013-04-01 | 2014-02-23
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G9825 | Silver Grove Repl fans on TB 23 | 0 |  | 0 |  |  | 34060.17 | 36332.39 | -2272.22 | 2013-03-25 | 2013-12-31 | 2013-05-01 | 2013-09-07
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9849 | DC emax 3983251 White Tower 41 | -9518.5 |  | -9518.5 | 100% |  | 106542.75 | 50988.41 | 55554.34 | 2013-03-26 | 2014-03-31 | 2013-04-01 | 2013-11-22
75084-DE Kentucky Power Deliv - Ele | SUBCHAIRS | G9909 | Substation Chair Replacement | 0 |  | 0 |  |  | 1587.47 | 2040 | -452.53 | 2013-04-09 | 2013-04-22 | 2013-06-01 | 2013-10-01
75084-DE Kentucky Power Deliv - Ele | AMKY0752 | G9955 | Augustine SEL Dist Upgrades | 0 |  | 0 |  |  | 435665.83 | 427895 | 7770.83 | 2013-04-16 | 2014-03-31 | 2013-04-01 | 2014-03-20
75084-DE Kentucky Power Deliv - Ele | FGISEAMKE | GISEAMKE | GIS-EAM R3 INTERFACE & SW-KENTUCKY | 0 |  | 0 |  |  | 24182.73 | 28545 | -4362.27 | 2009-10-20 | 2011-03-30 | 2009-11-01 | 2011-05-01
75084-DE Kentucky Power Deliv - Ele | FGISPLOTK | GISPLOTKE | GIS PLOTTING ENHANCEMENTS | 0 |  | 0 |  |  | 45184.55 | 8873 | 36311.55 | 2010-11-23 | 2011-06-30 | 2010-12-01 | 2011-08-16
75084-DE Kentucky Power Deliv - Ele | GLPRDFA | GLPRDKY | Pole Repl Gnd Line-D | 100259.25 |  | 100259.25 | 100% |  | 950714.11 | 200 | 950514.11 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | GLPRTKY | Pole Repl Gnd Line-T | 51536.8 |  | 51536.8 | 100% |  | 502629.55 | 100 | 502529.55 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0000 | Silver Grove 138kV Install | 0 |  | 0 |  |  | 707880.4 | 484511 | 223369.4 | 2013-04-25 | 2015-09-01 | 2013-05-01 | 2014-07-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0009 | Silver Grove Inst TB1 & Rem Equip | 1451.99 |  | 1451.99 | 100% |  | 2352207.59 | 2110325 | 241882.59 | 2013-04-25 | 2015-09-01 | 2013-05-01 | 2015-01-28
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0014 | Silver Grove 41 New Feeder | 1366642.31 |  | 1366642.31 | 100% |  | 1407767.29 | 910678.56 | 497088.73 | 2013-04-25 | 2015-09-01 | 2013-11-01 | 2015-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0016 | Silver Grove 42 43 New Feeder | 400235.61 |  | 400235.61 | 100% |  | 513113.98 | 350451.67 | 162662.31 | 2013-04-25 | 2015-09-01 | 2013-11-01 | 2015-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0017 | Silver Grove 41 42 43 UG Exits | -22668.81 |  | -22668.81 | 100% |  | 670160.25 | 674137.23 | -3976.98 | 2013-04-25 | 2015-09-01 | 2013-07-01 | 2014-12-12
75084-DE Kentucky Power Deliv - Ele | NBFA | H0049 | NB emax 4052073 Retail North Bldg | 0 |  | 0 |  |  | 7068.61 | 6544.79 | 523.82 | 2013-05-02 | 2013-11-30 | 2013-05-01 | 2013-11-16
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0092 | Kenton Repl fans on TB 1 | 0 |  | 0 |  |  | 26578.59 | 15097.9 | 11480.69 | 2013-05-13 | 2013-12-31 | 2013-06-01 | 2013-09-20
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0093 | Kenton Repl fans on VR 3 | 0 |  | 0 |  |  | 14085.49 | 7427.65 | 6657.84 | 2013-05-13 | 2013-12-31 | 2013-06-01 | 2013-09-20
75084-DE Kentucky Power Deliv - Ele | NBFA | H0104 | NB emax 831 Heights Blvd | 0 |  | 0 |  |  | 4493.18 | 1688.38 | 2804.8 | 2013-05-14 | 2014-03-31 | 2013-07-01 | 2013-12-10
75084-DE Kentucky Power Deliv - Ele | AMKY0877 | H0128 | Augustine 41 Reconductor | 0 |  | 0 |  |  | 93590.12 | 119088 | -25497.88 | 2013-05-20 | 2014-09-01 | 2013-05-01 | 2014-01-10
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | H0163 | F5962 138kV Clear Corr OH | 0 |  | 0 |  |  | 10325.67 | 2500 | 7825.67 | 2013-05-23 | 2015-03-31 | 2013-07-01 | 2014-01-05
75084-DE Kentucky Power Deliv - Ele | RELDFA | H0282 | Prospect St-Robbins St-Jacob Price | 0 |  | 0 |  |  | 14514.78 | 53475.13 | -38960.35 | 2013-06-17 | 2014-01-01 | 2013-06-01 | 2014-01-16
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0296 | Crescent Install 22.4MVA TB3 | 852222.89 |  | 852222.89 | 100% |  | 1785022.49 | 1654143 | 130879.49 | 2013-06-20 | 2015-09-01 | 2013-08-01 | 2015-09-03
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0297 | Crescent UG 45 46 | 179816.96 |  | 179816.96 | 100% |  | 179816.96 | 182274 | -2457.04 | 2013-06-21 | 2016-05-01 | 2015-06-01 | 2016-03-23
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0298 | Crescent 45 | 472326.66 |  | 472326.66 | 100% |  | 480811.21 | 351997.91 | 128813.3 | 2013-06-21 | 2016-05-31 | 2014-10-01 | 2016-02-25
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0299 | Crescent 46 OH Part1 | 8493.98 |  | 8493.98 | 100% |  | 8493.98 | 377337 | -368843.02 | 2013-06-21 | 2019-03-31 | 2015-06-01
75084-DE Kentucky Power Deliv - Ele | NBFA | H0444 | NB emax 4158179 Old Alexandria Pike | 0 |  | 0 |  |  | 69133.62 | 41057.06 | 28076.56 | 2013-07-19 | 2014-11-16 | 2013-09-01 | 2014-02-04
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | H0476 | Limaburg Repl low side bush on TB 2 | 0 |  | 0 |  |  | 19749.13 | 10247.54 | 9501.59 | 2013-07-25 | 2013-10-29 | 2013-07-01 | 2013-10-27
75084-DE Kentucky Power Deliv - Ele | FMWMSW7 | H0499 | MWMS W7 REMEDIATION PROJ | 0 |  | 0 |  |  | 675.25 | 9972 | -9296.75 | 2013-08-01 | 2013-10-31 | 2013-08-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | H0503 | NB emax 4314177 IDI @ 30 Transport | 0 |  | 0 |  |  | 79269.25 | 84310.49 | -5041.24 | 2013-08-05 | 2015-01-14 | 2014-01-01 | 2014-07-31
75084-DE Kentucky Power Deliv - Ele | NBFA | H0638 | NB emax 3296995 Arcadia Ph A | 0 |  | 0 |  |  | -65977.39 | 92754.88 | -158732.27 | 2013-08-27 | 2014-11-30 | 2013-09-01 | 2014-03-27
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0663 | Claryville TB 3 Repl bushings | 0 |  | 0 |  |  | 24545.18 | 27216.63 | -2671.45 | 2013-08-29 | 2014-03-31 | 2013-12-01 | 2014-11-15
75084-DE Kentucky Power Deliv - Ele | RELDFA | H0669 | RI emax 4264899 95 Carothers Rd | 0 |  | 0 |  |  | 77791.3 | 53991.27 | 23800.03 | 2013-08-30 | 2014-08-31 | 2013-09-01 | 2014-06-25
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1124 | Blackwell Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 19591.14 | 36432 | -16840.86 | 2013-10-29 | 2015-09-01 | 2013-12-01 | 2014-07-02
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1126 | Covington Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 19635.46 | 36328 | -16692.54 | 2013-10-29 | 2015-09-01 | 2013-12-01 | 2014-06-05
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1128 | Dayton Upgrade Frame Relay Equip | -1314.96 |  | -1314.96 | 100% |  | 23922.63 | 36328 | -12405.37 | 2013-10-29 | 2015-09-01 | 2013-11-01 | 2014-05-14
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1129 | Mt. Zion Upgrade Frame Relay Equip | -458.35 |  | -458.35 | 100% |  | 30506.05 | 36328 | -5821.95 | 2013-10-29 | 2015-09-01 | 2014-01-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1134 | Thomas More Upgrd Frame Rlay Equip | 89.62 |  | 89.62 | 100% |  | 39481.99 | 36328 | 3153.99 | 2013-10-29 | 2015-09-01 | 2013-11-01 | 2015-02-11
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1136 | Hands Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 30412.03 | 61052 | -30639.97 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-07-31
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1137 | Kentucky Univ Upgrd Frme Rlay Equip | 0 |  | 0 |  |  | 33210.8 | 61052 | -27841.2 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-10-09
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1138 | York Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 30744.61 | 61052 | -30307.39 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-09-25
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1139 | Bellevue Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 58116.64 | 61052 | -2935.36 | 2013-10-30 | 2015-09-01 | 2014-01-01 | 2015-01-16
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1140 | Cold Spring Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 66994.91 | 63953 | 3041.91 | 2013-10-30 | 2015-09-01 | 2014-01-01 | 2014-07-16
75084-DE Kentucky Power Deliv - Ele | AMKY0974 | H1171 | Buffington-Repl CB 681 683 | 319111.39 |  | 319111.39 | 100% |  | 495173.27 | 295230 | 199943.27 | 2013-11-04 | 2015-09-01 | 2014-01-01 | 2015-06-30
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1196 | TR 4599000 Florence 46 | 64421.05 |  | 64421.05 | 100% |  | 66100.06 | 88196.63 | -22096.57 | 2013-11-06 | 2016-07-31 | 2013-11-01 | 2016-03-16
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1217 | TR 4597480 Florence 45 | -15705.27 |  | -15705.27 | 100% |  | 100352.79 | 145003.02 | -44650.23 | 2013-11-11 | 2015-10-31 | 2014-01-01 | 2015-08-05
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1225 | TR 4609673 Hebron 45 | 19.85 |  | 19.85 | 100% |  | 31097.36 | 51410.59 | -20313.23 | 2013-11-12 | 2015-07-31 | 2014-01-01 | 2015-06-18
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1231 | TR 4613012 Richwood 42 | 108573.12 |  | 108573.12 | 100% |  | 108573.12 | 133990.22 | -25417.1 | 2013-11-12 | 2016-12-30 | 2015-02-01 | 2016-06-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1233 | TR 4614262 Buffington 41 | 74255.28 |  | 74255.28 | 100% |  | 74255.28 | 103177.63 | -28922.35 | 2013-11-13 | 2015-12-30 | 2015-01-01 | 2015-07-29
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1236 | TR 4616175 Limaburg 41 | 37109.61 |  | 37109.61 | 100% |  | 37783.05 | 54189.11 | -16406.06 | 2013-11-13 | 2016-12-30 | 2013-11-01 | 2016-06-08
75084-DE Kentucky Power Deliv - Ele | MOFA | H1271 | OR 4599261 Bury 3PH Primary Covgtn | 0 |  | 0 |  |  | 53536.61 | 54433.57 | -896.96 | 2013-11-20 | 2014-11-25 | 2013-11-01 | 2014-11-14
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1313 | Beaver Sub SG DA | -11105.18 |  | -11105.18 | 100% |  | 383965.79 | 236862 | 147103.79 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1314 | Florence Sub SG DA | 0 |  | 0 |  |  | 330451.7 | 299642 | 30809.7 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-01-14
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1315 | Limaburg Sub SG DA | 16128.19 |  | 16128.19 | 100% |  | 583196.08 | 446848 | 136348.08 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1372 | TR 4655448 CLARYVILLE 41 | 155599.69 |  | 155599.69 | 100% |  | 274657.65 | 331178.02 | -56520.37 | 2013-12-03 | 2016-12-30 | 2014-10-01 | 2016-09-08
75084-DE Kentucky Power Deliv - Ele | NBFA | H1381 | JT 4655806 Arcadia West PH A electr | 0 |  | 0 |  |  | 73653.24 | 149749.52 | -76096.28 | 2013-12-04 | 2014-11-29 | 2013-12-01 | 2014-07-28
75084-DE Kentucky Power Deliv - Ele | NBFA | H1382 | NB 3941206 Stillbrooke Subdv Felice | 0 |  | 0 |  |  | 18021.21 | 44694.66 | -26673.45 | 2013-12-04 | 2014-11-30 | 2014-01-01 | 2014-08-08
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1397 | TR 4658415 Hands 41 | -1233.9 |  | -1233.9 | 100% |  | 134497.01 | 115397.25 | 19099.76 | 2013-12-05 | 2016-01-30 | 2014-05-01 | 2015-01-02
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1398 | TR 4660303 Hands 44 | 11471.41 |  | 11471.41 | 100% |  | 204608.79 | 227477.2 | -22868.41 | 2013-12-05 | 2016-06-30 | 2014-04-01 | 2016-02-15
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1404 | TR 4660722 Augustine 41 | 136602.72 |  | 136602.72 | 100% |  | 136602.72 | 199456.61 | -62853.89 | 2013-12-06 | 2016-06-30 | 2015-01-01 | 2016-02-18
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1446 | TR 4674272 Augustine 46 | 540.72 |  | 540.72 | 100% |  | 168565.55 | 214520.52 | -45954.97 | 2013-12-12 | 2015-03-31 | 2013-12-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1453 | TR 4675524 York 43 | 52581.31 |  | 52581.31 | 100% |  | 52749.92 | 64460.38 | -11710.46 | 2013-12-12 | 2016-06-01 | 2013-12-01 | 2015-06-17
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1462 | TR 4677452 Marshall 41 | -2781.39 |  | -2781.39 | 100% |  | 48642.69 | 73276.29 | -24633.6 | 2013-12-13 | 2015-03-31 | 2014-05-01 | 2014-10-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1464 | TR 4678169 KY UNIV 43 | 404.02 |  | 404.02 | 100% |  | 72686.45 | 121238 | -48551.55 | 2013-12-13 | 2015-07-31 | 2013-12-01 | 2015-06-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1487 | TR 4693232 Oakbrook 41 | 6770.87 |  | 6770.87 | 100% |  | 27718.89 | 54889.34 | -27170.45 | 2013-12-17 | 2015-10-30 | 2014-12-01 | 2015-04-19
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1488 | TR 4693837 Augustine 43 | 369.3 |  | 369.3 | 100% |  | 61024.42 | 75566.64 | -14542.22 | 2013-12-17 | 2016-06-30 | 2014-04-01 | 2016-02-17
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1489 | TR 4694697 Verona 42 | 78104.4 |  | 78104.4 | 100% |  | 78271.39 | 94811.65 | -16540.26 | 2013-12-17 | 2016-07-30 | 2013-12-01 | 2016-06-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H1600 | Augustine Repl LAs on TB 5 | 0 |  | 0 |  |  | 9535.91 | 7904.73 | 1631.18 | 2014-01-03 | 2015-03-31 | 2014-04-01 | 2015-02-12
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H1601 | Marshall Repl HS LAs on TB 1 | 0 |  | 0 |  |  | 7616.97 | 3529.83 | 4087.14 | 2014-01-03 | 2015-03-31 | 2014-03-01 | 2014-07-04
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | H1642 | DC 4759551 Verona 41 | 189.04 |  | 189.04 | 100% |  | 39654.36 | 37079.56 | 2574.8 | 2014-01-10 | 2015-06-30 | 2014-03-01 | 2015-03-23
75084-DE Kentucky Power Deliv - Ele | UGCRFA | H1679 | UG 4765860 URD 36 Brookwood | 0 |  | 0 |  |  | 154132.69 | 142644.34 | 11488.35 | 2014-01-15 | 2015-02-28 | 2014-01-01 | 2014-08-28
75084-DE Kentucky Power Deliv - Ele | PRDFA | H1728 | PR 4841795 Emerson Electric Reroute | 141.5 |  | 141.5 | 100% |  | 53672.57 | 56682.07 | -3009.5 | 2014-01-27 | 2015-03-31 | 2014-02-01 | 2014-10-31
75084-DE Kentucky Power Deliv - Ele | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 666306.67 |  | 666306.67 | 100% |  | 718635.28 | 823726 | -105090.72 | 2014-02-18 | 2019-03-01 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY1Q12 | Q1 2012 IK KY Blanket Roll Up Proj | 0 |  | 0 |  |  | 5870552.06 | 100 | 5870452.06 | 2012-02-03 | 2012-12-31 | 2012-01-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2013 | 2013 IK KY Blanket Roll Up Proj | 0 |  | 0 |  |  | 10494333.25 | 100 | 10494233.25 | 2012-12-21 | 2013-12-31 | 2012-12-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2014 | 2014 IK KY Blanket Roll Up Proj | 0 |  | 0 |  |  | 8190663.87 | 1 | 8190662.87 | 2013-12-27 | 2014-12-31 | 2013-12-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2015 | 2015 KY Dist Lines (IK) Roll | 4778538.53 |  | 4778538.53 | 100% |  | 5199091.21 | 1 | 5199090.21 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2015T | 2015 KY Dist Lines (IK) Roll - T | 4513063.53 |  | 4513063.53 | 100% |  | 5195932.69 | 1 | 5195931.69 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2016 | 2016 KY Dist Lines (IK) Roll | 644740.42 |  | 644740.42 | 100% |  | 644740.42 | 1 | 644739.42 | 2015-11-30 15:55 | 2016-12-31 | 2015-12-01
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2016T | 2016 KY Dist Lines (IK) Roll - T | 392978.71 |  | 392978.71 | 100% |  | 392978.71 | 1 | 392977.71 | 2015-11-30 16:03 | 2016-12-31 | 2015-12-01
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKYROL11 | 2011 IK KY Roll Up Blanket Project | 0 |  | 0 |  |  | 9791865.05 | 100 | 9791765.05 | 2011-12-16 | 2011-12-31 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | AMKY0953 | J0108 | Hebron Inst 69kV CB's | 1042402.66 |  | 1042402.66 | 100% |  | 1660110.45 | 1421424 | 238686.45 | 2014-03-24 | 2015-09-01 | 2014-03-01 | 2015-08-29
75084-DE Kentucky Power Deliv - Ele | AMKY0953 | J0109 | Villa Repl F2862 Relays | 136466.76 |  | 136466.76 | 100% |  | 193189.27 | 175606 | 17583.27 | 2014-03-24 | 2015-10-01 | 2014-03-01 | 2015-09-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | J0111 | Augustine Repl fans on TB 5 | 0 |  | 0 |  |  | 11977.54 | 11300.35 | 677.19 | 2014-03-24 | 2015-03-31 | 2014-07-01 | 2014-10-22
75084-DE Kentucky Power Deliv - Ele | CSPFA | J0118 | TR 5215691 Wilder 47 | 96167.18 |  | 96167.18 | 100% |  | 96167.18 | 70260.67 | 25906.51 | 2014-03-25 | 2016-03-31 | 2015-08-01 | 2015-12-31
75084-DE Kentucky Power Deliv - Ele | CSPFA | J4103 | TR 5247963 Augustine 45 | 0 |  | 0 |  |  | 403.39 | 64518.96 | -64115.57 | 2014-03-31 | 2016-12-30 | 2014-04-01 | 2016-09-15
75084-DE Kentucky Power Deliv - Ele | CSPFA | J4104 | TR 5249008 Longbranch 42 | 148852.99 |  | 148852.99 | 100% |  | 148852.99 | 187480.99 | -38628 | 2014-03-31 | 2017-01-31 | 2015-05-01 | 2016-11-02
75084-DE Kentucky Power Deliv - Ele | ESXIUPG14 | J9118 | 2014 ESXI Upgrade-Kentucky | -7.87 |  | -7.87 | 100% |  | 7230.09 | 6676 | 554.09 | 2014-04-11 | 2015-01-31 | 2014-04-01 | 2015-01-30
75084-DE Kentucky Power Deliv - Ele | CSPFA | K0104 | TR 5309940 Covington 43 | 42638.09 |  | 42638.09 | 100% |  | 42638.09 | 90553.06 | -47914.97 | 2014-04-11 | 2016-03-29 | 2015-05-01 | 2015-08-14
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | K4107 | Limaburg Repl failed TB 2 | 0 |  | 0 |  |  | 78277.62 | 62323.26 | 15954.36 | 2014-04-21 | 2014-09-30 | 2014-04-01 | 2014-08-08
75084-DE Kentucky Power Deliv - Ele | NBFA | K7108 | NB 4686312 512 Oak Ludlow | -111.7 |  | -111.7 | 100% |  | 7515.52 | 7804.98 | -289.46 | 2014-04-28 | 2015-04-28 | 2014-06-01 | 2014-09-24
75084-DE Kentucky Power Deliv - Ele | KETF47112 | KET347112 | DET 7347112 KY University 43 | 271991.41 |  | 271991.41 | 100% |  | 271991.41 | 216649.45 | 55341.96 | 2015-06-03 10:01 | 2016-03-31 | 2015-04-01 | 2015-11-25
75084-DE Kentucky Power Deliv - Ele | KETF47303 | KET347303 | DET 7347303 Beaver 41 | 109417.49 |  | 109417.49 | 100% |  | 109417.49 | 145648.28 | -36230.79 | 2015-06-03 14:01 | 2016-10-29 | 2015-06-01 | 2016-05-03
75084-DE Kentucky Power Deliv - Ele | KETF45693 | KET745693 | DET 8745693 SILVER GROVE | 17852.49 |  | 17852.49 | 100% |  | 17852.49 | 69025.9 | -51173.41 | 2015-10-13 14:06 | 2016-03-31 | 2015-10-01 | 2016-04-16
75084-DE Kentucky Power Deliv - Ele | KETF33444 | KET833444 | DET 8833444 Crescent 43 R | 4920.48 |  | 4920.48 | 100% |  | 4920.48 | 123996.11 | -119075.63 | 2015-12-10 14:04 | 2016-12-06 | 2015-12-01 | 2016-08-10
75084-DE Kentucky Power Deliv - Ele | KFSF97495 | KFS897495 | CS 6897495 Decoursey 41 | 7405.47 |  | 7405.47 | 100% |  | 7405.47 | 72374.22 | -64968.75 | 2015-06-01 14:01 | 2016-09-30 | 2015-09-01 | 2016-08-24
75084-DE Kentucky Power Deliv - Ele | KHRF77294 | KHR177294 | DOT 7177294 Hebron 42, in | 2544.55 |  | 2544.55 | 100% |  | 2544.55 | 46889.01 | -44344.46 | 2015-11-19 14:04 | 2016-08-09 | 2015-12-01 | 2016-06-17
75084-DE Kentucky Power Deliv - Ele | KHRF80227 | KHR180227 | DOT 7180227 Wilder 48 rep | 42773.26 |  | 42773.26 | 100% |  | 42773.26 | 103743.63 | -60970.37 | 2015-09-08 18:02 | 2016-09-01 | 2015-09-01 | 2016-08-31
75084-DE Kentucky Power Deliv - Ele | KILF49392 | KIL049392 | UG 7049392 Augustine 46 P | 437838.66 |  | 437838.66 | 100% |  | 437838.66 | 446005 | -8166.34 | 2015-07-07 10:01 | 2016-04-30 | 2015-09-01 | 2016-03-30
75084-DE Kentucky Power Deliv - Ele | FKPIAPP | KPIAPPL | Perf Meas App (KPI) - T&D & Gas | 195.28 |  | 195.28 | 100% |  | 195.28 | 3363 | -3167.72 | 2015-03-12 15:53 | 2016-02-28 | 2015-04-01 | 2016-01-29
75084-DE Kentucky Power Deliv - Ele | KTMF72080 | KTM272080 | SL 8272080 Manhattan Blvd | 73112.81 |  | 73112.81 | 100% |  | 73112.81 | 60641 | 12471.81 | 2015-08-04 18:01 | 2016-03-30 | 2015-09-01 | 2015-12-25
75084-DE Kentucky Power Deliv - Ele | KTMF66767 | KTM466767 | SL 7466767 Park South Bldg A | 53927.27 |  | 53927.27 | 100% |  | 53927.27 | 98420.62 | -44493.35 | 2015-05-04 14:01 | 2016-06-27 | 2015-05-01 | 2016-02-21
75084-DE Kentucky Power Deliv - Ele | KTMF28273 | KTM628273 | SL 7628273 St Rt 18 | 44294.78 |  | 44294.78 | 100% |  | 44294.78 | 57641.31 | -13346.53 | 2015-10-09 18:05 | 2016-04-20 | 2015-11-01 | 2016-03-29
75084-DE Kentucky Power Deliv - Ele | KSLF53633 | KTM853633 | SL 6853633 Heights Blvd | -110680.31 |  | -110680.31 | 100% |  | -110680.31 | 122072 | -232752.31 | 2015-06-22 14:01 | 2016-12-11 | 2015-09-01 | 2016-02-21
75084-DE Kentucky Power Deliv - Ele | KTMF99834 | KTM999834 | SL 7999834 Bellevue 13144 | 93624.57 |  | 93624.57 | 100% |  | 93624.57 | 95098.95 | -1474.38 | 2015-06-24 17:43 | 2017-01-24 | 2015-08-01 | 2016-01-09
75084-DE Kentucky Power Deliv - Ele | KUSF21914 | KUS021914 | NB 8021914 Aosta Valley Subd | 33372.79 |  | 33372.79 | 100% |  | 33372.79 | 62230.35 | -28857.56 | 2015-11-13 18:07 | 2016-09-30 | 2015-12-01 | 2016-04-29
75084-DE Kentucky Power Deliv - Ele | KUSF69963 | KUS069963 | NB 8069963 Memorial Parkway | 76256.48 |  | 76256.48 | 100% |  | 76256.48 | 240091.46 | -163834.98 | 2015-07-06 14:01 | 2016-06-30 | 2015-07-01 | 2016-06-22
75084-DE Kentucky Power Deliv - Ele | KUSF97225 | KUS497225 | UG 4497225 Heights Blvd | 65959.66 |  | 65959.66 | 100% |  | 65959.66 | 101040.22 | -35080.56 | 2015-06-22 10:01 | 2016-02-19 | 2015-08-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | KUSF97855 | KUS597855 | NB 7597855 Florence 44 St Rt 18 | 77283.34 |  | 77283.34 | 100% |  | 77283.34 | 101551.51 | -24268.17 | 2015-10-09 18:05 | 2016-04-19 | 2015-10-01 | 2016-03-29
75084-DE Kentucky Power Deliv - Ele | KUSF45398 | KUS945398 | NB 8945398 Aqua on the Le | 25481.29 |  | 25481.29 | 100% |  | 25481.29 | 103216.67 | -77735.38 | 2015-10-16 14:03 | 2016-03-31 | 2015-10-01 | 2016-05-03
75084-DE Kentucky Power Deliv - Ele | KUSF80889 | KUS980889 | NB 6980889 900 E. 6th St, | 58863.05 |  | 58863.05 | 100% |  | 58863.05 | 50568.93 | 8294.12 | 2015-10-01 18:04 | 2016-03-12 | 2015-11-01 | 2016-03-06
75084-DE Kentucky Power Deliv - Ele | RELTFA | KYRELT1 | F6763 DOT Mt Zion Rd-Dixie Hwy | 628.32 |  | 628.32 | 100% |  | 628.32 | 35000 | -34371.68 | 2015-07-25 18:59 | 2018-03-31 | 2015-09-01
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | L2102 | DC 5476661 Hebron 42 | 33589.51 |  | 33589.51 | 100% |  | 34429.94 | 57064.06 | -22634.12 | 2014-05-08 | 2015-11-01 | 2014-06-01 | 2015-08-07
75084-DE Kentucky Power Deliv - Ele | AMKY0944 | L2103 | Beaver-Install ATO | 108436.97 |  | 108436.97 | 100% |  | 267427.44 | 238543 | 28884.44 | 2014-05-08 | 2015-03-31 | 2014-05-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | L2104 | DC 5476709 Villa 43 | 59479.91 |  | 59479.91 | 100% |  | 61206.96 | 85000.43 | -23793.47 | 2014-05-08 | 2016-07-30 | 2014-06-01 | 2016-06-25
75084-DE Kentucky Power Deliv - Ele | AMKY0940 | L2107 | Limaburg-Install ATO | 637.03 |  | 637.03 | 100% |  | 210828.53 | 214396 | -3567.47 | 2014-05-08 | 2015-03-31 | 2014-05-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | AMKY0940 | L2109 | Buffington F6763 Reclosing | 134.88 |  | 134.88 | 100% |  | 11887.63 | 19372 | -7484.37 | 2014-05-08 | 2015-03-31 | 2014-07-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | AMKY1101 | L5122 | UG 5511344 Kenton 43 Bld New Fdr | 415506.62 |  | 415506.62 | 100% |  | 698213.09 | 529656.26 | 168556.83 | 2014-05-15 | 2016-03-31 | 2014-07-01 | 2015-07-16
75084-DE Kentucky Power Deliv - Ele | AMKY0941 | L9104 | Grant Install TLS | 627120.93 |  | 627120.93 | 100% |  | 705369.25 | 230617 | 474752.25 | 2014-05-21 | 2016-03-31 | 2014-06-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | AMKY0943 | L9108 | Cold Spring TLS | 203772.88 |  | 203772.88 | 100% |  | 272992.4 | 217493 | 55499.4 | 2014-05-22 | 2015-09-30 | 2014-06-01 | 2015-08-01
75084-DE Kentucky Power Deliv - Ele | AMKY1073 | L9115 | Buffington Repl VTs | 159850.25 |  | 159850.25 | 100% |  | 189218.31 | 109828 | 79390.31 | 2014-05-22 | 2015-09-01 | 2014-06-01 | 2015-06-30
75084-DE Kentucky Power Deliv - Ele | PILCFA | L9117 | UG 5466220 Buffington 45 PILC Repl | -84.81 |  | -84.81 | 100% |  | 26740.64 | 23138.33 | 3602.31 | 2014-05-22 | 2015-11-30 | 2014-07-01 | 2015-02-04
75084-DE Kentucky Power Deliv - Ele | PRDFA | LARCUKY | Limited Access Road Crossing Upgrad | 0 |  | 0 |  |  | 0 | 100000 | -100000 | 2012-05-23 | 2050-12-31 | 2012-10-01
75084-DE Kentucky Power Deliv - Ele | RLFA | LPFUKY | Line Patrol Insp followup KY | 96657.96 |  | 96657.96 | 100% |  | 96657.96 | 400000 | -303342.04 | 2010-12-22 | 2015-12-31 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | LPRFUKY | Line Patrol Followup Work | 316449.15 |  | 316449.15 | 100% |  | 559933.84 | 80000 | 479933.84 | 2013-03-20 | 2050-12-31 | 2013-11-01
75084-DE Kentucky Power Deliv - Ele | RLFA | LPSMEIKY | Dline Patrol SMEI Capital Followup | 4708.64 |  | 4708.64 | 100% |  | 4708.64 | 75000 | -70291.36 | 2012-04-30 | 2050-12-31 | 2013-02-01
75084-DE Kentucky Power Deliv - Ele | AMKY0942 | M1112 | Dry Ridge TLS | 208837.13 |  | 208837.13 | 100% |  | 270846.72 | 122334 | 148512.72 | 2014-05-29 | 2015-09-30 | 2014-06-01 | 2015-08-29
75084-DE Kentucky Power Deliv - Ele | RELDFA | M2116 | DOT 5395279 Taylor Mill Rd @ Walnut | -153982.9 |  | -153982.9 | 100% |  | 1012.41 | 119791.13 | -118778.72 | 2014-06-03 | 2015-05-02 | 2014-06-01 | 2015-02-20
75084-DE Kentucky Power Deliv - Ele | RLFA | MALTKY | Malten Switchgear Replacement KY | 0 |  | 0 |  |  | 0 | 100000 | -100000 | 2012-01-13 | 2015-12-31 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | NBFA | MATRETCAP | Material Returns Capital Only | 613.47 |  | 613.47 | 100% |  | 516.13 | 10000 | -9483.87 | 2012-08-28 | 2050-12-31 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | MAXH | Enable Maximo Hardware | 709.37 |  | 709.37 | 100% |  | 709.37 | 9267 | -8557.63 | 2015-03-30 12:42 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | MAXS | Enable Maximo Software | 232528.08 |  | 232528.08 | 100% |  | 232528.08 | 1352478 | -1119949.92 | 2015-03-30 14:04 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | RELDFA | MKRDYKY | Make Ready Kentucky | 49028.52 |  | 49028.52 | 100% |  | 49028.52 | 10 | 49018.52 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | MOBH | Enable Mobility Hardware | 2830.58 |  | 2830.58 | 100% |  | 2830.58 | 172489 | -169658.42 | 2015-03-30 15:55 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | MOBS | Enable Mobility Software | 117790.44 |  | 117790.44 | 100% |  | 117790.44 | 932343 | -814552.56 | 2015-03-30 14:54 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | MOFA | MOKY | Major Outage Followup-D | -1051.71 |  | -1051.71 | 100% |  | -1051.71 | 100 | -1151.71 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | FN1216KY | N1216SWKY | NINT1216 Tripwire Enterprise (TE) | 24792.16 |  | 24792.16 | 100% |  | 100426.96 | 18269 | 82157.96 | 2014-08-08 | 2015-11-30 | 2014-08-01 | 2015-07-27
75084-DE Kentucky Power Deliv - Ele | FNETSCALR | N5103 | Upgrade to Net Scaler | 2227.69 |  | 2227.69 | 100% |  | 8180.46 | 5460 | 2720.46 | 2014-06-25 | 2015-06-30 | 2014-07-01 | 2015-06-20
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7105 | Dixie Repl Sta Batteries | 0 |  | 0 |  |  | 5754.53 | 9371.25 | -3616.72 | 2014-06-27 | 2015-03-31 | 2014-07-01 | 2014-11-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7106 | Hands Sub Repl Sta Batteries | 0 |  | 0 |  |  | 9574.12 | 10634.99 | -1060.87 | 2014-06-27 | 2015-03-31 | 2014-07-01 | 2014-11-05
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7107 | Buffington Repl Cooling Fans | 0 |  | 0 |  |  | 6505.08 | 5806.34 | 698.74 | 2014-06-27 | 2015-03-31 | 2014-08-01 | 2014-11-25
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | N7108 | Wilder Repl Cooling Fans | 0 |  | 0 |  |  | 6432 | 5806.34 | 625.66 | 2014-06-27 | 2015-03-31 | 2014-08-01 | 2014-11-25
75084-DE Kentucky Power Deliv - Ele | UGCRFA | N8112 | UG 5759052 URD 52 Woodside Dr | -3222.09 |  | -3222.09 | 100% |  | 189919.24 | 158779.8 | 31139.44 | 2014-06-30 | 2015-06-30 | 2014-08-01 | 2015-03-02
75084-DE Kentucky Power Deliv - Ele | NBFA | NBKY | Customer Adds-MW-D | 536297.47 |  | 536297.47 | 100% |  | 5565746.57 | 200 | 5565546.57 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | NEWCAPFA | NEWCAPKY | New Capacitors | 0 |  | 0 |  |  | 33297.67 | 101 | 33196.67 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | NINT686FP | NINT686 | NINT686 IEE C+I Upgrade Project | 838.67 |  | 838.67 | 100% |  | 4909.01 | 30000 | -25090.99 | 2014-06-12 | 2014-10-23 | 2014-06-01 | 2015-04-15
75084-DE Kentucky Power Deliv - Ele | OM75084 | NONOLE | Overhead Non OLE Lt Insp/Maint | 0 |  | 0 |  |  | 0 |  | 0 | 2008-07-01 | 2020-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NUPOLSET | Non Utility work-Exp | 0 |  | 0 |  |  | 0 |  | 0 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NUTRANSF | Transfers-other companies-exp | 0 |  | 0 |  |  | 0 |  | 0 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2105 | Hebron Station eye wash station | 0 |  | 0 |  |  | 0 |  | 0 | 2014-07-11 | 2012-03-16 | 2014-08-01 | 2003-03-21
75084-DE Kentucky Power Deliv - Ele | DETCONFA | O2107 | DC 5809390 CRESCENT 42 | 401414.9 |  | 401414.9 | 100% |  | 503345.61 | 267130.7 | 236214.91 | 2014-07-12 | 2016-01-31 | 2014-07-01 | 2015-07-14
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2111 | Mt Zion Remov eye wash stat | 0 |  | 0 |  |  | 0 |  | 0 | 2014-07-14 | 2013-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2114 | Blackwell remove eyewas stat 7 gal | 0 |  | 0 |  |  | 0 |  | 0 | 2014-07-14 | 2013-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2115 | York remove eye wash stat | 0 |  | 0 |  |  | 0 |  | 0 | 2014-07-14 | 2012-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2116 | Dayton remove eye wash stat | 0 |  | 0 |  |  | 0 |  | 0 | 2014-07-14 | 2012-03-16 | 2014-08-01 | 2012-05-12
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2117 | Longbranch remove eye wash stat | 0 |  | 0 |  |  | 0 |  | 0 | 2014-07-14 | 2012-03-16 | 2014-09-01 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3102 | Cresent Repl 48VDC Sta Batteries | 5074.64 |  | 5074.64 | 100% |  | 9108.49 | 10390.57 | -1282.08 | 2014-07-16 | 2015-03-31 | 2014-10-01 | 2015-06-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3103 | Bellevue Repl Sta Batteries | 47.32 |  | 47.32 | 100% |  | 8304.79 | 14912.34 | -6607.55 | 2014-07-16 | 2016-09-30 | 2014-10-01 | 2016-04-13
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3106 | Cold Spring Repl Sta Batteries | 0 |  | 0 |  |  | 10700.12 | 10023.94 | 676.18 | 2014-07-16 | 2015-03-31 | 2014-08-01 | 2014-11-18
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O4106 | Hands Sub add gravel | 0 |  | 0 |  |  | 1493.02 | 11207.12 | -9714.1 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-11-15
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O4112 | Buffington Sub Add Gravel | 0 |  | 0 |  |  | 805.92 | 11207.12 | -10401.2 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | NBFA | O4116 | NB 4714818 4455 Olympic Blvd | 227.98 |  | 227.98 | 100% |  | 11436.73 | 33237.99 | -21801.26 | 2014-07-17 | 2015-11-28 | 2014-08-01 | 2014-10-17
75084-DE Kentucky Power Deliv - Ele | NBFA | O4137 | NB 4706432 629 Madison | 8357.95 |  | 8357.95 | 100% |  | 74218.76 | 25675.44 | 48543.32 | 2014-07-21 | 2015-06-14 | 2014-07-01 | 2015-01-22
75084-DE Kentucky Power Deliv - Ele | AMKY0085A | O4164 | Wilder Inst 13kV CB 170 | -314.38 |  | -314.38 | 100% |  | 37736.03 | 27000 | 10736.03 | 2014-07-23 | 2015-06-30 | 2014-08-01 | 2015-01-05
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | O5111 | Villa TB2 Repl Cooling Fans | -1156.06 |  | -1156.06 | 100% |  | 4543.82 | 4706.45 | -162.63 | 2014-07-25 | 2015-03-31 | 2014-08-01 | 2014-11-04
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | O6105 | Constance Repl TB1 Cooling Fans | 0 |  | 0 |  |  | 10180.71 | 10512.1 | -331.39 | 2014-07-28 | 2015-03-31 | 2014-08-01 | 2015-01-24
75084-DE Kentucky Power Deliv - Ele | RLFA | OHPCIKY | Mandated KY Overhead Prim Clearanc | 0 |  | 0 |  |  | -7.276e-12 | 381049 | -381049 | 2010-12-22 | 2050-12-31 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | RLFA | OHPCIKY | Mandated KY Overhead Prim Clearanc | 0 |  | 0 |  |  | -7.276e-12 | 381049 | -381049 | 2010-12-22 | 2050-12-31 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE08KY | Lighting-OLE-Inst | 0 |  | 0 |  |  | -3546.83 | 100 | -3646.83 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2008-12-20
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE08RPKY | Light Repl-OLE | 0 |  | 0 |  |  | 2.9559e-12 | 90 | -90 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-04-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OLE09KY | Lighting-OLE-Inst | 0 |  | 0 |  |  | 11031.05 | 97100 | -86068.95 | 2009-01-02 | 2050-12-31 | 2009-01-01 | 2009-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | OLE09RPKY | Light Repl-OLE | 0 |  | 0 |  |  | 914.48 | 97100 | -96185.52 | 2009-01-02 | 2050-12-31 | 2009-02-01 | 2009-12-31
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE11KY | Lighting-OLE-Inst-2011 | 0 |  | 0 |  |  | 0 | 100085 | -100085 | 2011-01-04 | 2012-12-31 | 2011-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE11RPKY | Light Repl-OLE-2011 | 0 |  | 0 |  |  | 0 | 84 | -84 | 2011-01-04 | 2050-12-31 | 2011-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE12KY | Kentucky Lighting OLE Install 2012 | 0 |  | 0 |  |  | 84224.87 | 100000 | -15775.13 | 2011-11-14 | 2013-06-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE12RPKY | Kentucky Lighting Replace OLE 2012 | 0 |  | 0 |  |  | 450 | 32000 | -31550 | 2011-11-14 | 2013-06-01 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE13KY | Kentucky Lighting OLE Install 2013 | 0 |  | 0 |  |  | 0 | 50085 | -50085 | 2013-01-04 | 2014-10-01 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE13RPKY | Kentucky Lighting OLE Replace 2013 | 0 |  | 0 |  |  | 0 | 10083 | -10083 | 2013-01-04 | 2014-10-01 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE14KY | Kentuck Lighting OLE Install 2014 | 1.4211e-14 |  | 1.4211e-14 | 100% |  | 1.4211e-14 | 85 | -85 | 2014-01-02 | 2015-09-30 | 2014-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE14KY | Kentuck Lighting OLE Install 2014 | 1.4211e-14 |  | 1.4211e-14 | 100% |  | 1.4211e-14 | 85 | -85 | 2014-01-02 | 2015-09-30 | 2014-01-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | OLEINT | OLE Interest | 0 |  | 0 |  |  | 0 |  | 0 | 2008-07-01 | 2050-12-31 | 2008-10-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | 271367.13 |  | 271367.13 | 100% |  | 271367.13 | 10 | 271357.13 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLERPKY | Kentcky Lighting Replacement - OLE | 627.73 |  | 627.73 | 100% |  | 627.73 | 9 | 618.73 | 2014-08-04 | 2020-12-31 | 2015-12-01
75084-DE Kentucky Power Deliv - Ele | FORCHARDK | ORCHARDKE | 1140 ORCHARD ST-YORK SUB-KENTUCKY | 0 |  | 0 |  |  | 28802.78 | 28072.72 | 730.06 | 2010-07-21 | 2010-10-01 | 2010-07-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | MTRCAPFA | ORDERTRK | Assemble Meter Sets | 0 |  | 0 |  |  | 171034.69 | 92 | 170942.69 | 2008-07-01 | 2025-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | ORDKY | Outage Restoration Cap-D | -1365.81 |  | -1365.81 | 100% |  | 158339.31 | 200 | 158139.31 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | ORTFA | ORTKY | Outage Restoration Cap-T | 19766.21 |  | 19766.21 | 100% |  | 39706.2 | 100 | 39606.2 | 2010-06-28 | 2050-12-31 | 2011-04-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | OTVSRKY | Cap Oil to Vac Switch Repl KY | 7.1054e-15 |  | 7.1054e-15 | 100% |  | 7.1054e-15 | 100000 | -100000 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | OUTAGES | Routine Outages | 0 |  | 0 |  |  | 0 |  | 0 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OUTRFUKY | Outage Reliability FollowUp Capital | -33520.24 |  | -33520.24 | 100% |  | -33520.24 | 50000 | -83520.24 | 2012-05-09 | 2050-12-31 | 2012-09-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | P0104 | RI 6000526 Newport High School | 63625.41 |  | 63625.41 | 100% |  | 66822.57 | 55761.4 | 11061.17 | 2014-08-04 | 2016-11-15 | 2014-09-01 | 2016-08-22
75084-DE Kentucky Power Deliv - Ele | RELDFA | P6165 | RI 4183102 Lowell St (Rt. 9) | 263471.83 |  | 263471.83 | 100% |  | 285347.22 | 190657.24 | 94689.98 | 2014-08-22 | 2016-03-14 | 2014-10-01 | 2015-07-27
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | P6216 | Wilder Repl TB1 Cooling Fans | 0 |  | 0 |  |  | 16403.43 | 16025.64 | 377.79 | 2014-08-28 | 2015-03-31 | 2014-09-01 | 2015-01-06
75084-DE Kentucky Power Deliv - Ele | CSFA | P6373 | CS 5062969 Cold Spring 49 | 69480.24 |  | 69480.24 | 100% |  | 87183.71 | 93658.11 | -6474.4 | 2014-09-24 | 2016-03-31 | 2014-10-01 | 2015-05-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P6425 | Limaburg TB1 Repl Cooling Fans | 13881.26 |  | 13881.26 | 100% |  | 21493.51 | 11376.4 | 10117.11 | 2014-09-29 | 2015-03-31 | 2014-11-01 | 2016-02-04
75084-DE Kentucky Power Deliv - Ele | AMKY1396 | P6550 | AM 6394804 Kenton 44 12kv | 394849.36 |  | 394849.36 | 100% |  | 507172.02 | 515418.38 | -8246.36 | 2014-10-09 | 2016-03-31 | 2014-10-01 | 2015-07-09
75084-DE Kentucky Power Deliv - Ele | AMKY1176 | P6679 | Villa CCVT Repl | 31397 |  | 31397 | 100% |  | 42601.38 | 90805 | -48203.62 | 2014-10-27 | 2016-03-31 | 2014-11-01 | 2015-09-13
75084-DE Kentucky Power Deliv - Ele | AMKY1396 | P6708 | AM 6394817 Kenton 44 Pt 2 reloc | 244438.05 |  | 244438.05 | 100% |  | 254988.87 | 150744.74 | 104244.13 | 2014-10-31 | 2016-03-31 | 2014-11-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | NBFA | P6718 | NB 5846054 Sunny Ridge Estates | 72417.71 |  | 72417.71 | 100% |  | 58571.71 | 74531.15 | -15959.44 | 2014-10-31 | 2015-11-26 | 2014-12-01 | 2015-07-28
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | P6992 | Mt Zion TB1 Repl HS Bushings | 51454.7 |  | 51454.7 | 100% |  | 51454.7 | 24820.84 | 26633.86 | 2014-12-08 | 2016-03-31 | 2015-05-01 | 2016-01-05
75084-DE Kentucky Power Deliv - Ele | NBFA | P7033 | NB 6573310 15 Spiral Dr | 84504.95 |  | 84504.95 | 100% |  | 41380.3 | 91801.87 | -50421.57 | 2014-12-12 | 2015-11-01 | 2014-12-01 | 2015-08-12
75084-DE Kentucky Power Deliv - Ele | DETCONFA | P7106 | DET 6589503 Cold Spring 49 | 67545.83 |  | 67545.83 | 100% |  | 68728.44 | 56012.44 | 12716 | 2014-12-18 | 2016-03-31 | 2014-12-01 | 2015-08-26
75084-DE Kentucky Power Deliv - Ele | NBFA | P7171 | NB 6319774 Arcadia Ph B | 105380.74 |  | 105380.74 | 100% |  | 105380.74 | 80707.3 | 24673.44 | 2014-12-30 | 2015-09-30 | 2015-01-01 | 2015-07-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P7228 | Cold Spring Repl Xtr bushings | 15674.09 |  | 15674.09 | 100% |  | 15674.09 | 11563.26 | 4110.83 | 2015-01-09 | 2016-03-31 | 2015-01-01 | 2015-09-15
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7272 | DEC 6892552 Oakbrook 41 | 59964.8 |  | 59964.8 | 100% |  | 59964.8 | 29484.29 | 30480.51 | 2015-01-14 | 2016-07-30 | 2015-02-01 | 2016-04-26
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7273 | DEC 6892574 Donaldson 41 | 32136.54 |  | 32136.54 | 100% |  | 32136.54 | 88334.91 | -56198.37 | 2015-01-14 | 2017-11-15 | 2015-01-01 | 2017-10-27
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7274 | DEC 6892567 Donaldson 41 | 48548.78 |  | 48548.78 | 100% |  | 48548.78 | 205737.82 | -157189.04 | 2015-01-14 | 2018-06-30 | 2015-01-01
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7275 | DEC 6892560 Oakbrook 42 | 44362.65 |  | 44362.65 | 100% |  | 44362.65 | 146224.02 | -101861.37 | 2015-01-14 | 2016-10-31 | 2015-01-01 | 2016-07-05
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P7314 | Donaldson TB1 Bushings | 5966 |  | 5966 | 100% |  | 5966 | 11563.26 | -5597.26 | 2015-01-16 | 2018-03-01 | 2015-03-01 | 2016-12-31
75084-DE Kentucky Power Deliv - Ele | AMKY1168 | P7405 | KY Univ Bus 4 Swgr and CB Repl | 311703.39 |  | 311703.39 | 100% |  | 311703.39 | 741889 | -430185.61 | 2015-01-22 | 2017-03-31 | 2015-02-01 | 2017-03-02
75084-DE Kentucky Power Deliv - Ele | CP15BATK | P7421 | Florence Repl Batteries | 7039.25 |  | 7039.25 | 100% |  | 7039.25 | 6813.73 | 225.52 | 2015-01-23 | 2016-03-31 | 2015-04-01 | 2015-07-15
75084-DE Kentucky Power Deliv - Ele | CSFA | P7652 | DA 6897728 Augustine 46 | 81860.32 |  | 81860.32 | 100% |  | 81860.32 | 71500.67 | 10359.65 | 2015-02-06 | 2016-03-31 | 2015-04-01 | 2016-01-29
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P8327 | Constance Repl Station Batt | 8039.76 |  | 8039.76 | 100% |  | 8039.76 | 17535.16 | -9495.4 | 2015-03-17 11:25 | 2016-03-31 | 2015-03-01 | 2015-07-31
75084-DE Kentucky Power Deliv - Ele | FNINT874 | P9120 | Substation Entry Log IVR | 14496.64 |  | 14496.64 | 100% |  | 14496.64 | 26792 | -12295.36 | 2015-03-23 12:54 | 2015-07-31 | 2015-04-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P9531 | Villa Repl TB1 Arresters | 2868.84 |  | 2868.84 | 100% |  | 2868.84 | 3265.27 | -396.43 | 2015-03-27 08:34 | 2016-03-31 | 2015-04-01 | 2015-08-18
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | P9532 | Atlas Repl Station batteries | 1590.37 |  | 1590.37 | 100% |  | 1590.37 | 958.67 | 631.7 | 2015-03-27 09:13 | 2016-03-31 | 2015-07-01 | 2015-11-30
75084-DE Kentucky Power Deliv - Ele | FDOMSIMPL | PCTAIT223 | DOMS IMPLEMENTATION W/AMI | 67205.58 |  | 67205.58 | 100% |  | 191109.03 | 216000 | -24890.97 | 2013-10-25 | 2016-12-31 | 2013-11-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 35430.91 |  | 35430.91 | 100% |  | 59096.17 | 19870 | 39226.17 | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75084-DE Kentucky Power Deliv - Ele | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | 2221.85 |  | 2221.85 | 100% |  | 10504.43 | 9783 | 721.43 | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75084-DE Kentucky Power Deliv - Ele | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 156989.59 |  | 156989.59 | 100% |  | 156989.59 | 285462.99 | -128473.4 | 2015-11-02 12:18 | 2017-09-30 | 2015-10-01 | 2017-07-31
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITH31 | INT165 Hardware | 2062.98 |  | 2062.98 | 100% |  | 2521.08 | 187177 | -184655.92 | 2014-08-14 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF6 | PCTAITH61 | INT83 Hardware | 551.67 |  | 551.67 | 100% |  | 1717.8 | 11602 | -9884.2 | 2014-08-18 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITQ03 | INT165 EI 1 Software | 48.8 |  | 48.8 | 100% |  | 48.8 | 3076 | -3027.2 | 2014-08-17 | 2018-01-31 | 2015-01-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITS31 | INT165 Software | 8873.38 |  | 8873.38 | 100% |  | 11072.02 | 621633 | -610560.98 | 2014-08-14 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITS41 | INT177 Software | 5620.12 |  | 5620.12 | 100% |  | 7634.71 | 46060 | -38425.29 | 2014-07-28 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF5 | PCTAITS51 | INT82b Software | 2724.52 |  | 2724.52 | 100% |  | 3303.17 | 134548 | -131244.83 | 2014-08-17 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF6 | PCTAITS61 | INT83 Software | 2392.18 |  | 2392.18 | 100% |  | 3800.24 | 73320 | -69519.76 | 2014-08-18 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITX03 | INT165 X 1 SOFTWARE | 34273.41 |  | 34273.41 | 100% |  | 48361.43 | 54733 | -6371.57 | 2014-08-24 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITX04 | INT165 X 1 Hardware | 571.93 |  | 571.93 | 100% |  | 2311.43 | 14842 | -12530.57 | 2014-08-24 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITX07 | INT177 X 2 SOFTWARE | 5306.08 |  | 5306.08 | 100% |  | 5308.86 | 5835 | -526.14 | 2014-08-24 | 2018-01-31 | 2014-12-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITX10 | INT177 X 3 Software | 3770.31 |  | 3770.31 | 100% |  | 7260.01 | 1585 | 5675.01 | 2014-08-24 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | FENRGACCT | PCTASW937 | Energy Acctg. & Transm Stand. | 84093.71 |  | 84093.71 | 100% |  | 112490.2 | 96515 | 15975.2 | 2014-07-09 | 2016-04-30 | 2014-08-01 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | PCTAIT85C | PCTAT85C | NetMotion Implementation INT85C | 33679.31 |  | 33679.31 | 100% |  | 53458.58 | 17851 | 35607.58 | 2014-06-08 | 2017-03-30 | 2014-06-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | FPCTAVM | PCTAVM | VEGETATION MGMT-KENTUCKY | 0.05 |  | 0.05 | 100% |  | 10.94 | 25919 | -25908.06 | 2012-11-30 | 2018-01-31 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | PILCFA | PILCKY | UG Cable Repl-PILC | 0 |  | 0 |  |  | 16236.36 | 100 | 16136.36 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | PILCFA | POTTKY | Dline Pothead Termination KY | 0 |  | 0 |  |  | -3.638e-12 | 60000 | -60000 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | FENABLES | PPS | Enable PowerPlan Software | 16315.56 |  | 16315.56 | 100% |  | 16315.56 | 64531 | -48215.44 | 2015-03-30 15:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | PRDFA | PRDKY | Pole Repl Other-D | 1201.84 |  | 1201.84 | 100% |  | 778309.11 | 200 | 778109.11 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | PRIMH | Enable Primavera Hardware | 789.3 |  | 789.3 | 100% |  | 789.3 | 3707 | -2917.7 | 2015-03-30 16:23 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | PRIMS | Enable Primavera Software | 11056.13 |  | 11056.13 | 100% |  | 11056.13 | 154922 | -143865.87 | 2015-03-30 15:12 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | PRTFA | PRTKY | Pole Repl Other-T | 21473.02 |  | 21473.02 | 100% |  | 233359.39 | 200 | 233159.39 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FRAC&SWCH | RAC&SWCHK | RACK & SWITCH INSTALLS | 0 |  | 0 |  |  | 3759.59 | 14463 | -10703.41 | 2010-12-02 | 2010-12-31 | 2011-03-01 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | FRADIOKY | RADIOKENT | IDEN RADIO-KENTUCKY PROJECT | 0 |  | 0 |  |  | 366057.54 | 224500 | 141557.54 | 2010-01-15 | 2011-07-31 | 2010-02-01 | 2011-09-01
75084-DE Kentucky Power Deliv - Ele | UGCIFA | RCABINJKY | Reactive Cable Replacement Kentucky | 0 |  | 0 |  |  | 0 | 250000 | -250000 | 2012-11-16 | 2050-12-31 | 2013-03-01
75084-DE Kentucky Power Deliv - Ele | RCLFA | RCLKY | Recloser Inst/Rem | 0 |  | 0 |  |  | 73437.47 | 200 | 73237.47 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | REGFA | REGKY | Regulator Inst/Rem | 0 |  | 0 |  |  | -1.3074e-12 | 100 | -100 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | RELDKY | Relocation-D | -797.71 |  | -797.71 | 100% |  | 656046.95 | 200 | 655846.95 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RELTFA | RELTKY | Relocation-T | 10833.58 |  | 10833.58 | 100% |  | 322474.73 | 100 | 322374.73 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | 75084 | RETCOV | Retire Covington | 0 |  | 0 |  |  | 0 |  | 0 | 2012-12-20 | 2013-01-05 | 2012-12-01 | 2013-04-05
75084-DE Kentucky Power Deliv - Ele | RLFA | RLKY | Reliability Other-FO-D | -152547.79 |  | -152547.79 | 100% |  | 560885.89 | 200 | 560685.89 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RLFA | RNOVAKY | Cooper Nova Replacement | 0 |  | 0 |  |  | 0 | 60000 | -60000 | 2012-11-02 | 2050-12-31 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | FRR19&AUG | RR19&AUG | 19TH & AUGUSTINE CC RR BLKT | 0 |  | 0 |  |  | 15188.13 | 1 | 15187.13 | 2010-08-30 | 2025-12-15 | 2010-11-01
75084-DE Kentucky Power Deliv - Ele | RRBLKKENT | RRCRITTEN | Critenden Substation Blanket | 0 |  | 0 |  |  | 571.41 | 50000 | -49428.59 | 2013-09-09 | 2050-12-15 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRERLANG | ERLANGER CC RR BLKT | 0 |  | 0 |  |  | 27778.55 | 1 | 27777.55 | 2010-08-30 | 2025-12-15 | 2010-11-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRERLNGMW | ERLANGER MICROWAV-RR BLKT | 0 |  | 0 |  |  | 1122.18 | 1 | 1121.18 | 2011-05-09 | 2025-12-15 | 2011-10-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRKENTON | Kenton Substation Blanket | 0 |  | 0 |  |  | 139.45 | 50000 | -49860.55 | 2012-07-27 | 2025-12-15 | 2012-07-01
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANHWKE | SAN EXPANSION - EMC NS-960 | 0 |  | 0 |  |  | 17560.4 | 62997.65 | -45437.25 | 2010-11-19 | 2011-03-31 | 2010-12-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANSWKE | SAN EXPANSION SOFTWARE | 0 |  | 0 |  |  | 4451.2 | 11152.26 | -6701.06 | 2010-11-19 | 2011-03-31 | 2010-12-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANUPGRKE | SAN FIBR CHANNEL SWCH UPGR | 0 |  | 0 |  |  | 3645.7 | 4023 | -377.3 | 2012-09-05 | 2013-02-18 | 2012-10-01 | 2013-06-13
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANXP12KE | SAN EXPANSION - EMC NS-960 | 0 |  | 0 |  |  | 9398.11 | 9781 | -382.89 | 2012-03-06 | 2012-05-15 | 2012-05-01 | 2012-08-15
75084-DE Kentucky Power Deliv - Ele | SCFOFA | SCFOKY | System Capacity-FO | 0 |  | 0 |  |  | 148499.05 | 100 | 148399.05 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | MTRCAPFA | SCRAPMETK | Scrap Meters | 0 |  | 0 |  |  | 0 | 92 | -92 | 2008-07-01 | 2025-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 5842.09 |  | 5842.09 | 100% |  | 5842.09 | 22774 | -16931.91 | 2015-03-30 14:43 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | CSFA | SDKYT111 | Villa 41, Crescent 41, Constance 44 | 0 |  | 0 |  |  | 179948.64 | 134316.91 | 45631.73 | 2011-08-03 | 2012-12-31 | 2011-09-01 | 2012-03-12
75084-DE Kentucky Power Deliv - Ele | 75084 | SFTWRE | Software Retirements-Asset Use | 0 |  | 0 |  |  | 0 |  | 0 | 2012-09-20 | 2026-03-30 | 2012-09-01
75084-DE Kentucky Power Deliv - Ele | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | 1829.57 |  | 1829.57 | 100% |  | 52164.94 | 250000 | -197835.06 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | SGAMIDMS | SGADMS33 | SG Upgrade Alstom DMS to ver 3.3 | 115240.02 |  | 115240.02 | 100% |  | 115249.68 | 68579 | 46670.68 | 2014-12-18 | 2016-07-20 | 2014-12-01 | 2016-07-15
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGAMIDOM | SG AMI to DOMS Outage Capital | 0 |  | 0 |  |  | 39944.15 | 39944.15 | 0 | 2011-05-26 | 2011-12-16 | 2011-06-01 | 2012-03-13
75084-DE Kentucky Power Deliv - Ele | SGITOMSGI | SGARCSRVC | Smart Grid ARC Server Project | 0 |  | 0 |  |  | 24134.87 | 35517 | -11382.13 | 2010-09-24 | 2010-11-30 | 2010-10-01 | 2011-03-08
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGBRWTRH | Bridgewater AAA Implement HW | 0 |  | 0 |  |  | 1860.57 | 2100 | -239.43 | 2011-12-08 | 2009-02-19 | 2011-12-01 | 2009-05-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGBRWTRS | Bridgewater AAA Implement SW | 0 |  | 0 |  |  | 4391.55 | 4800 | -408.45 | 2011-12-01 | 2009-02-19 | 2011-12-01 | 2009-05-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGCAMIHW | Smart Grid Carolinas AMI Hardware | 0 |  | 0 |  |  | 27968.85 | 15255 | 12713.85 | 2012-08-10 | 2012-12-31 | 2012-08-01 | 2013-03-20
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGCAPRIKY | SG Kentucky Capacitors for R&I | 42409.19 |  | 42409.19 | 100% |  | 214460.46 | 230000 | -15539.54 | 2013-11-01 | 2015-03-30 | 2013-12-01
75084-DE Kentucky Power Deliv - Ele | SGKYCS | SGCSDCI3 | ECS daily usage cap | 0 |  | 0 |  |  | 12362.77 | 15000 | -2637.23 | 2010-10-01 | 2014-12-31 | 2010-09-01 | 2010-06-24
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGCSRIKY | Circuit Sectionalization - KY | -41659.98 |  | -41659.98 | 100% |  | -41659.98 | 100 | -41759.98 | 2013-05-24 | 2015-06-30 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDADMS | Dist Mgt Sys cap | -84.64 |  | -84.64 | 100% |  | 1489518.8 | 1511877.7 | -22358.9 | 2010-10-01 | 2014-07-30 | 2010-09-01 | 2014-05-19
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDEETHW | SG DMS Distribution DEETS HW | 0 |  | 0 |  |  | 7954.17 | 2373 | 5581.17 | 2011-09-30 | 2014-10-31 | 2011-11-01 | 2013-07-29
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDEETSW | SG DMS Distribution DEETS SW | 0 |  | 0 |  |  | 18945.76 | 23915.77 | -4970.01 | 2011-09-30 | 2014-10-31 | 2011-10-01 | 2013-07-29
75084-DE Kentucky Power Deliv - Ele | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | -1.3878e-17 |  | -1.3878e-17 | 100% |  | 61898.59 | 62278.49 | -379.9 | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGECHLDA | SG Echelon Local Data Access | 0 |  | 0 |  |  | 8364.35 | 9765 | -1400.65 | 2010-09-30 | 2014-12-31 | 2010-09-01 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 7660.69 |  | 7660.69 | 100% |  | 7660.69 | 6421 | 1239.69 | 2015-06-10 18:11 | 2016-08-21 | 2015-06-01 | 2016-06-04
75084-DE Kentucky Power Deliv - Ele | SGETOASF | SGETOAS | SG TOA Replacement Software | 20881.45 |  | 20881.45 | 100% |  | 20881.45 | 208124 | -187242.55 | 2015-04-06 13:58 | 2019-03-27 | 2015-05-01
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0 |  | 0 |  |  | 132348 | 130000 | 2348 | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGITRNSLH | ITRON SG Solutions Hardware | 0 |  | 0 |  |  | 3779.19 | 6000 | -2220.81 | 2011-07-14 | 2012-06-30 | 2011-10-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | SGITRONLF | SGITRONL | SG Itron Meter Licenses | 148681.16 |  | 148681.16 | 100% |  | 148681.16 | 148524.18 | 156.98 | 2015-12-30 11:54 | 2016-04-30 | 2015-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGCIAMIF | SGKAMICI | SG Kentucky C&I AMI Meters | 93666.1 |  | 93666.1 | 100% |  | 93666.1 | 454386.03 | -360719.93 | 2015-05-29 12:53 | 2018-05-15 | 2015-09-01
75084-DE Kentucky Power Deliv - Ele | SGNMS | SGKIPV6ML | SG DEK ITRON Software NMS Endpoints | 0 |  | 0 |  |  | 585678.5 | 585000 | 678.5 | 2014-06-27 | 2015-01-31 | 2014-08-01 | 2014-12-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGKTLPLC | SG DEK Trans Pole Replacement | 31084.86 |  | 31084.86 | 100% |  | 31804.45 | 25000 | 6804.45 | 2014-09-12 | 2015-06-30 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | SGEZYWANF | SGKZYWAN | SG KY ZyWAN Modem Replace | 16494.46 |  | 16494.46 | 100% |  | 16494.46 | 11372 | 5122.46 | 2015-06-11 15:04 | 2016-03-15 | 2015-06-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGLSRIKY | SG KY Line Sensor Project for R&I | 100622.08 |  | 100622.08 | 100% |  | 350451.47 | 314000 | 36451.47 | 2013-11-01 | 2015-03-30 | 2013-12-01
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMFDHW | SG MDM Foundation Hardware | 0 |  | 0 |  |  | 73191.26 | 514545.92 | -441354.66 | 2012-04-20 | 2013-10-31 | 2012-05-01 | 2013-10-29
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMFDSW | SG MDM Foundation Custom SW | 0 |  | 0 |  |  | 509256.19 | 440000 | 69256.19 | 2012-04-20 | 2013-10-31 | 2012-04-01 | 2013-10-29
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMM2C | SG MDM Mass Market 2 - CMS Work | 0 |  | 0 |  |  | 3.61 | 31372 | -31368.39 | 2014-11-03 | 2015-02-16 | 2014-11-01 | 2015-02-17
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 370.73 |  | 370.73 | 100% |  | 40758.66 | 392765 | -352006.34 | 2014-04-28 | 2015-02-16 | 2014-04-01 | 2015-02-17
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMMH | SG MDM Mass Market Hardware | 0 |  | 0 |  |  | 10834.61 | 77000 | -66165.39 | 2013-07-10 | 2014-09-30 | 2013-12-01 | 2014-08-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0 |  | 0 |  |  | 183577.67 | 33000 | 150577.67 | 2013-07-10 | 2014-09-30 | 2013-07-01 | 2014-08-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMS | Meter Data Management System | 0 |  | 0 |  |  | 197462 | 252000 | -54538 | 2011-11-30 | 2010-06-18 | 2011-11-01 | 2010-09-18
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 0 |  | 0 |  |  | 71270.12 | 33000 | 38270.12 | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGMGTRIKY | SG KY Sectionalization R&I Mgmt Prj | -38986.88 |  | -38986.88 | 100% |  | 0 | 25000 | -25000 | 2013-11-01 | 2015-03-30 | 2013-12-01 | 2015-03-15
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGMWSCADH | Smart Grid Midwest SCADA Hardware | 0 |  | 0 |  |  | 14317.22 | 17715 | -3397.78 | 2011-06-29 | 2011-12-31 | 2011-10-01 | 2011-08-31
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGMWSCADS | Smart Grid Midwest SCADA Software | 0 |  | 0 |  |  | 133886.34 | 168748 | -34861.66 | 2011-06-29 | 2011-12-31 | 2011-10-01 | 2011-08-31
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGNDENSW | Echelon NET SW Cap | 0 |  | 0 |  |  | 31031.1 | 20000 | 11031.1 | 2010-09-30 | 2014-12-31 | 2010-09-01 | 2011-03-10
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG36 | NES 3.0 Upgrade SGS.036 | 0 |  | 0 |  |  | 3818.02 | 4238 | -419.98 | 2011-12-02 | 2009-03-18 | 2011-12-01 | 2009-06-18
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG38 | NES EM System SGS.038 | 0 |  | 0 |  |  | 5685.2 | 5424 | 261.2 | 2011-12-06 | 2009-10-20 | 2011-12-01 | 2010-01-20
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG45H | NES Test Envir SGS.045 HW | 0 |  | 0 |  |  | 3493.06 | 4916 | -1422.94 | 2011-12-06 | 2009-10-22 | 2011-12-01 | 2010-01-22
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG45S | NES Test Envir SGS.045 SW | 0 |  | 0 |  |  | 7913.38 | 6441 | 1472.38 | 2011-12-08 | 2009-10-22 | 2011-12-01 | 2010-01-22
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG51 | NES 4.1 Upgrade SGS.051 | 0 |  | 0 |  |  | 15797.81 | 6441 | 9356.81 | 2011-12-08 | 2010-12-10 | 2011-12-01 | 2011-03-10
75084-DE Kentucky Power Deliv - Ele | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 10485.52 |  | 10485.52 | 100% |  | 18566.54 | 43500 | -24933.46 | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 0 |  | 0 |  |  | 7630.72 | 7630.72 | 0 | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | 0 |  | 0 |  |  | 57834.44 | 60000 | -2165.56 | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 7.05 |  | 7.05 | 100% |  | 4758.71 | 170000 | -165241.29 | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75084-DE Kentucky Power Deliv - Ele | SGNNT1021 | SGNT1021B | SG NINT1021B - SERVERS | 0 |  | 0 |  |  | 220.7 | 170000 | -169779.3 | 2014-04-30 | 2014-11-30 | 2014-08-01 | 2015-02-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGRCRIKY | SG DEK Reserve Capacity Meters | 29451.84 |  | 29451.84 | 100% |  | 114673.9 | 115000 | -326.1 | 2014-05-12 | 2015-03-30 | 2014-06-01 | 2015-04-30
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGROFEDM6 | Remote Order Fulfillment EDM.06 | 0 |  | 0 |  |  | 15632.51 | 12543 | 3089.51 | 2011-12-08 | 2009-03-19 | 2011-12-01 | 2009-06-19
75084-DE Kentucky Power Deliv - Ele | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -469.77 |  | -469.77 | 100% |  | 480.58 | 1 | 479.58 | 2010-09-30 | 2017-12-31 | 2010-09-01
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI01 | SG Secure Network Infrastructure | 59777.59 |  | 59777.59 | 100% |  | 61436.24 | 50075 | 11361.24 | 2014-12-12 | 2016-08-30 | 2014-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI02 | SG Secure Network Infrastructure | 39954.94 |  | 39954.94 | 100% |  | 41563.66 | 50075 | -8511.34 | 2014-12-12 | 2016-06-30 | 2014-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGSTRGC | Smart Grid Storage Project | 0 |  | 0 |  |  | 128657.15 | 169806 | -41148.85 | 2010-06-16 | 2010-11-30 | 2010-09-01 | 2011-02-17
75084-DE Kentucky Power Deliv - Ele | SGITOMSGI | SGSWDOMC | SG AMI DOMS S/W Module Capital | 3132.96 |  | 3132.96 | 100% |  | 27733.01 | 37300 | -9566.99 | 2012-12-20 | 2015-08-29 | 2013-01-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGSYED11 | EDM.11 SG Scaling/Tech Hlth | 0 |  | 0 |  |  | 111333.51 | 465000 | -353666.49 | 2010-09-30 | 2010-03-04 | 2010-09-01 | 2010-06-04
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGSYED15 | SG EDM.15 EDMS Scalability-Hardware | 0 |  | 0 |  |  | 52213.53 | 73333 | -21119.47 | 2010-09-14 | 2010-09-30 | 2010-09-01 | 2011-02-24
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGSYEDP2 | SG Scalability Phase 2 EDM064 | 0 |  | 0 |  |  | 217795.82 | 800000 | -582204.18 | 2010-08-13 | 2011-09-30 | 2010-09-01 | 2011-08-13
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1102CP | Journal KY storm costs O&M to CAP | 0 |  | 0 |  |  | 1931.19 | 1985.66 | -54.47 | 2011-07-01 | 2012-07-31 | 2011-06-01 | 2011-09-30
75084-DE Kentucky Power Deliv - Ele | ORTFA | SKY1201TC | Kentucky Storm O&M to cap Trans | 0 |  | 0 |  |  | 65330.32 | 66245.76 | -915.44 | 2012-03-29 | 2012-07-31 | 2012-03-01 | 2012-06-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1203DC | Kentucky Storm O&M to Capital | 0 |  | 0 |  |  | 34459.11 | 42865.9 | -8406.79 | 2012-09-28 | 2012-10-31 | 2012-09-01 | 2012-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1204DC | Kentucky Storm O&M to Capital | 0 |  | 0 |  |  | 2532.42 | 2000 | 532.42 | 2012-12-31 | 2013-03-31 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1302DC | KENTUCKY O&M TO CAPITAL JOURNAL Q 2 | 0 |  | 0 |  |  | 16563.88 | 20425.5 | -3861.62 | 2013-06-20 | 2014-03-30 | 2013-06-01 | 2013-10-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1303DC | KENTUCKY O&M TO CAPITAL JRNL Q3 & 4 | 0 |  | 0 |  |  | 19866.39 | 22145.46 | -2279.07 | 2013-06-20 | 2014-03-30 | 2013-12-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1401DC | KENTUCKY O&M TO CAPITAL JOURNAL Q 1 | -10.83 |  | -10.83 | 100% |  | 1475.4 | 1330.27 | 145.13 | 2014-04-28 | 2016-03-31 | 2014-05-01 | 2014-09-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1404DC | Kentucky O&M - CAPITAL JOURNAL Q3&4 | -1.19 |  | -1.19 | 100% |  | 18025.48 | 20382.68 | -2357.2 | 2014-12-30 | 2016-03-31 | 2014-12-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1501DC | KENTUCKY O&M TO CAP JOURNAL Q 1 | 1215.79 |  | 1215.79 | 100% |  | 1215.79 | 1202.56 | 13.23 | 2015-04-01 09:50 | 2015-12-31 | 2015-03-01 | 2015-05-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1502DC | Kentucky O&M To Capital Journal | 987.64 |  | 987.64 | 100% |  | 987.64 | 987.64 | 0 | 2015-07-30 15:55 | 2016-12-31 | 2015-07-01 | 2015-10-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1504DC | Kentucky O&M To Capital Journal | 25594.95 |  | 25594.95 | 100% |  | 25594.95 | 26188 | -593.05 | 2015-10-15 15:45 | 2016-12-31 | 2015-10-01 | 2016-01-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1505DC | Kentucky O&M To Capital Journal | 13595.98 |  | 13595.98 | 100% |  | 13595.98 | 13749.97 | -153.99 | 2015-10-15 15:47 | 2016-12-31 | 2015-10-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | SLFA | SLKY | Light Repl-Tarriff | -1.4211e-14 |  | -1.4211e-14 | 100% |  | 144198.34 | 299 | 143899.34 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | SSDTH | Enable Subst Design Tool Hardware | 93.72 |  | 93.72 | 100% |  | 93.72 | 118 | -24.28 | 2015-03-30 15:04 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | SSDTS | Enable Subst Design Tool Software | 9298.35 |  | 9298.35 | 100% |  | 9298.35 | 79764 | -70465.65 | 2015-03-30 14:36 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT112 | Kenton 41 & Kenton 44 2012 | 0 |  | 0 |  |  | 122048.92 | 116524.81 | 5524.11 | 2011-10-31 | 2012-12-31 | 2011-11-01 | 2012-11-28
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT212 | Augustine 41 & Crescent 42 2012 | 0 |  | 0 |  |  | 77450.08 | 121431.31 | -43981.23 | 2011-10-31 | 2012-12-31 | 2011-11-01 | 2013-01-24
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT34 | SG Verona 41 & Crittenden 41 | 0 |  | 0 |  |  | 81187.39 | 72328.13 | 8859.26 | 2012-11-01 | 2014-03-31 | 2012-12-01 | 2013-08-30
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT36 | SG DEK Self Healing Team 36 Capital | 12028.73 |  | 12028.73 | 100% |  | 101437.63 | 206458.63 | -105021 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2014-12-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT37 | SG DEK Self Healing Team 37 Capital | 12579.45 |  | 12579.45 | 100% |  | 56843.7 | 71071.44 | -14227.74 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2015-01-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT38 | SG DEK Self Healing Team 38 Capital | 16707.04 |  | 16707.04 | 100% |  | 145785.26 | 122442.2 | 23343.06 | 2014-04-21 | 2015-07-31 | 2014-05-01 | 2015-04-30
75084-DE Kentucky Power Deliv - Ele | FSTRMTRLR | STORMTRLR | IDEN STORM TRAILER | 0 |  | 0 |  |  | 96106.51 | 124505 | -28398.49 | 2011-12-16 | 2012-11-15 | 2011-12-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | MTRTOOLFA | TBIMTRLAB | Metering Capital Tools | 0 |  | 0 |  |  | 23498.19 | 1 | 23497.19 | 2008-07-01 | 2050-12-31 | 2009-07-01
75084-DE Kentucky Power Deliv - Ele | FTDITKE | TDITCHAR | PD KENTUCKY IT HARDWARE | 0 |  | 0 |  |  | 144.8 |  | 144.8 | 2009-08-27 | 2025-12-25 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | TEMPSVC | Temporary Service | 0 |  | 0 |  |  | 0 |  | 0 | 2008-07-01 | 2008-06-28 21:34 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | THEFTCOND | REPL STOLEN IN-SRVC OVRHD COND - KY | 16947.23 |  | 16947.23 | 100% |  | 28808.51 | 100 | 28708.51 | 2014-06-10 | 2025-12-31 | 2014-06-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | TIMH | Enable TIM Hardware | 3.39 |  | 3.39 | 100% |  | 3.39 | 84 | -80.61 | 2015-03-30 14:56 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | TIMS | Enable TIM Software | 21438.31 |  | 21438.31 | 100% |  | 21438.31 | 239157 | -217718.69 | 2015-03-30 14:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | CERTFA | TLPIKY | Transm Lightning Perf Improvements | 0 |  | 0 |  |  | 15985.5 | 75000 | -59014.5 | 2012-01-04 | 2050-12-31 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | TLSRKY | Transm Line Switch Replacement | 0 |  | 0 |  |  | 5138.64 | 70000 | -64861.36 | 2012-01-04 | 2050-12-31 | 2014-07-01
75084-DE Kentucky Power Deliv - Ele | TOOLFA | TOOLKY | Tools & Equip | 135407.94 |  | 135407.94 | 100% |  | 965903.7 | 101 | 965802.7 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | TPCTH | Enable Trans Proj Cost Hardware | 185.66 |  | 185.66 | 100% |  | 185.66 | 1411 | -1225.34 | 2015-08-04 10:47 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | TPCTS | Enable Tran Proj Cost Software | 14951.57 |  | 14951.57 | 100% |  | 14951.57 | 208628 | -193676.43 | 2015-08-03 16:47 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLEH | TPETH | Enable Trans Proj Est Hardware | 193.27 |  | 193.27 | 100% |  | 193.27 | 1073 | -879.73 | 2015-08-04 11:22 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | TPETS | Enable Trans Proj Est Software | 26286.54 |  | 26286.54 | 100% |  | 26286.54 | 142915 | -116628.46 | 2015-08-03 16:52 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY10 | DIST TRANSFORMERS PUR 2010 | 0 |  | 0 |  |  | 1018111.3 | 1 | 1018110.3 | 2014-02-04 | 2015-12-31 | 2014-02-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY11 | DIST TRANSFORMERS PUR 2011 | 0 |  | 0 |  |  | 363165.36 | 1 | 363164.36 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY12 | DIST LINE TRANSFORMERS PUR 2012 | 0 |  | 0 |  |  | 300925.74 | 1 | 300924.74 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY13 | DIST LINE TRANSFORMERS PUR 2013 | 0 |  | 0 |  |  | 491191.31 | 1 | 491190.31 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | FNINT1229 | TRNPRIMAV | NINT1229 - Trans Primavera Upgr | 66856.16 |  | 66856.16 | 100% |  | 77723.64 | 78058.34 | -334.7 | 2014-08-03 | 2017-10-31 | 2014-08-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | UGCRFA | UGCRKY | UG Cable Repl | 23.24 |  | 23.24 | 100% |  | 337829.44 | 100 | 337729.44 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | VMDDTFA | VMCMCKY | R/W CKT MAINT CAP KENTUCKY | 365820.75 |  | 365820.75 | 100% |  | 1693769.16 | 1 | 1693768.16 | 2012-01-25 | 2050-12-31 | 2012-02-01
75084-DE Kentucky Power Deliv - Ele | VMDDTFA | VMDDTKY | Distr Line Clr Removal | 231450.8 |  | 231450.8 | 100% |  | 1414516.14 | 1 | 1414515.14 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | VMTDFA | VMTDKY | Trans Line Clr Removal | 36833.14 |  | 36833.14 | 100% |  | 172086.79 | 1 | 172085.79 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FENABLES | WRTS | Enable WRT & WMSP Software | 15320.2 |  | 15320.2 | 100% |  | 15320.2 | 168186 | -152865.8 | 2015-03-30 14:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | U14ZKVCH | ZC071 | ULHP DistLine Capacitor Switch | 0 |  | 0 |  |  | 0 | 1 | -1 | 2008-02-14 | 2050-12-31 | 2008-03-01
75084-DE Kentucky Power Deliv - Ele | 312ZLEL | ZE083 | OLE LIGHTING South ULHP CP3 | 0 |  | 0 |  |  | 0 | 1 | -1 | 2007-12-20 | 2009-04-01 | 2008-01-01
75084-DE Kentucky Power Deliv - Ele | U04ZTREE | ZV070 | DANGER TREE - TRANS - ULHP | 0 |  | 0 |  |  | 4273.99 | 1 | 4272.99 | 2007-04-26 | 2050-12-31 | 2007-04-01 | 2008-03-31
75084-DE Kentucky Power Deliv - Ele | U14ZTREE | ZV071 | DANGER TREE - DIST - ULHP | 0 |  | 0 |  |  | 0 | 1 | -1 | 2007-04-26 | 2050-12-31 | 2007-06-01
75085-DE Kentucky Cus Service - Ele | FPIT | 300893C | 300893C Proactive Communications | 68714.67 |  | 68714.67 | 100% |  | 68714.67 | 37518.23 | 31196.44 | 2015-04-20 15:04 | 2015-12-31 | 2015-05-01 | 2016-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | 307558AUG | 307558AUG Pro Comm Enhancements | 558.16 |  | 558.16 | 100% |  | 558.16 | 10594 | -10035.84 | 2015-12-21 10:37 | 2016-09-30 | 2015-12-01 | 2016-12-31
75085-DE Kentucky Cus Service - Ele | FPIT | 307558MAY | 307558MAY Pro Comm Enhancements | 2408.98 |  | 2408.98 | 100% |  | 2408.98 | 36481 | -34072.02 | 2015-12-21 09:51 | 2016-06-30 | 2015-12-01 | 2017-01-19
75085-DE Kentucky Cus Service - Ele | FPIT | 311803CS | Lighting System Integration Softwar | 8658.32 |  | 8658.32 | 100% |  | 8658.32 | 157966.53 | -149308.21 | 2015-09-14 13:59 | 2019-03-31 | 2015-11-01
75085-DE Kentucky Cus Service - Ele | AMIKY | C8779 | AMI Mt Zion Advanced Meter | 0 |  | 0 |  |  | 79580.84 | 101605 | -22024.16 | 2007-01-04 | 2007-12-31 | 2007-01-01 | 2007-12-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9041 | AMI Hands Advanced Meter | 0 |  | 0 |  |  | 202616.61 | 153106 | 49510.61 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9042 | AMI Empire Advanced Meter | 0 |  | 0 |  |  | 117897.99 | 137706 | -19808.01 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9043 | AMI Kenton Advanced Meter | 0 |  | 0 |  |  | 179935.34 | 197559 | -17623.66 | 2007-01-07 | 2007-12-31 | 2007-01-01 | 2007-12-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9044 | AMI Wilder Advanced Meter | 0 |  | 0 |  |  | 41017.98 | 200835 | -159817.02 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9045 | AMI Donaldson Advanced Meter | 0 |  | 0 |  |  | 59674.83 | 151468 | -91793.17 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9046 | AMI Oakbrook Advanced Meter | 0 |  | 0 |  |  | 62106.41 | 94724 | -32617.59 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9047 | AMI Atlas Advanced Meter | 0 |  | 0 |  |  | 11249.91 | 93304 | -82054.09 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9048 | AMI Claryville Advanced Meter | 0 |  | 0 |  |  | 35936.31 | 158349 | -122412.69 | 2007-01-07 | 2009-08-31 | 2007-07-01 | 2009-08-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9049 | AMI Florence Advanced Meter | 0 |  | 0 |  |  | 81306.22 | 189695 | -108388.78 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9050 | AMI Villa Advanced Meter | 0 |  | 0 |  |  | 59478.75 | 150703 | -91224.25 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9051 | AMI Dixie Advanced Meter | 0 |  | 0 |  |  | 50283.84 | 154744 | -104460.16 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2008-01-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9052 | AMI Buffington Advanced Meter | 0 |  | 0 |  |  | 76372.45 | 191879 | -115506.55 | 2007-01-07 | 2008-03-15 | 2007-02-01 | 2008-06-30
75085-DE Kentucky Cus Service - Ele | EMSBLADE | C9288 | Midwest EMS Blade Server Infra | 0 |  | 0 |  |  | 16913.75 | 18468 | -1554.25 | 2007-02-14 | 2007-12-31 | 2007-02-01 | 2008-03-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9449 | AMI Dry Ridge Advanced Meter | 0 |  | 0 |  |  | 56532.74 | 95052 | -38519.26 | 2007-03-16 | 2007-10-15 | 2007-04-01 | 2007-10-15
75085-DE Kentucky Cus Service - Ele | AMIKY | D1128 | AMI Thomas More Advanced Mete | 0 |  | 0 |  |  | 10657.81 | 1 | 10656.81 | 2007-07-04 | 2008-06-15 | 2007-07-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | D1144 | AMI West End Advanced Meter | 0 |  | 0 |  |  | 50286.69 | 50000 | 286.69 | 2007-07-06 | 2011-03-31 | 2007-07-01 | 2009-01-01
75085-DE Kentucky Cus Service - Ele | FEBPE1A | EBPE1 | Electronic Billing & Payment Ex Ph1 | 0 |  | 0 |  |  | 61896.29 | 72600 | -10703.71 | 2011-05-20 | 2011-12-31 | 2011-06-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FEBPE1A | EBPE2 | EBPE Phase 2 | 0 |  | 0 |  |  | 46724.42 | 47000 | -275.58 | 2012-02-20 | 2012-12-31 | 2012-02-01 | 2012-12-17
75085-DE Kentucky Cus Service - Ele | SGITCS | ECSDCI1 | Enterprise Cust syst DCI1 Capital | 0 |  | 0 |  |  | 31257.61 | 100000 | -68742.39 | 2011-02-24 | 2015-06-30 | 2011-03-01 | 2010-09-18
75085-DE Kentucky Cus Service - Ele | SGITCS | ECSDCI2 | Enterprise Cust system DCI2 Capital | 0 |  | 0 |  |  | 3473.74 | 100000 | -96526.26 | 2011-04-13 | 2015-03-15 | 2011-04-01 | 2011-11-30
75085-DE Kentucky Cus Service - Ele | RCPSPROJ | LRIEDM42 | Load Research Interfaces EDM042 | 0 |  | 0 |  |  | 28724.53 | 315500 | -286775.47 | 2011-05-24 | 2011-11-30 | 2011-06-01 | 2012-03-01
75085-DE Kentucky Cus Service - Ele | FPIT | MFEOLREPL | Mainframe EOL Repl | 0 |  | 0 |  |  | 51555.84 | 53881.98 | -2326.14 | 2012-05-31 | 2012-09-30 | 2012-06-01 | 2012-12-19
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1024C | NINT1024 Knowledge Management Tool | 125.35 |  | 125.35 | 100% |  | 18067.34 | 12541.38 | 5525.96 | 2014-01-13 | 2014-12-30 | 2014-02-01 | 2014-11-23
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1139H | NINT1139 CCO TPO MODEL | 658.12 |  | 658.12 | 100% |  | 658.12 | 3900.88 | -3242.76 | 2014-12-17 | 2014-12-31 | 2015-01-01 | 2015-08-18
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1139L | NINT1139 CCO TPO MODEL | 3267.81 |  | 3267.81 | 100% |  | 3267.81 | 3835.9 | -568.09 | 2014-12-17 | 2014-12-31 | 2015-04-01 | 2016-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 10.46 |  | 10.46 | 100% |  | 10.46 | 18000 | -17989.54 | 2015-11-16 14:15 | 2016-09-30 | 2015-12-01 | 2017-03-27
75085-DE Kentucky Cus Service - Ele | FPIT | NINT979C | NINT979C Combined Mobile SMS TXT | 1942.14 |  | 1942.14 | 100% |  | 31381.49 | 22322.04 | 9059.45 | 2014-10-01 | 2014-12-31 | 2014-10-01 | 2015-05-20
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA1049C | INT1049 BRNR | 23212.73 |  | 23212.73 | 100% |  | 45199.91 | 47222.49 | -2022.58 | 2014-10-23 | 2015-07-31 | 2014-11-01 | 2015-10-17
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175AC | Customer Contact Preference Center | 0 |  | 0 |  |  | 41139.94 | 34008 | 7131.94 | 2013-08-01 | 2014-10-14 | 2013-08-01 | 2014-10-14
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175BS | PCTA175BS CDS | 4697.68 |  | 4697.68 | 100% |  | 4988.82 | 78939.89 | -73951.07 | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA210C | Contact Channels Datamart & Dashboa | 0 |  | 0 |  |  | 8641.02 | 7351.4 | 1289.62 | 2013-10-22 | 2014-09-23 | 2013-11-01 | 2014-09-23
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AC | CA Lisa | 39 |  | 39 | 100% |  | 11718.57 | 9387.72 | 2330.85 | 2014-10-21 | 2015-11-30 | 2014-11-01 | 2015-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AH | INT481A CDP Hardware Implementation | -1.28 |  | -1.28 | 100% |  | 9160.87 | 14924.07 | -5763.2 | 2014-10-23 | 2015-11-30 | 2014-11-01 | 2015-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AS | Sitecore | 508964.25 |  | 508964.25 | 100% |  | 722868.67 | 520043.89 | 202824.78 | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75085-DE Kentucky Cus Service - Ele | FPIT | PCTAIT17X | Mobile Web Phase 1 | 0 |  | 0 |  |  | 6622.7 | 3580 | 3042.7 | 2013-01-20 | 2013-10-30 | 2013-03-01 | 2014-01-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTAIVRSW | IVR Software and Licenses | 0 |  | 0 |  |  | 83234.43 | 84000 | -765.57 | 2013-03-12 | 2014-07-31 | 2013-05-01 | 2014-08-15
75085-DE Kentucky Cus Service - Ele | FPIT | RCDPSSK | Dynamic Pricing Solution System | 0 |  | 0 |  |  | 83424.32 | 84000 | -575.68 | 2012-01-31 | 2013-03-31 | 2012-02-01 | 2013-01-28
75085-DE Kentucky Cus Service - Ele | FPIT | RCDRCETK | Daily Rating Charging Estimate Tool | 0 |  | 0 |  |  | 26202.58 | 27000 | -797.42 | 2012-01-31 | 2013-03-31 | 2012-02-01 | 2013-01-28
75085-DE Kentucky Cus Service - Ele | FPIT | RCIVRMKE | IVR Monitoring Systems | 0 |  | 0 |  |  | 3320.23 | 3450 | -129.77 | 2012-06-13 | 2012-12-31 | 2012-09-01 | 2013-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWHWC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 123830.93 | 124000 | -169.07 | 2011-07-22 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 232943.03 | 162502.14 | 70440.89 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWTELC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 10402.84 | 11000 | -597.16 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | AMIKYCS | ZY072 | AMI GAS & ELECTRIC METERS | 0 |  | 0 |  |  | 601512.93 | 1 | 601511.93 | 2007-02-05 | 2050-12-31 | 2007-07-01 | 2008-07-01
|  |  |  | 75942489.91 | 57228461.1278 | 18714028.7822 | 32.7%

## 2016
Duke Energy Kentucky Electric
Year 2016
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75080-DE Kentucky Other - Elec | FMWAVEKY | 20218019A | 20218019th & Augustine Test Equip | -0.41 |  | -0.41 | 100% |  | 2982.6 | 49950 | -46967.4 | 2015-06-10 17:09 | 2015-12-30 | 2015-07-01 | 2016-03-30
75080-DE Kentucky Other - Elec | FMWAVEKY | 307282AAA | 307282 - 19th&Augustine BndWth Proj | 9300.94 |  | 9300.94 | 100% |  | 9300.94 | 152096 | -142795.06 | 2016-10-19 08:11 | 2017-06-30 | 2016-11-01 | 2017-08-04
75080-DE Kentucky Other - Elec | MWAVEELEC | 307282AAB | 307282 - Augustine BndWth @ Sub. | 1284.52 |  | 1284.52 | 100% |  | 1284.52 | 21606 | -20321.48 | 2016-10-19 09:37 | 2017-06-30 | 2016-11-01 | 2017-08-04
75080-DE Kentucky Other - Elec | FMWAVEKY | 315218GLC | 315218 Markland Dam Mod. Glenco | 84.13 |  | 84.13 | 100% |  | 84.13 | 87365.45 | -87281.32 | 2016-11-03 10:59 | 2017-11-01 | 2016-12-01
75080-DE Kentucky Other - Elec | FMWAVEKY | 315218SPR | 315218 - Markland Dam Mod. Sparta | 83.88 |  | 83.88 | 100% |  | 83.88 | 113451.43 | -113367.55 | 2016-11-03 10:37 | 2017-11-01 | 2016-12-01
75080-DE Kentucky Other - Elec | FMWAVEKY | 315218VR2 | 315218 - Markland Dam Mod. Verona2 | 84.13 |  | 84.13 | 100% |  | 84.13 | 87728 | -87643.87 | 2016-11-03 11:49 | 2017-11-01 | 2016-12-01
75080-DE Kentucky Other - Elec | FMWAVEKY | 315218VRR | 315218 - Markland Dam Mod. Verona | 264.68 |  | 264.68 | 100% |  | 264.68 | 106349.71 | -106085.03 | 2016-11-02 16:24 | 2017-11-01 | 2016-12-01
75080-DE Kentucky Other - Elec | MWTELBLKT | ALEXCOOP | Alexandria Cooper Microwave Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-09-11 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | SITESVCS | BATGNKY09 | Install Backup Generators | 0 |  | 0 |  |  | 146836.04 | 146836 | 0.04 | 2009-06-03 | 2010-10-15 | 2009-11-01 | 2010-10-15
75080-DE Kentucky Other - Elec | MWTELBLKT | BUTLERBKT | Butler Tower Blanket | 0 |  | 0 |  |  | 270.59 | 50000 | -49729.41 | 2013-09-05 | 2025-12-31 | 2013-09-01
75080-DE Kentucky Other - Elec | TELBLKT | BVRLCKBKT | Beaverlick Tower Blanket | -5300 |  | -5300 | 100% |  | 2166.3 | 50000 | -47833.7 | 2011-10-18 | 2019-12-31 | 2011-12-01
75080-DE Kentucky Other - Elec | DCITEDM | C8768 | EDM Project | 0 |  | 0 |  |  | 742848.83 | 1 | 742847.83 | 2007-01-04 | 2009-05-31 | 2007-03-01 | 2009-07-19
75080-DE Kentucky Other - Elec | RADIOS07 | C9258 | RADIO REPLACEMENT PROGRAM 2007 | 0 |  | 0 |  |  | 1074336.23 | 1 | 1074335.23 | 2007-02-09 | 2008-12-31 | 2007-03-01 | 2008-12-31
75080-DE Kentucky Other - Elec | RADIO | CABLEKY13 | Install Pag Transmitter Cable & Ant | 0 |  | 0 |  |  | 14034.97 | 14034.97 | 0 | 2011-09-06 | 2013-12-31 | 2012-07-01 | 2014-04-09
75080-DE Kentucky Other - Elec | CIS123CP2 | CIS123LBM | BancTec Prod Bckp Svr_CIS 123 Pr Mg | 0 |  | 0 |  |  | 8895.78 | 7582 | 1313.78 | 2010-08-16 | 2011-04-29 | 2010-12-01 | 2011-08-06
75080-DE Kentucky Other - Elec | CIS123CAP | CIS123LBS | BancTec Software and Installation | 0 |  | 0 |  |  | 35115.81 | 25979 | 9136.81 | 2010-08-13 | 2011-04-29 | 2010-08-01 | 2011-08-06
75080-DE Kentucky Other - Elec | 75080 | CPRCRCT | CPR Corrections - Asset Acctg Only | 0 |  | 0 |  |  | 0 | 1 | -1 | 2012-08-28 | 2050-12-30 | 2012-10-01
75080-DE Kentucky Other - Elec | DCITCD2 | D1182 | Common Design Tools Phsase 2 | 0 |  | 0 |  |  | 6581.74 | 1 | 6580.74 | 2007-07-12 | 2011-03-31 | 2007-10-01 | 2011-03-17
75080-DE Kentucky Other - Elec | EPS100 | D1384 | ACS Migration Project | 0 |  | 0 |  |  | 14429.4 | 18253 | -3823.6 | 2007-08-12 | 2008-12-31 | 2007-09-01 | 2008-06-27
75080-DE Kentucky Other - Elec | 316ZBG | D1609 | Erlanger Oil separator install | 0 |  | 0 |  |  | 30771.18 | 40000 | -9228.82 | 2007-09-18 | 2008-06-25 | 2007-12-01 | 2008-03-25
75080-DE Kentucky Other - Elec | GASTRAN | D1838 | Implement Gas Transportation | 0 |  | 0 |  |  | 66251.43 | 1 | 66250.43 | 2007-10-14 | 2010-03-31 | 2007-11-01 | 2009-08-11
75080-DE Kentucky Other - Elec | MV90REPL | D2332 | MV90 meter reading replacement | 0 |  | 0 |  |  | 34915.31 | 1 | 34914.31 | 2007-12-12 | 2008-04-30 | 2007-12-01 | 2008-07-31
75080-DE Kentucky Other - Elec | TAGSPRO | D2484 | Implement TAGSPRO software for | 0 |  | 0 |  |  | 59046.2 | 1 | 59045.2 | 2008-01-08 | 2008-12-31 | 2008-03-01 | 2009-03-31
75080-DE Kentucky Other - Elec | RADIO | D2524KY | 2008 IDEN Backhaul | 0 |  | 0 |  |  | 871140.98 | 866250 | 4890.98 | 2010-01-13 | 2012-12-31 | 2010-01-01 | 2010-04-30
75080-DE Kentucky Other - Elec | DATAP | D2539 | Private Data Circuits | 0 |  | 0 |  |  | 116092.55 | 1 | 116091.55 | 2008-01-17 | 2009-01-30 | 2008-02-01 | 2009-04-30
75080-DE Kentucky Other - Elec | OPTIMALC | D3156 | Project Optimization Sftwr-Ky | 0 |  | 0 |  |  | 949.69 | 1 | 948.69 | 2008-03-26 | 2009-12-31 | 2008-05-01 | 2009-01-31
75080-DE Kentucky Other - Elec | FWSREFPH2 | DEPOTRF1 | depot refresh | 0 |  | 0 |  |  | 9131.1 | 9131 | 0.1 | 2015-04-15 08:59 | 2015-04-30 | 2015-04-01 | 2015-08-31
75080-DE Kentucky Other - Elec | FWSREFPH2 | DEPOTRF2 | Depot Refresh 2 | 26226.47 |  | 26226.47 | 100% |  | 26226.47 | 19665.46 | 6561.01 | 2016-06-13 10:43 | 2016-12-31 | 2016-08-01 | 2016-09-30
75080-DE Kentucky Other - Elec | DERSTUDY | DERSLRST | DER Solar Study | 2550 |  | 2550 | 100% |  | 2550 | 0 | 2550 | 2015-12-01 13:28 | 2025-01-01 | 2016-03-01
75080-DE Kentucky Other - Elec | MWTELBLKT | DRYRDGBKT | Dry Ridge Microwave Blanket | 0 |  | 0 |  |  | 23232.1 | 50000 | -26767.9 | 2012-04-09 | 2015-12-31 | 2012-04-01
75080-DE Kentucky Other - Elec | 100FACKY | E0884 | Purchase Recycling Bins KY | 0 |  | 0 |  |  | 6169.61 | 6162 | 7.61 | 2008-09-05 | 2008-12-31 | 2008-12-01 | 2008-12-31
75080-DE Kentucky Other - Elec | KYPYACCR | E1214 | Kentucky Quarterly Payroll Accrual | -103000 |  | -103000 | 100% |  | 102000 | 0 | 102000 | 2008-09-19 | 2050-12-31 | 2008-09-01
75080-DE Kentucky Other - Elec | MWEAMPH1 | E1456 | Kentucky EAM Phase 1 in Svc | 0 |  | 0 |  |  | 387939.96 | 316630.45 | 71309.51 | 2008-10-02 | 2008-09-02 | 2008-09-01 | 2008-09-02
75080-DE Kentucky Other - Elec | MWEAMCAP | E1460 | Kentucky EAM Capex | 0 |  | 0 |  |  | 591257.38 | 1100288.25 | -509030.87 | 2008-10-02 |  | 2008-09-01 | 2010-10-31
75080-DE Kentucky Other - Elec | TDIT | E3875 | Street Index - KY | 0 |  | 0 |  |  | 60473.27 | 82200 | -21726.73 | 2009-01-23 | 2051-03-31 | 2009-02-01 | 2009-08-15
75080-DE Kentucky Other - Elec | FEGISUPGR | EGISUPGRK | EGIS UPGRADE-HW KENTUCKY | 0 |  | 0 |  |  | 52056.02 | 56737 | -4680.98 | 2011-01-10 | 2014-04-30 | 2011-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | FEGISUPGS | EGISUPGSK | EGIS UPGR-SW | 0 |  | 0 |  |  | 58634.24 | 124474 | -65839.76 | 2011-01-24 | 2014-04-30 | 2011-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | CAPBUDK | ETSFHCAPK | CAPITAL BUDGET PROJECT KENT | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-07-01
75080-DE Kentucky Other - Elec | CAPBUDK | ETSPDCAPK | ETS Power Delivery Cap Overhead | 0 |  | 0 |  |  | 2606.47 | 0 | 2606.47 | 2008-07-07 | 2050-12-31 | 2008-07-01
75080-DE Kentucky Other - Elec | MWEAMPH2 | F1844 | Kentucky EAM Phase 2 in Service | 0 |  | 0 |  |  | 974499.36 | 1 | 974498.36 | 2009-11-02 | 2009-10-31 | 2009-10-01 | 2010-01-31
75080-DE Kentucky Other - Elec | CMSICNVK | F3171 | CIS.52 VB6 Conversion Kentucky | 0 |  | 0 |  |  | 334546.69 | 335000 | -453.31 | 2009-12-16 | 2011-10-31 | 2009-12-01 | 2011-11-30
75080-DE Kentucky Other - Elec | FIDENKENT | F9006 | IDEN MIBAS UPGRADE-KENTUCKY | 0 |  | 0 |  |  | 23268.81 | 14334 | 8934.81 | 2010-06-01 | 2010-12-30 | 2010-08-01 | 2011-01-18
75080-DE Kentucky Other - Elec | FITCOMKY | F9105 | IT COMMON - KENTUCKY | 0 |  | 0 |  |  | 5177.15 | 1 | 5176.15 | 2010-06-02 | 2012-12-31 | 2010-06-01
75080-DE Kentucky Other - Elec | MWAVE | FALMTHBKT | Falmouth Blanket | 0 |  | 0 |  |  | 7729.95 | 50000 | -42270.05 | 2012-06-26 | 2017-12-31 | 2012-06-01
75080-DE Kentucky Other - Elec | 100FACKY | FHKYLBPRT | Label Printers - FH Use | 0 |  | 0 |  |  | 9910.13 | 3000 | 6910.13 | 2009-12-02 | 2010-01-31 | 2009-12-01 | 2010-03-31
75080-DE Kentucky Other - Elec | FIBRUPG | FIBRKY09 | 2009 Fiber Upgrades - Kentucky | 0 |  | 0 |  |  | 39713.45 | 60000 | -20286.55 | 2009-03-11 | 2009-12-31 | 2009-05-01 | 2010-03-31
75080-DE Kentucky Other - Elec | TRANSPT | FIBRKY10 | Kentucky SONET additions | 0 |  | 0 |  |  | 56253.92 | 110000 | -53746.08 | 2010-01-22 | 2011-03-31 | 2010-01-01 | 2011-03-31
75080-DE Kentucky Other - Elec | FIDNEL10K | G1371 | MW iDEN RADIO UNITS & PARTS | 0 |  | 0 |  |  | -24893.88 | 73140 | -98033.88 | 2010-10-22 | 2010-12-31 | 2010-12-01 | 2011-03-31
75080-DE Kentucky Other - Elec | FBENTLYED | G1680 | BENTLEY EXPERT DESIGNER UPGR | 0 |  | 0 |  |  | 3969.45 | 8230 | -4260.55 | 2010-12-15 | 2011-06-30 | 2010-12-01 | 2011-08-27
75080-DE Kentucky Other - Elec | FBENTLEYK | G2242 | BENTLEY LDE WKFLOW/ED ENHANCEMENTS | 0 |  | 0 |  |  | 39066.41 | 14052 | 25014.41 | 2011-02-10 | 2011-06-30 | 2011-02-01 | 2012-02-14
75080-DE Kentucky Other - Elec | FEGISUPGR | G3022 | EGIS DEFECT RELEASE | 0 |  | 0 |  |  | 832.91 | 3372.07 | -2539.16 | 2011-04-13 | 2013-09-30 | 2011-04-01 | 2011-12-27
75080-DE Kentucky Other - Elec | FMAPLNKKE | G5253 | MAPLINK ENHANCEMENT-KENTUCKY | 0 |  | 0 |  |  | 64088.97 | 94938 | -30849.03 | 2011-10-06 | 2012-12-18 | 2011-10-01 | 2013-02-17
75080-DE Kentucky Other - Elec | 100FACKY | GD080001 | 19th & Augustine Windows | 0 |  | 0 |  |  | 83669.17 | 79587 | 4082.17 | 2009-05-29 | 2009-09-30 | 2009-05-01 | 2009-03-18
75080-DE Kentucky Other - Elec | MWTELBLKT | GLENCOMW | Glencoe Microwave Blanket | 0 |  | 0 |  |  | 1089.68 | 50000 | -48910.32 | 2012-07-26 | 2017-12-31 | 2013-06-01
75080-DE Kentucky Other - Elec | RADIO | IDEN08KY | iDEN In-building coverage | 0 |  | 0 |  |  | 2535.61 | 50000 | -47464.39 | 2008-09-15 | 2009-03-31 | 2009-02-01 | 2009-06-30
75080-DE Kentucky Other - Elec | RADIO | IDENKY09 | iDEN Radio additions | 0 |  | 0 |  |  | 527338.41 | 844550 | -317211.59 | 2009-04-09 | 2011-01-31 | 2009-05-01 | 2011-01-27
75080-DE Kentucky Other - Elec | RESBLDKY | KMW150211 | Stair Replacement @ Erlanger Ops | -126281.61 |  | -126281.61 | 100% |  | -12699.54 | 121466 | -134165.54 | 2015-06-24 14:04 | 2016-03-14 | 2015-07-01 | 2016-03-14
75080-DE Kentucky Other - Elec | RESBLDKY | KMW160127 | Design of Office Space | 141117.5 |  | 141117.5 | 100% |  | 141117.5 | 485870 | -344752.5 | 2016-07-13 10:28 | 2017-07-02 | 2016-07-01 | 2017-07-07
75080-DE Kentucky Other - Elec | RESBLDKY | KMW160131 | Modular Office Space | 55458.76 |  | 55458.76 | 100% |  | 55458.76 | 219071 | -163612.24 | 2016-07-21 13:54 | 2017-07-02 | 2016-08-01 | 2017-07-03
75080-DE Kentucky Other - Elec | RESBLDKY | KMW224972 | Parking Lot Lighting Replacement | 33000 |  | 33000 | 100% |  | 33000 | 29604 | 3396 | 2016-02-17 10:15 | 2016-08-30 | 2016-04-01 | 2016-07-08
75080-DE Kentucky Other - Elec | 100FACKY | KY090070 | Replace 30 Ton RTU at Augustine | 0 |  | 0 |  |  | 61918.78 | 70161 | -8242.22 | 2009-05-04 | 2009-11-01 | 2009-05-01 | 2009-12-10
75080-DE Kentucky Other - Elec | 100FACKY | KY090078 | Install VAV boxes at Erlanger Ops | 0 |  | 0 |  |  | 17038.06 | 18215 | -1176.94 | 2009-05-26 | 2009-10-01 | 2009-06-01 | 2009-12-15
75080-DE Kentucky Other - Elec | RESBLDKY | KY100094 | ERLANGER INS ALC LIGHTING CONTROLS | 0 |  | 0 |  |  | 5595.72 | 6569 | -973.28 | 2010-12-07 | 2011-03-27 | 2010-12-01 | 2011-03-28
75080-DE Kentucky Other - Elec | SITESVCS | KY100273 | NEW OH/KY TELECOM GROUP | 0 |  | 0 |  |  | 308443.3 | 322675 | -14231.7 | 2010-09-16 | 2011-07-31 | 2010-10-01 | 2011-12-31
75080-DE Kentucky Other - Elec | RESBLDKY | KY100302 | PURCHASE OF AEDS FOR AUGUSTINE | 0 |  | 0 |  |  | 1150.51 | 1255 | -104.49 | 2010-10-18 | 2011-05-08 | 2010-12-01 | 2011-03-07
75080-DE Kentucky Other - Elec | RESBLDKY | KY110306 | Office reconfig @ Erlanger Op Ctr | 0 |  | 0 |  |  | 38073.81 | 39848 | -1774.19 | 2011-09-07 | 2012-05-01 | 2011-09-01 | 2012-06-12
75080-DE Kentucky Other - Elec | 75080 | KY120048 | Inst generator monitors @ KY micros | 0 |  | 0 |  |  | 27321.34 | 14739 | 12582.34 | 2012-06-11 | 2013-01-31 | 2012-06-01 | 2013-02-01
75080-DE Kentucky Other - Elec | 75080 | KY130377 | Install New Driveway @ Erlanger Ops | 0 |  | 0 |  |  | 80324.11 | 93211 | -12886.89 | 2013-10-02 | 2014-03-31 | 2013-10-01 | 2014-02-13
75080-DE Kentucky Other - Elec | 75080 | KY130378 | Rplce Lighting @ Erlanger Warehouse | 0 |  | 0 |  |  | 73078.43 | 90127 | -17048.57 | 2013-10-02 | 2014-03-31 | 2013-10-01 | 2014-02-22
75080-DE Kentucky Other - Elec | RESBLDKY | KYF100333 | AUGUSTINE PAVEMENT REPLACEMENT | 0 |  | 0 |  |  | 5918.47 | 6167 | -248.53 | 2010-12-07 | 2011-12-30 | 2010-12-01 | 2011-03-31
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110233 | Replace Pavng/Retain Wall Augustine | 0 |  | 0 |  |  | 1914828.55 | 1938891 | -24062.45 | 2011-05-11 | 2013-03-01 | 2011-06-01 | 2013-01-25
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110683 | Repl Fire Extinguishers @ KY Facil | 0 |  | 0 |  |  | 3561.95 | 3987 | -425.05 | 2011-10-13 | 2012-03-14 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110713 | Rooftop Fall Protect @ Erlanger | 0 |  | 0 |  |  | 8051.17 | 8889 | -837.83 | 2011-11-15 | 2012-03-31 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | RESBLDKY | KYF110717 | Rooftop Fall Protection @ Augustine | 0 |  | 0 |  |  | 18810.1 | 19613 | -802.9 | 2011-11-15 | 2012-03-31 | 2011-12-01 | 2012-03-15
75080-DE Kentucky Other - Elec | 75080 | KYF120338 | Replace Ice Machines @ Erlanger | 0 |  | 0 |  |  | 13294.66 | 15385 | -2090.34 | 2012-09-06 | 2012-12-30 | 2012-11-01 | 2013-02-12
75080-DE Kentucky Other - Elec | 75080 | KYF120365 | Replace Heaters @ Erlanger Ops | 0 |  | 0 |  |  | 14900 | 16558 | -1658 | 2012-09-25 | 2013-02-28 | 2012-12-01 | 2013-03-12
75080-DE Kentucky Other - Elec | 75080 | KYF140753 | Rplce Conf Rm Furniture @ Erlanger | 0 |  | 0 |  |  | 43997.73 | 33308 | 10689.73 | 2014-10-20 | 2015-03-31 | 2014-12-01 | 2015-03-12
75080-DE Kentucky Other - Elec | 100FACKY | KYFM09001 | Replace fire&Intrustion Monitoring | 0 |  | 0 |  |  | 10391.56 | 10386 | 5.56 | 2009-08-07 | 2009-12-15 | 2009-12-01 | 2010-03-10
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10006 | Replace Concrete Drive Erlanger | 0 |  | 0 |  |  | 97989.98 | 105681 | -7691.02 | 2010-04-20 | 2010-11-30 | 2010-08-01 | 2011-02-12
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10007 | Install new ALC Board at Erlanger | 0 |  | 0 |  |  | 7613.19 | 7657 | -43.81 | 2010-05-18 | 2010-08-30 | 2011-01-01 | 2010-11-19
75080-DE Kentucky Other - Elec | RESBLDKY | KYFM10008 | WATER HEATER REPL @ AUGUSTINE | 0 |  | 0 |  |  | 24647.4 | 27241 | -2593.6 | 2010-08-30 | 2010-12-14 | 2010-12-01 | 2011-01-27
75080-DE Kentucky Other - Elec | MWAVE | KYMWVALRM | Kentucky Microwave Alarm | 0 |  | 0 |  |  | 264495.16 | 248300 | 16195.16 | 2011-02-10 | 2011-02-28 | 2011-02-01 | 2011-06-30
75080-DE Kentucky Other - Elec | RESBLDKY | KYP110242 | Inst Gen Monitor Equip @ KY Micro | 0 |  | 0 |  |  | 26510.69 | 23682 | 2828.69 | 2011-09-08 | 2012-04-30 | 2011-10-01 | 2012-05-01
75080-DE Kentucky Other - Elec | 75080 | KYP120201 | Upgrade Light Fixtures @ Erlanger | -2850 |  | -2850 | 100% |  | 38095.61 | 56806 | -18710.39 | 2012-07-26 | 2014-03-31 | 2012-08-01 | 2013-08-09
75080-DE Kentucky Other - Elec | 75080 | KYP120211 | Crew Rm Reconfig @ Erlanger Ops | 0 |  | 0 |  |  | 281871.68 | 346911 | -65039.32 | 2012-07-17 | 2013-04-30 | 2012-07-01 | 2013-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP130400 | Furniture Purchase I @ Erlanger | 0 |  | 0 |  |  | 20895.34 | 38968 | -18072.66 | 2013-12-06 | 2014-03-31 | 2014-01-01 | 2014-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP130568 | Repl Overhead Doors @ Erlanger Ops | 0 |  | 0 |  |  | 73467.32 | 79238 | -5770.68 | 2014-01-13 | 2014-05-29 | 2014-01-01 | 2014-05-31
75080-DE Kentucky Other - Elec | 75080 | KYP140021 | Install Ventilation Syst @ 19 & Aug | 0 |  | 0 |  |  | 337992.03 | 323771 | 14221.03 | 2014-02-05 | 2015-03-31 | 2014-04-01 | 2014-11-01
75080-DE Kentucky Other - Elec | 75080 | KYP140165 | Inst Fire Alarm Syst @ Erlanger Ops | 0 |  | 0 |  |  | 73366.57 | 87618 | -14251.43 | 2014-04-06 | 2014-09-13 | 2014-04-01 | 2014-09-13
75080-DE Kentucky Other - Elec | 75080 | KYP140215 | Inst Fall Protection @ Erlanger Ops | 0 |  | 0 |  |  | 26799.89 | 29710 | -2910.11 | 2014-06-15 | 2014-09-30 | 2014-06-01 | 2014-09-30
75080-DE Kentucky Other - Elec | 75080 | KYP140332 | Security Upgrades @ Augustine Off | 0 |  | 0 |  |  | 141137.47 | 152592 | -11454.53 | 2014-06-26 | 2015-03-01 | 2014-07-01 | 2015-03-31
75080-DE Kentucky Other - Elec | 75080 | KYP140674 | Inst Veh Charging Equip @ Erlanger | 0 |  | 0 |  |  | 10220 | 16165 | -5945 | 2014-11-21 | 2015-05-06 | 2015-01-01 | 2015-03-26
75080-DE Kentucky Other - Elec | 75080 | KYP140750 | Install Fuel KeyCard @ Erlanger Ops | 0 |  | 0 |  |  | 37021.21 | 48746 | -11724.79 | 2014-11-04 | 2015-08-29 | 2014-11-01 | 2015-08-28
75080-DE Kentucky Other - Elec | RADIO | MODKY09 | Replace vehicular radio modems | 0 |  | 0 |  |  | 145687.05 | 175000 | -29312.95 | 2009-04-13 | 2009-12-31 | 2009-04-01 | 2010-03-01
75080-DE Kentucky Other - Elec | FMWAVEKY | MW732REP | MW Comm Shelter Repl KY-NINT732 | -15109.91 |  | -15109.91 | 100% |  | 393300.68 | 430000 | -36699.32 | 2014-03-05 | 2014-12-31 | 2014-03-01 | 2015-04-30
75080-DE Kentucky Other - Elec | MWAVE | MWAVEKY10 | Upgrade MidW Microwave infra | 0 |  | 0 |  |  | 442410.49 | 341232 | 101178.49 | 2010-03-11 | 2011-08-31 | 2010-03-01 | 2011-11-30
75080-DE Kentucky Other - Elec | MWAVE | MWBUGENKY | Microwave Backup Generator Kentucky | 0 |  | 0 |  |  | 249540.28 | 242795.05 | 6745.23 | 2011-03-17 | 2012-04-30 | 2011-03-01 | 2012-08-15
75080-DE Kentucky Other - Elec | FMWAVEKY | MWEOLVERN | MW EOL Verona | -5.06 |  | -5.06 | 100% |  | 911.38 | 10000 | -9088.62 | 2014-05-29 | 2014-12-31 | 2014-08-01 | 2015-03-31
75080-DE Kentucky Other - Elec | FMWAVEKY | MWMWUPG | Verona Microwave Upgrades | -2132.83 |  | -2132.83 | 100% |  | 62030.92 | 60346 | 1684.92 | 2014-01-06 | 2014-12-31 | 2014-02-01 | 2014-09-17
75080-DE Kentucky Other - Elec | MWAVE | N1226SPAR | N1226 Sparta EOL | 26.7 |  | 26.7 | 100% |  | 1743.5 | 3015 | -1271.5 | 2015-05-27 15:35 | 2015-12-31 | 2015-07-01 | 2016-03-15
75080-DE Kentucky Other - Elec | FMWAVEKY | N1226TAMI | N1226 Taylor Mill Equip EOL | -15.24 |  | -15.24 | 100% |  | 3549.85 | 3015 | 534.85 | 2015-06-11 17:36 | 2015-12-31 | 2015-08-01 | 2015-09-23
75080-DE Kentucky Other - Elec | MWAVE | N1226UNIO | N1226 Midwest Pwr Equip Union | 0 |  | 0 |  |  | 1274.34 | 2640 | -1365.66 | 2014-07-14 | 2015-12-31 | 2014-09-01 | 2016-04-28
75080-DE Kentucky Other - Elec | MWAVE | N1226VERO | N1226 MWESTPWREQUIP EOL VERONA 2 | -8.68 |  | -8.68 | 100% |  | 1243.84 | 7640 | -6396.16 | 2014-06-23 | 2015-12-31 | 2014-07-01 | 2016-01-01
75080-DE Kentucky Other - Elec | MWAVE | N1226WNKR | N1226 Midwest Pwr Equip EOL WKNR | 6047.4 |  | 6047.4 | 100% |  | 46101.7 | 2640 | 43461.7 | 2014-07-14 | 2015-12-31 | 2014-09-01 | 2015-09-23
75080-DE Kentucky Other - Elec | FMWAVEKY | N1259WNKR | N1259WNKR Tower | -208.34 |  | -208.34 | 100% |  | 29720.5 | 18889 | 10831.5 | 2015-04-28 14:11 | 2015-12-31 | 2015-05-01 | 2015-10-10
75080-DE Kentucky Other - Elec | 100FACKY | NEWPORTRT | Ret Newport Plaza Cus Svc Bldg | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-04-08 | 2009-12-31 | 2011-08-01 | 2011-11-16
75080-DE Kentucky Other - Elec | MWAVE | NINT1309 | Dry Ridge KY Coms Tower Acquis | 14210.83 |  | 14210.83 | 100% |  | 161676.64 | 125000 | 36676.64 | 2014-08-27 | 2014-12-31 | 2014-09-01 | 2016-10-14
75080-DE Kentucky Other - Elec | NETWORK1 | NINT621 | Ops Center Technology Refresh | 0 |  | 0 |  |  | 40565.7 | 38205 | 2360.7 | 2012-11-27 | 2013-03-31 | 2012-12-01 | 2014-09-30
75080-DE Kentucky Other - Elec | FWSREFPH2 | P6367 | Workstation refresh project | 0 |  | 0 |  |  | 714626.09 | 737000 | -22373.91 | 2014-09-23 | 2014-09-22 | 2014-09-01 | 2014-01-31
75080-DE Kentucky Other - Elec | RADIO | PAGTRNKY | Pagin Transmitter replacement | 0 |  | 0 |  |  | 191767.68 | 190327.92 | 1439.76 | 2010-11-01 | 2012-12-31 | 2010-12-01 | 2012-06-30
75080-DE Kentucky Other - Elec | FEGISUPGS | PCTAIT214 | EGIS UPGR-SW | 0 |  | 0 |  |  | 161902.27 | 160816 | 1086.27 | 2013-10-25 | 2014-04-30 | 2013-11-01 | 2014-03-31
75080-DE Kentucky Other - Elec | FPIT | R5327 | Plantview Observation Program Mobil | 8946.64 |  | 8946.64 | 100% |  | 8946.64 | 5051.44 | 3895.2 | 2015-12-17 08:56 | 2017-02-18 | 2016-02-01 | 2017-02-18
75080-DE Kentucky Other - Elec | FPIT | R5526 | Kanawha Scales Integration | 1972.4 |  | 1972.4 | 100% |  | 1972.4 | 3645.22 | -1672.82 | 2016-01-06 07:53 | 2016-05-31 | 2016-01-01 | 2016-08-31
75080-DE Kentucky Other - Elec | FPIT | R6095 | Logistics Cycle Times | 15542.37 |  | 15542.37 | 100% |  | 15542.37 | 36719.92 | -21177.55 | 2016-01-21 13:27 | 2017-12-15 | 2016-02-01
75080-DE Kentucky Other - Elec | FPIT | R6164 | Logistics Cycle Times | 30.11 |  | 30.11 | 100% |  | 30.11 | 763 | -732.89 | 2016-01-25 15:04 | 2017-05-12 | 2016-07-01
75080-DE Kentucky Other - Elec | FPIT | R9205 | Trading Information Management Cons | 215.3 |  | 215.3 | 100% |  | 215.3 | 56252.04 | -56036.74 | 2016-03-28 15:16 | 2017-06-30 | 2016-05-01
75080-DE Kentucky Other - Elec | MWAVE | REPPWREQP | Midwest 2011 Power Equipment Replac | 0 |  | 0 |  |  | 14756 | 13000 | 1756 | 2011-05-18 | 2012-04-01 | 2012-07-01 | 2012-10-01
75080-DE Kentucky Other - Elec | 75080 | RETCOV | Retire Covington | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-12-20 | 2013-03-31 | 2012-12-01 | 2013-03-31
75080-DE Kentucky Other - Elec | 75080 | RETCOV2 | Retire Covington - Elec | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-12-20 | 2013-03-31 | 2012-12-01 | 2013-04-05
75080-DE Kentucky Other - Elec | MWTELBLKT | ROSHUGBKT | Ross Hughes MW Blanket | 0 |  | 0 |  |  | 2964 | 50000 | -47036 | 2012-07-20 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | RYLANDBKT | Ryland Heights MW Blanket | 0 |  | 0 |  |  | 2164.69 | 50000 | -47835.31 | 2012-09-11 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | FPIT | S6621 | Plantview Reliability Index Module | 2111.95 |  | 2111.95 | 100% |  | 2111.95 | 7144.63 | -5032.68 | 2016-05-17 13:49 | 2017-07-31 | 2016-05-01
75080-DE Kentucky Other - Elec | SCADA | SCADKY09 | 2009 SCADA projects Kentucky | 0 |  | 0 |  |  | 65109.41 | 25000 | 40109.41 | 2009-02-03 | 2009-12-31 | 2009-04-01 | 2010-03-31
75080-DE Kentucky Other - Elec | 75080 | SFTWRE | Software Retirement-Asset Use Only | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-09-20 | 2026-03-30 | 2012-09-01
75080-DE Kentucky Other - Elec | MWTELBLKT | SPARTABKT | Sparta Tower Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-02-08 | 2015-12-31 | 2012-02-01
75080-DE Kentucky Other - Elec | MWAVE | TAYLORBAT | Taylor Mill Battery replacement | 0 |  | 0 |  |  | 3820.95 | 3800 | 20.95 | 2012-08-23 | 2012-12-31 | 2013-01-01 | 2014-11-30
75080-DE Kentucky Other - Elec | MWAVE | TAYLRMBLK | Taylor Mill, KY, Microwave Blanket | 0 |  | 0 |  |  | -5005.32 | 50000 | -55005.32 | 2014-03-03 | 2025-12-31 | 2014-03-01
75080-DE Kentucky Other - Elec | MWTELBLKT | VERONAMW | Verona Microwave Blanket | 4273.68 |  | 4273.68 | 100% |  | 8177.05 | 50000 | -41822.95 | 2012-07-26 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | NETWORK1 | WANUPGRII | WAN EOL Upgrd Phase II | 0 |  | 0 |  |  | 23902.1 | 23907 | -4.9 | 2013-09-17 | 2014-06-30 | 2013-10-01 | 2014-09-30
75080-DE Kentucky Other - Elec | MWAVE | WILDERBAT | Wilder MW Battery Replacement | 0 |  | 0 |  |  | 2551.68 | 2500 | 51.68 | 2013-09-17 | 2013-12-31 | 2014-02-01 | 2014-11-30
75080-DE Kentucky Other - Elec | MWTELBLKT | WILDERBKT | Wilder Microwave Blanket | 0 |  | 0 |  |  | 0 | 50000 | -50000 | 2012-07-20 | 2017-12-31 | 2012-07-01
75080-DE Kentucky Other - Elec | MWTELBLKT | WNKRBLKT | WNKR Tower Blanket | 1483.22 |  | 1483.22 | 100% |  | 1483.22 | 50000 | -48516.78 | 2012-09-05 | 2025-12-31 | 2012-09-01
75080-DE Kentucky Other - Elec | AMIKYCS | ZY072 | AMI Gas & Electric Meters KY | 601512.93 |  | 601512.93 | 100% |  | 601512.93 | 1 | 601511.93 | 2016-04-28 10:25 | 2050-12-31 | 2016-04-01 | 2016-07-31
75081-DE Kentucky Fossil | PCTAIT137 | AIT13707H | Gas ETRM | 0 |  | 0 |  |  | 14.84 | 0 | 14.84 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTAIT137 | AIT13707S | Gas ETRM | 0 |  | 0 |  |  | 990.06 | 0 | 990.06 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTANT137 | AIT13708H | Gas ETRM | 0 |  | 0 |  |  | 268.31 | 0 | 268.31 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTANT137 | AIT13708S | Gas ETRM | 0 |  | 0 |  |  | 48601.71 | 0 | 48601.71 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75081-DE Kentucky Fossil | PCTAIT218 | AIT21808H | FSO Forecasting Consolidation | 0.26 |  | 0.26 | 100% |  | -13.04 | 0 | -13.04 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT218 | AIT21808S | FSO Forecasting Consolidation | 10.05 |  | 10.05 | 100% |  | -562.13 | 0 | -562.13 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT21C | AIT21809H | FSO Forecasting Consolidation | -5.95 |  | -5.95 | 100% |  | 508.4 | 0 | 508.4 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | PCTAIT21C | AIT21809S | FSO Forecasting Consolidation | -256.12 |  | -256.12 | 100% |  | 25358.79 | 0 | 25358.79 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081-DE Kentucky Fossil | ACLEB01 | AROCLEB01 | ABSAT East Bend Closure Project | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-04-22 11:22 | 2025-03-30 | 2016-07-01
75081-DE Kentucky Fossil | EB201316 | C9122 | EBS-Precipitator Key System | 0 |  | 0 |  |  | 163463.06 | 0 | 163463.06 | 2007-01-17 | 2008-02-13 | 2007-02-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01234 | C9145 | Circ Water Piping Anode Repl | 0 |  | 0 |  |  | 236141.69 | 0 | 236141.69 | 2007-01-24 | 2008-01-31 | 2007-01-01 | 2007-11-30
75081-DE Kentucky Fossil | EB1472 | C9152 | Cooling Tower Fan Blades-2007 | 0 |  | 0 |  |  | 69324.01 | 0 | 69324.01 | 2007-01-24 | 2007-12-31 | 2007-02-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01214 | C9221 | EBS-Module Inlt Turning Vanes | 0 |  | 0 |  |  | 151474.23 | 0 | 151474.23 | 2007-02-01 | 2008-06-05 | 2007-04-01 | 2007-10-31
75081-DE Kentucky Fossil | EB201351 | C9222 | EBS-Repl B Module Demistr Trys | 0 |  | 0 |  |  | 228799.58 | 0 | 228799.58 | 2007-02-01 | 2008-04-30 | 2007-03-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01229 | C9223 | EBS-Repl Module Inlt Exp Jnts | 0 |  | 0 |  |  | 209019.92 | 0 | 209019.92 | 2007-02-01 | 2008-04-30 | 2007-03-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01217 | C9224 | Inlt Vanes on Sec Air Windbox | 0 |  | 0 |  |  | 31346.36 | 0 | 31346.36 | 2007-02-01 | 2008-05-01 | 2007-02-01 | 2007-08-31
75081-DE Kentucky Fossil | EB201356 | C9318 | EBS-Repl Demin Sump Piping | 0 |  | 0 |  |  | 90123.7 | 0 | 90123.7 | 2007-02-22 | 2008-09-28 | 2007-02-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01253 | C9847 | New Generator Flux Shield | 0 |  | 0 |  |  | 47007.22 | 0 | 47007.22 | 2007-05-18 | 2007-08-31 | 2007-08-01 | 2007-11-30
75081-DE Kentucky Fossil | CEBGYP | CCEBGYP | East Bend Radial Stacker Paving | 63859.12 |  | 63859.12 | 100% |  | 63859.12 | 63830 | 29.12 | 2016-10-06 12:15 | 2016-11-05 | 2016-10-01 | 2017-01-06
75081-DE Kentucky Fossil | CEBLIDR | CCEBLIDR | CCP East Bend Landfill Ind Door Rep | 13583.54 |  | 13583.54 | 100% |  | 13583.54 | 12150.69 | 1432.85 | 2016-08-31 09:58 | 2017-01-15 | 2016-11-01 | 2017-03-06
75081-DE Kentucky Fossil | EB020290 | CEB020290 | Lined Retention Basin | 1025695.64 |  | 1025695.64 | 100% |  | 1025695.64 | 0 | 1025695.64 | 2016-07-11 18:39 | 2018-07-18 | 2016-08-01
75081-DE Kentucky Fossil | EB020298 | CEB020298 | East Bend SW / PW REROUTE | 970733.33 |  | 970733.33 | 100% |  | 970733.33 | 0 | 970733.33 | 2016-07-01 15:23 | 2018-07-30 | 2016-08-01
75081-DE Kentucky Fossil | EB021410 | CEB021410 | Dry Bottom Ash Conversion | 1469751.17 |  | 1469751.17 | 100% |  | 1623169.66 | 0 | 1623169.66 | 2015-10-15 14:37 | 2018-07-30 | 2015-12-01
75081-DE Kentucky Fossil | CCPCAP | CEB021493 | East Bend ByProducts Scale Mgmt Upg | 8733.88 |  | 8733.88 | 100% |  | 133993.68 | 0 | 133993.68 | 2015-01-23 | 2017-04-30 | 2015-09-01
75081-DE Kentucky Fossil | EB201219 | CEB201219 | EBS-Repl Cooling Towr Motr 07 | 0 |  | 0 |  |  | 69781.27 | 0 | 69781.27 | 2007-02-22 | 2008-06-30 | 2007-03-01 | 2008-05-31
75081-DE Kentucky Fossil | EB201253 | CEB201253 | 2-2 Repl Ash Sluice Pump Motor | 0 |  | 0 |  |  | 40822.56 | 0 | 40822.56 | 2008-02-21 | 2009-05-31 | 2008-04-01 | 2009-03-31
75081-DE Kentucky Fossil | EB201353 | CEB201353 | EBS-Repl Thicknr Rake Arms | 0 |  | 0 |  |  | 392542.71 | 0 | 392542.71 | 2007-04-12 | 2008-06-30 | 2007-04-01 | 2008-12-30
75081-DE Kentucky Fossil | EB201362 | CEB201362 | Cooling Tower Gearbox 2008 | 0 |  | 0 |  |  | 218058.69 | 0 | 218058.69 | 2008-01-24 | 2009-02-28 | 2008-02-01 | 2009-03-15
75081-DE Kentucky Fossil | CCPCAP | CEBLD1201 | CCP East Bend-14 Primary Spillway R | 588941.47 |  | 588941.47 | 100% |  | 10286261.23 | 9471135 | 815126.23 | 2015-02-25 16:25 | 2015-05-30 | 2015-03-01 | 2016-05-12
75081-DE Kentucky Fossil | EBS01209 | CEBS01209 | SAH Sootblower Addition | 0 |  | 0 |  |  | 960496.14 | 0 | 960496.14 | 2008-04-08 | 2009-09-30 | 2008-06-01 | 2009-09-29
75081-DE Kentucky Fossil | EBS01218 | CEBS01218 | EBS-Repl Turbine Room Roof | 0 |  | 0 |  |  | 127834.06 | 0 | 127834.06 | 2007-09-02 | 2008-04-10 | 2007-09-01 | 2008-01-13
75081-DE Kentucky Fossil | EBS01235 | CEBS01235 | EBS- Repl Security System | 0 |  | 0 |  |  | 321830.62 | 0 | 321830.62 | 2007-04-17 | 2009-10-15 | 2007-11-01 | 2009-04-30
75081-DE Kentucky Fossil | EBS01238 | CEBS01238 | EBS-Mercury Monitoring System | 0 |  | 0 |  |  | 1221862.51 | 0 | 1221862.51 | 2007-04-17 | 2011-07-31 | 2007-05-01 | 2011-10-25
75081-DE Kentucky Fossil | EBS01239 | CEBS01239 | 2007 Landfill Leachate Sys | 0 |  | 0 |  |  | 53575.18 | 0 | 53575.18 | 2007-10-16 | 2008-02-29 | 2007-12-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01251 | CEBS01251 | EBS-Rmove 2-2 PA Fan Silencer | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-04-17 | 2007-10-31 | 2009-05-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01252 | CEBS01252 | EBS-Repl Air Compressor Contrl | 0 |  | 0 |  |  | 55964.27 | 0 | 55964.27 | 2007-04-29 | 2008-04-01 | 2007-05-01 | 2007-12-31
75081-DE Kentucky Fossil | EBS01263 | CEBS01263 | Repl Turbine Blade Row | 0 |  | 0 |  |  | 3386310.93 | 0 | 3386310.93 | 2008-01-24 | 2009-11-30 | 2008-02-01 | 2009-08-25
75081-DE Kentucky Fossil | EBS01272 | CEBS01272 | Rewind 2-2 & 2-3 ID Fan Motr | 0 |  | 0 |  |  | 778291.95 | 0 | 778291.95 | 2007-11-06 | 2008-12-31 | 2007-12-01 | 2008-09-30
75081-DE Kentucky Fossil | EBS01274 | CEBS01274 | EBS-ED Fan Motor | 0 |  | 0 |  |  | 391358.53 | 0 | 391358.53 | 2007-09-02 | 2008-03-31 | 2007-09-01 | 2008-03-31
75081-DE Kentucky Fossil | EBS01281 | CEBS01281 | EBS-Landfill Excavator | 0 |  | 0 |  |  | 140911.52 | 0 | 140911.52 | 2007-09-02 | 2007-12-10 | 2007-10-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01305 | CEBS01305 | EBS-Ash Pnd Ground Wtr Monitor | 0 |  | 0 |  |  | 49419.39 | 0 | 49419.39 | 2007-09-25 | 2008-12-31 | 2007-09-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01309 | CEBS01309 | EBS-WSP Lime Feeder Platform | 0 |  | 0 |  |  | 16993.48 | 0 | 16993.48 | 2007-12-05 | 2008-02-29 | 2007-12-01 | 2008-01-31
75081-DE Kentucky Fossil | EBS01311 | CEBS01311 | Repl Service Wtr Strainer | 0 |  | 0 |  |  | 74479.66 | 0 | 74479.66 | 2008-03-06 | 2009-05-31 | 2008-03-01 | 2008-12-31
75081-DE Kentucky Fossil | EBS01314 | CEBS01314 | Repl SCR Ammonia Detectors | 0 |  | 0 |  |  | 50460.98 | 0 | 50460.98 | 2008-04-09 | 2008-12-31 | 2008-04-01 | 2009-03-22
75081-DE Kentucky Fossil | CGYEB115 | CGYPEB115 | CCP EB-115 T6 E. BEND GYPSUM MITIGA | 49262.78 |  | 49262.78 | 100% |  | 853723.29 | 1500000 | -646276.71 | 2015-06-04 17:33 | 2015-12-31 | 2015-08-01 | 2015-12-31
75081-DE Kentucky Fossil | MF5506 | CMF5506 | PLC in Chem Sample Rm | 0 |  | 0 |  |  | 39451.61 | 0 | 39451.61 | 2008-02-28 | 2009-03-31 | 2008-06-01 | 2008-12-31
75081-DE Kentucky Fossil | MF601219 | CMF601219 | LP/HP Htr Level Controls | 0 |  | 0 |  |  | 182812.04 | 0 | 182812.04 | 2008-02-28 | 2009-06-30 | 2008-05-01 | 2009-06-22
75081-DE Kentucky Fossil | MU060004 | CMU060004 | Miami Fort 6 Decommissioning | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-07-13 17:08 | 2021-12-31 | 2016-12-01
75081-DE Kentucky Fossil | MU601213 | CMU601213 | Repl FD Fan Drives | 0 |  | 0 |  |  | 107962.71 | 0 | 107962.71 | 2008-02-28 | 2009-04-08 | 2008-04-01 | 2009-02-01
75081-DE Kentucky Fossil | MU601216 | CMU601216 | MFS-6 Misc Valves | 0 |  | 0 |  |  | 291236.94 | 0 | 291236.94 | 2008-02-05 | 2019-03-31 | 2008-03-01 | 2015-06-30
75081-DE Kentucky Fossil | MU601217 | CMU601217 | MFS-6 General Equipment | 0 |  | 0 |  |  | 76017.65 | 0 | 76017.65 | 2008-02-05 | 2010-03-31 | 2008-02-01
75081-DE Kentucky Fossil | MU601224 | CMU601224 | MFS-6 Repl Condenser Bellows | 0 |  | 0 |  |  | 9887.7 | 0 | 9887.7 | 2007-07-23 | 2008-01-30 | 2007-09-01 | 2007-10-07
75081-DE Kentucky Fossil | MU601225 | CMU601225 | MFS-6 Repl Battery Chrgers 1&2 | 0 |  | 0 |  |  | 37574.91 | 0 | 37574.91 | 2007-11-08 | 2008-09-30 | 2008-03-01 | 2008-10-31
75081-DE Kentucky Fossil | MU601228 | CMU601228 | MFS-6 Repl Precipitator T/R | 0 |  | 0 |  |  | 93667.23 | 0 | 93667.23 | 2007-09-02 | 2008-07-31 | 2007-08-01 | 2008-06-30
75081-DE Kentucky Fossil | MU601231 | CMU601231 | MFS-6 Instl Coal Conveyor & Dr | 0 |  | 0 |  |  | 3770058.8 | 0 | 3770058.8 | 2007-11-28 | 2009-11-01 | 2007-12-01 | 2009-12-22
75081-DE Kentucky Fossil | MU601232 | CMU601232 | Repl Genratr Collctr Rings | 0 |  | 0 |  |  | 223008.94 | 0 | 223008.94 | 2008-04-09 | 2009-12-30 | 2008-05-01 | 2008-09-30
75081-DE Kentucky Fossil | OPTIM | COPTIM | Develop OPTIM Modeling Tool | 68331.5 |  | 68331.5 | 100% |  | 68331.5 | 0 | 68331.5 | 2016-01-15 13:13 | 2017-09-30 | 2016-01-01 | 2017-09-16
75081-DE Kentucky Fossil | PEM1202 | CPEM1202 | 070-PEM General Equipment | 0 |  | 0 |  |  | 33729.76 | 0 | 33729.76 | 2007-05-15 | 2014-12-31 | 2007-05-01 | 2014-01-31
75081-DE Kentucky Fossil | EBS01278 | D1138 | EBS-ID Fan Motor 2-1 Rewind | 0 |  | 0 |  |  | 226305.84 | 0 | 226305.84 | 2007-07-04 | 2008-03-31 | 2007-07-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01259 | D1148 | EBS-2-1 SAH Thrust Bearing | 0 |  | 0 |  |  | 75418.06 | 0 | 75418.06 | 2007-07-08 | 2007-12-30 | 2007-07-01 | 2007-08-31
75081-DE Kentucky Fossil | EBS01287 | D1437 | EBS-2-1 Silo Flyash Blowr Motr | 0 |  | 0 |  |  | 40265.22 | 0 | 40265.22 | 2007-09-02 | 2008-10-31 | 2007-09-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01307 | D1826 | EBS-Repl 2-4 Vacuum Pump Motor | 0 |  | 0 |  |  | 8819.9 | 0 | 8819.9 | 2007-10-12 | 2008-12-31 | 2007-10-01 | 2007-11-30
75081-DE Kentucky Fossil | EBS01248 | D3122 | Ky Sales & Use Tax Vintage 07 | 0 |  | 0 |  |  | 24324.22 | 0 | 24324.22 | 2008-03-21 | 2008-03-31 | 2008-03-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01248 | D3124 | Ky Sales & Use Tax Vintage 05 | 0 |  | 0 |  |  | 342714.76 | 0 | 342714.76 | 2008-03-21 | 2008-03-31 | 2008-03-01 | 2008-06-30
75081-DE Kentucky Fossil | EBS01267 | D3553 | Sludge Transfr Pmp Replacemnt | 0 |  | 0 |  |  | 136278.1 | 0 | 136278.1 | 2008-05-21 | 2009-08-24 | 2008-09-01 | 2009-02-14
75081-DE Kentucky Fossil | EB1482 | D3558 | Coolng Towr Fan Blades 2008 | 0 |  | 0 |  |  | 81896.2 | 0 | 81896.2 | 2008-05-21 | 2009-03-31 | 2008-08-01 | 2009-02-12
75081-DE Kentucky Fossil | EBS01206 | D3666 | Replace SAH Preheat Coils | 0 |  | 0 |  |  | 1982885.62 | 0 | 1982885.62 | 2008-06-12 | 2010-08-15 | 2008-11-01 | 2010-08-18
75081-DE Kentucky Fossil | EB020027 | EB020027X | #1 Lime Conveyor Belt Replacement | 151210.67 |  | 151210.67 | 100% |  | 297113.05 | 205213.25 | 91899.8 | 2015-10-19 12:59 | 2016-10-01 | 2015-11-01 | 2016-08-06
75081-DE Kentucky Fossil | EB020033 | EB020033X | Install Tube Bundle on 2-1A,B FWH | 704133.32 |  | 704133.32 | 100% |  | 1099977.74 | 990557.99 | 109419.75 | 2015-09-09 11:17 | 2016-08-01 | 2015-09-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020037 | EB020037X | Replace SAH Preheat Coils | 334495.49 |  | 334495.49 | 100% |  | 347086.63 | 323572 | 23514.63 | 2015-10-06 13:29 | 2016-12-31 | 2015-10-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020039 | EB020039X | New Relay & Maintenance Switches | 1156354.46 |  | 1156354.46 | 100% |  | 1186438.15 | 937934.72 | 248503.43 | 2015-12-18 08:03 | 2016-08-31 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020056 | EB020056X | Sec Superheat Outlet Header Rep | 237128.65 |  | 237128.65 | 100% |  | 237128.65 | 0 | 237128.65 | 2016-10-20 15:11 | 2018-12-01 | 2016-10-01
75081-DE Kentucky Fossil | EB020057 | EB020057X | SAH Seal Replacement | 1042087.66 |  | 1042087.66 | 100% |  | 1042087.66 | 965143.84 | 76943.82 | 2016-01-08 08:51 | 2016-06-01 | 2016-02-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020058 | EB020058X | CT Drift Elim Rplcmnt | 821495.48 |  | 821495.48 | 100% |  | 1056869.82 | 1263106.51 | -206236.69 | 2015-10-06 11:00 | 2016-06-01 | 2015-10-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020074 | EB020074X | Replace Stack Elevator | 141241.82 |  | 141241.82 | 100% |  | 141241.82 | 181669.72 | -40427.9 | 2016-12-09 09:30 | 2017-03-30 | 2016-12-01 | 2017-05-16
75081-DE Kentucky Fossil | EB020078 | EB020078X | Replace Data Network Equipment | 187010.87 |  | 187010.87 | 100% |  | 187010.87 | 197450.98 | -10440.11 | 2016-05-02 10:48 | 2016-12-15 | 2016-05-01 | 2016-11-27
75081-DE Kentucky Fossil | EB020083 | EB020083X | Replace NOx Monitors | 370483.36 |  | 370483.36 | 100% |  | 418164.76 | 366249.89 | 51914.87 | 2015-12-01 10:45 | 2016-05-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB020090 | EB020090X | Boiler Room Vent Fan on Mezzanine | 651253.39 |  | 651253.39 | 100% |  | 651253.39 | 496509.5 | 154743.89 | 2016-05-16 11:32 | 2016-12-31 | 2016-05-01 | 2017-02-28
75081-DE Kentucky Fossil | EB020100 | EB020100X | Demin Mixed Bed Vessel Replacement | 2948.11 |  | 2948.11 | 100% |  | 143669.3 | 138000.07 | 5669.23 | 2015-06-22 15:41 | 2015-11-01 | 2015-08-01 | 2016-01-05
75081-DE Kentucky Fossil | EB020135 | EB020135X | Install Emergency Warning System | 832510.25 |  | 832510.25 | 100% |  | 832510.25 | 895918.08 | -63407.83 | 2016-09-02 09:29 | 2017-04-30 | 2016-09-01 | 2017-05-23
75081-DE Kentucky Fossil | EB020224 | EB020224X | Replace Atomic Absorption Unit | 5744.89 |  | 5744.89 | 100% |  | 104688.05 | 95375 | 9313.05 | 2015-10-06 12:49 | 2015-12-07 | 2015-12-01 | 2016-04-08
75081-DE Kentucky Fossil | EB020250 | EB020250X | Precip Retention Wall | 54527.49 |  | 54527.49 | 100% |  | 116613.88 | 72234.75 | 44379.13 | 2015-11-17 10:58 | 2016-06-01 | 2015-12-01 | 2016-05-01
75081-DE Kentucky Fossil | EB020251 | EB020251X | Replace 2-1 Pugmill Gearbox | 0 |  | 0 |  |  | 16472.99 | 52573.25 | -36100.26 | 2015-11-17 10:29 | 2015-11-30 | 2015-12-01 | 2016-02-29
75081-DE Kentucky Fossil | EB020254 | EB020254X | Event Free: Nuva Feeder Bldg Lights | 4693.33 |  | 4693.33 | 100% |  | 56074.21 | 66165.53 | -10091.32 | 2015-12-15 14:34 | 2015-12-31 | 2015-12-01 | 2016-03-23
75081-DE Kentucky Fossil | EB020257 | EB020257X | Event Free: MSP Oil Room Lighting | 5428 |  | 5428 | 100% |  | 10232.36 | 27798.45 | -17566.09 | 2015-12-01 11:07 | 2015-12-31 | 2015-12-01 | 2016-03-23
75081-DE Kentucky Fossil | EB020261 | EB020261X | Replace North TUF Pump | -513.98 |  | -513.98 | 100% |  | 62433.47 | 50123.72 | 12309.75 | 2015-12-28 12:34 | 2015-04-01 | 2015-12-01 | 2015-07-01
75081-DE Kentucky Fossil | EB020263 | EB020263X | Material Handling Shelters-Event Fr | 49338.65 |  | 49338.65 | 100% |  | 112943.28 | 147117.24 | -34173.96 | 2015-12-14 08:52 | 2015-12-31 | 2015-12-01 | 2016-03-23
75081-DE Kentucky Fossil | EB020267 | EB020267X | 2-2 Condenser Vacuum Pump | 0 |  | 0 |  |  | 41302.83 | 58039.66 | -16736.83 | 2015-12-28 12:14 | 2015-12-31 | 2015-12-01 | 2016-03-10
75081-DE Kentucky Fossil | EB020277 | EB020277X | WSP Vac Pump 2-1 Replace | 54284.34 |  | 54284.34 | 100% |  | 54284.34 | 64614.24 | -10329.9 | 2016-06-30 10:23 | 2016-06-01 | 2016-06-01 | 2016-09-30
75081-DE Kentucky Fossil | EB020293 | EB020293X | Replace G Conveyor Belt | 98672.1 |  | 98672.1 | 100% |  | 98672.1 | 98397.97 | 274.13 | 2016-06-30 09:53 | 2016-06-01 | 2016-06-01 | 2016-09-30
75081-DE Kentucky Fossil | EB020358 | EB020358X | Used Oil Storage Building (EF) | 201281.95 |  | 201281.95 | 100% |  | 201281.95 | 152235.01 | 49046.94 | 2016-07-25 14:55 | 2016-12-31 | 2016-08-01 | 2017-03-20
75081-DE Kentucky Fossil | EB020400 | EB020400X | Replace 2-2 IDBF Coupling | 23922.8 |  | 23922.8 | 100% |  | 23922.8 | 20338.73 | 3584.07 | 2016-05-02 11:32 | 2016-05-31 | 2016-05-01 | 2016-08-20
75081-DE Kentucky Fossil | EB020405 | EB020405X | Replace 2-2 FD Fan Coupling | 21594.23 |  | 21594.23 | 100% |  | 21594.23 | 12499.56 | 9094.67 | 2016-05-02 11:39 | 2016-05-31 | 2016-05-01 | 2016-08-20
75081-DE Kentucky Fossil | EB020417 | EB020417X | 2-1 Mixer Feeder Belt Replacement | 9678.21 |  | 9678.21 | 100% |  | 9678.21 | 14775.17 | -5096.96 | 2016-06-01 09:29 | 2016-08-27 | 2016-05-01 | 2016-09-01
75081-DE Kentucky Fossil | EB020419 | EB020419X | Repl Precip Transformer/Rectifier | 23987.12 |  | 23987.12 | 100% |  | 23987.12 | 29881.49 | -5894.37 | 2016-05-16 12:46 | 2016-09-01 | 2016-05-01 | 2016-08-16
75081-DE Kentucky Fossil | EB020543 | EB020543X | Replace 2A.2 TUF Pump | 51564.12 |  | 51564.12 | 100% |  | 51564.12 | 56400.98 | -4836.86 | 2017-01-03 12:01 | 2016-12-31 | 2016-12-01 | 2017-04-04
75081-DE Kentucky Fossil | EB020561 | EB020561X | Replace 2-1 Clinker Grinder | 54458.08 |  | 54458.08 | 100% |  | 54458.08 | 94337.32 | -39879.24 | 2016-06-30 09:52 | 2016-10-01 | 2016-06-01 | 2016-09-30
75081-DE Kentucky Fossil | EB020563 | EB020563X | Replace PAH Inlet Exp Joint | 88905.91 |  | 88905.91 | 100% |  | 88905.91 | 88693.96 | 211.95 | 2016-06-30 09:07 | 2016-10-01 | 2016-06-01 | 2016-09-30
75081-DE Kentucky Fossil | EB020579 | EB020579X | Replace Training Bldg Air Handlers | 72046.5 |  | 72046.5 | 100% |  | 72046.5 | 94366.52 | -22320.02 | 2016-07-26 07:48 | 2016-12-22 | 2016-09-01 | 2017-02-18
75081-DE Kentucky Fossil | EB020584 | EB020584X | Replace Ammonia Forwarding Pmp Skid | 100215.03 |  | 100215.03 | 100% |  | 100215.03 | 108910 | -8694.97 | 2016-07-26 08:00 | 2016-12-31 | 2016-09-01 | 2017-03-12
75081-DE Kentucky Fossil | EB020587 | EB020587X | Repl WSP Flyash Flow Gate (EF) | 46156.36 |  | 46156.36 | 100% |  | 46156.36 | 42374.34 | 3782.02 | 2016-08-25 13:56 | 2016-12-30 | 2016-10-01 | 2017-02-28
75081-DE Kentucky Fossil | EB020589 | EB020589X | 2-6 CT Motor and Gearbox Repl | 206273.93 |  | 206273.93 | 100% |  | 206273.93 | 201151.22 | 5122.71 | 2016-10-06 14:28 | 2016-09-30 | 2016-10-01 | 2016-08-06
75081-DE Kentucky Fossil | EB020592 | EB020592X | WSP Pavement Expansion (EF) | 490882.01 |  | 490882.01 | 100% |  | 490882.01 | 320905.33 | 169976.68 | 2016-09-02 08:33 | 2016-12-31 | 2016-09-01 | 2017-02-18
75081-DE Kentucky Fossil | EB020597 | EB020597X | Shelter In Place Safe Haven NH3 | 141155.12 |  | 141155.12 | 100% |  | 141155.12 | 185610.01 | -44454.89 | 2016-09-09 11:14 | 2017-05-31 | 2016-09-01 | 2017-06-01
75081-DE Kentucky Fossil | EB020599 | EB020599X | 22 SBAC Cooler Replacement | 153431.22 |  | 153431.22 | 100% |  | 153431.22 | 166685.02 | -13253.8 | 2016-10-04 14:02 | 2016-12-31 | 2016-10-01 | 2017-01-04
75081-DE Kentucky Fossil | EB020600 | EB020600X | 2-2 CT Motor and Gearbox Repl | 214782.96 |  | 214782.96 | 100% |  | 214782.96 | 201151.22 | 13631.74 | 2016-10-06 15:56 | 2016-09-30 | 2016-10-01 | 2017-01-06
75081-DE Kentucky Fossil | EB020602 | EB020602X | C Conveyor Motor Rewind Cap Spare | 47612.08 |  | 47612.08 | 100% |  | 47612.08 | 49315.35 | -1703.27 | 2016-12-09 09:48 | 2016-12-31 | 2016-12-01 | 2017-03-09
75081-DE Kentucky Fossil | EB020603 | EB020603X | Replace Harbor/Deadman Cable | 170297.42 |  | 170297.42 | 100% |  | 170297.42 | 135135.48 | 35161.94 | 2016-11-14 10:11 | 2017-03-31 | 2016-11-01 | 2017-03-30
75081-DE Kentucky Fossil | EB020608 | EB020608X | Ammonia Monitoring System-Deep Dive | 44111.34 |  | 44111.34 | 100% |  | 44111.34 | 0 | 44111.34 | 2016-11-14 10:25 | 2017-11-30 | 2016-12-01
75081-DE Kentucky Fossil | EB020615 | EB020615X | Replace WSP Radial Stacker Belt | 24068.59 |  | 24068.59 | 100% |  | 24068.59 | 27975.18 | -3906.59 | 2016-12-19 11:58 | 2016-12-31 | 2016-12-01 | 2017-03-31
75081-DE Kentucky Fossil | EB021205 | EB021205X | Boiler Room Roof Replacement | 0 |  | 0 |  |  | 191888.5 | 426697 | -234808.5 | 2008-10-13 | 2009-09-16 | 2008-10-01 | 2009-04-06
75081-DE Kentucky Fossil | EB021207 | EB021207X | Coal Bunker Lighting | 0 |  | 0 |  |  | 17506.33 | 30961 | -13454.67 | 2009-03-30 | 2009-06-30 | 2009-05-01 | 2009-05-13
75081-DE Kentucky Fossil | EB021210 | EB021210X | INSTALL PARTICULATE MONTIOR | 0 |  | 0 |  |  | 164901.9 | 266016 | -101114.1 | 2011-04-26 | 2012-02-13 | 2011-05-01 | 2011-10-25
75081-DE Kentucky Fossil | EB021216 | EB021216X | SCR Winterization | 0 |  | 0 |  |  | 85622.78 | 105291 | -19668.22 | 2009-03-13 | 2009-03-30 | 2009-03-01 | 2009-06-13
75081-DE Kentucky Fossil | EB021217 | EB021217X | WSP Switchbreaker Lifter | 0 |  | 0 |  |  | 32798.36 | 44484 | -11685.64 | 2009-07-22 | 2010-01-15 | 2009-07-01 | 2010-01-01
75081-DE Kentucky Fossil | EB021219 | EB021219X | REPLACE FLOW MONITOR | 0 |  | 0 |  |  | 57213.81 | 79903 | -22689.19 | 2009-04-03 | 2009-08-07 | 2009-08-01 | 2009-08-18
75081-DE Kentucky Fossil | EB021221 | EB021221X | Purchase WSP Shovel and Loader | 0 |  | 0 |  |  | 69302.23 | 117133 | -47830.77 | 2009-03-30 | 2009-06-26 | 2009-04-01 | 2009-09-01
75081-DE Kentucky Fossil | EB021222 | EB021222X | Replace Stack Flow Monitor | 0 |  | 0 |  |  | 139968.04 | 103609 | 36359.04 | 2013-09-26 | 2014-06-01 | 2013-10-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021224 | EB021224X | Replace 3 sump pumps | 0 |  | 0 |  |  | 61100.22 | 76206 | -15105.78 | 2009-05-06 | 2010-07-31 | 2009-06-01 | 2010-07-02
75081-DE Kentucky Fossil | EB021231 | EB021231X | Replace CBU Buckets & Chains | 446380.08 |  | 446380.08 | 100% |  | 615217 | 567317.22 | 47899.78 | 2015-09-17 10:09 | 2016-08-01 | 2015-09-01 | 2016-08-10
75081-DE Kentucky Fossil | EB021233 | EB021233X | Replace CBU Chains and Buckets | 0 |  | 0 |  |  | 267717.34 | 357680 | -89962.66 | 2013-08-05 | 2014-08-01 | 2013-08-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021235 | EB021235X | Repl Circ Pip Sac Anodes | 178110.94 |  | 178110.94 | 100% |  | 178110.94 | 181755.68 | -3644.74 | 2015-09-02 13:08 | 2016-07-01 | 2016-06-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021236 | EB021236X | Replace BFP Outlet Valve | 0 |  | 0 |  |  | 406884.84 | 582388 | -175503.16 | 2009-08-20 | 2010-06-22 | 2009-08-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021238 | EB021238X | ID Fan VFD Control Board Rep | 0 |  | 0 |  |  | 338748.68 | 451841 | -113092.32 | 2013-08-26 | 2014-12-31 | 2013-09-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021244 | EB021244X | Replace 2-1 BFP Outlet Valve | 0 |  | 0 |  |  | 382978.67 | 595228 | -212249.33 | 2011-07-19 | 2012-06-07 | 2011-07-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021246 | EB021246X | HVAC Room Roof Replacement | 68.12 |  | 68.12 | 100% |  | 90581.57 | 83631 | 6950.57 | 2015-04-16 15:39 | 2015-09-01 | 2015-06-01 | 2015-09-30
75081-DE Kentucky Fossil | EB021247 | EB021247X | CBU Hoist and Electric Rm Roof | 0 |  | 0 |  |  | 8844.9 | 31973 | -23128.1 | 2012-08-21 | 2013-08-26 | 2013-04-01 | 2013-07-19
75081-DE Kentucky Fossil | EB021249 | EB021249X | CT Acid Metering Pump | 0 |  | 0 |  |  | 69129.57 | 61640 | 7489.57 | 2010-09-16 | 2011-06-20 | 2010-10-01 | 2011-04-20
75081-DE Kentucky Fossil | EB021250 | EB021250X | CBU Cable Reel and Drive | 0 |  | 0 |  |  | 182998.83 | 255347 | -72348.17 | 2012-10-22 | 2014-12-31 | 2012-12-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021257 | EB021257X | S.Thickner Tunnel E. Sump Pump | 0 |  | 0 |  |  | 84952.64 | 155583 | -70630.36 | 2012-08-31 | 2014-11-20 | 2012-09-01 | 2013-04-29
75081-DE Kentucky Fossil | EB021259 | EB021259X | 2-6 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 188695.13 | 357710 | -169014.87 | 2010-03-08 | 2011-02-01 | 2010-04-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021260 | EB021260X | 2-3 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 491833.81 | 423246 | 68587.81 | 2010-09-16 | 2011-07-27 | 2010-10-01 | 2011-02-12
75081-DE Kentucky Fossil | EB021261 | EB021261X | 2-5 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 395830.6 | 370132 | 25698.6 | 2011-08-12 | 2012-06-21 | 2011-09-01 | 2012-07-31
75081-DE Kentucky Fossil | EB021263 | EB021263X | 2-2 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 333065.96 | 544676 | -211610.04 | 2012-08-21 | 2015-05-25 | 2012-09-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021264 | EB021264X | 2-4 Pulverizer Roll Wheel Repl | 0 |  | 0 |  |  | 278972.93 | 358249 | -79276.07 | 2010-11-01 | 2012-10-22 | 2010-11-01 | 2011-03-15
75081-DE Kentucky Fossil | EB021270 | EB021270X | Replacement 2SR2 Transformer | 0 |  | 0 |  |  | 86017.34 | 119913 | -33895.66 | 2009-11-06 | 2010-10-20 | 2009-12-01 | 2010-08-17
75081-DE Kentucky Fossil | EB021271 | EB021271X | Replace F to G Coal Chute | 881078.04 |  | 881078.04 | 100% |  | 1104755.93 | 792558.1 | 312197.83 | 2015-08-28 10:35 | 2016-07-01 | 2015-09-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021275 | EB021275X | Landfill Cover 2010 | 0 |  | 0 |  |  | 3.6082e-16 | 0 | 3.6082e-16 | 2010-03-04 | 2012-01-31 | 2010-09-01 | 2012-03-31
75081-DE Kentucky Fossil | EB021276 | EB021276X | Replace UAT Bushings | 0 |  | 0 |  |  | 33811.56 | 66133 | -32321.44 | 2011-08-11 | 2013-03-25 | 2011-08-01 | 2012-06-28
75081-DE Kentucky Fossil | EB021277 | EB021277X | Replace 1st Layer SCR Catalyst | 0 |  | 0 |  |  | 1463751.22 | 1659977 | -196225.78 | 2014-11-04 | 2015-12-31 | 2014-10-01 | 2015-06-30
75081-DE Kentucky Fossil | EB021278 | EB021278X | Repl 6 IDB Fan inlet exp jts | 0 |  | 0 |  |  | 295183.81 | 511099 | -215915.19 | 2012-01-26 | 2012-12-01 | 2012-02-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021279 | EB021279X | Replace FGD Transformer 2SR1 | 0 |  | 0 |  |  | 74121.84 | 108674 | -34552.16 | 2009-07-31 | 2010-06-08 | 2009-07-01 | 2009-10-20
75081-DE Kentucky Fossil | EB021280 | EB021280X | IT Capital Project Support | 0 |  | 0 |  |  | 146397.99 | 109201 | 37196.99 | 2009-08-20 | 2013-03-30 | 2009-08-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021282 | EB021282X | Repl No 2 Boiler Room Sump Pump | 0 |  | 0 |  |  | 119075.66 | 170756 | -51680.34 | 2010-03-10 | 2011-06-10 | 2010-03-01 | 2010-12-29
75081-DE Kentucky Fossil | EB021283 | EB021283X | Repl FGD Common inlet exp jt | 0 |  | 0 |  |  | 174736.05 | 218989 | -44252.95 | 2011-11-09 | 2012-10-26 | 2011-12-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021284 | EB021284X | Repl 3 IDBF Outlet Exp Jts | 0 |  | 0 |  |  | 437749.47 | 476977 | -39227.53 | 2013-08-26 | 2014-08-01 | 2013-09-01 | 2014-08-31
75081-DE Kentucky Fossil | EB021286 | EB021286X | Replace RH Attemperator Line | 0 |  | 0 |  |  | 237323.9 | 354424 | -117100.1 | 2011-08-22 | 2012-06-08 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021291 | EB021291X | Landfill Cover 2012 | 0 |  | 0 |  |  | -4467.33 | 0 | -4467.33 | 2012-03-02 | 2014-12-31 | 2014-04-01 | 2014-03-31
75081-DE Kentucky Fossil | EB021293 | EB021293X | Landfill Cover 2014 | -52098.18 |  | -52098.18 | 100% |  | 0 | 0 | 0 | 2014-09-24 | 2016-01-31 | 2015-12-01 | 2016-03-31
75081-DE Kentucky Fossil | EB021299 | EB021299X | Replace Abs Module Outlet Duct | 0 |  | 0 |  |  | 741932.53 | 1029673 | -287740.47 | 2013-11-18 | 2014-08-01 | 2013-12-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021301 | EB021301X | Replace Radio System | 0 |  | 0 |  |  | 257396.74 | 439629 | -182232.26 | 2010-04-14 | 2011-03-03 | 2010-04-01 | 2010-12-08
75081-DE Kentucky Fossil | EB021306 | EB021306X | 2-6 Pulv Roll Wheel Repl 2014 | -3878.07 |  | -3878.07 | 100% |  | 630944.06 | 564903 | 66041.06 | 2014-11-24 | 2015-08-01 | 2014-12-01 | 2015-06-29
75081-DE Kentucky Fossil | EB021308 | EB021308X | 2-3 Pulv Roll Wheel Repl | 414603.88 |  | 414603.88 | 100% |  | 714976.79 | 780026.82 | -65050.03 | 2015-09-02 14:06 | 2016-06-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021310 | EB021310X | 2- 5 Pulv Roll Wheel Rep 2016 -2017 | 100329.43 |  | 100329.43 | 100% |  | 100329.43 | 830662.1 | -730332.67 | 2016-11-29 13:38 | 2017-08-31 | 2016-12-01 | 2017-08-11
75081-DE Kentucky Fossil | EB021312 | EB021312X | 2-1 Pulv Roll Wheel Repl | 0 |  | 0 |  |  | 429845.01 | 581014 | -151168.99 | 2013-09-23 | 2014-12-01 | 2013-10-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021314 | EB021314X | 2-4 Pulv Roll Wheel Repl 2015-2016 | 413954.62 |  | 413954.62 | 100% |  | 696856.97 | 777419.11 | -80562.14 | 2015-09-02 14:16 | 2016-06-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021317 | EB021317X | Replace Station Phone System | 0 |  | 0 |  |  | 173656.59 | 256732 | -83075.41 | 2013-06-28 | 2013-12-31 | 2013-07-01 | 2014-01-21
75081-DE Kentucky Fossil | EB021319 | EB021319X | BlrRm Elevator Control Upgrade | 0 |  | 0 |  |  | 368231.07 | 312468 | 55763.07 | 2010-10-05 | 2011-09-16 | 2010-11-01 | 2011-05-04
75081-DE Kentucky Fossil | EB021325 | EB021325X | CT Gearbox Replacement 2010 | 0 |  | 0 |  |  | 91028.11 | 134310 | -43281.89 | 2009-09-25 | 2010-08-19 | 2009-09-01 | 2009-12-28
75081-DE Kentucky Fossil | EB021332 | EB021332X | RHO Pendant Replacement | 0 |  | 0 |  |  | 10381311.76 | 10402876 | -21564.24 | 2012-11-02 | 2015-05-27 | 2012-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021335 | EB021335X | DRFT ELIMIN & HEADER RPLMNT | 0 |  | 0 |  |  | 150713.29 | 240023 | -89309.71 | 2011-11-07 | 2012-09-27 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB021336 | EB021336X | CT Bypass Valve Replacement 2016 | 391340.04 |  | 391340.04 | 100% |  | 411274.87 | 410058.61 | 1216.26 | 2015-10-06 11:44 | 2016-08-01 | 2015-10-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021338 | EB021338A | ARO - Cooling Tower Fill | 301.15 |  | 301.15 | 100% |  | -5.6843e-13 | 0 | -5.6843e-13 | 2010-10-12 | 2013-03-31 | 2012-07-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021351 | EB021351X | Replace Pug Mill Gear Box | 0 |  | 0 |  |  | 51452.97 | 66314 | -14861.03 | 2013-12-20 | 2015-03-18 | 2013-12-01 | 2014-03-31
75081-DE Kentucky Fossil | EB021352 | EB021352X | Retube Chiller in Control Room | 0 |  | 0 |  |  | 156704.78 | 137419 | 19285.78 | 2010-11-02 | 2011-09-16 | 2010-12-01 | 2011-05-31
75081-DE Kentucky Fossil | EB021353 | EB021353X | NH3 Slip Monitor 1 | 0 |  | 0 |  |  | 266572.2 | 242755 | 23817.2 | 2011-08-12 | 2012-06-19 | 2011-08-01 | 2012-04-27
75081-DE Kentucky Fossil | EB021355 | EB021355X | Replace Cond. Control Valve | 0 |  | 0 |  |  | 188557.17 | 245177 | -56619.83 | 2011-06-06 | 2012-04-16 | 2011-06-01 | 2012-07-20
75081-DE Kentucky Fossil | EB021356 | EB021356X | Replace WSP Dust Collector | 0 |  | 0 |  |  | 227631.19 | 133042 | 94589.19 | 2010-11-01 | 2012-05-20 | 2010-12-01 | 2011-11-17
75081-DE Kentucky Fossil | EB021357 | EB021357C | Ash Sluice Pump Soft Starters | -3611.35 |  | -3611.35 | 100% |  | 740689.89 | 649561 | 91128.89 | 2014-11-12 | 2015-10-01 | 2014-11-01 | 2015-11-01
75081-DE Kentucky Fossil | EB021358 | EB021358X | Voltage Regulator Transformers | 0 |  | 0 |  |  | 72696 | 108833 | -36137 | 2010-10-07 | 2011-07-25 | 2010-11-01 | 2011-07-03
75081-DE Kentucky Fossil | EB021362 | EB021362X | New Sulferic Acid System | 0 |  | 0 |  |  | 667594.57 | 654708 | 12886.57 | 2012-08-09 | 2013-08-25 | 2012-08-01 | 2013-06-07
75081-DE Kentucky Fossil | EB021364 | EB021364X | Pugmill Gear Box Replacement | 0 |  | 0 |  |  | 19990.69 | 24709 | -4718.31 | 2010-10-07 | 2012-12-31 | 2010-10-01 | 2011-02-04
75081-DE Kentucky Fossil | EB021365 | EB021365X | STORM WATER PIPE REPLACEMENT | 0 |  | 0 |  |  | 426775.84 | 550683 | -123907.16 | 2010-11-02 | 2011-10-12 | 2010-11-01 | 2011-03-10
75081-DE Kentucky Fossil | EB021366 | EB021366X | Replace Step-up Transformer | 0 |  | 0 |  |  | 5838602.22 | 6851486 | -1012883.78 | 2011-02-23 | 2013-04-01 | 2011-03-01 | 2012-07-19
75081-DE Kentucky Fossil | EB021369 | EB021369X | CT Gearbox Oil Filter | 0 |  | 0 |  |  | 336402.27 | 216834 | 119568.27 | 2012-11-15 | 2013-10-26 | 2012-11-01 | 2013-09-14
75081-DE Kentucky Fossil | EB021370 | EB021370X | Replace FGD Service Water Line | 0 |  | 0 |  |  | 57207.61 | 81196 | -23988.39 | 2011-04-26 | 2011-09-30 | 2011-05-01 | 2011-06-30
75081-DE Kentucky Fossil | EB021373 | EB021373X | WSP Shovel | 0 |  | 0 |  |  | 421891.27 | 553812 | -131920.73 | 2012-04-05 | 2013-01-14 | 2012-06-01 | 2012-09-01
75081-DE Kentucky Fossil | EB021375 | EB021375X | UPS Battery Replacement | 13828 |  | 13828 | 100% |  | 13981.94 | 19621.6 | -5639.66 | 2015-11-17 11:24 | 2016-07-01 | 2015-12-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021378 | EB021378X | Repl Flyash and Lime Scales | 0 |  | 0 |  |  | 212614.91 | 283188 | -70573.09 | 2012-08-21 | 2013-07-22 | 2012-09-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021380 | EB021380X | Ash Pond Modification | 0 |  | 0 |  |  | 162796.25 | 328913 | -166116.75 | 2012-08-02 | 2013-10-26 | 2012-09-01 | 2013-03-14
75081-DE Kentucky Fossil | EB021381 | EB021381X | Replace FGD Sludge Tank | 0 |  | 0 |  |  | 682213.74 | 758918 | -76704.26 | 2012-01-17 | 2012-11-30 | 2012-02-01 | 2012-07-13
75081-DE Kentucky Fossil | EB021383 | EB021383X | Unit Control Simulator | 397176.66 |  | 397176.66 | 100% |  | 1970803.76 | 1656726 | 314077.76 | 2012-12-27 | 2016-12-21 | 2012-12-01 | 2017-03-15
75081-DE Kentucky Fossil | EB021384 | EB021384X | 2-2 Precip Inlet Exp Jnt Repl | 0 |  | 0 |  |  | 456395 | 307763 | 148632 | 2013-10-31 | 2014-06-01 | 2013-12-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021387 | EB021387X | East Bend EAM | 0 |  | 0 |  |  | 544126.33 | 788588.88 | -244462.55 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2010-01-31
75081-DE Kentucky Fossil | EB021394 | EB021394X | Repl Filt Overflow Sumps Pumps | 0 |  | 0 |  |  | 37089.83 | 47672 | -10582.17 | 2011-11-29 | 2012-11-27 | 2011-12-01 | 2012-03-31
75081-DE Kentucky Fossil | EB021395 | EB021395X | Repl Emer Sump Pump Motors | 0 |  | 0 |  |  | 10699.04 | 18509 | -7809.96 | 2011-11-09 | 2012-10-10 | 2011-12-01 | 2012-02-18
75081-DE Kentucky Fossil | EB021396 | EB021396X | REPL PUG MILL GEAR BOX | 0 |  | 0 |  |  | 21919.94 | 42879 | -20959.06 | 2011-11-07 | 2012-10-08 | 2011-12-01 | 2012-01-14
75081-DE Kentucky Fossil | EB021397 | EB021397X | SB Air Compressor Cooler | 0 |  | 0 |  |  | 36018.83 | 40171 | -4152.17 | 2011-12-02 | 2012-11-14 | 2011-12-01 | 2012-01-25
75081-DE Kentucky Fossil | EB021398 | EB021398X | 2LHIM Transformer Replacement | 3221.27 |  | 3221.27 | 100% |  | 96798.69 | 101667 | -4868.31 | 2013-07-15 | 2016-06-30 | 2013-07-01 | 2016-08-06
75081-DE Kentucky Fossil | EB021402 | EB021402X | FGD HVAC Replacement | 0 |  | 0 |  |  | 46909.15 | 60520 | -13610.85 | 2012-07-13 | 2012-12-31 | 2012-09-01 | 2012-12-28
75081-DE Kentucky Fossil | EB021404 | EB021404X | SCR 3rd Layer Catalyst Removal | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-06-06 | 2013-05-22 | 2016-07-01 | 2012-07-23
75081-DE Kentucky Fossil | EB021409 | EB021409X | U2 Lime Injection System | 1353062 |  | 1353062 | 100% |  | 1353062 | 0 | 1353062 | 2016-05-16 11:48 | 2018-08-31 | 2016-05-01
75081-DE Kentucky Fossil | EB021411 | EB021411X | Filtrate Return Pumps | 0 |  | 0 |  |  | 75905.84 | 0 | 75905.84 | 2012-10-22 | 2013-04-26 | 2012-11-01 | 2013-08-23
75081-DE Kentucky Fossil | EB021412 | EB021412X | Install 3rd Layer SCR Catalyst | 0 |  | 0 |  |  | 536263.68 | 0 | 536263.68 | 2013-05-16 | 2013-12-31 | 2013-05-01 | 2013-07-19
75081-DE Kentucky Fossil | EB021414 | EB021414X | Replace Filtered Water Tank | 0 |  | 0 |  |  | 445700.13 | 0 | 445700.13 | 2013-09-23 | 2014-08-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021416 | EB021416X | Install 2nd Layer of Catalyst | 1080438.6 |  | 1080438.6 | 100% |  | 1458006.66 | 0 | 1458006.66 | 2015-10-30 09:26 | 2016-08-31 | 2015-11-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021417 | EB021417X | Station Cameras | 0 |  | 0 |  |  | 341806.24 | 0 | 341806.24 | 2013-02-15 | 2015-01-15 | 2013-03-01 | 2014-12-31
75081-DE Kentucky Fossil | EB021418 | EB021418X | SA Preheat Coils | 0 |  | 0 |  |  | 386370.97 | 0 | 386370.97 | 2013-02-15 | 2014-05-30 | 2013-02-01 | 2013-07-20
75081-DE Kentucky Fossil | EB021419 | EB021419X | Fuel Oil Tank Dike Liner Repl | 0 |  | 0 |  |  | 73436.19 | 0 | 73436.19 | 2012-09-04 | 2012-12-31 | 2012-09-01 | 2013-02-06
75081-DE Kentucky Fossil | EB021420 | EB021420X | CBU MCC HVAC Replacement | 0 |  | 0 |  |  | 9181.45 | 0 | 9181.45 | 2012-08-21 | 2013-03-30 | 2012-11-01 | 2013-03-07
75081-DE Kentucky Fossil | EB021422 | EB021422X | Precipitator Hot Side Rebuild | 627694.09 |  | 627694.09 | 100% |  | 627694.09 | 0 | 627694.09 | 2015-12-04 13:47 | 2018-08-31 | 2016-01-01
75081-DE Kentucky Fossil | EB021423 | EB021423X | Precipitator Upgrade 2014 | 0 |  | 0 |  |  | 9622912.66 | 0 | 9622912.66 | 2013-05-29 | 2014-08-05 | 2013-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021424 | EB021424X | 2-2 SB Air Compressor Cooler | 0 |  | 0 |  |  | 29719.28 | 0 | 29719.28 | 2012-08-10 | 2013-02-28 | 2012-08-01 | 2012-06-09
75081-DE Kentucky Fossil | EB021425 | EB021425X | Landfill Articulating Trucks | 0 |  | 0 |  |  | 768539.66 | 0 | 768539.66 | 2012-08-08 | 2012-11-30 | 2012-08-01 | 2012-11-30
75081-DE Kentucky Fossil | EB021426 | EB021426X | D6 Dozer | 0 |  | 0 |  |  | 340609.78 | 0 | 340609.78 | 2012-08-08 | 2012-11-30 | 2012-09-01 | 2012-12-11
75081-DE Kentucky Fossil | EB021427 | EB021427X | CEMS Hg Umbilical Replacement | 0 |  | 0 |  |  | 114565.63 | 0 | 114565.63 | 2012-08-31 | 2013-02-28 | 2012-09-01 | 2013-04-17
75081-DE Kentucky Fossil | EB021431 | EB021431X | Ash Sluice Pump Seal Water Pipe | 0 |  | 0 |  |  | 34889.91 | 0 | 34889.91 | 2012-11-28 | 2013-11-04 | 2012-12-01 | 2013-03-28
75081-DE Kentucky Fossil | EB021432 | EB021432X | Emissions Particulate Monitor | 0 |  | 0 |  |  | 88312.33 | 0 | 88312.33 | 2013-02-04 | 2013-05-31 | 2013-02-01 | 2013-03-31
75081-DE Kentucky Fossil | EB021433 | EB021433X | Purchase Dredge for Pond Cleaning | 0 |  | 0 |  |  | 165307.31 | 0 | 165307.31 | 2013-05-06 | 2013-12-21 | 2013-07-01 | 2014-01-31
75081-DE Kentucky Fossil | EB021434 | EB021434X | EB2 Precipitator T/R Sets | 0 |  | 0 |  |  | 66053.86 | 0 | 66053.86 | 2013-04-03 | 2013-12-31 | 2013-04-01 | 2013-08-03
75081-DE Kentucky Fossil | EB021436 | EB021436X | Replace LBU Roof | 0 |  | 0 |  |  | 28775.5 | 0 | 28775.5 | 2013-05-06 | 2013-12-31 | 2013-05-01 | 2013-07-15
75081-DE Kentucky Fossil | EB021438 | EB021438X | Replace IP Turbine Blades | 0 |  | 0 |  |  | 1797631.05 | 0 | 1797631.05 | 2013-08-05 | 2014-12-05 | 2013-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021443 | EB021443X | LBU Hold & Close Drive Replacement | 0 |  | 0 |  |  | 358125.71 | 0 | 358125.71 | 2013-08-27 | 2014-10-01 | 2013-10-01 | 2014-09-29
75081-DE Kentucky Fossil | EB021444 | EB021444X | Replace 1-2 SW Strainer | 61 |  | 61 | 100% |  | 184847.86 | 0 | 184847.86 | 2014-12-19 | 2015-10-01 | 2015-04-01 | 2015-08-22
75081-DE Kentucky Fossil | EB021446 | EB021446X | Replace Lining in WSP Sludge Tank | 0 |  | 0 |  |  | 372068.08 | 0 | 372068.08 | 2013-09-23 | 2014-07-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021448 | EB021448X | SSHO Partial Pendants - Mini Panels | 0 |  | 0 |  |  | 2375562.06 | 0 | 2375562.06 | 2013-10-17 | 2014-12-31 | 2013-11-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021455 | EB021455X | NERC CIP V5Upgrade | 1128535.78 |  | 1128535.78 | 100% |  | 1128535.78 | 0 | 1128535.78 | 2016-02-02 14:08 | 2017-06-30 | 2016-02-01 | 2017-09-23
75081-DE Kentucky Fossil | EB021456 | EB021456X | SmartGen Installation at East Bend | 1395488.53 |  | 1395488.53 | 100% |  | 3053252.83 | 0 | 3053252.83 | 2015-01-09 | 2017-12-31 | 2015-01-01
75081-DE Kentucky Fossil | EB021457 | EB021457X | Paving Eastside Parking Lot | 0 |  | 0 |  |  | 65121.93 | 0 | 65121.93 | 2013-08-27 | 2013-12-31 | 2013-08-01 | 2013-10-22
75081-DE Kentucky Fossil | EB021459 | EB021459X | Data Network Upgrade | -74.42 |  | -74.42 | 100% |  | 73954.52 | 0 | 73954.52 | 2013-08-27 | 2015-03-31 | 2013-12-01 | 2014-09-30
75081-DE Kentucky Fossil | EB021460 | EB021460X | PCME PM CEMS Monitor | 0 |  | 0 |  |  | 290389.77 | 0 | 290389.77 | 2014-02-20 | 2015-03-31 | 2014-05-01 | 2015-03-12
75081-DE Kentucky Fossil | EB021461 | EB021461X | Landfill Haul Road Drainage System | 0 |  | 0 |  |  | 72810.32 | 0 | 72810.32 | 2013-09-26 | 2014-07-31 | 2013-12-01 | 2014-06-01
75081-DE Kentucky Fossil | EB021462 | EB021462X | 125 DC Station Battery 2 | 0 |  | 0 |  |  | 59567.58 | 0 | 59567.58 | 2013-10-28 | 2014-03-31 | 2013-11-01 | 2014-06-23
75081-DE Kentucky Fossil | EB021463 | EB021463X | 2 Sec Air Water Sup Preheat Coils | 0 |  | 0 |  |  | 52343.66 | 0 | 52343.66 | 2014-01-08 | 2014-03-31 | 2014-11-01 | 2014-02-22
75081-DE Kentucky Fossil | EB021465 | EB021465X | Replace 2SR-7 Transformer | 0 |  | 0 |  |  | 57245.3 | 0 | 57245.3 | 2014-03-06 | 2015-03-31 | 2014-05-01 | 2014-08-20
75081-DE Kentucky Fossil | EB021466 | EB021466X | 2-2 SBAC Coolers and Controls | 0 |  | 0 |  |  | 287565.77 | 0 | 287565.77 | 2014-05-27 | 2014-08-31 | 2014-05-01 | 2014-09-27
75081-DE Kentucky Fossil | EB021468 | EB021468X | Isophase Bus Wall Bushings | 0 |  | 0 |  |  | 366324.33 | 0 | 366324.33 | 2014-05-23 | 2014-08-31 | 2014-05-01 | 2014-08-20
75081-DE Kentucky Fossil | EB021469 | EB021469X | Cooling Tower Motor Platforms | 0 |  | 0 |  |  | 51465.06 | 0 | 51465.06 | 2014-05-27 | 2014-08-31 | 2014-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB021470 | EB021470X | Data Network Upgrade | 0 |  | 0 |  |  | 82724.85 | 0 | 82724.85 | 2014-10-23 | 2015-09-02 | 2014-11-01 | 2014-11-28
75081-DE Kentucky Fossil | EB021471 | EB021471X | Boiler Room Exhaust Fan Blades Set | 0 |  | 0 |  |  | 37489.51 | 0 | 37489.51 | 2014-09-04 | 2014-12-23 | 2014-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EB021476 | EB021476X | Rep Penthouse Front Wall Insulation | -21.47 |  | -21.47 | 100% |  | 33853.69 | 0 | 33853.69 | 2015-03-09 08:14 | 2015-07-01 | 2015-03-01 | 2015-06-29
75081-DE Kentucky Fossil | EB021477 | EB021477X | Economizer Outlet Duct Insulation | 90834.25 |  | 90834.25 | 100% |  | 90834.25 | 0 | 90834.25 | 2016-02-26 11:31 | 2016-09-22 | 2016-05-01 | 2016-08-07
75081-DE Kentucky Fossil | EB021480 | EB021480X | Mercury CEMS | 0 |  | 0 |  |  | 313179.55 | 0 | 313179.55 | 2014-09-04 | 2015-03-06 | 2014-09-01 | 2015-04-09
75081-DE Kentucky Fossil | EB021482 | EB021482X | CT Gearbox and Fan Blades 2-10 | 0 |  | 0 |  |  | 66623.58 | 0 | 66623.58 | 2014-09-04 | 2014-08-31 | 2014-09-01 | 2014-11-20
75081-DE Kentucky Fossil | EB021483 | EB021483X | Remove 1st Layer SCR Catalyst | 0 |  | 0 |  |  | -5.6843e-14 | 0 | -5.6843e-14 | 2014-09-25 | 2014-12-31 | 2015-02-01 | 2014-12-08
75081-DE Kentucky Fossil | EB021486 | EB021486X | Replace Ash Sluice Pump Motor | 0 |  | 0 |  |  | 52516.02 | 0 | 52516.02 | 2014-11-07 | 2015-06-30 | 2014-11-01 | 2015-03-16
75081-DE Kentucky Fossil | EB021487 | EB021487X | Cake Transfer Belt | 0 |  | 0 |  |  | 18589.81 | 0 | 18589.81 | 2014-11-04 | 2014-11-28 | 2014-11-01 | 2015-01-21
75081-DE Kentucky Fossil | EB021488 | EB021488X | 30 Day Lime Silo Elec Bldg Roof | 0 |  | 0 |  |  | 6189.62 | 0 | 6189.62 | 2014-11-04 | 2014-12-01 | 2014-11-01 | 2015-02-03
75081-DE Kentucky Fossil | EB021489 | EB021489X | 2-2 Fly Ash Silo to Silo Blowers | 230190.28 |  | 230190.28 | 100% |  | 1307045.34 | 0 | 1307045.34 | 2014-12-08 | 2016-08-31 | 2014-12-01 | 2016-09-23
75081-DE Kentucky Fossil | EB021490 | EB021490X | SCR Condensate-Storm Sewer Improve | 4631.63 |  | 4631.63 | 100% |  | 685560 | 0 | 685560 | 2015-01-08 | 2016-02-28 | 2015-01-01 | 2016-02-12
75081-DE Kentucky Fossil | EB021491 | EB021491X | Purchase Landfill Property | 2876.57 |  | 2876.57 | 100% |  | 1226323.35 | 0 | 1226323.35 | 2015-01-08 | 2015-12-31 | 2015-10-01 | 2016-02-29
75081-DE Kentucky Fossil | EB021492 | EB021492X | TriState EB Parcels PP 29711 29690 | 0 |  | 0 |  |  | 595682.72 | 0 | 595682.72 | 2014-12-31 | 2014-12-31 | 2014-12-01 | 2015-03-31
75081-DE Kentucky Fossil | EB021494 | EB021494X | Mixer Discharge Belt | -8.59 |  | -8.59 | 100% |  | 6119.03 | 0 | 6119.03 | 2015-03-11 07:09 | 2015-06-30 | 2015-04-01 | 2015-06-07
75081-DE Kentucky Fossil | EB021495 | EB021495X | 2-1 SBAC Cooler Replacement | -143.38 |  | -143.38 | 100% |  | 85661.4 | 0 | 85661.4 | 2015-03-09 10:19 | 2015-02-28 | 2015-04-01 | 2014-06-01
75081-DE Kentucky Fossil | EB1922 | EB02CTA13 | Cost to Achieve 2013 | 75.32 |  | 75.32 | 100% |  | 7804.42 | 0 | 7804.42 | 2013-10-03 | 2014-12-31 | 2013-12-01 | 2014-03-31
75081-DE Kentucky Fossil | EB0412 | EB0412X | Repl Boiler Economizer | 272149.17 |  | 272149.17 | 100% |  | 272149.17 | 0 | 272149.17 | 2016-01-19 09:34 | 2018-12-31 | 2016-01-01
75081-DE Kentucky Fossil | EB0822 | EB0822X | EBS U2 REPLACE CARDOX CONTROLS | 0 |  | 0 |  |  | 442775.02 | 0 | 442775.02 | 2011-10-07 | 2012-08-24 | 2011-12-01 | 2012-07-15
75081-DE Kentucky Fossil | EB1152 | EB1152X | FGD Landfill Conc Spillway | 0 |  | 0 |  |  | 62419.41 | 0 | 62419.41 | 2008-09-02 | 2009-03-31 | 2008-11-01 | 2008-12-31
75081-DE Kentucky Fossil | EB200531 | EB200531X | Thickener Tunnel Emerg Sump Pump | 0 |  | 0 |  |  | 143341.64 | 0 | 143341.64 | 2008-09-02 | 2011-04-30 | 2008-11-01 | 2011-04-25
75081-DE Kentucky Fossil | EB201206 | EB201206X | Replace lower front wall Slope tube | 0 |  | 0 |  |  | 4419810.52 | 0 | 4419810.52 | 2009-01-26 | 2012-07-10 | 2009-07-01 | 2012-07-15
75081-DE Kentucky Fossil | EB201220 | EB201220X | Cooling Tower Motor Replace 08 | 0 |  | 0 |  |  | 94484.15 | 0 | 94484.15 | 2008-07-09 | 2009-07-31 | 2008-08-01 | 2009-03-22
75081-DE Kentucky Fossil | EB201259 | EB201259X | Replace 1 CT Fan Assembly | 0 |  | 0 |  |  | 33498.15 | 0 | 33498.15 | 2010-02-02 | 2011-01-04 | 2010-02-01 | 2010-08-14
75081-DE Kentucky Fossil | EB201333 | EB201333X | Retube Spare Hydrogen Cooler | 0 |  | 0 |  |  | 69629.15 | 0 | 69629.15 | 2010-03-18 | 2010-12-01 | 2010-03-01 | 2010-08-07
75081-DE Kentucky Fossil | EB201341 | EB201341X | FGD Lab | 0 |  | 0 |  |  | 23931.67 | 0 | 23931.67 | 2010-10-19 | 2012-08-14 | 2010-11-01 | 2011-03-08
75081-DE Kentucky Fossil | EB201344 | EB201344X | HVG Neutral Phase Bushing | 0 |  | 0 |  |  | 204035.6 | 0 | 204035.6 | 2011-11-27 | 2013-04-24 | 2011-12-01 | 2012-07-20
75081-DE Kentucky Fossil | EB201348 | EB201348X | FGD Controls Upgrade | 0 |  | 0 |  |  | 4503399.54 | 0 | 4503399.54 | 2010-12-20 | 2013-04-26 | 2010-12-01 | 2012-07-29
75081-DE Kentucky Fossil | EB201357 | EB201357X | Pulverizer Gbx Replace 1 of 6 | 0 |  | 0 |  |  | 309079.48 | 0 | 309079.48 | 2012-02-17 | 2012-12-03 | 2012-02-01 | 2012-07-20
75081-DE Kentucky Fossil | EB201365 | EB201365X | Cooling Tower Breakr Repl PH1 | 0 |  | 0 |  |  | 222532.07 | 0 | 222532.07 | 2010-02-15 | 2011-10-27 | 2010-03-01 | 2010-08-17
75081-DE Kentucky Fossil | EB201367 | EB201367X | CT BREAKER PHASE 2 | 0 |  | 0 |  |  | 404446.52 | 0 | 404446.52 | 2011-10-20 | 2012-11-30 | 2011-11-01 | 2012-07-29
75081-DE Kentucky Fossil | EB201370 | EB201370X | Install Stack Lining | 0 |  | 0 |  |  | 8580311.74 | 0 | 8580311.74 | 2011-06-06 | 2014-08-01 | 2011-06-01 | 2014-08-28
75081-DE Kentucky Fossil | EB201374 | EB201374X | DCS Network Upgrade | 0 |  | 0 |  |  | 839877.54 | 0 | 839877.54 | 2008-10-06 | 2010-05-24 | 2008-12-01 | 2009-08-25
75081-DE Kentucky Fossil | EB2922 | EB2922X | EB2-3rd Catalyst Bed-Addition | 0 |  | 0 |  |  | 1303087.13 | 0 | 1303087.13 | 2008-09-29 | 2009-08-20 | 2008-11-01 | 2009-08-29
75081-DE Kentucky Fossil | EBS01210 | EBS01210X | Filtrate Storage Tank Replacement | 0 |  | 0 |  |  | 515270.8 | 0 | 515270.8 | 2013-09-10 | 2014-08-01 | 2013-09-01 | 2014-09-01
75081-DE Kentucky Fossil | EBS01212 | EBS01212X | Cooling Tower Gearbox 2009 | 0 |  | 0 |  |  | 331650.49 | 0 | 331650.49 | 2009-02-05 | 2010-12-31 | 2009-02-01 | 2010-09-25
75081-DE Kentucky Fossil | EBS01213 | EBS01213X | Cooling Tower Gearbox 2010 | 0 |  | 0 |  |  | 319633.51 | 0 | 319633.51 | 2009-04-17 | 2011-03-25 | 2009-05-01 | 2011-01-20
75081-DE Kentucky Fossil | EBS01216 | EBS01216X | Furnace Sidewall Weld Overlay | 0 |  | 0 |  |  | 903384.86 | 0 | 903384.86 | 2009-02-05 | 2019-12-01 | 2009-02-01 | 2009-08-15
75081-DE Kentucky Fossil | EBS01243 | EBS01243X | New East Bend Landfill | 20464470.42 |  | 20464470.42 | 100% |  | 27216024.13 | 0 | 27216024.13 | 2013-11-19 | 2018-06-30 | 2013-12-01
75081-DE Kentucky Fossil | EBS01260 | EBS01260X | Sand Filter for WSP Serv Water | 0 |  | 0 |  |  | 28186.52 | 0 | 28186.52 | 2008-07-09 | 2009-04-23 | 2008-09-01 | 2009-04-23
75081-DE Kentucky Fossil | EBS01261 | EBS01261X | Replace CBU Chains | 0 |  | 0 |  |  | 121020.66 | 0 | 121020.66 | 2008-10-07 | 2010-08-15 | 2008-12-01 | 2010-08-17
75081-DE Kentucky Fossil | EBS01264 | EBS01264X | Filtered Water Pmp Replacement | 0 |  | 0 |  |  | 30048.92 | 0 | 30048.92 | 2008-07-09 | 2009-09-21 | 2008-09-01 | 2009-05-27
75081-DE Kentucky Fossil | EBS01266 | EBS01266X | Repl Lime Conv Metal Detector | -62.97 |  | -62.97 | 100% |  | 47980.9 | 0 | 47980.9 | 2013-08-01 | 2015-12-31 | 2013-09-01 | 2015-08-13
75081-DE Kentucky Fossil | EBS01277 | EBS01277X | ASH HOPPER DOWNCOMER REPLACEMT | 0 |  | 0 |  |  | 292221.11 | 0 | 292221.11 | 2011-10-05 | 2012-10-01 | 2011-10-01 | 2012-07-20
75081-DE Kentucky Fossil | EBS01280 | EBS01280X | Deep Well Addition | 0 |  | 0 |  |  | 560388.55 | 0 | 560388.55 | 2008-09-05 | 2010-01-31 | 2008-11-01 | 2010-02-05
75081-DE Kentucky Fossil | EBS01290 | EBS01290X | REPLACE CIRC PIP SAC ANODES | 0 |  | 0 |  |  | 184400.28 | 0 | 184400.28 | 2011-10-07 | 2012-08-21 | 2011-10-01 | 2012-07-20
75081-DE Kentucky Fossil | EBS01296 | EBS01296X | Demin Acid Tank | 885351.44 |  | 885351.44 | 100% |  | 1065711.15 | 0 | 1065711.15 | 2015-10-19 11:48 | 2016-09-30 | 2015-11-01 | 2016-10-08
75081-DE Kentucky Fossil | EBS01315 | EBS01315X | Replace 2-2 WS Strainer | 0 |  | 0 |  |  | 189703.05 | 0 | 189703.05 | 2009-04-22 | 2010-11-23 | 2009-07-01 | 2010-12-02
75081-DE Kentucky Fossil | EBS01317 | EBS01317X | Cooling Tower Motor Replace-09 | 0 |  | 0 |  |  | 175068.81 | 0 | 175068.81 | 2009-06-23 | 2011-02-28 | 2009-06-01 | 2010-07-01
75081-DE Kentucky Fossil | EBS01319 | EBS01319X | Cooling Tower Motor Repl | 0 |  | 0 |  |  | 165913.64 | 0 | 165913.64 | 2010-03-04 | 2011-12-31 | 2010-03-01 | 2011-02-05
75081-DE Kentucky Fossil | EBS01322 | EBS01322X | Replace RAT Bushings | 0 |  | 0 |  |  | 122951.63 | 0 | 122951.63 | 2010-08-17 | 2011-09-30 | 2010-09-01 | 2011-07-14
75081-DE Kentucky Fossil | EBS01324 | EBS01324X | Bottom Turbine Oil Cooler | 0 |  | 0 |  |  | 151889.36 | 0 | 151889.36 | 2008-11-11 | 2009-10-07 | 2009-02-01 | 2009-08-20
75081-DE Kentucky Fossil | EBS01328 | EBS01328X | Retire Turbine Doghouse | 0 |  | 0 |  |  | 1.2434e-14 | 0 | 1.2434e-14 | 2008-09-02 | 2008-10-31 | 2008-10-01 | 2009-03-01
75081-DE Kentucky Fossil | EBS01330 | EBS01330X | Replace Service Building Roof | 2.96 |  | 2.96 | 100% |  | 183035.58 | 0 | 183035.58 | 2015-04-16 13:58 | 2015-12-01 | 2015-07-01 | 2015-11-13
75081-DE Kentucky Fossil | EBS01340 | EBS01340X | Replace Coal Handling Controls | 0 |  | 0 |  |  | 2034071.32 | 0 | 2034071.32 | 2013-07-30 | 2014-12-31 | 2013-07-01 | 2014-09-29
75081-DE Kentucky Fossil | EBS01343 | EBS01343X | REPL ABS Pump Brkr Phase I | 0 |  | 0 |  |  | 182983.51 | 0 | 182983.51 | 2012-11-22 | 2013-10-01 | 2012-12-01 | 2013-07-29
75081-DE Kentucky Fossil | EBS01344 | EBS01344X | Repl ABS Pump Brkrs Phase II | 0 |  | 0 |  |  | 197243.67 | 0 | 197243.67 | 2012-11-23 | 2013-10-01 | 2012-12-01 | 2013-07-29
75081-DE Kentucky Fossil | EBS01349 | EBS01349X | Install CBU Drainage System | 0 |  | 0 |  |  | 97343.1 | 0 | 97343.1 | 2008-09-02 | 2009-03-31 | 2008-10-01 | 2009-03-19
75081-DE Kentucky Fossil | EBS01352 | EBS01352X | Repl Emergency Pond Pumps | 0 |  | 0 |  |  | 380231.98 | 0 | 380231.98 | 2012-08-31 | 2014-05-22 | 2012-09-01 | 2013-11-30
75081-DE Kentucky Fossil | EBS01356 | EBS01356X | Replace FGD Common Outlet Duct | 0 |  | 0 |  |  | 1184558.04 | 0 | 1184558.04 | 2008-09-19 | 2012-07-10 | 2008-10-01 | 2012-07-13
75081-DE Kentucky Fossil | EBS01364 | EBS01364X | SAH and PAH Gas Outlet Duct platfor | 0 |  | 0 |  |  | 31229.62 | 0 | 31229.62 | 2010-09-16 | 2011-08-22 | 2010-11-01 | 2011-04-13
75081-DE Kentucky Fossil | EBS01374 | EBS01374X | REPLACE SEWAGE TREATMENT PLANT | 0 |  | 0 |  |  | 219250.96 | 0 | 219250.96 | 2011-10-20 | 2013-02-28 | 2011-12-01 | 2013-03-28
75081-DE Kentucky Fossil | EBS01375 | EBS01375X | Rplc Transfer Tower Fire Det Syst | 0 |  | 0 |  |  | 203052.76 | 0 | 203052.76 | 2012-11-21 | 2013-11-06 | 2012-12-01 | 2013-07-20
75081-DE Kentucky Fossil | EBS01376 | EBS01376X | FGD plenum PIT purge system | 0 |  | 0 |  |  | 53794.53 | 0 | 53794.53 | 2009-04-14 | 2010-08-30 | 2009-04-01 | 2010-08-17
75081-DE Kentucky Fossil | EBS01379 | EBS01379X | Install New Trona Blower | 0 |  | 0 |  |  | 95083.85 | 0 | 95083.85 | 2008-09-02 | 2009-11-01 | 2008-11-01 | 2009-12-03
75081-DE Kentucky Fossil | EBS01382 | EBS01382X | West Landfill Monitoring Wells | 0 |  | 0 |  |  | 195449.12 | 0 | 195449.12 | 2008-08-24 | 2012-09-30 | 2008-11-01 | 2012-08-31
75081-DE Kentucky Fossil | EBS01383 | EBS01383X | Replace CEMS Shelter and DAS | 0 |  | 0 |  |  | 523455.62 | 0 | 523455.62 | 2008-12-16 | 2009-06-23 | 2008-12-01 | 2009-03-31
75081-DE Kentucky Fossil | NIST1067 | INT1067A | MI P&L Analyzer Software | -102.54 |  | -102.54 | 100% |  | 7457.32 | 0 | 7457.32 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75081-DE Kentucky Fossil | NINT1067 | INT1067C | MI P&L Analyzer Software | 0 |  | 0 |  |  | 24397.15 | 0 | 24397.15 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75081-DE Kentucky Fossil | PCTAIC910 | INT910C | Post Analysis (Genportal Addtl Uses | 1006.08 |  | 1006.08 | 100% |  | 150694.68 | 0 | 150694.68 | 2014-07-04 | 2015-07-31 | 2014-07-01 | 2016-03-31
75081-DE Kentucky Fossil | MF601200 | MF601200X | SAH Racks & Pinion Gears Repl | 0 |  | 0 |  |  | 66502.26 | 0 | 66502.26 | 2010-10-01 | 2011-07-06 | 2010-11-01 | 2011-02-21
75081-DE Kentucky Fossil | MU061200 | MU061200X | Replace 6 3 BFP Motor | 0 |  | 0 |  |  | 177463.48 | 0 | 177463.48 | 2008-09-11 | 2008-12-31 | 2008-09-01 | 2008-12-31
75081-DE Kentucky Fossil | MU061201 | MU061201X | 6-2 BFP Motor Replace Rotor | 0 |  | 0 |  |  | 41284.97 | 0 | 41284.97 | 2008-11-11 | 2009-05-01 | 2008-12-01 | 2009-06-17
75081-DE Kentucky Fossil | MU061236 | MU061236X | Exhauster Fan Replacement | 0 |  | 0 |  |  | 34972 | 0 | 34972 | 2010-05-10 | 2010-09-30 | 2010-06-01 | 2010-06-24
75081-DE Kentucky Fossil | MU061238 | MU061238X | replace 6-1 ID fan motor | 0 |  | 0 |  |  | 211104.15 | 0 | 211104.15 | 2010-05-07 | 2010-12-31 | 2010-06-01 | 2010-07-01
75081-DE Kentucky Fossil | MU061240 | MU061240X | FWH Safety Relief Tank | 0 |  | 0 |  |  | 54664.24 | 0 | 54664.24 | 2010-10-18 | 2011-07-29 | 2010-11-01 | 2011-02-19
75081-DE Kentucky Fossil | MU061241 | MU061241X | CO2 Analyzer Replacement | 0 |  | 0 |  |  | 10716.44 | 0 | 10716.44 | 2010-11-09 | 2012-11-24 | 2010-12-01 | 2011-05-10
75081-DE Kentucky Fossil | MU061249 | MU061249X | Miami Fort U6 EAM | 0 |  | 0 |  |  | 205409.1 | 0 | 205409.1 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2011-11-30
75081-DE Kentucky Fossil | MU601212 | MU601212X | Operator Console Replacement | 0 |  | 0 |  |  | 504274.86 | 0 | 504274.86 | 2010-02-02 | 2011-03-31 | 2010-02-01 | 2011-02-21
75081-DE Kentucky Fossil | MU601236 | MU601236X | Fire Detection Sys Install | 0 |  | 0 |  |  | 100337.73 | 0 | 100337.73 | 2009-03-03 | 2009-12-22 | 2009-03-01 | 2009-09-05
75081-DE Kentucky Fossil | MU601239 | MU601239A | Asbestos Abatement Replacement | -41005.04 |  | -41005.04 | 100% |  | 0 | 0 | 0 | 2009-05-06 | 2014-12-31 | 2009-05-01 | 2015-03-31
75081-DE Kentucky Fossil | FPCTAITKY | PCTAI1402 | Consolidated Fuels Mgt Pltfrm KY PH | 0 |  | 0 |  |  | 43062.05 | 0 | 43062.05 | 2013-12-12 | 2013-03-31 | 2013-12-01 | 2013-03-31
75081-DE Kentucky Fossil | FPCTAITMF | PCTAI1403 | Consolidated Fuels Mgmt Pltfrm MF P | 0 |  | 0 |  |  | 17072.65 | 0 | 17072.65 | 2013-12-12 | 2013-03-31 | 2013-12-01 | 2013-03-31
75081-DE Kentucky Fossil | PCTAIT31 | PCTAI31 | PGO Long Range Planning Tool | -720.29 |  | -720.29 | 100% |  | 75884.71 | 0 | 75884.71 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081-DE Kentucky Fossil | PCTAIT31 | PCTAI31J | PGO Long Range Planning Tool | -20.3 |  | -20.3 | 100% |  | 996.63 | 0 | 996.63 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081-DE Kentucky Fossil | PCTAITF2 | PCTAITH21 | INT164 Hardware | -33.39 |  | -33.39 | 100% |  | 4792.54 | 0 | 4792.54 | 2014-07-14 | 2016-02-29 | 2014-09-01 | 2016-05-31
75081-DE Kentucky Fossil | PCTAITF2 | PCTAITS21 | INT164 Software | 5160.78 |  | 5160.78 | 100% |  | 284967.47 | 0 | 284967.47 | 2014-07-14 | 2016-02-29 | 2014-08-01 | 2016-05-31
75081-DE Kentucky Fossil | EBS01204 | REBS01204 | EBS-Landfill Cover | -246.29 |  | -246.29 | 100% |  | 0.01 | 0 | 0.01 | 2007-03-21 | 2010-04-30 | 2008-10-01 | 2010-04-30
75081-DE Kentucky Fossil | EBS01312 | REBS01312 | Remove Bypass Ducts | 0 |  | 0 |  |  | 90267.94 | 0 | 90267.94 | 2008-03-12 | 2009-06-30 | 2008-10-01 | 2008-07-26
75082-DE Kentucky Combustion Turbin | PCTAIT137 | AIT13709H | Gas ETRM | 0 |  | 0 |  |  | 222.85 | 0 | 222.85 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082-DE Kentucky Combustion Turbin | PCTAIT137 | AIT13709S | Gas ETRM | 0 |  | 0 |  |  | 29470.27 | 0 | 29470.27 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21810H | FSO Forecasting Consolidation | -5.23 |  | -5.23 | 100% |  | 517.02 | 0 | 517.02 | 2014-04-11 | 2015-12-31 | 2014-06-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21810S | FSO Forecasting Consolidation | -63470.95 |  | -63470.95 | 100% |  | 62339.77 | 0 | 62339.77 | 2014-04-11 | 2015-12-31 | 2014-06-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT218 | AIT21826S | FSO Forecasting Phase III | 72137.66 |  | 72137.66 | 100% |  | 72137.66 | 0 | 72137.66 | 2016-12-16 08:18 | 2017-06-30 | 2016-12-01 | 2017-05-31
75082-DE Kentucky Combustion Turbin | OPTIM | COPTIM | Develop OPTIM Modeling Tool | 52958.56 |  | 52958.56 | 100% |  | 52958.56 | 0 | 52958.56 | 2016-01-15 14:16 | 2017-09-30 | 2016-01-01 | 2017-09-16
75082-DE Kentucky Combustion Turbin | WD101206 | CWD101206 | WGS CT1 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 19950.75 | 0 | 19950.75 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-16
75082-DE Kentucky Combustion Turbin | WD201203 | CWD201203 | WGS CT2 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 20220.8 | 0 | 20220.8 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-16
75082-DE Kentucky Combustion Turbin | WD401203 | CWD401203 | WGS CT4 PROPANE CNTL PNL REPL | 0 |  | 0 |  |  | 20551.77 | 0 | 20551.77 | 2008-03-28 | 2009-05-11 | 2008-05-01 | 2009-03-19
75082-DE Kentucky Combustion Turbin | WD601200 | CWD601200 | WGS CT6 AA Module HVAC Units | 0 |  | 0 |  |  | 25254.92 | 0 | 25254.92 | 2007-10-04 | 2007-12-31 | 2007-12-01 | 2008-07-15
75082-DE Kentucky Combustion Turbin | WD601201 | CWD601201 | WGS CT6 DD Module HVAC Unit | 0 |  | 0 |  |  | 8503.12 | 0 | 8503.12 | 2007-10-04 | 2007-12-31 | 2007-12-01 | 2008-07-09
75082-DE Kentucky Combustion Turbin | WDC01201 | CWDC01201 | WGS CT1-6 CEMS XML EDR Upgrade | 0 |  | 0 |  |  | 69278.98 | 0 | 69278.98 | 2008-02-06 | 2009-10-27 | 2008-03-01 | 2009-02-27
75082-DE Kentucky Combustion Turbin | WDC01204 | CWDC01204 | WGS RO ANALYZER REPLACEMENT | 0 |  | 0 |  |  | 27399.42 | 0 | 27399.42 | 2007-11-14 | 2008-06-21 | 2007-12-01 | 2008-05-07
75082-DE Kentucky Combustion Turbin | WDC01209 | CWDC01209 | INSTALL SYNC CHECK RELAY | 0 |  | 0 |  |  | 5782.47 | 0 | 5782.47 | 2008-03-06 | 2009-05-11 | 2008-04-01 | 2009-04-01
75082-DE Kentucky Combustion Turbin | WG0244 | CWG0244 | WGS-CT4 Major C Overhaul | 0 |  | 0 |  |  | 6943543.25 | 0 | 6943543.25 | 2007-08-05 | 2009-04-15 | 2007-12-01 | 2009-05-16
75082-DE Kentucky Combustion Turbin | WGS01205 | CWGS01205 | Security Camera System | 0 |  | 0 |  |  | 19811.72 | 0 | 19811.72 | 2007-01-04 | 2007-06-30 | 2007-01-01 | 2007-11-30
75082-DE Kentucky Combustion Turbin | WD201202 | D1487 | WGS-CT 24V Repl Battery Bank | 0 |  | 0 |  |  | 8047.88 | 0 | 8047.88 | 2007-08-26 | 2008-03-31 | 2007-11-01 | 2008-02-26
75082-DE Kentucky Combustion Turbin | NINT1067 | INT1067C | MI P&L Analyzer Software | 0 |  | 0 |  |  | 20241.9 | 0 | 20241.9 | 2014-05-20 | 2014-12-31 | 2014-06-01 | 2015-05-31
75082-DE Kentucky Combustion Turbin | PCTAIC910 | INT910C | Post Analysis (Genportal Addtl Uses | 566.18 |  | 566.18 | 100% |  | 93889.59 | 0 | 93889.59 | 2014-07-04 | 2015-07-31 | 2014-07-01 | 2016-03-31
75082-DE Kentucky Combustion Turbin | PCTAIT31 | PCTAI31 | PGO Long Range Planning Tool | 0 |  | 0 |  |  | 43066.58 | 0 | 43066.58 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75082-DE Kentucky Combustion Turbin | PCTAITF2 | PCTAITH21 | INT164 Hardware | -27.44 |  | -27.44 | 100% |  | 3798.99 | 0 | 3798.99 | 2014-07-14 | 2016-02-29 | 2014-09-01 | 2016-05-31
75082-DE Kentucky Combustion Turbin | PCTAITF2 | PCTAITS21 | INT164 Software | 4446.39 |  | 4446.39 | 100% |  | 384303.53 | 0 | 384303.53 | 2014-07-14 | 2016-02-29 | 2014-08-01 | 2016-05-31
75082-DE Kentucky Combustion Turbin | WD011201 | WD011201X | WGS Unit 1 Excitation Controls | -10000 |  | -10000 | 100% |  | 194495.39 | 0 | 194495.39 | 2011-09-20 | 2012-12-31 | 2011-10-01 | 2013-01-05
75082-DE Kentucky Combustion Turbin | WD021200 | WD021200X | CT2 REPLACE PROP. BLR CONTRL | 0 |  | 0 |  |  | 38713.45 | 0 | 38713.45 | 2008-10-12 | 2008-12-31 | 2008-12-01 | 2009-02-27
75082-DE Kentucky Combustion Turbin | WD021201 | WD021201X | WGS Unit 2 Excitation Controls | -10000 |  | -10000 | 100% |  | 196734.46 | 0 | 196734.46 | 2011-09-20 | 2012-12-31 | 2011-10-01 | 2013-01-16
75082-DE Kentucky Combustion Turbin | WD031200 | WD031200X | WGS No3 Comp Blade Replacement | 0 |  | 0 |  |  | 1050679.03 | 0 | 1050679.03 | 2009-08-18 | 2009-12-31 | 2009-08-01 | 2009-12-23
75082-DE Kentucky Combustion Turbin | WD031201 | WD031201X | WGS Unit 3 Excitation Controls | -133332.9 |  | -133332.9 | 100% |  | 254033.11 | 0 | 254033.11 | 2013-01-31 | 2013-12-31 | 2013-02-01 | 2014-01-15
75082-DE Kentucky Combustion Turbin | WD041200 | WD041200X | WGS Unit 4 Excitation Controls | 0 |  | 0 |  |  | 223925.11 | 0 | 223925.11 | 2013-02-07 | 2014-04-30 | 2013-02-01 | 2014-01-15
75082-DE Kentucky Combustion Turbin | WD051202 | WD051202X | WGS Unit 5 Excitation Controls | -6150 |  | -6150 | 100% |  | 273443.75 | 0 | 273443.75 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082-DE Kentucky Combustion Turbin | WD061200 | WD061200X | WGS Unit 6 Excitation Controls | -131226.01 |  | -131226.01 | 100% |  | 157727.59 | 0 | 157727.59 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082-DE Kentucky Combustion Turbin | WD061203 | WD061203X | WGS- U6 Compressor Blade Replc | 0 |  | 0 |  |  | 349669.18 | 0 | 349669.18 | 2012-05-30 | 2012-12-31 | 2012-06-01 | 2012-09-29
75082-DE Kentucky Combustion Turbin | WD101200 | WD101200X | WGS-CT1 AA Module HVAC Units | -29090.14 |  | -29090.14 | 100% |  | 37452.85 | 0 | 37452.85 | 2013-08-18 | 2015-04-25 | 2013-12-01 | 2014-03-16
75082-DE Kentucky Combustion Turbin | WD101201 | WD101201X | WGS-CT1 DD Module HVAC Unit | -9722.91 |  | -9722.91 | 100% |  | 19673.14 | 0 | 19673.14 | 2013-08-18 | 2015-05-27 | 2013-12-01 | 2014-03-16
75082-DE Kentucky Combustion Turbin | WD101209 | WD101209X | WGS CT 1 Overhaul #2 | 15208.95 |  | 15208.95 | 100% |  | 3160769.66 | 0 | 3160769.66 | 2011-11-11 | 2017-08-21 | 2011-12-01 | 2017-08-12
75082-DE Kentucky Combustion Turbin | WD201207 | WD201207X | WGS CT2 Major C Overhaul No1 | 0 |  | 0 |  |  | 8777822.09 | 0 | 8777822.09 | 2010-09-28 | 2011-09-01 | 2010-11-01 | 2011-08-27
75082-DE Kentucky Combustion Turbin | WD501200 | WD301200X | WGS-CT3 AA Module HVAC Units | 0 |  | 0 |  |  | 20730.67 | 0 | 20730.67 | 2008-10-27 | 2008-12-31 | 2008-12-01 | 2009-02-05
75082-DE Kentucky Combustion Turbin | WD501201 | WD301201X | WGS-CT3 DD Module HVAC Unit | 0 |  | 0 |  |  | 8171.87 | 0 | 8171.87 | 2008-10-27 | 2008-12-31 | 2008-12-01 | 2009-02-05
75082-DE Kentucky Combustion Turbin | WD301204 | WD301204X | WGS CT 3 Overhaul #2 | 0 |  | 0 |  |  | 7682178.86 | 0 | 7682178.86 | 2011-11-11 | 2012-12-31 | 2011-11-01 | 2012-08-23
75082-DE Kentucky Combustion Turbin | WD401201 | WD401201X | WGS CT4 AA MODULE HVAC Units | -5312.33 |  | -5312.33 | 100% |  | 46243.76 | 0 | 46243.76 | 2015-08-02 10:19 | 2015-12-01 | 2015-08-01 | 2016-01-01
75082-DE Kentucky Combustion Turbin | WD401202 | WD401202X | WGS CT4 DD Module HVAC Unit | -628.96 |  | -628.96 | 100% |  | 32057.94 | 0 | 32057.94 | 2015-08-02 00:37 | 2016-02-28 | 2015-08-01 | 2016-02-15
75082-DE Kentucky Combustion Turbin | WD501202 | WD501202X | WGS CT5 Major C Overhaul No2 | 0 |  | 0 |  |  | 7787980.27 | 0 | 7787980.27 | 2009-07-27 | 2010-03-31 | 2009-08-01 | 2010-03-09
75082-DE Kentucky Combustion Turbin | WD601206 | WD601206X | WGS CT6 Major C Overhaul No2 | 0 |  | 0 |  |  | 7960271.15 | 0 | 7960271.15 | 2009-12-22 | 2010-11-18 | 2009-12-01 | 2010-07-29
75082-DE Kentucky Combustion Turbin | WDC00003 | WDC00003X | Woodsdale Repl HVAC System | 119778.26 |  | 119778.26 | 100% |  | 119778.26 | 0 | 119778.26 | 2016-04-12 11:38 | 2016-07-31 | 2016-07-01 | 2016-10-15
75082-DE Kentucky Combustion Turbin | WDC00004 | WDC00004X | Install Fuel Oil System | 160161.57 |  | 160161.57 | 100% |  | 160161.57 | 0 | 160161.57 | 2016-08-22 15:04 | 2019-12-31 | 2016-08-01
75082-DE Kentucky Combustion Turbin | WDC00006 | WDC00006X | Cathodic Protection System Repl | 255427.25 |  | 255427.25 | 100% |  | 255427.25 | 0 | 255427.25 | 2016-01-20 12:00 | 2017-01-31 | 2016-01-01 | 2017-04-24
75082-DE Kentucky Combustion Turbin | WDC01208 | WDC01208X | WGS CT1-6 GEN PROT PANEL REPL | 0 |  | 0 |  |  | 1024162.98 | 0 | 1024162.98 | 2008-09-07 | 2011-12-31 | 2008-09-01 | 2012-03-07
75082-DE Kentucky Combustion Turbin | WDC01210 | WDC01210X | WDC-CAUSTIC TANK REPL | 0 |  | 0 |  |  | 117963.66 | 0 | 117963.66 | 2008-10-12 | 2009-10-25 | 2008-11-01 | 2009-04-08
75082-DE Kentucky Combustion Turbin | WDC01217 | WDC01217X | WGS U1-6 Prop Blr Cntrl Repl | 0 |  | 0 |  |  | 172189.84 | 0 | 172189.84 | 2011-08-23 | 2012-05-01 | 2011-10-01 | 2012-05-08
75082-DE Kentucky Combustion Turbin | WDC01223 | WDC01223X | Propane Piping Upgrade | 0 |  | 0 |  |  | 92648.07 | 0 | 92648.07 | 2008-07-14 | 2008-12-31 | 2008-07-01 | 2008-12-15
75082-DE Kentucky Combustion Turbin | WDC01225 | WDC01225X | WGS Blk Start Controls Cab AC | 0 |  | 0 |  |  | 7263.33 | 0 | 7263.33 | 2009-05-12 | 2009-12-31 | 2009-07-01 | 2009-09-19
75082-DE Kentucky Combustion Turbin | WDC01227 | WDC01227X | Convert WDS Phone Sys to VOIP | -1000 |  | -1000 | 100% |  | 78247.12 | 0 | 78247.12 | 2011-09-13 | 2011-12-31 | 2011-09-01 | 2012-02-18
75082-DE Kentucky Combustion Turbin | WDC01229 | WDC01229X | IT6000 Cyber Security | 0 |  | 0 |  |  | 7406.61 | 0 | 7406.61 | 2009-11-19 | 2009-12-31 | 2009-12-01 | 2010-02-20
75082-DE Kentucky Combustion Turbin | WDC01235 | WDC01235X | Replace Air Compressor B | 0 |  | 0 |  |  | 111830.9 | 0 | 111830.9 | 2010-09-20 | 2011-04-30 | 2010-09-01 | 2011-04-19
75082-DE Kentucky Combustion Turbin | WDC01236 | WDC01236X | Replace Site Radios | 0 |  | 0 |  |  | 71420.41 | 0 | 71420.41 | 2010-11-12 | 2011-12-31 | 2010-12-01 | 2011-12-13
75082-DE Kentucky Combustion Turbin | WDC01237 | WDC01237X | Gas Supply RTU | 0 |  | 0 |  |  | 144852.48 | 0 | 144852.48 | 2012-02-15 | 2013-12-31 | 2012-02-01 | 2014-08-05
75082-DE Kentucky Combustion Turbin | WDC01241 | WDC01241X | Black Start Diesel Generator | 0 |  | 0 |  |  | 2320125.59 | 0 | 2320125.59 | 2011-11-01 | 2013-12-31 | 2011-12-01 | 2013-08-18
75082-DE Kentucky Combustion Turbin | WDC01243 | WDC01243X | UVIR Propane Fire Prot Repl | 0 |  | 0 |  |  | 169784.14 | 0 | 169784.14 | 2012-08-30 | 2013-03-31 | 2012-08-01 | 2013-01-18
75082-DE Kentucky Combustion Turbin | WDC01244 | WDC01244X | Sewer Discharge to Butler Co | 0 |  | 0 |  |  | 911953.83 | 0 | 911953.83 | 2013-03-24 | 2014-08-25 | 2013-03-01 | 2014-11-01
75082-DE Kentucky Combustion Turbin | WDC01245 | WDC01245X | Network Firewall Upgrade | 0 |  | 0 |  |  | 10396.3 | 0 | 10396.3 | 2011-09-06 | 2012-07-27 | 2011-10-01 | 2012-06-29
75082-DE Kentucky Combustion Turbin | WDC01247 | WDC01247X | Woodsdale EAM | 0 |  | 0 |  |  | 596309.5 | 0 | 596309.5 | 2011-06-28 | 2009-10-31 | 2011-06-01 | 2010-01-31
75082-DE Kentucky Combustion Turbin | WDC01248 | WDC01248X | Platform Ladder Swing Gates | 0 |  | 0 |  |  | 88738.57 | 0 | 88738.57 | 2012-12-14 | 2013-12-31 | 2012-12-01 | 2014-01-31
75082-DE Kentucky Combustion Turbin | WDC01250 | WDC01250X | Diesel Fire Pump Controls | 0 |  | 0 |  |  | 17595.12 | 0 | 17595.12 | 2012-04-02 | 2012-09-30 | 2012-04-01 | 2012-04-25
75082-DE Kentucky Combustion Turbin | WDC01251 | WDC01251X | UPS Battery Replacement | -5122.25 |  | -5122.25 | 100% |  | 126953.2 | 0 | 126953.2 | 2012-08-09 | 2012-12-31 | 2012-08-01 | 2012-12-14
75082-DE Kentucky Combustion Turbin | WDC01252 | WDC01252X | Admin Building Roof Replacement | 0 |  | 0 |  |  | 177871.24 | 0 | 177871.24 | 2013-08-18 | 2013-12-31 | 2013-09-01 | 2014-02-15
75082-DE Kentucky Combustion Turbin | WDC01254 | WDC01254X | Stack Lighting Replacement | 0 |  | 0 |  |  | 52374.19 | 0 | 52374.19 | 2013-08-18 | 2015-09-25 | 2013-11-01 | 2014-02-15
75082-DE Kentucky Combustion Turbin | WDC01256 | WDC01256X | NERC CIP V | 116787.92 |  | 116787.92 | 100% |  | 117018.62 | 0 | 117018.62 | 2015-08-11 12:38 | 2016-12-30 | 2015-11-01 | 2017-03-16
75082-DE Kentucky Combustion Turbin | WDC01257 | WDC01257X | WGS - U1-6 EHC System Replacement | -5618.97 |  | -5618.97 | 100% |  | 254485.19 | 0 | 254485.19 | 2013-04-15 | 2015-06-30 | 2013-05-01 | 2015-07-10
75082-DE Kentucky Combustion Turbin | WDC01258 | WDC01258X | IT Uplift Project | 0 |  | 0 |  |  | 67198.36 | 0 | 67198.36 | 2012-12-09 | 2015-03-31 | 2012-12-01 | 2015-03-18
75082-DE Kentucky Combustion Turbin | WDC01260 | WDC01260X | Admin Building HVAC Replacement | -1612.12 |  | -1612.12 | 100% |  | 79591.38 | 0 | 79591.38 | 2014-06-16 | 2015-01-15 | 2014-06-01 | 2015-02-21
75082-DE Kentucky Combustion Turbin | WDC01261 | WDC01261X | Replace CO2 Fire Prot Panels | 431580 |  | 431580 | 100% |  | 786578.39 | 0 | 786578.39 | 2015-12-01 11:46 | 2016-05-30 | 2015-12-01 | 2016-08-28
75082-DE Kentucky Combustion Turbin | WDC01262 | WDC01262X | Security Camera Upgrade | -3200 |  | -3200 | 100% |  | 103184.26 | 0 | 103184.26 | 2013-09-26 | 2014-11-01 | 2013-10-01 | 2014-12-26
75082-DE Kentucky Combustion Turbin | WDC01263 | WDC01263X | Black Start PLC Replacement | 112718.61 |  | 112718.61 | 100% |  | 112718.61 | 0 | 112718.61 | 2016-03-16 11:02 | 2016-11-01 | 2016-04-01 | 2017-01-07
75082-DE Kentucky Combustion Turbin | WDC01266 | WDC01266X | Remote Racking Cart | -200.08 |  | -200.08 | 100% |  | 48711.14 | 0 | 48711.14 | 2015-02-09 | 2015-12-31 | 2015-02-01 | 2016-01-31
75082-DE Kentucky Combustion Turbin | WDC01267 | WDC01267X | IT Site Bandwidth Upgrade | 8378.42 |  | 8378.42 | 100% |  | 85785.51 | 0 | 85785.51 | 2015-05-13 08:49 | 2015-12-31 | 2015-05-01 | 2016-03-05
75082-DE Kentucky Combustion Turbin | WDC01268 | WDC01268X | Data Network Life Cycle Replacement | 20312.73 |  | 20312.73 | 100% |  | 106221.1 | 0 | 106221.1 | 2015-08-02 11:21 | 2016-08-15 | 2015-08-01 | 2016-07-01
75082-DE Kentucky Combustion Turbin | WDCM0017 | WDCM0017X | Main Security Guard House Bldg | 35008.08 |  | 35008.08 | 100% |  | 35008.08 | 0 | 35008.08 | 2016-08-15 09:55 | 2016-12-30 | 2016-09-01 | 2017-03-01
75082-DE Kentucky Combustion Turbin | WDCM1201 | WDCM1201X | RO Membrane Replacement | 0 |  | 0 |  |  | 235492.63 | 0 | 235492.63 | 2012-11-03 | 2013-02-28 | 2012-12-01 | 2013-03-13
75082-DE Kentucky Combustion Turbin | WDCM1205 | WDCM1205X | Station Outside Lighting | -19902.33 |  | -19902.33 | 100% |  | 35147.54 | 0 | 35147.54 | 2013-08-18 | 2014-03-30 | 2013-10-01 | 2014-05-21
75082-DE Kentucky Combustion Turbin | WDCM1206 | WDCM1206X | DC Voltage Monitoring System | -767.38 |  | -767.38 | 100% |  | 151952.18 | 0 | 151952.18 | 2014-04-11 | 2015-03-31 | 2014-05-01 | 2015-09-19
75082-DE Kentucky Combustion Turbin | WDCM1209 | WDCM1209X | SmartGen Installation | 45625.43 |  | 45625.43 | 100% |  | 256108.69 | 0 | 256108.69 | 2015-03-06 09:59 | 2017-12-30 | 2015-04-01
75082-DE Kentucky Combustion Turbin | WDCM1210 | WDCM1210X | Unit 1-3 EHC System Replacement | -2012.11 |  | -2012.11 | 100% |  | 180934.86 | 0 | 180934.86 | 2015-03-05 13:43 | 2015-08-29 | 2015-03-01 | 2015-09-01
75082-DE Kentucky Combustion Turbin | WGS01202 | WGS01202X | WGS CT1-6 WDPF Controls Rplcmt | 0 |  | 0 |  |  | 2093936.21 | 0 | 2093936.21 | 2011-09-08 | 2012-12-31 | 2011-09-01 | 2012-08-18
75082-DE Kentucky Combustion Turbin | WGS01204 | WGS01204X | CT1 6 Egatrol Replacement | 0 |  | 0 |  |  | 3017940.84 | 0 | 3017940.84 | 2010-08-24 | 2012-02-29 | 2010-09-01 | 2012-03-02
75082-DE Kentucky Combustion Turbin | WGS01208 | WGS01208X | Cyber Security | 0 |  | 0 |  |  | 1013820.32 | 0 | 1013820.32 | 2010-09-27 | 2012-02-28 | 2010-10-01 | 2012-03-02
75084-DE Kentucky Power Deliv - Ele | FNINT1096 | 1096BLACK | Blackwell EHS alarm monitoring | 1631.96 |  | 1631.96 | 100% |  | 1631.96 | 0 | 1631.96 | 2015-09-15 11:08 | 2016-02-28 | 2016-03-01 | 2016-06-15
75084-DE Kentucky Power Deliv - Ele | FNINT1096 | 1096BUFF | Buffington EHS alarm monitoring | 5419.82 |  | 5419.82 | 100% |  | 5419.82 | 0 | 5419.82 | 2015-09-15 09:36 | 2016-05-29 | 2016-01-01 | 2016-05-31
75084-DE Kentucky Power Deliv - Ele | FNINT1096 | 1096DONA | Donaldson EPS Station Alarm Monitor | 1221.72 |  | 1221.72 | 100% |  | 1221.72 | 0 | 1221.72 | 2015-09-25 11:59 | 2016-05-02 | 2016-02-01 | 2016-06-02
75084-DE Kentucky Power Deliv - Ele | FNINT1096 | 1096LIMA | Limaburg EHS alarm monitoring | 1948.03 |  | 1948.03 | 100% |  | 1948.03 | 0 | 1948.03 | 2015-09-15 09:43 | 2016-02-28 | 2016-03-01 | 2016-06-15
75084-DE Kentucky Power Deliv - Ele | FNINT1096 | 1096SILV | Silver Grove EHS alarm monitoring | 4780.99 |  | 4780.99 | 100% |  | 4780.99 | 0 | 4780.99 | 2015-09-15 11:13 | 2016-06-01 | 2016-01-01 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | FNINT1096 | 1096WILD | Wilder EHS Alarm Monitoring | 756.32 |  | 756.32 | 100% |  | 756.32 | 0 | 756.32 | 2015-09-15 08:30 | 2016-02-28 | 2016-03-01 | 2016-06-15
75084-DE Kentucky Power Deliv - Ele | CP15BATK | 15BA0019 | Hebron Repl Station Batteries | 0 |  | 0 |  |  | 10458.05 | 0 | 10458.05 | 2015-04-17 12:18 | 2016-03-31 | 2015-06-01 | 2015-11-30
75084-DE Kentucky Power Deliv - Ele | CP16AREK | 16AR03 | Buffington Repl LA's | 38205.78 |  | 38205.78 | 100% |  | 38205.78 | 0 | 38205.78 | 2016-02-18 14:52 | 2017-03-31 | 2016-10-01 | 2017-03-01
75084-DE Kentucky Power Deliv - Ele | CP16AREK | 16AR06 | Richwood Repl TB1 Arrester | 10471.81 |  | 10471.81 | 100% |  | 10471.81 | 0 | 10471.81 | 2016-03-17 16:34 | 2017-03-31 | 2016-03-01 | 2017-02-21
75084-DE Kentucky Power Deliv - Ele | CP16AREK | 16AR12 | Florence Repl TB4 Arresters | 8208.92 |  | 8208.92 | 100% |  | 8208.92 | 0 | 8208.92 | 2016-03-17 16:08 | 2017-03-31 | 2016-03-01 | 2016-12-23
75084-DE Kentucky Power Deliv - Ele | CP16AREK | 16AR13 | Wilder Repl TB2 Arresters | 10154.13 |  | 10154.13 | 100% |  | 10154.13 | 0 | 10154.13 | 2016-03-17 16:53 | 2017-03-31 | 2016-03-01 | 2016-11-15
75084-DE Kentucky Power Deliv - Ele | CP16AREK | 16AR22 | Dixie Repl Cir 41 & 42 Exit Arrest | 3524.05 |  | 3524.05 | 100% |  | 3524.05 | 0 | 3524.05 | 2016-08-25 10:10 | 2017-03-31 | 2016-08-01 | 2016-12-09
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC151 | Beaver Inst Oil Cont | 9018.65 |  | 9018.65 | 100% |  | 9018.65 | 0 | 9018.65 | 2016-08-17 11:30 | 2017-09-01 | 2016-10-01 | 2017-04-20
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC152 | Dayton Inst Oil Cont | 7952.34 |  | 7952.34 | 100% |  | 7952.34 | 0 | 7952.34 | 2016-08-17 11:33 | 2017-09-01 | 2016-10-01 | 2017-05-18
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC153 | Grant Inst Oil Cont | 6497.22 |  | 6497.22 | 100% |  | 6497.22 | 0 | 6497.22 | 2016-08-17 11:37 | 2018-03-01 | 2016-10-01 | 2017-05-13
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC154 | Longbranch Inst Oil Cont | 6754.97 |  | 6754.97 | 100% |  | 6754.97 | 0 | 6754.97 | 2016-08-17 11:42 | 2018-03-01 | 2016-10-01 | 2017-05-23
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC155 | Augustine Inst Oil Cont | 6588 |  | 6588 | 100% |  | 6588 | 0 | 6588 | 2016-08-17 12:02 | 2017-09-01 | 2016-10-01 | 2017-06-15
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC156 | Covington Inst Oil Cont | 7696.16 |  | 7696.16 | 100% |  | 7696.16 | 0 | 7696.16 | 2016-08-17 12:21 | 2018-03-01 | 2016-10-01 | 2017-06-15
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC157 | Dixie Inst Oil Cont | 6373.43 |  | 6373.43 | 100% |  | 6373.43 | 0 | 6373.43 | 2016-08-17 12:24 | 2017-09-01 | 2016-10-01 | 2017-05-14
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC158 | Hands Inst Oil Cont | 109.94 |  | 109.94 | 100% |  | 109.94 | 0 | 109.94 | 2016-08-17 12:26 | 2018-03-31 | 2016-12-01
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC159 | Kenton Inst Oil Cont | 219.85 |  | 219.85 | 100% |  | 219.85 | 0 | 219.85 | 2016-08-17 12:36 | 2018-03-31 | 2016-12-01
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC21 | Claryville Inst Oil Cont Berm | 26319.16 |  | 26319.16 | 100% |  | 26319.16 | 0 | 26319.16 | 2016-04-06 09:03 | 2017-03-31 | 2016-06-01 | 2016-08-31
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC23 | Decoursey Install Oil Cont Berm | 19768.94 |  | 19768.94 | 100% |  | 19768.94 | 0 | 19768.94 | 2016-04-06 09:26 | 2017-03-31 | 2016-08-01 | 2016-09-06
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC25 | Limaburg Install Oil Cont Berm | 30568.22 |  | 30568.22 | 100% |  | 30568.22 | 0 | 30568.22 | 2016-04-06 09:50 | 2017-03-31 | 2016-05-01 | 2016-07-07
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC28 | Marshall Install Oil Cont Berm | 16845.28 |  | 16845.28 | 100% |  | 16845.28 | 0 | 16845.28 | 2016-04-06 10:18 | 2017-03-31 | 2016-05-01 | 2016-08-24
75084-DE Kentucky Power Deliv - Ele | CP16SPCK | 16SPC33 | White Tower Inst Oil Cont Berm | 24395.61 |  | 24395.61 | 100% |  | 24395.61 | 0 | 24395.61 | 2016-04-06 11:29 | 2017-03-31 | 2016-05-01 | 2016-07-20
75084-DE Kentucky Power Deliv - Ele | CP16TBRK | 16TB02 | Bellevue Repl TB1 Bushings | 19427.57 |  | 19427.57 | 100% |  | 19427.57 | 0 | 19427.57 | 2015-12-30 11:47 | 2017-03-31 | 2016-05-01 | 2016-08-06
75084-DE Kentucky Power Deliv - Ele | CP16TBRK | 16TB04 | Florence Repl TB4 Bushings | 6317.35 |  | 6317.35 | 100% |  | 6317.35 | 0 | 6317.35 | 2015-12-30 12:00 | 2017-03-31 | 2016-09-01 | 2016-12-23
75084-DE Kentucky Power Deliv - Ele | F8.4ACRES | 8.4ACRESK | 8.4 ACRES FOR HEBRON SUB-KENTUCKY | 0 |  | 0 |  |  | 61500.18 | 0 | 61500.18 | 2010-07-21 | 2010-10-01 | 2010-07-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 0.49 |  | 0.49 | 100% |  | 12.94 | 0 | 12.94 | 2015-03-30 16:09 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 100555.43 |  | 100555.43 | 100% |  | 118526.08 | 0 | 118526.08 | 2015-03-30 14:59 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 0.41 |  | 0.41 | 100% |  | 10.33 | 0 | 10.33 | 2015-03-30 13:06 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | ARMS | Enable ARM Scheduler Software | 49926.4 |  | 49926.4 | 100% |  | 76759.24 | 0 | 76759.24 | 2015-03-30 14:11 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | RLFA | AT12KY | AT12 & Micro ATO Replace KY | 0 |  | 0 |  |  | 0 | 0 | 0 | 2010-12-22 | 2050-12-31 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C8961 | pp 870018/joe groeschen | 0 |  | 0 |  |  | -449.2 | 0 | -449.2 | 2007-01-03 | 2050-12-31 | 2007-02-01 | 2007-02-01
75084-DE Kentucky Power Deliv - Ele | U14ZKV | C9013 | ULH&P 2005 Capacitors | 0 |  | 0 |  |  | -162705.78 | 0 | -162705.78 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9015 | ULH&P 2005 Government Mandate | 0 |  | 0 |  |  | -42185.33 | 0 | -42185.33 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9021 | ULH&P 2005 New Business | 0 |  | 0 |  |  | -2062970.85 | 0 | -2062970.85 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZRL | C9024 | ULH&P 2005 Reliability | 0 |  | 0 |  |  | -406645.66 | 0 | -406645.66 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 312ZLL | C9025 | ULH&P 2005 Lighting | 0 |  | 0 |  |  | -300872.38 | 0 | -300872.38 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZUR | C9030 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -409635.37 | 0 | -409635.37 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C9034 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -208.67 | 0 | -208.67 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | 314ZLG | C9035 | ULH&P 2005 Load Growth | 0 |  | 0 |  |  | -113979.76 | 0 | -113979.76 | 2007-01-04 | 2007-01-31 | 2007-01-01 | 2007-01-31
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9044 | AMI Wilder Advanced Meter | 38538.65 |  | 38538.65 | 100% |  | 38538.65 | 0 | 38538.65 | 2016-06-28 12:28 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9045 | AMI Donaldson Advanced Meter | 56076.43 |  | 56076.43 | 100% |  | 56076.43 | 0 | 56076.43 | 2016-06-29 07:48 | 2017-09-30 | 2016-06-01 | 2007-11-30
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9047 | AMI Atlas Advanced Metering | 10584 |  | 10584 | 100% |  | 10584 | 0 | 10584 | 2016-06-29 16:13 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9048 | AMI Claryville Advanced Metering | 13528.08 |  | 13528.08 | 100% |  | 13528.08 | 0 | 13528.08 | 2016-06-29 16:19 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9049 | AMI Florence Advance Metering | 76513.9 |  | 76513.9 | 100% |  | 76513.9 | 0 | 76513.9 | 2016-06-29 16:25 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9050 | AMI Villa Advanced Metering | 46440 |  | 46440 | 100% |  | 46440 | 0 | 46440 | 2016-06-29 16:29 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9051 | AMI Dixie Advanced Metering | 12914.43 |  | 12914.43 | 100% |  | 12914.43 | 0 | 12914.43 | 2016-06-29 16:33 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9052 | AMI Buffington Advance Metering | 69301.06 |  | 69301.06 | 100% |  | 69301.06 | 0 | 69301.06 | 2016-06-29 16:36 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | 314G8757 | C9060 | PP872754 DAYTON 42 UNDERGRND | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-01-07 | 2008-12-01 | 2007-08-01 | 2008-05-19
75084-DE Kentucky Power Deliv - Ele | 314G8764 | C9062 | PP872756 DAYTON 43 UNDERGROUND | 0 |  | 0 |  |  | 120235.74 | 0 | 120235.74 | 2007-01-07 | 2008-12-01 | 2008-04-01 | 2008-06-02
75084-DE Kentucky Power Deliv - Ele | 314G8764 | C9063 | PP872757 DAYTON 43 EXITS OH | 0 |  | 0 |  |  | 245210.98 | 0 | 245210.98 | 2007-01-07 | 2008-12-01 | 2007-08-01 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | 314G8867 | C9067 | PP872787 WHITE TOWER 42 | -17122 |  | -17122 | 100% |  | 503691.77 | 0 | 503691.77 | 2007-01-07 | 2008-12-31 | 2007-10-01 | 2008-09-27
75084-DE Kentucky Power Deliv - Ele | 304G8909 | C9068 | PP872798 WHITE TOWER F5967 | 0 |  | 0 |  |  | 75276.69 | 0 | 75276.69 | 2007-01-07 | 2008-12-01 | 2007-03-01 | 2009-04-09
75084-DE Kentucky Power Deliv - Ele | 303G8848 | C9075 | Atlas Sub Repl Regulators | 0 |  | 0 |  |  | 271497.16 | 0 | 271497.16 | 2007-01-10 | 2008-11-15 | 2007-07-01 | 2008-07-10
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9115 | PP 863371/JOE GROESCHEN | 0 |  | 0 |  |  | -2331.3 | 0 | -2331.3 | 2007-01-16 | 2050-12-31 | 2007-01-01 | 2007-03-26
75084-DE Kentucky Power Deliv - Ele | 903G0504 | C9339 | Dixie replace arresters TB2 | 0 |  | 0 |  |  | 6138.14 | 0 | 6138.14 | 2007-02-25 | 2050-12-31 | 2007-05-01 | 2008-02-11
75084-DE Kentucky Power Deliv - Ele | U02Z7993 | C9471 | KY UNIV rep ABS 962 | 0 |  | 0 |  |  | 17071.23 | 0 | 17071.23 | 2007-03-20 | 2050-12-31 | 2007-03-01 | 2007-03-21
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9564 | RI-NO BEND RD FRM I-275 NORTH | 0 |  | 0 |  |  | 11782.24 | 0 | 11782.24 | 2007-04-10 | 2015-04-01 | 2007-04-01 | 2007-11-12
75084-DE Kentucky Power Deliv - Ele | 302G8860 | C9599 | White Tower TB 2 Transmission | 0 |  | 0 |  |  | 80216.74 | 0 | 80216.74 | 2007-04-17 | 2008-05-31 | 2007-05-01 | 2008-05-31
75084-DE Kentucky Power Deliv - Ele | 316H8978 | C9634 | Ft Mitchell Sub Land Sale | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-04-22 | 2010-12-31 | 2008-12-01 | 2010-07-31
75084-DE Kentucky Power Deliv - Ele | U14ZGM | C9664 | RI-ST ELZBTH ACCESS RELO DIST | 0 |  | 0 |  |  | 23075.94 | 0 | 23075.94 | 2007-04-27 | 2012-04-01 | 2007-05-01 | 2008-01-02
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9737 | PP 900903 - JOE FRICKE | 0 |  | 0 |  |  | 45685.81 | 0 | 45685.81 | 2007-05-04 | 2050-12-31 | 2007-08-01 | 2007-09-18
75084-DE Kentucky Power Deliv - Ele | 903G0504 | C9793 | Hands rep bush/arrest TB1 | 0 |  | 0 |  |  | 20303.93 | 0 | 20303.93 | 2007-05-12 | 2050-12-31 | 2007-05-01 | 2007-12-23
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | C9820 | AMI White Tower TB2 Adv Meter | 59557.99 |  | 59557.99 | 100% |  | 59557.99 | 0 | 59557.99 | 2016-04-29 12:16 | 2016-12-30 | 2016-04-01 | 2016-07-31
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9850 | PP 905263 - SANDY CONNLEY | 0 |  | 0 |  |  | 214646.51 | 0 | 214646.51 | 2007-05-20 | 2050-12-31 | 2007-06-01 | 2008-01-08
75084-DE Kentucky Power Deliv - Ele | 316ZBG | C9864 | Cold Springs Site Improvements | 0 |  | 0 |  |  | 40659.35 | 0 | 40659.35 | 2007-05-23 | 2008-07-01 | 2007-06-01 | 2008-03-15
75084-DE Kentucky Power Deliv - Ele | 314ZUR | C9886 | CHELSEA S/O VILLA MADONNA | 0 |  | 0 |  |  | -1382.28 | 0 | -1382.28 | 2007-05-30 | 2012-05-01 | 2007-06-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | U04ZUR | C9887 | CHELSEA S/O VILLA MADONNA-F966 | 0 |  | 0 |  |  | 645.24 | 0 | 645.24 | 2007-05-30 | 2012-05-01 | 2007-06-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | 310ZNB | C9888 | PP 892193/DONNA CARMACK | 0 |  | 0 |  |  | 60160.94 | 0 | 60160.94 | 2007-05-31 | 2050-12-31 | 2007-06-01 | 2007-12-18
75084-DE Kentucky Power Deliv - Ele | UGCIFA | CABINJKY | Underground Cable Injection - KY | 0 |  | 0 |  |  | 1.1369e-12 | 232000 | -232000 | 2011-03-15 | 2015-12-31 | 2011-04-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | CAPAUTOKY | Capacitor Automation - Kentucky | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-01-15 | 2020-12-31 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | CAPKY | Capacitor Inst/Rem | -355.18 |  | -355.18 | 100% |  | 200243.53 | 0 | 200243.53 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | CERTKY | Rel Major Cap T Equip Repl | -6070.82 |  | -6070.82 | 100% |  | 269098.4 | 0 | 269098.4 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FMWCF53SK | CF53AUGUS | Purch Panasonic CF53s repl MDTs | 28216.14 |  | 28216.14 | 100% |  | 281206.85 | 0 | 281206.85 | 2014-08-04 | 2017-03-31 | 2014-09-01 | 2017-03-05
75084-DE Kentucky Power Deliv - Ele | 75084 | CONVRTKYE | Precap Mat'l Conversion - Kentucky | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-02-19 | 2015-12-31 | 2016-02-01 | 2015-07-31
75084-DE Kentucky Power Deliv - Ele | CSFA | CSKY | Circuit Sectionalization | -38536.52 |  | -38536.52 | 100% |  | 25942.58 | 0 | 25942.58 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | CSPFA | CSPKY | Transformer Retrofit | 14400.11 |  | 14400.11 | 100% |  | 168244.25 | 0 | 168244.25 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | D1128 | AMI Thomas More Advance Meter | 10584 |  | 10584 | 100% |  | 10584 | 0 | 10584 | 2016-06-29 16:40 | 2017-12-30 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | 314G8865 | D1309 | PP924061 WHITE TOWER 43 UG | 0 |  | 0 |  |  | 34903.51 | 0 | 34903.51 | 2007-07-31 | 2008-12-31 | 2007-10-01 | 2008-06-27
75084-DE Kentucky Power Deliv - Ele | 314G8867 | D1310 | PP924057 WHITE TOWER 42 UG | 0 |  | 0 |  |  | 46150.46 | 0 | 46150.46 | 2007-07-31 | 2008-12-31 | 2007-10-01 | 2008-06-27
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D1391 | CNSTNCE 42-NIEWHNR RD-UG RECON | 0 |  | 0 |  |  | 65183.82 | 0 | 65183.82 | 2007-08-14 | 2012-08-01 | 2007-08-01 | 2008-12-20
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D1447 | WILDER 45-REMOVE 275 CROSSING | 0 |  | 0 |  |  | 46139.96 | 0 | 46139.96 | 2007-09-02 | 2012-08-01 | 2007-08-01 | 2009-06-25
75084-DE Kentucky Power Deliv - Ele | U04ZGM | D1507 | ri-dolwick rd ginny meyer | 0 |  | 0 |  |  | 52045 | 0 | 52045 | 2007-08-30 | 2050-12-31 | 2009-11-01 | 2003-08-22
75084-DE Kentucky Power Deliv - Ele | U03Z7357 | D1581 | Cold Spring TB9 failure | 0 |  | 0 |  |  | 30159.65 | 0 | 30159.65 | 2007-09-12 | 2050-12-31 | 2007-09-01 | 2007-09-21
75084-DE Kentucky Power Deliv - Ele | 304H9033 | D1596 | PP936435 F965 UPRATE 100 C | -2048.02 |  | -2048.02 | 100% |  | 154283.47 | 0 | 154283.47 | 2007-09-14 | 2011-03-31 | 2009-08-01 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | 302H9041 | D1628 | Kenton Sub Sell Excess Prop | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-09-19 | 2008-12-31 | 2007-09-01 | 2008-01-15
75084-DE Kentucky Power Deliv - Ele | 314G8840 | D1639 | PP938045 COVINGTON 41 OH PART | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-09-20 | 2009-04-30 | 2008-02-01 | 2009-01-28
75084-DE Kentucky Power Deliv - Ele | 314G8840 | D1640 | PP938046 COVINGTON 41 UG PART | 0 |  | 0 |  |  | 890658.52 | 0 | 890658.52 | 2007-09-20 | 2009-04-30 | 2007-11-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8844 | D1641 | PP938072 Covington 42- OH part | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-09-20 | 2008-12-01 | 2008-02-01 | 2009-01-17
75084-DE Kentucky Power Deliv - Ele | 314G8844 | D1642 | PP938073 Covington 42- UG part | 0 |  | 0 |  |  | 214376.63 | 0 | 214376.63 | 2007-09-20 | 2008-12-01 | 2007-12-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | 314G8846 | D1643 | PP938163 Covington 43- OH part | 0 |  | 0 |  |  | 333618.3 | 0 | 333618.3 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-11-14
75084-DE Kentucky Power Deliv - Ele | 314G8846 | D1644 | PP938164 Covington 43- UG part | 0 |  | 0 |  |  | 210161 | 0 | 210161 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-12-01
75084-DE Kentucky Power Deliv - Ele | U16Z7994 | D1697 | Wilder dispose mulsifyer house | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-10-02 | 2008-04-07 | 2010-08-01 | 2007-10-29
75084-DE Kentucky Power Deliv - Ele | 903G7996 | D1716 | Villa rep control battery | 0 |  | 0 |  |  | 3586.35 | 0 | 3586.35 | 2007-10-03 | 2050-12-31 | 2007-10-01 | 2007-11-03
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D1727 | RI-12TH ST RECONST -I-75/SCOTT | 0 |  | 0 |  |  | 120906.9 | 0 | 120906.9 | 2007-10-03 | 2012-10-01 | 2009-02-01 | 2009-12-15
75084-DE Kentucky Power Deliv - Ele | U16Z7994 | D1754 | Kenton replace roof | 0 |  | 0 |  |  | 14429.12 | 18456 | -4026.88 | 2007-10-05 | 2050-12-31 | 2007-11-01 | 2007-12-15
75084-DE Kentucky Power Deliv - Ele | 314ZRL | D1893 | LIMABURG 42-INSTL VOLTG REG | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-10-23 | 2012-10-01 | 2007-10-01 | 2008-01-07
75084-DE Kentucky Power Deliv - Ele | 310ZNB | D1912 | PP 879351 - M Billow | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-10-25 | 2050-12-31 | 2007-11-01 | 2008-03-06
75084-DE Kentucky Power Deliv - Ele | DKY1912 | D1912DS1 | Covington Xtr 2_RUSD - DKY1912 | 56028.54 |  | 56028.54 | 100% |  | 56028.54 | 0 | 56028.54 | 2016-08-19 09:12 | 2018-03-01 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | DKY1929 | D1929RS1 | RUSD Taylor Mill Purch Sub Property | 94.63 |  | 94.63 | 100% |  | 94.63 | 0 | 94.63 | 2016-08-17 13:44 | 2018-03-15 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | DKY1931 | D1931DL1 | AM 10894240 General Drive Part 1 | 11851.74 |  | 11851.74 | 100% |  | 11851.74 | 0 | 11851.74 | 2016-07-29 14:11 | 2018-03-15 | 2016-08-01 | 2017-08-18
75084-DE Kentucky Power Deliv - Ele | DKY1932 | D1932DS1 | Bellevue Upg Dist Cir Rel_RUSD - DK | 39750.71 |  | 39750.71 | 100% |  | 39750.71 | 0 | 39750.71 | 2016-08-19 09:32 | 2018-02-13 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | DKY1959 | D1959RS1 | Cov Sub Add Prop | 78411.33 |  | 78411.33 | 100% |  | 78411.33 | 0 | 78411.33 | 2016-07-29 07:27 | 2017-10-01 | 2016-08-01 | 2017-08-19
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D1970 | RI SR 16-I-275 TO SUBRITE DR | 0 |  | 0 |  |  | 353455.74 | 0 | 353455.74 | 2007-11-01 | 2012-10-01 | 2007-11-01 | 2012-03-29
75084-DE Kentucky Power Deliv - Ele | DKY1973 | D1973DL1 | AM 11028173 York 43 Ln Ext | 2830.18 |  | 2830.18 | 100% |  | 2830.18 | 0 | 2830.18 | 2016-08-17 08:12 | 2017-10-31 | 2016-08-01 | 2017-09-14
75084-DE Kentucky Power Deliv - Ele | TOALOGK | D2063 | Install Sun-Net TOA Kentucky | 0 |  | 0 |  |  | 38944.7 | 0 | 38944.7 | 2007-11-14 | 2010-11-30 | 2008-03-01 | 2010-10-01
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D2085 | RI-HAZELWOOD DR S/O BUTTERMILK | 0 |  | 0 |  |  | 41739.15 | 0 | 41739.15 | 2007-11-16 | 2012-11-01 | 2007-11-01 | 2008-01-13
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D2139 | CRESCENT 42-UG RECONDUCTOR | 0 |  | 0 |  |  | 48020.04 | 0 | 48020.04 | 2007-11-21 | 2012-10-01 | 2007-11-01 | 2009-02-04
75084-DE Kentucky Power Deliv - Ele | EPS100 | D2185 | Erlanger Micro Upgrade | 0 |  | 0 |  |  | 1818 | 0 | 1818 | 2007-12-04 | 2008-02-28 | 2008-02-01 | 2008-01-27
75084-DE Kentucky Power Deliv - Ele | 303H9052 | D2187 | Hebron Install 22/4MVA Xfmr | 0 |  | 0 |  |  | 1497635.9 | 0 | 1497635.9 | 2007-12-04 | 2009-09-01 | 2008-02-01 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | 903G0534 | D2365 | Beaver install switch and CB | 0 |  | 0 |  |  | 212250.69 | 0 | 212250.69 | 2007-12-18 | 2050-12-31 | 2007-12-01 | 2008-02-01
75084-DE Kentucky Power Deliv - Ele | EMSBLSRV | D2508 | MW EMS Blade Server Upgrade | 0 |  | 0 |  |  | 5419.5 | 0 | 5419.5 | 2008-01-10 | 2008-08-30 | 2008-01-01 | 2008-08-30
75084-DE Kentucky Power Deliv - Ele | 314G8867 | D2526 | White Tower 42 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-01-15 | 2008-09-27 | 2008-01-01 | 2008-09-27
75084-DE Kentucky Power Deliv - Ele | 114ZUG | D2553 | pp 966522 RR HARDIN | 0 |  | 0 |  |  | 30263.28 | 0 | 30263.28 | 2008-01-20 | 2050-12-31 | 2008-02-01 | 2009-01-21
75084-DE Kentucky Power Deliv - Ele | 314ZLG | D2740 | COLD SPRING 49 CONVERSION | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-02-05 | 2013-02-01 | 2008-02-01 | 2009-04-06
75084-DE Kentucky Power Deliv - Ele | 310ZNB | D2771 | PP 907295/MICHAEL SMITH | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-02-08 | 2050-12-31 | 2008-02-01 | 2008-10-16
75084-DE Kentucky Power Deliv - Ele | 903G0504 | D2883 | Crescent TB1 rem/inst ETM | 0 |  | 0 |  |  | 5479.14 | 0 | 5479.14 | 2008-02-21 | 2050-12-31 | 2008-04-01 | 2008-05-07
75084-DE Kentucky Power Deliv - Ele | 314H9055 | D2888 | PP974374 HEBRON 45 EXTEND UG | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-02-22 | 2009-09-01 | 2008-08-01 | 2009-09-15
75084-DE Kentucky Power Deliv - Ele | 314H9054 | D2895 | PP974383 HEBRON 44 EXTEND OH | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-02-22 | 2012-12-31 | 2009-05-01 | 2009-09-30
75084-DE Kentucky Power Deliv - Ele | 314H9054 | D2896 | PP974384 HEBRON 44 EXTEND UG | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-02-22 | 2009-09-01 | 2008-07-01 | 2009-09-30
75084-DE Kentucky Power Deliv - Ele | 314H9053 | D2908 | PP974767 HEBRON 43 | 0 |  | 0 |  |  | 365524.39 | 0 | 365524.39 | 2008-02-24 | 2009-09-01 | 2008-06-01 | 2009-10-14
75084-DE Kentucky Power Deliv - Ele | 314G8857 | D2914 | PP974771 WHITE TOWER 41 RECON | 0 |  | 0 |  |  | 276117.72 | 0 | 276117.72 | 2008-02-24 | 2010-09-01 | 2008-07-01 | 2010-10-09
75084-DE Kentucky Power Deliv - Ele | U14ZGM | D3355 | RI-GRAND AVE S/O MEMORIAL PKWY | 0 |  | 0 |  |  | -5.0932e-11 | 0 | -5.0932e-11 | 2008-04-24 | 2013-04-01 | 2008-06-01 | 2010-04-07
75084-DE Kentucky Power Deliv - Ele | 314ZLG | D3389 | CLRYVLLE 42-CNVRT 2/4KV STPDWN | 0 |  | 0 |  |  | 176612.71 | 0 | 176612.71 | 2008-04-30 | 2013-04-01 | 2008-05-01 | 2009-01-26
75084-DE Kentucky Power Deliv - Ele | 303J9130 | D3431 | Richwood TB1 Install Breaker | 0 |  | 0 |  |  | 274597.65 | 0 | 274597.65 | 2008-05-02 | 2009-09-01 | 2008-06-01 | 2009-09-12
75084-DE Kentucky Power Deliv - Ele | 314J9129 | D3435 | PP989939 RICHWOOD 41 LINE REAR | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-05-02 | 2010-01-31 | 2008-06-01 | 2010-02-24
75084-DE Kentucky Power Deliv - Ele | TRLERULH | D3446 | FORKLIFT | 0 |  | 0 |  |  | 34681.99 | 0 | 34681.99 | 2008-05-05 | 2050-12-31 | 2008-06-01 | 2008-10-28
75084-DE Kentucky Power Deliv - Ele | 303G8919 | D3495 | KY Univ Inst New 22/4 MVA Xfmr | 0 |  | 0 |  |  | 2036293.53 | 0 | 2036293.53 | 2008-05-20 | 2010-09-01 | 2008-08-01 | 2010-08-25
75084-DE Kentucky Power Deliv - Ele | 303G8834 | D3543 | Covington Area-new Substation | 0 |  | 0 |  |  | 967769.41 | 0 | 967769.41 | 2008-05-20 | 2009-02-14 | 2008-05-01 | 2008-11-14
75084-DE Kentucky Power Deliv - Ele | C16A7995 | D3550 | Crescent rep dbl doors | 0 |  | 0 |  |  | 21018.96 | 0 | 21018.96 | 2008-05-21 | 2050-12-31 | 2008-12-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | 100FACB4 | D3597 | Upgrade Erlanger Storm System | 0 |  | 0 |  |  | 57417.18 | 0 | 57417.18 | 2008-05-30 | 2008-12-31 | 2008-09-01 | 2008-11-10
75084-DE Kentucky Power Deliv - Ele | 303J9142 | D3694 | Kenton Relocate Driveway | 0 |  | 0 |  |  | 116611.85 | 0 | 116611.85 | 2008-06-16 | 2009-03-31 | 2008-07-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | TOOL002 | D3702 | TIRE CHANGER | 0 |  | 0 |  |  | 6207.56 | 0 | 6207.56 | 2008-06-19 | 2050-12-31 | 2008-07-01 | 2008-12-15
75084-DE Kentucky Power Deliv - Ele | 314ZUR | D3712 | CLARYVL 42-MAIN ST-RT 10-RECON | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-06-20 | 2013-06-01 | 2008-07-01 | 2010-02-24
75084-DE Kentucky Power Deliv - Ele | 314G8917 | D8917DL | AM 8915089 KY University UG | 177670.41 |  | 177670.41 | 100% |  | 180340.79 | 0 | 180340.79 | 2015-10-08 14:59 | 2016-10-29 | 2015-10-01 | 2016-09-27
75084-DE Kentucky Power Deliv - Ele | RLFA | DLSKY | DLine Switches 34.5kv Replace KY | 882.25 |  | 882.25 | 100% |  | 882.25 | 0 | 882.25 | 2014-08-04 | 2020-12-31 | 2016-03-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | DM0029 | Richwood Repl Sta Batt | 0 |  | 0 |  |  | 1684.3 | 0 | 1684.3 | 2015-07-24 10:48 | 2016-01-31 | 2015-08-01 | 2015-11-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | DM0072 | Levi Strauss Repl Tie Switch | 4656.55 |  | 4656.55 | 100% |  | 4656.55 | 0 | 4656.55 | 2016-01-05 13:32 | 2016-05-29 | 2016-01-01 | 2016-05-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | DP0028 | Augustine Repl failed TB5 Xtr | 901.5 |  | 901.5 | 100% |  | 520837.21 | 0 | 520837.21 | 2015-07-07 11:55 | 2016-06-01 | 2015-07-01 | 2015-11-26
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | DP0032 | Augustine Inst 2nd TB 22.4 | 892.9 |  | 892.9 | 100% |  | 892.9 | 0 | 892.9 | 2015-08-17 15:04 | 2018-09-21 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | FLKY0249E | DUKETCKYE | Fleet On-Road Vehicles - elec - KY | 45811.73 |  | 45811.73 | 100% |  | 50375.56 | 0 | 50375.56 | 2009-08-11 | 2050-12-31 | 2015-08-01
75084-DE Kentucky Power Deliv - Ele | FLKY0249E | DUKETEKYE | Fleet Off-Road Vehicles - KY | 0 |  | 0 |  |  | 193531.56 | 0 | 193531.56 | 2009-08-11 | 2050-12-31 | 2010-05-01
75084-DE Kentucky Power Deliv - Ele | NPDLOGMW | E0222 | Midwest Log Aggregation - Ky - HW | 0 |  | 0 |  |  | 14745.6 | 0 | 14745.6 | 2008-07-24 | 2008-12-31 | 2008-07-01 | 2009-02-28
75084-DE Kentucky Power Deliv - Ele | NPDLOGMW | E0234 | Midwest Log Aggregation - Ky - SW | 0 |  | 0 |  |  | 2203.32 | 0 | 2203.32 | 2008-07-24 | 2008-12-31 | 2008-10-01 | 2009-02-28
75084-DE Kentucky Power Deliv - Ele | TDIT | E0857 | EMS OML Kentucky | 0 |  | 0 |  |  | 9123.03 | 0 | 9123.03 | 2008-09-03 | 2009-12-31 | 2008-12-01 | 2010-03-14
75084-DE Kentucky Power Deliv - Ele | TRLERULH | E0933 | Erlanger ATV | 0 |  | 0 |  |  | 11770 | 0 | 11770 | 2008-09-09 | 2008-11-30 | 2008-10-01 | 2008-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | E1227 | Storm 12 - Ike (Kentucky) | 0 |  | 0 |  |  | 219722.62 | 0 | 219722.62 | 2008-09-19 | 2050-12-31 | 2008-09-01 | 2008-12-18
75084-DE Kentucky Power Deliv - Ele | OPTIMALC | E1235 | Project Optimization Sftwr-Ky | 0 |  | 0 |  |  | 12896.77 | 0 | 12896.77 | 2008-09-22 | 2010-12-31 | 2008-10-01 | 2009-07-31
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA | E1551 | Wilder - Replace Battery | 0 |  | 0 |  |  | 11727.24 | 0 | 11727.24 | 2008-10-08 | 2050-07-10 | 2009-05-01 | 2009-08-23
75084-DE Kentucky Power Deliv - Ele | RELDFA | E1613 | PP#924827 9Sanitati District #1 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-10-13 | 2009-03-31 | 2008-10-01 | 2007-12-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | E1614 | PP#949527 Sanitation District #1 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-10-13 | 2009-03-31 | 2008-10-01 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | FOKY0082 | E1673 | Kenton Install Electric Fence | 0 |  | 0 |  |  | 1593.78 | 0 | 1593.78 | 2008-10-15 | 2008-12-31 | 2008-10-01 | 2008-10-29
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E1833 | Augustine Repl TB5 Bushings | 0 |  | 0 |  |  | 15264.71 | 0 | 15264.71 | 2008-10-22 | 2050-07-08 | 2008-10-01 | 2009-01-24
75084-DE Kentucky Power Deliv - Ele | PILCFA | E1881 | NKU -Customer Switchgear | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-10-24 | 2009-06-01 | 2008-11-01 | 2009-09-19
75084-DE Kentucky Power Deliv - Ele | 303ZANLG | E1995 | Hebron Analog to Digital | 0 |  | 0 |  |  | 11503.48 | 0 | 11503.48 | 2008-10-30 | 2010-03-31 | 2009-01-01 | 2009-07-16
75084-DE Kentucky Power Deliv - Ele | 314H9053 | E1996 | HEBRON 43 -Install Conduit & Cable | 0 |  | 0 |  |  | 359675.59 | 0 | 359675.59 | 2008-10-30 | 2009-09-01 | 2008-12-01 | 2009-10-14
75084-DE Kentucky Power Deliv - Ele | TDIT | E2272 | EMS MH Standby Enhancement - Ky | 0 |  | 0 |  |  | 4289.25 | 0 | 4289.25 | 2008-11-12 | 2010-12-31 | 2008-12-01 | 2011-02-28
75084-DE Kentucky Power Deliv - Ele | RELDFA | E3613 | PP#1038389 S FT THOMAS AVE @ RIVER | 0 |  | 0 |  |  | 71990.4 | 0 | 71990.4 | 2009-01-14 | 2010-12-31 | 2009-01-01 | 2010-04-30
75084-DE Kentucky Power Deliv - Ele | 303G8919 | E3752 | Wilder Sub Retire DT Equipment | 0 |  | 0 |  |  | -1.5916e-12 | 0 | -1.5916e-12 | 2009-01-21 | 2010-12-01 | 2009-12-01 | 2010-09-18
75084-DE Kentucky Power Deliv - Ele | 303G8919 | E3753 | Silver Grove Sub Retire DT Equip | 0 |  | 0 |  |  | -3.7517e-12 | 0 | -3.7517e-12 | 2009-01-21 | 2010-12-01 | 2009-12-01 | 2010-09-03
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | E3824 | Pole Repl Gnd Line-T | 0 |  | 0 |  |  | 53058 | 0 | 53058 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | MOFA | E3825 | Major Outage Followup-D | 0 |  | 0 |  |  | 0 | 0 | 0 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | PILCFA | E3829 | UG Cable Repl-PILC | 0 |  | 0 |  |  | 0 | 0 | 0 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | REGFA | E3832 | Regulator Inst/Rem | 0 |  | 0 |  |  | 0 | 0 | 0 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | SCFOFA | E3836 | System Capacity-FO | 0 |  | 0 |  |  | 0 | 0 | 0 | 2009-01-22 | 2009-05-01 | 2009-01-01 | 2009-05-07
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4062 | Crescent-Repl Arr & Bushings in TB1 | 0 |  | 0 |  |  | 11703.28 | 0 | 11703.28 | 2009-02-03 | 2010-12-31 | 2009-02-01 | 2010-06-24
75084-DE Kentucky Power Deliv - Ele | ORDFA | E4291 | STORM 1 - 2009 - CAPITAL | 0 |  | 0 |  |  | 0 | 0 | 0 | 2009-02-12 | 2009-06-01 | 2009-02-01 | 2009-03-01
75084-DE Kentucky Power Deliv - Ele | ITKY0157 | E4303 | MDT Toughbooks - Ky | 0 |  | 0 |  |  | 218435.18 | 0 | 218435.18 | 2009-02-12 | 2009-10-31 | 2009-04-01 | 2010-02-28
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4340 | Cold Spring rep HS arresters on TB1 | 0 |  | 0 |  |  | 3407.68 | 0 | 3407.68 | 2009-02-13 | 2010-03-01 | 2009-03-01 | 2010-02-09
75084-DE Kentucky Power Deliv - Ele | NUMARAT | E4634 | EMS NUMARA - KY | 0 |  | 0 |  |  | 5551.02 | 0 | 5551.02 | 2009-03-02 | 2009-09-30 | 2009-03-01 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E4816 | Empire - Install LTC Oil Filtration | 0 |  | 0 |  |  | 10212.88 | 0 | 10212.88 | 2009-03-11 | 2010-12-31 | 2009-11-01 | 2010-02-17
75084-DE Kentucky Power Deliv - Ele | TDIT | E5392 | EMS SQL Cluster Infrastruc - KY | 0 |  | 0 |  |  | 9055.89 | 0 | 9055.89 | 2009-04-07 | 2009-11-30 | 2009-04-01 | 2010-03-28
75084-DE Kentucky Power Deliv - Ele | ITMW0195 | E5745 | Pole Inspection Replacement - KY | 0 |  | 0 |  |  | 81403.21 | 0 | 81403.21 | 2009-04-21 | 2011-04-30 | 2009-04-01 | 2011-12-31
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E5944 | Cold Spring - Repl Recloser | 0 |  | 0 |  |  | 4300.9 | 0 | 4300.9 | 2009-04-28 | 2009-12-30 | 2009-07-01 | 2009-07-24
75084-DE Kentucky Power Deliv - Ele | 314G8914 | E6225 | KY Univ 43 New Feeder | 0 |  | 0 |  |  | 10689.14 | 0 | 10689.14 | 2009-05-07 | 2010-10-01 | 2009-05-01
75084-DE Kentucky Power Deliv - Ele | 314G8914 | E6226 | KY Univ 43 UG Cable and Conduit | 0 |  | 0 |  |  | 1382283.91 | 0 | 1382283.91 | 2009-05-07 | 2010-10-01 | 2009-05-01 | 2010-10-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | E6464 | Claryville - Repl Voltage Regulator | 0 |  | 0 |  |  | 12505.6 | 0 | 12505.6 | 2009-05-19 | 2009-12-30 | 2009-05-01 | 2009-08-19
75084-DE Kentucky Power Deliv - Ele | UGCRFA | E6865 | PP#1068539 DERBY RIDGE APTS RECOND | 0 |  | 0 |  |  | 0 | 72432 | -72432 | 2009-06-04 | 2009-12-31 | 2009-07-01 | 2009-12-17
75084-DE Kentucky Power Deliv - Ele | UGCRFA | E6908 | PP#1068609 COUNTRY SQUIRE ESTATES | 0 |  | 0 |  |  | 0 | 83042 | -83042 | 2009-06-05 | 2010-06-01 | 2009-07-01 | 2010-02-19
75084-DE Kentucky Power Deliv - Ele | AMKY0036 | E7672 | Wilder 40 PILC Cable Replacement | 0 |  | 0 |  |  | 0 | 0 | 0 | 2009-07-10 | 2010-06-01 | 2009-09-01 | 2010-02-19
75084-DE Kentucky Power Deliv - Ele | AMKY0035 | E9944 | Augustine 42 Dist OH Reconductor | -2741.16 |  | -2741.16 | 100% |  | 34765.43 | 0 | 34765.43 | 2009-09-03 | 2010-05-31 | 2009-10-01 | 2010-06-09
75084-DE Kentucky Power Deliv - Ele | AMKY0035 | E9945 | Augustine 42 PILC Cable Replacement | 0 |  | 0 |  |  | 436906.32 | 0 | 436906.32 | 2009-09-03 | 2010-05-31 | 2009-09-01 | 2010-06-09
75084-DE Kentucky Power Deliv - Ele | FENABLEH | ECOMH | Enable ECOM Data Hub | 157.5 |  | 157.5 | 100% |  | 157.5 | 0 | 157.5 | 2015-09-29 09:53 | 2017-10-31 | 2016-01-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | ECOMS | Enable ECOM Data Hub Software | 35749.93 |  | 35749.93 | 100% |  | 41387.69 | 0 | 41387.69 | 2015-03-30 15:05 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLEH | EGISH | Enable EGIS Hardware | 302 |  | 302 | 100% |  | 885.18 | 0 | 885.18 | 2015-03-30 15:31 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | EGISS | Enable EGIS Software | 231993.08 |  | 231993.08 | 100% |  | 329028.76 | 0 | 329028.76 | 2015-03-30 14:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FEGISSYNK | EGISSYNKE | EGIS TO SYNERGEE INTERFACE | 0 |  | 0 |  |  | 47109.73 | 0 | 47109.73 | 2011-01-27 | 2011-09-30 | 2011-02-01 | 2011-11-22
75084-DE Kentucky Power Deliv - Ele | RCLFA | ELASTIMOL | Elastimold e-recloser pilot | 0 |  | 0 |  |  | 55832.08 | 0 | 55832.08 | 2012-09-06 | 2014-03-31 | 2012-09-01 | 2014-02-01
75084-DE Kentucky Power Deliv - Ele | 75084 | EMETERKY | Electric Meter Blanket | 465629.84 |  | 465629.84 | 100% |  | 766833.33 | 0 | 766833.33 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01
75084-DE Kentucky Power Deliv - Ele | FEMPCSITK | EMPCSITK | EMPCS CAOS/W2K8 R2 KENTUCKY | 0 |  | 0 |  |  | 2498.64 | 0 | 2498.64 | 2010-08-04 | 2010-08-30 | 2010-09-01 | 2011-02-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | EMR005 | Crescent Repl Bus Roof Bushings | 26296.17 |  | 26296.17 | 100% |  | 26296.17 | 0 | 26296.17 | 2016-02-12 13:43 | 2017-03-31 | 2016-03-01 | 2017-02-12
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | EMR020 | Limaburg Repl PH A Regulator | 23556.11 |  | 23556.11 | 100% |  | 23556.11 | 0 | 23556.11 | 2016-03-01 13:57 | 2017-03-31 | 2016-03-01 | 2016-06-03
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | EMR047 | White Tower Repl Cir41 Reg | 93937.04 |  | 93937.04 | 100% |  | 93937.04 | 0 | 93937.04 | 2016-04-07 08:32 | 2017-03-31 | 2016-04-01 | 2016-12-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | EMR131 | Hebron Repl PhA Bus Discnt Switch | 4859.85 |  | 4859.85 | 100% |  | 4859.85 | 0 | 4859.85 | 2016-07-26 07:04 | 2017-03-31 | 2016-08-01 | 2016-11-26
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | EMR132 | Beaver Repl Ph A Regulator | 22580.5 |  | 22580.5 | 100% |  | 22580.5 | 0 | 22580.5 | 2016-07-26 07:23 | 2017-03-31 | 2016-08-01 | 2017-02-10
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | EMR173 | Wilder Repl failed bushings | 439.43 |  | 439.43 | 100% |  | 439.43 | 0 | 439.43 | 2016-09-13 11:41 | 2018-03-31 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | EMR248 | Dixie Repl RTU Processor | 5396.1 |  | 5396.1 | 100% |  | 5396.1 | 0 | 5396.1 | 2016-11-09 15:17 | 2018-03-31 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | FEMSUPGRD | EMSUPGRVS | EMS EMP 2.6 UPGRADE PROJECT | 0 |  | 0 |  |  | 210750.47 | 0 | 210750.47 | 2011-03-30 | 2014-06-30 | 2011-09-01 | 2014-06-30
75084-DE Kentucky Power Deliv - Ele | FENABLES | ENABLETDG | ENABLETDG Clearing Project | 388203.09 |  | 388203.09 | 100% |  | 542627.84 | 0 | 542627.84 | 2015-05-12 14:57 | 2017-10-31 | 2015-05-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | EXPDH | Enable Expert Designer Hardware | 2.79 |  | 2.79 | 100% |  | 73.12 | 0 | 73.12 | 2015-03-30 13:46 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | EXPDS | Enable Expert Designer Software | 36938.29 |  | 36938.29 | 100% |  | 63398.83 | 0 | 63398.83 | 2015-03-30 14:25 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0244 | EKP-138kv Interconn-Webster R/W | 0 |  | 0 |  |  | -8.5129e-12 | 0 | -8.5129e-12 | 2009-09-15 | 2011-10-01 | 2011-03-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0245 | F6282-Loop thru Webster Ring Bus | 0 |  | 0 |  |  | 1856.61 | 0 | 1856.61 | 2009-09-15 | 2011-10-01 | 2009-09-01 | 2011-08-10
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0246 | Silver Grove Repl F6282 relays | 0 |  | 0 |  |  | 5210.7 | 0 | 5210.7 | 2009-09-15 | 2011-10-01 | 2010-02-01 | 2011-09-04
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0265 | Buffington Repl F6282 relays | 0 |  | 0 |  |  | 5.8209e-13 | 0 | 5.8209e-13 | 2009-09-15 | 2011-10-01 | 2009-12-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F0304 | Hands Sub Inst TB2 Transrupter | 0 |  | 0 |  |  | -2.9097e-12 | 0 | -2.9097e-12 | 2009-09-16 | 2011-10-01 | 2009-10-01 | 2011-09-04
75084-DE Kentucky Power Deliv - Ele | UGCRFA | F0709 | PP#1088919 URD 104 | 0 |  | 0 |  |  | 148789.21 | 163914.64 | -15125.43 | 2009-09-25 | 2010-12-31 | 2009-12-01 | 2010-10-07
75084-DE Kentucky Power Deliv - Ele | 903H8407X | F0824 | Alexandria Sub - Land | 0 |  | 0 |  |  | 544000 | 0 | 544000 | 2009-09-30 | 2009-09-30 | 2009-09-01 | 2001-09-30
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | F1085 | Crescent -Repl Ckt 1587 Direct Trip | 0 |  | 0 |  |  | 16412.23 | 0 | 16412.23 | 2009-10-09 | 2010-03-01 | 2009-12-01 | 2010-03-17
75084-DE Kentucky Power Deliv - Ele | AMKY0290 | F2324 | Aug 44 Extension, Conv Latonia C | 0 |  | 0 |  |  | 198422.01 | 0 | 198422.01 | 2009-11-18 | 2010-09-01 | 2009-12-01 | 2010-09-15
75084-DE Kentucky Power Deliv - Ele | FSRVCO201 | F3205 | ASSET MGMT OPT-KENTUCKY | 0 |  | 0 |  |  | 17905.67 | 0 | 17905.67 | 2009-12-17 | 2010-09-01 | 2009-12-01 | 2009-07-04
75084-DE Kentucky Power Deliv - Ele | PRDFA | F3394 | CHARGING 2009 BKTS to SPEC-KENTUCKY | 0 |  | 0 |  |  | 233994.57 | 0 | 233994.57 | 2009-12-22 | 2009-12-31 | 2009-12-01 | 2010-03-31
75084-DE Kentucky Power Deliv - Ele | AMKY0087 | F3404 | Dry Ridge 41 Reconductor | 0 |  | 0 |  |  | 344598.36 | 0 | 344598.36 | 2009-12-22 | 2011-06-01 | 2010-04-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FPTLOADKE | F3706 | PTLOAD-TOOL TO RATE TRNSF-KENTUCKY | 0 |  | 0 |  |  | 13342.02 | 0 | 13342.02 | 2010-01-05 | 2010-10-31 | 2010-03-01 | 2011-03-08
75084-DE Kentucky Power Deliv - Ele | RELDFA | F3824 | eMax#213832 Ky 237 Camp Ernst-Pleas | 0 |  | 0 |  |  | 179894.38 | 0 | 179894.38 | 2010-01-08 | 2015-01-06 | 2010-01-01 | 2010-10-07
75084-DE Kentucky Power Deliv - Ele | X02U8310 | F4206 | Buffington - Replace CB 682 | 0 |  | 0 |  |  | 273166.29 | 170830 | 102336.29 | 2010-01-19 | 2012-03-31 | 2011-01-01 | 2012-02-11
75084-DE Kentucky Power Deliv - Ele | UGCRFA | F5109 | eMax#395612 AMSTERDAM VILLAGE | 0 |  | 0 |  |  | 113614.48 | 124734.81 | -11120.33 | 2010-02-09 | 2010-12-31 | 2010-03-01 | 2010-10-28
75084-DE Kentucky Power Deliv - Ele | AMKY0126 | F5724 | Kenton Repl F6282 Carrier | 0 |  | 0 |  |  | 2.6193e-12 | 0 | 2.6193e-12 | 2010-02-23 | 2011-10-31 | 2010-04-01 | 2011-08-21
75084-DE Kentucky Power Deliv - Ele | FSRVCO201 | F5864 | PLS-CADD TO EMAX INTEGRATION | 0 |  | 0 |  |  | 21383.16 | 0 | 21383.16 | 2010-02-25 | 2010-11-30 | 2010-02-01 | 2010-02-28
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | F7484 | EMAX#523406 Crescent 43 Reliability | 0 |  | 0 |  |  | 30288.5 | 0 | 30288.5 | 2010-04-23 | 2010-12-31 | 2010-06-01 | 2011-02-06
75084-DE Kentucky Power Deliv - Ele | RELDFA | F7846 | RI-Industrial Rd-Dixie to Turkeyfot | 0 |  | 0 |  |  | 96927.03 | 0 | 96927.03 | 2010-04-27 | 2013-03-31 | 2010-05-01 | 2012-08-20
75084-DE Kentucky Power Deliv - Ele | RELDFA | F8924 | EMAX #585031 Johns Hill Rd | 0 |  | 0 |  |  | 243710.6 | 0 | 243710.6 | 2010-06-01 | 2013-04-01 | 2010-06-01 | 2012-10-31
75084-DE Kentucky Power Deliv - Ele | RELDFA | F9264 | EMAX #462348 31 Eastern Avenue | 0 |  | 0 |  |  | 111543.39 | 0 | 111543.39 | 2010-06-08 | 2010-12-31 | 2010-06-01 | 2010-12-21
75084-DE Kentucky Power Deliv - Ele | RELDFA | F9407 | EMAX 613555 RI-Taylor Mil Rd Recon | -186318.09 |  | -186318.09 | 100% |  | 828543.6 | 0 | 828543.6 | 2010-06-10 | 2012-05-31 | 2010-06-01 | 2012-02-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | F9524 | Marshall rep VR 41 phase1 | 0 |  | 0 |  |  | 10240.99 | 0 | 10240.99 | 2010-06-15 | 2010-08-18 | 2010-06-01 | 2010-09-16
75084-DE Kentucky Power Deliv - Ele | DETCONFA | F9909 | Old 17 & Hempling Deteriorated Cond | 0 |  | 0 |  |  | 50277.92 | 0 | 50277.92 | 2010-06-25 | 2012-10-31 | 2010-07-01 | 2012-03-29
75084-DE Kentucky Power Deliv - Ele | RLFA | FMSWGRR | Florence Mall Sw-gear Repl Program | 0 |  | 0 |  |  | 0 | 0 | 0 | 2013-01-29 | 2015-12-31 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | FNCTOFF | PD Indirect Offset | -0.06 |  | -0.06 | 100% |  | -2.13 | 0 | -2.13 | 2008-07-01 | 2008-06-28 21:34 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FFOOTPRNT | FOOTPRNSW | Footprints Upgrade Project | 3224.69 |  | 3224.69 | 100% |  | 3224.69 | 0 | 3224.69 | 2016-08-12 15:50 | 2017-08-15 | 2016-09-01 | 2017-08-23
75084-DE Kentucky Power Deliv - Ele | FRMRE12RR | FRM12INFR | 2012 COMM REPL INFRASTR-KEN | 0 |  | 0 |  |  | 156869.34 | 0 | 156869.34 | 2012-05-02 | 2014-04-30 | 2012-05-01 | 2014-05-31
75084-DE Kentucky Power Deliv - Ele | FRMRE13RR | FRM13INFR | 2013 PD COMM REPL INFRA-KENT | 0 |  | 0 |  |  | 169659.36 | 0 | 169659.36 | 2013-02-22 | 2015-07-30 | 2013-03-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0124 | Donaldson replace control batteries | 0 |  | 0 |  |  | 9962.83 | 0 | 9962.83 | 2010-07-06 | 2010-09-30 | 2010-08-01 | 2010-11-17
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G0125 | Beaver replace voltage regulator | 0 |  | 0 |  |  | 10229.64 | 0 | 10229.64 | 2010-07-06 | 2010-12-31 | 2010-07-01 | 2010-10-03
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0267 | Whites Tower 41 Sec 2 Hempfling Rd | 0 |  | 0 |  |  | 29428.7 | 0 | 29428.7 | 2010-07-08 | 2012-06-15 | 2010-09-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0268 | Whites Tower 41 Madison Pk | 0 |  | 0 |  |  | 42418.71 | 0 | 42418.71 | 2010-07-08 | 2012-07-31 | 2010-07-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0269 | Whites Tower 41 Sec 1 Madison Pk | 0 |  | 0 |  |  | 39341.78 | 0 | 39341.78 | 2010-07-08 | 2012-07-31 | 2010-11-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0270 | Whites Tower 41 Sec 2 Madison Pk | 0 |  | 0 |  |  | 25828.63 | 0 | 25828.63 | 2010-07-08 | 2012-07-31 | 2010-11-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | AMOH0389 | G0347 | Augustine | 0 |  | 0 |  |  | 19869.34 | 0 | 19869.34 | 2010-07-13 | 2011-03-31 | 2010-08-01 | 2010-12-16
75084-DE Kentucky Power Deliv - Ele | AMOH0389 | G0348 | Donaldson | 0 |  | 0 |  |  | 28793.65 | 0 | 28793.65 | 2010-07-13 | 2011-03-31 | 2010-09-01 | 2010-12-14
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G0397 | Wilder replace drive | 0 |  | 0 |  |  | 12308.24 | 0 | 12308.24 | 2010-08-31 | 2010-12-31 | 2010-10-01 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0425 | Hempfling Rd e/o Madison Sec 3 | 0 |  | 0 |  |  | 27144.97 | 0 | 27144.97 | 2010-07-14 | 2012-07-31 | 2010-07-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0529 | Old Madison Pk & Pony Dr Det Cond | 0 |  | 0 |  |  | 816.97 | 0 | 816.97 | 2010-07-20 | 2010-12-31 | 2010-09-01 | 2011-01-04
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0530 | Gleason Rd & Madison Pk Det Cond | 0 |  | 0 |  |  | 77346.52 | 0 | 77346.52 | 2010-07-20 | 2012-07-31 | 2010-09-01 | 2012-03-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G0531 | Spillman & Madison Pk Det Cond | 0 |  | 0 |  |  | 3789.54 | 0 | 3789.54 | 2010-07-21 | 2010-12-31 | 2010-10-01 | 2011-02-24
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G0660 | RELIABILITY - DECLARED CIRCUIT CRES | 0 |  | 0 |  |  | 17836.89 | 0 | 17836.89 | 2010-08-06 | 2010-12-31 | 2010-08-01 | 2011-03-20
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0670 | Alexandria S repl control batteries | 0 |  | 0 |  |  | 2117.18 | 0 | 2117.18 | 2010-08-10 | 2010-12-31 | 2010-08-01 | 2010-12-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0691 | Buffington install LTC filter | 0 |  | 0 |  |  | 6753.79 | 0 | 6753.79 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2010-12-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0696 | Constance install LTC filter | 0 |  | 0 |  |  | 7681.26 | 0 | 7681.26 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2011-01-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0701 | Wilder install LTC filter | 0 |  | 0 |  |  | 9788.56 | 0 | 9788.56 | 2010-08-11 | 2010-12-31 | 2010-08-01 | 2010-12-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0732 | Grant repl station control battery | 0 |  | 0 |  |  | 1116.77 | 0 | 1116.77 | 2010-08-12 | 2010-12-30 | 2010-09-01 | 2010-12-14
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G0734 | Marshall replace reclosers | 0 |  | 0 |  |  | 2399.15 | 0 | 2399.15 | 2010-08-13 | 2010-12-31 | 2010-08-01 | 2010-11-16
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G0763 | DECLARED CIRCUIT CRESCENT "43" | 0 |  | 0 |  |  | 111432.32 | 0 | 111432.32 | 2010-08-18 | 2011-01-11 | 2010-08-01 | 2011-03-06
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G0819 | Alexandria South replace sidewalk | 0 |  | 0 |  |  | 4984.1 | 0 | 4984.1 | 2010-08-30 | 2010-12-31 | 2010-09-01 | 2010-11-24
75084-DE Kentucky Power Deliv - Ele | AMKY0326 | G0849 | Augustine 43 TP for Repl Cable | -858.68 |  | -858.68 | 100% |  | 41245.38 | 0 | 41245.38 | 2010-09-01 | 2011-09-30 | 2011-03-01 | 2011-06-10
75084-DE Kentucky Power Deliv - Ele | AMKY0326 | G0852 | Augustine 43 PILC Cable Replacement | 0 |  | 0 |  |  | 167386.29 | 0 | 167386.29 | 2010-09-01 | 2011-09-30 | 2010-10-01 | 2011-06-14
75084-DE Kentucky Power Deliv - Ele | RELDFA | G0973 | EMAX #1009228 Taylor Mill Reconst | 0 |  | 0 |  |  | 21838.71 | 0 | 21838.71 | 2010-09-14 | 2015-06-30 | 2010-09-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1158 | Oakbrook repl TB 1 X3 bushing | 0 |  | 0 |  |  | 7121.45 | 0 | 7121.45 | 2010-09-30 | 2012-06-15 | 2010-12-01 | 2013-04-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1261 | Villa inst LTC filter on TB 1 | 0 |  | 0 |  |  | 15975.45 | 0 | 15975.45 | 2010-10-07 | 2012-06-15 | 2010-10-01 | 2012-08-11
75084-DE Kentucky Power Deliv - Ele | 107DSTOH | G1407 | ROLLUP PLH IK_KY_2008 | 0 |  | 0 |  |  | 4300519.49 | 0 | 4300519.49 | 2010-10-27 | 2010-03-31 | 2010-10-01 | 2010-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1416 | ROLLUP PLH IK_KY_2009 | 0 |  | 0 |  |  | 1508495.94 | 0 | 1508495.94 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2009-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1419 | ROLLUP PLH IK_KY_2007 | 0 |  | 0 |  |  | 6127147.35 | 0 | 6127147.35 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2008-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1420 | ROLLUP PLH IK_KY_2006 | 0 |  | 0 |  |  | 7382097.31 | 0 | 7382097.31 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2007-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1421 | ROLLUP PLH IK_KY_2005 | 0 |  | 0 |  |  | 3720153.83 | 0 | 3720153.83 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2006-03-31
75084-DE Kentucky Power Deliv - Ele | RLFA | G1422 | ROLLUP PLH IK_KY_2004 | 0 |  | 0 |  |  | 2349020.4 | 0 | 2349020.4 | 2010-10-28 | 2050-12-31 | 2010-10-01 | 2005-03-31
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1434 | EMAX 1347776 Constance 42 Decl Circ | 0 |  | 0 |  |  | 20086.8 | 0 | 20086.8 | 2010-11-01 | 2011-12-31 | 2010-11-01 | 2011-11-19
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1435 | EMAX 1347974 Crescent 44 Decl Circ | 0 |  | 0 |  |  | 84108.61 | 0 | 84108.61 | 2010-11-01 | 2013-03-31 | 2010-11-01 | 2013-01-15
75084-DE Kentucky Power Deliv - Ele | FFLDMTREQ | G1528 | REPL OF FIELD METER TEST EQUIP | 0 |  | 0 |  |  | 65356.9 | 0 | 65356.9 | 2010-11-18 | 2012-03-31 | 2011-12-01 | 2012-06-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G1558 | EMAX 1417885 15 Spiral Dr | 0 |  | 0 |  |  | 74303.72 | 0 | 74303.72 | 2010-11-29 | 2012-04-30 | 2011-05-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1561 | Claryville TB 2,3 replace fans | 0 |  | 0 |  |  | 4408.9 | 0 | 4408.9 | 2010-11-29 | 2011-05-31 | 2011-01-01 | 2011-05-01
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1562 | Kentucky Univ TB 4 replace fans | 0 |  | 0 |  |  | 11272.01 | 0 | 11272.01 | 2010-11-29 | 2011-08-31 | 2011-01-01 | 2011-05-16
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1563 | Limaburg TB 2 replace fans | 0 |  | 0 |  |  | 5044.69 | 0 | 5044.69 | 2010-11-29 | 2011-08-31 | 2011-01-01 | 2011-05-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1564 | Marshall TB 1 replace fans | 0 |  | 0 |  |  | 5611.87 | 0 | 5611.87 | 2010-11-29 | 2011-12-31 | 2011-01-01 | 2011-09-29
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G1654 | EMAX 1549494 15 Spiral Dr | 0 |  | 0 |  |  | 21078.52 | 0 | 21078.52 | 2010-12-13 | 2011-12-31 | 2011-05-01 | 2011-12-08
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G1661 | EMAX 1786573 URD 184 Richwood | 0 |  | 0 |  |  | 415673.18 | 585415.78 | -169742.6 | 2010-12-15 | 2013-03-31 | 2010-12-01 | 2011-07-29
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G1662 | Dayton install drainage system | 0 |  | 0 |  |  | 3853.99 | 0 | 3853.99 | 2010-12-15 | 2011-03-31 | 2010-12-01 | 2011-03-11
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1670 | Crescent TB 2 replace ETM | 0 |  | 0 |  |  | 10782.08 | 0 | 10782.08 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1671 | Dixie TB2 replace ETM | 0 |  | 0 |  |  | 6817.04 | 0 | 6817.04 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-15
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1672 | Hands TB 1 replace ETM | 0 |  | 0 |  |  | 7187.2 | 0 | 7187.2 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-19
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1675 | Wilder TB 3 replace ETM | 0 |  | 0 |  |  | 10922.24 | 0 | 10922.24 | 2010-12-15 | 2011-12-31 | 2011-02-01 | 2011-10-21
75084-DE Kentucky Power Deliv - Ele | RLFA | G1729 | ROLLUP PLH IK_KY_2010_BLKT_Rollup | 0 |  | 0 |  |  | 7488699.49 | 0 | 7488699.49 | 2010-12-22 | 2050-12-31 | 2010-12-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G1756 | EMAX 1696749 Constance 42 Decl Circ | -905.21 |  | -905.21 | 100% |  | 23582.5 | 0 | 23582.5 | 2011-01-04 | 2013-03-31 | 2011-01-01 | 2012-08-07
75084-DE Kentucky Power Deliv - Ele | AMKY0412 | G1816 | Wilder 44 PILC Cable Replace | 0 |  | 0 |  |  | 42551.42 | 0 | 42551.42 | 2011-01-10 | 2011-10-31 | 2011-03-01 | 2011-06-29
75084-DE Kentucky Power Deliv - Ele | AMKY0412 | G1817 | Wilder 44 PILC Install Cable | 0 |  | 0 |  |  | 77317.2 | 0 | 77317.2 | 2011-01-10 | 2011-10-31 | 2011-02-01 | 2011-06-29
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G1950 | Buffington TB 3 replace bushing | 0 |  | 0 |  |  | 5339.87 | 0 | 5339.87 | 2011-01-24 | 2012-06-15 | 2011-04-01 | 2012-02-05
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2194 | EMAX 1737953 NKU Univ Dr Ext | 0 |  | 0 |  |  | 9571.1 | 0 | 9571.1 | 2011-02-08 | 2014-09-08 | 2011-02-01 | 2013-02-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G2222 | Donaldson TB 1 replace fans | 0 |  | 0 |  |  | 3698.38 | 0 | 3698.38 | 2011-02-09 | 2011-12-31 | 2011-03-01 | 2011-06-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G2254 | Decoursey replace reclosers | 0 |  | 0 |  |  | 2235.41 | 0 | 2235.41 | 2011-02-11 | 2011-05-31 | 2011-02-01 | 2011-05-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G2301 | Decoursey TB 3 failure | 0 |  | 0 |  |  | 33472.65 | 0 | 33472.65 | 2011-02-15 | 2011-04-30 | 2011-02-01 | 2011-05-24
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2456 | EMAX 1983805 RI-Hands Pk w/o KY 16 | 0 |  | 0 |  |  | 66191.75 | 0 | 66191.75 | 2011-03-01 | 2015-02-01 | 2011-03-01 | 2011-08-16
75084-DE Kentucky Power Deliv - Ele | RELDFA | G2535 | EMAX 1783672 7660 Turfway Rd | 0 |  | 0 |  |  | 73189.28 | 0 | 73189.28 | 2011-03-04 | 2012-03-31 | 2011-03-01 | 2012-02-04
75084-DE Kentucky Power Deliv - Ele | FEMSUPGRD | G2860 | EMS EMP 2.6 UPGRADE PROJECT | 0 |  | 0 |  |  | 64278.93 | 0 | 64278.93 | 2011-03-30 | 2014-06-30 | 2011-07-01 | 2014-06-30
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G2918 | EMAX 2176614 Viewpoint Dr | 0 |  | 0 |  |  | 189414.82 | 0 | 189414.82 | 2011-04-05 | 2012-12-31 | 2011-04-01 | 2012-08-17
75084-DE Kentucky Power Deliv - Ele | AMKY0474 | G2953 | Constance Install TLS | 0 |  | 0 |  |  | 255060.57 | 0 | 255060.57 | 2011-04-07 | 2012-09-01 | 2011-04-01 | 2012-04-18
75084-DE Kentucky Power Deliv - Ele | AMKY0474 | G2957 | Villa F2862 Reclosing | 0 |  | 0 |  |  | 35714.36 | 0 | 35714.36 | 2011-04-08 | 2012-03-31 | 2011-06-01 | 2012-02-07
75084-DE Kentucky Power Deliv - Ele | FAUTODESK | G3197 | AUTODESK 2012 UPGRADE | 0 |  | 0 |  |  | 10289.91 | 0 | 10289.91 | 2011-05-02 | 2011-09-30 | 2011-05-01 | 2012-02-09
75084-DE Kentucky Power Deliv - Ele | AMKY0088 | G3276 | Mt Zion Rd Reconductor 2 | 0 |  | 0 |  |  | 250891.08 | 0 | 250891.08 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-05-14
75084-DE Kentucky Power Deliv - Ele | AMKY0088 | G3277 | Mt Zion Rd Reconductor 2 (RLE) | 0 |  | 0 |  |  | 708.64 | 0 | 708.64 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-03-01
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3363 | Kenton Repl Circuit 45 Cable | 0 |  | 0 |  |  | 4132.92 | 0 | 4132.92 | 2011-05-17 | 2012-09-30 | 2011-07-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3364 | Kenton 45 PILC Cable Replace OH | 0 |  | 0 |  |  | 109847.67 | 0 | 109847.67 | 2011-05-17 | 2012-09-30 | 2012-10-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | AMKY0328 | G3365 | Kenton 45 PILC Cable Replace UG | -104.68 |  | -104.68 | 100% |  | 27306.71 | 0 | 27306.71 | 2011-05-17 | 2012-09-30 | 2011-09-01 | 2012-07-27
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G3647 | EMAX 2346184 URD 105 Country Squire | 0 |  | 0 |  |  | 99612.1 | 119746.44 | -20134.34 | 2011-06-10 | 2013-03-31 | 2011-06-01 | 2012-04-19
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3700 | Claryville Recloser Replace | 0 |  | 0 |  |  | 465838.15 | 0 | 465838.15 | 2011-06-16 | 2013-03-31 | 2011-07-01 | 2012-09-02
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G3736 | EMAX 2374342 Crescent 44 Decl circ | 0 |  | 0 |  |  | 14220.23 | 0 | 14220.23 | 2011-06-21 | 2014-03-31 | 2011-08-01 | 2013-07-15
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3757 | Wilder F5962 Reclosing | 0 |  | 0 |  |  | 15848.51 | 0 | 15848.51 | 2011-06-22 | 2013-03-31 | 2011-11-01 | 2012-09-26
75084-DE Kentucky Power Deliv - Ele | AMKY0086 | G3773 | Claryville Inst Auto Throw Over | 0 |  | 0 |  |  | 97596.89 | 0 | 97596.89 | 2011-06-23 | 2013-03-31 | 2011-07-01 | 2012-09-26
75084-DE Kentucky Power Deliv - Ele | X02U8885 | G3793 | Wilder Replace CB 650 | 0 |  | 0 |  |  | 199403.84 | 147094 | 52309.84 | 2011-06-24 | 2013-03-31 | 2011-11-01 | 2013-03-18
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G3813 | EMAX 2389938 Oakbrook 41 Det | 0 |  | 0 |  |  | 52381.75 | 0 | 52381.75 | 2011-06-27 | 2011-12-31 | 2011-07-01 | 2012-02-02
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3956 | Constance 41-44 Circuits | 0 |  | 0 |  |  | 454677.69 | 0 | 454677.69 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-04-27
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3957 | Crescent 41-44 Circuits | 0 |  | 0 |  |  | 182951.42 | 0 | 182951.42 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-07-13
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3958 | Villa Sub 41-44 Circuits | 0 |  | 0 |  |  | 427855.42 | 0 | 427855.42 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-09-08
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G3959 | Kenton Circuits 41-46 | 0 |  | 0 |  |  | 223038.02 | 0 | 223038.02 | 2011-07-06 | 2012-09-01 | 2011-07-01 | 2012-05-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4004 | Bellevue TB2 Install LTC Filter | 0 |  | 0 |  |  | 11027.59 | 0 | 11027.59 | 2011-07-11 | 2012-03-31 | 2011-07-01 | 2012-03-10
75084-DE Kentucky Power Deliv - Ele | 314G8900 | G4034 | Aug 44 Ext Conv Latonia 4kV | 0 |  | 0 |  |  | 665967.65 | 0 | 665967.65 | 2011-07-13 | 2012-04-30 | 2011-07-01 | 2012-04-28
75084-DE Kentucky Power Deliv - Ele | AMKY0085 | G4117 | Wilder 13.2kV Bus | 0 |  | 0 |  |  | 2332545.27 | 0 | 2332545.27 | 2011-07-21 | 2014-03-31 | 2012-06-01 | 2013-08-09
75084-DE Kentucky Power Deliv - Ele | FEGIS/EMX | G4142 | EGIS/eMAX PD DEVICE INTEGRATION | 0 |  | 0 |  |  | 12059.65 | 0 | 12059.65 | 2011-07-22 | 2012-10-30 | 2011-07-01 | 2012-09-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4167 | Florence TB 2 instal LTC & 2 fans | 0 |  | 0 |  |  | 11201.45 | 0 | 11201.45 | 2011-07-26 | 2011-12-31 | 2011-07-01 | 2012-03-03
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G4174 | Donaldson TB 2 instl LTC filter | 0 |  | 0 |  |  | 11099.84 | 0 | 11099.84 | 2011-07-27 | 2012-06-15 | 2011-07-01 | 2012-03-17
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G4175 | Kenton replace control battery | 0 |  | 0 |  |  | 15190.97 | 0 | 15190.97 | 2011-07-27 | 2011-12-31 | 2011-08-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G4179 | Kenton resurface entire pavement | 0 |  | 0 |  |  | 6032.09 | 0 | 6032.09 | 2011-07-27 | 2011-12-31 | 2011-11-01 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | FEMSFIREW | G4243 | EMS FIREWALL PROJ HW KENTUCKY | 0 |  | 0 |  |  | 988.52 | 0 | 988.52 | 2011-08-01 | 2012-04-01 | 2011-12-01 | 2012-07-31
75084-DE Kentucky Power Deliv - Ele | NBFA | G4362 | EMAX 2432584 Envision Center | 0 |  | 0 |  |  | 18126.21 | 0 | 18126.21 | 2011-08-08 | 2012-03-31 | 2011-08-01 | 2012-01-25
75084-DE Kentucky Power Deliv - Ele | AMKY0515 | G4465 | Villa Install F2862 TLS | 0 |  | 0 |  |  | 43036.46 | 0 | 43036.46 | 2011-08-12 | 2012-09-01 | 2011-10-01 | 2012-09-08
75084-DE Kentucky Power Deliv - Ele | RELTFA | G4535 | EMAX 2523185 Barnes Pike | 0 |  | 0 |  |  | 59.52 | 0 | 59.52 | 2011-08-18 | 2012-12-31 | 2011-09-01 | 2012-04-12
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G4599 | Wilder Repl 138kV CB No. 834 | 0 |  | 0 |  |  | 82257.49 | 0 | 82257.49 | 2011-08-23 | 2011-12-16 | 2011-09-01 | 2011-11-26
75084-DE Kentucky Power Deliv - Ele | AMOH0424 | G4604 | 345kV Distr Clearance Capital (KY) | 0 |  | 0 |  |  | 1111.39 | 0 | 1111.39 | 2011-08-24 | 2012-09-01 | 2012-02-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G4633 | EMAX 2541613 Richwood 41 Det Cond | 0 |  | 0 |  |  | 7686.57 | 0 | 7686.57 | 2011-08-26 | 2012-04-30 | 2011-09-01 | 2012-03-04
75084-DE Kentucky Power Deliv - Ele | CSFA | G4676 | EMAX 2550566 G&W Viper Recloser | -170.88 |  | -170.88 | 100% |  | 74062.26 | 0 | 74062.26 | 2011-08-30 | 2012-08-31 | 2011-09-01 | 2012-02-17
75084-DE Kentucky Power Deliv - Ele | FITRNFCSK | G4864 | REPL INTEGR-ITRON FCS-KENT. | 0 |  | 0 |  |  | 41470.26 | 0 | 41470.26 | 2011-09-08 | 2012-12-31 | 2011-09-01 | 2013-02-12
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G4874 | Augustine Repl sta batteries | 0 |  | 0 |  |  | 13416.11 | 0 | 13416.11 | 2011-09-09 | 2012-03-31 | 2011-10-01 | 2012-01-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G5009 | White Tower Repl reclosers on c 41 | 0 |  | 0 |  |  | 1957.04 | 0 | 1957.04 | 2011-09-19 | 2011-12-30 | 2015-09-01 | 2011-12-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5013 | Florence Install LTC filter on TB 1 | 0 |  | 0 |  |  | 10672.06 | 0 | 10672.06 | 2011-09-20 | 2012-03-31 | 2011-09-01 | 2012-02-09
75084-DE Kentucky Power Deliv - Ele | AMKY0528 | G5038 | Grant 43 City of Williamstown | 0 |  | 0 |  |  | 1218.2 | 0 | 1218.2 | 2011-09-21 | 2012-10-01 | 2011-09-01 | 2012-10-24
75084-DE Kentucky Power Deliv - Ele | FMDT11KE | G5048 | MOBILE DISPATCH EXPANSION-KE | 0 |  | 0 |  |  | 37648.52 | 0 | 37648.52 | 2011-09-22 | 2012-09-30 | 2011-10-01 | 2012-12-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5463 | Constance instl LTC filter on TB 2 | 0 |  | 0 |  |  | 7380.68 | 0 | 7380.68 | 2011-10-25 | 2012-09-30 | 2011-12-01 | 2012-04-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5484 | Augustine instl LTC filter on TB 1 | 0 |  | 0 |  |  | 7080.51 | 0 | 7080.51 | 2011-10-26 | 2012-09-30 | 2011-12-01 | 2012-07-03
75084-DE Kentucky Power Deliv - Ele | RELDFA | G5515 | EMAX 2690060 377 Richwood Rd | 0 |  | 0 |  |  | 169.42 | 0 | 169.42 | 2011-10-27 | 2012-03-31 | 2011-11-01 | 2012-02-17
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5700 | Claryville repl X0,X1,X2,X3 bushing | 0 |  | 0 |  |  | 3910.89 | 0 | 3910.89 | 2011-11-07 | 2012-09-30 | 2011-12-01 | 2012-08-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G5800 | Hands repl cooling fans on TB 1 | 0 |  | 0 |  |  | 14912.34 | 0 | 14912.34 | 2011-11-14 | 2012-07-01 | 2011-12-01 | 2012-04-10
75084-DE Kentucky Power Deliv - Ele | NBFA | G5853 | EMAX 2516744 South Service Rd | 0 |  | 0 |  |  | 32109.43 | 0 | 32109.43 | 2011-11-16 | 2012-12-31 | 2011-12-01 | 2012-08-21
75084-DE Kentucky Power Deliv - Ele | RELDFA | G5905 | EMAX 2760735 Camp Ernst (KY 237) | 0 |  | 0 |  |  | 83348.65 | 0 | 83348.65 | 2011-11-21 | 2012-12-31 | 2012-02-01 | 2012-08-18
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G5938 | Thomas More remove eye wash station | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-11-23 | 2012-03-16 | 2014-04-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G5939 | Covington remove eye wash station | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-11-23 | 2012-03-16 | 2015-07-01 | 2012-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6108 | Blackwell Sub security system | 0 |  | 0 |  |  | 82686.31 | 0 | 82686.31 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6109 | Buffington Sub security system | 0 |  | 0 |  |  | 146449.24 | 0 | 146449.24 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G6112 | Silver Grove sub security system | 0 |  | 0 |  |  | 149197.11 | 0 | 149197.11 | 2011-12-08 | 2013-03-31 | 2011-12-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | CSFA | G6457 | EMAX 2834098 Second feed to UG syst | 0 |  | 0 |  |  | 84137.86 | 0 | 84137.86 | 2012-01-11 | 2013-03-31 | 2012-01-01 | 2012-05-17
75084-DE Kentucky Power Deliv - Ele | RELTFA | G6487 | EMAX 2876458 RI-Turkeyfoot Rd | 0 |  | 0 |  |  | 108634.47 | 0 | 108634.47 | 2012-01-16 | 2013-03-31 | 2012-01-01 | 2012-09-07
75084-DE Kentucky Power Deliv - Ele | NBFA | G6517 | EMAX 2869082 Post Glover Co | 0 |  | 0 |  |  | 18957.6 | 0 | 18957.6 | 2012-01-19 | 2012-12-31 | 2012-02-01 | 2012-06-29
75084-DE Kentucky Power Deliv - Ele | AMKY0571 | G6550 | Augustine 41 PILC Cable Replace | 0 |  | 0 |  |  | 1289624.24 | 0 | 1289624.24 | 2012-01-24 | 2013-03-31 | 2012-02-01 | 2013-02-28
75084-DE Kentucky Power Deliv - Ele | NBFA | G6573 | EMAX 2920684 15 Spiral Dr | 0 |  | 0 |  |  | 11667.36 | 0 | 11667.36 | 2012-01-26 | 2012-12-31 | 2012-03-01 | 2012-06-27
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G6611 | Dixie replace cooling fans TB 1 | 0 |  | 0 |  |  | 7584.18 | 0 | 7584.18 | 2012-01-30 | 2012-07-01 | 2012-02-01 | 2012-05-15
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | G6619 | KY Dist Line Assoc w 138kV CLR | 0 |  | 0 |  |  | 619233.04 | 0 | 619233.04 | 2012-01-30 | 2015-03-31 | 2013-01-01 | 2014-04-15
75084-DE Kentucky Power Deliv - Ele | RELDFA | G6642 | EMAX 2943027 KY 16 | 0 |  | 0 |  |  | 393948.82 | 0 | 393948.82 | 2012-02-02 | 2013-03-31 | 2012-02-01 | 2012-12-12
75084-DE Kentucky Power Deliv - Ele | FBLDENCLO | G6683 | CCA/NON-CCA ENCLOSURE | 0 |  | 0 |  |  | 3421.65 | 0 | 3421.65 | 2012-02-06 | 2012-03-15 | 2012-02-01 | 2012-08-23
75084-DE Kentucky Power Deliv - Ele | CERTFA | G6716 | F2862 Emergency R/P switch 547 | 0 |  | 0 |  |  | 53352.23 | 0 | 53352.23 | 2012-02-08 | 2013-03-31 | 2012-02-01 | 2012-05-08
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G6751 | EMAX 1334817 Dixie Hwy Crescent 43 | -553.49 |  | -553.49 | 100% |  | 18880.61 | 0 | 18880.61 | 2012-02-14 | 2013-03-31 | 2012-09-01 | 2012-12-12
75084-DE Kentucky Power Deliv - Ele | RELDFA | G6791 | EMAX 2880825 Turkeyfoot Rd Dist | 37021.42 |  | 37021.42 | 100% |  | 46436.73 | 0 | 46436.73 | 2012-02-16 | 2013-06-30 | 2012-03-01 | 2012-09-07
75084-DE Kentucky Power Deliv - Ele | AMKY0570 | G6835 | West End 1524 Aerial on Bridge (OH) | 0 |  | 0 |  |  | 483279.82 | 0 | 483279.82 | 2012-02-21 | 2013-03-31 | 2012-03-01 | 2012-12-21
75084-DE Kentucky Power Deliv - Ele | FMDT11KE | G6983 | MWMS USER SW LICENSES | 0 |  | 0 |  |  | 3598.06 | 0 | 3598.06 | 2012-03-08 | 2012-06-30 | 2012-06-01 | 2012-09-05
75084-DE Kentucky Power Deliv - Ele | AMKY0729 | G7002 | Dayton KY Sub Purch 825 Walnut -RLE | 0 |  | 0 |  |  | 140420.41 | 0 | 140420.41 | 2012-03-12 | 2013-03-31 | 2012-03-01 | 2013-02-02
75084-DE Kentucky Power Deliv - Ele | FTDITKY | G7195 | CC BLKT IT HW-ERLANGER, KE OP CTR | 0 |  | 0 |  |  | 15422.26 | 0 | 15422.26 | 2012-04-10 | 2012-06-24 | 2012-05-01
75084-DE Kentucky Power Deliv - Ele | AMKY0668 | G7206 | Wilder 43 Cable | 0 |  | 0 |  |  | 12864.89 | 0 | 12864.89 | 2012-04-12 | 2013-03-31 | 2012-07-01 | 2013-01-26
75084-DE Kentucky Power Deliv - Ele | AMKY0668 | G7210 | Wilder 43 PILC Replacement | 0 |  | 0 |  |  | 30891.12 | 0 | 30891.12 | 2012-04-12 | 2013-03-31 | 2012-10-01 | 2013-01-26
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G7235 | Wilder repl CCVT & line tuner | 0 |  | 0 |  |  | 20303.82 | 0 | 20303.82 | 2012-04-13 | 2013-01-31 | 2012-04-01 | 2013-01-18
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7273 | Buffington - KY SEL Dist Ckt Imprv | 0 |  | 0 |  |  | 438957.48 | 0 | 438957.48 | 2012-04-17 | 2014-03-31 | 2012-04-01 | 2013-02-20
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7274 | Donaldson KY SEL Dist Ckt Imprv | 0 |  | 0 |  |  | 229859.22 | 0 | 229859.22 | 2012-04-17 | 2015-03-31 | 2012-05-01 | 2014-09-14
75084-DE Kentucky Power Deliv - Ele | AMKY0699 | G7275 | Dixie KY SEL Dist Ckt Imprv | 0 |  | 0 |  |  | 246233.02 | 0 | 246233.02 | 2012-04-17 | 2014-03-31 | 2012-04-01 | 2013-06-15
75084-DE Kentucky Power Deliv - Ele | FSRVCOM12 | G7280 | SUBSTATION DESIGN SOLUTION | 0 |  | 0 |  |  | 89527.8 | 0 | 89527.8 | 2012-04-18 | 2011-07-01 | 2012-05-01 | 2011-06-25
75084-DE Kentucky Power Deliv - Ele | X03U8875 | G7392 | Donaldson TB1 TB2 Transrupters | 0 |  | 0 |  |  | 252759.6 | 248446 | 4313.6 | 2012-05-02 | 2015-03-31 | 2012-05-01 | 2014-09-14
75084-DE Kentucky Power Deliv - Ele | X03U9003 | G7393 | Florence TB1 TB2 TB4 | 0 |  | 0 |  |  | 662220 | 320573 | 341647 | 2012-05-02 | 2015-03-31 | 2012-05-01 | 2015-01-14
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G7406 | Silver Grove install ETM on TB 23 | 0 |  | 0 |  |  | 18593.04 | 0 | 18593.04 | 2012-05-04 | 2012-11-30 | 2012-05-01 | 2012-10-13
75084-DE Kentucky Power Deliv - Ele | 303G8901 | G7533 | Latonia Sub - Retire & Remove | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-05-15 | 2014-03-31 | 2014-08-01 | 2013-09-06
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7624 | Buffington replace ETM on TB 2 | 0 |  | 0 |  |  | 14778.92 | 0 | 14778.92 | 2012-05-22 | 2013-03-31 | 2012-07-01 | 2012-10-25
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7630 | Buffington replace ETM TB 7 | 0 |  | 0 |  |  | 18129.78 | 0 | 18129.78 | 2012-05-23 | 2013-03-31 | 2012-07-01 | 2012-11-02
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G7631 | Buffington replace ETM TB 4 | 0 |  | 0 |  |  | 11288.6 | 0 | 11288.6 | 2012-05-23 | 2013-03-31 | 2012-07-01 | 2012-10-26
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G7646 | Buffington H2 bushing changeout TB3 | 0 |  | 0 |  |  | -328.26 | 0 | -328.26 | 2012-05-24 | 2012-08-31 | 2012-05-01 | 2012-08-24
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G7835 | Grant replace CB 211 after failure | 0 |  | 0 |  |  | 8290.23 | 0 | 8290.23 | 2012-06-12 | 2012-12-22 | 2012-06-01 | 2012-11-16
75084-DE Kentucky Power Deliv - Ele | FCAORMRPL | G8039 | CAORM REPLACEMENT PROJ. | 0 |  | 0 |  |  | 1.0658e-14 | 0 | 1.0658e-14 | 2012-07-11 | 2013-08-30 | 2012-08-01 | 2013-09-25
75084-DE Kentucky Power Deliv - Ele | AMKY0750 | G8124 | Line Capacitor Installs for KY 2012 | 0 |  | 0 |  |  | 44560.81 | 0 | 44560.81 | 2012-07-27 | 2013-03-31 | 2012-08-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8336 | Crescent Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 8564.79 | 0 | 8564.79 | 2012-08-27 | 2014-03-31 | 2012-10-01 | 2013-12-06
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8338 | Kenton Upgrage Frame Relay Equip | 0 |  | 0 |  |  | 13966.48 | 0 | 13966.48 | 2012-08-27 | 2014-03-31 | 2012-10-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8339 | Long Branch Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 32120.9 | 0 | 32120.9 | 2012-08-27 | 2014-03-31 | 2012-11-01 | 2013-07-17
75084-DE Kentucky Power Deliv - Ele | ITKYFR12D | G8340 | Oakbrook Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 29745.64 | 0 | 29745.64 | 2012-08-27 | 2014-03-31 | 2012-11-01 | 2014-01-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8347 | Wilder repl H1 bushing TB 3 | 0 |  | 0 |  |  | 7261.43 | 0 | 7261.43 | 2012-08-28 | 2012-12-28 | 2012-09-01 | 2013-03-06
75084-DE Kentucky Power Deliv - Ele | RELDFA | G8369 | RI emax 2836864 Madison Ave | 0 |  | 0 |  |  | 42948.78 | 0 | 42948.78 | 2012-08-30 | 2015-05-07 | 2012-09-01 | 2015-03-12
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8409 | Limaburg Sub security system | 0 |  | 0 |  |  | 58231.92 | 0 | 58231.92 | 2012-09-06 | 2013-09-30 | 2012-09-01 | 2014-08-31
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8416 | Claryville TB2 Bank failure | 0 |  | 0 |  |  | 22979.54 | 0 | 22979.54 | 2012-09-10 | 2012-12-28 | 2012-09-01 | 2012-12-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8420 | Donaldson Sub security system | 0 |  | 0 |  |  | 50345.99 | 0 | 50345.99 | 2012-09-10 | 2013-03-31 | 2012-09-01 | 2014-02-28
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | G8423 | Wilder Sub security system | 0 |  | 0 |  |  | 102608.81 | 0 | 102608.81 | 2012-09-10 | 2013-03-31 | 2012-09-01 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | G8553 | ST emax 2178946 John Hills Rd NKU | 0 |  | 0 |  |  | 48605 | 0 | 48605 | 2012-10-01 | 2014-03-15 | 2012-11-01 | 2013-06-05
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G8576 | Wilder rem fence & instl animal fen | 0 |  | 0 |  |  | 351875.96 | 0 | 351875.96 | 2012-10-03 | 2013-03-07 | 2012-10-01 | 2013-03-21
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8589 | Claryville CIR 42 repl Phase A VR | 0 |  | 0 |  |  | 12895.47 | 0 | 12895.47 | 2012-10-05 | 2013-01-19 | 2012-10-01 | 2013-01-10
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8666 | Buffington TB 1 Cooler Replacement | 0 |  | 0 |  |  | 209704.63 | 0 | 209704.63 | 2012-10-15 | 2014-03-01 | 2013-01-01 | 2014-02-10
75084-DE Kentucky Power Deliv - Ele | NBFA | G8713 | NB emax 3478683 1780 Anderson Blvd | 0 |  | 0 |  |  | 17799.34 | 0 | 17799.34 | 2012-10-22 | 2013-10-30 | 2013-01-01 | 2013-06-04
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | G8780 | Decoursey CIR 41 repl 3 reclosers | 0 |  | 0 |  |  | 4358.34 | 0 | 4358.34 | 2012-11-01 | 2013-02-02 | 2012-11-01 | 2013-02-02
75084-DE Kentucky Power Deliv - Ele | AMKY0592 | G8851 | Wilder Replace DE KY CB741 | 0 |  | 0 |  |  | 237224.92 | 0 | 237224.92 | 2012-11-07 | 2015-03-31 | 2012-11-01 | 2015-02-07
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8885 | Limaburg repl HS bushings&LAs TB 2 | 0 |  | 0 |  |  | 18866.47 | 0 | 18866.47 | 2012-11-12 | 2013-09-28 | 2013-02-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G8886 | Limaburg repl HS LAs&LS bushingsTB1 | 0 |  | 0 |  |  | 12132.74 | 0 | 12132.74 | 2012-11-12 | 2013-12-27 | 2013-02-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | FTIMPHAII | G8986 | TIM PHASE II UPGRADE | 0 |  | 0 |  |  | 301140.04 | 0 | 301140.04 | 2012-11-26 | 2014-12-30 | 2012-12-01 | 2014-06-24
75084-DE Kentucky Power Deliv - Ele | RLFA | G9018 | NW emax 3205166 18th & Banklick | 0 |  | 0 |  |  | 42809.67 | 0 | 42809.67 | 2012-12-03 | 2014-03-31 | 2012-12-01 | 2013-06-24
75084-DE Kentucky Power Deliv - Ele | RELDFA | G9056 | RI emax 2760735 Camp Ernst (KY 237) | 0 |  | 0 |  |  | 537669.43 | 0 | 537669.43 | 2012-12-06 | 2013-09-07 | 2012-12-01 | 2013-06-02
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9064 | Wilder CB650 repl 2 bus disconnects | 0 |  | 0 |  |  | 40410.24 | 0 | 40410.24 | 2012-12-10 | 2013-12-30 | 2013-10-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | UGCRFA | G9111 | CR emax 3705007 Heritage Trails | 0 |  | 0 |  |  | 108295.1 | 85982.93 | 22312.17 | 2012-12-18 | 2015-06-30 | 2013-04-01 | 2014-01-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G9113 | Bellevue TB 1 repl HS arresters | 0 |  | 0 |  |  | 5681.9 | 0 | 5681.9 | 2012-12-18 | 2013-09-28 | 2013-02-01 | 2013-08-15
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9117 | Wilder repl pos 1&5 bushings CB831 | 0 |  | 0 |  |  | 12011.82 | 0 | 12011.82 | 2012-12-19 | 2013-06-29 | 2013-03-01 | 2013-06-18
75084-DE Kentucky Power Deliv - Ele | RELDFA | G9119 | RI emax 3707725 5th to 8th | 0 |  | 0 |  |  | 4138.93 | 0 | 4138.93 | 2012-12-19 | 2014-10-09 | 2012-12-01 | 2014-09-04
75084-DE Kentucky Power Deliv - Ele | AVAMARUPG | G9122 | EMPCS-AVAMAR UPGRADE | 0 |  | 0 |  |  | 140465.13 | 0 | 140465.13 | 2012-12-19 | 2013-05-30 | 2012-12-01 | 2013-07-31
75084-DE Kentucky Power Deliv - Ele | FESXIUPGR | G9133 | EMPCS-ESXI UPGRADE | 0 |  | 0 |  |  | 8288.7 | 0 | 8288.7 | 2012-12-20 | 2013-09-30 | 2012-12-01 | 2013-12-25
75084-DE Kentucky Power Deliv - Ele | FDOMSIMPL | G9136 | DOMS IMPLEMENTATION W/AMI | 1374.26 |  | 1374.26 | 100% |  | 10718.62 | 0 | 10718.62 | 2012-12-20 | 2017-03-31 | 2013-01-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | TPEQUIPFA | G9139 | Florence repl sw,motor,whip ABS859 | 0 |  | 0 |  |  | 45937.86 | 0 | 45937.86 | 2012-12-26 | 2013-12-27 | 2013-02-01 | 2014-03-13
75084-DE Kentucky Power Deliv - Ele | ITKYFR13D | G9165 | Hebron Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 29302.18 | 0 | 29302.18 | 2013-01-03 | 2014-09-01 | 2013-05-01 | 2013-10-10
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9171 | DC emax 3744831 Kenton 42 Decl | 0 |  | 0 |  |  | 43651.73 | 0 | 43651.73 | 2013-01-03 | 2014-03-31 | 2013-01-01 | 2013-07-09
75084-DE Kentucky Power Deliv - Ele | AMKY0806 | G9259 | Dist Line Cap Inst for KY 2013 | 0 |  | 0 |  |  | 74827.97 | 0 | 74827.97 | 2013-01-14 | 2014-03-31 | 2013-01-01 | 2013-10-08
75084-DE Kentucky Power Deliv - Ele | NBFA | G9304 | NB emax 3777704 7979 Vulcan Dr | 0 |  | 0 |  |  | 35799.65 | 0 | 35799.65 | 2013-01-17 | 2014-01-31 | 2013-04-01 | 2013-10-18
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | G9311 | F5967 138kV Clear Correct OH | 0 |  | 0 |  |  | 32930.29 | 0 | 32930.29 | 2013-01-18 | 2015-03-31 | 2013-01-01 | 2014-01-05
75084-DE Kentucky Power Deliv - Ele | AMKY0849 | G9410 | F5962 Re-route at NKU | 0 |  | 0 |  |  | 792.48 | 0 | 792.48 | 2013-01-31 | 2014-03-31 | 2013-02-01 | 2013-08-24
75084-DE Kentucky Power Deliv - Ele | DETCONFA | G9501 | DET emax 3873582 Murman Rd | 0 |  | 0 |  |  | 327179.97 | 0 | 327179.97 | 2013-02-14 | 2014-03-31 | 2013-02-01 | 2014-01-02
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9684 | DC 3925631 Kenton 42 | 0 |  | 0 |  |  | 125214.31 | 0 | 125214.31 | 2013-03-05 | 2014-03-31 | 2013-04-01 | 2014-02-23
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | G9825 | Silver Grove Repl fans on TB 23 | 0 |  | 0 |  |  | 34060.17 | 0 | 34060.17 | 2013-03-25 | 2013-12-31 | 2013-05-01 | 2013-09-07
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | G9849 | DC emax 3983251 White Tower 41 | 0 |  | 0 |  |  | 106542.75 | 0 | 106542.75 | 2013-03-26 | 2014-03-31 | 2013-04-01 | 2013-11-22
75084-DE Kentucky Power Deliv - Ele | SUBCHAIRS | G9909 | Substation Chair Replacement | 0 |  | 0 |  |  | 1587.47 | 0 | 1587.47 | 2013-04-09 | 2013-04-22 | 2013-06-01 | 2013-10-01
75084-DE Kentucky Power Deliv - Ele | AMKY0752 | G9955 | Augustine SEL Dist Upgrades | 0 |  | 0 |  |  | 435665.83 | 0 | 435665.83 | 2013-04-16 | 2014-03-31 | 2013-04-01 | 2014-03-20
75084-DE Kentucky Power Deliv - Ele | FGISEAMKE | GISEAMKE | GIS-EAM R3 INTERFACE & SW-KENTUCKY | 0 |  | 0 |  |  | 24182.73 | 0 | 24182.73 | 2009-10-20 | 2011-03-30 | 2009-11-01 | 2011-05-01
75084-DE Kentucky Power Deliv - Ele | FGISPLOTK | GISPLOTKE | GIS PLOTTING ENHANCEMENTS | 0 |  | 0 |  |  | 45184.55 | 0 | 45184.55 | 2010-11-23 | 2011-06-30 | 2010-12-01 | 2011-08-16
75084-DE Kentucky Power Deliv - Ele | GLPRDFA | GLPRDKY | Pole Repl Gnd Line-D | -101118 |  | -101118 | 100% |  | 849596.11 | 0 | 849596.11 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | GLPRTKY | Pole Repl Gnd Line-T | 7549.56 |  | 7549.56 | 100% |  | 510179.11 | 0 | 510179.11 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0000 | Silver Grove 138kV Install | 0 |  | 0 |  |  | 707880.4 | 0 | 707880.4 | 2013-04-25 | 2015-09-01 | 2013-05-01 | 2014-07-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0009 | Silver Grove Inst TB1 & Rem Equip | 0 |  | 0 |  |  | 2352207.59 | 0 | 2352207.59 | 2013-04-25 | 2015-09-01 | 2013-05-01 | 2015-01-28
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0014 | Silver Grove 41 New Feeder | -324021.83 |  | -324021.83 | 100% |  | 1083745.46 | 0 | 1083745.46 | 2013-04-25 | 2015-09-01 | 2013-11-01 | 2015-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0016 | Silver Grove 42 43 New Feeder | -12155.03 |  | -12155.03 | 100% |  | 500958.95 | 0 | 500958.95 | 2013-04-25 | 2015-09-01 | 2013-11-01 | 2015-08-21
75084-DE Kentucky Power Deliv - Ele | AMKY0905 | H0017 | Silver Grove 41 42 43 UG Exits | 0 |  | 0 |  |  | 670160.25 | 0 | 670160.25 | 2013-04-25 | 2015-09-01 | 2013-07-01 | 2014-12-12
75084-DE Kentucky Power Deliv - Ele | NBFA | H0049 | NB emax 4052073 Retail North Bldg | 0 |  | 0 |  |  | 7068.61 | 0 | 7068.61 | 2013-05-02 | 2013-11-30 | 2013-05-01 | 2013-11-16
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0092 | Kenton Repl fans on TB 1 | 0 |  | 0 |  |  | 26578.59 | 0 | 26578.59 | 2013-05-13 | 2013-12-31 | 2013-06-01 | 2013-09-20
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0093 | Kenton Repl fans on VR 3 | 0 |  | 0 |  |  | 14085.49 | 0 | 14085.49 | 2013-05-13 | 2013-12-31 | 2013-06-01 | 2013-09-20
75084-DE Kentucky Power Deliv - Ele | NBFA | H0104 | NB emax 831 Heights Blvd | 0 |  | 0 |  |  | 4493.18 | 0 | 4493.18 | 2013-05-14 | 2014-03-31 | 2013-07-01 | 2013-12-10
75084-DE Kentucky Power Deliv - Ele | AMKY0877 | H0128 | Augustine 41 Reconductor | 0 |  | 0 |  |  | 93590.12 | 0 | 93590.12 | 2013-05-20 | 2014-09-01 | 2013-05-01 | 2014-01-10
75084-DE Kentucky Power Deliv - Ele | AMOH0555 | H0163 | F5962 138kV Clear Corr OH | 0 |  | 0 |  |  | 10325.67 | 0 | 10325.67 | 2013-05-23 | 2015-03-31 | 2013-07-01 | 2014-01-05
75084-DE Kentucky Power Deliv - Ele | RELDFA | H0282 | Prospect St-Robbins St-Jacob Price | 0 |  | 0 |  |  | 14514.78 | 0 | 14514.78 | 2013-06-17 | 2014-01-01 | 2013-06-01 | 2014-01-16
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0296 | Crescent Install 22.4MVA TB3 | 1172.25 |  | 1172.25 | 100% |  | 1786194.74 | 0 | 1786194.74 | 2013-06-20 | 2015-09-01 | 2013-08-01 | 2015-09-03
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0297 | Crescent UG 45 46 | 10985.58 |  | 10985.58 | 100% |  | 190802.54 | 0 | 190802.54 | 2013-06-21 | 2016-05-01 | 2015-06-01 | 2016-03-23
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0298 | Crescent 45 | -160820.36 |  | -160820.36 | 100% |  | 319990.85 | 0 | 319990.85 | 2013-06-21 | 2016-05-31 | 2014-10-01 | 2016-02-25
75084-DE Kentucky Power Deliv - Ele | AMKY0808 | H0299 | Crescent 46 OH Part1 | 5112.5 |  | 5112.5 | 100% |  | 13606.48 | 0 | 13606.48 | 2013-06-21 | 2019-03-31 | 2015-06-01
75084-DE Kentucky Power Deliv - Ele | NBFA | H0444 | NB emax 4158179 Old Alexandria Pike | 0 |  | 0 |  |  | 69133.62 | 0 | 69133.62 | 2013-07-19 | 2014-11-16 | 2013-09-01 | 2014-02-04
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | H0476 | Limaburg Repl low side bush on TB 2 | 0 |  | 0 |  |  | 19749.13 | 0 | 19749.13 | 2013-07-25 | 2013-10-29 | 2013-07-01 | 2013-10-27
75084-DE Kentucky Power Deliv - Ele | FMWMSW7 | H0499 | MWMS W7 REMEDIATION PROJ | 0 |  | 0 |  |  | 675.25 | 0 | 675.25 | 2013-08-01 | 2013-10-31 | 2013-08-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | H0503 | NB emax 4314177 IDI @ 30 Transport | -835.58 |  | -835.58 | 100% |  | 78433.67 | 0 | 78433.67 | 2013-08-05 | 2015-01-14 | 2014-01-01 | 2014-07-31
75084-DE Kentucky Power Deliv - Ele | NBFA | H0638 | NB emax 3296995 Arcadia Ph A | 0 |  | 0 |  |  | -65977.39 | 0 | -65977.39 | 2013-08-27 | 2014-11-30 | 2013-09-01 | 2014-03-27
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H0663 | Claryville TB 3 Repl bushings | 0 |  | 0 |  |  | 24545.18 | 0 | 24545.18 | 2013-08-29 | 2014-03-31 | 2013-12-01 | 2014-11-15
75084-DE Kentucky Power Deliv - Ele | RELDFA | H0669 | RI emax 4264899 95 Carothers Rd | 0 |  | 0 |  |  | 77791.3 | 0 | 77791.3 | 2013-08-30 | 2014-08-31 | 2013-09-01 | 2014-06-25
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1124 | Blackwell Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 19591.14 | 0 | 19591.14 | 2013-10-29 | 2015-09-01 | 2013-12-01 | 2014-07-02
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1126 | Covington Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 19635.46 | 0 | 19635.46 | 2013-10-29 | 2015-09-01 | 2013-12-01 | 2014-06-05
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1128 | Dayton Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 23922.63 | 0 | 23922.63 | 2013-10-29 | 2015-09-01 | 2013-11-01 | 2014-05-14
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1129 | Mt. Zion Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 30506.05 | 0 | 30506.05 | 2013-10-29 | 2015-09-01 | 2014-01-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1134 | Thomas More Upgrd Frame Rlay Equip | 0 |  | 0 |  |  | 39481.99 | 0 | 39481.99 | 2013-10-29 | 2015-09-01 | 2013-11-01 | 2015-02-11
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1136 | Hands Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 30412.03 | 0 | 30412.03 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-07-31
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1137 | Kentucky Univ Upgrd Frme Rlay Equip | 0 |  | 0 |  |  | 33210.8 | 0 | 33210.8 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-10-09
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1138 | York Upgrade Frame Relay Equip | 0 |  | 0 |  |  | 30744.61 | 0 | 30744.61 | 2013-10-30 | 2015-09-01 | 2013-12-01 | 2014-09-25
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1139 | Bellevue Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 58116.64 | 0 | 58116.64 | 2013-10-30 | 2015-09-01 | 2014-01-01 | 2015-01-16
75084-DE Kentucky Power Deliv - Ele | ITKYFR14D | H1140 | Cold Spring Upgrd Frame Relay Equip | 0 |  | 0 |  |  | 66994.91 | 0 | 66994.91 | 2013-10-30 | 2015-09-01 | 2014-01-01 | 2014-07-16
75084-DE Kentucky Power Deliv - Ele | AMKY0974 | H1171 | Buffington-Repl CB 681 683 | 0 |  | 0 |  |  | 495173.27 | 0 | 495173.27 | 2013-11-04 | 2015-09-01 | 2014-01-01 | 2015-06-30
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1196 | TR 4599000 Florence 46 | -9898.92 |  | -9898.92 | 100% |  | 56201.14 | 0 | 56201.14 | 2013-11-06 | 2016-07-31 | 2013-11-01 | 2016-03-16
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1217 | TR 4597480 Florence 45 | 0 |  | 0 |  |  | 100352.79 | 0 | 100352.79 | 2013-11-11 | 2015-10-31 | 2014-01-01 | 2015-08-05
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1225 | TR 4609673 Hebron 45 | 0 |  | 0 |  |  | 31097.36 | 0 | 31097.36 | 2013-11-12 | 2015-07-31 | 2014-01-01 | 2015-06-18
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1231 | TR 4613012 Richwood 42 | 309.99 |  | 309.99 | 100% |  | 108883.11 | 0 | 108883.11 | 2013-11-12 | 2016-12-30 | 2015-02-01 | 2016-06-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1233 | TR 4614262 Buffington 41 | 0 |  | 0 |  |  | 74255.28 | 0 | 74255.28 | 2013-11-13 | 2015-12-30 | 2015-01-01 | 2015-07-29
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1236 | TR 4616175 Limaburg 41 | 139.95 |  | 139.95 | 100% |  | 37923 | 0 | 37923 | 2013-11-13 | 2016-12-30 | 2013-11-01 | 2016-06-08
75084-DE Kentucky Power Deliv - Ele | MOFA | H1271 | OR 4599261 Bury 3PH Primary Covgtn | 0 |  | 0 |  |  | 53536.61 | 0 | 53536.61 | 2013-11-20 | 2014-11-25 | 2013-11-01 | 2014-11-14
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1313 | Beaver Sub SG DA | 0 |  | 0 |  |  | 383965.79 | 0 | 383965.79 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1314 | Florence Sub SG DA | 0 |  | 0 |  |  | 330451.7 | 0 | 330451.7 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-01-14
75084-DE Kentucky Power Deliv - Ele | SGKDAISS | H1315 | Limaburg Sub SG DA | 0 |  | 0 |  |  | 583196.08 | 0 | 583196.08 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1372 | TR 4655448 CLARYVILLE 41 | 23607.65 |  | 23607.65 | 100% |  | 298265.3 | 0 | 298265.3 | 2013-12-03 | 2016-12-30 | 2014-10-01 | 2016-09-08
75084-DE Kentucky Power Deliv - Ele | NBFA | H1381 | JT 4655806 Arcadia West PH A electr | 0 |  | 0 |  |  | 73653.24 | 0 | 73653.24 | 2013-12-04 | 2014-11-29 | 2013-12-01 | 2014-07-28
75084-DE Kentucky Power Deliv - Ele | NBFA | H1382 | NB 3941206 Stillbrooke Subdv Felice | 0 |  | 0 |  |  | 18021.21 | 0 | 18021.21 | 2013-12-04 | 2014-11-30 | 2014-01-01 | 2014-08-08
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1397 | TR 4658415 Hands 41 | 0 |  | 0 |  |  | 134497.01 | 0 | 134497.01 | 2013-12-05 | 2016-01-30 | 2014-05-01 | 2015-01-02
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1398 | TR 4660303 Hands 44 | -24031.92 |  | -24031.92 | 100% |  | 180576.87 | 0 | 180576.87 | 2013-12-05 | 2016-06-30 | 2014-04-01 | 2016-02-15
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1404 | TR 4660722 Augustine 41 | -15862.01 |  | -15862.01 | 100% |  | 120740.71 | 0 | 120740.71 | 2013-12-06 | 2016-06-30 | 2015-01-01 | 2016-02-18
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1446 | TR 4674272 Augustine 46 | 0 |  | 0 |  |  | 168565.55 | 0 | 168565.55 | 2013-12-12 | 2015-03-31 | 2013-12-01 | 2015-02-14
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1453 | TR 4675524 York 43 | -7872.63 |  | -7872.63 | 100% |  | 44877.29 | 0 | 44877.29 | 2013-12-12 | 2016-06-01 | 2013-12-01 | 2015-06-17
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1462 | TR 4677452 Marshall 41 | 0 |  | 0 |  |  | 48642.69 | 0 | 48642.69 | 2013-12-13 | 2015-03-31 | 2014-05-01 | 2014-10-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1464 | TR 4678169 KY UNIV 43 | 0 |  | 0 |  |  | 72686.45 | 0 | 72686.45 | 2013-12-13 | 2015-07-31 | 2013-12-01 | 2015-06-20
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1487 | TR 4693232 Oakbrook 41 | -11282.4 |  | -11282.4 | 100% |  | 16436.49 | 0 | 16436.49 | 2013-12-17 | 2015-10-30 | 2014-12-01 | 2015-04-19
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1488 | TR 4693837 Augustine 43 | 1216.36 |  | 1216.36 | 100% |  | 62240.78 | 0 | 62240.78 | 2013-12-17 | 2016-06-30 | 2014-04-01 | 2016-02-17
75084-DE Kentucky Power Deliv - Ele | CSPFA | H1489 | TR 4694697 Verona 42 | -1553.11 |  | -1553.11 | 100% |  | 76718.28 | 0 | 76718.28 | 2013-12-17 | 2016-07-30 | 2013-12-01 | 2016-06-08
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H1600 | Augustine Repl LAs on TB 5 | 0 |  | 0 |  |  | 9535.91 | 0 | 9535.91 | 2014-01-03 | 2015-03-31 | 2014-04-01 | 2015-02-12
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | H1601 | Marshall Repl HS LAs on TB 1 | 0 |  | 0 |  |  | 7616.97 | 0 | 7616.97 | 2014-01-03 | 2015-03-31 | 2014-03-01 | 2014-07-04
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | H1642 | DC 4759551 Verona 41 | 0 |  | 0 |  |  | 39654.36 | 0 | 39654.36 | 2014-01-10 | 2015-06-30 | 2014-03-01 | 2015-03-23
75084-DE Kentucky Power Deliv - Ele | UGCRFA | H1679 | UG 4765860 URD 36 Brookwood | 0 |  | 0 |  |  | 154132.69 | 142644.34 | 11488.35 | 2014-01-15 | 2015-02-28 | 2014-01-01 | 2014-08-28
75084-DE Kentucky Power Deliv - Ele | PRDFA | H1728 | PR 4841795 Emerson Electric Reroute | 0 |  | 0 |  |  | 53672.57 | 0 | 53672.57 | 2014-01-27 | 2015-03-31 | 2014-02-01 | 2014-10-31
75084-DE Kentucky Power Deliv - Ele | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 56434.99 |  | 56434.99 | 100% |  | 775070.27 | 0 | 775070.27 | 2014-02-18 | 2019-03-01 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | CSPFA | I6126 | TR 5180760 Kenton 46 | 44501.86 |  | 44501.86 | 100% |  | 44501.86 | 0 | 44501.86 | 2014-03-19 | 2017-03-31 | 2016-02-01 | 2016-10-27
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY1Q12 | Q1 2012 IK KY Blanket Roll Up Proj | 0 |  | 0 |  |  | 5870552.06 | 0 | 5870552.06 | 2012-02-03 | 2012-12-31 | 2012-01-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2013 | 2013 IK KY Blanket Roll Up Proj | 0 |  | 0 |  |  | 10494333.25 | 0 | 10494333.25 | 2012-12-21 | 2013-12-31 | 2012-12-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2014 | 2014 IK KY Blanket Roll Up Proj | 0 |  | 0 |  |  | 8190663.87 | 0 | 8190663.87 | 2013-12-27 | 2014-12-31 | 2013-12-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2015 | 2015 KY Dist Lines (IK) Roll | 0 |  | 0 |  |  | 5199091.21 | 0 | 5199091.21 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2015T | 2015 KY Dist Lines (IK) Roll - T | 0 |  | 0 |  |  | 5195932.69 | 0 | 5195932.69 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2016 | 2016 KY Dist Lines (IK) Roll | 3252913.32 |  | 3252913.32 | 100% |  | 3897653.74 | 0 | 3897653.74 | 2015-11-30 15:55 | 2016-12-31 | 2015-12-01
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKY2016T | 2016 KY Dist Lines (IK) Roll - T | 3637724.98 |  | 3637724.98 | 100% |  | 4030703.69 | 0 | 4030703.69 | 2015-11-30 16:03 | 2016-12-31 | 2015-12-01
75084-DE Kentucky Power Deliv - Ele | NBFA | IKKYROL11 | 2011 IK KY Roll Up Blanket Project | 0 |  | 0 |  |  | 9791865.05 | 0 | 9791865.05 | 2011-12-16 | 2011-12-31 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | AMKY0953 | J0108 | Hebron Inst 69kV CB's | 24857.13 |  | 24857.13 | 100% |  | 1684967.58 | 0 | 1684967.58 | 2014-03-24 | 2015-09-01 | 2014-03-01 | 2015-08-29
75084-DE Kentucky Power Deliv - Ele | AMKY0953 | J0109 | Villa Repl F2862 Relays | 0 |  | 0 |  |  | 193189.27 | 0 | 193189.27 | 2014-03-24 | 2015-10-01 | 2014-03-01 | 2015-09-13
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | J0111 | Augustine Repl fans on TB 5 | 0 |  | 0 |  |  | 11977.54 | 0 | 11977.54 | 2014-03-24 | 2015-03-31 | 2014-07-01 | 2014-10-22
75084-DE Kentucky Power Deliv - Ele | CSPFA | J0118 | TR 5215691 Wilder 47 | -4386.65 |  | -4386.65 | 100% |  | 91780.53 | 0 | 91780.53 | 2014-03-25 | 2016-03-31 | 2015-08-01 | 2015-12-31
75084-DE Kentucky Power Deliv - Ele | CSPFA | J4103 | TR 5247963 Augustine 45 | 44642.99 |  | 44642.99 | 100% |  | 45046.38 | 0 | 45046.38 | 2014-03-31 | 2016-12-30 | 2014-04-01 | 2016-09-15
75084-DE Kentucky Power Deliv - Ele | CSPFA | J4104 | TR 5249008 Longbranch 42 | 5145.93 |  | 5145.93 | 100% |  | 153998.92 | 0 | 153998.92 | 2014-03-31 | 2017-01-31 | 2015-05-01 | 2016-11-02
75084-DE Kentucky Power Deliv - Ele | CSPFA | J4106 | TR 5225496 Augustine 44 | 63437.41 |  | 63437.41 | 100% |  | 63437.41 | 0 | 63437.41 | 2014-03-31 | 2017-01-31 | 2016-05-01 | 2016-11-23
75084-DE Kentucky Power Deliv - Ele | CSPFA | J5116 | TR 5263786 Cold Spring 41 | 120996.34 |  | 120996.34 | 100% |  | 120996.34 | 0 | 120996.34 | 2014-04-02 | 2017-01-31 | 2016-05-01 | 2016-11-05
75084-DE Kentucky Power Deliv - Ele | CSPFA | J5122 | TR 5267739 Cold Spring 49 | 159597.4 |  | 159597.4 | 100% |  | 159597.4 | 0 | 159597.4 | 2014-04-02 | 2018-01-31 | 2016-05-01 | 2017-07-28
75084-DE Kentucky Power Deliv - Ele | CSPFA | J7117 | TR 5215256 Donaldson 41 | 70991.7 |  | 70991.7 | 100% |  | 70991.7 | 0 | 70991.7 | 2014-04-07 | 2016-09-01 | 2016-02-01 | 2016-06-04
75084-DE Kentucky Power Deliv - Ele | CSPFA | J9110 | TR 5301582 Alexandria South 41 | 183558.57 |  | 183558.57 | 100% |  | 183558.57 | 0 | 183558.57 | 2014-04-10 | 2017-08-15 | 2016-04-01 | 2017-03-15
75084-DE Kentucky Power Deliv - Ele | ESXIUPG14 | J9118 | 2014 ESXI Upgrade-Kentucky | 0 |  | 0 |  |  | 7230.09 | 0 | 7230.09 | 2014-04-11 | 2015-01-31 | 2014-04-01 | 2015-01-30
75084-DE Kentucky Power Deliv - Ele | CSPFA | K0104 | TR 5309940 Covington 43 | 0 |  | 0 |  |  | 42638.09 | 0 | 42638.09 | 2014-04-11 | 2016-03-29 | 2015-05-01 | 2015-08-14
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | K4107 | Limaburg Repl failed TB 2 | 0 |  | 0 |  |  | 78277.62 | 0 | 78277.62 | 2014-04-21 | 2014-09-30 | 2014-04-01 | 2014-08-08
75084-DE Kentucky Power Deliv - Ele | NBFA | K7108 | NB 4686312 512 Oak Ludlow | 0 |  | 0 |  |  | 7515.52 | 0 | 7515.52 | 2014-04-28 | 2015-04-28 | 2014-06-01 | 2014-09-24
75084-DE Kentucky Power Deliv - Ele | KARF51805 | KAR851805 | LAR 10851805 Wilder 44 | 7435.35 |  | 7435.35 | 100% |  | 7435.35 | 0 | 7435.35 | 2016-07-26 14:03 | 2018-01-31 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | NCIPLOWK | KCIPLW001 | Augustine KY NERC CIP LW | 99084.79 |  | 99084.79 | 100% |  | 99084.79 | 0 | 99084.79 | 2016-09-22 10:40 | 2018-03-31 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | NCIPLOWK | KCIPLW002 | Wilder-Ky NERC CIP Low DS | 98894.55 |  | 98894.55 | 100% |  | 98894.55 | 0 | 98894.55 | 2016-09-22 13:54 | 2017-09-01 | 2016-09-01 | 2017-06-09
75084-DE Kentucky Power Deliv - Ele | NCIPLOWK | KCIPLW003 | York - Ky NERC CIP Low | 7793.2 |  | 7793.2 | 100% |  | 7793.2 | 0 | 7793.2 | 2016-11-17 12:52 | 2018-03-31 | 2016-11-01 | 2017-07-05
75084-DE Kentucky Power Deliv - Ele | NCIPLOWK | KCIPLW004 | Buffington - Ky NERC CIP Low | 8200.53 |  | 8200.53 | 100% |  | 8200.53 | 0 | 8200.53 | 2016-11-17 13:03 | 2018-03-31 | 2016-11-01 | 2017-08-10
75084-DE Kentucky Power Deliv - Ele | KECF20153 | KEC920153 | DC 8920153 Bellevue 42 | 2461.21 |  | 2461.21 | 100% |  | 2461.21 | 0 | 2461.21 | 2015-10-23 10:05 | 2019-07-31 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | KECF20154 | KEC920154 | DEC 8920154 Kenton 46 | 3927.04 |  | 3927.04 | 100% |  | 3927.04 | 0 | 3927.04 | 2015-10-23 10:05 | 2018-05-31 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | KECF20155 | KEC920155 | DEC 8920155 Oakbrook 41 | 4919.4 |  | 4919.4 | 100% |  | 4919.4 | 0 | 4919.4 | 2015-10-26 18:05 | 2019-08-31 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | KETF35851 | KET135851 | DET 10135851 West End 41 | 7875.54 |  | 7875.54 | 100% |  | 7875.54 | 0 | 7875.54 | 2016-05-02 14:04 | 2018-06-30 | 2016-05-01
75084-DE Kentucky Power Deliv - Ele | KETF35853 | KET135853 | DET 10135853 Hands 44 310 | 1152.34 |  | 1152.34 | 100% |  | 1152.34 | 0 | 1152.34 | 2016-11-07 10:03 | 2018-08-31 | 2016-12-01
75084-DE Kentucky Power Deliv - Ele | KETF35854 | KET135854 | DET 10135854 Villa 43 348 | 858.13 |  | 858.13 | 100% |  | 858.13 | 0 | 858.13 | 2016-11-04 18:06 | 2018-10-31 | 2016-12-01
75084-DE Kentucky Power Deliv - Ele | KETF47112 | KET347112 | DET 7347112 KY University 43 | -1940.96 |  | -1940.96 | 100% |  | 270050.45 | 0 | 270050.45 | 2015-06-03 10:01 | 2016-03-31 | 2015-04-01 | 2015-11-25
75084-DE Kentucky Power Deliv - Ele | KETF47303 | KET347303 | DET 7347303 Beaver 41 | 138376.97 |  | 138376.97 | 100% |  | 247794.46 | 0 | 247794.46 | 2015-06-03 14:01 | 2016-10-29 | 2015-06-01 | 2016-05-03
75084-DE Kentucky Power Deliv - Ele | KETF45693 | KET745693 | DET 8745693 SILVER GROVE | 84098.49 |  | 84098.49 | 100% |  | 101950.98 | 0 | 101950.98 | 2015-10-13 14:06 | 2016-03-31 | 2015-10-01 | 2016-04-16
75084-DE Kentucky Power Deliv - Ele | KETF33444 | KET833444 | DET 8833444 Crescent 43 R | 226728.7 |  | 226728.7 | 100% |  | 231649.18 | 0 | 231649.18 | 2015-12-10 14:04 | 2016-12-06 | 2015-12-01 | 2016-08-10
75084-DE Kentucky Power Deliv - Ele | KFSF97495 | KFS897495 | CS 6897495 Decoursey 41 | 107516.49 |  | 107516.49 | 100% |  | 114921.96 | 0 | 114921.96 | 2015-06-01 14:01 | 2016-09-30 | 2015-09-01 | 2016-08-24
75084-DE Kentucky Power Deliv - Ele | KHRF82804 | KHR082804 | RI 10082804 15 Spiral Dr | -60266.84 |  | -60266.84 | 100% |  | -60266.84 | 0 | -60266.84 | 2016-08-23 14:03 | 2017-08-28 | 2016-10-01 | 2018-01-04
75084-DE Kentucky Power Deliv - Ele | KHRF77294 | KHR177294 | DOT 7177294 Hebron 42, in | 100658.55 |  | 100658.55 | 100% |  | 103203.1 | 0 | 103203.1 | 2015-11-19 14:04 | 2016-08-09 | 2015-12-01 | 2016-06-17
75084-DE Kentucky Power Deliv - Ele | KHRF80227 | KHR180227 | DOT 7180227 Wilder 48 rep | 176447.2 |  | 176447.2 | 100% |  | 219220.46 | 0 | 219220.46 | 2015-09-08 18:02 | 2016-09-01 | 2015-09-01 | 2016-08-31
75084-DE Kentucky Power Deliv - Ele | KHRF97697 | KHR297697 | DOT 7297697 Covington 43 | 30970.73 |  | 30970.73 | 100% |  | 30970.73 | 0 | 30970.73 | 2016-07-07 18:05 | 2018-01-01 | 2016-07-01
75084-DE Kentucky Power Deliv - Ele | KHRF55669 | KHR355669 | RI 10355669 Washington St | -149992.38 |  | -149992.38 | 100% |  | -149992.38 | 0 | -149992.38 | 2016-07-22 18:06 | 2017-07-28 | 2016-08-01 | 2017-06-20
75084-DE Kentucky Power Deliv - Ele | KHRF51813 | KHR451813 | RI 10451813 5310 Madison | 3391.61 |  | 3391.61 | 100% |  | 3391.61 | 0 | 3391.61 | 2016-12-05 14:04 | 2017-08-15 | 2016-12-01 | 2018-01-29
75084-DE Kentucky Power Deliv - Ele | KHRF52071 | KHR652071 | DOT 4652071 Ky Univ 42 Ma | 215569.14 |  | 215569.14 | 100% |  | 215569.14 | 0 | 215569.14 | 2016-01-13 18:04 | 2016-12-30 | 2016-01-01 | 2016-10-29
75084-DE Kentucky Power Deliv - Ele | KHRF44679 | KHR744679 | RI 9744679 6th St e/o Cra | 12927.87 |  | 12927.87 | 100% |  | 12927.87 | 0 | 12927.87 | 2016-02-05 14:05 | 2018-06-30 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | KHRF44840 | KHR744840 | RI 9744840 6th St e/o Cra | 10227.71 |  | 10227.71 | 100% |  | 10227.71 | 0 | 10227.71 | 2016-02-08 14:04 | 2018-06-30 | 2016-03-01
75084-DE Kentucky Power Deliv - Ele | KHRF28828 | KHR928828 | RI 9928828 Hands 428 | 183216.81 |  | 183216.81 | 100% |  | 183216.81 | 0 | 183216.81 | 2016-03-16 14:04 | 2017-07-30 | 2016-03-01 | 2017-01-05
75084-DE Kentucky Power Deliv - Ele | KIAF92413 | KIA892413 | DA 8892413 White Tower 41 | 71420.04 |  | 71420.04 | 100% |  | 71420.04 | 0 | 71420.04 | 2015-10-30 10:05 | 2017-09-30 | 2016-07-01 | 2016-12-22
75084-DE Kentucky Power Deliv - Ele | KIAF92443 | KIA892443 | DA 8892443 Bellevue 42 | 80547.88 |  | 80547.88 | 100% |  | 80547.88 | 0 | 80547.88 | 2015-10-30 10:05 | 2016-11-30 | 2016-02-01 | 2016-10-29
75084-DE Kentucky Power Deliv - Ele | KILF49392 | KIL049392 | UG 7049392 Augustine 46 P | 2224.7 |  | 2224.7 | 100% |  | 440063.36 | 0 | 440063.36 | 2015-07-07 10:01 | 2016-04-30 | 2015-09-01 | 2016-03-30
75084-DE Kentucky Power Deliv - Ele | KILF64406 | KIL564406 | UG 10564406 West End 41 | 228783.37 |  | 228783.37 | 100% |  | 228783.37 | 0 | 228783.37 | 2016-07-01 18:06 | 2017-05-28 | 2016-08-01 | 2017-04-12
75084-DE Kentucky Power Deliv - Ele | FKPIAPP | KPIAPPL | Perf Meas App (KPI) - T&D & Gas | 21.46 |  | 21.46 | 100% |  | 216.74 | 0 | 216.74 | 2015-03-12 15:53 | 2016-02-28 | 2015-04-01 | 2016-01-29
75084-DE Kentucky Power Deliv - Ele | KUSF07426 | KSP707426 | NB 9707426 White Tower 42 | 57423.69 |  | 57423.69 | 100% |  | 57423.69 | 0 | 57423.69 | 2016-07-29 18:05 | 2016-12-29 | 2016-08-01 | 2016-12-19
75084-DE Kentucky Power Deliv - Ele | KSPF41656 | KSP941656 | NB 10941656 North Walton Pointe | 24298.84 |  | 24298.84 | 100% |  | 24298.84 | 0 | 24298.84 | 2016-08-16 14:04 | 2017-06-10 | 2016-08-01 | 2017-05-21
75084-DE Kentucky Power Deliv - Ele | KTMF72080 | KTM272080 | SL 8272080 Manhattan Blvd | -2180.36 |  | -2180.36 | 100% |  | 70932.45 | 0 | 70932.45 | 2015-08-04 18:01 | 2016-03-30 | 2015-09-01 | 2015-12-25
75084-DE Kentucky Power Deliv - Ele | KTMF66767 | KTM466767 | SL 7466767 Park South Bldg A | 85072.32 |  | 85072.32 | 100% |  | 138999.59 | 0 | 138999.59 | 2015-05-04 14:01 | 2016-06-27 | 2015-05-01 | 2016-02-21
75084-DE Kentucky Power Deliv - Ele | KTMF99778 | KTM499778 | SL 10499778 York 741 | 384266.21 |  | 384266.21 | 100% |  | 384266.21 | 0 | 384266.21 | 2016-06-13 10:04 | 2017-02-28 | 2016-09-01 | 2017-02-15
75084-DE Kentucky Power Deliv - Ele | KTMF82555 | KTM582555 | SL 9582555 55 Transport D | 85312.84 |  | 85312.84 | 100% |  | 85312.84 | 0 | 85312.84 | 2016-01-18 18:05 | 2017-02-28 | 2016-07-01 | 2017-01-19
75084-DE Kentucky Power Deliv - Ele | KTMF28273 | KTM628273 | SL 7628273 St Rt 18 | -150.62 |  | -150.62 | 100% |  | 44144.16 | 0 | 44144.16 | 2015-10-09 18:05 | 2016-04-20 | 2015-11-01 | 2016-03-29
75084-DE Kentucky Power Deliv - Ele | KSLF53633 | KTM853633 | SL 6853633 Heights Blvd | 173823.37 |  | 173823.37 | 100% |  | 63143.06 | 0 | 63143.06 | 2015-06-22 14:01 | 2016-12-11 | 2015-09-01 | 2016-02-21
75084-DE Kentucky Power Deliv - Ele | KTMF99834 | KTM999834 | SL 7999834 Bellevue 13144 | 2546.86 |  | 2546.86 | 100% |  | 96171.43 | 0 | 96171.43 | 2015-06-24 17:43 | 2017-01-24 | 2015-08-01 | 2016-01-09
75084-DE Kentucky Power Deliv - Ele | KTOF28218 | KTO628218 | SL 10628218 City of Edgewood | 13170.81 |  | 13170.81 | 100% |  | 13170.81 | 0 | 13170.81 | 2016-09-12 14:04 | 2017-03-16 | 2016-09-01 | 2017-02-08
75084-DE Kentucky Power Deliv - Ele | KUCF34911 | KUC234911 | UG 6234911 Hands 44 URD | 609552.37 |  | 609552.37 | 100% |  | 609552.37 | 0 | 609552.37 | 2015-11-23 14:07 | 2017-07-15 | 2016-01-01 | 2017-04-26
75084-DE Kentucky Power Deliv - Ele | KUCF42577 | KUC442577 | UG 8442577 Buffington 44, | 299275.46 |  | 299275.46 | 100% |  | 299275.46 | 0 | 299275.46 | 2015-09-10 18:02 | 2017-02-28 | 2016-01-01 | 2016-11-06
75084-DE Kentucky Power Deliv - Ele | KUSF21914 | KUS021914 | NB 8021914 Aosta Valley Subd | 25841.97 |  | 25841.97 | 100% |  | 59214.76 | 0 | 59214.76 | 2015-11-13 18:07 | 2016-09-30 | 2015-12-01 | 2016-04-29
75084-DE Kentucky Power Deliv - Ele | KUSF69963 | KUS069963 | NB 8069963 Memorial Parkway | 264880.67 |  | 264880.67 | 100% |  | 341137.15 | 0 | 341137.15 | 2015-07-06 14:01 | 2016-06-30 | 2015-07-01 | 2016-06-22
75084-DE Kentucky Power Deliv - Ele | KUSF72128 | KUS172128 | NB 9172128 820 Dolwick UG | 85707.01 |  | 85707.01 | 100% |  | 85707.01 | 0 | 85707.01 | 2016-02-08 14:04 | 2017-04-15 | 2016-04-01 | 2017-03-21
75084-DE Kentucky Power Deliv - Ele | KEFF91578 | KUS191578 | NB 7191578 Renshaw Retire | 134022.39 |  | 134022.39 | 100% |  | 134022.39 | 0 | 134022.39 | 2016-02-12 14:05 | 2017-03-30 | 2016-08-01 | 2017-02-14
75084-DE Kentucky Power Deliv - Ele | KUSF97225 | KUS497225 | UG 4497225 Heights Blvd | 5597.02 |  | 5597.02 | 100% |  | 71556.68 | 0 | 71556.68 | 2015-06-22 10:01 | 2016-02-19 | 2015-08-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | KUSF97855 | KUS597855 | NB 7597855 Florence 44 St Rt 18 | 42207.88 |  | 42207.88 | 100% |  | 119491.22 | 0 | 119491.22 | 2015-10-09 18:05 | 2016-04-19 | 2015-10-01 | 2016-03-29
75084-DE Kentucky Power Deliv - Ele | KUSF37967 | KUS837967 | NB 7837967 cold spring 41 | 34965.24 |  | 34965.24 | 100% |  | 34965.24 | 0 | 34965.24 | 2016-01-13 18:04 | 2016-09-30 | 2016-01-01 | 2016-08-04
75084-DE Kentucky Power Deliv - Ele | KUSF45398 | KUS945398 | NB 8945398 Aqua on the Le | 54724.89 |  | 54724.89 | 100% |  | 80206.18 | 0 | 80206.18 | 2015-10-16 14:03 | 2016-03-31 | 2015-10-01 | 2016-05-03
75084-DE Kentucky Power Deliv - Ele | KUSF63952 | KUS963952 | NB 8963952 Longbranch 43 | 173409.4 |  | 173409.4 | 100% |  | 173409.4 | 0 | 173409.4 | 2016-02-22 10:04 | 2017-03-31 | 2016-09-01 | 2017-01-13
75084-DE Kentucky Power Deliv - Ele | KUSF80889 | KUS980889 | NB 6980889 900 E. 6th St, | -1313.44 |  | -1313.44 | 100% |  | 57549.61 | 0 | 57549.61 | 2015-10-01 18:04 | 2016-03-12 | 2015-11-01 | 2016-03-06
75084-DE Kentucky Power Deliv - Ele | CERTFA | KYCERT1 | CERTKY P0 CIR 966 | 4758.91 |  | 4758.91 | 100% |  | 4758.91 | 0 | 4758.91 | 2016-10-28 08:37 | 2017-06-30 | 2016-11-01 | 2017-03-31
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | KYGLPR2 | GLT Cir 5967 P2 | 30154.78 |  | 30154.78 | 100% |  | 30154.78 | 0 | 30154.78 | 2016-02-10 14:55 | 2016-09-01 | 2016-03-01 | 2016-05-24
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | KYGLPR3 | GLT Cir 5962 P2 Repl X-Arms | 91316.4 |  | 91316.4 | 100% |  | 91316.4 | 0 | 91316.4 | 2016-02-12 10:09 | 2016-09-01 | 2016-03-01 | 2016-05-26
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | KYGLPR4 | GLT Cir 6763 P2 Str 518 | 70544.2 |  | 70544.2 | 100% |  | 70544.2 | 0 | 70544.2 | 2016-02-12 10:57 | 2018-02-01 | 2016-10-01 | 2017-03-02
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | KYGLPR5 | GLT Cir 2862B P1-P2 | 25902.58 |  | 25902.58 | 100% |  | 25902.58 | 0 | 25902.58 | 2016-06-13 16:14 | 2019-03-31 | 2016-07-01
75084-DE Kentucky Power Deliv - Ele | GLPRTFA | KYGLPR7 | GLT P2 Cir 5967 4 Poles | 103971.47 |  | 103971.47 | 100% |  | 103971.47 | 0 | 103971.47 | 2016-09-01 09:04 | 2017-01-30 | 2016-09-01 | 2017-01-17
75084-DE Kentucky Power Deliv - Ele | PRTFA | KYPRTF1 | F5967, 51CA-423 Pole Replacement | 49268.3 |  | 49268.3 | 100% |  | 49268.3 | 0 | 49268.3 | 2016-02-10 12:59 | 2017-03-31 | 2016-02-01 | 2016-11-26
75084-DE Kentucky Power Deliv - Ele | RELTFA | KYRELT1 | F6763 DOT Mt Zion Rd-Dixie Hwy | 2536.16 |  | 2536.16 | 100% |  | 3164.48 | 0 | 3164.48 | 2015-07-25 18:59 | 2018-03-31 | 2015-09-01
75084-DE Kentucky Power Deliv - Ele | RELTFA | KYRELT2 | F966 Rel 1 Trans Pole Chic-Fil-A | -144698.51 |  | -144698.51 | 100% |  | -144698.51 | 0 | -144698.51 | 2016-04-05 11:13 | 2017-01-01 | 2016-04-01 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | ORTFA | KYRELT3 | Storm 03- Circuit 5967 | 33588.76 |  | 33588.76 | 100% |  | 33588.76 | 0 | 33588.76 | 2016-11-14 16:28 | 2017-05-01 | 2016-11-01 | 2017-02-28
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | L2102 | DC 5476661 Hebron 42 | -21.51 |  | -21.51 | 100% |  | 34408.43 | 0 | 34408.43 | 2014-05-08 | 2015-11-01 | 2014-06-01 | 2015-08-07
75084-DE Kentucky Power Deliv - Ele | AMKY0944 | L2103 | Beaver-Install ATO | 0 |  | 0 |  |  | 267427.44 | 0 | 267427.44 | 2014-05-08 | 2015-03-31 | 2014-05-01 | 2015-03-30
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | L2104 | DC 5476709 Villa 43 | 8763.02 |  | 8763.02 | 100% |  | 69969.98 | 0 | 69969.98 | 2014-05-08 | 2016-07-30 | 2014-06-01 | 2016-06-25
75084-DE Kentucky Power Deliv - Ele | AMKY0940 | L2107 | Limaburg-Install ATO | 0 |  | 0 |  |  | 210828.53 | 0 | 210828.53 | 2014-05-08 | 2015-03-31 | 2014-05-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | AMKY0940 | L2109 | Buffington F6763 Reclosing | 0 |  | 0 |  |  | 11887.63 | 0 | 11887.63 | 2014-05-08 | 2015-03-31 | 2014-07-01 | 2015-03-09
75084-DE Kentucky Power Deliv - Ele | AMKY1101 | L5122 | UG 5511344 Kenton 43 Bld New Fdr | 0 |  | 0 |  |  | 698213.09 | 0 | 698213.09 | 2014-05-15 | 2016-03-31 | 2014-07-01 | 2015-07-16
75084-DE Kentucky Power Deliv - Ele | AMKY0941 | L9104 | Grant Install TLS | 7397.93 |  | 7397.93 | 100% |  | 712767.18 | 0 | 712767.18 | 2014-05-21 | 2016-03-31 | 2014-06-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | AMKY0943 | L9108 | Cold Spring TLS | 13262.61 |  | 13262.61 | 100% |  | 286255.01 | 0 | 286255.01 | 2014-05-22 | 2015-09-30 | 2014-06-01 | 2015-08-01
75084-DE Kentucky Power Deliv - Ele | AMKY1073 | L9115 | Buffington Repl VTs | 0 |  | 0 |  |  | 189218.31 | 0 | 189218.31 | 2014-05-22 | 2015-09-01 | 2014-06-01 | 2015-06-30
75084-DE Kentucky Power Deliv - Ele | PILCFA | L9117 | UG 5466220 Buffington 45 PILC Repl | 0 |  | 0 |  |  | 26740.64 | 0 | 26740.64 | 2014-05-22 | 2015-11-30 | 2014-07-01 | 2015-02-04
75084-DE Kentucky Power Deliv - Ele | PRDFA | LARCUKY | Limited Access Road Crossing Upgrad | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-05-23 | 2050-12-31 | 2012-10-01
75084-DE Kentucky Power Deliv - Ele | RLFA | LPFUKY | Line Patrol Insp followup KY | -97241.48 |  | -97241.48 | 100% |  | -583.52 | 0 | -583.52 | 2010-12-22 | 2015-12-31 | 2011-03-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | LPRFUKY | Line Patrol Followup Work | 8423.18 |  | 8423.18 | 100% |  | 568357.02 | 0 | 568357.02 | 2013-03-20 | 2050-12-31 | 2013-11-01
75084-DE Kentucky Power Deliv - Ele | RLFA | LPSMEIKY | Dline Patrol SMEI Capital Followup | -4708.64 |  | -4708.64 | 100% |  | 0 | 0 | 0 | 2012-04-30 | 2050-12-31 | 2013-02-01
75084-DE Kentucky Power Deliv - Ele | AMKY0942 | M1112 | Dry Ridge TLS | 3140.89 |  | 3140.89 | 100% |  | 273987.61 | 0 | 273987.61 | 2014-05-29 | 2015-09-30 | 2014-06-01 | 2015-08-29
75084-DE Kentucky Power Deliv - Ele | RELDFA | M2116 | DOT 5395279 Taylor Mill Rd @ Walnut | 0 |  | 0 |  |  | 1012.41 | 0 | 1012.41 | 2014-06-03 | 2015-05-02 | 2014-06-01 | 2015-02-20
75084-DE Kentucky Power Deliv - Ele | RLFA | MALTKY | Malten Switchgear Replacement KY | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-01-13 | 2015-12-31 | 2012-01-01
75084-DE Kentucky Power Deliv - Ele | NBFA | MATRETCAP | Material Returns Capital Only | 0 |  | 0 |  |  | 516.13 | 0 | 516.13 | 2012-08-28 | 2050-12-31 | 2014-03-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | MAXH | Enable Maximo Hardware | 3217.11 |  | 3217.11 | 100% |  | 3926.48 | 0 | 3926.48 | 2015-03-30 12:42 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | MAXS | Enable Maximo Software | 517494.72 |  | 517494.72 | 100% |  | 750022.8 | 0 | 750022.8 | 2015-03-30 14:04 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | RELDFA | MKRDYKY | Make Ready Kentucky | 71317.33 |  | 71317.33 | 100% |  | 120345.85 | 0 | 120345.85 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | MOBH | Enable Mobility Hardware | 49971.28 |  | 49971.28 | 100% |  | 52801.86 | 0 | 52801.86 | 2015-03-30 15:55 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | MOBS | Enable Mobility Software | 272763.44 |  | 272763.44 | 100% |  | 390553.88 | 0 | 390553.88 | 2015-03-30 14:54 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | MOFA | MOKY | Major Outage Followup-D | 1051.71 |  | 1051.71 | 100% |  | -4.3201e-12 | 0 | -4.3201e-12 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | FN1216KY | N1216SWKY | NINT1216 Tripwire Enterprise (TE) | -3142.78 |  | -3142.78 | 100% |  | 97284.18 | 0 | 97284.18 | 2014-08-08 | 2015-11-30 | 2014-08-01 | 2015-07-27
75084-DE Kentucky Power Deliv - Ele | FNETSCALR | N5103 | Upgrade to Net Scaler | 0 |  | 0 |  |  | 8180.46 | 0 | 8180.46 | 2014-06-25 | 2015-06-30 | 2014-07-01 | 2015-06-20
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7105 | Dixie Repl Sta Batteries | 0 |  | 0 |  |  | 5754.53 | 0 | 5754.53 | 2014-06-27 | 2015-03-31 | 2014-07-01 | 2014-11-11
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7106 | Hands Sub Repl Sta Batteries | 0 |  | 0 |  |  | 9574.12 | 0 | 9574.12 | 2014-06-27 | 2015-03-31 | 2014-07-01 | 2014-11-05
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | N7107 | Buffington Repl Cooling Fans | 0 |  | 0 |  |  | 6505.08 | 0 | 6505.08 | 2014-06-27 | 2015-03-31 | 2014-08-01 | 2014-11-25
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | N7108 | Wilder Repl Cooling Fans | 0 |  | 0 |  |  | 6432 | 0 | 6432 | 2014-06-27 | 2015-03-31 | 2014-08-01 | 2014-11-25
75084-DE Kentucky Power Deliv - Ele | UGCRFA | N8112 | UG 5759052 URD 52 Woodside Dr | 0 |  | 0 |  |  | 189919.24 | 158779.8 | 31139.44 | 2014-06-30 | 2015-06-30 | 2014-08-01 | 2015-03-02
75084-DE Kentucky Power Deliv - Ele | NBFA | NBKY | Customer Adds-MW-D | -530495.75 |  | -530495.75 | 100% |  | 5035250.82 | 0 | 5035250.82 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | NBFA | NBKYCI | Commerc & Indust Cust Adds-MW-D | 1025532.02 |  | 1025532.02 | 100% |  | 1025532.02 | 0 | 1025532.02 | 2016-01-21 13:58 | 2025-12-31 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | NBFA | NBKYRES | Residential Customer Adds-MW-D | 1640243.11 |  | 1640243.11 | 100% |  | 1640243.11 | 0 | 1640243.11 | 2016-01-21 13:51 | 2025-12-31 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | NEWCAPFA | NEWCAPKY | New Capacitors | 0 |  | 0 |  |  | 33297.67 | 0 | 33297.67 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | NINT686FP | NINT686 | NINT686 IEE C+I Upgrade Project | 0 |  | 0 |  |  | 4909.01 | 0 | 4909.01 | 2014-06-12 | 2014-10-23 | 2014-06-01 | 2015-04-15
75084-DE Kentucky Power Deliv - Ele | OM75084 | NONOLE | Overhead Non OLE Lt Insp/Maint | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2020-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NUPOLSET | Non Utility work-Exp | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | NUTRANSF | Transfers-other companies-exp | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2105 | Hebron Station eye wash station | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-11 | 2012-03-16 | 2014-08-01 | 2003-03-21
75084-DE Kentucky Power Deliv - Ele | DETCONFA | O2107 | DC 5809390 CRESCENT 42 | 0 |  | 0 |  |  | 503345.61 | 0 | 503345.61 | 2014-07-12 | 2016-01-31 | 2014-07-01 | 2015-07-14
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2111 | Mt Zion Remov eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2013-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2114 | Blackwell remove eyewas stat 7 gal | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2013-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2115 | York remove eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2012-03-16 | 2014-08-01 | 2012-05-21
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2116 | Dayton remove eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2012-03-16 | 2014-08-01 | 2012-05-12
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O2117 | Longbranch remove eye wash stat | 0 |  | 0 |  |  | 0 | 0 | 0 | 2014-07-14 | 2012-03-16 | 2014-09-01 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3102 | Cresent Repl 48VDC Sta Batteries | 0 |  | 0 |  |  | 9108.49 | 0 | 9108.49 | 2014-07-16 | 2015-03-31 | 2014-10-01 | 2015-06-02
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3103 | Bellevue Repl Sta Batteries | 10324.06 |  | 10324.06 | 100% |  | 18628.85 | 0 | 18628.85 | 2014-07-16 | 2016-09-30 | 2014-10-01 | 2016-04-13
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | O3106 | Cold Spring Repl Sta Batteries | 0 |  | 0 |  |  | 10700.12 | 0 | 10700.12 | 2014-07-16 | 2015-03-31 | 2014-08-01 | 2014-11-18
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O4106 | Hands Sub add gravel | 0 |  | 0 |  |  | 1493.02 | 0 | 1493.02 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-11-15
75084-DE Kentucky Power Deliv - Ele | BLDGSUBFA | O4112 | Buffington Sub Add Gravel | 0 |  | 0 |  |  | 805.92 | 0 | 805.92 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | NBFA | O4116 | NB 4714818 4455 Olympic Blvd | -375.74 |  | -375.74 | 100% |  | 11060.99 | 0 | 11060.99 | 2014-07-17 | 2015-11-28 | 2014-08-01 | 2014-10-17
75084-DE Kentucky Power Deliv - Ele | NBFA | O4137 | NB 4706432 629 Madison | 0 |  | 0 |  |  | 74218.76 | 0 | 74218.76 | 2014-07-21 | 2015-06-14 | 2014-07-01 | 2015-01-22
75084-DE Kentucky Power Deliv - Ele | AMKY0085A | O4164 | Wilder Inst 13kV CB 170 | 0 |  | 0 |  |  | 37736.03 | 0 | 37736.03 | 2014-07-23 | 2015-06-30 | 2014-08-01 | 2015-01-05
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | O5111 | Villa TB2 Repl Cooling Fans | 0 |  | 0 |  |  | 4543.82 | 0 | 4543.82 | 2014-07-25 | 2015-03-31 | 2014-08-01 | 2014-11-04
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | O6105 | Constance Repl TB1 Cooling Fans | 0 |  | 0 |  |  | 10180.71 | 0 | 10180.71 | 2014-07-28 | 2015-03-31 | 2014-08-01 | 2015-01-24
75084-DE Kentucky Power Deliv - Ele | RLFA | OHPCIKY | Mandated KY Overhead Prim Clearanc | 0 |  | 0 |  |  | -1.4552e-11 | 0 | -1.4552e-11 | 2010-12-22 | 2050-12-31 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | RLFA | OHPCIKY | Mandated KY Overhead Prim Clearanc | 0 |  | 0 |  |  | -1.4552e-11 | 0 | -1.4552e-11 | 2010-12-22 | 2050-12-31 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE08KY | Lighting-OLE-Inst | 0 |  | 0 |  |  | -3546.83 | 0 | -3546.83 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2008-12-20
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE08RPKY | Light Repl-OLE | 0 |  | 0 |  |  | 2.9559e-12 | 0 | 2.9559e-12 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-04-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OLE09KY | Lighting-OLE-Inst | 0 |  | 0 |  |  | 11031.05 | 0 | 11031.05 | 2009-01-02 | 2050-12-31 | 2009-01-01 | 2009-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | OLE09RPKY | Light Repl-OLE | 0 |  | 0 |  |  | 914.48 | 0 | 914.48 | 2009-01-02 | 2050-12-31 | 2009-02-01 | 2009-12-31
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE11KY | Lighting-OLE-Inst-2011 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-01-04 | 2012-12-31 | 2011-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE11RPKY | Light Repl-OLE-2011 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2011-01-04 | 2050-12-31 | 2011-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE12KY | Kentucky Lighting OLE Install 2012 | 0 |  | 0 |  |  | 84224.87 | 0 | 84224.87 | 2011-11-14 | 2013-06-01 | 2011-12-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE12RPKY | Kentucky Lighting Replace OLE 2012 | 0 |  | 0 |  |  | 450 | 0 | 450 | 2011-11-14 | 2013-06-01 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE13KY | Kentucky Lighting OLE Install 2013 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2013-01-04 | 2014-10-01 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLE13RPKY | Kentucky Lighting OLE Replace 2013 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2013-01-04 | 2014-10-01 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE14KY | Kentuck Lighting OLE Install 2014 | 0 |  | 0 |  |  | 2.8422e-14 | 0 | 2.8422e-14 | 2014-01-02 | 2015-09-30 | 2014-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLE14KY | Kentuck Lighting OLE Install 2014 | 0 |  | 0 |  |  | 2.8422e-14 | 0 | 2.8422e-14 | 2014-01-02 | 2015-09-30 | 2014-01-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | OLEINT | OLE Interest | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-10-01
75084-DE Kentucky Power Deliv - Ele | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | 474643.97 |  | 474643.97 | 100% |  | 746011.1 | 0 | 746011.1 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084-DE Kentucky Power Deliv - Ele | OLE08RPFA | OLERPKY | Kentcky Lighting Replacement - OLE | 2327.11 |  | 2327.11 | 100% |  | 2954.84 | 0 | 2954.84 | 2014-08-04 | 2020-12-31 | 2015-12-01
75084-DE Kentucky Power Deliv - Ele | FORCHARDK | ORCHARDKE | 1140 ORCHARD ST-YORK SUB-KENTUCKY | 0 |  | 0 |  |  | 28802.78 | 0 | 28802.78 | 2010-07-21 | 2010-10-01 | 2010-07-01 | 2011-03-31
75084-DE Kentucky Power Deliv - Ele | MTRCAPFA | ORDERTRK | Assemble Meter Sets | 0 |  | 0 |  |  | 171034.69 | 0 | 171034.69 | 2008-07-01 | 2025-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | ORDKY | Outage Restoration Cap-D | 1365.81 |  | 1365.81 | 100% |  | 159705.12 | 0 | 159705.12 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | ORTFA | ORTKY | Outage Restoration Cap-T | -20829.87 |  | -20829.87 | 100% |  | 18876.33 | 0 | 18876.33 | 2010-06-28 | 2050-12-31 | 2011-04-01
75084-DE Kentucky Power Deliv - Ele | CAPFA | OTVSRKY | Cap Oil to Vac Switch Repl KY | 0 |  | 0 |  |  | 7.1054e-15 | 0 | 7.1054e-15 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | OUTAGES | Routine Outages | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OUTOHRLKY | Outage Replace OH - Kentucky | 756214 |  | 756214 | 100% |  | 756214 | 0 | 756214 | 2015-06-13 14:20 | 2025-12-31 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OUTRFUKY | Outage Reliability FollowUp Capital | 33520.24 |  | 33520.24 | 100% |  | 0 | 0 | 0 | 2012-05-09 | 2050-12-31 | 2012-09-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | OUTUGRLKY | Outage Replace UG - Kentucky | 520863.3 |  | 520863.3 | 100% |  | 520863.3 | 0 | 520863.3 | 2015-06-13 14:34 | 2025-12-31 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | P0104 | RI 6000526 Newport High School | 238165.42 |  | 238165.42 | 100% |  | 304987.99 | 0 | 304987.99 | 2014-08-04 | 2016-11-15 | 2014-09-01 | 2016-08-22
75084-DE Kentucky Power Deliv - Ele | RELDFA | P6165 | RI 4183102 Lowell St (Rt. 9) | -18760.35 |  | -18760.35 | 100% |  | 266586.87 | 0 | 266586.87 | 2014-08-22 | 2016-03-14 | 2014-10-01 | 2015-07-27
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | P6216 | Wilder Repl TB1 Cooling Fans | 0 |  | 0 |  |  | 16403.43 | 0 | 16403.43 | 2014-08-28 | 2015-03-31 | 2014-09-01 | 2015-01-06
75084-DE Kentucky Power Deliv - Ele | CSFA | P6373 | CS 5062969 Cold Spring 49 | 0 |  | 0 |  |  | 87183.71 | 0 | 87183.71 | 2014-09-24 | 2016-03-31 | 2014-10-01 | 2015-05-24
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P6425 | Limaburg TB1 Repl Cooling Fans | 22756.14 |  | 22756.14 | 100% |  | 44249.65 | 0 | 44249.65 | 2014-09-29 | 2015-03-31 | 2014-11-01 | 2016-02-04
75084-DE Kentucky Power Deliv - Ele | AMKY1396 | P6550 | AM 6394804 Kenton 44 12kv | 0 |  | 0 |  |  | 507172.02 | 0 | 507172.02 | 2014-10-09 | 2016-03-31 | 2014-10-01 | 2015-07-09
75084-DE Kentucky Power Deliv - Ele | AMKY1176 | P6679 | Villa CCVT Repl | 0 |  | 0 |  |  | 42601.38 | 0 | 42601.38 | 2014-10-27 | 2016-03-31 | 2014-11-01 | 2015-09-13
75084-DE Kentucky Power Deliv - Ele | AMKY1396 | P6708 | AM 6394817 Kenton 44 Pt 2 reloc | -3183.55 |  | -3183.55 | 100% |  | 251805.32 | 0 | 251805.32 | 2014-10-31 | 2016-03-31 | 2014-11-01 | 2016-01-23
75084-DE Kentucky Power Deliv - Ele | NBFA | P6718 | NB 5846054 Sunny Ridge Estates | 0 |  | 0 |  |  | 58571.71 | 0 | 58571.71 | 2014-10-31 | 2015-11-26 | 2014-12-01 | 2015-07-28
75084-DE Kentucky Power Deliv - Ele | TMAJRIFA1 | P6992 | Mt Zion TB1 Repl HS Bushings | 68.9 |  | 68.9 | 100% |  | 51523.6 | 0 | 51523.6 | 2014-12-08 | 2016-03-31 | 2015-05-01 | 2016-01-05
75084-DE Kentucky Power Deliv - Ele | NBFA | P7033 | NB 6573310 15 Spiral Dr | 0 |  | 0 |  |  | 41380.3 | 0 | 41380.3 | 2014-12-12 | 2015-11-01 | 2014-12-01 | 2015-08-12
75084-DE Kentucky Power Deliv - Ele | DETCONFA | P7106 | DET 6589503 Cold Spring 49 | 0 |  | 0 |  |  | 68728.44 | 0 | 68728.44 | 2014-12-18 | 2016-03-31 | 2014-12-01 | 2015-08-26
75084-DE Kentucky Power Deliv - Ele | NBFA | P7171 | NB 6319774 Arcadia Ph B | 0 |  | 0 |  |  | 105380.74 | 0 | 105380.74 | 2014-12-30 | 2015-09-30 | 2015-01-01 | 2015-07-28
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P7228 | Cold Spring Repl Xtr bushings | 0 |  | 0 |  |  | 15674.09 | 0 | 15674.09 | 2015-01-09 | 2016-03-31 | 2015-01-01 | 2015-09-15
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7272 | DEC 6892552 Oakbrook 41 | -6384.96 |  | -6384.96 | 100% |  | 53579.84 | 0 | 53579.84 | 2015-01-14 | 2016-07-30 | 2015-02-01 | 2016-04-26
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7273 | DEC 6892574 Donaldson 41 | 100774.25 |  | 100774.25 | 100% |  | 132910.79 | 0 | 132910.79 | 2015-01-14 | 2017-11-15 | 2015-01-01 | 2017-10-27
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7274 | DEC 6892567 Donaldson 41 | 39734.04 |  | 39734.04 | 100% |  | 88282.82 | 0 | 88282.82 | 2015-01-14 | 2018-06-30 | 2015-01-01
75084-DE Kentucky Power Deliv - Ele | DECCIRFA | P7275 | DEC 6892560 Oakbrook 42 | 72817.53 |  | 72817.53 | 100% |  | 117180.18 | 0 | 117180.18 | 2015-01-14 | 2016-10-31 | 2015-01-01 | 2016-07-05
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P7314 | Donaldson TB1 Bushings | 16851.85 |  | 16851.85 | 100% |  | 22817.85 | 0 | 22817.85 | 2015-01-16 | 2018-03-01 | 2015-03-01 | 2016-12-31
75084-DE Kentucky Power Deliv - Ele | AMKY1168 | P7405 | KY Univ Bus 4 Swgr and CB Repl | 1510530.16 |  | 1510530.16 | 100% |  | 1822233.55 | 0 | 1822233.55 | 2015-01-22 | 2017-03-31 | 2015-02-01 | 2017-03-02
75084-DE Kentucky Power Deliv - Ele | CP15BATK | P7421 | Florence Repl Batteries | 0 |  | 0 |  |  | 7039.25 | 0 | 7039.25 | 2015-01-23 | 2016-03-31 | 2015-04-01 | 2015-07-15
75084-DE Kentucky Power Deliv - Ele | CSFA | P7652 | DA 6897728 Augustine 46 | -1645.65 |  | -1645.65 | 100% |  | 80214.67 | 0 | 80214.67 | 2015-02-06 | 2016-03-31 | 2015-04-01 | 2016-01-29
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P8327 | Constance Repl Station Batt | 7491.4 |  | 7491.4 | 100% |  | 15531.16 | 0 | 15531.16 | 2015-03-17 11:25 | 2016-03-31 | 2015-03-01 | 2015-07-31
75084-DE Kentucky Power Deliv - Ele | FNINT874 | P9120 | Substation Entry Log IVR | 0 |  | 0 |  |  | 14496.64 | 0 | 14496.64 | 2015-03-23 12:54 | 2015-07-31 | 2015-04-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | DMAJRIFA | P9531 | Villa Repl TB1 Arresters | 0 |  | 0 |  |  | 2868.84 | 0 | 2868.84 | 2015-03-27 08:34 | 2016-03-31 | 2015-04-01 | 2015-08-18
75084-DE Kentucky Power Deliv - Ele | DPEQUIPFA | P9532 | Atlas Repl Station batteries | 0 |  | 0 |  |  | 1590.37 | 0 | 1590.37 | 2015-03-27 09:13 | 2016-03-31 | 2015-07-01 | 2015-11-30
75084-DE Kentucky Power Deliv - Ele | FDOMSIMPL | PCTAIT223 | DOMS IMPLEMENTATION W/AMI | 22724.89 |  | 22724.89 | 100% |  | 213833.92 | 0 | 213833.92 | 2013-10-25 | 2016-12-31 | 2013-11-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 10378.15 |  | 10378.15 | 100% |  | 69474.32 | 0 | 69474.32 | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75084-DE Kentucky Power Deliv - Ele | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | -75.19 |  | -75.19 | 100% |  | 10429.24 | 0 | 10429.24 | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75084-DE Kentucky Power Deliv - Ele | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 111620.8 |  | 111620.8 | 100% |  | 268610.39 | 0 | 268610.39 | 2015-11-02 12:18 | 2017-09-30 | 2015-10-01 | 2017-07-31
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITH31 | INT165 Hardware | 1.26 |  | 1.26 | 100% |  | 2522.34 | 0 | 2522.34 | 2014-08-14 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF6 | PCTAITH61 | INT83 Hardware | 0 |  | 0 |  |  | 1717.8 | 0 | 1717.8 | 2014-08-18 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITQ03 | INT165 EI 1 Software | 0 |  | 0 |  |  | 48.8 | 0 | 48.8 | 2014-08-17 | 2018-01-31 | 2015-01-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITS31 | INT165 Software | 0 |  | 0 |  |  | 11072.02 | 0 | 11072.02 | 2014-08-14 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITS41 | INT177 Software | 40.54 |  | 40.54 | 100% |  | 7675.25 | 0 | 7675.25 | 2014-07-28 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF5 | PCTAITS51 | INT82b Software | 0 |  | 0 |  |  | 3303.17 | 0 | 3303.17 | 2014-08-17 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF6 | PCTAITS61 | INT83 Software | 0 |  | 0 |  |  | 3800.24 | 0 | 3800.24 | 2014-08-18 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITX03 | INT165 X 1 SOFTWARE | 0 |  | 0 |  |  | 48361.43 | 0 | 48361.43 | 2014-08-24 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF3 | PCTAITX04 | INT165 X 1 Hardware | 0 |  | 0 |  |  | 2311.43 | 0 | 2311.43 | 2014-08-24 | 2018-04-30 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITX07 | INT177 X 2 SOFTWARE | 0 |  | 0 |  |  | 5308.86 | 0 | 5308.86 | 2014-08-24 | 2018-01-31 | 2014-12-01
75084-DE Kentucky Power Deliv - Ele | PCTAITF4 | PCTAITX10 | INT177 X 3 Software | 0 |  | 0 |  |  | 7260.01 | 0 | 7260.01 | 2014-08-24 | 2018-01-31 | 2014-09-01
75084-DE Kentucky Power Deliv - Ele | FENRGACCT | PCTASW937 | Energy Acctg. & Transm Stand. | 2406.26 |  | 2406.26 | 100% |  | 114896.46 | 0 | 114896.46 | 2014-07-09 | 2016-04-30 | 2014-08-01 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | PCTAIT85C | PCTAT85C | NetMotion Implementation INT85C | 2257.07 |  | 2257.07 | 100% |  | 55715.65 | 0 | 55715.65 | 2014-06-08 | 2017-03-30 | 2014-06-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | FPCTAVM | PCTAVM | VEGETATION MGMT-KENTUCKY | 0 |  | 0 |  |  | 10.94 | 0 | 10.94 | 2012-11-30 | 2018-01-31 | 2013-01-01
75084-DE Kentucky Power Deliv - Ele | PCTA82F | PCTAVS82F | INT82F-EGIS Web Tool | 4159.53 |  | 4159.53 | 100% |  | 4159.53 | 0 | 4159.53 | 2014-07-22 | 2016-07-30 | 2016-04-01 | 2016-07-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | PDOHRPLKY | Public Damage Replace OH - Kentucky | 73882.41 |  | 73882.41 | 100% |  | 73882.41 | 0 | 73882.41 | 2015-06-13 14:43 | 2025-12-31 | 2016-02-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | PDUGRPLKY | Public Damage Replace UG - Kentucky | 55949.25 |  | 55949.25 | 100% |  | 55949.25 | 0 | 55949.25 | 2015-06-13 14:53 | 2025-12-31 | 2016-03-01
75084-DE Kentucky Power Deliv - Ele | PILCFA | PILCKY | UG Cable Repl-PILC | 42.29 |  | 42.29 | 100% |  | 16278.65 | 0 | 16278.65 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | PILCFA | POTTKY | Dline Pothead Termination KY | 0 |  | 0 |  |  | -3.638e-12 | 0 | -3.638e-12 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | FENABLES | PPS | Enable PowerPlan Software | 41693.52 |  | 41693.52 | 100% |  | 58009.08 | 0 | 58009.08 | 2015-03-30 15:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | PRDFA | PRDKY | Pole Repl Other-D | -635.35 |  | -635.35 | 100% |  | 777673.76 | 0 | 777673.76 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | PRIMH | Enable Primavera Hardware | 1294.44 |  | 1294.44 | 100% |  | 2083.74 | 0 | 2083.74 | 2015-03-30 16:23 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | PRIMS | Enable Primavera Software | 59219.08 |  | 59219.08 | 100% |  | 70275.21 | 0 | 70275.21 | 2015-03-30 15:12 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | PRTFA | PRTKY | Pole Repl Other-T | 5608.42 |  | 5608.42 | 100% |  | 238967.81 | 0 | 238967.81 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | FFLTRET | R6222 | DEK Vehicle Retirements | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-01-28 07:39 | 2016-02-29 | 2016-02-01 | 2016-05-31
75084-DE Kentucky Power Deliv - Ele | FRAC&SWCH | RAC&SWCHK | RACK & SWITCH INSTALLS | 0 |  | 0 |  |  | 3759.59 | 0 | 3759.59 | 2010-12-02 | 2010-12-31 | 2011-03-01 | 2011-08-01
75084-DE Kentucky Power Deliv - Ele | FRADIOKY | RADIOKENT | IDEN RADIO-KENTUCKY PROJECT | 0 |  | 0 |  |  | 366057.54 | 0 | 366057.54 | 2010-01-15 | 2011-07-31 | 2010-02-01 | 2011-09-01
75084-DE Kentucky Power Deliv - Ele | UGCIFA | RCABINJKY | Reactive Cable Replacement Kentucky | 0 |  | 0 |  |  | 0 | 250000 | -250000 | 2012-11-16 | 2050-12-31 | 2013-03-01
75084-DE Kentucky Power Deliv - Ele | RCLFA | RCLKY | Recloser Inst/Rem | -85.42 |  | -85.42 | 100% |  | 73352.05 | 0 | 73352.05 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | REGFA | REGKY | Regulator Inst/Rem | 0 |  | 0 |  |  | -1.3074e-12 | 0 | -1.3074e-12 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RELDFA | RELDKY | Relocation-D | 11589.98 |  | 11589.98 | 100% |  | 667636.93 | 0 | 667636.93 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RELTFA | RELTKY | Relocation-T | 13.33 |  | 13.33 | 100% |  | 322488.06 | 0 | 322488.06 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | 75084 | RETCOV | Retire Covington | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-12-20 | 2013-01-05 | 2012-12-01 | 2013-04-05
75084-DE Kentucky Power Deliv - Ele | RLFA | RLKY | Reliability Other-FO-D | 152535.1 |  | 152535.1 | 100% |  | 713420.99 | 0 | 713420.99 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | RLFA | RNOVAKY | Cooper Nova Replacement | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-11-02 | 2050-12-31 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | FRR19&AUG | RR19&AUG | 19TH & AUGUSTINE CC RR BLKT | 0 |  | 0 |  |  | 15188.13 | 0 | 15188.13 | 2010-08-30 | 2025-12-15 | 2010-11-01
75084-DE Kentucky Power Deliv - Ele | RRBLKKENT | RRCRITTEN | Critenden Substation Blanket | -639.13 |  | -639.13 | 100% |  | -67.72 | 0 | -67.72 | 2013-09-09 | 2050-12-15 | 2013-09-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRERLANG | ERLANGER CC RR BLKT | 0 |  | 0 |  |  | 27778.55 | 0 | 27778.55 | 2010-08-30 | 2025-12-15 | 2010-11-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRERLNGMW | ERLANGER MICROWAV-RR BLKT | 0 |  | 0 |  |  | 1122.18 | 0 | 1122.18 | 2011-05-09 | 2025-12-15 | 2011-10-01
75084-DE Kentucky Power Deliv - Ele | FRRERLANG | RRKENTON | Kenton Substation Blanket | 0 |  | 0 |  |  | 139.45 | 0 | 139.45 | 2012-07-27 | 2025-12-15 | 2012-07-01
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANHWKE | SAN EXPANSION - EMC NS-960 | 0 |  | 0 |  |  | 17560.4 | 0 | 17560.4 | 2010-11-19 | 2011-03-31 | 2010-12-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANSWKE | SAN EXPANSION SOFTWARE | 0 |  | 0 |  |  | 4451.2 | 0 | 4451.2 | 2010-11-19 | 2011-03-31 | 2010-12-01 | 2011-06-30
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANUPGRKE | SAN FIBR CHANNEL SWCH UPGR | 0 |  | 0 |  |  | 3645.7 | 0 | 3645.7 | 2012-09-05 | 2013-02-18 | 2012-10-01 | 2013-06-13
75084-DE Kentucky Power Deliv - Ele | FSANEXPKE | SANXP12KE | SAN EXPANSION - EMC NS-960 | 0 |  | 0 |  |  | 9398.11 | 0 | 9398.11 | 2012-03-06 | 2012-05-15 | 2012-05-01 | 2012-08-15
75084-DE Kentucky Power Deliv - Ele | SCFOFA | SCFOKY | System Capacity-FO | 909.6 |  | 909.6 | 100% |  | 149408.65 | 0 | 149408.65 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | MTRCAPFA | SCRAPMETK | Scrap Meters | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2025-12-31 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 38796.67 |  | 38796.67 | 100% |  | 44638.76 | 0 | 44638.76 | 2015-03-30 14:43 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | CSFA | SDKYT111 | Villa 41, Crescent 41, Constance 44 | 0 |  | 0 |  |  | 179948.64 | 0 | 179948.64 | 2011-08-03 | 2012-12-31 | 2011-09-01 | 2012-03-12
75084-DE Kentucky Power Deliv - Ele | 75084 | SFTWRE | Software Retirements-Asset Use | 0 |  | 0 |  |  | 0 | 0 | 0 | 2012-09-20 | 2026-03-30 | 2012-09-01
75084-DE Kentucky Power Deliv - Ele | SGEAMIOCF | SG305SVRS | SG DEE OpenWay Ops Center Servers | 4153.99 |  | 4153.99 | 100% |  | 4153.99 | 0 | 4153.99 | 2016-09-06 11:56 | 2018-09-12 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | SGEAMIOCF | SG305SW | SG DEE OpenWay Ops Center Software | 6746.16 |  | 6746.16 | 100% |  | 6746.16 | 0 | 6746.16 | 2016-08-01 10:09 | 2018-09-12 | 2016-08-01
75084-DE Kentucky Power Deliv - Ele | SG000336F | SG336SW | SG DEE DMS ADMS - Software | 11395.19 |  | 11395.19 | 100% |  | 11395.19 | 0 | 11395.19 | 2016-09-06 17:51 | 2021-04-01 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | SGAMF | SG344SW | SG DEE Distrib System Health - SW | 9203.36 |  | 9203.36 | 100% |  | 9203.36 | 0 | 9203.36 | 2015-12-18 14:25 | 2019-04-24 | 2016-01-01
75084-DE Kentucky Power Deliv - Ele | SG000358F | SG358CALL | SG 358 - DEE MDM Scale CA Lisa SW | 7528.44 |  | 7528.44 | 100% |  | 7528.44 | 0 | 7528.44 | 2016-06-17 11:48 | 2017-06-30 | 2016-08-01 | 2017-06-26
75084-DE Kentucky Power Deliv - Ele | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 83332.64 |  | 83332.64 | 100% |  | 83332.64 | 0 | 83332.64 | 2016-06-20 09:18 | 2017-06-30 | 2016-06-01 | 2017-06-26
75084-DE Kentucky Power Deliv - Ele | SG000358F | SG358SGGL | SG 358 - DEE MDM Scale - SGG Licens | 29865.9 |  | 29865.9 | 100% |  | 29865.9 | 0 | 29865.9 | 2016-06-17 13:41 | 2017-06-30 | 2016-07-01 | 2017-06-26
75084-DE Kentucky Power Deliv - Ele | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 292.2 |  | 292.2 | 100% |  | 292.2 | 0 | 292.2 | 2016-11-01 13:54 | 2018-02-28 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | SGDMSCF | SG361SW | SG DEE DMS Project 10 SW | 1057.85 |  | 1057.85 | 100% |  | 1057.85 | 0 | 1057.85 | 2015-12-18 15:11 | 2019-03-31 | 2016-01-01
75084-DE Kentucky Power Deliv - Ele | SG000430F | SG430A | Aero Pkwy Instl UG Conduit | 1373978.44 |  | 1373978.44 | 100% |  | 1373978.44 | 0 | 1373978.44 | 2016-04-04 13:28 | 2018-03-31 | 2016-04-01
75084-DE Kentucky Power Deliv - Ele | SG000430F | SG430B | Aero Pkwy Instl UG Cable | 10415.6 |  | 10415.6 | 100% |  | 10415.6 | 0 | 10415.6 | 2016-04-04 13:41 | 2018-03-31 | 2016-04-01
75084-DE Kentucky Power Deliv - Ele | SG000430F | SG430C | Aero Pkwy Instl OH | 65258.02 |  | 65258.02 | 100% |  | 65258.02 | 0 | 65258.02 | 2016-04-04 13:42 | 2017-09-01 | 2016-04-01 | 2016-12-02
75084-DE Kentucky Power Deliv - Ele | SG000448F | SG448SVR | SG DEE Openway Scale 2016 - Servers | 3032.32 |  | 3032.32 | 100% |  | 3032.32 | 0 | 3032.32 | 2016-07-13 17:28 | 2017-03-31 | 2016-07-01 | 2017-03-14
75084-DE Kentucky Power Deliv - Ele | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 851.7 |  | 851.7 | 100% |  | 851.7 | 0 | 851.7 | 2016-11-23 11:18 | 2017-11-30 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | -306.94 |  | -306.94 | 100% |  | 51858 | 0 | 51858 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | SGAMIDMS | SGADMS33 | SG Upgrade Alstom DMS to ver 3.3 | 21224.29 |  | 21224.29 | 100% |  | 136473.97 | 0 | 136473.97 | 2014-12-18 | 2016-07-20 | 2014-12-01 | 2016-07-15
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGAMIDOM | SG AMI to DOMS Outage Capital | 0 |  | 0 |  |  | 39944.15 | 0 | 39944.15 | 2011-05-26 | 2011-12-16 | 2011-06-01 | 2012-03-13
75084-DE Kentucky Power Deliv - Ele | SGITOMSGI | SGARCSRVC | Smart Grid ARC Server Project | 0 |  | 0 |  |  | 24134.87 | 0 | 24134.87 | 2010-09-24 | 2010-11-30 | 2010-10-01 | 2011-03-08
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGBRWTRH | Bridgewater AAA Implement HW | 0 |  | 0 |  |  | 1860.57 | 0 | 1860.57 | 2011-12-08 | 2009-02-19 | 2011-12-01 | 2009-05-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGBRWTRS | Bridgewater AAA Implement SW | 0 |  | 0 |  |  | 4391.55 | 0 | 4391.55 | 2011-12-01 | 2009-02-19 | 2011-12-01 | 2009-05-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGCAMIHW | Smart Grid Carolinas AMI Hardware | 0 |  | 0 |  |  | 27968.85 | 0 | 27968.85 | 2012-08-10 | 2012-12-31 | 2012-08-01 | 2013-03-20
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGCAPRIKY | SG Kentucky Capacitors for R&I | 0 |  | 0 |  |  | 214460.46 | 0 | 214460.46 | 2013-11-01 | 2015-03-30 | 2013-12-01
75084-DE Kentucky Power Deliv - Ele | SGKYCS | SGCSDCI3 | ECS daily usage cap | 0 |  | 0 |  |  | 12362.77 | 0 | 12362.77 | 2010-10-01 | 2014-12-31 | 2010-09-01 | 2010-06-24
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGCSRIKY | Circuit Sectionalization - KY | 41659.98 |  | 41659.98 | 100% |  | 0 | 0 | 0 | 2013-05-24 | 2015-06-30 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDADMS | Dist Mgt Sys cap | 0 |  | 0 |  |  | 1489518.8 | 0 | 1489518.8 | 2010-10-01 | 2014-07-30 | 2010-09-01 | 2014-05-19
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDEETHW | SG DMS Distribution DEETS HW | 0 |  | 0 |  |  | 7954.17 | 0 | 7954.17 | 2011-09-30 | 2014-10-31 | 2011-11-01 | 2013-07-29
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGDEETSW | SG DMS Distribution DEETS SW | 0 |  | 0 |  |  | 18945.76 | 0 | 18945.76 | 2011-09-30 | 2014-10-31 | 2011-10-01 | 2013-07-29
75084-DE Kentucky Power Deliv - Ele | SGEDMS3F | SGDMS3SW | DEE DMS 3.5 Upgrade - Software | 34070.74 |  | 34070.74 | 100% |  | 34070.74 | 0 | 34070.74 | 2015-11-19 10:10 | 2018-05-15 | 2016-09-01
75084-DE Kentucky Power Deliv - Ele | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 0 |  | 0 |  |  | 61898.59 | 0 | 61898.59 | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGECHLDA | SG Echelon Local Data Access | 0 |  | 0 |  |  | 8364.35 | 0 | 8364.35 | 2010-09-30 | 2014-12-31 | 2010-09-01 | 2011-02-01
75084-DE Kentucky Power Deliv - Ele | SGETOASF | SGECOA | SG COA Software | 15843.84 |  | 15843.84 | 100% |  | 15843.84 | 0 | 15843.84 | 2016-03-31 15:37 | 2017-09-30 | 2016-04-01 | 2017-09-08
75084-DE Kentucky Power Deliv - Ele | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 1444.1 |  | 1444.1 | 100% |  | 9104.79 | 0 | 9104.79 | 2015-06-10 18:11 | 2016-08-21 | 2015-06-01 | 2016-06-04
75084-DE Kentucky Power Deliv - Ele | SGETOASF | SGETOAS | SG TOA Replacement Software | 96814.37 |  | 96814.37 | 100% |  | 117695.82 | 0 | 117695.82 | 2015-04-06 13:58 | 2019-03-27 | 2015-05-01
75084-DE Kentucky Power Deliv - Ele | SG000437F | SGHYDRKY | DEK Recloser Replacements | 1902.4 |  | 1902.4 | 100% |  | 1902.4 | 0 | 1902.4 | 2016-05-16 10:20 | 2025-12-31 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0 |  | 0 |  |  | 132348 | 0 | 132348 | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGITRNSLH | ITRON SG Solutions Hardware | 0 |  | 0 |  |  | 3779.19 | 0 | 3779.19 | 2011-07-14 | 2012-06-30 | 2011-10-01 | 2012-08-31
75084-DE Kentucky Power Deliv - Ele | SGITRONLF | SGITRONL | SG Itron Meter Licenses | 72.02 |  | 72.02 | 100% |  | 148753.18 | 0 | 148753.18 | 2015-12-30 11:54 | 2016-04-30 | 2015-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGCIAMIF | SGKAMICI | SG Kentucky C&I AMI Meters | 302078.67 |  | 302078.67 | 100% |  | 395744.77 | 0 | 395744.77 | 2015-05-29 12:53 | 2018-05-15 | 2015-09-01
75084-DE Kentucky Power Deliv - Ele | SGKAMIF | SGKAMIMGT | DEK AMI Mgmt Project | 179095.51 |  | 179095.51 | 100% |  | 179095.51 | 0 | 179095.51 | 2016-01-20 16:12 | 2018-03-30 | 2016-01-01
75084-DE Kentucky Power Deliv - Ele | SGNMS | SGKIPV6ML | SG DEK ITRON Software NMS Endpoints | 0 |  | 0 |  |  | 585678.5 | 0 | 585678.5 | 2014-06-27 | 2015-01-31 | 2014-08-01 | 2014-12-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGKTLPLC | SG DEK Trans Pole Replacement | 0 |  | 0 |  |  | 31804.45 | 0 | 31804.45 | 2014-09-12 | 2015-06-30 | 2014-10-01
75084-DE Kentucky Power Deliv - Ele | SGEZYWANF | SGKZYWAN | SG KY ZyWAN Modem Replace | 1408.88 |  | 1408.88 | 100% |  | 17903.34 | 0 | 17903.34 | 2015-06-11 15:04 | 2016-03-15 | 2015-06-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGLSRIKY | SG KY Line Sensor Project for R&I | 0 |  | 0 |  |  | 350451.47 | 0 | 350451.47 | 2013-11-01 | 2015-03-30 | 2013-12-01
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMFDHW | SG MDM Foundation Hardware | 0 |  | 0 |  |  | 73191.26 | 0 | 73191.26 | 2012-04-20 | 2013-10-31 | 2012-05-01 | 2013-10-29
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMFDSW | SG MDM Foundation Custom SW | 0 |  | 0 |  |  | 509256.19 | 0 | 509256.19 | 2012-04-20 | 2013-10-31 | 2012-04-01 | 2013-10-29
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMM2C | SG MDM Mass Market 2 - CMS Work | 3320.17 |  | 3320.17 | 100% |  | 3323.78 | 0 | 3323.78 | 2014-11-03 | 2015-02-16 | 2014-11-01 | 2015-02-17
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | -3320.17 |  | -3320.17 | 100% |  | 37438.49 | 0 | 37438.49 | 2014-04-28 | 2015-02-16 | 2014-04-01 | 2015-02-17
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMMH | SG MDM Mass Market Hardware | 0 |  | 0 |  |  | 10834.61 | 0 | 10834.61 | 2013-07-10 | 2014-09-30 | 2013-12-01 | 2014-08-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0 |  | 0 |  |  | 183577.67 | 0 | 183577.67 | 2013-07-10 | 2014-09-30 | 2013-07-01 | 2014-08-19
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMS | Meter Data Management System | 0 |  | 0 |  |  | 197462 | 0 | 197462 | 2011-11-30 | 2010-06-18 | 2011-11-01 | 2010-09-18
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 0 |  | 0 |  |  | 71270.12 | 0 | 71270.12 | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGMGTRIKY | SG KY Sectionalization R&I Mgmt Prj | 0 |  | 0 |  |  | 0 | 0 | 0 | 2013-11-01 | 2015-03-30 | 2013-12-01 | 2015-03-15
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGMWSCADH | Smart Grid Midwest SCADA Hardware | 0 |  | 0 |  |  | 14317.22 | 0 | 14317.22 | 2011-06-29 | 2011-12-31 | 2011-10-01 | 2011-08-31
75084-DE Kentucky Power Deliv - Ele | SGKYDMS | SGMWSCADS | Smart Grid Midwest SCADA Software | 0 |  | 0 |  |  | 133886.34 | 0 | 133886.34 | 2011-06-29 | 2011-12-31 | 2011-10-01 | 2011-08-31
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGNDENSW | Echelon NET SW Cap | 0 |  | 0 |  |  | 31031.1 | 0 | 31031.1 | 2010-09-30 | 2014-12-31 | 2010-09-01 | 2011-03-10
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG36 | NES 3.0 Upgrade SGS.036 | 0 |  | 0 |  |  | 3818.02 | 0 | 3818.02 | 2011-12-02 | 2009-03-18 | 2011-12-01 | 2009-06-18
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG38 | NES EM System SGS.038 | 0 |  | 0 |  |  | 5685.2 | 0 | 5685.2 | 2011-12-06 | 2009-10-20 | 2011-12-01 | 2010-01-20
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG45H | NES Test Envir SGS.045 HW | 0 |  | 0 |  |  | 3493.06 | 0 | 3493.06 | 2011-12-06 | 2009-10-22 | 2011-12-01 | 2010-01-22
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG45S | NES Test Envir SGS.045 SW | 0 |  | 0 |  |  | 7913.38 | 0 | 7913.38 | 2011-12-08 | 2009-10-22 | 2011-12-01 | 2010-01-22
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNDSG51 | NES 4.1 Upgrade SGS.051 | 0 |  | 0 |  |  | 15797.81 | 0 | 15797.81 | 2011-12-08 | 2010-12-10 | 2011-12-01 | 2011-03-10
75084-DE Kentucky Power Deliv - Ele | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 0 |  | 0 |  |  | 18566.54 | 0 | 18566.54 | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNNT435H | SG Openway Scale-up Hardware | 0 |  | 0 |  |  | 7630.72 | 0 | 7630.72 | 2012-07-27 | 2013-08-01 | 2012-09-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | 0 |  | 0 |  |  | 57834.44 | 0 | 57834.44 | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75084-DE Kentucky Power Deliv - Ele | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 0 |  | 0 |  |  | 4758.71 | 0 | 4758.71 | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75084-DE Kentucky Power Deliv - Ele | SGNNT1021 | SGNT1021B | SG NINT1021B - SERVERS | 0 |  | 0 |  |  | 220.7 | 0 | 220.7 | 2014-04-30 | 2014-11-30 | 2014-08-01 | 2015-02-01
75084-DE Kentucky Power Deliv - Ele | SGKYPMO | SGOVH | Grid Solutions Overhead Allocation | 95.57 |  | 95.57 | 100% |  | 95.57 | 0 | 95.57 | 2016-01-08 16:23 | 2050-12-31 | 2016-01-01
75084-DE Kentucky Power Deliv - Ele | SGCSFA | SGRCRIKY | SG DEK Reserve Capacity Meters | 0 |  | 0 |  |  | 114673.9 | 0 | 114673.9 | 2014-05-12 | 2015-03-30 | 2014-06-01 | 2015-04-30
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGROFEDM6 | Remote Order Fulfillment EDM.06 | 0 |  | 0 |  |  | 15632.51 | 0 | 15632.51 | 2011-12-08 | 2009-03-19 | 2011-12-01 | 2009-06-19
75084-DE Kentucky Power Deliv - Ele | SG000434F | SGRTPKY | DEK Upgrade Dist Trans Stations | 2083.25 |  | 2083.25 | 100% |  | 2083.25 | 0 | 2083.25 | 2016-05-16 10:10 | 2025-12-31 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | SG000444F | SGRTRKY | DEK Upgrade Livefront Transformers | 1630.87 |  | 1630.87 | 100% |  | 1630.87 | 0 | 1630.87 | 2016-05-16 10:12 | 2025-12-31 | 2016-07-01
75084-DE Kentucky Power Deliv - Ele | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -473.84 |  | -473.84 | 100% |  | 6.74 | 0 | 6.74 | 2010-09-30 | 2017-12-31 | 2010-09-01
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI01 | SG Secure Network Infrastructure | 2743.46 |  | 2743.46 | 100% |  | 64179.7 | 0 | 64179.7 | 2014-12-12 | 2016-08-30 | 2014-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI02 | SG Secure Network Infrastructure | -1688.42 |  | -1688.42 | 100% |  | 39875.24 | 0 | 39875.24 | 2014-12-12 | 2016-06-30 | 2014-12-01 | 2016-04-30
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI03 | SG SNI - IPv6 | 18237.04 |  | 18237.04 | 100% |  | 18237.04 | 0 | 18237.04 | 2016-02-15 15:40 | 2017-02-28 | 2016-02-01 | 2017-02-28
75084-DE Kentucky Power Deliv - Ele | SGSNIF | SGSNI04 | SG SNI - IPv6 | 8878.13 |  | 8878.13 | 100% |  | 8878.13 | 0 | 8878.13 | 2016-02-18 12:04 | 2017-02-28 | 2016-02-01 | 2017-02-28
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGSTRGC | Smart Grid Storage Project | 0 |  | 0 |  |  | 128657.15 | 0 | 128657.15 | 2010-06-16 | 2010-11-30 | 2010-09-01 | 2011-02-17
75084-DE Kentucky Power Deliv - Ele | SG000445F | SGSUBTXKY | DEK URD Submersible Transformers | 26348.72 |  | 26348.72 | 100% |  | 26348.72 | 0 | 26348.72 | 2016-05-16 10:14 | 2025-12-31 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | SGITOMSGI | SGSWDOMC | SG AMI DOMS S/W Module Capital | 1261.28 |  | 1261.28 | 100% |  | 28994.29 | 0 | 28994.29 | 2012-12-20 | 2015-08-29 | 2013-01-01 | 2017-01-15
75084-DE Kentucky Power Deliv - Ele | SGKYMTRSY | SGSYED11 | EDM.11 SG Scaling/Tech Hlth | 0 |  | 0 |  |  | 111333.51 | 0 | 111333.51 | 2010-09-30 | 2010-03-04 | 2010-09-01 | 2010-06-04
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGSYED15 | SG EDM.15 EDMS Scalability-Hardware | 0 |  | 0 |  |  | 52213.53 | 0 | 52213.53 | 2010-09-14 | 2010-09-30 | 2010-09-01 | 2011-02-24
75084-DE Kentucky Power Deliv - Ele | SGITMTRSY | SGSYEDP2 | SG Scalability Phase 2 EDM064 | 0 |  | 0 |  |  | 217795.82 | 0 | 217795.82 | 2010-08-13 | 2011-09-30 | 2010-09-01 | 2011-08-13
75084-DE Kentucky Power Deliv - Ele | SGPMYUF | SGYFA2SW | DEE YFA Ver 2 DER - Software | 21420.26 |  | 21420.26 | 100% |  | 21420.26 | 0 | 21420.26 | 2016-01-08 10:09 | 2017-05-24 | 2016-01-01 | 2017-03-07
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1102CP | Journal KY storm costs O&M to CAP | 0 |  | 0 |  |  | 1931.19 | 0 | 1931.19 | 2011-07-01 | 2012-07-31 | 2011-06-01 | 2011-09-30
75084-DE Kentucky Power Deliv - Ele | ORTFA | SKY1201TC | Kentucky Storm O&M to cap Trans | -11688.76 |  | -11688.76 | 100% |  | 53641.56 | 0 | 53641.56 | 2012-03-29 | 2012-07-31 | 2012-03-01 | 2012-06-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1203DC | Kentucky Storm O&M to Capital | 0 |  | 0 |  |  | 34459.11 | 0 | 34459.11 | 2012-09-28 | 2012-10-31 | 2012-09-01 | 2012-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1204DC | Kentucky Storm O&M to Capital | 0 |  | 0 |  |  | 2532.42 | 0 | 2532.42 | 2012-12-31 | 2013-03-31 | 2012-12-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1302DC | KENTUCKY O&M TO CAPITAL JOURNAL Q 2 | 0 |  | 0 |  |  | 16563.88 | 0 | 16563.88 | 2013-06-20 | 2014-03-30 | 2013-06-01 | 2013-10-01
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1303DC | KENTUCKY O&M TO CAPITAL JRNL Q3 & 4 | 0 |  | 0 |  |  | 19866.39 | 0 | 19866.39 | 2013-06-20 | 2014-03-30 | 2013-12-01 | 2014-03-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1401DC | KENTUCKY O&M TO CAPITAL JOURNAL Q 1 | 0 |  | 0 |  |  | 1475.4 | 0 | 1475.4 | 2014-04-28 | 2016-03-31 | 2014-05-01 | 2014-09-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1404DC | Kentucky O&M - CAPITAL JOURNAL Q3&4 | 0 |  | 0 |  |  | 18025.48 | 0 | 18025.48 | 2014-12-30 | 2016-03-31 | 2014-12-01 | 2015-03-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1501DC | KENTUCKY O&M TO CAP JOURNAL Q 1 | 0 |  | 0 |  |  | 1215.79 | 0 | 1215.79 | 2015-04-01 09:50 | 2015-12-31 | 2015-03-01 | 2015-05-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1502DC | Kentucky O&M To Capital Journal | 0 |  | 0 |  |  | 987.64 | 0 | 987.64 | 2015-07-30 15:55 | 2016-12-31 | 2015-07-01 | 2015-10-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1504DC | Kentucky O&M To Capital Journal | -117.6 |  | -117.6 | 100% |  | 25477.35 | 0 | 25477.35 | 2015-10-15 15:45 | 2016-12-31 | 2015-10-01 | 2016-01-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1505DC | Kentucky O&M To Capital Journal | -0.73 |  | -0.73 | 100% |  | 13595.25 | 0 | 13595.25 | 2015-10-15 15:47 | 2016-12-31 | 2015-10-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1601DC | Kentucky O&M TO CAP JOURNAL Strm 1 | 1176.4 |  | 1176.4 | 100% |  | 1176.4 | 0 | 1176.4 | 2016-02-26 16:57 | 2016-10-31 | 2016-03-01 | 2016-07-15
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1603DC | DEK O&M TO CAPITAL JOURNAL Strm 3 | 4857.81 |  | 4857.81 | 100% |  | 4857.81 | 0 | 4857.81 | 2016-04-28 19:32 | 2016-12-31 | 2016-06-01 | 2016-08-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1604DC | DEK O&M TO CAPITAL JOURNAL Strm 4 | 5563.67 |  | 5563.67 | 100% |  | 5563.67 | 0 | 5563.67 | 2016-04-28 19:37 | 2016-12-31 | 2016-06-01 | 2016-08-30
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1605DC | Kentucky O&M TO CAPITAL JRNL Strm 5 | 7363.96 |  | 7363.96 | 100% |  | 7363.96 | 0 | 7363.96 | 2016-05-20 09:50 | 2017-09-30 | 2016-07-01 | 2016-10-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1606DC | DEK O&M TO CAPITAL JOURNAL Strm 6 | 1484.68 |  | 1484.68 | 100% |  | 1484.68 | 0 | 1484.68 | 2016-08-31 15:14 | 2017-12-31 | 2016-08-01 | 2016-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1607DC | DEK O&M TO CAPITAL JOURNAL Strm 7 | 8495.18 |  | 8495.18 | 100% |  | 8495.18 | 0 | 8495.18 | 2016-08-31 15:17 | 2017-12-31 | 2016-08-01 | 2016-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1608DC | DEK O&M TO CAPITAL JOURNAL Strm 8 | 11498.95 |  | 11498.95 | 100% |  | 11498.95 | 0 | 11498.95 | 2016-08-31 15:21 | 2017-12-31 | 2016-08-01 | 2016-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1609DC | DEK O&M TO CAPITAL JOURNAL Strm 9 | 3684.99 |  | 3684.99 | 100% |  | 3684.99 | 0 | 3684.99 | 2016-09-30 14:28 | 2017-06-30 | 2016-09-01 | 2017-01-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1610DC | DEK O&M TO CAPITAL JOURNAL Strm 10 | 20482.94 |  | 20482.94 | 100% |  | 20482.94 | 0 | 20482.94 | 2016-09-30 14:31 | 2017-06-30 | 2016-09-01 | 2016-12-31
75084-DE Kentucky Power Deliv - Ele | ORDFA | SKY1611DC | DEK O&M TO CAPITAL JOURNAL Strm 11 | 4105.7 |  | 4105.7 | 100% |  | 4105.7 | 0 | 4105.7 | 2016-11-01 08:15 | 2017-06-30 | 2016-11-01 | 2017-02-01
75084-DE Kentucky Power Deliv - Ele | SLFA | SLKY | Light Repl-Tarriff | 5018.42 |  | 5018.42 | 100% |  | 149216.76 | 0 | 149216.76 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | SLFA | SLKYUG | Kentucky Light Repl-Tarriff - UG | -498.89 |  | -498.89 | 100% |  | -498.89 | 0 | -498.89 | 2014-08-04 | 2020-12-31 | 2016-04-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | SSDTH | Enable Subst Design Tool Hardware | 3.74 |  | 3.74 | 100% |  | 97.46 | 0 | 97.46 | 2015-03-30 15:04 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | SSDTS | Enable Subst Design Tool Software | 11314.77 |  | 11314.77 | 100% |  | 20613.12 | 0 | 20613.12 | 2015-03-30 14:36 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT112 | Kenton 41 & Kenton 44 2012 | 0 |  | 0 |  |  | 122048.92 | 0 | 122048.92 | 2011-10-31 | 2012-12-31 | 2011-11-01 | 2012-11-28
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT212 | Augustine 41 & Crescent 42 2012 | -730.05 |  | -730.05 | 100% |  | 76720.03 | 0 | 76720.03 | 2011-10-31 | 2012-12-31 | 2011-11-01 | 2013-01-24
75084-DE Kentucky Power Deliv - Ele | CSFA | STKYT34 | SG Verona 41 & Crittenden 41 | 0 |  | 0 |  |  | 81187.39 | 0 | 81187.39 | 2012-11-01 | 2014-03-31 | 2012-12-01 | 2013-08-30
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT36 | SG DEK Self Healing Team 36 Capital | 0 |  | 0 |  |  | 101437.63 | 0 | 101437.63 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2014-12-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT37 | SG DEK Self Healing Team 37 Capital | 0 |  | 0 |  |  | 56843.7 | 0 | 56843.7 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2015-01-31
75084-DE Kentucky Power Deliv - Ele | SGCSFA | STKYT38 | SG DEK Self Healing Team 38 Capital | 0 |  | 0 |  |  | 145785.26 | 0 | 145785.26 | 2014-04-21 | 2015-07-31 | 2014-05-01 | 2015-04-30
75084-DE Kentucky Power Deliv - Ele | FSTRMTRLR | STORMTRLR | IDEN STORM TRAILER | 0 |  | 0 |  |  | 96106.51 | 0 | 96106.51 | 2011-12-16 | 2012-11-15 | 2011-12-01 | 2013-03-31
75084-DE Kentucky Power Deliv - Ele | UGCRFA | SUGCRKY | UG Secondary Cable Replace | 287.61 |  | 287.61 | 100% |  | 287.61 | 10 | 277.61 | 2015-02-24 10:56 | 2025-12-31 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | TKY1447 | T1447DS1 | Cold Spring Ckt Swi | 274568.2 |  | 274568.2 | 100% |  | 274568.2 | 0 | 274568.2 | 2016-02-12 10:59 | 2017-03-31 | 2016-02-01 | 2017-03-29
75084-DE Kentucky Power Deliv - Ele | TKY1453 | T1453DS1 | Dixie Bus 1 Swgr - TKY1453 | 93812.45 |  | 93812.45 | 100% |  | 93812.45 | 0 | 93812.45 | 2016-10-07 18:03 | 2018-07-31 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | TKY1453 | T1453TS1 | Dixie 69kV ABS - TKY1453 | 25197.12 |  | 25197.12 | 100% |  | 25197.12 | 0 | 25197.12 | 2016-10-07 18:03 | 2018-07-31 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | TKY1454 | T1454DS1 | Hands Bus 1 Swgr - TKY1454 | 96345.36 |  | 96345.36 | 100% |  | 96345.36 | 0 | 96345.36 | 2016-05-12 18:02 | 2018-03-01 | 2016-06-01
75084-DE Kentucky Power Deliv - Ele | TKY1518 | T1518DS1 | Mt Zion XTR 1 Rel Repl | 212650.66 |  | 212650.66 | 100% |  | 212650.66 | 0 | 212650.66 | 2015-11-18 18:02 | 2017-03-31 | 2016-03-01 | 2017-03-16
75084-DE Kentucky Power Deliv - Ele | TKY1519 | T1519DS1 | Thomas More XTR 1 Rel Rpl | 219235.61 |  | 219235.61 | 100% |  | 219235.61 | 0 | 219235.61 | 2016-02-24 18:03 | 2017-03-31 | 2016-03-01 | 2017-01-21
75084-DE Kentucky Power Deliv - Ele | TKY1672 | T1672TS1 | F965 Kenton Rel Repl | 89181.52 |  | 89181.52 | 100% |  | 89181.52 | 0 | 89181.52 | 2016-09-27 18:02 | 2018-03-31 | 2016-10-01 | 2017-07-06
75084-DE Kentucky Power Deliv - Ele | TKY1672 | T1672TS2 | F965 Wilder Rel Repl | 159527.78 |  | 159527.78 | 100% |  | 159527.78 | 0 | 159527.78 | 2016-09-27 18:02 | 2018-03-31 | 2016-10-01 | 2017-08-10
75084-DE Kentucky Power Deliv - Ele | TKY1695 | T1695TS1 | Buffington F966 CB Rel Repl - TKY16 | 87739.27 |  | 87739.27 | 100% |  | 87739.27 | 0 | 87739.27 | 2016-10-07 18:03 | 2020-02-29 | 2016-10-01
75084-DE Kentucky Power Deliv - Ele | TKY1695 | T1695TS2 | Kenton F966 Rel Repl - TKY1695 | 4712.4 |  | 4712.4 | 100% |  | 4712.4 | 0 | 4712.4 | 2016-10-07 18:03 | 2020-02-29 | 2016-12-01
75084-DE Kentucky Power Deliv - Ele | TKY1695 | T1695TS3 | Villa F966 Rel Repl - TKY1695 | 72126.87 |  | 72126.87 | 100% |  | 72126.87 | 0 | 72126.87 | 2016-10-07 18:03 | 2020-02-29 | 2016-12-01
75084-DE Kentucky Power Deliv - Ele | MTRTOOLFA | TBIMTRLAB | Metering Capital Tools | 0 |  | 0 |  |  | 23498.19 | 0 | 23498.19 | 2008-07-01 | 2050-12-31 | 2009-07-01
75084-DE Kentucky Power Deliv - Ele | FTDITKE | TDITCHAR | PD KENTUCKY IT HARDWARE | 0 |  | 0 |  |  | 144.8 | 0 | 144.8 | 2009-08-27 | 2025-12-25 | 2009-09-01
75084-DE Kentucky Power Deliv - Ele | FTDITKE | TDITKE | PD KENTUCKY IT HARDWARE | 734.91 |  | 734.91 | 100% |  | 734.91 | 0 | 734.91 | 2010-07-01 | 2025-12-25 | 2016-05-01
75084-DE Kentucky Power Deliv - Ele | OM75084 | TEMPSVC | Temporary Service | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-07-01 | 2008-06-28 21:34 | 2008-08-01
75084-DE Kentucky Power Deliv - Ele | DETCONFA | THEFTCOND | REPL STOLEN IN-SRVC OVRHD COND - KY | 8893.65 |  | 8893.65 | 100% |  | 37702.16 | 0 | 37702.16 | 2014-06-10 | 2025-12-31 | 2014-06-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | TIMH | Enable TIM Hardware | 24.4 |  | 24.4 | 100% |  | 27.79 | 0 | 27.79 | 2015-03-30 14:56 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | TIMS | Enable TIM Software | 62738.63 |  | 62738.63 | 100% |  | 84176.94 | 0 | 84176.94 | 2015-03-30 14:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | CERTFA | TLPIKY | Transm Lightning Perf Improvements | 0 |  | 0 |  |  | 15985.5 | 0 | 15985.5 | 2012-01-04 | 2050-12-31 | 2013-05-01
75084-DE Kentucky Power Deliv - Ele | CERTFA | TLSRKY | Transm Line Switch Replacement | 0 |  | 0 |  |  | 5138.64 | 0 | 5138.64 | 2012-01-04 | 2050-12-31 | 2014-07-01
75084-DE Kentucky Power Deliv - Ele | TOOLFA | TOOLKY | Tools & Equip | 489557.71 |  | 489557.71 | 100% |  | 1455461.41 | 0 | 1455461.41 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084-DE Kentucky Power Deliv - Ele | FENABLEH | TPCTH | Enable Trans Proj Cost Hardware | 468.25 |  | 468.25 | 100% |  | 653.91 | 0 | 653.91 | 2015-08-04 10:47 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | TPCTS | Enable Tran Proj Cost Software | 47627.04 |  | 47627.04 | 100% |  | 62578.61 | 0 | 62578.61 | 2015-08-03 16:47 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLEH | TPETH | Enable Trans Proj Est Hardware | 964.83 |  | 964.83 | 100% |  | 1158.1 | 0 | 1158.1 | 2015-08-04 11:22 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | FENABLES | TPETS | Enable Trans Proj Est Software | 70444.43 |  | 70444.43 | 100% |  | 96730.97 | 0 | 96730.97 | 2015-08-03 16:52 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY10 | DIST TRANSFORMERS PUR 2010 | 0 |  | 0 |  |  | 1018111.3 | 0 | 1018111.3 | 2014-02-04 | 2015-12-31 | 2014-02-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY11 | DIST TRANSFORMERS PUR 2011 | 0 |  | 0 |  |  | 363165.36 | 0 | 363165.36 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY12 | DIST LINE TRANSFORMERS PUR 2012 | 0 |  | 0 |  |  | 300925.74 | 0 | 300925.74 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | 906F0502 | TPURKY13 | DIST LINE TRANSFORMERS PUR 2013 | 0 |  | 0 |  |  | 491191.31 | 0 | 491191.31 | 2014-02-04 | 2015-12-31 | 2014-05-01
75084-DE Kentucky Power Deliv - Ele | FNINT1229 | TRNPRIMAV | NINT1229 - Trans Primavera Upgr | -86.81 |  | -86.81 | 100% |  | 77636.83 | 0 | 77636.83 | 2014-08-03 | 2017-10-31 | 2014-08-01 | 2016-03-31
75084-DE Kentucky Power Deliv - Ele | UGCRFA | UGCRKY | UG Cable Repl | 84237.28 |  | 84237.28 | 100% |  | 422066.72 | 100 | 421966.72 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | VMDDTFA | VMCMCKY | R/W CKT MAINT CAP KENTUCKY | 285853.99 |  | 285853.99 | 100% |  | 1979623.15 | 1 | 1979622.15 | 2012-01-25 | 2050-12-31 | 2012-02-01
75084-DE Kentucky Power Deliv - Ele | VMDDTFA | VMDDTKY | Distr Line Clr Removal | 412701.56 |  | 412701.56 | 100% |  | 1827217.7 | 1 | 1827216.7 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | VMTDFA | VMTDKY | Trans Line Clr Removal | 89868.27 |  | 89868.27 | 100% |  | 261955.06 | 1 | 261954.06 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084-DE Kentucky Power Deliv - Ele | NCIPLOWK | WALKKY | Walkdown - Kentucky | 211994.29 |  | 211994.29 | 100% |  | 211994.29 | 0 | 211994.29 | 2016-11-22 17:08 | 2019-03-31 | 2016-11-01
75084-DE Kentucky Power Deliv - Ele | FENABLES | WRTS | Enable WRT & WMSP Software | 49571.41 |  | 49571.41 | 100% |  | 64891.61 | 0 | 64891.61 | 2015-03-30 14:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084-DE Kentucky Power Deliv - Ele | U14ZKVCH | ZC071 | ULHP DistLine Capacitor Switch | 0 |  | 0 |  |  | 0 | 0 | 0 | 2008-02-14 | 2050-12-31 | 2008-03-01
75084-DE Kentucky Power Deliv - Ele | 312ZLEL | ZE083 | OLE LIGHTING South ULHP CP3 | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-12-20 | 2009-04-01 | 2008-01-01
75084-DE Kentucky Power Deliv - Ele | U04ZTREE | ZV070 | DANGER TREE - TRANS - ULHP | 0 |  | 0 |  |  | 4273.99 | 0 | 4273.99 | 2007-04-26 | 2050-12-31 | 2007-04-01 | 2008-03-31
75084-DE Kentucky Power Deliv - Ele | U14ZTREE | ZV071 | DANGER TREE - DIST - ULHP | 0 |  | 0 |  |  | 0 | 0 | 0 | 2007-04-26 | 2050-12-31 | 2007-06-01
75084-DE Kentucky Power Deliv - Ele | AMIKYCS | ZY070 | AMI Meters in Kentucky | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-03-29 11:43 | 2016-06-30 | 2016-03-01 | 2016-06-29
75085-DE Kentucky Cus Service - Ele | FPIT | 300893C | 300893C Proactive Communications | 1990.71 |  | 1990.71 | 100% |  | 70705.38 | 37518.23 | 33187.15 | 2015-04-20 15:04 | 2015-12-31 | 2015-05-01 | 2016-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | 307558AUG | 307558AUG Pro Comm Enhancements | 14665.97 |  | 14665.97 | 100% |  | 15224.13 | 10594 | 4630.13 | 2015-12-21 10:37 | 2016-09-30 | 2015-12-01 | 2016-12-31
75085-DE Kentucky Cus Service - Ele | FPIT | 307558MAY | 307558MAY Pro Comm Enhancements | 28955.8 |  | 28955.8 | 100% |  | 31364.78 | 36481 | -5116.22 | 2015-12-21 09:51 | 2016-06-30 | 2015-12-01 | 2017-01-19
75085-DE Kentucky Cus Service - Ele | FPIT | 311803CH | Lighting System Integration HW | 69.62 |  | 69.62 | 100% |  | 69.62 | 3243.47 | -3173.85 | 2015-09-18 10:13 | 2019-03-31 | 2016-01-01
75085-DE Kentucky Cus Service - Ele | FPIT | 311803CS | Lighting System Integration Softwar | 34805.49 |  | 34805.49 | 100% |  | 43463.81 | 157966.53 | -114502.72 | 2015-09-14 13:59 | 2019-03-31 | 2015-11-01
75085-DE Kentucky Cus Service - Ele | FPIT | 315263BTS | 315263BTS Encryption PH2 | 5159.24 |  | 5159.24 | 100% |  | 5159.24 | 19818 | -14658.76 | 2016-10-13 15:34 | 2016-12-31 | 2016-10-01 | 2017-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | 315263GDG | 315263GDG Encryption PH2 | 6094.8 |  | 6094.8 | 100% |  | 6094.8 | 5086 | 1008.8 | 2016-10-13 12:47 | 2016-12-31 | 2016-11-01 | 2017-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | 315263VER | 315263VER Encryption PH2 | 4520.14 |  | 4520.14 | 100% |  | 4520.14 | 9967 | -5446.86 | 2016-10-13 16:18 | 2016-12-31 | 2016-12-01 | 2017-03-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C8779 | AMI Mt Zion Advanced Meter | 0 |  | 0 |  |  | 79580.84 | 101605 | -22024.16 | 2007-01-04 | 2007-12-31 | 2007-01-01 | 2007-12-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9041 | AMI Hands Advanced Meter | 0 |  | 0 |  |  | 202616.61 | 153106 | 49510.61 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9042 | AMI Empire Advanced Meter | 0 |  | 0 |  |  | 117897.99 | 137706 | -19808.01 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9043 | AMI Kenton Advanced Meter | 0 |  | 0 |  |  | 179935.34 | 197559 | -17623.66 | 2007-01-07 | 2007-12-31 | 2007-01-01 | 2007-12-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9044 | AMI Wilder Advanced Meter | -38538.65 |  | -38538.65 | 100% |  | 2479.33 | 200835 | -198355.67 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9045 | AMI Donaldson Advanced Meter | -56076.43 |  | -56076.43 | 100% |  | 3598.4 | 151468 | -147869.6 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9046 | AMI Oakbrook Advanced Meter | 0 |  | 0 |  |  | 62106.41 | 94724 | -32617.59 | 2007-01-07 | 2007-10-31 | 2007-01-01 | 2007-10-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9047 | AMI Atlas Advanced Meter | -10584 |  | -10584 | 100% |  | 665.91 | 93304 | -92638.09 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9048 | AMI Claryville Advanced Meter | -32006.86 |  | -32006.86 | 100% |  | 3929.45 | 158349 | -154419.55 | 2007-01-07 | 2009-08-31 | 2007-07-01 | 2009-08-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9049 | AMI Florence Advanced Meter | -76513.9 |  | -76513.9 | 100% |  | 4792.32 | 189695 | -184902.68 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9050 | AMI Villa Advanced Meter | -55944 |  | -55944 | 100% |  | 3534.75 | 150703 | -147168.25 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | C9051 | AMI Dixie Advanced Meter | -46869.36 |  | -46869.36 | 100% |  | 3414.48 | 154744 | -151329.52 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2008-01-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9052 | AMI Buffington Advanced Meter | -69301.06 |  | -69301.06 | 100% |  | 7071.39 | 191879 | -184807.61 | 2007-01-07 | 2008-03-15 | 2007-02-01 | 2008-06-30
75085-DE Kentucky Cus Service - Ele | EMSBLADE | C9288 | Midwest EMS Blade Server Infra | 0 |  | 0 |  |  | 16913.75 | 18468 | -1554.25 | 2007-02-14 | 2007-12-31 | 2007-02-01 | 2008-03-31
75085-DE Kentucky Cus Service - Ele | AMIKY | C9449 | AMI Dry Ridge Advanced Meter | 0 |  | 0 |  |  | 56532.74 | 95052 | -38519.26 | 2007-03-16 | 2007-10-15 | 2007-04-01 | 2007-10-15
75085-DE Kentucky Cus Service - Ele | AMIKY | D1128 | AMI Thomas More Advanced Mete | -10584 |  | -10584 | 100% |  | 73.81 | 1 | 72.81 | 2007-07-04 | 2008-06-15 | 2007-07-01 | 2007-11-30
75085-DE Kentucky Cus Service - Ele | AMIKY | D1144 | AMI West End Advanced Meter | -47628 |  | -47628 | 100% |  | 2658.69 | 50000 | -47341.31 | 2007-07-06 | 2011-03-31 | 2007-07-01 | 2009-01-01
75085-DE Kentucky Cus Service - Ele | FEBPE1A | EBPE1 | Electronic Billing & Payment Ex Ph1 | 0 |  | 0 |  |  | 61896.29 | 72600 | -10703.71 | 2011-05-20 | 2011-12-31 | 2011-06-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FEBPE1A | EBPE2 | EBPE Phase 2 | 0 |  | 0 |  |  | 46724.42 | 47000 | -275.58 | 2012-02-20 | 2012-12-31 | 2012-02-01 | 2012-12-17
75085-DE Kentucky Cus Service - Ele | SGITCS | ECSDCI1 | Enterprise Cust syst DCI1 Capital | 0 |  | 0 |  |  | 31257.61 | 100000 | -68742.39 | 2011-02-24 | 2015-06-30 | 2011-03-01 | 2010-09-18
75085-DE Kentucky Cus Service - Ele | SGITCS | ECSDCI2 | Enterprise Cust system DCI2 Capital | 0 |  | 0 |  |  | 3473.74 | 100000 | -96526.26 | 2011-04-13 | 2015-03-15 | 2011-04-01 | 2011-11-30
75085-DE Kentucky Cus Service - Ele | RCPSPROJ | LRIEDM42 | Load Research Interfaces EDM042 | 0 |  | 0 |  |  | 28724.53 | 315500 | -286775.47 | 2011-05-24 | 2011-11-30 | 2011-06-01 | 2012-03-01
75085-DE Kentucky Cus Service - Ele | FPIT | MFEOLREPL | Mainframe EOL Repl | 0 |  | 0 |  |  | 51555.84 | 53881.98 | -2326.14 | 2012-05-31 | 2012-09-30 | 2012-06-01 | 2012-12-19
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1024C | NINT1024 Knowledge Management Tool | 0 |  | 0 |  |  | 18067.34 | 12541.38 | 5525.96 | 2014-01-13 | 2014-12-30 | 2014-02-01 | 2014-11-23
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1139H | NINT1139 CCO TPO MODEL | 0 |  | 0 |  |  | 658.12 | 3900.88 | -3242.76 | 2014-12-17 | 2014-12-31 | 2015-01-01 | 2015-08-18
75085-DE Kentucky Cus Service - Ele | FPIT | NINT1139L | NINT1139 CCO TPO MODEL | 0 |  | 0 |  |  | 3267.81 | 3835.9 | -568.09 | 2014-12-17 | 2014-12-31 | 2015-04-01 | 2016-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 18124.69 |  | 18124.69 | 100% |  | 18135.15 | 18000 | 135.15 | 2015-11-16 14:15 | 2016-09-30 | 2015-12-01 | 2017-03-27
75085-DE Kentucky Cus Service - Ele | FPIT | NINT979C | NINT979C Combined Mobile SMS TXT | 0 |  | 0 |  |  | 31381.49 | 22322.04 | 9059.45 | 2014-10-01 | 2014-12-31 | 2014-10-01 | 2015-05-20
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA1049C | INT1049 BRNR | 0 |  | 0 |  |  | 45199.91 | 47222.49 | -2022.58 | 2014-10-23 | 2015-07-31 | 2014-11-01 | 2015-10-17
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175AC | Customer Contact Preference Center | 0 |  | 0 |  |  | 41139.94 | 34008 | 7131.94 | 2013-08-01 | 2014-10-14 | 2013-08-01 | 2014-10-14
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175BS | PCTA175BS CDS | 61903.2 |  | 61903.2 | 100% |  | 66892.02 | 78939.89 | -12047.87 | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA175L | PCTA175L CDS Licenses | 2684.58 |  | 2684.58 | 100% |  | 2684.58 | 2670.01 | 14.57 | 2016-08-01 10:27 | 2016-12-31 | 2016-10-01 | 2017-02-15
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA210C | Contact Channels Datamart & Dashboa | 0 |  | 0 |  |  | 8641.02 | 7351.4 | 1289.62 | 2013-10-22 | 2014-09-23 | 2013-11-01 | 2014-09-23
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AC | CA Lisa | 0 |  | 0 |  |  | 11718.57 | 9387.72 | 2330.85 | 2014-10-21 | 2015-11-30 | 2014-11-01 | 2015-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AH | INT481A CDP Hardware Implementation | 0 |  | 0 |  |  | 9160.87 | 14924.07 | -5763.2 | 2014-10-23 | 2015-11-30 | 2014-11-01 | 2015-03-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AS | Sitecore | 465756.83 |  | 465756.83 | 100% |  | 1188625.5 | 520043.89 | 668581.61 | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75085-DE Kentucky Cus Service - Ele | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 836910.75 |  | 836910.75 | 100% |  | 836910.75 | 1159204 | -322293.25 | 2016-02-11 12:16 | 2018-09-30 | 2016-03-01
75085-DE Kentucky Cus Service - Ele | FPIT | PCTAIT17X | Mobile Web Phase 1 | 0 |  | 0 |  |  | 6622.7 | 3580 | 3042.7 | 2013-01-20 | 2013-10-30 | 2013-03-01 | 2014-01-31
75085-DE Kentucky Cus Service - Ele | FPIT | PCTAIVRSW | IVR Software and Licenses | 0 |  | 0 |  |  | 83234.43 | 84000 | -765.57 | 2013-03-12 | 2014-07-31 | 2013-05-01 | 2014-08-15
75085-DE Kentucky Cus Service - Ele | FPIT | RCDPSSK | Dynamic Pricing Solution System | 0 |  | 0 |  |  | 83424.32 | 84000 | -575.68 | 2012-01-31 | 2013-03-31 | 2012-02-01 | 2013-01-28
75085-DE Kentucky Cus Service - Ele | FPIT | RCDRCETK | Daily Rating Charging Estimate Tool | 0 |  | 0 |  |  | 26202.58 | 27000 | -797.42 | 2012-01-31 | 2013-03-31 | 2012-02-01 | 2013-01-28
75085-DE Kentucky Cus Service - Ele | FPIT | RCIVRMKE | IVR Monitoring Systems | 0 |  | 0 |  |  | 3320.23 | 3450 | -129.77 | 2012-06-13 | 2012-12-31 | 2012-09-01 | 2013-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWHWC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 123830.93 | 124000 | -169.07 | 2011-07-22 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 232943.03 | 162502.14 | 70440.89 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | FRCSW | RCSWTELC | Cust Call Ctr Switch Repl | 0 |  | 0 |  |  | 10402.84 | 11000 | -597.16 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085-DE Kentucky Cus Service - Ele | AMIKYCS | ZY072 | AMI GAS & ELECTRIC METERS | -601512.93 |  | -601512.93 | 100% |  | 0 | 1 | -1 | 2007-02-05 | 2050-12-31 | 2007-07-01 | 2008-07-01
|  |  |  | 73067914.47 | 85492908.0819 | -12424993.6119 | -14.53%

## 2017
Duke Energy Kentucky Electric
Year 2017
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75084 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 329.43 |  | 329.43 |  |  | 342.37 | 217 | 125.37 | 2015-03-30 16:09 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 26.57 |  | 26.57 |  |  | 36.9 | 217 | -180.1 | 2015-03-30 13:06 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084 | FENABLEH | ECOMH | Enable ECOM Data Hub | 585.26 |  | 585.26 |  |  | 742.76 | 685 | 57.76 | 2015-09-29 09:53 | 2017-10-31 | 2016-01-01 | 2017-11-07
75084 | FENABLEH | EGISH | Enable EGIS Hardware | 390.77 |  | 390.77 |  |  | 1275.95 | 1224 | 51.95 | 2015-03-30 15:31 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 17.29 |  | 17.29 |  |  | 90.41 | 136 | -45.59 | 2015-03-30 13:46 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084 | FENABLEH | MAXH | Enable Maximo Hardware | 4638.83 |  | 4638.83 |  |  | 8565.31 | 9267 | -701.69 | 2015-03-30 12:42 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLEH | MOBH | Enable Mobility Hardware | 138878.57 |  | 138878.57 |  |  | 191680.43 | 172489 | 19191.43 | 2015-03-30 15:55 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084 | FENABLEH | SDDTH | Enable Subdiv Design Tool Hardware | 16.53 |  | 16.53 |  |  | 16.53 | 15 | 1.53 | 2015-03-30 15:16 | 2017-10-31 | 2017-06-01 | 2017-11-07
75084 | FENABLEH | WRTH | Enable WRT & WMSP Hardware | 26.46 |  | 26.46 |  |  | 26.46 | 22 | 4.46 | 2015-03-30 13:25 | 2017-10-31 | 2017-06-01 | 2017-11-07
75084 | FENABLEH | TPETH | Enable Trans Proj Est Hardware | 282.29 |  | 282.29 |  |  | 1440.39 | 1073 | 367.39 | 2015-08-04 11:22 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084 | FENABLEH | PRIMH | Enable Primavera Hardware | 940.07 |  | 940.07 |  |  | 3023.81 | 3707 | -683.19 | 2015-03-30 16:23 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084 | FENABLEH | TPCTH | Enable Trans Proj Cost Hardware | 424 |  | 424 |  |  | 1077.91 | 1411 | -333.09 | 2015-08-04 10:47 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084 | FENABLEH | SSDTH | Enable Subst Design Tool Hardware | 17.54 |  | 17.54 |  |  | 115 | 118 | -3 | 2015-03-30 15:04 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084 | FENABLEH | TIMH | Enable TIM Hardware | 45.06 |  | 45.06 |  |  | 72.85 | 84 | -11.15 | 2015-03-30 14:56 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 95349.16 |  | 95349.16 |  |  | 213875.24 | 199412 | 14463.24 | 2015-03-30 14:59 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | ARMS | Enable ARM Scheduler Software | 113204.37 |  | 113204.37 |  |  | 189963.61 | 199412 | -9448.39 | 2015-03-30 14:11 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 80179.89 |  | 80179.89 |  |  | 121567.58 | 117858 | 3709.58 | 2015-03-30 15:05 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | EGISS | Enable EGIS Software | 416729.49 |  | 416729.49 |  |  | 745758.25 | 670125 | 75633.25 | 2015-03-30 14:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | ENABLETDG | ENABLETDG Clearing Project | -483252.51 |  | -483252.51 |  |  | 59375.33 | 801485.44 | -742110.11 | 2015-05-12 14:57 | 2018-10-01 | 2015-05-01
75084 | FENABLES | EXPDS | Enable Expert Designer Software | 83900.05 |  | 83900.05 |  |  | 147298.88 | 145274 | 2024.88 | 2015-03-30 14:25 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | MAXS | Enable Maximo Software | 660767.2 |  | 660767.2 |  |  | 1410790 | 1352478 | 58312 | 2015-03-30 14:04 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | MOBS | Enable Mobility Software | 477414.73 |  | 477414.73 |  |  | 867968.61 | 932343 | -64374.39 | 2015-03-30 14:54 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 66240.41 |  | 66240.41 |  |  | 110879.17 | 22774 | 88105.17 | 2015-03-30 14:43 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | WRTS | Enable WRT & WMSP Software | 111907.23 |  | 111907.23 |  |  | 176798.84 | 168186 | 8612.84 | 2015-03-30 14:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | PPS | Enable PowerPlan Software | 9682.24 |  | 9682.24 |  |  | 67691.32 | 64531 | 3160.32 | 2015-03-30 15:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | SSDTS | Enable Subst Design Tool Software | 47438.61 |  | 47438.61 |  |  | 68051.73 | 79764 | -11712.27 | 2015-03-30 14:36 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | PRIMS | Enable Primavera Software | 86534.53 |  | 86534.53 |  |  | 156809.74 | 154922 | 1887.74 | 2015-03-30 15:12 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLES | TIMS | Enable TIM Software | 157419.27 |  | 157419.27 |  |  | 241596.21 | 239157 | 2439.21 | 2015-03-30 14:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | TPETS | Enable Trans Proj Est Software | 108274.74 |  | 108274.74 |  |  | 205005.71 | 142915 | 62090.71 | 2015-08-03 16:52 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084 | FENABLES | TPCTS | Enable Tran Proj Cost Software | 92795.46 |  | 92795.46 |  |  | 155374.07 | 208628 | -53253.93 | 2015-08-03 16:47 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084 | SG000358F | SG358HW18 | SG 358 - MDM Scale Hardware Phase 3 | 84669.13 |  | 84669.13 |  |  | 84669.13 | 82572 | 2097.13 | 2017-05-30 17:39 | 2018-09-30 | 2017-06-01 | 2018-08-31
75084 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 22944.83 |  | 22944.83 |  |  | 23237.03 | 4208 | 19029.03 | 2016-11-01 13:54 | 2018-02-28 | 2016-11-01 | 2018-02-12
75084 | SG000358F | SG358SGGL | SG 358 - DEE MDM Scale - SGG Licens | 402.79 |  | 402.79 |  |  | 30268.69 | 36760 | -6491.31 | 2016-06-17 13:41 | 2017-06-30 | 2016-07-01 | 2017-06-26
75084 | SG000358F | SG358CALL | SG 358 - DEE MDM Scale CA Lisa SW | 101.55 |  | 101.55 |  |  | 7629.99 | 10422 | -2792.01 | 2016-06-17 11:48 | 2017-06-30 | 2016-08-01 | 2017-06-26
75084 | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 20456 |  | 20456 |  |  | 103788.64 | 323369 | -219580.36 | 2016-06-20 09:18 | 2017-06-30 | 2016-06-01 | 2017-06-26
75084 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 31084.67 |  | 31084.67 |  |  | 31084.67 | 44829.46 | -13744.79 | 2017-04-24 18:07 | 2018-12-31 | 2017-05-01 | 2019-03-31
75084 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 19125.28 |  | 19125.28 |  |  | 19976.98 | 22987.85 | -3010.87 | 2016-11-23 11:18 | 2018-12-31 | 2016-11-01 | 2019-03-31
75084 | SG000540F | SG540SW | DEE Vehicle Area Network | 4338.39 |  | 4338.39 |  |  | 4338.39 | 109210 | -104871.61 | 2017-04-13 09:21 | 2020-12-17 | 2017-04-01 | 2018-07-16
75084 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 0.07 |  | 0.07 |  |  | 9104.86 | 6421 | 2683.86 | 2015-06-10 18:11 | 2016-08-21 | 2015-06-01 | 2016-06-04
75084 | SGKAMIF | SG169MTRS | SG KY AMI Electric Meters - 169 | 10302906.75 |  | 10302906.75 |  |  | 10302906.75 | 23298670 | -12995763.25 | 2017-06-07 11:18 | 2019-02-28 | 2017-06-01
75084 | SGKAMIF | SG169KYEQ | SG KY AMI Equipment - 169 | 654589.12 |  | 654589.12 |  |  | 654589.12 | 1294611 | -640021.88 | 2017-06-07 15:50 | 2019-02-28 | 2017-07-01
75084 | SGKAMIF | SGKAMIMGT | DEK AMI Mgmt Project | 298393.98 |  | 298393.98 |  |  | 477489.49 | 603878 | -126388.51 | 2016-01-20 16:12 | 2019-06-30 | 2016-01-01 | 2019-06-30
75084 | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 0.09 |  | 0.09 |  |  | 71270.21 | 33000 | 38270.21 | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75084 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0.14 |  | 0.14 |  |  | 183577.81 | 33000 | 150577.81 | 2013-07-10 | 2014-09-30 | 2013-07-01 | 2014-08-19
75084 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 0.08 |  | 0.08 |  |  | 37438.57 | 392765 | -355326.43 | 2014-04-28 | 2015-02-16 | 2014-04-01 | 2015-02-17
75084 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0.08 |  | 0.08 |  |  | 132348.08 | 130000 | 2348.08 | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75084 | SGITMTRSY | SGNNT435S | SG Openway Scale-up Software | -0.06 |  | -0.06 |  |  | 57834.38 | 40200 | 17634.38 | 2012-07-30 | 2013-09-17 | 2012-09-01 | 2013-07-12
75084 | SG000448F | SG448SVR | SG DEE Openway Scale 2016 - Servers | 357.5 |  | 357.5 |  |  | 3389.82 | 5932.39 | -2542.57 | 2016-07-13 17:28 | 2017-03-31 | 2016-07-01 | 2017-03-14
75084 | SGKYPMO | SGOVH | Grid Solutions Overhead Allocation | -149.25 |  | -149.25 |  |  | -53.68 | 95 | -148.68 | 2016-01-08 16:23 | 2050-12-31 | 2016-01-01
75084 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -6.74 |  | -6.74 |  |  | 2.4301e-11 | 1 | -1 | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75084 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 24005.98 |  | 24005.98 |  |  | 292616.37 | 285462.99 | 7153.38 | 2015-11-02 12:18 | 2017-09-30 | 2015-10-01 | 2017-07-31
75084 | DKY2133 | MX2167589 | Mt Zion Rbld Sam Neace - DKY2133 | 5735.52 |  | 5735.52 |  |  | 5735.52 | 80732.48 | -74996.96 | 2017-09-14 18:02 | 2019-06-01 | 2017-09-01 | 2019-04-29
75084 | DKY2133 | MX2167975 | Mt Zion Rbld Weaver Rd - DKY2133 | 11787.85 |  | 11787.85 |  |  | 11787.85 | 242159.7 | -230371.85 | 2017-10-05 10:01 | 2019-12-29 | 2017-10-01
75084 | DKY1959 | D1959DS1 | Cov Sub expansion DKY1959 | 4557.14 |  | 4557.14 |  |  | 4557.14 | 290451 | -285893.86 | 2017-05-16 17:18 | 2019-04-18 | 2017-07-01 | 2019-02-01
75084 | DKY1959 | D1959RS1 | Cov Sub Add Prop | 56040.6 |  | 56040.6 |  |  | 134451.93 | 112393 | 22058.93 | 2016-07-29 07:27 | 2017-10-01 | 2016-08-01 | 2017-08-19
75084 | KYGLPRT | KYGLPR15 | GLT P2 Cir 5983 HLP 2 Poles Dist UB | 9582.55 |  | 9582.55 |  |  | 9582.55 | 20079 | -10496.45 | 2017-02-16 14:01 | 2020-03-31 | 2017-06-01
75084 | DKY2208 | D2208RS1 | Turfway Sub Site Purch | 40446.74 |  | 40446.74 |  |  | 40446.74 | 382562 | -342115.26 | 2017-05-23 15:54 | 2019-03-02 | 2017-06-01 | 2019-02-20
75084 | DETCONFA | G0529 | Old Madison Pk & Pony Dr Det Cond | 77.13 |  | 77.13 |  |  | 894.1 | 405.77 | 488.33 | 2010-07-20 | 2010-12-31 | 2010-09-01 | 2011-01-04
75084 | DETCONFA | G0531 | Spillman & Madison Pk Det Cond | -670 |  | -670 |  |  | 3119.54 | 8361.34 | -5241.8 | 2010-07-21 | 2010-12-31 | 2010-10-01 | 2011-02-24
75084 | DMAJRIFA | P7314 | Donaldson TB1 Bushings | -333.32 |  | -333.32 |  |  | 22484.53 | 11569.26 | 10915.27 | 2015-01-16 | 2018-03-01 | 2015-03-01 | 2016-12-31
75084 | DMAJRIFA | EMR290 | Constance Repl Cir 41 LA's | 952.2 |  | 952.2 |  |  | 952.2 | 1884.66 | -932.46 | 2017-01-11 12:34 | 2018-03-31 | 2017-01-01 | 2017-04-19
75084 | DMAJRIFA | EMR248 | Dixie Repl RTU Processor | 134.98 |  | 134.98 |  |  | 5531.08 | 5283.72 | 247.36 | 2016-11-09 15:17 | 2018-03-31 | 2016-11-01 | 2017-03-31
75084 | RELDFA | G2535 | EMAX 1783672 7660 Turfway Rd | -557.05 |  | -557.05 |  |  | 72632.23 | 74947.26 | -2315.03 | 2011-03-04 | 2012-03-31 | 2011-03-01 | 2012-02-04
75084 | RELDFA | G0973 | EMAX #1009228 Taylor Mill Reconst | -2547.21 |  | -2547.21 |  |  | 19291.5 | 109860.93 | -90569.43 | 2010-09-14 | 2015-06-30 | 2010-09-01 | 2012-02-28
75084 | RELDFA | G5515 | EMAX 2690060 377 Richwood Rd | -42.12 |  | -42.12 |  |  | 127.3 | 10846.41 | -10719.11 | 2011-10-27 | 2012-03-31 | 2011-11-01 | 2012-02-17
75084 | RELDFA | RELDKY | Relocation-D | 523137.11 |  | 523137.11 |  |  | 1190774.04 | 200 | 1190574.04 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | RELDFA | MKRDYKY | Make Ready Kentucky | 279697.8 |  | 279697.8 |  |  | 400043.65 | 10 | 400033.65 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084 | SGKYDMS | SGDEETSW | SG DMS Distribution DEETS SW | 0.01 |  | 0.01 |  |  | 18945.77 | 23915.77 | -4970 | 2011-09-30 | 2014-10-31 | 2011-10-01 | 2013-07-29
75084 | ORDFA | SKY1603DC | DEK O&M TO CAPITAL JOURNAL Strm 3 | 1910.29 |  | 1910.29 |  |  | 6768.1 | 6788.79 | -20.69 | 2016-04-28 19:32 | 2016-12-31 | 2016-06-01 | 2016-08-30
75084 | ORDFA | ORDKY | Outage Restoration Cap-D | -29211.53 |  | -29211.53 |  |  | 130493.59 | 200 | 130293.59 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | ORDFA | OUTRFUKY | Outage Reliability FollowUp Capital | -38051.8 |  | -38051.8 |  |  | -38051.8 | 50000 | -88051.8 | 2012-05-09 | 2050-12-31 | 2012-09-01
75084 | ORDFA | PDOHRPLKY | Public Damage Replace OH - Kentucky | 26570.68 |  | 26570.68 |  |  | 100453.09 | 1 | 100452.09 | 2015-06-13 14:43 | 2025-12-31 | 2016-02-01
75084 | ORDFA | OUTOHRLKY | Outage Replace OH - Kentucky | -316009.55 |  | -316009.55 |  |  | 440204.45 | 10 | 440194.45 | 2015-06-13 14:20 | 2025-12-31 | 2016-02-01
75084 | ORDFA | PDUGRPLKY | Public Damage Replace UG - Kentucky | 8421.89 |  | 8421.89 |  |  | 64371.14 | 1 | 64370.14 | 2015-06-13 14:53 | 2025-12-31 | 2016-03-01
75084 | ORDFA | OUTUGRLKY | Outage Replace UG - Kentucky | 772964.34 |  | 772964.34 |  |  | 1293827.64 | 0 | 1293827.64 | 2015-06-13 14:34 | 2025-12-31 | 2016-02-01
75084 | ORDFA | SKY1702DC | Kentucky O&M TO CAP JOURNAL Strm 2 | 122193.25 |  | 122193.25 |  |  | 122193.25 | 109852.57 | 12340.68 | 2017-02-21 16:08 | 2017-10-31 | 2017-03-01 | 2017-07-31
75084 | ORDFA | SKY1703DC | Kentucky O&M TO CAP JOURNAL Strm 3 | 11128.8 |  | 11128.8 |  |  | 11128.8 | 11181.97 | -53.17 | 2017-02-21 16:12 | 2017-12-31 | 2017-06-01 | 2017-09-30
75084 | ORDFA | SKY1706DC | TO CAPTURE 2017 CAPITAL STORM # 6 | 1794.99 |  | 1794.99 |  |  | 1794.99 | 2072.07 | -277.08 | 2017-07-13 13:41 | 2018-12-31 | 2017-08-01 | 2017-11-30
75084 | ORDFA | SKY1707DC | TO CAPTURE 2017 CAPITAL STORM # 7 | 6866.26 |  | 6866.26 |  |  | 6866.26 | 6509.66 | 356.6 | 2017-07-13 13:44 | 2018-12-31 | 2017-09-01 | 2017-12-31
75084 | ORDFA | SKY1612DC | DEK O&M TO CAPITAL JOURNAL Strm 12 | 4978.24 |  | 4978.24 |  |  | 4978.24 | 4787.25 | 190.99 | 2016-12-31 15:38 | 2017-04-30 | 2017-01-01 | 2017-04-15
75084 | RELTFA | KYRELT1 | F6763 DOT Mt Zion Rd-Dixie Hwy | 28745.86 |  | 28745.86 |  |  | 31910.34 | 35000 | -3089.66 | 2015-07-25 18:59 | 2020-05-13 | 2015-08-01
75084 | AMKY0808 | H0296 | Crescent Install 22.4MVA TB3 | -56.52 |  | -56.52 |  |  | 1786138.22 | 1654143 | 131995.22 | 2013-06-20 | 2015-09-01 | 2013-08-01 | 2015-09-03
75084 | AMKY0808 | H0299 | Crescent 46 OH Part1 | 1624.78 |  | 1624.78 |  |  | 15231.26 | 377337 | -362105.74 | 2013-06-21 | 2019-03-31 | 2015-06-01 | 2018-07-10
75084 | DECCIRFA | P7274 | DEC 6892567 Donaldson 41 | 62982.26 |  | 62982.26 |  |  | 151265.08 | 205737.82 | -54472.74 | 2015-01-14 | 2019-06-30 | 2015-01-01
75084 | DECCIRFA | P7273 | DEC 6892574 Donaldson 41 | 32456.21 |  | 32456.21 |  |  | 165367 | 88334.91 | 77032.09 | 2015-01-14 | 2017-11-15 | 2015-01-01 | 2017-10-27
75084 | 314G8840 | D1640 | PP938046 COVINGTON 41 UG PART | -67913.68 |  | -67913.68 |  |  | 822744.84 | 877242 | -54497.16 | 2007-09-20 | 2009-04-30 | 2007-11-01 | 2008-12-01
75084 | PILCFA | POTTKY | Dline Pothead Termination KY | 60572.36 |  | 60572.36 |  |  | 60572.36 | 60000 | 572.36 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084 | PILCFA | PILCKY | UG Cable Repl-PILC | 6546.43 |  | 6546.43 |  |  | 22825.08 | 100 | 22725.08 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084 | UGCRFA | UGCRKY | UG Cable Repl | -65507.31 |  | -65507.31 |  |  | 356559.41 | 100 | 356459.41 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | UGCRFA | SUGCRKY | UG Secondary Cable Replace | 378.07 |  | 378.07 |  |  | 665.68 | 10 | 655.68 | 2015-02-24 10:56 | 2025-12-31 | 2016-10-01
75084 | FLKY0249E | DUKETCKYE | Fleet On-Road Vehicles - elec - KY | -51637.44 |  | -51637.44 |  |  | -1261.88 | 40000 | -41261.88 | 2009-08-11 | 2050-12-31 | 2010-06-01 | 2016-04-05
75084 | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | 257906.43 |  | 257906.43 |  |  | 1003917.53 | 10 | 1003907.53 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084 | CSPFA | J4106 | TR 5225496 Augustine 44 | 2879.56 |  | 2879.56 |  |  | 66316.97 | 106661.94 | -40344.97 | 2014-03-31 | 2017-01-31 | 2016-05-01 | 2016-11-23
75084 | CSPFA | J4104 | TR 5249008 Longbranch 42 | 3128 |  | 3128 |  |  | 157126.92 | 187480.99 | -30354.07 | 2014-03-31 | 2017-01-31 | 2015-05-01 | 2016-11-02
75084 | CSPFA | J5116 | TR 5263786 Cold Spring 41 | -466.87 |  | -466.87 |  |  | 120529.47 | 221710.6 | -101181.13 | 2014-04-02 | 2017-01-31 | 2016-05-01 | 2016-11-05
75084 | CSPFA | H1372 | TR 4655448 CLARYVILLE 41 | -36585.25 |  | -36585.25 |  |  | 261680.05 | 331178.02 | -69497.97 | 2013-12-03 | 2016-12-30 | 2014-10-01 | 2016-09-08
75084 | CSPFA | CSPKY | Transformer Retrofit | 544293.8 |  | 544293.8 |  |  | 712538.05 | 200 | 712338.05 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | CSPFA | J9110 | TR 5301582 Alexandria South 41 | -47802.58 |  | -47802.58 |  |  | 135755.99 | 477036.32 | -341280.33 | 2014-04-10 | 2017-08-15 | 2016-04-01 | 2017-03-15
75084 | CSPFA | J5122 | TR 5267739 Cold Spring 49 | -8692.16 |  | -8692.16 |  |  | 150905.24 | 574055.99 | -423150.75 | 2014-04-02 | 2018-01-31 | 2016-05-01 | 2017-07-28
75084 | NBFA | H1381 | JT 4655806 Arcadia West PH A electr | -63.4 |  | -63.4 |  |  | 73589.84 | 149749.52 | -76159.68 | 2013-12-04 | 2014-11-29 | 2013-12-01 | 2014-07-28
75084 | NBFA | H0638 | NB emax 3296995 Arcadia Ph A | 65977.39 |  | 65977.39 |  |  | 4.0018e-11 | 92754.88 | -92754.88 | 2013-08-27 | 2014-11-30 | 2013-09-01 | 2014-03-27
75084 | NBFA | NBKY | Customer Adds-MW-D | 13785.87 |  | 13785.87 |  |  | 5049036.69 | 200 | 5048836.69 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | NBFA | IKKY2016 | 2016 KY Dist Lines (IK) Roll | 2666843.12 |  | 2666843.12 |  |  | 6564496.86 | 1 | 6564495.86 | 2015-11-30 15:55 | 2016-12-31 | 2015-12-01
75084 | NBFA | NBKYCI | Commerc & Indust Cust Adds-MW-D | 186829.05 |  | 186829.05 |  |  | 1212361.07 | 0 | 1212361.07 | 2016-01-21 13:58 | 2025-12-31 | 2016-02-01
75084 | NBFA | NBKYRES | Residential Customer Adds-MW-D | 607128.35 |  | 607128.35 |  |  | 2247371.46 | 0 | 2247371.46 | 2016-01-21 13:51 | 2025-12-31 | 2016-02-01
75084 | NBFA | IKKY2016T | 2016 KY Dist Lines (IK) Roll - T | 756089.39 |  | 756089.39 |  |  | 4786793.08 | 1 | 4786792.08 | 2015-11-30 16:03 | 2016-12-31 | 2015-12-01
75084 | NBFA | KIP101022 | NB 21101022 Litton Lane | 101928.88 |  | 101928.88 |  |  | 101928.88 | 95347.37 | 6581.51 | 2017-06-16 13:51 | 2018-03-31 | 2017-06-01 | 2017-11-03
75084 | CSFA | CSKY | Circuit Sectionalization | 123232.1 |  | 123232.1 |  |  | 149174.68 | 100 | 149074.68 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084 | KHRF77294 | KHR177294 | DOT 7177294 Hebron 42, in | 14915.57 |  | 14915.57 |  |  | 118118.67 | 46889.01 | 71229.66 | 2015-11-19 14:04 | 2016-08-09 | 2015-12-01 | 2016-06-17
75084 | SGSNIF | SGSNI01 | SG Secure Network Infrastructure | -0.17 |  | -0.17 |  |  | 64179.53 | 50075 | 14104.53 | 2014-12-12 | 2016-08-30 | 2014-12-01 | 2016-04-30
75084 | SGSNIF | SGSNI03 | SG SNI - IPv6 | 46.7 |  | 46.7 |  |  | 18283.74 | 12974 | 5309.74 | 2016-02-15 15:40 | 2017-02-28 | 2016-02-01 | 2017-02-28
75084 | SGSNIF | SGSNI04 | SG SNI - IPv6 | -3.3 |  | -3.3 |  |  | 8874.83 | 25947 | -17072.17 | 2016-02-18 12:04 | 2017-02-28 | 2016-02-01 | 2017-02-28
75084 | SGSNIF | SGSNI02 | SG Secure Network Infrastructure | 0.05 |  | 0.05 |  |  | 39875.29 | 50075 | -10199.71 | 2014-12-12 | 2016-06-30 | 2014-12-01 | 2016-04-30
75084 | CP16AREK | 16AR03 | Buffington Repl LA's | 4533.86 |  | 4533.86 |  |  | 42739.64 | 23111.8 | 19627.84 | 2016-02-18 14:52 | 2017-03-31 | 2016-10-01 | 2017-03-01
75084 | FMWCF53SK | CF53AUGUS | Purch Panasonic CF53s repl MDTs | 1115.89 |  | 1115.89 |  |  | 282322.74 | 158146 | 124176.74 | 2014-08-04 | 2017-03-31 | 2014-09-01 | 2017-03-05
75084 | AMIKYCS | C9045 | AMI Donaldson Advanced Meter | -15076.1 |  | -15076.1 |  |  | 41000.33 | 151468 | -110467.67 | 2016-06-29 07:48 | 2017-09-30 | 2016-06-01 | 2007-11-30
75084 | AMIKYCS | C9052 | AMI Buffington Advance Metering | -28434.45 |  | -28434.45 |  |  | 40866.61 | 75000 | -34133.39 | 2016-06-29 16:36 | 2019-03-31 | 2016-06-01
75084 | AMIKYCS | C9048 | AMI Claryville Advanced Metering | -13528.08 |  | -13528.08 |  |  | -1.89e-12 | 15000 | -15000 | 2016-06-29 16:19 | 2019-03-30 | 2016-06-01
75084 | AMIKYCS | C9051 | AMI Dixie Advanced Metering | -3207.42 |  | -3207.42 |  |  | 9707.01 | 17000 | -7292.99 | 2016-06-29 16:33 | 2019-03-31 | 2016-06-01
75084 | AMIKYCS | C9044 | AMI Wilder Advanced Meter | -38538.65 |  | -38538.65 |  |  | -1.8474e-12 | 40000 | -40000 | 2016-06-28 12:28 | 2019-03-30 | 2016-06-01
75084 | AMIKYCS | C9047 | AMI Atlas Advanced Metering | -10584 |  | -10584 |  |  | -3.979e-13 | 12000 | -12000 | 2016-06-29 16:13 | 2019-03-31 | 2016-06-01
75084 | AMIKYCS | C9049 | AMI Florence Advance Metering | -35354.59 |  | -35354.59 |  |  | 41159.31 | 80000 | -38840.69 | 2016-06-29 16:25 | 2019-03-31 | 2016-06-01
75084 | AMIKYCS | C9050 | AMI Villa Advanced Metering | -5749.65 |  | -5749.65 |  |  | 40690.35 | 50000 | -9309.65 | 2016-06-29 16:29 | 2019-03-31 | 2016-06-01
75084 | AMIKYCS | D1128 | AMI Thomas More Advance Meter | -10584 |  | -10584 |  |  | 0 | 11000 | -11000 | 2016-06-29 16:40 | 2019-03-31 | 2016-06-01
75084 | FDOMSIMPL | PCTAIT223 | DOMS IMPLEMENTATION W/AMI | 546.19 |  | 546.19 |  |  | 214380.11 | 216000 | -1619.89 | 2013-10-25 | 2016-12-31 | 2013-11-01 | 2017-01-15
75084 | FDOMSIMPL | G9136 | DOMS IMPLEMENTATION W/AMI | 27 |  | 27 |  |  | 10745.62 | 216000 | -205254.38 | 2012-12-20 | 2017-03-31 | 2013-01-01 | 2017-01-15
75084 | AMKY1168 | P7405 | KY Univ Bus 4 Swgr and CB Repl | -39054.39 |  | -39054.39 |  |  | 1783179.16 | 741889 | 1041290.16 | 2015-01-22 | 2017-03-31 | 2015-02-01 | 2017-03-02
75084 | CP16SPCK | 16SPC157 | Dixie Inst Oil Cont | 19667.49 |  | 19667.49 |  |  | 26040.92 | 64482 | -38441.08 | 2016-08-17 12:24 | 2017-09-01 | 2016-10-01 | 2017-05-14
75084 | CP16SPCK | 16SPC156 | Covington Inst Oil Cont | 18598.38 |  | 18598.38 |  |  | 26294.54 | 51549 | -25254.46 | 2016-08-17 12:21 | 2018-03-01 | 2016-10-01 | 2017-06-15
75084 | CP16SPCK | 16SPC153 | Grant Inst Oil Cont | 25090.59 |  | 25090.59 |  |  | 31587.81 | 59427 | -27839.19 | 2016-08-17 11:37 | 2018-03-01 | 2016-10-01 | 2017-05-13
75084 | CP16SPCK | 16SPC152 | Dayton Inst Oil Cont | 22475.1 |  | 22475.1 |  |  | 30427.44 | 59427 | -28999.56 | 2016-08-17 11:33 | 2017-09-01 | 2016-10-01 | 2017-05-18
75084 | CP16SPCK | 16SPC155 | Augustine Inst Oil Cont | 17108.41 |  | 17108.41 |  |  | 23696.41 | 37723 | -14026.59 | 2016-08-17 12:02 | 2017-09-01 | 2016-10-01 | 2017-06-15
75084 | CP16SPCK | 16SPC151 | Beaver Inst Oil Cont | 20058.73 |  | 20058.73 |  |  | 29077.38 | 69707 | -40629.62 | 2016-08-17 11:30 | 2017-09-01 | 2016-10-01 | 2017-04-20
75084 | CP16SPCK | 16SPC154 | Longbranch Inst Oil Cont | 19349.99 |  | 19349.99 |  |  | 26104.96 | 49185 | -23080.04 | 2016-08-17 11:42 | 2018-03-01 | 2016-10-01 | 2017-05-23
75084 | CP16SPCK | 16SPC158 | Hands Inst Oil Cont | 26719.58 |  | 26719.58 |  |  | 26829.52 | 47771 | -20941.48 | 2016-08-17 12:26 | 2018-03-31 | 2016-12-01 | 2018-03-05
75084 | KEFF91578 | KUS191578 | NB 7191578 Renshaw Retire | 178.15 |  | 178.15 |  |  | 134200.54 | 105542.36 | 28658.18 | 2016-02-12 14:05 | 2017-03-30 | 2016-08-01 | 2017-02-14
75084 | NCIPLOWK | KCIPLW002 | Wilder-Ky NERC CIP Low DS | 117702.41 |  | 117702.41 |  |  | 216596.96 | 195329 | 21267.96 | 2016-09-22 13:54 | 2017-09-01 | 2016-09-01 | 2017-06-09
75084 | NCIPLOWK | KCIPLW004 | Buffington - Ky NERC CIP Low | 210205.31 |  | 210205.31 |  |  | 218405.84 | 195323 | 23082.84 | 2016-11-17 13:03 | 2018-03-31 | 2016-11-01 | 2017-08-10
75084 | NCIPLOWK | KCIPLW003 | York - Ky NERC CIP Low | 118808.73 |  | 118808.73 |  |  | 126601.93 | 125323 | 1278.93 | 2016-11-17 12:52 | 2018-03-31 | 2016-11-01 | 2017-07-05
75084 | NCIPLOWK | KCIPLW001 | Augustine KY NERC CIP LW | 74926.71 |  | 74926.71 |  |  | 174011.5 | 195323 | -21311.5 | 2016-09-22 10:40 | 2018-03-31 | 2016-09-01 | 2018-02-28
75084 | NCIPLOWK | KCIPLW999 | Electronic Keys | 41809.7 |  | 41809.7 |  |  | 41809.7 | 29929 | 11880.7 | 2017-11-17 14:50 | 2020-03-31 | 2017-11-01
75084 | NCIPLOWK | KCIPLW086 | Mt_ Zion - Ky NERC CIP Low - NCIPLO | 23790.8 |  | 23790.8 |  |  | 23790.8 | 195323 | -171532.2 | 2017-02-09 15:51 | 2019-03-31 | 2017-03-01 | 2018-05-22
75084 | NCIPLOWK | KCIPLW074 | Cold Spring - Ky NERC CIP Low - NCI | 25583.15 |  | 25583.15 |  |  | 25583.15 | 195323 | -169739.85 | 2017-02-09 13:39 | 2019-03-31 | 2017-03-01 | 2018-06-27
75084 | NCIPLOWK | KCIPLW075 | Constance - Ky NERC CIP Low - NCIPL | 27481.43 |  | 27481.43 |  |  | 27481.43 | 195323 | -167841.57 | 2017-02-09 13:48 | 2019-03-31 | 2017-03-01 | 2018-05-27
75084 | NCIPLOWK | KCIPLW082 | Hebron - Ky NERC CIP Low - NCIPLOWK | 21639.93 |  | 21639.93 |  |  | 21639.93 | 195323 | -173683.07 | 2017-02-09 15:17 | 2019-03-31 | 2017-04-01 | 2018-07-12
75084 | NCIPLOWK | KCIPLW083 | Kenton - Ky NERC CIP Low - NCIPLOWK | 24875.05 |  | 24875.05 |  |  | 24875.05 | 195323 | -170447.95 | 2017-02-09 15:25 | 2019-03-31 | 2017-03-01 | 2018-07-10
75084 | NCIPLOWK | KCIPLW080 | Florence - Ky NERC CIP Low - NCIPLO | 26880.9 |  | 26880.9 |  |  | 26880.9 | 195323 | -168442.1 | 2017-02-09 14:57 | 2019-03-31 | 2017-05-01 | 2018-06-08
75084 | NCIPLOWK | KCIPLW079 | Donaldson - Ky NERC CIP Low - NCIPL | 43054.52 |  | 43054.52 |  |  | 43054.52 | 195323 | -152268.48 | 2017-02-09 14:50 | 2019-03-31 | 2017-03-01 | 2018-06-01
75084 | NCIPLOWK | KCIPLW072 | Bellevue - Ky NERC CIP Low - NCIPLO | 70627.65 |  | 70627.65 |  |  | 70627.65 | 195499.57 | -124871.92 | 2017-02-08 13:43 | 2017-11-21 | 2017-03-01 | 2017-12-13
75084 | NCIPLOWK | KCIPLW081 | Hands - Ky NERC CIP Low - NCIPLOWK | 22544.84 |  | 22544.84 |  |  | 22544.84 | 195323 | -172778.16 | 2017-02-09 15:04 | 2019-03-31 | 2017-05-01 | 2018-07-05
75084 | NCIPLOWK | KCIPLW078 | Dayton - Ky NERC CIP Low - NCIPLOWK | 20512.18 |  | 20512.18 |  |  | 20512.18 | 195323 | -174810.82 | 2017-02-09 14:42 | 2019-03-31 | 2017-03-01 | 2018-06-15
75084 | NCIPLOWK | KCIPLW084 | Kentucky University - Ky NERC CIP L | 103110.19 |  | 103110.19 |  |  | 103110.19 | 195323 | -92212.81 | 2017-02-09 15:36 | 2019-03-31 | 2017-03-01 | 2017-10-20
75084 | NCIPLOWK | KCIPLW077 | Crescent - Ky NERC CIP Low | 29333.65 |  | 29333.65 |  |  | 29333.65 | 195323 | -165989.35 | 2017-02-09 14:07 | 2019-03-31 | 2017-03-01 | 2018-06-06
75084 | KSLF53633 | KTM853633 | SL 6853633 Heights Blvd | 18.41 |  | 18.41 |  |  | 63161.47 | 122072 | -58910.53 | 2015-06-22 14:01 | 2016-12-11 | 2015-09-01 | 2016-02-21
75084 | TKY1687 | T1687DS2 | Alexandria Comm Upgrade - TKY1687 | 26037.34 |  | 26037.34 |  |  | 26037.34 | 68854 | -42816.66 | 2017-02-10 18:06 | 2018-11-08 | 2017-05-01 | 2018-11-08
75084 | TKY1687 | T1687DS5 | Verona Comm Upgrade - TKY1687 | 8313.03 |  | 8313.03 |  |  | 8313.03 | 68854 | -60540.97 | 2017-02-10 18:06 | 2018-09-30 | 2017-05-01 | 2018-07-26
75084 | TKY1687 | T1687DS4 | Richwood Comm Upgrade - TKY1687 | 4199.99 |  | 4199.99 |  |  | 4199.99 | 68854 | -64654.01 | 2017-02-10 18:06 | 2018-09-30 | 2017-05-01 | 2018-09-27
75084 | TKY1687 | T1687DS1 | Empire Comm Upgrade - TKY1687 | 2375.24 |  | 2375.24 |  |  | 2375.24 | 68854 | -66478.76 | 2017-02-10 18:06 | 2018-09-13 | 2017-05-01 | 2018-07-26
75084 | TKY1687 | T1687DS3 | Crittenden Comm Upgrade - TKY1687 | 7402.97 |  | 7402.97 |  |  | 7402.97 | 68854 | -61451.03 | 2017-02-10 18:06 | 2018-11-14 | 2017-05-01 | 2018-10-25
75084 | TKY1687 | T1687DS6 | White Tower Comm Upgrade - TKY1687 | 15733.19 |  | 15733.19 |  |  | 15733.19 | 68854 | -53120.81 | 2017-02-10 18:06 | 2018-11-14 | 2017-05-01 | 2018-10-11
75084 | DPEQUIPKY | EMR435 | Hebron Repl LTC Controllers - DPEQ | 1898.19 |  | 1898.19 |  |  | 1898.19 | 66338 | -64439.81 | 2017-06-02 10:04 | 2019-03-01 | 2017-07-01 | 2018-07-26
75084 | DPEQUIPKY | EMR436 | Oakbrook Repl LTC Controllers - DP | 2755.25 |  | 2755.25 |  |  | 2755.25 | 66338 | -63582.75 | 2017-06-02 10:07 | 2019-03-01 | 2017-07-01 | 2018-07-13
75084 | DPEQUIPKY | EMR364 | Villa Repl Bus1 SG Bush & LA's | 25658.48 |  | 25658.48 |  |  | 25658.48 | 10730 | 14928.48 | 2017-03-16 16:09 | 2018-03-31 | 2017-03-01 | 2017-06-30
75084 | DPEQUIPKY | EMR420 | Claryville Repl Cir 43 C Phase Reg | 18251.75 |  | 18251.75 |  |  | 18251.75 | 20222.39 | -1970.64 | 2017-05-18 10:15 | 2018-03-31 | 2017-05-01 | 2017-08-18
75084 | DPEQUIPKY | EMR377 | Empire Repl Station Batteries | 4175.72 |  | 4175.72 |  |  | 4175.72 | 1746.5 | 2429.22 | 2017-03-29 14:48 | 2018-03-31 | 2017-04-01 | 2017-09-28
75084 | DPEQUIPKY | EMR307 | Buffington Repl Bk4 LS LA's | 702.1 |  | 702.1 |  |  | 702.1 | 2764.91 | -2062.81 | 2017-02-01 12:33 | 2018-03-31 | 2017-02-01 | 2017-03-20
75084 | DPEQUIPKY | EMR347 | Decoursey Repl Cir 41 Reclosers | 47779.76 |  | 47779.76 |  |  | 47779.76 | 11949.13 | 35830.63 | 2017-03-03 16:23 | 2018-03-31 | 2017-03-01 | 2017-09-09
75084 | DKY2149 | D2149DL1 | AM 20708188 Beaver 41 Part 1B | 277496.91 |  | 277496.91 |  |  | 277496.91 | 178674.81 | 98822.1 | 2017-02-14 09:19 | 2018-03-31 | 2017-02-01 | 2018-03-06
75084 | DKY2149 | D2149DL2 | AM 20709176 Walton 2 Intercon | 50484.51 |  | 50484.51 |  |  | 50484.51 | 31950.28 | 18534.23 | 2017-02-14 09:34 | 2018-07-31 | 2017-10-01 | 2018-03-11
75084 | SG000430F | SG430B | Aero Pkwy Instl UG Cable | 1374969.36 |  | 1374969.36 |  |  | 1385384.96 | 1003250.66 | 382134.3 | 2016-04-04 13:41 | 2018-03-31 | 2016-04-01 | 2018-03-31
75084 | SG000430F | SG430C | Aero Pkwy Instl OH | -362.02 |  | -362.02 |  |  | 64896 | 29984.55 | 34911.45 | 2016-04-04 13:42 | 2017-09-01 | 2016-04-01 | 2016-12-02
75084 | SG000430F | SG430A | Aero Pkwy Instl UG Conduit | 603859.56 |  | 603859.56 |  |  | 1977838 | 1185872.83 | 791965.17 | 2016-04-04 13:28 | 2018-03-31 | 2016-04-01 | 2017-06-21
75084 | AMKY0035 | E9945 | Augustine 42 PILC Cable Replacement | -62621.14 |  | -62621.14 |  |  | 374285.18 | 431601 | -57315.82 | 2009-09-03 | 2010-05-31 | 2009-09-01 | 2010-06-09
75084 | DKY1930 | D1930DL2 | AM Erlanger Rd | 17189.83 |  | 17189.83 |  |  | 17189.83 | 75463.43 | -58273.6 | 2017-04-13 11:13 | 2018-06-15 | 2017-06-01 | 2018-04-05
75084 | DKY1930 | D1930DL1 | AM 11851684 Recd Donaldson 42 Riggs | 57912.32 |  | 57912.32 |  |  | 57912.32 | 261996.83 | -204084.51 | 2016-12-19 09:23 | 2018-08-30 | 2017-01-01 | 2018-08-30
75084 | RCLFA | RCLKY | Recloser Inst/Rem | 108166.48 |  | 108166.48 |  |  | 181518.53 | 200 | 181318.53 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | 314G8846 | D1644 | PP938164 Covington 43- UG part | -49905.46 |  | -49905.46 |  |  | 160255.54 | 207242 | -46986.46 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-12-01
75084 | AMKY0088 | G3276 | Mt Zion Rd Reconductor 2 | 690.13 |  | 690.13 |  |  | 251581.21 | 663636.23 | -412055.02 | 2011-05-05 | 2012-03-31 | 2011-05-01 | 2012-05-14
75084 | U04ZUR | C9034 | ULH&P 2005 Upgrade and Replace | 0 |  | 0 |  |  | -208.67 | 75231 | -75439.67 | 2007-01-04 | 2007-01-31 | 2006-12-01 | 2007-01-31
75084 | U04ZUR | C8961 | pp 870018/joe groeschen | 1015.14 |  | 1015.14 |  |  | 565.94 | 0 | 565.94 | 2007-01-03 | 2007-05-01 | 2007-01-01 | 2007-02-01
75084 | U14ZGM | D1727 | RI-12TH ST RECONST -I-75/SCOTT | -11950.71 |  | -11950.71 |  |  | 108956.19 | 60754 | 48202.19 | 2007-10-03 | 2012-10-01 | 2009-02-01 | 2009-12-15
75084 | RLFA | RLKY | Reliability Other-FO-D | 453675.72 |  | 453675.72 |  |  | 1167096.71 | 200 | 1166896.71 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | RLFA | LPFUKY | Line Patrol Insp followup KY | 1045185.82 |  | 1045185.82 |  |  | 1044602.3 | 400000 | 644602.3 | 2010-12-22 | 2015-12-31 | 2011-03-01
75084 | RLFA | LPSMEIKY | Dline Patrol SMEI Capital Followup | 23039 |  | 23039 |  |  | 23039 | 75000 | -51961 | 2012-04-30 | 2050-12-31 | 2013-02-01
75084 | RLFA | DLSKY | DLine Switches 34.5kv Replace KY | 24398.63 |  | 24398.63 |  |  | 25280.88 | 9 | 25271.88 | 2014-08-04 | 2020-12-31 | 2016-03-01
75084 | TMAJRIFA1 | EMR173 | Wilder Repl failed bushings | 86373.51 |  | 86373.51 |  |  | 86812.94 | 38599.82 | 48213.12 | 2016-09-13 11:41 | 2018-03-31 | 2016-10-01 | 2017-11-02
75084 | FFOOTPRNT | FOOTPRNSW | Footprints Upgrade Project | 2427.87 |  | 2427.87 |  |  | 5652.56 | 4705 | 947.56 | 2016-08-12 15:50 | 2017-08-15 | 2016-09-01 | 2017-08-23
75084 | SGPMYUF | SGYFA2SW | DEE YFA Ver 2 DER - Software | 3541.39 |  | 3541.39 |  |  | 24961.65 | 36217 | -11255.35 | 2016-01-08 10:09 | 2017-05-24 | 2016-01-01 | 2017-03-07
75084 | AMKY0326 | G0852 | Augustine 43 PILC Cable Replacement | -36825.59 |  | -36825.59 |  |  | 130560.7 | 201531 | -70970.3 | 2010-09-01 | 2011-09-30 | 2010-10-01 | 2011-06-14
75084 | MOFA | MOKY | Major Outage Followup-D | 32219.89 |  | 32219.89 |  |  | 32219.89 | 100 | 32119.89 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084 | PRDFA | PRDKY | Pole Repl Other-D | 552176.97 |  | 552176.97 |  |  | 1329850.73 | 200 | 1329650.73 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | KETF47303 | KET347303 | DET 7347303 Beaver 41 | -22469.42 |  | -22469.42 |  |  | 225325.04 | 145648.28 | 79676.76 | 2015-06-03 14:01 | 2016-10-29 | 2015-06-01 | 2016-05-03
75084 | SGITRONLF | SGITRONL | SG Itron Meter Licenses | -229 |  | -229 |  |  | 148524.18 | 148524.18 | 0 | 2015-12-30 11:54 | 2016-04-30 | 2015-12-01 | 2016-04-30
75084 | 314G8917 | D8917DL | AM 8915089 KY University UG | 30245.98 |  | 30245.98 |  |  | 210586.77 | 218868.92 | -8282.15 | 2015-10-08 14:59 | 2016-10-29 | 2015-10-01 | 2016-09-27
75084 | TKY1672 | T1672TS1 | F965 Kenton Rel Repl | 241538.75 |  | 241538.75 |  |  | 330720.27 | 348325 | -17604.73 | 2016-09-27 18:02 | 2018-03-31 | 2016-10-01 | 2017-07-06
75084 | TKY1672 | T1672TS2 | F965 Wilder Rel Repl | 212458.84 |  | 212458.84 |  |  | 371986.62 | 326080 | 45906.62 | 2016-09-27 18:02 | 2018-03-31 | 2016-10-01 | 2017-08-10
75084 | CERTFA | CERTKY | Rel Major Cap T Equip Repl | 4336.97 |  | 4336.97 |  |  | 273435.37 | 100 | 273335.37 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | CERTFA | LPRFUKY | Line Patrol Followup Work | 307.68 |  | 307.68 |  |  | 568664.7 | 80000 | 488664.7 | 2013-03-20 | 2050-12-31 | 2013-11-01
75084 | CERTFA | KYCERT1 | CERTKY P0 CIR 966 | 866.06 |  | 866.06 |  |  | 5624.97 | 5000 | 624.97 | 2016-10-28 08:37 | 2017-06-30 | 2016-11-01 | 2017-03-31
75084 | CERTFA | KYCERT2 | P2 Cir 5962 HL304,306,307,308,310,3 | 11543.09 |  | 11543.09 |  |  | 11543.09 | 27000 | -15456.91 | 2016-12-29 11:37 | 2018-03-31 | 2017-01-01 | 2017-05-01
75084 | 314G8914 | E6226 | KY Univ 43 UG Cable and Conduit | 10689.14 |  | 10689.14 |  |  | 1392973.05 | 1426651 | -33677.95 | 2009-05-07 | 2010-10-01 | 2009-05-01 | 2010-10-02
75084 | GLPRTFA | KYGLPR5 | GLT Cir 2862B P1-P2 | 30883.44 |  | 30883.44 |  |  | 56786.02 | 160000 | -103213.98 | 2016-06-13 16:14 | 2021-03-31 | 2016-07-01
75084 | GLPRTFA | KYGLPR11 | F5967 Repl HL867 to HL872 and HL876 | 39841.73 |  | 39841.73 |  |  | 39841.73 | 220579 | -180737.27 | 2016-11-14 13:36 | 2021-03-31 | 2017-05-01
75084 | GLPRTFA | GLPRTKY | Pole Repl Gnd Line-T | 3265.11 |  | 3265.11 |  |  | 513444.22 | 100 | 513344.22 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | GLPRTFA | KYGLPR4 | GLT Cir 6763 P2 Str 518 | -330.15 |  | -330.15 |  |  | 70214.05 | 40000 | 30214.05 | 2016-02-12 10:57 | 2018-02-01 | 2016-10-01 | 2017-03-02
75084 | KHRF28828 | KHR928828 | RI 9928828 Hands 428 | -128.88 |  | -128.88 |  |  | 183087.93 | 76177.94 | 106909.99 | 2016-03-16 14:04 | 2017-07-30 | 2016-03-01 | 2017-01-05
75084 | KUSF72128 | KUS172128 | NB 9172128 820 Dolwick UG | 9059.14 |  | 9059.14 |  |  | 94766.15 | 101906.76 | -7140.61 | 2016-02-08 14:04 | 2017-04-15 | 2016-04-01 | 2017-03-21
75084 | KFSF05496 | KFS705496 | CS 10705496 Bellevue 43 | 51758.47 |  | 51758.47 |  |  | 51758.47 | 53657.13 | -1898.66 | 2016-10-12 14:04 | 2017-09-30 | 2017-04-01 | 2017-08-24
75084 | SG000753F | SG753EQ | SG DEE Field Network Director - 753 | 102.28 |  | 102.28 |  |  | 102.28 | 3279 | -3176.72 | 2017-09-25 21:34 | 2018-11-18 | 2017-11-01 | 2018-11-08
75084 | SG000753F | SG753SW | SG DEE Field Network Director - 753 | 841.26 |  | 841.26 |  |  | 841.26 | 5093 | -4251.74 | 2017-09-25 21:04 | 2018-11-18 | 2017-10-01 | 2018-11-08
75084 | CP17BATK | 17BA23 | Verona Repl Batteries | 3146.39 |  | 3146.39 |  |  | 3146.39 | 3008.94 | 137.45 | 2017-06-02 15:53 | 2018-03-31 | 2017-06-01 | 2017-09-06
75084 | CP17BATK | 17BA31 | Crittenden Repl Batteries | 47.8 |  | 47.8 |  |  | 47.8 | 3524.3 | -3476.5 | 2017-07-05 14:53 | 2018-03-31 | 2017-12-01
75084 | CP17BATK | 17BA17 | Villa Repl Battery | 5184.05 |  | 5184.05 |  |  | 5184.05 | 5974.56 | -790.51 | 2017-03-31 15:44 | 2018-03-31 | 2017-06-01 | 2018-01-17
75084 | CP17BATK | 17BA15 | Oakbrook Repl Battery | 6387.94 |  | 6387.94 |  |  | 6387.94 | 8424.82 | -2036.88 | 2017-03-31 15:36 | 2018-03-31 | 2017-07-01 | 2018-01-13
75084 | CP17BATK | 17BA14 | Mt Zion Repl Battery | 8080.5 |  | 8080.5 |  |  | 8080.5 | 8424.82 | -344.32 | 2017-03-31 15:27 | 2018-03-31 | 2017-07-01 | 2018-01-20
75084 | CP17BATK | 17BA16 | Thomas More Repl Battery | 5762.63 |  | 5762.63 |  |  | 5762.63 | 8424.82 | -2662.19 | 2017-03-31 15:40 | 2018-03-31 | 2017-07-01 | 2017-12-29
75084 | CP17BATK | 17BA13 | Longbranch Repl Battery | 19230.86 |  | 19230.86 |  |  | 19230.86 | 15316.87 | 3913.99 | 2017-03-31 15:23 | 2018-03-31 | 2017-07-01 | 2018-01-17
75084 | CP17BATK | 17BA12 | Blackwell Repl Battery | 19152.62 |  | 19152.62 |  |  | 19152.62 | 15316.87 | 3835.75 | 2017-03-31 15:17 | 2018-03-31 | 2017-06-01 | 2017-09-23
75084 | CP17BATK | 17BA18 | York Repl Battery | 8122.62 |  | 8122.62 |  |  | 8122.62 | 8424.82 | -302.2 | 2017-03-31 15:48 | 2018-03-31 | 2017-07-01 | 2018-01-02
75084 | AMKY0750 | G8124 | Line Capacitor Installs for KY 2012 | -1332.79 |  | -1332.79 |  |  | 43228.02 | 53967.22 | -10739.2 | 2012-07-27 | 2013-03-31 | 2012-08-01 | 2013-03-31
75084 | KUSF97855 | KUS597855 | NB 7597855 Florence 44 St Rt 18 | -12266.88 |  | -12266.88 |  |  | 107224.34 | 101551.51 | 5672.83 | 2015-10-09 18:05 | 2016-04-19 | 2015-10-01 | 2016-03-29
75084 | DKY2205 | D2205DL1 | AM 20888790 Oakbrook 41-42 Rconf | 31600.76 |  | 31600.76 |  |  | 31600.76 | 36809.95 | -5209.19 | 2017-03-09 14:25 | 2018-07-31 | 2017-09-01 | 2018-06-02
75084 | ORTFA | ORTKY | Outage Restoration Cap-T | -2994.09 |  | -2994.09 |  |  | 15882.24 | 100 | 15782.24 | 2010-06-28 | 2050-12-31 | 2011-04-01
75084 | ORTFA | TK69V03 | KY Capital Storm Work | 376929.6 |  | 376929.6 |  |  | 376929.6 | 372000 | 4929.6 | 2016-12-13 09:52 | 2018-05-31 | 2017-05-01 | 2017-07-31
75084 | ORTFA | TK69V02 | KY Capital Storm Work | 13533.08 |  | 13533.08 |  |  | 13533.08 | 13221.16 | 311.92 | 2016-12-13 09:51 | 2017-12-31 | 2017-03-01 | 2017-07-31
75084 | ORTFA | TK69V01 | KY Capital Storm Work | 497835.1 |  | 497835.1 |  |  | 497835.1 | 454872.3 | 42962.8 | 2016-12-13 09:49 | 2017-12-31 | 2017-03-01 | 2017-07-31
75084 | ORTFA | KYRELT3 | Storm 03- Circuit 5967 | -189.38 |  | -189.38 |  |  | 33399.38 | 35000 | -1600.62 | 2016-11-14 16:28 | 2017-05-01 | 2016-11-01 | 2017-02-28
75084 | KTMF99778 | KTM499778 | SL 10499778 York 741 | -2062.42 |  | -2062.42 |  |  | 382203.79 | 295964.19 | 86239.6 | 2016-06-13 10:04 | 2017-02-28 | 2016-09-01 | 2017-02-15
75084 | SCFOFA | SCFOKY | System Capacity-FO | 347600.96 |  | 347600.96 |  |  | 497009.61 | 100 | 496909.61 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | SCFOFA | URDSTSP | Upgrade URD Subsm Transformers | 1082.56 |  | 1082.56 |  |  | 1082.56 | 49 | 1033.56 | 2017-05-26 16:16 | 2050-12-31 | 2017-10-01
75084 | U04ZGM | D1507 | ri-dolwick rd ginny meyer | 0 |  | 0 |  |  | 52045 | 52045 | 0 | 2007-08-30 | 2050-12-31 | 2009-11-01 | 2003-08-22
75084 | CAPFA | OTVSRKY | Cap Oil to Vac Switch Repl KY | 865.16 |  | 865.16 |  |  | 865.16 | 100000 | -99134.84 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084 | CAPFA | CAPAUTOKY | Capacitor Automation - Kentucky | 2584.09 |  | 2584.09 |  |  | 2584.09 | 49 | 2535.09 | 2014-01-15 | 2020-12-31 | 2014-03-01
75084 | CAPFA | CAPKY | Capacitor Inst/Rem | 29569.44 |  | 29569.44 |  |  | 229812.97 | 101 | 229711.97 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | VMTDFA | VMTDKY | Trans Line Clr Removal | 266686.9 |  | 266686.9 |  |  | 528641.96 | 2 | 528639.96 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | VMDDTFA | VMDDTKY | Distr Line Clr Removal | 105411.8 |  | 105411.8 |  |  | 1932629.5 | 1 | 1932628.5 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | VMDDTFA | VMCMCKY | R/W CKT MAINT CAP KENTUCKY | 289105.86 |  | 289105.86 |  |  | 2268729.01 | 1 | 2268728.01 | 2012-01-25 | 2050-12-31 | 2012-02-01
75084 | TOOLFA | TOOLKY | Tools & Equip | 327834.85 |  | 327834.85 |  |  | 1783296.26 | 101 | 1783195.26 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084 | GLPRDFA | GLPRDKY | Pole Repl Gnd Line-D | 922649.62 |  | 922649.62 |  |  | 1772245.73 | 200 | 1772045.73 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | OLE08RPFA | OLERPKY | Kentcky Lighting Replacement - OLE | 116.1 |  | 116.1 |  |  | 3070.94 | 9 | 3061.94 | 2014-08-04 | 2020-12-31 | 2015-12-01
75084 | SLFA | SLKY | Light Repl-Tarriff | 60499.97 |  | 60499.97 |  |  | 209716.73 | 299 | 209417.73 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | SGAMF | SG344SW | SG DEE Distrib System Health - SW | 22447.81 |  | 22447.81 |  |  | 31651.17 | 73774 | -42122.83 | 2015-12-18 14:25 | 2019-11-30 | 2016-01-01
75084 | FTDITKE | TDITKE | PD KENTUCKY IT HARDWARE | 654.73 |  | 654.73 |  |  | 1389.64 | 1 | 1388.64 | 2010-07-01 | 2025-12-25 | 2016-05-01
75084 | SGDMSCF | SG361SW | SG DEE DMS Project 10 SW | 87.64 |  | 87.64 |  |  | 1145.49 | 266133.19 | -264987.7 | 2015-12-18 15:11 | 2021-01-31 | 2016-01-01
75084 | SG000336F | SG336SW | SG DEE DMS ADMS - Software | 129926.82 |  | 129926.82 |  |  | 141322.01 | 1049863.37 | -908541.36 | 2016-09-06 17:51 | 2021-04-01 | 2016-09-01
75084 | SG000445F | SGSUBTXKY | DEK URD Submersible Transformers | 42.56 |  | 42.56 |  |  | 26391.28 | 83 | 26308.28 | 2016-05-16 10:14 | 2025-12-31 | 2016-11-01
75084 | SG000436F | SGOTVKY | DEK Cap Cutout Repl-Oil-to-Vac | 31.95 |  | 31.95 |  |  | 31.95 | 83 | -51.05 | 2016-05-16 10:18 | 2025-12-31 | 2017-01-01
75084 | SG000601F | SG601SW | DEE ADP Software - 601 | 20379.36 |  | 20379.36 |  |  | 20379.36 | 42090 | -21710.64 | 2017-06-21 17:55 | 2022-06-01 | 2017-06-01
75084 | SGEAMIOCF | SG305SVRS | SG DEE OpenWay Ops Center Servers | 15560.43 |  | 15560.43 |  |  | 19714.42 | 5323.07 | 14391.35 | 2016-09-06 11:56 | 2020-03-31 | 2016-09-01
75084 | SGEAMIOCF | SG305SW | SG DEE OpenWay Ops Center Software | 92906.17 |  | 92906.17 |  |  | 99652.33 | 189544.12 | -89891.79 | 2016-08-01 10:09 | 2020-03-31 | 2016-08-01
75084 | DKY2199 | D2199DL3 | AM 21607381 Hebron | 3130.35 |  | 3130.35 |  |  | 3130.35 | 250919.99 | -247789.64 | 2017-06-27 13:39 | 2020-03-31 | 2017-11-01
75084 | DKY2199 | D2199DL2 | AM 21607299 Hebron - DKY2199 | 4869.38 |  | 4869.38 |  |  | 4869.38 | 238000.64 | -233131.26 | 2017-06-27 13:32 | 2020-03-31 | 2017-07-01
75084 | DKY2199 | D2199DL1 | AM 21606995 Hebron | 651.87 |  | 651.87 |  |  | 651.87 | 65607.29 | -64955.42 | 2017-06-27 13:20 | 2019-11-01 | 2017-12-01 | 2019-09-28
75084 | DKY2016 | D2016DS1 | Donaldson TB 3 - DKY2016 | 70844.18 |  | 70844.18 |  |  | 70844.18 | 4019811 | -3948966.82 | 2017-07-18 07:20 | 2019-12-27 | 2017-08-01
75084 | DKY2016 | D2016DS2 | Donaldson TB 4 - DKY2016 | 38243.98 |  | 38243.98 |  |  | 38243.98 | 3960624 | -3922380.02 | 2017-07-18 07:32 | 2020-01-16 | 2017-08-01
75084 | DKY2016 | MX2175246 | Donaldson 48 Ln Ext - DKY2016 | 15070.59 |  | 15070.59 |  |  | 15070.59 | 162040.89 | -146970.3 | 2017-10-12 12:00 | 2020-01-02 | 2017-10-01
75084 | 75084IK | KOUTUG | Outage Related UG Cap Replacements | 478589.63 |  | 478589.63 |  |  | 478589.63 | 93 | 478496.63 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOTT | Pothead Termination | 65590.06 |  | 65590.06 |  |  | 65590.06 | 93 | 65497.06 | 2017-03-27 12:34 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOH | Non-Emergency OH Corrective Replace | 4708.7 |  | 4708.7 |  |  | 4708.7 | 93 | 4615.7 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEOH | Emergency OH Corrective Replacement | 4603.97 |  | 4603.97 |  |  | 4603.97 | 93 | 4510.97 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KPOLIR | Non Emerg Pole Replace Insp Based | 48438.21 |  | 48438.21 |  |  | 48438.21 | 93 | 48345.21 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPDMCPU | Public Damage UG Capital Replacemnt | 4717.84 |  | 4717.84 |  |  | 4717.84 | 93 | 4624.84 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRIOTCO | OH Imprvmnt From PQRI Outage Invest | 33379.23 |  | 33379.23 |  |  | 33379.23 | 93 | 33286.23 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLCM | Reactive Pole Replacements | 57287.23 |  | 57287.23 |  |  | 57287.23 | 93 | 57194.23 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KPPL | Stub Pole Removal Only | 52.96 |  | 52.96 |  |  | 52.96 | 2 | 50.96 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KLPF | Line Patrol Follow Up | 166359.05 |  | 166359.05 |  |  | 166359.05 | 93 | 166266.05 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTR1PH | Single PH Transformer Replace Dry | 1300.69 |  | 1300.69 |  |  | 1300.69 | 93 | 1207.69 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRUCSM | UG Primary Small Cable Replacement | 11397.22 |  | 11397.22 |  |  | 11397.22 | 93 | 11304.22 | 2017-03-27 14:22 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCUG | Non-Emergency UG Corrective Repl | 279.07 |  | 279.07 |  |  | 279.07 | 93 | 186.07 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KRRR | Recloser Replacements | 6808.9 |  | 6808.9 |  |  | 6808.9 | 96 | 6712.9 | 2017-03-27 13:10 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRIOTCU | UG Imprvmnt From PQRI Outage Invest | 21038.46 |  | 21038.46 |  |  | 21038.46 | 93 | 20945.46 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCIPOH | C&I Customer Additions OH | 612502.97 |  | 612502.97 |  |  | 612502.97 | 93 | 612409.97 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLEIR | Emergency Pole Replace Insp Based | 4424.5 |  | 4424.5 |  |  | 4424.5 | 93 | 4331.5 | 2017-03-27 12:25 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCEUG | Emergency UG Corrective Replacement | 1053.74 |  | 1053.74 |  |  | 1053.74 | 93 | 960.74 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRSOH | Residential Cust Adds Single Fam OH | 598697.29 |  | 598697.29 |  |  | 598697.29 | 93 | 598604.29 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KSTMOH | OH Capital Replacement Due to Storm | 6628.2 |  | 6628.2 |  |  | 6628.2 | 93 | 6535.2 | 2017-03-27 14:40 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KPDMCAP | Public Damage OH Capital Replacemen | 56482.33 |  | 56482.33 |  |  | 56482.33 | 80 | 56402.33 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KOUTOH | Outage Related OH Cap Replacements | 126807.16 |  | 126807.16 |  |  | 126807.16 | 93 | 126714.16 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRUPOH | Residential Customer Upgrade OH | 1575.8 |  | 1575.8 |  |  | 1575.8 | 93 | 1482.8 | 2017-03-27 14:26 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KCIUPOH | C&I Customer Upgrade OH | -2935.42 |  | -2935.42 |  |  | -2935.42 | 93 | -3028.42 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRMOH | Residential Cust Adds Multi Fam OH | 8426.32 |  | 8426.32 |  |  | 8426.32 | 93 | 8333.32 | 2017-03-27 13:07 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTXO | Overhead Transformer Replacement | 3720.23 |  | 3720.23 |  |  | 3720.23 | 93 | 3627.23 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KUGCBINJ | UG Cable Injection | 176263.56 |  | 176263.56 |  |  | 176263.56 | 95 | 176168.56 | 2017-03-27 14:37 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRTR3PH | Three PH Transformer Replace Dry | 15948.6 |  | 15948.6 |  |  | 15948.6 | 95 | 15853.6 | 2017-03-27 13:26 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRCR | Capacitor Replacements & Assoc UOP | 975.14 |  | 975.14 |  |  | 975.14 | 90 | 885.14 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRGR | Regulator replacements | 4243.49 |  | 4243.49 |  |  | 4243.49 | 0 | 4243.49 | 2017-07-27 13:27 | 2067-12-31 | 2017-11-01
75084 | 75084IK | KET135853 | DET 10135853 Hands 44 310 | 301191.19 |  | 301191.19 |  |  | 302343.53 | 656630.49 | -354286.96 | 2016-11-07 10:03 | 2020-09-28 | 2016-12-01 | 2019-11-03
75084 | 75084IK | MX0924912 | MXCONV-JT- E TRIPLE CROWN SUBD SEC | -6802.39 |  | -6802.39 |  |  | -6802.39 | 213849.76 | -220652.15 | 2017-11-03 14:01 | 2018-03-01 | 2017-11-01 | 2018-05-07
75084 | 75084IK | MX1236245 | INFRASTRUCTIURE FOR SUBDIVISION D | -2424 |  | -2424 |  |  | -2424 | 30202.98 | -32626.98 | 2017-11-03 14:01 | 2018-06-01 | 2017-11-01 | 2018-07-12
75084 | 75084IK | MX2345743 | JT, E-EAGLE RIDGE PH. 2 PT. 2 | -1774 |  | -1774 |  |  | -1774 | 13650.65 | -15424.65 | 2017-12-18 14:01 | 2018-08-31 | 2017-12-01 | 2018-08-02
75084 | 75084IK | MX1675871 | INFRASTRUCTIURE FOR SUBDIVISION D | -2494 |  | -2494 |  |  | -2494 | 28275 | -30769 | 2017-11-03 14:01 | 2018-03-01 | 2017-12-01 | 2018-06-12
75084 | 75084IK | MX1691827 | INFRASTRUCTIURE FOR SUBDIVISION D | -1441 |  | -1441 |  |  | -1441 | 12916.08 | -14357.08 | 2017-11-03 14:01 | 2018-07-02 | 2017-11-01 | 2018-09-04
75084 | SG000440F | SGRFSKY | DEK Sectionalization | 51.67 |  | 51.67 |  |  | 51.67 | 83 | -31.33 | 2016-05-16 10:23 | 2025-12-31 | 2017-01-01
75084 | DKY2017 | D2017DL5 | RUSD Donaldson Hwy Retire - DKY2017 | 5534.35 |  | 5534.35 |  |  | 5534.35 | 12270.87 | -6736.52 | 2017-04-25 11:29 | 2020-05-31 | 2017-12-01
75084 | DKY2017 | D2017DL3 | AM 21113304 Davidson Hwy - DKY2017 | 3265.73 |  | 3265.73 |  |  | 3265.73 | 204529.81 | -201264.08 | 2017-04-17 15:00 | 2019-12-30 | 2017-07-01
75084 | DKY2017 | D2017DL1 | AM 21113152 Donaldson Hwy | 41001.88 |  | 41001.88 |  |  | 41001.88 | 0 | 41001.88 | 2017-04-17 14:46 | 2020-03-31 | 2017-04-01
75084 | DKY2019 | D2019DL2 | AM 21269675 Rbld Industrial Rd West | 16179.49 |  | 16179.49 |  |  | 16179.49 | 0 | 16179.49 | 2017-05-09 09:46 | 2020-03-31 | 2017-05-01
75084 | DKY2019 | D2019DL3 | AM 21269760 Rbld Industrial Rd East | 9179.07 |  | 9179.07 |  |  | 9179.07 | 0 | 9179.07 | 2017-05-09 09:51 | 2020-03-31 | 2017-07-01
75084 | DKY2019 | D2019DL1 | Dixie 45 46 Exits - DKY2019 | 713.38 |  | 713.38 |  |  | 713.38 | 263109.52 | -262396.14 | 2017-05-09 09:41 | 2019-11-29 | 2017-07-01 | 2019-10-03
75084 | TKY1935 | T1935DS1 | Hebron XTR Rel Rpl - TKY1935 | 2236.4 |  | 2236.4 |  |  | 2236.4 | 342079 | -339842.6 | 2017-07-13 14:02 | 2020-02-11 | 2017-11-01
75084 | TKY1695 | T1695TS2 | Kenton F966 Rel Repl - TKY1695 | 100132.2 |  | 100132.2 |  |  | 104844.6 | 352819 | -247974.4 | 2016-10-07 18:03 | 2020-04-18 | 2016-12-01
75084 | TKY1695 | T1695TS1 | Buffington F966 CB Rel Repl - TKY16 | 328503.61 |  | 328503.61 |  |  | 416242.88 | 1153424 | -737181.12 | 2016-10-07 18:03 | 2020-02-24 | 2016-10-01
75084 | TKY1695 | T1695TS3 | Villa F966 Rel Repl - TKY1695 | 40241.15 |  | 40241.15 |  |  | 112368.02 | 356799 | -244430.98 | 2016-10-07 18:03 | 2019-08-06 | 2016-12-01 | 2017-03-25
75084 | KUCF61121 | KUC261121 | UG 10261121 Villa 44 | 2694.73 |  | 2694.73 |  |  | 2694.73 | 131529.73 | -128835 | 2017-04-11 14:03 | 2019-06-30 | 2017-06-01
75084 | SG000223F | SG223SW | DEE Transmission Health & Risk Mgt | 198384.04 |  | 198384.04 |  |  | 198384.04 | 1016639 | -818254.96 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01
75084 | SG000438F | SGSELFKY | DEK Segmentation & Automation | 423.7 |  | 423.7 |  |  | 423.7 | 1 | 422.7 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01
75084 | 75084HW | KHWYR | Highway Relocations Reimb | 69137.81 |  | 69137.81 |  |  | 69137.81 | 80 | 69057.81 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01
75084 | 75084HW | KCOU | Make Ready Other Util Attachments | 222169.18 |  | 222169.18 |  |  | 222169.18 | 91 | 222078.18 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01
75084 | 75084HW | KCRFR | Customer Requested Mods Reimb | 151.14 |  | 151.14 |  |  | 151.14 | 98 | 53.14 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01
75084 | 75084HW | KHWYN | Highway Relocations Nonreimb | 30294.49 |  | 30294.49 |  |  | 30294.49 | 80 | 30214.49 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01
75084 | 75084HW | MX1661647 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 115.28 |  | 115.28 |  |  | 115.28 | 228.31 | -113.03 | 2017-11-28 14:01 | 2020-07-30 | 2017-12-01
75084 | 75084HW | MX6295870 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 5139.89 |  | 5139.89 |  |  | 5139.89 | 83155.24 | -78015.35 | 2017-11-30 18:02 | 2019-06-01 | 2017-12-01 | 2019-05-21
75084 | 75084HW | MX6342340 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 2067.75 |  | 2067.75 |  |  | 2067.75 | 109582.18 | -107514.43 | 2017-11-28 14:01 | 2018-07-01 | 2017-12-01 | 2018-07-25
75084 | SGEDMS3F | SGDMS3SW | DEE DMS 3.5 Upgrade - Software | 126327.81 |  | 126327.81 |  |  | 160398.55 | 210242 | -49843.45 | 2015-11-19 10:10 | 2021-01-31 | 2016-09-01
75084 | KECF20154 | KEC920154 | DEC 8920154 Kenton 46 | 18977.92 |  | 18977.92 |  |  | 22904.96 | 150467.62 | -127562.66 | 2015-10-23 10:05 | 2019-12-30 | 2016-09-01
75084 | UGCIFA | CABINJKY | Underground Cable Injection - KY | 254940.5 |  | 254940.5 |  |  | 254940.5 | 232000 | 22940.5 | 2011-03-15 | 2015-12-31 | 2011-04-01
75084 | KARF51805 | KAR851805 | LAR 10851805 Wilder 44 | 4780.75 |  | 4780.75 |  |  | 12216.1 | 313344.88 | -301128.78 | 2016-07-26 14:03 | 2019-10-21 | 2016-09-01
75084 | SG990151F | SRICVUGKY | GS DEK Targeted Underground Blanket | 272.02 |  | 272.02 |  |  | 272.02 | 1 | 271.02 | 2017-05-22 11:49 | 2050-12-31 | 2017-09-01
75084 | TLRKY | TLR69KY | KY T-Line Repl of 69kV | 9899.93 |  | 9899.93 |  |  | 9899.93 | 6 | 9893.93 | 2017-01-17 09:51 | 2050-12-31 | 2017-09-01
75084 | TKY1791 | T1791DS1 | Villa TB2 and Bus 2 Swgr Rpl - TKY1 | 29804.62 |  | 29804.62 |  |  | 29804.62 | 3017308 | -2987503.38 | 2017-05-17 14:03 | 2020-02-25 | 2017-07-01
75084 | TKY1791 | T1791TS1 | Villa 69kV Bus 1 CCVT Rpl - TKY1791 | 4704.72 |  | 4704.72 |  |  | 4704.72 | 79695 | -74990.28 | 2017-05-17 14:03 | 2020-07-31 | 2017-08-01
75084 | TKY2128 | T2128TS1 | Villa-Inst 69 kV Ring Bus - TKY2128 | 19284.34 |  | 19284.34 |  |  | 19284.34 | 4045269 | -4025984.66 | 2017-05-30 14:04 | 2020-03-17 | 2017-08-01
75084 | 75084IL | KCAL | Area Light New Installs | 49408.42 |  | 49408.42 |  |  | 49408.42 | 98 | 49310.42 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KLEDSL | LED Street Light Retrofit | 862.67 |  | 862.67 |  |  | 862.67 | 58 | 804.67 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01
75084 | 75084IL | KSLRPL | Street Light Replacements | 0.3 |  | 0.3 |  |  | 0.3 | 58 | -57.7 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KALRPL | Area Light Replacements | -412.01 |  | -412.01 |  |  | -412.01 | 58 | -470.01 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01
75084 | 75084IL | MX1977699 | BBB, Notre Dame Academy Lighti | 29429.74 |  | 29429.74 |  |  | 29429.74 | 61644.58 | -32214.84 | 2017-11-15 14:01 | 2018-04-03 | 2017-12-01 | 2018-06-03
75084 | KIAF05495 | KIA705495 | DA 10705495 Alexandria So | 4638.39 |  | 4638.39 |  |  | 4638.39 | 53637.18 | -48998.79 | 2017-01-04 10:04 | 2019-03-01 | 2017-04-01
75084 | KECF20153 | KEC920153 | DC 8920153 Bellevue 42 | 5928.33 |  | 5928.33 |  |  | 8389.54 | 298274.18 | -289884.64 | 2015-10-23 10:05 | 2019-07-31 | 2016-09-01
75084 | SG000586F | SGDLSKY | RUSD DEK D-Line Switch Replacement | 27245.96 |  | 27245.96 |  |  | 27245.96 | 94 | 27151.96 | 2016-12-19 11:23 | 2025-12-31 | 2017-05-01
75084 | SG000441F | SGPOTTKY | DEK D Line Pothead Termination | 44.54 |  | 44.54 |  |  | 44.54 | 83 | -38.46 | 2016-05-16 10:07 | 2025-12-31 | 2017-01-01
75084 | SG000435F | SGCAPATKY | DEK Cap Automation | 301.3 |  | 301.3 |  |  | 301.3 | 83 | 218.3 | 2016-05-16 10:15 | 2025-12-31 | 2017-01-01
75084 | SG000439F | SGGENSWKY | DEK Switchgear Upgrades-Automation | 215.13 |  | 215.13 |  |  | 215.13 | 83 | 132.13 | 2016-05-16 10:22 | 2025-12-31 | 2017-01-01
75084 | TOUTKY | OUT69KY | KY T-line Emergency Repl on 69kV | 31256.84 |  | 31256.84 |  |  | 31256.84 | 6 | 31250.84 | 2017-01-17 10:23 | 2050-12-31 | 2017-01-01
75084 | SG000432F | SGRUCKY | DEK Cable Replacement | 98.5 |  | 98.5 |  |  | 98.5 | 83 | 15.5 | 2016-05-16 10:08 | 2025-12-31 | 2017-01-01
75084 | SGCIAMIF | SGKAMICI | SG Kentucky C&I AMI Meters | 0 |  | 0 |  |  | 395744.77 | 454386.03 | -58641.26 | 2015-05-29 12:53 | 2018-05-15 | 2015-09-01
75084 | KECF20155 | KEC920155 | DEC 8920155 Oakbrook 41 | 7804.25 |  | 7804.25 |  |  | 12723.65 | 18342.29 | -5618.64 | 2015-10-26 18:05 | 2019-08-31 | 2016-09-01
75084 | ICPRJDSTR | ICCONSTRT | Interconnection Capital Project | 4112.88 |  | 4112.88 |  |  | 4112.88 | 1 | 4111.88 | 2017-09-28 12:05 | 2030-09-30 | 2017-10-01
75084 | ICPRJDSTR | ICCONSTRD | Interconnection Capital Project | 4058.73 |  | 4058.73 |  |  | 4058.73 | 1 | 4057.73 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01
75084 | 75084 | EMETERKY | Electric Meter Blanket | 622765 |  | 622765 |  |  | 1389598.33 | 295697.19 | 1093901.14 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01 | 2019-05-14
75084 | SG000442F | SGPILCKY | DEK PILC Reactive | 17801.32 |  | 17801.32 |  |  | 17801.32 | 83 | 17718.32 | 2016-05-16 10:05 | 2025-12-31 | 2017-01-01
75084 | KYTOOLF | TKYTOOL | Transmission Capital Tool Purchases | 194587.8 |  | 194587.8 |  |  | 194587.8 | 100 | 194487.8 | 2017-11-16 13:07 | 2050-12-31 | 2017-11-01
75084 | CP17TBRK | 17TB15 | Constance Repl Bk1 Bush | 7037.58 |  | 7037.58 |  |  | 7037.58 | 20071.78 | -13034.2 | 2017-03-23 14:29 | 2019-03-31 | 2017-10-01
75084 | CP17TBRK | 17TB16 | Dixie Repl Bk2 Bush w/ LTC | 25848.19 |  | 25848.19 |  |  | 25848.19 | 20071.78 | 5776.41 | 2017-03-23 14:33 | 2019-03-31 | 2017-10-01 | 2019-05-06
75084 | CP17TBRK | 17TB17 | Kentucky Univ Repl Bk4 Bush | 5499.23 |  | 5499.23 |  |  | 5499.23 | 15322.35 | -9823.12 | 2017-03-23 14:37 | 2019-03-31 | 2017-10-01 | 2018-07-31
75084 | SG000437F | SGHYDRKY | DEK Recloser Replacements | 22.4 |  | 22.4 |  |  | 1924.8 | 83 | 1841.8 | 2016-05-16 10:20 | 2025-12-31 | 2016-10-01
75084 | DEMERKY | EMR326 | Thom More Ckt Sw Sw's - DEMERKY | 25017.4 |  | 25017.4 |  |  | 25017.4 | 39506 | -14488.6 | 2017-02-09 14:48 | 2018-01-31 | 2017-02-01 | 2018-01-27
75084 | SG000444F | SGRTRKY | DEK Upgrade Livefront Transformers | 22.4 |  | 22.4 |  |  | 1653.27 | 83 | 1570.27 | 2016-05-16 10:12 | 2025-12-31 | 2016-07-01
75084 | SG000443F | SGCBINJKY | DEK Cable Injection | 22.4 |  | 22.4 |  |  | 22.4 | 83 | -60.6 | 2016-05-16 09:52 | 2025-12-31 | 2017-01-01
75084 | DKY2020 | D2020DL1 | AM 20868748 Bellevue 43 Rlbd RUSD | 851.83 |  | 851.83 |  |  | 851.83 | 0 | 851.83 | 2017-03-07 10:12 | 2021-08-28 | 2017-04-01
75084 | KUCF48474 | KUC348474 | UG 10348474 Oakbrook '42' | 649.31 |  | 649.31 |  |  | 649.31 | 0 | 649.31 | 2017-02-15 14:04 | 2020-06-28 | 2017-07-01
75084 | KUCF48388 | KUC348388 | UG 10348388 Richwood 43 | 6929.12 |  | 6929.12 |  |  | 6929.12 | 0 | 6929.12 | 2017-04-11 14:03 | 2019-06-30 | 2017-06-01
75084 | KUCF48450 | KUC348450 | UG 10348450 Crescent 44 | 3344.84 |  | 3344.84 |  |  | 3344.84 | 0 | 3344.84 | 2017-04-11 14:03 | 2019-06-30 | 2017-10-01
75084 | KUCF48397 | KUC348397 | RUC 10348397. Cable repla | 2557.14 |  | 2557.14 |  |  | 2557.14 | 0 | 2557.14 | 2017-06-07 18:04 | 2019-03-01 | 2017-10-01
75084 | DKY1931 | D1931DL2 | AM 10895849 General Dr Part 2 | 17389.58 |  | 17389.58 |  |  | 17389.58 | 0 | 17389.58 | 2016-07-29 14:18 | 2022-11-29 | 2017-05-01
75084 | DKY1931 | D1931DL1 | AM 10894240 General Drive Part 1 | 184114.84 |  | 184114.84 |  |  | 195966.58 | 87223.94 | 108742.64 | 2016-07-29 14:11 | 2018-03-15 | 2016-08-01 | 2017-08-18
75084 | DKY2131 | D2131DL3 | AM 21798304 Hands 45 | 3251.82 |  | 3251.82 |  |  | 3251.82 | 0 | 3251.82 | 2017-07-25 13:52 | 2020-07-16 | 2017-10-01
75084 | DKY2131 | D2131DL1 | AM 21797163 Hands 45 - DKY2131 | 33640.57 |  | 33640.57 |  |  | 33640.57 | 378745.87 | -345105.3 | 2017-07-25 13:41 | 2019-12-14 | 2017-10-01 | 2019-11-24
75084 | TKY2188 | T2188DS1 | Augustine_Instl 22_4MVA XTR - TKY2 | 240665.36 |  | 240665.36 |  |  | 240665.36 | 2593925.42 | -2353260.06 | 2017-07-06 13:26 | 2019-02-15 | 2017-07-01 | 2019-01-27
75084 | SG000434F | SGRTPKY | DEK Upgrade Dist Trans Stations | 5371.61 |  | 5371.61 |  |  | 7454.86 | 0 | 7454.86 | 2016-05-16 10:10 | 2025-12-31 | 2016-11-01
75084 | SGAMIDMS | SGADMS33 | SG Upgrade Alstom DMS to ver 3.3 | 0.12 |  | 0.12 |  |  | 136474.09 | 68579 | 67895.09 | 2014-12-18 | 2016-07-20 | 2014-12-01 | 2016-07-15
75084 | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | 0.07 |  | 0.07 |  |  | 51858.07 | 250000 | -198141.93 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084 | SGETOASF | SGETOAS | SG TOA Replacement Software | 148604.19 |  | 148604.19 |  |  | 266300.01 | 208124 | 58176.01 | 2015-04-06 13:58 | 2020-03-31 | 2015-05-01 | 2019-10-20
75084 | SGETOASF | SGECOA | SG COA Software | 11636.98 |  | 11636.98 |  |  | 27480.82 | 13148 | 14332.82 | 2016-03-31 15:37 | 2017-09-30 | 2016-04-01 | 2017-09-08
75084 | AMKY0942 | M1112 | Dry Ridge TLS | -519.7 |  | -519.7 |  |  | 273467.91 | 122334 | 151133.91 | 2014-05-29 | 2015-09-30 | 2014-06-01 | 2015-08-29
75084 | KHRF51813 | KHR451813 | RI 10451813 5310 Madison | 59510.09 |  | 59510.09 |  |  | 62901.7 | 45244.52 | 17657.18 | 2016-12-05 14:04 | 2017-08-15 | 2016-12-01 | 2018-01-29
75084 | TKY1453 | T1453TS1 | Dixie 69kV ABS - TKY1453 | 322203.64 |  | 322203.64 |  |  | 347400.76 | 475115 | -127714.24 | 2016-10-07 18:03 | 2018-07-31 | 2016-10-01 | 2018-02-02
75084 | TKY1453 | T1453DS1 | Dixie Bus 1 Swgr - TKY1453 | 2038940.52 |  | 2038940.52 |  |  | 2132752.97 | 2686595 | -553842.03 | 2016-10-07 18:03 | 2018-07-31 | 2016-10-01 | 2018-08-03
75084 | TKY1453 | T1453DL1 | Dixie 41-42 UG Exits TKY1453 | 17433.87 |  | 17433.87 |  |  | 17433.87 | 66147.36 | -48713.49 | 2017-07-06 15:45 | 2019-05-04 | 2017-07-01 | 2018-08-03
75084 | TKY1454 | T1454DS1 | Hands Bus 1 Swgr - TKY1454 | 1228597.85 |  | 1228597.85 |  |  | 1324943.21 | 688608 | 636335.21 | 2016-05-12 18:02 | 2018-03-01 | 2016-06-01 | 2018-02-08
75084 | TKY1696 | T1696TS1 | Kenton XTR 4 Rel Repl - TKY1696 | 174213.32 |  | 174213.32 |  |  | 174213.32 | 288284 | -114070.68 | 2016-11-15 14:04 | 2018-03-01 | 2017-01-01 | 2018-02-28
75084 | KILF64406 | KIL564406 | UG 10564406 West End 41 | 100444.95 |  | 100444.95 |  |  | 329228.32 | 462121.21 | -132892.89 | 2016-07-01 18:06 | 2017-05-28 | 2016-08-01 | 2017-04-12
75084 | DKY1932 | D1932DS1 | Bellevue Upg Dist Cir Rel_RUSD - DK | 340544.63 |  | 340544.63 |  |  | 380295.34 | 277439 | 102856.34 | 2016-08-19 09:32 | 2018-01-29 | 2016-09-01 | 2018-02-10
75084 | KHRF53148 | KHR653148 | DOT 20653148 Ky 236 Mt Zion | 863207.75 |  | 863207.75 |  |  | 863207.75 | 265402.16 | 597805.59 | 2017-02-13 14:04 | 2018-03-31 | 2017-03-01 | 2018-05-03
75084 | TKY1611 | T1611DS1 | Augustine Swgr Repl - TKY1611 | 301854.77 |  | 301854.77 |  |  | 301854.77 | 1219379 | -917524.23 | 2017-03-23 18:02 | 2019-04-30 | 2017-03-01 | 2019-06-04
75084 | DKY1929 | D1929RS1 | RUSD Taylor Mill Purch Sub Property | 59922.43 |  | 59922.43 |  |  | 60017.06 | 282613 | -222595.94 | 2016-08-17 13:44 | 2019-04-04 | 2016-11-01 | 2019-03-18
75084 | DKY2018 | D2018DS1 | Dixie BK 4 - DKY2018 - DKY2018 | 154700.08 |  | 154700.08 |  |  | 154700.08 | 3407443 | -3252742.92 | 2017-06-07 07:50 | 2019-04-23 | 2017-08-01 | 2019-05-01
75084 | DKY2018 | D2018TL1 | Dixie 6764 Line Relo TL - DKY2018 | 1350.85 |  | 1350.85 |  |  | 1350.85 | 135025 | -133674.15 | 2017-06-07 08:15 | 2019-03-01 | 2017-11-01 | 2019-02-21
75084 | DKY2018 | D2018TS1 | Dixie 69kV Loop - DKY2018 | 51346.6 |  | 51346.6 |  |  | 51346.6 | 1145705 | -1094358.4 | 2017-06-07 07:42 | 2019-04-23 | 2017-07-01 | 2019-05-01
75084 | DKY2151 | D2151DL1 | AM 20710413 Crittenden Gen Intrc | 121144.19 |  | 121144.19 |  |  | 121144.19 | 75335.28 | 45808.91 | 2017-02-14 10:22 | 2018-07-31 | 2017-03-01 | 2018-03-15
75084 | DKY2151 | D2151DS1 | Crittenden PTs_chk VR DKY2151 (Pare | 30875.48 |  | 30875.48 |  |  | 30875.48 | 79115 | -48239.52 | 2017-07-20 13:56 | 2018-03-18 | 2017-07-01 | 2018-02-15
75084 | DKY1912 | D1912DL1 | RUSD Covington 43-44 UG - DKY1912 | 133829.2 |  | 133829.2 |  |  | 133829.2 | 99277.72 | 34551.48 | 2017-02-15 15:40 | 2018-03-31 | 2017-03-01 | 2018-03-22
75084 | DKY1912 | D1912DS1 | Covington Xtr 2_RUSD - DKY1912 | 2604941.1 |  | 2604941.1 |  |  | 2660969.64 | 2776527.3 | -115557.66 | 2016-08-19 09:12 | 2018-08-31 | 2016-09-01 | 2018-08-19
75084 | DKY1912 | D1912DL2 | RUSD Covington 44 OH - DKY1912 | 30267.47 |  | 30267.47 |  |  | 30267.47 | 20798.27 | 9469.2 | 2017-02-15 16:06 | 2018-03-31 | 2017-04-01 | 2017-09-16
75084 | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 72597.96 |  | 72597.96 |  |  | 847668.23 | 823726 | 23942.23 | 2014-02-18 | 2019-02-16 | 2014-03-01 | 2019-04-09
75084 | KIAF03715 | KIA703715 | DA 10703715 Constance 42 | 78282.17 |  | 78282.17 |  |  | 78282.17 | 64102.57 | 14179.6 | 2017-01-04 10:04 | 2018-03-31 | 2017-02-01 | 2018-02-02
75084 | DKY2150 | D2150DL1 | AM 20709498 Verona 42 Rbld | 312439.1 |  | 312439.1 |  |  | 312439.1 | 129954.31 | 182484.79 | 2017-02-14 10:11 | 2018-03-31 | 2017-02-01 | 2018-02-16
75084 | DKY2150 | D2150DS1 | Verona 42 PTs chk VR | 38210.51 |  | 38210.51 |  |  | 38210.51 | 79115 | -40904.49 | 2017-07-20 13:31 | 2018-03-31 | 2017-07-01 | 2018-03-01
75084 | DKY2150 | D2150DL2 | AM 20710216 Walton 1 Intercon | 56850.17 |  | 56850.17 |  |  | 56850.17 | 31697.43 | 25152.74 | 2017-02-14 10:16 | 2018-07-31 | 2017-10-01 | 2018-03-22
75084 | MWAVEKYEL | NINT2156B | Cisco Data Network | 8848.68 |  | 8848.68 |  |  | 8848.68 | 10183 | -1334.32 | 2017-02-20 07:17 | 2018-03-31 | 2017-07-01 | 2018-03-06
75084 | MWAVEKYEL | 336593AUG | Install CISCO Switches | 1190.97 |  | 1190.97 |  |  | 1190.97 | 33237 | -32046.03 | 2017-07-07 14:25 | 2017-11-30 | 2017-12-01 | 2017-11-30
75084 | SG000754F | SGITRONL2 | SG DEE Cisco NMS Licenses | 52005.08 |  | 52005.08 |  |  | 52005.08 | 60000 | -7994.92 | 2017-07-27 10:21 | 2017-11-01 | 2017-09-01 | 2018-02-01
75084 | TKY2009 | T2009DS1 | Kenton TB3 Rpl - TKY2009 | 77937.21 |  | 77937.21 |  |  | 77937.21 | 1962535 | -1884597.79 | 2017-04-27 14:03 | 2019-04-20 | 2017-06-01 | 2019-04-09
75084 | SG000726F | SG726SVRS | SG DEE AMI BlueCat Scale - 726 | 332.2 |  | 332.2 |  |  | 332.2 | 2783 | -2450.8 | 2017-06-29 15:36 | 2018-03-28 | 2017-07-01 | 2018-05-23
75084 | SG000726F | SG726SW | SG DEE AMI BlueCat Scale - 726 | 9170.36 |  | 9170.36 |  |  | 9170.36 | 9025 | 145.36 | 2017-06-29 15:27 | 2018-02-28 | 2017-07-01 | 2017-12-06
75084 | KHRF51720 | KHR851720 | RI 11851720 Rice Pike | 206487.69 |  | 206487.69 |  |  | 206487.69 | 75014.92 | 131472.77 | 2017-04-13 14:02 | 2018-05-01 | 2017-04-01 | 2018-07-04
75084 | TEMERKY | EMR448 | Hebron Repl CB311 Cir 43 Relay | 3454.71 |  | 3454.71 |  |  | 3454.71 | 5974.56 | -2519.85 | 2017-06-16 15:17 | 2018-03-31 | 2017-06-01 | 2017-11-03
75084 | DKY2217 | D2217RS1 | Petersburg Sub Site - DKY2217 | 29358.03 |  | 29358.03 |  |  | 29358.03 | 382562 | -353203.97 | 2017-05-18 18:02 | 2019-10-27 | 2017-07-01 | 2019-10-08
75084 | AMKY0941 | L9104 | Grant Install TLS | -519.57 |  | -519.57 |  |  | 712247.61 | 230617 | 481630.61 | 2014-05-21 | 2016-03-31 | 2014-06-01 | 2016-01-23
75084 | KTMF28273 | KTM628273 | SL 7628273 St Rt 18 | 12266.88 |  | 12266.88 |  |  | 56411.04 | 57641.31 | -1230.27 | 2015-10-09 18:05 | 2016-04-20 | 2015-11-01 | 2016-03-29
75084 | TKY1447 | T1447DS1 | Cold Spring Ckt Swi | 93571.13 |  | 93571.13 |  |  | 368139.33 | 206535 | 161604.33 | 2016-02-12 10:59 | 2017-03-31 | 2016-02-01 | 2017-03-29
75084 | KHRF55669 | KHR355669 | RI 10355669 Washington St | 345237.77 |  | 345237.77 |  |  | 195245.39 | 101560.5 | 93684.89 | 2016-07-22 18:06 | 2017-07-28 | 2016-08-01 | 2017-06-20
75084 | TKY1519 | T1519DS1 | Thomas More XTR 1 Rel Rpl | 0 |  | 0 |  |  | 219235.61 | 86863 | 132372.61 | 2016-02-24 18:03 | 2017-03-31 | 2016-03-01 | 2017-01-21
75084 | KUCF34911 | KUC234911 | UG 6234911 Hands 44 URD | 113725.94 |  | 113725.94 |  |  | 723278.31 | 349210.8 | 374067.51 | 2015-11-23 14:07 | 2017-07-15 | 2016-01-01 | 2017-04-26
75084 | KHRF97697 | KHR297697 | DOT 7297697 Covington 43 | 29958.74 |  | 29958.74 |  |  | 60929.47 | 39491.86 | 21437.61 | 2016-07-07 18:05 | 2018-01-01 | 2016-07-01 | 2017-10-10
75084 | KHRF82804 | KHR082804 | RI 10082804 15 Spiral Dr | 44582.6 |  | 44582.6 |  |  | -15684.24 | 59622.55 | -75306.79 | 2016-08-23 14:03 | 2017-08-28 | 2016-10-01 | 2018-01-04
75084 | KUCF61112 | KUC261112 | UG 10261112 Constance 42 | 470956.6 |  | 470956.6 |  |  | 470956.6 | 360637.32 | 110319.28 | 2017-01-10 14:04 | 2019-03-19 | 2017-03-01 | 2018-08-10
75084 | KIPF08146 | KIP708146 | NB 20708146 Beaver 41 Reb | 303750.34 |  | 303750.34 |  |  | 303750.34 | 200686.44 | 103063.9 | 2017-02-16 10:04 | 2018-01-31 | 2017-03-01 | 2017-12-06
75084 | TKY1876 | T1876DS1 | Dayton XTR 1 Rel Rpl - TKY1876 | 68470.54 |  | 68470.54 |  |  | 68470.54 | 175818 | -107347.46 | 2016-11-15 14:02 | 2018-07-31 | 2017-01-01 | 2018-06-21
75084 | KIAF03714 | KIA703714 | DA 10703714 Long Branch 4 | 44913.21 |  | 44913.21 |  |  | 44913.21 | 56580.26 | -11667.05 | 2016-10-03 18:05 | 2019-03-01 | 2017-12-01 | 2018-10-26
75084 | TKY1727 | T1727DS1 | Wilder XTR 4 Rel Repl - TKY1727 | 140540.99 |  | 140540.99 |  |  | 140540.99 | 237658 | -97117.01 | 2016-11-15 14:02 | 2018-03-01 | 2017-02-01 | 2018-03-31
75084 | KETF35854 | KET135854 | DET 10135854 Villa 43 348 | 172910.54 |  | 172910.54 |  |  | 173768.67 | 350417.94 | -176649.27 | 2016-11-04 18:06 | 2019-06-30 | 2016-12-01 | 2019-03-12
75084 | TKY1913 | T1913DS1 | Oakbrook XTR 1 Rel Rpl - TKY1913 | 70836.61 |  | 70836.61 |  |  | 70836.61 | 350616 | -279779.39 | 2017-04-10 14:03 | 2019-03-01 | 2017-04-01 | 2018-07-13
75084 | KETF35851 | KET135851 | DET 10135851 West End 41 | 54135.76 |  | 54135.76 |  |  | 62011.3 | 414893.11 | -352881.81 | 2016-05-02 14:04 | 2019-06-14 | 2016-05-01 | 2019-05-25
75084 | KUCF48463 | KUC348463 | UG 10348463 Decoursey 41 | 1044.55 |  | 1044.55 |  |  | 1044.55 | 199651.38 | -198606.83 | 2017-02-15 14:04 | 2019-03-01 | 2017-07-01 | 2019-03-31
75084 | TKY1518 | T1518DS1 | Mt Zion XTR 1 Rel Repl | 13066.27 |  | 13066.27 |  |  | 225716.93 | 115410 | 110306.93 | 2015-11-18 18:02 | 2017-03-31 | 2016-03-01 | 2017-03-16
75084 | KUCF47633 | KUC447633 | UG 20447633 Constance 42 | 1071791.26 |  | 1071791.26 |  |  | 1071791.26 | 328397.17 | 743394.09 | 2017-02-22 14:02 | 2018-04-30 | 2017-03-01 | 2018-07-17
75084 | DKY1973 | D1973DL1 | AM 11028173 York 43 Ln Ext | 234163.18 |  | 234163.18 |  |  | 236993.36 | 83908.12 | 153085.24 | 2016-08-17 08:12 | 2017-10-31 | 2016-08-01 | 2017-09-14
75084 | KOCF56175 | KOC556175 | DET 11556175 Kenton 44 Re | 621194.5 |  | 621194.5 |  |  | 621194.5 | 283200.78 | 337993.72 | 2017-01-10 18:05 | 2018-03-31 | 2017-03-01 | 2018-05-05
75084 | KUCF48481 | KUC348481 | UG 10348481 Crescent 41 | 12820.71 |  | 12820.71 |  |  | 12820.71 | 16692.2 | -3871.49 | 2017-02-20 18:06 | 2019-04-01 | 2017-07-01 | 2017-09-21
75084 | SG000598F | SG598CDEQ | SG DEE Secure Network Infrastructur | 111407.02 |  | 111407.02 |  |  | 111407.02 | 85620 | 25787.02 | 2017-09-12 16:44 | 2019-04-30 | 2017-09-01 | 2019-04-30
75084 | TKY1914 | T1914DS1 | Longbranch Rel Rpl XTR 1 - TKY1914 | 1853.64 |  | 1853.64 |  |  | 1853.64 | 247959 | -246105.36 | 2017-04-26 15:56 | 2019-06-29 | 2017-11-01 | 2019-01-22
75084 | KIPF03154 | KIP703154 | NB 10703154 9001 US 42 Un | 58372.54 |  | 58372.54 |  |  | 58372.54 | 57736.31 | 636.23 | 2016-08-09 18:04 | 2018-02-22 | 2017-03-01 | 2017-10-12
75084 | SG000752F | SG752SVR | DEE DOTS Grid Sim Strat Development | 2370.62 |  | 2370.62 |  |  | 2370.62 | 20643 | -18272.38 | 2017-08-08 15:31 | 2018-04-30 | 2017-09-01 | 2018-04-30
75084 | KSPF41656 | KSP941656 | NB 10941656 North Walton Pointe | 15699.64 |  | 15699.64 |  |  | 39998.48 | 51023.08 | -11024.6 | 2016-08-16 14:04 | 2017-06-10 | 2016-08-01 | 2017-05-21
75084 | KTMF88913 | KTM988913 | INSTALL 22 LIGHTS FOR IDI | 104473.52 |  | 104473.52 |  |  | 104473.52 | 60720.99 | 43752.53 | 2017-04-19 18:04 | 2018-03-31 | 2017-07-01 | 2017-12-28
75084 | KHRF81342 | KHR181342 | DOT 7181342 Empire 41 Rel | 742086.32 |  | 742086.32 |  |  | 742086.32 | 246600.03 | 495486.29 | 2017-01-18 14:05 | 2017-12-01 | 2017-02-01 | 2018-03-19
75084 | CP17LTCRK | 17LTCR03 | KY Univ Repl TB4 Load Tap Changer | 34834.54 |  | 34834.54 |  |  | 34834.54 | 52076.25 | -17241.71 | 2017-07-20 06:50 | 2019-03-31 | 2017-10-01 | 2018-07-31
75084 | KIPF44149 | KIP344149 | NB 21344149 RIVIERA DR - | 8922.02 |  | 8922.02 |  |  | 8922.02 | 14117.06 | -5195.04 | 2017-07-26 14:04 | 2017-12-01 | 2017-07-01 | 2017-12-27
75084 | KIPF89003 | KIP189003 | NB 11189003 Duveneck Squa | 58651.97 |  | 58651.97 |  |  | 58651.97 | 65005.6 | -6353.63 | 2017-02-23 18:03 | 2018-05-31 | 2017-10-01 | 2018-01-11
75085 | CUSTCONN | 315986A | Customer Connect - Core | 362974.1 |  | 362974.1 |  |  | 362974.1 | 3313201.21 | -2950227.11 | 2017-08-10 10:40 | 2022-06-30 | 2017-08-01
75085 | CUSTCONN | 315986B | Customer Connect- Analytics | 44553.54 |  | 44553.54 |  |  | 44553.54 | 99396.72 | -54843.18 | 2017-08-10 13:07 | 2018-09-30 | 2017-08-01 | 2018-09-30
75085 | CUSTCONN | 315986C | Customer Connect- CRM | 48390.46 |  | 48390.46 |  |  | 48390.46 | 267635.67 | -219245.21 | 2017-08-10 14:25 | 2019-05-28 | 2017-08-01 | 2019-06-18
75085 | CUSTCONN | 315986D | Customer Connect- Prepaid Advantage | 103952.41 |  | 103952.41 |  |  | 103952.41 | 399313.16 | -295360.75 | 2017-08-10 15:24 | 2019-12-30 | 2017-08-01
75085 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 74955.57 |  | 74955.57 |  |  | 74955.57 | 166907.14 | -91951.57 | 2017-08-11 10:38 | 2020-06-30 | 2017-08-01
75085 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 90193.12 |  | 90193.12 |  |  | 90193.12 | 62909 | 27284.12 | 2017-09-05 18:39 | 2018-10-01 | 2017-09-01 | 2018-10-01
75085 | CUSTCONN | 315986QC | CIS-Quality Center Licenses | 3542.57 |  | 3542.57 |  |  | 3542.57 | 3520 | 22.57 | 2017-08-01 16:32 | 2017-12-31 | 2017-07-01 | 2017-10-31
75085 | FPIT | 307482 | Customer Mobile App | 14945.22 |  | 14945.22 |  |  | 14945.22 | 28598 | -13652.78 | 2017-05-08 15:19 | 2019-06-25 | 2017-05-01 | 2019-06-25
75085 | FPIT | 325480C | Watson Explorer (Omnifind Replace) | 15583.86 |  | 15583.86 |  |  | 15583.86 | 18496.93 | -2913.07 | 2016-11-29 12:47 | 2018-05-31 | 2016-12-01 | 2018-09-08
75085 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 1394515.44 |  | 1394515.44 |  |  | 2231426.19 | 1159204 | 1072222.19 | 2016-02-11 12:16 | 2018-10-31 | 2016-03-01 | 2018-10-31
75085 | FPIT | PCTA481AS | Sitecore | 13221.8 |  | 13221.8 |  |  | 1201847.3 | 520043.89 | 681803.41 | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75085 | FPIT | 315263BTS | 315263BTS Encryption PH2 | 1040.82 |  | 1040.82 |  |  | 6200.06 | 19818 | -13617.94 | 2016-10-13 15:34 | 2016-12-31 | 2016-10-01 | 2017-03-31
75085 | FPIT | 315263GDG | 315263GDG Encryption PH2 | 49.49 |  | 49.49 |  |  | 6144.29 | 5086 | 1058.29 | 2016-10-13 12:47 | 2016-12-31 | 2016-11-01 | 2017-03-31
75085 | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 231.66 |  | 231.66 |  |  | 18366.81 | 18000 | 366.81 | 2015-11-16 14:15 | 2016-09-30 | 2015-12-01 | 2017-03-27
75085 | FPIT | 315263VER | 315263VER Encryption PH2 | -0.37 |  | -0.37 |  |  | 4519.77 | 9967 | -5447.23 | 2016-10-13 16:18 | 2016-12-31 | 2016-12-01 | 2017-03-31
75085 | FPIT | 311803CH | Lighting System Integration HW | 58.25 |  | 58.25 |  |  | 127.87 | 3243.47 | -3115.6 | 2015-09-18 10:13 | 2019-03-31 | 2016-01-01 | 2018-06-17
75085 | FPIT | 344368 | Customer Transformer Mapping Engine | 141.27 |  | 141.27 |  |  | 141.27 | 22936.91 | -22795.64 | 2017-10-23 13:29 | 2020-03-31 | 2017-11-01
75085 | FPIT | 342284C | Outage Detection Platform | 4740.95 |  | 4740.95 |  |  | 4740.95 | 9664.27 | -4923.32 | 2017-09-06 16:54 | 2020-03-31 | 2017-09-01
75085 | FPIT | 311803CS | Lighting System Integration Softwar | 84883.18 |  | 84883.18 |  |  | 128346.99 | 157966.53 | -29619.54 | 2015-09-14 13:59 | 2019-03-31 | 2015-11-01 | 2019-02-28
75085 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | -975.64 |  | -975.64 |  |  | 231967.39 | 162502.14 | 69465.25 | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75085 | AMIKY | C9045 | AMI Donaldson Advanced Meter | -3598.4 |  | -3598.4 |  |  | -7.276e-12 | 151468 | -151468 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085 | AMIKY | C9052 | AMI Buffington Advanced Meter | -7071.39 |  | -7071.39 |  |  | 3.638e-12 | 191879 | -191879 | 2007-01-07 | 2008-03-15 | 2007-02-01 | 2008-06-30
75085 | AMIKY | C9048 | AMI Claryville Advanced Meter | -3929.45 |  | -3929.45 |  |  | -2.6716e-12 | 158349 | -158349 | 2007-01-07 | 2009-08-31 | 2007-07-01 | 2009-08-31
75085 | AMIKY | C9051 | AMI Dixie Advanced Meter | -3414.48 |  | -3414.48 |  |  | 5.5991e-12 | 154744 | -154744 | 2007-01-07 | 2008-03-15 | 2007-07-01 | 2008-01-31
75085 | AMIKY | C9044 | AMI Wilder Advanced Meter | -2479.33 |  | -2479.33 |  |  | -6.5938e-12 | 200835 | -200835 | 2007-01-07 | 2008-03-15 | 2007-01-01 | 2007-11-30
75085 | AMIKY | C9049 | AMI Florence Advanced Meter | -4792.32 |  | -4792.32 |  |  | -7.276e-12 | 189695 | -189695 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75085 | AMIKY | C9050 | AMI Villa Advanced Meter | -3534.75 |  | -3534.75 |  |  | 0 | 150703 | -150703 | 2007-01-07 | 2008-03-15 | 2007-05-01 | 2007-11-30
75080 | FPIT | R6095 | Logistics Cycle Times | 48668 |  | 48668 |  |  | 64210.37 | 36719.92 | 27490.45 | 2016-01-21 13:27 | 2017-12-15 | 2016-02-01 | 2018-02-02
75080 | FPIT | 323326DEK | 2017 Workstation Refresh | 54486.71 |  | 54486.71 |  |  | 54486.71 | 43049 | 11437.71 | 2017-06-02 14:52 | 2018-03-29 | 2017-06-01 | 2018-03-29
75080 | FPIT | R5327 | Plantview Observation Program Mobil | -110.53 |  | -110.53 |  |  | 8836.11 | 5051.44 | 3784.67 | 2015-12-17 08:56 | 2017-02-18 | 2016-02-01 | 2017-02-18
75080 | FPIT | 336593EOC | Install CISCO Switches & Rtrs | 47765.57 |  | 47765.57 |  |  | 47765.57 | 88500 | -40734.43 | 2017-07-07 14:43 | 2018-06-30 | 2017-07-01 | 2018-05-31
75080 | FPIT | 323482KY | Replace EPM Tool 2017 | 8575.85 |  | 8575.85 |  |  | 8575.85 | 11076.27 | -2500.42 | 2017-02-10 14:00 | 2018-04-12 | 2017-02-01 | 2018-05-31
75080 | FPIT | NINT1105K | Implement Rates and Regulatory Stra | 229418.44 |  | 229418.44 |  |  | 229418.44 | 234263 | -4844.56 | 2017-08-15 14:48 | 2020-01-31 | 2017-08-01
75080 | FPIT | R9205 | Trading Information Management Cons | 5690.14 |  | 5690.14 |  |  | 5905.44 | 56252.04 | -50346.6 | 2016-03-28 15:16 | 2017-06-30 | 2016-05-01 | 2018-03-12
75080 | FPIT | RF17Q4DEK | 2017 Workstation Hardware | 1345.47 |  | 1345.47 |  |  | 1345.47 | 1504 | -158.53 | 2017-11-22 11:09 | 2018-03-31 | 2017-12-01 | 2018-03-31
75080 | FPIT | S6621 | Plantview Reliability Index Module | 3664.22 |  | 3664.22 |  |  | 5776.17 | 7144.63 | -1368.46 | 2016-05-17 13:49 | 2017-07-31 | 2016-05-01 | 2017-11-17
75080 | FPIT | 323174Q4I | Q4 2017 End of Life Server | 8890.39 |  | 8890.39 |  |  | 8890.39 | 8685 | 205.39 | 2017-10-16 14:30 | 2018-03-31 | 2017-12-01 | 2018-03-31
75080 | RESBLDKY | KMW160131 | Modular Office Space | 152163.02 |  | 152163.02 |  |  | 207621.78 | 219071 | -11449.22 | 2016-07-21 13:54 | 2017-07-02 | 2016-08-01 | 2017-07-03
75080 | RESBLDKY | KMW170046 | Design for replacement of windows | 2068253.02 |  | 2068253.02 |  |  | 2068253.02 | 3324206 | -1255952.98 | 2017-04-05 11:17 | 2018-07-20 | 2017-04-01 | 2018-07-20
75080 | RESBLDKY | KMW160127 | Design of Office Space | 338924.97 |  | 338924.97 |  |  | 480042.47 | 485870 | -5827.53 | 2016-07-13 10:28 | 2017-07-02 | 2016-07-01 | 2017-07-07
75080 | RESBLDKY | KMW170198 | Vestibule addition | 63969.78 |  | 63969.78 |  |  | 63969.78 | 82069 | -18099.22 | 2017-09-05 16:36 | 2018-03-31 | 2017-09-01 | 2018-03-28
75080 | RESBLDKY | KMW170248 | Ice Machine Replacement | 25582.85 |  | 25582.85 |  |  | 25582.85 | 30588 | -5005.15 | 2017-10-19 11:23 | 2018-03-31 | 2017-11-01 | 2018-03-28
75080 | FMWAVEKY | 307282AAA | 307282 - 19th&Augustine BndWth Proj | 67926.06 |  | 67926.06 |  |  | 77227 | 152096 | -74869 | 2016-10-19 08:11 | 2017-06-30 | 2016-11-01 | 2017-08-04
75080 | FMWAVEKY | 315218GLC | 315218 Markland Dam Mod. Glenco | 51096.66 |  | 51096.66 |  |  | 51180.79 | 87365.45 | -36184.66 | 2016-11-03 10:59 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | 315218VRR | 315218 - Markland Dam Mod. Verona | 58808.7 |  | 58808.7 |  |  | 59073.38 | 106349.71 | -47276.33 | 2016-11-02 16:24 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | 315218SPR | 315218 - Markland Dam Mod. Sparta | 139235.39 |  | 139235.39 |  |  | 139319.27 | 113451.43 | 25867.84 | 2016-11-03 10:37 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | 315218VR2 | 315218 - Markland Dam Mod. Verona2 | 36814.02 |  | 36814.02 |  |  | 36898.15 | 87728 | -50829.85 | 2016-11-03 11:49 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | NINT732B | Butler Microwave pre-fab building | 10200.77 |  | 10200.77 |  |  | 10200.77 | 113900 | -103699.23 | 2017-02-03 15:17 | 2018-11-30 | 2017-03-01 | 2018-11-11
75080 | MWAVEELEC | 307282AAB | 307282 - Augustine BndWth @ Sub. | 647.47 |  | 647.47 |  |  | 1931.99 | 21606 | -19674.01 | 2016-10-19 09:37 | 2017-06-30 | 2016-11-01 | 2017-08-04
75080 | CAPBUDK | ETSFHCAPK | CAPITAL BUDGET PROJECT KENT | 0 |  | 0 |  |  | 1.7053e-13 | 0 | 1.7053e-13 | 2008-07-01 | 2050-12-31 | 2008-07-01
75080 | CAPBUDK | ETSPDCAPK | ETS Power Delivery Cap Overhead | -2606.47 |  | -2606.47 |  |  | 1.063e-11 | 0 | 1.063e-11 | 2008-07-07 | 2050-12-31 | 2008-07-01
75080 | KYPYACCR | E1214 | Kentucky Quarterly Payroll Accrual | 35000 |  | 35000 |  |  | 137000 | 0 | 137000 | 2008-09-19 | 2050-12-31 | 2008-09-01
75080 | MWTELBLKT | VERONAMW | Verona Microwave Blanket | 0 |  | 0 |  |  | 8177.05 | 50000 | -41822.95 | 2012-07-26 | 2017-12-31 | 2012-07-01
75080 | MWTELBLKT | WNKRBLKT | WNKR Tower Blanket | 25000 |  | 25000 |  |  | 26483.22 | 50000 | -23516.78 | 2012-09-05 | 2025-12-31 | 2012-09-01
75080 | FLKY0249G | DUKETCKYE | Fleet On-Road Vehicles - Elec-KY | 341313.67 |  | 341313.67 |  |  | 341313.67 | 40000 | 301313.67 | 2017-01-19 14:28 | 2050-12-31 | 2017-03-01
75081 | EB021383 | EB021383X | Unit Control Simulator | 178.6 |  | 178.6 |  |  | 1970982.36 | 1656726 | 314256.36 | 2012-12-27 | 2016-12-21 | 2012-12-01 | 2017-03-15
75081 | EBS01266 | EBS01266X | Repl Lime Conv Metal Detector | -796.68 |  | -796.68 |  |  | 47184.22 | 87248 | -40063.78 | 2013-08-01 | 2015-12-31 | 2013-09-01 | 2015-08-13
75081 | EBS01296 | EBS01296X | Demin Acid Tank | 416.01 |  | 416.01 |  |  | 1066127.16 | 348320.7 | 717806.46 | 2015-10-19 11:48 | 2016-09-30 | 2015-11-01 | 2016-10-08
75081 | PCTAIT218 | AIT21808H | FSO Forecasting Consolidation | -0.39 |  | -0.39 |  |  | -13.43 | 1518.46 | -1531.89 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081 | EB021308 | EB021308X | 2-3 Pulv Roll Wheel Repl | 3718.98 |  | 3718.98 |  |  | 718695.77 | 780026.82 | -61331.05 | 2015-09-02 14:06 | 2016-06-01 | 2015-12-01 | 2016-08-07
75081 | EB020543 | EB020543X | Replace 2A.2 TUF Pump | 227.76 |  | 227.76 |  |  | 51791.88 | 56400.98 | -4609.1 | 2017-01-03 12:01 | 2016-12-31 | 2016-12-01 | 2017-04-04
75081 | EB020603 | EB020603X | Replace Harbor/Deadman Cable | 2922.22 |  | 2922.22 |  |  | 173219.64 | 135135.48 | 38084.16 | 2016-11-14 10:11 | 2017-03-31 | 2016-11-01 | 2017-03-30
75081 | OPTIM | COPTIM | Develop OPTIM Modeling Tool | 15049.64 |  | 15049.64 |  |  | 83381.14 | 73831.97 | 9549.17 | 2016-01-15 13:13 | 2017-09-30 | 2016-01-01 | 2017-09-16
75081 | EB020614 | EB020614X | D Conveyor Hood/Enclosure Repl | 73229.52 |  | 73229.52 |  |  | 73229.52 | 87536.59 | -14307.07 | 2017-01-17 13:04 | 2017-08-15 | 2017-01-01 | 2017-07-13
75081 | EB020623 | EB020623X | E Conveyor Belt Replacement | 106703.66 |  | 106703.66 |  |  | 106703.66 | 87236.02 | 19467.64 | 2017-03-13 10:24 | 2017-06-30 | 2017-03-01 | 2017-06-15
75081 | EB020135 | EB020135X | Install Emergency Warning System | 307387.75 |  | 307387.75 |  |  | 1139898 | 895918.08 | 243979.92 | 2016-09-02 09:29 | 2017-04-30 | 2016-09-01 | 2017-05-23
75081 | EB020361 | EB020361X | Replace A&B conveyor Chute (CD) | 310403.9 |  | 310403.9 |  |  | 310403.9 | 272417.64 | 37986.26 | 2017-02-20 13:39 | 2017-08-15 | 2017-02-01 | 2017-08-11
75081 | EB020622 | EB020622X | F1 1 & F1 2 Crusher Inlet Chute(CD) | 70688.26 |  | 70688.26 |  |  | 70688.26 | 96443.93 | -25755.67 | 2017-02-20 13:50 | 2017-08-15 | 2017-02-01 | 2017-08-11
75081 | EB020269 | EB020269X | Mixer Discharge Belt Replacement | 41229.85 |  | 41229.85 |  |  | 41229.85 | 28700.2 | 12529.65 | 2017-08-16 09:25 | 2017-09-02 | 2017-08-01 | 2017-11-15
75081 | EB020761 | EB020761X | Gen A Phase Bushing Replacement | 386405.76 |  | 386405.76 |  |  | 386405.76 | 351370.01 | 35035.75 | 2017-09-01 14:01 | 2017-10-31 | 2017-08-01 | 2017-10-08
75081 | EB021316 | EB021316X | 2-2 Pulv Roll Wheel repl | 189574.03 |  | 189574.03 |  |  | 189574.03 | 716013.49 | -526439.46 | 2017-10-06 13:37 | 2018-08-27 | 2017-10-01 | 2018-09-10
75081 | EB021456 | EB021456X | SmartGen Installation at East Bend | 1209785.72 |  | 1209785.72 |  |  | 4263038.55 | 4503175.79 | -240137.24 | 2015-01-09 | 2017-12-31 | 2015-01-01 | 2018-03-15
75081 | EB021271 | EB021271X | Replace F to G Coal Chute | 68350.99 |  | 68350.99 |  |  | 1173106.92 | 792558.1 | 380548.82 | 2015-08-28 10:35 | 2016-07-01 | 2015-09-01 | 2016-08-07
75081 | EB021489 | EB021489X | 2-2 Fly Ash Silo to Silo Blowers | -62.71 |  | -62.71 |  |  | 1306982.63 | 1072612 | 234370.63 | 2014-12-08 | 2016-08-31 | 2014-12-01 | 2016-09-23
75081 | EB020078 | EB020078X | Replace Data Network Equipment | -4260.58 |  | -4260.58 |  |  | 182750.29 | 197450.98 | -14700.69 | 2016-05-02 10:48 | 2016-12-15 | 2016-05-01 | 2016-11-27
75081 | EB020074 | EB020074X | Replace Stack Elevator | 87557.17 |  | 87557.17 |  |  | 228798.99 | 181669.72 | 47129.27 | 2016-12-09 09:30 | 2017-03-30 | 2016-12-01 | 2017-05-16
75081 | EB020380 | EB020380X | Replace 4th Floor HVAC Chillers | 1593110.84 |  | 1593110.84 |  |  | 1593110.84 | 1720186.3 | -127075.46 | 2017-01-24 07:51 | 2018-02-23 | 2017-01-01 | 2018-04-19
75081 | EB020433 | EB020433X | HCAD Repl C Conveyor to Surge Bin | 256130.56 |  | 256130.56 |  |  | 256130.56 | 1346868.67 | -1090738.11 | 2017-08-16 10:05 | 2018-08-01 | 2017-09-01 | 2018-08-12
75081 | EB021454 | EB021454X | HP Turbine Nozzle Block & Seals | 1123742.73 |  | 1123742.73 |  |  | 1123742.73 | 4869726.75 | -3745984.02 | 2017-01-24 08:33 | 2018-11-30 | 2017-02-01 | 2018-09-29
75081 | EB020320 | EB020320X | Replace SAH Collar Seals | 382324.29 |  | 382324.29 |  |  | 382324.29 | 1538836.64 | -1156512.35 | 2017-08-08 15:16 | 2018-12-31 | 2017-10-01 | 2018-09-29
75081 | EB020406 | EB020406X | CT Drift Elim Replmnt - Phase 2 | 267216.06 |  | 267216.06 |  |  | 267216.06 | 1311345.76 | -1044129.7 | 2017-11-28 10:50 | 2018-09-01 | 2017-12-01 | 2018-08-14
75081 | EBS01312 | REBS01312 | Remove Bypass Ducts | -90267.94 |  | -90267.94 |  |  | -6.9349e-12 | 26286 | -26286 | 2008-03-12 | 2009-06-30 | 2008-03-01 | 2008-07-26
75081 | EB020430 | EB020430X | Replace 2-1 Vacuum Pump Cooler | 42070.13 |  | 42070.13 |  |  | 42070.13 | 36681.41 | 5388.72 | 2017-01-24 14:31 | 2017-09-30 | 2017-03-01 | 2017-08-11
75081 | EB020624 | EB020624X | SSH Intermediate Pendant Rplc | 553343.09 |  | 553343.09 |  |  | 553343.09 | 3824632.83 | -3271289.74 | 2017-05-15 15:44 | 2018-09-01 | 2017-05-01 | 2018-09-29
75081 | EB020755 | EB020755X | 2-8 CT Motor & Gearbox Replacement | 239850.88 |  | 239850.88 |  |  | 239850.88 | 241534.35 | -1683.47 | 2017-06-28 09:50 | 2017-10-31 | 2017-06-01 | 2017-07-26
75081 | EB020382 | EB020382X | Circ Water Lining | 102287.55 |  | 102287.55 |  |  | 102287.55 | 1383331.55 | -1281044 | 2017-10-18 09:50 | 2018-08-27 | 2017-12-01 | 2018-08-14
75081 | EB020764 | EB020764X | LBU Rip Rap Placement | 12633.7 |  | 12633.7 |  |  | 12633.7 | 31452.78 | -18819.08 | 2017-08-16 10:53 | 2017-11-07 | 2017-09-01 | 2017-11-16
75081 | EB020305 | EB020305X | 2-1 WSP Vacuum Pump Repl (SM) | 38222.46 |  | 38222.46 |  |  | 38222.46 | 42653.42 | -4430.96 | 2017-10-06 12:05 | 2018-02-15 | 2017-10-01 | 2018-01-06
75081 | EB020330 | EB020330X | Repl F-1-1 Feeder Vibrator (CD) | 88301.78 |  | 88301.78 |  |  | 88301.78 | 99775.6 | -11473.82 | 2016-12-09 09:04 | 2017-05-31 | 2017-01-01 | 2017-08-11
75081 | EB020747 | EB020747X | Replace 21 Condenser EJ East Side | 76021.54 |  | 76021.54 |  |  | 76021.54 | 103568.92 | -27547.38 | 2017-06-27 08:18 | 2017-07-01 | 2017-06-01 | 2017-08-10
75081 | EB020757 | EB020757X | CBU Breasting Arm Containment | 67255.23 |  | 67255.23 |  |  | 67255.23 | 88385.3 | -21130.07 | 2017-08-03 11:17 | 2017-10-31 | 2017-08-01 | 2017-11-15
75081 | EB020754 | EB020754X | 2-6 CT Motor Replacement | 51715.51 |  | 51715.51 |  |  | 51715.51 | 52450.69 | -735.18 | 2017-06-28 09:29 | 2017-10-31 | 2017-06-01 | 2017-09-29
75081 | EB020753 | EB020753X | 2-5 CT Motor Replacement | 51735.77 |  | 51735.77 |  |  | 51735.77 | 52424.92 | -689.15 | 2017-06-28 09:42 | 2017-10-31 | 2017-06-01 | 2017-09-10
75081 | EB021409 | EB021409X | U2 Lime Injection System | 3393590.17 |  | 3393590.17 |  |  | 4746652.17 | 7935086.4 | -3188434.23 | 2016-05-16 11:48 | 2019-12-31 | 2016-05-01
75081 | EB020768 | CEB020768 | PSM Remote Safe Havens | 433044.83 |  | 433044.83 |  |  | 433044.83 | 976447.45 | -543402.62 | 2017-09-14 23:28 | 2020-03-31 | 2017-09-01
75081 | EBS01243 | EBS01243X | New East Bend Landfill | 12098161.98 |  | 12098161.98 |  |  | 39314186.11 | 13966995.52 | 25347190.59 | 2013-11-19 | 2018-06-30 | 2013-12-01 | 2018-03-15
75081 | EB021455 | EB021455X | NERC CIP V5Upgrade | 313444.34 |  | 313444.34 |  |  | 1441980.12 | 797045 | 644935.12 | 2016-02-02 14:08 | 2017-06-30 | 2016-02-01 | 2017-09-23
75081 | EB020592 | EB020592X | WSP Pavement Expansion (EF) | 1581.66 |  | 1581.66 |  |  | 492463.67 | 320905.33 | 171558.34 | 2016-09-02 08:33 | 2016-12-31 | 2016-09-01 | 2017-02-18
75081 | EB201285 | EB201285X | Condenser Outer Loop Retube | 2086838.7 |  | 2086838.7 |  |  | 2086838.7 | 5038518.05 | -2951679.35 | 2017-01-10 15:19 | 2018-07-01 | 2017-01-01 | 2018-08-14
75081 | EB020608 | EB020608X | Ammonia Monitoring System-Deep Dive | 269778.34 |  | 269778.34 |  |  | 313889.68 | 189130.15 | 124759.53 | 2016-11-14 10:25 | 2018-09-30 | 2016-12-01 | 2018-09-01
75081 | EB020056 | EB020056X | Sec Superheat Outlet Header Rep | 1236888.79 |  | 1236888.79 |  |  | 1474017.44 | 8908328.79 | -7434311.35 | 2016-10-20 15:11 | 2018-12-01 | 2016-10-01 | 2018-09-29
75081 | EB020597 | EB020597X | Shelter In Place Safe Haven NH3 | 49513.33 |  | 49513.33 |  |  | 190668.45 | 185610.01 | 5058.44 | 2016-09-09 11:14 | 2017-05-31 | 2016-09-01 | 2017-06-01
75081 | EB020281 | EB020281X | WSP Vacuum Filter Platforms | 119055.73 |  | 119055.73 |  |  | 119055.73 | 276375.59 | -157319.86 | 2017-01-20 15:26 | 2017-10-01 | 2017-02-01 | 2017-10-14
75081 | EB020290 | CEB020290 | Lined Retention Basin | 1653491.94 |  | 1653491.94 |  |  | 2679187.58 | 3085662 | -406474.42 | 2016-07-11 18:39 | 2018-11-15 | 2016-08-01 | 2019-02-28
75081 | EB020774 | EB020774X | Turbine Floor LED Lighting | 52850.78 |  | 52850.78 |  |  | 52850.78 | 79243.31 | -26392.53 | 2017-10-13 11:33 | 2018-03-31 | 2017-11-01 | 2018-04-03
75081 | EB021237 | EB021237X | ID Fan VFD Power Cell Rep | 793561.46 |  | 793561.46 |  |  | 793561.46 | 1092053.63 | -298492.17 | 2017-05-23 14:42 | 2018-08-26 | 2017-09-01 | 2018-09-08
75081 | EB020043 | CEB020043 | HCAD G Conveyor Washbox | 16617.2 |  | 16617.2 |  |  | 16617.2 | 180937.22 | -164320.02 | 2017-11-03 18:04 | 2018-09-01 | 2017-12-01 | 2018-09-06
75081 | EB020763 | CEB020763 | Crusher &Transfer House LED Light | 375311.99 |  | 375311.99 |  |  | 375311.99 | 396006.4 | -20694.41 | 2017-09-01 16:07 | 2018-11-30 | 2017-09-01 | 2018-11-30
75081 | EB020639 | EB020639X | Replace B Conveyor Belt | 77379.64 |  | 77379.64 |  |  | 77379.64 | 185065.65 | -107686.01 | 2017-12-15 14:37 | 2018-09-01 | 2017-12-01 | 2018-09-02
75081 | EB021410 | CEB021410 | Dry Bottom Ash Conversion | 11297658.82 |  | 11297658.82 |  |  | 12920828.48 | 24439593 | -11518764.52 | 2015-10-15 14:37 | 2018-08-30 | 2015-12-01 | 2018-09-10
75081 | EB020673 | EB020673X | CEMS Monitor Replacement | 156583.63 |  | 156583.63 |  |  | 156583.63 | 495143.52 | -338559.89 | 2017-07-05 10:17 | 2018-10-26 | 2017-07-01 | 2018-07-12
75081 | EB020672 | CEB020672 | SmartGen EBS UAT DGA | 36466.2 |  | 36466.2 |  |  | 36466.2 | 203942.38 | -167476.18 | 2017-11-03 18:20 | 2018-11-01 | 2017-12-01 | 2018-12-01
75081 | EBS01204 | REBS01204 | EBS-Landfill Cover | -0.01 |  | -0.01 |  |  | -6.8212e-13 | 0 | -6.8212e-13 | 2007-03-21 | 2010-04-30 | 2007-04-01 | 2010-04-30
75081 | EB021422 | EB021422X | Precipitator Hot Side Rebuild | 11604204.67 |  | 11604204.67 |  |  | 12231898.76 | 34338949.86 | -22107051.1 | 2015-12-04 13:47 | 2019-05-31 | 2016-01-01 | 2018-09-29
75081 | EB020584 | EB020584X | Replace Ammonia Forwarding Pmp Skid | 1299.47 |  | 1299.47 |  |  | 101514.5 | 108910 | -7395.5 | 2016-07-26 08:00 | 2016-12-31 | 2016-09-01 | 2017-03-12
75081 | EB021310 | EB021310X | 2- 5 Pulv Roll Wheel Rep 2016 -2017 | 432992.27 |  | 432992.27 |  |  | 533321.7 | 830662.1 | -297340.4 | 2016-11-29 13:38 | 2017-08-31 | 2016-12-01 | 2017-08-11
75081 | EB020551 | EB020551X | Replace 2-1 SBAC Controls | 221080.7 |  | 221080.7 |  |  | 221080.7 | 165619.85 | 55460.85 | 2017-01-24 08:59 | 2017-07-01 | 2017-02-01 | 2017-08-11
75081 | EB021429 | EB021429X | HCAD Bunker/Feeder Pipes & Iso Gate | 23237.08 |  | 23237.08 |  |  | 23237.08 | 306277.24 | -283040.16 | 2017-08-03 12:42 | 2019-09-01 | 2017-10-01 | 2018-09-09
75081 | EB020786 | EB020786X | Repl Training Bldg Facade | 7802 |  | 7802 |  |  | 7802 | 44778.94 | -36976.94 | 2017-10-23 09:28 | 2018-05-30 | 2017-12-01 | 2018-06-30
75081 | EBS01297 | EBS01297X | Replace Module Demister Trays | 401760.4 |  | 401760.4 |  |  | 401760.4 | 1206795.28 | -805034.88 | 2017-05-23 14:24 | 2018-08-02 | 2017-09-01 | 2018-08-22
75081 | EB020691 | CEB020691 | PSM Ammonia Storage Tank Level | 65639.99 |  | 65639.99 |  |  | 65639.99 | 181450.31 | -115810.32 | 2017-10-16 14:20 | 2019-03-31 | 2017-12-01 | 2018-09-01
75081 | EB021336 | EB021336X | CT Bypass Valve Replacement 2016 | -159.77 |  | -159.77 |  |  | 411115.1 | 410058.61 | 1056.49 | 2015-10-06 11:44 | 2016-08-01 | 2015-10-01 | 2016-08-07
75081 | EB020760 | EB020760X | 2-7 CT Gearbox Replacement | 239011.36 |  | 239011.36 |  |  | 239011.36 | 191860.68 | 47150.68 | 2017-08-14 09:31 | 2017-12-31 | 2017-08-01 | 2018-02-15
75081 | EB021248 | EB021248X | Replace Boiler Roof Exhaust Fans | 472099.83 |  | 472099.83 |  |  | 472099.83 | 582115.52 | -110015.69 | 2017-01-20 15:12 | 2018-06-01 | 2017-02-01 | 2018-05-23
75081 | EB021442 | EB021442X | Station Chargers & Batteries | 112033.08 |  | 112033.08 |  |  | 112033.08 | 570807.88 | -458774.8 | 2017-04-21 10:37 | 2018-07-01 | 2017-08-01 | 2018-08-18
75081 | EB020674 | EB020674X | Replace CBU Cantilever Hoist Drive | 56968.03 |  | 56968.03 |  |  | 56968.03 | 517624.69 | -460656.66 | 2017-10-06 12:16 | 2018-08-26 | 2017-10-01 | 2018-08-04
75081 | EB020758 | EB020758X | Replace #2 LP Turbine L-0 Row | 235506.73 |  | 235506.73 |  |  | 235506.73 | 2343723.09 | -2108216.36 | 2017-08-31 11:50 | 2018-09-01 | 2017-10-01 | 2018-09-29
75081 | EB0412 | EB0412X | Repl Boiler Economizer | 1295589.33 |  | 1295589.33 |  |  | 1567738.5 | 8380214.97 | -6812476.47 | 2016-01-19 09:34 | 2018-12-31 | 2016-01-01 | 2018-09-29
75081 | CGYEB115 | CGYPEB115 | CCP EB-115 T6 E. BEND GYPSUM MITIGA | -1306.45 |  | -1306.45 |  |  | 852416.84 | 1500000 | -647583.16 | 2015-06-04 17:33 | 2015-12-31 | 2015-08-01 | 2015-12-31
75081 | EB020358 | EB020358X | Used Oil Storage Building (EF) | 69366.04 |  | 69366.04 |  |  | 270647.99 | 152235.01 | 118412.98 | 2016-07-25 14:55 | 2016-12-31 | 2016-08-01 | 2017-03-20
75081 | EB020336 | EB020336X | Scanner/Igniter Replacement | 197820.08 |  | 197820.08 |  |  | 197820.08 | 488807.31 | -290987.23 | 2017-09-28 12:27 | 2018-08-15 | 2017-10-01 | 2018-09-29
75081 | EB020298 | CEB020298 | East Bend SW / PW REROUTE | 11128784.78 |  | 11128784.78 |  |  | 12099518.11 | 29960739 | -17861220.89 | 2016-07-01 15:23 | 2019-05-01 | 2016-08-01 | 2019-06-30
75081 | EB020765 | EB020765X | Replace ID Fan VFD Room HVAC | 108167.85 |  | 108167.85 |  |  | 108167.85 | 85728.11 | 22439.74 | 2017-09-28 12:42 | 2018-03-31 | 2017-10-01 | 2018-03-28
75081 | EB020785 | EB020785X | Replace Training Building Roof (SM) | 43548.79 |  | 43548.79 |  |  | 43548.79 | 54227.26 | -10678.47 | 2017-10-23 09:37 | 2018-03-31 | 2017-12-01 | 2018-03-28
75081 | EB020647 | CEB020647 | SmartGen EastBend Phase II BTLD | 104230.07 |  | 104230.07 |  |  | 104230.07 | 103621.3 | 608.77 | 2017-11-01 18:10 | 2018-11-01 | 2017-12-01 | 2018-11-01
75081 | EB020703 | EB020703X | HCAD Replace B to C Chute | 164452.98 |  | 164452.98 |  |  | 164452.98 | 927247.14 | -762794.16 | 2017-08-16 10:39 | 2018-09-30 | 2017-09-01 | 2018-08-12
75081 | EB020090 | EB020090X | Boiler Room Vent Fan on Mezzanine | 3435.22 |  | 3435.22 |  |  | 654688.61 | 496509.5 | 158179.11 | 2016-05-16 11:32 | 2016-12-31 | 2016-05-01 | 2017-02-28
75081 | EB020587 | EB020587X | Repl WSP Flyash Flow Gate (EF) | 13016.65 |  | 13016.65 |  |  | 59173.01 | 42374.34 | 16798.67 | 2016-08-25 13:56 | 2016-12-30 | 2016-10-01 | 2017-02-28
75081 | EB020643 | EB020643X | Cellular BDA Installation | 90321.65 |  | 90321.65 |  |  | 90321.65 | 50638.88 | 39682.77 | 2017-04-21 10:19 | 2018-03-31 | 2017-04-01 | 2018-03-22
75081 | EB020579 | EB020579X | Replace Training Bldg Air Handlers | 15917.97 |  | 15917.97 |  |  | 87964.47 | 94366.52 | -6402.05 | 2016-07-26 07:48 | 2016-12-22 | 2016-09-01 | 2017-02-18
75081 | EB020615 | EB020615X | Replace WSP Radial Stacker Belt | 0 |  | 0 |  |  | 24068.59 | 27975.18 | -3906.59 | 2016-12-19 11:58 | 2016-12-31 | 2016-12-01 | 2017-03-31
75081 | EB020332 | EB020332X | Replace Shuttle Barge Winches (EF) | 421770.43 |  | 421770.43 |  |  | 421770.43 | 284144.01 | 137626.42 | 2017-02-20 13:25 | 2017-08-01 | 2017-03-01 | 2017-08-11
75081 | EB020783 | EB020783X | WSP Filter Platforms Phase 2 | 235454.15 |  | 235454.15 |  |  | 235454.15 | 270754.36 | -35300.21 | 2017-10-23 10:17 | 2018-03-30 | 2017-11-01 | 2018-03-29
75081 | EB020784 | EB020784X | Repl Service Water Bldg Roof (SM) | 24532 |  | 24532 |  |  | 24532 | 47200.18 | -22668.18 | 2017-10-23 10:11 | 2018-06-30 | 2017-12-01 | 2018-07-18
75081 | EB020602 | EB020602X | C Conveyor Motor Rewind Cap Spare | -97.74 |  | -97.74 |  |  | 47514.34 | 49315.35 | -1801.01 | 2016-12-09 09:48 | 2016-12-31 | 2016-12-01 | 2017-03-09
75081 | EB021291 | EB021291X | Landfill Cover 2012 | 4467.33 |  | 4467.33 |  |  | -1.2648e-12 | 0 | -1.2648e-12 | 2012-03-02 | 2014-12-31 | 2012-05-01 | 2014-03-31
75081 | CEBLIDR | CCEBLIDR | CCP East Bend Landfill Ind Door Rep | 2568.43 |  | 2568.43 |  |  | 16151.97 | 12150.69 | 4001.28 | 2016-08-31 09:58 | 2017-01-15 | 2016-11-01 | 2017-03-06
75081 | EB020589 | EB020589X | 2-6 CT Motor and Gearbox Repl | -94.04 |  | -94.04 |  |  | 206179.89 | 201151.22 | 5028.67 | 2016-10-06 14:28 | 2016-09-30 | 2016-10-01 | 2016-08-06
75081 | EB020630 | EB020630X | Tractor Garage Sewer Line | 101294.35 |  | 101294.35 |  |  | 101294.35 | 51612.91 | 49681.44 | 2017-04-21 10:51 | 2017-07-30 | 2017-04-01 | 2017-08-19
75081 | EB020792 | EB020792X | 2-2 WSP Vacuum Pump Repl (SM) | 38694.47 |  | 38694.47 |  |  | 38694.47 | 38531.24 | 163.23 | 2017-12-15 15:50 | 2018-02-15 | 2017-12-01 | 2018-03-20
75082 | WDC01254 | WDC01254X | Stack Lighting Replacement | -23979.1 |  | -23979.1 |  |  | 28395.09 | 42673 | -14277.91 | 2013-08-18 | 2015-09-25 | 2013-11-01 | 2014-02-15
75082 | PCTAIT137 | AIT13709H | Gas ETRM | 0 |  | 0 |  |  | 222.85 | 390.53 | -167.68 | 2014-04-25 | 2014-12-31 | 2014-06-01 | 2014-11-30
75082 | WDC01260 | WDC01260X | Admin Building HVAC Replacement | 0 |  | 0 |  |  | 79591.38 | 70725 | 8866.38 | 2014-06-16 | 2015-01-15 | 2014-06-01 | 2015-02-21
75082 | WD061200 | WD061200X | WGS Unit 6 Excitation Controls | 18223.19 |  | 18223.19 |  |  | 175950.78 | 220214 | -44263.22 | 2013-08-18 | 2015-01-20 | 2013-10-01 | 2015-01-10
75082 | PCTAIT218 | AIT21826S | FSO Forecasting Phase III | -45.32 |  | -45.32 |  |  | 72092.34 | 120784.05 | -48691.71 | 2016-12-16 08:18 | 2017-06-30 | 2016-12-01 | 2017-05-31
75082 | OPTIM | COPTIM | Develop OPTIM Modeling Tool | 12227.6 |  | 12227.6 |  |  | 65186.16 | 18615.68 | 46570.48 | 2016-01-15 14:16 | 2017-09-30 | 2016-01-01 | 2017-09-16
75082 | WDC00006 | WDC00006X | Cathodic Protection System Repl | 5920.15 |  | 5920.15 |  |  | 261347.4 | 183144.44 | 78202.96 | 2016-01-20 12:00 | 2017-01-31 | 2016-01-01 | 2017-04-24
75082 | WDC01251 | WDC01251X | UPS Battery Replacement | 0 |  | 0 |  |  | 126953.2 | 100463 | 26490.2 | 2012-08-09 | 2012-12-31 | 2012-08-01 | 2012-12-14
75082 | WDC01252 | WDC01252X | Admin Building Roof Replacement | -18880 |  | -18880 |  |  | 158991.24 | 243442 | -84450.76 | 2013-08-18 | 2013-12-31 | 2013-09-01 | 2014-02-15
75082 | WDC01250 | WDC01250X | Diesel Fire Pump Controls | -500 |  | -500 |  |  | 17095.12 | 18229 | -1133.88 | 2012-04-02 | 2012-09-30 | 2012-04-01 | 2012-04-25
75082 | WDC01262 | WDC01262X | Security Camera Upgrade | 0 |  | 0 |  |  | 103184.26 | 110085 | -6900.74 | 2013-09-26 | 2014-11-01 | 2013-10-01 | 2014-12-26
75082 | WDC01267 | WDC01267X | IT Site Bandwidth Upgrade | 0 |  | 0 |  |  | 85785.51 | 162944.68 | -77159.17 | 2015-05-13 08:49 | 2015-12-31 | 2015-05-01 | 2016-03-05
75082 | WDC01256 | WDC01256X | NERC CIP V | -5.26 |  | -5.26 |  |  | 117013.36 | 118407 | -1393.64 | 2015-08-11 12:38 | 2016-12-30 | 2015-11-01 | 2017-03-16
75082 | WD101209 | WD101209X | WGS CT 1 Overhaul #2 | 7747159.27 |  | 7747159.27 |  |  | 10907928.93 | 9754682 | 1153246.93 | 2011-11-11 | 2017-08-21 | 2011-12-01 | 2017-08-12
75082 | WDC01245 | WDC01245X | Network Firewall Upgrade | -46.36 |  | -46.36 |  |  | 10349.94 | 18462 | -8112.06 | 2011-09-06 | 2012-07-27 | 2011-10-01 | 2012-06-29
75082 | KYSC0001 | WAL2EQPT | Walton 2 equipment | 906152.61 |  | 906152.61 |  |  | 906152.61 | 1335646.33 | -429493.72 | 2017-08-17 12:33 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | KYSCPM | KY solar common cost | 58219.83 |  | 58219.83 |  |  | 58219.83 | 1 | 58218.83 | 2017-08-17 12:39 | 2017-12-31 | 2017-08-01 | 2018-03-15
75082 | KYSC0001 | WAL1PM | Walton 1 solar owners cost | 374303.52 |  | 374303.52 |  |  | 374303.52 | 575893.12 | -201589.6 | 2017-08-17 12:40 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2CON | Walton 2 solar construction | 1768487.38 |  | 1768487.38 |  |  | 1768487.38 | 2018869.74 | -250382.36 | 2017-08-17 12:30 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL1CON | Walton 1 solar construction | 1830226.8 |  | 1830226.8 |  |  | 1830226.8 | 1994194.98 | -163968.18 | 2017-08-17 12:28 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | CRITCON | Crittenden solar construction | 2316058.43 |  | 2316058.43 |  |  | 2316058.43 | 3190661.23 | -874602.8 | 2017-08-17 12:31 | 2017-12-31 | 2017-08-01 | 2018-03-15
75082 | KYSC0001 | CRITEQPT | Crittenden equipment | 1422077.07 |  | 1422077.07 |  |  | 1422077.07 | 1780384.04 | -358306.97 | 2017-08-17 12:34 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2PM | Walton 2 solar owners cost | 342378.77 |  | 342378.77 |  |  | 342378.77 | 575723.1 | -233344.33 | 2017-08-17 12:40 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL1EQPT | Walton 1 equipment | 1216611.47 |  | 1216611.47 |  |  | 1216611.47 | 1336040.76 | -119429.29 | 2017-08-17 12:32 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | CRITGPM | Crittenden GPM | 57629.86 |  | 57629.86 |  |  | 57629.86 | 23846.56 | 33783.3 | 2017-08-17 12:38 | 2017-12-31 | 2017-11-01 | 2018-03-15
75082 | KYSC0001 | WAL1GPM | Walton 1 GPM | 20745.22 |  | 20745.22 |  |  | 20745.22 | 17895 | 2850.22 | 2017-08-17 12:36 | 2017-12-31 | 2017-11-01 | 2018-03-15
75082 | KYSC0001 | WAL2GPM | Walton 2 GPM | 20745.22 |  | 20745.22 |  |  | 20745.22 | 17889.72 | 2855.5 | 2017-08-17 12:37 | 2017-12-31 | 2017-11-01 | 2018-03-15
75082 | KYSC0001 | CRITPM | Crittenden solar owners cost | 612970.32 |  | 612970.32 |  |  | 612970.32 | 767424.88 | -154454.56 | 2017-08-17 12:41 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | WDC00004 | WDC00004X | Install Fuel Oil System - BOP | 1989386.95 |  | 1989386.95 |  |  | 2149548.52 | 25801931.95 | -23652383.43 | 2016-08-22 15:04 | 2019-07-01 | 2016-08-01 | 2019-07-05
75082 | WDC00015 | WDC00015X | Repl all units 4KV Aux Relay | 168960.72 |  | 168960.72 |  |  | 168960.72 | 159521.99 | 9438.73 | 2017-05-16 08:33 | 2017-12-31 | 2017-05-01 | 2018-01-15
75082 | WDCM0007 | WDCM0007X | LEL Gas Monitors and Shut Down | 167121.69 |  | 167121.69 |  |  | 167121.69 | 186303.87 | -19182.18 | 2017-08-24 12:55 | 2018-02-28 | 2017-09-01 | 2018-01-15
75082 | WDCM1209 | WDCM1209X | SmartGen Installation | 10720.43 |  | 10720.43 |  |  | 266829.12 | 154707 | 112122.12 | 2015-03-06 09:59 | 2017-12-30 | 2015-04-01 | 2017-10-19
75082 | WDC01268 | WDC01268X | Data Network Life Cycle Replacement | 8387.46 |  | 8387.46 |  |  | 114608.56 | 30681.83 | 83926.73 | 2015-08-02 11:21 | 2016-08-15 | 2015-08-01 | 2016-07-01
75082 | WDC01261 | WDC01261X | Replace CO2 Fire Prot Panels | 0 |  | 0 |  |  | 786578.39 | 717032.11 | 69546.28 | 2015-12-01 11:46 | 2016-05-30 | 2015-12-01 | 2016-08-28
75082 | WD040012 | WD040012X | WGS U4 Generator Rotor Rewind | 1073497.72 |  | 1073497.72 |  |  | 1073497.72 | 1555038.42 | -481540.7 | 2017-11-13 10:54 | 2018-05-15 | 2017-11-01 | 2018-05-27
75082 | WDCM0017 | WDCM0017X | Main Security Guard House Bldg | -1000 |  | -1000 |  |  | 34008.08 | 26000 | 8008.08 | 2016-08-15 09:55 | 2016-12-30 | 2016-09-01 | 2017-03-01
|  |  |  | 149551060.58 | 154174662.4608 | -4623601.8808 | -3.092%

## 2018
Duke Energy Kentucky Electric
Year 2018
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75084 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 0.05 |  | 0.05 |  |  | 342.42 | 217 | 125.42 | 2015-03-30 16:09 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 0.1 |  | 0.1 |  |  | 37 | 217 | -180 | 2015-03-30 13:06 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084 | FENABLEH | ECOMH | Enable ECOM Data Hub | 0.07 |  | 0.07 |  |  | 742.83 | 685 | 57.83 | 2015-09-29 09:53 | 2017-10-31 | 2016-01-01 | 2017-11-07
75084 | FENABLEH | EGISH | Enable EGIS Hardware | 0.29 |  | 0.29 |  |  | 1276.24 | 1224 | 52.24 | 2015-03-30 15:31 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 0.06 |  | 0.06 |  |  | 90.47 | 136 | -45.53 | 2015-03-30 13:46 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084 | FENABLEH | MAXH | Enable Maximo Hardware | 0.56 |  | 0.56 |  |  | 8565.87 | 9267 | -701.13 | 2015-03-30 12:42 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLEH | MOBH | Enable Mobility Hardware | 2.04 |  | 2.04 |  |  | 191682.47 | 172489 | 19193.47 | 2015-03-30 15:55 | 2017-10-31 | 2015-07-01 | 2017-11-07
75084 | FENABLEH | SDDTH | Enable Subdiv Design Tool Hardware | 0.06 |  | 0.06 |  |  | 16.59 | 15 | 1.59 | 2015-03-30 15:16 | 2017-10-31 | 2017-06-01 | 2017-11-07
75084 | FENABLEH | WRTH | Enable WRT & WMSP Hardware | 0.1 |  | 0.1 |  |  | 26.56 | 22 | 4.56 | 2015-03-30 13:25 | 2017-10-31 | 2017-06-01 | 2017-11-07
75084 | FENABLEH | TPETH | Enable Trans Proj Est Hardware | 0.1 |  | 0.1 |  |  | 1440.49 | 1073 | 367.49 | 2015-08-04 11:22 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084 | FENABLEH | PRIMH | Enable Primavera Hardware | 99.77 |  | 99.77 |  |  | 3123.58 | 3707 | -583.42 | 2015-03-30 16:23 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084 | FENABLEH | TPCTH | Enable Trans Proj Cost Hardware | 0.08 |  | 0.08 |  |  | 1077.99 | 1411 | -333.01 | 2015-08-04 10:47 | 2017-10-31 | 2015-11-01 | 2017-11-07
75084 | FENABLEH | SSDTH | Enable Subst Design Tool Hardware | 0.06 |  | 0.06 |  |  | 115.06 | 118 | -2.94 | 2015-03-30 15:04 | 2017-10-31 | 2015-08-01 | 2017-11-07
75084 | FENABLEH | TIMH | Enable TIM Hardware | 0.16 |  | 0.16 |  |  | 73.01 | 84 | -10.99 | 2015-03-30 14:56 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 3817.08 |  | 3817.08 |  |  | 217692.32 | 199412 | 18280.32 | 2015-03-30 14:59 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | ARMS | Enable ARM Scheduler Software | 4358.45 |  | 4358.45 |  |  | 194322.06 | 199412 | -5089.94 | 2015-03-30 14:11 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 2437.64 |  | 2437.64 |  |  | 124005.22 | 117858 | 6147.22 | 2015-03-30 15:05 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | EGISS | Enable EGIS Software | 15748.68 |  | 15748.68 |  |  | 761506.93 | 670125 | 91381.93 | 2015-03-30 14:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | ENABLETDG | ENABLETDG Clearing Project | -59376.64 |  | -59376.64 |  |  | -1.31 | 801485.44 | -801486.75 | 2015-05-12 14:57 | 2018-10-01 | 2015-05-01
75084 | FENABLES | EXPDS | Enable Expert Designer Software | 7501.04 |  | 7501.04 |  |  | 154799.92 | 145274 | 9525.92 | 2015-03-30 14:25 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | MAXS | Enable Maximo Software | 31886.85 |  | 31886.85 |  |  | 1442676.85 | 1352478 | 90198.85 | 2015-03-30 14:04 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | MOBS | Enable Mobility Software | 15445.86 |  | 15445.86 |  |  | 883414.47 | 932343 | -48928.53 | 2015-03-30 14:54 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 3666.74 |  | 3666.74 |  |  | 114545.91 | 22774 | 91771.91 | 2015-03-30 14:43 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | WRTS | Enable WRT & WMSP Software | 4390.16 |  | 4390.16 |  |  | 181189 | 168186 | 13003 | 2015-03-30 14:18 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | SSDTS | Enable Subst Design Tool Software | 6109.66 |  | 6109.66 |  |  | 74161.39 | 79764 | -5602.61 | 2015-03-30 14:36 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | PRIMS | Enable Primavera Software | 2717.94 |  | 2717.94 |  |  | 159527.68 | 154922 | 4605.68 | 2015-03-30 15:12 | 2017-10-31 | 2015-06-01 | 2017-11-07
75084 | FENABLES | TIMS | Enable TIM Software | 4884.71 |  | 4884.71 |  |  | 246480.92 | 239157 | 7323.92 | 2015-03-30 14:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FENABLES | TPETS | Enable Trans Proj Est Software | 2934.61 |  | 2934.61 |  |  | 207940.32 | 142915 | 65025.32 | 2015-08-03 16:52 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084 | FENABLES | TPCTS | Enable Tran Proj Cost Software | 2461.72 |  | 2461.72 |  |  | 157835.79 | 208628 | -50792.21 | 2015-08-03 16:47 | 2017-10-31 | 2015-10-01 | 2017-11-07
75084 | FPIT | 338802003 | EAM Platform Optimization | 15085.92 |  | 15085.92 |  |  | 15085.92 | 147321.02 | -132235.1 | 2018-04-25 12:44 | 2020-03-30 | 2018-06-01
75084 | FPIT | 338802008 | EcoSys Durable Team Acciunting | 1407.24 |  | 1407.24 |  |  | 1407.24 | 52026 | -50618.76 | 2018-09-14 13:41 | 2019-05-29 | 2018-09-01 | 2019-05-31
75084 | FPIT | 323850001 | Fleet Asset Lifecycle & Mobile Solu | 13085.43 |  | 13085.43 |  |  | 13085.43 | 31846 | -18760.57 | 2018-02-19 16:06 | 2020-01-14 | 2018-03-01
75084 | FPIT | 338802005 | Maximo Durable Team | 12459.93 |  | 12459.93 |  |  | 12459.93 | 33459 | -20999.07 | 2018-09-13 14:56 | 2020-03-30 | 2018-10-01
75084 | FPIT | 338802004 | Mobile Durable Team | 25511.72 |  | 25511.72 |  |  | 25511.72 | 52783 | -27271.28 | 2018-09-17 12:12 | 2020-03-31 | 2018-10-01
75084 | FPIT | 346954001 | ISOP Granular Forecasting | 22465.14 |  | 22465.14 |  |  | 22465.14 | 139345 | -116879.86 | 2018-05-14 11:31 | 2019-12-30 | 2018-05-01
75084 | FPIT | 323326007 | Workstation Refresh 2017-2019 | 7459.59 |  | 7459.59 |  |  | 7459.59 | 8934 | -1474.41 | 2018-11-06 12:04 | 2019-03-31 | 2018-12-01 | 2019-03-31
75084 | SG000358F | SG358HW18 | SG 358 - MDM Scale Hardware Phase 3 | 16561.39 |  | 16561.39 |  |  | 101230.52 | 82572 | 18658.52 | 2017-05-30 17:39 | 2018-09-30 | 2017-06-01 | 2018-08-31
75084 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 177.21 |  | 177.21 |  |  | 23414.24 | 4208 | 19206.24 | 2016-11-01 13:54 | 2018-02-28 | 2016-11-01 | 2018-02-12
75084 | SG000358F | SG358HW19 | SG DEE MDM Scale HWre Phase 4 - 358 | 51391.15 |  | 51391.15 |  |  | 51391.15 | 30270.21 | 21120.94 | 2018-05-09 10:54 | 2019-08-18 | 2018-05-01 | 2019-09-24
75084 | SG000358F | SG358SW2 | SG DEE MDM Scale Sftwre Phs 4 - 358 | 10937.13 |  | 10937.13 |  |  | 10937.13 | 10496.03 | 441.1 | 2018-05-07 16:55 | 2019-08-18 | 2018-05-01 | 2019-09-24
75084 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 10191.11 |  | 10191.11 |  |  | 41275.78 | 44829.46 | -3553.68 | 2017-04-24 18:07 | 2018-12-31 | 2017-05-01 | 2019-03-31
75084 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 9551.89 |  | 9551.89 |  |  | 29528.87 | 22987.85 | 6541.02 | 2016-11-23 11:18 | 2018-12-31 | 2016-11-01 | 2019-03-31
75084 | SG000540F | SG540SW | DEE Vehicle Area Network | -4338.39 |  | -4338.39 |  |  | -9.0949e-13 | 109210 | -109210 | 2017-04-13 09:21 | 2020-12-17 | 2017-04-01 | 2018-07-16
75084 | SG000540F | SG540HW | DEE Vehicle Area Network | 15822.83 |  | 15822.83 |  |  | 15822.83 | 273196 | -257373.17 | 2018-04-12 17:01 | 2020-12-17 | 2018-09-01
75084 | SG000540F | SG540SW2 | DEE Vehicle Area Network | 93203.51 |  | 93203.51 |  |  | 93203.51 | 0 | 93203.51 | 2018-04-18 18:04 | 2020-12-17 | 2018-10-01
75084 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 0.04 |  | 0.04 |  |  | 9104.9 | 6421 | 2683.9 | 2015-06-10 18:11 | 2016-08-21 | 2015-06-01 | 2016-06-04
75084 | SGKAMIF | SG169MTRS | SG KY AMI Electric Meters - 169 | 11258539.94 |  | 11258539.94 |  |  | 21561446.69 | 23298670 | -1737223.31 | 2017-06-07 11:18 | 2019-02-28 | 2017-06-01
75084 | SGKAMIF | SG169KYEQ | SG KY AMI Equipment - 169 | 15159.66 |  | 15159.66 |  |  | 669748.78 | 1294611 | -624862.22 | 2017-06-07 15:50 | 2019-02-28 | 2017-07-01
75084 | SGKAMIF | SGKAMIMGT | DEK AMI Mgmt Project | 816363.75 |  | 816363.75 |  |  | 1293853.24 | 603878 | 689975.24 | 2016-01-20 16:12 | 2019-06-30 | 2016-01-01 | 2019-06-30
75084 | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 0.01 |  | 0.01 |  |  | 4758.72 | 170000 | -165241.28 | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75084 | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 0.01 |  | 0.01 |  |  | 18566.55 | 43500 | -24933.45 | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75084 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | 42529.94 |  | 42529.94 |  |  | 42529.94 | 110269.74 | -67739.8 | 2018-07-12 09:08 | 2020-03-31 | 2018-07-01
75084 | FMDT2017 | MDTKE17 | Panasonic CF53 Units- Kentucky | 38331.43 |  | 38331.43 |  |  | 38331.43 | 87508.08 | -49176.65 | 2017-12-14 11:20 | 2020-06-01 | 2018-01-01
75084 | SGITMTRSY | SGMDMFDHW | SG MDM Foundation Hardware | 0 |  | 0 |  |  | 73191.26 | 77000 | -3808.74 | 2012-04-20 | 2013-10-31 | 2012-05-01 | 2013-10-29
75084 | SGITOMSGI | SGSWDOMC | SG AMI DOMS S/W Module Capital | 0 |  | 0 |  |  | 28994.29 | 37300 | -8305.71 | 2012-12-20 | 2015-08-29 | 2013-01-01 | 2017-01-15
75084 | DKY2133 | MX2167589 | Mt Zion Rbld Sam Neace - DKY2133 | 134550.91 |  | 134550.91 |  |  | 140286.43 | 80732.48 | 59553.95 | 2017-09-14 18:02 | 2019-06-01 | 2017-09-01 | 2019-04-29
75084 | DKY2133 | DKY213319 | Mt Zion 22.4MVA Bk 2 DS1 | 148809.68 |  | 148809.68 |  |  | 148809.68 | 3017877 | -2869067.32 | 2018-01-29 18:02 | 2020-05-29 | 2018-04-01
75084 | DKY2133 | MX2167975 | Mt Zion Rbld Weaver Rd - DKY2133 | 122297.68 |  | 122297.68 |  |  | 134085.53 | 242159.7 | -108074.17 | 2017-10-05 10:01 | 2019-12-29 | 2017-10-01
75084 | DKY2133 | DKY213318 | Mt Zion 138kV Loop TS1 | 132327.67 |  | 132327.67 |  |  | 132327.67 | 0 | 132327.67 | 2018-01-29 18:02 | 2020-05-26 | 2018-04-01
75084 | DKY2133 | DKY213321 | Bank 1 low-side breaker | 13214.7 |  | 13214.7 |  |  | 13214.7 | 0 | 13214.7 | 2018-10-24 18:03 | 2020-03-16 | 2018-11-01
75084 | DKY1959 | D1959DS1 | Cov Sub expansion DKY1959 | 284947.45 |  | 284947.45 |  |  | 289504.59 | 290451 | -946.41 | 2017-05-16 17:18 | 2019-04-18 | 2017-07-01 | 2019-02-01
75084 | DKY1959 | D1959RS1 | Cov Sub Add Prop | 5629.31 |  | 5629.31 |  |  | 140081.24 | 112393 | 27688.24 | 2016-07-29 07:27 | 2017-10-01 | 2016-08-01 | 2017-08-19
75084 | KYGLPRT | MX7343749 | 2166 P2 X-fer distribution underbui | 4776.78 |  | 4776.78 |  |  | 4776.78 | 18473.43 | -13696.65 | 2018-02-16 10:13 | 2019-06-01 | 2018-06-01 | 2019-04-04
75084 | KYGLPRT | MX7360458 | Transfer distribution underbuild fo | 1102.36 |  | 1102.36 |  |  | 1102.36 | 10915.73 | -9813.37 | 2018-02-26 14:50 | 2019-11-29 | 2018-12-01
75084 | KYGLPRT | MX8766989 | Transfer distribution underbuild fo | 60555.81 |  | 60555.81 |  |  | 60555.81 | 63063.25 | -2507.44 | 2018-07-17 14:02 | 2019-06-01 | 2018-08-01 | 2019-02-13
75084 | KYGLPRT | MX8520300 | Transfer distribution underbuild fo | 38998.94 |  | 38998.94 |  |  | 38998.94 | 42589.04 | -3590.1 | 2018-07-12 14:02 | 2019-06-01 | 2018-07-01 | 2019-04-08
75084 | DKY2208 | D2208RS1 | Turfway Sub Site Purch | 2310259.68 |  | 2310259.68 |  |  | 2350706.42 | 382562 | 1968144.42 | 2017-05-23 15:54 | 2019-03-02 | 2017-06-01 | 2019-02-20
75084 | DMAJRIFA | J0111 | Augustine Repl fans on TB 5 | -1092.98 |  | -1092.98 |  |  | 10884.56 | 11300.35 | -415.79 | 2014-03-24 | 2015-03-31 | 2014-07-01 | 2014-10-22
75084 | DMAJRIFA | P7314 | Donaldson TB1 Bushings | -1970.27 |  | -1970.27 |  |  | 20514.26 | 11569.26 | 8945 | 2015-01-16 | 2018-03-01 | 2015-03-01 | 2016-12-31
75084 | DMAJRIFA | DM0029 | Richwood Repl Sta Batt | -83.38 |  | -83.38 |  |  | 1600.92 | 2757.91 | -1156.99 | 2015-07-24 10:48 | 2016-01-31 | 2015-08-01 | 2015-11-28
75084 | DMAJRIFA | H1600 | Augustine Repl LAs on TB 5 | -1427.41 |  | -1427.41 |  |  | 8108.5 | 7904.73 | 203.77 | 2014-01-03 | 2015-03-31 | 2014-04-01 | 2015-02-12
75084 | DMAJRIFA | P8327 | Constance Repl Station Batt | -330.3 |  | -330.3 |  |  | 15200.86 | 17541.16 | -2340.3 | 2015-03-17 11:25 | 2016-03-31 | 2015-03-01 | 2015-07-31
75084 | DMAJRIFA | EMR290 | Constance Repl Cir 41 LA's | 672.17 |  | 672.17 |  |  | 1624.37 | 1884.66 | -260.29 | 2017-01-11 12:34 | 2018-03-31 | 2017-01-01 | 2017-04-19
75084 | RELDFA | RELDKY | Relocation-D | 22314.91 |  | 22314.91 |  |  | 1213088.95 | 200 | 1212888.95 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | RELDFA | MKRDYKY | Make Ready Kentucky | 2012.19 |  | 2012.19 |  |  | 402055.84 | 10 | 402045.84 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084 | ORDFA | ORDKY | Outage Restoration Cap-D | -1623.81 |  | -1623.81 |  |  | 128869.78 | 200 | 128669.78 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | ORDFA | OUTRFUKY | Outage Reliability FollowUp Capital | 0.05 |  | 0.05 |  |  | -38051.75 | 50000 | -88051.75 | 2012-05-09 | 2050-12-31 | 2012-09-01
75084 | ORDFA | PDOHRPLKY | Public Damage Replace OH - Kentucky | 10535.38 |  | 10535.38 |  |  | 110988.47 | 1 | 110987.47 | 2015-06-13 14:43 | 2025-12-31 | 2016-02-01
75084 | ORDFA | OUTOHRLKY | Outage Replace OH - Kentucky | -66251.24 |  | -66251.24 |  |  | 373953.21 | 10 | 373943.21 | 2015-06-13 14:20 | 2025-12-31 | 2016-02-01
75084 | ORDFA | OUTUGRLKY | Outage Replace UG - Kentucky | 1693.48 |  | 1693.48 |  |  | 1295521.12 | 0 | 1295521.12 | 2015-06-13 14:34 | 2025-12-31 | 2016-02-01
75084 | ORDFA | SKY1702DC | Kentucky O&M TO CAP JOURNAL Strm 2 | -4658.06 |  | -4658.06 |  |  | 117535.19 | 109852.57 | 7682.62 | 2017-02-21 16:08 | 2017-10-31 | 2017-03-01 | 2017-07-31
75084 | ORDFA | SKY1703DC | Kentucky O&M TO CAP JOURNAL Strm 3 | -252.33 |  | -252.33 |  |  | 10876.47 | 11181.97 | -305.5 | 2017-02-21 16:12 | 2017-12-31 | 2017-06-01 | 2017-09-30
75084 | ORDFA | SKY1706DC | TO CAPTURE 2017 CAPITAL STORM # 6 | -34.75 |  | -34.75 |  |  | 1760.24 | 2072.07 | -311.83 | 2017-07-13 13:41 | 2018-12-31 | 2017-08-01 | 2017-11-30
75084 | ORDFA | SKY1707DC | TO CAPTURE 2017 CAPITAL STORM # 7 | -107.35 |  | -107.35 |  |  | 6758.91 | 6509.66 | 249.25 | 2017-07-13 13:44 | 2018-12-31 | 2017-09-01 | 2017-12-31
75084 | DPEQUIPFA | O3103 | Bellevue Repl Sta Batteries | -313.43 |  | -313.43 |  |  | 18315.42 | 14918.34 | 3397.08 | 2014-07-16 | 2016-09-30 | 2014-10-01 | 2016-04-13
75084 | DPEQUIPFA | O3102 | Cresent Repl 48VDC Sta Batteries | -507.27 |  | -507.27 |  |  | 8601.22 | 10396.57 | -1795.35 | 2014-07-16 | 2015-03-31 | 2014-10-01 | 2015-06-02
75084 | DPEQUIPFA | P9532 | Atlas Repl Station batteries | -56.86 |  | -56.86 |  |  | 1533.51 | 958.67 | 574.84 | 2015-03-27 09:13 | 2016-03-31 | 2015-07-01 | 2015-11-30
75084 | DPEQUIPFA | EMR131 | Hebron Repl PhA Bus Discnt Switch | -958.29 |  | -958.29 |  |  | 3901.56 | 2274.86 | 1626.7 | 2016-07-26 07:04 | 2017-03-31 | 2016-08-01 | 2016-11-26
75084 | RELTFA | KYRELT1 | F6763 DOT Mt Zion Rd-Dixie Hwy | 473032.81 |  | 473032.81 |  |  | 504943.15 | 35000 | 469943.15 | 2015-07-25 18:59 | 2020-05-13 | 2015-08-01
75084 | AMKY0126 | F0245 | F6282-Loop thru Webster Ring Bus | 13460.66 |  | 13460.66 |  |  | 15317.27 | 952790.42 | -937473.15 | 2009-09-15 | 2011-10-01 | 2009-09-01 | 2011-08-10
75084 | DECCIRFA | P7274 | DEC 6892567 Donaldson 41 | -31831.25 |  | -31831.25 |  |  | 119433.83 | 205737.82 | -86303.99 | 2015-01-14 | 2019-06-30 | 2015-01-01
75084 | DECCIRFA | P7273 | DEC 6892574 Donaldson 41 | -757.98 |  | -757.98 |  |  | 164609.02 | 88334.91 | 76274.11 | 2015-01-14 | 2017-11-15 | 2015-01-01 | 2017-10-27
75084 | 314G8840 | D1640 | PP938046 COVINGTON 41 UG PART | 67913.69 |  | 67913.69 |  |  | 890658.53 | 877242 | 13416.53 | 2007-09-20 | 2009-04-30 | 2007-11-01 | 2008-12-01
75084 | FLKY0249E | DUKETCKYE | Fleet On-Road Vehicles - elec - KY | 1261.88 |  | 1261.88 |  |  | 0 | 40000 | -40000 | 2009-08-11 | 2050-12-31 | 2010-06-01 | 2016-04-05
75084 | OLE08FA | G8553 | ST emax 2178946 John Hills Rd NKU | 43.12 |  | 43.12 |  |  | 48648.12 | 105449.16 | -56801.04 | 2012-10-01 | 2014-03-15 | 2012-11-01 | 2013-06-05
75084 | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | -257190.51 |  | -257190.51 |  |  | 746727.02 | 10 | 746717.02 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084 | BLDGSUBFA | O4112 | Buffington Sub Add Gravel | -805.92 |  | -805.92 |  |  | -9.1038e-15 | 11207.12 | -11207.12 | 2014-07-17 | 2014-11-30 | 2014-07-01 | 2014-10-01
75084 | NBFA | NBKYCI | Commerc & Indust Cust Adds-MW-D | 124335.96 |  | 124335.96 |  |  | 1336697.03 | 0 | 1336697.03 | 2016-01-21 13:58 | 2025-12-31 | 2016-02-01
75084 | NBFA | NBKYRES | Residential Customer Adds-MW-D | 6348.05 |  | 6348.05 |  |  | 2253719.51 | 0 | 2253719.51 | 2016-01-21 13:51 | 2025-12-31 | 2016-02-01
75084 | AMKY1073 | L9115 | Buffington Repl VTs | -745.79 |  | -745.79 |  |  | 188472.52 | 185828 | 2644.52 | 2014-05-22 | 2015-09-01 | 2014-06-01 | 2015-06-30
75084 | CSFA | CSKY | Circuit Sectionalization | 8015.83 |  | 8015.83 |  |  | 157190.51 | 100 | 157090.51 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084 | CP16AREK | 16AR12 | Florence Repl TB4 Arresters | -412.55 |  | -412.55 |  |  | 7796.37 | 4718.91 | 3077.46 | 2016-03-17 16:08 | 2017-03-31 | 2016-03-01 | 2016-12-23
75084 | CP16AREK | 16AR13 | Wilder Repl TB2 Arresters | -691.7 |  | -691.7 |  |  | 9462.43 | 6251.7 | 3210.73 | 2016-03-17 16:53 | 2017-03-31 | 2016-03-01 | 2016-11-15
75084 | CP16AREK | 16AR06 | Richwood Repl TB1 Arrester | -949.65 |  | -949.65 |  |  | 9522.16 | 5226.33 | 4295.83 | 2016-03-17 16:34 | 2017-03-31 | 2016-03-01 | 2017-02-21
75084 | NCIPLOWK | KCIPLW002 | Wilder-Ky NERC CIP Low DS | 134.08 |  | 134.08 |  |  | 216731.04 | 195329 | 21402.04 | 2016-09-22 13:54 | 2017-09-01 | 2016-09-01 | 2017-06-09
75084 | NCIPLOWK | KCIPLW003 | York - Ky NERC CIP Low | -457.57 |  | -457.57 |  |  | 126144.36 | 125323 | 821.36 | 2016-11-17 12:52 | 2018-03-31 | 2016-11-01 | 2017-07-05
75084 | NCIPLOWK | KCIPLW001 | Augustine KY NERC CIP LW | 18619.44 |  | 18619.44 |  |  | 192630.94 | 195323 | -2692.06 | 2016-09-22 10:40 | 2018-03-31 | 2016-09-01 | 2018-02-28
75084 | NCIPLOWK | KCIPLW999 | Electronic Keys | 277014.12 |  | 277014.12 |  |  | 318823.82 | 29929 | 288894.82 | 2017-11-17 14:50 | 2020-03-31 | 2017-11-01
75084 | NCIPLOWK | KCIPLW086 | Mt_ Zion - Ky NERC CIP Low - NCIPLO | 83290.79 |  | 83290.79 |  |  | 107081.59 | 195323 | -88241.41 | 2017-02-09 15:51 | 2019-03-31 | 2017-03-01 | 2018-05-22
75084 | NCIPLOWK | KCIPLW074 | Cold Spring - Ky NERC CIP Low - NCI | 82048.91 |  | 82048.91 |  |  | 107632.06 | 195323 | -87690.94 | 2017-02-09 13:39 | 2019-03-31 | 2017-03-01 | 2018-06-27
75084 | NCIPLOWK | KCIPLW075 | Constance - Ky NERC CIP Low - NCIPL | 82236.73 |  | 82236.73 |  |  | 109718.16 | 195323 | -85604.84 | 2017-02-09 13:48 | 2019-03-31 | 2017-03-01 | 2018-05-27
75084 | NCIPLOWK | KCIPLW082 | Hebron - Ky NERC CIP Low - NCIPLOWK | 124889.9 |  | 124889.9 |  |  | 146529.83 | 195323 | -48793.17 | 2017-02-09 15:17 | 2019-03-31 | 2017-04-01 | 2018-07-12
75084 | NCIPLOWK | KCIPLW083 | Kenton - Ky NERC CIP Low - NCIPLOWK | 112233.29 |  | 112233.29 |  |  | 137108.34 | 195323 | -58214.66 | 2017-02-09 15:25 | 2019-03-31 | 2017-03-01 | 2018-07-10
75084 | NCIPLOWK | KCIPLW080 | Florence - Ky NERC CIP Low - NCIPLO | 81940.27 |  | 81940.27 |  |  | 108821.17 | 195323 | -86501.83 | 2017-02-09 14:57 | 2019-03-31 | 2017-05-01 | 2018-06-08
75084 | NCIPLOWK | KCIPLW079 | Donaldson - Ky NERC CIP Low - NCIPL | 81892.52 |  | 81892.52 |  |  | 124947.04 | 195323 | -70375.96 | 2017-02-09 14:50 | 2019-03-31 | 2017-03-01 | 2018-06-01
75084 | NCIPLOWK | KCIPLW072 | Bellevue - Ky NERC CIP Low - NCIPLO | 7852.98 |  | 7852.98 |  |  | 78480.63 | 195499.57 | -117018.94 | 2017-02-08 13:43 | 2017-11-21 | 2017-03-01 | 2017-12-13
75084 | NCIPLOWK | KCIPLW081 | Hands - Ky NERC CIP Low - NCIPLOWK | 67092.8 |  | 67092.8 |  |  | 89637.64 | 195323 | -105685.36 | 2017-02-09 15:04 | 2019-03-31 | 2017-05-01 | 2018-07-05
75084 | NCIPLOWK | KCIPLW078 | Dayton - Ky NERC CIP Low - NCIPLOWK | 92306.63 |  | 92306.63 |  |  | 112818.81 | 195323 | -82504.19 | 2017-02-09 14:42 | 2019-03-31 | 2017-03-01 | 2018-06-15
75084 | NCIPLOWK | KCIPLW084 | Kentucky University - Ky NERC CIP L | 17967.55 |  | 17967.55 |  |  | 121077.74 | 195323 | -74245.26 | 2017-02-09 15:36 | 2019-03-31 | 2017-03-01 | 2017-10-20
75084 | NCIPLOWK | KCIPLW077 | Crescent - Ky NERC CIP Low | 139500.21 |  | 139500.21 |  |  | 168833.86 | 195323 | -26489.14 | 2017-02-09 14:07 | 2019-03-31 | 2017-03-01 | 2018-06-06
75084 | TKY1687 | T1687DS2 | Alexandria Comm Upgrade - TKY1687 | 159388.72 |  | 159388.72 |  |  | 185426.06 | 68854 | 116572.06 | 2017-02-10 18:06 | 2018-11-08 | 2017-05-01 | 2018-11-08
75084 | TKY1687 | T1687DS5 | Verona Comm Upgrade - TKY1687 | 136364.54 |  | 136364.54 |  |  | 144677.57 | 68854 | 75823.57 | 2017-02-10 18:06 | 2018-09-30 | 2017-05-01 | 2018-07-26
75084 | TKY1687 | T1687DS4 | Richwood Comm Upgrade - TKY1687 | 187339.23 |  | 187339.23 |  |  | 191539.22 | 68854 | 122685.22 | 2017-02-10 18:06 | 2018-09-30 | 2017-05-01 | 2018-09-27
75084 | TKY1687 | T1687DS1 | Empire Comm Upgrade - TKY1687 | 148331.59 |  | 148331.59 |  |  | 150706.83 | 68854 | 81852.83 | 2017-02-10 18:06 | 2018-09-13 | 2017-05-01 | 2018-07-26
75084 | TKY1687 | T1687DS3 | Crittenden Comm Upgrade - TKY1687 | 141130.78 |  | 141130.78 |  |  | 148533.75 | 68854 | 79679.75 | 2017-02-10 18:06 | 2018-11-14 | 2017-05-01 | 2018-10-25
75084 | TKY1687 | T1687DS6 | White Tower Comm Upgrade - TKY1687 | 122214.34 |  | 122214.34 |  |  | 137947.53 | 68854 | 69093.53 | 2017-02-10 18:06 | 2018-11-14 | 2017-05-01 | 2018-10-11
75084 | DPEQUIPKY | EMR435 | Hebron Repl LTC Controllers - DPEQ | 36508.43 |  | 36508.43 |  |  | 38406.62 | 66338 | -27931.38 | 2017-06-02 10:04 | 2019-03-01 | 2017-07-01 | 2018-07-26
75084 | DPEQUIPKY | EMR436 | Oakbrook Repl LTC Controllers - DP | 8368.02 |  | 8368.02 |  |  | 11123.27 | 66338 | -55214.73 | 2017-06-02 10:07 | 2019-03-01 | 2017-07-01 | 2018-07-13
75084 | DPEQUIPKY | EMR364 | Villa Repl Bus1 SG Bush & LA's | -2998.53 |  | -2998.53 |  |  | 22659.95 | 10730 | 11929.95 | 2017-03-16 16:09 | 2018-03-31 | 2017-03-01 | 2017-06-30
75084 | DPEQUIPKY | EMR420 | Claryville Repl Cir 43 C Phase Reg | -232.76 |  | -232.76 |  |  | 18018.99 | 20222.39 | -2203.4 | 2017-05-18 10:15 | 2018-03-31 | 2017-05-01 | 2017-08-18
75084 | DPEQUIPKY | EMR377 | Empire Repl Station Batteries | 85.4 |  | 85.4 |  |  | 4261.12 | 1746.5 | 2514.62 | 2017-03-29 14:48 | 2018-03-31 | 2017-04-01 | 2017-09-28
75084 | DPEQUIPKY | EMR307 | Buffington Repl Bk4 LS LA's | 1748.36 |  | 1748.36 |  |  | 2450.46 | 2764.91 | -314.45 | 2017-02-01 12:33 | 2018-03-31 | 2017-02-01 | 2017-03-20
75084 | DPEQUIPKY | EMR347 | Decoursey Repl Cir 41 Reclosers | 1143.42 |  | 1143.42 |  |  | 48923.18 | 11949.13 | 36974.05 | 2017-03-03 16:23 | 2018-03-31 | 2017-03-01 | 2017-09-09
75084 | DKY2149 | D2149DL1 | AM 20708188 Beaver 41 Part 1B | -29443.97 |  | -29443.97 |  |  | 248052.94 | 178674.81 | 69378.13 | 2017-02-14 09:19 | 2018-03-31 | 2017-02-01 | 2018-03-06
75084 | DKY2149 | D2149DL2 | AM 20709176 Walton 2 Intercon | -2594.75 |  | -2594.75 |  |  | 47889.76 | 31950.28 | 15939.48 | 2017-02-14 09:34 | 2018-07-31 | 2017-10-01 | 2018-03-11
75084 | SG000430F | SG430B | Aero Pkwy Instl UG Cable | 110477.49 |  | 110477.49 |  |  | 1495862.45 | 1003250.66 | 492611.79 | 2016-04-04 13:41 | 2018-03-31 | 2016-04-01 | 2018-03-31
75084 | SG000430F | SG430A | Aero Pkwy Instl UG Conduit | -4029.58 |  | -4029.58 |  |  | 1973808.42 | 1185872.83 | 787935.59 | 2016-04-04 13:28 | 2018-03-31 | 2016-04-01 | 2017-06-21
75084 | DKY1930 | D1930DL2 | AM Erlanger Rd | 155434.15 |  | 155434.15 |  |  | 172623.98 | 75463.43 | 97160.55 | 2017-04-13 11:13 | 2018-06-15 | 2017-06-01 | 2018-04-05
75084 | DKY1930 | D1930DL1 | AM 11851684 Recd Donaldson 42 Riggs | 895043.56 |  | 895043.56 |  |  | 952955.88 | 261996.83 | 690959.05 | 2016-12-19 09:23 | 2018-08-30 | 2017-01-01 | 2018-08-30
75084 | KFSF45122 | KFS845122 | RFS 11845122 Beaver 42. I | 71995.11 |  | 71995.11 |  |  | 71995.11 | 62681.66 | 9313.45 | 2017-06-08 10:03 | 2018-07-30 | 2018-05-01 | 2018-11-06
75084 | RCLFA | RCLKY | Recloser Inst/Rem | 44407.18 |  | 44407.18 |  |  | 225925.71 | 200 | 225725.71 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | 314G8846 | D1644 | PP938164 Covington 43- UG part | 49905.49 |  | 49905.49 |  |  | 210161.03 | 207242 | 2919.03 | 2007-09-20 | 2008-12-01 | 2008-03-01 | 2008-12-01
75084 | U04ZUR | C8961 | pp 870018/joe groeschen | 0 |  | 0 |  |  | 565.94 | 0 | 565.94 | 2007-01-03 | 2007-05-01 | 2007-01-01 | 2007-02-01
75084 | TPEQUIPFA | G9064 | Wilder CB650 repl 2 bus disconnects | -2400.57 |  | -2400.57 |  |  | 38009.67 | 32086.93 | 5922.74 | 2012-12-10 | 2013-12-30 | 2013-10-01 | 2015-02-14
75084 | RLFA | RLKY | Reliability Other-FO-D | -390010.74 |  | -390010.74 |  |  | 777085.97 | 200 | 776885.97 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | RLFA | LPFUKY | Line Patrol Insp followup KY | 85814.05 |  | 85814.05 |  |  | 1130416.35 | 400000 | 730416.35 | 2010-12-22 | 2015-12-31 | 2011-03-01
75084 | RLFA | DLSKY | DLine Switches 34.5kv Replace KY | 4257.88 |  | 4257.88 |  |  | 29538.76 | 9 | 29529.76 | 2014-08-04 | 2020-12-31 | 2016-03-01
75084 | RLFA | KGENSWG | Kentucky Switchgear Repl Program | 5879.63 |  | 5879.63 |  |  | 5879.63 | 100 | 5779.63 | 2016-03-28 10:49 | 2030-12-31 | 2018-05-01
75084 | TMAJRIFA1 | EMR020 | Limaburg Repl PH A Regulator | -404.64 |  | -404.64 |  |  | 23151.47 | 17459.47 | 5692 | 2016-03-01 13:57 | 2017-03-31 | 2016-03-01 | 2016-06-03
75084 | TMAJRIFA1 | EMR173 | Wilder Repl failed bushings | -503.78 |  | -503.78 |  |  | 86309.16 | 38599.82 | 47709.34 | 2016-09-13 11:41 | 2018-03-31 | 2016-10-01 | 2017-11-02
75084 | SGKDAISS | H1313 | Beaver Sub SG DA | -30827.08 |  | -30827.08 |  |  | 353138.71 | 236862 | 116276.71 | 2013-11-27 | 2015-06-30 | 2013-12-01 | 2015-03-30
75084 | MOFA | MOKY | Major Outage Followup-D | 0.36 |  | 0.36 |  |  | 32220.25 | 100 | 32120.25 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084 | PRDFA | PRDKY | Pole Repl Other-D | 123948.67 |  | 123948.67 |  |  | 1453799.4 | 200 | 1453599.4 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | TKY1672 | T1672TS2 | F965 Wilder Rel Repl | -7536.95 |  | -7536.95 |  |  | 364449.67 | 326080 | 38369.67 | 2016-09-27 18:02 | 2018-03-31 | 2016-10-01 | 2017-08-10
75084 | SG000829F | SG829PT01 | Wireless & Optical Test Equipment | 23308.15 |  | 23308.15 |  |  | 23308.15 | 25644.65 | -2336.5 | 2018-05-23 15:02 | 2019-03-30 | 2018-06-01 | 2018-11-21
75084 | CP15BATK | 15BA0019 | Hebron Repl Station Batteries | -583.29 |  | -583.29 |  |  | 9874.76 | 10632.72 | -757.96 | 2015-04-17 12:18 | 2016-03-31 | 2015-06-01 | 2015-11-30
75084 | CERTFA | KYCERT1 | CERTKY P0 CIR 966 | -4484.46 |  | -4484.46 |  |  | 1140.51 | 5000 | -3859.49 | 2016-10-28 08:37 | 2017-06-30 | 2016-11-01 | 2017-03-31
75084 | AMKY1176 | P6679 | Villa CCVT Repl | -3375.93 |  | -3375.93 |  |  | 39225.45 | 90805 | -51579.55 | 2014-10-27 | 2016-03-31 | 2014-11-01 | 2015-09-13
75084 | GLPRTFA | KYGLPR5 | GLT Cir 2862B P1-P2 | -560.75 |  | -560.75 |  |  | 56225.27 | 160000 | -103774.73 | 2016-06-13 16:14 | 2021-03-31 | 2016-07-01
75084 | GLPRTFA | KYGLPR11 | F5967 Repl HL867 to HL872 and HL876 | 891.14 |  | 891.14 |  |  | 40732.87 | 220579 | -179846.13 | 2016-11-14 13:36 | 2021-03-31 | 2017-05-01
75084 | SG000753F | SG753EQ | SG DEE Field Network Director - 753 | 2970.06 |  | 2970.06 |  |  | 3072.34 | 3279 | -206.66 | 2017-09-25 21:34 | 2018-11-18 | 2017-11-01 | 2018-11-08
75084 | SG000753F | SG753SW | SG DEE Field Network Director - 753 | 4510.27 |  | 4510.27 |  |  | 5351.53 | 5093 | 258.53 | 2017-09-25 21:04 | 2018-11-18 | 2017-10-01 | 2018-11-08
75084 | CP17BATK | 17BA23 | Verona Repl Batteries | -328.16 |  | -328.16 |  |  | 2818.23 | 3008.94 | -190.71 | 2017-06-02 15:53 | 2018-03-31 | 2017-06-01 | 2017-09-06
75084 | CP17BATK | 17BA31 | Crittenden Repl Batteries | 5716.54 |  | 5716.54 |  |  | 5764.34 | 3524.3 | 2240.04 | 2017-07-05 14:53 | 2018-03-31 | 2017-12-01
75084 | CP17BATK | 17BA14 | Mt Zion Repl Battery | 0 |  | 0 |  |  | 8080.5 | 8424.82 | -344.32 | 2017-03-31 15:27 | 2018-03-31 | 2017-07-01 | 2018-01-20
75084 | CP17BATK | MX6589455 | Donaldson Repl 125VDC Station Batt | 13044 |  | 13044 |  |  | 13044 | 7271.16 | 5772.84 | 2017-12-07 18:02 | 2019-03-31 | 2018-01-01 | 2019-02-15
75084 | DKY2205 | D2205DL1 | AM 20888790 Oakbrook 41-42 Rconf | 17213.92 |  | 17213.92 |  |  | 48814.68 | 36809.95 | 12004.73 | 2017-03-09 14:25 | 2018-07-31 | 2017-09-01 | 2018-06-02
75084 | ORTFA | TK69V03 | KY Capital Storm Work | 29965.6 |  | 29965.6 |  |  | 406895.2 | 372000 | 34895.2 | 2016-12-13 09:52 | 2018-05-31 | 2017-05-01 | 2017-07-31
75084 | ORTFA | TK69V01 | KY Capital Storm Work | 8379.63 |  | 8379.63 |  |  | 506214.73 | 454872.3 | 51342.43 | 2016-12-13 09:49 | 2017-12-31 | 2017-03-01 | 2017-07-31
75084 | SCFOFA | SCFOKY | System Capacity-FO | 286242.72 |  | 286242.72 |  |  | 783252.33 | 100 | 783152.33 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | CAPFA | OTVSRKY | Cap Oil to Vac Switch Repl KY | 22706.28 |  | 22706.28 |  |  | 23571.44 | 100000 | -76428.56 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084 | VMTDFA | VMTDKY | Trans Line Clr Removal | 313956.9 |  | 313956.9 |  |  | 842598.86 | 2 | 842596.86 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | VMDDTFA | VMDDTKY | Distr Line Clr Removal | 75371.13 |  | 75371.13 |  |  | 2008000.63 | 1 | 2007999.63 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | VMDDTFA | VMCMCKY | R/W CKT MAINT CAP KENTUCKY | -36406.86 |  | -36406.86 |  |  | 2232322.15 | 1 | 2232321.15 | 2012-01-25 | 2050-12-31 | 2012-02-01
75084 | TOOLFA | TOOLKY | Tools & Equip | 26893.56 |  | 26893.56 |  |  | 1810189.82 | 101 | 1810088.82 | 2008-07-01 | 2050-12-31 | 2008-09-01
75084 | GLPRDFA | GLPRDKY | Pole Repl Gnd Line-D | 34032.43 |  | 34032.43 |  |  | 1806278.16 | 200 | 1806078.16 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | OLE08RPFA | OLE08RPKY | Light Repl-OLE | 1792.06 |  | 1792.06 |  |  | 1792.06 | 90 | 1702.06 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-04-01
75084 | NEWCAPFA | NEWCAPKY | New Capacitors | 2792.97 |  | 2792.97 |  |  | 36090.64 | 101 | 35989.64 | 2008-07-01 | 2050-12-31 | 2008-08-01
75084 | SLFA | SLKY | Light Repl-Tarriff | 1586.21 |  | 1586.21 |  |  | 211302.94 | 299 | 211003.94 | 2008-07-01 | 2050-12-31 | 2008-07-01
75084 | SGAMF | SG344SW | SG DEE Distrib System Health - SW | 16503.55 |  | 16503.55 |  |  | 48154.72 | 73774 | -25619.28 | 2015-12-18 14:25 | 2019-11-30 | 2016-01-01
75084 | FTDITKE | TDITKE | PD KENTUCKY IT HARDWARE | 928.23 |  | 928.23 |  |  | 2317.87 | 1 | 2316.87 | 2010-07-01 | 2025-12-25 | 2016-05-01
75084 | SGDMSCF | SG361SW | SG DEE DMS Project 10 SW | 1037.42 |  | 1037.42 |  |  | 2182.91 | 266133.19 | -263950.28 | 2015-12-18 15:11 | 2021-01-31 | 2016-01-01
75084 | SG000336F | SG336SW | SG DEE DMS ADMS - Software | 239604.15 |  | 239604.15 |  |  | 380926.16 | 1049863.37 | -668937.21 | 2016-09-06 17:51 | 2021-04-01 | 2016-09-01
75084 | SG000336F | SG336OUA | SG Oracle Utilities Analytics Softw | 15011.61 |  | 15011.61 |  |  | 15011.61 | 0 | 15011.61 | 2018-07-30 10:48 | 2020-04-30 | 2018-08-01
75084 | SG000601F | SG601SW | DEE ADP Software - 601 | -1377.3 |  | -1377.3 |  |  | 19002.06 | 42090 | -23087.94 | 2017-06-21 17:55 | 2022-06-01 | 2017-06-01
75084 | SGEAMIOCF | SG305SVRS | SG DEE OpenWay Ops Center Servers | 5116.68 |  | 5116.68 |  |  | 24831.1 | 5323.07 | 19508.03 | 2016-09-06 11:56 | 2020-03-31 | 2016-09-01
75084 | SGEAMIOCF | SG305SW | SG DEE OpenWay Ops Center Software | 41490.52 |  | 41490.52 |  |  | 141142.85 | 189544.12 | -48401.27 | 2016-08-01 10:09 | 2020-03-31 | 2016-08-01
75084 | DKY2199 | D2199DL3 | AM 21607381 Hebron | 6848.86 |  | 6848.86 |  |  | 9979.21 | 250919.99 | -240940.78 | 2017-06-27 13:39 | 2020-03-31 | 2017-11-01
75084 | DKY2199 | D2199DL2 | AM 21607299 Hebron - DKY2199 | 198818.28 |  | 198818.28 |  |  | 203687.66 | 238000.64 | -34312.98 | 2017-06-27 13:32 | 2020-03-31 | 2017-07-01
75084 | DKY2199 | D2199DL4 | AM 21607440 Hebron | 764.63 |  | 764.63 |  |  | 764.63 | 41400.28 | -40635.65 | 2017-06-27 13:44 | 2019-10-31 | 2018-03-01
75084 | DKY2199 | D2199DL1 | AM 21606995 Hebron | 37254.63 |  | 37254.63 |  |  | 37906.5 | 65607.29 | -27700.79 | 2017-06-27 13:20 | 2019-11-01 | 2017-12-01 | 2019-09-28
75084 | DKY2016 | D2016DS1 | Donaldson TB 3 - DKY2016 | 613816.55 |  | 613816.55 |  |  | 684660.73 | 4019811 | -3335150.27 | 2017-07-18 07:20 | 2019-12-27 | 2017-08-01
75084 | DKY2016 | D2016DS2 | Donaldson TB 4 - DKY2016 | 454783.89 |  | 454783.89 |  |  | 493027.87 | 3960624 | -3467596.13 | 2017-07-18 07:32 | 2020-01-16 | 2017-08-01
75084 | DKY2016 | MX2175246 | Donaldson 48 Ln Ext - DKY2016 | 549741.28 |  | 549741.28 |  |  | 564811.87 | 162040.89 | 402770.98 | 2017-10-12 12:00 | 2020-01-02 | 2017-10-01
75084 | DKY2016 | MX9917129 | Donaldson 48 UG Exits Conduit - DKY | 155061.12 |  | 155061.12 |  |  | 155061.12 | 0 | 155061.12 | 2018-09-25 14:02 | 2019-12-26 | 2018-11-01
75084 | DKY2016 | MX0265492 | De-energize Segment Circuit 41 - DK | 1212.27 |  | 1212.27 |  |  | 1212.27 | 0 | 1212.27 | 2018-11-09 14:02 | 2020-10-30 | 2018-12-01
75084 | DKY2016 | MX2175719 | Donaldson 46 Ln Ext - DKY2016 | 83483.25 |  | 83483.25 |  |  | 83483.25 | 147197.24 | -63713.99 | 2017-10-12 14:01 | 2019-06-01 | 2017-10-01 | 2018-12-24
75084 | DKY2016 | MX9916539 | Donaldson 46 UG Exits Conduit - DKY | 360.43 |  | 360.43 |  |  | 360.43 | 5502.55 | -5142.12 | 2018-09-25 14:02 | 2019-09-01 | 2018-10-01 | 2019-05-29
75084 | 75084IK | KOUTUG | Outage Related UG Cap Replacements | 882141.52 |  | 882141.52 |  |  | 1360731.15 | 93 | 1360638.15 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOTT | Pothead Termination | 71649.46 |  | 71649.46 |  |  | 137239.52 | 93 | 137146.52 | 2017-03-27 12:34 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOH | Non-Emergency OH Corrective Replace | -180229.6 |  | -180229.6 |  |  | -175520.9 | 93 | -175613.9 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEOH | Emergency OH Corrective Replacement | 186606.02 |  | 186606.02 |  |  | 191209.99 | 93 | 191116.99 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KPOLIR | Non Emerg Pole Replace Insp Based | 307070.52 |  | 307070.52 |  |  | 355508.73 | 93 | 355415.73 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPDMCPU | Public Damage UG Capital Replacemnt | -57954.52 |  | -57954.52 |  |  | -53236.68 | 93 | -53329.68 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRIOTCO | OH Imprvmnt From PQRI Outage Invest | 117604.79 |  | 117604.79 |  |  | 150984.02 | 93 | 150891.02 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLCM | Reactive Pole Replacements | 350546 |  | 350546 |  |  | 407833.23 | 93 | 407740.23 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KPPL | Stub Pole Removal Only | 12918 |  | 12918 |  |  | 12970.96 | 2 | 12968.96 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KCAPAUTO | Capacitor Automation Upgrade | 428570.96 |  | 428570.96 |  |  | 428570.96 | 93 | 428477.96 | 2017-03-24 15:35 | 2067-12-31 | 2018-01-01
75084 | 75084IK | KLPF | Line Patrol Follow Up | 713872.9 |  | 713872.9 |  |  | 880231.95 | 93 | 880138.95 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTR1PH | Single PH Transformer Replace Dry | 18663.52 |  | 18663.52 |  |  | 19964.21 | 93 | 19871.21 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRUCSM | UG Primary Small Cable Replacement | 113757.12 |  | 113757.12 |  |  | 125154.34 | 93 | 125061.34 | 2017-03-27 14:22 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCUG | Non-Emergency UG Corrective Repl | 35507.54 |  | 35507.54 |  |  | 35786.61 | 93 | 35693.61 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KSMF | Capital Replacements from SMEI Insp | 5534.34 |  | 5534.34 |  |  | 5534.34 | 93 | 5441.34 | 2017-03-27 14:35 | 2067-12-31 | 2018-03-01
75084 | 75084IK | KCBLDT | UG Cable Replacement Dwntn Network | 14138.13 |  | 14138.13 |  |  | 14138.13 | 93 | 14045.13 | 2017-03-24 15:38 | 2067-12-31 | 2018-10-01
75084 | 75084IK | KRRR | Recloser Replacements | 458020.15 |  | 458020.15 |  |  | 464829.05 | 96 | 464733.05 | 2017-03-27 13:10 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRIOTCU | UG Imprvmnt From PQRI Outage Invest | 2937.2 |  | 2937.2 |  |  | 23975.66 | 93 | 23882.66 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCIPOH | C&I Customer Additions OH | 1476818.49 |  | 1476818.49 |  |  | 2089321.46 | 93 | 2089228.46 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLEIR | Emergency Pole Replace Insp Based | 25909.19 |  | 25909.19 |  |  | 30333.69 | 93 | 30240.69 | 2017-03-27 12:25 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRXR | Transformer Retrofit | 225136.51 |  | 225136.51 |  |  | 225136.51 | 84 | 225052.51 | 2017-03-27 14:28 | 2067-12-31 | 2017-11-01
75084 | 75084IK | KCMCEUG | Emergency UG Corrective Replacement | 128224.75 |  | 128224.75 |  |  | 129278.49 | 93 | 129185.49 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRFS | Circuit Sectionalization | 134025.58 |  | 134025.58 |  |  | 134025.58 | 95 | 133930.58 | 2017-03-27 12:39 | 2067-12-31 | 2018-02-01
75084 | 75084IK | MX8683892 | Declared Circuit - Donaldson (55) 5 | 3877.66 |  | 3877.66 |  |  | 3877.66 | 49876.34 | -45998.68 | 2018-09-27 14:02 | 2020-06-30 | 2018-12-01
75084 | 75084IK | KDLS | Dline Switch Replacements | 63312.16 |  | 63312.16 |  |  | 63312.16 | 70 | 63242.16 | 2017-03-27 11:53 | 2067-12-31 | 2018-02-01
75084 | 75084IK | MX0920154 | MXCONV-Declared Circuits Kenton 46 | 304044.11 |  | 304044.11 |  |  | 304044.11 | 118477.7 | 185566.41 | 2018-03-14 18:02 | 2020-05-31 | 2018-06-01
75084 | 75084IK | KRSOH | Residential Cust Adds Single Fam OH | 1069179.59 |  | 1069179.59 |  |  | 1667876.88 | 93 | 1667783.88 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KSTMOH | OH Capital Replacement Due to Storm | 76671.67 |  | 76671.67 |  |  | 83299.87 | 93 | 83206.87 | 2017-03-27 14:40 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KRTP1PH | Single PH Transformer Replac Leaker | 2332.4 |  | 2332.4 |  |  | 2332.4 | 93 | 2239.4 | 2017-03-27 13:17 | 2067-12-31 | 2018-07-01
75084 | 75084IK | KPDMCAP | Public Damage OH Capital Replacemen | 102656.38 |  | 102656.38 |  |  | 159138.71 | 80 | 159058.71 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KOTV | Cap Oil to Vac Changeout | 26631.78 |  | 26631.78 |  |  | 26631.78 | 93 | 26538.78 | 2017-03-27 12:11 | 2067-12-31 | 2018-02-01
75084 | 75084IK | KOUTOH | Outage Related OH Cap Replacements | 601479.67 |  | 601479.67 |  |  | 728286.83 | 93 | 728193.83 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01
75084 | 75084IK | MX0675382 | Westpack Customer Station | 1019.09 |  | 1019.09 |  |  | 1019.09 | 10800.23 | -9781.14 | 2017-12-15 14:01 | 2021-03-31 | 2018-03-01
75084 | 75084IK | KRUCSEC | UG Sec/Service Cable Replacement | 6658.43 |  | 6658.43 |  |  | 6658.43 | 93 | 6565.43 | 2017-03-27 13:33 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRUPOH | Residential Customer Upgrade OH | 340417.18 |  | 340417.18 |  |  | 341992.98 | 93 | 341899.98 | 2017-03-27 14:26 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KCIUPOH | C&I Customer Upgrade OH | -403.96 |  | -403.96 |  |  | -3339.38 | 93 | -3432.38 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01
75084 | 75084IK | MX1848383 | MXCONV-Capacitor Automation MT. ZIO | 42182.39 |  | 42182.39 |  |  | 42182.39 | 57824.65 | -15642.26 | 2018-03-12 14:01 | 2018-10-17 | 2018-08-01
75084 | 75084IK | KRMOH | Residential Cust Adds Multi Fam OH | 17843.79 |  | 17843.79 |  |  | 26270.11 | 93 | 26177.11 | 2017-03-27 13:07 | 2067-12-31 | 2017-08-01
75084 | 75084IK | MX9127121 | JT-E- TRAEMORE PH A | -6289.75 |  | -6289.75 |  |  | -6289.75 | 88590.34 | -94880.09 | 2018-07-17 14:02 | 2019-10-11 | 2018-09-01
75084 | 75084IK | MX7639718 | MXCONV-Upgrade Distri Transformer S | 943.02 |  | 943.02 |  |  | 943.02 | 13028.17 | -12085.15 | 2018-03-19 10:01 | 2020-07-30 | 2018-03-01
75084 | 75084IK | KRTXO | Overhead Transformer Replacement | 13776.5 |  | 13776.5 |  |  | 17496.73 | 93 | 17403.73 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEDT | Emerg DTUG Corrective Replacements | 27040.33 |  | 27040.33 |  |  | 27040.33 | 93 | 26947.33 | 2017-03-24 15:47 | 2067-12-31 | 2018-06-01
75084 | 75084IK | KCMCDT | Non-Emerg DTUG Corrective Replace | 371.36 |  | 371.36 |  |  | 371.36 | 93 | 278.36 | 2017-03-24 15:45 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KUGCBINJ | UG Cable Injection | 67986.44 |  | 67986.44 |  |  | 244250 | 95 | 244155 | 2017-03-27 14:37 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRTP3PH | Three PH Transformer Replace Leaker | 42813.21 |  | 42813.21 |  |  | 42813.21 | 95 | 42718.21 | 2017-03-27 13:19 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRTXLF | Transformer Livefront Replace | 69220.19 |  | 69220.19 |  |  | 69220.19 | 72691.76 | -3471.57 | 2017-07-27 15:37 | 2067-12-31 | 2018-10-01
75084 | 75084IK | KRCR | Capacitor Replacements & Assoc UOP | 20708.22 |  | 20708.22 |  |  | 21683.36 | 90 | 21593.36 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOWS | Secondary OH Wire Corr Replacement | 2141.06 |  | 2141.06 |  |  | 2141.06 | 93 | 2048.06 | 2017-03-27 11:47 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KCMCOWP | Primary OH Wire Corr Replacement | 460.61 |  | 460.61 |  |  | 460.61 | 93 | 367.61 | 2017-03-27 11:33 | 2067-12-31 | 2018-11-01
75084 | 75084IK | MX9998915 | URD Wilder 41 | 15940.53 |  | 15940.53 |  |  | 15940.53 | 0 | 15940.53 | 2018-04-27 10:01 | 2020-07-30 | 2018-05-01
75084 | 75084IK | MX9998916 | Transformer Replacement Kenton 41 | 230.69 |  | 230.69 |  |  | 230.69 | 0 | 230.69 | 2018-03-26 10:02 | 2020-11-30 | 2018-05-01
75084 | 75084IK | KRGR | Regulator replacements | 15681.75 |  | 15681.75 |  |  | 19925.24 | 0 | 19925.24 | 2017-07-27 13:27 | 2067-12-31 | 2017-11-01
75084 | 75084IK | MX9214707 | SOG Circuit Segmentation Batavia 4 | 84.02 |  | 84.02 |  |  | 84.02 | 0 | 84.02 | 2018-12-13 14:01 | 2019-12-31 | 2018-12-01
75084 | 75084IK | KSVDTUG | Instl/Repl Pump W Stop Valve in Vau | 30839.04 |  | 30839.04 |  |  | 30839.04 | 0 | 30839.04 | 2017-12-07 11:41 | 2068-03-31 | 2018-08-01
75084 | 75084IK | KROC | OH Deteriorated Conductor Replace | 768.07 |  | 768.07 |  |  | 768.07 | 0 | 768.07 | 2018-07-11 10:07 | 2067-12-31 | 2018-11-01
75084 | 75084IK | KET135853 | DET 10135853 Hands 44 310 | 422753.93 |  | 422753.93 |  |  | 725097.46 | 656630.49 | 68466.97 | 2016-11-07 10:03 | 2020-09-28 | 2016-12-01 | 2019-11-03
75084 | 75084IK | MX2140942 | UG LINE EXT - 1730 LAKELAND PARK DR | 15592.01 |  | 15592.01 |  |  | 15592.01 | 56759.24 | -41167.23 | 2017-12-13 10:01 | 2018-01-05 | 2018-01-01 | 2018-05-08
75084 | 75084IK | MX8285098 | INFRASTRUCTIURE FOR SUBDIVISION D | 13311.45 |  | 13311.45 |  |  | 13311.45 | 14166.09 | -854.64 | 2018-05-09 18:05 | 2019-06-01 | 2018-05-01 | 2019-01-20
75084 | 75084IK | MX0705683 | TDSIC UPGRADE OF CAPACITORS BY ADDI | 23921.88 |  | 23921.88 |  |  | 23921.88 | 63278.29 | -39356.41 | 2018-03-20 18:02 | 2018-07-31 | 2018-06-01 | 2018-11-24
75084 | 75084IK | MX1281917 | INFRASTRUCTIURE FOR SUBDIVISION D | 8298.68 |  | 8298.68 |  |  | 8298.68 | 8191.98 | 106.7 | 2017-11-03 14:01 | 2019-01-31 | 2018-04-01 | 2018-12-19
75084 | 75084IK | MX0090259 | MXCONV-Transformer Retrofit YORK 42 | 30958.02 |  | 30958.02 |  |  | 30958.02 | 42782.63 | -11824.61 | 2018-04-18 14:01 | 2018-12-28 | 2018-06-01 | 2018-11-09
75084 | 75084IK | MX7691568 | Circuit Segementation Self Healing | 7885.35 |  | 7885.35 |  |  | 7885.35 | 48280.72 | -40395.37 | 2018-05-25 14:02 | 2019-07-01 | 2018-06-01 | 2019-08-13
75084 | 75084IK | MX9579446 | JT- E - Arcadia Highlands Phase 4 | -934 |  | -934 |  |  | -934 | 12695.07 | -13629.07 | 2018-08-24 18:04 | 2019-08-30 | 2018-09-01 | 2019-07-14
75084 | 75084IK | MX0924912 | MXCONV-JT- E TRIPLE CROWN SUBD SEC | 53433.15 |  | 53433.15 |  |  | 46630.76 | 213849.76 | -167219 | 2017-11-03 14:01 | 2018-03-01 | 2017-11-01 | 2018-05-07
75084 | 75084IK | MX7740641 | JT, E-AOSTA VALLEY PH. 6 | 13151.69 |  | 13151.69 |  |  | 13151.69 | 19174.35 | -6022.66 | 2018-04-11 18:02 | 2019-06-01 | 2018-04-01 | 2018-12-27
75084 | 75084IK | MX0705495 | INSTALLATION OF SELF HEALING NEWWOR | 58116.25 |  | 58116.25 |  |  | 58116.25 | 55214.64 | 2901.61 | 2018-02-14 10:01 | 2019-06-01 | 2018-03-01 | 2019-01-08
75084 | 75084IK | MX7691570 | Circuit Segmentation Self Healing B | 33683.02 |  | 33683.02 |  |  | 33683.02 | 44183.81 | -10500.79 | 2018-06-26 18:03 | 2019-07-30 | 2018-07-01 | 2019-05-29
75084 | 75084IK | MX0090254 | MXCONV-Transformer Retrofit LIMABUR | 24818.59 |  | 24818.59 |  |  | 24818.59 | 52534.55 | -27715.96 | 2018-04-17 14:01 | 2019-06-01 | 2018-06-01 | 2018-11-22
75084 | 75084IK | MX7691569 | Circuit Segementation Self Healing | 29503.31 |  | 29503.31 |  |  | 29503.31 | 39899.12 | -10395.81 | 2018-06-25 10:02 | 2019-12-29 | 2018-07-01 | 2019-10-31
75084 | 75084IK | MX1236245 | INFRASTRUCTIURE FOR SUBDIVISION D | 49340.63 |  | 49340.63 |  |  | 46916.63 | 30202.98 | 16713.65 | 2017-11-03 14:01 | 2018-06-01 | 2017-11-01 | 2018-07-12
75084 | 75084IK | MX1655106 | INFRASTRUCTIURE FOR SUBDIVISION D | 22616.14 |  | 22616.14 |  |  | 22616.14 | 12941.13 | 9675.01 | 2017-11-03 14:01 | 2018-05-18 | 2018-01-01 | 2018-06-15
75084 | 75084IK | MX7691571 | Circuit Segmentation Self Healing B | 31198.08 |  | 31198.08 |  |  | 31198.08 | 58415 | -27216.92 | 2018-06-27 10:02 | 2019-07-30 | 2018-07-01 | 2019-06-11
75084 | 75084IK | MX7743111 | INFRASTRUCTIURE FOR SUBDIVISION D | 15959.4 |  | 15959.4 |  |  | 15959.4 | 26179.83 | -10220.43 | 2018-03-26 14:02 | 2018-11-24 | 2018-05-01 | 2018-11-26
75084 | 75084IK | MX7691573 | Circuit Segmentation Self Healing W | 30321.69 |  | 30321.69 |  |  | 30321.69 | 48785.98 | -18464.29 | 2018-06-19 10:01 | 2019-07-30 | 2018-07-01 | 2019-08-18
75084 | 75084IK | MX7691572 | Circuit Segmentation Self Healing B | 35323.57 |  | 35323.57 |  |  | 35323.57 | 43667.13 | -8343.56 | 2018-06-29 14:03 | 2019-08-14 | 2018-07-01 | 2019-05-12
75084 | 75084IK | MX8683121 | Declared Circuit - Limaburg (189) 1 | 3709 |  | 3709 |  |  | 3709 | 8916.15 | -5207.15 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-05-27
75084 | 75084IK | MX0169713 | MXCONV-Circuit Sectionalization Bea | 27556.05 |  | 27556.05 |  |  | 27556.05 | 100852.4 | -73296.35 | 2017-11-03 14:01 | 2018-06-30 | 2018-03-01 | 2018-08-21
75084 | 75084IK | MX0090253 | MXCONV-Transformer Retrofit KENTON | 47478.24 |  | 47478.24 |  |  | 47478.24 | 66741.76 | -19263.52 | 2018-04-18 10:02 | 2019-06-01 | 2018-06-01 | 2019-01-21
75084 | 75084IK | MX2345743 | JT, E-EAGLE RIDGE PH. 2 PT. 2 | 10318.22 |  | 10318.22 |  |  | 8544.22 | 13650.65 | -5106.43 | 2017-12-18 14:01 | 2018-08-31 | 2017-12-01 | 2018-08-02
75084 | 75084IK | MX7880714 | JT, E-WALTON POINTE PHASE 3 | -2193 |  | -2193 |  |  | -2193 | 24220.88 | -26413.88 | 2018-04-11 14:01 | 2019-07-31 | 2018-06-01 | 2019-07-21
75084 | 75084IK | MX7972270 | MAJOR IMPROVE DIST RELIABLITY LINE | 96116.38 |  | 96116.38 |  |  | 96116.38 | 87518.4 | 8597.98 | 2018-07-24 14:02 | 2019-09-02 | 2018-08-01 | 2019-05-10
75084 | 75084IK | MX7997177 | JT, E-TUSCANY PHASE B SECTION 1 | -17526 |  | -17526 |  |  | -17526 | 78395.14 | -95921.14 | 2018-04-12 10:01 | 2019-07-30 | 2018-06-01 | 2019-06-02
75084 | 75084IK | MX1675871 | INFRASTRUCTIURE FOR SUBDIVISION D | 27727.75 |  | 27727.75 |  |  | 25233.75 | 28275 | -3041.25 | 2017-11-03 14:01 | 2018-03-01 | 2017-12-01 | 2018-06-12
75084 | 75084IK | MX8684198 | Declared Circuit - Hebron (152) 152 | 3059.87 |  | 3059.87 |  |  | 3059.87 | 14209.12 | -11149.25 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-09-17
75084 | 75084IK | MX6843545 | INFRASTRUCTIURE FOR SUBDIVISION D | 16480.6 |  | 16480.6 |  |  | 16480.6 | 17816 | -1335.4 | 2018-01-04 14:01 | 2019-06-22 | 2018-03-01 | 2019-03-19
75084 | 75084IK | MX7838790 | JT, E-ASHLEY OAKS SUBDIVISION | -1065.25 |  | -1065.25 |  |  | -1065.25 | 9052.39 | -10117.64 | 2018-04-11 14:01 | 2019-11-29 | 2018-06-01 | 2019-06-30
75084 | 75084IK | MX1948881 | SAWGRASS SUBDIVISION PHASE A | 36926.46 |  | 36926.46 |  |  | 36926.46 | 36830.14 | 96.32 | 2017-11-03 14:01 | 2019-03-31 | 2018-01-01 | 2018-09-24
75084 | 75084IK | MX8735624 | JT-E- HARMONY PH.D PT.1 | -2096.25 |  | -2096.25 |  |  | -2096.25 | 22271.65 | -24367.9 | 2018-08-03 10:02 | 2019-04-18 | 2018-08-01 | 2019-06-10
75084 | 75084IK | MX8684114 | Declared Circuit - Hebron (152) 152 | 2635.66 |  | 2635.66 |  |  | 2635.66 | 3958.41 | -1322.75 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-07-30
75084 | 75084IK | MX2163149 | TED BUSHELMAN BLVD | 94071.95 |  | 94071.95 |  |  | 94071.95 | 96365.48 | -2293.53 | 2017-12-13 10:01 | 2018-01-19 | 2018-02-01 | 2018-05-21
75084 | 75084IK | MX1691827 | INFRASTRUCTIURE FOR SUBDIVISION D | 12618.8 |  | 12618.8 |  |  | 11177.8 | 12916.08 | -1738.28 | 2017-11-03 14:01 | 2018-07-02 | 2017-11-01 | 2018-09-04
75084 | 75084IK | MX0090256 | MXCONV-Transformer Retrofit SILVER | 49023.48 |  | 49023.48 |  |  | 49023.48 | 120339.21 | -71315.73 | 2018-09-17 10:02 | 2019-06-01 | 2018-09-01 | 2019-01-25
75084 | 75084IK | MX7708497 | JT, E-RESERVE AT MEADOWOOD | 20477.72 |  | 20477.72 |  |  | 20477.72 | 50046.7 | -29568.98 | 2018-03-20 18:02 | 2019-06-28 | 2018-05-01 | 2019-05-28
75084 | 75084IK | MX6839574 | COMMERCIAL PRIMARY/SECONDARY/SVC | 200584.09 |  | 200584.09 |  |  | 200584.09 | 168944.61 | 31639.48 | 2018-10-24 18:03 | 2019-07-01 | 2018-11-01 | 2019-02-28
75084 | 75084IK | MX0004925 | INFRASTRUCTIURE FOR SUBDIVISION D | -4214 |  | -4214 |  |  | -4214 | 32901.06 | -37115.06 | 2018-10-24 18:03 | 2019-11-29 | 2018-11-01 | 2019-07-29
75084 | 75084IK | MX8215200 | JT, E-AUDUBON FOREST SUBDIVISION | -3757 |  | -3757 |  |  | -3757 | 24640.12 | -28397.12 | 2018-05-01 14:01 | 2019-12-01 | 2018-12-01 | 2019-07-30
75084 | 75084IK | MX9481816 | INFRASTRUCTIURE FOR SUBDIVISION D | -1462 |  | -1462 |  |  | -1462 | 12428.57 | -13890.57 | 2018-09-26 10:02 | 2019-08-31 | 2018-09-01 | 2019-06-24
75084 | 75084IK | MX8684039 | Declared Circuit - Oakbrook (210) 2 | 4137.01 |  | 4137.01 |  |  | 4137.01 | 11313.35 | -7176.34 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-07-23
75084 | SG000440F | SGRFSKY | DEK Sectionalization | 60445.19 |  | 60445.19 |  |  | 60496.86 | 83 | 60413.86 | 2016-05-16 10:23 | 2025-12-31 | 2017-01-01
75084 | DKY2017 | D2017DL5 | RUSD Donaldson Hwy Retire - DKY2017 | 7557.68 |  | 7557.68 |  |  | 13092.03 | 12270.87 | 821.16 | 2017-04-25 11:29 | 2020-05-31 | 2017-12-01
75084 | DKY2017 | D2017DL3 | AM 21113304 Davidson Hwy - DKY2017 | -263.13 |  | -263.13 |  |  | 3002.6 | 204529.81 | -201527.21 | 2017-04-17 15:00 | 2019-12-30 | 2017-07-01
75084 | DKY2017 | D2017DL1 | AM 21113152 Donaldson Hwy | 32501.72 |  | 32501.72 |  |  | 73503.6 | 0 | 73503.6 | 2017-04-17 14:46 | 2020-03-31 | 2017-04-01
75084 | DKY2019 | MX2240021 | Buffington 43 Ln Ext - DKY2019 | 18228.74 |  | 18228.74 |  |  | 18228.74 | 108589.89 | -90361.15 | 2017-10-18 18:02 | 2020-03-30 | 2018-01-01
75084 | DKY2019 | MX2239929 | Buffington 43 UB Pt 2 - DKY2019 | 10746.47 |  | 10746.47 |  |  | 10746.47 | 84712.23 | -73965.76 | 2017-10-18 18:02 | 2020-01-29 | 2018-01-01
75084 | DKY2019 | MX2239881 | Dixie 46 Ln Ext - DKY2019 | 13052.7 |  | 13052.7 |  |  | 13052.7 | 183148.71 | -170096.01 | 2017-10-18 18:02 | 2019-12-31 | 2018-01-01
75084 | DKY2019 | MX2239971 | Dixie 45 Ln Ext - DKY2019 | 26203.9 |  | 26203.9 |  |  | 26203.9 | 145406.88 | -119202.98 | 2017-10-18 18:02 | 2020-03-30 | 2018-01-01
75084 | DKY2019 | MX1269760 | Buffington 43 UB PT 1 - DKY2019 | 7129.39 |  | 7129.39 |  |  | 7129.39 | 20243.51 | -13114.12 | 2018-03-19 14:01 | 2020-03-30 | 2018-04-01
75084 | DKY2019 | D2019DL2 | AM 21269675 Rbld Industrial Rd West | 13751.41 |  | 13751.41 |  |  | 29930.9 | 0 | 29930.9 | 2017-05-09 09:46 | 2020-03-31 | 2017-05-01
75084 | DKY2019 | D2019DL3 | AM 21269760 Rbld Industrial Rd East | 3859.66 |  | 3859.66 |  |  | 13038.73 | 0 | 13038.73 | 2017-05-09 09:51 | 2020-03-31 | 2017-07-01
75084 | DKY2019 | MX2240623 | Buffington 42 UB Trnsfr - DKY2019 | 10833.65 |  | 10833.65 |  |  | 10833.65 | 0 | 10833.65 | 2017-10-18 18:02 | 2020-03-30 | 2018-01-01
75084 | DKY2019 | D2019DL1 | Dixie 45 46 Exits - DKY2019 | 20470.41 |  | 20470.41 |  |  | 21183.79 | 263109.52 | -241925.73 | 2017-05-09 09:41 | 2019-11-29 | 2017-07-01 | 2019-10-03
75084 | TKY1935 | T1935DS1 | Hebron XTR Rel Rpl - TKY1935 | 260423.73 |  | 260423.73 |  |  | 262660.13 | 342079 | -79418.87 | 2017-07-13 14:02 | 2020-02-11 | 2017-11-01
75084 | TKY1695 | T1695TS2 | Kenton F966 Rel Repl - TKY1695 | 6355.04 |  | 6355.04 |  |  | 111199.64 | 352819 | -241619.36 | 2016-10-07 18:03 | 2020-04-18 | 2016-12-01
75084 | TKY1695 | T1695TS1 | Buffington F966 CB Rel Repl - TKY16 | 78507.71 |  | 78507.71 |  |  | 494750.59 | 1153424 | -658673.41 | 2016-10-07 18:03 | 2020-02-24 | 2016-10-01
75084 | TKY1695 | T1695TS3 | Villa F966 Rel Repl - TKY1695 | -115877.84 |  | -115877.84 |  |  | -3509.82 | 356799 | -360308.82 | 2016-10-07 18:03 | 2019-08-06 | 2016-12-01 | 2017-03-25
75084 | KUCF61121 | KUC261121 | UG 10261121 Villa 44 | -943.48 |  | -943.48 |  |  | 1751.25 | 131529.73 | -129778.48 | 2017-04-11 14:03 | 2019-06-30 | 2017-06-01
75084 | SG000459F | SG459FB01 | 2018 Midwest Fiber Activation | 13354.32 |  | 13354.32 |  |  | 13354.32 | 37132 | -23777.68 | 2018-02-08 16:47 | 2019-03-31 | 2018-02-01
75084 | SG000459F | SG459FB02 | 2018 Midwest Fiber Activation | 2613.7 |  | 2613.7 |  |  | 2613.7 | 37132 | -34518.3 | 2018-02-08 16:57 | 2019-03-31 | 2018-02-01
75084 | SG000223F | SG223SW | DEE Transmission Health & Risk Mgt | 82246.59 |  | 82246.59 |  |  | 280630.63 | 1016639 | -736008.37 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01
75084 | SG000732F | SG732BTR | SG DEK Battery Replacement | 75700.55 |  | 75700.55 |  |  | 75700.55 | 33850 | 41850.55 | 2017-10-11 15:39 | 2026-03-31 | 2018-02-01
75084 | SG000732F | SG732TR01 | DEK Towers & Shelters - Verona | 3635.42 |  | 3635.42 |  |  | 3635.42 | 968336.2 | -964700.78 | 2018-09-11 15:00 | 2020-03-31 | 2018-09-01
75084 | SG000776F | SG776OPS | 2018 Transport Terminal Optical EOL | 19337.78 |  | 19337.78 |  |  | 19337.78 | 371480 | -352142.22 | 2018-02-14 12:38 | 2019-03-31 | 2018-03-01
75084 | SG000776F | SG776MTR | 2018 Transport Terminal Optical EOL | 329541 |  | 329541 |  |  | 329541 | 1 | 329540 | 2018-02-15 09:50 | 2019-06-30 | 2018-03-01
75084 | SG000438F | SGSELFKY | DEK Segmentation & Automation | 73554.43 |  | 73554.43 |  |  | 73978.13 | 1 | 73977.13 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01
75084 | SG000438F | SG438LIC | SG DEK YFA Device Licenses | 45065.1 |  | 45065.1 |  |  | 45065.1 | 8250 | 36815.1 | 2018-06-11 10:54 | 2020-03-31 | 2018-07-01
75084 | 75084HW | KHWYR | Highway Relocations Reimb | 36407.1 |  | 36407.1 |  |  | 105544.91 | 80 | 105464.91 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01
75084 | 75084HW | MX9624173 | Ri-I-71/I-75 & KY 536 Inneerchange | 2616.02 |  | 2616.02 |  |  | 2616.02 | 142487.26 | -139871.24 | 2018-09-06 14:02 | 2020-03-29 | 2018-09-01
75084 | 75084HW | KCOU | Make Ready Other Util Attachments | 272135.05 |  | 272135.05 |  |  | 494304.23 | 91 | 494213.23 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01
75084 | 75084HW | KCRFN | Customer Requested Mods Nonreimb | 40632.28 |  | 40632.28 |  |  | 40632.28 | 80 | 40552.28 | 2017-03-24 15:19 | 2067-12-31 | 2018-06-01
75084 | 75084HW | KCRFR | Customer Requested Mods Reimb | -12059.47 |  | -12059.47 |  |  | -11908.33 | 98 | -12006.33 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01
75084 | 75084HW | KHWYN | Highway Relocations Nonreimb | 110900.59 |  | 110900.59 |  |  | 141195.08 | 80 | 141115.08 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01
75084 | 75084HW | MX9612876 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 4878.51 |  | 4878.51 |  |  | 4878.51 | 132976.53 | -128098.02 | 2018-08-28 10:02 | 2020-06-30 | 2018-09-01
75084 | 75084HW | MX1661647 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 36101.04 |  | 36101.04 |  |  | 36216.32 | 228.31 | 35988.01 | 2017-11-28 14:01 | 2020-07-30 | 2017-12-01
75084 | 75084HW | MX7090228 | RI-6th St Beautification, undergrou | 9554.53 |  | 9554.53 |  |  | 9554.53 | 150507.84 | -140953.31 | 2018-04-10 10:01 | 2020-03-23 | 2018-04-01
75084 | 75084HW | MX7090285 | RI-6th St Beautification, overhead | 12099.99 |  | 12099.99 |  |  | 12099.99 | 155930.4 | -143830.41 | 2018-04-10 10:01 | 2020-03-23 | 2018-04-01
75084 | 75084HW | MX9060418 | I-71 /I-75 & KY 536 Interchange (D | 33143.97 |  | 33143.97 |  |  | 33143.97 | 68431.55 | -35287.58 | 2018-07-12 14:02 | 2019-12-01 | 2018-07-01
75084 | 75084HW | KMODC | Other Capital Modifications | 8184.27 |  | 8184.27 |  |  | 8184.27 | 80 | 8104.27 | 2017-03-24 15:33 | 2067-12-31 | 2018-07-01
75084 | 75084HW | MX6295185 | RI-Ky 338 Reconstruction & Sidewalk | 87771.77 |  | 87771.77 |  |  | 87771.77 | 62118.25 | 25653.52 | 2018-02-09 14:01 | 2018-03-23 | 2018-02-01 | 2018-06-24
75084 | 75084HW | MX8360139 | MXCONV-RI-North Bend Road at World | 60124.13 |  | 60124.13 |  |  | 60124.13 | 59842.81 | 281.32 | 2018-05-07 18:02 | 2019-06-01 | 2018-05-01 | 2019-01-16
75084 | 75084HW | MX6295870 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 100926.05 |  | 100926.05 |  |  | 106065.94 | 83155.24 | 22910.7 | 2017-11-30 18:02 | 2019-06-01 | 2017-12-01 | 2019-05-21
75084 | 75084HW | MX6342340 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 141650.37 |  | 141650.37 |  |  | 143718.12 | 109582.18 | 34135.94 | 2017-11-28 14:01 | 2018-07-01 | 2017-12-01 | 2018-07-25
75084 | 75084HW | MX7752157 | RI-Amsterdam Rd Road Improvement | 794.9 |  | 794.9 |  |  | 794.9 | 163902.06 | -163107.16 | 2018-11-06 14:02 | 2019-09-02 | 2018-11-01 | 2019-07-28
75084 | SGEDMS3F | SGDMS3SW | DEE DMS 3.5 Upgrade - Software | 52154.9 |  | 52154.9 |  |  | 212553.45 | 210242 | 2311.45 | 2015-11-19 10:10 | 2021-01-31 | 2016-09-01
75084 | KECF20154 | KEC920154 | DEC 8920154 Kenton 46 | 8416.08 |  | 8416.08 |  |  | 31321.04 | 150467.62 | -119146.58 | 2015-10-23 10:05 | 2019-12-30 | 2016-09-01
75084 | CP18SUBK | MX8667739 | Marshall TB1 replace X0,1,2,3 Bushi | 5861.51 |  | 5861.51 |  |  | 5861.51 | 9204.03 | -3342.52 | 2018-06-05 14:02 | 2020-03-30 | 2018-08-01
75084 | CP18SUBK | MX8693329 | CAPITAL Richwood TB2 replace H2, X2 | 7376.76 |  | 7376.76 |  |  | 7376.76 | 9907.33 | -2530.57 | 2018-06-08 10:01 | 2020-03-30 | 2018-10-01
75084 | CP18SUBK | MX8693627 | CAPITAL Richwood TB3 replace X3 Bus | 2435.72 |  | 2435.72 |  |  | 2435.72 | 3280.81 | -845.09 | 2018-06-08 10:01 | 2020-03-30 | 2018-10-01
75084 | CP18SUBK | MX0093848 | CAPITAL Kenton TB3 replace one bad | 500.22 |  | 500.22 |  |  | 500.22 | 466.04 | 34.18 | 2018-10-09 14:02 | 2019-12-31 | 2018-11-01
75084 | CP18SUBK | MX0106047 | CAPITAL White Tower TB1 replace two | 1096.5 |  | 1096.5 |  |  | 1096.5 | 882.31 | 214.19 | 2018-10-10 14:02 | 2020-03-31 | 2018-11-01 | 2019-10-24
75084 | CP18SUBK | MX8593684 | CAPITAL Bellevue TB1 repl 13kV Arre | 1000.2 |  | 1000.2 |  |  | 1000.2 | 856.83 | 143.37 | 2018-06-01 10:01 | 2019-03-31 | 2018-06-01 | 2019-03-04
75084 | CP18SUBK | MX0076115 | CAPITAL Dixie TB2 replace one bad f | 523.84 |  | 523.84 |  |  | 523.84 | 466.04 | 57.8 | 2018-10-08 18:02 | 2020-03-31 | 2018-10-01 | 2019-10-24
75084 | CP18SUBK | MX0077066 | CAPITAL Crescent TB2 replace one ba | 600.31 |  | 600.31 |  |  | 600.31 | 447.05 | 153.26 | 2018-10-09 10:02 | 2020-03-31 | 2018-11-01 | 2019-10-24
75084 | CP18SUBK | MX0090746 | CAPITAL Bellevue TB1 replace one ba | 600.31 |  | 600.31 |  |  | 600.31 | 447.05 | 153.26 | 2018-10-09 14:02 | 2020-03-31 | 2018-11-01 | 2019-11-26
75084 | CP18SUBK | MX0088995 | CAPITAL Buffington TB7 replace one | 709.24 |  | 709.24 |  |  | 709.24 | 540.75 | 168.49 | 2018-10-09 14:02 | 2019-03-31 | 2018-11-01 | 2019-06-05
75084 | CP18SUBK | MX0089985 | CAPITAL Claryville TB1 replace one | 773.4 |  | 773.4 |  |  | 773.4 | 466.04 | 307.36 | 2018-10-09 14:02 | 2019-03-31 | 2018-11-01 | 2019-03-12
75084 | TKY2204 | T2204DS1 | Buffington Rcfgr 4_5 - TKY2204 | 86059.09 |  | 86059.09 |  |  | 86059.09 | 2109259 | -2023199.91 | 2018-05-02 10:01 | 2021-02-19 | 2018-06-01
75084 | KARF51805 | KAR851805 | LAR 10851805 Wilder 44 | 88269.03 |  | 88269.03 |  |  | 100485.13 | 313344.88 | -212859.75 | 2016-07-26 14:03 | 2019-10-21 | 2016-09-01
75084 | SG990151F | SRICVUGKY | GS DEK Targeted Underground Blanket | 1845.51 |  | 1845.51 |  |  | 2117.53 | 1 | 2116.53 | 2017-05-22 11:49 | 2050-12-31 | 2017-09-01
75084 | TLRKY | TLRKY01 | FIF P1 6763 Rpl 2 poles | 109315.55 |  | 109315.55 |  |  | 109315.55 | 36000 | 73315.55 | 2018-04-09 18:02 | 2018-11-21 | 2018-05-01 | 2018-11-01
75084 | TKY1791 | T1791DS1 | Villa TB2 and Bus 2 Swgr Rpl - TKY1 | 570890.89 |  | 570890.89 |  |  | 600695.51 | 3017308 | -2416612.49 | 2017-05-17 14:03 | 2020-02-25 | 2017-07-01
75084 | TKY1791 | T1791TS1 | Villa 69kV Bus 1 CCVT Rpl - TKY1791 | 296091.78 |  | 296091.78 |  |  | 300796.5 | 79695 | 221101.5 | 2017-05-17 14:03 | 2020-07-31 | 2017-08-01
75084 | TKY2128 | T2128TL1 | F966 Rcnfgr Villa Loop TL - TKY2128 | 12880.61 |  | 12880.61 |  |  | 12880.61 | 118357 | -105476.39 | 2017-05-30 14:04 | 2020-02-29 | 2018-02-01
75084 | TKY2128 | T2128TS1 | Villa-Inst 69 kV Ring Bus - TKY2128 | 746590.26 |  | 746590.26 |  |  | 765874.6 | 4045269 | -3279394.4 | 2017-05-30 14:04 | 2020-03-17 | 2017-08-01
75084 | 75084IL | KSLNOLE | Non Ole Street Light Replacements | 23971.09 |  | 23971.09 |  |  | 23971.09 | 58 | 23913.09 | 2017-03-28 09:41 | 2067-04-01 | 2018-02-01
75084 | 75084IL | KCAL | Area Light New Installs | -18434.78 |  | -18434.78 |  |  | 30973.64 | 98 | 30875.64 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KLEDSL | LED Street Light Retrofit | 390529.55 |  | 390529.55 |  |  | 391392.22 | 58 | 391334.22 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01
75084 | 75084IL | KSLRPL | Street Light Replacements | 51125.54 |  | 51125.54 |  |  | 51125.84 | 58 | 51067.84 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KALRPL | Area Light Replacements | 5949.77 |  | 5949.77 |  |  | 5537.76 | 58 | 5479.76 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01
75084 | 75084IL | KRUL | UG Cable Lighting Replacements | 2281.73 |  | 2281.73 |  |  | 2281.73 | 91 | 2190.73 | 2017-03-28 09:39 | 2067-04-01 | 2018-05-01
75084 | 75084IL | MX6293181 | Florence Lighting Upgrade Phase 1 | -185541.05 |  | -185541.05 |  |  | -185541.05 | 240125.13 | -425666.18 | 2018-03-12 14:01 | 2019-01-30 | 2018-03-01 | 2019-03-04
75084 | 75084IL | MX6293467 | Florence Lighting Upgrade Phase 2 | -257088.54 |  | -257088.54 |  |  | -257088.54 | 343744.48 | -600833.02 | 2018-03-12 14:01 | 2019-01-25 | 2018-04-01 | 2019-03-04
75084 | 75084IL | MX1977699 | BBB, Notre Dame Academy Lighti | 52921.1 |  | 52921.1 |  |  | 82350.84 | 61644.58 | 20706.26 | 2017-11-15 14:01 | 2018-04-03 | 2017-12-01 | 2018-06-03
75084 | 75084IL | MX6486641 | Florence Lighting Upgrade Phase 3 | -37286.2 |  | -37286.2 |  |  | -37286.2 | 66900.04 | -104186.24 | 2018-03-12 14:01 | 2018-09-28 | 2018-05-01 | 2019-01-29
75084 | 75084IL | MX7423928 | STREET LIGHT REMOVE/INSTALL | 90196.07 |  | 90196.07 |  |  | 90196.07 | 132816.68 | -42620.61 | 2018-08-20 10:03 | 2019-05-01 | 2018-10-01 | 2019-06-10
75084 | SG000468F | SG468MDM | SG DEK Next Gen Cellular | 96759.45 |  | 96759.45 |  |  | 96759.45 | 1684462.49 | -1587703.04 | 2017-10-10 12:47 | 2026-03-31 | 2018-01-01
75084 | KIAF05495 | KIA705495 | DA 10705495 Alexandria So | 1295.35 |  | 1295.35 |  |  | 5933.74 | 53637.18 | -47703.44 | 2017-01-04 10:04 | 2019-03-01 | 2017-04-01
75084 | KECF20153 | KEC920153 | DC 8920153 Bellevue 42 | 7500 |  | 7500 |  |  | 15889.54 | 298274.18 | -282384.64 | 2015-10-23 10:05 | 2019-07-31 | 2016-09-01
75084 | 75084VM | VDHAZPGKY | VDHAZPGKY | 352932.22 |  | 352932.22 |  |  | 352932.22 | 1 | 352931.22 | 2017-05-25 15:32 | 2050-12-31 | 2018-01-01
75084 | 75084VM | VDREMVCKY | VDREMVCKY | 239972.7 |  | 239972.7 |  |  | 239972.7 | 1 | 239971.7 | 2017-05-25 11:52 | 2050-12-30 | 2018-01-01
75084 | SG000586F | SGDLSKY | RUSD DEK D-Line Switch Replacement | 270454.92 |  | 270454.92 |  |  | 297700.88 | 94 | 297606.88 | 2016-12-19 11:23 | 2025-12-31 | 2017-05-01
75084 | DKY2134 | D2134DL2 | AM 21801679 Oakbrook 42 | 21954.87 |  | 21954.87 |  |  | 21954.87 | 529469.63 | -507514.76 | 2017-07-25 14:20 | 2019-12-31 | 2018-03-01
75084 | SG000794F | SG794DES | DEK Land Mobile Radio Design | 57671.02 |  | 57671.02 |  |  | 57671.02 | 3707866 | -3650194.98 | 2018-06-15 13:19 | 2025-03-01 | 2018-06-01
75084 | SG000435F | SGCAPATKY | DEK Cap Automation | 20101.11 |  | 20101.11 |  |  | 20402.41 | 83 | 20319.41 | 2016-05-16 10:15 | 2025-12-31 | 2017-01-01
75084 | SG000439F | SGGENSWKY | DEK Switchgear Upgrades-Automation | 3573.32 |  | 3573.32 |  |  | 3788.45 | 83 | 3705.45 | 2016-05-16 10:22 | 2025-12-31 | 2017-01-01
75084 | SG000744F | SG744MTR | DEK GridWAN | 2162.72 |  | 2162.72 |  |  | 2162.72 | 248821.93 | -246659.21 | 2018-05-25 13:28 | 2020-03-31 | 2018-07-01
75084 | SG000744F | SG744BLK | DEK GridWAN | 1647.46 |  | 1647.46 |  |  | 1647.46 | 248821.93 | -247174.47 | 2018-05-25 13:54 | 2020-03-31 | 2018-11-01
75084 | FARCOSSW | ARCOSSW | ARCOS System Outage Project | 46519.66 |  | 46519.66 |  |  | 46519.66 | 129249 | -82729.34 | 2018-06-10 21:10 | 2020-03-30 | 2018-07-01
75084 | TOUTKY | OUT69KY | KY T-line Emergency Repl on 69kV | 30131.72 |  | 30131.72 |  |  | 61388.56 | 6 | 61382.56 | 2017-01-17 10:23 | 2050-12-31 | 2017-01-01
75084 | TOUTKY | TOUTKY01 | Servc rest P1 Due to high winds on | 153006.74 |  | 153006.74 |  |  | 153006.74 | 18000 | 135006.74 | 2018-02-09 10:02 | 2021-03-01 | 2018-11-01
75084 | TOUTKY | TOUTKY04 | Auto Damage 966 Pole K107-106 Stub | 190231.51 |  | 190231.51 |  |  | 190231.51 | 42635.16 | 147596.35 | 2018-04-16 10:01 | 2018-10-29 | 2018-04-01 | 2018-11-01
75084 | TOUTKY | TOUTKY03 | Auto Damage 6761 Pole 5G-328 Stub P | 13129.8 |  | 13129.8 |  |  | 13129.8 | 18000 | -4870.2 | 2018-04-09 18:02 | 2019-09-01 | 2018-05-01 | 2019-02-27
75084 | PRTFA | KYPRTF2 | PRTOH P1 Cir 6763 HLP626 | 11437.8 |  | 11437.8 |  |  | 11437.8 | 27000 | -15562.2 | 2016-12-22 14:57 | 2021-03-31 | 2018-04-01
75084 | DKY2198 | MX7724805 | Constance 41 LN Ext PME at sub - DK | 5861.94 |  | 5861.94 |  |  | 5861.94 | 92830.61 | -86968.67 | 2018-03-20 18:02 | 2020-01-29 | 2018-06-01
75084 | DKY2198 | MX7724731 | Constance 41 Ln Ext Cable - DKY2198 | 106215.27 |  | 106215.27 |  |  | 106215.27 | 0 | 106215.27 | 2018-03-20 18:02 | 2019-12-29 | 2018-08-01
75084 | DKY2198 | MX7724526 | Constance 41 Ln Ext Pt1 - DKY2198 | 612022.48 |  | 612022.48 |  |  | 612022.48 | 951049.63 | -339027.15 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2018-07-27
75084 | DKY2198 | MX7724611 | Constance 41-43 LN Ext Pt II - DKY2 | 67641.31 |  | 67641.31 |  |  | 67641.31 | 186281.75 | -118640.44 | 2018-03-20 18:02 | 2019-12-29 | 2018-03-01 | 2019-12-05
75084 | DKY2198 | MX7724670 | Constance 41-43 LN Ext Pt III - DKY | 343502.77 |  | 343502.77 |  |  | 343502.77 | 778204.8 | -434702.03 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2019-08-04
75084 | TKY1901 | T1901TS1 | Buffington TB1 Rpl - TKY1901 | 268253.92 |  | 268253.92 |  |  | 268253.92 | 2785992 | -2517738.08 | 2017-12-14 15:58 | 2020-02-29 | 2018-02-01
75084 | TKY1901 | TKY190101 | Rpl TPU Relays for TB7 | 46234.04 |  | 46234.04 |  |  | 46234.04 | 205975 | -159740.96 | 2018-07-30 10:02 | 2021-03-01 | 2018-07-01
75084 | TKY1901 | T1901DS1 | Buffington Swgr Rpl - TKY1901 | 458386.63 |  | 458386.63 |  |  | 458386.63 | 3344657 | -2886270.37 | 2017-12-04 15:07 | 2020-01-25 | 2018-04-01
75084 | TKY2227 | T2227TL2 | F5967 Decoursey Pole Repl TL | 12257.22 |  | 12257.22 |  |  | 12257.22 | 6725687 | -6713429.78 | 2018-04-30 14:01 | 2025-10-13 | 2018-09-01
75084 | TKY2227 | T2227TL1 | F5967 Claryville Pole Repl TL | 5036.46 |  | 5036.46 |  |  | 5036.46 | 7186714 | -7181677.54 | 2018-04-30 14:01 | 2025-11-08 | 2018-09-01
75084 | SG000792F | SG792SW | SG DEE Gen Liab Claim Anlytic - 792 | 1687.26 |  | 1687.26 |  |  | 1687.26 | 22428.18 | -20740.92 | 2018-07-25 14:52 | 2019-03-31 | 2018-07-01
75084 | ICPRJDSTR | ICCONSTRT | Interconnection Capital Project | -4112.88 |  | -4112.88 |  |  | 1.1369e-13 | 1 | -1 | 2017-09-28 12:05 | 2030-09-30 | 2017-10-01
75084 | ICPRJDSTR | ICCONSTRD | Interconnection Capital Project | -4058.73 |  | -4058.73 |  |  | -4.5475e-13 | 1 | -1 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01
75084 | 75084 | KMTROWS | KY - Meters-AMI-Self Contained | 864.13 |  | 864.13 |  |  | 864.13 | 99863.96 | -98999.83 | 2018-11-02 18:04 | 2026-03-31 | 2018-12-01
75084 | 75084 | EMETERKY | Electric Meter Blanket | 821824.75 |  | 821824.75 |  |  | 2211423.08 | 295697.19 | 1915725.89 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01 | 2019-05-14
75084 | 75084 | MX2586486 | OLD TWENHOFEL MIDDLE SCHOOL | 14426.72 |  | 14426.72 |  |  | 14426.72 | 37465.22 | -23038.5 | 2018-01-09 14:01 | 2018-02-16 | 2018-01-01 | 2018-08-23
75084 | 75084 | MX1977353 | BBB - 8299 Dixie Hwy - Mubea | 53257.6 |  | 53257.6 |  |  | 53257.6 | 84405.85 | -31148.25 | 2018-01-09 10:01 | 2018-01-29 | 2018-01-01 | 2018-07-16
75084 | SG000795F | SG795SW | SG DEE Auto Mter Provisioning - 795 | 379.66 |  | 379.66 |  |  | 379.66 | 13121 | -12741.34 | 2018-07-03 13:02 | 2019-12-15 | 2018-07-01
75084 | SG000442F | SGPILCKY | DEK PILC Reactive | 96324.12 |  | 96324.12 |  |  | 114125.44 | 83 | 114042.44 | 2016-05-16 10:05 | 2025-12-31 | 2017-01-01
75084 | KYTOOLF | TKYTOOL | Transmission Capital Tool Purchases | -40805.56 |  | -40805.56 |  |  | 153782.24 | 100 | 153682.24 | 2017-11-16 13:07 | 2050-12-31 | 2017-11-01
75084 | SG990113F | SCMCOWSKY | SG-Sec OH Wire Cor Replcmnt DMWKY | 49497.24 |  | 49497.24 |  |  | 49497.24 | 1 | 49496.24 | 2017-04-03 14:03 | 2050-12-31 | 2018-03-01
75084 | CP17TBRK | 17TB15 | Constance Repl Bk1 Bush | 118.4 |  | 118.4 |  |  | 7155.98 | 20071.78 | -12915.8 | 2017-03-23 14:29 | 2019-03-31 | 2017-10-01
75084 | CP17TBRK | 17TB16 | Dixie Repl Bk2 Bush w/ LTC | 711.24 |  | 711.24 |  |  | 26559.43 | 20071.78 | 6487.65 | 2017-03-23 14:33 | 2019-03-31 | 2017-10-01 | 2019-05-06
75084 | CP17TBRK | 17TB17 | Kentucky Univ Repl Bk4 Bush | 11890.45 |  | 11890.45 |  |  | 17389.68 | 15322.35 | 2067.33 | 2017-03-23 14:37 | 2019-03-31 | 2017-10-01 | 2018-07-31
75084 | SG000770F | SG770MAS | 2018 MAS Radio | 57657.59 |  | 57657.59 |  |  | 57657.59 | 112986 | -55328.41 | 2018-02-13 17:18 | 2019-03-31 | 2018-02-01
75084 | SG000797F | SG797SVRS | SG DEE FND Upgrade - 797 | 3987.95 |  | 3987.95 |  |  | 3987.95 | 2476 | 1511.95 | 2018-08-14 17:33 | 2020-03-30 | 2018-09-01
75084 | SG000797F | SG797SW | SG DEE FND Upgrade - 797 | 1184.68 |  | 1184.68 |  |  | 1184.68 | 18436 | -17251.32 | 2018-08-14 17:01 | 2020-03-31 | 2018-09-01
75084 | ETERRASRC | E-TERRASR | Modeling Tool e-terrasource | 7549.31 |  | 7549.31 |  |  | 7549.31 | 264721.28 | -257171.97 | 2018-08-09 12:41 | 2019-11-30 | 2018-08-01
75084 | DEMERKY | MX7048752 | Covington Repl Cooling Fans TB1 | 12366.41 |  | 12366.41 |  |  | 12366.41 | 7451.28 | 4915.13 | 2018-01-23 20:20 | 2020-03-31 | 2018-01-01
75084 | DEMERKY | EMR326 | Thom More Ckt Sw Sw's - DEMERKY | 150.77 |  | 150.77 |  |  | 25168.17 | 39506 | -14337.83 | 2017-02-09 14:48 | 2018-01-31 | 2017-02-01 | 2018-01-27
75084 | KCTFOOL | KCTOOL | TOOLS BLANKET | 36726.19 |  | 36726.19 |  |  | 36726.19 | 1 | 36725.19 | 2018-07-27 15:23 | 2069-04-01 | 2018-11-01
75084 | 75084DOM | KFPLOMX | Foreign Pole Repl OM | 9922.49 |  | 9922.49 |  |  | 9922.49 | 0 | 9922.49 | 2017-04-07 07:33 | 2067-12-31 | 2017-09-01
75084 | DKY2020 | D2020DL1 | AM 20868748 Bellevue 43 Rlbd RUSD | 4.78 |  | 4.78 |  |  | 856.61 | 0 | 856.61 | 2017-03-07 10:12 | 2021-08-28 | 2017-04-01
75084 | KUCF48388 | KUC348388 | UG 10348388 Richwood 43 | -691.15 |  | -691.15 |  |  | 6237.97 | 0 | 6237.97 | 2017-04-11 14:03 | 2019-06-30 | 2017-06-01
75084 | KUCF48450 | KUC348450 | UG 10348450 Crescent 44 | -816.87 |  | -816.87 |  |  | 2527.97 | 0 | 2527.97 | 2017-04-11 14:03 | 2019-06-30 | 2017-10-01
75084 | KUCF48397 | KUC348397 | RUC 10348397. Cable repla | 205236.28 |  | 205236.28 |  |  | 207793.42 | 0 | 207793.42 | 2017-06-07 18:04 | 2019-03-01 | 2017-10-01
75084 | DKY1931 | D1931DL2 | AM 10895849 General Dr Part 2 | 841.18 |  | 841.18 |  |  | 18230.76 | 0 | 18230.76 | 2016-07-29 14:18 | 2022-11-29 | 2017-05-01
75084 | DKY1931 | D1931DL1 | AM 10894240 General Drive Part 1 | -700.26 |  | -700.26 |  |  | 195266.32 | 87223.94 | 108042.38 | 2016-07-29 14:11 | 2018-03-15 | 2016-08-01 | 2017-08-18
75084 | M170111 | M17011101 | Litton Sub Prop Purch | 9559.23 |  | 9559.23 |  |  | 9559.23 | 0 | 9559.23 | 2018-08-20 18:03 | 2020-02-25 | 2018-08-01
75084 | M180077 | M18007706 | T LIne RLE - Oakbrook-Aero-Woodspoi | 41.45 |  | 41.45 |  |  | 41.45 | 0 | 41.45 | 2018-11-08 18:02 | 2020-12-21 | 2018-12-01
75084 | M180077 | M18007702 | Aero Substation - New Sub | 21491.16 |  | 21491.16 |  |  | 21491.16 | 0 | 21491.16 | 2018-11-08 18:02 | 2021-05-25 | 2018-11-01
75084 | M180077 | M18007704 | Oakbrook Substation | 1820.45 |  | 1820.45 |  |  | 1820.45 | 0 | 1820.45 | 2018-11-08 18:02 | 2021-01-05 | 2018-12-01
75084 | M180077 | M18007705 | 138kV Oakbrook to Aero Line | 414.81 |  | 414.81 |  |  | 414.81 | 0 | 414.81 | 2018-11-08 18:02 | 2021-01-12 | 2018-12-01
75084 | M180077 | M18007703 | 138KV F23983 Woodspoint to Aero | 414.81 |  | 414.81 |  |  | 414.81 | 0 | 414.81 | 2018-11-08 18:02 | 2020-12-27 | 2018-12-01
75084 | M180077 | M18007701 | Woodspoint Substation | 162.03 |  | 162.03 |  |  | 162.03 | 0 | 162.03 | 2018-11-08 18:02 | 2021-02-19 | 2018-12-01
75084 | KHRF44679 | KHR744679 | RI 9744679 6th St e/o Cra | -13958.85 |  | -13958.85 |  |  | -1030.98 | 0 | -1030.98 | 2016-02-05 14:05 | 2020-02-01 | 2016-02-01
75084 | DKY2131 | D2131DL3 | AM 21798304 Hands 45 | 15838.73 |  | 15838.73 |  |  | 19090.55 | 0 | 19090.55 | 2017-07-25 13:52 | 2020-07-16 | 2017-10-01
75084 | DKY2131 | D2131DL1 | AM 21797163 Hands 45 - DKY2131 | 86087.49 |  | 86087.49 |  |  | 119728.06 | 378745.87 | -259017.81 | 2017-07-25 13:41 | 2019-12-14 | 2017-10-01 | 2019-11-24
75084 | TKY2188 | MX9749639 | Augustine F5985 12kV Rbld UB - TKY2 | 6349.56 |  | 6349.56 |  |  | 6349.56 | 0 | 6349.56 | 2018-09-07 10:02 | 2020-03-31 | 2018-11-01
75084 | TKY2188 | T2188DS1 | Augustine_Instl 22_4MVA XTR - TKY2 | 2688664.43 |  | 2688664.43 |  |  | 2929329.79 | 2593925.42 | 335404.37 | 2017-07-06 13:26 | 2019-02-15 | 2017-07-01 | 2019-01-27
75084 | SG00359F | SG359SW | SG SADM Software - 359 | 7747.15 |  | 7747.15 |  |  | 7747.15 | 0 | 7747.15 | 2018-09-27 06:52 | 2022-12-01 | 2018-09-01
75084 | DKY2132 | DKY213201 | Longbranch EKPC 138kV Loop TS | 9360.45 |  | 9360.45 |  |  | 9360.45 | 0 | 9360.45 | 2018-06-21 10:05 | 2021-01-24 | 2018-09-01
75084 | TKY1904 | TKY190402 | Blackwell F6761 Rel Rpl | 365.05 |  | 365.05 |  |  | 365.05 | 0 | 365.05 | 2018-08-30 14:02 | 2022-12-27 | 2018-12-01
75084 | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | 0.23 |  | 0.23 |  |  | 51858.3 | 250000 | -198141.7 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084 | SGETOASF | SGETOAS | SG TOA Replacement Software | 145089.88 |  | 145089.88 |  |  | 411389.89 | 208124 | 203265.89 | 2015-04-06 13:58 | 2020-03-31 | 2015-05-01 | 2019-10-20
75084 | SGETOASF | SGECOA | SG COA Software | 0.03 |  | 0.03 |  |  | 27480.85 | 13148 | 14332.85 | 2016-03-31 15:37 | 2017-09-30 | 2016-04-01 | 2017-09-08
75084 | AMKY0943 | L9108 | Cold Spring TLS | -26430.74 |  | -26430.74 |  |  | 259824.27 | 250498 | 9326.27 | 2014-05-22 | 2015-09-30 | 2014-06-01 | 2015-08-01
75084 | KHRF51813 | KHR451813 | RI 10451813 5310 Madison | -1221.02 |  | -1221.02 |  |  | 61680.68 | 45244.52 | 16436.16 | 2016-12-05 14:04 | 2017-08-15 | 2016-12-01 | 2018-01-29
75084 | CP16TBRK | 16TB02 | Bellevue Repl TB1 Bushings | -2357.33 |  | -2357.33 |  |  | 17070.24 | 12916.6 | 4153.64 | 2015-12-30 11:47 | 2017-03-31 | 2016-05-01 | 2016-08-06
75084 | CP16TBRK | 16TB04 | Florence Repl TB4 Bushings | -576.6 |  | -576.6 |  |  | 5740.75 | 14410.04 | -8669.29 | 2015-12-30 12:00 | 2017-03-31 | 2016-09-01 | 2016-12-23
75084 | KTOF28218 | KTO628218 | SL 10628218 City of Edgewood | -1534.61 |  | -1534.61 |  |  | 11636.2 | 55009.53 | -43373.33 | 2016-09-12 14:04 | 2017-03-16 | 2016-09-01 | 2017-02-08
75084 | TKY1453 | T1453TS1 | Dixie 69kV ABS - TKY1453 | 201422.36 |  | 201422.36 |  |  | 548823.12 | 475115 | 73708.12 | 2016-10-07 18:03 | 2018-07-31 | 2016-10-01 | 2018-02-02
75084 | TKY1453 | T1453DS1 | Dixie Bus 1 Swgr - TKY1453 | 917255.87 |  | 917255.87 |  |  | 3050008.84 | 2686595 | 363413.84 | 2016-10-07 18:03 | 2018-07-31 | 2016-10-01 | 2018-08-03
75084 | TKY1453 | T1453DL1 | Dixie 41-42 UG Exits TKY1453 | 208811.03 |  | 208811.03 |  |  | 226244.9 | 66147.36 | 160097.54 | 2017-07-06 15:45 | 2019-05-04 | 2017-07-01 | 2018-08-03
75084 | TKY1454 | T1454DS1 | Hands Bus 1 Swgr - TKY1454 | -22802.86 |  | -22802.86 |  |  | 1302140.35 | 688608 | 613532.35 | 2016-05-12 18:02 | 2018-03-01 | 2016-06-01 | 2018-02-08
75084 | TKY1696 | T1696TS1 | Kenton XTR 4 Rel Repl - TKY1696 | 6901.24 |  | 6901.24 |  |  | 181114.56 | 288284 | -107169.44 | 2016-11-15 14:04 | 2018-03-01 | 2017-01-01 | 2018-02-28
75084 | DKY1932 | D1932DS1 | Bellevue Upg Dist Cir Rel_RUSD - DK | 220.44 |  | 220.44 |  |  | 380515.78 | 277439 | 103076.78 | 2016-08-19 09:32 | 2018-01-29 | 2016-09-01 | 2018-02-10
75084 | KHRF53148 | KHR653148 | DOT 20653148 Ky 236 Mt Zion | -181126.42 |  | -181126.42 |  |  | 682081.33 | 265402.16 | 416679.17 | 2017-02-13 14:04 | 2018-03-31 | 2017-03-01 | 2018-05-03
75084 | TKY1611 | T1611DS1 | Augustine Swgr Repl - TKY1611 | 116282.8 |  | 116282.8 |  |  | 418137.57 | 1219379 | -801241.43 | 2017-03-23 18:02 | 2019-04-30 | 2017-03-01 | 2019-06-04
75084 | DKY1929 | D1929RS1 | RUSD Taylor Mill Purch Sub Property | 162929.38 |  | 162929.38 |  |  | 222946.44 | 282613 | -59666.56 | 2016-08-17 13:44 | 2019-04-04 | 2016-11-01 | 2019-03-18
75084 | DKY2018 | D2018DS1 | Dixie BK 4 - DKY2018 - DKY2018 | 2068010.26 |  | 2068010.26 |  |  | 2222710.34 | 3407443 | -1184732.66 | 2017-06-07 07:50 | 2019-04-23 | 2017-08-01 | 2019-05-01
75084 | DKY2018 | D2018TL1 | Dixie 6764 Line Relo TL - DKY2018 | 17635.07 |  | 17635.07 |  |  | 18985.92 | 135025 | -116039.08 | 2017-06-07 08:15 | 2019-03-01 | 2017-11-01 | 2019-02-21
75084 | DKY2018 | DKY201801 | Dixie 6763 Line Relo TL2 - DKY2018 | 120133.04 |  | 120133.04 |  |  | 120133.04 | 16258.14 | 103874.9 | 2018-01-23 20:20 | 2019-01-01 | 2018-01-01 | 2018-06-28
75084 | DKY2018 | D2018TS1 | Dixie 69kV Loop - DKY2018 | 403374.84 |  | 403374.84 |  |  | 454721.44 | 1145705 | -690983.56 | 2017-06-07 07:42 | 2019-04-23 | 2017-07-01 | 2019-05-01
75084 | DKY2018 | MX9533906 | Dixie Bank 4 Bus Duct Tie - DKY2018 | 15758.93 |  | 15758.93 |  |  | 15758.93 | 5192.15 | 10566.78 | 2018-08-24 10:02 | 2019-09-01 | 2018-11-01 | 2019-05-01
75084 | DKY2151 | D2151DL1 | AM 20710413 Crittenden Gen Intrc | 2871.73 |  | 2871.73 |  |  | 124015.92 | 75335.28 | 48680.64 | 2017-02-14 10:22 | 2018-07-31 | 2017-03-01 | 2018-03-15
75084 | DKY2151 | D2151DS1 | Crittenden PTs_chk VR DKY2151 (Pare | 22755.16 |  | 22755.16 |  |  | 53630.64 | 79115 | -25484.36 | 2017-07-20 13:56 | 2018-03-18 | 2017-07-01 | 2018-02-15
75084 | DKY1912 | D1912DL1 | RUSD Covington 43-44 UG - DKY1912 | 19139.63 |  | 19139.63 |  |  | 152968.83 | 99277.72 | 53691.11 | 2017-02-15 15:40 | 2018-03-31 | 2017-03-01 | 2018-03-22
75084 | DKY1912 | D1912DS1 | Covington Xtr 2_RUSD - DKY1912 | 371569.56 |  | 371569.56 |  |  | 3032539.2 | 2776527.3 | 256011.9 | 2016-08-19 09:12 | 2018-08-31 | 2016-09-01 | 2018-08-19
75084 | DKY1912 | D1912DL2 | RUSD Covington 44 OH - DKY1912 | 1029.19 |  | 1029.19 |  |  | 31296.66 | 20798.27 | 10498.39 | 2017-02-15 16:06 | 2018-03-31 | 2017-04-01 | 2017-09-16
75084 | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 298882.75 |  | 298882.75 |  |  | 1146550.98 | 823726 | 322824.98 | 2014-02-18 | 2019-02-16 | 2014-03-01 | 2019-04-09
75084 | KIAF03715 | KIA703715 | DA 10703715 Constance 42 | 367.36 |  | 367.36 |  |  | 78649.53 | 64102.57 | 14546.96 | 2017-01-04 10:04 | 2018-03-31 | 2017-02-01 | 2018-02-02
75084 | DKY2150 | D2150DL1 | AM 20709498 Verona 42 Rbld | -9984.15 |  | -9984.15 |  |  | 302454.95 | 129954.31 | 172500.64 | 2017-02-14 10:11 | 2018-03-31 | 2017-02-01 | 2018-02-16
75084 | DKY2150 | D2150DS1 | Verona 42 PTs chk VR | 31364.25 |  | 31364.25 |  |  | 69574.76 | 79115 | -9540.24 | 2017-07-20 13:31 | 2018-03-31 | 2017-07-01 | 2018-03-01
75084 | DKY2150 | D2150DL2 | AM 20710216 Walton 1 Intercon | 1590.99 |  | 1590.99 |  |  | 58441.16 | 31697.43 | 26743.73 | 2017-02-14 10:16 | 2018-07-31 | 2017-10-01 | 2018-03-22
75084 | MWAVEKYEL | NINT2156B | Cisco Data Network | 614.8 |  | 614.8 |  |  | 9463.48 | 10183 | -719.52 | 2017-02-20 07:17 | 2018-03-31 | 2017-07-01 | 2018-03-06
75084 | TKY2009 | T2009DS1 | Kenton TB3 Rpl - TKY2009 | 1372045.89 |  | 1372045.89 |  |  | 1449983.1 | 1962535 | -512551.9 | 2017-04-27 14:03 | 2019-04-20 | 2017-06-01 | 2019-04-09
75084 | SG000726F | SG726SVRS | SG DEE AMI BlueCat Scale - 726 | 488.94 |  | 488.94 |  |  | 821.14 | 2783 | -1961.86 | 2017-06-29 15:36 | 2018-03-28 | 2017-07-01 | 2018-05-23
75084 | KHRF51720 | KHR851720 | RI 11851720 Rice Pike | 112952.79 |  | 112952.79 |  |  | 319440.48 | 75014.92 | 244425.56 | 2017-04-13 14:02 | 2018-05-01 | 2017-04-01 | 2018-07-04
75084 | SG000790F | SG790TMGR | SG DEE TUG Systems Target Manager | 18178.62 |  | 18178.62 |  |  | 18178.62 | 33758.02 | -15579.4 | 2018-04-17 15:07 | 2019-09-30 | 2018-04-01 | 2019-09-11
75084 | SG000790F | SG790VISU | SG DEE TUG Target Visualization | 9724.75 |  | 9724.75 |  |  | 9724.75 | 26181.24 | -16456.49 | 2018-04-17 17:00 | 2019-07-30 | 2018-04-01 | 2019-09-11
75084 | DKY2127 | DKY212701 | Verona New 69kV V structure - DKY21 | 392542.04 |  | 392542.04 |  |  | 392542.04 | 726368 | -333825.96 | 2018-01-25 14:02 | 2019-10-15 | 2018-04-01 | 2019-11-15
75084 | DKY2127 | DKY212703 | Verona F6761 Loop TL - DKY2127 | 129841.41 |  | 129841.41 |  |  | 129841.41 | 860984 | -731142.59 | 2018-01-25 14:02 | 2019-10-15 | 2018-08-01 | 2019-11-15
75084 | DKY2127 | DKY212702 | Verona BK 2 - DKY2127 | 200865.09 |  | 200865.09 |  |  | 200865.09 | 2299493 | -2098627.91 | 2018-01-25 14:02 | 2019-10-15 | 2018-04-01 | 2019-11-15
75084 | TEMERKY | MX8442100 | CAPITAL Wilder CB 832 replace (6) B | 44198.56 |  | 44198.56 |  |  | 44198.56 | 35418.31 | 8780.25 | 2018-05-17 14:02 | 2019-03-31 | 2018-09-01 | 2019-01-17
75084 | TEMERKY | MX8897771 | CAPITAL Buffington repl 125VDC Batt | 33914.92 |  | 33914.92 |  |  | 33914.92 | 43032.5 | -9117.58 | 2018-06-28 10:02 | 2019-03-31 | 2018-09-01 | 2019-05-06
75084 | TEMERKY | MX8430902 | CAPITAL Wilder CB 830 replace 6 Bus | 57209.5 |  | 57209.5 |  |  | 57209.5 | 35418.31 | 21791.19 | 2018-05-17 10:02 | 2019-03-31 | 2018-09-01 | 2019-01-29
75084 | TEMERKY | MX8898156 | CAPITAL Buffington repl 125VDC Batt | 33914.92 |  | 33914.92 |  |  | 33914.92 | 40659.11 | -6744.19 | 2018-06-28 10:02 | 2019-03-31 | 2018-09-01 | 2019-05-06
75084 | TEMERKY | MX7600673 | CAPITAL Wilder Repl Main Battery Ba | 34023.95 |  | 34023.95 |  |  | 34023.95 | 41644.35 | -7620.4 | 2018-03-12 14:01 | 2019-03-31 | 2018-08-01 | 2018-12-26
75084 | DKY2217 | D2217RS1 | Petersburg Sub Site - DKY2217 | 56053.53 |  | 56053.53 |  |  | 85411.56 | 382562 | -297150.44 | 2017-05-18 18:02 | 2019-10-27 | 2017-07-01 | 2019-10-08
75084 | TKY1447 | T1447DS1 | Cold Spring Ckt Swi | 3194.8 |  | 3194.8 |  |  | 371334.13 | 206535 | 164799.13 | 2016-02-12 10:59 | 2017-03-31 | 2016-02-01 | 2017-03-29
75084 | KHRF55669 | KHR355669 | RI 10355669 Washington St | -50728.57 |  | -50728.57 |  |  | 144516.82 | 101560.5 | 42956.32 | 2016-07-22 18:06 | 2017-07-28 | 2016-08-01 | 2017-06-20
75084 | KHRF97697 | KHR297697 | DOT 7297697 Covington 43 | -7238.49 |  | -7238.49 |  |  | 53690.98 | 39491.86 | 14199.12 | 2016-07-07 18:05 | 2018-01-01 | 2016-07-01 | 2017-10-10
75084 | KHRF82804 | KHR082804 | RI 10082804 15 Spiral Dr | 8905.81 |  | 8905.81 |  |  | -6778.43 | 59622.55 | -66400.98 | 2016-08-23 14:03 | 2017-08-28 | 2016-10-01 | 2018-01-04
75084 | KUCF61112 | KUC261112 | UG 10261112 Constance 42 | 332564.86 |  | 332564.86 |  |  | 803521.46 | 360637.32 | 442884.14 | 2017-01-10 14:04 | 2019-03-19 | 2017-03-01 | 2018-08-10
75084 | KIPF08146 | KIP708146 | NB 20708146 Beaver 41 Reb | 25081.15 |  | 25081.15 |  |  | 328831.49 | 200686.44 | 128145.05 | 2017-02-16 10:04 | 2018-01-31 | 2017-03-01 | 2017-12-06
75084 | TKY1876 | T1876DS1 | Dayton XTR 1 Rel Rpl - TKY1876 | 173524.34 |  | 173524.34 |  |  | 241994.88 | 175818 | 66176.88 | 2016-11-15 14:02 | 2018-07-31 | 2017-01-01 | 2018-06-21
75084 | KIAF03714 | KIA703714 | DA 10703714 Long Branch 4 | 9698.08 |  | 9698.08 |  |  | 54611.29 | 56580.26 | -1968.97 | 2016-10-03 18:05 | 2019-03-01 | 2017-12-01 | 2018-10-26
75084 | TKY1727 | T1727DS1 | Wilder XTR 4 Rel Repl - TKY1727 | 28341.75 |  | 28341.75 |  |  | 168882.74 | 237658 | -68775.26 | 2016-11-15 14:02 | 2018-03-01 | 2017-02-01 | 2018-03-31
75084 | KETF35854 | KET135854 | DET 10135854 Villa 43 348 | 1143791.33 |  | 1143791.33 |  |  | 1317560 | 350417.94 | 967142.06 | 2016-11-04 18:06 | 2019-06-30 | 2016-12-01 | 2019-03-12
75084 | TKY1913 | T1913DS1 | Oakbrook XTR 1 Rel Rpl - TKY1913 | 128858.28 |  | 128858.28 |  |  | 199694.89 | 350616 | -150921.11 | 2017-04-10 14:03 | 2019-03-01 | 2017-04-01 | 2018-07-13
75084 | KETF35851 | KET135851 | DET 10135851 West End 41 | 1433062.72 |  | 1433062.72 |  |  | 1495074.02 | 414893.11 | 1080180.91 | 2016-05-02 14:04 | 2019-06-14 | 2016-05-01 | 2019-05-25
75084 | KUCF48463 | KUC348463 | UG 10348463 Decoursey 41 | 268291.93 |  | 268291.93 |  |  | 269336.48 | 199651.38 | 69685.1 | 2017-02-15 14:04 | 2019-03-01 | 2017-07-01 | 2019-03-31
75084 | KUCF47633 | KUC447633 | UG 20447633 Constance 42 | 87158.29 |  | 87158.29 |  |  | 1158949.55 | 328397.17 | 830552.38 | 2017-02-22 14:02 | 2018-04-30 | 2017-03-01 | 2018-07-17
75084 | DKY1973 | D1973DL1 | AM 11028173 York 43 Ln Ext | -33072.54 |  | -33072.54 |  |  | 203920.82 | 83908.12 | 120012.7 | 2016-08-17 08:12 | 2017-10-31 | 2016-08-01 | 2017-09-14
75084 | KOCF56175 | KOC556175 | DET 11556175 Kenton 44 Re | 111234.1 |  | 111234.1 |  |  | 732428.6 | 283200.78 | 449227.82 | 2017-01-10 18:05 | 2018-03-31 | 2017-03-01 | 2018-05-05
75084 | KUCF48481 | KUC348481 | UG 10348481 Crescent 41 | -455.19 |  | -455.19 |  |  | 12365.52 | 16692.2 | -4326.68 | 2017-02-20 18:06 | 2019-04-01 | 2017-07-01 | 2017-09-21
75084 | SG000598F | SG598CDEQ | SG DEE Secure Network Infrastructur | 31334.24 |  | 31334.24 |  |  | 142741.26 | 85620 | 57121.26 | 2017-09-12 16:44 | 2019-04-30 | 2017-09-01 | 2019-04-30
75084 | TKY1914 | T1914DS1 | Longbranch Rel Rpl XTR 1 - TKY1914 | 305748.69 |  | 305748.69 |  |  | 307602.33 | 247959 | 59643.33 | 2017-04-26 15:56 | 2019-06-29 | 2017-11-01 | 2019-01-22
75084 | KIPF03154 | KIP703154 | NB 10703154 9001 US 42 Un | 2702.41 |  | 2702.41 |  |  | 61074.95 | 57736.31 | 3338.64 | 2016-08-09 18:04 | 2018-02-22 | 2017-03-01 | 2017-10-12
75084 | SG000752F | SG752SVR | DEE DOTS Grid Sim Strat Development | 7195.97 |  | 7195.97 |  |  | 9566.59 | 20643 | -11076.41 | 2017-08-08 15:31 | 2018-04-30 | 2017-09-01 | 2018-04-30
75084 | KTMF88913 | KTM988913 | INSTALL 22 LIGHTS FOR IDI | 663.56 |  | 663.56 |  |  | 105137.08 | 60720.99 | 44416.09 | 2017-04-19 18:04 | 2018-03-31 | 2017-07-01 | 2017-12-28
75084 | KYRELT | KYRELT02 | F6761 Richwood eo 71/75 | 8000.81 |  | 8000.81 |  |  | 8000.81 | 1152231 | -1144230.19 | 2018-09-04 10:02 | 2019-09-04 | 2018-09-01 | 2019-08-10
75084 | KHRF81342 | KHR181342 | DOT 7181342 Empire 41 Rel | -39.68 |  | -39.68 |  |  | 742046.64 | 246600.03 | 495446.61 | 2017-01-18 14:05 | 2017-12-01 | 2017-02-01 | 2018-03-19
75084 | CP17LTCRK | 17LTCR03 | KY Univ Repl TB4 Load Tap Changer | 14212.55 |  | 14212.55 |  |  | 49047.09 | 52076.25 | -3029.16 | 2017-07-20 06:50 | 2019-03-31 | 2017-10-01 | 2018-07-31
75084 | M180463 | M18046301 | EMERGENT - Cold Spring Circuit 49 - | 23283.88 |  | 23283.88 |  |  | 23283.88 | 48795.63 | -25511.75 | 2018-07-23 18:03 | 2019-05-08 | 2018-08-01 | 2019-02-28
75084 | M180164 | M18016401 | SPCC Upg Kenton | 37044.77 |  | 37044.77 |  |  | 37044.77 | 310204 | -273159.23 | 2018-05-02 18:02 | 2019-08-27 | 2018-06-01 | 2019-09-21
75084 | M180346 | M18034601 | Emergent - Circuit #5962 10 Pole re | 16481.67 |  | 16481.67 |  |  | 16481.67 | 2274991 | -2258509.33 | 2018-07-16 14:02 | 2019-08-10 | 2018-08-01 | 2019-07-05
75084 | KIPF44149 | KIP344149 | NB 21344149 RIVIERA DR - | -681.58 |  | -681.58 |  |  | 8240.44 | 14117.06 | -5876.62 | 2017-07-26 14:04 | 2017-12-01 | 2017-07-01 | 2017-12-27
75084 | TKYBLDG | BLD38 | HVAC Replacement | 5712.25 |  | 5712.25 |  |  | 5712.25 | 2758.4 | 2953.85 | 2018-06-25 14:06 | 2018-12-01 | 2018-07-01 | 2018-10-02
75084 | M180581 | M18058101 | EMERGENCY - Replace Buffington TB 4 | 416459.1 |  | 416459.1 |  |  | 416459.1 | 736486.42 | -320027.32 | 2018-11-19 14:01 | 2019-04-30 | 2018-11-01 | 2019-04-25
75084 | KIPF89003 | KIP189003 | NB 11189003 Duveneck Squa | 1942.83 |  | 1942.83 |  |  | 60594.8 | 65005.6 | -4410.8 | 2017-02-23 18:03 | 2018-05-31 | 2017-10-01 | 2018-01-11
75084 | SG000485F | SG485SW | SG Ext Cust Facing Wbpge SW - 485 | 0.55 |  | 0.55 |  |  | 0.55 | 37848 | -37847.45 | 2018-06-12 09:57 | 2020-02-28 | 2018-06-01 | 2019-01-01
75084 | SG000485F | SG485SVRS | SG Ext Cust Facing Wbpge HW - 485 | 0.05 |  | 0.05 |  |  | 0.05 | 3200 | -3199.95 | 2018-06-12 10:52 | 2020-02-28 | 2018-06-01 | 2019-01-01
75085 | CUSTCONN | 315986A | Customer Connect - Core | 183433.88 |  | 183433.88 |  |  | 546407.98 | 3313201.21 | -2766793.23 | 2017-08-10 10:40 | 2022-06-30 | 2017-08-01
75085 | CUSTCONN | 315986B | Customer Connect- Analytics | 111099.2 |  | 111099.2 |  |  | 155652.74 | 99396.72 | 56256.02 | 2017-08-10 13:07 | 2018-09-30 | 2017-08-01 | 2018-09-30
75085 | CUSTCONN | 315986C | Customer Connect- CRM | 228278.22 |  | 228278.22 |  |  | 276668.68 | 267635.67 | 9033.01 | 2017-08-10 14:25 | 2019-05-28 | 2017-08-01 | 2019-06-18
75085 | CUSTCONN | 315986D | Customer Connect- Prepaid Advantage | 46460.94 |  | 46460.94 |  |  | 150413.35 | 399313.16 | -248899.81 | 2017-08-10 15:24 | 2019-12-30 | 2017-08-01
75085 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 17738.87 |  | 17738.87 |  |  | 92694.44 | 166907.14 | -74212.7 | 2017-08-11 10:38 | 2020-06-30 | 2017-08-01
75085 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 148704.68 |  | 148704.68 |  |  | 238897.8 | 62909 | 175988.8 | 2017-09-05 18:39 | 2018-10-01 | 2017-09-01 | 2018-10-01
75085 | CUSTCONN | 315986HW4 | Customer Connect- Hardware Proj 2 | 98591.19 |  | 98591.19 |  |  | 98591.19 | 76896 | 21695.19 | 2018-08-31 12:26 | 2019-06-01 | 2018-08-01 | 2019-08-01
75085 | FPIT | 307482 | Customer Mobile App | 26978.35 |  | 26978.35 |  |  | 41923.57 | 28598 | 13325.57 | 2017-05-08 15:19 | 2019-06-25 | 2017-05-01 | 2019-06-25
75085 | FPIT | 325480C | Watson Explorer (Omnifind Replace) | 7956.1 |  | 7956.1 |  |  | 23539.96 | 18496.93 | 5043.03 | 2016-11-29 12:47 | 2018-05-31 | 2016-12-01 | 2018-09-08
75085 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 483815.01 |  | 483815.01 |  |  | 2715241.2 | 1159204 | 1556037.2 | 2016-02-11 12:16 | 2018-10-31 | 2016-03-01 | 2018-10-31
75085 | FPIT | 336593019 | New Call Ctr SIP Trunks | 13526.21 |  | 13526.21 |  |  | 13526.21 | 14982 | -1455.79 | 2018-03-14 16:41 | 2020-03-31 | 2018-03-01
75085 | FPIT | 344598001 | Duke Customer IVR Replacement | 34715.42 |  | 34715.42 |  |  | 34715.42 | 282698 | -247982.58 | 2018-04-10 15:20 | 2019-12-24 | 2018-04-01
75085 | FPIT | 344637001 | MW Test Data Enhancement | 2.06 |  | 2.06 |  |  | 2.06 | 2622 | -2619.94 | 2018-03-14 10:39 | 2018-12-28 | 2018-03-01 | 2018-12-28
75085 | FPIT | 311803CH | Lighting System Integration HW | 995.39 |  | 995.39 |  |  | 1123.26 | 3243.47 | -2120.21 | 2015-09-18 10:13 | 2019-03-31 | 2016-01-01 | 2018-06-17
75085 | FPIT | 344368 | Customer Transformer Mapping Engine | 19908.2 |  | 19908.2 |  |  | 20049.47 | 22936.91 | -2887.44 | 2017-10-23 13:29 | 2020-03-31 | 2017-11-01
75085 | FPIT | 342284C | Outage Detection Platform | 22990.85 |  | 22990.85 |  |  | 27731.8 | 9664.27 | 18067.53 | 2017-09-06 16:54 | 2020-03-31 | 2017-09-01
75085 | FPIT | 311803CS | Lighting System Integration Softwar | 51626.94 |  | 51626.94 |  |  | 179973.93 | 157966.53 | 22007.4 | 2015-09-14 13:59 | 2019-03-31 | 2015-11-01 | 2019-02-28
75080 | FPIT | R6095 | Logistics Cycle Times | 9036.37 |  | 9036.37 |  |  | 73246.74 | 36719.92 | 36526.82 | 2016-01-21 13:27 | 2017-12-15 | 2016-02-01 | 2018-02-02
75080 | FPIT | 323326DEK | 2017 Workstation Refresh | 8597.4 |  | 8597.4 |  |  | 63084.11 | 43049 | 20035.11 | 2017-06-02 14:52 | 2018-03-29 | 2017-06-01 | 2018-03-29
75080 | FPIT | 307600DEK | BASS Program- Phase 1 Release 3 KY | 49575.8 |  | 49575.8 |  |  | 49575.8 | 156838 | -107262.2 | 2017-12-11 12:35 | 2019-02-15 | 2017-12-01 | 2019-01-15
75080 | FPIT | 336593EOC | Install CISCO Switches & Rtrs | 1705.86 |  | 1705.86 |  |  | 49471.43 | 88500 | -39028.57 | 2017-07-07 14:43 | 2018-06-30 | 2017-07-01 | 2018-05-31
75080 | FPIT | 323482KY | Replace EPM Tool 2017 | 2041.52 |  | 2041.52 |  |  | 10617.37 | 11076.27 | -458.9 | 2017-02-10 14:00 | 2018-04-12 | 2017-02-01 | 2018-05-31
75080 | FPIT | 307600007 | BASS - Ground Water Sample | 785.68 |  | 785.68 |  |  | 785.68 | 59475 | -58689.32 | 2018-08-14 10:14 | 2020-01-01 | 2018-11-01
75080 | FPIT | NINT1105K | Implement Rates and Regulatory Stra | 1398.97 |  | 1398.97 |  |  | 230817.41 | 234263 | -3445.59 | 2017-08-15 14:48 | 2020-01-31 | 2017-08-01
75080 | FPIT | 354154SG1 | DXT Spend Governance | 46258.14 |  | 46258.14 |  |  | 46258.14 | 62115 | -15856.86 | 2018-11-26 13:36 | 2020-03-31 | 2018-11-01
75080 | FPIT | 354154001 | DXT Agile Product Team | 446.05 |  | 446.05 |  |  | 446.05 | 100336 | -99889.95 | 2018-11-13 13:30 | 2020-03-31 | 2018-12-01
75080 | FPIT | R9205 | Trading Information Management Cons | 149.19 |  | 149.19 |  |  | 6054.63 | 56252.04 | -50197.41 | 2016-03-28 15:16 | 2017-06-30 | 2016-05-01 | 2018-03-12
75080 | FPIT | RF17Q4DEK | 2017 Workstation Hardware | -0.11 |  | -0.11 |  |  | 1345.36 | 1504 | -158.64 | 2017-11-22 11:09 | 2018-03-31 | 2017-12-01 | 2018-03-31
75080 | FPIT | S6621 | Plantview Reliability Index Module | -122.72 |  | -122.72 |  |  | 5653.45 | 7144.63 | -1491.18 | 2016-05-17 13:49 | 2017-07-31 | 2016-05-01 | 2017-11-17
75080 | FPIT | 323326005 | Workstation Refresh 2017-2019 | 9241.31 |  | 9241.31 |  |  | 9241.31 | 212265 | -203023.69 | 2018-06-19 16:01 | 2019-06-30 | 2018-07-01 | 2019-03-31
75080 | FPIT | 323174Q4I | Q4 2017 End of Life Server | -0.72 |  | -0.72 |  |  | 8889.67 | 8685 | 204.67 | 2017-10-16 14:30 | 2018-03-31 | 2017-12-01 | 2018-03-31
75080 | FPIT | 323326002 | 2018 Workstation Refresh-Phase 2-Q1 | 329892.34 |  | 329892.34 |  |  | 329892.34 | 86615 | 243277.34 | 2018-01-17 13:39 | 2018-12-29 | 2018-02-01 | 2018-12-31
75080 | FPIT | 359688001 | ISOP Spend Governance Non-Project W | 12680.8 |  | 12680.8 |  |  | 12680.8 | 18130 | -5449.2 | 2018-12-13 11:24 | 2019-07-30 | 2018-12-01 | 2019-07-31
75080 | RESBLDKY | KMW150211 | Stair Replacement @ Erlanger Ops | 121551 |  | 121551 |  |  | 108851.46 | 121466 | -12614.54 | 2015-06-24 14:04 | 2016-03-14 | 2015-07-01 | 2016-03-14
75080 | RESBLDKY | KMW170046 | Design for replacement of windows | 1176914.1 |  | 1176914.1 |  |  | 3245167.12 | 3324206 | -79038.88 | 2017-04-05 11:17 | 2018-07-20 | 2017-04-01 | 2018-07-20
75080 | RESBLDKY | KMW180042 | Augustine Ops Lighting Replacement | 137434.02 |  | 137434.02 |  |  | 137434.02 | 137525 | -90.98 | 2018-03-12 11:01 | 2018-09-06 | 2018-04-01 | 2018-08-24
75080 | RESBLDKY | KMW170198 | Vestibule addition | 126.69 |  | 126.69 |  |  | 64096.47 | 82069 | -17972.53 | 2017-09-05 16:36 | 2018-03-31 | 2017-09-01 | 2018-03-28
75080 | RESBLDKY | KMW170248 | Ice Machine Replacement | 36.3 |  | 36.3 |  |  | 25619.15 | 30588 | -4968.85 | 2017-10-19 11:23 | 2018-03-31 | 2017-11-01 | 2018-03-28
75080 | RESBLDKY | KMW286555 | Complete Replace of HVAC System | 16488 |  | 16488 |  |  | 16488 | 18857 | -2369 | 2016-08-05 12:44 | 2017-01-28 | 2016-09-01 | 2016-12-29
75080 | RESBLDKY | KMW180109 | Warehouse Entry | 128378.36 |  | 128378.36 |  |  | 128378.36 | 157515 | -29136.64 | 2018-05-04 14:53 | 2018-12-06 | 2018-06-01 | 2018-12-07
75080 | RESBLDKY | KMW100007 | Water Heater Replacement | 19280 |  | 19280 |  |  | 19280 | 21250 | -1970 | 2018-11-14 15:55 | 2019-07-14 | 2018-12-01 | 2019-03-14
75080 | RESBLDKY | KMW477910 | Electronic furniture assembly | 2999.36 |  | 2999.36 |  |  | 2999.36 | 2615 | 384.36 | 2018-06-14 14:47 | 2018-12-14 | 2018-09-01 | 2018-12-17
75080 | RESBLDKY | KMW498659 | Envision Center Compressor Replacem | 9818.02 |  | 9818.02 |  |  | 9818.02 | 10419 | -600.98 | 2018-08-16 15:54 | 2019-03-15 | 2018-11-01 | 2018-11-30
75080 | FMWAVEKY | 315218GLC | 315218 Markland Dam Mod. Glenco | -614.03 |  | -614.03 |  |  | 50566.76 | 87365.45 | -36798.69 | 2016-11-03 10:59 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | 315218VRR | 315218 - Markland Dam Mod. Verona | -488.89 |  | -488.89 |  |  | 58584.49 | 106349.71 | -47765.22 | 2016-11-02 16:24 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | 315218SPR | 315218 - Markland Dam Mod. Sparta | 359.63 |  | 359.63 |  |  | 139678.9 | 113451.43 | 26227.47 | 2016-11-03 10:37 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | 315218VR2 | 315218 - Markland Dam Mod. Verona2 | -175.14 |  | -175.14 |  |  | 36723.01 | 87728 | -51004.99 | 2016-11-03 11:49 | 2017-11-01 | 2016-12-01 | 2018-01-31
75080 | FMWAVEKY | NINT732B | Butler Microwave pre-fab building | 102992.75 |  | 102992.75 |  |  | 113193.52 | 113900 | -706.48 | 2017-02-03 15:17 | 2018-11-30 | 2017-03-01 | 2018-11-11
75080 | RESMDKY | KMW18289B | Acquisition of 1 building at 1262 C | 2733253.24 |  | 2733253.24 |  |  | 2733253.24 | 2802750 | -69496.76 | 2018-10-24 09:35 | 2019-03-31 | 2018-10-01 | 2019-03-19
75080 | RESMDKY | KMW18289A | Acquisition of 6.68 acres at 1262 C | 881634.27 |  | 881634.27 |  |  | 881634.27 | 934250 | -52615.73 | 2018-10-24 09:52 | 2019-03-31 | 2018-10-01 | 2019-03-19
75080 | MWAVE | 348643007 | CIOPS RFID Asset Tracking DEK | 2971.59 |  | 2971.59 |  |  | 2971.59 | 59330 | -56358.41 | 2018-04-20 16:08 | 2020-03-01 | 2018-06-01
75080 | CAPBUDK | ETSFHCAPK | CAPITAL BUDGET PROJECT KENT | 0.01 |  | 0.01 |  |  | 0.01 | 0 | 0.01 | 2008-07-01 | 2050-12-31 | 2008-07-01
75080 | CAPBUDK | ETSPDCAPK | ETS Power Delivery Cap Overhead | -62353.96 |  | -62353.96 |  |  | -62353.96 | 0 | -62353.96 | 2008-07-07 | 2050-12-31 | 2008-07-01
75080 | CAPBUDK | DISOHDK | DEK Distribution Overhead Pool | 8294.51 |  | 8294.51 |  |  | 8294.51 | 0 | 8294.51 | 2017-07-31 11:00 | 2026-03-31 | 2018-01-01
75080 | KYPYACCR | E1214 | Kentucky Quarterly Payroll Accrual | 24000 |  | 24000 |  |  | 161000 | 0 | 161000 | 2008-09-19 | 2050-12-31 | 2008-09-01
75080 | FLKY0249G | DUKTKYE18 | Fleet Off-Road Vehicles - KY | 73690.25 |  | 73690.25 |  |  | 73690.25 | 20000 | 53690.25 | 2018-02-01 16:33 | 2018-12-31 | 2018-03-01
75080 | FLKY0249G | DUKETCKYE | Fleet On-Road Vehicles - Elec-KY | -1261.88 |  | -1261.88 |  |  | 340051.79 | 40000 | 300051.79 | 2017-01-19 14:28 | 2050-12-31 | 2017-03-01
75080 | ASSETCPAK | CPADEK | DEK Capital CPA ALLOCATION | 478.46 |  | 478.46 |  |  | 478.46 | 1 | 477.46 | 2018-01-31 08:58 | 2050-12-31 | 2018-03-01
75080 | FPTABLETS | DEKTABLET | Fleet Services Tablet Purchases | 11551.87 |  | 11551.87 |  |  | 11551.87 | 11858 | -306.13 | 2018-07-18 11:46 | 2018-11-30 | 2018-12-01
75081 | EBS01296 | EBS01296X | Demin Acid Tank | -1412.44 |  | -1412.44 |  |  | 1064714.72 | 348320.7 | 716394.02 | 2015-10-19 11:48 | 2016-09-30 | 2015-11-01 | 2016-10-08
75081 | EB021316 | EB021316X | 2-2 Pulv Roll Wheel repl | 359630 |  | 359630 |  |  | 549204.03 | 716013.49 | -166809.46 | 2017-10-06 13:37 | 2018-08-27 | 2017-10-01 | 2018-09-10
75081 | EB021456 | EB021456X | SmartGen Installation at East Bend | 20428.74 |  | 20428.74 |  |  | 4283467.29 | 4503175.79 | -219708.5 | 2015-01-09 | 2017-12-31 | 2015-01-01 | 2018-03-15
75081 | EB021271 | EB021271X | Replace F to G Coal Chute | -763.63 |  | -763.63 |  |  | 1172343.29 | 792558.1 | 379785.19 | 2015-08-28 10:35 | 2016-07-01 | 2015-09-01 | 2016-08-07
75081 | EB021489 | EB021489X | 2-2 Fly Ash Silo to Silo Blowers | -250.97 |  | -250.97 |  |  | 1306731.66 | 1072612 | 234119.66 | 2014-12-08 | 2016-08-31 | 2014-12-01 | 2016-09-23
75081 | EB020380 | EB020380X | Replace 4th Floor HVAC Chillers | 252580.46 |  | 252580.46 |  |  | 1845691.3 | 1720186.3 | 125505 | 2017-01-24 07:51 | 2018-02-23 | 2017-01-01 | 2018-04-19
75081 | EB020433 | EB020433X | HCAD Repl C Conveyor to Surge Bin | 807705.06 |  | 807705.06 |  |  | 1063835.62 | 1346868.67 | -283033.05 | 2017-08-16 10:05 | 2018-08-01 | 2017-09-01 | 2018-08-12
75081 | EB021454 | EB021454X | HP Turbine Nozzle Block & Seals | 3399640.91 |  | 3399640.91 |  |  | 4523383.64 | 4869726.75 | -346343.11 | 2017-01-24 08:33 | 2018-11-30 | 2017-02-01 | 2018-09-29
75081 | EB020320 | EB020320X | Replace SAH Collar Seals | 999232.95 |  | 999232.95 |  |  | 1381557.24 | 1538836.64 | -157279.4 | 2017-08-08 15:16 | 2018-12-31 | 2017-10-01 | 2018-09-29
75081 | EB020406 | EB020406X | CT Drift Elim Replmnt - Phase 2 | 970006.6 |  | 970006.6 |  |  | 1237222.66 | 1311345.76 | -74123.1 | 2017-11-28 10:50 | 2018-09-01 | 2017-12-01 | 2018-08-14
75081 | EB020624 | EB020624X | SSH Intermediate Pendant Rplc | 2751001.12 |  | 2751001.12 |  |  | 3304344.21 | 3824632.83 | -520288.62 | 2017-05-15 15:44 | 2018-09-01 | 2017-05-01 | 2018-09-29
75081 | EB020382 | EB020382X | Circ Water Lining | 1322311.26 |  | 1322311.26 |  |  | 1424598.81 | 1383331.55 | 41267.26 | 2017-10-18 09:50 | 2018-08-27 | 2017-12-01 | 2018-08-14
75081 | FPITF | 307600001 | BASS-DMR Deployments Fossil/Hydro | 25259.11 |  | 25259.11 |  |  | 25259.11 | 12302 | 12957.11 | 2017-12-21 15:57 | 2019-12-01 | 2018-01-01
75081 | FPITF | 323123DEK | GenVision- FHO Data Analytics | 15048.11 |  | 15048.11 |  |  | 15048.11 | 11446 | 3602.11 | 2017-12-20 07:17 | 2020-03-28 | 2018-01-01
75081 | FPITF | 337767001 | KMS Upgrade | 2800.89 |  | 2800.89 |  |  | 2800.89 | 2357 | 443.89 | 2018-09-25 12:52 | 2019-12-17 | 2018-10-01
75081 | EB021409 | EB021409X | U2 Lime Injection System | 2315376.07 |  | 2315376.07 |  |  | 7062028.24 | 7935086.4 | -873058.16 | 2016-05-16 11:48 | 2019-12-31 | 2016-05-01
75081 | EB020768 | CEB020768 | PSM Remote Safe Havens | 429470.03 |  | 429470.03 |  |  | 862514.86 | 976447.45 | -113932.59 | 2017-09-14 23:28 | 2020-03-31 | 2017-09-01
75081 | EB021281 | CEB021281 | EB W. Landfill Cell 2 Construction | 273310.42 |  | 273310.42 |  |  | 273310.42 | 21601631.47 | -21328321.05 | 2017-11-30 08:30 | 2020-05-31 | 2018-01-01
75081 | EB020745 | CEB020745 | CCP EB Lined Retention Basin - East | 3044.8 |  | 3044.8 |  |  | 3044.8 | 12974782.23 | -12971737.43 | 2018-11-16 14:14 | 2020-06-30 | 2018-12-01
75081 | EB020557 | CEB020557 | PSM Ammonia Tank Vapor Barrier | 113770.78 |  | 113770.78 |  |  | 113770.78 | 1268272.81 | -1154502.03 | 2018-11-20 09:13 | 2019-12-31 | 2018-12-01
75081 | EBS01243 | EBS01243X | New East Bend Landfill | 884203.32 |  | 884203.32 |  |  | 40198389.43 | 13966995.52 | 26231393.91 | 2013-11-19 | 2018-06-30 | 2013-12-01 | 2018-03-15
75081 | EB201285 | EB201285X | Condenser Outer Loop Retube | 2159710.18 |  | 2159710.18 |  |  | 4246548.88 | 5038518.05 | -791969.17 | 2017-01-10 15:19 | 2018-07-01 | 2017-01-01 | 2018-08-14
75081 | EB020608 | EB020608X | Ammonia Monitoring System-Deep Dive | 16703.41 |  | 16703.41 |  |  | 330593.09 | 189130.15 | 141462.94 | 2016-11-14 10:25 | 2018-09-30 | 2016-12-01 | 2018-09-01
75081 | EB020056 | EB020056X | Sec Superheat Outlet Header Rep | 5279498.05 |  | 5279498.05 |  |  | 6753515.49 | 8908328.79 | -2154813.3 | 2016-10-20 15:11 | 2018-12-01 | 2016-10-01 | 2018-09-29
75081 | EB020290 | CEB020290 | Lined Retention Basin | 7511722.03 |  | 7511722.03 |  |  | 10190909.61 | 3085662 | 7105247.61 | 2016-07-11 18:39 | 2018-11-15 | 2016-08-01 | 2019-02-28
75081 | EB020774 | EB020774X | Turbine Floor LED Lighting | 25684.52 |  | 25684.52 |  |  | 78535.3 | 79243.31 | -708.01 | 2017-10-13 11:33 | 2018-03-31 | 2017-11-01 | 2018-04-03
75081 | EB021237 | EB021237X | ID Fan VFD Power Cell Rep | 1030221.12 |  | 1030221.12 |  |  | 1823782.58 | 1092053.63 | 731728.95 | 2017-05-23 14:42 | 2018-08-26 | 2017-09-01 | 2018-09-08
75081 | EB020043 | CEB020043 | HCAD G Conveyor Washbox | 260600.71 |  | 260600.71 |  |  | 277217.91 | 180937.22 | 96280.69 | 2017-11-03 18:04 | 2018-09-01 | 2017-12-01 | 2018-09-06
75081 | EB020763 | CEB020763 | Crusher &Transfer House LED Light | 21980.43 |  | 21980.43 |  |  | 397292.42 | 396006.4 | 1286.02 | 2017-09-01 16:07 | 2018-11-30 | 2017-09-01 | 2018-11-30
75081 | EB020807 | EB020807X | 2-3 CT Motor and Gearbox Replacemen | 225736.24 |  | 225736.24 |  |  | 225736.24 | 221882.41 | 3853.83 | 2018-03-02 08:19 | 2018-08-30 | 2018-03-01 | 2018-09-08
75081 | EB020639 | EB020639X | Replace B Conveyor Belt | 135175.67 |  | 135175.67 |  |  | 212555.31 | 185065.65 | 27489.66 | 2017-12-15 14:37 | 2018-09-01 | 2017-12-01 | 2018-09-02
75081 | EB020888 | EB020888X | Repl MSP AHU Heat Exchanger | 71995.36 |  | 71995.36 |  |  | 71995.36 | 73431.49 | -1436.13 | 2018-04-09 12:51 | 2018-09-30 | 2018-05-01 | 2018-09-06
75081 | EB021410 | CEB021410 | Dry Bottom Ash Conversion | 17893408.04 |  | 17893408.04 |  |  | 30814236.52 | 24439593 | 6374643.52 | 2015-10-15 14:37 | 2018-08-30 | 2015-12-01 | 2018-09-10
75081 | EB020673 | EB020673X | CEMS Monitor Replacement | 226730.88 |  | 226730.88 |  |  | 383314.51 | 495143.52 | -111829.01 | 2017-07-05 10:17 | 2018-10-26 | 2017-07-01 | 2018-07-12
75081 | EB020672 | CEB020672 | SmartGen EBS UAT DGA | 302617.61 |  | 302617.61 |  |  | 339083.81 | 203942.38 | 135141.43 | 2017-11-03 18:20 | 2018-11-01 | 2017-12-01 | 2018-12-01
75081 | EB021422 | EB021422X | Precipitator Hot Side Rebuild | 24626203.97 |  | 24626203.97 |  |  | 36858102.73 | 34338949.86 | 2519152.87 | 2015-12-04 13:47 | 2019-05-31 | 2016-01-01 | 2018-09-29
75081 | EB021429 | EB021429X | HCAD Bunker/Feeder Pipes & Iso Gate | 263193.6 |  | 263193.6 |  |  | 286430.68 | 306277.24 | -19846.56 | 2017-08-03 12:42 | 2019-09-01 | 2017-10-01 | 2018-09-09
75081 | EB020642 | EB020642X | Replace CBU Counterweight Wire Rope | 484878.7 |  | 484878.7 |  |  | 484878.7 | 590714.68 | -105835.98 | 2017-09-20 08:32 | 2018-09-01 | 2018-01-01 | 2018-08-04
75081 | EB020786 | EB020786X | Repl Training Bldg Facade | 20448.4 |  | 20448.4 |  |  | 28250.4 | 44778.94 | -16528.54 | 2017-10-23 09:28 | 2018-05-30 | 2017-12-01 | 2018-06-30
75081 | EB020797 | EB020797X | 2-4 CT Motor and Gearbox Repl | 237792.48 |  | 237792.48 |  |  | 237792.48 | 245752.51 | -7960.03 | 2018-02-12 19:38 | 2018-08-30 | 2018-02-01 | 2018-09-08
75081 | EB020132 | EB020132X | Retire Hydroveyor | -1.7764e-14 |  | -1.7764e-14 |  |  | -1.954e-14 | 0 | -1.954e-14 | 2017-10-13 11:45 | 2019-05-31 | 2017-11-01 | 2019-06-15
75081 | EBS01297 | EBS01297X | Replace Module Demister Trays | 1346022.43 |  | 1346022.43 |  |  | 1747782.83 | 1206795.28 | 540987.55 | 2017-05-23 14:24 | 2018-08-02 | 2017-09-01 | 2018-08-22
75081 | EB020810 | EB020810X | WSP Pug Mill Mixer Disch Chute | 155279.83 |  | 155279.83 |  |  | 155279.83 | 135490.95 | 19788.88 | 2018-03-02 08:42 | 2018-05-15 | 2018-03-01 | 2018-08-18
75081 | EB020691 | CEB020691 | PSM Ammonia Storage Tank Level | 190556.17 |  | 190556.17 |  |  | 256196.16 | 181450.31 | 74745.85 | 2017-10-16 14:20 | 2019-03-31 | 2017-12-01 | 2018-09-01
75081 | EB020812 | EB020812X | South Thickener Tunnel Door (SM18) | 12897.69 |  | 12897.69 |  |  | 12897.69 | 12950 | -52.31 | 2018-08-13 10:32 | 2018-09-15 | 2018-08-01 | 2018-12-15
75081 | EB020917 | EB020917X | Replace 2-2 IDF Outlet Expan Joint | 28072.2 |  | 28072.2 |  |  | 28072.2 | 28065.2 | 7 | 2018-11-30 13:08 | 2018-12-31 | 2018-11-01 | 2019-02-28
75081 | EB021336 | EB021336X | CT Bypass Valve Replacement 2016 | -446.91 |  | -446.91 |  |  | 410668.19 | 410058.61 | 609.58 | 2015-10-06 11:44 | 2016-08-01 | 2015-10-01 | 2016-08-07
75081 | EB020760 | EB020760X | 2-7 CT Gearbox Replacement | 142.91 |  | 142.91 |  |  | 239154.27 | 191860.68 | 47293.59 | 2017-08-14 09:31 | 2017-12-31 | 2017-08-01 | 2018-02-15
75081 | EB021248 | EB021248X | Replace Boiler Roof Exhaust Fans | 104196.61 |  | 104196.61 |  |  | 576296.44 | 582115.52 | -5819.08 | 2017-01-20 15:12 | 2018-06-01 | 2017-02-01 | 2018-05-23
75081 | EB021442 | EB021442X | Station Chargers & Batteries | 560137.61 |  | 560137.61 |  |  | 672170.69 | 570807.88 | 101362.81 | 2017-04-21 10:37 | 2018-07-01 | 2017-08-01 | 2018-08-18
75081 | EB020674 | EB020674X | Replace CBU Cantilever Hoist Drive | 686392.58 |  | 686392.58 |  |  | 743360.61 | 517624.69 | 225735.92 | 2017-10-06 12:16 | 2018-08-26 | 2017-10-01 | 2018-08-04
75081 | EB020758 | EB020758X | Replace #2 LP Turbine L-0 Row | 1271754.97 |  | 1271754.97 |  |  | 1507261.7 | 2343723.09 | -836461.39 | 2017-08-31 11:50 | 2018-09-01 | 2017-10-01 | 2018-09-29
75081 | EB020918 | EB020918X | Replace 2A3 Mist Elim Valve Cable | 3500.86 |  | 3500.86 |  |  | 3500.86 | 6740.58 | -3239.72 | 2018-11-30 15:08 | 2018-12-31 | 2018-11-01 | 2019-02-28
75081 | EB0412 | EB0412X | Repl Boiler Economizer | 2968441.98 |  | 2968441.98 |  |  | 4536180.48 | 8380214.97 | -3844034.49 | 2016-01-19 09:34 | 2018-12-31 | 2016-01-01 | 2018-09-29
75081 | CGYEB115 | CGYPEB115 | CCP EB-115 T6 E. BEND GYPSUM MITIGA | -5420.97 |  | -5420.97 |  |  | 846995.87 | 1500000 | -653004.13 | 2015-06-04 17:33 | 2015-12-31 | 2015-08-01 | 2015-12-31
75081 | EB020336 | EB020336X | Scanner/Igniter Replacement | 513092.45 |  | 513092.45 |  |  | 710912.53 | 488807.31 | 222105.22 | 2017-09-28 12:27 | 2018-08-15 | 2017-10-01 | 2018-09-29
75081 | EB020298 | CEB020298 | East Bend SW / PW REROUTE | 16786623.23 |  | 16786623.23 |  |  | 28886141.34 | 29960739 | -1074597.66 | 2016-07-01 15:23 | 2019-05-01 | 2016-08-01 | 2019-06-30
75081 | EB020765 | EB020765X | Replace ID Fan VFD Room HVAC | 3915.12 |  | 3915.12 |  |  | 112082.97 | 85728.11 | 26354.86 | 2017-09-28 12:42 | 2018-03-31 | 2017-10-01 | 2018-03-28
75081 | EB020785 | EB020785X | Replace Training Building Roof (SM) | 10144.37 |  | 10144.37 |  |  | 53693.16 | 54227.26 | -534.1 | 2017-10-23 09:37 | 2018-03-31 | 2017-12-01 | 2018-03-28
75081 | EB020647 | CEB020647 | SmartGen EastBend Phase II BTLD | 75924.03 |  | 75924.03 |  |  | 180154.1 | 103621.3 | 76532.8 | 2017-11-01 18:10 | 2018-11-01 | 2017-12-01 | 2018-11-01
75081 | EB020703 | EB020703X | HCAD Replace B to C Chute | 437378.64 |  | 437378.64 |  |  | 601831.62 | 927247.14 | -325415.52 | 2017-08-16 10:39 | 2018-09-30 | 2017-09-01 | 2018-08-12
75081 | EB020941 | EB020941X | Replace F Conveyor Tower Siding | 12458.4 |  | 12458.4 |  |  | 12458.4 | 101553.09 | -89094.69 | 2018-11-30 13:59 | 2019-08-15 | 2018-12-01 | 2019-09-01
75081 | EB020800 | EB020800X | 2-2 Condenser Vac Pump HE | 24683.68 |  | 24683.68 |  |  | 24683.68 | 40301.21 | -15617.53 | 2018-02-12 19:13 | 2018-08-31 | 2018-06-01 | 2018-09-11
75081 | EB020090 | EB020090X | Boiler Room Vent Fan on Mezzanine | 21568.39 |  | 21568.39 |  |  | 676257 | 496509.5 | 179747.5 | 2016-05-16 11:32 | 2016-12-31 | 2016-05-01 | 2017-02-28
75081 | EB020643 | EB020643X | Cellular BDA Installation | 4309.99 |  | 4309.99 |  |  | 94631.64 | 50638.88 | 43992.76 | 2017-04-21 10:19 | 2018-03-31 | 2017-04-01 | 2018-03-22
75081 | EB020889 | EB020889X | Replace B Module Outlet Exp Joint | 57973.36 |  | 57973.36 |  |  | 57973.36 | 87956.73 | -29983.37 | 2018-08-13 13:44 | 2018-09-15 | 2018-08-01 | 2018-12-15
75081 | EB020783 | EB020783X | WSP Filter Platforms Phase 2 | 121405.59 |  | 121405.59 |  |  | 356859.74 | 270754.36 | 86105.38 | 2017-10-23 10:17 | 2018-03-30 | 2017-11-01 | 2018-03-29
75081 | EB020784 | EB020784X | Repl Service Water Bldg Roof (SM) | 92123.03 |  | 92123.03 |  |  | 116655.03 | 47200.18 | 69454.85 | 2017-10-23 10:11 | 2018-06-30 | 2017-12-01 | 2018-07-18
75081 | EB020902 | EB020902X | Rep B Conv Mag Sep Rectifier (SM18) | 10871.02 |  | 10871.02 |  |  | 10871.02 | 11241.03 | -370.01 | 2018-11-30 10:23 | 2018-12-31 | 2018-12-01 | 2019-02-28
75081 | EB020911 | EB020911X | 2-6 CT Motor and Gearbox Repl | 227193.1 |  | 227193.1 |  |  | 227193.1 | 224104.86 | 3088.24 | 2018-09-26 12:37 | 2018-11-30 | 2018-09-01 | 2018-12-26
75081 | EB020900 | EB020900X | Repl Gen Air Side Seal Oil CLR SM18 | 6771.25 |  | 6771.25 |  |  | 6771.25 | 11925.38 | -5154.13 | 2018-11-30 10:35 | 2018-12-31 | 2018-11-01 | 2019-02-28
75081 | EB020801 | EB020801X | Replace D Conveyor Belt | 137502.43 |  | 137502.43 |  |  | 137502.43 | 132777.24 | 4725.19 | 2018-02-12 20:41 | 2018-05-31 | 2018-03-01 | 2018-05-31
75081 | EB020802 | EB020802X | Tractor Garage Service Door | 19154.36 |  | 19154.36 |  |  | 19154.36 | 30443.88 | -11289.52 | 2018-02-13 07:38 | 2018-06-15 | 2018-03-01 | 2018-07-18
75081 | EB020146 | EB020146X | Replace 2nd Layer SCR Catalyst | 404594.79 |  | 404594.79 |  |  | 404594.79 | 2971507.27 | -2566912.48 | 2018-09-19 12:49 | 2019-09-08 | 2018-10-01 | 2019-08-03
75081 | EB020915 | EB020915X | 2-2 CW Pump Outlet Expansion Joint | 29607.13 |  | 29607.13 |  |  | 29607.13 | 41894.18 | -12287.05 | 2018-10-30 10:02 | 2018-11-30 | 2018-10-01 | 2019-01-31
75081 | EB020919 | EB020919X | Replace LBU Fire Protection Piping | 33088.46 |  | 33088.46 |  |  | 33088.46 | 61088.19 | -27999.73 | 2018-11-30 15:18 | 2018-12-31 | 2018-12-01 | 2019-02-28
75081 | EB020892 | EB020892X | Replace 2-3 IDBF Coupling (SM18) | 24508.79 |  | 24508.79 |  |  | 24508.79 | 22000 | 2508.79 | 2018-08-13 10:42 | 2018-09-15 | 2018-08-01 | 2018-12-15
75081 | EB020908 | EB020908X | Replace 2-1 ID Fan Outlet Exp Joint | 19988.77 |  | 19988.77 |  |  | 19988.77 | 19579.33 | 409.44 | 2018-11-30 12:47 | 2018-12-31 | 2018-11-01 | 2019-02-28
75081 | EBS01335 | EBS01335X | Repl Condenser Dogbone EJ | 58984.85 |  | 58984.85 |  |  | 58984.85 | 110497.16 | -51512.31 | 2017-05-08 11:21 | 2018-07-01 | 2018-04-01 | 2018-08-14
75081 | EB020792 | EB020792X | 2-2 WSP Vacuum Pump Repl (SM) | 1630.05 |  | 1630.05 |  |  | 40324.52 | 38531.24 | 1793.28 | 2017-12-15 15:50 | 2018-02-15 | 2017-12-01 | 2018-03-20
75081 | EB020690 | CEB020690 | PSM Barrier for pipeline | 155203.58 |  | 155203.58 |  |  | 155203.58 | 223972.13 | -68768.55 | 2018-09-14 15:07 | 2018-12-31 | 2018-10-01 | 2019-03-21
75081 | EB020937 | EB020937X | Replace Trailer City Network Cable | 11669.78 |  | 11669.78 |  |  | 11669.78 | 28964.93 | -17295.15 | 2018-11-30 14:24 | 2018-12-31 | 2018-12-01 | 2019-02-28
75081 | EB020904 | EB020904X | Replace WSP Radial Stacker Belt | 17275.28 |  | 17275.28 |  |  | 17275.28 | 19840.9 | -2565.62 | 2018-11-30 13:20 | 2018-12-31 | 2018-11-01 | 2019-02-28
75081 | EB020898 | EB020898X | Repl 2-4 IDF Inlet-Outlet Exp Joint | 53437.76 |  | 53437.76 |  |  | 53437.76 | 58084.66 | -4646.9 | 2018-10-04 14:42 | 2018-12-31 | 2018-10-01 | 2019-01-04
75081 | EB020939 | EB020939X | Replace G Conveyor Belt | 50239.11 |  | 50239.11 |  |  | 50239.11 | 103455.8 | -53216.69 | 2018-12-27 11:33 | 2019-06-30 | 2018-12-01 | 2019-08-03
75081 | EB020906 | EB020906X | Replace LBU HVACs | 51962 |  | 51962 |  |  | 51962 | 76830.69 | -24868.69 | 2018-09-26 12:17 | 2019-07-30 | 2018-12-01 | 2019-08-14
75081 | EB020945 | EB020945X | 2-10 CT Motor and Gearbox Repl | 17767.4 |  | 17767.4 |  |  | 17767.4 | 229420.39 | -211652.99 | 2018-11-30 15:37 | 2019-07-01 | 2018-12-01 | 2019-06-13
75081 | EB020940 | EB020940X | 2-1 Vertimill Gearbox Repl | 127101.25 |  | 127101.25 |  |  | 127101.25 | 127848.55 | -747.3 | 2018-12-28 09:33 | 2018-12-31 | 2018-12-01 | 2019-03-28
75082 | OPTIM | COPTIM | Develop OPTIM Modeling Tool | 0 |  | 0 |  |  | 65186.16 | 18615.68 | 46570.48 | 2016-01-15 14:16 | 2017-09-30 | 2016-01-01 | 2017-09-16
75082 | WDC00006 | WDC00006X | Cathodic Protection System Repl | 0 |  | 0 |  |  | 261347.4 | 183144.44 | 78202.96 | 2016-01-20 12:00 | 2017-01-31 | 2016-01-01 | 2017-04-24
75082 | FPITF | TC1800006 | Replace EOL servers and storage - f | 33428.8 |  | 33428.8 |  |  | 33428.8 | 46426 | -12997.2 | 2018-03-02 10:21 | 2019-03-31 | 2018-05-01 | 2019-02-28
75082 | FPITF | 307600001 | BASS-DMR Deployments Fossil/Hydro | 22437.77 |  | 22437.77 |  |  | 22437.77 | 73111 | -50673.23 | 2017-12-21 17:56 | 2019-12-01 | 2018-01-01
75082 | FPITF | 323123DKT | GenVision- FHO Data Analytics | 11471.08 |  | 11471.08 |  |  | 11471.08 | 68016 | -56544.92 | 2017-12-21 13:54 | 2020-03-28 | 2018-01-01
75082 | FPITF | 337767001 | KMS Upgrade | 2232.59 |  | 2232.59 |  |  | 2232.59 | 1878 | 354.59 | 2018-09-25 14:30 | 2019-12-17 | 2018-10-01
75082 | KYSC0001 | KYSCOCC | Emerson Ovation Compact Controller | 57219.26 |  | 57219.26 |  |  | 57219.26 | 0 | 57219.26 | 2018-10-30 11:20 | 2019-01-01 | 2018-11-01
75082 | KYSC0001 | WAL2EQPT | Walton 2 equipment | 4768.86 |  | 4768.86 |  |  | 910921.47 | 1335646.33 | -424724.86 | 2017-08-17 12:33 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | KYSCPM | KY solar common cost | -33164.03 |  | -33164.03 |  |  | 25055.8 | 1 | 25054.8 | 2017-08-17 12:39 | 2017-12-31 | 2017-08-01 | 2018-03-15
75082 | KYSC0001 | WAL1PM | Walton 1 solar owners cost | 135342.91 |  | 135342.91 |  |  | 509646.43 | 575893.12 | -66246.69 | 2017-08-17 12:40 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2CON | Walton 2 solar construction | -107499.39 |  | -107499.39 |  |  | 1660987.99 | 2018869.74 | -357881.75 | 2017-08-17 12:30 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL1CON | Walton 1 solar construction | 138602.45 |  | 138602.45 |  |  | 1968829.25 | 1994194.98 | -25365.73 | 2017-08-17 12:28 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | CRITCON | Crittenden solar construction | 401121.45 |  | 401121.45 |  |  | 2717179.88 | 3190661.23 | -473481.35 | 2017-08-17 12:31 | 2017-12-31 | 2017-08-01 | 2018-03-15
75082 | KYSC0001 | CRITEQPT | Crittenden equipment | 5358.48 |  | 5358.48 |  |  | 1427435.55 | 1780384.04 | -352948.49 | 2017-08-17 12:34 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2PM | Walton 2 solar owners cost | 136901.83 |  | 136901.83 |  |  | 479280.6 | 575723.1 | -96442.5 | 2017-08-17 12:40 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | KYSCPIT | KY PIT costs | 34041.22 |  | 34041.22 |  |  | 34041.22 | 0 | 34041.22 | 2017-08-17 12:42 | 2017-12-31 | 2018-01-01 | 2018-03-15
75082 | KYSC0001 | WAL1EQPT | Walton 1 equipment | 4768.86 |  | 4768.86 |  |  | 1221380.33 | 1336040.76 | -114660.43 | 2017-08-17 12:32 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | CRITPM | Crittenden solar owners cost | 182643.99 |  | 182643.99 |  |  | 795614.31 | 767424.88 | 28189.43 | 2017-08-17 12:41 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2PIT | Walton 2 PIT costs | 2162.11 |  | 2162.11 |  |  | 2162.11 | 23210.84 | -21048.73 | 2017-08-17 12:44 | 2017-12-31 | 2018-05-01 | 2018-03-15
75082 | KYSC0001 | WAL1PIT | Walton 1 PIT costs | 2162.11 |  | 2162.11 |  |  | 2162.11 | 23217.7 | -21055.59 | 2017-08-17 12:43 | 2017-12-31 | 2018-05-01 | 2018-03-15
75082 | KYSC0001 | CRITPIT | Crittenden PIT costs | 2882.82 |  | 2882.82 |  |  | 2882.82 | 30939.49 | -28056.67 | 2017-08-17 12:45 | 2017-12-31 | 2018-05-01 | 2018-03-15
75082 | WDC00004 | WDC00004X | Install Fuel Oil System - BOP | 37026724.02 |  | 37026724.02 |  |  | 39176272.54 | 25801931.95 | 13374340.59 | 2016-08-22 15:04 | 2019-07-01 | 2016-08-01 | 2019-07-05
75082 | WDC00015 | WDC00015X | Repl all units 4KV Aux Relay | 170.2 |  | 170.2 |  |  | 169130.92 | 159521.99 | 9608.93 | 2017-05-16 08:33 | 2017-12-31 | 2017-05-01 | 2018-01-15
75082 | WD050009 | WD050009X | WGS U5 Battery Replacement | 5935.5 |  | 5935.5 |  |  | 5935.5 | 23111.02 | -17175.52 | 2018-02-08 14:34 | 2018-09-30 | 2018-03-01 | 2018-08-28
75082 | WD040012 | WD040012X | WGS U4 Generator Rotor Rewind | 474619.64 |  | 474619.64 |  |  | 1548117.36 | 1555038.42 | -6921.06 | 2017-11-13 10:54 | 2018-05-15 | 2017-11-01 | 2018-05-27
75082 | WD060011 | WD060011X | WGS U6 Battery Replacement | 34035.77 |  | 34035.77 |  |  | 34035.77 | 22147.81 | 11887.96 | 2018-02-08 14:22 | 2018-08-30 | 2018-03-01 | 2018-08-28
75082 | WDCM0003 | WDCM0003X | WDC - Replace Station UPS | 187143.73 |  | 187143.73 |  |  | 187143.73 | 174255.39 | 12888.34 | 2018-01-17 11:42 | 2018-11-18 | 2018-01-01 | 2019-01-10
75082 | WDCM0035 | WDCM0035X | WGS-Hot Water Heater Replacement | 23643.54 |  | 23643.54 |  |  | 23643.54 | 17727.72 | 5915.82 | 2018-06-26 08:55 | 2018-10-15 | 2018-07-01 | 2018-10-26
75082 | WDCM0042 | CWDCM0042 | McAfee & Equip Install | 37573.31 |  | 37573.31 |  |  | 37573.31 | 175341.82 | -137768.51 | 2018-10-13 11:25 | 2019-04-30 | 2018-12-01 | 2019-06-25
|  |  |  | 205191811.29 | 191055742.6145 | 14136068.6755 | 6.889%