## Line Extensions Contract A
2013 Water System Improvements - Contract A - Water Lines
City of Princeton, KY
H & D Project No. 1037-07
Bid Date: Tuesday, May 22, 2018, at 11:00 a.m. local time
Contract Awarded To: JSJ Construction, LLC
Final Adjusting Change Order (Change Order #3) Supplemental Information
SCHEDULE A: AS-BUILT CONTRACT VALUE
Item | Description | Original Contract Amount |  |  |  | Revised Contract Amount With Previously Approved Change Orders |  |  |  | Construction/As-Built Amounts |  | Amount Over/Under
|  | Qty | Unit | Unit Price | Bid Value ($) | Qty | Unit | Unit Price | Value ($) | Actual Qty. | Actual Value ($) | Qty. | Amount ($)
1 | 16-inch C905 PVC DR 21 Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, testing, seeding and strawing in easement/ROW areas | 4800 | LF | 42 | 201600 | 4800 | LF | 42 | 201600 | 4378 | 183876 | -422 | -17724
2 | 16-inch C905 PVC DR 21 Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, and testing in traffic areas | 3050 | LF | 51 | 155550 | 3050 | LF | 51 | 155550 | 3448 | 175848 | 398 | 20298
3 | 16-inch PC 250 MJ DIP Water Line complete and in place including fittings with restraint, concrete thrust blocking, and testing, in traffic areas (Sta 25+00 to 25+81; sta 43+11 to 44+06) | 180 | LF | 78 | 14040 | 180 | LF | 78 | 14040 | 131 | 10218 | -49 | -3822
4 | 8-inch Class 200 PVC Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, testing, seeding and strawing in easement/ROW areas | 6600 | LF | 20 | 132000 | 6600 | LF | 20 | 132000 | 6329 | 126580 | -271 | -5420
5 | 8-inch Class 200 PVC Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, and testing in traffic areas | 800 | LF | 30 | 24000 | 800 | LF | 30 | 24000 | 869 | 26070 | 69 | 2070
6 | 6-inch Class 200 PVC Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, testing, seeding and strawing in easement/ROW areas | 2900 | LF | 17 | 49300 | 2900 | LF | 17 | 49300 | 2590 | 44030 | -310 | -5270
7 | 6-inch Class 200 PVC Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, and testing in traffic areas | 120 | LF | 41 | 4920 | 120 | LF | 41 | 4920 | 420 | 17220 | 300 | 12300
8 | 2-inch Class 200 PVC Water Line complete and in place including fittings with restraint, concrete thrust blocking, tracer wire, testing, seeding and strawing in easement/ROW areas | 444 | LF | 20 | 8880 | 444 | LF | 20 | 8880 | 438 | 8760 | -6 | -120
9 | 16-inch DIP mounted on bridge complete and in place including but not limited to all joint restraint, expansion joint, brackets, pipe hangers, insulation, anchoring, core drilling, wing wall restoration (Sta 45+15 to 46+75) | 1 | LS | 95000 | 95000 | 1 | LS | 95000 | 95000 | 1 | 95000 | 0 | 0
10 | 30-inch Steel Casing (min wall thickness 0.375-inch) with fusible 16-inch C905 PVC and tracer wire, with spacers, end seals and other appurtenances for a complete installation, installed under State Hwys by Bore and Jack | 40 | LF | 460 | 18400 | 40 | LF | 460 | 18400 | 40 | 18400 | 0 | 0
11 | 16-inch Steel Casing (min wall thickness 0.312-inch) with 8-inch CL 350 DIP and tracer wire, with spacers, end seals and other appurtenances for a complete installation, installed under State Hwys by Bore and Jack | 20 | LF | 480 | 9600 | 20 | LF | 480 | 9600 | 10 | 4800 | -10 | -4800
12 | 16-inch Steel Casing (min wall thickness 0.312-inch) with fusible 8-inch C900 PVC and tracer wire, with spacers, end seals and other appurtenances for a complete installation, installed under State Hwys by Bore and Jack | 25 | LF | 480 | 12000 | 25 | LF | 480 | 12000 | 25 | 12000 | 0 | 0
13 | 16-inch C905 PVC Pipe Restraint Harnesses at various locations shown on the Plans | 90 | EA | 418 | 37620 | 90 | EA | 418 | 37620 | 72 | 30096 | -18 | -7524
14 | 16-inch MJ DIP Pipe Restraint at various locations shown on the Plans | 10 | EA | 300 | 3000 | 10 | EA | 300 | 3000 | 21 | 6300 | 11 | 3300
15 | 16-inch Butterfly Valve and Valve Box complete, in place and accepted | 7 | EA | 2920 | 20440 | 7 | EA | 2920 | 20440 | 8 | 23360 | 1 | 2920
16 | 8-inch Gate Valve and Valve Box complete, in place and accepted | 3 | EA | 1315 | 3945 | 3 | EA | 1315 | 3945 | 6 | 7890 | 3 | 3945
17 | 6-inch Gate Valve and Valve Box complete, in place and accepted | 2 | EA | 920 | 1840 | 2 | EA | 920 | 1840 | 9 | 8280 | 7 | 6440
18 | 6-inch Inserta Valve and Valve Box complete, in place and accepted | 2 | EA | 8350 | 16700 | 2 | EA | 8350 | 16700 | 1 | 8350 | -1 | -8350
19 | 8 x 8-inch Tapping Sleeve and Valves at various locations shown on the plans | 3 | EA | 5700 | 17100 | 3 | EA | 5700 | 17100 | 3 | 17100 | 0 | 0
20 | 6 x 6-inch Tapping Sleeve and Valves at various locations shown on the plans | 6 | EA | 4300 | 25800 | 6 | EA | 4300 | 25800 | 4 | 17200 | -2 | -8600
21 | 6 x 2-inch Tapping Sleeve and Valves at various locations shown on the plans | 1 | EA | 1700 | 1700 | 1 | EA | 1700 | 1700 | 1 | 1700 | 0 | 0
22 | 6-inch Check Valve Assemblies on existing water lines, including Insertion Valve, two 6-inch TSVs, Vault, Drain, DI Piping with restraint per Detail 6 on Sheet D-2 | 3 | EA | 19375 | 58125 | 3 | EA | 19375 | 58125 | 3 | 58125 | 0 | 0
23 | Connection No. 1 - 16-inch Water Line Tie-in including 16 x 16-inch Tapping Sleeve and 16-inch Butterfly Valve, cutting and capping existing 10-inch Water Line, and including any ancillaries that may be considered incidental complete and in place to complete the connection (sta. 0+00) | 1 | LS | 21000 | 21000 | 1 | LS | 21000 | 21000 | 1 | 21000 | 0 | 0
24 | Connection No. 2 - Connection to existing 2-inch Water Line with installation of 16 x 6 Tee, 6 x 2 Tee, 6-inch Cap, 2-inch TSV, associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 3+30) | 1 | LS | 3600 | 3600 | 1 | LS | 3600 | 3600 | 1 | 3600 | 0 | 0
25 | Connection No. 3 - Connection to existing 6-inch Water Line with installation of 16 x 6 Tee, 6-inch GV, 6-inch Cap on Existing Line, associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 19+541) | 1 | LS | 3800 | 3800 | 1 | LS | 3800 | 3800 | 1 | 3800 | 0 | 0
26 | Connection No. 4 - Connection to existing 4-inch Water Line with installation of 16 x 6 Tee, 6 x 4 Reducer, 4-inch Cap on Existing Line, associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 19+58) | 1 | LS | 4000 | 4000 | 1 | LS | 4000 | 4000 | 1 | 4000 | 0 | 0
27 | Connection No. 5 - Connection to existing 4-inch Water Line with installation of 16 x 6 Tee, 6-inch GV, 6 x 4 Reducer, 4-inch Cap on Existing Line, associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 25+40) | 1 | LS | 4200 | 4200 | 1 | LS | 4200 | 4200 | 1 | 4200 | 0 | 0
28 | Connection No. 6 - Connection to existing 4-inch Water Line with installation of 16 x 6 Tee, 6-inch GV, FH Assembly, 6 x 4 Reducer, 4-inch Cap on Existing Line, associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 48+51) | 1 | LS | 8200 | 8200 | 1 | LS | 8200 | 8200 | 1 | 8200 | 0 | 0
29 | Connection No. 7 - Connection to existing 6-inch Water Line with installation of 16 x 6 Tee, 6-inch TSV, 6-inch Cap on Existing Line, thrust restraint at end of capped line associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 53+65) | 1 | LS | 5870 | 5870 | 1 | LS | 5870 | 5870 | 1 | 5870 | 0 | 0
30 | Connection No. 8 - Connection to existing 10-inch Water Line with installation of 16 x 10 Tee, 10-inch TSV, 10-inch Cap on Existing Line, thrust restraint at end of capped line, associated pipe, any other fittings, and including any ancillaries that may be considered incidental to complete the connection (Sta. 80+48) | 1 | LS | 9200 | 9200 | 1 | LS | 9200 | 9200 | 1 | 9200 | 0 | 0
31 | 2-inch ARV Assemblies with Saddles on 16-inch WL in easement area | 1 | EA | 2500 | 2500 | 1 | EA | 2500 | 2500 | 1 | 2500 | 0 | 0
32 | 2-inch offset ARV Assemblies with Saddles on 16-inch WL in traffic area | 1 | EA | 2675 | 2675 | 1 | EA | 2675 | 2675 | 1 | 2675 | 0 | 0
33 | 1-inch ARV Assemblies on 8-inch WL | 5 | EA | 1060 | 5300 | 5 | EA | 1060 | 5300 | 4 | 4240 | -1 | -1060
34 | 2-inch Blowoff Assembly | 1 | EA | 2150 | 2150 | 1 | EA | 2150 | 2150 | 1 | 2150 | 0 | 0
35 | Fire Hydrant Assembly, complete and in place including Tee, Valve, Valve Box, Hydrant, RJ Glands/Gaskets at all connections and any other ancillaries that are considered incidental. | 14 | EA | 3737 | 52318 | 14 | EA | 3737 | 52318 | 14 | 52318 | 0 | 0
36 | 4-inch Master Meter Assembly (no. 1, 3 & 4) complete and in place including Vault, Drain, DI Piping with restraint, Isolation Valves, Insertion Valve, Turbine Meter, and any other ancillaries that are considered incidental to the installation of this pay item as detailed on Sheet C-14. | 3 | EA | 23550 | 70650 | 3 | EA | 23550 | 70650 | 3 | 70650 | 0 | 0
37 | 6-inch Master Meter Assembly (No. 2) complete and in place including Vault, Drain, DI Piping with restraint, Isolation Valves, Insertion Valve, Turbine Meter, and any other ancillaries that are considered incidental to the installation of this pay item as detailed on Sheet C-14. | 1 | EA | 32500 | 32500 | 1 | EA | 32500 | 32500 | 1 | 32500 | 0 | 0
38 | Water Meter Assembly including meter box, 10 LF of 3/4" HDPE CTS DR 9 service piping, new tapping saddle, corporation stop, associated valves and fittings, meter, excavation and backfill and restoration where directed by the Owner | 10 | EA | 1776 | 17760 | 10 | EA | 1776 | 17760 | 32 | 56832 | 22 | 39072
39 | Water Service Reconnection including installation of corporation stop, tapping saddle, 3/4" or 1" HDPE CTS DR 9 service piping, tracer wire, coupling for reconnection to existing service line or assembly, all associated valves and fittings, excavation, backfill and restoration | 75 | EA | 925 | 69375 | 75 | EA | 925 | 69375 | 65 | 60125 | -10 | -9250
40 | Additional 3/4" or 1" HDPE CTS DR 9 service piping above and beyond the 10 linear feet included in the Water Service and Water Reconnection pay items where may be required from the main line tap to the meter assembly (outside of roadways) including water service piping, tracer wire, coupling, trench excavation, backfill, and restoration. | 1000 | LF | 16 | 16000 | 1000 | LF | 16 | 16000 | 915 | 14640 | -85 | -1360
41 | Free boring 3/4" or 1" HDPE service piping under streets and roads including excavation, boring, service pipe, tracer wire, alignment, backfill, and restoration. | 1000 | LF | 27 | 27000 | 1000 | LF | 27 | 27000 | 282 | 7614 | -718 | -19386
42 | Trench Patch Pavement Repair in Streets and Roads | 600 | LF | 45 | 27000 | 600 | LF | 45 | 27000 | 0 | 0 | -600 | -27000
43 | Trench Patch Pavement Repair for Driveways | 45 | LF | 56 | 2520 | 45 | LF | 56 | 2520 | 31 | 1736 | -14 | -784
44 | Asphalt Pavement Binder in Trench (9-inch Depth) | 2700 | LF | 45 | 121500 | 2700 | LF | 45 | 121500 | 3437 | 154665 | 737 | 33165
45 | Asphalt Pavement Binder in Trench (5-inch Depth) | 700 | LF | 40 | 28000 | 700 | LF | 40 | 28000 | 691 | 27640 | -9 | -360
46 | 2-inch Pavement Milling (One Lane Width) | 3300 | SY | 3.8 | 12540 | 3300 | SY | 3.8 | 12540 | 6123.46 | 23269.148 | 2823.46 | 10729.148
47 | Asphalt Pavement Surface Full Width - (2-inch Depth) | 4700 | SY | 17 | 79900 | 4700 | SY | 17 | 79900 | 9350.87 | 158964.79 | 4650.87 | 79064.79
48 | Undercut of Water Transmission Main Trench in excess of details shown on the Plans and as Specified in order to remove unsuitable materials | 400 | CY | 21 | 8400 | 400 | CY | 21 | 8400 | 291.46 | 6120.66 | -108.54 | -2279.34
49 | Concrete Pavement Repair | 40 | SY | 175 | 7000 | 40 | SY | 175 | 7000 | 144.34 | 25259.5 | 104.34 | 18259.5
50 | Crushed Stone Installation to refill undercut of unsuitable materials | 400 | CY | 15 | 6000 | 400 | CY | 15 | 6000 | 228.66 | 3429.9 | -171.34 | -2570.1
51 | Silt Fence for Erosion and Sediment Control | 17500 | LF | 1.35 | 23625 | 17500 | LF | 1.35 | 23625 | 11156 | 15060.6 | -6344 | -8564.4
52 | Rip Rap for Check Dams for Erosion and Sediment Control | 50 | LF | 13 | 650 | 50 | LF | 13 | 650 | 0 | 0 | -50 | -650
53 | Straw Wattle for Erosion and Sediment Control | 10 | LF | 8 | 80 | 10 | LF | 8 | 80 | 0 | 0 | -10 | -80
54 | Bacteriological Test Taps | 17 | EA | 1760 | 29920 | 17 | EA | 1760 | 29920 | 12 | 21120 | -5 | -8800
55 | Concrete Encasement | 75 | LF | 30 | 2250 | 75 | LF | 30 | 2250 | 21 | 630 | -54 | -1620
56 | Flowable Fill Backfill (Line 3 - Sta 0+00 to 0+10) in Dawson Road at Pipe Connection | 5 | CY | 130 | 650 | 5 | CY | 130 | 650 | 55 | 7150 | 50 | 6500
57 | Meter Box Replacement only where directed by Owner | 10 | EA | 690 | 6900 | 10 | EA | 690 | 6900 | 1 | 690 | -9 | -6210
58 | Allowance for Flaggers and Inspector from Paducah and Louisville RR while performing pipeline installation on Bridge over RR Tracks | 1 | LS | 30000 | 30000 | 1 | LS | 30000 | 30000 | 0.26691 | 8007.168 | -0.73309 | -21992.832
59 | CO#1 - 24" hydrant extension | N/A | N/A | N/A | N/A | 2 | EA | 1045.68 | 2091.36 | 3 | 3137.04 | 1 | 1045.68
60 | CO#1 - 30" hydrant extension | N/A | N/A | N/A | N/A | 1 | EA | 1528.68 | 1528.68 | 1 | 1528.68 | 0 | 0
61 | CO#1 - Labor/Equip for two hydrant swap outs | N/A | N/A | N/A | N/A | 1 | LS | 3022.89 | 3022.89 | 1 | 3022.89 | 0 | 0
62 | CO#1 - Cutting out 24" storm casing | N/A | N/A | N/A | N/A | 1 | LS | 2472.2 | 2472.2 | 1 | 2472.2 | 0 | 0
63 | CO#1 - 2" service connection Sta.29+85 Line 1 | N/A | N/A | N/A | N/A | 1 | LS | 3336.7 | 3336.7 | 1 | 3336.7 | 0 | 0
64 | CO#1 - Additional cost for Fire Hydrants | N/A | N/A | N/A | N/A | 14 | EA | 199 | 2786 | 14 | 2786 | 0 | 0
65 | CO#2 - APTUS Cost less the $95k in Line Item No.9 | N/A | N/A | N/A | N/A | 1 | LS | 112000 | 112000 | 1 | 112000 | 0 | 0
66 | CO#2 - JSJ Attorney Fees | N/A | N/A | N/A | N/A | 1 | LS | 5200 | 5200 | 1 | 5200 | 0 | 0
67 | CO#2 - JSJ labor and equipment | N/A | N/A | N/A | N/A | 1 | LS | 3711.32 | 3711.32 | 1 | 3711.32 | 0 | 0
68 | CO#2 - Traffic Control | N/A | N/A | N/A | N/A | 1 | LS | 6750 | 6750 | 0 | 0 | -1 | -6750
69 | CO#2 - JSJ Overhead & Profit (10%) | N/A | N/A | N/A | N/A | 1 | LS | 22266.13 | 22266.13 | 1 | 22266.13 | 0 | 0
70 | CO#2 - APTUS additional costs due to downtime | N/A | N/A | N/A | N/A | 50 | HR | 450 | 22500 | 0 | 0 | -50 | -22500
SCHEDULE A TOTALS = |  |  |  |  | 1656593 |  |  |  | 1844258.28 |  | 1880520.726 |  | 36262.446

## Soft Costs
Engineering Costs - Hethcoat & Davis
Task | Contract A | Contract B
Study/Report Phase | 13500 | 4500
Engineering Design | 100000 | 31160
Engineering Construction Administration | 31500 | 10331.11
Resident Project Inspection | 70000 | 22000
Totals = | 215000 | 67991.11
Loan Costs of Closing
Bond Counsel - Rubin & Hays | 13140.76
Local Counsel - Todd Wetzel | 6519.75
Easements | 2218
Woodall Agency - Bonding | 4072
Planters Bank - Loan Fee | 1172
Planters Bank Interest | 237.73
Planters Bank Interest | 833.81
Planters Bank Interest | 1472.04
Planters Bank Interest | 3504.1
Planters Bank Interest | 4804.77
Planters Bank Interest | 5251.93
Planters Bank Interest | 6157.32
Planters Bank Interest | 6680.64
Planters Bank Interest | 7440.79
Planters Bank Interest | 8586.53
Planters Bank Interest | 13485.23
85577.4