## Final Adjusting Change Order
2013 Water System Improvements: Contract B - Skyline Tank Rehabilitation
City of Princeton, KY (Princeton Water & Wastewater Commission)
H & D Project No. 1037-07
Bid Date: Tuesday, May 22, 2018, at 11:00 a.m. local time
Contract Awarded To: Preferred Sandblasting & Painting, LLC
Final Adjusting Change Order (Change Order #2) Supplemental Information
BASE BID: UNIT PRICE BID
Item | Description | Original Contract Amount |  |  |  | Revised Contract Amount With Previously Approved Change Orders |  |  |  | Construction/As-Built Amounts |  | Amount Over/Under
|  | Qty | Unit | Unit Price | Bid Value ($) | Qty | Unit | Unit Price | Value ($) | Actual Qty. | Actual Value ($) | Qty. | Amount ($)
1 | Exterior Water Tank Painting including preparation - (Zinc/Urethane/Fluoropolymer System) | 1 | LS | 208900 | 208900 | 1 | LS | 208900 | 208900 | 1 | 208900 | 0 | 0
2 | Interior Water Tank Painting including preparation (Zinc Rich Primer/High Solids Epoxy System) | 1 | LS | 60000 | 60000 | 1 | LS | 60000 | 60000 | 1 | 60000 | 0 | 0
3 | Interior Dry Riser Painting including prepartion (Zinc Rich Primer/High Solids Epoxy System) | 1 | LS | 9500 | 9500 | 1 | LS | 9500 | 9500 | 1 | 9500 | 0 | 0
4 | Replacement of Top 6 Ladder Rungs | 1 | LS | 300 | 300 | 1 | LS | 300 | 300 | 1 | 300 | 0 | 0
5 | Installation of New Safety Climb Cable System to repalce existing system on ladder in dry riser | 1 | LS | 2800 | 2800 | 1 | LS | 2800 | 2800 | 1 | 2800 | 0 | 0
6 | Installation of New Safety Climb Cable System to repalce existing system on ladder in water tank | 1 | LS | 2200 | 2200 | 1 | LS | 2200 | 2200 | 1 | 2200 | 0 | 0
7 | Installation of New 1" Thick, Aluminum Jacketed Insulation on 12" Inlet/Outlet Water Piping in Dry Riser | 1 | LS | 6500 | 6500 | 1 | LS | 6500 | 6500 | 1 | 6500 | 0 | 0
8 | Interior Seam Sealing at roof | 150 | LF | 4.5 | 675 | 150 | LF | 4.5 | 675 | 13 | 58.5 | -137 | -616.5
9 | Replace existing overflow pipe screen with new 24 mesh non-corrosive stainless steel insect screen and install new flap valve | 1 | LS | 300 | 300 | 1 | LS | 300 | 300 | 1 | 300 | 0 | 0
10 | Welding repairs where directed by the Owner or Engineer | 240 | Inches | 7 | 1680 | 240 | Inches | 7 | 1680 | 0 | 0 | -240 | -1680
11 | Interior Seam Sealing and/or Pit Sealing where directed by the Engineer | 400 | Inches | 4 | 1600 | 400 | Inches | 4 | 1600 | 0 | 0 | -400 | -1600
12 | Replace existing roof vent screen with new 24 mesh non-corrosive stainless steel insect screen | 1 | LS | 300 | 300 | 1 | LS | 300 | 300 | 1 | 300 | 0 | 0
13 | Install new Chain Link Fence around Tank Site | 1 | LS | 22000 | 22000 | 1 | LS | 22000 | 22000 | 1 | 22000 | 0 | 0
14 | Re-grade existing gravel access drive and install Compact Crushed Stone (4" Thickness) | 1 | LS | 5000 | 5000 | 1 | LS | 5000 | 5000 | 1 | 5000 | 0 | 0
15 | Modular Building complete and in place including Concrete Pad | 1 | LS | 2000 | 2000 | 1 | LS | 2000 | 2000 | 1 | 2000 | 0 | 0
16 | Mobilization and Bonds | 1 | LS | 3500 | 3500 | 1 | LS | 3500 | 3500 | 1 | 3500 | 0 | 0
17 | Tank Sterilization | 1 | LS | 600 | 600 | 1 | LS | 600 | 600 | 1 | 600
18 | CO#1 - replace roof hatch | N/A | N/A | N/A | N/A | 1 | LS | 3500 | 3500 | 1 | 3500
19 | CO#1 - replace roof vent | N/A | N/A | N/A | N/A | 1 | LS | 5100 | 5100 | 1 | 5100
20 | CO#1 - repair weld burns and paint from replacing roof hatch and vent | N/A | N/A | N/A | N/A | 1 | LS | 1500 | 1500 | 1 | 1500
TOTALS = |  |  |  |  | 327855 |  |  |  | 337955 |  | 334058.5 |  | -3896.5