## Schedule C1
Kentucky Power Company
Case No. 2020-00174
Construction Projects
For the Five Years Ended December 31, 2019
Schedule C1
Budget to Actual Variance Information - 2015 through 2019 - (Under)/Over Budget
| Project Information |  |  |  |  | Actual Information - 2015 through 2019 | [5 empty] | Budget Information - 2015 through 2019 | [5 empty] | 2015 |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | Total
Line No. | GLBU | PROJECT_ID | Project DESCR | Date Actual Start (1) | Date Actual End (2) | 2015 | 2016 | 2017 | 2018 | 2019 | Total | 2015 | 2016 | 2017 | 2018 | 2019 | Total | $ | % of Budget | $ | % of Budget | $ | % of Budget | $ | % of Budget | $ | % of Budget | $ | % of Budget
1 | 110 | 000007818 | KP/Small Local Asset Improv | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1544393.81 | 1959643.91 | 3330130.15 | 4089610.38 | 9196871.74 | 20120649.99 | 2708274 | 1580226 | 1758586 | 4317225 | 6849535 | 17213846 | -1163880.19 | -42.97% | 379417.91 | 24.01% | 1571544.15 | 89.36% | -227614.62 | -5.272% | 2347336.74 | 34.27% | 2906803.99 | 16.89%
2 | 110 | EON011326 | Line Transformer/Kp | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 3584312.01 | 2855592.73 | 3326170.75 | 3292740.4 | 4169778.13 | 17228594.02 | 2427453 | 2340889 | 2427931 | 2365793 | 2437289 | 11999355 | 1156859.01 | 47.66% | 514703.73 | 21.99% | 898239.75 | 37% | 926947.4 | 39.18% | 1732489.13 | 71.08% | 5229239.02 | 43.58%
3 | 110 | 000009160 | Forestry KP D Base R W | Charges Began Prior to Jan 2015 | 6/1/2019 | 5699747.91 | 3718526.09 | 3789067.12 | 3124617.13 | 145069.9 | 16477028.15 | 2637469 | 2433956 | 2510310 | 3504729 | 34941 | 11121405 | 3062278.91 | 116.1% | 1284570.09 | 52.78% | 1278757.12 | 50.94% | -380111.87 | -10.85% | 110128.9 | 315.2% | 5355623.15 | 48.16%
4 | 110 | EDN014651 | Ds/Kp/Cs-New Customers | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 3335645.71 | 3210096.17 | 2794003.84 | 2799137.59 | 3205327.67 | 15344210.98 | 4155257 | 4174634 | 2556007 | 2478649 | 3550848 | 16915395 | -819611.29 | -19.72% | -964537.83 | -23.1% | 237996.84 | 9.311% | 320488.59 | 12.93% | -345520.33 | -9.731% | -1571184.02 | -9.288%
5 | 110 | 000001818 | KY/Svc Restoration NonMjr Evt | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1861640.65 | 1853385.96 | 3010056.02 | 3735553.75 | 4814165.52 | 15274801.9 | 1624657 | 1707031 | 1855290 | 1865612 | 3090207 | 10142797 | 236983.65 | 14.59% | 146354.96 | 8.574% | 1154766.02 | 62.24% | 1869941.75 | 100.2% | 1723958.52 | 55.79% | 5132004.9 | 50.6%
6 | 110 | 000005234 | KyPCo-D Capital Software Dev | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 2244966.01 | 2234450.04 | 2512743.98 | 3570402.201 | 3166476.01 | 13729038.241 | 0 | 0 | 0 | 0 | 0 | 0 | 2244966.01 | n.m. | 2234450.04 | n.m. | 2512743.98 | n.m. | 3570402.201 | n.m. | 3166476.01 | n.m. | 13729038.241 | n.m.
7 | 110 | 000007599 | KP-Failed Equip No Outage | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1865796.47 | 2831098.83 | 2075336.53 | 2226747.2 | 3059416.88 | 12058395.91 | 1179594 | 1142649 | 1304570 | 1310580 | 2918934 | 7856327 | 686202.47 | 58.17% | 1688449.83 | 147.8% | 770766.53 | 59.08% | 916167.2 | 69.91% | 140482.88 | 4.813% | 4202068.91 | 53.49%
8 | 110 | EDN100033 | Ds/Kp/C&I New | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 2276665.02 | 2424539.52 | 2258601.01 | 2314915.6 | 2646558.92 | 11921280.07 | 1398413 | 2265066 | 1017530 | 987583 | 2223282 | 7891874 | 878252.02 | 62.8% | 159473.52 | 7.041% | 1241071.01 | 122% | 1327332.6 | 134.4% | 423276.92 | 19.04% | 4029406.07 | 51.06%
9 | 110 | TREEREL19 | ROW Capital widening & removal | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 11096862.67 | 11096862.67 | 0 | 0 | 0 | 0 | 7303071 | 7303071 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3793791.67 | 51.95% | 3793791.67 | 51.95%
10 | 110 | EDN014680 | Ds-Kp-Ai Pole Replacement | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 2513684.06 | 1258024.66 | 838090.16 | 3274647.1 | 2154427.2 | 10038873.18 | 977599 | 1339520 | 2116755 | 3859086 | 2737897 | 11030857 | 1536085.06 | 157.1% | -81495.34 | -6.084% | -1278664.84 | -60.41% | -584438.9 | -15.14% | -583469.8 | -21.31% | -991983.82 | -8.993%
11 | 110 | ITCW11004 | KY Next Generation Radio Sys | 4/1/2017 | Charges Continued After Dec 2019 |  |  | 1108843.68 | 35132.57 | 5423767.51 | 6567743.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1108843.68 | n.m. | 35132.57 | n.m. | 5423767.51 | n.m. | 6567743.76 | n.m.
12 | 110 | 000016528 | KYCutout-Arrester | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 |  | 928814.84 | 1167879.18 | 1965461.66 | 2055322.59 | 6117478.27 | 556359 | 549528 | 594640 | 1366391 | 1527534 | 4594452 | -556359 | -100% | 379286.84 | 69.02% | 573239.18 | 96.4% | 599070.66 | 43.84% | 527788.59 | 34.55% | 1523026.27 | 33.15%
13 | 110 | TREEREL18 | ROW Capital widening & removal | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 5800827.92 | 207427.86 | 6008255.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5800827.92 | n.m. | 207427.86 | n.m. | 6008255.78 | n.m.
14 | 110 | DR15K02B0 | KP/Princess Station DStation | 5/1/2018 | Charges Continued After Dec 2019 |  |  |  | 823609.81 | 4921431.416 | 5745041.226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 823609.81 | n.m. | 4921431.416 | n.m. | 5745041.226 | n.m.
15 | 110 | EDN014720 | Ds-Kp-Ai Recloser Replacement | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1210393.68 | 1234451.14 | 829206.53 | 1125173.25 | 1191423.86 | 5590648.46 | 930388 | 898645 | 716920 | 707953 | 1270558 | 4524464 | 280005.68 | 30.1% | 335806.14 | 37.37% | 112286.53 | 15.66% | 417220.25 | 58.93% | -79134.14 | -6.228% | 1066184.46 | 23.56%
16 | 110 | EDN100577 | Ds-Kp-Ai Ckt Inspections | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 219900.18 | 1012209.03 | 1125927.15 | 1002217.69 | 1233400.35 | 4593654.4 | 0 | 1375486 | 1510008 | 1504505 | 1330458 | 5720457 | 219900.18 | n.m. | -363276.97 | -26.41% | -384080.85 | -25.44% | -502287.31 | -33.39% | -97057.65 | -7.295% | -1126802.6 | -19.7%
17 | 110 | EDN011333 | Customer Meter/Kp | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 862622.03 | 1262408.16 | 906579.23 | 616111.64 | 659050.63 | 4306771.69 | 1209121 | 939350 | 834163 | 884425 | 815111 | 4682170 | -346498.97 | -28.66% | 323058.16 | 34.39% | 72416.23 | 8.681% | -268313.36 | -30.34% | -156060.37 | -19.15% | -375398.31 | -8.018%
18 | 110 | ITCB11000 | KENTUCKY POWER - DIST | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 985805.79 | 855944.87 | 691896.15 | 1122604.55 | 638681.62 | 4294932.98 | 0 | 0 | 0 | 0 | 0 | 0 | 985805.79 | n.m. | 855944.87 | n.m. | 691896.15 | n.m. | 1122604.55 | n.m. | 638681.62 | n.m. | 4294932.98 | n.m.
19 | 110 | IT110BILL | Corp Prgrm Billing - KP Distri | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 2017773.31 | 431990.74 | 1219442.56 | 3669206.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2017773.31 | n.m. | 431990.74 | n.m. | 1219442.56 | n.m. | 3669206.61 | n.m.
20 | 110 | P18025001 | Kewanee Station - Baseline Wor | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 483499.47 | 2564136.48 | 3047635.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 483499.47 | n.m. | 2564136.48 | n.m. | 3047635.95 | n.m.
21 | 110 | P11161006 | D/KP Stanville Station KPCo | 7/1/2015 | 8/1/2019 | 3486.22 | 77727.55 | 220728.29 | 2657028.76 | 86497.01 | 3045467.83 | 0 | 222342 | 144339 | 2707765 | 9754 | 3084200 | 3486.22 | n.m. | -144614.45 | -65.04% | 76389.29 | 52.92% | -50736.24 | -1.874% | 76743.01 | 786.8% | -38732.17 | -1.256%
22 | 110 | 000025229 | 2018 Gen Plt Cap Blkt - KYPC-D | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1096100.6 | 1866210.29 | 2962310.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1096100.6 | n.m. | 1866210.29 | n.m. | 2962310.89 | n.m.
23 | 110 | KY5YCYCLE | KY D 2017-00179 | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2952531.33 | 2952531.33 | 0 | 0 | 0 | 0 | 3827319 | 3827319 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -874787.67 | -22.86% | -874787.67 | -22.86%
24 | 110 | EDN014694 | Ds-Kp-Ai Other Make Ready | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 489702.66 | -889006.15 | 883506.4 | 1475972.9 | 713622.11 | 2673797.92 | 346340 | 270915 | 244878 | 249038 | 402475 | 1513646 | 143362.66 | 41.39% | -1159921.15 | -428.1% | 638628.4 | 260.8% | 1226934.9 | 492.7% | 311147.11 | 77.31% | 1160151.92 | 76.65%
25 | 110 | P11063003 | TKYVicco Station Improvement | Charges Began Prior to Jan 2015 | 3/1/2019 | 495089.69 | 505575.08 | 1473289.53 | 17038.49 | 2189.15 | 2493181.94 | 1169024 | -8197 | 141592 | 0 | 0 | 1302419 | -673934.31 | -57.65% | 513772.08 | -6268% | 1331697.53 | 940.5% | 17038.49 | n.m. | 2189.15 | n.m. | 1190762.94 | 91.43%
26 | 110 | A16928013 | Mobile KPCo 118 Purchase | 7/1/2017 | 3/1/2019 |  |  | 1211927.41 | 1108482.28 | 109282.22 | 2429691.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1211927.41 | n.m. | 1108482.28 | n.m. | 109282.22 | n.m. | 2429691.91 | n.m.
27 | 110 | 000004737 | KPSectionalizing Program | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 283314.49 | 454586.9 | 47385.59 | 785162.79 | 831334.8 | 2401784.57 | 0 | 0 | 0 | 0 | 674130 | 674130 | 283314.49 | n.m. | 454586.9 | n.m. | 47385.59 | n.m. | 785162.79 | n.m. | 157204.8 | 23.32% | 1727654.57 | 256.3%
28 | 110 | B110KYSRR | D/KY/Non-Specific Work - Sta | 11/1/2016 | Charges Continued After Dec 2019 |  | 31483.19 | 715273.99 | 694499.54 | 912988.96 | 2354245.68 | 0 | 0 | 0 | 1442302 | 953626 | 2395928 | 0 | n.m. | 31483.19 | n.m. | 715273.99 | n.m. | -747802.46 | -51.85% | -40637.04 | -4.261% | -41682.32 | -1.74%
29 | 110 | EDN012370 | Ds/Kp/Public Relocation | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 480321.98 | 401894.13 | 1270.84 | 752217.3 | 486999.36 | 2122703.61 | 249390 | 60964 | 2090923 | 2086548 | 2376977 | 6864802 | 230931.98 | 92.6% | 340930.13 | 559.2% | -2089652.16 | -99.94% | -1334330.7 | -63.95% | -1889977.64 | -79.51% | -4742098.39 | -69.08%
30 | 110 | DCTSUVLKY | KY CATS Monthly Unvouch Liab | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 531417.32 | -262696.24 | -383147.73 | 1735717.14 | 259951.18 | 1881241.67 | 0 | 0 | 0 | 0 | 0 | 0 | 531417.32 | n.m. | -262696.24 | n.m. | -383147.73 | n.m. | 1735717.14 | n.m. | 259951.18 | n.m. | 1881241.67 | n.m.
31 | 110 | 000025820 | Kentucky Power State Office | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 984.2 | 1842610.84 | 1843595.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 984.2 | n.m. | 1842610.84 | n.m. | 1843595.04 | n.m.
32 | 110 | DMS15KK07 | KYMETStorm 71315 | 7/1/2015 | 1/1/2016 | 830365.81 | 967949.29 |  |  |  | 1798315.1 | 0 | 0 | 0 | 0 | 0 | 0 | 830365.81 | n.m. | 967949.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1798315.1 | n.m.
33 | 110 | A15702051 | Pikeville Stn RepBank#1 | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 4086.27 | 765874.35 | 999432.22 | 1769392.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 4086.27 | n.m. | 765874.35 | n.m. | 999432.22 | n.m. | 1769392.84 | n.m.
34 | 110 | A16928014 | Skid Station KPCo 1002 Purchas | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 457746.16 | 980687.65 | 232200.47 | 1670634.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 457746.16 | n.m. | 980687.65 | n.m. | 232200.47 | n.m. | 1670634.28 | n.m.
35 | 110 | IT1101421 | Maximo Imp - KYP - D | 3/1/2016 | Charges Continued After Dec 2019 |  | 178843.92 | 339019.22 | 547153.3 | 605026.08 | 1670042.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 178843.92 | n.m. | 339019.22 | n.m. | 547153.3 | n.m. | 605026.08 | n.m. | 1670042.52 | n.m.
36 | 110 | DR18K03B5 | Breaker Rpl - S Pikeville | 5/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1283232.09 | 202700.73 | 1485932.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1283232.09 | n.m. | 202700.73 | n.m. | 1485932.82 | n.m.
37 | 110 | P11028021 | DKPBreaks-D Portion of Elkho | Charges Began Prior to Jan 2015 | 1/1/2017 | 1174471.54 | 182648.43 | -17000 |  |  | 1340119.97 | 278243 | 238030 | 0 | 0 | 0 | 516273 | 896228.54 | 322.1% | -55381.57 | -23.27% | -17000 | n.m. | 0 | n.m. | 0 | n.m. | 823846.97 | 159.6%
38 | 110 | 000024101 | KYPCo-D General Plt Cap Blkt | 3/1/2016 | 1/1/2018 |  | 790143.13 | 528106.03 | 6168.57 |  | 1324417.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 790143.13 | n.m. | 528106.03 | n.m. | 6168.57 | n.m. | 0 | n.m. | 1324417.73 | n.m.
39 | 110 | EDN015042 | Ds-Kp-Small Wire Repl Ovhd | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 60297.34 | 218202.67 | 130494.23 | 383665.93 | 463033.17 | 1255693.34 | 0 | 0 | 0 | 222923 | 426949 | 649872 | 60297.34 | n.m. | 218202.67 | n.m. | 130494.23 | n.m. | 160742.93 | 72.11% | 36084.17 | 8.452% | 605821.34 | 93.22%
40 | 110 | EDN014658 | Ds/Kp/Cs-Upgrades | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 297262.15 | 296814.09 | 226686.7 | 172256.35 | 261639.36 | 1254658.65 | 62402 | 62788 | 46466 | 42029 | 164801 | 378486 | 234860.15 | 376.4% | 234026.09 | 372.7% | 180220.7 | 387.9% | 130227.35 | 309.9% | 96838.36 | 58.76% | 876172.65 | 231.5%
41 | 110 | 000002241 | KP-Damage Claims-Reimburse | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 212367.56 | 300964.29 | 230250.25 | 237814.74 | 234703.53 | 1216100.37 | -188291 | 58439 | -28541 | -26791 | 110887 | -74297 | 400658.56 | -212.8% | 242525.29 | 415% | 258791.25 | -906.7% | 264605.74 | -987.7% | 123816.53 | 111.7% | 1290397.37 | -1737%
42 | 110 | DR18K04B0 | Pikeville Sta - Trans upgrade | 8/1/2018 | Charges Continued After Dec 2019 |  |  |  | 341023.98 | 863555.66 | 1204579.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 341023.98 | n.m. | 863555.66 | n.m. | 1204579.64 | n.m.
43 | 110 | DR15K02A0 | KP/Princess Station D Line | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 737337.68 | 403072.35 | 1140410.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 737337.68 | n.m. | 403072.35 | n.m. | 1140410.03 | n.m.
44 | 110 | KYCR012DL | KP/VoltVar Circ Reconfig DLine | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 336640.38 | 452536.59 | 64188.7 | 185457.02 | 81473.15 | 1120295.84 | 0 | 0 | 0 | 0 | 0 | 0 | 336640.38 | n.m. | 452536.59 | n.m. | 64188.7 | n.m. | 185457.02 | n.m. | 81473.15 | n.m. | 1120295.84 | n.m.
45 | 110 | A15710004 | Ashland SC Tele Modernization | 9/1/2016 | 5/1/2018 |  | 26473.87 | 1041844.26 | 23114.04 |  | 1091432.17 | 0 | 0 | 56540 | 0 | 0 | 56540 | 0 | n.m. | 26473.87 | n.m. | 985304.26 | 1743% | 23114.04 | n.m. | 0 | n.m. | 1034892.17 | 1830%
46 | 110 | P12057001 | T/KP/BECKHAM-(KPCo) | Charges Began Prior to Jan 2015 | 11/1/2018 | -1115.21 | 918.71 | 1057533.95 | 33137.79 |  | 1090475.24 | 0 | 0 | 0 | 0 | 0 | 0 | -1115.21 | n.m. | 918.71 | n.m. | 1057533.95 | n.m. | 33137.79 | n.m. | 0 | n.m. | 1090475.24 | n.m.
47 | 110 | SI110KYRE | DB/SI/KyP-KENTUCKY SYS REHAB | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 579833.45 | 373749.53 | 100694.64 | -11732.42 | 1755.18 | 1044300.38 | 0 | 0 | 0 | 0 | 0 | 0 | 579833.45 | n.m. | 373749.53 | n.m. | 100694.64 | n.m. | -11732.42 | n.m. | 1755.18 | n.m. | 1044300.38 | n.m.
48 | 110 | DR19K02A0 | Ashland DA 2019 - D line | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1001143.91 | 1001143.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1001143.91 | n.m. | 1001143.91 | n.m.
49 | 110 | DR14K03B0 | KP/Haddix Sta - D Sta. 3rd Brk | 8/1/2015 | 9/1/2017 | 3284.93 | 812912 | 138141.47 |  |  | 954338.4 | 0 | 0 | 0 | 0 | 0 | 0 | 3284.93 | n.m. | 812912 | n.m. | 138141.47 | n.m. | 0 | n.m. | 0 | n.m. | 954338.4 | n.m.
50 | 110 | DMS17KK01 | KYMEWind 3117 | 3/1/2017 | 11/1/2017 |  |  | 945096.07 |  |  | 945096.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 945096.07 | n.m. | 0 | n.m. | 0 | n.m. | 945096.07 | n.m.
51 | 110 | 000024645 | KYPCo-D General Plt Cap Blkt | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 698962.89 | 173478.84 | 396.9 | 872838.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 698962.89 | n.m. | 173478.84 | n.m. | 396.9 | n.m. | 872838.63 | n.m.
52 | 110 | A13002031 | D/KP/S.Pikeville-ReplTrf Bank1 | 5/1/2015 | 1/1/2018 | 761100.32 | 60227.69 | 43675.91 | -6795.75 |  | 858208.17 | 0 | 0 | 0 | 0 | 0 | 0 | 761100.32 | n.m. | 60227.69 | n.m. | 43675.91 | n.m. | -6795.75 | n.m. | 0 | n.m. | 858208.17 | n.m.
53 | 110 | P11161002 | D/KP/S.PIKEV -Remote End | 9/1/2015 | 8/1/2019 | 1809.15 | 50432.23 | 132539.47 | 585543.55 | 67952.08 | 838276.48 | 0 | 97376 | 50877 | 473057 | 0 | 621310 | 1809.15 | n.m. | -46943.77 | -48.21% | 81662.47 | 160.5% | 112486.55 | 23.78% | 67952.08 | n.m. | 216966.48 | 34.92%
54 | 110 | DR18K02A0 | Hazard 2018 DA Plan | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 782023.02 | 782023.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 782023.02 | n.m. | 782023.02 | n.m.
55 | 110 | 000025522 | Lovely\Lovely Sectionalizing | 6/1/2018 | Charges Continued After Dec 2019 |  |  |  | 344446.15 | 430200.15 | 774646.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 344446.15 | n.m. | 430200.15 | n.m. | 774646.3 | n.m.
56 | 110 | A13212036 | Ashland (KY) Telecom Pilot Wir | 11/1/2015 | 5/1/2019 | 115.75 | 16024.57 | 704218.23 | 13923.97 | 3998.69 | 738281.21 | 0 | 0 | 0 | 0 | 0 | 0 | 115.75 | n.m. | 16024.57 | n.m. | 704218.23 | n.m. | 13923.97 | n.m. | 3998.69 | n.m. | 738281.21 | n.m.
57 | 110 | 000007615 | KP-Cust Req Relocate | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 178765.69 | 203394.79 | 160230.97 | 46726.92 | 134290.16 | 723408.53 | 103596 | 102838 | 105759 | 107114 | 232736 | 652043 | 75169.69 | 72.56% | 100556.79 | 97.78% | 54471.97 | 51.51% | -60387.08 | -56.38% | -98445.84 | -42.3% | 71365.53 | 10.94%
58 | 110 | IT1101323 | High Avail Data Ctr-KYP-D | Charges Began Prior to Jan 2015 | 3/1/2016 | 524351.85 | 183092.44 |  |  |  | 707444.29 | 0 | 0 | 0 | 0 | 0 | 0 | 524351.85 | n.m. | 183092.44 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 707444.29 | n.m.
59 | 110 | DP14K02B0 | KP/Raccoon Sta - 30 MVA 138-34 | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 64563.59 | 639872.63 | 704436.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 64563.59 | n.m. | 639872.63 | n.m. | 704436.22 | n.m.
60 | 110 | DP15K05L0 | Raccoon Station site purchase | 12/1/2015 | Charges Continued After Dec 2019 | 270774.22 | -222225.27 | 638992.06 | 812.37 |  | 688353.38 | 0 | 0 | 0 | 0 | 0 | 0 | 270774.22 | n.m. | -222225.27 | n.m. | 638992.06 | n.m. | 812.37 | n.m. | 0 | n.m. | 688353.38 | n.m.
61 | 110 | A15710030 | Beavercreek TS TTMP | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 467454.47 | 212242.63 | 679697.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 467454.47 | n.m. | 212242.63 | n.m. | 679697.1 | n.m.
62 | 110 | DR14K03A0 | KP/Haddix Sta - D Line 3rd Brk | 6/1/2016 | 7/1/2017 |  | 560518.99 | 97146.07 |  |  | 657665.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 560518.99 | n.m. | 97146.07 | n.m. | 0 | n.m. | 0 | n.m. | 657665.06 | n.m.
63 | 110 | DR14K01A0 | KP/Soft Shell Beckham Tie Line | Charges Began Prior to Jan 2015 | 11/1/2015 | 655672.14 |  |  |  |  | 655672.14 | 456789 | 0 | 0 | 0 | 0 | 456789 | 198883.14 | 43.54% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 198883.14 | 43.54%
64 | 110 | EDN100044 | Ds/Kp/C&I Upgrades | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 178292.91 | 121167.96 | 107943.06 | 131836.06 | 106813.27 | 646053.26 | 0 | 0 | 0 | 0 | 86240 | 86240 | 178292.91 | n.m. | 121167.96 | n.m. | 107943.06 | n.m. | 131836.06 | n.m. | 20573.27 | 23.86% | 559813.26 | 649.1%
65 | 110 | P11161021 | Stanville DLINE Components | 7/1/2017 | 11/1/2019 |  |  | 72454.37 | 471649.68 | 96611.17 | 640715.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 72454.37 | n.m. | 471649.68 | n.m. | 96611.17 | n.m. | 640715.22 | n.m.
66 | 110 | A13212028 | Second Fork - Telecom Legacy | 8/1/2015 | 4/1/2018 | 214316.7 | 259753.73 | 151073.4 | 242 |  | 625385.83 | 0 | 0 | 0 | 0 | 0 | 0 | 214316.7 | n.m. | 259753.73 | n.m. | 151073.4 | n.m. | 242 | n.m. | 0 | n.m. | 625385.83 | n.m.
67 | 110 | A13212029 | Elwood (KP) - Telecom Legacy | 9/1/2015 | 8/1/2018 | 170514.1 | 270878.28 | 123192.77 | 49400.99 |  | 613986.14 | 0 | 0 | 0 | 0 | 0 | 0 | 170514.1 | n.m. | 270878.28 | n.m. | 123192.77 | n.m. | 49400.99 | n.m. | 0 | n.m. | 613986.14 | n.m.
68 | 110 | 000025473 | Purchase Hazard Service Center | 12/1/2017 | 7/1/2018 |  |  | 596356.47 | 5684.59 |  | 602041.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 596356.47 | n.m. | 5684.59 | n.m. | 0 | n.m. | 602041.06 | n.m.
69 | 110 | A16928010 | Ashland Srvc Purch Sp Transf | 12/1/2017 | 1/1/2019 |  |  | 337807.94 | 249639.95 | 2672.51 | 590120.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 337807.94 | n.m. | 249639.95 | n.m. | 2672.51 | n.m. | 590120.4 | n.m.
70 | 110 | DR14K05A0 | KP/Louisa Station Retire DLine | Charges Began Prior to Jan 2015 | 10/1/2017 | 262674.17 | 208815.48 | 113960.38 |  |  | 585450.03 | 0 | 0 | 0 | 0 | 0 | 0 | 262674.17 | n.m. | 208815.48 | n.m. | 113960.38 | n.m. | 0 | n.m. | 0 | n.m. | 585450.03 | n.m.
71 | 110 | DR19K04A0 | Pikeville DA 2019 - D line | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 556826.61 | 556826.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 556826.61 | n.m. | 556826.61 | n.m.
72 | 110 | 000021855 | KYPCO\Haz Replace Co | Charges Began Prior to Jan 2015 | 10/1/2017 | 363175.64 | 189083.82 | -3242.4 |  |  | 549017.06 | 0 | 0 | 0 | 0 | 0 | 0 | 363175.64 | n.m. | 189083.82 | n.m. | -3242.4 | n.m. | 0 | n.m. | 0 | n.m. | 549017.06 | n.m.
73 | 110 | DMS19KK01 | KP/ME/Wind Storm 02/24/19 | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 534591.08 | 534591.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 534591.08 | n.m. | 534591.08 | n.m.
74 | 110 | A16928012 | Pikeville Purchase Spare | 8/1/2017 | 1/1/2019 |  |  | 119149.01 | 394738.33 | 3.09 | 513890.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 119149.01 | n.m. | 394738.33 | n.m. | 3.09 | n.m. | 513890.43 | n.m.
75 | 110 | DP14K04B0 | KPPrestonburg Sta Upg Reg | 10/1/2015 | 7/1/2017 | 7425.16 | 489226.06 | 329.15 |  |  | 496980.37 | 0 | 0 | 0 | 0 | 0 | 0 | 7425.16 | n.m. | 489226.06 | n.m. | 329.15 | n.m. | 0 | n.m. | 0 | n.m. | 496980.37 | n.m.
76 | 110 | DR19K06B0 | Breaker Repl - Ashland | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 481201.09 | 481201.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 481201.09 | n.m. | 481201.09 | n.m.
77 | 110 | A17212002 | Hayward RTU Replacement | 7/1/2018 | Charges Continued After Dec 2019 |  |  |  | 23803.41 | 456749.66 | 480553.07 | 0 | 0 | 0 | 0 | 240055 | 240055 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23803.41 | n.m. | 216694.66 | 90.27% | 240498.07 | 100.2%
78 | 110 | P16113007 | Coalton Line Relaying | 12/1/2016 | Charges Continued After Dec 2019 |  | 3802.47 | 3003.32 | 180930.76 | 284568.3 | 472304.85 | 0 | 0 | 0 | 0 | 38814 | 38814 | 0 | n.m. | 3802.47 | n.m. | 3003.32 | n.m. | 180930.76 | n.m. | 245754.3 | 633.2% | 433490.85 | 1117%
79 | 110 | DX16K02A0 | Coalton Sta - US RT 60 PPR | 2/1/2017 | Charges Continued After Dec 2019 |  |  | 270926.23 | 52701.02 | 146866.72 | 470493.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 270926.23 | n.m. | 52701.02 | n.m. | 146866.72 | n.m. | 470493.97 | n.m.
80 | 110 | A15702009 | Prestonsburg Rpl OCB C | 5/1/2017 | 10/1/2018 |  |  | 418910.69 | 49550.29 |  | 468460.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 418910.69 | n.m. | 49550.29 | n.m. | 0 | n.m. | 468460.98 | n.m.
81 | 110 | DR19K06B1 | Breaker Repl - Lovely | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 451477.36 | 451477.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 451477.36 | n.m. | 451477.36 | n.m.
82 | 110 | A13212039 | Argentum Telecom Legacy Circui | 9/1/2016 | 1/1/2018 |  | 2852.62 | 442339.71 | 173.49 |  | 445365.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 2852.62 | n.m. | 442339.71 | n.m. | 173.49 | n.m. | 0 | n.m. | 445365.82 | n.m.
83 | 110 | A13002034 | D/KP/Kimper-ReplFailedTrf 1B | 9/1/2015 | 1/1/2018 | 411983.84 | 15913.81 | 17885.45 | -16141.83 |  | 429641.27 | 0 | 0 | 0 | 0 | 0 | 0 | 411983.84 | n.m. | 15913.81 | n.m. | 17885.45 | n.m. | -16141.83 | n.m. | 0 | n.m. | 429641.27 | n.m.
84 | 110 | A13212033 | Grayson (KY) - Telecom Legacy | 10/1/2015 | 2/1/2017 | 18501.82 | 410392.12 | 330.4 |  |  | 429224.34 | 0 | 0 | 0 | 0 | 0 | 0 | 18501.82 | n.m. | 410392.12 | n.m. | 330.4 | n.m. | 0 | n.m. | 0 | n.m. | 429224.34 | n.m.
85 | 110 | 000021856 | KYPCO\Pike Replace CO | Charges Began Prior to Jan 2015 | 8/1/2016 | 323430.2 | 102980.15 |  |  |  | 426410.35 | 0 | 0 | 0 | 0 | 0 | 0 | 323430.2 | n.m. | 102980.15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 426410.35 | n.m.
86 | 110 | A13212032 | Beefhide (KY) - Telecom Legacy | 10/1/2015 | 5/1/2017 | 16816.76 | 406517.78 | 2470.29 |  |  | 425804.83 | 0 | 0 | 1696137 | 0 | 0 | 1696137 | 16816.76 | n.m. | 406517.78 | n.m. | -1693666.71 | -99.85% | 0 | n.m. | 0 | n.m. | -1270332.17 | -74.9%
87 | 110 | 000024552 | Draffin-Yellow Hill Relo | 4/1/2016 | 5/1/2017 |  | 370529.62 | 32238.23 |  |  | 402767.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 370529.62 | n.m. | 32238.23 | n.m. | 0 | n.m. | 0 | n.m. | 402767.85 | n.m.
88 | 110 | DMS15KK02 | KY Snow 3 4 2015 | 3/1/2015 | 10/1/2015 | 387625.18 |  |  |  |  | 387625.18 | 0 | 0 | 0 | 0 | 0 | 0 | 387625.18 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 387625.18 | n.m.
89 | 110 | 000024362 | Kenwood \Prestonsburg Tie | 11/1/2015 | 11/1/2016 | 143462.96 | 237750.18 |  |  |  | 381213.14 | 0 | 0 | 0 | 0 | 0 | 0 | 143462.96 | n.m. | 237750.18 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 381213.14 | n.m.
90 | 110 | A13212031 | Bulan Station- Telecom Legacy | 10/1/2015 | 6/1/2017 | 42388.59 | 325481.52 | 2412.88 |  |  | 370282.99 | 0 | 0 | 0 | 0 | 0 | 0 | 42388.59 | n.m. | 325481.52 | n.m. | 2412.88 | n.m. | 0 | n.m. | 0 | n.m. | 370282.99 | n.m.
91 | 110 | DR19K02B0 | Ashland DA 2019 - Busseyville | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 365765.98 | 365765.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 365765.98 | n.m. | 365765.98 | n.m.
92 | 110 | 000024565 | Prestonsburg\UniversityKenwood | 5/1/2016 | 8/1/2017 |  | 286181.53 | 62636.78 |  |  | 348818.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 286181.53 | n.m. | 62636.78 | n.m. | 0 | n.m. | 0 | n.m. | 348818.31 | n.m.
93 | 110 | 000020955 | KYPCO/Ash Replace C.O. | Charges Began Prior to Jan 2015 | 7/1/2016 | 341669.78 | 3263.36 |  |  |  | 344933.14 | 0 | 0 | 0 | 0 | 0 | 0 | 341669.78 | n.m. | 3263.36 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 344933.14 | n.m.
94 | 110 | DP16K02A0 | Add Two D circuits-Cedar Ck | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 342442.72 | 342442.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 342442.72 | n.m. | 342442.72 | n.m.
95 | 110 | 000007558 | KP-PQ-QOS Mitigation | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 27771.87 | 49046.15 | 96102.71 | 49820.07 | 115860.03 | 338600.83 | 1080115 | 1050130 | 1043813 | 1035749 | 588714 | 4798521 | -1052343.13 | -97.43% | -1001083.85 | -95.33% | -947710.29 | -90.79% | -985928.93 | -95.19% | -472853.97 | -80.32% | -4459920.17 | -92.94%
96 | 110 | A15710011 | Hagler Hill TS Tele Modernizat | 1/1/2017 | 5/1/2019 |  |  | 238689.9 | 95835.73 | 1171.92 | 335697.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 238689.9 | n.m. | 95835.73 | n.m. | 1171.92 | n.m. | 335697.55 | n.m.
97 | 110 | DMS16KK05 | KYMETStorm 62316 | 6/1/2016 | 12/1/2016 |  | 326575.34 |  |  |  | 326575.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 326575.34 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 326575.34 | n.m.
98 | 110 | A15702050 | Tenth St.-Transformer 2 Failur | 6/1/2017 | 6/1/2018 |  |  | 438119.35 | -116197.76 |  | 321921.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 438119.35 | n.m. | -116197.76 | n.m. | 0 | n.m. | 321921.59 | n.m.
99 | 110 | 000014717 | KY/DOP/Copper Theft | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 109575.41 | 96936.66 | 50415.63 | 2913.04 | 52986.21 | 312826.95 | 114835 | 113463 | 127141 | 131334 | 165094 | 651867 | -5259.59 | -4.58% | -16526.34 | -14.57% | -76725.37 | -60.35% | -128420.96 | -97.78% | -112107.79 | -67.91% | -339040.05 | -52.01%
100 | 110 | 000023644 | General Plant Blanket KYPCo-D | 8/1/2015 | 1/1/2018 | 289664.28 | 21609.84 | 526.02 | 989.7 |  | 312789.84 | 0 | 0 | 0 | 0 | 0 | 0 | 289664.28 | n.m. | 21609.84 | n.m. | 526.02 | n.m. | 989.7 | n.m. | 0 | n.m. | 312789.84 | n.m.
101 | 110 | DMS15KK03 | KY Tstorm 4 3 15 | 4/1/2015 | 10/1/2015 | 302826.95 |  |  |  |  | 302826.95 | 0 | 0 | 0 | 0 | 0 | 0 | 302826.95 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 302826.95 | n.m.
102 | 110 | 000023930 | Ash\Rep Spacer Cable Various | 5/1/2015 | 8/1/2017 | 200388.86 | 65349.82 | 33785.3 |  |  | 299523.98 | 0 | 0 | 0 | 0 | 0 | 0 | 200388.86 | n.m. | 65349.82 | n.m. | 33785.3 | n.m. | 0 | n.m. | 0 | n.m. | 299523.98 | n.m.
103 | 110 | A13002025 | /DKP/RussellFork-RetiningWall | 2/1/2015 | 1/1/2018 | 535.15 | 8256.9 | 286320.02 | 28.74 |  | 295140.81 | 0 | 0 | 0 | 0 | 0 | 0 | 535.15 | n.m. | 8256.9 | n.m. | 286320.02 | n.m. | 28.74 | n.m. | 0 | n.m. | 295140.81 | n.m.
104 | 110 | A15710010 | Catalpa TS Shelter upgradeTTMP | 12/1/2016 | 3/1/2019 |  | 5594 | 191997.55 | 87274.66 | 1170.26 | 286036.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 5594 | n.m. | 191997.55 | n.m. | 87274.66 | n.m. | 1170.26 | n.m. | 286036.47 | n.m.
105 | 110 | DMS18KK03 | KY/ME/Wind Storm 04/04/18 | 4/1/2018 | 3/1/2019 |  |  |  | 276983.7 | 578.75 | 277562.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 276983.7 | n.m. | 578.75 | n.m. | 277562.45 | n.m.
106 | 110 | DR18K02B0 | Jeff Sta - Add DRTU | 9/1/2018 | Charges Continued After Dec 2019 |  |  |  | 25497.33 | 250106.49 | 275603.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25497.33 | n.m. | 250106.49 | n.m. | 275603.82 | n.m.
107 | 110 | A17750006 | Cannonsburg Failed TR1 | 8/1/2018 | 9/1/2019 |  |  |  | 231357.56 | 41478.7 | 272836.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 231357.56 | n.m. | 41478.7 | n.m. | 272836.26 | n.m.
108 | 110 | 000024269 | Dewey Inez Relocation | 9/1/2015 | 1/1/2016 | 237698.52 | 33792.34 |  |  |  | 271490.86 | 0 | 0 | 0 | 0 | 0 | 0 | 237698.52 | n.m. | 33792.34 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 271490.86 | n.m.
109 | 110 | KYCAPTOOL | KY Purch. Cap Tools | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 266473.3 | 266473.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 266473.3 | n.m. | 266473.3 | n.m.
110 | 110 | 000025595 | Fords Br. Shelby Circuit. | 3/1/2018 | 1/1/2019 |  |  |  | 261404.04 | 1.65 | 261405.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 261404.04 | n.m. | 1.65 | n.m. | 261405.69 | n.m.
111 | 110 | 000023931 | Ash DLine Relo Seed Tick | 5/1/2015 | 2/1/2016 | 260760.87 | 106.72 |  |  |  | 260867.59 | 0 | 0 | 0 | 0 | 0 | 0 | 260760.87 | n.m. | 106.72 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 260867.59 | n.m.
112 | 110 | 000025514 | Mayking Milstone SH | 7/1/2018 | 2/1/2019 |  |  |  | 200602.18 | 55876.95 | 256479.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 200602.18 | n.m. | 55876.95 | n.m. | 256479.13 | n.m.
113 | 110 | DR18K02B3 | Vicco Sta - Add DRTU | 10/1/2018 | Charges Continued After Dec 2019 |  |  |  | 22963.94 | 228128.8 | 251092.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22963.94 | n.m. | 228128.8 | n.m. | 251092.74 | n.m.
114 | 110 | 000024270 | Fords Br Regina Tie Line | 9/1/2015 | 5/1/2016 | 183914.56 | 62448.69 |  |  |  | 246363.25 | 0 | 0 | 0 | 0 | 0 | 0 | 183914.56 | n.m. | 62448.69 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 246363.25 | n.m.
115 | 110 | DP18K03L0 | Tygart Sta - Purchase property | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 243336.09 | 243336.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 243336.09 | n.m. | 243336.09 | n.m.
116 | 110 | A13212027 | Mayking Station - Telecom Lega | 9/1/2015 | 4/1/2017 | 61980.73 | 170570.37 | 4758.51 |  |  | 237309.61 | 0 | 0 | 0 | 0 | 0 | 0 | 61980.73 | n.m. | 170570.37 | n.m. | 4758.51 | n.m. | 0 | n.m. | 0 | n.m. | 237309.61 | n.m.
117 | 110 | DP15K03A0 | Tie Elkhorn City D Circ to Sta | Charges Began Prior to Jan 2015 | 8/1/2016 | 32529.21 | 200230.72 |  |  |  | 232759.93 | 0 | 0 | 0 | 0 | 0 | 0 | 32529.21 | n.m. | 200230.72 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 232759.93 | n.m.
118 | 110 | 000007577 | KP-UG Cable Repl Failure | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 129974.34 | 33640.85 | 1778.98 | 10277.53 | 54149.1 | 229820.8 | 0 | 0 | 0 | 0 | 45903 | 45903 | 129974.34 | n.m. | 33640.85 | n.m. | 1778.98 | n.m. | 10277.53 | n.m. | 8246.1 | 17.96% | 183917.8 | 400.7%
119 | 110 | P11161003 | Allen Remote End | 2/1/2016 | 7/1/2019 |  | 17026.02 | 27784.44 | 180007.18 | 2623.95 | 227441.59 | 11125 | 0 | 0 | 149659 | 0 | 160784 | -11125 | -100% | 17026.02 | n.m. | 27784.44 | n.m. | 30348.18 | 20.28% | 2623.95 | n.m. | 66657.59 | 41.46%
120 | 110 | EDN014701 | Ds Kp Ai Support Cs Res | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 95535.76 | 45047.04 | 42440.26 | 26050.37 | 17236.03 | 226309.46 | 0 | 0 | 0 | 0 | 28829 | 28829 | 95535.76 | n.m. | 45047.04 | n.m. | 42440.26 | n.m. | 26050.37 | n.m. | -11592.97 | -40.21% | 197480.46 | 685%
121 | 110 | 000023933 | Pik Elkhorn City Tie Line | 3/1/2015 | 11/1/2015 | 215745.85 |  |  |  |  | 215745.85 | 0 | 0 | 0 | 0 | 0 | 0 | 215745.85 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 215745.85 | n.m.
122 | 110 | EDN103175 | Ds Kp Anda | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | -5872.3 | 26678.194 | 10648.27 | 65599.8 | 116372.3 | 213426.264 | 0 | 0 | 0 | 0 | 0 | 0 | -5872.3 | n.m. | 26678.194 | n.m. | 10648.27 | n.m. | 65599.8 | n.m. | 116372.3 | n.m. | 213426.264 | n.m.
123 | 110 | KYCR30009 | KY CR Highland Sta | 5/1/2016 | 10/1/2018 |  | 92223.81 | 85403.52 | 28466.29 |  | 206093.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 92223.81 | n.m. | 85403.52 | n.m. | 28466.29 | n.m. | 0 | n.m. | 206093.62 | n.m.
124 | 110 | DX17K01B0 | Elwood Sta - Repl Brkr R | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 188239.79 | 17214.79 | 205454.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 188239.79 | n.m. | 17214.79 | n.m. | 205454.58 | n.m.
125 | 110 | A13212009 | D/KP/Coalton - Telecom Legacy | Charges Began Prior to Jan 2015 | 12/1/2015 | 201808.53 |  |  |  |  | 201808.53 | 226161 | 0 | 0 | 0 | 0 | 226161 | -24352.47 | -10.77% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -24352.47 | -10.77%
126 | 110 | A13002013 | D/KP/Highland-Repl BPLC Rly | 5/1/2017 | 9/1/2019 |  |  | 81079.14 | 79878.37 | 39683.16 | 200640.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 81079.14 | n.m. | 79878.37 | n.m. | 39683.16 | n.m. | 200640.67 | n.m.
127 | 110 | DMS18KK05 | KY/ME/Wind Storm 7/20/18 | 7/1/2018 | 3/1/2019 |  |  |  | 191048.05 | 1778.53 | 192826.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 191048.05 | n.m. | 1778.53 | n.m. | 192826.58 | n.m.
128 | 110 | DMS19KK05 | KY Pre/Valid Major Storm 5 | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 191864.87 | 191864.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 191864.87 | n.m. | 191864.87 | n.m.
129 | 110 | A13002014 | D/KP/Raceland-Repl BPLC Rly | 5/1/2017 | 9/1/2019 |  |  | 88833.24 | 75459.01 | 27366.05 | 191658.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 88833.24 | n.m. | 75459.01 | n.m. | 27366.05 | n.m. | 191658.3 | n.m.
130 | 110 | DR14K02A0 | Big Sandy Sta D-line 3rd Brk | 1/1/2016 | 6/1/2017 |  | 184944.49 | 4849.06 |  |  | 189793.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 184944.49 | n.m. | 4849.06 | n.m. | 0 | n.m. | 0 | n.m. | 189793.55 | n.m.
131 | 110 | EDN101114 | Ds Kp Ai Support Cs C I | Charges Began Prior to Jan 2015 | 10/1/2019 | 23561.33 | 140025.86 | 9922.3 | 4737.05 | 4350.89 | 182597.43 | 0 | 0 | 0 | 0 | 42166 | 42166 | 23561.33 | n.m. | 140025.86 | n.m. | 9922.3 | n.m. | 4737.05 | n.m. | -37815.11 | -89.68% | 140431.43 | 333%
132 | 110 | DMS19KK02 | KY Pre/Valid Major Storm 2 | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 179885.64 | 179885.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 179885.64 | n.m. | 179885.64 | n.m.
133 | 110 | KYCR33111 | KY CR Stinnett Sta | 12/1/2015 | 9/1/2018 | 737.99 | 100061.26 | 47225.54 | 24704.68 |  | 172729.47 | 0 | 0 | 0 | 0 | 0 | 0 | 737.99 | n.m. | 100061.26 | n.m. | 47225.54 | n.m. | 24704.68 | n.m. | 0 | n.m. | 172729.47 | n.m.
134 | 110 | A15702012 | Combs - Rpl Failed RTU | 1/1/2017 | 1/1/2018 |  |  | 170093.4 | 1.46 |  | 170094.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 170093.4 | n.m. | 1.46 | n.m. | 0 | n.m. | 170094.86 | n.m.
135 | 110 | 000025524 | Feds Cr. Exit Relocation | 5/1/2018 | 7/1/2019 |  |  |  | 100656.97 | 65337.49 | 165994.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 100656.97 | n.m. | 65337.49 | n.m. | 165994.46 | n.m.
136 | 110 | DMS19KK06 | KY Pre/Valid Major Storm 6 | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 164826.4 | 164826.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 164826.4 | n.m. | 164826.4 | n.m.
137 | 110 | KYCR31167 | KY CR Belhaven Sta | 5/1/2016 | Charges Continued After Dec 2019 |  | 71722.52 | 156231.92 | -64580.53 | 6.55 | 163380.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 71722.52 | n.m. | 156231.92 | n.m. | -64580.53 | n.m. | 6.55 | n.m. | 163380.46 | n.m.
138 | 110 | P18216001 | Hoods Creek Land Purchase | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 160314.63 | 160314.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 160314.63 | n.m. | 160314.63 | n.m.
139 | 110 | A15710005 | Ashland POP Tele Modernization | 9/1/2016 | Charges Continued After Dec 2019 |  | 531264.37 | -424505.32 | 20302.14 | 23554.35 | 150615.54 | 0 | 0 | 13567 | 0 | 0 | 13567 | 0 | n.m. | 531264.37 | n.m. | -438072.32 | -3229% | 20302.14 | n.m. | 23554.35 | n.m. | 137048.54 | 1010%
140 | 110 | DMS18KK02 | KY/Pre Valid Major Event | 3/1/2018 | 11/1/2018 |  |  |  | 143091.85 |  | 143091.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 143091.85 | n.m. | 0 | n.m. | 143091.85 | n.m.
141 | 110 | DR19K06B2 | Breaker Repl - 47th St | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 139188.306 | 139188.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 139188.306 | n.m. | 139188.306 | n.m.
142 | 110 | KYCR30106 | KY CR Russell Sta | 5/1/2016 | 10/1/2018 |  | 48288.8 | 54323.21 | 35481.85 |  | 138093.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 48288.8 | n.m. | 54323.21 | n.m. | 35481.85 | n.m. | 0 | n.m. | 138093.86 | n.m.
143 | 110 | A13002026 | D/KP/Grayson-ReplFailedRegulat | Charges Began Prior to Jan 2015 | 7/1/2015 | 137480.17 |  |  |  |  | 137480.17 | 0 | 0 | 0 | 0 | 0 | 0 | 137480.17 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 137480.17 | n.m.
144 | 110 | 000023433 | Replace 800mhz Mobile Radios | Charges Began Prior to Jan 2015 | 2/1/2017 | 176416.37 | -44886.03 | -22.57 |  |  | 131507.77 | 0 | 0 | 0 | 0 | 0 | 0 | 176416.37 | n.m. | -44886.03 | n.m. | -22.57 | n.m. | 0 | n.m. | 0 | n.m. | 131507.77 | n.m.
145 | 110 | 000024007 | Big Sandy 3rd Circuit | 3/1/2015 | 11/1/2015 | 131052.66 |  |  |  |  | 131052.66 | 0 | 0 | 0 | 0 | 0 | 0 | 131052.66 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 131052.66 | n.m.
146 | 110 | KYCR31109 | KY CR Wurtland Sta | 5/1/2016 | 1/1/2019 |  | 50440.03 | 51261.89 | 26366.16 | 0.42 | 128068.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 50440.03 | n.m. | 51261.89 | n.m. | 26366.16 | n.m. | 0.42 | n.m. | 128068.5 | n.m.
147 | 110 | 000024063 | Lilly Cornett Woods Relocation | 6/1/2015 | 11/1/2015 | 127703.31 |  |  |  |  | 127703.31 | 0 | 0 | 0 | 0 | 0 | 0 | 127703.31 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 127703.31 | n.m.
148 | 110 | KYCR34119 | KY CR Fords Branch Sta | 1/1/2016 | 1/1/2019 |  | 58695.25 | 49386.18 | 18108.32 | 7.61 | 126197.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 58695.25 | n.m. | 49386.18 | n.m. | 18108.32 | n.m. | 7.61 | n.m. | 126197.36 | n.m.
149 | 110 | P17076002 | Kenwood Station | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 35067.42 | 74909.04 | 14613.37 | 124589.83 | 0 | 0 | 0 | 0 | 32919 | 32919 | 0 | n.m. | 0 | n.m. | 35067.42 | n.m. | 74909.04 | n.m. | -18305.63 | -55.61% | 91670.83 | 278.5%
150 | 110 | A20212001 | Lovely RTU Reliability | 10/1/2018 | Charges Continued After Dec 2019 |  |  |  | 6463.43 | 115260.03 | 121723.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6463.43 | n.m. | 115260.03 | n.m. | 121723.46 | n.m.
151 | 110 | 000023777 | South Shore Sand Hill | 1/1/2015 | 11/1/2015 | 119923.5 |  |  |  |  | 119923.5 | 0 | 0 | 0 | 0 | 0 | 0 | 119923.5 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 119923.5 | n.m.
152 | 110 | A15710017 | West Paintsville Telecom Moder | 1/1/2017 | Charges Continued After Dec 2019 |  |  | 26190.95 | 47661.86 | 46007.19 | 119860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 26190.95 | n.m. | 47661.86 | n.m. | 46007.19 | n.m. | 119860 | n.m.
153 | 110 | EDN101520 | Ds/Field-Ins/Test Mtrs Regular | 12/1/2016 | 6/1/2017 |  | 114716.22 | 4840.69 |  |  | 119556.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 114716.22 | n.m. | 4840.69 | n.m. | 0 | n.m. | 0 | n.m. | 119556.91 | n.m.
154 | 110 | 000025570 | BlueGrass\Walker Town Tie | 4/1/2018 | 10/1/2018 |  |  |  | 114855.51 |  | 114855.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 114855.51 | n.m. | 0 | n.m. | 114855.51 | n.m.
155 | 110 | DX17K02B0 | Second Fork Sta - add SCADA | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 98845.51 | 14277.65 | 113123.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 98845.51 | n.m. | 14277.65 | n.m. | 113123.16 | n.m.
156 | 110 | KYVVO12DL | KP/KY Volt/VAR Opt D-Line | Charges Began Prior to Jan 2015 | 5/1/2017 | 55834.24 | 43247.63 | 13781.76 |  |  | 112863.63 | 0 | 43093 | 0 | 0 | 0 | 43093 | 55834.24 | n.m. | 154.63 | 0.3588% | 13781.76 | n.m. | 0 | n.m. | 0 | n.m. | 69770.63 | 161.9%
157 | 110 | P18025002 | Kewanee Station Land Purchase | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 105184.23 | 4031.76 | 109215.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 105184.23 | n.m. | 4031.76 | n.m. | 109215.99 | n.m.
158 | 110 | DMS15KK06 | KY Wind Storm 7 9 15 | 7/1/2015 | 10/1/2015 | 105840.69 |  |  |  |  | 105840.69 | 0 | 0 | 0 | 0 | 0 | 0 | 105840.69 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 105840.69 | n.m.
159 | 110 | DMS18KK08 | KP/Pre Valid Major Event 8 | 10/1/2018 | 6/1/2019 |  |  |  | 114623.46 | -16055.64 | 98567.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 114623.46 | n.m. | -16055.64 | n.m. | 98567.82 | n.m.
160 | 110 | TA1807312 | D/KPCO/SEL GE Relay | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 98563.372 | 98563.372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 98563.372 | n.m. | 98563.372 | n.m.
161 | 110 | DMS17KK02 | KYMEWind05-01-17 | 5/1/2017 | 8/1/2017 |  |  | 94042.57 |  |  | 94042.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 94042.57 | n.m. | 0 | n.m. | 0 | n.m. | 94042.57 | n.m.
162 | 110 | EDN100296 | Ds-Kp-Ai Small Wire Repl Urd | Charges Began Prior to Jan 2015 | 2/1/2017 | 89056.5 | 2733.7 | 1953.4 |  |  | 93743.6 | 0 | 0 | 0 | 334385 | 297741 | 632126 | 89056.5 | n.m. | 2733.7 | n.m. | 1953.4 | n.m. | -334385 | -100% | -297741 | -100% | -538382.4 | -85.17%
163 | 110 | DMS17KK03 | KY/ME/Thunder 6/23/17 | 6/1/2017 | 3/1/2018 |  |  | 91053.37 | -3487.38 |  | 87565.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 91053.37 | n.m. | -3487.38 | n.m. | 0 | n.m. | 87565.99 | n.m.
164 | 110 | 000008154 | KP Cust Serv Eng Support | Charges Began Prior to Jan 2015 | 6/1/2019 |  | 75640.72 | 9782.39 |  | 0 | 85423.11 | 3069151 | 3243511 | 1905889 | 1940592 | 2213871 | 12373014 | -3069151 | -100% | -3167870.28 | -97.67% | -1896106.61 | -99.49% | -1940592 | -100% | -2213871 | -100% | -12287590.89 | -99.31%
165 | 110 | 000022304 | KY Forensics I&R | Charges Began Prior to Jan 2015 | 12/1/2015 | 84129.32 |  |  |  |  | 84129.32 | 0 | 0 | 0 | 0 | 0 | 0 | 84129.32 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 84129.32 | n.m.
166 | 110 | P17084024 | DO NOT USE | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 1211.87 | 70833.52 | 6914.06 | 78959.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1211.87 | n.m. | 70833.52 | n.m. | 6914.06 | n.m. | 78959.45 | n.m.
167 | 110 | EDN014687 | Ds-Kp-Ai Aepc Make Ready | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 6993.61 | 13503.63 | 26764.54 | 55887.42 | -26443.85 | 76705.35 | 15231 | 15347 | 16854 | 16787 | 0 | 64219 | -8237.39 | -54.08% | -1843.37 | -12.01% | 9910.54 | 58.8% | 39100.42 | 232.9% | -26443.85 | n.m. | 12486.35 | 19.44%
168 | 110 | DMS15KK05 | KY Wind Storm 6 8 15 | 6/1/2015 | 12/1/2015 | 76182.37 |  |  |  |  | 76182.37 | 0 | 0 | 0 | 0 | 0 | 0 | 76182.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 76182.37 | n.m.
169 | 110 | A13002024 | D/KP/Coleman-Repl 69kV CB H | Charges Began Prior to Jan 2015 | 6/1/2015 | 75699.51 |  |  |  |  | 75699.51 | 0 | 0 | 0 | 0 | 0 | 0 | 75699.51 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 75699.51 | n.m.
170 | 110 | DMS15KK01 | KY Moderate Ice Storm 2 21 15 | 2/1/2015 | 8/1/2015 | 73600.29 |  |  |  |  | 73600.29 | 0 | 0 | 0 | 0 | 0 | 0 | 73600.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 73600.29 | n.m.
171 | 110 | 000022834 | Gen Plt Blkt - KYPCO - Dist | Charges Began Prior to Jan 2015 | 11/1/2015 | 69962.92 |  |  |  |  | 69962.92 | 0 | 0 | 0 | 0 | 0 | 0 | 69962.92 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 69962.92 | n.m.
172 | 110 | A15710039 | Pikeville TTMP | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 21422.42 | 46064.98 | 67487.4 | 0 | 0 | 0 | 0 | 37787 | 37787 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21422.42 | n.m. | 8277.98 | 21.91% | 29700.4 | 78.6%
173 | 110 | A15710040 | South PIkeville TTMP | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 33633.56 | 32801.13 | 66434.69 | 0 | 0 | 0 | 0 | 37787 | 37787 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33633.56 | n.m. | -4985.87 | -13.19% | 28647.69 | 75.81%
174 | 110 | A15710012 | Busseyville Telecom Modernizat | 1/1/2017 | 6/1/2019 |  |  | 18416.7 | 42112.1 | 3765.19 | 64293.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 18416.7 | n.m. | 42112.1 | n.m. | 3765.19 | n.m. | 64293.99 | n.m.
175 | 110 | DMS16KK10 | KYWind Storm 121716 | 12/1/2016 | 4/1/2017 |  | 29418.26 | 34662.75 |  |  | 64081.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 29418.26 | n.m. | 34662.75 | n.m. | 0 | n.m. | 0 | n.m. | 64081.01 | n.m.
176 | 110 | DMS18KK04 | KY/Pre Valid Major Event | 7/1/2018 | 10/1/2018 |  |  |  | 62537.37 |  | 62537.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 62537.37 | n.m. | 0 | n.m. | 62537.37 | n.m.
177 | 110 | DMS15KK04 | KY Pre Valid Major Event 4 | 4/1/2015 | 10/1/2015 | 61119.82 |  |  |  |  | 61119.82 | 0 | 0 | 0 | 0 | 0 | 0 | 61119.82 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 61119.82 | n.m.
178 | 110 | DMS17KK04 | KY/Pre Valid Major Event 4 | 11/1/2017 | 2/1/2018 |  |  | 59168.11 | 670.35 |  | 59838.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 59168.11 | n.m. | 670.35 | n.m. | 0 | n.m. | 59838.46 | n.m.
179 | 110 | DMS19KK03 | KY Pre/Valid Major Storm 3 | 6/1/2019 | 10/1/2019 |  |  |  |  | 57887.79 | 57887.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 57887.79 | n.m. | 57887.79 | n.m.
180 | 110 | DMS16KK04 | KYPre Valid Major Event 4 | 4/1/2016 | 12/1/2016 |  | 56180.49 |  |  |  | 56180.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 56180.49 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 56180.49 | n.m.
181 | 110 | P19091002 | Cancel Middle Creek Stn Land | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 55537.35 | 55537.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 55537.35 | n.m. | 55537.35 | n.m.
182 | 110 | DMS18KK01 | KY/ME/Snow Storm 3/12/18 | 3/1/2018 | 1/1/2019 |  |  |  | 55271.19 | 6.68 | 55277.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 55271.19 | n.m. | 6.68 | n.m. | 55277.87 | n.m.
183 | 110 | DMS16KK06 | KYPre Valid Major Event 6 | 7/1/2016 | 10/1/2016 |  | 50704.64 |  |  |  | 50704.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 50704.64 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50704.64 | n.m.
184 | 110 | P17076003 | Prestonsburg Remote End Work | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 18835.38 | 28795.27 | 2467.63 | 50098.28 | 0 | 0 | 0 | 0 | 13229 | 13229 | 0 | n.m. | 0 | n.m. | 18835.38 | n.m. | 28795.27 | n.m. | -10761.37 | -81.35% | 36869.28 | 278.7%
185 | 110 | 000023341 | Ashland Crossarm Replacement | Charges Began Prior to Jan 2015 | 12/1/2015 | 48809.59 |  |  |  |  | 48809.59 | 0 | 0 | 0 | 0 | 0 | 0 | 48809.59 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 48809.59 | n.m.
186 | 110 | A15710026 | Jenkins Station TTMP | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 17308.58 | 30551.35 | 47859.93 | 0 | 0 | 0 | 20676 | 0 | 20676 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -3367.42 | -16.29% | 30551.35 | n.m. | 27183.93 | 131.5%
187 | 110 | DR19K05A0 | Hazard DA 2019 - D line | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 47657.63 | 47657.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 47657.63 | n.m. | 47657.63 | n.m.
188 | 110 | 000025516 | Lilly Cornett Woods SH | 4/1/2018 | 10/1/2018 |  |  |  | 47547.76 |  | 47547.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 47547.76 | n.m. | 0 | n.m. | 47547.76 | n.m.
189 | 110 | DP16K03B0 | Tygart Sta - Dist Station | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 43569.35 | 43569.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 43569.35 | n.m. | 43569.35 | n.m.
190 | 110 | P19091009 | Cancel Mid Crk Station (KP D) | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 42325.42 | 42325.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 42325.42 | n.m. | 42325.42 | n.m.
191 | 110 | A15710021 | Allen Station TTMP | 1/1/2017 | Charges Continued After Dec 2019 |  |  | 11176.01 | 19883.95 | 10527.1 | 41587.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 11176.01 | n.m. | 19883.95 | n.m. | 10527.1 | n.m. | 41587.06 | n.m.
192 | 110 | A15710016 | Oakland TS Telecom Modernizati | 1/1/2017 | 8/1/2019 |  |  | 14980.56 | 19197.69 | 4043.09 | 38221.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 14980.56 | n.m. | 19197.69 | n.m. | 4043.09 | n.m. | 38221.34 | n.m.
193 | 110 | DR19K05B0 | Hazard DA 2019 - Shamrock | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 35878.69 | 35878.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35878.69 | n.m. | 35878.69 | n.m.
194 | 110 | P17084005 | Myra Station | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 16847.15 | 7433.68 | 11508.2 | 35789.03 | 0 | 0 | 0 | 0 | 466518 | 466518 | 0 | n.m. | 0 | n.m. | 16847.15 | n.m. | 7433.68 | n.m. | -455009.8 | -97.53% | -430728.97 | -92.33%
195 | 110 | DMS16KK07 | KYPre Valid Major Event 7 | 7/1/2016 | 10/1/2016 |  | 35579.4 |  |  |  | 35579.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 35579.4 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35579.4 | n.m.
196 | 110 | DMS18KK09 | KP/Pre Valid Major Event 9 | 12/1/2018 | 2/1/2019 |  |  |  | 51612.43 | -16293.02 | 35319.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 51612.43 | n.m. | -16293.02 | n.m. | 35319.41 | n.m.
197 | 110 | A15710019 | Coalton Station TTMP | 1/1/2017 | 8/1/2019 |  |  | 14613.49 | 5765.99 | 13991.56 | 34371.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 14613.49 | n.m. | 5765.99 | n.m. | 13991.56 | n.m. | 34371.04 | n.m.
198 | 110 | 000025521 | Bishop Knobb SH | 8/1/2018 | 9/1/2018 |  |  |  | 33931.76 |  | 33931.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33931.76 | n.m. | 0 | n.m. | 33931.76 | n.m.
199 | 110 | A15710020 | Prestonburg Station TTMP | 1/1/2017 | Charges Continued After Dec 2019 |  |  | 12780.65 | 11676.44 | 9321.53 | 33778.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 12780.65 | n.m. | 11676.44 | n.m. | 9321.53 | n.m. | 33778.62 | n.m.
200 | 110 | DR19K05B2 | Hazard DA 2019 - Slemp | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 33526.33 | 33526.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33526.33 | n.m. | 33526.33 | n.m.
201 | 110 | DMS16KK01 | KYSnow Storm 12016 | 1/1/2016 | 12/1/2016 |  | 33273.06 |  |  |  | 33273.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 33273.06 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33273.06 | n.m.
202 | 110 | 000023343 | Jackson Tie to Haddix | Charges Began Prior to Jan 2015 | 4/1/2015 | 31217.62 |  |  |  |  | 31217.62 | 0 | 0 | 0 | 0 | 0 | 0 | 31217.62 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 31217.62 | n.m.
203 | 110 | DR19K05B1 | Hazard DA 2019 - Engle | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 30740.71 | 30740.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30740.71 | n.m. | 30740.71 | n.m.
204 | 110 | TP1010502 | DSKPCOBusseyville 138kV upgr | Charges Began Prior to Jan 2015 | 10/1/2015 | 30418.98 |  |  |  |  | 30418.98 | 0 | 0 | 0 | 0 | 0 | 0 | 30418.98 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30418.98 | n.m.
205 | 110 | DMS18KK06 | KP/Pre Valid Major Event 6 | 9/1/2018 | 1/1/2019 |  |  |  | 27714.93 | 1494.35 | 29209.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 27714.93 | n.m. | 1494.35 | n.m. | 29209.28 | n.m.
206 | 110 | P17084014 | Henry Clay Station Retirement | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 20500.64 | 5826.03 | 1554.45 | 27881.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 20500.64 | n.m. | 5826.03 | n.m. | 1554.45 | n.m. | 27881.12 | n.m.
207 | 110 | A15710038 | Grayson TTMP | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 10749.3 | 15080.74 | 25830.04 | 0 | 0 | 0 | 0 | 23627 | 23627 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10749.3 | n.m. | -8546.26 | -36.17% | 2203.04 | 9.324%
208 | 110 | P17084009 | Burton Station Retirement | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 21665.74 | -462.3 | 4475.54 | 25678.98 | 0 | 0 | 0 | 0 | 1123549 | 1123549 | 0 | n.m. | 0 | n.m. | 21665.74 | n.m. | -462.3 | n.m. | -1119073.46 | -99.6% | -1097870.02 | -97.71%
209 | 110 | DMS16KK03 | KYPre Valid Major Event 3 | 4/1/2016 | 6/1/2016 |  | 23145.72 |  |  |  | 23145.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 23145.72 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23145.72 | n.m.
210 | 110 | A15710013 | Cannonsburg Telecom Modernizat | 1/1/2018 | 3/1/2019 |  |  |  | 19217.07 | 3057.88 | 22274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19217.07 | n.m. | 3057.88 | n.m. | 22274.95 | n.m.
211 | 110 | P17084025 | Elwood Station Retirement | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 18480.92 | 1946.45 | 1517.48 | 21944.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 18480.92 | n.m. | 1946.45 | n.m. | 1517.48 | n.m. | 21944.85 | n.m.
212 | 110 | P14030009 | Stinnett Station & Telecom | 11/1/2016 | Charges Continued After Dec 2019 |  | 10913.45 | 5520.01 | 3353.69 | 2130.05 | 21917.2 | 0 | 0 | 0 | 0 | 76161 | 76161 | 0 | n.m. | 10913.45 | n.m. | 5520.01 | n.m. | 3353.69 | n.m. | -74030.95 | -97.2% | -54243.8 | -71.22%
213 | 110 | A13212024 | PINEVILLE(LG&E)-Telecom Legacy | 5/1/2015 | 4/1/2016 | 21575.91 | 90.47 |  |  |  | 21666.38 | 0 | 325 | 0 | 0 | 0 | 325 | 21575.91 | n.m. | -234.53 | -72.16% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21341.38 | 6567%
214 | 110 | DMS16KK02 | KYPre Valid Major Event 2 | 3/1/2016 | 5/1/2016 |  | 20277.94 |  |  |  | 20277.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 20277.94 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20277.94 | n.m.
215 | 110 | DX14K01B0 | KP/47th St Sta - replace RTU | Charges Began Prior to Jan 2015 | 9/1/2016 | 15916.13 | 4310.15 |  |  |  | 20226.28 | 0 | 0 | 0 | 0 | 0 | 0 | 15916.13 | n.m. | 4310.15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20226.28 | n.m.
216 | 110 | A19442001 | Grayson Meter Mod | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 20045.12 | 20045.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20045.12 | n.m. | 20045.12 | n.m.
217 | 110 | DMS16KK09 | KYPre Valid Major Event 9 | 8/1/2016 | 2/1/2017 |  | 18327.44 | 202.5 |  |  | 18529.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 18327.44 | n.m. | 202.5 | n.m. | 0 | n.m. | 0 | n.m. | 18529.94 | n.m.
218 | 110 | DMS19KK04 | KY Pre/Valid Major Storm 4 | 10/1/2019 | 11/1/2019 |  |  |  |  | 17278.42 | 17278.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17278.42 | n.m. | 17278.42 | n.m.
219 | 110 | A20705033 | Barrenshe Station Pre-Eng | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 16770.15 | 16770.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16770.15 | n.m. | 16770.15 | n.m.
220 | 110 | P17225006 | Ramey Station | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 2313.05 | 12437.46 | 1579.12 | 16329.63 | 0 | 0 | 0 | 0 | 3421180 | 3421180 | 0 | n.m. | 0 | n.m. | 2313.05 | n.m. | 12437.46 | n.m. | -3419600.88 | -99.95% | -3404850.37 | -99.52%
221 | 110 | P19092002 | Cancel Allen Station (Dist) | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 15212.19 | 15212.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15212.19 | n.m. | 15212.19 | n.m.
222 | 110 | A15710002 | Princess Tele. Moderniz. Stati | 12/1/2016 | 5/1/2018 |  | 70.46 | 3536.58 | 10376.59 |  | 13983.63 | 0 | 0 | 9046 | 0 | 0 | 9046 | 0 | n.m. | 70.46 | n.m. | -5509.42 | -60.9% | 10376.59 | n.m. | 0 | n.m. | 4937.63 | 54.58%
223 | 110 | 000023347 | Prestonsburg Rep Spacer CBL | Charges Began Prior to Jan 2015 | 4/1/2015 | 13470.88 |  |  |  |  | 13470.88 | 0 | 0 | 0 | 0 | 0 | 0 | 13470.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13470.88 | n.m.
224 | 110 | A20705058 | Falcon Station 46kV removal | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 12176.27 | 12176.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12176.27 | n.m. | 12176.27 | n.m.
225 | 110 | DMS16KK08 | KYPre Valid Major Event 8 | 7/1/2016 | 9/1/2016 |  | 11598.88 |  |  |  | 11598.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 11598.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11598.88 | n.m.
226 | 110 | P17083016 | McKinney Station Work | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 9341.56 | 9341.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9341.56 | n.m. | 9341.56 | n.m.
227 | 110 | 000023796 | Cannonsburg - Alley Br. Relo | Charges Began Prior to Jan 2015 | 4/1/2015 | 8646.31 |  |  |  |  | 8646.31 | 0 | 0 | 0 | 0 | 0 | 0 | 8646.31 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8646.31 | n.m.
228 | 110 | B110KYCSV | D/KY/Customer Service | 9/1/2017 | 12/1/2018 |  |  | 7720.39 | 689.7 |  | 8410.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7720.39 | n.m. | 689.7 | n.m. | 0 | n.m. | 8410.09 | n.m.
229 | 110 | P18025003 | DO NOT USE | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1213.43 | 6787.34 | 8000.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1213.43 | n.m. | 6787.34 | n.m. | 8000.77 | n.m.
230 | 110 | A12102010 | D/KP/Baker765-PurchCapSpTrf | Charges Began Prior to Jan 2015 | 8/1/2015 | 7805.71 |  |  |  |  | 7805.71 | 0 | 0 | 0 | 0 | 0 | 0 | 7805.71 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7805.71 | n.m.
231 | 110 | P17083030 | Garrett Station (Distribution) | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 7740.45 | 7740.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7740.45 | n.m. | 7740.45 | n.m.
232 | 110 | A20705084 | Belfry Needs Assessment | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 7626.92 | 7626.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7626.92 | n.m. | 7626.92 | n.m.
233 | 110 | 000025515 | Long Span Rehab 2018 | 8/1/2019 | 10/1/2019 |  |  |  |  | 7494.87 | 7494.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7494.87 | n.m. | 7494.87 | n.m.
234 | 110 | A20705085 | Tom Watkins Station Needs Asmt | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6985.08 | 6985.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6985.08 | n.m. | 6985.08 | n.m.
235 | 110 | A20705068 | Coleman Stn Needs Assessment | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6725.33 | 6725.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6725.33 | n.m. | 6725.33 | n.m.
236 | 110 | P17076011 | Distribution work at Kenwood | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 4433.95 | 1242.45 | 5676.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4433.95 | n.m. | 1242.45 | n.m. | 5676.4 | n.m.
237 | 110 | P18221011 | Collier Remote End | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5200.66 | 5200.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5200.66 | n.m. | 5200.66 | n.m.
238 | 110 | P13117019 | Daisy Station- Replace 69kV sw | Charges Began Prior to Jan 2015 | 6/1/2017 | 2836.5 | 660.22 | 695.52 |  |  | 4192.24 | 55649 | 0 | 0 | 0 | 0 | 55649 | -52812.5 | -94.9% | 660.22 | n.m. | 695.52 | n.m. | 0 | n.m. | 0 | n.m. | -51456.76 | -92.47%
239 | 110 | TA1210013 | DS/KYPCO/Replace &Refurbish | Charges Began Prior to Jan 2015 | 5/1/2015 | 3846.2 |  |  |  |  | 3846.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3846.2 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3846.2 | n.m.
240 | 110 | DP18K01L0 | Lloyd Sta - Purchase property | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3668.09 | 3668.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3668.09 | n.m. | 3668.09 | n.m.
241 | 110 | KYVVO12DS | KP/KY VoltVar Opt D Station | Charges Began Prior to Jan 2015 | 1/1/2018 | -174.04 | 1025.99 | 923.28 | 1737.12 |  | 3512.35 | 0 | 607942 | 0 | 0 | 0 | 607942 | -174.04 | n.m. | -606916.01 | -99.83% | 923.28 | n.m. | 1737.12 | n.m. | 0 | n.m. | -604429.65 | -99.42%
242 | 110 | EDN014673 | Ds-Kp-Ai Pole Reinforcement | 4/1/2014 | 5/1/2018 |  |  | 6.3949e-14 | 3380.07 |  | 3380.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 6.3949e-14 | n.m. | 3380.07 | n.m. | 0 | n.m. | 3380.07 | n.m.
243 | 110 | A15710086 | Hayward Station TTMP | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3039.53 | 3039.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3039.53 | n.m. | 3039.53 | n.m.
244 | 110 | A15710076 | Russell Station TTMP | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2893.26 | 2893.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2893.26 | n.m. | 2893.26 | n.m.
245 | 110 | 000023345 | Bonnyman Big Cr Hazard tie | Charges Began Prior to Jan 2015 | 3/1/2015 | 2755.52 |  |  |  |  | 2755.52 | 0 | 0 | 0 | 0 | 0 | 0 | 2755.52 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2755.52 | n.m.
246 | 110 | A15710075 | Belhaven Station TTMP | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2719.9 | 2719.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2719.9 | n.m. | 2719.9 | n.m.
247 | 110 | A15710080 | Tenth Street Station TTMP | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2711.45 | 2711.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2711.45 | n.m. | 2711.45 | n.m.
248 | 110 | P13117018 | Slemp Station KPCo | Charges Began Prior to Jan 2015 | 6/1/2017 | 915.91 | 860.41 | 906.42 |  |  | 2682.74 | 55765 | 0 | 0 | 0 | 0 | 55765 | -54849.09 | -98.36% | 860.41 | n.m. | 906.42 | n.m. | 0 | n.m. | 0 | n.m. | -53082.26 | -95.19%
249 | 110 | A15710079 | Hitchins Station TTMP | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2556.72 | 2556.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2556.72 | n.m. | 2556.72 | n.m.
250 | 110 | DX16K01A0 | Falcon Sta - Mtn Parkway PPR | 4/1/2016 | 7/1/2017 |  | 68095.29 | -65684.51 |  |  | 2410.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 68095.29 | n.m. | -65684.51 | n.m. | 0 | n.m. | 0 | n.m. | 2410.78 | n.m.
251 | 110 | P19092014 | Prestonsburg Remote End | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2215.6 | 2215.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2215.6 | n.m. | 2215.6 | n.m.
252 | 110 | A15710072 | Raccoon Station TTMP | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1963.97 | 1963.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1963.97 | n.m. | 1963.97 | n.m.
253 | 110 | P17083025 | Soft Shell Station Work (KPCo) | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1756.78 | 1756.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1756.78 | n.m. | 1756.78 | n.m.
254 | 110 | A15710085 | Olive Hill Station TTMP | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1605.89 | 1605.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1605.89 | n.m. | 1605.89 | n.m.
255 | 110 | P19092016 | McKinney Remote End Work | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1569.96 | 1569.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1569.96 | n.m. | 1569.96 | n.m.
256 | 110 | P13064028 | D Line Work | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1488.42 | 1488.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1488.42 | n.m. | 1488.42 | n.m.
257 | 110 | 000023349 | Coleman Peter Cr. Recond | Charges Began Prior to Jan 2015 | 6/1/2015 | 1440.26 |  |  |  |  | 1440.26 | 0 | 0 | 0 | 0 | 0 | 0 | 1440.26 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1440.26 | n.m.
258 | 110 | P17225007 | Ramey Station - Distribution | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 1022.38 | 53.42 | 55.72 | 1131.52 | 0 | 0 | 0 | 0 | 1960984 | 1960984 | 0 | n.m. | 0 | n.m. | 1022.38 | n.m. | 53.42 | n.m. | -1960928.28 | -100% | -1959852.48 | -99.94%
259 | 110 | P18221016 | Jackhorn Distribution work | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 904.11 | 904.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 904.11 | n.m. | 904.11 | n.m.
260 | 110 | A13212015 | D/KP/Whitesburg - Telecom Lega | Charges Began Prior to Jan 2015 | 6/1/2015 | 818.16 |  |  |  |  | 818.16 | 0 | 0 | 0 | 0 | 0 | 0 | 818.16 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 818.16 | n.m.
261 | 110 | A13212004 | D/KP/McKinney - Telecom Legacy | Charges Began Prior to Jan 2015 | 10/1/2018 |  | -12.44 | 634.52 | -5.62 |  | 616.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | -12.44 | n.m. | 634.52 | n.m. | -5.62 | n.m. | 0 | n.m. | 616.46 | n.m.
262 | 110 | P18025004 | DO NOT USE | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 520.72 | 26.97 | 547.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 520.72 | n.m. | 26.97 | n.m. | 547.69 | n.m.
263 | 110 | TP0921001 | DS/KYPCO/Beckham 138kV Cntl Ho | Charges Began Prior to Jan 2015 | 11/1/2015 | 520.54 |  |  |  |  | 520.54 | 0 | 0 | 0 | 0 | 0 | 0 | 520.54 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 520.54 | n.m.
264 | 110 | A13212010 | D/KP/Coleman - Telecom Legacy | Charges Began Prior to Jan 2015 | 4/1/2015 | 494.49 |  |  |  |  | 494.49 | 0 | 0 | 0 | 0 | 0 | 0 | 494.49 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 494.49 | n.m.
265 | 110 | A13212011 | D/KP/Salisbury (KP) - Telecom | Charges Began Prior to Jan 2015 | 3/1/2015 | 379.88 |  |  |  |  | 379.88 | 0 | 0 | 0 | 0 | 0 | 0 | 379.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 379.88 | n.m.
266 | 110 | DR19K04B2 | Pikeville DA 2019 - Stanv. D | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 344.26 | 344.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 344.26 | n.m. | 344.26 | n.m.
267 | 110 | A15710060 | Pikesville SC TTMP | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 136 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 136 | n.m. | 136 | n.m.
268 | 110 | A13212014 | D/KP/Topmost - Telecom Legacy | Charges Began Prior to Jan 2015 | 2/1/2015 | 125.89 |  |  |  |  | 125.89 | 0 | 0 | 0 | 0 | 0 | 0 | 125.89 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 125.89 | n.m.
269 | 110 | 000023348 | McDowell Relocation | Charges Began Prior to Jan 2015 | 1/1/2015 | 101.09 |  |  |  |  | 101.09 | 0 | 0 | 0 | 0 | 0 | 0 | 101.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 101.09 | n.m.
270 | 110 | DR20K02B3 | Breaker Repl - Jenkins | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 78.69 | 78.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 78.69 | n.m. | 78.69 | n.m.
271 | 110 | DR20K02B1 | Breaker Repl - Sidney | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 78.69 | 78.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 78.69 | n.m. | 78.69 | n.m.
272 | 110 | DR20K02B0 | Breaker Repl - E Prestonsburg | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 78.69 | 78.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 78.69 | n.m. | 78.69 | n.m.
273 | 110 | DMS14KK11 | KY Pre Valid Major Event 11 | Charges Began Prior to Jan 2015 | 1/1/2015 | 71.05 |  |  |  |  | 71.05 | 0 | 0 | 0 | 0 | 0 | 0 | 71.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 71.05 | n.m.
274 | 110 | 000012305 | KP Attachment Serv Rentals | Charges Began Prior to Jan 2015 | 9/1/2015 | 43.99 |  |  |  |  | 43.99 | 0 | 0 | 0 | 0 | 0 | 0 | 43.99 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 43.99 | n.m.
275 | 110 | DP11K03A0 | KPJeff Station Circuit D-Line | Charges Began Prior to Jan 2015 | 2/1/2015 | 30.05 |  |  |  |  | 30.05 | 0 | 0 | 0 | 0 | 0 | 0 | 30.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30.05 | n.m.
276 | 110 | P17084001 | Cancel: DO NOT USE | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 33704.73 | 38121.92 | -71822.63 | 4.02 | 0 | 0 | 0 | 0 | 47296 | 47296 | 0 | n.m. | 0 | n.m. | 33704.73 | n.m. | 38121.92 | n.m. | -119118.63 | -251.9% | -47291.98 | -99.99%
277 | 110 | A18702002 | CANCELLED | 4/1/2018 | 7/1/2018 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m.
278 | 110 | DMS18KK07 | KP/Pre Valid Major Event 7 | 9/1/2018 | 12/1/2018 |  |  |  | -6.0507e-15 |  | -6.0507e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -6.0507e-15 | n.m. | 0 | n.m. | -6.0507e-15 | n.m.
279 | 110 | A15702008 | CANCELLED | 12/1/2016 | 10/1/2018 |  | 800 | 57603.55 | -58403.55 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 800 | n.m. | 57603.55 | n.m. | -58403.55 | n.m. | 0 | n.m. | 0 | n.m.
280 | 110 | P17225011 | Hoods Creek Land Purchase | 2/1/2018 | 8/1/2019 |  |  |  | 27503.24 | -27503.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 27503.24 | n.m. | -27503.24 | n.m. | 0 | n.m.
281 | 110 | ETN000110 | T Kp D Anda | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 4.1837e-11 | 0 | -4.502e-11 | 7.6398e-11 | -1.5007e-11 | 5.8208e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1837e-11 | n.m. | 0 | n.m. | -4.502e-11 | n.m. | 7.6398e-11 | n.m. | -1.5007e-11 | n.m. | 5.8208e-11 | n.m.
282 | 110 | A13212022 | D/KP/Busseyville - Telecom Leg | Charges Began Prior to Jan 2015 | 9/1/2015 | -166.28 |  |  |  |  | -166.28 | 0 | 0 | 0 | 0 | 0 | 0 | -166.28 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -166.28 | n.m.
283 | 110 | DMS14KK07 | KY Wind Storm 6-10-14 | 6/1/2014 | 4/1/2015 | -509.21 |  |  |  |  | -509.21 | 0 | 0 | 0 | 0 | 0 | 0 | -509.21 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -509.21 | n.m.
284 | 110 | DP12H33B2 | KP Pikevlle Sta Xfrmr Monitor | Charges Began Prior to Jan 2015 | 4/1/2015 | -643.17 |  |  |  |  | -643.17 | 0 | 0 | 0 | 0 | 0 | 0 | -643.17 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -643.17 | n.m.
285 | 110 | 000023346 | Jenkins Burdine Reconductor | Charges Began Prior to Jan 2015 | 3/1/2015 | -1069.33 |  |  |  |  | -1069.33 | 0 | 0 | 0 | 0 | 0 | 0 | -1069.33 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1069.33 | n.m.
286 | 110 | P19091007 | Cancel Prestonsburg Remote End | 8/1/2019 | 10/1/2019 |  |  |  |  | -1146.23 | -1146.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1146.23 | n.m. | -1146.23 | n.m.
287 | 110 | A13212012 | D/KP/Soft Shell - Telecom Lega | Charges Began Prior to Jan 2015 | 5/1/2015 | -2397.43 |  |  |  |  | -2397.43 | 0 | 0 | 0 | 0 | 0 | 0 | -2397.43 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -2397.43 | n.m.
288 | 110 | DP11K03B0 | KPJeff Sta - Add 69-34.5 kV | Charges Began Prior to Jan 2015 | 5/1/2015 | -3903.03 |  |  |  |  | -3903.03 | 0 | 0 | 0 | 0 | 0 | 0 | -3903.03 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -3903.03 | n.m.
289 | 110 | P12057005 | Motorize Topmost Switch '11' | Charges Began Prior to Jan 2015 | 11/1/2017 | 1126.63 | 2260.79 | -15428.43 |  |  | -12041.01 | 0 | 0 | 0 | 0 | 0 | 0 | 1126.63 | n.m. | 2260.79 | n.m. | -15428.43 | n.m. | 0 | n.m. | 0 | n.m. | -12041.01 | n.m.
290 | 110 | KYCR012DS | KP/VoltVar Circ Reconfig DSta | Charges Began Prior to Jan 2015 | 4/1/2016 | 51775.65 | -64321.19 |  |  |  | -12545.54 | 0 | 0 | 0 | 0 | 0 | 0 | 51775.65 | n.m. | -64321.19 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -12545.54 | n.m.
291 | 110 | P13117020 | T/KP/Collier Station- Remote e | Charges Began Prior to Jan 2015 | 7/1/2017 | 635.68 | 542.7 | -14592.38 |  |  | -13414 | 55649 | 0 | 0 | 0 | 0 | 55649 | -55013.32 | -98.86% | 542.7 | n.m. | -14592.38 | n.m. | 0 | n.m. | 0 | n.m. | -69063 | -124.1%
292 | 110 | ITUOP0005 | IT Utility Operations Blanket | Charges Began Prior to Jan 2015 | 3/1/2017 | 1520.49 | -39649.16 | 7615.55 |  |  | -30513.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1520.49 | n.m. | -39649.16 | n.m. | 7615.55 | n.m. | 0 | n.m. | 0 | n.m. | -30513.12 | n.m.
293 | 110 | P12124003 | DKPLOVELY Station SCADA Upgr | Charges Began Prior to Jan 2015 | 2/1/2019 | 14996.61 | 6584.63 | 900.85 | -120644.7 | 16935.77 | -81226.84 | 55630 | 1012819 | 0 | 0 | 0 | 1068449 | -40633.39 | -73.04% | -1006234.37 | -99.35% | 900.85 | n.m. | -120644.7 | n.m. | 16935.77 | n.m. | -1149675.84 | -107.6%
294 | 110 | Other Budgeted Projects |  | Other | Other | 0 | 0 | 0 | 0 | 0 | 0 | 11689955 | 11235005 | 8914930 | 22759750 | 20941109 | 75540749 | -11689955 | -100% | -11235005 | -100% | -8914930 | -100% | -22759750 | -100% | -20941109 | -100% | -75540749 | -100%
295 | 110 Total |  |  |  |  | 43270746.99 | 40033232.374 | 48939230.31 | 64555463.901 | 88614408.034 | 285413081.609 | 38711343 | 39174110 | 35782920 | 58845448 | 77198892 | 249712713 | 4559403.99 | 11.78% | 859122.374 | 2.193% | 13156310.31 | 36.77% | 5710015.901 | 9.703% | 11415516.034 | 14.79% | 35700368.609 | 14.3%
296 | 117 | 000021297 | BS U1 Gas Conversion | Charges Began Prior to Jan 2015 | 4/1/2017 | 24674275.91 | 30805282.84 | -48161.54 |  |  | 55431397.21 | 21246219.859 | 20645133.265 | 0 | 0 | 0 | 41891353.124 | 3428056.051 | 16.13% | 10160149.575 | 49.21% | -48161.54 | n.m. | 0 | n.m. | 0 | n.m. | 13540044.086 | 32.32%
297 | 117 | 000005237 | KyPCo-G Capital Software Dev | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1912662.57 | 2383850.8 | 3003925.83 | 3951851.2 | 2434708.91 | 13686999.31 | 0 | 1225909.682 | 1508938.455 | 7849.761 | 0 | 2742697.898 | 1912662.57 | n.m. | 1157941.118 | 94.46% | 1494987.375 | 99.08% | 3944001.439 | 50244% | 2434708.91 | n.m. | 10944301.412 | 399%
298 | 117 | 000022392 | ML LANDFILL EXPANSION - PH 3 | 9/1/2016 | Charges Continued After Dec 2019 |  | 567508.75 | 2866690.57 | 5001223.22 | 4075206.479 | 12510629.019 | 0 | 140329.257 | 7719992.548 | 6548798.546 | 6639060.198 | 21048180.549 | 0 | n.m. | 427179.493 | 304.4% | -4853301.978 | -62.87% | -1547575.326 | -23.63% | -2563853.719 | -38.62% | -8537551.53 | -40.56%
299 | 117 | 000021737 | BS Repurpose BAP | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 806782.14 | 5604089.6 | 6410871.74 | 0 | 0 | 435591.012 | 3204614.575 | 63986.64 | 3704192.227 | 0 | n.m. | 0 | n.m. | -435591.012 | -100% | -2397832.435 | -74.82% | 5540102.96 | 8658% | 2706679.513 | 73.07%
300 | 117 | BSPPB0013 | Other Costs PPB<$100k | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1092400.06 | 1218837.54 | 1836265.71 | 822841.17 | 1025412.4 | 5995756.88 | 52678.605 | 117379.228 | 153604.655 | 6152.041 | 41464.751 | 371279.28 | 1039721.455 | 1974% | 1101458.312 | 938.4% | 1682661.055 | 1095% | 816689.129 | 13275% | 983947.649 | 2373% | 5624477.6 | 1515%
301 | 117 | IT1171421 | Maximo Imp - KYP - G | 3/1/2016 | Charges Continued After Dec 2019 |  | 465910.54 | 887506.696 | 1378551.17 | 1452005.5 | 4183973.906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 465910.54 | n.m. | 887506.696 | n.m. | 1378551.17 | n.m. | 1452005.5 | n.m. | 4183973.906 | n.m.
302 | 117 | IT117BILL | Corp Prgrm Billing - KYPCO Gen | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 2141826.38 | 457878.61 | 1193125.32 | 3792830.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2141826.38 | n.m. | 457878.61 | n.m. | 1193125.32 | n.m. | 3792830.31 | n.m.
303 | 117 | BS0000038 | Big Sandy U1 HP IPSFLP Overha | 1/1/2018 | 11/1/2018 |  |  |  | 3563720.16 |  | 3563720.16 | 0 | 0 | 0 | 2117803.537 | 1884.65 | 2119688.187 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1445916.623 | 68.27% | -1884.65 | -100% | 1444031.973 | 68.12%
304 | 117 | KMLFALFCI | ML U0 New Landfill | Charges Began Prior to Jan 2015 | 4/1/2018 | 3356544.16 | -15532.27 | -37856.96 | 5967.71 |  | 3309122.64 | 3626082.013 | -49951.31 | 0 | 0 | 0 | 3576130.703 | -269537.853 | -7.433% | 34419.04 | -68.91% | -37856.96 | n.m. | 5967.71 | n.m. | 0 | n.m. | -267008.063 | -7.466%
305 | 117 | 000020312 | ML U0 Cooling Tower Blow Down | Charges Began Prior to Jan 2015 | 4/1/2016 | 3109498.29 | -13243.22 |  |  |  | 3096255.07 | 2131425.336 | 0 | 0 | 0 | 0 | 2131425.336 | 978072.954 | 45.89% | -13243.22 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 964829.734 | 45.27%
306 | 117 | ML119SC02 | ML U1 ECON PARTITION WALL RPL | 8/1/2018 | Charges Continued After Dec 2019 |  |  |  | 115498.38 | 2854954.9 | 2970453.28 | 0 | 0 | 0 | 0 | 1328078.491 | 1328078.491 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 115498.38 | n.m. | 1526876.409 | 115% | 1642374.789 | 123.7%
307 | 117 | 000023820 | Mitchell Controls Upgrade KY | Charges Began Prior to Jan 2015 | 4/1/2016 | 2582050.01 | -24255.94 |  |  |  | 2557794.07 | 1693489.271 | 591.09 | 0 | 0 | 0 | 1694080.361 | 888560.739 | 52.47% | -24847.03 | -4204% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 863713.709 | 50.98%
308 | 117 | 000022308 | ML U1 ESP Project | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 110827.14 | 2422707.58 | 2533534.72 | 0 | 0 | 0 | 0 | 3810922.273 | 3810922.273 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 110827.14 | n.m. | -1388214.693 | -36.43% | -1277387.553 | -33.52%
309 | 117 | 000022998 | ML Coping Power | Charges Began Prior to Jan 2015 | 6/1/2016 | 2390714.68 | -8017.73 |  |  |  | 2382696.95 | 1040375.164 | 0 | 0 | 0 | 0 | 1040375.164 | 1350339.516 | 129.8% | -8017.73 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1342321.786 | 129%
310 | 117 | ML1EC1302 | ML1 E PHASE 1 GSU TRANSFORMER | 5/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1016323.31 | 982086.07 | 1998409.38 | 0 | 0 | 911499.197 | -1153.63 | 1926700.328 | 2837045.895 | 0 | n.m. | 0 | n.m. | -911499.197 | -100% | 1017476.94 | -88198% | -944614.258 | -49.03% | -838636.515 | -29.56%
311 | 117 | ML2E15CKP | ML2 HP 2nd RH TURB INSPECT | Charges Began Prior to Jan 2015 | 1/1/2016 | 1850727.05 | 110.85 |  |  |  | 1850837.9 | 1188676.34 | 0 | 0 | 0 | 0 | 1188676.34 | 662050.71 | 55.7% | 110.85 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 662161.56 | 55.71%
312 | 117 | NRCCPKPCO | NERC CIP KYPCO | 9/1/2016 | Charges Continued After Dec 2019 |  | 21570.36 | 316409.71 | 1310014.19 | 31983.25 | 1679977.51 | 0 | 841161.141 | -79852.964 | 1364112.891 | 83130.097 | 2208551.165 | 0 | n.m. | -819590.781 | -97.44% | 396262.674 | -496.2% | -54098.701 | -3.966% | -51146.847 | -61.53% | -528573.655 | -23.93%
313 | 117 | ML1VC1601 | ML1 V CATALYST REPLACEMENT 3 L | 12/1/2016 | Charges Continued After Dec 2019 |  | 16036.5 | 978918.14 | 486935.82 | 104662.13 | 1586552.59 | 0 | 413726.926 | 1244836.154 | 1238690.003 | 0 | 2897253.083 | 0 | n.m. | -397690.426 | -96.12% | -265918.014 | -21.36% | -751754.183 | -60.69% | 104662.13 | n.m. | -1310700.493 | -45.24%
314 | 117 | ML2VC1601 | ML2 V CATALYST REPLACEMENT 3 L | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 1000799.68 | 495998.88 | 2173.81 | 1498972.37 | 0 | 0 | 421423.016 | 1182821.549 | 0 | 1604244.565 | 0 | n.m. | 0 | n.m. | 579376.664 | 137.5% | -686822.669 | -58.07% | 2173.81 | n.m. | -105272.195 | -6.562%
315 | 117 | ML1E18C05 | MLU1 LP TURBINE ROTOR REPAIR | 9/1/2017 | 11/1/2019 |  |  | 597966.76 | 562669.49 | 219858.11 | 1380494.36 | 0 | 0 | 0 | 520848.41 | 0 | 520848.41 | 0 | n.m. | 0 | n.m. | 597966.76 | n.m. | 41821.08 | 8.029% | 219858.11 | n.m. | 859645.95 | 165%
316 | 117 | ML1SC1810 | ML1 S BREECHING DUCT RPL | 12/1/2018 | Charges Continued After Dec 2019 |  |  |  | 6215.14 | 1050781.52 | 1056996.66 | 0 | 0 | 0 | 0 | 1074746.662 | 1074746.662 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6215.14 | n.m. | -23965.142 | -2.23% | -17750.002 | -1.652%
317 | 117 | BSPPBOUT1 | Unit 1PPB Outage<100k | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 152356.82 | 234017.03 | 34371.02 | 621388.14 | -2967.15 | 1039165.86 | 51246.722 | 0 | 1684687.921 | 949600.069 | 690285.217 | 3375819.929 | 101110.098 | 197.3% | 234017.03 | n.m. | -1650316.901 | -97.96% | -328211.929 | -34.56% | -693252.367 | -100.4% | -2336654.069 | -69.22%
318 | 117 | ML1VC1511 | ML1 PURCHASE ID FAN HUBS | 8/1/2015 | 6/1/2016 | 1033536.12 | 1455.16 |  |  |  | 1034991.28 | 0 | 0 | 0 | 0 | 0 | 0 | 1033536.12 | n.m. | 1455.16 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1034991.28 | n.m.
319 | 117 | ML016VP11 | ML - 2016 FGD NON OUTAGE PPB | 11/1/2016 | 8/1/2019 |  | 483690.36 | 478670.47 | 36063.64 | 9119.91 | 1007544.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 483690.36 | n.m. | 478670.47 | n.m. | 36063.64 | n.m. | 9119.91 | n.m. | 1007544.38 | n.m.
320 | 117 | BSPPB0002 | Boiler & Auxiliaries PPB<100k | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 133134.69 | 183486.26 | 333545.11 | 232591.6 | 110441.28 | 993198.94 | 0 | 0 | 180341.86 | 167583.019 | 181633.254 | 529558.133 | 133134.69 | n.m. | 183486.26 | n.m. | 153203.25 | 84.95% | 65008.581 | 38.79% | -71191.974 | -39.2% | 463640.807 | 87.55%
321 | 117 | ARCFLA117 | Arc Flash Protection Swi KYPCo | Charges Began Prior to Jan 2015 | 8/1/2019 | 434509.85 | 179716.29 | 229056.62 | 57261.68 | 56433.93 | 956978.37 | 101603.437 | 233522.879 | 0 | 0 | 0 | 335126.316 | 332906.413 | 327.7% | -53806.589 | -23.04% | 229056.62 | n.m. | 57261.68 | n.m. | 56433.93 | n.m. | 621852.054 | 185.6%
322 | 117 | BS2DCOM20 | Big Sandy U1 CEMS Building | 11/1/2017 | 1/1/2019 |  |  | 223930.01 | 643384.91 | 62.82 | 867377.74 | 0 | 0 | 0 | 234258.77 | 0 | 234258.77 | 0 | n.m. | 0 | n.m. | 223930.01 | n.m. | 409126.14 | 174.6% | 62.82 | n.m. | 633118.97 | 270.3%
323 | 117 | ML2VC1401 | ML2 V CATALYST REPLACEMENT 1 L | Charges Began Prior to Jan 2015 | 12/1/2017 | 818293.25 | 3093.55 | 32763.26 |  |  | 854150.06 | 990692.242 | 0 | 0 | 0 | 0 | 990692.242 | -172398.992 | -17.4% | 3093.55 | n.m. | 32763.26 | n.m. | 0 | n.m. | 0 | n.m. | -136542.182 | -13.78%
324 | 117 | BSPPBS312 | New CCR Rule GW Wells | 6/1/2015 | 5/1/2017 | 55458.7 | 724038.22 | 12475.33 |  |  | 791972.25 | 0 | 0 | 0 | 0 | 0 | 0 | 55458.7 | n.m. | 724038.22 | n.m. | 12475.33 | n.m. | 0 | n.m. | 0 | n.m. | 791972.25 | n.m.
325 | 117 | 000021259 | ML U2 ESP Upgrades | Charges Began Prior to Jan 2015 | 11/1/2015 | 791621.85 |  |  |  |  | 791621.85 | 830765.729 | 0 | 0 | 0 | 0 | 830765.729 | -39143.879 | -4.712% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -39143.879 | -4.712%
326 | 117 | IT1171323 | High Avail Data Ctr-KYP-G | Charges Began Prior to Jan 2015 | 3/1/2016 | 415541.15 | 312746.85 |  |  |  | 728288 | 0 | 0 | 0 | 0 | 0 | 0 | 415541.15 | n.m. | 312746.85 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 728288 | n.m.
327 | 117 | 000019836 | ML U1&2 Dry Fly Ash Conversion | Charges Began Prior to Jan 2015 | 9/1/2016 | 482530.6 | 225392.28 |  |  |  | 707922.88 | 0 | 157200.602 | 0 | 0 | 0 | 157200.602 | 482530.6 | n.m. | 68191.678 | 43.38% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 550722.278 | 350.3%
328 | 117 | BSPPBS314 | BS1 - REP THIRD FLOOR WALLS | 9/1/2015 | 3/1/2017 | 286196.87 | 383040.31 | 9935.85 |  |  | 679173.03 | 0 | 0 | 0 | 0 | 0 | 0 | 286196.87 | n.m. | 383040.31 | n.m. | 9935.85 | n.m. | 0 | n.m. | 0 | n.m. | 679173.03 | n.m.
329 | 117 | ML018VP01 | ML - NON OUTAGE PPB FGD | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 590253.77 | 69582.83 | 659836.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 590253.77 | n.m. | 69582.83 | n.m. | 659836.6 | n.m.
330 | 117 | MLP17EP04 | MLP E LIGHTING PANEL REPLACE | 10/1/2016 | 1/1/2019 |  | 59168.85 | 549619.85 | 20621.47 | 27.24 | 629437.41 | 0 | 0 | 129221.307 | 108684.395 | 7.053 | 237912.755 | 0 | n.m. | 59168.85 | n.m. | 420398.543 | 325.3% | -88062.925 | -81.03% | 20.187 | 286.2% | 391524.655 | 164.6%
331 | 117 | BSPPBS316 | BS1 - REP THIRD FLOOR FLOORING | 10/1/2015 | 5/1/2016 | 342974.93 | 277214.45 |  |  |  | 620189.38 | 0 | 0 | 0 | 0 | 0 | 0 | 342974.93 | n.m. | 277214.45 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 620189.38 | n.m.
332 | 117 | ML018MP05 | ML 2018 PLANT CAPITAL PAVING | 8/1/2018 | 3/1/2019 |  |  |  | 606985.67 | -519.08 | 606466.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 606985.67 | n.m. | -519.08 | n.m. | 606466.59 | n.m.
333 | 117 | ML018NP01 | ML CAPITAL TOOLS | 3/1/2018 | 10/1/2019 |  |  |  | 497621.6 | 53554.48 | 551176.08 | 0 | 0 | 0 | 0 | 167679.091 | 167679.091 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 497621.6 | n.m. | -114124.611 | -68.06% | 383496.989 | 228.7%
334 | 117 | ML016VC01 | ML GYPSUM ENCLOSURE PROJECT | 10/1/2016 | 10/1/2017 |  | 287322.46 | 254563.52 |  |  | 541885.98 | 0 | 0 | -139947.276 | 0 | 0 | -139947.276 | 0 | n.m. | 287322.46 | n.m. | 394510.796 | -281.9% | 0 | n.m. | 0 | n.m. | 681833.256 | -487.2%
335 | 117 | ML1E18C02 | ML1 2nd RH TURBINE REPLACEMENT | 7/1/2017 | 4/1/2018 |  |  | 520805.21 | 3901.58 |  | 524706.79 | 0 | 0 | 0 | 680.58 | 0 | 680.58 | 0 | n.m. | 0 | n.m. | 520805.21 | n.m. | 3221 | 473.3% | 0 | n.m. | 524026.21 | 76997%
336 | 117 | BSPPBS326 | Boiler Orifice Upgrade | 10/1/2016 | 7/1/2017 |  | 10993.41 | 485962.34 |  |  | 496955.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 10993.41 | n.m. | 485962.34 | n.m. | 0 | n.m. | 0 | n.m. | 496955.75 | n.m.
337 | 117 | BSPPB0016 | Turb & Support Sys PPB<100k | Charges Began Prior to Jan 2015 | 2018-07-01 | 66849.63 | 200535.74 | 61501.6 | 113389.93 |  | 442276.9 | 0 | 0 | 0 | 0 | 0 | 0 | 66849.63 | n.m. | 200535.74 | n.m. | 61501.6 | n.m. | 113389.93 | n.m. | 0 | n.m. | 442276.9 | n.m.
338 | 117 | ML017MP01 | ML 2017 PLANT CAPITAL PAVING | 10/1/2017 | 5/1/2018 |  |  | 381065.75 | 37737.09 |  | 418802.84 | 0 | 0 | 145140.805 | 96.56 | 0 | 145237.365 | 0 | n.m. | 0 | n.m. | 235924.945 | 162.5% | 37640.53 | 38981% | 0 | n.m. | 273565.475 | 188.4%
339 | 117 | ML1S15P01 | ML1 PRECIPITATOR EJ RPL | 8/1/2015 | 3/1/2016 | 394707.51 | 10444.45 |  |  |  | 405151.96 | 210593.62 | 65.2 | 0 | 0 | 0 | 210658.82 | 184113.89 | 87.43% | 10379.25 | 15919% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 194493.14 | 92.33%
340 | 117 | ML0M18C01 | ML COAL YARD PLC REPLACEMENT | 9/1/2017 | 8/1/2018 |  |  | 162525.17 | 230688.63 |  | 393213.8 | 0 | 0 | 0 | 250943.379 | 0 | 250943.379 | 0 | n.m. | 0 | n.m. | 162525.17 | n.m. | -20254.749 | -8.071% | 0 | n.m. | 142270.421 | 56.69%
341 | 117 | BSPPBS347 | REP U1 BFPT Rotor with Spare | 11/1/2018 | 3/1/2019 |  |  |  | 297879.73 | 88890.82 | 386770.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 297879.73 | n.m. | 88890.82 | n.m. | 386770.55 | n.m.
342 | 117 | ML018VP04 | ML ID FAN DRIVE END HUB PURCHA | 7/1/2018 | 8/1/2019 |  |  |  | 390173.51 | -29288.6 | 360884.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 390173.51 | n.m. | -29288.6 | n.m. | 360884.91 | n.m.
343 | 117 | BSPPBS322 | Repl HVAC U1 Mezzanine Area | 12/1/2015 | 6/1/2016 | 161500 | 187056.5 |  |  |  | 348556.5 | 0 | 0 | 0 | 0 | 0 | 0 | 161500 | n.m. | 187056.5 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 348556.5 | n.m.
344 | 117 | ML1E18C03 | MLU1 LPB TURBINE REPLACEMENT | 7/1/2017 | 4/1/2018 |  |  | 337683.7 | 2529.58 |  | 340213.28 | 0 | 0 | 0 | 308.23 | 0 | 308.23 | 0 | n.m. | 0 | n.m. | 337683.7 | n.m. | 2221.35 | 720.7% | 0 | n.m. | 339905.05 | 110276%
345 | 117 | ML016NP06 | MLP CAPITAL TOOLS | 1/1/2016 | 3/1/2019 |  | 324443.96 | 11762.65 | 2056.83 | -9.25 | 338254.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 324443.96 | n.m. | 11762.65 | n.m. | 2056.83 | n.m. | -9.25 | n.m. | 338254.19 | n.m.
346 | 117 | MLP17SP01 | INSTALL R3/R4 FIRE HEADER CTIE | 5/1/2017 | 8/1/2019 |  |  | 255480.27 | 70358.15 | 8635.15 | 334473.57 | 0 | 0 | 221107.813 | 0 | 0 | 221107.813 | 0 | n.m. | 0 | n.m. | 34372.457 | 15.55% | 70358.15 | n.m. | 8635.15 | n.m. | 113365.757 | 51.27%
347 | 117 | BSPPBS319 | BS0 NEW SEWAGE TRMT PLANT | 8/1/2015 | 5/1/2016 | 322385.71 | 11719.54 |  |  |  | 334105.25 | 0 | 0 | 0 | 0 | 0 | 0 | 322385.71 | n.m. | 11719.54 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 334105.25 | n.m.
348 | 117 | ML018MP03 | ML MH CONVEYOR BELT REPLACE | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 321529.07 | 4107.27 | 325636.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 321529.07 | n.m. | 4107.27 | n.m. | 325636.34 | n.m.
349 | 117 | ML0VP1401 | CAP BLKT PROD PLANT BLNKT | Charges Began Prior to Jan 2015 | 12/1/2016 | 128875.56 | 191619.21 |  |  |  | 320494.77 | 48.677 | 0 | 0 | 0 | 0 | 48.677 | 128826.883 | 264657% | 191619.21 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 320446.093 | 658311%
350 | 117 | ML017NP01 | Capital Tools | 1/1/2017 | 11/1/2019 |  |  | 272633.83 | 47179.63 | 365.07 | 320178.53 | 0 | 0 | 117982.657 | 164970.598 | 92.956 | 283046.211 | 0 | n.m. | 0 | n.m. | 154651.173 | 131.1% | -117790.968 | -71.4% | 272.114 | 292.7% | 37132.319 | 13.12%
351 | 117 | ML1E15P01 | ML1 PURCHASE LP & RH BLADES | 12/1/2015 | 6/1/2016 | 429272.31 | -113119.51 |  |  |  | 316152.8 | 0 | 1804711.945 | -110243.713 | 0 | 0 | 1694468.232 | 429272.31 | n.m. | -1917831.455 | -106.3% | 110243.713 | -100% | 0 | n.m. | 0 | n.m. | -1378315.432 | -81.34%
352 | 117 | BSPPBS313 | REP U1 BFPT Rotor with Spare | 5/1/2015 | 4/1/2016 | 235139.07 | 71915.42 |  |  |  | 307054.49 | 0 | 0 | 0 | 0 | 0 | 0 | 235139.07 | n.m. | 71915.42 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 307054.49 | n.m.
353 | 117 | ML0VC1510 | ML UREA COND PIPING RPL | 9/1/2015 | 4/1/2016 | 273161.69 | 23358.22 |  |  |  | 296519.91 | 0 | 0 | 0 | 0 | 0 | 0 | 273161.69 | n.m. | 23358.22 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 296519.91 | n.m.
354 | 117 | BSPPBS341 | Replace Bushings on 102 Transf | 4/1/2018 | 3/1/2019 |  |  |  | 290044.94 | 5852.52 | 295897.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 290044.94 | n.m. | 5852.52 | n.m. | 295897.46 | n.m.
355 | 117 | ML2E18C05 | ML Unit 2 High Energy Piping | 12/1/2017 | 9/1/2018 |  |  | 49664.17 | 239551.2 |  | 289215.37 | 0 | 0 | 0 | 361099.519 | 0 | 361099.519 | 0 | n.m. | 0 | n.m. | 49664.17 | n.m. | -121548.319 | -33.66% | 0 | n.m. | -71884.149 | -19.91%
356 | 117 | MLP18EP04 | ML E LIGHTING PANEL REPLACE | 2/1/2018 | 7/1/2019 |  |  |  | 283802.77 | -111.56 | 283691.21 | 0 | 0 | 0 | 0 | 114120.294 | 114120.294 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 283802.77 | n.m. | -114231.854 | -100.1% | 169570.916 | 148.6%
357 | 117 | ML217SP04 | REPLACE U2 PULVERIZER YOKE | 9/1/2016 | 6/1/2017 |  | 58187.05 | 215704.6 |  |  | 273891.65 | 0 | 0 | 0 | 54509.599 | 0 | 54509.599 | 0 | n.m. | 58187.05 | n.m. | 215704.6 | n.m. | -54509.599 | -100% | 0 | n.m. | 219382.051 | 402.5%
358 | 117 | ML1SP1550 | ML1 S COAL PIPE | 9/1/2015 | 1/1/2016 | 260403.34 | 3001 |  |  |  | 263404.34 | 156391.047 | 49.85 | 0 | 0 | 0 | 156440.897 | 104012.293 | 66.51% | 2951.15 | 5920% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 106963.443 | 68.37%
359 | 117 | ML019SP01 | ML PULVERIZER REBUILD CAP (#xx | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 262170.25 | 262170.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 262170.25 | n.m. | 262170.25 | n.m.
360 | 117 | ML218EP05 | ML U2 CT SHELL MONITORING SYST | 3/1/2018 | 7/1/2019 |  |  |  | 261469.98 | -58.67 | 261411.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 261469.98 | n.m. | -58.67 | n.m. | 261411.31 | n.m.
361 | 117 | ML018NP12 | ML SERVICE BUILDING ROOF | 9/1/2018 | Charges Continued After Dec 2019 |  |  |  | 244165.04 | 15120.12 | 259285.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 244165.04 | n.m. | 15120.12 | n.m. | 259285.16 | n.m.
362 | 117 | ML115SP01 | #12 PULVERIZER REBUILD | 7/1/2015 | 2/1/2016 | 263627.3 | -4405.24 |  |  |  | 259222.06 | 0 | 0 | 0 | 0 | 0 | 0 | 263627.3 | n.m. | -4405.24 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 259222.06 | n.m.
363 | 117 | ML120SP01 | ML U1 Lime Inj Rig and Pig Buy | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 258792.11 | 258792.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 258792.11 | n.m. | 258792.11 | n.m.
364 | 117 | ML016MP06 | 2016 PAVING | 12/1/2016 | 1/1/2017 |  | 253355.18 | 1356.96 |  |  | 254712.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 253355.18 | n.m. | 1356.96 | n.m. | 0 | n.m. | 0 | n.m. | 254712.14 | n.m.
365 | 117 | ML017MP02 | MH- BARGEUNLOADER CHAIN&BUCKET | 12/1/2016 | 11/1/2017 |  | 145315.2 | 108038.7 |  |  | 253353.9 | 0 | 0 | 47654.692 | 0 | 0 | 47654.692 | 0 | n.m. | 145315.2 | n.m. | 60384.008 | 126.7% | 0 | n.m. | 0 | n.m. | 205699.208 | 431.6%
366 | 117 | ML118SP22 | ML U1 BOILER CAMERA UPGRADE | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 185551.79 | 67516 | 253067.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 185551.79 | n.m. | 67516 | n.m. | 253067.79 | n.m.
367 | 117 | BSPPBS325 | Install Lagging North Side U1 | 10/1/2016 | 1/1/2017 |  | 251526.53 | 1100.52 |  |  | 252627.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 251526.53 | n.m. | 1100.52 | n.m. | 0 | n.m. | 0 | n.m. | 252627.05 | n.m.
368 | 117 | ML015VP01 | MLU0 CCR COMPLIANCE | 6/1/2015 | Charges Continued After Dec 2019 | 70724.2 | 70470.9 | 41603.21 | 36797.72 | 12230.74 | 231826.77 | 0 | 0 | 0 | 0 | 0 | 0 | 70724.2 | n.m. | 70470.9 | n.m. | 41603.21 | n.m. | 36797.72 | n.m. | 12230.74 | n.m. | 231826.77 | n.m.
369 | 117 | ML219SP06 | MLU2 21 PULVERIZER REBUILD | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 230994.26 | 230994.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 230994.26 | n.m. | 230994.26 | n.m.
370 | 117 | ML0E17C02 | ML REPLACE AMMONIA TANK | 9/1/2017 | 3/1/2018 |  |  | 197864.61 | 30413.77 |  | 228278.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 197864.61 | n.m. | 30413.77 | n.m. | 0 | n.m. | 228278.38 | n.m.
371 | 117 | MLP15SP02 | MLP S PULVERIZER REBUILD CAP | Charges Began Prior to Jan 2015 | 10/1/2015 | 220013.98 |  |  |  |  | 220013.98 | 174007.171 | 0 | 0 | 0 | 0 | 174007.171 | 46006.809 | 26.44% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 46006.809 | 26.44%
372 | 117 | ML018MP06 | ML HIGH SULFUR STAMLER REBUILD | 9/1/2018 | Charges Continued After Dec 2019 |  |  |  | 144645.08 | 68880.38 | 213525.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 144645.08 | n.m. | 68880.38 | n.m. | 213525.46 | n.m.
373 | 117 | ML017VP04 | ML-NON OUTAGE PPB FGD | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 200538.66 | 12751.9 | 77.33 | 213367.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 200538.66 | n.m. | 12751.9 | n.m. | 77.33 | n.m. | 213367.89 | n.m.
374 | 117 | ML1VC1512 | ML 12 ID FAN HUB REPLACEMENT | 9/1/2015 | 4/1/2016 | 220079.2 | -9207.1 |  |  |  | 210872.1 | 0 | 0 | 0 | 0 | 0 | 0 | 220079.2 | n.m. | -9207.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 210872.1 | n.m.
375 | 117 | MLP19EP04 | ML E LIGHTING PANEL REPLACE | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 209318.24 | 209318.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 209318.24 | n.m. | 209318.24 | n.m.
376 | 117 | BSPPBS348 | Replace 4KV Brkr Racking Mech | 8/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 208359.69 | 208359.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 208359.69 | n.m. | 208359.69 | n.m.
377 | 117 | ML217EP05 | REPLACE 21 AIR COMPRESSOR | 3/1/2017 | 11/1/2017 |  |  | 203177.53 |  |  | 203177.53 | 0 | 0 | 219043.322 | 0 | 0 | 219043.322 | 0 | n.m. | 0 | n.m. | -15865.792 | -7.243% | 0 | n.m. | 0 | n.m. | -15865.792 | -7.243%
378 | 117 | ML016VP01 | Cap Blkt - Prod Plant Blnkt | 1/1/2016 | 12/1/2017 |  | 217673.72 | -15479.53 |  |  | 202194.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 217673.72 | n.m. | -15479.53 | n.m. | 0 | n.m. | 0 | n.m. | 202194.19 | n.m.
379 | 117 | ML219VP06 | ML 21 ID FAN DE HUB REPLACE | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 201875.99 | 201875.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 201875.99 | n.m. | 201875.99 | n.m.
380 | 117 | ML017MP03 | ML MH LANDFILL FACILITY | 7/1/2017 | 3/1/2018 |  |  | 172663.53 | 28402.68 |  | 201066.21 | 0 | 0 | 270028.385 | 0 | 0 | 270028.385 | 0 | n.m. | 0 | n.m. | -97364.855 | -36.06% | 28402.68 | n.m. | 0 | n.m. | -68962.175 | -25.54%
381 | 117 | MLP19MP03 | ML MH R4 COAL CHUTE REPLACEMT | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 199325.51 | 199325.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 199325.51 | n.m. | 199325.51 | n.m.
382 | 117 | ML2VP1501 | ML2 FGD CAPITAL OUTAGE PROJECT | Charges Began Prior to Jan 2015 | 4/1/2016 | 204314.86 | -7065.2 |  |  |  | 197249.66 | 69666.554 | 0 | 0 | 0 | 0 | 69666.554 | 134648.306 | 193.3% | -7065.2 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 127583.106 | 183.1%
383 | 117 | ML116EP01 | REPAIR UNIT1 2nd RH ROTOR @CMS | 9/1/2016 | 4/1/2017 |  | 120773.29 | 75572.23 |  |  | 196345.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 120773.29 | n.m. | 75572.23 | n.m. | 0 | n.m. | 0 | n.m. | 196345.52 | n.m.
384 | 117 | MLP19EP03 | ML E PUMP REPLACEMENT DR 10 HP | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 194707.38 | 194707.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 194707.38 | n.m. | 194707.38 | n.m.
385 | 117 | ML018SP01 | PULVERIZER REBUILD CAPITAL(#xx | 3/1/2018 | 8/1/2018 |  |  |  | 190972.11 |  | 190972.11 | 0 | 0 | 0 | 0 | 188086.783 | 188086.783 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 190972.11 | n.m. | -188086.783 | -100% | 2885.327 | 1.534%
386 | 117 | ML019VP01 | ML - NON OUTAGE PPB FGD | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 189928.63 | 189928.63 | 0 | 0 | 0 | 0 | 219507.56 | 219507.56 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -29578.93 | -13.48% | -29578.93 | -13.48%
387 | 117 | ML2SM1515 | ML U2 PRECIP ROOF BAY 3-1 | 3/1/2015 | 8/1/2015 | 189564.5 |  |  |  |  | 189564.5 | 0 | 0 | 0 | 0 | 0 | 0 | 189564.5 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 189564.5 | n.m.
388 | 117 | BSPPBS332 | INST INSUL E ECON OUTLET DUCT | 5/1/2017 | 8/1/2017 |  |  | 189185.38 |  |  | 189185.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 189185.38 | n.m. | 0 | n.m. | 0 | n.m. | 189185.38 | n.m.
389 | 117 | ML217SP08 | ML U2 PRECIP ROOF BAY BOX VVV | 12/1/2017 | 9/1/2018 |  |  | 4650.38 | 181716.27 |  | 186366.65 | 0 | 0 | 0 | 228940.317 | 0 | 228940.317 | 0 | n.m. | 0 | n.m. | 4650.38 | n.m. | -47224.047 | -20.63% | 0 | n.m. | -42573.667 | -18.6%
390 | 117 | ML117SP09 | ML S PULVERIZER GEARBOX | 7/1/2017 | 1/1/2018 |  |  | 188042.46 | -2517 |  | 185525.46 | 0 | 0 | 0 | 352068.549 | 0 | 352068.549 | 0 | n.m. | 0 | n.m. | 188042.46 | n.m. | -354585.549 | -100.7% | 0 | n.m. | -166543.089 | -47.3%
391 | 117 | MLP18EP02 | ML E MOTOR REWIND / REPL +10HP | 7/1/2018 | Charges Continued After Dec 2019 |  |  |  | 123699.65 | 59760.74 | 183460.39 | 0 | 0 | 0 | 0 | 36584.593 | 36584.593 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 123699.65 | n.m. | 23176.147 | 63.35% | 146875.797 | 401.5%
392 | 117 | ML117SP11 | U1 PULVERIZER PA DUCT EJ RPL | 2/1/2017 | 5/1/2017 |  |  | 181854.09 |  |  | 181854.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 181854.09 | n.m. | 0 | n.m. | 0 | n.m. | 181854.09 | n.m.
393 | 117 | ML2SM1516 | ML U2 PRECIP ROOF BAY 4-3 | 3/1/2015 | 8/1/2015 | 180334.52 |  |  |  |  | 180334.52 | 0 | 0 | 0 | 0 | 0 | 0 | 180334.52 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 180334.52 | n.m.
394 | 117 | ML118EP07 | ML REPAIR U1 2nd RH ROTOR @CMS | 10/1/2017 | 3/1/2018 |  |  | 153741.35 | 25894.11 |  | 179635.46 | 0 | 0 | 0 | 158742.579 | 0 | 158742.579 | 0 | n.m. | 0 | n.m. | 153741.35 | n.m. | -132848.469 | -83.69% | 0 | n.m. | 20892.881 | 13.16%
395 | 117 | BSPPBS300 | BS1 Rep Storeroom Area | Charges Began Prior to Jan 2015 | 12/1/2015 | 179414.35 |  |  |  |  | 179414.35 | 21.657 | 0 | 0 | 0 | 0 | 21.657 | 179392.693 | 828336% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 179392.693 | 828336%
396 | 117 | ML219SP05 | MLU2 PRECIP ROOF BAY BOX4ROW7 | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 178925.45 | 178925.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 178925.45 | n.m. | 178925.45 | n.m.
397 | 117 | BSPPB0008 | Clg Water Facilities PPB<100k | Charges Began Prior to Jan 2015 | 6/1/2017 | -264.7 | 156178.55 | 22228.14 |  |  | 178141.99 | 67.295 | 0 | 0 | 0 | 0 | 67.295 | -331.995 | -493.3% | 156178.55 | n.m. | 22228.14 | n.m. | 0 | n.m. | 0 | n.m. | 178074.695 | 264618%
398 | 117 | ML2SP1501 | ML2 S PREC EJ REPLACEMENT | Charges Began Prior to Jan 2015 | 8/1/2015 | 177190.32 |  |  |  |  | 177190.32 | 0 | 0 | 0 | 0 | 0 | 0 | 177190.32 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 177190.32 | n.m.
399 | 117 | ML016MP03 | ML MH CONVEYOR BELT REPLACE | 6/1/2016 | 2017-06-01 |  | 113177.73 | 63508.97 | 0 |  | 176686.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 113177.73 | n.m. | 63508.97 | n.m. | 0 | n.m. | 0 | n.m. | 176686.7 | n.m.
400 | 117 | BSPPBS320 | REP U1 FD FAN DAMPER DRIVES | 10/1/2015 | 7/1/2016 | 117905.28 | 58301.18 |  |  |  | 176206.46 | 0 | 0 | 0 | 0 | 0 | 0 | 117905.28 | n.m. | 58301.18 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 176206.46 | n.m.
401 | 117 | ML218SP10 | ML U2 PRECIP EJ REPLACEMENT | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 171607.89 | 1125.42 | 172733.31 | 0 | 0 | 0 | 240963.106 | 134.281 | 241097.387 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -69355.216 | -28.78% | 991.139 | 738.1% | -68364.077 | -28.36%
402 | 117 | MLP19MP02 | MLP MH CONVEYOR BELT REPLACE | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 172014.78 | 172014.78 | 0 | 0 | 0 | 0 | 213409.83 | 213409.83 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -41395.05 | -19.4% | -41395.05 | -19.4%
403 | 117 | 000020310 | ML U0 ELG Compliance | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 170487.51 | 170487.51 | 0 | 203094.645 | 1680115.452 | 2423.2 | 338277.705 | 2223911.002 | 0 | n.m. | -203094.645 | -100% | -1680115.452 | -100% | -2423.2 | -100% | -167790.195 | -49.6% | -2053423.492 | -92.33%
404 | 117 | ML12E15P1 | ML E DROP 47 CONTROL UPGRADES | Charges Began Prior to Jan 2015 | 10/1/2015 | 169898.93 |  |  |  |  | 169898.93 | 17.584 | 0 | 0 | 0 | 0 | 17.584 | 169881.346 | 966113% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 169881.346 | 966113%
405 | 117 | MLP17EP03 | MLP E PUMP REPLACEMENT DR 10 H | 1/1/2017 | 4/1/2018 |  |  | 167367.95 | 2332.35 |  | 169700.3 | 0 | 0 | 176001.144 | 181224.389 | 56.652 | 357282.185 | 0 | n.m. | 0 | n.m. | -8633.194 | -4.905% | -178892.039 | -98.71% | -56.652 | -100% | -187581.885 | -52.5%
406 | 117 | ML016SP03 | ML S PULVERIZER REBUILD | 5/1/2016 | 5/1/2017 |  | 116861.33 | 51868.99 |  |  | 168730.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 116861.33 | n.m. | 51868.99 | n.m. | 0 | n.m. | 0 | n.m. | 168730.32 | n.m.
407 | 117 | ML1NP1710 | ML1 INSULATION RPL | 9/1/2016 | 3/1/2017 |  | 158575.07 | 2934.94 |  |  | 161510.01 | 0 | 0 | -28250.173 | 0 | 0 | -28250.173 | 0 | n.m. | 158575.07 | n.m. | 31185.113 | -110.4% | 0 | n.m. | 0 | n.m. | 189760.183 | -671.7%
408 | 117 | ML016SP01 | ML S PULVERIZER GEARBOX | 4/1/2016 | 1/1/2017 |  | 161457.28 | 6.74 |  |  | 161464.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 161457.28 | n.m. | 6.74 | n.m. | 0 | n.m. | 0 | n.m. | 161464.02 | n.m.
409 | 117 | ML1VP1504 | MLU1 #11 ID FAN REBUILD | 4/1/2015 | 6/1/2016 | 174430.31 | -15217.17 |  |  |  | 159213.14 | 0 | 0 | 0 | 0 | 0 | 0 | 174430.31 | n.m. | -15217.17 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 159213.14 | n.m.
410 | 117 | MLP14CO01 | MLP 2013 CARRY OVER | Charges Began Prior to Jan 2015 | 9/1/2016 | 153602.57 | 5477.29 |  |  |  | 159079.86 | 152.831 | 0 | 0 | 0 | 0 | 152.831 | 153449.739 | 100405% | 5477.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 158927.029 | 103989%
411 | 117 | ML119EP04 | ML UNIT 1 HIGH ENERGY PIPING | 1/1/2019 | 11/1/2019 |  |  |  |  | 154923.07 | 154923.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 154923.07 | n.m. | 154923.07 | n.m.
412 | 117 | ML217VP03 | ML2 PURCHASE 2nd RH BLADES 3RW | 12/1/2016 | 1/1/2017 |  | 293816.33 | -140139.27 |  |  | 153677.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 293816.33 | n.m. | -140139.27 | n.m. | 0 | n.m. | 0 | n.m. | 153677.06 | n.m.
413 | 117 | ML216SP04 | #21 PULVERIZER REBUILD | 3/1/2016 | 6/1/2016 |  | 152803.98 |  |  |  | 152803.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 152803.98 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 152803.98 | n.m.
414 | 117 | ML018MP01 | REPLACE COALCONVEYOR SAMPLERS | 9/1/2017 | 11/1/2018 |  |  | 38605.12 | 112106.85 |  | 150711.97 | 0 | 0 | 0 | 147165.015 | 42.802 | 147207.817 | 0 | n.m. | 0 | n.m. | 38605.12 | n.m. | -35058.165 | -23.82% | -42.802 | -100% | 3504.153 | 2.38%
415 | 117 | MLP18EP07 | ML #12 CIRCULATOR PUMP ELEMENT | 7/1/2018 | 8/1/2019 |  |  |  | 129151.55 | 21117.15 | 150268.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 129151.55 | n.m. | 21117.15 | n.m. | 150268.7 | n.m.
416 | 117 | ML118VP07 | ML #12 ID FAN HUBS PPB PORTION | 4/1/2018 | 6/1/2018 |  |  |  | 149614.49 |  | 149614.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 149614.49 | n.m. | 0 | n.m. | 149614.49 | n.m.
417 | 117 | ML217SP09 | ML U2 PRECIP ROOF BAY BOX WWW | 12/1/2017 | 9/1/2018 |  |  | 4697.36 | 141853.25 |  | 146550.61 | 0 | 0 | 0 | 228940.317 | 0 | 228940.317 | 0 | n.m. | 0 | n.m. | 4697.36 | n.m. | -87087.067 | -38.04% | 0 | n.m. | -82389.707 | -35.99%
418 | 117 | ML017SP01 | PULVERIZER REBUILD CAPITAL(#xx | 9/1/2016 | 3/1/2017 |  | 146133.44 | 228.8 |  |  | 146362.24 | 0 | 0 | 0 | 192618.863 | 0 | 192618.863 | 0 | n.m. | 146133.44 | n.m. | 228.8 | n.m. | -192618.863 | -100% | 0 | n.m. | -46256.623 | -24.01%
419 | 117 | BSPPBS338 | Repl 7 Banks Combustion Coils | 5/1/2018 | 9/1/2018 |  |  |  | 146250.98 |  | 146250.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 146250.98 | n.m. | 0 | n.m. | 146250.98 | n.m.
420 | 117 | ML0VP1603 | ML REPL SCAFFOLDING w/PLATFORM | 10/1/2016 | 3/1/2018 |  | 26568.19 | 123702.07 | -4410.51 |  | 145859.75 | 0 | 23992.248 | 11136.237 | 27247.494 | 0 | 62375.979 | 0 | n.m. | 2575.942 | 10.74% | 112565.833 | 1011% | -31658.004 | -116.2% | 0 | n.m. | 83483.771 | 133.8%
421 | 117 | ML217SP06 | ML U2 PRECIP ROOF BAY BOX YYY | 12/1/2017 | 9/1/2018 |  |  | 4650.37 | 141081.15 |  | 145731.52 | 0 | 0 | 134458.105 | 228828.157 | 0 | 363286.262 | 0 | n.m. | 0 | n.m. | -129807.735 | -96.54% | -87747.007 | -38.35% | 0 | n.m. | -217554.742 | -59.89%
422 | 117 | MLP15EP03 | MLP PUMP REPLACEMENT DR 10 H | 1/1/2015 | 7/1/2016 | 145230.7 | -24.62 |  |  |  | 145206.08 | 155860.48 | 119.25 | 0 | 0 | 0 | 155979.73 | -10629.78 | -6.82% | -143.87 | -120.6% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -10773.65 | -6.907%
423 | 117 | BSPPBS342 | REPL CATHODIC PROT TEST STA | 4/1/2018 | 8/1/2018 |  |  |  | 144648.43 |  | 144648.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 144648.43 | n.m. | 0 | n.m. | 144648.43 | n.m.
424 | 117 | ML018EP14 | ML SEWAGE TREATMNT PLANT COVER | 9/1/2018 | Charges Continued After Dec 2019 |  |  |  | 32182.6 | 111888.79 | 144071.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 32182.6 | n.m. | 111888.79 | n.m. | 144071.39 | n.m.
425 | 117 | ML017MP06 | ML MH CONVEYOR BELT REPLACE | 3/1/2017 | 4/1/2018 |  |  | 54316.02 | 88682.44 |  | 142998.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 54316.02 | n.m. | 88682.44 | n.m. | 0 | n.m. | 142998.46 | n.m.
426 | 117 | MLP17EP05 | MLP E POWER CABLE REPLACEMENT | 2/1/2017 | 1/1/2019 |  |  | 121534.39 | 22579.84 | -1594.32 | 142519.91 | 0 | 0 | 20593.778 | 28794.932 | 16.229 | 49404.939 | 0 | n.m. | 0 | n.m. | 100940.612 | 490.2% | -6215.092 | -21.58% | -1610.549 | -9924% | 93114.971 | 188.5%
427 | 117 | MLP15MP06 | MLP MH COAL CHUTE TRIPPER U2 | 3/1/2015 | 8/1/2015 | 140775.45 |  |  |  |  | 140775.45 | 0 | 0 | 0 | 0 | 0 | 0 | 140775.45 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 140775.45 | n.m.
428 | 117 | ML217SP05 | ML U2 PRECIP ROOF BAY BOX XXX | 12/1/2017 | 9/1/2018 |  |  | 6796.82 | 133839.65 |  | 140636.47 | 0 | 0 | 134458.105 | 228828.157 | 0 | 363286.262 | 0 | n.m. | 0 | n.m. | -127661.285 | -94.95% | -94988.507 | -41.51% | 0 | n.m. | -222649.792 | -61.29%
429 | 117 | ML016VP03 | ML1 AR PP REPLACE | 3/1/2016 | 9/1/2016 |  | 137966.68 |  |  |  | 137966.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 137966.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 137966.68 | n.m.
430 | 117 | ML2VP1450 | ML V AR PP RPL | Charges Began Prior to Jan 2015 | 4/1/2016 | 136260.88 | 1422.7 |  |  |  | 137683.58 | 22.267 | 0 | 0 | 0 | 0 | 22.267 | 136238.613 | 611841% | 1422.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 137661.313 | 618230%
431 | 117 | ML119EP01 | RPL MAIN TURB OIL TANK VALVE | 2/1/2019 | 11/1/2019 |  |  |  |  | 134147.92 | 134147.92 | 0 | 0 | 0 | 0 | 140974.649 | 140974.649 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -6826.729 | -4.843% | -6826.729 | -4.843%
432 | 117 | BSPPB0003 | Boiler MU Water Supply PPB<100 | Charges Began Prior to Jan 2015 | 2/1/2019 | -6136.11 |  | 136804.32 | 3188.81 | 258.98 | 134116 | 31305.885 | 42154.121 | 184912.562 | 175002.489 | 0 | 433375.057 | -37441.995 | -119.6% | -42154.121 | -100% | -48108.242 | -26.02% | -171813.679 | -98.18% | 258.98 | n.m. | -299259.057 | -69.05%
433 | 117 | ML0VP1501 | CAP BLKT PROD PLANT BLNKT | 1/1/2015 | 7/1/2016 | 134544.8 | -568.28 |  |  |  | 133976.52 | 155845.99 | 83.51 | 0 | 0 | 0 | 155929.5 | -21301.19 | -13.67% | -651.79 | -780.5% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -21952.98 | -14.08%
434 | 117 | ML018EP04 | ML HVAC REPLACEMENT | 2/1/2018 | 3/1/2019 |  |  |  | 129725.41 | 4104.19 | 133829.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 129725.41 | n.m. | 4104.19 | n.m. | 133829.6 | n.m.
435 | 117 | BSPPBS311 | BS1 REP MAIN SHAFT 15 PULV | 3/1/2015 | 4/1/2016 | 128964.46 | 3829.46 |  |  |  | 132793.92 | 0 | 0 | 0 | 0 | 0 | 0 | 128964.46 | n.m. | 3829.46 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 132793.92 | n.m.
436 | 117 | ML1EP1520 | ML1 VALVE REPLACEMENT | 2/1/2015 | 6/1/2016 | 130929.63 | 1638.8 |  |  |  | 132568.43 | 65259.099 | 16.67 | 0 | 0 | 0 | 65275.769 | 65670.531 | 100.6% | 1622.13 | 9731% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 67292.661 | 103.1%
437 | 117 | ML219SP04 | MLU2 PRECIP ROOF BAY BOX3ROW7 | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 131813.08 | 131813.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 131813.08 | n.m. | 131813.08 | n.m.
438 | 117 | ML1E16P02 | ML1 DFLP SPARE ROTOR INST | 7/1/2016 | 3/1/2017 |  | 101710.3 | 29069.32 |  |  | 130779.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 101710.3 | n.m. | 29069.32 | n.m. | 0 | n.m. | 0 | n.m. | 130779.62 | n.m.
439 | 117 | ML016EP03 | ML0 E PUMP REPLACE DR 10 HP | 3/1/2016 | 6/1/2017 |  | 115231.28 | 10957.97 |  |  | 126189.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 115231.28 | n.m. | 10957.97 | n.m. | 0 | n.m. | 0 | n.m. | 126189.25 | n.m.
440 | 117 | ML018NP10 | ML GUARD RAIL UPGRADES | 10/1/2018 | 3/1/2019 |  |  |  | 108006.88 | 18016.09 | 126022.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 108006.88 | n.m. | 18016.09 | n.m. | 126022.97 | n.m.
441 | 117 | ML1VP1550 | ML V AR PP RPL | 11/1/2015 | 1/1/2017 | 7236.73 | 116771.05 | 1671.78 |  |  | 125679.56 | 119798.551 | 0 | 0 | 0 | 0 | 119798.551 | -112561.821 | -93.96% | 116771.05 | n.m. | 1671.78 | n.m. | 0 | n.m. | 0 | n.m. | 5881.009 | 4.909%
442 | 117 | ML116VP03 | SPARE IP BLADES 2nd RH 2 ROWS | 12/1/2016 | 4/1/2017 |  | 123931.73 | 1046.78 |  |  | 124978.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 123931.73 | n.m. | 1046.78 | n.m. | 0 | n.m. | 0 | n.m. | 124978.51 | n.m.
443 | 117 | ITCB11700 | KENTUCKY POWER - GEN | Charges Began Prior to Jan 2015 | 3/1/2019 |  | 29128.41 | 88626.3 | 6323.97 | 615.43 | 124694.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 29128.41 | n.m. | 88626.3 | n.m. | 6323.97 | n.m. | 615.43 | n.m. | 124694.11 | n.m.
444 | 117 | MLP14NP06 | MLP CAPITAL TOOLS | Charges Began Prior to Jan 2015 | 4/1/2016 | 126960.97 | -2850.1 |  |  |  | 124110.87 | 25.111 | 0 | 0 | 0 | 0 | 25.111 | 126935.859 | 505499% | -2850.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 124085.759 | 494149%
445 | 117 | BSPPBS303 | BS2 Rep Stack Alimak Power Con | Charges Began Prior to Jan 2015 | 3/1/2016 | 123292.16 | 494.78 |  |  |  | 123786.94 | 0 | 0 | 0 | 0 | 0 | 0 | 123292.16 | n.m. | 494.78 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 123786.94 | n.m.
446 | 117 | BSPPBS328 | BS1 REPL TURBINE FLOOR SURFACE | 11/1/2016 | 1/1/2017 |  | 122127.14 | 934.55 |  |  | 123061.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 122127.14 | n.m. | 934.55 | n.m. | 0 | n.m. | 0 | n.m. | 123061.69 | n.m.
447 | 117 | ML119SP08 | ML U1 DEMINERALIZER RESIN RPL | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 6.7 | 121997.79 | 122004.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6.7 | n.m. | 121997.79 | n.m. | 122004.49 | n.m.
448 | 117 | ML217SP07 | ML U2 PRECIP ROOF BAY BOX ZZZ | 12/1/2017 | 9/1/2018 |  |  | 4650.38 | 116972.32 |  | 121622.7 | 0 | 0 | 134458.105 | 228828.157 | 0 | 363286.262 | 0 | n.m. | 0 | n.m. | -129807.725 | -96.54% | -111855.837 | -48.88% | 0 | n.m. | -241663.562 | -66.52%
449 | 117 | ML017SP02 | PULVERIZER REBUILD CAPITAL(#YY | 8/1/2017 | 1/1/2018 |  |  | 123876.98 | -4802.5 |  | 119074.48 | 0 | 0 | 0 | 191225.297 | 0 | 191225.297 | 0 | n.m. | 0 | n.m. | 123876.98 | n.m. | -196027.797 | -102.5% | 0 | n.m. | -72150.817 | -37.73%
450 | 117 | ML219EP03 | ML UNIT2 ACID LINE REPLACEMENT | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 118896.84 | 118896.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 118896.84 | n.m. | 118896.84 | n.m.
451 | 117 | ML215SM01 | BURNER REFRACTORY | 5/1/2015 | 8/1/2015 | 118205.81 |  |  |  |  | 118205.81 | 0 | 0 | 0 | 0 | 0 | 0 | 118205.81 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 118205.81 | n.m.
452 | 117 | ML12E15P2 | ML E PLC PURCHASE AND INSTALL | Charges Began Prior to Jan 2015 | 9/1/2015 | 117424.17 |  |  |  |  | 117424.17 | 74.786 | 0 | 0 | 0 | 0 | 74.786 | 117349.384 | 156914% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 117349.384 | 156914%
453 | 117 | BSPPBS321 | BS1 REPL BOILER OBSERV CAMERA | 12/1/2015 | 11/1/2016 | 71905 | 44368.09 |  |  |  | 116273.09 | 0 | 0 | 0 | 0 | 0 | 0 | 71905 | n.m. | 44368.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 116273.09 | n.m.
454 | 117 | ML016MP04 | BARGE UNLOADR CHAIN CAP SPARE | 10/1/2016 | 4/1/2017 |  | 116001.21 | -327.74 |  |  | 115673.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 116001.21 | n.m. | -327.74 | n.m. | 0 | n.m. | 0 | n.m. | 115673.47 | n.m.
455 | 117 | BSPPBS308 | BS1 Rep 15 Pulv Grinding Zone | 2/1/2015 | 5/1/2015 | 114645.78 |  |  |  |  | 114645.78 | 0 | 0 | 0 | 0 | 0 | 0 | 114645.78 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 114645.78 | n.m.
456 | 117 | ML018NP04 | ML STOREROOM SECURITY SYSTEM | 7/1/2018 | 6/1/2019 |  |  |  | 96213.52 | 18104.38 | 114317.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 96213.52 | n.m. | 18104.38 | n.m. | 114317.9 | n.m.
457 | 117 | ML218SP08 | ML2 LONGER O2 PROBE REPLACEMN | 10/1/2017 | 5/1/2018 |  |  | 82807.51 | 30336.21 |  | 113143.72 | 0 | 0 | 0 | 100240.072 | 56.173 | 100296.245 | 0 | n.m. | 0 | n.m. | 82807.51 | n.m. | -69903.862 | -69.74% | -56.173 | -100% | 12847.475 | 12.81%
458 | 117 | MLP18EP06 | MLP E VALVE REPLACEMENT 6 IN G | 1/1/2018 | 9/1/2019 |  |  |  | 101505.8 | 11604.92 | 113110.72 | 0 | 0 | 0 | 0 | 110180.444 | 110180.444 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 101505.8 | n.m. | -98575.524 | -89.47% | 2930.276 | 2.66%
459 | 117 | ML017EP04 | ML HVAC REPLACEMENT | 5/1/2017 | 3/1/2018 |  |  | 103312.14 | 9341.29 |  | 112653.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 103312.14 | n.m. | 9341.29 | n.m. | 0 | n.m. | 112653.43 | n.m.
460 | 117 | BSPPBS302 | BS1 RepRebuild E W Air Comp | Charges Began Prior to Jan 2015 | 9/1/2015 | 112533.32 |  |  |  |  | 112533.32 | 4.136 | 0 | 0 | 0 | 0 | 4.136 | 112529.184 | 2720725% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 112529.184 | 2720725%
461 | 117 | ML219VP07 | ML 22 ID FAN DE HUB REPLACEMEN | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 112115.88 | 112115.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 112115.88 | n.m. | 112115.88 | n.m.
462 | 117 | ML117EP10 | ML1 RPL FEEDWATER CHEM PUMPS | 8/1/2017 | 1/1/2019 |  |  | 57587.71 | 54966.6 | -584.97 | 111969.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 57587.71 | n.m. | 54966.6 | n.m. | -584.97 | n.m. | 111969.34 | n.m.
463 | 117 | MLP15EP04 | MLP E LIGHTING PANEL REPLACE | 2/1/2015 | 1/1/2017 | 79394.6 | 32281.2 | 4.76 |  |  | 111680.56 | 154316.545 | 95.34 | 0 | 0 | 0 | 154411.885 | -74921.945 | -48.55% | 32185.86 | 33759% | 4.76 | n.m. | 0 | n.m. | 0 | n.m. | -42731.325 | -27.67%
464 | 117 | ML0VP1604 | ML BRIDGE TO ACCESS HYDROCLONE | 10/1/2016 | 7/1/2017 |  | 95521.85 | 14979.21 |  |  | 110501.06 | 0 | 71976.703 | 0 | 0 | 0 | 71976.703 | 0 | n.m. | 23545.147 | 32.71% | 14979.21 | n.m. | 0 | n.m. | 0 | n.m. | 38524.357 | 53.52%
465 | 117 | IT1171321 | Regulated RTU Project - KPCO | 3/1/2015 | 12/1/2016 | 26306.34 | 83706.18 |  |  |  | 110012.52 | 283344.962 | 151.8 | 0 | 0 | 0 | 283496.762 | -257038.622 | -90.72% | 83554.38 | 55042% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -173484.242 | -61.19%
466 | 117 | MLP19MP01 | MLP MH COAL CHUTE REPLACEMENT | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 109504.57 | 109504.57 | 0 | 0 | 0 | 0 | 44389.673 | 44389.673 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 65114.897 | 146.7% | 65114.897 | 146.7%
467 | 117 | MLP15NP01 | MLP NP PLANT LABOR FOR CAPITAL | 2/1/2015 | 6/1/2016 | 64846.11 | 43871.31 |  |  |  | 108717.42 | 183010.892 | 63.21 | 0 | 0 | 0 | 183074.102 | -118164.782 | -64.57% | 43808.1 | 69306% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -74356.682 | -40.62%
468 | 117 | BSPPBS317 | BS1 REP 13 PA FAN MTRBRG BSE | 6/1/2015 | 9/1/2015 | 107523.41 |  |  |  |  | 107523.41 | 0 | 0 | 0 | 0 | 0 | 0 | 107523.41 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 107523.41 | n.m.
469 | 117 | MLU213CO1 | ML2 E BFPT INSPECTION | 3/1/2015 | 1/1/2016 | 107217.81 | -296.24 |  |  |  | 106921.57 | 128433.833 | 0 | 0 | 0 | 0 | 128433.833 | -21216.023 | -16.52% | -296.24 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -21512.263 | -16.75%
470 | 117 | ML016VP04 | PURCHASE ID FAN BLADES | 4/1/2016 | 4/1/2016 |  | 106559.28 |  |  |  | 106559.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 106559.28 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 106559.28 | n.m.
471 | 117 | 000025231 | 2018 Gen Plt Cap Blkt - KYPC-G | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 39895.79 | 66042.98 | 105938.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 39895.79 | n.m. | 66042.98 | n.m. | 105938.77 | n.m.
472 | 117 | ML117EP03 | REPLACE U1 WELL WATER TANK PPB | 1/1/2017 | 3/1/2018 |  |  | 123113.12 | -17892.41 |  | 105220.71 | 0 | 0 | 252172.101 | 0 | 0 | 252172.101 | 0 | n.m. | 0 | n.m. | -129058.981 | -51.18% | -17892.41 | n.m. | 0 | n.m. | -146951.391 | -58.27%
473 | 117 | ML2EP1715 | ML2 E RESIN REPLACEMENT | 9/1/2016 | 1/1/2017 |  | 104300.77 | 373.52 |  |  | 104674.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 104300.77 | n.m. | 373.52 | n.m. | 0 | n.m. | 0 | n.m. | 104674.29 | n.m.
474 | 117 | MLP15EP01 | ML CABLE PULL | 2/1/2015 | 6/1/2016 | 105201.57 | -892.35 |  |  |  | 104309.22 | 83117.833 | 44.62 | 0 | 0 | 0 | 83162.453 | 22083.737 | 26.57% | -936.97 | -2100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21146.767 | 25.43%
475 | 117 | ML116SP02 | UNIT 1 OUTLET DUCTWORK CAPITAL | 9/1/2016 | 3/1/2017 |  | 67084.31 | 36717.06 |  |  | 103801.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 67084.31 | n.m. | 36717.06 | n.m. | 0 | n.m. | 0 | n.m. | 103801.37 | n.m.
476 | 117 | BSPPBS307 | BS1 REP 16 PULV GRINDING ZONE | 2/1/2015 | 6/1/2015 | 102673.63 |  |  |  |  | 102673.63 | 0 | 0 | 0 | 0 | 0 | 0 | 102673.63 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 102673.63 | n.m.
477 | 117 | ML116SP06 | ML1 O2 PROBE REPLACEMENT | 12/1/2016 | 5/1/2017 |  | 72353.69 | 29361.92 |  |  | 101715.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 72353.69 | n.m. | 29361.92 | n.m. | 0 | n.m. | 0 | n.m. | 101715.61 | n.m.
478 | 117 | ML018EP16 | ML CEMS HG SORBENT BU SYSTEM | 10/1/2018 | 10/1/2019 |  |  |  | 10154.14 | 91389.28 | 101543.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10154.14 | n.m. | 91389.28 | n.m. | 101543.42 | n.m.
479 | 117 | ML118SP01 | ML U1 PRECIP EJ REPLACEMENT | 3/1/2018 | 7/1/2019 |  |  |  | 101112.26 | -280.98 | 100831.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 101112.26 | n.m. | -280.98 | n.m. | 100831.28 | n.m.
480 | 117 | MLP19EP01 | ML E MOTORS GREATER THAN 10 HP | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 100699.74 | 100699.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 100699.74 | n.m. | 100699.74 | n.m.
481 | 117 | ML016EP07 | ML0 E CIRCUIT BRKR REPLACE | 2/1/2016 | 10/1/2017 |  | 80848.25 | 19081.03 | 0 |  | 99929.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 80848.25 | n.m. | 19081.03 | n.m. | 0 | n.m. | 0 | n.m. | 99929.28 | n.m.
482 | 117 | ML018VP02 | ML0 V BALL MILL REBUILD | 10/1/2018 | 6/1/2019 |  |  |  | 96636.49 | 1920.67 | 98557.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 96636.49 | n.m. | 1920.67 | n.m. | 98557.16 | n.m.
483 | 117 | MLP18SP01 | ML SAFETY VALVES ( 4 ) | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 96297.65 | 96297.65 | 0 | 0 | 0 | 89917.761 | 13.035 | 89930.796 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -89917.761 | -100% | 96284.615 | 738662% | 6366.854 | 7.08%
484 | 117 | ML018EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 2/1/2018 | 7/1/2019 |  |  |  | 96189.96 | -209.01 | 95980.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 96189.96 | n.m. | -209.01 | n.m. | 95980.95 | n.m.
485 | 117 | ML019NP01 | ML CAPITAL TOOLS | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 95839.41 | 95839.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 95839.41 | n.m. | 95839.41 | n.m.
486 | 117 | 000023038 | ML Hg Monitoring - MATS | Charges Began Prior to Jan 2015 | 3/1/2016 | 92466.08 | 3239.77 |  |  |  | 95705.85 | 48457.122 | 0 | 0 | 0 | 0 | 48457.122 | 44008.958 | 90.82% | 3239.77 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 47248.728 | 97.51%
487 | 117 | ML019VP02 | ML0 V BALL MILL REBUILD | 11/1/2018 | 11/1/2019 |  |  |  | 430.74 | 95205.44 | 95636.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 430.74 | n.m. | 95205.44 | n.m. | 95636.18 | n.m.
488 | 117 | ML015MP01 | Coal Crusher Rebuild | 6/1/2015 | 6/1/2016 | 95601.43 | -368.45 |  |  |  | 95232.98 | 0 | 0 | 0 | 0 | 0 | 0 | 95601.43 | n.m. | -368.45 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 95232.98 | n.m.
489 | 117 | ML017EP03 | ML E ELLIOTT AIR COMPRESSOR RP | 4/1/2017 | 10/1/2017 |  |  | 94678.76 |  |  | 94678.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 94678.76 | n.m. | 0 | n.m. | 0 | n.m. | 94678.76 | n.m.
490 | 117 | ML016EP04 | ML0E LIGHTING PANEL REPLACE | 2/1/2016 | 11/1/2017 |  | 70659.13 | 22004.68 |  |  | 92663.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 70659.13 | n.m. | 22004.68 | n.m. | 0 | n.m. | 0 | n.m. | 92663.81 | n.m.
491 | 117 | MLP15MP02 | MLP MH CONVEYOR BELT REPLACE | 2/1/2015 | 5/1/2018 | 91079.07 | 911.79 | -326.33 | 298.62 |  | 91963.15 | 15635.695 | 0 | 0 | 0 | 0 | 15635.695 | 75443.375 | 482.5% | 911.79 | n.m. | -326.33 | n.m. | 298.62 | n.m. | 0 | n.m. | 76327.455 | 488.2%
492 | 117 | ML117EP09 | U1 2nd RH TURBINE ROTOR REPLAC | 1/1/2017 | 12/1/2017 |  |  | 91766.58 |  |  | 91766.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 91766.58 | n.m. | 0 | n.m. | 0 | n.m. | 91766.58 | n.m.
493 | 117 | BSPPBS351 | Replace Auto Voltage Regulator | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 91562.77 | 91562.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 91562.77 | n.m. | 91562.77 | n.m.
494 | 117 | ML1SP1560 | ML1 S CAPACITY DAMPER DRIVE RP | Charges Began Prior to Jan 2015 | 2/1/2016 | 91015.47 | 210.67 |  |  |  | 91226.14 | 0.78 | 0 | 0 | 0 | 0 | 0.78 | 91014.69 | 11668550% | 210.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 91225.36 | 11695559%
495 | 117 | ML0VP1601 | Cap Blkt - Prod Plant Blnkt | 1/1/2016 | 3/1/2017 |  | 84902.8 | 5663.01 |  |  | 90565.81 | 0 | 58517.09 | 35.985 | 0 | 0 | 58553.075 | 0 | n.m. | 26385.71 | 45.09% | 5627.025 | 15637% | 0 | n.m. | 0 | n.m. | 32012.735 | 54.67%
496 | 117 | MLP14MP03 | ML MH MATERIAL HANDLING PPB | Charges Began Prior to Jan 2015 | 12/1/2015 | 88812.86 |  |  |  |  | 88812.86 | 212.903 | 0 | 0 | 0 | 0 | 212.903 | 88599.957 | 41615% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 88599.957 | 41615%
497 | 117 | ML118EP08 | ML U1 RPL PLANT CONTRL BATTERY | 12/1/2017 | 6/1/2018 |  |  | 69570.05 | 19218.11 |  | 88788.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 69570.05 | n.m. | 19218.11 | n.m. | 0 | n.m. | 88788.16 | n.m.
498 | 117 | ML016EP11 | CFB BUILDING UPSTAIRS HVAC RPL | 10/1/2016 | 4/1/2017 |  | 101222.07 | -12920.44 |  |  | 88301.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 101222.07 | n.m. | -12920.44 | n.m. | 0 | n.m. | 0 | n.m. | 88301.63 | n.m.
499 | 117 | ML017EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 5/1/2017 | 8/1/2018 |  |  | 74903.62 | 13035.23 |  | 87938.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 74903.62 | n.m. | 13035.23 | n.m. | 0 | n.m. | 87938.85 | n.m.
500 | 117 | BSPPBS363 | BS1 BFPT (SPARE) BLADE REPLACE | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 87715.37 | 87715.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 87715.37 | n.m. | 87715.37 | n.m.
501 | 117 | MLTRANS15 | ML2 CC CC2 TIE IN | 5/1/2015 | 12/1/2015 | 86591.39 |  |  |  |  | 86591.39 | 0 | 0 | 0 | 0 | 0 | 0 | 86591.39 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 86591.39 | n.m.
502 | 117 | ML218EP07 | ML #21A CIRC WATER PUMP REPLAC | 9/1/2018 | 3/1/2019 |  |  |  | 66189.37 | 20322.96 | 86512.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 66189.37 | n.m. | 20322.96 | n.m. | 86512.33 | n.m.
503 | 117 | ML218SP06 | REPLACE 26E BURNERTUBE OPENING | 12/1/2017 | 7/1/2018 |  |  | 12946 | 72951.4 |  | 85897.4 | 0 | 0 | 0 | 124713.087 | 0 | 124713.087 | 0 | n.m. | 0 | n.m. | 12946 | n.m. | -51761.687 | -41.5% | 0 | n.m. | -38815.687 | -31.12%
504 | 117 | ML017NP04 | ML UPGRADE RSO BREAK AREA | 11/1/2017 | 2/1/2018 |  |  | 71621.01 | 14012.14 |  | 85633.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 71621.01 | n.m. | 14012.14 | n.m. | 0 | n.m. | 85633.15 | n.m.
505 | 117 | ML219VP08 | ML 22 ID FAN DCHG VLV EJ | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 84840.09 | 84840.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 84840.09 | n.m. | 84840.09 | n.m.
506 | 117 | ML018EP11 | ML CIRCULATING WATERPMP MOTORS | 10/1/2018 | 11/1/2019 |  |  |  | 51113.76 | 33148.37 | 84262.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 51113.76 | n.m. | 33148.37 | n.m. | 84262.13 | n.m.
507 | 117 | ML218SP20 | ML REPLACE U2 PULVERIZER YOKE | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 86610.09 | -2473.46 | 84136.63 | 0 | 0 | 0 | 0 | 59751.963 | 59751.963 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 86610.09 | n.m. | -62225.423 | -104.1% | 24384.667 | 40.81%
508 | 117 | ML016VP08 | UPS ON FGD | 12/1/2016 | 1/1/2019 |  | 39306.92 | 19097.64 | 27113.22 | -1731.93 | 83785.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 39306.92 | n.m. | 19097.64 | n.m. | 27113.22 | n.m. | -1731.93 | n.m. | 83785.85 | n.m.
509 | 117 | ML216SP06 | ML-REPLACE CROSSOVER PIPE EJ | 2/1/2016 | 11/1/2016 |  | 83366.75 |  |  |  | 83366.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 83366.75 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 83366.75 | n.m.
510 | 117 | ML119EP07 | ML UNIT1 ACID LINE REPLACEMENT | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 81852.43 | 81852.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 81852.43 | n.m. | 81852.43 | n.m.
511 | 117 | MLP17EP01 | MLP E MOTORS GREATER THAN 10 H | 3/1/2017 | 7/1/2018 |  |  | 78323.54 | 2708.04 |  | 81031.58 | 0 | 0 | 68648.474 | 70.56 | 0 | 68719.034 | 0 | n.m. | 0 | n.m. | 9675.066 | 14.09% | 2637.48 | 3738% | 0 | n.m. | 12312.546 | 17.92%
512 | 117 | BSPPB0017 | Turb Valves & Ctrls PPB<100k | 12/1/2016 | 4/1/2018 |  | 1639.26 | 76489 | 2636.25 |  | 80764.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1639.26 | n.m. | 76489 | n.m. | 2636.25 | n.m. | 0 | n.m. | 80764.51 | n.m.
513 | 117 | MLP15NP06 | MLP CAPITAL TOOLS | 5/1/2015 | 3/1/2017 | 105370.29 | -24976.8 | 147.28 |  |  | 80540.77 | 0 | 0 | 0 | 0 | 0 | 0 | 105370.29 | n.m. | -24976.8 | n.m. | 147.28 | n.m. | 0 | n.m. | 0 | n.m. | 80540.77 | n.m.
514 | 117 | ML218SP07 | REPLACE 26F BURNERTUBE OPENING | 12/1/2017 | 9/1/2018 |  |  | 12946 | 67132.66 |  | 80078.66 | 0 | 0 | 0 | 124713.087 | 0 | 124713.087 | 0 | n.m. | 0 | n.m. | 12946 | n.m. | -57580.427 | -46.17% | 0 | n.m. | -44634.427 | -35.79%
515 | 117 | BSPPB0015 | SCR Projects PPB<100k | Charges Began Prior to Jan 2015 | 3/1/2016 | 53963.54 | 24892.52 |  |  |  | 78856.06 | 11.143 | 0 | 0 | 0 | 0 | 11.143 | 53952.397 | 484182% | 24892.52 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 78844.917 | 707574%
516 | 117 | ML017EP11 | ML WASTE TANK CATHODIC PROTECT | 12/1/2017 | 7/1/2018 |  |  | -253306.54 | 331395.96 |  | 78089.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | -253306.54 | n.m. | 331395.96 | n.m. | 0 | n.m. | 78089.42 | n.m.
517 | 117 | ML018NP07 | ML NEW GATE FOR GATE 3 | 8/1/2018 | Charges Continued After Dec 2019 |  |  |  | 61295.05 | 15746.09 | 77041.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 61295.05 | n.m. | 15746.09 | n.m. | 77041.14 | n.m.
518 | 117 | MLP16EP08 | ML PDM UPGRADES | 3/1/2016 | 1/1/2017 |  | 71256.24 | 4357.02 |  |  | 75613.26 | 0 | 58517.09 | 35.99 | 0 | 0 | 58553.08 | 0 | n.m. | 12739.15 | 21.77% | 4321.03 | 12006% | 0 | n.m. | 0 | n.m. | 17060.18 | 29.14%
519 | 117 | ML218SP05 | REPLACE 26D BURNERTUBE OPENING | 12/1/2017 | 9/1/2018 |  |  | 12946 | 61586.52 |  | 74532.52 | 0 | 0 | 0 | 124713.087 | 0 | 124713.087 | 0 | n.m. | 0 | n.m. | 12946 | n.m. | -63126.567 | -50.62% | 0 | n.m. | -50180.567 | -40.24%
520 | 117 | MLP18EP08 | ML #12 CIRCULATOR PUMP MOTOR | 8/1/2018 | 11/1/2019 |  |  |  | 50006.17 | 24310.06 | 74316.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50006.17 | n.m. | 24310.06 | n.m. | 74316.23 | n.m.
521 | 117 | ML016VP06 | INSTALL STEPS TO ID FAN | 11/1/2016 | 4/1/2017 |  | 47407.43 | 26588.26 |  |  | 73995.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 47407.43 | n.m. | 26588.26 | n.m. | 0 | n.m. | 0 | n.m. | 73995.69 | n.m.
522 | 117 | BSPPBS327 | Repl U1 Turbine Walls Beams | 10/1/2016 | 1/1/2017 |  | 71024.85 | 469.44 |  |  | 71494.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 71024.85 | n.m. | 469.44 | n.m. | 0 | n.m. | 0 | n.m. | 71494.29 | n.m.
523 | 117 | ML2EP1520 | ML2 VALVE REPLACEMENT | 2/1/2015 | 12/1/2015 | 71349.04 |  |  |  |  | 71349.04 | 64134.41 | 0 | 0 | 0 | 0 | 64134.41 | 7214.63 | 11.25% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7214.63 | 11.25%
524 | 117 | ML017EP06 | GATE1 LIGHTS & GUARDGATE POWER | 3/1/2017 | 1/1/2018 |  |  | 69385.12 | 1803.27 |  | 71188.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 69385.12 | n.m. | 1803.27 | n.m. | 0 | n.m. | 71188.39 | n.m.
525 | 117 | ML117EP11 | ML U1 1st RH EXH PIPING SPRING | 12/1/2017 | 5/1/2018 |  |  | 112.32 | 69372.38 |  | 69484.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 112.32 | n.m. | 69372.38 | n.m. | 0 | n.m. | 69484.7 | n.m.
526 | 117 | FHNERC117 | FHG NERC PPB KEPCo | Charges Began Prior to Jan 2015 | 10/1/2017 | 51439.39 | 16209.15 | 861.89 |  |  | 68510.43 | 6.7 | 0 | 0 | 0 | 0 | 6.7 | 51432.69 | 767652% | 16209.15 | n.m. | 861.89 | n.m. | 0 | n.m. | 0 | n.m. | 68503.73 | 1022444%
527 | 117 | MLP18EP03 | ML E PUMP REPLACEMENT DR 10 HP | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 68223.93 | 38.85 | 68262.78 | 0 | 0 | 0 | 0 | 183716.278 | 183716.278 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 68223.93 | n.m. | -183677.428 | -99.98% | -115453.498 | -62.84%
528 | 117 | ML118EP04 | REP RFL9300 PILOT WIRE SYSTEM | 2/1/2019 | 11/1/2019 |  |  |  |  | 67456.46 | 67456.46 | 0 | 0 | 0 | 90361.153 | 117880.6 | 208241.753 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -90361.153 | -100% | -50424.14 | -42.78% | -140785.293 | -67.61%
529 | 117 | ML019EP02 | ML TRANSFORMER REPLACEMENT | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 67033.21 | 67033.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 67033.21 | n.m. | 67033.21 | n.m.
530 | 117 | ML117EP04 | REPLACE #11 RDV to NASH PUMP | 2/1/2019 | 11/1/2019 |  |  |  |  | 66949.39 | 66949.39 | 0 | 0 | 0 | 0 | 145001.883 | 145001.883 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -78052.493 | -53.83% | -78052.493 | -53.83%
531 | 117 | ML118SP19 | ML U1 TURBINE BASEMENT FIRE SY | 11/1/2018 | 1/1/2019 |  |  |  | 66806.57 | -187.27 | 66619.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 66806.57 | n.m. | -187.27 | n.m. | 66619.3 | n.m.
532 | 117 | MLP19EP02 | ML E MOTOR REWINDSOVER 10HP | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 65591.32 | 65591.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 65591.32 | n.m. | 65591.32 | n.m.
533 | 117 | ML217VP05 | INSTALL 2nd RH BLADES 3rd ROW | 5/1/2017 | 7/1/2018 |  |  | 62572.06 | 1809.67 |  | 64381.73 | 0 | 0 | 3546.884 | 0 | 0 | 3546.884 | 0 | n.m. | 0 | n.m. | 59025.176 | 1664% | 1809.67 | n.m. | 0 | n.m. | 60834.846 | 1715%
534 | 117 | ML216EP06 | ML2 RPL FAILED BFP ROTATING EL | 12/1/2016 | 4/1/2017 |  | 1039.04 | 61178 |  |  | 62217.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1039.04 | n.m. | 61178 | n.m. | 0 | n.m. | 0 | n.m. | 62217.04 | n.m.
535 | 117 | ML018NP08 | ML TURNSTILE ROOFS AND GRATING | 8/1/2018 | Charges Continued After Dec 2019 |  |  |  | 51275.75 | 10793.78 | 62069.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 51275.75 | n.m. | 10793.78 | n.m. | 62069.53 | n.m.
536 | 117 | ML016VP09 | SELF CONTAINED RESTROOM SYSTEM | 12/1/2016 | 3/1/2018 |  | 30600 | 30877 | 296.19 |  | 61773.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 30600 | n.m. | 30877 | n.m. | 296.19 | n.m. | 0 | n.m. | 61773.19 | n.m.
537 | 117 | ML115VP01 | ML1 FD & PA FAN VIBRTN MNTR | 8/1/2015 | 3/1/2016 | 60618.36 | 894.46 |  |  |  | 61512.82 | 0 | 0 | 0 | 0 | 0 | 0 | 60618.36 | n.m. | 894.46 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 61512.82 | n.m.
538 | 117 | ML219EP14 | ML219 21 CIRC MTR DIODE RING | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 60390.91 | 60390.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 60390.91 | n.m. | 60390.91 | n.m.
539 | 117 | MLP18EP01 | ML E MOTORS GREATER THAN 10 HP | 1/1/2018 | 6/1/2019 |  |  |  | 55492.12 | 4648.15 | 60140.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 55492.12 | n.m. | 4648.15 | n.m. | 60140.27 | n.m.
540 | 117 | BSPPBS324 | BS1 REPL TURBINE FLR LIGHTING | 9/1/2016 | 12/1/2016 |  | 59887.57 |  |  |  | 59887.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 59887.57 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 59887.57 | n.m.
541 | 117 | ML116EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 4/1/2016 | 4/1/2018 |  | 32094.33 | 17642.23 | 9751.38 |  | 59487.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 32094.33 | n.m. | 17642.23 | n.m. | 9751.38 | n.m. | 0 | n.m. | 59487.94 | n.m.
542 | 117 | MLU217PPI | MLU2 PPB PROJECT INSTALL | 9/1/2016 | 12/1/2016 |  | 59469.39 |  |  |  | 59469.39 | 0 | 0 | -79760.51 | -141.73 | 0 | -79902.24 | 0 | n.m. | 59469.39 | n.m. | 79760.51 | -100% | 141.73 | -100% | 0 | n.m. | 139371.63 | -174.4%
543 | 117 | BSPPBS329 | BS1 REPLACE TURB COATING | 10/1/2016 | 1/1/2017 |  | 59083.35 | 229.84 |  |  | 59313.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 59083.35 | n.m. | 229.84 | n.m. | 0 | n.m. | 0 | n.m. | 59313.19 | n.m.
544 | 117 | ML018EP06 | ML #12 RIVER WATER MU PUMP RPL | 8/1/2018 | 10/1/2018 |  |  |  | 59009.28 |  | 59009.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 59009.28 | n.m. | 0 | n.m. | 59009.28 | n.m.
545 | 117 | MLP15MP04 | MLP MH COAL CHUTE TRIPPER U1 | 3/1/2015 | 7/1/2015 | 58433.26 |  |  |  |  | 58433.26 | 0 | 0 | 0 | 0 | 0 | 0 | 58433.26 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 58433.26 | n.m.
546 | 117 | ML117EP02 | U1 AH SOOTBLOWER ECON SONICHRN | 8/1/2017 | 12/1/2017 |  |  | 58422.77 |  |  | 58422.77 | 0 | 0 | 80633.729 | 53.65 | 0 | 80687.379 | 0 | n.m. | 0 | n.m. | -22210.959 | -27.55% | -53.65 | -100% | 0 | n.m. | -22264.609 | -27.59%
547 | 117 | ML018NP11 | ML GATE 3 EMPLOYEE STAIRS | 9/1/2018 | 4/1/2019 |  |  |  | 27112.12 | 30771.7 | 57883.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 27112.12 | n.m. | 30771.7 | n.m. | 57883.82 | n.m.
548 | 117 | 000023459 | ML U0 Connor Run (KYPCO) | Charges Began Prior to Jan 2015 | 2015-08-01 | 57605.97 |  |  |  |  | 57605.97 | -1873928.033 | 0 | 0 | 0 | 0 | -1873928.033 | 1931534.003 | -103.1% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1931534.003 | -103.1%
549 | 117 | ML216SP12 | ML2 #5 PRECIP EXPJOINT REPLACE | 12/1/2016 | 9/1/2018 |  | 51825.45 | -43156.98 | 48814.58 |  | 57483.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 51825.45 | n.m. | -43156.98 | n.m. | 48814.58 | n.m. | 0 | n.m. | 57483.05 | n.m.
550 | 117 | ML115EP03 | ML1 RH STEAM LEAD - HE PIPING | 9/1/2015 | 3/1/2016 | 49877.01 | 6829.36 |  |  |  | 56706.37 | 0 | 0 | 0 | 0 | 0 | 0 | 49877.01 | n.m. | 6829.36 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 56706.37 | n.m.
551 | 117 | ML017EP02 | REPLACE AMMONIA TANK | 10/1/2016 | 8/1/2019 |  | 60892.02 | -23222.48 | 9225.69 | 9343.95 | 56239.18 | 0 | 0 | 43275.359 | 0 | 0 | 43275.359 | 0 | n.m. | 60892.02 | n.m. | -66497.839 | -153.7% | 9225.69 | n.m. | 9343.95 | n.m. | 12963.821 | 29.96%
552 | 117 | ML117VP06 | RPL #11 ID FAN HYDRAULIC CYL | 3/1/2018 | 6/1/2019 |  |  |  | 58724.84 | -2504.21 | 56220.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 58724.84 | n.m. | -2504.21 | n.m. | 56220.63 | n.m.
553 | 117 | ML118SP05 | RPL AUMA TEMPER AIR DAMPER DRV | 12/1/2017 | 5/1/2018 |  |  | 45139.82 | 10708.76 |  | 55848.58 | 0 | 0 | 0 | 0 | 50077.912 | 50077.912 | 0 | n.m. | 0 | n.m. | 45139.82 | n.m. | 10708.76 | n.m. | -50077.912 | -100% | 5770.668 | 11.52%
554 | 117 | BSPPBS330 | REPLACE 8 17 OUTFALLS | 10/1/2016 | 1/1/2017 |  | 54831.89 | 132.05 |  |  | 54963.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 54831.89 | n.m. | 132.05 | n.m. | 0 | n.m. | 0 | n.m. | 54963.94 | n.m.
555 | 117 | ML1S15P02 | ML1 #12 EXPANSION JOINT | 4/1/2015 | 11/1/2015 | 54795.37 |  |  |  |  | 54795.37 | 0 | 0 | 0 | 0 | 0 | 0 | 54795.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 54795.37 | n.m.
556 | 117 | ML117SP03 | REPLACE U1 PULVERIZER YOKE | 8/1/2017 | 10/1/2017 |  |  | 53785.01 |  |  | 53785.01 | 0 | 0 | 57624.978 | 54509.599 | 0 | 112134.577 | 0 | n.m. | 0 | n.m. | -3839.968 | -6.664% | -54509.599 | -100% | 0 | n.m. | -58349.567 | -52.04%
557 | 117 | ML119EP05 | ML #11B CIRC WATER PUMP REPLMT | 3/1/2019 | 7/1/2019 |  |  |  |  | 53357.1 | 53357.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 53357.1 | n.m. | 53357.1 | n.m.
558 | 117 | ML1VC1401 | ML1 V CATALYST REPLACEMENT 1 L | Charges Began Prior to Jan 2015 | 1/1/2015 | 52870.15 |  |  |  |  | 52870.15 | 27393.216 | 0 | 0 | 0 | 0 | 27393.216 | 25476.934 | 93% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25476.934 | 93%
559 | 117 | ML1VP1704 | ML1 ID FAN GUILLOTINE DAMPER | 8/1/2017 | 7/1/2018 |  |  | 52342.59 | 474.23 |  | 52816.82 | 0 | 0 | 60304.123 | 0 | 0 | 60304.123 | 0 | n.m. | 0 | n.m. | -7961.533 | -13.2% | 474.23 | n.m. | 0 | n.m. | -7487.303 | -12.42%
560 | 117 | ML215VP01 | ML2 FD & PA FAN VIBRTN MNTR | 8/1/2015 | 3/1/2016 | 51839.89 | 892.33 |  |  |  | 52732.22 | 0 | 0 | 0 | 0 | 0 | 0 | 51839.89 | n.m. | 892.33 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 52732.22 | n.m.
561 | 117 | MLP19EP06 | LP E VALVE REPLACEMENT 6 IN + | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 52345.57 | 52345.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 52345.57 | n.m. | 52345.57 | n.m.
562 | 117 | ML018EP01 | ML REPLACEMENT OF TRANSMITTERS | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 50480.49 | 1279.78 | 51760.27 | 0 | 0 | 0 | 0 | 64091.052 | 64091.052 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50480.49 | n.m. | -62811.272 | -98% | -12330.782 | -19.24%
563 | 117 | ML216NP01 | ML2 INSULATION REPLACE | 2/1/2016 | 6/1/2016 |  | 51560.92 |  |  |  | 51560.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 51560.92 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 51560.92 | n.m.
564 | 117 | MLP14EP15 | ML ROOF REPLACEMENT | Charges Began Prior to Jan 2015 | 6/1/2016 | 56022.2 | -4515.68 |  |  |  | 51506.52 | 0.03 | 0 | 0 | 0 | 0 | 0.03 | 56022.17 | 186740567% | -4515.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 51506.49 | 171688300%
565 | 117 | ML0VP1702 | REDUNDANT HDR SLURRY FEED TNK | 12/1/2017 | 7/1/2018 |  |  | 8271.48 | 42956.13 |  | 51227.61 | 0 | 0 | 90456.186 | 0 | 0 | 90456.186 | 0 | n.m. | 0 | n.m. | -82184.706 | -90.86% | 42956.13 | n.m. | 0 | n.m. | -39228.576 | -43.37%
566 | 117 | ML016MP05 | MAT H STACKER RAIL REPLACEMENT | 12/1/2016 | 12/1/2017 |  | 78710.12 | -28150.42 |  |  | 50559.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 78710.12 | n.m. | -28150.42 | n.m. | 0 | n.m. | 0 | n.m. | 50559.7 | n.m.
567 | 117 | ML218SP04 | REPLACE FD INLET VANE DRIVES | 3/1/2018 | 5/1/2018 |  |  |  | 50404.09 |  | 50404.09 | 0 | 0 | 0 | 66264.917 | 36.929 | 66301.846 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -15860.827 | -23.94% | -36.929 | -100% | -15897.756 | -23.98%
568 | 117 | MLP15MP07 | MH FEEDER CHAIN AND SPROCKETS | 2/1/2016 | 6/1/2016 |  | 49847.44 |  |  |  | 49847.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 49847.44 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49847.44 | n.m.
569 | 117 | ML018EP17 | ML R3 TRANSFORMER REPLACEMENT | 10/1/2018 | Charges Continued After Dec 2019 |  |  |  | 20609.8 | 29085.31 | 49695.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20609.8 | n.m. | 29085.31 | n.m. | 49695.11 | n.m.
570 | 117 | MLP18EP09 | ML1 2019 HIGH ENERGY PIPE MAT | 9/1/2018 | 6/1/2019 |  |  |  | 603.23 | 49010.5 | 49613.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 603.23 | n.m. | 49010.5 | n.m. | 49613.73 | n.m.
571 | 117 | ML119SP07 | ML1 E PRECIPITATOR EJ REPLACE | 1/1/2019 | 11/1/2019 |  |  |  |  | 49348.05 | 49348.05 | 0 | 0 | 0 | 0 | 176745.429 | 176745.429 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -127397.379 | -72.08% | -127397.379 | -72.08%
572 | 117 | ML117VP02 | U1 PRECIPITATOR PLC UPGRADE | 2/1/2017 | 6/1/2017 |  |  | 49243.08 |  |  | 49243.08 | 0 | 0 | 81348.311 | 0 | 0 | 81348.311 | 0 | n.m. | 0 | n.m. | -32105.231 | -39.47% | 0 | n.m. | 0 | n.m. | -32105.231 | -39.47%
573 | 117 | MLP17EP06 | MLP E VALVE REPLACEMENT 6 IN G | 1/1/2017 | 1/1/2019 |  |  | 36383.74 | 13103.46 | -288.9 | 49198.3 | 0 | 0 | 94573.086 | 108224.814 | 15.431 | 202813.331 | 0 | n.m. | 0 | n.m. | -58189.346 | -61.53% | -95121.354 | -87.89% | -304.331 | -1972% | -153615.031 | -75.74%
574 | 117 | 000024102 | KYPCo-G General Plt Cap Blkt | 10/1/2016 | 1/1/2017 |  | 47400.73 | 1726.24 |  |  | 49126.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 47400.73 | n.m. | 1726.24 | n.m. | 0 | n.m. | 0 | n.m. | 49126.97 | n.m.
575 | 117 | ML016EP08 | ML0 E HVAC REPLACE | 5/1/2016 | 5/1/2017 |  | 41657.33 | 7020.48 |  |  | 48677.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 41657.33 | n.m. | 7020.48 | n.m. | 0 | n.m. | 0 | n.m. | 48677.81 | n.m.
576 | 117 | ML016EP14 | ML SECURITY CAMERA SYSTEM | 11/1/2016 | 6/1/2017 |  | 45148.64 | 1825.54 |  |  | 46974.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 45148.64 | n.m. | 1825.54 | n.m. | 0 | n.m. | 0 | n.m. | 46974.18 | n.m.
577 | 117 | ML218SP03 | RPL AUMA TEMPER AIR DAMPER DRV | 12/1/2017 | 6/1/2018 |  |  | 31863.41 | 15037.97 |  | 46901.38 | 0 | 0 | 0 | 51204.698 | 28.536 | 51233.234 | 0 | n.m. | 0 | n.m. | 31863.41 | n.m. | -36166.728 | -70.63% | -28.536 | -100% | -4331.854 | -8.455%
578 | 117 | MLP17EP20 | MLP E CARBONE FILTER BUILDING | 9/1/2017 | 3/1/2018 |  |  | 41351.03 | 4934.18 |  | 46285.21 | 0 | 0 | 77591.429 | 0 | 0 | 77591.429 | 0 | n.m. | 0 | n.m. | -36240.399 | -46.71% | 4934.18 | n.m. | 0 | n.m. | -31306.219 | -40.35%
579 | 117 | ML1NP1911 | ML1 INSULATION & LAGGING RPL | 3/1/2019 | 11/1/2019 |  |  |  |  | 45133.97 | 45133.97 | 0 | 0 | 0 | 0 | 118871.889 | 118871.889 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -73737.919 | -62.03% | -73737.919 | -62.03%
580 | 117 | ML119SP14 | ML U1 SCR INLET EXP JOINT | 4/1/2019 | 11/1/2019 |  |  |  |  | 45023.69 | 45023.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45023.69 | n.m. | 45023.69 | n.m.
581 | 117 | ML018SP03 | ML U1&2 WATER CANNON UPGRADE | 4/1/2018 | 4/1/2019 |  |  |  | 44892.44 | 15.1 | 44907.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 44892.44 | n.m. | 15.1 | n.m. | 44907.54 | n.m.
582 | 117 | ML119SP13 | REPLACE U1 PULVERIZER YOKE | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 44589.82 | 44589.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 44589.82 | n.m. | 44589.82 | n.m.
583 | 117 | MLP15EP06 | MLP E VALVE REPLACEMENT 6 IN G | 1/1/2015 | 6/1/2016 | 58508.71 | -15334.07 |  |  |  | 43174.64 | 93519.224 | 63.5 | 0 | 0 | 0 | 93582.724 | -35010.514 | -37.44% | -15397.57 | -24248% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -50408.084 | -53.86%
584 | 117 | ML016EP06 | ML0 E VALVE REPLACE 6" GREATER | 4/1/2016 | 11/1/2017 |  | 133468.88 | -90531.61 |  |  | 42937.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 133468.88 | n.m. | -90531.61 | n.m. | 0 | n.m. | 0 | n.m. | 42937.27 | n.m.
585 | 117 | MLP14EP40 | ML E COOLING TOWER DELUGE HOUS | Charges Began Prior to Jan 2015 | 5/1/2015 | 42855.57 |  |  |  |  | 42855.57 | 153562.555 | 0 | 0 | 0 | 0 | 153562.555 | -110706.985 | -72.09% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -110706.985 | -72.09%
586 | 117 | MLP14EP04 | MLP E LIGHTING PANEL REPLACEME | Charges Began Prior to Jan 2015 | 2/1/2016 | 41851.98 | 304.27 |  |  |  | 42156.25 | 85.482 | 0 | 0 | 0 | 0 | 85.482 | 41766.498 | 48860% | 304.27 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 42070.768 | 49216%
587 | 117 | ML115EP02 | MLU1 BFP ELEMENT | 9/1/2015 | 6/1/2016 | 41996.85 | -132.05 |  |  |  | 41864.8 | 0 | 0 | 0 | 0 | 0 | 0 | 41996.85 | n.m. | -132.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 41864.8 | n.m.
588 | 117 | ML016VP07 | FGD DUCT WORK INSULATION | 9/1/2016 | 1/1/2017 |  | 50283.46 | -8484.6 |  |  | 41798.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 50283.46 | n.m. | -8484.6 | n.m. | 0 | n.m. | 0 | n.m. | 41798.86 | n.m.
589 | 117 | ML119SP04 | RPL BURNER SLEEVE DAMPER DRIVE | 12/1/2016 | 4/1/2017 |  | 83802.66 | -42550.21 |  |  | 41252.45 | 0 | 0 | 0 | 0 | 0.125 | 0.125 | 0 | n.m. | 83802.66 | n.m. | -42550.21 | n.m. | 0 | n.m. | -0.125 | -100% | 41252.325 | 33001860%
590 | 117 | ML019EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 40984.97 | 40984.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 40984.97 | n.m. | 40984.97 | n.m.
591 | 117 | ML017MP05 | ML MH COAL CHUTE REPLACEMENT | 9/1/2017 | 7/1/2018 |  |  | 30377.38 | 10208.59 |  | 40585.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 30377.38 | n.m. | 10208.59 | n.m. | 0 | n.m. | 40585.97 | n.m.
592 | 117 | ML217VP04 | U2 PRECIPITATOR PLC UPGRADE | 12/1/2017 | 2018-06-01 |  |  | 20653.17 | 19881.88 |  | 40535.05 | 0 | 0 | 76064.971 | 0 | 0 | 76064.971 | 0 | n.m. | 0 | n.m. | -55411.801 | -72.85% | 19881.88 | n.m. | 0 | n.m. | -35529.921 | -46.71%
593 | 117 | ML116SP01 | UNIT 1 #208 EJ REPLACEMENT | 8/1/2016 | 12/1/2016 |  | 40355.78 |  |  |  | 40355.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 40355.78 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 40355.78 | n.m.
594 | 117 | ML017EP01 | Replacement of Transmitters | 6/1/2017 | 5/1/2018 |  |  | 39817.18 | 85.68 |  | 39902.86 | 0 | 0 | 44877.861 | 65843.532 | 10.953 | 110732.346 | 0 | n.m. | 0 | n.m. | -5060.681 | -11.28% | -65757.852 | -99.87% | -10.953 | -100% | -70829.486 | -63.96%
595 | 117 | ML118EP10 | ML U1 STATOR DO & CONDUCTIVITY | 9/1/2018 | 11/1/2019 |  |  |  | 16825.37 | 22977.3 | 39802.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16825.37 | n.m. | 22977.3 | n.m. | 39802.67 | n.m.
596 | 117 | ML117EP01 | U1 SLAG BLOWER PLC UPGRADE | 1/1/2017 | 6/1/2017 |  |  | 39109.58 |  |  | 39109.58 | 0 | 0 | 47735.146 | 31.75 | 0 | 47766.896 | 0 | n.m. | 0 | n.m. | -8625.566 | -18.07% | -31.75 | -100% | 0 | n.m. | -8657.316 | -18.12%
597 | 117 | ML118EP12 | ML UNIT 1 INSTRUMENTATION PPB | 1/1/2018 | Charges Continued After Dec 2019 |  |  |  | 35446.03 | 3222.13 | 38668.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35446.03 | n.m. | 3222.13 | n.m. | 38668.16 | n.m.
598 | 117 | ML218SP02 | RPL AUMA HOT AIR DAMPER DRIVES | 12/1/2017 | 5/1/2018 |  |  | 31332.35 | 6768.76 |  | 38101.11 | 0 | 0 | 0 | 29980.269 | 0 | 29980.269 | 0 | n.m. | 0 | n.m. | 31332.35 | n.m. | -23211.509 | -77.42% | 0 | n.m. | 8120.841 | 27.09%
599 | 117 | ML216EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 3/1/2016 | 5/1/2018 |  | 29034.14 | 8496.85 | 507.29 |  | 38038.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 29034.14 | n.m. | 8496.85 | n.m. | 507.29 | n.m. | 0 | n.m. | 38038.28 | n.m.
600 | 117 | ML217SP11 | ML2 CROSSOVER PIPE @ CMS | 6/1/2017 | 2/1/2018 |  |  | 36699.69 | 847.55 |  | 37547.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 36699.69 | n.m. | 847.55 | n.m. | 0 | n.m. | 37547.24 | n.m.
601 | 117 | ML116SP05 | REPL SOUTH SOOTBLOWER ROOF U1 | 11/1/2016 | 5/1/2017 |  | 71579.58 | -34402.83 |  |  | 37176.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 71579.58 | n.m. | -34402.83 | n.m. | 0 | n.m. | 0 | n.m. | 37176.75 | n.m.
602 | 117 | ML219SP07 | MLU2 PRECIP EXP JOINT #1 | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 37034.1 | 37034.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 37034.1 | n.m. | 37034.1 | n.m.
603 | 117 | ML017MP04 | MH 11YARD BUCKET FOR ECRANE | 12/1/2016 | 4/1/2017 |  | 36931.12 | -18.06 |  |  | 36913.06 | 0 | 0 | 4765.483 | 0 | 0 | 4765.483 | 0 | n.m. | 36931.12 | n.m. | -4783.543 | -100.4% | 0 | n.m. | 0 | n.m. | 32147.577 | 674.6%
604 | 117 | ML219EP01 | ML U2 555 LEAK DECTECT HP HEAT | 12/1/2018 | Charges Continued After Dec 2019 |  |  |  | 7225.96 | 29272.29 | 36498.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7225.96 | n.m. | 29272.29 | n.m. | 36498.25 | n.m.
605 | 117 | ML018EP12 | ML HIGH WIND WARNING LIGHTS | 9/1/2018 | 2/1/2019 |  |  |  | 31688.11 | 3995.95 | 35684.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 31688.11 | n.m. | 3995.95 | n.m. | 35684.06 | n.m.
606 | 117 | ML019EP01 | ML REPLACEMENT OF TRANSMITTER | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 35046.52 | 35046.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35046.52 | n.m. | 35046.52 | n.m.
607 | 117 | ML216SP11 | REPL SOUTH SOOTBLOWER ROOF U2 | 1/1/2017 | 6/1/2017 |  |  | 35040.13 |  |  | 35040.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 35040.13 | n.m. | 0 | n.m. | 0 | n.m. | 35040.13 | n.m.
608 | 117 | ML218SP11 | ML U2 #21 PA DUCT EJ REPLACEMT | 1/1/2018 | 7/1/2018 |  |  |  | 35019.76 |  | 35019.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35019.76 | n.m. | 0 | n.m. | 35019.76 | n.m.
609 | 117 | MLP15SP01 | ML S PULVERIZER GEARBOX | 10/1/2015 | 4/1/2016 | 34938.65 | 47.55 |  |  |  | 34986.2 | 309375.424 | 0 | 0 | 0 | 0 | 309375.424 | -274436.774 | -88.71% | 47.55 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -274389.224 | -88.69%
610 | 117 | ML218SP16 | ML U2 #26 PA DUCT EJ REPLACEMT | 1/1/2018 | 6/1/2018 |  |  |  | 34667.68 |  | 34667.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 34667.68 | n.m. | 0 | n.m. | 34667.68 | n.m.
611 | 117 | BSPPBS301 | BS1 New Machine Shop Tool | Charges Began Prior to Jan 2015 | 3/1/2016 | 27204.77 | 7002.9 |  |  |  | 34207.67 | 59.307 | 0 | 0 | 0 | 0 | 59.307 | 27145.463 | 45771% | 7002.9 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 34148.363 | 57579%
612 | 117 | ML016EP16 | REPLACE RO MEMBRANE | 12/1/2016 | 2/1/2017 |  | 31428.97 | 2613.85 |  |  | 34042.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 31428.97 | n.m. | 2613.85 | n.m. | 0 | n.m. | 0 | n.m. | 34042.82 | n.m.
613 | 117 | ML115EP05 | MLU1 BFP ELEMENT REPLACE | 12/1/2015 | 4/1/2016 | 28176.37 | 4826.5 |  |  |  | 33002.87 | 0 | 0 | 0 | 0 | 0 | 0 | 28176.37 | n.m. | 4826.5 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33002.87 | n.m.
614 | 117 | ML219EP02 | ML INTERTEK HIGH ENERGY PIPING | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 32875.13 | 32875.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 32875.13 | n.m. | 32875.13 | n.m.
615 | 117 | 000025026 | Gen Plt Blkt KY-G Mitchell117 | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 30178.71 | 130.68 | 2133.39 | 32442.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 30178.71 | n.m. | 130.68 | n.m. | 2133.39 | n.m. | 32442.78 | n.m.
616 | 117 | ML1SP1501 | ML1 S CLINKER GRINDER RPL | 5/1/2015 | 11/1/2015 | 32324.9 |  |  |  |  | 32324.9 | 0 | 0 | 0 | 0 | 0 | 0 | 32324.9 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 32324.9 | n.m.
617 | 117 | ML017EP14 | ML REPLACE 14 NASH VACUUM PUMP | 11/1/2017 | 12/1/2017 |  |  | 31427.76 |  |  | 31427.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 31427.76 | n.m. | 0 | n.m. | 0 | n.m. | 31427.76 | n.m.
618 | 117 | ML116EP03 | MLU1 AUX TRANSFORMER BUSHING | 10/1/2016 | 1/1/2017 |  | 31193.18 | 120.04 |  |  | 31313.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 31193.18 | n.m. | 120.04 | n.m. | 0 | n.m. | 0 | n.m. | 31313.22 | n.m.
619 | 117 | ML218EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 22502.24 | 8671.47 | 31173.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22502.24 | n.m. | 8671.47 | n.m. | 31173.71 | n.m.
620 | 117 | ML218EP03 | ML REPLACE#24 NASH VACUUM PUMP | 3/1/2018 | 1/1/2019 |  |  |  | 31290.93 | -296.89 | 30994.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 31290.93 | n.m. | -296.89 | n.m. | 30994.04 | n.m.
621 | 117 | ML119EP03 | ML U1 555 LEAK DECTECT HP HEAT | 12/1/2018 | 12/1/2019 |  |  |  | 7225.96 | 23641.13 | 30867.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7225.96 | n.m. | 23641.13 | n.m. | 30867.09 | n.m.
622 | 117 | ML016MP09 | REPLACE R2 DELUGE VALVES (5) | 12/1/2016 | 1/1/2017 |  | 27576.53 | 3031.89 |  |  | 30608.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 27576.53 | n.m. | 3031.89 | n.m. | 0 | n.m. | 0 | n.m. | 30608.42 | n.m.
623 | 117 | ML218SP15 | ML U2 #25 PA DUCT EJ REPLACEMT | 1/1/2018 | 5/1/2018 |  |  |  | 30338.29 |  | 30338.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30338.29 | n.m. | 0 | n.m. | 30338.29 | n.m.
624 | 117 | MLP15EP07 | MLP E CIRCUIT BREAKER REPL | 7/1/2015 | 3/1/2017 | 16929.72 | 13020.98 | 131.48 |  |  | 30082.18 | 12467.678 | 6.67 | 0 | 0 | 0 | 12474.348 | 4462.042 | 35.79% | 13014.31 | 195117% | 131.48 | n.m. | 0 | n.m. | 0 | n.m. | 17607.832 | 141.2%
625 | 117 | ML218SP14 | ML U2 #24 PA DUCT EJ REPLACEMT | 12/1/2017 | 5/1/2018 |  |  | 8271.5 | 21591.56 |  | 29863.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 8271.5 | n.m. | 21591.56 | n.m. | 0 | n.m. | 29863.06 | n.m.
626 | 117 | ML017EP13 | ML PROTECTOWIRE 1600 PANEL RPL | 9/1/2017 | 3/1/2018 |  |  | 29053.58 | 588.62 |  | 29642.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 29053.58 | n.m. | 588.62 | n.m. | 0 | n.m. | 29642.2 | n.m.
627 | 117 | MLP17EP02 | ML E MOTOR REWINDSOVER 10HP | 8/1/2017 | 12/1/2017 |  |  | 29102.25 |  |  | 29102.25 | 0 | 0 | 25742.23 | 35993.678 | 5.214 | 61741.122 | 0 | n.m. | 0 | n.m. | 3360.02 | 13.05% | -35993.678 | -100% | -5.214 | -100% | -32638.872 | -52.86%
628 | 117 | ML217EP02 | U2 SLAG BLOWER PLC UPGRADE | 11/1/2017 | 8/1/2018 |  |  | 15370.29 | 13504.96 |  | 28875.25 | 0 | 0 | 44542.068 | 0 | 0 | 44542.068 | 0 | n.m. | 0 | n.m. | -29171.778 | -65.49% | 13504.96 | n.m. | 0 | n.m. | -15666.818 | -35.17%
629 | 117 | BSPPBS299 | BS1 New Hydraulic Press Break | Charges Began Prior to Jan 2015 | 10/1/2015 | 28485.43 |  |  |  |  | 28485.43 | 83.472 | 0 | 0 | 0 | 0 | 83.472 | 28401.958 | 34026% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28401.958 | 34026%
630 | 117 | ML117SP13 | ML U1 ECONOMIZER STRUCTURE TC | 3/1/2017 | 7/1/2017 |  |  | 28383.44 |  |  | 28383.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 28383.44 | n.m. | 0 | n.m. | 0 | n.m. | 28383.44 | n.m.
631 | 117 | ML218SP13 | ML U2 #23 PA DUCT EJ REPLACEMT | 12/1/2017 | 6/1/2018 |  |  | 8271.5 | 20071.11 |  | 28342.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 8271.5 | n.m. | 20071.11 | n.m. | 0 | n.m. | 28342.61 | n.m.
632 | 117 | ML016MP07 | HS TUNNEL VENTFAN FAILURE WARN | 10/1/2016 | 3/1/2017 |  | 26782.31 | 894.17 |  |  | 27676.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 26782.31 | n.m. | 894.17 | n.m. | 0 | n.m. | 0 | n.m. | 27676.48 | n.m.
633 | 117 | ML117EP05 | ML U1 LPB TURBINE REPLACEMENT | 1/1/2017 | 12/1/2017 |  |  | 27098.59 |  |  | 27098.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 27098.59 | n.m. | 0 | n.m. | 0 | n.m. | 27098.59 | n.m.
634 | 117 | ML018NP05 | ML FIRE HOUSE UPGRADES | 9/1/2018 | 2/1/2019 |  |  |  | 20663.25 | 6018.3 | 26681.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20663.25 | n.m. | 6018.3 | n.m. | 26681.55 | n.m.
635 | 117 | ML115EP01 | ML1 INLET SCREENS | 9/1/2015 | 6/1/2016 | 26456.39 | -72.3 |  |  |  | 26384.09 | 0 | 0 | 0 | 0 | 0 | 0 | 26456.39 | n.m. | -72.3 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 26384.09 | n.m.
636 | 117 | ML218SP12 | ML U2 #22 PA DUCT EJ REPLACEMT | 12/1/2017 | 6/1/2018 |  |  | 8271.5 | 17880.7 |  | 26152.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 8271.5 | n.m. | 17880.7 | n.m. | 0 | n.m. | 26152.2 | n.m.
637 | 117 | ML017VP02 | Cap Blkt - Prod Plant Blnkt | 1/1/2017 | 10/1/2017 |  |  | 26120.16 |  |  | 26120.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 26120.16 | n.m. | 0 | n.m. | 0 | n.m. | 26120.16 | n.m.
638 | 117 | ML018EP10 | ML CIRCULATING WATER PUMP | 10/1/2018 | 3/1/2019 |  |  |  | 32231.88 | -6117.11 | 26114.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 32231.88 | n.m. | -6117.11 | n.m. | 26114.77 | n.m.
639 | 117 | BSPPBS315 | BS1 - REP THIRD FLOOR CEILING | 9/1/2015 | 4/1/2016 | 17965.32 | 7898.46 |  |  |  | 25863.78 | 0 | 0 | 0 | 0 | 0 | 0 | 17965.32 | n.m. | 7898.46 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25863.78 | n.m.
640 | 117 | ML019EP10 | ML MH UPGRADE SCALE ELECTRONIC | 8/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 25677.18 | 25677.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25677.18 | n.m. | 25677.18 | n.m.
641 | 117 | ML117SP12 | U1 RPL 1300 SQ FT INSULAT &LAG | 3/1/2017 | 6/1/2017 |  |  | 25592.72 |  |  | 25592.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 25592.72 | n.m. | 0 | n.m. | 0 | n.m. | 25592.72 | n.m.
642 | 117 | ML2S15P07 | MLU2 #1 ID FAN EXP JOINT | 4/1/2015 | 1/1/2016 | 25628.07 | -760.02 |  |  |  | 24868.05 | 0 | 0 | 0 | 0 | 0 | 0 | 25628.07 | n.m. | -760.02 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24868.05 | n.m.
643 | 117 | ML119SP10 | ML #12 CLINKER GRINDER REPLACE | 3/1/2019 | 7/1/2019 |  |  |  |  | 24685.34 | 24685.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24685.34 | n.m. | 24685.34 | n.m.
644 | 117 | ML119SP16 | ML PENTHOUSE ROOF INSULATION | 4/1/2019 | 11/1/2019 |  |  |  |  | 24577.97 | 24577.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24577.97 | n.m. | 24577.97 | n.m.
645 | 117 | ML2S15P06 | MLU2 #2 ID FAN EXP JOINT | 4/1/2015 | 1/1/2016 | 25227.63 | -751.65 |  |  |  | 24475.98 | 0 | 0 | 0 | 0 | 0 | 0 | 25227.63 | n.m. | -751.65 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24475.98 | n.m.
646 | 117 | MLP14EP01 | MLP E MOTORS GREATER THAN 10 H | Charges Began Prior to Jan 2015 | 1/1/2016 | 24280.47 | -38.86 |  |  |  | 24241.61 | 7.572 | 0 | 0 | 0 | 0 | 7.572 | 24272.898 | 320561% | -38.86 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24234.038 | 320048%
647 | 117 | ML216SP02 | #21 CLINKER GRINDER REPLACEMNT | 4/1/2016 | 5/1/2016 |  | 24234.48 |  |  |  | 24234.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 24234.48 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24234.48 | n.m.
648 | 117 | ML018EP15 | ML CPS POTABLE WATER PUMP | 9/1/2018 | 3/1/2019 |  |  |  | 16867.23 | 7131.86 | 23999.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16867.23 | n.m. | 7131.86 | n.m. | 23999.09 | n.m.
649 | 117 | ML216SP03 | ML2 S PRECIPITATOR EXP JOINT R | 3/1/2016 | 6/1/2016 |  | 23994.14 |  |  |  | 23994.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 23994.14 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23994.14 | n.m.
650 | 117 | ML017VP06 | ML U1&2 IDFAN INST ACCESS BRID | 8/1/2017 | 2/1/2018 |  |  | 23364.94 | 620.24 |  | 23985.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 23364.94 | n.m. | 620.24 | n.m. | 0 | n.m. | 23985.18 | n.m.
651 | 117 | ML219EP16 | ML219 21B CIRC WTR PMP REBUILD | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 23833.86 | 23833.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23833.86 | n.m. | 23833.86 | n.m.
652 | 117 | ML118EP01 | RFP9300 PILOT to GE190 SEL411L | 2/1/2019 | 11/1/2019 |  |  |  |  | 23106.78 | 23106.78 | 0 | 0 | 0 | 84745.884 | 120139.412 | 204885.296 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -84745.884 | -100% | -97032.632 | -80.77% | -181778.516 | -88.72%
653 | 117 | ML216VP04 | ID FAN #21/2 INLET TUBE AH ASY | 10/1/2016 | 2/1/2017 |  | 12158.96 | 10776.85 |  |  | 22935.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 12158.96 | n.m. | 10776.85 | n.m. | 0 | n.m. | 0 | n.m. | 22935.81 | n.m.
654 | 117 | ML219VP05 | 21 ID FAN DISCHARGE EJ REPLACE | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 22933.56 | 22933.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22933.56 | n.m. | 22933.56 | n.m.
655 | 117 | ML218SP17 | ML #22 CLINKER GRINDER REPLACE | 4/1/2018 | 5/1/2018 |  |  |  | 22828.62 |  | 22828.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22828.62 | n.m. | 0 | n.m. | 22828.62 | n.m.
656 | 117 | ML117SP08 | #11 EJ REPLACEMENT (OLD STK ) | 9/1/2016 | 1/1/2017 |  | 21523.85 | 776.93 |  |  | 22300.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 21523.85 | n.m. | 776.93 | n.m. | 0 | n.m. | 0 | n.m. | 22300.78 | n.m.
657 | 117 | ML216SP08 | 2nd RH CROSSOVER PIPE REPLACMT | 9/1/2016 | 12/1/2016 |  | 22146.31 |  |  |  | 22146.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 22146.31 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22146.31 | n.m.
658 | 117 | ML018EP07 | ML HVAC CFB BLUE BUILDING REP | 11/1/2018 | 1/1/2019 |  |  |  | 14767.2 | 7041.41 | 21808.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14767.2 | n.m. | 7041.41 | n.m. | 21808.61 | n.m.
659 | 117 | ML219SP03 | REPL DFA FILTER SEPARATOR BAGS | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 21515.41 | 21515.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21515.41 | n.m. | 21515.41 | n.m.
660 | 117 | ML016EP13 | STORE ROOM STORAGE CABINETS | 10/1/2016 | 11/1/2016 |  | 21379.84 |  |  |  | 21379.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 21379.84 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21379.84 | n.m.
661 | 117 | ML218EP04 | ML U2 COOL TOWER VALVE REPL | 3/1/2018 | 6/1/2018 |  |  |  | 21189.05 |  | 21189.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21189.05 | n.m. | 0 | n.m. | 21189.05 | n.m.
662 | 117 | ML118EP09 | MLU1 COOL TOWER VALVE REPL | 3/1/2018 | 5/1/2018 |  |  |  | 21102.24 |  | 21102.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21102.24 | n.m. | 0 | n.m. | 21102.24 | n.m.
663 | 117 | MLP17EP25 | MLP E CHLORINE BUILDING | 11/1/2017 | 12/1/2017 |  |  | 21013.78 |  |  | 21013.78 | 0 | 0 | 96989.253 | 0 | 0 | 96989.253 | 0 | n.m. | 0 | n.m. | -75975.473 | -78.33% | 0 | n.m. | 0 | n.m. | -75975.473 | -78.33%
664 | 117 | ML117EP07 | ML U1 DOGBONE EJ LPB TURBINE | 1/1/2017 | 4/1/2017 |  |  | 20626.1 |  |  | 20626.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 20626.1 | n.m. | 0 | n.m. | 0 | n.m. | 20626.1 | n.m.
665 | 117 | MLP14ECKP | MLP BLADES FOR SPARE LP ROTORS | Charges Began Prior to Jan 2015 | 8/1/2015 | 20589.38 |  |  |  |  | 20589.38 | 0 | 0 | 0 | 0 | 0 | 0 | 20589.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20589.38 | n.m.
666 | 117 | ML219EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 19825.42 | 19825.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19825.42 | n.m. | 19825.42 | n.m.
667 | 117 | ML019NP06 | ML U0 Gate 4 Automatic Gate | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 19496.65 | 19496.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19496.65 | n.m. | 19496.65 | n.m.
668 | 117 | ML215SP01 | ML UNIT2 CROSSOVER PIPE REPLAC | 12/1/2015 | 4/1/2016 | 229.66 | 19045.57 |  |  |  | 19275.23 | 0 | 0 | 0 | 0 | 0 | 0 | 229.66 | n.m. | 19045.57 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19275.23 | n.m.
669 | 117 | ML016EP01 | ML0E MOTORS GRTR THAN 10 HP | 1/1/2016 | 2/1/2017 |  | 18423.49 | 539.24 |  |  | 18962.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 18423.49 | n.m. | 539.24 | n.m. | 0 | n.m. | 0 | n.m. | 18962.73 | n.m.
670 | 117 | ML116SP04 | MLU1 ASH PIT NOISE ENCLOSURE | 11/1/2016 | 3/1/2017 |  | 15850.67 | 3016.4 |  |  | 18867.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 15850.67 | n.m. | 3016.4 | n.m. | 0 | n.m. | 0 | n.m. | 18867.07 | n.m.
671 | 117 | MLP16EP06 | MLP E VALVE REPLACEMENT 6 IN G | 12/1/2016 | 4/1/2017 |  | 4473.68 | 14351.71 |  |  | 18825.39 | 0 | 106774.17 | 82.921 | 0 | 0 | 106857.091 | 0 | n.m. | -102300.49 | -95.81% | 14268.789 | 17208% | 0 | n.m. | 0 | n.m. | -88031.701 | -82.38%
672 | 117 | ML016EP09 | RESTORE SERVICE to KAMMER LC | 6/1/2016 | 11/1/2016 |  | 18639.29 |  |  |  | 18639.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 18639.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 18639.29 | n.m.
673 | 117 | ML219VP11 | ML2 STACK FLUE EJ @ ELE 250 | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 18519.63 | 18519.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 18519.63 | n.m. | 18519.63 | n.m.
674 | 117 | ML017SP03 | RPL #12 HOT AIR DAMPNER w/BECK | 9/1/2017 | 11/1/2017 |  |  | 18461.53 |  |  | 18461.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 18461.53 | n.m. | 0 | n.m. | 0 | n.m. | 18461.53 | n.m.
675 | 117 | ML216SP05 | 2nd RH CROSSOVER PIPE REPLACE | 3/1/2016 | 5/1/2016 |  | 18255.48 |  |  |  | 18255.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 18255.48 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 18255.48 | n.m.
676 | 117 | ML119SP15 | ML #51 SAFETY VALVE REPLACEMNT | 4/1/2019 | 11/1/2019 |  |  |  |  | 17556.68 | 17556.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17556.68 | n.m. | 17556.68 | n.m.
677 | 117 | ML018EP13 | ML1 CONVEYOR 7 FIREDELUGE VALV | 9/1/2018 | 3/1/2019 |  |  |  | 17416.63 | -22.45 | 17394.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17416.63 | n.m. | -22.45 | n.m. | 17394.18 | n.m.
678 | 117 | MLP17EP26 | MLP E WATER TANK CONTROLS | 9/1/2016 | 6/1/2017 |  | 15482.08 | 1870.79 |  |  | 17352.87 | 0 | 0 | 154994.662 | 0 | 0 | 154994.662 | 0 | n.m. | 15482.08 | n.m. | -153123.872 | -98.79% | 0 | n.m. | 0 | n.m. | -137641.792 | -88.8%
679 | 117 | ML119SP17 | ML U1 Purge Air Heater Pnchlst | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 17149.22 | 17149.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17149.22 | n.m. | 17149.22 | n.m.
680 | 117 | ML216SP07 | REPL ASH PIT LINES to WW SUMP | 5/1/2016 | 8/1/2016 |  | 16586.09 |  |  |  | 16586.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 16586.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16586.09 | n.m.
681 | 117 | ML2SP1505 | ML2 S COAL FEEDER CONTROLS | Charges Began Prior to Jan 2015 | 1/1/2016 | 17868.47 | -1511.52 |  |  |  | 16356.95 | 0.016 | 0 | 0 | 0 | 0 | 0.016 | 17868.454 | 111677838% | -1511.52 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16356.934 | 102230838%
682 | 117 | ML218SP09 | REPL DFA FILTER SEPARATOR BAGS | 7/1/2018 | 4/1/2019 |  |  |  | 8070.99 | 7767.21 | 15838.2 | 0 | 0 | 0 | 20586.523 | 21256.207 | 41842.73 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -12515.533 | -60.79% | -13488.997 | -63.46% | -26004.53 | -62.15%
683 | 117 | MLP15MP05 | MLP MH PPB PROJECTS | 3/1/2015 | 11/1/2015 | 15749.15 |  |  |  |  | 15749.15 | 33738.094 | 6.01 | 0 | 0 | 0 | 33744.104 | -17988.944 | -53.32% | -6.01 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -17994.954 | -53.33%
684 | 117 | BSPPB0011 | Generator & Support PPB<100k | Charges Began Prior to Jan 2015 | 9/1/2018 | 1680.44 |  |  | 12901.66 |  | 14582.1 | 17.228 | 290491.168 | 0 | 0 | 0 | 290508.396 | 1663.212 | 9654% | -290491.168 | -100% | 0 | n.m. | 12901.66 | n.m. | 0 | n.m. | -275926.296 | -94.98%
685 | 117 | ML018MP04 | ML MH TOWBOAT UPGRADE REPLACE | 7/1/2018 | 4/1/2019 |  |  |  | 25506.44 | -10956.22 | 14550.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25506.44 | n.m. | -10956.22 | n.m. | 14550.22 | n.m.
686 | 117 | ML016VP10 | GAS PUMP & FUEL MANAGEMENT | 12/1/2016 | 1/1/2018 |  | 10749.42 | 3566.79 | 72.63 |  | 14388.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 10749.42 | n.m. | 3566.79 | n.m. | 72.63 | n.m. | 0 | n.m. | 14388.84 | n.m.
687 | 117 | ML018MP09 | ML MH DFA SCALE UPGRADES | 12/1/2018 | 7/1/2019 |  |  |  | 13207.57 | 957.87 | 14165.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13207.57 | n.m. | 957.87 | n.m. | 14165.44 | n.m.
688 | 117 | ML119EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 14112.19 | 14112.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14112.19 | n.m. | 14112.19 | n.m.
689 | 117 | ML017MP07 | ML COAL SAMPLE CRUSHER RPL | 6/1/2017 | 10/1/2017 |  |  | 13750.07 |  |  | 13750.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 13750.07 | n.m. | 0 | n.m. | 0 | n.m. | 13750.07 | n.m.
690 | 117 | MLP16EP03 | MLP E PUMP REPLACEMENT DR 10 H | 2/1/2017 | 4/1/2017 |  |  | 13694.29 |  |  | 13694.29 | 0 | 182437.25 | 154.055 | 0 | 0 | 182591.305 | 0 | n.m. | -182437.25 | -100% | 13540.235 | 8789% | 0 | n.m. | 0 | n.m. | -168897.015 | -92.5%
691 | 117 | BSPPBS304 | BS0 Rep Plant Security Cameras | Charges Began Prior to Jan 2015 | 6/1/2015 | 13554.51 |  |  |  |  | 13554.51 | 0 | 0 | 0 | 0 | 0 | 0 | 13554.51 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13554.51 | n.m.
692 | 117 | ML018EP02 | ML UNIT 1 & UNIT 2 PI SERVERS | 7/1/2018 | 10/1/2019 |  |  |  | 11150.9 | 2153.58 | 13304.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11150.9 | n.m. | 2153.58 | n.m. | 13304.48 | n.m.
693 | 117 | ML216SP10 | MLU2 ASH PIT NOISE ENCLOSURE | 11/1/2016 | 4/1/2017 |  | 9442.6 | 3257.99 |  |  | 12700.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 9442.6 | n.m. | 3257.99 | n.m. | 0 | n.m. | 0 | n.m. | 12700.59 | n.m.
694 | 117 | MLP14EP03 | MLP E PUMP REPLACEMENT DR 10 H | Charges Began Prior to Jan 2015 | 6/1/2015 | 12606.88 |  |  |  |  | 12606.88 | 35.484 | 0 | 0 | 0 | 0 | 35.484 | 12571.396 | 35428% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12571.396 | 35428%
695 | 117 | BSPPB0007 | Condenser & Aux. PPB<100k | Charges Began Prior to Jan 2015 | 3/1/2019 | -52.65 |  |  |  | 11911.9 | 11859.25 | 3.998 | 0 | 0 | 0 | 0 | 3.998 | -56.648 | -1417% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11911.9 | n.m. | 11855.252 | 296530%
696 | 117 | ML119SP09 | REPL DFA FILTER SEPARTOR BAGS | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 11490.78 | 11490.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11490.78 | n.m. | 11490.78 | n.m.
697 | 117 | ML2SP1502 | ML2 S CLINKER GRINDER RPL | Charges Began Prior to Jan 2015 | 9/1/2015 | 11030.94 |  |  |  |  | 11030.94 | 0 | 0 | 0 | 0 | 0 | 0 | 11030.94 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11030.94 | n.m.
698 | 117 | ML217VP08 | ML RPL#22 ID FAN HYDRAULIC CYL | 12/1/2017 | 7/1/2018 |  |  | 10523.39 | 252.65 |  | 10776.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 10523.39 | n.m. | 252.65 | n.m. | 0 | n.m. | 10776.04 | n.m.
699 | 117 | BSPPB0001 | Ash Handling PPB <100k | Charges Began Prior to Jan 2015 | 4/1/2016 | 10699.23 | 16.14 |  |  |  | 10715.37 | 6.401 | 0 | 0 | 0 | 0 | 6.401 | 10692.829 | 167049% | 16.14 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10708.969 | 167301%
700 | 117 | ML216VP02 | RPL OXAIR BLOWER C DISCH VALVE | 9/1/2016 | 12/1/2016 |  | 10191.09 |  |  |  | 10191.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 10191.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10191.09 | n.m.
701 | 117 | BSPPBS306 | BS1 New Passenger Elevator Sys | Charges Began Prior to Jan 2015 | 6/1/2015 | 10082.3 |  |  |  |  | 10082.3 | 0 | 0 | 0 | 0 | 0 | 0 | 10082.3 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10082.3 | n.m.
702 | 117 | ML218SP27 | ML U2 FOAM SYSTEM DELUGE VALVE | 4/1/2018 | 6/1/2018 |  |  |  | 9696.72 |  | 9696.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9696.72 | n.m. | 0 | n.m. | 9696.72 | n.m.
703 | 117 | ML019EP11 | SULFURIC ACID LEAK DETECTION | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 8869.5 | 8869.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8869.5 | n.m. | 8869.5 | n.m.
704 | 117 | ITCB11701 | Kentucky Power - Gen-Miitchell | 11/1/2017 | 3/1/2019 |  |  | 1718.53 | 6326.74 | 660.68 | 8705.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1718.53 | n.m. | 6326.74 | n.m. | 660.68 | n.m. | 8705.95 | n.m.
705 | 117 | ML219EP23 | MLU2 EXCITER BRUSH RIGGING | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 8598.74 | 8598.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8598.74 | n.m. | 8598.74 | n.m.
706 | 117 | ML119EP22 | REPLACE DEMINERALIZER HMI | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 8279.22 | 8279.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8279.22 | n.m. | 8279.22 | n.m.
707 | 117 | ML018MP08 | ML BARGE UNLOADER NETWORK UPGR | 9/1/2018 | 1/1/2019 |  |  |  | 8142.51 | -28.51 | 8114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8142.51 | n.m. | -28.51 | n.m. | 8114 | n.m.
708 | 117 | ML116SP03 | RPL TRANS STATION FILTER BAG | 10/1/2016 | 11/1/2016 |  | 7948.29 |  |  |  | 7948.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 7948.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7948.29 | n.m.
709 | 117 | ML018EP18 | ML OUTFALL HEATED SAMPLERS | 11/1/2018 | 1/1/2019 |  |  |  | 7791.16 | -11.01 | 7780.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7791.16 | n.m. | -11.01 | n.m. | 7780.15 | n.m.
710 | 117 | ML017EP12 | ML R6 PROTECTOWIRE PANEL UPGRA | 8/1/2017 | 12/1/2017 |  |  | 7599.18 |  |  | 7599.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7599.18 | n.m. | 0 | n.m. | 0 | n.m. | 7599.18 | n.m.
711 | 117 | ML218SP26 | ML U2 TURBINE BASEMENT FIRE SY | 12/1/2018 | 3/1/2019 |  |  |  | 19523.31 | -11932.98 | 7590.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19523.31 | n.m. | -11932.98 | n.m. | 7590.33 | n.m.
712 | 117 | MLP15EP05 | MLP E POWER CABLE REPLACEMENT | 2/1/2015 | 4/1/2016 | 7414.58 | 143.69 |  |  |  | 7558.27 | 24935.36 | 13.37 | 0 | 0 | 0 | 24948.73 | -17520.78 | -70.26% | 130.32 | 974.7% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -17390.46 | -69.7%
713 | 117 | ML118SP20 | ML U1 FOAM SYSTEM DELUGE VALVE | 4/1/2018 | 7/1/2018 |  |  |  | 7335.84 |  | 7335.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7335.84 | n.m. | 0 | n.m. | 7335.84 | n.m.
714 | 117 | ML118SP07 | REPL DFA FILTER SEPARTOR BAGS | 11/1/2018 | 4/1/2019 |  |  |  | 7328.23 | -37.51 | 7290.72 | 0 | 0 | 0 | 20586.523 | 21256.207 | 41842.73 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -13258.293 | -64.4% | -21293.717 | -100.2% | -34552.01 | -82.58%
715 | 117 | ML216SP01 | #21 RECEIVING HOPPER REPLACEMT | 5/1/2016 | 11/1/2016 |  | 7227.63 |  |  |  | 7227.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 7227.63 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7227.63 | n.m.
716 | 117 | ML216SP09 | RPL TRANS STATION FILTER BAG | 9/1/2016 | 11/1/2016 |  | 6904.68 |  |  |  | 6904.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6904.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6904.68 | n.m.
717 | 117 | ML016EP15 | ECONOMIZER TRANSMITTERS | 12/1/2016 | 1/1/2017 |  | 6828.53 | 36.56 |  |  | 6865.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6828.53 | n.m. | 36.56 | n.m. | 0 | n.m. | 0 | n.m. | 6865.09 | n.m.
718 | 117 | ML1S14P01 | ML1 S PRECIPITATOR EJ RPL | Charges Began Prior to Jan 2015 | 5/1/2015 | 6836.04 |  |  |  |  | 6836.04 | 64.925 | 0 | 0 | 0 | 0 | 64.925 | 6771.115 | 10429% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6771.115 | 10429%
719 | 117 | ML116EP10 | MLU1 #4 LP HEATER LEVEL PROBE | 5/1/2016 | 2017-06-01 |  | 6473.36 | -45.24 | 0 |  | 6428.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6473.36 | n.m. | -45.24 | n.m. | 0 | n.m. | 0 | n.m. | 6428.12 | n.m.
720 | 117 | MLP19EP05 | ML E POWER CABLE REPLACEMENT | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6324.76 | 6324.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6324.76 | n.m. | 6324.76 | n.m.
721 | 117 | ML218EP06 | ML REPLACE #22 ECH PUMP | 3/1/2018 | 6/1/2018 |  |  |  | 6302.74 |  | 6302.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6302.74 | n.m. | 0 | n.m. | 6302.74 | n.m.
722 | 117 | ML1VP1603 | ML1 V FGD CAPITAL PROJECTS | 2015-10-01 | 4/1/2016 | 6334.4 | -35.92 |  |  |  | 6298.48 | 70534.62 | 15.59 | 0 | 0 | 0 | 70550.21 | -64200.22 | -91.02% | -51.51 | -330.4% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -64251.73 | -91.07%
723 | 117 | ML119SP12 | RPL PULVERIZER CLASSIFIER ASBY | 1/1/2019 | 11/1/2019 |  |  |  |  | 6218.19 | 6218.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6218.19 | n.m. | 6218.19 | n.m.
724 | 117 | MLP14EP66 | ML E VALVE REPLACEMENT | Charges Began Prior to Jan 2015 | 12/1/2015 | 6028.5 |  |  |  |  | 6028.5 | 23.552 | 0 | 0 | 0 | 0 | 23.552 | 6004.948 | 25497% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6004.948 | 25497%
725 | 117 | ML116EP02 | UNIT 1 CAUSTIC VAULT HEATER | 10/1/2016 | 12/1/2016 |  | 5971.88 |  |  |  | 5971.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 5971.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5971.88 | n.m.
726 | 117 | ML017VP03 | RPL CHEMICAL INJ SKID CPS CLAR | 8/1/2017 | 7/1/2019 |  |  | 5116.63 | 478.82 | 98.92 | 5694.37 | 0 | 0 | 119136.724 | 0 | 0 | 119136.724 | 0 | n.m. | 0 | n.m. | -114020.094 | -95.71% | 478.82 | n.m. | 98.92 | n.m. | -113442.354 | -95.22%
727 | 117 | ML018MP11 | ML MH BARGE UNLDR AUTO GREASE | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 5411.8 | 187.8 | 5599.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5411.8 | n.m. | 187.8 | n.m. | 5599.6 | n.m.
728 | 117 | ML118SP18 | RPL 6" HSO-AUX STEAM-CHEM STA | 3/1/2018 | 7/1/2018 |  |  |  | 5435.17 |  | 5435.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5435.17 | n.m. | 0 | n.m. | 5435.17 | n.m.
729 | 117 | ML219EP19 | MLU2 22B CIRC WTR PMP EJ | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5352.45 | 5352.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5352.45 | n.m. | 5352.45 | n.m.
730 | 117 | ML019EP04 | ML E HVAC UNIT REPLACEMENTS | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5092.33 | 5092.33 | 0 | 0 | 0 | 0 | 24685.287 | 24685.287 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -19592.957 | -79.37% | -19592.957 | -79.37%
731 | 117 | ML118SP21 | ML #12F BURNER LINE SLIP JOINT | 4/1/2018 | 10/1/2018 |  |  |  | 5090.81 |  | 5090.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5090.81 | n.m. | 0 | n.m. | 5090.81 | n.m.
732 | 117 | BSPPBENEW | BSP PPB Envr. New | Charges Began Prior to Jan 2015 | 12/1/2017 |  |  | 5012.05 |  |  | 5012.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 5012.05 | n.m. | 0 | n.m. | 0 | n.m. | 5012.05 | n.m.
733 | 117 | ML020SP01 | ML MITCHELL DSI PROJECT | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4797.62 | 4797.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4797.62 | n.m. | 4797.62 | n.m.
734 | 117 | ML216EP04 | UNIT 2 CAUSTIC VAULT HEATER | 10/1/2016 | 12/1/2016 |  | 4757.38 |  |  |  | 4757.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 4757.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4757.38 | n.m.
735 | 117 | ML116VP01 | #11 ID FAN INLET TUBE AH ASBLY | 12/1/2016 | 1/1/2017 |  | 4246.86 | -21.06 |  |  | 4225.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 4246.86 | n.m. | -21.06 | n.m. | 0 | n.m. | 0 | n.m. | 4225.8 | n.m.
736 | 117 | ML019EP09 | ML AMMONIA TANK N2 BLANKETING | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4076.62 | 4076.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4076.62 | n.m. | 4076.62 | n.m.
737 | 117 | ML218SP18 | ML #22 RECEIVING HOPPER REPLAC | 4/1/2018 | 5/1/2018 |  |  |  | 4075.1 |  | 4075.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4075.1 | n.m. | 0 | n.m. | 4075.1 | n.m.
738 | 117 | ML118VP06 | ML RPL #12 ID FAN OUTLET EJ | 4/1/2018 | 6/1/2018 |  |  |  | 4049.74 |  | 4049.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4049.74 | n.m. | 0 | n.m. | 4049.74 | n.m.
739 | 117 | ML018VP06 | ML SILICON CARBIDE AR PUMP | 12/1/2018 | Charges Continued After Dec 2019 |  |  |  | 3372.28 | 380.05 | 3752.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3372.28 | n.m. | 380.05 | n.m. | 3752.33 | n.m.
740 | 117 | ML219EP15 | ML219 22 CIRC MTR DIODE RING | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3664.13 | 3664.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3664.13 | n.m. | 3664.13 | n.m.
741 | 117 | ML219EP22 | REPLACE DEMINERALIZER HMI | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3566.42 | 3566.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3566.42 | n.m. | 3566.42 | n.m.
742 | 117 | ML018MP10 | ML MT HANDLING MOBILE HEATERS | 11/1/2018 | 4/1/2019 |  |  |  | 3102.67 | 210.07 | 3312.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3102.67 | n.m. | 210.07 | n.m. | 3312.74 | n.m.
743 | 117 | ML216EP09 | ML-U2 DI ACID CAB TRANSMITTER | 3/1/2016 | 5/1/2016 |  | 3269.82 |  |  |  | 3269.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 3269.82 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3269.82 | n.m.
744 | 117 | ML018NP03 | ML HAUL ROAD RELOCATION PRELIM | 11/1/2018 | Charges Continued After Dec 2019 |  |  |  | 234.49 | 2939.48 | 3173.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 234.49 | n.m. | 2939.48 | n.m. | 3173.97 | n.m.
745 | 117 | MLP16EP01 | MLP E MOTORS GREATER THAN 10 H | 7/1/2016 | 9/1/2016 |  | 2956.4 |  |  |  | 2956.4 | 0 | 93627.071 | 57.562 | 0 | 0 | 93684.633 | 0 | n.m. | -90670.671 | -96.84% | -57.562 | -100% | 0 | n.m. | 0 | n.m. | -90728.233 | -96.84%
746 | 117 | BSPPBS333 | VOLT VAR PROJECT | 8/1/2017 | 7/1/2018 |  |  | 2501.12 | 71.07 |  | 2572.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2501.12 | n.m. | 71.07 | n.m. | 0 | n.m. | 2572.19 | n.m.
747 | 117 | BSPPB0004 | Coal Pulv/ Mills PPB<100k | Charges Began Prior to Jan 2015 | 4/1/2015 | 2558.36 |  |  |  |  | 2558.36 | 309562.746 | 0 | 0 | 0 | 0 | 309562.746 | -307004.386 | -99.17% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -307004.386 | -99.17%
748 | 117 | ML216SM01 | #26 SILO GATE REPLACEMENT | 4/1/2016 | 5/1/2016 |  | 2441.11 |  |  |  | 2441.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 2441.11 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2441.11 | n.m.
749 | 117 | MLP17SP02 | ML SAFETY VALVES ( 4 ) | 6/1/2017 | 10/1/2017 |  |  | 2382.4 |  |  | 2382.4 | 0 | 0 | 64355.567 | 66.1 | 0 | 64421.667 | 0 | n.m. | 0 | n.m. | -61973.167 | -96.3% | -66.1 | -100% | 0 | n.m. | -62039.267 | -96.3%
750 | 117 | ML117EP08 | RPL#11 CLARITE FILTER HSO VALV | 2/1/2017 | 4/1/2017 |  |  | 2353.98 |  |  | 2353.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2353.98 | n.m. | 0 | n.m. | 0 | n.m. | 2353.98 | n.m.
751 | 117 | MLP14EP45 | ML E ELLIOTT AIR COMPRESSOR RP | Charges Began Prior to Jan 2015 | 2/1/2015 | 2287.58 |  |  |  |  | 2287.58 | 85.633 | 0 | 0 | 0 | 0 | 85.633 | 2201.947 | 2571% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2201.947 | 2571%
752 | 117 | ML118SP11 | DFA EXHAUST BLOWER REPLACEMENT | 10/1/2018 | 4/1/2019 |  |  |  | 2262.25 | -29.27 | 2232.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2262.25 | n.m. | -29.27 | n.m. | 2232.98 | n.m.
753 | 117 | ML017EP09 | ML U1/U2 VOLT / VAR COMPLIANCE | 7/1/2017 | 7/1/2018 |  |  | 1950.14 | 168.32 |  | 2118.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1950.14 | n.m. | 168.32 | n.m. | 0 | n.m. | 2118.46 | n.m.
754 | 117 | ML216EP02 | #22 ASH WATERPUMP 10" CHK VALV | 4/1/2016 | 6/1/2016 |  | 2083.94 |  |  |  | 2083.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 2083.94 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2083.94 | n.m.
755 | 117 | ML016VP05 | FGD REAGENT SLURRY FEED PUMP | 10/1/2016 | 12/1/2016 |  | 2060.66 |  |  |  | 2060.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 2060.66 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2060.66 | n.m.
756 | 117 | ML117SP14 | ML UNIT 1 ECONOMIZER EJ | 10/1/2017 | 5/1/2018 |  |  | 1585.16 | 38.08 |  | 1623.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1585.16 | n.m. | 38.08 | n.m. | 0 | n.m. | 1623.24 | n.m.
757 | 117 | ML119SP11 | ML #12 RECEIVING HOPPER REPLAC | 4/1/2019 | 10/1/2019 |  |  |  |  | 1510.43 | 1510.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1510.43 | n.m. | 1510.43 | n.m.
758 | 117 | ML216EP01 | #22 ASH WATER PUMP 10" B VALVE | 4/1/2016 | 6/1/2016 |  | 1444.27 |  |  |  | 1444.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1444.27 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1444.27 | n.m.
759 | 117 | ML116VP02 | ID FAN #11/#12 DIS INSP VALVES | 9/1/2016 | 12/1/2016 |  | 1354.1 |  |  |  | 1354.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1354.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1354.1 | n.m.
760 | 117 | ML216VP03 | ID FAN #21/#22 DIS INSP VALVES | 9/1/2016 | 12/1/2016 |  | 1347.67 |  |  |  | 1347.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1347.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1347.67 | n.m.
761 | 117 | ML216EP05 | U2 STATOR OUTLET CONDUCT ANLYZ | 12/1/2016 | 5/1/2017 |  | 739.3 | 570.64 |  |  | 1309.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 739.3 | n.m. | 570.64 | n.m. | 0 | n.m. | 0 | n.m. | 1309.94 | n.m.
762 | 117 | BSPPBS298 | BS1 Rep 12 Pulv Grinding Zone | Charges Began Prior to Jan 2015 | 3/1/2015 | 1184.48 |  |  |  |  | 1184.48 | 78.307 | 0 | 0 | 0 | 0 | 78.307 | 1106.173 | 1413% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1106.173 | 1413%
763 | 117 | ML016EP05 | ML0 E POWER CABLE REPLACE | 10/1/2016 | 1/1/2017 |  | 890.2 | -1.13 |  |  | 889.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 890.2 | n.m. | -1.13 | n.m. | 0 | n.m. | 0 | n.m. | 889.07 | n.m.
764 | 117 | ML017EP10 | ML - WEATHER MONITORING SYSTEM | 6/1/2017 | 10/1/2017 |  |  | 787.9 |  |  | 787.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 787.9 | n.m. | 0 | n.m. | 0 | n.m. | 787.9 | n.m.
765 | 117 | MLP14NP01 | MLP NP PLANT LABOR FOR CAPITAL | Charges Began Prior to Jan 2015 | 6/1/2015 | 665.06 |  |  |  |  | 665.06 | 25.138 | 0 | 0 | 0 | 0 | 25.138 | 639.922 | 2546% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 639.922 | 2546%
766 | 117 | 000019892 | ML Coal Pile Runoff | Charges Began Prior to Jan 2015 | 4/1/2015 | 473.46 |  |  |  |  | 473.46 | 0 | 0 | 0 | 0 | 0 | 0 | 473.46 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 473.46 | n.m.
767 | 117 | ML1S14P05 | ML1S STEAM PROCESS | Charges Began Prior to Jan 2015 | 3/1/2015 | 217.59 |  |  |  |  | 217.59 | 26.672 | 0 | 0 | 0 | 0 | 26.672 | 190.918 | 715.8% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 190.918 | 715.8%
768 | 117 | ML1SP1430 | ML1 S CLINKER GRINDER HOPPER | Charges Began Prior to Jan 2015 | 1/1/2015 | 163.19 |  |  |  |  | 163.19 | 16.496 | 0 | 0 | 0 | 0 | 16.496 | 146.694 | 889.3% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 146.694 | 889.3%
769 | 117 | WSN103015 | ML0-Conners Run Expansion | Charges Began Prior to Jan 2015 | 3/1/2015 | 130.53 |  |  |  |  | 130.53 | 0 | 0 | 0 | 0 | 0 | 0 | 130.53 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 130.53 | n.m.
770 | 117 | ML1VP1403 | ML1 V FGD CAPITAL PROJECTS | Charges Began Prior to Jan 2015 | 1/1/2015 | 54.39 |  |  |  |  | 54.39 | 70.791 | 0 | 0 | 0 | 0 | 70.791 | -16.401 | -23.17% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -16.401 | -23.17%
771 | 117 | MLPAUXTRN | 138 KV SUPPORT TRANSMISSION PR | Charges Began Prior to Jan 2015 | 1/1/2015 | 0.93 |  |  |  |  | 0.93 | 0.085 | 0 | 0 | 0 | 0 | 0.085 | 0.845 | 994.1% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0.845 | 994.1%
772 | 117 | BSPPBS340 | REPLACE 15 BREAKERS "B" BUS | 11/1/2018 | 11/1/2019 |  |  |  | 337.41 | -337.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 337.41 | n.m. | -337.41 | n.m. | 0 | n.m.
773 | 117 | 000009633 | BIG SANDY U2 DFGD W FF | Charges Began Prior to Jan 2015 | 2015-04-01 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m.
774 | 117 | ML118VP08 | ML RPL#12 ID FAN HYDRAULIC CYL | 4/1/2018 | 11/1/2018 |  |  |  | -1.7764e-15 |  | -1.7764e-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1.7764e-15 | n.m. | 0 | n.m. | -1.7764e-15 | n.m.
775 | 117 | BSPPBS339 | REPLACE 15 BREAKERS "A" BUS | 11/1/2018 | 11/1/2019 |  |  |  | 253.06 | -253.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 253.06 | n.m. | -253.06 | n.m. | 0 | n.m.
776 | 117 | 000008348 | Big Sandy FGD Landfill | Charges Began Prior to Jan 2015 | 2015-07-01 | -2.3283e-10 |  |  |  |  | -2.3283e-10 | 0 | 0 | 0 | 0 | 0 | 0 | -2.3283e-10 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -2.3283e-10 | n.m.
777 | 117 | BSPPBOUT2 | U 2 PPB Outage <100k | Charges Began Prior to Jan 2015 | 3/1/2015 | -635.44 |  |  |  |  | -635.44 | 20.342 | 0 | 0 | 0 | 0 | 20.342 | -655.782 | -3224% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -655.782 | -3224%
778 | 117 | MLP14MP02 | MLP MH CONVEYOR BELT REPLACEME | Charges Began Prior to Jan 2015 | 1/1/2015 | -738.03 |  |  |  |  | -738.03 | 30.738 | 0 | 0 | 0 | 0 | 30.738 | -768.768 | -2501% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -768.768 | -2501%
779 | 117 | GENREB117 | Generation Rebate Program | 1/1/2018 | 1/1/2018 |  |  |  | -1292.95 |  | -1292.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1292.95 | n.m. | 0 | n.m. | -1292.95 | n.m.
780 | 117 | KMLFALFHR | ML New Landfill Haul Road | Charges Began Prior to Jan 2015 | 2/1/2015 | -1494.03 |  |  |  |  | -1494.03 | 0 | 0 | 0 | 0 | 0 | 0 | -1494.03 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1494.03 | n.m.
781 | 117 | ML016SP05 | ML PULVERIZER YOKE PURCHASE | 12/1/2016 | 3/1/2017 |  | 34656.01 | -36888.6 |  |  | -2232.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 34656.01 | n.m. | -36888.6 | n.m. | 0 | n.m. | 0 | n.m. | -2232.59 | n.m.
782 | 117 | MLP14SP02 | MLP S PULVERIZER REBUILD CAP | Charges Began Prior to Jan 2015 | 1/1/2015 | -3841.37 |  |  |  |  | -3841.37 | 129.812 | 0 | 0 | 0 | 0 | 129.812 | -3971.182 | -3059% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -3971.182 | -3059%
783 | 117 | ML1E14P02 | ML1 E CONTROLS AND RECORDERS | Charges Began Prior to Jan 2015 | 10/1/2015 | -4092.21 |  |  |  |  | -4092.21 | 101.188 | 0 | 0 | 0 | 0 | 101.188 | -4193.398 | -4144% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -4193.398 | -4144%
784 | 117 | BSPPBS294 | BS1 Reb 11 Pulv Grinding Zone | Charges Began Prior to Jan 2015 | 2015-04-01 | -4114.26 |  |  |  |  | -4114.26 | 90.738 | 0 | 0 | 0 | 0 | 90.738 | -4204.998 | -4634% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -4204.998 | -4634%
785 | 117 | BSPPBS297 | BS1 Rep Precipitator Wires | Charges Began Prior to Jan 2015 | 2/1/2015 | -4880.23 |  |  |  |  | -4880.23 | 196.924 | 0 | 0 | 0 | 0 | 196.924 | -5077.154 | -2578% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -5077.154 | -2578%
786 | 117 | BSPPBS295 | BS1 Rep Pulv #11 Drive Train | Charges Began Prior to Jan 2015 | 2/1/2015 | -5334.03 |  |  |  |  | -5334.03 | 114.184 | 0 | 0 | 0 | 0 | 114.184 | -5448.214 | -4771% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -5448.214 | -4771%
787 | 117 | BSPPB0010 | Fuel Delivery PPB<100k | Charges Began Prior to Jan 2015 | 5/1/2015 | -7963.12 |  |  |  |  | -7963.12 | 260.182 | 0 | 0 | 0 | 0 | 260.182 | -8223.302 | -3161% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -8223.302 | -3161%
788 | 117 | ML1VP1450 | ML V AR PP REPLACEMENT | Charges Began Prior to Jan 2015 | 10/1/2015 | -14065.84 |  |  |  |  | -14065.84 | 65.1 | 0 | 0 | 0 | 0 | 65.1 | -14130.94 | -21707% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -14130.94 | -21707%
789 | 117 | BSPPBS296 | BS1 Rep Pulv #13 Drive Train | Charges Began Prior to Jan 2015 | 3/1/2015 | -30473.21 |  |  |  |  | -30473.21 | 137.937 | 0 | 0 | 0 | 0 | 137.937 | -30611.147 | -22192% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -30611.147 | -22192%
790 | 117 | MLP14MP01 | MLP MH COAL CHUTE REPLACEMENT | Charges Began Prior to Jan 2015 | 7/1/2015 | -58453.29 |  |  |  |  | -58453.29 | 23.062 | 0 | 0 | 0 | 0 | 23.062 | -58476.352 | -253561% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -58476.352 | -253561%
791 | 117 | BS0000021 | Rep Main Steam Attemperator U1 | Charges Began Prior to Jan 2015 | 10/1/2015 | -604009.81 |  |  |  |  | -604009.81 | 404.186 | -952.62 | 0 | 0 | 0 | -548.434 | -604413.996 | -149539% | 952.62 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -603461.376 | 110034%
792 | 117 | Other Budgeted Projects |  | Other | Other | 0 | 0 | 0 | 0 | 0 | 0 | 8628024 | 6279470 | 3725476 | 16083006 | 15186836 | 49902812 | -8628024 | -100% | -6279470 | -100% | -3725476 | -100% | -16083006 | -100% | -15186836 | -100% | -49902812 | -100%
793 | 117 Total |  |  |  |  | 53854969.35 | 46043976.07 | 22986399.326 | 32001996.29 | 29935961.239 | 184823302.275 | 42844550.143 | 32940608.231 | 22764393.789 | 38600798.433 | 33705929.671 | 170856280.267 | 11010419.207 | 25.7% | 13103367.839 | 39.78% | 222005.537 | 0.9752% | -6598802.143 | -17.09% | -3769968.432 | -11.18% | 13967022.008 | 8.175%
794 | 180 | P16113009 | Cannonsburg - S.NEAL TL KPCo | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 7540.89 | 4320320.91 | 7004790.82 | 11332652.62 | 0 | 0 | 0 | 0 | 8359355.36 | 8359355.36 | 0 | n.m. | 0 | n.m. | 7540.89 | n.m. | 4320320.91 | n.m. | -1354564.54 | -16.2% | 2973297.26 | 35.57%
795 | 180 | P13064029 | Hazard-Wooton Change to KPCo | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 813891.56 | 675391.51 | 6595819.03 | 8085102.1 | 0 | 0 | 0 | 0 | 4828882.973 | 4828882.973 | 0 | n.m. | 0 | n.m. | 813891.56 | n.m. | 675391.51 | n.m. | 1766936.057 | 36.59% | 3256219.127 | 67.43%
796 | 180 | B180KYLRC | T/KY/Non-Specific Work - Line | 2/1/2017 | Charges Continued After Dec 2019 |  |  | 1768592.73 | 2010328 | 2127355.99 | 5906276.72 | 0 | 0 | 0 | 448089.568 | 59159.74 | 507249.308 | 0 | n.m. | 0 | n.m. | 1768592.73 | n.m. | 1562238.432 | 348.6% | 2068196.25 | 3496% | 5399027.412 | 1064%
797 | 180 | A15702033 | Jackson - Helech Str. Replace | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 37880.11 | 259941.49 | 5306860.72 | 5604682.32 | 0 | 0 | 0 | 0 | 12844779.434 | 12844779.434 | 0 | n.m. | 0 | n.m. | 37880.11 | n.m. | 259941.49 | n.m. | -7537918.714 | -58.68% | -7240097.114 | -56.37%
798 | 180 | 000005273 | KyPCo-T Capital Software Dev | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 881984.31 | 680088.34 | 933614.69 | 1189138.17 | 969627.8 | 4654453.31 | 0 | 0 | 0 | 0 | 0 | 0 | 881984.31 | n.m. | 680088.34 | n.m. | 933614.69 | n.m. | 1189138.17 | n.m. | 969627.8 | n.m. | 4654453.31 | n.m.
799 | 180 | A14068001 | Baker 765kV Improvements | 6/1/2015 | Charges Continued After Dec 2019 | 114334.33 | 1742688.44 | 742349.12 | 1009283.18 | 669643.87 | 4278298.94 | 0 | 0 | 0 | 0 | 0 | 0 | 114334.33 | n.m. | 1742688.44 | n.m. | 742349.12 | n.m. | 1009283.18 | n.m. | 669643.87 | n.m. | 4278298.94 | n.m.
800 | 180 | P11161025 | Betsy Layne - Allen TLINE KPCo | 8/1/2017 | 11/1/2019 |  |  | 314194.85 | 3478613.48 | 4349.29 | 3797157.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 314194.85 | n.m. | 3478613.48 | n.m. | 4349.29 | n.m. | 3797157.62 | n.m.
801 | 180 | DP16K02B0 | Cedar Creek add D trans | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 174338.2 | 3351786.76 | 3526124.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 174338.2 | n.m. | 3351786.76 | n.m. | 3526124.96 | n.m.
802 | 180 | A15702028 | Dorton 138/46 XF Replacement | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 53312.99 | 300657.27 | 2724152.33 | 3078122.59 | 0 | 0 | 0 | 0 | 1183837.901 | 1183837.901 | 0 | n.m. | 0 | n.m. | 53312.99 | n.m. | 300657.27 | n.m. | 1540314.429 | 130.1% | 1894284.689 | 160%
803 | 180 | 000012898 | Forestry KP T non-NERC | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 470357.38 | 567769.77 | 802835.58 | 602604.59 | 571002.63 | 3014569.95 | 643418.886 | 503242.817 | 750207.978 | 456588.044 | 551703.459 | 2905161.184 | -173061.506 | -26.9% | 64526.953 | 12.82% | 52627.602 | 7.015% | 146016.546 | 31.98% | 19299.171 | 3.498% | 109408.766 | 3.766%
804 | 180 | A15702027 | Johns Creek 138/34 kV XF | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 46300.59 | 311674.8 | 2650274.174 | 3008249.564 | 0 | 0 | 0 | -101077.411 | 2057113.891 | 1956036.48 | 0 | n.m. | 0 | n.m. | 46300.59 | n.m. | 412752.211 | -408.4% | 593160.283 | 28.83% | 1052213.084 | 53.79%
805 | 180 | P10115014 | Stone Change to KPCo | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 132520.92 | 318182.17 | 2296332.66 | 2747035.75 | 0 | 0 | 0 | 0 | 1876865.534 | 1876865.534 | 0 | n.m. | 0 | n.m. | 132520.92 | n.m. | 318182.17 | n.m. | 419467.126 | 22.35% | 870170.216 | 46.36%
806 | 180 | 000010377 | Forestry KY T NERC | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 114927.89 | 64949.72 |  |  | 2554140.67 | 2734018.28 | 140186.89 | 109645.593 | 104503.319 | 96483.595 | 97359.442 | 548178.839 | -25259 | -18.02% | -44695.873 | -40.76% | -104503.319 | -100% | -96483.595 | -100% | 2456781.228 | 2523% | 2185839.441 | 398.7%
807 | 180 | B180KYSRR | T/KY/Non-Specific Work - Stati | 10/1/2016 | Charges Continued After Dec 2019 |  | 85449.97 | 1597339.14 | 523423.37 | 352442.93 | 2558655.41 | 0 | 0 | 0 | 243439.978 | 161321.275 | 404761.253 | 0 | n.m. | 85449.97 | n.m. | 1597339.14 | n.m. | 279983.392 | 115% | 191121.655 | 118.5% | 2153894.157 | 532.1%
808 | 180 | A15702007 | Beaver Creek- Repl Cap Bk AACC | 6/1/2017 | Charges Continued After Dec 2019 |  |  | 229289.27 | 1962726.31 | 112955.25 | 2304970.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 229289.27 | n.m. | 1962726.31 | n.m. | 112955.25 | n.m. | 2304970.83 | n.m.
809 | 180 | P13064030 | Hazard Station Change to KPCo | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 763106.31 | 500058.38 | 886589.15 | 2149753.84 | 0 | 0 | 0 | 0 | 2913451.109 | 2913451.109 | 0 | n.m. | 0 | n.m. | 763106.31 | n.m. | 500058.38 | n.m. | -2026861.959 | -69.57% | -763697.269 | -26.21%
810 | 180 | A15042010 | Stone Station Incr. KPCo | 6/1/2017 | Charges Continued After Dec 2019 |  |  | 90383.36 | 1036651.52 | 939832.72 | 2066867.6 | 0 | 0 | 0 | 0 | 1093822.817 | 1093822.817 | 0 | n.m. | 0 | n.m. | 90383.36 | n.m. | 1036651.52 | n.m. | -153990.097 | -14.08% | 973044.783 | 88.96%
811 | 180 | SI180KYLR | TB/SI/KyP/KY - LINE REHAB | Charges Began Prior to Jan 2015 | 11/1/2018 | 713972.77 | 1053970.85 | 277675.66 | -2550.21 |  | 2043069.07 | 165529.683 | 0 | 0 | 0 | 0 | 165529.683 | 548443.087 | 331.3% | 1053970.85 | n.m. | 277675.66 | n.m. | -2550.21 | n.m. | 0 | n.m. | 1877539.387 | 1134%
812 | 180 | A15702034 | Hazard-Jackson Str Rep Part 2 | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 60682.8 | 197411.94 | 1725260.08 | 1983354.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 60682.8 | n.m. | 197411.94 | n.m. | 1725260.08 | n.m. | 1983354.82 | n.m.
813 | 180 | P11063002 | TKYHazard Station Improvemen | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 1099329.07 | 459567.8 | 223066.51 | 131011.07 | 63677.51 | 1976651.96 | 910237.103 | 76455.642 | 447709.093 | 381080.832 | 0 | 1815482.67 | 189091.967 | 20.77% | 383112.158 | 501.1% | -224642.583 | -50.18% | -250069.762 | -65.62% | 63677.51 | n.m. | 161169.29 | 8.877%
814 | 180 | P11161023 | Stanville Ext TLINE KPCo | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 399786.79 | 1512509.76 | 53324.31 | 1965620.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 399786.79 | n.m. | 1512509.76 | n.m. | 53324.31 | n.m. | 1965620.86 | n.m.
815 | 180 | A15702041 | Hazard CB/XF Replacements | 6/1/2017 | Charges Continued After Dec 2019 |  |  | 1018560.74 | 1518203.93 | -571646.29 | 1965118.38 | 0 | 0 | 0 | 567301.567 | 979758.817 | 1547060.384 | 0 | n.m. | 0 | n.m. | 1018560.74 | n.m. | 950902.363 | 167.6% | -1551405.107 | -158.3% | 418057.996 | 27.02%
816 | 180 | A18730015 | Spring Fork Tap Str 2 Failure | 6/1/2018 | Charges Continued After Dec 2019 |  |  |  | 791072.28 | 1022812.5 | 1813884.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 791072.28 | n.m. | 1022812.5 | n.m. | 1813884.78 | n.m.
817 | 180 | A15702029 | Leslie 161/69kV XF Replacement | 6/1/2017 | Charges Continued After Dec 2019 |  |  | 940124.79 | 1013743.01 | -256968.03 | 1696899.77 | 0 | 0 | 0 | 0 | 2686855.333 | 2686855.333 | 0 | n.m. | 0 | n.m. | 940124.79 | n.m. | 1013743.01 | n.m. | -2943823.363 | -109.6% | -989955.563 | -36.84%
818 | 180 | A18730013 | Baker - Don Marquis STR 162-26 | 4/1/2018 | 11/1/2019 |  |  |  | 1549100.86 | 126248.27 | 1675349.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1549100.86 | n.m. | 126248.27 | n.m. | 1675349.13 | n.m.
819 | 180 | A16928011 | Chadwick Spare Purchase XF | 6/1/2017 | 1/1/2019 |  |  | 509856.98 | 1036398.4 | 1656.08 | 1547911.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 509856.98 | n.m. | 1036398.4 | n.m. | 1656.08 | n.m. | 1547911.46 | n.m.
820 | 180 | P10115002 | TKPStone-RetRem Switches | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 3643.56 | 16879.4 | 1467356.49 | 1487879.45 | 16050.539 | 0 | 0 | 0 | 429782.812 | 445833.351 | -16050.539 | -100% | 0 | n.m. | 3643.56 | n.m. | 16879.4 | n.m. | 1037573.678 | 241.4% | 1042046.099 | 233.7%
821 | 180 | P13064031 | Hazard 161/138 Spare KPCo | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 553939.71 | 364898.71 | 563347.92 | 1482186.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 553939.71 | n.m. | 364898.71 | n.m. | 563347.92 | n.m. | 1482186.34 | n.m.
822 | 180 | A15702053 | Beaver Creek-Betsy Lane Remedi | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 1207646.13 | 196614.2 | 54298.25 | 1458558.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1207646.13 | n.m. | 196614.2 | n.m. | 54298.25 | n.m. | 1458558.58 | n.m.
823 | 180 | A15702010 | Thelma Rpl CB "B, D, BB" | 12/1/2016 | 3/1/2019 |  | 861.66 | 790563.74 | 652950.46 | -926.04 | 1443449.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 861.66 | n.m. | 790563.74 | n.m. | 652950.46 | n.m. | -926.04 | n.m. | 1443449.82 | n.m.
824 | 180 | A16902001 | Big Sandy Remote End Relaying | 11/1/2016 | Charges Continued After Dec 2019 |  | 2011.96 | 439780.35 | 894180.08 | 61986.96 | 1397959.35 | 0 | 0 | 0 | 528809.236 | 0 | 528809.236 | 0 | n.m. | 2011.96 | n.m. | 439780.35 | n.m. | 365370.844 | 69.09% | 61986.96 | n.m. | 869150.114 | 164.4%
825 | 180 | A13002033 | T/KP/Bonnyman-ReplTransf#1 | 7/1/2015 | 9/1/2017 | 1130413.98 | 181089.71 | -902.1 |  |  | 1310601.59 | 0 | 0 | 0 | 0 | 0 | 0 | 1130413.98 | n.m. | 181089.71 | n.m. | -902.1 | n.m. | 0 | n.m. | 0 | n.m. | 1310601.59 | n.m.
826 | 180 | A19750001 | B Sandy - Broadf KP 765 Slide | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1303628.53 | 1303628.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1303628.53 | n.m. | 1303628.53 | n.m.
827 | 180 | P10115010 | T/KP/Inez: replace 138kV Bus # | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 227.44 | 579.31 | 351900.52 | 394397.7 | 465488.27 | 1212593.24 | 58934.746 | -5032.184 | 0 | -3.335 | 384340.491 | 438239.718 | -58707.306 | -99.61% | 5611.494 | -111.5% | 351900.52 | n.m. | 394401.035 | -11826118% | 81147.779 | 21.11% | 774353.522 | 176.7%
828 | 180 | P11161012 | B.Layne-S.Pikeville 69kV KPCo | 12/1/2015 | 8/1/2019 | 364.75 | 25763.22 | 158314.03 | 978802.07 | 21464.08 | 1184708.15 | 0 | 65546.53 | 42779.968 | 337697.632 | 92333.018 | 538357.148 | 364.75 | n.m. | -39783.31 | -60.69% | 115534.062 | 270.1% | 641104.438 | 189.8% | -70868.938 | -76.75% | 646351.002 | 120.1%
829 | 180 | A13002029 | T/KP/Prstnsbrg-MddlCrk-Slide | 4/1/2015 | 7/1/2017 | 1333142.6 | -179722.72 | 22686.32 |  |  | 1176106.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1333142.6 | n.m. | -179722.72 | n.m. | 22686.32 | n.m. | 0 | n.m. | 0 | n.m. | 1176106.2 | n.m.
830 | 180 | P13064025 | Hazard - Wooton ROW KPCo | 4/1/2017 | Charges Continued After Dec 2019 |  |  | 161590.51 | 622675.89 | 383495.28 | 1167761.68 | 0 | 74203.62 | 0 | 0 | 307860.651 | 382064.271 | 0 | n.m. | -74203.62 | -100% | 161590.51 | n.m. | 622675.89 | n.m. | 75634.629 | 24.57% | 785697.409 | 205.6%
831 | 180 | P11028016 | TKPBreaks 69kV Extension - C | Charges Began Prior to Jan 2015 | 7/1/2018 | 703066.68 | 407177.48 | 8712.33 | 30228.86 |  | 1149185.35 | 165526.905 | 30702.439 | 0 | 0 | 0 | 196229.344 | 537539.775 | 324.7% | 376475.041 | 1226% | 8712.33 | n.m. | 30228.86 | n.m. | 0 | n.m. | 952956.006 | 485.6%
832 | 180 | IT1801421 | Maximo Imp - KYP - T | 3/1/2016 | Charges Continued After Dec 2019 |  | 122023.34 | 231969.35 | 376600.48 | 414418.06 | 1145011.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 122023.34 | n.m. | 231969.35 | n.m. | 376600.48 | n.m. | 414418.06 | n.m. | 1145011.23 | n.m.
833 | 180 | P14105001 | T KP DortonLoop138kVSagStudy | 1/1/2015 | 10/1/2015 | 1131260.77 |  |  |  |  | 1131260.77 | 0 | 0 | 0 | 0 | 0 | 0 | 1131260.77 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1131260.77 | n.m.
834 | 180 | P12026001 | TKYDorton-RetireRemove Equi | Charges Began Prior to Jan 2015 | 12/1/2016 | 929390.88 | 172536.36 |  |  |  | 1101927.24 | 404422.895 | 111305.429 | 0 | 0 | 0 | 515728.324 | 524967.985 | 129.8% | 61230.931 | 55.01% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 586198.916 | 113.7%
835 | 180 | P11161007 | T/KP Line Work Betsy-Dewey | 4/1/2016 | 8/1/2019 |  | 5383.78 | 24599.56 | 924496.22 | 105926.81 | 1060406.37 | 0 | 117489.064 | 74341.713 | 417648.411 | 0 | 609479.188 | 0 | n.m. | -112105.284 | -95.42% | -49742.153 | -66.91% | 506847.809 | 121.4% | 105926.81 | n.m. | 450927.182 | 73.99%
836 | 180 | A13212035 | Bellefonte Telecom Legacy Pilo | 11/1/2015 | 7/1/2019 | 129.35 | 86955.46 | 222258.26 | 707745.35 | 16006.67 | 1033095.09 | 0 | 0 | 0 | 0 | 0 | 0 | 129.35 | n.m. | 86955.46 | n.m. | 222258.26 | n.m. | 707745.35 | n.m. | 16006.67 | n.m. | 1033095.09 | n.m.
837 | 180 | P13121005 | Leach: Breaker Replace/Retire | 6/1/2015 | 3/1/2018 | 29162.87 | 445537 | 545341.39 | 1069.61 |  | 1021110.87 | 0 | 371018.096 | 71138.48 | 0 | 0 | 442156.576 | 29162.87 | n.m. | 74518.904 | 20.08% | 474202.91 | 666.6% | 1069.61 | n.m. | 0 | n.m. | 578954.294 | 130.9%
838 | 180 | SI180KYRE | TBSIKyP-KENTUCKY SYS REHAB | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 430379.77 | 557262.53 | 19500.4 | -15663.8 | 2309.96 | 993788.86 | 2060710.279 | 797395.26 | 1316368.069 | -27.514 | 0 | 4174446.094 | -1630330.509 | -79.11% | -240132.73 | -30.11% | -1296867.669 | -98.52% | -15636.286 | 56830% | 2309.96 | n.m. | -3180657.234 | -76.19%
839 | 180 | A15710034 | Coalton-Leon Fiber TelModFib | 8/1/2018 | Charges Continued After Dec 2019 |  |  |  | 313203.45 | 637154.24 | 950357.69 | 0 | 0 | 0 | 0 | 786189.585 | 786189.585 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 313203.45 | n.m. | -149035.345 | -18.96% | 164168.105 | 20.88%
840 | 180 | P10115013 | Johns Creek Change to KPCo | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 136056.95 | 205629.86 | 552392.63 | 894079.44 | 0 | 0 | 0 | 0 | 1521282.561 | 1521282.561 | 0 | n.m. | 0 | n.m. | 136056.95 | n.m. | 205629.86 | n.m. | -968889.931 | -63.69% | -627203.121 | -41.23%
841 | 180 | IT180BILL | Corp Prgrm Billing-KYPCO Trans | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 393453.01 | 87242.76 | 356624.46 | 837320.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 393453.01 | n.m. | 87242.76 | n.m. | 356624.46 | n.m. | 837320.23 | n.m.
842 | 180 | P17225004 | Moore Hollow 138kV Ext ROW | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 6063.81 | 693594.62 | 127433.91 | 827092.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 6063.81 | n.m. | 693594.62 | n.m. | 127433.91 | n.m. | 827092.34 | n.m.
843 | 180 | A19750002 | Betsy Layne- Allen 138kV Slide | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 823087.88 | 823087.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 823087.88 | n.m. | 823087.88 | n.m.
844 | 180 | P11028009 | TKPLine work at Elkhorn City | Charges Began Prior to Jan 2015 | 9/1/2016 | 557769.94 | 243481.67 |  |  |  | 801251.61 | 297953.194 | 0 | 0 | 0 | 0 | 297953.194 | 259816.746 | 87.2% | 243481.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 503298.416 | 168.9%
845 | 180 | TP1015202 | T/KY/Baker 765/345 CANCELLED | Charges Began Prior to Jan 2015 | 10/1/2016 | 576319.87 | 201700.54 |  |  |  | 778020.41 | 391537.045 | 2729.807 | 0 | 0 | 0 | 394266.852 | 184782.825 | 47.19% | 198970.733 | 7289% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 383753.558 | 97.33%
846 | 180 | P13121006 | Bellefonte Remote for Chadwick | 1/1/2016 | 5/1/2018 |  | 243597.14 | 496319.21 | 14731.28 |  | 754647.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 243597.14 | n.m. | 496319.21 | n.m. | 14731.28 | n.m. | 0 | n.m. | 754647.63 | n.m.
847 | 180 | A17750008 | Prestonsburg-Mid Creek46kVSlid | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 743577.65 | 743577.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 743577.65 | n.m. | 743577.65 | n.m.
848 | 180 | P18025005 | Kewanee 138 Ext TLINE | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 612822.72 | 118175.72 | 730998.44 | 0 | 0 | 0 | 0 | 9583873.895 | 9583873.895 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 612822.72 | n.m. | -9465698.175 | -98.77% | -8852875.455 | -92.37%
849 | 180 | P10115015 | Inez Change to KPCo | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 288411.06 | 170485.39 | 256169.66 | 715066.11 | 0 | 0 | 0 | 0 | 250460.836 | 250460.836 | 0 | n.m. | 0 | n.m. | 288411.06 | n.m. | 170485.39 | n.m. | 5708.824 | 2.279% | 464605.274 | 185.5%
850 | 180 | P11161008 | Dewey Remote ends | 1/1/2016 | 8/1/2019 |  | 57357.99 | 114281.97 | 534468.83 | 5667.65 | 711776.44 | 0 | 0 | 0 | 422441.37 | 9778.922 | 432220.292 | 0 | n.m. | 57357.99 | n.m. | 114281.97 | n.m. | 112027.46 | 26.52% | -4111.272 | -42.04% | 279556.148 | 64.68%
851 | 180 | P12001005 | T/KP/Cedar Creek Station: re | Charges Began Prior to Jan 2015 | 2/1/2017 | 570881.92 | 139360.34 | 774.42 |  |  | 711016.68 | 244975.117 | 55794.751 | 0 | 0 | 0 | 300769.868 | 325906.803 | 133% | 83565.589 | 149.8% | 774.42 | n.m. | 0 | n.m. | 0 | n.m. | 410246.812 | 136.4%
852 | 180 | P16113003 | Cannonsburg-SNeal ROW (KY) | 12/1/2016 | Charges Continued After Dec 2019 |  | 2346.7 | 8666.61 | 638478.47 | 35478.57 | 684970.35 | 0 | 0 | 0 | 0 | 137372.857 | 137372.857 | 0 | n.m. | 2346.7 | n.m. | 8666.61 | n.m. | 638478.47 | n.m. | -101894.287 | -74.17% | 547597.493 | 398.6%
853 | 180 | P11161010 | B.Layne - Allen 46 kV KPCo | 7/1/2015 | Charges Continued After Dec 2019 | 4955.8 | 26148.17 | 95099.55 | 519715.5 | 26585.13 | 672504.15 | 0 | 77048.091 | 49909.86 | 270432.192 | 0 | 397390.143 | 4955.8 | n.m. | -50899.921 | -66.06% | 45189.69 | 90.54% | 249283.308 | 92.18% | 26585.13 | n.m. | 275114.007 | 69.23%
854 | 180 | TP0921005 | T/KY/Line: Conxt: Bonnyman-Sof | Charges Began Prior to Jan 2015 | 5/1/2019 | 309045.95 | 87116.93 | 2171.75 | 64673.03 | 207547.41 | 670555.07 | 0 | 0 | 0 | 0 | 0 | 0 | 309045.95 | n.m. | 87116.93 | n.m. | 2171.75 | n.m. | 64673.03 | n.m. | 207547.41 | n.m. | 670555.07 | n.m.
855 | 180 | A17959001 | KPCO/StormRcvry/BarrensheCole | 5/1/2017 | 10/1/2018 |  |  | 635834.14 | 33851.27 |  | 669685.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 635834.14 | n.m. | 33851.27 | n.m. | 0 | n.m. | 669685.41 | n.m.
856 | 180 | A17750007 | Prestonsburg-Thelma 69kV Slide | 2/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 645803.49 | 645803.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 645803.49 | n.m. | 645803.49 | n.m.
857 | 180 | P14105002 | T KP Dorton-Fleming138kVSagStu | Charges Began Prior to Jan 2015 | 10/1/2015 | 616660.36 |  |  |  |  | 616660.36 | 0 | 0 | 0 | 0 | 0 | 0 | 616660.36 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 616660.36 | n.m.
858 | 180 | DR14K02D0 | Big Sandy Sta Add 3rd Brk | 8/1/2015 | 5/1/2017 | 92149.67 | 513540.47 | 5102.59 |  |  | 610792.73 | 0 | 0 | 0 | 0 | 0 | 0 | 92149.67 | n.m. | 513540.47 | n.m. | 5102.59 | n.m. | 0 | n.m. | 0 | n.m. | 610792.73 | n.m.
859 | 180 | P10115001 | TKPJohns Creek-RetRem MOABs | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 362.26 | 5654.31 | 13741.25 | 6820.96 | 555075.19 | 581653.97 | 132748.887 | 3955.565 | 0 | 401413.805 | 904564.883 | 1442683.14 | -132386.627 | -99.73% | 1698.745 | 42.95% | 13741.25 | n.m. | -394592.845 | -98.3% | -349489.693 | -38.64% | -861029.17 | -59.68%
860 | 180 | P11028010 | TKPLine work at Elkhorn City | Charges Began Prior to Jan 2015 | 1/1/2018 | 48257.63 | 375508.5 | 133533.99 | 747.53 |  | 558047.65 | 264840.663 | 138.998 | 0 | 0 | 0 | 264979.661 | -216583.033 | -81.78% | 375369.502 | 270054% | 133533.99 | n.m. | 747.53 | n.m. | 0 | n.m. | 293067.989 | 110.6%
861 | 180 | P17225003 | Moore Hollow 138kV Extension | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 57369.32 | 407881.71 | 86371.57 | 551622.6 | 0 | 0 | 0 | 0 | 1192.354 | 1192.354 | 0 | n.m. | 0 | n.m. | 57369.32 | n.m. | 407881.71 | n.m. | 85179.216 | 7144% | 550430.246 | 46163%
862 | 180 | KEPCS1701 | KPCo Storm - Transmission | 3/1/2017 | 2/1/2019 |  |  | 547969.14 | 13927.23 | -15776.97 | 546119.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 547969.14 | n.m. | 13927.23 | n.m. | -15776.97 | n.m. | 546119.4 | n.m.
863 | 180 | P12001003 | TKPBEAVER CREEK - Remote End | Charges Began Prior to Jan 2015 | 5/1/2016 | 524687.13 | 7637.73 |  |  |  | 532324.86 | 425867.633 | 0 | 0 | 0 | 0 | 425867.633 | 98819.497 | 23.2% | 7637.73 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 106457.227 | 25%
864 | 180 | A13002009 | Hanging Rock - Jefferson (KP) | Charges Began Prior to Jan 2015 | 3/1/2016 | 536531.51 | -5584.05 |  |  |  | 530947.46 | 0 | 0 | 0 | 0 | 0 | 0 | 536531.51 | n.m. | -5584.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 530947.46 | n.m.
865 | 180 | A15702055 | Hazard Stn Rplc Fld Bnk #4 | 6/1/2017 | 11/1/2018 |  |  | 312105.73 | 202565.77 |  | 514671.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 312105.73 | n.m. | 202565.77 | n.m. | 0 | n.m. | 514671.5 | n.m.
866 | 180 | P18221017 | Jackhorn Land Purchase | 8/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 508480.8 | 508480.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 508480.8 | n.m. | 508480.8 | n.m.
867 | 180 | P11063001 | TKYBeaver Creek Station Rela | Charges Began Prior to Jan 2015 | 8/1/2016 | 490532.7 | 15485.08 |  |  |  | 506017.78 | 165526.905 | 0 | 0 | 0 | 0 | 165526.905 | 325005.795 | 196.3% | 15485.08 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 340490.875 | 205.7%
868 | 180 | P11161024 | Stanville Ext ROW KPCo | 8/1/2017 | 4/1/2019 |  |  | 317110.58 | 188306.53 | -1508.67 | 503908.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 317110.58 | n.m. | 188306.53 | n.m. | -1508.67 | n.m. | 503908.44 | n.m.
869 | 180 | A15710033 | Morgan Fork Fiber TelModFib | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 1207.34 | 264457.51 | 236448.82 | 502113.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1207.34 | n.m. | 264457.51 | n.m. | 236448.82 | n.m. | 502113.67 | n.m.
870 | 180 | P13121013 | TLINE work @ Chadwick: KES | 4/1/2016 | 1/1/2018 |  | 38347.18 | 454960.53 | 0.48 |  | 493308.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 38347.18 | n.m. | 454960.53 | n.m. | 0.48 | n.m. | 0 | n.m. | 493308.19 | n.m.
871 | 180 | A17042001 | Big Sandy-Baker 138kV Tie | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 498449.3 | -28657.28 | 469792.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 498449.3 | n.m. | -28657.28 | n.m. | 469792.02 | n.m.
872 | 180 | P13037005 | Beaver Creek Station - Remote | Charges Began Prior to Jan 2015 | 10/1/2016 | 459405.51 | 7880.64 |  |  |  | 467286.15 | 230907.371 | 3747.4 | 0 | 0 | 0 | 234654.771 | 228498.139 | 98.96% | 4133.24 | 110.3% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 232631.379 | 99.14%
873 | 180 | A17938021 | KPCO-Trans-Security AccSys-Est | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 193069.43 | 209512.37 | 56579.02 | 459160.82 | 0 | 0 | 0 | 0.013 | 0 | 0.013 | 0 | n.m. | 0 | n.m. | 193069.43 | n.m. | 209512.357 | 1611633515% | 56579.02 | n.m. | 459160.807 | 3532006208%
874 | 180 | P11161009 | Morgan Fork Remote End | 7/1/2015 | 8/1/2019 | 983.09 | 39606.65 | 114244.99 | 295810.42 | 3153.62 | 453798.77 | 0 | 0 | 0 | 357422.402 | 0 | 357422.402 | 983.09 | n.m. | 39606.65 | n.m. | 114244.99 | n.m. | -61611.982 | -17.24% | 3153.62 | n.m. | 96376.368 | 26.96%
875 | 180 | P11028008 | TKPLine work at Elkhorn City | Charges Began Prior to Jan 2015 | 9/1/2016 | 373138.48 | 65684.69 |  |  |  | 438823.17 | 215182.195 | 0 | 0 | 0 | 0 | 215182.195 | 157956.285 | 73.41% | 65684.69 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 223640.975 | 103.9%
876 | 180 | A15042007 | Highland-Raceland FC ADSS | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 23852.45 | 289721.06 | 124459.48 | 438032.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 23852.45 | n.m. | 289721.06 | n.m. | 124459.48 | n.m. | 438032.99 | n.m.
877 | 180 | A19750003 | Hazard - Pineville 161kV Fail | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 432150.41 | 432150.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 432150.41 | n.m. | 432150.41 | n.m.
878 | 180 | A15702002 | T/KY/BigSandy-Inez138kv:Lights | 8/1/2016 | 1/1/2019 |  | 188289.43 | 101192.35 | 136452.58 | 93.83 | 426028.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 188289.43 | n.m. | 101192.35 | n.m. | 136452.58 | n.m. | 93.83 | n.m. | 426028.19 | n.m.
879 | 180 | A17212001 | Big Sandy 138KV RTU Replacemen | 7/1/2018 | Charges Continued After Dec 2019 |  |  |  | 21816.23 | 398626.29 | 420442.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21816.23 | n.m. | 398626.29 | n.m. | 420442.52 | n.m.
880 | 180 | A18730016 | Bonnyman-Softshell St 88 Failr | 6/1/2018 | Charges Continued After Dec 2019 |  |  |  | 54508.75 | 365512.83 | 420021.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 54508.75 | n.m. | 365512.83 | n.m. | 420021.58 | n.m.
881 | 180 | P13121002 | D/KP/Chadwick: remove 138kV eq | 6/1/2015 | 3/1/2018 | 12914.81 | 177946.57 | 218292.74 | 1160.98 |  | 410315.1 | 265674.947 | 27396.525 | 71251.784 | 0 | 0 | 364323.256 | -252760.137 | -95.14% | 150550.045 | 549.5% | 147040.956 | 206.4% | 1160.98 | n.m. | 0 | n.m. | 45991.844 | 12.62%
882 | 180 | A15702030 | Morehead: Replace CB B | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 53760.33 | 141796.29 | 214606.12 | 410162.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 53760.33 | n.m. | 141796.29 | n.m. | 214606.12 | n.m. | 410162.74 | n.m.
883 | 180 | A16928002 | Baker Station: Purchase 69/13k | 12/1/2017 | 9/1/2018 |  |  | 320322.1 | 89757.4 |  | 410079.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 320322.1 | n.m. | 89757.4 | n.m. | 0 | n.m. | 410079.5 | n.m.
884 | 180 | A13212034 | Leon SW (KY) Telecom Legacy C | 11/1/2015 | 1/1/2017 | 5992.6 | 396074.11 | 0.69 |  |  | 402067.4 | 0 | 0 | 0 | 0 | 0 | 0 | 5992.6 | n.m. | 396074.11 | n.m. | 0.69 | n.m. | 0 | n.m. | 0 | n.m. | 402067.4 | n.m.
885 | 180 | A13212030 | Hatfield (KP) - Telecom Legacy | 10/1/2015 | 12/1/2017 | 54656.67 | 324282.32 | 11206.89 |  |  | 390145.88 | 0 | 0 | 0 | 0 | 0 | 0 | 54656.67 | n.m. | 324282.32 | n.m. | 11206.89 | n.m. | 0 | n.m. | 0 | n.m. | 390145.88 | n.m.
886 | 180 | A15702013 | T/KP/Leach:S.Neal pilot wire | 12/1/2016 | 8/1/2019 |  | 3286.62 | 331693.32 | 42436.91 | 5191.51 | 382608.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 3286.62 | n.m. | 331693.32 | n.m. | 42436.91 | n.m. | 5191.51 | n.m. | 382608.36 | n.m.
887 | 180 | B180KYSRC | T/KY/Non-Specific Work-Station | 12/1/2016 | Charges Continued After Dec 2019 |  | 8691.59 | 188169.68 | 176022.82 | 8350.25 | 381234.34 | 0 | 0 | 0 | 214901.349 | 134451.604 | 349352.953 | 0 | n.m. | 8691.59 | n.m. | 188169.68 | n.m. | -38878.529 | -18.09% | -126101.354 | -93.79% | 31881.387 | 9.126%
888 | 180 | ITCW18001 | KY Next Generation Radio Sys | 4/1/2017 | 12/1/2018 |  |  | 337224.86 | 25745.3 |  | 362970.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 337224.86 | n.m. | 25745.3 | n.m. | 0 | n.m. | 362970.16 | n.m.
889 | 180 | P12088002 | Bellefonte: 69kV SUPP Work | 9/1/2015 | 10/1/2018 | 12345.01 | 5428.31 | 173162.55 | 171950.34 |  | 362886.21 | 49240.102 | 37101.809 | 178927.735 | 0 | 0 | 265269.646 | -36895.092 | -74.93% | -31673.499 | -85.37% | -5765.185 | -3.222% | 171950.34 | n.m. | 0 | n.m. | 97616.564 | 36.8%
890 | 180 | B180KYTRE | T/KP/Transmission Region Tools | 3/1/2017 | 1/1/2019 |  |  | 229072.19 | 129816.33 | 117.59 | 359006.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 229072.19 | n.m. | 129816.33 | n.m. | 117.59 | n.m. | 359006.11 | n.m.
891 | 180 | A15710035 | Pikeville Fiber TelModFib | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 313088.78 | 313088.78 | 0 | 0 | 0 | 0 | 455158.307 | 455158.307 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -142069.527 | -31.21% | -142069.527 | -31.21%
892 | 180 | P17110001 | Chadwick Station Work | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 29060.53 | 153194.94 | 120071.61 | 302327.08 | 0 | 0 | 0 | 0 | 10473192.521 | 10473192.521 | 0 | n.m. | 0 | n.m. | 29060.53 | n.m. | 153194.94 | n.m. | -10353120.911 | -98.85% | -10170865.441 | -97.11%
893 | 180 | A12102008 | T/KP/Dorton-Purch Z-Z Gnd Xfmr | Charges Began Prior to Jan 2015 | 5/1/2015 | 296766.52 |  |  |  |  | 296766.52 | 0 | 0 | 0 | 0 | 0 | 0 | 296766.52 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 296766.52 | n.m.
894 | 180 | A15042011 | Coleman-Stone 69kV reconfig | 6/1/2017 | 11/1/2019 |  |  | 3909.81 | 14283.08 | 277568.61 | 295761.5 | 0 | 0 | 0 | 0 | 183752.859 | 183752.859 | 0 | n.m. | 0 | n.m. | 3909.81 | n.m. | 14283.08 | n.m. | 93815.751 | 51.06% | 112008.641 | 60.96%
895 | 180 | TP0700502 | TS/KyP/Bonnyman Sta removal | Charges Began Prior to Jan 2015 | 7/1/2016 | 41407.9 | 251068.39 |  |  |  | 292476.29 | 0 | 374728.277 | 0 | 0 | 0 | 374728.277 | 41407.9 | n.m. | -123659.887 | -33% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -82251.987 | -21.95%
896 | 180 | A15702035 | Hazard - Fleming Str. Replace | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 93262.04 | 42152.55 | 155338.27 | 290752.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 93262.04 | n.m. | 42152.55 | n.m. | 155338.27 | n.m. | 290752.86 | n.m.
897 | 180 | A15010001 | Ashland-Kenova69kV-Relocate | 2/1/2015 | 10/1/2018 | 82869.72 | 5069.13 | 35082.43 | 160985 |  | 284006.28 | 0 | 0 | 0 | 0 | 0 | 0 | 82869.72 | n.m. | 5069.13 | n.m. | 35082.43 | n.m. | 160985 | n.m. | 0 | n.m. | 284006.28 | n.m.
898 | 180 | A15705185 | Johns Creek 69kV Breaker Failu | 12/1/2016 | 4/1/2019 |  | 16120.56 | 281066.36 | -15369.17 | 240.88 | 282058.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 16120.56 | n.m. | 281066.36 | n.m. | -15369.17 | n.m. | 240.88 | n.m. | 282058.63 | n.m.
899 | 180 | A15702054 | Stone TF Failre Rplcment | 6/1/2017 | 11/1/2019 |  |  | 238825.38 | 13164.15 | 29096.05 | 281085.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 238825.38 | n.m. | 13164.15 | n.m. | 29096.05 | n.m. | 281085.58 | n.m.
900 | 180 | P11161026 | Betsy Layne - Allen ROW KPCo | 11/1/2017 | 9/1/2019 |  |  | 203099.73 | 80143.03 | -3132.22 | 280110.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 203099.73 | n.m. | 80143.03 | n.m. | -3132.22 | n.m. | 280110.54 | n.m.
901 | 180 | P13064021 | T/KP/Hazard - Jackson 69kV Lin | 5/1/2016 | Charges Continued After Dec 2019 |  | 3870.4 | 34393.3 | 68845.73 | 170634.35 | 277743.78 | 63404.442 | 227805.112 | 243436.386 | 97109.67 | 0 | 631755.61 | -63404.442 | -100% | -223934.712 | -98.3% | -209043.086 | -85.87% | -28263.94 | -29.11% | 170634.35 | n.m. | -354011.83 | -56.04%
902 | 180 | P12104006 | T/KP/Bellefonte 138kV Remote R | 10/1/2015 | 9/1/2018 | 10511.23 | 127289.63 | 112715.08 | 21678.83 |  | 272194.77 | 0 | 5952.187 | 0 | 0 | 0 | 5952.187 | 10511.23 | n.m. | 121337.443 | 2039% | 112715.08 | n.m. | 21678.83 | n.m. | 0 | n.m. | 266242.583 | 4473%
903 | 180 | P11161022 | Beaver Cr - Betsy L TLINE KPCo | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 19561.31 | 237458.83 | 11037.43 | 268057.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 19561.31 | n.m. | 237458.83 | n.m. | 11037.43 | n.m. | 268057.57 | n.m.
904 | 180 | A16905009 | Cancelled - DO NOT USE | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 54478.49 | 191240.08 | 21020.17 | 266738.74 | 0 | 0 | 0 | 739624.373 | 252889.975 | 992514.348 | 0 | n.m. | 0 | n.m. | 54478.49 | n.m. | -548384.293 | -74.14% | -231869.805 | -91.69% | -725775.608 | -73.12%
905 | 180 | P13064002 | T/KP/Hazard Station / OPCO | 8/1/2016 | Charges Continued After Dec 2019 |  | 53475.35 | 26713.33 | 97377.45 | 87526.79 | 265092.92 | 0 | 101411.612 | 71138.48 | 6449.891 | 183906.257 | 362906.24 | 0 | n.m. | -47936.262 | -47.27% | -44425.15 | -62.45% | 90927.559 | 1410% | -96379.467 | -52.41% | -97813.32 | -26.95%
906 | 180 | A15702047 | Leon KY Remote End Work | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 43621.37 | 46892.46 | 171661.77 | 262175.6 | 0 | 0 | 0 | 285610.988 | 0 | 285610.988 | 0 | n.m. | 0 | n.m. | 43621.37 | n.m. | -238718.528 | -83.58% | 171661.77 | n.m. | -23435.388 | -8.205%
907 | 180 | A15042005 | Baker-Big Sandy Fiber Cable | 2/1/2018 | 7/1/2019 |  |  |  | 164733.23 | 92470.61 | 257203.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 164733.23 | n.m. | 92470.61 | n.m. | 257203.84 | n.m.
908 | 180 | P16116005 | Stinnett -Pineville TL to KPCo | 7/1/2017 | Charges Continued After Dec 2019 |  |  | 200465.77 | 46889.45 | 8507.52 | 255862.74 | 0 | 0 | 0 | 0 | 6571.577 | 6571.577 | 0 | n.m. | 0 | n.m. | 200465.77 | n.m. | 46889.45 | n.m. | 1935.943 | 29.46% | 249291.163 | 3793%
909 | 180 | KYCR34118 | KY CR Johns Creek Sta | 1/1/2016 | 7/1/2018 |  | 184733.54 | 54177.99 | 10395.37 |  | 249306.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 184733.54 | n.m. | 54177.99 | n.m. | 10395.37 | n.m. | 0 | n.m. | 249306.9 | n.m.
910 | 180 | DR18K02B1 | Bonnyman Sta - Add DRTU | 9/1/2018 | Charges Continued After Dec 2019 |  |  |  | 25128.3 | 223313.576 | 248441.876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25128.3 | n.m. | 223313.576 | n.m. | 248441.876 | n.m.
911 | 180 | A14068005 | Ashland to Coalton Fiber Build | 8/1/2018 | 7/1/2019 |  |  |  | 175518.61 | 72690.9 | 248209.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 175518.61 | n.m. | 72690.9 | n.m. | 248209.51 | n.m.
912 | 180 | P10115003 | TKPStone Tap - Retire | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 392.25 | 682.99 | 5203.4 | 6676.93 | 234792.99 | 247748.56 | 23001.988 | -333.595 | 0 | 197236.433 | 366127.501 | 586032.327 | -22609.738 | -98.29% | 1016.585 | -304.7% | 5203.4 | n.m. | -190559.503 | -96.61% | -131334.511 | -35.87% | -338283.767 | -57.72%
913 | 180 | P18025006 | Kewanee 138 Ext ROW | 5/1/2018 | Charges Continued After Dec 2019 |  |  |  | 183103.49 | 43342.38 | 226445.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 183103.49 | n.m. | 43342.38 | n.m. | 226445.87 | n.m.
914 | 180 | P17225001 | Moore Hollow 138kV Station | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 33260.79 | 129797.23 | 61988.87 | 225046.89 | 0 | 0 | 0 | 0 | 1207.917 | 1207.917 | 0 | n.m. | 0 | n.m. | 33260.79 | n.m. | 129797.23 | n.m. | 60780.953 | 5032% | 223838.973 | 18531%
915 | 180 | A13002022 | NERC CIP V5 UPGRADES - KYPCO | Charges Began Prior to Jan 2015 | 1/1/2017 | 210415.86 | 1740.44 | 268.96 |  |  | 212425.26 | 0 | 0 | 0 | 0 | 0 | 0 | 210415.86 | n.m. | 1740.44 | n.m. | 268.96 | n.m. | 0 | n.m. | 0 | n.m. | 212425.26 | n.m.
916 | 180 | DR18K02B2 | Leslie Sta - breaker control | 10/1/2018 | Charges Continued After Dec 2019 |  |  |  | 23524.05 | 186915.484 | 210439.534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23524.05 | n.m. | 186915.484 | n.m. | 210439.534 | n.m.
917 | 180 | KYCR33039 | KY CR Leslie Sta | 1/1/2016 | 7/1/2018 |  | 138472.9 | 62923.72 | 8656.31 |  | 210052.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 138472.9 | n.m. | 62923.72 | n.m. | 8656.31 | n.m. | 0 | n.m. | 210052.93 | n.m.
918 | 180 | A13002016 | T/KP/Dorton-Repl Z-Z Gnd Bank | Charges Began Prior to Jan 2015 | 5/1/2016 | 202791.04 | 4306.97 |  |  |  | 207098.01 | 78953.992 | 0 | 0 | 0 | 0 | 78953.992 | 123837.048 | 156.8% | 4306.97 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 128144.018 | 162.3%
919 | 180 | A13212018 | T/KP/Morehead-Telecom Upgrades | Charges Began Prior to Jan 2015 | 1/1/2016 | 196600.76 | 18.42 |  |  |  | 196619.18 | 0 | 0 | 0 | 0 | 0 | 0 | 196600.76 | n.m. | 18.42 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 196619.18 | n.m.
920 | 180 | P12088005 | Bellefonte Rem/Rep XF (KPCo) | 5/1/2016 | 9/1/2018 |  | 1691.95 | 38133.32 | 153218.39 |  | 193043.66 | 0 | 0 | 52565.894 | 0 | 0 | 52565.894 | 0 | n.m. | 1691.95 | n.m. | -14432.574 | -27.46% | 153218.39 | n.m. | 0 | n.m. | 140477.766 | 267.2%
921 | 180 | P14030102 | Leslie - Wooton TL to KPCo | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 178691.37 | 9354.36 | 3255.84 | 191301.57 | 0 | 0 | 0 | 0 | 492670.31 | 492670.31 | 0 | n.m. | 0 | n.m. | 178691.37 | n.m. | 9354.36 | n.m. | -489414.47 | -99.34% | -301368.74 | -61.17%
922 | 180 | DR19K04B0 | Pikeville DA 2019 - Beaver Ck | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 184594.808 | 184594.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 184594.808 | n.m. | 184594.808 | n.m.
923 | 180 | P12001001 | TKPCedar Creek-RetireRemove | Charges Began Prior to Jan 2015 | 12/1/2016 | 162013.76 | 19937.94 |  |  |  | 181951.7 | 81694.336 | 77518.402 | 0 | 0 | 0 | 159212.738 | 80319.424 | 98.32% | -57580.462 | -74.28% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22738.962 | 14.28%
924 | 180 | DR19K04B1 | Pikeville DA 2019 - Stanville | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 180747.28 | 180747.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 180747.28 | n.m. | 180747.28 | n.m.
925 | 180 | KYCR30003 | KY CR Bellefonte Sta | 12/1/2015 | 8/1/2019 | 657.13 | 61892.59 | 17685.29 | 62344.13 | 31701.54 | 174280.68 | 0 | 0 | 0 | 0 | 0 | 0 | 657.13 | n.m. | 61892.59 | n.m. | 17685.29 | n.m. | 62344.13 | n.m. | 31701.54 | n.m. | 174280.68 | n.m.
926 | 180 | A13212037 | South Portsmouth Telecom Legac | 5/1/2016 | 5/1/2018 |  | 53932.27 | 103358.35 | 560.56 |  | 157851.18 | 0 | 0 | 0 | 60960.177 | 0 | 60960.177 | 0 | n.m. | 53932.27 | n.m. | 103358.35 | n.m. | -60399.617 | -99.08% | 0 | n.m. | 96891.003 | 158.9%
927 | 180 | A18730009 | T/KY/EngleTapLighting:Failure | 2/1/2018 | 3/1/2019 |  |  |  | 153717.73 | 3013.63 | 156731.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 153717.73 | n.m. | 3013.63 | n.m. | 156731.36 | n.m.
928 | 180 | A15702014 | Thelma-2017GEUpgrade | 2/1/2017 | 6/1/2018 |  |  | 147769.33 | 3176.93 |  | 150946.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 147769.33 | n.m. | 3176.93 | n.m. | 0 | n.m. | 150946.26 | n.m.
929 | 180 | IT1801323 | High Avail Data Ctr-KYP-T | Charges Began Prior to Jan 2015 | 3/1/2016 | 2736.26 | 136974.4 |  |  |  | 139710.66 | 0 | 0 | 0 | 0 | 0 | 0 | 2736.26 | n.m. | 136974.4 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 139710.66 | n.m.
930 | 180 | P13064003 | T/KP/Wooton Station - Station | 5/1/2016 | Charges Continued After Dec 2019 |  | 60034.68 | 14260.35 | 50469.33 | 8722.14 | 133486.5 | 0 | 0 | 0 | 140682.994 | 0 | 140682.994 | 0 | n.m. | 60034.68 | n.m. | 14260.35 | n.m. | -90213.664 | -64.13% | 8722.14 | n.m. | -7196.494 | -5.115%
931 | 180 | A15702036 | Daisy-Clover Fork Str. Replace | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 44584.96 | 32286.6 | 52416.61 | 129288.17 | 0 | 0 | 0 | 91283.252 | 0 | 91283.252 | 0 | n.m. | 0 | n.m. | 44584.96 | n.m. | -58996.652 | -64.63% | 52416.61 | n.m. | 38004.918 | 41.63%
932 | 180 | O17EST025 | SCADA - SERVERS - KPCO | 6/1/2017 | 3/1/2018 |  |  | 119086.58 | 3565.04 |  | 122651.62 | 0 | 0 | 229036.436 | 14749.977 | 0 | 243786.413 | 0 | n.m. | 0 | n.m. | -109949.856 | -48.01% | -11184.937 | -75.83% | 0 | n.m. | -121134.793 | -49.69%
933 | 180 | A18730002 | Jackson-Helech Str Rplc ROW | 8/1/2017 | 11/1/2019 |  |  | 21977.08 | 54126.39 | 35180.46 | 111283.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 21977.08 | n.m. | 54126.39 | n.m. | 35180.46 | n.m. | 111283.93 | n.m.
934 | 180 | A13002030 | T/KP/Baker-DonMarquis765kV-Str | 5/1/2015 | 7/1/2016 | 98150.25 | 10894.59 |  |  |  | 109044.84 | 0 | 0 | 0 | 0 | 0 | 0 | 98150.25 | n.m. | 10894.59 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 109044.84 | n.m.
935 | 180 | A18730003 | Hazard-Jackson Str. Replc ROW | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 15934.18 | 63942.18 | 27961.35 | 107837.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 15934.18 | n.m. | 63942.18 | n.m. | 27961.35 | n.m. | 107837.71 | n.m.
936 | 180 | P14030008 | T/KP/Leslie Station Work | 6/1/2016 | Charges Continued After Dec 2019 |  | 73821.45 | 16541.85 | 7293.75 | 9273.34 | 106930.39 | 0 | 0 | 10059284.528 | 229712.995 | 183059.485 | 10472057.008 | 0 | n.m. | 73821.45 | n.m. | -10042742.678 | -99.84% | -222419.245 | -96.82% | -173786.145 | -94.93% | -10365126.618 | -98.98%
937 | 180 | A15710041 | Grayson Fiber Ext TelModFib | 12/1/2018 | Charges Continued After Dec 2019 |  |  |  | 615.08 | 101515.23 | 102130.31 | 0 | 0 | 0 | 0 | 22997.958 | 22997.958 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 615.08 | n.m. | 78517.272 | 341.4% | 79132.352 | 344.1%
938 | 180 | A15702032 | Hazard-Bonnyman Str. Replace | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 48959.79 | 11917.2 | 40290.91 | 101167.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 48959.79 | n.m. | 11917.2 | n.m. | 40290.91 | n.m. | 101167.9 | n.m.
939 | 180 | P17076001 | Kenwood Extension TLINE | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 39895.57 | 42179.34 | 18155.44 | 100230.35 | 0 | 0 | 0 | 0 | 183363.544 | 183363.544 | 0 | n.m. | 0 | n.m. | 39895.57 | n.m. | 42179.34 | n.m. | -165208.104 | -90.1% | -83133.194 | -45.34%
940 | 180 | P17225013 | Ramey 138 kV Extension TLINE | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 8367.06 | 8134.21 | 79063.44 | 95564.71 | 0 | 0 | 0 | 0 | 3136266.36 | 3136266.36 | 0 | n.m. | 0 | n.m. | 8367.06 | n.m. | 8134.21 | n.m. | -3057202.92 | -97.48% | -3040701.65 | -96.95%
941 | 180 | P18221013 | Beaver Creek Remote End | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 90105.69 | 90105.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 90105.69 | n.m. | 90105.69 | n.m.
942 | 180 | P17084003 | Cancel - DO NOT USE | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 6436 | 68946.52 | 5762.35 | 81144.87 | 0 | 0 | 0 | 0 | 3116953.091 | 3116953.091 | 0 | n.m. | 0 | n.m. | 6436 | n.m. | 68946.52 | n.m. | -3111190.741 | -99.82% | -3035808.221 | -97.4%
943 | 180 | A15702006 | KYPCo BAT HCP | 4/1/2016 | Charges Continued After Dec 2019 |  | 1350.05 | 9662.59 | 39897.95 | 29581.08 | 80491.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1350.05 | n.m. | 9662.59 | n.m. | 39897.95 | n.m. | 29581.08 | n.m. | 80491.67 | n.m.
944 | 180 | A15042012 | Stone-Sprigg 46kV Reconfig | 6/1/2017 | Charges Continued After Dec 2019 |  |  | 4127.83 | 10080.79 | 64395.24 | 78603.86 | 0 | 0 | 0 | 0 | 54651.858 | 54651.858 | 0 | n.m. | 0 | n.m. | 4127.83 | n.m. | 10080.79 | n.m. | 9743.382 | 17.83% | 23952.002 | 43.83%
945 | 180 | P17110003 | Bellefonte Remote end Work | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 7228.55 | 51699.85 | 15626.41 | 74554.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7228.55 | n.m. | 51699.85 | n.m. | 15626.41 | n.m. | 74554.81 | n.m.
946 | 180 | SI180KYUN | TB SI KYPCO - KENTUCKY UNCAT | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 33680.05 | 11370.35 | 23270.78 | 3125.6 | 2228.26 | 73675.04 | 0 | 0 | 0 | 0 | 0 | 0 | 33680.05 | n.m. | 11370.35 | n.m. | 23270.78 | n.m. | 3125.6 | n.m. | 2228.26 | n.m. | 73675.04 | n.m.
947 | 180 | A15702003 | Inez Station - UPFC Retirement | 4/1/2017 | 6/1/2018 |  |  | 41286.31 | 29983.79 |  | 71270.1 | 0 | 0 | 116189.99 | 0 | 0 | 116189.99 | 0 | n.m. | 0 | n.m. | -74903.68 | -64.47% | 29983.79 | n.m. | 0 | n.m. | -44919.89 | -38.66%
948 | 180 | P17083001 | Garrett-Soft Shell 138kV TLINE | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 71239.76 | 71239.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 71239.76 | n.m. | 71239.76 | n.m.
949 | 180 | A15710024 | Beaver Creek TTMP | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 1596.44 | 37260.08 | 29772.29 | 68628.81 | 0 | 0 | 0 | 21340.364 | 0 | 21340.364 | 0 | n.m. | 0 | n.m. | 1596.44 | n.m. | 15919.716 | 74.6% | 29772.29 | n.m. | 47288.446 | 221.6%
950 | 180 | P17084026 | Beaver Creek - Fleming Cut in | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 8222.22 | 52732.61 | 7092.29 | 68047.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 8222.22 | n.m. | 52732.61 | n.m. | 7092.29 | n.m. | 68047.12 | n.m.
951 | 180 | P17084016 | DO NOT USE | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 28139.73 | 35173.91 | 2953.17 | 66266.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 28139.73 | n.m. | 35173.91 | n.m. | 2953.17 | n.m. | 66266.81 | n.m.
952 | 180 | A15702016 | BeaverCreek-2017GEUpgrade | 1/1/2017 | 6/1/2018 |  |  | 66182.72 | -361.9 |  | 65820.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 66182.72 | n.m. | -361.9 | n.m. | 0 | n.m. | 65820.82 | n.m.
953 | 180 | ITCB18000 | KENTUCKY POWER - TRANSM | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 4579.91 | 43591.15 | 7160.94 |  | 10464.66 | 65796.66 | 0 | 0 | 0 | 0 | 0 | 0 | 4579.91 | n.m. | 43591.15 | n.m. | 7160.94 | n.m. | 0 | n.m. | 10464.66 | n.m. | 65796.66 | n.m.
954 | 180 | A13212026 | Thelma Station - Telecom Legac | 6/1/2015 | 3/1/2016 | 62153.86 | 3510.2 |  |  |  | 65664.06 | 0 | 0 | 0 | 0 | 0 | 0 | 62153.86 | n.m. | 3510.2 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 65664.06 | n.m.
955 | 180 | A10119028 | T/KP/Baker765-Ret/Rem Reactors | Charges Began Prior to Jan 2015 | 1/1/2017 | 45291.94 | 20293.73 | 9.76 |  |  | 65595.43 | 41375.764 | 0 | 0 | 0 | 0 | 41375.764 | 3916.176 | 9.465% | 20293.73 | n.m. | 9.76 | n.m. | 0 | n.m. | 0 | n.m. | 24219.666 | 58.54%
956 | 180 | DP14K02C0 | KP/Raccoon Sta - T line in & o | 8/1/2018 | Charges Continued After Dec 2019 |  |  |  | 7775.82 | 56643.65 | 64419.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7775.82 | n.m. | 56643.65 | n.m. | 64419.47 | n.m.
957 | 180 | A18730011 | T/KY/EngleTapLighting: ROW | 3/1/2018 | 3/1/2019 |  |  |  | 62081.16 | 65.05 | 62146.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 62081.16 | n.m. | 65.05 | n.m. | 62146.21 | n.m.
958 | 180 | A15702060 | Wooton-2018Geupgrade | 1/1/2018 | 3/1/2019 |  |  |  | 54911.46 | -1101.7 | 53809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 54911.46 | n.m. | -1101.7 | n.m. | 53809.76 | n.m.
959 | 180 | P19215003 | Chadwick - England Hill TLINE | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 50615.36 | 50615.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50615.36 | n.m. | 50615.36 | n.m.
960 | 180 | P17225015 | East Park - Princess 138kV TL | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 26880.47 | 16833.87 | 6560.95 | 50275.29 | 0 | 0 | 0 | 0 | 3678127.282 | 3678127.282 | 0 | n.m. | 0 | n.m. | 26880.47 | n.m. | 16833.87 | n.m. | -3671566.332 | -99.82% | -3627851.992 | -98.63%
961 | 180 | O15EST026 | MOE - REV METERING LCTE - KY | 11/1/2014 | 1/1/2016 | 48961 | 320.82 |  |  |  | 49281.82 | 0 | 0 | 0 | 0 | 0 | 0 | 48961 | n.m. | 320.82 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49281.82 | n.m.
962 | 180 | DR19K06D0 | Breaker Repl - Bellefonte | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 48563.4 | 48563.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 48563.4 | n.m. | 48563.4 | n.m.
963 | 180 | DP14K02C1 | Sprigg-Beaver Creek-Tower Rplc | 10/1/2018 | Charges Continued After Dec 2019 |  |  |  | 756 | 46430.2 | 47186.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 756 | n.m. | 46430.2 | n.m. | 47186.2 | n.m.
964 | 180 | KEPCS1601 | KPCo Storm - Transmission | 6/1/2016 | 12/1/2017 |  | 45500.34 | -158.66 |  |  | 45341.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 45500.34 | n.m. | -158.66 | n.m. | 0 | n.m. | 0 | n.m. | 45341.68 | n.m.
965 | 180 | A15702023 | Leslie-2017GEUpgrade | 3/1/2017 | 1/1/2018 |  |  | 45608.68 | -623.89 |  | 44984.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 45608.68 | n.m. | -623.89 | n.m. | 0 | n.m. | 44984.79 | n.m.
966 | 180 | A15702045 | Morgan Fork 2017 GE Upgrade | 3/1/2017 | 3/1/2018 |  |  | 43873.49 | 905.38 |  | 44778.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 43873.49 | n.m. | 905.38 | n.m. | 0 | n.m. | 44778.87 | n.m.
967 | 180 | A13002023 | T/KP/Dewey-Repl 69kV CB A | Charges Began Prior to Jan 2015 | 6/1/2015 | 44354.86 |  |  |  |  | 44354.86 | 173595.292 | 0 | 0 | 0 | 0 | 173595.292 | -129240.432 | -74.45% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -129240.432 | -74.45%
968 | 180 | P17084007 | Myra 138kV Extension TLINE | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 4242.91 | 33774.11 | 4315.53 | 42332.55 | 0 | 0 | 0 | 0 | 1530205.186 | 1530205.186 | 0 | n.m. | 0 | n.m. | 4242.91 | n.m. | 33774.11 | n.m. | -1525889.656 | -99.72% | -1487872.636 | -97.23%
969 | 180 | P13121012 | TLINE work @ Chadwick: Bellfnt | 4/1/2016 | 1/1/2018 |  | 7641.28 | 34539.21 | 0.41 |  | 42180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 7641.28 | n.m. | 34539.21 | n.m. | 0.41 | n.m. | 0 | n.m. | 42180.9 | n.m.
970 | 180 | P14030013 | Wooton Relaying Work & Telecom | 9/1/2016 | Charges Continued After Dec 2019 |  | 24646.72 | 13536.55 | 1763.39 | 1863.26 | 41809.92 | 0 | 0 | 0 | 189018.805 | 165351.839 | 354370.644 | 0 | n.m. | 24646.72 | n.m. | 13536.55 | n.m. | -187255.415 | -99.07% | -163488.579 | -98.87% | -312560.724 | -88.2%
971 | 180 | A15702022 | LeeCity-2017GEUpgrade | 3/1/2017 | 2/1/2018 |  |  | 43316.55 | -1625.16 |  | 41691.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 43316.55 | n.m. | -1625.16 | n.m. | 0 | n.m. | 41691.39 | n.m.
972 | 180 | A15702019 | BigSandy138kv-2017GEUpgrade | 1/1/2017 | 1/1/2018 |  |  | 37336.5 | 614.12 |  | 37950.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 37336.5 | n.m. | 614.12 | n.m. | 0 | n.m. | 37950.62 | n.m.
973 | 180 | A15710001 | Bellefonte 138KV Tele. Moderni | 12/1/2016 | 5/1/2018 |  | 402.91 | 32901.24 | 4327.59 |  | 37631.74 | 0 | 0 | 9484.641 | 0 | 0 | 9484.641 | 0 | n.m. | 402.91 | n.m. | 23416.599 | 246.9% | 4327.59 | n.m. | 0 | n.m. | 28147.099 | 296.8%
974 | 180 | A15702020 | Dewey-2017GEUpgrade | 3/1/2017 | 6/1/2018 |  |  | 37083.12 | 16.67 |  | 37099.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 37083.12 | n.m. | 16.67 | n.m. | 0 | n.m. | 37099.79 | n.m.
975 | 180 | A13002002 | T/KP/Big Sandy-Bellefonte 138 | Charges Began Prior to Jan 2015 | 10/1/2015 | 36471.3 |  |  |  |  | 36471.3 | 0 | 0 | 0 | 0 | 0 | 0 | 36471.3 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 36471.3 | n.m.
976 | 180 | DR19K05D0 | Hazard DA 2019 - Hazard Sta | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 35353.96 | 35353.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35353.96 | n.m. | 35353.96 | n.m.
977 | 180 | A13002021 | Dewey replace failed Cap Sw. | Charges Began Prior to Jan 2015 | 5/1/2015 | 33444.21 |  |  |  |  | 33444.21 | 0 | 0 | 0 | 0 | 0 | 0 | 33444.21 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33444.21 | n.m.
978 | 180 | A18730012 | S Neal - Leach: Hdware & Gnd | 4/1/2018 | 2/1/2019 |  |  |  | 29422.26 | 2735.82 | 32158.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 29422.26 | n.m. | 2735.82 | n.m. | 32158.08 | n.m.
979 | 180 | P16116003 | Stinnett - Pineville ROW KPCo | 11/1/2016 | Charges Continued After Dec 2019 |  | 277.58 | 18889.46 | 12427.87 | 498.93 | 32093.84 | 0 | 0 | 0 | 0 | 6546.732 | 6546.732 | 0 | n.m. | 277.58 | n.m. | 18889.46 | n.m. | 12427.87 | n.m. | -6047.802 | -92.38% | 25547.108 | 390.2%
980 | 180 | P11028011 | TAPROWLine work at Elkhorn | Charges Began Prior to Jan 2015 | 6/1/2017 | 17852 | 10895.85 | 1993.91 |  |  | 30741.76 | 8283.101 | 5007.391 | 0 | 0 | 0 | 13290.492 | 9568.899 | 115.5% | 5888.459 | 117.6% | 1993.91 | n.m. | 0 | n.m. | 0 | n.m. | 17451.268 | 131.3%
981 | 180 | A15710036 | Hays Branch TTMP | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 129.1 | 20639.75 | 9390.32 | 30159.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 129.1 | n.m. | 20639.75 | n.m. | 9390.32 | n.m. | 30159.17 | n.m.
982 | 180 | A15702018 | BetsyLayne-2017GEUpgrade | 2/1/2017 | 1/1/2018 |  |  | 29258.01 | 481.24 |  | 29739.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 29258.01 | n.m. | 481.24 | n.m. | 0 | n.m. | 29739.25 | n.m.
983 | 180 | B180KYCSV | T/KY/Customer Service | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 29394.28 | 29394.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 29394.28 | n.m. | 29394.28 | n.m.
984 | 180 | P13121007 | England Hill Removal (KPCo) | 3/1/2016 | 10/1/2017 |  | 26312.81 | 2925.15 |  |  | 29237.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 26312.81 | n.m. | 2925.15 | n.m. | 0 | n.m. | 0 | n.m. | 29237.96 | n.m.
985 | 180 | A18730004 | Hazard-Fleming Str. Replc ROW | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 14049.67 | 1863.65 | 12801.85 | 28715.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 14049.67 | n.m. | 1863.65 | n.m. | 12801.85 | n.m. | 28715.17 | n.m.
986 | 180 | A13002001 | T/KP/Bellefonte Extension (KP) | Charges Began Prior to Jan 2015 | 7/1/2015 | 28446.88 |  |  |  |  | 28446.88 | 0 | 0 | 0 | 0 | 0 | 0 | 28446.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28446.88 | n.m.
987 | 180 | A18502002 | Baker 765 Firewall Install | 12/1/2018 | 8/1/2019 |  |  |  | 2107.25 | 26217.54 | 28324.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2107.25 | n.m. | 26217.54 | n.m. | 28324.79 | n.m.
988 | 180 | P17225017 | Bellefonte - Coalton 138 kV TL | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 18958.87 | 6147.35 | 1708.24 | 26814.46 | 0 | 0 | 0 | 0 | 849719.823 | 849719.823 | 0 | n.m. | 0 | n.m. | 18958.87 | n.m. | 6147.35 | n.m. | -848011.583 | -99.8% | -822905.363 | -96.84%
989 | 180 | A18730001 | Hazard-Bonnyman Str Replce ROW | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 11738.73 | 1702.44 | 13156.93 | 26598.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 11738.73 | n.m. | 1702.44 | n.m. | 13156.93 | n.m. | 26598.1 | n.m.
990 | 180 | DR19K06D1 | RTU Repl - Bonnyman | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 26376.5 | 26376.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 26376.5 | n.m. | 26376.5 | n.m.
991 | 180 | P18221005 | Beaver Creek - Fleming 69kV | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 25976.7 | 25976.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25976.7 | n.m. | 25976.7 | n.m.
992 | 180 | A15004001 | Jackson-Helechawa69kV-Relocate | 2/1/2015 | 10/1/2017 | 84173.63 | 20386.07 | -78700.78 |  |  | 25858.92 | 0 | 320312.29 | 0 | 0 | 0 | 320312.29 | 84173.63 | n.m. | -299926.22 | -93.64% | -78700.78 | n.m. | 0 | n.m. | 0 | n.m. | -294453.37 | -91.93%
993 | 180 | 000025230 | 2018 Gen Plt Cap Blkt - KYPC-T | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 6403.03 | 19382.74 | 25785.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6403.03 | n.m. | 19382.74 | n.m. | 25785.77 | n.m.
994 | 180 | P13064020 | T/KP/Hazard - Jackson 69kV ROW | 5/1/2017 | Charges Continued After Dec 2019 |  |  | 3400 | 12940.82 | 9400.05 | 25740.87 | 0 | 126888.19 | 0 | 38740.942 | 606.179 | 166235.311 | 0 | n.m. | -126888.19 | -100% | 3400 | n.m. | -25800.122 | -66.6% | 8793.871 | 1451% | -140494.441 | -84.52%
995 | 180 | A18730005 | Daisy - Clover Fork ROW | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 12599.11 | 999.85 | 11865.28 | 25464.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 12599.11 | n.m. | 999.85 | n.m. | 11865.28 | n.m. | 25464.24 | n.m.
996 | 180 | A13002008 | T/KY/Clinch River - Beaver Cre | Charges Began Prior to Jan 2015 | 5/1/2016 | 23458.18 | 566.55 |  |  |  | 24024.73 | 0 | 0 | 0 | 0 | 0 | 0 | 23458.18 | n.m. | 566.55 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24024.73 | n.m.
997 | 180 | A20705052 | Coleman - Stone 69kV Pre Eng | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 24020.59 | 24020.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24020.59 | n.m. | 24020.59 | n.m.
998 | 180 | P17110002 | Bellefonte - Grangston Cut in | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 943.14 | 12603.7 | 8658.6 | 22205.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 943.14 | n.m. | 12603.7 | n.m. | 8658.6 | n.m. | 22205.44 | n.m.
999 | 180 | A15702044 | INEZ 2017 GE Upgrade | 3/1/2017 | 6/1/2018 |  |  | 22152.45 | -231.66 |  | 21920.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 22152.45 | n.m. | -231.66 | n.m. | 0 | n.m. | 21920.79 | n.m.
1000 | 180 | P11161001 | T/KY/Betsy Layne: Retirement | 10/1/2018 | 1/1/2019 |  |  |  | 21780.93 | 21.14 | 21802.07 | 82661.74 | 0 | 812382.663 | 0.026 | 0 | 895044.429 | -82661.74 | -100% | 0 | n.m. | -812382.663 | -100% | 21780.904 | 83772708% | 21.14 | n.m. | -873242.359 | -97.56%
1001 | 180 | A15702021 | Fleming-2017GEUpgrade | 3/1/2017 | 1/1/2018 |  |  | 22095.85 | -431.08 |  | 21664.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 22095.85 | n.m. | -431.08 | n.m. | 0 | n.m. | 21664.77 | n.m.
1002 | 180 | A15702025 | Baker 765 kV PK Removals | 11/1/2016 | 7/1/2019 |  | 2179.81 | 7795.22 | 2665.67 | 8774.67 | 21415.37 | 0 | 0 | 0 | 1268820.755 | 0 | 1268820.755 | 0 | n.m. | 2179.81 | n.m. | 7795.22 | n.m. | -1266155.085 | -99.79% | 8774.67 | n.m. | -1247405.385 | -98.31%
1003 | 180 | A15710022 | Morgan Fork TTMP | 1/1/2017 | Charges Continued After Dec 2019 |  |  | 1330.87 | 9983.9 | 9731.57 | 21046.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1330.87 | n.m. | 9983.9 | n.m. | 9731.57 | n.m. | 21046.34 | n.m.
1004 | 180 | A20705037 | Big Sandy - Thelma Pre Eng | 8/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 20945.85 | 20945.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20945.85 | n.m. | 20945.85 | n.m.
1005 | 180 | A15702015 | MorganCounty-2017GEUpgrade | 3/1/2017 | 1/1/2018 |  |  | 19934.44 | 327.24 |  | 20261.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 19934.44 | n.m. | 327.24 | n.m. | 0 | n.m. | 20261.68 | n.m.
1006 | 180 | P17084019 | Elwood - Cedar Cr. Reconfig. | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 5529.38 | 12573.1 | 1680.75 | 19783.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 5529.38 | n.m. | 12573.1 | n.m. | 1680.75 | n.m. | 19783.23 | n.m.
1007 | 180 | A13002017 | T/KP/BigSandy-Thelma-SagStudy | Charges Began Prior to Jan 2015 | 1/1/2016 | 19763.32 | 0.93 |  |  |  | 19764.25 | 0 | 0 | 0 | 0 | 0 | 0 | 19763.32 | n.m. | 0.93 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19764.25 | n.m.
1008 | 180 | P18025013 | Sprigg - Beaver Cr. TLINE Work | 6/1/2018 | Charges Continued After Dec 2019 |  |  |  | 12715.99 | 7004.4 | 19720.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12715.99 | n.m. | 7004.4 | n.m. | 19720.39 | n.m.
1009 | 180 | P19104010 | Bellefonte Ext (KY) Line work | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 19091.71 | 19091.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19091.71 | n.m. | 19091.71 | n.m.
1010 | 180 | A15710037 | Leon TTMP | 12/1/2017 | 11/1/2019 |  |  | 119 | 564.19 | 17862.24 | 18545.43 | 0 | 0 | 0 | 0 | 36781.25 | 36781.25 | 0 | n.m. | 0 | n.m. | 119 | n.m. | 564.19 | n.m. | -18919.01 | -51.44% | -18235.82 | -49.58%
1011 | 180 | P17084036 | DO NOT USE | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 11927.72 | 5017.52 | 790.4 | 17735.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 11927.72 | n.m. | 5017.52 | n.m. | 790.4 | n.m. | 17735.64 | n.m.
1012 | 180 | P17076005 | Prestonsburg - Thelma 69kV | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 4589.49 | 10949.16 | 1785.54 | 17324.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 4589.49 | n.m. | 10949.16 | n.m. | 1785.54 | n.m. | 17324.19 | n.m.
1013 | 180 | P17110005 | Chadwick - Leach Relocation | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 1712.08 | 9126.53 | 6289.94 | 17128.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1712.08 | n.m. | 9126.53 | n.m. | 6289.94 | n.m. | 17128.55 | n.m.
1014 | 180 | A20705028 | Sprigg-Barrenshe 69kV Pre Eng | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 16952.39 | 16952.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16952.39 | n.m. | 16952.39 | n.m.
1015 | 180 | P17084037 | Beaver Creek Remote End | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 11865.98 | 3958.39 | 738.1 | 16562.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 11865.98 | n.m. | 3958.39 | n.m. | 738.1 | n.m. | 16562.47 | n.m.
1016 | 180 | P14030103 | Leslie - Stinnett TL to KPCo | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 15010.1 | 693.21 | 732.48 | 16435.79 | 0 | 0 | 0 | 0 | 951378.753 | 951378.753 | 0 | n.m. | 0 | n.m. | 15010.1 | n.m. | 693.21 | n.m. | -950646.273 | -99.92% | -934942.963 | -98.27%
1017 | 180 | A18702003 | Leach RE Work | 5/1/2018 | 10/1/2018 |  |  |  | 16387.34 |  | 16387.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16387.34 | n.m. | 0 | n.m. | 16387.34 | n.m.
1018 | 180 | TA1807311 | T/KPCO/SEL GE Relay | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 15656.27 | 15656.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15656.27 | n.m. | 15656.27 | n.m.
1019 | 180 | A17016001 | T/KY/Hazard-Jackson69kv:Reloc | 10/1/2017 | 2/1/2019 |  |  | 29048.99 | 73200.01 | -86747.85 | 15501.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 29048.99 | n.m. | 73200.01 | n.m. | -86747.85 | n.m. | 15501.15 | n.m.
1020 | 180 | A13002020 | T/KP/BeaverCrk-BetsyLan-Struct | Charges Began Prior to Jan 2015 | 8/1/2016 | 26260.19 | -10787.71 |  |  |  | 15472.48 | 0 | 0 | 0 | 0 | 0 | 0 | 26260.19 | n.m. | -10787.71 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15472.48 | n.m.
1021 | 180 | P18025007 | Cedar Creek Remote End | 5/1/2018 | Charges Continued After Dec 2019 |  |  |  | 11429.84 | 3974.25 | 15404.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11429.84 | n.m. | 3974.25 | n.m. | 15404.09 | n.m.
1022 | 180 | B180KYRMB | Reimbursable-DOP-180 Kentucky | 7/1/2019 | 9/1/2019 |  |  |  |  | 15117.27 | 15117.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15117.27 | n.m. | 15117.27 | n.m.
1023 | 180 | TP0921003 | T/KyPCO/Trans two 69kV Structu | Charges Began Prior to Jan 2015 | 11/1/2015 | 15066.18 |  |  |  |  | 15066.18 | 0 | 0 | 0 | 0 | 0 | 0 | 15066.18 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15066.18 | n.m.
1024 | 180 | A15004002 | T/KP/Jackson-Helechawa-ROW | 1/1/2017 | 8/1/2017 |  |  | 14924.37 |  |  | 14924.37 | 0 | 102226.884 | 11408.448 | 0 | 0 | 113635.332 | 0 | n.m. | -102226.884 | -100% | 3515.922 | 30.82% | 0 | n.m. | 0 | n.m. | -98710.962 | -86.87%
1025 | 180 | A15702061 | Johnscreek-2018Geupgrade | 1/1/2018 | 12/1/2018 |  |  |  | 14295.31 |  | 14295.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14295.31 | n.m. | 0 | n.m. | 14295.31 | n.m.
1026 | 180 | O15EST025 | SCADA - SERVERS - KPCO | 8/1/2014 | 1/1/2016 | 14199.82 | 87.23 |  |  |  | 14287.05 | 32457.159 | 0 | 0 | 0 | 0 | 32457.159 | -18257.339 | -56.25% | 87.23 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -18170.109 | -55.98%
1027 | 180 | P17225016 | East Park - Princess 138kV ROW | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 5867.33 | 7679.82 | 207.29 | 13754.44 | 0 | 0 | 0 | 0 | 463063.138 | 463063.138 | 0 | n.m. | 0 | n.m. | 5867.33 | n.m. | 7679.82 | n.m. | -462855.848 | -99.96% | -449308.698 | -97.03%
1028 | 180 | A20705029 | Barrenshe-Coleman Pre Eng | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 13276.96 | 13276.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13276.96 | n.m. | 13276.96 | n.m.
1029 | 180 | P14030104 | Leslie Ext Install to KPCo | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 9810.21 | 453.07 | 2617.29 | 12880.57 | 0 | 0 | 0 | 0 | 100859.839 | 100859.839 | 0 | n.m. | 0 | n.m. | 9810.21 | n.m. | 453.07 | n.m. | -98242.549 | -97.41% | -87979.269 | -87.23%
1030 | 180 | A17750109 | Allen-Prestonsburg Fld sliding | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 12573.39 | 12573.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12573.39 | n.m. | 12573.39 | n.m.
1031 | 180 | P19215005 | Chadwick - Leach TLINE | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 12434 | 12434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12434 | n.m. | 12434 | n.m.
1032 | 180 | P19092020 | Cancel -Dwale Extension T Line | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 12351.3 | 12351.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12351.3 | n.m. | 12351.3 | n.m.
1033 | 180 | P11028013 | TAPROWLine work at Elkhorn | Charges Began Prior to Jan 2015 | 5/1/2017 | 11569.1 | 464.45 | -209.11 |  |  | 11824.44 | 8283.101 | 676.767 | 0 | 0 | 0 | 8959.868 | 3285.999 | 39.67% | -212.317 | -31.37% | -209.11 | n.m. | 0 | n.m. | 0 | n.m. | 2864.572 | 31.97%
1034 | 180 | A15702057 | Fleming-2018Geupgrade | 1/1/2018 | 3/1/2019 |  |  |  | 11221.28 | 524.01 | 11745.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11221.28 | n.m. | 524.01 | n.m. | 11745.29 | n.m.
1035 | 180 | P17225018 | Bellefonte - Coalton 138kV ROW | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 5867.45 | 5431.12 | 172.88 | 11471.45 | 0 | 0 | 0 | 0 | 3457360.241 | 3457360.241 | 0 | n.m. | 0 | n.m. | 5867.45 | n.m. | 5431.12 | n.m. | -3457187.361 | -99.99% | -3445888.791 | -99.67%
1036 | 180 | P17225014 | Ramey 138 kV Extension ROW | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 5867.45 | 5373.62 | 172 | 11413.07 | 0 | 0 | 0 | 0 | 463063.138 | 463063.138 | 0 | n.m. | 0 | n.m. | 5867.45 | n.m. | 5373.62 | n.m. | -462891.138 | -99.96% | -451650.068 | -97.54%
1037 | 180 | P18221002 | Dorton - Fleming 138kV | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 10913.72 | 10913.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10913.72 | n.m. | 10913.72 | n.m.
1038 | 180 | A19750104 | Daisy-Cloverfork Failure | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 10840.75 | 10840.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10840.75 | n.m. | 10840.75 | n.m.
1039 | 180 | P12190003 | T KP Salt Lick Station Replac | Charges Began Prior to Jan 2015 | 4/1/2015 | 10552.74 |  |  |  |  | 10552.74 | 0 | 0 | 0 | 0 | 0 | 0 | 10552.74 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10552.74 | n.m.
1040 | 180 | P17083003 | Garrett Switch (Removal) | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 10549.74 | 10549.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10549.74 | n.m. | 10549.74 | n.m.
1041 | 180 | A20705035 | Middle Creek-Falcon 46kV Remvl | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 10380.62 | 10380.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10380.62 | n.m. | 10380.62 | n.m.
1042 | 180 | P14030002 | Stinnett Loop Install OPGW | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 8037.16 | 1452.67 | 442.63 | 9932.46 | 0 | 0 | 0 | 20967.305 | 16481.024 | 37448.329 | 0 | n.m. | 0 | n.m. | 8037.16 | n.m. | -19514.635 | -93.07% | -16038.394 | -97.31% | -27515.869 | -73.48%
1043 | 180 | 000025076 | Pikeville Transmission SC | 6/1/2017 | Charges Continued After Dec 2019 |  |  | 2157727.88 | -225829.77 | -1922035.03 | 9863.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2157727.88 | n.m. | -225829.77 | n.m. | -1922035.03 | n.m. | 9863.08 | n.m.
1044 | 180 | A21212002 | Bellefonte 34kV - RTU Replacem | 6/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 9441.19 | 9441.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9441.19 | n.m. | 9441.19 | n.m.
1045 | 180 | A20705082 | Bellefonte138kV&69kV Needs Asm | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 9363.66 | 9363.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9363.66 | n.m. | 9363.66 | n.m.
1046 | 180 | P17110007 | Chadwick - Tri State #2 Reloca | 2/1/2018 | Charges Continued After Dec 2019 |  |  |  | 5058.04 | 4284.06 | 9342.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5058.04 | n.m. | 4284.06 | n.m. | 9342.1 | n.m.
1047 | 180 | A20705083 | Bellefonte 34.5kV St Needs Asm | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 9234.02 | 9234.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9234.02 | n.m. | 9234.02 | n.m.
1048 | 180 | A17750107 | Prestonsburg-Thelma69kVSlidROW | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 9198.34 | 9198.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9198.34 | n.m. | 9198.34 | n.m.
1049 | 180 | P17110006 | Chadwick - Tri State #1 Reloca | 7/1/2018 | Charges Continued After Dec 2019 |  |  |  | 2935.16 | 5917.58 | 8852.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2935.16 | n.m. | 5917.58 | n.m. | 8852.74 | n.m.
1050 | 180 | P19092007 | Allen -East Prestonsburg TLINE | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 8048.73 | 8048.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8048.73 | n.m. | 8048.73 | n.m.
1051 | 180 | P17084017 | Beaver Creek - Fremont Cut in | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 4290.49 | 3222.55 | 350.44 | 7863.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 4290.49 | n.m. | 3222.55 | n.m. | 350.44 | n.m. | 7863.48 | n.m.
1052 | 180 | A19750101 | B Sandy - Broadf 765 Slide ROW | 6/1/2019 | 12/1/2019 |  |  |  |  | 7780.32 | 7780.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7780.32 | n.m. | 7780.32 | n.m.
1053 | 180 | P16113004 | Cannonsburg-SNeal KY Remove | 12/1/2016 | Charges Continued After Dec 2019 |  | 900.27 | 746.33 | 2766.67 | 3221.92 | 7635.19 | 0 | 0 | 0 | -1.722 | 0 | -1.722 | 0 | n.m. | 900.27 | n.m. | 746.33 | n.m. | 2768.392 | -160766% | 3221.92 | n.m. | 7636.912 | -443491%
1054 | 180 | P19092013 | Allen - Prestonsburg TLINE | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 7132.98 | 7132.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7132.98 | n.m. | 7132.98 | n.m.
1055 | 180 | A20705036 | Middle Creek-Prestonsburg Rebu | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6943.39 | 6943.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6943.39 | n.m. | 6943.39 | n.m.
1056 | 180 | P17084022 | Henry Clay - Dorton Reconfig. | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 3040.9 | 1270.34 | 2432.88 | 6744.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 3040.9 | n.m. | 1270.34 | n.m. | 2432.88 | n.m. | 6744.12 | n.m.
1057 | 180 | P19092021 | Cancel - Dwale Extension ROW | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6738.62 | 6738.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6738.62 | n.m. | 6738.62 | n.m.
1058 | 180 | O18EST033 | SCADA - SERVERS - KPCO | 10/1/2018 | 1/1/2019 |  |  |  | 6389.51 | 154.74 | 6544.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6389.51 | n.m. | 154.74 | n.m. | 6544.25 | n.m.
1059 | 180 | P19092019 | Allen - Prestonsburg ROW | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6503.47 | 6503.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6503.47 | n.m. | 6503.47 | n.m.
1060 | 180 | A17016002 | T/KY/Hazard-Jkson69kv:RelocROW | 11/1/2017 | 3/1/2019 |  |  | 22266.79 | 73809.07 | -89640.16 | 6435.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 22266.79 | n.m. | 73809.07 | n.m. | -89640.16 | n.m. | 6435.7 | n.m.
1061 | 180 | P18025008 | Beaver Creek Remote End Work | 5/1/2018 | Charges Continued After Dec 2019 |  |  |  | 5985.62 | 279.21 | 6264.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5985.62 | n.m. | 279.21 | n.m. | 6264.83 | n.m.
1062 | 180 | P19215004 | Chadwick - England Hill ROW | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6145 | 6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6145 | n.m. | 6145 | n.m.
1063 | 180 | A15702056 | Topmost SS Failure | 8/1/2017 | Charges Continued After Dec 2019 |  |  | 66569.52 | -84483.3 | 24033.04 | 6119.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 66569.52 | n.m. | -84483.3 | n.m. | 24033.04 | n.m. | 6119.26 | n.m.
1064 | 180 | A15710050 | 2BCXLD Pikesville SC-Johns Cr | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6000 | n.m. | 6000 | n.m.
1065 | 180 | P17083005 | Hays Branch S.S | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5860.03 | 5860.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5860.03 | n.m. | 5860.03 | n.m.
1066 | 180 | A20705073 | Sprigg-StoneKP 46kV KY | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5818.65 | 5818.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5818.65 | n.m. | 5818.65 | n.m.
1067 | 180 | P18221003 | Hazard - Fleming 69kV | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5365.09 | 5365.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5365.09 | n.m. | 5365.09 | n.m.
1068 | 180 | P19215006 | Chadwick - Leach ROW | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 5355 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5355 | n.m. | 5355 | n.m.
1069 | 180 | A15710044 | 2 BCXLD Beckham - Vicco TelMod | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4775.02 | 4775.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4775.02 | n.m. | 4775.02 | n.m.
1070 | 180 | P19092011 | McKinney -Allen reconfigure | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4328.28 | 4328.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4328.28 | n.m. | 4328.28 | n.m.
1071 | 180 | P17084023 | Henry Clay - Elk. City Reconfi | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 2551.62 | 1577.5 | 192.6 | 4321.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2551.62 | n.m. | 1577.5 | n.m. | 192.6 | n.m. | 4321.72 | n.m.
1072 | 180 | P18221004 | Fleming - Fremont 69kV | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4246.65 | 4246.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4246.65 | n.m. | 4246.65 | n.m.
1073 | 180 | P19092017 | McKinney - Allen ROW | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4214.9 | 4214.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4214.9 | n.m. | 4214.9 | n.m.
1074 | 180 | A20705067 | McInness SW Needs Assessment | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 4015.7 | 4015.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4015.7 | n.m. | 4015.7 | n.m.
1075 | 180 | P19104012 | Bellefonte Ext (KY) ROW | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3995.08 | 3995.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3995.08 | n.m. | 3995.08 | n.m.
1076 | 180 | P13064001 | T/KP/Hazard-Wooton 161kV line | 4/1/2016 | 8/1/2017 |  | 5126.09 | -1146.15 |  |  | 3979.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 5126.09 | n.m. | -1146.15 | n.m. | 0 | n.m. | 0 | n.m. | 3979.94 | n.m.
1077 | 180 | A15702059 | Morganfork-2018Geupgrade | 3/1/2018 | 12/1/2018 |  |  |  | 3951.17 |  | 3951.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3951.17 | n.m. | 0 | n.m. | 3951.17 | n.m.
1078 | 180 | P18221010 | Dorton Remote End | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3802.9 | 3802.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3802.9 | n.m. | 3802.9 | n.m.
1079 | 180 | P16116002 | Stinnett - Pineville Removal | 11/1/2016 | Charges Continued After Dec 2019 |  | 366.53 | 1783.64 | 1011.72 | 556.48 | 3718.37 | 0 | 0 | 0 | 0 | 208.159 | 208.159 | 0 | n.m. | 366.53 | n.m. | 1783.64 | n.m. | 1011.72 | n.m. | 348.321 | 167.3% | 3510.211 | 1686%
1080 | 180 | P19092008 | Allen -East Prestonsburg ROW | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3708.47 | 3708.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3708.47 | n.m. | 3708.47 | n.m.
1081 | 180 | P19092012 | Betsy Layne - Allen Reconfigur | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3298.96 | 3298.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3298.96 | n.m. | 3298.96 | n.m.
1082 | 180 | P19091003 | Middle Creek- Prestonsburg | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3283.18 | 3283.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3283.18 | n.m. | 3283.18 | n.m.
1083 | 180 | A15710047 | 2BCXLD Jeff - Daisy TelModFib | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 3254.54 | 3254.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3254.54 | n.m. | 3254.54 | n.m.
1084 | 180 | P17084021 | DO NOT USE | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 2777.61 | 128.28 | 135.53 | 3041.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2777.61 | n.m. | 128.28 | n.m. | 135.53 | n.m. | 3041.42 | n.m.
1085 | 180 | P17084038 | Dorton Remote End | 11/1/2017 | Charges Continued After Dec 2019 |  |  | 5806.99 | -2927.7 | 134.31 | 3013.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 5806.99 | n.m. | -2927.7 | n.m. | 134.31 | n.m. | 3013.6 | n.m.
1086 | 180 | P19092018 | Betsy Layne - Allen ROW | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2979.9 | 2979.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2979.9 | n.m. | 2979.9 | n.m.
1087 | 180 | P17084020 | Elwood - Henry Cl. Recon. @ EL | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 2645.87 | 122.19 | 129.1 | 2897.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2645.87 | n.m. | 122.19 | n.m. | 129.1 | n.m. | 2897.16 | n.m.
1088 | 180 | P17076006 | Kenwood Extension ROW | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 1015.63 | 46.89 | 1738.4 | 2800.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1015.63 | n.m. | 46.89 | n.m. | 1738.4 | n.m. | 2800.92 | n.m.
1089 | 180 | P11028012 | TAPROWLine work at Elkhorn | 5/1/2014 | 1/1/2016 | 2795.34 | 0.46 |  |  |  | 2795.8 | 2979.533 | 2273.57 | 0 | 0 | 0 | 5253.103 | -184.193 | -6.182% | -2273.11 | -99.98% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -2457.303 | -46.78%
1090 | 180 | P18066001 | Chadwick - England Hill PQ Mit | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 2570.05 | 119.88 | 2689.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2570.05 | n.m. | 119.88 | n.m. | 2689.93 | n.m.
1091 | 180 | A15710071 | Morehead Station TTMP | 7/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2591.81 | 2591.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2591.81 | n.m. | 2591.81 | n.m.
1092 | 180 | A15710043 | 2BCXLD Topmost 138 - Beckham 1 | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2588.17 | 2588.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2588.17 | n.m. | 2588.17 | n.m.
1093 | 180 | P17084029 | New Henry Clay Extension | 10/1/2017 | Charges Continued After Dec 2019 |  |  | 1197.09 | 1217.05 | 112.59 | 2526.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1197.09 | n.m. | 1217.05 | n.m. | 112.59 | n.m. | 2526.73 | n.m.
1094 | 180 | P12190002 | T KP Salt Lick Extension New | Charges Began Prior to Jan 2015 | 4/1/2015 | 2471.41 |  |  |  |  | 2471.41 | 0 | 0 | 0 | 0 | 0 | 0 | 2471.41 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2471.41 | n.m.
1095 | 180 | P17084013 | Henry Clay S.S Retirement | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 5253.12 | -2906.76 | 109.42 | 2455.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 5253.12 | n.m. | -2906.76 | n.m. | 109.42 | n.m. | 2455.78 | n.m.
1096 | 180 | A20705057 | Big Sandy Station Pre Eng | 9/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2247.48 | 2247.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2247.48 | n.m. | 2247.48 | n.m.
1097 | 180 | P18090001 | Inez Proactive Rehab Work | 7/1/2018 | 5/1/2019 |  |  |  | 24526.39 | -22312.19 | 2214.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24526.39 | n.m. | -22312.19 | n.m. | 2214.2 | n.m.
1098 | 180 | A20705001 | Inez Station Pre-Eng | 8/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2127.29 | 2127.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2127.29 | n.m. | 2127.29 | n.m.
1099 | 180 | A15710045 | 2BCXLD Vicco - Jeff TelModFib | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 2118.37 | 2118.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2118.37 | n.m. | 2118.37 | n.m.
1100 | 180 | A15710061 | Johns Creek Station TTMP | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1983.77 | 1983.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1983.77 | n.m. | 1983.77 | n.m.
1101 | 180 | DP14K02T0 | KP/Raccoon Sta - T ROW | 10/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1175.66 | 706.82 | 1882.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1175.66 | n.m. | 706.82 | n.m. | 1882.48 | n.m.
1102 | 180 | P17084018 | Beaver Creek - Elwood Retire | 9/1/2017 | Charges Continued After Dec 2019 |  |  | 1658.6 | 76.6 | 80.91 | 1816.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1658.6 | n.m. | 76.6 | n.m. | 80.91 | n.m. | 1816.11 | n.m.
1103 | 180 | P18066003 | Kenova-Eng. Hill KY PQ Mit | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1988.55 | -425.91 | 1562.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1988.55 | n.m. | -425.91 | n.m. | 1562.64 | n.m.
1104 | 180 | A15710051 | 2BCXLD Johns Creek - Coleman T | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1500 | n.m. | 1500 | n.m.
1105 | 180 | A12102523 | T/KP/BAKER765-Spare138CBs | Charges Began Prior to Jan 2015 | 8/1/2015 | 1396.37 |  |  |  |  | 1396.37 | 0 | 0 | 0 | 0 | 0 | 0 | 1396.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1396.37 | n.m.
1106 | 180 | P18066005 | ASFI Tap PQ Mitigations | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1333.13 | 62.18 | 1395.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1333.13 | n.m. | 62.18 | n.m. | 1395.31 | n.m.
1107 | 180 | P18025012 | Cedar Creek - Elwood TLINE Wor | 9/1/2018 | Charges Continued After Dec 2019 |  |  |  | 1078.89 | 240.66 | 1319.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1078.89 | n.m. | 240.66 | n.m. | 1319.55 | n.m.
1108 | 180 | P17083034 | Morgan Fork Remote End | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1189.06 | 1189.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1189.06 | n.m. | 1189.06 | n.m.
1109 | 180 | DP16K03C0 | Tygart Sta - T line work | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 1087.28 | 1087.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1087.28 | n.m. | 1087.28 | n.m.
1110 | 180 | A15710046 | 2BCXLD Jeff - Hazard TelModFib | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 948.88 | 948.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 948.88 | n.m. | 948.88 | n.m.
1111 | 180 | P17225008 | Princess Station | 12/1/2017 | Charges Continued After Dec 2019 |  |  | 2038.28 | 35077.43 | -36215.67 | 900.04 | 0 | 0 | 0 | 0 | 626806.252 | 626806.252 | 0 | n.m. | 0 | n.m. | 2038.28 | n.m. | 35077.43 | n.m. | -663021.922 | -105.8% | -625906.212 | -99.86%
1112 | 180 | A15710064 | 2BCXLD Sprigg-Cinderella KY Te | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 895.36 | 895.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 895.36 | n.m. | 895.36 | n.m.
1113 | 180 | P17076010 | Van Lear - Kenwood Str Replace | 6/1/2018 | Charges Continued After Dec 2019 |  |  |  | 42.46 | 830.67 | 873.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 42.46 | n.m. | 830.67 | n.m. | 873.13 | n.m.
1114 | 180 | P17083008 | Hays Br. - Morgan Frk. 138 TLN | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 834.47 | 834.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 834.47 | n.m. | 834.47 | n.m.
1115 | 180 | P14030101 | Leslie - Clover Fork Line Work | 3/1/2017 | Charges Continued After Dec 2019 |  |  | 644.16 | 29.74 | 31.44 | 705.34 | 0 | 0 | 0 | 0 | 23659.511 | 23659.511 | 0 | n.m. | 0 | n.m. | 644.16 | n.m. | 29.74 | n.m. | -23628.071 | -99.87% | -22954.171 | -97.02%
1116 | 180 | A15710052 | 2BCXLD Falcon - West Paintsvil | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 700 | n.m. | 700 | n.m.
1117 | 180 | P17083006 | Garrett - Eastern 138 TLN | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 667.8 | 667.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 667.8 | n.m. | 667.8 | n.m.
1118 | 180 | DP16K03C1 | Tygart Sta - T line work | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 663.94 | 663.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 663.94 | n.m. | 663.94 | n.m.
1119 | 180 | A15710042 | 2BCXL Topmost 138 TelModFib | 4/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 650.61 | 650.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 650.61 | n.m. | 650.61 | n.m.
1120 | 180 | P14030016 | Leslie - Stinnett ROW (KPCo) | 11/1/2016 | Charges Continued After Dec 2019 |  | 111.62 | 270.87 | 119.15 | 7.68 | 509.32 | 0 | 0 | 0 | 0 | 566590.384 | 566590.384 | 0 | n.m. | 111.62 | n.m. | 270.87 | n.m. | 119.15 | n.m. | -566582.704 | -100% | -566081.064 | -99.91%
1121 | 180 | A15702062 | Morehead Station: Stn Entrnce | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 482.37 | 482.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 482.37 | n.m. | 482.37 | n.m.
1122 | 180 | A13002018 | ROW Hanging Rock - Jefferson ( | Charges Began Prior to Jan 2015 | 3/1/2015 | 471.48 |  |  |  |  | 471.48 | 0 | 0 | 0 | 0 | 0 | 0 | 471.48 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 471.48 | n.m.
1123 | 180 | P18221014 | Fleming (Jackhorn) 138KV ADSS | 10/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 413.9 | 413.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 413.9 | n.m. | 413.9 | n.m.
1124 | 180 | P18001001 | South Neal - Leach KPCo PQ | 2/1/2018 | 2/1/2019 |  |  |  | 802.96 | -407.46 | 395.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 802.96 | n.m. | -407.46 | n.m. | 395.5 | n.m.
1125 | 180 | P18066002 | Chadwick-Leach PQ Mit | 4/1/2018 | Charges Continued After Dec 2019 |  |  |  | 343.77 | 16.03 | 359.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 343.77 | n.m. | 16.03 | n.m. | 359.8 | n.m.
1126 | 180 | A20705079 | McInnessMet69kV Needs Asm | 11/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 303.48 | 303.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 303.48 | n.m. | 303.48 | n.m.
1127 | 180 | A15702031 | CHECKBOOK BPID- NO WO'S | 5/1/2017 | 5/1/2017 |  |  | 254.26 |  |  | 254.26 | 0 | 0 | 0 | 23666226.116 | 0 | 23666226.116 | 0 | n.m. | 0 | n.m. | 254.26 | n.m. | -23666226.116 | -100% | 0 | n.m. | -23665971.856 | -100%
1128 | 180 | P17083026 | Hays Br-Soft Shell Trans Fiber | 3/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 201.27 | 201.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 201.27 | n.m. | 201.27 | n.m.
1129 | 180 | P14030015 | Lesile - Stinnett Removal | 11/1/2016 | Charges Continued After Dec 2019 |  | 304.26 | -393.13 | 247.37 | 10.35 | 168.85 | 0 | 0 | 0 | 0 | 20112.967 | 20112.967 | 0 | n.m. | 304.26 | n.m. | -393.13 | n.m. | 247.37 | n.m. | -20102.617 | -99.95% | -19944.117 | -99.16%
1130 | 180 | P19091004 | Middle Creek- Prestonsburg ROW | 12/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 133.9 | 133.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 133.9 | n.m. | 133.9 | n.m.
1131 | 180 | P18025010 | Kewanee Fiber Termination | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 72.48 | 72.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 72.48 | n.m. | 72.48 | n.m.
1132 | 180 | P18025009 | Cedar Creek Fiber Extension | 5/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 72.48 | 72.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 72.48 | n.m. | 72.48 | n.m.
1133 | 180 | P17074009 | CANCEL-Millbrook Frost TL KPCo | 9/1/2017 | 2/1/2019 |  |  | 56592.11 | -56592.11 | 71.25 | 71.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 56592.11 | n.m. | -56592.11 | n.m. | 71.25 | n.m. | 71.25 | n.m.
1134 | 180 | A15702049 | Cancel | 3/1/2018 | Charges Continued After Dec 2019 |  |  |  | 43902.9 | -43844.3 | 58.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 43902.9 | n.m. | -43844.3 | n.m. | 58.6 | n.m.
1135 | 180 | KYCR012TS | KP/VoltVar Circ Reconfig TSta | Charges Began Prior to Jan 2015 | 5/1/2015 | 39.35 |  |  |  |  | 39.35 | 0 | 0 | 0 | 0 | 0 | 0 | 39.35 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 39.35 | n.m.
1136 | 180 | A16928015 | Leslie Station Spare Purchase | 1/1/2019 | Charges Continued After Dec 2019 |  |  |  |  | 31.46 | 31.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 31.46 | n.m. | 31.46 | n.m.
1137 | 180 | ETNANDA | Transmission Anda | 1/1/2016 | 1/1/2016 |  | 19.12 |  |  |  | 19.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 19.12 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19.12 | n.m.
1138 | 180 | TP1004101 | TL KYPCO Fleming to Jenkins | Charges Began Prior to Jan 2015 | 1/1/2015 | 1.24 |  |  |  |  | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1.24 | n.m.
1139 | 180 | ETN000180 | T Kp T Anda | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | 0.002 | -2.4884e-09 | 0.09 | -6.5972e-10 | 7.064e-09 | 0.092 | 0.003 | 0 | 0 | 0 | 0 | 0.003 | -0.001 | -33.33% | -2.4884e-09 | n.m. | 0.09 | n.m. | -6.5972e-10 | n.m. | 7.064e-09 | n.m. | 0.089 | 2967%
1140 | 180 | A13212020 | T/KP/Dorton - Telecom Legacy C | Charges Began Prior to Jan 2015 | 1/1/2015 | 0.01 |  |  |  |  | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0.01 | n.m.
1141 | 180 | A15702042 | Fleming XF/CB Replacements | 5/1/2017 | 11/1/2019 |  |  | 29914.55 | 236062.7 | -265977.25 | 0 | 0 | 0 | 0 | 952036.629 | 92501.93 | 1044538.559 | 0 | n.m. | 0 | n.m. | 29914.55 | n.m. | -715973.929 | -75.2% | -358479.18 | -387.5% | -1044538.559 | -100%
1142 | 180 | A15702039 | CANCELLED | 5/1/2017 | 3/1/2018 |  |  | 34645.08 | -34645.08 |  | 0 | 0 | 0 | 0 | 281690.578 | 0 | 281690.578 | 0 | n.m. | 0 | n.m. | 34645.08 | n.m. | -316335.658 | -112.3% | 0 | n.m. | -281690.578 | -100%
1143 | 180 | P17074001 | CANCEL-Frost Station | 9/1/2017 | 12/1/2018 |  |  | 27468.64 | -27468.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 27468.64 | n.m. | -27468.64 | n.m. | 0 | n.m. | 0 | n.m.
1144 | 180 | A18730007 | CANCELLED | 8/1/2017 | 3/1/2018 |  |  | 13147.1 | -13147.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 13147.1 | n.m. | -13147.1 | n.m. | 0 | n.m. | 0 | n.m.
1145 | 180 | P17074010 | CANCELMillbrook Frost ROW KPCo | 9/1/2017 | 12/1/2018 |  |  | 568.37 | -568.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 568.37 | n.m. | -568.37 | n.m. | 0 | n.m. | 0 | n.m.
1146 | 180 | A15702038 | CANCELLED | 5/1/2017 | 1/1/2019 |  |  | -4.46 |  | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | -4.46 | n.m. | 0 | n.m. | 4.46 | n.m. | 0 | n.m.
1147 | 180 | A15710048 | 2BCXLD Pikeville SC extension | 4/1/2019 | 11/1/2019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m.
1148 | 180 | P17074005 | Millbrook - Siloam Cut in | 9/1/2017 | 12/1/2019 |  |  | 921.37 | -788.46 | -132.91 | -2.8422e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 921.37 | n.m. | -788.46 | n.m. | -132.91 | n.m. | -2.8422e-13 | n.m.
1149 | 180 | A15702040 | CANCELLED | 5/1/2017 | 5/1/2019 |  |  | 5747.48 | -5496.74 | -250.74 | -8.5265e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 5747.48 | n.m. | -5496.74 | n.m. | -250.74 | n.m. | -8.5265e-13 | n.m.
1150 | 180 | A18730006 | CANCELLED | 8/1/2017 | 3/1/2018 |  |  | 18757.84 | -18757.84 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 18757.84 | n.m. | -18757.84 | n.m. | 0 | n.m. | 0 | n.m.
1151 | 180 | P12088004 | Bellefonte 69 BUS TIE REMOVE | 4/1/2016 | 5/1/2018 |  | 1604.27 | 6414.61 | -8018.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1604.27 | n.m. | 6414.61 | n.m. | -8018.88 | n.m. | 0 | n.m. | 0 | n.m.
1152 | 180 | A15702037 | CANCELLED | 5/1/2017 | 5/1/2018 |  |  | 45046.03 | -45046.03 |  | 0 | 0 | 0 | 0 | 472097.904 | 0 | 472097.904 | 0 | n.m. | 0 | n.m. | 45046.03 | n.m. | -517143.934 | -109.5% | 0 | n.m. | -472097.904 | -100%
1153 | 180 | A15702043 | Beaver Creek CB AB replace | 5/1/2017 | 11/1/2019 |  |  | 22489.95 | 51476.16 | -73966.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 22489.95 | n.m. | 51476.16 | n.m. | -73966.11 | n.m. | 0 | n.m.
1154 | 180 | P17083009 | Hays Br. Morgan Frk. 138 ROW | 3/1/2019 | 3/1/2019 |  |  |  |  | -393.38 | -393.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -393.38 | n.m. | -393.38 | n.m.
1155 | 180 | TP0921004 | TL/KYPCo/Beaver Creek-Hazard S | Charges Began Prior to Jan 2015 | 4/1/2015 | -1765.04 |  |  |  |  | -1765.04 | 0 | 0 | 0 | 0 | 0 | 0 | -1765.04 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1765.04 | n.m.
1156 | 180 | P13117015 | Slemp Extension ROW | 10/1/2014 | 6/1/2017 |  | 13.48 | -2208.11 |  |  | -2194.63 | 67198.375 | 0 | 0 | 0 | 0 | 67198.375 | -67198.375 | -100% | 13.48 | n.m. | -2208.11 | n.m. | 0 | n.m. | 0 | n.m. | -69393.005 | -103.3%
1157 | 180 | P13117013 | Blair Fork S.S Retirement | Charges Began Prior to Jan 2015 | 7/1/2017 | 35.3 | 89.89 | -2606.4 |  |  | -2481.21 | 16268.243 | 0 | 0 | 0 | 0 | 16268.243 | -16232.943 | -99.78% | 89.89 | n.m. | -2606.4 | n.m. | 0 | n.m. | 0 | n.m. | -18749.453 | -115.3%
1158 | 180 | DP11K03C0 | KPJeff Station - 69kv install | Charges Began Prior to Jan 2015 | 6/1/2015 | -2573.84 |  |  |  |  | -2573.84 | 0 | 0 | 0 | 0 | 0 | 0 | -2573.84 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -2573.84 | n.m.
1159 | 180 | P10115004 | Canceled | Charges Began Prior to Jan 2015 | 12/1/2019 | 963.39 | 44.15 | 6618.96 | 2349.12 | -16199.45 | -6223.83 | 0 | 0 | 0 | 0 | 0 | 0 | 963.39 | n.m. | 44.15 | n.m. | 6618.96 | n.m. | 2349.12 | n.m. | -16199.45 | n.m. | -6223.83 | n.m.
1160 | 180 | P13117014 | Slemp Extension | Charges Began Prior to Jan 2015 | 7/1/2017 | 788.2 | 327.82 | -9506.88 |  |  | -8390.86 | 82764.644 | 0 | 0 | -0.848 | 0 | 82763.796 | -81976.444 | -99.05% | 327.82 | n.m. | -9506.88 | n.m. | 0.848 | -100% | 0 | n.m. | -91154.656 | -110.1%
1161 | 180 | SI180KYRL | TB SI KyP - KENTUCKY SERV RELI | Charges Began Prior to Jan 2015 | 9/1/2015 | -23249.35 |  |  |  |  | -23249.35 | 0 | 0 | 0 | 0 | 0 | 0 | -23249.35 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -23249.35 | n.m.
1162 | 180 | P11028004 | CANCELLED | Charges Began Prior to Jan 2015 | 7/1/2018 | -12953.08 |  |  | -63462.89 |  | -76415.97 | 0 | 0 | 0 | 0 | 0 | 0 | -12953.08 | n.m. | 0 | n.m. | 0 | n.m. | -63462.89 | n.m. | 0 | n.m. | -76415.97 | n.m.
1163 | 180 | 000017437 | TLKYPHazard-Pineville 161kV | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2019 | -274388.04 | 243.85 | 2.69 | 6.87 | 7.91 | -274126.72 | 0 | 0 | 0 | 0 | 0 | 0 | -274388.04 | n.m. | 243.85 | n.m. | 2.69 | n.m. | 6.87 | n.m. | 7.91 | n.m. | -274126.72 | n.m.
1164 | 180 | TA1210104 | T/KYPCO/Line Rehab/Replace | Charges Began Prior to Jan 2015 | 1/1/2017 | -1604969.08 | 2186.83 | -2941.4 |  |  | -1605723.65 | 0 | 0 | 0 | 0 | 0 | 0 | -1604969.08 | n.m. | 2186.83 | n.m. | -2941.4 | n.m. | 0 | n.m. | 0 | n.m. | -1605723.65 | n.m.
1165 | 180 | Other Budgeted Projects |  | Other | Other | 0 | 0 | 0 | 0 | 0 | 0 | 4338824.27 | 12338978.57 | 6321935.383 | 23447095.097 | 14896229.338 | 61343062.658 | -4338824.27 | -100% | -12338978.57 | -100% | -6321935.383 | -100% | -23447095.097 | -100% | -14896229.338 | -100% | -61343062.658 | -100%
1166 | 180 Total |  |  |  |  | 14284691.262 | 11077191.96 | 28461295.55 | 43145011.25 | 55397644.722 | 152365834.744 | 12351217.968 | 16143330.909 | 21034000.848 | 57264094.435 | 101296174.039 | 208088818.199 | 1933473.294 | 15.65% | -5066138.949 | -31.38% | 7427294.702 | 35.31% | -14119083.185 | -24.66% | -45898529.317 | -45.31% | -55722983.455 | -26.78%
1167 | Total Kentucky Power CWIP Additions |  |  |  |  | 111410407.602 | 97154400.404 | 100386925.186 | 139702471.441 | 173948013.995 | 622602218.628 | 93907111.111 | 88258049.14 | 79581314.637 | 154710340.868 | 212200995.71 | 628657811.466 | 17503296.491 | 18.64% | 8896351.264 | 10.08% | 20805610.549 | 26.14% | -15007869.427 | -9.701% | -38252981.715 | -18.03% | -6055592.838 | -0.9633%
1168
1169 | 110 | X00000317 | For Property Acctg Use Only | Property Acctg | Property Acctg | -41577205.85 | -40181940.03 | -45544126.64 | -52970703.32 | -72563908.817 | -252837884.657 | 0 | 0 | 0 | 0 | 0 | 0 | -41577205.85 | n.m. | -40181940.03 | n.m. | -45544126.64 | n.m. | -52970703.32 | n.m. | -72563908.817 | n.m. | -252837884.657 | n.m.
1170 | 117 | X00000288 | For Property Acctg Use Only | Property Acctg | Property Acctg | -36462243.01 | -79805151.19 | -19073712.78 | -22703950.39 | -37706926.57 | -195751983.94 | 0 | 0 | 0 | 0 | 0 | 0 | -36462243.01 | n.m. | -79805151.19 | n.m. | -19073712.78 | n.m. | -22703950.39 | n.m. | -37706926.57 | n.m. | -195751983.94 | n.m.
1171 | 180 | X00000306 | For Property Acctg Use Only | Property Acctg | Property Acctg | -13214425.77 | -9138516.54 | -11006882.28 | -31422001.35 | -49753622.32 | -114535448.26 | 0 | 0 | 0 | 0 | 0 | 0 | -13214425.77 | n.m. | -9138516.54 | n.m. | -11006882.28 | n.m. | -31422001.35 | n.m. | -49753622.32 | n.m. | -114535448.26 | n.m.
1172 | Total Kentucky Power Transfers to 101/106 |  |  |  |  | -91253874.63 | -129125607.76 | -75624721.7 | -107096655.06 | -160024457.707 | -563125316.857 | 0 | 0 | 0 | 0 | 0 | 0 | -91253874.63 | n.m. | -129125607.76 | n.m. | -75624721.7 | n.m. | -107096655.06 | n.m. | -160024457.707 | n.m. | -563125316.857 | n.m.
1173
1174 | Total Kentucky Power CWIP Activity by Year |  |  |  |  | 20156532.972 | -31971207.356 | 24762203.486 | 32605816.381 | 13923556.288 | 59476901.771 | 93907111.111 | 88258049.14 | 79581314.637 | 154710340.868 | 212200995.71 | 628657811.466 | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m.
1175
1176 | (1) | Represents the month project expenditures were initially recorded to CWIP (Account 107).
1177 | (2) | Represents the month project expenditures ceased being recorded to CWIP (Account 107).
1178 | Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
1179 | Other | Other amounts reflected in budget; do not directly relate to a project with actual spend during the periods presented.

## Schedule C2
Kentucky Power Company
Case No. 2020-00174
Calculation of Capital Slippage Factor
For the Five Years Ended December 31, 2019
Schedule C2
Year | Actual Annual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2015 | 111410407.602 | 93907111.111 | 17503296.491 | 18.64% | 118.6%
2016 | 97154400.404 | 88258049.14 | 8896351.264 | 10.08% | 110.1%
2017 | 100386925.186 | 79581314.637 | 20805610.549 | 26.14% | 126.1%
2018 | 139702471.441 | 154710340.868 | -15007869.427 | -9.701% | 90.3%
2019 | 173948013.995 | 212200995.71 | -38252981.715 | -18.03% | 81.97%
Totals | 622602218.628 | 628657811.466 | -6055592.838 | -0.9633% | 99.04%
Five Year Average Slippage Factor |  |  |  |  | 105.4%