## Test Year
Schedule D (Historical Test Year)
Kentucky Power Company
Case No. 2020-00174
Construction Projects for the Historical Test Year
April 2019 - March 2020
Actual Accumulated Costs - April 2019 through March 2020
Line No. | Project No. | Description of Project | Most Recent Budget Estimate | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost | Estimated Physical Percent Completed April 2019 Through March 2020
(A) | (B) | (C) | (I) | (D) | (E)* | (F)* | (G=D+E+F) | (H) = (G)/(I)
1 | GLBU 110 (Distribution)
2 | TREEREL19 | ROW Capital widening & removal | 13148865.013 | 9908102.76 |  |  | 9908102.76 | 75.35%
3 | 000007818 | KP/Small Local Asset Improv | 6463660.004 | 7346577.45 | 47879.35 | 1816063.08 | 9210519.88 | 142.5%
4 | ITCW11004 | KY Next Generation Radio Sys | 2018167.959 | 6457896.75 | 44896.98 |  | 6502793.73 | 322.2%
5 | DR15K02B0 | KP/Princess Station DStation | 0 | 3923302.026 | 96834.26 | 901457.34 | 4921593.626 | n.m.
6 | 000001818 | KY/Svc Restoration NonMjr Evt | 2927501.269 | 3945029.5 | 921.26 | 920318.92 | 4866269.68 | 166.2%
7 | 000005234 | KyPCo-D Capital Software Dev | 0 | 4482702.32 |  |  | 4482702.32 | n.m.
8 | EON011326 | Line Transformer/Kp | 2495554.084 | 3102841.14 |  | 769522.55 | 3872363.69 | 155.2%
9 | EDN014651 | Ds/Kp/Cs-New Customers | 2974637.412 | 2755140.99 | 1306.97 | 693359.55 | 3449807.51 | 116%
10 | 000007599 | KP-Failed Equip No Outage | 2670590.404 | 2694441.91 | 4970.3 | 686073.91 | 3385486.12 | 126.8%
11 | KY5YCYCLE | KY D 2017-00179 | 3638799.148 | 3161984.68 | 410.58 | 63969.49 | 3226364.75 | 88.67%
12 | EDN100033 | Ds/Kp/C&I New | 1936272.549 | 2138011.29 | 1714.65 | 528417.42 | 2668143.36 | 137.8%
13 | P18025001 | Kewanee Station - Baseline Wor | -2920954.075 | 2201759.37 |  | 374806.29 | 2576565.66 | -88.21%
14 | TREEREL20 | ROW Capital widening & removal | 1843344.009 | 2279705.73 |  |  | 2279705.73 | 123.7%
15 | DP14K02B0 | KP/Raccoon Sta - 30 MVA 138-34 | 0 | 1762110.39 | 13406 | 372593.09 | 2148109.48 | n.m.
16 | 000025820 | Kentucky Power State Office | 923799.658 | 1972847.3 | 6590 |  | 1979437.3 | 214.3%
17 | 000025229 | 2018 Gen Plt Cap Blkt - KYPC-D | 1423388.007 | 1953609.91 | 9612.08 |  | 1963221.99 | 137.9%
18 | EDN014680 | Ds-Kp-Ai Pole Replacement | 3123792.595 | 1337498.74 | 825.79 | 322225.84 | 1660550.37 | 53.16%
19 | 000016528 | KYCutout-Arrester | 1692472.317 | 1333574.65 | 6031.41 | 315080.93 | 1654686.99 | 97.77%
20 | EDN100577 | Ds-Kp-Ai Ckt Inspections | 1227349.994 | 1248798.57 | 2379.79 | 324785.6 | 1575963.96 | 128.4%
21 | DR19K02A0 | Ashland DA 2019 - D line | 0 | 856699.23 | 3015.36 | 173011.26 | 1032725.85 | n.m.
22 | DR18K02A0 | Hazard 2018 DA Plan | 0 | 860979.98 | 5982.25 | 110425.38 | 977387.61 | n.m.
23 | DCTSUVLKY | KY CATS Monthly Unvouch Liab | 0 | 865613.2 |  |  | 865613.2 | n.m.
24 | EDN014720 | Ds-Kp-Ai Recloser Replacement | 1193184.663 | 637391.47 | 5205.29 | 160800.11 | 803396.87 | 67.33%
25 | B110KYSRR | D/KY/Non-Specific Work - Sta | 647009.12 | 657500.41 | -14193.4 | 159176.24 | 802483.25 | 124%
26 | DR19K04A0 | Pikeville DA 2019 - D line | 0 | 604914.54 | 2273.28 | 134577.27 | 741765.09 | n.m.
27 | DR19K05A0 | Hazard DA 2019 - D line | 906290.566 | 587555.16 | 471.8 | 136064.91 | 724091.87 | 79.9%
28 | 000004737 | KPSectionalizing Program | 644802.442 | 558489.29 | 4011.24 | 139581.11 | 702081.64 | 108.9%
29 | EDN015042 | Ds-Kp-Small Wire Repl Ovhd | 452100.225 | 563885.1 | 4062.09 | 126395.22 | 694342.41 | 153.6%
30 | ITCB11000 | KENTUCKY POWER - DIST | 643830.808 | 661764 | 16392.43 | 1914.74 | 680071.17 | 105.6%
31 | A17212002 | Hayward RTU Replacement | 189893.539 | 485499.38 | 2245.96 | 146249.64 | 633994.98 | 333.9%
32 | EDN011333 | Customer Meter/Kp | 792770.687 | 475575.39 |  | 139841.09 | 615416.48 | 77.63%
33 | IT110BILL | Corp Prgrm Billing - KP Distri | 0 | 510990.13 | 34397.91 |  | 545388.04 | n.m.
34 | A15702051 | Pikeville Stn RepBank#1 | 0 | 392330.1 | 25481.25 | 90001.69 | 507813.04 | n.m.
35 | IT1101421 | Maximo Imp - KYP - D | 0 | 449335.97 | 44010.53 |  | 493346.5 | n.m.
36 | DR19K06B0 | Breaker Repl - Ashland | 0 | 395688.12 | 4985.7 | 90791 | 491464.82 | n.m.
37 | DR15K02A0 | KP/Princess Station D Line | 0 | 388188.58 | 2051.32 | 92558.28 | 482798.18 | n.m.
38 | DR18K04B0 | Pikeville Sta - Trans upgrade | 0 | 346284.06 | 12456.1 | 117256.14 | 475996.3 | n.m.
39 | DR19K06B1 | Breaker Repl - Lovely | 0 | 376291.15 | 2218.56 | 94112.21 | 472621.92 | n.m.
40 | DP18K03L0 | Tygart Sta - Purchase property | 0 | 448650.77 |  |  | 448650.77 | n.m.
41 | EDN012370 | Ds/Kp/Public Relocation | 1925873.587 | 284461.76 | 788.24 | 135077.37 | 420327.37 | 21.83%
42 | DR19K02B0 | Ashland DA 2019 - Busseyville | 0 | 321477.92 | 1131.7 | 83675.62 | 406285.24 | n.m.
43 | EDN014694 | Ds-Kp-Ai Other Make Ready | 420637.81 | 207076.23 | 405.45 | 175264.46 | 382746.14 | 90.99%
44 | DP16K02A0 | Add Two D circuits-Cedar Ck | 186568.001 | 289356.79 | 2725.92 | 72684.21 | 364766.92 | 195.5%
45 | DMS20KK01 | KY/ME/Wind Storm 01/11/2020 | 0 | 278412.5 | 63.46 | 80774.23 | 359250.19 | n.m.
46 | 000025522 | Lovely\Lovely Sectionalizing | 0 | 256084.32 | 3314.72 | 57088.79 | 316487.83 | n.m.
47 | 000002241 | KP-Damage Claims-Reimburse | 89795.494 | 232796.57 | 940.44 | 74299.66 | 308036.67 | 343%
48 | KYCAPTOOL | KY Purch. Cap Tools | 141004.797 | 262298.16 | 11.38 | 9930.34 | 272239.88 | 193.1%
49 | A20212001 | Lovely RTU Reliability | 106221.346 | 200670.71 | 1467.35 | 59911.01 | 262049.07 | 246.7%
50 | EDN014658 | Ds/Kp/Cs-Upgrades | 164759.717 | 202302.64 | 182.08 | 53672.35 | 256157.07 | 155.5%
51 | DR18K02B0 | Jeff Sta - Add DRTU | 0 | 155962.43 | 1861.72 | 40114.89 | 197939.04 | n.m.
52 | P16113007 | Coalton Line Relaying | 25958.12 | 149375.92 | 7441.16 | 40917.45 | 197734.53 | 761.7%
53 | DMS19KK05 | KY Pre/Valid Major Storm 5 | 0 | 152976.07 | 55.24 | 39185.35 | 192216.66 | n.m.
54 | DR18K02B3 | Vicco Sta - Add DRTU | 0 | 147679.21 | 5270.94 | 34268.65 | 187218.8 | n.m.
55 | DMS19KK02 | KY Pre/Valid Major Storm 2 | 0 | 145052.17 | 7.25 | 35198.4 | 180257.82 | n.m.
56 | DMS19KK06 | KY Pre/Valid Major Storm 6 | 0 | 131776.18 | 4.93 | 42659.85 | 174440.96 | n.m.
57 | P18216001 | Hoods Creek Land Purchase | 0 | 166553.7 |  |  | 166553.7 | n.m.
58 | DR19K06B2 | Breaker Repl - 47th St | 0 | 116303.636 | 1487.23 | 28084.47 | 145875.336 | n.m.
59 | TA1807312 | D/KPCO/SEL GE Relay | 0 | 119382.452 | 1168.42 | 25206.88 | 145757.752 | n.m.
60 | 000007615 | KP-Cust Req Relocate | 214913.7 | 101823.62 | 86.13 | 41360.71 | 143270.46 | 66.66%
61 | A15710030 | Beavercreek TS TTMP | 0 | 99835.19 | 15426.71 | 25520.78 | 140782.68 | n.m.
62 | DP16K03B0 | Tygart Sta - Dist Station | 0 | 96915.41 | 429.33 | 23683.32 | 121028.06 | n.m.
63 | EDN103175 | Ds Kp Anda | -0.034 | 11430311.93 |  | -11310988.19 | 119323.74 | -350952165%
64 | A16928014 | Skid Station KPCo 1002 Purchas | 0 | 54596.08 | 42400.8 | 13612.5 | 110609.38 | n.m.
65 | 000007558 | KP-PQ-QOS Mitigation | 456088.81 | 93405.1 | 76.67 | 10000.46 | 103482.23 | 22.69%
66 | P11161021 | Stanville DLINE Components | 0 | 81694.97 | 130.07 | 20836.43 | 102661.47 | n.m.
67 | P11161006 | D/KP Stanville Station KPCo | 0 | 40339.97 | 16207.99 | 10782.78 | 67330.74 | n.m.
68 | 000014717 | KY/DOP/Copper Theft | 138762.193 | 53470.99 | 56.24 | 12907.03 | 66434.26 | 47.88%
69 | P19091002 | Cancel Middle Creek Stn Land | 0 | 50825.25 | 646.19 | 12451.46 | 63922.9 | n.m.
70 | KYCR012DL | KP/VoltVar Circ Reconfig DLine | 0 | 59663.88 | 3626.36 | -2211.53 | 61078.71 | n.m.
71 | EDN100044 | Ds/Kp/C&I Upgrades | 89730.029 | 30162.33 | 138.08 | 30713.06 | 61013.47 | 68%
72 | 000007577 | KP-UG Cable Repl Failure | 34365.094 | 44318.7 | -119.1 | 14890.74 | 59090.34 | 171.9%
73 | DMS19KK03 | KY Pre/Valid Major Storm 3 | 0 | 49446.31 | 1.56 | 8439.92 | 57887.79 | n.m.
74 | A15710017 | West Paintsville Telecom Moder | 0 | 43502.48 | 2489.48 | 11758.99 | 57750.95 | n.m.
75 | DR19K05B1 | Hazard DA 2019 - Engle | 178234.919 | 46719.07 | 399.11 | 8870.69 | 55988.87 | 31.41%
76 | DR19K05B0 | Hazard DA 2019 - Shamrock | 217853.488 | 44638.41 | 476.26 | 10808.26 | 55922.93 | 25.67%
77 | DR19K05B2 | Hazard DA 2019 - Slemp | 262287.437 | 44561.6 | 449.68 | 8840.42 | 53851.7 | 20.53%
78 | DMS20KK02 | KY Pre\Valid Major Storm 02 | 0 | 46454.87 | 1.15 | 841.2 | 47297.22 | n.m.
79 | A15710039 | Pikeville TTMP | 28288.448 | 35205.25 | 1790.8 | 7875.06 | 44871.11 | 158.6%
80 | A19442001 | Grayson Meter Mod | 38521.46 | 30721.86 | 175.54 | 8612.08 | 39509.48 | 102.6%
81 | P13064028 | D Line Work | 0 | 25658.09 | 11.16 | 7090.8 | 32760.05 | n.m.
82 | A15710040 | South PIkeville TTMP | 28288.448 | 24013.45 | 1864.33 | 6260.8 | 32138.58 | 113.6%
83 | P19091009 | Cancel Mid Crk Station (KP D) | 0 | 32545.51 | 87.39 | -2334.47 | 30298.43 | n.m.
84 | P19092002 | Cancel Allen Station (Dist) | 0 | 18075.07 | 116.46 | 5009.82 | 23201.35 | n.m.
85 | P17084005 | Myra Station | 563294.483 | 16695.25 | 1098.77 | 4498.81 | 22292.83 | 3.958%
86 | A13002013 | D/KP/Highland-Repl BPLC Rly | 0 | 15863.44 | 1360.49 | 4875.24 | 22099.17 | n.m.
87 | P17083030 | Garrett Station (Distribution) | 9063.281 | 19241.38 | 202.12 | 2208.18 | 21651.68 | 238.9%
88 | P17083016 | McKinney Station Work | 23473.404 | 17146.67 | 276.28 | 3316.66 | 20739.61 | 88.35%
89 | P11161002 | D/KP/S.PIKEV -Remote End | 0 | 10892.14 | 6073.58 | 2748.93 | 19714.65 | n.m.
90 | DX17K01B0 | Elwood Sta - Repl Brkr R | 0 | 8702.19 | 6841.94 | 2576.61 | 18120.74 | n.m.
91 | A15710005 | Ashland POP Tele Modernization | 0 | 17929.4 |  |  | 17929.4 | n.m.
92 | DMS19KK04 | KY Pre/Valid Major Storm 4 | 0 | 14563.1 | 8.01 | 2707.31 | 17278.42 | n.m.
93 | A20705033 | Barrenshe Station Pre-Eng | 0 | 14419.72 | 230.93 | 2544.34 | 17194.99 | n.m.
94 | A20705058 | Falcon Station 46kV removal | 0 | 12439.78 | 136.99 | 3399.84 | 15976.61 | n.m.
95 | A15710062 | Coleman Station TTMP | 8385.898 | 11722.26 |  | 2882.98 | 14605.24 | 174.2%
96 | DP15K05L0 | Raccoon Station site purchase | 0 | 10867.16 | 3387.37 |  | 14254.53 | n.m.
97 | A15710021 | Allen Station TTMP | 0 | 8644.48 | 1009.8 | 2376.66 | 12030.94 | n.m.
98 | EDN014701 | Ds Kp Ai Support Cs Res | 21582.861 | 8638.73 | 5.9 | 2384.25 | 11028.88 | 51.1%
99 | A15710020 | Prestonburg Station TTMP | 0 | 8082.72 | 828.02 | 2001.66 | 10912.4 | n.m.
100 | A13002014 | D/KP/Raceland-Repl BPLC Rly | 0 | 6926.09 | 1497.36 | 2136.64 | 10560.09 | n.m.
101 | P17076002 | Kenwood Station | 76403.478 | 4759.73 | 4605.72 | 1188.37 | 10553.82 | 13.81%
102 | A15710026 | Jenkins Station TTMP | 0 | 8288.52 |  | 1988.03 | 10276.55 | n.m.
103 | DX17K02B0 | Second Fork Sta - add SCADA | 0 | 4523.59 | 4165.89 | 1345.64 | 10035.12 | n.m.
104 | A15710038 | Grayson TTMP | 17687.725 | 7565.29 | 483.12 | 1853.83 | 9902.24 | 55.98%
105 | A15710056 | Jeff Station TTMP | 8385.898 | 7352.77 |  | 1918.51 | 9271.28 | 110.6%
106 | A20705068 | Coleman Stn Needs Assessment | 0 | 7491.05 | 63.17 | 1713.52 | 9267.74 | n.m.
107 | A20705084 | Belfry Needs Assessment | 0 | 7055.85 | 47.49 | 2085.42 | 9188.76 | n.m.
108 | A20705085 | Tom Watkins Station Needs Asmt | 0 | 7033.22 | 42.66 | 2054.5 | 9130.38 | n.m.
109 | 000025515 | Long Span Rehab 2018 | 0 | 5865.67 | 3.96 | 1625.24 | 7494.87 | n.m.
110 | P17084024 | CANCELLED | 0 | 2991.14 | 2598.76 | 643.97 | 6233.87 | n.m.
111 | EDN101114 | Ds Kp Ai Support Cs C I | 31567.217 | 4575.07 | 2.31 | 1005.78 | 5583.16 | 17.69%
112 | P18221011 | Collier Remote End | 0 | 4165.22 | 88.52 | 1078.66 | 5332.4 | n.m.
113 | A15710055 | Vicco Station TTMP | 8385.898 | 4633.15 |  | 473.72 | 5106.87 | 60.9%
114 | A15710019 | Coalton Station TTMP | 0 | 4226.88 |  | 763.18 | 4990.06 | n.m.
115 | A15710057 | Daisy Station TTMP | 2236.232 | 3643.02 |  | 1157.01 | 4800.03 | 214.6%
116 | A15710054 | Beckham Station TTMP | 8385.898 | 4707.17 |  |  | 4707.17 | 56.13%
117 | P18025002 | Kewanee Station Land Purchase | 0 | 4370.97 |  |  | 4370.97 | n.m.
118 | P17084009 | Burton Station Retirement | 1708411.202 | 2795.38 | 659.56 | 758.55 | 4213.49 | 0.2466%
119 | A15710085 | Olive Hill Station TTMP | 0 | 3253.04 | 17.25 | 735.15 | 4005.44 | n.m.
120 | DP18K01L0 | Lloyd Sta - Purchase property | 0 | 3943.35 |  |  | 3943.35 | n.m.
121 | A15710086 | Hayward Station TTMP | 0 | 3007.18 | 33.14 | 661.02 | 3701.34 | n.m.
122 | 000024645 | KYPCo-D General Plt Cap Blkt | 312.281 | 3139.54 |  |  | 3139.54 | 1005%
123 | A15710076 | Russell Station TTMP | 0 | 2473.42 | 34.38 | 489.72 | 2997.52 | n.m.
124 | A15710016 | Oakland TS Telecom Modernizati | 0 | 2787.53 | 83.66 |  | 2871.19 | n.m.
125 | A15710075 | Belhaven Station TTMP | 0 | 2299.64 | 30.69 | 489.43 | 2819.76 | n.m.
126 | A15710080 | Tenth Street Station TTMP | 0 | 2324.42 | 30.02 | 456.65 | 2811.09 | n.m.
127 | A15710079 | Hitchins Station TTMP | 0 | 2187.99 | 31.22 | 402.27 | 2621.48 | n.m.
128 | P19092014 | Prestonsburg Remote End | 0 | 1812.17 | 34.37 | 425.2 | 2271.74 | n.m.
129 | P17076003 | Prestonsburg Remote End Work | 13727.515 | 991.62 | 942.77 | 279.85 | 2214.24 | 16.13%
130 | A15710072 | Raccoon Station TTMP | 0 | 1675.89 | 18.96 | 318.88 | 2013.73 | n.m.
131 | P19092016 | McKinney Remote End Work | 0 | 1496.29 | 32.21 | 371.03 | 1899.53 | n.m.
132 | A17750006 | Cannonsburg Failed TR1 | 0 | 1376.7 |  | 367.53 | 1744.23 | n.m.
133 | P17083033 | Garrett Land Purchase | 49073.629 | 1715.68 |  |  | 1715.68 | 3.496%
134 | P17084025 | Elwood Station Retirement | 0 | 910.81 | 506.89 | 252.9 | 1670.6 | n.m.
135 | P17225006 | Ramey Station | -294764.389 | 651.24 | 597.33 | 195.42 | 1443.99 | -0.4899%
136 | A15710053 | Topmost Station TTMP | 8385.898 | 1103.04 |  | 326.59 | 1429.63 | 17.05%
137 | A15710063 | Falcon Station TTMP | 10622.138 | 1127.24 |  | 274.45 | 1401.69 | 13.2%
138 | P14030009 | Stinnett Station & Telecom | 77878.648 | 654.84 | 499.25 | 176.25 | 1330.34 | 1.708%
139 | P17084014 | Henry Clay Station Retirement | 0 | 494.65 | 649.43 | 137.16 | 1281.24 | n.m.
140 | 000025524 | Feds Cr. Exit Relocation | 0 | 801.55 | 1.51 | 352.54 | 1155.6 | n.m.
141 | SI110KYRE | DB/SI/KyP-KENTUCKY SYS REHAB | 0 | 990.71 | -29.82 | 179.47 | 1140.36 | n.m.
142 | P18025003 | CANCELLED | -284853.143 | 126.31 | 223.8 | 740.69 | 1090.8 | -0.3829%
143 | DR20K02B3 | Breaker Repl - Jenkins | 0 | 788.81 | 2.48 | 227.09 | 1018.38 | n.m.
144 | A13212036 | Ashland (KY) Telecom Pilot Wir | 0 | 799.81 |  | 186.06 | 985.87 | n.m.
145 | P18221016 | Jackhorn Distribution work | 0 | 720.16 | 11.5 | 195.35 | 927.01 | n.m.
146 | P11161003 | Allen Remote End | 0 | 680.48 |  | 179.81 | 860.29 | n.m.
147 | A15710011 | Hagler Hill TS Tele Modernizat | 0 | 660.31 |  |  | 660.31 | n.m.
148 | DR19K04B2 | Pikeville DA 2019 - Stanv. D | 0 | 570.88 |  |  | 570.88 | n.m.
149 | DR20K02B1 | Breaker Repl - Sidney | 0 | 445.45 | 0.67 | 121.35 | 567.47 | n.m.
150 | P17076011 | Distribution work at Kenwood | 17686.037 | 187.45 | 156.01 | 50.84 | 394.3 | 2.229%
151 | A15710012 | Busseyville Telecom Modernizat | 0 | 224.71 |  | 49.84 | 274.55 | n.m.
152 | DR20K02B2 | Breaker Repl - Grayson | 0 | 202.01 | 0.41 | 66.71 | 269.13 | n.m.
153 | DR20K02B0 | Breaker Repl - E Prestonsburg | 0 | 196.75 | 0.81 | 62.32 | 259.88 | n.m.
154 | A15710059 | Keyser Station TTMP | 2236.232 | 236.94 |  |  | 236.94 | 10.6%
155 | A15710060 | Pikesville SC TTMP | 8385.898 | 151.37 |  |  | 151.37 | 1.805%
156 | P17225007 | Ramey Station - Distribution | -139995.245 | 17.86 | 21.29 | 5.21 | 44.36 | -0.03169%
157 | P18025004 | CANCELLED | 0 | 8.65 | 10.3 | 2.52 | 21.47 | n.m.
158 | KYCR31167 | KY CR Belhaven Sta | 0 | 5.7 |  |  | 5.7 | n.m.
159 | 000008154 | KP Cust Serv Eng Support | 1638884.711 | 0 |  |  | 0 | 0%
160 | 000009160 | Forestry KP D Base R W | 26302.58 | 0 |  |  | 0 | 0%
161 | ETN000110 | T Kp D Anda | 0 | 174702.56 |  | -174702.56 | 0 | n.m.
162 | P17083025 | Soft Shell Station Work (KPCo) | 0 | -245.3 | 1.21 | -391.08 | -635.17 | n.m.
163 | DR18K03B5 | Breaker Rpl - S Pikeville | 0 | -20124.36 | 17735.44 | -7286.09 | -9675.01 | n.m.
164 | P19091007 | Cancel Prestonsburg Remote End | 0 | 0 | 40.07 | -10500.12 | -10460.05 | n.m.
165 | P17225011 | Hoods Creek Land Purchase | 0 | -31175.65 |  |  | -31175.65 | n.m.
166 | DMS18KK08 | KP/Pre Valid Major Event 8 | 0 | -25960.1 |  | -6809.98 | -32770.08 | n.m.
167 | EDN014687 | Ds-Kp-Ai Aepc Make Ready | 0 | -45667.51 | 31.33 | 9974.51 | -35661.67 | n.m.
168 | P17084001 | Cancel: DO NOT USE | 0 | -58987.53 | -4609.36 | -10902.14 | -74499.03 | n.m.
169 | TREEREL18 | ROW Capital widening & removal | 0 | 1518.67 | -76528.35 | 187.72 | -74821.96 | n.m.
170 | DMS19KK01 | KP/ME/Wind Storm 02/24/19 | 0 | -88408.05 |  | 392.23 | -88015.82 | n.m.
171 | DX16K02A0 | Coalton Sta - US RT 60 PPR | 0 | -171854.17 | 12545.8 | 31690.2 | -127618.17 | n.m.
172 | Other Budgeted Projects |  | 13287871.949 | 0 | 0 | 0 | 0 | Other
173 | Total GLBU 110 (Distribution) |  | 72714293.475 | 91708325.214 | 497018.5 | -22178.57 | 92183165.144 | 126.8%
174 | GLBU 117 (Generation)
175 | 000021737 | BS Repurpose BAP | 5256341.21 | 5450033.67 | 107172.94 | 756454.47 | 6313661.08 | 120.1%
176 | 000022392 | ML LANDFILL EXPANSION - PH 3 | 2456251.425 | 2863238.929 | 267875.06 | 291744.16 | 3422858.149 | 139.4%
177 | 000005237 | KyPCo-G Capital Software Dev | 0 | 3219411.06 |  |  | 3219411.06 | n.m.
178 | ML119SC02 | ML U1 ECON PARTITION WALL RPL | 1445747.071 | 1995456.12 | 47160.9 | 146903.39 | 2189520.41 | 151.4%
179 | 000022308 | ML U1 ESP Project | -1723978.457 | 1415393.74 | 42960.3 | 105171.62 | 1563525.66 | -90.69%
180 | BSPPB0013 | Other Costs PPB<$100k | 96805.513 | 997846.79 | 5815.12 | 176380.5 | 1180042.41 | 1219%
181 | IT1171421 | Maximo Imp - KYP - G | 0 | 1063098.84 | 113397.88 |  | 1176496.72 | n.m.
182 | 000020310 | ML U0 ELG Compliance | 1202066.443 | 685861.07 | 2367.06 | 136544.02 | 824772.15 | 68.61%
183 | ML1SC1810 | ML1 S BREECHING DUCT RPL | 407796.43 | 665932.83 | 13525.58 | 48455.53 | 727913.94 | 178.5%
184 | IT117BILL | Corp Prgrm Billing - KYPCO Gen | 0 | 489259.79 | 34799.87 |  | 524059.66 | n.m.
185 | ML1EC1302 | ML1 E PHASE 1 GSU TRANSFORMER | 1145726.809 | 230422.94 | 20351.48 | 38169.7 | 288944.12 | 25.22%
186 | MLP19EP03 | ML E PUMP REPLACEMENT DR 10 HP | 350000 | 244123.13 | 2401.16 | 32270.95 | 278795.24 | 79.66%
187 | ML019SP01 | ML PULVERIZER REBUILD CAP (#xx | 0 | 235004.21 | 5831.57 | 23879.62 | 264715.4 | n.m.
188 | MLP19EP04 | ML E LIGHTING PANEL REPLACE | 0 | 226232.13 | 2086.19 | 36294.24 | 264612.56 | n.m.
189 | ML120SP01 | ML U1 Lime Inj Rig and Pig Buy | 0 | 214577.3 | 1490.94 | 45265.35 | 261333.59 | n.m.
190 | ML219SP06 | MLU2 21 PULVERIZER REBUILD | 0 | 207015.8 | 1875.36 | 26432.58 | 235323.74 | n.m.
191 | MLP19MP01 | MLP MH COAL CHUTE REPLACEMENT | 382566.814 | 182231.35 | 554.44 | 39119.03 | 221904.82 | 58%
192 | ML219VP06 | ML 21 ID FAN DE HUB REPLACE | 0 | 180201.62 | 251.09 | 35224.03 | 215676.74 | n.m.
193 | BSPPBS348 | Replace 4KV Brkr Racking Mech | 214952.823 | 181989.63 | 980.07 | 25811.8 | 208781.5 | 97.13%
194 | ML019VP01 | ML - NON OUTAGE PPB FGD | 462564.592 | 172310.33 | 1171.99 | 25587.12 | 199069.44 | 43.04%
195 | MLP19MP03 | ML MH R4 COAL CHUTE REPLACEMT | 0 | 176897.96 | 833.23 | 18380.81 | 196112 | n.m.
196 | MLP19MP02 | MLP MH CONVEYOR BELT REPLACE | 148325.816 | 155427.16 | 1747.84 | 16774.13 | 173949.13 | 117.3%
197 | ML219SP05 | MLU2 PRECIP ROOF BAY BOX4ROW7 | 396167.5 | 130087.69 | 1005.4 | 20587.87 | 151680.96 | 38.29%
198 | BSPPBS363 | BS1 BFPT (SPARE) BLADE REPLACE | 124080.436 | 112941.58 | 614.68 | 25445.27 | 139001.53 | 112%
199 | ML219SP04 | MLU2 PRECIP ROOF BAY BOX3ROW7 | 396167.5 | 117516.91 | 865.56 | 19895.77 | 138278.24 | 34.9%
200 | ML1E18C05 | MLU1 LP TURBINE ROTOR REPAIR | -68389.718 | 85077.89 | 35006.23 | 6567.89 | 126652.01 | -185.2%
201 | ML2VC1601 | ML2 V CATALYST REPLACEMENT 3 L | 0 | 75791.48 | 37117.44 | 13363.45 | 126272.37 | n.m.
202 | ML119EP04 | ML UNIT 1 HIGH ENERGY PIPING | 0 | 117618.03 | 727.89 | 7543.33 | 125889.25 | n.m.
203 | ML219EP03 | ML UNIT2 ACID LINE REPLACEMENT | 0 | 110879.05 | 879.76 | 13838.89 | 125597.7 | n.m.
204 | BSPPBS351 | Replace Auto Voltage Regulator | 87976.133 | 104037.01 | 693.23 | 20161.48 | 124891.72 | 142%
205 | ML119SP08 | ML U1 DEMINERALIZER RESIN RPL | 0 | 113516.79 | 524.52 | 8196.31 | 122237.62 | n.m.
206 | ML219VP07 | ML 22 ID FAN DE HUB REPLACEMEN | 0 | 102603.97 | 137.49 | 17060.4 | 119801.86 | n.m.
207 | MLP19EP01 | ML E MOTORS GREATER THAN 10 HP | 0 | 105273.58 | 1012.59 | 9540.39 | 115826.56 | n.m.
208 | MLP18SP01 | ML SAFETY VALVES ( 4 ) | 0 | 89224.94 | 3351.06 | 4666.24 | 97242.24 | n.m.
209 | ML019NP01 | ML CAPITAL TOOLS | 0 | 82376.75 | 1011.69 | 12673.3 | 96061.74 | n.m.
210 | ML019VP02 | ML0 V BALL MILL REBUILD | 0 | 89005.29 | 451 | 5742.34 | 95198.63 | n.m.
211 | BSPPBOUT1 | Unit 1PPB Outage<100k | 603250.122 | 70726.58 | 152.08 | 18924.58 | 89803.24 | 14.89%
212 | ML219VP08 | ML 22 ID FAN DCHG VLV EJ | 0 | 76214.83 | 82.45 | 12512.66 | 88809.94 | n.m.
213 | ML119EP07 | ML UNIT1 ACID LINE REPLACEMENT | 0 | 76117.7 | 1250.1 | 10444.27 | 87812.07 | n.m.
214 | ML1VC1601 | ML1 V CATALYST REPLACEMENT 3 L | 0 | 60148.16 | 20196.3 | 7462.53 | 87806.99 | n.m.
215 | 000025231 | 2018 Gen Plt Cap Blkt - KYPC-G | 0 | 73381.9 | 837.52 | 6749.78 | 80969.2 | n.m.
216 | ML219EP14 | ML219 21 CIRC MTR DIODE RING | 0 | 71574.48 | 483.78 | 5452.44 | 77510.7 | n.m.
217 | ML019EP02 | ML TRANSFORMER REPLACEMENT | 0 | 66043.55 | 369.36 | 9486.4 | 75899.31 | n.m.
218 | ML220VP01 | ML U2 ID Fan Hub Shell Replace | 0 | 54204.45 | 258.52 | 10160.58 | 64623.55 | n.m.
219 | BSPPB0002 | Boiler & Auxiliaries PPB<100k | 84085.706 | 56365.47 | 330.31 | 3170.36 | 59866.14 | 71.2%
220 | ARCFLA117 | Arc Flash Protection Swi KYPCo | 0 |  | 56433.93 |  | 56433.93 | n.m.
221 | ML118SP22 | ML U1 BOILER CAMERA UPGRADE | 0 | 44216.15 | 9017.14 | 2962.3 | 56195.59 | n.m.
222 | MLP19EP06 | LP E VALVE REPLACEMENT 6 IN + | 0 | 49727.42 | 403.13 | 5761.63 | 55892.18 | n.m.
223 | ML118EP04 | REP RFL9300 PILOT WIRE SYSTEM | 110839.455 | 41715.33 | 374.75 | 4093.2 | 46183.28 | 41.67%
224 | ML119SP13 | REPLACE U1 PULVERIZER YOKE | 0 | 41107.21 | 1006.28 | 2913.64 | 45027.13 | n.m.
225 | ML119SP14 | ML U1 SCR INLET EXP JOINT | 0 | 42201.99 | 222.25 | 2599.45 | 45023.69 | n.m.
226 | ML219SP07 | MLU2 PRECIP EXP JOINT #1 | 0 | 36746.36 | 228.49 | 6849.24 | 43824.09 | n.m.
227 | ML019EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 0 | 36125.78 | 415.58 | 5345.13 | 41886.49 | n.m.
228 | ML1NP1911 | ML1 INSULATION & LAGGING RPL | 111510.047 | 37441.68 | 295.53 | 2431.99 | 40169.2 | 36.02%
229 | MLP19EP02 | ML E MOTOR REWINDSOVER 10HP | 0 | 37281.92 | 197.45 | 2660.77 | 40140.14 | n.m.
230 | ML119SP17 | ML U1 Purge Air Heater Pnchlst | 40000 | 32093.05 | 131.44 | 6681.47 | 38905.96 | 97.26%
231 | ML019NP06 | ML U0 Gate 4 Automatic Gate | 0 | 31095.71 | 134.82 | 6178.16 | 37408.69 | n.m.
232 | ML119SP07 | ML1 E PRECIPITATOR EJ REPLACE | 166259.227 | 34056.94 | 282.89 | 2115.05 | 36454.88 | 21.93%
233 | ML019EP01 | ML REPLACEMENT OF TRANSMITTER | 0 | 31778.79 | 455.01 | 3098.5 | 35332.3 | n.m.
234 | ML219EP02 | ML INTERTEK HIGH ENERGY PIPING | 0 | 30286.64 | 775.9 | 2135.18 | 33197.72 | n.m.
235 | NRCCPKPCO | NERC CIP KYPCO | -79683.338 | -21926.32 | 42653.27 | 12316.47 | 33043.42 | -41.47%
236 | ML018EP11 | ML CIRCULATING WATERPMP MOTORS | 0 | 27875.8 | 755.87 | 1990.32 | 30621.99 | n.m.
237 | ML119EP05 | ML #11B CIRC WATER PUMP REPLMT | 0 | 26399.6 | 433.37 | 1687.06 | 28520.03 | n.m.
238 | ML019EP10 | ML MH UPGRADE SCALE ELECTRONIC | 0 | 23457.2 | 15.88 | 3865.69 | 27338.77 | n.m.
239 | ML219VP05 | 21 ID FAN DISCHARGE EJ REPLACE | 0 | 22125.46 | 6.23 | 3629.56 | 25761.25 | n.m.
240 | ML219EP01 | ML U2 555 LEAK DECTECT HP HEAT | 0 | 21939.42 | 527.63 | 2707.56 | 25174.61 | n.m.
241 | ML018EP14 | ML SEWAGE TREATMNT PLANT COVER | 0 | 18424.37 | 4637.88 | 1908.24 | 24970.49 | n.m.
242 | ML119SP16 | ML PENTHOUSE ROOF INSULATION | 0 | 23032.01 | 85.46 | 1460.5 | 24577.97 | n.m.
243 | ML219EP16 | ML219 21B CIRC WTR PMP REBUILD | 0 | 20102.35 | 18.02 | 3818.95 | 23939.32 | n.m.
244 | ML119EP01 | RPL MAIN TURB OIL TANK VALVE | 0 | 19788.67 | 1498.37 | 1044 | 22331.04 | n.m.
245 | ML117EP04 | REPLACE #11 RDV to NASH PUMP | 137032.421 | 18183.65 | 553.18 | 3054.7 | 21791.53 | 15.9%
246 | MLP20VP01 | ML V FGD Non Outage Capital | 0 | 15531.79 | 21.57 | 4632.35 | 20185.71 | n.m.
247 | ML219VP11 | ML2 STACK FLUE EJ @ ELE 250 | 0 | 16265.57 | 106.44 | 3165.93 | 19537.94 | n.m.
248 | ML020SP01 | ML MITCHELL DSI PROJECT | 150984.312 | 14709.08 | 69.65 | 3110.42 | 17889.15 | 11.85%
249 | ML119SP15 | ML #51 SAFETY VALVE REPLACEMNT | 0 | 16443.26 | 52.03 | 1061.39 | 17556.68 | n.m.
250 | ML219EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 0 | 13308.77 | 98.68 | 2720.97 | 16128.42 | n.m.
251 | ML118EP10 | ML U1 STATOR DO & CONDUCTIVITY | 0 | 13570.92 | 821.94 | 824.78 | 15217.64 | n.m.
252 | MLP20VP03 | ML V FGD and CPS Pumps Capital | 0 | 15074.78 | 0.09 | 27.02 | 15101.89 | n.m.
253 | ML020VP01 | ML - NON OUTAGE PPB FGD | 0 | 11505.86 | 10.44 | 2780.29 | 14296.59 | n.m.
254 | ML018VP01 | ML - NON OUTAGE PPB FGD | 0 | 13592.91 | -167.78 | 804.66 | 14229.79 | n.m.
255 | ML018NP01 | ML CAPITAL TOOLS | 154525.356 | 18045.65 | -5621.43 | 1484.01 | 13908.23 | 9.001%
256 | MLP18EP08 | ML #12 CIRCULATOR PUMP MOTOR | 0 | 13407.53 | -1255.77 | 790.71 | 12942.47 | n.m.
257 | ML018NP07 | ML NEW GATE FOR GATE 3 | 0 | 11624.26 | 44.88 | 1148.08 | 12817.22 | n.m.
258 | ML019EP11 | SULFURIC ACID LEAK DETECTION | 0 | 10463.12 | 57.76 | 2012.33 | 12533.21 | n.m.
259 | ML119EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 0 | 10561.06 | 77.04 | 1668.52 | 12306.62 | n.m.
260 | MLP20MP05 | ML U0 Limestone Stamler Cap | 0 | 9302.32 | 12.54 | 2790.86 | 12105.72 | n.m.
261 | ML015VP01 | MLU0 CCR COMPLIANCE | 0 | 7805.2 | 2493.66 | 1354.9 | 11653.76 | n.m.
262 | MLP20MP06 | ML M Pump Replacements MH Cap | 0 | 9176.49 | 26.34 | 2150.89 | 11353.72 | n.m.
263 | MLP18EP07 | ML #12 CIRCULATOR PUMP ELEMENT | 0 | 1878.84 | 9062.88 | 106.27 | 11047.99 | n.m.
264 | ML119EP03 | ML U1 555 LEAK DECTECT HP HEAT | 0 | 9981.51 | 178.58 | 634.67 | 10794.76 | n.m.
265 | ML219SP03 | REPL DFA FILTER SEPARATOR BAGS | 0 | 8951.5 | 226.61 | 1581.97 | 10760.08 | n.m.
266 | MLP20EP02 | ML-E-MOTOR REWINDS/REPLACEMENT | 0 | 8273.34 | 21.27 | 2046.52 | 10341.13 | n.m.
267 | MLP20EP06 | ML E Valve Replacements Cptl | 0 | 8566.17 | 40.86 | 1605.71 | 10212.74 | n.m.
268 | ML018NP12 | ML SERVICE BUILDING ROOF | 0 | 2613.16 | 7195.75 | 346.19 | 10155.1 | n.m.
269 | ML018EP17 | ML R3 TRANSFORMER REPLACEMENT | 0 | 6481.74 | 1647.25 | 1251.28 | 9380.27 | n.m.
270 | ML017EP02 | REPLACE AMMONIA TANK | 0 |  | 9343.95 |  | 9343.95 | n.m.
271 | MLP18EP06 | MLP E VALVE REPLACEMENT 6 IN G | 107958.806 | 8040 | -225.9 | 1500.3 | 9314.4 | 8.628%
272 | ML018MP06 | ML HIGH SULFUR STAMLER REBUILD | 0 | 44.44 | 4527.75 | 4649.17 | 9221.36 | n.m.
273 | ML016VP11 | ML - 2016 FGD NON OUTAGE PPB | 0 |  | 9119.91 |  | 9119.91 | n.m.
274 | ML119EP22 | REPLACE DEMINERALIZER HMI | 0 | 7490.01 | 3.03 | 1540.22 | 9033.26 | n.m.
275 | ML219EP23 | MLU2 EXCITER BRUSH RIGGING | 0 | 7326.99 | 54.93 | 1301.26 | 8683.18 | n.m.
276 | MLP17SP01 | INSTALL R3/R4 FIRE HEADER CTIE | 0 |  | 8635.15 |  | 8635.15 | n.m.
277 | ML219EP22 | REPLACE DEMINERALIZER HMI | 0 | 6089.95 | 14.62 | 933.47 | 7038.04 | n.m.
278 | ML118EP12 | ML UNIT 1 INSTRUMENTATION PPB | 0 | 5774.32 | 649.13 | 384.72 | 6808.17 | n.m.
279 | ML119SP09 | REPL DFA FILTER SEPARTOR BAGS | 0 | 5690.43 | 10.85 | 704.32 | 6405.6 | n.m.
280 | MLP19EP05 | ML E POWER CABLE REPLACEMENT | 0 | 6351.09 |  |  | 6351.09 | n.m.
281 | MLP20VP02 | ML V Oxidation Air Blower Cap | 0 | 4789.09 | 4.79 | 1508.39 | 6302.27 | n.m.
282 | ML219EP19 | MLU2 22B CIRC WTR PMP EJ | 0 | 4833.64 | 47.24 | 534.42 | 5415.3 | n.m.
283 | ML118EP01 | RFP9300 PILOT to GE190 SEL411L | 80809.143 | 4832.24 | 237.67 | 294.59 | 5364.5 | 6.638%
284 | MLP18EP02 | ML E MOTOR REWIND / REPL +10HP | 36822.355 | 3130.52 | 1958.68 | 205.38 | 5294.58 | 14.38%
285 | MLP20EP03 | ML E Pump Replacements (Cap) | 0 | 3702.62 | 5.17 | 980.05 | 4687.84 | n.m.
286 | ML020MP01 | ML U0 Conveyor Belt Rplcmts | 0 | 3345.62 | 3.35 | 1053.75 | 4402.72 | n.m.
287 | ML119SP12 | RPL PULVERIZER CLASSIFIER ASBY | 0 | 4055.38 | 40.25 | 270.27 | 4365.9 | n.m.
288 | ML219EP15 | ML219 22 CIRC MTR DIODE RING | 0 | 3646.72 | 29.72 | 446.61 | 4123.05 | n.m.
289 | ML218EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 0 | 3377.81 | 108 | 444.11 | 3929.92 | n.m.
290 | ML119SP10 | ML #12 CLINKER GRINDER REPLACE | 0 | 3015.68 | 279.35 | 155.56 | 3450.59 | n.m.
291 | MLP20EP09 | ML E Transmitter Replcmts Cap | 0 | 2543 | 2.55 | 800.95 | 3346.5 | n.m.
292 | MLP20EP10 | ML E Battery Charger Replace | 0 | 2226.48 | 1.23 | 695.15 | 2922.86 | n.m.
293 | MLP20SP04 | ML S Lime Inj Load Cell U1 | 0 | 1988.9 | 1.99 | 626.45 | 2617.34 | n.m.
294 | ML017VP04 | ML-NON OUTAGE PPB FGD | 0 | 2106.81 | 0.38 | 444.68 | 2551.87 | n.m.
295 | ML018NP03 | ML HAUL ROAD RELOCATION PRELIM | 0 | 2202.67 | 85.31 | 142 | 2429.98 | n.m.
296 | MLP19SP01 | ML SAFETY VALVES ( 4 ) | 63568.573 | 1810 | 1.81 | 570.08 | 2381.89 | 3.747%
297 | BSPPB0009 | Effluent WW Treating PPB<100k | 0 | 1803.82 | 1.81 | 568.14 | 2373.77 | n.m.
298 | ML019EP09 | ML AMMONIA TANK N2 BLANKETING | 0 | 2049.67 | 46.46 | 135.26 | 2231.39 | n.m.
299 | 000025026 | Gen Plt Blkt KY-G Mitchell117 | 0 | 1843.25 | 28.94 | 280.5 | 2152.69 | n.m.
300 | ML119SP11 | ML #12 RECEIVING HOPPER REPLAC | 0 | 1423.01 | 14.02 | 73.4 | 1510.43 | n.m.
301 | MLP20NP02 | ML N Security Gates | 0 | 1029.84 | 1.03 | 324.36 | 1355.23 | n.m.
302 | MLP20SP03 | ML S Pump Replacements (Cap) | 0 | 990.17 | 2.87 | 230.97 | 1224.01 | n.m.
303 | MLP20NP01 | ML CAPITAL TOOLS | 0 | 866.6 | 0.87 | 272.95 | 1140.42 | n.m.
304 | ML018EP01 | ML REPLACEMENT OF TRANSMITTERS | 64430.28 | 946 | 6.07 | 136.27 | 1088.34 | 1.689%
305 | ML120VP01 | ML U1 ID Fan Capital Work | 0 | 725.14 | 2.1 | 169.15 | 896.39 | n.m.
306 | ML019SP02 | ML PULVERIZER REBUILD CAP(#YY | 0 | 623.76 | 0.62 | 196.47 | 820.85 | n.m.
307 | ML019EP04 | ML E HVAC UNIT REPLACEMENTS | 22838.517 | 625.8 | 3.64 | 124.19 | 753.63 | 3.3%
308 | ML018EP02 | ML UNIT 1 & UNIT 2 PI SERVERS | 0 | 531.29 | 153.26 | 27.4 | 711.95 | n.m.
309 | MLP18EP09 | ML1 2019 HIGH ENERGY PIPE MAT | 0 |  | 576.46 |  | 576.46 | n.m.
310 | ML017NP01 | Capital Tools | 0 | 148 | 239.2 | 8.14 | 395.34 | n.m.
311 | ML018NP08 | ML TURNSTILE ROOFS AND GRATING | 0 | 400.68 | -297.98 | 75.1 | 177.8 | n.m.
312 | MLP20MP07 | ML M Control Upgrades Matl Han | 0 | 121.6 | 0.12 | 38.31 | 160.03 | n.m.
313 | ML018NP04 | ML STOREROOM SECURITY SYSTEM | 0 | -123 | 269.89 |  | 146.89 | n.m.
314 | ML018MP11 | ML MH BARGE UNLDR AUTO GREASE | 0 | 23.32 | 105.06 | 4.37 | 132.75 | n.m.
315 | MLP18EP03 | ML E PUMP REPLACEMENT DR 10 HP | 177139.503 | -9.73 | 104.37 | 5.48 | 100.12 | 0.05652%
316 | ML018VP06 | ML SILICON CARBIDE AR PUMP | 0 | 0.78 | 61.48 | 0.14 | 62.4 | n.m.
317 | ML018EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 0 |  | 17.15 |  | 17.15 | n.m.
318 | ML017VP03 | RPL CHEMICAL INJ SKID CPS CLAR | 0 |  | -14.81 |  | -14.81 | n.m.
319 | ML018MP10 | ML MT HANDLING MOBILE HEATERS | 0 |  | -56.22 |  | -56.22 | n.m.
320 | MLP18EP01 | ML E MOTORS GREATER THAN 10 HP | 0 | 24.64 | -82.71 | 1.61 | -56.46 | n.m.
321 | ML118SP11 | DFA EXHAUST BLOWER REPLACEMENT | 0 |  | -65.03 |  | -65.03 | n.m.
322 | ML218EP05 | ML U2 CT SHELL MONITORING SYST | 0 |  | -123.66 |  | -123.66 | n.m.
323 | ML118SP07 | REPL DFA FILTER SEPARTOR BAGS | 19074.915 |  | -153.39 |  | -153.39 | -0.8041%
324 | ML018MP04 | ML MH TOWBOAT UPGRADE REPLACE | 0 |  | -167.93 |  | -167.93 | n.m.
325 | ML018MP09 | ML MH DFA SCALE UPGRADES | 0 | 3.35 | -181.17 | 0.23 | -177.59 | n.m.
326 | ML018SP03 | ML U1&2 WATER CANNON UPGRADE | 0 |  | -201.52 |  | -201.52 | n.m.
327 | BSPPBS339 | REPLACE 15 BREAKERS "A" BUS | 0 | -228.57 | -6.32 | -24.85 | -259.74 | n.m.
328 | ML018EP16 | ML CEMS HG SORBENT BU SYSTEM | 0 |  | -263.98 |  | -263.98 | n.m.
329 | BSPPBS340 | REPLACE 15 BREAKERS "B" BUS | 0 | -304.76 | -8.41 | -33.14 | -346.31 | n.m.
330 | ML218SP09 | REPL DFA FILTER SEPARATOR BAGS | 19074.915 |  | -361.57 |  | -361.57 | -1.896%
331 | MLP18EP04 | ML E LIGHTING PANEL REPLACE | 104497.205 |  | -386.14 |  | -386.14 | -0.3695%
332 | ML118SP01 | ML U1 PRECIP EJ REPLACEMENT | 0 |  | -521.67 |  | -521.67 | n.m.
333 | ML018NP11 | ML GATE 3 EMPLOYEE STAIRS | 0 |  | -592.22 |  | -592.22 | n.m.
334 | ML018MP03 | ML MH CONVEYOR BELT REPLACE | 0 | 5520.63 | -7296.64 | 441.13 | -1334.88 | n.m.
335 | ML018VP02 | ML0 V BALL MILL REBUILD | 0 |  | -1844.85 |  | -1844.85 | n.m.
336 | ML117VP06 | RPL #11 ID FAN HYDRAULIC CYL | 0 |  | -3432.9 |  | -3432.9 | n.m.
337 | ML018VP04 | ML ID FAN DRIVE END HUB PURCHA | 0 |  | -3797.81 |  | -3797.81 | n.m.
338 | ML218SP10 | ML U2 PRECIP EJ REPLACEMENT | 0 | 361.61 | -4277.95 | 63.67 | -3852.67 | n.m.
339 | Other Budgeted Projects |  | 9575339 | 0 | 0 | 0 | 0 | Other
340 | Total GLBU 117 (Generation) |  | 24531524.86 | 24402917.799 | 931231.51 | 2451224.21 | 27785373.519 | 113.3%
341 | GLBU 180 (Transmission)
342 | P13064029 | Hazard-Wooton Change to KPCo | 4187641.736 | 8145384.65 | 198295.27 | 699048.91 | 9042728.83 | 215.9%
343 | A15702033 | Jackson - Helech Str. Replace | 9609276.577 | 4170137.36 | 64961.76 | 441081.17 | 4676180.29 | 48.66%
344 | P16113009 | Cannonsburg - S.NEAL TL KPCo | 6614454.337 | 4144793.67 | 199287.23 | 280666.48 | 4624747.38 | 69.92%
345 | DP16K02B0 | Cedar Creek add D trans | 0 | 2840434.07 | 42713.05 | 285618.52 | 3168765.64 | n.m.
346 | A15702027 | Johns Creek 138/34 kV XF | 2061336.457 | 2636007.994 | 58981.37 | 287656.29 | 2982645.654 | 144.7%
347 | 000010377 | Forestry KY T NERC | 142133.131 | 2216567.2 | 4422.56 | 293761.65 | 2514751.41 | 1769%
348 | B180KYLRC | T/KY/Non-Specific Work - Line | 411557.842 | 2234158.61 | 27146.34 | 196426.56 | 2457731.51 | 597.2%
349 | P13064030 | Hazard Station Change to KPCo | 4855797.276 | 2192838.16 | 4432.77 | 167343.54 | 2364614.47 | 48.7%
350 | P10115014 | Stone Change to KPCo | 1876865.534 | 2095568.56 | 17875.5 | 191590.4 | 2305034.46 | 122.8%
351 | A15702034 | Hazard-Jackson Str Rep Part 2 | 0 | 1333643.92 | 35322.32 | 142935.63 | 1511901.87 | n.m.
352 | A19750002 | Betsy Layne- Allen 138kV Slide | 0 | 1287331.63 | 1469.06 | 86573.77 | 1375374.46 | n.m.
353 | A19750001 | B Sandy - Broadf KP 765 Slide | 0 | 1254626.16 | 2937.85 | 108501.87 | 1366065.88 | n.m.
354 | A15702028 | Dorton 138/46 XF Replacement | 885638.081 | 1065236.01 | 65881.08 | 123413.19 | 1254530.28 | 141.7%
355 | P10115002 | TKPStone-RetRem Switches | 429782.812 | 1063380.18 | 25164.33 | 90339.72 | 1178884.23 | 274.3%
356 | 000005273 | KyPCo-T Capital Software Dev | 0 | 1097326.58 |  |  | 1097326.58 | n.m.
357 | A17750008 | Prestonsburg-Mid Creek46kVSlid | 0 | 914710.08 | 1020.07 | 99113.4 | 1014843.55 | n.m.
358 | P10115013 | Johns Creek Change to KPCo | 675798.843 | 874590.78 | 17796.24 | 64179.01 | 956566.03 | 141.5%
359 | P10115001 | TKPJohns Creek-RetRem MOABs | 248952.037 | 771546.99 | 5941.46 | 69290.09 | 846778.54 | 340.1%
360 | A15042010 | Stone Station Incr. KPCo | 1093822.817 | 738274.11 | 45126.52 | 63208.28 | 846608.91 | 77.4%
361 | A14068001 | Baker 765kV Improvement | 948843.809 | 518039.92 | 153146.73 | 50421.68 | 721608.33 | 76.05%
362 | P13064031 | Hazard 161/138 Spare KPCo | 58997.877 | 564100.92 |  | 67308.53 | 631409.45 | 1070%
363 | A17750007 | Prestonsburg-Thelma 69kV Slide | 0 | 555152.83 | 5412.44 | 51485.47 | 612050.74 | n.m.
364 | 000012898 | Forestry KP T non-NERC | 716129.616 | 558570.07 | 2047.29 | 47686.38 | 608303.74 | 84.94%
365 | P10115010 | T/KP/Inez: replace 138kV Bus # | 384340.491 | 465985.93 | 1468.37 | 52155.6 | 519609.9 | 135.2%
366 | P18221017 | Jackhorn Land Purchase | 0 | 516711.33 |  |  | 516711.33 | n.m.
367 | A19750104 | Daisy-Cloverfork Failure | 0 | 476607.7 | 399.2 | 10070.91 | 487077.81 | n.m.
368 | A19750003 | Hazard - Pineville 161kV Fail | 0 | 434018.92 | 986.44 | 42015.25 | 477020.61 | n.m.
369 | B180KYSRR | T/KY/Non-Specific Work - Stati | 213368.368 | 413305.03 | 4398.33 | 32354.51 | 450057.87 | 210.9%
370 | A17212001 | Big Sandy 138KV RTU Replacemen | 0 | 381439.7 | 1934.24 | 53381.06 | 436755 | n.m.
371 | A15710034 | Coalton-Leon Fiber TelModFib | 587779.376 | 292851.13 | 15681.87 | 33177.44 | 341710.44 | 58.14%
372 | A15702047 | Leon KY Remote End Work | 325540.823 | 305432.51 | 8953.98 | 27142.89 | 341529.38 | 104.9%
373 | A18730016 | Bonnyman-Softshell St 88 Failr | 0 | 307140.18 | 2659.77 | 30874.27 | 340674.22 | n.m.
374 | IT1801421 | Maximo Imp - KYP - T | 0 | 307898.18 | 30169.19 |  | 338067.37 | n.m.
375 | A15710035 | Pikeville Fiber TelModFib | 340290.27 | 293136.79 | 8505.13 | 35967.22 | 337609.14 | 99.21%
376 | P13064025 | Hazard - Wooton ROW KPCo | 30226.516 | 330508.54 |  |  | 330508.54 | 1093%
377 | P10115015 | Inez Change to KPCo | 250460.836 | 273176.73 | 26514.05 | 22949.23 | 322640.01 | 128.8%
378 | P10115003 | TKPStone Tap - Retire | 366127.63 | 283408.54 | 5621.49 | 31195.92 | 320225.95 | 87.46%
379 | DP14K02C0 | KP/Raccoon Sta - T line in & o | 0 | 267287.88 | 1545.79 | 18899.25 | 287732.92 | n.m.
380 | A18730015 | Spring Fork Tap Str 2 Failure | 0 | 212881.54 | 7673.12 | 20886.78 | 241441.44 | n.m.
381 | A15042011 | Coleman-Stone 69kV reconfig | 183752.859 | 217018.21 | 585.22 | 19137.09 | 236740.52 | 128.8%
382 | P19091011 | Middle Creek BESS | 0 | 185079.53 | 2101.02 | 49335.76 | 236516.31 | n.m.
383 | A15710033 | Morgan Fork Fiber TelModFib | 0 | 206576.84 |  | 17395.2 | 223972.04 | n.m.
384 | A15702030 | Morehead: Replace CB B | 164274.202 | 179849.57 | 13016.26 | 18704.19 | 211570.02 | 128.8%
385 | IT180BILL | Corp Prgrm Billing-KYPCO Trans | 0 | 200617.9 | 9309.89 |  | 209927.79 | n.m.
386 | TP0921005 | T/KY/Line: Conxt: Bonnyman-Sof | 0 | 191457.39 | 937.26 | 15152.76 | 207547.41 | n.m.
387 | DR19K04B0 | Pikeville DA 2019 - Beaver Ck | 0 | 177133.748 | 567.09 | 17348.37 | 195049.208 | n.m.
388 | DR19K04B1 | Pikeville DA 2019 - Stanville | 0 | 172388.58 | 435.51 | 17272.44 | 190096.53 | n.m.
389 | P13064021 | T/KP/Hazard - Jackson 69kV Lin | 115675.383 | 164935.42 | 5862.61 | 14657.13 | 185455.16 | 160.3%
390 | DR18K02B1 | Bonnyman Sta - Add DRTU | 0 | 165419.526 | 1134.93 | 16046.96 | 182601.416 | n.m.
391 | A15702035 | Hazard - Fleming Str. Replace | -1.182 | 137578.51 | 8238.31 | 12125.89 | 157942.71 | -13362327%
392 | DP14K02C1 | Sprigg-Beaver Creek-Tower Rplc | 0 | 139540.94 | 565.21 | 8954.57 | 149060.72 | n.m.
393 | A15042012 | Stone-Sprigg 46kV Reconfig | 54651.858 | 129231.33 | 1760.31 | 14904.43 | 145896.07 | 267%
394 | DR18K02B2 | Leslie Sta - breaker control | 0 | 130216.704 | 909.5 | 12603.78 | 143729.984 | n.m.
395 | A15702007 | Beaver Creek- Repl Cap Bk AACC | 0 | 114973.44 | 2543.53 | 10432.13 | 127949.1 | n.m.
396 | A15702029 | Leslie 161/69kV XF Replacement | 2890809.267 | 58070.97 | 62723.33 | 6225.75 | 127020.05 | 4.394%
397 | P11161025 | Betsy Layne - Allen TLINE KPCo | 0 | 62185.55 | 49505.9 | 5471.45 | 117162.9 | n.m.
398 | P17225004 | Moore Hollow 138kV Ext ROW | 0 | 101024.23 |  |  | 101024.23 | n.m.
399 | P17110001 | Chadwick Station Work | 9010628.817 | 78478.64 | 9892.55 | 9155.07 | 97526.26 | 1.082%
400 | A15710041 | Grayson Fiber Ext TelModFib | 17193.976 | 84223.87 | 465.72 | 9400.83 | 94090.42 | 547.2%
401 | P18221013 | Beaver Creek Remote End | 0 | 71259.82 | 4662.48 | 16060.07 | 91982.37 | n.m.
402 | P11161023 | Stanville Ext TLINE KPCo | 0 | 83822.88 | 262.08 | 7645.1 | 91730.06 | n.m.
403 | P13064002 | T/KP/Hazard Station / OPCO | 1703014.064 | 73575.98 | 8010.75 | 7096 | 88682.73 | 5.207%
404 | P17083001 | Garrett-Soft Shell 138kV TLINE | 281178.243 | 76169.62 | 1650.5 | 8990.77 | 86810.89 | 30.87%
405 | A17938021 | KPCO-Trans-Security AccSys-Est | 0 | 67065.51 | 7588.56 | 6726.14 | 81380.21 | n.m.
406 | DR19K06D0 | Breaker Repl - Bellefonte | 0 | 79394.47 | 20.67 | 1076.05 | 80491.19 | n.m.
407 | P17225003 | Moore Hollow 138kV Extension | 1041366.793 | 52580.23 | 19660.94 | 5070.25 | 77311.42 | 7.424%
408 | B180KYTRE | T/KP/Transmission Region Tools | 0 | 73246.37 |  |  | 73246.37 | n.m.
409 | P17225013 | Ramey 138 kV Extension TLINE | 3256796.772 | 66827.98 | 2285.92 | 288.91 | 69402.81 | 2.131%
410 | P11063002 | TKYHazard Station Improvemen | 0 | 60676.97 |  | 7029.03 | 67706 | n.m.
411 | DR19K05D0 | Hazard DA 2019 - Hazard Sta | 0 | 59897.83 | 467.07 | 5253.79 | 65618.69 | n.m.
412 | P19215003 | Chadwick - England Hill TLINE | 0 | 54392.82 | 596.05 | 5537.79 | 60526.66 | n.m.
413 | P18025006 | Kewanee 138 Ext ROW | 14200.471 | 58953.9 |  | 503.25 | 59457.15 | 418.7%
414 | P19091003 | Middle Creek- Prestonsburg | 0 | 49475.84 | 90.49 | 9821.39 | 59387.72 | n.m.
415 | P17084003 | Cancel - DO NOT USE | 2331354.843 | 39165.29 | 7318.23 | 12797.32 | 59280.84 | 2.543%
416 | A15702053 | Beaver Creek-Betsy Lane Remedi | 0 | 49324.73 | 1281.78 | 3758.89 | 54365.4 | n.m.
417 | A15702032 | Hazard-Bonnyman Str. Replace | -0.267 | 37975.41 | 3031.41 | 3547.88 | 44554.7 | -16687154%
418 | A15702036 | Daisy-Clover Fork Str. Replace | 50.908 | 33180.05 | 3894.2 | 3507.99 | 40582.24 | 79717%
419 | A15042007 | Highland-Raceland FC ADSS | 0 | 25748.18 | 6582.61 | 2312.66 | 34643.45 | n.m.
420 | B180KYCSV | T/KY/Customer Service | 0 | 31411.12 | 277.98 | 2656.33 | 34345.43 | n.m.
421 | TA1807311 | T/KPCO/SEL GE Relay | 0 | 29640.87 | 244.2 | 2308.61 | 32193.68 | n.m.
422 | P18221005 | Beaver Creek - Fleming 69kV | 0 | 27665.02 | 158.86 | 3985.71 | 31809.59 | n.m.
423 | P19091012 | Middle Creek Station Land | 0 | 31539.88 |  |  | 31539.88 | n.m.
424 | A15702006 | KYPCo BAT HCP | 0 | 27711.61 | 2575.2 |  | 30286.81 | n.m.
425 | DR19K06D1 | RTU Repl - Bonnyman | 0 | 24147.02 | 679.52 | 2099.32 | 26925.86 | n.m.
426 | A15710024 | Beaver Creek TTMP | 0 | 22256.86 | 1555.19 | 2486.22 | 26298.27 | n.m.
427 | P17084007 | Myra 138kV Extension TLINE | 1584958.649 | 23486.5 | 1441.58 | 1348.68 | 26276.76 | 1.658%
428 | KYCR30003 | KY CR Bellefonte Sta | 0 | 17518.21 | 5580.08 | 2145.56 | 25243.85 | n.m.
429 | P19092013 | Allen - Prestonsburg TLINE | 0 | 22137.64 | 152.83 | 2840.35 | 25130.82 | n.m.
430 | A20705052 | Coleman - Stone 69kV Pre Eng | 0 | 22521.66 | 220.91 | 2006.7 | 24749.27 | n.m.
431 | P19104010 | Bellefonte Ext (KY) Line work | 0 | 21069.91 | 224.77 | 2095.85 | 23390.53 | n.m.
432 | P11161010 | B.Layne - Allen 46 kV KPCo | 0 | 4678.06 | 16801.81 | 415.25 | 21895.12 | n.m.
433 | A20705037 | Big Sandy - Thelma Pre Eng | 0 | 19097.66 | 258.18 | 2026.25 | 21382.09 | n.m.
434 | A16902001 | Big Sandy Remote End Relaying | 0 | -14488.57 | 32407.93 | 1689.13 | 19608.49 | n.m.
435 | P17225001 | Moore Hollow 138kV Station | 911063.686 | 8240.24 | 8148.12 | 3131.07 | 19519.43 | 2.142%
436 | A20705028 | Sprigg-Barrenshe 69kV Pre Eng | 0 | 14739.01 | 252.44 | 2314.02 | 17305.47 | n.m.
437 | P19215005 | Chadwick - Leach TLINE | 0 | 14995.93 | 147.68 | 1544.19 | 16687.8 | n.m.
438 | B180KYRMB | Reimbursable-DOP-180 Kentucky | 0 | 13667.37 | 1.83 | 1448.07 | 15117.27 | n.m.
439 | P17083003 | Garrett Switch (Removal) | 0 | 13446.98 | 232.86 | 1350.22 | 15030.06 | n.m.
440 | P19092019 | Allen - Prestonsburg ROW | 0 | 14270.25 |  |  | 14270.25 | n.m.
441 | P19305001 | Belfry - Stone TLINE | 0 | 12691.42 | 1.15 | 1564.37 | 14256.94 | n.m.
442 | DP16K03C0 | Tygart Sta - T line work | 0 | 13141.03 | 18.31 | 850.04 | 14009.38 | n.m.
443 | A17750109 | Allen-Prestonsburg Fld sliding | 0 | 12305.83 | 216.1 | 1294.38 | 13816.31 | n.m.
444 | A18730003 | Hazard-Jackson Str. Replc ROW | 0 | 8643.91 | 3902.54 | 1014.46 | 13560.91 | n.m.
445 | A20705029 | Barrenshe-Coleman Pre Eng | 0 | 11717.01 | 184.22 | 1652.25 | 13553.48 | n.m.
446 | A18730004 | Hazard-Fleming Str. Replc ROW | 0 | 11056.82 | 913.44 | 918.64 | 12888.9 | n.m.
447 | A15710052 | 2BCXLD Falcon - West Paintsvil | 1104.085 | 12629.2 |  |  | 12629.2 | 1144%
448 | P18221002 | Dorton - Fleming 138kV | 0 | 10946.75 | 139.78 | 1363.49 | 12450.02 | n.m.
449 | P17076001 | Kenwood Extension TLINE | 260631.397 | 8017.19 | 3623.96 | 754.65 | 12395.8 | 4.756%
450 | P17083005 | Hays Branch S.S | 0 | 10882.9 | 147.73 | 1053.44 | 12084.07 | n.m.
451 | A15710036 | Hays Branch TTMP | 0 | 9879.1 | 814.65 | 1155.35 | 11849.1 | n.m.
452 | P19215001 | Leach Station Work | 0 | 10374.73 | 16.49 | 1319.58 | 11710.8 | n.m.
453 | A18730005 | Daisy - Clover Fork ROW | 0 | 9679.63 | 807.63 | 799.05 | 11286.31 | n.m.
454 | P11161022 | Beaver Cr - Betsy L TLINE KPCo | 0 | 10400.58 | 88.21 | 778.52 | 11267.31 | n.m.
455 | A18730001 | Hazard-Bonnyman Str Replce ROW | 0 | 9604.98 | 857.13 | 801.69 | 11263.8 | n.m.
456 | P17110003 | Bellefonte Remote end Work | 311802.957 | 7805.21 | 2646.74 | 750.75 | 11202.7 | 3.593%
457 | A18730013 | Baker - Don Marquis STR 162-26 | 0 | 8685.47 |  | 2221.55 | 10907.02 | n.m.
458 | A20705035 | Middle Creek-Falcon 46kV Remvl | 0 | 9602.33 | 115.32 | 879.17 | 10596.82 | n.m.
459 | A18502002 | Baker 765 Firewall Install | 0 | 10577.88 |  |  | 10577.88 | n.m.
460 | A20705083 | Bellefonte 34.5kV St Needs Asm | 0 | 9593.16 | 80.84 | 885.81 | 10559.81 | n.m.
461 | A15710022 | Morgan Fork TTMP | 0 | 9004.58 | 487.51 | 944.17 | 10436.26 | n.m.
462 | SI180KYRE | TBSIKyP-KENTUCKY SYS REHAB | 0 | 8720.71 | 583.92 | 1128.31 | 10432.94 | n.m.
463 | A20705082 | Bellefonte138kV&69kV Needs Asm | 0 | 9267.85 | 77.76 | 833.84 | 10179.45 | n.m.
464 | A15710037 | Leon TTMP | 27498.787 | 8367.2 | 193.43 | 1549.96 | 10110.59 | 36.77%
465 | P19092007 | Allen -East Prestonsburg TLINE | 0 | 8977.01 | 107.42 | 945.43 | 10029.86 | n.m.
466 | A18730002 | Jackson-Helech Str Rplc ROW | -0.043 | 5391.56 | 2772.62 | 1289.78 | 9453.96 | -21985953%
467 | P19092008 | Allen -East Prestonsburg ROW | 0 | 9376.12 |  |  | 9376.12 | n.m.
468 | A17750107 | Prestonsburg-Thelma69kVSlidROW | 0 | 8310.75 | 78.59 | 811.21 | 9200.55 | n.m.
469 | A20705077 | JohnsC - LeslieN1 69 Needs Asm | 0 | 8274.17 | 20.01 | 778.3 | 9072.48 | n.m.
470 | A20705078 | LeslieNo1-Hatfield69 NeedsAsm | 0 | 7974.17 | 25.29 | 1004.49 | 9003.95 | n.m.
471 | P14030008 | T/KP/Leslie Station Work | 156314.365 | 5235.97 | 3111.23 | 507.86 | 8855.06 | 5.665%
472 | A20705073 | Sprigg-StoneKP 46kV KY | 0 | 7834.26 | 41.46 | 820.42 | 8696.14 | n.m.
473 | B180KYSRC | T/KY/Non-Specific Work-Station | 155059.949 | 7918.43 | 54.09 | 711.39 | 8683.91 | 5.6%
474 | A19750101 | B Sandy - Broadf 765 Slide ROW | 0 | 7780.32 |  |  | 7780.32 | n.m.
475 | P19092011 | McKinney -Allen reconfigure | 0 | 6735.43 | 49.88 | 753.34 | 7538.65 | n.m.
476 | A20705036 | Middle Creek-Prestonsburg Rebu | 0 | 6400.91 | 84.61 | 602.48 | 7088 | n.m.
477 | A15710044 | 2 BCXLD Beckham - Vicco TelMod | 1182.945 | 7056.38 |  | -1.4211e-14 | 7056.38 | 596.5%
478 | P17110002 | Bellefonte - Grangston Cut in | 265697.018 | 5742.07 | 690.21 | 570.97 | 7003.25 | 2.636%
479 | P13064003 | T/KP/Wooton Station - Station | 219377.045 | 2692.34 | 3941.66 | 289.68 | 6923.68 | 3.156%
480 | P19215004 | Chadwick - England Hill ROW | 0 | 6805.92 |  |  | 6805.92 | n.m.
481 | A20705067 | McInness SW Needs Assessment | 0 | 6204.81 | 24.17 | 524.95 | 6753.93 | n.m.
482 | A15710058 | Hazard Station TTMP | 11726.091 | 6345.12 |  | 333.88 | 6679 | 56.96%
483 | P19104012 | Bellefonte Ext (KY) ROW | 0 | 6200.94 | 20.31 |  | 6221.25 | n.m.
484 | A17042001 | Big Sandy-Baker 138kV Tie | 0 | 5717.39 |  | 456.01 | 6173.4 | n.m.
485 | P19305010 | Stone Station Work | 0 | 5486.28 | 0.72 | 624.5 | 6111.5 | n.m.
486 | P19215006 | Chadwick - Leach ROW | 0 | 6044.69 |  |  | 6044.69 | n.m.
487 | P18221003 | Hazard - Fleming 69kV | 0 | 4653.05 | 86.86 | 736.92 | 5476.83 | n.m.
488 | P17084026 | Beaver Creek - Fleming Cut in | 0.87 | 2885.04 | 2273.55 | 309.04 | 5467.63 | 628463%
489 | P16116005 | Stinnett -Pineville TL to KPCo | 92659.716 | 4812.58 |  | 579.22 | 5391.8 | 5.819%
490 | A13212035 | Bellefonte Telecom Legacy Pilo | 0 | 4725.57 |  | 391.5 | 5117.07 | n.m.
491 | A20705001 | Inez Station Pre-Eng | 0 | 4251.35 | 38.49 | 739.58 | 5029.42 | n.m.
492 | A15710043 | 2BCXLD Topmost 138 - Beckham 1 | 1104.085 | 4843.62 |  | -3.5527e-14 | 4843.62 | 438.7%
493 | A15710061 | Johns Creek Station TTMP | 7817.394 | 4379.91 | 16.84 | 444.26 | 4841.01 | 61.93%
494 | 000025230 | 2018 Gen Plt Cap Blkt - KYPC-T | 0 | 3995.4 | 46.4 | 732.29 | 4774.09 | n.m.
495 | P13064020 | T/KP/Hazard - Jackson 69kV ROW | 5336.503 | 3994.01 |  | 475.48 | 4469.49 | 83.75%
496 | P19092012 | Betsy Layne - Allen Reconfigur | 0 | 3979.82 | 34.68 | 444.18 | 4458.68 | n.m.
497 | P19092017 | McKinney - Allen ROW | 0 | 4409.79 |  |  | 4409.79 | n.m.
498 | P18221004 | Fleming - Fremont 69kV | 0 | 3710.42 | 69.42 | 555.25 | 4335.09 | n.m.
499 | A15702025 | Baker 765 kV PK Removals | 0 | 3960.4 |  | 358.43 | 4318.83 | n.m.
500 | P17225015 | East Park - Princess 138kV TL | 3634720.176 | 2493.25 | 1474.39 | 282.83 | 4250.47 | 0.1169%
501 | P17110005 | Chadwick - Leach Relocation | 275633.565 | 3293.15 | 592.57 | 332.72 | 4218.44 | 1.53%
502 | P19091004 | Middle Creek- Prestonsburg ROW | 0 | 3962.3 |  |  | 3962.3 | n.m.
503 | P18221010 | Dorton Remote End | 0 | 3505.13 | 59.19 | 317.78 | 3882.1 | n.m.
504 | A15710045 | 2BCXLD Vicco - Jeff TelModFib | 112570.584 | 3861.87 |  | 5.6843e-14 | 3861.87 | 3.431%
505 | P19092018 | Betsy Layne - Allen ROW | 0 | 3666.22 |  |  | 3666.22 | n.m.
506 | A15710046 | 2BCXLD Jeff - Hazard TelModFib | 84427.938 | 3427.87 |  | 0 | 3427.87 | 4.06%
507 | A14068005 | Ashland to Coalton Fiber Build | 0 | 3088.82 |  | 319.87 | 3408.69 | n.m.
508 | P14030102 | Leslie - Wooton TL to KPCo | 439418.079 | 2888.51 | 0 | 339.7 | 3228.21 | 0.7347%
509 | P17083002 | Garrett - Soft Shell 138kV ROW | 56818.812 | 3106.85 |  |  | 3106.85 | 5.468%
510 | P18025007 | Cedar Creek Remote End | 0 | 2454.74 | 385.83 | 239.86 | 3080.43 | n.m.
511 | A15710064 | 2BCXLD Sprigg-Cinderella KY Te | 91204.067 | 3011.28 | 3.9968e-15 | -27.82 | 2983.46 | 3.271%
512 | A20705057 | Big Sandy Station Pre Eng | 0 | 2711.27 | 18.04 | 248.28 | 2977.59 | n.m.
513 | A15710047 | 2BCXLD Jeff - Daisy TelModFib | 165728.921 | 2969.08 |  | 1.4211e-14 | 2969.08 | 1.792%
514 | A15702013 | T/KP/Leach:S.Neal pilot wire | 0 | 2567.79 |  | 271.32 | 2839.11 | n.m.
515 | P17110006 | Chadwick - Tri State #1 Reloca | 6290.554 | 2324.7 | 302.48 | 195.87 | 2823.05 | 44.88%
516 | P14030013 | Wooton Relaying Work & Telecom | 161792.441 | 1877.05 | 786.13 | 143.98 | 2807.16 | 1.735%
517 | P17110007 | Chadwick - Tri State #2 Reloca | 5091.318 | 2236.73 | 321.65 | 188.44 | 2746.82 | 53.95%
518 | P17083006 | Garrett - Eastern 138 TLN | 220353.643 | 2374.61 | 23.92 | 285.16 | 2683.69 | 1.218%
519 | A15710071 | Morehead Station TTMP | 0 | 2410.57 | 29.81 | 218.02 | 2658.4 | n.m.
520 | P16113004 | Cannonsburg-SNeal KY Remove | 0 | 2220.89 | 179.52 | 215.5 | 2615.91 | n.m.
521 | P14030104 | Leslie Ext Install to KPCo | 92643.808 | 1993.21 | 383.66 | 179.1 | 2555.97 | 2.759%
522 | P17084019 | Elwood - Cedar Cr. Reconfig. | 0.558 | 1748.41 | 397.86 | 175.14 | 2321.41 | 416023%
523 | P17084016 | CANCELLED | 0 | 941.6 | 1245.98 | 112.55 | 2300.13 | n.m.
524 | DP16K03C1 | Tygart Sta - T line work | 0 | 1651.41 | 6.83 | 184.91 | 1843.15 | n.m.
525 | P11161008 | Dewey Remote ends | 0 | 1660.08 |  | 155.81 | 1815.89 | n.m.
526 | A19511004 | Bonnyman SEL/GE Relay Upgrade | 0 | 1605.99 | 1.2 | 93.56 | 1700.75 | n.m.
527 | P11161009 | Morgan Fork Remote End | 0 | 1543.98 |  | 133.07 | 1677.05 | n.m.
528 | P17076005 | Prestonsburg - Thelma 69kV | 0 | 993.84 | 559.13 | 94.37 | 1647.34 | n.m.
529 | P17084022 | Henry Clay - Dorton Reconfig. | 7.54 | 1218.07 | 233.47 | 110.77 | 1562.31 | 20720%
530 | P19305009 | Hatfield Station Work | 0 | 1383.19 | 0.4 | 122.17 | 1505.76 | n.m.
531 | P17225017 | Bellefonte - Coalton 138 kV TL | 895857.654 | 680.61 | 705.95 | 73.89 | 1460.45 | 0.163%
532 | A15710042 | 2BCXL Topmost 138 TelModFib | 98499.258 | 1419.58 |  | -1.4211e-14 | 1419.58 | 1.441%
533 | P16113003 | Cannonsburg-SNeal ROW (KY) | 114586.801 | 1337.24 |  |  | 1337.24 | 1.167%
534 | P19305016 | Belfry - New Camp TLINE | 0 | 1206.16 | 0.37 | 85.43 | 1291.96 | n.m.
535 | A20705079 | McInnessMet69kV Needs Asm | 0 | 1004.38 | 4.59 | 107.26 | 1116.23 | n.m.
536 | SI180KYUN | TB SI KYPCO - KENTUCKY UNCAT | 0 | 822.07 | 286.76 |  | 1108.83 | n.m.
537 | A19511003 | Big Sandy SEL/GE Relay Upgrade | 0 | 1026.03 | 0.75 | 58.98 | 1085.76 | n.m.
538 | P17083031 | Eastern-Hays Branch SS TLINE | 556.35 | 954.36 | 3.35 | 113.22 | 1070.93 | 192.5%
539 | P17084036 | CANCELLED | 0 | 639.3 | 334.15 | 82.91 | 1056.36 | n.m.
540 | P17076010 | Van Lear - Kenwood Str Replace | 0 | 760.09 | 20.97 | 66.43 | 847.49 | n.m.
541 | P17083008 | Hays Br. - Morgan Frk. 138 TLN | 249.024 | 774.89 | 5.87 | 58.01 | 838.77 | 336.8%
542 | A15702054 | Stone TF Failre Rplcment | 0 | 754 |  | 68.73 | 822.73 | n.m.
543 | P19305002 | Belfry - Stone ROW | 0 | 811.74 |  |  | 811.74 | n.m.
544 | P19305017 | Belfry - New Camp ROW | 0 | 811.74 |  |  | 811.74 | n.m.
545 | A20705080 | Sidney 69kV Loop Needs Asm | 0 | 718.05 | 2.56 | 85.82 | 806.43 | n.m.
546 | A20705081 | Bevins 69kV Tap Needs Asm | 0 | 718.05 | 2.56 | 85.82 | 806.43 | n.m.
547 | A15710050 | 2BCXLD Pikesville SC-Johns Cr | 165728.921 | 780.22 |  |  | 780.22 | 0.4708%
548 | P18025013 | Sprigg - Beaver Cr. TLINE Work | 0 | 280.21 | 448.9 | 33.49 | 762.6 | n.m.
549 | DP14K02T0 | KP/Raccoon Sta - T ROW | 0 | 617.97 | 41.53 | 48.78 | 708.28 | n.m.
550 | P19305018 | New Camp Tap TLINE | 0 | 641.38 | 0.37 | 53.32 | 695.07 | n.m.
551 | P17084037 | Beaver Creek Remote End | 0 | 329.52 | 311.75 | 39.38 | 680.65 | n.m.
552 | P17083007 | Garrett - Eastern 138 ROW | 439794.427 | 673.37 |  |  | 673.37 | 0.1531%
553 | P17076006 | Kenwood Extension ROW | 99915.295 | 400.8 | 95.22 | 89.54 | 585.56 | 0.5861%
554 | P14030103 | Leslie - Stinnett TL to KPCo | 852224.104 | 233.54 | 309.04 | 27.92 | 570.5 | 0.06694%
555 | P16116002 | Stinnett - Pineville Removal | 0 | 374.84 | 126.97 | 30.59 | 532.4 | n.m.
556 | A15702062 | Morehead Station: Stn Entrnce | 17177.439 | 446.97 | 8.65 | 36.79 | 492.41 | 2.867%
557 | P16116003 | Stinnett - Pineville ROW KPCo | 83002.59 | 471.52 |  |  | 471.52 | 0.5681%
558 | P18221014 | Fleming (Jackhorn) 138KV ADSS | 0 | 384.07 | 3.93 | 34.53 | 422.53 | n.m.
559 | ITCB18000 | KENTUCKY POWER - TRANSM | 0 | 148.7 | 238.16 |  | 386.86 | n.m.
560 | P17083034 | Morgan Fork Remote End | 74.441 | 325.01 | 33.56 | 26.41 | 384.98 | 517.2%
561 | P14030002 | Stinnett Loop Install OPGW | 14743.599 | 141.13 | 186.75 | 16.87 | 344.75 | 2.338%
562 | P17084017 | Beaver Creek - Fremont Cut in | -0.322 | 111.73 | 147.85 | 13.35 | 272.93 | -84761%
563 | P18025010 | Kewanee Fiber Termination | 0 | 247.76 | 2.19 | 21.78 | 271.73 | n.m.
564 | P18025008 | Beaver Creek Remote End Work | 0 | 89.02 | 117.8 | 10.64 | 217.46 | n.m.
565 | P17225016 | East Park - Princess 138kV ROW | 175640.238 | 195.44 |  |  | 195.44 | 0.1113%
566 | P17225018 | Bellefonte - Coalton 138kV ROW | 3236277.35 | 163 |  |  | 163 | 0.005037%
567 | P17225014 | Ramey 138 kV Extension ROW | 45352.294 | 162.17 |  |  | 162.17 | 0.3576%
568 | P17084023 | Henry Clay - Elk. City Reconfi | 7.536 | 61.41 | 81.26 | 7.34 | 150.01 | 1991%
569 | P17084021 | CANCELLED | 583.88 | 43.22 | 57.19 | 5.16 | 105.57 | 18.08%
570 | P17084038 | Dorton Remote End | 0 | 42.82 | 56.67 | 5.12 | 104.61 | n.m.
571 | P17084020 | Elwood - Henry Cl. Recon. @ EL | 0.508 | 41.17 | 54.47 | 4.92 | 100.56 | 19795%
572 | A15702056 | Topmost SS Failure | 0 | 86.95 |  | 10.4 | 97.35 | n.m.
573 | A15042005 | Baker-Big Sandy Fiber Cable | 0 | 89.11 |  | 8.04 | 97.15 | n.m.
574 | P17084029 | New Henry Clay Extension | 0 | 35.9 | 47.5 | 4.29 | 87.69 | n.m.
575 | P17084013 | Henry Clay S.S Retirement | 0.594 | 34.89 | 46.16 | 4.18 | 85.23 | 14348%
576 | P18025009 | Cedar Creek Fiber Extension | 0 | 66.33 | 1.86 | 5.79 | 73.98 | n.m.
577 | P18025012 | Cedar Creek - Elwood TLINE Wor | 0 | 18.75 | 38.55 | 14.99 | 72.29 | n.m.
578 | P17084018 | Beaver Creek - Elwood Retire | 0 | 25.81 | 34.14 | 3.09 | 63.04 | n.m.
579 | P14030101 | Leslie - Clover Fork Line Work | 22755.031 | 10.02 | 13.26 | 1.2 | 24.48 | 0.1076%
580 | A19511007 | Wooton SEL/GE Relay Upgrade | 0 | 17.88 | 0.04 | 2.44 | 20.36 | n.m.
581 | A19511005 | Dewey SEL/GE Relay Upgrade | 0 | 17.84 | 0.01 | 1.02 | 18.87 | n.m.
582 | A19511006 | Hazard SEL/GE Relay Upgrade | 0 | 17.84 | 0.01 | 1.02 | 18.87 | n.m.
583 | A19511002 | Bellefonte SEL/GE Relay Upgrad | 0 | 7.76 | 0.02 | 1.06 | 8.84 | n.m.
584 | P17083026 | Hays Br-Soft Shell Trans Fiber | 67.715 | 2.86 | 5.26 | 0.34 | 8.46 | 12.49%
585 | P14030015 | Lesile - Stinnett Removal | 16832.186 | 2.4 | 5.03 | 0.28 | 7.71 | 0.04581%
586 | 000017437 | TLKYPHazard-Pineville 161kV | 0 | 7.46 |  |  | 7.46 | n.m.
587 | P14030016 | Leslie - Stinnett ROW (KPCo) | 533855.938 | 7.24 |  |  | 7.24 | 0.001356%
588 | A15710051 | 2BCXLD Johns Creek - Coleman T | 243902.931 | 7.276e-12 |  |  | 7.276e-12 | 2.983e-15%
589 | A15710048 | 2BCXLD Pikeville SC extension | 98499.258 | 0 |  |  | 0 | 0%
590 | A21212002 | Bellefonte 34kV - RTU Replacem | 0 | 0 | 0 | 0 | 0 | n.m.
591 | P19092021 | Cancel - Dwale Extension ROW | 0 | 0 |  |  | 0 | n.m.
592 | ETN000180 | T Kp T Anda | 0 | 4631371.41 |  | -4631371.41 | 0 | n.m.
593 | A16928015 | Leslie Station Spare Purchase | 0 | 0 | -17.18 | -0.01 | -17.19 | n.m.
594 | P17074005 | Millbrook - Siloam Cut in | 0 | -11.22 | -22.49 | -103.46 | -137.17 | n.m.
595 | P18066002 | Chadwick-Leach PQ Mit | 0.071 | -311.62 | -14.68 | -28.51 | -354.81 | -499732%
596 | A15705185 | Johns Creek 69kV Breaker Failu | 0 | -465.43 |  |  | -465.43 | n.m.
597 | P19092020 | Cancel -Dwale Extension T Line | 0 | 5.6843e-13 | 20.05 | -633.9 | -613.85 | n.m.
598 | A15702040 | CANCELLED | 0 | -1200 |  | -104.76 | -1304.76 | n.m.
599 | P18066005 | ASFI Tap PQ Mitigations | 202768.176 | -1205.83 | -55.95 | -114.16 | -1375.94 | -0.6786%
600 | P11161024 | Stanville Ext ROW KPCo | 0 | -1508.67 |  |  | -1508.67 | n.m.
601 | P18066001 | Chadwick - England Hill PQ Mit | 0.071 | -1412.45 | -134.04 |  | -1546.49 | -2178155%
602 | P18066003 | Kenova-Eng. Hill KY PQ Mit | 202768.176 | -1798.2 | -83.3 | -38.42 | -1919.92 | -0.9469%
603 | P11161026 | Betsy Layne - Allen ROW KPCo | 0 | -2856.67 | -275.55 |  | -3132.22 | n.m.
604 | P18025005 | Kewanee 138 Ext TLINE | 4758458.812 | -6806.56 | -5388.44 | -5834.3 | -18029.3 | -0.3789%
605 | P11161012 | B.Layne-S.Pikeville 69kV KPCo | 92333.018 | -36538.76 |  | 342.4 | -36196.36 | -39.2%
606 | P17225008 | Princess Station | 468620.05 | -35432.58 | -887.19 | -2363.8 | -38683.57 | -8.255%
607 | P18090001 | Inez Proactive Rehab Work | 0 | -18172.41 | -12640.81 | -7984.28 | -38797.5 | n.m.
608 | P11161007 | T/KP Line Work Betsy-Dewey | 0 | -43927.75 |  | 103.29 | -43824.46 | n.m.
609 | A15702049 | Cancel | 0 | -49059.73 |  |  | -49059.73 | n.m.
610 | P10115004 | Canceled | 0 | -66692.7 | 0.01 | -1673.58 | -68366.27 | n.m.
611 | A15702043 | Beaver Creek CB AB replace | 0 | -64002.01 | -3909.69 | -10602.97 | -78514.67 | n.m.
612 | A16905009 | Cancelled - DO NOT USE | 257154.082 | -201990.27 | -12266.01 | -26056.29 | -240312.57 | -93.45%
613 | A15702042 | Fleming XF/CB Replacements | 92501.93 | -227333.5 | -11456.24 | -40963.06 | -279752.8 | -302.4%
614 | A15702041 | Hazard CB/XF Replacements | 1033568.33 | -1285524.51 |  | -62894.39 | -1348418.9 | -130.5%
615 | 000025076 | Pikeville Transmission SC | 0 | -1925336.35 |  |  | -1925336.35 | n.m.
616 | Other Budgeted Projects |  | 13076423.94 | 0 | 0 | 0 | 0 | Other
617 | Total GLBU 180 (Transmission) |  | 95080929.298 | 54436671.532 | 1398469.97 | -4674.29 | 55830467.212 | 58.72%
618 | Total Kentucky Power CWIP Additions |  | 192326747.633 | 170547914.545 | 2826719.98 | 2424371.35 | 175799005.875 | 91.41%
619
620 | X00000317 | For Property Acctg Use Only - GLBU 110 | Property Acctg | -87085169.097 | -62953.32 |  | -87148122.417 | Property Acctg
621 | X00000288 | For Property Acctg Use Only - GLBU 117 | Property Acctg | -40066873.83 | -266554.98 | -3865490.91 | -44198919.72 | Property Acctg
622 | X00000306 | For Property Acctg Use Only - GLBU 180 | Property Acctg | -49850353.34 | -188213.18 |  | -50038566.52 | Property Acctg
623 | Total Kentucky Power Transfers to 101/106 |  |  | -177002396.267 | -517721.48 | -3865490.91 | -181385608.657
624
625 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year April 2019 - March 2020 |  | 192326747.633 | -6454481.722 | 2308998.5 | -1441119.56 | -5586602.782
626
627
628 | Definitions: |  |  |  | Reconciliation of AFUDC Capitalized to Section V, Schedule 8, Line 13 of the Company's Application
629 | (E)* | Represents AFUDC Debt and AFUDC Equity (Cost Components 023 and 024, respectively) |  |  | 2308998.5 | AFUDC Capitalized per General Ledger Reported on Line 625
630 | (F)* | Represents allocated construction overheads (Cost Component 020) |  |  | -74719.04 | Reconciling Item: Other Manual Credits to AFUDC Recorded in General Ledger
631 | n.m. | Not meaningful |  |  | 2383717.54 | AFUDC Capitalized per Property Subledger Reported in Section V, Schedule 8, Line 13
632 | Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.

## 12 Mos. Preceding Test Year
Schedule D (12 Months Preceding the Historical Test Year)
Kentucky Power Company
Case No. 2020-00174
Construction Projects for the 12 Months Preceding the Historical Test Year
April 2018 - March 2019
Actual Accumulated Costs - April 2018 through March 2019
Line No. | Project No. | Description of Project | Most Recent Budget Estimate | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost | Estimated Physical Percent Completed April 2018 Through March 2019
(A) | (B) | (C) | (I) | (D) | (E)* | (F)* | (G=D+E+F) | (H) = (G)/(I)
1 | GLBU 110 (Distribution)
2 | TREEREL18 | ROW Capital widening & removal | 5950480.57 | 4473512.43 | 235920.73 | 796897.54 | 5506330.7 | 92.54%
3 | 000007818 | KP/Small Local Asset Improv | 5049581.047 | 4447107.96 | 44676.73 | 873739.89 | 5365524.58 | 106.3%
4 | EDN014680 | Ds-Kp-Ai Pole Replacement | 2911291.21 | 3273043.55 | 6303.58 | 612974.73 | 3892321.86 | 133.7%
5 | EON011326 | Line Transformer/Kp | 2913720.671 | 3062409.36 |  | 590400.05 | 3652809.41 | 125.4%
6 | 000001818 | KY/Svc Restoration NonMjr Evt | 2332477.401 | 2973582.75 | 908.26 | 585542.46 | 3560033.47 | 152.6%
7 | 000005234 | KyPCo-D Capital Software Dev | 0 | 3341837.641 |  |  | 3341837.641 | n.m.
8 | EDN014651 | Ds/Kp/Cs-New Customers | 2473697.281 | 2486770.83 | 1995.21 | 460263.12 | 2949029.16 | 119.2%
9 | EDN100033 | Ds/Kp/C&I New | 1356127.519 | 2041511.74 | 4816.77 | 517458.68 | 2563787.19 | 189.1%
10 | 000007599 | KP-Failed Equip No Outage | 1682296.152 | 2006236.16 | 6550.15 | 402233.1 | 2415019.41 | 143.6%
11 | 000009160 | Forestry KP D Base R W | 2579889.794 | 1996884.28 |  | 370483.24 | 2367367.52 | 91.76%
12 | TREEREL19 | ROW Capital widening & removal | 2211748.24 | 2211748.24 |  |  | 2211748.24 | 100%
13 | 000016528 | KYCutout-Arrester | 2160652.652 | 1664515.98 | 8979.32 | 338495.23 | 2011990.53 | 93.12%
14 | EDN014694 | Ds-Kp-Ai Other Make Ready | 572395.655 | 1474278.91 | 783.7 | 313058.61 | 1788121.22 | 312.4%
15 | P11161006 | D/KP Stanville Station KPCo | -758580.984 | 1414030.56 | 53876.15 | 296564.28 | 1764470.99 | -232.6%
16 | EDN014720 | Ds-Kp-Ai Recloser Replacement | 1232264.113 | 1384511.3 | 16838.7 | 263747.58 | 1665097.58 | 135.1%
17 | DCTSUVLKY | KY CATS Monthly Unvouch Liab | 276647.79 | 1485695.06 |  |  | 1485695.06 | 537%
18 | DR18K03B5 | Breaker Rpl - S Pikeville | 88197.81 | 1153387.87 | 34507.75 | 201943.57 | 1389839.19 | 1576%
19 | DR15K02B0 | KP/Princess Station DStation | 1853487.361 | 1098587.13 | 18370.53 | 180968.78 | 1297926.44 | 70.03%
20 | A15702051 | Pikeville Stn RepBank#1 | 488204.78 | 995127.78 | 22562.95 | 202099.85 | 1219790.58 | 249.9%
21 | ITCB11000 | KENTUCKY POWER - DIST | 0 | 1161835.97 | -58206.77 |  | 1103629.2 | n.m.
22 | A16928013 | Mobile KPCo 118 Purchase | 90846.85 | 855821.83 | 86459.23 | 156633.94 | 1098915 | 1210%
23 | 000025229 | 2018 Gen Plt Cap Blkt - KYPC-D | 0 | 1078347.89 | 11168.9 |  | 1089516.79 | n.m.
24 | 000004737 | KPSectionalizing Program | 916879.772 | 825228.24 | 5508.79 | 163937.32 | 994674.35 | 108.5%
25 | A16928014 | Skid Station KPCo 1002 Purchas | 100775.08 | 744699.58 | 70806.06 | 126374.41 | 941880.05 | 934.6%
26 | B110KYSRR | D/KY/Non-Specific Work - Sta | 1091691.689 | 621264.14 | 32547.14 | 134878.5 | 788689.78 | 72.24%
27 | DR15K02A0 | KP/Princess Station D Line | 1296646.383 | 626520.62 | 1289.08 | 109527.98 | 737337.68 | 56.86%
28 | IT110BILL | Corp Prgrm Billing - KP Distri | 0 | 732269.02 |  |  | 732269.02 | n.m.
29 | EDN100577 | Ds-Kp-Ai Ckt Inspections | 1210003.64 | 568905.91 | 3240.09 | 110389.44 | 682535.44 | 56.41%
30 | DR18K04B0 | Pikeville Sta - Trans upgrade | 316595.35 | 576024.51 | 9968.65 | 78267.22 | 664260.38 | 209.8%
31 | EDN012370 | Ds/Kp/Public Relocation | 1509019.438 | 503291.12 | 5595.48 | 121656.31 | 630542.91 | 41.78%
32 | P11161002 | D/KP/S.PIKEV -Remote End | 288029.232 | 501262.19 | 16430.43 | 99410.14 | 617102.76 | 214.3%
33 | KY5YCYCLE | KY D 2017-00179 | 610067.82 | 610067.82 |  |  | 610067.82 | 100%
34 | DMS19KK01 | KP/ME/Wind Storm 02/24/19 | 606305.52 | 488637.85 | 42.57 | 117667.67 | 606348.09 | 100%
35 | IT1101421 | Maximo Imp - KYP - D | 0 | 509001.79 | 55376.49 |  | 564378.28 | n.m.
36 | EDN011333 | Customer Meter/Kp | 728171.525 | 516952.6 |  | 46107.15 | 563059.75 | 77.33%
37 | P18025001 | Kewanee Station - Baseline Wor | 444780.18 | 450591.39 | 10307.32 | 89365.14 | 550263.85 | 123.7%
38 | A15710030 | Beavercreek TS TTMP | 69162.63 | 433306.87 | 15160.46 | 78954.61 | 527421.94 | 762.6%
39 | 000025522 | Lovely\Lovely Sectionalizing | 117821.3 | 379689.31 | 9628.3 | 76469.73 | 465787.34 | 395.3%
40 | P11161021 | Stanville DLINE Components | -6050.3 | 388772.94 | 2016.58 | 74547.35 | 465336.87 | -7691%
41 | EDN015042 | Ds-Kp-Small Wire Repl Ovhd | 469768.64 | 321816.69 | 745.07 | 63450.22 | 386011.98 | 82.17%
42 | DMS18KK03 | KY/ME/Wind Storm 04/04/18 | 578.75 | 240881.96 | 165.09 | 36515.4 | 277562.45 | 47959%
43 | A17750006 | Cannonsburg Failed TR1 | 39734.47 | 223540.92 | 659.2 | 46891.91 | 271092.03 | 682.3%
44 | 000025514 | Mayking Milstone SH | 55876.95 | 214104.46 | 1108.63 | 41266.04 | 256479.13 | 459%
45 | 000025595 | Fords Br. Shelby Circuit. | 1.65 | 195623.74 | 1455.92 | 37148.71 | 234228.37 | 14195659%
46 | P16113007 | Coalton Line Relaying | 65093.808 | 176797.26 | 4502.47 | 28174.81 | 209474.54 | 321.8%
47 | KYCR012DL | KP/VoltVar Circ Reconfig DLine | 31335.99 | 201525.92 | 6073.34 |  | 207599.26 | 662.5%
48 | EDN014658 | Ds/Kp/Cs-Upgrades | 97136.012 | 169210.53 | 33.77 | 34430.31 | 203674.61 | 209.7%
49 | 000002241 | KP-Damage Claims-Reimburse | 24011.559 | 157826.99 | 385.93 | 40609.77 | 198822.69 | 828%
50 | DMS18KK05 | KY/ME/Wind Storm 7/20/18 | 1778.53 | 165093.55 | 19.96 | 27713.07 | 192826.58 | 10842%
51 | 000025524 | Feds Cr. Exit Relocation | 64173.79 | 137982.86 | 2064.07 | 24791.93 | 164838.86 | 256.9%
52 | P11161003 | Allen Remote End | 130947.893 | 132948.94 | 4861.88 | 23388.71 | 161199.53 | 123.1%
53 | DX16K02A0 | Coalton Sta - US RT 60 PPR | 86845.53 | 96142.27 | 18637.7 | 20795.78 | 135575.75 | 156.1%
54 | DMS18KK08 | KP/Pre Valid Major Event 8 | 16714.44 | 108362.77 | 12.04 | 22963.09 | 131337.9 | 785.8%
55 | DMS18KK02 | KY/Pre Valid Major Event | 0 | 106379.76 |  | 21237.38 | 127617.14 | n.m.
56 | EDN100044 | Ds/Kp/C&I Upgrades | 21813.82 | 99555.44 | 491.43 | 23177.04 | 123223.91 | 564.9%
57 | DX17K01B0 | Elwood Sta - Repl Brkr R | 4116.58 | 93452.59 | 9739.14 | 17232.98 | 120424.71 | 2925%
58 | 000025570 | BlueGrass\Walker Town Tie | 0 | 97040.98 | 280.81 | 17533.72 | 114855.51 | n.m.
59 | DX17K02B0 | Second Fork Sta - add SCADA | 7183.37 | 85799.79 | 5042.58 | 14621.48 | 105463.85 | 1468%
60 | P18025002 | Kewanee Station Land Purchase | 1402.8 | 103082.1 |  |  | 103082.1 | 7348%
61 | 000024645 | KYPCo-D General Plt Cap Blkt | 2856546.925 | 102601.14 | 471 |  | 103072.14 | 3.608%
62 | DP14K02B0 | KP/Raccoon Sta - 30 MVA 138-34 | 21046.19 | 69594.61 | 3071.77 | 14064.15 | 86730.53 | 412.1%
63 | DR18K02B0 | Jeff Sta - Add DRTU | 53992.28 | 71227.68 | 653.99 | 8189.87 | 80071.54 | 148.3%
64 | A13002013 | D/KP/Highland-Repl BPLC Rly | 17583.99 | 64464.32 | 4224.97 | 10019.83 | 78709.12 | 447.6%
65 | 000007615 | KP-Cust Req Relocate | 99376.922 | 48972.13 | 209.37 | 29140.2 | 78321.7 | 78.81%
66 | 000007558 | KP-PQ-QOS Mitigation | 757071.945 | 70276.44 | 18.92 | 3684.61 | 73979.97 | 9.772%
67 | P17084024 | CANCELLED | 1539.07 | 59239.45 | 3119.86 | 10965.08 | 73324.39 | 4764%
68 | DR18K02B3 | Vicco Sta - Add DRTU | 49821.96 | 64691.97 | 542.46 | 8044.24 | 73278.67 | 147.1%
69 | A16928012 | Pikeville Purchase Spare | -221156.06 | 46509.38 | 16021.05 | 9188.66 | 71719.09 | -32.43%
70 | A15710010 | Catalpa TS Shelter upgradeTTMP | 1170.26 | 71699.76 |  |  | 71699.76 | 6127%
71 | A13002014 | D/KP/Raceland-Repl BPLC Rly | 16805.96 | 56607.15 | 4677.48 | 9734.97 | 71019.6 | 422.6%
72 | A16928010 | Ashland Srvc Purch Sp Transf | 2672.51 | 39634.31 | 18931.08 | 7092.71 | 65658.1 | 2457%
73 | EDN103175 | Ds Kp Anda | 10789.802 | 9177696.09 |  | -9112751.33 | 64944.76 | 601.9%
74 | A15710011 | Hagler Hill TS Tele Modernizat | 511.61 | 63515.91 |  |  | 63515.91 | 12415%
75 | DMS18KK04 | KY/Pre Valid Major Event | 0 | 52341.97 | 24.56 | 10170.84 | 62537.37 | n.m.
76 | A15710017 | West Paintsville Telecom Moder | 4883.6 | 38328.45 | 3722.81 | 7181.09 | 49232.35 | 1008%
77 | 000025516 | Lilly Cornett Woods SH | 0 | 40505.76 | 274.62 | 6767.38 | 47547.76 | n.m.
78 | DR18K02A0 | Hazard 2018 DA Plan | 40759.52 | 31319.38 | 70.88 | 9440.14 | 40830.4 | 100.2%
79 | A15710012 | Busseyville Telecom Modernizat | 3490.64 | 32614.84 | 1127.91 | 6319.28 | 40062.03 | 1148%
80 | A15710040 | South PIkeville TTMP | 1890.43 | 29840.44 | 857.12 | 4891.58 | 35589.14 | 1883%
81 | DMS18KK09 | KP/Pre Valid Major Event 9 | -16293.02 | 30686.66 | 28.2 | 4604.55 | 35319.41 | -216.8%
82 | 000025521 | Bishop Knobb SH | 0 | 28550.32 | 3.88 | 5377.56 | 33931.76 | n.m.
83 | DMS18KK06 | KP/Pre Valid Major Event 6 | 1494.35 | 24752.31 | 14.02 | 4442.95 | 29209.28 | 1955%
84 | A15710026 | Jenkins Station TTMP | 36734.699 | 23192.18 |  | 5998.66 | 29190.84 | 79.46%
85 | P17076002 | Kenwood Station | 6555.77 | 15220.87 | 6660.8 | 5418.24 | 27299.91 | 416.4%
86 | A15710039 | Pikeville TTMP | 3687.86 | 21000.86 | 433.99 | 4019.01 | 25453.86 | 690.2%
87 | A17212002 | Hayward RTU Replacement | 631.2 | 19834.48 | 595.92 | 4381.34 | 24811.74 | 3931%
88 | P17225011 | Hoods Creek Land Purchase | 3672.41 | 22739.67 |  |  | 22739.67 | 619.2%
89 | 000025820 | Kentucky Power State Office | 0 | 21476.47 | 85.03 |  | 21561.5 | n.m.
90 | A15710013 | Cannonsburg Telecom Modernizat | 2902.8 | 17488.36 | 594.76 | 3384.66 | 21467.78 | 739.6%
91 | P17084001 | Cancel: DO NOT USE | 1534.4 | 11436.43 | 4159.45 | 5132.16 | 20728.04 | 1351%
92 | DMS18KK01 | KY/ME/Snow Storm 3/12/18 | 6.68 | 17044.54 |  | 2768.96 | 19813.5 | 296609%
93 | A15710021 | Allen Station TTMP | 904.19 | 14716.27 | 1737.02 | 2552.49 | 19005.78 | 2102%
94 | A15710038 | Grayson TTMP | 5306.6 | 12812.41 | 413.55 | 2832.09 | 16058.05 | 302.6%
95 | A13212036 | Ashland (KY) Telecom Pilot Wir | 3012.82 | 12791.32 |  | 2263.68 | 15055 | 499.7%
96 | EDN014701 | Ds Kp Ai Support Cs Res | 9014.82 | 11833.29 | 11.29 | 2383.77 | 14228.35 | 157.8%
97 | A15710005 | Ashland POP Tele Modernization | 9301.14 | 14222.16 |  |  | 14222.16 | 152.9%
98 | A15710019 | Coalton Station TTMP | 8945.12 | 9652.86 | 932.83 | 2173.6 | 12759.29 | 142.6%
99 | KYCR31109 | KY CR Wurtland Sta | 0.42 | 10775.86 |  | 1973.84 | 12749.7 | 3035643%
100 | 000014717 | KY/DOP/Copper Theft | 100533.714 | 9569.08 | 18.33 | 2163 | 11750.41 | 11.69%
101 | ITCW11004 | KY Next Generation Radio Sys | 0 | 30375.04 | -18683.29 |  | 11691.75 | n.m.
102 | EDN014687 | Ds-Kp-Ai Aepc Make Ready | 1077.11 | 6807.62 | 255.75 | 4419.33 | 11482.7 | 1066%
103 | A15710016 | Oakland TS Telecom Modernizati | 631.41 | 9181.27 | 2035.15 |  | 11216.42 | 1776%
104 | P12057001 | T/KP/BECKHAM-(KPCo) | -0.173 | 6343.4 |  | 4664.3 | 11007.7 | -6362832%
105 | P17084005 | Myra Station | 1977.82 | 8082.45 | 1232.59 | 1539.45 | 10854.49 | 548.8%
106 | 000007577 | KP-UG Cable Repl Failure | 114.31 | 8538.68 | 133.36 | 1804.57 | 10476.61 | 9165%
107 | KYCR34119 | KY CR Fords Branch Sta | 7.61 | 8492.87 |  | 1402.26 | 9895.13 | 130028%
108 | KYCR30106 | KY CR Russell Sta | 0 | 8215.44 |  | 1471.46 | 9686.9 | n.m.
109 | A15710020 | Prestonburg Station TTMP | 954.62 | 6368.85 | 1401.24 | 1194.2 | 8964.29 | 939%
110 | KYCR30009 | KY CR Highland Sta | 0 | 7016.4 |  | 1270.09 | 8286.49 | n.m.
111 | P18025003 | CANCELLED | 25876.23 | 6372.49 | 46.46 | 583.57 | 7002.52 | 27.06%
112 | P17084009 | Burton Station Retirement | 1509.9 | 4631.1 | 1249.49 | 841.52 | 6722.11 | 445.2%
113 | A20212001 | Lovely RTU Reliability | 138.07 | 5451.99 | 156.7 | 1095.22 | 6703.91 | 4855%
114 | P17076003 | Prestonsburg Remote End Work | 1017.51 | 2296.74 | 2941.98 | 772.68 | 6011.4 | 590.8%
115 | P17225006 | Ramey Station | 315.11 | 3477.35 | 852.19 | 1390.51 | 5720.05 | 1815%
116 | P17076011 | Distribution work at Kenwood | 921.7 | 4350.2 | 180.16 | 895.54 | 5425.9 | 588.7%
117 | P17084014 | Henry Clay Station Retirement | 562.41 | 3068.64 | 1569.32 | 572.34 | 5210.3 | 926.4%
118 | A13212029 | Elwood (KP) - Telecom Legacy | 0 | 520.47 |  | 3567.73 | 4088.2 | n.m.
119 | A15702009 | Prestonsburg Rpl OCB C | 0 | 1162.1 |  | 2724.6 | 3886.7 | n.m.
120 | EDN101114 | Ds Kp Ai Support Cs C I | -1232.27 | 2467.97 | 3.44 | 1033.37 | 3504.78 | -284.4%
121 | KYCAPTOOL | KY Purch. Cap Tools | 3452.98 | 3452.98 |  |  | 3452.98 | 100%
122 | KYCR33111 | KY CR Stinnett Sta | 0 | 2925.07 |  | 494.2 | 3419.27 | n.m.
123 | EDN014673 | Ds-Kp-Ai Pole Reinforcement | 0 | 2869.84 | 2.35 | 482.39 | 3354.58 | n.m.
124 | P14030009 | Stinnett Station & Telecom | 1418.32 | 1344.3 | 946.75 | 295.87 | 2586.92 | 182.4%
125 | KYCR31167 | KY CR Belhaven Sta | 6.55 | 2087.4 | -2.4425e-15 | 312.11 | 2399.51 | 36634%
126 | P17084025 | Elwood Station Retirement | 436.38 | 943.86 | 869.35 | 164.75 | 1977.96 | 453.3%
127 | 000025473 | Purchase Hazard Service Center | 0 | 1491.39 |  |  | 1491.39 | n.m.
128 | A15710004 | Ashland SC Tele Modernization | 0 | 1246.84 |  |  | 1246.84 | n.m.
129 | P17083016 | McKinney Station Work | 948.47 | 728.8 |  | 219.67 | 948.47 | 100%
130 | A15710002 | Princess Tele. Moderniz. Stati | 0 | 614.11 |  | 101.71 | 715.82 | n.m.
131 | TA1807312 | D/KPCO/SEL GE Relay | 601.88 | 462.48 |  | 139.4 | 601.88 | 100%
132 | P18025004 | CANCELLED | 11.13 | 346.66 | 25.16 | 58.15 | 429.97 | 3863%
133 | B110KYCSV | D/KY/Customer Service | 0 | 542.93 | -218.77 | 89.28 | 413.44 | n.m.
134 | DP15K05L0 | Raccoon Station site purchase | 0 | 347.15 |  |  | 347.15 | n.m.
135 | P17083025 | Soft Shell Station Work (KPCo) | 319.24 | 245.3 |  | 73.94 | 319.24 | 100%
136 | A15702050 | Tenth St.-Transformer 2 Failur | 0 | 228.4 |  | 37.77 | 266.17 | n.m.
137 | A15710060 | Pikesville SC TTMP | 136 | 136 |  |  | 136 | 100%
138 | P17225007 | Ramey Station - Distribution | 22.98 | 19.87 | 33.86 | 3.11 | 56.84 | 247.3%
139 | DR19K02A0 | Ashland DA 2019 - D line | 36.01 | 27.67 |  | 8.34 | 36.01 | 100%
140 | A13212028 | Second Fork - Telecom Legacy | 0 | 0.07 |  | 0.01 | 0.08 | n.m.
141 | ETN000110 | T Kp D Anda | -0.004 | 262229.91 |  | -262229.91 | 0 | 0%
142 | 000008154 | KP Cust Serv Eng Support | 1352902.244 | 0 |  |  | 0 | 0%
143 | A18702002 | CANCELLED | 0 | 0 | 0 | 0 | 0 | n.m.
144 | DMS18KK07 | KP/Pre Valid Major Event 7 | 0 | -3.5527e-15 | 5.5511e-17 | -8.8818e-16 | -4.3854e-15 | n.m.
145 | A13212004 | D/KP/McKinney - Telecom Legacy | 0 |  | -27.89 |  | -27.89 | n.m.
146 | SI110KYRE | DB/SI/KyP-KENTUCKY SYS REHAB | 870.44 | 979.3 | -3931.54 | 240.57 | -2711.67 | -311.5%
147 | P11063003 | TKYVicco Station Improvement | 2189.15 | -3785.25 |  | 72.74 | -3712.51 | -169.6%
148 | A15702008 | CANCELLED | 0 | -57908.49 | -3221.22 | -807.14 | -61936.85 | n.m.
149 | P12124003 | DKPLOVELY Station SCADA Upgr | 16935.77 | -93368.24 | -10883.24 | -1522.87 | -105774.35 | -624.6%
150 | Other Budgeted Projects |  | 8429267.786 | 0 | 0 | 0 | 0 | Other
151 | Total GLBU 110 (Distribution) |  | 59624009.973 | 69527347.641 | 841386.63 | 6490.66 | 70375224.931 | 118%
152 | GLBU 117 (Generation)
153 | 000022392 | ML LANDFILL EXPANSION - PH 3 | 412548.78 | 3836776.96 | 442287.43 | 420685.79 | 4699750.18 | 1139%
154 | 000005237 | KyPCo-G Capital Software Dev | 2909.928 | 3544452.04 |  |  | 3544452.04 | 121805%
155 | BS0000038 | Big Sandy U1 HP IPSFLP Overha | 1516064.9 | 2990612.56 | 18409.47 | 191959.67 | 3200981.7 | 211.1%
156 | ML1EC1302 | ML1 E PHASE 1 GSU TRANSFORMER | 912507.885 | 1617279.75 | 40624.34 | 62587.62 | 1720491.71 | 188.5%
157 | IT1171421 | Maximo Imp - KYP - G | 0 | 1264246.745 | 146292.17 |  | 1410538.915 | n.m.
158 | BSPPB0013 | Other Costs PPB<$100k | 211845.156 | 931081.34 | 5576.72 | 110898.92 | 1047556.98 | 494.5%
159 | 000022308 | ML U1 ESP Project | 3953651.813 | 898972.52 | 4453.87 | 66885.59 | 970311.98 | 24.54%
160 | NRCCPKPCO | NERC CIP KYPCO | 3017697.026 | 840827.04 | 37405.29 | 86861.77 | 965094.1 | 31.98%
161 | ML1E18C05 | MLU1 LP TURBINE ROTOR REPAIR | 2492798.444 | 867956.77 | 37627.43 | 48612.9 | 954197.1 | 38.28%
162 | ML119SC02 | ML U1 ECON PARTITION WALL RPL | 1620588.74 | 721609.28 | 6087.06 | 53241.21 | 780937.55 | 48.19%
163 | IT117BILL | Corp Prgrm Billing - KYPCO Gen | 0 | 711614.5 | 1855.22 |  | 713469.72 | n.m.
164 | 000021737 | BS Repurpose BAP | 2224954.559 | 576206.75 | 43172 | 83563.44 | 702942.19 | 31.59%
165 | ML018MP05 | ML 2018 PLANT CAPITAL PAVING | 0 | 539809.97 | 4825.13 | 61831.49 | 606466.59 | n.m.
166 | ML018VP01 | ML - NON OUTAGE PPB FGD | 0 | 498556.77 | 16142.97 | 54224 | 568923.74 | n.m.
167 | ML018NP01 | ML CAPITAL TOOLS | 39365.307 | 509741.2 | 6705.84 | 20696.56 | 537143.6 | 1365%
168 | BSPPBOUT1 | Unit 1PPB Outage<100k | -2061352.777 | 450080.01 | 4043.89 | 23904.25 | 478028.15 | -23.19%
169 | BSPPBS347 | REP U1 BFPT Rotor with Spare | 365000 | 355867 | 613.23 | 30290.32 | 386770.55 | 106%
170 | ML018VP04 | ML ID FAN DRIVE END HUB PURCHA | 0 | 330795.54 | 9410.49 | 24476.69 | 364682.72 | n.m.
171 | BS2DCOM20 | Big Sandy U1 CEMS Building | 223824.752 | 324560.17 | 9000.84 | 28430.38 | 361991.39 | 161.7%
172 | ML1SC1810 | ML1 S BREECHING DUCT RPL | 472336.665 | 297520.58 | 1490.32 | 30076.5 | 329087.4 | 69.67%
173 | BSPPBS341 | Replace Bushings on 102 Transf | 0 | 259280.95 | 7333.37 | 29283.14 | 295897.46 | n.m.
174 | ML018NP12 | ML SERVICE BUILDING ROOF | 0 | 220611.23 | 5933.99 | 22584.84 | 249130.06 | n.m.
175 | ML018MP03 | ML MH CONVEYOR BELT REPLACE | 0 | 208953.35 | 8357.16 | 27180.21 | 244490.72 | n.m.
176 | MLP18EP04 | ML E LIGHTING PANEL REPLACE | 25934 | 217464.71 | 4149.66 | 22410.79 | 244025.16 | 940.9%
177 | BSPPB0002 | Boiler & Auxiliaries PPB<100k | -77272.576 | 194475.2 | 1145.34 | 40964.73 | 236585.27 | -306.2%
178 | ML2VC1601 | ML2 V CATALYST REPLACEMENT 3 L | -27600.342 | 216016.72 | 10772.6 | 9626.53 | 236415.85 | -856.6%
179 | ML218EP05 | ML U2 CT SHELL MONITORING SYST | 0 | 208893.14 | 796.8 | 11390.54 | 221080.48 | n.m.
180 | ML018MP06 | ML HIGH SULFUR STAMLER REBUILD | 0 | 186068.17 | 3846.66 | 20063.48 | 209978.31 | n.m.
181 | ML118SP22 | ML U1 BOILER CAMERA UPGRADE | 0 | 175241.78 | 4650.16 | 19462.03 | 199353.97 | n.m.
182 | ML1VC1601 | ML1 V CATALYST REPLACEMENT 3 L | -1356255.727 | 149238.83 | 3817.6 | 40131.87 | 193188.3 | -14.24%
183 | ML018SP01 | PULVERIZER REBUILD CAPITAL(#xx | 0 | 165284.16 | 287.92 | 10577.96 | 176150.04 | n.m.
184 | MLP18EP02 | ML E MOTOR REWIND / REPL +10HP | 8588.67 | 149769.41 | 4284.75 | 20702.95 | 174757.11 | 2035%
185 | ML2E18C05 | ML Unit 2 High Energy Piping | -628470.424 | 156736.71 | 1212.01 | 8109.54 | 166058.26 | -26.42%
186 | ML118VP07 | ML #12 ID FAN HUBS PPB PORTION | 0 | 142129.6 | 0 | 7484.89 | 149614.49 | n.m.
187 | BSPPBS338 | Repl 7 Banks Combustion Coils | 0 | 127827.9 | 892.83 | 17530.25 | 146250.98 | n.m.
188 | BSPPBS342 | REPL CATHODIC PROT TEST STA | 0 | 127013.75 | 355.82 | 17278.86 | 144648.43 | n.m.
189 | ML218SP10 | ML U2 PRECIP EJ REPLACEMENT | 254003.612 | 124973.84 | 10109.11 | 9324.72 | 144407.67 | 56.85%
190 | MLP18EP07 | ML #12 CIRCULATOR PUMP ELEMENT | 0 | 112610.59 | 5490.83 | 21119.29 | 139220.71 | n.m.
191 | ML217SP08 | ML U2 PRECIP ROOF BAY BOX VVV | -537513.452 | 116382.08 | 861.2 | 9053.61 | 126296.89 | -23.5%
192 | ML018NP10 | ML GUARD RAIL UPGRADES | 0 | 106478.01 | 0.07 | 19544.89 | 126022.97 | n.m.
193 | ML018EP14 | ML SEWAGE TREATMNT PLANT COVER | 0 | 102646.26 | 1291.68 | 16064.56 | 120002.5 | n.m.
194 | ML018NP04 | ML STOREROOM SECURITY SYSTEM | 0 | 101237.35 | 1944.37 | 10989.29 | 114171.01 | n.m.
195 | BSPPB0016 | Turb & Support Sys PPB<100k | 0 | 105762.52 |  | 7627.41 | 113389.93 | n.m.
196 | ML119EP01 | RPL MAIN TURB OIL TANK VALVE | 151738.476 | 96344.53 | 297.25 | 15175.1 | 111816.88 | 73.69%
197 | ML018EP04 | ML HVAC REPLACEMENT | 0 | 100398.53 | 1534.83 | 8846.68 | 110780.04 | n.m.
198 | ML018EP16 | ML CEMS HG SORBENT BU SYSTEM | 0 | 88890.87 | 1466.05 | 11450.48 | 101807.4 | n.m.
199 | ML018VP02 | ML0 V BALL MILL REBUILD | 0 | 87132.98 | 2821.33 | 10447.7 | 100402.01 | n.m.
200 | ML118SP01 | ML U1 PRECIP EJ REPLACEMENT | 0 | 92188.05 | 889 | 6001.43 | 99078.48 | n.m.
201 | ML217SP05 | ML U2 PRECIP ROOF BAY BOX XXX | -537513.452 | 86899.21 | 695.68 | 6186.41 | 93781.3 | -17.45%
202 | ML217SP06 | ML U2 PRECIP ROOF BAY BOX YYY | -537513.452 | 83536.88 | 734.28 | 7058.94 | 91330.1 | -16.99%
203 | ML217SP09 | ML U2 PRECIP ROOF BAY BOX WWW | -537513.452 | 79435.83 | 763.01 | 6730.52 | 86929.36 | -16.17%
204 | ML218EP07 | ML #21A CIRC WATER PUMP REPLAC | 0 | 76577.39 | 234.91 | 9700.03 | 86512.33 | n.m.
205 | ML018EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 0 | 76279.53 | 1239.96 | 6741.02 | 84260.51 | n.m.
206 | ML218SP20 | ML REPLACE U2 PULVERIZER YOKE | 27027.091 | 77911.07 | 382.83 | 5842.73 | 84136.63 | 311.3%
207 | ML018MP01 | REPLACE COALCONVEYOR SAMPLERS | -1985.24 | 61567.2 | 2500.08 | 9357.21 | 73424.49 | -3699%
208 | ML118SP19 | ML U1 TURBINE BASEMENT FIRE SY | 0 | 60330.55 | 80.83 | 6207.92 | 66619.3 | n.m.
209 | ML217SP07 | ML U2 PRECIP ROOF BAY BOX ZZZ | -537513.452 | 59733.4 | 660.07 | 5649.12 | 66042.59 | -12.29%
210 | ML018NP07 | ML NEW GATE FOR GATE 3 | 0 | 58131.53 | 315.8 | 5797.7 | 64245.03 | n.m.
211 | ML018NP08 | ML TURNSTILE ROOFS AND GRATING | 0 | 55031.6 | 666.03 | 6269.2 | 61966.83 | n.m.
212 | MLP18EP08 | ML #12 CIRCULATOR PUMP MOTOR | 0 | 48066.87 | 1997.77 | 11309.12 | 61373.76 | n.m.
213 | MLP18EP03 | ML E PUMP REPLACEMENT DR 10 HP | 17177.336 | 55826.45 | 344.31 | 5070.22 | 61240.98 | 356.5%
214 | ML018EP06 | ML #12 RIVER WATER MU PUMP RPL | 0 | 46205.1 | 591.56 | 12212.62 | 59009.28 | n.m.
215 | ML018NP11 | ML GATE 3 EMPLOYEE STAIRS | 0 | 51119.59 | 698.67 | 6657.78 | 58476.04 | n.m.
216 | MLP17SP01 | INSTALL R3/R4 FIRE HEADER CTIE | 0 | 39402.34 | 4547.26 | 14260.41 | 58210.01 | n.m.
217 | ML218SP07 | REPLACE 26F BURNERTUBE OPENING | -147029.705 | 50370.96 | 309.63 | 5619.66 | 56300.25 | -38.29%
218 | ML018EP11 | ML CIRCULATING WATERPMP MOTORS | 0 | 46874.78 | 682.66 | 6082.7 | 53640.14 | n.m.
219 | ML018EP01 | ML REPLACEMENT OF TRANSMITTERS | 14990.511 | 45124.64 | 424.79 | 3756.37 | 49305.8 | 328.9%
220 | MLP18EP09 | ML1 2019 HIGH ENERGY PIPE MAT | 0 | 42738.06 | 622.56 | 5676.65 | 49037.27 | n.m.
221 | ML216SP12 | ML2 #5 PRECIP EXPJOINT REPLACE | 0 | 44446.64 | 196.84 | 3176.13 | 47819.61 | n.m.
222 | ML218SP06 | REPLACE 26E BURNERTUBE OPENING | -147029.705 | 41811.4 | 402.38 | 4968.19 | 47181.97 | -32.09%
223 | ML117VP06 | RPL #11 ID FAN HYDRAULIC CYL | 0 | 39832.83 | 3505.92 | 3688.89 | 47027.64 | n.m.
224 | ML117EP04 | REPLACE #11 RDV to NASH PUMP | 0 | 43977.72 | 35.79 | 1144.35 | 45157.86 | n.m.
225 | ML018SP03 | ML U1&2 WATER CANNON UPGRADE | 0 | 41425.62 | 303.65 | 3379.79 | 45109.06 | n.m.
226 | MLP18EP01 | ML E MOTORS GREATER THAN 10 HP | 0 | 38066.24 | 187.21 | 3513.87 | 41767.32 | n.m.
227 | ML018EP17 | ML R3 TRANSFORMER REPLACEMENT | 0 | 36819.86 | 674.63 | 3920.12 | 41414.61 | n.m.
228 | ML0M18C01 | ML COAL YARD PLC REPLACEMENT | -423831.941 | 30212.48 | 932.92 | 7277.69 | 38423.09 | -9.066%
229 | ML218SP05 | REPLACE 26D BURNERTUBE OPENING | -147029.705 | 32673.34 | 314.03 | 5302.74 | 38290.11 | -26.04%
230 | ARCFLA117 | Arc Flash Protection Swi KYPCo | 27738.36 | 19066.54 | 11623.88 | 6405.7 | 37096.12 | 133.7%
231 | MLP18EP06 | MLP E VALVE REPLACEMENT 6 IN G | 17177.336 | 33853.1 | 275.84 | 2324.34 | 36453.28 | 212.2%
232 | ML018EP12 | ML HIGH WIND WARNING LIGHTS | 0 | 32203.85 | 203.08 | 3277.13 | 35684.06 | n.m.
233 | ML015VP01 | MLU0 CCR COMPLIANCE | 0 | 25884.72 | 3497.36 | 2570.43 | 31952.51 | n.m.
234 | 000025231 | 2018 Gen Plt Cap Blkt - KYPC-G | 0 | 28177.78 | 1308.67 |  | 29486.45 | n.m.
235 | ML119EP04 | ML UNIT 1 HIGH ENERGY PIPING | 0 | 24859.61 | 220.48 | 3953.73 | 29033.82 | n.m.
236 | ML018NP05 | ML FIRE HOUSE UPGRADES | 0 | 23790.9 | 147.68 | 2742.97 | 26681.55 | n.m.
237 | ML018EP10 | ML CIRCULATING WATER PUMP | 0 | 23115.17 | 0.07 | 2999.53 | 26114.77 | n.m.
238 | ML117EP10 | ML1 RPL FEEDWATER CHEM PUMPS | 0 | 21684.45 | 1771.96 | 2589.36 | 26045.77 | n.m.
239 | MLP19EP02 | ML E MOTOR REWINDSOVER 10HP | 0 | 22283.39 | 98.82 | 3640.83 | 26023.04 | n.m.
240 | ML119EP05 | ML #11B CIRC WATER PUMP REPLMT | 0 | 21407.06 | 64.58 | 3365.43 | 24837.07 | n.m.
241 | ML118EP10 | ML U1 STATOR DO & CONDUCTIVITY | 0 | 21452.55 | 505.11 | 2627.37 | 24585.03 | n.m.
242 | ML118EP12 | ML UNIT 1 INSTRUMENTATION PPB | 0 | 21489.07 | 509.03 | 2425.74 | 24423.84 | n.m.
243 | ML018EP15 | ML CPS POTABLE WATER PUMP | 0 | 21964.7 | 131.57 | 1902.82 | 23999.09 | n.m.
244 | ML218EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 0 | 20110.03 | 352.36 | 3204.41 | 23666.8 | n.m.
245 | ML016VP08 | UPS ON FGD | 0 | 20239.83 | 1631.82 | 1725.2 | 23596.85 | n.m.
246 | ML218SP17 | ML #22 CLINKER GRINDER REPLACE | 0 | 21071.29 | 116.66 | 1640.67 | 22828.62 | n.m.
247 | ML018EP07 | ML HVAC CFB BLUE BUILDING REP | 0 | 19303.72 | 0.04 | 2504.85 | 21808.61 | n.m.
248 | ML118EP04 | REP RFL9300 PILOT WIRE SYSTEM | 95251.345 | 18080.05 | 109.87 | 3083.26 | 21273.18 | 22.33%
249 | ML119SP10 | ML #12 CLINKER GRINDER REPLACE | 0 | 18302.23 | 55.21 | 2877.31 | 21234.75 | n.m.
250 | ML117EP11 | ML U1 1st RH EXH PIPING SPRING | 0 | 19660.04 | 146.16 | 1376.39 | 21182.59 | n.m.
251 | ML218SP11 | ML U2 #21 PA DUCT EJ REPLACEMT | 0 | 18562.92 | 189.23 | 1327.81 | 20079.96 | n.m.
252 | ML119EP03 | ML U1 555 LEAK DECTECT HP HEAT | 0 | 17865.18 | 200.1 | 2007.05 | 20072.33 | n.m.
253 | ML218SP16 | ML U2 #26 PA DUCT EJ REPLACEMT | 0 | 18128.48 | 176.26 | 1580.06 | 19884.8 | n.m.
254 | ML218EP04 | ML U2 COOL TOWER VALVE REPL | 0 | 17876.84 | 30.59 | 1390.77 | 19298.2 | n.m.
255 | ML118EP09 | MLU1 COOL TOWER VALVE REPL | 0 | 17647.89 | 31.55 | 1389.69 | 19069.13 | n.m.
256 | ML118EP01 | RFP9300 PILOT to GE190 SEL411L | -22791.833 | 14930.28 | 123.45 | 2688.55 | 17742.28 | -77.84%
257 | ML016VP11 | ML - 2016 FGD NON OUTAGE PPB | 0 | 13322.07 | 2398.81 | 1798.86 | 17519.74 | n.m.
258 | ML018EP13 | ML1 CONVEYOR 7 FIREDELUGE VALV | 0 | 16243.86 | 0.88 | 1149.44 | 17394.18 | n.m.
259 | ML218SP09 | REPL DFA FILTER SEPARATOR BAGS | 21667.065 | 13905.29 | 364.77 | 1929.71 | 16199.77 | 74.77%
260 | ML219SP03 | REPL DFA FILTER SEPARATOR BAGS | 0 | 13619.25 | 65.36 | 2246.69 | 15931.3 | n.m.
261 | ML018MP04 | ML MH TOWBOAT UPGRADE REPLACE | 0 | 12861.98 | 187.46 | 1668.71 | 14718.15 | n.m.
262 | MLP17EP05 | MLP E POWER CABLE REPLACEMENT | 10141.304 | 9570.74 | 3136.43 | 1659.08 | 14366.25 | 141.7%
263 | ML018MP09 | ML MH DFA SCALE UPGRADES | 0 | 13438.19 | 261.01 | 643.83 | 14343.03 | n.m.
264 | ML218SP12 | ML U2 #22 PA DUCT EJ REPLACEMT | 0 | 12876.33 | 160.18 | 1001.06 | 14037.57 | n.m.
265 | ML218SP08 | ML2 LONGER O2 PROBE REPLACEMN | 106254.725 | 11583.08 | 861.38 | 893.64 | 13338.1 | 12.55%
266 | ML218SP15 | ML U2 #25 PA DUCT EJ REPLACEMT | 0 | 11733.13 | 179.64 | 1326.21 | 13238.98 | n.m.
267 | BSPPB0011 | Generator & Support PPB<100k | 0 | 10032.84 | 16.4 | 2852.42 | 12901.66 | n.m.
268 | ML119SP07 | ML1 E PRECIPITATOR EJ REPLACE | 0 | 11239.42 | 142.24 | 1511.51 | 12893.17 | n.m.
269 | ML018EP02 | ML UNIT 1 & UNIT 2 PI SERVERS | 0 | 10800.98 | 391.15 | 1400.4 | 12592.53 | n.m.
270 | ML218SP13 | ML U2 #23 PA DUCT EJ REPLACEMT | 0 | 10833.49 | 166.57 | 1203.24 | 12203.3 | n.m.
271 | BSPPB0007 | Condenser & Aux. PPB<100k | 0 | 10205.14 | 5.35 | 1701.41 | 11911.9 | n.m.
272 | ML219EP01 | ML U2 555 LEAK DECTECT HP HEAT | 0 | 10588.04 | 175.9 | 859.88 | 11623.82 | n.m.
273 | ML017NP01 | Capital Tools | 58099.342 | 7924.3 | 1221.88 | 990.01 | 10136.19 | 17.45%
274 | ML218SP27 | ML U2 FOAM SYSTEM DELUGE VALVE | 0 | 9144.16 | 1.12 | 551.44 | 9696.72 | n.m.
275 | ML018MP08 | ML BARGE UNLOADER NETWORK UPGR | 0 | 7258.08 | 46.72 | 809.2 | 8114 | n.m.
276 | ML018EP18 | ML OUTFALL HEATED SAMPLERS | 0 | 7449.12 | 12.84 | 318.19 | 7780.15 | n.m.
277 | MLP17EP06 | MLP E VALVE REPLACEMENT 6 IN G | 25346.749 | 7196.1 | 141.25 | 436.82 | 7774.17 | 30.67%
278 | ML218SP26 | ML U2 TURBINE BASEMENT FIRE SY | 0 | 7273.1 | -1.7764e-15 | 317.23 | 7590.33 | n.m.
279 | ML019VP01 | ML - NON OUTAGE PPB FGD | 51532.015 | 6415.67 | 70.15 | 1000.74 | 7486.56 | 14.53%
280 | ML118SP07 | REPL DFA FILTER SEPARTOR BAGS | 21667.065 | 6604.21 | 176.55 | 663.35 | 7444.11 | 34.36%
281 | ML118SP20 | ML U1 FOAM SYSTEM DELUGE VALVE | 0 | 6894.96 | 1.34 | 439.54 | 7335.84 | n.m.
282 | ML019EP02 | ML TRANSFORMER REPLACEMENT | 0 | 5845.68 | 39.22 | 1012.96 | 6897.86 | n.m.
283 | ITCB11700 | KENTUCKY POWER - GEN | 0 | 6895.32 |  |  | 6895.32 | n.m.
284 | ML217EP02 | U2 SLAG BLOWER PLC UPGRADE | 0 | 6240.09 | 64.93 | 445 | 6750.02 | n.m.
285 | ML017EP02 | REPLACE AMMONIA TANK | 0 | 5218.47 | -112.2 | 434.68 | 5540.95 | n.m.
286 | ML018MP11 | ML MH BARGE UNLDR AUTO GREASE | 0 | 5195.47 | 102.47 | 223.91 | 5521.85 | n.m.
287 | ML118EP08 | ML U1 RPL PLANT CONTRL BATTERY | 0 | 4007.64 | 222.77 | 1004.2 | 5234.61 | n.m.
288 | ML119SP09 | REPL DFA FILTER SEPARTOR BAGS | 0 | 4434.9 | 29.3 | 766.5 | 5230.7 | n.m.
289 | ML118SP21 | ML #12F BURNER LINE SLIP JOINT | 0 | 4694.5 | 26.64 | 369.67 | 5090.81 | n.m.
290 | ML1NP1911 | ML1 INSULATION & LAGGING RPL | 0 | 4279.13 | 12.91 | 672.73 | 4964.77 | n.m.
291 | ML217VP04 | U2 PRECIPITATOR PLC UPGRADE | 0 | 4285.44 | 308.41 | 334.46 | 4928.31 | n.m.
292 | ML019NP01 | ML CAPITAL TOOLS | 0 | 4166.94 | 14.62 | 663.99 | 4845.55 | n.m.
293 | ML118SP18 | RPL 6" HSO-AUX STEAM-CHEM STA | 0 | 4454.67 | 6.03 | 307.76 | 4768.46 | n.m.
294 | ITCB11701 | Kentucky Power - Gen-Miitchell | 0 | 4149.33 |  |  | 4149.33 | n.m.
295 | ML218SP18 | ML #22 RECEIVING HOPPER REPLAC | 0 | 3757.85 | 21.34 | 295.91 | 4075.1 | n.m.
296 | ML118VP06 | ML RPL #12 ID FAN OUTLET EJ | 0 | 3765.95 | 4.6 | 279.19 | 4049.74 | n.m.
297 | ML219EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 0 | 3357.54 | 15.93 | 480.36 | 3853.83 | n.m.
298 | ML0VP1702 | REDUNDANT HDR SLURRY FEED TNK | 0 | 1726.27 | 75.45 | 2015.6 | 3817.32 | n.m.
299 | ML018VP06 | ML SILICON CARBIDE AR PUMP | 0 | 3464.42 | 67.12 | 168.7 | 3700.24 | n.m.
300 | ML218SP03 | RPL AUMA TEMPER AIR DAMPER DRV | 53975.787 | 2666.96 | 351.35 | 472.89 | 3491.2 | 6.468%
301 | BSPPB0003 | Boiler MU Water Supply PPB<100 | 186758.617 | 3261.26 | 19.03 | 167.5 | 3447.79 | 1.846%
302 | ML018MP10 | ML MT HANDLING MOBILE HEATERS | 0 | 3156.03 | 61.35 | 151.58 | 3368.96 | n.m.
303 | MLP19EP04 | ML E LIGHTING PANEL REPLACE | 0 | 2850.95 | 8.64 | 448.34 | 3307.93 | n.m.
304 | ML218EP03 | ML REPLACE#24 NASH VACUUM PUMP | 0 | 2106.2 | 967.08 | 224.86 | 3298.14 | n.m.
305 | MLP19EP06 | LP E VALVE REPLACEMENT 6 IN + | 0 | 2636.5 | 21.36 | 472.89 | 3130.75 | n.m.
306 | MLP19EP01 | ML E MOTORS GREATER THAN 10 HP | 0 | 2724.26 | 4.72 | 397.49 | 3126.47 | n.m.
307 | ML118SP11 | DFA EXHAUST BLOWER REPLACEMENT | 0 | 1987.01 | 68.08 | 242.92 | 2298.01 | n.m.
308 | ML017MP06 | ML MH CONVEYOR BELT REPLACE | 0 | 2043.29 | -23.61 | 160.9 | 2180.58 | n.m.
309 | ML016NP06 | MLP CAPITAL TOOLS | 0 | 1814.7 | 10.96 | 221.92 | 2047.58 | n.m.
310 | ML119SP12 | RPL PULVERIZER CLASSIFIER ASBY | 0 | 1584.93 | 12.58 | 254.78 | 1852.29 | n.m.
311 | ML119EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 0 | 1550.46 | 8.68 | 281.04 | 1840.18 | n.m.
312 | ML019EP09 | ML AMMONIA TANK N2 BLANKETING | 0 | 1555.41 | 4.69 | 244.53 | 1804.63 | n.m.
313 | MLP19EP03 | ML E PUMP REPLACEMENT DR 10 HP | 0 | 1544.16 | 4.7 | 242.91 | 1791.77 | n.m.
314 | MLP17EP04 | MLP E LIGHTING PANEL REPLACE | -245069.32 | 1352.38 | 598.67 | -597.5 | 1353.55 | -0.5523%
315 | ML017MP01 | ML 2017 PLANT CAPITAL PAVING | 0 | 716.56 | 519.26 | 44.86 | 1280.68 | n.m.
316 | ML017MP05 | ML MH COAL CHUTE REPLACEMENT | 0 | 1100.05 | 94.59 | 57.02 | 1251.66 | n.m.
317 | ML218EP06 | ML REPLACE #22 ECH PUMP | 0 | 741.1 | 47.87 | 58.36 | 847.33 | n.m.
318 | ML018NP03 | ML HAUL ROAD RELOCATION PRELIM | 0 | 671.3 | 8.86 | 94.95 | 775.11 | n.m.
319 | ML218SP02 | RPL AUMA HOT AIR DAMPER DRIVES | -70388.666 | 198.96 | 301.87 | 15.67 | 516.5 | -0.7338%
320 | ML217VP05 | INSTALL 2nd RH BLADES 3rd ROW | 0 |  | 511.04 |  | 511.04 | n.m.
321 | ML017VP03 | RPL CHEMICAL INJ SKID CPS CLAR | 0 | 127.1 | 349.29 | 9.97 | 486.36 | n.m.
322 | ML118SP05 | RPL AUMA TEMPER AIR DAMPER DRV | 0 |  | 443.32 |  | 443.32 | n.m.
323 | ML019VP02 | ML0 V BALL MILL REBUILD | 0 | 385.09 | 10.67 | 41.79 | 437.55 | n.m.
324 | ML218SP04 | REPLACE FD INLET VANE DRIVES | 69851.036 |  | 400.11 |  | 400.11 | 0.5728%
325 | BSPPBS340 | REPLACE 15 BREAKERS "B" BUS | 0 | 304.76 | 8.41 | 33.14 | 346.31 | n.m.
326 | MLP15MP02 | MLP MH CONVEYOR BELT REPLACE | 0 |  |  | 298.62 | 298.62 | n.m.
327 | ML216EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 0 |  |  | 289.62 | 289.62 | n.m.
328 | BSPPBS339 | REPLACE 15 BREAKERS "A" BUS | 0 | 228.57 | 6.32 | 24.85 | 259.74 | n.m.
329 | MLP19MP03 | ML MH R4 COAL CHUTE REPLACEMT | 0 | 172.73 | 0.52 | 27.15 | 200.4 | n.m.
330 | BSPPB0017 | Turb Valves & Ctrls PPB<100k | 0 |  | 134.9 |  | 134.9 | n.m.
331 | ML217VP08 | ML RPL#22 ID FAN HYDRAULIC CYL | 0 |  | 85.53 |  | 85.53 | n.m.
332 | ML117SP14 | ML UNIT 1 ECONOMIZER EJ | 0 |  | 12.89 |  | 12.89 | n.m.
333 | MLP19MP02 | MLP MH CONVEYOR BELT REPLACE | 50101.146 | 9.14 | 0.13 | 1.19 | 10.46 | 0.02088%
334 | ML119SP08 | ML U1 DEMINERALIZER RESIN RPL | 0 | 5.98 | 0.16 | 0.65 | 6.79 | n.m.
335 | ML118VP08 | ML RPL#12 ID FAN HYDRAULIC CYL | 0 | -7.69 | 1.1102e-16 | 7.69 | 0 | n.m.
336 | ML017EP11 | ML WASTE TANK CATHODIC PROTECT | 0 |  | 0 |  | 0 | n.m.
337 | ML017EP01 | Replacement of Transmitters | 24015.961 | -0.22 |  | -0.01 | -0.23 | -0.0009577%
338 | ML116EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 0 |  | -16.06 |  | -16.06 | n.m.
339 | ML017EP09 | ML U1/U2 VOLT / VAR COMPLIANCE | 0 |  | -17.26 |  | -17.26 | n.m.
340 | BSPPBS333 | VOLT VAR PROJECT | 0 |  | -50.64 |  | -50.64 | n.m.
341 | MLP17EP01 | MLP E MOTORS GREATER THAN 10 H | 0 |  | -79.35 |  | -79.35 | n.m.
342 | ML017EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 0 | 28.66 | -118.68 | 2.07 | -87.95 | n.m.
343 | MLP17EP03 | MLP E PUMP REPLACEMENT DR 10 H | 58806.519 |  | -150.55 |  | -150.55 | -0.256%
344 | ML1VP1704 | ML1 ID FAN GUILLOTINE DAMPER | 0 | 28.66 | -236.75 | 2.07 | -206.02 | n.m.
345 | ML017VP04 | ML-NON OUTAGE PPB FGD | 0 | -1882.87 | -1279.07 | -121.96 | -3283.9 | n.m.
346 | ML1E18C03 | MLU1 LPB TURBINE REPLACEMENT | 0 |  | -4478.5 |  | -4478.5 | n.m.
347 | KMLFALFCI | ML U0 New Landfill | 0 |  | -4811.47 | -1232.19 | -6043.66 | n.m.
348 | ML1E18C02 | ML1 2nd RH TURBINE REPLACEMENT | 0 |  | -6907.14 |  | -6907.14 | n.m.
349 | ML218SP14 | ML U2 #24 PA DUCT EJ REPLACEMT | 0 | -11026.25 | 178.77 | 1296.05 | -9551.43 | n.m.
350 | Other Budgeted Projects |  | 23960924 | 0 | 0 | 0 | 0 | Other
351 | Total GLBU 117 (Generation) |  | 34761186.802 | 28745648.765 | 967305.83 | 2163021.21 | 31875975.805 | 91.7%
352 | GLBU 180 (Transmission)
353 | P16113009 | Cannonsburg - S.NEAL TL KPCo | 1744901.023 | 6384871.25 | 102689.15 | 262061.16 | 6749621.56 | 386.8%
354 | P11161025 | Betsy Layne - Allen TLINE KPCo | 0 | 2107804.5 | 77554.26 | 228971.05 | 2414329.81 | n.m.
355 | A15702028 | Dorton 138/46 XF Replacement | 298199.82 | 1596961.81 | 17469.34 | 168094 | 1782525.15 | 597.8%
356 | B180KYLRC | T/KY/Non-Specific Work - Line | 329278.781 | 1444201.25 | 33124.55 | 193454.27 | 1670780.07 | 507.4%
357 | A18730013 | Baker - Don Marquis STR 162-26 | 0 | 1483416.56 | 345.17 | 180680.38 | 1664442.11 | n.m.
358 | A18730015 | Spring Fork Tap Str 2 Failure | 0 | 1432644.01 | 13496.14 | 131170.65 | 1577310.8 | n.m.
359 | A15702007 | Beaver Creek- Repl Cap Bk AACC | 0 | 1075933.62 | 16671.81 | 94292.12 | 1186897.55 | n.m.
360 | A15702041 | Hazard CB/XF Replacements | 1401312.087 | 965539.26 | 94353.09 | 122479.27 | 1182371.62 | 84.38%
361 | 000005273 | KyPCo-T Capital Software Dev | 0 | 1104262.09 |  |  | 1104262.09 | n.m.
362 | A15702033 | Jackson - Helech Str. Replace | 3235502.857 | 974532.75 | 11525.2 | 105580.93 | 1091638.88 | 33.74%
363 | P11161007 | T/KP Line Work Betsy-Dewey | 425658.817 | 838314.39 | 17787.12 | 62627.15 | 918728.66 | 215.8%
364 | A14068001 | Baker 765kV Improvement | 0 | 598923.93 | 212757.06 | 57512.64 | 869193.63 | n.m.
365 | A15042010 | Stone Station Incr. KPCo | 0 | 675369.45 | 52720.04 | 110759.5 | 838848.99 | n.m.
366 | P11161023 | Stanville Ext TLINE KPCo | 0 | 679138.48 | 39546.83 | 116886.82 | 835572.13 | n.m.
367 | A15702027 | Johns Creek 138/34 kV XF | 2115359.372 | 764235.63 | 18426.16 | 41116.8 | 823778.59 | 38.94%
368 | A16928011 | Chadwick Spare Purchase XF | 0 | 628364.17 | 35397.55 | 119998.15 | 783759.87 | n.m.
369 | P18025005 | Kewanee 138 Ext TLINE | 4825415.083 | 630837.49 | 16605.35 | 95353.9 | 742796.74 | 15.39%
370 | A15702034 | Hazard-Jackson Str Rep Part 2 | 0 | 636873.24 | 10156.31 | 54571.25 | 701600.8 | n.m.
371 | P13064029 | Hazard-Wooton Change to KPCo | 1396727.955 | 544994.17 | 85682.25 | 69024.88 | 699701.3 | 50.1%
372 | P17225004 | Moore Hollow 138kV Ext ROW | 0 | 692084.83 |  |  | 692084.83 | n.m.
373 | P16113003 | Cannonsburg-SNeal ROW (KY) | 22786.056 | 672920.6 |  |  | 672920.6 | 2953%
374 | A15710034 | Coalton-Leon Fiber TelModFib | 198410.209 | 562800.27 | 8200.31 | 50621.74 | 621622.32 | 313.3%
375 | A16902001 | Big Sandy Remote End Relaying | 528809.236 | 498011.58 | 46754.67 | 75127.45 | 619893.7 | 117.2%
376 | 000012898 | Forestry KP T non-NERC | 672623.435 | 549530.35 | 8229.72 | 59540.28 | 617300.35 | 91.78%
377 | P11161012 | B.Layne-S.Pikeville 69kV KPCo | 284259.098 | 493185.71 | 25382.81 | 48465.96 | 567034.48 | 199.5%
378 | P13064025 | Hazard - Wooton ROW KPCo | 278780.017 | 538578.39 |  |  | 538578.39 | 193.2%
379 | B180KYSRR | T/KY/Non-Specific Work - Stati | 211493.22 | 435064.36 | -13477.76 | 60548.8 | 482135.4 | 228%
380 | DP16K02B0 | Cedar Creek add D trans | 0 | 425841.98 | 5102.28 | 36111.97 | 467056.23 | n.m.
381 | A17042001 | Big Sandy-Baker 138kV Tie | 0 | 366484.17 | 6107.65 | 89503.3 | 462095.12 | n.m.
382 | A13212035 | Bellefonte Telecom Legacy Pilo | 0 | 346332.06 | 8425.04 | 63011.53 | 417768.63 | n.m.
383 | A15702010 | Thelma Rpl CB "B, D, BB" | 0 | 349734.85 | 14487.36 | 46046.86 | 410269.07 | n.m.
384 | P13064030 | Hazard Station Change to KPCo | 651890.486 | 338996.15 | 42399.68 | 27560.83 | 408956.66 | 62.73%
385 | IT1801421 | Maximo Imp - KYP - T | 0 | 351000.29 | 37935.09 |  | 388935.38 | n.m.
386 | P10115014 | Stone Change to KPCo | 0 | 312444.69 | 17760.69 | 46644.24 | 376849.62 | n.m.
387 | P13064031 | Hazard 161/138 Spare KPCo | 0 | 309592.59 | 15370.21 | 23020.66 | 347983.46 | n.m.
388 | P11161008 | Dewey Remote ends | 203574.827 | 286997.51 | 5234.05 | 36746.44 | 328978 | 161.6%
389 | P10115002 | TKPStone-RetRem Switches | 0 | 265854.8 | 1747.27 | 28691.22 | 296293.29 | n.m.
390 | P17225003 | Moore Hollow 138kV Extension | 2144.768 | 224664.7 | 22697.55 | 41676.66 | 289038.91 | 13476%
391 | A15710033 | Morgan Fork Fiber TelModFib | 0 | 245956.54 |  | 38479.13 | 284435.67 | n.m.
392 | A15042007 | Highland-Raceland FC ADSS | 0 | 215664.05 | 14965.75 | 33795.08 | 264424.88 | n.m.
393 | A15042005 | Baker-Big Sandy Fiber Cable | 0 | 222472.11 | 4284.46 | 21629.26 | 248385.83 | n.m.
394 | A14068005 | Ashland to Coalton Fiber Build | 0 | 218517.12 | 2862.84 | 23420.86 | 244800.82 | n.m.
395 | A15702029 | Leslie 161/69kV XF Replacement | 0 | 117573.44 | 87416.05 | 36300.64 | 241290.13 | n.m.
396 | A15702042 | Fleming XF/CB Replacements | 952036.629 | 183532.47 | 10324.94 | 36086.5 | 229943.91 | 24.15%
397 | P18025006 | Kewanee 138 Ext ROW | 0 | 192636.93 | 4686.9 | 29122.04 | 226445.87 | n.m.
398 | A15702030 | Morehead: Replace CB B | 0 | 180123.87 | 8702.9 | 18370.54 | 207197.31 | n.m.
399 | A17938021 | KPCO-Trans-Security AccSys-Est | 0.009 | 158855.64 | 10692.79 | 34308.04 | 203856.47 | 2265071889%
400 | IT180BILL | Corp Prgrm Billing-KYPCO Trans | 0 | 170422.38 |  |  | 170422.38 | n.m.
401 | P17110001 | Chadwick Station Work | 2560954.31 | 138653.88 | 8375.33 | 22096.29 | 169125.5 | 6.604%
402 | A15710035 | Pikeville Fiber TelModFib | 114868.037 | 146929.68 | 206.07 | 5093.1 | 152228.85 | 132.5%
403 | P11161024 | Stanville Ext ROW KPCo | 0 | 151982.79 |  |  | 151982.79 | n.m.
404 | A15702047 | Leon KY Remote End Work | 285610.988 | 133602.17 | 4450.58 | 9831.56 | 147884.31 | 51.78%
405 | A15702055 | Hazard Stn Rplc Fld Bnk #4 | 0 | 135747.5 |  | 7051.96 | 142799.46 | n.m.
406 | P11161010 | B.Layne - Allen 46 kV KPCo | 250874.897 | 107555.98 | 20980.52 | 11021.42 | 139557.92 | 55.63%
407 | A18730009 | T/KY/EngleTapLighting:Failure | 0 | 120023.51 | 902.72 | 17854.38 | 138780.61 | n.m.
408 | A15702002 | T/KY/BigSandy-Inez138kv:Lights | 0 | 98577.32 | 14278.17 | 8746.48 | 121601.97 | n.m.
409 | P17225001 | Moore Hollow 138kV Station | 2172.366 | 89406.38 | 8442.72 | 18466.41 | 116315.51 | 5354%
410 | P10115010 | T/KP/Inez: replace 138kV Bus # | 8.663 | 47381.06 | 19368.04 | 49202.8 | 115951.9 | 1338473%
411 | B180KYTRE | T/KP/Transmission Region Tools | 0 | 109695.86 |  |  | 109695.86 | n.m.
412 | P11063002 | TKYHazard Station Improvemen | 381080.589 | 3539.72 | 92598.13 | -15.74 | 96122.11 | 25.22%
413 | P10115003 | TKPStone Tap - Retire | 197255.993 | 85139.1 | 2456.79 | 8508.6 | 96104.49 | 48.72%
414 | A18730016 | Bonnyman-Softshell St 88 Failr | 0 | 78912.66 | 1655.56 | 12943.68 | 93511.9 | n.m.
415 | A18730002 | Jackson-Helech Str Rplc ROW | 0 | 68205.3 | 2810.84 | 8452.19 | 79468.33 | n.m.
416 | A18730003 | Hazard-Jackson Str. Replc ROW | 0 | 63932.83 | 2997.29 | 8187.1 | 75117.22 | n.m.
417 | DR18K02B1 | Bonnyman Sta - Add DRTU | 0 | 64733.08 | 578.59 | 3994.87 | 69306.54 | n.m.
418 | A16905009 | Cancelled - DO NOT USE | 608413.479 | 40602.3 | 11450.86 | 14897.22 | 66950.38 | 11%
419 | P17084003 | Cancel - DO NOT USE | 785596.981 | 54901.81 | 3653.82 | 6410.87 | 64966.5 | 8.27%
420 | DR18K02B2 | Leslie Sta - breaker control | 0 | 59361.58 | 500.15 | 3433.94 | 63295.67 | n.m.
421 | KYCR30003 | KY CR Bellefonte Sta | 0 | 52556.86 | 3404.38 | 5769.68 | 61730.92 | n.m.
422 | TP0921005 | T/KY/Line: Conxt: Bonnyman-Sof | 0 | 60648.25 | 0 |  | 60648.25 | n.m.
423 | P17110003 | Bellefonte Remote end Work | 0 | 49946.92 | 2524.76 | 6172.63 | 58644.31 | n.m.
424 | P10115004 | Canceled | 0 | 53241.78 | -0.01 |  | 53241.77 | n.m.
425 | P13064021 | T/KP/Hazard - Jackson 69kV Lin | 88682.244 | 41266.85 | 5671.07 | 5841.33 | 52779.25 | 59.52%
426 | P11161022 | Beaver Cr - Betsy L TLINE KPCo | 0 | 40204.87 | -281.74 | 12104.71 | 52027.84 | n.m.
427 | A15042011 | Coleman-Stone 69kV reconfig | 0 | 45815.42 | 1103.25 | 5006.11 | 51924.78 | n.m.
428 | P11161009 | Morgan Fork Remote End | 151060.449 | 46706.06 | -9.2 | 3205.16 | 49902.02 | 33.03%
429 | A15702043 | Beaver Creek CB AB replace | 0 | 39609.38 | 2937.25 | 6926.88 | 49473.51 | n.m.
430 | A18730011 | T/KY/EngleTapLighting: ROW | 0 | 46008.83 | 456.52 |  | 46465.35 | n.m.
431 | P17084026 | Beaver Creek - Fleming Cut in | 0 | 37281.05 | 3259.68 | 4329.48 | 44870.21 | n.m.
432 | P10115015 | Inez Change to KPCo | 0 | 14332.77 | 28901.13 | 1529.95 | 44763.85 | n.m.
433 | P13064002 | T/KP/Hazard Station / OPCO | 74210.168 | 26607.78 | 10695.74 | 6777.74 | 44081.26 | 59.4%
434 | A15702049 | Cancel | 0 | 43595.67 |  |  | 43595.67 | n.m.
435 | A15702035 | Hazard - Fleming Str. Replace | 0 | 30788.33 | 8358.54 | 3511.72 | 42658.59 | n.m.
436 | P16116005 | Stinnett -Pineville TL to KPCo | 6571.577 | 29055.99 | 9949.56 | 2345.87 | 41351.42 | 629.2%
437 | P18090001 | Inez Proactive Rehab Work | 0 | 20209.65 | 12640.81 | 8161.24 | 41011.7 | n.m.
438 | A17750007 | Prestonsburg-Thelma 69kV Slide | 0 | 35633.78 | 1.4 | 3840.58 | 39475.76 | n.m.
439 | A15702054 | Stone TF Failre Rplcment | 0 | 35356.91 |  | 2928.66 | 38285.57 | n.m.
440 | A15702036 | Daisy-Clover Fork Str. Replace | 743630.061 | 26634.75 | 4685.72 | 2300.18 | 33620.65 | 4.521%
441 | P17225008 | Princess Station | 158186.202 | 30411.03 | 970.37 | 2215.87 | 33597.27 | 21.24%
442 | P17076001 | Kenwood Extension TLINE | 36471.608 | 24612.77 | 4439.65 | 3969.18 | 33021.6 | 90.54%
443 | A15702006 | KYPCo BAT HCP | 0 | 30208.4 | 2764.93 |  | 32973.33 | n.m.
444 | A18730012 | S Neal - Leach: Hdware & Gnd | 0 | 28854.17 | 65.86 | 3238.05 | 32158.08 | n.m.
445 | P17083001 | Garrett-Soft Shell 138kV TLINE | 0 | 30485.26 |  | 729.77 | 31215.03 | n.m.
446 | P17084007 | Myra 138kV Extension TLINE | 271090.725 | 27451.88 | 485.66 | 2741.63 | 30679.17 | 11.32%
447 | P11028016 | TKPBreaks 69kV Extension - C | 0 | 25893 |  | 4335.86 | 30228.86 | n.m.
448 | B180KYSRC | T/KY/Non-Specific Work-Station | 184691.406 | 29365.76 | -459.96 | 308.19 | 29213.99 | 15.82%
449 | A15702060 | Wooton-2018Geupgrade | 0 | 25075.07 | 949.03 | 2066.43 | 28090.53 | n.m.
450 | A16928002 | Baker Station: Purchase 69/13k | 0 | 25515.47 | -1021.93 | 3519.26 | 28012.8 | n.m.
451 | A15710024 | Beaver Creek TTMP | 14970.925 | 21841.86 | 2289.04 | 2325.96 | 26456.86 | 176.7%
452 | A15042012 | Stone-Sprigg 46kV Reconfig | 0 | 21339.02 | 822.19 | 2378.39 | 24539.6 | n.m.
453 | A17212001 | Big Sandy 138KV RTU Replacemen | 0 | 21561.29 | 492 | 2336.44 | 24389.73 | n.m.
454 | A15702032 | Hazard-Bonnyman Str. Replace | 0 | 19187.57 | 3835.32 | 561.58 | 23584.47 | n.m.
455 | P11161001 | T/KY/Betsy Layne: Retirement | 0.018 | 19861.51 | 9.67 | 1930.89 | 21802.07 | 121122611%
456 | P12104006 | T/KP/Bellefonte 138kV Remote R | 0 | 17425.72 |  | 4253.11 | 21678.83 | n.m.
457 | 000025230 | 2018 Gen Plt Cap Blkt - KYPC-T | 0 | 20843.07 | 98.6 | 116.99 | 21058.66 | n.m.
458 | P18025013 | Sprigg - Beaver Cr. TLINE Work | 0 | 15980.28 | 493.66 | 2894.57 | 19368.51 | n.m.
459 | P13064003 | T/KP/Wooton Station - Station | 100497.386 | 10145.89 | 7723.11 | 1254.57 | 19123.57 | 19.03%
460 | A15702053 | Beaver Creek-Betsy Lane Remedi | 0 | 15713.03 |  | 2817.83 | 18530.86 | n.m.
461 | A18502002 | Baker 765 Firewall Install | 0 | 17746.91 |  |  | 17746.91 | n.m.
462 | A15702013 | T/KP/Leach:S.Neal pilot wire | 0 | 15529.28 |  | 1309.93 | 16839.21 | n.m.
463 | A18702003 | Leach RE Work | 0 | 13759.37 | 61.24 | 2566.73 | 16387.34 | n.m.
464 | A15702003 | Inez Station - UPFC Retirement | 0 | 14556.68 |  | 1178.6 | 15735.28 | n.m.
465 | P17225013 | Ramey 138 kV Extension TLINE | 791497.723 | 13288.84 | 957.55 | 1447.18 | 15693.57 | 1.983%
466 | A15705185 | Johns Creek 69kV Breaker Failu | 0 | 12252.05 |  | 2647.77 | 14899.82 | n.m.
467 | A15710036 | Hays Branch TTMP | 0 | 10673.86 | 1075.43 | 1808.6 | 13557.89 | n.m.
468 | P13064020 | T/KP/Hazard - Jackson 69kV ROW | 23272.875 | 13295.04 |  |  | 13295.04 | 57.13%
469 | P18025007 | Cedar Creek Remote End | 0 | 10932.68 | 508.73 | 1717.76 | 13159.17 | n.m.
470 | A15702057 | Fleming-2018Geupgrade | 0 | 9900.15 | 102.13 | 1676.71 | 11678.99 | n.m.
471 | P10115013 | Johns Creek Change to KPCo | 848004.748 | -19144.8 | 19802.17 | 10708.11 | 11365.48 | 1.34%
472 | P17084037 | Beaver Creek Remote End | 0 | 9104.22 | 834.95 | 1124.55 | 11063.72 | n.m.
473 | ITCB18000 | KENTUCKY POWER - TRANSM | 0 | 10199.34 | 78.6 |  | 10277.94 | n.m.
474 | A15710041 | Grayson Fiber Ext TelModFib | 5803.982 | 9729.63 | 19.27 | 497.62 | 10246.52 | 176.5%
475 | P17110002 | Bellefonte - Grangston Cut in | 0 | 8140.82 | 659.9 | 1348.5 | 10149.22 | n.m.
476 | DP14K02C0 | KP/Raccoon Sta - T line in & o | 0 | 7593.52 | 270.06 | 1508.99 | 9372.57 | n.m.
477 | P14030008 | T/KP/Leslie Station Work | 205878.788 | 3656.93 | 4624.98 | 244.9 | 8526.81 | 4.142%
478 | A15710037 | Leon TTMP | 9282.463 | 7477.56 | 29.69 | 805.06 | 8312.31 | 89.55%
479 | P17110005 | Chadwick - Leach Relocation | 0 | 6348.24 | 557.06 | 927.56 | 7832.86 | n.m.
480 | A15010001 | Ashland-Kenova69kV-Relocate | 0 | 6061.01 |  | 1442.02 | 7503.03 | n.m.
481 | P14030102 | Leslie - Wooton TL to KPCo | 53886.354 | 3302.11 | 3543.14 | 251.78 | 7097.03 | 13.17%
482 | P10115001 | TKPJohns Creek-RetRem MOABs | 947157.574 | 4470.91 | 1697.65 | 574.4 | 6742.96 | 0.7119%
483 | O18EST033 | SCADA - SERVERS - KPCO | 0 | 6544.25 |  |  | 6544.25 | n.m.
484 | P17084016 | CANCELLED | 0 | 1302.35 | 3847.73 | 1335.63 | 6485.71 | n.m.
485 | P17110006 | Chadwick - Tri State #1 Reloca | 0 | 5238.67 | 93.89 | 881.51 | 6214.07 | n.m.
486 | P18025008 | Beaver Creek Remote End Work | 0 | 5102.75 | 276.93 | 798.17 | 6177.85 | n.m.
487 | P13121006 | Bellefonte Remote for Chadwick | 0 | 5081.44 |  | 430.74 | 5512.18 | n.m.
488 | A18730001 | Hazard-Bonnyman Str Replce ROW | 0 | 3981.25 | 611.13 | 740.73 | 5333.11 | n.m.
489 | A15702025 | Baker 765 kV PK Removals | 1157402.401 | 2544.83 | -471.24 | 3018.26 | 5091.85 | 0.4399%
490 | A17959001 | KPCO/StormRcvry/BarrensheCole | 0 | 4425.5 |  | 445.52 | 4871.02 | n.m.
491 | P17076005 | Prestonsburg - Thelma 69kV | 0 | 2846.12 | 859.49 | 978.79 | 4684.4 | n.m.
492 | P12088005 | Bellefonte Rem/Rep XF (KPCo) | 0 | 3533.06 |  | 718.76 | 4251.82 | n.m.
493 | A15710022 | Morgan Fork TTMP | 0 | 2717.3 | 602.54 | 597.22 | 3917.06 | n.m.
494 | P17110007 | Chadwick - Tri State #2 Reloca | 0 | 3022.82 | 255.57 | 483.54 | 3761.93 | n.m.
495 | A18730004 | Hazard-Fleming Str. Replc ROW | 0 | 2249.86 | 730.49 | 508.98 | 3489.33 | n.m.
496 | P16113004 | Cannonsburg-SNeal KY Remove | 6.579 | 2788.97 | 230.92 | 326.7 | 3346.59 | 50868%
497 | SI180KYUN | TB SI KYPCO - KENTUCKY UNCAT | 0 | 1096.01 | 2250.3 |  | 3346.31 | n.m.
498 | A18730005 | Daisy - Clover Fork ROW | 0 | 2200.33 | 630.42 | 436.35 | 3267.1 | n.m.
499 | KYCR33039 | KY CR Leslie Sta | 0 | 2925.34 |  | 205.75 | 3131.09 | n.m.
500 | P17084036 | CANCELLED | 0 | 1254.32 | 950.82 | 517.65 | 2722.79 | n.m.
501 | P18066001 | Chadwick - England Hill PQ Mit | 0 | 2282.99 | 134.04 | 235.56 | 2652.59 | n.m.
502 | A15702061 | Johnscreek-2018Geupgrade | 0 | 1895.59 | 287.37 | 305.15 | 2488.11 | n.m.
503 | P17084019 | Elwood - Cedar Cr. Reconfig. | 0 | 696.44 | 983.13 | 576.28 | 2255.85 | n.m.
504 | P18066003 | Kenova-Eng. Hill KY PQ Mit | 0 | 1798.2 | 83.3 | 170.91 | 2052.41 | n.m.
505 | KYCR34118 | KY CR Johns Creek Sta | 0 | 1845.04 |  | 157.48 | 2002.52 | n.m.
506 | P14030013 | Wooton Relaying Work & Telecom | 184595.376 | 611.24 | 1255.37 | 41.09 | 1907.7 | 1.033%
507 | P17084017 | Beaver Creek - Fremont Cut in | 0 | 1197.67 | 459.89 | 133.58 | 1791.14 | n.m.
508 | A15710001 | Bellefonte 138KV Tele. Moderni | 0 | 1497.37 |  | 144.17 | 1641.54 | n.m.
509 | DP14K02C1 | Sprigg-Beaver Creek-Tower Rplc | 0 | 1425.31 | 21.45 | 193.55 | 1640.31 | n.m.
510 | A17750008 | Prestonsburg-Mid Creek46kVSlid | 0 | 1407.3 |  | 187.23 | 1594.53 | n.m.
511 | P18066005 | ASFI Tap PQ Mitigations | 0 | 1205.83 | 55.95 | 114.16 | 1375.94 | n.m.
512 | P17083003 | Garrett Switch (Removal) | 0 | 1187.36 |  | 157.97 | 1345.33 | n.m.
513 | P18025012 | Cedar Creek - Elwood TLINE Wor | 0 | 991.7 | 32.51 | 250.54 | 1274.75 | n.m.
514 | P17076006 | Kenwood Extension ROW | 0 | 1080.26 | 42.41 | 105.13 | 1227.8 | n.m.
515 | DP14K02T0 | KP/Raccoon Sta - T ROW | 0 | 1038.77 | 22.84 | 151.8 | 1213.41 | n.m.
516 | P17084022 | Henry Clay - Dorton Reconfig. | 0 | 836.11 | 178.3 | 106.89 | 1121.3 | n.m.
517 | P17084038 | Dorton Remote End | 0 | 885.83 | 153.08 | 45.52 | 1084.43 | n.m.
518 | P17225017 | Bellefonte - Coalton 138 kV TL | 214441.184 | -78.84 | 1038.4 | 25.83 | 985.39 | 0.4595%
519 | P17083034 | Morgan Fork Remote End | 0 | 731.54 |  | 97.32 | 828.86 | n.m.
520 | P14030103 | Leslie - Stinnett TL to KPCo | 100121.258 | 240.28 | 493.51 | 16.16 | 749.95 | 0.749%
521 | P14030002 | Stinnett Loop Install OPGW | 18757.709 | 145.21 | 439.59 | 73.06 | 657.86 | 3.507%
522 | P17225014 | Ramey 138 kV Extension ROW | 417710.844 | 657 |  |  | 657 | 0.1573%
523 | SI180KYRE | TBSIKyP-KENTUCKY SYS REHAB | 73.635 | 392.7 | 226.74 | 34.31 | 653.75 | 887.8%
524 | P17084013 | Henry Clay S.S Retirement | 0 | 353.97 | 94.23 | 118.41 | 566.61 | n.m.
525 | P17083006 | Garrett - Eastern 138 TLN | 0 | 479.78 |  | 63.84 | 543.62 | n.m.
526 | P14030104 | Leslie Ext Install to KPCo | 9036.345 | 157.04 | 322.55 | 10.55 | 490.14 | 5.424%
527 | P18066002 | Chadwick-Leach PQ Mit | 0 | 311.62 | 14.68 | 28.51 | 354.81 | n.m.
528 | A15702059 | Morganfork-2018Geupgrade | 0 | 0 | 4.54 | 346.63 | 351.17 | n.m.
529 | P17084023 | Henry Clay - Elk. City Reconfi | 0 | 63.18 | 170.78 | 4.25 | 238.21 | n.m.
530 | A15710064 | 2BCXLD Sprigg-Cinderella KY Te | 0 | 209.11 |  | 27.82 | 236.93 | n.m.
531 | P17225016 | East Park - Princess 138kV ROW | 417710.844 | 216.29 |  |  | 216.29 | 0.05178%
532 | P17083026 | Hays Br-Soft Shell Trans Fiber | 0 | 173.87 |  | 23.13 | 197 | n.m.
533 | P16116002 | Stinnett - Pineville Removal | 208.159 | 48.38 | 130.77 | 3.25 | 182.4 | 87.63%
534 | P17225018 | Bellefonte - Coalton 138kV ROW | 872531.999 | 172.88 |  |  | 172.88 | 0.01981%
535 | P11161026 | Betsy Layne - Allen ROW KPCo | 0 | 164.69 |  |  | 164.69 | n.m.
536 | P17084029 | New Henry Clay Extension | 0 | 36.94 | 99.84 | 2.48 | 139.26 | n.m.
537 | P17084021 | CANCELLED | 0 | 44.46 | 91.32 | 2.99 | 138.77 | n.m.
538 | A13212037 | South Portsmouth Telecom Legac | 11640.544 | 124 |  | 11.94 | 135.94 | 1.168%
539 | P17084020 | Elwood - Henry Cl. Recon. @ EL | 0 | 42.35 | 86.99 | 2.85 | 132.19 | n.m.
540 | P17225015 | East Park - Princess 138kV TL | 928246.321 | -3034.25 | 2715.78 | 435.45 | 116.98 | 0.0126%
541 | P17074005 | Millbrook - Siloam Cut in | 0 | 87.34 | 6.22 | 14.42 | 107.98 | n.m.
542 | P17084018 | Beaver Creek - Elwood Retire | 0 | 26.55 | 54.53 | 1.78 | 82.86 | n.m.
543 | P17076010 | Van Lear - Kenwood Str Replace | 0 | 40.29 | 1.76 | 1.77 | 43.82 | n.m.
544 | P14030101 | Leslie - Clover Fork Line Work | 904.48 | 10.31 | 21.18 | 0.69 | 32.18 | 3.558%
545 | A16928015 | Leslie Station Spare Purchase | 0 | 80.68 | 17.18 | -67.06 | 30.8 | n.m.
546 | P17083008 | Hays Br. - Morgan Frk. 138 TLN | 0 | 11.52 | 0.03 | 1.53 | 13.08 | n.m.
547 | P14030015 | Lesile - Stinnett Removal | 3613.694 | 2.43 | 8.06 | 0.16 | 10.65 | 0.2947%
548 | 000017437 | TLKYPHazard-Pineville 161kV | 0 | 7.91 |  |  | 7.91 | n.m.
549 | P14030016 | Leslie - Stinnett ROW (KPCo) | 36136.934 | 7.68 |  |  | 7.68 | 0.02125%
550 | A15702038 | CANCELLED | 0 |  |  | 4.46 | 4.46 | n.m.
551 | ETN000180 | T Kp T Anda | 0.003 | 3608625.02 |  | -3608625.02 | 0 | 0%
552 | P17074010 | CANCELMillbrook Frost ROW KPCo | 0 | -7.66 |  |  | -7.66 | n.m.
553 | P12088002 | Bellefonte: 69kV SUPP Work | 0 | 1382.58 | -4167.68 | 2773.42 | -11.68 | n.m.
554 | P17083009 | Hays Br. Morgan Frk. 138 ROW | 0 | -393.38 |  |  | -393.38 | n.m.
555 | P17074001 | CANCEL-Frost Station | 0 | 2200.83 | -377.52 | -2585.91 | -762.6 | n.m.
556 | A15702044 | INEZ 2017 GE Upgrade | 0 |  | -970.31 |  | -970.31 | n.m.
557 | ITCW18001 | KY Next Generation Radio Sys | 0 |  | -1004.54 |  | -1004.54 | n.m.
558 | A15702020 | Dewey-2017GEUpgrade | 0 |  | -1089.06 |  | -1089.06 | n.m.
559 | A15702014 | Thelma-2017GEUpgrade | 0 |  | -1229.17 |  | -1229.17 | n.m.
560 | A15702016 | BeaverCreek-2017GEUpgrade | 0 |  | -2336.26 |  | -2336.26 | n.m.
561 | P17074009 | CANCEL-Millbrook Frost TL KPCo | 0 | 1268.23 | -642.2 | -3867.68 | -3241.65 | n.m.
562 | P12088004 | Bellefonte 69 BUS TIE REMOVE | 0 | -2441.75 | -408.03 | -982.1 | -3831.88 | n.m.
563 | A15702040 | CANCELLED | 0 | -3953.76 | -279.85 | -380.48 | -4614.09 | n.m.
564 | P16116003 | Stinnett - Pineville ROW KPCo | 6546.732 | -4956.56 |  |  | -4956.56 | -75.71%
565 | SI180KYLR | TB/SI/KyP/KY - LINE REHAB | 0 | 0 | -5141.7 |  | -5141.7 | n.m.
566 | P18001001 | South Neal - Leach KPCo PQ | 0 | -5428.2 | -27.85 | 88.85 | -5367.2 | n.m.
567 | KEPCS1701 | KPCo Storm - Transmission | 0 | 6298.38 | -24910.55 | 423.43 | -18188.74 | n.m.
568 | A15702037 | CANCELLED | 1124444.713 | -40337.58 | -1490.23 | -5871.99 | -47699.8 | -4.242%
569 | A17016002 | T/KY/Hazard-Jkson69kv:RelocROW | 0 | -57776.18 | 4727.19 | 4311.29 | -48737.7 | n.m.
570 | A15702056 | Topmost SS Failure | 0 | -56657.26 | -1568.14 | -5224.97 | -63450.37 | n.m.
571 | P11028004 | CANCELLED | 0 | -55973.78 | 0 | -7489.11 | -63462.89 | n.m.
572 | A17016001 | T/KY/Hazard-Jackson69kv:Reloc | 0 | -133918.32 | 6751.15 | -4410.41 | -131577.58 | n.m.
573 | 000025076 | Pikeville Transmission SC | 0 | -419803.39 | -8847.33 |  | -428650.72 | n.m.
574 | Other Budgeted Projects |  | 46159043.28 |  |  |  |  | Other
575 | Total GLBU 180 (Transmission) |  | 81344020.398 | 40638917.6 | 1578990.65 | -20877.5 | 42197030.75 | 51.87%
576 | Total Kentucky Power CWIP Additions |  | 175729217.173 | 138911914.006 | 3387683.11 | 2148634.37 | 144448231.486 | 82.2%
577
578 | X00000317 | For Property Acctg Use Only - GLBU 110 | Property Acctg | -55108922.43 | 62953.32 |  | -55045969.11 | Property Acctg
579 | X00000288 | For Property Acctg Use Only - GLBU 117 | Property Acctg | -20638416.76 | 266554.98 | -3709908.49 | -24081770.27 | Property Acctg
580 | X00000306 | For Property Acctg Use Only - GLBU 180 | Property Acctg | -33530942.73 | 188213.18 |  | -33342729.55 | Property Acctg
581 | Total Kentucky Power Transfers to 101/106 |  |  | -109278281.92 | 517721.48 | -3709908.49 | -112470468.93
582
583 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year April 2018 - March 2019 |  | 175729217.173 | 29633632.086 | 3905404.59 | -1561274.12 | 31977762.556
584
585
586 | Definitions:
587 | (E)* | Represents AFUDC Debt and AFUDC Equity (Cost Components 023 and 024, respectively)
588 | (F)* | Represents allocated construction overheads (Cost Component 020)
589 | n.m. | Not meaningful
590 | Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.