## Test Year
Schedule E (Historical Test Year)
Kentucky Power Company
Case No. 2020-00174
Construction Projects for the Historical Test Year
April 2019 - March 2020
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time through March 31, 2020 (J)* | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures April 2019 through March 2020
(A) | (B) | (C)* | (D) | (E) = ((J)- (C)) / ((D) -(C)) | (F) | (G) | (H)* | (I) = (H)/(G)
1 | GLBU 110 (Distribution)
2 | TREEREL19 | 4/1/2014 | Blanket | Blanket | 7322534.111 | 13148865.013 | 9908102.76 | 75.35%
3 | 000007818 | Blanket | Blanket | Blanket | 5546163.324 | 6463660.004 | 9210519.88 | 142.5%
4 | ITCW11004 | 4/1/2017 | 2022-12-01 | 52.9% | 3531071.126 | 2018167.959 | 6502793.73 | 322.2%
5 | DR15K02B0 | 5/1/2018 | 2020-12-01 | 74.07% | 0 | 0 | 4921593.626 | 0%
6 | 000001818 | Blanket | Blanket | Blanket | 2995243.445 | 2927501.269 | 4866269.68 | 166.2%
7 | 000005234 | Blanket | Blanket | Blanket | 0 | 0 | 4482702.32 | 0%
8 | EON011326 | 2/1/2018 | Blanket | Blanket | 2506109.586 | 2495554.084 | 3872363.69 | 155.2%
9 | EDN014651 | 2/1/2018 | Blanket | Blanket | 3094581.811 | 2974637.412 | 3449807.51 | 116%
10 | 000007599 | Blanket | Blanket | Blanket | 2706816.934 | 2670590.404 | 3385486.12 | 126.8%
11 | KY5YCYCLE | 1/1/2019 | Blanket | Blanket | 3645171.025 | 3638799.148 | 3226364.75 | 88.67%
12 | EDN100033 | 2/1/2018 | Blanket | Blanket | 2014641.169 | 1936272.549 | 2668143.36 | 137.8%
13 | P18025001 | 2/1/2018 | 2024-06-01 | 34.13% | 0 | -2920954.075 | 2576565.66 | -88.21%
14 | TREEREL20 | 4/1/2014 | Blanket | Blanket | 0 | 1843344.009 | 2279705.73 | 123.7%
15 | DP14K02B0 | 3/1/2018 | 2021-10-01 | 58.09% | 0 | 0 | 2148109.48 | 0%
16 | 000025820 | Charges Began Prior to Jan 2015 | 2020-11-01 | n.m. | 0 | 923799.658 | 1979437.3 | 214.3%
17 | 000025229 | Blanket | Blanket | Blanket | 176716.203 | 1423388.007 | 1963221.99 | 137.9%
18 | EDN014680 | 2/1/2018 | Blanket | Blanket | 3146694.852 | 3123792.595 | 1660550.37 | 53.16%
19 | 000016528 | Blanket | Blanket | Blanket | 1704140.168 | 1692472.317 | 1654686.99 | 97.77%
20 | EDN100577 | 2/1/2018 | Blanket | Blanket | 1230656.947 | 1227349.994 | 1575963.96 | 128.4%
21 | DR19K02A0 | 3/1/2019 | 2020-12-01 | 61.78% | 0 | 0 | 1032725.85 | 0%
22 | DR18K02A0 | 3/1/2019 | 2020-12-01 | 61.78% | 0 | 0 | 977387.61 | 0%
23 | DCTSUVLKY | 12/1/2019 | Blanket | Blanket | 0 | 0 | 865613.2 | 0%
24 | EDN014720 | 2/1/2018 | Blanket | Blanket | 1203564.362 | 1193184.663 | 803396.87 | 67.33%
25 | B110KYSRR | 11/1/2016 | Blanket | Blanket | 647710.74 | 647009.12 | 802483.25 | 124%
26 | DR19K04A0 | 7/1/2019 | 2020-12-01 | 52.79% | 0 | 0 | 741765.09 | 0%
27 | DR19K05A0 | 5/1/2019 | 2021-10-01 | 37.9% | 0 | 906290.566 | 724091.87 | 79.9%
28 | 000004737 | Blanket | Blanket | Blanket | 647036.091 | 644802.442 | 702081.64 | 108.9%
29 | EDN015042 | 2/1/2018 | Blanket | Blanket | 453438.444 | 452100.225 | 694342.41 | 153.6%
30 | ITCB11000 | 7/1/2017 | Blanket | Blanket | 632604.397 | 643830.808 | 680071.17 | 105.6%
31 | A17212002 | 7/1/2018 | 2020-10-01 | 77.64% | 187753.504 | 189893.539 | 633994.98 | 333.9%
32 | EDN011333 | 2/1/2018 | Blanket | Blanket | 795930.677 | 792770.687 | 615416.48 | 77.63%
33 | IT110BILL | 7/1/2017 | Blanket | Blanket | 0 | 0 | 545388.04 | 0%
34 | A15702051 | 12/1/2017 | 2020-12-01 | 77.65% | 0 | 0 | 507813.04 | 0%
35 | IT1101421 | 3/1/2016 | Blanket | Blanket | 0 | 0 | 493346.5 | 0%
36 | DR19K06B0 | 4/1/2019 | 2020-12-01 | 59.84% | 0 | 0 | 491464.82 | 0%
37 | DR15K02A0 | 4/1/2018 | 2020-12-01 | 74.87% | 0 | 0 | 482798.18 | 0%
38 | DR18K04B0 | 8/1/2018 | 2020-12-01 | 71.28% | 0 | 0 | 475996.3 | 0%
39 | DR19K06B1 | 4/1/2019 | 2020-12-01 | 59.84% | 0 | 0 | 472621.92 | 0%
40 | DP18K03L0 | 6/1/2019 | 2020-10-01 | 62.3% | 0 | 0 | 448650.77 | 0%
41 | EDN012370 | 2/1/2018 | Blanket | Blanket | 2001780.849 | 1925873.587 | 420327.37 | 21.83%
42 | DR19K02B0 | 5/1/2019 | 2021-09-01 | 39.23% | 0 | 0 | 406285.24 | 0%
43 | EDN014694 | 2/1/2018 | Blanket | Blanket | 430012.679 | 420637.81 | 382746.14 | 90.99%
44 | DP16K02A0 | 6/1/2019 | 2020-10-01 | 62.3% | 0 | 186568.001 | 364766.92 | 195.5%
45 | DMS20KK01 | 11/1/2019 | 2020-10-01 | 45.07% | 0 | 0 | 359250.19 | 0%
46 | 000025522 | Charges Began Prior to Jan 2015 | 2020-12-01 | n.m. | 0 | 0 | 316487.83 | 0%
47 | 000002241 | Blanket | Blanket | Blanket | 91944.176 | 89795.494 | 308036.67 | 343%
48 | KYCAPTOOL | 3/1/2019 | Blanket | Blanket | 28720.589 | 141004.797 | 272239.88 | 193.1%
49 | A20212001 | 10/1/2018 | 2021-12-01 | 47.28% | 108085.401 | 106221.346 | 262049.07 | 246.7%
50 | EDN014658 | 2/1/2018 | Blanket | Blanket | 167558.46 | 164759.717 | 256157.07 | 155.5%
51 | DR18K02B0 | 9/1/2018 | 2020-10-01 | 75.82% | 0 | 0 | 197939.04 | 0%
52 | P16113007 | 12/1/2016 | 2020-10-01 | 86.86% | 25822.037 | 25958.12 | 197734.53 | 761.7%
53 | DMS19KK05 | 10/1/2019 | 2020-10-01 | 49.73% | 0 | 0 | 192216.66 | 0%
54 | DR18K02B3 | 10/1/2018 | 2020-10-01 | 74.83% | 0 | 0 | 187218.8 | 0%
55 | DMS19KK02 | 5/1/2019 | 2020-10-01 | 64.55% | 0 | 0 | 180257.82 | 0%
56 | DMS19KK06 | 11/1/2019 | 2020-10-01 | 45.07% | 0 | 0 | 174440.96 | 0%
57 | P18216001 | 7/1/2018 | 2021-12-01 | 51.16% | 0 | 0 | 166553.7 | 0%
58 | DR19K06B2 | 4/1/2019 | 2020-12-01 | 59.84% | 0 | 0 | 145875.336 | 0%
59 | TA1807312 | 4/1/2014 | 2020-12-01 | 89.94% | 0 | 0 | 145757.752 | 0%
60 | 000007615 | Blanket | Blanket | Blanket | 218885.286 | 214913.7 | 143270.46 | 66.66%
61 | A15710030 | 3/1/2018 | 2021-12-01 | 55.51% | 0 | 0 | 140782.68 | 0%
62 | DP16K03B0 | 10/1/2019 | 2023-12-01 | 11.96% | 0 | 0 | 121028.06 | 0%
63 | EDN103175 | 2/1/2018 | Blanket | Blanket | -0.005 | -0.034 | 119323.74 | -350952165%
64 | A16928014 | 11/1/2017 | 2020-12-01 | 78.24% | 0 | 0 | 110609.38 | 0%
65 | 000007558 | Blanket | Blanket | Blanket | 466693.947 | 456088.81 | 103482.23 | 22.69%
66 | P11161021 | 7/1/2015 | 2020-10-01 | 90.41% | 0 | 0 | 102661.47 | 0%
67 | P11161006 | 7/1/2017 | 2020-10-01 | 84.51% | 0 | 0 | 67330.74 | 0%
68 | 000014717 | Blanket | Blanket | Blanket | 143070.792 | 138762.193 | 66434.26 | 47.88%
69 | P19091002 | 7/1/2018 | 2021-12-01 | 51.16% | 0 | 0 | 63922.9 | 0%
70 | KYCR012DL | 3/1/2019 | 2020-12-01 | 61.78% | 0 | 0 | 61078.71 | 0%
71 | EDN100044 | 2/1/2018 | Blanket | Blanket | 90454.349 | 89730.029 | 61013.47 | 68%
72 | 000007577 | Blanket | Blanket | Blanket | 34289.538 | 34365.094 | 59090.34 | 171.9%
73 | DMS19KK03 | 5/1/2019 | 2020-10-01 | 64.55% | 0 | 0 | 57887.79 | 0%
74 | A15710017 | 1/1/2017 | 2021-12-01 | 66.02% | 0 | 0 | 57750.95 | 0%
75 | DR19K05B1 | 6/1/2019 | 2021-10-01 | 35.64% | 0 | 178234.919 | 55988.87 | 31.41%
76 | DR19K05B0 | 6/1/2019 | 2021-10-01 | 35.64% | 0 | 217853.488 | 55922.93 | 25.67%
77 | DR19K05B2 | 6/1/2019 | 2021-10-01 | 35.64% | 0 | 262287.437 | 53851.7 | 20.53%
78 | DMS20KK02 | 11/1/2019 | 2020-12-01 | 38.13% | 0 | 0 | 47297.22 | 0%
79 | A15710039 | 11/1/2018 | 2021-06-01 | 54.72% | 28225.334 | 28288.448 | 44871.11 | 158.6%
80 | A19442001 | 5/1/2019 | 2021-12-01 | 35.45% | 39197.462 | 38521.46 | 39509.48 | 102.6%
81 | P13064028 | 11/1/2019 | 2020-10-01 | 45.07% | 0 | 0 | 32760.05 | 0%
82 | A15710040 | 3/1/2018 | 2021-06-01 | 64.06% | 28225.334 | 28288.448 | 32138.58 | 113.6%
83 | P19091009 | 8/1/2019 | 2021-12-01 | 28.49% | 0 | 0 | 30298.43 | 0%
84 | P19092002 | 8/1/2019 | 2021-12-01 | 28.49% | 0 | 0 | 23201.35 | 0%
85 | P17084005 | 11/1/2017 | 2024-12-01 | 34.05% | 565853.499 | 563294.483 | 22292.83 | 3.958%
86 | A13002013 | Charges Began Prior to Jan 2015 | 2021-12-01 | n.m. | 0 | 0 | 22099.17 | 0%
87 | P17083030 | 4/1/2019 | 2024-12-01 | 17.62% | 10597.039 | 9063.281 | 21651.68 | 238.9%
88 | P17083016 | 3/1/2019 | 2024-12-01 | 18.84% | 24065.074 | 23473.404 | 20739.61 | 88.35%
89 | P11161002 | 7/1/2017 | 2020-10-01 | 84.51% | 0 | 0 | 19714.65 | 0%
90 | DX17K01B0 | 2/1/2018 | 2021-12-01 | 56.4% | 0 | 0 | 18120.74 | 0%
91 | A15710005 | 9/1/2016 | 2021-06-01 | 75.37% | 0 | 0 | 17929.4 | 0%
92 | DMS19KK04 | 5/1/2019 | 2020-10-01 | 64.55% | 0 | 0 | 17278.42 | 0%
93 | A20705033 | 7/1/2019 | 2021-12-01 | 31% | 0 | 0 | 17194.99 | 0%
94 | A20705058 | 9/1/2019 | 2022-12-01 | 17.86% | 0 | 0 | 15976.61 | 0%
95 | A15710062 | 10/1/2019 | 2020-12-01 | 42.62% | 8533.062 | 8385.898 | 14605.24 | 174.2%
96 | DP15K05L0 | 12/1/2015 | 2020-10-01 | 89.58% | 0 | 0 | 14254.53 | 0%
97 | A15710021 | 1/1/2017 | 2021-12-01 | 66.02% | 0 | 0 | 12030.94 | 0%
98 | EDN014701 | 2/1/2018 | Blanket | Blanket | 21535.166 | 21582.861 | 11028.88 | 51.1%
99 | A15710020 | 1/1/2017 | 2021-12-01 | 66.02% | 0 | 0 | 10912.4 | 0%
100 | A13002014 | Charges Began Prior to Jan 2015 | 2020-12-01 | n.m. | 0 | 0 | 10560.09 | 0%
101 | P17076002 | 9/1/2017 | 2024-12-01 | 35.57% | 77037.153 | 76403.478 | 10553.82 | 13.81%
102 | A15710026 | 2/1/2018 | 2021-06-01 | 64.88% | 0 | 0 | 10276.55 | 0%
103 | DX17K02B0 | 2/1/2018 | 2021-12-01 | 56.4% | 0 | 0 | 10035.12 | 0%
104 | A15710038 | 3/1/2018 | 2021-06-01 | 64.06% | 17648.259 | 17687.725 | 9902.24 | 55.98%
105 | A15710056 | 11/1/2019 | 2021-06-01 | 26.12% | 8533.062 | 8385.898 | 9271.28 | 110.6%
106 | A20705068 | 9/1/2019 | 2024-12-01 | 11.05% | 0 | 0 | 9267.74 | 0%
107 | A20705084 | 11/1/2019 | 2024-12-01 | 8.131% | 0 | 0 | 9188.76 | 0%
108 | A20705085 | 11/1/2019 | 2024-12-01 | 8.131% | 0 | 0 | 9130.38 | 0%
109 | 000025515 | Charges Began Prior to Jan 2015 | 2020-10-01 | n.m. | 0 | 0 | 7494.87 | 0%
110 | P17084024 | 10/1/2017 | 2020-10-01 | 83.21% | 0 | 0 | 6233.87 | 0%
111 | EDN101114 | 2/1/2018 | Blanket | Blanket | 31496.252 | 31567.217 | 5583.16 | 17.69%
112 | P18221011 | 7/1/2018 | 2021-06-01 | 59.94% | 0 | 0 | 5332.4 | 0%
113 | A15710055 | 11/1/2019 | 2021-06-01 | 26.12% | 8533.062 | 8385.898 | 5106.87 | 60.9%
114 | A15710019 | 1/1/2017 | 2021-06-01 | 73.51% | 0 | 0 | 4990.06 | 0%
115 | A15710057 | 11/1/2019 | 2021-06-01 | 26.12% | 2275.477 | 2236.232 | 4800.03 | 214.6%
116 | A15710054 | 11/1/2019 | 2021-06-01 | 26.12% | 8533.062 | 8385.898 | 4707.17 | 56.13%
117 | P18025002 | 2/1/2018 | 2020-10-01 | 81.09% | 0 | 0 | 4370.97 | 0%
118 | P17084009 | 9/1/2017 | 2024-12-01 | 35.57% | 1722172.144 | 1708411.202 | 4213.49 | 0.2466%
119 | A15710085 | 7/1/2019 | 2021-06-01 | 39.09% | 0 | 0 | 4005.44 | 0%
120 | DP18K01L0 | 6/1/2019 | 2020-10-01 | 62.3% | 0 | 0 | 3943.35 | 0%
121 | A15710086 | 7/1/2019 | 2021-06-01 | 39.09% | 0 | 0 | 3701.34 | 0%
122 | 000024645 | Blanket | Blanket | Blanket | 22534.244 | 312.281 | 3139.54 | 1005%
123 | A15710076 | 7/1/2019 | 2021-06-01 | 39.09% | 0 | 0 | 2997.52 | 0%
124 | A15710016 | 9/1/2016 | 2021-06-01 | 75.37% | 0 | 0 | 2871.19 | 0%
125 | A15710075 | 6/1/2019 | 2021-06-01 | 41.59% | 0 | 0 | 2819.76 | 0%
126 | A15710080 | 6/1/2019 | 2021-06-01 | 41.59% | 0 | 0 | 2811.09 | 0%
127 | A15710079 | 7/1/2019 | 2021-06-01 | 39.09% | 0 | 0 | 2621.48 | 0%
128 | P19092014 | 8/1/2019 | 2021-12-01 | 28.49% | 0 | 0 | 2271.74 | 0%
129 | P17076003 | 9/1/2017 | 2021-12-01 | 60.7% | 13770.283 | 13727.515 | 2214.24 | 16.13%
130 | A15710072 | 9/1/2019 | 2021-12-01 | 25.79% | 0 | 0 | 2013.73 | 0%
131 | P19092016 | 8/1/2019 | 2024-12-01 | 12.47% | 0 | 0 | 1899.53 | 0%
132 | A17750006 | 7/1/2018 | 2020-10-01 | 77.64% | 0 | 0 | 1744.23 | 0%
133 | P17083033 | 4/1/2019 | 2023-12-01 | 21.41% | 37.172 | 49073.629 | 1715.68 | 3.496%
134 | P17084025 | 9/1/2017 | 2024-12-01 | 35.57% | 0 | 0 | 1670.6 | 0%
135 | P17225006 | 3/1/2019 | 2025-12-01 | 16.05% | 3124382.529 | -294764.389 | 1443.99 | -0.4899%
136 | A15710053 | 11/1/2019 | 2021-06-01 | 26.12% | 8533.062 | 8385.898 | 1429.63 | 17.05%
137 | A15710063 | 10/1/2019 | 2021-06-01 | 29.89% | 10808.547 | 10622.138 | 1401.69 | 13.2%
138 | P14030009 | 11/1/2016 | 2021-06-01 | 74.48% | 78403.283 | 77878.648 | 1330.34 | 1.708%
139 | P17084014 | 9/1/2017 | 2024-12-01 | 35.57% | 0 | 0 | 1281.24 | 0%
140 | 000025524 | Charges Began Prior to Jan 2015 | 2020-10-01 | n.m. | 0 | 0 | 1155.6 | 0%
141 | SI110KYRE | 8/1/2019 | Blanket | Blanket | 0 | 0 | 1140.36 | 0%
142 | P18025003 | 2/1/2018 | 2020-10-01 | 81.09% | 0 | -284853.143 | 1090.8 | -0.3829%
143 | DR20K02B3 | 12/1/2019 | 2021-12-01 | 16.55% | 0 | 0 | 1018.38 | 0%
144 | A13212036 | Charges Began Prior to Jan 2015 | 2020-12-01 | n.m. | 0 | 0 | 985.87 | 0%
145 | P18221016 | 7/1/2018 | 2023-12-01 | 32.29% | 0 | 0 | 927.01 | 0%
146 | P11161003 | 7/1/2017 | 2020-10-01 | 84.51% | 0 | 0 | 860.29 | 0%
147 | A15710011 | 9/1/2016 | 2021-06-01 | 75.37% | 0 | 0 | 660.31 | 0%
148 | DR19K04B2 | 11/1/2019 | 2020-10-01 | 45.07% | 0 | 0 | 570.88 | 0%
149 | DR20K02B1 | 12/1/2019 | 2021-12-01 | 16.55% | 0 | 0 | 567.47 | 0%
150 | P17076011 | 4/1/2018 | 2024-06-01 | 32.4% | 17993.233 | 17686.037 | 394.3 | 2.229%
151 | A15710012 | 9/1/2016 | 2021-06-01 | 75.37% | 0 | 0 | 274.55 | 0%
152 | DR20K02B2 | 12/1/2019 | 2021-12-01 | 16.55% | 0 | 0 | 269.13 | 0%
153 | DR20K02B0 | 12/1/2019 | 2021-12-01 | 16.55% | 0 | 0 | 259.88 | 0%
154 | A15710059 | 11/1/2019 | 2021-06-01 | 26.12% | 2275.477 | 2236.232 | 236.94 | 10.6%
155 | A15710060 | 2/1/2019 | 2021-06-01 | 49.82% | 8533.062 | 8385.898 | 151.37 | 1.805%
156 | P17225007 | 3/1/2019 | 2024-06-01 | 20.64% | 1820330.31 | -139995.245 | 44.36 | -0.03169%
157 | P18025004 | 2/1/2018 | 2020-10-01 | 81.09% | 0 | 0 | 21.47 | 0%
158 | KYCR31167 | 5/1/2016 | 2021-12-01 | 70.1% | 0 | 0 | 5.7 | 0%
159 | 000008154 | Blanket | Blanket | Blanket | 1663596.465 | 1638884.711 | 0 | n.m.
160 | 000009160 | Blanket | Blanket | Blanket | 26248.592 | 26302.58 | 0 | n.m.
161 | ETN000110 | 2/1/2018 | Blanket | Blanket | 0 | 0 | 0 | n.m.
162 | P17083025 | 3/1/2019 | 2020-12-01 | 61.78% | 0 | 0 | -635.17 | 0%
163 | DR18K03B5 | 5/1/2018 | 2020-12-01 | 74.07% | 0 | 0 | -9675.01 | 0%
164 | P19091007 | 8/1/2019 | 2020-12-01 | 49.8% | 0 | 0 | -10460.05 | 0%
165 | P17225011 | 2/1/2018 | 2021-06-01 | 64.88% | 0 | 0 | -31175.65 | 0%
166 | DMS18KK08 | 12/1/2019 | 2020-10-01 | 39.67% | 0 | 0 | -32770.08 | 0%
167 | EDN014687 | 2/1/2018 | Blanket | Blanket | 0 | 0 | -35661.67 | 0%
168 | P17084001 | 11/1/2017 | 2020-10-01 | 82.72% | 0 | 0 | -74499.03 | 0%
169 | TREEREL18 | 4/1/2014 | Blanket | Blanket | 0 | 0 | -74821.96 | 0%
170 | DMS19KK01 | 2/1/2019 | 2020-10-01 | 69.74% | 0 | 0 | -88015.82 | 0%
171 | DX16K02A0 | 2/1/2017 | 2021-06-01 | 72.99% | 0 | 0 | -127618.17 | 0%
172 | Other Budgeted Projects | Other | Other | Other | 21037572.18 | 13287871.949 | 0 | Other
173 | Total GLBU 110 (Distribution) |  |  |  | 78433375.894 | 72714293.475 | 92183165.144 | 126.8%
174 | GLBU 117 (Generation)
175 | 000021737 | 2018-01-01 | 2020-04-01 | 99.88% | 8982.769 | 5256341.21 | 6313661.08 | 120.1%
176 | 000022392 | 2016-09-01 | 2019-12-01 | 110.2% | 6337298.546 | 2456251.425 | 3422858.149 | 139.4%
177 | 000005237 | Blanket | Blanket | Blanket | 0 | 0 | 3219411.06 | 0%
178 | ML119SC02 | 2018-08-01 | 2019-06-01 | 200% | 878892.725 | 1445747.071 | 2189520.41 | 151.4%
179 | 000022308 | 2018-11-01 | 2019-06-01 | 243.4% | 24870.356 | -1723978.457 | 1563525.66 | -90.69%
180 | BSPPB0013 | Blanket | Blanket | Blanket | 170672.21 | 96805.513 | 1180042.41 | 1219%
181 | IT1171421 | 2016-03-01 | 2019-12-01 | 108.8% | 3458.04 | 0 | 1176496.72 | 0%
182 | 000020310 | 2019-12-01 | 2024-12-01 | 6.623% | 224365.179 | 1202066.443 | 824772.15 | 68.61%
183 | ML1SC1810 | 2018-12-01 | 2019-05-01 | 321.9% | 629146.652 | 407796.43 | 727913.94 | 178.5%
184 | IT117BILL | 2017-07-01 | 2027-06-01 | 27.72% | 0 | 0 | 524059.66 | 0%
185 | ML1EC1302 | 2018-05-01 | 2019-12-01 | 120.9% | 1926324.933 | 1145726.809 | 288944.12 | 25.22%
186 | MLP19EP03 | 2019-02-01 | Blanket | Blanket | 0 | 350000 | 278795.24 | 79.66%
187 | ML019SP01 | 2019-05-01 | Blanket | Blanket | 0 | 0 | 264715.4 | 0%
188 | MLP19EP04 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 264612.56 | 0%
189 | ML120SP01 | 2019-12-01 | Blanket | Blanket | 0 | 0 | 261333.59 | 0%
190 | ML219SP06 | 2019-10-01 | Blanket | Blanket | 0 | 0 | 235323.74 | 0%
191 | MLP19MP01 | 2019-10-01 | Blanket | Blanket | 44389.673 | 382566.814 | 221904.82 | 58%
192 | ML219VP06 | 2019-10-01 | 2020-03-01 | 119.7% | 0 | 0 | 215676.74 | 0%
193 | BSPPBS348 | 2019-09-01 | 2020-02-01 | 138.6% | 0 | 214952.823 | 208781.5 | 97.13%
194 | ML019VP01 | 2019-01-01 | Blanket | Blanket | 164234.405 | 462564.592 | 199069.44 | 43.04%
195 | MLP19MP03 | 2019-03-01 | 2020-01-01 | 129.4% | 0 | 0 | 196112 | 0%
196 | MLP19MP02 | 2019-01-01 | Blanket | Blanket | 159671.409 | 148325.816 | 173949.13 | 117.3%
197 | ML219SP05 | 2019-10-01 | Blanket | Blanket | 0 | 396167.5 | 151680.96 | 38.29%
198 | BSPPBS363 | 2019-12-01 | Blanket | Blanket | 0 | 124080.436 | 139001.53 | 112%
199 | ML219SP04 | 2019-10-01 | Blanket | Blanket | 0 | 396167.5 | 138278.24 | 34.9%
200 | ML1E18C05 | 2017-09-01 | 2018-07-01 | 310.9% | 0 | -68389.718 | 126652.01 | -185.2%
201 | ML2VC1601 | 2017-07-01 | 2018-05-01 | 330.3% | 0 | 0 | 126272.37 | 0%
202 | ML119EP04 | 2019-01-01 | 2019-11-01 | 149.7% | 0 | 0 | 125889.25 | 0%
203 | ML219EP03 | 2019-07-01 | Blanket | Blanket | 0 | 0 | 125597.7 | 0%
204 | BSPPBS351 | 2019-06-01 | Blanket | Blanket | 167471.025 | 87976.133 | 124891.72 | 142%
205 | ML119SP08 | 2018-11-01 | 2020-02-01 | 112.9% | 0 | 0 | 122237.62 | 0%
206 | ML219VP07 | 2019-10-01 | 2020-03-01 | 119.7% | 0 | 0 | 119801.86 | 0%
207 | MLP19EP01 | 2019-01-01 | Blanket | Blanket | 0 | 0 | 115826.56 | 0%
208 | MLP18SP01 | 2019-04-01 | 2020-05-01 | 92.17% | 0 | 0 | 97242.24 | 0%
209 | ML019NP01 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 96061.74 | 0%
210 | ML019VP02 | 2018-11-01 | 2019-11-01 | 141.4% | 0 | 0 | 95198.63 | 0%
211 | BSPPBOUT1 | Blanket | Blanket | Blanket | 1057420.968 | 603250.122 | 89803.24 | 14.89%
212 | ML219VP08 | 2019-10-01 | 2020-03-01 | 119.7% | 0 | 0 | 88809.94 | 0%
213 | ML119EP07 | 2019-07-01 | Blanket | Blanket | 0 | 0 | 87812.07 | 0%
214 | ML1VC1601 | 2016-12-01 | 2017-12-01 | 333.2% | 0 | 0 | 87806.99 | 0%
215 | 000025231 | 2018-03-01 | Blanket | Blanket | 0 | 0 | 80969.2 | 0%
216 | ML219EP14 | 2019-11-01 | Blanket | Blanket | 0 | 0 | 77510.7 | 0%
217 | ML019EP02 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 75899.31 | 0%
218 | ML220VP01 | 2020-01-01 | 2020-12-01 | 26.87% | 0 | 0 | 64623.55 | 0%
219 | BSPPB0002 | Blanket | Blanket | Blanket | 94227.43 | 84085.706 | 59866.14 | 71.2%
220 | ARCFLA117 | Blanket | Blanket | Blanket | 0 | 0 | 56433.93 | 0%
221 | ML118SP22 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 56195.59 | 0%
222 | MLP19EP06 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 55892.18 | 0%
223 | ML118EP04 | 2019-02-01 | 2020-01-01 | 126.9% | 117851.366 | 110839.455 | 46183.28 | 41.67%
224 | ML119SP13 | 2019-05-01 | Blanket | Blanket | 0 | 0 | 45027.13 | 0%
225 | ML119SP14 | 2019-04-01 | 2019-11-01 | 170.6% | 0 | 0 | 45023.69 | 0%
226 | ML219SP07 | 2019-11-01 | Blanket | Blanket | 0 | 0 | 43824.09 | 0%
227 | ML019EP08 | 2019-07-01 | Blanket | Blanket | 0 | 0 | 41886.49 | 0%
228 | ML1NP1911 | 2019-03-01 | 2020-01-01 | 129.4% | 118891.667 | 111510.047 | 40169.2 | 36.02%
229 | MLP19EP02 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 40140.14 | 0%
230 | ML119SP17 | 2019-12-01 | Blanket | Blanket | 0 | 40000 | 38905.96 | 97.26%
231 | ML019NP06 | 2019-12-01 | Blanket | Blanket | 0 | 0 | 37408.69 | 0%
232 | ML119SP07 | 2019-01-01 | 2020-01-01 | 124.7% | 176777.081 | 166259.227 | 36454.88 | 21.93%
233 | ML019EP01 | 2019-04-01 | Blanket | Blanket | 0 | 0 | 35332.3 | 0%
234 | ML219EP02 | 2019-04-01 | 2020-05-01 | 92.17% | 0 | 0 | 33197.72 | 0%
235 | NRCCPKPCO | 2016-09-01 | 2018-06-01 | 204.9% | 41025.206 | -79683.338 | 33043.42 | -41.47%
236 | ML018EP11 | 2018-10-01 | 2019-11-01 | 138.1% | 0 | 0 | 30621.99 | 0%
237 | ML119EP05 | 2019-03-01 | 2019-07-01 | 324.6% | 0 | 0 | 28520.03 | 0%
238 | ML019EP10 | 2019-08-01 | 2020-02-01 | 132.1% | 0 | 0 | 27338.77 | 0%
239 | ML219VP05 | 2019-11-01 | 2020-03-01 | 124.8% | 0 | 0 | 25761.25 | 0%
240 | ML219EP01 | 2018-12-01 | 2020-01-01 | 122.7% | 0 | 0 | 25174.61 | 0%
241 | ML018EP14 | 2018-09-01 | 2020-03-01 | 105.5% | 0 | 0 | 24970.49 | 0%
242 | ML119SP16 | 2019-04-01 | 2019-11-01 | 170.6% | 0 | 0 | 24577.97 | 0%
243 | ML219EP16 | 2019-11-01 | 2020-01-01 | 247.5% | 0 | 0 | 23939.32 | 0%
244 | ML119EP01 | 2019-02-01 | 2019-11-01 | 155.3% | 0 | 0 | 22331.04 | 0%
245 | ML117EP04 | 2019-02-01 | 2019-12-01 | 139.9% | 145001.883 | 137032.421 | 21791.53 | 15.9%
246 | MLP20VP01 | 2020-02-01 | Blanket | Blanket | 0 | 0 | 20185.71 | 0%
247 | ML219VP11 | 2019-11-01 | Blanket | Blanket | 0 | 0 | 19537.94 | 0%
248 | ML020SP01 | 2019-12-01 | 2021-12-01 | 16.55% | 919649.144 | 150984.312 | 17889.15 | 11.85%
249 | ML119SP15 | 2019-04-01 | 2019-11-01 | 170.6% | 0 | 0 | 17556.68 | 0%
250 | ML219EP13 | 2019-01-01 | Blanket | Blanket | 0 | 0 | 16128.42 | 0%
251 | ML118EP10 | 2018-09-01 | 2019-11-01 | 135.4% | 0 | 0 | 15217.64 | 0%
252 | MLP20VP03 | 2020-03-01 | Blanket | Blanket | 0 | 0 | 15101.89 | 0%
253 | ML020VP01 | 2020-01-01 | Blanket | Blanket | 80554.182 | 0 | 14296.59 | 0%
254 | ML018VP01 | 2018-01-01 | 2020-03-01 | 103.8% | 0 | 0 | 14229.79 | 0%
255 | ML018NP01 | 2018-03-01 | Blanket | Blanket | 170209.193 | 154525.356 | 13908.23 | 9.001%
256 | MLP18EP08 | 2018-08-01 | 2019-11-01 | 133% | 0 | 0 | 12942.47 | 0%
257 | ML018NP07 | 2018-08-01 | 2020-03-01 | 105.2% | 0 | 0 | 12817.22 | 0%
258 | ML019EP11 | 2019-11-01 | 2020-05-01 | 82.97% | 0 | 0 | 12533.21 | 0%
259 | ML119EP12 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 12306.62 | 0%
260 | MLP20MP05 | 2020-02-01 | 2020-12-01 | 19.41% | 0 | 0 | 12105.72 | 0%
261 | ML015VP01 | 2015-06-01 | Blanket | Blanket | 0 | 0 | 11653.76 | 0%
262 | MLP20MP06 | 2020-02-01 | Blanket | Blanket | 0 | 0 | 11353.72 | 0%
263 | MLP18EP07 | 2018-07-01 | 2019-08-01 | 161.4% | 0 | 0 | 11047.99 | 0%
264 | ML119EP03 | 2018-12-01 | 2019-12-01 | 133.2% | 0 | 0 | 10794.76 | 0%
265 | ML219SP03 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 10760.08 | 0%
266 | MLP20EP02 | 2020-02-01 | 2020-12-01 | 19.41% | 0 | 0 | 10341.13 | 0%
267 | MLP20EP06 | 2020-01-01 | Blanket | Blanket | 0 | 0 | 10212.74 | 0%
268 | ML018NP12 | 2018-09-01 | Blanket | Blanket | 0 | 0 | 10155.1 | 0%
269 | ML018EP17 | 2018-10-01 | Blanket | Blanket | 0 | 0 | 9380.27 | 0%
270 | ML017EP02 | 2016-10-01 | 2019-08-01 | 123.5% | 0 | 0 | 9343.95 | 0%
271 | MLP18EP06 | 2018-01-01 | Blanket | Blanket | 118620.906 | 107958.806 | 9314.4 | 8.628%
272 | ML018MP06 | 2018-09-01 | Blanket | Blanket | 0 | 0 | 9221.36 | 0%
273 | ML016VP11 | 2016-11-01 | 2019-08-01 | 124.2% | 0 | 0 | 9119.91 | 0%
274 | ML119EP22 | 2019-12-01 | 2020-03-01 | 133% | 0 | 0 | 9033.26 | 0%
275 | ML219EP23 | 2019-11-01 | Blanket | Blanket | 0 | 0 | 8683.18 | 0%
276 | MLP17SP01 | 2017-05-01 | 2019-08-01 | 129.6% | 0 | 0 | 8635.15 | 0%
277 | ML219EP22 | 2019-09-01 | 2020-01-01 | 173.8% | 0 | 0 | 7038.04 | 0%
278 | ML118EP12 | 2018-01-01 | Blanket | Blanket | 0 | 0 | 6808.17 | 0%
279 | ML119SP09 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 6405.6 | 0%
280 | MLP19EP05 | 2019-07-01 | 2020-01-01 | 148.9% | 0 | 0 | 6351.09 | 0%
281 | MLP20VP02 | 2020-03-01 | 2020-12-01 | 10.91% | 0 | 0 | 6302.27 | 0%
282 | ML219EP19 | 2019-10-01 | 2020-04-01 | 99.45% | 0 | 0 | 5415.3 | 0%
283 | ML118EP01 | 2019-02-01 | 2019-11-01 | 155.3% | 89999.472 | 80809.143 | 5364.5 | 6.638%
284 | MLP18EP02 | 2018-07-01 | Blanket | Blanket | 40798.258 | 36822.355 | 5294.58 | 14.38%
285 | MLP20EP03 | 2020-02-01 | Blanket | Blanket | 0 | 0 | 4687.84 | 0%
286 | ML020MP01 | 2020-03-01 | Blanket | Blanket | 0 | 0 | 4402.72 | 0%
287 | ML119SP12 | 2019-01-01 | 2019-11-01 | 149.7% | 0 | 0 | 4365.9 | 0%
288 | ML219EP15 | 2019-10-01 | Blanket | Blanket | 0 | 0 | 4123.05 | 0%
289 | ML218EP13 | 2018-02-01 | 2020-01-01 | 112.9% | 0 | 0 | 3929.92 | 0%
290 | ML119SP10 | 2019-03-01 | 2019-07-01 | 324.6% | 0 | 0 | 3450.59 | 0%
291 | MLP20EP09 | 2020-03-01 | Blanket | Blanket | 0 | 0 | 3346.5 | 0%
292 | MLP20EP10 | 2020-02-01 | Blanket | Blanket | 0 | 0 | 2922.86 | 0%
293 | MLP20SP04 | 2020-03-01 | 2020-12-01 | 10.91% | 0 | 0 | 2617.34 | 0%
294 | ML017VP04 | 2017-03-01 | Blanket | Blanket | 0 | 0 | 2551.87 | 0%
295 | ML018NP03 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 2429.98 | 0%
296 | MLP19SP01 | 2020-03-01 | Blanket | Blanket | 68430.967 | 63568.573 | 2381.89 | 3.747%
297 | BSPPB0009 | 2020-03-01 | Blanket | Blanket | 0 | 0 | 2373.77 | 0%
298 | ML019EP09 | 2019-03-01 | 2020-01-01 | 129.4% | 0 | 0 | 2231.39 | 0%
299 | 000025026 | 2017-10-01 | 2020-03-01 | 103.4% | 0 | 0 | 2152.69 | 0%
300 | ML119SP11 | 2019-04-01 | 2019-10-01 | 199.5% | 0 | 0 | 1510.43 | 0%
301 | MLP20NP02 | 2020-03-01 | 2020-12-01 | 10.91% | 0 | 0 | 1355.23 | 0%
302 | MLP20SP03 | 2020-02-01 | Blanket | Blanket | 0 | 0 | 1224.01 | 0%
303 | MLP20NP01 | 2020-03-01 | Blanket | Blanket | 0 | 0 | 1140.42 | 0%
304 | ML018EP01 | 2018-02-01 | Blanket | Blanket | 71444.562 | 64430.28 | 1088.34 | 1.689%
305 | ML120VP01 | 2020-02-01 | 2020-12-01 | 19.41% | 0 | 0 | 896.39 | 0%
306 | ML019SP02 | 2020-03-01 | 2020-12-01 | 10.91% | 0 | 0 | 820.85 | 0%
307 | ML019EP04 | 2019-12-01 | 2020-04-01 | 99.18% | 24685.287 | 22838.517 | 753.63 | 3.3%
308 | ML018EP02 | 2018-07-01 | 2019-10-01 | 139.8% | 0 | 0 | 711.95 | 0%
309 | MLP18EP09 | 2018-09-01 | 2019-06-01 | 211.4% | 0 | 0 | 576.46 | 0%
310 | ML017NP01 | 2017-01-01 | 2019-11-01 | 114.6% | 0 | 0 | 395.34 | 0%
311 | ML018NP08 | 2018-08-01 | 2020-01-01 | 117.4% | 0 | 0 | 177.8 | 0%
312 | MLP20MP07 | 2020-03-01 | 2020-12-01 | 10.91% | 0 | 0 | 160.03 | 0%
313 | ML018NP04 | 2018-07-01 | 2019-06-01 | 190.7% | 0 | 0 | 146.89 | 0%
314 | ML018MP11 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 132.75 | 0%
315 | MLP18EP03 | 2018-01-01 | Blanket | Blanket | 192180.259 | 177139.503 | 100.12 | 0.05652%
316 | ML018VP06 | 2018-12-01 | 2020-03-01 | 106.6% | 0 | 0 | 62.4 | 0%
317 | ML018EP08 | 2018-02-01 | 2019-07-01 | 153.2% | 0 | 0 | 17.15 | 0%
318 | ML017VP03 | 2017-08-01 | 2019-07-01 | 139.2% | 0 | 0 | -14.81 | 0%
319 | ML018MP10 | 2018-11-01 | 2019-04-01 | 341.7% | 0 | 0 | -56.22 | 0%
320 | MLP18EP01 | 2018-01-01 | 2019-06-01 | 158.9% | 0 | 0 | -56.46 | 0%
321 | ML118SP11 | 2018-10-01 | 2019-04-01 | 300.5% | 0 | 0 | -65.03 | 0%
322 | ML218EP05 | 2018-03-01 | 2019-07-01 | 156.3% | 0 | 0 | -123.66 | 0%
323 | ML118SP07 | 2018-11-01 | Blanket | Blanket | 21256.207 | 19074.915 | -153.39 | -0.8041%
324 | ML018MP04 | 2018-07-01 | 2019-04-01 | 233.2% | 0 | 0 | -167.93 | 0%
325 | ML018MP09 | 2018-12-01 | 2019-07-01 | 229.2% | 0 | 0 | -177.59 | 0%
326 | ML018SP03 | 2018-04-01 | 2019-04-01 | 200% | 0 | 0 | -201.52 | 0%
327 | BSPPBS339 | 2018-11-01 | Blanket | Blanket | 0 | 0 | -259.74 | 0%
328 | ML018EP16 | 2018-10-01 | 2019-10-01 | 149.9% | 0 | 0 | -263.98 | 0%
329 | BSPPBS340 | 2018-11-01 | Blanket | Blanket | 0 | 0 | -346.31 | 0%
330 | ML218SP09 | 2018-07-01 | Blanket | Blanket | 21256.207 | 19074.915 | -361.57 | -1.896%
331 | MLP18EP04 | 2018-02-01 | Blanket | Blanket | 114122.505 | 104497.205 | -386.14 | -0.3695%
332 | ML118SP01 | 2018-03-01 | 2019-07-01 | 156.3% | 0 | 0 | -521.67 | 0%
333 | ML018NP11 | 2018-09-01 | 2019-04-01 | 272.2% | 0 | 0 | -592.22 | 0%
334 | ML018MP03 | 2018-01-01 | 2020-02-01 | 107.8% | 0 | 0 | -1334.88 | 0%
335 | ML018VP02 | 2018-10-01 | 2019-06-01 | 225.1% | 0 | 0 | -1844.85 | 0%
336 | ML117VP06 | 2018-03-01 | 2019-06-01 | 166.5% | 0 | 0 | -3432.9 | 0%
337 | ML018VP04 | 2018-07-01 | 2019-08-01 | 161.4% | 0 | 0 | -3797.81 | 0%
338 | ML218SP10 | 2018-01-01 | Blanket | Blanket | 0 | 0 | -3852.67 | 0%
339 | Other Budgeted Projects | Other | Other | Other | 13233965 | 9575339 | 0 | Other
340 | Total GLBU 117 (Generation) |  |  |  | 27658145.672 | 24531524.86 | 27785373.519 | 113.3%
341 | GLBU 180 (Transmission)
342 | P13064029 | 8/1/2017 | 2020-12-18 | 78.79% | 4187641.736 | 4187641.736 | 9042728.83 | 215.9%
343 | A15702033 | 5/1/2017 | 2019-10-15 | 118.7% | 9609276.577 | 9609276.577 | 4676180.29 | 48.66%
344 | P16113009 | 11/1/2017 | 2019-11-27 | 116.5% | 6614454.337 | 6614454.337 | 4624747.38 | 69.92%
345 | DP16K02B0 | 4/1/2018 | 2019-10-25 | 127.6% | 0 | 0 | 3168765.64 | 0%
346 | A15702027 | 5/1/2017 | 2020-05-11 | 96.29% | 2061336.457 | 2061336.457 | 2982645.654 | 144.7%
347 | 000010377 | Blanket | Blanket | Blanket | 142133.131 | 142133.131 | 2514751.41 | 1769%
348 | B180KYLRC | 2/1/2017 | Blanket | Blanket | 411557.842 | 411557.842 | 2457731.51 | 597.2%
349 | P13064030 | 9/1/2017 | 2021-11-15 | 61.33% | 4855797.276 | 4855797.276 | 2364614.47 | 48.7%
350 | P10115014 | 7/1/2017 | 2019-11-14 | 115.9% | 1876865.534 | 1876865.534 | 2305034.46 | 122.8%
351 | A15702034 | 5/1/2017 | 2020-10-16 | 84.26% | 0 | 0 | 1511901.87 | 0%
352 | A19750002 | 5/1/2019 | 2020-01-28 | 123.2% | 0 | 0 | 1375374.46 | 0%
353 | A19750001 | 5/1/2019 | 2019-11-13 | 170.9% | 0 | 0 | 1366065.88 | 0%
354 | A15702028 | 5/1/2017 | 2019-07-23 | 131% | 885638.081 | 885638.081 | 1254530.28 | 141.7%
355 | P10115002 | 3/1/2017 | 2019-12-19 | 110.1% | 429782.812 | 429782.812 | 1178884.23 | 274.3%
356 | 000005273 | Charges Began Prior to Jan 2015 | 2018-01-23 | n.m. | 0 | 0 | 1097326.58 | 0%
357 | A17750008 | 3/1/2019 | 2019-12-26 | 132% | 0 | 0 | 1014843.55 | 0%
358 | P10115013 | 7/1/2017 | 2020-05-11 | 96.08% | 675798.843 | 675798.843 | 956566.03 | 141.5%
359 | P10115001 | 9/1/2016 | 2020-06-18 | 94.3% | 248952.037 | 248952.037 | 846778.54 | 340.1%
360 | A15042010 | Charges Began Prior to Jan 2015 | 2019-11-14 | n.m. | 1093822.817 | 1093822.817 | 846608.91 | 77.4%
361 | A14068001 | Charges Began Prior to Jan 2015 | 2022-09-15 | n.m. | 948843.809 | 948843.809 | 721608.33 | 76.05%
362 | P13064031 | 12/1/2017 | 2021-11-15 | 58.89% | 58997.877 | 58997.877 | 631409.45 | 1070%
363 | A17750007 | 2/1/2019 | 2019-08-05 | 229.2% | 0 | 0 | 612050.74 | 0%
364 | 000012898 | Blanket | Blanket | Blanket | 716129.616 | 716129.616 | 608303.74 | 84.94%
365 | P10115010 | 3/1/2017 | 2019-10-17 | 117.3% | 384340.491 | 384340.491 | 519609.9 | 135.2%
366 | P18221017 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 516711.33 | 0%
367 | A19750104 | 9/1/2019 | 2020-01-28 | 142.3% | 0 | 0 | 487077.81 | 0%
368 | A19750003 | 6/1/2019 | 2019-12-31 | 142.7% | 0 | 0 | 477020.61 | 0%
369 | B180KYSRR | 10/1/2016 | Blanket | Blanket | 213368.368 | 213368.368 | 450057.87 | 210.9%
370 | A17212001 | 7/1/2018 | 2019-10-09 | 137.4% | 0 | 0 | 436755 | 0%
371 | A15710034 | 8/1/2018 | 2019-09-09 | 150.5% | 587779.376 | 587779.376 | 341710.44 | 58.14%
372 | A15702047 | 5/1/2017 | 2020-12-01 | 81.3% | 325540.823 | 325540.823 | 341529.38 | 104.9%
373 | A18730016 | 6/1/2018 | 2019-09-26 | 138.8% | 0 | 0 | 340674.22 | 0%
374 | IT1801421 | 3/1/2016 | 2019-12-31 | 106.5% | 0 | 0 | 338067.37 | 0%
375 | A15710035 | 1/1/2019 | 2020-07-22 | 80.11% | 340290.27 | 340290.27 | 337609.14 | 99.21%
376 | P13064025 | 4/1/2017 | 2020-12-18 | 80.69% | 30226.516 | 30226.516 | 330508.54 | 1093%
377 | P10115015 | 7/1/2017 | 2019-10-17 | 119.8% | 250460.836 | 250460.836 | 322640.01 | 128.8%
378 | P10115003 | 3/1/2017 | 2019-11-15 | 113.9% | 366127.63 | 366127.63 | 320225.95 | 87.46%
379 | DP14K02C0 | 8/1/2018 | 2021-07-21 | 56.04% | 0 | 0 | 287732.92 | 0%
380 | A18730015 | 6/1/2018 | 2019-03-01 | 245.1% | 0 | 0 | 241441.44 | 0%
381 | A15042011 | Charges Began Prior to Jan 2015 | 2019-05-16 | n.m. | 183752.859 | 183752.859 | 236740.52 | 128.8%
382 | P19091011 | 8/1/2019 | 2022-11-15 | 20.22% | 0 | 0 | 236516.31 | 0%
383 | A15710033 | 12/1/2017 | 2020-02-14 | 105.7% | 0 | 0 | 223972.04 | 0%
384 | A15702030 | 5/1/2017 | 2020-12-01 | 81.3% | 164274.202 | 164274.202 | 211570.02 | 128.8%
385 | IT180BILL | 7/1/2017 | Blanket | Blanket | 0 | 0 | 209927.79 | 0%
386 | TP0921005 | 4/1/2014 | 2014-10-28 | 1043% | 0 | 0 | 207547.41 | 0%
387 | DR19K04B0 | 5/1/2019 | 2019-11-12 | 171.8% | 0 | 0 | 195049.208 | 0%
388 | DR19K04B1 | 6/1/2019 | 2019-11-12 | 185.4% | 0 | 0 | 190096.53 | 0%
389 | P13064021 | 5/1/2016 | 2020-12-03 | 85.27% | 115675.383 | 115675.383 | 185455.16 | 160.3%
390 | DR18K02B1 | 9/1/2018 | 2019-06-28 | 192.3% | 0 | 0 | 182601.416 | 0%
391 | A15702035 | 5/1/2017 | 2021-12-17 | 62.98% | -1.182 | -1.182 | 157942.71 | -13362327%
392 | DP14K02C1 | 10/1/2018 | 2021-07-21 | 53.42% | 0 | 0 | 149060.72 | 0%
393 | A15042012 | 6/1/2017 | 2019-11-15 | 115.3% | 54651.858 | 54651.858 | 145896.07 | 267%
394 | DR18K02B2 | 10/1/2018 | 2019-06-28 | 202.6% | 0 | 0 | 143729.984 | 0%
395 | A15702007 | 6/1/2017 | 2018-06-28 | 263.8% | 0 | 0 | 127949.1 | 0%
396 | A15702029 | 6/1/2017 | 2022-11-18 | 51.8% | 2890809.267 | 2890809.267 | 127020.05 | 4.394%
397 | P11161025 | 8/1/2017 | 2018-10-18 | 219.6% | 0 | 0 | 117162.9 | 0%
398 | P17225004 | 3/1/2019 | 2023-01-12 | 28.03% | 0 | 0 | 101024.23 | 0%
399 | P17110001 | 10/1/2017 | 2021-11-19 | 60.4% | 9010628.817 | 9010628.817 | 97526.26 | 1.082%
400 | A15710041 | 12/1/2018 | 2019-08-19 | 186.2% | 17193.976 | 17193.976 | 94090.42 | 547.2%
401 | P18221013 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 91982.37 | 0%
402 | P11161023 | 8/1/2017 | 2018-09-26 | 231.1% | 0 | 0 | 91730.06 | 0%
403 | P13064002 | 8/1/2016 | 2021-11-15 | 69.25% | 1703014.064 | 1703014.064 | 88682.73 | 5.207%
404 | P17083001 | 3/1/2019 | 2023-11-15 | 23.02% | 281178.243 | 281178.243 | 86810.89 | 30.87%
405 | A17938021 | 10/1/2017 | 2018-11-29 | 215.1% | 0 | 0 | 81380.21 | 0%
406 | DR19K06D0 | 4/1/2019 | 2020-04-01 | 99.73% | 0 | 0 | 80491.19 | 0%
407 | P17225003 | 3/1/2019 | 2023-01-12 | 28.03% | 1041366.793 | 1041366.793 | 77311.42 | 7.424%
408 | B180KYTRE | 10/1/2016 | Blanket | Blanket | 0 | 0 | 73246.37 | 0%
409 | P17225013 | 2/1/2018 | 2023-06-29 | 39.97% | 3256796.772 | 3256796.772 | 69402.81 | 2.131%
410 | P11063002 | 7/1/2017 | 2021-06-04 | 70.01% | 0 | 0 | 67706 | 0%
411 | DR19K05D0 | 6/1/2019 | 2020-08-28 | 66.96% | 0 | 0 | 65618.69 | 0%
412 | P19215003 | 8/1/2019 | 2021-11-19 | 28.89% | 0 | 0 | 60526.66 | 0%
413 | P18025006 | 2/1/2018 | 2023-11-17 | 37.3% | 14200.471 | 14200.471 | 59457.15 | 418.7%
414 | P19091003 | 7/1/2018 | 2022-11-15 | 39.99% | 0 | 0 | 59387.72 | 0%
415 | P17084003 | 10/1/2017 | 2021-12-02 | 59.88% | 2331354.843 | 2331354.843 | 59280.84 | 2.543%
416 | A15702053 | 5/1/2017 | 2017-12-16 | 465.1% | 0 | 0 | 54365.4 | 0%
417 | A15702032 | 5/1/2017 | 2021-12-17 | 62.98% | -0.267 | -0.267 | 44554.7 | -16687154%
418 | A15702036 | 5/1/2017 | 2021-12-17 | 62.98% | 50.908 | 50.908 | 40582.24 | 79717%
419 | A15042007 | Charges Began Prior to Jan 2015 | 2019-07-31 | n.m. | 0 | 0 | 34643.45 | 0%
420 | B180KYCSV | 9/1/2019 | Blanket | Blanket | 0 | 0 | 34345.43 | 0%
421 | TA1807311 | 4/1/2014 | 2020-12-31 | 88.85% | 0 | 0 | 32193.68 | 0%
422 | P18221005 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 31809.59 | 0%
423 | P19091012 | 8/1/2019 | 2022-11-15 | 20.22% | 0 | 0 | 31539.88 | 0%
424 | A15702006 | 4/1/2016 | 2021-12-31 | 69.52% | 0 | 0 | 30286.81 | 0%
425 | DR19K06D1 | 5/1/2019 | 2019-12-31 | 137.3% | 0 | 0 | 26925.86 | 0%
426 | A15710024 | 8/1/2017 | 2019-10-31 | 118.5% | 0 | 0 | 26298.27 | 0%
427 | P17084007 | 10/1/2017 | 2023-11-10 | 40.88% | 1584958.649 | 1584958.649 | 26276.76 | 1.658%
428 | KYCR30003 | 3/1/2019 | 2019-11-01 | 161.6% | 0 | 0 | 25243.85 | 0%
429 | P19092013 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 25130.82 | 0%
430 | A20705052 | 9/1/2019 | Preliminary | Preliminary | 0 | 0 | 24749.27 | 0%
431 | P19104010 | 8/1/2019 | 2022-08-30 | 21.6% | 0 | 0 | 23390.53 | 0%
432 | P11161010 | 7/1/2015 | 2018-10-18 | 144% | 0 | 0 | 21895.12 | 0%
433 | A20705037 | 8/1/2019 | Preliminary | Preliminary | 0 | 0 | 21382.09 | 0%
434 | A16902001 | 11/1/2016 | 2018-12-06 | 162.9% | 0 | 0 | 19608.49 | 0%
435 | P17225001 | 3/1/2019 | 2023-01-12 | 28.03% | 911063.686 | 911063.686 | 19519.43 | 2.142%
436 | A20705028 | 7/1/2019 | Preliminary | Preliminary | 0 | 0 | 17305.47 | 0%
437 | P19215005 | 8/1/2019 | 2021-11-19 | 28.89% | 0 | 0 | 16687.8 | 0%
438 | B180KYRMB | 2/1/2017 | Blanket | Blanket | 0 | 0 | 15117.27 | 0%
439 | P17083003 | 3/1/2019 | 2023-11-15 | 23.02% | 0 | 0 | 15030.06 | 0%
440 | P19092019 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 14270.25 | 0%
441 | P19305001 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 14256.94 | 0%
442 | DP16K03C0 | 11/1/2019 | 2022-10-04 | 14.14% | 0 | 0 | 14009.38 | 0%
443 | A17750109 | 6/1/2019 | 2019-11-29 | 168% | 0 | 0 | 13816.31 | 0%
444 | A18730003 | 8/1/2017 | 2020-10-16 | 83.02% | 0 | 0 | 13560.91 | 0%
445 | A20705029 | 7/1/2019 | Preliminary | Preliminary | 0 | 0 | 13553.48 | 0%
446 | A18730004 | 8/1/2017 | 2021-12-17 | 60.85% | 0 | 0 | 12888.9 | 0%
447 | A15710052 | 11/1/2019 | 2020-07-29 | 55.72% | 1104.085 | 1104.085 | 12629.2 | 1144%
448 | P18221002 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 12450.02 | 0%
449 | P17076001 | 9/1/2017 | 2023-11-01 | 41.83% | 260631.397 | 260631.397 | 12395.8 | 4.756%
450 | P17083005 | 4/1/2019 | 2023-11-15 | 21.61% | 0 | 0 | 12084.07 | 0%
451 | A15710036 | 12/1/2017 | 2020-02-14 | 105.7% | 0 | 0 | 11849.1 | 0%
452 | P19215001 | 8/1/2019 | 2021-11-19 | 28.89% | 0 | 0 | 11710.8 | 0%
453 | A18730005 | 8/1/2017 | 2021-12-17 | 60.85% | 0 | 0 | 11286.31 | 0%
454 | P11161022 | 3/1/2017 | 2018-03-30 | 285.8% | 0 | 0 | 11267.31 | 0%
455 | A18730001 | 8/1/2017 | 2021-12-17 | 60.85% | 0 | 0 | 11263.8 | 0%
456 | P17110003 | 11/1/2017 | 2021-11-19 | 59.57% | 311802.957 | 311802.957 | 11202.7 | 3.593%
457 | A18730013 | 8/1/2017 | 2018-05-31 | 321.1% | 0 | 0 | 10907.02 | 0%
458 | A20705035 | 9/1/2019 | 2024-03-31 | 12.67% | 0 | 0 | 10596.82 | 0%
459 | A18502002 | 10/1/2017 | 2019-04-15 | 162.6% | 0 | 0 | 10577.88 | 0%
460 | A20705083 | 10/1/2019 | Preliminary | Preliminary | 0 | 0 | 10559.81 | 0%
461 | A15710022 | 1/1/2017 | 2020-02-14 | 104% | 0 | 0 | 10436.26 | 0%
462 | SI180KYRE | 8/1/2019 | 2021-12-31 | 27.52% | 0 | 0 | 10432.94 | 0%
463 | A20705082 | 10/1/2019 | Preliminary | Preliminary | 0 | 0 | 10179.45 | 0%
464 | A15710037 | 12/1/2017 | 2019-08-12 | 137.5% | 27498.787 | 27498.787 | 10110.59 | 36.77%
465 | P19092007 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 10029.86 | 0%
466 | A18730002 | 8/1/2017 | 2019-10-15 | 120.9% | -0.043 | -0.043 | 9453.96 | -21985953%
467 | P19092008 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 9376.12 | 0%
468 | A17750107 | 4/1/2019 | 2019-08-05 | 289.7% | 0 | 0 | 9200.55 | 0%
469 | A20705077 | 10/1/2019 | Preliminary | Preliminary | 0 | 0 | 9072.48 | 0%
470 | A20705078 | 10/1/2019 | Preliminary | Preliminary | 0 | 0 | 9003.95 | 0%
471 | P14030008 | 6/1/2016 | 2023-11-15 | 51.38% | 156314.365 | 156314.365 | 8855.06 | 5.665%
472 | A20705073 | 10/1/2019 | 2023-10-20 | 12.3% | 0 | 0 | 8696.14 | 0%
473 | B180KYSRC | 12/1/2016 | Blanket | Blanket | 155059.949 | 155059.949 | 8683.91 | 5.6%
474 | A19750101 | 6/1/2019 | 2019-11-13 | 184.2% | 0 | 0 | 7780.32 | 0%
475 | P19092011 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 7538.65 | 0%
476 | A20705036 | 9/1/2019 | 2024-03-31 | 12.67% | 0 | 0 | 7088 | 0%
477 | A15710044 | 4/1/2019 | 2020-06-23 | 81.29% | 1182.945 | 1182.945 | 7056.38 | 596.5%
478 | P17110002 | 11/1/2017 | 2021-11-19 | 59.57% | 265697.018 | 265697.018 | 7003.25 | 2.636%
479 | P13064003 | 5/1/2016 | 2021-11-15 | 70.65% | 219377.045 | 219377.045 | 6923.68 | 3.156%
480 | P19215004 | 8/1/2019 | 2021-11-19 | 28.89% | 0 | 0 | 6805.92 | 0%
481 | A20705067 | 11/1/2019 | Preliminary | Preliminary | 0 | 0 | 6753.93 | 0%
482 | A15710058 | 11/1/2019 | 2021-01-21 | 33.78% | 11726.091 | 11726.091 | 6679 | 56.96%
483 | P19104012 | 8/1/2019 | 2022-08-30 | 21.6% | 0 | 0 | 6221.25 | 0%
484 | A17042001 | 2/1/2018 | 2018-12-06 | 256.2% | 0 | 0 | 6173.4 | 0%
485 | P19305010 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 6111.5 | 0%
486 | P19215006 | 8/1/2019 | 2021-11-19 | 28.89% | 0 | 0 | 6044.69 | 0%
487 | P18221003 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 5476.83 | 0%
488 | P17084026 | 9/1/2017 | 2024-07-05 | 37.7% | 0.87 | 0.87 | 5467.63 | 628463%
489 | P16116005 | 7/1/2017 | 2025-11-15 | 32.82% | 92659.716 | 92659.716 | 5391.8 | 5.819%
490 | A13212035 | Charges Began Prior to Jan 2015 | 2018-07-27 | n.m. | 0 | 0 | 5117.07 | 0%
491 | A20705001 | 8/1/2019 | 2022-10-31 | 20.47% | 0 | 0 | 5029.42 | 0%
492 | A15710043 | 4/1/2019 | 2020-06-23 | 81.29% | 1104.085 | 1104.085 | 4843.62 | 438.7%
493 | A15710061 | 10/1/2019 | 2021-01-14 | 38.64% | 7817.394 | 7817.394 | 4841.01 | 61.93%
494 | 000025230 | Blanket | Blanket | Blanket | 0 | 0 | 4774.09 | 0%
495 | P13064020 | 5/1/2017 | 2020-12-03 | 81.17% | 5336.503 | 5336.503 | 4469.49 | 83.75%
496 | P19092012 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 4458.68 | 0%
497 | P19092017 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 4409.79 | 0%
498 | P18221004 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 4335.09 | 0%
499 | A15702025 | 6/1/2017 | 2018-12-06 | 187% | 0 | 0 | 4318.83 | 0%
500 | P17225015 | 2/1/2018 | 2023-06-29 | 39.97% | 3634720.176 | 3634720.176 | 4250.47 | 0.1169%
501 | P17110005 | 10/1/2017 | 2021-11-19 | 60.4% | 275633.565 | 275633.565 | 4218.44 | 1.53%
502 | P19091004 | 7/1/2018 | 2022-11-15 | 39.99% | 0 | 0 | 3962.3 | 0%
503 | P18221010 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 3882.1 | 0%
504 | A15710045 | 4/1/2019 | 2020-06-23 | 81.29% | 112570.584 | 112570.584 | 3861.87 | 3.431%
505 | P19092018 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 3666.22 | 0%
506 | A15710046 | 4/1/2019 | 2020-06-23 | 81.29% | 84427.938 | 84427.938 | 3427.87 | 4.06%
507 | A14068005 | Charges Began Prior to Jan 2015 | 2018-12-28 | n.m. | 0 | 0 | 3408.69 | 0%
508 | P14030102 | 12/1/2017 | 2023-09-05 | 40.45% | 439418.079 | 439418.079 | 3228.21 | 0.7347%
509 | P17083002 | 3/1/2019 | 2023-11-15 | 23.02% | 56818.812 | 56818.812 | 3106.85 | 5.468%
510 | P18025007 | 2/1/2018 | 2023-11-17 | 37.3% | 0 | 0 | 3080.43 | 0%
511 | A15710064 | 3/1/2019 | 2020-08-10 | 75% | 91204.067 | 91204.067 | 2983.46 | 3.271%
512 | A20705057 | 9/1/2019 | Preliminary | Preliminary | 0 | 0 | 2977.59 | 0%
513 | A15710047 | 4/1/2019 | 2020-06-23 | 81.29% | 165728.921 | 165728.921 | 2969.08 | 1.792%
514 | A15702013 | 6/1/2017 | 2017-12-21 | 509.4% | 0 | 0 | 2839.11 | 0%
515 | P17110006 | 7/1/2018 | 2021-11-19 | 51.66% | 6290.554 | 6290.554 | 2823.05 | 44.88%
516 | P14030013 | 9/1/2016 | 2023-11-15 | 49.68% | 161792.441 | 161792.441 | 2807.16 | 1.735%
517 | P17110007 | 3/1/2019 | 2021-11-19 | 39.84% | 5091.318 | 5091.318 | 2746.82 | 53.95%
518 | P17083006 | 3/1/2019 | 2023-11-15 | 23.02% | 220353.643 | 220353.643 | 2683.69 | 1.218%
519 | A15710071 | 7/1/2019 | 2021-08-26 | 34.82% | 0 | 0 | 2658.4 | 0%
520 | P16113004 | 12/1/2016 | 2019-11-27 | 111.5% | 0 | 0 | 2615.91 | 0%
521 | P14030104 | 12/1/2017 | 2024-01-22 | 37.94% | 92643.808 | 92643.808 | 2555.97 | 2.759%
522 | P17084019 | 9/1/2017 | 2023-11-10 | 41.66% | 0.558 | 0.558 | 2321.41 | 416023%
523 | P17084016 | 9/1/2017 | 2024-07-05 | 37.7% | 0 | 0 | 2300.13 | 0%
524 | DP16K03C1 | 12/1/2019 | 2022-10-04 | 11.66% | 0 | 0 | 1843.15 | 0%
525 | P11161008 | 7/1/2017 | 2018-06-10 | 291.9% | 0 | 0 | 1815.89 | 0%
526 | A19511004 | 5/1/2019 | 2020-12-31 | 54.92% | 0 | 0 | 1700.75 | 0%
527 | P11161009 | 7/1/2017 | 2018-03-09 | 400% | 0 | 0 | 1677.05 | 0%
528 | P17076005 | 9/1/2017 | 2023-11-01 | 41.83% | 0 | 0 | 1647.34 | 0%
529 | P17084022 | 9/1/2017 | 2024-07-05 | 37.7% | 7.54 | 7.54 | 1562.31 | 20720%
530 | P19305009 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 1505.76 | 0%
531 | P17225017 | 2/1/2018 | 2023-06-29 | 39.97% | 895857.654 | 895857.654 | 1460.45 | 0.163%
532 | A15710042 | 4/1/2019 | 2020-06-23 | 81.29% | 98499.258 | 98499.258 | 1419.58 | 1.441%
533 | P16113003 | 12/1/2016 | 2019-11-18 | 112.4% | 114586.801 | 114586.801 | 1337.24 | 1.167%
534 | P19305016 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 1291.96 | 0%
535 | A20705079 | 11/1/2019 | Preliminary | Preliminary | 0 | 0 | 1116.23 | 0%
536 | SI180KYUN | 8/1/2019 | Blanket | Blanket | 0 | 0 | 1108.83 | 0%
537 | A19511003 | 5/1/2019 | 2020-12-31 | 54.92% | 0 | 0 | 1085.76 | 0%
538 | P17083031 | 4/1/2019 | 2023-11-15 | 21.61% | 556.35 | 556.35 | 1070.93 | 192.5%
539 | P17084036 | 11/1/2017 | 2024-07-05 | 36.14% | 0 | 0 | 1056.36 | 0%
540 | P17076010 | 6/1/2018 | 2023-11-01 | 33.8% | 0 | 0 | 847.49 | 0%
541 | P17083008 | 3/1/2019 | 2023-11-15 | 23.02% | 249.024 | 249.024 | 838.77 | 336.8%
542 | A15702054 | 5/1/2017 | 2017-08-28 | 895% | 0 | 0 | 822.73 | 0%
543 | P19305002 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 811.74 | 0%
544 | P19305017 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 811.74 | 0%
545 | A20705080 | 11/1/2019 | Preliminary | Preliminary | 0 | 0 | 806.43 | 0%
546 | A20705081 | 11/1/2019 | Preliminary | Preliminary | 0 | 0 | 806.43 | 0%
547 | A15710050 | 4/1/2019 | 2020-08-12 | 73.15% | 165728.921 | 165728.921 | 780.22 | 0.4708%
548 | P18025013 | 2/1/2018 | 2023-11-17 | 37.3% | 0 | 0 | 762.6 | 0%
549 | DP14K02T0 | 10/1/2018 | 2021-07-21 | 53.42% | 0 | 0 | 708.28 | 0%
550 | P19305018 | 8/1/2019 | 2023-10-20 | 15.77% | 0 | 0 | 695.07 | 0%
551 | P17084037 | 11/1/2017 | 2024-07-05 | 36.14% | 0 | 0 | 680.65 | 0%
552 | P17083007 | 3/1/2019 | 2023-11-15 | 23.02% | 439794.427 | 439794.427 | 673.37 | 0.1531%
553 | P17076006 | 10/1/2017 | 2023-11-01 | 41.04% | 99915.295 | 99915.295 | 585.56 | 0.5861%
554 | P14030103 | 12/1/2017 | 2023-11-15 | 39.13% | 852224.104 | 852224.104 | 570.5 | 0.06694%
555 | P16116002 | 11/1/2016 | 2025-11-15 | 37.75% | 0 | 0 | 532.4 | 0%
556 | A15702062 | 5/1/2019 | 2020-12-01 | 57.76% | 17177.439 | 17177.439 | 492.41 | 2.867%
557 | P16116003 | 11/1/2016 | 2025-11-15 | 37.75% | 83002.59 | 83002.59 | 471.52 | 0.5681%
558 | P18221014 | 7/1/2018 | 2022-09-01 | 41.96% | 0 | 0 | 422.53 | 0%
559 | ITCB18000 | 7/1/2017 | Blanket | Blanket | 0 | 0 | 386.86 | 0%
560 | P17083034 | 3/1/2019 | 2023-11-15 | 23.02% | 74.441 | 74.441 | 384.98 | 517.2%
561 | P14030002 | 3/1/2017 | 2023-12-19 | 45.33% | 14743.599 | 14743.599 | 344.75 | 2.338%
562 | P17084017 | 9/1/2017 | 2023-11-10 | 41.66% | -0.322 | -0.322 | 272.93 | -84761%
563 | P18025010 | 2/1/2018 | 2023-11-17 | 37.3% | 0 | 0 | 271.73 | 0%
564 | P18025008 | 2/1/2018 | 2023-11-17 | 37.3% | 0 | 0 | 217.46 | 0%
565 | P17225016 | 2/1/2018 | 2023-06-29 | 39.97% | 175640.238 | 175640.238 | 195.44 | 0.1113%
566 | P17225018 | 2/1/2018 | 2023-06-29 | 39.97% | 3236277.35 | 3236277.35 | 163 | 0.005037%
567 | P17225014 | 2/1/2018 | 2023-06-29 | 39.97% | 45352.294 | 45352.294 | 162.17 | 0.3576%
568 | P17084023 | 9/1/2017 | 2024-07-05 | 37.7% | 7.536 | 7.536 | 150.01 | 1991%
569 | P17084021 | 9/1/2017 | 2024-07-05 | 37.7% | 583.88 | 583.88 | 105.57 | 18.08%
570 | P17084038 | 11/1/2017 | 2024-07-05 | 36.14% | 0 | 0 | 104.61 | 0%
571 | P17084020 | 9/1/2017 | 2023-11-10 | 41.66% | 0.508 | 0.508 | 100.56 | 19795%
572 | A15702056 | 8/1/2017 | 2020-05-04 | 96.62% | 0 | 0 | 97.35 | 0%
573 | A15042005 | Charges Began Prior to Jan 2015 | 2019-01-18 | n.m. | 0 | 0 | 97.15 | 0%
574 | P17084029 | 10/1/2017 | 2024-07-05 | 36.94% | 0 | 0 | 87.69 | 0%
575 | P17084013 | 9/1/2017 | 2024-07-05 | 37.7% | 0.594 | 0.594 | 85.23 | 14348%
576 | P18025009 | 2/1/2018 | 2023-11-17 | 37.3% | 0 | 0 | 73.98 | 0%
577 | P18025012 | 2/1/2018 | 2023-11-17 | 37.3% | 0 | 0 | 72.29 | 0%
578 | P17084018 | 9/1/2017 | 2023-11-10 | 41.66% | 0 | 0 | 63.04 | 0%
579 | P14030101 | 3/1/2017 | 2023-11-15 | 45.96% | 22755.031 | 22755.031 | 24.48 | 0.1076%
580 | A19511007 | 5/1/2019 | 2020-12-31 | 54.92% | 0 | 0 | 20.36 | 0%
581 | A19511005 | 5/1/2019 | 2020-12-31 | 54.92% | 0 | 0 | 18.87 | 0%
582 | A19511006 | 5/1/2019 | 2020-12-31 | 54.92% | 0 | 0 | 18.87 | 0%
583 | A19511002 | 5/1/2019 | 2020-12-31 | 54.92% | 0 | 0 | 8.84 | 0%
584 | P17083026 | 3/1/2019 | 2020-12-31 | 59.02% | 67.715 | 67.715 | 8.46 | 12.49%
585 | P14030015 | 11/1/2016 | 2023-11-15 | 48.48% | 16832.186 | 16832.186 | 7.71 | 0.04581%
586 | 000017437 | Charges Began Prior to Jan 2015 | 2015-12-31 | n.m. | 0 | 0 | 7.46 | 0%
587 | P14030016 | 11/1/2016 | 2023-11-15 | 48.48% | 533855.938 | 533855.938 | 7.24 | 0.001356%
588 | A15710051 | 10/1/2019 | 2020-08-12 | 57.59% | 243902.931 | 243902.931 | 7.276e-12 | n.m.
589 | A15710048 | 4/1/2019 | 2020-08-12 | 73.15% | 98499.258 | 98499.258 | 0 | n.m.
590 | A21212002 | 6/1/2019 | 2020-06-01 | 83.06% | 0 | 0 | 0 | n.m.
591 | P19092021 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | 0 | n.m.
592 | ETN000180 | 2/1/2018 | Blanket | Blanket | 0 | 0 | 0 | n.m.
593 | A16928015 | 1/1/2019 | 2020-05-05 | 92.86% | 0 | 0 | -17.19 | 0%
594 | P17074005 | 7/1/2017 | 2019-04-01 | 157.1% | 0 | 0 | -137.17 | 0%
595 | P18066002 | 2/1/2018 | 2020-06-01 | 92.71% | 0.071 | 0.071 | -354.81 | -499732%
596 | A15705185 | 5/1/2019 | 2017-06-01 | -47.93% | 0 | 0 | -465.43 | 0%
597 | P19092020 | 8/1/2019 | 2023-10-01 | 15.97% | 0 | 0 | -613.85 | 0%
598 | A15702040 | 5/1/2017 | 2019-05-01 | 145.9% | 0 | 0 | -1304.76 | 0%
599 | P18066005 | 2/1/2018 | 2020-06-01 | 92.71% | 202768.176 | 202768.176 | -1375.94 | -0.6786%
600 | P11161024 | 8/1/2017 | 2018-09-26 | 231.1% | 0 | 0 | -1508.67 | 0%
601 | P18066001 | 2/1/2018 | 2020-06-01 | 92.71% | 0.071 | 0.071 | -1546.49 | -2178155%
602 | P18066003 | 2/1/2018 | 2020-06-01 | 92.71% | 202768.176 | 202768.176 | -1919.92 | -0.9469%
603 | P11161026 | 8/1/2017 | 2018-10-18 | 219.6% | 0 | 0 | -3132.22 | 0%
604 | P18025005 | 2/1/2018 | 2023-11-17 | 37.3% | 4758458.812 | 4758458.812 | -18029.3 | -0.3789%
605 | P11161012 | 7/1/2015 | 2018-10-11 | 144.8% | 92333.018 | 92333.018 | -36196.36 | -39.2%
606 | P17225008 | 3/1/2019 | 2023-06-29 | 25.05% | 468620.05 | 468620.05 | -38683.57 | -8.255%
607 | P18090001 | 7/1/2018 | 2020-12-30 | 69.99% | 0 | 0 | -38797.5 | 0%
608 | P11161007 | 7/1/2017 | 2018-09-26 | 222.1% | 0 | 0 | -43824.46 | 0%
609 | A15702049 | 3/1/2018 | 2022-09-01 | 46.26% | 0 | 0 | -49059.73 | 0%
610 | P10115004 | 3/1/2017 | 2020-07-13 | 91.54% | 0 | 0 | -68366.27 | 0%
611 | A15702043 | 6/1/2017 | 2021-09-01 | 66.58% | 0 | 0 | -78514.67 | 0%
612 | A16905009 | 3/1/2017 | 2021-11-19 | 65.31% | 257154.082 | 257154.082 | -240312.57 | -93.45%
613 | A15702042 | 6/1/2017 | 2021-09-01 | 66.58% | 92501.93 | 92501.93 | -279752.8 | -302.4%
614 | A15702041 | 6/1/2017 | 2022-11-15 | 51.88% | 1033568.33 | 1033568.33 | -1348418.9 | -130.5%
615 | 000025076 | Charges Began Prior to Jan 2015 | 2020-04-30 | n.m. | 0 | 0 | -1925336.35 | 0%
616 | Other Budgeted Projects | Other | Other | Other | 13076423.94 | 13076423.94 | 0 | Other
617 | Total GLBU 180 (Transmission) |  |  |  | 95080929.298 | 95080929.298 | 55830467.212 | 58.72%
618 | Total Kentucky Power CWIP Additions |  |  |  | 201172450.864 | 192326747.633 | 175799005.875 | 91.41%
619
620 | X00000317 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -87148122.417 | Property Acctg
621 | X00000288 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -44198919.72 | Property Acctg
622 | X00000306 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -50038566.52 | Property Acctg
623 | Total Kentucky Power Transfers to 101/106 | [5 empty] | -181385608.657
624
625 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year April 2019 - March 2020 |  |  |  | 201172450.864 | 192326747.633 | -5586602.782
626
627
628 | Definitions:
629 | (C)* | Represents the month project expenditures were initially recorded to CWIP (Account 107).
630 | (H)* | Represents Total Cost (G) per Schedule D.
631 | (J)* | 2020-03-31
632 | Blanket | Repetitive and predictable project charged and closed continuously throughout the calendar year.
633 | Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
634 | Other | Other amounts reflected in budget; do not directly relate to a project with actual spend during the period.
635 | Preliminary | Requires assessments and pre-engineering activities for developing detail scopes and estimates. Costs are transferred to new a project once enough data is available for project creation.
636 | n.m. | Not meaningful.

## 12 Mos. Preceding Test Year
Schedule E (12 Months Preceding the Historical Test Year)
Kentucky Power Company
Case No. 2020-00174
Construction Projects for the 12 Months Preceding the Historical Test Year
April 2018 - March 2019
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time through March 31, 2019 (J)* | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures April 2018 through March 2019
(A) | (B) | (C)* | (D) | (E) = ((J)- (C)) / ((D) -(C)) | (F) | (G) | (H)* | (I) = (G)/(H)
1 | GLBU 110 (Distribution)
2 | TREEREL18 | 4/1/2014 | Blanket | Blanket | 0 | 5950480.57 | 5506330.7 | 108.1%
3 | 000007818 | Blanket | Blanket | Blanket | 4964157.085 | 5049581.047 | 5365524.58 | 94.11%
4 | EDN014680 | 2/1/2018 | Blanket | Blanket | 3550264.645 | 2911291.21 | 3892321.86 | 74.8%
5 | EON011326 | 2/1/2018 | Blanket | Blanket | 2384364.982 | 2913720.671 | 3652809.41 | 79.77%
6 | 000001818 | Blanket | Blanket | Blanket | 2171696.631 | 2332477.401 | 3560033.47 | 65.52%
7 | 000005234 | Blanket | Blanket | Blanket | 0 | 0 | 3341837.641 | 0%
8 | EDN014651 | 2/1/2018 | Blanket | Blanket | 2733382.128 | 2473697.281 | 2949029.16 | 83.88%
9 | EDN100033 | 2/1/2018 | Blanket | Blanket | 1296886.018 | 1356127.519 | 2563787.19 | 52.9%
10 | 000007599 | Blanket | Blanket | Blanket | 1719624.346 | 1682296.152 | 2415019.41 | 69.66%
11 | 000009160 | Blanket | Blanket | Blanket | 2637982.883 | 2579889.794 | 2367367.52 | 109%
12 | TREEREL19 | 4/1/2014 | Blanket | Blanket | 1847375 | 2211748.24 | 2211748.24 | 100%
13 | 000016528 | Blanket | Blanket | Blanket | 1410188.81 | 2160652.652 | 2011990.53 | 107.4%
14 | EDN014694 | 2/1/2018 | Blanket | Blanket | 288106.079 | 572395.655 | 1788121.22 | 32.01%
15 | P11161006 | 7/1/2017 | 2020-10-01 | 53.7% | 2598662.262 | -758580.984 | 1764470.99 | -42.99%
16 | EDN014720 | 2/1/2018 | Blanket | Blanket | 850738.942 | 1232264.113 | 1665097.58 | 74.01%
17 | DCTSUVLKY | 12/1/2019 | Blanket | Blanket | 0 | 276647.79 | 1485695.06 | 18.62%
18 | DR18K03B5 | 5/1/2018 | 2020-12-01 | 35.34% | 0 | 88197.81 | 1389839.19 | 6.346%
19 | DR15K02B0 | 5/1/2018 | 2020-12-01 | 35.34% | 0 | 1853487.361 | 1297926.44 | 142.8%
20 | A15702051 | 12/1/2017 | 2020-12-01 | 44.25% | 0 | 488204.78 | 1219790.58 | 40.02%
21 | ITCB11000 | 7/1/2017 | Blanket | Blanket | 0 | 0 | 1103629.2 | 0%
22 | A16928013 | 3/1/2017 | 2020-12-01 | 55.43% | 0 | 90846.85 | 1098915 | 8.267%
23 | 000025229 | 2017-12-07 | Blanket | Blanket | 0 | 0 | 1089516.79 | 0%
24 | 000004737 | Blanket | Blanket | Blanket | 170527 | 916879.772 | 994674.35 | 92.18%
25 | A16928014 | 11/1/2017 | 2020-12-01 | 45.74% | 0 | 100775.08 | 941880.05 | 10.7%
26 | B110KYSRR | 11/1/2016 | Blanket | Blanket | 989251.171 | 1091691.689 | 788689.78 | 138.4%
27 | DR15K02A0 | 4/1/2018 | 2020-12-01 | 37.33% | 0 | 1296646.383 | 737337.68 | 175.9%
28 | IT110BILL | 7/1/2017 | Blanket | Blanket | 0 | 0 | 732269.02 | 0%
29 | EDN100577 | 2/1/2018 | Blanket | Blanket | 1465050.91 | 1210003.64 | 682535.44 | 177.3%
30 | DR18K04B0 | 8/1/2018 | 2020-12-01 | 28.37% | 0 | 316595.35 | 664260.38 | 47.66%
31 | EDN012370 | 2/1/2018 | Blanket | Blanket | 2166304.138 | 1509019.438 | 630542.91 | 239.3%
32 | P11161002 | 7/1/2017 | 2020-10-01 | 53.7% | 230082.398 | 288029.232 | 617102.76 | 46.67%
33 | KY5YCYCLE | 1/1/2019 | Blanket | Blanket | 937694 | 610067.82 | 610067.82 | 100%
34 | DMS19KK01 | 2/1/2019 | 2020-10-01 | 9.539% | 0 | 606305.52 | 606348.09 | 99.99%
35 | IT1101421 | 3/1/2016 | Blanket | Blanket | 0 | 0 | 564378.28 | 0%
36 | EDN011333 | 2/1/2018 | Blanket | Blanket | 867153.451 | 728171.525 | 563059.75 | 129.3%
37 | P18025001 | 2/1/2018 | 2024-06-01 | 18.3% | 0 | 444780.18 | 550263.85 | 80.83%
38 | A15710030 | 3/1/2018 | 2021-12-01 | 28.81% | 0 | 69162.63 | 527421.94 | 13.11%
39 | 000025522 | 2018-01-01 | 2020-12-01 | 42.63% | 0 | 117821.3 | 465787.34 | 25.3%
40 | P11161021 | 7/1/2015 | 2020-10-01 | 71.34% | 0 | -6050.3 | 465336.87 | -1.3%
41 | EDN015042 | 2/1/2018 | Blanket | Blanket | 275210.75 | 469768.64 | 386011.98 | 121.7%
42 | DMS18KK03 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 578.75 | 277562.45 | 0.2085%
43 | A17750006 | 7/1/2018 | 2020-10-01 | 33.17% | 0 | 39734.47 | 271092.03 | 14.66%
44 | 000025514 | 2018-01-01 | 2021-06-01 | 36.41% | 0 | 55876.95 | 256479.13 | 21.79%
45 | 000025595 | 2018-02-01 | 2021-12-01 | 30.24% | 0 | 1.65 | 234228.37 | 0.0007044%
46 | P16113007 | 12/1/2016 | 2020-10-01 | 60.71% | 12992 | 65093.808 | 209474.54 | 31.07%
47 | KYCR012DL | 3/1/2019 | 2020-12-01 | 4.68% | 0 | 31335.99 | 207599.26 | 15.09%
48 | EDN014658 | 2/1/2018 | Blanket | Blanket | 73225.017 | 97136.012 | 203674.61 | 47.69%
49 | 000002241 | Blanket | Blanket | Blanket | 7805.896 | 24011.559 | 198822.69 | 12.08%
50 | DMS18KK05 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 1778.53 | 192826.58 | 0.9223%
51 | 000025524 | 2018-01-01 | 2020-10-01 | 45.22% | 0 | 64173.79 | 164838.86 | 38.93%
52 | P11161003 | 7/1/2017 | 2020-10-01 | 53.7% | 127523.38 | 130947.893 | 161199.53 | 81.23%
53 | DX16K02A0 | 2/1/2017 | 2021-06-01 | 49.84% | 0 | 86845.53 | 135575.75 | 64.06%
54 | DMS18KK08 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 16714.44 | 131337.9 | 12.73%
55 | DMS18KK02 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 0 | 127617.14 | 0%
56 | EDN100044 | 2/1/2018 | Blanket | Blanket | 21819 | 21813.82 | 123223.91 | 17.7%
57 | DX17K01B0 | 2/1/2018 | 2021-12-01 | 30.24% | 0 | 4116.58 | 120424.71 | 3.418%
58 | 000025570 | 2018-02-01 | 2021-12-01 | 30.24% | 0 | 0 | 114855.51 | 0%
59 | DX17K02B0 | 2/1/2018 | 2021-12-01 | 30.24% | 0 | 7183.37 | 105463.85 | 6.811%
60 | P18025002 | 2/1/2018 | 2020-10-01 | 43.47% | 0 | 1402.8 | 103082.1 | 1.361%
61 | 000024645 | 2017-01-01 | Blanket | Blanket | 6593318.537 | 2856546.925 | 103072.14 | 2771%
62 | DP14K02B0 | 3/1/2018 | 2021-10-01 | 30.15% | 0 | 21046.19 | 86730.53 | 24.27%
63 | DR18K02B0 | 9/1/2018 | 2020-10-01 | 27.73% | 0 | 53992.28 | 80071.54 | 67.43%
64 | A13002013 | Charges Began Prior to Jan 2015 | 2021-12-01 | n.m. | 0 | 17583.99 | 78709.12 | 22.34%
65 | 000007615 | Blanket | Blanket | Blanket | 139088.038 | 99376.922 | 78321.7 | 126.9%
66 | 000007558 | Blanket | Blanket | Blanket | 924214.115 | 757071.945 | 73979.97 | 1023%
67 | P17084024 | 10/1/2017 | 2020-10-01 | 49.82% | 0 | 1539.07 | 73324.39 | 2.099%
68 | DR18K02B3 | 10/1/2018 | 2020-10-01 | 24.76% | 0 | 49821.96 | 73278.67 | 67.99%
69 | A16928012 | 3/1/2017 | 2020-12-01 | 55.43% | 0 | -221156.06 | 71719.09 | -308.4%
70 | A15710010 | 9/1/2016 | 2021-06-01 | 54.27% | 0 | 1170.26 | 71699.76 | 1.632%
71 | A13002014 | Charges Began Prior to Jan 2015 | 2020-12-01 | n.m. | 0 | 16805.96 | 71019.6 | 23.66%
72 | A16928010 | 3/1/2017 | 2020-12-01 | 55.43% | 0 | 2672.51 | 65658.1 | 4.07%
73 | EDN103175 | 2/1/2018 | Blanket | Blanket | -0.007 | 10789.802 | 64944.76 | 16.61%
74 | A15710011 | 9/1/2016 | 2021-06-01 | 54.27% | 0 | 511.61 | 63515.91 | 0.8055%
75 | DMS18KK04 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 0 | 62537.37 | 0%
76 | A15710017 | 1/1/2017 | 2021-12-01 | 45.63% | 0 | 4883.6 | 49232.35 | 9.919%
77 | 000025516 | 2018-01-01 | 2021-06-01 | 36.41% | 0 | 0 | 47547.76 | 0%
78 | DR18K02A0 | 3/1/2019 | 2020-12-01 | 4.68% | 0 | 40759.52 | 40830.4 | 99.83%
79 | A15710012 | 9/1/2016 | 2021-06-01 | 54.27% | 0 | 3490.64 | 40062.03 | 8.713%
80 | A15710040 | 3/1/2018 | 2021-06-01 | 33.25% | 9561 | 1890.43 | 35589.14 | 5.312%
81 | DMS18KK09 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | -16293.02 | 35319.41 | -46.13%
82 | 000025521 | 2018-01-01 | 2021-12-01 | 31.75% | 0 | 0 | 33931.76 | 0%
83 | DMS18KK06 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 1494.35 | 29209.28 | 5.116%
84 | A15710026 | 2/1/2018 | 2021-06-01 | 34.79% | 15466.555 | 36734.699 | 29190.84 | 125.8%
85 | P17076002 | 9/1/2017 | 2024-12-01 | 21.75% | 3203 | 6555.77 | 27299.91 | 24.01%
86 | A15710039 | 11/1/2018 | 2021-06-01 | 15.91% | 9561 | 3687.86 | 25453.86 | 14.49%
87 | A17212002 | 7/1/2018 | 2020-10-01 | 33.17% | 52301 | 631.2 | 24811.74 | 2.544%
88 | P17225011 | 2/1/2018 | 2021-06-01 | 34.79% | 0 | 3672.41 | 22739.67 | 16.15%
89 | 000025820 | 2018-10-01 | 2020-11-01 | 23.75% | 0 | 0 | 21561.5 | 0%
90 | A15710013 | 9/1/2016 | 2021-06-01 | 54.27% | 0 | 2902.8 | 21467.78 | 13.52%
91 | P17084001 | 11/1/2017 | 2020-10-01 | 48.36% | 47296 | 1534.4 | 20728.04 | 7.403%
92 | DMS18KK01 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 6.68 | 19813.5 | 0.03371%
93 | A15710021 | 1/1/2017 | 2021-12-01 | 45.63% | 0 | 904.19 | 19005.78 | 4.757%
94 | A15710038 | 3/1/2018 | 2021-06-01 | 33.25% | 5978 | 5306.6 | 16058.05 | 33.05%
95 | A13212036 | Charges Began Prior to Jan 2015 | 2020-12-01 | n.m. | 0 | 3012.82 | 15055 | 20.01%
96 | EDN014701 | 2/1/2018 | Blanket | Blanket | 7294 | 9014.82 | 14228.35 | 63.36%
97 | A15710005 | 9/1/2016 | 2021-06-01 | 54.27% | 0 | 9301.14 | 14222.16 | 65.4%
98 | A15710019 | 1/1/2017 | 2021-06-01 | 50.81% | 0 | 8945.12 | 12759.29 | 70.11%
99 | KYCR31109 | 3/1/2019 | 2021-06-01 | 3.645% | 0 | 0.42 | 12749.7 | 0.003294%
100 | 000014717 | Blanket | Blanket | Blanket | 140201.797 | 100533.714 | 11750.41 | 855.6%
101 | ITCW11004 | 4/1/2017 | 2022-12-01 | 35.22% | 0 | 0 | 11691.75 | 0%
102 | EDN014687 | 2/1/2018 | Blanket | Blanket | 12590.299 | 1077.11 | 11482.7 | 9.38%
103 | A15710016 | 9/1/2016 | 2021-06-01 | 54.27% | 0 | 631.41 | 11216.42 | 5.629%
104 | P12057001 | 8/1/2017 | 2021-12-01 | 38.34% | 0.465 | -0.173 | 11007.7 | -0.001572%
105 | P17084005 | 11/1/2017 | 2024-12-01 | 19.91% | 0 | 1977.82 | 10854.49 | 18.22%
106 | 000007577 | Blanket | Blanket | Blanket | 11614 | 114.31 | 10476.61 | 1.091%
107 | KYCR34119 | 5/1/2016 | 2022-12-01 | 44.24% | 0 | 7.61 | 9895.13 | 0.07691%
108 | KYCR30106 | 3/1/2019 | 2021-12-01 | 2.982% | 0 | 0 | 9686.9 | 0%
109 | A15710020 | 1/1/2017 | 2021-12-01 | 45.63% | 0 | 954.62 | 8964.29 | 10.65%
110 | KYCR30009 | 3/1/2019 | 2021-12-01 | 2.982% | 0 | 0 | 8286.49 | 0%
111 | P18025003 | 2/1/2018 | 2020-10-01 | 43.47% | 0 | 25876.23 | 7002.52 | 369.5%
112 | P17084009 | 9/1/2017 | 2024-12-01 | 21.75% | 284212 | 1509.9 | 6722.11 | 22.46%
113 | A20212001 | 10/1/2018 | 2021-12-01 | 15.64% | 0 | 138.07 | 6703.91 | 2.06%
114 | P17076003 | 9/1/2017 | 2021-12-01 | 37.11% | 2872 | 1017.51 | 6011.4 | 16.93%
115 | P17225006 | 3/1/2019 | 2025-12-01 | 1.216% | 865666 | 315.11 | 5720.05 | 5.509%
116 | P17076011 | 4/1/2018 | 2024-06-01 | 16.16% | 0 | 921.7 | 5425.9 | 16.99%
117 | P17084014 | 9/1/2017 | 2024-12-01 | 21.75% | 0 | 562.41 | 5210.3 | 10.79%
118 | A13212029 | Charges Began Prior to Jan 2015 | 2021-12-01 | n.m. | 0 | 0 | 4088.2 | 0%
119 | A15702009 | 6/1/2017 | 2021-12-01 | 40.63% | 0 | 0 | 3886.7 | 0%
120 | EDN101114 | 2/1/2018 | Blanket | Blanket | 10670 | -1232.27 | 3504.78 | -35.16%
121 | KYCAPTOOL | 3/1/2019 | Blanket | Blanket | 0 | 3452.98 | 3452.98 | 100%
122 | KYCR33111 | 5/1/2016 | 2021-12-01 | 52.16% | 0 | 0 | 3419.27 | 0%
123 | EDN014673 | 2/1/2018 | Blanket | Blanket | 0 | 0 | 3354.58 | 0%
124 | P14030009 | 11/1/2016 | 2021-06-01 | 52.6% | 1895 | 1418.32 | 2586.92 | 54.83%
125 | KYCR31167 | 5/1/2016 | 2021-12-01 | 52.16% | 0 | 6.55 | 2399.51 | 0.273%
126 | P17084025 | 9/1/2017 | 2024-12-01 | 21.75% | 0 | 436.38 | 1977.96 | 22.06%
127 | 000025473 | 2017-11-01 | 2025-12-01 | 17.45% | 0 | 0 | 1491.39 | 0%
128 | A15710004 | 5/1/2019 | 2021-06-01 | -4.068% | 0 | 0 | 1246.84 | 0%
129 | P17083016 | 3/1/2019 | 2024-12-01 | 1.427% | 0 | 948.47 | 948.47 | 100%
130 | A15710002 | 5/1/2019 | 2021-06-01 | -4.068% | 0 | 0 | 715.82 | 0%
131 | TA1807312 | 4/1/2014 | Blanket | Blanket | 0 | 601.88 | 601.88 | 100%
132 | P18025004 | 2/1/2018 | 2020-10-01 | 43.47% | 0 | 11.13 | 429.97 | 2.589%
133 | B110KYCSV | 6/1/2019 | 2020-10-01 | -12.7% | 0 | 0 | 413.44 | 0%
134 | DP15K05L0 | 12/1/2015 | 2020-10-01 | 68.86% | 0 | 0 | 347.15 | 0%
135 | P17083025 | 3/1/2019 | 2020-12-01 | 4.68% | 0 | 319.24 | 319.24 | 100%
136 | A15702050 | 3/1/2018 | 2020-10-01 | 41.8% | 0 | 0 | 266.17 | 0%
137 | A15710060 | 2/1/2019 | 2021-06-01 | 6.816% | 0 | 136 | 136 | 100%
138 | P17225007 | 3/1/2019 | 2024-06-01 | 1.563% | 496195 | 22.98 | 56.84 | 40.43%
139 | DR19K02A0 | 3/1/2019 | 2020-12-01 | 4.68% | 0 | 36.01 | 36.01 | 100%
140 | A13212028 | Charges Began Prior to Jan 2015 | 2021-12-01 | n.m. | 0 | 0 | 0.08 | 0%
141 | ETN000110 | 2/1/2018 | Blanket | Blanket | -0.001 | -0.004 | 0 | n.m.
142 | 000008154 | Blanket | Blanket | Blanket | 2014990.614 | 1352902.244 | 0 | n.m.
143 | A18702002 | 10/1/2017 | 2020-10-01 | 49.82% | 0 | 0 | 0 | n.m.
144 | DMS18KK07 | 12/1/2019 | 2020-10-01 | -80.33% | 0 | 0 | -4.3854e-15 | 0%
145 | A13212004 | Charges Began Prior to Jan 2015 | 2021-06-01 | n.m. | 0 | 0 | -27.89 | 0%
146 | SI110KYRE | 8/1/2019 | Blanket | Blanket | 0 | 870.44 | -2711.67 | -32.1%
147 | P11063003 | 7/1/2017 | 2021-12-01 | 39.53% | 0 | 2189.15 | -3712.51 | -58.97%
148 | A15702008 | 6/1/2017 | 2020-12-01 | 52.23% | 0 | 0 | -61936.85 | 0%
149 | P12124003 | 8/1/2017 | 2021-12-01 | 38.34% | 0 | 16935.77 | -105774.35 | -16.01%
150 | Other Budgeted Projects | Other | Other | Other | 16496660.5 | 8429267.786 | 0 | Other
151 | Total GLBU 110 (Distribution) |  |  |  | 63942917.834 | 59624009.973 | 70375224.931 | 84.72%
152 | GLBU 117 (Generation)
153 | 000022392 | 2016-09-01 | 2019-12-01 | 79.34% | 412548.78 | 412548.78 | 4699750.18 | 8.778%
154 | 000005237 | Blanket | Blanket | Blanket | 2909.928 | 2909.928 | 3544452.04 | 0.0821%
155 | BS0000038 | 2018-01-01 | 2018-06-01 | 300.7% | 1516064.9 | 1516064.9 | 3200981.7 | 47.36%
156 | ML1EC1302 | 2018-05-01 | 2019-12-01 | 57.69% | 912507.885 | 912507.885 | 1720491.71 | 53.04%
157 | IT1171421 | 2016-03-01 | 2019-12-01 | 82.12% | 0 | 0 | 1410538.915 | 0%
158 | BSPPB0013 | Blanket | Blanket | Blanket | 211845.156 | 211845.156 | 1047556.98 | 20.22%
159 | 000022308 | 2018-11-01 | 2019-06-01 | 70.75% | 3953651.813 | 3953651.813 | 970311.98 | 407.5%
160 | NRCCPKPCO | 2016-09-01 | 2018-06-01 | 147.5% | 3017697.026 | 3017697.026 | 965094.1 | 312.7%
161 | ML1E18C05 | 2017-09-01 | 2018-07-01 | 190.1% | 2492798.444 | 2492798.444 | 954197.1 | 261.2%
162 | ML119SC02 | 2018-08-01 | 2019-06-01 | 79.61% | 1620588.74 | 1620588.74 | 780937.55 | 207.5%
163 | IT117BILL | 2017-07-01 | 2027-06-01 | 17.61% | 0 | 0 | 713469.72 | 0%
164 | 000021737 | 2018-01-01 | 2020-04-01 | 55.3% | 2224954.559 | 2224954.559 | 702942.19 | 316.5%
165 | ML018MP05 | 2018-08-01 | 2019-03-01 | 114.2% | 0 | 0 | 606466.59 | 0%
166 | ML018VP01 | 2018-01-01 | 2020-03-01 | 57.47% | 0 | 0 | 568923.74 | 0%
167 | ML018NP01 | 2018-03-01 | Blanket | Blanket | 39365.307 | 39365.307 | 537143.6 | 7.329%
168 | BSPPBOUT1 | Blanket | Blanket | Blanket | -2061352.777 | -2061352.777 | 478028.15 | -431.2%
169 | BSPPBS347 | 2018-11-01 | 2019-03-01 | 125% | 365000 | 365000 | 386770.55 | 94.37%
170 | ML018VP04 | 2018-07-01 | 2019-08-01 | 68.94% | 0 | 0 | 364682.72 | 0%
171 | BS2DCOM20 | 2017-11-01 | 2018-05-01 | 284.5% | 223824.752 | 223824.752 | 361991.39 | 61.83%
172 | ML1SC1810 | 2018-12-01 | 2019-05-01 | 79.47% | 472336.665 | 472336.665 | 329087.4 | 143.5%
173 | BSPPBS341 | 2018-04-01 | 2019-03-01 | 109% | 0 | 0 | 295897.46 | 0%
174 | ML018NP12 | 2018-09-01 | Blanket | Blanket | 0 | 0 | 249130.06 | 0%
175 | ML018MP03 | 2018-01-01 | 2020-02-01 | 59.66% | 0 | 0 | 244490.72 | 0%
176 | MLP18EP04 | 2018-02-01 | Blanket | Blanket | 25934 | 25934 | 244025.16 | 10.63%
177 | BSPPB0002 | Blanket | Blanket | Blanket | -77272.576 | -77272.576 | 236585.27 | -32.66%
178 | ML2VC1601 | 2017-07-01 | 2017-12-01 | 417% | -27600.342 | -27600.342 | 236415.85 | -11.67%
179 | ML218EP05 | 2018-03-01 | 2019-07-01 | 81.11% | 0 | 0 | 221080.48 | 0%
180 | ML018MP06 | 2018-09-01 | Blanket | Blanket | 0 | 0 | 209978.31 | 0%
181 | ML118SP22 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 199353.97 | 0%
182 | ML1VC1601 | 2016-12-01 | 2017-12-01 | 232.9% | -1356255.727 | -1356255.727 | 193188.3 | -702%
183 | ML018SP01 | 2018-03-01 | Blanket | Blanket | 0 | 0 | 176150.04 | 0%
184 | MLP18EP02 | 2018-07-01 | Blanket | Blanket | 8588.67 | 8588.67 | 174757.11 | 4.915%
185 | ML2E18C05 | 2017-12-01 | 2018-05-01 | 321.2% | -628470.424 | -628470.424 | 166058.26 | -378.5%
186 | ML118VP07 | 2018-04-01 | 2018-06-01 | 596.7% | 0 | 0 | 149614.49 | 0%
187 | BSPPBS338 | 2018-05-01 | 2018-09-01 | 271.5% | 0 | 0 | 146250.98 | 0%
188 | BSPPBS342 | 2018-04-01 | 2018-08-01 | 298.4% | 0 | 0 | 144648.43 | 0%
189 | ML218SP10 | 2018-01-01 | Blanket | Blanket | 254003.612 | 254003.612 | 144407.67 | 175.9%
190 | MLP18EP07 | 2018-07-01 | 2019-08-01 | 68.94% | 0 | 0 | 139220.71 | 0%
191 | ML217SP08 | 2017-12-01 | 2018-09-01 | 177% | -537513.452 | -537513.452 | 126296.89 | -425.6%
192 | ML018NP10 | 2018-10-01 | 2019-03-01 | 119.9% | 0 | 0 | 126022.97 | 0%
193 | ML018EP14 | 2018-09-01 | 2020-03-01 | 38.57% | 0 | 0 | 120002.5 | 0%
194 | ML018NP04 | 2018-07-01 | 2019-06-01 | 81.49% | 0 | 0 | 114171.01 | 0%
195 | BSPPB0016 | Charges Began Prior to Jan 2015 | 2018-07-01 | n.m. | 0 | 0 | 113389.93 | 0%
196 | ML119EP01 | 2019-02-01 | 2019-11-01 | 21.25% | 151738.476 | 151738.476 | 111816.88 | 135.7%
197 | ML018EP04 | 2018-02-01 | 2019-03-01 | 107.6% | 0 | 0 | 110780.04 | 0%
198 | ML018EP16 | 2018-10-01 | 2019-10-01 | 49.59% | 0 | 0 | 101807.4 | 0%
199 | ML018VP02 | 2018-10-01 | 2019-06-01 | 74.49% | 0 | 0 | 100402.01 | 0%
200 | ML118SP01 | 2018-03-01 | 2019-07-01 | 81.11% | 0 | 0 | 99078.48 | 0%
201 | ML217SP05 | 2017-12-01 | 2018-09-01 | 177% | -537513.452 | -537513.452 | 93781.3 | -573.2%
202 | ML217SP06 | 2017-12-01 | 2018-09-01 | 177% | -537513.452 | -537513.452 | 91330.1 | -588.5%
203 | ML217SP09 | 2017-12-01 | 2018-09-01 | 177% | -537513.452 | -537513.452 | 86929.36 | -618.3%
204 | ML218EP07 | 2018-09-01 | 2019-03-01 | 116.6% | 0 | 0 | 86512.33 | 0%
205 | ML018EP08 | 2018-02-01 | 2019-07-01 | 82.14% | 0 | 0 | 84260.51 | 0%
206 | ML218SP20 | 2018-04-01 | 2020-06-01 | 45.96% | 27027.091 | 27027.091 | 84136.63 | 32.12%
207 | ML018MP01 | 2017-09-01 | 2019-01-01 | 118.3% | -1985.24 | -1985.24 | 73424.49 | -2.704%
208 | ML118SP19 | 2018-11-01 | 2019-01-01 | 245.9% | 0 | 0 | 66619.3 | 0%
209 | ML217SP07 | 2017-12-01 | 2018-09-01 | 177% | -537513.452 | -537513.452 | 66042.59 | -813.9%
210 | ML018NP07 | 2018-08-01 | 2020-03-01 | 41.87% | 0 | 0 | 64245.03 | 0%
211 | ML018NP08 | 2018-08-01 | 2020-01-01 | 46.72% | 0 | 0 | 61966.83 | 0%
212 | MLP18EP08 | 2018-08-01 | 2019-11-01 | 52.95% | 0 | 0 | 61373.76 | 0%
213 | MLP18EP03 | 2018-01-01 | Blanket | Blanket | 17177.336 | 17177.336 | 61240.98 | 28.05%
214 | ML018EP06 | 2018-08-01 | 2018-10-01 | 396.7% | 0 | 0 | 59009.28 | 0%
215 | ML018NP11 | 2018-09-01 | 2019-04-01 | 99.53% | 0 | 0 | 58476.04 | 0%
216 | MLP17SP01 | 2017-05-01 | 2019-08-01 | 85.04% | 0 | 0 | 58210.01 | 0%
217 | ML218SP07 | 2017-12-01 | 2018-09-01 | 177% | -147029.705 | -147029.705 | 56300.25 | -261.2%
218 | ML018EP11 | 2018-10-01 | 2019-11-01 | 45.71% | 0 | 0 | 53640.14 | 0%
219 | ML018EP01 | 2018-02-01 | Blanket | Blanket | 14990.511 | 14990.511 | 49305.8 | 30.4%
220 | MLP18EP09 | 2018-09-01 | 2019-06-01 | 77.29% | 0 | 0 | 49037.27 | 0%
221 | ML216SP12 | 2016-12-01 | 2018-09-01 | 133% | 0 | 0 | 47819.61 | 0%
222 | ML218SP06 | 2017-12-01 | 2018-07-01 | 228.8% | -147029.705 | -147029.705 | 47181.97 | -311.6%
223 | ML117VP06 | 2018-03-01 | 2019-06-01 | 86.43% | 0 | 0 | 47027.64 | 0%
224 | ML117EP04 | 2019-02-01 | 2019-12-01 | 19.14% | 0 | 0 | 45157.86 | 0%
225 | ML018SP03 | 2018-04-01 | 2019-04-01 | 99.73% | 0 | 0 | 45109.06 | 0%
226 | MLP18EP01 | 2018-01-01 | 2019-06-01 | 87.98% | 0 | 0 | 41767.32 | 0%
227 | ML018EP17 | 2018-10-01 | Blanket | Blanket | 0 | 0 | 41414.61 | 0%
228 | ML0M18C01 | 2017-09-01 | 2018-04-01 | 271.7% | -423831.941 | -423831.941 | 38423.09 | -1103%
229 | ML218SP05 | 2017-12-01 | 2018-09-01 | 177% | -147029.705 | -147029.705 | 38290.11 | -384%
230 | ARCFLA117 | Blanket | Blanket | Blanket | 27738.36 | 27738.36 | 37096.12 | 74.77%
231 | MLP18EP06 | 2018-01-01 | Blanket | Blanket | 17177.336 | 17177.336 | 36453.28 | 47.12%
232 | ML018EP12 | 2018-09-01 | 2019-02-01 | 137.9% | 0 | 0 | 35684.06 | 0%
233 | ML015VP01 | 2015-06-01 | Blanket | Blanket | 0 | 0 | 31952.51 | 0%
234 | 000025231 | 2018-03-01 | Blanket | Blanket | 0 | 0 | 29486.45 | 0%
235 | ML119EP04 | 2019-01-01 | 2019-11-01 | 29.28% | 0 | 0 | 29033.82 | 0%
236 | ML018NP05 | 2018-09-01 | 2019-02-01 | 137.9% | 0 | 0 | 26681.55 | 0%
237 | ML018EP10 | 2018-10-01 | 2019-03-01 | 119.9% | 0 | 0 | 26114.77 | 0%
238 | ML117EP10 | 2017-08-01 | 2019-01-01 | 117.2% | 0 | 0 | 26045.77 | 0%
239 | MLP19EP02 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 26023.04 | 0%
240 | ML119EP05 | 2019-03-01 | 2019-07-01 | 24.59% | 0 | 0 | 24837.07 | 0%
241 | ML118EP10 | 2018-09-01 | 2019-11-01 | 49.53% | 0 | 0 | 24585.03 | 0%
242 | ML118EP12 | 2018-01-01 | Blanket | Blanket | 0 | 0 | 24423.84 | 0%
243 | ML018EP15 | 2018-09-01 | 2019-03-01 | 116.6% | 0 | 0 | 23999.09 | 0%
244 | ML218EP13 | 2018-02-01 | 2020-01-01 | 60.52% | 0 | 0 | 23666.8 | 0%
245 | ML016VP08 | 2016-12-01 | 2019-01-01 | 111.7% | 0 | 0 | 23596.85 | 0%
246 | ML218SP17 | 2018-04-01 | 2018-05-01 | 1213% | 0 | 0 | 22828.62 | 0%
247 | ML018EP07 | 2018-11-01 | 2019-01-01 | 245.9% | 0 | 0 | 21808.61 | 0%
248 | ML118EP04 | 2019-02-01 | 2020-01-01 | 17.37% | 95251.345 | 95251.345 | 21273.18 | 447.8%
249 | ML119SP10 | 2019-03-01 | 2019-07-01 | 24.59% | 0 | 0 | 21234.75 | 0%
250 | ML117EP11 | 2017-12-01 | 2018-05-01 | 321.2% | 0 | 0 | 21182.59 | 0%
251 | ML218SP11 | 2018-01-01 | 2018-07-01 | 250.8% | 0 | 0 | 20079.96 | 0%
252 | ML119EP03 | 2018-12-01 | 2019-12-01 | 32.88% | 0 | 0 | 20072.33 | 0%
253 | ML218SP16 | 2018-01-01 | 2018-06-01 | 300.7% | 0 | 0 | 19884.8 | 0%
254 | ML218EP04 | 2018-03-01 | 2018-06-01 | 429.3% | 0 | 0 | 19298.2 | 0%
255 | ML118EP09 | 2018-03-01 | 2018-05-01 | 647.5% | 0 | 0 | 19069.13 | 0%
256 | ML118EP01 | 2019-02-01 | 2019-11-01 | 21.25% | -22791.833 | -22791.833 | 17742.28 | -128.5%
257 | ML016VP11 | 2016-11-01 | 2019-08-01 | 87.74% | 0 | 0 | 17519.74 | 0%
258 | ML018EP13 | 2018-09-01 | 2019-03-01 | 116.6% | 0 | 0 | 17394.18 | 0%
259 | ML218SP09 | 2018-07-01 | Blanket | Blanket | 21667.065 | 21667.065 | 16199.77 | 133.7%
260 | ML219SP03 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 15931.3 | 0%
261 | ML018MP04 | 2018-07-01 | 2019-04-01 | 99.64% | 0 | 0 | 14718.15 | 0%
262 | MLP17EP05 | 2017-02-01 | 2019-01-01 | 112.7% | 10141.304 | 10141.304 | 14366.25 | 70.59%
263 | ML018MP09 | 2018-12-01 | 2019-07-01 | 56.6% | 0 | 0 | 14343.03 | 0%
264 | ML218SP12 | 2017-12-01 | 2018-06-01 | 266.5% | 0 | 0 | 14037.57 | 0%
265 | ML218SP08 | 2017-10-01 | 2018-05-01 | 257.5% | 106254.725 | 106254.725 | 13338.1 | 796.6%
266 | ML218SP15 | 2018-01-01 | 2018-05-01 | 378.3% | 0 | 0 | 13238.98 | 0%
267 | BSPPB0011 | Blanket | Blanket | Blanket | 0 | 0 | 12901.66 | 0%
268 | ML119SP07 | 2019-01-01 | 2020-01-01 | 24.38% | 0 | 0 | 12893.17 | 0%
269 | ML018EP02 | 2018-07-01 | 2019-10-01 | 59.74% | 0 | 0 | 12592.53 | 0%
270 | ML218SP13 | 2017-12-01 | 2018-06-01 | 266.5% | 0 | 0 | 12203.3 | 0%
271 | BSPPB0007 | Blanket | Blanket | Blanket | 0 | 0 | 11911.9 | 0%
272 | ML219EP01 | 2018-12-01 | 2020-01-01 | 30.3% | 0 | 0 | 11623.82 | 0%
273 | ML017NP01 | 2017-01-01 | 2019-11-01 | 79.21% | 58099.342 | 58099.342 | 10136.19 | 573.2%
274 | ML218SP27 | 2018-04-01 | 2018-06-01 | 596.7% | 0 | 0 | 9696.72 | 0%
275 | ML018MP08 | 2018-09-01 | 2019-01-01 | 173% | 0 | 0 | 8114 | 0%
276 | ML018EP18 | 2018-11-01 | 2019-01-01 | 245.9% | 0 | 0 | 7780.15 | 0%
277 | MLP17EP06 | 2017-01-01 | 2019-01-01 | 112.2% | 25346.749 | 25346.749 | 7774.17 | 326%
278 | ML218SP26 | 2018-12-01 | 2019-03-01 | 133.3% | 0 | 0 | 7590.33 | 0%
279 | ML019VP01 | 2019-01-01 | Blanket | Blanket | 51532.015 | 51532.015 | 7486.56 | 688.3%
280 | ML118SP07 | 2018-11-01 | Blanket | Blanket | 21667.065 | 21667.065 | 7444.11 | 291.1%
281 | ML118SP20 | 2018-04-01 | 2018-07-01 | 400% | 0 | 0 | 7335.84 | 0%
282 | ML019EP02 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 6897.86 | 0%
283 | ITCB11700 | Charges Began Prior to Jan 2015 | 2019-03-01 | n.m. | 0 | 0 | 6895.32 | 0%
284 | ML217EP02 | 2017-11-01 | 2018-08-01 | 188.6% | 0 | 0 | 6750.02 | 0%
285 | ML017EP02 | 2016-10-01 | 2019-08-01 | 88.1% | 0 | 0 | 5540.95 | 0%
286 | ML018MP11 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 5521.85 | 0%
287 | ML118EP08 | 2017-12-01 | 2018-06-01 | 266.5% | 0 | 0 | 5234.61 | 0%
288 | ML119SP09 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 5230.7 | 0%
289 | ML118SP21 | 2018-04-01 | 2018-10-01 | 198.9% | 0 | 0 | 5090.81 | 0%
290 | ML1NP1911 | 2019-03-01 | 2020-01-01 | 9.804% | 0 | 0 | 4964.77 | 0%
291 | ML217VP04 | 2017-12-01 | 2018-06-01 | 266.5% | 0 | 0 | 4928.31 | 0%
292 | ML019NP01 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 4845.55 | 0%
293 | ML118SP18 | 2018-03-01 | 2018-07-01 | 323.8% | 0 | 0 | 4768.46 | 0%
294 | ITCB11701 | 2017-11-01 | 2019-03-01 | 106.2% | 0 | 0 | 4149.33 | 0%
295 | ML218SP18 | 2018-04-01 | 2018-05-01 | 1213% | 0 | 0 | 4075.1 | 0%
296 | ML118VP06 | 2018-04-01 | 2018-06-01 | 596.7% | 0 | 0 | 4049.74 | 0%
297 | ML219EP13 | 2019-01-01 | Blanket | Blanket | 0 | 0 | 3853.83 | 0%
298 | ML0VP1702 | 2017-12-01 | 2018-07-01 | 228.8% | 0 | 0 | 3817.32 | 0%
299 | ML018VP06 | 2018-12-01 | 2020-03-01 | 26.32% | 0 | 0 | 3700.24 | 0%
300 | ML218SP03 | 2017-12-01 | 2018-06-01 | 266.5% | 53975.787 | 53975.787 | 3491.2 | 1546%
301 | BSPPB0003 | Blanket | Blanket | Blanket | 186758.617 | 186758.617 | 3447.79 | 5417%
302 | ML018MP10 | 2018-11-01 | 2019-04-01 | 99.34% | 0 | 0 | 3368.96 | 0%
303 | MLP19EP04 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 3307.93 | 0%
304 | ML218EP03 | 2018-03-01 | 2019-01-01 | 129.1% | 0 | 0 | 3298.14 | 0%
305 | MLP19EP06 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 3130.75 | 0%
306 | MLP19EP01 | 2019-01-01 | Blanket | Blanket | 0 | 0 | 3126.47 | 0%
307 | ML118SP11 | 2018-10-01 | 2019-04-01 | 99.45% | 0 | 0 | 2298.01 | 0%
308 | ML017MP06 | 2017-03-01 | 2018-04-01 | 191.9% | 0 | 0 | 2180.58 | 0%
309 | ML016NP06 | 2016-01-01 | 2019-03-01 | 102.6% | 0 | 0 | 2047.58 | 0%
310 | ML119SP12 | 2019-01-01 | 2019-11-01 | 29.28% | 0 | 0 | 1852.29 | 0%
311 | ML119EP12 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 1840.18 | 0%
312 | ML019EP09 | 2019-03-01 | 2020-01-01 | 9.804% | 0 | 0 | 1804.63 | 0%
313 | MLP19EP03 | 2019-02-01 | Blanket | Blanket | 0 | 0 | 1791.77 | 0%
314 | MLP17EP04 | 2016-10-01 | 2019-01-01 | 110.8% | -245069.32 | -245069.32 | 1353.55 | -18106%
315 | ML017MP01 | 2017-10-01 | 2018-05-01 | 257.5% | 0 | 0 | 1280.68 | 0%
316 | ML017MP05 | 2017-09-01 | 2018-07-01 | 190.1% | 0 | 0 | 1251.66 | 0%
317 | ML218EP06 | 2018-03-01 | 2018-06-01 | 429.3% | 0 | 0 | 847.33 | 0%
318 | ML018NP03 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 775.11 | 0%
319 | ML218SP02 | 2017-12-01 | 2018-05-01 | 321.2% | -70388.666 | -70388.666 | 516.5 | -13628%
320 | ML217VP05 | 2017-05-01 | 2018-07-01 | 164.1% | 0 | 0 | 511.04 | 0%
321 | ML017VP03 | 2017-08-01 | 2019-07-01 | 86.84% | 0 | 0 | 486.36 | 0%
322 | ML118SP05 | 2017-12-01 | 2018-05-01 | 321.2% | 0 | 0 | 443.32 | 0%
323 | ML019VP02 | 2018-11-01 | 2019-11-01 | 41.1% | 0 | 0 | 437.55 | 0%
324 | ML218SP04 | 2018-03-01 | 2018-05-01 | 647.5% | 69851.036 | 69851.036 | 400.11 | 17458%
325 | BSPPBS340 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 346.31 | 0%
326 | MLP15MP02 | 2015-02-01 | 2018-05-01 | 128.2% | 0 | 0 | 298.62 | 0%
327 | ML216EP13 | 2016-03-01 | 2018-05-01 | 142.2% | 0 | 0 | 289.62 | 0%
328 | BSPPBS339 | 2018-11-01 | Blanket | Blanket | 0 | 0 | 259.74 | 0%
329 | MLP19MP03 | 2019-03-01 | 2020-01-01 | 9.804% | 0 | 0 | 200.4 | 0%
330 | BSPPB0017 | 2016-12-01 | Blanket | Blanket | 0 | 0 | 134.9 | 0%
331 | ML217VP08 | 2017-12-01 | 2018-07-01 | 228.8% | 0 | 0 | 85.53 | 0%
332 | ML117SP14 | 2017-10-01 | 2018-05-01 | 257.5% | 0 | 0 | 12.89 | 0%
333 | MLP19MP02 | 2019-01-01 | Blanket | Blanket | 50101.146 | 50101.146 | 10.46 | 478978%
334 | ML119SP08 | 2018-11-01 | 2020-02-01 | 32.82% | 0 | 0 | 6.79 | 0%
335 | ML118VP08 | 2018-04-01 | 2018-11-01 | 170.1% | 0 | 0 | 0 | n.m.
336 | ML017EP11 | 2017-12-01 | 2018-07-01 | 228.8% | 0 | 0 | 0 | n.m.
337 | ML017EP01 | 2017-06-01 | 2018-05-01 | 200% | 24015.961 | 24015.961 | -0.23 | -10441722%
338 | ML116EP12 | 2016-04-01 | 2018-04-01 | 149.9% | 0 | 0 | -16.06 | 0%
339 | ML017EP09 | 2017-07-01 | 2018-07-01 | 174.8% | 0 | 0 | -17.26 | 0%
340 | BSPPBS333 | 2017-08-01 | 2018-12-01 | 124.6% | 0 | 0 | -50.64 | 0%
341 | MLP17EP01 | 2017-03-01 | 2018-07-01 | 156.1% | 0 | 0 | -79.35 | 0%
342 | ML017EP08 | 2017-05-01 | 2018-08-01 | 153% | 0 | 0 | -87.95 | 0%
343 | MLP17EP03 | 2017-01-01 | 2018-04-01 | 180% | 58806.519 | 58806.519 | -150.55 | -39061%
344 | ML1VP1704 | 2017-08-01 | 2018-07-01 | 181.7% | 0 | 0 | -206.02 | 0%
345 | ML017VP04 | 2017-03-01 | Blanket | Blanket | 0 | 0 | -3283.9 | 0%
346 | ML1E18C03 | 2017-07-01 | 2017-03-01 | -523% | 0 | 0 | -4478.5 | 0%
347 | KMLFALFCI | Charges Began Prior to Jan 2015 | 2015-12-01 | n.m. | 0 | 0 | -6043.66 | 0%
348 | ML1E18C02 | 2017-07-01 | 2018-07-01 | 174.8% | 0 | 0 | -6907.14 | 0%
349 | ML218SP14 | 2017-12-01 | 2018-05-01 | 321.2% | 0 | 0 | -9551.43 | 0%
350 | Other Budgeted Projects | Other | Other | Other | 30460517 | 23960924 | 0 | Other
351 | Total GLBU 117 (Generation) |  |  |  | 41260779.802 | 34761186.802 | 31875975.805 | 109.1%
352 | GLBU 180 (Transmission)
353 | P16113009 | 11/1/2017 | 2019-11-27 | 68.12% | 1744901.023 | 1744901.023 | 6749621.56 | 25.85%
354 | P11161025 | 8/1/2017 | 2018-10-18 | 137% | 0 | 0 | 2414329.81 | 0%
355 | A15702028 | 5/1/2017 | 2019-07-23 | 85.98% | 298199.82 | 298199.82 | 1782525.15 | 16.73%
356 | B180KYLRC | 2/1/2017 | Blanket | n.m. | 329278.781 | 329278.781 | 1670780.07 | 19.71%
357 | A18730013 | 8/1/2017 | 2018-05-31 | 200.3% | 0 | 0 | 1664442.11 | 0%
358 | A18730015 | 6/1/2018 | 2019-03-01 | 111% | 0 | 0 | 1577310.8 | 0%
359 | A15702007 | 6/1/2017 | 2018-06-28 | 170.4% | 0 | 0 | 1186897.55 | 0%
360 | A15702041 | 6/1/2017 | 2022-11-15 | 33.52% | 1401312.087 | 1401312.087 | 1182371.62 | 118.5%
361 | 000005273 | Charges Began Prior to Jan 2015 | 2018-01-23 | n.m. | 0 | 0 | 1104262.09 | 0%
362 | A15702033 | 5/1/2017 | 2019-10-15 | 77.93% | 3235502.857 | 3235502.857 | 1091638.88 | 296.4%
363 | P11161007 | 7/1/2017 | 2018-09-26 | 141.2% | 425658.817 | 425658.817 | 918728.66 | 46.33%
364 | A14068001 | Charges Began Prior to Jan 2015 | 2022-09-15 | n.m. | 0 | 0 | 869193.63 | 0%
365 | A15042010 | Charges Began Prior to Jan 2015 | 2019-11-14 | n.m. | 0 | 0 | 838848.99 | 0%
366 | P11161023 | 8/1/2017 | 2018-09-26 | 144.2% | 0 | 0 | 835572.13 | 0%
367 | A15702027 | 5/1/2017 | 2020-05-11 | 63.2% | 2115359.372 | 2115359.372 | 823778.59 | 256.8%
368 | A16928011 | 3/1/2017 | 2018-11-28 | 119.3% | 0 | 0 | 783759.87 | 0%
369 | P18025005 | 2/1/2018 | 2023-11-17 | 20% | 4825415.083 | 4825415.083 | 742796.74 | 649.6%
370 | A15702034 | 5/1/2017 | 2020-10-16 | 55.3% | 0 | 0 | 701600.8 | 0%
371 | P13064029 | 8/1/2017 | 2020-12-18 | 49.15% | 1396727.955 | 1396727.955 | 699701.3 | 199.6%
372 | P17225004 | 3/1/2019 | 2023-01-12 | 2.123% | 0 | 0 | 692084.83 | 0%
373 | P16113003 | 12/1/2016 | 2019-11-18 | 78.56% | 22786.056 | 22786.056 | 672920.6 | 3.386%
374 | A15710034 | 8/1/2018 | 2019-09-09 | 59.9% | 198410.209 | 198410.209 | 621622.32 | 31.92%
375 | A16902001 | 11/1/2016 | 2018-12-06 | 115% | 528809.236 | 528809.236 | 619893.7 | 85.31%
376 | 000012898 | Blanket | Blanket | Blanket | 672623.435 | 672623.435 | 617300.35 | 109%
377 | P11161012 | 7/1/2015 | 2018-10-11 | 114.3% | 284259.098 | 284259.098 | 567034.48 | 50.13%
378 | P13064025 | 4/1/2017 | 2020-12-18 | 53.72% | 278780.017 | 278780.017 | 538578.39 | 51.76%
379 | B180KYSRR | 10/1/2016 | Blanket | Blanket | 211493.22 | 211493.22 | 482135.4 | 43.87%
380 | DP16K02B0 | 4/1/2018 | 2019-10-25 | 63.64% | 0 | 0 | 467056.23 | 0%
381 | A17042001 | 2/1/2018 | 2018-12-06 | 137.3% | 0 | 0 | 462095.12 | 0%
382 | A13212035 | Charges Began Prior to Jan 2015 | 2018-07-27 | n.m. | 0 | 0 | 417768.63 | 0%
383 | A15702010 | 6/1/2017 | 2018-06-05 | 181% | 0 | 0 | 410269.07 | 0%
384 | P13064030 | 9/1/2017 | 2021-11-15 | 37.5% | 651890.486 | 651890.486 | 408956.66 | 159.4%
385 | IT1801421 | 3/1/2016 | 2019-12-31 | 80.36% | 0 | 0 | 388935.38 | 0%
386 | P10115014 | 7/1/2017 | 2019-11-14 | 73.67% | 0 | 0 | 376849.62 | 0%
387 | P13064031 | 12/1/2017 | 2021-11-15 | 33.56% | 0 | 0 | 347983.46 | 0%
388 | P11161008 | 7/1/2017 | 2018-06-10 | 185.5% | 203574.827 | 203574.827 | 328978 | 61.88%
389 | P10115002 | 3/1/2017 | 2019-12-19 | 74.29% | 0 | 0 | 296293.29 | 0%
390 | P17225003 | 3/1/2019 | 2023-01-12 | 2.123% | 2144.768 | 2144.768 | 289038.91 | 0.742%
391 | A15710033 | 12/1/2017 | 2020-02-14 | 60.25% | 0 | 0 | 284435.67 | 0%
392 | A15042007 | Charges Began Prior to Jan 2015 | 2019-07-31 | n.m. | 0 | 0 | 264424.88 | 0%
393 | A15042005 | Charges Began Prior to Jan 2015 | 2019-01-18 | n.m. | 0 | 0 | 248385.83 | 0%
394 | A14068005 | Charges Began Prior to Jan 2015 | 2018-12-28 | n.m. | 0 | 0 | 244800.82 | 0%
395 | A15702029 | 6/1/2017 | 2022-11-18 | 33.47% | 0 | 0 | 241290.13 | 0%
396 | A15702042 | 6/1/2017 | 2021-09-01 | 43.01% | 952036.629 | 952036.629 | 229943.91 | 414%
397 | P18025006 | 2/1/2018 | 2023-11-17 | 20% | 0 | 0 | 226445.87 | 0%
398 | A15702030 | 5/1/2017 | 2020-12-01 | 53.36% | 0 | 0 | 207197.31 | 0%
399 | A17938021 | 10/1/2017 | 2018-11-29 | 128.8% | 0.009 | 0.009 | 203856.47 | 4.415e-06%
400 | IT180BILL | 7/1/2017 | Blanket | Blanket | 0 | 0 | 170422.38 | 0%
401 | P17110001 | 10/1/2017 | 2021-11-19 | 36.16% | 2560954.31 | 2560954.31 | 169125.5 | 1514%
402 | A15710035 | 1/1/2019 | 2020-07-22 | 15.67% | 114868.037 | 114868.037 | 152228.85 | 75.46%
403 | P11161024 | 8/1/2017 | 2018-09-26 | 144.2% | 0 | 0 | 151982.79 | 0%
404 | A15702047 | 5/1/2017 | 2020-12-01 | 53.36% | 285610.988 | 285610.988 | 147884.31 | 193.1%
405 | A15702055 | 5/1/2017 | 2018-11-01 | 127.3% | 0 | 0 | 142799.46 | 0%
406 | P11161010 | 7/1/2015 | 2018-10-18 | 113.6% | 250874.897 | 250874.897 | 139557.92 | 179.8%
407 | A18730009 | 8/1/2017 | 2018-08-29 | 154.5% | 0 | 0 | 138780.61 | 0%
408 | A15702002 | 6/1/2017 | 2016-08-31 | -243.8% | 0 | 0 | 121601.97 | 0%
409 | P17225001 | 3/1/2019 | 2023-01-12 | 2.123% | 2172.366 | 2172.366 | 116315.51 | 1.868%
410 | P10115010 | 3/1/2017 | 2019-10-17 | 79.17% | 8.663 | 8.663 | 115951.9 | 0.007471%
411 | B180KYTRE | 10/1/2016 | Blanket | Blanket | 0 | 0 | 109695.86 | 0%
412 | P11063002 | 7/1/2017 | 2021-06-04 | 44.49% | 381080.589 | 381080.589 | 96122.11 | 396.5%
413 | P10115003 | 3/1/2017 | 2019-11-15 | 76.85% | 197255.993 | 197255.993 | 96104.49 | 205.3%
414 | A18730016 | 6/1/2018 | 2019-09-26 | 62.86% | 0 | 0 | 93511.9 | 0%
415 | A18730002 | 8/1/2017 | 2019-10-15 | 75.4% | 0 | 0 | 79468.33 | 0%
416 | A18730003 | 8/1/2017 | 2020-10-16 | 51.79% | 0 | 0 | 75117.22 | 0%
417 | DR18K02B1 | 9/1/2018 | 2019-06-28 | 70.33% | 0 | 0 | 69306.54 | 0%
418 | A16905009 | 3/1/2017 | 2021-11-19 | 44.08% | 608413.479 | 608413.479 | 66950.38 | 908.8%
419 | P17084003 | 10/1/2017 | 2021-12-02 | 35.85% | 785596.981 | 785596.981 | 64966.5 | 1209%
420 | DR18K02B2 | 10/1/2018 | 2019-06-28 | 67.04% | 0 | 0 | 63295.67 | 0%
421 | KYCR30003 | 3/1/2019 | 2018-03-01 | -8.219% | 0 | 0 | 61730.92 | 0%
422 | TP0921005 | 4/1/2014 | 2014-10-28 | 869% | 0 | 0 | 60648.25 | 0%
423 | P17110003 | 11/1/2017 | 2021-11-19 | 34.82% | 0 | 0 | 58644.31 | 0%
424 | P10115004 | 3/1/2017 | 2020-07-13 | 61.79% | 0 | 0 | 53241.77 | 0%
425 | P13064021 | 5/1/2016 | 2020-12-03 | 63.45% | 88682.244 | 88682.244 | 52779.25 | 168%
426 | P11161022 | 3/1/2017 | 2018-03-30 | 192.9% | 0 | 0 | 52027.84 | 0%
427 | A15042011 | Charges Began Prior to Jan 2015 | 2019-05-16 | n.m. | 0 | 0 | 51924.78 | 0%
428 | P11161009 | 7/1/2017 | 2018-03-09 | 254.2% | 151060.449 | 151060.449 | 49902.02 | 302.7%
429 | A15702043 | 6/1/2017 | 2021-09-01 | 43.01% | 0 | 0 | 49473.51 | 0%
430 | A18730011 | 8/1/2017 | 2018-08-29 | 154.5% | 0 | 0 | 46465.35 | 0%
431 | P17084026 | 9/1/2017 | 2024-07-05 | 23.05% | 0 | 0 | 44870.21 | 0%
432 | P10115015 | 7/1/2017 | 2019-10-17 | 76.13% | 0 | 0 | 44763.85 | 0%
433 | P13064002 | 8/1/2016 | 2021-11-15 | 50.31% | 74210.168 | 74210.168 | 44081.26 | 168.3%
434 | A15702049 | 3/1/2018 | 2022-09-01 | 24.01% | 0 | 0 | 43595.67 | 0%
435 | A15702035 | 5/1/2017 | 2021-12-17 | 41.34% | 0 | 0 | 42658.59 | 0%
436 | P16116005 | 7/1/2017 | 2025-11-15 | 20.86% | 6571.577 | 6571.577 | 41351.42 | 15.89%
437 | P18090001 | 7/1/2018 | 2019-06-01 | 81.49% | 0 | 0 | 41011.7 | 0%
438 | A17750007 | 2/1/2019 | 2019-08-05 | 31.35% | 0 | 0 | 39475.76 | 0%
439 | A15702054 | 5/1/2017 | 2017-08-28 | 587.4% | 0 | 0 | 38285.57 | 0%
440 | A15702036 | 5/1/2017 | 2021-12-17 | 41.34% | 743630.061 | 743630.061 | 33620.65 | 2212%
441 | P17225008 | 3/1/2019 | 2023-06-29 | 1.898% | 158186.202 | 158186.202 | 33597.27 | 470.8%
442 | P17076001 | 9/1/2017 | 2023-11-01 | 25.58% | 36471.608 | 36471.608 | 33021.6 | 110.4%
443 | A15702006 | 4/1/2016 | 2021-12-31 | 52.1% | 0 | 0 | 32973.33 | 0%
444 | A18730012 | 8/1/2017 | 2018-06-20 | 187.9% | 0 | 0 | 32158.08 | 0%
445 | P17083001 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | 31215.03 | 0%
446 | P17084007 | 10/1/2017 | 2023-11-10 | 24.47% | 271090.725 | 271090.725 | 30679.17 | 883.6%
447 | P11028016 | 7/1/2017 | 2018-11-01 | 130.7% | 0 | 0 | 30228.86 | 0%
448 | B180KYSRC | 12/1/2016 | 2020-12-31 | 57.01% | 184691.406 | 184691.406 | 29213.99 | 632.2%
449 | A15702060 | 8/1/2017 | 2018-12-31 | 117.4% | 0 | 0 | 28090.53 | 0%
450 | A16928002 | 3/1/2017 | 2019-01-01 | 113.3% | 0 | 0 | 28012.8 | 0%
451 | A15710024 | 8/1/2017 | 2019-10-31 | 73.93% | 14970.925 | 14970.925 | 26456.86 | 56.59%
452 | A15042012 | 6/1/2017 | 2019-11-15 | 74.47% | 0 | 0 | 24539.6 | 0%
453 | A17212001 | 7/1/2018 | 2019-10-09 | 58.71% | 0 | 0 | 24389.73 | 0%
454 | A15702032 | 5/1/2017 | 2021-12-17 | 41.34% | 0 | 0 | 23584.47 | 0%
455 | P11161001 | 7/1/2017 | 2018-11-02 | 130.5% | 0.018 | 0.018 | 21802.07 | 8.256e-05%
456 | P12104006 | 8/1/2017 | 2019-02-01 | 110.6% | 0 | 0 | 21678.83 | 0%
457 | 000025230 | Blanket | Blanket | Blanket | 0 | 0 | 21058.66 | 0%
458 | P18025013 | 2/1/2018 | 2023-11-17 | 20% | 0 | 0 | 19368.51 | 0%
459 | P13064003 | 5/1/2016 | 2021-11-15 | 52.57% | 100497.386 | 100497.386 | 19123.57 | 525.5%
460 | A15702053 | 5/1/2017 | 2017-12-16 | 305.2% | 0 | 0 | 18530.86 | 0%
461 | A18502002 | 10/1/2017 | 2019-04-15 | 97.33% | 0 | 0 | 17746.91 | 0%
462 | A15702013 | 6/1/2017 | 2017-12-21 | 329.1% | 0 | 0 | 16839.21 | 0%
463 | A18702003 | 10/1/2017 | 2019-09-01 | 78% | 0 | 0 | 16387.34 | 0%
464 | A15702003 | 6/1/2017 | 2017-11-28 | 371.1% | 0 | 0 | 15735.28 | 0%
465 | P17225013 | 2/1/2018 | 2023-06-29 | 21.43% | 791497.723 | 791497.723 | 15693.57 | 5043%
466 | A15705185 | 5/1/2019 | 2017-06-01 | 4.435% | 0 | 0 | 14899.82 | 0%
467 | A15710036 | 12/1/2017 | 2020-02-14 | 60.25% | 0 | 0 | 13557.89 | 0%
468 | P13064020 | 5/1/2017 | 2020-12-03 | 53.28% | 23272.875 | 23272.875 | 13295.04 | 175%
469 | P18025007 | 2/1/2018 | 2023-11-17 | 20% | 0 | 0 | 13159.17 | 0%
470 | A15702057 | 8/1/2017 | 2018-12-31 | 117.4% | 0 | 0 | 11678.99 | 0%
471 | P10115013 | 7/1/2017 | 2020-05-11 | 61.05% | 848004.748 | 848004.748 | 11365.48 | 7461%
472 | P17084037 | 11/1/2017 | 2024-07-05 | 21.12% | 0 | 0 | 11063.72 | 0%
473 | ITCB18000 | 7/1/2017 | Blanket | Blanket | 0 | 0 | 10277.94 | 0%
474 | A15710041 | 12/1/2018 | 2019-08-19 | 45.98% | 5803.982 | 5803.982 | 10246.52 | 56.64%
475 | P17110002 | 11/1/2017 | 2021-11-19 | 34.82% | 0 | 0 | 10149.22 | 0%
476 | DP14K02C0 | 8/1/2018 | 2021-07-21 | 22.3% | 0 | 0 | 9372.57 | 0%
477 | P14030008 | 6/1/2016 | 2023-11-15 | 37.94% | 205878.788 | 205878.788 | 8526.81 | 2414%
478 | A15710037 | 12/1/2017 | 2019-08-12 | 78.35% | 9282.463 | 9282.463 | 8312.31 | 111.7%
479 | P17110005 | 10/1/2017 | 2021-11-19 | 36.16% | 0 | 0 | 7832.86 | 0%
480 | A15010001 | Charges Began Prior to Jan 2015 | 2018-11-01 | n.m. | 0 | 0 | 7503.03 | 0%
481 | P14030102 | 12/1/2017 | 2023-09-05 | 23.05% | 53886.354 | 53886.354 | 7097.03 | 759.3%
482 | P10115001 | 9/1/2016 | 2020-06-18 | 67.89% | 947157.574 | 947157.574 | 6742.96 | 14047%
483 | O18EST033 | 9/1/2016 | Blanket | Blanket | 0 | 0 | 6544.25 | 0%
484 | P17084016 | 9/1/2017 | 2024-07-05 | 23.05% | 0 | 0 | 6485.71 | 0%
485 | P17110006 | 7/1/2018 | 2021-11-19 | 22.07% | 0 | 0 | 6214.07 | 0%
486 | P18025008 | 2/1/2018 | 2023-11-17 | 20% | 0 | 0 | 6177.85 | 0%
487 | P13121006 | 12/1/2017 | 2018-06-01 | 266.5% | 0 | 0 | 5512.18 | 0%
488 | A18730001 | 8/1/2017 | 2021-12-17 | 37.96% | 0 | 0 | 5333.11 | 0%
489 | A15702025 | 6/1/2017 | 2018-12-06 | 120.8% | 1157402.401 | 1157402.401 | 5091.85 | 22730%
490 | A17959001 | 10/1/2017 | 2018-10-01 | 149.6% | 0 | 0 | 4871.02 | 0%
491 | P17076005 | 9/1/2017 | 2023-11-01 | 25.58% | 0 | 0 | 4684.4 | 0%
492 | P12088005 | 8/1/2017 | 2018-12-01 | 124.6% | 0 | 0 | 4251.82 | 0%
493 | A15710022 | 1/1/2017 | 2020-02-14 | 71.91% | 0 | 0 | 3917.06 | 0%
494 | P17110007 | 3/1/2019 | 2021-11-19 | 3.018% | 0 | 0 | 3761.93 | 0%
495 | A18730004 | 8/1/2017 | 2021-12-17 | 37.96% | 0 | 0 | 3489.33 | 0%
496 | P16113004 | 12/1/2016 | 2019-11-27 | 77.91% | 6.579 | 6.579 | 3346.59 | 0.1966%
497 | SI180KYUN | 8/1/2019 | Blanket | Blanket | 0 | 0 | 3346.31 | 0%
498 | A18730005 | 8/1/2017 | 2021-12-17 | 37.96% | 0 | 0 | 3267.1 | 0%
499 | KYCR33039 | 5/1/2016 | 2017-12-29 | 175.3% | 0 | 0 | 3131.09 | 0%
500 | P17084036 | 11/1/2017 | 2024-07-05 | 21.12% | 0 | 0 | 2722.79 | 0%
501 | P18066001 | 2/1/2018 | 2020-06-01 | 49.71% | 0 | 0 | 2652.59 | 0%
502 | A15702061 | 8/1/2017 | 2019-08-01 | 83.15% | 0 | 0 | 2488.11 | 0%
503 | P17084019 | 9/1/2017 | 2023-11-10 | 25.48% | 0 | 0 | 2255.85 | 0%
504 | P18066003 | 2/1/2018 | 2020-06-01 | 49.71% | 0 | 0 | 2052.41 | 0%
505 | KYCR34118 | 5/1/2016 | 2017-12-29 | 175.3% | 0 | 0 | 2002.52 | 0%
506 | P14030013 | 9/1/2016 | 2023-11-15 | 35.77% | 184595.376 | 184595.376 | 1907.7 | 9676%
507 | P17084017 | 9/1/2017 | 2023-11-10 | 25.48% | 0 | 0 | 1791.14 | 0%
508 | A15710001 | 5/1/2019 | 2018-07-01 | 10.2% | 0 | 0 | 1641.54 | 0%
509 | DP14K02C1 | 10/1/2018 | 2021-07-21 | 17.68% | 0 | 0 | 1640.31 | 0%
510 | A17750008 | 3/1/2019 | 2019-12-26 | 10% | 0 | 0 | 1594.53 | 0%
511 | P18066005 | 2/1/2018 | 2020-06-01 | 49.71% | 0 | 0 | 1375.94 | 0%
512 | P17083003 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | 1345.33 | 0%
513 | P18025012 | 2/1/2018 | 2023-11-17 | 20% | 0 | 0 | 1274.75 | 0%
514 | P17076006 | 10/1/2017 | 2023-11-01 | 24.57% | 0 | 0 | 1227.8 | 0%
515 | DP14K02T0 | 10/1/2018 | 2021-07-21 | 17.68% | 0 | 0 | 1213.41 | 0%
516 | P17084022 | 9/1/2017 | 2024-07-05 | 23.05% | 0 | 0 | 1121.3 | 0%
517 | P17084038 | 11/1/2017 | 2024-07-05 | 21.12% | 0 | 0 | 1084.43 | 0%
518 | P17225017 | 2/1/2018 | 2023-06-29 | 21.43% | 214441.184 | 214441.184 | 985.39 | 21762%
519 | P17083034 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | 828.86 | 0%
520 | P14030103 | 12/1/2017 | 2023-11-15 | 22.3% | 100121.258 | 100121.258 | 749.95 | 13350%
521 | P14030002 | 3/1/2017 | 2023-12-19 | 30.6% | 18757.709 | 18757.709 | 657.86 | 2851%
522 | P17225014 | 2/1/2018 | 2023-06-29 | 21.43% | 417710.844 | 417710.844 | 657 | 63579%
523 | SI180KYRE | 8/1/2019 | 2021-12-31 | -13.93% | 73.635 | 73.635 | 653.75 | 11.26%
524 | P17084013 | 9/1/2017 | 2024-07-05 | 23.05% | 0 | 0 | 566.61 | 0%
525 | P17083006 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | 543.62 | 0%
526 | P14030104 | 12/1/2017 | 2024-01-22 | 21.62% | 9036.345 | 9036.345 | 490.14 | 1844%
527 | P18066002 | 2/1/2018 | 2020-06-01 | 49.71% | 0 | 0 | 354.81 | 0%
528 | A15702059 | 8/1/2017 | 2019-08-01 | 83.15% | 0 | 0 | 351.17 | 0%
529 | P17084023 | 9/1/2017 | 2024-07-05 | 23.05% | 0 | 0 | 238.21 | 0%
530 | A15710064 | 3/1/2019 | 2020-08-10 | 5.682% | 0 | 0 | 236.93 | 0%
531 | P17225016 | 2/1/2018 | 2023-06-29 | 21.43% | 417710.844 | 417710.844 | 216.29 | 193125%
532 | P17083026 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | 197 | 0%
533 | P16116002 | 11/1/2016 | 2025-11-15 | 26.66% | 208.159 | 208.159 | 182.4 | 114.1%
534 | P17225018 | 2/1/2018 | 2023-06-29 | 21.43% | 872531.999 | 872531.999 | 172.88 | 504704%
535 | P11161026 | 8/1/2017 | 2018-10-18 | 137% | 0 | 0 | 164.69 | 0%
536 | P17084029 | 10/1/2017 | 2024-07-05 | 22.11% | 0 | 0 | 139.26 | 0%
537 | P17084021 | 9/1/2017 | 2024-07-05 | 23.05% | 0 | 0 | 138.77 | 0%
538 | A13212037 | Charges Began Prior to Jan 2015 | 2018-12-01 | n.m. | 11640.544 | 11640.544 | 135.94 | 8563%
539 | P17084020 | 9/1/2017 | 2023-11-10 | 25.48% | 0 | 0 | 132.19 | 0%
540 | P17225015 | 2/1/2018 | 2023-06-29 | 21.43% | 928246.321 | 928246.321 | 116.98 | 793509%
541 | P17074005 | 7/1/2017 | 2019-04-01 | 99.84% | 0 | 0 | 107.98 | 0%
542 | P17084018 | 9/1/2017 | 2023-11-10 | 25.48% | 0 | 0 | 82.86 | 0%
543 | P17076010 | 6/1/2018 | 2023-11-01 | 15.31% | 0 | 0 | 43.82 | 0%
544 | P14030101 | 3/1/2017 | 2023-11-15 | 31.02% | 904.48 | 904.48 | 32.18 | 2811%
545 | A16928015 | 1/1/2019 | 2020-05-05 | 18.16% | 0 | 0 | 30.8 | 0%
546 | P17083008 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | 13.08 | 0%
547 | P14030015 | 11/1/2016 | 2023-11-15 | 34.24% | 3613.694 | 3613.694 | 10.65 | 33931%
548 | 000017437 | Charges Began Prior to Jan 2015 | 2015-12-31 | n.m. | 0 | 0 | 7.91 | 0%
549 | P14030016 | 11/1/2016 | 2023-11-15 | 34.24% | 36136.934 | 36136.934 | 7.68 | 470533%
550 | A15702038 | 5/1/2017 | 2019-03-01 | 104.5% | 0 | 0 | 4.46 | 0%
551 | ETN000180 | 2/1/2018 | Blanket | Blanket | 0.003 | 0.003 | 0 | n.m.
552 | P17074010 | 7/1/2017 | 2019-07-01 | 87.4% | 0 | 0 | -7.66 | 0%
553 | P12088002 | 8/1/2017 | 2018-12-01 | 124.6% | 0 | 0 | -11.68 | 0%
554 | P17083009 | 3/1/2019 | 2023-11-15 | 1.744% | 0 | 0 | -393.38 | 0%
555 | P17074001 | 7/1/2017 | 2019-05-01 | 95.37% | 0 | 0 | -762.6 | 0%
556 | A15702044 | 6/1/2017 | 2018-10-01 | 137.2% | 0 | 0 | -970.31 | 0%
557 | ITCW18001 | 4/1/2017 | 2019-04-01 | 99.86% | 0 | 0 | -1004.54 | 0%
558 | A15702020 | 6/1/2017 | 2018-10-01 | 137.2% | 0 | 0 | -1089.06 | 0%
559 | A15702014 | 6/1/2017 | 2018-10-01 | 137.2% | 0 | 0 | -1229.17 | 0%
560 | A15702016 | 6/1/2017 | 2018-10-01 | 137.2% | 0 | 0 | -2336.26 | 0%
561 | P17074009 | 7/1/2017 | 2019-05-01 | 95.37% | 0 | 0 | -3241.65 | 0%
562 | P12088004 | 8/1/2017 | 2018-11-01 | 132.8% | 0 | 0 | -3831.88 | 0%
563 | A15702040 | 5/1/2017 | 2019-05-01 | 95.75% | 0 | 0 | -4614.09 | 0%
564 | P16116003 | 11/1/2016 | 2025-11-15 | 26.66% | 6546.732 | 6546.732 | -4956.56 | -132.1%
565 | SI180KYLR | 8/1/2019 | 2015-12-31 | 9.396% | 0 | 0 | -5141.7 | 0%
566 | P18001001 | 2/1/2018 | 2019-03-01 | 107.6% | 0 | 0 | -5367.2 | 0%
567 | KEPCS1701 | 4/1/2017 | 2020-03-18 | 67.38% | 0 | 0 | -18188.74 | 0%
568 | A15702037 | 5/1/2017 | 2018-09-01 | 143.2% | 1124444.713 | 1124444.713 | -47699.8 | -2357%
569 | A17016002 | 1/1/2019 | 2019-12-27 | 24.72% | 0 | 0 | -48737.7 | 0%
570 | A15702056 | 8/1/2017 | 2020-05-04 | 60.28% | 0 | 0 | -63450.37 | 0%
571 | P11028004 | 7/1/2017 | 2018-09-01 | 149.4% | 0 | 0 | -63462.89 | 0%
572 | A17016001 | 1/1/2019 | 2019-12-27 | 24.72% | 0 | 0 | -131577.58 | 0%
573 | 000025076 | Charges Began Prior to Jan 2015 | 2020-04-30 | n.m. | 0 | 0 | -428650.72 | 0%
574 | Other Budgeted Projects | Other | Other | Other | 46159043.28 | 46159043.28 |  | Other
575 | Total GLBU 180 (Transmission) |  |  |  | 81344020.398 | 81344020.398 | 42197030.75 | 192.8%
576 | Total Kentucky Power CWIP Additions |  |  |  | 186547718.034 | 175729217.173 | 144448231.486 | 121.7%
577
578 | X00000317 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -55045969.11 | Property Acctg
579 | X00000288 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -24081770.27 | Property Acctg
580 | X00000306 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -33342729.55 | Property Acctg
581 | Total Kentucky Power Transfers to 101/106 | [5 empty] | -112470468.93
582
583 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year April 2018 - March 2019 |  |  |  | 186547718.034 | 175729217.173 | 31977762.556
584
585
586 | Definitions:
587 | (C)* | Represents the month project expenditures were initially recorded to CWIP (Account 107).
588 | (H)* | Represents Total Cost (G) per Schedule D.
589 | (J)* | 2019-03-31
590 | Blanket | Repetitive and predictable work charged and closed continuously throughout the calendar year.
591 | Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
592 | Other | Other amounts reflected in budget; do not directly relate to a project with actual spend during the period.
593 | n.m. | Not meaningful