## AG - PH1
Bluegrass Water UOC, LLC
Construction Item Actual Costs
For Invoices Received or Costs Accrued as of April 30, 2021
| Service Area | Type | Item Code | Item | Actual | Budget Cost | Status | Variance
| Airview | CON | AV.1 | Collection system repair for I and I | 42743.05 | 55000 | P | -12256.95
| Airview | CON | AV.2 | Sludge Holding tank renovation | 41079.6 | 5000 | C | 36079.6
| Airview | CON | AV.3 | Clarifier Repairs | 5471 | 20000 | C | -14529
| Airview | CON | AV.4 | Replace diffusers in aeration tankage | 13355.68 | 30000 | C | -16644.32
| Airview | CON | AV.5 | Replace RAS lines from clarifier | 13747.31 | 15000 | C | -1252.69
| Airview | CON | AV.6 | Replace blower | 7230.76 | 25000 | C | -17769.24
| Airview | CON | AV.7 | Replace effluent pipe | 7731.37 | 15000 | C | -7268.63
| Airview | CON | AV.8 | Remove contact chamber from creek | 5317.5 | 5000 | C | 317.5
| Airview | CON | AV.9 | Smoke test system | 9575.09 | 9000 | C | 575.09
| Brocklyn | CON | BR.1 | Yard piping and miscellaneous piping | 12405.11 | 50000 | P | -37594.89
| Brocklyn | CON | BR.2 | Lagoon closure | 229328.59 | 199000 | C | 30328.59
| Brocklyn | CON | BR.3 | Sludge judge lagoon cell | 2939 | 2500 | C | 439
| Brocklyn | CON | BR.4 | Cleanup sludge from creek | 10290.46 | 10000 | C | 290.46
| Brocklyn | CON | BR.5 | Smoke test system | 7674.24 | 7000 | C | 674.24
| Center Ridge 1 | CON | CR1.1 | Building repairs (inside and outside) | 25987.14 | 30000 | P | -4012.86
| Center Ridge 1 | CON | CR1.2 | Well Inspection | 1292 | 1250 | C | 42
| Center Ridge 1 | CON | CR1.3 | Replace well pump and wiring | 8095.24 | 30000 | C | -21904.76
| Center Ridge 1 | CON | CR1.4 | New magnetic flow meter for well | 4603.51 | 4500 | C | 103.51
| Center Ridge 1 | CON | CR1.5 | Mission monitoring | 20618.39 | 8000 | C | 12618.39
| Center Ridge 1 | CON | CR1.6 | Electrical upgrades in well house | 2088.84 | 10000 | C | -7911.16
| Center Ridge 2 | CON | CR2.1 | Return existing out of use well to service | 34168.59 | 20000 | C | 14168.59
| Center Ridge 2 | CON | CR2.2 | Building repairs on southern building(inside and outside) | 29109.23 | 40000 | C | -10890.77
| Center Ridge 2 | CON | CR2.3 | Repaint existing hydropneumatic tank | 3643.93 | 10000 | C | -6356.07
| Center Ridge 2 | CON | CR2.4 | Well Inspection | 2347 | 2500 | C | -153
| Center Ridge 2 | CON | CR2.5 | Replace well pump and wiring | 7549.13 | 15000 | C | -7450.87
| Center Ridge 2 | CON | CR2.6 | New magnetic flow meter for well | 15918.54 | 9000 | C | 6918.54
| Center Ridge 2 | CON | CR2.7 | Mission monitoring | 15918.53 | 16000 | C | -81.47
| Center Ridge 3 | CON | CR3.1 | Gravel for all weather road | 3673 | 5000 | C | -1327
| Center Ridge 3 | CON | CR3.2 | New well house and appurtenances | 46621.99 | 85000 | C | -38378.01
| Center Ridge 3 | CON | CR3.3 | Miscellaneous yard piping | 5852.64 | 30000 | C | -24147.36
| Center Ridge 3 | CON | CR3.4 | Well Inspection | 2832 | 2500 | C | 332
| Center Ridge 3 | CON | CR3.5 | Replace well pump and wiring | 257.5 | 40000 | C | -39742.5
| Center Ridge 3 | CON | CR3.6 | Mission monitoring | 10143.09 | 8000 | C | 2143.09
| Center Ridge 4 | CON | CR4.1 | Building repairs (inside and outside) | 15162.54 | 15000 | P | 162.54
| Center Ridge 4 | CON | CR4.2 | Gravel for all weather road | 3376.98 | 15000 | C | -11623.02
| Center Ridge 4 | CON | CR4.3 | Well Inspection | 1569 | 1250 | C | 319
| Center Ridge 4 | CON | CR4.4 | Replace well pump and wiring | 11750.76 | 20000 | C | -8249.24
| Center Ridge 4 | CON | CR4.5 | New magnetic flow meter for well | 0 | 4500 | C | -4500
| Center Ridge 4 | CON | CR4.6 | Mission monitoring | 2101.95 | 8000 | C | -5898.05
| Center Ridge 4 | CON | CR4.7 | Electrical upgrades in well house | 15767.73 | 15000 | C | 767.73
| Fox Run | CON | FR.1 | Collection system repair for I and I | 12319.99 | 20000 | P | -7680.01
| Fox Run | CON | FR.10 | Collection system lift station overhaul | 26687.8 | 33000 | C | -6312.2
| Fox Run | CON | FR.11 | Smoke test system | 7733.33 | 7500 | C | 233.33
| Fox Run | CON | FR.12 | Granular rock per easement deal | 5863.42 | 5000 | C | 863.42
| Fox Run | CON | FR.2 | Overhaul influent pump station | 48038.08 | 15000 | C | 33038.08
| Fox Run | CON | FR.3 | Install Mission Alarm and wiring with meter | 5423.56 | 10000 | C | -4576.44
| Fox Run | CON | FR.4 | Install Mission Alarm on collection lift station | 5423.55 | 12000 | C | -6576.45
| Fox Run | CON | FR.5 | Replace diffusers in aeration tankage | 11189.4 | 15000 | C | -3810.6
| Fox Run | CON | FR.6 | Replace RAS lines from clarifier | 7543.35 | 7500 | C | 43.35
| Fox Run | CON | FR.8 | Replace blower | 16336.19 | 20000 | C | -3663.81
| Fox Run | CON | FR.9 | Sand blast and paint tankage | 14052.05 | 10000 | C | 4052.05
| Golden Acres | CON | GA.1 | Sanitary sewer video inspection | 9008.69 | 6500 | P | 2508.69
| Golden Acres | CON | GA.2 | Replace effluent pipe | 12819.17 | 25000 | P | -12180.83
| Golden Acres | CON | GA.3 | Install Mission Alarm and wiring with meter | 17207.8695 | 15000 | C | 2207.8695
| Golden Acres | CON | GA.4 | Replace blower | 17759.1295 | 15000 | C | 2759.1295
| Golden Acres | CON | GA.5 | Dechlorination | 226.87 | 1500 | C | -1273.13
| Golden Acres | CON | GA.6 | Sludge Digestor | 2270 | 15000 | C | -12730
| Golden Acres | CON | GA.7 | Smoke test system | 5316.28 | 6000 | C | -683.72
| Great Oaks | CON | GO.1 | Collection system repair for I and I | 6927.84 | 20000 | P | -13072.16
| Great Oaks | CON | GO.10 | Pump down aeration and clarifier due to trash and clean | 4162.5 | 10000 | C | -5837.5
| Great Oaks | CON | GO.2 | Overhaul influent lift station | 20318.23 | 10000 | C | 10318.23
| Great Oaks | CON | GO.3 | Install Mission Alarm and wiring with meter | 12799.28 | 10000 | C | 2799.28
| Great Oaks | CON | GO.4 | Replace diffusers in aeration tankage | 19101.81 | 20000 | C | -898.19
| Great Oaks | CON | GO.5 | Replace RAS lines from clarifier | 9541.07 | 15000 | C | -5458.93
| Great Oaks | CON | GO.6 | Replace blower | 7709.62 | 7500 | C | 209.62
| Great Oaks | CON | GO.7 | Sand blast and repaint tankage, cat walk and railing | 20335.67 | 36000 | C | -15664.33
| Great Oaks | CON | GO.8 | Fencing repair | 2221 | 6000 | C | -3779
| Great Oaks | CON | GO.9 | Smoke test system | 1186.25 | 14000 | C | -12813.75
| Kingswood | CON | KW.1 | Cleanup blower house and equipment | 19070.67 | 15000 | P | 4070.67
| Kingswood | CON | KW.2 | Install Mission Alarm, wiring and mag meter | 15005.33 | 11000 | C | 4005.33
| Kingswood | CON | KW.3 | Lift Station Check valves replaced - failed | 15114.97 | 2500 | C | 12614.97
| Kingswood | CON | KW.4 | Air header replacement due to lack of air to aeration | 7345.77 | 10000 | C | -2654.23
| Kingswood | CON | KW.5 | Smoke Test system (Might be pressure, to verify) | 10585.24 | 20000 | C | -9414.76
| Lake Columbia | CON | LC.1 | Repair bar screen system | 1458.52 | 5000 | C | -3541.48
| Lake Columbia | CON | LC.2 | Install Mission Alarm and wiring with meter | 3329.41 | 10000 | C | -6670.59
| Lake Columbia | CON | LC.3 | Return piping from new clarifier | 5172.37 | 5000 | C | 172.37
| Lake Columbia | CON | LC.4 | Trank replacement for Bar Screen and Contact Chamber | 11501.94 | 25000 | C | -13498.06
| Lake Columbia | CON | LC.5 | Replace motor on blower | 30422.61 | 13000 | C | 17422.61
| Lake Columbia | CON | LC.6 | Sand blast, paint, and repair tankage | 41184.17 | 20000 | C | 21184.17
| Lake Columbia | CON | LC.7 | Cleanup sludge from creek | 7174.14 | 10000 | C | -2825.86
| Lake Columbia | CON | LC.8 | Smoke test system | 6362.18 | 15000 | C | -8637.82
| Longview/Homestead | CON | LH.1 | Cleanup blower house and equipment | 13090.65 | 15000 | C | -1909.35
| Longview/Homestead | CON | LH.2 | Install Mission Alarm and wiring | 7706.91 | 7500 | C | 206.91
| Longview/Homestead | CON | LH.3 | Replace diffusers in aeration tankage | 6550.02 | 10000 | C | -3449.98
| Longview/Homestead | CON | LH.4 | Smoke Test system | 32572.39 | 13000 | C | 19572.39
| Persimmon Ridge | CON | PR.1 | Airmaster Aerator (1 - 25 Hp units) | 28895.05 | 36667 | C | -7771.95
| Persimmon Ridge | CON | PR.2 | Electrical upgrades for Airmaster and install | 23792.45 | 35000 | C | -11207.55
| Persimmon Ridge | CON | PR.3 | Install Mission Alarm and wiring with meter | 1666.01 | 10000 | C | -8333.99
| Persimmon Ridge | CON | PR.4 | Install Mission Alarm and wiring at pumps stations | 26951.51 | 30000 | C | -3048.49
| Persimmon Ridge | CON | PR.5 | Repair existing aerators | 12737.86 | 10000 | C | 2737.86
| Persimmon Ridge | CON | PR.6 | Smoke test system | 46087.97 | 27000 | C | 19087.97
| River Bluffs | CON | RB.1 | Mission Monitoring | 20659.75 | 18000 | C | 2659.75
| River Bluffs | CON | RB.2 | Lift station cleanup | 25449.86 | 33000 | C | -7550.14
| River Bluffs | CON | RB.3 | Control Panel Replacement | 12995.55 | 10000 | C | 2995.55
| River Bluffs | CON | RB.4 | Replace influent/exposed PVC pipe | 25164.25 | 10000 | C | 15164.25
| River Bluffs | CON | RB.5 | Treatment facility cleanup and repair | 231578.54 | 20000 | C | 211578.54
| River Bluffs | CON | RB.6 | Replace diffusers and blowers | 96558.85 | 32500 | C | 64058.85
| River Bluffs | CON | RB.7 | Replace air header | 35000 | 5000 | C | 30000
| River Bluffs | CON | RB.8 | Replace sludge returns | 12958 | 10000 | C | 2958
| Randview | CON | RV.1 | Clear vegetation from berms | 10933.1 | 30000 | C | -19066.9
| Joann Estates | CON | TM.1 | Treatment facility cleanup and repair (Air headers, returns, and path welding) | 20488.11 | 50000 | P | -29511.89
| Joann Estates | CON | TM.2 | contact chamber (with plans to switch to PAA in the future) | 2264.53 | 20000 | P | -17735.47
| Joann Estates | CON | TM.3 | Mission Monitoring | 3405.35 | 8000 | C | -4594.65
| Joann Estates | CON | TM.4 | Lift station overhaul | 40184.03 | 40000 | C | 184.03
| Joann Estates | CON | TM.5 | Berm Maintenance and rock interior | 28215.17 | 35000 | C | -6784.83
| Joann Estates | CON | TM.6 | New upgraded electrical service and panel | 106 | 25000 | C | -24894
[6 empty] | 1982667 |  | -14067.761
0

## Construction Invoices
Bluegrass Utility Operating Company, LLC
CIP Invoice Listing
Vendor | Inv # | Budget Code | Date | Amount | Item Code
Midwest Water Operations LLC | 1165 | Airview - Wastewater | 2020-01-31 | 17132.71 | AV.1
Midwest Water Operations LLC | 1108 | Airview - Wastewater | 2019-12-31 | 9399.86 | AV.1
Midwest Water Operations LLC | 1055 | Airview - Wastewater | 2019-11-30 | 9381.6 | AV.1
Midwest Water Operations LLC | 1479 | Airview - Wastewater | 2020-05-01 | 3583.88 | AV.1
Midwest Water Operations LLC | 1230 | Airview - Wastewater | 2020-02-28 | 1209.17 | AV.1
J. R. Hoe & Sons, Inc. | 163828 | Airview - Wastewater | 2020-02-19 | 813.02 | AV.1
Midwest Water Operations LLC | 1575 | Airview - Wastewater | 2020-06-01 | 635 | AV.1
Midwest Water Operations LLC | 1230 | Airview - Wastewater | 2020-02-28 | 587.81 | AV.1
Midwest Water Operations LLC | 1575 | Airview - Wastewater | 2020-06-01 | 26168.26 | AV.2
Midwest Water Operations LLC | 1479 | Airview - Wastewater | 2020-05-01 | 6088.88 | AV.2
Midwest Water Operations LLC | 1108 | Airview - Wastewater | 2019-12-31 | 2684.51 | AV.2
Midwest Water Operations LLC | 1055 | Airview - Wastewater | 2019-11-30 | 2206.71 | AV.2
Midwest Water Operations LLC | 962 | Airview - Wastewater | 2019-10-01 | 1854.75 | AV.2
Midwest Water Operations LLC | BG-Pay App #4 | Airview - Wastewater | 2021-02-28 | 1689 | AV.2
Midwest Water Operations LLC | 794 | Airview - Wastewater | 2020-08-31 | 387.49 | AV.2
Midwest Water Operations LLC | 1165 | Airview - Wastewater | 2020-01-31 | 2475.34 | AV.3
Midwest Water Operations LLC | 1008 | Airview - Wastewater | 2019-10-31 | 850 | AV.3
Midwest Water Operations LLC | 1230 | Airview - Wastewater | 2020-02-28 | 845.66 | AV.3
Midwest Water Operations LLC | 1055 | Airview - Wastewater | 2019-11-30 | 490 | AV.3
Midwest Water Operations LLC | 794 | Airview - Wastewater | 2020-08-31 | 420 | AV.3
Midwest Water Operations LLC | 1230 | Airview - Wastewater | 2020-02-28 | 250 | AV.3
21 Design Group Inc. | 5488 | Airview - Wastewater | 2020-07-01 | 140 | AV.3
Midwest Water Operations LLC | 1108 | Airview - Wastewater | 2019-12-31 | 9528.61 | AV.4
Midwest Water Operations LLC | 909 | Airview - Wastewater | 2020-09-01 | 2132.85 | AV.4
Midwest Water Operations LLC | 1676 | Airview - Wastewater | 2020-06-30 | 1369.22 | AV.4
Midwest Water Operations LLC | 1383 | Airview - Wastewater | 2020-03-31 | 325 | AV.4
Midwest Water Operations LLC | 1108 | Airview - Wastewater | 2019-12-31 | 7502.09 | AV.5
TNT Technologies Inc | 1643 | Airview - Wastewater | 2021-03-03 | 1581 | AV.5
Midwest Water Operations LLC | 1055 | Airview - Wastewater | 2019-11-30 | 1545 | AV.5
Midwest Water Operations LLC | 1429 | Airview - Wastewater | 2020-04-01 | 1281.03 | AV.5
Midwest Water Operations LLC | 1230 | Airview - Wastewater | 2020-02-28 | 1013.19 | AV.5
Midwest Water Operations LLC | 1383 | Airview - Wastewater | 2020-03-31 | 615 | AV.5
Midwest Water Operations LLC | 1165 | Airview - Wastewater | 2020-01-31 | 210 | AV.5
Midwest Water Operations LLC | 1008 | Airview - Wastewater | 2019-10-31 | 2218.33 | AV.6
TNT Technologies Inc | 1340 | Airview - Wastewater | 2020-07-30 | 1836.86 | AV.6
Midwest Water Operations LLC | 1575 | Airview - Wastewater | 2020-06-01 | 1241.03 | AV.6
Midwest Water Operations LLC | 1165 | Airview - Wastewater | 2020-01-31 | 867.54 | AV.6
Midwest Water Operations LLC | 794 | Airview - Wastewater | 2020-08-31 | 665 | AV.6
Midwest Water Operations LLC | Pay App 2- BG | Airview - Wastewater | 2020-12-31 | 402 | AV.6
Midwest Water Operations LLC | 1479 | Airview - Wastewater | 2020-05-01 | 3583.88 | AV.7
Midwest Water Operations LLC | 1008 | Airview - Wastewater | 2019-10-31 | 3292.49 | AV.7
Midwest Water Operations LLC | 1230 | Airview - Wastewater | 2020-02-28 | 520 | AV.7
Midwest Water Operations LLC | 1383 | Airview - Wastewater | 2020-03-31 | 335 | AV.7
Midwest Water Operations LLC | BG-Pay App #4 | Airview - Wastewater | 2021-02-28 | 5000 | AV.8
Midwest Water Operations LLC | 1350 | Airview - Wastewater | 2020-03-31 | 317.5 | AV.8
21 Design Group Inc. | 3712 | Airview - Wastewater | 2019-10-31 | 9575.09 | AV.9
Midwest Water Operations LLC | 1109 | Brocklyn - Wastewater | 2019-12-31 | 6392.6 | BR.1
Midwest Water Operations LLC | 1481 | Brocklyn - Wastewater | 2020-05-01 | 5363.84 | BR.1
Midwest Water Operations LLC | Pay App 2- BG | Brocklyn - Wastewater | 2020-12-31 | 422 | BR.1
21 Design Group Inc. | 4921 | Brocklyn - Wastewater | 2020-04-01 | 130 | BR.1
Midwest Water Operations LLC | 1009 | Brocklyn - Wastewater | 2019-10-31 | 96.67 | BR.1
Midwest Water Operations LLC | 902 | Brocklyn - Wastewater | 2020-08-31 | 204058.54 | BR.2
Midwest Water Operations LLC | 1693 | Brocklyn - Wastewater | 2020-08-01 | 25270.05 | BR.2
Midwest Water Operations LLC | Pay App 3-BG | Brocklyn - Wastewater | 2021-02-01 | 1619 | BR.3
Midwest Water Operations LLC | 1694 | Brocklyn - Wastewater | 2020-08-01 | 1050 | BR.3
Midwest Water Operations, LLC | 740 | Brocklyn - Wastewater | 2019-07-31 | 270 | BR.3
Midwest Water Operations LLC | 795 | Brocklyn - Wastewater | 2020-08-01 | 7505.46 | BR.4
Midwest Water Operations LLC | 1056 | Brocklyn - Wastewater | 2019-11-30 | 1565 | BR.4
TNT Technologies Inc | 1662 | Brocklyn - Wastewater | 2021-03-24 | 1220 | BR.4
21 Design Group Inc. | 2953 | Brocklyn - Wastewater | 2019-07-31 | 7674.24 | BR.5
Midwest Water Operations LLC | 916 | Center Ridge - Water | 2020-09-01 | 8724.22 | CR1.1
Midwest Water Operations LLC | 1667 | Center Ridge - Water | 2020-11-01 | 6513.2 | CR1.1
Midwest Water Operations LLC | 1699 | Center Ridge - Water | 2020-08-01 | 5724.32 | CR1.1
Midwest Water Operations LLC | 1437 | Center Ridge - Water | 2020-10-01 | 1842.4 | CR1.1
Midwest Water Operations LLC | 1586 | Center Ridge - Water | 2020-07-01 | 1610 | CR1.1
Midwest Water Operations LLC | 1585 | Center Ridge - Water | 2020-06-01 | 700 | CR1.1
Midwest Water Operations LLC | 1583 | Center Ridge - Water | 2020-06-01 | 490 | CR1.1
Midwest Water Operations LLC | 1668 | Center Ridge - Water | 2020-11-01 | 280 | CR1.1
Midwest Water Operations LLC | BG-Pay App #5 | Center Ridge - Water | 2021-04-01 | 103 | CR1.1
Midwest Water Operations LLC | 2470 | Center Ridge - Water | 2021-02-01 | 770 | CR1.2
Midwest Water Operations LLC | Pay App 2- BG | Center Ridge - Water | 2020-12-31 | 522 | CR1.2
Midwest Water Operations LLC | 917 | Center Ridge - Water | 2020-09-01 | 5757.73 | CR1.3
Hawkins Inc. | 4746979 | Center Ridge - Water | 2020-07-02 | 1674.8 | CR1.3
Hawkins Inc. | 4761563 | Center Ridge - Water | 2020-07-24 | 662.71 | CR1.3
Midwest Water Operations LLC | 1700 | Center Ridge - Water | 2020-08-01 | 4603.51 | CR1.4
Midwest Water Operations LLC | 801 | Center Ridge - Water | 2020-08-01 | 20618.39 | CR1.5
Midwest Water Operations LLC | 802 | Center Ridge - Water | 2020-08-01 | 1373.93 | CR1.6
Hawkins Inc. | 4869850 | Center Ridge - Water | 2021-01-26 | 714.91 | CR1.6
Midwest Water Operations LLC | 804 | Center Ridge 2 - Water | 2020-08-01 | 17020 | CR2.1
Midwest Water Operations LLC | Pay App 2- BG | Center Ridge 2 - Water | 2020-12-31 | 7908 | CR2.1
Midwest Water Operations LLC | 1702 | Center Ridge 2 - Water | 2020-08-01 | 4865 | CR2.1
Midwest Water Operations LLC | 2153 | Center Ridge 2 - Water | 2020-12-31 | 2338.85 | CR2.1
Midwest Water Operations LLC | 919 | Center Ridge 2 - Water | 2020-09-01 | 1886.74 | CR2.1
Midwest Water Operations LLC | 1439 | Center Ridge 2 - Water | 2020-10-01 | 150 | CR2.1
Midwest Water Operations LLC | Pay App 2- BG | Center Ridge 2 - Water | 2020-12-31 | 8814 | CR2.2
Midwest Water Operations LLC | 1701 | Center Ridge 2 - Water | 2020-08-01 | 5200.76 | CR2.2
Midwest Water Operations LLC | Pay App 2- BG | Center Ridge 2 - Water | 2020-12-31 | 5000 | CR2.2
Midwest Water Operations LLC | Pay App 2- BG | Center Ridge 2 - Water | 2020-12-31 | 5000 | CR2.2
Midwest Water Operations LLC | 918 | Center Ridge 2 - Water | 2020-09-01 | 4908.47 | CR2.2
Midwest Water Operations LLC | BG Pay App-1 | Center Ridge 2 - Water | 2020-12-01 | 186 | CR2.2
Midwest Water Operations LLC | 1438 | Center Ridge 2 - Water | 2020-10-01 | 3643.93 | CR2.3
Midwest Water Operations LLC | BG-Pay App #5 | Center Ridge 2 - Water | 2021-04-01 | 2347 | CR2.4
Midwest Water Operations LLC | Pay App 3-BG | Center Ridge 2 - Water | 2021-02-01 | 2616 | CR2.5
Midwest Water Operations LLC | 2471 | Center Ridge 2 - Water | 2021-02-01 | 2475.38 | CR2.5
Midwest Water Operations LLC | 1669 | Center Ridge 2 - Water | 2020-11-01 | 2457.75 | CR2.5
Midwest Water Operations LLC | 803 | Center Ridge 2 - Water | 2020-08-01 | 15918.54 | CR2.6
Midwest Water Operations LLC | 803 | Center Ridge 2 - Water | 2020-08-01 | 15918.53 | CR2.7
Midwest Water Operations LLC | BG Pay App-1 | Center Ridge 3 - Water | 2020-12-01 | 2983 | CR3.1
Midwest Water Operations LLC | BG-Pay App #5 | Center Ridge 3 - Water | 2021-04-01 | 690 | CR3.1
Midwest Water Operations LLC | Pay App 3-BG | Center Ridge 3 - Water | 2021-02-01 | 21364 | CR3.2
Midwest Water Operations LLC | Pay App 2- BG | Center Ridge 3 - Water | 2020-12-31 | 9607 | CR3.2
Midwest Water Operations LLC | 920 | Center Ridge 3 - Water | 2020-09-01 | 4938.86 | CR3.2
Midwest Water Operations LLC | 1704 | Center Ridge 3 - Water | 2020-08-01 | 3465 | CR3.2
Midwest Water Operations LLC | 1703 | Center Ridge 3 - Water | 2020-08-01 | 3376.88 | CR3.2
Midwest Water Operations LLC | 1440 | Center Ridge 3 - Water | 2020-10-01 | 2033.56 | CR3.2
Midwest Water Operations LLC | BG-Pay App #5 | Center Ridge 3 - Water | 2021-04-01 | 1075 | CR3.2
Asher Construction Management, LLC | CM001-BG | Center Ridge 3 - Water | 2020-12-01 | 501.69 | CR3.2
Asher Construction Management, LLC | ACM003 | Center Ridge 3 - Water | 2021-03-01 | 260 | CR3.2
Midwest Water Operations LLC | 806 | Center Ridge 3 - Water | 2020-08-01 | 3047.64 | CR3.3
Midwest Water Operations LLC | 921 | Center Ridge 3 - Water | 2020-09-01 | 2665 | CR3.3
Midwest Water Operations LLC | 1441 | Center Ridge 3 - Water | 2020-10-01 | 140 | CR3.3
Midwest Water Operations LLC | BG-Pay App #4 | Center Ridge 3 - Water | 2021-02-28 | 2832 | CR3.4
Midwest Water Operations LLC | 1671 | Center Ridge 3 - Water | 2020-11-01 | 257.5 | CR3.5
Midwest Water Operations LLC | 805 | Center Ridge 3 - Water | 2020-08-01 | 10143.09 | CR3.6
Midwest Water Operations LLC | 922 | Center Ridge 4 - Water | 2020-09-01 | 8110 | CR4.1
Midwest Water Operations LLC | 1442 | Center Ridge 4 - Water | 2020-10-01 | 3739.57 | CR4.1
Midwest Water Operations LLC | 1673 | Center Ridge 4 - Water | 2020-11-01 | 3312.97 | CR4.1
Midwest Water Operations LLC | 2155 | Center Ridge 4 - Water | 2020-12-31 | 3376.98 | CR4.2
Midwest Water Operations LLC | BG-Pay App #4 | Center Ridge 4 - Water | 2021-02-28 | 1569 | CR4.3
Midwest Water Operations LLC | 1705 | Center Ridge 4 - Water | 2020-08-01 | 9549.2 | CR4.4
Midwest Water Operations LLC | 1706 | Center Ridge 4 - Water | 2020-08-01 | 2201.56 | CR4.4
Midwest Water Operations LLC | 807 | Center Ridge 4 - Water | 2020-08-01 | 2101.95 | CR4.6
Midwest Water Operations LLC | BG Pay App-1 | Center Ridge 4 - Water | 2020-12-01 | 6577 | CR4.7
Midwest Water Operations LLC | BG-Pay App #5 | Center Ridge 4 - Water | 2021-04-01 | 5550 | CR4.7
Midwest Water Operations LLC | 807 | Center Ridge 4 - Water | 2020-08-01 | 3105 | CR4.7
Midwest Water Operations LLC | 808 | Center Ridge 4 - Water | 2020-08-01 | 395.73 | CR4.7
Midwest Water Operations LLC | 1674 | Center Ridge 4 - Water | 2020-11-01 | 140 | CR4.7
Midwest Water Operations LLC | 1707 | Fox Run - Wastewater | 2020-08-01 | 5420 | FR.1
| 1707 | Fox Run - Wastewater | 2020-08-01 | 4610 | FR.1
Midwest Water Operations LLC | 1110 | Fox Run - Wastewater | 2019-12-31 | 2180 | FR.1
Midwest Water Operations LLC | 1433 | Fox Run - Wastewater | 2020-04-01 | 109.99 | FR.1
Midwest Water Operations LLC | 1386 | Fox Run - Wastewater | 2020-03-31 | 12658.06 | FR.10
Midwest Water Operations LLC | 1707 | Fox Run - Wastewater | 2020-08-01 | 4936.52 | FR.10
Midwest Water Operations LLC | 1707 | Fox Run - Wastewater | 2020-08-01 | 3990 | FR.10
Midwest Water Operations LLC | 2156 | Fox Run - Wastewater | 2020-12-31 | 2343 | FR.10
Midwest Water Operations LLC | 1110 | Fox Run - Wastewater | 2019-12-31 | 1258.91 | FR.10
Midwest Water Operations LLC | 1010 | Fox Run - Wastewater | 2019-10-31 | 522.58 | FR.10
Midwest Water Operations LLC | 924 | Fox Run - Wastewater | 2020-09-01 | 447.5 | FR.10
Midwest Water Operations LLC | 1057 | Fox Run - Wastewater | 2019-11-30 | 391.23 | FR.10
Midwest Water Operations LLC | 925 | Fox Run - Wastewater | 2020-09-01 | 140 | FR.10
21 Design Group Inc. | 3714 | Fox Run - Wastewater | 2019-10-31 | 7733.33 | FR.11
Midwest Water Operations LLC | 1234 | Fox Run - Wastewater | 2020-02-28 | 5863.42 | FR.12
Midwest Water Operations LLC | 1678 | Fox Run - Wastewater | 2020-06-30 | 27825 | FR.2
Midwest Water Operations LLC | 1110 | Fox Run - Wastewater | 2019-12-31 | 13873.87 | FR.2
Midwest Water Operations LLC | 1057 | Fox Run - Wastewater | 2019-11-30 | 4018.27 | FR.2
Midwest Water Operations LLC | 1234 | Fox Run - Wastewater | 2020-02-28 | 861.92 | FR.2
Midwest Water Operations LLC | 1234 | Fox Run - Wastewater | 2020-02-28 | 839.02 | FR.2
Midwest Water Operations LLC | 964 | Fox Run - Wastewater | 2019-10-01 | 620 | FR.2
Midwest Water Operations LLC | 1010 | Fox Run - Wastewater | 2019-10-31 | 3144.55 | FR.3
Midwest Water Operations LLC | 1234 | Fox Run - Wastewater | 2020-02-28 | 1235 | FR.3
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 1044.01 | FR.3
Midwest Water Operations LLC | 1010 | Fox Run - Wastewater | 2019-10-31 | 3144.55 | FR.4
Midwest Water Operations LLC | 1234 | Fox Run - Wastewater | 2020-02-28 | 1235 | FR.4
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 1044 | FR.4
Midwest Water Operations LLC | 1588 | Fox Run - Wastewater | 2020-06-01 | 6829.69 | FR.5
Midwest Water Operations LLC | 1110 | Fox Run - Wastewater | 2019-12-31 | 4359.71 | FR.5
Midwest Water Operations LLC | 10228 | Fox Run - Wastewater | 2019-08-31 | 4133 | FR.6
Midwest Water Operations LLC | Pay App 3-BG | Fox Run - Wastewater | 2021-02-01 | 2552 | FR.6
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 623.35 | FR.6
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 235 | FR.6
Midwest Water Operations LLC | 1057 | Fox Run - Wastewater | 2019-11-30 | 4668.11 | FR.8
Midwest Water Operations LLC | 1386 | Fox Run - Wastewater | 2020-03-31 | 4396.41 | FR.8
Midwest Water Operations LLC | 1234 | Fox Run - Wastewater | 2020-02-28 | 2071.1 | FR.8
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 1603.03 | FR.8
Midwest Water Operations LLC | 1587 | Fox Run - Wastewater | 2020-06-01 | 1385 | FR.8
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 1297.68 | FR.8
Midwest Water Operations LLC | 1167 | Fox Run - Wastewater | 2020-01-31 | 914.86 | FR.8
Midwest Water Operations LLC | 809 | Fox Run - Wastewater | 2020-08-01 | 10283.59 | FR.9
Midwest Water Operations LLC | 1057 | Fox Run - Wastewater | 2019-11-30 | 2265.63 | FR.9
Midwest Water Operations LLC | 1110 | Fox Run - Wastewater | 2019-12-31 | 1145 | FR.9
Midwest Water Operations LLC | 1010 | Fox Run - Wastewater | 2019-10-31 | 357.83 | FR.9
Midwest Water Operations LLC | 1677 | Golden Acres - Wastewater | 2020-11-01 | 5810 | GA.1
Midwest Water Operations LLC | 1446 | Golden Acres - Wastewater | 2020-10-01 | 3198.69 | GA.1
Midwest Water Operations LLC | 1168 | Golden Acres - Wastewater | 2020-01-31 | 6447.12 | GA.2
Midwest Water Operations LLC | BG Pay App-1 | Golden Acres - Wastewater | 2020-12-01 | 2845 | GA.2
Midwest Water Operations LLC | 2472 | Golden Acres - Wastewater | 2021-02-01 | 2017.81 | GA.2
Midwest Water Operations LLC | 1709 | Golden Acres - Wastewater | 2020-08-01 | 1494.24 | GA.2
Midwest Water Operations LLC | Pay App 3-BG | Golden Acres - Wastewater | 2021-02-01 | 15 | GA.2
Midwest Water Operations LLC | 1483 | Golden Acres - Wastewater | 2020-05-01 | 8382.06 | GA.3
Midwest Water Operations LLC | 1011 | Golden Acres - Wastewater | 2019-10-31 | 6371.0995 | GA.3
Midwest Water Operations LLC | 1235 | Golden Acres - Wastewater | 2020-02-28 | 2454.71 | GA.3
Midwest Water Operations LLC | 1387 | Golden Acres - Wastewater | 2020-03-31 | 11651.2 | GA.4
Midwest Water Operations LLC | 1235 | Golden Acres - Wastewater | 2020-02-28 | 6107.9295 | GA.4
Midwest Water Operations LLC | 926 | Golden Acres - Wastewater | 2020-09-01 | 226.87 | GA.5
21 Design Group Inc. | 6926 | Golden Acres - Wastewater | 2020-12-01 | 1545 | GA.6
Midwest Water Operations LLC | 1447 | Golden Acres - Wastewater | 2020-10-01 | 500 | GA.6
Midwest Water Operations LLC | BG-Pay App #5 | Golden Acres - Wastewater | 2021-04-01 | 225 | GA.6
21 Design Group Inc. | 3198 | Golden Acres - Wastewater | 2019-08-31 | 5316.28 | GA.7
Midwest Water Operations LLC | 1449 | Great Oaks - Wastewater | 2020-10-01 | 3480 | GO.1
Midwest Water Operations LLC | 928 | Great Oaks - Wastewater | 2020-09-01 | 2335 | GO.1
Midwest Water Operations LLC | 1059 | Great Oaks - Wastewater | 2019-11-30 | 1112.84 | GO.1
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 2100 | GO.10
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 1050 | GO.10
Midwest Water Operations LLC | 1112 | Great Oaks - Wastewater | 2019-12-31 | 1012.5 | GO.10
Midwest Water Operations LLC | 1112 | Great Oaks - Wastewater | 2019-12-31 | 8225.29 | GO.2
Midwest Water Operations LLC | 1448 | Great Oaks - Wastewater | 2020-10-01 | 4987.96 | GO.2
Midwest Water Operations LLC | 1169 | Great Oaks - Wastewater | 2020-01-31 | 2676.49 | GO.2
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 1575 | GO.2
Midwest Water Operations LLC | 1237 | Great Oaks - Wastewater | 2020-03-01 | 1200 | GO.2
Midwest Water Operations LLC | 1012 | Great Oaks - Wastewater | 2019-10-31 | 883.49 | GO.2
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 435 | GO.2
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 335 | GO.2
Midwest Water Operations LLC | 956 | Great Oaks - Wastewater | 2019-08-31 | 4133 | GO.3
Midwest Water Operations LLC | 1012 | Great Oaks - Wastewater | 2019-10-31 | 4019.9 | GO.3
Midwest Water Operations LLC | 1589 | Great Oaks - Wastewater | 2020-06-01 | 3296.38 | GO.3
Midwest Water Operations LLC | 1112 | Great Oaks - Wastewater | 2019-12-31 | 1350 | GO.3
Midwest Water Operations LLC | 1388 | Great Oaks - Wastewater | 2020-03-31 | 10211.82 | GO.4
Midwest Water Operations LLC | 1388 | Great Oaks - Wastewater | 2020-03-31 | 6792.7 | GO.4
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 1013.54 | GO.4
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 900 | GO.4
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 183.75 | GO.4
Midwest Water Operations LLC | 1436 | Great Oaks - Wastewater | 2020-04-01 | 9541.07 | GO.5
Midwest Water Operations LLC | 1237 | Great Oaks - Wastewater | 2020-03-01 | 6567.95 | GO.6
Midwest Water Operations LLC | 1388 | Great Oaks - Wastewater | 2020-03-31 | 1141.67 | GO.6
Midwest Water Operations LLC | 1484 | Great Oaks - Wastewater | 2020-05-01 | 8034.64 | GO.7
Midwest Water Operations LLC | 1711 | Great Oaks - Wastewater | 2020-08-01 | 7786.81 | GO.7
Midwest Water Operations LLC | 1589 | Great Oaks - Wastewater | 2020-06-01 | 4514.22 | GO.7
Midwest Water Operations LLC | BG Pay App-1 | Great Oaks - Wastewater | 2020-12-01 | 1189 | GO.8
Midwest Water Operations LLC | Pay App 2- BG | Great Oaks - Wastewater | 2020-12-31 | 1032 | GO.8
21 Design Group Inc. | 4923 | Great Oaks - Wastewater | 2020-04-01 | 1186.25 | GO.9
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 6771.76 | KW.1
Midwest Water Operations LLC | 1113 | Kingswood - Wastewater | 2019-12-31 | 6424.92 | KW.1
Midwest Water Operations LLC | 1060 | Kingswood - Wastewater | 2019-11-30 | 3342.19 | KW.1
TNT Technologies Inc | 1524 | Kingswood - Wastewater | 2020-12-30 | 1378.74 | KW.1
Midwest Water Operations LLC | 1113 | Kingswood - Wastewater | 2019-12-31 | 908.06 | KW.1
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 245 | kw.1
Midwest Water Operations LLC | 1013 | Kingswood - Wastewater | 2019-10-31 | 6256.09 | KW.2
Midwest Water Operations LLC | BG-Pay App #4 | Kingswood - Wastewater | 2021-02-28 | 5551 | KW.2
Midwest Water Operations LLC | BG-Pay App #5 | Kingswood - Wastewater | 2021-04-01 | 2410 | KW.2
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 453.24 | KW.2
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 335 | KW.2
TNT Technologies Inc | 1606 | Kingswood - Wastewater | 2021-02-01 | 6588.5 | KW.3
Midwest Water Operations LLC | 930 | Kingswood - Wastewater | 2020-09-01 | 4224.14 | KW.3
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 2730 | KW.3
Midwest Water Operations LLC | 1113 | Kingswood - Wastewater | 2019-12-31 | 872.33 | KW.3
Midwest Water Operations LLC | 1591 | Kingswood - Wastewater | 2020-06-01 | 700 | KW.3
Midwest Water Operations LLC | 1060 | Kingswood - Wastewater | 2019-11-30 | 3776.21 | KW.4
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 1750.63 | KW.4
Midwest Water Operations LLC | 1170 | Kingswood - Wastewater | 2020-01-31 | 805 | KW.4
Midwest Water Operations LLC | BG Pay App-1 | Kingswood - Wastewater | 2020-12-01 | 410 | KW.4
Hawkins Inc. | 4780003 | Kingswood - Wastewater | 2020-08-20 | 399.93 | KW.4
Midwest Water Operations LLC | Pay App 2- BG | Kingswood - Wastewater | 2020-12-31 | 204 | KW.4
21 Design Group Inc. | 3716 | Kingswood - Wastewater | 2019-10-31 | 9815.24 | KW.5
Midwest Water Operations LLC | 1389 | Kingswood - Wastewater | 2020-03-31 | 770 | KW.5
Midwest Water Operations LLC | 1390 | Lake Columbia - Wastewater | 2020-03-31 | 935 | LC.1
Midwest Water Operations LLC | 1241 | Lake Columbia - Wastewater | 2020-02-28 | 523.52 | LC.1
Midwest Water Operations LLC | 1171 | Lake Columbia - Wastewater | 2020-01-31 | 1554.28 | LC.2
Midwest Water Operations LLC | 1714 | Lake Columbia - Wastewater | 2020-08-01 | 1310 | LC.2
Midwest Water Operations LLC | 1241 | Lake Columbia - Wastewater | 2020-02-28 | 465.13 | LC.2
Midwest Water Operations LLC | 1114 | Lake Columbia - Wastewater | 2019-12-31 | 3657.21 | LC.3
Midwest Water Operations LLC | 1390 | Lake Columbia - Wastewater | 2020-03-31 | 770 | LC.3
Midwest Water Operations LLC | 1171 | Lake Columbia - Wastewater | 2020-01-31 | 522.61 | LC.3
Midwest Water Operations LLC | 1114 | Lake Columbia - Wastewater | 2019-12-31 | 222.55 | LC.3
Midwest Water Operations LLC | 1390 | Lake Columbia - Wastewater | 2020-03-31 | 7326.08 | LC.4
Midwest Water Operations LLC | 1241 | Lake Columbia - Wastewater | 2020-02-28 | 2670.86 | LC.4
Midwest Water Operations LLC | 1439 | Lake Columbia - Wastewater | 2020-04-01 | 1365 | lc.4
Midwest Water Operations LLC | 1171 | Lake Columbia - Wastewater | 2020-01-31 | 140 | LC.4
Midwest Water Operations LLC | 1487 | Lake Columbia - Wastewater | 2020-05-01 | 27858.69 | LC.5
Midwest Water Operations LLC | 1061 | Lake Columbia - Wastewater | 2019-11-30 | 2563.92 | LC.5
Midwest Water Operations LLC | 1593 | Lake Columbia - Wastewater | 2020-06-01 | 29223.87 | LC.6
Midwest Water Operations LLC | 1061 | Lake Columbia - Wastewater | 2019-11-30 | 4014.37 | LC.6
Midwest Water Operations LLC | 1241 | Lake Columbia - Wastewater | 2020-02-28 | 2574.35 | LC.6
Midwest Water Operations LLC | 816 | Lake Columbia - Wastewater | 2020-08-01 | 2448.52 | LC.6
Midwest Water Operations LLC | 1390 | Lake Columbia - Wastewater | 2020-03-31 | 2080 | LC.6
Midwest Water Operations LLC | 1171 | Lake Columbia - Wastewater | 2020-01-31 | 843.06 | LC.6
Midwest Water Operations LLC | 1451 | Lake Columbia - Wastewater | 2020-10-01 | 6185.14 | LC.7
Midwest Water Operations LLC | 1488 | Lake Columbia - Wastewater | 2020-05-01 | 595 | LC.7
Midwest Water Operations LLC | Pay App 2- BG | Lake Columbia - Wastewater | 2020-12-31 | 254 | LC.7
Midwest Water Operations LLC | 1452 | Lake Columbia - Wastewater | 2020-10-01 | 140 | LC.7
21 Design Group Inc. | 3713 | Lake Columbia - Wastewater | 2019-10-31 | 6362.18 | LC.8
Midwest Water Operations LLC | BG Pay App-1 | LH Treatment - Wastewater | 2020-12-01 | 9208 | LH.1
Midwest Water Operations LLC | 1490 | LH Treatment - Wastewater | 2020-05-01 | 1330 | LH.1
Midwest Water Operations LLC | 1391 | LH Treatment - Wastewater | 2020-03-31 | 1040 | LH.1
Midwest Water Operations LLC | 1172 | LH Treatment - Wastewater | 2020-01-31 | 607.65 | LH.1
Midwest Water Operations LLC | 1062 | LH Treatment - Wastewater | 2019-11-30 | 310 | LH.1
Midwest Water Operations LLC | 1391 | LH Treatment - Wastewater | 2020-03-31 | 250 | LH.1
Midwest Water Operations LLC | 1115 | LH Treatment - Wastewater | 2019-12-31 | 245 | LH.1
Midwest Water Operations LLC | 818 | LH Treatment - Wastewater | 2020-08-31 | 100 | LH.1
Midwest Water Operations LLC | 1391 | LH Treatment - Wastewater | 2020-03-31 | 3284.16 | LH.2
Midwest Water Operations LLC | 1015 | LH Treatment - Wastewater | 2019-10-31 | 3087.75 | LH.2
Midwest Water Operations LLC | 1243 | LH Treatment - Wastewater | 2020-02-28 | 900 | LH.2
Midwest Water Operations LLC | 1595 | LH Treatment - Wastewater | 2020-06-01 | 435 | LH.2
Midwest Water Operations LLC | BG-Pay App #5 | LH Treatment - Wastewater | 2021-04-01 | 3335 | LH.3
Midwest Water Operations LLC | 1243 | LH Treatment - Wastewater | 2020-02-28 | 2415.02 | LH.3
Midwest Water Operations LLC | 1454 | LH Treatment - Wastewater | 2020-10-01 | 420 | LH.3
Midwest Water Operations LLC | 1716 | LH Treatment - Wastewater | 2020-08-31 | 280 | LH.3
Midwest Water Operations LLC | Inv MWW 818 | LH Treatment - Wastewater | 2020-08-31 | 100 | LH.3
Midwest Water Operations LLC | 1683 | LH Treatment - Wastewater | 2020-11-01 | 18729.43 | LH.4
21 Design Group Inc. | 3715 | LH Treatment - Wastewater | 2019-10-31 | 13402.96 | LH.4
Midwest Water Operations LLC | 1243 | LH Treatment - Wastewater | 2020-02-28 | 440 | LH.4
Midwest Water Operations LLC | 1717 | Persimmon Ridge - Wastewater | 2020-08-01 | 27414.55 | PR.1
Midwest Water Operations, LLC | 542 | Persimmon Ridge - Wastewater | 2019-02-28 | 1480.5 | PR.1
Midwest Water Operations LLC | 1597 | Persimmon Ridge - Wastewater | 2020-06-01 | 13125.31 | PR.2
Midwest Water Operations LLC | 819 | Persimmon Ridge - Wastewater | 2020-08-01 | 9892.14 | PR.2
21 Design Group Inc. | 5487 | Persimmon Ridge - Wastewater | 2020-07-01 | 775 | PR.2
Midwest Water Operations LLC | 1173 | Persimmon Ridge - Wastewater | 2020-01-31 | 1356.57 | PR.3
Midwest Water Operations LLC | 1173 | Persimmon Ridge - Wastewater | 2019-12-31 | 309.44 | PR.3
Midwest Water Operations LLC | 1016 | Persimmon Ridge - Wastewater | 2019-12-31 | 22097.88 | PR.4
Midwest Water Operations LLC | 1245 | Persimmon Ridge - Wastewater | 2020-02-28 | 2668.61 | PR.4
TNT Technologies Inc | 1688 | Persimmon Ridge - Wastewater | 2021-03-31 | 1360 | pr.4
Midwest Water Operations LLC | 1063 | Persimmon Ridge - Wastewater | 2019-11-30 | 825.02 | PR.4
TNT Technologies Inc | 1485 | Persimmon Ridge - Wastewater | 2020-11-11 | 7133.85 | PR.5
TNT Technologies Inc | 1604 | Persimmon Ridge - Wastewater | 2021-02-03 | 5604.01 | PR.5
21 Design Group Inc. | 2477 | Persimmon Ridge - Wastewater | 2019-05-01 | 46087.97 | PR.6
Midwest Water Operations LLC | 1579 | River Bluffs - Wastewater | 2020-06-01 | 18804.75 | RB.1
Midwest Water Operations LLC | 1696 | River Bluffs - Wastewater | 2020-08-01 | 1855 | RB.1
Midwest Water Operations LLC | 1677 | River Bluffs - Wastewater | 2020-06-30 | 7239.75 | RB.2
Midwest Water Operations LLC | 1580 | River Bluffs - Wastewater | 2020-06-01 | 6821.37 | RB.2
TNT Technologies Inc | 1275 | River Bluffs - Wastewater | 2020-05-27 | 6348.5 | RB.2
Midwest Water Operations LLC | 903 | River Bluffs - Wastewater | 2020-08-20 | 5040.24 | RB.2
Midwest Water Operations LLC | 797 | River Bluffs - Wastewater | 2020-08-01 | 11715.55 | RB.3
TNT Technologies Inc | 1653 | River Bluffs - Wastewater | 2021-03-10 | 1280 | RB.3
Midwest Water Operations LLC | 2163 | River Bluffs - Wastewater | 2020-12-31 | 25164.25 | RB.4
Midwest Water Operations LLC | 1663 | River Bluffs - Wastewater | 2020-11-01 | 85507.89 | RB.5
Midwest Water Operations LLC | Pay App 2- BG | River Bluffs - Wastewater | 2020-12-31 | 50334 | RB.5
Midwest Water Operations LLC | BG Pay App-1 | River Bluffs - Wastewater | 2020-12-01 | 25265 | RB.5
Midwest Water Operations LLC | 913 | River Bluffs - Wastewater | 2020-09-01 | 17529.1 | RB.5
Midwest Water Operations LLC | 798 | River Bluffs - Wastewater | 2020-08-01 | 16698.19 | RB.5
TNT Technologies Inc | 1477 | River Bluffs - Wastewater | 2020-11-11 | 15448.18 | RB.5
Midwest Water Operations LLC | Pay App 2- BG | River Bluffs - Wastewater | 2020-12-31 | 7500 | RB.5
Midwest Water Operations LLC | 1433 | River Bluffs - Wastewater | 2020-10-01 | 6856.18 | RB.5
Midwest Water Operations LLC | 1434 | River Bluffs - Wastewater | 2020-10-01 | 6440 | RB.5
Midwest Water Operations LLC | 1695 | River Bluffs - Wastewater | 2020-08-01 | 54162.85 | RB.6
Midwest Water Operations LLC | Pay App 3-BG | River Bluffs - Wastewater | 2021-02-01 | 22396 | RB.6
Midwest Water Operations LLC | BG Pay App-1 | River Bluffs - Wastewater | 2020-12-01 | 10000 | RB.6
Midwest Water Operations LLC | Pay App 2- BG | River Bluffs - Wastewater | 2020-12-31 | 10000 | RB.6
Midwest Water Operations LLC | BG Pay App-1 | River Bluffs - Wastewater | 2020-12-01 | 30500 | RB.7
Midwest Water Operations LLC | Pay App 2- BG | River Bluffs - Wastewater | 2020-12-31 | 4500 | RB.7
Midwest Water Operations LLC | BG-Pay App #5 | River Bluffs - Wastewater | 2021-04-01 | 12958 | RB.8
Midwest Water Operations LLC | Pay App 3-BG | Randview - Wastewater | 2021-02-01 | 6470 | RV.1
Midwest Water Operations LLC | BG-Pay App #4 | Randview - Wastewater | 2021-02-28 | 3000 | RV.1
Midwest Water Operations LLC | 2162 | Randview - Wastewater | 2020-12-31 | 836.1 | RV.1
Asher Construction Management | CM002-BG | Randview - Wastewater | 2021-01-31 | 455 | RV.1
Midwest Water Operations LLC | Pay App 2- BG | Randview - Wastewater | 2020-12-31 | 97 | RV.1
Midwest Water Operations LLC | BG-Pay App #5 | Randview - Wastewater | 2021-04-01 | 75 | RV.1
Midwest Water Operations LLC | 1665 | Timberland - Wastewater | 2020-11-01 | 16156.35 | TM.1
Asher Construction Management, LLC | CM001-BG | Timberland - Wastewater | 2020-12-01 | 1796.76 | TM.1
Midwest Water Operations LLC | 1436 | Timberland - Wastewater | 2020-10-01 | 1060 | TM.1
Asher Construction Management, LLC | ACM003 | Timberland - Wastewater | 2021-03-01 | 988 | TM.1
Midwest Water Operations LLC | 1581 | Timberland - Wastewater | 2020-06-01 | 350 | TM.1
Midwest Water Operations LLC | BG Pay App-1 | Timberland - Wastewater | 2020-12-01 | 137 | TM.1
Midwest Water Operations LLC | 799 | Timberland - Wastewater | 2020-08-01 | 1471.53 | TM.2
Midwest Water Operations LLC | Pay App 3-BG | Timberland - Wastewater | 2021-02-01 | 793 | TM.2
Midwest Water Operations LLC | 904 | Timberland - Wastewater | 2020-08-19 | 3405.35 | TM.3
Midwest Water Operations LLC | 1435 | Timberland - Wastewater | 2020-10-01 | 14339 | TM.4
Midwest Water Operations LLC | 915 | Timberland - Wastewater | 2020-09-01 | 12538 | TM.4
Midwest Water Operations LLC | 1697 | Timberland - Wastewater | 2020-08-01 | 6741.62 | TM.4
Midwest Water Operations LLC | 1581 | Timberland - Wastewater | 2020-06-01 | 5480.41 | TM.4
Midwest Water Operations LLC | 1582 | Timberland - Wastewater | 2020-06-01 | 1085 | TM.4
Midwest Water Operations LLC | 1435 | Timberland - Wastewater | 2020-10-01 | 14339 | TM.5
Midwest Water Operations LLC | 915 | Timberland - Wastewater | 2020-09-01 | 12538 | TM.5
Midwest Water Operations LLC | 3005 | Timberland - Wastewater | 2021-03-01 | 778.17 | TM.5
Midwest Water Operations LLC | 1698 | Timberland - Wastewater | 2020-08-01 | 560 | TM.5
Midwest Water Operations LLC | Pay App 2- BG | Timberland - Wastewater | 2020-12-31 | 106 | TM.6
1968599.239