## Data
KY FAC Request
May 2020 - October 2020
Unit Name | Event Type | Month | Scheduled Hours | Forced Hours | Actual Hours | Event Duration | Event Start | Event End | Description
East Bend 2 | PO | 2020-05-14 01:00 | 247 |  | 247 | 247 | 2020-05-14 01:00 | 2020-05-24 08:00 | Planned outage for Flue Gas Desulphurization (Scrubber) cleaning
East Bend 2 | U1 | 2020-06-01 17:45 |  | 27.25 | 27.25 | 27.25 | 2020-06-01 17:45 | 2020-06-02 21:00 | 2-2 Induced Draft Booster Fan Variable Inlet Vane
East Bend 2 | U1 | 2020-07-25 19:18 |  | 6.7333 | 6.7333 | 6.7333 | 2020-07-25 19:18 | 2020-07-26 02:02 | High furnace pressure swing from slag fall
East Bend 2 | PO | 2020-09-18 17:12 | 1514.7667 |  | 1514.7667 | 1514.7667 | 2020-09-18 17:12 | 2020-11-20 19:58 | 2020 Fall Planned Outage
Woodsdale CT1 | MO | 2020-06-11 10:00 | 3 |  | 3 | 3 | 2020-06-11 10:00 | 2020-06-11 13:00 | STACK INSPECTION
Woodsdale CT1 | MO | 2020-06-23 07:32 | 4.4833 |  | 4.4833 | 4.4833 | 2020-06-23 07:32 | 2020-06-23 12:01 | Stack Repair
Woodsdale CT1 | PO | 2020-09-12 06:00 | 175.25 |  | 175.25 | 175.25 | 2020-09-12 06:00 | 2020-09-19 13:15 | Main NG to plant isolated for modifications
Woodsdale CT1 | U1 | 2020-09-19 13:15 |  | 209.75 | 209.75 | 209.75 | 2020-09-19 13:15 | 2020-09-28 07:00 | Unavailable due to Unit 2 stack repairs
Woodsdale CT1 | MO | 2020-10-16 08:05 | 2.4167 |  | 2.4167 | 2.4167 | 2020-10-16 08:05 | 2020-10-16 10:30 | Hose replacement on #1 Bearing
Woodsdale CT2 | PO | 2020-09-12 06:00 | 156.9167 |  | 156.9167 | 156.9167 | 2020-09-12 06:00 | 2020-09-18 18:55 | Main NG to plant isolated for modifications
Woodsdale CT2 | U1 | 2020-09-18 18:55 |  | 502.3 | 502.3 | 502.3 | 2020-09-18 18:55 | 2020-10-09 17:13 | Stack repairs
Woodsdale CT2 | U1 | 2020-10-13 09:51 |  | 1.15 | 1.15 | 1.15 | 2020-10-13 09:51 | 2020-10-13 11:00 | Took unit offline because of CEMS issue: H2O injection rate exceedance alarm.
Woodsdale CT3 | MO | 2020-05-11 06:00 | 34.8167 |  | 34.8167 | 34.8167 | 2020-05-11 06:00 | 2020-05-12 16:49 | Troubleshoot Combustor Drain
Woodsdale CT3 | SF | 2020-07-03 17:12 |  | 2.0667 | 2.0667 | 2.0667 | 2020-07-03 17:12 | 2020-07-03 19:16 | Remote start. AVR fault unit did not start.
Woodsdale CT3 | MO | 2020-07-23 13:00 | 49.15 |  | 49.15 | 49.15 | 2020-07-23 13:00 | 2020-07-25 14:09 | Replaced rotor bar piston
Woodsdale CT3 | MO | 2020-08-18 06:00 | 14.1667 |  | 14.1667 | 14.1667 | 2020-08-18 06:00 | 2020-08-18 20:10 | STACK INSPECTION
Woodsdale CT3 | PO | 2020-09-12 06:00 | 156.9167 |  | 156.9167 | 156.9167 | 2020-09-12 06:00 | 2020-09-18 18:55 | Main NG to plant isolated for modifications
Woodsdale CT3 | PO | 2020-09-18 18:55 | 502.3 |  | 502.3 | 502.3 | 2020-09-18 18:55 | 2020-10-09 17:13 | Stack repairs
Woodsdale CT4 | MO | 2020-05-11 06:00 | 34.8167 |  | 34.8167 | 34.8167 | 2020-05-11 06:00 | 2020-05-12 16:49 | Troubleshoot Combustor Drain
Woodsdale CT4 | MO | 2020-06-10 09:50 | 1.2167 |  | 1.2167 | 1.2167 | 2020-06-10 09:50 | 2020-06-10 11:03 | Made unavailable to change out #2 Blow Off Valve Regulator
Woodsdale CT4 | SF | 2020-08-14 13:34 |  | 1.7667 | 1.7667 | 1.7667 | 2020-08-14 13:34 | 2020-08-14 15:20 | Sync control issue
Woodsdale CT4 | PO | 2020-09-12 06:00 | 156.9167 |  | 156.9167 | 156.9167 | 2020-09-12 06:00 | 2020-09-18 18:55 | Main NG to plant isolated for modifications
Woodsdale CT4 | PO | 2020-09-18 18:55 | 425.2333 |  | 425.2333 | 425.2333 | 2020-09-18 18:55 | 2020-10-06 12:09 | Stack repairs
Woodsdale CT5 | MO | 2020-07-23 20:20 | 1.0167 |  | 1.0167 | 1.0167 | 2020-07-23 20:20 | 2020-07-23 21:21 | Oil leak
Woodsdale CT5 | PO | 2020-09-12 06:00 | 197.9167 |  | 197.9167 | 197.9167 | 2020-09-12 06:00 | 2020-09-20 11:55 | Main NG to plant isolated for modifications
Woodsdale CT6 | MO | 2020-07-16 07:55 | 1.4333 |  | 1.4333 | 1.4333 | 2020-07-16 07:55 | 2020-07-16 09:21 | Replaced jacking oil motor
Woodsdale CT6 | PO | 2020-09-12 06:00 | 197.4667 |  | 197.4667 | 197.4667 | 2020-09-12 06:00 | 2020-09-20 11:28 | Main NG to plant isolated for modifications
Event Type Legend:
PO | Planned Outage
PE | Planned Outage Extension
MO | Maintenance Outage
ME | Maintenance Outage Extension
U1 | Unplanned (Forced) Outage – Immediate
U2 | Unplanned (Forced) Outage – Delayed
U3 | Unplanned (Forced) Outage – Postponed
SF | Startup Failure