## Sheet1
Stafford Map | Project Name | Street Name | Linear Feet Replaced | Pipe Size | Pipe Material | Est. Cost | Exhibit 2 Number | Street Name | Linear Feet Replaced | Pipe Size | Pipe Material | Est. Cost
A | Fairway Phase I | Appletree Ln | 3100 | 2", 6" | CI | 775000 | Year 1 Project 36 | Appletree Ln - 700 Block | 980 | 2", 6" | CI | 147000
|  | Clayton Ave |  |  |  |  | Year 1 Project 37 | Clayton Ave - 1600 Block | 1644 | 2", 6" | CI | 246600
|  | Courtney Ave |  |  |  |  | Year 2 Project 1 | Courtney Ave - 1600 Block | 1490 | 2", 6" | CI | 223500
|  | Emery Ct |  |  |  |  | Year 2 Project 2 | Emery Ct | 2058 | 2" | CI | 308700
[8 empty] | Courtney Ave - 1600 Block |  | 2", 6" | CI
[8 empty] | Total Linear Feet | 6172 |  | Total Est. Cost | 925800
B | Wyatt Ave | Wyatt Pkwy | 6130 | 2.25", 6" | CI, AC | 1532500
Lindy Ln
Appletree Ln
|  | Johnsdale Dr |  |  |  |  | Year 5 Project 24 | Johnsdale Dr - 800 Block | 552 | 2.25", 6" | CI | 82800
Benwood Dr
[8 empty] | Total Linear Feet | 552 |  | Total Est. Cost | 82800
C | Bluegrass/Highlawn | Bluegrass Ave | 2500 | 2", 4", 6" | CI | 625000
Highlawn Ave
Willowlawn Ave
D | Codell Dr | Codell Dr | 5250 | 2.25", 6", 8" | CI, PVC | 1312500
Elkwood Ct
Elderberry Ct
Timberhill Ct
|  | Mirahill Dr |  |  |  |  | Year 5 Project 17 | Mirahill Dr - 2400 Block | 1042 | 2.25", 6" | CI | 156300
|  | Windwood Ct | [5 empty] | Windwood Ct - 2400 Block
|  | Heaton Ct | [5 empty] | Heaton Ct
[8 empty] | Total Linear Feet | 1042 |  | Total Est. Cost | 156300
E | N Ashland/Aurora | N Ashland Ave | 4000 | 2", 6", 8" | CI, Other | 1000000
Aurora Ave
Hanover Ct
|  | Memory Ln |  |  |  |  | Year 5 Project 31 | Memory Ln - 300 Block | 396 | 2", 6" | CI | 59400
Richmond Ave
[8 empty] | Total Linear Feet | 396 |  | Total Est. Cost | 59400
F | National Ave | National Ave | 3500 | 2", 6" | CI | 875000 | Year 5 Project 33 | National Ave - 700 Block | 1242 | 2", 6" | CI | 186300
|  | Given Ave | [5 empty] | National Ave - 900 Block
Richmond Ave
[8 empty] | Total Linear Feet | 1242 |  | Total Est. Cost | 186300
Stafford Map | Project Name | Street Name | Linear Feet Replaced | Pipe Size | Pipe Material | Est. Cost | Exhibit 2 Number | Street Name | Linear Feet Replaced | Pipe Size | Pipe Material | Est. Cost
G | Whitney/Ash | Whitney Ave | 6600 | 2", 6", 8" | CI | 1650000 | Year 1 Project 2 | Whitney Ave - 900 Block | 1030 | 2", 6" | CI | 154500
Ash St
Michigan St
Elm St
Booker St
Oak St
[8 empty] | Total Linear Feet | 1030 |  | Total Est. Cost | 154500
H | Clays Mill Road Phase II | Clays Mill Rd | 6300 | 2", 6" | CI | 1575000
|  | McCubbing Dr |  |  |  |  | Year 1 Project 33 | McCubbing Dr - 500 Block | 2290 | 2", 6" | CI | 343500
|  | Blue Ash Dr |  |  |  |  | Year 2 Project 3 | Blue Ash Dr - 600 Block | 940 | 2" | CI | 141000
[8 empty] | Total Linear Feet | 3230 |  | Total Est. Cost | 484500
I | Montclair Dr | Montclair Dr | 2200 | 6", 8" | CI, AC | 550000
J | Summit/Kastle | Summit Dr | 2900 | 6" | CI | 725000
Scoville Rd
Eldemere Rd
K | Valley Farm Dr | Costigan Dr | 5400 | 2.25", 6", 8" | CI | 1350000 | Year 4 Project 29 | Costigan Dr - 1600 Block | 3536 | 2.25", 6", 8" | CI | 530400
|  | Leitner Ct | [5 empty] | Leitner Ct - 1900 Block
|  | Bedinger Ct | [5 empty] | Bedinger Ct - 1900 Block
|  | Cobyville Ct | [5 empty] | Cobyville Ct - 1900 Block
|  | Valley Farm Dr and Ct | [5 empty] | Valley Farm Dr - 900 Block
|  | Chris Dr | [5 empty] | Chris Dr - 1900 Block
[8 empty] | Total Linear Feet | 3536 |  | Total Est. Cost | 530400
L | Colchester/Barksdale | Colchester Dr | 3700 | 2.25", 6", 8" | CI | 925000 | Year 3 Project 50 | Colchester Dr - 1800 Block | 2484 | 2.25", 6", 8" | CI | 372600
|  | Feltner Ct | [5 empty] | Feltner Ct
|  | Bowen Ct | [5 empty] | Bowen Ct - 1800 Block
|  | Barksdale Dr | [5 empty] | Barksdale Dr - 1800 Block
Colchester Dr - 1800 Block
[8 empty] | Total Linear Feet | 2484 |  | Total Est. Cost | 372600
M | Campbell Ln | Campbell Ln | 1100 | 2", 3" | CI, PVC | 275000 | Year 5 Project 10 | Campbell Ln - 800 Block | 1184 | 2", 3" | CI, PVC | 177600
[8 empty] | Total Linear Feet | 1184 |  | Total Est. Cost | 177600
N | Westgate/Hamilton Park | Hamilton Park | 3600 | 2", 4", 6" | CI | 900000 | Year 1 Project 7 | Hamilton Park - 200 Block | 978 | 2", 4", 6" | CI | 146700
|  | Westgate Dr |  |  |  |  | Year 5 Project 2 | Westgate Dr - 100 Block | 2022 | 2", 6" | CI | 303300
Leisure Ln
[8 empty] | Total Linear Feet | 3000 |  | Total Est. Cost | 450000
Stafford Map | Project Name | Street Name | Linear Feet Replaced | Pipe Size | Pipe Material | Est. Cost | Exhibit 2 Number | Street Name | Linear Feet Replaced | Pipe Size | Pipe Material | Est. Cost
O | Lancelot Ln | King Arthur Ct | 2470 | 2", 6", 8" | CI | 617500 | Year 3 Project 36 | King Arthur Ct | 1272 | 2", 6" | CI | 190800
|  | King Arthur Dr | [5 empty] | King Arthur Dr - 3400 Block
Lancelot Ln
[8 empty] | Total Linear Feet | 1272 |  | Total Est. Cost | 190800
P | Kilrush/Caywood | Kelsey Ct | 6270 | 2", 2.25", 6", 8" | CI | 1567500 | Year 3 Project 29 | Kelsey Ct | 1694 | 2", 2.25", 8" | CI | 254100
|  | Kelsey Pl | [5 empty] | Kelsey Pl
|  | Yarmouth Ct | [5 empty] | Yarmouth Ct
|  | Kilrush Dr | [5 empty] | Kilrush Dr - 1100 Block
Kelsey Dr
Caywood Dr
Caywood Cir
Carson Dr
Carson Ct
[8 empty] | Total Linear Feet | 1694 |  | Total Est. Cost | 254100
Q | Merrimac/Fogo/Crewe | Fogo Ct | 3440 | 2.25", 6", 8" | CI | 860000 | Year 4 Project 10 | Fogo Ct - 600 Block | 2020 | 2.25", 6" | CI | 303000
|  | Crewe Ct | [5 empty] | Crewe Ct - 600 Block
|  | Merrimac Dr |  |  |  |  | *Note that Year 4 Project 10 includes 4 streets total and does not directly correlate to Map Q.
[8 empty] | Total Linear Feet | 2020 |  | Total Est. Cost | 303000
R | Tisdale/Fraserdale | Fraserdale Ct | 5290 | 2.25", 6", 8" | CI | 1322500 | Year 4 Project 10 | Fraserdale Ct - 3400 Block | 2020 | 2.25", 6" | CI | 303000
|  | Fraserdale Dr |  |  |  |  | *Note that Year 4 Project 10 includes 4 streets total and does not directly correlate to Map R.
Tisdale Ct
Tisdale Dr
[8 empty] | Total Linear Feet | 2020 |  | Total Est. Cost | 303000
S | Montavesta Rd | Montavesta Rd | 4350 | 2", 6", 8" | CI | 1087500 | Year 4 Project 1 | Old Crow Ct - 3100 Block | 1916 | 2", 6" | CI | 287400
|  | Montavesta Ct | [5 empty] | Clair Rd - 3100 Block
|  | Clair Rd | [5 empty] | Montavesta Ct
|  | Old Crow Ct |  |  |  |  | Year 4 Project 11 | Montavesta Rd - 2900 Block | 866 | 2", 6", 8" | CI | 129900
|  | Lookout Cir | [5 empty] | Lookout Cir
[8 empty] | Total Linear Feet | 2782 |  | Total Est. Cost | 417300