## Schedule I1
KY PSC Case No. 2021-00183
Staff 1-25
Schedule I1
Columbia Gas of Kentucky Case No. 2021-00183 Attachment A Construction Projects For 5 years ended December 31, 2020
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
15026616700 | INSTALL CATALYTIC HEATER | - | - | - | - | 0.01441% | 4027.47 | 5466.4506 | -1438.9806 | 2016-01-01 | 2016-12-31 | 2016-01-04 | 2016-01-04 | VARIANCE EXPLANATION NOT REQUIRED
15026572300 | INSTALL 38'-3" PMLP MAIN | - | - | - | - | 0.02518% | 7036.26 | 14065.6284 | -7029.3684 | 2016-01-01 | 2016-12-31 | 2016-01-04 | 2016-01-11 | 7/1/16 NO EXPLANATION REQUIRED IN ACCORDANCE WITH NEW CAPITAL GOVERNACE POL LICY DATED 3/1/16. GES
15026618900 | INSTALL 4" PIF | - | - | - | - | 0.06539% | 18274.93 | 24735.0886 | -6460.1586 | 2016-01-01 | 2016-12-31 | 2016-01-04 | 2016-01-08 | 7/1/16 VARIANCE EXPLANATION - NONE REQUIRED PER CAPITAL GOVERNANCE POLICY D ATED 3/1/16. GES
15026621300 | INSTALL 128' OF 2" PMMP | - | - | - | - | 0.02924% | 8171.22 | 10601.58 | -2430.36 | 2016-01-01 | 2016-12-31 | 2016-01-04 | 2016-01-06 | VARIANCE EXPLANATION NOT REQUIRED
15026574300 | INSTALL 1633' OF 2" PMMP | - | - | - | - | 0.1261% | 35232.52 | 41595.1588 | -6362.6388 | 2016-01-01 | 2016-12-31 | 2015-12-17 | 2016-01-12 | 7/1/16 VARIANCE AMOUNT DOES NOT REQUIRE AN EXPLANATION. GES
15026624700 | INSTALL MI MINI-AT EFC W/MODEM | - | - | - | - | 0.05059% | 14137.37 | 3473.3009 | 10664.0691 | 2016-01-01 | 2016-12-31 | 2016-03-22 | 2016-01-12 | 7/1/16 VARIANCE EXPLANATION - NONE REQUIRED PER CAPITAL GOVERNANCE POLICY D ATED 3/1/16. GES
16026626500 | INSTALL 217' OF 2"PMMP | - | - | - | - | 0.01287% | 3597.43 | 5562.757 | -1965.327 | 2016-01-01 | 2016-12-31 | 2016-01-05 | 2016-01-12 | VARIANCE EXPLANATION NOT REQUIRED
15026569101 | INSTALL 120' OF 12"CSHP MAIN | - | - | - | - | 0.4561% | 127468.59 | 110485.7115 | 16982.8785 | 2016-01-01 | 2016-12-31 | 2015-09-25 | 2016-01-08 | VARIANCE EXPLANATION NOT REQUIRED
15026619100 | INSTALL 125' OF 2" PMMP | - | - | - | - | 0.02988% | 8349.79 | 21872.3 | -13522.51 | 2016-01-01 | 2016-12-31 | 2016-01-12 | 2016-01-18 | 7/1/16 VARIANCE EXPLANATION - NONE REQUIRED PER CAPITAL GOVERNANCE POLICY D ATED 3/1/16. GES
15026622800 | INSTALL 15' OF 2"PMMP W/2"SST | - | - | - | - | 0.04717% | 13181.46 | 23166.8814 | -9985.4214 | 2016-01-01 | 2016-12-31 | 2016-01-11 | 2016-01-13 | 7/1/16 VARIANCE INSUFFICIENT TO REQUIRE AN EXPLNATION IN ACCORDANCE WITH NE W CAPITAL GOVERNANCE POLICY DATED 3/1/16. GES
16026627100 | INSTALL 2"SS FITTING | - | - | - | - | 0.005721% | 1598.71 | 3072.3567 | -1473.6467 | 2016-01-01 | 2016-12-31 | 2016-01-04 | 2016-01-13 | VARIANCE EXPLANATION NOT REQUIRED
15026601700 | NSTALL GROUNDBED | - | - | - | - | 0.06964% | 19462.79 | 9757.0589 | 9705.7311 | 2016-01-01 | 2016-12-31 | 2015-11-03 | 2016-04-11 | INSTALLED 2ND GROUNDBED DESIGNED TO PROTECT 8" BARE STEEL ROAD CROSSING 3 MMO ANDES SPECED 40' APART AND 7' OFF OF MAIN ANODE WIRE RUN INTO JUNCTION BOX FOR DEEP WELL NEW GROUND BED FACILITY 673036 INSTALLED RMU BULLHORN UNIT 673037 04-11-16 1341 JMM INSTALLED 2ND GROUD BED FACILITY 673036 ALL PAPERWORK SUBMITTED TO CAPITOL CLOSE-OUT 04-11-2016 1348 JMM 7/1/16 VARIANCE EXPLANATION - NONE REQUIRED - CAPITAL GOVERNANCE POLICY DAT ED 3/1/16. GES
15026604800 | INSTALL 192' - 2" PM | - | - | - | - | 0.1005% | 28076.81 | 28596.2858 | -519.4758 | 2016-01-01 | 2016-12-31 | 2016-01-07 | 2016-03-02 | VARIANCE EXPLANATION NOT REQUIRED
15026604700 | INSTALL 182' - 2" PM | - | - | - | - | 0.1168% | 32635.37 | 28604.2858 | 4031.0842 | 2016-01-01 | 2016-12-31 | 2016-02-02 | 2016-03-02 | VARIANCE EXPLANATION NOT REQUIRED
15026586300 | INSTALL 160'-4" PMLP | - | - | - | - | 0.1188% | 33208.11 | 16767.6318 | 16440.4782 | 2016-01-01 | 2016-12-31 | 2016-01-05 | 2016-01-27 | 7/1/16 NO EXPLANATION REQUIRED IN ACCORDANCE WITH NEW CAPITAL GOVERNANCE PO LICY DATED 3/1/16. GES
15026583901 | INSTALL 436'-6" PMLP | - | - | - | - | 0.2592% | 72444.17 | 69382.5463 | 3061.6237 | 2016-01-01 | 2016-12-31 | 2016-02-15 | 2016-02-26 | VARIANCE EXPLANATION NOT REQUIRED
15026608201 | INSTALL 392' OF 6" PMLP | - | - | - | - | 0.9878% | 276073.7 | 249063.3127 | 27010.3873 | 2016-01-01 | 2016-12-31 | 2015-11-19 | 2016-02-23 | VARIANCE EXPLANTION NOT REQUIRED SEE PROJECT ID 14-23264. THE ENTIRE PROJECT RETIRED PRIORITY PIPE. MULTIPLE JOB ORDER FOR DIFFERENT STREETS AND MAINS.
15026562600 | INSTALL 1200' OF 4" PMLP | - | - | - | - | 0.8691% | 242885.14 | 211167.7004 | 31717.4396 | 2016-01-01 | 2016-12-31 | 2016-01-05 | 2016-03-18 | THIS PROJECT IS UNDERRUNNING DUE TO THE PAVING COSTS NOT YET BEING APPLIED TO THE JOB ORDER. PENDING PAVING ORDER 16-3961852-00. CSPARKS 7/20/16 OVERRUN EXPLANATION: THIS PROJECT OVERRAN BECAUSE 3600 SF OF 6&2 WAS REQUIR ED TO COMPLETE THE JOB, BUT IT WAS NOT ESTIMATED INITIALLY.
15026568101 | INSTALL 200' OF 2"PMLP MAIN | - | - | - | - | 0.1365% | 38143.85 | 32627.4629 | 5516.3871 | 2016-01-01 | 2016-12-31 | 2016-01-06 | 2016-02-19 | 3/7/16 NO EXPLANATION REQUIRED ON THIS JOB ORDER IN ACCORDANCE WITH NEW CAP ITAL GOVERNANCE POLICY. GES
14026550200 | INSTALL 400' OF 4" PMMP | - | - | - | - | 0.3232% | 90333.59 | 122276.0126 | -31942.4226 | 2016-01-01 | 2016-12-31 | 2015-12-09 | 2016-02-10 | PRACTICE COMMENTS 7/7/16 STILL AWAITING $45,000 IN RESTORATIONS COST TO BE COMPLETED. PAVING HAS NOT BEEN DONE. D.LEMONS 9/16/16 PAVING STILL NOT COMPLETE. D.LEMONS UNDERRUN EXPLANATION: 1600 FEET OF 6&2 WERE ESTIMATED BUT NOT REQUIRED.
15026571400 | INSTALL NEW REG STRUCTURE | - | - | - | - | 0.1942% | 54273.72 | 64363.1255 | -10089.4055 | 2016-01-01 | 2016-12-31 | 2016-02-05 | 2016-02-05 | INSTALLED NEW COMMUNICATIONS BUILDING JOB RAN OVER INTO 2016
15026591100 | INSTALL 5025' OF 2"PMMP MAIN | - | - | - | - | 0.356% | 99488.63 | 93216.7926 | 6271.8374 | 2016-01-01 | 2016-12-31 | 2015-12-03 | 2016-02-26 | VARIANCE EXPLANATION NOT REQUIRED
16026631100 | INSTALL 770'-6" CSHP | - | - | - | - | 2.144% | 599181.36 | 603927.8304 | -4746.4704 | 2016-01-01 | 2016-12-31 | 2016-02-18 | 2016-02-26 | MATERIAL NOTE:6"STEEL PIPE WAS SPECIAL ORDERED ON ORIGINAL JOB 13-0264505-02. THIS COULD NOT BE TRANSFERRED TO JOB SO IT IS SHOWN AS LOCAL PURCHASE 7/5/16 - $448,987.00 OF COST HAS NOT BEEN TRANSFERED FROM VOIDED JO 13-0264 505-02. D.LEMONS
16026628900 | INSTALL 30' OF 4"PMLP MAIN | - | - | - | - | 0.0555% | 15511.61 | 13287.6081 | 2224.0019 | 2016-01-01 | 2016-12-31 | 2016-02-03 | 2016-02-11 | VARIANCE EXPLANATION NOT REQUIRED
15026600500 | INSTALL 250' OF 2"PMMP | - | - | - | - | 0.04787% | 13377 | 9443.1289 | 3933.8711 | 2016-01-01 | 2016-12-31 | 2016-02-11 | 2016-02-26 | VARIANCE EXPLANATION NOT REQUIRED
16026631500 | INSTALL 150'-4"PMMP | - | - | - | - | 0.06991% | 19537.95 | 9921.9074 | 9616.0426 | 2016-01-01 | 2016-12-31 | 2016-02-15 | 2016-02-19 | PER BRIAN JACKSON IN/OUT SERVICE DATE 05/19/2016 IS CORRECT FOR PRESSURE TE ST AND GAS FLOW DATE - USED THIS DATE TO MAP PIPE LINE IN GIS, DGRIFFI 05/18/2016. 7/1/16 VARIANCE EXPLANATION - NONE REQUIRED PER CAPITAL GOVERNANCE POLICY D ATED 3/1/16. GES
15026616901 | INSTALL 292' - 2" PM | - | - | - | - | 0.1889% | 52784.08 | 50631.2656 | 2152.8144 | 2016-01-01 | 2016-12-31 | 2016-02-09 | 2016-03-03 | WEATHER CAUSED JOB TO GO OVER COMMIT DATE
15026618800 | INSTALL RECTIFIER & DEEP WELL | - | - | - | - | 0.2493% | 69678.26 | 67884.57 | 1793.69 | 2016-01-01 | 2016-12-31 | 2015-12-14 | 2016-04-11 | . INSTALLED UNIVERSAL RECTIFIER WITH FAC 660128 INSTALLED 300' DEEP WELL WITH 10 ANODES & 100 BAGS OF COKE FAC 672005 CREATED RT 923598 TO MONITOR BI-MONTHLY READINGS AT RECTIFIER INSTALLED RMU BULLHORN WITH FAC 672007 RECTIFIER WILL MONITOR 11 TEST STATIONS TOTAL IN DOWNTOWN MT. STERLING WILL BE RECTIFIED TEST STATION BOOK 24R 04-11-2016 1118 JMM SUBMITTED ALL NECESSARY PAPERWORK TO CAPITOL CLOSE-OUT TEAM 04-11-2016 1141 JMM
16026626700 | INSTALL 92' OF 2"PMIP | - | - | - | - | 0.05105% | 14267.11 | 13243.6081 | 1023.5019 | 2016-01-01 | 2016-12-31 | 2016-02-25 | 2016-02-29 | VARIANCE EXPLANATION NOT REQUIRED
15026576701 | INSTALL 391-4" PMLP | - | - | - | - | 0.527% | 147294.63 | 93576.2116 | 53718.4184 | 2016-01-01 | 2016-12-31 | 2016-02-26 | 2016-03-14 | 7/1/16 NEW CAPITAL GOVERNANCE PLOICY DOES NOT REQUIRE AN EXPLNATION WITH A VARIANCE OF THIS MAGNITUDE. GES 9/15/16 100' OF ADDITIONAL MAIN INSTALLED ABOVE ESTIMATED. INCREASED LABOR COST BY $1500, MATERIAL BY $1000. RESTORATION INCREASED BY $8000 IN COLD MI X AND $21500 FOR PAVING. PAVING ESTIMATED AT 800 SF, BUT 2157 SF WAS PAID. THIS INCREASED SEGA BY $13000. TOTAL INCREASE OF $45000. D.LEMONS
14026535200 | INSTALL 240'-2" PMMP | - | - | - | - | 0.06912% | 19317.63 | 39849.7152 | -20532.0852 | 2016-01-01 | 2016-12-31 | 2016-02-29 | 2016-03-04 | 7/1/16 VARIANCE EXPLANATION - NONE REQUIRED PER CAPITAL GOVERNANCE POLICY D ATED 3/1/16. GES
15026570100 | INSTALL 1600' OF 2"PMMP MAIN | - | - | - | - | 0.2311% | 64583.96 | 41816.9257 | 22767.0343 | 2016-01-01 | 2016-12-31 | 2016-01-27 | 2016-03-01 | 7/1/16 NO EXPLNATION REQUIRED ON THIS JOB ORDER IN ACCORDNACE WITH NEW CAPI TAL GOVERNANCE POLICY DATED 3/1/16. GES
14026558201 | REPLACE GMB SETTING | - | - | - | - | 0.1488% | 41593.71 | 28475.3909 | 13118.3191 | 2016-01-01 | 2016-12-31 | 2016-02-16 | 2016-03-04 | VARIANCE EXPLANATION NOT REQUIRED REPLACED VALVES
15026614400 | INSTALL 50' OF 6" PMMP BYPASS | - | - | - | - | 0.112% | 31307.81 | 14830.8412 | 16476.9688 | 2016-01-01 | 2016-12-31 | 2015-12-29 | 2016-03-04 | INSTALLED 40'-2"HD PLASTIC, 20' OF MP, 2 - 2" SHORTSTOPP TEE, 1-6" SHORTSTOPP FITTING & 1-8" SHORTSTOP FITTING
15026602201 | INSTALL 100'-6"PMMP | - | - | - | - | 0.1681% | 46987.46 | 37776.2577 | 9211.2023 | 2016-01-01 | 2016-12-31 | 2016-02-22 | 2016-03-22 | VARIANCE EXPLANATION NOT REQUIRED
16026631700 | INSTALL MI WIRELESS | - | - | - | - | 0.03374% | 9430.54 | 21366.1997 | -11935.6597 | 2016-01-01 | 2016-12-31 | 2016-03-09 | 2016-03-09 | VARIANCE EXPLANATION NOT REQUIRED
16026630800 | INSTALL MI-WIRELESS | - | - | - | - | 0.000426% | 119.05 | 21366.1997 | -21247.1497 | 2016-01-01 | 2016-12-31 |  | 2016-03-16 | VARIANCE EXPLANATION NOT REQUIRED
16026627400 | INSTALL 100' OF 2" PMMP | - | - | - | - | 0.02369% | 6619.25 | 29645.3326 | -23026.0826 | 2016-01-01 | 2016-12-31 | 2016-03-14 | 2016-03-14
15026564901 | INSTALL 1523' - 12" CSHP | - | - | - | - | 1.051% | 293835.58 | 314077.848 | -20242.268 | 2016-01-01 | 2016-12-31 | 2016-03-10 | 2016-03-17 | UNDERRUN EXPLANATION - AS OF 7/15/16 THE PIPE HAS NOT BEEN PAID FOR, THUS, NOT SHOWING UP IN WMS OR POWERPLANT RESULTING IN THE OVERRUN (BKS)
15026599800 | INSTALL 1125' OF 2"PMMP MAIN | - | - | - | - | 0.07594% | 21224.25 | 21575.9654 | -351.7154 | 2016-01-01 | 2016-12-31 | 2016-03-14 | 2016-03-17 | VARIANCE EXPLANATION NOT REQUIRED
15026624901 | INSTALL 225' OF 4"PMLP | - | - | - | - | 0.2556% | 71434.21 | 55397.1247 | 16037.0853 | 2016-01-01 | 2016-12-31 | 2016-02-26 | 2016-03-17 | TWALKER/KY 07-25-16: PROJECT SHOWING COST UNDER RUN AT THIS TIME BUT 1100' OF FINAL PAVING COST HAVE NOT HIT JOB ORDER YET.
15026588901 | INSTALL 1150' OF 4" PMMP | - | - | - | - | 0.6947% | 194159.91 | 187499.3925 | 6660.5175 | 2016-01-01 | 2016-12-31 | 2016-01-07 | 2016-03-22 | VARIANCE EXPLANATION NOT REQUIRED
15026618600 | INSTALL 660'-4" PMLP | - | - | - | - | 0.1411% | 39446.15 | 127906.862 | -88460.712 | 2016-01-01 | 2016-12-31 | 2016-02-29 | 2016-03-24 | PROJECT UNDERRUN DUE TO OVER ESTIMATIONOF CONTRACT AND SEGA RATES AS DESCRIBED BELOW. ONCE CONSTRUCTION CREW BEGAN PROJECT THEY WERE ABLE TO LAY THE NEW MAIN OFF THE EDGE OF PAVEMENT, WHICH DID NOT REQUIRE PAVEMENT RESTORATION: ESTIMATED 3300 UNITS OF PAVEMENT RESTORATION AND ONLY 300 WERE CHARGED(VARIANCE OF $42,840).DUE TO A REDUCTION IN PAVEMENT RESTORATION THE AMOUNT OF STONE AND DUST USED DECREASED(VARIANCE OF $25,264). SINCE THE PAVEMENT RESTORATION WAS REDUCED THE SEGA RATES DECREASED.
16026628700 | INSTALL 24'-4" PM&CS | - | - | - | - | 0.2895% | 80900.64 | 61397.2175 | 19503.4225 | 2016-01-01 | 2016-12-31 | 2016-03-07 | 2016-03-21 | VARIANCE EXPLANATION NOT REQUIRED
15026607800 | INSTALL 250' - 2" PM | - | - | - | - | 0.08066% | 22543.12 | 21457.5442 | 1085.5758 | 2016-01-01 | 2016-12-31 | 2016-03-04 | 2016-03-23 | VARIANCE EXPLANATION NOT REQUIRED
16026629900 | INSTALL 140'-4"&6" PMMP | - | - | - | - | 0.3094% | 86477.79 | 85795.9567 | 681.8333 | 2016-01-01 | 2016-12-31 | 2016-02-15 | 2016-03-31 | VARIANCE EXPLANATION NOT REQUIRED
15026599200 | INSTALL 400' OF 4"PMMP | - | - | - | - | 0.1389% | 38817.38 | 48946.0136 | -10128.6336 | 2016-01-01 | 2016-12-31 | 2016-02-15 | 2016-02-25 | VARIANCE EXPLANATION NOT REQUIRED
15026569300 | INSTALL WIRELESS EFC | - | - | - | - | 0.02647% | 7397.62 | 10858.0878 | -3460.4678 | 2016-01-01 | 2016-12-31 | 2016-03-30 | 2016-03-30
15026587801 | INSTALL 2600' OF 2"/4"PMMP | - | - | - | - | 0.7965% | 222598.59 | 149112.2494 | 73486.3406 | 2016-01-01 | 2016-12-31 | 2016-03-17 | 2016-03-30 | THIS JOB WENT PAST THE COMMIT DATE DUE TO SEWER LATERALS NOT BEING LOCATABL E. THIS REQUIRED MY CREW TO OPEN CUT IN THE SIDEWALK INSTEAD OF BORING THE MAIN AS ORIGINALLY PLANNED. TWALKER/KY-09-13-16: JOB OVER RUN DUE TO FACT MAIN WAS INSTALLED OPEN CUT IN THE STREET AND SIDEWALK. STREET CUT TEMP AND PERM REPAIRS ADDED $10000. SIDEWALK AND DRIVEWAY REPAIRS ADDED $15000. ERROSION SEEDING WAS $11000. FINALLY SEGA WAS $19000 HIGHER, MATERIAL $1000 AND COMPANY LABOR $1200 HIGHER THAN ESTIMATE. TWALKER/KY 07-27-17: ADDED LEVEL 2 VARIANCE REPORT TO PROJECT.
15026609000 | INSTALL 100' OF 2" PMIP | - | - | - | - | 0.1547% | 43240.24 | 21145.055 | 22095.185 | 2016-01-01 | 2016-12-31 | 2016-03-22 | 2016-03-30 | PROJECT OVERRUN DUE TO UNDER ESTIMATION OF THE DURATION OF THE PROJECT. CONTRACT UNITS ARE WHAT CAUSED THE OVERRUN, AND ARE DUE TO THE FOLLOWING: PROJECT WAS PLANNED FOR 32 HOURS, BUT TOOK 62.5 WITH A 3 MAN CREW TO COMPLETE ($7686 VARIANCE). THERE WAS NO TIME ESTIMATED FOR A WELD & RIG, BUT 30.5 HOURS WERE CHARGED FOR ONE TIE-IN ($4042 VARIANCE). NO PAVEMENT RESTORATION WAS ESTIMATED BECAUSE THE PROJECT WAS DESIGNED TO BE INSTALLED IN THE GRASS, BUT 25 UNITS OF 6" & 2" WERE CHARGED ($1073 VARIANCE). NO PER DIEM WAS ESTIMATED BUT 10 UNITS WERE CHARGE ($1000 VARIANCE).
16026631300 | INSTALL 3300'-2",4",6" PMMP | - | - | - | - | 2.032% | 567836.15 | 481639.357 | 86196.793 | 2016-01-01 | 2016-12-31 | 2016-02-18 | 2016-04-04 | UNFORSEEN ISSUES AROSE FROM WORKING WITH OTHER, THAT LEAD TO ADDITIONAL MAT ERIALS OF $7000 AND CONTRACT OF $52000 FOR SPECIAL SHORING EQUIPMENT AND LA BOR THAT WERE NOT ESTIMATED. THIS ALSO IMPACTED COMPANY LABOR COST BY $200 00. D.LEMONS 7/19/16
15026578600 | INSTALL 1500' OF 2" PMMP | - | - | - | - | 0.1873% | 52353.59 | 61244.2257 | -8890.6357 | 2016-01-01 | 2016-12-31 | 2016-03-17 | 2016-04-04
16026628500 | INSTALL 50' OF 4"PMLP | - | - | - | - | 0.1934% | 54063.23 | 28864.5913 | 25198.6387 | 2016-01-01 | 2016-12-31 | 2016-03-21 | 2016-04-05 | HAD TO EXTEND PIPE FOOTAGE BECAUSE OF BAD PIPE
16026638900 | INSERT 100' OF 2"PMLP | - | - | - | - | 0.07999% | 22355.27 | 20136.3332 | 2218.9368 | 2016-01-01 | 2016-12-31 | 2016-04-05 | 2016-04-15
16026639100 | INSTALL 300' OF 2"PMMP | - | - | - | - | 0.1242% | 34720.01 | 19642.3332 | 15077.6768 | 2016-01-01 | 2016-12-31 | 2016-04-04 | 2016-04-06
15026613100 | INSTALL 30' - 4" PMMP | - | - | - | - | 0.03223% | 9007.91 | 15032.8731 | -6024.9631 | 2016-01-01 | 2016-12-31 | 2016-04-08 | 2016-04-11
16026641400 | INSTALL NEW REG SETTING VALVES | - | - | - | - | 0.08509% | 23779.98 | 16686.93 | 7093.05 | 2016-01-01 | 2016-12-31 | 2016-04-06 | 2016-04-12 | REPLACED INLET / OUTLET AND BYPASS BLOCK VALVES ON IP SETTING - R-1403
16026655400 | INSTALL 4" SST AT R-1403 | - | - | - | - | 0.004914% | 1373.29 | 4639.2855 | -3265.9955 | 2016-01-01 | 2016-12-31 | 2017-01-04 | 2017-01-04 | INSTALLED 4" SST IN CONJUNCTION WITH JO# 16026641400
16026627000 | INSTALL 1100'-2" PMMP | - | - | - | - | 0.09208% | 25734.2 | 51250.6652 | -25516.4652 | 2016-01-01 | 2016-12-31 | 2016-04-08 | 2016-04-14 | JOB SHORTENED BECAUSE FINAL GRADE HAS NOT BEEN MET
16026641200 | INSTALL 40' OF 2" PMMP | - | - | - | - | 0.01857% | 5189.65 | 11363.7662 | -6174.1162 | 2016-01-01 | 2016-12-31 | 2016-04-14 | 2016-04-28
15026560901 | INSTALL 200' OF 2" PMIP | - | - | - | - | 0.1861% | 52003.37 | 60650.6184 | -8647.2484 | 2016-01-01 | 2016-12-31 | 2016-04-04 | 2016-04-19
16026637900 | INSTALL 485' OF 2"PMMP | - | - | - | - | 0.0491% | 13723.11 | 23557.3332 | -9834.2232 | 2016-01-01 | 2016-12-31 | 2016-04-14 | 2016-04-19
14026521900 | INSTALL 230'-6" WTHP & 10'-12" | - | - | - | - | 0.6157% | 172077.98 | 162626.4189 | 9451.5611 | 2016-01-01 | 2016-12-31 | 2016-03-14 | 2016-04-20
16026635900 | INSTALL 50' OF 4"PMLP MAIN | - | - | - | - | 0.05832% | 16298.08 | 24740.9264 | -8442.8464 | 2016-01-01 | 2016-12-31 | 2016-04-22 | 2016-04-22
16026638700 | INSTALL MI WIRELESS/EFC | - | - | - | - | 0.06196% | 17314.97 | 11497.1666 | 5817.8034 | 2016-01-01 | 2016-12-31 | 2016-03-28 | 2016-04-21
14026548701 | INSTALL 11500' OF 4"/6" PMMP | - | - | - | - | 6.182% | 1727674.97 | 987245.9543 | 740429.0157 | 2016-01-01 | 2016-12-31 | 2016-03-10 | 2016-04-22 | 11/25/15 188653 LARRY BROWN TRAVIS SPENCER 11/30/15 11/25/15 188676 LARRY BROWN WILL TERRELL 11/30/15 12/03/15 188677 LARRY BROWN WILL TERRELL 12/04/15 12/14/15 188678 LARRY BROWN WILL TERRELL 12/16/15 12/19/15 188658 LARRY BROWN WILL TERRELL 12/21/15 01/25/16 188678 EMT//TO CORRECT WILL TERRELL 01/29/16 OVERRUN EXPLANATION: LEVEL 2 BUDGET VARAINCE SUBMITTED AND APPROVED.
15026614100 | INSTALL 60' - 12" CS-HP | - | - | - | - | 1.058% | 295710.54 | 191112.4022 | 104598.1378 | 2016-01-01 | 2016-12-31 | 2016-04-11 | 2016-04-26 | THIS WAS ESTIMATED AS A UNITIZED JOB WHEN IT WAS AN HOURLY JOB THAT TOOK SI GNIFICANTLY LONGER THAN ANTICIPATED RESULTING IN THE OVERRUN. GES
15026623201 | INSTALL 550'-4" PMMP | - | - | - | - | 0.2401% | 67088.49 | 59234.8369 | 7853.6531 | 2016-01-01 | 2016-12-31 | 2016-02-29 | 2016-04-26
15026597600 | INSTALL EFC | - | - | - | - | 0.05276% | 14746.17 | 3979.3698 | 10766.8002 | 2016-01-01 | 2016-12-31 | 2015-10-02 | 2016-05-05
15026613900 | INSTALL 100' - 2" PMMP | - | - | - | - | 0.2062% | 57623.1 | 40270.0136 | 17353.0864 | 2016-01-01 | 2016-12-31 | 2016-04-19 | 2016-05-09
16026645500 | INSTALL 56'-4"PMLP | - | - | - | - | 0.1633% | 45634.07 | 35856.1858 | 9777.8842 | 2016-01-01 | 2016-12-31 | 2016-05-02 | 2016-05-16 | REPLACED MAIN,TESTED NEW MAIN,90LB FOR 1HR,SOAP TESTED CONN POINTS AT OP TIME 0300AM 5-6-16
15026623900 | INSTALL 6800' OF 12" CSHP | - | - | - | - | 3.657% | 1021902.31 | 1922533.7002 | -900631.3902 | 2016-01-01 | 2016-12-31 | 2016-03-02 | 2016-06-02 | ODOR LEVEL REPORT/JUNE/JULY 6/15/2016 - 4630 BOSWORTH LN LEXINGTON KY - JAMIE LYNN - 02 7/5/2016 - 1580 PSIGAH PK FG31 VERSAILLIES KY - JAMIE LYNN - .35 7/5/2016 - 4630 BOSWORTH LN LEXINGTON KY - JAMIE LYNN - .2 THIS PROJECT UNDERRAN DUE TO LESS ROCK BEING ENCOUNTERED THAN EXPECTED. 240 0' ESTIMATED HEAVY ROCK BORE AND ONLY 2327' FT/FT ROCK. NO PADDING REQUIRED AS ESTIMATED. NO EXTRA EQUIPMENT REQUIRED ON SITE AS ESTIMATED. PROJECT DUR ATION SHORTER THAN EXPECTED. CSPARKS 10/28/16
15026605000 | INSTALL NEW GMB SETTING | - | - | - | - | 0.3548% | 99143.39 | 56153.6914 | 42989.6986 | 2016-01-01 | 2016-12-31 | 2016-01-15 | 2016-05-18 | THIS PROJECT OVERRAN DUE TO THE PROJECT DURATION BEING LONGER THAN ESTIMATE D AND THE EQUIPMENT BEING MORE EXPENSIVE THAN ANTICIPATED. CSPARKS 10/28/16
16026640600 | INSTALL 522 OF 4"PMMP | - | - | - | - | 0.1672% | 46723.3 | 44238.7622 | 2484.5378 | 2016-01-01 | 2016-12-31 | 2016-04-27 | 2016-05-16 | COMPLETION DATE EXTENDED DUE TO RAIN NUMEROUS DAY AND HAVING TO DIG IN EXTR EMELY UNSTABLE FILL SOIL.
16026635400 | INSTALL 250' OF 2" PMMP | - | - | - | - | 0.1027% | 28692.44 | 21570.3645 | 7122.0755 | 2016-01-01 | 2016-12-31 | 2016-05-09 | 2016-05-30
16026637400 | INSTALL 300' OF 2"PMMP | - | - | - | - | 0.1771% | 49505.44 | 41438.4165 | 8067.0235 | 2016-01-01 | 2016-12-31 | 2016-05-12 | 2016-05-23
16026630600 | INSTALL 770' OF 2"PMMP | - | - | - | - | 0.366% | 102297.43 | 56907.1827 | 45390.2473 | 2016-01-01 | 2016-12-31 | 2016-05-17 | 2016-05-31 | TWALKER/KY 10-26-16: JOB OVER RUN DUE TO PROJECT PLANNED FOR STANLEY PIPELINE BUT ALL WORK COMPLETED BY TEAM FISHEL. PROJECT HAD ADDITIONAL 750' OF HARD SERVICE REPAIRS WHICH ADDED $40000 WITH TEAM FISHEL PRICES. ALSO SEGA WAS $10000 HIGHER THAN EST AND LAND SERVICES COST $3700 HIGHER DUE TO EASEMENT PROBLEMS WITH LAND OWNER-MACYS. I COULD NOT REVISE PROJECT IN WMS DUE TO UNPAID INVOICES IN WMS.
16026634700 | INSTALL 105' OF 2" PMMP | - | - | - | - | 0.1327% | 37097.69 | 14375.8187 | 22721.8713 | 2016-01-01 | 2016-12-31 | 2016-05-10 | 2016-05-25
16026648200 | INSTALL 35' OF 4"PMMP | - | - | - | - | 0.0783% | 21881.31 | 27698.2661 | -5816.9561 | 2016-01-01 | 2016-12-31 | 2016-05-23 | 2016-06-22
15026588700 | INSERT 120' - 3" PMLP | - | - | - | - | 0.01521% | 4249.86 | 18619.6978 | -14369.8378 | 2016-01-01 | 2016-12-31 | 2016-05-17 | 2016-06-03 | INSTALLED 8FEET OF 4"P AND 43' OF 3"P TESTED ALL 3-4"P @90#FOR 1HR SOAPED TIE-INS
15026591201 | INSTALL 5200' OF 4"PMMP | - | - | - | - | 7.378% | 2062006.59 | 1731007.511 | 330999.079 | 2016-01-01 | 2016-12-31 | 2016-02-15 | 2016-08-17 | TWALKER/KY 10-26-16: JOB OVER RUN DUE TO KDOT REQUIRE MILL/OVERLAY OF TAYLOR AVE AND SECOND AVE, THIS ADDED $200,000 IN HARD SURFACE REPAIRS ALSO SPEND $40,000 FOR OFF DUTY POLICE FOR SECURITY AND TRAFFIC CONTROL FINALLY SEGA WA $90000 HIGHER THAN PLANNED
15026583201 | INSTALL 1163'-2" PMMP | - | - | - | - | 0.52% | 145327.25 | 184406.1206 | -39078.8706 | 2016-01-01 | 2016-12-31 | 2016-04-29 | 2016-07-08 | TWALKER/KY 10-26-16: JOB UNDER RUN DUE TO LESS HARD SERVICE REPAIRS THAN ESTIMATED WHICH LOWER CONTRACT COST $9000. FINALLY SEGA WAS $8000 LESS THAN ESTIMATE.
15026578400 | INSTALL 100' OF 12" CSHP | - | - | - | - | 0.6377% | 178205.19 | 135287.4933 | 42917.6967 | 2016-01-01 | 2016-12-31 | 2016-05-11 | 2016-06-15 | PROJECT OVERRAN DUE TO THE JOB ORDER ESTIMATE BEING ON 2015 CONTRACTS AND P ROJECT WORKED ON 2016 CONTRACTS. PROJECT ESIMATED FOR 120 HR - 3 MAN CREW A ND WAS WORKED AS 164 HR - 5 MAN CREW. CSPARKS 10/28/16
13026465402 | INSTALL 3685' OF 2"/6" PMMP | - | - | - | - | 1.394% | 389513.48 | 430807.4614 | -41293.9814 | 2016-01-01 | 2016-12-31 | 2016-03-22 | 2016-09-14
16026644600 | INSTALL 10' - 3" WTMP & 4" VLV | - | - | - | - | 0.1371% | 38314.23 | 46961.1712 | -8646.9412 | 2016-01-01 | 2016-12-31 | 2016-05-27 | 2016-06-08
15026617202 | INSTALL 1628'-2"&4" PMMP | - | - | - | - | 0.8924% | 249387.13 | 281307.0414 | -31919.9114 | 2016-01-01 | 2016-12-31 | 2016-10-26 | 2016-12-05 | CONTRACT CREWS WERE PULLED OFF OF PROJECT MANY TIMES DUE TO CITY AND SEWER CONTRACTOR BEING IN THE WAY , OR OUR PIPELINE BEING IN THEIR WAY . UNDERRUN EXPLANATION: THIS PROJECT UNDERRAN BECAUSE APPROXIMATELY 500 UNITS OF 4" SIDEWALK AND 760 UNITS OF 4" ASPHALT WAS PERFORMED BY OTHERS. THOUGH THE ESTIMATE OF LABOR HOURS WAS CLOSE, THE RATE USED WAS HIGHER THAN THE RA TE OF THE EMPLOYEES PERFORMING THE WORK RESULTING IN ABOUT 13K OF THE UNDER RUN. THE OH EFFECT OF THESE TWO UNDERRUNS RESULTED IN ANOTHER $13K UNDER.
13026477400 | INSTALL 10644'-2"&4" PMIP | - | - | - | - | 5.153% | 1440036.79 | 969382.192 | 470654.598 | 2016-01-01 | 2016-12-31 | 2015-08-11 | 2016-06-17 | LEVEL TWO BUDGET VARIANCE POSTED IN WMSDOCS. DNL
15026606100 | INSTALL RECORDING GAUGE | - | - | - | - | 0.009312% | 2602.4 | 5959.4013 | -3357.0013 | 2016-01-01 | 2016-12-31 | 2016-06-23 | 2016-06-23
16026632100 | INSTALL 2" BYPASS VALVE | - | - | - | - | 0.01473% | 4117.07 | 2141.3891 | 1975.6809 | 2016-01-01 | 2016-12-31 | 2016-06-23 | 2016-06-23
16026632901 | INSTALL 425' OF 2" PMMP | - | - | - | - | 0.223% | 62316.09 | 52546.554 | 9769.536 | 2016-01-01 | 2016-12-31 | 2016-06-07 | 2016-06-27
15026617400 | INSTALL 600' - 4" PM | - | - | - | - | 0.2581% | 72143.43 | 45262.74 | 26880.69 | 2016-01-01 | 2016-12-31 | 2016-04-18 | 2016-07-14
16026645800 | INSTALL 175' OF 4"PMIP | - | - | - | - | 0.04115% | 11500.26 | 12625.8344 | -1125.5744 | 2016-01-01 | 2016-12-31 | 2016-06-29 | 2016-07-12
16026649400 | INSTALL 150' OF 2"PMMP | - | - | - | - | 0.055% | 15370.48 | 13288.6012 | 2081.8788 | 2016-01-01 | 2016-12-31 | 2016-06-27 | 2016-07-08
16026648100 | INSTALL 500' OF 2"PMMP | - | - | - | - | 0.07348% | 20536.1 | 19210.3626 | 1325.7374 | 2016-01-01 | 2016-12-31 | 2016-06-27 | 2016-07-29
16026655700 | INSTALL NEW EFC'S | - | - | - | - | 0.0251% | 7013.86 | 7767.0147 | -753.1547 | 2016-01-01 | 2016-12-31 | 2016-07-05 | 2016-07-22 | REPLACED EFCS AND INSTALLED NEW GROUNDING SYSTEM
16026650800 | INSTALL 100' OF 2" PMMP | - | - | - | - | 0.02425% | 6777.53 | 11873.5385 | -5096.0085 | 2016-01-01 | 2016-12-31 | 2016-07-05 | 2016-07-07
17026684100 | INSTALL METAL BUILDING | - | - | - | - | 0.08085% | 22594.89 | 23649.1074 | -1054.2174 | 2016-01-01 | 2016-12-31 |  | 2016-07-08 | THERE WAS AN EXISTING METAL BUILDING AT THIS PREMISE THAT DID NOT HAVE A FACILITY CREATED FOR IT. REPAIRS WERE MADE TO THE BUILDING THIS JOB WAS CREATED TO CORRECTLY ADD THE BUILDING FACILITY AND THE ORIGINAL JOB ORDERS THAT WERE INCORRECTLY CREATED WERE VOIDED ORIGINAL VOIDED JOB ORDERS WERE 16-0266449-00 AND 16-0266448-00 ALL EXPENSES AND TIME ON THE VOIDED ORDERS WERE ASSOCIATED TO THIS NEW CAPITAL JOB ORDER
15026618201 | INSTALL 3640' OF 6" PMMP | - | - | - | - | 1.942% | 542727.17 | 532804.3405 | 9922.8295 | 2016-01-01 | 2016-12-31 | 2016-06-29 | 2016-07-28
16026648400 | INSTALL 700' OF 2"PMMP | - | - | - | - | 0.06473% | 18091 | 21811.0351 | -3720.0351 | 2016-01-01 | 2016-12-31 | 2016-07-11 | 2016-07-14
16026659500 | INSTALL 20'-4"&6" PMMP | - | - | - | - | 0.0009113% | 254.68 | 4701.0442 | -4446.3642 | 2016-01-01 | 2016-12-31 | 2016-07-28 | 2016-08-16 | INSTALLED NEW INT TEE TO REPLACE LEAK ON C/V INSTALLED NEW INLINE TEE WITH PUPS -TESTED ON SITE FOR 1 HR W AIR SOAP TESTED TIE INS AT OP CGI BANKS OK SDADAMS 07-28-16 1534 TESTED AT #90 FOR 1 HR. TESTED FROM 12:35 TP 13:35 OK
16026629100 | INSTALL 1450' OF 4" PMLP | - | - | - | - | 0% | 0 | 76.8083 | -76.8083 | 2016-01-01 | 2016-12-31 | 2016-05-27 | 2016-07-18
16026646000 | INSTAL VALVES & FITTINGS | - | - | - | - | 0.01017% | 2841.32 | 3131.0743 | -289.7543 | 2016-01-01 | 2016-12-31 | 2016-07-18 | 2016-07-29
16026646101 | INSTALL FITTINGS | - | - | - | - | 0.1582% | 44213.6 | 44992.0373 | -778.4373 | 2016-01-01 | 2016-12-31 | 2016-06-14 | 2016-07-21
16026638200 | INSTALL 75' - 4" PMLP | - | - | - | - | 0.07229% | 20202.2 | 36369.7464 | -16167.5464 | 2016-01-01 | 2016-12-31 | 2016-07-25 | 2016-12-13
16026641900 | INSTALL 100' - 2" PM | - | - | - | - | 0.04912% | 13727.71 | 14860.5108 | -1132.8008 | 2016-01-01 | 2016-12-31 | 2016-07-27 | 2016-08-01
16026651400 | INSTALL 460' OF 6"CSHP | - | - | - | - | 0.5495% | 153567.67 | 120193.3494 | 33374.3206 | 2016-01-01 | 2016-12-31 | 2016-07-18 | 2016-08-03 | TWALKER/KY 12-07-16: JOB OVER RUN DUE HIGHER CONTRACT COST RELATED TO EXTRA DEPTH REQUIRED FOR KDOT AND TO AVOID EXISTING WATER LINES, EXTRA COST $23,00 (ITEM 36-030) ST0ONE DUST/BACKFILL MATERIAL, $5100 (ITEM 39-030) EXTRA DEPTH $5100, ROCK EXCAVATE (ITEM 37-005) $3300 AND ADDITIONAL FLAGGER/TRAFFIC CONTROL FOR WORKING AT NIGHT (ITEM 98-140) $4900 HIGHER THAN ESTIMATE.
16026660800 | INSTALL 2 - 6" SS | - | - | - | - | 0.01085% | 3031.15 | 42622.8247 | -39591.6747 | 2016-01-01 | 2016-12-31 | 2016-08-03 | 2016-08-03 | THIS PROJECT UNDERRAN BECAUSE NO HARD SURFACE RESTORATION WAS REQUIRED AND THE WORK WAS PERFORMED BY A COMPANY CREW INSTEAD OF A CONTRACT CREW. THE PR OJECT DURATION WAS ALSO MUCH SHORTER THAN ANTICIPATED. CSPARKS 1/18/17
16026630301 | INSTALL 325' OF 2"PMMP | - | - | - | - | 0.1711% | 47821.99 | 52823.2395 | -5001.2495 | 2016-01-01 | 2016-12-31 | 2016-08-09 | 2016-08-22
16026647600 | INSTALL 300' - 4" PMIP | - | - | - | - | 0.1595% | 44562.91 | 50682.3424 | -6119.4324 | 2016-01-01 | 2016-12-31 | 2016-08-01 | 2016-12-13 | INSTALLED 293' OF 4" MP TESTED AND 2 SHORT STOP TEES TESTED 100 PSIG 1 HOUR RETIRED 266' OF 2" BS SOAP TESTED RETIRE POINT OPERATING PRESSURE
16026662000 | INSTALL REGULATOR | - | - | - | - | 0.001029% | 287.49 | 920.8997 | -633.4097 | 2016-01-01 | 2016-12-31 | 2016-08-15 | 2016-08-15
16026646200 | REPLACE VALVE C-10;INOPERABLE | - | - | - | - | 0.1568% | 43833 | 27510.1027 | 16322.8973 | 2016-01-01 | 2016-12-31 | 2016-06-28 | 2016-08-15
15026584401 | INSTALL 2050'-4" PMMP | - | - | - | - | 0.1752% | 48969.27 | 62170.2395 | -13200.9695 | 2016-01-01 | 2016-12-31 | 2016-08-10 | 2016-08-11
15026618002 | INSTALL 1200' OF 4"/8" PMMP | - | - | - | - | 1.949% | 544628.16 | 570029.6921 | -25401.5321 | 2016-01-01 | 2016-12-31 | 2016-06-29 | 2016-09-26 | JOB ORDER CREATED FOR TWO SYSTEMS (32010131-MP & 32010143-LP) SOME MATERIAL S CHARGED TO THIS JO USED ON PROJECT ID# 15-34183. SEE JO ORDERS 15-0266180 -02, 15-0266181-00, 15-0266257-00 & 15-026258-00. SEE ENGINEERING FOR DETAI LS ABOUT INCORRECTLY CHARGED MATERIALS. 1/10/2017 DGRIFFI
16026662500 | INSTALL 200'-2" PMMP | - | - | - | - | 0.06649% | 18581.48 | 70832.7262 | -52251.2462 | 2016-01-01 | 2016-12-31 | 2016-08-16 | 2016-08-16 | INSTALLED 218' OF 2" P W/ WIRE. TESTED 90# FOR 1HR. TEST END 1532 08/15/16. SOAP TESTED TIE IN AT OP FOR 5MINS. CGI BANKS, OK. GAS ON 1645 08/15/16. INSTALLED LM W/ WIRE & 8 MARKER BALLS UNDERRUN EXPLANATION: INITALLY THIS WAS ESTIMATED WITH APPROXIMATELY $34K I N COMPANY LABOR WITH A CONTRACT CREW PERFORMING THE RESTORATION. ONLY $7,00 0 IN COMPLANY LABOR WAS REQUIRED TO COMPLETE THE WORK.
16026662800 | INSTALL 10' OF 4"PMMP | - | - | - | - | 0.008761% | 2448.52 | 2494.4526 | -45.9326 | 2016-01-01 | 2016-12-31 | 2016-08-18 | 2016-08-24 | CUTOUT 13' OF 4" P. INSTALLED OFFSET TO GO UNDER STORM DRAIN. TESTED PIPE 90LBS FOR 1HR. SOAP TESTED TIE-INS AT OP FOR 5MINS. CGI'D BANKS, NO READING LSTANFIELD 8/18/16
16026642000 | INSTALL 200' - 2" PM | - | - | - | - | 0.03003% | 8392.96 | 3525.8203 | 4867.1397 | 2016-01-01 | 2016-12-31 | 2016-08-22 | 2016-12-13
15026607600 | INSTALL 360'-6"PMLP | - | - | - | - | 0.3634% | 101563.62 | 122602.1912 | -21038.5712 | 2016-01-01 | 2016-12-31 | 2016-07-11 | 2016-09-01
16026659700 | INSTALL EFC | - | - | - | - | 0% | 0 | 364.2537 | -364.2537 | 2016-01-01 | 2016-12-31 |  | 2016-08-23 | REPLACED MECHANICAL GAUGE WITH ON HAND EFC REMOVED FROM ANOTHER ACCOUNT AFT ER UPGRADE
14026550000 | INSTALL 2140' OF 2" & 4" MP | - | - | - | - | 1.084% | 302905.55 | 375887.3727 | -72981.8227 | 2016-01-01 | 2016-12-31 | 2016-04-14 | 2016-08-25 | TIME OVER RUN DUE TO ROCK AND WEATHER UNDERRUN EXPLANATION: THIS PROJECT IS UNDERRUNNING BECAUSE VERY LITTLE OF T HE FINAL RESTORATION HAS BEEN COMPLETED. CONTINUE TO MONITOR UNTIL THE FINA L RESTORATION IS COMPLETE.
13026474404 | INSTALL 1200' OF 2"/6" PMMP | - | - | - | - | 0.7988% | 223233.64 | 169719.3853 | 53514.2547 | 2016-01-01 | 2016-12-31 | 2016-05-27 | 2016-08-25 | GES THE AUTHORIZED SPEND ON THIS PROJECT WAS $269,000 AS INDICATED ON THE P ROJECT BUDGET REQUEST IN WMSDOCS; THEREFORE, A LEVEL TWO VARIANCE IS NOT RE QUIRED SINCE WE UNDER-RAN THE PBR REQUEST. OVER-RUN EXPLANATION: THIS PROJECT OVERRAN BECAUSE 2086 UNITS OF 6&2 WERE R EQUIRED TO COMPLETE THE WORK WHILE ONLY 500 UNITS WERE ESTIMATED. ALSO 1075 FEET OF 6" CONCRETE WERE REQUIRED WHILE NO UNITS WERE ESTIMATED FOR THIS IT EM. TTOY 07/31/17 COMPLETED LEVEL 2 VARIANCE REPORT AND ADDED REPORT TO WMSDOCS
16026633900 | INSTALL SPITFIRE RELITER | - | - | - | - | 0.05227% | 14608.64 | 9543.226 | 5065.414 | 2016-01-01 | 2016-12-31 | 2016-07-18 | 2016-08-25 | ONLY LINES INSTALLED IS SWADGELOK TUBING AND MAX PRESSURE TUBING IS EXPOSED TO IS 25 PSIG. PER RYAN WILLIAMS
16026634000 | INSTALL SPITFIRE RELITER | - | - | - | - | 0.05148% | 14387.02 | 9578.3339 | 4808.6861 | 2016-01-01 | 2016-12-31 | 2016-07-19 | 2016-08-25
16026661900 | INSTALL 300' OF 2"PMMP | - | - | - | - | 0.05283% | 14764.94 | 15832.5305 | -1067.5905 | 2016-01-01 | 2016-12-31 | 2016-08-22 | 2016-08-25 | GAS ON MAIN: 08/25/2016, 18:23
16026664500 | INSTALL 15' OF 2"PMLP | - | - | - | - | 0.008579% | 2397.64 | 2657.2562 | -259.6162 | 2016-01-01 | 2016-12-31 | 2016-08-25 | 2016-08-25
13026478400 | INSTALL 2 NEW FISHER 627 REGS | - | - | - | - | 0.02177% | 6084.2 | 13101.9345 | -7017.7345 | 2016-01-01 | 2016-12-31 | 2016-07-21 | 2016-08-29 | REPLACED MONITOR AND CONTROL REGULATOR
16026647100 | INSTALL 285' - 2" PMMP | - | - | - | - | 0.07565% | 21140.9 | 23214.0272 | -2073.1272 | 2016-01-01 | 2016-12-31 | 2016-08-15 | 2016-08-29
16026637800 | INSTALL ERX FOR R-1274 | - | - | - | - | 0.04686% | 13094.71 | 24466.5458 | -11371.8358 | 2016-01-01 | 2016-12-31 | 2016-08-09 | 2016-08-31 | INSTALLED NEW ERX WITH SOLAR SYSTEM
16026660300 | INSTALL 300' OF 2"PMMP | - | - | - | - | 0.06962% | 19455.48 | 24635.9085 | -5180.4285 | 2016-01-01 | 2016-12-31 | 2016-08-29 | 2016-08-31
15026608700 | INSTALL 4500' OF 2" PMMP | - | - | - | - | 1.715% | 479169.53 | 622665.0001 | -143495.4701 | 2016-01-01 | 2016-12-31 | 2016-03-22 | 2016-10-27 | UNDERRUN EXPLANATION: 20000 UNITS OF 6&2 WERE ESTIMATED, BUT NONE WERE REQU IRED.
16026649101 | INSTALL 600' OF 2"PMMP | - | - | - | - | 0.08544% | 23877.85 | 24598.7665 | -720.9165 | 2016-01-01 | 2016-12-31 | 2016-08-29 | 2016-09-01
15026582700 | INSTALL 2795' - 4" & 2" PMMP | - | - | - | - | 0.6344% | 177304.18 | 233068.4062 | -55764.2262 | 2016-01-01 | 2016-12-31 | 2016-07-18 | 2016-09-08 | DIDNOT SHOW COMPLETE DO TO CONTRACT CREW THOUGHT THEY WERE GOING BACK TO KI LL TEMPORARY TWO INCH PIPE LAID AT TIME OF COSTRUCTION AND LAY FOUR INCH BA CK 01/11/17: UNDERRUN EXPLANATION = ROAD CORRIDOR WAS CLOSED TO TRAFFIC AT TIME OF PIPELINE CONSTRUCTION SO NO DB REQ'D, 500 LF LESS SILT FENCE REQ'D, AND NO ECB OR SAFETY FENCE REQ'D. LESS DUST & STONE BACKFILL AND NO HARD SURFACE RESTORATION OR FLAGGER REQ'D SINCE ROAD CONTRACTOR HAD SHUT ROAD.
16026639500 | INSTAL NEW RECTIFIER & GB | - | - | - | - | 0.2117% | 59150.42 | 67085.4945 | -7935.0745 | 2016-01-01 | 2016-12-31 | 2016-05-16 | 2016-09-14
16026657200 | INSTALL 500' OF 4" PMMP | - | - | - | - | 0.3371% | 94199.85 | 129286.3383 | -35086.4883 | 2016-01-01 | 2016-12-31 | 2016-08-24 | 2016-09-19 | UNDERRUN EXPLANATION: THIS PROJECT WAS PLANNED FOR OPEN CUT WITH A SIGNIFIC ANT AMOUNT OF COLD PATCH AND 6&2; HOWEVER, WE WERE ABLE TO DIRECTIONALLY BO RE THE PIPE IN AND AVOID THE HARD SURFACE REPAIRS. ADDITIONALLY, 100 FF OF ROCK WAS ESTIMATED ALONG WITH A COMMENSURATE AMOUNT OF SPECIAL BACKFILL. HO WEVER, NONE OF THAT WAS REQUIRED.
15026613700 | INSTALL 750' OF 2"PMMP | - | - | - | - | 0.06178% | 17266.07 | 20886.6687 | -3620.5987 | 2016-01-01 | 2016-12-31 | 2016-09-13 | 2016-09-19
15026616401 | INSTALL MI MINI-AT EFC W/MODEM | - | - | - | - | 0.02796% | 7812.73 | 10774.7297 | -2961.9997 | 2016-01-01 | 2016-12-31 | 2016-09-15 | 2016-09-15 | INSTALLED NEW EFC AND MI-WIRELESS UNIT
15026625700 | INSTALL 880' OF 6" PMLP | - | - | - | - | 0.0002301% | 64.3 | 76.8083 | -12.5083 | 2016-01-01 | 2016-12-31 | 2016-03-21 | 2016-09-15 | JOB ORDER CREATED FOR TWO SYSTEMS (32010131-MP & 32010143-LP) SOME MATERITA LS CHAREGED TO THIS JO USED ON PROJECT ID# 15-34183. SEE ENGINEERING FOR DE TAILS ABOUT INCORRECTLY CHARGED MATERIALS. 01/10/2017 DGRIFFI
16026629501 | INSTALL 1850' OF 2"PMMP | - | - | - | - | 0.1947% | 54402.79 | 63641.9173 | -9239.1273 | 2016-01-01 | 2016-12-31 | 2016-09-13 | 2016-09-15
16026653401 | INSTALL MI MINI-AT EFC | - | - | - | - | 0.01979% | 5531.83 | 10150.7297 | -4618.8997 | 2016-01-01 | 2016-12-31 | 2016-06-20 | 2016-09-16 | INSTALLED NEW EFC/MI-WIRELESS UNIT
16026637001 | INSTALL 350' OF 4" PMMP | - | - | - | - | 0.2832% | 79136.19 | 64218.3135 | 14917.8765 | 2016-01-01 | 2016-12-31 | 2016-08-29 | 2016-09-21
16026666900 | INSTALL 120' OF 2" PMMP | - | - | - | - | 0.04591% | 12830.21 | 14869.5401 | -2039.3301 | 2016-01-01 | 2016-12-31 | 2016-09-21 | 2016-09-27
16026648000 | INSTALL 650' OF 2"PMMP | - | - | - | - | 0.05533% | 15462.69 | 30744.7077 | -15282.0177 | 2016-01-01 | 2016-12-31 | 2016-09-21 | 2016-09-27
16026648501 | INSTALL 133'-2" PMMP | - | - | - | - | 0.05899% | 16485.07 | 35305.1858 | -18820.1158 | 2016-01-01 | 2016-12-31 | 2016-09-26 | 2016-10-27
16026652100 | INSTALL 10' - 4" PMMP | - | - | - | - | 0.0349% | 9754.42 | 10199.7704 | -445.3504 | 2016-01-01 | 2016-12-31 | 2016-09-28 | 2016-10-03
15026609800 | INSTALL 1310' - 2" PMMP | - | - | - | - | 0.6758% | 188862.93 | 181171.8324 | 7691.0976 | 2016-01-01 | 2016-12-31 | 2016-08-09 | 2016-12-08 | HAD OTHER JOBS PUSHED DATE PAST DUE
16026664900 | INSTALL 350' OF 2"PMMP | - | - | - | - | 0.06397% | 17878.05 | 21842.469 | -3964.419 | 2016-01-01 | 2016-12-31 | 2016-10-03 | 2016-10-10
15026600301 | INSTALL 425' OF 2"PMMP | - | - | - | - | 0.0839% | 23446.9 | 41832.2902 | -18385.3902 | 2016-01-01 | 2016-12-31 | 2016-10-03 | 2016-10-12
15026623500 | INSTALL 3000' OF 4"PMMP | - | - | - | - | 0.5055% | 141271.03 | 115368.4992 | 25902.5308 | 2016-01-01 | 2016-12-31 | 2016-08-30 | 2016-10-05
16026665200 | INSTALL 4" SETTING VALVES | - | - | - | - | 0.03509% | 9806.78 | 13548.8966 | -3742.1166 | 2016-01-01 | 2016-12-31 | 2016-10-04 | 2016-10-05 | INSTALLED 3 - 4" VALVES
16026665400 | MAVITY - INSTALL 8" SS FITTING | - | - | - | - | 0.03747% | 10470.71 | 14539.7278 | -4069.0178 | 2016-01-01 | 2016-12-31 | 2016-10-03 | 2016-10-05 | INSTALLED 8" SS FITTING
15026602000 | INSTALL NEW FENCE FOR R-1439 | - | - | - | - | 0.02013% | 5625.76 | 5664.86 | -39.1 | 2016-01-01 | 2016-12-31 | 2016-06-06 | 2016-10-06 | INSTALLED 10' X 10' X 10' X 10' FENCE WITH TWO MANUAL GATES
16026653700 | INSTALL 10'-6" PMMP & VALVE | - | - | - | - | 0.04287% | 11981.8 | 11082.0483 | 899.7517 | 2016-01-01 | 2016-12-31 | 2016-10-04 | 2016-10-10
15026582900 | INSTALL 5700'-4" & 2" PMMP | - | - | - | - | 2.194% | 613027.42 | 724237.089 | -111209.669 | 2016-01-01 | 2016-12-31 | 2016-04-01 | 2016-10-11 | 1/18/17: UNDERRUN EXPLANATION (BKSLONE) = CONSIDERABLY LESS HARD SURFACE WAS REQUIRED TO BE RESTORED THAN ORIGINALLY ESTIMATED BECAUSE THE ROAD CONTRACTOR WAS FALLING RIGHT IN BEHIND OUR PIPELINE CONTRACTOR. ITEMS CONSISTING OF 6"&2" CONC/ASPH, 4" & 6" CONC, SW, CONC CURB, CURB & GUTTER, COLD PATCH, SAW CUT, AND CUT & REMOVE AMOUNTED TO $80,000 LESS. ALSO FLAGGING WAS MUCH LESS THAN ESTIMATED (764 VS 800) AMOUNTING TO $31,500 SAVINGS. THIS PROJECT WAS PHASED DUE TO KDOT REQUIREMENTS. SOME JOB ORDERS IN THE SE T RETIRED PRIORITY PIPE WHILE OTHERS DID NOT. THERE WAS ONE INSTALL AND THREE RETIREMENTS:5830,6371,6372.
15026615700 | INSTALL 7200' - 2" & 4" PMMP | - | - | - | - | 2.345% | 655434.24 | 696093.9197 | -40659.6797 | 2016-01-01 | 2016-12-31 | 2016-05-31 | 2016-12-14
16026669500 | INSTALL 350' OF 2"PMMP | - | - | - | - | 0.0649% | 18138.01 | 19892.3669 | -1754.3569 | 2016-01-01 | 2016-12-31 | 2016-10-05 | 2016-10-11
16026639900 | INSTALL 200'-8" PMMP | - | - | - | - | 0.1946% | 54381.95 | 78644.1934 | -24262.2434 | 2016-01-01 | 2016-12-31 | 2016-09-20 | 2016-10-13
15026598200 | INSTALL FENCE FOR R-1217 | - | - | - | - | 0.02103% | 5876.33 | 4459.86 | 1416.47 | 2016-01-01 | 2016-12-31 | 2016-09-01 | 2016-10-16
16026660100 | INSTALL 40' OF 6" PMLP | - | - | - | - | 0.0751% | 20988.21 | 47183.8247 | -26195.6147 | 2016-01-01 | 2016-12-31 | 2016-10-12 | 2016-10-18 | COMPLETION DATE EXCEEDED THE COMMIT DATE DUE TO THE PREVIOUS PROJECT TAKING LONGER THAN EXPECTED.
16026670400 | INSTALL MI WIRELESS EFC | - | - | - | - | 0.02787% | 7787.51 | 11853.2679 | -4065.7579 | 2016-01-01 | 2016-12-31 | 2016-10-24 | 2016-10-24 | INSTALLED NEW EFC AND MI-WIRELESS
16026642400 | INSTALL MI WIRELESS | - | - | - | - | 0.03928% | 10978.62 | 14387.7459 | -3409.1259 | 2016-01-01 | 2016-12-31 | 2016-10-17 | 2016-10-26 | INSTALLED EFC & MI-WIRELESS
16026671400 | INSTALL 350' OF 2"PMMP | - | - | - | - | 0.05058% | 14134.99 | 17461.7634 | -3326.7734 | 2016-01-01 | 2016-12-31 | 2016-10-24 | 2016-10-26
16026629400 | INSTALL 900' OF 2" PMMP | - | - | - | - | 0.09393% | 26251.09 | 82776.0432 | -56524.9532 | 2016-01-01 | 2016-12-31 | 2016-10-17 | 2016-10-27 | UNDERRUN EXPLANATION: THIS PROJECT UNDERRAN BECAUSE ESTIMATED ROCK AND A CO MMENSURATE ABOUNT OF BACKFILE WAS NOT ENCOUNDERED. THE ESTIMATE CONTAINED 1 800 FF OF ROCK WHILE ONLY 100 FF WERE REQUIRED. ALSO, THE NECESSARY BACKFIL L WAS NOT REQUIRED. ALSO, THE PROJECT HAD ESTIMATED HARD SURFACE REPAIRS TH AT WERE NOT NECESSARY.
16026667000 | INSTALL 15' OF 6" PMMP | - | - | - | - | 0.13% | 36321.57 | 23530.0801 | 12791.4899 | 2016-01-01 | 2016-12-31 | 2016-10-19 | 2016-11-03
16026668200 | INSTALL 300' OF 2"PMMP | - | - | - | - | 0.1457% | 40721.79 | 14300.3669 | 26421.4231 | 2016-01-01 | 2016-12-31 | 2016-10-20 | 2016-11-01
15026594600 | INSTALL DUAL RUN REGULATOR | - | - | - | - | -0.02993% | -8365.28 | 110700.927 | -119066.207 | 2016-01-01 | 2016-12-31 | 2016-10-18 | 2016-11-02 | JOB NOT RELEASED UNTIL MID 2016 -HOLD UP WITH CITY OF LEXINGTON UNDERUN EXPLANATION: MATERIALS OVERESTIMATED BY $20,000. SOME MATERIAL COST WERE COVERED UNDER CONTRACT ITEMS. LABOR ALSO UNDERRAN BY 40 HOURS. THIS C AUSED SEGA AND OTHER TO UNDERUUN BY $20,000. POWERPLANT SHOWS BOOKED COST O F $71,000 TO ORIGINAL ESTIMATE OF $111,000. D.LEMONS 5/23/17
16026639801 | INSTALL 5615' OF 6"/4"/2"PMMP | - | - | - | - | 0.9999% | 279431.16 | 241632.2302 | 37798.9298 | 2016-01-01 | 2016-12-31 | 2016-08-08 | 2016-11-07 | TWALKER/KY 02-10-17: JOB OVER RUN DUE TO EXTRA 400' OF MAIN INSTALLED VS ESTIMATE WHICH ALSO REQUIRE 800' OF ASPHALT CUTTING THIS ADDED $10000 IN CONTRACT COST, PLUS SEGA WAS $10000 HIGHER THAN ESTIMATE.
16026658700 | INSTALL 250' OF 2" PMLP | - | - | - | - | 0.218% | 60913.61 | 57757.4009 | 3156.2091 | 2016-01-01 | 2016-12-31 | 2016-11-03 | 2016-11-14
16026635500 | INSTALL 160'-4" PMMP | - | - | - | - | 0.07354% | 20551.96 | 16468.0289 | 4083.9311 | 2016-01-01 | 2016-12-31 | 2016-11-08 | 2016-12-13 | INSTALLED 154' OF 4" MP AND RETIRED 2" BYPASS SOAP TESTED RETIRE AND FINAL CONN. OPERATING PRESSURE
14026550501 | INSTALL 102' OF 4" PMLP | - | - | - | - | 0.2821% | 78840.11 | 64910.162 | 13929.948 | 2016-01-01 | 2016-12-31 | 2016-10-13 | 2016-11-10
15026625100 | INSTALL 7156'-2"&4"PMIP | - | - | - | - | 3.023% | 844869.6 | 948640.697 | -103771.097 | 2016-01-01 | 2016-12-31 | 2016-04-13 | 2016-12-19 | UNDERRUN DUE TO ONLY INSTALLING 6,000 OF THE ESTIMATED 10,500 FEET OF PIPE. STATE PERMIT WAS NOT GRANTED FOR A PORTION OF THE PROJECT. RESULT IN UNDER RUN OF $265,000 IN CONTRACT COSTS, $11,000 IN COMPANY LABOR, AND $68,000 IN S SEGA COSTS. MATERIALS OVERRAN BY $8,000 DUE TO ADDITINAL TIE-IN MATERIAL S BEING NEEDED. D.LEMONS 4/27/17
16026635700 | INSTALL 1275' - 2" PMIP | - | - | - | - | 0.4368% | 122075.19 | 57323.4108 | 64751.7792 | 2016-01-01 | 2016-12-31 | 2016-09-15 | 2016-11-09 | OVERRUN EXPLANATION: THE CONSTRUCTION COORDINATOR INSTALLED 1,036 MORE FEET THAT THE JOB WAS APPROVED FOR. A SCOPE CHANGE WAS NOT REQUESTED. A LEVEL 2 BUDGET REQUEST WAS SUBMITTED TO CLOSE OUT ON 4/24/17.
16026673400 | INSTALL PRIVACY FENCE | - | - | - | - | 0.01668% | 4660.94 | 6158.5048 | -1497.5648 | 2016-01-01 | 2016-12-31 | 2016-11-11 | 2016-11-11
15026593901 | INSTALL 2040'-2" PMMP | - | - | - | - | 1.031% | 288206.56 | 361731.1926 | -73524.6326 | 2016-01-01 | 2016-12-31 | 2016-10-19 | 2016-11-28 | THIS PROJECT IS UNDERRUNNING DUE TO PAVING COSTS NOT YET HITTING. OVER 4,00 0 SQUARE FEET OF 6" CONCRETE AND 2" ASPHALT HASN'T HIT THE JOB ORDER YET. C SPARKS 01/18/17 THIS PROJECT UNDERRAN DUE TO PAVING COSTS BEING LESS THAN ANTICIPATED. 4,00 0 SQUARE FEET OF 6&2 NEVER HIT THE JOB ORDER. CSPARKS 04/26/17
16026677300 | INSTALL 11' - 6" CS HP | - | - | - | - | 0.02987% | 8347.08 | 19923.3349 | -11576.2549 | 2016-01-01 | 2016-12-31 | 2016-11-16 | 2016-11-16 | VERIFIED IN FAAR THAT THIS WAS 1928 BARE PIPE.
16026675200 | INSTALL EFC & MI WIRELESS | - | - | - | - | 0.01171% | 3272.81 | 17908.5557 | -14635.7457 | 2016-01-01 | 2016-12-31 | 2016-11-17 | 2016-11-17 | INSTALLED NEW EFC SER # 0709827 AND NEW MI-WIRELESS UNIT W/SOLAR PANEL
15026603801 | INSTALL 3035' OF 2"/4"/6"PMMP | - | - | - | - | 2.261% | 631921.53 | 718211.0027 | -86289.4727 | 2016-01-01 | 2016-12-31 | 2016-09-02 | 2016-12-05
16026678100 | INSTALL BUS ASSEMBLY BLDG | - | - | - | - | 0.03284% | 9177.53 | 10342.5556 | -1165.0256 | 2016-01-01 | 2016-12-31 |  | 2016-11-21
16026663000 | INSTALL 90'-2" PMMP PVT R/W | - | - | - | - | 0.04245% | 11862.34 | 12853.8837 | -991.5437 | 2016-01-01 | 2016-12-31 | 2016-11-21 | 2016-11-23
16026678500 | INSTALL NEW ODORIZER | - | - | - | - | 0.0007105% | 198.57 | 1696.7779 | -1498.2079 | 2016-01-01 | 2016-12-31 | 2016-11-28 | 2016-11-28 | RETIRED ODORANT TANK INSTALLED NEW FARM TAP ODOR BOTTLE
16026675400 | INSTALL 240' - 4" PMMP | - | - | - | - | 0.03865% | 10802.08 | 15110.2227 | -4308.1427 | 2016-01-01 | 2016-12-31 | 2016-11-28 | 2016-11-29
16026639701 | INSTALL NEW SKID REG STATION | - | - | - | - | 0.4518% | 126266.52 | 119269.3345 | 6997.1855 | 2016-01-01 | 2016-12-31 | 2016-10-10 | 2016-12-02
16026666600 | INSTALL GMB SETTING | - | - | - | - | 0.03803% | 10628.99 | 11625.6624 | -996.6724 | 2016-01-01 | 2016-12-31 | 2016-12-01 | 2016-12-02 | JOB DELAYED - CUSTOMER WAS NOT READY - INSTALLED NEW GMB SETTING W/EFC AND MIWIRELESS UNIT
15026622500 | INSTALL CATALYTIC HEATER | - | - | - | - | 0.01056% | 2952.37 | 4604.72 | -1652.35 | 2016-01-01 | 2016-12-31 | 2016-12-05 | 2016-12-05
16026661800 | INSTALL 800' OF 2"PMMP | - | - | - | - | 0.06123% | 17112.66 | 28272.4132 | -11159.7532 | 2016-01-01 | 2016-12-31 | 2016-12-01 | 2016-12-07
16026675500 | INSTAL 20'-2" PMMP | - | - | - | - | 0.01691% | 4726.11 | 29163.8932 | -24437.7832 | 2016-01-01 | 2016-12-31 | 2016-12-06 | 2016-12-07
15026611400 | INSTALL R-1860 | - | - | - | - | 0.316% | 88302.06 | 78119.9559 | 10182.1041 | 2016-01-01 | 2016-12-31 | 2016-10-20 | 2016-12-08 | JOB NOT RELEASED FOR CONSTRUCTION UNTIL LATE 2016 INSTALLED & PUT IN SERVICE NEW DUAL RUN STATION
16026657901 | INSTALL 220' OF 4" CSHP | - | - | - | - | 0.17% | 47514.56 | 60998.3135 | -13483.7535 | 2016-01-01 | 2016-12-31 | 2016-11-07 | 2016-12-12
16026658000 | 725' OF 6" PMMP R-1860 OUTLET | - | - | - | - | 0.2095% | 58545.27 | 64902.8519 | -6357.5819 | 2016-01-01 | 2016-12-31 | 2016-11-17 | 2016-12-12
16026681600 | INSTALL 13' OF 6"PMLP MAIN | - | - | - | - | 0.1036% | 28943.78 | 32167.3521 | -3223.5721 | 2016-01-01 | 2016-12-31 | 2016-12-10 | 2017-01-03
16026679900 | INSTALL 164' OF 4"PMLP MAIN | - | - | - | - | 0.2838% | 79326.07 | 48653.273 | 30672.797 | 2016-01-01 | 2016-12-31 | 2016-12-21 | 2016-12-22 | OVERRUN EXPLANATION: 1205 UNITS OF 10" CONCRETE WERE REQUIRED INSTEAD OF TH E 600 UNITS OF 6&2. THIS CONTRIBUTED TO AN OVERRUN IN THE CONSTRUCTION COST S.
16026676600 | INSTALL 336' - 2" PMIP | - | - | - | - | 0.05141% | 14368.54 | 14702.667 | -334.127 | 2016-01-01 | 2016-12-31 | 2016-12-13 | 2016-12-15
16026674500 | INSTALL 300' OF 6"PMMP | - | - | - | - | 0.2862% | 79991.76 | 95959.7798 | -15968.0198 | 2016-01-01 | 2016-12-31 | 2016-11-28 | 2016-12-20
16026669801 | INSTALL 615' OF 6" PMMP | - | - | - | - | 0.9431% | 263554.54 | 176080.8006 | 87473.7394 | 2016-01-01 | 2016-12-31 | 2016-11-15 | 2017-01-05 | TWALKER/KY 04-24-17: LEVEL 2 VARIANCE REPORTS TO EXPLAIN JOB OVER RUN ADDED TO WMS.DOCS. COST OVER RUN TO HIGHER PAVING/HARD SURFACE RESTORATION COST FROM FISHEL.
16026649600 | INSTALL 501' - 2" PMMP | - | - | - | - | 0.1073% | 29974.31 | 42901.5241 | -12927.2141 | 2016-01-01 | 2016-12-31 | 2016-12-06 | 2016-12-28
16026671700 | INSTALL 240' OF 2"PMMP | - | - | - | - | 0.04343% | 12138.12 | 14513.0107 | -2374.8907 | 2016-01-01 | 2016-12-31 | 2016-12-27 | 2016-12-29
|  | - | - | - | - |  | 2016 Construction Project Budget | 27947000
16026674700 | INSTALL 675' - 2" PMMP | - | - | - | - | 0.3661% | 126744.65 | 95497.7784 | 31246.8716 | 2017-01-01 | 2017-12-31 | 2016-12-13 | 2017-01-13 | PASSED COMMIT DATE BECAUSE OF WEATHER AND HOLIDAYS
16026658200 | INSTALL 6" PCF | - | - | - | - | 0.02406% | 8329.54 | 6440.7524 | 1888.7876 | 2017-01-01 | 2017-12-31 | 2016-12-13 | 2017-01-17
15026580902 | INSTALL 900'OF 8"/12" CSHP | - | - | - | - | 1.194% | 413491.23 | 406599.0053 | 6892.2247 | 2017-01-01 | 2017-12-31 | 2016-11-28 | 2017-01-18
16026658500 | INSTALL 300' OF 2" PMMP | - | - | - | - | 0.1046% | 36224.19 | 54170.6202 | -17946.4302 | 2017-01-01 | 2017-12-31 | 2017-01-10 | 2017-01-31
16026678400 | INSTALL 115' - 2" PMIP | - | - | - | - | 0.05548% | 19206.08 | 6882.4447 | 12323.6353 | 2017-01-01 | 2017-12-31 | 2017-01-16 | 2017-01-26
16026681800 | INSTALL 200' OF 2"PMMP | - | - | - | - | 0.03733% | 12924.21 | 12283.2948 | 640.9152 | 2017-01-01 | 2017-12-31 | 2017-01-10 | 2017-01-24
16026659000 | INSTALL 350' OF 2" PMMP | - | - | - | - | 0.0312% | 10800.19 | 17535.6831 | -6735.4931 | 2017-01-01 | 2017-12-31 | 2017-01-18 | 2017-01-26
16026667801 | INSTALL 50'-6" PMMP | - | - | - | - | 0.32% | 110762.83 | 134221.1146 | -23458.2846 | 2017-01-01 | 2017-12-31 | 2016-12-21 | 2017-02-02
16026675000 | INSTALL 200' - 2" PMMP | - | - | - | - | 0.09513% | 32931.71 | 21436.667 | 11495.043 | 2017-01-01 | 2017-12-31 | 2017-01-16 | 2017-01-26
16026679200 | INSTALL 1500'-2" PMMP | - | - | - | - | 0.126% | 43632.04 | 54417.3948 | -10785.3548 | 2017-01-01 | 2017-12-31 | 2017-01-16 | 2017-01-31
16026682500 | INSTALL 950' OF 2"PMMP | - | - | - | - | 0.06943% | 24035.42 | 23304.2371 | 731.1829 | 2017-01-01 | 2017-12-31 | 2017-01-30 | 2017-02-02 | TEST
16026640800 | INSTALL 30'-4" PMLP | - | - | - | - | 0.04557% | 15775.1 | 13653.5905 | 2121.5095 | 2017-01-01 | 2017-12-31 | 2017-02-01 | 2017-02-06
15026620401 | INSTALL 1750' OF 2"PMMP | - | - | - | - | 0.3168% | 109663.42 | 104252.6766 | 5410.7434 | 2017-01-01 | 2017-12-31 | 2017-01-18 | 2017-03-13
16026677000 | INSTALL 100' - 4" PMLP MAIN | - | - | - | - | 0.05024% | 17391.95 | 15690.667 | 1701.283 | 2017-01-01 | 2017-12-31 | 2017-02-02 | 2017-02-08 | DUE TO WEATHER
17026686700 | INSTALL NON-PRIMARY RELIEF | - | - | - | - | 0.002555% | 884.51 | 2295.3456 | -1410.8356 | 2017-01-01 | 2017-12-31 | 2017-02-09 | 2017-02-09
17026689400 | INSTALL 10' - 2" PMMP | - | - | - | - | 0.001365% | 472.55 | 4460.2919 | -3987.7419 | 2017-01-01 | 2017-12-31 | 2017-02-10 | 2017-02-10 | 5' 2" PM PIPE TEST OFF SITE SEE WORK ORDER #16-4281339-00. U129900 2/13/17
16026651600 | INSTALL 400' - 2" PMLP | - | - | - | - | 0.3055% | 105760.11 | 89973.6202 | 15786.4898 | 2017-01-01 | 2017-12-31 | 2017-01-16 | 2017-02-14
16026659200 | INSTALL 40' - 4" PMLP | - | - | - | - | 0.05933% | 20536.88 | 15002.667 | 5534.213 | 2017-01-01 | 2017-12-31 | 2017-02-09 | 2017-02-14
16026678900 | INSTALL 510' - 2" PMMP | - | - | - | - | 0.3065% | 106091.19 | 106125.949 | -34.759 | 2017-01-01 | 2017-12-31 | 2017-01-23 | 2017-05-01
16026680600 | INSTALL 475' OF 2"PMIP MAIN | - | - | - | - | 0.06199% | 21459.29 | 25656.4746 | -4197.1846 | 2017-01-01 | 2017-12-31 | 2017-02-02 | 2017-02-15
17026685100 | INSTALL 230'-2" PMLP | - | - | - | - | 0.1216% | 42097.07 | 48357.3054 | -6260.2354 | 2017-01-01 | 2017-12-31 | 2017-02-06 | 2017-02-20
16026641600 | INSTALL 375'-4"PMLP | - | - | - | - | 0.1313% | 45437.48 | 71594.554 | -26157.074 | 2017-01-01 | 2017-12-31 | 2017-01-31 | 2017-02-23
16026675900 | INSTALL 2850' OF 2"/4"PMMP | - | - | - | - | 0.1891% | 65452.64 | 68731.9452 | -3279.3052 | 2017-01-01 | 2017-12-31 | 2017-02-06 | 2017-02-23
16026637601 | INSTALL 20'-8" CSHP | - | - | - | - | 0.6932% | 239958.48 | 225383.9816 | 14574.4984 | 2017-01-01 | 2017-12-31 | 2016-12-27 | 2017-03-02
16026674800 | INSTALL 500'-2" PMMP | - | - | - | - | 0.2879% | 99654.31 | 212345.6694 | -112691.3594 | 2017-01-01 | 2017-12-31 | 2017-01-17 | 2017-02-28 | UNDERRUN EXPLANATION: PROJECT WAS PLANNED FOR FULL RESTORATION, NOT KNOWING OTHER CONTRACTORS SCHEDULE. THRU COORDINATION WITH CITY CONTRACTOR, RESTORA TION COST WERE REDUCED. OVERESTIMATED IN ROCK EXCAVATION BY 1000 UNITS, COL D PATCH BY 1200 UNITS, CONCRETE BY 1550 UNITS AND LABOR AND FLAGGIN MAN HOU RS. THIS RESULTED IN APPROXIMATELY $87,000 IN SAVINGS TO CONTRACTOR COST. A LSO A REDUCTION IN SEGA OF $8000 DUE TO LOWERE CONTRACTOR COSTS FOR A TOTAL REDUCTION OF $95,000. D.LEMONS 6/21/17
16026683700 | INSTALL 150' - 2" PMMP | - | - | - | - | 0.02419% | 8372.7 | 11221.079 | -2848.379 | 2017-01-01 | 2017-12-31 | 2017-02-28 | 2017-02-28
16026677200 | INSTALL 400' - 2" PMMP | - | - | - | - | 0.1252% | 43347.05 | 30602.334 | 12744.716 | 2017-01-01 | 2017-12-31 | 2017-02-09 | 2017-03-02
15026597400 | INSTALL 360'-4" PMLP | - | - | - | - | 0.1802% | 62390.2 | 53119.6951 | 9270.5049 | 2017-01-01 | 2017-12-31 | 2017-02-22 | 2017-03-08
17026695400 | INSTALL NEW PAPER GAUGE | - | - | - | - | 0.0003525% | 122.04 | 908.4973 | -786.4573 | 2017-01-01 | 2017-12-31 | 2017-03-31 | 2017-03-08 | REPLACED PRESSURE RECORDING GAUGE
17026694500 | INSTALL MI WIRELESS | - | - | - | - | 0.01146% | 3967.7 | 13082.4485 | -9114.7485 | 2017-01-01 | 2017-12-31 | 2017-03-09 | 2017-03-09 | REPLACED EFC W/NEW MINI-AT AND MI-WIRELESS UNIT EFC SERIAL 13215318 MI-SERIAL 13191898 MDN 859-382-6087 IP 10.22.7.117:2203 TWALKER/KY-TEST COMMENTS
16026683300 | RELOCATE 50'-2" PMMP | - | - | - | - | 0.009856% | 3411.75 | 20529.2292 | -17117.4792 | 2017-01-01 | 2017-12-31 | 2017-03-08 | 2017-04-25
17026687300 | INSTALL 900' OF 2"PMMP | - | - | - | - | 0.04644% | 16076.78 | 21790.2426 | -5713.4626 | 2017-01-01 | 2017-12-31 | 2017-03-08 | 2017-03-14
17026688300 | INSTALL NEW RV-50 4G MODEM | - | - | - | - | 0.009995% | 3460.09 | 5921.2243 | -2461.1343 | 2017-01-01 | 2017-12-31 |  | 2017-03-14
17026686300 | INSTALL 600' OF 4"PMMP | - | - | - | - | 0.09289% | 32154.88 | 38541.2426 | -6386.3626 | 2017-01-01 | 2017-12-31 | 2017-02-27 | 2017-03-16
16026672500 | INSERT 20'-2" PMLP | - | - | - | - | 0.01278% | 4423.67 | 14317.0006 | -9893.3306 | 2017-01-01 | 2017-12-31 | 2017-02-03 | 2017-03-16
17026689900 | INSTALL 550' - 4" PMLP | - | - | - | - | 0.1611% | 55755.49 | 83648.4852 | -27892.9952 | 2017-01-01 | 2017-12-31 | 2017-03-13 | 2017-03-27
16026683800 | INSTALL 100' - 2" PMMP | - | - | - | - | 0.009483% | 3282.84 | 8044.5881 | -4761.7481 | 2017-01-01 | 2017-12-31 |  | 2017-04-21
17026697000 | INSTALL 100' OF 2"PMMP | - | - | - | - | 0.01497% | 5181.19 | 7933.2433 | -2752.0533 | 2017-01-01 | 2017-12-31 | 2017-03-21 | 2017-03-24 | INSTALLED 101' 020 PMMP. WORK PERFORMED AND TESTED BY STANLEY PIPELINE. FOREMAN:JOSH HALL
17026685600 | INSTALL 520' OF 4"PMLP | - | - | - | - | 0.126% | 43617.96 | 45721.7278 | -2103.7678 | 2017-01-01 | 2017-12-31 | 2017-03-20 | 2017-03-30
16026657500 | INSTALL 3" MOONEY CONTROL REG | - | - | - | - | 0.01564% | 5413.36 | 6149.0147 | -735.6547 | 2017-01-01 | 2017-12-31 | 2017-03-29 | 2017-03-29
16026676300 | INSTALL METAL BUILDING | - | - | - | - | 0.1435% | 49678.19 | 48767.2227 | 910.9673 | 2017-01-01 | 2017-12-31 | 2017-01-24 | 2017-03-30
17026700000 | INSTALL 100' - 2" PMLP | - | - | - | - | 0.02028% | 7020.54 | 7862.0224 | -841.4824 | 2017-01-01 | 2017-12-31 | 2017-03-29 | 2017-04-04 | MCR 4-4-17
17026704300 | INSTALL 90'2" PMLP | - | - | - | - | 0.01953% | 6760.58 | 5620.0846 | 1140.4954 | 2017-01-01 | 2017-12-31 |  | 2017-04-14 | INSTALLED 90' OF 2" PLASTIC MAIN
16026643500 | INSTALL 2" VALVES | - | - | - | - | 0.003012% | 1042.53 | 24215.2351 | -23172.7051 | 2017-01-01 | 2017-12-31 | 2017-04-06 | 2017-04-06
16026678800 | INSTALL 1400'-4" CSHP | - | - | - | - | 0.4267% | 147694.99 | 181476.0029 | -33781.0129 | 2017-01-01 | 2017-12-31 | 2017-02-16 | 2017-05-23 | JOB ESTIMATED TO INCLUDE 900 FT OS SILT FENCE, 500 SY OR EROSION SEEDING, A ND 4" STOPPER WITH WELD THAT WERE NOT NEEDED. TIE-IN WAS COMPLETED WITHOUT USE OF 4" STOPPER AND OTHER CONTRACTORS IN AREA ELIMINATED THE NEED FOR TH E EROSION ITEMS. 80 SF OF HARD SURFACE RESTORATION WAS ESTIMATED, BUT NOT R EQUIRED. 3000 FT OF ROCK WAS ESTIMATED FOR MAIN INSTALATION, BUT ONLY 700 F T REQUIRED. THESE ITEMS REDUCED COST OF PROJECT BY $36,000. D. LEMONS 8/24/ 17
15026568401 | INSTALL 350' - 4" PMIP | - | - | - | - | 0.2788% | 96499.62 | 97615.7036 | -1116.0836 | 2017-01-01 | 2017-12-31 | 2017-03-15 | 2017-05-05
17026697800 | INSTALL 200' - 2" PMMP | - | - | - | - | 0.04394% | 15209.12 | 10221.499 | 4987.621 | 2017-01-01 | 2017-12-31 | 2017-04-13 | 2017-04-21
16026671500 | INSTALL 1626' - 2" PMMP | - | - | - | - | 0.2044% | 70759.55 | 97571.8602 | -26812.3102 | 2017-01-01 | 2017-12-31 | 2017-03-14 | 2017-04-20 | COMMENTS RELATED TO 2" PLASTIC PIPE LIC. 512' OF 2"PLASTIC PIPE SHOWN IN THE LIC TOTAL WAS INSTALLED BUT COULD NOT BE USED DUE TO SITE GRADING THAT TOOK PLACE AFTER IT WAS INSTALLED. SHOWED AS LIC BECAUSE THE CONSTRACTOR WAS PAID FOR PIPE INSTALLATION. SITE GRADING PLAN WAS NOT INCLUDED IN PROJECT INFORMATION GIVEN TO CONSTRUCTION.
16026644000 | INSTALL 987' - 2" PMMP | - | - | - | - | 0.169% | 58502.8 | 88008.2014 | -29505.4014 | 2017-01-01 | 2017-12-31 | 2017-03-01 | 2017-04-27
17026700900 | INSTAL MI WIRELESS | - | - | - | - | 0.02642% | 9144.25 | 12405.0828 | -3260.8328 | 2017-01-01 | 2017-12-31 | 2017-04-07 | 2017-04-21 | INSTALLED NEW EFC AND MI-WIRELESS
17026697200 | INSTALL 20' - 4" PMIP | - | - | - | - | 0.02371% | 8206.74 | 16017.9573 | -7811.2173 | 2017-01-01 | 2017-12-31 | 2017-04-25 | 2017-04-26
17026687400 | INSTALL 2550' OF 2"/4" PMIP | - | - | - | - | 0.2782% | 96318.63 | 100949.4852 | -4630.8552 | 2017-01-01 | 2017-12-31 | 2017-04-12 | 2017-05-04 | MAIN COMPLETE ON 4/27, TAPS COMPLETED WEEK OF 5/1 BY DIFFERENT CREW. SPENDLE
17026694200 | INSTALL 125' OF 2"PMMP | - | - | - | - | 0.02344% | 8113.41 | 9731.4713 | -1618.0613 | 2017-01-01 | 2017-12-31 | 2017-05-01 | 2017-05-01
15026581701 | INSTALL 2400'-4" PMMP | - | - | - | - | 0.9864% | 341453.99 | 303011.7908 | 38442.1992 | 2017-01-01 | 2017-12-31 | 2017-03-18 | 2017-06-15
17026687900 | INSTALL 1850' - 2" PMMP | - | - | - | - | 0.2188% | 75751.2 | 77940.9337 | -2189.7337 | 2017-01-01 | 2017-12-31 | 2017-04-24 | 2017-05-12
17026699700 | INSTALL 215' OF 2"PMIP | - | - | - | - | 0.04029% | 13948.02 | 20111.9737 | -6163.9537 | 2017-01-01 | 2017-12-31 | 2017-05-08 | 2017-05-12
16026667300 | ACQUIRE ESMT - EARLYMEADE FARM | - | - | - | - | 0.05116% | 17710.18 | 16071 | 1639.18 | 2017-01-01 | 2017-12-31 | 2016-09-13 | 2017-06-28 | 11-20-17: EASEMENT ACQUISITION ONLY - NO MAIN INSTALLED (BKSLONE) 12/26/17: THIS ACQUISITION WAS NECESSARY BECAUSE THE ORIGINAL EASEMENT ACQU ISITION WAS NOT RECORDED AT THE COURTHOUSE NOR WAS THE LAND OWNER PAID. THI S IS A LEGITIMATE CAPITAL CHARGE AND SINCE IT INCLUDES A PROPERTY UNIT, WE WERE NOT AWARE OF ANOTHER WAY TO PAY FOR IT OR CHARGE IT AND HAVE IT HIT TH E APPROPRIATE ACCOUNTS. MIKE SUCHARSKI ALSO ADVISED THAT HE HAD CHANRGED IN THIS MANNER WHEN EASEMENTS WERE ACQUIRED FOR THE NORTHERN COLUMBUS LOOP. AD DITIONALLY, SINCE WMS REQUIRES A PRESSURE TEST, I RECOMMEND USING THE ORIGI NAL PRESSURE TEST FROM WHEN THE PIPE WAS INSTALLED. HOWEVER, ANY SUBSEQUANT MAOP INQUIRY NEEDS TO REFER TO THE ORIGINAL JOB ORDER FOR THE DOCUMENTATION .
17026699200 | INSTALL CRITICAL VALVE | - | - | - | - | 0.04315% | 14937.72 | 14881.46 | 56.26 | 2017-01-01 | 2017-12-31 | 2017-04-06 | 2018-01-17
17026697500 | INSTALL 5000' OF 2"/4"PMMP | - | - | - | - | 0.1684% | 58309.92 | 123953.9199 | -65643.9999 | 2017-01-01 | 2017-12-31 | 2017-05-08 | 2017-05-18 | UNDERRUN EXPLANATION: THE JOB WAS PLANNED FOR INSTALLATION OF 5000 FEET OF PIPE, BUT ONLY 2390 FEET COULD BE INSTALLED THROUGH NO FAULT OF COLUMBIA'S. A SECOND PHASE TO PICK UP THE ADDITIONAL FOOTAGE WILL BE CREATED WHEN THE S TREETS AND ROADS ARE READY.
15026614900 | INSTALL 1360'-2"/4" PMMP | - | - | - | - | 0.5516% | 190946.66 | 167573.5417 | 23373.1183 | 2017-01-01 | 2017-12-31 | 2017-04-12 | 2017-06-12
16026676100 | INSTALL NEW GMB SETTING | - | - | - | - | 0.111% | 38420.01 | 48263.4451 | -9843.4351 | 2017-01-01 | 2017-12-31 | 2017-04-25 | 2017-05-18 | PROJECT HAD BEEN ON HOLD JUST RELEASED TO CONSTRUCTION
17026708801 | INSTALL 220'- 2" PMMP | - | - | - | - | 0.01203% | 4163.36 | 15643.5628 | -11480.2028 | 2017-01-01 | 2017-12-31 | 2017-05-17 | 2017-05-19
17026711000 | INSTALL 84' - 4" PMLP | - | - | - | - | 0.07058% | 24432.62 | 32414.3088 | -7981.6888 | 2017-01-01 | 2017-12-31 | 2017-05-24 | 2017-06-05 | INSTALL 81' OF 4"PMLP TEST 90LBS 1HR NO LEAKS S/T TIE IN NGF BAR HOLE BANKS NGF INT/EXT CORR OK TIE OVER 2 S/L TEST AS NEW 90LBS 5MIN NO LEAKS S/T TIE IN NGF INSTALL 4 MARKER BALLS INSTALL ANODE WRAP MAIN G.HALE 5-26-17
15026619600 | INSTALL 50'-6" PM | - | - | - | - | 0.04577% | 15843.12 | 21748.8294 | -5905.7094 | 2017-01-01 | 2017-12-31 | 2017-03-08 | 2017-06-15
15026620700 | INSTALL 1585' - 2" PMMP | - | - | - | - | 0.6093% | 210931.38 | 213123.3973 | -2192.0173 | 2017-01-01 | 2017-12-31 | 2017-05-15 | 2017-07-10
16026647500 | INSTALL 1200' - 2" PMMP | - | - | - | - | 0.08316% | 28788.79 | 29478.2739 | -689.4839 | 2017-01-01 | 2017-12-31 | 2017-05-23 | 2017-06-06
17026684900 | INSTALL 9X8X7 CHAIN LINK FENCE | - | - | - | - | 0.0341% | 11804 | 14032.2433 | -2228.2433 | 2017-01-01 | 2017-12-31 |  | 2017-06-06 | FENCE AND GUARD RAIL INSTALLED
16026677700 | INSTALL 165' OF 2"PMMP | - | - | - | - | 0.0338% | 11699.98 | 12723.6791 | -1023.6991 | 2017-01-01 | 2017-12-31 | 2017-06-06 | 2017-06-07
17026693000 | INSTALL 800'-2" PMMP | - | - | - | - | 0.1135% | 39281.68 | 45114.476 | -5832.796 | 2017-01-01 | 2017-12-31 | 2017-06-08 | 2017-06-19
16026661401 | INSTALL 3610' OF 2"/4" PMMP | - | - | - | - | 1.923% | 665544.3 | 725389.3036 | -59845.0036 | 2017-01-01 | 2017-12-31 | 2017-02-15 | 2017-06-26
15026623601 | INSTALL 2,200' OF 6" & 2" PMMP | - | - | - | - | 1.697% | 587467.03 | 382171.6138 | 205295.4162 | 2017-01-01 | 2017-12-31 | 2017-05-19 | 2017-07-28 | 2 SERVICES(569 AND 571 E MAIN) AS WELL AS 558(600 E MAIN) TO BE COMPLETED O N A LATER DATE. STEVE CANOY OVERRUN EXPLANATION: THE JOB ORDER WAS REVISED UNDER THE ASSUMPTION THAT TH E COSTS FOR THE SIDEWALK RESTORATION HAD ALREADY HIT THE JOB. ONCE THESE CO STS SUBSEQUANTLY HIT, THE JOB OVERRAN. LEVEL TWO UPLOADED IN DOCS.
17026686400 | INSTALL 2500' OF 2"PMMP MAIN | - | - | - | - | 0.1952% | 67584.03 | 94056.7395 | -26472.7095 | 2017-01-01 | 2017-12-31 | 2017-06-12 | 2017-06-23
17026697600 | INSTALL 400' - 2" PMMP | - | - | - | - | 0.05563% | 19258.63 | 41766.9893 | -22508.3593 | 2017-01-01 | 2017-12-31 | 2017-06-19 | 2017-06-22
16026678202 | INSTALL 4,045' OF 2"/4" PMMP | - | - | - | - | 2.522% | 873085.51 | 1074028.5443 | -200943.0343 | 2017-01-01 | 2017-12-31 | 2017-12-12 | 2017-12-12 | UNDERRUN EXPLANATION: WAITING FOR THE REMAINDER OF THE PAVING TO BE APPLED TO THE JOB ORDER. 2/27/18 STILL WAITING. 3/28/18 STILL WAITING. 4/20/18 GES. THIS PROJECT UNDERRAN DUE TO AN INVOICING ERROR. A REFUND WAS ISSUED TO TH E CONTRACTOR. CSPARKS 6/25/18
17026703600 | INSTALL 100' OF 2"PMIP | - | - | - | - | 0.0653% | 22604.66 | 17117.5422 | 5487.1178 | 2017-01-01 | 2017-12-31 | 2017-06-22 | 2017-07-03
17026716000 | INSTALL 24'-3" PMLP | - | - | - | - | 0.04247% | 14703.06 | 8808.8705 | 5894.1895 | 2017-01-01 | 2017-12-31 | 2018-03-28 | 2018-03-28 | INSTALLED 23' 3" PLASTIC, OPEN TRENCH, PRESSURE TESTED MAINLINE ON SITE 90# FOR 1 HR PER FOL APPROVAL, SOAP TEST LAST FITTING NO LEAKS, INSTALLED WIRE
16026656002 | INSTALL 2655' OF 2"/6" PMMP | - | - | - | - | 1.413% | 488968.73 | 492362.7859 | -3394.0559 | 2017-01-01 | 2017-12-31 | 2017-08-16 | 2017-08-23
17026706800 | INSTALL 170' - 4"/6" PMLP | - | - | - | - | 0.1739% | 60202.98 | 45554.3015 | 14648.6785 | 2017-01-01 | 2017-12-31 | 2017-06-23 | 2017-07-14
17026701300 | REPLACE FI 630W/ FI 627 | - | - | - | - | 0.004169% | 1443.22 | 618.8749 | 824.3451 | 2017-01-01 | 2017-12-31 | 2017-07-12 | 2017-07-12 | MAOP IS 190 PSIG FOR CFARIS
17026711400 | INSTALL 200'-2" PMIP | - | - | - | - | 0.1348% | 46680.08 | 31262.9008 | 15417.1792 | 2017-01-01 | 2017-12-31 | 2017-06-28 | 2017-07-14
17026717600 | INSTALL PRESSURE RELIEF VALVE | - | - | - | - | 0.0001904% | 65.91 | 1195.9784 | -1130.0684 | 2017-01-01 | 2017-12-31 |  | 2017-07-15 | INSTALLED NEW PRESSURE RELIEF REGULATOR
17026710801 | INSTALL 15'-10" CSMP | - | - | - | - | 0.2698% | 93404.33 | 146302.2212 | -52897.8912 | 2017-01-01 | 2017-12-31 | 2017-06-29 | 2017-07-17 | UNDERRUN EXPLANATION: THE HARD SURFACE REPAIRS HAVE NOT BEEN MADE YET. THIS IS A PUBLIC IMPROVEMENT PROJECT SO IT'S POSSIBLE THOSE REPAIRS WILL NOT BE NECESSARY.
16026649702 | INSTALL 930'-2"&4" PMMP | - | - | - | - | 0.5907% | 204470.07 | 192331.9619 | 12138.1081 | 2017-01-01 | 2017-12-31 | 2017-06-30 | 2017-08-01 | LABORER HRS WAS FOR WHEELBARROWING DIRT AND GRAVEL IN AND OUT OF JOB SITE OVERRUN EXPLANATION: THE RIGHT OF WAY PAYMENT WAS $1200 HIGHER THAN ESTIMAT ED AND THE SURVEY COSTS WERE ABOUT $12,000 HIGHER THAN ESTIMATED. ALSO THE TEMPORARY AND PERMANENT PAVING WAS $24,000 HIGHER THAN ESTIMATED.
17026714800 | INSTALL 212'-4" PMIP | - | - | - | - | 0.04274% | 14794.6 | 27227.5928 | -12432.9928 | 2017-01-01 | 2017-12-31 | 2017-07-17 | 2017-07-19
17026719700 | INSTALL 150'-2" PMIP | - | - | - | - | 0.002788% | 965.13 | 14399.3803 | -13434.2503 | 2017-01-01 | 2017-12-31 | 2017-08-24 | 2017-08-24 | INSTALLED 151' OF 2" PLASTIC AND 2' OF 3" PLASTIC TESTED 100 PSIG 1 HR. AND SOAP TESTED TIE INS ON BOTH ENDS AT OPERATING PRESSURE 15 MIN
16026680300 | INSTALL NEW GMB W/EFC | - | - | - | - | 0.2621% | 90714.69 | 83331.7941 | 7382.8959 | 2017-01-01 | 2017-12-31 | 2017-03-08 | 2017-07-24 | JOB LATE DUE TO CUSTOMER NOT READY AND WAITING ON METER AND REGULATOR SETTING FROM BANGS
16026663201 | INSTALL 2100' OF 2" PMMP | - | - | - | - | 0.3574% | 123707.93 | 125703.4856 | -1995.5556 | 2017-01-01 | 2017-12-31 | 2017-07-06 | 2017-08-01
16026666700 | RELOCATE 12" HP MAIN | - | - | - | - | 0.4697% | 162610.4 | 120312.0436 | 42298.3564 | 2017-01-01 | 2017-12-31 | 2017-07-06 | 2017-07-27 | LEVEL 2 BUDGET VARIANCE COMPLETED 12/6/17 AND LOADED INTO WMSDOCS. D.LEMONS
17026686100 | INSTALL 315' OF 4" PMMP | - | - | - | - | 0.1839% | 63652.06 | 71845.6471 | -8193.5871 | 2017-01-01 | 2017-12-31 | 2017-06-08 | 2017-07-31
16026633101 | INSTALL 425' OF 2"PMMP MAIN | - | - | - | - | 0.09336% | 32317.59 | 38135.1802 | -5817.5902 | 2017-01-01 | 2017-12-31 | 2017-07-25 | 2017-08-01
13026482501 | INSERT 1100'-8"PMMP | - | - | - | - | 0.4126% | 142816.33 | 99599.5093 | 43216.8207 | 2017-01-01 | 2017-12-31 | 2017-07-10 | 2017-09-12 | TWALKER/KY 02-13-18:PROJECT OVER RUN DUE TO $40,000 HIGHER CONTRACT COST
16026655802 | INSTALL 720' OF 2" PMMP | - | - | - | - | 1.189% | 411435.23 | 260189.2446 | 151245.9854 | 2017-01-01 | 2017-12-31 | 2017-07-18 | 2017-08-03 | OVERRUN EXPLANATION: MORE MILL AND OVERLAY ASPHALT RESTORATION WAS COMPLETE D THAN ANTICPATED. 70 HOURS OF ADDITIONALLY FLAGGING TIME WAS ALSO REQUIRED DURING THE RESTORATION. CJS
17026711900 | INSTALL 215' OF 2"PMMP MAIN | - | - | - | - | 0.03032% | 10496.29 | 13768.2916 | -3272.0016 | 2017-01-01 | 2017-12-31 | 2017-08-07 | 2017-08-15
16026651800 | INSTALL 778' 6" PMLP | - | - | - | - | 0.3815% | 132071.6 | 206269.2792 | -74197.6792 | 2017-01-01 | 2017-12-31 | 2017-07-05 | 2017-09-01 | UNDERRUN EXPLANATION: THIS PROJECT IS UNDERRUNNING BECAUSE THE HARD SURFACE REPAIRS HAVE NOT BOOKED YET.
16026655000 | PM RELOCATE 5600'-12"CSHP (TC) | - | - | - | - | 0.8536% | 295488.34 | 4499999.6127 | -4204511.2727 | 2017-01-01 | 2017-12-31 | 2017-04-13 | 2017-09-07
17026687100 | INSTALL 2700' OF 2"/4"PMMP | - | - | - | - | 0.176% | 60939.83 | 68305.7495 | -7365.9195 | 2017-01-01 | 2017-12-31 | 2017-08-03 | 2017-08-15
17026718200 | INSTALL 175' - 2" PMMP | - | - | - | - | 0.008242% | 2853.16 | 16047.9352 | -13194.7752 | 2017-01-01 | 2017-12-31 | 2017-08-10 | 2017-08-15
17026700600 | INSTALL 250' OF 4"PMMP MAIN | - | - | - | - | 0.04389% | 15193.48 | 19721.3133 | -4527.8333 | 2017-01-01 | 2017-12-31 | 2017-08-14 | 2017-08-17
17026710701 | INSTALL 300' OF 2"PMMP | - | - | - | - | 0.05896% | 20410.26 | 24493.7659 | -4083.5059 | 2017-01-01 | 2017-12-31 | 2017-08-16 | 2017-08-28
16026664101 | INSTALL 1450' OF 2'/4"PMMP | - | - | - | - | 0.3444% | 119218.81 | 129586.2976 | -10367.4876 | 2017-01-01 | 2017-12-31 | 2017-08-10 | 2017-08-24
17026693800 | INSTALL CHAIN LINK FENCE | - | - | - | - | 0.01836% | 6356.97 | 24081.1213 | -17724.1513 | 2017-01-01 | 2017-12-31 | 2017-08-01 | 2017-08-29
17026714200 | INSTALL 300' - 2" PMMP | - | - | - | - | 0.05455% | 18883.56 | 18413.9137 | 469.6463 | 2017-01-01 | 2017-12-31 | 2017-08-15 | 2017-08-29
17026716800 | INSTALL 180'-2" PMIP | - | - | - | - | 0.03601% | 12467.15 | 14116.6288 | -1649.4788 | 2017-01-01 | 2017-12-31 | 2017-08-28 | 2017-08-29
16026670800 | INSTALL 2350' OF 12" CSHP | - | - | - | - | 0.93% | 321937.01 | 403531.8115 | -81594.8015 | 2017-01-01 | 2017-12-31 | 2017-08-10 | 2017-09-29 | 1 TEST STATION INSTALLED BY CONSTRUCTION COORDINATOR PER CORROSION TECH REC OMMENDATION DURING CONSTRUCTION. SEE JOB ORDER SKETCH. DGRIFFI 01/02/2018 TWALKER/KY 02-13-18: JOB COST UNDER RUN DUE TO SEGA WAS $53,800 LESS THAN ESTIMATED. ALSO CONSTRUCTION COORD TIME WAS LESS AND SAVE $5000
16026674401 | PM INSTALL 26,000'-6"/8" HDPE | - | - | - | - | 6.486% | 2245431.65 | 2985687.0715 | -740255.4215 | 2017-01-01 | 2017-12-31 | 2017-05-09 | 2017-08-31
17026698000 | PM MIDWAY INTALL REG STATION | - | - | - | - | 0.8406% | 290986.4 | 367126.1581 | -76139.7581 | 2017-01-01 | 2017-12-31 | 2017-08-09 | 2017-08-30
17026701500 | REPLACE FI 630 W/ FI 627 | - | - | - | - | 0.002654% | 918.87 | 1206.8749 | -288.0049 | 2017-01-01 | 2017-12-31 |  | 2017-08-30 | MAOP IS 939 PSIG PER CFARIS.
17026729800 | PM HP INLET PIPE - MIDWAY PROJ | - | - | - | - | 0.008866% | 3069.07 | 0 | 3069.07 | 2017-01-01 | 2017-12-31 | 2017-04-18 | 2017-08-31
17026693300 | INSTALL NEW CHAIN LINK FENCE | - | - | - | - | 0.02709% | 9378.26 | 19185.1213 | -9806.8613 | 2017-01-01 | 2017-12-31 | 2017-08-01 | 2017-08-31
17026724400 | INSTALL EFC | - | - | - | - | 0.0001262% | 43.68 | 313.6411 | -269.9611 | 2017-01-01 | 2017-12-31 | 2017-10-03 | 2017-09-06 | OWNED BY TRANSCANADA AND IS NOT MAPPED
17026705001 | INSTALL 340' - 4" PMLP | - | - | - | - | 0.1569% | 54316.39 | 26493.1289 | 27823.2611 | 2017-01-01 | 2017-12-31 | 2017-09-07 | 2017-09-14 | GATHERED UP PARTS FOR MAIN LINE JOB START MONDAY COMPLETED JO AFTER RETURNING FROM VACATION UNABLE TO COMPLETE BEFORE 09/1 9/17 OTHER POUCH AND COMPUTER PROBLEMS UN ABLE TO COMPLETE WORK ON COMPUTER
17026702200 | REPLACE FI 630 W/ FI 627 | - | - | - | - | 0.004911% | 1700.09 | 1793.8749 | -93.7849 | 2017-01-01 | 2017-12-31 | 2017-09-08 | 2017-09-08 | REMOVED FH 630 BIG JOE REGULATORS INSTALLED FH627 REGS
16026665700 | INSTALL 200' - 2" PMMP | - | - | - | - | 0.3533% | 122294.32 | 45883.6065 | 76410.7135 | 2017-01-01 | 2017-12-31 | 2017-07-20 | 2017-09-27 | OVERRUN EXPLANATION: IT WAS RECOGNIZED THAT THIS ONE WAS GOING TO OVERRUN A ND A REVISION WAS PREPARED, BUT THE JOB ORDER WAS COED BEFORE THE REVISION COULD BE PROCESSED. THE REASON THE CHANGE REQUEST WAS INITIATED WAS BECAUSE IT WAS NECESSARY TO USE FLOWABLE FILL AND MILL AND PAVE THAT WAS NOT ORIGIN ALLY ESTIMATED. ALSO FOUND 60 TONS OF SAND AND 70 TONS OF STONE AND 280 HOU RS OF FLAGGER AND 46 CREW HORS WERE NOT ESTIMATED.
17026716600 | INSTALL 90' OF 2"PMMP MAIN | - | - | - | - | 0.01495% | 5175.81 | 10790.4825 | -5614.6725 | 2017-01-01 | 2017-12-31 | 2017-09-11 | 2017-09-12
15026610900 | INSTALL REGS & HEATER | - | - | - | - | 0.02581% | 8933.19 | 5013.8354 | 3919.3546 | 2017-01-01 | 2017-12-31 | 2017-10-18 | 2017-09-14
17026727100 | INSTALL 50'-4" PMLP | - | - | - | - | 0.04647% | 16086.02 | 24324.285 | -8238.265 | 2017-01-01 | 2017-12-31 |  | 2017-10-18
17026719300 | INSTALL 250' OF 2"PMMP | - | - | - | - | 0.0416% | 14399.94 | 17006.8829 | -2606.9429 | 2017-01-01 | 2017-12-31 | 2017-09-13 | 2017-09-21
17026718100 | INSTALL 100' - 4" PMMP | - | - | - | - | 0.07227% | 25016.23 | 23282.9137 | 1733.3163 | 2017-01-01 | 2017-12-31 | 2017-09-18 | 2017-09-23
16026671001 | INSTALL 8125' OF 2"PMMP | - | - | - | - | 1.378% | 477092.94 | 524789.771 | -47696.831 | 2017-01-01 | 2017-12-31 | 2017-02-20 | 2017-10-03
17026712600 | INSTALL 875' - 2" PMMP | - | - | - | - | 0.2238% | 77483.07 | 114909.1688 | -37426.0988 | 2017-01-01 | 2017-12-31 | 2017-08-31 | 2017-09-25 | TTOY 02-13-18: JOB UNDER RUN DUE TO LESS PAVING/HARD SURFACES REPAIRS REQUIRED SAVING $20,000 IN CONTRACT COST ALSO SEGA WAS $12,000 LESS THAN ESTIMATE.
17026694101 | INSTALL 3400' - 4" PMIP | - | - | - | - | 0.4953% | 171444.23 | 219406.6529 | -47962.4229 | 2017-01-01 | 2017-12-31 | 2017-08-01 | 2017-12-13 | DUE TO LANDOWNERS AND COUNTY ROAD DEPARTMENT, PROJECT WAS SHORTENED BY 900 FEET (24%). THIS LED TO SAVINGS OF 25% ON MATERIAL ($2500), 21% ON CONTRAC T ($27000), 30% ON LABOR ($6000). OTHER COST WERE OVER ESTIMATED BY $20000 AS A 10% CONTINGENCY WAS NOT REMOVED DURING REVISION. THESE COST AND OTHER FACTORS CAUSED SEGA TO BE OVERESTIMATED BY $23500. FOR APPROXIMATE TOTAL OF $79000 IN COST UNDERRUN FROM ESTIMATED.
17026729500 | INSERT 110'-3" PMIP IN 4" CI | - | - | - | - | 0.0008677% | 300.37 | 17473.5317 | -17173.1617 | 2017-01-01 | 2017-12-31 | 2017-09-29 | 2017-09-29 | INSTALLED NEW MAIN TO REPL CI TESTED NEW PL ML @ 90 # FOR 1 HR SOAP TESED C CONNECTION POINTS @ OP
17026727700 | INSTALL 30' OF 2"PMMP MAIN | - | - | - | - | 0.01912% | 6617.58 | 4311.4728 | 2306.1072 | 2017-01-01 | 2017-12-31 | 2017-09-27 | 2017-10-10
16026643001 | INSTALL 490'- 8"& 2" PHHP | - | - | - | - | 0.4389% | 151949.3 | 158886.2976 | -6936.9976 | 2017-01-01 | 2017-12-31 | 2017-09-11 | 2017-10-04
16026682101 | INSTALL 1025' OF 2"PMMP | - | - | - | - | 0.05654% | 19573.27 | 44106.469 | -24533.199 | 2017-01-01 | 2017-12-31 | 2017-09-22 | 2017-09-29
17026701700 | REPLACE FI 630 W/ FI 627 | - | - | - | - | 0.004695% | 1625.1 | 1793.8749 | -168.7749 | 2017-01-01 | 2017-12-31 | 2017-10-04 | 2017-10-04
16026670602 | INSTALL 7750'OF 2"PMMP | - | - | - | - | 5.26% | 1820890.47 | 1815026.263 | 5864.207 | 2017-01-01 | 2017-12-31 | 2017-10-24 | 2017-11-29
17026730300 | INSTALL 80' - 3" PMLP | - | - | - | - | 0.003741% | 1295.04 | 29266.3656 | -27971.3256 | 2017-01-01 | 2017-12-31 |  | 2017-12-04
16026646402 | INSTALL NEW WATER BATH HEATER | - | - | - | - | 0.2036% | 70477.8 | 82741.9513 | -12264.1513 | 2017-01-01 | 2017-12-31 | 2017-12-06 | 2017-10-10 | 2/11/18: UNDERRUN EXPLANATION - MANY INSTALL CHARGES WERE INCORRECTLY LODGED AGAINST THE THE RETIRE JOB ORDER (16-0266465-00), HOWEVER, I HAD PLANT ACCOUNTING (DYLAN KRANER) TRANSFER MUCH OF IT BACK TO THE INSTALL JOB ORDER (16-0266464-02) ON 12/28/17 AND THAT'S WHAT POWER PLANT CURRENTLY REFLECTS ($68,370 ACTUAL TOTAL COST) RESULTING IN A ($17,372) COST VARIANCE OR -17% PERCENT VARIANCE (BKSLONE).
17026705900 | INSTALL 160' OF 2"PMMP | - | - | - | - | 0.03564% | 12336.08 | 17619.8829 | -5283.8029 | 2017-01-01 | 2017-12-31 | 2017-09-28 | 2017-10-10
17026714400 | INSTALL 1100' - 2" PMMP | - | - | - | - | 0.112% | 38759.39 | 62676.1688 | -23916.7788 | 2017-01-01 | 2017-12-31 | 2017-10-02 | 2017-10-12
15026598602 | INSTALL 740' - 2"/4" PMIP | - | - | - | - | 0.1846% | 63907.98 | 59728.1343 | 4179.8457 | 2017-01-01 | 2017-12-31 | 2017-09-13 | 2017-10-17
17026731900 | INSTALL 2 FISHER 627S | - | - | - | - | 0% | 0 | 2596.1759 | -2596.1759 | 2017-01-01 | 2017-12-31 |  | 2017-10-12
16026656900 | INSTALL 5150' OF 2" PMMP | - | - | - | - | 3.435% | 1189015.29 | 1133000.911 | 56014.379 | 2017-01-01 | 2017-12-31 | 2017-06-20 | 2017-10-09
17026713600 | INSTALL 625' OF 2"PMMP | - | - | - | - | 0.07632% | 26419.97 | 24176.891 | 2243.079 | 2017-01-01 | 2017-12-31 | 2017-10-03 | 2017-10-18
17026698200 | PM WOODFORD RESERVE MIDWAY | - | - | - | - | 0.1438% | 49779.12 | 101156.7132 | -51377.5932 | 2017-01-01 | 2017-12-31 | 2017-08-24 | 2017-10-19 | 6" VALVE AND BOX ARE SHOWN ON THE 563 JO
17026720300 | INSTALL 275'-2" PMMP | - | - | - | - | 0.03293% | 11399.35 | 18240.4601 | -6841.1101 | 2017-01-01 | 2017-12-31 | 2017-09-22 | 2017-10-19
15026595002 | INSTALL 260'-4"-CS/PMMP | - | - | - | - | 0.1995% | 69058.58 | 94831.2335 | -25772.6535 | 2017-01-01 | 2017-12-31 | 2017-10-11 | 2017-10-20 | 2/11/18: UNDERRUN EXPLANATION - ROCK WAS ANTICIPATED REQUIRING A MEDIUM DUTY TRACK HOE BUT ALL ROCK ENCOUNTERED WAS REMOVED VIA A BACKHOE, THEREFORE, NO PAYMENT FOR BREAKING ROCK OR TRACKHOE. THIS ALSO RESULTED IN LESS STONE BACKFILL REQUIRED. IN ADDITION, 8" STEEL CASING WAS PLANNED BUT ENDED UP NOT INSTALLING WHICH REMOVED ALL UNITS ASSOCIATED WITH THE 8" STEEL INCLUDING THE PLANNED 16 HOURS OF MAINS & SERVICES 4 MAN CREW. LASTLY, DUE TO ABOVE, LESS COMPANY LABOR INVOLVED THEREBY REDUCING COSTS INCLUDING OH'S. (BKSLONE). PROJECT HAS NOT BEEN FINAL BILLED YET BECAUSE THE ROAD CONTRACTOR REQUESTED A DESIGN CHANGE THAT MAY AFFECT OUR PIPE. WE PLAN TO FINAL BILL BEFORE 10/2 0/2018.
16026641700 | INSTALL 4176' - 6" PM | - | - | - | - | 1.399% | 484210.88 | 828583.7051 | -344372.8251 | 2017-01-01 | 2017-12-31 | 2017-09-05 | 2017-12-18 | UNDERRUN EXPLANATION: WAITING TO SEE IF THERE IS ANYMORE PAVING TO HIT IN 2 018. 2/27/18 UNDERRUN EXPLANATION: SIGNIFICANTLY LESS PAVING HIT THAN WAS ESTIMATED.
17026692300 | INSTALL 246'-8"/4" PMMP | - | - | - | - | 0.3119% | 107953.84 | 88750.5953 | 19203.2447 | 2017-01-01 | 2017-12-31 | 2017-09-23 | 2017-10-28
15026568600 | INSTALL 350' - 4" PMLP | - | - | - | - | 0.2343% | 81116.67 | 86877.8294 | -5761.1594 | 2017-01-01 | 2017-12-31 | 2017-10-13 | 2017-11-09
16026654800 | INSTALL 1200' OF 2"PMMP | - | - | - | - | 0.4033% | 139604.77 | 150278.8346 | -10674.0646 | 2017-01-01 | 2017-12-31 | 2017-08-31 | 2017-11-16
17026698700 | INSTALL NEW REGULATOR & ORIFIC | - | - | - | - | 0.01987% | 6877.85 | 3227.9947 | 3649.8553 | 2017-01-01 | 2017-12-31 | 2017-06-28 | 2017-10-27
17026684200 | INSTALL 500' - 2" PMMP | - | - | - | - | 0.07414% | 25665.56 | 52559.7685 | -26894.2085 | 2017-01-01 | 2017-12-31 | 2017-09-22 | 2017-10-31
12026410402 | INSTALL 3400' OF 12"CSHP | - | - | - | - | 2.776% | 960931.92 | 954076.3495 | 6855.5705 | 2017-01-01 | 2017-12-31 | 2017-11-07 | 2017-11-13
17026712800 | INSTALL NEW SKID GMB SETTING | - | - | - | - | 0.1176% | 40726.4 | 75608.2507 | -34881.8507 | 2017-01-01 | 2017-12-31 | 2017-07-05 | 2017-11-01 | DELAY WAS DUE TO CUSTOMER NOT READY TWALKER/KY 03-28-18: JOB UNDER RUN DUE TO GMB SETTING COST WAS LESS THAN BANGS ESTIMATE BY $25,000, CURRENTLY THIS JOB COST SHOW $55,000 IN POWERPLANT. FINALLY SEGA WAS $5000 LESS THAN ESTIMATE.
17026703001 | INSTALL 200' - 4" CSHP | - | - | - | - | 0.2804% | 97075 | 60636.623 | 36438.377 | 2017-01-01 | 2017-12-31 | 2017-08-11 | 2017-11-02 | THE ENVIRONMENTAL COSTS FOR THE ENTIRE PROJECT WERE CHARGED TO THIS JOB ORD ER WHICH IS THE INLET PIPING TO THE REGULATOR STATION. THIS CAUSED $20,000 OF THE OVERRUN. THE REST IS THAT THE PROJECT TOOK LONGER THAN ESTIMATED. CS PARKS 6/25/18
17026707500 | INSTALL CWT HEATER & INSTR. | - | - | - | - | 1.037% | 358866.68 | 292410.5473 | 66456.1327 | 2017-01-01 | 2017-12-31 | 2017-08-10 | 2017-11-02 | PIPING INSTALLED IS ALL ABOVE GROUND PLEASE SEE BUDGET VARIANCE EXPLANATION IN WMSDOCS. D.LEMONS 4/12/18 OVERRUN EXPLANATION: OVERHEADS WERE THE MAJOR CONTRIBUTOR TO THE COST OVERR UN. THERE WAS AN OVERHEAD ADJUSTMENT IN NOVEMBER 2017 THAT WAS NOT EXPECTED OR PLANNED. THIS ADJUSTMENT CAUSED A $62K OVERRUN. IT APPEARS THAT ACCOUNTI NG HAD UNDERCOLLECTED ON OVERHEADS AND THEY USED THE REMAINING OPEN JOB ORD ERS TO CORRECT THAT UNDERCOLLECTION.
16026649200 | INSERT 275' - 2" PMLP | - | - | - | - | 0.1412% | 48885 | 24953.762 | 23931.238 | 2017-01-01 | 2017-12-31 | 2017-10-31 | 2017-11-14
17026703201 | INSTALL 3925' - 2"/6" PMMP | - | - | - | - | 3.531% | 1222203.66 | 1034520.2055 | 187683.4545 | 2017-01-01 | 2017-12-31 | 2017-09-15 | 2017-12-28
17026708200 | INSTALL NEW REGULATOR STATION | - | - | - | - | 0.3359% | 116264.78 | 98438 | 17826.78 | 2017-01-01 | 2017-12-31 | 2017-07-31 | 2017-11-06
17026711200 | INSTALL 3500' OF 2"/4"PMMP | - | - | - | - | 0.2423% | 83862.34 | 72064.2531 | 11798.0869 | 2017-01-01 | 2017-12-31 | 2017-08-15 | 2017-11-07
17026712900 | INSTALL 1575' 4"/6" PMMP | - | - | - | - | 0.5798% | 200713.26 | 181779.7592 | 18933.5008 | 2017-01-01 | 2017-12-31 | 2017-08-21 | 2017-11-08
16026668801 | INSTALL TWO 2" SS - FITTINGS | - | - | - | - | 0.2084% | 72142.72 | 53972.0925 | 18170.6275 | 2017-01-01 | 2017-12-31 | 2017-11-03 | 2017-11-28
17026703400 | INSTALL 900' - 2" PMMP | - | - | - | - | 0.4119% | 142580.93 | 188603.7194 | -46022.7894 | 2017-01-01 | 2017-12-31 | 2017-10-23 | 2017-11-27 | TTOY 02/13/18: JOB UNDER RUN DUE TO LESS PAVING/HARD SURFACE REPAIRS SAVING $45,000 IN CONTRACT COST.
17026708001 | REPLACE SETTING VALVES | - | - | - | - | 0.06069% | 21007.83 | 12811.7438 | 8196.0862 | 2017-01-01 | 2017-12-31 | 2017-11-06 | 2017-11-09 | REPLACED INLET, OUTLET AND BYPASS VALVES
17026735300 | INSTALL 625' OF 2"PMMP MAIN | - | - | - | - | 0.03912% | 13540.77 | 15553.7103 | -2012.9403 | 2017-01-01 | 2017-12-31 | 2017-11-14 | 2017-11-15
17026691502 | INSTALL 1600' OF 2"PMMP | - | - | - | - | 0.9873% | 341758.92 | 305382.3485 | 36376.5715 | 2017-01-01 | 2017-12-31 | 2017-11-14 | 2017-11-16
17026694300 | INSTALL 80'-6"PMLP MAIN | - | - | - | - | 0.139% | 48115.93 | 24679.365 | 23436.565 | 2017-01-01 | 2017-12-31 | 2017-11-13 | 2017-11-17 | INSTALLED 20' SECTION OF 6" PE MAIN. TESTED @ 90 PSIG FOR 1 HOUR. SOAP TEST ED TIE-INS.
17026725400 | INSTALL FISHER 627 REGULATORS | - | - | - | - | 0.005547% | 1920.05 | 3074.2822 | -1154.2322 | 2017-01-01 | 2017-12-31 | 2017-11-18 | 2017-11-18
16026631900 | INSTALL CHAIN LINK FENCE | - | - | - | - | 0.02513% | 8698 | 15948.2999 | -7250.2999 | 2017-01-01 | 2017-12-31 |  | 2017-11-22 | DELAY DUE TO ROAD CONSTRUCTION PROJECT
17026739900 | INSTALL NEW RELIEF VALVE | - | - | - | - | 0.01268% | 4390.46 | 8756.6523 | -4366.1923 | 2017-01-01 | 2017-12-31 | 2017-11-22 | 2017-11-22 | INSTALLED RELIEF REGULATOR
13026477201 | INSTALL 3435' - 2"/4" PMMP | - | - | - | - | 2.257% | 781236.18 | 719646.2705 | 61589.9095 | 2017-01-01 | 2017-12-31 | 2017-11-07 | 2017-11-29
17026718400 | INSTALL 175' OF 2"PMMP | - | - | - | - | 0.06598% | 22840.5 | 11350.2056 | 11490.2944 | 2017-01-01 | 2017-12-31 | 2017-10-03 | 2017-11-27
17026740000 | INSTALL 210'-2" PMMP | - | - | - | - | 0.1178% | 40794.67 | 22421.8479 | 18372.8221 | 2017-01-01 | 2017-12-31 |  | 2017-11-27 | CONTRACTOR COST ASSOICATED TO THE O&M JOB ORDER TO MAINTAIN COST ON DAMAGE REPORT/JO. PER OPERATIONS REQUEST FOR REPAIR COST TO BE ACCESSABLE FOR BILL ING TO DAMAGING CONTRACTOR. DGRIFFI/GSULLIVAN 12/27/2017
16026681900 | INSTALL 1400'-2"&4" PMIP | - | - | - | - | 0.7344% | 254210.82 | 259689.9094 | -5479.0894 | 2017-01-01 | 2017-12-31 | 2017-07-17 | 2017-12-01
17026686900 | INSTALL 662'-4"/6" PMLP | - | - | - | - | 0.7585% | 262581.4 | 113502.8897 | 149078.5103 | 2017-01-01 | 2017-12-31 | 2017-10-24 | 2017-12-15 | SBRADY 6/14/18 LEVEL TWO VARIENCE REPORT ADDED TO WMS DOCS. JOB OVER RUN DU E TO PAVING AND HARD SURFACE RESTORATION ADDED $80,000 SEGA INCREASED BY $5 6,000
17026693500 | INSTALL REG STATION FENCE | - | - | - | - | 0.02836% | 9816.17 | 11814.9433 | -1998.7733 | 2017-01-01 | 2017-12-31 | 2017-05-08 | 2017-11-29
17026698300 | PM MIDWAY GMB FENCING | - | - | - | - | 0.004461% | 1544.33 | 26767 | -25222.67 | 2017-01-01 | 2017-12-31 | 2017-10-25 | 2017-11-29 | WAITING ON FENCING COMPANY
17026729700 | INSTALL 475' OF 2"PMIP MAIN | - | - | - | - | 0.07585% | 26258.47 | 23295.0099 | 2963.4601 | 2017-01-01 | 2017-12-31 | 2017-11-27 | 2017-11-30
17026738800 | PM INSTALL FENCING AT POD | - | - | - | - | 0% | 0 | 0 | 0 | 2017-01-01 | 2017-12-31 |  | 2017-11-29
16026673100 | INSTALL 510' - 2" PMLP | - | - | - | - | 0.4985% | 172550.71 | 104572.6911 | 67978.0189 | 2017-01-01 | 2017-12-31 | 2017-10-31 | 2017-12-18 | TTOY 3/28/18: JOB OVER RUN DUE TO EXTRA PAVEMENT REQUIREMENTS BY CITY TO MILL AND OVERLAY FOR $30,000, AND SEGA WAS ADDITIONAL $35,000 MORE THAN PLANNED.
17026733700 | INSTALL 300' - 2" PMMP | - | - | - | - | 0.06182% | 21400.7 | 22363.1243 | -962.4243 | 2017-01-01 | 2017-12-31 | 2017-11-13 | 2017-12-01
17026711801 | INSTALL 2200' OF 2"/4"PMMP | - | - | - | - | 0.146% | 50529.35 | 53791.6609 | -3262.3109 | 2017-01-01 | 2017-12-31 | 2017-08-25 | 2017-12-05
17026736900 | INSTALL NEW MI EFC | - | - | - | - | 0.03767% | 13040.95 | 10065.2174 | 2975.7326 | 2017-01-01 | 2017-12-31 | 2017-12-05 | 2017-12-05
17026721401 | INSTALL 275' OF 2"PMMP | - | - | - | - | 0.04414% | 15278.84 | 13134.625 | 2144.215 | 2017-01-01 | 2017-12-31 | 2017-12-06 | 2017-12-07
18026772100 | INSTALL 5' OF 2"PMMP MAIN | - | - | - | - | 0.03621% | 12533.17 | 8723.7386 | 3809.4314 | 2017-01-01 | 2017-12-31 | 2017-12-07 | 2018-05-30
17026692501 | INSTALL 100' - 12" CSHP | - | - | - | - | 0.6466% | 223830.78 | 169516.8385 | 54313.9415 | 2017-01-01 | 2017-12-31 | 2017-12-06 | 2017-12-12 | TTOY 6/19/18 - JOB OVER RUN DUE TO LENGTH OF JOB BECAUSE OF SITE CONDITIONS , SEGA 30,000 MORE THAN PLANNED, LESS MATERIAL REQUIRED THAN PREVIOUSLY PLANNED
17026717800 | INSTALL GMB SETTING | - | - | - | - | 0.4474% | 154867.73 | 99765 | 55102.73 | 2017-01-01 | 2017-12-31 | 2017-10-18 | 2019-01-17 | TEMPORARY SETTING INSTALLED AND PLACED IN SERVICE 12/11/17 WAITING ON NEW METER SKID FROM BANGS ONCE SETTING ARRIVED HAD TO WAIT TO GET ON THE SCHEDULE FOR CONSTRUCTION SERVICES OVERRUN EXPLANATION: FURTHER INQUIRY IS REQUIRED.
17026722601 | INSTALL 125' - 4" PMLP | - | - | - | - | 0.1501% | 51971.62 | 23824.8796 | 28146.7404 | 2017-01-01 | 2017-12-31 | 2017-11-29 | 2017-12-11
16026633401 | INSTALL 750' OF 4" PMIP | - | - | - | - | 0.442% | 152993.85 | 175821.3472 | -22827.4972 | 2017-01-01 | 2017-12-31 | 2017-11-10 | 2017-12-14 | UNDERRUN EXPLANATION: CONTRACTOR WAS ABLE TO DIRECTIONALLY BORE MUCH MORE T HAN ORIGINALLY ANTICIPATED TO AVOID ALMOST ALL OF THE PAVING.
17026737700 | INSTALL 275' OF 2"PMMP MAIN | - | - | - | - | 0.06109% | 21146.51 | 15276.75 | 5869.76 | 2017-01-01 | 2017-12-31 | 2017-12-12 | 2017-12-18
17026741700 | INSTALL 3-4" VALVES METER RUN | - | - | - | - | 0.1224% | 42360.31 | 8182.5529 | 34177.7571 | 2017-01-01 | 2017-12-31 | 2017-12-13 | 2017-12-18 | TWALKER/KY 04-20-18: JOB OVER RUN DUE TO PROJECT COULD NOT BE WORK AS PLANNED DUE TO VALVE ON SETTING WOULD NOT CLOSE WHICH FORCED THE NEED FOR TEMP REG STATION TO USED IN ORDER TO MAINTAIN FEED TO HOSPITAL WHICH INCREASED COMPANY LABOR BY $9700, CONTRACTOR WAS USED COST $9400 SEGA INCREASED BY $11500 I TRIED TO REVISE JOB ORDER BUT WMS WOULD NOT ALLOW ME AT THE TIME.
17026711501 | INSTALL 1200' - 2" PMMP | - | - | - | - | 0.2714% | 93954.9 | 88897.3337 | 5057.5663 | 2017-01-01 | 2017-12-31 | 2017-12-05 | 2017-12-19
15026594800 | NEW BUILDING FOR REG SITE | - | - | - | - | -0.01165% | -4034.45 | 66807.0064 | -70841.4564 | 2017-01-01 | 2017-12-31 | 2017-02-01 | 2017-12-29 | PROJECT HELD UP WAITING ON CITY
17026713700 | INSTALL CONTROLLS | - | - | - | - | 0.6303% | 218196.2 | 273377.0391 | -55180.8391 | 2017-01-01 | 2017-12-31 | 2017-11-08 | 2017-12-29 | UNDERRUN OF $55,000.00. MATERIALS WERE $27,000.00 LESS THAN QUOTED. CONTRAC T COST WERE MORE THAN ESTIMATED, BUT WERE OFFSET BY REDUCED LABOR COSTS. AP PROXIMATELY $28,000.00 OF OTHER COST WERE ESTIMATED, BUT NOT USED. THESE CO ST WERE ASSOCIATED WITH SITE PREP AND RESTORATION. D.LEMONS 4/20/18
|  | - | - | - | - |  | 2017 Construction Project Budget | 34617000
17026736800 | INSTALL 800' - 2" PMMP | - | - | - | - | 0.09686% | 41818.28 | 37639.6523 | 4178.6277 | 2018-01-01 | 2018-12-31 | 2017-12-18 | 2018-01-04
16026635100 | INSTALL NEW METER AND SETTING | - | - | - | - | 0.09844% | 42500.47 | 69280.6219 | -26780.1519 | 2018-01-01 | 2018-12-31 | 2017-11-14 | 2018-01-19 | JOB WAS ON HOLD WAITING ON UK
17026725200 | INSTALL 20' OF 2"PMIP MAIN | - | - | - | - | 0.02143% | 9250.64 | 5010.35 | 4240.29 | 2018-01-01 | 2018-12-31 | 2018-01-02 | 2018-01-09
18026746600 | INSTALL 1320'-2" PMMP | - | - | - | - | 0.325% | 140295.81 | 110516.4868 | 29779.3232 | 2018-01-01 | 2018-12-31 | 2018-10-25 | 2019-02-22
17026738200 | INSTALL 425' OF 2"PMMP MAIN | - | - | - | - | 0.04915% | 21220.29 | 18453.3983 | 2766.8917 | 2018-01-01 | 2018-12-31 | 2018-01-12 | 2018-01-24
17026729000 | INSTALL 500' OF 2"/4"PMMP | - | - | - | - | 0.1184% | 51110.52 | 37050.0198 | 14060.5002 | 2018-01-01 | 2018-12-31 | 2017-10-03 | 2018-01-25 | COMMIT DATE WAS MISSED DUE TO SEVERAL DAYS THAT CONTRACTORS COULD NOT WORK DUE TO BAD WEATHER.
17026731201 | INSTALL 550' - 2" PMMP | - | - | - | - | 0.1278% | 55174.46 | 52379.7224 | 2794.7376 | 2018-01-01 | 2018-12-31 | 2018-01-09 | 2018-02-05 | USED 7'- 4" PLASTIC PER TESTED # 17-5691704-00 DATED TESTED 12-28-17 ON LEX INGTON AV.
17026738000 | INSTALL 180'-2" PMIP | - | - | - | - | 0.03867% | 16694.36 | 21131.6477 | -4437.2877 | 2018-01-01 | 2018-12-31 | 2018-01-22 | 2018-01-25
17026710101 | INSTALL 6,605' - 2" PHHP | - | - | - | - | 0.4512% | 194790.85 | 158619.4051 | 36171.4449 | 2018-01-01 | 2018-12-31 | 2018-02-02 | 2018-02-01 | THE OVERRUN ON THIS PROJECT WAS CAUSED BY EXTRA EROSION CONTROL BLANKET THA N ESTIMATED. CSPARKS 6/25/18
17026737200 | INSTALL 605' - 2" PMMP | - | - | - | - | 0.1437% | 62039.11 | 55506.0871 | 6533.0229 | 2018-01-01 | 2018-12-31 | 2018-01-31 | 2018-02-16 | LOST A FEW DAYS DUE TO WEATHER AND HAD TO MAKE SURE THIS JOB DIDN'T NEED RE VISING.
17026715800 | INSTALL 1200' OF 2"PMMP MAIN | - | - | - | - | 0.2456% | 106052.58 | 218986.5683 | -112933.9883 | 2018-01-01 | 2018-12-31 | 2018-01-18 | 2018-02-27 | TWALKER/KY 06-22-18: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS FOR COST UNDER RUN, CONTRACT COST LOWER BY $75,000 DUE TO NO HARD SURFACE REPAIRS REQUIRED AND SEGA $18,000 LOWER THAN ESTIMATE.
18026746100 | INSTALL 2100' - 2" PMMP MAIN | - | - | - | - | 0.1001% | 43220.98 | 49200.5771 | -5979.5971 | 2018-01-01 | 2018-12-31 | 2018-01-26 | 2018-02-06
18026746200 | INSERT 15' - 3" PMMP | - | - | - | - | 0% | 0 | 2923.0559 | -2923.0559 | 2018-01-01 | 2018-12-31 | 2018-02-07 | 2018-02-16 | CAPITAL JOB ORDER CREATED DURING WORK ON DPI # FOR 899 WYNDHAM HILL S DR. REPLACED 23' 4"P MAIN W/3"PMMP MAIN. PART OF 3" INSERTED INTO 4"MAIN, RECLAIMED AS CASING. 2/14/2018 DGRIFFI SEE WORK ORDER #18-5756522-00.
18026750800 | INSTALL 20'-2" PMMP | - | - | - | - | 0.01646% | 7107.59 | 8838.5848 | -1730.9948 | 2018-01-01 | 2018-12-31 | 2018-02-15 | 2018-02-21
17026715600 | INSTALL 4" SS | - | - | - | - | 0.01172% | 5059.47 | 7959.2174 | -2899.7474 | 2018-01-01 | 2018-12-31 | 2018-02-23 | 2018-03-15
18026745200 | INSTALL 120' OF 4"PMMP MAIN | - | - | - | - | 0.1041% | 44941.26 | 10847.2036 | 34094.0564 | 2018-01-01 | 2018-12-31 | 2018-02-08 | 2018-02-26 | TWALKER/KY 06-22-18: JOB OVER RUN DUE TO PROJECT COULD BE BORED AS ESTIMATE, PROJECT HAD TO BE OPEN CUT IN SIDEWALK/DRIVEWAY APRONS ALSO PROJECT PLANNED FOR 20 HOURS BUT TOOK 61 HOURS THESE FACTORS ADDED $25,000 TO CONTRACT COST, SEGA WAS ALSO $4300 HIGHER THAN PLANNED. I TRIED TO REVISE JOB ORDER BUT COULD NOT DUE TO WMS UNPAID INVOICES.
17026684601 | INSTALL 5700' OF 2"/4"PMMP | - | - | - | - | 0.5064% | 218652.77 | 213351.2757 | 5301.4943 | 2018-01-01 | 2018-12-31 | 2018-02-02 | 2018-03-02
17026723800 | INSTALL 523'-4" PMMP | - | - | - | - | 0.05593% | 24148.21 | 28994.4349 | -4846.2249 | 2018-01-01 | 2018-12-31 | 2018-02-14 | 2018-03-01
17026741200 | INSTALL 160' OF 2"PMMP MAIN | - | - | - | - | 0.0454% | 19600.57 | 12264.2036 | 7336.3664 | 2018-01-01 | 2018-12-31 | 2018-02-27 | 2018-03-02
18026750500 | INSTALL EFC & MI WIRELESS | - | - | - | - | 0.02632% | 11364.34 | 19542.3042 | -8177.9642 | 2018-01-01 | 2018-12-31 | 2018-03-05 | 2018-08-01
18026756500 | INSTALL 127'-2" PMLP | - | - | - | - | 0.07615% | 32876.88 | 80593.2577 | -47716.3777 | 2018-01-01 | 2018-12-31 | 2018-03-07 | 2018-03-22 | UNDERRUN EXPLANATION: IT LOOKS AS IF SOME OF THE CHARGES ON A RELATED PROJE CT MAY HAVE BEEN CHARGED INCORRECTLY. THAT JOB ORDER OVERRAN; WHEREAS, THIS ONE UNDERRAN. WE WILL INVESTIGATE FURTHER.
18026753800 | INSTALL 525' OF 2"PMIP | - | - | - | - | 0.04592% | 19826.38 | 23575.5345 | -3749.1545 | 2018-01-01 | 2018-12-31 | 2018-03-06 | 2018-03-13
18026747800 | INSTALL GROUND BED | - | - | - | - | 0.009942% | 4292.49 | 6720.6138 | -2428.1238 | 2018-01-01 | 2018-12-31 | 2018-03-07 | 2018-03-14 | INSTALLED 38' OF #4 CP WIRE FROM NEW GROUND BED TO RECTIFIER WILL USE RECENTLY RETIRED 6" BARE STEEL MAIN ABANDONED WITH JOB 17-0266926-00 / 10, 850' OF 6" BARE STEEL MAIN (SCRAP STEEL) NEW GROUND BED RUNS FROM BUCK CUT AT RXR CROSSING IN S-CURVE IN VERSAILLES TO DUCKERS GOLF COURSE IN FRANKFORT. THIS SCRAP STEEL GROUND BED WILL PARALLEL THE 10" CSHP WE ARE PROTECTING. 2 #4 WIRES ARE RUN IN DITCH, ONE IN RECTIFIER CABINET, ONE LEFT IN JUNCTION BOX BELOW THE RECTIFIER ON POLE.
18026751301 | INSTALL 8" FITTING | - | - | - | - | 0% | 0 | 28684.8158 | -28684.8158 | 2018-01-01 | 2018-12-31 |  | 2018-03-14
16026676401 | INSTALL 1950' - 8" PHHP | - | - | - | - | 0.7597% | 327980.6 | 352418.4839 | -24437.8839 | 2018-01-01 | 2018-12-31 | 2018-03-15 | 2018-03-28
16026682600 | INSTALL 1141'-4"/2" PMMP | - | - | - | - | 0.4692% | 202589.6 | 130979.8481 | 71609.7519 | 2018-01-01 | 2018-12-31 | 2017-11-14 | 2018-03-15 | 7/10/18: (BKSLONE) OVERRUN EXPLANATION = USE OF CNG WAS NOT ORIGINALLY PLANNED, HOWEVER, UTI ENDED UP PROVIDING CNG TO THREE CUSTOMERS FOR A COUPLE OF MONTHS DURING LATE WINTER/EARLY SPRING AT A COST OF $41,050. JOB SLOW DRUG OUT THROUGH THE WINTER INCREASING COMPANY LABOR. THESE PLUS OH'S CONTRIBUTED TO THE BULK OF THE OVERRUN.
17026734001 | INSTALL 3425' OF 2"PMMP MAIN | - | - | - | - | 0.1668% | 72004.97 | 75105.1378 | -3100.1678 | 2018-01-01 | 2018-12-31 | 2018-02-19 | 2018-03-16
17026740400 | INSTALL 250'-2" PHHP | - | - | - | - | 0.06246% | 26964.73 | 33762.9976 | -6798.2676 | 2018-01-01 | 2018-12-31 | 2018-03-02 | 2018-03-21
18026762400 | LAND FOR RECIFITIER SITE | - | - | - | - | 0.02137% | 9228.4 | 13255.5943 | -4027.1943 | 2018-01-01 | 2018-12-31 | 2018-03-16 | 2018-03-16
18026764200 | INSERT 50'-3" PMLP | - | - | - | - | 0.03908% | 16872.78 | 16026.8772 | 845.9028 | 2018-01-01 | 2018-12-31 |  | 2018-03-16
18026757100 | INSTALL NEW MI EFC | - | - | - | - | 0.02441% | 10540.82 | 9933.5096 | 607.3104 | 2018-01-01 | 2018-12-31 | 2018-03-22 | 2018-03-22 | REPLACED EFC AND INSTALLED MI-WIRELESS
17026715200 | INSERT 115' - 3" PMLP | - | - | - | - | 0.09883% | 42668.87 | 13602.9352 | 29065.9348 | 2018-01-01 | 2018-12-31 | 2018-03-19 | 2018-03-28 | INSTALLED 142' LF OF 030 PL LP TESTED 90 # FOR 1 HR W/ AIR. RE RAN 2 SL AND RECONNECTED 2 TESTED ALL SL @ 90 # FOR 5 MINS. MOVED 2 MTRS OUT. INSTALLED MB @ OFFSET AND CONNECTION POINTS.
18026757400 | INSTALL INLET/OUTLET VALVES | - | - | - | - | 0.004893% | 2112.32 | 1490.7548 | 621.5652 | 2018-01-01 | 2018-12-31 | 2018-03-27 | 2018-03-27 | REMOVED OLD VALVES AND INSTALLED NEW INLET AND OUTLET VALVES NEW VALVES BALONS 285# 2" 150 SERIES FULL PORT
18026758700 | INSTALL MI WIRELESS W/SOLAR | - | - | - | - | 0.02077% | 8966.01 | 11647.5943 | -2681.5843 | 2018-01-01 | 2018-12-31 | 2018-03-28 | 2018-03-28 | INSTALLED EFC/MI-WIRELESS
18026763800 | INSTALL 334' 4/2" PMMP (EMERG) | - | - | - | - | 0.07387% | 31893.99 | 34743.7008 | -2849.7108 | 2018-01-01 | 2018-12-31 | 2018-03-31 | 2018-06-19 | INSTALLED 406' OF 2'' PMMP AND 5' OF 4'' PMMP FOR NEW MAIN LINE, TESTED MAIN AT 0100PSIG/1HR, SOAP TESTED FC AT OP, INT/EXT CORR INSPECTED MOST OF THE CHARGES WERE CHARGED TO O&M INSTEAD OF THIS JOB ORDER. THERE IS A CORRECTION IN THE WORKS THAT WILL BE TAKEN CARE OF SOON.
15026584901 | INSTALL 15'-6" PMMP | - | - | - | - | 0.07952% | 34333.28 | 31539.1564 | 2794.1236 | 2018-01-01 | 2018-12-31 | 2017-09-22 | 2018-04-03
17026728600 | INSTALL 834'- 6" PMLP | - | - | - | - | 0.3757% | 162200.31 | 128212.7006 | 33987.6094 | 2018-01-01 | 2018-12-31 | 2018-02-09 | 2018-05-01 | OVERRUN EXPLANATION: THIS PROJECT OVER RAN BECAUSE THE LABOR ESTIMATING TOO L PREDICTED ABOUT HALF AS MANY HOURS AS WAS REQUIRED. WE HAD TO WORK AROUND OTHER UNTILITES SINCE THIS WAS A RELOCATION, AND THAT SIGNIFICANLTY SLOWED DOWN OUR PROGRESS.
17026727900 | INSTALL 175' - 3" PMLP | - | - | - | - | 0.08549% | 36907.8 | 31751.2667 | 5156.5333 | 2018-01-01 | 2018-12-31 | 2018-03-26 | 2018-04-06
18026766100 | NEW LAND AND EASEMENT | - | - | - | - | 0.01781% | 7690.17 | 7515.1908 | 174.9792 | 2018-01-01 | 2018-12-31 | 2018-04-09 | 2018-04-09
17026732603 | INSTALL 2024' - 2" PMMP | - | - | - | - | 0.8898% | 384179.6 | 356154.5731 | 28025.0269 | 2018-01-01 | 2018-12-31 | 2018-03-07 | 2018-05-01
18026788100 | INSTALL 6" SST | - | - | - | - | 0.001787% | 771.45 | 3588.5842 | -2817.1342 | 2018-01-01 | 2018-12-31 |  | 2018-05-01
16026634401 | INSTALL 475'-4" & 6" PMMP | - | - | - | - | 0.2947% | 127224.47 | 121107.4104 | 6117.0596 | 2018-01-01 | 2018-12-31 | 2018-03-15 | 2018-04-15
17026713900 | INSTALL 9X9X7 CHAIN LINK FENCE | - | - | - | - | 0.02205% | 9520.9 | 11969.5422 | -2448.6422 | 2018-01-01 | 2018-12-31 | 2018-04-12 | 2018-04-13 | WAITING ON LAND SERVICES AND CONTRACTOR
17026730201 | INSTALL 1100' OF 2"/6"PMMP MN | - | - | - | - | 0.09526% | 41125.53 | 45252.1227 | -4126.5927 | 2018-01-01 | 2018-12-31 | 2018-04-13 | 2018-04-14
18026767400 | ACQUIRE SITE FOR NEW REG STA | - | - | - | - | 0.07205% | 31109 | 35632 | -4523 | 2018-01-01 | 2018-12-31 | 2018-04-12 | 2018-04-13
17026738900 | INSTALL 6,312'-2"/4" PMMP | - | - | - | - | 2.386% | 1029932.98 | 764372.8713 | 265560.1087 | 2018-01-01 | 2018-12-31 | 2018-01-22 | 2018-05-11 | OVERRUN EXPLANATION: SIGNIFICANTLY MORE PAVING WAS REQUIRED THAN ESTIMATED.
18026768100 | SET UP EASEMENT FACILITY | - | - | - | - | 0.02805% | 12111.41 | 10206.1908 | 1905.2192 | 2018-01-01 | 2018-12-31 | 2018-04-16 | 2018-04-16
18026768300 | INSTALL 33' OF 6"PMLP MAIN | - | - | - | - | 0.01413% | 6098.88 | 10546.5117 | -4447.6317 | 2018-01-01 | 2018-12-31 | 2018-04-18 | 2018-04-18
18026757600 | ACQUIRE RECTIFIER SITE | - | - | - | - | 0.02338% | 10095.08 | 6477.0391 | 3618.0409 | 2018-01-01 | 2018-12-31 | 2018-03-07 | 2018-04-23
17026696600 | INSTALL 1000' OF 4"PMMP MAIN | - | - | - | - | 0.6159% | 265907.98 | 282069.8591 | -16161.8791 | 2018-01-01 | 2018-12-31 | 2018-01-25 | 2018-06-14 | 1-28-18 98-300 3HR FOR FOR SITE PREP 1-28-18 CORRECTION 98-300 4HR FOR SITE PREP UNDERRUN EXPLANATION: THE PAVE AND CONC JOB ORDERS HAVE NOT BEEN EXECUTED Y ET. MORE CHARGES SHOULD FOLLOW.
17026717901 | INSTALL 1300' OF 4"/8"CSHP MN | - | - | - | - | 1.258% | 543162.32 | 453832.1269 | 89330.1931 | 2018-01-01 | 2018-12-31 | 2018-03-14 | 2018-04-27 | OVERRUN EXPLANATION: APPROXIMATELY THREE TIMES AS MUCH FLAGGING WAS NECESSA RY THAN WAS ESTIMATED AND $37K MORE IN PAVING WAS REQUIRED. ALSO THE OVERHE AD EFFECT OF THESE INCREASED THE DISPARITY BETWEEN THE ESTIMATE AND ACTUAL.
18026763400 | INSTALL 700'-2" PMMP | - | - | - | - | 0.06986% | 30161.86 | 31042.5478 | -880.6878 | 2018-01-01 | 2018-12-31 | 2018-04-20 | 2018-05-03 | MAIN INSTALLED BY STANLEY PIPELINE BEN YOUNG FOREMAN
17026719001 | INSTALL 2600' - 2" PMMP | - | - | - | - | 0.08851% | 38213.16 | 40148.6317 | -1935.4717 | 2018-01-01 | 2018-12-31 | 2018-04-10 | 2018-05-04
18026767900 | INSTALL NEW REGULATOR/HEATER | - | - | - | - | 0.009723% | 4197.68 | 10394.679 | -6196.999 | 2018-01-01 | 2018-12-31 | 2018-05-07 | 2018-05-21
18026771700 | INSTALL 57' OF 4"PMLP MAIN | - | - | - | - | 0.03443% | 14864.4 | 17249.8397 | -2385.4397 | 2018-01-01 | 2018-12-31 |  | 2018-05-08
18026766501 | INSTALL SS FITTING | - | - | - | - | 0.06335% | 27349.3 | 33470.3697 | -6121.0697 | 2018-01-01 | 2018-12-31 | 2018-05-10 | 2018-05-11
18026749800 | INSTALL 100'-6" PMLP | - | - | - | - | 0.0485% | 20940.87 | 20270.2348 | 670.6352 | 2018-01-01 | 2018-12-31 | 2018-05-08 | 2018-05-12
16026674000 | INSTALL 350' - 4" PM | - | - | - | - | 0.2422% | 104555.89 | 98141.7851 | 6414.1049 | 2018-01-01 | 2018-12-31 | 2018-04-09 | 2018-05-14
18026758400 | INSTALL 120'-2" PMMP | - | - | - | - | 0.02918% | 12599.15 | 18116.0586 | -5516.9086 | 2018-01-01 | 2018-12-31 | 2018-05-14 | 2018-05-15
17026721700 | INSTALL 8760' OF 2"/4"PMMP | - | - | - | - | 0.4379% | 189076.96 | 220888.3342 | -31811.3742 | 2018-01-01 | 2018-12-31 | 2018-04-16 | 2018-05-17 | UNDERRUN EXPLANATION: LESS ROCK BORE, ROCK EXCAVATION, AND BACKFILL MATERIA L WAS REQUIRED OVER THE AMOUNT THAT WAS ESTIMATED. SINCE THERE WAS LESS ROC K, THERE WAS LESS TIME AND THEREFORE COMPANY LABOR REQUIRED TO COMPLETE THE JOB.
17026737400 | INSTALL 100' -2" PMMP | - | - | - | - | 0.01567% | 6763.22 | 11562.7827 | -4799.5627 | 2018-01-01 | 2018-12-31 | 2018-05-16 | 2018-05-16
18026763700 | INSTALL 130'-2" PMIP MAIN | - | - | - | - | 0.05798% | 25033.89 | 17234.7622 | 7799.1278 | 2018-01-01 | 2018-12-31 | 2018-05-17 | 2018-05-19 | FCA 9067 SUBMITTED TO REMOVE PU 665516 FOR 2"SS CREATED IN ERROR - FACILITY WAS RETIRED BUT WMS WILL NOT ALLOW QTY TO BE UPDATED. -JC/JL 8/30/2018
18026772400 | INSTALL 2" BALON B-P VALVES | - | - | - | - | 0.02069% | 8932.53 | 10290.9984 | -1358.4684 | 2018-01-01 | 2018-12-31 | 2018-05-16 | 2018-05-21
17026684300 | INSTALL 250'-2" PMMP | - | - | - | - | 0.07756% | 33485.21 | 31690.1289 | 1795.0811 | 2018-01-01 | 2018-12-31 | 2018-05-17 | 2018-05-23
17026696200 | INSTALL 670' OF 2"PMMP MAIN | - | - | - | - | 0.3444% | 148687.99 | 155468.109 | -6780.119 | 2018-01-01 | 2018-12-31 | 2018-04-28 | 2018-07-23
18026770300 | INSTALL EFC | - | - | - | - | 0.02556% | 11034.78 | 11518.6905 | -483.9105 | 2018-01-01 | 2018-12-31 | 2018-05-30 | 2018-05-30
18026770500 | INSTALL EFC | - | - | - | - | 0.02537% | 10953.27 | 11518.6905 | -565.4205 | 2018-01-01 | 2018-12-31 | 2018-05-31 | 2018-05-31
18026754400 | ACQUIRE ESMT FOR R-1380 EXP'N | - | - | - | - | 0.03021% | 13041.93 | 14342 | -1300.07 | 2018-01-01 | 2018-12-31 | 2018-02-28 | 2018-08-03 | 1/7/20: COMPLETED BY BRYAN SLONE FOR TAYLOR CLARK OF TEAM FISHEL
18026765600 | INSTALL 175' - 4" PMLP | - | - | - | - | 0.2201% | 95029.63 | 30187.5987 | 64842.0313 | 2018-01-01 | 2018-12-31 | 2018-05-04 | 2018-06-05 | OVERRUN EXPLANATION: THE SCOPE OF THE PROJECT DOUBLED. ADDITIONALLY SIGNIFI CANTLY MORE ROCK EXCAVATION WAS REQUIRED THAN WAS ESTIMATED ALONG WITH THE SPECIAL BACKFILL THAT WAS REQUIRED TO PAD THE PIPE. THE ORGINAL JOB WAS TO BE DONE ON HOURLY.
17026725100 | INSTALL 530' - 2" PMMP | - | - | - | - | 0.03106% | 13409.15 | 13849.0191 | -439.8691 | 2018-01-01 | 2018-12-31 | 2018-06-06 | 2018-06-07 | MAIN INSTALLED BY STANLEY PIPELINE 1 HR KULMAN TEST GOOD.1500 PM TO 1600 P M 06/06/18
18026773700 | INSTALL 20' OF 3"PMMP MAIN | - | - | - | - | 0.02028% | 8754.72 | 22530.019 | -13775.299 | 2018-01-01 | 2018-12-31 |  | 2018-06-08
18026751000 | INSTALL 750' - 2" PMMP | - | - | - | - | 0.07143% | 30839.44 | 36154.0383 | -5314.5983 | 2018-01-01 | 2018-12-31 | 2018-06-01 | 2018-06-14 | INSTALL 585' 2" P MP. LINE TEST GOOD 90 LB FOR 1 HR
18026771400 | INSTALL 2300' OF 2"PMMP MAIN | - | - | - | - | 0.1672% | 72168.48 | 63530.2523 | 8638.2277 | 2018-01-01 | 2018-12-31 | 2018-05-21 | 2018-06-08
18026769000 | INSTALL 50' - 3" PMLP | - | - | - | - | 0.0214% | 9241.09 | 13730.2058 | -4489.1158 | 2018-01-01 | 2018-12-31 | 2018-06-11 | 2018-06-18
17026720700 | INSTALL 1845'-4" PMIP | - | - | - | - | 0.4343% | 187499.33 | 307695.2182 | -120195.8882 | 2018-01-01 | 2018-12-31 | 2018-05-16 | 2018-07-20 | UNDERRUN EXPLANATION: CONTRACTOR CHANGED AND AVOIDED 96 DAYS OF PER DIEM. T HE ESTIMATED FLAGGING PROVED UNNECESSARY AS WELL. DID NOT HAVE TO PAY AS MU CH HARD SURFACE RESTORATION.
18026750000 | INSTALL 125' OF 2"PMMP MAIN | - | - | - | - | 0.06065% | 26185.48 | 12809.2058 | 13376.2742 | 2018-01-01 | 2018-12-31 | 2018-06-11 | 2018-06-18
15026626101 | INSTALL 1658'-4"PMMP | - | - | - | - | 0.4829% | 208505.24 | 197065.8319 | 11439.4081 | 2018-01-01 | 2018-12-31 | 2018-07-03 | 2018-07-11
18026775100 | INSTALL 35' - 2" PMMP | - | - | - | - | 0.00157% | 677.75 | 4816.0072 | -4138.2572 | 2018-01-01 | 2018-12-31 |  | 2018-06-19
18026748701 | INSTALL 975' OF 2"PMMP MAIN | - | - | - | - | 0.1042% | 44989.88 | 43685.2789 | 1304.6011 | 2018-01-01 | 2018-12-31 | 2018-06-20 | 2018-07-05 | INSTALL 585' 2' PLASTIC
17026707301 | INSTALL 1950' OF 2"PMMP | - | - | - | - | 0.6747% | 291281.94 | 221016.633 | 70265.307 | 2018-01-01 | 2018-12-31 | 2018-04-25 | 2018-07-20 | OVERRUN EXPLANATION: THE CONCRETE AND ASHPHALT CHANGES WERE ABOUT $40K HOGH ER THAN WAS ESTIMATED.
18026773500 | INSTALL 205'-2" PMMP | - | - | - | - | 0.0655% | 28281.06 | 13911.4555 | 14369.6045 | 2018-01-01 | 2018-12-31 | 2018-07-09 | 2018-07-12
18026747700 | INSTALL 1300' - 4" PMLP | - | - | - | - | 0.1902% | 82128.71 | 45983.7408 | 36144.9692 | 2018-01-01 | 2018-12-31 | 2018-06-07 | 2018-07-13 | HIT ROCK HAD TO DO A ROCK BORE RAIN DAYS AND THUNDER STORMSDELAY. AND EQU IPTMENT BREAKDOWNS DELAYED JOB. BROKE ROCK LEDGE ALSO OVERRUN EXPLANATION: ROCK EXCAVATION AND RELATED BACKFILL INCREASED BY 70 F EET/FEET AND DOUBLED RESPECTIVELY. ADDITIONALLY, 10,800 FEET ADDITIONALY ER OSION CONTROL BLANKET AND FLAGGING WERE REQUIRED ADDING ABOUT 100 HOURS TO THE CONTRACT COSTS AND LABOR COSTS.
18026764600 | INSTALL 175' - 4" PMMP | - | - | - | - | 0.04887% | 21098 | 14145.7592 | 6952.2408 | 2018-01-01 | 2018-12-31 | 2018-06-26 | 2018-07-13
18026768200 | INSTALL 475' OF 2"PMMP MAIN | - | - | - | - | 0.05286% | 22819.91 | 22495.5987 | 324.3113 | 2018-01-01 | 2018-12-31 | 2018-07-10 | 2018-07-13
18026780200 | INSTALL 12'-8" PMLP | - | - | - | - | 0.06965% | 30072.49 | 11998.4555 | 18074.0345 | 2018-01-01 | 2018-12-31 | 2018-07-10 | 2018-07-13
17026736301 | INSTALL 3344' OF 2"/4"/6"PMMP | - | - | - | - | 1.967% | 849426.85 | 605787.3509 | 243639.4991 | 2018-01-01 | 2018-12-31 | 2018-08-06 | 2018-09-05 | PAPER WORK DELAY DUE TO MASS INCIDENT OVERRUN EXPLANATION: MORE INQUIRY IS NEEDED BY 2OO MORE HOURS OF FLAGGER WE RE USED THAN ESTIMATED. THERE WAS $25K EXTRA IN LABOR AND THE OVERHEAD EFFE CT OF THE OVERRRUNS WAS $60,000. HOWEVER, THERE ARE CHANGES THAT CAME FROM OTHER JOB ORDERS THAT CAN'T BE FOUND. NEED TO INVESTIGATE FUTHRE.
17026734801 | INSTALL 2192'-4"PMLP | - | - | - | - | 0.7664% | 330883.22 | 345981.5064 | -15098.2864 | 2018-01-01 | 2018-12-31 | 2018-07-18 | 2018-12-10 | UNDERRUN EXPLANATION: THIS PROJECT IS UNDERRUNNING CURRENTLY BECAUSE THERE IS 500 FEWER FLAGGING HOURS THAN ESTIMATED. HOWEVER, THE FINAL RESTORATION HAS NOT BEEN COMPLETED. THIS PROJECT SEEMS TO BE ON TARGET TO HIT THE ESTMA TE ONCE THE HARD SURFACE REPAIRS HIT.
18026775500 | INSTALL 1500'-2" PHHP | - | - | - | - | 0.1118% | 48281.24 | 48705.9109 | -424.6709 | 2018-01-01 | 2018-12-31 | 2018-07-09 | 2018-07-19
18026785000 | INSTALL NEW CONTROL REGULATOR | - | - | - | - | 0.0008343% | 360.19 | 2388.8263 | -2028.6363 | 2018-01-01 | 2018-12-31 |  | 2018-07-18
18026765100 | INSTALL 2825' - 2"PMMP | - | - | - | - | 0.1597% | 68942.65 | 62925.0703 | 6017.5797 | 2018-01-01 | 2018-12-31 | 2018-06-25 | 2018-07-20
18026782800 | INSTALL NEW EFC W/MI WIRELESS | - | - | - | - | 0.01843% | 7955.15 | 12899.916 | -4944.766 | 2018-01-01 | 2018-12-31 | 2018-07-23 | 2018-07-23
18026782900 | INSTALL NEW EFC W/MI WIRELESS | - | - | - | - | 0.01887% | 8145.78 | 12899.916 | -4754.136 | 2018-01-01 | 2018-12-31 | 2018-07-23 | 2018-07-23
15026603702 | INSTALL 15' OF 2" PMMP | - | - | - | - | 0.03019% | 13032.5 | 14665.2633 | -1632.7633 | 2018-01-01 | 2018-12-31 | 2018-07-23 | 2018-07-27
18026771601 | INSTALL 800' OF 2"PMMP MAIN | - | - | - | - | 0.07344% | 31706.21 | 36097.9475 | -4391.7375 | 2018-01-01 | 2018-12-31 | 2018-07-16 | 2018-07-26
17026722300 | INSTALL 1000' OF 2"PMMP MAIN | - | - | - | - | 0.08776% | 37887.93 | 39965.6173 | -2077.6873 | 2018-01-01 | 2018-12-31 | 2018-07-18 | 2018-08-01
18026769700 | INSTALL 700' OF 2"PMMP MAIN | - | - | - | - | 0.08355% | 36070.5 | 30298.4174 | 5772.0826 | 2018-01-01 | 2018-12-31 | 2018-07-23 | 2018-07-31
18026782500 | INSTALL 200' - 2" PMMP | - | - | - | - | 0.01219% | 5262.38 | 12261.958 | -6999.578 | 2018-01-01 | 2018-12-31 | 2018-07-26 | 2018-07-27
17026736601 | INSTALL 40'- 4"PMLP | - | - | - | - | 0.1405% | 60680.33 | 64825.5054 | -4145.1754 | 2018-01-01 | 2018-12-31 | 2018-08-01 | 2018-08-06
18026775900 | INSTALL EFC - MI WIRELESS UNIT | - | - | - | - | 0.02049% | 8848.16 | 10110.2848 | -1262.1248 | 2018-01-01 | 2018-12-31 | 2018-08-02 | 2018-08-02
18026777500 | INSTALL 300' OF 2"PMMP MAIN | - | - | - | - | 0.08466% | 36549.31 | 22749.8591 | 13799.4509 | 2018-01-01 | 2018-12-31 | 2018-07-27 | 2018-08-07
17026722800 | INSERT 120' - 3" PMLP | - | - | - | - | 0.05136% | 22175.87 | 21522.2667 | 653.6033 | 2018-01-01 | 2018-12-31 | 2018-08-02 | 2018-08-09
18026781400 | INSTALL 500' - 2" PMMP | - | - | - | - | 0.04957% | 21400.13 | 23908.2633 | -2508.1333 | 2018-01-01 | 2018-12-31 | 2018-08-08 | 2018-08-10
17026726301 | INSTALL 1400' - 4" PMIP | - | - | - | - | 0.4198% | 181243.14 | 142935.1369 | 38308.0031 | 2018-01-01 | 2018-12-31 | 2018-06-04 | 2018-08-15 | OVERRUN EXPLANATION: PROJECT OVERRAN BECAUSE WE WERE UNABLE TO FIND GOOD PI PE TO TIE-IN TO AND EVENTUALLY HAD TO LAY AN EXTRA 1000 FEET BECAUSE OF A S TREAM.
17026742100 | INSTALL 1,428'-2"/6" PMMP | - | - | - | - | 0.8258% | 356543.76 | 213643.4676 | 142900.2924 | 2018-01-01 | 2018-12-31 | 2018-04-09 | 2018-08-13 | OVERRUN EXPLANATION: PROJECT OVERRAN BECAUSE WE HAD TO LAY AN EXTRA 1000 FE ET OF PIPE BECAUSE WE COULD NOT BORE WILIKINSON AS WE HAD PLANNED BECAUSE O F LAND PROBLEMS. CONSEQUENTLY, WE CHANGED THE SCOPE OF THE PROJECT AND EXTE NDED OFF THE LP CAUSING THE EXTRA FOOTAGE.
18026787200 | INSTALL 40' OF 4"PMMP MAIN | - | - | - | - | 0.02432% | 10500.34 | 28073.4342 | -17573.0942 | 2018-01-01 | 2018-12-31 | 2018-08-13 | 2018-08-16 | INSTALLED 24' OF 4" PL MAIN. TESTED MAIN AND ALL SHORT STOPS AND BY PASS FOR 1 HR @ 90 # SOAP TESTED ALL CONN POINTS @ OP ONCE NEW MAIN WAS GASED UP. INSTALLED 4 ANODES AND MB
18026788600 | EMERGENCY 80'-4"BSLP REPL | - | - | - | - | 0.1209% | 52206.38 | 16939.7623 | 35266.6177 | 2018-01-01 | 2018-12-31 |  | 2018-08-21 | OVERRUN EXPLANATION: THIS WAS AN EMERGENCY JOB. ABOUT $12K IN ADDITIONAL PA VEING AND $12K IN ADDITIONAL FLAGGING WAS REQUIRED OVER WHAT WAS ESTMATED.
18026790100 | INSTALL 900' OF 4"PMLP MAIN | - | - | - | - | 0.008744% | 3775.31 | 3810.5842 | -35.2742 | 2018-01-01 | 2018-12-31 | 2018-08-21 | 2018-08-14
18026787600 | INSTALL NEW RECTIFIER | - | - | - | - | 0.01502% | 6483.3 | 6423.4781 | 59.8219 | 2018-01-01 | 2018-12-31 | 2018-08-13 | 2018-08-15 | INSTALLED NEW MESA RECTIFIER AND UPDATED FACILITY. OLD GROUNDBED STILL IN OPERATION/SPLICED BROKEN CABLE AND EXISTING GROUND BED IS STILL OPERATIONAL.. TIM SWARTS 8/15/2018
17026690500 | INSTALL 370'- 4" PMLP | - | - | - | - | 0.1305% | 56333.01 | 44947.9668 | 11385.0432 | 2018-01-01 | 2018-12-31 | 2018-04-18 | 2018-08-30
18026769900 | INSTALL 3100' OF 2"PMMP MAIN | - | - | - | - | 0.331% | 142919.51 | 113279.9095 | 29639.6005 | 2018-01-01 | 2018-12-31 | 2018-07-16 | 2018-08-17
17026690100 | INSTALL 1050'- 8" & 4" PMMP | - | - | - | - | 0.7178% | 309910.75 | 303456.534 | 6454.216 | 2018-01-01 | 2018-12-31 | 2018-03-20 | 2018-08-30
17026690300 | INSTALL 671'- 4" PM/CSIP | - | - | - | - | 0.2022% | 87299.33 | 91546.6668 | -4247.3368 | 2018-01-01 | 2018-12-31 | 2018-04-13 | 2018-08-30
18026785300 | INSTALL 24'-4" PMIP | - | - | - | - | 0.1161% | 50122.97 | 28413.2128 | 21709.7572 | 2018-01-01 | 2018-12-31 | 2018-08-10 | 2018-08-21
18026755300 | INSTALL 275' OF 2"PMMP MAIN | - | - | - | - | 0.04964% | 21433.19 | 16234.4604 | 5198.7296 | 2018-01-01 | 2018-12-31 | 2018-08-15 | 2018-08-23
18026784900 | INSTALL 400'-2" PMHP | - | - | - | - | 0.05277% | 22783.29 | 22702.0896 | 81.2004 | 2018-01-01 | 2018-12-31 | 2018-08-16 | 2018-08-24
18026766000 | INSTALL 185' OF 2"PMMP MAIN | - | - | - | - | 0.03588% | 15492.11 | 17973.6784 | -2481.5684 | 2018-01-01 | 2018-12-31 | 2018-08-15 | 2018-08-24
18026774300 | INSTALL 1500'-2" PMMP | - | - | - | - | 0.5233% | 225939.85 | 295064.9243 | -69125.0743 | 2018-01-01 | 2018-12-31 | 2018-07-30 | 2018-10-31 | CONTRACT COSTS UNDERRAN BY ABOUT $65,000. THIS WAS DUE TO LOWER SPECIAL BACKFILL COSTS BY NOT HAVING ANY ROCK EXCAVATION. ALSO, ONLY ABOUT HALF OF THE COLD PATCH THAT WAS ESTIMATED WAS NEEDED.
17026719900 | INSTALL 100'-4" PMLP | - | - | - | - | 0.07883% | 34033.59 | 26581.4555 | 7452.1345 | 2018-01-01 | 2018-12-31 | 2018-08-20 | 2018-08-28 | TESTED MAIN AND ENTIRE SERVICE LINE TOGETHER 95 PSIG FOR 1 HOUR SERVICE LIN E JO#17-0267200-00 MARCUS BLANKENSHIP/CJH MATTHEW TURNER TEST STATION WAS USED FOR TRACER WIRE STATION.
17026726000 | INSTALL 3,812' - 6"/2" PMMP | - | - | - | - | 1.733% | 748182.83 | 582687.0231 | 165495.8069 | 2018-01-01 | 2018-12-31 | 2018-04-06 | 2018-08-30 | INSTALLED 2168' OF 6" PLASTIC MAIN AND 2120' OF 2" PLASTIC MAIN. PERFORMED 3 PRESSURE TEST CHARTS, TEST ALL OK. ABANDONED 5704' OF MAINLINE. PRE AND P OST SEWER CAMERA COMPLETED. ALL TEST CHARTS UPLOADED INTO WMSDOCS. OVERRUN EXPLANATION: MORE FOOTAGE WAS INSTALLED THAN ESTIMATED. FURTHER INQ UIRY REQUIRED.
18026769300 | INSTALL GROUND BED RECTIFIER | - | - | - | - | 0.04532% | 19566.07 | 39677.7758 | -20111.7058 | 2018-01-01 | 2018-12-31 | 2018-08-06 | 2018-08-27
18026771000 | INSTALL CHAIN LINK FENCE | - | - | - | - | 0.01147% | 4950.19 | 8178.7386 | -3228.5486 | 2018-01-01 | 2018-12-31 | 2018-05-31 | 2018-08-27
17026723900 | CONVERT CAB TO GMB | - | - | - | - | 0.03077% | 13285.55 | 18863.5645 | -5578.0145 | 2018-01-01 | 2018-12-31 | 2018-08-27 | 2018-10-22 | JOB ON HOLD WAITING ON CUSTOMER
17026741401 | INSTALL 2915'-2" PMMP | - | - | - | - | 0.8022% | 346362.3 | 712485.4152 | -366123.1152 | 2018-01-01 | 2018-12-31 | 2018-07-12 | 2018-12-08 | UNDERRUN EXPLANATION: PROJECT UNDERAN BECAUSE THE CITY OF MAYSVILLE DID THE PAVING FOR US AT A MUCH CHEAPER COST THAN OUR CONTRACTORS COULD DO IT FOR.
18026744400 | INSTALL 2800' OF 6"PMMP MAIN | - | - | - | - | 0.3033% | 130941.62 | 150927.995 | -19986.375 | 2018-01-01 | 2018-12-31 | 2018-08-03 | 2018-08-29
18026782000 | INSTALL 100'-2" PMIP | - | - | - | - | 0.02071% | 8942.09 | 15360.6538 | -6418.5638 | 2018-01-01 | 2018-12-31 | 2018-08-28 | 2018-08-29
18026782401 | INSTALL 150' - 4" PMLP | - | - | - | - | 0.04341% | 18743.17 | 16688.7188 | 2054.4512 | 2018-01-01 | 2018-12-31 | 2018-08-27 | 2018-09-05
17026690700 | INSTALL 2"-IP & LP DUAL RUN RS | - | - | - | - | 0.1817% | 78437 | 89150.4001 | -10713.4001 | 2018-01-01 | 2018-12-31 | 2018-03-13 | 2018-10-08 | WAITING ON MATERIAL
18026762200 | INSTALL 400'-2" PMIP | - | - | - | - | 0.07653% | 33043.11 | 25803.7294 | 7239.3806 | 2018-01-01 | 2018-12-31 | 2018-08-30 | 2018-09-11
17026723400 | INSTALL 1800' - 2/4" PMMP | - | - | - | - | 0.2033% | 87757.72 | 72180.8231 | 15576.8969 | 2018-01-01 | 2018-12-31 | 2018-08-22 | 2018-09-11 | MISSED COMMIT DUE TO ROCK, EQUIPMENT FAILURE
18026792700 | INSTALL 4" BP VALVE | - | - | - | - | 0.008571% | 3700.33 | 5690.6907 | -1990.3607 | 2018-01-01 | 2018-12-31 | 2018-09-10 | 2018-09-11
17026721000 | INSTALL 2800' - 12" CSHP | - | - | - | - | 1.967% | 849320.98 | 864219.4988 | -14898.5188 | 2018-01-01 | 2018-12-31 | 2018-07-16 | 2018-09-14
18026784800 | INSTALL 1650' OF 2"PMMP MAIN | - | - | - | - | 0.06713% | 28983.91 | 31155.3341 | -2171.4241 | 2018-01-01 | 2018-12-31 | 2018-08-27 | 2018-09-13
18026788000 | INSTALL 70' - 2" PMMP | - | - | - | - | 0.009896% | 4272.57 | 10233.7188 | -5961.1488 | 2018-01-01 | 2018-12-31 | 2018-09-10 | 2018-09-12
18026795300 | REPLACE MONITOR/CONTROL REGS | - | - | - | - | 0.0001589% | 68.61 | 1655.6198 | -1587.0098 | 2018-01-01 | 2018-12-31 | 2018-09-19 | 2018-09-13 | RETIRED AND REPLACED MONITOR AND CONTROL REGULATORS WITH 627M AND 627R
18026751701 | INSTALL 750' - 6" PMMP | - | - | - | - | 0.3135% | 135342.51 | 160937.396 | -25594.886 | 2018-01-01 | 2018-12-31 | 2018-09-07 | 2018-09-22
18026792200 | INSTALL BYPASS & OUTLET VALVES | - | - | - | - | 0.0233% | 10059.72 | 6123.9724 | 3935.7476 | 2018-01-01 | 2018-12-31 | 2018-09-05 | 2018-09-14 | RETIRED BYPASS GATE VALVE INSTALLED NEW NORDSTROM 300 SERIES BYPASS PLUG VALVE 500# MOP 8 BOLT
18026786900 | INSTALL 120'-2" PMMP | - | - | - | - | 0.01538% | 6640.11 | 14588.3108 | -7948.2008 | 2018-01-01 | 2018-12-31 | 2018-09-07 | 2018-09-18
15026569503 | PM INSTALL POD HUNTINGTON ALLO | - | - | - | - | 3.601% | 1554911.1 | 935721 | 619190.1 | 2018-01-01 | 2018-12-31 | 2018-03-22 | 2018-10-10 | THIS WAS A MAJOR PROJECTS PROJECT. INQUIRE WITH THAT TEAM AS TO THE NATURE OF THIS OVERRUN.
15026569602 | PM INSTALL GMB HUNINGTON ALLOY | - | - | - | - | 0.3731% | 161063.11 | 304013 | -142949.89 | 2018-01-01 | 2018-12-31 | 2018-04-23 | 2018-10-10 | THIS WAS A MAJOR PROJECTS PROJECT. INQUIRE WITH THAT TEAM AS TO THE NATURE OF THIS OVERRUN.
16026680200 | PM INSTALL 3600'- 6"HDPE | - | - | - | - | 1.23% | 530875.15 | 415898 | 114977.15 | 2018-01-01 | 2018-12-31 | 2018-04-23 | 2018-10-10
18026752100 | PM - GMB STATION FENCE | - | - | - | - | 0% | 0 | 83.5943 | -83.5943 | 2018-01-01 | 2018-12-31 | 2018-09-26 | 2018-10-10
18026781600 | INSTALL 900' OF 2"PMMP MAIN | - | - | - | - | 0.1311% | 56582.39 | 37549.3102 | 19033.0798 | 2018-01-01 | 2018-12-31 | 2018-09-12 | 2018-09-27
18026791000 | INSTALL 140' OF 2"PMMP MAIN | - | - | - | - | 0.03098% | 13377.16 | 11571.8594 | 1805.3006 | 2018-01-01 | 2018-12-31 | 2018-09-21 | 2018-09-27
18026766700 | INSTALL 660'-2" PMMP | - | - | - | - | 0.4009% | 173075.26 | 196978.2773 | -23903.0173 | 2018-01-01 | 2018-12-31 | 2018-09-06 | 2018-10-05
18026753900 | INSTALL 50' - 2" PMMP | - | - | - | - | 0.02742% | 11836.69 | 12804.7525 | -968.0625 | 2018-01-01 | 2018-12-31 | 2018-09-28 | 2018-10-03
18026777400 | INSTALL 4000' OF 2"PMMP MAIN | - | - | - | - | 0.2357% | 101741.4 | 133000.3919 | -31258.9919 | 2018-01-01 | 2018-12-31 | 2018-06-29 | 2018-10-05 | UNDERRUN EXPLANATION: THE SCOPE OF THE PROJECT CHANGED TO WHERE WE OPEN CUT THE PROJECT INSTEAD OF DIRECTIONALLY BORING WHICH CAUSED THE UNDERRUN OF $ 34,000.
18026791300 | INSTALL 535' OF 2"PMMP MAIN | - | - | - | - | 0.06328% | 27320.59 | 22934.099 | 4386.491 | 2018-01-01 | 2018-12-31 | 2018-09-27 | 2018-10-04
17026717000 | INSTALL 8,725' - 2"/4" PMMP | - | - | - | - | 1.141% | 492598.58 | 541056.5841 | -48458.0041 | 2018-01-01 | 2018-12-31 | 2018-01-29 | 2018-10-15
18026789400 | INSTALL 600'-2" PMIP | - | - | - | - | 0.04067% | 17559.53 | 26849.4089 | -9289.8789 | 2018-01-01 | 2018-12-31 | 2018-09-27 | 2018-10-08
17026691100 | INSTALL STRUCTURE; R-1317 RELO | - | - | - | - | 0.1899% | 81981.79 | 91119.1334 | -9137.3434 | 2018-01-01 | 2018-12-31 | 2018-07-27 | 2018-10-08 | JOB WAS ON HOLD WAITING FOR MATERIAL
18026752200 | PM - INSTALL POD FENCING | - | - | - | - | 0% | 0 | 83.5943 | -83.5943 | 2018-01-01 | 2018-12-31 | 2018-09-26 | 2018-10-09
18026788900 | INSTALL 400' - 2" PMMP | - | - | - | - | 0.05727% | 24726.47 | 23846.5075 | 879.9625 | 2018-01-01 | 2018-12-31 | 2018-10-08 | 2018-10-11
17026739201 | INSTALL 400' OF 2"PMMP MAIN | - | - | - | - | 0.09426% | 40694.63 | 43805.099 | -3110.469 | 2018-01-01 | 2018-12-31 | 2018-10-05 | 2018-10-11
18026748400 | INSTALL 270'-2" PMMP | - | - | - | - | 0.0288% | 12435.84 | 20348.7501 | -7912.9101 | 2018-01-01 | 2018-12-31 | 2018-10-11 | 2018-10-26
18026789800 | INSTALL 525' OF 2"PMMP MAIN | - | - | - | - | 0.05049% | 21796.82 | 25393.4792 | -3596.6592 | 2018-01-01 | 2018-12-31 | 2018-10-10 | 2018-10-12
18026750100 | INSTALL 1200' OF 2"PMMP MAIN | - | - | - | - | 0.05712% | 24662.6 | 29326.4607 | -4663.8607 | 2018-01-01 | 2018-12-31 | 2018-10-04 | 2018-11-09 | IN SERVICE 10-16. DELAY IN PAPERWORK BECAUSE OF MASS
18026752900 | INSTALL 3 VRG PILOTS | - | - | - | - | 0.08414% | 36328.01 | 27587.3267 | 8740.6833 | 2018-01-01 | 2018-12-31 | 2018-06-26 | 2019-03-12 | JOB ON HOLD PER FLL JIM COLYER
18026771900 | INSTALL NEW MON/CON REGULATORS | - | - | - | - | 0.6121% | 264261.42 | 139764.0803 | 124497.3397 | 2018-01-01 | 2018-12-31 | 2018-06-13 | 2019-03-12 | JOB WAS ON HOLD PER FLL JIM COLYER OVERRUN EXPLANATIONS: EMERGENCY REPAIRS FOR THE FAILURE IN THE MONITOR REGU LATOR ON THE 4" RUN. THE OVERRUN WAS DUE TO THE VACUUM EXCAVATION TAKING MU CH LONGER THAN ESTIMATED AND THE COSTS FOR THE CRANE BEING UNDERESTIMATED. ADDITIONALLY, THE SHORING EQUIPMENT WAS NEEDED FOR MUCH LONGER THAN ESTIMAT ED DRIVING UP THE COST OF SHORING EQUIPMENT RENTAL. LABOR INCREASED BY AROU ND 900 HOURS DUE TO MORE EMPLYEES BEING REQUIRED THAN ESTIMATED. LEVEL 2 VARIANCE EXPLANATION PROVIDED TO CLOSE OUT TO UPLOAD.
18026792600 | INSTALL 100' OF 2"PMIP MAIN | - | - | - | - | 0.01973% | 8517.2 | 11234.5495 | -2717.3495 | 2018-01-01 | 2018-12-31 | 2018-10-16 | 2018-10-22
18026751100 | INSTALL 7'-3" WTHP | - | - | - | - | 0.04797% | 20711.17 | 26572.1879 | -5861.0179 | 2018-01-01 | 2018-12-31 | 2018-10-16 | 2018-10-18
18026788500 | INSTALL 1500'-2"PMMP | - | - | - | - | 0.0724% | 31257.41 | 65744.8415 | -34487.4315 | 2018-01-01 | 2018-12-31 | 2018-10-05 | 2018-10-17 | UNDERRUN EXPLANATION: SOIL CONDITIONS WERE BETTER THAN ESTIMATED AND WE DID NOT NEED THE 500 TONS OF SPECIAL BACKFILE THAT WAS ESTIMATED.
17026695602 | INSTALL 4225' OF 2"/4"/8"PMLP | - | - | - | - | 2.718% | 1173531.41 | 998106.9644 | 175424.4456 | 2018-01-01 | 2018-12-31 | 2018-02-26 | 2019-03-18 | OVERRUN EXPLANATION: THIS PROJECT OVERRAN DUE TO ADDITIONAL PAVING REQUIREM ENTS IMPOSED BY THE CITY OF LEXINGTON. BETWEEN CKY AND THE WATER COMPANY, W E HAD TO PAVE THE ENTIRE ROAD WHICH LEAD TO A $390K OVERRUN DUE TO PAVING A ND THE OH EFFECT OF THIS ACCOUNTED FOR ANOTHER $32K.
17026699001 | INSTALL 1825' - 2" PMMP | - | - | - | - | 0.6164% | 266140.26 | 221605.4105 | 44534.8495 | 2018-01-01 | 2018-12-31 | 2018-08-22 | 2018-12-03 | OVERRUN EXPLANATION: THE SCOPE OF THE WORK CHANGED BECAUSE OF A CITY PROJEC T IN THE VICINITY AND AS A RESULT THE CONTRACT COSTS EXCEEDED THE ESTIMATED BY ABOUT $40,000.
18026775600 | INSTALL 370'-4" PMIP | - | - | - | - | 0.03407% | 14708.4 | 41665.2821 | -26956.8821 | 2018-01-01 | 2018-12-31 | 2018-10-11 | 2018-10-19
19026879600 | DOCUMENT MP MAIN INSTALL | - | - | - | - | 0.00505% | 2180.35 | 75.154 | 2105.196 | 2018-01-01 | 2018-12-31 | 2018-01-29 | 2019-06-06
17026735900 | INSTALL BYPASS VALVE | - | - | - | - | 0.01083% | 4676.94 | 3946.7045 | 730.2355 | 2018-01-01 | 2018-12-31 | 2018-10-18 | 2018-10-19
18026748100 | INSTALL 105'-2" PMMP | - | - | - | - | 0.03312% | 14299.07 | 21179.7501 | -6880.6801 | 2018-01-01 | 2018-12-31 | 2018-10-17 | 2018-10-26
18026790700 | INSTALL SS FITTING | - | - | - | - | 0.03124% | 13489.35 | 20483.536 | -6994.186 | 2018-01-01 | 2018-12-31 | 2018-08-30 | 2018-10-22
16026677500 | INSTALL 2905' OF 12"CSHP MAIN | - | - | - | - | 1.952% | 842850.97 | 803059.2299 | 39791.7401 | 2018-01-01 | 2018-12-31 | 2018-04-30 | 2018-11-13
18026790800 | INSTALL 250' - 2" PMMP | - | - | - | - | 0.03298% | 14239.34 | 14776.4792 | -537.1392 | 2018-01-01 | 2018-12-31 | 2018-10-22 | 2018-10-22
18026761900 | INSTALL 20'-2" PMP | - | - | - | - | 0.2536% | 109473.95 | 27540.2128 | 81933.7372 | 2018-01-01 | 2018-12-31 | 2018-10-10 | 2018-11-06 | OVERRUN EXPLANATION: THE CONTRACTOR CHANGED AFTER PROJECT WAS ESTIMATED. AD DITIONALLY, EIGHT TIMES AS MUCH BACKFILL WAS REQUIRED AS ESTIMATED. TWELVE MORE HOURS OF WELDING WAS REQUIRED AND TOW AND A HALF MORE HOURS OF 4 MAN C REW WERE NEEDED. FINALLY, 242 HOURS OF FLAGGING WERE NEEDED TO COMPLETE THE WORK. ALL THIS RESULTED IN A $69,000 OVERRUN. A LEVEL 2 VARIANCE EXPLANATION WAS PROVIDED.
18026797000 | INSTALL 175' OF 2"PMMP MAIN | - | - | - | - | 0.02502% | 10802.52 | 17539.341 | -6736.821 | 2018-01-01 | 2018-12-31 | 2018-10-23 | 2018-10-24
18026761500 | INSTALL 1100' OF 2"PMMP MAIN | - | - | - | - | 0.05378% | 23219.37 | 22277.6726 | 941.6974 | 2018-01-01 | 2018-12-31 | 2018-10-24 | 2018-10-30
18026800600 | INSTALL 60' OF 2"PMLP MAIN | - | - | - | - | 0.03661% | 15804.17 | 28611.2534 | -12807.0834 | 2018-01-01 | 2018-12-31 |  | 2018-10-26
18026792900 | INSTALL 500' OF 2"PMMP MAIN | - | - | - | - | 0.05835% | 25193.54 | 24897.099 | 296.441 | 2018-01-01 | 2018-12-31 | 2018-10-23 | 2018-11-01
17026731301 | INSTALL 16,843' - 2"/4" PMMP | - | - | - | - | 5.006% | 2161385.67 | 2372597.5254 | -211211.8554 | 2018-01-01 | 2018-12-31 | 2018-08-20 | 2018-12-24
18026791400 | INSTALL 375' - 2" PMMP | - | - | - | - | 0.0442% | 19083.76 | 50710.6819 | -31626.9219 | 2018-01-01 | 2018-12-31 | 2018-10-29 | 2018-11-02 | WORK RAINED OUT ON 2 SEPERATE DAYS STEVE CANOY11-02-2018 UNDERRUN EXPLANATION: NONE OF THE ANTICIPATED ROCK EXCAVATION AND RELATED P COSTS WERE ENCOUNTERED. LIKEWISE, WE WERE ABLE TO AVOID THE PAVEMENT RESTOR ATION AND FLAGGING COSTS. THIS REDUCED THE CONTRACT COSTS BY ABOUT A THIRD. AS A RESULT, SEGA WAS REDUCED A COMMENSURATE AMOUNT.
18026772600 | INSTALL 930'-8" PMMP | - | - | - | - | 0.4817% | 207961.38 | 357192.6932 | -149231.3132 | 2018-01-01 | 2018-12-31 | 2018-09-18 | 2018-11-07 | UNDERRUN EXPLANATION: NO ROCK EXCAVATION OR FLAGGING WAS REQUIRED. ADDITION ALLY, NO BORING WAS PERFORMED THEREFORE NO VIDEO CAMERING WAS PERFORMED. MU CH LESS CONCRETE WAS USED COMPARED TO WHAT WAS ESTIMATED. ALL THAT REDUCED THE LABOR AND THE ASSOCIATED SEGA COSTS. LEVEL 2 VARIANCE EXPLANATION NOT REQUIRED FOR UNDERRUNS.
18026785700 | INSTALL 30' OF 8"PMLP MAIN | - | - | - | - | 0.08141% | 35149.2 | 31520.0067 | 3629.1933 | 2018-01-01 | 2018-12-31 | 2018-10-29 | 2018-11-06
18026791800 | INSTALL 175' - 2" PMMP | - | - | - | - | 0.02731% | 11789.41 | 12672.5495 | -883.1395 | 2018-01-01 | 2018-12-31 | 2018-11-05 | 2018-11-06 | ALL MATERIALS HAD NOT BEEN ADDED TO JOB AS OF DATE OF COMPLETION PER TOM WA LKER ENGINEER
15026578201 | INSTALL 600'-4" PMMP | - | - | - | - | 0.1388% | 59941.57 | 62361.0924 | -2419.5224 | 2018-01-01 | 2018-12-31 | 2018-10-22 | 2018-11-08
16026644200 | INSTALL 750' OF 2"PMMP MAIN | - | - | - | - | 0.3073% | 132689.61 | 144783.2087 | -12093.5987 | 2018-01-01 | 2018-12-31 | 2018-09-04 | 2018-11-07
17026727300 | NEW REG STATION 1216 | - | - | - | - | 0.1358% | 58641.72 | 78951.8142 | -20310.0942 | 2018-01-01 | 2018-12-31 | 2018-04-23 | 2018-12-26
17026725601 | INSTALL 2,442' - 2"/4" PMMP | - | - | - | - | 1.67% | 720801.28 | 450266.5029 | 270534.7771 | 2018-01-01 | 2018-12-31 | 2018-06-01 | 2018-12-03 | ARRIVAL TIME 1:57 AM, FOR ASSISTANCE FOR SAFETY PER S.BARKER 12-19-18 OM ARRIVAL TIME 1:57 AM, FOR ASSISTANCE FOR SAFETY PER S.BARKER 12-19-18 OM SERVICE WORK COMPLETE 12-19-2018 0358 AM BA INSTALLED 1389' OF 2" PLASTIC MAIN AND 1096' OF 4" PLASTIC MAIN. TEST CHART S UPLOADED TO WMSDOCS. UPRATE WAS COMPLETED ON 12-20-2018. OVERRUN EXPLANATION: THIS WAS THE ELKHORN DRIVE PROJECT. THIS PROJECT INVOL VED A COMPLEX UPRATE. 1200 MORE HOURS OF FLAGGING WERE REQUIRED THAN ESTIMA TED AND 217 MORE HOURS ON OVERTIME WERE REQUIRED THAN ESTIMATED. 102 HOURS OF VIDEO CAMERAING WERE REQUIRED OVER THE ESTIMATED PLUS A COMMENSURATE AMO UNT OF ADDITIONAL SEGA. THESE ADDED EXPENSES LED TO THE OVERRUN.
17026719501 | INSTALL 8" SS | - | - | - | - | 0.1749% | 75520.84 | 64412.8232 | 11108.0168 | 2018-01-01 | 2018-12-31 | 2018-09-17 | 2018-11-26
18026845200 | INSTALL 10'-4" PMMP | - | - | - | - | 0.01026% | 4427.97 | 4025.438 | 402.532 | 2018-01-01 | 2018-12-31 | 2018-11-13 | 2018-11-13
13026486800 | INSTALL 250'-12" CSHP | - | - | - | - | 1.187% | 512308.25 | 486540.7394 | 25767.5106 | 2018-01-01 | 2018-12-31 | 2018-08-24 | 2018-12-11
18026846000 | INSTALL 100' OF 2"PMMP MAIN | - | - | - | - | 0.02604% | 11243.25 | 7443.8588 | 3799.3912 | 2018-01-01 | 2018-12-31 | 2018-11-17 | 2018-11-19
18026795101 | INSTALL 210'-2" PMMP | - | - | - | - | 0.1018% | 43940.89 | 48760.3055 | -4819.4155 | 2018-01-01 | 2018-12-31 | 2018-11-14 | 2018-11-30
18026841600 | INSTALL 185'-4" PMLP | - | - | - | - | 0.1525% | 65858.15 | 12772.8646 | 53085.2854 | 2018-01-01 | 2018-12-31 | 2018-11-07 | 2018-11-30 | OVERRUN EXPLNATION: CONTRACTOR COSTS INCREASED BY $22,500 AND SEGA INCREASE D BY $5,000. COMPANY LABOR INREASED AS WELL.
18026842300 | INSTALL 50'-4" PMLP | - | - | - | - | 0.04264% | 18411.25 | 13072.8646 | 5338.3854 | 2018-01-01 | 2018-12-31 | 2018-11-21 | 2018-11-30
18026752500 | INSTALL VRG PILOT FOR MONITOR | - | - | - | - | 0.01374% | 5932.05 | 5590.6534 | 341.3966 | 2018-01-01 | 2018-12-31 | 2018-10-08 | 2018-12-29
17026708400 | INSTALL FENCE FOR R1862 | - | - | - | - | 0.06622% | 28589.69 | 8216 | 20373.69 | 2018-01-01 | 2018-12-31 | 2018-11-21 | 2019-08-10 | WAITING ON FENCE CONTRACTOR
18026845400 | INSTALL EFC UNIT | - | - | - | - | 0.01355% | 5850.16 | 5528.9058 | 321.2542 | 2018-01-01 | 2018-12-31 | 2018-12-01 | 2018-12-01 | REPLACED EFC
18026753100 | INSTALL 2 VRG PILOTS | - | - | - | - | 0.03926% | 16948.81 | 10099.3267 | 6849.4833 | 2018-01-01 | 2018-12-31 | 2018-11-26 | 2019-01-02 | JOB WAS ON HOLD DUE TO SCHEDULING
18026846600 | INSTALL 225' OF 2"PMMP MAIN | - | - | - | - | 0.03674% | 15862.26 | 13144.8881 | 2717.3719 | 2018-01-01 | 2018-12-31 | 2018-12-05 | 2018-12-07
18026776300 | INSTALL 3 SSTS | - | - | - | - | 0.1574% | 67963.93 | 26633.4257 | 41330.5043 | 2018-01-01 | 2018-12-31 | 2018-11-26 | 2018-12-14 | OVERRUN EXPLANATION: CONTRACT LABOR INCREASED SIGNIFICANTLY. 16 MORE HOURS OF 5 MAN CREW WERE REQUIRED AND 6.5 HOURS OF ADDITIONAL CONTRACT CREW OT HO URS WERE REQUIRED. 13 ORE HOURS OF 3 MAN CREW HOURS WERE REQUIRED.
17026730002 | INSTALL 14248' - 2"/4" PMMP | - | - | - | - | 3.365% | 1452897.69 | 1798995.594 | -346097.904 | 2018-01-01 | 2018-12-31 | 2018-08-20 | 2018-12-19 | REPLACED SERVICE. INT/EXT INSPECTION COMPLETED BY BJACKSON @ 1000 ON 5-18-1 8. TESTED SERVICE @ 90 PSIG FOR 5 MINS. SOAP TESTED CAP. UMAC 700 EFV INSTA LLED. 5/18/18-JOB ORDER CODED COMPLETE IN ERROR, STILL IN PROGRESS. INSTALLED 8681' OF 2" PE MAIN AND 3291' OF 4" PE MAIN. UNDERRUN EXPLANATION: BECAUSE WE WERE GETTING LATE IN THE YEAR, WE DECIDED TO TAKE OFF A STREET FROM THIS PROJECT AND COMPLETE IT IN 2019. THIS RESULT ED IN LESS PIPELINE WORK AND LESS PAVING RESTORATION.
17026728401 | INSTALL 3209' - 4"/2" PMLP | - | - | - | - | 1.197% | 516625.22 | 687146.0204 | -170520.8004 | 2018-01-01 | 2018-12-31 | 2018-09-20 | 2019-04-05 | UNDERRUN EXPLNATION: THE PAVING COSTS HAVE NOT BEEN ENCOUNTERED YET. THAT S HOULD OCCUR IN THE NEAR FUTURE. EVERYTHING ELSE APPEARS TO BE ON TRACK TO H IT THIS ESTIMATE ONCE THE PAVING LANDS. UNDERRUN EXPLANATION: THE PAVING WAS NOT AS EXPENSIVE AS ESTIMATED.
18026785500 | INSTALL EFC | - | - | - | - | 0.02804% | 12107.47 | 14797.4604 | -2689.9904 | 2018-01-01 | 2018-12-31 | 2018-12-19 | 2018-12-29 | INSTALLED EFC AND MI-WIRELESS UNIT
18026848400 | INSTALL 80'-2" PMMP | - | - | - | - | 0.007237% | 3124.34 | 23093.1885 | -19968.8485 | 2018-01-01 | 2018-12-31 | 2018-12-19 | 2019-01-18 | INSTALLED 73' OF 2" P MP OC LINE. TIED ONTO 50' OF EXISTING 2" P MP. TESTED AT 100PSIG FOR 1 HR. /SOAP TESTED FINAL AT OP. PRESSURE./SOAP TEST CAP AT OP. PRESSURE. AJM
18026848200 | INSTALL 200' OF 4"PMMP MAIN | - | - | - | - | 0.04406% | 19023.71 | 7492.964 | 11530.746 | 2018-01-01 | 2018-12-31 | 2018-12-21 | 2018-12-28
|  | - | - | - | - |  | 2018 Construction Project Budget | 43174000
18026843000 | INSTALL 110'-2" PMLP | - | - | - | - | 0.1509% | 78922.81 | 34180.4409 | 44742.3691 | 2019-01-01 | 2019-12-31 | 2018-12-11 | 2019-01-04 | OVERRUN EXPLANATION: COMPANY LABOR EXCEEDED THE ESTIMATE BECAUSE THE LEAKAG E HAD TO BE MONITORED UNTIL WE COULD GET A BORING MACHINE UP THERE AND GET THE PIPE REPLACED.
18026849000 | INSTALL MI WIRELESS UNIT | - | - | - | - | 0.01401% | 7324.71 | 6384.5731 | 940.1369 | 2019-01-01 | 2019-12-31 | 2019-01-07 | 2019-01-07
18026848800 | INSTALL MI WIRELESS UNIT | - | - | - | - | 0.02046% | 10698.17 | 10197.5731 | 500.5969 | 2019-01-01 | 2019-12-31 | 2019-01-08 | 2019-01-08
18026850000 | REPLACE VALVE | - | - | - | - | 0.02341% | 12239.28 | 7869.4493 | 4369.8307 | 2019-01-01 | 2019-12-31 | 2019-01-10 | 2019-01-10 | REPLACED 4" PLASTIC BALL VALVE. TESTED AT 90PSIG FOR 1 HOUR.
18026761600 | INSTALL 4" PIF | - | - | - | - | 0.05828% | 30474.32 | 21889.8854 | 8584.4346 | 2019-01-01 | 2019-12-31 | 2019-01-08 | 2019-01-23
18026798100 | INSTALL 2" SS FITTING | - | - | - | - | 0.01703% | 8906.34 | 7049.9001 | 1856.4399 | 2019-01-01 | 2019-12-31 | 2019-01-04 | 2019-01-14 | ABANDONED 78' OF 2" CSMP MAIN. TESTED 2" SST @ 90 PSIG FOR 15MINS. SOAP TE STED CAPS.
18026778601 | INSTALL 3100' - 2"/4" PMMP | - | - | - | - | 0.2147% | 112278.35 | 99496.0368 | 12782.3132 | 2019-01-01 | 2019-12-31 | 2018-10-15 | 2019-01-16
19026855100 | INSTALL 50' - 2" PMMP | - | - | - | - | 0.01495% | 7816.21 | 7788.2638 | 27.9462 | 2019-01-01 | 2019-12-31 | 2019-01-16 | 2019-01-16 | INSTALLED 40' OF 2''
18026798900 | INSTALL 625' OF 2"PMMP MAIN | - | - | - | - | 0.06451% | 33732.14 | 24146.8881 | 9585.2519 | 2019-01-01 | 2019-12-31 | 2019-01-02 | 2019-01-18
19026856500 | INSTALL 445'-4" PMLP | - | - | - | - | 0.3295% | 172303.77 | 29115.9203 | 143187.8497 | 2019-01-01 | 2019-12-31 | 2019-01-18 | 2019-01-23 | REPLACED 4" BSLP MAIN WITH 4" PE. OVERRUN EXPLANATION: THIS WAS A MULTIPLE DAY WATER OFF ISSUE WITH MANY EMPL OYES WORKING LONG HOURS FOR MORE THAN ONE OUTAGE. THE CHARGES FOR THE EMPLOYEES THAT WERE SUPPORTING THE EFFORT WHERE NOT CO NSIDERED IN THE ORIGINAL ESTIMATE. ADDITIONALLY, THE 4 MAN CONSTRACT CREW WORKED 52 HOURS OF OVERTIME AND THRE E TIMES THE AMOUNT OF ESTIMATED REGULAR TIME.
19026855900 | INSTALL NON-PRIMARY RELIEF | - | - | - | - | 0.0113% | 5907.62 | 1903.7546 | 4003.8654 | 2019-01-01 | 2019-12-31 | 2019-01-24 | 2019-03-13
17026725301 | INSTALL 3300' OF 4"PMMP MAIN | - | - | - | - | 0.4075% | 213118.5 | 202202.0123 | 10916.4877 | 2019-01-01 | 2019-12-31 | 2019-01-22 | 2019-02-05
18026746400 | INSTALL 115'-6" PHHP/CSHP | - | - | - | - | 0.06545% | 34226.61 | 29746.8817 | 4479.7283 | 2019-01-01 | 2019-12-31 | 2019-02-01 | 2019-02-22
18026800500 | INSTALL 150'-2" PMLP | - | - | - | - | 0.1224% | 64011.45 | 30813.8501 | 33197.5999 | 2019-01-01 | 2019-12-31 | 2018-11-26 | 2019-02-06 | HAD TO WAIT ON M&R TECH FOR TIE IN DUE TO LP TIE INS OVERRUN EXPLANATION: THE JOB TOOK 8X LONGER THAN THE LABOR ESTIMATING TOOL PREDICTED RESULTING IN $12K IN TRUCK AND LABOR EXPENSES MORE THAN ESTIMATED . THERE WAS ABOUT $5K IN ADDITIONAL OVERHEADS DUE TO THE ADDITIONAL WORK. T HERE WAS ALSO $8K IN ADDITIONAL PAVING OVER WHAT WAS ESTIMATED.
19026860100 | INSTALL EFC | - | - | - | - | 0.01063% | 5560.7 | 7262.6656 | -1701.9656 | 2019-01-01 | 2019-12-31 | 2019-02-13 | 2019-02-13 | REPLACED EFC COMMIT DATE ENTERED AS 12/31/18 BY MISTAKE COMMIT DATE ACUALLY SHOULD HAVE BEEN 12//31/19
15026601101 | INSTALL 3854'- 12 & 4" CSHP | - | - | - | - | 4.092% | 2139888.06 | 2142667.2506 | -2779.1906 | 2019-01-01 | 2019-12-31 | 2018-11-13 | 2019-02-22
17026734200 | INSTALL 800' - 2" PMMP MAIN | - | - | - | - | 0.304% | 158951.66 | 147884.7838 | 11066.8762 | 2019-01-01 | 2019-12-31 | 2019-01-22 | 2019-05-22
16026683601 | INSTALL 800' OF 2"/4"PMMP MAIN | - | - | - | - | 0.1255% | 65648.19 | 46066.6033 | 19581.5867 | 2019-01-01 | 2019-12-31 | 2019-01-23 | 2019-02-15
18026779000 | R-1133 INSTALL NEW REG SETTING | - | - | - | - | 0.1253% | 65530.53 | 90267.2523 | -24736.7223 | 2019-01-01 | 2019-12-31 | 2018-10-23 | 2019-03-01 | JOB WAS ON HOLD - WAITING ON STATE HIGHWAY DEPARTMENT
19026857400 | INSTALL 80' OF 2"PMMP MAIN | - | - | - | - | 0.01005% | 5253.13 | 7770.1797 | -2517.0497 | 2019-01-01 | 2019-12-31 | 2019-02-14 | 2019-02-14
19026858000 | INSTALL 400' OF 4"PMLP MAIN | - | - | - | - | 0.0813% | 42516.78 | 23897.5118 | 18619.2682 | 2019-01-01 | 2019-12-31 | 2019-02-04 | 2019-02-15
18026775701 | INSTALL 1,490' - 2"/6" PMIP | - | - | - | - | 0.3332% | 174227.61 | 156681.1595 | 17546.4505 | 2019-01-01 | 2019-12-31 | 2019-02-12 | 2019-02-27
19026858200 | INSTALL 300' OF 2" PMMP MAIN | - | - | - | - | 0.03851% | 20136.36 | 16963.2095 | 3173.1505 | 2019-01-01 | 2019-12-31 | 2019-02-11 | 2019-02-18
19026863100 | INSTALL NEW CHAIN LINK FENCE | - | - | - | - | 0.01313% | 6867.37 | 12912.8016 | -6045.4316 | 2019-01-01 | 2019-12-31 | 2019-02-15 | 2019-02-18
18026845900 | INSTALL 110'- 4"CSHP INLET MN | - | - | - | - | 0.1126% | 58871.29 | 42605.0459 | 16266.2441 | 2019-01-01 | 2019-12-31 | 2019-01-22 | 2019-02-27
19026857100 | INSTALL 40'-4" PMIP | - | - | - | - | 0.03684% | 19263.47 | 25566.3252 | -6302.8552 | 2019-01-01 | 2019-12-31 | 2019-02-18 | 2019-02-22
18026756300 | INSTALL 550' OF 2"PMMP MAIN | - | - | - | - | 0.0423% | 22117.37 | 23888.4008 | -1771.0308 | 2019-01-01 | 2019-12-31 | 2019-02-19 | 2019-02-22
19026857500 | INSTALL 400' OF 2"PMMP MAIN | - | - | - | - | 0.04188% | 21900.72 | 23797.3839 | -1896.6639 | 2019-01-01 | 2019-12-31 | 2019-02-20 | 2019-02-28
18026767601 | INSTALL 420'-4"&6" PMMP | - | - | - | - | 0.2667% | 139472.01 | 103809.9847 | 35662.0253 | 2019-01-01 | 2019-12-31 | 2019-04-10 | 2019-03-29 | OVERRUN EXPLANATION: THE JOB TOOK 39% MORE LABOR THAT ESTIMATED RESULTING I N $4500 OVER IN LABOR AND TRUCK EXPENSE. ADDITIONALLY, WE OVERRAN APROXIMAT ELY $12K IN PAVING.
19026864700 | INSTALL 10' OF 4"PMLP MAIN | - | - | - | - | 0.01528% | 7990.59 | 12412.0783 | -4421.4883 | 2019-01-01 | 2019-12-31 | 2019-03-07 | 2019-05-02 | TWALKER/KY 05-02-19: PER GS 1500.010 7.2.4, THIS PROJECT WAS AN EMERGENCY LEAK REPAIR ON LP MAIN/SERVICE LINE (MAOP 14"WC) THE 4" PLASTIC PIPE WAS PRE-TESTED ON JOB 18-6316798-00 TESTED LESS THAN 1 HOUR. I REVIEWED TEST AND PROJECT WILL GARY SULLIVAN, I HEREBY APPROVE TEST AND TIME.
17026740201 | INSTALL 1900'-2"PMIP | - | - | - | - | 0.2441% | 127641.85 | 99934.492 | 27707.358 | 2019-01-01 | 2019-12-31 | 2018-09-12 | 2019-03-19
18026746900 | INSTALL 1700' 12" CSHP | - | - | - | - | 1.853% | 969011.19 | 1088739.318 | -119728.128 | 2019-01-01 | 2019-12-31 | 2019-01-10 | 2019-03-18
19026861200 | INSTALL 80'-2" PMMP | - | - | - | - | 0.008529% | 4460.3 | 7543.6626 | -3083.3626 | 2019-01-01 | 2019-12-31 | 2019-03-15 | 2019-03-22 | INSTALLED 23' OF 2" PLASTIC MAIN LINE TESTED 100 PSIG 1 HOUR SOAP TESTED FINAL CONN. OP
19026859000 | INSTALL 60'-4" PMLP | - | - | - | - | 0.03087% | 16141.38 | 10460.1658 | 5681.2142 | 2019-01-01 | 2019-12-31 | 2019-05-03 | 2019-05-03
18026786300 | NEW EASEMENT FOR REG STATION | - | - | - | - | 0.03283% | 17170 | 8647.1239 | 8522.8761 | 2019-01-01 | 2019-12-31 |  | 2019-03-19
18026755802 | INSTALL 70'-6" PMLP | - | - | - | - | 0.2874% | 150272.74 | 147474.234 | 2798.506 | 2019-01-01 | 2019-12-31 | 2019-03-20 | 2019-03-22
18026794800 | INSTALL 2200' OF 4"PMMP MAIN | - | - | - | - | 0.1315% | 68775.48 | 69179.2466 | -403.7666 | 2019-01-01 | 2019-12-31 | 2019-03-05 | 2019-03-21
19026860200 | INSTALL 1025' OF 2"PMMP MAIN | - | - | - | - | 0.06816% | 35644.66 | 44639.7355 | -8995.0755 | 2019-01-01 | 2019-12-31 | 2019-03-12 | 2019-03-25
19026865400 | INSTALL 4'-3" PMMP | - | - | - | - | 0.01084% | 5670.75 | 10175.6826 | -4504.9326 | 2019-01-01 | 2019-12-31 | 2019-03-20 | 2019-03-21 | INSTALLED 48.5'' OF 3'' PMP MAIN WITH CRITICAL VALVE. PRE TESTED PIPE FOR 1HR AT 90LBS TEST OK. INSTALLED WITH 2 EFC SOAP TEST FINAL TIE INS NGF. BARHOLE BANKS NGF. DPI IS CLEARED ON JO-19026865500 -- REFERENCE JO-19026865500 FOR THIS JOB AND JOB NUMBER FOR MATERIALS, PRESSURE TEST DATA, AND FACILITY FAILURE. KKINDER 03/21/19 1600
19026867300 | INSTALL 40' OF 3"PMLP MAIN | - | - | - | - | 0.05232% | 27361.96 | 24214.6883 | 3147.2717 | 2019-01-01 | 2019-12-31 | 2019-04-12 | 2019-04-12 | INSTALLED 33' OF NEW 030 PL MAIN TESTED ON SITE FOR 61 MINS REFUR TO DPI D094589
18026786201 | INSTALL 3,250' - 2" PMMP | - | - | - | - | 0.3228% | 168826.19 | 142507.1449 | 26319.0451 | 2019-01-01 | 2019-12-31 | 2018-11-05 | 2019-03-26
18026781901 | INSTALL 1000' OF 6"PMMP MAIN | - | - | - | - | 0.404% | 211247.45 | 215170.0254 | -3922.5754 | 2019-01-01 | 2019-12-31 | 2019-02-27 | 2019-03-26
17026739300 | INSTALL 274'- 8" PM/CSMP | - | - | - | - | 0.1785% | 93319.94 | 76197.5408 | 17122.3992 | 2019-01-01 | 2019-12-31 | 2019-03-11 | 2019-03-29
17026740501 | INSTALL 4,450' - 6/4/2" PMMP | - | - | - | - | 0.9165% | 479246.27 | 450558.9213 | 28687.3487 | 2019-01-01 | 2019-12-31 | 2018-11-12 | 2019-04-03 | PROJECT OVER RAN COMMIT DATE DUE TO HEAVY ROCK OVER 1000' WITH A MAJOR ROCK BORE
19026861600 | INSTALL 97'-3" PMMP | - | - | - | - | 0.1138% | 59513.17 | 45857.1641 | 13656.0059 | 2019-01-01 | 2019-12-31 | 2019-03-13 | 2019-03-29
19026850600 | INSTALL 375' OF 4"PMMP MAIN | - | - | - | - | 0.04529% | 23683.26 | 23051.3839 | 631.8761 | 2019-01-01 | 2019-12-31 | 2019-03-27 | 2019-04-01 | INSTALLED 400' OF 4" PLASTIC MAIN. TESTED AT 90PSIG FOR 1 HOURS. INSTALLED BY OC.
19026859200 | INSTALL 3250' OF 2"PMMP MAIN | - | - | - | - | 0.3109% | 162596.23 | 151407.471 | 11188.759 | 2019-01-01 | 2019-12-31 | 2019-03-04 | 2019-04-04
19026869300 | INSTALL 10'-3" PMLP | - | - | - | - | 0% | 0 | 7452.8403 | -7452.8403 | 2019-01-01 | 2019-12-31 | 2019-04-04 | 2019-04-04
19026878800 | INSTALL REGULATION | - | - | - | - | 0% | 0 | 1744.2587 | -1744.2587 | 2019-01-01 | 2019-12-31 | 2019-04-05 | 2019-04-05 | WORK DONE ON 2612 JOB ORDER 19-6826920-00 TO CORRECT AUDIT FINDING CAPITAL JOB OBTAINED AFTER WORK COMPLETED
18026756801 | INSTALL 500' - 2" CSHP | - | - | - | - | 0.1379% | 72110.42 | 56417.9027 | 15692.5173 | 2019-01-01 | 2019-12-31 | 2019-04-01 | 2019-04-19
18026783401 | INSTALL 5,400' - 2"/4" PMMP | - | - | - | - | 0.4795% | 250762.09 | 230334.9213 | 20427.1687 | 2019-01-01 | 2019-12-31 | 2019-01-19 | 2019-04-10
19026850701 | INSTALL 675' OF 2"PMMP MAIN | - | - | - | - | 0.1604% | 83893.15 | 105956.0473 | -22062.8973 | 2019-01-01 | 2019-12-31 | 2019-04-04 | 2019-04-08 | INSTALLED 669' OF 2" MAIN LINE PLASTIC PIPE. TESTED AT 90PSIG FOR 1 HOURS. INSTALLED BY DIRECTIONAL BORING. ALL PRE AND POST SEWER VIDEO WORK DONE.
19026858300 | INSTALL 3100' OF 2"PMMP MAIN | - | - | - | - | 0.1128% | 58970.19 | 69931.5371 | -10961.3471 | 2019-01-01 | 2019-12-31 | 2019-03-21 | 2019-04-10
18026784001 | INSTALL 1385'-6" PMMP | - | - | - | - | 0.8172% | 427330.33 | 471729.6551 | -44399.3251 | 2019-01-01 | 2019-12-31 | 2019-01-22 | 2019-04-10 | UNDERRUN EXPLANATION: IT APPEARS THAT SOME OF THE HARD SURFACE RESTORATION WAS CHARGED TO THE ASSOCIATED LP PROJECT THAT WAS WORKED SIMULTANEOUSLY WIT H THIS ONE.
18026783800 | INSTALL 320'-8" PMLP | - | - | - | - | 0.4428% | 231561.52 | 186541.4534 | 45020.0666 | 2019-01-01 | 2019-12-31 | 2019-02-14 | 2019-04-11 | OVERRUN EXPLANATION: THIS PROJECT HAD TO BE WORKED AT NIGHT AND THE HOURLY CREW RATES TOOK EFFECT AND LED TO SUBSTANTUALLY MORE CONTRACT LABOR THAN ES TIMATED. ADDITIONALLY, THE CITY REQUIRED THAT WE USE THEIR SPECIFIED PAVER DUE TO THEIR INCREASED CAPABILITIES WHICH LED TO INCREASED COSTS AS WELL.
17026714900 | INSTALL 4225' OF 2"PMMP MAIN | - | - | - | - | 1.765% | 923117.22 | 813635.1267 | 109482.0933 | 2019-01-01 | 2019-12-31 | 2018-03-19 | 2019-05-30
18026772800 | INSTALL 250' OF 2"PMMP | - | - | - | - | 0.02955% | 15452.23 | 17789.2058 | -2336.9758 | 2019-01-01 | 2019-12-31 | 2018-06-14 | 2019-04-15
18026849900 | INSTALL REG #1863 DUAL RUN | - | - | - | - | 0.1713% | 89581.34 | 93915.8656 | -4334.5256 | 2019-01-01 | 2019-12-31 | 2019-01-28 | 2019-05-04 | JOB WAS ON HOLD FOR LAND/ACCESS ISSUES AND CREW AVAILABILITY
19026870300 | INSTALL 35' OF 2"PMMP MAIN | - | - | - | - | 0.007913% | 4138.06 | 4141.4247 | -3.3647 | 2019-01-01 | 2019-12-31 | 2019-04-16 | 2019-04-18
19026864100 | INSTALL 485' OF 2"PMMP MAIN | - | - | - | - | 0.05138% | 26868.66 | 22646.8678 | 4221.7922 | 2019-01-01 | 2019-12-31 | 2019-04-08 | 2019-04-19
19026870000 | INSTALL 60' OF 3"BSLP MAIN | - | - | - | - | 0.005272% | 2756.75 | 24476.1553 | -21719.4053 | 2019-01-01 | 2019-12-31 | 2019-05-09 | 2019-05-09 | INSTALLED 45' OF 030 AND 4' OF 040 PL ML TO REPL LEAKING 030 BS ML NEW ML TESTED @ 90 # FOR 1 HR THEN PIGGED INSTALLED 2 ANODES AND TRACER WIRE MB @ ALL POINTS NEEED
18026801800 | INST. FN 59 EXTRA LP OPP | - | - | - | - | 1.802% | 942304.58 | 21708.8722 | 920595.7078 | 2019-01-01 | 2019-12-31 | 2019-04-15 | 2021-04-28 | REGULATOR INSTALLED BY JAMES PASLEY ON 4/24/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
17026705600 | INSTALL 2"GV-10' 2"CSHP MAIN | - | - | - | - | 0.1088% | 56876.12 | 47831.1411 | 9044.9789 | 2019-01-01 | 2019-12-31 | 2019-04-17 | 2019-05-01
18026821500 | INST. FN 42 EXTRA LP OPP | - | - | - | - | 0.1256% | 65668.91 | 21708.8722 | 43960.0378 | 2019-01-01 | 2019-12-31 | 2019-04-15 | 2021-04-14 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 4/29/2019 ER350 INSTALLED ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026863200 | INSTALL 1600' OF 2"PMIP MAIN | - | - | - | - | 0.2004% | 104820.38 | 63001.6694 | 41818.7106 | 2019-01-01 | 2019-12-31 | 2019-03-28 | 2019-05-02 | COMMIT DATE WAS NOT MET DUE TO THE CREW ENCOUNTERING ROCK DURING THE BORING PROCESS. SCHEDULING AND ENGINEERING ADV OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR REGULATOR DIRECTIONAL BORE; HO WEVER, THERE WERE 533 UNDITS OF DIRECTIONAL ROCK BORE THAT WERE REQUIRED. T HE ADDED COST OF ROCK BORE PLUS THE OVERHEAD EFFECT OF THOSE ADDITIONAL COS T WERE THE PRIMARY DRIVERS OF OVERRUN.
19026864000 | INSTALL 200' OF 2"PMMP MAIN | - | - | - | - | 0.03732% | 19517.08 | 13477.9207 | 6039.1593 | 2019-01-01 | 2019-12-31 | 2019-04-16 | 2019-04-30
18026821700 | INST. FN 43 EXTRA LP OPP | - | - | - | - | 0.05093% | 26633.47 | 21708.8722 | 4924.5978 | 2019-01-01 | 2019-12-31 | 2019-04-30 | 2021-04-14 | CCC CALLED BY JPASLEY CLEARANCE TICKET# 13241 REGULATOR INSTALLED BY RYAN WILLIAMS ON 4/30/2019 ER350 INSTALLED ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026868200 | INSTALL MI WIRELESS EFC | - | - | - | - | 0.008569% | 4481.07 | 11104.5495 | -6623.4795 | 2019-01-01 | 2019-12-31 | 2019-04-30 | 2019-04-30
18026802400 | INST. FN 13485 EXTRA LP OPP | - | - | - | - | 0.07246% | 37892.29 | 21708.8722 | 16183.4178 | 2019-01-01 | 2019-12-31 | 2019-04-30 | 2021-02-19 | REGULATOR REPLACED BY JAMES PASLEY ON 5/1/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026810800 | INST. FN 14064 EXTRA LP OPP | - | - | - | - | 0.09228% | 48256.49 | 21708.8722 | 26547.6178 | 2019-01-01 | 2019-12-31 | 2019-04-25 | 2021-05-19 | GCCC TICKET NOT REQUIRED NOT AT ANY STATION OFF SITE WORKING ON PAPERWORK CFARIS 1/29/21 REGULATOR INSTALLED BY JAMES PASLEY ON 5/1/2019 ER350 INSTALLED ON 12/7/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/19/2021 GCCC TICKET NOT REQUIRED ON 5/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026821900 | INST. FN 44 EXTRA LP OPP | - | - | - | - | 0.03588% | 18761.34 | 21708.8722 | -2947.5322 | 2019-01-01 | 2019-12-31 | 2019-05-01 | 2021-04-14 | CONTROL SHEET 007558 VOIDED INFO ENTERED ON CONTROR SHEET 007556 CCC# 14639 REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/1/2019 ER350 INSTALLED ON 7/31/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026824000 | INST. FN 220 EXTRA LP OPP | - | - | - | - | 0.03809% | 19919.69 | 21708.8722 | -1789.1822 | 2019-01-01 | 2019-12-31 | 2019-05-01 | 2021-04-14 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/1/2019 ER350 INSTALLED ON 7/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026803600 | INST. FN 78 EXTRA LP OPP | - | - | - | - | 0.06958% | 36386.58 | 21708.8722 | 14677.7078 | 2019-01-01 | 2019-12-31 | 2019-05-02 | 2021-04-28 | CMCHOLAN 2-23-2021 CCC# 12914 GCCC# 12914 REGULATOR INSTALLED BY JAMES PASLEY ON 5/2/2019 ER350 INSTALLED ON 2/23/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026828600 | INST. FN 21193 EXTRA LP OPP | - | - | - | - | 0.03955% | 20684.05 | 21708.8722 | -1024.8222 | 2019-01-01 | 2019-12-31 | 2019-05-02 | 2021-04-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/2/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS GASKET STRAINER NOT REQUIRED SETTING HAS T-STRAINER INSTALLED
18026828800 | INST. FN 21194 EXTRA LP OPP | - | - | - | - | 0.02868% | 14999.81 | 21708.8722 | -6709.0622 | 2019-01-01 | 2019-12-31 | 2019-05-02 | 2021-04-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/2/2019 GASKET STRAINER NOT REQUIRED T-STAINER INSTALLED IN SETTING CRY-IN ER350 INSTALLED ON RUN 1 GCCC TICKET NOT REQUIRED ON 4/26/2021 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026803800 | INST. FN 14160 EXTRA LP OPP | - | - | - | - | 0.05337% | 27911.19 | 21708.8722 | 6202.3178 | 2019-01-01 | 2019-12-31 | 2019-05-03 | 2021-02-18 | REGULATOR REPLACED BY JAMES PASLEY ON 5/3/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823800 | INST. FN 183 EXTRA LP OPP | - | - | - | - | 0.0324% | 16942.25 | 21708.8722 | -4766.6222 | 2019-01-01 | 2019-12-31 | 2019-05-03 | 2021-04-27 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/3/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026767000 | ACQUIRE LAND FOR SCADA BUILD. | - | - | - | - | 0.02967% | 15516.89 | 10852 | 4664.89 | 2019-01-01 | 2019-12-31 | 2018-04-12 | 2019-05-04 | 1/7/20: COMPLETED BY BRYAN SLONE FOR CHRIS DAVIS W/TEAM FISHEL
18026827900 | INST. FN 694 EXTRA LP OPP | - | - | - | - | 0.03715% | 19425.28 | 21708.8722 | -2283.5922 | 2019-01-01 | 2019-12-31 | 2019-05-04 | 2021-04-29 | PAID STRIGHT TIME INSTEAD OF TIME AND 1/2 PAID MAKEUP 4 HRS 98-150 AND 4 HRS 98-130 .MAKE UP UNDER PAY FOR SATURDAY 05/04/19 ADVISED GREGORY PECK REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/4/2019 ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT RQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026768600 | INSTALL 1402'-2"&4" PMIP | - | - | - | - | 0.364% | 190345.26 | 105475.5706 | 84869.6894 | 2019-01-01 | 2019-12-31 | 2019-04-01 | 2019-07-02 | OVERRUN EXPLANATION: 580 HOURS OF FLAGGING WERE REQUIRED OVER WHAT WAS ESTI MATED AND 52 DAYS OF PER DIEM. IN ADDITION, 1166 UNITS OF EXTRA DEPTH AND 591 UNITS OF COLD PATCH WERE NOT ESTIMATED ALL OF WHCIH CONTRIBUTED TO THE OVERRUN. LEVEL 2 VARIANCE ENTERED IN WMSDOCS.
18026801200 | INST. FN 50 EXTRA LP OPP | - | - | - | - | 0.04681% | 24479.58 | 21708.8722 | 2770.7078 | 2019-01-01 | 2019-12-31 | 2019-05-06 | 2021-02-16 | REGULATOR REPLACED BY CYNTHIA FARIS ON 5/6/2019 ER350 INSTALLED BY WADE SHIMFESS ON 7/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
18026827700 | INST. FN 693 EXTRA LP OPP | - | - | - | - | 0.0414% | 21647.58 | 21708.8722 | -61.2922 | 2019-01-01 | 2019-12-31 | 2019-05-06 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/6/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/2021 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026806000 | INST. FN 13441 EXTRA LP OPP | - | - | - | - | 0.1043% | 54555.63 | 21708.8722 | 32846.7578 | 2019-01-01 | 2019-12-31 | 2019-05-07 | 2021-02-19 | GCCC TICKET NOT REQUIRED ON 2/17/21 NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS REGULATOR REPLACED BY CYNTHIA FARIS ON 5/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026822200 | INST. FN 47 EXTRA LP OPP | - | - | - | - | 0.0448% | 23426.71 | 21708.8722 | 1717.8378 | 2019-01-01 | 2019-12-31 | 2019-04-18 | 2021-04-27 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026822400 | INST. FN 48 EXTRA LP OPP | - | - | - | - | 0.04135% | 21624.51 | 21708.8722 | -84.3622 | 2019-01-01 | 2019-12-31 | 2019-05-07 | 2021-04-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS LP SYSTEM IN IRVINE HAS BEEN SEPERATED THIS IS NOW A SINGLE FEED STATION WITH NEW SYSTEM NUMBER 32049011 I&C HAS BEEN ADVISED THAT THEY WILL NEED TO CONVERT THIS TO A FULL TIME MONITORED ER350
18026801400 | INST. FN 16538 EXTRA LP OPP | - | - | - | - | 0.05446% | 28480.37 | 21708.8722 | 6771.4978 | 2019-01-01 | 2019-12-31 | 2019-05-06 | 2021-05-13 | REGULATOR INSTALLED BY JAMES KEESEE ON 5/8/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026801600 | INST. FN 14063 EXTRA LP OPP | - | - | - | - | 0.03683% | 19260.99 | 21708.8722 | -2447.8822 | 2019-01-01 | 2019-12-31 | 2019-05-08 | 2021-04-28 | GCCC# 11422 GCCC# 12986 CMCHOLAN 2-24-2021 CCC# 12986 REGULATOR INSTALLED BY JAMES KEESEE ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026824200 | INST. FN 221 EXTRA LP OPP | - | - | - | - | 0.03192% | 16691.68 | 21708.8722 | -5017.1922 | 2019-01-01 | 2019-12-31 | 2019-05-08 | 2021-04-27 | 12 HRS FLAGGING PAID AS LABORERS STRIGHT TIME PER GREGORY PECK REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026815100 | INST. FN 130 EXTRA LP OPP | - | - | - | - | 0.05449% | 28495.96 | 21708.8722 | 6787.0878 | 2019-01-01 | 2019-12-31 | 2019-05-06 | 2021-02-05 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 5/9/19 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/3/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026824400 | INST. FN 13986 EXTRA LP OPP | - | - | - | - | 0.03519% | 18399.76 | 21708.8722 | -3309.1122 | 2019-01-01 | 2019-12-31 | 2019-05-09 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/9/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026875500 | INSTALL 14' OF 4"PMMP MAIN | - | - | - | - | 0.03177% | 16610.89 | 6535.4567 | 10075.4333 | 2019-01-01 | 2019-12-31 | 2019-05-09 | 2019-05-13
19026864600 | INSTALL 435' OF 2"PMMP MAIN | - | - | - | - | 0.07152% | 37399.62 | 20756.3589 | 16643.2611 | 2019-01-01 | 2019-12-31 | 2019-05-03 | 2019-05-15
19026863500 | INSTALL 850' OF 2"PMMP MAIN | - | - | - | - | 0.05965% | 31192.57 | 33977.8678 | -2785.2978 | 2019-01-01 | 2019-12-31 | 2019-05-03 | 2019-05-16
18026844201 | INSTALL 1619'-4"/2" PMLP | - | - | - | - | 0.4711% | 246337.53 | 271601.8206 | -25264.2906 | 2019-01-01 | 2019-12-31 | 2019-04-02 | 2019-07-03
19026871100 | INSTALL 40' OF 4"PMMP MAIN | - | - | - | - | 0.009803% | 5126.15 | 6260.678 | -1134.528 | 2019-01-01 | 2019-12-31 | 2019-05-16 | 2019-05-17 | SEE PAPER COPIES IN PACKET PIPE TEST WAS PERFORMED ON SITE AND WAS ACCEPTABLE/ 90# FOR ONE HOUR AND THE TIE IN JOINTS WERE SOAP TESTED FOR 5 MINUTES AT OPERATING PRESSURE SEE PAPER PACKET
19026870400 | INSTALL 60' OF 2"PMMP MAIN | - | - | - | - | 0.01414% | 7392.67 | 7261.6795 | 130.9905 | 2019-01-01 | 2019-12-31 | 2019-05-17 | 2019-05-17
18026817100 | INST. FN 193 EXTRA LP OPP | - | - | - | - | 0.05066% | 26494.08 | 21708.8722 | 4785.2078 | 2019-01-01 | 2019-12-31 | 2019-05-10 | 2021-01-25 | INLET AND OUTLET VALVE ON AND LOCKED - BYPASS VALVE OFF AND LOCKED JPASLEY 5-20-19 REGULATOR REPLACED BY JIM PASLEY ON 5/20/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/25/21
18026822800 | INST. FN 162 EXTRA LP OPP | - | - | - | - | 0.05299% | 27711.91 | 21708.8722 | 6003.0378 | 2019-01-01 | 2019-12-31 | 2019-05-10 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/20/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026873400 | INSTALL 2'-2" PMMP | - | - | - | - | 0.0003511% | 183.62 | 4522.9032 | -4339.2832 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2019-06-18 | INSTALLED 4 FT PEICE OF 2 IN MAIN TEST 90 LB FOR 20 MIN TEST BYPASS FOR 1 HR SOAP TEST FINAL TIE IN AT OP FOR 5 MIN BAR HOLE BANKS NO READINGS FOUND
18026816900 | INST. FN 190 EXTRA LP OPP | - | - | - | - | 0.06411% | 33524.23 | 21708.8722 | 11815.3578 | 2019-01-01 | 2019-12-31 | 2019-05-10 | 2021-01-25 | INLET AND OUTLET VLVS FULLY OPEN AND BYPASS VLV OFF AND LOCKED JPASLEY 5-21-19 1050 PF REGULATOR INSTALLED BY JPASLEY 5/21/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/21
18026817300 | INST. FN 194 EXTRA LP OPP | - | - | - | - | 0.06682% | 34943.03 | 21708.8722 | 13234.1578 | 2019-01-01 | 2019-12-31 | 2019-05-15 | 2020-12-28 | INLET AND OUTLET VLV ON AND LOCKED - BYPASS VLV OFF AND LOCKED LOWERED PRESSURES BACK TO 10" WC REGULATOR INSTALLED BY JAMES PASLEY ER350 INSTALLED BY CYNTHIA FARIS WITH ACP PAPERWORK COMPLETED BY CYNTHIA FARIS APPROVAL JUST OBTAINED TO CO JOB AND SEND TO CLOSE OUT
18026826400 | INST. FN 317 EXTRA LP OPP | - | - | - | - | 0.04368% | 22843.73 | 21708.8722 | 1134.8578 | 2019-01-01 | 2019-12-31 | 2019-05-13 | 2021-04-28 | JKEESEE 5-21-19 1524 INLET AND OUTLET VALVES ON / BYPASS OFF SENSING LINES ON REGULATOR INSTALLED BY JAMES KEESEE ON 5/21/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026872900 | INSTALL 378' 4" & 10' 3" PMMP | - | - | - | - | 0.1458% | 76245.32 | 98659.184 | -22413.864 | 2019-01-01 | 2019-12-31 | 2019-05-09 | 2019-06-25
18026817500 | INST. FN 199 EXTRA LP OPP | - | - | - | - | 0.0599% | 31321.51 | 21708.8722 | 9612.6378 | 2019-01-01 | 2019-12-31 | 2019-05-22 | 2021-01-25 | INLET AND OUTLET VALVES FULL OPEN - BYPASS VALVE FULLY CLOSED JPASLEY 5-22-19 MONITOR REGULATOR INSTALLED BY JAMES PASLEY 5/22/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/21 GCCC TICKET NOT REQUIRED FOR PAPERWORK COMPLETION 1/25/21 NOT AT STATION OFF SITE AT REMOTE LOCATION
18026827500 | INST. FN 691 EXTRA LP OPP | - | - | - | - | 0.05066% | 26489.75 | 21708.8722 | 4780.8778 | 2019-01-01 | 2019-12-31 | 2019-05-22 | 2021-04-27 | JKEESEE 5-22-19 1330 INLET AND OUTLET VALVES ON / BYPASS OFF SENSE LINES ON REGULATOR INSTALLED BY JAMES KEESEE ON 5/22/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE OCMPLETING PAPERWORK CFARIS
18026772900 | INSTALL 575' OF 2"PMMP MAIN | - | - | - | - | 0.04482% | 23438.09 | 27269.8864 | -3831.7964 | 2019-01-01 | 2019-12-31 | 2019-05-17 | 2018-05-24
18026813400 | INST. FN 22195 EXTRA LP OPP | - | - | - | - | 0.04338% | 22683.93 | 21708.8722 | 975.0578 | 2019-01-01 | 2019-12-31 | 2019-05-23 | 2021-02-19 | INLET AND OUTLET VLV FULL OPEN - NO BYPASS VALVE REGULATOR REPLACED BY JAMES PASLEY ON 5/23/2019 ER350 INSTALLED BY CHRIS COX ON 7/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026813600 | INST. FN 22196 EXTRA LP OPP | - | - | - | - | 0.04214% | 22036.53 | 21708.8722 | 327.6578 | 2019-01-01 | 2019-12-31 | 2019-05-24 | 2021-02-19 | REGULATOR REPLACED BY JAMES PASLEY ON 5/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026869900 | INSTALL 225' OF 2"PMMP MAIN | - | - | - | - | 0.0246% | 12861.74 | 14833.8493 | -1972.1093 | 2019-01-01 | 2019-12-31 |  | 2019-05-24
19026870901 | INSTALL 15'-2" PMMP | - | - | - | - | 0.04013% | 20986.01 | 25434.5407 | -4448.5307 | 2019-01-01 | 2019-12-31 | 2019-04-17 | 2020-02-20
19026867701 | INSTALL 2100' OF 2"PMMP MAIN | - | - | - | - | 0.3048% | 159409.72 | 146669.7395 | 12739.9805 | 2019-01-01 | 2019-12-31 | 2019-05-02 | 2019-06-10
18026835800 | INST. FN 216 EXTRA LP OPP | - | - | - | - | 0.0366% | 19139.06 | 21708.8722 | -2569.8122 | 2019-01-01 | 2019-12-31 | 2019-05-30 | 2021-03-24 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/30/2019 ER350 INSTALLED BY DANNY ASH ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026836500 | INST. FN 12831 EXTRA LP OPP | - | - | - | - | 0.04885% | 25544.43 | 21708.8722 | 3835.5578 | 2019-01-01 | 2019-12-31 | 2019-05-28 | 2021-04-08 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/30/2019 ER350 INSTALLED BY JOSH MULLINS ON 10/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026781000 | R-1222 ACQUIRE 25X25 REG SITE | - | - | - | - | 0.03598% | 18817.11 | 28537 | -9719.89 | 2019-01-01 | 2019-12-31 |  | 2019-05-31 | REG SITE & EASEMENT ACQUIRED BY AUTUMN DMYTREWYCZ MAY, 2019 (BKSLONE)
18026829800 | INST. FN 12 EXTRA LP OPP | - | - | - | - | 0.04649% | 24308.45 | 22950.8722 | 1357.5778 | 2019-01-01 | 2019-12-31 | 2019-05-13 | 2021-03-25 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/31/2019 ER350 INSTALLED BY DANNY ASH ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/25/2021 GCCC TICKET NOT REQUIRED ON 3/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026865100 | ACQUIRE ESMT OVER CARMAN PROPY | - | - | - | - | 0.2489% | 130139.09 | 170919 | -40779.91 | 2019-01-01 | 2019-12-31 | 2019-03-07 | 2019-05-31 | EASEMENT ACQUIRED BY AUTUMN DYMTREWYCZ MAY, 2019 (BKSLONE) UNDERRUN EXPLANATION: WE WERE ABLE TO GET THE EASEMENT FOR LESS THAN WE ORI GINALLY ESTIMATED. IN ADDITON, OVERHEADS WERE NOT APPLIED TO THIS EXPENSE.
18026836200 | INST. FN 12819 EXTRA LP OPP | - | - | - | - | 0.05128% | 26817.82 | 21708.8722 | 5108.9478 | 2019-01-01 | 2019-12-31 | 2019-06-01 | 2021-03-23 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/01/2019 ER350 INSTALLED BY JOSH MULLINS ON 08/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 03/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026830200 | INST. FN 14 EXTRA LP OPP | - | - | - | - | 0.03196% | 16714.92 | 22950.8722 | -6235.9522 | 2019-01-01 | 2019-12-31 | 2019-06-03 | 2021-03-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/3/2019 ER350 INSTALLED BY DANNY ASH ON 6/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026830400 | INST. FN 16 EXTRA LP OPP | - | - | - | - | 0.03383% | 17690.8 | 22950.8722 | -5260.0722 | 2019-01-01 | 2019-12-31 | 2019-06-03 | 2021-03-22 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/3/2019 ER350 INSTALLED BY DANNY ASH ON 6/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
19026869500 | INSTALL 265' OF 2"PMMP MAIN | - | - | - | - | 0.03333% | 17429.7 | 16744.8667 | 684.8333 | 2019-01-01 | 2019-12-31 | 2019-05-28 | 2019-06-06
18026806600 | INST. FN 14143 EXTRA LP OPP | - | - | - | - | 0.06413% | 33534.32 | 21708.8722 | 11825.4478 | 2019-01-01 | 2019-12-31 | 2019-05-28 | 2021-05-12 | INLET VALVE AND OUTLET VALVE FULL ON. BYPASS VALVE OFF AND LOCKED. JPASLEY 05/31/2019. REGULATOR INSTALLED BY JAMES PASLEY ON 6/4/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026831900 | INST. FN 24 EXTRA LP OPP | - | - | - | - | 0.0334% | 17468.35 | 22950.8722 | -5482.5222 | 2019-01-01 | 2019-12-31 | 2019-06-04 | 2021-03-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/4/2019 ER350 INSTALLED BY DANNY ASH ON 6/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026836000 | INST. FN 13023 EXTRA LP OPP | - | - | - | - | 0.04081% | 21341.08 | 21708.8722 | -367.7922 | 2019-01-01 | 2019-12-31 | 2019-06-04 | 2021-03-24 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/04/2019 ER350 INSTALLED BY DANNY ASH ON 06/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 03/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026834900 | INST. FN 158 EXTRA LP OPP | - | - | - | - | 0.068% | 35558.27 | 22950.8722 | 12607.3978 | 2019-01-01 | 2019-12-31 | 2019-06-05 | 2021-03-22 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/06/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026879700 | INSTALL 5'-3" PMIP EMERGENCY | - | - | - | - | 0.0001032% | 53.98 | 114.7501 | -60.7701 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2019-06-18 | INSTALLED 5' OF 3" PLASTIC TO REPAIR DIG IN SEE JO# 19711923300
18026820700 | INST. FN 37 EXTRA LP OPP | - | - | - | - | 0.03107% | 16248.49 | 21708.8722 | -5460.3822 | 2019-01-01 | 2019-12-31 | 2019-06-08 | 2021-04-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026818100 | INST. FN 14201 EXTRA LP OPP | - | - | - | - | 0.07094% | 37098.15 | 21708.8722 | 15389.2778 | 2019-01-01 | 2019-12-31 | 2019-05-28 | 2021-02-26 | REGULATOR INSTALLED BY JAMES PASLEY ON 6/10/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026835400 | INST. FN 167 EXTRA LP OPP | - | - | - | - | 0.0437% | 22849.98 | 21708.8722 | 1141.1078 | 2019-01-01 | 2019-12-31 | 2019-06-05 | 2021-03-31 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/10/2019 ER350 INSTALLED BY DANNY ASH ON 6/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026818500 | INST. FN 208 EXTRA LP OPP | - | - | - | - | 0.0579% | 30275.86 | 21708.8722 | 8566.9878 | 2019-01-01 | 2019-12-31 | 2019-06-04 | 2021-02-26 | INSTALLED SLAM SHUT SET POINTS 4" AND 20" W.C. MONITOR SET AT 14"W.C. INLE T & OUTLET VLVS ON, BYPASS OFF AND ALL VLV LOCKED. SOAP TEST OK. MMCKUNE 6-11-19. REGULATOR INSTALLED BY MIKE MCKUNE ON 6/11/2019 ER350 INSTALLED BY CYNTHIA FARIS ON 9/6/2019 ER350 REPLACED BY CHRIS COX ON 10/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT RQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026834700 | INST. FN 157 EXTRA LP OPP | - | - | - | - | 0.03993% | 20878.98 | 22950.8722 | -2071.8922 | 2019-01-01 | 2019-12-31 | 2019-06-11 | 2021-03-23 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/11/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026836400 | INST. FN 12813 EXTRA LP OPP | - | - | - | - | 0.04197% | 21946.94 | 21708.8722 | 238.0678 | 2019-01-01 | 2019-12-31 | 2019-06-11 | 2021-03-24 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/11/2019 ER350 INSTALLED BY DANNY ASH ON 6/29/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026818300 | INST. FN 207 EXTRA LP OPP | - | - | - | - | 0.0872% | 45598.27 | 21708.8722 | 23889.3978 | 2019-01-01 | 2019-12-31 | 2019-05-30 | 2021-02-26 | INLET AND OUTLET VLV FULL ON - BYPASS OFF AND LOCKED REGULATOR INSTALLED BY JAMES PASLEY ON 6/13/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026827200 | INST. FN 661 EXTRA LP OPP | - | - | - | - | 0.03029% | 15841.11 | 21708.8722 | -5867.7622 | 2019-01-01 | 2019-12-31 | 2019-06-13 | 2021-04-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/13/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026879900 | INSTALL 40' OF 4"PMLP MAIN | - | - | - | - | 0.02771% | 14489.69 | 19353.5151 | -4863.8251 | 2019-01-01 | 2019-12-31 | 2019-06-20 | 2019-06-20
18026781300 | INSTALL 750' OF 4"PMLP MAIN | - | - | - | - | 0.04649% | 24308.98 | 21512.6987 | 2796.2813 | 2019-01-01 | 2019-12-31 | 2019-06-10 | 2019-06-14 | REVIEWED TIE-IN PLAN WITH ENGINEERING ON 6-14-19 MISSED COMMIT DUE TO WEATHER/PERSONNEL/EQUIPMENT
18026815300 | INST. FN 132 EXTRA LP OPP | - | - | - | - | 0.05042% | 26365.04 | 21708.8722 | 4656.1678 | 2019-01-01 | 2019-12-31 | 2019-06-14 | 2021-04-28 | INLET AND OUTLET VLVS FULL OPEN - BYPASS VLV OFF AND LOCKED GCCC# 13164 CMCHOLAN 2-25-2021 CCC# 13164 GCCC#13706 CMCHOLAN 3-2-2021 CCC#13706 REGULATOR INSTALLED BY JAMES PASLEY ON 6/14/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026818900 | INST. FN 210 EXTRA LP OPP | - | - | - | - | 0.06277% | 32824.45 | 21708.8722 | 11115.5778 | 2019-01-01 | 2019-12-31 | 2019-06-04 | 2021-02-26 | INLET AND OUTLET VLVS FULL OPEN - BYPASS VLV OFF AND LOCKED REGULATOR INSTALLED BY JAMES PASLEY ON 6/14/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026880100 | INSTALL 11'-3" PMLP | - | - | - | - | 0.02823% | 14762.46 | 7810.5277 | 6951.9323 | 2019-01-01 | 2019-12-31 | 2019-07-11 | 2019-06-14
19026880400 | LAND FACILITY FOR REG STATION | - | - | - | - | 0.002295% | 1200 | 72.0899 | 1127.9101 | 2019-01-01 | 2019-12-31 |  | 2019-06-14
18026819300 | INST. FN 218 EXTRA LP OPP | - | - | - | - | 0.05054% | 26426.63 | 21708.8722 | 4717.7578 | 2019-01-01 | 2019-12-31 | 2019-06-15 | 2021-02-25 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/15/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026806400 | INST. FN 14199 EXTRA LP OPP | - | - | - | - | 0.04171% | 21811.55 | 21708.8722 | 102.6778 | 2019-01-01 | 2019-12-31 | 2019-06-17 | 2021-04-28 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/17/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807800 | INST. FN 119 EXTRA LP OPP | - | - | - | - | 0.03593% | 18787.09 | 21708.8722 | -2921.7822 | 2019-01-01 | 2019-12-31 | 2019-06-17 | 2021-02-02 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/17/19 ER350 INSTALLED BY CYNTHIA FARIS ON 9/10/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/2/21 GCCC TICKET NOT REQUIRED ON 2/2/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026815500 | INST. FN 134 EXTRA LP OPP | - | - | - | - | 0.03176% | 16605.74 | 21708.8722 | -5103.1322 | 2019-01-01 | 2019-12-31 | 2019-06-17 | 2021-02-25 | INLET AND OUTLET VLVS FULL ON - OUTLET VLVS OFF AND LOCKED JPASLEY REGULATOR INSTALLED BY JAMES PASLEY ON 6/17/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026813700 | INST. FN 21499 EXTRA LP OPP | - | - | - | - | 0.02615% | 13674.88 | 21708.8722 | -8033.9922 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2021-04-28 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/18/2019 GASKET STRAINER NOT REQUIRED SETTING HAS EXISTING T-STRAINER PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026813900 | INST. FN 21500 EXTRA LP OPP | - | - | - | - | 0.02417% | 12637.21 | 21708.8722 | -9071.6622 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2021-04-28 | CHECK TO SEE IF ASV WAS CLOSED, IT WAS OPEN, POSSIBLE CABLE CHANGE SMCHOLAN 10-20-2020 REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/18/2019 GASKET STRAINER NOT REQUIRED SETTING HAS EXISTING T-STRAINER THIS IS PARALLEL RUN ER350 INSTALLED WITH RUN 1 JOB ORDER PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026815900 | INST. FN 136 EXTRA LP OPP | - | - | - | - | 0.03246% | 16973.25 | 21708.8722 | -4735.6222 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2021-02-05 | INLET AND OUTLEY VLV FULL OPEN - BYPASS VLV OFF AND LOCKED JPASLEY 6-18-19 REGULATOR INSTALLED BY JAMES PASLEY ON 6/18/19 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/22/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026813200 | INST. FN 19921 EXTRA LP OPP | - | - | - | - | 0.05545% | 28996.62 | 21708.8722 | 7287.7478 | 2019-01-01 | 2019-12-31 | 2019-06-19 | 2021-05-04 | INLET AND OUTLET VLVS ON - BYPASS VLV OFF AND LOCKED REGULATOR REPLACED BY JAMES PASLEY ON 06/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/4/2021 GCCC TICKET NOT REQUIRED ON 5/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
17026723100 | INSTALL TEMP REG STATION | - | - | - | - | 0.03157% | 16506.37 | 3792.9756 | 12713.3944 | 2019-01-01 | 2019-12-31 | 2019-06-20 | 2019-08-02 | INSTALLED TEMP MOONEY SKID
18026805200 | INST. FN 88 EXTRA LP OPP | - | - | - | - | 0.05158% | 26972.31 | 21708.8722 | 5263.4378 | 2019-01-01 | 2019-12-31 | 2019-06-20 | 2021-01-29 | INLET AND OUTLET VLV FULL OPEN - BYPASS VLV OFF AND LOCKED REGULATOR INSTALLED BY JAMES PASLEY ON 6/20/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/2021 GCCC TICKET NOT REQUIRED ON 1/29/21 PAPERWORK COMPLETED OFF SITE NOT AT REQULATOR STATION
18026806200 | INST. FN 13573 EXTRA LP OPP | - | - | - | - | 0.05993% | 31338.57 | 21708.8722 | 9629.6978 | 2019-01-01 | 2019-12-31 | 2019-06-20 | 2021-05-11 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 06202019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/11/2021 GCCC TICKET NOT RQUIRED ON 5/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026873100 | INSTALL 60' OF 2"CSHP MAIN | - | - | - | - | 0.09758% | 51028 | 21475.2385 | 29552.7615 | 2019-01-01 | 2019-12-31 | 2019-05-28 | 2019-06-25
19026877500 | INSTALL 50' OF 2"PMMP MAIN | - | - | - | - | 0.0195% | 10196 | 17465.4636 | -7269.4636 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2019-06-24
18026773101 | INSTALL 175' - 12" CSHP | - | - | - | - | 1.198% | 626549.16 | 599149.5397 | 27399.6203 | 2019-01-01 | 2019-12-31 | 2019-03-04 | 2019-08-07
18026792402 | INSTALL 19,575' OF 2"/4" PMMP | - | - | - | - | 2.093% | 1094564.81 | 993828.312 | 100736.498 | 2019-01-01 | 2019-12-31 | 2019-08-19 | 2019-12-10
18026807600 | INST. FN 14207 EXTRA LP OPP | - | - | - | - | 0.03795% | 19843.61 | 21708.8722 | -1865.2622 | 2019-01-01 | 2019-12-31 | 2019-06-21 | 2021-05-13 | REGULATOR INSTALLED BY JAMES PASLEY ON 6/21/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026812800 | INST. FN 13476 EXTRA LP OPP | - | - | - | - | 0.04387% | 22943.07 | 21708.8722 | 1234.1978 | 2019-01-01 | 2019-12-31 | 2019-06-21 | 2021-05-12 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/21/2019 ER350 INSTALLED BYWADE SHIMFESSEL ON 8/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026868301 | INSTALL 450' OF 2"PMMP MAIN | - | - | - | - | 0.1064% | 55625.1 | 72806.603 | -17181.503 | 2019-01-01 | 2019-12-31 | 2019-05-31 | 2019-06-27
19026895800 | INSTALL 12" CSHP | - | - | - | - | 0% | 0 | 72.869 | -72.869 | 2019-01-01 | 2019-12-31 | 2019-03-04 | 2019-09-25 | THIS JO WAS CREATED TO ACCOUNT FOR FACILITIES/PROPERTY UNITS INSTALLED AND ABANDONED ON SYSTEM 32010138. ALL FACILITIES FOR THIS JO ARE ON INSTALL JO 18-0267731-01 AND ABN JO 18-0267732-00
18026816100 | INST. FN 14429 EXTRA LP OPP | - | - | - | - | 0.05025% | 26276.03 | 21708.8722 | 4567.1578 | 2019-01-01 | 2019-12-31 | 2019-06-22 | 2021-04-27 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026812400 | INST. FN 14068 EXTRA LP OPP | - | - | - | - | 0.05404% | 28260.36 | 21708.8722 | 6551.4878 | 2019-01-01 | 2019-12-31 | 2019-06-24 | 2021-02-19 | INLET AND OUTLET VLV FULL ON - BYPASS OFF AND LOCKED JPASLEY GCCC# 11659 CMCHOLAN 2-10-2021 CCC# 11659 REGULATOR REPLACED BY JAMES PASLEY ON 6/24/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026835000 | INST. FN 12957 EXTRA LP OPP | - | - | - | - | 0.06439% | 33671.59 | 21579.1646 | 12092.4254 | 2019-01-01 | 2019-12-31 | 2019-06-24 | 2021-03-23 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/24/2019 ER350 INSTALLED BY SHANE GIORDIANO ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026808200 | INST. FN 13665 EXTRA LP OPP | - | - | - | - | 0.05614% | 29358.36 | 21708.8722 | 7649.4878 | 2019-01-01 | 2019-12-31 | 2019-06-25 | 2021-05-04 | REGULATOR INSTALLED BY JAMES PASLEY ON 6/25/2019 ER350 INSTALLED BY CHRIS COX ON 8/13/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/4/2021 GCCC TICKET NOT REQUIRED ON 5/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026830600 | INST. FN 17 EXTRA LP OPP | - | - | - | - | 0.04467% | 23360.67 | 22950.8722 | 409.7978 | 2019-01-01 | 2019-12-31 | 2019-06-25 | 2021-04-12 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 06/25/2019 ER350 INSTALLED BY DANNY ASH ON 06/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/12/2021 GCCC TICKET NOT REQUIRED ON 4/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026847801 | INSTALL 925' OF 2"/4"PMMP MAIN | - | - | - | - | 0.1988% | 103960.01 | 93860.0334 | 10099.9766 | 2019-01-01 | 2019-12-31 | 2019-05-28 | 2019-06-27
18026805600 | INST. FN 13351 EXTRA LP OPP | - | - | - | - | 0.04835% | 25284.87 | 21708.8722 | 3575.9978 | 2019-01-01 | 2019-12-31 | 2019-06-26 | 2021-01-29 | REGULATOR INSTALLED BY JAMES PASLEY ON 06-26-2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8-28-2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1-29-2021 GCCC TICKET NOT REQUIRED ON 1-29-21 PAPERWORK COMPLETED OFF SITE NOT AT REGULATOR STATION
18026831300 | INST. FN 21 EXTRA LP OPP | - | - | - | - | 0.03637% | 19019.14 | 22950.8722 | -3931.7322 | 2019-01-01 | 2019-12-31 | 2019-06-26 | 2021-03-26 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/26/2019 ER350 INSTALLED BY DANNY ASH ON 6/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026794900 | INSTALL 10' - 3" PMLP | - | - | - | - | 0.05744% | 30034.59 | 9712.4728 | 20322.1172 | 2019-01-01 | 2019-12-31 | 2019-05-30 | 2019-09-12 | INSTALLED 27' OF 3" P-MAIN, TEST MAIN ONSITE 90PSI 1HR OK, ST 2 BOLTED COUP AT TIE INS AND 6 SADDLES AT OP OK, BHB CGI NGF, CO OFFSITE, BAGGED OFF MAIN ALLOWED WAIT TIME FOR GAUGES BEFORE AND AFTER, INSTALLED 2- 9LB ANODES ON BOTH SIDES OP PLASTIC, MAIN READ BEFORE SEPERATION -0.592, MAIN READ ON CLAYTON AVE SIDE AFTER SEPERATION -0.601, MAIN READ ON E.JACKSON SIDE AFTER SEPERATION -0.586, CDESPAIN, DWAUGH RLA INSTALLED 27' OF 3" P-MAIN, TEST MAIN ONSITE 90PSI 1HR OK, ST 2 BOLTED COUP AT TIE INS AND 6 SADDLES AT OP OK, BHB CGI NGF, CO OFFSITE, BAGGED OFF MAIN ALLOWED WAIT TIME FOR GAUGES BEFORE AND AFTER, CDESPAIN RLA DWAUGH
18026831700 | INST. FN 23 EXTRA LP OPP | - | - | - | - | 0.05059% | 26452.43 | 22950.8722 | 3501.5578 | 2019-01-01 | 2019-12-31 | 2019-06-27 | 2021-03-24 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/27/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026873600 | INSTALL 24'-4" PMIP | - | - | - | - | 0.04384% | 22926.06 | 15596.7203 | 7329.3397 | 2019-01-01 | 2019-12-31 | 2019-06-26 | 2019-06-28
18026809200 | INST. FN 264 EXTRA LP OPP | - | - | - | - | 0.04433% | 23180.92 | 21708.8722 | 1472.0478 | 2019-01-01 | 2019-12-31 | 2019-06-28 | 2021-02-02 | REGULATOR REPLACED BY JAMES PASLEY ON 6/28/19 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/28/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/2/21 GCCC TICKET NOT REQUIRED ON 2/2/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026829400 | INST. FN 10 EXTRA LP OPP | - | - | - | - | 0.03949% | 20649.88 | 40101.1646 | -19451.2846 | 2019-01-01 | 2019-12-31 | 2019-06-28 | 2021-03-26 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/28/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026829200 | INST. FN 7 EXTRA LP OPP | - | - | - | - | 0.05177% | 27071.64 | 40101.1646 | -13029.5246 | 2019-01-01 | 2019-12-31 | 2019-06-18 | 2021-03-25 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/29/2019 ER250 INSTALLED BY DANNY ASH ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/25/2021 GCCC TICKET NOT REQUIRED ON 3/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026819500 | INST. FN 219 EXTRA LP OPP | - | - | - | - | 0.04696% | 24557.84 | 21708.8722 | 2848.9678 | 2019-01-01 | 2019-12-31 | 2019-07-01 | 2021-02-22 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/22/2021 GCCC TICKET NOT REQUIRED ON 2/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026790300 | INSTALL 350' OF 2"PMMP MAIN | - | - | - | - | 0.0346% | 18094.74 | 14329.8594 | 3764.8806 | 2019-01-01 | 2019-12-31 | 2019-06-28 | 2019-07-03
19026879500 | INSTALL 900' OF 2"PMMP MAIN | - | - | - | - | 0.03944% | 20625.19 | 20687.159 | -61.969 | 2019-01-01 | 2019-12-31 | 2019-06-25 | 2019-07-03
18026816700 | INST. FN 147 EXTRA LP OPP | - | - | - | - | 0.02761% | 14439.85 | 21708.8722 | -7269.0222 | 2019-01-01 | 2019-12-31 | 2019-07-03 | 2021-02-23 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/23/2021 GCCC TICKET NOT REQUIRED ON 2/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS PER CYNTHIA FARIS - STATION HAD EXISTING ERX, BATTERY, SOLAR & RV50 NO NEW FACILITIES CREATED FOR THESE.
18026823600 | INST. FN 182 EXTRA LP OPP | - | - | - | - | 0.03336% | 17445.99 | 43700.1646 | -26254.1746 | 2019-01-01 | 2019-12-31 | 2019-07-01 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/3/2019 ER350 INSTALLED BY WADE SHIMFESEL ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026856200 | INSTALL 630'-2" PMMP | - | - | - | - | 0.1366% | 71454.45 | 44437.9939 | 27016.4561 | 2019-01-01 | 2019-12-31 | 2019-04-15 | 2019-07-10 | INSTALLED 622' OF 2" PLASTIC MAIN BY OC. TESTED AT 90PSIG FOR 1 HOUR
18026830800 | INST. FN 18 EXTRA LP OPP | - | - | - | - | 0.03618% | 18921.27 | 40101.1646 | -21179.8946 | 2019-01-01 | 2019-12-31 | 2019-07-01 | 2021-04-26 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/8/2019 ER350 INSTALLED BY DANNY ASH ON 6/12/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026803200 | INST. FN 13481 EXTRA LP OPP | - | - | - | - | 0.06508% | 34032.31 | 21708.8722 | 12323.4378 | 2019-01-01 | 2019-12-31 | 2019-06-20 | 2021-05-12 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/9/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026832500 | INST. FN 27 EXTRA LP OPP | - | - | - | - | 0.05256% | 27485.25 | 40101.1646 | -12615.9146 | 2019-01-01 | 2019-12-31 | 2019-07-09 | 2021-03-24 | CCC#14002 CC# 14002. REPLACED ER-350. 3/4/21 DSASH 14002CCC REGULATOR REPLACED BY RYAN WILLIAMS ON 7/9/2019 ER350 INSTALLED BY DANNY ASH ON 6/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026868400 | INSTALL 70'-2" CSHP TO R-1222 | - | - | - | - | 0.08352% | 43675.52 | 21448.1103 | 22227.4097 | 2019-01-01 | 2019-12-31 | 2019-06-26 | 2019-07-10
17026742700 | INSTALL 14'-8"CS&PMLP | - | - | - | - | 0.09537% | 49872.05 | 43711.5377 | 6160.5123 | 2019-01-01 | 2019-12-31 | 2019-06-25 | 2019-07-31
18026804300 | INST. FN 83 EXTRA LP OPP | - | - | - | - | 0.07613% | 39809.77 | 21708.8722 | 18100.8978 | 2019-01-01 | 2019-12-31 | 2019-06-20 | 2021-01-29 | REGULATOR INSTALLED BY JAMES PASLEY ON 07-10-2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 08-17-2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 01292021 GCCC TICKET NOT REQUIRED ON 1-29-21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
18026830900 | INST. FN 19 EXTRA LP OPP | - | - | - | - | 0.03099% | 16204.83 | 40101.1646 | -23896.3346 | 2019-01-01 | 2019-12-31 | 2019-07-10 | 2021-03-22 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/10/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/12/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
19026861900 | INSTALL 250' OF 2"/4"PMMP | - | - | - | - | 0.03621% | 18936.14 | 17824.6192 | 1111.5208 | 2019-01-01 | 2019-12-31 | 2019-06-28 | 2019-07-10 | UNABLE TO MAKE COMMIT DATE DUE TO TIMING OF START DATE AND EXTRA BORE ADDED TO JOB .
18026819100 | INST. FN 14426 EXTRA LP OPP | - | - | - | - | 0.05888% | 30788.1 | 21708.8722 | 9079.2278 | 2019-01-01 | 2019-12-31 | 2019-07-11 | 2021-02-04 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/11/19 ER350 INSTALLED 10/30/20 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/4/21 GCCC TICKET NOT REQUIRED ON 2/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026836900 | INST. FN 804 EXTRA LP OPP | - | - | - | - | 0.04199% | 21955.72 | 40101.1646 | -18145.4446 | 2019-01-01 | 2019-12-31 | 2019-08-03 | 2021-03-26 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/11/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/16/2020 PAPERWORK COMPLETD BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026820100 | INST. FN 352 EXTRA LP OPP | - | - | - | - | 0.04238% | 22164.28 | 21708.8722 | 455.4078 | 2019-01-01 | 2019-12-31 | 2019-07-12 | 2021-02-05 | GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON PAPERWORK 2/4/21 CFARIS REGULATOR INSTALLED BY JAMES PASLEY 7/12/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE WORKING ON PAPERWORK CFARIS
18026832100 | INST. FN 25 EXTRA LP OPP | - | - | - | - | 0.03708% | 19387.73 | 40101.1646 | -20713.4346 | 2019-01-01 | 2019-12-31 | 2019-07-12 | 2021-03-24 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/10/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026839300 | INST. FN 19900 EXTRA LP OPP | - | - | - | - | 0.04054% | 21200.07 | 21708.8722 | -508.8022 | 2019-01-01 | 2019-12-31 | 2019-07-15 | 2021-05-05 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/15/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026824800 | INST. FN 233 EXTRA LP OPP | - | - | - | - | 0.03857% | 20170.78 | 21708.8722 | -1538.0922 | 2019-01-01 | 2019-12-31 | 2019-07-17 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/16/2019 ER350 INSTALLED BY CHRIS COX ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026837200 | INST. FN 174 EXTRA LP OPP | - | - | - | - | 0.0329% | 17202.74 | 21708.8722 | -4506.1322 | 2019-01-01 | 2019-12-31 | 2019-07-17 | 2021-05-17 | INSTALLED NEW MONITOR REG, SET POINTS ON SLAM SHUT 4.5" AND 20 " W.C. MONITOR SET POINT 14"W.C, INLET OUTLET, CONTROL LINES VLVS ON BYPASS OFF. 7-17-19 MMCKUNE REGULATOR INSTALLED BY MIKE MCKUNE ON 7/17/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026777900 | INSTALL 20'-6" CSHP-LEAKAGE | - | - | - | - | 0.225% | 117680.81 | 60097.6347 | 57583.1753 | 2019-01-01 | 2019-12-31 | 2019-07-09 | 2019-07-19 | OVERRUN EXPLANATION: THE CONTRACT LABOR WAS WAY UNDERESTIMATED. LEVEL 2 SUBMITTED TO CLOSE OUT
18026837800 | INST. FN 19809 EXTRA LP OPP | - | - | - | - | 0.0521% | 27242.75 | 21708.8722 | 5533.8778 | 2019-01-01 | 2019-12-31 | 2019-07-15 | 2021-05-05 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/18/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026873800 | INSTALL 223'-4' CS/PMIP | - | - | - | - | 0.1415% | 73995.15 | 76834.8811 | -2839.7311 | 2019-01-01 | 2019-12-31 | 2019-07-01 | 2019-07-19
18026826200 | INST. FN 316 EXTRA LP OPP | - | - | - | - | 0.06471% | 33840.66 | 46766.1646 | -12925.5046 | 2019-01-01 | 2019-12-31 | 2019-07-13 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/19/2019 ER350 NOT INSTALLED STATION HAD EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026838000 | INST. FN 179 EXTRA LP OPP | - | - | - | - | 0.06062% | 31699.29 | 21708.8722 | 9990.4178 | 2019-01-01 | 2019-12-31 | 2019-07-16 | 2021-05-05 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026803000 | INST. FN 72 EXTRA LP OPP | - | - | - | - | 0.07458% | 38998.63 | 21708.8722 | 17289.7578 | 2019-01-01 | 2019-12-31 | 2019-07-22 | 2021-02-18 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026802600 | INST. FN 13502 EXTRA LP OPP | - | - | - | - | 0.05016% | 26227.89 | 22950.8722 | 3277.0178 | 2019-01-01 | 2019-12-31 | 2019-07-23 | 2021-02-18 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 07/23/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026814100 | INST. FN 22270 EXTRA LP OPP | - | - | - | - | 0.04657% | 24352.72 | 22950.8722 | 1401.8478 | 2019-01-01 | 2019-12-31 | 2019-07-24 | 2021-02-11 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/11/2021 GCCC TICKET NOT REQUIRED ON 2/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026814300 | INST. FN 22271 EXTRA LP OPP | - | - | - | - | 0.03117% | 16301.08 | 22950.8722 | -6649.7922 | 2019-01-01 | 2019-12-31 | 2019-07-24 | 2021-02-12 | CHECKED SLAM SHUT ON RUN 2 TO SEE IF IT HAD CLOSED, IT WAS NOT CLOSED SO POSSIBLE BAD ASV CABLE SMCHOLAN 10-20-2020 REGULATOR REPLACED BY WADE SHIMFESSEL 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/12/2021 GCCC TICKET NOT REQUIRED ON 2/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS THIS IS PARELLEL SETING SO THERE IS ONLY 1 ER350 THAT WATCHES BOTH RUNS. IT WAS CREATED ON THE RUN 1 JOB . ALSO THERE IS NO GASKET STRAINERS BECAUSE OF EXISTING T-STRAINERS SO THE GASKETS WERE NOT REQUIRED.PER CYNITHIA FARIS
18026824600 | INST. FN 232 EXTRA LP OPP | - | - | - | - | 0.03031% | 15847.81 | 21708.8722 | -5861.0622 | 2019-01-01 | 2019-12-31 | 2019-07-24 | 2021-04-27 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/24/2019 ER350 INSTALLED BY CHRIS COX ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026868001 | INSTALL 1050' OF 2"PMMP MAIN | - | - | - | - | 0.1939% | 101407.9 | 94155.5888 | 7252.3112 | 2019-01-01 | 2019-12-31 | 2019-07-12 | 2019-07-29 | MISSED COMMIT DUE TO OUR START DATE AND CHANGED FROM GRASS STRIP TO STREET BORE .
18026804000 | INST. FN 14154 EXTRA LP OPP | - | - | - | - | 0.04212% | 22027.96 | 22950.8722 | -922.9122 | 2019-01-01 | 2019-12-31 | 2019-07-25 | 2021-05-11 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 7/25/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/11/2021 GCCC TICKET NOT REQUIRED ON 5/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026842000 | INSTALL 725' OF 2"PMMP MAIN | - | - | - | - | 0.1778% | 92959.4 | 154390.9956 | -61431.5956 | 2019-01-01 | 2019-12-31 | 2019-07-22 | 2019-08-07 | UNDERRUN EXPLANATION: THIS WAS ESTIMATED WITH UNITS BUT PERFORMED HOURLY WH ICH IN THIS CASE LOWERED THE COSTS. ALSO, PAVING OF THE STANDARD REQUIRED O F A HIGHWAY WAS ESTIMATED, BUT REPLACED IN A MANNER INDICATIVE OF A PARKING LOT. A LEVEL 2 BUDGET VARIANCE EXPLANTION IS NOT REQUIRED FOR AN UNDERRUN.
18026805800 | INST. FN 13487 EXTRA LP OPP | - | - | - | - | 0.04968% | 25980.27 | 22950.8722 | 3029.3978 | 2019-01-01 | 2019-12-31 | 2019-07-26 | 2021-04-28 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 7/26/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823400 | INST. FN 165 EXTRA LP OPP | - | - | - | - | 0.04768% | 24935.5 | 46766.1646 | -21830.6646 | 2019-01-01 | 2019-12-31 | 2019-07-26 | 2021-04-27 | CCC# 15036 REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/26/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026843700 | INSTALL 8200' OF 2"PMMP MAIN | - | - | - | - | 1.277% | 667631.39 | 645599.7026 | 22031.6874 | 2019-01-01 | 2019-12-31 | 2019-04-08 | 2019-09-17
19026887500 | INSTALL 20'-4" PMLP | - | - | - | - | 0.01582% | 8274.61 | 14674.4724 | -6399.8624 | 2019-01-01 | 2019-12-31 | 2019-07-26 | 2019-07-26
17026728201 | INSTL 3778'-6"&8"PMLP D096801 | - | - | - | - | 2.205% | 1152970.88 | 999130.1284 | 153840.7516 | 2019-01-01 | 2019-12-31 | 2019-07-19 | 2019-11-01 | PROJECT OVERRUN OF $153,000 DUE TO UNDERESTIMATING RESTORATION. ADDITIONAL $300,000 IN CONTRACT COSTS PAID, BUT RESTORATION WAS ESTIMATED UNDER MISC MATERIALS WHICH UNDERRAN $190,000. THERE WAS ALSO A INCREASE IN LABOR AND O VERHEADS $59,000. D.LEMONS 6/30/2020
19026887700 | INSTALL 1' - 2" PMMP AS-BUILT | - | - | - | - | 0.005902% | 3086.49 | 3265.9525 | -179.4625 | 2019-01-01 | 2019-12-31 | 2019-08-01 | 2019-07-27 | CUT OUT AND REPLACED DMAGE TESTED NEW MAIN 100 PSIG 0005 MIN SOAP TESTED FI NAL CONN. OP 31 PSIG MAP CORRECTION WAS MADE AFTER THE CONSTRUCTION COORDINATOR PROVIDED THE EXA CT COORDINATES OF THIS 1" REPLACEMENT.
18026802200 | INST. FN 14459 EXTRA LP OPP | - | - | - | - | 0.07121% | 37240.32 | 21708.8722 | 15531.4478 | 2019-01-01 | 2019-12-31 | 2019-07-29 | 2021-04-28 | REGULATORS INSTALLED BY JAMES PASLEY ON 7/29/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026829000 | INST. FN 5 EXTRA LP OPP | - | - | - | - | 0.04486% | 23457.1 | 40101.1646 | -16644.0646 | 2019-01-01 | 2019-12-31 | 2019-07-29 | 2021-03-24 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 7/29/2019 ER350 INSTALLED BY DANY ASH ON 6/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026885100 | INSTALL 16' OF 2"PMMP MAIN | - | - | - | - | 0.03096% | 16190.44 | 23899.0834 | -7708.6434 | 2019-01-01 | 2019-12-31 | 2019-07-29 | 2019-07-30 | INSTALLED 16' OF NEW 020 PL MAIN TO REPL LEAKING COMP CPLG
18026811800 | INST. FN 373 EXTRA LP OPP | - | - | - | - | 0.03776% | 19746.85 | 21708.8722 | -1962.0222 | 2019-01-01 | 2019-12-31 | 2019-07-30 | 2021-04-28 | GCCC# 13164 CMCHOLAN 2-25-2021 CCC# 13164 REGULATOR INSTALLED BY JAMES PASLEY ON 7/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026832300 | INST. FN 26 EXTRA LP OPP | - | - | - | - | 0.04242% | 22181.12 | 43801.1646 | -21620.0446 | 2019-01-01 | 2019-12-31 | 2019-07-30 | 2021-03-24 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 7/30/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026754500 | INSTALL 1260'-4"&6" PMLP | - | - | - | - | 0.4021% | 210289.46 | 300465.316 | -90175.856 | 2019-01-01 | 2019-12-31 | 2019-05-31 | 2019-07-31 | UNDERRUN EXPLANATION: THE COMPANY DECIDED TO BORE MOST OF THE PROJECT INSTE AD OF OPEN CUT AND THOUGH THE BORE COST WAS MORE AVOIDE A SIGNIFICANT AMOUN T OF EXPENSIVE HARD SURFACE REPAIRS. . A LEVEL 2 VARIANCE EXPLANATION IS NOT REQUIRED FOR AN UNDERRUN.
18026812000 | INST. FN 13501 EXTRA LP OPP | - | - | - | - | 0.03303% | 17270.98 | 22950.8722 | -5679.8922 | 2019-01-01 | 2019-12-31 | 2019-07-31 | 2021-05-12 | GCCC# 13340 CMCHOLAN 2-26-2021 CCC#13340 REGULATOR INSTALLED BY JAMES PASLEY ON 7/31/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026832700 | INST. FN 28 EXTRA LP OPP | - | - | - | - | 0.05312% | 27775.64 | 43801.1646 | -16025.5246 | 2019-01-01 | 2019-12-31 | 2019-07-31 | 2021-03-22 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 7/31/2019 ER350 INSTALLED BY DANNY ASH ON 6/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 3/22/21 CFARIS
19026881000 | INSTALL 28' OF 12"CSHP MAIN | - | - | - | - | 0.1806% | 94423.9 | 54774.4112 | 39649.4888 | 2019-01-01 | 2019-12-31 | 2019-07-18 | 2019-08-07 | TWALKER/KY 08-01-19: TRIED TO REVISE PROJECT DUE TO ADDITIONAL 70' OF MAIN REQUIRED TO REPAIR LEAK BUT WMS WOULD NOT ALLOW ME TO REVISE DUE TO UNPAID INVOICE. REVIEWED PROJECT WILL JSMITH COORDINATOR. JOB COST OVER RUN EXPECTED DUE TO ADDITIONAL FOOTAGE. TWALKER/KY 9-21-2020: COST OVER RUN DUE TO ADDITIONAL 60' OF MAIN LINE REQUIRED, EXISTING MAIN LINE HP MAIN IS COUPLED, PROJECT REQUIRED 4 MAIN CREW AND WELDER, INCREASED CONTRACT COST BY $32,000 AND SEGA INCREASED BY $6000.
19026885300 | INSTALL 340' OF 2"PMLP | - | - | - | - | 0.02879% | 15057.16 | 10016.8061 | 5040.3539 | 2019-01-01 | 2019-12-31 | 2019-07-29 | 2019-08-12
18026831500 | INST. FN 22 EXTRA LP OPP | - | - | - | - | 0.04812% | 25160.98 | 48480.1646 | -23319.1846 | 2019-01-01 | 2019-12-31 | 2019-08-01 | 2021-03-26 | NO ITEMS ENTERED FILLED OUT BY MISTAKE DISREGARD REGULATOR INSTALLED BY CYNTHIA FARIS ON 8/2/2019 ER350 INSTALLED BY DANNY ASH ON 6/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026836700 | INST. FN 254 EXTRA LP OPP | - | - | - | - | 0.03166% | 16555.99 | 35132.1646 | -18576.1746 | 2019-01-01 | 2019-12-31 | 2019-08-03 | 2021-03-31 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 8/3/2019 ER350 INSTALLED BY DANNY ASH ON 6/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026886800 | INSTALL 30' 2" PMMP | - | - | - | - | 0.01802% | 9422.71 | 11471.3026 | -2048.5926 | 2019-01-01 | 2019-12-31 | 2019-08-02 | 2019-08-03
17026722401 | INSTALL 250' - 4" CSHP | - | - | - | - | 0.3248% | 169858.55 | 137260.0836 | 32598.4664 | 2019-01-01 | 2019-12-31 | 2019-07-09 | 2019-08-08 | OVERRUN EXPLANATION: THE ORIGINAL ESTIMATE DID NOT INCLUDE ENVIRONEMENTAL D OLLARS WHICH WAS ABOUT $4,000. IT ALSO DID NOT INCLULDE NON-DESTRUCTIVE TES TING WHICH WAS ABOUT $5000. THE COSTRACT COSTS ALSO EXCEEDED THE ESTIMATE P RIMARILY DUE TO ADDITIONAL OPERATOR HOURS REQUIRED.
17026736101 | INSTALL 12500' OF 2"PMMP MAIN | - | - | - | - | 2.164% | 1131815.22 | 934081.8376 | 197733.3824 | 2019-01-01 | 2019-12-31 | 2019-04-08 | 2019-12-03 | TWALKER/KY 12-23-19: JOB VARIANCE DUE TO ADDITIONAL STREET/ROAD REPAIRS REQUIRED BY LFUCG AT THE END OF PROJECT - ADDED OVER $100,000 IN PAVING CONTRACT COST.
18026830000 | INST. FN 12954 EXTRA LP OPP | - | - | - | - | 0.03415% | 17856.59 | 43677.1646 | -25820.5746 | 2019-01-01 | 2019-12-31 | 2019-08-05 | 2021-02-05 | REGULATOR REPLACED BY RYAN WILLIAMS ON 8/5/19 ER350 INSTALLED BY DANNY ASH ON 6/17/20 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026874700 | INSTALL 700' OF 2"PMMP MAIN | - | - | - | - | 0.06109% | 31948.16 | 30503.159 | 1445.001 | 2019-01-01 | 2019-12-31 | 2019-07-29 | 2019-08-07
18026848501 | INSTALL 7400' OF 2"/4"/6"PMMP | - | - | - | - | 1.097% | 573876.27 | 499644.9702 | 74231.2998 | 2019-01-01 | 2019-12-31 | 2019-04-11 | 2019-08-15 | PAST COMMIT DATE DUE TO WEATHER, ROCK ON JOB, BEING PULLED OFF TO COMPLETE OTHER JOBS
19026883200 | INSTALL 100'-4" PMIP | - | - | - | - | 0.02098% | 10971.63 | 15476.1437 | -4504.5137 | 2019-01-01 | 2019-12-31 | 2019-08-02 | 2019-08-06
19026878600 | INSTALL 320' OF 4"PMLP MAIN | - | - | - | - | 0.0702% | 36710.05 | 41650.159 | -4940.109 | 2019-01-01 | 2019-12-31 | 2019-07-31 | 2019-08-14
18026795700 | INSTALL 1720'-2"&4" PMMP | - | - | - | - | 0.1969% | 102973.29 | 134950.54 | -31977.25 | 2019-01-01 | 2019-12-31 | 2019-07-08 | 2019-09-30 | UNDERRUN EXPLANATION: WE CHANGED CONTRACTORS THAT DECREASED COSTS AND WE DI D NOT UTILIZE MANY OF THE PAVING ITEMS BECAUSE THIS WAS A RELOCATION.
19026890200 | INSTALL 5' - 2" PMMP | - | - | - | - | 0.004429% | 2315.86 | 3857.6547 | -1541.7947 | 2019-01-01 | 2019-12-31 |  | 2019-08-09
19026866200 | INSTALL TWO 2" SS | - | - | - | - | 0.07977% | 41712.88 | 27449.4916 | 14263.3884 | 2019-01-01 | 2019-12-31 | 2019-08-08 | 2019-08-13
19026878200 | INSTALL 55' OF 3"PMLP MAIN | - | - | - | - | 0.008582% | 4487.67 | 22186.5674 | -17698.8974 | 2019-01-01 | 2019-12-31 | 2019-08-12 | 2019-08-12 | ABN 56' OF 040 SL MAIN. INSTALLED NEW 030 PL MAIN ON 8-7-19
19026873300 | INSTALL 4000' OF 2"PMMP MAIN | - | - | - | - | 0.3574% | 186876.14 | 133806.5895 | 53069.5505 | 2019-01-01 | 2019-12-31 | 2019-07-08 | 2019-08-20 | TWALKER/KY 12-23-19: JOB OVER RUN DUE TO ADDITIONAL ROCK AND DIRECTIONAL BORE REQUIRED (ALSO INCREASED SEWER VIDEO) WHICH ADDED $40,000 TO CONTRACT COST. ALSO INCREASE COMPANY LABOR BY $4000 DUE TO LONGER JOB DURATION THAN PLANNED. FINALLY SEGA WAS $9000 HIGHER THAN ESTIMATED. TWALKER/KY 9-21-2020: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS
18026754700 | INSTALL 640'-4"PMLP | - | - | - | - | 0.06631% | 34674.16 | 64602.7097 | -29928.5497 | 2019-01-01 | 2019-12-31 | 2019-07-15 | 2019-08-30 | UNDERRUN EXPLANATION: THE UNDERRUN WAS CAUSED BY NOT HAVING TO PAY AS MUCH PAVING AS WAS ESTIMATED.
18026796401 | INSTALL 11,750' OF 2"/4"PMMP | - | - | - | - | 1.632% | 853373.69 | 814656.4822 | 38717.2078 | 2019-01-01 | 2019-12-31 | 2019-06-25 | 2019-12-13
19026891800 | INSTALL 1' - 3" PMMP | - | - | - | - | 0.04617% | 24141.14 | 24821.333 | -680.193 | 2019-01-01 | 2019-12-31 | 2019-09-12 | 2019-09-12 | INSTALLED 30' OF 3" PLASTIC, TEST ONSITE 90PSI 1HR OK, TEST 5-3X1 TEES 90PSI 1HR OK, ST 2- EF COUPLINGS AND ALL DE CAPS AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN BSEXTON RLA INSTALLED 30' OF 3" PLASTIC, TEST ONSITE 90PSI 1HR OK, TEST 4-3X1 TEES 90PSI 1HR OK, ST 2- EF COUPLINGS AND ALL DE CAPS AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN BSEXTON RLA INSTALLED 30' OF 3" PLASTIC, TEST ONSITE 90PSI 1HR OK, TEST 5-3X1 TEES 90PSI 1HR OK, ST 2- EF COUPLINGS AND ALL DE CAPS AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, DOUBLE SQUEEZE OFF MAIN, 2 WAY FEED, INSTALLED GAUGES ALLOWED 30MIN WAIT TIME AFTER SQUEEZE OFF AND AFTER SQUEEZE OFFS REMOVED, CDESPAIN BSEXTON RLA
19026877700 | INSTALL 154'-2" PM/CSMP | - | - | - | - | 0.07506% | 39253.55 | 49694.9832 | -10441.4332 | 2019-01-01 | 2019-12-31 | 2019-08-14 | 2019-08-26
19026892000 | INSTALL 1' - 2" PMMP | - | - | - | - | 0.01046% | 5470.4 | 5823.0355 | -352.6355 | 2019-01-01 | 2019-12-31 | 2019-09-04 | 2019-08-21
19026893400 | INSTALL 1' - 2" PMMP | - | - | - | - | 0.005504% | 2877.95 | 12063.6947 | -9185.7447 | 2019-01-01 | 2019-12-31 | 2019-08-22 | 2019-08-22
19026891100 | OFFSET 20'-2"P-MP MAIN | - | - | - | - | 0.001062% | 555.23 | 2980.8091 | -2425.5791 | 2019-01-01 | 2019-12-31 | 2019-08-26 | 2019-08-26 | INSTALLED 020 P MP OFFSET. TESTED AT 90# FOR 1 HOUR. SOAP TEST CAPS ON HVTT , NO LEAKS. NO CHANGE IN OPER PRESSURE. MARKER BALLS PLACED ON 90S AND TAPP ING TEES. MAP REVISION COMP. J HOWARD 8-26-19
19026891500 | INSTALL 1' - 2" PMMP | - | - | - | - | 0.01252% | 6549.04 | 6675.3807 | -126.3407 | 2019-01-01 | 2019-12-31 | 2019-08-23 | 2019-08-26
19026892800 | INSTALL 1' 2" PMLP | - | - | - | - | 0.003327% | 1739.79 | 4989.5667 | -3249.7767 | 2019-01-01 | 2019-12-31 | 2019-08-23 | 2019-08-23
18026774100 | INSTALL 25'-4" PMIP | - | - | - | - | 0.09684% | 50642.22 | 48783.4232 | 1858.7968 | 2019-01-01 | 2019-12-31 | 2019-08-19 | 2019-08-28
19026890900 | INSTALL 4" POLY VALVE | - | - | - | - | 0.001214% | 634.89 | 4599.6049 | -3964.7149 | 2019-01-01 | 2019-12-31 | 2019-08-27 | 2019-08-27
18026763500 | R-1238 INSTALL CWT HEATER | - | - | - | - | 2.421% | 1266069.09 | 974892.3519 | 291176.7381 | 2019-01-01 | 2019-12-31 | 2019-04-23 | 2019-08-28 | 12/24/19: VARIANCE EXPLANATION = 1) CONTRACT LABOR WAS NOT ADEQUATELY ACCOUNTED FOR IN THE ORIGNAL ESTIMATE RESULTING IN $130K +/- OVERAGE; 2) RTU EQUIPMENT WAS ORIGINALLY UNDER ESTIMATED RESULTING IN $70K +/- OVERAGE; 3) COMPANY LABOR WAS OVER FIVE TIMES THE ORIGINAL ESTIMATE RESULTING IN $30K OVERAGE; + 4) OVERHEADS ASSOCIATED WITH THESE RESULTED IN AND ADDITIONAL $50K +/- OVERAGE = CAPTURES THE MAJORITY OF THE OVERRUN. . ATTEMPTS TO REVISE THE JOB ORDER DURING CONSTRUCTION WERE UNSUCCESSFUL DUE TO OUTSTANDING CONTRACT AND/OR MATERIAL INVOICES (BKSLONE).
19026860701 | INSTALL INLET/OUTLET PIPING | - | - | - | - | 0.3162% | 165360.2 | 153225.0225 | 12135.1775 | 2019-01-01 | 2019-12-31 | 2019-08-09 | 2019-08-28
19026878500 | INSTALL 1500' OF 4"PHHP MAIN | - | - | - | - | 0.1981% | 103609.21 | 99430.7331 | 4178.4769 | 2019-01-01 | 2019-12-31 |  | 2019-08-29
19026860900 | RELOCATE REG STATION #1684 | - | - | - | - | 0.0464% | 24264.55 | 24955.7243 | -691.1743 | 2019-01-01 | 2019-12-31 | 2019-08-12 | 2019-09-03
19026877200 | INSTALL 4,500' - 6" PMMP | - | - | - | - | 0.5577% | 291652.33 | 317849.8474 | -26197.5174 | 2019-01-01 | 2019-12-31 | 2019-08-01 | 2019-09-18
19026894500 | INSTALL 3' - 3" PMMP | - | - | - | - | 0.02355% | 12316.08 | 8920.8573 | 3395.2227 | 2019-01-01 | 2019-12-31 | 2019-09-03 | 2019-09-04 | ALL WORK AND TIME CHARGED TO JOB 19-6806841-00 WHICH WAS CHARGED TO CAPITOL JOB 19-0268945-00
19026869100 | INSTALL 150' - 4" PMMP | - | - | - | - | 0.1113% | 58200.14 | 30279.2551 | 27920.8849 | 2019-01-01 | 2019-12-31 | 2019-08-24 | 2019-09-06 | ATTEMPTED TO REVISE JO, UNABLE DUE TO UNPAID INVOICES, EXTRA SIDEWALK AND ASPHALT RESTORATION REQUIRED, NON-STANDARD SERVICE LINE FOUND TTOY 9/6/19 MISSED COMMIT DATE DUE HOLIDAY WEEKEND AND RAIN DAY . ALSO HAD TO WORK EXTR A SERVICE LINE REPLACEMENT AT 706 CYPRESS ST
19026889300 | INSTALL 6" SS | - | - | - | - | 0.02581% | 13497.3 | 15110.228 | -1612.928 | 2019-01-01 | 2019-12-31 | 2019-09-03 | 2019-09-06
18026775800 | INSTALL 215'-2" PMIP | - | - | - | - | 0.05259% | 27502.38 | 38240.2156 | -10737.8356 | 2019-01-01 | 2019-12-31 | 8/130/19 | 2019-09-12
19026882701 | INSTALL 90' OF 2"PMMP MAIN | - | - | - | - | 0.03721% | 19457.63 | 22347.5159 | -2889.8859 | 2019-01-01 | 2019-12-31 | 2019-09-05 | 2019-09-10
19026895900 | REPLACE MAIN - LEAKAGE | - | - | - | - | 0.005082% | 2657.76 | 3261.701 | -603.941 | 2019-01-01 | 2019-12-31 |  | 2019-09-11
19026896300 | INSTALL 5'-6" PMLP | - | - | - | - | 0% | 0 | 1441.3238 | -1441.3238 | 2019-01-01 | 2019-12-31 | 2019-09-13 | 2019-09-13
19026870200 | INSTALL 100' OF 2"PMMP MAIN | - | - | - | - | 0.03229% | 16886.43 | 10252.9622 | 6633.4678 | 2019-01-01 | 2019-12-31 | 2019-09-12 | 2019-09-17
15026619300 | INSTALL NEW 2" BYPASS REGS | - | - | - | - | 0.001228% | 642.3 | 1699.7526 | -1057.4526 | 2019-01-01 | 2019-12-31 | 2019-09-17 | 2019-09-17
19026893800 | INSTALL 40' OF 3"PMMP MAIN | - | - | - | - | 0.1108% | 57922.77 | 57421.3808 | 501.3892 | 2019-01-01 | 2019-12-31 | 2019-09-11 | 2019-10-02 | INSTALLED 53' OF 030 PL WITH 3 SS TESTED FOR 15 MINS AND 3 SS TEES, 53' OF PL, 3 90 AND 3 TRANS FITTING ALL TESTED FOR 1 HR, INSTALLED NEW CV AND NEW TEST STATION SEALED ENDS OF ABN ML INT/EXT CORR INSPT COMPLETED 9-13-19 JEN
19026897600 | REPLACE MAIN - DIG IN | - | - | - | - | 0.01027% | 5369.59 | 3086.8087 | 2282.7813 | 2019-01-01 | 2019-12-31 | 2019-09-25 | 2019-10-15 | INSTALLED 2' OF 4" PLASTIC TESTED 100 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 11 IWC
19026896800 | REPLACE MAIN - DIG IN | - | - | - | - | 0.004603% | 2407.06 | 1669.0599 | 738.0001 | 2019-01-01 | 2019-12-31 | 2019-10-15 | 2019-10-15
19026866500 | INSTALL VRG CONTROLLER | - | - | - | - | 0.05153% | 26945.7 | 15490.7518 | 11454.9482 | 2019-01-01 | 2019-12-31 | 2019-06-19 | 2019-09-20 | REPLACED CONTROLLERS AND RELOCATED SUPPLY LINES AND TAPS
18026779200 | R-1133 INSTALL NEW 19X24 FENCE | - | - | - | - | 0.01834% | 9592.7 | 16030.7484 | -6438.0484 | 2019-01-01 | 2019-12-31 | 2019-09-06 | 2019-09-23 | FENCE INSTALLED BY INTERSTATE FENCE COMPANY
18026799501 | INSTALL 4" PV | - | - | - | - | 0.02911% | 15223.31 | 14476.0833 | 747.2267 | 2019-01-01 | 2019-12-31 |  | 2019-09-24
18026799700 | INSTALL 6" PV | - | - | - | - | 0.02342% | 12249.1 | 10736.1251 | 1512.9749 | 2019-01-01 | 2019-12-31 |  | 2019-09-24
17026739600 | INSTALL 295 -4"/8" PHHP+VALVES | - | - | - | - | 0.2678% | 140058.6 | 117387.4666 | 22671.1334 | 2019-01-01 | 2019-12-31 | 2019-08-28 | 2019-10-02
18026754200 | INSTALL RECTIFIER | - | - | - | - | 0.04163% | 21767.18 | 14431.6138 | 7335.5662 | 2019-01-01 | 2019-12-31 | 2019-09-24 | 2019-09-25 | INSTALLED NEW DROP POLE & RECTIFIER 50V/25A (UNIVERSAL) SERIAL #183368 REUSED EXISTING GROUND BED FAC 287748/ REUSED EXISTING STRUCTURE WIRE ALL RELATED TEST STATIONS AND FACILITIES FROM RETIRED REC 287747 WILL BE RELATED TO NEW RECTIFIER MAIN AND GROUND BED NOT EXPOSEED / 09-25-2019 JMM NEW RM4014 INSTALLED WITH FAC #751414
19026882501 | INSTALL 2500' OF 2"PMMP MAIN | - | - | - | - | 0.2925% | 152956.98 | 161456.0751 | -8499.0951 | 2019-01-01 | 2019-12-31 | 2019-09-24 | 2019-09-25
19026885800 | INSTALL 550' OF 2"PMMP MAIN | - | - | - | - | 0.04927% | 25765.69 | 29896.7566 | -4131.0666 | 2019-01-01 | 2019-12-31 | 2019-09-16 | 2019-09-26
19026888000 | INSTALL 40'-2" PMMP | - | - | - | - | 0.08516% | 44534.95 | 31034.6635 | 13500.2865 | 2019-01-01 | 2019-12-31 | 2019-08-03 | 2019-10-01
19026899200 | INSTALL 20'- 2" PMMP | - | - | - | - | 0.0007403% | 387.15 | 8977.3613 | -8590.2113 | 2019-01-01 | 2019-12-31 | 2019-09-25 | 2019-09-25 | 19-7450990-00 REPLACED SL, TEST NEW MAIN TO MTR VLV 90PSI 5MIN OK, ST TEE CAP AT OP OK, 2" ORANGE PLASTIC MAIN, BHB CGI NGF, WORKED WITH MAIN REPLACEMENT JOB, LEAK CLEARED, CDESPAIN 9-25-19
19026863900 | INSTALL 1450'-2" PMMP | - | - | - | - | 0.102% | 53339.99 | 52175.9118 | 1164.0782 | 2019-01-01 | 2019-12-31 | 2019-09-12 | 2019-09-28
19026892500 | INSTALL NEW CHAIN LINK FENCE | - | - | - | - | 0.01745% | 9123.55 | 6787.7217 | 2335.8283 | 2019-01-01 | 2019-12-31 | 2019-09-26 | 2020-04-14 | M&R TECH THAT WAS ON SITE WITH FENCE CREW DID NOT TURN IN INFORMATION AND IS NO LONGER IN THE DEPARTMENT
19026891200 | INSTALL 20'OF 8"PMLP MAIN | - | - | - | - | 0.2188% | 114420.23 | 48701.1043 | 65719.1257 | 2019-01-01 | 2019-12-31 | 2019-09-03 | 2019-10-01 | TWALKER/KY 03-04-20: LEVEL 2 VARIANCE REPORT IN WMS.DOCS FOR COST OVER RUN I COULD NOT REVISE JOB DUE TO UNPAID INVOICE FOR MATERIAL. THIS PROJECT TOOK AN EXTRA WEEK TO COMPLETED WHICH INCREASED COMPANY LABOR BY $4,000. ALSO, THIS PROJECT REQUIRED ADDITIONAL FLAGGERS DUE TO TRAFFIC/LANE CLOSURE PERMITS REQUIREMETNS AND STREET/HARD SURFACE REPAIR WHICH INCREASE CONTRACT COST BY $48,000. FINALLY, CHANGE IN TIE IN PROCESS ADDED $5,000 MATERIAL COST AND SEGA INCREASED BY $6,000
19026900400 | INSTALL 5' - 2" PMMP D096803 | - | - | - | - | 0.02332% | 12194.13 | 8024.1801 | 4169.9499 | 2019-01-01 | 2019-12-31 |  | 2019-10-01
19026896700 | INSTALL 100' OF 2"PMMP MAIN | - | - | - | - | 0.01746% | 9132.58 | 7866.9075 | 1265.6725 | 2019-01-01 | 2019-12-31 | 2019-09-30 | 2019-10-02
17026708901 | INSTALL 4400' OF 2"/4"PMMP | - | - | - | - | 2.227% | 1164501.13 | 820561.0822 | 343940.0478 | 2019-01-01 | 2019-12-31 | 2019-09-17 | 2019-12-23 | LEVEL 2 VARIANCE EXPLANATION IN DOCS
17026733101 | INSTALL 6075' OF 2"/4"PMMP | - | - | - | - | 0.6972% | 364568.47 | 394597.4169 | -30028.9469 | 2019-01-01 | 2019-12-31 | 2019-02-01 | 2019-12-18
19026886500 | INSTALL 1736'-2"PMIP | - | - | - | - | 0.2209% | 115502.44 | 80811.325 | 34691.115 | 2019-01-01 | 2019-12-31 | 2019-09-16 | 2019-11-08 | OVERRUN EXPLANATION: JOB REQUIRED 65 TONS MORE OF SAND AND STONE THAN ESTIM ATED. ALSO, $4100 OF ADDITIONAL PAVING WAS REQUIRED, AND IT TOOK 200 MORE H OURS THAN THE LABOR ESTIMATING TOOL PREDICTED. THESE ITEMS PLUSS THE OVERHE AD EFFECT OF THESE COSTS RESULTING IN THE TOTAL OVERRUN.
19026897200 | INSTALL 2" SS FITTING | - | - | - | - | 0.009324% | 4876.06 | 6488.17 | -1612.11 | 2019-01-01 | 2019-12-31 | 2019-10-03 | 2019-10-03
19026898700 | INSERT 221' OF 4"PMLP MAIN | - | - | - | - | 0.1021% | 53400.95 | 45101.8024 | 8299.1476 | 2019-01-01 | 2019-12-31 | 2019-09-30 | 2019-10-08
18026800402 | INSTALL 9000' OF 2"PMMP MAIN | - | - | - | - | 1.15% | 601602 | 597234.6599 | 4367.3401 | 2019-01-01 | 2019-12-31 | 2019-03-05 | 2019-10-08
19026880501 | INSTALL 590' OF 4"/8"PMLP MAIN | - | - | - | - | 0.1449% | 75795.04 | 89456.2428 | -13661.2028 | 2019-01-01 | 2019-12-31 | 2019-09-03 | 2020-06-09 | JOB COMPLETED TO COMPAMY STANDARDS.
18026749200 | INSTALL 1170'-4"/2" PMMP | - | - | - | - | 0.3543% | 185275.59 | 206432.4814 | -21156.8914 | 2019-01-01 | 2019-12-31 | 2019-09-16 | 2019-11-07
18026849700 | INSTALL 825' OF 2"PMMP MAIN | - | - | - | - | 0.08393% | 43887.53 | 24468.6987 | 19418.8313 | 2019-01-01 | 2019-12-31 | 2019-06-27 | 2019-10-14
19026862600 | INSTALL 2400'-2" PMMP | - | - | - | - | 0.7876% | 411838.03 | 436945.7962 | -25107.7662 | 2019-01-01 | 2019-12-31 | 2019-07-11 | 2019-12-20 | UNDERRUN EXPLANATION: PROJECT UNDERRAN BECAUSE THE 10000 UNITS OF PAVING AN D 500 UNITS OF ROCK EXCAVATION WERE NOT REQUIRED.
19026877000 | INSTALL 623' OF 4"CSHP MAIN | - | - | - | - | 0.2193% | 114659.91 | 125819.9196 | -11160.0096 | 2019-01-01 | 2019-12-31 | 2019-09-18 | 2019-11-02
19026903800 | INSTALL 5'-2" P-IP | - | - | - | - | 0.003833% | 2004.22 | 1653.0599 | 351.1601 | 2019-01-01 | 2019-12-31 | 2019-10-16 | 2019-10-17
18026848300 | INSTALL 100' OF 2"PMMP MAIN | - | - | - | - | 0.0251% | 13128.1 | 15477.1344 | -2349.0344 | 2019-01-01 | 2019-12-31 | 2019-10-10 | 2019-10-16
18026797401 | INSTALL 13225' OF 2"PMMP MAIN | - | - | - | - | 2.867% | 1499060.49 | 1622403.4384 | -123342.9484 | 2019-01-01 | 2019-12-31 | 2020-01-21 | 2020-07-15
17026732801 | INSTALL 6450' OF 4"/6"/8" PMLP | - | - | - | - | 3.217% | 1682192.54 | 1270165.8463 | 412026.6937 | 2019-01-01 | 2019-12-31 | 2019-08-27 | 2019-12-18 | THE HOURLY ON INVOICE # 122237 WAS FOR TIE IN'S ON CLAYS MILL WORKED RELIGHTS FROM OUTAGE ON STRATFORD DR. PER GHATTON. 10/29/19 ZMARTIN LEVEL 2 EXPLANATION IN DOCS.
18026780700 | INSTALL NEW REG STA R-1222 | - | - | - | - | 0.0649% | 33940.47 | 56249.1748 | -22308.7048 | 2019-01-01 | 2019-12-31 | 2019-07-08 | 2019-10-18
19026904500 | INSTALL 8' OF 3"PMMP MAIN | - | - | - | - | 0.0002909% | 152.13 | 9724.607 | -9572.477 | 2019-01-01 | 2019-12-31 | 2019-10-28 | 2019-10-28 | INSTALLED 5 FT OF 3 IN MAIN TEST 90 LB FOR 20 MIN TEST OK TESTED ALL TEES 90 LB FOR 5 MIN SOAP TESTED ALL TIE INS AND END CAPS ON TEES AT OP FOR 5MIN BAR HOLE BANKS NO GAS FOUND
18026842500 | INSTALL 1615'-12"/8" CSHP | - | - | - | - | 1.627% | 850897.48 | 778679.7562 | 72217.7238 | 2019-01-01 | 2019-12-31 | 2019-03-29 | 2019-10-29
18026846900 | INSTALL 200'-2" PMIP | - | - | - | - | 0.09022% | 47178.86 | 14331.1641 | 32847.6959 | 2019-01-01 | 2019-12-31 | 2019-07-03 | 2019-10-21 | OVERRUN EXPLANATION: JOB WAS ESTIMATED FOR 40 HRS, BUT TOOK 110 HRS. APPROX IMATELY 75 FEET OF ADDITIONAL MAIN WAS INSTALLED. COST OVERRUN MAINLY CONTR IBUTED TO ADDITIONAL 30 HRS OF 3 MAN CREW, 198 UNITS OF EXTRA DEPTH AND ERR OSION CONTROL DEVICES NOT ORIGINALLY ESTIMATED (APPROXIMATELY $22,000). THE ADDITIONAL LABOR HOURS, OTHER COST AND SEGA ACOUNT FOR APPROXIMATELY $8,000 MORE IN OVERALL COST. D.LEMONS 3/4/2020
19026894900 | INSTALL 100' 2" PMMP | - | - | - | - | 0.02898% | 15155.82 | 13228.3613 | 1927.4587 | 2019-01-01 | 2019-12-31 | 2019-10-14 | 2019-10-22
19026904700 | DIG IN - INSTALL 5'-4" PMLP | - | - | - | - | 0% | 0 | 5076.4924 | -5076.4924 | 2019-01-01 | 2019-12-31 | 2019-10-22 | 2019-10-22
17026728801 | INSTALL 1200' - 4" PMMP | - | - | - | - | 1.921% | 1004690.34 | 856768.8391 | 147921.5009 | 2019-01-01 | 2019-12-31 | 2019-08-13 | 2019-11-08 | TTOY - 3/5/20 JOB OVERUN DUE TO ~$30,000 IN ADDITIONAL SEGA COSTS, MATERIAL ORDERED MULTIPLE TIMES AT AN ADDITIONAL COST OF $11,475, EXTRA AFUDC COSTS OF $9,307, ADDITIONAL CONTRACT COSTS OF MISC DOLLARS FOR ~$40,000, AND ADDITIONAL LABOR ADDING UP TO $7,616.
19026871300 | INSTAL 100'-2" PMMP | - | - | - | - | 0.03965% | 20735.1 | 10670.6344 | 10064.4656 | 2019-01-01 | 2019-12-31 | 2019-10-22 | 2019-10-25
18026793101 | INSTALL 2990' OF 2"/4" PMMP | - | - | - | - | 2.041% | 1067558.09 | 1176455.3136 | -108897.2236 | 2019-01-01 | 2019-12-31 | 2019-10-12 | 2020-06-11 | 3-12-20 98-140 (16) CUT WINDOWS FOR SL'S TO 286/256 CLAY AV 3-13-20 98-140 (12) 98-300 (5.5) FINISH CUTTING WINDOWS ON CLAY AV JOB COMPLETE. TWALKER/KY 06-30-20: JOB CURRENTLY UNDER RUN DUE TO PAVING COST HAVE NOT BEEN APPLIED TO 557 JOB#
18026764401 | INSTALL 2000'-10" PMMP | - | - | - | - | 1.99% | 1040888.94 | 1012979.8273 | 27909.1127 | 2019-01-01 | 2019-12-31 | 2019-08-19 | 2019-12-04
19026872200 | INSTALL 225' 2" PMMP | - | - | - | - | 0.1272% | 66538.37 | 65634.421 | 903.949 | 2019-01-01 | 2019-12-31 | 2019-10-01 | 2019-10-29
19026886000 | INSTALL 440' OF 4"PMMP MAIN | - | - | - | - | 0.07687% | 40198.78 | 47785.9525 | -7587.1725 | 2019-01-01 | 2019-12-31 | 2019-10-22 | 2019-11-05 | INSTALL 427' OF MAIN EXTENSION
19026906100 | INSTALL 10' OF 3"PMIP MAIN | - | - | - | - | 0.02102% | 10991.02 | 15368.93 | -4377.91 | 2019-01-01 | 2019-12-31 | 2019-10-31 | 2019-10-31 | CUT OUT OLD MAIN PLACED WITH NEW PEICE OF MAIN TESTED 90 LB FOR FOR 20 MIN SOAP TEST FINAL TIE IN AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
19026886100 | INSTALL 10' 4" PMLP | - | - | - | - | 0.04887% | 25555.38 | 38744.9642 | -13189.5842 | 2019-01-01 | 2019-12-31 | 2019-10-28 | 2019-10-30
19026906400 | INSTALL 6' - 4" PMIP | - | - | - | - | 0.009827% | 5138.67 | 8611.5734 | -3472.9034 | 2019-01-01 | 2019-12-31 | 2019-11-14 | 2019-11-14 | TEST PIPE 90 LB FOR 20 MIN OK TEST ALL TEES 90 LB FOR 5 MIN OK SOAP TEST EFC 5 MIN AT OP SOAP TEST ALL END CAPS ON TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
19026874401 | INSTALL 2520' OF 2"PMMP MAIN | - | - | - | - | 0.9187% | 480392.26 | 460145.7795 | 20246.4805 | 2019-01-01 | 2019-12-31 | 2019-09-19 | 2019-12-16
19026880700 | INSTALL DUAL RUN REG STATION | - | - | - | - | 0.05549% | 29017.59 | 48448.5827 | -19430.9927 | 2019-01-01 | 2019-12-31 | 2019-09-09 | 2020-11-04 | WAITING ON MATERIAL FOR ERX AND PRV IN ORDER TO COMPLETE ALL COMPONENT INSTALLS ALSO WAITING ON CONSTRUCTION TO COMPLETE MAIN LINE JOBS AND SERVICE TIE-OVERS DELAYED DUE TO COVID 19
19026904400 | INSTALL 40'-2" PMMP | - | - | - | - | 0.004397% | 2299.29 | 8368.9054 | -6069.6154 | 2019-01-01 | 2019-12-31 | 2019-11-06 | 2019-11-07 | INSTALLED 40' OF 2" PMMP MAIN. TESTED MAIN 0090 PSIG FOR 1HR WITH AIR USING KUHLMAN GAUGE. TIME OF TEST 2:50PM-3:50PM 11-06-2019 CWHEELE 11-07-2019
18026776901 | INSTALL 15,400 OF 2"/4"/6"PMMP | - | - | - | - | 5.872% | 3070837.26 | 2640238.4188 | 430598.8412 | 2019-01-01 | 2019-12-31 | 2019-07-30 | 2019-11-20 | TWALKER/KY 06-05-2020: JOB OVER RUN DUE TO CITY OF FRANKFORT PAVING REQUIRE MENTS WHICH ADDED $300,000 COST.
18026789202 | INSTALL 350' OF 2"PMMP MAIN | - | - | - | - | 0.04637% | 24248.55 | 22611.6744 | 1636.8756 | 2019-01-01 | 2019-12-31 | 2019-10-30 | 2019-11-11
19026902300 | INSTALL 200'-4" PMMP | - | - | - | - | 0.2131% | 111439.24 | 75295.2308 | 36144.0092 | 2019-01-01 | 2019-12-31 | 2019-10-22 | 2019-11-14 | KEVIN KOUNS COMPLETED PAPERWORK CONTRACT LABOR WAS $31,000 MORE THAN ESTIMATED, WHICH ALSO INCREASED SEGA B Y $9,000. THERE WAS A REDUCTION IN OTHER COSTS OF $6,000. D.LEMONS 6/16/202 0
19026907600 | INSTALL 10'-3" PMLP EMERGENCY | - | - | - | - | 0.04198% | 21952.97 | 8524.8696 | 13428.1004 | 2019-01-01 | 2019-12-31 | 2019-11-14 | 2019-11-14
18026796000 | INSTALL 2450' OF 4"PMLP MAIN | - | - | - | - | 1.49% | 779231.58 | 651866.7814 | 127364.7986 | 2019-01-01 | 2019-12-31 | 2019-07-09 | 2019-11-22 | TWALKER/KY 06-30-2020: JOB OVER RUN DUE TO CITY OF LEXINGTON REQUIRED ADDIT IONAL MILL/PAVE FOR STREET CUTS WHICH INCREASED COST BY $100,000 AND SEGA INCREASED BY $19,000 VS ESTIMATED.
19026908900 | INSTALL 3'-4" PMLP | - | - | - | - | 0.01118% | 5847.26 | 6559.5374 | -712.2774 | 2019-01-01 | 2019-12-31 | 2019-11-13 | 2019-11-13
19026875100 | INSTALL 550' OF 2"PMMP MAIN | - | - | - | - | 0.2237% | 117001.48 | 91886.5131 | 25114.9669 | 2019-01-01 | 2019-12-31 | 2019-11-08 | 2019-12-02 | INSTALLED 540' OF 2" PE MAIN ALONG RICHMOND RD BETWEEN DESHA RD AND IRVINE RD. TESTED MAIN @ 95 PSIG FOR 1 HOUR.SOAP TESTED TIE INS AND DEAD END CAPS AT OPERATING PRESSURE FOR 5 MINS.
19026909500 | INSTALL 5'-4" PMIP | - | - | - | - | 0.001508% | 788.33 | 5292.3952 | -4504.0652 | 2019-01-01 | 2019-12-31 | 2019-11-18 | 2019-11-18 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG 0015 MIN
19026858401 | INSTALL 1020'-2" PMMP | - | - | - | - | 0.2318% | 121199.77 | 120785.7301 | 414.0399 | 2019-01-01 | 2019-12-31 | 2019-10-09 | 2019-11-22
19026881200 | INSTALL 5'-4" PMLP | - | - | - | - | 0.05909% | 30902.5 | 21041.8141 | 9860.6859 | 2019-01-01 | 2019-12-31 | 2019-11-19 | 2019-11-21
19026876700 | INSTALL 3117'-2"PMMP | - | - | - | - | 1.297% | 678268.01 | 359131.1637 | 319136.8463 | 2019-01-01 | 2019-12-31 | 2019-08-28 | 2019-12-17 | OVERRUN EXPLANATION: IT APPEARS THAT $279,268 IN SERVICE LINE MATERIALS WAS CHARGED TO THIS JOB ORDER INSTEAD OF THE BLANKET SERVICE LINE BUDGET. WE NE ED TO VERIFY.
19026905700 | INSTALL ERX | - | - | - | - | 0.001732% | 905.65 | 4096.5878 | -3190.9378 | 2019-01-01 | 2019-12-31 | 2019-11-21 | 2019-11-21 | REPLACED EFC
18026747300 | INSTALL 33' - 4" CSHP | - | - | - | - | 0.05009% | 26193.3 | 35486.9695 | -9293.6695 | 2019-01-01 | 2019-12-31 | 2019-11-22 | 2019-12-04
19026866100 | INSTALL 450' OF 2"PMMP | - | - | - | - | 0.1092% | 57080.5 | 35637.9457 | 21442.5543 | 2019-01-01 | 2019-12-31 | 2019-11-04 | 2019-11-22
19026868801 | INSTALL 393'-4" CS/PMMP | - | - | - | - | 0.1882% | 98423.03 | 88186.6195 | 10236.4105 | 2019-01-01 | 2019-12-31 | 2019-11-04 | 2019-12-05
19026899500 | INSTALL 385' OF 2"PMMP MAIN | - | - | - | - | 0.05456% | 28529.4 | 27253.815 | 1275.585 | 2019-01-01 | 2019-12-31 | 2019-11-27 | 2019-12-04
19026899400 | INSTALL 350' OF 2"PMMP MAIN | - | - | - | - | 0.108% | 56465.73 | 21423.1564 | 35042.5736 | 2019-01-01 | 2019-12-31 | 2019-11-19 | 2019-12-06 | COMPLETED PAST COMMIT DATE DUE TO WEATHER,EXTRA VACUUM EXCAVATING DUE TO MISS MARKED UTILITY LOCATES, AND WAITING ON DEMO MACHINE TO MAKE ROCK BORE. TWALKER/KY 6-5-2020: PROJECT PLANNED FOR DIRECT BORE BUT CREWS HIT ROCK AND SPOTTING OTHER UTILITIES ADDED $28,000 IN CONTRACT COST, CO LABOR INCREASED BY $3000 AND SEGA WAS $5000 HIGHER THAN ESTIMATE.
18026747501 | INSTALL 1140'-4" PMLP | - | - | - | - | 0.3683% | 192579.3 | 212341.9469 | -19762.6469 | 2019-01-01 | 2019-12-31 | 2019-11-08 | 2019-12-07
19026861800 | INSTALL HEATER | - | - | - | - | 0.008893% | 4650.58 | 4140.0298 | 510.5502 | 2019-01-01 | 2019-12-31 | 2019-12-06 | 2019-12-06 | CAT HEATER INSTALL
19026887200 | REPLACE DAMAGED BUILDING | - | - | - | - | 0.1221% | 63861.4 | 65318.7178 | -1457.3178 | 2019-01-01 | 2019-12-31 | 2019-11-25 | 2019-12-10
19026901300 | INSTALL 5'-6" PMMP | - | - | - | - | 0.04134% | 21620.33 | 16908.4616 | 4711.8684 | 2019-01-01 | 2019-12-31 | 2019-10-08 | 2019-12-10
18026841700 | INSTALL 950' OF 2"PMMP MAIN | - | - | - | - | 0.3336% | 174447.7 | 190505.477 | -16057.777 | 2019-01-01 | 2019-12-31 | 2019-10-15 | 2020-06-03 | PORTABLE TOILET 4/28 THRU 5/17 - $78.35 TOP SOIL - 3 CY - $90.00 - #120169 - 6/3/20 TWALKER/KY 06-30-2020: JOB UNDER RUN DUE TO CKY PAID PROPERTY OWNER TO REPA IR PARKING LOT (THEY WERE IN THE PROCESS OF REPAVING THE FRONT SECTION OF THE SHOPPING CENTER). THIS LOWERED OUR PAVING COST/CONTRACTOR COST BY $30,000.
18026791701 | INSTALL 5400' OF 2"/4"PMMP | - | - | - | - | 0.3427% | 179187.44 | 204633.9866 | -25446.5466 | 2019-01-01 | 2019-12-31 | 2019-10-18 | 2019-12-20 | TWALKER/KY 06-05-2020: JOB COST UNDER RUN DUE TO LESS HARD SURFACE REPAIRS REQUIRED WHICH LOWERED CONTRACT COST BY $30000
20026917300 | INSTALL 5' - 2" PMMP | - | - | - | - | 0.000224% | 117.13 | 1409.1077 | -1291.9777 | 2019-01-01 | 2019-12-31 | 2019-12-19 | 2019-12-19
18026763000 | INSTALL 1600' OF 8"CSHP MAIN | - | - | - | - | 1.327% | 693909.46 | 605139.9338 | 88769.5262 | 2019-01-01 | 2019-12-31 | 2019-03-25 | 2020-01-07 | IN SERVICE ON 12/23/2019 BUT ABANDONMENT TOO PLACE ON 01/06/2020. FLL'S AND ENGINEERING ADVISED
18026780900 | R-1222 INSTALL NEW 20X20 FENCE | - | - | - | - | 0.03541% | 18519.29 | 16537.9613 | 1981.3287 | 2019-01-01 | 2019-12-31 | 2019-11-19 | 2019-12-23 | SIGNS UP REG STATION LOCKED AND SECURED APARKS 12-20-19
19026907400 | REPLACE EFC WITH EC350 | - | - | - | - | 0.009012% | 4712.62 | 3366.2939 | 1346.3261 | 2019-01-01 | 2019-12-31 | 2019-12-23 | 2019-12-23
19026912700 | INSTALL FENCE & BOLLARDS | - | - | - | - | 0.01646% | 8608.62 | 8318.1356 | 290.4844 | 2019-01-01 | 2019-12-31 | 2019-12-27 | 2019-12-27 | SIGNS UP APARKS 01-09-20
19026903500 | INSTALL ELECTRONIC EQUIP | - | - | - | - | 0.01083% | 5663.17 | 6741.6923 | -1078.5223 | 2019-01-01 | 2019-12-31 |  | 2020-04-14 | EQUIPMENT REPLACED BY NOLL DAVIS AND ACP
19026915100 | BUY PERMANENT NS RR RIGHTS | - | - | - | - | 0.04955% | 25911.05 | 25861 | 50.05 | 2019-01-01 | 2019-12-31 | 2019-12-20 | 2019-12-31
20026916400 | INSTALL 5' OF 4"PMLP MAIN | - | - | - | - | 0.009495% | 4965.37 | 9665.1077 | -4699.7377 | 2019-01-01 | 2019-12-31 | 2019-12-31 | 2019-12-31 | TWALKER/KY 1-30-20: THIS NOTE TO DOCUMENT APPROVAL FROM FOL BYRAN MORAN AND MYSELF ON THE 20 MINUTE TEST TIME FOR THIS SECTION OF REPLACEMENT MAIN FOR THIS EMERGENCY LEAK REPAIR PROJECT.
20026948200 | LAND AGREEMENT LR114666 | - | - | - | - | 0% | 0 | 0 | 0 | 2019-01-01 | 2019-12-31 |  | 2019-12-31
20026948400 | LAND AGREEMENT LR115003 | - | - | - | - | 3.758e-05% | 19.65 | 0 | 19.65 | 2019-01-01 | 2019-12-31 |  | 2019-12-31
20026948500 | LAND AGREEMENT LR114662 | - | - | - | - | 0% | 0 | 0 | 0 | 2019-01-01 | 2019-12-31 |  | 2019-12-31
|  | - | - | - | - |  | 2019 Construction Project Budget | 52293000
20026917700 | INSTALL 5'-2" PMMP | - | - | - | - | 0.004884% | 3055.88 | 3370.5385 | -314.6585 | 2020-01-01 | 2020-12-31 | 2020-01-08 | 2020-01-08 | INSTALLED 5 FT PEICE OF MAIN TEST 90 LB FOR 1 HR TEST OK SOAP TEST FINALL COUPLINGS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
20026918500 | INSTALL 6'-2"PMMP | - | - | - | - | 0.007741% | 4843.5 | 5610.7846 | -767.2846 | 2020-01-01 | 2020-12-31 | 2020-01-14 | 2020-01-14 | REPLACED 6 FT OF MAIN TEST 90 LB FFOR 1 HR TEST ALL TEES 90 LB FOR 5 MIN SOAP TEST FINAL EFC AT OP FOR 5 MIN 13 LB BAR HOLE BANKS NO GAS FOUND
19026865000 | INSTALL 253'-4" PMMP | - | - | - | - | 0.08499% | 53177.8 | 35049.1103 | 18128.6897 | 2020-01-01 | 2020-12-31 | 2019-02-06 | 2020-01-10
19026906700 | INSTALL RECTIFIER, POLE | - | - | - | - | 0.004554% | 2849.17 | 9754.8443 | -6905.6743 | 2020-01-01 | 2020-12-31 | 2020-02-06 | 2020-01-08
19026893200 | INSTALL 40' - 4" PMMP | - | - | - | - | 0.01145% | 7165.25 | 32848.7614 | -25683.5114 | 2020-01-01 | 2020-12-31 | 2020-02-18 | 2020-02-18 | INSTALLED 15' OF 4" AND 16' OF 2" TO FIX LEAK ON MAIN. ALL MAIN WAS GPS'ED DUE TO NO WIRE TO TIE ON TO. SWING TIES TAKEN TO ALL FITTINGS FROM 2001 FORT HARROD AND THE LIGHT POLE
19026896200 | INSTALL 570' OF 2"PMMP MAIN | - | - | - | - | 0.1059% | 66254.84 | 26113.7225 | 40141.1175 | 2020-01-01 | 2020-12-31 | 2019-02-06 | 2020-01-10 | OVERRUN EXPLANATION: THIS JOB NEEDED 334 EXTRA UNITS OF HEAVY ROCK BORE INS TEAD OF THE DIRECTIONAL BORE ESTIMATED.
20026919200 | INSTALL 5'-4"PMLP | - | - | - | - | 0.000406% | 254.03 | 5187.7846 | -4933.7546 | 2020-01-01 | 2020-12-31 |  | 2020-01-26 | INSTALLED 5'1" OF NEW 040 PL ML TO REPL LEAKING SF CPLG OFF SRV TEE TESTED @ 90 FOR 1 HR ON SITE. PURGE TEE TESTED @ 90 FOR 5 MINS ON SITE. CONN PTS TESTED @ 9.5" WC MB INSTTALLED OVER TEE 1-13-20 JENS
19026901500 | INSTALL CHAIN LINK FENCE | - | - | - | - | 0.01865% | 11671.37 | 9450.3856 | 2220.9844 | 2020-01-01 | 2020-12-31 | 2019-12-26 | 2020-01-14 | SIGNS UP APARKS
19026904900 | INSTALL NEW CHAIN LINK FENCE | - | - | - | - | 0.01526% | 9545.78 | 7539.783 | 2005.997 | 2020-01-01 | 2020-12-31 | 2019-11-18 | 2020-01-14 | SIGNS UP /// REG STATION SECURED APARKS 12-20-19
19026912600 | INSTALL 150' OF 2"PMMP | - | - | - | - | 0.02305% | 14418.82 | 12601.0923 | 1817.7277 | 2020-01-01 | 2020-12-31 | 2020-01-10 | 2020-01-16
16026676800 | INSTALL 350'-4" PMMP | - | - | - | - | 0.01583% | 9902.28 | 21485.8363 | -11583.5563 | 2020-01-01 | 2020-12-31 | 2020-01-20 | 2020-01-23 | INSTALLED 271' OF 4" PL-PRESS TEST 90LBS 1HR TEST OK-SOAP TEST FINAL TIE IN @OP TEST OK-50PSI VERIFIED-PERFORMED SQUEEZEING&GAUGEING&PURGING TO GAS STA NDARDS SOAP TESTED 4 TEE CAPS AND DE CAPS @ OP TEST OK-ANICHOLS 1-22-20
18026744800 | INSTALL 35'-6" CSHP | - | - | - | - | 0.2384% | 149186.46 | 61047.2348 | 88139.2252 | 2020-01-01 | 2020-12-31 | 2019-12-09 | 2020-01-27 | LEVEL 2 VARIANCE EXPLANATION FILLED OUT AND SENT FOR APPROVAL. D.LEMONS 6/1 6/2020
18026763200 | INSTALL 6500' - 2"/4" PMMP | - | - | - | - | 0.7149% | 447309.97 | 367443.8945 | 79866.0755 | 2020-01-01 | 2020-12-31 | 2019-10-01 | 2020-01-27 | TTOY 6/8/2020 OVERRUN EXPLANATION: CONTRACT CHANGE MID PROJECT, INCREASED UNIT PRICES, ADDITIONAL LABOR ACCOUNTED FOR ~$25,000, AFUDC ACCOUNTED FOR EXTRA $2,500, SEGA INCREASED BY $8,000, ADDITIONAL ROCK EXCAVATION AND HEAVY ROCK BORE REQUIRED
18026783500 | INSTALL 1500' - 4" PMMP | - | - | - | - | 0.1483% | 92809.31 | 54214.2804 | 38595.0296 | 2020-01-01 | 2020-12-31 | 2020-01-06 | 2020-02-04 | TTOY 6/8/2020 OVERRUN EXPLANATION: CONTRACT UPDATE CAUSING INCREASED UNIT COSTS, UNANTICIPATED ROCK EXCAVATION, ADDITIONAL ROCK CAUSING LONGER DURATION AND INCREASED HOURS, SEGA INCREASED $3,000, ADDTIONAL LABOR ADDING UP TO $10,000
19026876100 | INSTALL 2760' OF 2"/4"PMMP | - | - | - | - | 0.1097% | 68619.9 | 70211.5565 | -1591.6565 | 2020-01-01 | 2020-12-31 | 2020-01-17 | 2020-02-20 | TWALKER/KY 2-13-20: SEE JOB ORDER CHANGE REQUEST IN WMS.DOCS, ONE OF THE PL ANNED STREETS FOR THIS DEVELOPMENT NOT INSTALLED AND PROJECT FOOTAGE IS 800' LESS THAN PLANNED. WMS WOULD NOT ALLOW REVISION DUE TO UNPAID INVOICES FOR MATERIAL
18026849200 | INSTALL MI WIRELESS EFC | - | - | - | - | 0.02085% | 13047.12 | 10338.964 | 2708.156 | 2020-01-01 | 2020-12-31 | 2019-01-10 | 2020-02-14 | WAITING ON EQUIPMENT EFC BACKORDERED
14026531302 | INSTALL 20'-6" CSHP | - | - | - | - | 0.1197% | 74916.27 | 40462.1821 | 34454.0879 | 2020-01-01 | 2020-12-31 | 2020-01-30 | 2020-02-18 | PROJECT OVERRUN OF $34,000 DUE TO SEVERAL MOVEIN/MOVE-OUTS AND REVISIONS TO THE PROJECT. PROJECT WAS PAID HOURLY AND HOURLY CONTRACT UNITS WERE UNDER ESTIMATED BY $23,000, LABOR WAS UNDERESTIMATED BY 100 HOURS WHICH INCREASED COST BY $5,000. THERE WAS ALSO INCREASE IN SEGA AND OVERHEADS OF $4,000. D.LEMONS 6/30/2020
19026874100 | INSTALL 2800' OF 2"/4"PMMP | - | - | - | - | 0.1707% | 106780.18 | 93000.1288 | 13780.0512 | 2020-01-01 | 2020-12-31 | 2020-01-13 | 2020-02-17
19026885901 | INSTALL 400' OF 2"PMMP MAIN | - | - | - | - | 0.05823% | 36432.55 | 43080.7988 | -6648.2488 | 2020-01-01 | 2020-12-31 | 2020-02-04 | 2020-02-18
20026924800 | REPLACE 40'-2"PMMP | - | - | - | - | 0.004053% | 2535.57 | 1911.1195 | 624.4505 | 2020-01-01 | 2020-12-31 | 2020-02-17 | 2020-02-17 | INSTALLED 37' OF 2'' PLASTIC PIPE IN OPEN TRENCH
19026897500 | INSTALL 3400' OF 2"/4"PMMP | - | - | - | - | 0.1218% | 76209.9 | 75934.4643 | 275.4357 | 2020-01-01 | 2020-12-31 | 2020-01-20 | 2020-02-19
18026798301 | INSTALL 2500'-12" CSHP | - | - | - | - | 1.801% | 1126864.73 | 1166541.2469 | -39676.5169 | 2020-01-01 | 2020-12-31 | 2019-10-31 | 2020-02-27
19026887301 | INSTALL 925' OF 2"PMMP MAIN | - | - | - | - | 0.09992% | 62516.06 | 59176.4383 | 3339.6217 | 2020-01-01 | 2020-12-31 | 2020-02-04 | 2020-02-21
20026946900 | INSTALL 300' OF 2"PMMP MAIN | - | - | - | - | 0.01671% | 10451.88 | 16395.5214 | -5943.6414 | 2020-01-01 | 2020-12-31 | 2020-05-19 | 2020-05-21
18026780001 | R-1221 ACQUIRE NEW REG SITE | - | - | - | - | 0.1027% | 64226.88 | 50787 | 13439.88 | 2020-01-01 | 2020-12-31 |  | 2020-02-24 | 24FEB20: COMPLETED BY AUTUMN DMYTREWYCZ OF TEMA FISHEL (BKSLONE)
20026930600 | INSTALL 10'-2" PMMP | - | - | - | - | 0.003039% | 1901.31 | 5414.5548 | -3513.2448 | 2020-01-01 | 2020-12-31 | 2020-02-25 | 2020-02-26
18026785901 | INSTALL 1400'-6" PMLP-LEAKAGE | - | - | - | - | 0.6842% | 428087.51 | 310400.4669 | 117687.0431 | 2020-01-01 | 2020-12-31 | 2019-10-14 | 2020-03-03 | OVERRUN EXPLANATION: THIS POJECT TOOK A LITTLE OVER TWICE THE LABOR HOURS T O COMPLETE OVER WHAT WAS ESTIMATED RESULTING IN $33K IN EXTRA LABOR. ADDITI ONALLY, WE HAD TO GET OUR IN THE STREET MORE THAN ESTIMATED RESULTING IN AN OTHER $60K IN EXTRA PAVING CHARGES.
19026883300 | INSTALL 100' OF 2"PMIP MAIN | - | - | - | - | 0.04086% | 25567.26 | 25386.0335 | 181.2265 | 2020-01-01 | 2020-12-31 | 2020-02-24 | 2020-02-28
20026916700 | INSTALL 65' OF 4"PMMP | - | - | - | - | 0.07114% | 44512.84 | 32594.999 | 11917.841 | 2020-01-01 | 2020-12-31 | 2020-02-18 | 2020-03-02 | COMMIT DATE WAS ON SUNDAY 3-1-2020
19026882300 | INSTALL 130' OF 3"PMLP MAIN | - | - | - | - | 0.06675% | 41762.72 | 45765.5621 | -4002.8421 | 2020-01-01 | 2020-12-31 | 2020-03-04 | 2020-04-16 | INSTALLED 128' OF NEW 030 PL ML TESTED @ 90 # FOR 1 HR ONSITE. INSTALLED 4 ANODES ON BS ML. INSTALLED 5 MB AND TW STATION TO LOCATE NEW PLML INT/EXT CORR INSPT COMPLETED 2-28-20 JENS/RLA
19026899900 | INSTALL 3720' OF 2"/4"PMMP | - | - | - | - | 0.1515% | 94770.28 | 83267.4643 | 11502.8157 | 2020-01-01 | 2020-12-31 | 2020-01-17 | 2020-03-03 | MISSED COMMIT DATE DUE TO BAD WEATHER CONDITIONS.
20026921400 | INSTALL 30' OF 2"PMLP MAIN | - | - | - | - | 0.07597% | 47531.53 | 25344.1992 | 22187.3308 | 2020-01-01 | 2020-12-31 | 2020-02-17 | 2020-03-06 | TWALKER/KY 03-09-20: I TRIED TO REVISE JOB ORDER AFTER SCOPE CHANGE AND ADDITIONAL WORK REQUIRED BY CONSTRUCTION BUT WMS WOULD NOT ALLOW REVISION DUE TO UNPAID INVOICES MESSAGE.
19026890600 | INSTALL 1440'-6" PMMP | - | - | - | - | 0.4993% | 312393.01 | 257137.6403 | 55255.3697 | 2020-01-01 | 2020-12-31 | 2020-01-07 | 2020-03-04 | DNLEMONS/KY 8/15/2020: JOB OVERRUN DUE TO ADDITIANAL CONTRACT COST AND LABO R HOURS. CONTRACT COST OVER BY $34,000 DUE TO ADDITIONAL VACUMEN EXCAVATION AND CONTRACT ENGINEERING AND LS TIME FOR FIELD ADJUSTMENTS. LABOR OVERRAN 150 HOURS FOR ADDITIONAL $15,000 IN COSTS.
19026878700 | ACQUIRE ESMT ON HOLT, ET AL | - | - | - | - | 0.06678% | 41783.72 | 56500 | -14716.28 | 2020-01-01 | 2020-12-31 | 2019-05-23 | 2020-03-06 | COMPLETED BY CHRIS DAVIS W/TEAM FISHEL WHO ACQUIRED PERMANENT ESMTS OVER COLBY FARM, HOLT, ET AL, AND COYLE PROPERTIES (BKSLONE)
19026884501 | INSTALL 70'-2" PMMP | - | - | - | - | 0.2079% | 130100.01 | 62432.7017 | 67667.3083 | 2020-01-01 | 2020-12-31 | 2020-01-27 | 2020-03-06 | ON EXTRA SECTION OF MAIN WAS FOUND THAT NEEDED TO BE RE-ROUTED WHICH ADDED TIME TO THE JOB. SCOPE CHANGE COMPLETED TO REFLECT SUBMITTED LEVEL 2 EXPLANATION AND LOADED INTO WMSDOCS. D.LEMONS 9/21/2020
18026848100 | ACQUIRE LAND FOR USS | - | - | - | - | 0.01787% | 11183.58 | 5291 | 5892.58 | 2020-01-01 | 2020-12-31 | 2018-12-10 | 2020-03-10
19026888600 | ACQUIRE LAND RIGHTS | - | - | - | - | 0.002563% | 1603.85 | 5332 | -3728.15 | 2020-01-01 | 2020-12-31 | 2019-07-30 | 2020-03-10
20026938300 | INSTALL 5' OF 6"PMLP MAIN | - | - | - | - | 0.0002927% | 183.13 | 8731.8561 | -8548.7261 | 2020-01-01 | 2020-12-31 | 2020-03-12 | 2020-03-13
20026919900 | INSTALL 100'-8" PMLP | - | - | - | - | 0.1453% | 90885.82 | 72449.2726 | 18436.5474 | 2020-01-01 | 2020-12-31 | 2020-02-25 | 2020-03-17
19026905900 | INSTALL 35' OF 2"/4"PMMP MAIN | - | - | - | - | 0.09912% | 62018.23 | 24704.1056 | 37314.1244 | 2020-01-01 | 2020-12-31 | 2019-10-25 | 2020-03-19 | OVERRUN EXPLANTION: PROJECT WAS ESTIMATED FOR A 3 MAN CREW FOR 40 HOURS WHE N A 4 MAN CREW FOR 69 HOURS WAS REQUIRED. COMPANY LABOR ALSO OVERRAN BOTH L EADING TO THE OVERRUN. TWALKER/KY 09-21-2020: COST OVER DUE TO PROJECT PLANNED FOR 3 MAIN CREW BUT PAIDFOR 4 MAIN CREW PLUS ADDITION WORK REQUIRED INCREASED CONTRACT COST BY $20,000 SEGA WAS INCREASED BY $3000
20026921900 | INSTALL 5'-1"CSHP W/GATE VLV | - | - | - | - | 0.05289% | 33092.16 | 29034.4738 | 4057.6862 | 2020-01-01 | 2020-12-31 | 2020-03-10 | 2020-03-17
18026790901 | INSTALL 800' OF 4"PMMP MAIN | - | - | - | - | 0.2038% | 127535.23 | 130601.3453 | -3066.1153 | 2020-01-01 | 2020-12-31 | 2020-02-20 | 2020-03-30
20026938800 | INSTALL 10' OF 2"PMMP MAIN | - | - | - | - | 0.005989% | 3747.38 | 11025.9805 | -7278.6005 | 2020-01-01 | 2020-12-31 | 2020-03-25 | 2020-03-26 | INSTALLED 13' OF 020 MAIN. TESTED FROM HV TEE TO HV TEE FOR 1HR AT 90LBS. TEST OK.SQUEEZED OFF 040 TO CUT OUT TEE.INSTALLED END CAPS ON 040.SOAP TEST FITTINGS AT OP NGF.
19026904100 | INSTALL 1300' OF 2"PMMP MAIN | - | - | - | - | 0.2707% | 169376.29 | 155044.5883 | 14331.7017 | 2020-01-01 | 2020-12-31 | 2020-03-19 | 2020-08-12
20026940300 | INSTALL 10' PMIP | - | - | - | - | 0.007104% | 4445 | 4738.9093 | -293.9093 | 2020-01-01 | 2020-12-31 | 2020-03-27 | 2020-03-30 | ELECTROFUSE COUPLINGS WITH DEAD END CAPS FOR 5MINS @ OP, SOAP TESTED ALL END CAPS AT VERIFICATION TEES AND PURGE TEES FOR 5MINS @ OP, 3-30-2020 OM ELECTROFUSE COUPLINGS WITH DEAD END CAPS FOR 5MINS @ OP, SOAP TESTED ALL END CAPS AT VERIFICATION TEES AND PURGE TEES FOR 5MINS @ OP, 3-30-2020 OM INSTALLED 7' 10" OF 2" PLASTIC PIPE INCLUDING 2 90'S & 2 HV TEES, TESTED 2" PLASTIC PIPE INCLUDING 2 90'S & 2 HV TEES @ 90 PSI FOR 1HR, TESTED ALL VERIFICATION TEES & PURGE TEES @ 90 PSI FOR 1HR , SOAP TESTED BOTH
20026940500 | INSTALL 10' OF 4"PMMP MAIN | - | - | - | - | 0.002814% | 1760.54 | 7726.7 | -5966.16 | 2020-01-01 | 2020-12-31 | 2020-04-15 | 2020-03-30
18026794100 | INSTALL 80' - 4" PMLP | - | - | - | - | 0.04911% | 30729.55 | 69878.1892 | -39148.6392 | 2020-01-01 | 2020-12-31 | 2020-03-26 | 2020-04-02 | UNDERRUN EXPLANATION: PROJECT WAS INITIALLY ESTIMATED FOR MUCH MORE CONCRET E AND ASPHAULT. INFACT 250 AND 240 USNITS RESPECTIVELY. NO HARD SURFACE REP ARES WERE USED WHICH THE UNDERRUN INDICATES.
19026914900 | INSTALL 1430'- 2" PMMP | - | - | - | - | 0.2767% | 173110.85 | 168273.1947 | 4837.6553 | 2020-01-01 | 2020-12-31 | 2020-02-11 | 2020-09-18 | 10/13/20 - COST TO DATE APPEARS UNDER DUE TO PAVING. PAVING HAS NOT BEEN PROCESSED AT THIS TIME. -VAH POWERPLANT IS SHOWING $171,982 IN CHARGES WHICH IS IN TOLERENCE. SINCE POWE RPLANT IS THE SYSTEM OF RECORD, POWERPLANT IS PRESUMEND CORRECT.
19026911800 | INSTALL 3,000' - 2"/4" PMMP | - | - | - | - | 0.09796% | 61292.18 | 99658.7961 | -38366.6161 | 2020-01-01 | 2020-12-31 | 2020-03-30 | 2020-04-09 | GAS ON MAIN:11:03 AM - 04/08/2020 PAID MISC DOLLARS & CENTS FOR PORTAPOTTY 05/27/2020 CONTROL# 118352 $107.39 UNDERRUN EXPLANATION: ORIGINAL ESTIMATE FOR 3,000' OF 2" PMMP, ACTUAL INSTALL FOOTAGE 1,600' - 2" PMMP, DEVELOPMENT WAS NOT READY FOR ALL OF PLANNED FOOTAGE, PROJECT COST UNDERRUN BY 40% WHICH IS EQUIVALENT TO INSTALLED MAIN UDERRUN TTOY 9/21/2020
19026908401 | INSTALL 560-2" PMMP | - | - | - | - | 0.1393% | 87168.26 | 124681.7584 | -37513.4984 | 2020-01-01 | 2020-12-31 | 2020-03-19 | 2020-04-14 | UNDERRUN EXPLANATION: THE ESTIMATED COLD PATCH AND OTHER HARD SURFACE REPAL RES WAS NOT NEEDED AS WAS ORIGINALLY INTENED LEADING TO THE UNDERRUN.
18026747100 | INSTALL 753'-4" CSHP | - | - | - | - | 0.2981% | 186509.1 | 160773.9961 | 25735.1039 | 2020-01-01 | 2020-12-31 | 2020-03-09 | 2020-04-16
18026747200 | INSTALL 216-8" CSHP | - | - | - | - | 0.1257% | 78657.87 | 83038.4197 | -4380.5497 | 2020-01-01 | 2020-12-31 | 2020-03-25 | 2020-04-16
19026897801 | INSTALL 12,500' - 2"/4" PMMP | - | - | - | - | 3.564% | 2230105.6 | 2200144.6236 | 29960.9764 | 2020-01-01 | 2020-12-31 | 2020-06-03 | 2020-12-09
19026907800 | RELOCATE 10'-3" PMMP | - | - | - | - | 0.01754% | 10974.69 | 16966.8702 | -5992.1802 | 2020-01-01 | 2020-12-31 | 2020-04-13 | 2020-04-14
20026945800 | INSTAL 5'-2" PMMP (AS BUILT) | - | - | - | - | 0.004345% | 2718.62 | 4095.9465 | -1377.3265 | 2020-01-01 | 2020-12-31 |  | 2020-04-14
18026774600 | INSTALL 900' OF 8"CSHP | - | - | - | - | 0.6538% | 409037.76 | 362869.5724 | 46168.1876 | 2020-01-01 | 2020-12-31 | 2020-02-19 | 2020-04-21 | TWALKER/KY 07-02-2020: PROCESSED THIS PAID RELOCATION FOR FINAL BILLING AND ADDITIONAL AMOUT DUE BY CUSTOMER
19026889500 | INSTALL 410' OF 4"PMLP MAIN | - | - | - | - | 0.3062% | 191568.67 | 184461.6222 | 7107.0478 | 2020-01-01 | 2020-12-31 | 2020-02-27 | 2020-06-17 | MISC DOLLARS AND CENTS PAID FOR PARKING METERS ON JOB PARTIAL LINE GASSED UP, FROM N MILL TO W SHORT ST INCLUDING CHURCHST
19026884200 | INSTALL 5'- 4" PMLP | - | - | - | - | 0.04793% | 29990.35 | 38126.7812 | -8136.4312 | 2020-01-01 | 2020-12-31 | 2020-04-06 | 2020-04-21
20026922100 | INSTALL 400' OF 8"PMMP MAIN | - | - | - | - | 0.1287% | 80494.44 | 78194.4624 | 2299.9776 | 2020-01-01 | 2020-12-31 | 2020-03-27 | 2020-04-21
20026943900 | INSTALL NEW 4"POLY VALVE | - | - | - | - | 0.004697% | 2938.81 | 5878.4625 | -2939.6525 | 2020-01-01 | 2020-12-31 | 2020-04-15 | 2020-04-21
19026870700 | INSTALL 1500' OF 6"PMMP MAIN | - | - | - | - | 0.3755% | 234941.1 | 242580.6463 | -7639.5463 | 2020-01-01 | 2020-12-31 | 2020-02-26 | 2020-04-27
20026947100 | INSTALL 20'-4" PMLP | - | - | - | - | 0.0171% | 10696.02 | 9973.7353 | 722.2847 | 2020-01-01 | 2020-12-31 | 2020-04-22 | 2020-04-23 | MATERIALS FAILED TO BE ORDERED WITH ORIGINAL JOB ORDER (20-0269471-00) THEREFORE WERE ORDER 5/5/20 TO REPLINISH STOCK VIA MATL J.O. 20-8074409-00
18026849400 | INSTALL MI WIRELESS EFC | - | - | - | - | 0.0133% | 8318.67 | 10338.964 | -2020.294 | 2020-01-01 | 2020-12-31 | 2019-01-10 | 2020-04-24 | SOME MATERIAL BACK ORDERED FOR ALMOST 1 YEAR THEN PAPERWORK DID NOT GET TURNED IN FOR COMPLETION
18026844501 | INSTALL 2478'-4" PMLP | - | - | - | - | 1.041% | 651316.9 | 400557.4129 | 250759.4871 | 2020-01-01 | 2020-12-31 | 2020-01-16 | 2020-06-08 | OVERRUN EXPLANATION: TOTAL LABOR WAS ABOUT TWICE WHAT WAS ESTIMATED. ADDITI ONALLY CONTRACT COST WAS ABOUT TWICE AS MUCH AS WELL. THE PROJECT WAS ESTIM ATED UNDER A 2018 CONTRACT, BUT WORKED UNDER A 2020 CONTRACT. THERE WERE 57 0 MORE FLAGGER HOURS THAN ESTIMATED AND SIGNFICANTLY MORE COLD PATCH AND OT HER HARD SURFACE REPAIRS THAT ESTIMATED. FINALLY, THE OVERHEAD EFFECT FROM ALL THESE OVERRUNS CONTRIBUTED AS WELL.
20026929200 | UPGRADE ELECTRONICS | - | - | - | - | 0.005845% | 3657.08 | 3038 | 619.08 | 2020-01-01 | 2020-12-31 | 2020-04-27 | 2020-04-27 | UPGRADED CELL MODEM TO RV50 4G/5G EQUPIMENT INSTALLED BY ACP
20026935800 | UPGRADE ELECTRONICS | - | - | - | - | 0.005707% | 3570.85 | 3205 | 365.85 | 2020-01-01 | 2020-12-31 | 2020-04-27 | 2020-04-27 | UPGRADED CELL MODEM TO RV50 4G/5G EQUPIMENT INSTALLED BY ACP
20026927700 | UPGRADE ELECTRONICS | - | - | - | - | 0.005839% | 3653.56 | 3038 | 615.56 | 2020-01-01 | 2020-12-31 | 2020-04-28 | 2020-04-28 | UPGRADED 2G/3G MODEM TO RV50 4G/5G MODEM EQUIPMENT INSTALLED BY ACP
20026929000 | UPGRADE ELECTRONICS | - | - | - | - | 0.01139% | 7127.42 | 3038 | 4089.42 | 2020-01-01 | 2020-12-31 | 2020-04-28 | 2020-04-28 | REPLACE 2G/3G MODEM WITH RV50 4G/5G MODEM EQUPIMENT INSTALLED BY ACP
20026938500 | INSTALL 2" STOPPLE FITTING | - | - | - | - | 0.01013% | 6336.08 | 16117.9739 | -9781.8939 | 2020-01-01 | 2020-12-31 | 2020-04-28 | 2020-04-28
20026925700 | UPGRADE ELECTRONICS | - | - | - | - | 0.005796% | 3626.23 | 3038 | 588.23 | 2020-01-01 | 2020-12-31 | 2020-04-29 | 2020-04-29 | UPGRADED CELL MODEM FROM 2G/3G TO RV50 4G/5G MODEM EQUIPMENT INSTALLED BY ACP
20026927000 | UPGRADE ELECTRONICS | - | - | - | - | 0.01386% | 8671.75 | 3038 | 5633.75 | 2020-01-01 | 2020-12-31 | 2020-04-29 | 2020-04-29 | UPGRADED 2G/3G MODEM TO RV50 4G/5G MODEM EQUIPMENT INSTALLED BY ACP
20026920200 | INSTALL 205'-2" PMMP | - | - | - | - | 0.06664% | 41692.15 | 24080.9323 | 17611.2177 | 2020-01-01 | 2020-12-31 | 2020-04-08 | 2020-06-02
20026927400 | UPGRADE ELECTRONICS | - | - | - | - | 0.006035% | 3775.71 | 3038 | 737.71 | 2020-01-01 | 2020-12-31 | 2020-04-30 | 2020-04-30 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUPIMENT INSTALLED BY ACP
20026927600 | UPGRADE ELECTRONICS | - | - | - | - | 0.005759% | 3603.22 | 3038 | 565.22 | 2020-01-01 | 2020-12-31 | 2020-04-30 | 2020-04-30 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
20026925600 | UPGRADE ELECTRONICS | - | - | - | - | 0.005811% | 3635.83 | 3038 | 597.83 | 2020-01-01 | 2020-12-31 | 2020-05-01 | 2020-05-01 | UPGRADED CELL MODEM FROM 2G/3G TO RV50 4G/5G EQUIPMENT INSTALLED BY ACP
20026927300 | UPGRADE ELECTRONICS | - | - | - | - | 0.00592% | 3704.23 | 3038 | 666.23 | 2020-01-01 | 2020-12-31 | 2020-05-01 | 2020-05-01 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
20026945700 | INSTALL 100' OF 2" PMMP MAIN | - | - | - | - | 0.01517% | 9491.38 | 11849.2172 | -2357.8372 | 2020-01-01 | 2020-12-31 | 2020-04-29 | 2020-05-01
20026948800 | INSTALL 6'-4"/2" PMMP | - | - | - | - | 0.007611% | 4762.09 | 8336.5018 | -3574.4118 | 2020-01-01 | 2020-12-31 | 2020-05-01 | 2020-05-01
20026925100 | UPGRADE ELECTRONICS | - | - | - | - | 0.005779% | 3615.83 | 3205 | 410.83 | 2020-01-01 | 2020-12-31 | 2020-05-04 | 2020-05-04 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
20026927200 | UPGRADE ELECTRONICS | - | - | - | - | 0.005937% | 3714.82 | 3038 | 676.82 | 2020-01-01 | 2020-12-31 | 2020-05-04 | 2020-05-04 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
20026927500 | UPGRADE ELECTRONICS | - | - | - | - | 0.01295% | 8101.24 | 3038 | 5063.24 | 2020-01-01 | 2020-12-31 | 2020-05-04 | 2020-05-04 | UPGRADED CELL MODEM FROM 2G/3G TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
20026929800 | UPGRADE ELECTRONICS | - | - | - | - | 0.00617% | 3860.13 | 3038 | 822.13 | 2020-01-01 | 2020-12-31 | 2020-05-05 | 2020-05-11 | UPGRADED 2G/3G CELL MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
20026929900 | UPGRADE ELECTRONICS | - | - | - | - | 0.01964% | 12290.02 | 3038 | 9252.02 | 2020-01-01 | 2020-12-31 | 2020-05-05 | 2020-05-05 | UPGRADED 2G/3G CELL MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
19026871400 | INSTALL 1000'-2" PMIP | - | - | - | - | 0.1279% | 80013.85 | 75531.5699 | 4482.2801 | 2020-01-01 | 2020-12-31 | 2020-04-08 | 2020-05-06
19026881600 | INSTALL 2240'-4" PMLP | - | - | - | - | 0.6282% | 393029.99 | 332950.5928 | 60079.3972 | 2020-01-01 | 2020-12-31 | 2020-02-06 | 2020-07-23
20026931000 | UPGRADE ELECTRONICS | - | - | - | - | 0.000749% | 468.63 | 3150 | -2681.37 | 2020-01-01 | 2020-12-31 | 2020-05-06 | 2020-05-06 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
19026886901 | INSTALL 985'-2" PMMP | - | - | - | - | 0.381% | 238352.12 | 189725.2878 | 48626.8322 | 2020-01-01 | 2020-12-31 | 2020-04-20 | 2020-06-05 | UNDERRUN EXPLANATION: THE 3000 FEET OF 6 & 2 HAS NOT HIT YET. THAT AMOUNT A ND THE CUMULATIVE EFFECT OF THAT AMOUT HAS LED TO THE UNDERRUN. THOSE CHARG ES ARE EXPECTED TO HIT. OVERUN EXPLANATION: THE PAVING COSTS FINALY HIT. THOSE EXCEEDED ESTIMATED B Y $37,800. THAT AMOUNT PLUS THE OVERHEAD EFFECT FROM THOSE CHANGES CONTROIB TED TO THE OVERRUN.
20026949400 | INSTALL 5' OF 2"PMMP MAIN | - | - | - | - | 0.003028% | 1894.3 | 8641.697 | -6747.397 | 2020-01-01 | 2020-12-31 | 2020-05-11 | 2020-05-11
18026776501 | INSTALL 12,000' - 2"/4" PMMP | - | - | - | - | 2.963% | 1853804.2 | 1751148.4008 | 102655.7992 | 2020-01-01 | 2020-12-31 | 2020-06-23 | 2020-11-05 | UNDERRUN EXPLANATION: THE WMS OUT OF TOLERENCE REPORT IS INCORRECT. POWERPL ANT INDICATES $1.77M HAS HIT TO DATE 11/24/2020. THAT IS WITHIN TOLERENCE A ND NO EXPLANATION IS NEEDED AT THIS TIME.
19026893001 | INSTALL 75' - 4" CSHP | - | - | - | - | 0.196% | 122604.58 | 102933.7365 | 19670.8435 | 2020-01-01 | 2020-12-31 | 2020-04-28 | 2020-05-19
19026915201 | INSTALL 5075' OF 4"/6"PMLP MN | - | - | - | - | 2.587% | 1618733.89 | 1601511.955 | 17221.935 | 2020-01-01 | 2020-12-31 | 2020-05-08 | 2020-10-26 | UNDERRUN EXPLANATION: APPARENTLY POWERPLANT DID NOT UPDATE WMS THIS MONTH. WHILE THE OUT OF TOLERANCE REPORT SHOWS A SIGNIFICANT UNDERRUN, POWER PLANT SHOWS A SPEND OF$1,537,407 AS OF 11/24/2020. SINCE POWERPLANT IS THE SYSTE M OF RECORD, POWERPLANT IS PRESUMED CORRECT. THERE FOR NO EXPLANATION IS NE EDED.
18026779600 | R-1221 INSTALL NEW REG SETTING | - | - | - | - | 0.08285% | 51837.32 | 85333.0009 | -33495.6809 | 2020-01-01 | 2020-12-31 | 2020-03-30 | 2020-05-15 | DELAY IN PROJECT WITH STATE HIGHWAY DEPARTMENT AND ALSO WITH ACQUIRING LAND FOR THE STATION . 22SEP20 UNDERRUN EXPLANATION: ACTUAL UNDERRUN WAS ONLY $13240 (15.5%) AND WAS DUE MOSTLY TO FISHEL CONTRACT LABOR $5000 LESS THAN ESTIMATED AND THE ESTIMATED MISC DOLLARS AND CONTINGENCY AMOUNTING TO $8500 THAT NOT NEEDED MAKING UP THE AMOUNT OF UNDERRUN (BKSLONE).
20026949700 | INSTALL 20' OF 8"PMLP MAIN | - | - | - | - | 0.008274% | 5176.53 | 8890.7193 | -3714.1893 | 2020-01-01 | 2020-12-31 | 2020-05-20 | 2020-05-21 | CUT OUT STEEL TO STEEL COUPLING-AND REPLACED WITH 15' OF 8" PLASTIC-PRESS TESTED @ 90LBS FOR 1 HR TEST OK-SOAP TEST FINAL TIE INS AND PAC CLAMPS @ OP TEST OK-BHBNGF-11IWC VERIFIED-COMPLETED TO TIE IN PLAN -ANICHOLS 5-20-2020
18026796201 | INSTALL 7600' - 2" PMMP | - | - | - | - | 2.099% | 1313128.04 | 1236118.6701 | 77009.3699 | 2020-01-01 | 2020-12-31 | 2020-05-26 | 2020-12-07
20026944700 | INSTALL 791' - 2" PMLP | - | - | - | - | 0.2281% | 142734.85 | 146581.9295 | -3847.0795 | 2020-01-01 | 2020-12-31 | 2020-05-08 | 2020-06-05 | UNDERRUN EXPLANATION: PAVING HAS NOT HIT YET FOR THIS JOB SO IT IS TOO EARL Y FOR AN EXPLANATION. UPDATE EXPLANATION 11/24/2020. STILL NOT PAVING HAS HIT. 2400 UNITS OF 6 & 2 IS EXPECTED.
20026925400 | INSTALL 775' OF 2"PMMP MAIN | - | - | - | - | 0.3371% | 210896.27 | 314223.8791 | -103327.6091 | 2020-01-01 | 2020-12-31 | 2020-04-21 | 2020-08-06 | TWALKER/KY 09-21-2020: JOB UNDER RUNNING IN WMS DUE TO PAVING/RESTORATION COST HAVE NOT POSTED AT THIS TIME. EXPLANATION UPDATE: SOME OF THE PAVING HAS HIT, BUT NOT ALL. ALSO POWERPLAN T MAY NOT HAVE UPDATED WMS THIS MONTH. POWERPLANT SHOWS ABOUT $100,000 MORE COSTS THAN WMS. POWER PLANT PRESUMEND CORRECT.
20026920100 | INSTALL 350'-2" PMMP | - | - | - | - | 0.02294% | 14350.38 | 26075.9323 | -11725.5523 | 2020-01-01 | 2020-12-31 | 2020-04-02 | 2020-06-17
20026923800 | INSTALL 815'-4" PMLP/DIXON ST | - | - | - | - | 0.1821% | 113908.72 | 99856.4425 | 14052.2775 | 2020-01-01 | 2020-12-31 | 2020-03-03 | 2020-06-18
20026952300 | INSTALL 5'-6" PMMP | - | - | - | - | 0.007419% | 4641.7 | 2468.8932 | 2172.8068 | 2020-01-01 | 2020-12-31 | 2020-05-26 | 2020-05-26
20026952100 | INSTALL 20' OF 2"PMMP MAIN | - | - | - | - | 0.0008909% | 557.41 | 8084.5356 | -7527.1256 | 2020-01-01 | 2020-12-31 | 2020-05-27 | 2020-05-27 | CUT OUT AND REPLACED 14' SECTION OF MAIN-PRESS. TEST NEW MAIN @ 90LBS FOR 1HR TEST OK-SOAP TESTED FINAL TIE IN @OP TEST OK- SOAP TEST TEE CAPS @OP TEST OK- 14 PSI VERIFIED-BHBNGF-ANICHOLS 5-27-2020
20026945500 | INSTALL 535'-4"PMLP | - | - | - | - | 0.1197% | 74906.33 | 99653.3864 | -24747.0564 | 2020-01-01 | 2020-12-31 | 2020-05-04 | 2020-06-18
18026820300 | INST. FN 354 EXTRA LP OPP | - | - | - | - | 0.05864% | 36688.19 | 42364.1646 | -5675.9746 | 2020-01-01 | 2020-12-31 | 2020-05-29 | 2021-05-13 | 2/17/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS 2/19/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING LP PAPERWORK CFARIS REGULATOR AND ER350 INSTALLED BY JAMES PASLEY ON 6/4/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026883600 | INSTALL GMB STATION | - | - | - | - | 0.1318% | 82488.69 | 104215.9406 | -21727.2506 | 2020-01-01 | 2020-12-31 | 2020-05-12 | 2020-06-30 | COMPLETION DELAYED WAITING ON RUPP ARENA
20026953300 | INSTALL 20' OF 4"PMMP MAIN | - | - | - | - | 0.006218% | 3890.43 | 6050.3807 | -2159.9507 | 2020-01-01 | 2020-12-31 | 2020-06-04 | 2020-06-05 | FOR 5MINS TEST OK. SOAP TESTED EFC AT OP.TEST OK. TESTED S/L FOR 418 FROM MAIN TO MTR FOR 5MINS AT 90LBS TEST OK. REMOVED BYPASS AND GAUGES. INSTALLED END CAPS ON TEES. SOAP TESTED CAPS AT OP. NGF. BHB NGF INSTALLED 8' SECTION OF 040 WHILE ON MAIN ON BYPASS.TESTED MAIN FOR 20MINS AT 90LBS TEST OK.TEST BYPASS AND TEES FOR 1HR AT 90LBS TEST OK. TESTED VERF -ICATION TEES FOR 5MINS AT 90LBS TEST OK. TESTED PURGE TEE/ SCV TEE AT 90LB
20026953500 | INSTALL 20' OF 2"PMIP MAIN | - | - | - | - | 0.004296% | 2688.06 | 4692.5356 | -2004.4756 | 2020-01-01 | 2020-12-31 | 2020-06-04 | 2020-06-05
17026730900 | INSTALL 3700'-12" CSHP | - | - | - | - | 1.243% | 777938.36 | 812061.6863 | -34123.3263 | 2020-01-01 | 2020-12-31 | 2020-03-24 | 2020-06-22
15026620100 | INSTALL 1735'-4"/2" PMMP | - | - | - | - | 0.3562% | 222838.78 | 250393.7292 | -27554.9492 | 2020-01-01 | 2020-12-31 | 2020-04-29 | 2020-06-17 | 22MAR21: UNDERUN EXPLANATION: THE GREATEST CONTRIBUTORS TO THE UNDERRUN CAME FROM: 1) CJHUGHES' ACTUAL CONTRACT BEING ABOUT $53K LESS THAN ESTIMATED BECAUSE OF LESS ROCK ENCOUNTERED, LESS SAND & STONE BACKFILL REQUIRED, LESS HARD SURFACE RESTORATION NEEDED, AND NO DOZER & LESS TRACKHOE REQUIRED AND 2) $25K IN CONTINGENCY FUNDS THAT WE NOT NEEDED. FORELL'S $20K CLEARING CHARGES, ORIGINALLY ESTIMATED UNDER "OTHER", WAS CAPTURED UNDER CONTRACT LABOR.
20026948600 | INSTALL 10' - 2" PMMP | - | - | - | - | 0.007693% | 4813.41 | 3859.8968 | 953.5132 | 2020-01-01 | 2020-12-31 | 2020-06-09 | 2020-07-17 | SEE PAPER PACKET SEE DPI COMMENTS
18026835600 | INST. FN 168 EXTRA LP OPP | - | - | - | - | 0.0821% | 51366.67 | 40101.1646 | 11265.5054 | 2020-01-01 | 2020-12-31 | 2020-02-20 | 2021-04-08 | CCC TICKET NOT REQUIRED NOT AT STATION 4/7/21 CFARIS CCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS REGULATORS AND ER350 INSTALLED BY DANNY ASH ON 6/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021
19026909901 | INSTALL 1696'-4",6"&8" PMMP | - | - | - | - | 0.5899% | 369056.91 | 558448.3569 | -189391.4469 | 2020-01-01 | 2020-12-31 | 2020-04-13 | 2020-07-22 | PAID MISC DOLLARS AND CENTS FOR CONCRETE BLOCK. PAID MISC DOLLARS AND CENTS FOR PORTABLE TOILET INSTALLED: 1197' - 8" PMMP 357' - 4" PMMP 84' - 6" PMMP ABANDONED: 1455' - 8" BSMP 321' - 4" PMMP UNDERRUN EXPLANATION: PAVING COSTS WERE ESTIMATED THAT THE CITY ENDED UP PE RFORMING AND PAYING FOR.
18026833100 | INST. FN 31 EXTRA LP OPP | - | - | - | - | 0.03687% | 23067.9 | 23795.1646 | -727.2646 | 2020-01-01 | 2020-12-31 | 2020-06-11 | 2021-04-08 | REGULATOR AND ER350 INSTALLED BY DANNY ASH ON 6/11/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
17026730701 | INSTALL 780' 2" PMIP | - | - | - | - | 0.07702% | 48188.8 | 83787.7101 | -35598.9101 | 2020-01-01 | 2020-12-31 | 2020-06-10 | 2020-07-01 | UNDERRUN EXPLANATION: THIS PROJECT WAS ESTIMATED FOR ONE CONTRACTOR WHOSE UNIT COSTS WERE HIGHER THAT THE CONTRACTOR WHO PERFORMED THE WORK LEADING T O THE UNDERRUN OF $36K.
19026855600 | INSTALL 4,275' OF 2"/4" PMMP | - | - | - | - | 1.046% | 654541.34 | 444260.5602 | 210280.7798 | 2020-01-01 | 2020-12-31 | 2020-04-09 | 2020-09-01 | OVERRUN EXPLANATION: PROJECT TOOK 544 MORE HOURS THAN LABOR ESTIMATING TOOL SUGGESTED RESULTING AN A $31K INCREASE IN LABOR. ALSO THE PAVING ESTIMATE W AS $183,510 BUT THE ACTUAL HARD SURFACE REPAIRS WAS $293,070. THESE INCREAS ES CAUSED A COMMENSURATE INCREASE IN THE OVERHEARDS.
20026956500 | INSTALL 5'-4" PMMP | - | - | - | - | 0.02479% | 15511.9 | 4635.7623 | 10876.1377 | 2020-01-01 | 2020-12-31 | 2020-06-18 | 2020-06-16 | ABN 4 FEET OF 4" PL GM AFTER FACDAM - INSTALLED 4 FEET OF 4" PL TESTED PIPE ON SITE 90 PSI FOR 20 MINS - TESTED OK - SOAP TESTED 2 E/F CPLGS @ OP CGI BANKS FOR SECONDARY DAMAGE OK - SDADAMS 06-17-20 0030 CO OFF SITE
18026779800 | R-1221 INSTALL NEW REG BLDG | - | - | - | - | 0.1542% | 96473.83 | 89078.2364 | 7395.5936 | 2020-01-01 | 2020-12-31 | 2020-06-09 | 2020-06-30 | ESPARKS 06-18-20
20026931600 | INSTALL 920' OF 6"PMLP MAIN | - | - | - | - | 0.2074% | 129734.27 | 135039.5537 | -5305.2837 | 2020-01-01 | 2020-12-31 | 2020-05-11 | 2020-07-14
20026956700 | INSTALL 5'-4" PMLP AS-BUILT | - | - | - | - | 0.0003349% | 209.55 | 3901.6492 | -3692.0992 | 2020-01-01 | 2020-12-31 | 2020-06-19 | 2020-06-19 | INSTALLED 2' OF 4" PL TO REPAIR DAMAGE TO SERVICE TEE TESTED MAIN 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11" WC
20026957100 | INSTALL 5'-2" PMMP | - | - | - | - | 0.005293% | 3311.4 | 3193.011 | 118.389 | 2020-01-01 | 2020-12-31 | 2020-06-23 | 2020-06-23 | INSTALLED NEW PEICE OF MAIN TEST 90 LB FOR 20 MIN FOL ON SITE PURGED OUT SOAP TEST FINAL TIE IN AT OP BAR HOLE BANKS NO GAS FOUND
20026957400 | INSTALL 5'-2" PMMP | - | - | - | - | 0.00191% | 1195.21 | 3933.3497 | -2738.1397 | 2020-01-01 | 2020-12-31 |  | 2020-06-22 | TEST 90LBS 20 MINS WITH AIR PER EMERGENCY LEAK/ENGINEERING RC
18026796700 | INSTALL 2150' - 2" PMMP | - | - | - | - | 0.6367% | 398357.79 | 526359.4092 | -128001.6192 | 2020-01-01 | 2020-12-31 | 2020-04-08 | 2020-09-09 | UNDERRUN EXPLANATION: IT DOES NOT APPARE ALL OF THE PAVING HAS HIT YET. REC OMMEND WAITING UNTIL THAT OCCURS AND MAKE ANOTHER ASSESSMENT. 11/24/2020 UPDATE TO UNDERRUN EXPLANATION: SOME OF THE PAVING DID HIT AND P ERHAPS ALL OF IT. POWERPLANT SHOWS THE COSTS DIFFERENTLY THAN WMS. SINCE PO WERPLANT IS THE FINANCIAL SYSTEM OF RECORD, POWER PLANT IS PRESUMED CORRECT . THE COSTS AS OF 11/24/2020 ARE $358620.THE UNDERRUN IS DUE TO PAVING. TH IS WAS WORKED IN CONJUNCTION WITH A MUNICIPAL PROJECT AND PERHAPS THE CITY BILLED US LESS THAN WE ANTICIPATED.
19026901901 | INSTALL 3480' OF 2"/4"PMMP | - | - | - | - | 0.2695% | 168603.1 | 154827.601 | 13775.499 | 2020-01-01 | 2020-12-31 | 2020-05-18 | 2020-06-25
20026958000 | INSTALL 5'-4" PMIP LEAK REPAIR | - | - | - | - | 0.003065% | 1917.85 | 6231.4115 | -4313.5615 | 2020-01-01 | 2020-12-31 | 2020-06-26 | 2020-06-26 | INSTALLED 2' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
20026958600 | INSTAL 5'2" PMMP | - | - | - | - | 0.03814% | 23861.05 | 3022.0586 | 20838.9914 | 2020-01-01 | 2020-12-31 | 2020-06-30 | 2020-08-18
18026835200 | INST. FN 160 EXTRA LP OPP | - | - | - | - | 0.04548% | 28453.14 | 40101.1646 | -11648.0246 | 2020-01-01 | 2020-12-31 | 2020-02-19 | 2021-03-24 | CLEARNCE 4817 REGULATOR AND ER350 INSTALLED BY JOSH MULLINS ON 7/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026959400 | INSTALL 5'-4" PMMP | - | - | - | - | 0.01617% | 10119.92 | 5950.5246 | 4169.3954 | 2020-01-01 | 2020-12-31 | 2020-07-08 | 2020-07-03
18026833500 | INST. FN 33 EXTRA LP OPP | - | - | - | - | 0.03804% | 23799.46 | 40101.1646 | -16301.7046 | 2020-01-01 | 2020-12-31 | 2019-08-30 | 2021-04-09 | REGULATOR AND ER350 INSTALLED BY DANNY ASH ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/9/2021 GCCC TICKET NOT REQUIRED ON 4/9/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026960000 | INSTALL 5'-2" PMMP | - | - | - | - | 0.0002464% | 154.14 | 5425.135 | -5270.995 | 2020-01-01 | 2020-12-31 | 2020-07-24 | 2020-07-24 | INSTALLED 5 FT OF 2 IN MAIN TEST 90 LB FOR 20 MIN SOAP TEST FINAL TIE IN AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND GAUGED OFF OF METER SET
18026832900 | INST. FN 29 EXTRA LP OPP | - | - | - | - | 0.03087% | 19315.51 | 42364.1646 | -23048.6546 | 2020-01-01 | 2020-12-31 | 2020-07-07 | 2021-03-26 | REGULATOR AND ER350 INSTALLED BY DANNY ASH ON 7/7/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026932600 | INSTALL 900' OF 2"PMMP MAIN | - | - | - | - | 0.1337% | 83635.99 | 109561.4915 | -25925.5015 | 2020-01-01 | 2020-12-31 | 2020-06-24 | 2020-07-14
20026959800 | INSTALL 3' - 4" PMLP | - | - | - | - | 0.0002866% | 179.33 | 4448.189 | -4268.859 | 2020-01-01 | 2020-12-31 |  | 2020-07-27
18026803400 | INST. FN 14049 EXTRA LP OPP | - | - | - | - | 0.03803% | 23794.44 | 21579.1646 | 2215.2754 | 2020-01-01 | 2020-12-31 | 2020-03-04 | 2021-02-19 | GCCC# 11422 REGULATOR REPLACED AND ER350 INSTALLED BY CHRIS COX ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 02192021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026818700 | INST. FN 209 EXTRA LP OPP | - | - | - | - | 0.0626% | 39166.53 | 21767.1646 | 17399.3654 | 2020-01-01 | 2020-12-31 | 2020-06-19 | 2021-02-26 | GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK 2/25/2021 CFARIS REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026833700 | INST. FN 35 EXTRA LP OPP | - | - | - | - | 0.06086% | 38079.03 | 40101.1646 | -2022.1346 | 2020-01-01 | 2020-12-31 | 2020-06-26 | 2021-03-31 | CC# 15636. 3/18/21 DSASH CCC 15636 REGULATOR AND ER350 INSTALLED BY JOSH MULLINS ON 7/8/2020 REGULATOR REPLACED BY DANNY ASH ON 3/19/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026843900 | NSP INSTALL 800'-2" PMMP | - | - | - | - | 0.09208% | 57609.11 | 53353.5894 | 4255.5206 | 2020-01-01 | 2020-12-31 | 2020-06-29 | 2020-07-20
20026957700 | INSTALL 150' - 6" PMMP | - | - | - | - | 0.1056% | 66063.67 | 67436.4193 | -1372.7493 | 2020-01-01 | 2020-12-31 | 2020-06-30 | 2020-07-13
20026939700 | ACQ ESMT OFF OF 325 WEBSTER AV | - | - | - | - | 0.04776% | 29880.88 | 34881 | -5000.12 | 2020-01-01 | 2020-12-31 | 2020-03-19 | 2020-07-13 | 16JUL20: ALL EASEMENTS ACQUIRED BY TAYLOR CLARK W/FISHEL & LRT'S CLEARED BY TIFFANY FRITCHLEY
20026960200 | INSTALL 5' OF 4"PMMP MAIN | - | - | - | - | 0.0004587% | 286.98 | 7137.1177 | -6850.1377 | 2020-01-01 | 2020-12-31 | 2020-07-20 | 2020-07-13
17026712401 | INSTALL 4000'-2" & 6" PMMP | - | - | - | - | 1.509% | 943947.17 | 767672.4953 | 176274.6747 | 2020-01-01 | 2020-12-31 | 2020-04-06 | 2020-10-12 | OVERRUN EXPLANATION:THE FINA PAVING WAS ANTICIPATED TO BE DONE BY THE CITY; EVER, THAT FELL THROUGH. THE PAVING EXCEEDED THE ESTIMATE BY $280,000.
18026807400 | INST. FN 117 EXTRA LP OPP | - | - | - | - | 0.05017% | 31387.14 | 22920.1646 | 8466.9754 | 2020-01-01 | 2020-12-31 | 2020-11-13 | 2021-04-28 | GCCC# 12986 CMCHOLAN 2-24-2021 CCC#12986 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 7/20/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026960900 | INSTALL 40' OF 2"PMMP MAIN | - | - | - | - | 0.009815% | 6140.89 | 17478.1738 | -11337.2838 | 2020-01-01 | 2020-12-31 | 2020-07-27 | 2020-07-21
20026933101 | INSTALL 430' 4" PMLP | - | - | - | - | 0.2146% | 134274.52 | 181605.0857 | -47330.5657 | 2020-01-01 | 2020-12-31 | 2020-06-17 | 2020-09-16 | UNDERRUN EXPLANATION: THIS PROJECT IS UNDERRUNNING BECUASE 1600' OF 6 & 2 D ID NOT GET USED AS WELL AS TEMPORARY PAVING. THIS IS A COMMUNITY THAT PAVES OUR WORK AND WE HAVE NOT BEEN BILLED YET.
18026821300 | INST. FN 41 EXTRA LP OPP | - | - | - | - | 0.04769% | 29840.14 | 24062.1646 | 5777.9754 | 2020-01-01 | 2020-12-31 | 2020-03-26 | 2021-04-23 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/27/2020 ER350 INSTALLED BY JAMES PASLEY ON 7/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/23/2021 GCCC TICKET NOT REQUIRED ON 4/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026947500 | INSTALL 300' - 2" PMMP | - | - | - | - | 0.05618% | 35150.12 | 24580.9634 | 10569.1566 | 2020-01-01 | 2020-12-31 | 2020-07-21 | 2020-07-28
20026961900 | REPLACE REGULATORS | - | - | - | - | 0.03219% | 20141.23 | 2574.9763 | 17566.2537 | 2020-01-01 | 2020-12-31 |  | 2020-07-27
18026812200 | INST. FN 14184 EXTRA LP OPP | - | - | - | - | 0.05111% | 31976.99 | 23795.1646 | 8181.8254 | 2020-01-01 | 2020-12-31 | 2020-07-23 | 2021-04-29 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 7/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026817900 | INST. FN 14557 EXTRA LP OPP | - | - | - | - | 0.07338% | 45908.85 | 39207.1646 | 6701.6854 | 2020-01-01 | 2020-12-31 | 2019-08-06 | 2021-02-26 | REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026956400 | INSTALL 3000' OF 2"PMMP MAIN | - | - | - | - | 0.1399% | 87524.3 | 83398.4788 | 4125.8212 | 2020-01-01 | 2020-12-31 | 2020-07-14 | 2020-07-31
20026955300 | INSTALL 3700' OF 2"/4"PMMP | - | - | - | - | 0.1818% | 113734.73 | 100593.9609 | 13140.7691 | 2020-01-01 | 2020-12-31 | 2020-07-14 | 2020-08-03 | PAID MISC DOLLARS AND CENTS FOR PORTABLE TOILET $117.49 CONTROL# 166019 10/02/2020
20026963900 | INSTALL 10' - 2" PMMP | - | - | - | - | 0.004819% | 3015.21 | 2010.0583 | 1005.1517 | 2020-01-01 | 2020-12-31 | 2020-08-03 | 2020-08-03
20026964400 | INSTALL 5' OF 4"PMMP MAIN | - | - | - | - | 0.01575% | 9852.15 | 4046.0767 | 5806.0733 | 2020-01-01 | 2020-12-31 | 2020-08-18 | 2020-08-18 | REPLACED 6' - 4" P-MP MAIN, 4 BOLT COUP PL TO PL LEAKING, TEST NEW MAIN ONSITE 90PSI 1 HR OK, ST 2- 4" EF COUP AT OP OK, ST ALL TEES AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN 8-4-20
20026964600 | INSTALL 2" SS | - | - | - | - | 0.0007785% | 487.11 | 3010.1002 | -2522.9902 | 2020-01-01 | 2020-12-31 |  | 2020-08-04
20026964800 | INSTALL 5' OF 2"PMMP MAIN | - | - | - | - | 0.003281% | 2052.61 | 3448.1587 | -1395.5487 | 2020-01-01 | 2020-12-31 |  | 2020-08-19
18026797902 | INSTALL 925'- 4" PMMP MAIN | - | - | - | - | 0.4108% | 257013.83 | 200349.0518 | 56664.7782 | 2020-01-01 | 2020-12-31 | 2020-04-10 | 2020-09-16 | OVERRUN EXPLANATION: PAVING EXCEEDED THE ESTIMATE DUE TO HAVING TO MAKE ADD ITIONAL TIE-INS IN STATE RIGHT OF WAY THAT WERE NOT ANTICIPATED.
20026959600 | INSTALL 800' OF 2"PMIP MAIN | - | - | - | - | 0.0239% | 14955.41 | 33356.3922 | -18400.9822 | 2020-01-01 | 2020-12-31 | 2020-08-04 | 2020-08-10
18026822100 | INST. FN 45 EXTRA LP OPP | - | - | - | - | 0.03901% | 24405.96 | 23886.1646 | 519.7954 | 2020-01-01 | 2020-12-31 | 2020-07-31 | 2021-04-14 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 8/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026923300 | INSTALL 790'-2" PMMP | - | - | - | - | 0.1398% | 87441.25 | 76231.0959 | 11210.1541 | 2020-01-01 | 2020-12-31 | 2020-05-08 | 2020-08-25
18026822600 | INST. FN 161 EXTRA LP OPP | - | - | - | - | 0.07133% | 44631.35 | 24062.1646 | 20569.1854 | 2020-01-01 | 2020-12-31 | 2020-03-27 | 2021-04-27 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 8/11/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807200 | INST. FN 116 EXTRA LP OPP | - | - | - | - | 0.03418% | 21387.49 | 24062.1646 | -2674.6746 | 2020-01-01 | 2020-12-31 | 2020-07-31 | 2021-02-26 | GCCC# 11279 CMCOX 2/5/21 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 8/12/2020 ER350 INSTALLED BY CHRIS COX ON 2/5/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/8/21 GCCC TICKET NOT REQUIRED ON 2/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026898200 | INSTALL 300'-8" CSHP | - | - | - | - | 0.3399% | 212694.57 | 160063.0632 | 52631.5068 | 2020-01-01 | 2020-12-31 | 2020-07-15 | 2020-08-18 | OVERRUN EXPLNATION: PROJECT OVERRAN BECAUSE NON DESTRUCTIVE TESTING WAS NOT ESTIMATED. ADDITIONALLY, 40 HOURS OF SEWER LOCATE SERVICES WERE REQUIRED BUT NOT ESTIM ATED.
19026908201 | INSTALL 54'-4" PMMP | - | - | - | - | 0.1086% | 67959.55 | 73887.2898 | -5927.7398 | 2020-01-01 | 2020-12-31 | 2020-07-30 | 2020-08-14
20026966500 | REPLACE MAIN - LEAKAGE | - | - | - | - | 0.01425% | 8918.57 | 7662.8219 | 1255.7481 | 2020-01-01 | 2020-12-31 | 2020-08-12 | 2020-08-18 | REPLACED 3' - 4" P- MP MAIN, TEST MAIN ONSITE 90PSI 1 HOUR OK, ST 2 - EF COUP AT OP OK, ST ALL TEE CAPS AND END CAPS AT OP OK, BHB CGI NGF LEAK CLEARED, CDESPAIN 8-12-20
20026966900 | OBTAIN EASEMENT FOR 3"CSMP MN | - | - | - | - | 0.02408% | 15068.43 | 18170 | -3101.57 | 2020-01-01 | 2020-12-31 | 2020-08-13 | 2020-08-13
15026619900 | INSTALL 575'-8" PHHP | - | - | - | - | 0.4854% | 303711.63 | 428889.7324 | -125178.1024 | 2020-01-01 | 2020-12-31 | 2020-06-19 | 2020-08-19 | UNDERRUN EXPLANATION: THIS PROJECT AFFECTED THE INLET SUPPLY TO A STEEL FAC TORY. WHEN THE PROJECT WAS DESIGNED AND RELEASED, WE HAD INTENDED TO USE SO ME HIGH DOLLAR BUY-AMERICA COMPLIANT FITTINGS TO KEEP THE STEEL FACTORY IN GAS. TDW HAD DESIGNED ANSI 600 CLASS FITTINGS INSTEAD OF ANSI 150. IT WAS S UMMER BY THE TIME THE WORK WAS PERFORMED AND THE STEEL FACOTRY WENT TO MINI MUM DEMAND ON WEEKENDS AND WE SCHEDULED THE WORK TO COINCIDE. WE ALLOWED PR ODUCTION GAS TO BACKFEED AND SUPPLY THE GAS TO KEEP THE BLAST FURNACE HOT, BUT WERE ABLE TO SHUT VALVES AND TIE-IN STRAIGHT AND AVOID HAVING TO INSTAL L THE HIGH DOLLAR FITTINGS RESULTING IN AN UNDERRUN.
19026900200 | INSTALL 2775' 2"PMMP | - | - | - | - | 0.6914% | 432608.56 | 550649.658 | -118041.098 | 2020-01-01 | 2020-12-31 | 2020-06-11 | 2020-11-24 | UNDERRUN EXPLANATIONS: THE UNDERRUN IS DUE TO PAVING THAT HAS NOT BEEN PERF ORMED YET. THERE ARE TWO FAR JOBS STILL IN PENDING THAT WILL CLOSE THE GAP.
20026966100 | INSTALL 12" FITTING | - | - | - | - | 0.1794% | 112217.25 | 20319.9407 | 91897.3093 | 2020-01-01 | 2020-12-31 | 2020-08-05 | 2020-08-17 | LEVEL 2 BUDGET VARIANCE EXPLANATION LOADED INTO WMSDOCS. 3/22/2021 D. LEMON S
20026941200 | INSTALL 145' OF 4"PMMP | - | - | - | - | 0.04358% | 27268.21 | 27431.3922 | -163.1822 | 2020-01-01 | 2020-12-31 | 2020-08-10 | 2020-08-19
20026967700 | REPLACE MAIN - LEAKAGE | - | - | - | - | 0.001153% | 721.17 | 7808.2374 | -7087.0674 | 2020-01-01 | 2020-12-31 | 2020-08-18 | 2020-08-18
17026743700 | INSTALL 450'-2" PMMP | - | - | - | - | 0.03951% | 24717.31 | 39245.9421 | -14528.6321 | 2020-01-01 | 2020-12-31 | 2020-08-17 | 2020-09-10 | PROJECT ID FOR THIS AND 19-0268690-00 ARE THE SAME. STEVE CANOY 09/10/2020.
20026968900 | INSTALL 15' OF 4"PMMP MAIN | - | - | - | - | 0.007483% | 4682 | 7221.6954 | -2539.6954 | 2020-01-01 | 2020-12-31 |  | 2020-08-20
20026970600 | INSTALL 5' OF 4"PMLP MAIN | - | - | - | - | 0.00357% | 2233.47 | 5549.8956 | -3316.4256 | 2020-01-01 | 2020-12-31 |  | 2020-09-11
19026900001 | INSTALL 10150'-2"/6"/8"PMMP | - | - | - | - | 4.058% | 2539048.57 | 1924983.1791 | 614065.3909 | 2020-01-01 | 2020-12-31 | 2020-11-05 | 2020-12-18
18026821100 | INST. FN 40 EXTRA LP OPP | - | - | - | - | 0.04612% | 28858.08 | 39233.1646 | -10375.0846 | 2020-01-01 | 2020-12-31 | 2020-07-28 | 2021-05-18 | REGULATOR AND ER350 INSTALLED BY JAMES PASLEY ON 8/26/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026914300 | INSTALL 555'-4" PMLP MAIN | - | - | - | - | 0.1299% | 81264.75 | 98513.05 | -17248.3 | 2020-01-01 | 2020-12-31 | 2020-08-24 | 2020-09-02
20026921200 | INSTALL 150' - 4" PMMP | - | - | - | - | 0.07529% | 47105.95 | 12877.4661 | 34228.4839 | 2020-01-01 | 2020-12-31 | 2020-08-19 | 2020-08-27 | OVERRUN EXPLNATION: PROJECT WAS INITIALLY ESTIMATED UNDER A DATED CONTRACT. IT WAS ESTIMATED HOURLY. HOWEVER, BY THE TIME THE PROJECT CAME TO CONSTRUCT ION THE SCOPE HAD CREEPED TO OVER THE AMOUNT ALLOWED FOR HOURLY RATES. AS A RESULT, THE CONTRACT INSTALLATION WAS MUCH HIGHER DUE TO SIGNIFICANTLY MOR E ROCK EXCAVATION BACKFILL AND MORE FOOTAGE.
18026820900 | INST. FN 38 EXTRA LP OPP | - | - | - | - | 0.04934% | 30870.72 | 39188.1646 | -8317.4446 | 2020-01-01 | 2020-12-31 | 2020-08-26 | 2021-05-17 | REGULATOR AND ER350 INSTALLED BY JAMES PASLEY ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026946500 | INSTALL 1012'/2" PMIP MAIN | - | - | - | - | 0.1124% | 70309.8 | 173270.4097 | -102960.6097 | 2020-01-01 | 2020-12-31 | 2020-07-30 | 2020-09-14 | UNDERRUN EXPLANATION: IT DOES NOT APPEAR THAT THE PAVING COSTS HAVE HIT YET . THERE ARE 3500 SQUARE FEET OF HARD SURFACE REPAIRS THAT HAVE NOT HIT.
18026808600 | INST. FN 224 EXTRA LP OPP | - | - | - | - | 0.2446% | 153064.14 | 24062.1646 | 129001.9754 | 2020-01-01 | 2020-12-31 | 2020-08-20 | 2021-05-17 | ESPARKS 11-20-20 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 9/2/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026810200 | INST. FN 275 EXTRA LP OPP | - | - | - | - | 0.06645% | 41578.43 | 23795.1646 | 17783.2654 | 2020-01-01 | 2020-12-31 | 2020-08-21 | 2021-04-30 | 2/4/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/22/21 CFARIS CCC TICKET NOT REQUIRED 4/8/21 NOT AT STATION CFARIS REGULATOR INSTALLED BY CHRIS COX ON 9/3/2020 ER350 INSTALLED BY CHRIS COX ON 10/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/30/2021 GCCC TICKET NOT REQUIRED ON 4/30/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026869000 | INSTALL 575'-2" PMMP | - | - | - | - | 0.06336% | 39642.81 | 51230.9421 | -11588.1321 | 2020-01-01 | 2020-12-31 | 2020-08-28 | 2020-09-10 | PROJECT ID INCLUDES THIS AND 17-0267437-00. STEVE CANOY 09-10-2020
18026813000 | INST. FN 842 EXTRA LP OPP | - | - | - | - | 0.04646% | 29067.19 | 23795.1646 | 5272.0254 | 2020-01-01 | 2020-12-31 | 2020-08-22 | 2021-04-29 | 1/18/21 GCCC TICKET NOT REQUIRED NOT ON SITE AT ANY STATION OFF SITE WORKING ON PAPERWORK GCCC TICKET NOT REQUIRED 2/18/21 NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS CCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 4/12/21 CFARIS CCC TICKET NOT REQUIRED 4/15/21 REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 9/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026912301 | INSTALL 1800' OF 2"PMMP MAIN | - | - | - | - | 0.1094% | 68420.98 | 62341.3739 | 6079.6061 | 2020-01-01 | 2020-12-31 | 2020-08-19 | 2020-09-09
20026932800 | INSTALL FENCE | - | - | - | - | -0.001781% | -1114.6 | 4126.5897 | -5241.1897 | 2020-01-01 | 2020-12-31 | 2020-09-12 | 2020-09-12
20026956901 | INSTALL 20'-6" PMMP | - | - | - | - | 0.05221% | 32666.72 | 42614.3064 | -9947.5864 | 2020-01-01 | 2020-12-31 | 2020-08-31 | 2020-09-16
20026968000 | INSTALL 10' OF 3"PMMP MAIN | - | - | - | - | 0.03495% | 21864.5 | 28353.826 | -6489.326 | 2020-01-01 | 2020-12-31 | 2020-09-10 | 2020-09-14
18026815700 | INST. FN 135 EXTRA LP OPP | - | - | - | - | 0.06347% | 39708.38 | 22470.1646 | 17238.2154 | 2020-01-01 | 2020-12-31 | 2020-01-30 | 2021-02-25 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 9/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026917901 | INSTALL 1150' OF 2"PMMP MAIN | - | - | - | - | 0.05747% | 35956.86 | 40732.3468 | -4775.4868 | 2020-01-01 | 2020-12-31 | 2020-09-03 | 2020-09-17
20026955200 | INSTALL 1850' OF 2"/4"PMMP | - | - | - | - | 0.2183% | 136599.49 | 88356.8591 | 48242.6309 | 2020-01-01 | 2020-12-31 | 2020-08-05 | 2020-09-16 | TWALKER/KY 09-16-2020: I TRIED TO REVISE JOB DUE TO ROCK ENCOUNTERED DURING CONSTRUCTION BUT WMS WOULD NOT ALLOW ME TO REVISE DUE TO UNPAID INVOICES. I EXPECT CONTRACT COST TO INCREASE BY $50000
18026828300 | INST. FN 854 EXTRA LP OPP | - | - | - | - | 0.07093% | 44381.28 | 42364.1646 | 2017.1154 | 2020-01-01 | 2020-12-31 | 2020-07-01 | 2021-04-14 | ACTUAL DATE 04/14/2020 04/16/2020 ENTERED INTO COMPUTER BY MISTAKE ON CONTROL SHEET 122348 ON CONTROL SHEET 122349 ACTUAL DATE 04/15/2020 04/14/2020 ENTERED INTO COMPUTER BY MISTAKE REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 9/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026921800 | INSTALL 1050'4" PMMP | - | - | - | - | 0.06356% | 39770.15 | 33901.1755 | 5868.9745 | 2020-01-01 | 2020-12-31 | 2020-08-31 | 2020-09-21
20026955100 | INSTALL 400'-4" PMMP | - | - | - | - | 0.0308% | 19268.03 | 36445.6461 | -17177.6161 | 2020-01-01 | 2020-12-31 | 2020-09-15 | 2020-09-18
20026961300 | INSTALL 10'-6" PMMP | - | - | - | - | 0.01154% | 7217.5 | 13678.3374 | -6460.8374 | 2020-01-01 | 2020-12-31 | 2020-09-21 | 2020-09-22
20026974800 | INSTALL 15' OF 6"PMLP MAIN | - | - | - | - | 0.01421% | 8893.63 | 12246.4323 | -3352.8023 | 2020-01-01 | 2020-12-31 | 2020-09-21 | 2020-09-24
18026802000 | INST. FN 64 EXTRA LP OPP | - | - | - | - | 0.05831% | 36484.2 | 23795.1646 | 12689.0354 | 2020-01-01 | 2020-12-31 | 2020-09-23 | 2021-05-17 | ESPARKS 11-16-20 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 9/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026805000 | INST. FN 13503 EXTRA LP OPP | - | - | - | - | 0.1028% | 64342.13 | 44603.1646 | 19738.9654 | 2020-01-01 | 2020-12-31 | 2020-04-16 | 2021-05-18 | VOIDED PAY SHEET 008277 PU IN WRONG DATE CORRECTED ON CONTROL SHEET 008278 REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 9/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026976700 | INSTALL 5'-2" PMMP | - | - | - | - | 0% | 0 | 2239.0606 | -2239.0606 | 2020-01-01 | 2020-12-31 | 2020-09-24 | 2020-09-24
20026949100 | INSTALL 12'-2" CSHP HEATER PIP | - | - | - | - | 0.04623% | 28923.83 | 23398.3235 | 5525.5065 | 2020-01-01 | 2020-12-31 | 2020-09-11 | 2020-09-29
20026967500 | INSTALL 90' - 2" PMMP | - | - | - | - | 0.03337% | 20878.42 | 11568.0567 | 9310.3633 | 2020-01-01 | 2020-12-31 | 2020-09-23 | 2020-09-25
19026866900 | INSTALL VRG CONTROLLER | - | - | - | - | 0.04874% | 30497.41 | 15490.7518 | 15006.6582 | 2020-01-01 | 2020-12-31 | 2019-05-07 | 2020-12-30 | JOB DELAYED DUE TO MANPOWER AND COMPLIANCE WORK
20026965500 | INST. FN 24836 EXTRA LP OPP | - | - | - | - | 0.003129% | 1958.03 | 21960.5353 | -20002.5053 | 2020-01-01 | 2020-12-31 | 2020-09-28 | 2021-05-20 | REGULATOR REPLACED BY DANNY ASH ON 9/29/2020 GASKET STRAINER NOT REQUIRED OR INSTALLED SETTING HAS EXISTING T-STRAINER ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/21 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026828100 | INST. FN 733 EXTRA LP OPP | - | - | - | - | 0.04757% | 29764.27 | 23795.1646 | 5969.1054 | 2020-01-01 | 2020-12-31 | 2020-08-22 | 2021-04-14 | ESPARKS 12-15-20 CCC #14454 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 9/29/2020 ER350 INSTALLED BY CHRIS COX ON 12/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026977900 | INSTALL 10' - 2" PMMP | - | - | - | - | 0.0003652% | 228.49 | 4498.8377 | -4270.3477 | 2020-01-01 | 2020-12-31 | 2020-09-29 | 2020-10-02
19026914700 | INSTALL NEW CWT HEATER | - | - | - | - | 0.2209% | 138206.36 | 297220.7055 | -159014.3455 | 2020-01-01 | 2020-12-31 | 2020-09-02 | 2020-12-30 | JOB WAS ON HOLD DUE TO COVID AND WEATHER 22MAR21: UNDER-RUN EXPLANATION: THE GREATEST CONTRIBUTOR TO THE UNDERRUN CAME FROM AN APPARENT DISCREPANCY IN ESTIMATED MATERIAL COSTS BETWEEN WHAT WMS IS SHOWING ($183,970) VS THE CORRECT ESTIMATED MATERIAL COST ($93,235) AS SHOWN ON THE JO APPROVAL COPY IN WMS DOCS, RESULTING IN A NET DIFFERENCE OF -$90,735. THE BALANCE OF THE OVER-RUN IS CONTRIBUTED TO: 1) FISHEL'S ACTUAL CONTRACT BEING ABOUT $26K LESS THAN ESTIMATED BECAUSE THE MAJORITY OF THEIR TIME ENDED UP BEING CHARGED TO THE RELATED (555) 20-0269491-00, 2) $20K IN CONTINGENCY FUNDS THAT WERE NOT NEEDED, 3) $11K IN REDUCED OH'S, AND 4) $10K IN R/W COSTS THAT WAS ESTIMATED UNDER "OTHER" TO COVER A PORITON OF PSI CHARGES, HOWEVER, ENDED UP BEING CAPTURED UNDER CONTRACT LABOR.
20026976100 | INSTALL 100' - 2" PMMP | - | - | - | - | 0.02285% | 14297.06 | 10097.5832 | 4199.4768 | 2020-01-01 | 2020-12-31 | 2020-09-29 | 2020-09-30
20026978700 | INSTALL 10' - 3" PMMP | - | - | - | - | 0.005733% | 3586.89 | 3412.3872 | 174.5028 | 2020-01-01 | 2020-12-31 |  | 2020-10-01
17026689601 | INSTALL 4100' OF 2"/4"PMMP | - | - | - | - | 1.653% | 1034381.72 | 1070240.1923 | -35858.4723 | 2020-01-01 | 2020-12-31 | 2020-07-14 | 2020-11-13
20026943500 | INSTALL 420'-4" PMMP | - | - | - | - | 0.07493% | 46882.16 | 59269.1596 | -12386.9996 | 2020-01-01 | 2020-12-31 | 2020-09-24 | 2020-10-05
20026969200 | INSTALL 490' OF 4"PMIP MAIN | - | - | - | - | 0.07002% | 43812.04 | 34319.2429 | 9492.7971 | 2020-01-01 | 2020-12-31 | 2020-09-21 | 2020-10-02
20026946100 | INSTALL 1725' OF 2"PMMP MAIN | - | - | - | - | 0.6593% | 412502.72 | 289443.1144 | 123059.6056 | 2020-01-01 | 2020-12-31 | 2020-08-03 | 2020-11-12 | TWALKER/KY 03-18-21: LEVEL 2 EXPLAINATION ADDED TO WMS.DOCS DUE TO HIGHER PROJECT COST THAT RESULTED FROM ADDITIONAL HARD SURFACE/PAVING COST AND PROJECT TOOK ADDITIONAL TIME TO COMPLETED.
18026802800 | INST. FN 14168 EXTRA LP OPP | - | - | - | - | 0.08271% | 51752.13 | 42784.1646 | 8967.9654 | 2020-01-01 | 2020-12-31 | 2019-08-02 | 2021-02-18 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 10/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026898000 | INSTALL 3,350' - 2" PMMP | - | - | - | - | 0.5131% | 321058.32 | 299913.4411 | 21144.8789 | 2020-01-01 | 2020-12-31 | 2020-08-25 | 2020-12-01
19026888900 | INSTALL 810' OF 8"CSHP MAIN | - | - | - | - | 0.3988% | 249526.43 | 389698.1154 | -140171.6854 | 2020-01-01 | 2020-12-31 | 2020-09-21 | 2020-10-07 | TWALKER/KY 03-22-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS FOR JOB ORDER UNDER RUN EXPLANATION, CKY WAS ABLE TO OPEN CUT 1/2 THE PROJECT INSTEAD OF PLANNED DIRECT ROCK BORE THE IS LOWER CONTRACT COST AND COMPANY LABOR.
20026979800 | INSTALL 5'-2" PMMP | - | - | - | - | 0.001384% | 866.05 | 4118.0606 | -3252.0106 | 2020-01-01 | 2020-12-31 | 2020-10-07 | 2020-10-07
19026915400 | PM INSTALL REG BUILDING PMF | - | - | - | - | 0.3881% | 242843.56 | 268939 | -26095.44 | 2020-01-01 | 2020-12-31 | 2020-06-24 | 2020-11-04 | COMPLETED PAPERWORK AND CREATED FACILITIES AND RTS 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND IN CHARGE OF PROJECT
19026915500 | PM INSTALL REGULATION PMF | - | - | - | - | 6.046% | 3782591 | 3736473.7717 | 46117.2283 | 2020-01-01 | 2020-12-31 | 2020-06-24 | 2020-12-05 | ESPARKS 09-11-20 ESPARKS 11-03-20 DID ALL STAINLESS STEEL TUBING WORK AND CATALYTIC HEATER INSTALLS INSPECTED REGULATORS AND PLACE STATION IN SERVICE ALL PIPING AND EQUIPMENT INSTALLED BY CONTRACTOR 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND IN CHARGE OF JOB CFARIS 12/5/20
19026916100 | PM INSTALL OUTLET PIPING PMF | - | - | - | - | 0.1168% | 73070.39 | 224570 | -151499.61 | 2020-01-01 | 2020-12-31 | 2020-06-24 | 2020-12-05 | OUT OF TOLERERACE EXPLNATION: THIS IS A MAJOR PROJECTS PROJECT. ACCORDING T O LIZ EISENHART, JENNIFER HAMMONDS WAS ASKED TO DO AN EXPLANATION FOR THE O UT OF TOLERENCE SITUATION. HOWEVER, FIELD ENGINEERING DID NOT SEE THAT EXPL ANATION. CONTACT HEATH HOLMAN PROJECT MANAGER IF YOU HAVE ANY QUESTIONS. I PRESUME IT WILL BE DOCUMENATED IN WMSDOCS.
20026978500 | INSTALL 15' - 2" PMMP | - | - | - | - | 0.009535% | 5965.56 | 10711.935 | -4746.375 | 2020-01-01 | 2020-12-31 | 2020-10-08 | 2020-10-09
20026989100 | PM INSTALL REG PMF (FAC ONLY) | - | - | - | - | 0.004467% | 2795.05 | 0 | 2795.05 | 2020-01-01 | 2020-12-31 |  | 2020-12-05 | THIS JOB WAS CREATED AND USED ONLY FOR FACILITY CREATION ALL WORK WAS PERFORMED ON 583 JOB ORDER 19-0269155-00 CFARIS
20026944100 | INSTALL 1150'-2" PMMP | - | - | - | - | 0.2879% | 180126.1 | 197605.192 | -17479.092 | 2020-01-01 | 2020-12-31 | 2020-08-20 | 2020-10-13
20026951100 | INSTALL 550' OF 2"PMMP MAIN | - | - | - | - | 0.05676% | 35511.21 | 46540.7015 | -11029.4915 | 2020-01-01 | 2020-12-31 | 2020-10-02 | 2020-10-14
18026819700 | INST. FN 350 EXTRA LP OPP | - | - | - | - | 0.0681% | 42610.31 | 40148.1646 | 2462.1454 | 2020-01-01 | 2020-12-31 | 2020-08-24 | 2021-01-29 | ACTUAL DATE 04/13/2020 04/16/2020 ENTERED BY MISTAKE INTO COMPUTER NEAL JOHNSON GCCC TICKET NOT REQUIRED OFF SITE NOT AT ANY STATION WORKING ON LP PAPERWORK CFARIS 1/28/21 REGULATORS INSTALLED BY CYTHIA FARIS AND JAMES PASLEY ON 10/14/20 ER350 INSTALLED BY CHRIS COX ON 10/21/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/20 GCCC TICKET NOT REQUIRED ON 1/29/20 NOT AT STATION COMPLETING PAPERWORK
20026958301 | INSTALL 720'-6" PMLP | - | - | - | - | 0.4892% | 306076.63 | 282646.1716 | 23430.4584 | 2020-01-01 | 2020-12-31 | 2020-09-18 | 2020-12-18
20026983100 | INSTALL 10' OF 3"PMMP MAIN | - | - | - | - | 0.006304% | 3944.31 | 4601.6704 | -657.3604 | 2020-01-01 | 2020-12-31 | 2020-12-23 | 2020-10-20
18026801100 | INST. FN 49 EXTRA LP OPP | - | - | - | - | 0.06296% | 39390.89 | 41778.1646 | -2387.2746 | 2020-01-01 | 2020-12-31 | 2020-09-04 | 2021-01-29 | REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 10/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/2020 GCCC TICKET NOT REQUIRED ON 1/29/20 NOT AT STATION OFF SITE COMPETING PAPERWORK
20026980800 | INSTALL 50'-2" PMMP | - | - | - | - | 0.00941% | 5887.25 | 13229.5604 | -7342.3104 | 2020-01-01 | 2020-12-31 | 2020-10-19 | 2020-10-22
20026966300 | INSTALL 200'-2" PMMP | - | - | - | - | 0.04343% | 27172.24 | 29254.458 | -2082.218 | 2020-01-01 | 2020-12-31 | 2020-10-19 | 2020-10-28
20026959100 | INSTALL 200'-2" PMMP | - | - | - | - | 0.04379% | 27395.73 | 41735.7329 | -14340.0029 | 2020-01-01 | 2020-12-31 | 2020-10-19 | 2020-12-18
20026963300 | INSTALL 30' OF 4"PMMP MAIN | - | - | - | - | 0.05882% | 36804.73 | 43056.4342 | -6251.7042 | 2020-01-01 | 2020-12-31 | 2020-10-21 | 2020-10-30
19026888700 | INSTALL NEW GMB SETTING | - | - | - | - | 0.1031% | 64525.44 | 83475.5624 | -18950.1224 | 2020-01-01 | 2020-12-31 | 2020-05-12 | 2020-11-18 | TAPED AND PIPE DOPED FITTINGS TO BE READY FOR INSTALL. WAITING ON CUSTOMER TO INSTALL HOUSE LINE
20026925801 | INSTALL 6,500' - 2"/6" PMMP | - | - | - | - | 2.27% | 1420295.35 | 1499015.1136 | -78719.7636 | 2020-01-01 | 2020-12-31 | 2020-07-21 | 2020-12-16 | JOB ORDER CODED COMPLETE IN ERROR. SCHEDULED COMPLETION DATE WILL BE END OF NOVEMBER 2020. SPENDLE PER COORDINATOR 10/5/20
19026874900 | INSTALL 4500' OF 2"PMMP MAIN | - | - | - | - | 0.8996% | 562873 | 756708.0009 | -193835.0009 | 2020-01-01 | 2020-12-31 | 2020-06-29 | 2020-11-04
18026823000 | INST. FN 163 EXTRA LP OPP | - | - | - | - | 0.08166% | 51093.24 | 23889.1646 | 27204.0754 | 2020-01-01 | 2020-12-31 | 2020-07-15 | 2021-04-30 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/4/2020 PAPERWROK COMPLETED BY CYNTHIA FARIS ON 4/30/2021 GCCC TICKET NOT REQUIRED ON 4/30/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026893600 | INSTALL 6132'-2" PMMP/2" CSMP | - | - | - | - | 1.119% | 700039.08 | 887844.9551 | -187805.8751 | 2020-01-01 | 2020-12-31 | 2020-09-10 | 2020-11-25
20026954200 | INSTALL 825' OF 4" PMMP MAIN | - | - | - | - | 0.1354% | 84698.91 | 96092.6837 | -11393.7737 | 2020-01-01 | 2020-12-31 | 2020-10-05 | 2020-11-04
18026804200 | INST. FN 82 EXTRA LP OPP | - | - | - | - | 0.04026% | 25188.67 | 23795.1646 | 1393.5054 | 2020-01-01 | 2020-12-31 | 2020-08-24 | 2021-02-23 | GCCC# 11659 REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/23/2021 GCCC TICKET NOT REQUIRED ON 2/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026805400 | INST. FN 89 EXTRA LP OPP | - | - | - | - | 0.03741% | 23408.39 | 23795.1646 | -386.7746 | 2020-01-01 | 2020-12-31 | 2020-08-24 | 2021-05-17 | REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/9/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026985900 | INSTALL 5'-4" PMLP DIG IN | - | - | - | - | 0.00261% | 1632.83 | 5898.0652 | -4265.2352 | 2020-01-01 | 2020-12-31 | 2020-11-09 | 2021-01-08
18026804700 | INST. FN 13493 EXTRA LP OPP | - | - | - | - | 0.05056% | 31634.76 | 40101.1646 | -8466.4046 | 2020-01-01 | 2020-12-31 | 2020-09-04 | 2021-05-17 | GCCC# 11422 REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026916900 | INSTALL 2960' 2" PMMP | - | - | - | - | 0.1149% | 71866.74 | 72637.757 | -771.017 | 2020-01-01 | 2020-12-31 | 2020-10-16 | 2020-11-12
20026986200 | INSTALL 5'-6" PMMP | - | - | - | - | 0.0005275% | 330.04 | 11648.0607 | -11318.0207 | 2020-01-01 | 2020-12-31 | 2020-11-12 | 2020-11-11
20026971300 | INSTALL 1900' OF 2"PMMP MAIN | - | - | - | - | 0.1081% | 67618.93 | 60260.4679 | 7358.4621 | 2020-01-01 | 2020-12-31 | 2020-11-28 | 2020-11-12
20026986700 | INSTALL 5' - 4" PMLP MAIN | - | - | - | - | 0.001026% | 642.11 | 4734.5045 | -4092.3945 | 2020-01-01 | 2020-12-31 | 2020-12-17 | 2020-12-17 | INSTALLED 5' OF 4" PL TO REPAIR DAMAGE BY CITY OF ASHLAND SEWER TESTED 90 P SIG 1 HR SOAP TESTED FINAL CONN OP 8" WC
18026806800 | INST. FN 114 EXTRA LP OPP | - | - | - | - | 0.06871% | 42987.89 | 43910.1646 | -922.2746 | 2020-01-01 | 2020-12-31 | 2020-08-06 | 2021-05-18 | ESPARKS 11-18-20 REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 11/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026930200 | UPGRADE ELECTRONICS | - | - | - | - | 0.00998% | 6244.14 | 3038 | 3206.14 | 2020-01-01 | 2020-12-31 | 2020-11-10 | 2020-11-17 | CHANGED METER AND REPLACED EFC
20026987200 | EMER-INSTALL 8' OF 2"PMMP MAIN | - | - | - | - | 0.004822% | 3016.93 | 4618.1073 | -1601.1773 | 2020-01-01 | 2020-12-31 | 2020-11-17 | 2020-11-18 | ABANDONED SECTION OF MAIN-LEFT BYPASS AS NEW MAIN PER ENGINEERING AND TIE IN PLAN-BHBNGF-ALL READINGS GONE-COMPLETED JOB TO TIE IN PLAN-PRESS. TEST NEW MAIN @90LBS FOR 1HR SEE TESTPRESS. FORM-13PSI VERIFIED-ANICHOLS11-17-20
17026726500 | INSTALL 922' 6"-PHHP | - | - | - | - | 0.2372% | 148437.9 | 180053.1311 | -31615.2311 | 2020-01-01 | 2020-12-31 | 2020-10-12 | 2020-12-01
20026924001 | INSTALL 165'-4" CSHP | - | - | - | - | 0.1334% | 83463.69 | 67409.6919 | 16053.9981 | 2020-01-01 | 2020-12-31 | 2020-09-28 | 2020-11-20
18026814900 | INST. FN 129 EXTRA LP OPP | - | - | - | - | 0.06485% | 40576.58 | 24062.1646 | 16514.4154 | 2020-01-01 | 2020-12-31 | 2020-02-10 | 2021-02-25 | REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 11/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026804500 | INST. FN 84 EXTRA LP OPP | - | - | - | - | 0.03586% | 22435.72 | 23795.1646 | -1359.4446 | 2020-01-01 | 2020-12-31 | 2020-11-24 | 2021-02-22 | REGULATORS REPLACED AND ER350 INSTALLED BY CHRIS COX ON 11/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/22/2021 GCCC TICKET NOT REQUIRED ON 2/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026927800 | UPGRADE ELECTRONICS | - | - | - | - | 0.01024% | 6404.17 | 3038 | 3366.17 | 2020-01-01 | 2020-12-31 | 2020-11-25 | 2021-01-08 | EFC REPLACED BY CHRIS COX AND JIM PASLEY PAPERWORK COMPLETED BY CYNTHIA FARIS JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK
20026950800 | INSTALL WOOD FENCE | - | - | - | - | 0.006916% | 4327.44 | 9731.8452 | -5404.4052 | 2020-01-01 | 2020-12-31 | 2020-11-18 | 2020-11-30 | MONITORED FENCE INSTALL - ESPARKS 11-24-20 GCCC REF# 3641 ESPARKS 11-30-20 JOB ON HOLD DUE TO COVID19
20026924201 | INSTALL 2000'-6" PMMP | - | - | - | - | 1.783% | 1115631.15 | 975569.1751 | 140061.9749 | 2020-01-01 | 2020-12-31 | 2020-09-17 | 2020-12-29
20026924600 | INSTAL REGULATOR STATION | - | - | - | - | 0.1818% | 113750.17 | 149467.4285 | -35717.2585 | 2020-01-01 | 2020-12-31 | 2020-08-12 | 2020-12-30 | ESPARKS 11-19-20 CCC#3481 11-23-20 0920 APARKS INSTALL NEW REG STATION, RUN1 CONTROL @ 29#, MONITOR @ 34#, RUN 2 CONTROL @ 27#, MONITOR @ 34#, INLET @ 136#, PRV @ 35# SOAP TEST AT 2:15PM, INSPECTED SEAT TO SEAT, INLET OUTLET AND CONTROL LINES ON TO BOTH RUNS, NO BYPASS, MONITORED 30 MIN CMCHOLAN 12-2-2020 STATION PLACED IN SERVICE BY SHAUN MCHOLAN PAPERWORK COMPLETED BY CYNTHIA FARIS
20026986500 | INSTALL FENCE AT R-1143 | - | - | - | - | 0.01976% | 12363.62 | 7073.5793 | 5290.0407 | 2020-01-01 | 2020-12-31 | 2020-12-02 | 2020-12-30
20026989300 | EMRG - INSTALL 5'-4"PMLP MAIN | - | - | - | - | 0.004728% | 2958.08 | 5551.8207 | -2593.7407 | 2020-01-01 | 2020-12-31 | 2020-12-02 | 2020-12-08 | INSTALLED END CAPS ON 3 TEE'S. SOAP TEST CAPS AT OP. TEST OK. BHB NGF. CHARGE TIME FROM 2412 TO 557 AND 558. KKINDER INSTALLED 2 VERFICATION GAUGES.SQUEEZED OFF 2 WAY FED MAIN IN SEPRATE BELLHOLES. REPLACED DAMAGED SECTION OF PIPE. SOAP TEST 2 EFC'S AT OP TEST OK.PURGED OUT MAIN WITH PURGE STACK CONNECTED TO PURGE TEE ON MAIN.
20026964301 | OBTAIN EASEMENTS FOR HP MAIN | - | - | - | - | 0.5842% | 365491.68 | 250078 | 115413.68 | 2020-01-01 | 2020-12-31 | 2020-12-07 | 2020-12-07
20026989900 | EMRG - INSTALL 5'-2"PMMP MAIN | - | - | - | - | 0.004177% | 2613.3 | 4780.1273 | -2166.8273 | 2020-01-01 | 2020-12-31 | 2020-12-08 | 2020-12-08 | STACK. SOAP TEST EFC AT OP.TEST OK. SOAP TEST END CAP ON TEE AT OP. TEST OK. BHB NGF. ABOVE GROUND SQUEEZED OFF TO MAKE SAFE.INSTALLED VERFICATION GAUGE.TESTED TEE FOR 5MINS AT 90LBS.TEST OK. REPLACED 2' OF 020 DAMAGED MAIN.TESTED 020 PIPE FOR 20MINS AT 90LBS.TEST OK.PURGED MAIN AT EOM 112' AWAY WITH PURGE
18026804800 | INST. FN 86 EXTRA LP OPP | - | - | - | - | 0.09741% | 60948.24 | 43801.1646 | 17147.0754 | 2020-01-01 | 2020-12-31 | 2020-06-22 | 2021-05-12 | PAID FRIDAY 05/22/20 ON THURSDAY 05/21/20 REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 12/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026811200 | INST. FN 311 EXTRA LP OPP | - | - | - | - | 0.04685% | 29313.81 | 38500.1646 | -9186.3546 | 2020-01-01 | 2020-12-31 | 2020-02-05 | 2021-05-12 | REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 12/9/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026966701 | INSTALL 3740' OF 2/4"PMMP MAIN | - | - | - | - | 0.604% | 377921.86 | 367967.1067 | 9954.7533 | 2020-01-01 | 2020-12-31 | 2020-10-14 | 2021-02-04
18026819900 | INST. FN 351 EXTRA LP OPP | - | - | - | - | 0.04762% | 29797.04 | 21708.8722 | 8088.1678 | 2020-01-01 | 2020-12-31 | 2019-09-09 | 2021-04-27 | REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 12/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026826600 | INST. FN 357 EXTRA LP OPP | - | - | - | - | 0.06796% | 42518.46 | 24062.1646 | 18456.2954 | 2020-01-01 | 2020-12-31 | 2020-08-27 | 2021-04-14 | ESPARKS 12-14-20 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 09/02/2020 REGULATOR REPLACED AND ER350 INSTALLED BY CHRIS COX ON 12/14/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026969500 | INSTALL 680' OF 4"PMMP MAIN | - | - | - | - | 0.08494% | 53143.47 | 52475.5703 | 667.8997 | 2020-01-01 | 2020-12-31 | 2020-11-30 | 2020-12-14
17026735602 | INSTALL 3486'-6" PMIP | - | - | - | - | 0.8928% | 558619.72 | 400560.0388 | 158059.6812 | 2020-01-01 | 2020-12-31 | 2020-08-26 | 2021-03-30
18026808000 | INST. FN 212 EXTRA LP OPP | - | - | - | - | 0.08845% | 55338.78 | 24102.8722 | 31235.9078 | 2020-01-01 | 2020-12-31 | 2019-08-01 | 2021-05-12 | ESPARKS 12-16-20 REGULATOR INSTALLED BY CHRIS COX ON 12/16/2020 ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026911400 | INSTALL NEW RECTIFIER | - | - | - | - | 0.01503% | 9404.7 | 10181.0696 | -776.3696 | 2020-01-01 | 2020-12-31 |  | 2020-12-21
20026981900 | INSTALL 170'-2" PMMP | - | - | - | - | 0.01461% | 9138.12 | 14695.1167 | -5556.9967 | 2020-01-01 | 2020-12-31 | 2020-12-18 | 2020-12-22 | OPEN CUT MAIN TO METER. VERIFIED CONTENT AND PRESSURE.
18026791102 | INSTALL 2,700' - 8" PHHP | - | - | - | - | 1.232% | 770651.16 | 623910.1849 | 146740.9751 | 2020-01-01 | 2020-12-31 | 2020-09-24 | 2020-12-28 | 7173
20026992700 | EMER-INSTALL 5'-4" PMMP | - | - | - | - | 0.004539% | 2839.86 | 12865.6489 | -10025.7889 | 2020-01-01 | 2020-12-31 |  | 2021-01-04 | IDENTIFIED A LEAKING BUTT WELD ON MAIN LINE. REPLACED SECTION OF MAIN LINE THAT WAS LEAKING WITH A NEW PEICE OF MAIN. PRESSURE TESTED NEW PEICE OF MAIN @ 90PSIG FOR 1HR. TEST OK. BHB, NGF. VERIFIED CONTENT & PRESSURE
20026992300 | EMRG - INSTALL 5' OF 3"PMMP | - | - | - | - | 0.05065% | 31687.89 | 38582.9134 | -6895.0234 | 2020-01-01 | 2020-12-31 | 2020-12-28 | 2020-12-28 | EXPOSED LEAKING PAC CLAMP OVER OLD SVC TEE. CUT OUT REPLACED 7.75' OF 3" P MP MAIN PER GAS STANDARDS AND TIE-IN PLAN. BHB NGF. MCRAIG 12/28/20
19026912100 | INSTALL NEW RECTIFIER | - | - | - | - | 0.01065% | 6662.91 | 10181.0696 | -3518.1596 |  | 2020-12-31 |  | 2020-12-28
|  | - | - | - | - |  | 2020 Construction Project Budget | 62567000