## Sheet1
KY PSC Case No. 2021-00183
Staff 1-25
Schedule I2
Columbia Gas of Kentucky
Case No. 2021-00183
Calculation of Capital Construction Project Slippage Factor
Source: | Schedule I1 - Construction Projects
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percentage | Slippage Factor
2016 | 27024000 | 27947000 | -923000 | -3.303% | 0.96697
2017 | 34934000 | 34617000 | 317000 | 0.9157% | 1.0092
2018 | 43102000 | 43174000 | -72000 | -0.1668% | 0.99833
2019 | 53837000 | 52293000 | 1544000 | 2.953% | 1.0295
2020 | 64965000 | 62567000 | 2398000 | 3.833% | 1.0383
Totals | 223862000 | 220598000 | 3264000 | 1.48%
5 Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 5 years) |  |  |  |  | 1.0085
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule I1. Total all projects for a given year.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor for each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.