## Forecast Test Period
Year 2021
Plant | Project Description | Project Amount Without AFDUC | AFUDC | Project Amount With AFDUC | Inception-to-Date Without AFDUC | AFDUC | Inception-to-Date With AFDUC | Actual Start Date | Expected Start Date | Expected Completion Date
| Nicholasville Aldyl-A PRP | 1604169 | 0 | 1604169 | 340775.46 | 0 | 340775.46 | 2021-04-01 |  | 2021-08-31
| Corbin Aldyl-A PRP | 1046556 | 0 | 1046556 | 421522.09 | 0 | 421522.09 | 2021-04-01 |  | 2021-07-31
| Berea Aldyl-A PRP | 2399859 | 0 | 2399859 | n/a | 0 | n/a |  | 2021-06-01 | 2021-12-31
| Lincoln Co. EDX | 3746240 | 0 | 3746240 | n/a | 0 | n/a |  | 2021-06-01 | 2021-12-31
| All Other Projects < 5% | 9711476 | 0 | 9711476 | 2335419.01 | 0 | 2335419.01
Total |  | 18508300 |  | 18508300
Year 2022
Plant | Project Description | Project Amount Without AFDUC | AFUDC | Project Amount With AFDUC | Inception-to-Date Without AFDUC | AFDUC | Inception-to-Date With AFDUC | Actual Start Date | Expected Start Date | Expected Completion Date
| Farmers/Midland Aldyl-A PRP | 1835379 | 0 | 1835379 | n/a | 0 | n/a |  | 2022-04-01 | 2022-08-31
| Mt. Olivet Aldyl-A PRP | 2176020 | 0 | 2176020 | n/a | 0 | n/a |  | 2022-09-01 | 2022-12-31
| Croley Bend PRP Transmission | 1654300 | 0 | 1654300 | n/a | 0 | n/a |  | 2022-05-01 | 2022-07-31
| Nicholasville Pipeline Right-of-Way | 1750299 | 0 | 1750299 | n/a | 0 | n/a |  | 2022-01-01 | 2022-12-31
| All Other Projects < 5% | 10167804 | 0 | 10167804 | n/a | 0 | n/a
Total |  | 17583802 |  | 17583802
Year 2023
Plant | Project Description | Project Amount Without AFDUC | AFUDC | Project Amount With AFDUC | Inception-to-Date Without AFDUC | AFDUC | Inception-to-Date With AFDUC | Actual Start Date | Expected Start Date | Expected Completion Date
| Renfro Valley Right-of-Way (22 Miles) | 1500000 | 0 | 1500000 | n/a | 0 | n/a |  | 2023-01-01 | 2023-12-31
| Nicholasville Pipeline | 13000000 | 0 | 13000000 | n/a | 0 | n/a |  | 2023-04-01 | 2023-12-31
| All Other Projects < 5% | 19000000 | 0 | 19000000 | n/a | 0 | n/a
Total |  | 33500000 |  | 33500000
Year 2024
Plant | Project Description | Project Amount Without AFDUC | AFUDC | Project Amount With AFDUC | Inception-to-Date Without AFDUC | AFDUC | Inception-to-Date With AFDUC | Actual Start Date | Expected Start Date | Expected Completion Date
| Renfro Valley Pipeline | 13000000 | 0 | 13000000 | n/a | 0 | n/a |  | 2024-04-01 | 2024-12-31
| All Other Projects < 5% | 17500000 | 0 | 17500000 | n/a | 0 | n/a
Total |  | 30500000 | 0 | 30500000 | n/a | 0 | n/a