## August 31 2020
Schedule G
Delta Natural Gas Company, Inc
Case No. 2021-00185
Construction Projects
As of August 31, 2020
Delta -1600 |  |  | Accumulated Costs
Line |  |  | Construction | AFUDC | Indirect Costs |  | Estimated
No. | Project No. | Description of Project | Amount | Capitalized | Other | Total Cost | Physical Percent |  | Cost to date
( A ) | ( B ) | ( C ) | ( D ) | ( E ) | ( F ) | (G=D+E+F) | Completed | Order # | as of 4/30/2021
1 | 501.19.016.1 | REP-6700 FT PL MAIN IN MIDLAND | 25696.62 | 0 | 0 | 25696.62 | 5.683% | 10064680 | 452182.79
2 | 501.20.014.1 | REPLACE Aldyl-A PIPE US Hwy 60 | 51418.06 | 0 | 0 | 51418.06 | 10% | 10076478 | 51509.58
3 | 501.20.015.1 | REPLACE Aldyl-A MAIN HWY 60 | 66537.67 | 0 | 0 | 66537.67 | 10% | 10076479 | 68009.69
4 | 501.20.017.1 | INS LVM TRANSM FARMERS PURCH S | 578671.06 | 0 | 0 | 578671.06 | 89.92% | 10077101 | 643539.52
5 | 501.20.020.1 | INS LVM APPHARVEST GH ROWAN CO | 50846.29 | 0 | 0 | 50846.29 | 70.72% | 10077579 | 71902.04
6 | 502.19.019.1 | REP-2" ML PL ALONG MULTI LOCAT | 424725.59 | 0 | 0 | 424725.59 | 72.94% | 10065862 | 582256.23
7 | 502.19.031.1 | REP ALDYL PIPE BEREA CITY LIMI | 100939 | 0 | 0 | 100939 | 10% | 10071160 | 100939
8 | 502.19.032.1 | REP IPE BEREA CITY LIMITS E HA | 20285.04 | 0 | 0 | 20285.04 | 10% | 10071161 | 20285.04
9 | 502.20.012.1 | INSTALL METER SET BLDG(CLA) AT | 582.28 | 0 | 0 | 582.28 | 6.88% | 10075619 | 8462.76
10 | 503.19.019.1 | REP 26300' PIPE AT MULTIPLE LO | 49846.58 | 0 | 0 | 49846.58 | 10% | 10068784 | 236411.37
11 | 505.19.008.1 | 19STAT-REP 4483 FT KYTC RD PRO | 59662.05 | 0 | 0 | 59662.05 | 5% | 10067751 | 65170.5
12 | 505.19.010.1 | REL ALONG KY 231 STATE HWY PRO | 2309.92 | 0 | 0 | 2309.92 | 0.754% | 10068601 | 306370.63
13 | 506.19.004.1 | 19LOND-REP BS PIPE S DIXIE ST | 9684.96 | 0 | 0 | 9684.96 | 10% | 10064089 | 9684.96
14 | 506.20.007.1 | REP METERSET 804 W 5TH ST | 2196.85 | 0 | 0 | 2196.85 | 73.88% | 10080271 | 2973.45
15 | 510.19.010.1 | REP BS WITH PL PIPE PVILLE CIT | 12600.17 | 0 | 0 | 12600.17 | 8.621% | 10064923 | 146158.57
16 | 510.19.011.1 | REP BS WITH PL PIPE IN BELL CO | 15869.53 | 0 | 0 | 15869.53 | 4.365% | 10064922 | 363558.42
17 | 510.19.017.1 | REP BS SEVERAL LOCATIONS | 85733.64 | 0 | 0 | 85733.64 | 10% | 10072731 | 85733.64
18 | 511.19.022.1 | BILL-REL MAIN 25E PROJECT HWY | 673253.04 | 0 | 0 | 673253.04 | 70.37% | 10066731 | 956690.8
19 | 511.19.025.1 | REP 2" PL 1185 S HWY 1223 | 5821.23 | 0 | 0 | 5821.23 | 100% | 10069798 | 5821.23
20 | 511.20.010.1 | REP ML VARIOUS LOC CORBIN CITY | 111772.71 | 0 | 0 | 111772.71 | 29.48% | 10077450 | 379204.49
21 | 511.20.017.1 | REP 3/4" 1" 2" MAINS VARIOS LO | 984.4 | 0 | 0 | 984.4 | 0.3295% | 10079616 | 298749.08
22 | 512.20.004.1 | REPLACE 4" PLASTIC ALONG KY 63 | 3544.45 | 0 | 0 | 3544.45 | 18% | 10075719 | 19688.33
23 | 512.20.007.1 | REPLAC ALDYL-A MAIN BURNING SP | 57946.16 | 0 | 0 | 57946.16 | 5% | 10076533 | 57946.16
24 | 525.19.006.1 | REP- COATED STEEL TYNER JACKSO | 94233.06 | 0 | 0 | 94233.06 | 100% | 10063990 | 0 | 94233.06 was reimbursed expense from the state of kentucky for hwy project
25 | 525.19.017.1 | REP KY 11 LEE COUNTY HWY 4" ST | 1143.45 | 0 | 0 | 1143.45 | 5% | 10067752 | 1258.36
26 | 525.19.031.1 | REP 6" CS TL 108 MEADOWLARK DR | 1223.26 | 0 | 0 | 1223.26 | 100% | 10071522 | 1223.26
27 | 525.20.014.1 | EXT 6" CS FOR APP HARVEST-I | 896.79 | 0 | 0 | 896.79 | 1.582% | 10077712 | 56678.99
28 | 526.19.005.1 | 19MIDD-REP CRANK & ROD CAN MTN | 12563.93 | 0 | 0 | 12563.93 | 100% | 10072764 | 12563.93
29 | D9525.MISCMTRMAT | DELTA MISC METER MATERIAL | 42954.99 | 0 | 0 | 42954.99 | NA | NA
30 | DELTAOH.CONS | DELTA OVERHEAD - CONSTRUCTION | 148493.14 | 0 | 0 | 148493.14 | NA | NA
31 | SW.DELT.CPMS.PH4.2 | SW CPMS PH4 - IN HOUSE | 28349.76 | 0 | 0 | 28349.76 | 64.98% | NA | 43626.02
32 | SW.DELT.HANA.UPGRD.2 | SW BW HANA UPGRADE - IN HOUSE | 429.02 | 0 | 0 | 429.02 | 98.25% | NA | 436.68 | Small amt - Double checked - ok - KE
33 | SW.DELT.SAP.20.LICEN.3 | SW SAP 2020 LICENSES - PURCHAS | 17946.65 | 0 | 0 | 17946.65 | 100% | NA | 17946.65
34 | SW.DELT.WFO.PH5.2 | SW WORKFORCE OPT PH5 - IN HOUS | 42008.39 | 0 | 0 | 42008.39 | 71.29% | NA | 58928.48
35 | SW.DELTA.CRB.2 | SW.DELTA.CRB.2 IN-HOUSE | 3016082.27 | 0 | 0 | 3016082.27 | 74% | NA | 3969638.24 | Also in CWIP at 4/30/2021
36 | SW.DELTA.MITEL.MIGRTN.3 | SW MITEL PHONE MIGTATION - PUR | 2951.02 | 0 | 0 | 2951.02 | 21.96% | NA | 13437.39
37 | SW.DELTA.PERCEP.UPGRD.2 | SW PERCEPTIVE UPGRADE - IN HOU | 2709.6 | 0 | 0 | 2709.6 | 100% | NA | 2709.6
38 | SW.DELTA.PERCEP.UPGRD.3 | SW PERCEPTIVE UPGRADE - PURCHA | 4409.53 | 0 | 0 | 4409.53 | 100% | NA | 4409.53
39 | SW.SIP.DELT.EAM.REDSGN.2 | SW EAM REDESIGN - IN HOUSE | 76384.23 | 0 | 0 | 76384.23 | 42% | NA | 183220.88 | Also in CWIP at 4/30/2021
40 | SW.SIP.DELT.WORKDAY.2 | SW WORKDAY IMPLEMENT - IN HOUS | 31.99 | 0 | 0 | 31.99 | 0% | NA | 31.99 | Also in CWIP at 4/30/2021
NA
TOTAL |  |  | 5903738.38 | 0 | 0 | 5903738.38 |  | NA
NA
NA
PKYC - 1300 |  |  | Accumulated Costs |  |  |  |  | NA
NA
Line |  |  | Construction | AFUDC | Indirect Costs |  | Estimated | NA
No. | Project No. | Description of Project | Amount | Capitalized | Other | Total Cost | Physical Percent | NA
( A ) | ( B ) | ( C ) | ( D ) | ( E ) | ( F ) * | (G=D+E+F) | Completed** | NA
41 | SW.PKYC.CRM.PH1.2 | SW CRM REPLACE PH1 - IN HOUSE | 45504.11 | 2134.59 | 0 | 47638.7 | 70% | NA | 50109.32
42 | SW.PKYC.DELINQ.CUST.2 | SW DELINQUENT CUST MODEL - IN | 813.72 | 12.36 | 0 | 826.08 | 99.25% | NA | 832.31
43 | SW.PKYC.HANA.UPGRD.2 | SW BW HANA UPGRADE - IN HOUSE | 35.93 | 0.18 | 0 | 36.11 | 97.78% | NA | 36.93
44 | SW.PKYC.OQRMS.2 | SW OPER QUALIFICATION - IN HOU | 330.94 | 0 | 0 | 330.94 | 50% | NA | 580.02
45 | SW.PKYC.PERCEP.UPGRD.2 | SW PERCEPTIVE UPGRADE - IN HOU | 228.75 | 2.94 | 0 | 231.69 | 99.02% | NA | 233.98
46 | SW.PKYC.PERCEP.UPGRD.3 | SW PERCEPTIVE UPGRADE - PURCHA | 371.25 | 3.79 | 0 | 375.04 | 98.76% | NA | 379.73
47 | SW.PKYC.SAP.20.LICEN.3 | SW SAP 2020 LICENSES - PURCHAS | 1499.52 | 3.96 | 0 | 1503.48 | 99.26% | NA | 1514.74
48 | SW.PKYC.WFO.PH5.2 | SW WORKFORCE OPT PH5 - IN HOUS | 3528.4 | 27.69 | 0 | 3556.09 | 71.41% | NA | 4979.78
49 | SW.SIP.PKYC.WORKDAY.2 | SW WORKDAY IMPLEMENT - IN HOUS | 2.67 | 0.01 | 0 | 2.68 | 0.1766% | NA | 1517.5
TOTAL |  |  | 52315.29 | 2185.52 | 0 | 54500.81
Note on K11: Kathy Estes: Used to calculate column H for project completed at 2021. For projects still in progress at Aug 2021, Eng updated percent
Note on C40: Kathy Estes: Blanket WBS - never ciompletes - cost fluctuates - cleared Qtr to Acct 382
Note on H40: Kathy Estes: Blanket - never completes
Note on C41: Kathy Estes: Blanket WBS for surcharges - never completes - cost fluctuates
Note on H41: Kathy Estes: Blanket - never completes
Note on K42: Kathy Estes: Used to calculate column H for software completed at 2021. For projects still in progress at Aug 2021, Barry L updated percent
Note on H46: Kathy Estes: Barry L reviewed
Note on H50: Kathy Estes: Reviewed by Barry L
Note on H51: Kathy Estes: Reviewed by Barry L
Note on H61: Kathy Estes: Reviewed by BL
Note on H62: Kathy Estes: Reviewed by BL
Note on H64: Kathy Estes: reviewed by BL

## August 31 2021
Schedule G
Delta Natural Gas Company, Inc
Case No. 2021-00185
Construction Projects
As of August 31, 2021
Delta -1600 |  |  | Accumulated Costs
Line |  |  | Construction | AFUDC | Indirect Costs |  | Estimated
No. | Project No. | Description of Project | Amount | Capitalized | Other | Total Cost | Physical Percent | Order
( A ) | ( B ) | ( C ) | ( D ) | ( E ) | ( F ) | (G=D+E+F) | Completed | Number
1 | 501.20.014.1 | REPLACE Aldyl-A PIPE US Hwy 60 | 51509.58 | 0 | 0 | 51509.58 | 10% | 10076478
2 | 501.20.015.1 | REPLACE Aldyl-A MAIN HWY 60 | 68009.96 | 0 | 0 | 68009.96 | 10% | 10076479
3 | 501.20.021.1 | REP MAIN VARIOUS RD CAMARGO | 45168.25 | 0 | 0 | 45168.25 | 5% | 10078537
4 | 502.19.031.1 | REP ALDYL PIPE BEREA CITY LIMI | 280939 | 0 | 0 | 280939 | 10% | 10071160
5 | 502.19.032.1 | REP IPE BEREA CITY LIMITS E HA | 207155.04 | 0 | 0 | 207155.04 | 50% | 10071161
6 | 503.19.019.1 | REP 26300' PIPE AT MULTIPLE LO | 1210000 | 0 | 0 | 1210000 | 95% | 10068784
7 | 505.19.008.1 | 19STAT-REP 4483 FT KYTC RD PRO | 65170.5 | 0 | 0 | 65170.5 | 10% | 10067751
8 | 506.19.004.1 | 19LOND-REP BS PIPE S DIXIE ST | 9684.96 | 0 | 0 | 9684.96 | 10% | 10064089
9 | 506.21.001.1 | REP KY 129 and HWY 229 | 80000 | 0 | 0 | 80000 | 5% | 10087958
10 | 506.21.005.1 | REP KY 192 5th Street Portion | 19000 | 0 | 0 | 19000 | 5%
11 | 507.20.004.1 | REP 2" PE MAIN ON SILER ST | 942.16 | 0 | 0 | 942.16 | 10% | 10081499
12 | 507.21.001.1 | REP 2" CS PENNY LN & KY 296 | 1542.97 | 0 | 0 | 1542.97 | 10% | 10090043
13 | 510.19.017.1 | REP BS SEVERAL LOCATIONS | 85733.64 | 0 | 0 | 85733.64 | 10% | 10072731
14 | 510.21.005.1 | REP DOWNSTREAM PIPE KI PINEVIL | 121.92 | 0 | 0 | 121.92 | 5% | 10089720
15 | 511.21.001.1 | REP PIPE LAUREL COUNTY CORB | 60.66 | 0 | 0 | 60.66 | 5% | 10086602
16 | 511.21.002.1 | REP 8" CS ELLISON STREET | 60.66 | 0 | 0 | 60.66 | 5% | 10086603
17 | 512.20.007.1 | REPLAC ALDYL-A MAIN BURNING SP | 57946.16 | 0 | 0 | 57946.16 | 5% | 10076533
18 | 525.19.017.1 | REP KY 11 LEE COUNTY HWY 4" ST | 1258.36 | 0 | 0 | 1258.36 | 10% | 10067752
19 | 526.19.005.1 | 19MIDD-REP CRANK & ROD CAN MTN | 14483.93 | 0 | 0 | 14483.93 | 95% | 10072764
20 | 525.21.004.1 | Croley Bend Transmission Line Replcmt | 5121.33 | 0 | 0 | 5121.33 | 2%
21 | 501.21.004.1 | Rep Main City Mt Olivet | 17333 | 0 | 0 | 17333 | 10% | 10091542
22 | 501.21.005.1 | Rep Main Hwy 62 Sardis | 17333 | 0 | 0 | 17333 | 10% | 10091544
23 | 501.21.006.1 | Rep a main thru Hwy 62 to Sardis | 17334 | 0 | 0 | 17334 | 10% | 10091546
24 | 525.21.021.1 | 21BEREA-INS-M&R STATION LINCOLN CO | 2574600 | 0 | 0 | 2574600 | 10%
25 | 525.21.022.1 | 21BEREA-INS-8" TRANS LINE LINCOLN CO | 249612 | 0 | 0 | 249612 | 20%
26 | D9525.MISCMTRMAT | DELTA MISC METER MATERIAL | 31200 | 0 | 0 | 31200 | NA | NA
27 | DELTAOH.CONS | DELTA OVERHEAD - CONSTRUCTION | 258700 | 0 | 0 | 258700 | NA | NA
28 | DELTAOH.GA | DELTA OVERHEAD - G&A | 250000 | 0 | 0 | 250000 | NA | NA
29 | SW.DELT.CPMS.PH5.2 | SW CPMS PH5 - IN HOUSE | 30000 | 0 | 0 | 30000 | 67% | NA
30 | SW.DELT.DUNNING.2 | SW DUNNING STRATEGY - IN HOUSE | 10000 | 0 | 0 | 10000 | 25% | NA
31 | SW.DELT.WFO.PH6.2 | SW WORKFORCE OPT PH6 - IN HOUS | 40000 | 0 | 0 | 40000 | 67% | NA
32 | SW.SIP.DELT.CONT.MGT.2 | SW SIP CONTRACT MGMT - IN HOUS | 25000 | 0 | 0 | 25000 | 15% | NA
33 | SW.SIP.DELT.PWRPLN.BLD.2 | SW SIP POWERPLAN BUILDOUT - IN | 100000 | 0 | 0 | 100000 | 67% | NA
34 | SW.SIP.DELT.SAP.BPC.2 | SW SIP SAP BPC IMPLEMENT - IN | 25000 | 0 | 0 | 25000 | 50% | NA
35 | SW.SIP.DELT.SRVR.INFRA.3 | SW SIP SERVER INFRASTRUCTURE - | 23090.29 | 0 | 0 | 23090.29 | 75% | NA
36 | SW.SIP.DELT.WORKDAY.2 | SW WORKDAY IMPLEMENT - IN HOUS | 31.99 | 0 | 0 | 31.99 | 0% | NA | 31.99 | Was in CWIP at Aug 31 2020
37 | SW.DELT.SIP.VALMS21.2 | SW SIP VERTICAL ASSET MGMT IMPL | 30000 | 0 | 0 | 30000 | 40% | NA
38 | SW.SIP.DELT.WRKMGT21.2 | SW SIP WORK MANAGEMENT IMPLEMENT | 30000 | 0 | 0 | 30000 | 40% | NA
39 | VENTYX.VERS9.8.2 | SW Ventyx Upgrade | 5000 | 0 | 0 | 5000 | 50% | NA
TOTAL |  |  | 5938143.36 | 0 | 0 | 5938143.36
Note on D12: Kathy Estes: Completed by RN and RM
Note on H12: Kathy Estes: For Constr Projects - completed by RN and RM
Note on B31: Kathy Estes: NA - Project has not been created yet
Note on B37: Kathy Estes: Blanket WBS for meter material - never completes - balance fluctuates - transferred quarterly to Acct 382 meter installations
Note on D37: Kathy Estes: Estimate
Note on H37: Kathy Estes: see note on WBS #
Note on B38: Kathy Estes: Blanket WBS for surcharges - never completes - balance fluctuates
Note on D38: Kathy Estes: estimate
Note on B39: Kathy Estes: Blanket WBS for surcharges - never completes - balance fluctuates
Note on D39: Kathy Estes: estimate
Note on D40: Kathy Estes: Barry Lunch and Joe Brado reviewed and udpated software cost for 8 -31-2021
Note on H40: Kathy Estes: Barry Lunch and Joe Brado reviewed and udpated software % completed for 8 -31-2021

## Dec 31, 2022
Schedule G
Delta Natural Gas Company, Inc
Case No. 2021-00185
Construction Projects
As of December 31, 2022
Delta -1600 |  |  | Accumulated Costs
Line |  |  | Construction | AFUDC | Indirect Costs |  | Estimated
No. | Project No. | Description of Project | Amount | Capitalized | Other | Total Cost | Physical Percent
( A ) | ( B ) | ( C ) | ( D ) | ( E ) | ( F ) | (G=D+E+F) | Completed | Order
1 | 501.20.021.1 | REP MAIN VARIOUS RD CAMARGO (2023) | 45168.25 | 0 | 0 | 45168.25 | 10% | 10078537
2 | 506.19.004.1 | 19LOND-REP BS PIPE S DIXIE ST (2023) | 9684.96 | 0 | 0 | 9684.96 | 10% | 10064089
3 | 511.21.001.1 | REP PIPE LAUREL COUNTY CORB (2023) | 60.66 | 0 | 0 | 60.66 | 10% | 10086602
4 | 511.21.002.1 | REP 8" CS ELLISON STREET (2023) | 60.66 | 0 | 0 | 60.66 | 10% | 10086603
5 | 512.20.007.1 | REPLAC ALDYL-A MAIN BURNING SP (2023) | 57946.16 | 0 | 0 | 57946.16 | 10% | 10076533
6 | N/A | Outside Engineering Services PRP Projects | 400000 | 0 | 0 | 400000 | 10%
7 | N/A | Nicholasville Transmission Line | 1750299 | 0 | 0 | 1750299 | 10%
8 | DELTAOH.CONS | DELTA OVERHEAD - CONSTRUCTION | 80000 | 0 | 0 | 80000 | NA
9 | DELTAOH.GA | DELTA OVERHEAD - G&A | 240000 | 0 | 0 | 240000 | NA
10 | N/A | Computer Software | 393700 | 0 | 0 | 393700 | 40%
11 |  |  |  | 0 | 0 | 0 | 0%
12 |  |  |  | 0 | 0 | 0 | 0%
13 |  |  |  | 0 | 0 | 0 | 0%
14 |  |  |  | 0 | 0 | 0 | 0%
15 |  |  |  | 0 | 0 | 0 | 0%
16 |  |  |  | 0 | 0 | 0 | 0%
17 |  |  |  | 0 | 0 | 0 | 0%
18 |  |  |  | 0 | 0 | 0 | 0%
19 |  |  |  | 0 | 0 | 0 | 0%
20 |  |  |  | 0 | 0 | 0 | 0%
21 |  |  |  | 0 | 0 | 0 | 0%
22 |  |  |  | 0 | 0 | 0 | 0%
23 |  |  |  | 0 | 0 | 0 | 0%
24 |  |  |  | 0 | 0 | 0 | 0%
25 |  |  |  | 0 | 0 | 0 | 0%
26 |  |  |  | 0 | 0 | 0 | 0%
27 |  |  |  | 0 | 0 | 0 | 0%
28 |  |  |  | 0 | 0 | 0 | 0%
29 |  |  |  | 0 | 0 | 0 | 0%
30 |  |  |  | 0 | 0 | 0 | 0%
31 |  |  |  | 0 | 0 | 0 | 0%
32 |  |  |  | 0 | 0 | 0 | 0%
33 |  |  |  | 0 | 0 | 0 | 0%
34 |  |  |  | 0 | 0 | 0 | 0%
35 |  |  |  | 0 | 0 | 0 | 0%
36 |  |  |  | 0 | 0 | 0 | 0%
37 |  |  |  | 0 | 0 | 0 | 0%
38 |  |  |  | 0 | 0 | 0 | 0%
39 |  |  |  | 0 | 0 | 0 | 0%
40 |  |  |  | 0 | 0 | 0 | 0%
41 |  |  |  | 0 | 0 | 0 | 0%
42 |  |  |  | 0 | 0 | 0 | 0%
TOTAL |  |  | 2976919.69 | 0 | 0 | 2976919.69
Note on H15: Kathy Estes: RN and RM reviewed
Note on B20: Kathy Estes: N/A - project has not been created yet
Note on B22: Kathy Estes: Blanket WBS for surcharges - never completes - balance fluctuates
Note on D22: Kathy Estes: Amount fluctuates. Estimate based on balance at Dec 2020
Note on B23: Kathy Estes: Blanket WBS for surcharges - never completes - balance fluctuates
Note on D23: Kathy Estes: Balance fluctuates. Estimate based on balance at Dec 2020
Note on D24: Kathy Estes: 2022 capital budget for the last qtr
Note on H24: Kathy Estes: Barry L reviewed amount and percent