## as of 8-31-2020
Schedule H
Delta Natural Gas Company, Inc
Case No. 2021-00185
Construction Work in Progress - Percent Complete*
as of August 31, 2020
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (G/H) | Order
1 | 501.19.016.1 | 2019-05-19 | NA | NA | NA | NA | 25696.62 | NA | 10064680
2 | 501.20.014.1 | 2020-04-30 | NA | NA | NA | NA | 51418.06 | NA | 10076478
3 | 501.20.015.1 | 2020-04-30 | NA | NA | NA | NA | 66537.67 | NA | 10076479
4 | 501.20.017.1 | 2020-04-16 | NA | NA | NA | NA | 578671.06 | NA | 10077101
5 | 501.20.020.1 | 2020-05-05 | NA | NA | NA | NA | 50846.29 | NA | 10077579
6 | 502.19.019.1 | 2019-06-05 | NA | NA | NA | NA | 424725.59 | NA | 10065862
7 | 502.19.031.1 | 2019-11-01 | NA | NA | NA | NA | 100939 | NA | 10071160
8 | 502.19.032.1 | 2019-11-01 | NA | NA | NA | NA | 20285.04 | NA | 10071161
9 | 502.20.012.1 | 2020-03-03 | NA | NA | NA | NA | 582.28 | NA | 10075619
10 | 503.19.019.1 | 2019-08-28 | NA | NA | NA | NA | 49846.58 | NA | 10068784
11 | 505.19.008.1 | 2019-08-01 | NA | NA | NA | NA | 59662.05 | NA | 10067751
12 | 505.19.010.1 | 2019-09-23 | NA | NA | NA | NA | 2309.92 | NA | 10068601
13 | 506.19.004.1 | 2019-05-31 | NA | NA | NA | NA | 9684.96 | NA | 10064089
14 | 506.20.007.1 | 2020-08-24 | NA | NA | NA | NA | 2196.85 | NA | 10080271
15 | 510.19.010.1 | 2019-05-10 | NA | NA | NA | NA | 12600.17 | NA | 10064923
16 | 510.19.011.1 | 2019-05-10 | NA | NA | NA | NA | 15869.53 | NA | 10064922
17 | 510.19.017.1 | 2019-12-17 | NA | NA | NA | NA | 85733.64 | NA | 10072731
18 | 511.19.022.1 | 2019-07-03 | NA | NA | NA | NA | 673253.04 | NA | 10066731
19 | 511.19.025.1 | 2019-10-02 | NA | NA | NA | NA | 5821.23 | NA | 10069798
20 | 511.20.010.1 | 2020-04-29 | NA | NA | NA | NA | 111772.71 | NA | 10077450
21 | 511.20.017.1 | 2020-07-02 | NA | NA | NA | NA | 984.4 | NA | 10079616
22 | 512.20.004.1 | 2020-06-24 | NA | NA | NA | NA | 3544.45 | NA | 10075719
23 | 512.20.007.1 | 2020-04-02 | NA | NA | NA | NA | 57946.16 | NA | 10076533
24 | 525.19.006.1 | 2020-05-21 | NA | NA | NA | NA | 94233.06 | NA | 10063990
25 | 525.19.017.1 | 2019-08-01 | NA | NA | NA | NA | 1143.45 | NA | 10067752
26 | 525.19.031.1 | 2019-10-31 | NA | NA | NA | NA | 1223.26 | NA | 10071522
27 | 525.20.014.1 | 2020-07-13 | NA | NA | NA | NA | 896.79 | NA | 10077712
28 | 526.19.005.1 | 2020-03-09 | NA | NA | NA | NA | 12563.93 | NA | 10072764
29 | D9525.MISCMTRMAT | NA | NA | NA | NA | NA | 42954.99 | NA | NA
30 | DELTAOH.CONS | NA | NA | NA | NA | NA | 148493.14 | NA | NA
31 | SW.DELT.CPMS.PH4.2 | 2020-02-06 | NA | NA | NA | NA | 28349.76 | NA | NA
32 | SW.DELT.HANA.UPGRD.2 | 2020-07-02 | NA | NA | NA | NA | 429.02 | NA | NA
33 | SW.DELT.SAP.20.LICEN.3 | 2020-08-05 | NA | NA | NA | NA | 17946.65 | NA | NA
34 | SW.DELT.WFO.PH5.2 | 2020-02-06 | NA | NA | NA | NA | 42008.39 | NA | NA
35 | SW.DELTA.CRB.2 | 2019-02-01 | NA | NA | NA | NA | 3016082.27 | NA | NA | Also included in CWIP at 4/2021
36 | SW.DELTA.MITEL.MIGRTN.3 | 2019-12-19 | NA | NA | NA | NA | 2951.02 | NA | NA
37 | SW.DELTA.PERCEP.UPGRD.2 | 2019-10-03 | NA | NA | NA | NA | 2709.6 | NA | NA
38 | SW.DELTA.PERCEP.UPGRD.3 | 2020-05-05 | NA | NA | NA | NA | 4409.53 | NA | NA
39 | SW.SIP.DELT.EAM.REDSGN.2 | 2020-06-02 | NA | NA | NA | NA | 76384.23 | NA | NA | Also included in CWIP at 4/2021
40 | SW.SIP.DELT.WORKDAY.2 | 2020-06-02 | NA | NA | NA | NA | 31.99 | NA | NA | Also included in CWIP at 4/2021
5903738.38
PKYC - 1300
Line
No. | Project No.
( A ) | ( B )
1 | SW.PKYC.CRM.PH1.2 | 2018-01-01 | NA | NA | NA | NA | 47638.7 | NA
2 | SW.PKYC.DELINQ.CUST.2 | 2020-02-01 | NA | NA | NA | NA | 826.08 | NA
3 | SW.PKYC.HANA.UPGRD.2 | 2020-07-02 | NA | NA | NA | NA | 36.11 | NA
4 | SW.PKYC.OQRMS.2 | 2020-08-01 | NA | NA | NA | NA | 330.94 | NA
5 | SW.PKYC.PERCEP.UPGRD.2 | 2019-10-03 | NA | NA | NA | NA | 231.69 | NA
6 | SW.PKYC.PERCEP.UPGRD.3 | 2020-05-05 | NA | NA | NA | NA | 375.04 | NA
7 | SW.PKYC.SAP.20.LICEN.3 | 2020-08-05 | NA | NA | NA | NA | 1503.48 | NA
8 | SW.PKYC.WFO.PH5.2 | 2020-02-06 | NA | NA | NA | NA | 3556.09 | NA
9 | SW.SIP.PKYC.WORKDAY.2 | 2020-06-02 | NA | NA | NA | NA | 2.68 | NA
54500.81
*Should be based on expenditures including AFUDC
Note on C7: Kathy Estes: First month charges appear on project
Note on B36: Kathy Estes: Blanket WBS - never completes
Note on B37: Kathy Estes: Blanket WBS for Surcharges - never completes
Note on C38: Kathy Estes: For software -first month charges appeared
Note on H49: Kathy Estes: CWIP 8-31-2020
Note on H64: Kathy Estes: CWIP as of 8-31-2020

## as of 8-31-2021
Schedule H
Delta Natural Gas Company, Inc
Case No. 2021-00185
Construction Work in Progress - Percent Complete*
as of August 31, 2021
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (G/H) | Order |  | As of Date
1 | 501.20.014.1 | 2020-04-30 | 2022-12-01 | 51.64% | NA | NA | 51509.58 | NA | 10076478 |  | 2021-08-31
2 | 501.20.015.1 | 2020-04-30 | 2022-12-01 | 51.64% | NA | NA | 68009.96 | NA | 10076479
3 | 501.20.021.1 | 2020-06-01 | 2023-12-01 | 35.68% | NA | NA | 45168.25 | NA | 10078537
4 | 502.19.031.1 | 2019-11-01 | 2021-12-31 | 84.58% | NA | NA | 280939 | NA | 10071160
5 | 502.19.032.1 | 2019-11-01 | 2021-12-31 | 84.58% | NA | NA | 207155.04 | NA | 10071161
6 | 503.19.019.1 | 2019-08-28 | 2021-12-31 | 85.75% | NA | NA | 1210000 | NA | 10068784
7 | 505.19.008.1 | 2019-08-01 | 2022-01-31 | 83.26% | NA | NA | 65170.5 | NA | 10067751
8 | 506.19.004.1 | 2019-06-05 | 2023-12-31 | 48.98% | NA | NA | 9684.96 | NA | 10064089
9 | 506.21.001.1 | 2021-03-29 | 2022-12-31 | 24.14% | NA | NA | 80000 | NA | 10087958
10 | 506.21.005.1 | 2021-03-29 | 2022-12-31 | 24.14% | NA | NA | 19000 | NA
11 | 507.20.004.1 | 2020-09-29 | 2022-12-31 | 40.83% | NA | NA | 942.16 | NA | 10081499
12 | 507.21.001.1 | 2021-03-29 | 2021-12-31 | 55.96% | NA | NA | 1542.97 | NA | 10090043
13 | 510.19.017.1 | 2020-01-31 | 2022-12-31 | 54.27% | NA | NA | 85733.64 | NA | 10072731
14 | 510.21.005.1 | 2021-04-06 | 2022-12-31 | 23.19% | NA | NA | 121.92 | NA | 10089720
15 | 511.21.001.1 | 2021-02-22 | 2023-12-31 | 18.23% | NA | NA | 60.66 | NA | 10086602
16 | 511.21.002.1 | 2021-02-22 | 2023-12-31 | 18.23% | NA | NA | 60.66 | NA | 10086603
17 | 512.20.007.1 | 2020-04-02 | 2023-12-31 | 37.72% | NA | NA | 57946.16 | NA | 10076533
18 | 525.19.017.1 | 2019-09-05 | 2022-01-31 | 82.59% | NA | NA | 1258.36 | NA | 10067752
19 | 526.19.005.1 | 2020-03-09 | 2021-12-31 | 81.57% | NA | NA | 14483.93 | NA | 10072764
20 | 525.21.004.1 | 2021-02-22 | 2022-12-31 | 28.06% | NA | NA | 5121.33 | NA
21 | 501.21.004.1 | 2021-04-16 | 2022-12-31 | 21.96% | NA | NA | 17333 | NA
22 | 501.21.005.1 | 2021-04-16 | 2022-12-31 | 21.96% | NA | NA | 17333 | NA
23 | 501.21.006.1 | 2021-04-16 | 2022-12-31 | 21.96% | NA | NA | 17334 | NA
24 | 525.21.021.1 | 2021-06-15 | 2022-12-31 | 13.65% | NA | NA | 2574600 | NA
25 | 525.21.022.1 | 2021-06-15 | 2022-12-31 | 13.65% | NA | NA | 249612 | NA
26 | D9525.MISCMTRMAT | NA | NA | NA | NA | NA | 31200 | NA | NA
27 | DELTAOH.CONS | NA | NA | NA | NA | NA | 258700 | NA | NA
28 | DELTAOH.GA | NA | NA | NA | NA | NA | 250000 | NA | NA
29 | SW.DELT.CPMS.PH5.2 | 2021-02-05 | 2021-12-31 | 62.92% | NA | NA | 30000 | NA | NA
30 | SW.DELT.DUNNING.2 | 2021-04-05 | 2021-12-31 | 54.81% | NA | NA | 10000 | NA | NA
31 | SW.DELT.WFO.PH6.2 | 2021-02-25 | 2021-12-31 | 60.52% | NA | NA | 40000 | NA | NA
32 | SW.SIP.DELT.CONT.MGT.2 | 2021-01-25 | 2022-06-30 | 41.84% | NA | NA | 25000 | NA | NA
33 | SW.SIP.DELT.PWRPLN.BLD.2 | 2021-04-05 | 2021-12-31 | 54.81% | NA | NA | 100000 | NA | NA
34 | SW.SIP.DELT.SAP.BPC.2 | 2021-04-05 | 2022-04-30 | 37.95% | NA | NA | 25000 | NA | NA
35 | SW.SIP.DELT.SRVR.INFRA.3 | 2021-05-04 | 2022-04-30 | 32.96% | NA | NA | 23090.29 | NA | NA
36 | SW.SIP.DELT.WORKDAY.2 | 2020-06-02 | 2022-12-31 | 48.3% | NA | NA | 31.99 | NA | NA | Was also included in CWIP at 8/2020
37 | SW.SIP.DELT.VALMS21.2 | 2021-05-04 | 2021-12-31 | 49.38% | NA | NA | 30000 | NA | NA
38 | SW.SIP.DELT.WRKMGT21.2 | 2021-05-04 | 2021-12-31 | 49.38% | NA | NA | 30000 | NA | NA
39 | VENTYX.VERS9.8.2 | 2021-06-02 | 2021-12-31 | 42.45% | NA | NA | 5000 | NA | NA
5938143.36
*Should be based on expenditures including AFUDC
Note on C7: Kathy Estes: First month charges appear on project
Note on D7: Kathy Estes: For construction projects - supplied by RN
Note on H8: Kathy Estes: Jonathan and Robert N
Note on B33: Kathy Estes: Blanket WBS - never completes - clears quarterly acct 382
Note on B34: Kathy Estes: Blanket WBS for surcharges - never completes
Note on B35: Kathy Estes: Blanket WBS for surcharges - never completes
Note on C36: Kathy Estes: for software - first date charges began
Note on D36: Kathy Estes: Barry Lynch

## as of 12-31-2022
Schedule H
Delta Natural Gas Company, Inc
Case No. 2021-00185
Construction Work in Progress - Percent Complete*
as of December 31, 2022
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (G/H) | as of date
1 | 501.20.021.1 | 2020-06-01 | 2023-12-31 | 72.09% | N/A | N/A | 45168.25 | N/A | 2022-12-31
2 | 506.19.004.1 | 2019-06-05 | 2023-12-31 | 78.14% | N/A | N/A | 9684.96 | N/A
3 | 511.21.001.1 | 2021-02-22 | 2023-12-31 | 64.97% | N/A | N/A | 60.66 | N/A
4 | 511.21.002.1 | 2021-02-22 | 2023-12-31 | 64.97% | N/A | N/A | 60.66 | N/A
5 | 512.20.007.1 | 2020-04-02 | 2023-12-31 | 73.32% | N/A | N/A | 57946.16 | N/A
6 | Outside Engineering Services PRP Proj | 2022-01-01 | 2024-12-31 | 33.24% | N/A | N/A | 400000 | N/A
7 | Nicholasville Transmission Line | 2022-01-01 | 2023-12-31 | 49.93% | N/A | N/A | 1750299 | N/A
8 | DELTAOH.CONS | NA | NA | NA | N/A | N/A | 80000 | N/A
9 | DELTAOH.GA | NA | NA | NA | N/A | N/A | 240000 | N/A
10 | Computer Software | 2022-09-01 | 2023-03-31 | 57.35% | N/A | N/A | 393700 | N/A
2976919.69
*Should be based on expenditures including AFUDC
Note on B16: Kathy Estes: Blanket WBS for surcharges - never completes - balance fluctuates
Note on H16: Kathy Estes: Amount fluctuates. Estimate based on balance at Dec 2020
Note on B17: Kathy Estes: Blanket WBS for surcharges - never completes - balance fluctuates
Note on H17: Kathy Estes: Balance fluctuates. Estimate based on balance at Dec 2020