## Sheet1
Schedule I2
Delta Natural Gas Company, Inc.
Case No. 2021-00185
Calculation of Capital Construction Project Slippage Factor
Source: Schedule I1 - Construction Projects
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
1 | 7482356 | 9113250 | 1630894 | 17.9% | 82.1%
2 | 9531363 | 7515200 | -2016163 | -26.83% | 126.8%
3 | 10251645 | 7424100 | -2827545 | -38.09% | 138.1%
4 | 14355903 | 13646600 | -709303 | -5.198% | 105.2%
5 | 12851168 | 13499800 | 648632 | 4.805% | 95.2%
Totals | 54472435 | 51198950 | -3273485 | -6.394% | 106.4%
5 Year Average Slippage Factor (Mathematic Average of Yearly Slippage Factors / 5 years) |  |  |  |  | 109.5%
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule I1. Total all projects for a given year.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor for each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.