## Schedule H
Schedule H
DUKE ENERGY KENTUCKY
CASE NO. 2021-00190
CONSTRUCTION WORK IN PROGRESS - PERCENT COMPLETE
AS OF AUGUST 31, 2020
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (H/G)
1 | 107GASCK | 2008-07-01 | 2050-12-31 | 28.63% | 0 | 0 | 426488
2 | 307482001 | 2018-12-28 09:17 | 2020-03-20 | 100% | 28166 | 28166 | 19811 | 70.34%
3 | 307482002 | 2019-12-19 13:54 | 2021-06-30 | 45.8% | 26324 | 26324 | 3034 | 11.53%
4 | 315986A | 2017-08-10 10:55 | 2022-09-05 | 60.31% | 2325960.3 | 2325960.3 | 2432164 | 104.6%
5 | 315986E | 2017-08-11 10:44 | 2020-09-01 | 99.91% | 117210.08 | 117210.08 | 167608 | 143%
6 | 359990001 | 2019-02-26 15:25 | 2019-12-01 | 100% | 60858 | 60858 | 67908 | 111.6%
7 | AW0938 | 2019-08-09 13:08 | 2020-11-30 | 81% | 64259 | 64259 | 11228 | 17.47%
8 | AW1568 | 2019-12-18 15:27 | 2021-12-30 | 34.59% | 190631 | 190631 | 67986 | 35.66%
9 | AW1592 | 2020-01-05 02:41 | 2021-09-30 | 37.7% | 3390200 | 10253358 | 450790 | 4.397%
10 | CC1900001 | 2020-01-27 08:12 | 2021-09-30 | 35.46% | 8542 | 26306 | 6586 | 25.04%
11 | CS1900001 | 2020-01-29 16:09 | 2021-12-31 | 30.63% | 8542 | 13742 | 6853 | 49.87%
12 | CY190HW15 | 2019-12-11 08:05 | 2022-06-30 | 28.33% | 75995 | 75995 | 90 | 0.1184%
13 | GASKYIND | 2008-07-01 | 2020-12-31 | 97.33% | 0 | 0 | 823
14 | GCTA30060 | 2017-04-11 15:19 | 2020-06-30 | 100% | 149205 | 149205 | 251423 | 168.5%
15 | GCTA30062 | 2017-08-08 09:43 | 2019-07-31 | 100% | 133026 | 133026 | -10619 | -7.983%
16 | GCTA3006K | 2019-11-15 07:17 | 2021-12-17 | 38.01% | 133026 | 133026 | 89187 | 67.04%
17 | GCTA30073 | 2017-03-30 17:09 | 2021-03-31 | 85.5% | 853149 | 853149 | 729709 | 85.53%
18 | GCTA30114 | 2017-06-21 11:37 | 2020-11-10 | 94.26% | 94588 | 94588 | 154537 | 163.4%
19 | GCTA30128 | 2017-06-30 10:05 | 2019-10-31 | 100% | 28617 | 28617 | 16959 | 59.26%
20 | GCTA30391 | 2018-12-18 14:49 | 2020-12-31 | 83.6% | 224469 | 224469 | 70604 | 31.45%
21 | GCTA30436 | 2018-05-21 15:50 | 2019-12-01 | 100% | 513619 | 513619 | 48512 | 9.445%
22 | GCTA33039 | 2018-06-19 11:18 | 2020-03-31 | 100% | 25853 | 120205 | 51269 | 42.65%
23 | GCTA43704 | 2018-10-10 11:35 | 2020-01-18 | 100% | 37076 | 37076 | 35461 | 95.64%
24 | GCTA47001 | 2018-12-06 14:57 | 2020-05-31 | 100% | 120205 | 120205 | 82278 | 68.45%
25 | IT1900065 | 2020-02-07 07:49 | 2021-03-31 | 49.28% | 87832 | 87832 | 42481 | 48.37%
26 | IT1900073 | 2020-01-20 08:44 | 2021-06-08 | 44.36% | 36572 | 36572 | 1671 | 4.569%
27 | IT1900074 | 2020-01-20 10:57 | 2021-06-08 | 44.36% | 229288 | 229288 | 1057 | 0.461%
28 | MDTGAS20 | 2019-10-10 14:30 | 2020-12-31 | 72.77% | 403995 | 403995 | 432208 | 107%
29 | MX0181170 | 2018-12-12 18:01 | 2019-11-27 | 100% | 27834.24 | 64213.24 | 22097 | 34.41%
30 | MX0270903 | 2019-03-21 14:01 | 2019-07-19 | 100% | 165436 | 365844.57 | 414221 | 113.2%
31 | MX0556249 | 2019-01-14 10:01 | 2019-07-26 | 100% | 84022.09 | 84022.09 | 277359 | 330.1%
32 | MX0590999 | 2019-07-31 14:01 | 2019-10-11 | 100% | 119350.5 | 119350.5 | 369227 | 309.4%
33 | MX0602571 | 2019-07-16 10:02 | 2019-09-13 | 100% | 84922.63 | 112220.53 | 15846 | 14.12%
34 | MX0790794 | 2018-01-23 20:20 | 2018-09-26 | 100% | 57170.82 | 182903.74 | 353160 | 193.1%
35 | MX1130180 | 2019-02-07 10:02 | 2019-03-20 | 100% | 41137.04 | 41137.04 | 74540 | 181.2%
36 | MX1304901 | 2019-06-26 14:01 | 2019-08-16 | 100% | 24358.58 | 46479.42 | 34706 | 74.67%
37 | MX1356700 | 2019-06-27 10:02 | 2019-09-27 | 100% | 117515.64 | 147466.28 | 258523 | 175.3%
38 | MX1376296 | 2019-08-02 14:01 | 2020-09-15 | 96.34% | 70969.1 | 70969.1 | 378355 | 533.1%
39 | MX1958084 | 2020-02-05 10:02 | 2020-05-08 | 100% | 147505.69 | 147505.69 | 575005 | 389.8%
40 | MX2142600 | 2019-07-18 18:01 | 2019-09-20 | 100% | 23842.87 | 54541.9 | 28086 | 51.49%
41 | MX2143073 | 2019-05-21 18:01 | 2019-08-02 | 100% | 21151 | 43437.77 | 37156 | 85.54%
42 | MX2217622 | 2017-09-22 14:01 | 2021-12-31 | 68.8% | 87907.04 | 54616.8 | 12382 | 22.67%
43 | MX2271880 | 2019-07-30 10:01 | 2019-11-29 | 100% | 44948.03 | 44948.03 | 240175 | 534.3%
44 | MX2424919 | 2019-07-02 14:01 | 2019-09-13 | 100% | 28079.12 | 50615.9 | 32354 | 63.92%
45 | MX2624631 | 2019-10-01 18:01 | 2020-04-09 | 100% | 25634.94 | 25634.94 | 25557 | 99.7%
46 | MX2848811 | 2019-09-30 10:01 | 2019-11-01 | 100% | 1779.49 | 35185 | 5552 | 15.78%
47 | MX2911494 | 2019-08-02 14:01 | 2020-09-15 | 96.34% | 7616.99 | 7616.99 | 27090 | 355.7%
48 | MX4146445 | 2019-10-01 14:01 | 2019-11-15 | 100% | 732.05 | 13325 | 3285 | 24.65%
49 | MX4210795 | 2019-12-19 10:01 | 2020-10-02 | 88.89% | 43704.39 | 52790 | 37037 | 70.16%
50 | MX6693835 | 2017-12-15 14:01 | 2020-12-31 | 89.03% | 43660.93 | 106314.24 | 59193 | 55.68%
51 | MX6800938 | 2018-01-10 18:02 | 2021-06-08 | 77.43% | 43953.52 | 43660.93 | 76621 | 175.5%
52 | MX6828172 | 2018-04-04 10:01 | 2020-12-31 | 87.82% | 43660.93 | 139842.24 | 29036 | 20.76%
53 | MX7507727 | 2018-04-06 18:03 | 2018-10-26 | 100% | 55108.78 | 238847.13 | 238643 | 99.91%
54 | MX7599942 | 2019-08-02 10:01 | 2020-02-29 | 100% | 50904.78 | 50904.78 | 169022 | 332%
55 | MX7625297 | 2018-04-04 14:01 | 2018-05-25 | 100% | 11456.17 | 45950.78 | 16531 | 35.98%
56 | MX8175168 | 2019-11-19 14:01 | 2020-12-31 | 70.1% | 8604.87 | 62696 | 6812 | 10.87%
57 | MX8574441 | 2018-08-22 14:02 | 2018-10-05 | 100% | 80515.92 | 95525.92 | 101535 | 106.3%
58 | MX8672523 | 2019-03-21 14:01 | 2020-07-31 | 100% | 55267 | 262006.08 | 40674 | 15.52%
59 | MX8760866 | 2018-06-14 14:01 | 2019-02-03 | 100% | 780.32 | 126080.99 | 368824 | 292.5%
60 | MX9177637 | 2018-09-24 14:02 | 2019-04-03 | 100% | 0 | 0 | 2377
61 | MX9244894 | 2019-11-08 10:01 | 2021-07-27 | 47.37% | 277825.33 | 277825.33 | 148557 | 53.47%
62 | MX9545566 | 2019-11-12 10:01 | 2020-10-30 | 83% | 436724.68 | 1413710 | 140109 | 9.911%
63 | OMGPCVNTN | 2009-11-04 | 2050-12-31 | 26.3% | 0 | 0 | 225
64 | OMGPNWPRT | 2009-11-04 | 2050-12-31 | 26.3% | 0 | 0 | 270
65 | R8822 | 2016-03-21 13:26 | 2017-02-01 | 100% | 67177.92 | 67177.92 | 177 | 0.2635%
66 | S2732 | 2016-04-29 10:50 | 2018-08-11 | 100% | 91976.45 | 91976.45 | 38530 | 41.89%
67 | SG358SW2 | 2018-05-07 17:00 | 2019-09-24 | 100% | 7317.09 | 7317.09 | 6464 | 88.34%
68 | SG489SW | 2016-11-23 11:25 | 2019-03-31 | 100% | 16065.37 | 16065.37 | 47 | 0.2926%
69 | SG781SW | 2018-07-12 09:17 | 2020-12-31 | 86.49% | 76873.76 | 76873.76 | 2321 | 3.019%
70 | T2904 | 2017-03-08 13:44 | 2018-09-28 | 100% | 29846.02 | 29846.02 | 2125 | 7.12%
71 | T4002 | 2017-03-17 11:42 | 2018-08-30 | 100% | 31943.04 | 31943.04 | 2408 | 7.538%
72 | T7778 | 2017-05-03 08:00 | 2018-03-29 | 100% | 165811.2 | 165811.2 | 1059 | 0.6387%
73 | T9340 | 2017-07-14 10:10 | 2018-06-01 | 100% | 28102.56 | 28102.56 | 2701 | 9.611%
74 | T9341 | 2017-07-14 10:19 | 2018-06-01 | 100% | 28102.56 | 28102.56 | 2989 | 10.64%
75 | V5136 | 2018-08-20 08:22 | 2018-12-31 | 100% | 23120 | 23120 | 27590 | 119.3%
76 | V7283 | 2018-11-14 14:31 | 2020-06-30 | 100% | 397420 | 416794 | 1491626 | 357.9%
77 | V8351 | 2019-02-11 09:25 | 2021-03-13 | 74.51% | 6083876 | 6287827 | 1168208 | 18.58%
78 | V8967 | 2019-04-17 13:32 | 2020-08-30 | 100% | 244737.99 | 244737.99 | 89646 | 36.63%
79 | V9444 | 2019-06-12 07:56 | 2021-12-30 | 47.85% | 18389510 | 22514005 | 1669267 | 7.414%
80 | V9445 | 2019-06-12 08:04 | 2021-11-30 | 49.45% | 693000 | 2343000 | 591552 | 25.25%
81 | 315986HW4 | 2018-08-31 12:34 | 2019-08-01 | 100% | 53607 | 53607 | 13695 | 25.55%
82 | 315986HW5 | 2019-09-03 14:48 | 2020-06-15 | 100% | 42700 | 42700 | 18608 | 43.58%
83 | 338802003 | 2018-04-25 14:30 | 2020-03-31 | 100% | 147321.02 | 147321.02 | 32178 | 21.84%
84 | 338802004 | 2018-09-17 12:23 | 2020-05-28 | 100% | 60564 | 52783 | -6 | -0.01137%
85 | 344598001 | 2018-04-10 15:29 | 2020-01-30 | 100% | 197081 | 197081 | 77 | 0.03907%
86 | GCTA4700A | 2018-12-04 14:21 | 2021-03-14 | 76.53% | 29280 | 29280 | 63 | 0.2152%
87 | GCTA4700B | 2018-12-06 13:26 | 2021-03-14 | 76.48% | 215691 | 215691 | 103404 | 47.94%
88 | IT1900021 | 2019-08-01 11:16 | 2021-01-17 | 74.02% | 485841 | 485841 | 237430 | 48.87%
89 | MX1233047 | 2019-10-23 18:01 | 2020-12-14 | 74.88% | 780.32 | 92509 | 52428 | 56.67%
90 | MX4342633 | 2019-10-18 10:01 | 2020-06-26 | 100% | 38858.96 | 166756 | 387126 | 232.2%
91 | SMARTPH2 | 2015-12-11 15:15 | 2017-12-31 | 100% | 0 | 0 | 1512
92 | V8191 | 2019-01-23 15:21 | 2021-02-25 | 76.7% | 25947195 | 26326195 | 24912011 | 94.63%
93 | V8352 | 2019-02-11 09:32 | 2021-02-25 | 76.11% | 2279000 | 1941000 | 4788104 | 246.7%
94 | MX4125743 | 2020-01-29 14:01 | 2020-12-16 | 66.77% | 87214.46 | 152669 | 114723 | 75.14%
95 | 307482SW2 | 2020-04-13 09:32 | 2021-06-30 | 31.6% | 30258 | 30258 | 9971 | 32.95%
96 | 315986C | 2017-08-10 14:30 | 2019-06-18 | 100% | 187946.4 | 283305 | 49499 | 17.47%
97 | 315986HW6 | 2020-03-12 11:33 | 2021-06-01 | 38.57% | 21350 | 21350 | 36057 | 168.9%
98 | 338802HW3 | 2018-04-25 15:10 | 2020-03-31 | 100% | 119744 | 119744 | 4 | 0.00334%
99 | 349395006 | 2020-04-13 16:35 | 2022-06-30 | 17.33% | 1775 | 1775 | 109639 | 6177%
100 | AW0832 | 2019-07-26 13:48 | 2020-12-03 | 81.05% | 564646 | 564646 | 244379 | 43.28%
101 | AW2017 | 2020-04-09 07:34 | 2021-01-05 | 53.14% | 1944700 | 2024700 | 1065376 | 52.62%
102 | AW2021 | 2020-04-13 10:21 | 2021-09-30 | 26.17% | 115000 | 115000 | 60916 | 52.97%
103 | AW2146 | 2020-05-19 16:54 | 2022-06-01 | 14% | 6528636 | 6528636 | 240950 | 3.691%
104 | CC2000001 | 2020-03-30 13:53 | 2021-12-31 | 24.02% | 40230 | 76276 | 20694 | 27.13%
105 | CC2000003 | 2020-06-25 21:36 | 2021-12-30 | 12.12% | 28721 | 28721 | 179 | 0.6232%
106 | IT1900069 | 2020-02-21 15:10 | 2021-09-24 | 33.05% | 65041 | 65041 | 27362 | 42.07%
107 | MX3298765 | 2020-07-28 10:01 | 2021-01-11 | 20.36% | 41781.3 | 94800 | 5650 | 5.96%
108 | MX4355391 | 2020-05-27 10:01 | 2020-11-30 | 51.34% | 133519.8 | 225972 | 19126 | 8.464%
109 | MX4837396 | 2020-02-24 14:07 | 2021-07-14 | 37.35% | 55748.27 | 81024 | 298 | 0.3678%
110 | MX4861864 | 2020-06-12 14:01 | 2021-01-12 | 37.38% | 99212.68 | 166549 | 18093 | 10.86%
111 | MX4875568 | 2020-03-03 10:01 | 2020-12-26 | 60.74% | 765.33 | 1255100 | 711865 | 56.72%
112 | MX5040349 | 2020-04-23 14:01 | 2020-11-24 | 60.47% | 58773.18 | 114071 | 94020 | 82.42%
113 | MX5373035 | 2020-04-03 11:02 | 2020-11-27 | 63.03% | 24267.63 | 27389.07 | 39437 | 144%
114 | MX5515912 | 2020-04-16 18:01 | 2021-04-04 | 38.81% | 110097.1 | 107923.51 | 37572 | 34.81%
115 | MX5518434 | 2020-04-16 18:01 | 2021-02-11 | 45.51% | 110214.71 | 110214.71 | 8182 | 7.424%
116 | MX6180533 | 2020-07-29 14:01 | 2021-01-25 | 18.33% | 32051.66 | 74687 | 1880 | 2.517%
117 | MX6243694 | 2020-06-18 10:01 | 2021-04-07 | 25.26% | 51376.02 | 104176 | 6216 | 5.967%
118 | MX6477976 | 2020-04-29 14:01 | 2021-01-11 | 48.25% | 44200.97 | 99251 | 142221 | 143.3%
119 | MX6628393 | 2020-05-18 10:01 | 2020-11-17 | 57.38% | 114190.79 | 399033 | 147675 | 37.01%
120 | MX6840192 | 2020-08-13 18:01 | 2020-10-23 | 25.35% | 24443.59 | 48085 | 98 | 0.2038%
121 | MX6842755 | 2020-07-09 10:01 | 2020-12-15 | 33.33% | 3113.23 | 25737 | 4580 | 17.8%
122 | MX6889178 | 2020-05-22 14:01 | 2021-02-16 | 37.41% | 765.33 | 274232 | 31795 | 11.59%
123 | MX6891268 | 2020-05-22 14:01 | 2021-04-05 | 31.76% | 765.33 | 319190 | 211184 | 66.16%
124 | MX7035169 | 2020-07-08 18:01 | 2020-12-07 | 35.53% | 33783.36 | 74108 | 11672 | 15.75%
125 | MX7078370 | 2020-08-14 10:01 | 2020-09-30 | 36.17% | 15754.65 | 39282 | 843 | 2.146%
126 | MX7281845 | 2020-07-07 10:01 | 2020-12-31 | 31.07% | 44953.52 | 44953.52 | 2642 | 5.877%
127 | MX7281967 | 2020-07-07 10:01 | 2020-12-31 | 31.07% | 48953.52 | 48953.52 | 3931 | 8.03%
128 | MX7282035 | 2020-07-14 10:02 | 2020-12-31 | 28.24% | 48953.52 | 48953.52 | 12672 | 25.89%
129 | MX7783733 | 2020-08-17 10:01 | 2020-10-16 | 23.33% | 20824.66 | 48085 | 98 | 0.2038%
130 | SG723SW | 2020-03-03 09:59 | 2021-11-08 | 29.43% | 26599 | 26599 | 6329 | 23.79%
131 | SG724SW | 2020-08-19 16:46 | 2021-04-24 | 4.839% | 15916 | 15916 | 245 | 1.539%
132 | SG940SVR | 2020-04-24 15:59 | 2021-02-07 | 44.64% | 23022 | 23022 | 1132 | 4.917%
133 | Blank Project ID | [5 empty] | -28368
49392425