## 2016
Duke Energy Kentucky Gas
Year 2016
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 875.56 |  |  |  |  | 198044.32 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 315263BTS | 315263BTS Encryption PH2 | 3595.43 |  |  |  |  | 3595.43 |  |  | 2016-10-13 15:38 | 2016-12-31 | 2016-10-01 | 2017-04-23
75087 | FPIT | 315263GDG | 315263GDG Encryption PH2 | 4261.93 |  |  |  |  | 4261.93 |  |  | 2016-10-13 12:55 | 2016-12-31 | 2016-11-01 | 2017-06-30
75087 | FPIT | 315263VER | 315263VER Encryption PH2 | 3159.71 |  |  |  |  | 3159.71 |  |  | 2016-10-13 16:23 | 2016-12-31 | 2016-12-01 | 2017-06-30
75086 | G7SERVNEW | 3CMNEW70 | Install New C-M 3" | 110547.92 |  |  |  |  | 182500.59 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | 3MCNEW70 | Install New M-C 3" | 80494.07 |  |  |  |  | 183385.15 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVMC | 3MCR70 | Replace M-C 3" - Kentucky | 407.19 |  |  |  |  | 50255.16 |  |  | 2008-07-01 | 2050-12-31 | 2008-08-01
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 42026.26 |  |  |  |  | 207236.08 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 4736.92 |  |  |  |  | 95820.44 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 6CMNEW70 | Install New C-M 6" | 54872.15 |  |  |  |  | 91369.17 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 11328.15 |  |  |  |  | 47267.2 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | 8CMNEW70 | Install New C-M 8" | -1539.3 |  |  |  |  | 39809.86 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7SERVNEW | 8MCNEW70 | Install New M-C 8" | -7083.8 |  |  |  |  | 15423.17 |  |  | 2011-03-23 | 2050-12-31 | 2012-08-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 166084.65 |  |  |  |  | 245258.15 |  |  | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 1369349.47 |  |  |  |  | 2396729.28 |  |  | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 0.35 |  |  |  |  | 9.02 |  |  | 2015-03-30 16:20 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 77635.8 |  |  |  |  | 94465.82 |  |  | 2015-03-30 16:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 0.28 |  |  |  |  | 7.37 |  |  | 2015-03-30 14:15 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | FENABLES | ARMS | Enable ARM Scheduler Software | 39547.64 |  |  |  |  | 71015.43 |  |  | 2015-03-30 16:26 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | GITKYCAP | BOES | Boes Replacement (AGOES) for Gas | 22862.22 |  |  |  |  | 63280.02 |  |  | 2015-05-01 11:05 | 2016-06-30 | 2015-08-01 | 2017-01-25
75086 | FCF53SKEG | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 4473.34 |  |  |  |  | 4473.34 |  |  | 2014-08-04 | 2017-03-31 | 2016-07-01 | 2017-03-05
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 25757.83 |  |  |  |  | 44301.11 |  |  | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 104398.85 |  |  |  |  | 145320.18 |  |  | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 19312.07 |  |  |  |  | 47380.89 |  |  | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 1275443.69 |  |  |  |  | 5135016.16 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 4950.27 |  |  |  |  | 4950.27 |  |  | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 888018.51 |  |  |  |  | 8682965.83 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | 2" or less steel C-M Replace | 3756.35 |  |  |  |  | 3756.35 |  |  | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 1072854.48 |  |  |  |  | 1261535.26 |  |  | 2015-03-04 11:36 | 2022-12-31 | 2015-07-01
75086 | FEWLANKEG | COVINGTON | Enable WLAN Remediation | 10522.97 |  |  |  |  | 10522.97 |  |  | 2016-02-03 17:41 | 2017-03-31 | 2016-03-01 | 2016-10-10
75086 | GITKYCAP | CPMANGENH | CP Manager Enhancements | 152251 |  |  |  |  | 152251 |  |  | 2016-02-22 14:06 | 2017-03-04 | 2016-03-01 | 2016-12-12
75086 | FENABLEH | ECOMH | Enable ECOM Data Hub | 106.9 |  |  |  |  | 106.9 |  |  | 2015-09-29 10:00 | 2017-10-31 | 2016-01-01 | 2017-11-07
75086 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 24919.32 |  |  |  |  | 28592.44 |  |  | 2015-03-30 16:52 | 2017-10-31 | 2015-05-01 | 2017-11-07
75087 | SGITCS | ECSPH2 | Enterprise Cust systems Ph2 Capital | 0 |  |  |  |  | 0 |  |  | 2011-02-28 | 2015-06-30 | 2011-03-01
75086 | FENABLEH | EGISH | Enable EGIS Hardware | 213.27 |  |  |  |  | 619.16 |  |  | 2015-03-30 15:51 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | EGISS | Enable EGIS Software | 147613.66 |  |  |  |  | 218539.8 |  |  | 2015-03-30 16:42 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | 232589.61 |  |  |  |  | 345923.04 |  |  | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01
75086 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 2.13 |  |  |  |  | 51.22 |  |  | 2015-03-30 14:50 | 2017-10-31 | 2015-08-01 | 2017-11-07
75086 | FENABLES | EXPDS | Enable Expert Designer Software | 49865.51 |  |  |  |  | 80034.43 |  |  | 2015-03-30 16:33 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 39389.54 |  |  |  |  | 44141.41 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | CPERNST2 | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 157977.7 |  |  |  |  | 683163.99 |  |  | 2012-05-22 | 2015-01-15 | 2012-12-01 | 2014-07-01
75086 | G7PUBIMP | G8241 | Sunset Drive - Three Mile Rd Imp | 17040.91 |  |  |  |  | 153857.86 |  |  | 2012-08-16 | 2016-01-31 | 2015-02-01 | 2016-02-05
75086 | G7PUBIMP | G8242 | AM00 - NKU | 206733.22 |  |  |  |  | 1176811.19 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | 53314.83 |  |  |  |  | 53314.83 |  |  | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01
75086 | G7LGMR | H0264 | Reg 118K Inlet & Outlet Piping | -399.94 |  |  |  |  | 80240.04 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0265 | Reg 118K Installation | 6418.16 |  |  |  |  | 208966.68 |  |  | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0350 | STA 535K1 (UL33 to HP) Modification | 438.6 |  |  |  |  | 23297.23 |  |  | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7REPL | H0383 | REG 117K - Inlet & Outlet Piping | -4760.77 |  |  |  |  | 152422.35 |  |  | 2013-07-05 | 2015-06-30 | 2013-12-01 | 2014-07-24
75086 | G7LGMR | H0384 | Reg 117K-Amsterdam & Redwood | -4687.01 |  |  |  |  | 128065.73 |  |  | 2013-07-05 | 2015-06-30 | 2013-10-01 | 2014-07-24
75086 | G7LGMR | H0485 | Reg 21K Improvements-Grand & Ft Tho | 160942.05 |  |  |  |  | 162220.76 |  |  | 2013-07-29 | 2015-06-30 | 2013-11-01 | 2014-02-11
75086 | G7MAINS | H1364 | Sutter Drive Main Extension | -4.87 |  |  |  |  | 552.36 |  |  | 2013-12-02 | 2014-11-30 | 2015-08-01 | 2015-12-09
75086 | GITKYCAP | H1444 | PCS Upgrade | -119.92 |  |  |  |  | 2844.55 |  |  | 2013-12-11 | 2014-06-30 | 2013-12-01 | 2014-03-31
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 153644.98 |  |  |  |  | 243934.66 |  |  | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 89628.97 |  |  |  |  | 89628.97 |  |  | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | 5059.16 |  |  |  |  | 5059.16 |  |  | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LCMSP70 | ASRP Greater than 2" C-M Install | 808.28 |  |  |  |  | 808.28 |  |  | 2016-01-13 11:25 | 2022-12-31 | 2016-07-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 118827.24 |  |  |  |  | 118827.24 |  |  | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 2017.94 |  |  |  |  | 2017.94 |  |  | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 83837.72 |  |  |  |  | 83837.72 |  |  | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LMCSP70 | ASRP Greater than 2" M-C Replace | 5202.19 |  |  |  |  | 5202.19 |  |  | 2016-01-13 11:21 | 2022-12-31 | 2016-04-01
75086 | G7MSCPRD | M6102 | Replace Compress 6&7 oil lube sys | -879.53 |  |  |  |  | 52782.65 |  |  | 2014-06-11 | 2016-06-30 | 2014-09-01 | 2015-01-14
75086 | G7MSCPRD | M6103 | Erlanger GP Aftercooler Retube | -2530.54 |  |  |  |  | 86537.8 |  |  | 2014-06-11 | 2016-06-30 | 2014-06-01 | 2015-01-21
75086 | GITKYCAP | MAOP7SFTW | Maximum Allowable Operating Pressur | 253010.94 |  |  |  |  | 288960.04 |  |  | 2015-03-12 12:19 | 2016-04-30 | 2015-04-01 | 2016-12-12
75086 | FENABLEH | MAXH | Enable Maximo Hardware | 2194.48 |  |  |  |  | 2688.05 |  |  | 2015-03-30 13:58 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | MAXS | Enable Maximo Software | 506831.72 |  |  |  |  | 740826.63 |  |  | 2015-03-30 16:21 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 2343661.89 |  |  |  |  | 6240540.03 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 19254.83 |  |  |  |  | 138141 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1569790.26 |  |  |  |  | 10316756.86 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 141814.14 |  |  |  |  | 430120.07 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 3261747.13 |  |  |  |  | 3670641.19 |  |  | 2015-03-04 11:18 | 2022-12-31 | 2015-07-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 453409.12 |  |  |  |  | 453409.12 |  |  | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 25469.16 |  |  |  |  | 27494.22 |  |  | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | 268021.07 |  |  |  |  | 369729.6 |  |  | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUBIMP | N8164 | Summit Lane | 34602.93 |  |  |  |  | 136994.83 |  |  | 2014-07-03 | 2015-02-01 | 2014-07-01 | 2014-10-16
75087 | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 13080.63 |  |  |  |  | 13088.22 |  |  | 2015-11-16 14:22 | 2016-09-30 | 2015-12-01 | 2017-03-27
75086 | G7PUBIMP | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 3431.59 |  |  |  |  | 249693.98 |  |  | 2014-08-22 | 2015-06-28 | 2014-12-01 | 2015-08-05
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | 123011.54 |  |  |  |  | 159602.57 |  |  | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7IMPRPL | P6709 | Deep Well Erlanger Gas Plant | -740.33 |  |  |  |  | 57999.96 |  |  | 2014-10-31 | 2015-04-27 | 2014-11-01 | 2015-03-10
75086 | G7IMPRPL | P6754 | T/L AM07 - Install Corrosion Monito | 29583.71 |  |  |  |  | 56827.59 |  |  | 2014-11-05 | 2015-11-01 | 2014-12-01 | 2015-10-15
75086 | G7LGMR | P7279 | Rossford Avenue (STA #101) | 753886.31 |  |  |  |  | 753886.31 |  |  | 2015-01-14 | 2017-02-15 | 2016-04-01 | 2016-12-28
75086 | G7PUBIMP | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | -1259.74 |  |  |  |  | 76819.78 |  |  | 2015-01-14 | 2015-09-25 | 2015-02-01 | 2015-06-20
75086 | G7SERVNEW | P7311 | KY SR 63 (ARK Encounter) | -3944.35 |  |  |  |  | 79006.95 |  |  | 2015-01-16 | 2016-02-28 | 2015-05-01 | 2016-03-16
75086 | G7REPL | P7671 | Y000 - KY Portion - 16" Ohio River | 45658.83 |  |  |  |  | 300913.29 |  |  | 2015-02-09 | 2016-04-30 | 2015-03-01 | 2015-09-26
75086 | G7MSCPRD | P8054 | Replace BTU measurement at Erlanger | 5498.75 |  |  |  |  | 53587.37 |  |  | 2015-03-12 14:27 | 2016-04-30 | 2015-07-01 | 2016-01-30
75086 | FKPIAPP | P8060 | Perf Meas App (KPI) - T&D & Gas | 15.18 |  |  |  |  | 144.23 |  |  | 2015-03-12 16:05 | 2016-02-28 | 2015-04-01 | 2016-01-30
75086 | G7LGMR | P9838 | Erlanger STA 149 | 30673.78 |  |  |  |  | 502950.41 |  |  | 2015-04-02 15:27 | 2016-03-01 | 2015-08-01 | 2016-01-15
75087 | FPIT | PCTA175BS | PCTA175BS CDS | 43574.01 |  |  |  |  | 47081.79 |  |  | 2014-11-17 | 2016-07-31 | 2014-12-01 | 2016-10-05
75087 | FPIT | PCTA175L | PCTA175L CDS Licenses | 1886.12 |  |  |  |  | 1886.12 |  |  | 2016-08-01 10:30 | 2016-12-31 | 2016-10-01 | 2017-02-15
75087 | FPIT | PCTA481AS | Sitecore | 566763.56 |  |  |  |  | 1155984.87 |  |  | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75087 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 833298.71 |  |  |  |  | 833298.71 |  |  | 2016-02-11 12:05 | 2018-10-31 | 2016-03-01 | 2018-10-31
75086 | PCTA82F | PCTAIT82F | INT82F-EGIS Web Tool | 7004.74 |  |  |  |  | 48051.24 |  |  | 2014-07-22 | 2015-07-30 | 2014-07-01 | 2015-12-28
75086 | PCTA82G | PCTAIT82G | INT82G - GeoSpatial Data store | -56.27 |  |  |  |  | 7310.21 |  |  | 2014-07-22 | 2015-07-30 | 2014-08-01 | 2015-12-28
75086 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 1235606.36 |  |  |  |  | 1439811.23 |  |  | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | PCTA82F | PCTAVS82F | INT82F-EGIS Web Tool | 2878.08 |  |  |  |  | 2878.08 |  |  | 2014-07-22 | 2016-07-30 | 2016-04-01 | 2016-07-31
75086 | FENABLES | PPS | Enable PowerPlan Software | 27928.98 |  |  |  |  | 34441.93 |  |  | 2015-03-30 16:57 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | G7MAINS | Q3775 | 6th St Newport MEA | 12264.78 |  |  |  |  | 37942.42 |  |  | 2015-05-01 09:30 | 2016-02-01 | 2015-10-01 | 2016-04-21
75086 | G7MAINS | Q8319 | Lacresta Dr MEA | -208.43 |  |  |  |  | 12329.65 |  |  | 2015-05-15 15:28 | 2016-01-20 | 2015-06-01 | 2015-10-12
75086 | G7LGMR | Q9751 | STA 149 Hydro Test of AM07 | 141324.03 |  |  |  |  | 469700.7 |  |  | 2015-06-01 15:33 | 2016-04-01 | 2015-07-01 | 2016-01-15
75086 | G7MAINS | R0735 | JT 7988830 Gun Powder Trails | -335.01 |  |  |  |  | 20743.76 |  |  | 2015-06-24 15:44 | 2016-03-01 | 2015-08-01 | 2015-12-15
75086 | G7MAINS | R0738 | JT 7992398 Crown Point | 16590.18 |  |  |  |  | 16590.18 |  |  | 2015-06-24 15:55 | 2017-03-15 | 2016-02-01 | 2016-05-25
75086 | G7MAINS | R0773 | Crown Point Subdivision | 497896.82 |  |  |  |  | 522338.43 |  |  | 2015-06-26 07:02 | 2016-09-30 | 2015-12-01 | 2016-09-02
75086 | G7IMPRPL | R0964 | Replace Banklick Rd Station Inlet P | 263358 |  |  |  |  | 576252.43 |  |  | 2015-07-06 15:00 | 2016-09-10 | 2015-07-01 | 2016-08-27
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | 2017505.06 |  |  |  |  | 2079801.18 |  |  | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7IMPRPL | R0981 | WP23 "AM07" Pressure Test | 828521.39 |  |  |  |  | 828521.39 |  |  | 2015-07-06 16:45 | 2017-02-28 | 2016-02-01 | 2016-10-20
75086 | G7REPL | R1014 | Griffin Industries - UL-27 replacem | 145030.17 |  |  |  |  | 326184.32 |  |  | 2015-07-07 10:38 | 2016-04-15 | 2015-07-01 | 2016-01-10
75086 | G7MAINS | R1468 | Heights Blvd MEA | 36523.05 |  |  |  |  | 62105.29 |  |  | 2015-07-15 13:34 | 2016-07-15 | 2015-08-01 | 2016-03-16
75086 | G7MAINS | R1475 | Cecelia Dr MEA | -83.32 |  |  |  |  | 20696.38 |  |  | 2015-07-15 14:10 | 2016-07-15 | 2015-09-01 | 2016-01-01
75086 | G7MAINS | R1752 | JT 8164269 Lakemont | 24853.63 |  |  |  |  | 28425 |  |  | 2015-07-20 17:33 | 2016-10-30 | 2015-12-01 | 2015-07-02
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 1545519.39 |  |  |  |  | 1582263.62 |  |  | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7MAINS | R2222 | 826 Elizabeth Dr Florence Ky MEA | 214.49 |  |  |  |  | 17528.67 |  |  | 2015-08-05 16:31 | 2016-03-18 | 2015-09-01 | 2016-01-05
75086 | G7MAINS | R2479 | Regal Ridge Dr MEA | 2065.04 |  |  |  |  | 92562.51 |  |  | 2015-08-13 15:18 | 2016-06-03 | 2015-10-01 | 2016-01-21
75086 | G7MAINS | R2646 | 1418 N. Main St Williamstown MEA | 2647.86 |  |  |  |  | 36802.81 |  |  | 2015-08-26 08:20 | 2016-04-23 | 2015-10-01 | 2015-12-31
75086 | G7MAINS | R2817 | JT 8560406 Shadybrook Bluffs | 8282.48 |  |  |  |  | 10243.93 |  |  | 2015-09-04 08:23 | 2016-08-19 | 2015-12-01 | 2016-05-19
75086 | G7IMPRPL | R2898 | AM01 Exposed F/L Structure Install | 140674.2 |  |  |  |  | 203769.32 |  |  | 2015-09-10 15:41 | 2016-05-02 | 2015-09-01 | 2016-02-02
75086 | G7LGMR | R2900 | Cox Rd Station Rpl | 30398.68 |  |  |  |  | 30398.68 |  |  | 2015-09-10 16:08 | 2017-08-01 | 2016-02-01 | 2017-04-11
75086 | G7LGMR | R2901 | STA 838 Mineola Pike - Station | 45225.31 |  |  |  |  | 45225.31 |  |  | 2015-09-10 16:12 | 2018-05-31 | 2016-04-01 | 2018-02-14
75086 | G7MAINS | R2915 | JT 8022710 Arcadia | 1517 |  |  |  |  | 6984.95 |  |  | 2015-09-11 09:38 | 2016-05-26 | 2015-10-01 | 2016-01-19
75086 | G7MAINS | R2925 | JT 8637217 Triple Crown | 15723.83 |  |  |  |  | 15723.83 |  |  | 2015-09-11 10:58 | 2016-08-20 | 2016-01-01 | 2016-06-24
75086 | G7MAINS | R3114 | JT 8728425 Triple Crown Sect 32 | 49489.78 |  |  |  |  | 59508.05 |  |  | 2015-09-24 09:07 | 2016-06-14 | 2015-12-01 | 2016-05-18
75086 | G7MAINS | R3118 | JT 8760245 Triple Crown Sect 29 | 15976.13 |  |  |  |  | 15976.13 |  |  | 2015-09-24 09:23 | 2016-06-28 | 2016-01-01 | 2016-05-31
75086 | G7REPL | R3316 | Glencoe - Webster/Railroad St | 1623.07 |  |  |  |  | 9082.38 |  |  | 2015-09-28 09:36 | 2016-04-09 | 2015-10-01 | 2015-12-31
75086 | G7MAINS | R3386 | Mills Rd Drees Homes MEA | 1380.57 |  |  |  |  | 45531.21 |  |  | 2015-09-30 11:50 | 2016-04-29 | 2015-10-01 | 2016-02-12
75086 | G7MAINS | R3391 | Highwater MEA | 15334.55 |  |  |  |  | 18741 |  |  | 2015-09-30 14:40 | 2016-06-18 | 2015-11-01 | 2016-03-11
75086 | G7LGMR | R3460 | Station 577 (Ky-17 & US-27) | 59208.15 |  |  |  |  | 237165.15 |  |  | 2015-10-05 14:36 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3461 | Station 577 Inlet Piping | -97.56 |  |  |  |  | 6828.92 |  |  | 2015-10-05 15:02 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3462 | Station 577 Outlet Piping | -3.51 |  |  |  |  | 3239.31 |  |  | 2015-10-05 15:10 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7MAINS | R3494 | JT 8245984 Orleans North Phase I | 5987.02 |  |  |  |  | 8800.58 |  |  | 2015-10-07 09:11 | 2016-06-21 | 2015-11-01 | 2016-04-04
75086 | G7MAINS | R3798 | JT 8022787 Brigadoon | 6042.73 |  |  |  |  | 10361.69 |  |  | 2015-10-16 14:49 | 2016-07-15 | 2015-12-01 | 2016-03-17
75086 | G7MAINS | R3801 | JT 8022212 Aosta Valley | 6325.68 |  |  |  |  | 12329.72 |  |  | 2015-10-16 14:56 | 2016-07-15 | 2015-11-01 | 2016-04-18
75086 | G7REPL | R4154 | NKU - Sunset Dr Repl | 44850.6 |  |  |  |  | 88935.97 |  |  | 2015-10-30 08:34 | 2016-08-31 | 2015-12-01 | 2016-07-05
75086 | G7MAINS | R4166 | 1513 Woodside Dr MEA | 26396.59 |  |  |  |  | 27041.14 |  |  | 2015-10-30 11:21 | 2016-07-25 | 2015-12-01 | 2016-05-25
75086 | G7MAINS | R4170 | 5935 Merchants St MEA | 46749.86 |  |  |  |  | 50123.9 |  |  | 2015-10-30 11:39 | 2016-07-18 | 2015-12-01 | 2016-04-20
75086 | G7IMPRPL | R4306 | AM07 Exposed T/L Project | -20.75 |  |  |  |  | 17951.09 |  |  | 2015-11-09 13:31 | 2016-06-30 | 2015-11-01 | 2016-02-09
75086 | G7REPL | R4407 | RP 9097151 AM-01 at Covington | 291898.91 |  |  |  |  | 461552.17 |  |  | 2015-11-11 12:51 | 2017-03-01 | 2015-11-01 | 2016-02-18
75086 | G7MAINS | R4462 | GM 8830449 Coachlight | 12895.32 |  |  |  |  | 13885.07 |  |  | 2015-11-13 14:44 | 2016-06-30 | 2015-12-01 | 2016-04-15
75086 | G7MAINS | R4463 | GM 9001226 Wright Blvd | 27468.57 |  |  |  |  | 27468.57 |  |  | 2015-11-13 15:02 | 2016-08-08 | 2016-02-01 | 2016-06-03
75086 | G7REPL | R4609 | RP 8866200 Ripple Creek | 70227.5 |  |  |  |  | 74927.28 |  |  | 2015-11-19 12:28 | 2016-06-18 | 2015-12-01 | 2016-05-20
75086 | G7IMPRPL | R4858 | AM-09 Segment 3700 Main Rpl | 1458023.26 |  |  |  |  | 1458273.3 |  |  | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | GITKYCAP | R4959 | Rick Analysis Gas Transmission Line | 273.33 |  |  |  |  | 273.33 |  |  | 2015-12-07 16:48 | 2017-01-01 | 2016-04-01 | 2016-12-29
75086 | G7MAINS | R5234 | GO 8623141 Turfway Rd | 67598.71 |  |  |  |  | 70264.32 |  |  | 2015-12-11 14:53 | 2016-07-22 | 2015-12-01 | 2016-05-01
75086 | G7MAINS | R5266 | JT 9122622 Battleridge | 4916.09 |  |  |  |  | 4916.09 |  |  | 2015-12-14 15:36 | 2017-01-31 | 2016-02-01 | 2016-06-16
75086 | G7PUBIMP | R5767 | GO 8346362 KY 9 North recon | 142360.07 |  |  |  |  | 142360.07 |  |  | 2016-01-11 10:41 | 2018-06-01 | 2016-01-01 | 2016-07-12
75086 | G7MAINS | R6359 | GO 9487293 Pat Fanning Way | 73058.45 |  |  |  |  | 73058.45 |  |  | 2016-02-02 10:25 | 2016-10-01 | 2016-02-01 | 2016-07-21
75086 | G7MAINS | R6365 | GO 9487340 Cedar Ln | 27449.74 |  |  |  |  | 27449.74 |  |  | 2016-02-02 10:31 | 2016-12-01 | 2016-03-01 | 2016-07-22
75086 | G7MAINS | R6366 | GO 9609542 Grandview Rd | 79653.52 |  |  |  |  | 79653.52 |  |  | 2016-02-02 10:46 | 2016-12-01 | 2016-02-01 | 2016-07-18
75086 | G7MAINS | R6367 | GO 9487246 Autumn Ln to Low Gap | 317571.85 |  |  |  |  | 317571.85 |  |  | 2016-02-02 10:51 | 2016-10-01 | 2016-02-01 | 2016-08-05
75086 | G7MAINS | R6484 | GO 9694099 208 Vine St | 8089.92 |  |  |  |  | 8089.92 |  |  | 2016-02-04 15:33 | 2016-10-01 | 2016-02-01 | 2016-06-16
75086 | G7MAINS | R6540 | GO 9775945 AA Highway Crossover | 109728.69 |  |  |  |  | 109728.69 |  |  | 2016-02-05 15:35 | 2016-09-30 | 2016-03-01 | 2016-07-29
75086 | G7REPL | R6767 | RPL 9818927 21st St Levee | 362052.7 |  |  |  |  | 362052.7 |  |  | 2016-02-11 13:42 | 2017-04-30 | 2016-06-01 | 2016-12-13
75086 | G7PUBIMP | R6768 | STI 9359472 Robbins Ave | 31437.94 |  |  |  |  | 31437.94 |  |  | 2016-02-11 14:00 | 2016-09-30 | 2016-03-01 | 2016-07-15
75086 | GITKYCAP | R8365 | Gas Fusion Document Classes | 19402.52 |  |  |  |  | 19402.52 |  |  | 2016-03-11 13:41 | 2016-09-30 | 2016-03-01 | 2016-11-23
75086 | G7MAINS | R8374 | GO 9591573 1973 Sarah Lane | 42904.77 |  |  |  |  | 42904.77 |  |  | 2016-03-11 15:38 | 2016-11-13 | 2016-03-01 | 2016-08-19
75086 | G7IMPRPL | R9162 | INT 9146891 Henry Ct & US 27 | 162176.9 |  |  |  |  | 162176.9 |  |  | 2016-03-28 10:17 | 2017-06-30 | 2016-06-01 | 2017-03-01
75086 | GITKYCAP | RISKANSFT | Risk Analysis Software Emergent | 133504.56 |  |  |  |  | 133504.56 |  |  | 2015-12-07 16:24 | 2017-01-01 | 2016-01-01 | 2016-12-29
75086 | G7PUBIMP | S1056 | STI 10177360 Latonia Lakes Str Impr | 95709.69 |  |  |  |  | 95709.69 |  |  | 2016-04-15 16:46 | 2016-10-31 | 2016-04-01 | 2016-09-18
75086 | G7LGMR | S1094 | STA 249: Three Mile - Station | 210792.09 |  |  |  |  | 210792.09 |  |  | 2016-04-18 09:31 | 2020-01-30 | 2016-07-01 | 2017-02-16
75086 | G7MAINS | S2732 | GO 9691430 Sta 836 Inlet Piping | 166792.21 |  |  |  |  | 166792.21 |  |  | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01
75086 | G7MAINS | S2752 | GO 9691542 Sta 836 Outlet Piping | 234646.3 |  |  |  |  | 234646.3 |  |  | 2016-04-29 11:23 | 2018-05-11 | 2016-05-01 | 2016-12-28
75086 | G7PUBIMP | S4545 | STI 10221124 Altavia Ave | 43243.27 |  |  |  |  | 43243.27 |  |  | 2016-05-10 07:49 | 2016-10-31 | 2016-05-01 | 2016-09-14
75086 | G7REPL | S5697 | RPL 10420236 Ft Wright Elem | 1755.86 |  |  |  |  | 1755.86 |  |  | 2016-05-13 08:59 | 2016-10-22 | 2016-05-01 | 2016-10-16
75086 | G7REPL | S6913 | RPL 10348116 Williamstown Exp Main | 22382.27 |  |  |  |  | 22382.27 |  |  | 2016-05-23 09:47 | 2016-11-12 | 2016-07-01 | 2016-12-21
75086 | G7LGMR | S7437 | STA 10565374 Foster Station | 71565.81 |  |  |  |  | 71565.81 |  |  | 2016-06-06 12:25 | 2017-06-30 | 2016-09-01 | 2016-12-09
75086 | G7LGMR | S7568 | STA 822 Cox Rd Outlet | 22723.05 |  |  |  |  | 22723.05 |  |  | 2016-06-08 12:42 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | S7572 | STA 822 Cox Rd Inlet | 52558.51 |  |  |  |  | 52558.51 |  |  | 2016-06-08 12:51 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7PUBIMP | S7874 | STI 4844778 Thomas More Pkwy | 61698.14 |  |  |  |  | 61698.14 |  |  | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7LGMR | S8250 | STA 822 Cox Rd - Station | 106063.06 |  |  |  |  | 106063.06 |  |  | 2016-06-21 14:28 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7MAINS | S8387 | GO 10416501 279 Riverside Pkwy | 18470.94 |  |  |  |  | 18470.94 |  |  | 2016-06-23 15:08 | 2017-01-31 | 2016-06-01 | 2016-10-26
75086 | G7REPL | S8507 | Sta 809 Waterworks Rd Outlet | 1128.72 |  |  |  |  | 1128.72 |  |  | 2016-06-30 10:57 | 2018-12-31 | 2016-10-01
75086 | G7REPL | S8584 | RPL 10117658 Loomis Rd Airport | 4173.73 |  |  |  |  | 4173.73 |  |  | 2016-07-06 10:52 | 2019-04-30 | 2016-08-01
75086 | G7MAINS | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 105029.81 |  |  |  |  | 105029.81 |  |  | 2016-07-12 14:21 | 2017-06-12 | 2016-08-01 | 2016-12-17
75086 | G7PUBIMP | S8820 | STI 10670525 Edgewood & Lyndale | 280125.77 |  |  |  |  | 280125.77 |  |  | 2016-07-20 11:50 | 2017-03-16 | 2016-07-01 | 2016-12-05
75086 | G7MAINS | S8833 | GO 10529464 3876 Burlington Pk | 29062.32 |  |  |  |  | 29062.32 |  |  | 2016-07-21 14:21 | 2017-03-02 | 2016-08-01 | 2016-12-14
75086 | G7MAINS | S8847 | GO 9527853 820 Dolwick Dr | 41433.97 |  |  |  |  | 41433.97 |  |  | 2016-07-25 12:25 | 2017-03-31 | 2016-07-01 | 2017-02-15
75086 | G7MAINS | S9061 | GO 9451838 132 E. Alexandria Pike | 90519.43 |  |  |  |  | 90519.43 |  |  | 2016-08-10 13:33 | 2017-04-30 | 2016-09-01 | 2017-01-12
75086 | G7IMPRPL | S9414 | INT 11119187 AM04 Carntown | 51349.45 |  |  |  |  | 51349.45 |  |  | 2016-08-30 09:53 | 2018-12-16 | 2016-11-01 | 2018-04-15
75086 | G7MAINS | S9476 | GO 10744494 15 Sprial Dr | 167704.48 |  |  |  |  | 167704.48 |  |  | 2016-09-01 09:38 | 2017-04-21 | 2016-09-01 | 2017-02-02
75086 | G7MAINS | S9515 | GO 10692255 236 Wendel H Ford | 49426.72 |  |  |  |  | 49426.72 |  |  | 2016-09-06 10:41 | 2017-04-30 | 2016-10-01 | 2017-02-28
75086 | G7MAINS | S9567 | GO 10865647 9001 US Hwy 42 | 28431.18 |  |  |  |  | 28431.18 |  |  | 2016-09-09 11:32 | 2018-05-30 | 2016-10-01 | 2017-03-14
75086 | G7MAINS | S9584 | GO 10825411 Hawk's Landing | 97788.4 |  |  |  |  | 97788.4 |  |  | 2016-09-12 09:53 | 2017-05-11 | 2016-10-01 | 2017-03-22
75086 | G7LGMR | S9586 | STA 11212247 Erlanger Compressor | 8355.71 |  |  |  |  | 8355.71 |  |  | 2016-09-12 14:54 | 2018-12-31 | 2016-10-01
75086 | G7PUBIMP | S9644 | STI 11229534 Lyndale Rd | 10950.99 |  |  |  |  | 10950.99 |  |  | 2016-09-16 08:49 | 2017-08-28 | 2016-10-01 | 2017-06-15
75086 | G7MAINS | S9655 | GO 10945062 1495 Dolwick | 29269.73 |  |  |  |  | 29269.73 |  |  | 2016-09-16 13:35 | 2017-04-28 | 2016-10-01 | 2017-02-15
75086 | G7MAINS | S9659 | GO 10888391 5905 Merchant St | 3461.47 |  |  |  |  | 3461.47 |  |  | 2016-09-19 09:06 | 2017-08-03 | 2016-12-01 | 2017-05-11
75086 | G7MAINS | S9687 | GO 11090743 1606 Highwater | 2693.65 |  |  |  |  | 2693.65 |  |  | 2016-09-20 10:46 | 2017-06-30 | 2016-10-01 | 2017-03-20
75086 | G7MAINS | S9749 | GO 10916480 2403 Stonewall Tr | 37173.86 |  |  |  |  | 37173.86 |  |  | 2016-09-26 15:59 | 2017-03-15 | 2016-10-01 | 2017-03-08
75086 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 27135.22 |  |  |  |  | 31247.45 |  |  | 2015-03-30 16:38 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 430046.01 |  |  |  |  | 727572.66 |  |  | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SG000358F | SG358CALL | SG 358 - DEE MDM Scale CA Lisa SW | 5272.71 |  |  |  |  | 5272.71 |  |  | 2016-06-17 11:51 | 2017-06-30 | 2016-08-01 | 2017-06-26
75086 | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 58177.44 |  |  |  |  | 58177.44 |  |  | 2016-06-22 12:04 | 2017-06-30 | 2016-06-01 | 2017-06-26
75086 | SG000358F | SG358SGGL | SG 358 - DEE MDM Scale - SGG Licens | 20877.32 |  |  |  |  | 20877.32 |  |  | 2016-06-17 13:43 | 2017-06-30 | 2016-07-01 | 2017-06-26
75086 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 204.3 |  |  |  |  | 204.3 |  |  | 2016-11-01 13:58 | 2018-02-28 | 2016-11-01 | 2018-02-12
75086 | SG000448F | SG448SVR | SG DEE Openway Scale 2016 - Servers | 2120.66 |  |  |  |  | 2120.66 |  |  | 2016-07-14 08:52 | 2017-03-31 | 2016-07-01 | 2017-03-14
75086 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 595.45 |  |  |  |  | 595.45 |  |  | 2016-11-23 11:25 | 2018-12-31 | 2016-11-01
75086 | SGKYCS | SGCSECS | Enterprise Cust systems cap | 0 |  |  |  |  | 1.4552e-11 |  |  | 2010-10-01 | 2014-12-31 | 2010-09-01
75086 | SGITEAMWM | SGDVINTG | Smart Grid Device Integration | 0 |  |  |  |  | 58164.74 |  |  | 2011-06-24 | 2012-12-31 | 2011-07-01 | 2013-03-21
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 1011.54 |  |  |  |  | 6381.04 |  |  | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0 |  |  |  |  | 122795.82 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMMM2C | SG MDM Mass Market 2 - CMS Work | 2696.86 |  |  |  |  | 2699.39 |  |  | 2014-11-03 | 2015-02-15 | 2014-11-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | -2696.86 |  |  |  |  | 35397.81 |  |  | 2014-04-28 | 2015-02-15 | 2014-04-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0 |  |  |  |  | 180397.16 |  |  | 2013-07-12 | 2014-09-30 | 2013-07-01 | 2014-08-19
75086 | SGKYPMO | SGOVH | Grid Solutions Overhead Allocation | 0 |  |  |  |  | 0 |  |  | 2016-01-08 16:28 | 2050-12-31 | 2016-01-01
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -331.15 |  |  |  |  | 2.7 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | GSMARTK | SMARTKYP1 | Gas Smart Implementation Phase 1 | 32520.91 |  |  |  |  | 340241.03 |  |  | 2014-07-02 | 2017-02-07 | 2014-07-01 | 2016-03-14
75086 | GITKYCAP | SMARTPH2 | Gas Smart Data Availability Phase 2 | -3007.01 |  |  |  |  | 1488.07 |  |  | 2015-12-11 15:15 | 2018-06-30 | 2015-12-01
75086 | G7MAINS | T0386 | GO 10848852 5355 Idlewild Rd | 3087.22 |  |  |  |  | 3087.22 |  |  | 2016-11-01 15:01 | 2017-07-31 | 2016-11-01 | 2017-04-03
75086 | G7REPL | T0387 | RPL 11339902 Chesapeake St | 19351.54 |  |  |  |  | 19351.54 |  |  | 2016-11-01 15:08 | 2017-07-06 | 2016-11-01 | 2017-04-09
75086 | G7REPL | T0647 | RPL 11581212 140 Railroad St | 17402.02 |  |  |  |  | 17402.02 |  |  | 2016-11-14 10:54 | 2017-07-31 | 2016-11-01 | 2017-02-14
75086 | G73MILES | T0747 | AM00a Automation of RCV -Alexandria | 8912.87 |  |  |  |  | 8912.87 |  |  | 2016-11-18 11:23 | 2020-01-30 | 2016-12-01
75086 | G7REPL | T1130 | RPL 11859007 Ballyshannon - relocat | -39500 |  |  |  |  | -39500 |  |  | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | FVANKEG | VANKENGAS | Vehicle Area Network | 3697.45 |  |  |  |  | 24833.18 |  |  | 2015-10-09 14:02 | 2017-02-28 | 2015-10-01 | 2016-08-20
75086 | FENABLES | WRTS | Enable WRT & WMSP Software | 49929.66 |  |  |  |  | 71295.3 |  |  | 2015-03-30 16:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
|  |  |  | 31967128.74 | 21963857 | -10003271.74
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2017
Duke Energy Kentucky Gas
Year 2017
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 24930.38 |  |  |  |  | 222974.7 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 307482 | Customer Mobile App | 10270.91 |  |  |  |  | 10270.91 |  |  | 2017-05-08 15:22 | 2019-01-31 | 2017-05-01
75087 | FPIT | 315263BTS | 315263BTS Encryption PH2 | 978.22 |  |  |  |  | 4573.65 |  |  | 2016-10-13 15:38 | 2016-12-31 | 2016-10-01 | 2017-04-23
75087 | FPIT | 315263GDG | 315263GDG Encryption PH2 | 117.51 |  |  |  |  | 4379.44 |  |  | 2016-10-13 12:55 | 2016-12-31 | 2016-11-01 | 2017-06-30
75087 | FPIT | 315263VER | 315263VER Encryption PH2 | 49.76 |  |  |  |  | 3209.47 |  |  | 2016-10-13 16:23 | 2016-12-31 | 2016-12-01 | 2017-06-30
75087 | CUSTCONN | 315986A | Customer Connect - Core | 253543.14 |  |  |  |  | 253543.14 |  |  | 2017-08-10 10:55 | 2022-06-30 | 2017-08-01
75087 | CUSTCONN | 315986B | Customer Connect- Analytics | 31123.7 |  |  |  |  | 31123.7 |  |  | 2017-08-10 13:13 | 2018-09-30 | 2017-08-01 | 2018-09-30
75087 | CUSTCONN | 315986C | Customer Connect- CRM | 33804.23 |  |  |  |  | 33804.23 |  |  | 2017-08-10 14:30 | 2019-02-28 | 2017-08-01
75087 | CUSTCONN | 315986D | Customer Connect- Prepaid Advantage | 72617.9 |  |  |  |  | 72617.9 |  |  | 2017-08-10 15:35 | 2019-12-30 | 2017-08-01
75087 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 52361.83 |  |  |  |  | 52361.83 |  |  | 2017-08-11 10:44 | 2020-06-30 | 2017-08-01
75087 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 62871.57 |  |  |  |  | 62871.57 |  |  | 2017-09-05 18:46 | 2018-10-01 | 2017-09-01 | 2018-10-01
75087 | CUSTCONN | 315986QC | CIS-Quality Center Licenses | 2466.28 |  |  |  |  | 2466.28 |  |  | 2017-08-02 08:14 | 2017-12-31 | 2017-07-01 | 2017-10-31
75087 | FPIT | 325480C | Watson Explorer (Replace Omnifind) | 10901.31 |  |  |  |  | 10901.31 |  |  | 2016-11-30 16:55 | 2018-05-31 | 2016-12-01 | 2018-09-08
75086 | FPIT | 336593EGP | Install CISCO Switch | 369.82 |  |  |  |  | 369.82 |  |  | 2017-07-07 16:16 | 2017-11-30 | 2017-08-01 | 2017-11-30
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 9731.26 |  |  |  |  | 216967.34 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 105.06 |  |  |  |  | 95925.5 |  |  | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVMC | 6CMR70 | Replace C-M 6" Kentucky Blanket | 2754.8 |  |  |  |  | 36610.9 |  |  | 2008-07-31 | 2050-12-31 | 2014-05-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 9920.17 |  |  |  |  | 57187.37 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | 8MCR70 | Replace M-C 8" and Greater | -3485 |  |  |  |  | 210.39 |  |  | 2010-05-05 | 2050-12-31 | 2013-03-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 119637.97 |  |  |  |  | 364896.12 |  |  | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 1126521.33 |  |  |  |  | 3523250.61 |  |  | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 230.65 |  |  |  |  | 239.67 |  |  | 2015-03-30 16:20 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 73870.98 |  |  |  |  | 168336.8 |  |  | 2015-03-30 16:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 19.96 |  |  |  |  | 27.33 |  |  | 2015-03-30 14:15 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | FENABLES | ARMS | Enable ARM Scheduler Software | 82982.86 |  |  |  |  | 153998.29 |  |  | 2015-03-30 16:26 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | GITKYCAP | BOES | Boes Replacement (AGOES) for Gas | 223.97 |  |  |  |  | 63503.99 |  |  | 2015-05-01 11:05 | 2016-06-30 | 2015-08-01 | 2017-01-25
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 50273.37 |  |  |  |  | 94574.48 |  |  | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 519988.05 |  |  |  |  | 665308.23 |  |  | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 72669.25 |  |  |  |  | 120050.14 |  |  | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 922829.66 |  |  |  |  | 6057845.82 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 14280.69 |  |  |  |  | 19230.96 |  |  | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 2357637.64 |  |  |  |  | 11040603.47 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | 2" or less steel C-M Replace | 11744.46 |  |  |  |  | 15500.81 |  |  | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 1789322.03 |  |  |  |  | 3050857.29 |  |  | 2015-03-04 11:36 | 2022-12-31 | 2015-07-01
75086 | FLKY0251G | DUKETCKYG | Fleet On-Road Vehicles - Gas - KY | 20774.38 |  |  |  |  | 20774.38 |  |  | 2009-08-14 | 2050-12-31 | 2010-06-01
75086 | FLKY0251G | DUKETEKYG | Fleet Off-Road Vehicles - KY | 168272.24 |  |  |  |  | 168272.24 |  |  | 2009-08-14 | 2050-12-31 | 2010-06-01
75086 | FENABLEH | ECOMH | Enable ECOM Data Hub | 407.81 |  |  |  |  | 514.71 |  |  | 2015-09-29 10:00 | 2017-10-31 | 2016-01-01 | 2017-11-07
75086 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 54215.41 |  |  |  |  | 82807.85 |  |  | 2015-03-30 16:52 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | EGISH | Enable EGIS Hardware | 363.02 |  |  |  |  | 982.18 |  |  | 2015-03-30 15:51 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | EGISS | Enable EGIS Software | 274172.11 |  |  |  |  | 492711.91 |  |  | 2015-03-30 16:42 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | -295893.51 |  |  |  |  | 50029.53 |  |  | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01
75086 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 13.83 |  |  |  |  | 65.05 |  |  | 2015-03-30 14:50 | 2017-10-31 | 2015-08-01 | 2017-11-07
75086 | FENABLES | EXPDS | Enable Expert Designer Software | 65286.94 |  |  |  |  | 145321.37 |  |  | 2015-03-30 16:33 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7LGMR | G0224 | STA 809 - Waterworks Rd- Station | 9413.37 |  |  |  |  | 53554.78 |  |  | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | G7PUBIMP | G8242 | AM00 - NKU | -1011414.58 |  |  |  |  | 165396.61 |  |  | 2012-08-16 | 2017-05-28 | 2013-04-01 | 2016-02-12
75086 | FPCTAVMKY | G9238 | Vegetation Mgmt Kentucky | -1390.65 |  |  |  |  | -6.1391e-12 |  |  | 2013-01-10 | 2017-08-30 | 2013-01-01 | 2015-02-28
75086 | FPIT | GCTA30062 | INTGO_PI SCADA Data Implementation | 71764.16 |  |  |  |  | 71764.16 |  |  | 2017-08-08 09:43 | 2019-10-30 | 2017-09-01
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | 138204.55 |  |  |  |  | 191519.38 |  |  | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01
75086 | G7LGMR | H0485 | Reg 21K Improvements-Grand & Ft Tho | 4354.55 |  |  |  |  | 166575.31 |  |  | 2013-07-29 | 2015-06-30 | 2013-11-01 | 2014-02-11
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 239782.13 |  |  |  |  | 483716.79 |  |  | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 116272.5 |  |  |  |  | 205901.47 |  |  | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | -6786.25 |  |  |  |  | -1727.09 |  |  | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LCMRS70 | Greater than 2" C-M Steel Replaceme | 8899.09 |  |  |  |  | 8899.09 |  |  | 2017-03-10 10:36 | 2050-12-31 | 2017-09-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 56545.45 |  |  |  |  | 175372.69 |  |  | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 3853.03 |  |  |  |  | 5870.97 |  |  | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 40502.36 |  |  |  |  | 124340.08 |  |  | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | Greater than 2" M-C REPL Steel | 3485 |  |  |  |  | 3485 |  |  | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | GITKYCAP | MAOP7SFTW | Maximum Allowable Operating Pressur | 3303.25 |  |  |  |  | 292263.29 |  |  | 2015-03-12 12:19 | 2016-04-30 | 2015-04-01 | 2016-12-12
75086 | FENABLEH | MAXH | Enable Maximo Hardware | 3238.01 |  |  |  |  | 5926.06 |  |  | 2015-03-30 13:58 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | MAXS | Enable Maximo Software | 561623.77 |  |  |  |  | 1302450.4 |  |  | 2015-03-30 16:21 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 994863.1 |  |  |  |  | 7235403.13 |  |  | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 43958.47 |  |  |  |  | 182099.47 |  |  | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 3028308.72 |  |  |  |  | 13345065.58 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 25496.4 |  |  |  |  | 455616.47 |  |  | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 11567978.2 |  |  |  |  | 15238619.39 |  |  | 2015-03-04 11:18 | 2022-12-31 | 2015-07-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 984557.89 |  |  |  |  | 1437967.01 |  |  | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 70296.48 |  |  |  |  | 97790.7 |  |  | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | 348700.06 |  |  |  |  | 718429.66 |  |  | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7MAINS | MX1470330 | Extending 8" gas main 2085' to feed | 110166.28 |  |  |  |  | 110166.28 |  |  | 2017-10-13 14:01 | 2018-05-28 | 2017-10-01
75086 | G7MAINS | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 8980.59 |  |  |  |  | 8980.59 |  |  | 2017-09-19 10:01 | 2018-05-16 | 2017-10-01 | 2018-02-18
75086 | G7MAINS | MX1990005 | 8001 Veterans Memorial Dr. | 2031.48 |  |  |  |  | 2031.48 |  |  | 2017-10-10 14:01 | 2018-04-28 | 2017-11-01 | 2018-04-03
75086 | G7IMPRPL | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 26641.08 |  |  |  |  | 26641.08 |  |  | 2017-09-11 18:02 | 2019-01-30 | 2017-10-01
75086 | G7REPL | MX1998720 | Safran (Messier Bugatti) Main Rep | -392030.72 |  |  |  |  | -392030.72 |  |  | 2017-10-26 18:02 | 2018-05-01 | 2017-11-01 | 2018-05-20
75086 | G7MAINS | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 7066.93 |  |  |  |  | 7066.93 |  |  | 2017-10-20 10:01 | 2017-11-30 | 2017-11-01 | 2018-04-30
75086 | G7LGMR | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 3721.16 |  |  |  |  | 3721.16 |  |  | 2017-09-22 14:01 | 2018-01-10 | 2017-10-01
75086 | G7LGMR | MX2217911 | STA 863 - GRANDVIEW ROAD | 27825.12 |  |  |  |  | 27825.12 |  |  | 2017-09-22 14:01 | 2019-03-31 | 2017-10-01 | 2018-08-16
75086 | G7LGMR | MX2218039 | INSTALL SCADA EQUIPMENT | 82977.49 |  |  |  |  | 82977.49 |  |  | 2017-09-21 14:01 | 2018-12-31 | 2017-10-01
75086 | G7MAINS | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 4475.45 |  |  |  |  | 4475.45 |  |  | 2017-09-19 14:01 | 2018-01-01 | 2017-10-01 | 2018-04-08
75086 | G7LGMR | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 87783.06 |  |  |  |  | 87783.06 |  |  | 2017-10-06 18:03 | 2019-01-30 | 2017-11-01
75086 | G7LGMR | MX2336558 | STA 865 Southridge Dr | 2793.16 |  |  |  |  | 2793.16 |  |  | 2017-10-18 10:47 | 2018-10-15 | 2017-10-01
75086 | G7IMPRPL | MX6468802 | AM07 Casing 46 Replacement | 1306.27 |  |  |  |  | 1306.27 |  |  | 2017-12-05 14:02 | 2019-01-01 | 2017-12-01
75087 | FPIT | NINT2068S | NINT2068S Replace WebSphere Voice | 139.42 |  |  |  |  | 13227.64 |  |  | 2015-11-16 14:22 | 2016-09-30 | 2015-12-01 | 2017-03-27
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | 640 |  |  |  |  | 160242.57 |  |  | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7LGMR | P7279 | Rossford Avenue (STA #101) | -482319.5 |  |  |  |  | 271566.81 |  |  | 2015-01-14 | 2017-02-15 | 2016-04-01 | 2016-12-28
75087 | FPIT | PCTA481AS | Sitecore | 14689.87 |  |  |  |  | 1170674.74 |  |  | 2014-10-22 | 2016-12-31 | 2014-11-01 | 2017-01-21
75087 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 1593625.32 |  |  |  |  | 2426924.03 |  |  | 2016-02-11 12:05 | 2018-10-31 | 2016-03-01 | 2018-10-31
75086 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 290419.65 |  |  |  |  | 1730230.88 |  |  | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | FENABLES | PPS | Enable PowerPlan Software | 6680.98 |  |  |  |  | 41122.91 |  |  | 2015-03-30 16:57 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | G7IMPRPL | R0964 | Replace Banklick Rd Station Inlet P | 28973.69 |  |  |  |  | 605226.12 |  |  | 2015-07-06 15:00 | 2016-09-10 | 2015-07-01 | 2016-08-27
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | 805872.03 |  |  |  |  | 2885673.21 |  |  | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 9769026.95 |  |  |  |  | 11351290.57 |  |  | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7LGMR | R2901 | STA 838 Mineola Pike - Station | 170601.73 |  |  |  |  | 215827.04 |  |  | 2015-09-10 16:12 | 2018-05-31 | 2016-04-01 | 2018-02-14
75086 | G7MAINS | R3796 | JT 8916678 Freedom Park II | 14281.38 |  |  |  |  | 14281.38 |  |  | 2015-10-16 14:44 | 2017-11-17 | 2017-03-01 | 2017-07-26
75086 | G7REPL | R4154 | NKU - Sunset Dr Repl | 2285.22 |  |  |  |  | 91221.19 |  |  | 2015-10-30 08:34 | 2016-08-31 | 2015-12-01 | 2016-07-05
75086 | G7BIGBON | R4856 | Big Bone 8" IP Main to Richwood | 195481.52 |  |  |  |  | 195481.52 |  |  | 2015-12-02 14:04 | 2018-04-30 | 2017-02-01 | 2017-12-05
75086 | G7IMPRPL | R4858 | AM-09 Segment 3700 Main Rpl | 112017.26 |  |  |  |  | 1570290.56 |  |  | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | G7PUBIMP | R5767 | GO 8346362 KY 9 North recon | 9633.94 |  |  |  |  | 151994.01 |  |  | 2016-01-11 10:41 | 2018-06-01 | 2016-01-01 | 2016-07-12
75086 | G7REPL | R6767 | RPL 9818927 21st St Levee | 242098.37 |  |  |  |  | 604151.07 |  |  | 2016-02-11 13:42 | 2017-04-30 | 2016-06-01 | 2016-12-13
75086 | G7MSCPRD | R8744 | PLNT 10059137 Erlanger Propane | 10.07 |  |  |  |  | 10.07 |  |  | 2016-03-18 09:53 | 2017-05-01 | 2017-02-01
75086 | G7IMPRPL | R9162 | INT 9146891 Henry Ct & US 27 | -383.71 |  |  |  |  | 161793.19 |  |  | 2016-03-28 10:17 | 2017-06-30 | 2016-06-01 | 2017-03-01
75087 | FRCSW | RCSWSWC | Cust Call Ctr Switch Repl | -686.2 |  |  |  |  | 163798.84 |  |  | 2011-07-25 | 2011-12-31 | 2011-08-01 | 2012-03-31
75086 | GITKYCAP | RISKANSFT | Risk Analysis Software Emergent | -26.37 |  |  |  |  | 133478.19 |  |  | 2015-12-07 16:24 | 2017-01-01 | 2016-01-01 | 2016-12-29
75086 | G7PUBIMP | S1056 | STI 10177360 Latonia Lakes Str Impr | -429.93 |  |  |  |  | 95279.76 |  |  | 2016-04-15 16:46 | 2016-10-31 | 2016-04-01 | 2016-09-18
75086 | G7LGMR | S1094 | STA 249: Three Mile - Station | 122975.62 |  |  |  |  | 333767.71 |  |  | 2016-04-18 09:31 | 2020-01-30 | 2016-07-01 | 2017-02-16
75086 | G7MAINS | S2732 | GO 9691430 Sta 836 Inlet Piping | 9791.61 |  |  |  |  | 176583.82 |  |  | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01
75086 | G7MAINS | S2752 | GO 9691542 Sta 836 Outlet Piping | -632.48 |  |  |  |  | 234013.82 |  |  | 2016-04-29 11:23 | 2018-05-11 | 2016-05-01 | 2016-12-28
75086 | G7REPL | S6913 | RPL 10348116 Williamstown Exp Main | 784.41 |  |  |  |  | 23166.68 |  |  | 2016-05-23 09:47 | 2016-11-12 | 2016-07-01 | 2016-12-21
75086 | G7LGMR | S7568 | STA 822 Cox Rd Outlet | 7115.3 |  |  |  |  | 29838.35 |  |  | 2016-06-08 12:42 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | S7572 | STA 822 Cox Rd Inlet | 15236.79 |  |  |  |  | 67795.3 |  |  | 2016-06-08 12:51 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7PUBIMP | S7874 | STI 4844778 Thomas More Pkwy | 11650.37 |  |  |  |  | 73348.51 |  |  | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7LGMR | S8250 | STA 822 Cox Rd - Station | 57937.73 |  |  |  |  | 164000.79 |  |  | 2016-06-21 14:28 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7REPL | S8375 | STA 838 Mineola Pike - Inlet | 54577.01 |  |  |  |  | 54577.01 |  |  | 2016-06-23 09:04 | 2018-12-30 | 2017-08-01 | 2018-02-14
75086 | G7REPL | S8507 | Sta 809 Waterworks Rd Outlet | 17.96 |  |  |  |  | 1146.68 |  |  | 2016-06-30 10:57 | 2018-12-31 | 2016-10-01
75086 | G7REPL | S8584 | RPL 10117658 Loomis Rd Airport | 23.22 |  |  |  |  | 4196.95 |  |  | 2016-07-06 10:52 | 2019-04-30 | 2016-08-01
75086 | G7PUBIMP | S8820 | STI 10670525 Edgewood & Lyndale | 3069.54 |  |  |  |  | 283195.31 |  |  | 2016-07-20 11:50 | 2017-03-16 | 2016-07-01 | 2016-12-05
75086 | G7MAINS | S8847 | GO 9527853 820 Dolwick Dr | 35856.54 |  |  |  |  | 77290.51 |  |  | 2016-07-25 12:25 | 2017-03-31 | 2016-07-01 | 2017-02-15
75086 | G7PUBIMP | S8867 | STI 10873483 Mt Zion Rd | 280747.38 |  |  |  |  | 280747.38 |  |  | 2016-07-26 13:07 | 2018-11-30 | 2017-01-01
75086 | G7IMPRPL | S9414 | INT 11119187 AM04 Carntown | 3538873.2 |  |  |  |  | 3590222.65 |  |  | 2016-08-30 09:53 | 2018-12-16 | 2016-11-01 | 2018-04-15
75086 | G7MAINS | S9476 | GO 10744494 15 Sprial Dr | 24825.33 |  |  |  |  | 192529.81 |  |  | 2016-09-01 09:38 | 2017-04-21 | 2016-09-01 | 2017-02-02
75086 | G7MAINS | S9515 | GO 10692255 236 Wendel H Ford | -59.47 |  |  |  |  | 49367.25 |  |  | 2016-09-06 10:41 | 2017-04-30 | 2016-10-01 | 2017-02-28
75086 | G7MAINS | S9567 | GO 10865647 9001 US Hwy 42 | 66269.38 |  |  |  |  | 94700.56 |  |  | 2016-09-09 11:32 | 2018-05-30 | 2016-10-01 | 2017-03-14
75086 | G7MAINS | S9584 | GO 10825411 Hawk's Landing | 88421.13 |  |  |  |  | 186209.53 |  |  | 2016-09-12 09:53 | 2017-05-11 | 2016-10-01 | 2017-03-22
75086 | G7LGMR | S9586 | STA 11212247 Erlanger Compressor | 181.72 |  |  |  |  | 8537.43 |  |  | 2016-09-12 14:54 | 2018-12-31 | 2016-10-01
75086 | G7PUBIMP | S9644 | STI 11229534 Lyndale Rd | 182947.69 |  |  |  |  | 193898.68 |  |  | 2016-09-16 08:49 | 2017-08-28 | 2016-10-01 | 2017-06-15
75086 | G7MAINS | S9655 | GO 10945062 1495 Dolwick | 1201.37 |  |  |  |  | 30471.1 |  |  | 2016-09-16 13:35 | 2017-04-28 | 2016-10-01 | 2017-02-15
75086 | G7MAINS | S9659 | GO 10888391 5905 Merchant St | 42139.01 |  |  |  |  | 45600.48 |  |  | 2016-09-19 09:06 | 2017-08-03 | 2016-12-01 | 2017-05-11
75086 | G7MAINS | S9687 | GO 11090743 1606 Highwater | 18282.77 |  |  |  |  | 20976.42 |  |  | 2016-09-20 10:46 | 2017-06-30 | 2016-10-01 | 2017-03-20
75086 | G7MAINS | S9749 | GO 10916480 2403 Stonewall Tr | -36.61 |  |  |  |  | 37137.25 |  |  | 2016-09-26 15:59 | 2017-03-15 | 2016-10-01 | 2017-03-08
75086 | FENABLEH | SDDTH | Enable Subdiv Design Tool Hardware | 13.23 |  |  |  |  | 13.23 |  |  | 2015-03-30 15:28 | 2017-10-31 | 2017-06-01 | 2017-11-07
75086 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 59535.28 |  |  |  |  | 90782.73 |  |  | 2015-03-30 16:38 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 1382003.08 |  |  |  |  | 2109575.74 |  |  | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SGKAMIF | SG169MTRS | SG KY AMI Gas Meters - 169 | 4606581.71 |  |  |  |  | 4606581.71 |  |  | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75086 | SG000358F | SG358CALL | SG 358 - DEE MDM Scale CA Lisa SW | 78.6 |  |  |  |  | 5351.31 |  |  | 2016-06-17 11:51 | 2017-06-30 | 2016-08-01 | 2017-06-26
75086 | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 14355.8 |  |  |  |  | 72533.24 |  |  | 2016-06-22 12:04 | 2017-06-30 | 2016-06-01 | 2017-06-26
75086 | SG000358F | SG358HW18 | SG 358 - MDM Scale Hardware Phase 3 | 59043.76 |  |  |  |  | 59043.76 |  |  | 2017-05-30 17:55 | 2018-09-30 | 2017-06-01 | 2018-08-31
75086 | SG000358F | SG358SGGL | SG 358 - DEE MDM Scale - SGG Licens | 311.21 |  |  |  |  | 21188.53 |  |  | 2016-06-17 13:43 | 2017-06-30 | 2016-07-01 | 2017-06-26
75086 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 16002.68 |  |  |  |  | 16206.98 |  |  | 2016-11-01 13:58 | 2018-02-28 | 2016-11-01 | 2018-02-12
75086 | SG000448F | SG448SVR | SG DEE Openway Scale 2016 - Servers | 249.27 |  |  |  |  | 2369.93 |  |  | 2016-07-14 08:52 | 2017-03-31 | 2016-07-01 | 2017-03-14
75086 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 21721.78 |  |  |  |  | 21721.78 |  |  | 2017-04-24 18:13 | 2018-12-31 | 2017-05-01
75086 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 13378.81 |  |  |  |  | 13974.26 |  |  | 2016-11-23 11:25 | 2018-12-31 | 2016-11-01
75086 | SG000540F | SG540SW | DEE Vehicle Area Network | 3026.84 |  |  |  |  | 3026.84 |  |  | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 0.01 |  |  |  |  | 6381.05 |  |  | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGITMTRSY | SGITRNSL | ITRON SG Solutions Program | 0.07 |  |  |  |  | 122795.89 |  |  | 2011-05-24 | 2012-06-30 | 2011-06-01 | 2012-08-31
75086 | SGITMTRSY | SGMDMMM2S | SG MDM Mass Market Project 2 | 0.07 |  |  |  |  | 35397.88 |  |  | 2014-04-28 | 2015-02-15 | 2014-04-01 | 2015-02-17
75086 | SGITMTRSY | SGMDMMMS | SG MDM Mass Market Software | 0.1 |  |  |  |  | 180397.26 |  |  | 2013-07-12 | 2014-09-30 | 2013-07-01 | 2014-08-19
75086 | SGITMTRSY | SGMDMUHBS | SG MDM Usage Hub Software | 0.04 |  |  |  |  | 68297.26 |  |  | 2012-11-30 | 2014-09-16 | 2012-12-01 | 2014-09-23
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | -2.7 |  |  |  |  | 2.934e-11 |  |  | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | GITKYCAP | SMARTPH2 | Gas Smart Data Availability Phase 2 | 23.66 |  |  |  |  | 1511.73 |  |  | 2015-12-11 15:15 | 2018-06-30 | 2015-12-01
75086 | G7MAINS | T0386 | GO 10848852 5355 Idlewild Rd | 21912.12 |  |  |  |  | 24999.34 |  |  | 2016-11-01 15:01 | 2017-07-31 | 2016-11-01 | 2017-04-03
75086 | G7REPL | T0387 | RPL 11339902 Chesapeake St | 24526.53 |  |  |  |  | 43878.07 |  |  | 2016-11-01 15:08 | 2017-07-06 | 2016-11-01 | 2017-04-09
75086 | G7LGMR | T0425 | SCAD 11456765 Mineola Pike Sta | 24813.31 |  |  |  |  | 24813.31 |  |  | 2016-11-03 09:31 | 2018-12-01 | 2017-01-01
75086 | G7LGMR | T0645 | STA 839 Richwood Station | 79560.49 |  |  |  |  | 79560.49 |  |  | 2016-11-14 09:37 | 2018-12-28 | 2017-02-01
75086 | G7LGMR | T0646 | STA 835 Walton - Station | 34467.03 |  |  |  |  | 34467.03 |  |  | 2016-11-14 09:54 | 2018-12-01 | 2017-04-01 | 2018-09-06
75086 | G7REPL | T0647 | RPL 11581212 140 Railroad St | 323.49 |  |  |  |  | 17725.51 |  |  | 2016-11-14 10:54 | 2017-07-31 | 2016-11-01 | 2017-02-14
75086 | G7LGMR | T0746 | AM00a Automation of RCV Cold Spring | 173215.39 |  |  |  |  | 173215.39 |  |  | 2016-11-18 11:04 | 2018-12-30 | 2017-02-01
75086 | G73MILES | T0747 | AM00a Automation of RCV -Alexandria | 154222.49 |  |  |  |  | 163135.36 |  |  | 2016-11-18 11:23 | 2020-01-30 | 2016-12-01
75086 | G7BIGBON | T0881 | Big Bone Odorant Station - SCADA | 108899.64 |  |  |  |  | 108899.64 |  |  | 2016-12-01 12:00 | 2018-12-01 | 2017-04-01 | 2018-08-05
75086 | G7REPL | T1130 | RPL 11859007 Ballyshannon - relocat | 39755.61 |  |  |  |  | 255.61 |  |  | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | G7MAINS | T1131 | GO 11485457 1962 SARAH LN; | 28532.48 |  |  |  |  | 28532.48 |  |  | 2016-12-20 12:02 | 2017-07-01 | 2017-01-01 | 2017-05-15
75086 | G7MAINS | T1135 | GO 11648289 1099 KEATING DR COLD S | 12528.78 |  |  |  |  | 12528.78 |  |  | 2016-12-20 12:13 | 2017-07-01 | 2017-02-01 | 2017-05-22
75086 | G73MILES | T1437 | STA 249: Three Mile Rd | 610745.8 |  |  |  |  | 610745.8 |  |  | 2017-01-05 11:19 | 2018-06-01 | 2017-01-01
75086 | G7LGMR | T1465 | STA 855 Taylor Mill Rd - Station | 69936.98 |  |  |  |  | 69936.98 |  |  | 2017-01-06 16:24 | 2018-04-19 | 2017-03-01 | 2018-04-24
75086 | G7LGMR | T1485 | STA 855 Taylor Mill Rd - Inlet | 16747.95 |  |  |  |  | 16747.95 |  |  | 2017-01-09 11:13 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7LGMR | T1486 | STA 855 Taylor Mill Rd - Outlet | 7961.18 |  |  |  |  | 7961.18 |  |  | 2017-01-09 11:23 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7IMPRPL | T1525 | AM02 Exposed Main in Southgate, KY | 105870.05 |  |  |  |  | 105870.05 |  |  | 2017-01-12 09:24 | 2018-09-30 | 2017-01-01
75086 | G7MAINS | T1715 | GO 11582821 2400 Litton Ln | 75914.62 |  |  |  |  | 75914.62 |  |  | 2017-01-25 09:05 | 2018-04-15 | 2017-03-01 | 2017-09-02
75086 | G7MAINS | T1737 | GO 11797721 Matinee Blvd | 37889.3 |  |  |  |  | 37889.3 |  |  | 2017-01-25 13:07 | 2017-12-06 | 2017-02-01 | 2017-10-07
75086 | G7REPL | T1796 | Showcase AM07 | -514972.06 |  |  |  |  | -514972.06 |  |  | 2017-01-27 15:35 | 2018-12-31 | 2017-01-01 | 2018-08-09
75086 | G7LGMR | T2218 | STA 838 Mineola Pike - Outlet | 10414.05 |  |  |  |  | 10414.05 |  |  | 2017-02-15 15:45 | 2018-08-31 | 2017-05-01 | 2008-02-14
75086 | G7REPL | T2230 | RPL 20745900 Hudson Ave | -49319.64 |  |  |  |  | -49319.64 |  |  | 2017-02-16 14:11 | 2018-03-31 | 2017-02-01 | 2017-09-28
75086 | G7MAINS | T2639 | GO 20629592 89 Mel Lawn Dr | 3380.57 |  |  |  |  | 3380.57 |  |  | 2017-03-03 07:16 | 2017-11-30 | 2017-03-01 | 2017-06-29
75086 | G7PUINEW | T2904 | MTR 11540114 1 Carbon Way | 2064.02 |  |  |  |  | 2064.02 |  |  | 2017-03-08 13:44 | 2018-12-31 | 2017-12-01
75086 | G7LGMR | T4002 | STA 20933317 Erlanger CP | 2393.38 |  |  |  |  | 2393.38 |  |  | 2017-03-17 11:42 | 2018-12-30 | 2017-08-01
75086 | G73MILES | T4422 | AM07 Barleycorns | 72640.26 |  |  |  |  | 72640.26 |  |  | 2017-03-22 16:39 | 2020-03-31 | 2017-04-01
75086 | G7LGMR | T4893 | Mineola Pike STA Meter Rep & Panels | 33460.43 |  |  |  |  | 33460.43 |  |  | 2017-03-28 11:26 | 2018-12-30 | 2017-05-01
75086 | G7LGMR | T5473 | SCAD 21012299 Pressure Transmiitter | 47382.04 |  |  |  |  | 47382.04 |  |  | 2017-03-31 07:27 | 2018-12-01 | 2017-06-01
75086 | G7MAINS | T7104 | GO 11376429 Lot 14 Norbotten Dr | 24076.03 |  |  |  |  | 24076.03 |  |  | 2017-04-13 10:28 | 2018-02-28 | 2017-05-01 | 2017-10-05
75086 | G7IMPRPL | T7752 | AM07 Grey Stable Ln | 73105.68 |  |  |  |  | 73105.68 |  |  | 2017-05-01 16:13 | 2018-09-15 | 2017-05-01 | 2018-06-15
75086 | G7LGMR | T7778 | SCAD 21153712 KY | 421.46 |  |  |  |  | 421.46 |  |  | 2017-05-03 08:00 | 2018-06-29 | 2017-05-01
75086 | G7LGMR | T7966 | STA 859 Banklick Rd - Station | 4318.49 |  |  |  |  | 4318.49 |  |  | 2017-05-10 15:15 | 2018-07-01 | 2017-09-01 | 2018-07-17
75086 | G7MAINS | T8147 | GO 21080428 Beech Dr. | 22296.38 |  |  |  |  | 22296.38 |  |  | 2017-05-22 14:58 | 2018-04-14 | 2017-07-01 | 2017-12-11
75086 | G7REPL | T8295 | RPL 21421581 Latonia Lakes | 208485.17 |  |  |  |  | 208485.17 |  |  | 2017-05-30 16:11 | 2018-03-30 | 2017-06-01 | 2017-10-15
75086 | G7PUBIMP | T8343 | STI 20956764 Weaver Rd. | 49048.27 |  |  |  |  | 49048.27 |  |  | 2017-05-31 13:21 | 2018-05-01 | 2017-07-01 | 2017-11-29
75086 | G7LGMR | T8405 | WALTON-NICHOLS AM03 RCV Valve | 514.27 |  |  |  |  | 514.27 |  |  | 2017-06-02 11:04 | 2019-04-20 | 2017-06-01
75086 | G7LGMR | T9338 | STA 809 Waterworks Dr - Station | 16683.62 |  |  |  |  | 16683.62 |  |  | 2017-07-14 10:03 | 2018-09-01 | 2017-09-01
75086 | FENABLEH | WRTH | Enable WRT & WMSP Hardware | 16.54 |  |  |  |  | 16.54 |  |  | 2015-03-30 14:39 | 2017-10-31 | 2017-06-01 | 2017-11-07
75086 | FENABLES | WRTS | Enable WRT & WMSP Software | 78014.83 |  |  |  |  | 149310.13 |  |  | 2015-03-30 16:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
|  |  |  | 50508222.9 | 43830565 | -6677657.9
(a) Duke Energy Kentucky does not maintain capital budget data at the individual project level

## 2018
Duke Energy Kentucky Gas
Year 2018
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 66165.25 |  | 66165.25 |  |  | 289139.95 | 0 | 289139.95 | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 307482 | Customer Mobile App | 20472.62 |  | 20472.62 |  |  | 30743.53 | 19937 | 10806.53 | 2017-05-08 15:22 | 2019-06-25 | 2017-05-01 | 2019-06-25
75087 | CUSTCONN | 315986A | Customer Connect - Core | 158606.99 |  | 158606.99 |  |  | 412150.13 | 2325960.3 | -1913810.17 | 2017-08-10 10:55 | 2022-12-05 | 2017-08-01
75087 | CUSTCONN | 315986B | Customer Connect- Analytics | 77586.31 |  | 77586.31 |  |  | 108710.01 | 69801.07 | 38908.94 | 2017-08-10 13:13 | 2018-09-30 | 2017-08-01 | 2018-09-30
75087 | CUSTCONN | 315986C | Customer Connect- Release 2 | 180602.92 |  | 180602.92 |  |  | 214407.15 | 187946.4 | 26460.75 | 2017-08-10 14:30 | 2019-05-28 | 2017-08-01 | 2019-06-18
75087 | CUSTCONN | 315986D | Customer Connect- Release 3 | 33740.08 |  | 33740.08 |  |  | 106357.98 | 280416.54 | -174058.56 | 2017-08-10 15:35 | 2019-12-30 | 2017-08-01 | 2019-12-31
75087 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 12574.69 |  | 12574.69 |  |  | 64936.52 | 117210.08 | -52273.56 | 2017-08-11 10:44 | 2020-09-01 | 2017-08-01 | 2020-09-01
75087 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 103840.7 |  | 103840.7 |  |  | 166712.27 | 43856 | 122856.27 | 2017-09-05 18:46 | 2018-10-01 | 2017-09-01 | 2018-10-01
75087 | CUSTCONN | 315986HW4 | Customer Connect- Hardware Proj 2 | 68740.58 |  | 68740.58 |  |  | 68740.58 | 53607 | 15133.58 | 2018-08-31 12:34 | 2019-06-01 | 2018-08-01 | 2019-08-01
75086 | FPIT | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 22896.31 |  | 22896.31 |  |  | 22896.31 | 73735 | -50838.69 | 2018-06-12 13:16 | 2019-04-21 | 2018-07-01 | 2019-04-29
75086 | FPIT | 323850001 | Fleet Asset Lifecycle & Mobile Solu | 11956.76 |  | 11956.76 |  |  | 11956.76 | 28034 | -16077.24 | 2018-04-25 09:31 | 2020-02-15 | 2018-04-01 | 2020-02-11
75087 | FPIT | 325480C | Watson Explorer (Replace Omnifind) | 2373.66 |  | 2373.66 |  |  | 13274.97 | 12926.83 | 348.14 | 2016-11-30 16:55 | 2018-05-31 | 2016-12-01 | 2018-09-08
75087 | FPIT | 336593019 | New Call Ctr SIP Trunks | 10066.15 |  | 10066.15 |  |  | 10066.15 | 10444 | -377.85 | 2018-03-14 16:47 | 2020-03-31 | 2018-03-01 | 2020-03-31
75086 | FPIT | 338802003 | EAM Platform Optimization | 10102.56 |  | 10102.56 |  |  | 10102.56 | 147321.02 | -137218.46 | 2018-04-25 14:30 | 2020-05-30 | 2018-06-01 | 2020-03-31
75086 | FPIT | 338802004 | Mobile Durable Team | 25518.77 |  | 25518.77 |  |  | 25518.77 | 52783 | -27264.23 | 2018-09-17 12:23 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802005 | Maximo Durable Team | 12463.41 |  | 12463.41 |  |  | 12463.41 | 33459 | -20995.59 | 2018-09-13 15:18 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802008 | EcoSys Durable Team Acciunting | 1407.59 |  | 1407.59 |  |  | 1407.59 | 52026 | -50618.41 | 2018-09-13 10:17 | 2020-03-30 | 2018-09-01 | 2020-03-30
75087 | FPIT | 344598001 | Duke Customer IVR Replacement | 27260.6 |  | 27260.6 |  |  | 27260.6 | 197081 | -169820.4 | 2018-04-10 15:29 | 2020-01-28 | 2018-04-01 | 2020-01-30
75086 | FPIT | 347565014 | 2018 Cisco EOL KY Phase 1 | 379288.07 |  | 379288.07 |  |  | 379288.07 | 17736 | 361552.07 | 2018-02-20 17:32 | 2019-07-30 | 2018-03-01 | 2019-07-31
75086 | G7SERVNEW | 4CMNEW70 | Install New C-M 4" | 38714.85 |  | 38714.85 |  |  | 255682.19 | 1 | 255681.19 | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7SERVNEW | 6MCNEW70 | Install New M-C 6" | 10479.16 |  | 10479.16 |  |  | 67666.53 | 1 | 67665.53 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 46526.92 |  | 46526.92 |  |  | 411423.04 | 350000 | 61423.04 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 875866.04 |  | 875866.04 |  |  | 4399116.65 | 14500000 | -10100883.35 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FENABLEH | ARCGH | Enable ArcGIS/ESRI Hardware | 0.04 |  | 0.04 |  |  | 239.71 | 151 | 88.71 | 2015-03-30 16:20 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | ARCGS | Enable ArcGIS/ESRI Software | 2760.64 |  | 2760.64 |  |  | 171097.44 | 138916 | 32181.44 | 2015-03-30 16:49 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | ARMH | Enable ARM Scheduler Hardware | 0.07 |  | 0.07 |  |  | 27.4 | 151 | -123.6 | 2015-03-30 14:15 | 2017-10-31 | 2015-10-01 | 2017-11-07
75086 | FENABLES | ARMS | Enable ARM Scheduler Software | 3144.41 |  | 3144.41 |  |  | 157142.7 | 138916 | 18226.7 | 2015-03-30 16:26 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 44987.78 |  | 44987.78 |  |  | 139562.26 | 725000 | -585437.74 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 979921.81 |  | 979921.81 |  |  | 1645230.04 | 1250000 | 395230.04 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 32287.73 |  | 32287.73 |  |  | 152337.87 | 800000 | -647662.13 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 240478.76 |  | 240478.76 |  |  | 6298324.58 | 1 | 6298323.58 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 93469.4 |  | 93469.4 |  |  | 112700.36 | 5000000 | -4887299.64 | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 475189.65 |  | 475189.65 |  |  | 11515793.12 | 0 | 11515793.12 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | 2" or less steel C-M Replace | 27063.3 |  | 27063.3 |  |  | 42564.11 | 1000000 | -957435.89 | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 3810061 |  | 3810061 |  |  | 6860918.29 | 20388002 | -13527083.71 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | G7REPL | E4280 | Dry Creek LP03 R/W | -8.49 |  | -8.49 |  |  | 11.86 | 9510 | -9498.14 | 2009-02-11 | 2014-02-11 | 2009-05-01 | 2009-09-10
75086 | FENABLEH | ECOMH | Enable ECOM Data Hub | 0.05 |  | 0.05 |  |  | 514.76 | 477 | 37.76 | 2015-09-29 10:00 | 2017-10-31 | 2016-01-01 | 2017-11-07
75086 | FENABLES | ECOMS | Enable ECOM Data Hub Software | 1723.72 |  | 1723.72 |  |  | 84531.57 | 82103 | 2428.57 | 2015-03-30 16:52 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLEH | EGISH | Enable EGIS Hardware | 0.2 |  | 0.2 |  |  | 982.38 | 853 | 129.38 | 2015-03-30 15:51 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | EGISS | Enable EGIS Software | 8927.46 |  | 8927.46 |  |  | 501639.37 | 466828 | 34811.37 | 2015-03-30 16:42 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | -50030.36 |  | -50030.36 |  |  | -0.83 | 511967.66 | -511968.49 | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01 | 2019-03-31
75086 | FENABLEH | EXPDH | Enable Expert Designer Hardware | 0.05 |  | 0.05 |  |  | 65.1 | 95 | -29.9 | 2015-03-30 14:50 | 2017-10-31 | 2015-08-01 | 2017-11-07
75086 | FENABLES | EXPDS | Enable Expert Designer Software | 5458.32 |  | 5458.32 |  |  | 150779.69 | 101202 | 49577.69 | 2015-03-30 16:33 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7LGMR | G3775 | Lafarge Install Cover-Meas STA 704 | -5.75 |  | -5.75 |  |  | 779.71 | 6412.99 | -5633.28 | 2011-06-23 | 2012-06-30 | 2011-08-01 | 2011-12-20
75086 | CASINGKY | G7752 | Casing #87 BS Turkeyfoot AM07 | -3395.54 |  | -3395.54 |  |  | 653827.15 | 540264.1 | 113563.05 | 2012-06-05 | 2013-06-30 | 2012-08-01 | 2013-01-01
75086 | OM75086 | GASKYIND | Indirect Pool | 749.24 |  | 749.24 |  |  | 822.78 | 0 | 822.78 | 2008-07-01 | 2020-12-31 | 2008-07-01
75086 | FPIT | GCTA30060 | Consolidated SCADA App Analysis | 45801.14 |  | 45801.14 |  |  | 45801.14 | 149205 | -103403.86 | 2017-04-11 15:19 | 2020-06-30 | 2017-04-01 | 2020-06-30
75086 | FPIT | GCTA30073 | Project 2 Gas Supply System | 296642.62 |  | 296642.62 |  |  | 296642.62 | 853149 | -556506.38 | 2017-03-30 17:09 | 2021-03-31 | 2017-07-01 | 2021-03-31
75086 | FPIT | GCTA30114 | Sales Force Automation Conso Strate | 18326.37 |  | 18326.37 |  |  | 18326.37 | 0 | 18326.37 | 2017-06-21 11:37 | 2020-11-30 | 2017-10-01 | 2020-11-10
75086 | FPIT | GCTA30128 | INTGO_Conso Gas Eng Calculators | 3834.47 |  | 3834.47 |  |  | 3834.47 | 28617 | -24782.53 | 2017-06-30 10:05 | 2019-10-31 | 2017-08-01 | 2019-10-31
75086 | FPIT | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 147627.77 |  | 147627.77 |  |  | 147627.77 | 513619 | -365991.23 | 2018-05-21 15:50 | 2019-12-29 | 2018-06-01 | 2019-12-01
75086 | FPIT | GCTA31738 | INTET-Enterprise Data Platform | 3991.87 |  | 3991.87 |  |  | 3991.87 | 28965 | -24973.13 | 2017-06-09 09:52 | 2018-07-30 | 2017-10-01 | 2018-07-31
75086 | FPIT | GCTA33039 | INTGO_Consolidated CAD Tools | 11099.87 |  | 11099.87 |  |  | 11099.87 | 120205 | -109105.13 | 2018-06-19 11:18 | 2020-09-24 | 2018-08-01 | 2020-03-31
75086 | FPIT | GCTA43704 | Natural Gas Bus Contractor Registra | 7316.68 |  | 7316.68 |  |  | 7316.68 | 37076 | -29759.32 | 2018-10-10 11:35 | 2020-03-18 | 2018-10-01 | 2020-01-18
75086 | FPIT | GCTA4700B | INTGO_Traceability Form FDC | 166 |  | 166 |  |  | 166 | 215691 | -215525 | 2018-12-06 13:26 | 2021-03-31 | 2018-12-01 | 2021-03-14
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | 39607.72 |  | 39607.72 |  |  | 231127.1 | 136600 | 94527.1 | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01 | 2019-08-30
75086 | G7MAINS | H1364 | Sutter Drive Main Extension | -1.9 |  | -1.9 |  |  | 550.46 | 1 | 549.46 | 2013-12-02 | 2014-11-30 | 2015-08-01 | 2015-12-09
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 289671.64 |  | 289671.64 |  |  | 773388.43 | 800000 | -26611.57 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | RESKYGAS | KMW417109 | New furniture assemblies | 3328 |  | 3328 |  |  | 3328 | 23280 | -19952 | 2017-11-07 12:24 | 2018-03-31 | 2018-03-01 | 2018-04-25
75086 | RESKYGAS | KMW431275 | New furniture assembly | 21979.98 |  | 21979.98 |  |  | 21979.98 | 20177 | 1802.98 | 2017-12-27 11:32 | 2018-05-30 | 2018-02-01 | 2018-05-14
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 19785.09 |  | 19785.09 |  |  | 225686.56 | 2500000 | -2274313.44 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | 17819.43 |  | 17819.43 |  |  | 16092.34 | 2500000 | -2483907.66 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LCMSP70 | ASRP Greater than 2" C-M Install | -266782.9 |  | -266782.9 |  |  | -265974.62 | 10000000 | -10265974.62 | 2016-01-13 11:25 | 2019-12-31 | 2016-07-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 41445.11 |  | 41445.11 |  |  | 216817.8 | 2500000 | -2283182.2 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 16017.63 |  | 16017.63 |  |  | 21888.6 | 2500000 | -2478111.4 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 74160.06 |  | 74160.06 |  |  | 198500.14 | 2500000 | -2301499.86 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | Greater than 2" M-C REPL Steel | 2789.98 |  | 2789.98 |  |  | 6274.98 | 1000000 | -993725.02 | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | FENABLEH | MAXH | Enable Maximo Hardware | 0.38 |  | 0.38 |  |  | 5926.44 | 6456 | -529.56 | 2015-03-30 13:58 | 2017-10-31 | 2015-06-01 | 2017-11-07
75086 | FENABLES | MAXS | Enable Maximo Software | 19729.53 |  | 19729.53 |  |  | 1322179.93 | 942175 | 380004.93 | 2015-03-30 16:21 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 1594376.68 |  | 1594376.68 |  |  | 8829779.81 | 1 | 8829778.81 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 18745.88 |  | 18745.88 |  |  | 200845.35 | 1 | 200844.35 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1082714.1 |  | 1082714.1 |  |  | 14427779.68 | 0 | 14427779.68 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 61528.59 |  | 61528.59 |  |  | 517145.06 | 0 | 517145.06 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 7601407.64 |  | 7601407.64 |  |  | 22840027.03 | 19954384 | 2885643.03 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | FMDT2017 | MDTKE17 | CF53 Purchases for MDT Replac | 7750.27 |  | 7750.27 |  |  | 7750.27 | 33851 | -26100.73 | 2018-02-07 15:38 | 2020-06-01 | 2018-02-01 | 2020-05-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 556511.38 |  | 556511.38 |  |  | 1994478.39 | 10000000 | -8005521.61 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 1.1 |  | 1.1 |  |  | 97791.8 | 120161 | -22369.2 | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | 10745.67 |  | 10745.67 |  |  | 729175.33 | 649497 | 79678.33 | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7REPL | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | -69493.25 |  | -69493.25 |  |  | -69493.25 | 64213.24 | -133706.49 | 2018-12-12 18:01 | 2019-11-21 | 2018-12-01 | 2019-11-27
75086 | GMAINS | MX0225249 | Litton Ln. PRESSURE IMPROVEMENT PRO | 22874.75 |  | 22874.75 |  |  | 22874.75 | 133009.25 | -110134.5 | 2018-12-06 18:01 | 2019-03-10 | 2018-12-01 | 2019-04-10
75086 | G7PUBIMP | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 1294366.21 |  | 1294366.21 |  |  | 1294366.21 | 1689689.28 | -395323.07 | 2018-04-26 10:01 | 2018-08-25 | 2018-05-01 | 2019-01-22
75086 | G7PUBIMP | MX0790794 | Arlington Rd. Roadway IMP | 248909.98 |  | 248909.98 |  |  | 248909.98 | 227712 | 21197.98 | 2018-01-23 20:20 | 2018-03-30 | 2018-03-01 | 2018-09-26
75086 | G7PUBIMP | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 503802.08 |  | 503802.08 |  |  | 503802.08 | 274447.64 | 229354.44 | 2018-07-19 18:03 | 2018-10-28 | 2018-07-01 | 2018-12-19
75086 | G7MAINS | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 129037.35 |  | 129037.35 |  |  | 239203.63 | 65934.9 | 173268.73 | 2017-10-13 14:01 | 2018-05-28 | 2017-10-01 | 2018-04-17
75086 | G7MAINS | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 5966.86 |  | 5966.86 |  |  | 14947.45 | 21108.51 | -6161.06 | 2017-09-19 10:01 | 2018-05-16 | 2017-10-01 | 2018-02-18
75086 | G7MAINS | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 44193.99 |  | 44193.99 |  |  | 44193.99 | 59353.94 | -15159.95 | 2018-03-26 14:06 | 2018-08-03 | 2018-04-01 | 2019-01-06
75086 | G7LGMR | MX1715658 | STA 809 - WATERWORKS RD - Station | 190108.74 |  | 190108.74 |  |  | 190108.74 | 258620 | -68511.26 | 2017-12-05 10:02 | 2019-03-31 | 2018-03-01 | 2018-09-08
75086 | G7MAINS | MX1990005 | 8001 Veterans Memorial Dr. | 22194.24 |  | 22194.24 |  |  | 24225.72 | 7192.72 | 17033 | 2017-10-10 14:01 | 2018-04-28 | 2017-11-01 | 2018-04-03
75086 | G7IMPRPL | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 571504.37 |  | 571504.37 |  |  | 598145.45 | 436474.83 | 161670.62 | 2017-09-11 18:02 | 2019-07-31 | 2017-10-01 | 2019-09-10
75086 | G7REPL | MX1998720 | Safran (Messier Bugatti) Main Rep | 405920.88 |  | 405920.88 |  |  | 13890.16 | 436546.75 | -422656.59 | 2017-10-26 18:02 | 2018-05-01 | 2017-11-01 | 2018-05-20
75086 | G7MAINS | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 67557.3 |  | 67557.3 |  |  | 74624.23 | 50913.96 | 23710.27 | 2017-10-20 10:01 | 2017-11-30 | 2017-11-01 | 2018-04-30
75086 | G7MAINS | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 25925.89 |  | 25925.89 |  |  | 25925.89 | 13475.07 | 12450.82 | 2017-12-14 18:02 | 2018-02-09 | 2018-01-01 | 2018-05-20
75086 | G7MREG118 | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 8660.39 |  | 8660.39 |  |  | 12381.55 | 87907.04 | -75525.49 | 2017-09-22 14:01 | 2022-03-31 | 2017-10-01
75086 | G7LGMR | MX2217911 | STA 863 - GRANDVIEW ROAD | 294185.12 |  | 294185.12 |  |  | 322010.24 | 199415.84 | 122594.4 | 2017-09-22 14:01 | 2019-03-31 | 2017-10-01 | 2018-08-16
75086 | G7MAINS | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 184671.84 |  | 184671.84 |  |  | 184671.84 | 57107 | 127564.84 | 2018-01-30 14:01 | 2018-09-01 | 2018-03-01 | 2018-08-16
75086 | G7MAINS | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 116478.72 |  | 116478.72 |  |  | 116478.72 | 138689 | -22210.28 | 2018-01-30 18:02 | 2018-07-01 | 2018-03-01 | 2018-08-16
75086 | G7LGMR | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 133671.97 |  | 133671.97 |  |  | 216649.46 | 411228.18 | -194578.72 | 2017-09-21 14:01 | 2020-07-10 | 2017-10-01 | 2020-09-15
75086 | G7MAINS | MX2243303 | STA 809 - WATERWORKS RD INLET | 158457.71 |  | 158457.71 |  |  | 158457.71 | 269953 | -111495.29 | 2018-01-30 18:02 | 2018-07-01 | 2018-03-01 | 2018-09-08
75086 | G7MAINS | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 8059.8 |  | 8059.8 |  |  | 8059.8 | 245005 | -236945.2 | 2018-01-30 18:02 | 2018-07-01 | 2018-03-01 | 2018-09-08
75086 | G7MAINS | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 68801.75 |  | 68801.75 |  |  | 73277.2 | 30707.14 | 42570.06 | 2017-09-19 14:01 | 2018-01-01 | 2017-10-01 | 2018-04-08
75086 | G7LGMR | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 1899258.97 |  | 1899258.97 |  |  | 1987042.03 | 12669920 | -10682877.97 | 2017-10-06 18:03 | 2019-08-15 | 2017-11-01 | 2019-09-19
75086 | G7LGMR | MX2336558 | STA 865 Southridge Dr | 53154.54 |  | 53154.54 |  |  | 55947.7 | 334647 | -278699.3 | 2017-10-18 10:47 | 2019-06-01 | 2017-10-01 | 2019-06-19
75086 | G7MAINS | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 3409.66 |  | 3409.66 |  |  | 3409.66 | 51328.32 | -47918.66 | 2018-06-04 10:02 | 2019-06-01 | 2018-07-01 | 2019-06-17
75086 | G7MAINS | MX2336650 | INSTALL STATION OUTLET PIPING | 1573.98 |  | 1573.98 |  |  | 1573.98 | 45232.32 | -43658.34 | 2018-06-04 10:02 | 2018-11-01 | 2018-07-01 | 2019-06-19
75086 | G7PUBIMP | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 31675.34 |  | 31675.34 |  |  | 31675.34 | 129952.9 | -98277.56 | 2018-05-14 14:02 | 2018-08-26 | 2018-05-01 | 2018-10-24
75086 | G7PUBIMP | MX2541899 | KY-36/I-75 Interchange Reconstruct | 666779.33 |  | 666779.33 |  |  | 666779.33 | 906757 | -239977.67 | 2018-03-02 10:01 | 2018-06-03 | 2018-04-01 | 2018-11-02
75086 | G7MAINS | MX2663890 | STA 859 - BANKLICK RD -Inlet | 54031.84 |  | 54031.84 |  |  | 54031.84 | 59964.09 | -5932.25 | 2018-01-29 18:02 | 2018-07-01 | 2018-02-01 | 2018-07-17
75086 | G7MAINS | MX2663986 | STA 859 - BANKLICK RD OUTLET | 326586.24 |  | 326586.24 |  |  | 326586.24 | 77096.68 | 249489.56 | 2018-01-29 18:02 | 2018-07-01 | 2018-02-01 | 2018-07-17
75086 | G7MAINS | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 11048.35 |  | 11048.35 |  |  | 11048.35 | 8634.01 | 2414.34 | 2018-01-04 14:01 | 2018-02-28 | 2018-02-01 | 2018-05-28
75086 | G7MAINS | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 49793.9 |  | 49793.9 |  |  | 49793.9 | 53677.2 | -3883.3 | 2018-03-26 14:02 | 2018-10-20 | 2018-04-01 | 2018-08-19
75086 | G7IMPRPL | MX6468802 | AM07 Casing #46 Replacement | 1767733.32 |  | 1767733.32 |  |  | 1769039.59 | 2040466 | -271426.41 | 2017-12-05 14:02 | 2019-01-01 | 2017-12-01 | 2019-01-12
75086 | G7MAINS | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 36256.81 |  | 36256.81 |  |  | 36256.81 | 34074.87 | 2181.94 | 2018-02-13 14:01 | 2018-04-13 | 2018-03-01 | 2018-07-18
75086 | G7LGMR | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 34526.02 |  | 34526.02 |  |  | 34526.02 | 106314.24 | -71788.22 | 2017-12-15 14:01 | 2021-03-31 | 2018-02-01
75086 | G7PUBIMP | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 44170.59 |  | 44170.59 |  |  | 44170.59 | 279194 | -235023.41 | 2018-03-02 10:01 | 2018-05-25 | 2018-03-01 | 2018-10-25
75086 | G7MAINS | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 28171.33 |  | 28171.33 |  |  | 28171.33 | 92300.06 | -64128.73 | 2018-09-04 18:02 | 2018-11-09 | 2018-10-01 | 2019-04-03
75086 | G7STA876 | MX6800938 | STA 876 WARSAW TOWN BORDER- Station | 12712.27 |  | 12712.27 |  |  | 12712.27 | 252984 | -240271.73 | 2018-01-10 18:02 | 2021-09-06 | 2018-01-01
75086 | G7MAINS | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 22240.26 |  | 22240.26 |  |  | 22240.26 | 38542.37 | -16302.11 | 2018-02-20 18:02 | 2018-04-09 | 2018-03-01 | 2018-10-04
75086 | G7REPL | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 119038.78 |  | 119038.78 |  |  | 119038.78 | 64481.4 | 54557.38 | 2018-03-29 18:04 | 2018-07-15 | 2018-04-01 | 2018-09-21
75086 | G7MAINS | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 4708.7 |  | 4708.7 |  |  | 4708.7 | 57864.49 | -53155.79 | 2018-04-30 10:28 | 2018-09-07 | 2018-05-01 | 2018-12-12
75086 | G7PUBIMP | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 223305.66 |  | 223305.66 |  |  | 223305.66 | 238847.13 | -15541.47 | 2018-04-06 18:03 | 2018-08-24 | 2018-04-01 | 2018-10-26
75086 | G7REPL | MX7584379 | INSTALL REPLACEMENT PROJECT | 131110.05 |  | 131110.05 |  |  | 131110.05 | 112501.75 | 18608.3 | 2018-04-12 18:02 | 2018-08-24 | 2018-04-01 | 2018-10-05
75086 | G7MAINS | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 26644.84 |  | 26644.84 |  |  | 26644.84 | 172975.63 | -146330.79 | 2018-08-07 10:03 | 2018-11-12 | 2018-10-01 | 2019-03-08
75086 | G7PUBIMP | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 50170.87 |  | 50170.87 |  |  | 50170.87 | 45950.78 | 4220.09 | 2018-04-04 14:01 | 2018-08-24 | 2018-04-01
75086 | G7LGMR | MX7686017 | INSTALL SCADA EQUIPMENT | 6739.77 |  | 6739.77 |  |  | 6739.77 | 24676.61 | -17936.84 | 2018-03-23 10:01 | 2018-10-01 | 2018-04-01 | 2019-01-01
75086 | G7MAINS | MX7722964 | MEA PROJECT LIMABURG RD | 58416.98 |  | 58416.98 |  |  | 58416.98 | 302578.49 | -244161.51 | 2018-08-15 14:02 | 2018-10-05 | 2018-08-01 | 2019-03-03
75086 | G7MAINS | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 4660.19 |  | 4660.19 |  |  | 4660.19 | 3766.66 | 893.53 | 2018-08-27 14:02 | 2018-11-20 | 2018-08-01 | 2018-12-26
75086 | G7MAINS | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 6445.56 |  | 6445.56 |  |  | 6445.56 | 38185.68 | -31740.12 | 2018-05-02 14:01 | 2018-09-17 | 2018-05-01 | 2018-10-11
75086 | G7MAINS | MX7865414 | Gas Main Extension - Production Dr, | 33048.7 |  | 33048.7 |  |  | 33048.7 | 100410.13 | -67361.43 | 2018-06-28 16:40 | 2018-08-31 | 2018-07-01 | 2019-01-20
75086 | G7REPL | MX8171793 | INSTALL REPLACEMENT PROJECT | -59716.51 |  | -59716.51 |  |  | -59716.51 | 84327.5 | -144044.01 | 2018-08-03 18:04 | 2018-09-28 | 2018-08-01 | 2019-01-16
75086 | G7LGMR | MX8312879 | Install Odorant Flare Systems KY | 677.03 |  | 677.03 |  |  | 677.03 | 8112.3 | -7435.27 | 2018-06-01 10:01 | 2018-12-31 | 2018-08-01 | 2019-03-31
75086 | G7MAINS | MX8362357 | INSTALL LARGE MEA PROJECT | 10584.66 |  | 10584.66 |  |  | 10584.66 | 25102.59 | -14517.93 | 2018-05-15 10:02 | 2018-08-03 | 2018-05-01 | 2018-09-21
75086 | G7MAINS | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 5172.02 |  | 5172.02 |  |  | 5172.02 | 65454.13 | -60282.11 | 2018-08-21 14:02 | 2019-06-06 | 2018-11-01 | 2019-05-19
75086 | G7MAINS | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 16366.12 |  | 16366.12 |  |  | 16366.12 | 80515.92 | -64149.8 | 2018-08-22 14:02 | 2018-10-19 | 2018-08-01
75086 | G7MAINS | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 10533.41 |  | 10533.41 |  |  | 10533.41 | 68031.36 | -57497.95 | 2018-09-28 14:02 | 2019-06-06 | 2018-11-01 | 2019-04-15
75086 | G7PUBIMP | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 35011.89 |  | 35011.89 |  |  | 35011.89 | 208010.18 | -172998.29 | 2018-06-14 14:01 | 2018-10-12 | 2018-06-01 | 2019-02-03
75086 | G7REPL | MX9056339 | St. Matthews Circle Replacement | 5023.38 |  | 5023.38 |  |  | 5023.38 | 107808.25 | -102784.87 | 2018-09-25 14:02 | 2019-02-03 | 2018-10-01 | 2019-08-20
75086 | G7PRESIM | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 2376.12 |  | 2376.12 |  |  | 2376.12 | 0 | 2376.12 | 2018-09-24 14:02 | 2018-11-16 | 2018-12-01 | 2019-04-03
75086 | GPRESIMP | MX9177822 | INSTALL PRESSURE IMPROVEMENT PROJEC | 36913.46 |  | 36913.46 |  |  | 36913.46 | 283021.16 | -246107.7 | 2018-11-14 10:01 | 2019-01-11 | 2018-12-01 | 2019-04-04
75086 | G7MAINS | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 18447.8 |  | 18447.8 |  |  | 18447.8 | 179827.05 | -161379.25 | 2018-10-11 18:03 | 2018-12-14 | 2018-10-01 | 2019-02-06
75086 | G7MAINS | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 9407.94 |  | 9407.94 |  |  | 9407.94 | 152463.07 | -143055.13 | 2018-11-09 14:02 | 2019-02-24 | 2018-12-01 | 2019-04-14
75086 | G7PUBIMP | O4165 | Dudley Rd Improvement | 1422.97 |  | 1422.97 |  |  | 107234.72 | 145627.17 | -38392.45 | 2014-07-23 | 2015-03-01 | 2014-08-01 | 2014-11-01
75086 | G7PUBIMP | P6538 | Ky 9 Reconstruction-South | -144848.75 |  | -144848.75 |  |  | 15393.82 | 376789.01 | -361395.19 | 2014-10-08 | 2016-06-01 | 2014-11-01 | 2016-06-10
75086 | G7LGMR | P7279 | Rossford Avenue (STA #101) | -4530.95 |  | -4530.95 |  |  | 267035.86 | 114357.6 | 152678.26 | 2015-01-14 | 2017-02-15 | 2016-04-01 | 2016-12-28
75087 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 522039.73 |  | 522039.73 |  |  | 2948963.76 | 807214 | 2141749.76 | 2016-02-11 12:05 | 2018-10-31 | 2016-03-01 | 2018-10-31
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | 25798.61 |  | 25798.61 |  |  | 2911471.82 | 105161.63 | 2806310.19 | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7IMPRPL | R0981 | WP23 "AM07" Pressure Test | 12656.56 |  | 12656.56 |  |  | 841177.95 | 98206.56 | 742971.39 | 2015-07-06 16:45 | 2017-02-28 | 2016-02-01 | 2016-10-20
75086 | G7REPL | R1014 | Griffin Industries - UL-27 replacem | 1836.45 |  | 1836.45 |  |  | 328020.77 | 1311188.64 | -983167.87 | 2015-07-07 10:38 | 2016-04-15 | 2015-07-01 | 2016-01-10
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 15879538.01 |  | 15879538.01 |  |  | 27230828.58 | 25488221 | 1742607.58 | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7LGMR | R2901 | STA 838 Mineola Pike - Station | 254070.28 |  | 254070.28 |  |  | 469897.32 | 209397.6 | 260499.72 | 2015-09-10 16:12 | 2018-05-31 | 2016-04-01 | 2018-02-14
75086 | G7MAINS | R3796 | JT 8916678 Freedom Park II | -15.65 |  | -15.65 |  |  | 14265.73 | 2977.64 | 11288.09 | 2015-10-16 14:44 | 2017-11-17 | 2017-03-01 | 2017-07-26
75086 | G7BIGBON | R4856 | Big Bone 8" IP Main to Richwood | -109.53 |  | -109.53 |  |  | 195371.99 | 352501.52 | -157129.53 | 2015-12-02 14:04 | 2018-04-30 | 2017-02-01 | 2017-12-05
75086 | G7PUBIMP | R5767 | GO 8346362 KY 9 North recon | -127310.27 |  | -127310.27 |  |  | 24683.74 | 335536.03 | -310852.29 | 2016-01-11 10:41 | 2018-06-01 | 2016-01-01 | 2016-07-12
75086 | G7REPL | R6767 | RPL 9818927 21st St Levee | 2372 |  | 2372 |  |  | 606523.07 | 476000.06 | 130523.01 | 2016-02-11 13:42 | 2017-04-30 | 2016-06-01 | 2016-12-13
75086 | G7IMPRPL | R9162 | INT 9146891 Henry Ct & US 27 | 2882.13 |  | 2882.13 |  |  | 164675.32 | 213360 | -48684.68 | 2016-03-28 10:17 | 2017-06-30 | 2016-06-01 | 2017-03-01
75086 | G7PUBIMP | S1056 | STI 10177360 Latonia Lakes Str Impr | -83715.66 |  | -83715.66 |  |  | 11564.1 | 52785.89 | -41221.79 | 2016-04-15 16:46 | 2016-10-31 | 2016-04-01 | 2016-09-18
75086 | G7LGMR | S1094 | STA 249: Three Mile - Station | 273929.05 |  | 273929.05 |  |  | 607696.76 | 197894.45 | 409802.31 | 2016-04-18 09:31 | 2020-01-30 | 2016-07-01 | 2017-02-16
75086 | G7MAINS | S2732 | GO 9691430 Sta 836 Inlet Piping | -138613.96 |  | -138613.96 |  |  | 37969.86 | 91976.45 | -54006.59 | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01
75086 | G7MAINS | S2752 | GO 9691542 Sta 836 Outlet Piping | -197354.09 |  | -197354.09 |  |  | 36659.73 | 48219.36 | -11559.63 | 2016-04-29 11:23 | 2018-05-11 | 2016-05-01 | 2016-12-28
75086 | G7REPL | S5697 | RPL 10420236 Ft Wright Elem | -1433.69 |  | -1433.69 |  |  | 322.17 | 15249.75 | -14927.58 | 2016-05-13 08:59 | 2016-10-22 | 2016-05-01 | 2016-10-16
75086 | G7PUBIMP | S7874 | STI 4844778 Thomas More Pkwy | -2803.46 |  | -2803.46 |  |  | 70545.05 | 11696.61 | 58848.44 | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7REPL | S8375 | STA 838 Mineola Pike - Inlet | 40259.88 |  | 40259.88 |  |  | 94836.89 | 33588.96 | 61247.93 | 2016-06-23 09:04 | 2018-12-30 | 2017-08-01 | 2018-02-14
75086 | G7MAINS | S8847 | GO 9527853 820 Dolwick Dr | 1370.15 |  | 1370.15 |  |  | 78660.66 | 169442.7 | -90782.04 | 2016-07-25 12:25 | 2017-03-31 | 2016-07-01 | 2017-02-15
75086 | G7PUBIMP | S8867 | STI 10873483 Mt Zion Rd | 531730.94 |  | 531730.94 |  |  | 812478.32 | 447690.24 | 364788.08 | 2016-07-26 13:07 | 2020-01-30 | 2017-01-01 | 2019-12-21
75086 | FENABLEH | SDDTH | Enable Subdiv Design Tool Hardware | 0.05 |  | 0.05 |  |  | 13.28 | 11 | 2.28 | 2015-03-30 15:28 | 2017-10-31 | 2017-06-01 | 2017-11-07
75086 | FENABLES | SDDTS | Enable Subdiv Design Tool Software | 2722.38 |  | 2722.38 |  |  | 93505.11 | 78341 | 15164.11 | 2015-03-30 16:38 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 2400751.02 |  | 2400751.02 |  |  | 4510326.76 | 2250000 | 2260326.76 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SGKAMIF | SG169MTRS | SG KY AMI Gas Meters - 169 | 4886387.66 |  | 4886387.66 |  |  | 9492969.37 | 9563026 | -70056.63 | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75086 | SG000358F | SG358HW18 | SG 358 - MDM Scale Hardware Phase 3 | 11663.21 |  | 11663.21 |  |  | 70706.97 | 57585 | 13121.97 | 2017-05-30 17:55 | 2018-09-30 | 2017-06-01 | 2018-08-31
75086 | SG000358F | SG358HW19 | SG DEE MDM Scale HWre Phase 4 - 358 | 35838.19 |  | 35838.19 |  |  | 35838.19 | 21102.66 | 14735.53 | 2018-05-09 10:59 | 2019-08-18 | 2018-05-01 | 2019-09-24
75086 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 123.55 |  | 123.55 |  |  | 16330.53 | 2935 | 13395.53 | 2016-11-01 13:58 | 2018-02-28 | 2016-11-01 | 2018-02-12
75086 | SG000358F | SG358SW2 | SG DEE MDM Scale Sftwre Phs 4 - 358 | 12880.69 |  | 12880.69 |  |  | 12880.69 | 7317.09 | 5563.6 | 2018-05-07 17:00 | 2019-08-18 | 2018-05-01 | 2019-09-24
75086 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 7178.26 |  | 7178.26 |  |  | 28900.04 | 31329.67 | -2429.63 | 2017-04-24 18:13 | 2018-12-31 | 2017-05-01 | 2019-03-31
75086 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | 6707.82 |  | 6707.82 |  |  | 20682.08 | 16065.37 | 4616.71 | 2016-11-23 11:25 | 2018-12-31 | 2016-11-01 | 2019-03-31
75086 | SG000540F | SG540HW | DEE Vehicle Area Network | 6779.65 |  | 6779.65 |  |  | 6779.65 | 117926 | -111146.35 | 2018-04-13 13:13 | 2020-12-17 | 2018-09-01
75086 | SG000540F | SG540SW | DEE Vehicle Area Network | -3026.84 |  | -3026.84 |  |  | -6.8212e-13 | 107801 | -107801 | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01 | 2018-07-16
75086 | SG000540F | SG540SW2 | DEE Vehicle Area Network | 41254.01 |  | 41254.01 |  |  | 41254.01 | 70013 | -28758.99 | 2018-04-18 18:10 | 2020-12-17 | 2018-10-01
75086 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | 29657.55 |  | 29657.55 |  |  | 29657.55 | 76873.76 | -47216.21 | 2018-07-12 09:17 | 2021-03-31 | 2018-07-01
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 0.03 |  | 0.03 |  |  | 6381.08 | 4498 | 1883.08 | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGOPENW14 | SGNNT1273 | SG Openway Software Upgrade to 6.1 | 0.01 |  | 0.01 |  |  | 13003.7 | 14500 | -1496.3 | 2014-07-28 | 2015-06-13 | 2014-10-01 | 2015-06-15
75086 | SGNNT1021 | SGNT1021A | SG NINT1021A - SERVERS | 0.01 |  | 0.01 |  |  | 3322.36 | 170000 | -166677.64 | 2014-04-30 | 2014-09-30 | 2014-05-01 | 2015-02-01
75086 | G7LGMR | T0425 | SCAD 11456765 Mineola Pike Sta | -775.28 |  | -775.28 |  |  | 24038.03 | 55991.76 | -31953.73 | 2016-11-03 09:31 | 2018-12-01 | 2017-01-01 | 2018-04-30
75086 | G7LGMR | T0645 | STA 839 Richwood Station | 272783.65 |  | 272783.65 |  |  | 352344.14 | 157154.88 | 195189.26 | 2016-11-14 09:37 | 2018-12-28 | 2017-02-01 | 2018-08-05
75086 | G7LGMR | T0646 | STA 835 Walton - Station | 728245.22 |  | 728245.22 |  |  | 762712.25 | 157154.88 | 605557.37 | 2016-11-14 09:54 | 2018-12-01 | 2017-04-01 | 2018-09-06
75086 | G7LGMR | T0746 | AM00a Automation of RCV Cold Spring | 263899.33 |  | 263899.33 |  |  | 437114.72 | 380490 | 56624.72 | 2016-11-18 11:04 | 2018-12-30 | 2017-02-01 | 2019-01-04
75086 | G73MILES | T0747 | AM00a Automation of RCV -Alexandria | 13749.52 |  | 13749.52 |  |  | 176884.88 | 415030 | -238145.12 | 2016-11-18 11:23 | 2020-02-28 | 2016-12-01 | 2018-06-15
75086 | G7BIGBON | T0881 | Big Bone Odorant Station - SCADA | 76769.52 |  | 76769.52 |  |  | 185669.16 | 351251.52 | -165582.36 | 2016-12-01 12:00 | 2018-12-01 | 2017-04-01 | 2018-08-05
75086 | G73MILES | T1437 | STA 249: Three Mile Rd | 2942242.58 |  | 2942242.58 |  |  | 3552988.38 | 15406228 | -11853239.62 | 2017-01-05 11:19 | 2020-08-28 | 2017-01-01 | 2020-09-15
75086 | G73MILES | T1437LAND | 3 Mile Station (LAND) | 2581.47 |  | 2581.47 |  |  | 2581.47 | 40000 | -37418.53 | 2018-06-22 15:02 | 2020-07-28 | 2018-09-01 | 2020-09-15
75086 | G7LGMR | T1465 | STA 855 Taylor Mill Rd - Station | 122223.16 |  | 122223.16 |  |  | 192160.14 | 83246.98 | 108913.16 | 2017-01-06 16:24 | 2018-04-19 | 2017-03-01 | 2018-04-24
75086 | G7LGMR | T1485 | STA 855 Taylor Mill Rd - Inlet | 43703.2 |  | 43703.2 |  |  | 60451.15 | 23969.47 | 36481.68 | 2017-01-09 11:13 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7LGMR | T1486 | STA 855 Taylor Mill Rd - Outlet | 23556.26 |  | 23556.26 |  |  | 31517.44 | 18239.23 | 13278.21 | 2017-01-09 11:23 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7IMPRPL | T1525 | AM02 Exposed Main in Southgate, KY | 744779.5 |  | 744779.5 |  |  | 850649.55 | 351129.6 | 499519.95 | 2017-01-12 09:24 | 2018-09-30 | 2017-01-01 | 2018-11-24
75086 | G7REPL | T1796 | Showcase AM07 | 1722698.39 |  | 1722698.39 |  |  | 1207726.33 | 3343471.9 | -2135745.57 | 2017-01-27 15:35 | 2018-04-30 | 2017-01-01 | 2018-08-09
75086 | G7LGMR | T2218 | STA 838 Mineola Pike - Outlet | 34324.53 |  | 34324.53 |  |  | 44738.58 | 23225.76 | 21512.82 | 2017-02-15 15:45 | 2018-08-31 | 2017-05-01 | 2018-02-14
75086 | G7REPL | T2230 | RPL 20745900 Hudson Ave | 20868 |  | 20868 |  |  | -28451.64 | 105241.34 | -133692.98 | 2017-02-16 14:11 | 2018-03-31 | 2017-02-01 | 2017-09-28
75086 | G7PUINEW | T2904 | MTR 11540114 1 Carbon Way | 61.27 |  | 61.27 |  |  | 2125.29 | 29846.02 | -27720.73 | 2017-03-08 13:44 | 2018-12-31 | 2017-12-01
75086 | G7LGMR | T4002 | STA 20933317 Erlanger CP | 14.59 |  | 14.59 |  |  | 2407.97 | 31943.04 | -29535.07 | 2017-03-17 11:42 | 2018-12-30 | 2017-08-01
75086 | G73MILES | T4422 | AM07 Barleycorns | 885.06 |  | 885.06 |  |  | 73525.32 | 190195.2 | -116669.88 | 2017-03-22 16:39 | 2020-07-28 | 2017-04-01 | 2019-12-01
75086 | G7LGMR | T4893 | Mineola Pike STA Meter Rep & Panels | 10815.86 |  | 10815.86 |  |  | 44276.29 | 119176.8 | -74900.51 | 2017-03-28 11:26 | 2018-12-30 | 2017-05-01 | 2018-10-02
75086 | G7LGMR | T5473 | SCAD 21012299 Pressure Transmiitter | 4969.13 |  | 4969.13 |  |  | 52351.17 | 91500.96 | -39149.79 | 2017-03-31 07:27 | 2018-12-01 | 2017-06-01 | 2017-09-30
75086 | G7IMPRPL | T7752 | AM07 Grey Stable Ln | 109058.92 |  | 109058.92 |  |  | 182164.6 | 183855.36 | -1690.76 | 2017-05-01 16:13 | 2018-09-15 | 2017-05-01 | 2018-06-15
75086 | G7LGMR | T7966 | STA 859 Banklick Rd - Station | 307874.7 |  | 307874.7 |  |  | 312193.19 | 215078.32 | 97114.87 | 2017-05-10 15:15 | 2018-07-01 | 2017-09-01 | 2018-07-17
75086 | G7REPL | T8295 | RPL 21421581 Latonia Lakes | -211784.79 |  | -211784.79 |  |  | -3299.62 | 118055.14 | -121354.76 | 2017-05-30 16:11 | 2018-03-30 | 2017-06-01 | 2017-10-15
75086 | G7PUBIMP | T8343 | STI 20956764 Weaver Rd. | -43073.13 |  | -43073.13 |  |  | 5975.14 | 39100.39 | -33125.25 | 2017-05-31 13:21 | 2018-05-01 | 2017-07-01 | 2017-11-29
75086 | G7LP3 | U8785 | Emergency Line LP-3 | 8463775.97 |  | 8463775.97 |  |  | 8463775.97 | 7865574 | 598201.97 | 2018-03-21 08:40 | 2019-02-28 | 2018-04-01 | 2019-02-16
75086 | G7UL02 | V0767 | UL02 ECDA Scheduled Digs | 223934.78 |  | 223934.78 |  |  | 223934.78 | 35000 | 188934.78 | 2018-05-10 12:53 | 2018-11-30 | 2018-10-01 | 2018-11-30
75086 | G7ERLACPI | V2339 | Erlangar OP Center Anodes | 140023.1 |  | 140023.1 |  |  | 140023.1 | 350000 | -209976.9 | 2018-06-20 15:56 | 2018-12-30 | 2018-06-01 | 2019-02-15
75086 | G7CAS112 | V4266 | Casing 112 Line AM07 | 65368.36 |  | 65368.36 |  |  | 65368.36 | 257083 | -191714.64 | 2018-08-02 14:00 | 2018-12-30 | 2018-08-01 | 2019-01-22
75086 | G7CAS22 | V4278 | Casing 22 Line AM07 | 19945.99 |  | 19945.99 |  |  | 19945.99 | 311445 | -291499.01 | 2018-08-02 16:45 | 2018-12-30 | 2018-08-01 | 2019-01-01
75086 | FPIT | V5136 | Communication Radio Install | 26827.57 |  | 26827.57 |  |  | 26827.57 | 23120 | 3707.57 | 2018-08-20 08:22 | 2018-12-31 | 2018-08-01
75086 | G7ERLPLAN | V5155 | Erlanger Propane Plant Upgrades | 941860.16 |  | 941860.16 |  |  | 941860.16 | 403571.6 | 538288.56 | 2018-08-21 12:58 | 2018-12-31 | 2018-08-01 | 2019-07-01
75086 | FP647 | V5213 | AM07 Casing Rem 647 Erlanger rd | 76142.4 |  | 76142.4 |  |  | 76142.4 | 115206.73 | -39064.33 | 2018-08-22 09:19 | 2019-03-30 | 2018-09-01 | 2018-11-23
75086 | G7CAS53 | V5417 | Casing 53 Line AM07 | 43414.61 |  | 43414.61 |  |  | 43414.61 | 409578 | -366163.39 | 2018-08-29 07:10 | 2018-12-30 | 2018-10-01 | 2019-03-01
75086 | G7EUL06 | V5625 | ECDA Line UL06 | 241083.25 |  | 241083.25 |  |  | 241083.25 | 494420 | -253336.75 | 2018-09-10 09:20 | 2019-03-30 | 2018-10-01 | 2019-03-17
75086 | G7LNLP03 | V5652 | Line LP03 | 863292.67 |  | 863292.67 |  |  | 863292.67 | 1325999 | -462706.33 | 2018-09-11 07:37 | 2019-02-28 | 2018-10-01 | 2019-02-15
75086 | G7EUL47 | V6391 | Line UL47 scheduled digs | 247015.9 |  | 247015.9 |  |  | 247015.9 | 724400 | -477384.1 | 2018-10-10 08:17 | 2019-03-30 | 2018-10-01 | 2019-03-14
75086 | G7PHMSA | V7283 | PHMSA CRM Plan | 152506.18 |  | 152506.18 |  |  | 152506.18 | 416794 | -264287.82 | 2018-11-14 14:31 | 2020-09-30 | 2018-12-01
75086 | G7CAS106 | V7737 | Casing#106 AM07 & Martha Layne | 2755.39 |  | 2755.39 |  |  | 2755.39 | 1749344 | -1746588.61 | 2018-11-28 14:40 | 2019-12-30 | 2018-12-01 | 2020-01-23
75086 | G7CAS42 | V7739 | Casing#42 abandon- AM07 & Hulbert | 2755.39 |  | 2755.39 |  |  | 2755.39 | 1939294 | -1936538.61 | 2018-11-28 14:52 | 2019-11-30 | 2018-12-01 | 2019-11-15
75086 | FENABLEH | WRTH | Enable WRT & WMSP Hardware | 0.06 |  | 0.06 |  |  | 16.6 | 15 | 1.6 | 2015-03-30 14:39 | 2017-10-31 | 2017-06-01 | 2017-11-07
75086 | FENABLES | WRTS | Enable WRT & WMSP Software | 2767.22 |  | 2767.22 |  |  | 152077.35 | 117163 | 34914.35 | 2015-03-30 16:30 | 2017-10-31 | 2015-05-01 | 2017-11-07
|  |  |  | 72844266.85 | 51372783 | -21471483.85

## 2019
Duke Energy Kentucky Gas
Year 2019
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | -74314.25 |  | -74314.25 |  |  | 214825.7 | 0 | 214825.7 | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 307482 | Customer Mobile App | 2272.98 |  | 2272.98 |  |  | 33016.51 | 19937 | 13079.51 | 2017-05-08 15:22 | 2019-06-25 | 2017-05-01 | 2019-06-25
75087 | FPIT | 307482001 | Customer Mobile App - Phase 2 | 21239.6 |  | 21239.6 |  |  | 21239.6 | 28166 | -6926.4 | 2018-12-28 09:17 | 2020-03-31 | 2019-01-01 | 2020-03-20
75087 | CUSTCONN | 315986A | Customer Connect - Core | 1158565.33 |  | 1158565.33 |  |  | 1570715.46 | 2325960.3 | -755244.84 | 2017-08-10 10:55 | 2022-12-05 | 2017-08-01
75087 | CUSTCONN | 315986B | Customer Connect- Analytics | -28.55 |  | -28.55 |  |  | 108681.46 | 69801.07 | 38880.39 | 2017-08-10 13:13 | 2018-09-30 | 2017-08-01 | 2018-09-30
75087 | CUSTCONN | 315986C | Customer Connect- Release 2 | 86721.19 |  | 86721.19 |  |  | 301128.34 | 187946.4 | 113181.94 | 2017-08-10 14:30 | 2019-05-28 | 2017-08-01 | 2019-06-18
75087 | CUSTCONN | 315986D | Customer Connect- Release 3 | 86655.88 |  | 86655.88 |  |  | 193013.86 | 280416.54 | -87402.68 | 2017-08-10 15:35 | 2019-12-30 | 2017-08-01 | 2019-12-31
75087 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 94675.27 |  | 94675.27 |  |  | 159611.79 | 117210.08 | 42401.71 | 2017-08-11 10:44 | 2020-09-01 | 2017-08-01 | 2020-09-01
75087 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 126.68 |  | 126.68 |  |  | 166838.95 | 43856 | 122982.95 | 2017-09-05 18:46 | 2018-10-01 | 2017-09-01 | 2018-10-01
75087 | CUSTCONN | 315986HW4 | Customer Connect- Hardware Proj 2 | 64832.91 |  | 64832.91 |  |  | 133573.49 | 53607 | 79966.49 | 2018-08-31 12:34 | 2019-06-01 | 2018-08-01 | 2019-08-01
75087 | CUSTCONN | 315986HW5 | Customer Connect- Hardware Proj 3 | 63324.12 |  | 63324.12 |  |  | 63324.12 | 42700 | 20624.12 | 2019-09-03 14:48 | 2020-06-01 | 2019-09-01 | 2020-06-15
75086 | FPIT | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 2502.47 |  | 2502.47 |  |  | 25398.78 | 73735 | -48336.22 | 2018-06-12 13:16 | 2019-04-21 | 2018-07-01 | 2019-04-29
75086 | FPIT | 323850001 | Fleet Asset Lifecycle & Mobile Solu | 10290.59 |  | 10290.59 |  |  | 22247.35 | 28034 | -5786.65 | 2018-04-25 09:31 | 2020-02-15 | 2018-04-01 | 2020-02-11
75086 | G7S3300 | 3300LAND | Line UL02 S3300 LAND RTS | 66178.72 |  | 66178.72 |  |  | 66178.72 | 82000 | -15821.28 | 2018-11-08 10:08 | 2018-12-30 | 2019-05-01 | 2019-12-01
75087 | FPIT | 336593019 | New Call Ctr SIP Trunks | 5665.71 |  | 5665.71 |  |  | 15731.86 | 10444 | 5287.86 | 2018-03-14 16:47 | 2020-03-31 | 2018-03-01 | 2020-03-31
75086 | FPIT | 338802003 | EAM Platform Optimization | 30337.36 |  | 30337.36 |  |  | 40439.92 | 147321.02 | -106881.1 | 2018-04-25 14:30 | 2020-05-30 | 2018-06-01 | 2020-03-31
75086 | FPIT | 338802004 | Mobile Durable Team | 75768.29 |  | 75768.29 |  |  | 101287.06 | 52783 | 48504.06 | 2018-09-17 12:23 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802005 | Maximo Durable Team | 148312.16 |  | 148312.16 |  |  | 160775.57 | 33459 | 127316.57 | 2018-09-13 15:18 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802006 | Smallworld/myWorld Durable Team | 343.59 |  | 343.59 |  |  | 343.59 | 48911 | -48567.41 | 2018-09-06 13:43 | 2020-05-28 | 2018-10-01 | 2020-11-10
75086 | FPIT | 338802008 | EcoSys Durable Team Acciunting | 220.61 |  | 220.61 |  |  | 1628.2 | 52026 | -50397.8 | 2018-09-13 10:17 | 2020-03-30 | 2018-09-01 | 2020-03-30
75087 | FPIT | 344598001 | Duke Customer IVR Replacement | 114828.39 |  | 114828.39 |  |  | 142088.99 | 197081 | -54992.01 | 2018-04-10 15:29 | 2020-01-28 | 2018-04-01 | 2020-01-30
75086 | FPIT | 347565014 | 2018 Cisco EOL KY Phase 1 | 115277.13 |  | 115277.13 |  |  | 494565.2 | 17736 | 476829.2 | 2018-02-20 17:32 | 2019-07-30 | 2018-03-01 | 2019-07-31
75087 | FPIT | 348527007 | My Duke Replacement | 64098.76 |  | 64098.76 |  |  | 64098.76 | 51758 | 12340.76 | 2019-10-02 08:40 | 2020-03-31 | 2019-10-01 | 2020-02-15
75087 | FPIT | 354299001 | Outage Map Refresh | 19206.98 |  | 19206.98 |  |  | 19206.98 | 21192.7 | -1985.72 | 2019-10-02 10:55 | 2020-04-30 | 2019-10-01 | 2020-04-30
75086 | FPIT | 359990001 | Field Test Equipment Calibration So | 67205.2 |  | 67205.2 |  |  | 67205.2 | 60858 | 6347.2 | 2019-02-26 15:25 | 2019-12-29 | 2019-03-01 | 2019-12-01
75086 | G7SERVNEW | 4MCNEW70 | Install New M-C 4" | 206.83 |  | 206.83 |  |  | 96132.33 | 1 | 96131.33 | 2010-12-31 | 2050-12-31 | 2011-02-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 62304.75 |  | 62304.75 |  |  | 473727.79 | 350000 | 123727.79 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 827659.12 |  | 827659.12 |  |  | 5226775.77 | 14500000 | -9273224.23 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | G71373 | AW0856 | 1373 US 27 Bridge Attachment | 71074.62 |  | 71074.62 |  |  | 71074.62 | 91770 | -20695.38 | 2019-07-30 08:26 | 2020-02-25 | 2019-11-01 | 2020-03-30
75086 | G7HMISTAT | AW0938 | HMI Work Station Erlanger | 4978.34 |  | 4978.34 |  |  | 4978.34 | 64259 | -59280.66 | 2019-08-09 13:08 | 2021-03-02 | 2019-10-01
75086 | G7AM07CUT | AW1330 | AM07 Cutout Fidelity | 308747.47 |  | 308747.47 |  |  | 308747.47 | 1236780 | -928032.53 | 2019-10-23 11:50 | 2019-12-30 | 2019-10-01 | 2020-02-02
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | 25419.41 |  | 25419.41 |  |  | 164981.67 | 725000 | -560018.33 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 731695.06 |  | 731695.06 |  |  | 2376925.1 | 1250000 | 1126925.1 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 1091.77 |  | 1091.77 |  |  | 153429.64 | 800000 | -646570.36 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 950271.9 |  | 950271.9 |  |  | 7248596.48 | 1 | 7248595.48 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 168650.28 |  | 168650.28 |  |  | 281350.64 | 5000000 | -4718649.36 | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 715666.47 |  | 715666.47 |  |  | 12231459.59 | 0 | 12231459.59 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | 2" or less steel C-M Replace | 4947.08 |  | 4947.08 |  |  | 47511.19 | 1000000 | -952488.81 | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 2010413.22 |  | 2010413.22 |  |  | 8871331.51 | 20388002 | -11516670.49 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | FLKY0251G | DKEKYG19 | Fleet On-Road Vehicles - Gas - KY | 6499.34 |  | 6499.34 |  |  | 6499.34 | 40000 | -33500.66 | 2019-01-14 10:18 | 2050-12-31 | 2019-05-01
75086 | FPIT | GCTA30060 | Consolidated SCADA App Analysis | 177806.19 |  | 177806.19 |  |  | 223607.33 | 149205 | 74402.33 | 2017-04-11 15:19 | 2020-06-30 | 2017-04-01 | 2020-06-30
75086 | FPIT | GCTA3006K | INTGO_PI SCADA Data Implementation | 88195.48 |  | 88195.48 |  |  | 88195.48 | 133026 | -44830.52 | 2019-11-15 07:17 | 2022-03-17 | 2019-11-01
75086 | FPIT | GCTA30073 | Project 2 Gas Supply System | 388687.24 |  | 388687.24 |  |  | 685329.86 | 853149 | -167819.14 | 2017-03-30 17:09 | 2021-03-31 | 2017-07-01 | 2021-03-31
75086 | FPIT | GCTA30114 | Sales Force Automation Conso Strate | 191187.42 |  | 191187.42 |  |  | 209513.79 | 0 | 209513.79 | 2017-06-21 11:37 | 2020-11-30 | 2017-10-01 | 2020-11-10
75086 | FPIT | GCTA30128 | INTGO_Conso Gas Eng Calculators | 14060.15 |  | 14060.15 |  |  | 17894.62 | 28617 | -10722.38 | 2017-06-30 10:05 | 2019-10-31 | 2017-08-01 | 2019-10-31
75086 | FPIT | GCTA30389 | INTGO_Gas Distribution Proj Managem | 37045.19 |  | 37045.19 |  |  | 37045.19 | 117422 | -80376.81 | 2018-06-05 12:36 | 2020-01-14 | 2019-01-01 | 2019-06-30
75086 | FPIT | GCTA30391 | INTGO_Gas Major Projects Mgmt | 24412.3 |  | 24412.3 |  |  | 24412.3 | 224469 | -200056.7 | 2018-12-18 14:49 | 2020-12-30 | 2019-01-01 | 2020-12-31
75086 | FPIT | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 460319.12 |  | 460319.12 |  |  | 607946.89 | 513619 | 94327.89 | 2018-05-21 15:50 | 2019-12-29 | 2018-06-01 | 2019-12-01
75086 | FPIT | GCTA31738 | INTET-Enterprise Data Platform | 7872.66 |  | 7872.66 |  |  | 11864.53 | 28965 | -17100.47 | 2017-06-09 09:52 | 2018-07-30 | 2017-10-01 | 2018-07-31
75086 | FPIT | GCTA33039 | INTGO_Consolidated CAD Tools | 45288.34 |  | 45288.34 |  |  | 56388.21 | 120205 | -63816.79 | 2018-06-19 11:18 | 2020-09-24 | 2018-08-01 | 2020-03-31
75086 | FPIT | GCTA43704 | Natural Gas Bus Contractor Registra | 30476.06 |  | 30476.06 |  |  | 37792.74 | 37076 | 716.74 | 2018-10-10 11:35 | 2020-03-18 | 2018-10-01 | 2020-01-18
75086 | FPIT | GCTA47001 | INTGO_Materials Traceability | 43833.87 |  | 43833.87 |  |  | 43833.87 | 120205 | -76371.13 | 2018-12-06 14:57 | 2022-03-31 | 2019-01-01 | 2020-05-31
75086 | FPIT | GCTA4700A | INTGO_Traceability Form EAM | 62.82 |  | 62.82 |  |  | 62.82 | 29280 | -29217.18 | 2018-12-04 14:21 | 2021-03-31 | 2019-01-01 | 2021-03-14
75086 | FPIT | GCTA4700B | INTGO_Traceability Form FDC | 82058.54 |  | 82058.54 |  |  | 82224.54 | 215691 | -133466.46 | 2018-12-06 13:26 | 2021-03-31 | 2018-12-01 | 2021-03-14
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | 4902.88 |  | 4902.88 |  |  | 236029.98 | 136600 | 99429.98 | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01 | 2019-08-30
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 339040.61 |  | 339040.61 |  |  | 1112429.04 | 800000 | 312429.04 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | FPIT | IT1900021 | GIS Alignment for PCS - Midwest | 116848.1 |  | 116848.1 |  |  | 116848.1 | 485841 | -368992.9 | 2019-08-01 11:16 | 2021-01-31 | 2019-09-01 | 2021-01-17
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 7917.62 |  | 7917.62 |  |  | 233604.18 | 2500000 | -2266395.82 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVNEW | LCMNEWS70 | Greater than 2" C-M Steel | 3469.39 |  | 3469.39 |  |  | 3469.39 | 1000000 | -996530.61 | 2017-03-10 10:26 | 2050-12-31 | 2019-07-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | 145.82 |  | 145.82 |  |  | 16238.16 | 2500000 | -2483761.84 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LCMSP70 | ASRP Greater than 2" C-M Install | 6932.55 |  | 6932.55 |  |  | -259042.07 | 10000000 | -10259042.07 | 2016-01-13 11:25 | 2019-12-31 | 2016-07-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 72190.02 |  | 72190.02 |  |  | 289007.82 | 2500000 | -2210992.18 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 22643.56 |  | 22643.56 |  |  | 44532.16 | 2500000 | -2455467.84 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 1562.05 |  | 1562.05 |  |  | 200062.19 | 2500000 | -2299937.81 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | FPIT | LTHWOOPS | Lighthouse:WO Optimization Gas- SW | 31688.73 |  | 31688.73 |  |  | 31688.73 | 24900 | 6788.73 | 2019-03-12 15:21 | 2019-12-29 | 2019-03-01 | 2019-09-30
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 3895122 |  | 3895122 |  |  | 12724901.81 | 1 | 12724900.81 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 3522.42 |  | 3522.42 |  |  | 204367.77 | 1 | 204366.77 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1319424.15 |  | 1319424.15 |  |  | 15747203.83 | 0 | 15747203.83 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 7862.26 |  | 7862.26 |  |  | 525007.32 | 0 | 525007.32 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 17881766.96 |  | 17881766.96 |  |  | 40721793.99 | 19954384 | 20767409.99 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | FMDT2020 | MDTGAS20 | Install Win 7 Panasonic Toughbooks | 304195.36 |  | 304195.36 |  |  | 304195.36 | 403995 | -99799.64 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01
75086 | FMDT2017 | MDTKE17 | CF53 Purchases for MDT Replac | 22897.3 |  | 22897.3 |  |  | 30647.57 | 33851 | -3203.43 | 2018-02-07 15:38 | 2020-06-01 | 2018-02-01 | 2020-05-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 970941.54 |  | 970941.54 |  |  | 2965419.93 | 10000000 | -7034580.07 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | G7REPL | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 111235.39 |  | 111235.39 |  |  | 41742.14 | 64213.24 | -22471.1 | 2018-12-12 18:01 | 2019-11-21 | 2018-12-01 | 2019-11-27
75086 | GMAINS | MX0225249 | Litton Ln. PRESSURE IMPROVEMENT PRO | 147234.88 |  | 147234.88 |  |  | 170109.63 | 133009.25 | 37100.38 | 2018-12-06 18:01 | 2019-03-10 | 2018-12-01 | 2019-04-10
75086 | G7MAINS | MX0246467 | FARM TAP PROJ.-AARON LN | 54465.29 |  | 54465.29 |  |  | 54465.29 | 73522.53 | -19057.24 | 2018-12-10 14:01 | 2019-04-21 | 2019-01-01 | 2019-05-26
75086 | G7MAINS | MX0270903 | FARM TAP PROJ. 3 MILE RD | 407734.83 |  | 407734.83 |  |  | 407734.83 | 365844.57 | 41890.26 | 2019-03-21 14:01 | 2019-10-19 | 2019-04-01
75086 | G7MAINS | MX0376199 | FARM TAP PROJ; RODGERS RD | 38175.36 |  | 38175.36 |  |  | 38175.36 | 38989.27 | -813.91 | 2018-12-12 18:01 | 2019-04-21 | 2019-01-01 | 2019-09-18
75086 | G7MAINS | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 274275.4 |  | 274275.4 |  |  | 274275.4 | 123394.12 | 150881.28 | 2019-01-14 10:01 | 2019-10-24 | 2019-05-01
75086 | G7LGMR | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 10860.3 |  | 10860.3 |  |  | 10860.3 | 31485.84 | -20625.54 | 2018-11-19 14:01 | 2019-02-28 | 2019-04-01 | 2019-07-19
75086 | G7LGMR | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 9772.54 |  | 9772.54 |  |  | 9772.54 | 26609.04 | -16836.5 | 2018-11-19 14:01 | 2019-02-28 | 2019-04-01 | 2019-07-11
75086 | G7MAINS | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 314508.41 |  | 314508.41 |  |  | 314508.41 | 0 | 314508.41 | 2019-07-31 14:01 | 2019-10-25 | 2019-08-01
75086 | G7MAINS | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 15822.74 |  | 15822.74 |  |  | 15822.74 | 112220.53 | -96397.79 | 2019-07-16 10:02 | 2019-12-12 | 2019-07-01
75086 | G7LGMR | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 170319.71 |  | 170319.71 |  |  | 170319.71 | 81442.56 | 88877.15 | 2018-12-06 10:01 | 2019-08-30 | 2019-03-01 | 2019-10-27
75086 | G7PUBIMP | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 561979.86 |  | 561979.86 |  |  | 1856346.07 | 1689689.28 | 166656.79 | 2018-04-26 10:01 | 2018-08-25 | 2018-05-01 | 2019-01-22
75086 | G7PUBIMP | MX0790794 | Arlington Rd. Roadway IMP | 147909.86 |  | 147909.86 |  |  | 396819.84 | 227712 | 169107.84 | 2018-01-23 20:20 | 2018-03-30 | 2018-03-01 | 2018-09-26
75086 | G7MAINS | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 22852.56 |  | 22852.56 |  |  | 22852.56 | 35195.33 | -12342.77 | 2019-01-14 10:01 | 2019-03-01 | 2019-02-01 | 2019-07-09
75086 | G7PUBIMP | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | -17515.66 |  | -17515.66 |  |  | 486286.42 | 274447.64 | 211838.78 | 2018-07-19 18:03 | 2018-10-28 | 2018-07-01 | 2018-12-19
75086 | G7MAINS | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 73599.1 |  | 73599.1 |  |  | 73599.1 | 62900.69 | 10698.41 | 2019-02-07 10:02 | 2019-04-03 | 2019-03-01
75086 | G7MAINS | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 70432.39 |  | 70432.39 |  |  | 70432.39 | 85840.23 | -15407.84 | 2019-02-18 10:01 | 2019-06-02 | 2019-02-01 | 2019-09-18
75086 | G7REPL | MX1233047 | KY-9 FLOOD GATE-RPL | 4944.55 |  | 4944.55 |  |  | 4944.55 | 92509 | -87564.45 | 2019-10-23 18:01 | 2020-07-10 | 2019-10-01 | 2020-12-14
75086 | G7MAINS | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 83484.92 |  | 83484.92 |  |  | 83484.92 | 91176.31 | -7691.39 | 2019-02-21 10:02 | 2019-06-09 | 2019-02-01 | 2019-12-13
75086 | G7MAINS | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 3024.49 |  | 3024.49 |  |  | 3024.49 | 1976.99 | 1047.5 | 2019-06-14 10:02 | 2019-11-07 | 2019-07-01 | 2019-09-18
75086 | G7MAINS | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 38448.36 |  | 38448.36 |  |  | 38448.36 | 73554.85 | -35106.49 | 2019-07-24 10:01 | 2020-01-19 | 2019-08-01 | 2020-03-13
75086 | G7MAINS | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 32850.76 |  | 32850.76 |  |  | 32850.76 | 46479.42 | -13628.66 | 2019-06-26 14:01 | 2019-11-14 | 2019-07-01
75086 | G7MAINS | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 270890.93 |  | 270890.93 |  |  | 270890.93 | 346753.22 | -75862.29 | 2019-09-11 14:01 | 2020-03-29 | 2019-09-01 | 2020-05-15
75086 | G7MAINS | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 16394.44 |  | 16394.44 |  |  | 16394.44 | 37755.1 | -21360.66 | 2019-03-15 18:01 | 2019-06-30 | 2019-03-01 | 2019-09-19
75086 | G7MAINS | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 29060.78 |  | 29060.78 |  |  | 29060.78 | 42406.63 | -13345.85 | 2019-03-05 18:01 | 2019-06-09 | 2019-03-01 | 2019-08-18
75086 | G7MAINS | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 254837.76 |  | 254837.76 |  |  | 254837.76 | 147466.28 | 107371.48 | 2019-06-27 10:02 | 2019-12-26 | 2019-07-01
75086 | G7MAINS | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 256521.07 |  | 256521.07 |  |  | 256521.07 | 515675 | -259153.93 | 2019-10-25 18:01 | 2020-05-28 | 2019-10-01 | 2020-07-20
75086 | G7PUBIMP | MX1376296 | Longbranch Rd. | 113809.28 |  | 113809.28 |  |  | 113809.28 | 70969.1 | 42840.18 | 2019-08-02 14:01 | 2020-03-05 | 2019-09-01 | 2020-09-15
75086 | G7PRESIM | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 888721.98 |  | 888721.98 |  |  | 888721.98 | 760041.64 | 128680.34 | 2019-06-04 14:01 | 2020-02-26 | 2019-06-01 | 2020-01-15
75086 | G7MAINS | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | -73.28 |  | -73.28 |  |  | 44120.71 | 59353.94 | -15233.23 | 2018-03-26 14:06 | 2018-08-03 | 2018-04-01 | 2019-01-06
75086 | G7LGMR | MX1715658 | STA 809 - WATERWORKS RD - Station | 586101.32 |  | 586101.32 |  |  | 776210.06 | 258620 | 517590.06 | 2017-12-05 10:02 | 2019-03-31 | 2018-03-01 | 2018-09-08
75086 | G7PUBIMP | MX1761035 | WENDELL H. FORD BLVD. | -15207.21 |  | -15207.21 |  |  | -15207.21 | 46004.5 | -61211.71 | 2019-03-20 14:01 | 2019-05-10 | 2019-03-01 | 2019-09-01
75086 | G7MAINS | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 114031.58 |  | 114031.58 |  |  | 114031.58 | 115345.51 | -1313.93 | 2019-04-08 14:01 | 2019-08-18 | 2019-05-01 | 2019-10-19
75086 | G7IMPRPL | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 214164.36 |  | 214164.36 |  |  | 812309.81 | 436474.83 | 375834.98 | 2017-09-11 18:02 | 2019-07-31 | 2017-10-01 | 2019-09-10
75086 | G7REPL | MX1998720 | Safran (Messier Bugatti) Main Rep | 5567.84 |  | 5567.84 |  |  | 19458 | 436546.75 | -417088.75 | 2017-10-26 18:02 | 2018-05-01 | 2017-11-01 | 2018-05-20
75086 | G7MAINS | MX2142600 | FARM TAP PROJ; THORNTON RD | 25699.46 |  | 25699.46 |  |  | 25699.46 | 54541.9 | -28842.44 | 2019-07-18 18:01 | 2019-12-19 | 2019-07-01
75086 | G7MAINS | MX2143073 | FARM TAP PROJ; REIDLIN RD | 36743.3 |  | 36743.3 |  |  | 36743.3 | 43437.77 | -6694.47 | 2019-05-21 18:01 | 2019-10-31 | 2019-06-01
75086 | G7LGMR | MX2217911 | STA 863 - GRANDVIEW ROAD | -109869.78 |  | -109869.78 |  |  | 212140.46 | 199415.84 | 12724.62 | 2017-09-22 14:01 | 2019-03-31 | 2017-10-01 | 2018-08-16
75086 | G7LGMR | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 9277.31 |  | 9277.31 |  |  | 225926.77 | 411228.18 | -185301.41 | 2017-09-21 14:01 | 2020-07-10 | 2017-10-01 | 2020-09-15
75086 | G7MAINS | MX2243303 | STA 809 - WATERWORKS RD INLET | 80869.11 |  | 80869.11 |  |  | 239326.82 | 269953 | -30626.18 | 2018-01-30 18:02 | 2018-07-01 | 2018-03-01 | 2018-09-08
75086 | G7MAINS | MX2271880 | MEA ~800 FT; 494 JONES RD | 214602.63 |  | 214602.63 |  |  | 214602.63 | 163070 | 51532.63 | 2019-07-30 10:01 | 2020-02-27 | 2019-08-01
75086 | G7LGMR | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 11266260.67 |  | 11266260.67 |  |  | 13253302.7 | 12669920 | 583382.7 | 2017-10-06 18:03 | 2019-08-15 | 2017-11-01 | 2019-09-19
75086 | G7LGMR | MX2336558 | STA 865 Southridge Dr | 964623.54 |  | 964623.54 |  |  | 1020571.24 | 334647 | 685924.24 | 2017-10-18 10:47 | 2019-06-01 | 2017-10-01 | 2019-06-19
75086 | G7MAINS | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 36324.36 |  | 36324.36 |  |  | 39734.02 | 51328.32 | -11594.3 | 2018-06-04 10:02 | 2019-06-01 | 2018-07-01 | 2019-06-17
75086 | G7MAINS | MX2336650 | INSTALL STATION OUTLET PIPING | 13178.4 |  | 13178.4 |  |  | 14752.38 | 45232.32 | -30479.94 | 2018-06-04 10:02 | 2018-11-01 | 2018-07-01 | 2019-06-19
75086 | G7PUBIMP | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 109005.89 |  | 109005.89 |  |  | 140681.23 | 129952.9 | 10728.33 | 2018-05-14 14:02 | 2018-08-26 | 2018-05-01 | 2018-10-24
75086 | G7LGMR | MX2386654 | STA 901 - MARY GRUBBS | 318288.07 |  | 318288.07 |  |  | 318288.07 | 357835.2 | -39547.13 | 2019-06-24 10:02 | 2019-10-31 | 2019-06-01 | 2020-02-19
75086 | G7MAINS | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 60030.81 |  | 60030.81 |  |  | 60030.81 | 52259.7 | 7771.11 | 2019-06-19 14:01 | 2019-10-06 | 2019-06-01 | 2019-12-30
75086 | G7MAINS | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 31945.84 |  | 31945.84 |  |  | 31945.84 | 50615.9 | -18670.06 | 2019-07-02 14:01 | 2019-12-12 | 2019-07-01
75086 | G7MAINS | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 19249.68 |  | 19249.68 |  |  | 19249.68 | 64364 | -45114.32 | 2019-08-13 10:01 | 2020-07-28 | 2019-09-01 | 2020-03-10
75086 | G7PUBIMP | MX2541899 | KY-36/I-75 Interchange Reconstruct | 457280.85 |  | 457280.85 |  |  | 1124060.18 | 906757 | 217303.18 | 2018-03-02 10:01 | 2018-06-03 | 2018-04-01 | 2018-11-02
75086 | G7MAINS | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 85823.72 |  | 85823.72 |  |  | 85823.72 | 205184 | -119360.28 | 2019-10-04 14:01 | 2020-03-11 | 2019-11-01 | 2020-05-15
75086 | G7MAINS | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 46373.76 |  | 46373.76 |  |  | 46373.76 | 60768.22 | -14394.46 | 2019-08-27 18:01 | 2020-03-18 | 2019-09-01 | 2020-06-08
75086 | G7PUBIMP | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | -24402.04 |  | -24402.04 |  |  | -24402.04 | 101493.8 | -125895.84 | 2019-10-01 18:01 | 2020-02-27 | 2019-10-01 | 2020-04-09
75086 | G7MAINS | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 4814.36 |  | 4814.36 |  |  | 4814.36 | 60345 | -55530.64 | 2019-11-19 10:01 | 2020-04-23 | 2019-12-01 | 2020-05-31
75086 | G7PUBIMP | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 21052.4 |  | 21052.4 |  |  | 21052.4 | 99383.99 | -78331.59 | 2019-09-20 14:01 | 2020-04-03 | 2019-12-01 | 2020-07-09
75086 | G7MAINS | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 54923.89 |  | 54923.89 |  |  | 54923.89 | 77219 | -22295.11 | 2019-09-30 15:56 | 2020-01-19 | 2019-10-01 | 2020-03-11
75086 | G7MAINS | MX2848811 | INDEPENDENCE RD MEA - | 5311.07 |  | 5311.07 |  |  | 5311.07 | 35185 | -29873.93 | 2019-09-30 10:01 | 2020-01-30 | 2019-10-01
75086 | G7PUBIMP | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 22251.94 |  | 22251.94 |  |  | 22251.94 | 51296.38 | -29044.44 | 2019-08-02 14:01 | 2020-01-09 | 2019-09-01 | 2020-09-15
75086 | G7MAINS | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 36341.25 |  | 36341.25 |  |  | 36341.25 | 51274.67 | -14933.42 | 2019-08-28 14:01 | 2020-01-05 | 2019-09-01 | 2020-03-26
75086 | G7MAINS | MX3444104 | MEA ~970 FT; ASHLEY DR | 50199.51 |  | 50199.51 |  |  | 50199.51 | 93363 | -43163.49 | 2019-09-13 14:01 | 2019-12-29 | 2019-09-01 | 2020-02-25
75086 | G7MAINS | MX3745351 | MEA ~200 FT; LEE LN | 14101.86 |  | 14101.86 |  |  | 14101.86 | 34346 | -20244.14 | 2019-10-18 10:01 | 2020-02-02 | 2019-10-01 | 2020-04-02
75086 | G7MAINS | MX3790373 | Williams Way-MEA | 17723.44 |  | 17723.44 |  |  | 17723.44 | 33505 | -15781.56 | 2019-10-08 10:01 | 2020-01-19 | 2019-10-01 | 2020-03-01
75086 | G7MAINS | MX4018013 | JOHNS HILL RD MEA | 17098.45 |  | 17098.45 |  |  | 17098.45 | 73344 | -56245.55 | 2019-11-13 10:01 | 2020-01-03 | 2019-11-01 | 2020-06-18
75086 | G7REPL | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 32749.08 |  | 32749.08 |  |  | 32749.08 | 72427 | -39677.92 | 2019-10-11 10:01 | 2020-03-19 | 2019-10-01 | 2020-04-15
75086 | G7MAINS | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 4242.12 |  | 4242.12 |  |  | 4242.12 | 95523.06 | -91280.94 | 2019-12-02 14:01 | 2020-04-22 | 2019-12-01 | 2020-08-16
75086 | G7MAINS | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 1863.41 |  | 1863.41 |  |  | 1863.41 | 41217 | -39353.59 | 2019-12-02 18:01 | 2021-04-02 | 2019-12-01 | 2020-06-18
75086 | G7MAINS | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 2184.2 |  | 2184.2 |  |  | 2184.2 | 13325 | -11140.8 | 2019-10-01 14:01 | 2020-02-13 | 2019-11-01
75086 | G7REPL | MX4342633 | Pleasant Valley Steel Rep (Founders | 26848.36 |  | 26848.36 |  |  | 26848.36 | 166756 | -139907.64 | 2019-10-18 10:01 | 2020-02-28 | 2019-10-01 | 2020-06-26
75086 | G7IMPRPL | MX6468802 | AM07 Casing #46 Replacement | 177359.13 |  | 177359.13 |  |  | 1946398.72 | 2040466 | -94067.28 | 2017-12-05 14:02 | 2019-01-01 | 2017-12-01 | 2019-01-12
75086 | G7LGMR | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 3086.02 |  | 3086.02 |  |  | 37612.04 | 106314.24 | -68702.2 | 2017-12-15 14:01 | 2021-03-31 | 2018-02-01
75086 | G7PUBIMP | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 145064.25 |  | 145064.25 |  |  | 189234.84 | 279194 | -89959.16 | 2018-03-02 10:01 | 2018-05-25 | 2018-03-01 | 2018-10-25
75086 | G7MAINS | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 160235.37 |  | 160235.37 |  |  | 188406.7 | 92300.06 | 96106.64 | 2018-09-04 18:02 | 2018-11-09 | 2018-10-01 | 2019-04-03
75086 | G7STA876 | MX6800938 | STA 876 WARSAW TOWN BORDER- Station | 26442.32 |  | 26442.32 |  |  | 39154.59 | 252984 | -213829.41 | 2018-01-10 18:02 | 2021-09-06 | 2018-01-01
75086 | G7LGMR | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 28481.54 |  | 28481.54 |  |  | 28481.54 | 139842.24 | -111360.7 | 2018-04-04 10:01 | 2021-03-31 | 2019-01-01
75086 | G7MAINS | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 1414.86 |  | 1414.86 |  |  | 23655.12 | 38542.37 | -14887.25 | 2018-02-20 18:02 | 2018-04-09 | 2018-03-01 | 2018-10-04
75086 | G7REPL | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | -116600.88 |  | -116600.88 |  |  | 2437.9 | 64481.4 | -62043.5 | 2018-03-29 18:04 | 2018-07-15 | 2018-04-01 | 2018-09-21
75086 | G7MAINS | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 33707.56 |  | 33707.56 |  |  | 33707.56 | 55888.13 | -22180.57 | 2018-05-10 14:01 | 2018-11-01 | 2019-02-01 | 2019-07-06
75086 | G7MAINS | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | -317.88 |  | -317.88 |  |  | 4390.82 | 57864.49 | -53473.67 | 2018-04-30 10:28 | 2018-09-07 | 2018-05-01 | 2018-12-12
75086 | G7PUBIMP | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 8955.41 |  | 8955.41 |  |  | 232261.07 | 238847.13 | -6586.06 | 2018-04-06 18:03 | 2018-08-24 | 2018-04-01 | 2018-10-26
75086 | G7PUBIMP | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 49629.1 |  | 49629.1 |  |  | 49629.1 | 99125.15 | -49496.05 | 2019-08-02 10:01 | 2020-02-27 | 2019-08-01 | 2020-02-29
75086 | G7MAINS | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 150044.97 |  | 150044.97 |  |  | 176689.81 | 172975.63 | 3714.18 | 2018-08-07 10:03 | 2018-11-12 | 2018-10-01 | 2019-03-08
75086 | G7PUBIMP | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | -33639.56 |  | -33639.56 |  |  | 16531.31 | 45950.78 | -29419.47 | 2018-04-04 14:01 | 2018-08-24 | 2018-04-01
75086 | G7LGMR | MX7686017 | INSTALL SCADA EQUIPMENT | -50.81 |  | -50.81 |  |  | 6688.96 | 24676.61 | -17987.65 | 2018-03-23 10:01 | 2018-10-01 | 2018-04-01 | 2019-01-01
75086 | G7PUBIMP | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 185438.58 |  | 185438.58 |  |  | 185438.58 | 183481.42 | 1957.16 | 2019-04-03 14:01 | 2019-07-14 | 2019-04-01 | 2019-10-03
75086 | G7MAINS | MX7722964 | MEA PROJECT LIMABURG RD | 272282.29 |  | 272282.29 |  |  | 330699.27 | 302578.49 | 28120.78 | 2018-08-15 14:02 | 2018-10-05 | 2018-08-01 | 2019-03-03
75086 | G7MAINS | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 29638.62 |  | 29638.62 |  |  | 36084.18 | 38185.68 | -2101.5 | 2018-05-02 14:01 | 2018-09-17 | 2018-05-01 | 2018-10-11
75086 | G7MAINS | MX7865414 | Gas Main Extension - Production Dr, | 116376.71 |  | 116376.71 |  |  | 149425.41 | 100410.13 | 49015.28 | 2018-06-28 16:40 | 2018-08-31 | 2018-07-01 | 2019-01-20
75086 | G7REPL | MX8171793 | INSTALL REPLACEMENT PROJECT | 49362.74 |  | 49362.74 |  |  | -10353.77 | 84327.5 | -94681.27 | 2018-08-03 18:04 | 2018-09-28 | 2018-08-01 | 2019-01-16
75086 | G7LGMR | MX8312879 | Install Odorant Flare Systems KY | -0.1 |  | -0.1 |  |  | 676.93 | 8112.3 | -7435.37 | 2018-06-01 10:01 | 2018-12-31 | 2018-08-01 | 2019-03-31
75086 | G7MAINS | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 6824.02 |  | 6824.02 |  |  | 6824.02 | 57033 | -50208.98 | 2018-09-28 14:02 | 2019-01-25 | 2019-11-01 | 2020-07-06
75086 | G7MAINS | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 25283.57 |  | 25283.57 |  |  | 30455.59 | 65454.13 | -34998.54 | 2018-08-21 14:02 | 2019-06-06 | 2018-11-01 | 2019-05-19
75086 | G7MAINS | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 83887.37 |  | 83887.37 |  |  | 100253.49 | 80515.92 | 19737.57 | 2018-08-22 14:02 | 2018-10-19 | 2018-08-01
75086 | G7LGMR | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 18714.98 |  | 18714.98 |  |  | 18714.98 | 107193 | -88478.02 | 2018-12-11 10:01 | 2019-09-30 | 2019-03-01 | 2019-10-24
75086 | G7MAINS | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 28953.54 |  | 28953.54 |  |  | 39486.95 | 68031.36 | -28544.41 | 2018-09-28 14:02 | 2019-06-06 | 2018-11-01 | 2019-04-15
75086 | G7LGMR | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 40540.06 |  | 40540.06 |  |  | 40540.06 | 262006.08 | -221466.02 | 2019-03-21 14:01 | 2020-08-31 | 2019-05-01
75086 | G7PUBIMP | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 333833.59 |  | 333833.59 |  |  | 368845.48 | 208010.18 | 160835.3 | 2018-06-14 14:01 | 2018-10-12 | 2018-06-01 | 2019-02-03
75086 | G7MAINS | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 50175.29 |  | 50175.29 |  |  | 50175.29 | 54068 | -3892.71 | 2018-09-28 14:02 | 2019-06-14 | 2019-02-01 | 2019-07-06
75086 | G7REPL | MX9056339 | St. Matthews Circle Replacement | 89026.63 |  | 89026.63 |  |  | 94050.01 | 107808.25 | -13758.24 | 2018-09-25 14:02 | 2019-02-03 | 2018-10-01 | 2019-08-20
75086 | G7PRESIM | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0.7 |  | 0.7 |  |  | 2376.82 | 0 | 2376.82 | 2018-09-24 14:02 | 2018-11-16 | 2018-12-01 | 2019-04-03
75086 | GPRESIMP | MX9177822 | INSTALL PRESSURE IMPROVEMENT PROJEC | 341702.57 |  | 341702.57 |  |  | 378616.03 | 283021.16 | 95594.87 | 2018-11-14 10:01 | 2019-01-11 | 2018-12-01 | 2019-04-04
75086 | G7MAINS | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | -1667.23 |  | -1667.23 |  |  | 16780.57 | 179827.05 | -163046.48 | 2018-10-11 18:03 | 2018-12-14 | 2018-10-01 | 2019-02-06
75086 | G7MAINS | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 149504.67 |  | 149504.67 |  |  | 158912.61 | 152463.07 | 6449.54 | 2018-11-09 14:02 | 2019-02-24 | 2018-12-01 | 2019-04-14
75086 | G7PUBIMP | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 26327.73 |  | 26327.73 |  |  | 26327.73 | 50718.49 | -24390.76 | 2019-04-10 14:01 | 2019-08-04 | 2019-05-01 | 2019-09-01
75087 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 156.05 |  | 156.05 |  |  | 2949119.81 | 807214 | 2141905.81 | 2016-02-11 12:05 | 2018-10-31 | 2016-03-01 | 2018-10-31
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | -38372.33 |  | -38372.33 |  |  | 2873099.49 | 105161.63 | 2767937.86 | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7BIGBON | R2190 | Big Bone Pipeline | 531323.56 |  | 531323.56 |  |  | 27762152.14 | 25488221 | 2273931.14 | 2015-08-04 16:11 | 2018-05-28 | 2015-10-01 | 2018-08-05
75086 | G7LGMR | R2901 | STA 838 Mineola Pike - Station | 10388.79 |  | 10388.79 |  |  | 480286.11 | 209397.6 | 270888.51 | 2015-09-10 16:12 | 2018-05-31 | 2016-04-01 | 2018-02-14
75086 | G7REPL | R4407 | RP 9097151 AM | -179.63 |  | -179.63 |  |  | 461372.54 | 467928.96 | -6556.42 | 2015-11-11 12:51 | 2017-03-01 | 2015-11-01 | 2016-02-18
75086 | G7PUBIMP | R5767 | GO 8346362 KY 9 North recon | 64716.74 |  | 64716.74 |  |  | 89400.48 | 335536.03 | -246135.55 | 2016-01-11 10:41 | 2018-06-01 | 2016-01-01 | 2016-07-12
75086 | G7PUBIMP | S1056 | STI 10177360 Latonia Lakes Str Impr | 83548.01 |  | 83548.01 |  |  | 95112.11 | 52785.89 | 42326.22 | 2016-04-15 16:46 | 2016-10-31 | 2016-04-01 | 2016-09-18
75086 | G7MAINS | S2732 | GO 9691430 Sta 836 Inlet Piping | 559.7 |  | 559.7 |  |  | 38529.56 | 91976.45 | -53446.89 | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01
75086 | G7REPL | S5697 | RPL 10420236 Ft Wright Elem | 2122.98 |  | 2122.98 |  |  | 2445.15 | 15249.75 | -12804.6 | 2016-05-13 08:59 | 2016-10-22 | 2016-05-01 | 2016-10-16
75086 | G7REPL | S8375 | STA 838 Mineola Pike - Inlet | -76.17 |  | -76.17 |  |  | 94760.72 | 33588.96 | 61171.76 | 2016-06-23 09:04 | 2018-12-30 | 2017-08-01 | 2018-02-14
75086 | G7MAINS | S8847 | GO 9527853 820 Dolwick Dr | -81.98 |  | -81.98 |  |  | 78578.68 | 169442.7 | -90864.02 | 2016-07-25 12:25 | 2017-03-31 | 2016-07-01 | 2017-02-15
75086 | G7PUBIMP | S8867 | STI 10873483 Mt Zion Rd | 463800.67 |  | 463800.67 |  |  | 1276278.99 | 447690.24 | 828588.75 | 2016-07-26 13:07 | 2020-01-30 | 2017-01-01 | 2019-12-21
75086 | G7LGMR | S9586 | STA 11212247 Erlanger Compressor | -232.72 |  | -232.72 |  |  | 8304.71 | 28706.06 | -20401.35 | 2016-09-12 14:54 | 2018-12-31 | 2016-10-01 | 2017-02-28
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 1884796.28 |  | 1884796.28 |  |  | 6395123.04 | 2250000 | 4145123.04 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SGKAMIF | SG169MTRS | SG KY AMI Gas Meters - 169 | -119031.56 |  | -119031.56 |  |  | 9373937.81 | 9563026 | -189088.19 | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75086 | SG000358F | SG358HW19 | SG DEE MDM Scale HWre Phase 4 - 358 | 4352.74 |  | 4352.74 |  |  | 40190.93 | 21102.66 | 19088.27 | 2018-05-09 10:59 | 2019-08-18 | 2018-05-01 | 2019-09-24
75086 | SG000358F | SG358SVR | DEE MDM Scale | 792.43 |  | 792.43 |  |  | 792.43 | 1048 | -255.57 | 2019-09-24 08:02 | 2020-01-31 | 2019-11-01 | 2020-03-31
75086 | SG000358F | SG358SW2 | SG DEE MDM Scale Sftwre Phs 4 - 358 | 10972.21 |  | 10972.21 |  |  | 23852.9 | 7317.09 | 16535.81 | 2018-05-07 17:00 | 2019-08-18 | 2018-05-01 | 2019-09-24
75086 | SG000489F | SG489SVR2 | DEE Openway Scale | 10747.48 |  | 10747.48 |  |  | 10747.48 | 15568 | -4820.52 | 2019-01-22 21:54 | 2020-03-31 | 2019-01-01 | 2019-09-30
75086 | SG000489F | SG489SVR3 | DEE Openway Scale | 7.22 |  | 7.22 |  |  | 7.22 | 1190 | -1182.78 | 2019-09-25 08:08 | 2020-10-31 | 2019-09-01 | 2020-10-26
75086 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 690.37 |  | 690.37 |  |  | 29590.41 | 31329.67 | -1739.26 | 2017-04-24 18:13 | 2018-12-31 | 2017-05-01 | 2019-03-31
75086 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | -36.99 |  | -36.99 |  |  | 20645.09 | 16065.37 | 4579.72 | 2016-11-23 11:25 | 2018-12-31 | 2016-11-01 | 2019-03-31
75086 | SG000540F | SG540HW | DEE Vehicle Area Network | 50807.03 |  | 50807.03 |  |  | 57586.68 | 117926 | -60339.32 | 2018-04-13 13:13 | 2020-12-17 | 2018-09-01
75086 | SG000540F | SG540SW | DEE Vehicle Area Network | 0.02 |  | 0.02 |  |  | 0.02 | 107801 | -107800.98 | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01 | 2018-07-16
75086 | SG000540F | SG540SW3 | DEE Vehicle Area Network | 188953.57 |  | 188953.57 |  |  | 188953.57 | 9610 | 179343.57 | 2018-04-19 09:58 | 2020-12-17 | 2019-04-01
75086 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | 48791.12 |  | 48791.12 |  |  | 78448.67 | 76873.76 | 1574.91 | 2018-07-12 09:17 | 2021-03-31 | 2018-07-01
75086 | G7LGMR | T0425 | SCAD 11456765 Mineola Pike Sta | -849.69 |  | -849.69 |  |  | 23188.34 | 55991.76 | -32803.42 | 2016-11-03 09:31 | 2018-12-01 | 2017-01-01 | 2018-04-30
75086 | G7LGMR | T0645 | STA 839 Richwood Station | 9728.13 |  | 9728.13 |  |  | 362072.27 | 157154.88 | 204917.39 | 2016-11-14 09:37 | 2018-12-28 | 2017-02-01 | 2018-08-05
75086 | G7LGMR | T0646 | STA 835 Walton - Station | -269815.55 |  | -269815.55 |  |  | 492896.7 | 157154.88 | 335741.82 | 2016-11-14 09:54 | 2018-12-01 | 2017-04-01 | 2018-09-06
75086 | G7REPL | T0647 | RPL 11581212 140 Railroad St | -1331.46 |  | -1331.46 |  |  | 16394.05 | 32101.54 | -15707.49 | 2016-11-14 10:54 | 2017-07-31 | 2016-11-01 | 2017-02-14
75086 | G7LGMR | T0746 | AM00a Automation of RCV Cold Spring | -118690.33 |  | -118690.33 |  |  | 318424.39 | 380490 | -62065.61 | 2016-11-18 11:04 | 2018-12-30 | 2017-02-01 | 2019-01-04
75086 | G73MILES | T0747 | AM00a Automation of RCV -Alexandria | -25366.57 |  | -25366.57 |  |  | 151518.31 | 415030 | -263511.69 | 2016-11-18 11:23 | 2020-02-28 | 2016-12-01 | 2018-06-15
75086 | G7BIGBON | T0881 | Big Bone Odorant Station - SCADA | 9579.67 |  | 9579.67 |  |  | 195248.83 | 351251.52 | -156002.69 | 2016-12-01 12:00 | 2018-12-01 | 2017-04-01 | 2018-08-05
75086 | G73MILES | T1437 | STA 249: Three Mile Rd | 9991909.53 |  | 9991909.53 |  |  | 13544897.91 | 15406228 | -1861330.09 | 2017-01-05 11:19 | 2020-08-28 | 2017-01-01 | 2020-09-15
75086 | G73MILES | T1437LAND | 3 Mile Station (LAND) | 38.05 |  | 38.05 |  |  | 2619.52 | 40000 | -37380.48 | 2018-06-22 15:02 | 2020-07-28 | 2018-09-01 | 2020-09-15
75086 | G7LGMR | T1465 | STA 855 Taylor Mill Rd - Station | 12662.99 |  | 12662.99 |  |  | 204823.13 | 83246.98 | 121576.15 | 2017-01-06 16:24 | 2018-04-19 | 2017-03-01 | 2018-04-24
75086 | G7LGMR | T1486 | STA 855 Taylor Mill Rd - Outlet | -718.63 |  | -718.63 |  |  | 30798.81 | 18239.23 | 12559.58 | 2017-01-09 11:23 | 2018-04-19 | 2017-09-01 | 2018-04-24
75086 | G7IMPRPL | T1525 | AM02 Exposed Main in Southgate, KY | 23393.98 |  | 23393.98 |  |  | 874043.53 | 351129.6 | 522913.93 | 2017-01-12 09:24 | 2018-09-30 | 2017-01-01 | 2018-11-24
75086 | G7REPL | T1796 | Showcase AM07 | -1183320.01 |  | -1183320.01 |  |  | 24406.32 | 3343471.9 | -3319065.58 | 2017-01-27 15:35 | 2018-04-30 | 2017-01-01 | 2018-08-09
75086 | G7LGMR | T2218 | STA 838 Mineola Pike - Outlet | 93.34 |  | 93.34 |  |  | 44831.92 | 23225.76 | 21606.16 | 2017-02-15 15:45 | 2018-08-31 | 2017-05-01 | 2018-02-14
75086 | G73MILES | T4422 | AM07 Barleycorns | 148020.04 |  | 148020.04 |  |  | 221545.36 | 190195.2 | 31350.16 | 2017-03-22 16:39 | 2020-07-28 | 2017-04-01 | 2019-12-01
75086 | G7LGMR | T5473 | SCAD 21012299 Pressure Transmiitter | -1847.05 |  | -1847.05 |  |  | 50504.12 | 91500.96 | -40996.84 | 2017-03-31 07:27 | 2018-12-01 | 2017-06-01 | 2017-09-30
75086 | G7LGMR | T7966 | STA 859 Banklick Rd - Station | -30763.88 |  | -30763.88 |  |  | 281429.31 | 215078.32 | 66350.99 | 2017-05-10 15:15 | 2018-07-01 | 2017-09-01 | 2018-07-17
75086 | G7REPL | T8295 | RPL 21421581 Latonia Lakes | 214070.28 |  | 214070.28 |  |  | 210770.66 | 118055.14 | 92715.52 | 2017-05-30 16:11 | 2018-03-30 | 2017-06-01 | 2017-10-15
75086 | G7PUBIMP | T8343 | STI 20956764 Weaver Rd. | 550.57 |  | 550.57 |  |  | 6525.71 | 39100.39 | -32574.68 | 2017-05-31 13:21 | 2018-05-01 | 2017-07-01 | 2017-11-29
75086 | G7LP3 | U8785 | Emergency Line LP-3 | 235652.02 |  | 235652.02 |  |  | 8699427.99 | 7865574 | 833853.99 | 2018-03-21 08:40 | 2019-02-28 | 2018-04-01 | 2019-02-16
75086 | G7UL02 | V0767 | UL02 ECDA Scheduled Digs | 576.86 |  | 576.86 |  |  | 224511.64 | 35000 | 189511.64 | 2018-05-10 12:53 | 2018-11-30 | 2018-10-01 | 2018-11-30
75086 | G7ERLACPI | V2339 | Erlangar OP Center Anodes | 54625.88 |  | 54625.88 |  |  | 194648.98 | 350000 | -155351.02 | 2018-06-20 15:56 | 2018-12-30 | 2018-06-01 | 2019-02-15
75086 | G7CAS112 | V4266 | Casing 112 Line AM07 | 188340.08 |  | 188340.08 |  |  | 253708.44 | 257083 | -3374.56 | 2018-08-02 14:00 | 2018-12-30 | 2018-08-01 | 2019-01-22
75086 | G7CAS22 | V4278 | Casing 22 Line AM07 | 221975.11 |  | 221975.11 |  |  | 241921.1 | 311445 | -69523.9 | 2018-08-02 16:45 | 2018-12-30 | 2018-08-01 | 2019-01-01
75086 | FPIT | V5136 | Communication Radio Install | 522.85 |  | 522.85 |  |  | 27350.42 | 23120 | 4230.42 | 2018-08-20 08:22 | 2018-12-31 | 2018-08-01
75086 | G7ERLPLAN | V5155 | Erlanger Propane Plant Upgrades | 90364.66 |  | 90364.66 |  |  | 1032224.82 | 403571.6 | 628653.22 | 2018-08-21 12:58 | 2018-12-31 | 2018-08-01 | 2019-07-01
75086 | G7SECCON | V5175 | Erlanger Propane Security Upgrade | 2919607.46 |  | 2919607.46 |  |  | 2919607.46 | 950000 | 1969607.46 | 2018-08-21 17:03 | 2020-05-14 | 2019-02-01 | 2020-03-31
75086 | G7SECCAM | V5199 | Erlanger Security Camera | 38477.67 |  | 38477.67 |  |  | 38477.67 | 214455.54 | -175977.87 | 2018-08-22 08:59 | 2019-03-30 | 2019-07-01 | 2019-07-01
75086 | FP647 | V5213 | AM07 Casing Rem 647 Erlanger rd | -1854.68 |  | -1854.68 |  |  | 74287.72 | 115206.73 | -40919.01 | 2018-08-22 09:19 | 2019-03-30 | 2018-09-01 | 2018-11-23
75086 | G7CAS53 | V5417 | Casing 53 Line AM07 | 43050.27 |  | 43050.27 |  |  | 86464.88 | 409578 | -323113.12 | 2018-08-29 07:10 | 2018-12-30 | 2018-10-01 | 2019-03-01
75086 | G7EUL06 | V5625 | ECDA Line UL06 | 60296.55 |  | 60296.55 |  |  | 301379.8 | 494420 | -193040.2 | 2018-09-10 09:20 | 2019-03-30 | 2018-10-01 | 2019-03-17
75086 | G7LNLP03 | V5652 | Line LP03 | 23574.31 |  | 23574.31 |  |  | 886866.98 | 1325999 | -439132.02 | 2018-09-11 07:37 | 2019-02-28 | 2018-10-01 | 2019-02-15
75086 | G7EUL47 | V6391 | Line UL47 scheduled digs | 741449.94 |  | 741449.94 |  |  | 988465.84 | 724400 | 264065.84 | 2018-10-10 08:17 | 2019-03-30 | 2018-10-01 | 2019-03-14
75086 | G7S3300 | V7041 | Line UL02 Seg 3300 Pleasant Valley | 1754856.27 |  | 1754856.27 |  |  | 1754856.27 | 2643704 | -888847.73 | 2018-11-06 14:02 | 2020-07-30 | 2019-01-01 | 2020-01-15
75086 | G7PHMSA | V7283 | PHMSA CRM Plan | 1284077.13 |  | 1284077.13 |  |  | 1436583.31 | 416794 | 1019789.31 | 2018-11-14 14:31 | 2020-09-30 | 2018-12-01
75086 | G7CAS106 | V7737 | Casing#106 AM07 & Martha Layne | 2174001.6 |  | 2174001.6 |  |  | 2176756.99 | 1749344 | 427412.99 | 2018-11-28 14:40 | 2019-12-30 | 2018-12-01 | 2020-01-23
75086 | G7CAS106 | V7738 | Casing#106 AM07 & Martha Layne(LAND | 96493.01 |  | 96493.01 |  |  | 96493.01 | 10000 | 86493.01 | 2018-11-28 14:46 | 2019-12-30 | 2019-01-01 | 2020-01-23
75086 | G7CAS42 | V7739 | Casing#42 abandon- AM07 & Hulbert | 1712152.13 |  | 1712152.13 |  |  | 1714907.52 | 1939294 | -224386.48 | 2018-11-28 14:52 | 2019-11-30 | 2018-12-01 | 2019-11-15
75086 | G7CAS49 | V7902 | Casing #49 abandon - AM07 & I-75 | 6981908.44 |  | 6981908.44 |  |  | 6981908.44 | 6131715 | 850193.44 | 2018-12-14 14:26 | 2020-02-28 | 2019-01-01 | 2020-02-23
75086 | G7CAS717 | V7904 | Casing #717 Line AM07 -US RT 50 | 401129.12 |  | 401129.12 |  |  | 401129.12 | 2072166 | -1671036.88 | 2018-12-14 14:36 | 2019-07-25 | 2019-01-01 | 2019-08-21
75086 | G7STA883 | V8108 | STA-883 Chapman Lane Station | 762040.12 |  | 762040.12 |  |  | 762040.12 | 767000 | -4959.88 | 2019-01-14 08:15 | 2019-07-30 | 2019-01-01 | 2019-06-20
75086 | G7UL02PH1 | V8191 | UL60 Pipeline Phase 1 (PIPE) | 1796837.14 |  | 1796837.14 |  |  | 1796837.14 | 26326195 | -24529357.86 | 2019-01-23 15:21 | 2021-03-30 | 2019-01-01 | 2021-02-25
75086 | G7UL02PH1 | V8351 | UL60 Pipeline Phase 1 (STATION) | 344.15 |  | 344.15 |  |  | 344.15 | 6287827 | -6287482.85 | 2019-02-11 09:25 | 2021-03-30 | 2019-07-01 | 2021-03-13
75086 | G7UL02PH1 | V8352 | UL60 Pipeline P1 - LAND RIGHTS Proj | 1054937.39 |  | 1054937.39 |  |  | 1054937.39 | 1941000 | -886062.61 | 2019-02-11 09:32 | 2021-03-30 | 2019-03-01 | 2021-02-25
75086 | G73701 | V8405 | Bridge Attach 3701 Narrows Rd | 13226.07 |  | 13226.07 |  |  | 13226.07 | 11495.55 | 1730.52 | 2019-02-18 10:01 | 2020-02-25 | 2019-09-01 | 2019-12-18
75086 | G7CAS718 | V8637 | Casing #718 AM07C US RT 50 | 810360.91 |  | 810360.91 |  |  | 810360.91 | 723819 | 86541.91 | 2019-03-13 15:45 | 2019-12-30 | 2019-04-01 | 2019-12-06
75086 | G7AM07DIG | V8815 | Line AM07 Integrity Digs | 1243684.85 |  | 1243684.85 |  |  | 1243684.85 | 923350 | 320334.85 | 2019-04-02 12:33 | 2019-12-30 | 2019-06-01 | 2019-12-31
75086 | G7EQUIP | V8884 | KET NGBU Equipment | 17454.51 |  | 17454.51 |  |  | 17454.51 | 150768 | -133313.49 | 2019-04-11 08:23 | 2020-03-30 | 2019-06-01 | 2020-02-29
75086 | G7ECOMPLX | V8967 | Erlanger Modular Complex | 21036.84 |  | 21036.84 |  |  | 21036.84 | 244737.99 | -223701.15 | 2019-04-17 13:32 | 2020-10-30 | 2019-06-01
75086 | G7EPROPAN | V9131 | Erlanger OPP | 311963.53 |  | 311963.53 |  |  | 311963.53 | 954130.54 | -642167.01 | 2019-05-03 10:23 | 2020-03-30 | 2019-08-01 | 2020-10-31
75086 | G7ERLCP19 | V9157 | 2019 Erlanger Ops Mag Anodes | 350649.67 |  | 350649.67 |  |  | 350649.67 | 350811.63 | -161.96 | 2019-05-08 10:16 | 2020-07-30 | 2019-05-01 | 2020-09-08
75086 | G7UL02PH2 | V9444 | UL60 Pipeline Phase II - Pipe | 70934.76 |  | 70934.76 |  |  | 70934.76 | 22514005 | -22443070.24 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01
75086 | G7UL02PH2 | V9445 | UL60 Pipeline Phase II- LAND RIGHTS | 109142.95 |  | 109142.95 |  |  | 109142.95 | 733000 | -623857.05 | 2019-06-12 08:04 | 2022-02-02 | 2019-07-01
|  |  |  | 94023325.59 | 49489262 | -44534063.59

## 2020
Duke Energy Kentucky Gas
Year 2020
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | G7AM07ILI | 0233100 | Line AM07 Pipeline Replacement Phas | 1433.07 |  | 1433.07 |  |  | 1433.07 | 37717000 | -37715566.93 | 2020-12-09 14:11 | 2024-02-28 | 2020-12-01
75086 | FUNCTOHKY | 107GASCK | Gas Capital Overhead | 316382.58 |  | 316382.58 |  |  | 531208.28 | 0 | 531208.28 | 2008-07-01 | 2050-12-31 | 2008-07-01
75087 | FPIT | 307482001 | Customer Mobile App - Phase 2 | 127.69 |  | 127.69 |  |  | 21367.29 | 28166 | -6798.71 | 2018-12-28 09:17 | 2020-03-31 | 2019-01-01 | 2020-03-20
75087 | FPIT | 307482002 | Customer Mobile App - Phase 3 | 3036.26 |  | 3036.26 |  |  | 3036.26 | 26324 | -23287.74 | 2019-12-19 13:54 | 2021-09-30 | 2020-01-01
75087 | FPIT | 307482SW2 | Customer Mobile App - Phase 3 | 13533.33 |  | 13533.33 |  |  | 13533.33 | 30258 | -16724.67 | 2020-04-13 09:32 | 2021-09-30 | 2020-04-01
75087 | CUSTCONN | 315986A | Customer Connect - Core | 1357935.72 |  | 1357935.72 |  |  | 2928651.18 | 2325960.3 | 602690.88 | 2017-08-10 10:55 | 2022-12-05 | 2017-08-01
75087 | CUSTCONN | 315986C | Customer Connect- Release 2 | 4981.53 |  | 4981.53 |  |  | 306109.87 | 187946.4 | 118163.47 | 2017-08-10 14:30 | 2019-05-28 | 2017-08-01 | 2019-06-18
75087 | CUSTCONN | 315986D | Customer Connect- Release 3 | 399.64 |  | 399.64 |  |  | 193413.5 | 280416.54 | -87003.04 | 2017-08-10 15:35 | 2019-12-30 | 2017-08-01 | 2019-12-31
75087 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 84172.15 |  | 84172.15 |  |  | 243783.94 | 117210.08 | 126573.86 | 2017-08-11 10:44 | 2020-09-01 | 2017-08-01 | 2020-09-01
75087 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 0 |  | 0 |  |  | 166838.95 | 43856 | 122982.95 | 2017-09-05 18:46 | 2018-10-01 | 2017-09-01 | 2018-10-01
75087 | CUSTCONN | 315986HW4 | Customer Connect- Hardware Proj 2 | 0 |  | 0 |  |  | 133573.49 | 53607 | 79966.49 | 2018-08-31 12:34 | 2019-06-01 | 2018-08-01 | 2019-08-01
75087 | CUSTCONN | 315986HW5 | Customer Connect- Hardware Proj 3 | 12854.79 |  | 12854.79 |  |  | 76178.91 | 42700 | 33478.91 | 2019-09-03 14:48 | 2020-06-01 | 2019-09-01 | 2020-06-15
75087 | CUSTCONN | 315986HW6 | Customer Connect- Hardware Proj 4 | 58411.03 |  | 58411.03 |  |  | 58411.03 | 21350 | 37061.03 | 2020-03-12 11:33 | 2021-03-15 | 2020-03-01 | 2021-06-01
75087 | FPIT | 336593019 | New Call Ctr SIP Trunks | 60.93 |  | 60.93 |  |  | 15792.79 | 10444 | 5348.79 | 2018-03-14 16:47 | 2020-03-31 | 2018-03-01 | 2020-03-31
75086 | FPIT | 338802003 | EAM Platform Optimization | 484.76 |  | 484.76 |  |  | 40924.68 | 147321.02 | -106396.34 | 2018-04-25 14:30 | 2020-05-30 | 2018-06-01 | 2020-03-31
75086 | FPIT | 338802004 | Mobile Durable Team | 26076.87 |  | 26076.87 |  |  | 127363.93 | 52783 | 74580.93 | 2018-09-17 12:23 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802005 | Maximo Durable Team | 2415.54 |  | 2415.54 |  |  | 163191.11 | 33459 | 129732.11 | 2018-09-13 15:18 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802006 | Smallworld/myWorld Durable Team | -332.6 |  | -332.6 |  |  | 10.99 | 48911 | -48900.01 | 2018-09-06 13:43 | 2020-05-28 | 2018-10-01 | 2020-11-10
75086 | FPIT | 338802008 | EcoSys Durable Team Acciunting | -431.31 |  | -431.31 |  |  | 1196.89 | 52026 | -50829.11 | 2018-09-13 10:17 | 2020-03-30 | 2018-09-01 | 2020-03-30
75086 | FPIT | 338802HW3 | EAM Platform Optimization | 4.09 |  | 4.09 |  |  | 4.09 | 59872 | -59867.91 | 2018-04-25 14:36 | 2019-10-31 | 2020-07-01 | 2020-03-31
75087 | FPIT | 344598001 | Duke Customer IVR Replacement | 9285.23 |  | 9285.23 |  |  | 151374.22 | 197081 | -45706.78 | 2018-04-10 15:29 | 2020-01-28 | 2018-04-01 | 2020-01-30
75087 | FPIT | 348527007 | My Duke Replacement | 4708.09 |  | 4708.09 |  |  | 68806.85 | 51758 | 17048.85 | 2019-10-02 08:40 | 2020-03-31 | 2019-10-01 | 2020-02-15
75088 | CY1900015 | 349395006 | ITOT OT SIEM Phase 2 Workstream | 120149.71 |  | 120149.71 |  |  | 120149.71 | 1775 | 118374.71 | 2020-04-13 16:35 | 2022-09-28 | 2020-05-01
75086 | FPIT | 349472HW1 | Multi-instance of Service Suite | 5095.77 |  | 5095.77 |  |  | 5095.77 | 13125 | -8029.23 | 2020-03-06 11:31 | 2020-11-29 | 2020-03-01 | 2020-11-29
75086 | FPIT | 349472SW1 | Multi-instance of Service Suite | 17546.98 |  | 17546.98 |  |  | 17546.98 | 36419 | -18872.02 | 2020-03-06 09:55 | 2020-11-29 | 2020-03-01 | 2020-11-29
75087 | FPIT | 354154002 | Durable Team - DXT | 3252.22 |  | 3252.22 |  |  | 3252.22 | 20684 | -17431.78 | 2020-03-05 14:57 | 2020-09-28 | 2020-03-01 | 2020-09-30
75087 | FPIT | 354299001 | Outage Map Refresh | 1552.87 |  | 1552.87 |  |  | 20759.85 | 21192.7 | -432.85 | 2019-10-02 10:55 | 2020-04-30 | 2019-10-01 | 2020-04-30
75086 | FPIT | 359990001 | Field Test Equipment Calibration So | 438.56 |  | 438.56 |  |  | 67643.76 | 60858 | 6785.76 | 2019-02-26 15:25 | 2019-12-29 | 2019-03-01 | 2019-12-01
75086 | G7PUINMR | AGECHGLG | Kentucky Age Change Large Meter | 58360.99 |  | 58360.99 |  |  | 532088.78 | 350000 | 182088.78 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | Kentucky Age Change Small Meter | 315841.83 |  | 315841.83 |  |  | 5542617.6 | 14500000 | -8957382.4 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | FARCOSSW | ARCOS21 | ARCOS Renewal | 59326.81 |  | 59326.81 |  |  | 59326.81 | 59327 | -0.19 | 2020-12-17 10:40 | 2021-09-30 | 2020-12-01
75086 | G7LNUL57 | AW0832 | Line UL57 monolithic insulators | 1026789.49 |  | 1026789.49 |  |  | 1026789.49 | 564646 | 462143.49 | 2019-07-26 13:48 | 2020-12-25 | 2020-03-01 | 2020-12-03
75086 | G71373 | AW0856 | 1373 US 27 Bridge Attachment | -3553.73 |  | -3553.73 |  |  | 67520.89 | 91770 | -24249.11 | 2019-07-30 08:26 | 2020-02-25 | 2019-11-01 | 2020-03-30
75086 | G7HMISTAT | AW0938 | HMI Work Station Erlanger | 83932.99 |  | 83932.99 |  |  | 88911.33 | 64259 | 24652.33 | 2019-08-09 13:08 | 2021-03-02 | 2019-10-01
75086 | G7AM07CUT | AW1330 | AM07 Cutout Fidelity | 1298962.33 |  | 1298962.33 |  |  | 1607709.8 | 1236780 | 370929.8 | 2019-10-23 11:50 | 2019-12-30 | 2019-10-01 | 2020-02-02
75086 | G7ERLREC | AW1547 | Erlanger Rectifier Remote Monitor I | 56423.61 |  | 56423.61 |  |  | 56423.61 | 60320.29 | -3896.68 | 2019-12-11 14:42 | 2020-12-31 | 2020-02-01 | 2020-09-08
75086 | G7MRUPG | AW1568 | Station 338 MR Upgrade | 68188.66 |  | 68188.66 |  |  | 68188.66 | 190631 | -122442.34 | 2019-12-18 15:27 | 2022-03-30 | 2020-02-01
75086 | G7MRUPG | AW1569 | Station 286 Riley Road MR Upgrade | 45326.33 |  | 45326.33 |  |  | 45326.33 | 190631 | -145304.67 | 2019-12-18 15:32 | 2022-03-30 | 2020-02-01
75086 | G7TUL06 | AW1592 | Line UL06 - Pipeline Replacements | 570464.62 |  | 570464.62 |  |  | 570464.62 | 3390200 | -2819735.38 | 2020-01-05 02:41 | 2021-12-30 | 2020-02-01
75086 | G7ERLCP | AW1656 | Erlanger Mag Anodes | 485978.94 |  | 485978.94 |  |  | 485978.94 | 2442881.69 | -1956902.75 | 2020-01-21 15:36 | 2026-12-31 | 2020-04-01
75086 | G7INTDIG | AW2017 | Line UL06 Integrity Digs | 1388557.63 |  | 1388557.63 |  |  | 1388557.63 | 2024700 | -636142.37 | 2020-04-09 07:34 | 2021-01-30 | 2020-04-01 | 2021-01-05
75086 | G7INTDIG | AW2018 | Line UL47 Integrity Digs | 837382.06 |  | 837382.06 |  |  | 837382.06 | 748000 | 89382.06 | 2020-04-09 07:40 | 2021-01-30 | 2020-04-01 | 2020-10-09
75086 | G7TUL06 | AW2021 | Line UL06 - Pipeline Replacements L | 88255.28 |  | 88255.28 |  |  | 88255.28 | 115000 | -26744.72 | 2020-04-13 10:21 | 2021-12-31 | 2020-07-01
75086 | G7TAM00B | AW2146 | Line AM00b Retrofit Repl | 641732.44 |  | 641732.44 |  |  | 641732.44 | 6528636 | -5886903.56 | 2020-05-19 16:54 | 2022-10-15 | 2020-05-01
75086 | G7LUL02 | AW2880 | Line UL02 - MAOP Replacement | 21357.99 |  | 21357.99 |  |  | 21357.99 | 1717200 | -1695842.01 | 2020-10-07 12:58 | 2022-03-31 | 2020-10-01
75087 | FPIT | CC1900001 | Customer Analytics Engine | 15571.32 |  | 15571.32 |  |  | 15571.32 | 26306 | -10734.68 | 2020-01-27 08:12 | 2021-12-31 | 2020-02-01 | 2021-03-31
75086 | FPIT | CC2000001 | NGBU Communications Platform | 24951.31 |  | 24951.31 |  |  | 24951.31 | 1242489 | -1217537.69 | 2020-03-30 13:53 | 2022-03-31 | 2020-04-01
75087 | FPIT | CC2000003 | SiteCore JSS Front End Modernizatio | 13423.97 |  | 13423.97 |  |  | 13423.97 | 28721 | -15297.03 | 2020-06-25 21:36 | 2022-03-30 | 2020-08-01
75086 | G7PUINMR | CHGMTRLG | Change Large Meter Kentucky | -22.45 |  | -22.45 |  |  | 164959.22 | 725000 | -560040.78 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | Change Small Meter Kentucky | 228923.8 |  | 228923.8 |  |  | 2605848.9 | 1250000 | 1355848.9 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | Change Regulator/Relief Kentucky | 2003.33 |  | 2003.33 |  |  | 155432.97 | 800000 | -644567.03 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7SERVNEW | CMNEWP70 | New C-M Plastic 2 inch and Under KY | 419805.6 |  | 419805.6 |  |  | 7668402.08 | 1 | 7668401.08 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | 2" or less Steel new C-M | 1153.07 |  | 1153.07 |  |  | 282503.71 | 5000000 | -4717496.29 | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVMC | CMRP70 | Replace C-M Plastic 2 inch and Unde | 203768.63 |  | 203768.63 |  |  | 12435228.22 | 0 | 12435228.22 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | CMSP70 | ASRP Curb to Meter 3" or Less | 8101.25 |  | 8101.25 |  |  | 8879432.76 | 20388002 | -11508569.24 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75087 | FPIT | CS1900001 | Voice of the Customer Engagement Pl | 17478.27 |  | 17478.27 |  |  | 17478.27 | 13742 | 3736.27 | 2020-01-29 16:09 | 2022-03-31 | 2020-02-01
75088 | CY1900015 | CY190HW15 | IT-OT ANA Workstream HW | 91.94 |  | 91.94 |  |  | 91.94 | 75995 | -75903.06 | 2019-12-11 08:05 | 2022-09-28 | 2020-01-01
75086 | G7PUBIMP | D3299 | PP 978761/LLM | -263.05 |  | -263.05 |  |  | 90038.82 | 78725 | 11313.82 | 2008-04-15 | 2050-12-31 | 2008-04-01 | 2008-08-28
75086 | G7PUBIMP | D3414 | PP 967604/LAURA MATE | -590.29 |  | -590.29 |  |  | 133477.23 | 52008 | 81469.23 | 2008-05-01 | 2050-12-31 | 2008-07-01 | 2008-11-28
75086 | G7LGMR | D3747 | REG 112K-WATERWORKS/CWA | -5400.3 |  | -5400.3 |  |  | 32561.53 | 99488 | -66926.47 | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7PUBIMP | E0294 | Hilton Dr | -41.5 |  | -41.5 |  |  | 1157.44 | 6415 | -5257.56 | 2008-07-29 | 2009-12-31 | 2008-08-01 | 2009-04-15
75086 | G7MAINS | E0469 | Sta 795 Inlet Piping | -242.16 |  | -242.16 |  |  | 6363.05 | 6569 | -205.95 | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7LGMR | E0472 | Sta 795 Sandman Dr | -1140.29 |  | -1140.29 |  |  | 71391.09 | 71874 | -482.91 | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7LGMR | E4533 | Reg 111K - 5th & Craig | -856.3 |  | -856.3 |  |  | 94852.3 | 103681 | -8828.7 | 2009-02-24 | 2014-02-23 | 2009-03-01 | 2010-03-08
75086 | G7LGMR | E4592 | Reg 108K - Hwy & David | -3472.04 |  | -3472.04 |  |  | 55608.83 | 96097 | -40488.17 | 2009-02-27 | 2014-02-24 | 2009-04-01 | 2010-01-28
75086 | G7PUBIMP | E4594 | Rogers Rd Villa Hills | -245.2 |  | -245.2 |  |  | 119453.76 | 91099 | 28354.76 | 2009-02-27 | 2014-02-27 | 2009-04-01 | 2009-09-24
75086 | FENABLES | ENABLETDG | ENABLETDG - Clearing Project | 0.83 |  | 0.83 |  |  | 3.2628e-11 | 511967.66 | -511967.66 | 2015-05-12 15:22 | 2018-10-01 | 2015-05-01 | 2019-03-31
75086 | G7LGMR | F2907 | STA 804 Lookaway Drive | 9840.88 |  | 9840.88 |  |  | 68369.54 | 39821 | 28548.54 | 2009-12-09 | 2012-06-30 | 2009-12-01 | 2011-06-24
75086 | G7LGMR | G2537 | Rpl SCADA Radio Equip KY | -12437 |  | -12437 |  |  | 267110.52 | 120750 | 146360.52 | 2011-03-04 | 2014-07-31 | 2011-03-01 | 2013-03-15
75086 | G7REPL | G4517 | F/L 'UL07' McCullum Rd Slide | -1832.85 |  | -1832.85 |  |  | 95659.21 | 76220.15 | 19439.06 | 2011-08-17 | 2012-06-01 | 2011-09-01 | 2012-03-17
75086 | G7LGMR | G6976 | Concrete Stairwell Rpl | -833.56 |  | -833.56 |  |  | 13126.97 | 18897.6 | -5770.63 | 2012-03-07 | 2013-03-10 | 2012-07-01 | 2012-11-01
75086 | G7REPL | G8159 | Reg 115K - Inlet & Outlet Piping | -435.59 |  | -435.59 |  |  | 28810.93 | 39684.96 | -10874.03 | 2012-07-30 | 2013-06-30 | 2012-09-01 | 2013-03-05
75086 | G7PUBIMP | G8241 | Sunset Drive - Three Mile Rd Imp | -472.76 |  | -472.76 |  |  | 153385.1 | 175201.13 | -21816.03 | 2012-08-16 | 2016-01-31 | 2015-02-01 | 2016-02-05
75086 | G7FRAME | G9421 | Frame Relay Kentucky | -1000.51 |  | -1000.51 |  |  | 47574.92 | 190202.72 | -142627.8 | 2013-02-01 | 2014-06-30 | 2013-02-01 | 2014-12-01
75086 | FPIT | GCTA30060 | Consolidated SCADA App Analysis | 54017.81 |  | 54017.81 |  |  | 277625.14 | 149205 | 128420.14 | 2017-04-11 15:19 | 2020-06-30 | 2017-04-01 | 2020-06-30
75086 | FPIT | GCTA3006K | INTGO_PI SCADA Data Implementation | 991.52 |  | 991.52 |  |  | 89187 | 133026 | -43839 | 2019-11-15 07:17 | 2022-03-17 | 2019-11-01
75086 | FPIT | GCTA30073 | Project 2 Gas Supply System | 57553.73 |  | 57553.73 |  |  | 742883.59 | 853149 | -110265.41 | 2017-03-30 17:09 | 2021-03-31 | 2017-07-01 | 2021-03-31
75086 | FPIT | GCTA30114 | Sales Force Automation Conso Strate | 54387.33 |  | 54387.33 |  |  | 263901.12 | 0 | 263901.12 | 2017-06-21 11:37 | 2020-11-30 | 2017-10-01 | 2020-11-10
75086 | FPIT | GCTA30391 | INTGO_Gas Major Projects Mgmt | 59027.81 |  | 59027.81 |  |  | 83440.11 | 224469 | -141028.89 | 2018-12-18 14:49 | 2020-12-30 | 2019-01-01 | 2020-12-31
75086 | FPIT | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | -733.27 |  | -733.27 |  |  | 607213.62 | 513619 | 93594.62 | 2018-05-21 15:50 | 2019-12-29 | 2018-06-01 | 2019-12-01
75086 | FPIT | GCTA33039 | INTGO_Consolidated CAD Tools | 51.42 |  | 51.42 |  |  | 56439.63 | 120205 | -63765.37 | 2018-06-19 11:18 | 2020-09-24 | 2018-08-01 | 2020-03-31
75086 | FPIT | GCTA47001 | INTGO_Materials Traceability | 57723.94 |  | 57723.94 |  |  | 101557.81 | 120205 | -18647.19 | 2018-12-06 14:57 | 2022-03-31 | 2019-01-01 | 2020-05-31
75086 | FPIT | GCTA4700B | INTGO_Traceability Form FDC | 23695.56 |  | 23695.56 |  |  | 105920.1 | 215691 | -109770.9 | 2018-12-06 13:26 | 2021-03-31 | 2018-12-01 | 2021-03-14
75086 | GITKYCAP | GSMRTLKSV | Gas Smart - Leak Survey Line Patrol | -3861.59 |  | -3861.59 |  |  | 232168.39 | 136600 | 95568.39 | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01 | 2019-08-30
75086 | G7LGMR | H0264 | Reg 118K Inlet & Outlet Piping | -811.51 |  | -811.51 |  |  | 79428.53 | 48938.56 | 30489.97 | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0350 | STA 535K1 (UL33 to HP) Modification | -692.76 |  | -692.76 |  |  | 22604.47 | 19577.76 | 3026.71 | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7PUINEW | INSREGREL | Install or Remove Regulator/Relief | 118213.44 |  | 118213.44 |  |  | 1230642.48 | 800000 | 430642.48 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | FPIT | IT1900021 | GIS Alignment for PCS - Midwest | 120582.31 |  | 120582.31 |  |  | 237430.41 | 485841 | -248410.59 | 2019-08-01 11:16 | 2021-01-31 | 2019-09-01 | 2021-01-17
75086 | FPIT | IT1900065 | GDPM Phase 2 | 69068.69 |  | 69068.69 |  |  | 69068.69 | 87832 | -18763.31 | 2020-02-07 07:49 | 2021-03-31 | 2020-02-01 | 2021-03-31
75086 | FPIT | IT1900067 | ARM to Maximo Integration | 1053.21 |  | 1053.21 |  |  | 1053.21 | 0 | 1053.21 | 2020-10-12 17:08 | 2021-07-31 | 2020-10-01 | 2021-07-27
75086 | FPIT | IT1900069 | TRG - WAM Measurement Project | 27545.21 |  | 27545.21 |  |  | 27545.21 | 65041 | -37495.79 | 2020-02-21 15:10 | 2021-12-31 | 2020-03-01
75086 | FPIT | IT1900073 | EAM 2020 Mobile Durable Team | 73236.57 |  | 73236.57 |  |  | 73236.57 | 36572 | 36664.57 | 2020-01-20 08:44 | 2021-05-30 | 2020-01-01 | 2021-06-08
75086 | FPIT | IT1900074 | EAM 2020 Maximo Durable Team | 184717.28 |  | 184717.28 |  |  | 184717.28 | 229288 | -44570.72 | 2020-01-20 10:57 | 2021-05-30 | 2020-01-01 | 2021-06-08
75086 | G7MSCPRD | L4115 | Replace Control Valves at Constance | -1280.91 |  | -1280.91 |  |  | 31357.45 | 58753.25 | -27395.8 | 2014-05-13 | 2015-06-30 | 2014-06-01 | 2014-11-01
75086 | G7SERVNEW | LCMNEWP70 | Greater than 2" C-M Plastic | 528.97 |  | 528.97 |  |  | 234133.15 | 2500000 | -2265866.85 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVMC | LCMRP70 | Greater than 2" C-M REPL Plastic | 7137.67 |  | 7137.67 |  |  | 23375.83 | 2500000 | -2476624.17 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7ASRP | LCMSP70 | ASRP Greater than 2" C-M Install | 74283.42 |  | 74283.42 |  |  | -184758.65 | 10000000 | -10184758.65 | 2016-01-13 11:25 | 2019-12-31 | 2016-07-01
75086 | G7SERVNEW | LMCNEWP70 | Greater than 2" M-C Plastic | 158343.86 |  | 158343.86 |  |  | 447351.68 | 2500000 | -2052648.32 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | Greater than 2" M-C Steel | 57673.89 |  | 57673.89 |  |  | 102206.05 | 2500000 | -2397793.95 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | Greater than 2" M-C REPL Plastic | 55359.16 |  | 55359.16 |  |  | 255421.35 | 2500000 | -2244578.65 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | FPIT | LTHWOOPS | Lighthouse:WO Optimization Gas- SW | -3270.36 |  | -3270.36 |  |  | 28418.37 | 24900 | 3518.37 | 2019-03-12 15:21 | 2019-12-29 | 2019-03-01 | 2019-09-30
75086 | G7MSCPRD | M6102 | Replace Compress 6&7 oil lube sys | -3833.96 |  | -3833.96 |  |  | 48948.69 | 30641.11 | 18307.58 | 2014-06-11 | 2016-06-30 | 2014-09-01 | 2015-01-14
75086 | G7SERVNEW | MCNEWP70 | New M-C Plastic 2 inch and Under KY | 2451660.13 |  | 2451660.13 |  |  | 15176561.94 | 1 | 15176560.94 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | New M-C Steel 2 inch and Under KY | 31171.62 |  | 31171.62 |  |  | 235539.39 | 1 | 235538.39 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVMC | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 1095778.75 |  | 1095778.75 |  |  | 16842982.58 | 0 | 16842982.58 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | Replace M-C Steel 2 inch and Under | 5523.08 |  | 5523.08 |  |  | 530530.4 | 0 | 530530.4 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7ASRP | MCSP70 | ASRP Main to Curb 3" or less | 670516.98 |  | 670516.98 |  |  | 41392310.97 | 19954384 | 21437926.97 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | FMDT2020 | MDTGAS20 | Install Win 7 Panasonic Toughbooks | 160648.5 |  | 160648.5 |  |  | 464843.86 | 403995 | 60848.86 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01
75086 | FMDT2017 | MDTKE17 | CF53 Purchases for MDT Replac | 274.98 |  | 274.98 |  |  | 30922.55 | 33851 | -2928.45 | 2018-02-07 15:38 | 2020-06-01 | 2018-02-01 | 2020-05-01
75086 | G7MAINS | MEAPJT70 | Joint Trench plasitc main extension | 785143.34 |  | 785143.34 |  |  | 3750563.27 | 10000000 | -6249436.73 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | FENABLEH | MOBH | Enable Mobility Hardware | 0 |  | 0 |  |  | 97791.8 | 120161 | -22369.2 | 2015-03-30 16:05 | 2017-10-31 | 2015-07-01 | 2017-11-07
75086 | FENABLES | MOBS | Enable Mobility Software | -5.5 |  | -5.5 |  |  | 729169.83 | 649497 | 79672.83 | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | G7REPL | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | -19645.33 |  | -19645.33 |  |  | 22096.81 | 64213.24 | -42116.43 | 2018-12-12 18:01 | 2019-11-21 | 2018-12-01 | 2019-11-27
75086 | GMAINS | MX0225249 | Litton Ln. PRESSURE IMPROVEMENT PRO | 4041.26 |  | 4041.26 |  |  | 174150.89 | 133009.25 | 41141.64 | 2018-12-06 18:01 | 2019-03-10 | 2018-12-01 | 2019-04-10
75086 | G7MAINS | MX0270903 | FARM TAP PROJ. 3 MILE RD | 6486.4 |  | 6486.4 |  |  | 414221.23 | 365844.57 | 48376.66 | 2019-03-21 14:01 | 2019-10-19 | 2019-04-01
75086 | G7MAINS | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 3083.49 |  | 3083.49 |  |  | 277358.89 | 123394.12 | 153964.77 | 2019-01-14 10:01 | 2019-10-24 | 2019-05-01
75086 | G7LGMR | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | -248.31 |  | -248.31 |  |  | 10611.99 | 31485.84 | -20873.85 | 2018-11-19 14:01 | 2019-02-28 | 2019-04-01 | 2019-07-19
75086 | G7LGMR | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | -231.37 |  | -231.37 |  |  | 9541.17 | 26609.04 | -17067.87 | 2018-11-19 14:01 | 2019-02-28 | 2019-04-01 | 2019-07-11
75086 | G7MAINS | MX0579746 | JT-G-RIVERS POINTE ESTATES PHASE 1 | 25270.49 |  | 25270.49 |  |  | 25270.49 | 109259 | -83988.51 | 2020-03-09 14:01 | 2020-09-24 | 2020-11-01 | 2021-06-13
75086 | G7MAINS | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 58282.71 |  | 58282.71 |  |  | 372791.12 | 0 | 372791.12 | 2019-07-31 14:01 | 2019-10-25 | 2019-08-01
75086 | G7MAINS | MX0602140 | FARM TAP PROJ; ENZWEILER RD | 7227.47 |  | 7227.47 |  |  | 7227.47 | 83366.18 | -76138.71 | 2020-09-01 18:01 | 2021-10-17 | 2020-09-01
75086 | G7MAINS | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 231.99 |  | 231.99 |  |  | 16054.73 | 112220.53 | -96165.8 | 2019-07-16 10:02 | 2019-12-12 | 2019-07-01
75086 | G7LGMR | MX0671045 | REG 101 - COVERT RUN & TAYLOR | -2343.63 |  | -2343.63 |  |  | 167976.08 | 81442.56 | 86533.52 | 2018-12-06 10:01 | 2019-08-30 | 2019-03-01 | 2019-10-27
75086 | G7PUBIMP | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 98763.06 |  | 98763.06 |  |  | 1955109.13 | 1689689.28 | 265419.85 | 2018-04-26 10:01 | 2018-08-25 | 2018-05-01 | 2019-01-22
75086 | G7PUBIMP | MX0790794 | Arlington Rd. Roadway IMP | -43659.63 |  | -43659.63 |  |  | 353160.21 | 227712 | 125448.21 | 2018-01-23 20:20 | 2018-03-30 | 2018-03-01 | 2018-09-26
75086 | G7PUBIMP | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 86222.38 |  | 86222.38 |  |  | 572508.8 | 274447.64 | 298061.16 | 2018-07-19 18:03 | 2018-10-28 | 2018-07-01 | 2018-12-19
75086 | G7MAINS | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 940.49 |  | 940.49 |  |  | 74539.59 | 62900.69 | 11638.9 | 2019-02-07 10:02 | 2019-04-03 | 2019-03-01
75086 | G7REPL | MX1233047 | KY-9 FLOOD GATE-RPL | 190751.64 |  | 190751.64 |  |  | 195696.19 | 92509 | 103187.19 | 2019-10-23 18:01 | 2020-07-10 | 2019-10-01 | 2020-12-14
75086 | G7MAINS | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 3331.14 |  | 3331.14 |  |  | 41779.5 | 73554.85 | -31775.35 | 2019-07-24 10:01 | 2020-01-19 | 2019-08-01 | 2020-03-13
75086 | G7MAINS | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 2255.03 |  | 2255.03 |  |  | 35105.79 | 46479.42 | -11373.63 | 2019-06-26 14:01 | 2019-11-14 | 2019-07-01
75086 | G7MAINS | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 118172.94 |  | 118172.94 |  |  | 389063.87 | 346753.22 | 42310.65 | 2019-09-11 14:01 | 2020-03-29 | 2019-09-01 | 2020-05-15
75086 | G7MAINS | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 3685.09 |  | 3685.09 |  |  | 258522.85 | 147466.28 | 111056.57 | 2019-06-27 10:02 | 2019-12-26 | 2019-07-01
75086 | G7MAINS | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 253723.97 |  | 253723.97 |  |  | 510245.04 | 515675 | -5429.96 | 2019-10-25 18:01 | 2020-05-28 | 2019-10-01 | 2020-07-20
75086 | G7PUBIMP | MX1376296 | Longbranch Rd. | 256216.47 |  | 256216.47 |  |  | 370025.75 | 70969.1 | 299056.65 | 2019-08-02 14:01 | 2020-03-05 | 2019-09-01 | 2020-09-15
75086 | G7PRESIM | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | -27117.24 |  | -27117.24 |  |  | 861604.74 | 760041.64 | 101563.1 | 2019-06-04 14:01 | 2020-02-26 | 2019-06-01 | 2020-01-15
75086 | G7MAINS | MX1957438 | FARM TAP PROJ; GRANDVIEW RD | 51623.05 |  | 51623.05 |  |  | 51623.05 | 0 | 51623.05 | 2020-09-29 10:01 | 2021-07-23 | 2020-09-01
75086 | G7MAINS | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 581074.43 |  | 581074.43 |  |  | 581074.43 | 541626 | 39448.43 | 2020-02-05 10:02 | 2020-05-22 | 2020-02-01
75086 | G7IMPRPL | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | -14794.79 |  | -14794.79 |  |  | 797515.02 | 436474.83 | 361040.19 | 2017-09-11 18:02 | 2019-07-31 | 2017-10-01 | 2019-09-10
75086 | G7MAINS | MX2142600 | FARM TAP PROJ; THORNTON RD | 2386.94 |  | 2386.94 |  |  | 28086.4 | 54541.9 | -26455.5 | 2019-07-18 18:01 | 2019-12-19 | 2019-07-01
75086 | G7MAINS | MX2143073 | FARM TAP PROJ; REIDLIN RD | 413.07 |  | 413.07 |  |  | 37156.37 | 43437.77 | -6281.4 | 2019-05-21 18:01 | 2019-10-31 | 2019-06-01
75086 | G7MREG118 | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 13060.87 |  | 13060.87 |  |  | 25442.42 | 87907.04 | -62464.62 | 2017-09-22 14:01 | 2022-03-31 | 2017-10-01
75086 | G7LGMR | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 322616.22 |  | 322616.22 |  |  | 548542.99 | 411228.18 | 137314.81 | 2017-09-21 14:01 | 2020-07-10 | 2017-10-01 | 2020-09-15
75086 | G7MAINS | MX2271880 | MEA ~800 FT; 494 JONES RD | 28147.5 |  | 28147.5 |  |  | 242750.13 | 163070 | 79680.13 | 2019-07-30 10:01 | 2020-02-27 | 2019-08-01
75086 | G7LGMR | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 538294.42 |  | 538294.42 |  |  | 13791597.12 | 12669920 | 1121677.12 | 2017-10-06 18:03 | 2019-08-15 | 2017-11-01 | 2019-09-19
75086 | G7PUBIMP | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | -3520.67 |  | -3520.67 |  |  | 137160.56 | 129952.9 | 7207.66 | 2018-05-14 14:02 | 2018-08-26 | 2018-05-01 | 2018-10-24
75086 | G7LGMR | MX2386654 | STA 901 - MARY GRUBBS | -7701.92 |  | -7701.92 |  |  | 310586.15 | 357835.2 | -47249.05 | 2019-06-24 10:02 | 2019-10-31 | 2019-06-01 | 2020-02-19
75086 | G7MAINS | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 408.23 |  | 408.23 |  |  | 32354.07 | 50615.9 | -18261.83 | 2019-07-02 14:01 | 2019-12-12 | 2019-07-01
75086 | G7PUBIMP | MX2541899 | KY-36/I-75 Interchange Reconstruct | -1294.77 |  | -1294.77 |  |  | 1122765.41 | 906757 | 216008.41 | 2018-03-02 10:01 | 2018-06-03 | 2018-04-01 | 2018-11-02
75086 | G7MAINS | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 106383.51 |  | 106383.51 |  |  | 192207.23 | 205184 | -12976.77 | 2019-10-04 14:01 | 2020-03-11 | 2019-11-01 | 2020-05-15
75086 | G7MAINS | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 100717.75 |  | 100717.75 |  |  | 147091.51 | 60768.22 | 86323.29 | 2019-08-27 18:01 | 2020-03-18 | 2019-09-01 | 2020-06-08
75086 | G7PUBIMP | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 50130.67 |  | 50130.67 |  |  | 25728.63 | 101493.8 | -75765.17 | 2019-10-01 18:01 | 2020-02-27 | 2019-10-01 | 2020-04-09
75086 | G7MAINS | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 47208.91 |  | 47208.91 |  |  | 52023.27 | 60345 | -8321.73 | 2019-11-19 10:01 | 2020-04-23 | 2019-12-01 | 2020-05-31
75086 | G7PUBIMP | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 288357.99 |  | 288357.99 |  |  | 309410.39 | 99383.99 | 210026.4 | 2019-09-20 14:01 | 2020-04-03 | 2019-12-01 | 2020-07-09
75086 | G7MAINS | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 606.98 |  | 606.98 |  |  | 55530.87 | 77219 | -21688.13 | 2019-09-30 15:56 | 2020-01-19 | 2019-10-01 | 2020-03-11
75086 | G7MAINS | MX2848811 | INDEPENDENCE RD MEA - | 240.74 |  | 240.74 |  |  | 5551.81 | 35185 | -29633.19 | 2019-09-30 10:01 | 2020-01-30 | 2019-10-01
75086 | G7MAINS | MX2866813 | JT-G-ARCADIA PHASE I | 9202.26 |  | 9202.26 |  |  | 9202.26 | 57563 | -48360.74 | 2019-12-18 10:01 | 2020-03-31 | 2020-03-01 | 2020-08-19
75086 | G7PUBIMP | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 6587.83 |  | 6587.83 |  |  | 28839.77 | 51296.38 | -22456.61 | 2019-08-02 14:01 | 2020-01-09 | 2019-09-01 | 2020-09-15
75086 | G7PUBIMP | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 57215.91 |  | 57215.91 |  |  | 57215.91 | 94800 | -37584.09 | 2020-07-28 10:01 | 2020-10-16 | 2020-07-01 | 2021-01-11
75086 | G7MAINS | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | -525.3 |  | -525.3 |  |  | 35815.95 | 51274.67 | -15458.72 | 2019-08-28 14:01 | 2020-01-05 | 2019-09-01 | 2020-03-26
75086 | G7MAINS | MX3444104 | MEA ~970 FT; ASHLEY DR | -1154.99 |  | -1154.99 |  |  | 49044.52 | 93363 | -44318.48 | 2019-09-13 14:01 | 2019-12-29 | 2019-09-01 | 2020-02-25
75086 | G7MAINS | MX3745351 | MEA ~200 FT; LEE LN | 316.45 |  | 316.45 |  |  | 14418.31 | 34346 | -19927.69 | 2019-10-18 10:01 | 2020-02-02 | 2019-10-01 | 2020-04-02
75086 | G7MAINS | MX4018013 | JOHNS HILL RD MEA | 192865.35 |  | 192865.35 |  |  | 209963.8 | 73344 | 136619.8 | 2019-11-13 10:01 | 2020-01-03 | 2019-11-01 | 2020-06-18
75086 | G7REPL | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 7014.04 |  | 7014.04 |  |  | 39763.12 | 72427 | -32663.88 | 2019-10-11 10:01 | 2020-03-19 | 2019-10-01 | 2020-04-15
75086 | G7MAINS | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 89837.87 |  | 89837.87 |  |  | 94079.99 | 95523.06 | -1443.07 | 2019-12-02 14:01 | 2020-04-22 | 2019-12-01 | 2020-08-16
75086 | G7MAINS | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 16717.98 |  | 16717.98 |  |  | 18581.39 | 41217 | -22635.61 | 2019-12-02 18:01 | 2021-04-02 | 2019-12-01 | 2020-06-18
75086 | G7MAINS | MX4125743 | 2,000 FT MEA; DAMASCUS | 142604.75 |  | 142604.75 |  |  | 142604.75 | 152669 | -10064.25 | 2020-01-29 14:01 | 2020-06-10 | 2020-02-01 | 2020-12-16
75086 | G7MAINS | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 1101.17 |  | 1101.17 |  |  | 3285.37 | 13325 | -10039.63 | 2019-10-01 14:01 | 2020-02-13 | 2019-11-01
75086 | G7MAINS | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 37525.79 |  | 37525.79 |  |  | 37525.79 | 52790 | -15264.21 | 2019-12-19 10:01 | 2020-12-31 | 2020-01-01
75086 | G7MAINS | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 6861.87 |  | 6861.87 |  |  | 6861.87 | 51469 | -44607.13 | 2019-11-19 10:01 | 2021-01-11 | 2020-02-01 | 2020-08-02
75086 | G7REPL | MX4342633 | Pleasant Valley Steel Rep (Founders | 359638.27 |  | 359638.27 |  |  | 386486.63 | 166756 | 219730.63 | 2019-10-18 10:01 | 2020-02-28 | 2019-10-01 | 2020-06-26
75086 | G7MAINS | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 251265.94 |  | 251265.94 |  |  | 251265.94 | 225972 | 25293.94 | 2020-05-27 10:01 | 2020-08-25 | 2020-06-01 | 2020-11-30
75086 | G7MAINS | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 67067.76 |  | 67067.76 |  |  | 67067.76 | 116703 | -49635.24 | 2020-02-17 14:01 | 2020-04-24 | 2020-02-01 | 2020-08-12
75086 | G7MAINS | MX4837396 | JT-G-PARK POINTE | 298.02 |  | 298.02 |  |  | 298.02 | 81024 | -80725.98 | 2020-02-24 14:07 | 2021-02-24 | 2020-03-01 | 2021-07-14
75086 | G7MAINS | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 159154.32 |  | 159154.32 |  |  | 159154.32 | 166549 | -7394.68 | 2020-06-12 14:01 | 2020-12-17 | 2020-06-01 | 2021-01-12
75086 | G7MAINS | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 943847.01 |  | 943847.01 |  |  | 943847.01 | 1255100 | -311252.99 | 2020-03-03 10:01 | 2020-09-11 | 2020-03-01 | 2020-12-26
75086 | G7MAINS | MX5040349 | GLENRIDGE DRIVE - MEA | 100239.48 |  | 100239.48 |  |  | 100239.48 | 114071 | -13831.52 | 2020-04-23 14:01 | 2020-07-10 | 2020-05-01 | 2020-11-24
75086 | G7MAINS | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 57401.87 |  | 57401.87 |  |  | 57401.87 | 44298 | 13103.87 | 2020-04-03 11:02 | 2020-10-21 | 2020-06-01 | 2020-11-27
75086 | G7ASDD | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 56387.87 |  | 56387.87 |  |  | 56387.87 | 307485 | -251097.13 | 2020-04-16 18:01 | 2020-10-11 | 2020-05-01 | 2021-04-04
75086 | G7WFD | MX5518434 | WENDELL FORD DIST. PROJ; | 48672.71 |  | 48672.71 |  |  | 48672.71 | 262528 | -213855.29 | 2020-04-16 18:01 | 2020-10-02 | 2020-05-01 | 2021-02-11
75086 | G7MAINS | MX5652554 | FARM TAP PROJ; MASON RD MEA | 5001.25 |  | 5001.25 |  |  | 5001.25 | 0 | 5001.25 | 2020-12-16 10:17 | 2021-03-19 | 2020-12-01
75086 | G7MAINS | MX5653109 | FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 778.47 |  | 778.47 |  |  | 778.47 | 194197.42 | -193418.95 | 2020-09-29 10:01 | 2021-05-14 | 2020-10-01
75086 | G7MAINS | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 104235.64 |  | 104235.64 |  |  | 104235.64 | 74687 | 29548.64 | 2020-07-29 14:01 | 2020-10-16 | 2020-08-01 | 2021-01-25
75086 | G7MAINS | MX6243694 | ~400 FT MEA; DOLWICK DR | 59485.09 |  | 59485.09 |  |  | 59485.09 | 104176 | -44690.91 | 2020-06-18 10:01 | 2020-09-29 | 2020-07-01 | 2021-04-07
75086 | G7MAINS | MX6245365 | ~425 FT MEA; SARAH LN | 10580.55 |  | 10580.55 |  |  | 10580.55 | 26839.9 | -16259.35 | 2020-08-31 14:01 | 2020-11-15 | 2020-09-01 | 2021-02-10
75086 | G7PUBIMP | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 179928.25 |  | 179928.25 |  |  | 179928.25 | 99251 | 80677.25 | 2020-04-29 14:01 | 2020-06-26 | 2020-05-01 | 2021-01-11
75086 | G7PUBIMP | MX6628393 | Pleasant Valley 2020 Relocation | 458429.77 |  | 458429.77 |  |  | 458429.77 | 399033 | 59396.77 | 2020-05-18 10:01 | 2020-10-29 | 2020-06-01 | 2020-11-17
75086 | G7MAINS | MX6684040 | ~1825 FTMEA; WRIGHT BLVD | 49898.59 |  | 49898.59 |  |  | 49898.59 | 117730.07 | -67831.48 | 2020-10-02 10:01 | 2020-12-18 | 2020-10-01 | 2021-03-08
75086 | G7LGMR | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 21618.78 |  | 21618.78 |  |  | 59230.82 | 106314.24 | -47083.42 | 2017-12-15 14:01 | 2021-03-31 | 2018-02-01
75086 | G7PUBIMP | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | -26325.58 |  | -26325.58 |  |  | 162909.26 | 279194 | -116284.74 | 2018-03-02 10:01 | 2018-05-25 | 2018-03-01 | 2018-10-25
75086 | G7STA876 | MX6800938 | STA 876 WARSAW TOWN BORDER- Station | 44447.29 |  | 44447.29 |  |  | 83601.88 | 252984 | -169382.12 | 2018-01-10 18:02 | 2021-09-06 | 2018-01-01
75086 | G7LGMR | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 572.64 |  | 572.64 |  |  | 29054.18 | 139842.24 | -110788.06 | 2018-04-04 10:01 | 2021-03-31 | 2019-01-01
75086 | G7MAINS | MX6835553 | JT-G-SOUTHWICK PHASE B PART 1 | 57.88 |  | 57.88 |  |  | 57.88 | 46988.86 | -46930.98 | 2020-11-23 18:02 | 2021-08-19 | 2020-12-01 | 2021-07-25
75086 | G7MAINS | MX6842755 | MAIN EXTENSION AARON DR-85 FT 2 IN- | 5099.04 |  | 5099.04 |  |  | 5099.04 | 25737 | -20637.96 | 2020-07-09 10:01 | 2020-08-28 | 2020-08-01 | 2020-12-15
75086 | G7MAINS | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 275739.24 |  | 275739.24 |  |  | 275739.24 | 319190 | -43450.76 | 2020-05-22 14:01 | 2021-03-31 | 2020-05-01 | 2021-04-05
75086 | G7PUBIMP | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 98905.75 |  | 98905.75 |  |  | 98905.75 | 74108 | 24797.75 | 2020-07-08 18:01 | 2020-11-26 | 2020-07-01 | 2020-12-07
75086 | G7MAINS | MX7122512 | 100 FT MEA; 10009 INDIAN HILL DR | 26071.71 |  | 26071.71 |  |  | 26071.71 | 21629.68 | 4442.03 | 2020-09-22 10:01 | 2020-11-27 | 2020-10-01 | 2021-03-12
75086 | G7MAINS | MX7231229 | Stonewater Approach Main | 4611.95 |  | 4611.95 |  |  | 4611.95 | 201665.76 | -197053.81 | 2020-12-15 10:01 | 2021-03-23 | 2020-12-01
75086 | G7REG0057 | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 2667.59 |  | 2667.59 |  |  | 2667.59 | 44953.52 | -42285.93 | 2020-07-07 10:01 | 2021-03-31 | 2020-07-01
75086 | G7REG0026 | MX7281967 | REG 0026 Uphil and Highway - Reg Sw | 8805.99 |  | 8805.99 |  |  | 8805.99 | 48953.52 | -40147.53 | 2020-07-07 10:01 | 2021-03-31 | 2020-08-01
75086 | G7REG0048 | MX7282035 | REG 0048 Fifth and Philadelphia - R | 12794.79 |  | 12794.79 |  |  | 12794.79 | 48953.52 | -36158.73 | 2020-07-14 10:02 | 2021-03-31 | 2020-08-01
75086 | G7MAINS | MX7488442 | SANCTUARY VILLAGE PHASE 1 PART 3 | 116.24 |  | 116.24 |  |  | 116.24 | 44181.42 | -44065.18 | 2020-09-23 10:01 | 2020-12-18 | 2020-10-01
75086 | G7PUBIMP | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 6382.24 |  | 6382.24 |  |  | 238643.31 | 238847.13 | -203.82 | 2018-04-06 18:03 | 2018-08-24 | 2018-04-01 | 2018-10-26
75086 | G7PUBIMP | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 117038.47 |  | 117038.47 |  |  | 166667.57 | 99125.15 | 67542.42 | 2019-08-02 10:01 | 2020-02-27 | 2019-08-01 | 2020-02-29
75086 | G7PUBIMP | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 5288.84 |  | 5288.84 |  |  | 190727.42 | 183481.42 | 7246 | 2019-04-03 14:01 | 2019-07-14 | 2019-04-01 | 2019-10-03
75086 | G7MAINS | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 394.69 |  | 394.69 |  |  | 5054.88 | 3766.66 | 1288.22 | 2018-08-27 14:02 | 2018-11-20 | 2018-08-01 | 2018-12-26
75086 | G7237BEAV | MX7783733 | BEAVER RD INSTALL REPLACEMENT PROJE | 15890.83 |  | 15890.83 |  |  | 15890.83 | 48085 | -32194.17 | 2020-08-17 10:01 | 2020-10-30 | 2020-08-01
75086 | G7MAINS | MX8030455 | Camp Ernst and Solomon MAE | 32948.67 |  | 32948.67 |  |  | 32948.67 | 42778.64 | -9829.97 | 2020-10-19 18:01 | 2021-04-12 | 2020-11-01 | 2021-04-26
75086 | G7MAINS | MX8059955 | ~440 FT MEA; 2 IN PL HP | 2480.81 |  | 2480.81 |  |  | 2480.81 | 29426.19 | -26945.38 | 2020-12-01 14:18 | 2021-02-28 | 2020-12-01
75086 | G7MAINS | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 13339.15 |  | 13339.15 |  |  | 20163.17 | 57033 | -36869.83 | 2018-09-28 14:02 | 2019-01-25 | 2019-11-01 | 2020-07-06
75086 | G7MAINS | MX8451945 | INVESTMENT WAY MEA | 26815.39 |  | 26815.39 |  |  | 26815.39 | 16224.75 | 10590.64 | 2020-10-16 10:01 | 2020-12-30 | 2020-11-01 | 2021-02-02
75086 | G7MAINS | MX8505395 | ~350 FT MEA; 351 KENTON LANDS | 453.3 |  | 453.3 |  |  | 453.3 | 32683.85 | -32230.55 | 2020-12-01 14:18 | 2021-02-28 | 2020-12-01 | 2021-06-28
75086 | G7MAINS | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 1281.1 |  | 1281.1 |  |  | 101534.59 | 80515.92 | 21018.67 | 2018-08-22 14:02 | 2018-10-19 | 2018-08-01
75086 | G7LGMR | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 133.69 |  | 133.69 |  |  | 40673.75 | 262006.08 | -221332.33 | 2019-03-21 14:01 | 2020-08-31 | 2019-05-01
75086 | G7PUBIMP | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 214.95 |  | 214.95 |  |  | 369060.43 | 208010.18 | 161050.25 | 2018-06-14 14:01 | 2018-10-12 | 2018-06-01 | 2019-02-03
75086 | G7REPL | MX9056339 | St. Matthews Circle Replacement | -12893.84 |  | -12893.84 |  |  | 81156.17 | 107808.25 | -26652.08 | 2018-09-25 14:02 | 2019-02-03 | 2018-10-01 | 2019-08-20
75086 | G7PUBIMP | MX9244894 | MT.ZION RD KY536 STI | 244141.81 |  | 244141.81 |  |  | 244141.81 | 1026778 | -782636.19 | 2019-11-08 10:01 | 2021-03-31 | 2020-01-01 | 2021-07-27
75086 | G7REPL | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 265087.55 |  | 265087.55 |  |  | 265087.55 | 1413710 | -1148622.45 | 2019-11-12 10:01 | 2021-01-28 | 2020-01-01
75086 | G7MAINS | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 143321.64 |  | 143321.64 |  |  | 143321.64 | 131212 | 12109.64 | 2019-12-12 18:01 | 2020-06-11 | 2020-01-01 | 2020-08-05
75086 | G7PUBIMP | O4165 | Dudley Rd Improvement | -336 |  | -336 |  |  | 106898.72 | 145627.17 | -38728.45 | 2014-07-23 | 2015-03-01 | 2014-08-01 | 2014-11-01
75086 | G7PUBIMP | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | -2442.37 |  | -2442.37 |  |  | 247251.61 | 60740.54 | 186511.07 | 2014-08-22 | 2015-06-28 | 2014-12-01 | 2015-08-05
75086 | G7REPL | P6335 | Dudley Rd - Relocation For Rstorm | -5228.42 |  | -5228.42 |  |  | 92992.87 | 74701.31 | 18291.56 | 2014-09-19 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7PUBIMP | P6497 | Hayes Station Rd | -320.09 |  | -320.09 |  |  | 10640.75 | 15956.89 | -5316.14 | 2014-10-03 | 2015-04-10 | 2014-10-01 | 2014-12-05
75086 | G7PUBIMP | P6551 | Dudley Rd - Relocation for Storm | -4891.56 |  | -4891.56 |  |  | 70848.38 | 60831.98 | 10016.4 | 2014-10-09 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7PUBIMP | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | -8797.74 |  | -8797.74 |  |  | 68022.04 | 27834.34 | 40187.7 | 2015-01-14 | 2015-09-25 | 2015-02-01 | 2015-06-20
75086 | G7MSCPRD | P8054 | Replace BTU measurement at Erlanger | -1260.77 |  | -1260.77 |  |  | 52326.6 | 49804.32 | 2522.28 | 2015-03-12 14:27 | 2016-04-30 | 2015-07-01 | 2016-01-30
75087 | FPIT | PCTA210C | Contact Channels Datamart & Dashboa | 0 |  | 0 |  |  | 5369.19 | 5162.5 | 206.69 | 2013-10-22 | 2014-09-23 | 2013-11-01 | 2014-09-23
75086 | PCTAITMWM | PCTAIT85B | INT85B CTA MWMS Consolidation | 22.33 |  | 22.33 |  |  | 1730253.21 | 285463 | 1444790.21 | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | G7IMPRPL | R0978 | AM07 Pressure Test WP18 | -1848.08 |  | -1848.08 |  |  | 2871251.41 | 105161.63 | 2766089.78 | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7IMPRPL | R0981 | WP23 "AM07" Pressure Test | 139.83 |  | 139.83 |  |  | 841317.78 | 98206.56 | 743111.22 | 2015-07-06 16:45 | 2017-02-28 | 2016-02-01 | 2016-10-20
75086 | G7LGMR | R2900 | Cox Rd Station Rpl | -827.74 |  | -827.74 |  |  | 29570.94 | 171480.48 | -141909.54 | 2015-09-10 16:08 | 2017-08-01 | 2016-02-01 | 2017-04-11
75086 | G7REPL | R3316 | Glencoe - Webster/Railroad St | -385.25 |  | -385.25 |  |  | 8697.13 | 13545.31 | -4848.18 | 2015-09-28 09:36 | 2016-04-09 | 2015-10-01 | 2015-12-31
75086 | G7LGMR | R3460 | Station 577 (Ky-17 & US-27) | -15060.2 |  | -15060.2 |  |  | 222104.95 | 79638.14 | 142466.81 | 2015-10-05 14:36 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3461 | Station 577 Inlet Piping | -437.01 |  | -437.01 |  |  | 6391.91 | 43879.01 | -37487.1 | 2015-10-05 15:02 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3462 | Station 577 Outlet Piping | -468.57 |  | -468.57 |  |  | 2770.74 | 17739.36 | -14968.62 | 2015-10-05 15:10 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R4609 | RP 8866200 Ripple Creek | -3216 |  | -3216 |  |  | 71711.28 | 51984.25 | 19727.03 | 2015-11-19 12:28 | 2016-06-18 | 2015-12-01 | 2016-05-20
75086 | G7IMPRPL | R4858 | AM-09 Segment 3700 Main Rpl | 3691.66 |  | 3691.66 |  |  | 1573982.22 | 367588.8 | 1206393.42 | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | G7PUBIMP | R6768 | STI 9359472 Robbins Ave | -1029.42 |  | -1029.42 |  |  | 30408.52 | 20414.42 | 9994.1 | 2016-02-11 14:00 | 2016-09-30 | 2016-03-01 | 2016-07-15
75086 | G7PUBIMP | S4545 | STI 10221124 Altavia Ave | -121.56 |  | -121.56 |  |  | 43121.71 | 15146.09 | 27975.62 | 2016-05-10 07:49 | 2016-10-31 | 2016-05-01 | 2016-09-14
75086 | G7LGMR | S7568 | STA 822 Cox Rd Outlet | -422.66 |  | -422.66 |  |  | 29415.69 | 25054.56 | 4361.13 | 2016-06-08 12:42 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | S7572 | STA 822 Cox Rd Inlet | -960.33 |  | -960.33 |  |  | 66834.97 | 25054.56 | 41780.41 | 2016-06-08 12:51 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7PUBIMP | S7874 | STI 4844778 Thomas More Pkwy | -611.47 |  | -611.47 |  |  | 69933.58 | 11696.61 | 58236.97 | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7PUBIMP | S8867 | STI 10873483 Mt Zion Rd | -43839.97 |  | -43839.97 |  |  | 1232439.02 | 447690.24 | 784748.78 | 2016-07-26 13:07 | 2020-01-30 | 2017-01-01 | 2019-12-21
75086 | G7PUINEW | SETMETER | Set or Remove Meter | 1306156.64 |  | 1306156.64 |  |  | 7701279.68 | 2250000 | 5451279.68 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | SG001040F | SG1040SW | DEE SGG License Extension | 5410.35 |  | 5410.35 |  |  | 5410.35 | 0 | 5410.35 | 2020-04-16 17:27 | 2020-05-31 | 2020-04-01 | 2020-07-21
75086 | SG001042F | SG1042SW | DEE Openway License Extension | 12021.54 |  | 12021.54 |  |  | 12021.54 | 11784 | 237.54 | 2020-07-28 22:06 | 2020-10-30 | 2020-09-01 | 2020-12-31
75086 | SGKAMIF | SG169MTRS | SG KY AMI Gas Meters - 169 | 1416.17 |  | 1416.17 |  |  | 9375353.98 | 9563026 | -187672.02 | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75086 | SG000358F | SG358HW16 | SG 358 - DEE MDM Scale Hardware 16 | 0 |  | 0 |  |  | 72533.24 | 225545 | -153011.76 | 2016-06-22 12:04 | 2017-06-30 | 2016-06-01 | 2017-06-26
75086 | SG000358F | SG358HW19 | SG DEE MDM Scale HWre Phase 4 - 358 | -8.88 |  | -8.88 |  |  | 40182.05 | 21102.66 | 19079.39 | 2018-05-09 10:59 | 2019-08-18 | 2018-05-01 | 2019-09-24
75086 | SG000358F | SG358SVR | DEE MDM Scale | 998.71 |  | 998.71 |  |  | 1791.14 | 1048 | 743.14 | 2019-09-24 08:02 | 2020-01-31 | 2019-11-01 | 2020-03-31
75086 | SG000358F | SG358SVR2 | DEE MDM Scale | 1309.93 |  | 1309.93 |  |  | 1309.93 | 1378 | -68.07 | 2020-04-16 07:19 | 2020-08-31 | 2020-04-01 | 2020-07-31
75086 | SG000358F | SG358SW1 | SG DEE MDM Scale Software 1 | 0 |  | 0 |  |  | 16330.53 | 2935 | 13395.53 | 2016-11-01 13:58 | 2018-02-28 | 2016-11-01 | 2018-02-12
75086 | SG000489F | SG489SVR2 | DEE Openway Scale | 198.82 |  | 198.82 |  |  | 10946.3 | 15568 | -4621.7 | 2019-01-22 21:54 | 2020-03-31 | 2019-01-01 | 2019-09-30
75086 | SG000489F | SG489SVR3 | DEE Openway Scale | 3508.69 |  | 3508.69 |  |  | 3515.91 | 1190 | 2325.91 | 2019-09-25 08:08 | 2020-10-31 | 2019-09-01 | 2020-10-26
75086 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 0.06 |  | 0.06 |  |  | 29590.47 | 31329.67 | -1739.2 | 2017-04-24 18:13 | 2018-12-31 | 2017-05-01 | 2019-03-31
75086 | SG000489F | SG489SW2 | DEE Openway Scale | 4525.02 |  | 4525.02 |  |  | 4525.02 | 2008 | 2517.02 | 2020-02-03 09:12 | 2020-10-31 | 2020-01-01 | 2020-10-26
75086 | SG000540F | SG540HW | DEE Vehicle Area Network | 7311.18 |  | 7311.18 |  |  | 64897.86 | 117926 | -53028.14 | 2018-04-13 13:13 | 2020-12-17 | 2018-09-01
75086 | SG000540F | SG540SW | DEE Vehicle Area Network | 0.02 |  | 0.02 |  |  | 0.04 | 107801 | -107800.96 | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01 | 2018-07-16
75086 | SG000723F | SG723SW | DEE AMI Operations Tool | 12707.36 |  | 12707.36 |  |  | 12707.36 | 26599 | -13891.64 | 2020-03-03 09:59 | 2022-01-13 | 2020-03-01
75086 | SG000724F | SG724SW | DEE MDM Technical Health | 8509.02 |  | 8509.02 |  |  | 8509.02 | 15916 | -7406.98 | 2020-08-19 16:46 | 2021-06-24 | 2020-08-01
75086 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | -512.91 |  | -512.91 |  |  | 77935.76 | 76873.76 | 1062 | 2018-07-12 09:17 | 2021-03-31 | 2018-07-01
75086 | SG000940F | SG940SVR | DEE EDMS Platform Upgrade | 11756.78 |  | 11756.78 |  |  | 11756.78 | 9477 | 2279.78 | 2020-04-24 15:54 | 2020-12-18 | 2020-05-01 | 2021-02-07
75086 | SGEOSEF | SGEOSE | DEE Openway Security Enhancements | 0 |  | 0 |  |  | 6381.08 | 4498 | 1883.08 | 2015-06-10 18:16 | 2016-08-21 | 2015-06-01 | 2016-06-04
75086 | SGKYPMO | SGSGC | Smart Grid to SG Capital - PMO | 0 |  | 0 |  |  | 2.934e-11 | 1 | -1 | 2010-09-30 | 2017-12-31 | 2010-09-01 | 2018-03-04
75086 | G7REPL | T1130 | RPL 11859007 Ballyshannon - relocat | 337.54 |  | 337.54 |  |  | 593.15 | 37387.77 | -36794.62 | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | G73MILES | T1437 | STA 249: Three Mile Rd | 11898463.9 |  | 11898463.9 |  |  | 25443361.81 | 15406228 | 10037133.81 | 2017-01-05 11:19 | 2020-08-28 | 2017-01-01 | 2020-09-15
75086 | G73MILES | T1437LAND | 3 Mile Station (LAND) | 17706.6 |  | 17706.6 |  |  | 20326.12 | 40000 | -19673.88 | 2018-06-22 15:02 | 2020-07-28 | 2018-09-01 | 2020-09-15
75086 | G7LGMR | T1465 | STA 855 Taylor Mill Rd - Station | -2295.9 |  | -2295.9 |  |  | 202527.23 | 83246.98 | 119280.25 | 2017-01-06 16:24 | 2018-04-19 | 2017-03-01 | 2018-04-24
75086 | G73MILES | T4422 | AM07 Barleycorns | -3189.46 |  | -3189.46 |  |  | 218355.9 | 190195.2 | 28160.7 | 2017-03-22 16:39 | 2020-07-28 | 2017-04-01 | 2019-12-01
75086 | G7LGMR | T5473 | SCAD 21012299 Pressure Transmiitter | 5764.48 |  | 5764.48 |  |  | 56268.6 | 91500.96 | -35232.36 | 2017-03-31 07:27 | 2018-12-01 | 2017-06-01 | 2017-09-30
75086 | G7CAS112 | V4266 | Casing 112 Line AM07 | 9734.26 |  | 9734.26 |  |  | 263442.7 | 257083 | 6359.7 | 2018-08-02 14:00 | 2018-12-30 | 2018-08-01 | 2019-01-22
75086 | G7CAS22 | V4278 | Casing 22 Line AM07 | 9637.88 |  | 9637.88 |  |  | 251558.98 | 311445 | -59886.02 | 2018-08-02 16:45 | 2018-12-30 | 2018-08-01 | 2019-01-01
75086 | FPIT | V5136 | Communication Radio Install | 239.61 |  | 239.61 |  |  | 27590.03 | 23120 | 4470.03 | 2018-08-20 08:22 | 2018-12-31 | 2018-08-01
75086 | G7SECCON | V5175 | Erlanger Propane Security Upgrade | 29783.02 |  | 29783.02 |  |  | 2949390.48 | 950000 | 1999390.48 | 2018-08-21 17:03 | 2020-05-14 | 2019-02-01 | 2020-03-31
75086 | FP647 | V5213 | AM07 Casing Rem 647 Erlanger rd | 39887.14 |  | 39887.14 |  |  | 114174.86 | 115206.73 | -1031.87 | 2018-08-22 09:19 | 2019-03-30 | 2018-09-01 | 2018-11-23
75086 | G7CAS53 | V5417 | Casing 53 Line AM07 | 2348.92 |  | 2348.92 |  |  | 88813.8 | 409578 | -320764.2 | 2018-08-29 07:10 | 2018-12-30 | 2018-10-01 | 2019-03-01
75086 | G7EUL06 | V5625 | ECDA Line UL06 | 25760.68 |  | 25760.68 |  |  | 327140.48 | 494420 | -167279.52 | 2018-09-10 09:20 | 2019-03-30 | 2018-10-01 | 2019-03-17
75086 | G7LNLP03 | V5652 | Line LP03 | 11.25 |  | 11.25 |  |  | 886878.23 | 1325999 | -439120.77 | 2018-09-11 07:37 | 2019-02-28 | 2018-10-01 | 2019-02-15
75086 | G7EUL47 | V6391 | Line UL47 scheduled digs | 956.89 |  | 956.89 |  |  | 989422.73 | 724400 | 265022.73 | 2018-10-10 08:17 | 2019-03-30 | 2018-10-01 | 2019-03-14
75086 | G7S3300 | V7041 | Line UL02 Seg 3300 Pleasant Valley | -1802822.22 |  | -1802822.22 |  |  | -47965.95 | 2643704 | -2691669.95 | 2018-11-06 14:02 | 2020-07-30 | 2019-01-01 | 2020-01-15
75086 | G7PHMSA | V7283 | PHMSA CRM Plan | 407568.62 |  | 407568.62 |  |  | 1844151.93 | 416794 | 1427357.93 | 2018-11-14 14:31 | 2020-09-30 | 2018-12-01
75086 | G7CAS106 | V7737 | Casing#106 AM07 & Martha Layne | -187023.53 |  | -187023.53 |  |  | 1989733.46 | 1749344 | 240389.46 | 2018-11-28 14:40 | 2019-12-30 | 2018-12-01 | 2020-01-23
75086 | G7CAS106 | V7738 | Casing#106 AM07 & Martha Layne(LAND | 16857.21 |  | 16857.21 |  |  | 113350.22 | 10000 | 103350.22 | 2018-11-28 14:46 | 2019-12-30 | 2019-01-01 | 2020-01-23
75086 | G7CAS42 | V7739 | Casing#42 abandon- AM07 & Hulbert | -16773.81 |  | -16773.81 |  |  | 1698133.71 | 1939294 | -241160.29 | 2018-11-28 14:52 | 2019-11-30 | 2018-12-01 | 2019-11-15
75086 | G7CAS49 | V7902 | Casing #49 abandon - AM07 & I-75 | 354155.85 |  | 354155.85 |  |  | 7336064.29 | 6131715 | 1204349.29 | 2018-12-14 14:26 | 2020-02-28 | 2019-01-01 | 2020-02-23
75086 | G7CAS717 | V7904 | Casing #717 Line AM07 -US RT 50 | 9389.43 |  | 9389.43 |  |  | 410518.55 | 2072166 | -1661647.45 | 2018-12-14 14:36 | 2019-07-25 | 2019-01-01 | 2019-08-21
75086 | G7UL02PH1 | V8191 | UL60 Pipeline Phase 1 (PIPE) | 36195166.34 |  | 36195166.34 |  |  | 37992003.48 | 26326195 | 11665808.48 | 2019-01-23 15:21 | 2021-03-30 | 2019-01-01 | 2021-02-25
75086 | G7UL02PH1 | V8351 | UL60 Pipeline Phase 1 (STATION) | 1729006.09 |  | 1729006.09 |  |  | 1729350.24 | 6287827 | -4558476.76 | 2019-02-11 09:25 | 2021-03-30 | 2019-07-01 | 2021-03-13
75086 | G7UL02PH1 | V8352 | UL60 Pipeline P1 - LAND RIGHTS Proj | 3798057.96 |  | 3798057.96 |  |  | 4852995.35 | 1941000 | 2911995.35 | 2019-02-11 09:32 | 2021-03-30 | 2019-03-01 | 2021-02-25
75086 | G73701 | V8405 | Bridge Attach 3701 Narrows Rd | -508.06 |  | -508.06 |  |  | 12718.01 | 11495.55 | 1222.46 | 2019-02-18 10:01 | 2020-02-25 | 2019-09-01 | 2019-12-18
75086 | G7CAS717 | V8640 | Casing #717 LineAM074-USRT50 Land | 11229.28 |  | 11229.28 |  |  | 11229.28 | 15000 | -3770.72 | 2019-03-14 08:00 | 2020-09-25 | 2020-02-01 | 2019-08-21
75086 | G7AM07DIG | V8815 | Line AM07 Integrity Digs | 63305.46 |  | 63305.46 |  |  | 1306990.31 | 923350 | 383640.31 | 2019-04-02 12:33 | 2019-12-30 | 2019-06-01 | 2019-12-31
75086 | G7EQUIP | V8884 | KET NGBU Equipment | 15878.16 |  | 15878.16 |  |  | 33332.67 | 150768 | -117435.33 | 2019-04-11 08:23 | 2020-03-30 | 2019-06-01 | 2020-02-29
75086 | G7ECOMPLX | V8967 | Erlanger Modular Complex | 185878.01 |  | 185878.01 |  |  | 206914.85 | 244737.99 | -37823.14 | 2019-04-17 13:32 | 2020-10-30 | 2019-06-01
75086 | G7EPROPAN | V9131 | Erlanger OPP | 11124.29 |  | 11124.29 |  |  | 323087.82 | 954130.54 | -631042.72 | 2019-05-03 10:23 | 2020-03-30 | 2019-08-01 | 2020-10-31
75086 | G7ERLCP19 | V9157 | 2019 Erlanger Ops Mag Anodes | 39694.74 |  | 39694.74 |  |  | 390344.41 | 350811.63 | 39532.78 | 2019-05-08 10:16 | 2020-07-30 | 2019-05-01 | 2020-09-08
75086 | G7UL02PH2 | V9444 | UL60 Pipeline Phase II - Pipe | 1526340 |  | 1526340 |  |  | 1597274.76 | 22514005 | -20916730.24 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01
75086 | G7UL02PH2 | V9445 | UL60 Pipeline Phase II- LAND RIGHTS | 1604209.27 |  | 1604209.27 |  |  | 1713352.22 | 733000 | 980352.22 | 2019-06-12 08:04 | 2022-02-02 | 2019-07-01
|  |  |  | 81672473.53 | 64205604 | -17466869.53