## Summary
Duke Enegy Kentucky, Inc.
Calculation of Capital Construction Project Slippage Factor
Source: Schedule 25a - Construction Projects
(in millions)
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2016 | 32 | 22 | -10 | -45.45% | 145.5%
2017 | 51 | 44 | -7 | -15.91% | 115.9%
2018 | 73 | 51 | -22 | -43.14% | 143.1%
2019 | 94 | 49 | -45 | -91.84% | 191.8%
2020 | 82 | 64 | -18 | -28.12% | 128.1%
5 Year Avg Slippage | 332 | 230 | -102 | -44.35% | 144.3%
Costs include AFUDC - Debt