## Project Plans
Name | Start | Finish | 4Q2017 | 1Q2018 | 2Q2018 | 3Q2018 | 4Q2018 | 1Q2019 | 2Q2019 | 3Q2019 | 4Q2019 | 1Q2020 | 2Q2020 | 3Q2020 | 4Q2020 | 1Q2021 | 2Q2021 | 3Q2021 | 4Q2021 | 1Q2022 | 2Q2022 | 3Q2022 | 4Q2022 | 1Q2023
Release 1 Plan
Tasks | Mon 11/6/17 | Fri 7/27/18
2017 Pre-Planning | Mon 11/6/17 | Fri 1/12/18
Plan Phase | Tue 1/2/18 | Fri 2/23/18
Initiate Phase | Tue 1/9/18 | Fri 2/23/18
Design, Build, Validate Phase | Mon 1/22/18 | Thu 5/10/18
Test and Service Introduction Phase | Mon 3/26/18 | Thu 7/19/18
Deploy Phase | Mon 4/9/18 | Tue 6/19/18
R1 Go Live | Mon 6/18/18 | Mon 6/18/18
Warranty Phase | Thu 6/14/18 | Fri 7/27/18
Release 2 Plan
Tasks | Mon 11/6/17 | Fri 5/17/19
2017 Pre-Planning | Mon 11/6/17 | Fri 12/15/17
Plan Phase | Tue 1/2/18 | Tue 3/6/18
Initiate Phase | Fri 1/26/18 | Thu 6/7/18
Design, Build, Validate Phase | Fri 4/13/18 | Fri 2/15/19
Test and Service Introduction Phase | Mon 4/16/18 | Thu 2/28/19
Deploy Phase | Wed 8/15/18 | Thu 2/28/19
R2 Go Live | Mon 2/18/19 | Mon 2/18/19
Warranty Phase | Mon 2/18/19 | Fri 5/17/19
Release 3 Plan
Tasks | Mon 6/11/18 | Fri 12/13/19
Plan Phase | Mon 6/11/18 | Fri 9/7/18
Initiate Phase | Wed 8/1/18 | Fri 12/14/18
Design, Build, Validate Phase | Wed 8/1/18 | Fri 12/13/19
Test and Service Introduction Phase | Mon 3/25/19 | Fri 11/22/19
Deploy Phase | Mon 6/10/19 | Thu 10/31/19
R3 Go Live2 (2 deployments) | Mon 6/29/19 | Mon 9/30/19
Warranty Phase | Mon 7/2/18 | Fri 12/13/19
Release 4 Plan
Tasks | Thu 2/1/18 | Mon 7/27/20
Bill Format Design | Thu 2/1/18 | Thu 12/13/18
Plan Phase | Wed 1/2/19 | Fri 4/12/19
Initiate Phase | Thu 2/28/19 | Fri 5/17/19
Design, Build, Validate Phase | Mon 4/15/19 | Fri 12/6/19
Test and Service Introduction Phase | Mon 8/5/19 | Tue 5/26/20
Deploy Phase | Thu 10/10/19 | Tue 5/26/20
R4 Go Lives (4 deployments) | Mon 5/4/20 | Mon 6/15/20
Warranty Phase | Mon 6/1/20 | Mon 7/27/20
Release 5 Plan
Tasks | Tue 1/2/18 | Wed 9/22/21
Plan Phase | Tue 1/2/18 | Thu 3/29/18
Initiate Phase | Mon 2/19/18 | Mon 10/22/18
Design, Build, Validate Phase | Wed 8/15/18 | Thu 3/11/21
Test and Service Introduction Phase | Mon 7/30/18 | Tue 3/30/21
Deploy Phase | Wed 3/25/20 | Tue 3/30/21
DEC Go Live | Mon 4/5/21 | Mon 4/5/21
Warranty Phase | Tue 4/6/21 | Tue 6/29/21
Release 6-7 Plan
Tasks | Mon 8/31/20 | Fri 1/28/22
Design, Build, Validate Phase | Mon 8/31/20 | Tue 9/21/21
Test and Service Introduction Phase | Mon 2/15/21 | Fri 10/8/21
Deploy Phase | Fri 10/15/21 | Fri 11/5/21
DEF/DEP Go Live | Fri 11/5/21 | Fri 11/5/21
Warranty Phase | Mon 11/8/21 | Fri 1/28/22
Release 8 Plan
Tasks | Mon 7/5/21 | Wed 6/29/22
Design, Build, Validate Phase | Mon 7/5/21 | Fri 11/5/21
Test and Service Introduction Phase | Mon 7/5/21 | Fri 3/18/22
Deploy Phase | Thu 3/31/22 | Wed 4/6/22
DEMW Go Live | Wed 4/6/22 | Wed 4/6/22
Warranty Phase | Fri 12/3/21 | Wed 6/29/22
System Retirement Plan
Tasks | Mon 10/7/19 | Fri 3/31/23
Plan Phase | Mon 10/7/19 | Tue 8/24/21
Decommission Phase | Tue 11/17/20 | Fri 5/27/22
Archive Phase | Mon 2/15/21 | Fri 11/11/22
Dataview Phase | Mon 5/20/21 | Tue 10/4/22
Retirement Phase | Wed 5/12/21 | Mon 3/27/23
Retirements Complete | Fri 3/31/23 | Fri 3/31/23