## Project Controls Report (hidden)
Funding Project ID PRD | Funding Project Short Descr PRD | Bus Unit ID CB | Owner CD PRD | Post In Service Carrying Charge PRD | FP Business Program Name PRD | Accounting Period CMD | Fiscal Year CMD | Oper Unit ID CB | ENT Jurisdiction | Oper Unit Long Descr CB | Oper Unit Long Descr CB | Project ID CB | Project Short Descr CB | Original Budget Year Total Amount SUM | Actual In Service Date PRD | Estimated In Service Date PRD | Project Mgr Last Name PRD | Actual MTD Amount SUM | Budget MTD Amount SUM | Actual YTD Amount SUM | Budget YTD Amount SUM | Actual TTD Amount SUM | Budget TTD Amount SUM
|  | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
|  | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky |  | NO VALUE | 0 |  | 2958101 |  | 0 | 0 | 0 | 0 | -34225266.99 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -1.3952e-08 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -5.5565e-10 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | 4.5217e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -2.0627e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | 3.6089e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -3.0632e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -5.2505e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -8.0945e-10 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -1.0738e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | 3.9977e-10 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | 4.6057e-09 | 0
107GASOH | GAS OVERHEAD | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Z0071 | ULHP GAS CONSTR OVERHEADS | 0 |  | 42369 |  | 0 | 0 | 0 | 0 | -1.2858e-08 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -2.8422e-14 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 2.4301e-12 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 1.9895e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 8.5265e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -3.979e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 2.7285e-12 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -2.2737e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 1.4779e-12 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 2.8422e-14 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 1.7053e-12 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 6.8212e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -2.2737e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -1.0925e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 9.0949e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 8.0291e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -1.4211e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 7.4163e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 3.979e-13 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -1.1937e-12 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 9.9476e-14 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 1.3642e-12 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1358 | Brent Spence Bridge Rpl AM1 | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 2.8422e-14 | 0
AM01 | AM01 RIVER CROSSING | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1887 | Brent Spence Bridge Gas | 0 |  | 42369 | Shoemaker | 0 | 0 | 0 | 0 | -5.2838e-12 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3607 | PP 982909/ CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 30747.43 | 0
BETMEAIN | BETHEL INLET PIPING | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3608 | PP 982905/CWA | 0 | 2008-11-17 | 39769 | Shoemaker | 0 | 0 | 0 | 0 | 29360.02 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7638 | Casing AM07 Dixie Hwy | 0 | 2012-10-16 | 41204 | Shoemaker | 0 | 0 | 0 | 0 | 637184.75 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7750 | Casing Crescent Springs LP03 | 0 | 2012-08-03 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 81617.13 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7751 | Casing BS #48 AM07 | 0 | 2012-09-12 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 674201.79 | 0
CASINGKY | CASING REPLACEMENT KY | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7752 | Casing #87 BS Turkeyfoot AM07 | 0 | 2012-10-01 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 653041.76 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST1 | CAMP ERNST RD | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0904 | KY 237 Imp Pleasant Valley | 0 | 2012-08-01 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 903775.32 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
CPERNST2 | Camp Ernst Phase 2 | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7625 | Camp Ernst Rd - Rogers Ln to KY 18 | 0 | 2014-04-01 | 41835 | Shoemaker | 0 | 0 | 0 | 0 | 669787.31 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FCF53SKEG | Purch Panasonic CF53s repl MDTs | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CF53ERLAN | Purch Panasonic CF53s repl MDTs | 0 | 2016-12-05 | 42735 | Cole | 0 | 0 | 0 | 0 | 4395.16 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | -377.84 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | EGISS | Enable EGIS Software | 0 | 2017-08-07 | 42954 | Glenn | 0 | 0 | 0 | 0 | -16587.9 | 0
FENABLES | Enable Software Gas DEK. | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | ENABLETDG | ENABLETDG - Clearing Project | 0 | 2018-12-31 | 43282 | Glenn | 0 | 0 | 0 | 0 | 377.84 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FGISEAMGK | GIS-EAM R3 INTERFACE & SW-KENT. GAS | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GISEAMGK | GIS-EAM R3 INTERFACE & SW-GAS KENT. | 0 | 2011-02-01 | 40632 | Clippinger | 0 | 0 | 0 | 0 | 16469.82 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FKPIAPP | Perf Meas App(KPI) for T&D & Gas | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8060 | Perf Meas App (KPI) - T&D & Gas | 0 | 2015-10-30 | 42338 | Cole | 0 | 0 | 0 | 0 | 142.27 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 0 | 0 | 74287.72 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 0 | 0 | 74287.72 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 39887.14 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FP647 | AM07 Casing Rem 647 Erlanger rd | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5213 | AM07 Casing Rem 647 Erlanger rd | 0 | 2018-08-23 | 43464 | Colyer | 0 | 0 | 39887.14 | 0 | 114174.86 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPCTAVMKY | Vegetation Mgmt Kentucky | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9238 | Vegetation Mgmt Kentucky | 0 | 2014-11-30 | 42885 | Cole | 0 | 0 | 0 | 0 | 359.63 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 42.72 | 0 | 42.72 | 0 | 486.62 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 0 | 0 | 67127.36 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 8543.85 | 0 | 8543.85 | 0 | 228965.19 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 137.77 | 0 | 137.77 | 0 | 84616.62 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 5658.21 | 0 | 5658.21 | 0 | 676633.45 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 16538.22 | 0 | 16538.22 | 0 | 223863.35 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 15896.98 | 0 | 15896.98 | 0 | 40101.48 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | -744.3 | 0 | -744.3 | 0 | 599583.71 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 146.93 | 0 | 146.93 | 0 | 55566.14 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 3762.47 | 0 | 3762.47 | 0 | 47152.59 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 3790.31 | 0 | 3790.31 | 0 | 85483.6 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 40.88 | 0 | 83.6 | 0 | 527.5 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 68.4 | 0 | 68.4 | 0 | 67195.76 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 20173.12 | 0 | 28716.97 | 0 | 249138.31 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 131.83 | 0 | 269.6 | 0 | 84748.45 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 8279.88 | 0 | 13938.09 | 0 | 684913.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 9563.49 | 0 | 26101.71 | 0 | 233426.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 4003.13 | 0 | 19900.11 | 0 | 44104.61 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -744.3 | 0 | 599583.71 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 84.37 | 0 | 231.3 | 0 | 55650.51 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 3379.25 | 0 | 7141.72 | 0 | 50531.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 199.38 | 0 | 3989.69 | 0 | 85682.98 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 40.54 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0.37 | 0 | 68.77 | 0 | 67196.13 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | -6167.01 | 0 | 22549.96 | 0 | 242971.3 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 130.72 | 0 | 400.32 | 0 | 84879.17 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 6092.45 | 0 | 20030.54 | 0 | 691005.78 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 6214.41 | 0 | 32316.12 | 0 | 239641.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 3875.77 | 0 | 23775.88 | 0 | 47980.38 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 11.03 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 83.66 | 0 | 314.96 | 0 | 55734.17 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 5067.48 | 0 | 12209.2 | 0 | 55599.32 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 3037.61 | 0 | 7027.3 | 0 | 88720.59 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 13324.26 | 0 | 13324.26 | 0 | 13324.26 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 1644.32 | 0 | 1713.09 | 0 | 68840.45 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 20862.24 | 0 | 43412.2 | 0 | 263833.54 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 131.16 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 5102.4 | 0 | 25132.94 | 0 | 696108.18 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 4970.12 | 0 | 37286.24 | 0 | 244611.37 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 11292.9 | 0 | 35068.78 | 0 | 59273.28 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 83.94 | 0 | 398.9 | 0 | 55818.11 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 5228.25 | 0 | 17437.45 | 0 | 60827.57 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 4246.54 | 0 | 11273.84 | 0 | 92967.13 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 7400.8 | 0 | 20725.06 | 0 | 20725.06 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 1618.57 | 0 | 1618.57 | 0 | 1618.57 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | -1274.53 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 2226.4 | 0 | 45638.6 | 0 | 266059.94 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 4534.7 | 0 | 29667.64 | 0 | 700642.88 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 6960.88 | 0 | 44247.12 | 0 | 251572.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 111.9 | 0 | 35180.68 | 0 | 59385.18 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 59.71 | 0 | 458.61 | 0 | 55877.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 4942.06 | 0 | 22379.51 | 0 | 65769.63 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 2990.61 | 0 | 14264.45 | 0 | 95957.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 4880.71 | 0 | 25605.77 | 0 | 25605.77 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 3433.62 | 0 | 5052.19 | 0 | 5052.19 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 584.65 | 0 | 46223.25 | 0 | 266644.59 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 3146.65 | 0 | 32814.29 | 0 | 703789.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 3767.73 | 0 | 48014.85 | 0 | 255339.98 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 7080.03 | 0 | 42260.71 | 0 | 66465.21 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | -402.42 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 4920.43 | 0 | 27299.94 | 0 | 70690.06 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 6098.12 | 0 | 20362.57 | 0 | 102055.86 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 1642.76 | 0 | 27248.53 | 0 | 27248.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 5449.53 | 0 | 10501.72 | 0 | 10501.72 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 87.5 | 0 | 46310.75 | 0 | 266732.09 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 4193.62 | 0 | 37007.91 | 0 | 707983.15 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 3928.1 | 0 | 51942.95 | 0 | 259268.08 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 3524.98 | 0 | 45785.69 | 0 | 69990.19 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 0 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 5155.67 | 0 | 32455.61 | 0 | 75845.73 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 64 | 0 | 20426.57 | 0 | 102119.86 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 13.83 | 0 | 27262.36 | 0 | 27262.36 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 4700.83 | 0 | 15202.55 | 0 | 15202.55 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 5.08 | 0 | 46315.83 | 0 | 266737.17 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 1995.2 | 0 | 39003.11 | 0 | 709978.35 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 2207.72 | 0 | 54150.67 | 0 | 261475.8 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 26.39 | 0 | 45812.08 | 0 | 70016.58 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 0 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 5553.67 | 0 | 38009.28 | 0 | 81399.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 55.55 | 0 | 20482.12 | 0 | 102175.41 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 10.23 | 0 | 27272.59 | 0 | 27272.59 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 5463.25 | 0 | 20665.8 | 0 | 20665.8 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 6.62 | 0 | 6.62 | 0 | 6.62 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 4.95 | 0 | 46320.78 | 0 | 266742.12 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 1984.46 | 0 | 40987.57 | 0 | 711962.81 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | -47.11 | 0 | 54103.56 | 0 | 261428.69 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 7050.88 | 0 | 52862.96 | 0 | 77067.46 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 0 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 5146.23 | 0 | 43155.51 | 0 | 86545.63 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 29.25 | 0 | 20511.37 | 0 | 102204.66 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 7.74 | 0 | 27280.33 | 0 | 27280.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 5531.32 | 0 | 26197.12 | 0 | 26197.12 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 17.78 | 0 | 24.4 | 0 | 24.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 0 | 0 | 46320.78 | 0 | 266742.12 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 1503.83 | 0 | 42491.4 | 0 | 713466.64 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 0 | 0 | 54103.56 | 0 | 261428.69 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 0 | 0 | 52862.96 | 0 | 77067.46 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 0 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 4745.44 | 0 | 47900.95 | 0 | 91291.07 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 69.43 | 0 | 20580.8 | 0 | 102274.09 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900067 | ARM to Maximo Integration | 0 | 2021-04-27 | 44313 | Wood | 559.89 | 0 | 559.89 | 0 | 559.89 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 18.37 | 0 | 27298.7 | 0 | 27298.7 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 883.3 | 0 | 27080.42 | 0 | 27080.42 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 24.77 | 0 | 49.17 | 0 | 49.17 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 0 | 0 | 46320.78 | 0 | 266742.12 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 3080.07 | 0 | 45571.47 | 0 | 716546.71 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 0 | 0 | 54103.56 | 0 | 261428.69 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 4099.87 | 0 | 56962.83 | 0 | 81167.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 0 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 4080.24 | 0 | 51981.19 | 0 | 95371.31 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 1795.93 | 0 | 22376.73 | 0 | 104070.02 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900067 | ARM to Maximo Integration | 0 | 2021-04-27 | 44313 | Wood | 207.22 | 0 | 767.11 | 0 | 767.11 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 27.87 | 0 | 27326.57 | 0 | 27326.57 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | -5256.24 | 0 | 21824.18 | 0 | 21824.18 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 124.14 | 0 | 568.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 322957EGI | EGIS & Gas Fusion Linkage Enhance | 0 | 2019-01-29 | 43486 |  | 0 | 0 | 0 | 0 | 25387.96 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 347565014 | 2018 Cisco EOL KY Phase 1 | 0 | 2019-04-30 | 43585 |  | 0 | 0 | 0 | 0 | 488417.84 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 359990001 | Field Test Equipment Calibration So | 0 | 2019-09-01 | 43738 |  | 0 | 0 | 438.56 | 0 | 67565.92 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 2775.25 | 0 | 2824.42 | 0 | 2824.42 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30060 | Consolidated SCADA App Analysis | 0 | 2020-03-31 | 43921 |  | 6724 | 0 | 53044.78 | 0 | 273466.12 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30062 | INTGO_PI SCADA Data Implementation | 0 |  | 43677 | Correll | 0 | 0 | 0 | 0 | -10619.25 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA3006K | INTGO_PI SCADA Data Implementation | 0 |  | 44547 |  | 0 | 0 | 531.48 | 0 | 85010.33 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30073 | Project 2 Gas Supply System | 0 | 2020-12-31 | 44196 |  | 1633.56 | 0 | 47205.03 | 0 | 718180.27 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30114 | Sales Force Automation Conso Strate | 0 | 2020-08-10 | 44073 | Correll | 0 | 0 | 54103.56 | 0 | 261428.69 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30128 | INTGO_Conso Gas Eng Calculators | 0 | 2019-07-31 | 43677 | Correll | 0 | 0 | 0 | 0 | 17728.16 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30391 | INTGO_Gas Major Projects Mgmt | 0 | 2020-09-30 | 44104 |  | 1659.39 | 0 | 58622.22 | 0 | 82826.72 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30436 | INTGO_Gas SCADA Consolidation Progr | 0 | 2019-09-01 | 43738 |  | 0 | 0 | -733.27 | 0 | 599594.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA31738 | INTET-Enterprise Data Platform | 0 | 2018-04-30 | 43220 | Correll | 0 | 0 | 0 | 0 | 11864.53 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA33039 | INTGO_Consolidated CAD Tools | 0 | 2019-12-31 | 44008 |  | 0 | 0 | 56.19 | 0 | 55475.4 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA43704 | Natural Gas Bus Contractor Registra | 0 | 2019-10-18 | 43756 |  | 0 | 0 | 0 | 0 | 37372.39 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA47001 | INTGO_Materials Traceability | 0 | 2020-02-29 | 44561 |  | 4668.66 | 0 | 56649.85 | 0 | 100039.97 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700A | INTGO_Traceability Form EAM | 0 | 2020-12-14 | 44196 |  | 0 | 0 | 0 | 0 | 61.95 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA4700B | INTGO_Traceability Form FDC | 0 | 2020-12-14 | 44196 |  | 36.7 | 0 | 22413.43 | 0 | 104106.72 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900067 | ARM to Maximo Integration | 0 | 2021-04-27 | 44313 | Wood | 282.08 | 0 | 1049.19 | 0 | 1049.19 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900069 | TRG - WAM Measurement Project | 0 |  | 44463 | Gilliam | 0 | 0 | 27326.57 | 0 | 27326.57 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5136 | Communication Radio Install | 0 |  | 43465 | Long | 0 | 0 | 0 | 0 | 26381.82 | 0
FPIT | IT Funding Project for Demand Work | 75086 |  |  | IS-INFORMATION SERVICES | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CC2000001 | NGBU Communications Platform | 0 |  | 44561 | Jordan | 107.14 | 0 | 21931.32 | 0 | 21931.32 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 0 | 0 | 116848.1 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 0 | 0 | 116848.1 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 44060.97 | 0 | 44060.97 | 0 | 160909.07 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 44060.97 | 0 | 160909.07 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 44060.97 | 0 | 160909.07 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 50955.06 | 0 | 95016.03 | 0 | 211864.13 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 23980.17 | 0 | 118996.2 | 0 | 235844.3 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 1586.11 | 0 | 120582.31 | 0 | 237430.41 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 120582.31 | 0 | 237430.41 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 120582.31 | 0 | 237430.41 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 120582.31 | 0 | 237430.41 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | GCTA30389 | INTGO_Gas Distribution Proj Managem | 0 | 2019-03-31 | 43752 |  | 0 | 0 | 0 | 0 | 37028.01 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900021 | GIS Alignment for PCS - Midwest | 0 | 2020-10-17 | 44119 | Abril Herrera | 0 | 0 | 120582.31 | 0 | 237430.41 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5414.92 | 0 | 5414.92 | 0 | 5414.92
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5433.7 | 0 | 10848.62 | 0 | 10848.62
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5452.55 | 0 | 16301.17 | 0 | 16301.17
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5471.48 | 0 | 21772.65 | 0 | 21772.65
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5490.46 | 0 | 27263.11 | 0 | 27263.11
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5509.51 | 0 | 32772.62 | 0 | 32772.62
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5528.63 | 0 | 38301.25 | 0 | 38301.25
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5547.82 | 0 | 43849.07 | 0 | 43849.07
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5567.06 | 0 | 49416.13 | 0 | 49416.13
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5586.38 | 0 | 55002.51 | 0 | 55002.51
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5605.77 | 0 | 60608.28 | 0 | 60608.28
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FPIT | IT Funding Project for Demand Work | 2080-11-02 00:43 |  | 55153 |  | 0 | 5443.75 | 0 | 66052.03 | 0 | 66052.03
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 423.78 | 0 | 423.78 | 0 | 423.78 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 11452.46 | 0 | 11876.24 | 0 | 11876.24 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 825.22 | 0 | 12701.46 | 0 | 12701.46 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 12781.1 | 0 | 25482.56 | 0 | 25482.56 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 1834.14 | 0 | 27316.7 | 0 | 27316.7 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 2096.94 | 0 | 29413.64 | 0 | 29413.64 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 12979.41 | 0 | 42393.05 | 0 | 42393.05 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 8502.69 | 0 | 50895.74 | 0 | 50895.74 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 2238.12 | 0 | 53133.86 | 0 | 53133.86 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 7623.18 | 0 | 60757.04 | 0 | 60757.04 | 0
FPIT | IT Funding Project for Demand Work | 75086 | Gas Ops - M&R, LNG & Maintenance |  | IS-INFORMATION SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | IT1900065 | GDPM Phase 2 | 0 | 2020-12-31 | 44196 | Wood | 7840.88 | 0 | 68597.92 | 0 | 68597.92 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 786993.43 | 0 | 786993.43 | 0 | 505120.37 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 27616.5 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -754725.57 | 23304.018 | -754725.57 | 23304.018 | -286664.526 | 23304.018
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 1 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 11881.04 | 0 | 798874.47 | 0 | 517001.41 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 195.04 | 0 | 195.04 | 0 | 27811.54 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | 5018.87 | 2533.039 | -749706.7 | 25837.057 | -281645.656 | 25837.057
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 2 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 72346.53 | 0 | 871221 | 0 | 589347.94 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 195.04 | 0 | 27811.54 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -38237.31 | 3079.205 | -787944.01 | 28916.262 | -319882.966 | 28916.262
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 3 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 147859.95 | 0 | 1019080.95 | 0 | 737207.89 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 195.04 | 0 | 27811.54 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -116732.58 | 2999.874 | -904676.59 | 31916.136 | -436615.546 | 31916.136
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 4 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 137400.93 | 0 | 1156481.88 | 0 | 874608.82 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 195.04 | 0 | 27811.54 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -105175.83 | 4914.951 | -1009852.42 | 36831.087 | -541791.376 | 36831.087
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 5 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 112631.28 | 0 | 1269113.16 | 0 | 987240.1 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 195.04 | 0 | 27811.54 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -89542.24 | 2966.201 | -1099394.66 | 39797.288 | -631333.616 | 39797.288
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 6 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 161652.01 | 0 | 1430765.17 | 0 | 1148892.11 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 195.04 | 0 | 27811.54 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -139279.8 | 14897.476 | -1238674.46 | 54694.764 | -770613.416 | 54694.764
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 7 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 130187.33 | 0 | 1560952.5 | 0 | 1279079.44 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 25.8 | 0 | 220.84 | 0 | 27837.34 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -110836.75 | 2733.172 | -1349511.21 | 57427.936 | -881450.166 | 57427.936
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 8 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 121040.13 | 0 | 1681992.63 | 0 | 1400119.57 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 220.84 | 0 | 27837.34 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -81352.3 | 2570.284 | -1430863.51 | 59998.22 | -962802.466 | 59998.22
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 9 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 72527.78 | 0 | 1754520.41 | 0 | 1472647.35 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 220.84 | 0 | 27837.34 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -50988.1 | 2707.459 | -1481851.61 | 62705.679 | -1013790.566 | 62705.679
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 10 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 192898.51 | 0 | 1947418.92 | 0 | 1665545.86 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 12 | 0 | 232.84 | 0 | 27849.34 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -163258.61 | 2727.136 | -1645110.22 | 65432.815 | -1177049.176 | 65432.815
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 11 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 154751.96 | 0 | 2102170.88 | 0 | 1820297.82 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 232.84 | 0 | 27849.34 | 0
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 107GASCK | Gas Capital Overhead | 2117-09-11 19:28 |  | 55153 | Clippinger | -140910.92 | 14080.996 | -1786021.14 | 79513.811 | -1317960.096 | 79513.811
FUNCTOHKY | Allocations | 75086 |  |  | MISC-MISCELLANEOUS PROJECTS | 12 | 2020 | GOKY | Duke Energy Kentucky - Gas | Gas Ops Other Kentucky | Gas Ops Other Kentucky | 107GASCK | Gas Capital Overhead | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | 20 | 0
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1906.89 | 0 | -1906.89 | 0 | -1906.89
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1913.51 | 0 | -3820.4 | 0 | -3820.4
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1920.15 | 0 | -5740.55 | 0 | -5740.55
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1926.81 | 0 | -7667.36 | 0 | -7667.36
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1933.49 | 0 | -9600.85 | 0 | -9600.85
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1940.2 | 0 | -11541.05 | 0 | -11541.05
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1946.94 | 0 | -13487.99 | 0 | -13487.99
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1953.69 | 0 | -15441.68 | 0 | -15441.68
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1960.47 | 0 | -17402.15 | 0 | -17402.15
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1967.27 | 0 | -19369.42 | 0 | -19369.42
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1974.1 | 0 | -21343.52 | 0 | -21343.52
FUNCTOHKY | Allocations | 75086 | Gas Ops - Corporate & Other | Rate Case Lag | MISC-MISCELLANEOUS PROJECTS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | FUNCTOHKY | Allocations | -23324.47 |  | 55153 | Reynolds | 0 | -1980.95 | 0 | -23324.47 | 0 | -23324.47
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 5654.53 | 0 | 5654.53 | 0 | 5654.53
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 6041.2 | 0 | 11695.73 | 0 | 11695.73
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 6577.52 | 0 | 18273.25 | 0 | 18273.25
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 7033.53 | 0 | 25306.78 | 0 | 25306.78
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 7610.58 | 0 | 32917.36 | 0 | 32917.36
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 9676.33 | 0 | 42593.69 | 0 | 42593.69
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 10350.3 | 0 | 52943.99 | 0 | 52943.99
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 13075.9 | 0 | 66019.89 | 0 | 66019.89
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 15754.65 | 0 | 81774.54 | 0 | 81774.54
G712237 | Hebron 12" Pl. SegII Elijah to 237 | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G712237 | Hebron 12" Pl. SegII Elijah to 237 | 2180-11-02 03:07 |  | 44500 | Fritsch | 0 | 20801.59 | 0 | 102576.13 | 0 | 102576.13
G712THST | 12TH STREET | 75086 |  | 2010 |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7330 | 12TH STREET, COVINGTON | 0 | 2010-07-22 | 41814 | Shoemaker | 0 | 0 | 0 | 0 | 858723.29 | 0
G712THST | 12TH STREET | 75086 |  | 2010 |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0844 | Madison Ave | 0 | 2010-03-10 | 40298 | Shoemaker | 0 | 0 | 0 | 0 | 164115.26 | 0
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -5.14 | 70780.41 | -5.14
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -10.28 | 70780.41 | -10.28
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -15.42 | 70780.41 | -15.42
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -20.56 | 70780.41 | -20.56
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -25.7 | 70780.41 | -25.7
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -30.84 | 70780.41 | -30.84
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -35.98 | 70780.41 | -35.98
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -41.12 | 70780.41 | -41.12
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | 0 | -46.26 | 70780.41 | -46.26
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | -3553.73 | -5.14 | -3553.73 | -51.4 | 67226.68 | -51.4
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | -3553.73 | -56.54 | 67226.68 | -56.54
G71373 | 1373 US 27 Bridge Attachment | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0856 | 1373 US 27 Bridge Attachment | -61.68 | 2019-12-30 | 43799 | Gusler | 0 | -5.14 | -3553.73 | -61.68 | 67226.68 | -61.68
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 21023.29 | 0 | 21023.29 | 0 | 21023.29
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 22546.56 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G71373 | 1373 US 27 Bridge Attachment | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G71373 | 1373 US 27 Bridge Attachment | 2019-04-14 20:24 | 2019-12-30 | 43799 | Mitchell | 0 | 0 | 0 | 43569.85 | 0 | 43569.85
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7783733 | BEAVER RD INSTALL REPLACEMENT PROJE | 0 | 2020-10-12 | 44120 | Shelton | 97.64 | 0 | 97.64 | 0 | 97.64 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7783733 | BEAVER RD INSTALL REPLACEMENT PROJE | 0 | 2020-10-12 | 44120 | Shelton | 13424.62 | 0 | 13522.26 | 0 | 13522.26 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7783733 | BEAVER RD INSTALL REPLACEMENT PROJE | 0 | 2020-10-12 | 44120 | Shelton | 2236.68 | 0 | 15758.94 | 0 | 15758.94 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7783733 | BEAVER RD INSTALL REPLACEMENT PROJE | 0 | 2020-10-12 | 44120 | Shelton | 16.03 | 0 | 15774.97 | 0 | 15774.97 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7783733 | BEAVER RD INSTALL REPLACEMENT PROJE | 0 | 2020-10-12 | 44120 | Shelton | 13.11 | 0 | 15788.08 | 0 | 15788.08 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 965.18 | 0 | 965.18 | 0 | 965.18
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 1451.15 | 0 | 2416.33 | 0 | 2416.33
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 4366.68 | 0 | 6783.01 | 0 | 6783.01
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 10319.49 | 0 | 17102.5 | 0 | 17102.5
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 11067.2 | 0 | 28169.7 | 0 | 28169.7
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 6271.59 | 0 | 34441.29 | 0 | 34441.29
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 1234.17 | 0 | 35675.46 | 0 | 35675.46
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 0 | 0 | 35675.46 | 0 | 35675.46
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 0 | 0 | 35675.46 | 0 | 35675.46
G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7237BEAV | Pipeline Exposure - 237 Beaver Rd K | 1997-09-02 11:02 | 2020-10-12 | 44012 | Fritsch | 0 | 0 | 0 | 35675.46 | 0 | 35675.46
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | -72.11 | -0.99 | -72.11 | -0.99 | 13044.48 | -0.99
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -1.98 | 13044.48 | -1.98
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -2.97 | 13044.48 | -2.97
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -3.96 | 13044.48 | -3.96
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -4.95 | 13044.48 | -4.95
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -5.94 | 13044.48 | -5.94
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -6.93 | 13044.48 | -6.93
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -7.92 | 13044.48 | -7.92
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -72.11 | -8.91 | 13044.48 | -8.91
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | -331.9 | -0.99 | -404.01 | -9.9 | 12712.58 | -9.9
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -404.01 | -10.89 | 12712.58 | -10.89
G73701 | Bridge Attach 3701 Narrows Rd | 75086 |  |  | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8405 | Bridge Attach 3701 Narrows Rd | -11.88 | 2019-09-18 | 43799 | Mitchell | 0 | -0.99 | -404.01 | -11.88 | 12712.58 | -11.88
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 1628.76 | 0 | 1628.76 | 0 | 1628.76
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 1735.93 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73701 | Bridge Attach 3701 Narrows Rd | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73701 | Bridge Attach 3701 Narrows Rd | 1909-03-17 16:34 | 2019-09-18 | 43799 | Mitchell | 0 | 0 | 0 | 3364.69 | 0 | 3364.69
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 1821674.36 | 0 | 1821674.36 | 0 | 15125573.81 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 0 | 0 | 2580.74 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 346.08 | 0 | 346.08 | 0 | 217075.83 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 828.13 | 0 | 828.13 | 0 | 12378.09 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 2281.78 | 0 | 2281.78 | 0 | 2927.68 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 2082335.81 | 0 | 3904010.17 | 0 | 17207909.62 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 0 | 0 | 2580.74 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 331.15 | 0 | 677.23 | 0 | 217406.98 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 828.13 | 0 | 12378.09 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 33 | 0 | 2314.78 | 0 | 2960.68 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 2286237.72 | 0 | 6190247.89 | 0 | 19494147.34 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 0 | 0 | 2580.74 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 328.37 | 0 | 1005.6 | 0 | 217735.35 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 8.15 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 25.2 | 0 | 2339.98 | 0 | 2985.88 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 1700732.18 | 0 | 7890980.07 | 0 | 21194879.52 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 0 | 0 | 2580.74 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 329.46 | 0 | 1335.06 | 0 | 218064.81 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 2339.98 | 0 | 2985.88 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 922825.59 | 0 | 8813805.66 | 0 | 22117705.11 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 0 | 0 | 2580.74 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 234.34 | 0 | 1569.4 | 0 | 218299.15 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 12225.39 | 0 | 14565.37 | 0 | 15211.27 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 1053150.07 | 0 | 9866955.73 | 0 | 23170855.18 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 17704.11 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | -2932.38 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | -58.77 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 503473.93 | 0 | 10370429.66 | 0 | 23674329.11 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 0 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | -10166.67 | 0 | 10360262.99 | 0 | 23664162.44 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 0 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 913219.56 | 0 | 11273482.55 | 0 | 24577382 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 0 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 337797.33 | 0 | 11611279.88 | 0 | 24915179.33 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 0 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 177943.88 | 0 | 11789223.76 | 0 | 25093123.21 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 0 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0747 | AM00a Automation of RCV -Alexandria | 0 | 2018-03-15 | 43784 | Perkins | 0 | 0 | 0 | 0 | 147178.12 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 728.05 | 0 | 11789951.81 | 0 | 25093851.26 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1437LAND | 3 Mile Station (LAND) | 0 | 2020-06-15 | 43941 | Pollak | 0 | 0 | 17704.11 | 0 | 20284.85 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4422 | AM07 Barleycorns | 0 | 2019-09-01 | 43936 | Seiter | 0 | 0 | -1362.98 | 0 | 215366.77 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 836.28 | 0 | 12386.24 | 0
G73MILES | Three Mile Station Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1437 | STA 249: Three Mile Rd | 0 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 14506.6 | 0 | 15152.5 | 0
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 1169847.11 | 0 | 1169847.11 | 0 | 1169847.11
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 1360854.01 | 0 | 2530701.12 | 0 | 2530701.12
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 1017295.66 | 0 | 3547996.78 | 0 | 3547996.78
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 692264.81 | 0 | 4240261.59 | 0 | 4240261.59
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 374210.03 | 0 | 4614471.62 | 0 | 4614471.62
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 191971.33 | 0 | 4806442.95 | 0 | 4806442.95
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 0 | 4806442.95 | 0 | 4806442.95
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 0 | 4806442.95 | 0 | 4806442.95
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 0 | 4806442.95 | 0 | 4806442.95
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 0 | 4806442.95 | 0 | 4806442.95
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 0 | 4806442.95 | 0 | 4806442.95
G73MILES | Three Mile Station Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G73MILES | Three Mile Station Replacement | 4806442.95 | 2020-06-15 | 43971 | Pollak | 0 | 0 | 0 | 4806442.95 | 0 | 4806442.95
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 6168.47 | 0 | 6168.47 | 0 | 6168.47
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 6781.97 | 0 | 12950.44 | 0 | 12950.44
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 7421.91 | 0 | 20372.35 | 0 | 20372.35
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 8216.55 | 0 | 28588.9 | 0 | 28588.9
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 9837.83 | 0 | 38426.73 | 0 | 38426.73
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 11581.21 | 0 | 50007.94 | 0 | 50007.94
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 13488.08 | 0 | 63496.02 | 0 | 63496.02
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 18355.86 | 0 | 81851.88 | 0 | 81851.88
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 24491.4 | 0 | 106343.28 | 0 | 106343.28
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 30664.33 | 0 | 137007.61 | 0 | 137007.61
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 91872.53 | 0 | 228880.14 | 0 | 228880.14
G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AIRAMA | (Cancel) Airport Pr. Upg Amazon | 362652.02 |  | 44377 | Fritsch | 0 | 133771.88 | 0 | 362652.02 | 0 | 362652.02
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 23165.57 | 0 | 23165.57 | 0 | 23165.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 4340 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM04A | (Cancel) CP Remediat AM04A,AM04B | 1975-04-21 13:41 |  | 43799 | Gusler | 0 | 0 | 0 | 27505.57 | 0 | 27505.57
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 72437.2 | 0 | 72437.2 | 0 | 381164.91 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 1213047.87 | 0 | 1285485.07 | 0 | 1594212.78 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 13477.26 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07CUT | AM07 Cutout Fidelity | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1330 | AM07 Cutout Fidelity | 0 | 2019-11-02 | 43771 | Seiter | 0 | 0 | 1298962.33 | 0 | 1607690.04 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 0 | 0 | 1243620.01 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 0 | 0 | 1243620.01 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 63305.46 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07DIG | Line AM07 Integrity Digs | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8815 | Line AM07 Integrity Digs | 0 | 2019-09-30 | 43738 | Schuchter | 0 | 0 | 63305.46 | 0 | 1306925.47 | 0
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 0233100 | Line AM07 Pipeline Replacement Phas | 0 |  | 45260 | Seiter | 1431.57 | 0 | 1431.57 | 0 | 1431.57 | 0
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 405688.26 | 0 | 405688.26 | 0 | 405688.26
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 428664.84 | 0 | 834353.1 | 0 | 834353.1
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 430840.93 | 0 | 1265194.03 | 0 | 1265194.03
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 431839.37 | 0 | 1697033.4 | 0 | 1697033.4
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 432296.98 | 0 | 2129330.38 | 0 | 2129330.38
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 433936.97 | 0 | 2563267.35 | 0 | 2563267.35
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 422481.19 | 0 | 2985748.54 | 0 | 2985748.54
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 436799.49 | 0 | 3422548.03 | 0 | 3422548.03
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 438541.25 | 0 | 3861089.28 | 0 | 3861089.28
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 440117.56 | 0 | 4301206.84 | 0 | 4301206.84
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 441620.28 | 0 | 4742827.12 | 0 | 4742827.12
G7AM07ILI | Line AM07 - Pipeline Replacement | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AM07ILI | Line AM07 - Pipeline Replacement | 5173646.88 |  | 45290 | Seiter | 0 | 430819.76 | 0 | 5173646.88 | 0 | 5173646.88
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 261.71 | 0 | 261.71 | 0 | 261.71
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 300.78 | 0 | 562.49 | 0 | 562.49
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 356.39 | 0 | 918.88 | 0 | 918.88
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 457.03 | 0 | 1375.91 | 0 | 1375.91
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 692.37 | 0 | 2068.28 | 0 | 2068.28
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 1563.16 | 0 | 3631.44 | 0 | 3631.44
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 2693.4 | 0 | 6324.84 | 0 | 6324.84
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 4617.29 | 0 | 10942.13 | 0 | 10942.13
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 3218.66 | 0 | 14160.79 | 0 | 14160.79
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 4529.25 | 0 | 18690.04 | 0 | 18690.04
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 4544.6 | 0 | 23234.64 | 0 | 23234.64
G7AMRP | KY AMRP Bare Steel | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7AMRP | KY AMRP Bare Steel | 1970-05-20 16:19 |  | 44134 | Fritsch | 0 | 2474.04 | 0 | 25708.68 | 0 | 25708.68
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 21027.23 | 0 | 21027.23 | 0 | 21027.23 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 1626.95 | 0 | 22654.18 | 0 | 22654.18 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 7198.07 | 0 | 29852.25 | 0 | 29852.25 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 7661.26 | 0 | 37513.51 | 0 | 37513.51 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 10.63 | 0 | 37524.14 | 0 | 37524.14 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 1205.3 | 0 | 38729.44 | 0 | 38729.44 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 12637.25 | 0 | 51366.69 | 0 | 51366.69 | 0
G7ASDD | Amazon SW Delivery Dist (UL60) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5515912 | AMAZON SOUTHWEST DELIVERY DIST. PRO | 0 | 2021-01-04 | 44025 | Helm | 4650.71 | 0 | 56017.4 | 0 | 56017.4 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 8072.44 | 0 | 8072.44 | 0 | 8878895.16 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | -259042.07 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 260922.63 | 0 | 260922.63 | 0 | 40976536.3 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6.22 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8072.44 | 0 | 8878895.16 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | -259042.07 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 87841.12 | 0 | 348763.75 | 0 | 41064377.42 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 6.42 | 0 | 6.42 | 0 | 12.64 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 28.81 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 74283.42 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 7413.48 | 0 | 356177.23 | 0 | 41071790.9 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0.06 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 1871.35 | 0 | 358048.58 | 0 | 41073662.25 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 57290.56 | 0 | 415339.14 | 0 | 41130952.81 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 12925.56 | 0 | 428264.7 | 0 | 41143878.37 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 16107.58 | 0 | 444372.28 | 0 | 41159985.95 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 77383.8 | 0 | 521756.08 | 0 | 41237369.75 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 29064.71 | 0 | 550820.79 | 0 | 41266434.46 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 22243.2 | 0 | 573063.99 | 0 | 41288677.66 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 86815.55 | 0 | 659879.54 | 0 | 41375493.21 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 8101.25 | 0 | 8878923.97 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMSP70 | ASRP Greater than 2" C-M Install | 0 |  | 43830 | Davis | 0 | 0 | 74283.42 | 0 | -184758.65 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCSP70 | ASRP Greater than 2" M-C Replace | 0 |  | 43830 | Davis | 0 | 0 | 0 | 0 | 5202.19 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 10630.96 | 0 | 670510.5 | 0 | 41386124.17 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMSP70 | ASRP Curb to Meter 3" or Less | 0 |  | 43830 | Reynolds | 0 | 0 | 0 | 0 | 508.79 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 0 | 0 | 6174.1 | 0
G7ASRP | ASRP KENTUCKY | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCSP70 | ASRP Main to Curb 3" or less | 0 |  | 43830 | Shoemaker | 0 | 0 | 6.48 | 0 | 12.7 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7ASRP | ASRP KENTUCKY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ASRP | ASRP KENTUCKY | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 27181604.27 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4856 | Big Bone 8" IP Main to Richwood | 0 | 2017-09-05 | 43039 | Perkins | 0 | 0 | 0 | 0 | 194484.12 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0881 | Big Bone Odorant Station - SCADA | 0 | 2018-05-05 | 43342 | Perkins | 0 | 0 | 0 | 0 | 190872.42 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 1838.88 | 0
G7BIGBON | Big Bone Pipeline (UL57) | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2190 | Big Bone Pipeline | 0 | 2018-05-05 | 43159 | Perkins | 0 | 0 | 0 | 0 | 3368.92 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7458 | Covington Augustine Bldg | 0 | 2006-10-30 | 39020 |  | 0 | 0 | 0 | 0 | 124.41 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1396 | 19th & Augustine windows | 0 | 2008-12-18 | 39813 |  | 0 | 0 | 0 | 0 | -3128.39 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2104 | Automatic Gates 19th & Augustine | 0 | 2009-12-22 | 40162 |  | 0 | 0 | 0 | 0 | 146105.79 | 0
G7BUPG | KENTUCKY BUILDING UPGRADES | 75086 |  |  | BLDG-BUILDINGS AND LAND | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4602 | Install Auto Gate -Erlanger Gas Pl | 0 | 2012-09-27 | 41228 | Shoemaker | 0 | 0 | 0 | 0 | 99213.95 | 0
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 3089.13 | 0 | 3089.13 | 0 | 3089.13
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 4269.4 | 0 | 7358.53 | 0 | 7358.53
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 5956.26 | 0 | 13314.79 | 0 | 13314.79
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 9023.02 | 0 | 22337.81 | 0 | 22337.81
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 16220.2 | 0 | 38558.01 | 0 | 38558.01
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 34676.43 | 0 | 73234.44 | 0 | 73234.44
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 61688.41 | 0 | 134922.85 | 0 | 134922.85
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 104785.76 | 0 | 239708.61 | 0 | 239708.61
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 85184.4 | 0 | 324893.01 | 0 | 324893.01
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 133531.22 | 0 | 458424.23 | 0 | 458424.23
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 133983.77 | 0 | 592408 | 0 | 592408
G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS103 | Casing# 103 700US RT 27 Falmouth KY | 662930.6 |  | 44195 | Fritsch | 0 | 70522.6 | 0 | 662930.6 | 0 | 662930.6
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | -251339.82 | 0 | -251339.82 | 0 | 1920433.04 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 14007.01 | 0 | 14007.01 | 0 | 110100.59 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 29443.6 | 0 | -221896.22 | 0 | 1949876.64 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 14007.01 | 0 | 110100.59 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 29946.47 | 0 | -191949.75 | 0 | 1979823.11 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 2850.2 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 4926.22 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | -187023.53 | 0 | 1984749.33 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7738 | Casing#106 AM07 & Martha Layne(LAND | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 16857.21 | 0 | 112950.79 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7737 | Casing#106 AM07 & Martha Layne | 0 | 2019-10-23 | 43739 | Seiter | 0 | 0 | 0 | 0 | 2063.76 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS106 | Casing #106 Martha Layne Collins Bl | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS106 | Casing #106 Martha Layne Collins Bl | 0 | 2019-10-23 | 43748 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 0 | 0 | 253697.53 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 0 | 0 | 253697.53 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 0 | 0 | 253697.53 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 0 | 0 | 253697.53 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 0 | 0 | 253697.53 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 0 | 0 | 253697.53 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 9734.26 | 0 | 9734.26 | 0 | 263431.79 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 9734.26 | 0 | 263431.79 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 9734.26 | 0 | 263431.79 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 9734.26 | 0 | 263431.79 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 9734.26 | 0 | 263431.79 | 0
G7CAS112 | Casing 112 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4266 | Casing 112 Line AM07 | 0 | 2018-10-22 | 43395 | Seiter | 0 | 0 | 9734.26 | 0 | 263431.79 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 0 | 0 | 241921.1 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 9637.88 | 0 | 9637.88 | 0 | 251558.98 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 9637.88 | 0 | 251558.98 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 9637.88 | 0 | 251558.98 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 9637.88 | 0 | 251558.98 | 0
G7CAS22 | AM07 Casing #22 Removal | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V4278 | Casing 22 Line AM07 | 0 | 2018-10-01 | 43398 | Seiter | 0 | 0 | 9637.88 | 0 | 251558.98 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 120150.39 | 0 | 120150.39 | 0 | 1832259.45 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | -141136.55 | 0 | -20986.16 | 0 | 1691122.9 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 4212.35 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | -16773.81 | 0 | 1695335.25 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7739 | Casing#42 abandon- AM07 & Hulbert | 0 | 2019-08-15 | 43692 | Seiter | 0 | 0 | 0 | 0 | 2009.27 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS42 | Casing #42 Line AM07 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS42 | Casing #42 Line AM07 | 0 | 2019-08-15 | 43707 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 83021.21 | 0 | 83021.21 | 0 | 7046103.92 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 0 | 0 | 614.63 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 159907.67 | 0 | 242928.88 | 0 | 7206011.59 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 1508.73 | 0 | 1508.73 | 0 | 2123.36 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 41742.12 | 0 | 284671 | 0 | 7247753.71 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 9.55 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 60429.96 | 0 | 345100.96 | 0 | 7308183.67 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | -17672.65 | 0 | 327428.31 | 0 | 7290511.02 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 41 | 0 | 327469.31 | 0 | 7290552.02 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 36319.18 | 0 | 363788.49 | 0 | 7326871.2 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | -11150.92 | 0 | 352637.57 | 0 | 7315720.28 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 352637.57 | 0 | 7315720.28 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 352637.57 | 0 | 7315720.28 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 352637.57 | 0 | 7315720.28 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 352637.57 | 0 | 7315720.28 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | V7902 | Casing #49 abandon - AM07 & I-75 | 0 | 2019-11-23 | 43829 | Seiter | 0 | 0 | 1518.28 | 0 | 2132.91 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS49 | Casing #49 Line AM07 I-71,75,275 | 0 | 2019-11-23 | 43860 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 0 | 0 | 86447.14 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 2348.92 | 0 | 2348.92 | 0 | 88796.06 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 2348.92 | 0 | 88796.06 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 2348.92 | 0 | 88796.06 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 2348.92 | 0 | 88796.06 | 0
G7CAS53 | Casing 53 Line AM07 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5417 | Casing 53 Line AM07 | 0 | 2018-12-01 | 43419 | Seiter | 0 | 0 | 2348.92 | 0 | 88796.06 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 11136.12 | 0 | 11136.12 | 0 | 11136.12 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 117.94 | 0 | 11254.06 | 0 | 11254.06 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 16.62 | 0 | 11270.68 | 0 | 11270.68 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | -41.4 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 0 | 0 | 0 | 0 | 400549.49 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7904 | Casing #717 Line AM07 -US RT 50 | 0 | 2019-05-21 | 43585 | Seiter | 9389.43 | 0 | 9389.43 | 0 | 409938.92 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8640 | Casing #717 LineAM074-USRT50 Land | 0 | 2019-05-21 | 44012 | Seiter | 0 | 0 | 11229.28 | 0 | 11229.28 | 0
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 130.65 | 0 | 130.65 | 0 | 130.65
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 131.11 | 0 | 261.76 | 0 | 261.76
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 131.56 | 0 | 393.32 | 0 | 393.32
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 132.02 | 0 | 525.34 | 0 | 525.34
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 132.48 | 0 | 657.82 | 0 | 657.82
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 128.51 | 0 | 786.33 | 0 | 786.33
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 0 | 0 | 786.33 | 0 | 786.33
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 0 | 0 | 786.33 | 0 | 786.33
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | -0.01 | 0 | 786.32 | 0 | 786.32
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 0 | 0 | 786.32 | 0 | 786.32
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 0 | 0 | 786.32 | 0 | 786.32
G7CAS717 | Casing #717 Line AM074 - US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS717 | Casing #717 Line AM074 - US RT 50 | 1902-02-24 07:41 | 2019-05-19 | 44012 | Seiter | 0 | 0 | 0 | 786.32 | 0 | 786.32
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 |  |  | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8637 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 809722.97 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7CAS718 | Casing #718 AM07C US RT 50 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CSNG-CASING & REMEDIATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7CAS718 | Casing #718 AM07C US RT 50 | 0 | 2019-09-06 | 43738 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 209849.52 | 0 | 209849.52 | 0 | 209849.52
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 219830.15 | 0 | 429679.67 | 0 | 429679.67
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 220879.93 | 0 | 650559.6 | 0 | 650559.6
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 221424.46 | 0 | 871984.06 | 0 | 871984.06
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 221737.18 | 0 | 1093721.24 | 0 | 1093721.24
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 222558.02 | 0 | 1316279.26 | 0 | 1316279.26
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 217756.22 | 0 | 1534035.48 | 0 | 1534035.48
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 224021.57 | 0 | 1758057.05 | 0 | 1758057.05
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 224887.32 | 0 | 1982944.37 | 0 | 1982944.37
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 225682.4 | 0 | 2208626.77 | 0 | 2208626.77
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 226446.26 | 0 | 2435073.03 | 0 | 2435073.03
G7DIMPOOL | DIMP Kentucky Pool | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DIMPOOL | DIMP Kentucky Pool | 2657000.95 |  | 46295 | Mitchell | 0 | 221927.92 | 0 | 2657000.95 | 0 | 2657000.95
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 25001.53 | 0 | 25001.53 | 0 | 25001.53
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 13177.78 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7DUDLEY | (Cancel) Dudley RD Reg Station | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7DUDLEY | (Cancel) Dudley RD Reg Station | 2004-07-11 07:26 |  | 43799 | Mitchell | 0 | 0 | 0 | 38179.31 | 0 | 38179.31
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 2154.92 | 0 | 2154.92 | 0 | 23020.44 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 6395.35 | 0 | 8550.27 | 0 | 29415.79 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 4131.38 | 0 | 12681.65 | 0 | 33547.17 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 1445.89 | 0 | 14127.54 | 0 | 34993.06 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 2604.3 | 0 | 16731.84 | 0 | 37597.36 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 1534.8 | 0 | 18266.64 | 0 | 39132.16 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 6563.96 | 0 | 24830.6 | 0 | 45696.12 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 43528.93 | 0 | 68359.53 | 0 | 89225.05 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 40535.85 | 0 | 108895.38 | 0 | 129760.9 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 25654.19 | 0 | 134549.57 | 0 | 155415.09 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 25156.69 | 0 | 159706.26 | 0 | 180571.78 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8967 | Erlanger Modular Complex | 0 |  | 44073 | Long | 24787.25 | 0 | 184493.51 | 0 | 205359.03 | 0
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 27483.85 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ECOMPLX | Erlanger Modular Complex | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ECOMPLX | Erlanger Modular Complex | 1975-03-30 20:24 |  | 44073 | Long | 0 | 0 | 0 | 27483.85 | 0 | 27483.85
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 96315.89 | 0 | 96315.89 | 0 | 96315.89
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 72863.63 | 0 | 169179.52 | 0 | 169179.52
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 36976.79 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7ELIJAH | (Cancel) Hebron System Capacity | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ELIJAH | (Cancel) Hebron System Capacity | 206156.31 |  | 43829 | Fritsch | 0 | 0 | 0 | 206156.31 | 0 | 206156.31
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 956.78 | 0 | 956.78 | 0 | 310993.89 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 467 | 0 | 1423.78 | 0 | 311460.89 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 709.35 | 0 | 2133.13 | 0 | 312170.24 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 464.99 | 0 | 2598.12 | 0 | 312635.23 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 5946.14 | 0 | 8544.26 | 0 | 318581.37 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 200.88 | 0 | 8745.14 | 0 | 318782.25 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 163.42 | 0 | 8908.56 | 0 | 318945.67 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | -5.27 | 0 | 8903.29 | 0 | 318940.4 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 0 | 0 | 8903.29 | 0 | 318940.4 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 0 | 0 | 8903.29 | 0 | 318940.4 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 0 | 0 | 8903.29 | 0 | 318940.4 | 0
G7EPROPAN | Erlanger OPP | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9131 | Erlanger OPP | 0 | 2020-07-31 | 43830 | Lawhead | 0 | 0 | 8903.29 | 0 | 318940.4 | 0
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 70816.24 | 0 | 70816.24 | 0 | 70816.24
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 46601.94 | 0 | 117418.18 | 0 | 117418.18
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 26348.07 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EPROPAN | Erlanger OPP | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EPROPAN | Erlanger OPP | 2293-08-12 06:00 | 2020-07-31 | 43830 | Long | 0 | 0 | 0 | 143766.25 | 0 | 143766.25
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 16688.16 | 0 | 16688.16 | 0 | 34021.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | -810 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7EQUIP | Kentucky Equipment | 75086 |  |  | TOOLS-TOOLS, EQUIPMENT & TRANSPORTATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V8884 | KET NGBU Equipment | 0 | 2019-11-30 | 43829 | Robson | 0 | 0 | 15878.16 | 0 | 33211.66 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 |  |  | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V2339 | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43434 | Mitchell | 0 | 0 | 0 | 0 | 194415.79 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLACPI | Erlangar OP Center Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLACPI | Erlangar OP Center Anodes | 0 | 2018-11-15 | 43373 | Mitchell | 0 | 0 | 0 | 0 | 0 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 37093.8 | 0 | 37093.8 | 0 | 37093.8 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 41617.6 | 0 | 78711.4 | 0 | 78711.4 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 58818.38 | 0 | 137529.78 | 0 | 137529.78 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 33251.77 | 0 | 170781.55 | 0 | 170781.55 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 8182.25 | 0 | 178963.8 | 0 | 178963.8 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 23403.16 | 0 | 202366.96 | 0 | 202366.96 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 139412.6 | 0 | 341779.56 | 0 | 341779.56 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 109224.68 | 0 | 451004.24 | 0 | 451004.24 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1656 | Erlanger Mag Anodes | 0 |  | 46295 | Gusler | 34974.7 | 0 | 485978.94 | 0 | 485978.94 | 0
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 28338.71 | 0 | 28338.71 | 0 | 28338.71
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29762.16 | 0 | 58100.87 | 0 | 58100.87
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29808.74 | 0 | 87909.61 | 0 | 87909.61
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29777.14 | 0 | 117686.75 | 0 | 117686.75
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29709.35 | 0 | 147396.1 | 0 | 147396.1
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29719.49 | 0 | 177115.59 | 0 | 177115.59
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 28862.59 | 0 | 205978.18 | 0 | 205978.18
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29711.1 | 0 | 235689.28 | 0 | 235689.28
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29726.97 | 0 | 265416.25 | 0 | 265416.25
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29731.49 | 0 | 295147.74 | 0 | 295147.74
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 29730.82 | 0 | 324878.56 | 0 | 324878.56
G7ERLCP | Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP | Erlanger Mag Anodes | 353794.13 |  | 46295 | Gusler | 0 | 28915.57 | 0 | 353794.13 | 0 | 353794.13
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 15197.26 | 0 | 15197.26 | 0 | 363000.61 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 20270.82 | 0 | 35468.08 | 0 | 383271.43 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 1013.04 | 0 | 36481.12 | 0 | 384284.47 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 573.02 | 0 | 37054.14 | 0 | 384857.49 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 407.58 | 0 | 37461.72 | 0 | 385265.07 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 56.76 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V9157 | 2019 Erlanger Ops Mag Anodes | 0 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 37518.48 | 0 | 385321.83 | 0
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 29149.56 | 0 | 29149.56 | 0 | 29149.56
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 16130.4 | 0 | 45279.96 | 0 | 45279.96
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 7065.22 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLCP19 | 2019 Erlanger Mag Anodes | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLCP19 | 2019 Erlanger Mag Anodes | 2043-04-24 04:19 | 2020-06-08 | 44012 | Gusler | 0 | 0 | 0 | 52345.18 | 0 | 52345.18
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 0 | 0 | 0 | 0 | 0
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 0 | 0 | 0 | 0 | 0
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 0 | 0 | 0 | 0 | 0
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 1475.8 | 0 | 1475.8 | 0 | 1475.8
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 1908.74 | 0 | 3384.54 | 0 | 3384.54
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 3083.07 | 0 | 6467.61 | 0 | 6467.61
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 10108.8 | 0 | 16576.41 | 0 | 16576.41
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 19958.24 | 0 | 36534.65 | 0 | 36534.65
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 20197.1 | 0 | 56731.75 | 0 | 56731.75
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 18883.42 | 0 | 75615.17 | 0 | 75615.17
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 4980.48 | 0 | 80595.65 | 0 | 80595.65
G7ERLNEW | Erlanger New Rectifier & Ground Bed | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLNEW | Erlanger New Rectifier & Ground Bed | 2125-07-29 09:50 |  | 44469 | Gusler | 0 | 1795.76 | 0 | 82391.41 | 0 | 82391.41
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLPLAN | Erlanger Propane Plant | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5155 | Erlanger Propane Plant Upgrades | 0 | 2019-04-01 | 43465 | Lawhead | 0 | 0 | 0 | 0 | 1029145.21 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 55998.88 | 0 | 55998.88 | 0 | 55998.88 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 82.55 | 0 | 56081.43 | 0 | 56081.43 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 82.83 | 0 | 56164.26 | 0 | 56164.26 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 58.91 | 0 | 56223.17 | 0 | 56223.17 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 8.2 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 0 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 2020-06-08 | 44104 | Gusler | 0 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 43990 | 44104 | Gusler | 0 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 43990 | 44104 | Gusler | 0 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 43990 | 44104 | Gusler | 0 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1547 | Erlanger Rectifier Remote Monitor I | 0 | 43990 | 44104 | Gusler | 0 | 0 | 56231.37 | 0 | 56231.37 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 0 | 0 | 0 | 0 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 0 | 0 | 0 | 0 | 0
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 987.24 | 0 | 987.24 | 0 | 987.24
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 1194.82 | 0 | 2182.06 | 0 | 2182.06
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 1859.82 | 0 | 4041.88 | 0 | 4041.88
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 4321.58 | 0 | 8363.46 | 0 | 8363.46
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 11103.51 | 0 | 19466.97 | 0 | 19466.97
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 12384.42 | 0 | 31851.39 | 0 | 31851.39
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 15331.76 | 0 | 47183.15 | 0 | 47183.15
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 10726.25 | 0 | 57909.4 | 0 | 57909.4
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 1951.96 | 0 | 59861.36 | 0 | 59861.36
G7ERLREC | Erlanger Rectifier Remote Monitor I | 75086 | Gas Ops - Corrosion | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERLREC | Erlanger Rectifier Remote Monitor I | 61084.69 | 43990 | 44104 | Gusler | 0 | 1223.33 | 0 | 61084.69 | 0 | 61084.69
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 21848.81 | 0 | 21848.81 | 0 | 21848.81
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23467.72 | 0 | 45316.53 | 0 | 45316.53
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23598.05 | 0 | 68914.58 | 0 | 68914.58
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23644.06 | 0 | 92558.64 | 0 | 92558.64
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23651.25 | 0 | 116209.89 | 0 | 116209.89
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23743 | 0 | 139952.89 | 0 | 139952.89
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 22897.43 | 0 | 162850.32 | 0 | 162850.32
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23896.29 | 0 | 186746.61 | 0 | 186746.61
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23995.01 | 0 | 210741.62 | 0 | 210741.62
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 24081.81 | 0 | 234823.43 | 0 | 234823.43
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 24163.28 | 0 | 258986.71 | 0 | 258986.71
G7ERPROPN | Erlanger Propane Pools | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7ERPROPN | Erlanger Propane Pools | 282350.89 |  | 46022 | Lawhead | 0 | 23364.18 | 0 | 282350.89 | 0 | 282350.89
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 0 | 0 | 301363.63 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 0 | 0 | 301363.63 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 17581.9 | 0 | 17581.9 | 0 | 318945.53 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 17581.9 | 0 | 318945.53 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 8178.78 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5625 | ECDA Line UL06 | 0 | 43451 | 43464 | Pace | 0 | 0 | 25760.68 | 0 | 327124.31 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL06 | ECDA Line UL06 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7EUL06 | ECDA Line UL06 | 0 | 43451 | 43399 | Pace | 0 | 0 | 0 | 0 | 0 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 0 | 0 | 988338.48 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 0 | 0 | 988338.48 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 0 | 0 | 988338.48 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 0 | 0 | 988338.48 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 956.89 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7EUL47 | Line UL47 scheduled digs | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V6391 | Line UL47 scheduled digs | 0 | 43448 | 43464 | Pace | 0 | 0 | 956.89 | 0 | 989295.37 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 46839.02 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | -1000.51 | 0 | -1000.51 | 0 | 45838.51 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | -1000.51 | 0 | 45838.51 | 0
G7FRAME | FRAME RELAY SCADA COMMUNICATION | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9421 | Frame Relay Kentucky | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | -1000.51 | 0 | 45838.51 | 0
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 3842.21 | 0 | 3842.21 | 0 | 3842.21
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 5307.32 | 0 | 9149.53 | 0 | 9149.53
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 7735.87 | 0 | 16885.4 | 0 | 16885.4
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 13339.09 | 0 | 30224.49 | 0 | 30224.49
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 28079.72 | 0 | 58304.21 | 0 | 58304.21
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 55607.98 | 0 | 113912.19 | 0 | 113912.19
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 94069.98 | 0 | 207982.17 | 0 | 207982.17
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 92936.59 | 0 | 300918.76 | 0 | 300918.76
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 131812.12 | 0 | 432730.88 | 0 | 432730.88
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 104174.43 | 0 | 536905.31 | 0 | 536905.31
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 38309.55 | 0 | 575214.86 | 0 | 575214.86
G7HICKSP | Hicks Pike looping | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7HICKSP | Hicks Pike looping | 583163.33 |  | 44135 | Fritsch | 0 | 7948.47 | 0 | 583163.33 | 0 | 583163.33
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 226 | 0 | 226 | 0 | 1073.42 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 7.95 | 0 | 7.95 | 0 | 4129.14 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 241.67 | 0 | 467.67 | 0 | 1315.09 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 7.96 | 0 | 15.91 | 0 | 4137.1 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 235.13 | 0 | 702.8 | 0 | 1550.22 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 8.24 | 0 | 24.15 | 0 | 4145.34 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 112.65 | 0 | 815.45 | 0 | 1662.87 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 8.53 | 0 | 32.68 | 0 | 4153.87 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 662.84 | 0 | 1478.29 | 0 | 2325.71 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 6.47 | 0 | 39.15 | 0 | 4160.34 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 696.73 | 0 | 2175.02 | 0 | 3022.44 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 4.29 | 0 | 43.44 | 0 | 4164.63 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 3972.88 | 0 | 6147.9 | 0 | 6995.32 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 4.67 | 0 | 48.11 | 0 | 4169.3 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 0 | 0 | 6147.9 | 0 | 6995.32 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 4.2 | 0 | 52.31 | 0 | 4173.5 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 337.91 | 0 | 6485.81 | 0 | 7333.23 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 3.22 | 0 | 55.53 | 0 | 4176.72 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 722.82 | 0 | 7208.63 | 0 | 8056.05 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 17499.94 | 0 | 17555.47 | 0 | 21676.66 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 0 | 0 | 7208.63 | 0 | 8056.05 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 58662.64 | 0 | 76218.11 | 0 | 80339.3 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GA70 | Duke Energy Kentucky - Gas | GAS OPERATIONS GA KEN | GAS OPERATIONS GA KEN | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 0 | 0 | 7208.63 | 0 | 8056.05 | 0
G7HMISTAT | HMI Work Station (Erlanger) | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0938 | HMI Work Station Erlanger | 0 |  | 44165 | Lawhead | 73.34 | 0 | 76291.45 | 0 | 80412.64 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | -9967.61 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | -1.7764e-15 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | -1848.08 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 139.83 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 0 | 0 | 1556888.95 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -5.1736e-13 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | -1.7764e-15 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 0 | 0 | 1556888.95 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -9.6545e-13 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 0 | 0 | 1556888.95 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -2.0464e-12 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 1.7764e-15 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 3691.66 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -4.0217e-12 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | -1.7764e-15 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | 1.8208e-13 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -9967.61 | 0 | 778800.1 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -6.5681e-13 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 4728.74 | 0 | -5238.87 | 0 | 783528.84 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -1.3642e-12 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -5238.87 | 0 | 783528.84 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | 2.2737e-12 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -5238.87 | 0 | 783528.84 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -5.1203e-13 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -5238.87 | 0 | 783528.84 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | -2.1529e-12 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K9112 | Install O2 and H2S Sensors at Foste | 0 | 42064 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 104936.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1996777 | AM07 Exposure-Horsebranch Rd. Segme | 0 | 43626 | 43677 | Kuisti | 0 | 0 | -5238.87 | 0 | 783528.84 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6468802 | AM07 Casing #46 Replacement | 0 | 43385 | 43374 | Seiter | 0 | 0 | 0 | 0 | 1945508.14 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6470695 | AM09 Casing 13223 REP | 0 |  | 43374 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6709 | Deep Well Erlanger Gas Plant | 0 | 41983 | 41939 | Shoemaker | 0 | 0 | 0 | 0 | 57841.52 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6754 | T/L AM07 - Install Corrosion Monito | 0 | 42200 | 42125 | Shoemaker | 0 | 0 | 0 | 0 | 56553.78 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6758 | T/L UL02 - Install Corrosion Monito | 0 | 41973 | 41973 | Shoemaker | 0 | 0 | 0 | 0 | 18430.48 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0964 | Replace Banklick Rd Station Inlet P | 0 | 42517 | 42531 | Shoemaker | 0 | 0 | 0 | 0 | 598248.63 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0978 | AM07 Pressure Test WP18 | 0 | 42924 | 42917 | Seiter | 0 | 0 | -1848.08 | 0 | 2772914.65 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 139.83 | 0 | 835629.45 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2898 | AM01 Exposed F/L Structure Install | 0 | 42310 | 42310 | Seiter | 0 | 0 | 0 | 0 | 203667.22 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4306 | AM07 Exposed T/L Project | 0 | 42317 | 42369 | Seiter | 0 | 0 | 0 | 0 | 17951.03 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4858 | AM-09 Segment 3700 Main Rpl | 0 | 42675 | 42628 | Seiter | 0 | 0 | 3691.66 | 0 | 1560580.61 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R9162 | INT 9146891 Henry Ct & US 27 | 0 | 42705 | 42765 | Seiter | 0 | 0 | 0 | 0 | 163166.89 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9414 | INT 11119187 AM04 Carntown | 0 |  | 43359 | Johnson | 0 | 0 | 0 | 0 | 1.4033e-13 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1525 | AM02 Exposed Main in Southgate, KY | 0 | 43336 | 43327 | Perkins | 0 | 0 | 0 | 0 | 868425.71 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7752 | AM07 Grey Stable Ln | 0 | 43174 | 43266 | Seiter | 0 | 0 | 0 | 0 | 179504.79 | 0
G7IMPRPL | INTEGRITY MANAGEMENT PROGRAM | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GFKY | Duke Energy Kentucky - Gas | Kentucky - Gas Field & Sys Ops | Kentucky - Gas Field & Sys Ops | R0981 | WP23 "AM07" Pressure Test | 0 | 42571 | 42613 | Seiter | 0 | 0 | 0 | 0 | 3293.3 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 1651.6 | 0 | 1651.6 | 0 | 1651.6 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 961.43 | 0 | 961.43 | 0 | 961.43 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 75410.04 | 0 | 77061.64 | 0 | 77061.64 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 37846.13 | 0 | 38807.56 | 0 | 38807.56 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 601.14 | 0 | 601.14 | 0 | 601.14 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 33563.13 | 0 | 110624.77 | 0 | 110624.77 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 443460.52 | 0 | 482268.08 | 0 | 482268.08 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 0 | 0 | 601.14 | 0 | 601.14 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 578374.7 | 0 | 688999.47 | 0 | 688999.47 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 94252.27 | 0 | 576520.35 | 0 | 576520.35 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 109.87 | 0 | 711.01 | 0 | 711.01 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 714.13 | 0 | 714.13 | 0 | 714.13 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 375389.17 | 0 | 1064388.64 | 0 | 1064388.64 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 244807.85 | 0 | 821328.2 | 0 | 821328.2 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 0 | 0 | 711.01 | 0 | 711.01 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 0 | 0 | 714.13 | 0 | 714.13 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 26262.32 | 0 | 1090650.96 | 0 | 1090650.96 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 2359.74 | 0 | 823687.94 | 0 | 823687.94 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 0 | 0 | 711.01 | 0 | 711.01 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 0 | 0 | 714.13 | 0 | 714.13 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 250677.86 | 0 | 1341328.82 | 0 | 1341328.82 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 923.72 | 0 | 824611.66 | 0 | 824611.66 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 0 | 0 | 711.01 | 0 | 711.01 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 0 | 0 | 714.13 | 0 | 714.13 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 39370.74 | 0 | 1380699.56 | 0 | 1380699.56 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 114.07 | 0 | 824725.73 | 0 | 824725.73 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 0 | 0 | 711.01 | 0 | 711.01 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 0 | 0 | 714.13 | 0 | 714.13 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 6642.38 | 0 | 1387341.94 | 0 | 1387341.94 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 11881.32 | 0 | 836607.05 | 0 | 836607.05 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2017 | Line UL06 Integrity Digs | 0 | 44109 | 44105 | Schuchter | 0 | 0 | 711.01 | 0 | 711.01 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 |  | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | AW2018 | Line UL47 Integrity Digs | 0 | 44021 | 44105 | Schuchter | 0 | 0 | 714.13 | 0 | 714.13 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 0 | 0 | 0 | 0 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 0 | 0 | 0 | 0 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 0 | 0 | 0 | 0 | 0
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 35549 | 0 | 35549 | 0 | 35549
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 35567.56 | 0 | 71116.56 | 0 | 71116.56
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 72083.89 | 0 | 143200.45 | 0 | 143200.45
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 69439.54 | 0 | 212639.99 | 0 | 212639.99
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 72549.61 | 0 | 285189.6 | 0 | 285189.6
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 72851.32 | 0 | 358040.92 | 0 | 358040.92
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 73115.8 | 0 | 431156.72 | 0 | 431156.72
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 1484.18 | 0 | 432640.9 | 0 | 432640.9
G7INTDIG | Integrity Digs Kentucky Pools | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7INTDIG | Integrity Digs Kentucky Pools | 434130.22 |  | 46387 | Schuchter | 0 | 1489.32 | 0 | 434130.22 | 0 | 434130.22
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 1930.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 263635.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 2.8866e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | -130.85 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | -121.21 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | -1018.97 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 31632.4 | 0 | 31632.4 | 0 | 249140.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 524028.31 | 0 | 524028.31 | 0 | 13688605.81 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 707.33 | 0 | 707.33 | 0 | 317362.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 0 | 0 | 0 | 0 | 36481.81 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 44.49 | 0 | 44.49 | 0 | 28105.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 63.33 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 203400.22 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 0 | 0 | 50410.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 4.4409e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 2939.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 2.1316e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | -1448.16 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 263635.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 384.34 | 0 | 32016.74 | 0 | 249525.1 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 9691.77 | 0 | 533720.08 | 0 | 13698297.58 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 3231.59 | 0 | 3938.92 | 0 | 320594.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 0 | 0 | 0 | 0 | 36481.81 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 48.58 | 0 | 93.07 | 0 | 28154.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | -2295.9 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 0 | 0 | 50410.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 5.3291e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | -152.4 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 3.6593e-13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 263635.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 5164.87 | 0 | 37181.61 | 0 | 254689.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 88.36 | 0 | 533808.44 | 0 | 13698385.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 223.72 | 0 | 4162.64 | 0 | 320817.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 16858.78 | 0 | 16858.78 | 0 | 53340.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 96.92 | 0 | 189.99 | 0 | 28251.23 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 0 | 0 | 50410.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 2.8422e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 3.6593e-13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 263635.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 2.8866e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 24329.5 | 0 | 61511.11 | 0 | 279019.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 533808.44 | 0 | 13698385.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | -14193.06 | 0 | -10030.42 | 0 | 306624.81 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 4315.53 | 0 | 21174.31 | 0 | 57656.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 71.35 | 0 | 261.34 | 0 | 28322.58 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 3284.85 | 0 | 3284.85 | 0 | 53695.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 8.8818e-16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 3.6593e-13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 263635.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 84529.89 | 0 | 146041 | 0 | 363549.36 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 371.25 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 3277.44 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 61.61 | 0 | 21235.92 | 0 | 57717.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 30.22 | 0 | 291.56 | 0 | 28352.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 56.69 | 0 | 3341.54 | 0 | 53752.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 3.6593e-13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 263635.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 2.8866e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 47504.78 | 0 | 193545.78 | 0 | 411054.14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 36.77 | 0 | 21272.69 | 0 | 57754.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 18.04 | 0 | 309.6 | 0 | 28370.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 1027.34 | 0 | 4368.88 | 0 | 54779.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -2.6645e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 2.8422e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 57685.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | -12437 | 0 | -12437 | 0 | 251198.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 2.8866e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 97608.25 | 0 | 291154.03 | 0 | 508662.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 29.91 | 0 | 21302.6 | 0 | 57784.41 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 14.67 | 0 | 324.27 | 0 | 28385.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 1395.6 | 0 | 5764.48 | 0 | 56175.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -4.4409e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 9840.88 | 0 | 9840.88 | 0 | 67526.72 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | -12437 | 0 | 251198.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 2.8866e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 5398.94 | 0 | 296552.97 | 0 | 514061.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 22.12 | 0 | 21324.72 | 0 | 57806.53 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 10.85 | 0 | 335.12 | 0 | 28396.36 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 5764.48 | 0 | 56175.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 8.8818e-16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 37253.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 72492.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 94083.13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 58618.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 9840.88 | 0 | 67526.72 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | -12437 | 0 | 251198.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | 0 | 0 | 13935.76 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 79351.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 23279.95 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 14304.48 | 0 | 310857.45 | 0 | 528365.81 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 16.75 | 0 | 21341.47 | 0 | 57823.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 8.21 | 0 | 343.33 | 0 | 28404.57 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 29650.96 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 236951.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 29635.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 67391.54 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 5764.48 | 0 | 56175.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 2.276e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 1.7764e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8625 | REG-9 IMPROVEMENTS/CWA | 0 | 38579 | 38579 | Shoemaker | -848.36 | 0 | -848.36 | 0 | -848.36 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | -5400.3 | 0 | -5400.3 | 0 | 31853.41 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | -1140.29 | 0 | -1140.29 | 0 | 71352.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | -856.3 | 0 | -856.3 | 0 | 93226.83 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | -3472.04 | 0 | -3472.04 | 0 | 55146.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 9840.88 | 0 | 67526.72 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | -12437 | 0 | 251198.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | -833.56 | 0 | -833.56 | 0 | 13102.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | -811.51 | 0 | -811.51 | 0 | 78539.77 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 2.8866e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | -692.76 | 0 | -692.76 | 0 | 22587.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 1865.98 | 0 | 312723.43 | 0 | 530231.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 0 | 0 | 21341.47 | 0 | 57823.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 0 | 0 | 343.33 | 0 | 28404.57 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | -827.74 | 0 | -827.74 | 0 | 28823.22 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | -15060.2 | 0 | -15060.2 | 0 | 221890.82 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | -422.66 | 0 | -422.66 | 0 | 29212.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | -960.33 | 0 | -960.33 | 0 | 66431.21 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 5764.48 | 0 | 56175.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -8.8818e-16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8625 | REG-9 IMPROVEMENTS/CWA | 0 | 38579 | 38579 | Shoemaker | 0 | 0 | -848.36 | 0 | -848.36 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | -5400.3 | 0 | 31853.41 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | -1140.29 | 0 | 71352.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | -856.3 | 0 | 93226.83 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | -3472.04 | 0 | 55146.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 9840.88 | 0 | 67526.72 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | -12437 | 0 | 251198.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | -833.56 | 0 | 13102.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | -811.51 | 0 | 78539.77 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | -692.76 | 0 | 22587.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 8225.48 | 0 | 320948.91 | 0 | 538457.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 0 | 0 | 21341.47 | 0 | 57823.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 0 | 0 | 343.33 | 0 | 28404.57 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | -827.74 | 0 | 28823.22 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | -15060.2 | 0 | 221890.82 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | -422.66 | 0 | 29212.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | -960.33 | 0 | 66431.21 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 5764.48 | 0 | 56175.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -2.6645e-15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | 2.1316e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 3.6593e-13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2812 | AMR REPL-KY/KEF | 0 | 38929 | 38929 |  | 0 | 0 | 0 | 0 | 20979.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8625 | REG-9 IMPROVEMENTS/CWA | 0 | 38579 | 38579 | Shoemaker | 0 | 0 | -848.36 | 0 | -848.36 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9217 | STA 745 INLET PIPING/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 20517.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9218 | STA 745-BROOKWOOD DR/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 34160.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1221 | STA 750 TURFWAY RD & 175/CWA | 0 | 38818 | 38818 |  | 0 | 0 | 0 | 0 | -3585.94 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5406 | RPL RTU AT PENDL/06-3513-6/DB | 0 | 38940 | 38940 |  | 0 | 0 | 0 | 0 | 6790.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5407 | RPL RTU-ALEX STA/06-3514-4/DB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 6393.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5408 | ERLANGER RPL EQUP/06-3515-1/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 1867.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5420 | INSTL ODOR MON/06-3518-5/DB | 0 | 38825 | 38825 |  | 0 | 0 | 0 | 0 | 13778.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5421 | INSTL ODOR MON/06-3519-3/DB | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 11520.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5448 | RPL EQUIP-3 MI/06-3509-4/DB | 0 | 38891 | 38891 |  | 0 | 0 | 0 | 0 | 20709.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5881 | INSTL MEAS EQUIP/06-3517-7/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 15919.26 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5882 | INSTL MEAS EQUIP/06-3516-9/DB | 0 | 39091 | 39091 |  | 0 | 0 | 0 | 0 | 18590.5 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6028 | FROGTOWN RD/PPWo 777314/KA | 0 | 38806 | 38806 |  | 0 | 0 | 0 | 0 | 6285.09 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6035 | STA 769-BROOKWOOD 06-3202-6/CA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 39868 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6393 | STA 745/CWA | 0 | 38897 | 38897 |  | 0 | 0 | 0 | 0 | -0.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7041 | STA 23 ABAN/REPLACEMENT/CWA | 0 | 38800 | 38800 |  | 0 | 0 | 0 | 0 | 1081.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7045 | STA 732 GUNPOWDER/DH | 0 | 40101 | 40101 |  | 0 | 0 | 0 | 0 | 14403.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7060 | STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 92744.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7341 | 343 WEAVER RD/PPW00812376/KGA | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 3745.02 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7552 | STA 770-GRAVEN & MAHER/CWA | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 47806.12 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7750 | STA 105 ABAN/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 3725.16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7752 | REG 107K-DUDLEY/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 28598.62 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8076 | STA 763-NICHOLSON/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 31365.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8358 | STA 776-MULLEN DR/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 27488.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8629 | STA 771-AOSTA VALLEY/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 35156.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9160 | FOSTER RTU/DZB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 55199.73 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9523 | PP864309/CWA | 0 | 39322 | 39322 | Shoemaker | 0 | 0 | 0 | 0 | 98742.44 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9571 | STA 781-NUNN & UNV/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -12979.98 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1231 | 897588/Chris Ampher | 0 | 39455 | 39455 | Shoemaker | 0 | 0 | 0 | 0 | 161560.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1889 | 07-3521-7/DZB | 0 | 39475 | 39475 |  | 0 | 0 | 0 | 0 | 5802.15 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3481 | STA 793-CAMP ERNST/CWA | 0 | 40141 | 40178 |  | 0 | 0 | 0 | 0 | 119115.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3747 | REG 112K-WATERWORKS/CWA | 0 | 39842 | 39994 | Shoemaker | 0 | 0 | -5400.3 | 0 | 31853.41 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0353 | Install Metretek Equip | 0 | 39743 | 40178 |  | 0 | 0 | 0 | 0 | 22416.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0472 | Sta 795 Sandman Dr | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | -1140.29 | 0 | 71352.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0838 | Sta 794 Shorland Drive | 0 | 39778 | 40058 |  | 0 | 0 | 0 | 0 | 62252.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1512 | Reg 113K-8th & Greenup | 0 | 39771 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 57673.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1514 | STA 796 - Longbranch Rd | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 73402.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2017 | AM3 Telemeter | 0 | 39832 | 40178 |  | 0 | 0 | 0 | 0 | 14757.47 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4533 | Reg 111K - 5th & Craig | 0 | 40155 | 40543 | Shoemaker | 0 | 0 | -856.3 | 0 | 93226.83 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4592 | Reg 108K - Hwy & David | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | -3472.04 | 0 | 55146.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4656 | Abandon System STA 58 | 0 | 40049 | 40574 | Shoemaker | 0 | 0 | 0 | 0 | 1240 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7332 | STA 535 - F/L UL33 to AM3 | 0 | 40073 | 40178 |  | 0 | 0 | 0 | 0 | 139335.56 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F2907 | STA 804 Lookaway Drive | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 9840.88 | 0 | 67526.72 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F4704 | STA 149 Gas Heater Removal | 0 | 40383 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 4800.45 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6526 | RTU cabinet at LaFarge | 0 | 40259 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 3680.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6547 | Install backup gener Three Mile | 0 | 40736 | 40909 | Shoemaker | 0 | 0 | 0 | 0 | 8684.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7286 | Radio Master Erlanger Tower | 0 | 41073 | 41075 | Shoemaker | 0 | 0 | 0 | 0 | 70626 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9125 | STA 806 - Grand Ave | 0 | 40844 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 98258.35 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9465 | Gas Control Router Upgrade KY | 0 | 40543 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 16541.67 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | -1448.16 | 0 | 482.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0446 | Reg 114K - Amsterdam Rd at Hamilton | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 129278.31 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1978 | STA 810 - Taylor Mill South | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 175994.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2041 | REG 55K Modifications Wright& Sprin | 0 | 40812 | 40817 | Shoemaker | 0 | 0 | 0 | 0 | 59759.8 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2537 | Rpl SCADA Radio Equip KY | 0 | 41258 | 41670 | Shoemaker | 0 | 0 | -12437 | 0 | 251198.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3136 | 1340 KY HWY 177E | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 5693.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3775 | Lafarge Install Cover-Meas STA 704 | 0 | 40806 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 779.71 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3790 | Rpl Transmitters KY | 0 | 41883 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 15258.52 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3792 | Rpl CDMA Radios for Telemeters KY | 0 | 41243 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 24402.65 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3997 | Reg 110K - Woodfill Ave @ US 27 | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 168938.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4281 | Ky Hwy 177 East | 0 | 40837 | 40897 | Shoemaker | 0 | 0 | 0 | 0 | 4527.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4494 | Replace generator at Foster Sta | 0 | 40765 | 40767 | Shoemaker | 0 | 0 | 0 | 0 | 2951.42 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6589 | Easement Dayton Valve house | 0 | 41121 | 40968 | Morris | 0 | 0 | 0 | 0 | 152.55 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6976 | Concrete Stairwell Rpl | 0 | 41122 | 41162 | Shoemaker | 0 | 0 | -833.56 | 0 | 13102.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7850 | Reg 109K - Main St @ Dixie Hwy | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 106237.85 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7851 | 4th & Saratogo (Rpl Reg 18K) | 0 | 41248 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 150529 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8248 | REG 116K - Holman and Watkins | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 227521.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8500 | STA 792 - Arcadia Dr | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 50215.91 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0264 | Reg 118K Inlet & Outlet Piping | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | -811.51 | 0 | 78539.77 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 206130.7 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0292 | STA 826 Old Taylor Mill | 0 |  | 41579 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0350 | STA 535K1 (UL33 to HP) Modification | 0 | 41963 | 42004 | Shoemaker | 0 | 0 | -692.76 | 0 | 22587.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0384 | Reg 117K-Amsterdam & Redwood | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 127536.84 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0485 | Reg 21K Improvements-Grand & Ft Tho | 0 | 41589 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166574.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573301 | REG 17 - FOOTE & FAIRFIELD DOWNSIZE | 0 | 43574 | 43510 | Hughes | 0 | 0 | -130.85 | 0 | 10607.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0573477 | REG 95 - BAUM & BURNET DOWNSIZE | 0 | 43566 | 43510 | Hughes | 0 | 0 | -121.21 | 0 | 9538.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0671045 | REG 101 - COVERT RUN & TAYLOR | 0 | 43673 | 43617 | Hughes | 0 | 0 | -1018.97 | 0 | 167819.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 775834.51 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217911 | STA 863 - GRANDVIEW ROAD | 0 | 43236 | 43465 | Seiter | 0 | 0 | 0 | 0 | 211172.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2218039 | INSTALL SCADA EQ-Three Mile Rd Sta | 0 | 43997 | 43931 | Brownstein | 90.84 | 0 | 321039.75 | 0 | 538548.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 534179.69 | 0 | 13698757.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336558 | STA 865 Southridge Dr | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 1019380.33 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2386654 | STA 901 - MARY GRUBBS | 0 | 43788 | 43736 | Hughes | 0 | 0 | -6752.98 | 0 | 309902.25 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6693835 | REGULATOR 412 - 9TH & OVERTON | 0 |  | 44196 | Hughes | 0 | 0 | 21341.47 | 0 | 57823.28 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6828172 | REG 420 BELAIR AND SPICEWOOD | 0 |  | 44196 | Smith | 0 | 0 | 343.33 | 0 | 28404.57 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7686017 | INSTALL SCADA EQUIPMENT | 0 | 43374 | 43374 | Brownstein | 0 | 0 | 0 | 0 | 6676.19 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8312879 | Install Odorant Flare Systems KY | 0 | 43465 | 43465 | Brownstein | 0 | 0 | 0 | 0 | 672.99 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8652267 | OAKLAND VALVE HOUSE SCADA INSTALL | 0 | 43672 | 43636 | Seiter | 0 | 0 | 0 | 0 | 18712.06 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8672523 | REG 119 BRISTOW AND RICHARDSON | 0 |  | 44043 | Smith | 0 | 0 | 63.33 | 0 | 40221.2 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9913996 | TO BE CANCELLED | 0 |  | 43435 | Hughes | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6323 | Install Mercaptan Meas at Alexandri | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 24522.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6324 | Install Mercaptan Meas at Cold Spri | 0 | 42125 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 14642.29 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7147 | 4455 Olympic Blvd | 0 | 41865 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 5107.24 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7279 | Rossford Avenue (STA #101) | 0 | 42641 | 42597 | Shoemaker | 0 | 0 | 0 | 0 | 266143.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9838 | Erlanger STA 149 | 0 | 42292 | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 502550.61 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9751 | STA 149 Hydro Test of AM07 | 0 | 42292 | 42278 | Shoemaker | 0 | 0 | 0 | 0 | 469587.59 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | -827.74 | 0 | 28823.22 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 476472.11 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3460 | Station 577 (Ky-17 & US-27) | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | -15060.2 | 0 | 221890.82 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8822 | STA 10055288 Waits & Kellogg | 0 |  | 42767 | Davis | 0 | 0 | 0 | 0 | 176.97 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1094 | STA 249: Three Mile - Station | 0 | 42690 | 43769 | Perkins | 0 | 0 | 0 | 0 | 606053.48 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7437 | STA 10565374 Foster Station | 0 | 42622 | 42735 | Smith | 0 | 0 | 0 | 0 | 71521.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7568 | STA 822 Cox Rd Outlet | 0 | 42746 | 42767 | Smith | 0 | 0 | -422.66 | 0 | 29212.37 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7572 | STA 822 Cox Rd Inlet | 0 | 42746 | 42767 | Smith | 0 | 0 | -960.33 | 0 | 66431.21 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8250 | STA 822 Cox Rd - Station | 0 | 42746 | 42767 | Smith | 0 | 0 | 0 | 0 | 162626.79 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 8286.74 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0425 | SCAD 11456765 Mineola Pike Sta | 0 | 43130 | 43343 | Smith | 0 | 0 | 0 | 0 | 22540.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0645 | STA 839 Richwood Station | 0 | 43225 | 43371 | Perkins | 0 | 0 | 0 | 0 | 359063.03 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0646 | STA 835 Walton - Station | 0 | 43257 | 43313 | Perkins | 0 | 0 | 0 | 0 | 491020.88 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0746 | AM00a Automation of RCV Cold Spring | 0 | 43377 | 43343 | Perkins | 0 | 0 | 0 | 0 | 310927.87 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1465 | STA 855 Taylor Mill Rd - Station | 0 | 43124 | 43119 | Perkins | 0 | 0 | -2295.9 | 0 | 201104.32 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1485 | STA 855 Taylor Mill Rd - Inlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 60255.01 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1486 | STA 855 Taylor Mill Rd - Outlet | 0 | 43124 | 43119 | Perkins | 0 | 0 | 0 | 0 | 30664.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2218 | STA 838 Mineola Pike - Outlet | 0 | 43053 | 43248 | Perkins | 0 | 0 | 0 | 0 | 44764.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4002 | STA 20933317 Erlanger CP | 0 |  | 43342 | Shoemaker | 0 | 0 | 0 | 0 | 2355.69 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T4893 | Mineola Pike STA Meter Rep & Panels | 0 | 43283 | 43342 | Perkins | 0 | 0 | 0 | 0 | 42627.07 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T5473 | SCAD 21012299 Pressure Transmiitter | 0 | 42916 | 43313 | Reynolds | 0 | 0 | 5764.48 | 0 | 56175.27 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7778 | cancel-SCAD 21153712 KY | 0 |  | 43188 | Reynolds | 0 | 0 | 0 | 0 | 1027.64 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7966 | STA 859 Banklick Rd - Station | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 281178.39 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8405 | WALTON-NICHOLS AM03 RCV Valve | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -3.8858e-16 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | -152.4 | 0 | 2786.93 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | 15.92 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | R2901 | STA 838 Mineola Pike - Station | 0 | 43053 | 43133 | Perkins | 0 | 0 | 0 | 0 | 187.05 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G0224 | Cancel STA 809 - Waterworks Rd- Sta | 0 |  | 43282 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0265 | Reg 118K Installation | 0 | 42302 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1715658 | STA 809 - WATERWORKS RD - Station | 0 | 43259 | 43465 | Seiter | 0 | 0 | 0 | 0 | -2.08 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2335804 | STA 872 - OAKLAND VALVE HOUSE | 0 | 43637 | 43615 | Seiter | 0 | 0 | 0 | 0 | 60.4 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | R2900 | Cox Rd Station Rpl | 0 | 42746 | 42767 | Shoemaker | 0 | 0 | 0 | 0 | -2.1316e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S9586 | STA 11212247 Erlanger Compressor | 0 | 42704 | 43373 | Smith | 0 | 0 | 0 | 0 | 3.6593e-13 | 0
G7LGMR | LARGE M&R S Pools | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T9338 | Cancel STA 809 Waterworks Dr - Sta | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 29923.25 | 0 | 29923.25 | 0 | 29923.25
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 60543.77 | 0 | 60543.77
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 91164.29 | 0 | 91164.29
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 121784.81 | 0 | 121784.81
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 61241.03 | 0 | 183025.84 | 0 | 183025.84
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 61241.03 | 0 | 244266.87 | 0 | 244266.87
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 61241.03 | 0 | 305507.9 | 0 | 305507.9
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 61241.03 | 0 | 366748.93 | 0 | 366748.93
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 397369.45 | 0 | 397369.45
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 427989.97 | 0 | 427989.97
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 458610.49 | 0 | 458610.49
G7LGMR | LARGE M&R S Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LGMR | LARGE M&R S Pools | 489231.01 |  | 55153 | Casstevens | 0 | 30620.52 | 0 | 489231.01 | 0 | 489231.01
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 886748.24 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 11.25 | 0 | 11.25 | 0 | 886759.49 | 0
G7LNLP03 | Line LP03 | 75086 |  | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5652 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 11.25 | 0 | 886759.49 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNLP03 | Line LP03 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNLP03 | Line LP03 | 0 | 43419 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 1907.56 | 0 | 1907.56 | 0 | 1907.56 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 5753.92 | 0 | 7661.48 | 0 | 7661.48 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 11953.93 | 0 | 19615.41 | 0 | 19615.41 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 19742.17 | 0 | 39357.58 | 0 | 39357.58 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 14598.3 | 0 | 53955.88 | 0 | 53955.88 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 190314.16 | 0 | 244270.04 | 0 | 244270.04 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 656212.96 | 0 | 900483 | 0 | 900483 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 121532.82 | 0 | 1022015.82 | 0 | 1022015.82 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 2369.2 | 0 | 1024385.02 | 0 | 1024385.02 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 |  | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW0832 | Line UL57 monolithic insulators | 0 | 44077 | 44104 | Schuchter | 2291.45 | 0 | 1026676.47 | 0 | 1026676.47 | 0
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 28832.58 | 0 | 28832.58 | 0 | 28832.58
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 21239.07 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LNUL57 | Line UL57 monolithic insulators | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | CORR-CORROSION CONTROL | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LNUL57 | Line UL57 monolithic insulators | 50071.65 | 44077 | 44104 | Schuchter | 0 | 0 | 0 | 50071.65 | 0 | 50071.65
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | 0 | 0 | 11.25 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | -11.25 | 0 | -11.25 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LP3LAND | Cancel Emergency Line LP-3 (LAND) | 0 | 43341 | 43342 | Olberding | 0 | 0 | -11.25 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | U8785 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 8686725.64 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LP3 | Emergency Line LP-3 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7LP3 | Emergency Line LP-3 | 0 | 43420 | 43434 | Olberding | 0 | 0 | 0 | 0 | 0 | 0
G7LUL02 | Line UL02 - MAOP Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2880 | Line UL02 - MAOP Replacement | 0 |  | 44561 | Klein | 2734.94 | 0 | 2734.94 | 0 | 2734.94 | 0
G7LUL02 | Line UL02 - MAOP Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2880 | Line UL02 - MAOP Replacement | 0 |  | 44561 | Klein | 5496.43 | 0 | 8231.37 | 0 | 8231.37 | 0
G7LUL02 | Line UL02 - MAOP Replacement | 75086 |  |  | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW2880 | Line UL02 - MAOP Replacement | 0 |  | 44561 | Klein | 13078.79 | 0 | 21310.16 | 0 | 21310.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -1734 | -769887.31 | -1734
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 7.1054e-15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 45880.26 | 0 | 45880.26 | 0 | 3011300.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 636.92 | 0 | 636.92 | 0 | 404642.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 428.45 | 0 | 428.45 | 0 | 272262.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 10833.47 | 0 | 10833.47 | 0 | 323804.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 796.79 | 0 | 796.79 | 0 | 16521.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 114.97 | 0 | 114.97 | 0 | 72874.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 291.42 | 0 | 291.42 | 0 | 38618.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 194.78 | 0 | 194.78 | 0 | 32784.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 30151.17 | 0 | 30151.17 | 0 | 300220.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 541.54 | 0 | 541.54 | 0 | 253805.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 52592.18 | 0 | 52592.18 | 0 | 308626.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 1991.91 | 0 | 1991.91 | 0 | 27502.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 57.4 | 0 | 57.4 | 0 | 36528.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 14953.43 | 0 | 14953.43 | 0 | 228269.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | -440683.56 | 0 | -440683.56 | 0 | 3.9563e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | -83344.75 | 0 | -83344.75 | 0 | 371.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 49.9 | 0 | 49.9 | 0 | 31766.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 69463.15 | 0 | 69463.15 | 0 | 155171.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 82851.59 | 0 | 82851.59 | 0 | 129089.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 34370.68 | 0 | 34370.68 | 0 | 39178.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 317.16 | 0 | 317.16 | 0 | 55026.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 173.43 | 0 | 173.43 | 0 | 5464.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | -525.3 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 665.54 | 0 | 665.54 | 0 | 50658.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 253.39 | 0 | 253.39 | 0 | 14326.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 497.18 | 0 | 497.18 | 0 | 17534.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 235.95 | 0 | 235.95 | 0 | 4472.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 1060.66 | 0 | 1060.66 | 0 | 2921.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 791.53 | 0 | 791.53 | 0 | 2966.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 523.97 | 0 | 523.97 | 0 | 523.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 785.06 | 0 | 785.06 | 0 | 5445.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 10.66 | 0 | 10.66 | 0 | 6816.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 156.61 | 0 | 156.61 | 0 | 98919.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 3279.12 | 0 | 3279.12 | 0 | 3279.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -3468 | -769887.31 | -3468
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 29206.86 | 0 | 75087.12 | 0 | 3040507.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 837.82 | 0 | 1474.74 | 0 | 405480.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 409.96 | 0 | 838.41 | 0 | 272672.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 14842.34 | 0 | 25675.81 | 0 | 338647.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 231.55 | 0 | 1028.34 | 0 | 16753.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 110.01 | 0 | 224.98 | 0 | 72984.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 2815.83 | 0 | 3107.25 | 0 | 41434.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 49.32 | 0 | 244.1 | 0 | 32834.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 40624.09 | 0 | 70775.26 | 0 | 340844.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 381.12 | 0 | 922.66 | 0 | 254186.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 74622.29 | 0 | 127214.47 | 0 | 383249.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 8329.66 | 0 | 8329.66 | 0 | 8329.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 41.32 | 0 | 2033.23 | 0 | 27544.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 54.92 | 0 | 112.32 | 0 | 36583.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 1270.37 | 0 | 16223.8 | 0 | 229539.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | -7.6739e-13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83344.75 | 0 | 371.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 47.75 | 0 | 97.65 | 0 | 31813.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 20984.65 | 0 | 90447.8 | 0 | 176155.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 9858.41 | 0 | 92710 | 0 | 138947.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 9763.72 | 0 | 44134.4 | 0 | 48942.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 212.83 | 0 | 529.99 | 0 | 55239.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 8.18 | 0 | 181.61 | 0 | 5473.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | -1688.33 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | -26.84 | 0 | 226.55 | 0 | 14299.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 104989.74 | 0 | 105486.92 | 0 | 122524.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 39717.89 | 0 | 39953.84 | 0 | 44190.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 6072.22 | 0 | 7132.88 | 0 | 8993.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 162.82 | 0 | 162.82 | 0 | 162.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 4.44 | 0 | 795.97 | 0 | 2970.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 11668.32 | 0 | 12192.29 | 0 | 12192.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 9752.18 | 0 | 9752.18 | 0 | 9752.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 244.23 | 0 | 244.23 | 0 | 244.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | -390.37 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 10.2 | 0 | 20.86 | 0 | 6826.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 149.85 | 0 | 306.46 | 0 | 99069.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 13226.82 | 0 | 16505.94 | 0 | 16505.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -5202 | -769887.31 | -5202
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 3.5527e-15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 120167 | 0 | 195254.12 | 0 | 3160674.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 606.76 | 0 | 2081.5 | 0 | 406086.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 406.53 | 0 | 1244.94 | 0 | 273078.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 7271.03 | 0 | 32946.84 | 0 | 345918.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | -2025.86 | 0 | -997.52 | 0 | 14727.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 109.09 | 0 | 334.07 | 0 | 73093.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 89.22 | 0 | 3196.47 | 0 | 41523.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 51.44 | 0 | 295.54 | 0 | 32885.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 5274.81 | 0 | 76050.07 | 0 | 346119.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 380.47 | 0 | 1303.13 | 0 | 254566.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 31148.33 | 0 | 158362.8 | 0 | 414397.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 41812.24 | 0 | 50141.9 | 0 | 50141.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 96.79 | 0 | 2130.02 | 0 | 27640.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 54.46 | 0 | 166.78 | 0 | 36638.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 777.51 | 0 | 17001.31 | 0 | 230316.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | -1.254e-10 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83344.75 | 0 | 371.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 47.35 | 0 | 145 | 0 | 31861.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 6568.8 | 0 | 97016.6 | 0 | 182724.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 12638.1 | 0 | 105348.1 | 0 | 151585.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 702.38 | 0 | 44836.78 | 0 | 49644.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 164.06 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 8.12 | 0 | 189.73 | 0 | 5481.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 4531.38 | 0 | 4531.38 | 0 | 4531.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 2.68 | 0 | 229.23 | 0 | 14301.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 71830.43 | 0 | 177317.35 | 0 | 194355.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 42028.46 | 0 | 81982.3 | 0 | 86218.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 8570.32 | 0 | 15703.2 | 0 | 17564.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 12891.22 | 0 | 13054.04 | 0 | 13054.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 268.86 | 0 | 1064.83 | 0 | 3239.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 160.26 | 0 | 12352.55 | 0 | 12352.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 185.1 | 0 | 9937.28 | 0 | 9937.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 6397.29 | 0 | 6641.52 | 0 | 6641.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 295.62 | 0 | 295.62 | 0 | 295.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 81370.45 | 0 | 81370.45 | 0 | 81370.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 10.11 | 0 | 30.97 | 0 | 6837.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 148.59 | 0 | 455.05 | 0 | 99218.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 11860.32 | 0 | 28366.26 | 0 | 28366.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -6936 | -769887.31 | -6936
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 61002.12 | 0 | 256256.24 | 0 | 3221676.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 606.69 | 0 | 2688.19 | 0 | 406693.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 407.88 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 718.43 | 0 | 33665.27 | 0 | 346636.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 521.92 | 0 | -475.6 | 0 | 15249.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 109.45 | 0 | 443.52 | 0 | 73202.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | -50.13 | 0 | 3146.34 | 0 | 41473.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 1215.22 | 0 | 1510.76 | 0 | 34100.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 26104.65 | 0 | 102154.72 | 0 | 372224.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 379.19 | 0 | 1682.32 | 0 | 254946.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 20050 | 0 | 178412.8 | 0 | 434447.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 6494.53 | 0 | 56636.43 | 0 | 56636.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 41.2 | 0 | 2171.22 | 0 | 27682.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 54.64 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 5353.83 | 0 | 22355.14 | 0 | 235670.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | 1.0937e-10 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83344.75 | 0 | 371.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 47.51 | 0 | 192.51 | 0 | 31908.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 8094 | 0 | 105110.6 | 0 | 190818.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | -2027.72 | 0 | 103320.38 | 0 | 149558.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 163.66 | 0 | 45000.44 | 0 | 49808.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 8.14 | 0 | 197.87 | 0 | 5489.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 6.68 | 0 | 4538.06 | 0 | 4538.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 85.63 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 4537.39 | 0 | 181854.74 | 0 | 198892.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 4933.85 | 0 | 86916.15 | 0 | 91152.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 15703.2 | 0 | 17564.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 19.26 | 0 | 13073.3 | 0 | 13073.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 4.81 | 0 | 1069.64 | 0 | 3244.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 18.24 | 0 | 12370.79 | 0 | 12370.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | -1839.23 | 0 | 8098.05 | 0 | 8098.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 4567.97 | 0 | 11209.49 | 0 | 11209.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0.44 | 0 | 296.06 | 0 | 296.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 100922.54 | 0 | 182292.99 | 0 | 182292.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 70.33 | 0 | 101.3 | 0 | 6907.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 149.09 | 0 | 604.14 | 0 | 99367.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 17101.83 | 0 | 45468.09 | 0 | 45468.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -8670 | -769887.31 | -8670
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 38977.82 | 0 | 295234.06 | 0 | 3260653.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 431.53 | 0 | 3119.72 | 0 | 407125.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 25290.76 | 0 | 58956.03 | 0 | 371927.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 145.05 | 0 | -330.55 | 0 | 15394.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 77.85 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 224.93 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 36.12 | 0 | 1546.88 | 0 | 34136.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 2556.9 | 0 | 104711.62 | 0 | 374781.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 269.71 | 0 | 1952.03 | 0 | 255215.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 10318.24 | 0 | 188731.04 | 0 | 444765.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 293554.43 | 0 | 350190.86 | 0 | 350190.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 29.3 | 0 | 2200.52 | 0 | 27711.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 958.92 | 0 | 23314.06 | 0 | 236629.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | 7.0827e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | -371.25 | 0 | -83716 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 33.79 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 647.56 | 0 | 105758.16 | 0 | 191466.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | -3101.07 | 0 | 100219.31 | 0 | 146457.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 1986.9 | 0 | 46987.34 | 0 | 51795.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 5.79 | 0 | 203.66 | 0 | 5495.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 4.75 | 0 | 4542.81 | 0 | 4542.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 10709.43 | 0 | 192564.17 | 0 | 209601.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 2067.66 | 0 | 88983.81 | 0 | 93220.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 1153.42 | 0 | 16856.62 | 0 | 18717.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 26563.63 | 0 | 39636.93 | 0 | 39636.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 3.42 | 0 | 1073.06 | 0 | 3247.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | -282.8 | 0 | 12087.99 | 0 | 12087.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | -2247.62 | 0 | 5850.43 | 0 | 5850.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 49329.34 | 0 | 60538.83 | 0 | 60538.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0.31 | 0 | 296.37 | 0 | 296.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 327526.04 | 0 | 509819.03 | 0 | 509819.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 3872.78 | 0 | 3872.78 | 0 | 3872.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 3246.82 | 0 | 3246.82 | 0 | 3246.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | -3370.49 | 0 | -3269.19 | 0 | 3536.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 106.04 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 85880.2 | 0 | 131348.29 | 0 | 131348.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -10404 | -769887.31 | -10404
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 3.5527e-15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 75117.17 | 0 | 370351.23 | 0 | 3335771.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 257.53 | 0 | 3377.25 | 0 | 407382.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | -24064.8 | 0 | 34891.23 | 0 | 347862.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 9.71 | 0 | -320.84 | 0 | 15404.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 21.56 | 0 | 1568.44 | 0 | 34158.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 320.41 | 0 | 105032.03 | 0 | 375101.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 160.96 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 2568.31 | 0 | 191299.35 | 0 | 447334.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 148794.03 | 0 | 498984.89 | 0 | 498984.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 17.49 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 277.31 | 0 | 23591.37 | 0 | 236907 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | -8.5834e-12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | -9.3792e-13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 128.17 | 0 | 105886.33 | 0 | 191594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 128.17 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 0 | 0 | 46987.34 | 0 | 51795.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 3.46 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | -1086.69 | 0 | 3456.12 | 0 | 3456.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 64.07 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 624.11 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | -160.25 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 60132.23 | 0 | 99769.16 | 0 | 99769.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 2.04 | 0 | 1075.1 | 0 | 3249.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 3996.34 | 0 | 16084.33 | 0 | 16084.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 1086.9 | 0 | 6937.33 | 0 | 6937.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | 15242.81 | 0 | 15242.81 | 0 | 15242.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 1538.31 | 0 | 62077.14 | 0 | 62077.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0.19 | 0 | 296.56 | 0 | 296.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 252.57 | 0 | 252.57 | 0 | 252.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 88212.93 | 0 | 598031.96 | 0 | 598031.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 5588.75 | 0 | 9461.53 | 0 | 9461.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | 252.57 | 0 | 252.57 | 0 | 252.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 18400.27 | 0 | 21647.09 | 0 | 21647.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 16578.18 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 3838.47 | 0 | 135186.76 | 0 | 135186.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -12138 | -769887.31 | -12138
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 1.4211e-14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 34480.46 | 0 | 404831.69 | 0 | 3370251.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 209.5 | 0 | 3586.75 | 0 | 407592.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 249.48 | 0 | 35140.71 | 0 | 348112.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 217.03 | 0 | -103.81 | 0 | 15621.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 17.54 | 0 | 1585.98 | 0 | 34176 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 1914.19 | 0 | 106946.22 | 0 | 377015.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 0 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 1352.65 | 0 | 192652 | 0 | 448686.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 75465.35 | 0 | 574450.24 | 0 | 574450.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 0 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 121.36 | 0 | 23712.73 | 0 | 237028.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | 7.6369e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | 8.7397e-13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 0 | 0 | 105886.33 | 0 | 191594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 0 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 127.09 | 0 | 47114.43 | 0 | 51922.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 0 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 5737.47 | 0 | 9193.59 | 0 | 9193.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 0 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 0 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 2870.99 | 0 | 102640.15 | 0 | 102640.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 1.66 | 0 | 1076.76 | 0 | 3251.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 21780.08 | 0 | 37864.41 | 0 | 37864.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | -125.9 | 0 | 6811.43 | 0 | 6811.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | 3199.49 | 0 | 18442.3 | 0 | 18442.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 4177.16 | 0 | 66254.3 | 0 | 66254.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0.15 | 0 | 296.71 | 0 | 296.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 14290.77 | 0 | 14543.34 | 0 | 14543.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 111204.02 | 0 | 709235.98 | 0 | 709235.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 71869.79 | 0 | 81331.32 | 0 | 81331.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | 8965.39 | 0 | 9217.96 | 0 | 9217.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6243694 | ~400 FT MEA; DOLWICK DR | 0 | 44203 | 44071 | Shelton | 6207.25 | 0 | 6207.25 | 0 | 6207.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 161790.45 | 0 | 183437.54 | 0 | 183437.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 0 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 7263.47 | 0 | 142450.23 | 0 | 142450.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -13872 | -769887.31 | -13872
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 1.4211e-14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 71833.89 | 0 | 476665.58 | 0 | 3442085.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 0 | 0 | 3586.75 | 0 | 407592.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 16972.41 | 0 | 52113.12 | 0 | 365084.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 5.92 | 0 | -97.89 | 0 | 15627.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 12.97 | 0 | 1598.95 | 0 | 34188.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 10539.3 | 0 | 117485.52 | 0 | 387555.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 0 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 4715.84 | 0 | 197367.84 | 0 | 453402.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | -652.28 | 0 | 573797.96 | 0 | 573797.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 0 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 89.77 | 0 | 23802.5 | 0 | 237118.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | 9.0267e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | 1.08e-12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 189.36 | 0 | 106075.69 | 0 | 191783.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 0 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 0 | 0 | 47114.43 | 0 | 51922.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 0 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 0 | 0 | 9193.59 | 0 | 9193.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 0 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 0 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 11861.66 | 0 | 114501.81 | 0 | 114501.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 1.23 | 0 | 1077.99 | 0 | 3252.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | -920.49 | 0 | 36943.92 | 0 | 36943.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 22.99 | 0 | 6834.42 | 0 | 6834.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | 653.97 | 0 | 19096.27 | 0 | 19096.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 794.23 | 0 | 67048.53 | 0 | 67048.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0.11 | 0 | 296.82 | 0 | 296.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 3533.51 | 0 | 18076.85 | 0 | 18076.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 1023.13 | 0 | 710259.11 | 0 | 710259.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 12593.69 | 0 | 93925.01 | 0 | 93925.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | 30201.18 | 0 | 39419.14 | 0 | 39419.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 0 | 44131 | 44092 | Shelton | 1878.99 | 0 | 1878.99 | 0 | 1878.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6243694 | ~400 FT MEA; DOLWICK DR | 0 | 44203 | 44071 | Shelton | 2.32 | 0 | 6209.57 | 0 | 6209.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6842755 | MAIN EXTENSION AARON DR-85 FT 2 IN- | 0 | 44090 | 44057 | Shelton | 4578.97 | 0 | 4578.97 | 0 | 4578.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 27535.11 | 0 | 210972.65 | 0 | 210972.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7078370 | CANCEL INVESTMENT WAY MEA | 0 |  | 44104 | Shelton | 843.13 | 0 | 843.13 | 0 | 843.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 0 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 784.03 | 0 | 143234.26 | 0 | 143234.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -15606 | -769887.31 | -15606
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6594.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | -3.5527e-15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 53597.86 | 0 | 530263.44 | 0 | 3495683.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 0 | 0 | 3586.75 | 0 | 407592.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 104.45 | 0 | 52217.57 | 0 | 365188.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602140 | FARM TAP PROJ; ENZWEILER RD | 0 |  | 44396 | Shelton | 1143.6 | 0 | 1143.6 | 0 | 1143.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 59.46 | 0 | -38.43 | 0 | 15686.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 9.82 | 0 | 1608.77 | 0 | 34198.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 0 | 0 | 117485.52 | 0 | 387555.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 0 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | -167.01 | 0 | 197200.83 | 0 | 453235.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1957438 | FARM TAP PROJ; GRANDVIEW RD | 0 |  | 44379 | Hacker | 25627.74 | 0 | 25627.74 | 0 | 25627.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 264.17 | 0 | 574062.13 | 0 | 574062.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 0 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 67.95 | 0 | 23870.45 | 0 | 237186.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | -5.457e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | 3.9151e-12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 0 | 0 | 106075.69 | 0 | 191783.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 0 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 0 | 0 | 47114.43 | 0 | 51922.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 0 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 0 | 0 | 9193.59 | 0 | 9193.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 0 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 0 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 2003.16 | 0 | 116504.97 | 0 | 116504.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 0 | 0 | 1077.99 | 0 | 3252.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 10.48 | 0 | 36954.4 | 0 | 36954.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 0 | 0 | 6834.42 | 0 | 6834.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | 133699.3 | 0 | 152795.57 | 0 | 152795.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 0 | 0 | 67048.53 | 0 | 67048.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0 | 0 | 296.82 | 0 | 296.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 17594.08 | 0 | 35670.93 | 0 | 35670.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 229266.66 | 0 | 939525.77 | 0 | 939525.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 1668.94 | 0 | 95593.95 | 0 | 95593.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | 1279.82 | 0 | 40698.96 | 0 | 40698.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 0 | 44131 | 44092 | Shelton | 4419.64 | 0 | 6298.63 | 0 | 6298.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6243694 | ~400 FT MEA; DOLWICK DR | 0 | 44203 | 44071 | Shelton | 1.76 | 0 | 6211.33 | 0 | 6211.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6245365 | ~425 FT MEA; SARAH LN | 0 | 44147 | 44134 | Shelton | 4421.41 | 0 | 4421.41 | 0 | 4421.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6842755 | MAIN EXTENSION AARON DR-85 FT 2 IN- | 0 | 44090 | 44057 | Shelton | 128.02 | 0 | 4706.99 | 0 | 4706.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 3128.26 | 0 | 214100.91 | 0 | 214100.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7078370 | CANCEL INVESTMENT WAY MEA | 0 |  | 44104 | Shelton | 1984.17 | 0 | 2827.3 | 0 | 2827.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 0 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 0 | 0 | 143234.26 | 0 | 143234.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -17340 | -769887.31 | -17340
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | -242.16 | 0 | -242.16 | 0 | 6352.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 7.1054e-15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 72005.1 | 0 | 602268.54 | 0 | 3567688.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 0 | 0 | 3586.75 | 0 | 407592.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 247.91 | 0 | 52465.48 | 0 | 365436.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602140 | FARM TAP PROJ; ENZWEILER RD | 0 |  | 44396 | Shelton | 1799.88 | 0 | 2943.48 | 0 | 2943.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 10.68 | 0 | -27.75 | 0 | 15697.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 0 | 0 | 1608.77 | 0 | 34198.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 0 | 0 | 117485.52 | 0 | 387555.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 0 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 30943.46 | 0 | 228144.29 | 0 | 484178.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1957438 | FARM TAP PROJ; GRANDVIEW RD | 0 |  | 44379 | Hacker | 25585.61 | 0 | 51213.35 | 0 | 51213.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 386.14 | 0 | 574448.27 | 0 | 574448.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 0 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 161.26 | 0 | 24031.71 | 0 | 237347.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | -5.15e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | 2.0464e-12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 0 | 0 | 106075.69 | 0 | 191783.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 0 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 0 | 0 | 47114.43 | 0 | 51922.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 0 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 0 | 0 | 9193.59 | 0 | 9193.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 0 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 0 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 24954.72 | 0 | 141459.69 | 0 | 141459.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 0 | 0 | 1077.99 | 0 | 3252.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 24.87 | 0 | 36979.27 | 0 | 36979.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 0 | 0 | 6834.42 | 0 | 6834.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | 98722.96 | 0 | 251518.53 | 0 | 251518.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 0 | 0 | 67048.53 | 0 | 67048.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0 | 0 | 296.82 | 0 | 296.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 98367.26 | 0 | 134038.19 | 0 | 134038.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 5491.06 | 0 | 945016.83 | 0 | 945016.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 3880.46 | 0 | 99474.41 | 0 | 99474.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | -114.63 | 0 | 40584.33 | 0 | 40584.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5653109 | FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 0 |  | 44302 | Hacker | 772.68 | 0 | 772.68 | 0 | 772.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 0 | 44131 | 44092 | Shelton | 14851.08 | 0 | 21149.71 | 0 | 21149.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6243694 | ~400 FT MEA; DOLWICK DR | 0 | 44203 | 44071 | Shelton | 4.17 | 0 | 6215.5 | 0 | 6215.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6245365 | ~425 FT MEA; SARAH LN | 0 | 44147 | 44134 | Shelton | 2447.27 | 0 | 6868.68 | 0 | 6868.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6684040 | ~1825 FTMEA; WRIGHT BLVD | 0 | 44173 | 44165 | Shelton | 251.15 | 0 | 251.15 | 0 | 251.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6842755 | MAIN EXTENSION AARON DR-85 FT 2 IN- | 0 | 44090 | 44057 | Shelton | 0 | 0 | 4706.99 | 0 | 4706.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 12738.45 | 0 | 226839.36 | 0 | 226839.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7078370 | CANCEL INVESTMENT WAY MEA | 0 |  | 44104 | Shelton | 13348.43 | 0 | 16175.73 | 0 | 16175.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7122512 | 100 FT MEA; 10009 INDIAN HILL DR | 0 | 44177 | 44141 | Shelton | 2495.96 | 0 | 2495.96 | 0 | 2495.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7488442 | SANCTUARY VILLAGE PHASE 1 PART 3 | 0 |  | 44156 | Shelton | 115.37 | 0 | 115.37 | 0 | 115.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 0 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 0 | 0 | 143234.26 | 0 | 143234.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -19074 | -769887.31 | -19074
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | -242.16 | 0 | 6352.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 1.4211e-14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 106446.72 | 0 | 708715.26 | 0 | 3674135.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 0 | 0 | 3586.75 | 0 | 407592.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0579746 | JT-G-RIVERS POINTE ESTATES PHASE 1 | 0 | 44270 | 44008 | Shelton | 25162.95 | 0 | 25162.95 | 0 | 25162.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 376.03 | 0 | 52841.51 | 0 | 365812.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602140 | FARM TAP PROJ; ENZWEILER RD | 0 |  | 44396 | Shelton | 290.14 | 0 | 3233.62 | 0 | 3233.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 16.19 | 0 | -11.56 | 0 | 15713.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 0 | 0 | 1608.77 | 0 | 34198.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 0 | 0 | 117485.52 | 0 | 387555.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 0 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 15317.71 | 0 | 243462 | 0 | 499496.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1957438 | FARM TAP PROJ; GRANDVIEW RD | 0 |  | 44379 | Hacker | 52.07 | 0 | 51265.42 | 0 | 51265.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 1000.04 | 0 | 575448.31 | 0 | 575448.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 0 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 244.6 | 0 | 24276.31 | 0 | 237591.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | -4.9113e-11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | 7.5673e-13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 0 | 0 | 106075.69 | 0 | 191783.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 0 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 0 | 0 | 47114.43 | 0 | 51922.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 0 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 0 | 0 | 9193.59 | 0 | 9193.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 0 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 0 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 902.18 | 0 | 142361.87 | 0 | 142361.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 0 | 0 | 1077.99 | 0 | 3252.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 168.12 | 0 | 37147.39 | 0 | 37147.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 0 | 0 | 6834.42 | 0 | 6834.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | -282.27 | 0 | 251236.26 | 0 | 251236.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 0 | 0 | 67048.53 | 0 | 67048.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0 | 0 | 296.82 | 0 | 296.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 23345.55 | 0 | 157383.74 | 0 | 157383.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | -4284.63 | 0 | 940732.2 | 0 | 940732.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 554.16 | 0 | 100028.57 | 0 | 100028.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | 16800.84 | 0 | 57385.17 | 0 | 57385.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5653109 | FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 0 |  | 44302 | Hacker | 0.79 | 0 | 773.47 | 0 | 773.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 0 | 44131 | 44092 | Shelton | 68704.22 | 0 | 89853.93 | 0 | 89853.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6243694 | ~400 FT MEA; DOLWICK DR | 0 | 44203 | 44071 | Shelton | 600.85 | 0 | 6816.35 | 0 | 6816.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6245365 | ~425 FT MEA; SARAH LN | 0 | 44147 | 44134 | Shelton | 3954.31 | 0 | 10822.99 | 0 | 10822.99 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6684040 | ~1825 FTMEA; WRIGHT BLVD | 0 | 44173 | 44165 | Shelton | 6243.9 | 0 | 6495.05 | 0 | 6495.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6842755 | MAIN EXTENSION AARON DR-85 FT 2 IN- | 0 | 44090 | 44057 | Shelton | 195.49 | 0 | 4902.48 | 0 | 4902.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 32752.62 | 0 | 259591.98 | 0 | 259591.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7078370 | CANCEL INVESTMENT WAY MEA | 0 |  | 44104 | Shelton | 5963.15 | 0 | 22138.88 | 0 | 22138.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7122512 | 100 FT MEA; 10009 INDIAN HILL DR | 0 | 44177 | 44141 | Shelton | 1410.56 | 0 | 3906.52 | 0 | 3906.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7488442 | SANCTUARY VILLAGE PHASE 1 PART 3 | 0 |  | 44156 | Shelton | 0.12 | 0 | 115.49 | 0 | 115.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8030455 | Camp Ernst and Solomon MAE | 0 | 44222 | 44208 | Shelton | 4520.37 | 0 | 4520.37 | 0 | 4520.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 0 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8451945 | INVESTMENT WAY MEA | 0 | 44139 | 44130 | Shelton | 250.58 | 0 | 250.58 | 0 | 250.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 0 | 0 | 143234.26 | 0 | 143234.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28075 | TO ACCUMULATE CREDITS TO PLANT FOR | -20808 | 40179 | 39814 | Clippinger | 0 | -1734 | 0 | -20808 | -769887.31 | -20808
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8173 | 01-2255-6 | 0 |  |  |  | 0 | 0 | 0 | 0 | -259.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9996 | 02-2137-4 - JHR | 0 |  |  |  | 0 | 0 | 0 | 0 | -222.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B1982 | 02-2239-8 - John Ranson | 0 |  |  |  | 0 | 0 | 0 | 0 | -235.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7375 | 04-2062-0 PP 592293 RIDGEWOOD | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 12010.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B7692 | 04-2095-0 | 0 |  |  |  | 0 | 0 | 0 | 0 | -74.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8039 | 04-2131-3 | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B8075 | Burgandy Hills Apts PH 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | -77.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1764.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9133 | 641702 CANTWELL | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 13045.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 2114.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2680 | 708300 J MCCORD | 0 | 38889 | 38889 |  | 0 | 0 | 0 | 0 | 19350.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | 73.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3252 | STA 745-OUTLET/05-1063-6/CWA | 0 | 38615 | 38615 |  | 0 | 0 | 0 | 0 | 7670.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3301 | PP 726286 J GROESCHEN | 0 | 39003 | 39003 |  | 0 | 0 | 0 | 0 | 63.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3302 | PP 726778 J GROESCHEN | 0 | 39766 | 39766 |  | 0 | 0 | 0 | 0 | 6291.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3369 | PP 712509 JOSH MCCORD | 0 | 38614 | 38614 |  | 0 | 0 | 0 | 0 | 2195.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3372 | pp 729514 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | -216.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3378 | pp 729803 j groeschen | 0 | 39034 | 39034 |  | 0 | 0 | 0 | 0 | 141269.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3613 | pp 736175 j groeschen | 0 | 38867 | 38867 |  | 0 | 0 | 0 | 0 | 14902.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3681 | pp736750/dan charlton | 0 |  |  |  | 0 | 0 | 0 | 0 | -7.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3838 | pp 742070 j groeschen | 0 | 38868 | 38868 |  | 0 | 0 | 0 | 0 | 22925.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3839 | PP 742089 | 0 | 39679 | 39679 |  | 0 | 0 | 0 | 0 | 15818.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3902 | PP 743895 | 0 | 39072 | 39072 |  | 0 | 0 | 0 | 0 | 12027.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4062 | PP 736715 JOSH MCCORD 0523498 | 0 | 39170 | 39170 |  | 0 | 0 | 0 | 0 | 8702.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 978.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4455 | 05-2169-0 D CARMACK | 0 | 39007 | 39007 |  | 0 | 0 | 0 | 0 | 54.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4892 | 05-2359-9 DONNA CARMACK | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 18489.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5003 | 05-2377-9 CARMACK PP 767000 | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 31593.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5126 | 05-2381-1 MCCORD | 0 | 39062 | 39062 |  | 0 | 0 | 0 | 0 | 20902.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5181 | 0542043 DONNA CARMACK 773243 | 0 | 38849 | 38849 |  | 0 | 0 | 0 | 0 | 30458.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5187 | 05-2157-5 DONNA CARMACK | 0 | 39153 | 39153 |  | 0 | 0 | 0 | 0 | 11928.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5240 | Foundation Dr PP 753544 DN | 0 | 38726 | 38726 |  | 0 | 0 | 0 | 0 | 6014.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5254 | 05-2148-4 DONNA CARMACK | 0 | 38996 | 38996 |  | 0 | 0 | 0 | 0 | 14485.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5296 | PP 769499 JOSH MCCORD | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 10055.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5325 | 05-4200-1 DONNA CARMACK | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 24838.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5338 | PP 778532 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 357.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5339 | PP 778584 M MANYET | 0 | 38814 | 38814 |  | 0 | 0 | 0 | 0 | 46476.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5357 | Donald Dr PP 779803 SC | 0 | 38756 | 38756 |  | 0 | 0 | 0 | 0 | 5299.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2252.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5372 | 06-2026-0 J GROESCHEN 780009 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 26763.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5373 | 06-4054-0 J GROESCHEN PP780073 | 0 | 38941 | 38941 |  | 0 | 0 | 0 | 0 | 103045.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5471 | Neyer Holdings Dr PP 781949 MB | 0 | 38908 | 38908 |  | 0 | 0 | 0 | 0 | 13037.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5691 | Meadow Glen Sub PH 6 | 0 | 39442 | 39442 |  | 0 | 0 | 0 | 0 | 19208.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5692 | Meadow Glen Sub PH 5 | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 14709.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5749 | PP 737637 J MCCORD | 0 | 39241 | 39241 |  | 0 | 0 | 0 | 0 | 24683.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5790 | 05-2338-1 donna carmack | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 41900 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5795 | pp 788167 kathleen owen | 0 | 39085 | 39085 |  | 0 | 0 | 0 | 0 | 24501.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5932 | g06-4002-9/ J CRUSE- R CANTWEL | 0 | 38995 | 38995 |  | 0 | 0 | 0 | 0 | 50257.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5946 | 06-2117-7 DONNA CARMACK | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 65087.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5950 | Apex Dr PP 792460 JC/DC | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 13532.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6020 | pp 794096 JOE GROESCHEN | 0 | 38937 | 38937 |  | 0 | 0 | 0 | 0 | 14892.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6023 | PP 792888 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 84223.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6024 | JPP 792874 MARJORIE MANYET | 0 | 38894 | 38894 |  | 0 | 0 | 0 | 0 | 29397.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6073 | Wildcat Dr PP 795977 MB | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 2429.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6093 | PP 796471 JOSH MCCORD | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 27765.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6097 | PP 776095 DONNA CARMACK | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 14864.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6107 | PP 796644 JOE G 06-2134-2 | 0 | 38951 | 38951 |  | 0 | 0 | 0 | 0 | 15134.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6185 | PP 764595 MARJORIE MANYET | 0 | 38903 | 38903 |  | 0 | 0 | 0 | 0 | 9919.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6219 | PP 788818 0620245 D CARMACK | 0 | 38953 | 38953 |  | 0 | 0 | 0 | 0 | 15113.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6242 | PP 798799 KATHLEEN OWEN | 0 | 39041 | 39041 |  | 0 | 0 | 0 | 0 | 51209.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6302 | Watkins & Euclid PP 801135 JF | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | 20915.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6304 | PP 801384 - BRIAN YORK | 0 | 39013 | 39013 |  | 0 | 0 | 0 | 0 | 248377.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6325 | pp801663 Josh Mccord | 0 | 39086 | 39086 |  | 0 | 0 | 0 | 0 | 14749.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2656.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6463 | 06-2112-8 DONNA CARMACK | 0 | 38980 | 38980 |  | 0 | 0 | 0 | 0 | 10042.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6487 | 06-2155-7 DONNA CARMACK | 0 | 39177 | 39177 |  | 0 | 0 | 0 | 0 | 60898.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6498 | 06-2162-3 JOE GROESCHEN PP 807 | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11337.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6530 | M MITTENDORF | 0 | 38989 | 38989 |  | 0 | 0 | 0 | 0 | 11465.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6729 | Orphanage Rd PP 813162 JF | 0 | 38863 | 38863 |  | 0 | 0 | 0 | 0 | 3104.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6786 | G0621862 J GROESCHEN PP 815190 | 0 | 38904 | 38904 |  | 0 | 0 | 0 | 0 | 17406.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6825 | PP - 816205/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 86880.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6873 | pp817642 JOE GROESCHEN | 0 | 38931 | 38931 |  | 0 | 0 | 0 | 0 | 11473.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6952 | pp 814448/JOSH MCCORD | 0 | 39195 | 39195 |  | 0 | 0 | 0 | 0 | 26643.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7024 | PP 821469 / JOE GROESCHEN | 0 | 39297 | 39297 |  | 0 | 0 | 0 | 0 | 15921.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7117 | PP 817981 DN | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 31266.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7135 | PP 809751/DONNA CARMACK | 0 | 39192 | 39192 |  | 0 | 0 | 0 | 0 | 29700.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7296 | Hargrave Dr PP 822374 MB | 0 | 38986 | 38986 |  | 0 | 0 | 0 | 0 | 16302.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7299 | 06-2178-9 DONNA CARMACK | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 46531.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7314 | 06-2205-0 PP 826800 J GROESCHE | 0 | 39070 | 39070 |  | 0 | 0 | 0 | 0 | 85357.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7384 | PP - 828750/CHARLES NORDIN | 0 | 39196 | 39196 |  | 0 | 0 | 0 | 0 | 43230.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7404 | INDEPENDENCE VILLAGE BLVD RC | 0 | 39167 | 39167 |  | 0 | 0 | 0 | 0 | 28871.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7405 | 06-2209-2 CARMACK/NORDIN | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7406 | PP 829509 JOSH MCCORD | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 15307.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7414 | Scott Ascent Condos PP 805962 | 0 | 39037 | 39037 |  | 0 | 0 | 0 | 0 | 46470.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7423 | PP 829518/JOE GROESCHEN | 0 | 39069 | 39069 |  | 0 | 0 | 0 | 0 | 15875.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7478 | PP 825652 - FRED GOODMAN | 0 | 38968 | 38968 |  | 0 | 0 | 0 | 0 | 6067.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7531 | 05-2362-9 DONNA CARMACK | 0 | 39111 | 39111 |  | 0 | 0 | 0 | 0 | 24650.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7555 | 832258 M MANYET | 0 | 39164 | 39164 |  | 0 | 0 | 0 | 0 | 37497.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7559 | STA 770-INLET PIP/CWA | 0 | 39029 | 39029 |  | 0 | 0 | 0 | 0 | 14101.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7565 | 832625 JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 76.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7617 | 843361 JOE GROESCHEN | 0 | 39384 | 39384 |  | 0 | 0 | 0 | 0 | 18173.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7651 | Richwood Common East PP 835254 | 0 | 39027 | 39027 |  | 0 | 0 | 0 | 0 | 86868.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7671 | PP 834744/MARJORIE MANYET | 0 | 39066 | 39066 |  | 0 | 0 | 0 | 0 | 17679.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7695 | 06-2169-8/DONNA CARMACK | 0 | 39052 | 39052 |  | 0 | 0 | 0 | 0 | 13208.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7729 | PP 837315/JOE GROESCHEN | 0 | 39222 | 39222 |  | 0 | 0 | 0 | 0 | 23303.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7730 | PP 837520/JOE GROESCHEN | 0 | 39252 | 39252 |  | 0 | 0 | 0 | 0 | 18180.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7753 | REG 107K MEA/CWA | 0 | 39043 | 39043 |  | 0 | 0 | 0 | 0 | 40209.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7812 | PP 839626/DONNA CARMACK | 0 | 39168 | 39168 |  | 0 | 0 | 0 | 0 | 114762.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7885 | PP 834544/MARJORIE MANYET | 0 | 39269 | 39269 |  | 0 | 0 | 0 | 0 | 14975.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7886 | PP 842459/JOE GROESCHEN | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 11882.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7937 | DONNA CARMACK | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 25043.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7968 | PP 844220/JOE GROESCHEN | 0 | 39150 | 39150 |  | 0 | 0 | 0 | 0 | 28540.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7994 | PP 845758/JOE GROESCHEN | 0 | 39133 | 39133 |  | 0 | 0 | 0 | 0 | 10615.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8011 | PP 845752/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 28484.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8082 | STA 763 INLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 22257.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8083 | STA 763 OUTLET PIPING/CWA | 0 | 39160 | 39160 |  | 0 | 0 | 0 | 0 | 6471.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 262.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1975.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8166 | PP 849654/JOSHUA MCCORD | 0 | 39282 | 39282 |  | 0 | 0 | 0 | 0 | 30468.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8194 | PP 849881/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -0.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8221 | PP 846957/DONNA CARMACK | 0 | 39099 | 39099 |  | 0 | 0 | 0 | 0 | 11378.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8294 | PP 853137/DONNA CARMACK | 0 | 39188 | 39188 |  | 0 | 0 | 0 | 0 | 31893.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8311 | pp 854289/joe groeschen | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 28426.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8337 | CALLIE WY UNION PT PP 832182 | 0 | 39135 | 39135 |  | 0 | 0 | 0 | 0 | 9532.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8360 | STA 776 - INLET PIPING/CWA | 0 | 39084 | 39084 |  | 0 | 0 | 0 | 0 | 14647.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8398 | pp 855454/donna carmack | 0 | 39211 | 39211 |  | 0 | 0 | 0 | 0 | 36271.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8422 | pp857323/KATHLEEN OWEN | 0 | 39198 | 39198 |  | 0 | 0 | 0 | 0 | 18037.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2056.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | 1995.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8619 | PP 861043/DONNA CARMACK | 0 | 39357 | 39357 |  | 0 | 0 | 0 | 0 | 23953.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8627 | STA 771 INLET/CWA | 0 | 39157 | 39157 |  | 0 | 0 | 0 | 0 | 20265.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8688 | 864712/joe groeschen | 0 |  |  |  | 0 | 0 | 0 | 0 | -2.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1338.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8818 | Calvary & Parkside PP832164 SC | 0 | 39176 | 39176 |  | 0 | 0 | 0 | 0 | 56580.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8888 | Ferncliff PP 869133 JF | 0 | 39114 | 39114 |  | 0 | 0 | 0 | 0 | 4111.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8935 | PP 869760/JOE GROESCHEN | 0 | 39429 | 39429 |  | 0 | 0 | 0 | 0 | 30300.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1186.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9154 | PP 874854/MICHAEL SMITH | 0 | 39287 | 39287 |  | 0 | 0 | 0 | 0 | 24009.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9155 | PP 876484/JOE GROESCHEN | 0 | 39455 | 39455 |  | 0 | 0 | 0 | 0 | 58883.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9252 | Walton Towne Center PP 879595 | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 74721.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9269 | Plantation Pt Ph 2 PP 832157 | 0 | 39218 | 39218 |  | 0 | 0 | 0 | 0 | 16774.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 2174.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9442 | enterprise 5 ph 5a/ pp878207 | 0 | 39293 | 39293 |  | 0 | 0 | 0 | 0 | 38897.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9505 | PP 888525/DONNA CARMACK | 0 | 39268 | 39268 |  | 0 | 0 | 0 | 0 | 8800.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9560 | pp 894004/JOE GROESCHEN | 0 | 39371 | 39371 |  | 0 | 0 | 0 | 0 | 9490.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9561 | pp 894039/JOE GROESCHEN | 0 | 39335 | 39335 |  | 0 | 0 | 0 | 0 | 64670.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9645 | Mercedes Dr PP 881776 JF | 0 | 39366 | 39366 |  | 0 | 0 | 0 | 0 | 13408.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9658 | PP 895625/DONNA CARMACK | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 65012.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9767 | PP 901908 Joe Fricke | 0 | 39353 | 39353 |  | 0 | 0 | 0 | 0 | 45030.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9770 | STA 781-INLET/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9826.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9771 | STA 781-OUTLET/CWA | 0 | 39255 | 39255 |  | 0 | 0 | 0 | 0 | -19013.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9879 | Service Rd Walton Town Center | 0 | 39310 | 39310 |  | 0 | 0 | 0 | 0 | 3536.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9889 | PP 892193/DONNA CARMACK | 0 | 39422 | 39422 |  | 0 | 0 | 0 | 0 | 41577.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 3096.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9918 | PP908630/JOE GROESCHEN | 0 | 39322 | 39322 |  | 0 | 0 | 0 | 0 | 22175.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9941 | 906176/John Betsch | 0 | 39244 | 39244 |  | 0 | 0 | 0 | 0 | 8575.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1020 | Valley View PP 911790 BB | 0 | 39279 | 39279 |  | 0 | 0 | 0 | 0 | 7420.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1092 | PP 907226/DONNA CARMACK | 0 | 39398 | 39398 |  | 0 | 0 | 0 | 0 | 9605.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1193 | Chamber Center Dr PP920339 /BB | 0 | 39303 | 39303 |  | 0 | 0 | 0 | 0 | 3355.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 7336.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1200 | pp 917654/donna carmack | 0 | 39444 | 39444 |  | 0 | 0 | 0 | 0 | 18245.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1201 | PP 920146/MICHAEL SMITH | 0 | 39462 | 39462 |  | 0 | 0 | 0 | 0 | 16904.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1208 | Frogtown Connector Rd PP910275 | 0 | 39372 | 39372 |  | 0 | 0 | 0 | 0 | 47471.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1230 | 844337/Chris Ampher | 0 | 39540 | 39540 | Shoemaker | 0 | 0 | 0 | 0 | -5408.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 1323.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1345 | Kustom Dr PP925906 MB | 0 | 39356 | 39356 |  | 0 | 0 | 0 | 0 | 10262.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 66056.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 66.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 42078.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1428 | pp 709296/adam rauch | 0 | 39552 | 39552 |  | 0 | 0 | 0 | 0 | 22323.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | 6256.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1480 | PP 922726/MICHAEL SMITH | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 5800.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1584 | STEVE TWEHUES/07-2059-9 | 0 | 39518 | 39518 |  | 0 | 0 | 0 | 0 | 8164.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1638 | Viox Dr PP 937815 MB | 0 | 39561 | 39561 |  | 0 | 0 | 0 | 0 | 7224.29 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1882 | ASH RD/CHRIS AMPHER | 0 | 39358 | 39358 |  | 0 | 0 | 0 | 0 | 135.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1928 | 07-2054-0 DONNA CARMACK | 0 | 39477 | 39477 |  | 0 | 0 | 0 | 0 | 8125.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1982 | PP 947383/JOE GROESCHEN | 0 | 39461 | 39461 |  | 0 | 0 | 0 | 0 | 12630.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2020 | PP 935528/STEVE TWEHUES | 0 | 39577 | 39577 |  | 0 | 0 | 0 | 0 | 10694.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2131 | PP 954490 - MIKE BILLOW | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 59871.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2196 | PP956319/LAURA MATE | 0 | 39469 | 39469 |  | 0 | 0 | 0 | 0 | 39628.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2230 | Conner Crossing Dr PP 917670 | 0 | 39625 | 39625 |  | 0 | 0 | 0 | 0 | 7895.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2304 | PP 950302/DONNA CARMACK | 0 | 39542 | 39542 |  | 0 | 0 | 0 | 0 | 20334.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2428 | PP 876161/MARJORIE MANYET | 0 | 39624 | 39624 |  | 0 | 0 | 0 | 0 | 15052.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2582 | PP960454/DONNA CARMACK | 0 | 39689 | 39689 |  | 0 | 0 | 0 | 0 | 21174.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2772 | PP 709296/DONNA CARMACK | 0 | 39681 | 39681 |  | 0 | 0 | 0 | 0 | 5917.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2773 | PP 969628/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 9.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3074 | PP 976606/JOE GROESCHEN | 0 | 39667 | 39667 |  | 0 | 0 | 0 | 0 | 17792.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3136 | WILDER CROSSINGS PP 980705 AR | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 19790.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3167 | Turfrider Ct PP 981670 JF | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 2037.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3184 | PP 977665/DONNA CARMACK | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 16.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3292 | PP 984314/DONNA CARMACK | 0 | 39645 | 39645 |  | 0 | 0 | 0 | 0 | 4176.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3343 | PP987555 HARMONY SUBD | 0 | 39616 | 39616 |  | 0 | 0 | 0 | 0 | -1508.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3458 | PP990266 WILLIAMS CREEK | 0 | 39657 | 39657 |  | 0 | 0 | 0 | 0 | 14118.68 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | 175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3594 | 4800 bk Far Hill Dr Indep KY | 0 | 39596 | 39596 |  | 0 | 0 | 0 | 0 | 325.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3748 | PP 985355/CWA | 0 | 39829 | 39829 | Shoemaker | 0 | 0 | 0 | 0 | 129886.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3759 | PP 1002389/DONNA CARMACK | 0 | 39855 | 40236 |  | 0 | 0 | 0 | 0 | 16327.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0001 | LONGBRANCH ROAD PRI PH 1 | 0 | 39643 | 41457 | Shoemaker | 0 | 0 | 0 | 0 | 37589.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0047 | PP #1005553 Joe Groeschen | 0 | 39702 | 41464 |  | 0 | 0 | 0 | 0 | 10233.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0111 | PP #1006234 Serenity Way | 0 | 40096 | 41274 | Davis | 0 | 0 | 0 | 0 | 4504.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0116 | PP#1005016 Marjorie Manyet | 0 | 39749 | 39722 |  | 0 | 0 | 0 | 0 | 1736.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0323 | ORLEANS SOUTH PH D PT 3 | 0 | 39715 | 55153 |  | 0 | 0 | 0 | 0 | 6363.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0351 | Reg 51 Inlet & Outlet | 0 | 39455 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 295.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0466 | 08-2044-9 LAKEMONT SUB'D PH 4A | 0 | 39749 | 55153 |  | 0 | 0 | 0 | 0 | 15144.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0468 | Sta 795 Outlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10147.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0469 | Sta 795 Inlet Piping | 0 | 39736 | 55153 | Shoemaker | 0 | 0 | -242.16 | 0 | 6352.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0712 | 08-2040-7 SUNDANCE ESTATES PH 2 | 0 | 39772 | 55153 |  | 0 | 0 | 0 | 0 | 17862.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0883 | 08-2046-4 FT THOMAS OVERLOOK PH3 | 0 | 39773 | 55153 |  | 0 | 0 | 0 | 0 | 3835.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0979 | 08-4085-0 Deckercrane Ln., Covingto | 0 | 40088 | 55153 | Davis | 0 | 0 | 0 | 0 | 1905.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1216 | Sta 795 Outlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 19594 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1217 | Sta 794 Inlet Piping | 0 | 39778 | 40178 |  | 0 | 0 | 0 | 0 | 28700.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1472 | 08-2041-5 COOL SPRINGS SEC 8 | 0 | 39833 | 41492 |  | 0 | 0 | 0 | 0 | 7621.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1513 | STA 796 Inlet Piping | 0 | 39770 | 40178 |  | 0 | 0 | 0 | 0 | 42135.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1732 | Hickory Valley Sub PhA Pt 3 | 0 | 39839 | 55153 |  | 0 | 0 | 0 | 0 | 9321.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2203 | F/L UL-55 Caulk Lane Walton | 0 | 39771 | 39813 |  | 0 | 0 | 0 | 0 | 15693.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2372 | 08-4086-8 Creek Rd. & Fowler Creek | 0 | 39762 | 55153 |  | 0 | 0 | 0 | 0 | 5274.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2394 | 08-4089-2 PAVILION PKWY, NEWPORT | 0 | 40074 | 55153 | Davis | 0 | 0 | 0 | 0 | 72880.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2433 | 08-4088-4 FRONTAGE RD, WALTON, KY | 0 | 39850 | 55153 | Davis | 0 | 0 | 0 | 0 | 9559.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2473 | 08-4087-6 TURKEYFOOT RD @ INDUSTRIA | 0 | 40081 | 55153 | Davis | 0 | 0 | 0 | 0 | 72606.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2592 | PP#1035992 Madison Heights | 0 | 39876 | 55153 |  | 0 | 0 | 0 | 0 | 29931.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2594 | PP#1035916 Gunpowder Trails | 0 | 39867 | 55153 |  | 0 | 0 | 0 | 0 | 14085.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E2595 | 08-2055-5 Thornwilde PH O PT 1 | 0 | 40145 | 55153 | Davis | 0 | 0 | 0 | 0 | 8981.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3135 | 08-2056-3 THORNWILDE PH O PT 1B | 0 | 40103 | 41611 | Davis | 0 | 0 | 0 | 0 | 7037.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E3615 | Violet Drive | 0 | 39836 | 39903 |  | 0 | 0 | 0 | 0 | 13275.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4614 | 09-4025-4 INSTALL 275' - 2" PL IP | 0 | 39923 | 40178 |  | 0 | 0 | 0 | 0 | 16364.64 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4954 | PP#1055138 2344 AMSTERDAM RD | 0 | 39995 | 40513 | Davis | 0 | 0 | 0 | 0 | 14795.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5274 | REG 108K-INLET & OUTLET | 0 | 40114 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 27415.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5277 | REG 111K INLET & OUTLET | 0 | 40015 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 97041.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5278 | STA 793 INLET PIPING | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 29476.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5285 | STA 793 - Outlet Piping | 0 | 40141 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 23332.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5367 | PP1057596 Hickory Valley Subd | 0 | 40089 | 41000 |  | 0 | 0 | 0 | 0 | 4160.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5864 | PP#1059733 - 09-2004-1 CLAIBORNE 5A | 0 | 40089 | 41016 |  | 0 | 0 | 0 | 0 | 9410.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6689 | Delta Ave | 0 | 40085 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 49581.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6864 | PP#1068616 502 GENERAL DR, FT WRIGH | 0 | 40049 | 40026 |  | 0 | 0 | 0 | 0 | 8407.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7331 | STA 535 Inlet Valve | 0 | 40073 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 41680.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7585 | PP#1073980 THORNWILDE PH O | 0 | 40147 | 41097 | Davis | 0 | 0 | 0 | 0 | 16332.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8184 | PP 1077275 Ripple Creek Subd | 0 | 40278 | 41114 | Davis | 0 | 0 | 0 | 0 | 10404.51 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8905 | PP#1079998 VILLA GRANDE PH 2 SUBD | 0 | 40154 | 40400 | Davis | 0 | 0 | 0 | 0 | 7239.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8944 | PP#1079997 GRANITE SPRING PH G SEC3 | 0 | 40168 | 40543 | Davis | 0 | 0 | 0 | 0 | 10980.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9864 | PP#1084507 GRIFFIN SUBD, GRIFFIN DR | 0 | 40418 | 41153 | Davis | 0 | 0 | 0 | 0 | 3400.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E9984 | PP#1085161 SHAKER RUN PH 2 PT B | 0 | 40117 | 41155 | Davis | 0 | 0 | 0 | 0 | 3997.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F0705 | EMAX 201475 Red Stone Village | 0 | 40846 | 41176 | Davis | 0 | 0 | 0 | 0 | 30366.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1424 | PP#1091929 MEADOW GLEN PH 1 PT4 | 0 | 40178 | 41931 | Davis | 0 | 0 | 0 | 0 | 6853.08 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1464 | PP1091905 CLAIBORNE PH 5B SUBD | 0 | 40261 | 41931 | Davis | 0 | 0 | 0 | 0 | 14115.05 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F3804 | PP#1078349 2025 DECLARATION DR, | 0 | 40137 | 40543 | Davis | 0 | 0 | 0 | 0 | 83.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7244 | Sherbourne Ph F, Twinridge | 0 |  | 40887 |  | 0 | 0 | 0 | 0 | 3.5527e-15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F7725 | 420 Independence Station Rd | 0 | 40498 | 40908 | Davis | 0 | 0 | 0 | 0 | 46757.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F9305 | EMAX #607352 Treetop Estates Subd | 0 | 40473 | 55153 | Davis | 0 | 0 | 0 | 0 | 16606.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0506 | EMAX #701496 Independence Oaks | 0 | 40821 | 40999 | Davis | 0 | 0 | 0 | 0 | 10128.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0582 | Reg 114K Inlet & Outlet | 0 | 40484 | 40634 | Shoemaker | 0 | 0 | 0 | 0 | 13659.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0606 | Sta 804 Inlet Piping | 0 | 40626 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 52143.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0607 | Sta 804 Outlet Piping | 0 | 40626 | 40847 | Shoemaker | 0 | 0 | 0 | 0 | 29555.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0659 | 747426 - CLAIBORNE PH 5C, KENTON CO | 0 | 40495 | 40877 | Davis | 0 | 0 | 0 | 0 | 4220.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0802 | EMAX 919073 Villa Grande Sec 4 | 0 | 40861 | 40908 | Davis | 0 | 0 | 0 | 0 | 8414.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1040 | EMAX #1054316 Saylor Woods Ph 2 | 0 | 40523 | 40602 | Davis | 0 | 0 | 0 | 0 | 8442.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 65900.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1178 | 1115901 J GROESCHEN Gunpowder Trail | 0 | 40796 | 40939 | Davis | 0 | 0 | 0 | 0 | 8305.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1354 | EMAX 1279677 French Quarter | 0 | 40603 | 40783 | Davis | 0 | 0 | 0 | 0 | 29644.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1998 | STA 810 Inlet Piping F/L UL16 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 20973.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1999 | STA 810 Outlet Piping F/L AM3 | 0 | 40851 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 16504.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2305 | EMAX 1928423 Granite Springs 3B | 0 | 40826 | 41044 | Davis | 0 | 0 | 0 | 0 | 5868.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 6007.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 21476.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3097 | EMAX 2225209 Harmony Sub Ph C | 0 | 40772 | 40999 | Davis | 0 | 0 | 0 | 0 | 8260.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3139 | EMAX 2197891 Sherbourne Ph F | 0 | 40876 | 40908 | Davis | 0 | 0 | 0 | 0 | 13645.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 6071.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3557 | EMAX 2321346 Weideman Hill | 0 | 40803 | 40907 | Davis | 0 | 0 | 0 | 0 | 1791.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3688 | STA 806 Outlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 78797.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3690 | STA 806 Inlet Piping | 0 | 40844 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 37595.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3854 | EMAX 2394542 Johanna Ln | 0 | 40781 | 40831 | Davis | 0 | 0 | 0 | 0 | 5114.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3999 | 7 & 9 Apple Ln inst hp main | 0 | 40731 | 40908 | Davis | 0 | 0 | 0 | 0 | 941.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4006 | US 177 Mago Asphalt Plant F/L UL 56 | 0 | 40786 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 200583.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4145 | EMAX 2455730 Saylor Estates | 0 | 40838 | 40908 | Davis | 0 | 0 | 0 | 0 | 5668.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5073 | EMAX 2609059 Province Pointe Subd | 0 | 41289 | 41364 | Davis | 0 | 0 | 0 | 0 | 5819.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5113 | REG 110K Inlet & Outlet Piping | 0 | 41138 | 41131 | Shoemaker | 0 | 0 | 0 | 0 | 89704.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5254 | 1305 Monmouth St Newport Ky | 0 | 40987 | 40939 | Davis | 0 | 0 | 0 | 0 | 60473.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6542 | EMAX 2911813 Triple Crown Ctry Club | 0 | 41214 | 41274 | Davis | 0 | 0 | 0 | 0 | 8826.97 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6918 | Burnet Ridge | 0 | 41158 | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 84345.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6964 | Wendell Ford Blvd | 0 | 41043 | 41151 | Shoemaker | 0 | 0 | 0 | 0 | 62289.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6968 | EMAX 3021646 Triple Crown Country | 0 | 41214 | 41455 | Davis | 0 | 0 | 0 | 0 | 31197.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7092 | EMAX 3065768 Shadybrook Bluffs Ph 4 | 0 | 41088 | 41274 | Davis | 0 | 0 | 0 | 0 | 8644.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7397 | GS emax 3148910 Lakemont Sub Ph 4B | 0 | 41143 | 41305 | Davis | 0 | 0 | 0 | 0 | 6554.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7425 | JT emax 3155555 Olde Ft Mitchell | 0 | 41232 | 41305 | Davis | 0 | 0 | 0 | 0 | 4092.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7596 | Harold Mason Lane | 0 | 41125 | 41110 | Shoemaker | 0 | 0 | 0 | 0 | 45448.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7648 | emax 3195744 Harmony Sub Ph D | 0 | 41187 | 41241 | Davis | 0 | 0 | 0 | 0 | 4905.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7950 | JT emax 3259578 Madison Heights | 0 | 41188 | 41274 | Davis | 0 | 0 | 0 | 0 | 20260.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7959 | JT emax 3268308 Triple Crown Sec 27 | 0 | 41218 | 41365 | Davis | 0 | 0 | 0 | 0 | 10660.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7982 | JT emax 3275676 Rainbow Terrace | 0 | 41198 | 41274 | Davis | 0 | 0 | 0 | 0 | 6023.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8058 | JT emax 3298935 Arcadia Ph A | 0 | 41604 | 41882 | Davis | 0 | 0 | 0 | 0 | -18008.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8091 | JT emax 3329101 Berlander Rd | 0 | 41516 | 41759 | Davis | 0 | 0 | 0 | 0 | 17867.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8186 | JT emax 3349041 Aosta Valley Ph 2 | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 8428.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8202 | JT emax 3366483 Ormond, Bistro | 0 | 41321 | 41425 | Davis | 0 | 0 | 0 | 0 | 12075.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8210 | JT emax 3371929 Triple Crown Sec 24 | 0 | 41214 | 41362 | Davis | 0 | 0 | 0 | 0 | 8326.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8345 | JT emax 3409638 Cool Springs Ph 4B | 0 | 41244 | 41486 | Davis | 0 | 0 | 0 | 0 | 5703.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8400 | JT emax 3437972 Thornwilde Ph O | 0 | 41255 | 41362 | Davis | 0 | 0 | 0 | 0 | 11829.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8498 | STA 792 Outlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 9222.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8499 | STA 792 Inlet | 0 | 41565 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 45552.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8766 | GM 100 Richwood Rd | 0 | 41282 | 41547 | Davis | 0 | 0 | 0 | 0 | 16118.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8918 | JT emax 3537650 Tree Tops Ph 3B | 0 | 41503 | 41639 | Davis | 0 | 0 | 0 | 0 | 7754.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8937 | JT emax 3624651 Dominion Trail | 0 | 41582 | 41639 | Davis | 0 | 0 | 0 | 0 | 24027.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8993 | JT emax 3484085 Battle Ridge Subd | 0 | 41544 | 41698 | Davis | 0 | 0 | 0 | 0 | 13722.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9170 | JT emax 3744516 Villa Grande Ph 4B | 0 | 41409 | 41608 | Davis | 0 | 0 | 0 | 0 | 5391.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9221 | JT emax 3759761 Ridgewood Valley | 0 | 41335 | 41486 | Davis | 0 | 0 | 0 | 0 | 6164.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9353 | JT emax 3806491 Villa Grande Ph 3A | 0 | 41409 | 41639 | Davis | 0 | 0 | 0 | 0 | 5394.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9462 | JT emax 3857326 Harmony Ph B Pt 2 | 0 | 41471 | 41639 | Davis | 0 | 0 | 0 | 0 | 9276.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9606 | GM 3741336 Ext Gas Main Ft Thomas | 0 | 41711 | 41619 | Davis | 0 | 0 | 0 | 0 | 9081.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9755 | GM 3941287 Grant Park PH 3 | 0 | 41475 | 41639 | Davis | 0 | 0 | 0 | 0 | 20881.98 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9799 | GM 3941206 Stillbrooke Subd | 0 | 41747 | 41879 | Davis | 0 | 0 | 0 | 0 | 17128.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9828 | JT emax 3972664 Thornwilde Ph O | 0 | 41491 | 41670 | Davis | 0 | 0 | 0 | 0 | 14524.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9876 | JT emax 3996921 Arbor Springs | 0 | 41527 | 41670 | Davis | 0 | 0 | 0 | 0 | 5015.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0034 | JT emax 3548558 Orleans South Ph D | 0 | 41882 | 41974 | Davis | 0 | 0 | 0 | 0 | 10426.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0053 | JT emax 4081400 Cauthen Run Subd | 0 | 41687 | 41698 | Davis | 0 | 0 | 0 | 0 | 3522.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0199 | JT emax 4158153 Triple Crown Sec 26 | 0 | 41627 | 41698 | Davis | 0 | 0 | 0 | 0 | 32174.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0219 | JT emax 4171671 Harmony Ph D Pt 2C | 0 | 41554 | 41698 | Davis | 0 | 0 | 0 | 0 | 5948.47 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0335 | Cold Springs Main Extension | 0 | 41554 | 41551 | Shoemaker | 0 | 0 | 0 | 0 | 4016.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0337 | Meadow Glen Main Extension | 0 | 41837 | 41821 | Shoemaker | 0 | 0 | 0 | 0 | 60567.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0440 | JT emax 4279992 Manhattan Harbour | 0 | 41790 | 41911 | Davis | 0 | 0 | 0 | 0 | 26774.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 21507.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0550 | JT emax 4358713 Sherbourne Ph G | 0 | 41652 | 41701 | Davis | 0 | 0 | 0 | 0 | 26978.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0554 | JT emax 4332613 Shadybrook Bluffs | 0 | 41596 | 41820 | Davis | 0 | 0 | 0 | 0 | 9171.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0644 | Independence Rd Main Extension | 0 | 41583 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 22708.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0665 | Transport Dr Main Extension | 0 | 41767 | 41729 | Shoemaker | 0 | 0 | 0 | 0 | 48665.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0688 | McCullum Dr & Courthouse Cr Ext | 0 | 41611 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 125599.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0779 | JT 4446105 Lakemont Main Ext | 0 | 41839 | 41639 | Davis | 0 | 0 | 0 | 0 | 12386.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0780 | JT 4448657 Triple Crown Cntry Clb | 0 | 41745 | 41305 | Davis | 0 | 0 | 0 | 0 | 29894.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0830 | Lakemont PT 2 | 0 | 41684 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 18221.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0894 | JT emax 4475887 Orleans Ph 1 Pt C | 0 | 41618 | 41820 | Davis | 0 | 0 | 0 | 0 | 7191.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0951 | 204 Hayes Station Rd Main Ext | 0 | 41681 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 12744.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1290 | Ferguson Blvd Dry Ridge | 0 | 41700 | 41699 | Shoemaker | 0 | 0 | 0 | 0 | 68373.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1364 | Sutter Drive Main Extension | 0 | 42256 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 550.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1380 | JT 4629095 Arcadia West PH A gas | 0 | 41750 | 41877 | Davis | 0 | 0 | 0 | 0 | 23374.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1463 | Sutter Drive Main Extension | 0 | 41689 | 41790 | Shoemaker | 0 | 0 | 0 | 0 | 23361.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1534 | JT 4172674 Cauthen Run PH 4 | 0 | 41832 | 41851 | Davis | 0 | 0 | 0 | 0 | 5108.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1710 | Southside Church Rd | 0 | 41830 | 41791 | Shoemaker | 0 | 0 | 0 | 0 | 20270.58 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J9116 | JT 5303098 Arc Highlnds PH 1 | 0 | 42013 | 42049 | Davis | 0 | 0 | 0 | 0 | 10607.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K0115 | JT 5293782 Villa Grande | 0 | 41982 | 42102 | Davis | 0 | 0 | 0 | 0 | 8998.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K1102 | JT 4565662 Thornwilde Ph O Pt 4 | 0 | 41845 | 42004 | Davis | 0 | 0 | 0 | 0 | 20585.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L1104 | JT 5457387 Harmony Ph D-3 | 0 | 42016 | 42211 | Davis | 0 | 0 | 0 | 0 | 8555.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L5120 | JT 5512293 Aosta Valley Ph 3 | 0 | 41944 | 42004 | Davis | 0 | 0 | 0 | 0 | 10306.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M5109 | JT 5667493 Lakemont Ph 2C | 0 | 41866 | 42094 | Davis | 0 | 0 | 0 | 0 | 14651.45 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MEAPJT70 | Joint Trench plasitc main extension | 0 | 42454 | 55153 | Davis | 76428.08 | 0 | 785143.34 | 0 | 3750563.27 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0246467 | FARM TAP PROJ.-AARON LN | 0 | 43522 | 43486 | Helm | 0 | 0 | 0 | 0 | 54450.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0270903 | FARM TAP PROJ. 3 MILE RD | 0 |  | 43665 | Helm | 0 | 0 | 3586.75 | 0 | 407592.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0376199 | FARM TAP PROJ; RODGERS RD | 0 | 43636 | 43486 | Helm | 0 | 0 | 0 | 0 | 38053.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0556249 | FARM TAP PROJ; CALIFORNIA CROSSROAD | 0 |  | 43672 | Helm | 0 | 0 | 1652.82 | 0 | 273486.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0579746 | JT-G-RIVERS POINTE ESTATES PHASE 1 | 0 | 44270 | 44008 | Shelton | 20.85 | 0 | 25183.8 | 0 | 25183.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0590999 | FARM TAP; E LOW GAP RD ALEXANDRIA | 0 |  | 43749 | Helm | 307.51 | 0 | 53149.02 | 0 | 366120.4 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602140 | FARM TAP PROJ; ENZWEILER RD | 0 |  | 44396 | Shelton | 3970.95 | 0 | 7204.57 | 0 | 7204.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0602571 | FARM TAP PROJ; JOHNS HILL RD | 0 |  | 43721 | Helm | 13.24 | 0 | 1.68 | 0 | 15726.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0843121 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43564 | 43511 | Helm | 0 | 0 | 0 | 0 | 22839.32 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1130180 | FARM TAP PROJ; MARTHA LAYNE COLLINS | 0 |  | 43544 | Helm | 0 | 0 | 521.37 | 0 | 73280.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1135581 | FARM TAP PROJ; ORCHARD LANE | 0 | 43636 | 43528 | Helm | 0 | 0 | 0 | 0 | 70304.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1236063 | FARM TAP PROJ; KNOLLWOOD DR | 0 | 43722 | 43535 | Helm | 0 | 0 | 0 | 0 | 83191.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1295025 | FARM TAP PROJ; JOYCE ANN LN-ALEXAND | 0 | 43634 | 43686 | Helm | 0 | 0 | 0 | 0 | 3024.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1296075 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43813 | 43759 | Shelton | 0 | 0 | 3371.27 | 0 | 41698.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1304901 | FARM TAP PROJ; WAGONER RD CALIFORNI | 0 |  | 43693 | Helm | 304.36 | 0 | 1913.13 | 0 | 34503.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1307140 | FARM TAP PROJ; BARRS BRANCH / E MAI | 0 | 43876 | 43829 | Helm | 0 | 0 | 117485.52 | 0 | 387555.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355616 | FARM TAP PROJ; WEAVER LN HIGHLAND H | 0 | 43635 | 43556 | Helm | 0 | 0 | 0 | 0 | 16378.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1355956 | FARM TAP PROJ; WESLEY DR HIGHLAND H | 0 | 43603 | 43535 | Helm | 0 | 0 | 0 | 0 | 29048.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1356700 | FARM TAP PROJ; WINTERS LN HIGHLAND | 0 |  | 43735 | Helm | 0 | 0 | 2112.99 | 0 | 255376.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1370091 | FARM TAP PROJ; MARY INGLES HWY | 0 | 43942 | 43889 | Helm | 8567.54 | 0 | 252029.54 | 0 | 508064.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1470330 | MAIN EXT; CVG 6A; TED BUSHELMAN; VA | 0 | 43117 | 43159 | Dube | 0 | 0 | 0 | 0 | 238522.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1605362 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43057 | 43055 | Dube | 0 | 0 | 0 | 0 | 14943.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1693827 | INSTALL GAS ONLY EXISTING SUBDIVISI | 0 | 43379 | 43224 | Helm | 0 | 0 | 0 | 0 | 44116.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1922232 | FARM TAP PROJ; THELMA LEE DR | 0 | 43665 | 43605 | Helm | 0 | 0 | 0 | 0 | 113954.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1957438 | FARM TAP PROJ; GRANDVIEW RD | 0 |  | 44379 | Hacker | 42.58 | 0 | 51308 | 0 | 51308 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1958084 | FARM TAP PROJ; FLAGG SPRINGS PIKE | 0 |  | 43959 | Helm | 479.32 | 0 | 575927.63 | 0 | 575927.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1990005 | 8001 Veterans Memorial Dr. | 0 | 43103 | 43131 | Dube | 0 | 0 | 0 | 0 | 24215.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2009109 | GAS MAIN EXTENSION - 1730 LAKELAND | 0 | 43130 | 43068 | Dube | 0 | 0 | 0 | 0 | 74624.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2142600 | FARM TAP PROJ; THORNTON RD | 0 |  | 43728 | Shelton | 0 | 0 | 2218.01 | 0 | 27728.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2143073 | FARM TAP PROJ; REIDLIN RD | 0 |  | 43679 | Helm | 0 | 0 | 221.42 | 0 | 36692.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2206892 | GAS MAIN EXTENSION - 629 SPARTA PIK | 0 | 43151 | 43138 | Dube | 0 | 0 | 0 | 0 | 25910.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217958 | STA 863 - GRANDVIEW RD - INLET | 0 | 43236 | 43252 | Seiter | 0 | 0 | 0 | 0 | 184633.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217983 | STA 863 - GRANDVIEW RD- Outlet | 0 | 43236 | 43191 | Seiter | 0 | 0 | 0 | 0 | 116461.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243303 | STA 809 - WATERWORKS RD INLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 239253.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2243327 | STA 809 - WATERWORKS RD OUTLET | 0 | 43259 | 43191 | Seiter | 0 | 0 | 0 | 0 | 8022.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 457 | 0 | 24733.31 | 0 | 238048.94 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2272964 | MEA - 242 MARY GRUBBS HWY; WALTON; | 0 | 43108 | 43099 | Dube | 0 | 0 | 0 | 0 | 73225.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335879 | Cancel STA 872 - Oakland Valve -In | 0 | 43637 | 43615 | Seiter | 0 | 0 | -440683.56 | 0 | 5.6843e-12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2335908 | Cancel Oakland Valve House Outlet | 0 | 43637 | 43556 | Seiter | 0 | 0 | -83716 | 0 | -5.7909e-13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336619 | STA 865 - SOUTHRIDGE DR INLET | 0 | 43543 | 43525 | Pollak | 0 | 0 | 0 | 0 | 39655.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2336650 | INSTALL STATION OUTLET PIPING | 0 | 43543 | 43374 | Hughes | 0 | 0 | 0 | 0 | 14713.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2404189 | MEA ~550 FT - 8520 GUNPOWDER RD | 0 | 43739 | 43654 | Helm | 0 | 0 | 0 | 0 | 60005.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2424919 | MEA ~550 FT; 2000 GATEWAY BLVD | 0 |  | 43721 | Shelton | 0 | 0 | 226.3 | 0 | 31942.57 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2470320 | JT-G-RESERVE AT MEADOWOOD PHASE 2 S | 0 | 43810 | 43950 | Shelton | 0 | 0 | 0 | 0 | 19140.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2562222 | MEA ~600 FT - 400 KENTON LANDS RD | 0 | 43876 | 43811 | Helm | 0 | 0 | 106075.69 | 0 | 191783.69 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2568722 | MEA ~230 FT; 500 S MAIN ST | 0 | 43900 | 43818 | Shelton | 0 | 0 | 100347.48 | 0 | 146585.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2626372 | ~675 FT MEA; 2344 AMSTERDAM RD | 0 | 43892 | 43854 | Shelton | 0 | 0 | 47114.43 | 0 | 51922.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663890 | STA 859 - BANKLICK RD -Inlet | 0 | 43207 | 43203 | Seiter | 0 | 0 | 0 | 0 | 53988.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2663986 | STA 859 - BANKLICK RD OUTLET | 0 | 43207 | 43191 | Seiter | 0 | 0 | 0 | 0 | 326531.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2669470 | GAS MAIN EXTENSION - 547 SUTTER DR | 0 | 43158 | 43156 | Dube | 0 | 0 | 0 | 0 | 11046.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2834473 | MEA ~640 FT; 8519 US RT 42 | 0 | 43811 | 43759 | Helm | 0 | 0 | 694.05 | 0 | 55403.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2848811 | INDEPENDENCE RD MEA - | 0 |  | 43770 | Helm | 0 | 0 | 207.12 | 0 | 5498.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2866813 | JT-G-ARCADIA PHASE I | 0 | 43972 | 43889 | Shelton | 0 | 0 | 9193.59 | 0 | 9193.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3354938 | ~MEA 450 FT; 3845 TURFWAY RD | 0 | 43826 | 43745 | Shelton | 0 | 0 | -525.3 | 0 | 35681.37 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3444104 | MEA ~970 FT; ASHLEY DR | 0 | 43796 | 43738 | Helm | 0 | 0 | -1022.79 | 0 | 48969.74 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3745351 | MEA ~200 FT; LEE LN | 0 | 43833 | 43773 | Helm | 0 | 0 | 314.86 | 0 | 14387.6 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3790373 | Williams Way-MEA | 0 | 43801 | 43759 | Helm | 0 | 0 | 0 | 0 | 17714.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4018013 | JOHNS HILL RD MEA | 0 | 43910 | 43819 | Helm | 0 | 0 | 192628.24 | 0 | 209665.9 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4086064 | MEA ~1400 FT; 479 ORPHANGE RD | 0 | 43969 | 43853 | Shelton | 0 | 0 | 89607.92 | 0 | 93844.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4108387 | MEA ~ 270 FT; 950 WENSTRUP LN | 0 | 43910 | 43896 | Shelton | 0 | 0 | 16696.37 | 0 | 18557.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4125743 | 2,000 FT MEA; DAMASCUS | 0 | 44091 | 43902 | Shelton | 0 | 0 | 142361.87 | 0 | 142361.87 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4146445 | MEA ~ 25 FT; 411 COACHLIGHT DR | 0 |  | 43784 | Helm | 0 | 0 | 1077.99 | 0 | 3252.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4210795 | JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 0 |  | 44106 | Shelton | 30.95 | 0 | 37178.34 | 0 | 37178.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4321381 | JT-G-STEEPLECHASE SECTION 18 | 0 | 43955 | 44117 | Shelton | 0 | 0 | 6834.42 | 0 | 6834.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4355391 | ~1,600 FT MEA; 300 RICHARD KNOCK HW | 0 | 44075 | 44043 | Shelton | 0 | 0 | 251236.26 | 0 | 251236.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4769285 | ~985 FT MEA; OAKRIDGE DR | 0 | 43963 | 43931 | Helm | 0 | 0 | 67048.53 | 0 | 67048.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4837396 | JT-G-PARK POINTE | 0 | 44301 | 44161 | Shelton | 0 | 0 | 296.82 | 0 | 296.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4861864 | TERMINAL DR MEA-CVG CONRAC PROJECT | 0 | 44118 | 44092 | Shelton | 1685.38 | 0 | 159069.12 | 0 | 159069.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4875568 | FARM TAP PROJECT; E ALEXANDRIA / CA | 0 | 44101 | 44057 | Helm | 1252.34 | 0 | 941984.54 | 0 | 941984.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5040349 | GLENRIDGE DRIVE - MEA | 0 | 44067 | 44008 | Shelton | 128.45 | 0 | 100157.02 | 0 | 100157.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5373035 | ~350 FT MEA; 390 MEIJER DR | 0 | 44072 | 44035 | Steinmetz | 0 | 0 | 57385.17 | 0 | 57385.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5652554 | MASON ROAD - TAYLOR MILL-4IN PE 6IN | 0 |  | 44438 | Hacker | 4996.02 | 0 | 4996.02 | 0 | 4996.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX5653109 | FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 0 |  | 44302 | Hacker | 0.64 | 0 | 774.11 | 0 | 774.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 0 | 44131 | 44092 | Shelton | 14099.13 | 0 | 103953.06 | 0 | 103953.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6243694 | ~400 FT MEA; DOLWICK DR | 0 | 44203 | 44071 | Shelton | 52562.81 | 0 | 59379.16 | 0 | 59379.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6245365 | ~425 FT MEA; SARAH LN | 0 | 44147 | 44134 | Shelton | -261.44 | 0 | 10561.55 | 0 | 10561.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6371724 | GAS MAIN EXTENSION- COMMERCIAL CONV | 0 | 43239 | 43292 | Helm | 0 | 0 | 0 | 0 | 49771.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628844 | GAS MAIN EXTENSION - 953 RIVERWATCH | 0 | 43208 | 43201 | Helm | 0 | 0 | 0 | 0 | 36256.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6684040 | ~1825 FTMEA; WRIGHT BLVD | 0 | 44173 | 44165 | Shelton | 43335.29 | 0 | 49830.34 | 0 | 49830.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6800571 | GAS MAIN EXTENSION - 9255 US-42, UN | 0 | 43468 | 43399 | Helm | 0 | 0 | 0 | 0 | 188305.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6831488 | MEA - NEARESET ADDY 501 CHESAPEAKE | 0 | 43287 | 43196 | Helm | 0 | 0 | 0 | 0 | 23655.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6835553 | JT-G-SOUTHWICK PHASE B PART 1 | 0 | 44312 | 44337 | Shelton | 57.82 | 0 | 57.82 | 0 | 57.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6842755 | MAIN EXTENSION AARON DR-85 FT 2 IN- | 0 | 44090 | 44057 | Shelton | 194.45 | 0 | 5096.93 | 0 | 5096.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6891268 | AMAZON SOUTHWEST DELIVERY DIST PROJ | 0 | 44201 | 44196 | Helm | 14271.17 | 0 | 273863.15 | 0 | 273863.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7078370 | CANCEL INVESTMENT WAY MEA | 0 |  | 44104 | Shelton | -22003.15 | 0 | 135.73 | 0 | 135.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7122512 | 100 FT MEA; 10009 INDIAN HILL DR | 0 | 44177 | 44141 | Shelton | 22143.33 | 0 | 26049.85 | 0 | 26049.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7231229 | Stonewater Approach Main | 0 | 44332 | 44458 | Shelton | 4607.13 | 0 | 4607.13 | 0 | 4607.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7443695 | JT-G-TREETOPS ESTATES PHASE 4 PART | 0 | 43561 | 43343 | Helm | 0 | 0 | 0 | 0 | 33635.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7473256 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43355 | 43255 | Helm | 0 | 0 | 0 | 0 | 4374.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7488442 | SANCTUARY VILLAGE PHASE 1 PART 3 | 0 |  | 44156 | Shelton | 0.1 | 0 | 115.59 | 0 | 115.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7612042 | Camp Ernst Rd. Burlington LOOP Proj | 0 | 43442 | 43406 | Helm | 0 | 0 | 0 | 0 | 176642.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7722964 | MEA PROJECT LIMABURG RD | 0 | 43437 | 43364 | Helm | 0 | 0 | 0 | 0 | 330591.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7752227 | INSTALL GAS ONLY APPROACH MAIN - NE | 0 | 43370 | 43334 | Helm | 0 | 0 | 394.69 | 0 | 5054.88 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7815869 | 27815869 - MEA - 250 FT OF 4 IN PL- | 0 | 43292 | 43269 | Helm | 0 | 0 | 0 | 0 | 36075.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7865414 | Gas Main Extension - Production Dr, | 0 | 43393 | 43322 | Helm | 0 | 0 | 0 | 0 | 149406.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8030455 | Camp Ernst and Solomon MAE | 0 | 44222 | 44208 | Shelton | 28383.04 | 0 | 32903.41 | 0 | 32903.41 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8059955 | ~440 FT MEA; 2 IN PL HP | 0 |  | 44225 | Shelton | 2478.22 | 0 | 2478.22 | 0 | 2478.22 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8362357 | INSTALL LARGE MEA PROJECT | 0 | 43272 | 43266 | Helm | 0 | 0 | 0 | 0 | 10583.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8377762 | JT-G-TRIPLE CROWN SECTION 18 PHASE | 0 | 43928 | 43465 | Helm | 0 | 0 | 13308.99 | 0 | 20115.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8451945 | INVESTMENT WAY MEA | 0 | 44139 | 44130 | Shelton | 26564.78 | 0 | 26815.36 | 0 | 26815.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8505395 | ~350 FT MEA; 351 KENTON LANDS | 0 | 44285 | 44225 | Shelton | 452.83 | 0 | 452.83 | 0 | 452.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8572486 | JT-G-VALLEY CREEK FARMS PHASE II | 0 | 43515 | 43462 | Helm | 0 | 0 | 0 | 0 | 30423.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8574441 | GAS MAIN EXTENSION - 10177 BIG BONE | 0 |  | 43378 | Helm | 0 | 0 | 710.18 | 0 | 99473.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8664613 | JT-G-BALLYSHANNON SECTION 5 PHASE 5 | 0 | 43480 | 43462 | Helm | 0 | 0 | 0 | 0 | 39433.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8991255 | JT-G-FRENCH QUARTER PHASE 4B-OWEN E | 0 | 43561 | 43462 | Helm | 0 | 0 | 0 | 0 | 50154.67 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9427886 | INSTALL LARGE MEA PROJECT MEADOW LN | 0 | 43410 | 43434 | Helm | 0 | 0 | 0 | 0 | 16771.8 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545252 | GAS MAIN EXTENSION - 3204 Mineola P | 0 | 43479 | 43430 | Helm | 0 | 0 | 0 | 0 | 158887.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MXA350358 | FARM TAP PROJ; THOMAS MORE PKWY | 0 | 43958 | 43903 | Helm | 0 | 0 | 143234.26 | 0 | 143234.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N0103 | JT 5704778 North Walton Pointe Ph 2 | 0 | 42017 | 42183 | Davis | 0 | 0 | 0 | 0 | 3805.62 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N4104 | JT 5506029 Walton Twn Cntr Owen Ele | 0 | 41940 | 42124 | Davis | 0 | 0 | 0 | 0 | 39305.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8125 | JT 5703309 Ridgewood Valley Sec 8B | 0 | 41950 | 42063 | Davis | 0 | 0 | 0 | 0 | 9240.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O3114 | JT 5843063 Reveres Crossing Ph 4 | 0 | 41999 | 42124 | Davis | 0 | 0 | 0 | 0 | 7396.85 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4163 | JT 5925052 Arcadia Ph A Pt 2 | 0 | 41923 | 42119 | Davis | 0 | 0 | 0 | 0 | 7993.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P3113 | JT 5557980 Harmony Ph C3 | 0 | 42026 | 42095 | Davis | 0 | 0 | 0 | 0 | 8172.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P4102 | JT 6024610 50-58 Orphange Rd | 0 | 41951 | 42095 | Davis | 0 | 0 | 0 | 0 | 2831.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6206 | JT 4940830 Williams Woods Ph 4 | 0 | 41925 | 42095 | Davis | 0 | 0 | 0 | 0 | 29890.34 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6292 | JT 5702282 Alson Place Ph 2 | 0 | 42020 | 42200 | Davis | 0 | 0 | 0 | 0 | 9967.43 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6377 | JT 5666593 Sycamore Creek Ph 2 | 0 | 42035 | 42170 | Davis | 0 | 0 | 0 | 0 | 18911.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6491 | JT 6339925 Triple Crown Country Clb | 0 | 42105 | 42369 | Davis | 0 | 0 | 0 | 0 | 46904.15 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6505 | JT 6381321 Hidden Creek II Ph 3 | 0 | 42154 | 42277 | Davis | 0 | 0 | 0 | 0 | 8438.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6518 | JT 6193597 Battle Ridge Subd | 0 | 42282 | 42264 | Davis | 0 | 0 | 0 | 0 | 12563.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6610 | JT 5948437 Lakemont 4C Part 4 | 0 | 42192 | 42309 | Davis | 0 | 0 | 0 | 0 | 9839.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6631 | JT 6445557 Triple Crown Sec 26 Ph 3 | 0 | 42133 | 42267 | Davis | 0 | 0 | 0 | 0 | 40680.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6632 | JT 6445860 Triple Crown Sec 29 Ph 1 | 0 | 42096 | 42267 | Davis | 0 | 0 | 0 | 0 | 53271.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6634 | Lauren Dr MEA | 0 | 41993 | 42063 | Shoemaker | 0 | 0 | 0 | 0 | 10408.38 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6666 | JT 6479375 Madison Heights | 0 | 42074 | 42274 | Davis | 0 | 0 | 0 | 0 | 7603.83 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6672 | JT 6319813 Arcadia Ph B | 0 | 42146 | 42262 | Davis | 0 | 0 | 0 | 0 | 15568.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6772 | JT 6597995 North Walton Pointe | 0 | 42132 | 42165 | Manyet | 0 | 0 | 0 | 0 | 5050.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6888 | 201 Steelman MEA | 0 | 42077 | 42055 | Shoemaker | 0 | 0 | 0 | 0 | 21297.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7015 | JT 6316270 Ballyshannon Sec 1 | 0 | 42108 | 42263 | Davis | 0 | 0 | 0 | 0 | 49558.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7141 | Fleet Blvd MEA | 0 | 42236 | 42430 | Shoemaker | 0 | 0 | 0 | 0 | 56726.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7294 | David Ct MEA | 0 |  | 42051 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8044 | JT 3941259 Arcadia Pod B Ph 1 | 0 | 42168 | 42293 | Shoemaker | 0 | 0 | 0 | 0 | 14011.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9484 | JT 7465123 French Quarter Ph 3D | 0 | 42203 | 42333 | Shoemaker | 0 | 0 | 0 | 0 | 11296.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q2231 | JT 7590611 Ashford Village | 0 | 42282 | 42222 | Shoemaker | 0 | 0 | 0 | 0 | 3679.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3775 | 6th St Newport MEA | 0 | 42390 | 42217 | Johnson | 0 | 0 | 0 | 0 | 37916.06 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q3776 | JT 7648670 Pond Creek Crossing | 0 | 42217 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 6238.53 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q8319 | Lacresta Dr MEA | 0 | 42197 | 42205 | Shoemaker | 0 | 0 | 0 | 0 | 12317.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9540 | JT 7724543 Triple Crown | 0 | 42210 | 42200 | Shoemaker | 0 | 0 | 0 | 0 | 18066.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | Q9644 | JT 7716232 Ballyshannon | 0 | 42208 | 42209 | Shoemaker | 0 | 0 | 0 | 0 | 24658.17 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0735 | JT 7988830 Gun Powder Trails | 0 | 42262 | 42370 | Shoemaker | 0 | 0 | 0 | 0 | 20735.42 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0738 | JT 7992398 Crown Point | 0 | 42425 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 16582.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R0773 | Crown Point Subdivision | 0 | 42523 | 42551 | Shoemaker | 0 | 0 | 0 | 0 | 515780.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1468 | Heights Blvd MEA | 0 | 42354 | 42384 | Perkins | 0 | 0 | 0 | 0 | 62007.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1475 | Cecelia Dr MEA | 0 | 42278 | 42384 | Perkins | 0 | 0 | 0 | 0 | 20695.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1752 | JT 8164269 Lakemont | 0 | 42096 | 42490 | Shoemaker | 0 | 0 | 0 | 0 | 28425 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2222 | 826 Elizabeth Dr Florence Ky MEA | 0 | 42282 | 42265 | Johnson | 0 | 0 | 0 | 0 | 17525.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2247 | JT 8022836 Manhattan Harbour | 0 | 42257 | 42279 | Shoemaker | 0 | 0 | 0 | 0 | 7228.04 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2479 | Regal Ridge Dr MEA | 0 | 42298 | 42341 | Johnson | 0 | 0 | 0 | 0 | 92559.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2646 | 1418 N. Main St Williamstown MEA | 0 | 42277 | 42300 | Johnson | 0 | 0 | 0 | 0 | 36802.81 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2817 | JT 8560406 Shadybrook Bluffs | 0 | 42419 | 42419 | Shoemaker | 0 | 0 | 0 | 0 | 10225.72 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2915 | JT 8022710 Arcadia | 0 | 42296 | 42334 | Shoemaker | 0 | 0 | 0 | 0 | 6982.13 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R2925 | JT 8637217 Triple Crown | 0 | 42453 | 42420 | Shoemaker | 0 | 0 | 0 | 0 | 15696.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3114 | JT 8728425 Triple Crown Sect 32 | 0 | 42418 | 42443 | Shoemaker | 0 | 0 | 0 | 0 | 59466.95 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3118 | JT 8760245 Triple Crown Sect 29 | 0 | 42429 | 42457 | Shoemaker | 0 | 0 | 0 | 0 | 15963.44 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3315 | Griffen Industries MEA | 0 | 42308 | 42308 | Perkins | 0 | 0 | 0 | 0 | 19912.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3386 | Mills Rd Drees Homes MEA | 0 | 42320 | 42306 | Johnson | 0 | 0 | 0 | 0 | 45513.96 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3391 | Highwater MEA | 0 | 42349 | 42356 | Johnson | 0 | 0 | 0 | 0 | 18738.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3494 | JT 8245984 Orleans North Phase I | 0 | 42373 | 42400 | Shoemaker | 0 | 0 | 0 | 0 | 8797.31 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3796 | JT 8916678 Freedom Park II | 0 | 42851 | 42872 | Shoemaker | 0 | 0 | 0 | 0 | 14244.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3798 | JT 8022787 Brigadoon | 0 | 42355 | 42384 | Shoemaker | 0 | 0 | 0 | 0 | 10360.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3801 | JT 8022212 Aosta Valley | 0 | 42387 | 42444 | Shoemaker | 0 | 0 | 0 | 0 | 12324.63 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4166 | 1513 Woodside Dr MEA | 0 | 42425 | 42394 | Johnson | 0 | 0 | 0 | 0 | 27029.01 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4170 | 5935 Merchants St MEA | 0 | 42389 | 42387 | Johnson | 0 | 0 | 0 | 0 | 50121.39 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4462 | GM 8830449 Coachlight | 0 | 42384 | 42369 | Perkins | 0 | 0 | 0 | 0 | 13884.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4463 | GM 9001226 Wright Blvd | 0 | 42432 | 42408 | Perkins | 0 | 0 | 0 | 0 | 27463.73 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5234 | GO 8623141 Turfway Rd | 0 | 42401 | 42391 | Shoemaker | 0 | 0 | 0 | 0 | 70262.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5266 | JT 9122622 Battleridge | 0 | 42445 | 42566 | Shoemaker | 0 | 0 | 0 | 0 | 4912.28 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6359 | GO 9487293 Pat Fanning Way | 0 | 42481 | 42552 | Perkins | 0 | 0 | 0 | 0 | 72983.65 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6365 | GO 9487340 Cedar Ln | 0 | 42482 | 42522 | Perkins | 0 | 0 | 0 | 0 | 27428.66 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6366 | GO 9609542 Grandview Rd | 0 | 42478 | 42522 | Perkins | 0 | 0 | 0 | 0 | 79600.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6367 | GO 9487246 Autumn Ln to Low Gap | 0 | 42495 | 42552 | Perkins | 0 | 0 | 0 | 0 | 317346.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6484 | GO 9694099 208 Vine St | 0 | 42445 | 42461 | Perkins | 0 | 0 | 0 | 0 | 8086.12 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6540 | GO 9775945 AA Highway Crossover | 0 | 42489 | 42551 | Perkins | 0 | 0 | 0 | 0 | 109703.36 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8374 | GO 9591573 1973 Sarah Lane | 0 | 42509 | 42521 | Perkins | 0 | 0 | 0 | 0 | 42870.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2732 | GO 9691430 Sta 836 Inlet Piping | 0 |  | 43323 | Smith | 0 | 0 | 0 | 0 | 24843.2 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S2752 | GO 9691542 Sta 836 Outlet Piping | 0 | 42641 | 43050 | Smith | 0 | 0 | 0 | 0 | 36155.09 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8387 | GO 10416501 279 Riverside Pkwy | 0 | 42577 | 42580 | Perkins | 0 | 0 | 0 | 0 | 18465.84 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8663 | JT 9793544 Ballyshannon S5 Ph 1A | 0 | 42630 | 42806 | Smith | 0 | 0 | 0 | 0 | 104856.23 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8833 | GO 10529464 3876 Burlington Pk | 0 | 42627 | 42615 | Perkins | 0 | 0 | 0 | 0 | 29053.92 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8847 | GO 9527853 820 Dolwick Dr | 0 | 42689 | 42674 | Perkins | 0 | 0 | 0 | 0 | 78494.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9061 | GO 9451838 132 E. Alexandria Pike | 0 | 42655 | 42674 | Perkins | 0 | 0 | 0 | 0 | 90445.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9476 | GO 10744494 15 Sprial Dr | 0 | 42676 | 42664 | Johnson | 0 | 0 | 0 | 0 | 192451.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9515 | GO 10692255 236 Wendel H Ford | 0 | 42703 | 42674 | Perkins | 0 | 0 | 0 | 0 | 49341.5 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9567 | GO 10865647 9001 US Hwy 42 | 0 | 42718 | 43069 | Perkins | 0 | 0 | 0 | 0 | 94611.52 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9584 | GO 10825411 Hawk's Landing | 0 | 42726 | 42719 | Perkins | 0 | 0 | 0 | 0 | 185926.46 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9655 | GO 10945062 1495 Dolwick | 0 | 42689 | 42671 | Pollak | 0 | 0 | 0 | 0 | 30451.24 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9659 | GO 10888391 5905 Merchant St | 0 | 42777 | 42769 | Pollak | 0 | 0 | 0 | 0 | 45542.93 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9687 | GO 11090743 1606 Highwater | 0 | 42724 | 42735 | Perkins | 0 | 0 | 0 | 0 | 20956.11 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9749 | GO 10916480 2403 Stonewall Tr | 0 | 42712 | 42719 | Perkins | 0 | 0 | 0 | 0 | 37102.55 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0386 | GO 10848852 5355 Idlewild Rd | 0 | 42738 | 42766 | Perkins | 0 | 0 | 0 | 0 | 24979.07 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1131 | GO 11485457 1962 SARAH LN; | 0 | 42781 | 42826 | Perkins | 0 | 0 | 0 | 0 | 28512.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1135 | GO 11648289 1099 KEATING DR COLD S | 0 | 42788 | 42826 | Perkins | 0 | 0 | 0 | 0 | 12526.25 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1715 | GO 11582821 2400 Litton Ln | 0 | 42888 | 43115 | Perkins | 0 | 0 | 0 | 0 | 75856.89 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1737 | GO 11797721 Matinee Blvd | 0 | 42923 | 42984 | Perkins | 0 | 0 | 0 | 0 | 37791.21 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2639 | GO 20629592 89 Mel Lawn Dr | 0 | 42823 | 42886 | Johnson | 0 | 0 | 0 | 0 | 3377.78 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T7104 | GO 11376429 Lot 14 Norbotten Dr | 0 | 42921 | 42977 | Reynolds | 0 | 0 | 0 | 0 | 24058.76 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8147 | GO 21080428 Beech Dr. | 0 | 42989 | 43114 | Reynolds | 0 | 0 | 0 | 0 | 22288.82 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9132 | 641698 CANTWELL | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1689.48 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | B9418 | 650906 JOSH MCCORD | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -1996.03 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C3205 | PP 724287 JOSH MCCORD | 0 | 38903 | -36433 |  | 0 | 0 | 0 | 0 | -2381.49 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C4450 | 05-2356-3 PP 758133 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -928.7 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C5363 | 05-2388-6 H GROESCHEN PP 77419 | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2135.86 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C6340 | pp 802473 Joe Groeschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2521.18 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8117 | PP 848275/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -249.19 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8162 | PP 849643/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1884.54 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8468 | pp 858288 joe greoschen | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1954.3 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8495 | PP 858811/JOE GROESCHEN | 0 |  |  |  | 0 | 0 | 0 | 0 | -1896.33 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C8758 | PP 866348/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1274.1 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9135 | PP 875134/STEVE TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1148.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9291 | PP 880671/S TWEHUES | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -2090.91 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | C9917 | PP909228/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -3013.79 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1195 | Villa Grande PH2 Chesapeake BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -7196.02 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1320 | PP 923837/JOE GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -1287.59 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1393 | pp 907295/MICHAEL SMITH | 0 | 39735 | 39735 |  | 0 | 0 | 0 | 0 | 142.71 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1417 | Grandview Dr PP927622 BB | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -60.14 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1418 | Grant Park Ph1 Chateau Dr BB | 0 | 39524 | 39524 |  | 0 | 0 | 0 | 0 | 6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D1452 | Grant Park Approach PP 918483 | 0 |  | -36403 |  | 0 | 0 | 0 | 0 | -6144.56 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | D3513 | PP992542 J GROESCHEN | 0 |  | -36433 |  | 0 | 0 | 0 | 0 | -175.16 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G1098 | Millakin Place | 0 | 40485 | 40724 | Shoemaker | 0 | 0 | 0 | 0 | 209.26 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2632 | EMAX 2114122 Grant Park Subd | 0 | 40747 | 40908 | Davis | 0 | 0 | 0 | 0 | 36.77 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2934 | EMAX 2179169 Triple Crown Sec 24 | 0 | 40898 | 40908 | Davis | 0 | 0 | 0 | 0 | 90.61 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G3537 | EMAX 2317816 Claiborne Ph 5 D | 0 | 41038 | 41274 | Davis | 0 | 0 | 0 | 0 | 70.35 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | H0511 | Install Main Pavilion Pkwy Newport | 0 | 41579 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 75.75 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX2271880 | MEA ~800 FT; 494 JONES RD | 0 |  | 43798 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7MAINS | MAINS Pools | 75086 |  |  | RANDC-NEW BUSINESS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX6180533 | 440 FT MEA; MEDICAL VILLAGE DR | 0 | 44131 | 44092 | Shelton | 261.34 | 0 | 261.34 | 0 | 261.34 | 0
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 238307.42 | 0 | 238307.42 | 0 | 238307.42
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 276563.56 | 0 | 514870.98 | 0 | 514870.98
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 325546.81 | 0 | 840417.79 | 0 | 840417.79
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 262841.73 | 0 | 1103259.52 | 0 | 1103259.52
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 252509.26 | 0 | 1355768.78 | 0 | 1355768.78
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 381462.36 | 0 | 1737231.14 | 0 | 1737231.14
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 269114.98 | 0 | 2006346.12 | 0 | 2006346.12
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 282743.87 | 0 | 2289089.99 | 0 | 2289089.99
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 240991.85 | 0 | 2530081.84 | 0 | 2530081.84
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 283047.25 | 0 | 2813129.09 | 0 | 2813129.09
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 344633.74 | 0 | 3157762.83 | 0 | 3157762.83
G7MAINS | MAINS Pools | 75086 | Gas Ops - Distribution DPS | Rev Producing | RANDC-NEW BUSINESS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MAINS | MAINS Pools | 3590486.45 |  | 55518 | Fritsch | 0 | 432723.62 | 0 | 3590486.45 | 0 | 3590486.45
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 3632.89 | 0 | 3632.89 | 0 | 3632.89
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 4426.11 | 0 | 8059 | 0 | 8059
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 6066.86 | 0 | 14125.86 | 0 | 14125.86
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 13185.24 | 0 | 27311.1 | 0 | 27311.1
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 30444.48 | 0 | 57755.58 | 0 | 57755.58
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 56017.77 | 0 | 113773.35 | 0 | 113773.35
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 48248.35 | 0 | 162021.7 | 0 | 162021.7
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 60598.02 | 0 | 222619.72 | 0 | 222619.72
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 30348.78 | 0 | 252968.5 | 0 | 252968.5
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 6848.13 | 0 | 259816.63 | 0 | 259816.63
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 4758.71 | 0 | 264575.34 | 0 | 264575.34
G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MERG121 | (Cancel) REG 121 Belair & Spicewood | 264575.34 |  | 44073 | Wells | 0 | 0 | 0 | 264575.34 | 0 | 264575.34
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 0 | 0 | 0 | 0 | 12381.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 4563.98 | 0 | 4563.98 | 0 | 16945.53 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 7170 | 0 | 11733.98 | 0 | 24115.53 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 |  |  | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2217622 | STATION 873 - 5TH & PHILADELPHIA | 0 |  | 44530 | Felt | 1195.02 | 0 | 12929 | 0 | 25310.55 | 0
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 618.26 | 0 | 618.26 | 0 | 618.26
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 653.57 | 0 | 1271.83 | 0 | 1271.83
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 713.18 | 0 | 1985.01 | 0 | 1985.01
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 800.93 | 0 | 2785.94 | 0 | 2785.94
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 845.51 | 0 | 3631.45 | 0 | 3631.45
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 1083.05 | 0 | 4714.5 | 0 | 4714.5
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 1241.08 | 0 | 5955.58 | 0 | 5955.58
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 1645.09 | 0 | 7600.67 | 0 | 7600.67
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 3018.93 | 0 | 10619.6 | 0 | 10619.6
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 3713.19 | 0 | 14332.79 | 0 | 14332.79
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 6505.12 | 0 | 20837.91 | 0 | 20837.91
G7MREG118 | REG 118 - 5th and Philadelphia | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG118 | REG 118 - 5th and Philadelphia | 28699.64 |  | 44469 | Felt | 0 | 7861.73 | 0 | 28699.64 | 0 | 28699.64
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 3632.89 | 0 | 3632.89 | 0 | 3632.89
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 4426.11 | 0 | 8059 | 0 | 8059
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 6066.86 | 0 | 14125.86 | 0 | 14125.86
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 13185.24 | 0 | 27311.1 | 0 | 27311.1
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 30444.48 | 0 | 57755.58 | 0 | 57755.58
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 56017.77 | 0 | 113773.35 | 0 | 113773.35
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 48248.35 | 0 | 162021.7 | 0 | 162021.7
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 60598.02 | 0 | 222619.72 | 0 | 222619.72
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 30348.78 | 0 | 252968.5 | 0 | 252968.5
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 6848.13 | 0 | 259816.63 | 0 | 259816.63
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 4758.71 | 0 | 264575.34 | 0 | 264575.34
G7MREG120 | (Cancel) REG 120 - 9th & Overton | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG120 | (Cancel) REG 120 - 9th & Overton | 264575.34 |  | 44073 | Wells | 0 | 0 | 0 | 264575.34 | 0 | 264575.34
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 176.7 | 0 | 176.7 | 0 | 176.7
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 187.18 | 0 | 363.88 | 0 | 363.88
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 205.22 | 0 | 569.1 | 0 | 569.1
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 216.07 | 0 | 785.17 | 0 | 785.17
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 234.86 | 0 | 1020.03 | 0 | 1020.03
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 275.03 | 0 | 1295.06 | 0 | 1295.06
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 304.54 | 0 | 1599.6 | 0 | 1599.6
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 352.63 | 0 | 1952.23 | 0 | 1952.23
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 436.12 | 0 | 2388.35 | 0 | 2388.35
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 507.32 | 0 | 2895.67 | 0 | 2895.67
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 712.21 | 0 | 3607.88 | 0 | 3607.88
G7MREG31 | REG 31 - 9th and York_Abandon | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MREG31 | REG 31 - 9th and York_Abandon | 4366.35 |  | 44499 | Wells | 0 | 758.47 | 0 | 4366.35 | 0 | 4366.35
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 44478.73 | 0 | 44478.73 | 0 | 44478.73 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 44478.74 | 0 | 44478.74 | 0 | 44478.74 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 471.09 | 0 | 44949.82 | 0 | 44949.82 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 471.09 | 0 | 44949.83 | 0 | 44949.83 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 66.39 | 0 | 45016.21 | 0 | 45016.21 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 66.39 | 0 | 45016.22 | 0 | 45016.22 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 22580.97 | 0 | 67597.18 | 0 | 67597.18 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 47.22 | 0 | 45063.44 | 0 | 45063.44 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 42.23 | 0 | 67639.41 | 0 | 67639.41 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 28.18 | 0 | 45091.62 | 0 | 45091.62 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 34.35 | 0 | 67673.76 | 0 | 67673.76 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 22.92 | 0 | 45114.54 | 0 | 45114.54 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 25.41 | 0 | 67699.17 | 0 | 67699.17 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 45114.54 | 0 | 45114.54 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 19.23 | 0 | 67718.4 | 0 | 67718.4 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 45114.54 | 0 | 45114.54 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 45.65 | 0 | 67764.05 | 0 | 67764.05 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 45114.54 | 0 | 45114.54 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 67764.05 | 0 | 67764.05 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 45114.54 | 0 | 45114.54 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1568 | Station 338 MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 67764.05 | 0 | 67764.05 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AW1569 | Station 286 Riley Road MR Upgrade | 0 |  | 44560 | Wells | 0 | 0 | 45114.54 | 0 | 45114.54 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 0 | 0 | 0 | 0 | 0
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 45489.19 | 0 | 45489.19 | 0 | 45489.19
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 45705.9 | 0 | 91195.09 | 0 | 91195.09
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 45812.33 | 0 | 137007.42 | 0 | 137007.42
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 45868.09 | 0 | 182875.51 | 0 | 182875.51
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 46034.67 | 0 | 228910.18 | 0 | 228910.18
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 44974.48 | 0 | 273884.66 | 0 | 273884.66
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 46328.87 | 0 | 320213.53 | 0 | 320213.53
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 46505.15 | 0 | 366718.68 | 0 | 366718.68
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 46665.94 | 0 | 413384.62 | 0 | 413384.62
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 46819.92 | 0 | 460204.54 | 0 | 460204.54
G7MRUPG | Kentucky MR Station Upgrades | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MRUPG | Kentucky MR Station Upgrades | 506025.87 |  | 45930 | Casstevens | 0 | 45821.33 | 0 | 506025.87 | 0 | 506025.87
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 7.1054e-14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 1.4211e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 2.558e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 8.5265e-14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | -1.9895e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 3.6948e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 3.5527e-14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 7.1054e-14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 32635.9 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 52728.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | 0 | 0 | 53265.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | -1280.91 | 0 | -1280.91 | 0 | 31354.99 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | -3833.96 | 0 | -3833.96 | 0 | 48894.45 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | -1260.77 | 0 | -1260.77 | 0 | 52005.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | -1.4211e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | -1280.91 | 0 | 31354.99 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | -3833.96 | 0 | 48894.45 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | -1260.77 | 0 | 52005.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3794 | REPLACE RTU AT CONS CAV/DB | 0 | 39294 | 39294 |  | 0 | 0 | 0 | 0 | 32779.14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4366 | ERLANGER UPGRADE CPU/DB | 0 | 40118 | 40178 |  | 0 | 0 | 0 | 0 | 25361.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5450 | RPL MISC VALVES/06-3510-2/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 12500.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5728 | RPL VAPORIZER/06-3511-0/DB | 0 | 39055 | 39055 |  | 0 | 0 | 0 | 0 | 54309.41 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7846 | REPL INST AIR COMP/DB | 0 | 39038 | 39038 |  | 0 | 0 | 0 | 0 | 16817.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9161 | ERLR INSTALL H20 SOFT/DZB | 0 | 39490 | 39490 |  | 0 | 0 | 0 | 0 | 6669.77 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9167 | ERLR RPL SHUTDN/DZB | 0 | 39325 | 39325 |  | 0 | 0 | 0 | 0 | 49678.24 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2753 | CONSTANCE CAVERN/DZB | 0 | 40717 | 40663 |  | 0 | 0 | 0 | 0 | 32641.57 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2775 | ERLANGER GAS PLANT/DZB | 0 | 39696 | 39696 |  | 0 | 0 | 0 | 0 | 30619.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2777 | CONSTANCE CAVERN/DZB | 0 |  | 40663 |  | 0 | 0 | 0 | 0 | 2.4158e-13 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3578 | INSTALL BOILER ERL/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 17840.16 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3676 | RPL 4 TO 8 IN PAUL 1 RUN/DZB | 0 | 39660 | 39660 |  | 0 | 0 | 0 | 0 | 18633.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6544 | Install backup generator at Erlange | 0 | 40664 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 14513.75 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6565 | Install heat trace tubing Constance | 0 |  | 42734 | Kemper | 0 | 0 | 0 | 0 | -1.7764e-14 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6566 | Inst no-flow pump cutoffs Constance | 0 | 40739 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 27720.58 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6567 | Inst flame detectors Constance Cav | 0 | 41090 | 41090 | Shoemaker | 0 | 0 | 0 | 0 | 6770.3 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F6571 | Inst Odorizer and Flame Det Erlange | 0 | 40831 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 143240.86 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0823 | Pneumatic guages Erlanger GP | 0 | 40543 | 40940 | Shoemaker | 0 | 0 | 0 | 0 | 4946.53 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1319 | Install MCCI at Erlanger GP | 0 | 40787 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 101857.5 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1322 | Replace Air Dryer Erlanger | 0 | 40585 | 40969 | Shoemaker | 0 | 0 | 0 | 0 | 24487.15 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4116 | LP-03 Erlanger KY | 0 | 40799 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 50186.96 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4181 | Replace F/L LP-03 under I-75 | 0 | 40858 | 41030 | Shoemaker | 0 | 0 | 0 | 0 | 271504.67 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5034 | LP-03 Launcher/Receiver | 0 | 41151 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 98708.55 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5035 | Replace arrestors Erlanger Gas Pl | 0 | 40880 | 40907 | Shoemaker | 0 | 0 | 0 | 0 | 2933.87 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7058 | F/L LP-03 Under I-275 | 0 | 41172 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 203497.54 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7059 | Constance Cavern Recondition | 0 | 41190 | 41152 | Shoemaker | 0 | 0 | 0 | 0 | 73260.84 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7254 | F/L LP-03 Launcher/Receiver Tie-ins | 0 | 41334 | 41320 | Shoemaker | 0 | 0 | 0 | 0 | 192839.97 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | I6105 | Replace Erlanger GP RTU's | 0 | 42064 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 166959.43 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | L4115 | Replace Control Valves at Constance | 0 | 41852 | 42004 | Shoemaker | 0 | 0 | -1280.91 | 0 | 31354.99 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6102 | Replace Compress 6&7 oil lube sys | 0 | 41926 | 42369 | Shoemaker | 0 | 0 | -3833.96 | 0 | 48894.45 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | M6103 | Erlanger GP Aftercooler Retube | 0 | 41933 | 42369 | Shoemaker | 0 | 0 | 0 | 0 | 86179.39 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P8054 | Replace BTU measurement at Erlanger | 0 | 42307 | 42307 | Shoemaker | 0 | 0 | -1260.77 | 0 | 52005.07 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P9839 | Erlanger STA 148 | 0 |  | 42248 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7MSCPRD | MISCELLANEOUS PRODUCTION | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R8744 | PLNT 10059137 Erlanger Propane | 0 |  | 42675 | Smith | 0 | 0 | 0 | 0 | 0 | 0
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 0 | 0 | 0 | 0 | 0
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 0 | 0 | 0 | 0 | 0
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35248.89 | 0 | 35248.89 | 0 | 35248.89
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35316.44 | 0 | 70565.33 | 0 | 70565.33
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35319.58 | 0 | 105884.91 | 0 | 105884.91
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35462.93 | 0 | 141347.84 | 0 | 141347.84
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 34051.42 | 0 | 175399.26 | 0 | 175399.26
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35699.51 | 0 | 211098.77 | 0 | 211098.77
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35854.41 | 0 | 246953.18 | 0 | 246953.18
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 35989.45 | 0 | 282942.63 | 0 | 282942.63
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 36115.58 | 0 | 319058.21 | 0 | 319058.21
G7MSRP | MSRP Service Line Program | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | RSERV-REPLACEMENT SERVICES | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7MSRP | MSRP Service Line Program | 353839.19 |  | 44561 | Casstevens | 0 | 34780.98 | 0 | 353839.19 | 0 | 353839.19
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7NOBNDR | NORTH BEND ROAD | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2336 | PP 447062/CHRIS LANGE | 0 | 39589 | 40261 | Shoemaker | 0 | 0 | 0 | 0 | 1500420.39 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 5568.99 | 0 | 5568.99 | 0 | 1426776.46 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 6810.32 | 0 | 12379.31 | 0 | 1433586.78 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 11183.12 | 0 | 23562.43 | 0 | 1444769.9 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 7458.78 | 0 | 31021.21 | 0 | 1452228.68 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 2149.09 | 0 | 33170.3 | 0 | 1454377.77 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 4519.2 | 0 | 37689.5 | 0 | 1458896.97 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 1348.96 | 0 | 39038.46 | 0 | 1460245.93 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 4870.13 | 0 | 43908.59 | 0 | 1465116.06 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 744.79 | 0 | 44653.38 | 0 | 1465860.85 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 1301.39 | 0 | 45954.77 | 0 | 1467162.24 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 1519.75 | 0 | 47474.52 | 0 | 1468681.99 | 0
G7PHMSA | PHMSA CRM Plan | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7283 | PHMSA CRM Plan | 0 |  | 44012 | Long | 338742.82 | 0 | 386217.34 | 0 | 1807424.81 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 6904.69 | 0 | 6904.69 | 0 | 887794.7 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 1336.61 | 0 | 8241.3 | 0 | 889131.31 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | -29518.83 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5310 | GROVE RD-PRE IMP/PPWo 75687/CL | 0 | 38777 | 38777 |  | 0 | 0 | 0 | 0 | 7983.07 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6033 | STA 769-INLET 06-1048-5/CWA | 0 | 38869 | 38869 | Shoemaker | 0 | 0 | 0 | 0 | 31308.89 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6034 | STA 769-OUTLET 06-1049-3/CWA | 0 | 38869 | 38869 |  | 0 | 0 | 0 | 0 | 14135.46 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2156 | 07-3665-2/LAURA MATE | 0 | 39506 | 39506 |  | 0 | 0 | 0 | 0 | 40635.06 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5747 | Legends Way | 0 | 39962 | 40178 |  | 0 | 0 | 0 | 0 | 63291.63 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7028 | Covington Ave Main Rplc | 0 | 40095 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 79987.62 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4955 | Carothers Rd Pres Imp | 0 | 41143 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 47551.9 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6396 | Turkeyfoot Rd @ Autumn | 0 | 41089 | 41093 | Shoemaker | 0 | 0 | 0 | 0 | 230467.53 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1640159 | ELIJAH CREEK PRESSURE IMPROVEMENT P | 0 | 43753 | 43797 | Helm | 0 | 0 | -21277.53 | 0 | 859612.48 | 0
G7PRESIM | PRESSURE IMPROVEMENTS | 75086 |  |  | SYSST-SYSTEM INFRASTRUCTURE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9177637 | INSTALL PRESSURE IMPROVEMENT PROJEC | 0 | 43468 | 43406 | Helm | 0 | 0 | 0 | 0 | 2373.24 | 0
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 0 | 0 | 0 | 0 | 0
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 0 | 0 | 0 | 0 | 0
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 19961.26 | 0 | 19961.26 | 0 | 19961.26
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20004.41 | 0 | 39965.67 | 0 | 39965.67
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20019.7 | 0 | 59985.37 | 0 | 59985.37
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20095.86 | 0 | 80081.23 | 0 | 80081.23
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 19497.26 | 0 | 99578.49 | 0 | 99578.49
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20226.64 | 0 | 119805.13 | 0 | 119805.13
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20308.01 | 0 | 140113.14 | 0 | 140113.14
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20380.78 | 0 | 160493.92 | 0 | 160493.92
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 20449.73 | 0 | 180943.65 | 0 | 180943.65
G7PRUPG | KY M&R Std Pressure Relief Upgrade | 75086 | Gas Ops - Technical Field Operations | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PRUPG | KY M&R Std Pressure Relief Upgrade | 200828.34 |  | 45930 | Casstevens | 0 | 19884.69 | 0 | 200828.34 | 0 | 200828.34
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | -5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 24311.81 | 0 | 24311.81 | 0 | 1879757.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 619.87 | 0 | 619.87 | 0 | 388317.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 0 | 0 | 486286.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 30756.42 | 0 | 30756.42 | 0 | 144035.66 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | -2.1316e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | 0 | 0 | 140660.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | 0 | 0 | 1123441.11 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 11910.71 | 0 | 11910.71 | 0 | -12136.94 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 56936.02 | 0 | 56936.02 | 0 | 77960.19 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 34.76 | 0 | 34.76 | 0 | 22196.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | 0 | 0 | 188941.56 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 362.82 | 0 | 362.82 | 0 | 226672.03 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 21457.8 | 0 | 21457.8 | 0 | 70802.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 5230.94 | 0 | 5230.94 | 0 | 190600.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 1.25 | 0 | 1.25 | 0 | 796.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 576.17 | 0 | 576.17 | 0 | 363474.94 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 70.51 | 0 | 70.51 | 0 | 70.51 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | 0 | 0 | 107234.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | 0 | 0 | 31414.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | 0 | 0 | 43227.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | -800.56 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 65724.65 | 0 | 65724.65 | 0 | 1295995.99 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 5728.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 282.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 2.6645e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | -1.1369e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 14090.77 | 0 | 38402.58 | 0 | 1893848.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | -48414.04 | 0 | -47794.17 | 0 | 339903.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | -1314.1 | 0 | -1314.1 | 0 | 484972.32 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 14289.01 | 0 | 45045.43 | 0 | 158324.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 1.279e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | -3502.29 | 0 | -3502.29 | 0 | 137158.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 1222.28 | 0 | 1222.28 | 0 | 1124663.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 909.7 | 0 | 12820.41 | 0 | -11227.24 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 18490.45 | 0 | 75426.47 | 0 | 96450.64 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 33.26 | 0 | 68.02 | 0 | 22229.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | 0 | 0 | 188941.56 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 3125.05 | 0 | 3487.87 | 0 | 229797.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 106.06 | 0 | 21563.86 | 0 | 70908.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5230.94 | 0 | 190600.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 1.19 | 0 | 2.44 | 0 | 797.82 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 3971.67 | 0 | 4547.84 | 0 | 367446.61 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 672.97 | 0 | 672.97 | 0 | 672.97 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 65.5 | 0 | 136.01 | 0 | 136.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | 0 | 0 | 107234.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | 0 | 0 | 31414.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | 0 | 0 | 43227.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 1694.49 | 0 | 67419.14 | 0 | 1297690.48 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 5728.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 282.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 8.6375e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 14268.45 | 0 | 52671.03 | 0 | 1908116.85 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 262.87 | 0 | -47531.3 | 0 | 340166.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | -11.11 | 0 | -1325.21 | 0 | 484961.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 6983.89 | 0 | 52029.32 | 0 | 165308.56 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 6.3949e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | -18.38 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | 1222.28 | 0 | 1124663.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 35294.71 | 0 | 48115.12 | 0 | 24067.47 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 6631.14 | 0 | 82057.61 | 0 | 103081.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 32.98 | 0 | 101 | 0 | 22262.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | -172164.31 | 0 | -172164.31 | 0 | 16777.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 362.85 | 0 | 3850.72 | 0 | 230159.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 484.58 | 0 | 22048.44 | 0 | 71392.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 57.9 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 1.18 | 0 | 3.62 | 0 | 799 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | -9050.46 | 0 | -4502.62 | 0 | 358396.15 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 7.12 | 0 | 680.09 | 0 | 680.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 70464.84 | 0 | 70600.85 | 0 | 70600.85 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | 0 | 0 | 107234.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | 0 | 0 | 31414.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | 0 | 0 | 43227.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 12563.14 | 0 | 79982.28 | 0 | 1310253.62 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 5728.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 282.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | -2.7311e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | -11405.74 | 0 | 41265.29 | 0 | 1896711.11 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 517.26 | 0 | -47014.04 | 0 | 340684.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | -1325.21 | 0 | 484961.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 19435.03 | 0 | 71464.35 | 0 | 184743.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | 1222.28 | 0 | 1124663.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | -279.14 | 0 | 47835.98 | 0 | 23788.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 80039.54 | 0 | 162097.15 | 0 | 183121.32 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 33.09 | 0 | 134.09 | 0 | 22296.02 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -172164.31 | 0 | 16777.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 349.53 | 0 | 4200.25 | 0 | 230509.46 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 5569.22 | 0 | 27617.66 | 0 | 76961.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 1.19 | 0 | 4.81 | 0 | 800.19 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 733.52 | 0 | -3769.1 | 0 | 359129.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 1 | 0 | 681.09 | 0 | 681.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 32767.13 | 0 | 103367.98 | 0 | 103367.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | -336 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | -1029.42 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | -121.56 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 6742.91 | 0 | 86725.19 | 0 | 1316996.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 5728.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | -3.979e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 282.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | -2.3093e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 13074 | 0 | 54339.29 | 0 | 1909785.11 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 367.92 | 0 | -46646.12 | 0 | 341051.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 87547.59 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 104097.32 | 0 | 175561.67 | 0 | 288840.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 2.8422e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | 1222.28 | 0 | 1124663.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 63 | 0 | 47898.98 | 0 | 23851.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 118853.74 | 0 | 280950.89 | 0 | 301975.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 2134.67 | 0 | 2268.76 | 0 | 24430.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 8578.34 | 0 | 8578.34 | 0 | 8578.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -172164.31 | 0 | 16777.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 248.61 | 0 | 4448.86 | 0 | 230758.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 62107.84 | 0 | 89725.5 | 0 | 139069.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 3922.99 | 0 | 3927.8 | 0 | 4723.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 383.88 | 0 | -3385.22 | 0 | 359513.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0.71 | 0 | 681.8 | 0 | 681.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 389.66 | 0 | 103757.64 | 0 | 103757.64 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | -61431.23 | 0 | 25293.96 | 0 | 1255565.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 5728.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 282.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 8.1823e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 9711 | 0 | 64050.29 | 0 | 1919496.11 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 219.57 | 0 | -46426.55 | 0 | 341271.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 54831.54 | 0 | 230393.21 | 0 | 343672.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | -2517.05 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 1993.46 | 0 | 49892.44 | 0 | 25844.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | -10115.78 | 0 | 270835.11 | 0 | 291859.28 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 2366.19 | 0 | 4634.95 | 0 | 26796.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 17642.08 | 0 | 26220.42 | 0 | 26220.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | 33172.83 | 0 | 33172.83 | 0 | 33172.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -172164.31 | 0 | 16777.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 148.37 | 0 | 4597.23 | 0 | 230906.44 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 20808.29 | 0 | 110533.79 | 0 | 159878.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 2062.43 | 0 | 5990.23 | 0 | 6785.61 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 229.1 | 0 | -3156.12 | 0 | 359742.65 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0.43 | 0 | 682.23 | 0 | 682.23 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 8839.8 | 0 | 112597.44 | 0 | 112597.44 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 1203.04 | 0 | 26497 | 0 | 1256768.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 5728.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | 0 | 0 | 282.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | -3.1863e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 4204 | 0 | 68254.29 | 0 | 1923700.11 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 178.62 | 0 | -46247.93 | 0 | 341450.12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 32417.71 | 0 | 262810.92 | 0 | 376090.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 6.3949e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 12.91 | 0 | 49905.35 | 0 | 25857.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 0 | 0 | 270835.11 | 0 | 291859.28 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 13.69 | 0 | 4648.64 | 0 | 26810.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 268.83 | 0 | 268.83 | 0 | 268.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 79555.42 | 0 | 105775.84 | 0 | 105775.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | 58099.09 | 0 | 91271.92 | 0 | 91271.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 145838.73 | 0 | -26325.58 | 0 | 162615.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 0 | 44082 | 44071 | Shelton | 3477.31 | 0 | 3477.31 | 0 | 3477.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 120.7 | 0 | 4717.93 | 0 | 231027.14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 8072.45 | 0 | 118606.24 | 0 | 167950.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 3.44 | 0 | 5993.67 | 0 | 6789.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 186.37 | 0 | -2969.75 | 0 | 359929.02 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0.35 | 0 | 682.58 | 0 | 682.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 25299.01 | 0 | 137896.45 | 0 | 137896.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | -69524.74 | 0 | -43027.74 | 0 | 1187243.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | -421.69 | 0 | -421.69 | 0 | 5306.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | -390.54 | 0 | -390.54 | 0 | -108.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 8.1712e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 1.3767e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 9785.97 | 0 | 78040.26 | 0 | 1933486.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 0 | 0 | -46247.93 | 0 | 341450.12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 141.41 | 0 | 262952.33 | 0 | 376231.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 9.55 | 0 | 49914.9 | 0 | 25867.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 3252.75 | 0 | 274087.86 | 0 | 295112.03 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 10.12 | 0 | 4658.76 | 0 | 26820.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 5379.78 | 0 | 5648.61 | 0 | 5648.61 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 36304.14 | 0 | 142079.98 | 0 | 142079.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | 56271.18 | 0 | 147543.1 | 0 | 147543.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -26325.58 | 0 | 162615.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 0 | 44082 | 44071 | Shelton | 8188.72 | 0 | 11666.03 | 0 | 11666.03 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 0 | 0 | 4717.93 | 0 | 231027.14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 63.17 | 0 | 118669.41 | 0 | 168013.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 2.55 | 0 | 5996.22 | 0 | 6791.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 137.85 | 0 | -2831.9 | 0 | 360066.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0 | 0 | 682.58 | 0 | 682.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 10234.8 | 0 | 148131.25 | 0 | 148131.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -43027.74 | 0 | 1187243.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -421.69 | 0 | 5306.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | -1.7053e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -390.54 | 0 | -108.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 28799.22 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | -5.9952e-15 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | 0 | 0 | 133786.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 1173.27 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 119314.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | -8.5265e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | 0 | 0 | 154059.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 2758.8 | 0 | 80799.06 | 0 | 1936244.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 0 | 0 | -46247.93 | 0 | 341450.12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 107.04 | 0 | 263059.37 | 0 | 376338.61 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | -4.2633e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 7.23 | 0 | 49922.13 | 0 | 25874.48 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 4173.51 | 0 | 278261.37 | 0 | 299285.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | -3.92 | 0 | 4654.84 | 0 | 26816.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 36590.32 | 0 | 42238.93 | 0 | 42238.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 5941.58 | 0 | 148021.56 | 0 | 148021.56 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | -21.62 | 0 | 147521.48 | 0 | 147521.48 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -26325.58 | 0 | 162615.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 0 | 44082 | 44071 | Shelton | 47870.25 | 0 | 59536.28 | 0 | 59536.28 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 0 | 0 | 4717.93 | 0 | 231027.14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | -24.45 | 0 | 118644.96 | 0 | 167989.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 1.93 | 0 | 5998.15 | 0 | 6793.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 104.34 | 0 | -2727.56 | 0 | 360171.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0 | 0 | 682.58 | 0 | 682.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 24197.63 | 0 | 172328.88 | 0 | 172328.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | 0 | 0 | 249427.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | 0 | 0 | 10960.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 75716.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | 0 | 0 | 76819.78 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -43027.74 | 0 | 1187243.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -421.69 | 0 | 5306.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 2.8422e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -390.54 | 0 | -108.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | -336.56 | 0 | -336.56 | 0 | 28462.66 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | -590.29 | 0 | -590.29 | 0 | 133196.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | -41.5 | 0 | -41.5 | 0 | 1131.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | -245.2 | 0 | -245.2 | 0 | 119069.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | -472.76 | 0 | -472.76 | 0 | 153586.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 14608.35 | 0 | 95407.41 | 0 | 1950853.23 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 0 | 0 | -46247.93 | 0 | 341450.12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | -11638.77 | 0 | 251420.6 | 0 | 364699.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 17.16 | 0 | 49939.29 | 0 | 25891.64 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 4244.38 | 0 | 282505.75 | 0 | 303529.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 1746.32 | 0 | 6401.16 | 0 | 28563.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 13119.14 | 0 | 55358.07 | 0 | 55358.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | -2547.79 | 0 | 145473.77 | 0 | 145473.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | 311092.92 | 0 | 458614.4 | 0 | 458614.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -26325.58 | 0 | 162615.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 0 | 44082 | 44071 | Shelton | 17481.55 | 0 | 77017.83 | 0 | 77017.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 0 | 0 | 4717.93 | 0 | 231027.14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | -3317.87 | 0 | 115327.09 | 0 | 164671.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 4.57 | 0 | 6002.72 | 0 | 6798.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | -2727.56 | 0 | 360171.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0 | 0 | 682.58 | 0 | 682.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 13449.04 | 0 | 185777.92 | 0 | 185777.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | -2442.37 | 0 | -2442.37 | 0 | 246985.2 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | -320.09 | 0 | -320.09 | 0 | 10640.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | -4891.56 | 0 | -4891.56 | 0 | 70824.99 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | -8797.74 | 0 | -8797.74 | 0 | 68022.04 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -43027.74 | 0 | 1187243.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -421.69 | 0 | 5306.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -390.54 | 0 | -108.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | -336.56 | 0 | 28462.66 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 1.7764e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | -590.29 | 0 | 133196.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | -41.5 | 0 | 1131.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | -245.2 | 0 | 119069.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | -472.76 | 0 | 153586.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 3355.65 | 0 | 98763.06 | 0 | 1954208.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 0 | 0 | -46247.93 | 0 | 341450.12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 373.24 | 0 | 251793.84 | 0 | 365073.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 26.03 | 0 | 49965.32 | 0 | 25917.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 4160.09 | 0 | 286665.84 | 0 | 307690.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 1.77 | 0 | 6402.93 | 0 | 28564.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 1429.81 | 0 | 56787.88 | 0 | 56787.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 33056.65 | 0 | 178530.42 | 0 | 178530.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | -3038.23 | 0 | 455576.17 | 0 | 455576.17 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -26325.58 | 0 | 162615.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 0 | 44082 | 44071 | Shelton | 12079.86 | 0 | 89097.69 | 0 | 89097.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 0 | 0 | 4717.93 | 0 | 231027.14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | -2.84 | 0 | 115324.25 | 0 | 164668.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 6.94 | 0 | 6009.66 | 0 | 6805.04 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | -2727.56 | 0 | 360171.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0 | 0 | 682.58 | 0 | 682.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 50417.71 | 0 | 236195.63 | 0 | 236195.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | -2442.37 | 0 | 246985.2 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | -320.09 | 0 | 10640.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | -4891.56 | 0 | 70824.99 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | -8797.74 | 0 | 68022.04 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -43027.74 | 0 | 1187243.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -421.69 | 0 | 5306.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | -4.5475e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 1044.26 | 0 | 1044.26 | 0 | 1044.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -390.54 | 0 | -108.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30323 | GRANDVIEW/GJH | 0 | 35520 | 35520 | Shoemaker | 25.16 | 0 | 25.16 | 0 | 25.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30936 | LICKING PIKE AT BANK/DLS | 0 | 36446 | 36446 |  | 0 | 0 | 0 | 0 | -20 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 34425 | FROGTOWN-RICHWOOD/WRP | 0 | 36595 | 36595 |  | 0 | 0 | 0 | 0 | 12967.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A5943 | WATER WORKS RD BRIDGE/WJR | 0 | 39708 | 39994 | Shoemaker | 0 | 0 | 0 | 0 | 220888 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8717 | TURKEYFOOT RD/CWA | 0 | 38281 | 38281 |  | 0 | 0 | 0 | 0 | 96604.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B2088 | 00-7015-1/CWA | 0 | 39358 | 39358 | Shoemaker | 0 | 0 | 0 | 0 | 381071.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4365 | PPWO 00237829/BILL ROTH | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 282689.37 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4491 | PPWO 00510044/C W AMPFER | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 142042.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | B4493 | PPWO 00510493/C W AMPFER | 0 | 38938 | 38938 |  | 0 | 0 | 0 | 0 | -8312.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1220 | KY-1017-TURFWAY-PP 419552/CWA | 0 | 39020 | 39020 | Brown | 0 | 0 | 0 | 0 | 414935.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2825 | TURKEYFOOT RD/PPWO 419589/CL | 0 | 39374 | 39374 | Shoemaker | 0 | 0 | 0 | 0 | 584925.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2928 | KY 17 UL7 419-00/PP 712423/CL | 0 | 39331 | 39331 | Shoemaker | 0 | 0 | 0 | 0 | 176929.08 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2929 | KY 17-STA 419-00/PP 698497/CL | 0 | 39331 | 39331 |  | 0 | 0 | 0 | 0 | 125269.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6588 | DAYTON FLOOD WALL/BR | 0 | 38855 | 38855 |  | 0 | 0 | 0 | 0 | 53818.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6676 | KENNEDY RD- IMP/PPW00803919/JB | 0 | 38898 | 38898 | Shoemaker | 0 | 0 | 0 | 0 | 30693.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7361 | BN CTY PUB LIB/PPW00818847/CL | 0 | 38916 | 38916 |  | 0 | 0 | 0 | 0 | 6016.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8630 | PP 829756/JOHN BETSCH | 0 | 39240 | 39240 |  | 0 | 0 | 0 | 0 | 54018.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9131 | PP620440/JOHN BETSCH | 0 | 39188 | 40178 | Shoemaker | 0 | 0 | -336.56 | 0 | 28462.66 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9267 | PP 452152/WRP | 0 | 39659 | 39659 | Shoemaker | 0 | 0 | 0 | 0 | 397158.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9298 | PP 880993/RALPH PFISTER | 0 | 39141 | 39141 |  | 0 | 0 | 0 | 0 | 12479.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9823 | PP825693/JOHN BETSCH | 0 | 39274 | 39274 |  | 0 | 0 | 0 | 0 | 26069.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9919 | 877813/CHRIS LANGE | 0 | 39289 | 39289 | Shoemaker | 0 | 0 | 0 | 0 | 178342.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1026 | PP898326/LLM | 0 | 39406 | 39406 |  | 0 | 0 | 0 | 0 | -1896.1 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1073 | 913105/JOHN BETSCH | 0 | 39307 | 39307 |  | 0 | 0 | 0 | 0 | -1221.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1323 | PP908965/LAURA MATE | 0 | 39324 | 39324 |  | 0 | 0 | 0 | 0 | 64697.13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1816 | PP830191/Laura Mate | 0 | 39470 | 39470 | Shoemaker | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2337 | PP495735/LAURA MATE | 0 | 40017 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 357566.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3033 | PP 848340/LAURA MATE | 0 | 39549 | 39549 |  | 0 | 0 | 0 | 0 | 56245.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3153 | PP 825665/LAURA MATE | 0 | 39575 | 39575 |  | 0 | 0 | 0 | 0 | 26874.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3214 | GRANDVIEW AVE close to C6457 | 0 | 38946 | 38946 | Shoemaker | 0 | 0 | 0 | 0 | 99191.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3215 | WALDEN LN close to C6341 | 0 | 38965 | 38965 | Shoemaker | 0 | 0 | 0 | 0 | 6985.16 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3216 | WESLY HLS close to C6343 | 0 | 38981 | 38981 | Shoemaker | 0 | 0 | 0 | 0 | 51140.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3243 | PP 983364/ LLM | 0 | 39556 | 39556 |  | 0 | 0 | 0 | 0 | 92775.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3381 | PP 982824/LLM | 0 | 39590 | 39590 |  | 0 | 0 | 0 | 0 | 19372.63 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3411 | PP 967867/LLM | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 37.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3413 | PP 980245/LAURA MATE | 0 | 39623 | 39623 |  | 0 | 0 | 0 | 0 | 55070.45 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3414 | PP 967604/LAURA MATE | 0 | 39688 | 39688 | Shoemaker | 0 | 0 | -590.29 | 0 | 133196.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3478 | PP 978790 LLM | 0 | 39674 | 39674 |  | 0 | 0 | 0 | 0 | 14748.53 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0002 | BRECKENRIDGE RD | 0 | 39653 | 39813 |  | 0 | 0 | 0 | 0 | 12649.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0125 | Lawrence Dr | 0 | 39660 | 39752 |  | 0 | 0 | 0 | 0 | 19656.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0294 | Hilton Dr | 0 | 39675 | 39813 | Shoemaker | 0 | 0 | -41.5 | 0 | 1131.77 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0916 | KY 17 Moreland Property | 0 | 39785 | 40178 |  | 0 | 0 | 0 | 0 | 38679.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1221 | Brookwood Dr Edgewood | 0 | 39742 | 40178 |  | 0 | 0 | 0 | 0 | 119705.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E1596 | Grand Ave Main Recloc Newport | 0 | 39759 | 40178 |  | 0 | 0 | 0 | 0 | 6801.4 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4594 | Rogers Rd Villa Hills | 0 | 39988 | 40178 | Shoemaker | 0 | 0 | -245.2 | 0 | 119069.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E5484 | Dry Creek LP03 Relocation | 0 | 39974 | 40543 |  | 0 | 0 | 0 | 0 | 26929.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6024 | Spillman Dr | 0 | 39965 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 78454.86 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6124 | Idlewild Rd | 0 |  | 40634 |  | 0 | 0 | 0 | 0 | -1.4211e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6264 | Conrad Ln / North Bend Rd | 0 | 39969 | 40178 |  | 0 | 0 | 0 | 0 | 35480.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E6947 | East Drive/Ft Mitchell | 0 | 40072 | 40178 |  | 0 | 0 | 0 | 0 | 30829.5 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8264 | Vidot Court | 0 | 40061 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 21606.74 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E8645 | Newport Pavilion | 0 | 40113 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 63311.69 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | F1504 | S.R. 35 Warsaw | 0 | 40123 | 40178 |  | 0 | 0 | 0 | 0 | 6015.35 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0795 | Edgecliff Rd | 0 | 40554 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 34801.42 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0796 | Hay & Willow Sts | 0 | 40434 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 27141.92 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0899 | Barnes Rd | 0 | 40962 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 116255.54 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0965 | Johns Hill Rd | 0 | 41073 | 41183 | Shoemaker | 0 | 0 | 0 | 0 | 208450.83 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1874 | Pleasant Ridge Ave | 0 | 41023 | 40664 | Shoemaker | 0 | 0 | 0 | 0 | 86486.3 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1877 | Comair Blvd - DHL Expansion | 0 | 40677 | 40983 | Shoemaker | 0 | 0 | 0 | 0 | 250687.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2527 | Silver Ave | 0 | 40644 | 40693 | Shoemaker | 0 | 0 | 0 | 0 | 105642.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | 147600.33 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3515 | Orland Drive | 0 | 40722 | 41029 | Shoemaker | 0 | 0 | 0 | 0 | 52698.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4496 | KY 22 Bridge | 0 | 41193 | 41187 | Shoemaker | 0 | 0 | 0 | 0 | 204518.7 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4998 | Summit Dr | 0 | 41000 | 40967 | Shoemaker | 0 | 0 | 0 | 0 | 73079.06 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G6413 | Mall Rd Kroger Marketplace | 0 | 41440 | 41517 | Shoemaker | 0 | 0 | 0 | 0 | 31396.01 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8241 | Sunset Drive - Three Mile Rd Imp | 0 | 42313 | 42216 | Shoemaker | 0 | 0 | -472.76 | 0 | 153586.93 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8242 | AM00 - NKU | 0 | 42320 | 42794 | Shoemaker | 0 | 0 | 0 | 0 | 158981.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9648 | Pleasant Ridge Ave | 0 | 41452 | 41456 | Shoemaker | 0 | 0 | 0 | 0 | 210003.96 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0260 | Langview Dr, Wilder KY | 0 | 41492 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 39661.05 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | J0107 | Upland Ave | 0 | 41759 | 41740 | Shoemaker | 0 | 0 | 0 | 0 | 35903.89 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0783884 | Pleasant Valley Road/Camp Ernst Roa | 0 | 43395 | 43332 | Johnson | 0 | 0 | 98763.06 | 0 | 1954208.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0790794 | Arlington Rd. Roadway IMP | 0 | 43277 | 43187 | Helm | 0 | 0 | -46247.93 | 0 | 341450.12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0976110 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43362 | 43311 | Helm | 0 | 0 | 86222.38 | 0 | 572508.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 305.23 | 0 | 252099.07 | 0 | 365378.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1761035 | WENDELL H. FORD BLVD. | 0 | 43617 | 43581 | Helm | 0 | 0 | 0 | 0 | -14929.49 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2232746 | Bunning Lane Relocation | 0 |  | 43000 | Kuisti | 0 | 0 | 0 | 0 | -4.9738e-14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2362841 | AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | 0 | 43305 | 43248 | Helm | 0 | 0 | -3520.67 | 0 | 137140.07 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2541899 | KY-36/I-75 Interchange Reconstruct | 0 | 43314 | 43164 | Helm | 0 | 0 | -1294.77 | 0 | 1122146.34 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2624631 | Ewing BlvdI STREET IMPROVEMENT PROJ | 0 | 43839 | 43798 | Helm | 0 | 0 | 49965.32 | 0 | 25917.67 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2698762 | DOH PENDELTON/CAMPBELL INSTALL STRE | 0 | 43931 | 43875 | Helm | 1332.24 | 0 | 287998.08 | 0 | 309022.25 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX2911494 | UL 35 STREET IMPROVEMENT PROJECT | 0 | 43997 | 43749 | Helm | 1.45 | 0 | 6404.38 | 0 | 28566.31 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 0 | 0 | 56787.88 | 0 | 56787.88 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6477976 | CAMP ERNST STREET IMPROVEMENT PROJE | 0 | 44117 | 43994 | Helm | 1110.15 | 0 | 179640.57 | 0 | 179640.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6628393 | Pleasant Valley 2020 Relocation | 0 | 44060 | 44043 | Johnson | 2753.67 | 0 | 458329.84 | 0 | 458329.84 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6770232 | KYTC-06-0412.00 RICE PK & U.S.42 ST | 0 | 43306 | 43210 | Helm | 0 | 0 | -26325.58 | 0 | 162615.98 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7035169 | BUTTERMILK PIKE STREET IMPROVEMENT | 0 | 44082 | 44071 | Shelton | 9799.25 | 0 | 98896.94 | 0 | 98896.94 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7507727 | MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 0 | 43307 | 43245 | Helm | 0 | 0 | 4717.93 | 0 | 231027.14 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | -1.89 | 0 | 115322.36 | 0 | 164666.66 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7625297 | STREET IMPROVEMENT PROJECT KY-338 J | 0 |  | 43245 | Helm | 0 | 0 | 0 | 0 | 15741.57 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7720357 | BEECHWOOD RD STREET IMPROVEMENT PRO | 0 | 43649 | 43570 | Helm | 0 | 0 | 5288.84 | 0 | 190658.79 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8175168 | Cancel BUTTERMILK PIKE STR IMPROV | 0 |  | 44196 | Helm | 0 | 0 | 6009.66 | 0 | 6805.04 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | -2727.56 | 0 | 360171.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8840782 | Cancel INSTALL STREET IMPROVEMENT | 0 |  | 43371 | Helm | 0 | 0 | 682.58 | 0 | 682.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9244894 | MT.ZION RD KY536 STI | 0 | 44314 | 44196 | Helm | 6087.8 | 0 | 242283.43 | 0 | 242283.43 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9936962 | E. 9TH ST.COVINGTON STREET IMPROVEM | 0 | 43617 | 43591 | Helm | 0 | 0 | 0 | 0 | 26327.73 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | N8164 | Summit Lane | 0 | 41836 | 41852 | Shoemaker | 0 | 0 | 0 | 0 | 136958.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | O4165 | Dudley Rd Improvement | 0 | 41852 | 41883 | Perkins | 0 | 0 | -336 | 0 | 106898.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6167 | Kyles Ln. @ Dixie Hwy Ft. Wright | 0 | 42129 | 42124 | Shoemaker | 0 | 0 | -2442.37 | 0 | 246985.2 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6497 | Hayes Station Rd | 0 | 41887 | 41922 | Shoemaker | 0 | 0 | -320.09 | 0 | 10640.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 14736.75 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6551 | Dudley Rd - Relocation for Storm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | -4891.56 | 0 | 70824.99 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7280 | GRAND AT FLORENCE ROADWAY IMPROVEME | 0 | 42083 | 42088 | Shoemaker | 0 | 0 | -8797.74 | 0 | 68022.04 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R5767 | GO 8346362 KY 9 North recon | 0 | 42472 | 43190 | Perkins | 0 | 0 | 0 | 0 | 89216.71 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6768 | STI 9359472 Robbins Ave | 0 | 42475 | 42551 | Perkins | 0 | 0 | -1029.42 | 0 | 30385.39 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S1056 | STI 10177360 Latonia Lakes Str Impr | 0 | 42539 | 42582 | Perkins | 0 | 0 | 0 | 0 | 95084.72 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S4545 | STI 10221124 Altavia Ave | 0 | 42535 | 42582 | Perkins | 0 | 0 | -121.56 | 0 | 43106.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S7874 | STI 4844778 Thomas More Pkwy | 0 | 42646 | 42735 | Perkins | 0 | 0 | -800.56 | 0 | 69933.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8820 | STI 10670525 Edgewood & Lyndale | 0 | 42618 | 42629 | Perkins | 0 | 0 | 0 | 0 | 283030.52 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -43027.74 | 0 | 1187243.6 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S9644 | STI 11229534 Lyndale Rd | 0 | 42809 | 42794 | Perkins | 0 | 0 | 0 | 0 | 193547.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8343 | STI 20956764 Weaver Rd. | 0 | 42976 | 43132 | Reynolds | 0 | 0 | 0 | 0 | 6482.81 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | P6538 | Ky 9 Reconstruction-South | 0 | 42439 | 42339 | Shoemaker | 0 | 0 | 0 | 0 | 1.29 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -421.69 | 0 | 5306.58 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | G2573 | S Airfield Connector | 0 | 40849 | 41091 | Shoemaker | 0 | 0 | 0 | 0 | -1.7053e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1376296 | Longbranch Rd. | 0 | 43997 | 43805 | Helm | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX3298765 | RIDGE RD. & WEST ORCHARD FT MITCHEL | 0 | 44117 | 44092 | Shelton | 386.09 | 0 | 386.09 | 0 | 386.09 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX7599942 | INSTALL STREET IMPROVEMENT PROJECT | 0 | 43798 | 43798 | Helm | 0 | 0 | 1044.26 | 0 | 1044.26 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX8760866 | WKIP ROADWAY IMPROVEMENT JONES RD | 0 | 43407 | 43371 | Helm | 0 | 0 | 0 | 0 | 4.91 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  |  | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | S8867 | STI 10873483 Mt Zion Rd | 0 | 43729 | 43769 | Perkins | 0 | 0 | -390.54 | 0 | -108.21 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 5.457e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 1.819e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | -1.5916e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | -1.819e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 4.0927e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | -4.5475e-13 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | -7.6739e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 3.638e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 1.1937e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | -5.457e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 0 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6341 | WALDEN LN/PPW792831/DS | 0 | 38965 | 38965 |  | 0 | 0 | 0 | 0 | 77689.38 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6343 | WESLY HLS/PPW792837/DS | 0 | 38981 | 38981 |  | 0 | 0 | 0 | 0 | 4.2775e-12 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2006 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6457 | GRANDVIEW AVE/RPL/CEX/DS | 0 | 38946 | 38946 |  | 0 | 0 | 0 | 0 | 302015.18 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9974 | 900138/JOHN BETSCH | 0 | 39332 | 39332 | Shoemaker | 0 | 0 | 0 | 0 | 65532.59 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9986 | 899477/DAN SCHULER | 0 | 39296 | 39296 | Shoemaker | 0 | 0 | 0 | 0 | 86815.95 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2007 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D1057 | 902784/LAURA MATE | 0 | 39301 | 39301 | Shoemaker | 0 | 0 | 0 | 0 | 77087.8 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | 0 | 0 | 90301.87 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | -263.05 | 0 | -263.05 | 0 | 90038.82 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | -263.05 | 0 | 90038.82 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3299 | PP 978761/LLM | 0 | 39587 | 39587 | Shoemaker | 0 | 0 | -263.05 | 0 | 90038.82 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 |  | 2008 | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D3344 | PP 959891/ LLM | 0 | 39713 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 833510.55 | 0
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 108566.7 | 0 | 108566.7 | 0 | 108566.7
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 208025.98 | 0 | 316592.68 | 0 | 316592.68
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 203518.29 | 0 | 520110.97 | 0 | 520110.97
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 189338.61 | 0 | 709449.58 | 0 | 709449.58
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 22264.28 | 0 | 731713.86 | 0 | 731713.86
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 97207.42 | 0 | 828921.28 | 0 | 828921.28
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 186413.77 | 0 | 1015335.05 | 0 | 1015335.05
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 68317.43 | 0 | 1083652.48 | 0 | 1083652.48
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 304992.35 | 0 | 1388644.83 | 0 | 1388644.83
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 232555.44 | 0 | 1621200.27 | 0 | 1621200.27
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 122846.67 | 0 | 1744046.94 | 0 | 1744046.94
G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | GRELO-GOVERNMENT RELOCATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUBIMP | PUBLIC IMPROVEMENTS Pools | 1920705.86 |  | 55153 | Fritsch | 0 | 176658.92 | 0 | 1920705.86 | 0 | 1920705.86
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 14950.76 | -225 | 14950.76 | -225 | 1119520.43 | -225
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 115345.95 | 0 | 115345.95 | 0 | 6429820.19 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 80648.8 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 3323.25 | -225 | 18274.01 | -450 | 1122843.68 | -450
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 221237.55 | 0 | 336583.5 | 0 | 6651057.74 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 25717.51 | 0 | 25717.51 | 0 | 106366.31 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 339.07 | -225 | 18613.08 | -675 | 1123182.75 | -675
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 167451.93 | 0 | 504035.43 | 0 | 6818509.67 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 15845.2 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 11771.85 | -225 | 30384.93 | -900 | 1134954.6 | -900
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 45097.16 | 0 | 549132.59 | 0 | 6863606.83 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 6715.71 | -225 | 37100.64 | -1125 | 1141670.31 | -1125
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 20686.5 | 0 | 569819.09 | 0 | 6884293.33 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 31403.24 | -225 | 68503.88 | -1350 | 1173073.55 | -1350
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 98372.63 | 0 | 668191.72 | 0 | 6982665.96 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 447.51 | -225 | 68951.39 | -1575 | 1173521.06 | -1575
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 49114.98 | 0 | 717306.7 | 0 | 7031780.94 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 196.43 | -225 | 69147.82 | -1800 | 1173717.49 | -1800
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 27778.63 | 0 | 745085.33 | 0 | 7059559.57 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 21585.47 | -225 | 90733.29 | -2025 | 1195302.96 | -2025
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 147426.66 | 0 | 892511.99 | 0 | 7206986.23 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 17797.67 | -225 | 108530.96 | -2250 | 1213100.63 | -2250
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 108111.47 | 0 | 1000623.46 | 0 | 7315097.7 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 41562.71 | 0 | 122211.51 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 976.54 | -225 | 109507.5 | -2475 | 1214077.17 | -2475
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 112048.41 | 0 | 1112671.87 | 0 | 7427146.11 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 26853.19 | 0 | 68415.9 | 0 | 149064.7 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | INSREGREL | Install or Remove Regulator/Relief | -2700 |  | 55153 | Shoemaker | 8705.94 | -225 | 118213.44 | -2700 | 1222783.11 | -2700
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 88050.77 | 0 | 1200722.64 | 0 | 7515196.88 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2904 | MTR 11540114 1 Carbon Way | 0 |  | 43371 | Shoemaker | 0 | 0 | 0 | 0 | 2076.22 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | INSREGREL | Install or Remove Regulator/Relief | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 7859.37 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 37018.1 | 0 | 105434 | 0 | 186082.8 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | SETMETER | Set or Remove Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 94227.83 | 0 | 94227.83 | 0 | 94227.83
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 101308.64 | 0 | 195536.47 | 0 | 195536.47
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 102674.62 | 0 | 298211.09 | 0 | 298211.09
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 101950.21 | 0 | 400161.3 | 0 | 400161.3
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 102180.09 | 0 | 502341.39 | 0 | 502341.39
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 101663.47 | 0 | 604004.86 | 0 | 604004.86
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 97968.22 | 0 | 701973.08 | 0 | 701973.08
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 102188.76 | 0 | 804161.84 | 0 | 804161.84
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 102267.54 | 0 | 906429.38 | 0 | 906429.38
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 102290.14 | 0 | 1008719.52 | 0 | 1008719.52
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 101719.8 | 0 | 1110439.32 | 0 | 1110439.32
G7PUINEW | Purchase & Install M&R Exp BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINEW | Purchase & Install M&R Exp BLANKET | 1208104.01 |  | 55153 | Fritsch | 0 | 97664.69 | 0 | 1208104.01 | 0 | 1208104.01
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -2500 | 6567689.48 | -2500
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 2791.67 | 0 | 2791.67 | 0 | 474511.52 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 3938.55 | 0 | 3938.55 | 0 | 4689934.08 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 3224.02 | 0 | 3224.02 | 0 | 2380149.12 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 151005.2 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -5000 | 6567689.48 | -5000
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 5788.4 | 0 | 8580.07 | 0 | 480299.92 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 26900.4 | 0 | 30838.95 | 0 | 4716834.48 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 2256.61 | 0 | 5480.63 | 0 | 2382405.73 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 151005.2 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -7500 | 6567689.48 | -7500
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 8942.18 | 0 | 17522.25 | 0 | 489242.1 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 18460.27 | 0 | 49299.22 | 0 | 4735294.75 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 60833.67 | 0 | 66314.3 | 0 | 2443239.4 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 499.88 | 0 | 499.88 | 0 | 151505.08 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | -3.5527e-14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -10000 | 6567689.48 | -10000
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 6915.8 | 0 | 24438.05 | 0 | 496157.9 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 11145.36 | 0 | 60444.58 | 0 | 4746440.11 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 507.58 | 0 | 66821.88 | 0 | 2443746.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 499.88 | 0 | 151505.08 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -12500 | 6567689.48 | -12500
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 6042.21 | 0 | 30480.26 | 0 | 502200.11 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 5428.17 | 0 | 65872.75 | 0 | 4751868.28 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 2108.91 | 0 | 68930.79 | 0 | 2445855.89 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 499.88 | 0 | 151505.08 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -15000 | 6567689.48 | -15000
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 4850.27 | 0 | 35330.53 | 0 | 507050.38 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 6053.66 | 0 | 71926.41 | 0 | 4757921.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 1645.88 | 0 | 70576.67 | 0 | 2447501.77 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 448.25 | 0 | 948.13 | 0 | 151953.33 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -17500 | 6567689.48 | -17500
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 5899.08 | 0 | 41229.61 | 0 | 512949.46 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 3425.9 | 0 | 75352.31 | 0 | 4761347.84 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 2288.93 | 0 | 72865.6 | 0 | 2449790.7 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 948.13 | 0 | 151953.33 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | -3.5527e-14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -20000 | 6567689.48 | -20000
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 2187.09 | 0 | 43416.7 | 0 | 515136.55 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 46418.39 | 0 | 121770.7 | 0 | 4807766.23 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 14957.91 | 0 | 87823.51 | 0 | 2464748.61 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 948.13 | 0 | 151953.33 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | -3.5527e-14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -22500 | 6567689.48 | -22500
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 2544.55 | 0 | 45961.25 | 0 | 517681.1 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 48756.86 | 0 | 170527.56 | 0 | 4856523.09 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 158332.14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 30645.26 | 0 | 118468.77 | 0 | 2495393.87 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 1056.91 | 0 | 2005.04 | 0 | 153010.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | -3.5527e-14 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -25000 | 6567689.48 | -25000
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 4899.63 | 0 | 50860.88 | 0 | 522580.73 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 55156.18 | 0 | 225683.74 | 0 | 4911679.27 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | -16.06 | 0 | -16.06 | 0 | 158316.08 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 44457.39 | 0 | 162926.16 | 0 | 2539851.26 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 2005.04 | 0 | 153010.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -27500 | 6567689.48 | -27500
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 2987.85 | 0 | 53848.73 | 0 | 525568.58 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 47956.26 | 0 | 273640 | 0 | 4959635.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | -5.82 | 0 | -21.88 | 0 | 158310.26 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 36266.4 | 0 | 199192.56 | 0 | 2576117.66 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 2005.04 | 0 | 153010.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 540780.24 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28062 | PURCHASE NEW METERS | -30000 | 42004 | 55153 | Clippinger | 0 | -2500 | 0 | -30000 | 6567689.48 | -30000
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28063 | PURCHASE NEW GAS REGULATORS | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 2461204.41 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28064 | TO INCLUDE ALL LABOR MATERIALS AND | 0 | 42004 | 55153 | Clippinger | 0 | 0 | 0 | 0 | 7581294.83 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 78062 | GAS METERS | 0 |  | 55153 | Clippinger | 0 | 0 | 0 | 0 | -1434.98 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 4512.26 | 0 | 58360.99 | 0 | 530080.84 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 39594.87 | 0 | 313234.87 | 0 | 4999230.4 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | -0.57 | 0 | -22.45 | 0 | 158309.69 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGMTRSM | Change Small Meter Kentucky | 0 |  | 55153 | Shoemaker | 29731.24 | 0 | 228923.8 | 0 | 2605848.9 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | -1.71 | 0 | 2003.33 | 0 | 153008.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5920 | Meters - Replacement | 0 |  | 41274 | Clippinger | 0 | 0 | 0 | 0 | 140049.76 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGLG | Kentucky Age Change Large Meter | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2007.94 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | AGECHGSM | Kentucky Age Change Small Meter | 0 |  | 55153 | Shoemaker | 2606.96 | 0 | 2606.96 | 0 | 543387.2 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGMTRLG | Change Large Meter Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 6649.53 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2424.44 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 |  |  | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | CHGREGREL | Change Regulator/Relief Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.37 | 0 | 135833.37 | 0 | 135833.37
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 271666.7 | 0 | 271666.7
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 407500.03 | 0 | 407500.03
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 543333.36 | 0 | 543333.36
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 679166.69 | 0 | 679166.69
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 815000.02 | 0 | 815000.02
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 950833.35 | 0 | 950833.35
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 1086666.68 | 0 | 1086666.68
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 1222500.01 | 0 | 1222500.01
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 1358333.34 | 0 | 1358333.34
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 1494166.67 | 0 | 1494166.67
G7PUINMR | GAS METERS AND REGULATORS BLANKET | 75086 | Gas Ops - Distribution DPS | Rev Producing | METER-PURCHASED METERS, ERTS, REGULATORS | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7PUINMR | GAS METERS AND REGULATORS BLANKET | 1630000 |  | 55153 | Fritsch | 0 | 135833.33 | 0 | 1630000 | 0 | 1630000
G7REG0026 | REG 0026 - Uphill and Highway - Reg | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281967 | REG 0026 Uphil and Highway - Reg Sw | 0 |  | 44196 | Felt | 3929.53 | 0 | 3929.53 | 0 | 3929.53 | 0
G7REG0026 | REG 0026 - Uphill and Highway - Reg | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281967 | REG 0026 Uphil and Highway - Reg Sw | 0 |  | 44196 | Felt | 1.11 | 0 | 3930.64 | 0 | 3930.64 | 0
G7REG0026 | REG 0026 - Uphill and Highway - Reg | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281967 | REG 0026 Uphil and Highway - Reg Sw | 0 |  | 44196 | Felt | 2.64 | 0 | 3933.28 | 0 | 3933.28 | 0
G7REG0026 | REG 0026 - Uphill and Highway - Reg | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281967 | REG 0026 Uphil and Highway - Reg Sw | 0 |  | 44196 | Felt | 4820.85 | 0 | 8754.13 | 0 | 8754.13 | 0
G7REG0026 | REG 0026 - Uphill and Highway - Reg | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281967 | REG 0026 Uphil and Highway - Reg Sw | 0 |  | 44196 | Felt | 7.26 | 0 | 8761.39 | 0 | 8761.39 | 0
G7REG0048 | REG 0048 - Fifth and Philadelphia - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7282035 | REG 0048 Fifth and Philadelphia - R | 0 |  | 44196 | Felt | 12668.93 | 0 | 12668.93 | 0 | 12668.93 | 0
G7REG0048 | REG 0048 - Fifth and Philadelphia - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7282035 | REG 0048 Fifth and Philadelphia - R | 0 |  | 44196 | Felt | 3.59 | 0 | 12672.52 | 0 | 12672.52 | 0
G7REG0048 | REG 0048 - Fifth and Philadelphia - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7282035 | REG 0048 Fifth and Philadelphia - R | 0 |  | 44196 | Felt | 8.51 | 0 | 12681.03 | 0 | 12681.03 | 0
G7REG0048 | REG 0048 - Fifth and Philadelphia - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7282035 | REG 0048 Fifth and Philadelphia - R | 0 |  | 44196 | Felt | 12.91 | 0 | 12693.94 | 0 | 12693.94 | 0
G7REG0048 | REG 0048 - Fifth and Philadelphia - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7282035 | REG 0048 Fifth and Philadelphia - R | 0 |  | 44196 | Felt | 10.55 | 0 | 12704.49 | 0 | 12704.49 | 0
G7REG0057 | REG 0057 - Saratoga and Eleventh - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 0 |  | 44196 | Felt | 2638.4 | 0 | 2638.4 | 0 | 2638.4 | 0
G7REG0057 | REG 0057 - Saratoga and Eleventh - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 0 |  | 44196 | Felt | 0.99 | 0 | 2639.39 | 0 | 2639.39 | 0
G7REG0057 | REG 0057 - Saratoga and Eleventh - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 0 |  | 44196 | Felt | 0.75 | 0 | 2640.14 | 0 | 2640.14 | 0
G7REG0057 | REG 0057 - Saratoga and Eleventh - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 0 |  | 44196 | Felt | 1.77 | 0 | 2641.91 | 0 | 2641.91 | 0
G7REG0057 | REG 0057 - Saratoga and Eleventh - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 0 |  | 44196 | Felt | 2.69 | 0 | 2644.6 | 0 | 2644.6 | 0
G7REG0057 | REG 0057 - Saratoga and Eleventh - | 75086 |  | Rate Case Lag | MANDR-MEASUREMENT & REGULATION | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7281845 | REG 0057 Saratoga and Eleventh - Or | 0 |  | 44196 | Felt | 2.2 | 0 | 2646.8 | 0 | 2646.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 4395.24 | 0 | 4395.24 | 0 | 1148638.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | 0 | 0 | 97362.4 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -1.4211e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | -19546.92 | 0 | -19546.92 | 0 | 22103.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 1436.1 | 0 | 1436.1 | 0 | 6347.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 2613.45 | 0 | 2613.45 | 0 | 35314.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 70891.23 | 0 | 70891.23 | 0 | 97645.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | 0 | 0 | 93900.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 85.2 | 0 | 85.2 | 0 | 85.2 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | 0 | 0 | 74859.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -5.7121e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 537.13 | 0 | 4932.37 | 0 | 1149175.9 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | 0 | 0 | 97362.4 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 33.15 | 0 | -19513.77 | 0 | 22136.79 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 9.52 | 0 | 1445.62 | 0 | 6356.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 834.19 | 0 | 3447.64 | 0 | 36148.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 90565.61 | 0 | 161456.84 | 0 | 188210.71 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | -12777.76 | 0 | -12777.76 | 0 | 81122.9 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 79.15 | 0 | 164.35 | 0 | 164.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | 0 | 0 | 74859.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 2.558e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 2.72 | 0 | 4935.09 | 0 | 1149178.62 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | 0 | 0 | 97362.4 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -1.1369e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | -353.49 | 0 | -19867.26 | 0 | 21783.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 34.79 | 0 | 1480.41 | 0 | 6391.6 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 85.93 | 0 | 3533.57 | 0 | 36234.57 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 13229.03 | 0 | 174685.87 | 0 | 201439.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | -116.08 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 108826.63 | 0 | 108990.98 | 0 | 108990.98 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | 0 | 0 | 74859.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 3.5527e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 207.29 | 0 | 5142.38 | 0 | 1149385.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | 0 | 0 | 97362.4 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 5.6843e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 32.41 | 0 | -19834.85 | 0 | 21815.71 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | -868.86 | 0 | 611.55 | 0 | 5522.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 1068.57 | 0 | 4602.14 | 0 | 37303.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 142607.84 | 0 | 317293.71 | 0 | 344047.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 12670.42 | 0 | 121661.4 | 0 | 121661.4 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | 0 | 0 | 74859.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -5.6843e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 29.46 | 0 | 29.46 | 0 | 29.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 18999.04 | 0 | 24141.42 | 0 | 1168384.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | -1832.85 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -2.8422e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 23.05 | 0 | -19811.8 | 0 | 21838.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 6193.58 | 0 | 6805.13 | 0 | 11716.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 2220.26 | 0 | 6822.4 | 0 | 39523.4 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 40680.59 | 0 | 357974.3 | 0 | 384728.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 4384.44 | 0 | 126045.84 | 0 | 126045.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | 0 | 0 | 74859.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 787.79 | 0 | 817.25 | 0 | 817.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 10062.63 | 0 | 34204.05 | 0 | 1178447.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -1.1369e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 13.76 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 21242.45 | 0 | 28047.58 | 0 | 32958.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 163.06 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 240.46 | 0 | 358214.76 | 0 | 384968.63 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 12861.43 | 0 | 138907.27 | 0 | 138907.27 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | -3216 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -1.35e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 268.19 | 0 | 1085.44 | 0 | 1085.44 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 183.63 | 0 | 34387.68 | 0 | 1178631.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -9.9476e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 0 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 4843.9 | 0 | 32891.48 | 0 | 37802.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 0 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 195.62 | 0 | 358410.38 | 0 | 385164.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 70.51 | 0 | 138977.78 | 0 | 138977.78 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -1.7764e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 128.52 | 0 | 1213.96 | 0 | 1213.96 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 871.22 | 0 | 35258.9 | 0 | 1179502.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 1.4211e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 0 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 14487.67 | 0 | 47379.15 | 0 | 52290.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 0 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 144.69 | 0 | 358555.07 | 0 | 385308.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6840192 | Cancel Beaver Rd INSTALL REPLACE | 0 |  | 44127 | Shelton | 97.64 | 0 | 97.64 | 0 | 97.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 621.57 | 0 | 139599.35 | 0 | 139599.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 1.7764e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | -38.95 | 0 | 1175.01 | 0 | 1175.01 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 3287.1 | 0 | 38546 | 0 | 1182789.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | 0 | 0 | 29215.76 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -3.4106e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 0 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 38516.5 | 0 | 85895.65 | 0 | 90806.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 0 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 603.48 | 0 | 359158.55 | 0 | 385912.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6840192 | Cancel Beaver Rd INSTALL REPLACE | 0 |  | 44127 | Shelton | 0.03 | 0 | 97.67 | 0 | 97.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 132500.55 | 0 | 272099.9 | 0 | 272099.9 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | 0 | 0 | 98161.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | 0 | 0 | 9082.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 6813.47 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | 0 | 0 | 3232.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | -1.7053e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 209.58 | 0 | 1384.59 | 0 | 1384.59 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 426.26 | 0 | 38972.26 | 0 | 1183215.79 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 2.2737e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | -435.59 | 0 | -435.59 | 0 | 28780.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | -5.6843e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 0 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 32378.73 | 0 | 118274.38 | 0 | 123185.57 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 0 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 0 | 0 | 359158.55 | 0 | 385912.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6840192 | Cancel Beaver Rd INSTALL REPLACE | 0 |  | 44127 | Shelton | 0.07 | 0 | 97.74 | 0 | 97.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 818.39 | 0 | 272918.29 | 0 | 272918.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | -5228.42 | 0 | -5228.42 | 0 | 92932.68 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | -385.25 | 0 | -385.25 | 0 | 8697.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | -437.01 | 0 | -437.01 | 0 | 6376.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | -468.57 | 0 | -468.57 | 0 | 2763.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 4.8317e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 160.75 | 0 | 1545.34 | 0 | 1545.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 103.07 | 0 | 39075.33 | 0 | 1183318.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | -435.59 | 0 | 28780.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 1.4211e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 0 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 71021.84 | 0 | 189296.22 | 0 | 194207.41 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 0 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 0 | 0 | 359158.55 | 0 | 385912.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6840192 | Cancel Beaver Rd INSTALL REPLACE | 0 |  | 44127 | Shelton | 0.1 | 0 | 97.84 | 0 | 97.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | -20670.19 | 0 | 252248.1 | 0 | 252248.1 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | -5228.42 | 0 | 92932.68 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | -385.25 | 0 | 8697.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | -437.01 | 0 | 6376.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | -468.57 | 0 | 2763.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 0 | 0 | 0 | 0 | -43.37 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 1.6315e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 0 | 0 | 0 | 0 | 448.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 92.52 | 0 | 1637.86 | 0 | 1637.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 2845.73 | 0 | 41921.06 | 0 | 1186164.59 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C1219 | F/L UL2 AT TURFWAY RD/CWA | 0 | 38818 | 38818 | Brown | 0 | 0 | 0 | 0 | 147574.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C2775 | FALMOUTH-BR SERV/PP 707917/CL | 0 | 39050 | 39050 | Shoemaker | 0 | 0 | 0 | 0 | 44528.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3109 | 05-7249-5 CHRIS LANGE | 0 | 38598 | 38598 | Shoemaker | 0 | 0 | 0 | 0 | -24509.58 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C3536 | RT 27 BRIDGE/PPWo 00688980/RP | 0 | 38898 | 38898 |  | 0 | 0 | 0 | 0 | -26890.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C4330 | KY 177-BRIDGE/PPWO 689577/CWA | 0 | 39031 | 39031 |  | 0 | 0 | 0 | 0 | 194607.8 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5067 | STA 761-OUT/PPWo 05-1071-9/CWA | 0 | 39251 | 39251 |  | 0 | 0 | 0 | 0 | 25076.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5308 | HOGANS MILL/PPWo 00773811/CL | 0 | 38828 | 38828 |  | 0 | 0 | 0 | 0 | 16700.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5955 | LOCUST ST/792309/DJS | 0 | 38798 | 38798 |  | 0 | 0 | 0 | 0 | 10927.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6662 | SUMMERFIELD PH1/PPW00795330/JB | 0 | 38966 | 38966 |  | 0 | 0 | 0 | 0 | 8581.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6990 | R/W FOR STA 761/CWA | 0 | 39251 | 39251 | Shoemaker | 0 | 0 | 0 | 0 | 10820.34 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7594 | STA 432IMP/CWA | 0 | 39051 | 39051 |  | 0 | 0 | 0 | 0 | 41717.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C7879 | WESTERN AVE/PPW00799839/JL | 0 |  | 40908 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8325 | SARATOGA ST/PPW00696694/CTL | 0 | 39049 | 39049 |  | 0 | 0 | 0 | 0 | 191090.06 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C8761 | PP847388/ RICHWOOD/CTL | 0 | 39090 | 39090 | Shoemaker | 0 | 0 | 0 | 0 | -0.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9452 | PP877187/WRP | 0 | 39174 | 39174 |  | 0 | 0 | 0 | 0 | 28676.03 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2155 | PP 941166/LAURA MATE | 0 | 39498 | 39498 |  | 0 | 0 | 0 | 0 | 171723.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | D2287 | KY 3035 AT KY 17/CWA | 0 | 39540 | 39540 |  | 0 | 0 | 0 | 0 | 92767.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0318 | AM01 Repl Covington | 0 | 39689 | 39813 | Shoemaker | 0 | 0 | 0 | 0 | 121676.21 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E0492 | Scott St. Dry Ridge | 0 | 39694 | 55153 |  | 0 | 0 | 0 | 0 | 4559.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E4280 | Dry Creek LP03 R/W | 0 | 39974 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 11.86 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G0860 | Tammy Lane | 0 | 40621 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 75615.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1427 | Comair Blvd | 0 | 40474 | 40695 | Shoemaker | 0 | 0 | 0 | 0 | 34269.09 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G1456 | UL27 Falmouth Bridge | 0 | 40522 | 40633 | Shoemaker | 0 | 0 | 0 | 0 | 178478.61 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2173 | Saratogo St Main Replacement | 0 | 40830 | 40908 | Shoemaker | 0 | 0 | 0 | 0 | 199710.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G2962 | Moore St | 0 | 40393 | 40648 | Shoemaker | 0 | 0 | 0 | 0 | 200.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G3073 | Ky Copper Mod 629 | 0 | 40938 | 41061 | Shoemaker | 0 | 0 | 0 | 0 | 357282.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4517 | F/L 'UL07' McCullum Rd Slide | 0 | 40894 | 40969 | Colyer | 0 | 0 | -1832.85 | 0 | 95529.55 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G4641 | KY Copper MOD 640 | 0 | 40995 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 162884.31 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G5376 | Belmont Rd | 0 | 40861 | 40875 | Shoemaker | 0 | 0 | 0 | 0 | 7132.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7849 | Reg 109K - Inlet & Outlet Piping | 0 | 41167 | 41274 | Shoemaker | 0 | 0 | 0 | 0 | 78353.72 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8159 | Reg 115K - Inlet & Outlet Piping | 0 | 41248 | 41244 | Shoemaker | 0 | 0 | -435.59 | 0 | 28780.17 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8188 | Clover Ave | 0 |  | 41243 | Shoemaker | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8249 | REG 116K Inlet & Outlet Lines | 0 | 41326 | 41426 | Shoemaker | 0 | 0 | 0 | 0 | 70837.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G8688 | Exposed Main Old Union Rd & US 42 | 0 | 41130 | 41130 | Shoemaker | 0 | 0 | 0 | 0 | 8338.11 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9007 | Miller St. Newport | 0 | 41288 | 41276 | Shoemaker | 0 | 0 | 0 | 0 | 45200.43 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G9930 | Exposed Main on Petersburg Rd | 0 | 41454 | 41578 | Shoemaker | 0 | 0 | 0 | 0 | 29669.91 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0070 | Exposed main SR 10 UL -27 | 0 | 41494 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 64075.38 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0238 | Kathy, Kristine, & Rhonda, Falmouth | 0 | 41442 | 41548 | Shoemaker | 0 | 0 | 0 | 0 | 10788.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0383 | REG 117K - Inlet & Outlet Piping | 0 | 41753 | 42004 | Shoemaker | 0 | 0 | 0 | 0 | 151420.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0613 | W. Fifth Street | 0 | 41521 | 41516 | Shoemaker | 0 | 0 | 0 | 0 | 36927.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H0835 | Stevenson Rd Erlanger | 0 | 41730 | 41685 | Shoemaker | 0 | 0 | 0 | 0 | 49102.18 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1646 | Caroline Ave | 0 | 41670 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 221.64 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | K5112 | Fox Street | 0 | 41787 | 41820 | Shoemaker | 0 | 0 | 0 | 0 | 9260.48 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX0181170 | CENTRAL AVE NEWPORT- REPLACEMENT PR | 0 | 43704 | 43700 | Helm | 0 | 0 | -19798.04 | 0 | 21852.52 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1233047 | KY-9 FLOOD GATE-RPL | 0 | 44089 | 44008 | Helm | 308.84 | 0 | 189605.06 | 0 | 194516.25 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 16723.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4065631 | CALIFORNIA CROSSROADS REPLACEMENT | 0 | 43846 | 43819 | Helm | 0 | 0 | 6985.46 | 0 | 39686.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX4342633 | Pleasant Valley Steel Rep (Founders | 0 | 43916 | 43799 | Johnson | 0 | 0 | 359158.55 | 0 | 385912.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX6840192 | Cancel Beaver Rd INSTALL REPLACE | 0 |  | 44127 | Shelton | 0.08 | 0 | 97.92 | 0 | 97.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7157521 | COVERT RUN PIKE-INSTALL REPLACEMENT | 0 | 43272 | 43206 | Helm | 0 | 0 | 0 | 0 | 2386.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX7584379 | INSTALL REPLACEMENT PROJECT | 0 | 43288 | 43245 | Helm | 0 | 0 | 0 | 0 | 131018.23 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX8171793 | INSTALL REPLACEMENT PROJECT | 0 | 43389 | 43357 | Helm | 0 | 0 | 0 | 0 | -10333.26 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9056339 | St. Matthews Circle Replacement | 0 | 43605 | 43409 | Helm | 0 | 0 | -12893.84 | 0 | 81006.82 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MX9545566 | RICHWOOD RD REPLACEMENT PROJ KY-338 | 0 |  | 44134 | Helm | 10545.69 | 0 | 262793.79 | 0 | 262793.79 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P6335 | Dudley Rd - Relocation For Rstorm | 0 | 41962 | 41943 | Shoemaker | 0 | 0 | -5228.42 | 0 | 92932.68 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | P7671 | Y000 - KY Portion - 16" Ohio River | 0 | 42181 | 42308 | Perkins | 0 | 0 | 0 | 0 | 300514.73 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R1014 | Griffin Industries - UL-27 replacem | 0 | 42287 | 42292 | Perkins | 0 | 0 | 0 | 0 | 331197.35 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3316 | Glencoe - Webster/Railroad St | 0 | 42277 | 42286 | Perkins | 0 | 0 | -385.25 | 0 | 8697.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3461 | Station 577 Inlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | -437.01 | 0 | 6376.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R3462 | Station 577 Outlet Piping | 0 | 42355 | 42353 | Shoemaker | 0 | 0 | -468.57 | 0 | 2763.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4154 | NKU - Sunset Dr Repl | 0 | 42465 | 42521 | Perkins | 0 | 0 | 0 | 0 | 90647.81 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4407 | RP 9097151 AM | 0 | 42326 | 42614 | Perkins | 0 | 0 | 0 | 0 | 461336.54 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R4609 | RP 8866200 Ripple Creek | 0 | 42420 | 42356 | Johnson | 0 | 0 | -3216 | 0 | 71643.53 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | R6767 | RPL 9818927 21st St Levee | 0 | 42626 | 42644 | Perkins | 0 | 0 | 0 | 0 | 605747.46 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S5697 | RPL 10420236 Ft Wright Elem | 0 | 42567 | 42573 | Perkins | 0 | 0 | 0 | 0 | 2493.24 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S6913 | RPL 10348116 Williamstown Exp Main | 0 | 42634 | 42594 | Smith | 0 | 0 | 0 | 0 | 23144.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8375 | STA 838 Mineola Pike - Inlet | 0 | 43053 | 43342 | Perkins | 0 | 0 | 0 | 0 | 94715.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8504 | Sta 809 Waterworks Rd - Inlet | 0 |  | 43252 | Seiter | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8507 | Cancel Sta 809 Waterworks Rd Outlet | 0 | 43282 | 43344 | Seiter | 15.17 | 0 | 15.17 | 0 | -28.2 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | S8584 | RPL 10117658 Loomis Rd Airport | 0 |  | 43404 | Perkins | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0387 | RPL 11339902 Chesapeake St | 0 | 42744 | 42741 | Perkins | 0 | 0 | 0 | 0 | 43798.22 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T0647 | RPL 11581212 140 Railroad St | 0 | 42688 | 42766 | Perkins | 0 | 0 | 0 | 0 | 16389.14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1130 | RPL 11859007 Ballyshannon - relocat | 0 | 42805 | 42826 | Perkins | 337.54 | 0 | 337.54 | 0 | 785.75 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 24219.45 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | -27525.74 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T8295 | RPL 21421581 Latonia Lakes | 0 | 42931 | 43099 | Perkins | 0 | 0 | 0 | 0 | 210608.84 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9340 | Cancel RPL Waterworks Rd. Inlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2678.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | T9341 | Cancel RPL Waterworks Rd. Outlet | 0 |  | 43252 | Reynolds | 0 | 0 | 0 | 0 | 2966.77 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 1022.85 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | 28051 | SMALL REPL KY | 0 |  | 55153 | Shoemaker | 318.46 | 0 | 1956.32 | 0 | 1956.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MX1998720 | Safran (Messier Bugatti) Main Rep | 0 | 43151 | 43132 | Perkins | 0 | 0 | 0 | 0 | 2734.13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T1796 | Showcase AM07 | 0 | 43229 | 43039 | Perkins | 0 | 0 | 0 | 0 | 186.87 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  |  | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | T2230 | RPL 20745900 Hudson Ave | 0 | 42914 | 43099 | Perkins | 0 | 0 | 0 | 0 | 120.66 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 8.5265e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 8.5265e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 9.9476e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 8.5265e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 8.5265e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 8.5265e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 1.1369e-13 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A8944 | C-M CIMOS SERV KY 2002 | 0 | 39082 | 39082 |  | 0 | 0 | 0 | 0 | 9.9476e-14 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6514 | TO C/O A8944 G7REPL 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 431797.67 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6515 | TO C/O A8944 G7REPL 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 274357.92 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6516 | TO C/O A8944 G7REPL 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 92445.89 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2002 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6517 | TO C/O A8944 G7REPL 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 196160.29 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6464 | ALTAVIA/DS | 0 | 39100 | 39100 |  | 0 | 0 | 0 | 0 | 374729.94 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9890 | PP874616/JBL | 0 | 39388 | 39388 | Shoemaker | 0 | 0 | 0 | 0 | 150331.3 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9891 | PP874617/JBL | 0 | 39366 | 39366 | Shoemaker | 0 | 0 | 0 | 0 | 55773.95 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2007 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9892 | PP86721/JBL | 0 | 39387 | 39387 | Shoemaker | 0 | 0 | 0 | 0 | 79100.32 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 |  | 2009 | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | E7527 | Stevenson Rd | 0 | 40134 | 40178 | Shoemaker | 0 | 0 | 0 | 0 | 90067.42 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7REPL | REPLACEMENTS Pools | 75086 | Gas Ops - Distribution DPS | Rate Case Lag | DIMP-DISTRIBUTION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7REPL | REPLACEMENTS Pools | 0 |  | 43830 | Fritsch | 0 | 0 | 0 | 0 | 0 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7RISER | RISER REPLACEMENT | 75086 |  |  |  | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | ZB001 | Curb to Meter Services ULH&P | 0 | 40163 | 41305 | Shoemaker | 0 | 0 | 0 | 0 | 9873138.76 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 77342.26 | 0 | 77342.26 | 0 | 1829732.59 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 24103.26 | 0 | 101445.52 | 0 | 1853835.85 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 16558.49 | 0 | 118004.01 | 0 | 1870394.34 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 10977.29 | 0 | 128981.3 | 0 | 1881371.63 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 4216.83 | 0 | 133198.13 | 0 | 1885588.46 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 0 | 0 | 133198.13 | 0 | 1885588.46 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 5486.65 | 0 | 138684.78 | 0 | 1891075.11 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | -1941507 | 0 | -1802822.22 | 0 | -50431.89 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 0 | 0 | -1802822.22 | 0 | -50431.89 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 0 | 0 | -1802822.22 | 0 | -50431.89 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 0 | 0 | -1802822.22 | 0 | -50431.89 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3300LAND | Line UL02 S3300 LAND RTS | 0 | 43709 | 43373 | Seiter | 0 | 0 | 0 | 0 | 65915.49 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 |  |  | GREIM-GOVERNMENT REIMBURSABLE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V7041 | Line UL02 Seg 3300 Pleasant Valley | 0 | 43753 | 43738 | Seiter | 0 | 0 | -1802822.22 | 0 | -50431.89 | 0
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 44288.95 | 0 | 44288.95 | 0 | 44288.95
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 46415.1 | 0 | 90704.05 | 0 | 90704.05
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 89259.47 | 0 | 179963.52 | 0 | 179963.52
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 110481.38 | 0 | 290444.9 | 0 | 290444.9
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | -1865902.13 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7S3300 | Line UL02 Seg 3300 Pleasant Valley | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | GREIM-GOVERNMENT REIMBURSABLE | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7S3300 | Line UL02 Seg 3300 Pleasant Valley | -1575457.23 | 43753 | 43738 | Seiter | 0 | 0 | 0 | -1575457.23 | 0 | -1575457.23
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 18749.01 | 0 | 18749.01 | 0 | 18749.01
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 20436.75 | 0 | 39185.76 | 0 | 39185.76
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 23727.37 | 0 | 62913.13 | 0 | 62913.13
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 26657.75 | 0 | 89570.88 | 0 | 89570.88
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 28457.19 | 0 | 118028.07 | 0 | 118028.07
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 32455.12 | 0 | 150483.19 | 0 | 150483.19
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 36249.03 | 0 | 186732.22 | 0 | 186732.22
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 251916.12 | 0 | 438648.34 | 0 | 438648.34
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 258601.67 | 0 | 697250.01 | 0 | 697250.01
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 60544.97 | 0 | 757794.98 | 0 | 757794.98
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 75363.07 | 0 | 833158.05 | 0 | 833158.05
G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 75086 | Gas Ops - EPM Cincinnati | Rate Case Lag | TIMP-TRANSMISSION INTEGRITY | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | G7SE1900 | (Cancel)Line AM00B Seg 1900,2000 | 927849.87 |  | 44713 | Seiter | 0 | 94691.82 | 0 | 927849.87 | 0 | 927849.87
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCAM | Erlanger Security Camera | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5199 | Erlanger Security Camera | 0 | 43556 | 43464 | Lawhead | 0 | 0 | 0 | 0 | 38477.67 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 17521.97 | 0 | 17521.97 | 0 | 2903763.52 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 6327.51 | 0 | 23849.48 | 0 | 2910091.03 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 6167.09 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 11 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SECCON | Erlanger Propane Security Upgrade | 75086 |  |  | PROP-PROPANE PLANT | 12 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | V5175 | Erlanger Propane Security Upgrade | 0 | 43830 | 43875 | Long | 0 | 0 | 30016.57 | 0 | 2916258.12 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -2427.6 | 2855957.45 | -2427.6
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 10450.03 | 0 | 10450.03 | 0 | 12239609.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 16238.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 773.2 | 0 | 773.2 | 0 | 200835.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 156460.18 | 0 | 156460.18 | 0 | 15892950.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 462.63 | 0 | 462.63 | 0 | 485188.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 1 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 127.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -4855.2 | 2855957.45 | -4855.2
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 26519.24 | 0 | 36969.27 | 0 | 12266128.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 16238.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 773.2 | 0 | 200835.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 78021.34 | 0 | 234481.52 | 0 | 15970971.35 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 462.63 | 0 | 485188.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 2 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 127.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -7282.8 | 2855957.45 | -7282.8
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 14380.81 | 0 | 51350.08 | 0 | 12280509.24 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 16238.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 5544.59 | 0 | 6317.79 | 0 | 206379.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 72988.23 | 0 | 307469.75 | 0 | 16043959.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 217.59 | 0 | 680.22 | 0 | 485406.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 3 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 127.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -9710.4 | 2855957.45 | -9710.4
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 8664.5 | 0 | 60014.58 | 0 | 12289173.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 16238.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 18768.45 | 0 | 25086.24 | 0 | 225148.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 79899.47 | 0 | 387369.22 | 0 | 16123859.05 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 157.61 | 0 | 837.83 | 0 | 485563.69 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 4 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 789.19 | 0 | 789.19 | 0 | 916.38 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -12138 | 2855957.45 | -12138
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 10666.64 | 0 | 70681.22 | 0 | 12299840.38 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 16238.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 23222.94 | 0 | 48309.18 | 0 | 248371.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 54672.04 | 0 | 442041.26 | 0 | 16178531.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 5.22 | 0 | 843.05 | 0 | 485568.91 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 5 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 3135.13 | 0 | 3924.32 | 0 | 4051.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -14565.6 | 2855957.45 | -14565.6
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 14629.05 | 0 | 85310.27 | 0 | 12314469.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 1558.97 | 0 | 1558.97 | 0 | 17797.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 908.14 | 0 | 49217.32 | 0 | 249279.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 75383.24 | 0 | 517424.5 | 0 | 16253914.33 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 67.92 | 0 | 910.97 | 0 | 485636.83 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 6 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 257.74 | 0 | 4182.06 | 0 | 4309.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -16993.2 | 2855957.45 | -16993.2
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 18429.13 | 0 | 103739.4 | 0 | 12332898.56 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 5578.7 | 0 | 7137.67 | 0 | 23375.83 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 2917.02 | 0 | 52134.34 | 0 | 252196.53 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 110976.84 | 0 | 628401.34 | 0 | 16364891.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 207.17 | 0 | 1118.14 | 0 | 485844 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 7 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 719.84 | 0 | 4901.9 | 0 | 5029.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -19420.8 | 2855957.45 | -19420.8
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 20629.31 | 0 | 124368.71 | 0 | 12353527.87 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 7137.67 | 0 | 23375.83 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 1576.81 | 0 | 53711.15 | 0 | 253773.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 89114.84 | 0 | 717516.18 | 0 | 16454006.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 1118.14 | 0 | 485844 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 8 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 4901.9 | 0 | 5029.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -21848.4 | 2855957.45 | -21848.4
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMN70 | Install New C-M 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 42667.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3CMR70 | Replace C-M 3" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33825.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCN70 | Install New M-C 3" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 39658.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 3MCR70 | Replace M-C 3" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 50249.23 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMN70 | Install New C-M 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 7632.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4CMR70 | Replace C-M 4" Kentucky Blanket | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 26441.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCN70 | Install New M-C 4" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 12004.31 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 4MCR70 | Replace M-C 4" - Kentucky | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 33964.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMN70 | Install New C-M 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1728.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6CMR70 | Replace C-M 6" Kentucky Blanket | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 36610.9 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCN70 | Install New M-C 6" - Kentucky | 0 | 40543 | 40543 | Shoemaker | 0 | 0 | 0 | 0 | 1719.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 6MCR70 | Replace M-C 6" - Kentucky | 0 |  | 55153 |  | 0 | 0 | 0 | 0 | 20106.57 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 8MCR70 | Replace M-C 8" and Greater | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 60.1 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1324 | BLANKET KY 3IN M-C 00-3039-5 | 0 | 37484 |  | Shoemaker | 0 | 0 | 0 | 0 | 62685.18 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1325 | BLANKET KY 4IN M-C 00-3040-3 | 0 | 39417 |  | Shoemaker | 0 | 0 | 0 | 0 | 58018.86 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A1326 | BLANKET KY 6IN M-C 00-3041-1 | 0 |  |  | Shoemaker | 0 | 0 | 0 | 0 | 12614.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2242 | 0000265/11 SHELBY/RENEW M-C | 0 | 36725 | 36725 | Shoemaker | 0 | 0 | 0 | 0 | -0.49 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A2577 | 0000299/7114 PRICE PK | 0 | 36754 | 36754 | Shoemaker | 0 | 0 | 0 | 0 | -2.3 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | A9256 | cm services replaced in ky | 0 | 37321 | 37321 |  | 0 | 0 | 0 | 0 | 1552339.34 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5532 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 347391.74 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5533 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 3124642.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5534 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 2793096.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5535 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 2724506.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5536 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 2187007.62 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5537 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 1900908.21 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5538 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 2294620.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5539 | ULH&P GAS SERVICES-1999 C/O | 0 | 36525 | 36525 |  | 0 | 0 | 0 | 0 | 13206.37 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5540 | ULH&P GAS SERVICES-2000 C/O | 0 | 36891 | 36891 |  | 0 | 0 | 0 | 0 | 140811.82 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5542 | ULH&P GAS SERVICES-2001 C/O | 0 | 37256 | 37256 |  | 0 | 0 | 0 | 0 | 95685.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5543 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 91936.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5544 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 105187.07 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5546 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 109222.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5547 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 83592.71 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5556 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 19161.16 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5557 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 46226.13 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5558 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 10769.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5559 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55487.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5560 | ULH&P GAS SERVICES-2002 C/O | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 33186.39 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5561 | ULH&P GAS SERVICES-2003 C/O | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 28898.01 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5562 | ULH&P GAS SERVICES-2004 C/O | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 39494.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C5563 | ULH&P GAS SERVICES-2005 C/O | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 55337.48 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6125 | MEMORIAL PKY/PP791048/KGA | 0 | 38936 | 38936 |  | 0 | 0 | 0 | 0 | 35325.61 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6518 | TO C/O A9256 G7SERVMC 2002 | 0 | 37621 | 37621 |  | 0 | 0 | 0 | 0 | 261137.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6519 | TO C/O A9256 G7SERVMC 2003 | 0 | 37986 | 37986 |  | 0 | 0 | 0 | 0 | 364877.17 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6520 | TO C/O A9256 G7SERVMC 2004 | 0 | 38352 | 38352 |  | 0 | 0 | 0 | 0 | 381807.72 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C6521 | TO C/O A9256 G7SERVMC 2005 | 0 | 38717 | 38717 |  | 0 | 0 | 0 | 0 | 238103.58 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | C9839 | PP896043/CWA | 0 | 39255 | 39255 | Shoemaker | 0 | 0 | 0 | 0 | -9355.08 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMNP70 | New C-M Plastic 2 inch and Under Se | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 865466.8 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 31130.38 | 0 | 155499.09 | 0 | 12384658.25 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | CMRS70 | 2" or less steel C-M Replace | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 47511.19 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1529 | 7080 Industrial Rd | 0 | 40718 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 2505.46 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1530 | 7100 Industrial Rd | 0 | 40702 | 41639 | Shoemaker | 0 | 0 | 0 | 0 | 3115.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1531 | 6850 Industrial Rd | 0 | 40717 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 3101.64 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | H1532 | 7090 Industrial Rd | 0 | 40710 | 41670 | Shoemaker | 0 | 0 | 0 | 0 | 2234.79 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRP70 | Greater than 2" C-M REPL Plastic | 0 |  | 55153 | Davis | 0 | 0 | 7137.67 | 0 | 23375.83 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LCMRS70 | Greater than 2" C-M Steel Replaceme | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 8899.09 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRP70 | Greater than 2" M-C REPL Plastic | 0 |  | 55153 | Davis | 1145.34 | 0 | 54856.49 | 0 | 254918.68 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | LMCRS70 | Greater than 2" M-C REPL Steel | 0 |  | 55153 | Davis | 0 | 0 | 0 | 0 | 6274.98 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNP70 | New M-C Plastic 2 inch and Under Se | 0 | 40167 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 1200264.06 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCNS70 | New M-C Steel 2 inch and Under Serv | 0 | 40543 | 43465 | Shoemaker | 0 | 0 | 0 | 0 | 20929.5 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 81997.95 | 0 | 799514.13 | 0 | 16536003.96 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 2853.68 | 0 | 3971.82 | 0 | 488697.68 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | CMRP70 | Replace C-M Plastic 2 inch and Unde | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 2300.43 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 10586.81 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF2 | Duke Energy Kentucky - Gas | DEK Gas Ops Functional Alloc | DEK Gas Ops Functional Alloc | MCRS70 | Replace M-C Steel 2 inch and Under | 0 |  | 55153 | Shoemaker | 0 | 0 | 0 | 0 | 3295.36 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 9 | 2020 | GOF4 | Duke Energy Kentucky - Gas | DEK Gas Cap OH Alloc | DEK Gas Cap OH Alloc | MCRP70 | Replace (non-AMRP) M-C Plastic 2 in | 0 | 40167 | 55153 | Shoemaker | 1242.79 | 0 | 6144.69 | 0 | 6271.88 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28047 | INST. 3/4", 1", OR 1 1/4" NEW SERVI | -29131.2 | 39447 | 55153 | Shoemaker | 0 | -2427.6 | 0 | -24276 | 2855957.45 | -24276
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28057 | SERVICES BLANKETS | 0 | 36526 |  | Shoemaker | 0 | 0 | 0 | 0 | 103377.84 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28716 | PARK PL 19/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.51 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28718 | ALLISON 212/DMG | 0 | 35215 | 35215 | Shoemaker | 0 | 0 | 0 | 0 | -0.29 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 28763 | LAKEVIEW DR/DMG | 0 | 35227 | 38353 | Shoemaker | 0 | 0 | 0 | 0 | -0.85 | 0
G7SERVMC | SERVICES MC BLANKET | 75086 |  |  | RSERV-REPLACEMENT SERVICES | 10 | 2020 | GD70 | Duke Energy Kentucky - Gas | Gas Operations DE Kentucky | Gas Operations DE Kentucky | 30144 | OAKMONT 821/DMG | 0 | 35374 | 35374 | Shoemaker | 0 | 0 | 0 | 0 | -1.02 | 0