## Submit
Atmos Energy Corporation, Kentucky
CWIP
Month | Project Number | Project Name | Total Project CWIP Expenditures As of June 30, 2021 | Estimated Start Date | Estimated Completion Date | Orginal Budget Estimate | Most Recent Budget Estimate | Project Type
201910 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
201910 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
201910 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
201910 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
201910 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
201910 | 050.50808 | 050.2637.Falconite Oakes Ext | 35799.42 | 2019-04-01 | 2019-11-30 | 33173.63 | 33173.63 | Non Functional
201910 | 050.50849 | 050.2637.Untoneable Replace | 0 | 2019-04-01 | 2020-05-30 | 193482.59 | 193482.59 | Non Functional
201910 | 050.50974 | 050.2739.CC Greens Drive | 36122.89 | 2019-05-06 | 2019-11-30 | 53745.38 | 53745.38 | Non Functional
201910 | 050.51354 | 2734.WMR Endpoints.FY2020 | 1441103.53 | 2019-10-01 | 2020-06-30 | 2720654.45 | 2720654.45 | Non Functional
201910 | 050.51483 | 050.2739.The Fairways | 33683.65 | 2019-06-17 | 2019-11-30 | 28212.69 | 28212.69 | Non Functional
201910 | 050.51491 | 050.2637.Ky 1322 Relocate | 40693.28 | 2019-06-10 | 2019-12-31 | 73147.82 | 73147.82 | Non Functional
201910 | 050.51493 | 2734.Baseboards BG Office | 12323.73 | 2018-10-01 | 2019-12-31 | 12843.6 | 12843.6 | Non Functional
201910 | 050.51674 | 2734.Blevins.Farms.Sub | 62634.62 | 2019-07-12 | 2020-06-01 | 34703.56 | 62578.76 | Non Functional
201910 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
201910 | 050.51766 | 2637.Equipment.FY2020 | 68521.15 | 2019-10-01 | 2020-01-31 | 63361.76 | 63361.76 | Non Functional
201910 | 050.51767 | 2638.Equipment.FY2020 | 5291.23 | 2019-10-01 | 2020-01-31 | 8562.4 | 8562.4 | Non Functional
201910 | 050.51768 | 2736.Equipment.FY2020 | 30662.85 | 2019-10-01 | 2019-12-31 | 30824.64 | 30824.64 | Non Functional
201910 | 050.51770 | 2636.Equipment.FY2020 | 62570.16 | 2019-10-01 | 2020-05-31 | 68621.52 | 68621.52 | Non Functional
201910 | 050.51771 | 2634.Equipment.FY2020 | 38109.72 | 2019-10-01 | 2019-12-31 | 51986 | 51986 | Non Functional
201910 | 050.51772 | 2635.Equipment.FY2020 | 8468.9 | 2019-10-01 | 2019-12-31 | 9174 | 9174 | Non Functional
201910 | 050.51778 | 2609.Mueller Equipment.FY2020 | 25985.62 | 2019-10-01 | 2020-02-28 | 24464 | 24464 | Non Functional
201910 | 050.51780 | 2735.Equipment.FY2020 | 23003.35 | 2019-10-01 | 2019-12-31 | 19448.88 | 19448.88 | Non Functional
201910 | 050.51781 | 2737.Equipment.FY2020 | 30445.87 | 2019-10-01 | 2019-12-31 | 30736.57 | 30736.57 | Non Functional
201910 | 050.51782 | 2738.Equipment.FY2020 | 17142.19 | 2019-10-01 | 2020-01-30 | 28378.24 | 28378.24 | Non Functional
201910 | 050.51783 | 2739.Equipment.FY2020 | 13954.84 | 2019-10-01 | 2019-11-30 | 15652.08 | 15652.08 | Non Functional
201910 | 050.51841 | PRP.2637.Ohio St | 353748.91 | 2019-10-01 | 2020-01-31 | 488008.46 | 488008.46 | Non Functional
201910 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
201910 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
201910 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
201910 | 050.51858 | 050.2637.Farm Tap Replacement | 291358.02 | 2019-10-01 | 2020-03-30 | 298846.67 | 298846.67 | Non Functional
201910 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
201910 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
201910 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
201910 | 050.51912 | PRP.2734.E Cedar St Franklin | 574936.26 | 2019-10-01 | 2020-06-10 | 491557.03 | 601135.12 | Non Functional
201910 | 050.51913 | PRP.2636.Allen Street | 598820.35 | 2019-10-01 | 2020-02-28 | 764393.76 | 764393.76 | Non Functional
201910 | 050.51920 | 050.2609 Farm Taps 2020 | 441099 | 2019-10-01 | 2020-08-30 | 1132668.45 | 1132668.45 | Non Functional
201910 | 050.51956 | PRP.2735.Woodsonville | 218428.08 | 2019-10-01 | 2020-01-31 | 266014.09 | 266014.09 | Non Functional
201910 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
201910 | 050.52045 | 050.2738.Campbellsville LP | 263596.55 | 2019-10-01 | 2020-01-30 | 368777.84 | 368777.84 | Non Functional
201910 | 050.52091 | 2634.SpottsvilleRelocation | 204380.48 | 2019-10-01 | 2019-11-08 | 218201.43 | 218201.43 | Non Functional
201910 | 050.52362 | 3302.KY.Desktops.FY20.Phase 1 | 11949.18 | 2019-10-01 | 2019-12-31 | 15779.28 | 15779.28 | Non Functional
201910 | 050.52369 | 3302.KY.MDT.FY20.Phase 1 | 34011.77 | 2019-10-01 | 2019-12-31 | 33943.8 | 33943.8 | Non Functional
201910 | 050.52421 | 050.2637.Hinkleville Rd Ext | 14980.77 | 2019-10-01 | 2019-11-30 | 18404.8 | 18404.8 | Non Functional
201910 | 050.52422 | 050.2637.Stonepoint Court Ext | 11029.21 | 2019-10-01 | 2019-12-30 | 14758.77 | 14758.77 | Non Functional
201910 | 050.52424 | 050.2637.Menards Rev Ext | 11613.24 | 2019-10-01 | 2019-11-30 | 15061.5 | 15061.5 | Non Functional
201910 | 050.52425 | 050.2637.Foxborough Ct Ext | 9227.27 | 2019-10-01 | 2019-11-30 | 11093.45 | 11093.45 | Non Functional
201910 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
201910 | 050.52427 | 050.2637.Hwy 60 W Rev Ext | 21499.91 | 2019-10-01 | 2019-11-30 | 28194.28 | 28194.28 | Non Functional
201910 | 050.52431 | 050.2638.Remington Lower Main | 13517 | 2019-10-01 | 2019-11-30 | 11204.31 | 11204.31 | Non Functional
201910 | 050.52500 | 050.2637.Cleary Dr Main Ext | 4164.88 | 2019-10-01 | 2020-01-30 | 4644.43 | 4644.43 | Non Functional
201910 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
201910 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
201911 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
201911 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
201911 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
201911 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
201911 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
201911 | 050.50849 | 050.2637.Untoneable Replace | 0 | 2019-04-01 | 2020-05-30 | 193482.59 | 193482.59 | Non Functional
201911 | 050.51354 | 2734.WMR Endpoints.FY2020 | 1441103.53 | 2019-10-01 | 2020-06-30 | 2720654.45 | 2720654.45 | Non Functional
201911 | 050.51483 | 050.2739.The Fairways | 33683.65 | 2019-06-17 | 2019-11-30 | 28212.69 | 28212.69 | Non Functional
201911 | 050.51493 | 2734.Baseboards BG Office | 12323.73 | 2018-10-01 | 2019-12-31 | 12843.6 | 12843.6 | Non Functional
201911 | 050.51674 | 2734.Blevins.Farms.Sub | 62634.62 | 2019-07-12 | 2020-06-01 | 34703.56 | 62578.76 | Non Functional
201911 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
201911 | 050.51766 | 2637.Equipment.FY2020 | 68521.15 | 2019-10-01 | 2020-01-31 | 63361.76 | 63361.76 | Non Functional
201911 | 050.51770 | 2636.Equipment.FY2020 | 62570.16 | 2019-10-01 | 2020-05-31 | 68621.52 | 68621.52 | Non Functional
201911 | 050.51771 | 2634.Equipment.FY2020 | 38109.72 | 2019-10-01 | 2019-12-31 | 51986 | 51986 | Non Functional
201911 | 050.51774 | 2609.Mueller Machine.FY2020 | 28829.88 | 2019-10-01 | 2020-01-31 | 26910.4 | 26910.4 | Non Functional
201911 | 050.51778 | 2609.Mueller Equipment.FY2020 | 25985.62 | 2019-10-01 | 2020-02-28 | 24464 | 24464 | Non Functional
201911 | 050.51780 | 2735.Equipment.FY2020 | 23003.35 | 2019-10-01 | 2019-12-31 | 19448.88 | 19448.88 | Non Functional
201911 | 050.51781 | 2737.Equipment.FY2020 | 30445.87 | 2019-10-01 | 2019-12-31 | 30736.57 | 30736.57 | Non Functional
201911 | 050.51782 | 2738.Equipment.FY2020 | 17142.19 | 2019-10-01 | 2020-01-30 | 28378.24 | 28378.24 | Non Functional
201911 | 050.51783 | 2739.Equipment.FY2020 | 13954.84 | 2019-10-01 | 2019-11-30 | 15652.08 | 15652.08 | Non Functional
201911 | 050.51841 | PRP.2637.Ohio St | 353748.91 | 2019-10-01 | 2020-01-31 | 488008.46 | 488008.46 | Non Functional
201911 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
201911 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
201911 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
201911 | 050.51858 | 050.2637.Farm Tap Replacement | 291358.02 | 2019-10-01 | 2020-03-30 | 298846.67 | 298846.67 | Non Functional
201911 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
201911 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
201911 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
201911 | 050.51912 | PRP.2734.E Cedar St Franklin | 574936.26 | 2019-10-01 | 2020-06-10 | 491557.03 | 601135.12 | Non Functional
201911 | 050.51913 | PRP.2636.Allen Street | 598820.35 | 2019-10-01 | 2020-02-28 | 764393.76 | 764393.76 | Non Functional
201911 | 050.51920 | 050.2609 Farm Taps 2020 | 441099 | 2019-10-01 | 2020-08-30 | 1132668.45 | 1132668.45 | Non Functional
201911 | 050.51956 | PRP.2735.Woodsonville | 218428.08 | 2019-10-01 | 2020-01-31 | 266014.09 | 266014.09 | Non Functional
201911 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
201911 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
201911 | 050.52045 | 050.2738.Campbellsville LP | 263596.55 | 2019-10-01 | 2020-01-30 | 368777.84 | 368777.84 | Non Functional
201911 | 050.52091 | 2634.SpottsvilleRelocation | 204380.48 | 2019-10-01 | 2019-11-08 | 218201.43 | 218201.43 | Non Functional
201911 | 050.52422 | 050.2637.Stonepoint Court Ext | 11029.21 | 2019-10-01 | 2019-12-30 | 14758.77 | 14758.77 | Non Functional
201911 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
201911 | 050.52432 | 2734.Crystal Gauges | 4129.21 | 2019-10-01 | 2019-11-30 | 3694.8 | 3694.8 | Non Functional
201911 | 050.52433 | 2737.Crystal Gauges | 2124.68 | 2019-10-01 | 2019-11-30 | 3694.8 | 3694.8 | Non Functional
201911 | 050.52475 | 2634.Hwy41APhaseII | 366463.97 | 2019-11-01 | 2020-04-01 | 364030.53 | 358038.03 | Non Functional
201911 | 050.52489 | 2636.DillardCt. | 13568.59 | 2019-11-05 | 2019-11-08 | 22219.07 | 22219.07 | Non Functional
201911 | 050.52500 | 050.2637.Cleary Dr Main Ext | 4164.88 | 2019-10-01 | 2020-01-30 | 4644.43 | 4644.43 | Non Functional
201911 | 050.52505 | 050.2637.Hwy 62 E Rev Ext | 31144.27 | 2019-10-01 | 2020-05-14 | 30773.57 | 30773.57 | Non Functional
201911 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
201911 | 050.52532 | 2636.CedarHurstRelocation | -2654.52 | 2019-11-05 | 2020-01-20 | 70078.29 | 50282.02 | Non Functional
201911 | 050.52551 | 050.2637.Central Ave Ext 2 | 5852.6 | 2019-10-01 | 2020-01-30 | 4578.19 | 4578.19 | Non Functional
201911 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
201911 | 050.52571 | 050.2735.Carnation Relocation | 46506.76 | 2019-11-04 | 2019-12-27 | 43019.99 | 43019.99 | Non Functional
201911 | 050.52583 | 050.2738.Roland Street | 4386.6 | 2019-11-04 | 2020-02-28 | 6117.06 | 6117.06 | Non Functional
201911 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
201911 | 050.52600 | RES.2737.Secretariat Drive | 6072.29 | 2019-11-04 | 2019-12-27 | 2992.01 | 2992.01 | Non Functional
201911 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
201912 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
201912 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
201912 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
201912 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
201912 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
201912 | 050.50849 | 050.2637.Untoneable Replace | 0 | 2019-04-01 | 2020-05-30 | 193482.59 | 193482.59 | Non Functional
201912 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
201912 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
201912 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
201912 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
201912 | 050.51858 | 050.2637.Farm Tap Replacement | 291358.02 | 2019-10-01 | 2020-03-30 | 298846.67 | 298846.67 | Non Functional
201912 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
201912 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
201912 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
201912 | 050.51912 | PRP.2734.E Cedar St Franklin | 574936.26 | 2019-10-01 | 2020-06-10 | 491557.03 | 601135.12 | Non Functional
201912 | 050.51913 | PRP.2636.Allen Street | 598820.35 | 2019-10-01 | 2020-02-28 | 764393.76 | 764393.76 | Non Functional
201912 | 050.51920 | 050.2609 Farm Taps 2020 | 441099 | 2019-10-01 | 2020-08-30 | 1132668.45 | 1132668.45 | Non Functional
201912 | 050.51956 | PRP.2735.Woodsonville | 218428.08 | 2019-10-01 | 2020-01-31 | 266014.09 | 266014.09 | Non Functional
201912 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
201912 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
201912 | 050.52045 | 050.2738.Campbellsville LP | 263596.55 | 2019-10-01 | 2020-01-30 | 368777.84 | 368777.84 | Non Functional
201912 | 050.52370 | 3302.KY.MDT.FY20.Phase 2 | 89432.72 | 2020-01-01 | 2020-09-30 | 101831.4 | 101831.4 | Non Functional
201912 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
201912 | 050.52475 | 2634.Hwy41APhaseII | 366463.97 | 2019-11-01 | 2020-04-01 | 364030.53 | 358038.03 | Non Functional
201912 | 050.52500 | 050.2637.Cleary Dr Main Ext | 4164.88 | 2019-10-01 | 2020-01-30 | 4644.43 | 4644.43 | Non Functional
201912 | 050.52505 | 050.2637.Hwy 62 E Rev Ext | 31144.27 | 2019-10-01 | 2020-05-14 | 30773.57 | 30773.57 | Non Functional
201912 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
201912 | 050.52532 | 2636.CedarHurstRelocation | -2654.52 | 2019-11-05 | 2020-01-20 | 70078.29 | 50282.02 | Non Functional
201912 | 050.52551 | 050.2637.Central Ave Ext 2 | 5852.6 | 2019-10-01 | 2020-01-30 | 4578.19 | 4578.19 | Non Functional
201912 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
201912 | 050.52583 | 050.2738.Roland Street | 4386.6 | 2019-11-04 | 2020-02-28 | 6117.06 | 6117.06 | Non Functional
201912 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
201912 | 050.52624 | 050.2637.Bleich Relocate 2019 | 10338.78 | 2019-10-01 | 2020-03-31 | 36997.48 | 36997.48 | Non Functional
201912 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
201912 | 050.52779 | 050.2637.Birch Bend Rev Ext | 47084.86 | 2019-11-19 | 2020-01-31 | 49734.06 | 49734.06 | Non Functional
201912 | 050.52828 | 050.2637.Carneal Rd Repair | 113124.85 | 2019-10-01 | 2020-01-31 | 82771.92 | 161566.45 | Non Functional
201912 | 050.52841 | COM.2738.Noe Road | 2545.44 | 2019-12-16 | 2020-01-24 | 3313.69 | 3313.69 | Non Functional
201912 | 050.52910 | 2734.WMR.Endpoints.Ph2.FY20 | 1402490.18 | 2019-12-30 | 2020-04-30 | 1477519.16 | 1477519.16 | Non Functional
201912 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202001 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202001 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
202001 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202001 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202001 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202001 | 050.50849 | 050.2637.Untoneable Replace | 0 | 2019-04-01 | 2020-05-30 | 193482.59 | 193482.59 | Non Functional
202001 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202001 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
202001 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202001 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202001 | 050.51858 | 050.2637.Farm Tap Replacement | 291358.02 | 2019-10-01 | 2020-03-30 | 298846.67 | 298846.67 | Non Functional
202001 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202001 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
202001 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
202001 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202001 | 050.51920 | 050.2609 Farm Taps 2020 | 441099 | 2019-10-01 | 2020-08-30 | 1132668.45 | 1132668.45 | Non Functional
202001 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202001 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
202001 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202001 | 050.52370 | 3302.KY.MDT.FY20.Phase 2 | 89432.72 | 2020-01-01 | 2020-09-30 | 101831.4 | 101831.4 | Non Functional
202001 | 050.52390 | 2612.KY.RTU Upgrades.FY20 | 188489.07 | 2020-01-01 | 2020-09-30 | 151162.36 | 220333.24 | Non Functional
202001 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202001 | 050.52475 | 2634.Hwy41APhaseII | 366463.97 | 2019-11-01 | 2020-04-01 | 364030.53 | 358038.03 | Non Functional
202001 | 050.52505 | 050.2637.Hwy 62 E Rev Ext | 31144.27 | 2019-10-01 | 2020-05-14 | 30773.57 | 30773.57 | Non Functional
202001 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202001 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202001 | 050.52583 | 050.2738.Roland Street | 4386.6 | 2019-11-04 | 2020-02-28 | 6117.06 | 6117.06 | Non Functional
202001 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202001 | 050.52624 | 050.2637.Bleich Relocate 2019 | 10338.78 | 2019-10-01 | 2020-03-31 | 36997.48 | 36997.48 | Non Functional
202001 | 050.52647 | 2634.JonesRd.StationUpgrade | 39178.12 | 2019-01-02 | 2020-02-28 | 41693.63 | 41693.63 | Non Functional
202001 | 050.52785 | 050.2638.Hwy 1748 Main Ext | 5101.85 | 2019-11-19 | 2020-02-28 | 3466.35 | 3466.35 | Non Functional
202001 | 050.52910 | 2734.WMR.Endpoints.Ph2.FY20 | 1402490.18 | 2019-12-30 | 2020-04-30 | 1477519.16 | 1477519.16 | Non Functional
202001 | 050.52935 | 2636.OldhartfordRd. | 63740.07 | 2020-01-02 | 2020-03-31 | 82964.25 | 82964.25 | Non Functional
202001 | 050.52961 | PRP.2737.Somerset St | 113460.34 | 2020-01-20 | 2020-03-30 | 69462.69 | 113341.92 | Non Functional
202001 | 050.52988 | 2734LP.Newton.Replc | 390680.79 | 2019-11-01 | 2020-07-31 | 472696.24 | 472696.24 | Non Functional
202001 | 050.52994 | 2734.Shady Ln. Ext | 7213.35 | 2019-12-17 | 2020-02-15 | 24113.56 | 24113.56 | Non Functional
202001 | 050.52997 | 2734.Patton.31W.Frk | 4703.89 | 2019-12-12 | 2020-03-31 | 27638.41 | 27638.41 | Non Functional
202001 | 050.53021 | 2734.Magnolia.Hills.Phase.II | 7889.2 | 2020-01-08 | 2020-04-30 | 13186.56 | 13186.56 | Non Functional
202001 | 050.53075 | RES.2637.Deer Ridge Tr Ext | 20559 | 2020-03-01 | 2020-04-30 | 17421.14 | 17421.14 | Non Functional
202001 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202001 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202001 | 050.53116 | 050.2739.Blackburn Farm Reloc | 3442.95 | 2020-01-27 | 2020-04-17 | 4385.42 | 4385.42 | Non Functional
202001 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202002 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202002 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
202002 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202002 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202002 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202002 | 050.50849 | 050.2637.Untoneable Replace | 0 | 2019-04-01 | 2020-05-30 | 193482.59 | 193482.59 | Non Functional
202002 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202002 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
202002 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202002 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202002 | 050.51858 | 050.2637.Farm Tap Replacement | 291358.02 | 2019-10-01 | 2020-03-30 | 298846.67 | 298846.67 | Non Functional
202002 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202002 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
202002 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
202002 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202002 | 050.51920 | 050.2609 Farm Taps 2020 | 441099 | 2019-10-01 | 2020-08-30 | 1132668.45 | 1132668.45 | Non Functional
202002 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202002 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
202002 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202002 | 050.52370 | 3302.KY.MDT.FY20.Phase 2 | 89432.72 | 2020-01-01 | 2020-09-30 | 101831.4 | 101831.4 | Non Functional
202002 | 050.52385 | 2612.KY.Emergency Regulators | 27362.3 | 2020-01-01 | 2020-03-31 | 30628.01 | 30628.01 | Non Functional
202002 | 050.52386 | 2612.Gas Supp RTU Install FY20 | 71195.26 | 2020-01-01 | 2020-09-30 | 112205.17 | 112205.17 | Non Functional
202002 | 050.52390 | 2612.KY.RTU Upgrades.FY20 | 188489.07 | 2020-01-01 | 2020-09-30 | 151162.36 | 220333.24 | Non Functional
202002 | 050.52397 | 2612.Calibration Kits FY20 | 73731.36 | 2020-01-01 | 2020-05-31 | 61160 | 73796.74 | Non Functional
202002 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202002 | 050.52475 | 2634.Hwy41APhaseII | 366463.97 | 2019-11-01 | 2020-04-01 | 364030.53 | 358038.03 | Non Functional
202002 | 050.52505 | 050.2637.Hwy 62 E Rev Ext | 31144.27 | 2019-10-01 | 2020-05-14 | 30773.57 | 30773.57 | Non Functional
202002 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202002 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202002 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202002 | 050.52624 | 050.2637.Bleich Relocate 2019 | 10338.78 | 2019-10-01 | 2020-03-31 | 36997.48 | 36997.48 | Non Functional
202002 | 050.52863 | 2738.4" TDW Shortstop Valves | 14064.47 | 2019-12-01 | 2020-02-28 | 13698.77 | 13698.77 | Non Functional
202002 | 050.52910 | 2734.WMR.Endpoints.Ph2.FY20 | 1402490.18 | 2019-12-30 | 2020-04-30 | 1477519.16 | 1477519.16 | Non Functional
202002 | 050.52933 | 050.2737.Danville ERX FY20 | 17143.63 | 2019-10-01 | 2020-04-30 | 16662.62 | 16662.62 | Non Functional
202002 | 050.52935 | 2636.OldhartfordRd. | 63740.07 | 2020-01-02 | 2020-03-31 | 82964.25 | 82964.25 | Non Functional
202002 | 050.52988 | 2734LP.Newton.Replc | 390680.79 | 2019-11-01 | 2020-07-31 | 472696.24 | 472696.24 | Non Functional
202002 | 050.52994 | 2734.Shady Ln. Ext | 7213.35 | 2019-12-17 | 2020-02-15 | 24113.56 | 24113.56 | Non Functional
202002 | 050.52997 | 2734.Patton.31W.Frk | 4703.89 | 2019-12-12 | 2020-03-31 | 27638.41 | 27638.41 | Non Functional
202002 | 050.53021 | 2734.Magnolia.Hills.Phase.II | 7889.2 | 2020-01-08 | 2020-04-30 | 13186.56 | 13186.56 | Non Functional
202002 | 050.53072 | 2636.PinHighTieIn | 1582.58 | 2020-02-04 | 2020-02-07 | 2299.6 | 2299.6 | Non Functional
202002 | 050.53075 | RES.2637.Deer Ridge Tr Ext | 20559 | 2020-03-01 | 2020-04-30 | 17421.14 | 17421.14 | Non Functional
202002 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202002 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202002 | 050.53116 | 050.2739.Blackburn Farm Reloc | 3442.95 | 2020-01-27 | 2020-04-17 | 4385.42 | 4385.42 | Non Functional
202002 | 050.53185 | 2734.Highland Way.Sub | 22386.73 | 2020-02-01 | 2020-07-30 | 23583.16 | 23583.16 | Non Functional
202002 | 050.53187 | 050.2735.Glasgow LP | 902782.81 | 2020-02-03 | 2020-07-30 | 580887.19 | 845652.39 | Non Functional
202002 | 050.53191 | 2636.GreenbackRd.MainExt. | 4084.64 | 2020-02-17 | 2020-03-15 | 5007.44 | 5007.44 | Non Functional
202002 | 050.53289 | 2636.SaddlePointPhaseI | 49197.72 | 2020-02-24 | 2020-03-23 | 61073.13 | 61073.13 | Non Functional
202002 | 050.53320 | COM.2638.Gideon Crossing | 19309.21 | 2020-03-01 | 2020-04-30 | 21075.69 | 21075.69 | Non Functional
202002 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202003 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202003 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
202003 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202003 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202003 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202003 | 050.50849 | 050.2637.Untoneable Replace | 0 | 2019-04-01 | 2020-05-30 | 193482.59 | 193482.59 | Non Functional
202003 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202003 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
202003 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202003 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202003 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202003 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
202003 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
202003 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202003 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202003 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
202003 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202003 | 050.52370 | 3302.KY.MDT.FY20.Phase 2 | 89432.72 | 2020-01-01 | 2020-09-30 | 101831.4 | 101831.4 | Non Functional
202003 | 050.52386 | 2612.Gas Supp RTU Install FY20 | 71195.26 | 2020-01-01 | 2020-09-30 | 112205.17 | 112205.17 | Non Functional
202003 | 050.52390 | 2612.KY.RTU Upgrades.FY20 | 188489.07 | 2020-01-01 | 2020-09-30 | 151162.36 | 220333.24 | Non Functional
202003 | 050.52403 | Mueller T Drilling Machine | 3089.57 | 2019-10-01 | 2020-04-15 | 2780.33 | 2780.33 | Non Functional
202003 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202003 | 050.52505 | 050.2637.Hwy 62 E Rev Ext | 31144.27 | 2019-10-01 | 2020-05-14 | 30773.57 | 30773.57 | Non Functional
202003 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202003 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202003 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202003 | 050.52895 | PRP.2636.Crabtree Ave | 796481.22 | 2020-02-20 | 2020-08-30 | 735985.77 | 735985.77 | Non Functional
202003 | 050.52933 | 050.2737.Danville ERX FY20 | 17143.63 | 2019-10-01 | 2020-04-30 | 16662.62 | 16662.62 | Non Functional
202003 | 050.52988 | 2734LP.Newton.Replc | 390680.79 | 2019-11-01 | 2020-07-31 | 472696.24 | 472696.24 | Non Functional
202003 | 050.52997 | 2734.Patton.31W.Frk | 4703.89 | 2019-12-12 | 2020-03-31 | 27638.41 | 27638.41 | Non Functional
202003 | 050.53046 | 2636Hwy60EHardinsburg | 5221.32 | 2020-02-04 | 2020-04-15 | 3405.28 | 3405.28 | Non Functional
202003 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202003 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202003 | 050.53116 | 050.2739.Blackburn Farm Reloc | 3442.95 | 2020-01-27 | 2020-04-17 | 4385.42 | 4385.42 | Non Functional
202003 | 050.53185 | 2734.Highland Way.Sub | 22386.73 | 2020-02-01 | 2020-07-30 | 23583.16 | 23583.16 | Non Functional
202003 | 050.53187 | 050.2735.Glasgow LP | 902782.81 | 2020-02-03 | 2020-07-30 | 580887.19 | 845652.39 | Non Functional
202003 | 050.53192 | 2734.Breckenridge,Sub. Ext | 114371.44 | 2020-01-24 | 2020-05-29 | 96948.92 | 96948.92 | Non Functional
202003 | 050.53291 | 26536.RummageRd.MainExt. | 2048.65 | 2020-03-06 | 2020-04-15 | 4832.93 | 4832.93 | Non Functional
202003 | 050.53308 | 2636.BurnsRd.MainExt | 4043.28 | 2020-04-30 | 2020-04-30 | 2197.25 | 2197.25 | Non Functional
202003 | 050.53320 | COM.2638.Gideon Crossing | 19309.21 | 2020-03-01 | 2020-04-30 | 21075.69 | 21075.69 | Non Functional
202003 | 050.53355 | 2734.BlueLeve.2 inch Ext | 1067.35 | 2020-03-03 | 2020-06-10 | 6137.68 | 6137.68 | Non Functional
202003 | 050.53448 | 2734.Hunters.Crossing.Frk | 18958.25 | 2020-03-18 | 2020-06-15 | 9718.81 | 22698.22 | Non Functional
202003 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202004 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202004 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
202004 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202004 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202004 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202004 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202004 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
202004 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202004 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202004 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202004 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
202004 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
202004 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202004 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202004 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
202004 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202004 | 050.52366 | 3302.KY.Laptops.FY20.Phase 2 | 12695.23 | 2020-01-01 | 2020-09-30 | 11620.4 | 11620.4 | Non Functional
202004 | 050.52370 | 3302.KY.MDT.FY20.Phase 2 | 89432.72 | 2020-01-01 | 2020-09-30 | 101831.4 | 101831.4 | Non Functional
202004 | 050.52386 | 2612.Gas Supp RTU Install FY20 | 71195.26 | 2020-01-01 | 2020-09-30 | 112205.17 | 112205.17 | Non Functional
202004 | 050.52390 | 2612.KY.RTU Upgrades.FY20 | 188489.07 | 2020-01-01 | 2020-09-30 | 151162.36 | 220333.24 | Non Functional
202004 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202004 | 050.52505 | 050.2637.Hwy 62 E Rev Ext | 31144.27 | 2019-10-01 | 2020-05-14 | 30773.57 | 30773.57 | Non Functional
202004 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202004 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202004 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202004 | 050.52895 | PRP.2636.Crabtree Ave | 796481.22 | 2020-02-20 | 2020-08-30 | 735985.77 | 735985.77 | Non Functional
202004 | 050.52988 | 2734LP.Newton.Replc | 390680.79 | 2019-11-01 | 2020-07-31 | 472696.24 | 472696.24 | Non Functional
202004 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202004 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202004 | 050.53185 | 2734.Highland Way.Sub | 22386.73 | 2020-02-01 | 2020-07-30 | 23583.16 | 23583.16 | Non Functional
202004 | 050.53187 | 050.2735.Glasgow LP | 902782.81 | 2020-02-03 | 2020-07-30 | 580887.19 | 845652.39 | Non Functional
202004 | 050.53192 | 2734.Breckenridge,Sub. Ext | 114371.44 | 2020-01-24 | 2020-05-29 | 96948.92 | 96948.92 | Non Functional
202004 | 050.53251 | PRP.2734.Hwy 383 Franklin | 291554.23 | 2020-03-07 | 2020-09-30 | 289076.25 | 289076.25 | Non Functional
202004 | 050.53448 | 2734.Hunters.Crossing.Frk | 18958.25 | 2020-03-18 | 2020-06-15 | 9718.81 | 22698.22 | Non Functional
202004 | 050.53601 | RES.2636.CherryBlossomCt. | 9424.44 | 2020-04-06 | 2020-04-30 | 12325.1 | 12325.1 | Non Functional
202004 | 050.53628 | 2734.LoversLn.6.inch Replc | 6743.43 | 2020-04-07 | 2020-06-16 | 26161.94 | 26161.94 | Non Functional
202004 | 050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 948.66 | 2020-04-13 | 2020-08-31 | 238496.08 | 238496.08 | Non Functional
202004 | 050.53682 | 050.2739.Ardmore Crossings | 29239.69 | 2020-04-13 | 2020-08-31 | 16431.93 | 29263.81 | Non Functional
202004 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202005 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202005 | 050.49552 | 050.2736.Central Avenue | 843747.62 | 2018-10-01 | 2020-09-30 | 667515.13 | 667515.13 | Non Functional
202005 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202005 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202005 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202005 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202005 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
202005 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202005 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202005 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202005 | 050.51868 | PRP.2738.W. Walnut St Lebanon | 1301735.19 | 2019-10-01 | 2020-09-30 | 1730472.58 | 1730472.58 | Non Functional
202005 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
202005 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202005 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202005 | 050.52016 | 2636. LP.Greenville, FY20 | 1106466.76 | 2019-10-01 | 2020-09-30 | 974040.36 | 1121740.25 | Non Functional
202005 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202005 | 050.52370 | 3302.KY.MDT.FY20.Phase 2 | 89432.72 | 2020-01-01 | 2020-09-30 | 101831.4 | 101831.4 | Non Functional
202005 | 050.52386 | 2612.Gas Supp RTU Install FY20 | 71195.26 | 2020-01-01 | 2020-09-30 | 112205.17 | 112205.17 | Non Functional
202005 | 050.52390 | 2612.KY.RTU Upgrades.FY20 | 188489.07 | 2020-01-01 | 2020-09-30 | 151162.36 | 220333.24 | Non Functional
202005 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202005 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202005 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202005 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202005 | 050.52895 | PRP.2636.Crabtree Ave | 796481.22 | 2020-02-20 | 2020-08-30 | 735985.77 | 735985.77 | Non Functional
202005 | 050.52988 | 2734LP.Newton.Replc | 390680.79 | 2019-11-01 | 2020-07-31 | 472696.24 | 472696.24 | Non Functional
202005 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202005 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202005 | 050.53185 | 2734.Highland Way.Sub | 22386.73 | 2020-02-01 | 2020-07-30 | 23583.16 | 23583.16 | Non Functional
202005 | 050.53187 | 050.2735.Glasgow LP | 902782.81 | 2020-02-03 | 2020-07-30 | 580887.19 | 845652.39 | Non Functional
202005 | 050.53192 | 2734.Breckenridge,Sub. Ext | 114371.44 | 2020-01-24 | 2020-05-29 | 96948.92 | 96948.92 | Non Functional
202005 | 050.53251 | PRP.2734.Hwy 383 Franklin | 291554.23 | 2020-03-07 | 2020-09-30 | 289076.25 | 289076.25 | Non Functional
202005 | 050.53428 | 2636.GoshenRd. | 6980.05 | 2020-05-01 | 2020-08-31 | 6384.94 | 11562.61 | Non Functional
202005 | 050.53448 | 2734.Hunters.Crossing.Frk | 18958.25 | 2020-03-18 | 2020-06-15 | 9718.81 | 22698.22 | Non Functional
202005 | 050.53628 | 2734.LoversLn.6.inch Replc | 6743.43 | 2020-04-07 | 2020-06-16 | 26161.94 | 26161.94 | Non Functional
202005 | 050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 948.66 | 2020-04-13 | 2020-08-31 | 238496.08 | 238496.08 | Non Functional
202005 | 050.53682 | 050.2739.Ardmore Crossings | 29239.69 | 2020-04-13 | 2020-08-31 | 16431.93 | 29263.81 | Non Functional
202005 | 050.53683 | COM.2735.Bald Knob Road | -512.61 | 2020-04-20 | 2020-07-30 | 8980.13 | 8980.13 | Non Functional
202005 | 050.53707 | PRP.2637.Old Mayfield Rd | 610211 | 2020-05-10 | 2020-09-30 | 909335.87 | 909335.87 | Non Functional
202005 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202005 | 050.53777 | 050.2634ERXMadisonville | 10065.49 | 2019-10-01 | 2020-05-31 | 10214.68 | 10214.68 | Non Functional
202005 | 050.53837 | 2734.Keystone.Commons,Ext | 5035.82 | 2020-05-05 | 2020-06-30 | 9649.92 | 9649.92 | Non Functional
202005 | 050.53912 | 2734.Carter.Crossing.Ext | 32685.33 | 2020-05-18 | 2020-07-31 | 42374.79 | 42374.79 | Non Functional
202005 | 050.54033 | RES.2737.Shawnee Run | 1715.96 | 2020-06-01 | 2020-08-14 | 5486.37 | 5486.37 | Non Functional
202005 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202006 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202006 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202006 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202006 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202006 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202006 | 050.51843 | PRP.2737.Hwy 150 | 1051752.03 | 2019-10-01 | 2020-07-30 | 682833.86 | 1049416.27 | Non Functional
202006 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202006 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202006 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202006 | 050.51876 | PRP.2738.W High St Lebanon | 1193587.1 | 2019-10-01 | 2020-09-30 | 1400133.73 | 1400133.73 | Non Functional
202006 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202006 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202006 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202006 | 050.52386 | 2612.Gas Supp RTU Install FY20 | 71195.26 | 2020-01-01 | 2020-09-30 | 112205.17 | 112205.17 | Non Functional
202006 | 050.52390 | 2612.KY.RTU Upgrades.FY20 | 188489.07 | 2020-01-01 | 2020-09-30 | 151162.36 | 220333.24 | Non Functional
202006 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202006 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202006 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202006 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202006 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202006 | 050.52895 | PRP.2636.Crabtree Ave | 796481.22 | 2020-02-20 | 2020-08-30 | 735985.77 | 735985.77 | Non Functional
202006 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202006 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202006 | 050.53187 | 050.2735.Glasgow LP | 902782.81 | 2020-02-03 | 2020-07-30 | 580887.19 | 845652.39 | Non Functional
202006 | 050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 948.66 | 2020-04-13 | 2020-08-31 | 238496.08 | 238496.08 | Non Functional
202006 | 050.53682 | 050.2739.Ardmore Crossings | 29239.69 | 2020-04-13 | 2020-08-31 | 16431.93 | 29263.81 | Non Functional
202006 | 050.53683 | COM.2735.Bald Knob Road | -512.61 | 2020-04-20 | 2020-07-30 | 8980.13 | 8980.13 | Non Functional
202006 | 050.53707 | PRP.2637.Old Mayfield Rd | 610211 | 2020-05-10 | 2020-09-30 | 909335.87 | 909335.87 | Non Functional
202006 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202006 | 050.53901 | 2636.CountFleetLoop | 11468.51 | 2020-09-01 | 2020-09-11 | 3921.53 | 12631.37 | Non Functional
202006 | 050.53912 | 2734.Carter.Crossing.Ext | 32685.33 | 2020-05-18 | 2020-07-31 | 42374.79 | 42374.79 | Non Functional
202006 | 050.54033 | RES.2737.Shawnee Run | 1715.96 | 2020-06-01 | 2020-08-14 | 5486.37 | 5486.37 | Non Functional
202006 | 050.54068 | 2636.BoothfieldRd. | 2280.42 | 2020-07-31 | 2020-07-31 | 2952.56 | 2952.56 | Non Functional
202006 | 050.54093 | RES.2738.Wilson Subdivision | 7515.85 | 2020-06-01 | 2020-08-31 | 4645.79 | 4645.79 | Non Functional
202006 | 050.54166 | 2734.Magnolis Hills II-A | 18058.63 | 2020-06-08 | 2020-08-14 | 13408.41 | 13408.41 | Non Functional
202006 | 050.54175 | RES.2734.McCoy Place V | 6716.28 | 2020-06-09 | 2020-08-14 | 10990.2 | 10990.2 | Non Functional
202006 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202007 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202007 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202007 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202007 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202007 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202007 | 050.51844 | PRP.2734.E 9th Russellville | 1232445.88 | 2019-10-01 | 2020-09-30 | 1020330.75 | 1228367 | Non Functional
202007 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202007 | 050.51867 | PRP.2734.Jackson - Pearl St | 1135040.62 | 2019-10-01 | 2020-09-30 | 1166313.96 | 1166313.96 | Non Functional
202007 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202007 | 050.51957 | PRP.2735.Lexington Ave | 1023666.67 | 2019-10-01 | 2020-09-30 | 1303458.7 | 1303458.7 | Non Functional
202007 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202007 | 050.52426 | 2734.S.Oak.Sub. Hwy 242 | 124954.17 | 2019-08-21 | 2020-09-30 | 104316.15 | 104316.15 | Non Functional
202007 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202007 | 050.52554 | IND.2735.Cave City Ind Park | 4346.94 | 2019-11-04 | 2020-08-31 | 4043.53 | 4043.53 | Non Functional
202007 | 050.52584 | 050.2637.Paddock At The Oaks | 144630.9 | 2019-10-01 | 2020-08-27 | 158911.13 | 158911.13 | Non Functional
202007 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202007 | 050.52895 | PRP.2636.Crabtree Ave | 796481.22 | 2020-02-20 | 2020-08-30 | 735985.77 | 735985.77 | Non Functional
202007 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202007 | 050.53086 | PRP.2634.Grapevine Rd. | 507677.62 | 2020-01-24 | 2020-08-30 | 452962.2 | 452962.2 | Non Functional
202007 | 050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 948.66 | 2020-04-13 | 2020-08-31 | 238496.08 | 238496.08 | Non Functional
202007 | 050.53682 | 050.2739.Ardmore Crossings | 29239.69 | 2020-04-13 | 2020-08-31 | 16431.93 | 29263.81 | Non Functional
202007 | 050.53707 | PRP.2637.Old Mayfield Rd | 610211 | 2020-05-10 | 2020-09-30 | 909335.87 | 909335.87 | Non Functional
202007 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202007 | 050.53901 | 2636.CountFleetLoop | 11468.51 | 2020-09-01 | 2020-09-11 | 3921.53 | 12631.37 | Non Functional
202007 | 050.54033 | RES.2737.Shawnee Run | 1715.96 | 2020-06-01 | 2020-08-14 | 5486.37 | 5486.37 | Non Functional
202007 | 050.54130 | PRP.2636.Poplar St Alley | 616055.78 | 2020-06-20 | 2020-09-30 | 637015.84 | 637015.84 | Non Functional
202007 | 050.54175 | RES.2734.McCoy Place V | 6716.28 | 2020-06-09 | 2020-08-14 | 10990.2 | 10990.2 | Non Functional
202007 | 050.54278 | COM.2734.Old Scottsville.6,Ext | 765 | 2020-06-23 | 2020-09-30 | 25293.11 | 25293.11 | Non Functional
202007 | 050.54307 | RES.2636.BluegrassCommons | 10049.47 | 2020-06-26 | 2020-07-20 | 17982.14 | 17982.14 | Non Functional
202007 | 050.54352 | 2734.Covington.Farms.Ct. | 14857.43 | 2020-06-25 | 2020-08-31 | 6592.53 | 14857.43 | Non Functional
202007 | 050.54374 | 2734.Shive Ln. II P.I. | 118350 | 2020-07-01 | 2020-09-30 | 194903.86 | 194903.86 | Non Functional
202007 | 050.54456 | 2635.FranklinSt.DawsonSprings | 18818.97 | 2020-08-03 | 2020-08-28 | 12873.37 | 12873.37 | Non Functional
202007 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202008 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202008 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202008 | 050.50660 | 2734.RiversLandingEdgeExt | 22018.21 | 2019-02-19 | 2020-09-30 | 34372.72 | 34372.72 | Non Functional
202008 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202008 | 050.51741 | Replace individual farm taps | 218243.16 | 2019-10-01 | 2020-08-30 | 621990.42 | 621990.42 | Non Functional
202008 | 050.51857 | PRP.2738.McCord St | 1153055.69 | 2019-10-01 | 2020-09-30 | 1474484.84 | 1474484.84 | Non Functional
202008 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202008 | 050.52351 | PRP.2637.S 28th St | 1262059.49 | 2019-12-25 | 2020-09-30 | 1256194.62 | 1256194.62 | Non Functional
202008 | 050.52522 | PRP.2737. Ky 52 - Danville St | 892078.91 | 2020-04-28 | 2020-09-30 | 1005664.77 | 1005664.77 | Non Functional
202008 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202008 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202008 | 050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 948.66 | 2020-04-13 | 2020-08-31 | 238496.08 | 238496.08 | Non Functional
202008 | 050.53755 | RES.2637.Lightfoot Rd Rev Ext | 4111.07 | 2020-06-01 | 2020-09-30 | 4672.64 | 4672.64 | Non Functional
202008 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202008 | 050.54130 | PRP.2636.Poplar St Alley | 616055.78 | 2020-06-20 | 2020-09-30 | 637015.84 | 637015.84 | Non Functional
202008 | 050.54175 | RES.2734.McCoy Place V | 6716.28 | 2020-06-09 | 2020-08-14 | 10990.2 | 10990.2 | Non Functional
202008 | 050.54248 | PRP.2637.Bridge St Phase 1 | 239030.9 | 2020-07-28 | 2020-09-30 | 291576.3 | 291576.3 | Non Functional
202008 | 050.54278 | COM.2734.Old Scottsville.6,Ext | 765 | 2020-06-23 | 2020-09-30 | 25293.11 | 25293.11 | Non Functional
202008 | 050.54374 | 2734.Shive Ln. II P.I. | 118350 | 2020-07-01 | 2020-09-30 | 194903.86 | 194903.86 | Non Functional
202008 | 050.54428 | 2734.Lovers.Ln.2".Ext. | 547.03 | 2020-07-14 | 2020-08-15 | 100 | 100 | Non Functional
202008 | 050.54440 | COM.2634.CadizCampGround | 16075.56 | 2020-08-17 | 2020-09-25 | 24549.76 | 28208.87 | Non Functional
202008 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202008 | 050.54508 | RES.2637.Villa Ridge Dr Ext 2 | 11530.94 | 2020-08-01 | 2020-09-30 | 11486.43 | 11486.43 | Non Functional
202008 | 050.54511 | RES.2734.McClellan Crossings | 12963.55 | 2020-07-20 | 2020-09-12 | 8300.03 | 12862.9 | Non Functional
202008 | 050.54514 | PRP.2635.Nichols St Princeton | 331753.97 | 2020-07-28 | 2020-09-30 | 307156.96 | 307156.96 | Non Functional
202008 | 050.54553 | RES.2734.Hardcastle.Ext | 3877.49 | 2020-07-29 | 2020-08-28 | 7510.88 | 7510.88 | Non Functional
202008 | 050.54617 | COM.2734.Cave Mill Station | 453.56 | 2020-08-10 | 2020-09-30 | 2147.35 | 2147.35 | Non Functional
202008 | 050.54670 | 2635.PineSt.Relocate | 22663.06 | 2020-08-17 | 2020-09-25 | 6986.64 | 22503.19 | Non Functional
202008 | 050.54687 | PRP.2636.KY 1473 Greenville | 382259.65 | 2020-08-18 | 2020-09-30 | 1473866.31 | 1473866.31 | Non Functional
202008 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202009 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202009 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202009 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202009 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202009 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202009 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202009 | 050.53755 | RES.2637.Lightfoot Rd Rev Ext | 4111.07 | 2020-06-01 | 2020-09-30 | 4672.64 | 4672.64 | Non Functional
202009 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202009 | 050.54278 | COM.2734.Old Scottsville.6,Ext | 765 | 2020-06-23 | 2020-09-30 | 25293.11 | 25293.11 | Non Functional
202009 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202009 | 050.54553 | RES.2734.Hardcastle.Ext | 3877.49 | 2020-07-29 | 2020-08-28 | 7510.88 | 7510.88 | Non Functional
202009 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202009 | 050.54816 | PRP.2635. S Mcnary St | 384864.01 | 2020-09-05 | 2020-09-30 | 243993.7 | 380638.23 | Non Functional
202009 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202010 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202010 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202010 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202010 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202010 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202010 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202010 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202010 | 050.54278 | COM.2734.Old Scottsville.6,Ext | 765 | 2020-06-23 | 2020-09-30 | 25293.11 | 25293.11 | Non Functional
202010 | 050.54279 | RES.2734.Springwater.Cove | 9606.32 | 2020-06-22 | 2020-08-14 | 46158.99 | 46158.99 | Non Functional
202010 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202010 | 050.54553 | RES.2734.Hardcastle.Ext | 3877.49 | 2020-07-29 | 2020-08-28 | 7510.88 | 7510.88 | Non Functional
202010 | 050.54596 | 050.2634.S.MadisonL/P.FY21 | 1159888.35 | 2020-10-01 | 2021-04-30 | 793784.89 | 793784.89 | Non Functional
202010 | 050.54598 | Virgie St Reg Sta Replace.FY21 | 23414.49 | 2020-10-01 | 2020-11-30 | 44744.25 | 44744.25 | Non Functional
202010 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202010 | 050.54626 | PRP.2737.Hill Ct Lancaster | 341501.55 | 2020-10-01 | 2021-01-01 | 247556.31 | 379578.67 | Non Functional
202010 | 050.54633 | 2635.Misc.Equipment.FY2021 | 12695.8 | 2020-10-01 | 2020-12-31 | 11938.32 | 11938.32 | Non Functional
202010 | 050.54634 | 2636.Misc.Equipment.FY2021 | 119369.02 | 2020-10-01 | 2020-12-31 | 116276.91 | 116276.91 | Non Functional
202010 | 050.54638 | 2651.Misc.Equipment.FY2021 | 50928.13 | 2020-10-01 | 2021-01-31 | 58863.42 | 58863.42 | Non Functional
202010 | 050.54642 | 2637.Misc.Equipment.FY2021 | 28275.48 | 2020-10-01 | 2020-11-30 | 30091.69 | 30091.69 | Non Functional
202010 | 050.54654 | 2735.Misc.Equipment.FY2021 | 30021.97 | 2020-10-01 | 2020-12-31 | 28129.58 | 28129.58 | Non Functional
202010 | 050.54655 | 2737.Misc.Equipment.FY2021 | 43589.31 | 2020-10-01 | 2020-12-31 | 45326.11 | 45326.11 | Non Functional
202010 | 050.54657 | 2738.Misc.Equipment.FY2021 | 2820.27 | 2020-10-01 | 2021-04-30 | 17809.37 | 17809.37 | Non Functional
202010 | 050.54661 | 2734.Misc.Equipment.FY2021 | 34017.06 | 2020-10-01 | 2021-01-31 | 41034.94 | 41034.94 | Non Functional
202010 | 050.54669 | Replace Mayfield Rd PRS.FY21 | 38640.45 | 2020-11-01 | 2021-04-30 | 44906.11 | 44906.11 | Non Functional
202010 | 050.54689 | PRP.2735.Hiseville | 343476.84 | 2020-10-01 | 2021-04-30 | 496483.36 | 496483.36 | Non Functional
202010 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202010 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202010 | 050.54723 | PRP.2737.W Broadway | 141370.55 | 2020-10-01 | 2021-02-01 | 416658.59 | 416658.59 | Non Functional
202010 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202010 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202010 | 050.54744 | PRP.2636.25th - Clay | 166686.88 | 2020-10-01 | 2020-10-31 | 166950.03 | 166950.03 | Non Functional
202010 | 050.54746 | 2636.East4Th.St.LowPressure | 1408424.76 | 2020-11-01 | 2021-04-30 | 1004220.15 | 1413924.4 | Non Functional
202010 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202010 | 050.54757 | 050.2739.KY 53 Widening | 173496.3 | 2020-10-01 | 2021-02-28 | 144926.28 | 175824.66 | Non Functional
202010 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202010 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202010 | 050.54761 | PRP.2637.Bridge St Phase 2 | 609754.46 | 2020-10-01 | 2021-04-07 | 788135.96 | 788135.96 | Non Functional
202010 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202010 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202010 | 050.54796 | 050.2636.4th.St.Services LP | 696871.38 | 2020-12-01 | 2021-04-30 | 638852.75 | 638852.75 | Non Functional
202010 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202010 | 050.54811 | PRP.2734.Pearl-Boat Lndg | 143475.96 | 2020-10-01 | 2021-01-31 | 140890.97 | 140890.97 | Non Functional
202010 | 050.54812 | 2736.LP East 19th Services | 820577.27 | 2020-12-01 | 2021-04-30 | 882128.21 | 882128.21 | Non Functional
202010 | 050.54822 | 2736. So. Main LP Repls.Hopk. | 1037611.3 | 2020-10-01 | 2021-05-31 | 911450.46 | 911450.46 | Non Functional
202010 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202010 | 050.54826 | Apricot - Services | 30796.55 | 2020-11-01 | 2020-12-31 | 64001.98 | 64001.98 | Non Functional
202010 | 050.54847 | 050.2736.E 19th Street | 1157115.82 | 2020-10-01 | 2021-03-22 | 885008.55 | 885008.55 | Non Functional
202010 | 050.54858 | 2638.WMR Endpoints.FY2021 | 165725.58 | 2020-10-01 | 2020-12-31 | 293046.64 | 293046.64 | Non Functional
202010 | 050.55155 | RES.2737.White Oak Road | 4523.72 | 2020-10-12 | 2020-11-27 | 4026.51 | 4026.51 | Non Functional
202010 | 050.55156 | 050.2739.Emma Lee Relocate | 779.92 | 2020-10-12 | 2020-11-27 | 1708.52 | 1708.52 | Non Functional
202010 | 050.55158 | COM.2737.Legion Drive | 917.9 | 2020-10-12 | 2020-11-27 | 2091.97 | 2091.97 | Non Functional
202010 | 050.55161 | RES.2636.LittleBlueStem | 18400.12 | 2020-11-03 | 2020-11-10 | 17343.14 | 35270.36 | Non Functional
202010 | 050.55162 | RES.2636.WatsonCircle | 22643.92 | 2020-10-20 | 2020-10-31 | 36563.61 | 36563.61 | Non Functional
202010 | 050.55163 | RES.2636.KraussCt. | 9859.26 | 2020-10-08 | 2020-10-30 | 14072.95 | 14072.95 | Non Functional
202010 | 050.55180 | RES.2736.Butler Rd. 2 inch HD | 6701.38 | 2020-10-14 | 2020-11-30 | 8737.43 | 8737.43 | Non Functional
202010 | 050.55183 | RES.2637.Calvert Drive Ext | 9893.12 | 2020-10-15 | 2020-11-30 | 7359.89 | 7359.89 | Non Functional
202010 | 050.55191 | 3302.KY MDT.FY21 | 21925.51 | 2020-10-01 | 2020-12-31 | 19111.5 | 19111.5 | Non Functional
202010 | 050.55205 | COM.2636.BENTREEDR.MN.EXT | 26631.18 | 2020-11-02 | 2020-12-06 | 6936.89 | 36853.33 | Non Functional
202010 | 050.55206 | COM.2734.The.Point.Peachtree. | 8824.65 | 2020-10-16 | 2020-11-30 | 6703.3 | 6703.3 | Non Functional
202010 | 050.55340 | Sorgho KY 4" Steel 3rd Party | 231638.66 | 2020-10-28 | 2020-11-30 | 200406.24 | 270764.62 | Non Functional
202010 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202011 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202011 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202011 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202011 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202011 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202011 | 050.53081 | COM.2734.A. FranklinBerryJr. | 2201.07 | 2019-12-11 | 2020-08-30 | 28076.74 | 28076.74 | Non Functional
202011 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202011 | 050.54278 | COM.2734.Old Scottsville.6,Ext | 765 | 2020-06-23 | 2020-09-30 | 25293.11 | 25293.11 | Non Functional
202011 | 050.54279 | RES.2734.Springwater.Cove | 9606.32 | 2020-06-22 | 2020-08-14 | 46158.99 | 46158.99 | Non Functional
202011 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202011 | 050.54553 | RES.2734.Hardcastle.Ext | 3877.49 | 2020-07-29 | 2020-08-28 | 7510.88 | 7510.88 | Non Functional
202011 | 050.54596 | 050.2634.S.MadisonL/P.FY21 | 1159888.35 | 2020-10-01 | 2021-04-30 | 793784.89 | 793784.89 | Non Functional
202011 | 050.54598 | Virgie St Reg Sta Replace.FY21 | 23414.49 | 2020-10-01 | 2020-11-30 | 44744.25 | 44744.25 | Non Functional
202011 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202011 | 050.54626 | PRP.2737.Hill Ct Lancaster | 341501.55 | 2020-10-01 | 2021-01-01 | 247556.31 | 379578.67 | Non Functional
202011 | 050.54634 | 2636.Misc.Equipment.FY2021 | 119369.02 | 2020-10-01 | 2020-12-31 | 116276.91 | 116276.91 | Non Functional
202011 | 050.54638 | 2651.Misc.Equipment.FY2021 | 50928.13 | 2020-10-01 | 2021-01-31 | 58863.42 | 58863.42 | Non Functional
202011 | 050.54654 | 2735.Misc.Equipment.FY2021 | 30021.97 | 2020-10-01 | 2020-12-31 | 28129.58 | 28129.58 | Non Functional
202011 | 050.54655 | 2737.Misc.Equipment.FY2021 | 43589.31 | 2020-10-01 | 2020-12-31 | 45326.11 | 45326.11 | Non Functional
202011 | 050.54657 | 2738.Misc.Equipment.FY2021 | 2820.27 | 2020-10-01 | 2021-04-30 | 17809.37 | 17809.37 | Non Functional
202011 | 050.54661 | 2734.Misc.Equipment.FY2021 | 34017.06 | 2020-10-01 | 2021-01-31 | 41034.94 | 41034.94 | Non Functional
202011 | 050.54669 | Replace Mayfield Rd PRS.FY21 | 38640.45 | 2020-11-01 | 2021-04-30 | 44906.11 | 44906.11 | Non Functional
202011 | 050.54689 | PRP.2735.Hiseville | 343476.84 | 2020-10-01 | 2021-04-30 | 496483.36 | 496483.36 | Non Functional
202011 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202011 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202011 | 050.54723 | PRP.2737.W Broadway | 141370.55 | 2020-10-01 | 2021-02-01 | 416658.59 | 416658.59 | Non Functional
202011 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202011 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202011 | 050.54746 | 2636.East4Th.St.LowPressure | 1408424.76 | 2020-11-01 | 2021-04-30 | 1004220.15 | 1413924.4 | Non Functional
202011 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202011 | 050.54757 | 050.2739.KY 53 Widening | 173496.3 | 2020-10-01 | 2021-02-28 | 144926.28 | 175824.66 | Non Functional
202011 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202011 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202011 | 050.54761 | PRP.2637.Bridge St Phase 2 | 609754.46 | 2020-10-01 | 2021-04-07 | 788135.96 | 788135.96 | Non Functional
202011 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202011 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202011 | 050.54796 | 050.2636.4th.St.Services LP | 696871.38 | 2020-12-01 | 2021-04-30 | 638852.75 | 638852.75 | Non Functional
202011 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202011 | 050.54811 | PRP.2734.Pearl-Boat Lndg | 143475.96 | 2020-10-01 | 2021-01-31 | 140890.97 | 140890.97 | Non Functional
202011 | 050.54812 | 2736.LP East 19th Services | 820577.27 | 2020-12-01 | 2021-04-30 | 882128.21 | 882128.21 | Non Functional
202011 | 050.54822 | 2736. So. Main LP Repls.Hopk. | 1037611.3 | 2020-10-01 | 2021-05-31 | 911450.46 | 911450.46 | Non Functional
202011 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202011 | 050.54847 | 050.2736.E 19th Street | 1157115.82 | 2020-10-01 | 2021-03-22 | 885008.55 | 885008.55 | Non Functional
202011 | 050.54856 | 2734.LP.Cherry.St. - Franklin | 125228.64 | 2020-11-03 | 2021-03-31 | 114236.25 | 126914.85 | Non Functional
202011 | 050.54858 | 2638.WMR Endpoints.FY2021 | 165725.58 | 2020-10-01 | 2020-12-31 | 293046.64 | 293046.64 | Non Functional
202011 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202011 | 050.55180 | RES.2736.Butler Rd. 2 inch HD | 6701.38 | 2020-10-14 | 2020-11-30 | 8737.43 | 8737.43 | Non Functional
202011 | 050.55183 | RES.2637.Calvert Drive Ext | 9893.12 | 2020-10-15 | 2020-11-30 | 7359.89 | 7359.89 | Non Functional
202011 | 050.55205 | COM.2636.BENTREEDR.MN.EXT | 26631.18 | 2020-11-02 | 2020-12-06 | 6936.89 | 36853.33 | Non Functional
202011 | 050.55206 | COM.2734.The.Point.Peachtree. | 8824.65 | 2020-10-16 | 2020-11-30 | 6703.3 | 6703.3 | Non Functional
202011 | 050.55304 | RES.2638.Twin Hill Rd Rev Ext | 4207.16 | 2020-10-01 | 2020-11-30 | 2501.99 | 2501.99 | Non Functional
202011 | 050.55326 | RES.2638.Race Track Rd Ext | 11530.59 | 2020-12-01 | 2021-01-30 | 5162.59 | 16125.32 | Non Functional
202011 | 050.55371 | RES.2637.Camilla Ln Main Ext | 2679.48 | 2020-11-05 | 2020-11-30 | 2824.57 | 2824.57 | Non Functional
202011 | 050.55413 | PRP.2635.W Main St | 805502.34 | 2020-11-20 | 2021-07-30 | 812241.67 | 812241.67 | Non Functional
202011 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202011 | 050.55440 | RES.2636.PECANAVE.S.MN.EXT | 22380.15 | 2020-11-12 | 2020-11-18 | 28514.31 | 28514.31 | Non Functional
202011 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202012 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202012 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202012 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202012 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202012 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202012 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202012 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202012 | 050.54596 | 050.2634.S.MadisonL/P.FY21 | 1159888.35 | 2020-10-01 | 2021-04-30 | 793784.89 | 793784.89 | Non Functional
202012 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202012 | 050.54634 | 2636.Misc.Equipment.FY2021 | 119369.02 | 2020-10-01 | 2020-12-31 | 116276.91 | 116276.91 | Non Functional
202012 | 050.54638 | 2651.Misc.Equipment.FY2021 | 50928.13 | 2020-10-01 | 2021-01-31 | 58863.42 | 58863.42 | Non Functional
202012 | 050.54657 | 2738.Misc.Equipment.FY2021 | 2820.27 | 2020-10-01 | 2021-04-30 | 17809.37 | 17809.37 | Non Functional
202012 | 050.54661 | 2734.Misc.Equipment.FY2021 | 34017.06 | 2020-10-01 | 2021-01-31 | 41034.94 | 41034.94 | Non Functional
202012 | 050.54669 | Replace Mayfield Rd PRS.FY21 | 38640.45 | 2020-11-01 | 2021-04-30 | 44906.11 | 44906.11 | Non Functional
202012 | 050.54689 | PRP.2735.Hiseville | 343476.84 | 2020-10-01 | 2021-04-30 | 496483.36 | 496483.36 | Non Functional
202012 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202012 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202012 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202012 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202012 | 050.54746 | 2636.East4Th.St.LowPressure | 1408424.76 | 2020-11-01 | 2021-04-30 | 1004220.15 | 1413924.4 | Non Functional
202012 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202012 | 050.54757 | 050.2739.KY 53 Widening | 173496.3 | 2020-10-01 | 2021-02-28 | 144926.28 | 175824.66 | Non Functional
202012 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202012 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202012 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202012 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202012 | 050.54796 | 050.2636.4th.St.Services LP | 696871.38 | 2020-12-01 | 2021-04-30 | 638852.75 | 638852.75 | Non Functional
202012 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202012 | 050.54812 | 2736.LP East 19th Services | 820577.27 | 2020-12-01 | 2021-04-30 | 882128.21 | 882128.21 | Non Functional
202012 | 050.54822 | 2736. So. Main LP Repls.Hopk. | 1037611.3 | 2020-10-01 | 2021-05-31 | 911450.46 | 911450.46 | Non Functional
202012 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202012 | 050.54830 | 2734.LP Cherry St Services | 24965.51 | 2020-11-01 | 2021-03-31 | 68539.38 | 68539.38 | Non Functional
202012 | 050.54847 | 050.2736.E 19th Street | 1157115.82 | 2020-10-01 | 2021-03-22 | 885008.55 | 885008.55 | Non Functional
202012 | 050.54856 | 2734.LP.Cherry.St. - Franklin | 125228.64 | 2020-11-03 | 2021-03-31 | 114236.25 | 126914.85 | Non Functional
202012 | 050.55122 | 2736.Elkton YZ Odorizer FY21 | 35895.18 | 2020-10-01 | 2020-12-31 | 32117.98 | 32117.98 | Non Functional
202012 | 050.55166 | 2612.KY Corrector Repl.FY21 | 38765.79 | 2020-10-01 | 2021-06-30 | 44686.42 | 44686.42 | Non Functional
202012 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202012 | 050.55413 | PRP.2635.W Main St | 805502.34 | 2020-11-20 | 2021-07-30 | 812241.67 | 812241.67 | Non Functional
202012 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202012 | 050.55455 | RES.2739.Twin Lakes Ph 2 | 54283.77 | 2020-11-23 | 2021-01-29 | 49511.79 | 55750.74 | Non Functional
202012 | 050.55456 | RES.2634.OATSST.MNEXT. | 25554.7 | 2020-12-02 | 2020-12-10 | 2581.81 | 26513.1 | Non Functional
202012 | 050.55510 | COM.2736.Davenport Ln. Ext. | -523.41 | 2020-11-16 | 2020-12-31 | 6806.53 | 6806.53 | Non Functional
202012 | 050.55511 | RES.2735.Short.Cut.HorseCave | 344.82 | 2020-11-24 | 2021-01-15 | 5694.71 | 5694.71 | Non Functional
202012 | 050.55525 | RES.2738.Highway 61 | -2103.44 | 2020-11-30 | 2020-12-31 | 4198.7 | 4198.7 | Non Functional
202012 | 050.55531 | RES.2737.Harvest Lane | 10738.31 | 2020-12-01 | 2021-01-29 | 3654.06 | 12309.9 | Non Functional
202012 | 050.55535 | COM.2734.So.Warren.Richpond | 176755.99 | 2020-12-01 | 2021-04-30 | 303253.71 | 303253.71 | Non Functional
202012 | 050.55561 | PRP.2637.Broad St | 518000.26 | 2020-12-18 | 2021-07-15 | 706386.28 | 706386.28 | Non Functional
202012 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202012 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202101 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202101 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202101 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202101 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202101 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202101 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202101 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202101 | 050.54596 | 050.2634.S.MadisonL/P.FY21 | 1159888.35 | 2020-10-01 | 2021-04-30 | 793784.89 | 793784.89 | Non Functional
202101 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202101 | 050.54657 | 2738.Misc.Equipment.FY2021 | 2820.27 | 2020-10-01 | 2021-04-30 | 17809.37 | 17809.37 | Non Functional
202101 | 050.54669 | Replace Mayfield Rd PRS.FY21 | 38640.45 | 2020-11-01 | 2021-04-30 | 44906.11 | 44906.11 | Non Functional
202101 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202101 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202101 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202101 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202101 | 050.54746 | 2636.East4Th.St.LowPressure | 1408424.76 | 2020-11-01 | 2021-04-30 | 1004220.15 | 1413924.4 | Non Functional
202101 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202101 | 050.54757 | 050.2739.KY 53 Widening | 173496.3 | 2020-10-01 | 2021-02-28 | 144926.28 | 175824.66 | Non Functional
202101 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202101 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202101 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202101 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202101 | 050.54796 | 050.2636.4th.St.Services LP | 696871.38 | 2020-12-01 | 2021-04-30 | 638852.75 | 638852.75 | Non Functional
202101 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202101 | 050.54812 | 2736.LP East 19th Services | 820577.27 | 2020-12-01 | 2021-04-30 | 882128.21 | 882128.21 | Non Functional
202101 | 050.54822 | 2736. So. Main LP Repls.Hopk. | 1037611.3 | 2020-10-01 | 2021-05-31 | 911450.46 | 911450.46 | Non Functional
202101 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202101 | 050.54830 | 2734.LP Cherry St Services | 24965.51 | 2020-11-01 | 2021-03-31 | 68539.38 | 68539.38 | Non Functional
202101 | 050.54847 | 050.2736.E 19th Street | 1157115.82 | 2020-10-01 | 2021-03-22 | 885008.55 | 885008.55 | Non Functional
202101 | 050.54856 | 2734.LP.Cherry.St. - Franklin | 125228.64 | 2020-11-03 | 2021-03-31 | 114236.25 | 126914.85 | Non Functional
202101 | 050.55122 | 2736.Elkton YZ Odorizer FY21 | 35895.18 | 2020-10-01 | 2020-12-31 | 32117.98 | 32117.98 | Non Functional
202101 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202101 | 050.55413 | PRP.2635.W Main St | 805502.34 | 2020-11-20 | 2021-07-30 | 812241.67 | 812241.67 | Non Functional
202101 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202101 | 050.55535 | COM.2734.So.Warren.Richpond | 176755.99 | 2020-12-01 | 2021-04-30 | 303253.71 | 303253.71 | Non Functional
202101 | 050.55561 | PRP.2637.Broad St | 518000.26 | 2020-12-18 | 2021-07-15 | 706386.28 | 706386.28 | Non Functional
202101 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202101 | 050.55639 | 050.2637.Buckner Ln Relocate | 23063.22 | 2021-01-01 | 2021-04-30 | 21861.11 | 21861.11 | Non Functional
202101 | 050.55667 | PRP.2737.Ledford Lane | 353033.83 | 2021-01-25 | 2021-07-30 | 488200.79 | 488200.79 | Non Functional
202101 | 050.55692 | PRP.2734.High St Alley BG | 312269.61 | 2021-01-22 | 2021-08-30 | 565455.01 | 565455.01 | Non Functional
202101 | 050.55693 | PRP.2734.US 31W - Emmett Ave | 97563.09 | 2021-01-05 | 2021-03-22 | 33709.34 | 100423.87 | Non Functional
202101 | 050.55705 | RES.2636.BRIDGEWOODDR.MN.EXT | 22607.46 | 2021-01-14 | 2021-01-25 | 23594.48 | 23594.48 | Non Functional
202101 | 050.55713 | RES.2734.Price Farms IA | 22882.75 | 2021-01-11 | 2021-04-16 | 23899.87 | 23899.87 | Non Functional
202101 | 050.55714 | RES.2734.Satgner Farms Phase | 46513.97 | 2021-01-11 | 2021-03-31 | 60045.57 | 60045.57 | Non Functional
202101 | 050.55716 | RES.2734.Carter Crossing IA | 42137.24 | 2021-06-01 | 2021-06-01 | 32277.52 | 32277.52 | Non Functional
202101 | 050.55738 | PRP.2636.25th St Ann | 238095.73 | 2021-01-19 | 2021-05-30 | 243403.02 | 243403.02 | Non Functional
202101 | 050.55740 | RES.2636.NORTHWOODDR.MN.EXT | 19972.92 | 2021-02-16 | 2021-02-25 | 19055.93 | 19055.93 | Non Functional
202101 | 050.55750 | RES.2636.CHELSADR.UTICAMN.EXT | 12041.93 | 2021-02-08 | 2021-02-15 | 14904.21 | 28820.22 | Non Functional
202101 | 050.55751 | RES.2636.MILTONRD.MN.EXT | -4802.11 | 2021-02-02 | 2021-09-30 | 13748.8 | 13748.8 | Non Functional
202101 | 050.55810 | PRP.2734.BG Centerline 3 | 202449.96 | 2021-01-28 | 2022-09-30 | 985873.4 | 985873.4 | Non Functional
202101 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202102 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202102 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202102 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202102 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202102 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202102 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202102 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202102 | 050.54596 | 050.2634.S.MadisonL/P.FY21 | 1159888.35 | 2020-10-01 | 2021-04-30 | 793784.89 | 793784.89 | Non Functional
202102 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202102 | 050.54657 | 2738.Misc.Equipment.FY2021 | 2820.27 | 2020-10-01 | 2021-04-30 | 17809.37 | 17809.37 | Non Functional
202102 | 050.54669 | Replace Mayfield Rd PRS.FY21 | 38640.45 | 2020-11-01 | 2021-04-30 | 44906.11 | 44906.11 | Non Functional
202102 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202102 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202102 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202102 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202102 | 050.54746 | 2636.East4Th.St.LowPressure | 1408424.76 | 2020-11-01 | 2021-04-30 | 1004220.15 | 1413924.4 | Non Functional
202102 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202102 | 050.54757 | 050.2739.KY 53 Widening | 173496.3 | 2020-10-01 | 2021-02-28 | 144926.28 | 175824.66 | Non Functional
202102 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202102 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202102 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202102 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202102 | 050.54796 | 050.2636.4th.St.Services LP | 696871.38 | 2020-12-01 | 2021-04-30 | 638852.75 | 638852.75 | Non Functional
202102 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202102 | 050.54812 | 2736.LP East 19th Services | 820577.27 | 2020-12-01 | 2021-04-30 | 882128.21 | 882128.21 | Non Functional
202102 | 050.54822 | 2736. So. Main LP Repls.Hopk. | 1037611.3 | 2020-10-01 | 2021-05-31 | 911450.46 | 911450.46 | Non Functional
202102 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202102 | 050.54830 | 2734.LP Cherry St Services | 24965.51 | 2020-11-01 | 2021-03-31 | 68539.38 | 68539.38 | Non Functional
202102 | 050.54847 | 050.2736.E 19th Street | 1157115.82 | 2020-10-01 | 2021-03-22 | 885008.55 | 885008.55 | Non Functional
202102 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202102 | 050.55413 | PRP.2635.W Main St | 805502.34 | 2020-11-20 | 2021-07-30 | 812241.67 | 812241.67 | Non Functional
202102 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202102 | 050.55528 | COM.2637.Holt Rd Rev Ext_ | 11346.34 | 2020-11-01 | 2021-03-28 | 11440.41 | 11440.41 | Non Functional
202102 | 050.55535 | COM.2734.So.Warren.Richpond | 176755.99 | 2020-12-01 | 2021-04-30 | 303253.71 | 303253.71 | Non Functional
202102 | 050.55561 | PRP.2637.Broad St | 518000.26 | 2020-12-18 | 2021-07-15 | 706386.28 | 706386.28 | Non Functional
202102 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202102 | 050.55639 | 050.2637.Buckner Ln Relocate | 23063.22 | 2021-01-01 | 2021-04-30 | 21861.11 | 21861.11 | Non Functional
202102 | 050.55667 | PRP.2737.Ledford Lane | 353033.83 | 2021-01-25 | 2021-07-30 | 488200.79 | 488200.79 | Non Functional
202102 | 050.55692 | PRP.2734.High St Alley BG | 312269.61 | 2021-01-22 | 2021-08-30 | 565455.01 | 565455.01 | Non Functional
202102 | 050.55693 | PRP.2734.US 31W - Emmett Ave | 97563.09 | 2021-01-05 | 2021-03-22 | 33709.34 | 100423.87 | Non Functional
202102 | 050.55705 | RES.2636.BRIDGEWOODDR.MN.EXT | 22607.46 | 2021-01-14 | 2021-01-25 | 23594.48 | 23594.48 | Non Functional
202102 | 050.55713 | RES.2734.Price Farms IA | 22882.75 | 2021-01-11 | 2021-04-16 | 23899.87 | 23899.87 | Non Functional
202102 | 050.55714 | RES.2734.Satgner Farms Phase | 46513.97 | 2021-01-11 | 2021-03-31 | 60045.57 | 60045.57 | Non Functional
202102 | 050.55716 | RES.2734.Carter Crossing IA | 42137.24 | 2021-06-01 | 2021-06-01 | 32277.52 | 32277.52 | Non Functional
202102 | 050.55738 | PRP.2636.25th St Ann | 238095.73 | 2021-01-19 | 2021-05-30 | 243403.02 | 243403.02 | Non Functional
202102 | 050.55740 | RES.2636.NORTHWOODDR.MN.EXT | 19972.92 | 2021-02-16 | 2021-02-25 | 19055.93 | 19055.93 | Non Functional
202102 | 050.55751 | RES.2636.MILTONRD.MN.EXT | -4802.11 | 2021-02-02 | 2021-09-30 | 13748.8 | 13748.8 | Non Functional
202102 | 050.55810 | PRP.2734.BG Centerline 3 | 202449.96 | 2021-01-28 | 2022-09-30 | 985873.4 | 985873.4 | Non Functional
202102 | 050.55902 | 2636.WinklerRd.Replacement | 891.05 | 2021-03-01 | 2021-03-31 | 3105.31 | 3105.31 | Non Functional
202102 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202103 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202103 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202103 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202103 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202103 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202103 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202103 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202103 | 050.54596 | 050.2634.S.MadisonL/P.FY21 | 1159888.35 | 2020-10-01 | 2021-04-30 | 793784.89 | 793784.89 | Non Functional
202103 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202103 | 050.54657 | 2738.Misc.Equipment.FY2021 | 2820.27 | 2020-10-01 | 2021-04-30 | 17809.37 | 17809.37 | Non Functional
202103 | 050.54669 | Replace Mayfield Rd PRS.FY21 | 38640.45 | 2020-11-01 | 2021-04-30 | 44906.11 | 44906.11 | Non Functional
202103 | 050.54690 | PRP.2735.Rowletts | 396837.11 | 2020-10-01 | 2021-05-30 | 442844.44 | 442844.44 | Non Functional
202103 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202103 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202103 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202103 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202103 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202103 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202103 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202103 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202103 | 050.54796 | 050.2636.4th.St.Services LP | 696871.38 | 2020-12-01 | 2021-04-30 | 638852.75 | 638852.75 | Non Functional
202103 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202103 | 050.54812 | 2736.LP East 19th Services | 820577.27 | 2020-12-01 | 2021-04-30 | 882128.21 | 882128.21 | Non Functional
202103 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202103 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202103 | 050.55413 | PRP.2635.W Main St | 805502.34 | 2020-11-20 | 2021-07-30 | 812241.67 | 812241.67 | Non Functional
202103 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202103 | 050.55535 | COM.2734.So.Warren.Richpond | 176755.99 | 2020-12-01 | 2021-04-30 | 303253.71 | 303253.71 | Non Functional
202103 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202103 | 050.55639 | 050.2637.Buckner Ln Relocate | 23063.22 | 2021-01-01 | 2021-04-30 | 21861.11 | 21861.11 | Non Functional
202103 | 050.55667 | PRP.2737.Ledford Lane | 353033.83 | 2021-01-25 | 2021-07-30 | 488200.79 | 488200.79 | Non Functional
202103 | 050.55692 | PRP.2734.High St Alley BG | 312269.61 | 2021-01-22 | 2021-08-30 | 565455.01 | 565455.01 | Non Functional
202103 | 050.55705 | RES.2636.BRIDGEWOODDR.MN.EXT | 22607.46 | 2021-01-14 | 2021-01-25 | 23594.48 | 23594.48 | Non Functional
202103 | 050.55714 | RES.2734.Satgner Farms Phase | 46513.97 | 2021-01-11 | 2021-03-31 | 60045.57 | 60045.57 | Non Functional
202103 | 050.55716 | RES.2734.Carter Crossing IA | 42137.24 | 2021-06-01 | 2021-06-01 | 32277.52 | 32277.52 | Non Functional
202103 | 050.55740 | RES.2636.NORTHWOODDR.MN.EXT | 19972.92 | 2021-02-16 | 2021-02-25 | 19055.93 | 19055.93 | Non Functional
202103 | 050.55751 | RES.2636.MILTONRD.MN.EXT | -4802.11 | 2021-02-02 | 2021-09-30 | 13748.8 | 13748.8 | Non Functional
202103 | 050.55810 | PRP.2734.BG Centerline 3 | 202449.96 | 2021-01-28 | 2022-09-30 | 985873.4 | 985873.4 | Non Functional
202103 | 050.55814 | PRP.2637.Hill St | 470738.56 | 2021-02-16 | 2021-09-30 | 610610.12 | 610610.12 | Non Functional
202103 | 050.55844 | COM.2637.Barkley Field Ext | 97119.6 | 2021-07-01 | 2021-09-30 | 347918.61 | 347918.61 | Non Functional
202103 | 050.55847 | RES.2736.Buttermilk Rd. Ext | 4119.66 | 2021-02-05 | 2021-04-30 | 4684.87 | 4684.87 | Non Functional
202103 | 050.55848 | RES.2636.BOSTONLAFOONRD.MN.EX | 5819.6 | 2021-03-03 | 2021-04-30 | 1781.15 | 1781.15 | Non Functional
202103 | 050.55902 | 2636.WinklerRd.Replacement | 891.05 | 2021-03-01 | 2021-03-31 | 3105.31 | 3105.31 | Non Functional
202103 | 050.55908 | Rotary Meters Replacement | 43383.18 | 2020-10-01 | 2021-05-30 | 63199.22 | 63199.22 | Non Functional
202103 | 050.55951 | IND.2738.American Wood Fiber | 135290.84 | 2021-03-01 | 2021-06-18 | 132015.59 | 132015.59 | Non Functional
202103 | 050.55997 | 2636.LP.FREDERICAST. | 843765.58 | 2021-03-01 | 2021-07-30 | 1002731.87 | 1002731.87 | Non Functional
202103 | 050.56027 | RES.2734.Par3 - Olde Stone | 9124.73 | 2021-03-10 | 2021-04-30 | 17638.06 | 17638.06 | Non Functional
202103 | 050.56030 | RES.2734.MagnoliaHillsIII | 8671.77 | 2021-03-10 | 2021-04-30 | 19616.56 | 19616.56 | Non Functional
202103 | 050.56052 | PRP.2636.14th St | 344817.21 | 2021-03-20 | 2021-07-30 | 827695.74 | 827695.74 | Non Functional
202103 | 050.56088 | RES.2636.KEENELANDSEBISCUITLP | 12192.27 | 2021-04-05 | 2021-04-09 | 16056.73 | 16056.73 | Non Functional
202103 | 050.56117 | RES.2636.OttawaDr. Main Ext. | 18552.64 | 2021-04-01 | 2021-04-21 | 23261.43 | 23261.43 | Non Functional
202103 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202104 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202104 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202104 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202104 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202104 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202104 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202104 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202104 | 050.54625 | PRP.2737.Danville Ave | 756723.65 | 2020-10-01 | 2021-09-30 | 900859.8 | 900859.8 | Non Functional
202104 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202104 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202104 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202104 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202104 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202104 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202104 | 050.54762 | PRP.2734.4th St | 842455.75 | 2020-10-01 | 2021-06-30 | 909357.01 | 909357.01 | Non Functional
202104 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202104 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202104 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202104 | 050.55165 | 2612. KY Emergency Reg.FY21 | 27306.81 | 2020-10-01 | 2021-06-30 | 31918.87 | 31918.87 | Non Functional
202104 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202104 | 050.55413 | PRP.2635.W Main St | 805502.34 | 2020-11-20 | 2021-07-30 | 812241.67 | 812241.67 | Non Functional
202104 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202104 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202104 | 050.55667 | PRP.2737.Ledford Lane | 353033.83 | 2021-01-25 | 2021-07-30 | 488200.79 | 488200.79 | Non Functional
202104 | 050.55692 | PRP.2734.High St Alley BG | 312269.61 | 2021-01-22 | 2021-08-30 | 565455.01 | 565455.01 | Non Functional
202104 | 050.55716 | RES.2734.Carter Crossing IA | 42137.24 | 2021-06-01 | 2021-06-01 | 32277.52 | 32277.52 | Non Functional
202104 | 050.55751 | RES.2636.MILTONRD.MN.EXT | -4802.11 | 2021-02-02 | 2021-09-30 | 13748.8 | 13748.8 | Non Functional
202104 | 050.55810 | PRP.2734.BG Centerline 3 | 202449.96 | 2021-01-28 | 2022-09-30 | 985873.4 | 985873.4 | Non Functional
202104 | 050.55814 | PRP.2637.Hill St | 470738.56 | 2021-02-16 | 2021-09-30 | 610610.12 | 610610.12 | Non Functional
202104 | 050.55844 | COM.2637.Barkley Field Ext | 97119.6 | 2021-07-01 | 2021-09-30 | 347918.61 | 347918.61 | Non Functional
202104 | 050.55908 | Rotary Meters Replacement | 43383.18 | 2020-10-01 | 2021-05-30 | 63199.22 | 63199.22 | Non Functional
202104 | 050.55917 | LP.2734.McGoodwin.Replc | 8160.95 | 2021-03-01 | 2021-07-30 | 332897.31 | 332897.31 | Non Functional
202104 | 050.55945 | RES.2636.BURLEWBLVDAPARTMENTS | 8583.12 | 2021-03-16 | 2021-05-30 | 2829.4 | 2829.4 | Non Functional
202104 | 050.55951 | IND.2738.American Wood Fiber | 135290.84 | 2021-03-01 | 2021-06-18 | 132015.59 | 132015.59 | Non Functional
202104 | 050.55997 | 2636.LP.FREDERICAST. | 843765.58 | 2021-03-01 | 2021-07-30 | 1002731.87 | 1002731.87 | Non Functional
202104 | 050.56052 | PRP.2636.14th St | 344817.21 | 2021-03-20 | 2021-07-30 | 827695.74 | 827695.74 | Non Functional
202104 | 050.56097 | PRP.2735.Oakland | 263168.88 | 2021-03-23 | 2021-08-28 | 468885.72 | 468885.72 | Non Functional
202104 | 050.56111 | IND.2734.Proj.SapphireII (AIC) | 52239.21 | 2021-03-19 | 2021-08-31 | 254906.88 | 254906.88 | Non Functional
202104 | 050.56112 | IND.2734.Proj.Sapphire (MEC) | 63422.79 | 2021-03-19 | 2021-08-30 | 267612.55 | 267612.55 | Non Functional
202104 | 050.56133 | 050.2636.Frederica St Services | 170412.07 | 2021-04-01 | 2021-09-30 | 375568.94 | 375568.94 | Non Functional
202104 | 050.56147 | RES.2739.Cherokee Drive | 2468.37 | 2021-03-29 | 2021-07-30 | 4243.98 | 4243.98 | Non Functional
202104 | 050.56164 | 050.2638.Hwy 121 SYS IMP | 54089.52 | 2021-05-01 | 2021-07-31 | 81806.15 | 81806.15 | Non Functional
202104 | 050.56170 | 2734.Redbud Sta. Retire | 6012.54 | 2021-03-26 | 2021-07-30 | 182193.03 | 182193.03 | Non Functional
202104 | 050.56254 | RES.2636.NEWBOLTRD.HAYDEN.MN. | 8134.79 | 2021-04-12 | 2021-05-30 | 6708.78 | 6708.78 | Non Functional
202104 | 050.56258 | 050.2637.Said Rd 6 in Replace | 9673.8 | 2021-05-01 | 2021-09-30 | 64526.22 | 64526.22 | Non Functional
202104 | 050.56303 | IND.2735.T.Marzetti - | 22808.98 | 2021-04-21 | 2021-08-31 | 150645.33 | 150645.33 | Non Functional
202104 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202105 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202105 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202105 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202105 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202105 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202105 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202105 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202105 | 050.54694 | PRP.2735.Grandview Dr | 655604.18 | 2020-10-01 | 2021-07-31 | 711033.35 | 711033.35 | Non Functional
202105 | 050.54742 | PRP.2738.Perryville Rd | 1079510.64 | 2020-10-01 | 2021-09-30 | 1139244.49 | 1139244.49 | Non Functional
202105 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202105 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202105 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202105 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202105 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202105 | 050.54809 | PRP.2734.E 3rd St Russellvill | 867005.05 | 2020-10-01 | 2021-07-30 | 548990.23 | 983557.94 | Non Functional
202105 | 050.54825 | 2736.LP S. Main Sevices | 336246.48 | 2020-12-01 | 2021-06-30 | 326874.1 | 326874.1 | Non Functional
202105 | 050.55167 | 2612.KY RTU Upgrades.FY21 | 101302.5 | 2020-10-01 | 2021-06-30 | 116699.86 | 116699.86 | Non Functional
202105 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202105 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202105 | 050.55692 | PRP.2734.High St Alley BG | 312269.61 | 2021-01-22 | 2021-08-30 | 565455.01 | 565455.01 | Non Functional
202105 | 050.55716 | RES.2734.Carter Crossing IA | 42137.24 | 2021-06-01 | 2021-06-01 | 32277.52 | 32277.52 | Non Functional
202105 | 050.55751 | RES.2636.MILTONRD.MN.EXT | -4802.11 | 2021-02-02 | 2021-09-30 | 13748.8 | 13748.8 | Non Functional
202105 | 050.55810 | PRP.2734.BG Centerline 3 | 202449.96 | 2021-01-28 | 2022-09-30 | 985873.4 | 985873.4 | Non Functional
202105 | 050.55814 | PRP.2637.Hill St | 470738.56 | 2021-02-16 | 2021-09-30 | 610610.12 | 610610.12 | Non Functional
202105 | 050.55844 | COM.2637.Barkley Field Ext | 97119.6 | 2021-07-01 | 2021-09-30 | 347918.61 | 347918.61 | Non Functional
202105 | 050.55917 | LP.2734.McGoodwin.Replc | 8160.95 | 2021-03-01 | 2021-07-30 | 332897.31 | 332897.31 | Non Functional
202105 | 050.55924 | Ground Bed - N 18th St | 23175.87 | 2021-03-01 | 2021-07-30 | 36756.7 | 36756.7 | Non Functional
202105 | 050.55951 | IND.2738.American Wood Fiber | 135290.84 | 2021-03-01 | 2021-06-18 | 132015.59 | 132015.59 | Non Functional
202105 | 050.55997 | 2636.LP.FREDERICAST. | 843765.58 | 2021-03-01 | 2021-07-30 | 1002731.87 | 1002731.87 | Non Functional
202105 | 050.56052 | PRP.2636.14th St | 344817.21 | 2021-03-20 | 2021-07-30 | 827695.74 | 827695.74 | Non Functional
202105 | 050.56097 | PRP.2735.Oakland | 263168.88 | 2021-03-23 | 2021-08-28 | 468885.72 | 468885.72 | Non Functional
202105 | 050.56111 | IND.2734.Proj.SapphireII (AIC) | 52239.21 | 2021-03-19 | 2021-08-31 | 254906.88 | 254906.88 | Non Functional
202105 | 050.56112 | IND.2734.Proj.Sapphire (MEC) | 63422.79 | 2021-03-19 | 2021-08-30 | 267612.55 | 267612.55 | Non Functional
202105 | 050.56133 | 050.2636.Frederica St Services | 170412.07 | 2021-04-01 | 2021-09-30 | 375568.94 | 375568.94 | Non Functional
202105 | 050.56147 | RES.2739.Cherokee Drive | 2468.37 | 2021-03-29 | 2021-07-30 | 4243.98 | 4243.98 | Non Functional
202105 | 050.56151 | LP.2736.17th.St.Replacement | 195666.75 | 2021-04-01 | 2021-09-30 | 706946.09 | 706946.09 | Non Functional
202105 | 050.56164 | 050.2638.Hwy 121 SYS IMP | 54089.52 | 2021-05-01 | 2021-07-31 | 81806.15 | 81806.15 | Non Functional
202105 | 050.56170 | 2734.Redbud Sta. Retire | 6012.54 | 2021-03-26 | 2021-07-30 | 182193.03 | 182193.03 | Non Functional
202105 | 050.56236 | COM.2735.Mammoth Cave Ext | 6900.28 | 2021-04-08 | 2021-05-31 | 10026.92 | 10026.92 | Non Functional
202105 | 050.56252 | Shelbyville KY WMR Towers.FY21 | 119788.04 | 2021-05-01 | 2021-10-31 | 183604.61 | 183604.61 | Non Functional
202105 | 050.56258 | 050.2637.Said Rd 6 in Replace | 9673.8 | 2021-05-01 | 2021-09-30 | 64526.22 | 64526.22 | Non Functional
202105 | 050.56260 | PRP.2637.S 3rd St | 23565.78 | 2021-06-30 | 2021-09-30 | 673866.89 | 673866.89 | Non Functional
202105 | 050.56268 | RES.2636.SETTLESRD.MN.EXT | 1106.51 | 2021-06-30 | 2021-06-30 | 6350.18 | 6350.18 | Non Functional
202105 | 050.56279 | RES.2636.HARMONSFERRYRD.MN.EX | 2460.63 | 2021-05-17 | 2021-07-30 | 7072.48 | 7072.48 | Non Functional
202105 | 050.56303 | IND.2735.T.Marzetti - | 22808.98 | 2021-04-21 | 2021-08-31 | 150645.33 | 150645.33 | Non Functional
202105 | 050.56348 | RES.2637.Kirby Ln Rev Ext | 6469.99 | 2021-05-17 | 2021-06-30 | 3834.14 | 3834.14 | Non Functional
202105 | 050.56356 | INT.2739.Clear Creek Exposure | 17713.49 | 2021-05-01 | 2021-09-15 | 187325.75 | 187325.75 | Non Functional
202105 | 050.56372 | PRP.2734.Sycamore St | 93322.02 | 2021-05-15 | 2021-09-30 | 835264.31 | 835264.31 | Non Functional
202105 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd
202106 | 050.46190 | 050.2634.Westside Vlv Replace | 12.25 | 2017-06-19 | 2021-09-28 | 6029.91 | 6029.91 | Non Functional
202106 | 050.50630 | 050.2637.Westhaven Dr Ext | 11.33 | 2019-02-07 | 2021-09-30 | 4095.19 | 4095.19 | Non Functional
202106 | 050.50720 | 050.2638.S.11th Street Ext | 1176.57 | 2019-02-21 | 2021-09-28 | 7578.6 | 7578.6 | Non Functional
202106 | 050.51911 | 2734.BogleTrailer Park Ret. | 22.17 | 2019-08-14 | 2019-09-27 | 164.58 | 164.58 | Non Functional
202106 | 050.52761 | 2634.FreeTown Rd.Ret | 188.67 | 2019-11-18 | 2019-11-30 | 5221.68 | 5221.68 | Non Functional
202106 | 050.53763 | PRP.2636.5th-Sycamore | 41194.65 | 2020-04-28 | 2021-09-30 | 53823.25 | 53823.25 | Non Functional
202106 | 050.54507 | RES.2637.Highland Ch Rd 2 | 130.42 | 2020-08-01 | 2021-09-30 | 2754.51 | 2754.51 | Non Functional
202106 | 050.54743 | PRP.2635.Princeton North | 1349144.19 | 2020-10-01 | 2021-08-31 | 899861.36 | 1505064.22 | Non Functional
202106 | 050.54755 | 050.2634.Low Pressure Services | 924049.71 | 2020-11-01 | 2021-07-30 | 941721.07 | 941721.07 | Non Functional
202106 | 050.54758 | PRP.2734.Brick St Franklin | 485208.58 | 2020-10-01 | 2021-07-30 | 623948.38 | 623948.38 | Non Functional
202106 | 050.54759 | PRP.2734.LP W Ky. Ave | 761744.04 | 2020-10-01 | 2021-09-30 | 864983.51 | 864983.51 | Non Functional
202106 | 050.54764 | PRP.2635.Maple Ave | 28578.84 | 2021-10-01 | 2022-04-30 | 557023.42 | 557023.42 | Non Functional
202106 | 050.55436 | IND.2734.Prosperity Phase 2 | 47517.69 | 2020-11-16 | 2021-09-30 | 308056.34 | 308056.34 | Non Functional
202106 | 050.55584 | RES.2636.HWY136.MN.EXT | 4057.49 | 2021-01-04 | 2021-08-30 | 14255.11 | 14255.11 | Non Functional
202106 | 050.55692 | PRP.2734.High St Alley BG | 312269.61 | 2021-01-22 | 2021-08-30 | 565455.01 | 565455.01 | Non Functional
202106 | 050.55751 | RES.2636.MILTONRD.MN.EXT | -4802.11 | 2021-02-02 | 2021-09-30 | 13748.8 | 13748.8 | Non Functional
202106 | 050.55810 | PRP.2734.BG Centerline 3 | 202449.96 | 2021-01-28 | 2022-09-30 | 985873.4 | 985873.4 | Non Functional
202106 | 050.55844 | COM.2637.Barkley Field Ext | 97119.6 | 2021-07-01 | 2021-09-30 | 347918.61 | 347918.61 | Non Functional
202106 | 050.55917 | LP.2734.McGoodwin.Replc | 8160.95 | 2021-03-01 | 2021-07-30 | 332897.31 | 332897.31 | Non Functional
202106 | 050.55924 | Ground Bed - N 18th St | 23175.87 | 2021-03-01 | 2021-07-30 | 36756.7 | 36756.7 | Non Functional
202106 | 050.55997 | 2636.LP.FREDERICAST. | 843765.58 | 2021-03-01 | 2021-07-30 | 1002731.87 | 1002731.87 | Non Functional
202106 | 050.56097 | PRP.2735.Oakland | 263168.88 | 2021-03-23 | 2021-08-28 | 468885.72 | 468885.72 | Non Functional
202106 | 050.56111 | IND.2734.Proj.SapphireII (AIC) | 52239.21 | 2021-03-19 | 2021-08-31 | 254906.88 | 254906.88 | Non Functional
202106 | 050.56112 | IND.2734.Proj.Sapphire (MEC) | 63422.79 | 2021-03-19 | 2021-08-30 | 267612.55 | 267612.55 | Non Functional
202106 | 050.56133 | 050.2636.Frederica St Services | 170412.07 | 2021-04-01 | 2021-09-30 | 375568.94 | 375568.94 | Non Functional
202106 | 050.56147 | RES.2739.Cherokee Drive | 2468.37 | 2021-03-29 | 2021-07-30 | 4243.98 | 4243.98 | Non Functional
202106 | 050.56151 | LP.2736.17th.St.Replacement | 195666.75 | 2021-04-01 | 2021-09-30 | 706946.09 | 706946.09 | Non Functional
202106 | 050.56170 | 2734.Redbud Sta. Retire | 6012.54 | 2021-03-26 | 2021-07-30 | 182193.03 | 182193.03 | Non Functional
202106 | 050.56209 | RES.2636.MAPLELEAFUTICA.MN.EX | 9898.76 | 2021-06-03 | 2021-07-30 | 22776.06 | 22776.06 | Non Functional
202106 | 050.56236 | COM.2735.Mammoth Cave Ext | 6900.28 | 2021-04-08 | 2021-05-31 | 10026.92 | 10026.92 | Non Functional
202106 | 050.56252 | Shelbyville KY WMR Towers.FY21 | 119788.04 | 2021-05-01 | 2021-10-31 | 183604.61 | 183604.61 | Non Functional
202106 | 050.56258 | 050.2637.Said Rd 6 in Replace | 9673.8 | 2021-05-01 | 2021-09-30 | 64526.22 | 64526.22 | Non Functional
202106 | 050.56260 | PRP.2637.S 3rd St | 23565.78 | 2021-06-30 | 2021-09-30 | 673866.89 | 673866.89 | Non Functional
202106 | 050.56264 | 050.2637.Estes Ln SYS IMP | 9257.14 | 2021-06-01 | 2021-09-30 | 228202.86 | 228202.86 | Non Functional
202106 | 050.56268 | RES.2636.SETTLESRD.MN.EXT | 1106.51 | 2021-06-30 | 2021-06-30 | 6350.18 | 6350.18 | Non Functional
202106 | 050.56279 | RES.2636.HARMONSFERRYRD.MN.EX | 2460.63 | 2021-05-17 | 2021-07-30 | 7072.48 | 7072.48 | Non Functional
202106 | 050.56303 | IND.2735.T.Marzetti - | 22808.98 | 2021-04-21 | 2021-08-31 | 150645.33 | 150645.33 | Non Functional
202106 | 050.56356 | INT.2739.Clear Creek Exposure | 17713.49 | 2021-05-01 | 2021-09-15 | 187325.75 | 187325.75 | Non Functional
202106 | 050.56372 | PRP.2734.Sycamore St | 93322.02 | 2021-05-15 | 2021-09-30 | 835264.31 | 835264.31 | Non Functional
202106 | 050.56437 | PRP.2734.Gayle Way | 13213.26 | 2021-05-20 | 2021-09-30 | 208227.98 | 208227.98 | Non Functional
202106 | 050.56500 | 2739.Rectifiers | 8073.28 | 2021-06-01 | 2021-08-31 | 7190.74 | 7190.74 | Non Functional
202106 | 050.56509 | RES.2637.May-Met Rd Rev Ext | 9.3 | 2021-07-01 | 2021-09-30 | 3746.92 | 3746.92 | Non Functional
202106 | 050.56524 | PRP.2636.Sycamore St | 34808.28 | 2021-06-10 | 2021-09-30 | 490317.21 | 490317.21 | Non Functional
202106 | 050.56555 | PRP.2635.HWY 62 Relocation | 26936.67 | 2021-06-23 | 2021-08-30 | 242620.95 | 242620.95 | Non Functional
202106 | 050.56567 | RES.2636.MONROEAVE.MN.EXT | 19495.58 | 2021-07-05 | 2021-07-12 | 22196.39 | 22196.39 | Non Functional
202106 | 050.56595 | RES.2637.Eagle Landing Ext | -14558.07 | 2021-06-14 | 2021-09-30 | 176638.35 | 176638.35 | Non Functional
202106 | 050.56630 | Pipe Locator - Schmidt | 1699.97 | 2021-06-16 | 2021-09-30 | 1845.72 | 1845.72 | Non Functional
202106 | 050.56689 | INT.2737.Centre College Reloc | -72491.18 | 2021-07-01 | 2021-08-31 | 81305.78 | 81305.78 | Non Functional
202106 | 050.56708 | COM.2638.Grace Park Rev Ext | -6000 | 2021-07-01 | 2021-09-30 | 57701.04 | 57701.04 | Non Functional
202106 | OH.050.17884 | WKG State A&G Overhead | -380.21 | 2006-09-20 | 2020-12-31 | 0 | 0 | Capital State Ovhd